## Sheet1
Activity Name | Activity Code | Phase | Area | Zone | Trade | Color | Start | Finish
Clean out & Pressure Wash | P1 | Building 7000 | Garage |  | Punch | #E36770 | 2025-03-10 | 2025-03-12
Install Doors & Hardware | J0 | Building 7000 | Garage |  | Doors / Hardware | #680E5B | 2025-03-13 | 2025-03-14
Install Snow Chute | G0 | Building 7000 | Garage |  | Gutters/Garages | #305496 | 2025-03-10 | 2025-03-14
Install Metal Railings | SA | Building 7000 | Garage |  | Steel | #A6A6A6 | 2025-03-13 | 2025-03-19
Test & Adjust Elevator | E1 | Building 7000 | Garage |  | Elevators | #38CCC5 | 2025-03-10
Paint Line Striping | 80 | Building 7000 | Garage |  | Paint | #F18D00 | 2025-03-17 | 2025-03-21
Finishes Accessories | A1 | Building 7000 | Garage |  | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-03-24 | 2025-03-26
Install Stair Rails | SB | Building 7000 | Garage |  | Steel | #A6A6A6 | 2025-03-13
Mechanical Rough In | 50 | Building 7000 | Garage |  | HVAC | #DDEBF7 | 2025-03-10 | 2025-03-28
Low Voltage & Fire Alarm Rough in | 60 | Building 7000 | Garage |  | Electrical | #FFF2CC | 2025-03-10 | 2025-03-28
Install Fencing & Gates at Bike Stor | A2 | Building 7000 | Garage |  | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-03-27 | 2025-03-31
Final MEP Inspections | 0I | Building 7000 | Garage |  | Inspections | #C00000 | 2025-03-31 | 2025-04-01
Corrections from LMC Deficiency | O1 | Building 7000 | Garage |  | LMC-Owners | #3E5E60 | 2025-04-01 | 2025-04-14
Corrections from Owner / Architect | O2 | Building 7000 | Garage |  | LMC-Owners | #3E5E60 | 2025-04-15 | 2025-04-24
Final Clean | P2 | Building 1000 | L3 | Units | Punch | #E36770 | 2025-03-10 | 2025-03-11
Final Clean | P2 | Building 1000 | L3 | Corridors | Punch | #E36770 | 2025-03-10 | 2025-03-10
Final Clean | P2 | Building 1000 | L2 | Units | Punch | #E36770 | 2025-03-10 | 2025-03-11
Final Clean | P2 | Building 1000 | L1 | Units | Punch | #E36770 | 2025-03-10 | 2025-03-11
Final Clean | P2 | Building 1000 | L1 | Study | Punch | #E36770 | 2025-03-10 | 2025-03-11
Final Clean | P2 | Building 1000 | L1 | Corridors | Punch | #E36770 | 2025-03-12 | 2025-03-13
Final FP Inspections and Life Safety | 1I | Building 1000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-03-14 | 2025-03-14
State Elevator Testing | EI | Building 1000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-03-10 | 2025-03-14
CofO Inspection Signoff | CI | Building 1000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-03-17 | 2025-03-21
FFE | A1 | Building 1000 | Inspections and Closeout |  | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-05-01 | 2025-05-05
Powder Puff Clean | P3 | Building 1000 | Inspections and Closeout |  | Punch | #E36770 | 2025-05-06 | 2025-05-07
Bldg. Final | FI | Building 2000 | L3 | Corridors | Inspections | #C00000 | 2025-03-10 | 2025-03-11
Final Clean | P2 | Building 2000 | L3 | Corridors | Punch | #E36770 | 2025-03-12 | 2025-03-13
Bldg. Final | FI | Building 2000 | L2 | Corridors | Inspections | #C00000 | 2025-03-12 | 2025-03-12
Final Clean | P2 | Building 2000 | L2 | Corridors | Punch | #E36770 | 2025-03-14 | 2025-03-14
Bldg. Inspection | BI | Building 2000 | L1 | Corridors | Inspections | #C00000 | 2025-03-13 | 2025-03-13
Final Clean | P2 | Building 2000 | L1 | Corridors | Punch | #E36770 | 2025-03-17 | 2025-03-17
1st Coat Paint Walls & Ceilings | 81 | Building 2000 | L1 | Fitness | Paint | #F18D00 | 2025-03-10 | 2025-03-11
Install Flooring | T0 | Building 2000 | L1 | Fitness | Flooring & Tile | #8CE8D4 | 2025-03-12 | 2025-03-14
Install Trim & Accessories | N0 | Building 2000 | L1 | Fitness | Carpentry | #FBC05F | 2025-03-17
Drywall Punch | 40 | Building 2000 | L1 | Fitness | Drywall | #F2C2F9 | 2025-03-21 | 2025-03-24
Final Paint | 82 | Building 2000 | L1 | Fitness | Paint | #F18D00 | 2025-03-25 | 2025-03-28
Install Mirrors | H0 | Building 2000 | L1 | Fitness | Glazing (Mirrors, Blinds) | #B0AAF8 | 2025-03-31 | 2025-04-01
Install Fitness Equipment | A3 | Building 2000 | L1 | Fitness | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-06-23 | 2025-06-27
Final FP Inspections and Life Safety | 1I | Building 2000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-03-14 | 2025-03-17
State Elevator Testing | EI | Building 2000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-03-17 | 2025-03-21
CofO Inspection Signoff | CI | Building 2000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-03-24 | 2025-03-28
FFE | A1 | Building 2000 | Inspections and Closeout |  | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-05-06 | 2025-05-09
Powder Puff Clean | P3 | Building 2000 | Inspections and Closeout |  | Punch | #E36770 | 2025-05-12 | 2025-05-13
Corrections from LMC Deficiency | O1 | Building 4000 | L4 | Units | LMC-Owners | #3E5E60 | 2025-03-10
Bldg. Final | FI | Building 4000 | L4 | Corridors | Inspections | #C00000 | 2025-03-12 | 2025-03-12
Final Clean | P2 | Building 4000 | L4 | Corridors | Punch | #E36770 | 2025-03-13 | 2025-03-17
Final Touch Up Paint | 83 | Building 4000 | L3 | Units | Paint | #F18D00 | 2025-03-17
Corrections from LMC Deficiency | O1 | Building 4000 | L3 | Units | LMC-Owners | #3E5E60 | 2025-03-10 | 2025-03-14
Bldg. Final | FI | Building 4000 | L3 | Units | Inspections | #C00000 | 2025-03-26
Final Clean | P2 | Building 4000 | L3 | Corridors | Punch | #E36770 | 2025-03-27
Final Touch Up Paint | 83 | Building 4000 | L3 | Units | Paint | #F18D00 | 2025-03-17 | 2025-03-20
Corrections from LMC Deficiency | O1 | Building 4000 | L2 | Units | LMC-Owners | #3E5E60 | 2025-03-21 | 2025-03-26
Final Paint | 82 | Building 4000 | L2 | Corridors | Paint | #F18D00 | 2025-03-10 | 2025-03-12
Install Flooring | T0 | Building 4000 | L2 | Corridors | Flooring & Tile | #8CE8D4 | 2025-03-10 | 2025-03-12
Bldg. Final | FI | Building 4000 | L2 | Corridors | Inspections | #C00000 | 2025-03-27 | 2025-03-27
Final Clean | P2 | Building 4000 | L2 | Corridors | Punch | #E36770 | 2025-03-28 | 2025-03-28
Tape Finish Drywall | 41 | Building 4000 | L1 | Leasing / Lobby | Drywall | #F2C2F9 | 2025-03-10 | 2025-03-15
1st Coat Paint Walls & Ceilings | 81 | Building 4000 | L1 | Leasing / Lobby | Paint | #F18D00 | 2025-03-17 | 2025-03-18
Install Bike Rack Equipment | A4 | Building 4000 | L1 | Leasing / Lobby | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-03-19 | 2025-03-20
1st Trim | M1 | Building 4000 | L1 | Leasing / Lobby | MEPs | #FF7C80 | 2025-03-19 | 2025-03-20
Install Water Fountain | LA | Building 4000 | L1 | Leasing / Lobby | Courtyards/Amenities | #A9D08E | 2025-03-21 | 2025-03-21
Trim Out Mechanical Devices | 51 | Building 4000 | L1 | Leasing / Lobby | HVAC | #DDEBF7 | 2025-03-21 | 2025-03-21
Install Storefront Doors | H1 | Building 4000 | L1 | Leasing / Lobby | Glazing (Mirrors, Blinds) | #B0AAF8 | 2025-03-21 | 2025-03-24
Install Doors & Hardware | J0 | Building 4000 | L1 | Leasing / Lobby | Doors / Hardware | #680E5B | 2025-03-25 | 2025-03-26
Install Interior Storefront | H2 | Building 4000 | L1 | Leasing / Lobby | Glazing (Mirrors, Blinds) | #B0AAF8 | 2025-03-21 | 2025-03-27
Install Flooring | T0 | Building 4000 | L1 | Leasing / Lobby | Flooring & Tile | #8CE8D4 | 2025-03-28 | 2025-04-01
Install Trim & Accessories | N0 | Building 4000 | L1 | Leasing / Lobby | Carpentry | #FBC05F | 2025-04-02 | 2025-04-03
Trim Out Fire Sprinkler | 20 | Building 4000 | L1 | Leasing / Lobby | Fire Protection | #FF7057 | 2025-04-02 | 2025-04-04
Drywall Punch | 40 | Building 4000 | L1 | Leasing / Lobby | Drywall | #F2C2F9 | 2025-04-08 | 2025-04-09
Final Paint | 82 | Building 4000 | L1 | Leasing / Lobby | Paint | #F18D00 | 2025-04-10 | 2025-04-14
Install Mirrors | H0 | Building 4000 | L1 | Leasing / Lobby | Glazing (Mirrors, Blinds) | #B0AAF8 | 2025-04-15 | 2025-04-15
Tape Finish Drywall | 41 | Building 4000 | L1 | Clubhouse | Drywall | #F2C2F9 | 2025-03-10 | 2025-03-17
Rough Clean | P1 | Building 4000 | L1 | Clubhouse | Punch | #E36770 | 2025-03-19 | 2025-03-19
Install Prehung Doors | J1 | Building 4000 | L1 | Clubhouse | Doors/Hardware | #680E5B | 2025-03-18 | 2025-03-19
1st Trim | M1 | Building 4000 | L1 | Clubhouse | MEPs | #FF7C80 | 2025-03-18 | 2025-03-20
1st Coat Paint Walls & Ceilings | 81 | Building 4000 | L1 | Clubhouse | Paint | #F18D00 | 2025-03-19 | 2025-03-21
Trim-out Electrical Devices | 61 | Building 4000 | L1 | Clubhouse | Electrical | #FFF2CC | 2025-03-24 | 2025-03-24
Install Interior Storefront | H2 | Building 4000 | L1 | Clubhouse | Glazing (Mirrors, Blinds) | #B0AAF8 | 2025-03-24 | 2025-03-25
Install Light Fixtures & Ceiling Fan | 62 | Building 4000 | L1 | Clubhouse | Electrical | #FFF2CC | 2025-03-25 | 2025-03-26
Trim-out Fire Alarm Devices | 63 | Building 4000 | L1 | Clubhouse | Electrical | #FFF2CC | 2025-03-27 | 2025-03-27
Install Appliances | A5 | Building 4000 | L1 | Clubhouse | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-03-26 | 2025-03-27
Install Casework | K0 | Building 4000 | L1 | Clubhouse | Cabinets & Tops | #D8A979 | 2025-03-24 | 2025-03-27
Trim Out Mechanical Devices | 51 | Building 4000 | L1 | Clubhouse | HVAC | #DDEBF7 | 2025-03-28 | 2025-03-28
Trim-out Low Voltage Devices | 64 | Building 4000 | L1 | Clubhouse | Electrical | #FFF2CC | 2025-03-28 | 2025-03-28
Final Mechanical Inspection | 5I | Building 4000 | L1 | Clubhouse | Inspections | #C00000 | 2025-03-31 | 2025-03-31
Install Countertop Sink | K1 | Building 4000 | L1 | Clubhouse | Cabinets & Tops | #D8A979 | 2025-03-28 | 2025-04-01
Drywall Punch | 40 | Building 4000 | L1 | Clubhouse | Drywall | #F2C2F9 | 2025-04-01 | 2025-04-02
Install Quartz Countertops | K2 | Building 4000 | L1 | Clubhouse | Cabinets & Tops | #D8A979 | 2025-04-02 | 2025-04-02
Trim Out Fire Sprinkler | 20 | Building 4000 | L1 | Clubhouse | Fire Protection | #FF7057 | 2025-03-28 | 2025-04-03
Install Plumbing Fixtures | 30 | Building 4000 | L1 | Clubhouse | Plumbing | #E2EFDA | 2025-04-01 | 2025-04-03
Install Custom Light fixtures | 65 | Building 4000 | L1 | Clubhouse | Electrical | #FFF2CC | 2025-04-03 | 2025-04-03
Final Plumbing Inspection | 3I | Building 4000 | L1 | Clubhouse | Inspections | #C00000 | 2025-04-04 | 2025-04-04
Install Banquette's in Lobby | A6 | Building 4000 | L1 | Clubhouse | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-04-03 | 2025-04-04
Bldg. Inspection | BI | Building 4000 | L1 | Clubhouse | Inspections | #C00000 | 2025-04-07 | 2025-04-07
Install Flooring | T0 | Building 4000 | L1 | Clubhouse | Flooring & Tile | #8CE8D4 | 2025-04-04 | 2025-04-17
Final Paint | 82 | Building 4000 | L1 | Clubhouse | Paint | #F18D00 | 2025-04-18 | 2025-04-23
Install Flooring | T0 | Building 4000 | L1 | Clubhouse | Flooring & Tile | #8CE8D4 | 2025-04-23 | 2025-04-25
Install Carpet Tile | T1 | Building 4000 | L1 | Clubhouse | Flooring & Tile | #8CE8D4 | 2025-04-24 | 2025-04-25
Install Appliances in Breakroom | A7 | Building 4000 | L1 | Clubhouse | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-04-28 | 2025-04-28
2nd Paint | 84 | Building 4000 | L1 | Clubhouse | Paint | #F18D00 | 2025-04-25 | 2025-04-29
Install Doors & Hardware | J0 | Building 4000 | L1 | Clubhouse | Doors / Hardware | #680E5B | 2025-04-30 | 2025-05-01
Install Window Treatments | W0 | Building 4000 | L1 | Clubhouse | Windows | #D9E1F2 | 2025-04-30 | 2025-05-01
Final Clean | P2 | Building 4000 | L1 | Clubhouse | Punch | #E36770 | 2025-05-02 | 2025-05-05
Install Floor Tile in Restrooms | T2 | Building 4000 | L1 | Clubhouse | Flooring & Tile | #8CE8D4 | 2025-03-24
Install Wall Tile | T3 | Building 4000 | L1 | Clubhouse | Flooring & Tile | #8CE8D4 | 2025-03-28 | 2025-04-02
Install Countertops | K2 | Building 4000 | L1 | Clubhouse | Cabinets & Tops | #D8A979 | 2025-04-03 | 2025-04-04
Install Toilet Partitions | A8 | Building 4000 | L1 | Clubhouse | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-04-07 | 2025-04-08
Install Toilets | 31 | Building 4000 | L1 | Clubhouse | Plumbing | #E2EFDA | 2025-04-09 | 2025-04-10
Install Sinks Fixtures | 32 | Building 4000 | L1 | Clubhouse | Plumbing | #E2EFDA | 2025-04-11 | 2025-04-14
Install Bathroom Accessories | 33 | Building 4000 | L1 | Clubhouse | Plumbing | #E2EFDA | 2025-04-15 | 2025-04-16
Install Mirrors | H0 | Building 4000 | L1 | Clubhouse | Glazing (Mirrors, Blinds) | #B0AAF8 | 2025-04-24 | 2025-04-24
Install Signage | V0 | Building 4000 | L1 | Corridors | Screens/Accesories | #9195AD | 2025-03-18 | 2025-03-18
Final Clean | P2 | Building 4000 | L1 | Corridors | Punch | #E36770 | 2025-03-31 | 2025-03-31
Final Paint | 82 | Building 4000 | L1 | Corridors | Paint | #F18D00 | 2025-04-01 | 2025-04-03
Bldg. Final | FI | Building 4000 | L1 | Corridors | Inspections | #C00000 | 2025-04-04
State Elevator Testing | EI | Building 4000 | Inspections and Closeout | Units | Inspections | #C00000 | 2025-03-20 | 2025-03-26
Final FP Inspections and Life Safety | 1I | Building 4000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-04-07 | 2025-04-08
CofO Inspection Signoff | CI | Building 4000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-04-21 | 2025-04-25
FFE | A1 | Building 4000 | Inspections and Closeout |  | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-05-12 | 2025-05-15
Powder Puff Clean | P3 | Building 4000 | Inspections and Closeout |  | Punch | #E36770 | 2025-05-16 | 2025-05-20
Exterior Trim Accessories | X5 | Building 5000 | Façade |  | Exteriors Finishes 1 | #375623 | 2024-11-04
Install Balcony Rails | SB | Building 5000 | Façade |  | Steel | #A6A6A6 | 2024-11-18
AHU Install, HVAC Trim Out | 52 | Building 5000 | L4 | Units | HVAC | #DDEBF7 | 2025-01-06
Rough Clean | P1 | Building 5000 | L4 | Units | Punch | #E36770 | 2025-03-10 | 2025-03-11
Meter Inspections HC AHU Startup | 53 | Building 5000 | L4 | Units | HVAC | #DDEBF7 | 2025-03-10 | 2025-03-11
Install WH, Toilets & Plumbing Fixtures | 34 | Building 5000 | L4 | Units | Plumbing | #E2EFDA | 2025-03-10 | 2025-03-13
Corrections from LMC Deficiency | O1 | Building 5000 | L4 | Units | LMC-Owners | #3E5E60 | 2025-03-10 | 2025-03-14
2nd Trim | M3 | Building 5000 | L4 | Units | MEPs | #FF7C80 | 2025-03-14 | 2025-03-17
Final Touch Up Paint | 83 | Building 5000 | L4 | Units | Paint | #F18D00 | 2025-03-17 | 2025-03-20
Final MEP | M2 | Building 5000 | L4 | Units | MEPs | #FF7C80 | 2025-03-21 | 2025-03-26
Final Clean | P2 | Building 5000 | L4 | Units | Punch | #E36770 | 2025-03-27 | 2025-03-28
Trim-out MEP | M4 | Building 5000 | L4 | Corridors | MEPs | #FF7C80 | 2025-03-10 | 2025-03-10
Install Signage | V0 | Building 5000 | L4 | Corridors | Screens/Accesories | #9195AD | 2025-03-10 | 2025-03-10
Final Clean | P2 | Building 5000 | L4 | Corridors | Punch | #E36770 | 2025-03-11 | 2025-03-11
1st Coat Paint Walls & Ceilings | 81 | Building 5000 | L4 | Corridors | Paint | #F18D00 | 2025-03-10 | 2025-03-12
Install Fire Extinguisher Cabinet | V1 | Building 5000 | L4 | Corridors | Screens/Accesories | #9195AD | 2025-03-13 | 2025-03-13
Final Paint | 82 | Building 5000 | L4 | Corridors | Paint | #F18D00 | 2025-03-12 | 2025-03-14
Bldg. Final | FI | Building 5000 | L4 | Corridors | Inspections | #C00000 | 2025-03-17 | 2025-03-17
Install Flooring | T0 | Building 5000 | L4 | Corridors | Flooring & Tile | #8CE8D4 | 2025-03-17 | 2025-03-19
AHU Install, HVAC Trim Out | 52 | Building 5000 | L3 | Units | HVAC | #DDEBF7 | 2024-12-09
Rough Clean | P1 | Building 5000 | L3 | Units | Punch | #E36770 | 2025-03-10 | 2025-03-11
Meter Inspections HC AHU Startup | 53 | Building 5000 | L3 | Units | HVAC | #DDEBF7 | 2025-03-10 | 2025-03-11
Hot check | 35 | Building 5000 | L3 | Units | Plumbing | #E2EFDA | 2025-03-12 | 2025-03-12
Install WH, Toilets & Plumbing Fixtures | 34 | Building 5000 | L3 | Units | Plumbing | #E2EFDA | 2025-03-10 | 2025-03-13
Install Door & Hardware | J2 | Building 5000 | L3 | Units | Doors/Hardware | #680E5B | 2025-03-14 | 2025-03-17
Corrections from LMC Deficiency | O1 | Building 5000 | L3 | Units | LMC-Owners | #3E5E60 | 2025-03-18 | 2025-03-24
Final Touch Up Paint | 83 | Building 5000 | L3 | Units | Paint | #F18D00 | 2025-03-25 | 2025-03-28
Final MEP Inspections | 0I | Building 5000 | L3 | Units | Inspections | #C00000 | 2025-03-31 | 2025-04-03
Final Paint | 82 | Building 5000 | L3 | Corridors | Paint | #F18D00 | 2025-03-27 | 2025-03-31
Bldg. Final | FI | Building 5000 | L3 | Corridors | Inspections | #C00000 | 2025-04-01 | 2025-04-01
AHU Install, HVAC Trim Out | 52 | Building 5000 | L2 | Corridors | HVAC | #DDEBF7 | 2024-12-11
Meter Inspections HC AHU Startup | 53 | Building 5000 | L2 | Corridors | HVAC | #DDEBF7 | 2025-03-10 | 2025-03-11
Rough Clean | P1 | Building 5000 | L2 | Units | Punch | #E36770 | 2025-03-10 | 2025-03-11
Install WH, Toilets & Plumbing Fixtures | 34 | Building 5000 | L2 | Units | Plumbing | #E2EFDA | 2025-03-10 | 2025-03-13
2nd Trim | M3 | Building 5000 | L2 | Units | MEPs | #FF7C80 | 2025-03-14 | 2025-03-14
Install Appliances | A5 | Building 5000 | L2 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-03-14 | 2025-03-17
Corrections from LMC Deficiency | O1 | Building 5000 | L2 | Units | LMC-Owners | #3E5E60 | 2025-03-18 | 2025-03-24
Final Touch Up Paint | 83 | Building 5000 | L2 | Units | Paint | #F18D00 | 2025-03-25 | 2025-03-28
Final MEP Inspections | 0I | Building 5000 | L2 | Units | Inspections | #C00000 | 2025-03-31 | 2025-04-03
Final Clean | P2 | Building 5000 | L2 | Units | Punch | #E36770 | 2025-04-04 | 2025-04-07
Install Flooring | T0 | Building 5000 | L2 | Corridors | Flooring & Tile | #8CE8D4 | 2025-03-25 | 2025-03-27
Install Signage | V0 | Building 5000 | L2 | Corridors | Screens/Accesories | #9195AD | 2025-03-28 | 2025-03-28
Final Clean | P2 | Building 5000 | L2 | Corridors | Punch | #E36770 | 2025-03-31 | 2025-03-31
Final Paint | 82 | Building 5000 | L2 | Corridors | Paint | #F18D00 | 2025-04-01 | 2025-04-03
Bldg. Final | FI | Building 5000 | L2 | Corridors | Inspections | #C00000 | 2025-04-04 | 2025-04-04
AHU Install, HVAC Trim Out | 52 | Building 5000 | L1 | Corridors | HVAC | #DDEBF7 | 2025-03-10
Rough Clean | P1 | Building 5000 | L1 | Units | Punch | #E36770 | 2025-03-10 | 2025-03-11
Install WH, Toilets & Plumbing Fixtures | 34 | Building 5000 | L1 | Units | Plumbing | #E2EFDA | 2025-03-10 | 2025-03-13
Drywall Punch | 40 | Building 5000 | L1 | Units | Drywall | #F2C2F9 | 2025-03-10 | 2025-03-13
2nd Trim | M3 | Building 5000 | L1 | Units | MEPs | #FF7C80 | 2025-03-14 | 2025-03-17
Meter Inspections HC AHU Startup | 53 | Building 5000 | L1 | Units | HVAC | #DDEBF7 | 2025-03-14 | 2025-03-17
Install Appliances | A5 | Building 5000 | L1 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-03-18 | 2025-03-19
Corrections from LMC Deficiency | O1 | Building 5000 | L1 | Units | LMC-Owners | #3E5E60 | 2025-03-20 | 2025-03-26
Final Touch Up Paint | 83 | Building 5000 | L1 | Units | Paint | #F18D00 | 2025-03-27 | 2025-04-01
Final MEP Inspections | 0I | Building 5000 | L1 | Units | Inspections | #C00000 | 2025-04-02 | 2025-04-07
Bldg. Final | FI | Building 5000 | L1 | Units | Inspections | #C00000 | 2025-04-08 | 2025-04-09
Install Flooring | T0 | Building 5000 | L1 | Corridors | Flooring & Tile | #8CE8D4 | 2025-03-28 | 2025-04-01
Install Signage | V0 | Building 5000 | L1 | Corridors | Screens/Accesories | #9195AD | 2025-04-02 | 2025-04-02
Final Clean | P2 | Building 5000 | L1 | Corridors | Punch | #E36770 | 2025-04-03 | 2025-04-03
Final Paint | 82 | Building 5000 | L1 | Corridors | Paint | #F18D00 | 2025-04-04 | 2025-04-08
Seal Concrete Flooring | CA | Building 5000 | L1 | Bike Rooms | Concrete | #DBDBDB | 2025-03-10 | 2025-03-14
Install Bike Rack Equipment | A4 | Building 5000 | L1 | Bike Rooms | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-03-17 | 2025-03-18
Install Fire Alarm Devices | 21 | Building 5000 | L1 | Commercial / Retail | Fire Protection | #FF7057 | 2025-03-10
Install Storefront Doors | H1 | Building 5000 | L1 | Commercial / Retail | Glazing (Mirrors, Blinds) | #B0AAF8 | 2025-03-10 | 2025-03-11
Install Doors & Hardware | J0 | Building 5000 | L1 | Commercial / Retail | Doors / Hardware | #680E5B | 2025-03-12 | 2025-03-13
Bldg. Inspection | BI | Building 5000 | L1 | Commercial / Retail | Inspections | #C00000 | 2025-03-14 | 2025-03-14
Install Custom Light fixtures | 65 | Building 5000 | L1 | Commercial Trash Room | Electrical | #FFF2CC | 2025-03-13 | 2025-03-14
Final Mechanical Inspection | 5I | Building 5000 | L1 | Commercial Trash Room | Inspections | #C00000 | 2025-03-14 | 2025-03-14
Install Floor Drain | 36 | Building 5000 | L1 | Commercial Trash Room | Plumbing | #E2EFDA | 2025-03-13 | 2025-03-17
Trim Out Fire Sprinkler | 20 | Building 5000 | L1 | Commercial Trash Room | Fire Protection | #FF7057 | 2025-03-13 | 2025-03-19
Trim-out Low Voltage Devices | 64 | Building 5000 | L1 | Commercial Trash Room | Electrical | #FFF2CC | 2025-03-19 | 2025-03-19
Rough Clean | P1 | Building 5000 | L1 | Commercial Trash Room | Punch | #E36770 | 2025-03-20 | 2025-03-20
Install Trash Compactor | A9 | Building 5000 | L1 | Commercial Trash Room | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-03-21 | 2025-03-27
Install Trash Compactor | A9 | Building 5000 | L1 | Commercial Trash Room | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-03-28 | 2025-03-31
Install Doors & Hardware | J0 | Building 5000 | L1 | Commercial Trash Room | Doors / Hardware | #680E5B | 2025-04-01 | 2025-04-02
Final Paint | 82 | Building 5000 | L1 | Commercial Trash Room | Paint | #F18D00 | 2025-04-03 | 2025-04-08
Final Clean | P2 | Building 5000 | L1 | Commercial Trash Room | Punch | #E36770 | 2025-04-09 | 2025-04-10
Insulate Ceiling | 70 | Building 5000 | L1 | Electric Rooms | Insulation | #868CC4 | 2025-03-10 | 2025-03-10
Inspection of Ceiling | DI | Building 5000 | L1 | Electric Rooms | Inspections | #C00000 | 2025-03-11 | 2025-03-11
Close Ceiling | R0 | Building 5000 | L1 | Electric Rooms | Roofing | #385623 | 2025-03-12 | 2025-03-12
Final Inspection | FI | Building 5000 | L1 | Electric Rooms | Inspections | #C00000 | 2025-03-13 | 2025-03-13
Set Transformer | 66 | Building 5000 | L1 | Electric Rooms | Electrical | #FFF2CC | 2025-03-10 | 2025-03-28
Set meters | 67 | Building 5000 | L1 | Electric Rooms | Electrical | #FFF2CC | 2025-03-31 | 2025-04-04
Test & Adjust Elevator | E1 | Building 5000 | L1 |  | Elevators | #38CCC5 | 2025-04-08 | 2025-04-17
State Elevator Testing | EI | Building 5000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-04-18 | 2025-04-24
CofO Inspection Signoff | CI | Building 5000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-04-25 | 2025-05-01
FFE | A1 | Building 5000 | Inspections and Closeout |  | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-06-05 | 2025-06-10
Powder Puff Clean | P3 | Building 5000 | Inspections and Closeout |  | Punch | #E36770 | 2025-06-11 | 2025-06-13
Exterior Trim Accessories | X5 | Building 6000 | Façade |  | Exteriors Finishes 1 | #375623 | 2025-03-10 | 2025-03-19
Install Balcony Rails | SB | Building 6000 | Façade |  | Steel | #A6A6A6 | 2025-04-02 | 2025-04-09
Rough Clean | P1 | Building 6000 | L4 | Units | Punch | #E36770 | 2025-03-10
Install WH, Toilets & Plumbing Fixtures | 34 | Building 6000 | L4 | Units | Plumbing | #E2EFDA | 2025-03-06
2nd Trim | M3 | Building 6000 | L4 | Units | MEPs | #FF7C80 | 2025-03-17 | 2025-03-18
Meter Inspections HC AHU Startup | 53 | Building 6000 | L4 | Units | HVAC | #DDEBF7 | 2025-03-25 | 2025-03-26
Install Appliances | A5 | Building 6000 | L4 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-03-27 | 2025-03-28
Corrections from LMC Deficiency | O1 | Building 6000 | L4 | Units | LMC-Owners | #3E5E60 | 2025-03-31
Final Touch Up Paint | 83 | Building 6000 | L4 | Units | Paint | #F18D00 | 2025-04-07 | 2025-04-10
Final MEP Inspections | 0I | Building 6000 | L4 | Units | Inspections | #C00000 | 2025-04-11 | 2025-04-16
Final Clean | P2 | Building 6000 | L4 | Units | Punch | #E36770 | 2025-04-17 | 2025-04-18
Final Clean | P2 | Building 6000 | L4 | Corridors | Punch | #E36770 | 2025-03-11 | 2025-03-11
Trim-out MEP | M4 | Building 6000 | L4 | Corridors | MEPs | #FF7C80 | 2025-03-10 | 2025-03-14
Final Paint | 82 | Building 6000 | L4 | Corridors | Paint | #F18D00 | 2025-03-12 | 2025-03-14
Bldg. Final | FI | Building 6000 | L4 | Corridors | Inspections | #C00000 | 2025-03-17 | 2025-03-17
1st Coat Paint Walls & Ceilings | 81 | Building 6000 | L4 | Corridors | Paint | #F18D00 | 2025-03-17 | 2025-03-19
Install Flooring | T0 | Building 6000 | L4 | Corridors | Flooring & Tile | #8CE8D4 | 2025-03-17 | 2025-03-19
Install Fire Extinguisher Cabinet | V1 | Building 6000 | L4 | Corridors | Screens/Accesories | #9195AD | 2025-03-20 | 2025-03-20
Rough Clean | P1 | Building 6000 | L4 | Corridors | Punch | #E36770 | 2025-03-21 | 2025-03-21
Stub-in Electrical | 67 | Building 6000 | L4 | Corridors | Electrical | #FFF2CC | 2025-03-24 | 2025-03-24
Trim Out Mechanical Devices | 51 | Building 6000 | L4 | Corridors | HVAC | #DDEBF7 | 2025-03-25 | 2025-03-25
AHU Install, HVAC Trim Out | 52 | Building 6000 | L3 | Units | HVAC | #DDEBF7 | 2025-01-08
Drywall Punch | 40 | Building 6000 | L3 | Units | Drywall | #F2C2F9 | 2025-03-10 | 2025-03-13
Meter Inspections HC AHU Startup | 53 | Building 6000 | L3 | Units | HVAC | #DDEBF7 | 2025-03-14 | 2025-03-17
Install Cabinets & Countertops | K3 | Building 6000 | L3 | Units | Cabinets & Tops | #D8A979 | 2025-03-10 | 2025-03-17
Rough Clean | P1 | Building 6000 | L3 | Units | Punch | #E36770 | 2025-03-18 | 2025-03-19
Install WH, Toilets & Plumbing Fixtures | 34 | Building 6000 | L3 | Units | Plumbing | #E2EFDA | 2025-03-17 | 2025-03-20
2nd Trim | M3 | Building 6000 | L3 | Units | MEPs | #FF7C80 | 2025-03-21 | 2025-03-24
Install Appliances | A5 | Building 6000 | L3 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-03-25 | 2025-03-26
Corrections from LMC Deficiency | O1 | Building 6000 | L3 | Units | LMC-Owners | #3E5E60 | 2025-03-27 | 2025-04-02
Final MEP Inspections | 0I | Building 6000 | L3 | Units | Inspections | #C00000 | 2025-04-09 | 2025-04-14
Bldg. Final | FI | Building 6000 | L3 | Corridors | Inspections | #C00000 | 2025-03-10 | 2025-03-14
1st Coat Paint Walls & Ceilings | 81 | Building 6000 | L3 | Corridors | Paint | #F18D00 | 2025-03-17 | 2025-03-19
Install Fire Extinguisher Cabinet | V1 | Building 6000 | L3 | Corridors | Screens/Accesories | #9195AD | 2025-03-20 | 2025-03-20
Install Flooring | T0 | Building 6000 | L3 | Corridors | Flooring & Tile | #8CE8D4 | 2025-03-21 | 2025-03-25
Install Signage | V0 | Building 6000 | L3 | Corridors | Screens/Accesories | #9195AD | 2025-03-26 | 2025-03-26
Final Clean | P2 | Building 6000 | L3 | Corridors | Punch | #E36770 | 2025-03-27 | 2025-03-27
Final Paint | 82 | Building 6000 | L3 | Corridors | Paint | #F18D00 | 2025-03-28 | 2025-04-01
Bldg. Final | FI | Building 6000 | L3 | Corridors | Inspections | #C00000 | 2025-04-02 | 2025-04-02
Install Cabinets & Countertops | K3 | Building 6000 | L2 | Units | Cabinets & Tops | #D8A979 | 2025-03-10 | 2025-03-17
2nd Paint | 84 | Building 6000 | L2 | Units | Paint | #F18D00 | 2025-03-20 | 2025-03-24
Install Flooring | T0 | Building 6000 | L2 | Units | Flooring & Tile | #8CE8D4 | 2025-03-25 | 2025-03-31
Install WH, Toilets & Plumbing Fixtures | 34 | Building 6000 | L2 | Units | Plumbing | #E2EFDA | 2025-04-01 | 2025-04-04
2nd Trim | M3 | Building 6000 | L2 | Units | MEPs | #FF7C80 | 2025-04-07 | 2025-04-08
Drywall Punch | 40 | Building 6000 | L2 | Units | Drywall | #F2C2F9 | 2025-04-09
Meter Inspections HC AHU Startup | 53 | Building 6000 | L2 | Units | HVAC | #DDEBF7 | 2025-04-15
Install Appliances | A5 | Building 6000 | L2 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-04-17
Corrections from LMC Deficiency | O1 | Building 6000 | L2 | Units | LMC-Owners | #3E5E60 | 2025-04-21
Final Touch Up Paint | 83 | Building 6000 | L2 | Units | Paint | #F18D00 | 2025-04-28 | 2025-05-01
Final MEP Inspections | 0I | Building 6000 | L2 | Units | Inspections | #C00000 | 2025-05-02 | 2025-05-07
Final Clean | P2 | Building 6000 | L2 | Corridors | Punch | #E36770 | 2025-03-17 | 2025-03-17
Final Paint | 82 | Building 6000 | L2 | Corridors | Paint | #F18D00 | 2025-03-18 | 2025-03-20
Bldg. Final | FI | Building 6000 | L2 | Corridors | Inspections | #C00000 | 2025-03-21 | 2025-03-21
1st Trim | M1 | Building 6000 | L1 | Units | MEPs | #FF7C80 | 2025-03-10 | 2025-03-14
Install Cabinets & Countertops | K3 | Building 6000 | L1 | Units | Cabinets & Tops | #D8A979 | 2025-03-17 | 2025-03-24
Rough Clean | P1 | Building 6000 | L1 | Units | Punch | #E36770 | 2025-03-25 | 2025-03-26
2nd Paint | 84 | Building 6000 | L1 | Units | Paint | #F18D00 | 2025-03-27 | 2025-03-31
Install Flooring | T0 | Building 6000 | L1 | Units | Flooring & Tile | #8CE8D4 | 2025-04-01 | 2025-04-07
Install WH, Toilets & Plumbing Fixtures | 34 | Building 6000 | L1 | Units | Plumbing | #E2EFDA | 2025-04-08 | 2025-04-11
2nd Trim | M3 | Building 6000 | L1 | Units | MEPs | #FF7C80 | 2025-04-14 | 2025-04-15
Drywall Punch | 40 | Building 6000 | L1 | Units | Drywall | #F2C2F9 | 2025-04-16 | 2025-04-21
Meter Inspections HC AHU Startup | 53 | Building 6000 | L1 | Units | HVAC | #DDEBF7 | 2025-04-22 | 2025-04-23
Install Appliances | A5 | Building 6000 | L1 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-04-24 | 2025-04-25
Corrections from LMC Deficiency | O1 | Building 6000 | L1 | Units | LMC-Owners | #3E5E60 | 2025-04-28 | 2025-05-02
Final Touch Up Paint | 83 | Building 6000 | L1 | Units | Paint | #F18D00 | 2025-05-05 | 2025-05-08
Final MEP Inspections | 0I | Building 6000 | L1 | Units | Inspections | #C00000 | 2025-05-09 | 2025-05-14
Final Clean | P2 | Building 6000 | L1 | Units | Punch | #E36770 | 2025-05-15 | 2025-05-16
Final Paint | 82 | Building 6000 | L1 | Corridors | Paint | #F18D00 | 2025-03-10 | 2025-03-12
Tape Finish Drywall | 41 | Building 6000 | L1 | Corridors | Drywall | #F2C2F9 | 2025-03-10 | 2025-03-14
Trim-out MEP | M4 | Building 6000 | L1 | Corridors | MEPs | #FF7C80 | 2025-03-17 | 2025-03-21
Rough Clean | P1 | Building 6000 | L1 | Corridors | Punch | #E36770 | 2025-03-25 | 2025-03-25
1st Coat Paint Walls & Ceilings | 81 | Building 6000 | L1 | Corridors | Paint | #F18D00 | 2025-03-24 | 2025-03-26
Install Fire Extinguisher Cabinet | V1 | Building 6000 | L1 | Corridors | Screens/Accesories | #9195AD | 2025-03-27 | 2025-03-27
Install Signage | V0 | Building 6000 | L1 | Corridors | Screens/Accesories | #9195AD | 2025-04-02 | 2025-04-02
Final Clean | P2 | Building 6000 | L1 | Corridors | Punch | #E36770 | 2025-04-03
Bldg. Final | FI | Building 6000 | L1 | Corridors | Inspections | #C00000 | 2025-04-04 | 2025-04-04
Install Fire Alarm Devices | 21 | Building 6000 | L1 | BOH / Retail | Fire Protection | #FF7057 | 2025-03-10 | 2025-03-10
Bldg. Inspection | BI | Building 6000 | L1 | BOH / Retail | Inspections | #C00000 | 2025-03-10 | 2025-03-10
Install Doors & Hardware | J0 | Building 6000 | L1 | BOH / Retail | Doors / Hardware | #680E5B | 2025-03-10 | 2025-03-11
Final Clean | P2 | Building 6000 | L1 | BOH / Retail | Punch | #E36770 | 2025-03-12 | 2025-03-13
Prime 1st Coat Paint | 85 | Building 6000 | L1 | BOH / Retail | Paint | #F18D00 | 2025-03-10 | 2025-03-12
Trim Out Mechanical Devices | 51 | Building 6000 | L1 | BOH / Retail | HVAC | #DDEBF7 | 2025-03-13 | 2025-03-13
Install Custom Light fixtures | 65 | Building 6000 | L1 | BOH / Retail | Electrical | #FFF2CC | 2025-03-13 | 2025-03-14
Trim-out Electrical Devices | 61 | Building 6000 | L1 | BOH / Retail | Electrical | #FFF2CC | 2025-03-17 | 2025-03-17
Trim-out Fire Alarm Devices | 63 | Building 6000 | L1 | BOH / Retail | Electrical | #FFF2CC | 2025-03-18 | 2025-03-18
Trim-out Low Voltage Devices | 64 | Building 6000 | L1 | BOH / Retail | Electrical | #FFF2CC | 2025-03-19 | 2025-03-19
Trim Out Fire Sprinkler | 20 | Building 6000 | L1 | BOH / Retail | Fire Protection | #FF7057 | 2025-03-13 | 2025-03-19
Rough Clean | P1 | Building 6000 | L1 | BOH / Retail | Punch | #E36770 | 2025-03-20 | 2025-03-20
Install Trash Compactor | A9 | Building 6000 | L1 | BOH / Retail | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-03-21 | 2025-03-27
Install Doors & Hardware | J0 | Building 6000 | L1 | BOH / Retail | Doors / Hardware | #680E5B | 2025-04-01 | 2025-04-02
Final Paint | 82 | Building 6000 | L1 | BOH / Retail | Paint | #F18D00 | 2025-04-03 | 2025-04-08
Bldg. Inspection | BI | Building 6000 | L1 | BOH / Retail | Inspections | #C00000 | 2025-04-09 | 2025-04-09
Final Clean | P2 | Building 6000 | L1 | BOH / Retail | Punch | #E36770 | 2025-04-10 | 2025-04-11
Install Bike Rack Equipment | A4 | Building 6000 | L1 | Bike Rooms | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-03-21 | 2025-03-24
Insulate Ceiling | 70 | Building 6000 | L1 | Electric Rooms | Insulation | #868CC4 | 2025-03-10
Inspection of Ceiling | DI | Building 6000 | L1 | Electric Rooms | Inspections | #C00000 | 2025-03-11 | 2025-03-11
Close Ceiling | R0 | Building 6000 | L1 | Electric Rooms | Roofing | #385623 | 2025-03-12 | 2025-03-12
Set Transformer | 66 | Building 6000 | L1 | Electric Rooms | Electrical | #FFF2CC | 2025-03-10 | 2025-03-28
Energize | 68 | Building 6000 | L1 | Electric Rooms | Electrical | #FFF2CC | 2025-04-07 | 2025-04-07
Final FP Inspections and Life Safety | 1I | Building 6000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-03-10 | 2025-03-11
State Elevator Testing | EI | Building 6000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-04-18 | 2025-04-24
CofO Inspection Signoff | CI | Building 6000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-04-25 | 2025-05-01
FFE | A1 | Building 6000 | Inspections and Closeout |  | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-06-02 | 2025-06-04
Powder Puff Clean | P3 | Building 6000 | Inspections and Closeout |  | Punch | #E36770 | 2025-06-05 | 2025-06-06
Install Lap Siding | X1 | Building 7000 - West | Façade |  | Exteriors Envelope | #CCCC00 | 2024-10-28
Install Panel Batten | X2 | Building 7000 - West | Façade |  | Exteriors Envelope | #548235 | 2024-11-18
Exterior Trim Accessories | X5 | Building 7000 - West | Façade |  | Exteriors Finishes 1 | #375623 | 2025-03-24 | 2025-04-04
Install Balcony Rails | SB | Building 7000 - West | Façade |  | Steel | #A6A6A6 | 2025-04-10 | 2025-04-17
Finish Balconies | X3 | Building 7000 - West | Façade |  | Exteriors Envelope | #A9D08E | 2025-04-18 | 2025-05-08
1st Coat Paint Walls & Ceilings | 81 | Building 7000 - West | Façade |  | Paint | #F18D00 | 2025-03-10 | 2025-03-10
Finish Ext Wall Activities ie Insdry | X4 | Building 7000 - West | Façade |  | Exteriors Envelope | #E2EFDA | 2025-03-11 | 2025-04-07
Screw Inspection | SI | Building 7000 - West | L5 | Units | Inspections | #C00000 | 2025-03-10 | 2025-03-10
Tape Finish Drywall | 41 | Building 7000 - West | L5 | Units | Drywall | #F2C2F9 | 2025-04-08 | 2025-04-15
Prime 1st Coat Paint Point Up | 85 | Building 7000 - West | L5 | Units | Paint | #F18D00 | 2025-04-16 | 2025-04-24
1st Trim | M1 | Building 7000 - West | L5 | Units | MEPs | #FF7C80 | 2025-04-25 | 2025-05-01
AHU Install, HVAC Trim Out | 52 | Building 7000 - West | L5 | Units | HVAC | #DDEBF7 | 2025-04-25 | 2025-05-01
Install Cabinets & Countertops | K3 | Building 7000 - West | L5 | Units | Cabinets & Tops | #D8A979 | 2025-05-02 | 2025-05-08
Rough Clean | P1 | Building 7000 - West | L5 | Units | Punch | #E36770 | 2025-05-09 | 2025-05-12
Install Flooring | T0 | Building 7000 - West | L5 | Units | Flooring & Tile | #8CE8D4 | 2025-05-13 | 2025-05-19
Meter Inspections HC AHU Startup | 53 | Building 7000 - West | L5 | Units | HVAC | #DDEBF7 | 2025-05-20 | 2025-05-21
Install Appliances | A5 | Building 7000 - West | L5 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-05-20 | 2025-05-21
Install WH, Toilets & Plumbing Fixtures | 34 | Building 7000 - West | L5 | Units | Plumbing | #E2EFDA | 2025-05-20 | 2025-05-23
Corrections from LMC Deficiency | O1 | Building 7000 - West | L5 | Units | LMC-Owners | #3E5E60 | 2025-05-22 | 2025-05-27
Hang Drywall | 42 | Building 7000 - West | L5 | Corridors | Drywall | #F2C2F9 | 2025-03-10
Screw Inspection | SI | Building 7000 - West | L5 | Corridors | Inspections | #C00000 | 2025-03-12 | 2025-03-12
Tape Finish Drywall | 41 | Building 7000 - West | L5 | Corridors | Drywall | #F2C2F9 | 2025-03-13 | 2025-03-17
Trim-out MEP | M4 | Building 7000 - West | L5 | Corridors | MEPs | #FF7C80 | 2025-03-18 | 2025-03-20
2nd Paint | 84 | Building 7000 - West | L5 | Corridors | Paint | #F18D00 | 2025-03-21 | 2025-03-25
Install Fire Extinguisher Cabinet | V1 | Building 7000 - West | L5 | Corridors | Screens/Accesories | #9195AD | 2025-03-26 | 2025-03-26
Final Paint | 82 | Building 7000 - West | L5 | Corridors | Paint | #F18D00 | 2025-06-03 | 2025-06-05
Install Signage | V0 | Building 7000 - West | L5 | Corridors | Screens/Accesories | #9195AD | 2025-06-06 | 2025-06-06
Install Flooring | T0 | Building 7000 - West | L5 | Corridors | Flooring & Tile | #8CE8D4 | 2025-06-06 | 2025-06-10
Final Clean | P2 | Building 7000 - West | L5 | Corridors | Punch | #E36770 | 2025-06-11 | 2025-06-11
Bldg. Final | FI | Building 7000 - West | L5 | Corridors | Inspections | #C00000 | 2025-06-12 | 2025-06-12
Insulation Inspection | II | Building 7000 - West | L4 | Units | Inspections | #C00000 | 2025-03-10 | 2025-03-10
Spray Foam Inspection | 7I | Building 7000 - West | L4 | Units | Inspections | #C00000 | 2025-03-10 | 2025-03-10
Hang Drywall | 42 | Building 7000 - West | L4 | Units | Drywall | #F2C2F9 | 2024-12-27
Screw Inspection | SI | Building 7000 - West | L4 | Units | Inspections | #C00000 | 2025-03-18 | 2025-03-18
Tape Finish Drywall | 41 | Building 7000 - West | L4 | Units | Drywall | #F2C2F9 | 2025-03-19 | 2025-03-26
Prime 1st Coat Paint Point Up | 85 | Building 7000 - West | L4 | Units | Paint | #F18D00 | 2025-04-25 | 2025-05-05
1st Trim | M1 | Building 7000 - West | L4 | Units | MEPs | #FF7C80 | 2025-05-06 | 2025-05-12
AHU Install, HVAC Trim Out | 52 | Building 7000 - West | L4 | Units | HVAC | #DDEBF7 | 2025-05-06 | 2025-05-12
Install Cabinets & Countertops | K3 | Building 7000 - West | L4 | Units | Cabinets & Tops | #D8A979 | 2025-05-13 | 2025-05-19
Rough Clean | P1 | Building 7000 - West | L4 | Units | Punch | #E36770 | 2025-05-20 | 2025-05-21
Install Flooring | T0 | Building 7000 - West | L4 | Units | Flooring & Tile | #8CE8D4 | 2025-05-22 | 2025-05-29
Install Appliances | A5 | Building 7000 - West | L4 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-05-30 | 2025-06-02
Install WH, Toilets & Plumbing Fixtures | 34 | Building 7000 - West | L4 | Units | Plumbing | #E2EFDA | 2025-05-30 | 2025-06-04
Corrections from LMC Deficiency | O1 | Building 7000 - West | L4 | Units | LMC-Owners | #3E5E60 | 2025-06-03 | 2025-06-05
2nd Trim | M3 | Building 7000 - West | L4 | Units | MEPs | #FF7C80 | 2025-06-05 | 2025-06-06
Drywall Punch | 40 | Building 7000 - West | L4 | Units | Drywall | #F2C2F9 | 2025-06-09 | 2025-06-10
Final Paint | 82 | Building 7000 - West | L4 | Units | Paint | #F18D00 | 2025-06-06 | 2025-06-11
Final Unit Inspection | UI | Building 7000 - West | L4 | Units | Inspections | #C00000 | 2025-06-12 | 2025-06-18
Final Clean | P2 | Building 7000 - West | L4 | Units | Punch | #E36770 | 2025-06-19 | 2025-06-20
Hang Drywall | 42 | Building 7000 - West | L4 | Corridors | Drywall | #F2C2F9 | 2025-03-18 | 2025-03-19
Screw Inspection | SI | Building 7000 - West | L4 | Corridors | Inspections | #C00000 | 2025-03-20 | 2025-03-20
Tape Finish Drywall | 41 | Building 7000 - West | L4 | Corridors | Drywall | #F2C2F9 | 2025-03-21 | 2025-03-25
Bldg. Final | FI | Building 7000 - West | L4 | Corridors | Inspections | #C00000 | 2025-03-26 | 2025-03-28
1st Coat Paint Walls & Ceilings | 81 | Building 7000 - West | L4 | Corridors | Paint | #F18D00 | 2025-03-31 | 2025-04-02
Install Fire Extinguisher Cabinet | V1 | Building 7000 - West | L4 | Corridors | Screens/Accesories | #9195AD | 2025-04-03 | 2025-04-03
Install Flooring | T0 | Building 7000 - West | L4 | Corridors | Flooring & Tile | #8CE8D4 | 2025-06-11 | 2025-06-13
Final Paint | 82 | Building 7000 - West | L4 | Corridors | Paint | #F18D00 | 2025-06-12 | 2025-06-16
Install Signage | V0 | Building 7000 - West | L4 | Corridors | Screens/Accesories | #9195AD | 2025-06-17 | 2025-06-17
Final Clean | P2 | Building 7000 - West | L4 | Corridors | Punch | #E36770 | 2025-06-17 | 2025-06-17
Bldg. Final | FI | Building 7000 - West | L4 | Corridors | Inspections | #C00000 | 2025-06-18 | 2025-06-18
Spray Foam Inspection | 7I | Building 7000 - West | L3 | Units | Inspections | #C00000 | 2025-03-10
Insulation | 71 | Building 7000 - West | L3 | Units | Insulation | #868CC4 | 2025-01-06
Insulation Inspection | II | Building 7000 - West | L3 | Units | Inspections | #C00000 | 2025-03-17 | 2025-03-17
Screw Inspection | SI | Building 7000 - West | L3 | Units | Inspections | #C00000 | 2025-03-10 | 2025-03-10
Tape Finish Drywall | 41 | Building 7000 - West | L3 | Units | Drywall | #F2C2F9 | 2025-03-11 | 2025-03-18
Prime 1st Coat Paint Point Up | 85 | Building 7000 - West | L3 | Units | Paint | #F18D00 | 2025-05-06 | 2025-05-14
AHU Install, HVAC Trim Out | 52 | Building 7000 - West | L3 | Units | HVAC | #DDEBF7 | 2025-05-15 | 2025-05-21
1st Trim | M1 | Building 7000 - West | L3 | Units | MEPs | #FF7C80 | 2025-05-15 | 2025-05-21
Install Cabinets & Countertops | K3 | Building 7000 - West | L3 | Units | Cabinets & Tops | #D8A979 | 2025-05-22 | 2025-05-29
Meter Inspections HC AHU Startup | 53 | Building 7000 - West | L3 | Units | HVAC | #DDEBF7 | 2025-06-10 | 2025-06-11
Install Appliances | A5 | Building 7000 - West | L3 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-06-10 | 2025-06-11
Install WH, Toilets & Plumbing Fixtures | 34 | Building 7000 - West | L3 | Units | Plumbing | #E2EFDA | 2025-06-10 | 2025-06-13
Corrections from LMC Deficiency | O1 | Building 7000 - West | L3 | Units | LMC-Owners | #3E5E60 | 2025-06-12 | 2025-06-16
2nd Trim | M3 | Building 7000 - West | L3 | Units | MEPs | #FF7C80 | 2025-06-16 | 2025-06-17
Drywall Punch | 40 | Building 7000 - West | L3 | Units | Drywall | #F2C2F9 | 2025-06-18 | 2025-06-19
Final Paint | 82 | Building 7000 - West | L3 | Units | Paint | #F18D00 | 2025-06-17 | 2025-06-20
Final Unit Inspection | UI | Building 7000 - West | L3 | Units | Inspections | #C00000 | 2025-06-23 | 2025-06-27
Final Clean | P2 | Building 7000 - West | L3 | Units | Punch | #E36770 | 2025-06-30 | 2025-07-01
Hang Drywall | 42 | Building 7000 - West | L3 | Corridors | Drywall | #F2C2F9 | 2025-03-20 | 2025-03-21
Screw Inspection | SI | Building 7000 - West | L3 | Corridors | Inspections | #C00000 | 2025-03-24 | 2025-03-24
Tape Finish Drywall | 41 | Building 7000 - West | L3 | Corridors | Drywall | #F2C2F9 | 2025-03-25 | 2025-03-28
Trim-out MEP | M4 | Building 7000 - West | L3 | Corridors | MEPs | #FF7C80 | 2025-03-31 | 2025-04-02
1st Coat Paint Walls & Ceilings | 81 | Building 7000 - West | L3 | Corridors | Paint | #F18D00 | 2025-04-03 | 2025-04-07
Install Fire Extinguisher Cabinet | V1 | Building 7000 - West | L3 | Corridors | Screens/Accesories | #9195AD | 2025-04-08 | 2025-04-08
Install Flooring | T0 | Building 7000 - West | L3 | Corridors | Flooring & Tile | #8CE8D4 | 2025-06-16 | 2025-06-18
Final Paint | 82 | Building 7000 - West | L3 | Corridors | Paint | #F18D00 | 2025-06-23 | 2025-06-25
Install Signage | V0 | Building 7000 - West | L3 | Corridors | Screens/Accesories | #9195AD | 2025-06-26 | 2025-06-26
Final Clean | P2 | Building 7000 - West | L3 | Corridors | Punch | #E36770 | 2025-06-26 | 2025-06-26
Bldg. Final | FI | Building 7000 - West | L3 | Corridors | Inspections | #C00000 | 2025-06-27 | 2025-06-27
Spray Foam Inspection | 7I | Building 7000 - West | L2 | Units | Inspections | #C00000 | 2025-03-10 | 2025-03-10
Insulation | 71 | Building 7000 - West | L2 | Units | Insulation | #868CC4 | 2025-01-14
Insulation Inspection | II | Building 7000 - West | L2 | Units | Inspections | #C00000 | 2025-03-26 | 2025-03-26
Screw Inspection | SI | Building 7000 - West | L2 | Units | Inspections | #C00000 | 2025-03-10
Prime 1st Coat Paint Point Up | 85 | Building 7000 - West | L2 | Units | Paint | #F18D00 | 2025-05-15 | 2025-05-23
AHU Install, HVAC Trim Out | 52 | Building 7000 - West | L2 | Units | HVAC | #DDEBF7 | 2025-05-27 | 2025-06-02
1st Trim | M1 | Building 7000 - West | L2 | Units | MEPs | #FF7C80 | 2025-05-27 | 2025-06-02
Install Cabinets & Countertops | K3 | Building 7000 - West | L2 | Units | Cabinets & Tops | #D8A979 | 2025-06-03 | 2025-06-09
Rough Clean | P1 | Building 7000 - West | L2 | Units | Punch | #E36770 | 2025-06-10 | 2025-06-11
Install Flooring | T0 | Building 7000 - West | L2 | Units | Flooring & Tile | #8CE8D4 | 2025-06-12 | 2025-06-18
Install Appliances | A5 | Building 7000 - West | L2 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-06-19 | 2025-06-20
Meter Inspections HC AHU Startup | 53 | Building 7000 - West | L2 | Units | HVAC | #DDEBF7 | 2025-06-19 | 2025-06-20
Install WH, Toilets & Plumbing Fixtures | 34 | Building 7000 - West | L2 | Units | Plumbing | #E2EFDA | 2025-06-19 | 2025-06-24
Corrections from LMC Deficiency | O1 | Building 7000 - West | L2 | Units | LMC-Owners | #3E5E60 | 2025-06-23 | 2025-06-25
Final Paint | 82 | Building 7000 - West | L2 | Units | Paint | #F18D00 | 2025-06-20 | 2025-06-25
2nd Trim | M3 | Building 7000 - West | L2 | Units | MEPs | #FF7C80 | 2025-06-25 | 2025-06-26
Drywall Punch | 40 | Building 7000 - West | L2 | Units | Drywall | #F2C2F9 | 2025-06-27 | 2025-06-30
Final Unit Inspection | UI | Building 7000 - West | L2 | Units | Inspections | #C00000 | 2025-06-30 | 2025-07-07
Final Clean | P2 | Building 7000 - West | L2 | Units | Punch | #E36770 | 2025-07-08 | 2025-07-09
Hang Drywall | 42 | Building 7000 - West | L2 | Corridors | Drywall | #F2C2F9 | 2025-03-22 | 2025-03-24
Tape Finish Drywall | 41 | Building 7000 - West | L2 | Corridors | Drywall | #F2C2F9 | 2025-03-26 | 2025-03-29
1st Coat Paint Walls & Ceilings | 81 | Building 7000 - West | L2 | Corridors | Paint | #F18D00 | 2025-04-03 | 2025-04-07
Install Fire Extinguisher Cabinet | V1 | Building 7000 - West | L2 | Corridors | Screens/Accesories | #9195AD | 2025-04-08 | 2025-04-08
Install Flooring | T0 | Building 7000 - West | L2 | Corridors | Flooring & Tile | #8CE8D4 | 2025-06-19 | 2025-06-23
Final Paint | 82 | Building 7000 - West | L2 | Corridors | Paint | #F18D00 | 2025-06-26 | 2025-06-30
Final Clean | P2 | Building 7000 - West | L2 | Corridors | Punch | #E36770 | 2025-07-01 | 2025-07-01
Install Signage | V0 | Building 7000 - West | L2 | Corridors | Screens/Accesories | #9195AD | 2025-07-01 | 2025-07-01
Bldg. Final | FI | Building 7000 - West | L2 | Corridors | Inspections | #C00000 | 2025-07-02 | 2025-07-02
Spray Foam Inspection | 7I | Building 7000 - West | L1 | Units | Inspections | #C00000 | 2025-03-10 | 2025-03-10
Insulation | 71 | Building 7000 - West | L1 | Units | Insulation | #868CC4 | 2025-01-21
Hang Drywall | 42 | Building 7000 - West | L1 | Units | Drywall | #F2C2F9 | 2025-03-11 | 2025-03-13
Screw Inspection | SI | Building 7000 - West | L1 | Units | Inspections | #C00000 | 2025-03-14 | 2025-03-14
Tape Finish Drywall | 41 | Building 7000 - West | L1 | Units | Drywall | #F2C2F9 | 2025-03-19 | 2025-03-26
Prime 1st Coat Paint Point Up | 85 | Building 7000 - West | L1 | Units | Paint | #F18D00 | 2025-03-27 | 2025-04-04
AHU Install, HVAC Trim Out | 52 | Building 7000 - West | L1 | Units | HVAC | #DDEBF7 | 2025-04-07 | 2025-04-11
1st Trim | M1 | Building 7000 - West | L1 | Units | MEPs | #FF7C80 | 2025-04-07 | 2025-04-11
Install Cabinets & Countertops | K3 | Building 7000 - West | L1 | Units | Cabinets & Tops | #D8A979 | 2025-04-14 | 2025-04-18
Rough Clean | P1 | Building 7000 - West | L1 | Units | Punch | #E36770 | 2025-04-21 | 2025-04-22
Install Flooring | T0 | Building 7000 - West | L1 | Units | Flooring & Tile | #8CE8D4 | 2025-04-23 | 2025-04-29
Meter Inspections HC AHU Startup | 53 | Building 7000 - West | L1 | Units | HVAC | #DDEBF7 | 2025-04-30 | 2025-05-01
Install WH, Toilets & Plumbing Fixtures | 34 | Building 7000 - West | L1 | Units | Plumbing | #E2EFDA | 2025-04-30 | 2025-05-05
2nd Trim | M3 | Building 7000 - West | L1 | Units | MEPs | #FF7C80 | 2025-05-06 | 2025-05-07
Drywall Punch | 40 | Building 7000 - West | L1 | Units | Drywall | #F2C2F9 | 2025-05-08 | 2025-05-09
Install Appliances | A5 | Building 7000 - West | L1 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-06-23 | 2025-06-24
Corrections from LMC Deficiency | O1 | Building 7000 - West | L1 | Units | LMC-Owners | #3E5E60 | 2025-06-25 | 2025-06-27
Hang Drywall | 42 | Building 7000 - West | L1 | Corridors | Drywall | #F2C2F9 | 2025-03-25 | 2025-03-26
Screw Inspection | SI | Building 7000 - West | L1 | Corridors | Inspections | #C00000 | 2025-03-27
Tape Finish Drywall | 41 | Building 7000 - West | L1 | Corridors | Drywall | #F2C2F9 | 2025-03-28
Trim-out MEP | M4 | Building 7000 - West | L1 | Corridors | MEPs | #FF7C80 | 2025-04-02 | 2025-04-04
1st Coat Paint Walls & Ceilings | 81 | Building 7000 - West | L1 | Corridors | Paint | #F18D00 | 2025-04-07 | 2025-04-09
Install Fire Extinguisher Cabinet | V1 | Building 7000 - West | L1 | Corridors | Screens/Accesories | #9195AD | 2025-04-10 | 2025-04-10
Install Flooring | T0 | Building 7000 - West | L1 | Corridors | Flooring & Tile | #8CE8D4 | 2025-06-24 | 2025-06-26
Final Paint | 82 | Building 7000 - West | L1 | Corridors | Paint | #F18D00 | 2025-07-07 | 2025-07-09
Install Signage | V0 | Building 7000 - West | L1 | Corridors | Screens/Accesories | #9195AD | 2025-07-10 | 2025-07-10
Bldg. Final | FI | Building 7000 - West | L1 | Corridors | Inspections | #C00000 | 2025-07-10 | 2025-07-10
Seal Concrete Flooring | CA | Building 7000 - West | L1 | Bike Rooms | Concrete | #DBDBDB | 2025-04-17
Install Mail Box Equipment | V2 | Building 7000 - West | L1 | Bike Rooms | Screens/Accesories | #9195AD | 2025-04-24 | 2025-04-25
Insulate Ceiling | 70 | Building 7000 - West | L1 | Electric Rooms | Insulation | #868CC4 | 2025-03-10 | 2025-03-10
Inspection of Ceiling | DI | Building 7000 - West | L1 | Electric Rooms | Inspections | #C00000 | 2025-03-11 | 2025-03-11
Insulate Ceiling | 70 | Building 7000 - West | L1 | Electric Rooms | Insulation | #868CC4 | 2025-03-10
Close Ceiling | R0 | Building 7000 - West | L1 | Electric Rooms | Roofing | #385623 | 2025-03-12
Final Inspection | FI | Building 7000 - West | L1 | Electric Rooms | Inspections | #C00000 | 2025-03-13
Land LV Racks | 69 | Building 7000 - West | L1 | IDF | Electrical | #FFF2CC | 2025-03-21 | 2025-03-26
Land LV Racks | 69 | Building 7000 - West | L1 | IDF | Electrical | #FFF2CC | 2025-04-03 | 2025-04-09
Punch Low Voltage Devices | 6A | Building 7000 - West | L1 | IDF | Electrical | #FFF2CC | 2025-04-10 | 2025-04-10
1st Coat Paint Walls & Ceilings | 81 | Building 7000 - East | Façade |  | Paint | #F18D00 | 2025-03-10
Finish Ext Wall Activities ie Insdry | X4 | Building 7000 - East | Façade |  | Exteriors Envelope | #E2EFDA | 2025-03-11
Spray Foam | 72 | Building 7000 - East | L5 | Units | Insulation | #868CC4 | 2025-03-03
Spray Foam Inspection | 7I | Building 7000 - East | L5 | Units | Inspections | #C00000 | 2025-03-14 | 2025-03-14
Final MEP Inspections | 0I | Building 7000 - East | L5 | Units | Inspections | #C00000 | 2025-03-10
Hang Drywall | 42 | Building 7000 - East | L5 | Units | Drywall | #F2C2F9 | 2025-03-10 | 2025-03-13
Screw Inspection | SI | Building 7000 - East | L5 | Units | Inspections | #C00000 | 2025-03-13 | 2025-03-14
Tape Finish Drywall | 41 | Building 7000 - East | L5 | Units | Drywall | #F2C2F9 | 2025-04-08 | 2025-04-14
Prime 1st Coat Paint Point Up | 85 | Building 7000 - East | L5 | Units | Paint | #F18D00 | 2025-04-15 | 2025-04-21
1st Trim | M1 | Building 7000 - East | L5 | Units | MEPs | #FF7C80 | 2025-04-22 | 2025-04-28
AHU Install, HVAC Trim Out | 52 | Building 7000 - East | L5 | Units | HVAC | #DDEBF7 | 2025-04-29 | 2025-05-05
Install Cabinets & Countertops | K3 | Building 7000 - East | L5 | Units | Cabinets & Tops | #D8A979 | 2025-05-05 | 2025-05-12
Rough Clean | P1 | Building 7000 - East | L5 | Units | Punch | #E36770 | 2025-05-12 | 2025-05-14
Install Flooring | T0 | Building 7000 - East | L5 | Units | Flooring & Tile | #8CE8D4 | 2025-05-14 | 2025-05-21
Install WH, Toilets & Plumbing Fixtures | 34 | Building 7000 - East | L5 | Units | Plumbing | #E2EFDA | 2025-05-21 | 2025-05-28
Meter Inspections HC AHU Startup | 53 | Building 7000 - East | L5 | Units | HVAC | #DDEBF7 | 2025-05-28 | 2025-05-30
2nd Trim | M3 | Building 7000 - East | L5 | Units | MEPs | #FF7C80 | 2025-05-30 | 2025-06-03
Drywall Punch | 40 | Building 7000 - East | L5 | Units | Drywall | #F2C2F9 | 2025-06-03 | 2025-06-05
Install Appliances | A5 | Building 7000 - East | L5 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-06-05 | 2025-06-09
Corrections from LMC Deficiency | O1 | Building 7000 - East | L5 | Units | LMC-Owners | #3E5E60 | 2025-06-09 | 2025-06-12
Final Paint | 82 | Building 7000 - East | L5 | Units | Paint | #F18D00 | 2025-06-12 | 2025-06-18
Final Unit Inspection | UI | Building 7000 - East | L5 | Units | Inspections | #C00000 | 2025-06-18 | 2025-06-25
Final Clean | P2 | Building 7000 - East | L5 | Units | Punch | #E36770 | 2025-06-25 | 2025-06-27
Hang Drywall | 42 | Building 7000 - East | L5 | Corridors | Drywall | #F2C2F9 | 2025-03-13
Screw Inspection | SI | Building 7000 - East | L5 | Corridors | Inspections | #C00000 | 2025-03-17 | 2025-03-17
Tape Finish Drywall | 41 | Building 7000 - East | L5 | Corridors | Drywall | #F2C2F9 | 2025-03-18 | 2025-03-21
Trim-out MEP | M4 | Building 7000 - East | L5 | Corridors | MEPs | #FF7C80 | 2025-03-24 | 2025-03-26
Prime 1st Coat Paint Point Up | 85 | Building 7000 - East | L5 | Corridors | Paint | #F18D00 | 2025-03-27 | 2025-03-31
Drywall Punch | 40 | Building 7000 - East | L5 | Corridors | Drywall | #F2C2F9 | 2025-04-01 | 2025-04-01
Install Fire Extinguisher Cabinet | V1 | Building 7000 - East | L5 | Corridors | Screens/Accesories | #9195AD | 2025-04-02 | 2025-04-02
Rough Clean | P1 | Building 7000 - East | L5 | Corridors | Punch | #E36770 | 2025-04-03 | 2025-04-04
Trim-out Low Voltage Devices | 64 | Building 7000 - East | L5 | Corridors | Electrical | #FFF2CC | 2025-04-07 | 2025-04-08
Install Flooring | T0 | Building 7000 - East | L5 | Corridors | Flooring & Tile | #8CE8D4 | 2025-04-09 | 2025-04-11
Install Signage | V0 | Building 7000 - East | L5 | Corridors | Screens/Accesories | #9195AD | 2025-04-17 | 2025-04-17
Final Clean | P2 | Building 7000 - East | L5 | Corridors | Punch | #E36770 | 2025-04-17 | 2025-04-17
Bldg. Final | FI | Building 7000 - East | L5 | Corridors | Inspections | #C00000 | 2025-04-18 | 2025-04-18
Hang Drywall | 42 | Building 7000 - East | L4 | Units | Drywall | #F2C2F9 | 2025-03-13 | 2025-03-18
Screw Inspection | SI | Building 7000 - East | L4 | Units | Inspections | #C00000 | 2025-03-18 | 2025-03-19
Tape Finish Drywall | 41 | Building 7000 - East | L4 | Units | Drywall | #F2C2F9 | 2025-03-19 | 2025-03-26
Prime 1st Coat Paint Point Up | 85 | Building 7000 - East | L4 | Units | Paint | #F18D00 | 2025-04-22 | 2025-04-28
AHU Install, HVAC Trim Out | 52 | Building 7000 - East | L4 | Units | HVAC | #DDEBF7 | 2025-04-29 | 2025-05-05
Trim-out MEP | M4 | Building 7000 - East | L4 | Units | MEPs | #FF7C80 | 2025-04-29 | 2025-05-05
Install Cabinets & Countertops | K3 | Building 7000 - East | L4 | Units | Cabinets & Tops | #D8A979 | 2025-05-06 | 2025-05-12
Install Flooring | T0 | Building 7000 - East | L4 | Units | Flooring & Tile | #8CE8D4 | 2025-05-14 | 2025-05-20
Meter Inspections HC AHU Startup | 53 | Building 7000 - East | L4 | Units | HVAC | #DDEBF7 | 2025-05-21 | 2025-05-22
Install WH, Toilets & Plumbing Fixtures | 34 | Building 7000 - East | L4 | Units | Plumbing | #E2EFDA | 2025-05-21 | 2025-05-27
2nd Trim | M3 | Building 7000 - East | L4 | Units | MEPs | #FF7C80 | 2025-05-28 | 2025-05-29
Drywall Punch | 40 | Building 7000 - East | L4 | Units | Drywall | #F2C2F9 | 2025-05-30 | 2025-06-02
Install Appliances | A5 | Building 7000 - East | L4 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-06-09 | 2025-06-11
Corrections from LMC Deficiency | O1 | Building 7000 - East | L4 | Units | LMC-Owners | #3E5E60 | 2025-06-11 | 2025-06-16
Final Paint | 82 | Building 7000 - East | L4 | Units | Paint | #F18D00 | 2025-06-16 | 2025-06-20
Final Unit Inspection | UI | Building 7000 - East | L4 | Units | Inspections | #C00000 | 2025-06-20 | 2025-06-27
Final Clean | P2 | Building 7000 - East | L4 | Units | Punch | #E36770 | 2025-06-27 | 2025-07-01
Hang Drywall | 42 | Building 7000 - East | L4 | Corridors | Drywall | #F2C2F9 | 2025-03-18 | 2025-03-20
Install Fire Extinguisher Cabinet | V1 | Building 7000 - East | L4 | Corridors | Screens/Accesories | #9195AD | 2025-04-03 | 2025-04-04
Install Flooring | T0 | Building 7000 - East | L4 | Corridors | Flooring & Tile | #8CE8D4 | 2025-05-21 | 2025-05-23
Final Paint | 82 | Building 7000 - East | L4 | Corridors | Paint | #F18D00 | 2025-06-20 | 2025-06-25
Install Signage | V0 | Building 7000 - East | L4 | Corridors | Screens/Accesories | #9195AD | 2025-06-25 | 2025-06-26
Final Clean | P2 | Building 7000 - East | L4 | Corridors | Punch | #E36770 | 2025-06-25 | 2025-06-26
Bldg. Final | FI | Building 7000 - East | L4 | Corridors | Inspections | #C00000 | 2025-06-26 | 2025-06-27
Insulation | 71 | Building 7000 - East | L3 | Units | Insulation | #868CC4 | 2025-02-19
Insulation Inspection | II | Building 7000 - East | L3 | Units | Inspections | #C00000 | 2025-03-11
Spray Foam | 72 | Building 7000 - East | L3 | Units | Insulation | #868CC4 | 2025-03-03
Spray Foam Inspection | 7I | Building 7000 - East | L3 | Units | Inspections | #C00000 | 2025-03-14
Stock Drywall | 43 | Building 7000 - East | L3 | Units | Drywall | #F2C2F9 | 2025-03-12 | 2025-03-12
Final MEP Inspections | 0I | Building 7000 - East | L3 | Units | Inspections | #C00000 | 2025-03-10 | 2025-03-12
Hang Drywall | 42 | Building 7000 - East | L3 | Units | Drywall | #F2C2F9 | 2025-03-13 | 2025-03-17
Screw Inspection | SI | Building 7000 - East | L3 | Units | Inspections | #C00000 | 2025-03-18 | 2025-03-18
Tape Finish Drywall | 41 | Building 7000 - East | L3 | Units | Drywall | #F2C2F9 | 2025-03-19 | 2025-03-26
Prime 1st Coat Paint Point Up | 85 | Building 7000 - East | L3 | Units | Paint | #F18D00 | 2025-04-29 | 2025-05-07
AHU Install, HVAC Trim Out | 52 | Building 7000 - East | L3 | Units | HVAC | #DDEBF7 | 2025-05-08 | 2025-05-14
1st Trim | M1 | Building 7000 - East | L3 | Units | MEPs | #FF7C80 | 2025-05-08 | 2025-05-14
Install Cabinets & Countertops | K3 | Building 7000 - East | L3 | Units | Cabinets & Tops | #D8A979 | 2025-05-15 | 2025-05-21
Rough Clean | P1 | Building 7000 - East | L3 | Units | Punch | #E36770 | 2025-05-22 | 2025-05-23
Install Flooring | T0 | Building 7000 - East | L3 | Units | Flooring & Tile | #8CE8D4 | 2025-05-27 | 2025-06-02
Meter Inspections HC AHU Startup | 53 | Building 7000 - East | L3 | Units | HVAC | #DDEBF7 | 2025-06-03 | 2025-06-04
Install WH, Toilets & Plumbing Fixtures | 34 | Building 7000 - East | L3 | Units | Plumbing | #E2EFDA | 2025-06-03 | 2025-06-06
2nd Trim | M3 | Building 7000 - East | L3 | Units | MEPs | #FF7C80 | 2025-06-09 | 2025-06-10
Drywall Punch | 40 | Building 7000 - East | L3 | Units | Drywall | #F2C2F9 | 2025-06-11 | 2025-06-12
Corrections from LMC Deficiency | O1 | Building 7000 - East | L3 | Units | LMC-Owners | #3E5E60 | 2025-06-13 | 2025-06-18
Final Paint | 82 | Building 7000 - East | L3 | Units | Paint | #F18D00 | 2025-06-18 | 2025-06-24
Final Unit Inspection | UI | Building 7000 - East | L3 | Units | Inspections | #C00000 | 2025-06-27 | 2025-07-07
Hang Drywall | 42 | Building 7000 - East | L3 | Corridors | Drywall | #F2C2F9 | 2025-03-20 | 2025-03-22
Screw Inspection | SI | Building 7000 - East | L3 | Corridors | Inspections | #C00000 | 2025-03-24 | 2025-03-24
Tape Finish Drywall | 41 | Building 7000 - East | L3 | Corridors | Drywall | #F2C2F9 | 2025-03-25 | 2025-03-28
Bldg. Final | FI | Building 7000 - East | L3 | Corridors | Inspections | #C00000 | 2025-03-31 | 2025-04-02
2nd Paint | 84 | Building 7000 - East | L3 | Corridors | Paint | #F18D00 | 2025-04-03 | 2025-04-07
Install Fire Extinguisher Cabinet | V1 | Building 7000 - East | L3 | Corridors | Screens/Accesories | #9195AD | 2025-04-08 | 2025-04-08
Install Flooring | T0 | Building 7000 - East | L3 | Corridors | Flooring & Tile | #8CE8D4 | 2025-06-03 | 2025-06-05
Final Paint | 82 | Building 7000 - East | L3 | Corridors | Paint | #F18D00 | 2025-06-24 | 2025-06-27
Final Clean | P2 | Building 7000 - East | L3 | Corridors | Punch | #E36770 | 2025-06-27 | 2025-06-30
Install Signage | V0 | Building 7000 - East | L3 | Corridors | Screens/Accesories | #9195AD | 2025-06-27 | 2025-06-30
Bldg. Final | FI | Building 7000 - East | L3 | Corridors | Inspections | #C00000 | 2025-06-30 | 2025-07-01
Spray Foam | 72 | Building 7000 - East | L2 | Units | Insulation | #868CC4 | 2025-03-03
Spray Foam Inspection | 7I | Building 7000 - East | L2 | Units | Inspections | #C00000 | 2025-03-14 | 2025-03-14
Insulation | 71 | Building 7000 - East | L2 | Units | Insulation | #868CC4 | 2025-03-11 | 2025-03-19
Insulation Inspection | II | Building 7000 - East | L2 | Units | Inspections | #C00000 | 2025-03-20 | 2025-03-20
Hang Drywall | 42 | Building 7000 - East | L2 | Units | Drywall | #F2C2F9 | 2025-03-22
Screw Inspection | SI | Building 7000 - East | L2 | Units | Inspections | #C00000 | 2025-03-27
Tape Finish Drywall | 41 | Building 7000 - East | L2 | Units | Drywall | #F2C2F9 | 2025-03-28
Prime 1st Coat Paint Point Up | 85 | Building 7000 - East | L2 | Units | Paint | #F18D00 | 2025-04-04
1st Trim | M1 | Building 7000 - East | L2 | Units | MEPs | #FF7C80 | 2025-04-11 | 2025-04-17
AHU Install, HVAC Trim Out | 52 | Building 7000 - East | L2 | Units | HVAC | #DDEBF7 | 2025-04-11 | 2025-04-17
Install Appliances | A5 | Building 7000 - East | L2 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-05-06 | 2025-05-07
Install WH, Toilets & Plumbing Fixtures | 34 | Building 7000 - East | L2 | Units | Plumbing | #E2EFDA | 2025-05-06 | 2025-05-09
Corrections from LMC Deficiency | O1 | Building 7000 - East | L2 | Units | LMC-Owners | #3E5E60 | 2025-05-08 | 2025-05-12
2nd Trim | M3 | Building 7000 - East | L2 | Units | MEPs | #FF7C80 | 2025-05-12 | 2025-05-13
Drywall Punch | 40 | Building 7000 - East | L2 | Units | Drywall | #F2C2F9 | 2025-05-14 | 2025-05-15
Final Paint | 82 | Building 7000 - East | L2 | Units | Paint | #F18D00 | 2025-05-16 | 2025-05-21
Meter Inspections HC AHU Startup | 53 | Building 7000 - East | L2 | Units | HVAC | #DDEBF7 | 2025-06-05 | 2025-06-06
Final Unit Inspection | UI | Building 7000 - East | L2 | Units | Inspections | #C00000 | 2025-07-07 | 2025-07-11
Final Paint | 82 | Building 7000 - East | L2 | Units | Paint | #F18D00 | 2025-07-11 | 2025-07-15
Hang Drywall | 42 | Building 7000 - East | L2 | Corridors | Drywall | #F2C2F9 | 2025-03-27 | 2025-03-28
Screw Inspection | SI | Building 7000 - East | L2 | Corridors | Inspections | #C00000 | 2025-03-31 | 2025-03-31
Tape Finish Drywall | 41 | Building 7000 - East | L2 | Corridors | Drywall | #F2C2F9 | 2025-04-01 | 2025-04-04
Trim-out MEP | M4 | Building 7000 - East | L2 | Corridors | MEPs | #FF7C80 | 2025-04-07 | 2025-04-09
1st Coat Paint Walls & Ceilings | 81 | Building 7000 - East | L2 | Corridors | Paint | #F18D00 | 2025-04-10 | 2025-04-14
Install Fire Extinguisher Cabinet | V1 | Building 7000 - East | L2 | Corridors | Screens/Accesories | #9195AD | 2025-04-15 | 2025-04-15
Install Flooring | T0 | Building 7000 - East | L2 | Corridors | Flooring & Tile | #8CE8D4 | 2025-06-06 | 2025-06-10
Install Signage | V0 | Building 7000 - East | L2 | Corridors | Screens/Accesories | #9195AD | 2025-06-11 | 2025-06-11
Final Paint | 82 | Building 7000 - East | L2 | Corridors | Paint | #F18D00 | 2025-06-12 | 2025-06-16
Final Clean | P2 | Building 7000 - East | L2 | Corridors | Punch | #E36770 | 2025-07-11 | 2025-07-14
Bldg. Final | FI | Building 7000 - East | L2 | Corridors | Inspections | #C00000 | 2025-07-14 | 2025-07-15
Spray Foam | 72 | Building 7000 - East | L1 | Units | Insulation | #868CC4 | 2025-03-03
Spray Foam Inspection | 7I | Building 7000 - East | L1 | Units | Inspections | #C00000 | 2025-03-14 | 2025-03-14
Insulation | 71 | Building 7000 - East | L1 | Units | Insulation | #868CC4 | 2025-03-20 | 2025-03-28
Hang Drywall | 42 | Building 7000 - East | L1 | Units | Drywall | #F2C2F9 | 2025-04-02 | 2025-04-05
Screw Inspection | SI | Building 7000 - East | L1 | Units | Inspections | #C00000 | 2025-04-07 | 2025-04-07
Tape Finish Drywall | 41 | Building 7000 - East | L1 | Units | Drywall | #F2C2F9 | 2025-04-08 | 2025-04-14
Prime 1st Coat Paint Point Up | 85 | Building 7000 - East | L1 | Units | Paint | #F18D00 | 2025-04-15 | 2025-04-21
AHU Install, HVAC Trim Out | 52 | Building 7000 - East | L1 | Units | HVAC | #DDEBF7 | 2025-04-22 | 2025-04-28
1st Trim | M1 | Building 7000 - East | L1 | Units | MEPs | #FF7C80 | 2025-04-22 | 2025-04-28
Meter Inspections HC AHU Startup | 53 | Building 7000 - East | L1 | Units | HVAC | #DDEBF7 | 2025-04-29 | 2025-04-30
Install Cabinets & Countertops | K3 | Building 7000 - East | L1 | Units | Cabinets & Tops | #D8A979 | 2025-04-29 | 2025-05-05
Rough Clean | P1 | Building 7000 - East | L1 | Units | Punch | #E36770 | 2025-05-06 | 2025-05-07
Install Flooring | T0 | Building 7000 - East | L1 | Units | Flooring & Tile | #8CE8D4 | 2025-05-08 | 2025-05-14
Install Appliances | A5 | Building 7000 - East | L1 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-05-15 | 2025-05-16
Install WH, Toilets & Plumbing Fixtures | 34 | Building 7000 - East | L1 | Units | Plumbing | #E2EFDA | 2025-05-15 | 2025-05-20
Corrections from LMC Deficiency | O1 | Building 7000 - East | L1 | Units | LMC-Owners | #3E5E60 | 2025-05-19 | 2025-05-21
2nd Trim | M3 | Building 7000 - East | L1 | Units | MEPs | #FF7C80 | 2025-05-21 | 2025-05-22
Drywall Punch | 40 | Building 7000 - East | L1 | Units | Drywall | #F2C2F9 | 2025-05-23 | 2025-05-27
Final Paint | 82 | Building 7000 - East | L1 | Units | Paint | #F18D00 | 2025-05-28 | 2025-06-02
Final Clean | P2 | Building 7000 - East | L1 | Units | Punch | #E36770 | 2025-06-03 | 2025-06-04
Final MEP Inspections | 0I | Building 7000 - East | L1 | Units | Inspections | #C00000 | 2025-06-05 | 2025-06-09
Hang Drywall | 42 | Building 7000 - East | L1 | Corridors | Drywall | #F2C2F9 | 2025-04-07 | 2025-04-08
Screw Inspection | SI | Building 7000 - East | L1 | Corridors | Inspections | #C00000 | 2025-04-09
Tape Finish Drywall | 41 | Building 7000 - East | L1 | Corridors | Drywall | #F2C2F9 | 2025-04-10
Trim-out MEP | M4 | Building 7000 - East | L1 | Corridors | MEPs | #FF7C80 | 2025-04-15
1st Coat Paint Walls & Ceilings | 81 | Building 7000 - East | L1 | Corridors | Paint | #F18D00 | 2025-04-18
Install Fire Extinguisher Cabinet | V1 | Building 7000 - East | L1 | Corridors | Screens/Accesories | #9195AD | 2025-04-23
Install Signage | V0 | Building 7000 - East | L1 | Corridors | Screens/Accesories | #9195AD | 2025-04-23
Install Flooring | T0 | Building 7000 - East | L1 | Corridors | Flooring & Tile | #8CE8D4 | 2025-05-15
2nd Trim | M3 | Building 7000 - East | L1 | Corridors | MEPs | #FF7C80 | 2025-05-20
Final Paint | 82 | Building 7000 - East | L1 | Corridors | Paint | #F18D00 | 2025-06-03 | 2025-06-05
Bldg. Final | FI | Building 7000 - East | L1 | Corridors | Inspections | #C00000 | 2025-06-06 | 2025-06-06
Seal Concrete Flooring | CA | Building 7000 - East | L1 | Bike Rooms | Concrete | #DBDBDB | 2025-03-10 | 2025-03-14
Seal Concrete Flooring | CA | Building 7000 - East | L1 | Mail Room | Concrete | #DBDBDB | 2025-03-17
Insulate Ceiling | 70 | Building 7000 - East | L1 | Electric Rooms | Insulation | #868CC4 | 2025-03-10 | 2025-03-10
Inspection of Ceiling | DI | Building 7000 - East | L1 | Electric Rooms | Inspections | #C00000 | 2025-03-11 | 2025-03-11
Close Ceiling | R0 | Building 7000 - East | L1 | Electric Rooms | Roofing | #385623 | 2025-03-12 | 2025-03-12
Final Inspection | FI | Building 7000 - East | L1 | Electric Rooms | Inspections | #C00000 | 2025-03-13 | 2025-03-13
Land LV Racks | 69 | Building 7000 - East | L1 | IDF | Electrical | #FFF2CC | 2025-03-19 | 2025-03-24
Land LV Racks | 69 | Building 7000 - East | L1 | IDF | Electrical | #FFF2CC | 2025-03-25 | 2025-03-31
Land LV Racks | 69 | Building 7000 - East | L1 | IDF | Electrical | #FFF2CC | 2025-04-01 | 2025-04-07
Punch Low Voltage Devices | 6A | Building 7000 - East | L1 | IDF | Electrical | #FFF2CC | 2025-04-08 | 2025-04-08
State Elevator Testing | EI | Building 7000 - East | Inspections and Closeout |  | Inspections | #C00000 | 2025-03-10 | 2025-03-14
Final FP Inspections and Life Safety | 1I | Building 7000 - East | Inspections and Closeout |  | Inspections | #C00000 | 2025-06-10 | 2025-06-12
CofO Inspection Signoff | CI | Building 7000 - East | Inspections and Closeout |  | Inspections | #C00000 | 2025-07-08 | 2025-07-14
FFE | A1 | Building 7000 - East | Inspections and Closeout |  | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-07-15 | 2025-07-23
Powder Puff Clean | P3 | Building 7000 - East | Inspections and Closeout |  | Punch | #E36770 | 2025-07-22 | 2025-07-25
Install Panel Batten | X2 | Building 3000 | Façade |  | Exteriors Envelope | #548235 | 2025-03-28 | 2025-04-01
Install Lap Siding | X1 | Building 3000 | Façade |  | Exteriors Envelope | #CCCC00 | 2024-12-18
Finish Balconies | X3 | Building 3000 | Façade |  | Exteriors Envelope | #A9D08E | 2025-04-02 | 2025-04-22
Install Balcony Rails | SB | Building 3000 | Façade |  | Steel | #A6A6A6 | 2025-04-23 | 2025-04-30
Exterior Trim Accessories | X5 | Building 3000 | Façade |  | Exteriors Finishes 1 | #375623 | 2025-04-23 | 2025-05-02
Stock Drywall | 43 | Building 3000 | L4 | Units | Drywall | #F2C2F9 | 2025-03-11
Hang Drywall | 42 | Building 3000 | L4 | Units | Drywall | #F2C2F9 | 2025-03-12
Tape Finish Drywall | 41 | Building 3000 | L4 | Units | Drywall | #F2C2F9 | 2025-03-18 | 2025-03-26
Prime 1st Coat Paint Point Up | 85 | Building 3000 | L4 | Units | Paint | #F18D00 | 2025-03-27 | 2025-04-07
Rough Clean | P1 | Building 3000 | L4 | Units | Punch | #E36770 | 2025-04-23 | 2025-04-24
Install Flooring | T0 | Building 3000 | L4 | Units | Flooring & Tile | #8CE8D4 | 2025-04-25 | 2025-05-01
Meter Inspections HC AHU Startup | 53 | Building 3000 | L4 | Units | HVAC | #DDEBF7 | 2025-05-02 | 2025-05-05
Install WH, Toilets & Plumbing Fixtures | 34 | Building 3000 | L4 | Units | Plumbing | #E2EFDA | 2025-05-02 | 2025-05-07
2nd Trim | M3 | Building 3000 | L4 | Units | MEPs | #FF7C80 | 2025-05-08 | 2025-05-09
Drywall Punch | 40 | Building 3000 | L4 | Units | Drywall | #F2C2F9 | 2025-05-12 | 2025-05-13
Install Appliances | A5 | Building 3000 | L4 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-05-14 | 2025-05-15
Corrections from LMC Deficiency | O1 | Building 3000 | L4 | Units | LMC-Owners | #3E5E60 | 2025-05-16 | 2025-05-20
Final Paint | 82 | Building 3000 | L4 | Units | Paint | #F18D00 | 2025-05-21 | 2025-05-27
Final MEP Inspections | 0I | Building 3000 | L4 | Units | Inspections | #C00000 | 2025-05-28 | 2025-05-30
Hang Drywall | 42 | Building 3000 | L4 | Corridors | Drywall | #F2C2F9 | 2025-03-15 | 2025-03-17
Screw Inspection | SI | Building 3000 | L4 | Corridors | Inspections | #C00000 | 2025-03-18 | 2025-03-18
Tape Finish Drywall | 41 | Building 3000 | L4 | Corridors | Drywall | #F2C2F9 | 2025-03-19 | 2025-03-26
Trim-out MEP | M4 | Building 3000 | L4 | Corridors | MEPs | #FF7C80 | 2025-03-27 | 2025-04-02
1st Coat Paint Walls & Ceilings | 81 | Building 3000 | L4 | Corridors | Paint | #F18D00 | 2025-04-03 | 2025-04-07
Install Fire Extinguisher Cabinet | V1 | Building 3000 | L4 | Corridors | Screens/Accesories | #9195AD | 2025-04-08 | 2025-04-08
Screw Inspection | SI | Building 3000 | L4 | Corridors | Inspections | #C00000 | 2025-03-17
Install Flooring | T0 | Building 3000 | L4 | Corridors | Flooring & Tile | #8CE8D4 | 2025-05-02 | 2025-05-06
Final Paint | 82 | Building 3000 | L4 | Corridors | Paint | #F18D00 | 2025-05-28 | 2025-05-30
Install Signage | V0 | Building 3000 | L4 | Corridors | Screens/Accesories | #9195AD | 2025-06-02 | 2025-06-02
Final Clean | P2 | Building 3000 | L4 | Corridors | Punch | #E36770 | 2025-06-02 | 2025-06-02
Bldg. Final | FI | Building 3000 | L4 | Corridors | Inspections | #C00000 | 2025-06-03 | 2025-06-03
Stock Drywall | 43 | Building 3000 | L3 | Units | Drywall | #F2C2F9 | 2025-03-11 | 2025-03-11
Hang Drywall | 42 | Building 3000 | L3 | Units | Drywall | #F2C2F9 | 2025-03-15 | 2025-03-18
Screw Inspection | SI | Building 3000 | L3 | Units | Inspections | #C00000 | 2025-03-19 | 2025-03-19
Tape Finish Drywall | 41 | Building 3000 | L3 | Units | Drywall | #F2C2F9 | 2025-03-20 | 2025-03-28
Prime 1st Coat Paint Point Up | 85 | Building 3000 | L3 | Units | Paint | #F18D00 | 2025-04-08 | 2025-04-17
AHU Install, HVAC Trim Out | 52 | Building 3000 | L3 | Units | HVAC | #DDEBF7 | 2025-04-18 | 2025-04-23
1st Trim | M1 | Building 3000 | L3 | Units | MEPs | #FF7C80 | 2025-04-18 | 2025-04-24
Install Cabinets & Countertops | K3 | Building 3000 | L3 | Units | Cabinets & Tops | #D8A979 | 2025-04-25 | 2025-05-02
Rough Clean | P1 | Building 3000 | L3 | Units | Punch | #E36770 | 2025-05-05 | 2025-05-06
Install Flooring | T0 | Building 3000 | L3 | Units | Flooring & Tile | #8CE8D4 | 2025-05-07 | 2025-05-13
Meter Inspections HC AHU Startup | 53 | Building 3000 | L3 | Units | HVAC | #DDEBF7 | 2025-05-14 | 2025-05-15
Install WH, Toilets & Plumbing Fixtures | 34 | Building 3000 | L3 | Units | Plumbing | #E2EFDA | 2025-05-14 | 2025-05-16
Install Appliances | A5 | Building 3000 | L3 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-05-16 | 2025-05-19
2nd Trim | M3 | Building 3000 | L3 | Units | MEPs | #FF7C80 | 2025-05-19 | 2025-05-20
Corrections from LMC Deficiency | O1 | Building 3000 | L3 | Units | LMC-Owners | #3E5E60 | 2025-05-20 | 2025-05-22
Drywall Punch | 40 | Building 3000 | L3 | Units | Drywall | #F2C2F9 | 2025-05-21 | 2025-05-22
Final Paint | 82 | Building 3000 | L3 | Units | Paint | #F18D00 | 2025-05-23 | 2025-05-29
Final MEP Inspections | 0I | Building 3000 | L3 | Units | Inspections | #C00000 | 2025-06-02 | 2025-06-04
Final Clean | P2 | Building 3000 | L3 | Units | Punch | #E36770 | 2025-06-05 | 2025-06-06
Screw Inspection | SI | Building 3000 | L3 | Corridors | Inspections | #C00000 | 2025-03-21 | 2025-03-21
Tape Finish Drywall | 41 | Building 3000 | L3 | Corridors | Drywall | #F2C2F9 | 2025-03-22 | 2025-03-29
Trim-out MEP | M4 | Building 3000 | L3 | Corridors | MEPs | #FF7C80 | 2025-03-31 | 2025-04-04
1st Coat Paint Walls & Ceilings | 81 | Building 3000 | L3 | Corridors | Paint | #F18D00 | 2025-04-07 | 2025-04-09
Install Fire Extinguisher Cabinet | V1 | Building 3000 | L3 | Corridors | Screens/Accesories | #9195AD | 2025-04-10 | 2025-04-10
Install Flooring | T0 | Building 3000 | L3 | Corridors | Flooring & Tile | #8CE8D4 | 2025-05-14
Final Paint | 82 | Building 3000 | L3 | Corridors | Paint | #F18D00 | 2025-05-30
Final Clean | P2 | Building 3000 | L3 | Corridors | Punch | #E36770 | 2025-06-04
Install Signage | V0 | Building 3000 | L3 | Corridors | Screens/Accesories | #9195AD | 2025-06-04
Bldg. Final | FI | Building 3000 | L3 | Corridors | Inspections | #C00000 | 2025-06-05
Insulation | 71 | Building 3000 | L2 | Units | Insulation | #868CC4 | 2025-03-10
Insulation Inspection | II | Building 3000 | L2 | Units | Inspections | #C00000 | 2025-03-17 | 2025-03-17
Stock Drywall | 43 | Building 3000 | L2 | Units | Drywall | #F2C2F9 | 2025-03-18 | 2025-03-18
Hang Drywall | 42 | Building 3000 | L2 | Units | Drywall | #F2C2F9 | 2025-03-19 | 2025-03-21
Screw Inspection | SI | Building 3000 | L2 | Units | Inspections | #C00000 | 2025-03-24 | 2025-03-24
Tape Finish Drywall | 41 | Building 3000 | L2 | Units | Drywall | #F2C2F9 | 2025-03-25 | 2025-04-02
Prime 1st Coat Paint Point Up | 85 | Building 3000 | L2 | Units | Paint | #F18D00 | 2025-04-18 | 2025-04-29
AHU Install, HVAC Trim Out | 52 | Building 3000 | L2 | Units | HVAC | #DDEBF7 | 2025-04-30 | 2025-05-05
1st Trim | M1 | Building 3000 | L2 | Units | MEPs | #FF7C80 | 2025-04-30 | 2025-05-06
Install Cabinets & Countertops | K3 | Building 3000 | L2 | Units | Cabinets & Tops | #D8A979 | 2025-05-07 | 2025-05-14
Rough Clean | P1 | Building 3000 | L2 | Units | Punch | #E36770 | 2025-05-15 | 2025-05-16
Install Flooring | T0 | Building 3000 | L2 | Units | Flooring & Tile | #8CE8D4 | 2025-05-19 | 2025-05-23
Meter Inspections HC AHU Startup | 53 | Building 3000 | L2 | Units | HVAC | #DDEBF7 | 2025-05-27 | 2025-05-28
Install Appliances | A5 | Building 3000 | L2 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-05-27 | 2025-05-28
Install WH, Toilets & Plumbing Fixtures | 34 | Building 3000 | L2 | Units | Plumbing | #E2EFDA | 2025-05-27 | 2025-05-29
2nd Trim | M3 | Building 3000 | L2 | Units | MEPs | #FF7C80 | 2025-05-30 | 2025-06-02
Corrections from LMC Deficiency | O1 | Building 3000 | L2 | Units | LMC-Owners | #3E5E60 | 2025-05-29 | 2025-06-02
Drywall Punch | 40 | Building 3000 | L2 | Units | Drywall | #F2C2F9 | 2025-06-03 | 2025-06-04
Final Paint | 82 | Building 3000 | L2 | Units | Paint | #F18D00 | 2025-06-03 | 2025-06-06
Final MEP Inspections | 0I | Building 3000 | L2 | Units | Inspections | #C00000 | 2025-06-09 | 2025-06-11
Final Clean | P2 | Building 3000 | L2 | Units | Punch | #E36770 | 2025-06-12 | 2025-06-13
Hang Drywall | 42 | Building 3000 | L2 | Corridors | Drywall | #F2C2F9 | 2025-03-22
Screw Inspection | SI | Building 3000 | L2 | Corridors | Inspections | #C00000 | 2025-03-25 | 2025-03-25
Tape Finish Drywall | 41 | Building 3000 | L2 | Corridors | Drywall | #F2C2F9 | 2025-03-26 | 2025-04-02
Trim-out MEP | M4 | Building 3000 | L2 | Corridors | MEPs | #FF7C80 | 2025-04-03 | 2025-04-09
1st Coat Paint Walls & Ceilings | 81 | Building 3000 | L2 | Corridors | Paint | #F18D00 | 2025-04-10 | 2025-04-14
Install Fire Extinguisher Cabinet | V1 | Building 3000 | L2 | Corridors | Screens/Accesories | #9195AD | 2025-04-15 | 2025-04-15
Install Flooring | T0 | Building 3000 | L2 | Corridors | Flooring & Tile | #8CE8D4 | 2025-05-27 | 2025-05-29
Final Paint | 82 | Building 3000 | L2 | Corridors | Paint | #F18D00 | 2025-06-09 | 2025-06-11
Final Clean | P2 | Building 3000 | L2 | Corridors | Punch | #E36770 | 2025-06-12
Install Signage | V0 | Building 3000 | L2 | Corridors | Screens/Accesories | #9195AD | 2025-06-12
Bldg. Final | FI | Building 3000 | L2 | Corridors | Inspections | #C00000 | 2025-06-13 | 2025-06-13
Spray Foam Inspection | 7I | Building 3000 | L1 | Units | Inspections | #C00000 | 2025-03-10 | 2025-03-10
Insulation | 71 | Building 3000 | L1 | Units | Insulation | #868CC4 | 2025-03-17 | 2025-03-20
Insulation Inspection | II | Building 3000 | L1 | Units | Inspections | #C00000 | 2025-03-21
Stock Drywall | 43 | Building 3000 | L1 | Units | Drywall | #F2C2F9 | 2025-03-24 | 2025-03-24
Hang Drywall | 42 | Building 3000 | L1 | Units | Drywall | #F2C2F9 | 2025-03-22 | 2025-03-25
Screw Inspection | SI | Building 3000 | L1 | Units | Inspections | #C00000 | 2025-03-26 | 2025-03-26
Tape Finish Drywall | 41 | Building 3000 | L1 | Units | Drywall | #F2C2F9 | 2025-03-27 | 2025-04-04
Prime 1st Coat Paint Point Up | 85 | Building 3000 | L1 | Units | Paint | #F18D00 | 2025-04-30 | 2025-05-09
AHU Install, HVAC Trim Out | 52 | Building 3000 | L1 | Units | HVAC | #DDEBF7 | 2025-05-12 | 2025-05-15
1st Trim | M1 | Building 3000 | L1 | Units | MEPs | #FF7C80 | 2025-05-12 | 2025-05-16
Rough Clean | P1 | Building 3000 | L1 | Units | Punch | #E36770 | 2025-05-28 | 2025-05-29
Install Flooring | T0 | Building 3000 | L1 | Units | Flooring & Tile | #8CE8D4 | 2025-05-30 | 2025-06-05
Meter Inspections HC AHU Startup | 53 | Building 3000 | L1 | Units | HVAC | #DDEBF7 | 2025-06-06 | 2025-06-09
Install Appliances | A5 | Building 3000 | L1 | Units | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-06-06 | 2025-06-09
Install WH, Toilets & Plumbing Fixtures | 34 | Building 3000 | L1 | Units | Plumbing | #E2EFDA | 2025-06-06 | 2025-06-10
2nd Trim | M3 | Building 3000 | L1 | Units | MEPs | #FF7C80 | 2025-06-11 | 2025-06-12
Corrections from LMC Deficiency | O1 | Building 3000 | L1 | Units | LMC-Owners | #3E5E60 | 2025-06-10 | 2025-06-12
Final Paint | 82 | Building 3000 | L1 | Units | Paint | #F18D00 | 2025-06-13 | 2025-06-18
Final MEP Inspections | 0I | Building 3000 | L1 | Units | Inspections | #C00000 | 2025-06-19 | 2025-06-23
Final Clean | P2 | Building 3000 | L1 | Units | Punch | #E36770 | 2025-06-24 | 2025-06-25
Hang Drywall | 42 | Building 3000 | L1 | Corridors | Drywall | #F2C2F9 | 2025-03-26 | 2025-03-27
Install Fire Extinguisher Cabinet | V1 | Building 3000 | L1 | Corridors | Screens/Accesories | #9195AD | 2025-04-17 | 2025-04-17
Install Flooring | T0 | Building 3000 | L1 | Corridors | Flooring & Tile | #8CE8D4 | 2025-06-06 | 2025-06-10
Final Paint | 82 | Building 3000 | L1 | Corridors | Paint | #F18D00 | 2025-06-19 | 2025-06-23
Install Signage | V0 | Building 3000 | L1 | Corridors | Screens/Accesories | #9195AD | 2025-06-24 | 2025-06-24
Final Clean | P2 | Building 3000 | L1 | Corridors | Punch | #E36770 | 2025-06-24 | 2025-06-24
Bldg. Final | FI | Building 3000 | L1 | Corridors | Inspections | #C00000 | 2025-06-25 | 2025-06-25
Stub-in Mechanical | 54 | Building 3000 | L1 | Commercial / Retail | HVAC | #DDEBF7 | 2025-03-10 | 2025-03-10
Stub-in Plumbing | 36 | Building 3000 | L1 | Commercial / Retail | Plumbing | #E2EFDA | 2025-03-10 | 2025-03-10
Stub-in Electrical | 67 | Building 3000 | L1 | Commercial / Retail | Electrical | #FFF2CC | 2025-03-10 | 2025-03-10
Install Storefront Doors | H1 | Building 3000 | L1 | Commercial / Retail | Glazing (Mirrors, Blinds) | #B0AAF8 | 2025-03-10 | 2025-03-11
Install Fire Alarm Devices | 21 | Building 3000 | L1 | Commercial / Retail | Fire Protection | #FF7057 | 2025-03-11 | 2025-03-11
Stub-in Low Voltage Devices | 6B | Building 3000 | L1 | Commercial / Retail | Electrical | #FFF2CC | 2025-03-12 | 2025-03-12
Final Mechanical Inspection | 5I | Building 3000 | L1 | Commercial / Retail | Inspections | #C00000 | 2025-03-13 | 2025-03-13
Install Doors & Hardware | J0 | Building 3000 | L1 | Commercial / Retail | Doors / Hardware | #680E5B | 2025-03-12 | 2025-03-13
Final Paint | 82 | Building 3000 | L1 | Commercial Trash Room | Paint | #F18D00 | 2025-03-10 | 2025-03-13
Prime 1st Coat Paint | 85 | Building 3000 | L1 | Commercial Trash Room | Paint | #F18D00 | 2025-05-12 | 2025-05-14
Trim Out Mechanical Devices | 51 | Building 3000 | L1 | Commercial Trash Room | HVAC | #DDEBF7 | 2025-05-15 | 2025-05-15
Install Custom Light fixtures | 65 | Building 3000 | L1 | Commercial Trash Room | Electrical | #FFF2CC | 2025-05-15 | 2025-05-16
Final Mechanical Inspection | 5I | Building 3000 | L1 | Commercial Trash Room | Inspections | #C00000 | 2025-05-16 | 2025-05-16
Install Floor Drain | 36 | Building 3000 | L1 | Commercial Trash Room | Plumbing | #E2EFDA | 2025-05-15 | 2025-05-19
Final Plumbing Inspection | 3I | Building 3000 | L1 | Commercial Trash Room | Inspections | #C00000 | 2025-05-20 | 2025-05-20
Trim-out Fire Alarm Devices | 63 | Building 3000 | L1 | Commercial Trash Room | Electrical | #FFF2CC | 2025-05-20 | 2025-05-20
Trim Out Fire Sprinkler | 20 | Building 3000 | L1 | Commercial Trash Room | Fire Protection | #FF7057 | 2025-05-15 | 2025-05-21
Trim-out Low Voltage Devices | 64 | Building 3000 | L1 | Commercial Trash Room | Electrical | #FFF2CC | 2025-05-21 | 2025-05-21
Rough Clean | P1 | Building 3000 | L1 | Commercial Trash Room | Punch | #E36770 | 2025-05-22 | 2025-05-22
Bldg. Inspection | BI | Building 3000 | L1 | Commercial Trash Room | Inspections | #C00000 | 2025-06-02 | 2025-06-02
Install Trash Compactor | A9 | Building 3000 | L1 | Commercial Trash Room | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-06-02 | 2025-06-03
Final Clean | P2 | Building 3000 | L1 | Commercial Trash Room | Punch | #E36770 | 2025-06-03 | 2025-06-04
Install Doors & Hardware | J0 | Building 3000 | L1 | Commercial Trash Room | Doors / Hardware | #680E5B | 2025-06-04 | 2025-06-05
Seal Concrete Flooring | CA | Building 3000 | L1 | Bike Rooms | Concrete | #DBDBDB | 2025-04-17 | 2025-04-23
Install Bike Rack Equipment | A4 | Building 3000 | L1 | Bike Rooms | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-04-24 | 2025-04-25
Seal Concrete Flooring | CA | Building 3000 | L1 | Mail Room | Concrete | #DBDBDB | 2025-04-24 | 2025-04-30
Install Mail Box Equipment | V2 | Building 3000 | L1 | Mail Room | Screens/Accesories | #9195AD | 2025-05-01 | 2025-05-02
Insulate Ceiling | 70 | Building 3000 | L1 | Electric Rooms | Insulation | #868CC4 | 2025-03-10 | 2025-03-10
Insulate Ceiling | 70 | Building 3000 | L1 | Electric Rooms | Insulation | #868CC4 | 2025-03-10 | 2025-03-10
Inspection of Ceiling | DI | Building 3000 | L1 | Electric Rooms | Inspections | #C00000 | 2025-03-11 | 2025-03-11
1st Coat Paint Walls & Ceilings | 81 | Building 3000 | L1 | Electric Rooms | Paint | #F18D00 | 2025-03-11 | 2025-03-11
Close Ceiling | R0 | Building 3000 | L1 | Electric Rooms | Roofing | #385623 | 2025-03-12 | 2025-03-12
Final Inspection | FI | Building 3000 | L1 | Electric Rooms | Inspections | #C00000 | 2025-03-13 | 2025-03-13
Set meters | 67 | Building 3000 | L1 | Electric Rooms | Electrical | #FFF2CC | 2025-03-14 | 2025-03-20
Set Racks | V3 | Building 3000 | L1 | Electric Rooms | Screens/Accesories | #9195AD | 2025-03-10 | 2025-03-11
Punch Low Voltage Devices | 6A | Building 3000 | L1 | IDF | Electrical | #FFF2CC | 2025-03-12 | 2025-03-18
State Elevator Testing | EI | Building 3000 | L1 | Elevator | Inspections | #C00000 | 2025-04-03
Final FP Inspections and Life Safety | 1I | Building 3000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-06-24 | 2025-06-26
CofO Inspection Signoff | CI | Building 3000 | Inspections and Closeout |  | Inspections | #C00000 | 2025-06-27 | 2025-07-03
Powder Puff Clean | P3 | Building 3000 | Inspections and Closeout |  | Punch | #E36770 | 2025-07-22 | 2025-07-23
FFE | A1 | Building 3000 | Inspections and Closeout |  | Hardware/Appliances/FF&Es | #F9AFD4 | 2025-07-21 | 2025-07-23
Fill Pool Coating Tile | T4 | Pool |  |  | Flooring & Tile | #8CE8D4 | 2025-04-02
Fill Pool and Treat | T5 | Pool |  |  | Flooring & Tile | #8CE8D4 | 2025-04-09
Final Testing and Commissioning | O3 | Pool |  |  | LMC-Owners | #3E5E60 | 2025-04-16
Pool Inspection by Local Health Department | PI | Pool |  |  | Inspections | #C00000 | 2025-04-23 | 2025-04-29
Install Hardscapes | L0 | Hardscapes / Landscapes |  |  | Landscaping / Hardscaping | #C32BA2 | 2025-03-10
Install Hardscapes | L0 | Hardscapes / Landscapes |  |  | Landscaping / Hardscaping | #C32BA2 | 2025-05-05
Install Hardscapes | L0 | Hardscapes / Landscapes |  |  | Landscaping / Hardscaping | #C32BA2 | 2025-05-19
Install Landscapes | L1 | Hardscapes / Landscapes |  |  | Landscaping / Hardscaping | #C32BA2 | 2025-06-03
Chlorination of Water System | LP | Hardscapes / Landscapes |  |  | Courtyards/Amenities | #A9D08E | 2025-05-21 | 2025-06-04