## Sheet1
phase | area | zone | trade | color | activity_code | wbs_code | activity_category | activity_name | start | finish
Milestones | General | N/A | CLAYCO | #EE5A1C | M-C | CHI-11-03-PROP-F | MATCHING | GEN MS- Clayco Proposal Due date | 12-Apr-2024 | 12-Apr-2024
Milestones | General | N/A | CLAYCO | #EE5A1C | M-C | CHI-11-03-MOB-S | MATCHING | GEN MS- GC Mobilization Start | 24-Jul-2024 | 24-Jul-2024
Milestones | General | N/A | CLAYCO | #EE5A1C | M-C | CHI-11-03-EW-S | MATCHING | GEN MS- Earthworks & U/G Utilities Start | 19-Aug-2024 | 19-Aug-2024
Milestones | General | N/A | CLAYCO | #EE5A1C | M-C | CHI-11-03-PAD-F | MATCHING | GEN MS- Building Footprint Pad Ready | 04-Sep-2024 | 04-Sep-2024
Milestones | General | N/A | CLAYCO | #EE5A1C | M-C | CHI-11-03-MOB-F | MATCHING | GEN MS- GC Mobilization Finish/ Site Secured | 16-Sep-2024 | 16-Sep-2024
Milestones | General | N/A | CLAYCO | #EE5A1C | M-C | CHI-11-03-PSR-F | MATCHING | GEN MS- PSR (Contract) Executed | 30-Sep-2024 | 30-Sep-2024
Milestones | General | N/A | CLAYCO | #EE5A1C | M-C | CHI-11-03-LHP-F | MATCHING | GEN MS- Complete Landscaping/ Hardscaping | 19-Nov-2025 | 19-Nov-2025
Milestones | Admin/ COLO 3 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-03-ROJ-S | MATCHING | Admin/COLO3- Start First ROJ CLAYCO Took over Storage 9/2/2024 | 02-Sep-2024 | 02-Sep-2024
Milestones | Admin/ COLO 3 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-03-FND-S | MATCHING | Admin/COLO3- Start Foundation | 19-Sep-2024 | 19-Sep-2024
Milestones | Admin/ COLO 3 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-03-FND-F | MATCHING | Admin/COLO3- Complete Foundation | 09-Oct-2024 | 09-Oct-2024
Milestones | Admin/ COLO 3 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-03-SUP-S | MATCHING | Admin/COLO3- Start Superstructure | 14-Oct-2024 | 14-Oct-2024
Milestones | Admin/ COLO 3 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-03-UGE-F | MATCHING | Admin/COLO3- Complete U/G Utilities/ MV UG Electrical | 14-Dec-2024 | 14-Dec-2024
Milestones | Admin/ COLO 3 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-03-SUP-F | MATCHING | Admin/COLO3- Complete Superstructure | 14-Dec-2024 | 14-Dec-2024
Milestones | Admin/ COLO 3 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-03-UGU-F | MATCHING | Admin/COLO3- Complete U/G Utilities (No Elec) | 14-Dec-2024 | 14-Dec-2024
Milestones | Admin/ COLO 3 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-03-DRY-F | MATCHING | Admin/COLO3- Complete Weather Tight | 06-Jan-2025 | 06-Jan-2025
Milestones | Admin/ COLO 3 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-03-SOG-F | MATCHING | Admin/COLO3- Complete SOG | 06-Jan-2025 | 06-Jan-2025
Milestones | Admin/ COLO 3 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-03-ROJ-F | MATCHING | Admin/COLO3- Complete Last ROJ | 03-Apr-2025 | 03-Apr-2025
Milestones | Admin/ COLO 3 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-03-L1CX-S | MATCHING | Admin/COLO3- Start L1 CX | 17-Mar-2025 | 17-Mar-2025
Milestones | Admin/ COLO 3 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-03-L2CX-S | MATCHING | Admin/COLO3- Start L2 CX (Yellow Tag) | 19-Mar-2025 | 19-Mar-2025
Milestones | Admin/ COLO 3 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-03-POW-F | MATCHING | Admin/COLO3- Complete Utility Power- On | 15-May-2025 | 15-May-2025
Milestones | Admin/ COLO 3 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-03-L1CX-F | MATCHING | Admin/COLO3- Complete L1 Cx (All Red Tags/ ROJ) | 09-Jul-2025 | 09-Jul-2025
Milestones | Admin/ COLO 3 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-03-L3CX-F | MATCHING | Admin/COLO3- Complete CX L3 (Green Tag) | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-03-L4CX-S | MATCHING | Admin/COLO3- Start L4 Cx (Blue Tag) | 15-Aug-2025 | 15-Aug-2025
Milestones | Admin/ COLO 3 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-03-L4CX-F | MATCHING | Admin/COLO3- Complete L4 Cx (Blue Tag) | 15-Sep-2025 | 15-Sep-2025
Milestones | Admin/ COLO 3 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-03-L5CX-S | MATCHING | Admin/COLO3- Start L5 Cx (White Tag) | 16-Sep-2025 | 16-Sep-2025
Milestones | Admin/ COLO 3 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-03-L5CX-F | MATCHING | Admin/COLO3- Cx L5 IST Complete (White Tag) | 18-Sep-2025 | 18-Sep-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-BNU-F | MATCHING | Admin/COLO3- Beneficial Use | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-BND-F | MATCHING | Admin/COLO3- Beneficial Use (IDF#1,#2,#3 & #4) | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-BSA-F | MATCHING | Admin/COLO3- Beneficial Use- Security Operations Center (SOC) | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-BSL-F | MATCHING | Admin/COLO3- Beneficial Use- Security Low Voltage (SLV) System | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-RoIP-F | MATCHING | Admin/COLO3- Beneficial Use - Radio Over Internet Protocol (RoIP) | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-MOR-F | MATCHING | Admin/COLO3- Beneficial Use - Middle of Row (MOR) Cabinets | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-BRN-F | MATCHING | Admin/COLO3- Beneficial Use- Regional Network Gateway (RNG) | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-BNS-F | MATCHING | Admin/COLO3- Beneficial Use - Security Equipment Room (SER) | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-BFA-F | MATCHING | Admin/COLO3- Beneficial Use- Facilities Operations Center (FOC) | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-BSC-F | MATCHING | Admin/COLO3- Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-DAS-F | MATCHING | Admin/COLO3- Beneficial Use - Distributed Antenna System (DAS) | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-BNF-F | MATCHING | Admin/COLO3- Beneficial Use - Facility Cable Room (FCR) | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-BNM-F | MATCHING | Admin/COLO3- Beneficial Use - Meet Me Room or Entry Rooms (MMR/ER) | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-BSHVS-F | MATCHING | Admin/COLO3- Beneficial Use - Secure & High Value Storage Rooms | 14-Aug-2025 | 14-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-03-RNI-F | MATCHING | Admin/COLO3- RNI | 20-Aug-2025 | 20-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-03-P1ST-F | MATCHING | Admin/COLO3- Phase 1 Security Pre-Testing Complete | 30-Aug-2025 | 30-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-03-EPMS-F | MATCHING | Admin/COLO3- Complete EPMS Testing | 30-Aug-2025 | 30-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-03-BAS-F | MATCHING | Admin/COLO3- Complete BAS Testing | 30-Aug-2025 | 30-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-03-FIR-F | MATCHING | Admin/COLO3- Complete Fire Alarm | 30-Aug-2025 | 30-Aug-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-03-P2ST-F | MATCHING | Admin/COLO3- Phase 2 Security Pre-Testing Complete | 04-Sep-2025 | 04-Sep-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-03-P3ST-F | MATCHING | Admin/COLO3- Phase 3 Security Pre-Testing Complete | 25-Sep-2025 | 25-Sep-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-03-TCO-F | MATCHING | Admin/COLO3- TCO / C of O | 30-Sep-2025 | 30-Sep-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-03-FITOUT-F | MATCHING | Admin/COLO- Admin & COLO3-5 Fitout Complete | 01-Oct-2025 | 01-Oct-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-03-SC-F | MATCHING | Admin/COLO3- Substantial Completion | 01-Oct-2025 | 01-Oct-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-03-BFN-F | MATCHING | Admin/COLO3- Beneficial Use - All Facility & Network Telecom Access/ Devices etc. | 01-Oct-2025 | 01-Oct-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-03-FC-F | MATCHING | Admin/COLO3- Final Completion/ Turnover to Operations | 02-Oct-2025 | 02-Oct-2025
Milestones | Admin/ COLO 3 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-03-SL-F | MATCHING | Admin/COLO3- Security Lockdown | 02-Oct-2025 | 02-Oct-2025
Milestones | COLO 4 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-04-ROJ-S | MATCHING | COLO4- Start First ROJ CLAYCO Took over Storage 9/2/2024 | 02-Sep-2024 | 02-Sep-2024
Milestones | COLO 4 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-04-FND-S | MATCHING | COLO4- Foundation Start | 19-Sep-2024 | 19-Sep-2024
Milestones | COLO 4 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-04-FND-F | MATCHING | COLO4- Complete Foundation | 31-Oct-2024 | 31-Oct-2024
Milestones | COLO 4 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-04-SUP-S | MATCHING | COLO4- Start Superstructure | 01-Nov-2024 | 01-Nov-2024
Milestones | COLO 4 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-04-UGE-F | MATCHING | COLO4- Complete U/G Utilities/ MV UG Electric | 06-Jan-2025 | 06-Jan-2025
Milestones | COLO 4 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-04-SUP-F | MATCHING | COLO4- Complete Superstructure | 11-Jan-2025 | 11-Jan-2025
Milestones | COLO 4 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-04-DRY-F | MATCHING | COLO4- Weather Tight | 17-Jan-2025 | 17-Jan-2025
Milestones | COLO 4 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-04-SOG-F | MATCHING | COLO4- Complete SOG | 17-Jan-2025 | 17-Jan-2025
Milestones | COLO 4 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-04-ROJ-F | MATCHING | COLO4- Complete Last ROJ | 16-Apr-2025 | 16-Apr-2025
Milestones | COLO 4 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-04-GEN-F | MATCHING | COLO4- Generator Ready for Fuel | 01-Jul-2025 | 01-Jul-2025
Milestones | COLO 4 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-04-L1CX-S | MATCHING | COLO4- Start L1 CX | 10-Apr-2025 | 10-Apr-2025
Milestones | COLO 4 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-04-L2CX-S | MATCHING | COLO4- Start L2 CX (Yellow Tag) | 22-Apr-2025 | 22-Apr-2025
Milestones | COLO 4 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-04-POW-F | MATCHING | COLO4- Complete Utility Power- On | 15-May-2025 | 15-May-2025
Milestones | COLO 4 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-04-L1CX-F | MATCHING | COLO4- Complete L1 Cx (All Red Tags/ ROJ) | 13-Jun-2025 | 13-Jun-2025
Milestones | COLO 4 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-04-L3Cx-F | MATCHING | COLO4- CX L3 Complete | 19-Sep-2025 | 19-Sep-2025
Milestones | COLO 4 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-04-L4CX-S | MATCHING | COLO4- Start L4 Cx (Blue Tag) | 20-Sep-2025 | 20-Sep-2025
Milestones | COLO 4 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-04-L4CX-F | MATCHING | COLO4- Complete L4 Cx (Blue Tag) | 16-Oct-2025 | 16-Oct-2025
Milestones | COLO 4 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-04-L5CX-S | MATCHING | COLO4- Start L5 Cx (White Tag) | 17-Oct-2025 | 17-Oct-2025
Milestones | COLO 4 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-04-L5Cx-F | MATCHING | COLO4- Cx L5 IST Complete | 20-Oct-2025 | 20-Oct-2025
Milestones | COLO 4 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-04-BND-F | MATCHING | COLO4- Beneficial Use- (IDF#1,#2,#3 & #4) | 19-Sep-2025 | 19-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-04-BNU-F | MATCHING | COLO4- Beneficial Use | 19-Sep-2025 | 19-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-04-MOR-F | MATCHING | COLO4- Beneficial Use- Middle of Row (MOR) Cabinets | 19-Sep-2025 | 19-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-04-BSC-F | MATCHING | COLO4- Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets | 19-Sep-2025 | 19-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-04-BSL-F | MATCHING | COLO4- Beneficial Use - Security Low Voltage (SLV) Systems | 19-Sep-2025 | 19-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-04-RoIP-F | MATCHING | COLO4- Beneficial Use- Radio OVer Internet Protocol (RoIP) | 19-Sep-2025 | 19-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-04-DAS-F | MATCHING | COLO4- Beneficial Use - Distrbuted Antenna System (DAS) | 19-Sep-2025 | 19-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-04-BFA-F | MATCHING | COLO4- Beneficial Use- Facilities Operations Center (FOC) | 19-Sep-2025 | 19-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-04-BNF-F | MATCHING | COLO4- Beneficial Use- Facility Cable Room (FCR) | 19-Sep-2025 | 19-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-04-BNM-F | MATCHING | COLO4- Beneficial Use- Meet Me Room or Entry Rooms (MMR/ER) | 19-Sep-2025 | 19-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-04-BSHVS-F | MATCHING | COLO4- Beneficial Use- Secure & High Value Storage Rooms | 19-Sep-2025 | 19-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP4 | CHI-11-04-RNI-F | MATCHING | COLO4- Ready for Network Install | 24-Sep-2025 | 24-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-04-P1ST-F | MATCHING | COLO4- Phase 1 Security Pre-Testing Complete | 30-Sep-2025 | 30-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-04-EPMS-F | MATCHING | COLO4- Complete EPMS Testing | 30-Sep-2025 | 30-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-04-BAS-F | MATCHING | COLO4- Complete BAS Testing | 30-Sep-2025 | 30-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-04-FIR-F | MATCHING | COLO4- Complete Fire Alarm | 30-Sep-2025 | 30-Sep-2025
Milestones | COLO 4 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-04-P2ST-F | MATCHING | COLO4- Phase 2 Security Pre-Testing Complete | 04-Oct-2025 | 04-Oct-2025
Milestones | COLO 4 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-04-P3ST-F | MATCHING | COLO4- Phase 3 Security Pre-Testing Complete | 23-Oct-2025 | 23-Oct-2025
Milestones | COLO 4 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-04-TCO-F | MATCHING | COLO4- TCO / C of O | 29-Oct-2025 | 29-Oct-2025
Milestones | COLO 4 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-04-SC-F | MATCHING | COLO4- Substantial Completion | 29-Oct-2025 | 29-Oct-2025
Milestones | COLO 4 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-04-FC-F | MATCHING | COLO4- Final Completion/ Turnover to Operations | 06-Nov-2025 | 06-Nov-2025
Milestones | COLO 4 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-04-SL-F | MATCHING | COLO4- Security Lockdown | 06-Nov-2025 | 06-Nov-2025
Milestones | COLO 5 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-05-ROJ-S | MATCHING | COLO5- Start First ROJ - CLAYCO Took over Storage 9/2/2024 | 02-Sep-2024 | 02-Sep-2024
Milestones | COLO 5 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-05-FND-S | MATCHING | COLO5- Foundation Start | 19-Sep-2024 | 19-Sep-2024
Milestones | COLO 5 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-05-SUP-S | MATCHING | COLO5- Start Superstructure | 12-Nov-2024 | 12-Nov-2024
Milestones | COLO 5 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-05-FND-F | MATCHING | COLO5- Complete Foundation | 12-Nov-2024 | 12-Nov-2024
Milestones | COLO 5 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-05-UGE-F | MATCHING | COLO5- Complete U/G Utilities/ MV UG Electric | 22-Jan-2025 | 22-Jan-2025
Milestones | COLO 5 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-05-SUP-F | MATCHING | COLO5- Complete Superstructure | 22-Jan-2025 | 22-Jan-2025
Milestones | COLO 5 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-05-DRY-F | MATCHING | Weather Tight - Entire Building | 07-Feb-2025 | 07-Feb-2025
Milestones | COLO 5 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-05-SOG-F | MATCHING | COLO5- Complete SOG | 07-Feb-2025 | 07-Feb-2025
Milestones | COLO 5 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-05-ROJ-F | MATCHING | COLO5- Complete Last ROJ | 02-May-2025 | 02-May-2025
Milestones | COLO 5 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-05-GEN-F | MATCHING | COLO5- Generator Ready for Fuel | 01-Aug-2025 | 01-Aug-2025
Milestones | COLO 5 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-05-L1CX-S | MATCHING | COLO5- Start L1 CX | 29-Apr-2025 | 29-Apr-2025
Milestones | COLO 5 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-05-L2CX-S | MATCHING | COLO5- Start L2 CX (Yellow Tag) | 05-May-2025 | 05-May-2025
Milestones | COLO 5 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-05-POW-F | MATCHING | COLO5- Complete Utility Power- On | 15-May-2025 | 15-May-2025
Milestones | COLO 5 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-05-L3CX-F | MATCHING | COLO5- CX Level 3 Complete | 11-Oct-2025 | 11-Oct-2025
Milestones | COLO 5 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-05-L4CX-S | MATCHING | COLO5- Start L4 Cx (Blue Tag) | 17-Oct-2025 | 17-Oct-2025
Milestones | COLO 5 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-05-L4CX-F | MATCHING | COLO5- Complete L4 Cx (Blue Tag) | 15-Nov-2025 | 15-Nov-2025
Milestones | COLO 5 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-05-L5CX-S | MATCHING | COLO5- Start L5 Cx (White Tag) | 17-Nov-2025 | 17-Nov-2025
Milestones | COLO 5 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-05-L5CX-F | MATCHING | COLO5- Cx Level 5 IST Complete | 19-Nov-2025 | 19-Nov-2025
Milestones | COLO 5 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-05-BND-F | MATCHING | COLO5- Beneficial Use (IDF#1,#2,#3 & #4) | 11-Oct-2025 | 11-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-05-BNU-F | MATCHING | COLO5- Beneficial Use | 11-Oct-2025 | 11-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-05-BMOR-F | MATCHING | COLO5- Beneficial Use- Middle of Row (MOR) Cabinets | 11-Oct-2025 | 11-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-05-BSC-F | MATCHING | COLO5- Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets | 11-Oct-2025 | 11-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-05-BSL-F | MATCHING | COLO5- Beneficial Use - Security Low Voltage (SLV) System | 11-Oct-2025 | 11-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-05-RoIP-F | MATCHING | COLO5- Beneficial Use- Radio Over Internet Protocol (RoIP) | 11-Oct-2025 | 11-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-05-DAS-F | MATCHING | COLO5- Beneficial Use - Distributed Antenna System (DAS) | 11-Oct-2025 | 11-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-05-BNF-F | MATCHING | COLO5- Beneficial Use Facility Cable Room (FCR) | 11-Oct-2025 | 11-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-05-BNM-F | MATCHING | COLO5- Beneficial Use Meet Me Room or Entry Rooms (MMR/ER) | 11-Oct-2025 | 11-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP1 | CHI-11-05-BSHVS-F | MATCHING | COLO5- Beneficial Use Secure & High Value Storage Rooms | 11-Oct-2025 | 11-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | MEP | #FF7BFF | MEP4 | CHI-11-05-RNI-F | MATCHING | COLO5- Ready for Network Install | 17-Oct-2025 | 17-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-05-P1ST-F | MATCHING | COLO5- Phase 1 Security Pre-Testing Complete | 31-Oct-2025 | 31-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-05-EPMS-F | MATCHING | COLO5- Complete EPMS Testing | 31-Oct-2025 | 31-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-05-BAS-F | MATCHING | COLO5- Complete BAS Testing | 31-Oct-2025 | 31-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-05-FIR-F | MATCHING | COLO5- Complete Fire Alarm | 31-Oct-2025 | 31-Oct-2025
Milestones | COLO 5 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-05-P2ST-F | MATCHING | COLO5- Phase 2 Security Pre-Testing Complete | 03-Nov-2025 | 03-Nov-2025
Milestones | COLO 5 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-05-P3ST-F | MATCHING | COLO5- Phase 3 Security Pre-Testing Complete | 26-Nov-2025 | 26-Nov-2025
Milestones | COLO 5 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-05-TCO-F | MATCHING | COLO5- TCO / C of O | 02-Dec-2025 | 02-Dec-2025
Milestones | COLO 5 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-05-SC-F | MATCHING | COLO5- Substantial Completion | 02-Dec-2025 | 02-Dec-2025
Milestones | COLO 5 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-05-FC-F | MATCHING | COLO5- Final Completion/Turnover to Operations | 04-Dec-2025 | 04-Dec-2025
Milestones | COLO 5 | Beneficial Use/ TCO | CLAYCO | #EE5A1C | M-C | CHI-11-05-SL-F | MATCHING | COLO5- Secuirty Lockdown | 04-Dec-2025 | 04-Dec-2025
Milestones | COLO 5 | Clayco Key Milestones | CLAYCO | #EE5A1C | M-C | CHI-11-MS-01 | MATCHING | CHI11: Construction Start | 19-Aug-2024 | 19-Aug-2024
Milestones | COLO 5 | Clayco Key Milestones | CLAYCO | #EE5A1C | M-C | CHI-11-MS-02 | MATCHING | CHI11: Building Pad Ready | 04-Sep-2024 | 04-Sep-2024
Milestones | COLO 5 | Clayco Key Milestones | CLAYCO | #EE5A1C | M-C | CHI-11-MS-04 | MATCHING | CHI11: Structure Start | 14-Oct-2024 | 14-Oct-2024
Milestones | COLO 5 | Clayco Key Milestones | CLAYCO | #EE5A1C | M-C | CHI-11-MS-03 | MATCHING | CHI11: Foundations Complete | 12-Nov-2024 | 12-Nov-2024
Milestones | COLO 5 | Clayco Key Milestones | CLAYCO | #EE5A1C | M-C | CHI-11-MS-05 | MATCHING | CHI11: Structure Complete | 21-Nov-2024 | 21-Nov-2024
Milestones | COLO 5 | Clayco Key Milestones | CLAYCO | #EE5A1C | M-C | CHI-11-MS-08 | MATCHING | CHI11: Enclosure Complete | 17-Jan-2025 | 17-Jan-2025
Milestones | COLO 5 | Clayco Key Milestones | CLAYCO | #EE5A1C | M-C | CHI-11-MS-07 | MATCHING | CHI11: Roofing Complete | 17-Jan-2025 | 17-Jan-2025
Milestones | COLO 5 | Clayco Key Milestones | CLAYCO | #EE5A1C | M-C | CHI-11-MS-09 | MATCHING | CHI11: Electrical Service Available | 15-May-2025 | 15-May-2025
Milestones | COLO 5 | Clayco Key Milestones | CLAYCO | #EE5A1C | M-C | CHI-11-MS-10 | MATCHING | CHI11: Commissioning Complete | 19-Nov-2025 | 19-Nov-2025
Milestones | COLO 5 | Clayco Key Milestones | CLAYCO | #EE5A1C | M-C | CHI-11-MS-11 | MATCHING | CHI11: Substantial Completion | 02-Dec-2025 | 02-Dec-2025
Milestones | COLO 5 | Clayco Key Milestones | CLAYCO | #EE5A1C | M-C | CHI-11-MS-12 | MATCHING | CHI11: Final Completion (SC+40d) | 22-Jan-2026 | 22-Jan-2026
Milestones | COLO 5 | Clayco Key Milestones | CLAYCO | #EE5A1C | M-C | CHI-11-MS-13 | MATCHING | CHI11: Closeout Complete | 22-Jan-2026 | 22-Jan-2026
Preconstruction | RFP / PSR | N/A | MSFT | #3DCD3A | CX2 | CHI11-RFP-10 | MATCHING | RFP- RFP Issued (Revised 3.21.24) and Proposal Due to MSFT | 25-Mar-2024 | 12-Apr-2024
Preconstruction | RFP / PSR | N/A | MSFT | #3DCD3A | CX3 | CHI11-RFP-15 | MATCHING | RFP- Microsoft Reviews Proposals | 15-Apr-2024 | 03-May-2024
Preconstruction | RFP / PSR | N/A | MSFT | #3DCD3A | CX4 | CHI11-RFP-20 | MATCHING | RFP- Microsoft Awards CHI11 | 06-May-2024 | 05-Jun-2024
Preconstruction | RFP / PSR | N/A | MSFT | #3DCD3A | CX5 | CHI11-RFP-25 | MATCHING | RFP- PSR Executed (Early Works) | 06-Jun-2024 | 06-Jun-2024
Preconstruction | RFP / PSR | N/A | MSFT | #3DCD3A | CX6 | CHI11-RFP-30 | MATCHING | RFP- PSR Executed (Full GMP) | 30-Sep-2024 | 30-Sep-2024
Preconstruction | BIM | N/A | BIM | #4679FF | BIM1 | CHI11-BIM-10 | MATCHING | BIM- BIM Kickoff | 18-Jul-2024 | 18-Jul-2024
Preconstruction | BIM | N/A | BIM | #4679FF | BIM2 | CHI11-BIM-15 | MATCHING | BIM- UG BIM Co-ordination | 19-Jul-2024 | 26-Sep-2024
Preconstruction | BIM | Coordination | BIM | #4679FF | BIM3 | CHI11-BIM-20 | MATCHING | BIM- Above ground BIM Co-ordination | 27-Sep-2024 | 03-Apr-2025
Procurement | Early Awards | N/A | OFCI | #900208 | M42 | CHI11-PROC-10 | MATCHING | PROCUREMENT- ARL & Subcontractor Awards | 07-Jun-2024 | 07-Sep-2024
Procurement | Early Awards | N/A | OFCI | #900208 | M12 | CHI11-PROC-15 | MATCHING | PROCUREMENT- Buyouts & Early Procurement | 07-Jun-2024 | 30-Sep-2024
Procurement MSFT OFCI ROJ Dates | COLO 3 | Busway / Busplugs | OFCI | #900208 | M27 | CHI-11-03-BUS-01 | MATCHING | Admin/C03- OFCI- Receive Busway / Busplugs (Starline Holding) (Del Date- 4/30/24) | 30-Apr-2024 | 30-Apr-2024
Procurement MSFT OFCI ROJ Dates | COLO 3 | Busway / Busplugs | OFCI | #900208 | M11 | CHI-11-03-BUS-02 | MATCHING | Admin/C03- OFCI- Busway / Busplugs (Starline Holding) Shipping/ ROJ | 19-Mar-2025 | 19-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Busway / Busplugs | OFCI | #900208 | M43 | CHI-11-03-BUS-03 | MATCHING | Admin/C03- OFCI- Busway / Busplugs (Starline Holding) Delivered | 19-Mar-2025 | 19-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | PEMB Procurement (1st Del) | OFCI | #900208 | M44 | CHI-11-03-PEMB-01 | MATCHING | Admin/C03-5- OFCI- Receive PEMB Procurement (1st Del) (Nucor) (SOW Del Date-10/3/24) | 14-Oct-2024 | 14-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 3 | PEMB Procurement (1st Del) | OFCI | #900208 | M18 | CHI-11-03-PEMB-02 | MATCHING | Admin/C03-5- OFCI- PEMB Procurement (1st Del) (Nucor) Shipping/ ROJ | 14-Oct-2024 | 14-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 3 | PEMB Procurement (1st Del) | OFCI | #900208 | M18 | CHI-11-03-PEMB-03 | MATCHING | Admin/C03-5- OFCI- PEMB Procurement (1st Del) (Nucor) Delivered | 14-Oct-2024 | 14-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 3 | LV Switchgear | OFCI | #900208 | M14 | CHI-11-03-LVS-01 | MATCHING | Admin/C03- OFCI- Receive LV Switchgear (LVS) (Eaton) (SOW Del Date- 2/28/25) | 28-Feb-2025 | 28-Feb-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | LV Switchgear | OFCI | #900208 | M14 | CHI-11-03-LVS-02 | MATCHING | Admin/C03- OFCI- LV Switchgear (LVS) (Eaton) Shipping/ ROJ | 17-Mar-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | LV Switchgear | OFCI | #900208 | M14 | CHI-11-03-LVS-03 | MATCHING | Admin/C03- OFCI- LV Switchgear (LVS) (Eaton) Delivered | 03-Apr-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Automatic Transfer Switches | OFCI | #900208 | M24 | CHI-11-03-ATS-01 | MATCHING | Admin/C03- OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 2/1/25) | 20-Jan-2025 | 20-Jan-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Automatic Transfer Switches | OFCI | #900208 | MH8 | CHI-11-03-ATS-02 | MATCHING | Admin/C03- OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ ROJ | 31-Mar-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Automatic Transfer Switches | OFCI | #900208 | MH8 | CHI-11-03-ATS-03 | MATCHING | Admin/C03- OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered | 03-Apr-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Elec Performance Monitoring System | OFCI | #900208 | MH28 | CHI-11-03-EPMS-01 | MATCHING | Admin/C03- OFCI- Receive Elec. Performance Monitoring System (EPMS) (Schneider) (SOW Del Date- 4/30/24) | 20-Sep-2024 | 20-Sep-2024
Procurement MSFT OFCI ROJ Dates | COLO 3 | Power Distribution Units | OFCI | #900208 | M34 | CHI-11-03-PDU-01 | MATCHING | Admin/C03- OFCI- Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 2/15/25) | 04-Jan-2025 | 04-Jan-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Power Distribution Units | OFCI | #900208 | M21 | CHI-11-03-PDU-02 | MATCHING | Admin/C03- OFCI- Power Distribution Units (PDU) Shipping/ ROJ | 07-Apr-2025 | 10-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Power Distribution Units | OFCI | #900208 | M21 | CHI-11-03-PDU-03 | MATCHING | Admin/C03- OFCI- Power Distribution Units (PDU) Delivered | 10-Apr-2025 | 10-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Air Handling Units | OFCI | #900208 | M22 | CHI-11-03-AHU-01 | MATCHING | Admin/C03- OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/04/24) | 09-Oct-2024 | 09-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 3 | Air Handling Units | OFCI | #900208 | MH6 | CHI-11-03-AHU-02 | MATCHING | Admin/C03- OFCI- Air Handling Units (AHU) (Stulz) Shipped/ROJ | 13-Mar-2025 | 02-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Air Handling Units | OFCI | #900208 | MH6 | CHI-11-03-AHU-03 | MATCHING | Admin/C03- OFCI- Air Handling Units (AHU) (Stulz) Delivered | 02-Apr-2025 | 02-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Packaged Diesel Generator Set | OFCI | #900208 | M32 | CHI-11-03-GEN-01 | MATCHING | Admin/C03- OFCI- Receive Packaged Diesel Generator Set (CAT Holt) (SOW Del Date- 5/14/24) | 17-Oct-2024 | 17-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 3 | Packaged Diesel Generator Set | OFCI | #900208 | M19 | CHI-11-03-GEN-02 | MATCHING | Admin/C03- OFCI- Packaged Diesel Generator Set (CAT Holt) Shipping/ ROJ | 06-Mar-2025 | 14-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Packaged Diesel Generator Set | OFCI | #900208 | M19 | CHI-11-03-GEN-03 | MATCHING | Admin/C03- OFCI- Packaged Diesel Generator Set (CAT Holt) Delivered | 14-Mar-2025 | 14-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Medium Voltage Switchgear | OFCI | #900208 | M31 | CHI-11-03-MVS-01 | MATCHING | Admin/C03- OFCI- Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 7/30/24) | 15-Oct-2024 | 15-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 3 | Medium Voltage Switchgear | OFCI | #900208 | M17 | CHI-11-03-MVS-02 | MATCHING | Admin/C03- OFCI- Medium Voltage Switchgear (MVS) (JD Power Sys) Shipping/ ROJ | 28-Mar-2025 | 14-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Medium Voltage Switchgear | OFCI | #900208 | M17 | CHI-11-03-MVS-03 | MATCHING | Admin/C03- OFCI- Medium Voltage Switchgear (MVS) (JD Power Sys) Delivered | 14-Apr-2025 | 14-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | UPS System W / Battery | OFCI | #900208 | M36 | CHI-11-03-UPS-01 | MATCHING | Admin/C03- OFCI- Received SUB Warehouse 9/28/2023 UPS System w/ Battery (UPS) (Eaton) (SOW Del Date- 8/13/23) | 02-Sep-2024 | 02-Sep-2024
Procurement MSFT OFCI ROJ Dates | COLO 3 | UPS System W / Battery | OFCI | #900208 | M40 | CHI-11-03-UPS-02 | MATCHING | Admin/C03- OFCI- UPS System w/ Battery (UPS) (Eaton) Shipping/ ROJ | 26-Mar-2025 | 31-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | UPS System W / Battery | OFCI | #900208 | M40 | CHI-11-03-UPS-03 | MATCHING | Admin/C03- OFCI- UPS System w/ Battery (UPS) (Eaton) Delivered | 31-Mar-2025 | 31-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Building Automation System | OFCI | #900208 | M26 | CHI-11-03-BAS-01 | MATCHING | Admin/C03- OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 2/15/25) | 07-Mar-2025 | 07-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Building Automation System | OFCI | #900208 | M10 | CHI-11-03-BAS-02 | MATCHING | Admin/C03- OFCI- Building Automation System (BAS) (ALC) Shipping/ ROJ | 10-Mar-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Building Automation System | OFCI | #900208 | M10 | CHI-11-03-BAS-03 | MATCHING | Admin/C03- OFCI- Building Automation System (BAS) (ALC) Delivered | 03-Apr-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Auto Transfer Control Panel | OFCI | #900208 | M23 | CHI-11-03-TCP-01 | MATCHING | Admin/C03- OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date- 3/8/2025) | 03-Apr-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Auto Transfer Control Panel | OFCI | #900208 | MH7 | CHI-11-03-TCP-02 | MATCHING | Admin/C03- OFCI- Auto Transfer Control Panel (TCP) Shipping/ ROJ | 03-Apr-2025 | 10-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Auto Transfer Control Panel | OFCI | #900208 | MH7 | CHI-11-03-TCP-03 | MATCHING | Admin/C03- OFCI- Auto Transfer Control Panel (TCP) Delivered | 10-Apr-2025 | 10-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Auxillary Power Distribution | OFCI | #900208 | M25 | CHI-11-03-ADP-01 | MATCHING | Admin/C03- OFCI- Receive Auxillary (Mech) Power Distribution Panels (ADP) (Del Date- 3/8/2025) | 27-Feb-2025 | 27-Feb-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Auxillary Power Distribution | OFCI | #900208 | MH9 | CHI-11-03-ADP-02 | MATCHING | Admin/C03- OFCI- Auxillary (Mech) Power Distribution Panels (ADP) Shipping/ ROJ | 21-Mar-2025 | 28-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Auxillary Power Distribution | OFCI | #900208 | MH9 | CHI-11-03-ADP-03 | MATCHING | Admin/C03- OFCI- Auxillary (Mech) Power Distribution Panels (ADP) Delivered | 28-Mar-2025 | 28-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Utility Pad Mount Switchgear | OFCI | #900208 | M35 | CHI-11-03-UPM-01 | MATCHING | Admin/C03- OFCI- Receive Utility Pad Mount Switchgear (Del Date- 7/30/2024) | 23-Oct-2024 | 23-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 3 | Utility Pad Mount Switchgear | OFCI | #900208 | M41 | CHI-11-03-UPM-02 | MATCHING | Admin/C03- OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ ROJ | 26-Mar-2025 | 15-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Utility Pad Mount Switchgear | OFCI | #900208 | M41 | CHI-11-03-UPM-03 | MATCHING | Admin/C03- OFCI- Utility Pad Mount Switchgear (UPM) Delivered | 15-Apr-2025 | 15-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Pad Mounted Transformers | OFCI | #900208 | M33 | CHI-11-03-XFM-01 | MATCHING | Admin/C03- OFCI- Receive Pad Mounted Transformers (XFM-TX) (Del Date- 7/30/2024) | 15-Oct-2024 | 15-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 3 | Pad Mounted Transformers | OFCI | #900208 | M20 | CHI-11-03-XFM-02 | MATCHING | Admin/C03- OFCI- Pad Mounted Transformers (XFM-TX) Shipping/ ROJ | 06-Mar-2025 | 15-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Pad Mounted Transformers | OFCI | #900208 | M20 | CHI-11-03-XFM-03 | MATCHING | Admin/C03- OFCI- Pad Mounted Transformers (XFM-TX) Delivered | 15-Mar-2025 | 15-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Main LV Switch Board | OFCI | #900208 | M29 | CHI-11-03-MSB-01 | MATCHING | Admin/C03- OFCI- Receive Main LV Switch Board (MSB) (SOW Del Date- 3/8/2025) | 10-Mar-2025 | 10-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Main LV Switch Board | OFCI | #900208 | M15 | CHI-11-03-MSB-02 | MATCHING | Admin/C03- OFCI- Main LV Switch Board (MSB) Shipping/ ROJ | 10-Mar-2025 | 07-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 3 | Main LV Switch Board | OFCI | #900208 | M15 | CHI-11-03-MSB-03 | MATCHING | Admin/C03- OFCI- Main LV Switch Board (MSB) Delivered | 31-Mar-2025 | 31-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Busway / Busplugs | OFCI | #900208 | M27 | CHI-11-04-BUS-01 | MATCHING | C04- OFCI- Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 5/1/25) | 16-Apr-2025 | 16-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Busway / Busplugs | OFCI | #900208 | M11 | CHI-11-04-BUS-02 | MATCHING | C04- OFCI- Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ | 16-Apr-2025 | 16-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Busway / Busplugs | OFCI | #900208 | M45 | CHI-11-04-BUS-03 | MATCHING | C04- OFCI- Busway / Busplugs (BSW) (Starline Holding) Delivered | 16-Apr-2025 | 16-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | LV Switchgear | OFCI | #900208 | M46 | CHI-11-04-LVS-01 | MATCHING | C04- OFCI- Receive LV Switchgear (Eaton) (SOW Del Date- 2/28/25) | 28-Mar-2025 | 28-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | LV Switchgear | OFCI | #900208 | M47 | CHI-11-04-LVS-02 | MATCHING | C04- OFCI- LV Switchgear (Eaton) Shipping/ROJ | 28-Mar-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | LV Switchgear | OFCI | #900208 | M48 | CHI-11-04-LVS-03 | MATCHING | C04- OFCI- LV Switchgear (Eaton) Delivered | 03-Apr-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Automatic Transfer Switches | OFCI | #900208 | M24 | CHI-11-04-ATS-01 | MATCHING | C04- OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 3/5/24) | 03-Feb-2025 | 03-Feb-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Automatic Transfer Switches | OFCI | #900208 | MH8 | CHI-11-04-ATS-02 | MATCHING | C04- OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ | 15-Apr-2025 | 19-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Automatic Transfer Switches | OFCI | #900208 | MH8 | CHI-11-04-ATS-03 | MATCHING | C04- OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered | 19-Apr-2025 | 19-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Elec Performance Monitoring System | OFCI | #900208 | MH28 | CHI-11-04-EPMS-01 | MATCHING | C04- OFCI- Receive Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) (SOW Del Date- 6/30/24) | 20-Sep-2024 | 20-Sep-2024
Procurement MSFT OFCI ROJ Dates | COLO 4 | Power Distribution Units | OFCI | #900208 | M38 | CHI-11-04-PDU-01 | MATCHING | C04- OFCI- Reveive Power Distribution Units (PDU) (ABB) (SOW Del Date- 3/15/25) | 27-Jan-2025 | 27-Jan-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Power Distribution Units | OFCI | #900208 | M21 | CHI-11-04-PDU-02 | MATCHING | C04- OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ | 02-May-2025 | 02-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Power Distribution Units | OFCI | #900208 | M21 | CHI-11-04-PDU-03 | MATCHING | C04- OFCI- Power Distribution Units (PDU) (ABB) Delivered | 02-May-2025 | 02-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Air Handling Units | OFCI | #900208 | M22 | CHI-11-04-AHU-01 | MATCHING | C04- OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/9/24) | 30-Sep-2024 | 30-Sep-2024
Procurement MSFT OFCI ROJ Dates | COLO 4 | Air Handling Units | OFCI | #900208 | MH6 | CHI-11-04-AHU-02 | MATCHING | C04- OFCI- Air Handling Units (AHU) (Stulz) Shipping/ ROJ | 09-Apr-2025 | 15-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Air Handling Units | OFCI | #900208 | MH6 | CHI-11-04-AHU-03 | MATCHING | C04- OFCI- Air Handling Units (AHU) (Stulz) Delivered | 15-Apr-2025 | 15-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Packaged Diesel Generator Set | OFCI | #900208 | M32 | CHI-11-04-GEN-01 | MATCHING | C04- OFCI- Receive Packaged Diesel Generator Set (GEN) (CAT Holt) (SOW Del Date- 6/4/24) | 17-Oct-2024 | 17-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 4 | Packaged Diesel Generator Set | OFCI | #900208 | M19 | CHI-11-04-GEN-02 | MATCHING | C04- OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ | 11-Apr-2025 | 15-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Packaged Diesel Generator Set | OFCI | #900208 | M19 | CHI-11-04-GEN-03 | MATCHING | C04- OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Delivered | 15-Apr-2025 | 15-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Medium Voltage Switchgear | OFCI | #900208 | M31 | CHI-11-04-MVS-01 | MATCHING | C04- OFCI- Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 8/30/24) | 23-Oct-2024 | 23-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 4 | Medium Voltage Switchgear | OFCI | #900208 | M17 | CHI-11-04-MVS-02 | MATCHING | C04- OFCI- Medium Voltage Switchgear (JDC Power Sys) Shipping/ROJ | 11-Apr-2025 | 30-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Medium Voltage Switchgear | OFCI | #900208 | M17 | CHI-11-04-MVS-03 | MATCHING | C04- OFCI- Medium Voltage Switchgear (JDC Power Sys) Delivered | 30-Apr-2025 | 30-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | UPS System W / Battery | OFCI | #900208 | M36 | CHI-11-04-UPS-01 | MATCHING | C04- OFCI- Received SUB Warehouse 11/23/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 11/11/23) | 02-Sep-2024 | 02-Sep-2024
Procurement MSFT OFCI ROJ Dates | COLO 4 | UPS System W / Battery | OFCI | #900208 | M39 | CHI-11-04-UPS-02 | MATCHING | C04- OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ | 16-Apr-2025 | 19-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | UPS System W / Battery | OFCI | #900208 | M39 | CHI-11-04-UPS-03 | MATCHING | C04- OFCI- Static UPS System W/Batt (UPS) (Eaton) Delivered | 19-Apr-2025 | 19-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Building Automation System | OFCI | #900208 | M26 | CHI-11-04-BAS-01 | MATCHING | C04- OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 3/15/25) | 15-Mar-2025 | 15-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Building Automation System | OFCI | #900208 | M10 | CHI-11-04-BAS-02 | MATCHING | C04- OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ | 04-Apr-2025 | 10-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Building Automation System | OFCI | #900208 | M10 | CHI-11-04-BAS-03 | MATCHING | C04- OFCI- Building Automation System (BAS) (Automated Logic Corp) Delivered | 10-Apr-2025 | 10-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Auto Transfer Control Panel | OFCI | #900208 | M23 | CHI-11-04-TCP-01 | MATCHING | C04- OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date-3/30/2025) | 03-Apr-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Auto Transfer Control Panel | OFCI | #900208 | MH7 | CHI-11-04-TCP-02 | MATCHING | C04- OFCI- Auto Transfer Control Panel (TCP) Shipping/ROJ | 18-Apr-2025 | 18-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Auto Transfer Control Panel | OFCI | #900208 | MH7 | CHI-11-04-TCP-03 | MATCHING | C04- OFCI- Auto Transfer Control Panel (TCP) Delivered | 18-Apr-2025 | 18-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Auxillary Power Distribution | OFCI | #900208 | MH30 | CHI-11-04-ADP-01 | MATCHING | C04- OFCI- Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) | 28-Feb-2025 | 28-Feb-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Auxillary Power Distribution | OFCI | #900208 | MH16 | CHI-11-04-ADP-02 | MATCHING | C04- OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ | 11-Apr-2025 | 15-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Auxillary Power Distribution | OFCI | #900208 | MH16 | CHI-11-04-ADP-03 | MATCHING | C04- OFCI- Mech Power Distribution Panels (ADP) Delivered | 15-Apr-2025 | 15-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Utility Pad Mount Switchgear | OFCI | #900208 | MH35 | CHI-11-04-UPM-01 | MATCHING | C04- OFCI- Receive Utility Pad Mount Switchgear (UPM) (Del Date 8/30/2024) | 23-Oct-2024 | 23-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 4 | Utility Pad Mount Switchgear | OFCI | #900208 | MH41 | CHI-11-04-UPM-02 | MATCHING | C04- OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ | 28-Apr-2025 | 01-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Utility Pad Mount Switchgear | OFCI | #900208 | MH41 | CHI-11-04-UPM-03 | MATCHING | C04- OFCI- Utility Pad Mount Switchgear (UPM) Delivered | 01-May-2025 | 01-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Pad Mounted Transformers | OFCI | #900208 | MH37 | CHI-11-04-XFM-01 | MATCHING | C04- OFCI- Reveive Pad Mounted Transformers (XMF) (Del Date 8/30/2024) | 23-Oct-2024 | 23-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 4 | Pad Mounted Transformers | OFCI | #900208 | MH20 | CHI-11-04-XFM-02 | MATCHING | C04- OFCI- Pad Mounted Transformers (XMF) Shipping/ROJ | 11-Apr-2025 | 15-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Pad Mounted Transformers | OFCI | #900208 | MH20 | CHI-11-04-XFM-03 | MATCHING | C04- OFCI- Pad Mounted Transformers (XMF) Delivered | 15-Apr-2025 | 15-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Main LV Switch Board | OFCI | #900208 | MH29 | CHI-11-04-MSB-01 | MATCHING | C04- OFCI- Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) | 28-Feb-2025 | 28-Feb-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Main LV Switch Board | OFCI | #900208 | MH15 | CHI-11-04-MSB-02 | MATCHING | C04- OFCI- Main LV Switch Board (MSB) Shipping/ROJ | 03-Apr-2025 | 10-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 4 | Main LV Switch Board | OFCI | #900208 | MH15 | CHI-11-04-MSB-03 | MATCHING | C04- OFCI- Main LV Switch Board (MSB) Delivered | 10-Apr-2025 | 10-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Busway / Busplugs | OFCI | #900208 | MH27 | CHI-11-05-BUS-01 | MATCHING | C05- OFCI- Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 5/8/25) | 02-May-2025 | 02-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Busway / Busplugs | OFCI | #900208 | MH11 | CHI-11-05-BUS-02 | MATCHING | C05- OFCI- Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ | 02-May-2025 | 02-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Busway / Busplugs | OFCI | #900208 | MH11 | CHI-11-05-BUS-03 | MATCHING | C05- OFCI- Busway / Busplugs (BSW) (Starline Holding) Delivered | 02-May-2025 | 02-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | LV Switchgear | OFCI | #900208 | MH46 | CHI-11-05-LVS-01 | MATCHING | C05- OFCI- Receive LV Switchgear (Eaton) (SOW Del Date- 3/30/25) | 30-Mar-2025 | 30-Mar-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | LV Switchgear | OFCI | #900208 | MH47 | CHI-11-05-LVS-02 | MATCHING | C05- OFCI- LV Switchgear (Eaton) Shipping/ROJ | 30-Mar-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | LV Switchgear | OFCI | #900208 | MH48 | CHI-11-05-LVS-03 | MATCHING | C05- OFCI- LV Switchgear (Eaton) Delivered | 03-Apr-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Automatic Transfer Switches | OFCI | #900208 | MH23 | CHI-11-05-ATS-01 | MATCHING | C05- OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 4/1/25) | 01-Apr-2025 | 01-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Automatic Transfer Switches | OFCI | #900208 | MH8 | CHI-11-05-ATS-02 | MATCHING | C05- OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ | 23-May-2025 | 23-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Automatic Transfer Switches | OFCI | #900208 | MH8 | CHI-11-05-ATS-03 | MATCHING | C05- OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered | 23-May-2025 | 23-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Elec Performance Monitoring System | OFCI | #900208 | M28 | CHI-11-05-EPMS-01 | MATCHING | C05- OFCI- Receive Elec. Performance Monitoring Syst. (EPMS) (Schneider) (SOW Del Date- 8/31/24) | 20-Sep-2024 | 20-Sep-2024
Procurement MSFT OFCI ROJ Dates | COLO 5 | Power Distribution Units | OFCI | #900208 | MH34 | CHI-11-05-PDU-01 | MATCHING | C05- OFCI- Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 5/8/25) | 31-Jan-2025 | 31-Jan-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Air Handling Units | OFCI | #900208 | M22 | CHI-11-05-AHU-01 | MATCHING | C05- OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/16/24) | 12-Sep-2024 | 12-Sep-2024
Procurement MSFT OFCI ROJ Dates | COLO 5 | Air Handling Units | OFCI | #900208 | MH6 | CHI-11-05-AHU-02 | MATCHING | C05- OFCI- Air Handling Units (AHU) (Stulz) Shipping/ROJ | 12-May-2025 | 15-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Air Handling Units | OFCI | #900208 | MH6 | CHI-11-05-AHU-03 | MATCHING | C05- OFCI- Air Handling Units (AHU) (Stulz) Delivered | 15-May-2025 | 15-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Packaged Diesel Generator Set | OFCI | #900208 | M32 | CHI-11-05-GEN-01 | MATCHING | C05- OFCI- Receive Packaged Diesel Generator Set (GPC) (CAT Holt) (SOW Del Date- 6/26/24) | 17-Oct-2024 | 17-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 5 | Packaged Diesel Generator Set | OFCI | #900208 | M19 | CHI-11-05-GEN-02 | MATCHING | C05- OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ | 24-Apr-2025 | 22-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Packaged Diesel Generator Set | OFCI | #900208 | MH19 | CHI-11-05-GEN-03 | MATCHING | C05- OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Delivered | 22-May-2025 | 22-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Medium Voltage Switchgear | OFCI | #900208 | MH31 | CHI-11-05-MVS-01 | MATCHING | C05- OFCI- Receive Medium Voltage Switchgear (MVS) (JDC Power Sys) (SOW Del Date- 10/30/24) | 30-Oct-2024 | 30-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 5 | Medium Voltage Switchgear | OFCI | #900208 | MH17 | CHI-11-05-MVS-02 | MATCHING | C05- OFCI- Medium Voltage Switchgear (MVS) (JDC Power Sys) Shipping/ROJ | 29-Apr-2025 | 28-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Medium Voltage Switchgear | OFCI | #900208 | MH17 | CHI-11-05-MVS-03 | MATCHING | C05- OFCI- Medium Voltage Switchgear (MVS) (JDC Power Sys) Delivered | 28-May-2025 | 28-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | UPS System W / Battery | OFCI | #900208 | M36 | CHI-11-05-UPS-01 | MATCHING | C05- OFCI- Received SUB Warehouse 12/28/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 12/11/23) | 02-Sep-2024 | 02-Sep-2024
Procurement MSFT OFCI ROJ Dates | COLO 5 | Auto Transfer Control Panel | OFCI | #900208 | MH23 | CHI-11-05-TCP-01 | MATCHING | C05- OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date 3/30/2025) | 03-Apr-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Building Automation System | OFCI | #900208 | MH26 | CHI-11-05-BAS-01 | MATCHING | C05- OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 4/22/25) | 03-Apr-2025 | 03-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Building Automation System | OFCI | #900208 | MH10 | CHI-11-05-BAS-02 | MATCHING | C05- OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ | 04-Apr-2025 | 08-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Building Automation System | OFCI | #900208 | MH10 | CHI-11-05-BAS-03 | MATCHING | C05- OFCI- Building Automation System (BAS) (Automated Logic Corp) Delivered | 08-Apr-2025 | 08-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Auxillary Power Distribution | OFCI | #900208 | M30 | CHI-11-05-ADP-01 | MATCHING | C05- OFCI- Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) | 01-Apr-2025 | 01-Apr-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Utility Pad Mount Switchgear | OFCI | #900208 | MH35 | CHI-11-05-UPM-01 | MATCHING | C05- OFCI- Receive Utility Pad Mount Switchgear (UPM) (Del Date 10/30/2024) | 23-Oct-2024 | 23-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 5 | Utility Pad Mount Switchgear | OFCI | #900208 | MH41 | CHI-11-05-UPM-02 | MATCHING | C05- OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ | 29-Apr-2025 | 29-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Utility Pad Mount Switchgear | OFCI | #900208 | MH41 | CHI-11-05-UPM-03 | MATCHING | C05- OFCI- Utility Pad Mount Switchgear (UPM) Delivered | 29-May-2025 | 29-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Pad Mounted Transformers | OFCI | #900208 | MH20 | CHI-11-05-XFM-01 | MATCHING | C05- OFCI- Receive Pad Mounted Transformers (XMF) (Del Date 10/30/2024) | 30-Oct-2024 | 30-Oct-2024
Procurement MSFT OFCI ROJ Dates | COLO 5 | Pad Mounted Transformers | OFCI | #900208 | MH20 | CHI-11-05-XFM-02 | MATCHING | C05- OFCI- Pad Mounted Transformers (XMF) Shipping/ROJ | 03-May-2025 | 22-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Pad Mounted Transformers | OFCI | #900208 | MH29 | CHI-11-05-XFM-03 | MATCHING | C05- OFCI- Pad Mounted Transformers (XMF) Delivered | 22-May-2025 | 22-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Main LV Switch Board | OFCI | #900208 | MH29 | CHI-11-05-MSB-01 | MATCHING | C05- OFCI- Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) | 30-Mar-2025 | 30-Mar-2025
Procurement CFCI (Critical Only) | N/A | N/A | CFCI | #5FFFFF | CFCI1 | CHI-11-CFCI-20 | MATCHING | CFCI- MV Cables Fabrication/ Lead Time | 17-Aug-2024 | 21-Apr-2025
Procurement CFCI (Critical Only) | N/A | N/A | CFCI | #5FFFFF | CFCI2 | CHI-11-CFCI-25 | MATCHING | CFCI- Cable Bus Fabrication/ Lead Time | 18-Nov-2024 | 11-Apr-2025
Procurement CFCI (Critical Only) | N/A | N/A | CFCI | #5FFFFF | CFCI3 | CHI-11-CFCI-30 | MATCHING | CFCI- HACs Fabrication/ Lead Time | 06-Dec-2024 | 13-Mar-2025
PROCUREMENT | BOM OFCI | COLO 3 | CLAYCO | #EE5A1C | M-C | CHI-11-BOM-OFCI-10-TEL | MATCHING | Maxcell Delivery | 10-Mar-2025 | 13-Mar-2025
Procurement | BOM OFCI | COLO 3 | CLAYCO | #EE5A1C | M-C | CHI-11-BOM-OFCI-50-TEL | MATCHING | 288's Production Cable COLO3 | 18-Apr-2025 | 22-Apr-2025
PROCUREMENT | BOM OFCI | COLO 3 | CLAYCO | #EE5A1C | M-C | CHI-11-BOM-OFCI-20-TEL | MATCHING | 2880's Production Cable COLO3 (3/17/2025) | 29-Apr-2025 | 11-May-2025
Procurement | BOM OFCI | COLO 3 | CLAYCO | #EE5A1C | M-C | CHI-11-CORNING-DELAY-1-TEL | MATCHING | 2880's Production Cable COLO3 (Late Delivery) ROJ+ 49 days | 11-May-2025 | 11-May-2025
Procurement | BOM OFCI | COLO 4 | CLAYCO | #EE5A1C | M-C | CHI-11-BOM-OFCI-60-TEL | MATCHING | 288's Production Cable COLO4 | 16-May-2025 | 21-May-2025
Procurement | BOM OFCI | COLO 4 | CLAYCO | #EE5A1C | M-C | CHI-11-CORNING-DELAY-2-TEL | MATCHING | 2880's Production Cable COLO4 (Late Delivery ROJ + 45 days | 29-May-2025 | 29-May-2025
PROCUREMENT | BOM OFCI | COLO 5 | CLAYCO | #EE5A1C | M-C | CHI-11-BOM-OFCI-40-TEL | MATCHING | 2880's Production Cable COLO5 (4/28/2025) | 05-Jun-2025 | 10-Jun-2025
Procurement | BOM OFCI | COLO 5 | CLAYCO | #EE5A1C | M-C | CHI-11-CORNING-DELAY-3-TEL | MATCHING | 2880's Production Cable COLO5 (Late Delivery ROJ + 38 days) | 05-Jun-2025 | 05-Jun-2025
Procurement | BOM OFCI | COLO5 | CLAYCO | #EE5A1C | M-C | CHI-11-BOM-OFCI-70-TEL | MATCHING | 288's Production Cable COLO5 | 09-Jun-2025 | 17-Jun-2025
Procurement | Non Potable Water Booster Pump | Pump Station | CLAYCO | #EE5A1C | M-C | CHI-11-CFCI-70 | MATCHING | NPW Booster Pump - Receive/Review/Approve Submital | 25-Mar-2025 | 29-Mar-2025
Procurement | Non Potable Water Booster Pump | Pump Station | CLAYCO | #EE5A1C | M-C | CHI-11-CFCI-80 | MATCHING | NPW Booster Pump - Fabrication Lead Time | 09-Jul-2025 | 09-Jul-2025
Procurement | Non Potable Water Booster Pump | Pump Station | CLAYCO | #EE5A1C | M-C | CHI-11-CFCI-90 | MATCHING | NPW Booster Pump - Delivery to Site | 09-Jul-2025 | 09-Jul-2025
Construction | Site Prep/ Mobilization | N/A | Site Utilities | #D0D0D0 | ST1 | CHI11-MOB-10 | MATCHING | Site Mobilization | 24-Jul-2024 | 24-Jul-2024
Construction | Site Prep/ Mobilization | N/A | Site Utilities | #D0D0D0 | ST2 | CHI11-MOB-15 | MATCHING | Set-Up Trailers & Install Temp Utilities | 25-Jul-2024 | 16-Sep-2024
Construction | Site Prep/ Mobilization | N/A | CLAYCO | #EE5A1C | MC | CHI11-MOB-20 | MATCHING | Fine Grading Building Pad | 19-Aug-2024 | 04-Sep-2024
Construction | Site Utilities | Overall | Plumbing | #1F595B | P4 | CHI11-SU-10 | MATCHING | Install Deep Telecom | 08-Oct-2024 | 14-Nov-2024
Construction | Site Utilities | Overall | Plumbing | #1F595B | P5 | CHI11-SU-30 | MATCHING | Install Storm Lines | 09-Oct-2024 | 26-Dec-2024
Construction | Site Utilities | Overall | Plumbing | #1F595B | P6 | CHI11-SU-15 | MATCHING | Install MV Ductbanks | 25-Oct-2024 | 20-Mar-2025
Construction | Site Utilities | Overall | Plumbing | #1F595B | P7 | CHI11-SU-35 | MATCHING | Install Sanitary Lines | 04-Nov-2024 | 27-Mar-2025
Construction | Site Utilities | Overall | Plumbing | #1F595B | P8 | CHI11-SU-40 | MATCHING | Install Water Line | 04-Nov-2024 | 27-Mar-2025
Construction | Site Utilities | Overall | GIBSON | #FFF9B1 | EE29 | CHI11-SU-50 | MATCHING | Permanent Power (Need by Date) | 15-May-2025 | 15-May-2025
Construction | Site Utilities | Under Building Pad | CLAYCO | #EE5A1C | M-C | CHI11-SU-20 | MATCHING | Install UG Telecom (under Building Pad) | 08-Oct-2024 | 10-Oct-2024
Construction | Site Utilities | Under Building Pad | CLAYCO | #EE5A1C | M-C | CHI11-SU-25 | MATCHING | Install UG Electrical / UPM Crossing (under Building Pad) | 25-Oct-2024 | 13-Nov-2024
Construction | Site Utilities | Under Building Pad | CLAYCO | #EE5A1C | M-C | CHI11-SU-45 | MATCHING | Backfill after UG work (MV / Telecom) | 05-Nov-2024 | 15-Nov-2024
Construction | Foundations | N/A | CLAYCO | #EE5A1C | M-C | CHI11-FDN-10 | MATCHING | Foundations / Stem Walls (50% Complete) | 19-Sep-2024 | 09-Oct-2024
Construction | Foundations | N/A | CLAYCO | #EE5A1C | M-C | CHI11-FDN-15 | MATCHING | Foundations / Stem Walls (100% Complete) | 10-Oct-2024 | 12-Nov-2024
Construction | Core & Shell | Admin/ COLO 3 | Imperial/Span | #E0D0D0 | X4 | CHI11-03-C&S-10 | MATCHING | Admin/C03- Install Primary Steel | 14-Oct-2024 | 07-Nov-2024
Construction | Core & Shell | Admin/ COLO 3 | MEP | #FF7BFF | MEP5 | CHI11-03-C&S-20 | MATCHING | Admin/C03- UG MEP Work AMS/Gibson | 13-Nov-2024 | 14-Dec-2024
Construction | Core & Shell | Admin/ COLO 3 | Imperial/Span | #E0D0D0 | X1 | CHI11-03-C&S-25 | MATCHING | Admin/C03- Install Exterior Wall Panels | 18-Nov-2024 | 14-Dec-2024
Construction | Core & Shell | Admin/ COLO 3 | Imperial/Span | #E0D0D0 | X5 | CHI11-03-C&S-15 | MATCHING | Admin/C03- Install Roof Panels | 26-Nov-2024 | 14-Dec-2024
Construction | Core & Shell | Admin/ COLO 3 | CLAYCO | #EE5A1C | M-C | CHI11-03-C&S-39 | MATCHING | Admin/C03- Weather Days 6/15 | 16-Dec-2024 | 21-Dec-2024
Construction | Core & Shell | Admin/ COLO 3 | Scurto | #83CCEB | S1 | CHI11-03-C&S-35 | MATCHING | Admin/C03- Prep / Place SOG | 23-Dec-2024 | 06-Jan-2025
Construction | Core & Shell | Admin/ COLO 3 | Imperial/Span | #E0D0D1 | X3 | CHI11-03-C&S-40 | MATCHING | Admin/C03- Install Misc. Metals (Trims, Gutters) | 06-Jan-2025 | 01-Feb-2025
Construction | Core & Shell | Admin/ COLO 3 | Imperial/Span | #E0D0D0 | X2 | CHI11-03-C&S-30 | MATCHING | Admin/C03- Install Louvers & Dampers | 08-Jan-2025 | 01-Feb-2025
Construction | Core & Shell | COLO 4 | Imperial/Span | #E0D0D0 | X4 | CHI11-04-C&S-10 | MATCHING | C04- Install Primary Steel | 01-Nov-2024 | 20-Nov-2024
Construction | Core & Shell | COLO 4 | Imperial/Span | #E0D0D0 | X1 | CHI11-04-C&S-25 | MATCHING | C04- Install Exterior Wall Panels | 09-Dec-2024 | 20-Dec-2024
Construction | Core & Shell | COLO 4 | Imperial/Span | #E0D0D1 | X3 | CHI11-04-C&S-40 | MATCHING | C04- Install Misc. Metals (Trims, Gutters) | 12-Dec-2024 | 03-Feb-2025
Construction | Core & Shell | COLO 4 | MEP | #FF7BFF | MEP5 | CHI11-04-C&S-20 | MATCHING | C04- UG MEP Work AMS/Gibson | 12-Dec-2024 | 06-Jan-2025
Construction | Core & Shell | COLO 4 | Imperial/Span | #E0D0D0 | X2 | CHI11-04-C&S-35 | MATCHING | C04- Install Louvers & Dampers | 16-Dec-2024 | 10-Feb-2025
Construction | Core & Shell | COLO 4 | Imperial/Span | #E0D0D0 | X5 | CHI11-04-C&S-15 | MATCHING | C04- Install Roof Panels | 21-Dec-2024 | 11-Jan-2025
Construction | Core & Shell | COLO 4 | Scurto | #83CCEB | S1 | CHI11-04-C&S-30 | MATCHING | C04- Prep / Place SOG | 07-Jan-2025 | 17-Jan-2025
Construction | Core & Shell | COLO 5 | Imperial/Span | #E0D0D0 | X4 | CHI11-05-C&S-10 | MATCHING | C05- Install Primary Steel | 12-Nov-2024 | 21-Nov-2024
Construction | Core & Shell | COLO 5 | MEP | #FF7BFF | MEP5 | CHI11-05-C&S-20 | MATCHING | C05- UG MEP Work AMS/Gibson | 04-Dec-2024 | 22-Jan-2025
Construction | Core & Shell | COLO 5 | Imperial/Span | #E0D0D0 | X1 | CHI11-05-C&S-25 | MATCHING | C05- Install Exterior Wall Panels | 20-Dec-2024 | 17-Jan-2025
Construction | Core & Shell | COLO 5 | Imperial/Span | #E0D0D0 | X5 | CHI11-05-C&S-15 | MATCHING | C05- Install Roof Panels | 08-Jan-2025 | 17-Jan-2025
Construction | Core & Shell | COLO 5 | Scurto | #83CCEB | S1 | CHI11-05-C&S-30 | MATCHING | C05- Prep / Place SOG | 23-Jan-2025 | 07-Feb-2025
Construction | Core & Shell | COLO 5 | Imperial/Span | #E0D0D1 | X3 | CHI11-05-C&S-40 | MATCHING | C05- Install Misc. Metals (Trims, Gutters) | 30-Jan-2025 | 14-Feb-2025
Construction | Core & Shell | COLO 5 | Imperial/Span | #E0D0D0 | X2 | CHI11-05-C&S-35 | MATCHING | C05- Install Louvers & Dampers | 11-Feb-2025 | 06-Mar-2025
Construction | CSA Exterior Work | Site | LIMA | #FFD407 | L1 | CHI11-CSA-270 | MATCHING | LIMA - Backfill & grading | 19-Jun-2025 | 02-Jul-2025
Construction | CSA Exterior Work | Site | TBV | #B5E6A2 | W1 | CHI11-CSA-30 | MATCHING | Install Screenwall Structure | 16-Jul-2025 | 28-Jul-2025
Construction | CSA Exterior Work | Site | TBV | #B5E6A2 | W2 | CHI11-CSA-70 | MATCHING | Install Screenwall | 29-Jul-2025 | 21-Aug-2025
Construction | CSA Exterior Work | Site | TBV | #5D1B0C | V3 | CHI11-CSA-290 | MATCHING | Install Asphalt Surface Course | 22-Aug-2025 | 27-Aug-2025
Construction | CSA Exterior Work | COLO 3 | GIBSON | #FFF9B1 | EE52 | CHI11-CSA-40 | MATCHING | Install Catwalk/ Cable Bus Tray North COLO3 | 25-Mar-2025 | 09-Apr-2025
Construction | CSA Exterior Work | COLO 3 | GIBSON | #FFF9B1 | EE52 | CHI11-CSA-160 | MATCHING | Install Catwalk/ Cable Bus Tray South COLO3 | 25-Mar-2025 | 09-Apr-2025
Construction | CSA Exterior Work | COLO 3 | Scurto | #83CCEB | S3 | CHI11-CSA-10 | MATCHING | Concrete Paving Around Generator North COLO3 GEN to Screenwall | 03-Jul-2025 | 10-Jul-2025
Construction | CSA Exterior Work | COLO 3 | Scurto | #83CCEB | S3 | CHI11-CSA-90 | MATCHING | Concrete Paving Around Generator South COLO3 GEN to Screenwall | 11-Jul-2025 | 15-Jul-2025
Construction | CSA Exterior Work | COLO 4 | GIBSON | #FFF9B1 | EE52 | CHI11-CSA-140 | MATCHING | Install Catwalk/ Cable Bus Support COLO4 South | 07-Apr-2025 | 02-May-2025
Construction | CSA Exterior Work | COLO 4 | GIBSON | #FFF9B1 | EE52 | CHI11-CSA-150 | MATCHING | Install Catwalk/ Cable Bus Support COLO4 North | 09-Apr-2025 | 02-May-2025
Construction | CSA Exterior Work | COLO 4 | Scurto | #83CCEB | S3 | CHI11-CSA-210 | MATCHING | Concrete Paving Around Generator North COLO4 GEN to Screenwall | 11-Jul-2025 | 16-Jul-2025
Construction | CSA Exterior Work | COLO 4 | Scurto | #83CCEB | S3 | CHI11-CSA-220 | MATCHING | Concrete Paving Around Generator South COLO4 GEN to Screenwall | 17-Jul-2025 | 22-Jul-2025
Construction | CSA Exterior Work | COLO 5 | GIBSON | #FFF9B1 | EE52 | CHI11-CSA-130 | MATCHING | Install Catwalk/ Cable Bus Tray North COLO5 | 05-May-2025 | 15-May-2025
Construction | CSA Exterior Work | COLO 5 | GIBSON | #FFF9B1 | EE52 | CHI11-CSA-120 | MATCHING | Install Catwalk/ Cable Bus Tray South COLO5 | 05-May-2025 | 15-May-2025
Electrical Yard | Fiber | COLO 3 Cell 1 | GIBSON | #FFF9B1 | EE53 | CHI11-TELECOM-21 | MATCHING | C03/01 Pull GPC+UPM Fiber | 02-May-2025 | 02-May-2025
Electrical Yard | Fiber | COLO 3 Cell 1 | GIBSON | #FFF9B1 | EE54 | CHI11-TELECOM-22 | MATCHING | C03/01 Term GPC+UPM Fiber | 05-May-2025 | 05-May-2025
Electrical Yard | Fiber | COLO 3 Cell 1 | GIBSON | #FFF9B1 | EE55 | CHI11-TELECOM-23 | MATCHING | C03/01 Test GPC+UPM Fiber | 06-May-2025 | 06-May-2025
Electrical Yard | Fiber | COLO 3 Cell 2 | GIBSON | #FFF9B1 | EE53 | CHI11-TELECOM-24 | MATCHING | C03/02 Pull GPC+UPM Fiber | 05-May-2025 | 05-May-2025
Electrical Yard | Fiber | COLO 3 Cell 2 | GIBSON | #FFF9B1 | EE54 | CHI11-TELECOM-25 | MATCHING | C03/02 Term GPC+UPM Fiber | 06-May-2025 | 08-May-2025
Electrical Yard | Fiber | COLO 3 Cell 2 | GIBSON | #FFF9B1 | EE55 | CHI11-TELECOM-26 | MATCHING | C03/02 Test GPC+UPM Fiber | 09-May-2025 | 09-May-2025
Electrical Yard | Fiber | COLO 3 Cell 3 | GIBSON | #FFF9B1 | EE53 | CHI11-TELECOM-27 | MATCHING | C03/03 Pull GPC+UPM Fiber | 06-May-2025 | 07-May-2025
Electrical Yard | Fiber | COLO 3 Cell 3 | GIBSON | #FFF9B1 | EE54 | CHI11-TELECOM-28 | MATCHING | C03/03 Term GPC+UPM Fiber | 08-May-2025 | 12-May-2025
Electrical Yard | Fiber | COLO 3 Cell 3 | GIBSON | #FFF9B1 | EE55 | CHI11-TELECOM-29 | MATCHING | C03/03 Test GPC+UPM Fiber | 12-May-2025 | 12-May-2025
Electrical Yard | Fiber | COLO 3 Cell 4 | GIBSON | #FFF9B1 | EE53 | CHI11-TELECOM-31 | MATCHING | C03/04 Pull GPC+UPM Fiber | 08-May-2025 | 09-May-2025
Electrical Yard | Fiber | COLO 3 Cell 4 | GIBSON | #FFF9B1 | EE54 | CHI11-TELECOM-32 | MATCHING | C03/04 Term GPC+UPM Fiber | 10-May-2025 | 12-May-2025
Electrical Yard | Fiber | COLO 3 Cell 4 | GIBSON | #FFF9B1 | EE55 | CHI11-TELECOM-33 | MATCHING | C03/04 Test GPC+UPM Fiber | 13-May-2025 | 13-May-2025
Electrical Yard | Fiber | COLO 4 Cell 1 | GIBSON | #FFF9B1 | EE53 | CHI11-TELECOM-34 | MATCHING | C04/01 Pull GPC+UPM Fiber | 31-May-2025 | 04-Jun-2025
Electrical Yard | Fiber | COLO 4 Cell 2 | GIBSON | #FFF9B1 | EE53 | CHI11-TELECOM-37 | MATCHING | C04/02 Pull GPC+UPM Fiber | 02-Jun-2025 | 03-Jun-2025
Electrical Yard | Fiber | COLO 4 Cell 2 | GIBSON | #FFF9B1 | EE54 | CHI11-TELECOM-38 | MATCHING | C04/02 Term GPC+UPM Fiber | 04-Jun-2025 | 06-Jun-2025
Electrical Yard | Fiber | COLO 4 Cell 3 | GIBSON | #FFF9B1 | EE53 | CHI11-TELECOM-41 | MATCHING | C04/03 Pull GPC+UPM Fiber | 04-Jun-2025 | 05-Jun-2025
Electrical Yard | Fiber | COLO 4 Cell 3 | GIBSON | #FFF9B1 | EE54 | CHI11-TELECOM-42 | MATCHING | C04/03 Term GPC+UPM Fiber | 06-Jun-2025 | 09-Jun-2025
Electrical Yard | Fiber | COLO 4 Cell 3 | GIBSON | #FFF9B1 | EE55 | CHI11-TELECOM-43 | MATCHING | C04/03 Test GPC+UPM Fiber | 10-Jun-2025 | 10-Jun-2025
Electrical Yard | Fiber | COLO 4 Cell 4 | GIBSON | #FFF9B1 | EE53 | CHI11-TELECOM-44 | MATCHING | C04/04 Pull GPC+UPM Fiber | 11-Jun-2025 | 12-Jun-2025
Electrical Yard | Fiber | COLO 4 Cell 4 | GIBSON | #FFF9B1 | EE54 | CHI11-TELECOM-45 | MATCHING | C04/04 Term GPC+UPM Fiber | 13-Jun-2025 | 17-Jun-2025
Electrical Yard | Fiber | COLO 4 Cell 4 | GIBSON | #FFF9B1 | EE55 | CHI11-TELECOM-46 | MATCHING | C04/04 Test GPC+UPM Fiber | 18-Jun-2025 | 18-Jun-2025
Construction | Electrical Yard | Admin/ COLO 3 | GIBSON | #FFF9B1 | EE6 | CHI11-03-YARD-10 | MATCHING | C03/Yard- Build Equipment Pads for XFMs | 03-Feb-2025 | 28-Feb-2025
Construction | Electrical Yard | Admin/ COLO 3 | GIBSON | #FFF9B1 | EE5 | CHI11-03-YARD-15 | MATCHING | C03/Yard- Build Equipment Pads for UPMs | 03-Feb-2025 | 03-Apr-2025
Construction | Electrical Yard | Admin/ COLO 3 | GIBSON | #FFF9B1 | EE4 | CHI11-03-YARD-20 | MATCHING | C03/Yard- Build Equipment Pads for UMSs | 03-Feb-2025 | 03-Apr-2025
Construction | Electrical Yard | Admin/ COLO 3 | GIBSON | #FFF9B1 | EE3 | CHI11-03-YARD-25 | MATCHING | C03/Yard- Build Equipment Pads for Generators | 03-Feb-2025 | 28-Feb-2025
Construction | Electrical Yard | Admin/ COLO 3 | GIBSON | #FFF9B1 | EE24 | CHI11-03-YARD-30 | MATCHING | C03/Yard- Install XFMs | 06-Mar-2025 | 15-Mar-2025
Construction | Electrical Yard | Admin/ COLO 3 | GIBSON | #FFF9B1 | EE19 | CHI11-03-YARD-45 | MATCHING | C03/Yard- Install Generators | 06-Mar-2025 | 14-Mar-2025
Construction | Electrical Yard | Admin/ COLO 3 | GIBSON | #FFF9B1 | EE22 | CHI11-03-YARD-40 | MATCHING | C03/Yard- Install UMSs | 07-Apr-2025 | 11-Apr-2025
Construction | Electrical Yard | Admin/ COLO 3 | GIBSON | #FFF9B1 | EE23 | CHI11-03-YARD-35 | MATCHING | C03/Yard- Install UPMs | 09-Apr-2025 | 15-Apr-2025
Construction | Electrical Yard | Admin/ COLO 3 | GIBSON | #FFF9B1 | EE26 | CHI11-03-YARD-50 | MATCHING | C03/Yard- MV Cable Pulling & Terminating | 18-Apr-2025 | 13-May-2025
Construction | Electrical Yard | Admin/ COLO 3 | GIBSON | #FFF9B1 | EE26 | CHI11-03-YARD-55 | MATCHING | C03/Yard- MV Cable Pulling & Terminating | 28-Apr-2025 | 13-May-2025
Construction | Electrical Yard | Admin/ COLO 3 | GIBSON | #FFF9B1 | EE26 | CHI11-03-YARD-60 | MATCHING | C03/Yard- MV Cable Pulling & Terminating | 06-May-2025 | 15-May-2025
Construction | Electrical Yard | Admin/ COLO 3 | GIBSON | #FFF9B1 | EE26 | CHI11-03-YARD-65 | MATCHING | C03/Yard- MV Cable Pulling & Terminating | 06-May-2025 | 15-May-2025
Construction | Electrical Yard | COLO 4 | GIBSON | #FFF9B1 | EE6 | CHI11-04-YARD-10 | MATCHING | C04/Yard- Build Equipment Pads for XFMs | 05-Mar-2025 | 10-Apr-2025
Construction | Electrical Yard | COLO 4 | GIBSON | #FFF9B1 | EE3 | CHI11-04-YARD-25 | MATCHING | C04/Yard- Build Equipment Pads for Generators | 05-Mar-2025 | 08-Apr-2025
Construction | Electrical Yard | COLO 4 | GIBSON | #FFF9B1 | EE5 | CHI11-04-YARD-15 | MATCHING | C04/Yard- Build Equipment Pads for UPMs | 28-Mar-2025 | 11-Apr-2025
Construction | Electrical Yard | COLO 4 | GIBSON | #FFF9B1 | EE24 | CHI11-04-YARD-30 | MATCHING | C04/Yard- Install XFMs | 16-Apr-2025 | 17-Apr-2025
Construction | Electrical Yard | COLO 4 | GIBSON | #FFF9B1 | EE19 | CHI11-04-YARD-45 | MATCHING | C04/Yard- Install Generators | 16-Apr-2025 | 17-Apr-2025
Construction | Electrical Yard | COLO 4 | GIBSON | #FFF9B1 | EE23 | CHI11-04-YARD-35 | MATCHING | C04/Yard- Install UPMs | 29-Apr-2025 | 07-May-2025
Construction | Electrical Yard | COLO 4 | GIBSON | #FFF9B1 | EE26 | CHI11-04-YARD-50 | MATCHING | C04/Yard- MV Cable Pulling & Terminating | 30-Apr-2025 | 20-Jun-2025
Construction | Electrical Yard | COLO 4 | GIBSON | #FFF9B1 | EE26 | CHI11-04-YARD-55 | MATCHING | C04/Yard- MV Cable Pulling & Terminating | 30-Apr-2025 | 20-Jun-2025
Construction | Electrical Yard | COLO 4 | GIBSON | #FFF9B1 | EE26 | CHI11-04-YARD-60 | MATCHING | C04/Yard- MV Cable Pulling & Terminating | 30-Apr-2025 | 27-Jun-2025
Construction | Electrical Yard | COLO 4 | GIBSON | #FFF9B1 | EE26 | CHI11-04-YARD-65 | MATCHING | C04/Yard- MV Cable Pulling & Terminating | 30-Apr-2025 | 27-Jun-2025
Construction | Electrical Yard | COLO 5 | GIBSON | #FFF9B1 | EE6 | CHI11-05-YARD-10 | MATCHING | C05/Yard- Build Equipment Pads for XFMs | 10-Apr-2025 | 08-May-2025
Construction | Electrical Yard | COLO 5 | GIBSON | #FFF9B1 | EE3 | CHI11-05-YARD-25 | MATCHING | C05/Yard- Build Equipment Pads for Generators | 10-Apr-2025 | 08-May-2025
Construction | Electrical Yard | COLO 5 | GIBSON | #FFF9B1 | EE5 | CHI11-05-YARD-15 | MATCHING | C05/Yard- Build Equipment Pads for UPMs | 18-Apr-2025 | 08-May-2025
Construction | Electrical Yard | COLO 5 | GIBSON | #FFF9B1 | EE19 | CHI11-05-YARD-55 | MATCHING | C05/Yard- Install Generators | 24-Apr-2025 | 22-May-2025
Construction | Electrical Yard | COLO 5 | GIBSON | #FFF9B1 | EE24 | CHI11-05-YARD-35 | MATCHING | C05/Yard- Install XFMs | 29-Apr-2025 | 22-May-2025
Construction | Electrical Yard | COLO 5 | GIBSON | #FFF9B1 | EE23 | CHI11-05-YARD-45 | MATCHING | C05/Yard- Install UPMs | 29-Apr-2025 | 29-May-2025
FITOUT | Admin Area | TELECOM | GIBSON | #FFF9B1 | EET2 | CHI11-TELECOM-10 | MATCHING | Pull Exterior MAXCELL | 17-Mar-2025 | 18-Apr-2025
FITOUT | Admin Area | TELECOM | CECCO | #EF9E5B | T9 | CHI11-TELECOM-30 | MATCHING | SET RACKS FCR Room | 19-Apr-2025 | 02-May-2025
FITOUT | Admin Area | TELECOM | GIBSON | #FFF9B1 | EET1 | CHI11-TELECOM-40 | MATCHING | Work Area Outlets | 30-Apr-2025 | 16-May-2025
FITOUT | Admin Area | TELECOM | CECCO | #EF9E5B | T10 | CHI11-TELECOM-20 | MATCHING | Pull Production Exterior Fiber (2880 COLO3) | 05-May-2025 | 10-Jun-2025
FITOUT | Admin Area | TELECOM | CECCO | #EF9E5B | T11 | CHI11-TELECOM-60 | MATCHING | Pull Production Exterior Fiber (2880 COLO4) | 11-Jun-2025 | 18-Jul-2025
FITOUT | Admin Area | TELECOM | CECCO | #EF9E5B | T12 | CHI11-TELECOM-70 | MATCHING | Pull Production Exterior Fiber (2880 COLO5) | 19-Jul-2025 | 25-Aug-2025
FITOUT | Admin Area | TELECOM | CECCO | #EF9E5B | T1 | CHI11-TELECOM-50 | MATCHING | Admin - Pull EPMS Copper | 21-Apr-2025 | 21-Apr-2025
Fitout | Admin Area | TELECOM | CECCO | #EF9E5B | T13 | CHI11-TELECOM-07 | MATCHING | Admin - Terminate EPMS Copper | 22-Apr-2025 | 27-Apr-2025
Fitout | Admin Area | TELECOM | CECCO | #EF9E5B | T14 | CHI11-TELECOM-08 | MATCHING | Admin - Test EPMS Copper | 28-Apr-2025 | 09-May-2025
Fitout | Admin Area | N/A | Anning Johnson | #2490FF | D1 | CHI11-ADMIN-99 | MATCHING | AJ Admin Area MOB & Layout Framing | 08-Jan-2025 | 13-Jan-2025
Fitout | Admin | Electrical Room | Shambaugh | #D76672 | R1 | CHI11-ADMIN-10 | MATCHING | Admin/Elec Rm- Fire Protection OH R/I | 15-Jan-2025 | 20-Jan-2025
Fitout | Admin | Electrical Room | Anning Johnson | #2490FF | D3 | CHI11-ADMIN-15 | MATCHING | Admin/ Elec Rm- Framing | 17-Jan-2025 | 13-Feb-2025
Fitout | Admin | Electrical Room | MEP | #FF7BFF | MEP3 | CHI11-ADMIN-25 | MATCHING | Admin/ Elec Rm- ELC Rough-In & OH | 20-Jan-2025 | 20-Mar-2025
Fitout | Admin | Electrical Room | Anning Johnson | #2490FF | D13 | CHI11-ADMIN-50 | MATCHING | Admin/ Elec Rm- Top Out Drywall | 13-Feb-2025 | 15-Feb-2025
Fitout | Admin | Electrical Room | Anning Johnson | #2490FF | D15 | CHI11-ADMIN-105 | MATCHING | Admin/ Elec Rm- Finsh Drywall and Wall Protection | 28-Feb-2025 | 03-Mar-2025
Fitout | Admin | Electrical Room | Continental - TBD | #D6F2FF | Y1 | CHI11-ADMIN-200 | MATCHING | Admin/ Elec Rm- Paint | 07-Mar-2025 | 13-Mar-2025
Fitout | Admin | Electrical Room | GIBSON | #FFF9B1 | EE43 | CHI11-ADMIN-230 | MATCHING | Admin/ Elec Rm- Set Electrical Equipment in Admin | 26-Mar-2025 | 11-Apr-2025
Fitout | Admin | Entry Room 1 | Shambaugh | #D76672 | R1 | CHI11-ADMIN-20 | MATCHING | Admin/ Ent Rm-01- Fire Protection OH R/I | 15-Jan-2025 | 23-Jan-2025
Fitout | Admin | Entry Room 1 | Anning Johnson | #2490FF | D3 | CHI11-ADMIN-30 | MATCHING | Admin/ Ent Rm-01- Framing | 17-Jan-2025 | 13-Feb-2025
Fitout | Admin | Entry Room 1 | MEP | #FF7BFF | MEP3 | CHI11-ADMIN-55 | MATCHING | Admin/ Ent Rm-01- MEP Rough-In & OH | 24-Jan-2025 | 20-Mar-2025
Fitout | Admin | Entry Room 1 | Anning Johnson | #2490FF | D13 | CHI11-ADMIN-85 | MATCHING | Admin/ Ent Rm-01- Top Out Drywall | 13-Feb-2025 | 15-Feb-2025
Fitout | Admin | Entry Room 1 | Anning Johnson | #2490FF | D15 | CHI11-ADMIN-155 | MATCHING | Admin/ Ent Rm-01- Finsh Drywall and Wall Protection | 28-Feb-2025 | 17-Mar-2025
Fitout | Admin | Entry Room 1 | Continental - TBD | #D6F2FF | Y1 | CHI11-ADMIN-235 | MATCHING | Admin/ Ent Rm-01- Paint | 07-Mar-2025 | 18-Mar-2025
Fitout | Admin | Entry Room 1 | GIBSON | #FFF9B1 | EE21 | CHI11-ADMIN-260 | MATCHING | Admin/ Ent Rm-01- Install Raceway | 28-Mar-2025 | 10-Apr-2025
Fitout | Admin | Entry Room 2 | Shambaugh | #D76672 | R1 | CHI11-ADMIN-35 | MATCHING | Admin/ Ent Rm-02- Fire Protection OH R/I | 15-Jan-2025 | 23-Jan-2025
Fitout | Admin | Entry Room 2 | Anning Johnson | #2490FF | D3 | CHI11-ADMIN-40 | MATCHING | Admin/ Ent Rm-02- Framing | 17-Jan-2025 | 13-Feb-2025
Fitout | Admin | Entry Room 2 | MEP | #FF7BFF | MEP3 | CHI11-ADMIN-90 | MATCHING | Admin/ Ent Rm-02- MEP Rough-In & OH | 27-Jan-2025 | 20-Mar-2025
Fitout | Admin | Entry Room 2 | Anning Johnson | #2490FF | D13 | CHI11-ADMIN-125 | MATCHING | Admin/ Ent Rm-02- Top Out Drywall | 13-Feb-2025 | 15-Feb-2025
Fitout | Admin | Entry Room 2 | Anning Johnson | #2490FF | D15 | CHI11-ADMIN-195 | MATCHING | Admin/ Ent Rm-02- Finsh Drywall and Wall Protection | 28-Feb-2025 | 17-Mar-2025
Fitout | Admin | Entry Room 2 | Continental - TBD | #D6F2FF | Y1 | CHI11-ADMIN-265 | MATCHING | Admin/ Ent Rm-02- Paint | 07-Mar-2025 | 18-Mar-2025
Fitout | Admin | Entry Room 2 | GIBSON | #FFF9B1 | EE21 | CHI11-ADMIN-285 | MATCHING | Admin/ Ent Rm-02- Install Raceway | 28-Mar-2025 | 10-Apr-2025
Fitout | Admin | FCR (Facilities Control Room) | Shambaugh | #D76672 | R1 | CHI11-ADMIN-45 | MATCHING | ADMIN/ FCR- Fire Protection OH R/I | 16-Jan-2025 | 23-Jan-2025
Fitout | Admin | FCR (Facilities Control Room) | MEP | #FF7BFF | MEP3 | CHI11-ADMIN-130 | MATCHING | ADMIN/ FCR- MEP Rough-In & OH | 29-Jan-2025 | 20-Mar-2025
Fitout | Admin | FCR (Facilities Control Room) | Anning Johnson | #2490FF | D3 | CHI11-ADMIN-60 | MATCHING | ADMIN/ FCR- Framing | 12-Feb-2025 | 13-Feb-2025
Fitout | Admin | FCR (Facilities Control Room) | Anning Johnson | #2490FF | D13 | CHI11-ADMIN-175 | MATCHING | ADMIN/ FCR- Top Out Drywall | 14-Feb-2025 | 15-Feb-2025
Fitout | Admin | FCR (Facilities Control Room) | Anning Johnson | #2490FF | D15 | CHI11-ADMIN-225 | MATCHING | ADMIN/ FCR- Finsh Drywall and Wall Protection | 28-Feb-2025 | 18-Mar-2025
Fitout | Admin | FCR (Facilities Control Room) | Continental - TBD | #D6F2FF | Y1 | CHI11-ADMIN-290 | MATCHING | ADMIN/ FCR- Paint | 07-Mar-2025 | 18-Mar-2025
Fitout | Admin | FCR (Facilities Control Room) | GIBSON | #FFF9B1 | EE21 | CHI11-ADMIN-325 | MATCHING | ADMIN/ FCR- Install Raceway | 04-Apr-2025 | 07-Apr-2025
Fitout | Admin | SER (Security Equipment Room) | Shambaugh | #D76672 | R1 | CHI11-ADMIN-65 | MATCHING | ADMIN/ SER- Fire Protection OH R/I | 16-Jan-2025 | 23-Jan-2025
Fitout | Admin | SER (Security Equipment Room) | Anning Johnson | #2490FF | D3 | CHI11-ADMIN-70 | MATCHING | ADMIN/ SER- Framing | 12-Feb-2025 | 13-Feb-2025
Fitout | Admin | SER (Security Equipment Room) | Anning Johnson | #2490FF | D13 | CHI11-ADMIN-210 | MATCHING | ADMIN/ SER- Top Out Drywall | 14-Feb-2025 | 15-Feb-2025
Fitout | Admin | SER (Security Equipment Room) | MEP | #FF7BFF | MEP3 | CHI11-ADMIN-180 | MATCHING | ADMIN/ SER- MEP Rough-In & OH | 18-Feb-2025 | 20-Mar-2025
Fitout | Admin | SER (Security Equipment Room) | Anning Johnson | #2490FF | D14 | CHI11-ADMIN-255 | MATCHING | ADMIN/ SER- Finsh Drywall | 28-Feb-2025 | 03-Mar-2025
Fitout | Admin | SER (Security Equipment Room) | Continental - TBD | #D6F2FF | Y1 | CHI11-ADMIN-295 | MATCHING | ADMIN/ SER- Paint | 07-Mar-2025 | 18-Mar-2025
Fitout | Admin | SER (Security Equipment Room) | GIBSON | #FFF9B1 | EE21 | CHI11-ADMIN-330 | MATCHING | ADMIN/ SER- Install Raceway | 04-Apr-2025 | 07-Apr-2025
Fitout | Admin | STORAGE (High Value & Secure) Rooms | Shambaugh | #D76672 | R1 | CHI11-ADMIN-75 | MATCHING | Admin/ High Value Rm- Fire Protection OH R/I | 16-Jan-2025 | 23-Jan-2025
Fitout | Admin | STORAGE (High Value & Secure) Rooms | Anning Johnson | #2490FF | D3 | CHI11-ADMIN-95 | MATCHING | Admin/ High Value Rm- Framing | 12-Feb-2025 | 13-Feb-2025
Fitout | Admin | STORAGE (High Value & Secure) Rooms | Anning Johnson | #2490FF | D13 | CHI11-ADMIN-245 | MATCHING | Admin/ High Value Rm- Top Out Drywall | 14-Feb-2025 | 15-Feb-2025
Fitout | Admin | STORAGE (High Value & Secure) Rooms | Hill Mechanical | #C9DF56 | M6 | CHI11-ADMIN-270 | MATCHING | Admin/ High Value Rm- Install Ductwork and Cracs | 14-Feb-2025 | 20-Mar-2025
Fitout | Admin | STORAGE (High Value & Secure) Rooms | MEP | #FF7BFF | MEP3 | CHI11-ADMIN-215 | MATCHING | Admin/ High Value Rm- MEP Rough-In & OH | 18-Feb-2025 | 20-Mar-2025
Fitout | Admin | STORAGE (High Value & Secure) Rooms | Anning Johnson | #2490FF | D14 | CHI11-ADMIN-420 | MATCHING | Admin/ High Value Rm- Finsh Drywall | 03-Mar-2025 | 06-Mar-2025
Fitout | Admin | STORAGE (High Value & Secure) Rooms | Continental - TBD | #D6F2FF | Y1 | CHI11-ADMIN-430 | MATCHING | Admin/ High Value Rm- Paint | 15-Mar-2025 | 17-Mar-2025
Fitout | Admin | Restrooms & Janitor Room | Shambaugh | #D76672 | R1 | CHI11-ADMIN-115 | MATCHING | Admin/ Other- Fire Protection OH R/I | 16-Jan-2025 | 31-Jan-2025
Fitout | Admin | Restrooms & Janitor Room | Anning Johnson | #2490FF | D3 | CHI11-ADMIN-135 | MATCHING | Admin/ Other- Framing | 12-Feb-2025 | 13-Feb-2025
Fitout | Admin | Restrooms & Janitor Room | Anning Johnson | #2490FF | D13 | CHI11-ADMIN-305 | MATCHING | Admin/ Other- Top Out Drywall | 14-Feb-2025 | 15-Feb-2025
Fitout | Admin | Restrooms & Janitor Room | MEP | #FF7BFF | MEP3 | CHI11-ADMIN-280 | MATCHING | Admin/ Other- MEP Rough-In & OH | 18-Feb-2025 | 20-Mar-2025
Fitout | Admin | Restrooms & Janitor Room | Anning Johnson | #2490FF | D14 | CHI11-ADMIN-335 | MATCHING | Admin/ Other- Finsh Drywall | 03-Mar-2025 | 29-Mar-2025
Fitout | Admin | Restrooms & Janitor Room | Continental - TBD | #D6F2FF | Y1 | CHI11-ADMIN-360 | MATCHING | Admin/ Other- Paint | 15-Mar-2025 | 07-May-2025
Fitout | Admin | Restrooms & Janitor Room | Anning Johnson | #2490FF | D2 | CHI11-ADMIN-385 | MATCHING | Admin/ Other- Ceiling Grid & Tile | 22-Apr-2025 | 24-Apr-2025
Fitout | Admin | Loading Dock | Shambaugh | #D76672 | R1 | CHI11-ADMIN-140 | MATCHING | Admin/ Loading Dock- Fire Protection OH R/I | 24-Jan-2025 | 28-Jan-2025
Fitout | Admin | Loading Dock | Anning Johnson | #2490FF | D3 | CHI11-ADMIN-165 | MATCHING | Admin/ Loading Dock- Framing | 12-Feb-2025 | 13-Feb-2025
Fitout | Admin | Loading Dock | Anning Johnson | #2490FF | D13 | CHI11-ADMIN-340 | MATCHING | Admin/ Loading Dock- Top Out Drywall | 14-Feb-2025 | 15-Feb-2025
Fitout | Admin | Loading Dock | MEP | #FF7BFF | MEP3 | CHI11-ADMIN-185 | MATCHING | Admin/ Loading Dock- Rough-in | 14-Feb-2025 | 14-Feb-2025
Fitout | Admin | Loading Dock | MEP | #FF7BFF | MEP3 | CHI11-ADMIN-315 | MATCHING | Admin/ Loading Dock- MEP Rough-In & OH | 18-Feb-2025 | 20-Mar-2025
Fitout | Admin | Loading Dock | Hill Mechanical | #C9DF56 | M1 | CHI11-ADMIN-150 | MATCHING | Admin/ Loading Dock- Install Ductwork | 25-Feb-2025 | 20-Mar-2025
Fitout | Admin | Loading Dock | Anning Johnson | #2490FF | D14 | CHI11-ADMIN-365 | MATCHING | Admin/ Loading Dock- Finsh Drywall | 03-Mar-2025 | 06-Mar-2025
Fitout | Admin | Loading Dock | Hill Mechanical | #C9DF56 | M1 | CHI11-ADMIN-160 | MATCHING | Admin/ Loading Dock- Install Ductwork (Remaining Rooms, Corridor) | 13-Mar-2025 | 20-Mar-2025
FITOUT | COLO 3 | CELL 1 TELECOM | CECCO | #EF9E5B | T2 | CHI11-03-01-TEL-20 | MATCHING | C03/01 - MOR Cabinets | 11-Apr-2025 | 12-May-2025
Fitout | COLO 3 | COLO 3 CELL 1 TELECOM | GIBSON | #FFF9B1 | EE56 | CHI11-03-01-TEL-92 | MATCHING | C03 - CEI Cabinet | 14-Apr-2025 | 15-Apr-2025
FITOUT | COLO 3 | CELL 1 TELECOM | CECCO | #EF9E5B | T7 | CHI11-03-01-TEL-30 | MATCHING | C03/01 - OOB (out of bands) | 30-Apr-2025 | 16-May-2025
FITOUT | COLO 3 | CELL 1 TELECOM | CECCO | #EF9E5B | T4 | CHI11-03-01-TEL-60 | MATCHING | C03/01 - Backbone Fiber | 05-May-2025 | 09-May-2025
Fitout | COLO 3 | COLO 3 CELL 1 TELECOM CEI Fiber Backbone | GIBSON | #FFF9B1 | EE57 | CHI11-03-01-TEL-41 | MATCHING | C03 - Pull EPMS Fiber Blue Route | 21-Apr-2025 | 26-Apr-2025
Fitout | COLO 3 | COLO 3 CELL 1 TELECOM CEI Fiber Backbone | GIBSON | #FFF9B1 | EE58 | CHI11-03-01-TEL-42 | MATCHING | C03 - Pull EPMS Fiber RED Route | 28-Apr-2025 | 05-May-2025
Fitout | COLO 3 | COLO 3 CELL 1 TELECOM CEI Fiber Backbone | GIBSON | #FFF9B1 | EE59 | CHI11-03-01-TEL-43 | MATCHING | C03 - Port Fiber Blue Route | 28-Apr-2025 | 02-May-2025
Fitout | COLO 3 | COLO 3 CELL 1 TELECOM CEI Fiber Backbone | GIBSON | #FFF9B1 | EE60 | CHI11-03-01-TEL-45 | MATCHING | C03 - Test EPMS Fiber Blue Route | 05-May-2025 | 05-May-2025
Fitout | COLO 3 | COLO 3 CELL 1 TELECOM CEI Fiber Backbone | GIBSON | #FFF9B1 | EE61 | CHI11-03-01-TEL-44 | MATCHING | C03 - Port Fiber Red Route | 05-May-2025 | 05-May-2025
Fitout | COLO 3 | COLO 3 CELL 1 TELECOM CEI Fiber Backbone | GIBSON | #FFF9B1 | EE62 | CHI11-03-01-TEL-46 | MATCHING | C03 - Test EPMS Fiber RED Route | 06-May-2025 | 06-May-2025
FITOUT | COLO 3 | CELL 1 TELECOM | CECCO | #EF9E5B | T1 | CHI11-03-01-TEL-40 | MATCHING | C03/01 - Pull EPMS Copper | 21-Apr-2025 | 24-Apr-2025
Fitout | COLO 3 | COLO 3 CELL 1 TELECOM EPMS | CECCO | #EF9E5B | T16 | CHI11-03-01-TEL-05 | MATCHING | C03/01 - Terminate EPMS Copper | 21-Apr-2025 | 02-May-2025
Fitout | COLO 3 | COLO 3 CELL 1 TELECOM EPMS | CECCO | #EF9E5B | T17 | CHI11-03-01-TEL-06 | MATCHING | C03/01 - Test EPMS Copper | 01-May-2025 | 06-May-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | Anning Johnson | #2490FF | D10 | CHI11-03-01-10 | MATCHING | C03/01-DH- Layout Framing | 14-Jan-2025 | 15-Jan-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | Anning Johnson | #2490FF | D7 | CHI11-03-01-15 | MATCHING | C03/01-DH- Install Framing | 17-Jan-2025 | 22-Jan-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | MEP | #FF7BFF | MEP2 | CHI11-03-01-20 | MATCHING | C03/01-DH- In-Wall R/I | 23-Jan-2025 | 25-Jan-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | Shambaugh | #D76672 | R2 | CHI11-03-01-30 | MATCHING | C03/01-DH- Overhead R/I - Fire Protection | 27-Jan-2025 | 31-Jan-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | Anning Johnson | #2490FF | D23 | CHI11-03-01-35 | MATCHING | C03/01-DH- Install Drywall (Drywall Tops) | 27-Jan-2025 | 31-Jan-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE51 | CHI11-03-01-45 | MATCHING | C03/01-DH- Overhead R/I - Fire Alarm | 01-Feb-2025 | 04-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE28 | CHI11-03-01-50 | MATCHING | C03/01-DH- Overhead R/I - Electrical | 01-Feb-2025 | 05-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | Anning Johnson | #2490FF | D20 | CHI11-03-01-55 | MATCHING | C03/01-DH- Finish Dry-Wall & Taping Bottoms | 10-Feb-2025 | 13-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | Continental - TBD | #D6F2FF | Y2 | CHI11-03-01-70 | MATCHING | C03/01-DH- Paint Dry-Wall | 12-Feb-2025 | 14-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | Imperial/Span | #E0D0D0 | X7 | CHI11-03-01-90 | MATCHING | C03/01-DH- Install Secondary Steel | 12-Feb-2025 | 13-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | Continental - TBD | #D6F2FF | Y3 | CHI11-03-01-110 | MATCHING | C03/01-DH- Paint Secondary Steel | 17-Feb-2025 | 18-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | Anning Johnson | #2490FF | D8 | CHI11-03-01-75 | MATCHING | C03/01-DH- Install Screen Mesh + Caulking | 19-Feb-2025 | 22-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | Anning Johnson | #2490FF | D4 | CHI11-03-01-140 | MATCHING | C03/01-DH- Install Ceiling Grid | 24-Feb-2025 | 26-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE10 | CHI11-03-01-65 | MATCHING | C03/01-DH- Drop Cable Tray [Hanging Rods] | 03-Mar-2025 | 29-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | Cleaning | #FFC6FF | C1 | CHI11-03-01-135 | MATCHING | C03/01-DH- General Cleaning | 11-Mar-2025 | 11-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | Anning Johnson | #2490FF | D21 | CHI11-03-01-175 | MATCHING | C03/01-DH- Install Device Tiles | 11-Mar-2025 | 12-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE20 | CHI11-03-01-150 | MATCHING | C03/01-DH- Install Perimeter Cable Trays | 14-Mar-2025 | 18-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE1 | CHI11-03-01-155 | MATCHING | C03/01-DH- Assemble HACs [Qty - 5] | 14-Mar-2025 | 19-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE14 | CHI11-03-01-165 | MATCHING | C03/01-DH- Install Busways on HAC Arms | 20-Mar-2025 | 27-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | Anning Johnson | #FFF9B1 | EE42 | CHI11-03-01-200 | MATCHING | C03/01-DH- Raise HACs | 28-Mar-2025 | 29-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE9 | CHI11-03-01-235 | MATCHING | C03/01-DH- Detail HACs | 31-Mar-2025 | 03-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE45 | CHI11-03-01-185 | MATCHING | C03/01-DH- Set PDUs | 04-Apr-2025 | 08-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE8 | CHI11-03-01-240 | MATCHING | C03/01-DH- Connect Perimeter Cable Trays to HAC Cable Trays | 11-Apr-2025 | 15-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE16 | CHI11-03-01-260 | MATCHING | C03/01-DH- Install Conduits PDU to Cable Trays | 18-Apr-2025 | 01-May-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE50 | CHI11-03-01-305 | MATCHING | C03/01-DH- Terminate PDUs | 08-May-2025 | 30-May-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE39 | CHI11-03-01-275 | MATCHING | C03/01-DH- Pull Feeders from PDUs to Busways | 09-May-2025 | 10-May-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | Shambaugh | #D76672 | R2 | CHI11-03-01-80 | MATCHING | C03/01-Elec Rm- Overhead R/I - Fire Protection | 31-Jan-2025 | 03-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE28 | CHI11-03-01-100 | MATCHING | C03/01-Elec Rm- Overhead R/I - Electrical | 03-Feb-2025 | 05-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE51 | CHI11-03-01-95 | MATCHING | C03/01-Elec Rm- Overhead R/I - Fire Alarm | 04-Feb-2025 | 05-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | Imperial/Span | #E0D0D0 | X7 | CHI11-03-01-450 | MATCHING | C03/01-Elec Rm- Install Secondary Steel | 07-Feb-2025 | 12-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | Anning Johnson | #2490FF | D7 | CHI11-03-01-25 | MATCHING | C03/01-Elec Rm- Install Framing | 12-Feb-2025 | 13-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | MEP | #FF7BFF | MEP2 | CHI11-03-01-40 | MATCHING | C03/01-Elec Rm- In-Wall R/I | 13-Feb-2025 | 20-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | Anning Johnson | #2490FF | D17 | CHI11-03-01-85 | MATCHING | C03/01-Elec Rm- Install Drywall [Elec + Battery Rooms] | 19-Feb-2025 | 20-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | Anning Johnson | #2490FF | D14 | CHI11-03-01-160 | MATCHING | C03/01-Elec Rm- Finish Dry-Wall | 20-Feb-2025 | 22-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | Continental - TBD | #D6F2FF | Y2 | CHI11-03-01-195 | MATCHING | C03/01-Elec Rm- Paint Dry-Wall | 03-Mar-2025 | 04-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE10 | CHI11-03-01-115 | MATCHING | C03/01-Elec Rm- Drop Cable Tray [Hanging Rods] | 06-Mar-2025 | 10-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | Cleaning | #FFC6FF | C1 | CHI11-03-01-215 | MATCHING | C03/01-Elec Rm- General Cleaning | 10-Mar-2025 | 10-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE43 | CHI11-03-01-230 | MATCHING | C03/01-Elec Rm- Set Electrical Equipments | 10-Mar-2025 | 14-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | Hill Mechanical | #C9DF56 | M3 | CHI11-03-01-60 | MATCHING | C03/01-Elec Rm- Overhead R/I - Mechanical | 18-Mar-2025 | 20-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE15 | CHI11-03-01-130 | MATCHING | C03/01-Elec Rm- Install Cable Trays / Pathways/Cable Bus | 14-Apr-2025 | 25-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE33 | CHI11-03-01-270 | MATCHING | C03/01-Elec Rm- Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 28-Apr-2025 | 15-May-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE38 | CHI11-03-01-295 | MATCHING | C03/01-DH- Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 28-Apr-2025 | 05-May-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | Shambaugh | #D76672 | R2 | CHI11-03-01-105 | MATCHING | C03/01-Mech Gallery- Overhead R/I - Fire Protection | 13-Feb-2025 | 14-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE51 | CHI11-03-01-120 | MATCHING | C03/01-Mech Gallery- Overhead R/I - Fire Alarm | 14-Feb-2025 | 17-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE28 | CHI11-03-01-125 | MATCHING | C03/01-Mech Gallery- Overhead R/I - Electrical | 14-Feb-2025 | 17-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | Hill Mechanical | #C9DF56 | M3 | CHI11-03-01-145 | MATCHING | C03/01-Mech Gallery- Overhead R/I - Mechanical | 18-Feb-2025 | 13-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | Anning Johnson | #2490FF | D18 | CHI11-03-01-190 | MATCHING | C03/01-Mech Gallery- Install Drywall [Mech Gallery] | 28-Feb-2025 | 04-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | Plumbing | #1F595B | P2 | CHI11-03-01-170 | MATCHING | C03/01-Mech Gallery- Overhead R/I - Plumbing | 28-Feb-2025 | 10-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | Anning Johnson | #2490FF | D14 | CHI11-03-01-205 | MATCHING | C03/01-Mech Gallery- Finish Dry-Wall | 05-Mar-2025 | 07-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | Continental - TBD | #D6F2FF | Y2 | CHI11-03-01-225 | MATCHING | C03/01-Mech Gallery- Paint Dry-Wall | 07-Mar-2025 | 08-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | Anning Johnson | #2490FF | D5 | CHI11-03-01-220 | MATCHING | C03/01-Mech Gallery- Install Ceiling Grid + Device Tiles | 07-Mar-2025 | 11-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | Cleaning | #FFC6FF | C1 | CHI11-03-01-245 | MATCHING | C03/01-Mech Gallery- General Cleaning | 10-Mar-2025 | 12-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE13 | CHI11-03-01-255 | MATCHING | C03/01-Mech Gallery- Install BAS Equipments | 12-Mar-2025 | 05-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | Hill Mechanical | #C9DF56 | M4 | CHI11-03-01-265 | MATCHING | C03/01-Mech Gallery- Set Mechanical Equipments | 13-Mar-2025 | 01-Apr-2025
FITOUT | COLO 3 | CELL 2 TELECOM | CECCO | #EF9E5B | T2 | CHI11-03-02-TEL-100 | MATCHING | C03/02 - MOR Cabinets | 29-Apr-2025 | 09-May-2025
FITOUT | COLO 3 | CELL 2 TELECOM | CECCO | #EF9E5B | T7 | CHI11-03-02-TEL-130 | MATCHING | C03/02 - OOB (out of bands) | 09-May-2025 | 22-May-2025
FITOUT | COLO 3 | CELL 2 TELECOM | CECCO | #EF9E5B | T4 | CHI11-03-02-TEL-180 | MATCHING | C03/02 - Backbone Fiber | 16-May-2025 | 22-May-2025
FITOUT | COLO 3 | CELL 2 TELECOM | CECCO | #EF9E5B | T6 | CHI11-03-02-TEL-150 | MATCHING | C03/02 - Production Fiber (Plug/TEST) | 11-Jun-2025 | 25-Jun-2025
FITOUT | COLO 3 | CELL 2 TELECOM | CECCO | #EF9E5B | T1 | CHI11-03-02-TEL-160 | MATCHING | C03/02 - Pull EPMS Copper | 25-Apr-2025 | 02-May-2025
Fitout | COLO 3 | COLO 3 CELL 2 TELECOM EPMS | CECCO | #EF9E5B | T16 | CHI11-03-02-TEL-09 | MATCHING | C03/02 - Terminate EPMS Copper | 02-May-2025 | 13-May-2025
Fitout | COLO 3 | COLO 3 CELL 2 TELECOM EPMS | CECCO | #EF9E5B | T17 | CHI11-03-02-TEL-11 | MATCHING | C03/02 - Test EPMS Copper | 07-May-2025 | 14-May-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | Anning Johnson | #2490FF | D10 | CHI11-03-02-10 | MATCHING | C03/02-DH- Layout Framing | 20-Jan-2025 | 22-Jan-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | Anning Johnson | #2490FF | D7 | CHI11-03-02-15 | MATCHING | C03/02-DH- Install Framing | 23-Jan-2025 | 31-Jan-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | MEP | #FF7BFF | MEP2 | CHI11-03-02-20 | MATCHING | C03/02-DH- In-Wall R/I | 31-Jan-2025 | 03-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | Shambaugh | #D76672 | R2 | CHI11-03-02-35 | MATCHING | C03/02-DH- Overhead R/I - Fire Protection | 04-Feb-2025 | 06-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE51 | CHI11-03-02-55 | MATCHING | C03/02-DH- Overhead R/I - Fire Alarm | 04-Feb-2025 | 06-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | Anning Johnson | #2490FF | D23 | CHI11-03-02-40 | MATCHING | C03/02-DH- Install Drywall (Drywall Tops) | 04-Feb-2025 | 06-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE28 | CHI11-03-02-60 | MATCHING | C03/02-DH- Overhead R/I - Electrical | 07-Feb-2025 | 12-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | Anning Johnson | #2490FF | D20 | CHI11-03-02-65 | MATCHING | C03/02-DH- Finish Dry-Wall & Taping Bottoms | 11-Feb-2025 | 14-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | Continental - TBD | #D6F2FF | Y2 | CHI11-03-02-115 | MATCHING | C03/02-DH- Paint Dry-Wall | 12-Feb-2025 | 19-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | Imperial/Span | #E0D0D0 | X7 | CHI11-03-02-145 | MATCHING | C03/02-DH- Install Secondary Steel | 13-Feb-2025 | 14-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | Continental - TBD | #D6F2FF | Y3 | CHI11-03-02-150 | MATCHING | C03/02-DH- Paint Secondary Steel | 20-Feb-2025 | 21-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | Anning Johnson | #2490FF | D8 | CHI11-03-02-135 | MATCHING | C03/02-DH- Install Screen Mesh + Caulking | 21-Feb-2025 | 24-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | Anning Johnson | #2490FF | D4 | CHI11-03-02-165 | MATCHING | C03/02-DH- Install Ceiling Grid | 25-Feb-2025 | 27-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE10 | CHI11-03-02-90 | MATCHING | C03/02-DH- Drop Cable Tray [Hanging Rods] | 04-Mar-2025 | 13-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | Anning Johnson | #2490FF | D21 | CHI11-03-02-210 | MATCHING | C03/02-DH- Install Device Tiles | 10-Mar-2025 | 11-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | Cleaning | #FFC6FF | C1 | CHI11-03-02-160 | MATCHING | C03/02-DH- General Cleaning | 13-Mar-2025 | 13-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE20 | CHI11-03-02-175 | MATCHING | C03/02-DH- Install Perimeter Cable Trays | 18-Mar-2025 | 21-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE1 | CHI11-03-02-180 | MATCHING | C03/02-DH- Assemble HACs [Qty - 5] | 20-Mar-2025 | 29-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE14 | CHI11-03-02-200 | MATCHING | C03/02-DH- Install Busways on HAC Arms | 31-Mar-2025 | 03-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | Anning Johnson | #2490FF | EE42 | CHI11-03-02-245 | MATCHING | C03/02-DH- Raise HACs | 31-Mar-2025 | 03-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE9 | CHI11-03-02-260 | MATCHING | C03/02-DH- Detail HACs | 04-Apr-2025 | 08-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE45 | CHI11-03-02-220 | MATCHING | C03/02-DH- Set PDUs | 04-Apr-2025 | 08-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE8 | CHI11-03-02-265 | MATCHING | C03/02-DH- Connect Perimeter Cable Trays to HAC Cable Trays | 11-Apr-2025 | 15-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE16 | CHI11-03-02-275 | MATCHING | C03/02-DH- Install Conduits PDU to Cable Trays | 28-Apr-2025 | 15-May-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE39 | CHI11-03-02-285 | MATCHING | C03/02-DH- Pull Feeders from PDUs to Busways | 28-Apr-2025 | 10-May-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE50 | CHI11-03-02-310 | MATCHING | C03/02-DH- Terminate PDUs | 12-May-2025 | 30-May-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | Shambaugh | #D76672 | R2 | CHI11-03-02-45 | MATCHING | C03/02-Elec Rm- Overhead R/I - Fire Protection | 31-Jan-2025 | 01-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE28 | CHI11-03-02-75 | MATCHING | C03/02-Elec Rm- Overhead R/I - Electrical | 31-Jan-2025 | 03-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE51 | CHI11-03-02-70 | MATCHING | C03/02-Elec Rm- Overhead R/I - Fire Alarm | 03-Feb-2025 | 04-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | Imperial/Span | #E0D0D0 | X7 | CHI11-03-02-600 | MATCHING | C03/02-Elec Rm- Install Secondary Steel | 07-Feb-2025 | 11-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | Anning Johnson | #2490FF | D7 | CHI11-03-02-25 | MATCHING | C03/02-Elec Rm- Install Framing | 12-Feb-2025 | 13-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | MEP | #FF7BFF | MEP2 | CHI11-03-02-30 | MATCHING | C03/02-Elec Rm- In-Wall R/I | 13-Feb-2025 | 14-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | Anning Johnson | #2490FF | D17 | CHI11-03-02-50 | MATCHING | C03/02-Elec Rm- Install Drywall [Elec + Battery Rooms] | 14-Feb-2025 | 19-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | Anning Johnson | #2490FF | D14 | CHI11-03-02-95 | MATCHING | C03/02-Elec Rm- Finish Dry-Wall | 20-Feb-2025 | 21-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | Continental - TBD | #D6F2FF | Y2 | CHI11-03-02-125 | MATCHING | C03/02-Elec Rm- Paint Dry-Wall | 03-Mar-2025 | 05-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE10 | CHI11-03-02-100 | MATCHING | C03/02-Elec Rm- Drop Cable Tray [Hanging Rods] | 06-Mar-2025 | 10-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | Cleaning | #FFC6FF | C1 | CHI11-03-02-140 | MATCHING | C03/02-Elec Rm- General Cleaning | 10-Mar-2025 | 10-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE43 | CHI11-03-02-250 | MATCHING | C03/02-Elec Rm- Set Electrical Equipments | 10-Mar-2025 | 14-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | Hill Mechanical | #C9DF56 | M3 | CHI11-03-02-85 | MATCHING | C03/02-Elec Rm- Overhead R/I - Mechanical | 18-Mar-2025 | 20-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE15 | CHI11-03-02-120 | MATCHING | C03/02-Elec Rm- Install Cable Trays / Pathways/Cable Bus | 11-Apr-2025 | 25-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | GIBSON | #FFF9B2 | EE33 | CHI11-03-02-295 | MATCHING | C03/02-Elec Rm- Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 01-May-2025 | 29-May-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | GIBSON | #FFF9B3 | EE38 | CHI11-03-02-305 | MATCHING | C03/02-Elec Rm- Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 01-May-2025 | 08-May-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | Shambaugh | #D76672 | R2 | CHI11-03-02-80 | MATCHING | C03/02-Mech Gallery- Overhead R/I - Fire Protection | 11-Feb-2025 | 12-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE51 | CHI11-03-02-105 | MATCHING | C03/02-Mech Gallery- Overhead R/I - Fire Alarm | 13-Feb-2025 | 14-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE28 | CHI11-03-02-110 | MATCHING | C03/02-Mech Gallery- Overhead R/I - Electrical | 13-Feb-2025 | 14-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | Hill Mechanical | #C9DF56 | M3 | CHI11-03-02-130 | MATCHING | C03/02-Mech Gallery- Overhead R/I - Mechanical | 17-Feb-2025 | 20-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | Plumbing | #1F595B | P2 | CHI11-03-02-155 | MATCHING | C03/02-Mech Gallery- Overhead R/I - Plumbing | 24-Feb-2025 | 10-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | Anning Johnson | #2490FF | D18 | CHI11-03-02-170 | MATCHING | C03/02-Mech Gallery- Install Drywall [Mech Gallery] | 25-Feb-2025 | 27-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | Anning Johnson | #2490FF | D14 | CHI11-03-02-185 | MATCHING | C03/02-Mech Gallery- Finish Dry-Wall | 04-Mar-2025 | 06-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | Continental - TBD | #D6F2FF | Y2 | CHI11-03-02-205 | MATCHING | C03/02-Mech Gallery- Paint Dry-Wall | 07-Mar-2025 | 11-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | Anning Johnson | #2490FF | D5 | CHI11-03-02-195 | MATCHING | C03/02-Mech Gallery- Install Ceiling Grid + Device Tiles | 08-Mar-2025 | 13-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE13 | CHI11-03-02-235 | MATCHING | C03/02-Mech Gallery- Install BAS Equipments | 28-Mar-2025 | 10-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | Hill Mechanical | #C9DF56 | M4 | CHI11-03-02-240 | MATCHING | C03/02-Mech Gallery- Set Mechanical Equipments | 02-Apr-2025 | 05-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | Cleaning | #FFC6FF | C1 | CHI11-03-02-225 | MATCHING | C03/02-Mech Gallery- General Cleaning | 03-Apr-2025 | 08-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE60 | CHI11-03-02-255 | MATCHING | C03/02-Mech Gallery- Pull Cable to Mechanical Equipments [From Electrical Room] | 29-May-2025 | 29-May-2025
FITOUT | COLO 3 | CELL 3 TELECOM | CECCO | #EF9E5B | T7 | CHI11-03-03-TEL-230 | MATCHING | C03/03 - OOB (out of bands) | 09-May-2025 | 15-May-2025
FITOUT | COLO 3 | CELL 3 TELECOM | CECCO | #EF9E5B | T2 | CHI11-03-03-TEL-190 | MATCHING | C03/03 - MOR Cabinets | 16-May-2025 | 19-May-2025
FITOUT | COLO 3 | CELL 3 TELECOM | CECCO | #EF9E5B | T4 | CHI11-03-03-TEL-260 | MATCHING | C03/03 - Backbone Fiber | 16-May-2025 | 22-May-2025
FITOUT | COLO 3 | CELL 3 TELECOM | CECCO | #EF9E5B | T1 | CHI11-03-03-TEL-240 | MATCHING | C03/03 - Pull EPMS | 29-Apr-2025 | 02-May-2025
Fitout | COLO 3 | COLO 3 CELL 3 TELECOM EPMS | CECCO | #EF9E5B | T16 | CHI11-03-03-TEL-13 | MATCHING | C03/03 - Terminate EPMS Copper | 30-Apr-2025 | 05-May-2025
Fitout | COLO 3 | COLO 3 CELL 3 TELECOM EPMS | CECCO | #EF9E5B | T17 | CHI11-03-03-TEL-14 | MATCHING | C03/03 - Test EPMS Copper | 05-May-2025 | 05-May-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | Anning Johnson | #2490FF | D10 | CHI11-03-03-10 | MATCHING | C03/03-DH- Layout Framing | 04-Feb-2025 | 04-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | Anning Johnson | #2490FF | D7 | CHI11-03-03-15 | MATCHING | C03/03-DH- Install Framing | 05-Feb-2025 | 06-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | MEP | #FF7BFF | MEP2 | CHI11-03-03-20 | MATCHING | C03/03-DH- In-Wall R/I | 07-Feb-2025 | 12-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | Shambaugh | #D76672 | R2 | CHI11-03-03-35 | MATCHING | C03/03-DH- Overhead R/I - Fire Protection | 13-Feb-2025 | 17-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE51 | CHI11-03-03-55 | MATCHING | C03/03-DH- Overhead R/I - Fire Alarm | 17-Feb-2025 | 20-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE28 | CHI11-03-03-60 | MATCHING | C03/03-DH- Overhead R/I - Electrical | 17-Feb-2025 | 20-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | Anning Johnson | #2490FF | D23 | CHI11-03-03-40 | MATCHING | C03/03-DH- Install Drywall (Drywall Tops) | 18-Feb-2025 | 20-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | Anning Johnson | #2490FF | D20 | CHI11-03-03-65 | MATCHING | C03/03-DH- Finish Dry-Wall & Taping Bottoms | 21-Feb-2025 | 24-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | Continental - TBD | #D6F2FF | Y2 | CHI11-03-03-115 | MATCHING | C03/03-DH- Paint Dry-Wall | 25-Feb-2025 | 26-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | Imperial/Span | #E0D0D0 | X7 | CHI11-03-03-150 | MATCHING | C03/03-DH- Install Secondary Steel | 27-Feb-2025 | 06-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | Anning Johnson | #2490FF | D8 | CHI11-03-03-135 | MATCHING | C03/03-DH- Install Screen Mesh + Caulking | 07-Mar-2025 | 11-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | Continental - TBD | #D6F2FF | Y3 | CHI11-03-03-155 | MATCHING | C03/03-DH- Paint Secondary Steel | 07-Mar-2025 | 11-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | Anning Johnson | #2490FF | D4 | CHI11-03-03-170 | MATCHING | C03/03-DH- Install Ceiling Grid | 08-Mar-2025 | 12-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE10 | CHI11-03-03-90 | MATCHING | C03/03-DH- Drop Cable Tray [Hanging Rods] | 13-Mar-2025 | 14-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | Anning Johnson | #2490FF | D21 | CHI11-03-03-215 | MATCHING | C03/03-DH- Install Device Tiles | 14-Mar-2025 | 14-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | Cleaning | #FFC6FF | C1 | CHI11-03-03-165 | MATCHING | C03/03-DH- General Cleaning | 15-Mar-2025 | 15-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE20 | CHI11-03-03-180 | MATCHING | C03/03-DH- Install Perimeter Cable Trays | 15-Mar-2025 | 19-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE1 | CHI11-03-03-185 | MATCHING | C03/03-DH- Assemble HACs [Qty - 5] | 31-Mar-2025 | 03-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE14 | CHI11-03-03-205 | MATCHING | C03/03-DH- Install Busways on HAC Arms | 03-Apr-2025 | 08-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE42 | CHI11-03-03-250 | MATCHING | C03/03-DH- Raise HACs | 09-Apr-2025 | 10-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE9 | CHI11-03-03-260 | MATCHING | C03/03-DH- Detail HACs | 09-Apr-2025 | 10-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE45 | CHI11-03-03-225 | MATCHING | C03/03-DH- Set PDUs | 11-Apr-2025 | 16-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE8 | CHI11-03-03-265 | MATCHING | C03/03-DH- Connect Perimeter Cable Trays to HAC Cable Trays | 11-Apr-2025 | 15-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE16 | CHI11-03-03-275 | MATCHING | C03/03-DH- Install Conduits PDU to Cable Trays | 30-Apr-2025 | 07-May-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | Shambaugh | #D76672 | R2 | CHI11-03-03-45 | MATCHING | C03/03-Elec Rm- Overhead R/I - Fire Protection | 04-Feb-2025 | 06-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE51 | CHI11-03-03-70 | MATCHING | C03/03-Elec Rm- Overhead R/I - Fire Alarm | 04-Feb-2025 | 06-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE28 | CHI11-03-03-75 | MATCHING | C03/03-Elec Rm- Overhead R/I - Electrical | 04-Feb-2025 | 06-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | Imperial/Span | #E0D0D0 | X7 | CHI11-03-03-850 | MATCHING | C03/03-Elec Rm- Secondary Steel | 14-Feb-2025 | 17-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | Anning Johnson | #2490FF | D7 | CHI11-03-03-25 | MATCHING | C03/03-Elec Rm- Install Framing | 18-Feb-2025 | 19-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | MEP | #FF7BFF | MEP2 | CHI11-03-03-30 | MATCHING | C03/03-Elec Rm- In-Wall R/I | 20-Feb-2025 | 21-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | Anning Johnson | #2490FF | D17 | CHI11-03-03-50 | MATCHING | C03/03-Elec Rm- Install Drywall [Elec + Battery Rooms] | 22-Feb-2025 | 25-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | Anning Johnson | #2490FF | D14 | CHI11-03-03-95 | MATCHING | C03/03-Elec Rm- Finish Dry-Wall | 26-Feb-2025 | 07-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | Continental - TBD | #D6F2FF | Y2 | CHI11-03-03-125 | MATCHING | C03/03-Elec Rm- Paint Dry-Wall | 08-Mar-2025 | 10-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | Hill Mechanical | #C9DF56 | M3 | CHI11-03-03-85 | MATCHING | C03/03-Elec Rm- Overhead R/I - Mechanical | 18-Mar-2025 | 20-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | Cleaning | #FFC6FF | C1 | CHI11-03-03-140 | MATCHING | C03/03-Elec Rm- General Cleaning | 21-Mar-2025 | 21-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE10 | CHI11-03-03-100 | MATCHING | C03/03-Elec Rm- Drop Cable Tray [Hanging Rods] | 21-Mar-2025 | 25-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE43 | CHI11-03-03-145 | MATCHING | C03/03-Elec Rm- Set Electrical Equipments | 17-Apr-2025 | 06-May-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE15 | CHI11-03-03-120 | MATCHING | C03/03-Elec Rm- Install Cable Trays / Pathways/Cable Bus | 21-Apr-2025 | 07-May-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE38 | CHI11-03-03-305 | MATCHING | C03/03-Elec Rm- Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 05-May-2025 | 19-May-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | Shambaugh | #D76672 | R2 | CHI11-03-03-80 | MATCHING | C03/03-Mech Gallery- Overhead R/I - Fire Protection | 21-Feb-2025 | 27-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE51 | CHI11-03-03-105 | MATCHING | C03/03-Mech Gallery- Overhead R/I - Fire Alarm | 21-Feb-2025 | 27-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE28 | CHI11-03-03-110 | MATCHING | C03/03-Mech Gallery- Overhead R/I - Electrical | 21-Feb-2025 | 27-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | Anning Johnson | #2490FF | D18 | CHI11-03-03-175 | MATCHING | C03/03-Mech Gallery- Install Drywall [Mech Gallery] | 28-Feb-2025 | 04-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | Hill Mechanical | #C9DF56 | M3 | CHI11-03-03-130 | MATCHING | C03/03-Mech Gallery- Overhead R/I - Mechanical | 03-Mar-2025 | 20-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | Anning Johnson | #2490FF | D14 | CHI11-03-03-190 | MATCHING | C03/03-Mech Gallery- Finish Dry-Wall | 05-Mar-2025 | 07-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | Continental - TBD | #D6F2FF | Y2 | CHI11-03-03-210 | MATCHING | C03/03-Mech Gallery- Paint Dry-Wall | 08-Mar-2025 | 10-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE13 | CHI11-03-03-240 | MATCHING | C03/03-Mech Gallery- Install BAS Equipments | 12-Mar-2025 | 10-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | Anning Johnson | #2490FF | D5 | CHI11-03-03-200 | MATCHING | C03/03-Mech Gallery- Install Ceiling Grid + Device Tiles | 20-Mar-2025 | 24-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | Plumbing | #1F595B | P2 | CHI11-03-03-160 | MATCHING | C03/03-Mech Gallery- Overhead R/I - Plumbing | 21-Mar-2025 | 10-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | Hill Mechanical | #C9DF56 | M4 | CHI11-03-03-245 | MATCHING | C03/03-Mech Gallery- Set Mechanical Equipments | 24-Mar-2025 | 01-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | Cleaning | #FFC6FF | C1 | CHI11-03-03-230 | MATCHING | C03/03-Mech Gallery- General Cleaning | 04-Apr-2025 | 07-Apr-2025
FITOUT | COLO 3 | CELL 4 TELECOM | CECCO | #EF9E5B | T7 | CHI11-03-04-TEL-320 | MATCHING | C03/04 - OOB (out of bands) | 09-May-2025 | 15-May-2025
FITOUT | COLO 3 | CELL 4 TELECOM | CECCO | #EF9E5B | T2 | CHI11-03-04-TEL-280 | MATCHING | C03/04 - MOR Cabinets | 16-May-2025 | 19-May-2025
FITOUT | COLO 3 | CELL 4 TELECOM | CECCO | #EF9E5B | T4 | CHI11-03-04-TEL-360 | MATCHING | C03/04 - Backbone Fiber | 20-May-2025 | 28-May-2025
FITOUT | COLO 3 | CELL 4 TELECOM | CECCO | #EF9E5B | T1 | CHI11-03-04-TEL-310 | MATCHING | C03/04 - Pull EPMS Copper | 30-Apr-2025 | 02-May-2025
Fitout | COLO 3 | COLO 3 CELL 4 TELECOM EPMS | CECCO | #EF9E5B | T16 | CHI11-03-04-TEL-31 | MATCHING | C03/04 - Terminate EPMS Copper | 30-Apr-2025 | 02-May-2025
Fitout | COLO 3 | COLO 3 CELL 4 TELECOM EPMS | CECCO | #EF9E5B | T17 | CHI11-03-04-TEL-32 | MATCHING | C03/04 - Test EPMS Copper | 30-Apr-2025 | 02-May-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | Anning Johnson | #2490FF | D10 | CHI11-03-04-10 | MATCHING | C03/04-DH- Layout Framing | 06-Feb-2025 | 06-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | Anning Johnson | #2490FF | D7 | CHI11-03-04-15 | MATCHING | C03/04-DH- Install Framing | 07-Feb-2025 | 10-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | MEP | #FF7BFF | MEP2 | CHI11-03-04-20 | MATCHING | C03/04-DH- In-Wall R/I | 11-Feb-2025 | 18-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | Shambaugh | #D76672 | R2 | CHI11-03-04-35 | MATCHING | C03/04-DH- Overhead R/I - Fire Protection | 15-Feb-2025 | 17-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE51 | CHI11-03-04-55 | MATCHING | C03/04-DH- Overhead R/I - Fire Alarm | 15-Feb-2025 | 17-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE28 | CHI11-03-04-60 | MATCHING | C03/04-DH- Overhead R/I - Electrical | 15-Feb-2025 | 17-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | Anning Johnson | #2490FF | D23 | CHI11-03-04-40 | MATCHING | C03/04-DH- Install Drywall (Drywall Tops) | 18-Feb-2025 | 20-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | Anning Johnson | #2490FF | D20 | CHI11-03-04-65 | MATCHING | C03/04-DH- Finish Dry-Wall & Taping Bottoms | 28-Feb-2025 | 05-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | Imperial/Span | #E0D0D0 | X7 | CHI11-03-04-150 | MATCHING | C03/04-DH- Install Secondary Steel | 04-Mar-2025 | 06-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | Continental - TBD | #D6F2FF | Y2 | CHI11-03-04-115 | MATCHING | C03/04-DH- Paint Dry-Wall | 06-Mar-2025 | 08-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | Continental - TBD | #D6F2FF | Y3 | CHI11-03-04-155 | MATCHING | C03/04-DH- Paint Secondary Steel | 06-Mar-2025 | 08-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | Anning Johnson | #2490FF | D8 | CHI11-03-04-135 | MATCHING | C03/04-DH- Install Screen Mesh + Caulking | 10-Mar-2025 | 12-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | Anning Johnson | #2490FF | D4 | CHI11-03-04-175 | MATCHING | C03/04-DH- Install Ceiling Grid | 13-Mar-2025 | 18-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE10 | CHI11-03-04-90 | MATCHING | C03/04-DH- Drop Cable Tray [Hanging Rods] | 19-Mar-2025 | 20-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | Anning Johnson | #2490FF | D21 | CHI11-03-04-220 | MATCHING | C03/04-DH- Install Device Tiles | 19-Mar-2025 | 20-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | Cleaning | #FFC6FF | C1 | CHI11-03-04-170 | MATCHING | C03/04-DH- General Cleaning | 04-Apr-2025 | 04-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE20 | CHI11-03-04-185 | MATCHING | C03/04-DH- Install Perimeter Cable Trays | 04-Apr-2025 | 08-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE39 | CHI11-03-04-295 | MATCHING | C03/04-DH- Pull Feeders from PDUs to Busways | 04-Apr-2025 | 10-May-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE1 | CHI11-03-04-190 | MATCHING | C03/04-DH- Assemble HACs [Qty - 5] | 05-Apr-2025 | 08-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE14 | CHI11-03-04-210 | MATCHING | C03/04-DH- Install Busways on HAC Arms | 08-Apr-2025 | 14-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE45 | CHI11-03-04-230 | MATCHING | C03/04-DH- Set PDUs | 11-Apr-2025 | 16-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | Anning Johnson | #FFF9B1 | EE42 | CHI11-03-04-260 | MATCHING | C03/04-DH- Raise HACs | 15-Apr-2025 | 17-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE9 | CHI11-03-04-270 | MATCHING | C03/04-DH- Detail HACs | 15-Apr-2025 | 15-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE8 | CHI11-03-04-275 | MATCHING | C03/04-DH- Connect Perimeter Cable Trays to HAC Cable Trays | 18-Apr-2025 | 21-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE16 | CHI11-03-04-285 | MATCHING | C03/04-DH- Install Conduits PDU to Cable Trays | 30-Apr-2025 | 02-May-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | Shambaugh | #D76672 | R2 | CHI11-03-04-45 | MATCHING | C03/04-Elec Rm- Overhead R/I - Fire Protection | 04-Feb-2025 | 06-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE51 | CHI11-03-04-70 | MATCHING | C03/04-Elec Rm- Overhead R/I - Fire Alarm | 04-Feb-2025 | 06-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE28 | CHI11-03-04-75 | MATCHING | C03/04-Elec Rm- Overhead R/I - Electrical | 04-Feb-2025 | 06-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | Imperial/Span | #E0D0D0 | X7 | CHI11-03-04-850 | MATCHING | C03/04-Elec Rm- Secondary Steel | 07-Feb-2025 | 19-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | Anning Johnson | #2490FF | D7 | CHI11-03-04-25 | MATCHING | C03/04-Elec Rm- Install Framing | 20-Feb-2025 | 20-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | MEP | #FF7BFF | MEP2 | CHI11-03-04-30 | MATCHING | C03/04-Elec Rm- In-Wall R/I | 28-Feb-2025 | 04-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | Anning Johnson | #2490FF | D17 | CHI11-03-04-50 | MATCHING | C03/04-Elec Rm- Install Drywall [Elec + Battery Rooms] | 05-Mar-2025 | 06-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | Anning Johnson | #2490FF | D14 | CHI11-03-04-95 | MATCHING | C03/04-Elec Rm- Finish Dry-Wall | 07-Mar-2025 | 10-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | Continental - TBD | #D6F2FF | Y2 | CHI11-03-04-125 | MATCHING | C03/04-Elec Rm- Paint Dry-Wall | 11-Mar-2025 | 12-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | Hill Mechanical | #C9DF56 | M3 | CHI11-03-04-85 | MATCHING | C03/04-Elec Rm- Overhead R/I - Mechanical | 14-Mar-2025 | 15-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE10 | CHI11-03-04-100 | MATCHING | C03/04-Elec Rm- Drop Cable Tray [Hanging Rods] | 15-Mar-2025 | 17-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | Cleaning | #FFC6FF | C1 | CHI11-03-04-140 | MATCHING | C03/04-Elec Rm- General Cleaning | 04-Apr-2025 | 04-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE43 | CHI11-03-04-145 | MATCHING | C03/04-Elec Rm- Set Electrical Equipments | 17-Apr-2025 | 06-May-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE15 | CHI11-03-04-120 | MATCHING | C03/04-Elec Rm- Install Cable Trays / Pathways/Cable Bus | 21-Apr-2025 | 12-May-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE38 | CHI11-03-04-305 | MATCHING | C03/04-Elec Rm- Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 09-May-2025 | 15-May-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | Shambaugh | #D76672 | R2 | CHI11-03-04-80 | MATCHING | C03/04-Mech Gallery- Overhead R/I - Fire Protection | 21-Feb-2025 | 27-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE51 | CHI11-03-04-105 | MATCHING | C03/04-Mech Gallery- Overhead R/I - Fire Alarm | 21-Feb-2025 | 27-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE28 | CHI11-03-04-110 | MATCHING | C03/04-Mech Gallery- Overhead R/I - Electrical | 21-Feb-2025 | 27-Feb-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | Anning Johnson | #2490FF | D18 | CHI11-03-04-180 | MATCHING | C03/04-Mech Gallery- Install Drywall [Mech Gallery] | 28-Feb-2025 | 04-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | Hill Mechanical | #C9DF56 | M3 | CHI11-03-04-130 | MATCHING | C03/04-Mech Gallery- Overhead R/I - Mechanical | 28-Feb-2025 | 19-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | Anning Johnson | #2490FF | D14 | CHI11-03-04-195 | MATCHING | C03/04-Mech Gallery- Finish Dry-Wall | 04-Mar-2025 | 06-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | Continental - TBD | #D6F2FF | Y2 | CHI11-03-04-215 | MATCHING | C03/04-Mech Gallery- Paint Dry-Wall | 07-Mar-2025 | 08-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | Anning Johnson | #2490FF | D5 | CHI11-03-04-205 | MATCHING | C03/04-Mech Gallery- Install Ceiling Grid + Device Tiles | 17-Mar-2025 | 20-Mar-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | Plumbing | #1F595B | P2 | CHI11-03-04-165 | MATCHING | C03/04-Mech Gallery- Overhead R/I - Plumbing | 21-Mar-2025 | 10-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | Hill Mechanical | #C9DF56 | M4 | CHI11-03-04-255 | MATCHING | C03/04-Mech Gallery- Set Mechanical Equipments | 03-Apr-2025 | 05-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE13 | CHI11-03-04-250 | MATCHING | C03/04-Mech Gallery- Install BAS Equipments | 03-Apr-2025 | 08-Apr-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | Cleaning | #FFC6FF | C1 | CHI11-03-04-235 | MATCHING | C03/04-Mech Gallery- General Cleaning | 04-Apr-2025 | 05-Apr-2025
Fitout | COLO 4 | COLO 4 CELL 1 TELECOM | GIBSON | #FFF9B1 | EE56 | CHI11-04-01-TEL-371 | MATCHING | C04 - CEI Cabinet | 30-Apr-2025 | 30-Apr-2025
FITOUT | COLO 4 | CELL 1 TELECOM | CECCO | #EF9E5B | T4 | CHI11-04-01-TEL-400 | MATCHING | C04/01 - Backbone Fiber | 11-Jun-2025 | 18-Jun-2025
FITOUT | COLO 4 | CELL 1 TELECOM | CECCO | #EF9E5B | T6 | CHI11-04-01-TEL-450 | MATCHING | C04/01 - Production Fiber (Plug/TEST) | 19-Jul-2025 | 02-Aug-2025
Fitout | COLO 4 | COLO 4 CELL 1 TELECOM CEI Fiber Backbone | GIBSON | #FFF9B1 | EE57 | CHI11-04-01-TEL-46 | MATCHING | C04 - Pull EPMS Fiber Blue Route | 16-May-2025 | 19-May-2025
Fitout | COLO 4 | COLO 4 CELL 1 TELECOM CEI Fiber Backbone | GIBSON | #FFF9B1 | EE58 | CHI11-04-01-TEL-47 | MATCHING | C04 - Pull EPMS Fiber RED Route | 20-May-2025 | 22-May-2025
Fitout | COLO 4 | COLO 4 CELL 1 TELECOM CEI Fiber Backbone | GIBSON | #FFF9B1 | EE59 | CHI11-04-01-TEL-48 | MATCHING | C04 - Port Fiber Blue Route | 23-May-2025 | 27-May-2025
Fitout | COLO 4 | COLO 4 CELL 1 TELECOM CEI Fiber Backbone | GIBSON | #FFF9B1 | EE60 | CHI11-04-01-TEL-49 | MATCHING | C04 - Test EPMS Fiber Blue Route | 28-May-2025 | 29-May-2025
Fitout | COLO 4 | COLO 4 CELL 1 TELECOM CEI Fiber Backbone | GIBSON | #FFF9B1 | EE61 | CHI11-04-01-TEL-51 | MATCHING | C04 - Port Fiber Red Route | 30-May-2025 | 30-May-2025
Fitout | COLO 4 | COLO 4 CELL 1 TELECOM CEI Fiber Backbone | GIBSON | #FFF9B1 | EE62 | CHI11-04-01-TEL-52 | MATCHING | C04 - Test EPMS Fiber RED Route | 31-May-2025 | 31-May-2025
FITOUT | COLO 4 | CELL 1 TELECOM | CECCO | #EF9E5B | T1 | CHI11-04-01-TEL-370 | MATCHING | C04/01 - Pull EPMS Copper | 12-May-2025 | 15-May-2025
Fitout | COLO 4 | COLO 4 CELL 1 TELECOM EPMS | CECCO | #EF9E5B | T16 | CHI11-04-01-TEL-53 | MATCHING | C04/01 - Terminate EPMS Copper | 16-May-2025 | 22-May-2025
Fitout | COLO 4 | COLO 4 CELL 1 TELECOM EPMS | CECCO | #EF9E5B | T17 | CHI11-04-01-TEL-54 | MATCHING | C04/01 - Test EPMS Copper | 23-May-2025 | 27-May-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | Anning Johnson | #2490FF | D10 | CHI11-04-01-10 | MATCHING | C04/01-DH- Layout Framing | 18-Feb-2025 | 19-Feb-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | Anning Johnson | #2490FF | D7 | CHI11-04-01-15 | MATCHING | C04/01-DH- IInstall Framing | 19-Feb-2025 | 21-Feb-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | MEP | #FF7BFF | MEP2 | CHI11-04-01-20 | MATCHING | C04/01-DH- In-Wall R/I | 21-Feb-2025 | 03-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | Imperial/Span | #E0D0D0 | X7 | CHI11-04-01-145 | MATCHING | C04/01-DH- Install Secondary Steel | 24-Feb-2025 | 27-Feb-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | Shambaugh | #D76672 | R2 | CHI11-04-01-35 | MATCHING | C04/01-DH- Overhead R/I - Fire Protection | 28-Feb-2025 | 13-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | Anning Johnson | #2490FF | D16 | CHI11-04-01-40 | MATCHING | C04/01-DH- Install Drywall (Drywall Tops) | 06-Mar-2025 | 08-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE51 | CHI11-04-01-55 | MATCHING | C04/01-DH- Overhead R/I - Fire Alarm | 08-Mar-2025 | 11-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE28 | CHI11-04-01-60 | MATCHING | C04/01-DH- Overhead R/I - Electrical | 08-Mar-2025 | 12-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | Anning Johnson | #2490FF | D14 | CHI11-04-01-65 | MATCHING | C04/01-DH- Finish Dry-Wall | 10-Mar-2025 | 12-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | Continental - TBD | #D6F2FF | Y2 | CHI11-04-01-115 | MATCHING | C04/01-DH- Paint Dry-Wall | 13-Mar-2025 | 13-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | Continental - TBD | #D6F2FF | Y3 | CHI11-04-01-150 | MATCHING | C04/01-DH- Paint Secondary Steel | 14-Mar-2025 | 15-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | Anning Johnson | #2490FF | D8 | CHI11-04-01-135 | MATCHING | C04/01-DH- Install Screen Mesh + Caulking | 15-Mar-2025 | 17-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | Anning Johnson | #2490FF | D4 | CHI11-04-01-165 | MATCHING | C04/01-DH- Install Ceiling Grid | 18-Mar-2025 | 20-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE10 | CHI11-04-01-90 | MATCHING | C04/01-DH- Drop Cable Tray [Hanging Rods] | 21-Mar-2025 | 24-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | Anning Johnson | #2490FF | D21 | CHI11-04-01-215 | MATCHING | C04/01-DH- Install Device Tiles | 21-Mar-2025 | 24-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | Cleaning | #FFC6FF | C1 | CHI11-04-01-160 | MATCHING | C04/01-DH- General Cleaning | 04-Apr-2025 | 04-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE1 | CHI11-04-01-180 | MATCHING | C04/01-DH- Assemble HACs [Qty - 5] | 04-Apr-2025 | 11-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE20 | CHI11-04-01-175 | MATCHING | C04/01-DH- Install Perimeter Cable Trays | 11-Apr-2025 | 16-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE14 | CHI11-04-01-205 | MATCHING | C04/01-DH- Install Busways on HAC Arms | 18-Apr-2025 | 23-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE42 | CHI11-04-01-255 | MATCHING | C04/01-DH- Raise HACs | 24-Apr-2025 | 28-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE9 | CHI11-04-01-265 | MATCHING | C04/01-DH- Detail HACs | 24-Apr-2025 | 28-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE8 | CHI11-04-01-270 | MATCHING | C04/01-DH- Connect Perimeter Cable Trays to HAC Cable Trays | 30-Apr-2025 | 02-May-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE45 | CHI11-04-01-225 | MATCHING | C04/01-DH- Set PDUs | 02-May-2025 | 02-May-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE16 | CHI11-04-01-280 | MATCHING | C04/01-DH- Install Conduits PDU to Cable Trays | 09-May-2025 | 14-May-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE39 | CHI11-04-01-300 | MATCHING | C04/01-DH- Pull Feeders from PDUs to Busways | 03-Jun-2025 | 17-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE50 | CHI11-04-01-310 | MATCHING | C04/01-DH- Terminate PDUs | 18-Jun-2025 | 28-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | Anning Johnson | #2490FF | D7 | CHI11-04-01-25 | MATCHING | C04/01-Elec Rm- Install Framing | 24-Feb-2025 | 06-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | Shambaugh | #D76672 | R2 | CHI11-04-01-45 | MATCHING | C04/01-Elec Rm- Overhead R/I - Fire Protection | 25-Feb-2025 | 26-Feb-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE28 | CHI11-04-01-75 | MATCHING | C04/01-Elec Rm- Overhead R/I - Electrical | 25-Feb-2025 | 27-Feb-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | Imperial/Span | #E0D0D0 | X7 | CHI11-04-01-850 | MATCHING | C04/01-Elec Rm- Secondary Steel | 25-Feb-2025 | 27-Feb-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE51 | CHI11-04-01-70 | MATCHING | C04/01-Elec Rm- Overhead R/I - Fire Alarm | 27-Feb-2025 | 14-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | MEP | #FF7BFF | MEP2 | CHI11-04-01-30 | MATCHING | C04/01-Elec Rm- In-Wall R/I | 07-Mar-2025 | 08-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | Anning Johnson | #2490FF | D17 | CHI11-04-01-50 | MATCHING | C04/01-Elec Rm- Install Drywall [Elec + Battery Rooms] | 10-Mar-2025 | 12-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | Anning Johnson | #2490FF | D14 | CHI11-04-01-95 | MATCHING | C04/01-Elec Rm- Finish Dry-Wall | 13-Mar-2025 | 14-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | Continental - TBD | #D6F2FF | Y2 | CHI11-04-01-125 | MATCHING | C04/01-Elec Rm- Paint Dry-Wall | 15-Mar-2025 | 17-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | Hill Mechanical | #C9DF56 | M3 | CHI11-04-01-85 | MATCHING | C04/01-Elec Rm- Overhead R/I - Mechanical | 21-Mar-2025 | 29-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE10 | CHI11-04-01-100 | MATCHING | C04/01-Elec Rm- Drop Cable Tray [Hanging Rods] | 24-Mar-2025 | 24-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE43 | CHI11-04-01-195 | MATCHING | C04/01-Elec Rm- Set Electrical Equipments | 03-Apr-2025 | 07-May-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | Cleaning | #FFC6FF | C1 | CHI11-04-01-140 | MATCHING | C04/01-Elec Rm- General Cleaning | 04-Apr-2025 | 04-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE15 | CHI11-04-01-120 | MATCHING | C04/01-Elec Rm- Install Cable Trays / Pathways/Cable Bus | 05-May-2025 | 08-May-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE38 | CHI11-04-01-290 | MATCHING | C04/01-Elec Rm- Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 03-Jun-2025 | 10-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE33 | CHI11-04-01-235 | MATCHING | C04/01-Elec Rm- Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 11-Jun-2025 | 13-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | Anning Johnson | #2490FF | D18 | CHI11-04-01-170 | MATCHING | C04/01-Mech Gallery- Install Drywall [Mech Gallery] | 04-Mar-2025 | 06-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | Shambaugh | #D76672 | R2 | CHI11-04-01-80 | MATCHING | C04/01-Mech Gallery- Overhead R/I - Fire Protection | 06-Mar-2025 | 10-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | Anning Johnson | #2490FF | D14 | CHI11-04-01-185 | MATCHING | C04/01-Mech Gallery- Finish Dry-Wall | 07-Mar-2025 | 10-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE51 | CHI11-04-01-105 | MATCHING | C04/01-Mech Gallery- Overhead R/I - Fire Alarm | 11-Mar-2025 | 12-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE28 | CHI11-04-01-110 | MATCHING | C04/01-Mech Gallery- Overhead R/I - Electrical | 11-Mar-2025 | 13-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | Hill Mechanical | #C9DF56 | M3 | CHI11-04-01-130 | MATCHING | C04/01-Mech Gallery- Overhead R/I - Mechanical | 14-Mar-2025 | 08-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | Continental - TBD | #D6F2FF | Y2 | CHI11-04-01-210 | MATCHING | C04/01-Mech Gallery- Paint Dry-Wall | 28-Mar-2025 | 29-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | Anning Johnson | #2490FF | D5 | CHI11-04-01-200 | MATCHING | C04/01-Mech Gallery- Install Ceiling Grid + Device Tiles | 29-Mar-2025 | 03-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | Plumbing | #1F595B | P2 | CHI11-04-01-155 | MATCHING | C04/01-Mech Gallery- Overhead R/I - Plumbing | 01-Apr-2025 | 10-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | Cleaning | #FFC6FF | C1 | CHI11-04-01-230 | MATCHING | C04/01-Mech Gallery- General Cleaning | 04-Apr-2025 | 07-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE13 | CHI11-04-01-245 | MATCHING | C04/01-Mech Gallery- Install BAS Equipments | 04-Apr-2025 | 16-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | Hill Mechanical | #C9DF56 | M4 | CHI11-04-01-250 | MATCHING | C04/01-Mech Gallery- Set Mechanical Equipments | 08-Apr-2025 | 10-Apr-2025
FITOUT | COLO 4 | CELL 2 TELECOM | CECCO | #EF9E5B | T4 | CHI11-04-02-TEL-510 | MATCHING | C04/02 - Backbone Fiber | 19-Jun-2025 | 25-Jun-2025
FITOUT | COLO 4 | CELL 2 TELECOM | CECCO | #EF9E5B | T6 | CHI11-04-02-TEL-540 | MATCHING | C04/02 - Production Fiber (Plug/TEST) | 19-Jul-2025 | 02-Aug-2025
FITOUT | COLO 4 | CELL 2 TELECOM | CECCO | #EF9E5B | T1 | CHI11-04-02-TEL-520 | MATCHING | C04/02 - Pull EPMS Copper | 16-May-2025 | 20-May-2025
Fitout | COLO 4 | COLO 4 CELL 2 TELECOM EPMS | CECCO | #EF9E5B | T16 | CHI11-04-02-TEL-521 | MATCHING | C04/02 - Terminate EPMS Copper | 21-May-2025 | 28-May-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | Anning Johnson | #2490FF | D10 | CHI11-04-02-10 | MATCHING | C04/02-DH- Layout Framing | 18-Feb-2025 | 19-Feb-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | Anning Johnson | #2490FF | D7 | CHI11-04-02-15 | MATCHING | C04/02-DH- Install Framing | 20-Feb-2025 | 21-Feb-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | MEP | #FF7BFF | MEP2 | CHI11-04-02-20 | MATCHING | C04/02-DH- In-Wall R/I | 21-Feb-2025 | 03-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | Imperial/Span | #E0D0D0 | X7 | CHI11-04-02-150 | MATCHING | C04/02-DH- Install Secondary Steel | 22-Feb-2025 | 27-Feb-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | Shambaugh | #D76672 | R2 | CHI11-04-02-35 | MATCHING | C04/02-DH- Overhead R/I - Fire Protection | 28-Feb-2025 | 07-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | Anning Johnson | #2490FF | D23 | CHI11-04-02-40 | MATCHING | C04/02-DH- Install Drywall (Drywall Tops) | 06-Mar-2025 | 08-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE51 | CHI11-04-02-55 | MATCHING | C04/02-DH- Overhead R/I - Fire Alarm | 08-Mar-2025 | 17-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE28 | CHI11-04-02-60 | MATCHING | C04/02-DH- Overhead R/I - Electrical | 08-Mar-2025 | 11-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | Anning Johnson | #2490FF | D20 | CHI11-04-02-65 | MATCHING | C04/02-DH- Finish Dry-Wall & Taping Bottoms | 10-Mar-2025 | 11-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | Continental - TBD | #D6F2FF | Y2 | CHI11-04-02-115 | MATCHING | C04/02-DH- Paint Dry-Wall | 12-Mar-2025 | 12-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | Continental - TBD | #D6F2FF | Y3 | CHI11-04-02-155 | MATCHING | C04/02-DH- Paint Secondary Steel | 13-Mar-2025 | 15-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | Anning Johnson | #2490FF | D8 | CHI11-04-02-135 | MATCHING | C04/02-DH- Install Screen Mesh + Caulking | 17-Mar-2025 | 18-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | Anning Johnson | #2490FF | D4 | CHI11-04-02-170 | MATCHING | C04/02-DH- Install Ceiling Grid | 19-Mar-2025 | 20-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE10 | CHI11-04-02-90 | MATCHING | C04/02-DH- Drop Cable Tray [Hanging Rods] | 21-Mar-2025 | 24-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | Anning Johnson | #2490FF | D21 | CHI11-04-02-215 | MATCHING | C04/02-DH- Install Device Tiles | 21-Mar-2025 | 24-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | Cleaning | #FFC6FF | C1 | CHI11-04-02-165 | MATCHING | C04/02-DH- General Cleaning | 04-Apr-2025 | 04-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE20 | CHI11-04-02-180 | MATCHING | C04/02-DH- Install Perimeter Cable Trays | 11-Apr-2025 | 09-May-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE1 | CHI11-04-02-185 | MATCHING | C04/02-DH- Assemble HACs [Qty - 5] | 11-Apr-2025 | 17-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE14 | CHI11-04-02-205 | MATCHING | C04/02-DH- Install Busways on HAC Arms | 30-Apr-2025 | 02-May-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE45 | CHI11-04-02-225 | MATCHING | C04/02-DH- Set PDUs | 02-May-2025 | 02-May-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE42 | CHI11-04-02-250 | MATCHING | C04/02-DH- Raise HACs | 03-May-2025 | 08-May-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE9 | CHI11-04-02-260 | MATCHING | C04/02-DH- Detail HACs | 03-May-2025 | 08-May-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE8 | CHI11-04-02-265 | MATCHING | C04/02-DH- Connect Perimeter Cable Trays to HAC Cable Trays | 12-May-2025 | 14-May-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE16 | CHI11-04-02-275 | MATCHING | C04/02-DH- Install Conduits PDU to Cable Trays | 16-May-2025 | 20-May-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE39 | CHI11-04-02-285 | MATCHING | C04/02-DH- Pull Feeders from PDUs to Busways | 09-Jun-2025 | 20-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE50 | CHI11-04-02-310 | MATCHING | C04/02-DH- Terminate PDUs | 21-Jun-2025 | 28-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | Anning Johnson | #2490FF | D7 | CHI11-04-02-25 | MATCHING | C04/02-Elec Rm- Install Framing | 24-Feb-2025 | 06-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | Shambaugh | #D76672 | R2 | CHI11-04-02-45 | MATCHING | C04/02-Elec Rm- Overhead R/I - Fire Protection | 25-Feb-2025 | 26-Feb-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE51 | CHI11-04-02-70 | MATCHING | C04/02-Elec Rm- Overhead R/I - Fire Alarm | 25-Feb-2025 | 26-Feb-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE28 | CHI11-04-02-75 | MATCHING | C04/02-Elec Rm- Overhead R/I - Electrical | 25-Feb-2025 | 26-Feb-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | Imperial/Span | #E0D0D0 | X7 | CHI11-04-02-850 | MATCHING | C04/02-Elec Rm- Secondary Steel | 28-Feb-2025 | 06-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | MEP | #FF7BFF | MEP2 | CHI11-04-02-30 | MATCHING | C04/02-Elec Rm- In-Wall R/I | 03-Mar-2025 | 05-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | Anning Johnson | #2490FF | D17 | CHI11-04-02-50 | MATCHING | C04/02-Elec Rm- Install Drywall [Elec + Battery Rooms] | 05-Mar-2025 | 08-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | Anning Johnson | #2490FF | D14 | CHI11-04-02-95 | MATCHING | C04/02-Elec Rm- Finish Dry-Wall | 10-Mar-2025 | 11-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | Continental - TBD | #D6F2FF | Y2 | CHI11-04-02-125 | MATCHING | C04/02-Elec Rm- Paint Dry-Wall | 12-Mar-2025 | 13-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | Hill Mechanical | #C9DF56 | M3 | CHI11-04-02-85 | MATCHING | C04/02-Elec Rm- Overhead R/I - Mechanical | 14-Mar-2025 | 31-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE10 | CHI11-04-02-100 | MATCHING | C04/02-Elec Rm- Drop Cable Tray [Hanging Rods] | 17-Mar-2025 | 18-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | Cleaning | #FFC6FF | C1 | CHI11-04-02-140 | MATCHING | C04/02-Elec Rm- General Cleaning | 02-Apr-2025 | 02-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE43 | CHI11-04-02-145 | MATCHING | C04/02-Elec Rm- Set Electrical Equipments | 30-Apr-2025 | 07-May-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE15 | CHI11-04-02-120 | MATCHING | C04/02-Elec Rm- Install Cable Trays / Pathways/Cable Bus | 01-May-2025 | 10-May-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE38 | CHI11-04-02-305 | MATCHING | C04/02-Elec Rm- Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 09-Jun-2025 | 17-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE33 | CHI11-04-02-290 | MATCHING | C04/02-Elec Rm- Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 16-Jun-2025 | 20-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | Shambaugh | #D76672 | R2 | CHI11-04-02-80 | MATCHING | C04/02-Mech Gallery- Overhead R/I - Fire Protection | 03-Mar-2025 | 18-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE51 | CHI11-04-02-105 | MATCHING | C04/02-Mech Gallery- Overhead R/I - Fire Alarm | 03-Mar-2025 | 18-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE28 | CHI11-04-02-110 | MATCHING | C04/02-Mech Gallery- Overhead R/I - Electrical | 03-Mar-2025 | 18-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | Anning Johnson | #2490FF | D18 | CHI11-04-02-175 | MATCHING | C04/02-Mech Gallery- Install Drywall [Mech Gallery] | 04-Mar-2025 | 06-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | Anning Johnson | #2490FF | D14 | CHI11-04-02-190 | MATCHING | C04/02-Mech Gallery- Finish Dry-Wall | 07-Mar-2025 | 08-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | Hill Mechanical | #C9DF56 | M3 | CHI11-04-02-130 | MATCHING | C04/02-Mech Gallery- Overhead R/I - Mechanical | 10-Mar-2025 | 08-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | Plumbing | #1F595B | P2 | CHI11-04-02-160 | MATCHING | C04/02-Mech Gallery- Overhead R/I - Plumbing | 10-Mar-2025 | 10-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | Continental - TBD | #D6F2FF | Y2 | CHI11-04-02-210 | MATCHING | C04/02-Mech Gallery- Paint Dry-Wall | 28-Mar-2025 | 29-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | Anning Johnson | #2490FF | D5 | CHI11-04-02-200 | MATCHING | C04/02-Mech Gallery- Install Ceiling Grid + Device Tiles | 31-Mar-2025 | 03-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | Cleaning | #FFC6FF | C1 | CHI11-04-02-230 | MATCHING | C04/02-Mech Gallery- General Cleaning | 04-Apr-2025 | 07-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE13 | CHI11-04-02-240 | MATCHING | C04/02-Mech Gallery- Install BAS Equipments | 04-Apr-2025 | 15-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | Hill Mechanical | #C9DF56 | M4 | CHI11-04-02-245 | MATCHING | C04/02-Mech Gallery- Set Mechanical Equipments | 15-Apr-2025 | 17-Apr-2025
FITOUT | COLO 4 | CELL 3 TELECOM | CECCO | #EF9E5B | T4 | CHI11-04-03-TEL-620 | MATCHING | C04/03 - Backbone Fiber | 26-Jun-2025 | 02-Jul-2025
FITOUT | COLO 4 | CELL 3 TELECOM | CECCO | #EF9E5B | T6 | CHI11-04-03-TEL-600 | MATCHING | C04/03 - Production Fiber (Plug/TEST) | 19-Jul-2025 | 02-Aug-2025
FITOUT | COLO 4 | CELL 3 TELECOM | CECCO | #EF9E5B | T1 | CHI11-04-03-TEL-610 | MATCHING | C04/03 - Pull EPMS Copper | 21-May-2025 | 27-May-2025
Fitout | COLO 4 | COLO 4 CELL 3 TELECOM EPMS | CECCO | #EF9E5B | T18 | CHI11-04-03-TEL-65 | MATCHING | C04/03 - Install Switch/Patch | 13-Jun-2025 | 19-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | Anning Johnson | #2490FF | D10 | CHI11-04-03-10 | MATCHING | C04/03-DH- Layout Framing | 28-Feb-2025 | 03-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | Anning Johnson | #2490FF | D7 | CHI11-04-03-15 | MATCHING | C04/03-DH- Install Framing | 04-Mar-2025 | 06-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | MEP | #FF7BFF | MEP2 | CHI11-04-03-20 | MATCHING | C04/03-DH- In-Wall R/I | 07-Mar-2025 | 10-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | Shambaugh | #D76672 | R2 | CHI11-04-03-35 | MATCHING | C04/03-DH- Overhead R/I - Fire Protection | 10-Mar-2025 | 17-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE51 | CHI11-04-03-55 | MATCHING | C04/03-DH- Overhead R/I - Fire Alarm | 10-Mar-2025 | 17-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE28 | CHI11-04-03-60 | MATCHING | C04/03-DH- Overhead R/I - Electrical | 10-Mar-2025 | 18-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | Anning Johnson | #2490FF | D16 | CHI11-04-03-40 | MATCHING | C04/03-DH- Install Drywall (One Side - Facing DH) | 11-Mar-2025 | 12-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | Anning Johnson | #2490FF | D14 | CHI11-04-03-65 | MATCHING | C04/03-DH- Finish Dry-Wall | 13-Mar-2025 | 14-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | Imperial/Span | #E0D0D0 | X7 | CHI11-04-03-150 | MATCHING | C04/03-DH- Install Secondary Steel | 15-Mar-2025 | 17-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | Continental - TBD | #D6F2FF | Y3 | CHI11-04-03-155 | MATCHING | C04/03-DH- Paint Secondary Steel | 18-Mar-2025 | 18-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | Anning Johnson | #2490FF | D8 | CHI11-04-03-135 | MATCHING | C04/03-DH- Install Screen Mesh + Caulking | 21-Mar-2025 | 25-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | Anning Johnson | #2490FF | D4 | CHI11-04-03-170 | MATCHING | C04/03-DH- Install Ceiling Grid | 26-Mar-2025 | 27-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | Anning Johnson | #2490FF | D21 | CHI11-04-03-215 | MATCHING | C04/03-DH- Install Device Tiles | 26-Mar-2025 | 27-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | Continental - TBD | #D6F2FF | Y2 | CHI11-04-03-115 | MATCHING | C04/03-DH- Paint Dry-Wall | 28-Mar-2025 | 31-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE10 | CHI11-04-03-90 | MATCHING | C04/03-DH- Drop Cable Tray [Hanging Rods] | 11-Apr-2025 | 14-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | Cleaning | #FFC6FF | C1 | CHI11-04-03-165 | MATCHING | C04/03-DH- General Cleaning | 15-Apr-2025 | 15-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE1 | CHI11-04-03-185 | MATCHING | C04/03-DH- Assemble HACs [Qty - 5] | 16-Apr-2025 | 21-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE20 | CHI11-04-03-180 | MATCHING | C04/03-DH- Install Perimeter Cable Trays | 18-Apr-2025 | 16-May-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE14 | CHI11-04-03-205 | MATCHING | C04/03-DH- Install Busways on HAC Arms | 22-Apr-2025 | 02-May-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE45 | CHI11-04-03-225 | MATCHING | C04/03-DH- Set PDUs | 02-May-2025 | 02-May-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE42 | CHI11-04-03-250 | MATCHING | C04/03-DH- Raise HACs | 03-May-2025 | 08-May-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE9 | CHI11-04-03-260 | MATCHING | C04/03-DH- Detail HACs | 03-May-2025 | 08-May-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | Shambaugh | #D76672 | R2 | CHI11-04-03-45 | MATCHING | C04/03-Elec Rm- Overhead R/I - Fire Protection | 10-Mar-2025 | 14-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE51 | CHI11-04-03-70 | MATCHING | C04/03-Elec Rm- Overhead R/I - Fire Alarm | 10-Mar-2025 | 14-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE28 | CHI11-04-03-75 | MATCHING | C04/03-Elec Rm- Overhead R/I - Electrical | 10-Mar-2025 | 14-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | Imperial/Span | #E0D0D0 | X7 | CHI11-04-03-850 | MATCHING | C04/03-Elec Rm- Secondary Steel | 15-Mar-2025 | 18-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | Anning Johnson | #2490FF | D7 | CHI11-04-03-25 | MATCHING | C04/03-Elec Rm- Install Framing | 19-Mar-2025 | 20-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | MEP | #FF7BFF | MEP2 | CHI11-04-03-30 | MATCHING | C04/03-Elec Rm- In-Wall R/I | 21-Mar-2025 | 24-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | Anning Johnson | #2490FF | D17 | CHI11-04-03-50 | MATCHING | C04/03-Elec Rm- Install Drywall [Elec + Battery Rooms] | 26-Mar-2025 | 27-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | Anning Johnson | #2490FF | D14 | CHI11-04-03-95 | MATCHING | C04/03-Elec Rm- Finish Dry-Wall | 26-Mar-2025 | 27-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | Continental - TBD | #D6F2FF | Y2 | CHI11-04-03-125 | MATCHING | C04/03-Elec Rm- Paint Dry-Wall | 28-Mar-2025 | 29-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | Hill Mechanical | #C9DF56 | M3 | CHI11-04-03-85 | MATCHING | C04/03-Elec Rm- Overhead R/I - Mechanical | 31-Mar-2025 | 02-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE10 | CHI11-04-03-100 | MATCHING | C04/03-Elec Rm- Drop Cable Tray [Hanging Rods] | 01-Apr-2025 | 03-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | Cleaning | #FFC6FF | C1 | CHI11-04-03-140 | MATCHING | C04/03-Elec Rm- General Cleaning | 05-May-2025 | 05-May-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE15 | CHI11-04-03-120 | MATCHING | C04/03-Elec Rm- Install Cable Trays / Pathways/Cable Bus | 05-May-2025 | 10-May-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE43 | CHI11-04-03-145 | MATCHING | C04/03-Elec Rm- Set Electrical Equipments | 05-May-2025 | 08-May-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE33 | CHI11-04-03-295 | MATCHING | C04/03-Elec Rm- Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 16-Jun-2025 | 27-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | Shambaugh | #D76672 | R2 | CHI11-04-03-80 | MATCHING | C04/03-Mech Gallery- - Overhead R/I - Fire Protection | 31-Mar-2025 | 01-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE51 | CHI11-04-03-105 | MATCHING | C04/03-Mech Gallery- - Overhead R/I - Fire Alarm | 31-Mar-2025 | 01-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE28 | CHI11-04-03-110 | MATCHING | C04/03-Mech Gallery- - Overhead R/I - Electrical | 31-Mar-2025 | 02-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | Hill Mechanical | #C9DF56 | M3 | CHI11-04-03-130 | MATCHING | C04/03-Mech Gallery- - Overhead R/I - Mechanical | 03-Apr-2025 | 08-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | Plumbing | #1F595B | P2 | CHI11-04-03-160 | MATCHING | C04/03-Mech Gallery- - Overhead R/I - Plumbing | 05-Apr-2025 | 10-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | Anning Johnson | #2490FF | D18 | CHI11-04-03-175 | MATCHING | C04/03-Mech Gallery- - Install Drywall [Mech Gallery] | 08-Apr-2025 | 10-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | Anning Johnson | #2490FF | D14 | CHI11-04-03-190 | MATCHING | C04/03-Mech Gallery- - Finish Dry-Wall | 08-Apr-2025 | 10-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | Anning Johnson | #2490FF | D5 | CHI11-04-03-200 | MATCHING | C04/03-Mech Gallery- - Install Ceiling Grid + Device Tiles | 08-Apr-2025 | 08-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | Hill Mechanical | #C9DF56 | M4 | CHI11-04-03-245 | MATCHING | C04/03-Mech Gallery- - Set Mechanical Equipments | 09-Apr-2025 | 10-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | Continental - TBD | #D6F2FF | Y2 | CHI11-04-03-210 | MATCHING | C04/03-Mech Gallery- - Paint Dry-Wall | 11-Apr-2025 | 14-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE13 | CHI11-04-03-240 | MATCHING | C04/03-Mech Gallery- - Install BAS Equipments | 11-Apr-2025 | 17-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | Cleaning | #FFC6FF | C1 | CHI11-04-03-230 | MATCHING | C04/03-Mech Gallery- - General Cleaning | 15-Apr-2025 | 17-Apr-2025
FITOUT | COLO 4 | CELL 4 TELECOM | CECCO | #EF9E5B | T4 | CHI11-04-04-TEL-690 | MATCHING | C04/04 - Backbone Fiber | 03-Jul-2025 | 11-Jul-2025
FITOUT | COLO 4 | CELL 4 TELECOM | CECCO | #EF9E5B | T6 | CHI11-04-04-TEL-710 | MATCHING | C04/04 - Production Fiber (Plug/TEST) | 19-Jul-2025 | 02-Aug-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | Anning Johnson | #2490FF | D10 | CHI11-04-04-10 | MATCHING | C04/04-DH-Layout Framing | 01-Mar-2025 | 03-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | Anning Johnson | #2490FF | D7 | CHI11-04-04-15 | MATCHING | C04/04-DH-Install Framing | 04-Mar-2025 | 06-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | MEP | #FF7BFF | MEP2 | CHI11-04-04-20 | MATCHING | C04/04-DH-In-Wall R/I | 11-Mar-2025 | 13-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | Shambaugh | #D76672 | R2 | CHI11-04-04-35 | MATCHING | C04/04-DH-Overhead R/I - Fire Protection | 14-Mar-2025 | 18-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | Anning Johnson | #2490FF | D16 | CHI11-04-04-40 | MATCHING | C04/04-DH-Install Drywall (Drywall Tops) | 14-Mar-2025 | 17-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE51 | CHI11-04-04-55 | MATCHING | C04/04-DH-Overhead R/I - Fire Alarm | 15-Mar-2025 | 17-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | Anning Johnson | #2490FF | D14 | CHI11-04-04-65 | MATCHING | C04/04-DH-Finish Dry-Wall | 15-Mar-2025 | 17-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE28 | CHI11-04-04-60 | MATCHING | C04/04-DH-Overhead R/I - Electrical | 18-Mar-2025 | 20-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | Imperial/Span | #E0D0D0 | X7 | CHI11-04-04-150 | MATCHING | C04/04-DH-Install Secondary Steel | 18-Mar-2025 | 20-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | Continental - TBD | #D6F2FF | Y2 | CHI11-04-04-115 | MATCHING | C04/04-DH-Paint Dry-Wall | 21-Mar-2025 | 21-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | Continental - TBD | #D6F2FF | Y3 | CHI11-04-04-155 | MATCHING | C04/04-DH-Paint Secondary Steel | 21-Mar-2025 | 21-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | Anning Johnson | #2490FF | D8 | CHI11-04-04-135 | MATCHING | C04/04-DH-Install Screen Mesh + Caulking | 22-Mar-2025 | 25-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | Anning Johnson | #2490FF | D4 | CHI11-04-04-170 | MATCHING | C04/04-DH-Install Ceiling Grid | 28-Mar-2025 | 01-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | Anning Johnson | #2490FF | D21 | CHI11-04-04-215 | MATCHING | C04/04-DH-Install Device Tiles | 28-Mar-2025 | 01-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE10 | CHI11-04-04-90 | MATCHING | C04/04-DH-Drop Cable Tray [Hanging Rods] | 11-Apr-2025 | 14-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | Cleaning | #FFC6FF | C1 | CHI11-04-04-165 | MATCHING | C04/04-DH-General Cleaning | 18-Apr-2025 | 18-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE1 | CHI11-04-04-185 | MATCHING | C04/04-DH-Assemble HACs [Qty - 5] | 22-Apr-2025 | 26-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE14 | CHI11-04-04-205 | MATCHING | C04/04-DH-Install Busways on HAC Arms | 28-Apr-2025 | 09-May-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE45 | CHI11-04-04-225 | MATCHING | C04/04-DH-Set PDUs | 02-May-2025 | 02-May-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE42 | CHI11-04-04-250 | MATCHING | C04/04-DH-Raise HACs | 12-May-2025 | 15-May-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE9 | CHI11-04-04-260 | MATCHING | C04/04-DH-Detail HACs | 12-May-2025 | 15-May-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | Shambaugh | #D76672 | R2 | CHI11-04-04-45 | MATCHING | C04/04-Elec Rm-Overhead R/I - Fire Protection | 04-Mar-2025 | 15-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE28 | CHI11-04-04-75 | MATCHING | C04/04-Elec Rm-Overhead R/I - Electrical | 04-Mar-2025 | 06-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE51 | CHI11-04-04-70 | MATCHING | C04/04-Elec Rm-Overhead R/I - Fire Alarm | 06-Mar-2025 | 15-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | Imperial/Span | #E0D0D0 | X7 | CHI11-04-04-850 | MATCHING | C04/04-Elec Rm- Secondary Steel | 08-Mar-2025 | 12-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | Anning Johnson | #2490FF | D7 | CHI11-04-04-25 | MATCHING | C04/04-Elec Rm-Install Framing | 10-Mar-2025 | 11-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | MEP | #FF7BFF | MEP2 | CHI11-04-04-30 | MATCHING | C04/04-Elec Rm-In-Wall R/I | 10-Mar-2025 | 13-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | Anning Johnson | #2490FF | D17 | CHI11-04-04-50 | MATCHING | C04/04-Elec Rm-Install Drywall [Elec + Battery Rooms] | 14-Mar-2025 | 17-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | Anning Johnson | #2490FF | D14 | CHI11-04-04-95 | MATCHING | C04/04-Elec Rm-Finish Dry-Wall | 18-Mar-2025 | 19-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | Continental - TBD | #D6F2FF | Y2 | CHI11-04-04-125 | MATCHING | C04/04-Elec Rm-Paint Dry-Wall | 20-Mar-2025 | 20-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | Hill Mechanical | #C9DF56 | M3 | CHI11-04-04-85 | MATCHING | C04/04-Elec Rm-Overhead R/I - Mechanical | 28-Mar-2025 | 31-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE10 | CHI11-04-04-100 | MATCHING | C04/04-Elec Rm-Drop Cable Tray [Hanging Rods] | 31-Mar-2025 | 31-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | Cleaning | #FFC6FF | C1 | CHI11-04-04-140 | MATCHING | C04/04-Elec Rm-General Cleaning | 05-May-2025 | 05-May-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE15 | CHI11-04-04-120 | MATCHING | C04/04-Elec Rm-Install Cable Trays / Pathways/Cable Bus | 05-May-2025 | 10-May-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE43 | CHI11-04-04-145 | MATCHING | C04/04-Elec Rm-Set Electrical Equipments | 05-May-2025 | 08-May-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE33 | CHI11-04-04-295 | MATCHING | C04/04-Elec Rm-Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 16-Jun-2025 | 27-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | Shambaugh | #D76672 | R2 | CHI11-04-04-80 | MATCHING | C04/04-Mech Gallery-Overhead R/I - Fire Protection | 27-Mar-2025 | 29-Mar-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE51 | CHI11-04-04-105 | MATCHING | C04/04-Mech Gallery-Overhead R/I - Fire Alarm | 31-Mar-2025 | 01-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE28 | CHI11-04-04-110 | MATCHING | C04/04-Mech Gallery-Overhead R/I - Electrical | 31-Mar-2025 | 02-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | Hill Mechanical | #C9DF56 | M3 | CHI11-04-04-130 | MATCHING | C04/04-Mech Gallery-Overhead R/I - Mechanical | 03-Apr-2025 | 08-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | Plumbing | #1F595B | P2 | CHI11-04-04-160 | MATCHING | C04/04-Mech Gallery-Overhead R/I - Plumbing | 05-Apr-2025 | 10-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | Anning Johnson | #2490FF | D18 | CHI11-04-04-175 | MATCHING | C04/04-Mech Gallery-Install Drywall [Mech Gallery] | 08-Apr-2025 | 10-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | Anning Johnson | #2490FF | D14 | CHI11-04-04-190 | MATCHING | C04/04-Mech Gallery-Finish Dry-Wall | 08-Apr-2025 | 10-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | Continental - TBD | #D6F2FF | Y2 | CHI11-04-04-210 | MATCHING | C04/04-Mech Gallery-Paint Dry-Wall | 11-Apr-2025 | 14-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | Anning Johnson | #2490FF | D5 | CHI11-04-04-200 | MATCHING | C04/04-Mech Gallery-Install Ceiling Grid + Device Tiles | 11-Apr-2025 | 16-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE13 | CHI11-04-04-240 | MATCHING | C04/04-Mech Gallery-Install BAS Equipments | 11-Apr-2025 | 17-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | Cleaning | #FFC6FF | C1 | CHI11-04-04-230 | MATCHING | C04/04-Mech Gallery-General Cleaning | 15-Apr-2025 | 17-Apr-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | Hill Mechanical | #C9DF56 | M4 | CHI11-04-04-245 | MATCHING | C04/04-Mech Gallery-Set Mechanical Equipments | 15-Apr-2025 | 17-Apr-2025
FITOUT | COLO 5 | CELL 1 TELECOM | CECCO | #EF9E5B | T5 | CHI11-05-01-TEL-780 | MATCHING | C05/01 - Production Fiber (PULL/DRESS) | 18-Jun-2025 | 24-Jun-2025
FITOUT | COLO 5 | CELL 1 TELECOM | CECCO | #EF9E5B | T4 | CHI11-05-01-TEL-770 | MATCHING | C05/01 - Backbone Fiber | 21-Jul-2025 | 28-Jul-2025
FITOUT | COLO 5 | CELL 1 TELECOM | CECCO | #EF9E5B | T6 | CHI11-05-01-TEL-810 | MATCHING | C05/01 - Production Fiber (Plug/TEST) | 26-Aug-2025 | 10-Sep-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | Anning Johnson | #2490FF | D10 | CHI11-05-01-10 | MATCHING | C05/01-DH- Layout Framing | 14-Mar-2025 | 15-Mar-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | Anning Johnson | #2490FF | D7 | CHI11-05-01-15 | MATCHING | C05/01-DH- Install Framing | 17-Mar-2025 | 19-Mar-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | MEP | #FF7BFF | MEP2 | CHI11-05-01-20 | MATCHING | C05/01-DH- In-Wall R/I | 20-Mar-2025 | 24-Mar-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | Shambaugh | #D76672 | R2 | CHI11-05-01-35 | MATCHING | C05/01-DH- Overhead R/I - Fire Protection | 25-Mar-2025 | 02-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | Anning Johnson | #2490FF | D16 | CHI11-05-01-40 | MATCHING | C05/01-DH- Install Drywall (One Side - Facing DH) | 31-Mar-2025 | 02-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | Anning Johnson | #2490FF | D14 | CHI11-05-01-65 | MATCHING | C05/01-DH- Finish Dry-Wall | 01-Apr-2025 | 03-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE51 | CHI11-05-01-55 | MATCHING | C05/01-DH- Overhead R/I - Fire Alarm | 03-Apr-2025 | 05-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE28 | CHI11-05-01-60 | MATCHING | C05/01-DH- Overhead R/I - Electrical | 03-Apr-2025 | 07-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | Imperial/Span | #E0D0D0 | X7 | CHI11-05-01-150 | MATCHING | C05/01-DH- Install Secondary Steel | 03-Apr-2025 | 05-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | Continental - TBD | #D6F2FF | Y2 | CHI11-05-01-115 | MATCHING | C05/01-DH- Paint Dry-Wall | 04-Apr-2025 | 07-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | Continental - TBD | #D6F2FF | Y3 | CHI11-05-01-155 | MATCHING | C05/01-DH- Paint Secondary Steel | 07-Apr-2025 | 08-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | Anning Johnson | #2490FF | D8 | CHI11-05-01-135 | MATCHING | C05/01-DH- Install Screen Mesh + Caulking | 09-Apr-2025 | 11-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | Anning Johnson | #2490FF | D4 | CHI11-05-01-170 | MATCHING | C05/01-DH- Install Ceiling Grid | 14-Apr-2025 | 17-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE10 | CHI11-05-01-90 | MATCHING | C05/01-DH- Drop Cable Tray [Hanging Rods] | 30-Apr-2025 | 10-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | Anning Johnson | #2490FF | D21 | CHI11-05-01-220 | MATCHING | C05/01-DH- Install Device Tiles | 30-Apr-2025 | 10-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | Cleaning | #FFC6FF | C1 | CHI11-05-01-165 | MATCHING | C05/01-DH- General Cleaning | 12-May-2025 | 12-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE1 | CHI11-05-01-185 | MATCHING | C05/01-DH- Assemble HACs [Qty - 5] | 13-May-2025 | 15-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE14 | CHI11-05-01-210 | MATCHING | C05/01-DH- Install Busways on HAC Arms | 15-May-2025 | 28-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE39 | CHI11-05-01-300 | MATCHING | C05/01-DH- Pull Feeders from PDUs to Busways | 07-Jul-2025 | 19-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE50 | CHI11-05-01-310 | MATCHING | C05/01-DH- Terminate PDUs | 21-Jul-2025 | 25-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | Shambaugh | #D76672 | R2 | CHI11-05-01-45 | MATCHING | C05/01-Elec Rm- Overhead R/I - Fire Protection | 27-Mar-2025 | 31-Mar-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE51 | CHI11-05-01-70 | MATCHING | C05/01-Elec Rm- Overhead R/I - Fire Alarm | 01-Apr-2025 | 02-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE28 | CHI11-05-01-75 | MATCHING | C05/01-Elec Rm- Overhead R/I - Electrical | 01-Apr-2025 | 03-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | Imperial/Span | #E0D0D0 | X7 | CHI11-05-01-850 | MATCHING | C05/01-Elec Rm- Secondary Steel | 04-Apr-2025 | 08-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | Anning Johnson | #2490FF | D7 | CHI11-05-01-25 | MATCHING | C05/01-Elec Rm- Install Framing | 05-Apr-2025 | 07-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | MEP | #FF7BFF | MEP2 | CHI11-05-01-30 | MATCHING | C05/01-Elec Rm- In-Wall R/I | 08-Apr-2025 | 10-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | Anning Johnson | #2490FF | D17 | CHI11-05-01-50 | MATCHING | C05/01-Elec Rm- Install Drywall [Elec + Battery Rooms] | 11-Apr-2025 | 19-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | Anning Johnson | #2490FF | D14 | CHI11-05-01-95 | MATCHING | C05/01-Elec Rm- Finish Dry-Wall | 16-Apr-2025 | 19-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | Continental - TBD | #D6F2FF | Y2 | CHI11-05-01-125 | MATCHING | C05/01-Elec Rm- Paint Dry-Wall | 30-Apr-2025 | 01-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | Hill Mechanical | #C9DF56 | M3 | CHI11-05-01-85 | MATCHING | C05/01-Elec Rm- Overhead R/I - Mechanical | 30-Apr-2025 | 02-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE10 | CHI11-05-01-100 | MATCHING | C05/01-Elec Rm- Drop Cable Tray [Hanging Rods] | 02-May-2025 | 02-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | Cleaning | #FFC6FF | C1 | CHI11-05-01-140 | MATCHING | C05/01-Elec Rm- General Cleaning | 09-May-2025 | 09-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE15 | CHI11-05-01-120 | MATCHING | C05/01-Elec Rm- Install Cable Trays / Pathways/Cable Bus | 12-May-2025 | 27-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE48 | CHI11-05-01-260 | MATCHING | C05/01-Elec Rm- Terminate Electrical Equipments [Inside Electrical Room] | 16-Jun-2025 | 25-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE33 | CHI11-05-01-190 | MATCHING | C05/01-Elec Rm- Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 07-Jul-2025 | 11-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE38 | CHI11-05-01-265 | MATCHING | C05/01-Elec Rm- Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 11-Jul-2025 | 19-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | Shambaugh | #D76672 | R2 | CHI11-05-01-80 | MATCHING | C05/01-Mech Gallery- Overhead R/I - Fire Protection | 07-Apr-2025 | 08-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE51 | CHI11-05-01-105 | MATCHING | C05/01-Mech Gallery- Overhead R/I - Fire Alarm | 09-Apr-2025 | 10-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE28 | CHI11-05-01-110 | MATCHING | C05/01-Mech Gallery- Overhead R/I - Electrical | 09-Apr-2025 | 11-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | Hill Mechanical | #C9DF56 | M3 | CHI11-05-01-130 | MATCHING | C05/01-Mech Gallery- Overhead R/I - Mechanical | 11-Apr-2025 | 17-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | Anning Johnson | #2490FF | D18 | CHI11-05-01-175 | MATCHING | C05/01-Mech Gallery- Install Drywall [Mech Gallery] | 23-Apr-2025 | 24-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | Anning Johnson | #2490FF | D14 | CHI11-05-01-195 | MATCHING | C05/01-Mech Gallery- Finish Dry-Wall | 25-Apr-2025 | 26-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | Continental - TBD | #D6F2FF | Y2 | CHI11-05-01-215 | MATCHING | C05/01-Mech Gallery- Paint Dry-Wall | 30-Apr-2025 | 01-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | Cleaning | #FFC6FF | C1 | CHI11-05-01-235 | MATCHING | C05/01-Mech Gallery- General Cleaning | 30-Apr-2025 | 02-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | Anning Johnson | #2490FF | D5 | CHI11-05-01-205 | MATCHING | C05/01-Mech Gallery- Install Ceiling Grid + Device Tiles | 30-Apr-2025 | 05-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | Hill Mechanical | #C9DF56 | M4 | CHI11-05-01-250 | MATCHING | C05/01-Mech Gallery- Set Mechanical Equipments | 15-May-2025 | 15-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE13 | CHI11-05-01-245 | MATCHING | C05/01-Mech Gallery- Install BAS Equipments | 16-May-2025 | 30-May-2025
FITOUT | COLO 5 | CELL 2 TELECOM | CECCO | #EF9E5B | T4 | CHI11-05-02-TEL-880 | MATCHING | C05/02 - Backbone Fiber | 29-Jul-2025 | 04-Aug-2025
FITOUT | COLO 5 | CELL 2 TELECOM | CECCO | #EF9E5B | T6 | CHI11-05-02-TEL-900 | MATCHING | C05/02 - Production Fiber (Plug/TEST) | 26-Aug-2025 | 10-Sep-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | Anning Johnson | #2490FF | D10 | CHI11-05-02-10 | MATCHING | C05/02-DH- Layout Framing | 21-Mar-2025 | 21-Mar-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | Anning Johnson | #2490FF | D7 | CHI11-05-02-15 | MATCHING | C05/02-DH- Install Framing | 24-Mar-2025 | 26-Mar-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | MEP | #FF7BFF | MEP2 | CHI11-05-02-20 | MATCHING | C05/02-DH- In-Wall R/I | 27-Mar-2025 | 29-Mar-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | Shambaugh | #D76672 | R2 | CHI11-05-02-35 | MATCHING | C05/02-DH- Overhead R/I - Fire Protection | 31-Mar-2025 | 02-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | Anning Johnson | #2490FF | D16 | CHI11-05-02-40 | MATCHING | C05/02-DH- Install Drywall (One Side - Facing DH) | 31-Mar-2025 | 02-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE51 | CHI11-05-02-55 | MATCHING | C05/02-DH- Overhead R/I - Fire Alarm | 03-Apr-2025 | 05-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE28 | CHI11-05-02-60 | MATCHING | C05/02-DH- Overhead R/I - Electrical | 03-Apr-2025 | 07-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | Anning Johnson | #2490FF | D14 | CHI11-05-02-65 | MATCHING | C05/02-DH- Finish Dry-Wall | 03-Apr-2025 | 05-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | Imperial/Span | #E0D0D0 | X7 | CHI11-05-02-150 | MATCHING | C05/02-DH- Install Secondary Steel | 03-Apr-2025 | 05-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | Continental - TBD | #D6F2FF | Y3 | CHI11-05-02-155 | MATCHING | C05/02-DH- Paint Secondary Steel | 08-Apr-2025 | 09-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | Continental - TBD | #D6F2FF | Y2 | CHI11-05-02-115 | MATCHING | C05/02-DH- Paint Dry-Wall | 11-Apr-2025 | 12-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | Anning Johnson | #2490FF | D8 | CHI11-05-02-135 | MATCHING | C05/02-DH- Install Screen Mesh + Caulking | 14-Apr-2025 | 16-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | Anning Johnson | #2490FF | D4 | CHI11-05-02-170 | MATCHING | C05/02-DH- Install Ceiling Grid | 14-Apr-2025 | 17-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE10 | CHI11-05-02-90 | MATCHING | C05/02-DH- Drop Cable Tray [Hanging Rods] | 30-Apr-2025 | 10-May-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | Anning Johnson | #2490FF | D21 | CHI11-05-02-215 | MATCHING | C05/02-DH- Install Device Tiles | 30-Apr-2025 | 10-May-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | Cleaning | #FFC6FF | C1 | CHI11-05-02-165 | MATCHING | C05/02-DH- General Cleaning | 02-May-2025 | 09-May-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE39 | CHI11-05-02-290 | MATCHING | C05/02-DH- Pull Feeders from PDUs to Busways | 07-Jul-2025 | 18-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE50 | CHI11-05-02-310 | MATCHING | C05/02-DH- Terminate PDUs | 09-Jul-2025 | 25-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | Shambaugh | #D76672 | R2 | CHI11-05-02-45 | MATCHING | C05/02-Elec Rm- Overhead R/I - Fire Protection | 26-Mar-2025 | 28-Mar-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE51 | CHI11-05-02-70 | MATCHING | C05/02-Elec Rm- Overhead R/I - Fire Alarm | 29-Mar-2025 | 31-Mar-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE28 | CHI11-05-02-75 | MATCHING | C05/02-Elec Rm- Overhead R/I - Electrical | 29-Mar-2025 | 01-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | Imperial/Span | #E0D0D0 | X7 | CHI11-05-02-850 | MATCHING | C05/02-Elec Rm- Secondary Steel | 04-Apr-2025 | 08-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | Anning Johnson | #2490FF | D7 | CHI11-05-02-25 | MATCHING | C05/02-Elec Rm- Install Framing | 09-Apr-2025 | 10-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | MEP | #FF7BFF | MEP2 | CHI11-05-02-30 | MATCHING | C05/02-Elec Rm- In-Wall R/I | 11-Apr-2025 | 15-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | Anning Johnson | #2490FF | D17 | CHI11-05-02-50 | MATCHING | C05/02-Elec Rm- Install Drywall [Elec + Battery Rooms] | 14-Apr-2025 | 22-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | Anning Johnson | #2490FF | D14 | CHI11-05-02-95 | MATCHING | C05/02-Elec Rm- Finish Dry-Wall | 16-Apr-2025 | 22-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | Continental - TBD | #D6F2FF | Y2 | CHI11-05-02-125 | MATCHING | C05/02-Elec Rm- Paint Dry-Wall | 22-Apr-2025 | 23-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | Hill Mechanical | #C9DF56 | M3 | CHI11-05-02-85 | MATCHING | C05/02-Elec Rm- Overhead R/I - Mechanical | 30-Apr-2025 | 01-May-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | Cleaning | #FFC6FF | C1 | CHI11-05-02-140 | MATCHING | C05/02-Elec Rm- General Cleaning | 09-May-2025 | 09-May-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE10 | CHI11-05-02-100 | MATCHING | C05/02-Elec Rm- Drop Cable Tray [Hanging Rods] | 09-May-2025 | 09-May-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE38 | CHI11-05-02-305 | MATCHING | C05/02-Elec Rm- Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 16-Jun-2025 | 10-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE33 | CHI11-05-02-270 | MATCHING | C05/02-Elec Rm- Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 07-Jul-2025 | 11-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | Shambaugh | #D76672 | R2 | CHI11-05-02-80 | MATCHING | C05/02-Mech Gallery- Overhead R/I - Fire Protection | 21-Apr-2025 | 22-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE51 | CHI11-05-02-105 | MATCHING | C05/02-Mech Gallery- Overhead R/I - Fire Alarm | 23-Apr-2025 | 24-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE28 | CHI11-05-02-110 | MATCHING | C05/02-Mech Gallery- Overhead R/I - Electrical | 23-Apr-2025 | 25-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | Hill Mechanical | #C9DF56 | M3 | CHI11-05-02-130 | MATCHING | C05/02-Mech Gallery- Overhead R/I - Mechanical | 23-Apr-2025 | 25-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | Anning Johnson | #2490FF | D18 | CHI11-05-02-175 | MATCHING | C05/02-Mech Gallery- Install Drywall [Mech Gallery] | 25-Apr-2025 | 26-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | Anning Johnson | #2490FF | D14 | CHI11-05-02-190 | MATCHING | C05/02-Mech Gallery- Finish Dry-Wall | 28-Apr-2025 | 29-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | Continental - TBD | #D6F2FF | Y2 | CHI11-05-02-210 | MATCHING | C05/02-Mech Gallery- Paint Dry-Wall | 30-Apr-2025 | 01-May-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | Anning Johnson | #2490FF | D5 | CHI11-05-02-200 | MATCHING | C05/02-Mech Gallery- Install Ceiling Grid + Device Tiles | 30-Apr-2025 | 05-May-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | Cleaning | #FFC6FF | C1 | CHI11-05-02-230 | MATCHING | C05/02-Mech Gallery- General Cleaning | 09-May-2025 | 12-May-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE13 | CHI11-05-02-240 | MATCHING | C05/02-Mech Gallery- Install BAS Equipments | 09-May-2025 | 30-May-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | Hill Mechanical | #C9DF56 | M4 | CHI11-05-02-245 | MATCHING | C05/02-Mech Gallery- Set Mechanical Equipments | 15-May-2025 | 15-May-2025
FITOUT | COLO 5 | CELL 3 TELECOM | CECCO | #EF9E5B | T4 | CHI11-05-03-TEL-970 | MATCHING | C05/03 - Backbone Fiber | 05-Aug-2025 | 11-Aug-2025
FITOUT | COLO 5 | CELL 3 TELECOM | CECCO | #EF9E5B | T6 | CHI11-05-03-TEL-930 | MATCHING | C05/03 - Production Fiber (Plug/TEST) | 26-Aug-2025 | 10-Sep-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | Anning Johnson | #2490FF | D10 | CHI11-05-03-10 | MATCHING | C05/03-DH- Layout Framing | 22-Apr-2025 | 22-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | Anning Johnson | #2490FF | D7 | CHI11-05-03-15 | MATCHING | C05/03-DH- Install Framing | 23-Apr-2025 | 24-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | MEP | #FF7BFF | MEP2 | CHI11-05-03-20 | MATCHING | C05/03-DH- In-Wall R/I | 24-Apr-2025 | 25-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | Shambaugh | #D76672 | R2 | CHI11-05-03-35 | MATCHING | C05/03-DH- Overhead R/I - Fire Protection | 24-Apr-2025 | 25-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | Anning Johnson | #2490FF | D16 | CHI11-05-03-40 | MATCHING | C05/03-DH- Install Drywall (One Side - Facing DH) | 26-Apr-2025 | 28-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE51 | CHI11-05-03-55 | MATCHING | C05/03-DH- Overhead R/I - Fire Alarm | 30-Apr-2025 | 02-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE28 | CHI11-05-03-60 | MATCHING | C05/03-DH- Overhead R/I - Electrical | 30-Apr-2025 | 05-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | Anning Johnson | #2490FF | D14 | CHI11-05-03-65 | MATCHING | C05/03-DH- Finish Dry-Wall | 30-Apr-2025 | 02-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | Continental - TBD | #D6F2FF | Y2 | CHI11-05-03-115 | MATCHING | C05/03-DH- Paint Dry-Wall | 30-Apr-2025 | 02-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | Imperial/Span | #E0D0D0 | X7 | CHI11-05-03-150 | MATCHING | C05/03-DH- Install Secondary Steel | 30-Apr-2025 | 02-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | Continental - TBD | #D6F2FF | Y3 | CHI11-05-03-155 | MATCHING | C05/03-DH- Paint Secondary Steel | 06-May-2025 | 07-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | Anning Johnson | #2490FF | D8 | CHI11-05-03-135 | MATCHING | C05/03-DH- Install Screen Mesh + Caulking | 16-May-2025 | 19-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | Anning Johnson | #2490FF | D4 | CHI11-05-03-170 | MATCHING | C05/03-DH- Install Ceiling Grid | 20-May-2025 | 29-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE10 | CHI11-05-03-90 | MATCHING | C05/03-DH- Drop Cable Tray [Hanging Rods] | 30-May-2025 | 31-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | Anning Johnson | #2490FF | D21 | CHI11-05-03-215 | MATCHING | C05/03-DH- Install Device Tiles | 30-May-2025 | 31-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | Cleaning | #FFC6FF | C1 | CHI11-05-03-165 | MATCHING | C05/03-DH- General Cleaning | 02-Jun-2025 | 02-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE39 | CHI11-05-03-285 | MATCHING | C05/03-DH- Pull Feeders from PDUs to Busways | 07-Jul-2025 | 22-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE50 | CHI11-05-03-310 | MATCHING | C05/03-DH- Terminate PDUs | 22-Jul-2025 | 01-Aug-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | Shambaugh | #D76672 | R2 | CHI11-05-03-45 | MATCHING | C05/03-Elec Rm- Overhead R/I - Fire Protection | 04-Apr-2025 | 05-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE51 | CHI11-05-03-70 | MATCHING | C05/03-Elec Rm- Overhead R/I - Fire Alarm | 07-Apr-2025 | 08-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE28 | CHI11-05-03-75 | MATCHING | C05/03-Elec Rm- Overhead R/I - Electrical | 07-Apr-2025 | 09-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | Imperial/Span | #E0D0D0 | X7 | CHI11-05-03-850 | MATCHING | C05/03-Elec Rm- Install Secondary Steel | 10-Apr-2025 | 15-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | Anning Johnson | #2490FF | D7 | CHI11-05-03-25 | MATCHING | C05/03-Elec Rm- Install Framing | 16-Apr-2025 | 19-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | MEP | #FF7BFF | MEP2 | CHI11-05-03-30 | MATCHING | C05/03-Elec Rm- In-Wall R/I | 18-Apr-2025 | 19-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | Anning Johnson | #2490FF | D17 | CHI11-05-03-50 | MATCHING | C05/03-Elec Rm- Install Drywall [Elec + Battery Rooms] | 21-Apr-2025 | 24-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | Anning Johnson | #2490FF | D14 | CHI11-05-03-95 | MATCHING | C05/03-Elec Rm- Finish Dry-Wall | 25-Apr-2025 | 26-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | Continental - TBD | #D6F2FF | Y2 | CHI11-05-03-125 | MATCHING | C05/03-Elec Rm- Paint Dry-Wall | 16-May-2025 | 17-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | Hill Mechanical | #C9DF56 | M3 | CHI11-05-03-85 | MATCHING | C05/03-Elec Rm- Overhead R/I - Mechanical | 19-May-2025 | 21-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE10 | CHI11-05-03-100 | MATCHING | C05/03-Elec Rm- Drop Cable Tray [Hanging Rods] | 21-May-2025 | 21-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | Cleaning | #FFC6FF | C1 | CHI11-05-03-140 | MATCHING | C05/03-Elec Rm- General Cleaning | 22-May-2025 | 22-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE38 | CHI11-05-03-305 | MATCHING | C05/03-Elec Rm- Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 07-Jul-2025 | 25-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE33 | CHI11-05-03-295 | MATCHING | C05/03-Elec Rm- Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 12-Jul-2025 | 18-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE48 | CHI11-05-03-300 | MATCHING | C05/03-Elec Rm- Terminate Electrical Equipments [Inside Electrical Room] | 12-Jul-2025 | 25-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | Shambaugh | #D76672 | R2 | CHI11-05-03-80 | MATCHING | C05/03-Mech Gallery- Overhead R/I - Fire Protection | 30-Apr-2025 | 01-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE51 | CHI11-05-03-105 | MATCHING | C05/03-Mech Gallery- Overhead R/I - Fire Alarm | 30-Apr-2025 | 02-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE28 | CHI11-05-03-110 | MATCHING | C05/03-Mech Gallery- Overhead R/I - Electrical | 30-Apr-2025 | 03-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | Anning Johnson | #2490FF | D18 | CHI11-05-03-175 | MATCHING | C05/03-Mech Gallery- Install Drywall [Mech Gallery] | 01-May-2025 | 03-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | Anning Johnson | #2490FF | D14 | CHI11-05-03-190 | MATCHING | C05/03-Mech Gallery- Finish Dry-Wall | 02-May-2025 | 05-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | Hill Mechanical | #C9DF56 | M3 | CHI11-05-03-130 | MATCHING | C05/03-Mech Gallery- Overhead R/I - Mechanical | 05-May-2025 | 07-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | Anning Johnson | #2490FF | D5 | CHI11-05-03-200 | MATCHING | C05/03-Mech Gallery- Install Ceiling Grid + Device Tiles | 06-May-2025 | 08-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | Continental - TBD | #D6F2FF | Y2 | CHI11-05-03-210 | MATCHING | C05/03-Mech Gallery- Paint Dry-Wall | 08-May-2025 | 08-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | Cleaning | #FFC6FF | C1 | CHI11-05-03-230 | MATCHING | C05/03-Mech Gallery- General Cleaning | 08-May-2025 | 08-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | Hill Mechanical | #C9DF56 | M4 | CHI11-05-03-245 | MATCHING | C05/03-Mech Gallery- Set Mechanical Equipments | 15-May-2025 | 15-May-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE60 | CHI11-05-03-255 | MATCHING | C05/03-Mech Gallery- Pull Cable to Mechanical Equipments [From Electrical Room] | 10-Jul-2025 | 23-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | Hill Mechanical | #C9DF56 | M5 | CHI11-05-03-290 | MATCHING | C05/03-Mech Gallery- Terminate Mechanical Equipments | 24-Jul-2025 | 02-Aug-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-05-03-280 | MATCHING | C05/03- Pre-Energization Checks | 04-Aug-2025 | 14-Aug-2025
FITOUT | COLO 5 | CELL 4 TELECOM | CECCO | #EF9E5B | T4 | CHI11-05-04-TEL-1000 | MATCHING | C05/04 - Backbone Fiber | 12-Aug-2025 | 19-Aug-2025
FITOUT | COLO 5 | CELL 4 TELECOM | CECCO | #EF9E5B | T6 | CHI11-05-04-TEL-980 | MATCHING | C05/04 - Production Fiber (Plug/TEST) | 26-Aug-2025 | 10-Sep-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | Anning Johnson | #2490FF | D10 | CHI11-05-04-10 | MATCHING | C05/04-DH- Layout Framing | 04-Apr-2025 | 04-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | Anning Johnson | #2490FF | D7 | CHI11-05-04-15 | MATCHING | C05/04-DH- Install Framing | 05-Apr-2025 | 08-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | MEP | #FF7BFF | MEP2 | CHI11-05-04-20 | MATCHING | C05/04-DH- In-Wall R/I | 09-Apr-2025 | 11-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | Shambaugh | #D76672 | R2 | CHI11-05-04-35 | MATCHING | C05/04-DH- Overhead R/I - Fire Protection | 14-Apr-2025 | 16-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | Anning Johnson | #2490FF | D16 | CHI11-05-04-40 | MATCHING | C05/04-DH- Install Drywall (One Side - Facing DH) | 14-Apr-2025 | 16-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | GIBSON | #FFF9B1 | EE51 | CHI11-05-04-55 | MATCHING | C05/04-DH- Overhead R/I - Fire Alarm | 17-Apr-2025 | 21-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | GIBSON | #FFF9B1 | EE28 | CHI11-05-04-60 | MATCHING | C05/04-DH- Overhead R/I - Electrical | 17-Apr-2025 | 22-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | Anning Johnson | #2490FF | D14 | CHI11-05-04-65 | MATCHING | C05/04-DH- Finish Dry-Wall | 17-Apr-2025 | 21-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | Continental - TBD | #D6F2FF | Y2 | CHI11-05-04-115 | MATCHING | C05/04-DH- Paint Dry-Wall | 22-Apr-2025 | 24-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | Imperial/Span | #E0D0D0 | X7 | CHI11-05-04-150 | MATCHING | C05/04-DH- Install Secondary Steel | 25-Apr-2025 | 26-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | Continental - TBD | #D6F2FF | Y3 | CHI11-05-04-155 | MATCHING | C05/04-DH- Paint Secondary Steel | 28-Apr-2025 | 28-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | Anning Johnson | #2490FF | D8 | CHI11-05-04-135 | MATCHING | C05/04-DH- Install Screen Mesh + Caulking | 30-Apr-2025 | 12-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | Shambaugh | #D76672 | R2 | CHI11-05-04-45 | MATCHING | C05/04-Elec Rm- Overhead R/I - Fire Protection | 08-Apr-2025 | 09-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE51 | CHI11-05-04-70 | MATCHING | C05/04-Elec Rm- Overhead R/I - Fire Alarm | 10-Apr-2025 | 14-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE28 | CHI11-05-04-75 | MATCHING | C05/04-Elec Rm- Overhead R/I - Electrical | 10-Apr-2025 | 14-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | Imperial/Span | #E0D0D0 | X7 | CHI11-05-04-850 | MATCHING | C05/04-Elec Rm- Secondary Steel | 15-Apr-2025 | 17-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | Anning Johnson | #2490FF | D7 | CHI11-05-04-25 | MATCHING | C05/04-Elec Rm- Install Framing | 21-Apr-2025 | 23-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | MEP | #FF7BFF | MEP2 | CHI11-05-04-30 | MATCHING | C05/04-Elec Rm- In-Wall R/I | 22-Apr-2025 | 24-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | Anning Johnson | #2490FF | D17 | CHI11-05-04-50 | MATCHING | C05/04-Elec Rm- Install Drywall [Elec + Battery Rooms] | 23-Apr-2025 | 25-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | Anning Johnson | #2490FF | D14 | CHI11-05-04-95 | MATCHING | C05/04-Elec Rm- Finish Dry-Wall | 26-Apr-2025 | 29-Apr-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | Continental - TBD | #D6F2FF | Y2 | CHI11-05-04-125 | MATCHING | C05/04-Elec Rm- Paint Dry-Wall | 30-Apr-2025 | 01-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | Hill Mechanical | #C9DF56 | M3 | CHI11-05-04-85 | MATCHING | C05/04-Elec Rm- Overhead R/I - Mechanical | 02-May-2025 | 10-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE10 | CHI11-05-04-100 | MATCHING | C05/04-Elec Rm- Drop Cable Tray [Hanging Rods] | 16-May-2025 | 16-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | Cleaning | #FFC6FF | C1 | CHI11-05-04-140 | MATCHING | C05/04-Elec Rm- General Cleaning | 22-May-2025 | 22-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE33 | CHI11-05-04-280 | MATCHING | C05/04-Elec Rm- Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 12-Jul-2025 | 19-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE38 | CHI11-05-04-305 | MATCHING | C05/04-Elec Rm- Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 12-Jul-2025 | 19-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE48 | CHI11-05-04-300 | MATCHING | C05/04-Elec Rm- Terminate Electrical Equipments [Inside Electrical Room] | 21-Jul-2025 | 01-Aug-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | Shambaugh | #D76672 | R2 | CHI11-05-04-80 | MATCHING | C05/04-Mech Gallery- Overhead R/I - Fire Protection | 30-Apr-2025 | 01-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE51 | CHI11-05-04-105 | MATCHING | C05/04-Mech Gallery- Overhead R/I - Fire Alarm | 30-Apr-2025 | 02-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE28 | CHI11-05-04-110 | MATCHING | C05/04-Mech Gallery- Overhead R/I - Electrical | 30-Apr-2025 | 03-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | Anning Johnson | #2490FF | D18 | CHI11-05-04-175 | MATCHING | C05/04-Mech Gallery- Install Drywall [Mech Gallery] | 01-May-2025 | 03-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | Anning Johnson | #2490FF | D14 | CHI11-05-04-190 | MATCHING | C05/04-Mech Gallery- Finish Dry-Wall | 02-May-2025 | 05-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | Hill Mechanical | #C9DF56 | M3 | CHI11-05-04-130 | MATCHING | C05/04-Mech Gallery- Overhead R/I - Mechanical | 05-May-2025 | 09-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | Continental - TBD | #D6F2FF | Y2 | CHI11-05-04-210 | MATCHING | C05/04-Mech Gallery- Paint Dry-Wall | 06-May-2025 | 08-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | Cleaning | #FFC6FF | C1 | CHI11-05-04-230 | MATCHING | C05/04-Mech Gallery- General Cleaning | 08-May-2025 | 08-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE13 | CHI11-05-04-240 | MATCHING | C05/04-Mech Gallery- Install BAS Equipments | 09-May-2025 | 30-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | Anning Johnson | #2490FF | D5 | CHI11-05-04-200 | MATCHING | C05/04-Mech Gallery- Install Ceiling Grid + Device Tiles | 12-May-2025 | 14-May-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | Hill Mechanical | #C9DF56 | M4 | CHI11-05-04-245 | MATCHING | C05/04-Mech Gallery- Set Mechanical Equipments | 15-May-2025 | 15-May-2025
Commissioning | Site | MVM-01 | MSFT | #3DCD3A | CX7 | CHI11-CX-10 | MATCHING | MEP Test/Pre Startup Installer (MVM01) | 18-Apr-2025 | 02-May-2025
Commissioning | Site | MVM-01 | MSFT | #3DCD3A | CX10 | CHI11-CX-11 | MATCHING | FOD Clean (MVM01) | 07-May-2025 | 07-May-2025
Commissioning | Site | MVM-01 | CLAYCO | #EE5A1C | Y11 | CHI11-CX-12 | MATCHING | L2 QA/QC FOD (MVM01) | 08-May-2025 | 08-May-2025
Commissioning | Site | MVM-01 | MSFT | #3DCD3A | CX12 | CHI11-CX-13 | MATCHING | IVC (MVM01) | 09-May-2025 | 09-May-2025
Commissioning | Site | MVM-01 | MSFT | #3DCD3A | CX13 | CHI11-CX-111 | MATCHING | CYT (MVM01) | 14-May-2025 | 14-May-2025
Commissioning | Site | MVM-01 | MSFT | #3DCD3A | CX14 | CHI11-CX-112 | MATCHING | Conditional Energization (MVM01) | 15-May-2025 | 15-May-2025
Commissioning | Site | MVM-01 | MSFT | #3DCD3A | CX15 | CHI11-CX-04 | MATCHING | De-Energization and Conditional Energization (MVM01) RFI343 | 22-May-2025 | 22-May-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | MSFT | #3DCD3A | CX7 | CHI11-CX-21 | MATCHING | MEP Test/Pre Startup Installer (UMS01-LA01) | 08-Apr-2025 | 25-Apr-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | MSFT | #3DCD3A | CX8 | CHI11-CX-20 | MATCHING | Pre Startup Vendor (UMS01-LA01) | 28-Apr-2025 | 02-May-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | MSFT | #3DCD3A | CX9 | CHI11-CX-31 | MATCHING | Control Checks (UMS01-LA01) | 05-May-2025 | 08-May-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | MSFT | #3DCD3A | CX10 | CHI11-CX-22 | MATCHING | FOD Clean (UMS01-LA01) | 09-May-2025 | 09-May-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | CLAYCO | #EE5A1C | Y11 | CHI11-CX-23 | MATCHING | L2 QA/QC FOD (UMS01-LA01) | 09-May-2025 | 12-May-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | MSFT | #3DCD3A | CX12 | CHI11-CX-24 | MATCHING | IVC (UMS01-LA01) | 09-May-2025 | 13-May-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | MSFT | #3DCD3A | CX13 | CHI11-CX-06 | MATCHING | CYT (UMS01-LA01) | 14-May-2025 | 14-May-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | MSFT | #3DCD3A | CX14 | CHI11-CX-07 | MATCHING | Conditional Energization (UMS01-LA01) | 15-May-2025 | 15-May-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | MSFT | #3DCD3A | CX15 | CHI11-CX-08 | MATCHING | De-Energization and Conditional Energization (UMS01-LA01) RFI343 | 22-May-2025 | 22-May-2025
Commissioning | Admin | ADMIN-XFM01 | MSFT | #3DCD3A | CX7 | CX4360 | MATCHING | MEP Test/Pre Startup Installer (ADMIN-XFM01) | 07-Apr-2025 | 06-May-2025
Commissioning | Admin | ADMIN-XFM01 | MSFT | #3DCD3A | CX8 | CX4370 | MATCHING | Pre Startup Vendor (ADMIN-XFM01) | 07-May-2025 | 07-May-2025
Commissioning | Admin | ADMIN-XFM01 | MSFT | #3DCD3A | CX9 | CX4380 | MATCHING | Control Checks (ADMIN-XFM01) | 13-May-2025 | 19-May-2025
Commissioning | Admin | ADMIN-XFM01 | MSFT | #3DCD3A | CX10 | CX4390 | MATCHING | FOD Clean (ADMIN-XFM01) | 20-May-2025 | 20-May-2025
Commissioning | Admin | ADMIN-XFM01 | CLAYCO | #EE5A1C | Y11 | CX4400 | MATCHING | L2 QA/QC FOD (ADMIN-XFM01) | 21-May-2025 | 21-May-2025
Commissioning | Admin | ADMIN-XFM01 | MSFT | #3DCD3A | CX12 | CX4410 | MATCHING | IVC (ADMIN-XFM01) | 22-May-2025 | 22-May-2025
Commissioning | Admin | ADMIN-PNL04 | MSFT | #3DCD3A | CX7 | CX4490 | MATCHING | MEP Test/Pre Startup Installer (ADMIN-PNL04) | 15-Apr-2025 | 09-May-2025
Commissioning | Admin | ADMIN-MSB01 | MSFT | #3DCD3A | CX8 | CX4890 | MATCHING | Pre Startup Vendor (ADMIN-MSB01) | 27-May-2025 | 28-May-2025
Commissioning | Admin | ADMIN-ATS (01-06) | MSFT | #3DCD3A | CX17 | CX4830 | MATCHING | Energization (ADMIN-ATS (01-06)) | 21-Jun-2025 | 21-Jun-2025
Commissioning | Admin | Admin-UOP,UIP,UPS | MSFT | #3DCD3A | CX10 | CX5030 | MATCHING | FOD Clean (ADMIN-UOP,UIP,UPS) | 06-Jun-2025 | 06-Jun-2025
Commissioning | COLO 3 | COLO3 & Admin UPM | MSFT | #3DCD3A | CX7 | A2890 | MATCHING | MEP Test/Pre Startup Installer (COLO3 and ADMIN UPM) | 11-Apr-2025 | 25-Apr-2025
Commissioning | COLO 3 | COLO3 & Admin UPM | MSFT | #3DCD3A | CX8 | A2900 | MATCHING | Pre Startup Vendor (COLO3 and ADMIN UPM) | 28-Apr-2025 | 05-May-2025
Commissioning | COLO 3 | COLO3 & Admin UPM | MSFT | #3DCD3A | CX9 | A2910 | MATCHING | Control Checks (COLO3 and ADMIN UPM) | 07-May-2025 | 09-May-2025
Commissioning | COLO 3 | COLO3 & Admin UPM | MSFT | #3DCD3A | CX16 | A2950 | MATCHING | Yellow Tag (COLO3 and ADMIN UPM) | 23-May-2025 | 27-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-XFM01 | MSFT | #3DCD3A | CX7 | A3020 | MATCHING | MEP Test/Pre Startup Installer (COLO3-CE1/CE2-XFM01) | 19-Mar-2025 | 05-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-XFM01 | MSFT | #3DCD3A | CX8 | A3030 | MATCHING | Pre Startup Vendor (COLO3-CE1/CE2-XFM01) | 06-May-2025 | 09-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | MSFT | #3DCD3A | CX7 | A3150 | MATCHING | MEP Test/Pre Startup Installer (COLO3-CE3/CE4-XFM01) | 19-Mar-2025 | 09-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | MSFT | #3DCD3A | CX8 | A3160 | MATCHING | Pre Startup Vendor (COLO3-CE3/CE4-XFM01) | 12-May-2025 | 13-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-PNL01 | MSFT | #3DCD3A | CX7 | CX1000 | MATCHING | MEP Test/Pre Startup Installer (COLO3-CE1/CE2-PNL02) | 02-Apr-2025 | 09-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-PNL01 | MSFT | #3DCD3A | CX7 | CX1130 | MATCHING | MEP Test/Pre Startup Installer (COLO3-CE3/CE4-PNL02) | 02-Apr-2025 | 13-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX7 | CX1370 | MATCHING | MEP Test/Pre Startup Installer (COLO3-CE3/CE4-MSB01 and TCP01) | 28-Mar-2025 | 23-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX8 | CX1380 | MATCHING | Pre Startup Vendor (COLO3-CE3/CE4-MSB01 and TCP01) | 27-May-2025 | 28-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX16 | CX1430 | MATCHING | Yellow Tag (COLO3-CE3/CE4-MSB01 and TCP01) | 12-Jun-2025 | 13-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX19 | CX1460 | MATCHING | IR Scans (COLO3-CE3/CE4-MSB01 and TCP01) | 26-Jun-2025 | 26-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX20 | CX1470 | MATCHING | EPMS SAT (COLO3-CE3/CE4-MSB01 and TCP01) | 26-Jun-2025 | 26-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | CLAYCO | #EE5A1C | Y10 | CX1480 | MATCHING | L3 PFC (COLO3-CE3/CE4-MSB01 and TCP01) | 27-Jun-2025 | 27-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX22 | CX1490 | MATCHING | Green Tag (COLO3-CE3/CE4-MSB01 and TCP01) | 28-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX7 | CX1500 | MATCHING | MEP Test/Pre Startup Installer (COLO3-CE1/CE2-ADP01) | 28-Mar-2025 | 23-May-2025
Commissioning | COLO 3 | COLO3-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX8 | CX2290 | MATCHING | Pre Startup Vendor (COLO3-CE3-PDU(01-06)) | 09-Jun-2025 | 11-Jun-2025
Commissioning | COLO 3 | COLO3-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX10 | CX2300 | MATCHING | FOD Clean (COLO3-CE3-PDU(01-06)) | 12-Jun-2025 | 13-Jun-2025
Commissioning | COLO 3 | COLO3-CE3-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y11 | CX2310 | MATCHING | L2 QA/QC FOD (COLO3-CE3-PDU(01-06)) | 16-Jun-2025 | 17-Jun-2025
Commissioning | COLO 3 | COLO3-CE4-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX8 | CX2410 | MATCHING | Pre Startup Vendor (COLO3-CE4-PDU(01-06)) | 09-Jun-2025 | 11-Jun-2025
Commissioning | COLO 3 | COLO3-CE4-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX10 | CX2420 | MATCHING | FOD Clean (COLO3-CE4-PDU(01-06)) | 12-Jun-2025 | 13-Jun-2025
Commissioning | COLO 3 | COLO3-CE4-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y11 | CX2430 | MATCHING | L2 QA/QC FOD (COLO3-CE4-PDU(01-06)) | 16-Jun-2025 | 17-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX7 | CX3390 | MATCHING | MEP Test/Pre Startup Installer (COLO3-CE1/CE2-ATS(01-06)) | 09-Apr-2025 | 02-May-2025
Commissioning | COLO 3 | COLO3-Control Panel and CC | MSFT | #3DCD3A | CX22 | CX3720 | MATCHING | Green Tag (COLO3-Control Panel and CC) | 01-Jul-2025 | 01-Jul-2025
Commissioning | COLO 3 | CHI11-FP/JP-01 | MSFT | #3DCD3A | CX10 | CX4280 | MATCHING | FOD Clean (CH11-FP/JP-01) | 29-Jul-2025 | 29-Jul-2025
Commissioning | COLO 3 | CHI11-FP/JP-01 | CLAYCO | #EE5A1C | Y11 | CX4290 | MATCHING | L2 QA/QC FOD (CH11-FP/JP-01) | 30-Jul-2025 | 30-Jul-2025
Commissioning | COLO 3 | CHI11-FP/JP-01 | MSFT | #3DCD3A | CX12 | CX4300 | MATCHING | IVC (CH11-FP/JP-01) | 31-Jul-2025 | 31-Jul-2025
Commissioning | COLO 3 | CHI11-FP/JP-01 | MSFT | #3DCD3A | CX16 | CX4310 | MATCHING | Yellow Tag (CH11-FP/JP-01) | 01-Aug-2025 | 01-Aug-2025
Commissioning | COLO 4 | COLO4 UPM | MSFT | #3DCD3A | CX7 | CX5230 | MATCHING | MEP Test/Pre Startup Installer (COLO4 UPM) | 30-Apr-2025 | 30-May-2025
Commissioning | COLO 4 | COLO4 XFM01 | MSFT | #3DCD3A | CX9 | CX5320 | MATCHING | Control Checks (COLO4 XFM01) | 12-Jun-2025 | 13-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX7 | CX5810 | MATCHING | MEP Test/Pre Startup Installer (COLO4-CE1/CE2-MSB01 and TCP01) | 22-Apr-2025 | 13-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX8 | CX5840 | MATCHING | Pre Startup Vendor (COLO4-CE1/CE2-MSB01 and TCP01) | 16-Jun-2025 | 17-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX9 | CX5850 | MATCHING | Control Checks (COLO4-CE1/CE2-MSB01 and TCP01) | 18-Jun-2025 | 20-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX10 | CX5740 | MATCHING | FOD Clean (COLO4-CE1/CE2-MSB01 and TCP01) | 23-Jun-2025 | 24-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-MSB01 and TCP01 | CLAYCO | #EE5A1C | Y11 | CX5750 | MATCHING | L2 QA/QC FOD (COLO4-CE1/CE2-MSB01 and TCP01) | 25-Jun-2025 | 26-Jun-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX7 | CX5940 | MATCHING | MEP Test/Pre Startup Installer (COLO4-CE3/CE4-MSB01 and TCP01) | 25-Apr-2025 | 20-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX7 | CX6070 | MATCHING | MEP Test/Pre Startup Installer (COLO4-CE1/CE2-ADP01) | 24-Apr-2025 | 20-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX8 | CX6100 | MATCHING | Pre Startup Vendor (COLO4-CE1/CE2-ADP01) | 23-Jun-2025 | 24-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX10 | CX6000 | MATCHING | FOD Clean (COLO4-CE1/CE2-ADP01) | 25-Jun-2025 | 26-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ADP01 | CLAYCO | #EE5A1C | Y11 | CX6010 | MATCHING | L2 QA/QC FOD (COLO4-CE1/CE2-ADP01) | 27-Jun-2025 | 30-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX12 | CX6020 | MATCHING | IVC (COLO4-CE1/CE2-ADP01) | 01-Jul-2025 | 02-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX16 | CX6030 | MATCHING | Yellow Tag (COLO4-CE1/CE2-ADP01) | 03-Jul-2025 | 07-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX8 | CX6230 | MATCHING | Pre Startup Vendor (COLO4-CE3/CE4-ADP01) | 30-Jun-2025 | 01-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX10 | CX6130 | MATCHING | FOD Clean (COLO4-CE3/CE4-ADP01) | 02-Jul-2025 | 03-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-ADP01 | CLAYCO | #EE5A1C | Y11 | CX6140 | MATCHING | L2 QA/QC FOD (COLO4-CE3/CE4-ADP01) | 07-Jul-2025 | 08-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX12 | CX6150 | MATCHING | IVC (COLO4-CE3/CE4-ADP01) | 09-Jul-2025 | 10-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX16 | CX6160 | MATCHING | Yellow Tag (COLO4-CE3/CE4-ADP01) | 11-Jul-2025 | 14-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX8 | CX6360 | MATCHING | Pre Startup Vendor (COLO4-CE1/CE2(UPS01-02)) | 30-Jun-2025 | 07-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX10 | CX6260 | MATCHING | FOD Clean (COLO4-CE1/CE2(UPS01-02)) | 08-Jul-2025 | 09-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2(UPS01-02) | CLAYCO | #EE5A1C | Y11 | CX6270 | MATCHING | L2 QA/QC FOD (COLO4-CE1/CE2(UPS01-02)) | 10-Jul-2025 | 11-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX22 | CX6250 | MATCHING | Green Tag (COLO4-CE1/CE2(UPS01-02)) | 12-Aug-2025 | 14-Aug-2025
Commissioning | COLO 4 | COLO4-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX7 | CX6460 | MATCHING | MEP Test/Pre Startup Installer (COLO4-CE3/CE4(UPS01-02)) | 02-May-2025 | 03-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX8 | CX6490 | MATCHING | Pre Startup Vendor (COLO4-CE3/CE4(UPS01-02)) | 07-Jul-2025 | 11-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4(UPS01-02) | CLAYCO | #EE5A1C | Y10 | CX6450 | MATCHING | L3 PFC (COLO4-CE3/CE4(UPS01-02)) | 11-Aug-2025 | 13-Aug-2025
Commissioning | COLO 4 | COLO4-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX22 | CX6380 | MATCHING | Green Tag (COLO4-CE3/CE4(UPS01-02)) | 14-Aug-2025 | 18-Aug-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX17 | CX7180 | MATCHING | Energization (COLO4-CE3/CE4-GPC01) | 21-Jul-2025 | 21-Jul-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | CLAYCO | #EE5A1C | Y9 | CX7190 | MATCHING | L3 Startup (COLO4-CE3/CE4-GPC01) | 21-Jul-2025 | 22-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX17 | CX7330 | MATCHING | Energization (CHI11-COLO4-CE3-LBP01/LBT01) | 22-Jul-2025 | 22-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3-LBP01/LBT01 | CLAYCO | #EE5A1C | Y9 | CX7370 | MATCHING | L3 Startup (CHI11-COLO4-CE3-LBP01/LBT01) | 23-Jul-2025 | 23-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX20 | CX7380 | MATCHING | EPMS SAT (CHI11-COLO4-CE3-LBP01/LBT01) | 24-Jul-2025 | 24-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX19 | CX7340 | MATCHING | IR Scans (CHI11-COLO4-CE3-LBP01/LBT01) | 25-Jul-2025 | 25-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3-LBP01/LBT01 | CLAYCO | #EE5A1C | Y10 | CX7350 | MATCHING | L3 PFC (CHI11-COLO4-CE3-LBP01/LBT01) | 28-Jul-2025 | 29-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX22 | CX7280 | MATCHING | Green Tag (CHI11-COLO4-CE3-LBP01/LBT01) | 30-Jul-2025 | 31-Jul-2025
Commissioning | COLO 4 | COLO4-Loadbank Busway | MSFT | #3DCD3A | CX7 | CX7920 | MATCHING | MEP Test/Pre Startup Installer (COLO4-CE1/CE2-ATS(01-06)) | 22-Apr-2025 | 09-May-2025
Commissioning | COLO 4 | COLO4-Loadbank Busway | MSFT | #3DCD3A | CX8 | CX7830 | MATCHING | Pre Startup Vendor (COLO4-CE1/CE2-ATS(01-06)) | 12-May-2025 | 14-May-2025
Commissioning | COLO 4 | COLO4-Loadbank Busway | MSFT | #3DCD3A | CX10 | CX7850 | MATCHING | FOD Clean (COLO4-CE1/CE2-ATS(01-06)) | 15-May-2025 | 16-May-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | MSFT | #3DCD3A | CX7 | CX8700 | MATCHING | MEP Test/Pre Startup Installer (CH11-COLO4-Water Heater) | 09-Jun-2025 | 13-Jun-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | MSFT | #3DCD3A | CX10 | CX8650 | MATCHING | FOD Clean (CH11-COLO4-Water Heater) | 16-Jun-2025 | 16-Jun-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | CLAYCO | #EE5A1C | Y11 | CX8660 | MATCHING | L2 QA/QC FOD (CH11-COLO4-Water Heater) | 17-Jun-2025 | 18-Jun-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | MSFT | #3DCD3A | CX12 | CX8670 | MATCHING | IVC (CH11-COLO4-Water Heater) | 19-Jun-2025 | 20-Jun-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | MSFT | #3DCD3A | CX16 | CX8680 | MATCHING | Yellow Tag (CH11-COLO4-Water Heater) | 23-Jun-2025 | 24-Jun-2025
Commissioning | COLO 5 | COLO5 UPM | MSFT | #3DCD3A | CX12 | CX9120 | MATCHING | IVC (COLO5 UPM) | 14-Jul-2025 | 16-Jul-2025
Commissioning | COLO 5 | COLO5 UPM | MSFT | #3DCD3A | CX16 | CX9130 | MATCHING | Yellow Tag (COLO5 UPM) | 17-Jul-2025 | 18-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-MSB01 | MSFT | #3DCD3A | CX8 | CX9540 | MATCHING | Pre Startup Vendor (COLO5-CE1/CE2-MSB01 and TCP01) | 14-Jul-2025 | 15-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-MSB01 | MSFT | #3DCD3A | CX9 | CX9550 | MATCHING | Control Checks (COLO5-CE1/CE2-MSB01 and TCP01) | 16-Jul-2025 | 18-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX8 | CX9800 | MATCHING | Pre Startup Vendor (COLO5-CE1/CE2-ADP01) | 21-Jul-2025 | 22-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX10 | CX9700 | MATCHING | FOD Clean (COLO5-CE1/CE2-ADP01) | 23-Jul-2025 | 24-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ADP01 | CLAYCO | #EE5A1C | Y11 | CX9710 | MATCHING | L2 QA/QC FOD (COLO5-CE1/CE2-ADP01) | 25-Jul-2025 | 28-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX12 | CX9720 | MATCHING | IVC (COLO5-CE1/CE2-ADP01) | 29-Jul-2025 | 30-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX16 | CX9730 | MATCHING | Yellow Tag (COLO5-CE1/CE2-ADP01) | 31-Jul-2025 | 01-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX8 | CX9930 | MATCHING | Pre Startup Vendor (COLO5-CE3/CE4-ADP01) | 28-Jul-2025 | 29-Jul-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX10 | CX9830 | MATCHING | FOD Clean (COLO5-CE3/CE4-ADP01) | 30-Jul-2025 | 31-Jul-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-ADP01 | CLAYCO | #EE5A1C | Y11 | CX9840 | MATCHING | L2 QA/QC FOD (COLO5-CE3/CE4-ADP01) | 01-Aug-2025 | 04-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX12 | CX9850 | MATCHING | IVC (COLO5-CE3/CE4-ADP01) | 05-Aug-2025 | 06-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX16 | CX9860 | MATCHING | Yellow Tag (COLO5-CE3/CE4-ADP01) | 07-Aug-2025 | 08-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX8 | CX10060 | MATCHING | Pre Startup Vendor (COLO5-CE1/CE2(UPS01-02)) | 28-Jul-2025 | 01-Aug-2025
Commissioning | COLO 5 | CHI11-COLO5-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX7 | CX11060 | MATCHING | MEP Test/Pre Startup Installer (CHI11-COLO5-CE3-LBP01/LBT01) | 02-Jul-2025 | 18-Jul-2025
Commissioning | COLO 5 | CHI11-COLO5-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX8 | CX10970 | MATCHING | Pre Startup Vendor (CHI11-COLO5-CE3-LBP01/LBT01) | 21-Jul-2025 | 22-Jul-2025
Commissioning | COLO 5 | CHI11-COLO5-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX10 | CX10990 | MATCHING | FOD Clean (CHI11-COLO5-CE3-LBP01/LBT01) | 23-Jul-2025 | 23-Jul-2025
Commissioning | COLO 5 | CHI11-COLO5-CE3-LBP01/LBT01 | CLAYCO | #EE5A1C | Y11 | CX11000 | MATCHING | L2 QA/QC FOD (CHI11-COLO5-CE3-LBP01/LBT01) | 24-Jul-2025 | 25-Jul-2025
Commissioning | COLO 5 | CHI11-COLO5-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX12 | CX11010 | MATCHING | IVC (CHI11-COLO5-CE3-LBP01/LBT01) | 28-Jul-2025 | 29-Jul-2025
Commissioning | COLO 5 | CHI11-COLO5-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX16 | CX11020 | MATCHING | Yellow Tag (CHI11-COLO5-CE3-LBP01/LBT01) | 30-Jul-2025 | 31-Jul-2025
Commissioning | COLO 5 | COLO5 LV Panel and XFM | MSFT | #3DCD3A | CX10 | CX11340 | MATCHING | FOD Clean (COLO5- Panel and XFM) | 24-Jul-2025 | 25-Jul-2025
Commissioning | COLO 5 | COLO5 LV Panel and XFM | CLAYCO | #EE5A1C | Y11 | CX11350 | MATCHING | L2 QA/QC FOD (COLO5- LV Panel and XFM) | 28-Jul-2025 | 29-Jul-2025
Commissioning | COLO 5 | COLO5 LV Panel and XFM | MSFT | #3DCD3A | CX12 | CX11360 | MATCHING | IVC (COLO5- LV Panel and XFM) | 30-Jul-2025 | 01-Aug-2025
Commissioning | COLO 5 | COLO5 LV Panel and XFM | MSFT | #3DCD3A | CX16 | CX11370 | MATCHING | Yellow Tag (COLO5-LV Panel and XFM) | 04-Aug-2025 | 05-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-AHU(01-08) | MSFT | #3DCD3A | CX8 | CX11640 | MATCHING | Pre Startup Vendor (COLO5-CE1/CE2-AHU(01-08)) | 23-Jul-2025 | 25-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-AHU(01-08) | MSFT | #3DCD3A | CX10 | CX11660 | MATCHING | FOD Clean (COLO5-CE1/CE2-AHU(01-08)) | 28-Jul-2025 | 30-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-AHU(01-08) | CLAYCO | #EE5A1C | Y11 | CX11670 | MATCHING | L2 QA/QC FOD (COLO5-CE1/CE2-AHU(01-08)) | 31-Jul-2025 | 01-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-AHU(01-08) | MSFT | #3DCD3A | CX12 | CX11680 | MATCHING | IVC (COLO5-CE1/CE2-AHU(01-08)) | 04-Aug-2025 | 06-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-AHU(01-08) | MSFT | #3DCD3A | CX16 | CX11690 | MATCHING | Yellow Tag (COLO5-CE1/CE2-AHU(01-08)) | 07-Aug-2025 | 08-Aug-2025
Commissioning (L2- L5) | COLO 3 | Functional Testing (Level 4 & 5) | MSFT | #3DCD3A | CX1 | CHI11-03-L4-10 | MATCHING | C03-L4Cx- Testing <MSFT Duration> | 15-Aug-2025 | 15-Sep-2025
Commissioning (L2- L5) | COLO 3 | Functional Testing (Level 4 & 5) | MSFT | #3DCD3A | CX1 | CHI11-03-L5-10 | MATCHING | C03-L5Cx- Testing <MSFT Duration> | 16-Sep-2025 | 18-Sep-2025
Commissioning (L2- L5) | COLO 4 | Functional Testing (Level 4 & 5) | MSFT | #3DCD3A | CX1 | CHI11-04-L4-10 | MATCHING | C04-L4Cx- Testing <MSFT Duration> | 20-Sep-2025 | 16-Oct-2025
Commissioning (L2- L5) | COLO 4 | Functional Testing (Level 4 & 5) | MSFT | #3DCD3A | CX1 | CHI11-04-L5-10 | MATCHING | C04-L5Cx- Testing <MSFT Duration> | 17-Oct-2025 | 20-Oct-2025
Commissioning (L2- L5) | COLO 5 | Functional Testing (Level 4 & 5) | MSFT | #3DCD3A | CX1 | CHI11-05-L4-10 | MATCHING | C05-L4Cx- Testing <MSFT Duration> | 17-Oct-2025 | 15-Nov-2025
Commissioning (L2- L5) | COLO 5 | Functional Testing (Level 4 & 5) | MSFT | #3DCD3A | CX1 | CHI11-05-L5-10 | MATCHING | C05-L5Cx- Testing <MSFT Duration> | 17-Nov-2025 | 19-Nov-2025
Milestones | General | N/A | CLAYCO | #EE5A1C | M-C | CHI-11-03-BNU-EARLY | MODIFIED | Admin/COLO3 - Early Beneficial Use Rooms | 06-Jun-2025 | 06-Jun-2025
Milestones | General | N/A | CLAYCO | #EE5A1C | M-C | CHI-11-03-EW-F | MODIFIED | GEN MS- Complete Earthwork & U/G Site Utilities | 18-Jun-2025 | 18-Jun-2025
Milestones | Admin/ COLO 3 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-03-GEN-F | MODIFIED | Admin/COLO3- Generator Ready for Fuel (Exterior Yard) | 20-Jun-2025 | 20-Jun-2025
Milestones | Admin/ COLO 3 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-03-L3CX-S | MODIFIED | Admin/COLO3- Start L3 CX (Green Tag) | 15-May-2025 | 15-May-2025
Milestones | Admin/ COLO 3 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-03-L2CX-F | MODIFIED | Admin/COLO3- Complete L2 Cx (Yellow Tag) | 04-Aug-2025 | 04-Aug-2025
Milestones | COLO 4 | Core & Shell/ Fitout | CLAYCO | #EE5A1C | M-C | CHI-11-04-EBNF | MODIFIED | COLO4 - Early Beneficial Use Rooms | 02-Jul-2025 | 02-Jul-2025
Milestones | COLO 4 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-04-L3CX-S | MODIFIED | COLO4- Start L3 CX | 26-Jun-2025 | 26-Jun-2025
Milestones | COLO 4 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-04-L2CX-F | MODIFIED | COLO4- Complete L2 Cx (Yellow Tag) | 01-Aug-2025 | 01-Aug-2025
Milestones | COLO 5 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-05-L1CX-F | MODIFIED | COLO5- Complete L1 Cx (All Red Tags/ ROJ) | 02-Jul-2025 | 02-Jul-2025
Milestones | COLO 5 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-05-L3CX-S | MODIFIED | COLO5- Start L3 CX | 19-Jul-2025 | 19-Jul-2025
Milestones | COLO 5 | Commissioning | CLAYCO | #EE5A1C | M-C | CHI-11-05-L2CX-F | MODIFIED | COLO5- Complete L2 Cx (Yellow Tag) | 05-Sep-2025 | 05-Sep-2025
Milestones | COLO 5 | Clayco Key Milestones | CLAYCO | #EE5A1C | M-C | CHI-11-MS-06 | MODIFIED | CHI11: Utilities Available to Owner (Gas Service N/A) | 18-Jun-2025 | 18-Jun-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Power Distribution Units | OFCI | #900208 | M21 | CHI-11-05-PDU-02 | MODIFIED | C05- OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ | 19-Jun-2025 | 19-Jun-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Power Distribution Units | OFCI | #900208 | M21 | CHI-11-05-PDU-03 | MODIFIED | C05- OFCI- Power Distribution Units (PDU) (ABB) Delivered | 19-Jun-2025 | 19-Jun-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | UPS System W / Battery | OFCI | #900208 | M39 | CHI-11-05-UPS-02 | MODIFIED | C05- OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ | 23-May-2025 | 29-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | UPS System W / Battery | OFCI | #900208 | MH39 | CHI-11-05-UPS-03 | MODIFIED | C05- OFCI- Static UPS System W/Batt (UPS) (Eaton) Delivered | 29-May-2025 | 29-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Auto Transfer Control Panel | OFCI | #900208 | MH7 | CHI-11-05-TCP-02 | MODIFIED | C05- OFCI- Auto Transfer Control Panel (TCP) Shipping/ROJ | 06-Jun-2025 | 07-Jun-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Auto Transfer Control Panel | OFCI | #900208 | MH7 | CHI-11-05-TCP-03 | MODIFIED | C05- OFCI- Auto Transfer Control Panel (TCP) Delivered | 07-Jun-2025 | 07-Jun-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Auxillary Power Distribution | OFCI | #900208 | M16 | CHI-11-05-ADP-02 | MODIFIED | C05- OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ | 15-May-2025 | 29-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Auxillary Power Distribution | OFCI | #900208 | M16 | CHI-11-05-ADP-03 | MODIFIED | C05- OFCI- Mech Power Distribution Panels (ADP) Delivered | 29-May-2025 | 29-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Main LV Switch Board | OFCI | #900208 | M15 | CHI-11-05-MSB-02 | MODIFIED | C05- OFCI- Main LV Switch Board (MSB) Shipping/ROJ | 12-May-2025 | 29-May-2025
Procurement MSFT OFCI ROJ Dates | COLO 5 | Main LV Switch Board | OFCI | #900208 | M15 | CHI-11-05-MSB-03 | MODIFIED | C05- OFCI- Main LV Switch Board (MSB) Delivered | 29-May-2025 | 29-May-2025
PROCUREMENT | BOM OFCI | COLO 4 | CLAYCO | #EE5A1C | M-C | CHI-11-BOM-OFCI-30-TEL | MODIFIED | 2880's Production Cable COLO4 (4/17/2025) | 29-May-2025 | 29-May-2025
Construction | Site Utilities | Overall | Plumbing | #1F595B | P9 | CHI11-SU-80 | MODIFIED | Install COLO3 Perf & Roof-Drains Pipe | 08-Mar-2025 | 29-May-2025
Construction | Site Utilities | Overall | Plumbing | #1F595B | P10 | CHI11-SU-100 | MODIFIED | Install COLO5 Perf & Roof-Drains Pipe | 01-May-2025 | 29-May-2025
Construction | Site Utilities | Overall | Plumbing | #1F595B | P3 | CHI11-SU-90 | MODIFIED | Install COLO4 Perf & Roof-Drains Pipe | 23-May-2025 | 29-May-2025
Construction | CSA Exterior Work | Site | Scurto | #83CCEB | S2 | CHI11-CSA-20 | MODIFIED | Install Caissons South | 23-May-2025 | 13-Jun-2025
Construction | CSA Exterior Work | Site | Scurto | #83CCEB | S2 | CHI11-CSA-80 | MODIFIED | Install Caissons North | 02-Jun-2025 | 13-Jun-2025
Construction | CSA Exterior Work | Site | CLAYCO | #EE5A1C | M-C1 | CHI11-CSA-250 | MODIFIED | Install Utilities Final Tying | 06-Jun-2025 | 18-Jun-2025
Construction | CSA Exterior Work | Site | TBV | #5D1B0C | V1 | CHI11-CSA-280 | MODIFIED | Install Asphalt Curb | 16-Jun-2025 | 20-Jun-2025
Construction | CSA Exterior Work | Site | TBV | #5D1B0C | V2 | CHI11-CSA-50 | MODIFIED | Install Asphalt Binder | 21-Jun-2025 | 26-Jun-2025
Construction | CSA Exterior Work | COLO 3 | Scurto | #83CCEB | S3 | CHI11-CSA-110 | MODIFIED | Concrete Paving Around Generator South COLO3 Bldg to GEN | 23-May-2025 | 27-May-2025
Construction | CSA Exterior Work | COLO 3 | Scurto | #83CCEB | S3 | CHI11-CSA-100 | MODIFIED | Concrete Paving Around Generator North COLO3 Bld to GEN | 23-May-2025 | 27-May-2025
Construction | CSA Exterior Work | COLO 4 | Scurto | #83CCEB | S3 | CHI11-CSA-170 | MODIFIED | Concrete Paving Around Generator South COLO4 Bldg to GEN | 10-Jun-2025 | 16-Jun-2025
Construction | CSA Exterior Work | COLO 4 | Scurto | #83CCEB | S3 | CHI11-CSA-190 | MODIFIED | Concrete Paving Around Generator North COLO4 Bld to GEN | 12-Jun-2025 | 18-Jun-2025
Construction | CSA Exterior Work | COLO 5 | Scurto | #83CCEB | S3 | CHI11-CSA-180 | MODIFIED | Concrete Paving Around Generator South COLO5 Bldg to GEN | 12-Jul-2025 | 17-Jul-2025
Construction | CSA Exterior Work | COLO 5 | Scurto | #83CCEB | S3 | CHI11-CSA-200 | MODIFIED | Concrete Paving Around Generator North COLO5 Bldg to GEN | 12-Jul-2025 | 17-Jul-2025
Construction | CSA Exterior Work | COLO 5 | Scurto | #83CCEB | S3 | CHI11-CSA-230 | MODIFIED | Concrete Paving Around Generator North COLO5 GEN to Screenwall | 23-Jul-2025 | 29-Jul-2025
Construction | CSA Exterior Work | COLO 5 | Scurto | #83CCEB | S3 | CHI11-CSA-240 | MODIFIED | Concrete Paving Around Generator South COLO5 GEN to Screenwall | 30-Jul-2025 | 04-Aug-2025
Electrical Yard | Fiber | COLO 4 Cell 1 | GIBSON | #FFF9B1 | EE54 | CHI11-TELECOM-35 | MODIFIED | C04/01 Term GPC+UPM Fiber | 06-Jun-2025 | 06-Jun-2025
Electrical Yard | Fiber | COLO 4 Cell 1 | GIBSON | #FFF9B1 | EE55 | CHI11-TELECOM-36 | MODIFIED | C04/01 Test GPC+UPM Fiber | 07-Jun-2025 | 07-Jun-2025
Electrical Yard | Fiber | COLO 4 Cell 2 | GIBSON | #FFF9B1 | EE55 | CHI11-TELECOM-39 | MODIFIED | C04/02 Test GPC+UPM Fiber | 06-Jun-2025 | 07-Jun-2025
Construction | Electrical Yard | Admin/ COLO 3 | CLAYCO | #EE5A1C | M-C | CHI11-03-C&S-45 | MODIFIED | Admin/C03- Weather Days 9/15 | 06-Jun-2025 | 17-Jun-2025
Construction | Electrical Yard | COLO 5 | GIBSON | #FFF9B1 | EE26 | CHI11-05-YARD-30 | MODIFIED | C05/Yard- MV Cable Pulling & Terminating | 20-May-2025 | 11-Jul-2025
Construction | Electrical Yard | COLO 5 | GIBSON | #FFF9B1 | EE26 | CHI11-05-YARD-40 | MODIFIED | C05/Yard- MV Cable Pulling & Terminating | 06-Jun-2025 | 11-Jul-2025
Construction | Electrical Yard | COLO 5 | GIBSON | #FFF9B1 | EE26 | CHI11-05-YARD-70 | MODIFIED | C05/Yard- MV Cable Pulling & Terminating | 06-Jun-2025 | 18-Jul-2025
Construction | Electrical Yard | COLO 5 | GIBSON | #FFF9B1 | EE26 | CHI11-05-YARD-60 | MODIFIED | C05/Yard- MV Cable Pulling & Terminating | 12-Jun-2025 | 18-Jul-2025
Fitout | Admin Area | TELECOM | CECCO | #EF9E5B | T15 | CHI11-TELECOM-09 | MODIFIED | Admin - Install Switch/Patch | 01-May-2025 | 06-Jun-2025
Fitout | Admin | Electrical Room | GIBSON | #FFF9B1 | EE40 | CHI11-ADMIN-355 | MODIFIED | Admin/ Elec Rm- Pull Cables | 23-Apr-2025 | 12-Jun-2025
Fitout | Admin | Electrical Room | GIBSON | #FFF9B1 | EE47 | CHI11-ADMIN-460 | MODIFIED | Admin/ Elec Rm- Terminate Electrical / Mechanical Equipment | 25-Apr-2025 | 12-Jun-2025
Fitout | Admin | Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-ADMIN-485 | MODIFIED | Admin - Beneficial Rooms Pre-Energization Checks | 06-Jun-2025 | 07-Jun-2025
Fitout | Admin | Loading Dock | Continental - TBD | #D6F2FF | Y1 | CHI11-ADMIN-390 | MODIFIED | Admin/ Loading Dock- Paint | 30-May-2025 | 31-May-2025
Fitout | Admin | Loading Dock | Anning Johnson | #2490FF | D6 | CHI11-ADMIN-410 | MODIFIED | ADMIN- Install Doors | 06-Jun-2025 | 10-Jun-2025
Fitout | Admin | Loading Dock | GIBSON | #FFF9B1 | EE34 | CHI11-ADMIN-455 | MODIFIED | Admin/ Loading Dock- Pull Cables | 06-Jun-2025 | 09-Jun-2025
Fitout | Admin | Loading Dock | GIBSON | #FFF9B1 | EE25 | CHI11-ADMIN-425 | MODIFIED | ADMIN- Light Fixtures Installation | 11-Jun-2025 | 18-Jun-2025
Fitout | Admin | Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-ADMIN-490 | MODIFIED | ADMIN- Remaining Area Pre-Energization Checks | 17-Jun-2025 | 21-Jun-2025
FITOUT | COLO 3 | CELL 1 TELECOM | GIBSON | #FFF9B1 | EET1 | CHI11-03-01-TEL-10 | MODIFIED | C03/01 - WORK AREA OUTLETS | 16-May-2025 | 06-Jun-2025
FITOUT | COLO 3 | CELL 1 TELECOM | CECCO | #EF9E5B | T3 | CHI11-03-01-TEL-50 | MODIFIED | C03/01 - Fiber Runner | 16-May-2025 | 27-Jun-2025
FITOUT | COLO 3 | CELL 1 TELECOM | CECCO | #EF9E5B | T5 | CHI11-03-01-TEL-70 | MODIFIED | C03/01 - Production Fiber (PULL/DRESS) | 28-May-2025 | 06-Jun-2025
FITOUT | COLO 3 | CELL 1 TELECOM | CECCO | #EF9E5B | T6 | CHI11-03-01-TEL-80 | MODIFIED | C03/01 - Production Fiber (Plug/TEST) | 29-May-2025 | 12-Jun-2025
Fitout | COLO 3 | COLO 3 CELL 1 TELECOM EPMS | CECCO | #EF9E5B | T18 | CHI11-03-01-TEL-07 | MODIFIED | C03/01 - Install Switch/Patch | 02-May-2025 | 06-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE48 | CHI11-03-01-290 | MODIFIED | C03/01-Elec Rm- Terminate Electrical Equipments [Inside Electrical Room] (18) | 01-May-2025 | 07-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE31 | CHI11-03-01-285 | MODIFIED | C03/01-Mech Gallery- Pull & Terminate BAS Equipments | 04-Apr-2025 | 30-May-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE60 | CHI11-03-01-280 | MODIFIED | C03/01-Mech Gallery- Pull Cable to Mechanical Equipments [From Electrical Room] | 28-May-2025 | 29-May-2025
Fitout | COLO 3 | COLO 3 - CELL 1 Mechanical Gallery | Hill Mechanical | #C9DF56 | M5 | CHI11-03-01-300 | MODIFIED | C03/01-Mech Gallery- Terminate Mechanical Equipments | 30-May-2025 | 07-Jun-2025
Fitout | COLO 3 | COLO 3- CELL 1 Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-03-01-310 | MODIFIED | C03/01- Pre-Energization Checks | 28-Jun-2025 | 11-Jul-2025
FITOUT | COLO 3 | CELL 2 TELECOM | CECCO | #EF9E5B | T3 | CHI11-03-02-TEL-120 | MODIFIED | C03/02 - Fiber Runner | 16-May-2025 | 26-Jun-2025
FITOUT | COLO 3 | CELL 2 TELECOM | GIBSON | #FFF9B1 | EET1 | CHI11-03-02-TEL-110 | MODIFIED | C03/02 - WORK AREA OUTLETS | 22-May-2025 | 06-Jun-2025
FITOUT | COLO 3 | CELL 2 TELECOM | CECCO | #EF9E5B | T5 | CHI11-03-02-TEL-140 | MODIFIED | C03/02 - Production Fiber (PULL/DRESS) | 06-Jun-2025 | 10-Jun-2025
Fitout | COLO 3 | COLO 3 CELL 2 TELECOM EPMS | CECCO | #EF9E5B | T16 | CHI11-03-02-TEL-12 | MODIFIED | C03/02 - Install Switch/Patch | 06-Jun-2025 | 06-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Electrical Room | GIBSON | #FFF9B2 | EE48 | CHI11-03-02-300 | MODIFIED | C03/02-Elec Rm- Terminate Electrical Equipments [Inside Electrical Room] | 01-May-2025 | 16-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE31 | CHI11-03-02-270 | MODIFIED | C03/02-Mech Gallery- Pull & Terminate BAS Equipments | 10-Apr-2025 | 06-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Mechanical Gallery | Hill Mechanical | #C9DF56 | M5 | CHI11-03-02-290 | MODIFIED | C03/02-Mech Gallery- Terminate Mechanical Equipments | 30-May-2025 | 07-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 2 Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-03-02-280 | MODIFIED | C03/C02- Pre-Energization Checks | 27-Jun-2025 | 10-Jul-2025
FITOUT | COLO 3 | CELL 3 TELECOM | GIBSON | #FFF9B1 | EET1 | CHI11-03-03-TEL-200 | MODIFIED | C03/03 - WORK AREA OUTLETS | 16-May-2025 | 06-Jun-2025
FITOUT | COLO 3 | CELL 3 TELECOM | CECCO | #EF9E5B | T3 | CHI11-03-03-TEL-210 | MODIFIED | C03/03 - Fiber Runner | 20-May-2025 | 27-Jun-2025
FITOUT | COLO 3 | CELL 3 TELECOM | CECCO | #EF9E5B | T5 | CHI11-03-03-TEL-220 | MODIFIED | C03/03 - Production Fiber (PULL/DRESS) | 11-Jun-2025 | 18-Jun-2025
FITOUT | COLO 3 | CELL 3 TELECOM | CECCO | #EF9E5B | T6 | CHI11-03-03-TEL-250 | MODIFIED | C03/03 - Production Fiber (Plug/TEST) | 19-Jun-2025 | 02-Jul-2025
Fitout | COLO 3 | COLO 3 CELL 3 TELECOM EPMS | CECCO | #EF9E5B | T16 | CHI11-03-03-TEL-15 | MODIFIED | C03/03 - Install Switch/Patch | 06-May-2025 | 06-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE39 | CHI11-03-03-285 | MODIFIED | C03/03-DH- Pull Feeders from PDUs to Busways | 09-Apr-2025 | 22-May-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE50 | CHI11-03-03-310 | MODIFIED | C03/03-DH- Terminate PDUs | 30-May-2025 | 07-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE48 | CHI11-03-03-300 | MODIFIED | C03/03-Elec Rm- Terminate Electrical Equipments [Inside Electrical Room] | 05-May-2025 | 07-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE33 | CHI11-03-03-295 | MODIFIED | C03/03-Elec Rm- Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 15-May-2025 | 29-May-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE31 | CHI11-03-03-270 | MODIFIED | C03/03-Mech Gallery- Pull & Terminate BAS Equipments | 17-Apr-2025 | 30-May-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE60 | CHI11-03-03-255 | MODIFIED | C03/03-Mech Gallery- Pull Cable to Mechanical Equipments [From Electrical Room] | 23-May-2025 | 29-May-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Mechanical Gallery | Hill Mechanical | #C9DF56 | M5 | CHI11-03-03-290 | MODIFIED | C03/03-Mech Gallery- Terminate Mechanical Equipments | 30-May-2025 | 07-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 3 Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-03-03-280 | MODIFIED | C03/03- Pre-Energization Checks | 28-Jun-2025 | 11-Jul-2025
FITOUT | COLO 3 | CELL 4 TELECOM | GIBSON | #FFF9B1 | EET1 | CHI11-03-04-TEL-290 | MODIFIED | C03/04 - WORK AREA OUTLETS | 16-May-2025 | 06-Jun-2025
FITOUT | COLO 3 | CELL 4 TELECOM | CECCO | #EF9E5B | T3 | CHI11-03-04-TEL-300 | MODIFIED | C03/04 - Fiber Runner | 20-May-2025 | 27-Jun-2025
FITOUT | COLO 3 | CELL 4 TELECOM | CECCO | #EF9E5B | T5 | CHI11-03-04-TEL-340 | MODIFIED | C03/04 - Production Fiber (PULL/DRESS) | 19-Jun-2025 | 25-Jun-2025
FITOUT | COLO 3 | CELL 4 TELECOM | CECCO | #EF9E5B | T6 | CHI11-03-04-TEL-350 | MODIFIED | C03/04 - Production Fiber (Plug/TEST) | 26-Jun-2025 | 11-Jul-2025
Fitout | COLO 3 | COLO 3 CELL 4 TELECOM EPMS | CECCO | #EF9E5B | T16 | CHI11-03-04-TEL-33 | MODIFIED | C03/04 - Install Switch/Patch | 05-May-2025 | 06-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE50 | CHI11-03-04-310 | MODIFIED | C03/04-DH- Terminate PDUs | 19-May-2025 | 07-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE33 | CHI11-03-04-160 | MODIFIED | C03/04-Elec Rm- Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 15-May-2025 | 29-May-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE48 | CHI11-03-04-240 | MODIFIED | C03/04-Elec Rm- Terminate Electrical Equipments [Inside Electrical Room] | 15-May-2025 | 07-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE31 | CHI11-03-04-280 | MODIFIED | C03/04-Mech Gallery- Pull & Terminate BAS Equipments | 17-Apr-2025 | 30-May-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE60 | CHI11-03-04-265 | MODIFIED | C03/04-Mech Gallery- Pull Cable to Mechanical Equipments [From Electrical Room] | 23-May-2025 | 29-May-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Mechanical Gallery | Hill Mechanical | #C9DF56 | M5 | CHI11-03-04-300 | MODIFIED | C03/04-Mech Gallery- Terminate Mechanical Equipments | 30-May-2025 | 07-Jun-2025
Fitout | COLO 3 | COLO 3 - CELL 4 Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-03-04-290 | MODIFIED | C03/04- Pre-Energization Checks | 28-Jun-2025 | 11-Jul-2025
FITOUT | COLO 4 | CELL 1 TELECOM | CECCO | #EF9E5B | T7 | CHI11-04-01-TEL-440 | MODIFIED | C04/01 - OOB (out of bands) | 06-Jun-2025 | 09-Jun-2025
FITOUT | COLO 4 | CELL 1 TELECOM | CECCO | #EF9E5B | T2 | CHI11-04-01-TEL-410 | MODIFIED | C04/01 - MOR Cabinets | 06-Jun-2025 | 09-Jun-2025
FITOUT | COLO 4 | CELL 1 TELECOM | CECCO | #EF9E5B | T5 | CHI11-04-01-TEL-390 | MODIFIED | C04/01 - Production Fiber (PULL/DRESS) | 06-Jun-2025 | 12-Jun-2025
FITOUT | COLO 4 | CELL 1 TELECOM | GIBSON | #FFF9B1 | EET1 | CHI11-04-01-TEL-420 | MODIFIED | C04/01 - WORK AREA OUTLETS | 10-Jun-2025 | 17-Jun-2025
FITOUT | COLO 4 | CELL 1 TELECOM | CECCO | #EF9E5B | T3 | CHI11-04-01-TEL-430 | MODIFIED | C04/01 - Fiber Runner | 10-Jun-2025 | 16-Jun-2025
Fitout | COLO 4 | COLO 4 CELL 1 TELECOM EPMS | CECCO | #EF9E5B | T19 | CHI11-04-01-TEL-56 | MODIFIED | C04/01 - Test Result Review/Submittal | 30-May-2025 | 05-Jun-2025
Fitout | COLO 4 | COLO 4 CELL 1 TELECOM EPMS | CECCO | #EF9E5B | T18 | CHI11-04-01-TEL-55 | MODIFIED | C04/01 - Install Switch/Patch | 06-Jun-2025 | 09-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE48 | CHI11-04-01-285 | MODIFIED | C04/01-Elec Rm- Terminate Electrical Equipments [Inside Electrical Room] | 06-Jun-2025 | 28-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE31 | CHI11-04-01-275 | MODIFIED | C04/01-Mech Gallery- Pull & Terminate BAS Equipments | 17-Apr-2025 | 21-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE60 | CHI11-04-01-260 | MODIFIED | C04/01-Mech Gallery- Pull Cable to Mechanical Equipments [From Electrical Room] | 19-Jun-2025 | 27-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Mechanical Gallery | Hill Mechanical | #C9DF56 | M5 | CHI11-04-01-305 | MODIFIED | C04/01-Mech Gallery- Terminate Mechanical Equipments | 21-Jun-2025 | 08-Jul-2025
Fitout | COLO 4 | COLO 4 - CELL 1 Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-04-01-295 | MODIFIED | C04/01- Pre-Energization Checks | 09-Jul-2025 | 19-Jul-2025
FITOUT | COLO 4 | CELL 2 TELECOM | CECCO | #EF9E5B | T7 | CHI11-04-02-TEL-490 | MODIFIED | C04/02 - OOB (out of bands) | 06-Jun-2025 | 12-Jun-2025
FITOUT | COLO 4 | CELL 2 TELECOM | CECCO | #EF9E5B | T2 | CHI11-04-02-TEL-460 | MODIFIED | C04/02 - MOR Cabinets | 06-Jun-2025 | 09-Jun-2025
FITOUT | COLO 4 | CELL 2 TELECOM | CECCO | #EF9E5B | T3 | CHI11-04-02-TEL-480 | MODIFIED | C04/02 - Fiber Runner | 10-Jun-2025 | 16-Jun-2025
FITOUT | COLO 4 | CELL 2 TELECOM | GIBSON | #FFF9B1 | EET1 | CHI11-04-02-TEL-470 | MODIFIED | C04/02 - WORK AREA OUTLETS | 13-Jun-2025 | 20-Jun-2025
FITOUT | COLO 4 | CELL 2 TELECOM | CECCO | #EF9E5B | T5 | CHI11-04-02-TEL-500 | MODIFIED | C04/02 - Production Fiber (PULL/DRESS) | 13-Jun-2025 | 20-Jun-2025
Fitout | COLO 4 | COLO 4 CELL 2 TELECOM EPMS | CECCO | #EF9E5B | T17 | CHI11-04-02-TEL-522 | MODIFIED | C04/02 - Test EPMS Copper | 29-May-2025 | 29-May-2025
Fitout | COLO 4 | COLO 4 CELL 2 TELECOM EPMS | CECCO | #EF9E5B | T19 | CHI11-04-02-TEL-523 | MODIFIED | C04/02 - Test Result Review/Submittal | 06-Jun-2025 | 12-Jun-2025
Fitout | COLO 4 | COLO 4 CELL 2 TELECOM EPMS | CECCO | #EF9E5B | T18 | CHI11-04-02-TEL-524 | MODIFIED | C04/02 - Install Switch/Patch | 13-Jun-2025 | 20-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE48 | CHI11-04-02-300 | MODIFIED | C04/02-Elec Rm- Terminate Electrical Equipments [Inside Electrical Room] | 21-Jun-2025 | 28-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE31 | CHI11-04-02-270 | MODIFIED | C04/02-Mech Gallery- Pull & Terminate BAS Equipments | 17-Apr-2025 | 21-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE60 | CHI11-04-02-255 | MODIFIED | C04/02-Mech Gallery- Pull Cable to Mechanical Equipments [From Electrical Room] | 19-Jun-2025 | 27-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Mechanical Gallery | Hill Mechanical | #C9DF56 | M5 | CHI11-04-02-295 | MODIFIED | C04/02-Mech Gallery- Terminate Mechanical Equipments | 28-Jun-2025 | 08-Jul-2025
Fitout | COLO 4 | COLO 4 - CELL 2 Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-04-02-280 | MODIFIED | C04/02- Pre-Energization Checks | 25-Jun-2025 | 08-Jul-2025
FITOUT | COLO 4 | CELL 3 TELECOM | CECCO | #EF9E5B | T7 | CHI11-04-03-TEL-590 | MODIFIED | C04/03 - OOB (out of bands) | 28-May-2025 | 10-Jun-2025
FITOUT | COLO 4 | CELL 3 TELECOM | CECCO | #EF9E5B | T2 | CHI11-04-03-TEL-560 | MODIFIED | C04/03 - MOR Cabinets | 06-Jun-2025 | 09-Jun-2025
FITOUT | COLO 4 | CELL 3 TELECOM | CECCO | #EF9E5B | T5 | CHI11-04-03-TEL-550 | MODIFIED | C04/03 - Production Fiber (PULL/DRESS) | 06-Jun-2025 | 12-Jun-2025
FITOUT | COLO 4 | CELL 3 TELECOM | CECCO | #EF9E5B | T3 | CHI11-04-03-TEL-580 | MODIFIED | C04/03 - Fiber Runner | 10-Jun-2025 | 16-Jun-2025
FITOUT | COLO 4 | CELL 3 TELECOM | GIBSON | #FFF9B1 | EET1 | CHI11-04-03-TEL-570 | MODIFIED | C04/03 - WORK AREA OUTLETS | 11-Jun-2025 | 18-Jun-2025
Fitout | COLO 4 | COLO 4 CELL 3 TELECOM EPMS | CECCO | #EF9E5B | T16 | CHI11-04-03-TEL-62 | MODIFIED | C04/03 - Terminate EPMS Copper | 28-May-2025 | 10-Jun-2025
Fitout | COLO 4 | COLO 4 CELL 3 TELECOM EPMS | CECCO | #EF9E5B | T17 | CHI11-04-03-TEL-63 | MODIFIED | C04/03 - Test EPMS Copper | 11-Jun-2025 | 12-Jun-2025
Fitout | COLO 4 | COLO 4 CELL 3 TELECOM EPMS | CECCO | #EF9E5B | T19 | CHI11-04-03-TEL-64 | MODIFIED | C04/03 - Test Result Review/Submittal | 13-Jun-2025 | 13-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE8 | CHI11-04-03-265 | MODIFIED | C04/03-DH- Connect Perimeter Cable Trays to HAC Cable Trays | 30-May-2025 | 02-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE16 | CHI11-04-03-275 | MODIFIED | C04/03-DH- Install Conduits PDU to Cable Trays | 03-Jun-2025 | 05-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE39 | CHI11-04-03-285 | MODIFIED | C04/03-DH- Pull Feeders from PDUs to Busways | 23-Jun-2025 | 27-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE50 | CHI11-04-03-310 | MODIFIED | C04/03-DH- Terminate PDUs | 30-Jun-2025 | 03-Jul-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE48 | CHI11-04-03-300 | MODIFIED | C04/03-Elec Rm- Terminate Electrical Equipments [Inside Electrical Room] | 18-Jun-2025 | 07-Jul-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE38 | CHI11-04-03-305 | MODIFIED | C04/03-Elec Rm- Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 23-Jun-2025 | 28-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE31 | CHI11-04-03-270 | MODIFIED | C04/03-Mech Gallery- - Pull & Terminate BAS Equipments | 24-Apr-2025 | 21-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE60 | CHI11-04-03-255 | MODIFIED | C04/03-Mech Gallery- - Pull Cable to Mechanical Equipments [From Electrical Room] | 25-Jun-2025 | 28-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Mechanical Gallery | Hill Mechanical | #C9DF56 | M5 | CHI11-04-03-290 | MODIFIED | C04/03-Mech Gallery- - Terminate Mechanical Equipments | 30-Jun-2025 | 08-Jul-2025
Fitout | COLO 4 | COLO 4 - CELL 3 Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-04-03-280 | MODIFIED | C04/03- Pre-Energization Checks | 07-Jul-2025 | 17-Jul-2025
FITOUT | COLO 4 | CELL 4 TELECOM | CECCO | #EF9E5B | T2 | CHI11-04-04-TEL-670 | MODIFIED | C04/04 - MOR Cabinets | 06-Jun-2025 | 09-Jun-2025
FITOUT | COLO 4 | CELL 4 TELECOM | CECCO | #EF9E5B | T3 | CHI11-04-04-TEL-680 | MODIFIED | C04/04 - Fiber Runner | 10-Jun-2025 | 16-Jun-2025
FITOUT | COLO 4 | CELL 4 TELECOM | CECCO | #EF9E5B | T7 | CHI11-04-04-TEL-660 | MODIFIED | C04/04 - OOB (out of bands) | 11-Jun-2025 | 18-Jun-2025
FITOUT | COLO 4 | CELL 4 TELECOM | CECCO | #EF9E5B | T5 | CHI11-04-04-TEL-700 | MODIFIED | C04/04 - Production Fiber (PULL/DRESS) | 13-Jun-2025 | 20-Jun-2025
FITOUT | COLO 4 | CELL 4 TELECOM | GIBSON | #FFF9B1 | EET1 | CHI11-04-04-TEL-640 | MODIFIED | C04/04 - WORK AREA OUTLETS | 19-Jun-2025 | 25-Jun-2025
FITOUT | COLO 4 | CELL 4 TELECOM | CECCO | #EF9E5B | T1 | CHI11-04-04-TEL-650 | MODIFIED | C04/04 - Pull EPMS Copper | 06-Jun-2025 | 10-Jun-2025
Fitout | COLO 4 | COLO 4 CELL 4 TELECOM EPMS | CECCO | #EF9E5B | T16 | CHI11-04-04-TEL-66 | MODIFIED | C04/03 - Terminate EPMS Copper | 11-Jun-2025 | 18-Jun-2025
Fitout | COLO 4 | COLO 4 CELL 4 TELECOM EPMS | CECCO | #EF9E5B | T17 | CHI11-04-04-TEL-67 | MODIFIED | C04/03 - Test EPMS Copper | 19-Jun-2025 | 20-Jun-2025
Fitout | COLO 4 | COLO 4 CELL 4 TELECOM EPMS | CECCO | #EF9E5B | T19 | CHI11-04-04-TEL-68 | MODIFIED | C04/03 - Test Result Review/Submittal | 21-Jun-2025 | 26-Jun-2025
Fitout | COLO 4 | COLO 4 CELL 4 TELECOM EPMS | CECCO | #EF9E5B | T18 | CHI11-04-04-TEL-69 | MODIFIED | C04/03 - Install Switch/Patch | 27-Jun-2025 | 02-Jul-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE20 | CHI11-04-04-180 | MODIFIED | C04/04-DH-Install Perimeter Cable Trays | 18-Apr-2025 | 06-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE8 | CHI11-04-04-265 | MODIFIED | C04/04-DH-Connect Perimeter Cable Trays to HAC Cable Trays | 30-May-2025 | 02-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE16 | CHI11-04-04-275 | MODIFIED | C04/04-DH-Install Conduits PDU to Cable Trays | 03-Jun-2025 | 03-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE39 | CHI11-04-04-285 | MODIFIED | C04/04-DH-Pull Feeders from PDUs to Busways | 23-Jun-2025 | 27-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Data Hall | GIBSON | #FFF9B1 | EE50 | CHI11-04-04-310 | MODIFIED | C04/04-DH-Terminate PDUs | 28-Jun-2025 | 03-Jul-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE48 | CHI11-04-04-300 | MODIFIED | C04/04-Elec Rm-Terminate Electrical Equipments [Inside Electrical Room] | 16-Jun-2025 | 03-Jul-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE38 | CHI11-04-04-305 | MODIFIED | C04/04-Elec Rm-Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 23-Jun-2025 | 27-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE31 | CHI11-04-04-270 | MODIFIED | C04/04-Mech Gallery-Pull & Terminate BAS Equipments | 24-Apr-2025 | 07-Jul-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE60 | CHI11-04-04-255 | MODIFIED | C04/04-Mech Gallery-Pull Cable to Mechanical Equipments [From Electrical Room] | 25-Jun-2025 | 28-Jun-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Mechanical Gallery | Hill Mechanical | #C9DF56 | M5 | CHI11-04-04-290 | MODIFIED | C04/04-Mech Gallery-Terminate Mechanical Equipments | 25-Jun-2025 | 08-Jul-2025
Fitout | COLO 4 | COLO 4 - CELL 4 Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-04-04-280 | MODIFIED | C04/04- Pre-Energization Checks | 09-Jul-2025 | 19-Jul-2025
FITOUT | COLO 5 | CELL 1 TELECOM | CECCO | #EF9E5B | T1 | CHI11-05-01-TEL-730 | MODIFIED | C05/01 - EPMS/BAS | 06-Jun-2025 | 12-Jun-2025
FITOUT | COLO 5 | CELL 1 TELECOM | CECCO | #EF9E5B | T2 | CHI11-05-01-TEL-740 | MODIFIED | C05/01 - MOR Cabinets | 06-Jun-2025 | 09-Jun-2025
Fitout | COLO 5 | COLO 5 CELL 1 TELECOM EPMS | GIBSON | #FFF9B1 | EE56 | CHI11-05-01-TEL-731 | MODIFIED | C05 - CEI Cabinet | 06-Jun-2025 | 06-Jun-2025
FITOUT | COLO 5 | CELL 1 TELECOM | CECCO | #EF9E5B | T3 | CHI11-05-01-TEL-760 | MODIFIED | C05/01 - Fiber Runner | 10-Jun-2025 | 16-Jun-2025
FITOUT | COLO 5 | CELL 1 TELECOM | CECCO | #EF9E5B | T7 | CHI11-05-01-TEL-800 | MODIFIED | C05/01 - OOB (out of bands) | 13-Jun-2025 | 20-Jun-2025
FITOUT | COLO 5 | CELL 1 TELECOM | GIBSON | #FFF9B1 | EET1 | CHI11-05-01-TEL-750 | MODIFIED | C05/01 - WORK AREA OUTLETS | 21-Jun-2025 | 27-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE42 | CHI11-05-01-255 | MODIFIED | C05/01-DH- Raise HACs | 29-May-2025 | 29-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE9 | CHI11-05-01-275 | MODIFIED | C05/01-DH- Detail HACs | 29-May-2025 | 29-May-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE20 | CHI11-05-01-180 | MODIFIED | C05/01-DH- Install Perimeter Cable Trays | 06-Jun-2025 | 10-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE8 | CHI11-05-01-280 | MODIFIED | C05/01-DH- Connect Perimeter Cable Trays to HAC Cable Trays | 06-Jun-2025 | 09-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE45 | CHI11-05-01-230 | MODIFIED | C05/01-DH- Set PDUs | 20-Jun-2025 | 23-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Data Hall | GIBSON | #FFF9B1 | EE16 | CHI11-05-01-290 | MODIFIED | C05/01-DH- Install Conduits PDU to Cable Trays | 24-Jun-2025 | 26-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Electrical Room | GIBSON | #FFF9B1 | EE43 | CHI11-05-01-145 | MODIFIED | C05/01-Elec Rm- Set Electrical Equipments | 12-May-2025 | 07-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE60 | CHI11-05-01-270 | MODIFIED | C05/01-Mech Gallery- Pull Cable to Mechanical Equipments [From Electrical Room] | 07-Jul-2025 | 19-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | GIBSON | #FFF9B1 | EE31 | CHI11-05-01-285 | MODIFIED | C05/01-Mech Gallery- Pull & Terminate BAS Equipments | 14-Jul-2025 | 19-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Mechanical Gallery | Hill Mechanical | #C9DF56 | M5 | CHI11-05-01-305 | MODIFIED | C05/01-Mech Gallery- Terminate Mechanical Equipments | 21-Jul-2025 | 12-Aug-2025
Fitout | COLO 5 | COLO 5 - CELL 1 Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-05-01-295 | MODIFIED | C05/01- Pre-Energization Checks | 01-Aug-2025 | 12-Aug-2025
FITOUT | COLO 5 | CELL 2 TELECOM | CECCO | #EF9E5B | T2 | CHI11-05-02-TEL-820 | MODIFIED | C05/02 - MOR Cabinets | 11-Jun-2025 | 13-Jun-2025
FITOUT | COLO 5 | CELL 2 TELECOM | CECCO | #EF9E5B | T1 | CHI11-05-02-TEL-860 | MODIFIED | C05/02 - EPMS/BAS | 13-Jun-2025 | 20-Jun-2025
FITOUT | COLO 5 | CELL 2 TELECOM | CECCO | #EF9E5B | T3 | CHI11-05-02-TEL-840 | MODIFIED | C05/02 - Fiber Runner | 16-Jun-2025 | 20-Jun-2025
FITOUT | COLO 5 | CELL 2 TELECOM | CECCO | #EF9E5B | T7 | CHI11-05-02-TEL-850 | MODIFIED | C05/02 - OOB (out of bands) | 21-Jun-2025 | 27-Jun-2025
FITOUT | COLO 5 | CELL 2 TELECOM | CECCO | #EF9E5B | T5 | CHI11-05-02-TEL-890 | MODIFIED | C05/02 - Production Fiber (PULL/DRESS) | 24-Jun-2025 | 30-Jun-2025
FITOUT | COLO 5 | CELL 2 TELECOM | GIBSON | #FFF9B1 | EET1 | CHI11-05-02-TEL-830 | MODIFIED | C05/02 - WORK AREA OUTLETS | 28-Jun-2025 | 07-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE1 | CHI11-05-02-185 | MODIFIED | C05/02-DH- Assemble HACs [Qty - 5] | 30-May-2025 | 04-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE14 | CHI11-05-02-205 | MODIFIED | C05/02-DH- Install Busways on HAC Arms | 02-Jun-2025 | 06-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE20 | CHI11-05-02-180 | MODIFIED | C05/02-DH- Install Perimeter Cable Trays | 06-Jun-2025 | 10-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE42 | CHI11-05-02-250 | MODIFIED | C05/02-DH- Raise HACs | 07-Jun-2025 | 10-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE9 | CHI11-05-02-260 | MODIFIED | C05/02-DH- Detail HACs | 11-Jun-2025 | 16-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE8 | CHI11-05-02-265 | MODIFIED | C05/02-DH- Connect Perimeter Cable Trays to HAC Cable Trays | 11-Jun-2025 | 13-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE45 | CHI11-05-02-225 | MODIFIED | C05/02-DH- Set PDUs | 21-Jun-2025 | 24-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Data Hall | GIBSON | #FFF9B1 | EE16 | CHI11-05-02-280 | MODIFIED | C05/02-DH- Install Conduits PDU to Cable Trays | 25-Jun-2025 | 27-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE43 | CHI11-05-02-145 | MODIFIED | C05/02-Elec Rm- Set Electrical Equipments | 12-May-2025 | 07-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE15 | CHI11-05-02-120 | MODIFIED | C05/02-Elec Rm- Install Cable Trays / Pathways/Cable Bus | 06-Jun-2025 | 12-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Electrical Room | GIBSON | #FFF9B1 | EE48 | CHI11-05-02-300 | MODIFIED | C05/02-Elec Rm- Terminate Electrical Equipments [Inside Electrical Room] | 16-Jun-2025 | 25-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE31 | CHI11-05-02-275 | MODIFIED | C05/02-Mech Gallery- Pull & Terminate BAS Equipments | 06-Jun-2025 | 21-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | GIBSON | #FFF9B1 | EE60 | CHI11-05-02-255 | MODIFIED | C05/02-Mech Gallery- Pull Cable to Mechanical Equipments [From Electrical Room] | 07-Jul-2025 | 25-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Mechanical Gallery | Hill Mechanical | #C9DF56 | M5 | CHI11-05-02-295 | MODIFIED | C05/02-Mech Gallery- Terminate Mechanical Equipments | 28-Jul-2025 | 13-Aug-2025
Fitout | COLO 5 | COLO 5 - CELL 2 Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-05-02-285 | MODIFIED | C05/02- Pre-Energization Checks | 14-Aug-2025 | 26-Aug-2025
FITOUT | COLO 5 | CELL 3 TELECOM | CECCO | #EF9E5B | T2 | CHI11-05-03-TEL-940 | MODIFIED | C05/03 - MOR Cabinets | 20-Jun-2025 | 23-Jun-2025
FITOUT | COLO 5 | CELL 3 TELECOM | CECCO | #EF9E5B | T1 | CHI11-05-03-TEL-990 | MODIFIED | C05/03 - EPMS/BAS | 21-Jun-2025 | 27-Jun-2025
FITOUT | COLO 5 | CELL 3 TELECOM | CECCO | #EF9E5B | T3 | CHI11-05-03-TEL-960 | MODIFIED | C05/03 - Fiber Runner | 24-Jun-2025 | 28-Jun-2025
FITOUT | COLO 5 | CELL 3 TELECOM | CECCO | #EF9E5B | T7 | CHI11-05-03-TEL-980 | MODIFIED | C05/03 - OOB (out of bands) | 28-Jun-2025 | 07-Jul-2025
FITOUT | COLO 5 | CELL 3 TELECOM | GIBSON | #FFF9B1 | EET1 | CHI11-05-03-TEL-950 | MODIFIED | C05/03 - WORK AREA OUTLETS | 08-Jul-2025 | 14-Jul-2025
FITOUT | COLO 5 | CELL 3 TELECOM | CECCO | #EF9E5B | T5 | CHI11-05-03-TEL-920 | MODIFIED | C05/03 - Production Fiber (PULL/DRESS) | 12-Jul-2025 | 18-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE20 | CHI11-05-03-180 | MODIFIED | C05/03-DH- Install Perimeter Cable Trays | 06-Jun-2025 | 10-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE1 | CHI11-05-03-185 | MODIFIED | C05/03-DH- Assemble HACs [Qty - 5] | 06-Jun-2025 | 11-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE14 | CHI11-05-03-205 | MODIFIED | C05/03-DH- Install Busways on HAC Arms | 09-Jun-2025 | 13-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE42 | CHI11-05-03-250 | MODIFIED | C05/03-DH- Raise HACs | 16-Jun-2025 | 19-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE9 | CHI11-05-03-260 | MODIFIED | C05/03-DH- Detail HACs | 20-Jun-2025 | 24-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE8 | CHI11-05-03-265 | MODIFIED | C05/03-DH- Connect Perimeter Cable Trays to HAC Cable Trays | 20-Jun-2025 | 23-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE45 | CHI11-05-03-225 | MODIFIED | C05/03-DH- Set PDUs | 23-Jun-2025 | 26-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Data Hall | GIBSON | #FFF9B1 | EE16 | CHI11-05-03-275 | MODIFIED | C05/03-DH- Install Conduits PDU to Cable Trays | 27-Jun-2025 | 30-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE15 | CHI11-05-03-120 | MODIFIED | C05/03-Elec Rm- Install Cable Trays / Pathways/Cable Bus | 23-May-2025 | 12-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Electrical Room | GIBSON | #FFF9B1 | EE43 | CHI11-05-03-145 | MODIFIED | C05/03-Elec Rm- Set Electrical Equipments | 05-Jun-2025 | 16-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE13 | CHI11-05-03-240 | MODIFIED | C05/03-Mech Gallery- Install BAS Equipments | 30-May-2025 | 05-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 3 Mechanical Gallery | GIBSON | #FFF9B1 | EE31 | CHI11-05-03-270 | MODIFIED | C05/03-Mech Gallery- Pull & Terminate BAS Equipments | 06-Jun-2025 | 21-Jun-2025
FITOUT | COLO 5 | CELL 4 TELECOM | CECCO | #EF9E5B | T1 | CHI11-05-04-TEL-970 | MODIFIED | C05/04 - EPMS/BAS | 28-Jun-2025 | 07-Jul-2025
FITOUT | COLO 5 | CELL 4 TELECOM | CECCO | #EF9E5B | T7 | CHI11-05-04-TEL-950 | MODIFIED | C05/04 - OOB (out of bands) | 08-Jul-2025 | 14-Jul-2025
FITOUT | COLO 5 | CELL 4 TELECOM | CECCO | #EF9E5B | T2 | CHI11-05-04-TEL-920 | MODIFIED | C05/04 - MOR Cabinets | 09-Jul-2025 | 11-Jul-2025
FITOUT | COLO 5 | CELL 4 TELECOM | CECCO | #EF9E5B | T3 | CHI11-05-04-TEL-940 | MODIFIED | C05/04 - Fiber Runner | 12-Jul-2025 | 17-Jul-2025
FITOUT | COLO 5 | CELL 4 TELECOM | GIBSON | #FFF9B1 | EET1 | CHI11-05-04-TEL-930 | MODIFIED | C05/04 - WORK AREA OUTLETS | 15-Jul-2025 | 21-Jul-2025
FITOUT | COLO 5 | CELL 4 TELECOM | CECCO | #EF9E5B | T5 | CHI11-05-04-TEL-960 | MODIFIED | C05/04 - Production Fiber (PULL/DRESS) | 19-Jul-2025 | 25-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | Anning Johnson | #2490FF | D4 | CHI11-05-04-170 | MODIFIED | C05/04-DH- Install Ceiling Grid | 05-May-2025 | 10-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | GIBSON | #FFF9B1 | EE10 | CHI11-05-04-90 | MODIFIED | C05/04-DH- Drop Cable Tray [Hanging Rods] | 21-May-2025 | 07-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | Cleaning | #FFC6FF | C1 | CHI11-05-04-165 | MODIFIED | C05/04-DH- General Cleaning | 09-Jun-2025 | 09-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | Anning Johnson | #2490FF | D21 | CHI11-05-04-215 | MODIFIED | C05/04-DH- Install Device Tiles | 11-Jun-2025 | 12-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | GIBSON | #FFF9B1 | EE20 | CHI11-05-04-180 | MODIFIED | C05/04-DH- Install Perimeter Cable Trays | 25-Jun-2025 | 27-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | GIBSON | #FFF9B1 | EE1 | CHI11-05-04-185 | MODIFIED | C05/04-DH- Assemble HACs [Qty - 5] | 25-Jun-2025 | 28-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | GIBSON | #FFF9B1 | EE14 | CHI11-05-04-205 | MODIFIED | C05/04-DH- Install Busways on HAC Arms | 27-Jun-2025 | 01-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | GIBSON | #FFF9B1 | EE42 | CHI11-05-04-250 | MODIFIED | C05/04-DH- Raise HACs | 02-Jul-2025 | 08-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | GIBSON | #FFF9B1 | EE45 | CHI11-05-04-225 | MODIFIED | C05/04-DH- Set PDUs | 02-Jul-2025 | 02-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | GIBSON | #FFF9B1 | EE9 | CHI11-05-04-260 | MODIFIED | C05/04-DH- Detail HACs | 09-Jul-2025 | 12-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | GIBSON | #FFF9B1 | EE8 | CHI11-05-04-265 | MODIFIED | C05/04-DH- Connect Perimeter Cable Trays to HAC Cable Trays | 09-Jul-2025 | 11-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | GIBSON | #FFF9B1 | EE16 | CHI11-05-04-275 | MODIFIED | C05/04-DH- Install Conduits PDU to Cable Trays | 12-Jul-2025 | 15-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | GIBSON | #FFF9B1 | EE39 | CHI11-05-04-290 | MODIFIED | C05/04-DH- Pull Feeders from PDUs to Busways | 12-Jul-2025 | 25-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Data Hall Fitout Activities | GIBSON | #FFF9B1 | EE50 | CHI11-05-04-310 | MODIFIED | C05/04-DH- Terminate PDUs | 28-Jul-2025 | 07-Aug-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE43 | CHI11-05-04-145 | MODIFIED | C05/04-Elec Rm- Set Electrical Equipments | 05-Jun-2025 | 18-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Electrical Room | GIBSON | #FFF9B1 | EE15 | CHI11-05-04-120 | MODIFIED | C05/04-Elec Rm- Install Cable Trays / Pathways/Cable Bus | 06-Jun-2025 | 18-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE31 | CHI11-05-04-270 | MODIFIED | C05/04-Mech Gallery- Pull & Terminate BAS Equipments | 06-Jun-2025 | 21-Jun-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | GIBSON | #FFF9B1 | EE60 | CHI11-05-04-255 | MODIFIED | C05/04-Mech Gallery- Pull Cable to Mechanical Equipments [From Electrical Room] | 10-Jul-2025 | 23-Jul-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Mechanical Gallery | Hill Mechanical | #C9DF56 | M5 | CHI11-05-04-295 | MODIFIED | C05/04-Mech Gallery- Terminate Mechanical Equipments | 24-Jul-2025 | 02-Aug-2025
Fitout | COLO 5 | COLO 5 - CELL 4 Pre-Energization Checks | GIBSON | #FFF9B1 | EE27 | CHI11-05-04-285 | MODIFIED | C05/04- Pre-Energization Checks | 29-Jul-2025 | 08-Aug-2025
Commissioning | Site | MVM-01 | MSFT | #3DCD3A | CX16 | CHI11-CX-14 | MODIFIED | Yellow Tag (MVM01) (Paper Work Complete in NEXUS) | 20-Jun-2025 | 20-Jun-2025
Commissioning | Site | MVM-01 | MSFT | #3DCD3A | CX19 | CHI11-CX-17 | MODIFIED | IR Scans (MVM01) | 23-Jun-2025 | 23-Jun-2025
Commissioning | Site | MVM-01 | CLAYCO | #EE5A1C | Y10 | CHI11-CX-18 | MODIFIED | L3 PFC (MVM01) | 24-Jun-2025 | 24-Jun-2025
Commissioning | Site | MVM-01 | MSFT | #3DCD3A | CX22 | CHI11-CX-445 | MODIFIED | Green Tag (MVM01) | 25-Jun-2025 | 25-Jun-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | CLAYCO | #EE5A1C | Y9 | CHI11-CX-32 | MODIFIED | L3 Startup (UMS01-LA01) | 23-May-2025 | 30-May-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | MSFT | #3DCD3A | CX20 | CHI11-CX-33 | MODIFIED | EPMS SAT (UMS01-LA01) | 06-Jun-2025 | 09-Jun-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | MSFT | #3DCD3A | CX19 | CHI11-CX-28 | MODIFIED | IR Scans (UMS01-LA01) | 16-Jun-2025 | 16-Jun-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | CLAYCO | #EE5A1C | Y10 | CHI11-CX-29 | MODIFIED | L3 PFC (UMS01-LA01) | 17-Jun-2025 | 18-Jun-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | MSFT | #3DCD3A | CX22 | CHI11-CX-555 | MODIFIED | Green Tag (UMS01-LA01) | 19-Jun-2025 | 21-Jun-2025
Commissioning | Site | UMS-01 & UMS01-LA01 | MSFT | #3DCD3A | CX16 | CHI11-CX-26 | MODIFIED | Yellow Tag (UMS01-LA01) (Paper Work Complete in NEXUS) | 20-Jun-2025 | 20-Jun-2025
Commissioning | Site | UMS-02 & UMS02-LA02 | MSFT | #3DCD3A | CX7 | A2760 | MODIFIED | MEP Test/Pre Startup Installer (UMS01-LA02) | 16-Jun-2025 | 27-Jun-2025
Commissioning | Site | UMS-02 & UMS02-LA02 | MSFT | #3DCD3A | CX8 | A2770 | MODIFIED | Pre Startup Vendor (UMS02-LA02) | 30-Jun-2025 | 07-Jul-2025
Commissioning | Site | UMS-02 & UMS02-LA02 | MSFT | #3DCD3A | CX9 | A2780 | MODIFIED | Control Checks (UMS02-LA02) | 02-Jul-2025 | 07-Jul-2025
Commissioning | Site | UMS-02 & UMS02-LA02 | MSFT | #3DCD3A | CX10 | A2790 | MODIFIED | FOD Clean (UMS02-LA02) | 08-Jul-2025 | 08-Jul-2025
Commissioning | Site | UMS-02 & UMS02-LA02 | CLAYCO | #EE5A1C | Y11 | A2800 | MODIFIED | L2 QA/QC FOD (UMS02-LA02) | 09-Jul-2025 | 10-Jul-2025
Commissioning | Site | UMS-02 & UMS02-LA02 | MSFT | #3DCD3A | CX12 | A2810 | MODIFIED | IVC (UMS02-LA02) | 11-Jul-2025 | 14-Jul-2025
Commissioning | Site | UMS-02 & UMS02-LA02 | MSFT | #3DCD3A | CX16 | A2820 | MODIFIED | Yellow Tag (UMS02-LA02) | 15-Jul-2025 | 16-Jul-2025
Commissioning | Site | UMS-02 & UMS02-LA02 | MSFT | #3DCD3A | CX17 | A2830 | MODIFIED | Energization (UMS02-LA02) | 17-Jul-2025 | 17-Jul-2025
Commissioning | Site | UMS-02 & UMS02-LA02 | CLAYCO | #EE5A1C | Y9 | A2840 | MODIFIED | L3 Startup (UMS02-LA02) | 18-Jul-2025 | 21-Jul-2025
Commissioning | Site | UMS-02 & UMS02-LA02 | MSFT | #3DCD3A | CX19 | A2850 | MODIFIED | IR Scans (UMS02-LA02) | 22-Jul-2025 | 22-Jul-2025
Commissioning | Site | UMS-02 & UMS02-LA02 | MSFT | #3DCD3A | CX20 | A2860 | MODIFIED | EPMS SAT (UMS02-LA02) | 22-Jul-2025 | 24-Jul-2025
Commissioning | Site | UMS-02 & UMS02-LA02 | CLAYCO | #EE5A1C | Y10 | A2870 | MODIFIED | L3 PFC (UMS02-LA02) | 25-Jul-2025 | 28-Jul-2025
Commissioning | Site | UMS-02 & UMS02-LA02 | MSFT | #3DCD3A | CX22 | A2880 | MODIFIED | Green Tag (UMS02-LA02) | 29-Jul-2025 | 31-Jul-2025
Commissioning | Admin | ADMIN-XFM01 | MSFT | #3DCD3A | CX16 | CX4420 | MODIFIED | Yellow Tag (ADMIN-XFM01) | 23-May-2025 | 06-Jun-2025
Commissioning | Admin | ADMIN-XFM01 | MSFT | #3DCD3A | CX17 | CX4430 | MODIFIED | Energization (ADMIN-XFM01) | 11-Jun-2025 | 11-Jun-2025
Commissioning | Admin | ADMIN-XFM01 | CLAYCO | #EE5A1C | Y9 | CX4440 | MODIFIED | L3 Startup (ADMIN-XFM01) | 12-Jun-2025 | 12-Jun-2025
Commissioning | Admin | ADMIN-XFM01 | MSFT | #3DCD3A | CX19 | CX4450 | MODIFIED | IR Scans (ADMIN-XFM01) | 13-Jun-2025 | 13-Jun-2025
Commissioning | Admin | ADMIN-XFM01 | MSFT | #3DCD3A | CX20 | CX4460 | MODIFIED | EPMS SAT (ADMIN-XFM01) | 13-Jun-2025 | 13-Jun-2025
Commissioning | Admin | ADMIN-XFM01 | CLAYCO | #EE5A1C | Y10 | CX4470 | MODIFIED | L3 PFC (ADMIN-XFM01) | 16-Jun-2025 | 17-Jun-2025
Commissioning | Admin | ADMIN-XFM01 | MSFT | #3DCD3A | CX22 | CX4480 | MODIFIED | Green Tag (ADMIN-XFM01) | 18-Jun-2025 | 18-Jun-2025
Commissioning | Admin | ADMIN-PNL04 | MSFT | #3DCD3A | CX10 | CX4520 | MODIFIED | FOD Clean (ADMIN-PNL04) | 09-Jun-2025 | 10-Jun-2025
Commissioning | Admin | ADMIN-PNL04 | CLAYCO | #EE5A1C | Y11 | CX4530 | MODIFIED | L2 QA/QC FOD (ADMIN-PNL04) | 11-Jun-2025 | 12-Jun-2025
Commissioning | Admin | ADMIN-PNL04 | MSFT | #3DCD3A | CX12 | CX4540 | MODIFIED | IVC (ADMIN-PNL04) | 13-Jun-2025 | 16-Jun-2025
Commissioning | Admin | ADMIN-PNL04 | MSFT | #3DCD3A | CX16 | CX4550 | MODIFIED | Yellow Tag (ADMIN-PNL04) | 17-Jun-2025 | 18-Jun-2025
Commissioning | Admin | ADMIN-PNL04 | MSFT | #3DCD3A | CX17 | CX4560 | MODIFIED | Energization (ADMIN-PNL04) | 18-Jun-2025 | 19-Jun-2025
Commissioning | Admin | ADMIN-PNL04 | MSFT | #3DCD3A | CX19 | CX4580 | MODIFIED | IR Scans (ADMIN-PNL04) | 20-Jun-2025 | 25-Jun-2025
Commissioning | Admin | ADMIN-PNL04 | CLAYCO | #EE5A1C | Y9 | CX4570 | MODIFIED | L3 Startup (ADMIN-PNL04) | 20-Jun-2025 | 25-Jun-2025
Commissioning | Admin | ADMIN-PNL04 | CLAYCO | #EE5A1C | Y10 | CX4600 | MODIFIED | L3 PFC (ADMIN-PNL04) | 26-Jun-2025 | 27-Jun-2025
Commissioning | Admin | ADMIN-PNL04 | MSFT | #3DCD3A | CX22 | CX4610 | MODIFIED | Green Tag (ADMIN-PNL04) | 28-Jun-2025 | 30-Jun-2025
Commissioning | Admin | ADMIN-MSB01 | MSFT | #3DCD3A | CX7 | CX4880 | MODIFIED | MEP Test/Pre Startup Installer (ADMIN-MSB01) | 31-Mar-2025 | 26-May-2025
Commissioning | Admin | ADMIN-MSB01 | MSFT | #3DCD3A | CX9 | CX4900 | MODIFIED | Control Checks (ADMIN-MSB01) | 02-Jun-2025 | 05-Jun-2025
Commissioning | Admin | ADMIN-MSB01 | MSFT | #3DCD3A | CX10 | CX4910 | MODIFIED | FOD Clean (ADMIN-MSB01) | 06-Jun-2025 | 07-Jun-2025
Commissioning | Admin | ADMIN-MSB01 | CLAYCO | #EE5A1C | Y11 | CX4920 | MODIFIED | L2 QA/QC FOD (ADMIN-MSB01) | 09-Jun-2025 | 10-Jun-2025
Commissioning | Admin | ADMIN-MSB01 | MSFT | #3DCD3A | CX12 | CX4930 | MODIFIED | IVC (ADMIN-MSB01) | 11-Jun-2025 | 12-Jun-2025
Commissioning | Admin | ADMIN-MSB01 | MSFT | #3DCD3A | CX16 | CX4940 | MODIFIED | Yellow Tag (ADMIN-MSB01) | 13-Jun-2025 | 16-Jun-2025
Commissioning | Admin | ADMIN-MSB01 | MSFT | #3DCD3A | CX17 | CX4950 | MODIFIED | Energization (ADMIN-MSB01) | 17-Jun-2025 | 17-Jun-2025
Commissioning | Admin | ADMIN-MSB01 | MSFT | #3DCD3A | CX19 | CX4970 | MODIFIED | IR Scans (ADMIN-MSB01) | 18-Jun-2025 | 19-Jun-2025
Commissioning | Admin | ADMIN-MSB01 | CLAYCO | #EE5A1C | Y9 | CX4960 | MODIFIED | L3 Startup (ADMIN-MSB01) | 18-Jun-2025 | 19-Jun-2025
Commissioning | Admin | ADMIN-MSB01 | MSFT | #3DCD3A | CX20 | CX4980 | MODIFIED | EPMS SAT (ADMIN-MSB01) | 20-Jun-2025 | 20-Jun-2025
Commissioning | Admin | ADMIN-MSB01 | CLAYCO | #EE5A1C | Y10 | CX4990 | MODIFIED | L3 PFC (ADMIN-MSB01) | 21-Jun-2025 | 24-Jun-2025
Commissioning | Admin | ADMIN-MSB01 | MSFT | #3DCD3A | CX22 | CX5000 | MODIFIED | Green Tag (ADMIN-MSB01) | 25-Jun-2025 | 25-Jun-2025
Commissioning | Admin | ADMIN-ATS (01-06) | MSFT | #3DCD3A | CX8 | CX4760 | MODIFIED | Pre Startup Vendor (ADMIN-ATS (01-06)) | 04-Apr-2025 | 04-Jun-2025
Commissioning | Admin | ADMIN-ATS (01-06) | MSFT | #3DCD3A | CX7 | CX4750 | MODIFIED | MEP Test/Pre Startup Installer (ADMIN-ATS (01-06)) | 04-Apr-2025 | 04-Jun-2025
Commissioning | Admin | ADMIN-ATS (01-06) | MSFT | #3DCD3A | CX10 | CX4770 | MODIFIED | FOD Clean (ADMIN-ATS (01-06)) | 07-Jun-2025 | 09-Jun-2025
Commissioning | Admin | ADMIN-ATS (01-06) | CLAYCO | #EE5A1C | Y11 | CX4780 | MODIFIED | L2 QA/QC FOD (ADMIN-ATS (01-06)) | 10-Jun-2025 | 11-Jun-2025
Commissioning | Admin | ADMIN-ATS (01-06) | MSFT | #3DCD3A | CX12 | CX4790 | MODIFIED | IVC (ADMIN-ATS (01-06)) | 12-Jun-2025 | 13-Jun-2025
Commissioning | Admin | ADMIN-ATS (01-06) | MSFT | #3DCD3A | CX16 | CX4800 | MODIFIED | Yellow Tag (ADMIN-ATS (01-06)) | 16-Jun-2025 | 17-Jun-2025
Commissioning | Admin | ADMIN-ATS (01-06) | MSFT | #3DCD3A | CX9 | CX4810 | MODIFIED | Control Checks (ADMIN-ATS (01-06)) | 19-Jun-2025 | 20-Jun-2025
Commissioning | Admin | ADMIN-ATS (01-06) | CLAYCO | #EE5A1C | Y9 | CX4840 | MODIFIED | L3 Startup (ADMIN-ATS (01-06)) | 23-Jun-2025 | 27-Jun-2025
Commissioning | Admin | ADMIN-ATS (01-06) | MSFT | #3DCD3A | CX20 | CX5130 | MODIFIED | EPMS SAT (ADMIN-ATS (01-06)) | 28-Jun-2025 | 03-Jul-2025
Commissioning | Admin | ADMIN-ATS (01-06) | CLAYCO | #EE5A1C | Y10 | CX4860 | MODIFIED | L3 PFC (ADMIN-ATS (01-06)) | 07-Jul-2025 | 08-Jul-2025
Commissioning | Admin | ADMIN-ATS (01-06) | MSFT | #3DCD3A | CX22 | CX4870 | MODIFIED | Green Tag (ADMIN-ATS (01-06)) | 09-Jul-2025 | 10-Jul-2025
Commissioning | Admin | Admin-UOP,UIP,UPS | MSFT | #3DCD3A | CX7 | CX5010 | MODIFIED | MEP Test/Pre Startup Installer (ADMIN-UOP,UIP,UPS) | 02-Apr-2025 | 30-May-2025
Commissioning | Admin | Admin-UOP,UIP,UPS | MSFT | #3DCD3A | CX8 | CX5020 | MODIFIED | Pre Startup Vendor (ADMIN-UOP,UIP,UPS) | 02-Jun-2025 | 04-Jun-2025
Commissioning | Admin | Admin-UOP,UIP,UPS | CLAYCO | #EE5A1C | Y11 | CX5040 | MODIFIED | L2 QA/QC FOD (ADMIN-UOP,UIP,UPS) | 07-Jun-2025 | 09-Jun-2025
Commissioning | Admin | Admin-UOP,UIP,UPS | MSFT | #3DCD3A | CX12 | CX5050 | MODIFIED | IVC (ADMIN-UOP,UIP,UPS) | 10-Jun-2025 | 11-Jun-2025
Commissioning | Admin | Admin-UOP,UIP,UPS | MSFT | #3DCD3A | CX16 | CX5060 | MODIFIED | Yellow Tag (ADMIN-UOP,UIP,UPS) | 12-Jun-2025 | 13-Jun-2025
Commissioning | Admin | Admin-UOP,UIP,UPS | MSFT | #3DCD3A | CX9 | CX5070 | MODIFIED | Control Checks (ADMIN-UOP,UIP,UPS) | 17-Jun-2025 | 17-Jun-2025
Commissioning | Admin | Admin-UOP,UIP,UPS | MSFT | #3DCD3A | CX17 | CX5080 | MODIFIED | Energization (ADMIN-UOP,UIP,UPS) | 21-Jun-2025 | 21-Jun-2025
Commissioning | Admin | Admin-UOP,UIP,UPS | CLAYCO | #EE5A1C | Y9 | CX5090 | MODIFIED | L3 Startup (ADMIN-UOP,UIP,UPS) | 23-Jun-2025 | 27-Jun-2025
Commissioning | Admin | Admin-UOP,UIP,UPS | MSFT | #3DCD3A | CX19 | CX5100 | MODIFIED | IR Scans (ADMIN-UOP,UIP,UPS) | 28-Jun-2025 | 30-Jun-2025
Commissioning | Admin | Admin-UOP,UIP,UPS | CLAYCO | #EE5A1C | Y10 | CX5110 | MODIFIED | L3 PFC (ADMIN-UOP,UIP,UPS) | 01-Jul-2025 | 02-Jul-2025
Commissioning | Admin | Admin-UOP,UIP,UPS | MSFT | #3DCD3A | CX22 | CX5120 | MODIFIED | Green Tag (ADMIN-UOP,UIP,UPS) | 03-Jul-2025 | 07-Jul-2025
Commissioning | COLO 3 | COLO3 & Admin UPM | MSFT | #3DCD3A | CX10 | A2920 | MODIFIED | FOD Clean (COLO3 and ADMIN UPM) | 12-May-2025 | 16-May-2025
Commissioning | COLO 3 | COLO3 & Admin UPM | CLAYCO | #EE5A1C | Y11 | A2930 | MODIFIED | L2 QA/QC FOD (COLO3 and ADMIN UPM) | 19-May-2025 | 20-May-2025
Commissioning | COLO 3 | COLO3 & Admin UPM | MSFT | #3DCD3A | CX12 | A2940 | MODIFIED | IVC (COLO3 and ADMIN UPM) | 19-May-2025 | 20-May-2025
Commissioning | COLO 3 | COLO3 & Admin UPM | MSFT | #3DCD3A | CX17 | A2960 | MODIFIED | Energization (COLO3 and ADMIN UPM) | 05-Jun-2025 | 05-Jun-2025
Commissioning | COLO 3 | COLO3 & Admin UPM | CLAYCO | #EE5A1C | Y9 | A2970 | MODIFIED | L3 Startup (COLO3 and ADMIN UPM) | 06-Jun-2025 | 09-Jun-2025
Commissioning | COLO 3 | COLO3 & Admin UPM | MSFT | #3DCD3A | CX19 | A2980 | MODIFIED | IR Scans (COLO3 and ADMIN UPM) | 10-Jun-2025 | 10-Jun-2025
Commissioning | COLO 3 | COLO3 & Admin UPM | MSFT | #3DCD3A | CX20 | A2990 | MODIFIED | EPMS SAT (COLO3 and ADMIN UPM) | 10-Jun-2025 | 12-Jun-2025
Commissioning | COLO 3 | COLO3 & Admin UPM | CLAYCO | #EE5A1C | Y10 | A3000 | MODIFIED | L3 PFC (COLO3 and ADMIN UPM) | 13-Jun-2025 | 16-Jun-2025
Commissioning | COLO 3 | COLO3 & Admin UPM | MSFT | #3DCD3A | CX22 | A3010 | MODIFIED | Green Tag (COLO3 and ADMIN UPM) | 17-Jun-2025 | 17-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-XFM01 | MSFT | #3DCD3A | CX9 | A3040 | MODIFIED | Control Checks (COLO3-CE1/CE2-XFM01) | 13-May-2025 | 20-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-XFM01 | MSFT | #3DCD3A | CX10 | A3050 | MODIFIED | FOD Clean (COLO3-CE1/CE2-XFM01) | 21-May-2025 | 21-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-XFM01 | CLAYCO | #EE5A1C | Y11 | A3060 | MODIFIED | L2 QA/QC FOD (COLO3-CE1/CE2-XFM01) | 22-May-2025 | 22-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-XFM01 | MSFT | #3DCD3A | CX12 | A3070 | MODIFIED | IVC (COLO3-CE1/CE2-XFM01) | 22-May-2025 | 23-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-XFM01 | MSFT | #3DCD3A | CX16 | A3080 | MODIFIED | Yellow Tag (COLO3-CE1/CE2-XFM01) | 27-May-2025 | 09-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-XFM01 | MSFT | #3DCD3A | CX17 | A3090 | MODIFIED | Energization (COLO3-CE1/CE2-XFM01) | 11-Jun-2025 | 11-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-XFM01 | CLAYCO | #EE5A1C | Y9 | A3100 | MODIFIED | L3 Startup (COLO3-CE1/CE2-XFM01) | 12-Jun-2025 | 17-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-XFM01 | MSFT | #3DCD3A | CX19 | A3110 | MODIFIED | IR Scans (COLO3-CE1/CE2-XFM01) | 18-Jun-2025 | 18-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-XFM01 | MSFT | #3DCD3A | CX20 | A3120 | MODIFIED | EPMS SAT (COLO3-CE1/CE2-XFM01) | 18-Jun-2025 | 19-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-XFM01 | CLAYCO | #EE5A1C | Y10 | A3130 | MODIFIED | L3 PFC (COLO3-CE1/CE2-XFM01) | 20-Jun-2025 | 21-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-XFM01 | MSFT | #3DCD3A | CX22 | A3140 | MODIFIED | Green Tag (COLO3-CE1/CE2-XFM01) | 23-Jun-2025 | 23-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | MSFT | #3DCD3A | CX9 | A3170 | MODIFIED | Control Checks (COLO3-CE3/CE4-XFM01) | 16-May-2025 | 20-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | MSFT | #3DCD3A | CX10 | A3180 | MODIFIED | FOD Clean (COLO3-CE3/CE4-XFM01) | 21-May-2025 | 21-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | CLAYCO | #EE5A1C | Y11 | A3190 | MODIFIED | L2 QA/QC FOD (COLO3-CE3/CE4-XFM01) | 22-May-2025 | 23-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | MSFT | #3DCD3A | CX12 | A3200 | MODIFIED | IVC (COLO3-CE3/CE4-XFM01) | 22-May-2025 | 23-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | MSFT | #3DCD3A | CX16 | A3210 | MODIFIED | Yellow Tag (COLO3-CE3/CE4-XFM01) | 27-May-2025 | 09-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | MSFT | #3DCD3A | CX17 | A3220 | MODIFIED | Energization (COLO3-CE3/CE4-XFM01) | 18-Jun-2025 | 18-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | CLAYCO | #EE5A1C | Y9 | A3230 | MODIFIED | L3 Startup (COLO3-CE3/CE4-XFM01) | 19-Jun-2025 | 23-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | MSFT | #3DCD3A | CX19 | A3240 | MODIFIED | IR Scans (COLO3-CE3/CE4-XFM01) | 24-Jun-2025 | 24-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | MSFT | #3DCD3A | CX20 | A3250 | MODIFIED | EPMS SAT (COLO3-CE3/CE4-XFM01) | 24-Jun-2025 | 25-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | CLAYCO | #EE5A1C | Y10 | A3260 | MODIFIED | L3 PFC (COLO3-CE3/CE4-XFM01) | 26-Jun-2025 | 27-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | MSFT | #3DCD3A | CX22 | A3270 | MODIFIED | Green Tag (COLO3-CE3/CE4-XFM01) | 28-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-PNL01 | MSFT | #3DCD3A | CX10 | CX1030 | MODIFIED | FOD Clean (COLO3-CE1/CE2-PNL02) | 10-Jun-2025 | 11-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-PNL01 | CLAYCO | #EE5A1C | Y11 | CX1040 | MODIFIED | L2 QA/QC FOD (COLO3-CE1/CE2-PNL02) | 12-Jun-2025 | 13-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-PNL01 | MSFT | #3DCD3A | CX12 | CX1050 | MODIFIED | IVC (COLO3-CE1/CE2-PNL02) | 16-Jun-2025 | 17-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-PNL01 | MSFT | #3DCD3A | CX16 | CX1060 | MODIFIED | Yellow Tag (COLO3-CE1/CE2-PNL02) | 18-Jun-2025 | 19-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-PNL01 | MSFT | #3DCD3A | CX17 | CX1070 | MODIFIED | Energization (COLO3-CE1/CE2-PNL02) | 20-Jun-2025 | 21-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-PNL01 | MSFT | #3DCD3A | CX19 | CX1090 | MODIFIED | IR Scans (COLO3-CE1/CE2-PNL02) | 23-Jun-2025 | 27-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-PNL01 | CLAYCO | #EE5A1C | Y9 | CX1080 | MODIFIED | L3 Startup (COLO3-CE1/CE2-PNL02) | 23-Jun-2025 | 27-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-PNL01 | CLAYCO | #EE5A1C | Y10 | CX1110 | MODIFIED | L3 PFC (COLO3-CE1/CE2-PNL02) | 28-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-PNL01 | MSFT | #3DCD3A | CX22 | CX1120 | MODIFIED | Green Tag (COLO3-CE1/CE2-PNL02) | 30-Jun-2025 | 30-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-PNL01 | MSFT | #3DCD3A | CX10 | CX1140 | MODIFIED | FOD Clean (COLO3-CE3/CE4-PNL02) | 11-Jun-2025 | 12-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-PNL01 | CLAYCO | #EE5A1C | Y11 | CX1150 | MODIFIED | L2 QA/QC FOD (COLO3-CE3/CE4-PNL02) | 13-Jun-2025 | 16-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-PNL01 | MSFT | #3DCD3A | CX12 | CX1160 | MODIFIED | IVC (COLO3-CE3/CE4-PNL02) | 17-Jun-2025 | 18-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-PNL01 | MSFT | #3DCD3A | CX16 | CX1170 | MODIFIED | Yellow Tag (COLO3-CE3/CE4-PNL02) | 19-Jun-2025 | 20-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-PNL01 | MSFT | #3DCD3A | CX17 | CX1180 | MODIFIED | Energization (COLO3-CE3/CE4-PNL02) | 23-Jun-2025 | 23-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-PNL01 | MSFT | #3DCD3A | CX19 | CX1200 | MODIFIED | IR Scans (COLO3-CE3/CE4-PNL02) | 24-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-PNL01 | CLAYCO | #EE5A1C | Y9 | CX1190 | MODIFIED | L3 Startup (COLO3-CE3/CE4-PNL02) | 24-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-PNL01 | CLAYCO | #EE5A1C | Y10 | CX1220 | MODIFIED | L3 PFC (COLO3-CE3/CE4-PNL02) | 30-Jun-2025 | 30-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX22 | CX1230 | MODIFIED | Green Tag (COLO3-CE3/CE4-PNL02) | 01-Jul-2025 | 01-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX7 | CX1240 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-CE1/CE2-MSB01 and TCP01) | 28-Mar-2025 | 16-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX8 | CX1350 | MODIFIED | Pre Startup Vendor (COLO3-CE1/CE2-MSB01 and TCP01) | 19-May-2025 | 21-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX9 | CX1360 | MODIFIED | Control Checks (COLO3-CE1/CE2-MSB01 and TCP01) | 28-May-2025 | 29-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX16 | CX1280 | MODIFIED | Yellow Tag (COLO3-CE1/CE2-MSB01 and TCP01) | 05-Jun-2025 | 12-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX10 | CX1250 | MODIFIED | FOD Clean (COLO3-CE1/CE2-MSB01 and TCP01) | 06-Jun-2025 | 06-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | CLAYCO | #EE5A1C | Y11 | CX1260 | MODIFIED | L2 QA/QC FOD (COLO3-CE1/CE2-MSB01 and TCP01) | 06-Jun-2025 | 09-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX12 | CX1270 | MODIFIED | IVC (COLO3-CE1/CE2-MSB01 and TCP01) | 10-Jun-2025 | 11-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX17 | CX1290 | MODIFIED | Energization (COLO3-CE1/CE2-MSB01 and TCP01) | 12-Jun-2025 | 13-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | CLAYCO | #EE5A1C | Y9 | CX1300 | MODIFIED | L3 Startup (COLO3-CE1/CE2-MSB01 and TCP01) | 16-Jun-2025 | 19-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX19 | CX1310 | MODIFIED | IR Scans (COLO3-CE1/CE2-MSB01 and TCP01) | 20-Jun-2025 | 20-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX20 | CX1320 | MODIFIED | EPMS SAT (COLO3-CE1/CE2-MSB01 and TCP01) | 20-Jun-2025 | 20-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | CLAYCO | #EE5A1C | Y11 | CX1330 | MODIFIED | L3 PFC (COLO3-CE1/CE2-MSB01 and TCP01) | 21-Jun-2025 | 21-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX22 | CX1340 | MODIFIED | Green Tag (COLO3-CE1/CE2-MSB01 and TCP01) | 23-Jun-2025 | 23-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX9 | CX1390 | MODIFIED | Control Checks (COLO3-CE3/CE4-MSB01 and TCP01) | 02-Jun-2025 | 04-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX10 | CX1400 | MODIFIED | FOD Clean (COLO3-CE3/CE4-MSB01 and TCP01) | 05-Jun-2025 | 06-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | CLAYCO | #EE5A1C | Y11 | CX1410 | MODIFIED | L2 QA/QC FOD (COLO3-CE3/CE4-MSB01 and TCP01) | 06-Jun-2025 | 09-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX12 | CX1420 | MODIFIED | IVC (COLO3-CE3/CE4-MSB01 and TCP01) | 10-Jun-2025 | 11-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX17 | CX1440 | MODIFIED | Energization (COLO3-CE3/CE4-MSB01 and TCP01) | 19-Jun-2025 | 20-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | CLAYCO | #EE5A1C | Y9 | CX1450 | MODIFIED | L3 Startup (COLO3-CE3/CE4-MSB01 and TCP01) | 21-Jun-2025 | 25-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX8 | CX1510 | MODIFIED | Pre Startup Vendor (COLO3-CE1/CE2-ADP01) | 06-Jun-2025 | 07-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX10 | CX1530 | MODIFIED | FOD Clean (COLO3-CE1/CE2-ADP01) | 09-Jun-2025 | 10-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ADP01 | CLAYCO | #EE5A1C | Y11 | CX1540 | MODIFIED | L2 QA/QC FOD (COLO3-CE1/CE2-ADP01) | 11-Jun-2025 | 12-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX12 | CX1550 | MODIFIED | IVC (COLO3-CE1/CE2-ADP01) | 13-Jun-2025 | 16-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX16 | CX1560 | MODIFIED | Yellow Tag (COLO3-CE1/CE2-ADP01) | 17-Jun-2025 | 18-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX9 | CX1630 | MODIFIED | Control Checks (COLO3-CE1/CE2-ADP01) | 19-Jun-2025 | 19-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX17 | CX1570 | MODIFIED | Energization (COLO3-CE1/CE2-ADP01) | 20-Jun-2025 | 21-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ADP01 | CLAYCO | #EE5A1C | Y9 | CX1580 | MODIFIED | L3 Startup (COLO3-CE1/CE2-ADP01) | 23-Jun-2025 | 24-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX19 | CX1590 | MODIFIED | IR Scans (COLO3-CE1/CE2-ADP01) | 25-Jun-2025 | 25-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX20 | CX1600 | MODIFIED | EPMS SAT (COLO3-CE1/CE2-ADP01) | 25-Jun-2025 | 25-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ADP01 | CLAYCO | #EE5A1C | Y10 | CX1610 | MODIFIED | L3 PFC (COLO3-CE1/CE2-ADP01) | 26-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX22 | CX1620 | MODIFIED | Green Tag (COLO3-CE1/CE2-ADP01) | 30-Jun-2025 | 02-Jul-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX7 | CX1640 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-CE3/CE4-ADP01) | 28-Mar-2025 | 06-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX8 | CX1650 | MODIFIED | Pre Startup Vendor (COLO3-CE3/CE4-ADP01) | 02-Jun-2025 | 09-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX10 | CX1660 | MODIFIED | FOD Clean (COLO3-CE3/CE4-ADP01) | 09-Jun-2025 | 10-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-ADP01 | CLAYCO | #EE5A1C | Y11 | CX1670 | MODIFIED | L2 QA/QC FOD (COLO3-CE3/CE4-ADP01) | 11-Jun-2025 | 13-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX12 | CX1680 | MODIFIED | IVC (COLO3-CE3/CE4-ADP01) | 16-Jun-2025 | 17-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX16 | CX1690 | MODIFIED | Yellow Tag (COLO3-CE3/CE4-ADP01) | 18-Jun-2025 | 19-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX9 | CX1700 | MODIFIED | Control Checks (COLO3-CE3/CE4-ADP01) | 21-Jun-2025 | 21-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX17 | CX1710 | MODIFIED | Energization (COLO3-CE3/CE4-ADP01) | 23-Jun-2025 | 24-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-ADP01 | CLAYCO | #EE5A1C | Y9 | CX1720 | MODIFIED | L3 Startup (COLO3-CE3/CE4-ADP01) | 26-Jun-2025 | 27-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX19 | CX1730 | MODIFIED | IR Scans (COLO3-CE3/CE4-ADP01) | 28-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX20 | CX1740 | MODIFIED | EPMS SAT (COLO3-CE3/CE4-ADP01) | 28-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-ADP01 | CLAYCO | #EE5A1C | Y10 | CX1750 | MODIFIED | L3 PFC (COLO3-CE3/CE4-ADP01) | 30-Jun-2025 | 03-Jul-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX22 | CX1760 | MODIFIED | Green Tag (COLO3-CE3/CE4-ADP01) | 07-Jul-2025 | 09-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX7 | CX1770 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-CE1/CE2(UPS01-02)) | 03-Apr-2025 | 28-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX8 | CX1780 | MODIFIED | Pre Startup Vendor (COLO3-CE1/CE2(UPS01-02)) | 29-May-2025 | 06-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX10 | CX1790 | MODIFIED | FOD Clean (COLO3-CE1/CE2(UPS01-02)) | 07-Jun-2025 | 09-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2(UPS01-02) | CLAYCO | #EE5A1C | Y11 | CX1800 | MODIFIED | L2 QA/QC FOD (COLO3-CE1/CE2(UPS01-02)) | 10-Jun-2025 | 11-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX12 | CX1810 | MODIFIED | IVC (COLO3-CE1/CE2(UPS01-02)) | 12-Jun-2025 | 13-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX16 | CX1820 | MODIFIED | Yellow Tag (COLO3-CE1/CE2(UPS01-02)) | 16-Jun-2025 | 17-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX9 | CX1830 | MODIFIED | Control Checks (COLO3-CE1/CE2(UPS01-02)) | 18-Jun-2025 | 19-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX17 | CX1840 | MODIFIED | Energization (COLO3-CE1/CE2(UPS01-02)) | 20-Jun-2025 | 20-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2(UPS01-02) | CLAYCO | #EE5A1C | Y9 | CX1850 | MODIFIED | L3 Startup (COLO3-CE1/CE2(UPS01-02)) | 21-Jun-2025 | 25-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX20 | CX1870 | MODIFIED | EPMS SAT (COLO3-CE1/CE2(UPS01-02)) | 26-Jun-2025 | 27-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX19 | CX1860 | MODIFIED | IR Scans (COLO3-CE1/CE2(UPS01-02)) | 08-Jul-2025 | 09-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2(UPS01-02) | CLAYCO | #EE5A1C | Y10 | CX1880 | MODIFIED | L3 PFC (COLO3-CE1/CE2(UPS01-02)) | 10-Jul-2025 | 12-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX22 | CX1890 | MODIFIED | Green Tag (COLO3-CE1/CE2(UPS01-02)) | 14-Jul-2025 | 16-Jul-2025
Commissioning | COLO 3 | COLO3-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX7 | CX1900 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-CE3/CE4(UPS01-02)) | 03-Apr-2025 | 16-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX8 | CX1910 | MODIFIED | Pre Startup Vendor (COLO3-CE3/CE4(UPS01-02)) | 03-Jun-2025 | 16-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX10 | CX1920 | MODIFIED | FOD Clean (COLO3-CE3/CE4(UPS01-02)) | 17-Jun-2025 | 18-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4(UPS01-02) | CLAYCO | #EE5A1C | Y11 | CX1930 | MODIFIED | L2 QA/QC FOD (COLO3-CE3/CE4(UPS01-02)) | 19-Jun-2025 | 20-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX12 | CX1940 | MODIFIED | IVC (COLO3-CE3/CE4(UPS01-02)) | 21-Jun-2025 | 23-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX16 | CX1950 | MODIFIED | Yellow Tag (COLO3-CE3/CE4(UPS01-02)) | 24-Jun-2025 | 25-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX9 | CX1960 | MODIFIED | Control Checks (COLO3-CE3/CE4(UPS01-02)) | 26-Jun-2025 | 27-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX17 | CX1970 | MODIFIED | Energization (COLO3-CE3/CE4(UPS01-02)) | 28-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE3/CE4(UPS01-02) | CLAYCO | #EE5A1C | Y9 | CX1980 | MODIFIED | L3 Startup (COLO3-CE3/CE4(UPS01-02)) | 03-Jul-2025 | 09-Jul-2025
Commissioning | COLO 3 | COLO3-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX19 | CX2000 | MODIFIED | IR Scans (COLO3-CE3/CE4(UPS01-02)) | 10-Jul-2025 | 11-Jul-2025
Commissioning | COLO 3 | COLO3-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX20 | CX1990 | MODIFIED | EPMS SAT (COLO3-CE3/CE4(UPS01-02)) | 10-Jul-2025 | 11-Jul-2025
Commissioning | COLO 3 | COLO3-CE3/CE4(UPS01-02) | CLAYCO | #EE5A1C | Y10 | CX2010 | MODIFIED | L3 PFC (COLO3-CE3/CE4(UPS01-02)) | 12-Jul-2025 | 15-Jul-2025
Commissioning | COLO 3 | COLO3-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX22 | CX2020 | MODIFIED | Green Tag (COLO3-CE3/CE4(UPS01-02)) | 16-Jul-2025 | 18-Jul-2025
Commissioning | COLO 3 | COLO3-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX7 | CX2030 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-CE1-PDU(01-06)) | 14-Apr-2025 | 30-May-2025
Commissioning | COLO 3 | COLO3-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX8 | CX2040 | MODIFIED | Pre Startup Vendor (COLO3-CE1-PDU(01-06)) | 04-Jun-2025 | 06-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX10 | CX2050 | MODIFIED | FOD Clean (COLO3-CE1-PDU(01-06)) | 06-Jun-2025 | 06-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y11 | CX2060 | MODIFIED | L2 QA/QC FOD (COLO3-CE1-PDU(01-06)) | 07-Jun-2025 | 09-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX12 | CX2070 | MODIFIED | IVC (COLO3-CE1-PDU(01-06)) | 10-Jun-2025 | 13-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX16 | CX2080 | MODIFIED | Yellow Tag (COLO3-CE1-PDU(01-06)) | 16-Jun-2025 | 17-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX9 | CX2090 | MODIFIED | Control Checks (COLO3-CE1-PDU(01-06)) | 19-Jun-2025 | 20-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX17 | CX2100 | MODIFIED | Energization (COLO3-CE1-PDU(01-06)) | 21-Jun-2025 | 21-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX19 | CX2130 | MODIFIED | IR Scans (COLO3-CE1-PDU(01-06)) | 23-Jun-2025 | 25-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX20 | CX2120 | MODIFIED | EPMS SAT (COLO3-CE1-PDU(01-06)) | 27-Jun-2025 | 30-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y10 | CX2140 | MODIFIED | L3 PFC (COLO3-CE1-PDU(01-06)) | 01-Jul-2025 | 03-Jul-2025
Commissioning | COLO 3 | COLO3-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX22 | CX2150 | MODIFIED | Green Tag (COLO3-CE1-PDU(01-06)) | 07-Jul-2025 | 09-Jul-2025
Commissioning | COLO 3 | COLO3-CE2-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX7 | CX2160 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-CE2-PDU(01-06)) | 14-Apr-2025 | 30-May-2025
Commissioning | COLO 3 | COLO3-CE2-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX8 | CX2170 | MODIFIED | Pre Startup Vendor (COLO3-CE2-PDU(01-06)) | 04-Jun-2025 | 06-Jun-2025
Commissioning | COLO 3 | COLO3-CE2-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX10 | CX2180 | MODIFIED | FOD Clean (COLO3-CE2-PDU(01-06)) | 06-Jun-2025 | 07-Jun-2025
Commissioning | COLO 3 | COLO3-CE2-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y11 | CX2190 | MODIFIED | L2 QA/QC FOD (COLO3-CE2-PDU(01-06)) | 09-Jun-2025 | 09-Jun-2025
Commissioning | COLO 3 | COLO3-CE2-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX12 | CX2200 | MODIFIED | IVC (COLO3-CE2-PDU(01-06)) | 10-Jun-2025 | 13-Jun-2025
Commissioning | COLO 3 | COLO3-CE2-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX16 | CX2210 | MODIFIED | Yellow Tag (COLO3-CE2-PDU(01-06)) | 16-Jun-2025 | 17-Jun-2025
Commissioning | COLO 3 | COLO3-CE2-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX9 | CX2220 | MODIFIED | Control Checks (COLO3-CE2-PDU(01-06)) | 18-Jun-2025 | 20-Jun-2025
Commissioning | COLO 3 | COLO3-CE2-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX17 | CX2230 | MODIFIED | Energization (COLO3-CE2-PDU(01-06)) | 21-Jun-2025 | 21-Jun-2025
Commissioning | COLO 3 | COLO3-CE2-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX19 | CX2240 | MODIFIED | IR Scans (COLO3-CE2-PDU(01-06)) | 24-Jun-2025 | 26-Jun-2025
Commissioning | COLO 3 | COLO3-CE2-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX20 | CX2250 | MODIFIED | EPMS SAT (COLO3-CE2-PDU(01-06)) | 27-Jun-2025 | 30-Jun-2025
Commissioning | COLO 3 | COLO3-CE2-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y10 | CX2260 | MODIFIED | L3 PFC (COLO3-CE2-PDU(01-06)) | 01-Jul-2025 | 03-Jul-2025
Commissioning | COLO 3 | COLO3-CE2-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX22 | CX2270 | MODIFIED | Green Tag (COLO3-CE2-PDU(01-06)) | 07-Jul-2025 | 09-Jul-2025
Commissioning | COLO 3 | COLO3-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX7 | CX2280 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-CE3-PDU(01-06)) | 15-Apr-2025 | 07-Jun-2025
Commissioning | COLO 3 | COLO3-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX12 | CX2320 | MODIFIED | IVC (COLO3-CE3-PDU(01-06)) | 18-Jun-2025 | 21-Jun-2025
Commissioning | COLO 3 | COLO3-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX16 | CX2330 | MODIFIED | Yellow Tag (COLO3-CE3-PDU(01-06)) | 23-Jun-2025 | 24-Jun-2025
Commissioning | COLO 3 | COLO3-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX9 | CX2340 | MODIFIED | Control Checks (COLO3-CE3-PDU(01-06)) | 25-Jun-2025 | 27-Jun-2025
Commissioning | COLO 3 | COLO3-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX17 | CX2350 | MODIFIED | Energization (COLO3-CE3-PDU(01-06)) | 28-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX19 | CX2360 | MODIFIED | IR Scans (COLO3-CE3-PDU(01-06)) | 30-Jun-2025 | 02-Jul-2025
Commissioning | COLO 3 | COLO3-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX20 | CX2370 | MODIFIED | EPMS SAT (COLO3-CE3-PDU(01-06)) | 03-Jul-2025 | 08-Jul-2025
Commissioning | COLO 3 | COLO3-CE3-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y10 | CX2380 | MODIFIED | L3 PFC (COLO3-CE3-PDU(01-06)) | 09-Jul-2025 | 11-Jul-2025
Commissioning | COLO 3 | COLO3-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX22 | CX2390 | MODIFIED | Green Tag (COLO3-CE3-PDU(01-06)) | 12-Jul-2025 | 15-Jul-2025
Commissioning | COLO 3 | COLO3-CE4-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX7 | CX2400 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-CE4-PDU(01-06)) | 16-Apr-2025 | 07-Jun-2025
Commissioning | COLO 3 | COLO3-CE4-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX12 | CX2440 | MODIFIED | IVC (COLO3-CE4-PDU(01-06)) | 18-Jun-2025 | 21-Jun-2025
Commissioning | COLO 3 | COLO3-CE4-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX16 | CX2450 | MODIFIED | Yellow Tag (COLO3-CE4-PDU(01-06)) | 23-Jun-2025 | 24-Jun-2025
Commissioning | COLO 3 | COLO3-CE4-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX9 | CX2460 | MODIFIED | Control Checks (COLO3-CE4-PDU(01-06)) | 25-Jun-2025 | 27-Jun-2025
Commissioning | COLO 3 | COLO3-CE4-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX17 | CX2470 | MODIFIED | Energization (COLO3-CE4-PDU(01-06)) | 28-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE4-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX19 | CX2480 | MODIFIED | IR Scans (COLO3-CE4-PDU(01-06)) | 28-Jun-2025 | 01-Jul-2025
Commissioning | COLO 3 | COLO3-CE4-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX20 | CX2490 | MODIFIED | EPMS SAT (COLO3-CE4-PDU(01-06)) | 02-Jul-2025 | 07-Jul-2025
Commissioning | COLO 3 | COLO3-CE4-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y10 | CX2500 | MODIFIED | L3 PFC (COLO3-CE4-PDU(01-06)) | 09-Jul-2025 | 11-Jul-2025
Commissioning | COLO 3 | COLO3-CE4-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX22 | CX2510 | MODIFIED | Green Tag (COLO3-CE4-PDU(01-06)) | 12-Jul-2025 | 15-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX7 | CX2520 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-CE1/CE2-GPC01) | 19-Mar-2025 | 16-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX8 | CX2530 | MODIFIED | Pre Startup Vendor (COLO3-CE1/CE2-GPC01) | 19-May-2025 | 23-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX9 | CX2580 | MODIFIED | Control Checks (COLO3-CE1/CE2-GPC01) | 27-May-2025 | 28-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX10 | CX2540 | MODIFIED | FOD Clean (COLO3-CE1/CE2-GPC01) | 29-May-2025 | 30-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | CLAYCO | #EE5A1C | Y11 | CX2550 | MODIFIED | L2 QA/QC FOD (COLO3-CE1/CE2-GPC01) | 02-Jun-2025 | 03-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX12 | CX2560 | MODIFIED | IVC (COLO3-CE1/CE2-GPC01) | 04-Jun-2025 | 06-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX16 | CX2570 | MODIFIED | Yellow Tag (COLO3-CE1/CE2-GPC01) | 07-Jun-2025 | 09-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX17 | CX2590 | MODIFIED | Energization (COLO3-CE1/CE2-GPC01) | 20-Jun-2025 | 20-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | CLAYCO | #EE5A1C | Y9 | CX2600 | MODIFIED | L3 Startup (COLO3-CE1/CE2-GPC01) | 21-Jun-2025 | 26-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX19 | CX2620 | MODIFIED | IR SCANS (COLO3-CE1/CE2-GPC01) | 27-Jun-2025 | 01-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX23 | CX2610 | MODIFIED | Load Banking (COLO3-CE1/CE2-GPC01) | 27-Jun-2025 | 01-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX20 | CX2630 | MODIFIED | EPMS SAT (COLO3-CE1/CE2-GPC01) | 02-Jul-2025 | 08-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | CLAYCO | #EE5A1C | Y10 | CX2640 | MODIFIED | L3 PFC (COLO3-CE1/CE2-GPC01) | 09-Jul-2025 | 11-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX22 | CX2650 | MODIFIED | Green Tag (COLO3-CE1/CE2-GPC01) | 12-Jul-2025 | 15-Jul-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX7 | CX2660 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-CE3/CE4-GPC01) | 19-Mar-2025 | 27-May-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX8 | CX2670 | MODIFIED | Pre Startup Vendor (COLO3-CE3/CE4-GPC01) | 28-May-2025 | 03-Jun-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX9 | CX2680 | MODIFIED | Control Checks (COLO3-CE3/CE4-GPC01) | 06-Jun-2025 | 07-Jun-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX10 | CX2690 | MODIFIED | FOD Clean (COLO3-CE3/CE4-GPC01) | 09-Jun-2025 | 10-Jun-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | CLAYCO | #EE5A1C | Y11 | CX2700 | MODIFIED | L2 QA/QC FOD (COLO3-CE3/CE4-GPC01) | 11-Jun-2025 | 12-Jun-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX12 | CX2710 | MODIFIED | IVC (COLO3-CE3/CE4-GPC01) | 13-Jun-2025 | 17-Jun-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX16 | CX2720 | MODIFIED | Yellow Tag (COLO3-CE3/CE4-GPC01) | 18-Jun-2025 | 19-Jun-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX17 | CX2730 | MODIFIED | Energization (COLO3-CE3/CE4-GPC01) | 24-Jun-2025 | 24-Jun-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | CLAYCO | #EE5A1C | Y9 | CX2740 | MODIFIED | L3 Startup (COLO3-CE3/CE4-GPC01) | 27-Jun-2025 | 02-Jul-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX19 | CX2750 | MODIFIED | IR SCANS (COLO3-CE3/CE4-GPC01) | 02-Jul-2025 | 08-Jul-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX23 | CX2760 | MODIFIED | Load Banking (COLO3-CE3/CE4-GPC01) | 02-Jul-2025 | 08-Jul-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX20 | CX2770 | MODIFIED | EPMS SAT (COLO3-CE3/CE4-GPC01) | 09-Jul-2025 | 12-Jul-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | CLAYCO | #EE5A1C | Y10 | CX2780 | MODIFIED | L3 PFC (COLO3-CE3/CE4-GPC01) | 14-Jul-2025 | 16-Jul-2025
Commissioning | COLO 3 | COLO3-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX22 | CX2790 | MODIFIED | Green Tag (COLO3-CE3/CE4-GPC01) | 17-Jul-2025 | 19-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX7 | CX2800 | MODIFIED | MEP Test/Pre Startup Installer (CHI11-COLO3-CE3-LBP01/LBT01) | 08-May-2025 | 27-May-2025
Commissioning | COLO 3 | CHI11-COLO3-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX8 | CX2810 | MODIFIED | Pre Startup Vendor (CHI11-COLO3-CE3-LBP01/LBT01) | 28-May-2025 | 29-May-2025
Commissioning | COLO 3 | CHI11-COLO3-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX10 | CX2830 | MODIFIED | FOD Clean (CHI11-COLO3-CE3-LBP01/LBT01) | 30-May-2025 | 30-May-2025
Commissioning | COLO 3 | CHI11-COLO3-CE3-LBP01/LBT01 | CLAYCO | #EE5A1C | Y11 | CX2840 | MODIFIED | L2 QA/QC FOD (CHI11-COLO3-CE3-LBP01/LBT01) | 02-Jun-2025 | 03-Jun-2025
Commissioning | COLO 3 | CHI11-COLO3-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX12 | CX2850 | MODIFIED | IVC (CHI11-COLO3-CE3-LBP01/LBT01) | 04-Jun-2025 | 05-Jun-2025
Commissioning | COLO 3 | CHI11-COLO3-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX16 | CX2860 | MODIFIED | Yellow Tag (CHI11-COLO3-CE3-LBP01/LBT01) | 06-Jun-2025 | 07-Jun-2025
Commissioning | COLO 3 | CHI11-COLO3-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX17 | CX2870 | MODIFIED | Energization (CHI11-COLO3-CE3-LBP01/LBT01) | 25-Jun-2025 | 25-Jun-2025
Commissioning | COLO 3 | CHI11-COLO3-CE3-LBP01/LBT01 | CLAYCO | #EE5A1C | Y9 | CX2880 | MODIFIED | L3 Startup (CHI11-COLO3-CE3-LBP01/LBT01) | 26-Jun-2025 | 26-Jun-2025
Commissioning | COLO 3 | CHI11-COLO3-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX20 | CX2900 | MODIFIED | EPMS SAT (CHI11-COLO3-CE3-LBP01/LBT01) | 27-Jun-2025 | 27-Jun-2025
Commissioning | COLO 3 | CHI11-COLO3-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX19 | CX2890 | MODIFIED | IR Scans (CHI11-COLO3-CE3-LBP01/LBT01) | 28-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | CHI11-COLO3-CE3-LBP01/LBT01 | CLAYCO | #EE5A1C | Y10 | CX2910 | MODIFIED | L3 PFC (CHI11-COLO3-CE3-LBP01/LBT01) | 30-Jun-2025 | 01-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX22 | CX2920 | MODIFIED | Green Tag (CHI11-COLO3-CE3-LBP01/LBT01) | 02-Jul-2025 | 03-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX7 | CX2930 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-CE1/CE4-ATS(01-06)) | 08-Apr-2025 | 06-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX8 | CX2940 | MODIFIED | Pre Startup Vendor (COLO3-CE1/CE4-ATS(01-06)) | 09-Jun-2025 | 13-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX10 | CX2950 | MODIFIED | FOD Clean (COLO3-CE1/CE4-ATS(01-06)) | 16-Jun-2025 | 18-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | CLAYCO | #EE5A1C | Y11 | CX2960 | MODIFIED | L2 QA/QC FOD (COLO3-CE1/CE4-ATS(01-06)) | 19-Jun-2025 | 21-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX12 | CX2970 | MODIFIED | IVC (COLO3-CE1/CE4-ATS(01-06)) | 23-Jun-2025 | 25-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX16 | CX2980 | MODIFIED | Yellow Tag (COLO3-CE1/CE4-ATS(01-06)) | 26-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX17 | CX2990 | MODIFIED | Energization (COLO3-CE1/CE4-ATS(01-06)) | 09-Jul-2025 | 10-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX19 | CX3020 | MODIFIED | IR Scans (COLO3-CE1/CE4-ATS(01-06)) | 11-Jul-2025 | 15-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | CLAYCO | #EE5A1C | Y9 | CX3000 | MODIFIED | L3 Startup (COLO3-CE1/CE4-ATS(01-06)) | 11-Jul-2025 | 17-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX20 | CX3010 | MODIFIED | EPMS SAT (COLO3-CE1/CE4-ATS(01-06)) | 18-Jul-2025 | 22-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | CLAYCO | #EE5A1C | Y10 | CX3030 | MODIFIED | L3 PFC (COLO3-CE1/CE4-ATS(01-06)) | 23-Jul-2025 | 28-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX22 | CX3040 | MODIFIED | Green Tag (COLO3-CE1/CE4-ATS(01-06)) | 29-Jul-2025 | 01-Aug-2025
Commissioning | COLO 3 | COLO3-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX7 | CX3170 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-CE1/CE4 LV Panel and XFM) | 02-Apr-2025 | 07-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX10 | CX3190 | MODIFIED | FOD Clean (COLO3-CE1/CE4 LV Panel and XFM) | 09-Jun-2025 | 10-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2 LV Panel and XFM | CLAYCO | #EE5A1C | Y11 | CX3200 | MODIFIED | L2 QA/QC FOD (COLO3-CE1/CE4 LV Panel and XFM) | 11-Jun-2025 | 13-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX12 | CX3210 | MODIFIED | IVC (COLO3-CE1/CE4 LV Panel and XFM) | 16-Jun-2025 | 19-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX16 | CX3220 | MODIFIED | Yellow Tag (COLO3-CE1/CE4 LV Panel and XFM) | 20-Jun-2025 | 21-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX17 | CX3230 | MODIFIED | Energization (COLO3-CE1/CE4 LV Panel and XFM) | 11-Jul-2025 | 12-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX19 | CX3240 | MODIFIED | IR Scans (COLO3-CE1/CE4 LV Panel and XFM) | 14-Jul-2025 | 18-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2 LV Panel and XFM | CLAYCO | #EE5A1C | Y9 | CX3250 | MODIFIED | L3 Startup (COLO3-CE1/CE4 LV Panel and XFM) | 14-Jul-2025 | 18-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2 LV Panel and XFM | CLAYCO | #EE5A1C | Y10 | CX3270 | MODIFIED | L3 PFC (COLO3-CE1/CE4 LV Panel and XFM) | 19-Jul-2025 | 19-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX22 | CX3280 | MODIFIED | Green Tag (COLO3-CE1/CE4 LV Panel and XFM) | 21-Jul-2025 | 21-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX8 | CX3400 | MODIFIED | Pre Startup Vendor (COLO3-CE1/CE2-ATS(01-06)) | 05-May-2025 | 07-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX10 | CX3410 | MODIFIED | FOD Clean (COLO3-CE1/CE2-ATS(01-06)) | 08-May-2025 | 09-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | CLAYCO | #EE5A1C | Y11 | CX3420 | MODIFIED | L2 QA/QC FOD (COLO3-CE1/CE2-ATS(01-06)) | 12-May-2025 | 14-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX12 | CX3430 | MODIFIED | IVC (COLO3-CE1/CE2-ATS(01-06)) | 15-May-2025 | 20-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX16 | CX3440 | MODIFIED | Yellow Tag (COLO3-CE1/CE2-ATS(01-06)) | 05-Jun-2025 | 07-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX17 | CX3450 | MODIFIED | Energization (COLO3-CE1/CE2-ATS(01-06)) | 18-Jun-2025 | 18-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX19 | CX3460 | MODIFIED | IR Scans (COLO3-CE1/CE2-ATS(01-06)) | 19-Jun-2025 | 20-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | CLAYCO | #EE5A1C | Y9 | CX3470 | MODIFIED | L3 Startup (COLO3-CE1/CE2-ATS(01-06)) | 19-Jun-2025 | 24-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | CLAYCO | #EE5A1C | Y10 | CX3490 | MODIFIED | L3 PFC (COLO3-CE1/CE2-ATS(01-06)) | 25-Jun-2025 | 25-Jun-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX22 | CX3500 | MODIFIED | Green Tag (COLO3-CE1/CE2-ATS(01-06)) | 26-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-AHU(01-08) | MSFT | #3DCD3A | CX7 | A3280 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-CE1/CE4-AHU(01-08)) | 02-Apr-2025 | 07-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-AHU(01-08) | MSFT | #3DCD3A | CX8 | A3290 | MODIFIED | Pre Startup Vendor (COLO3-CE1/CE4-AHU(01-08)) (Using NPW TEMP SKID) | 09-Jun-2025 | 17-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-AHU(01-08) | MSFT | #3DCD3A | CX10 | A3300 | MODIFIED | FOD Clean (COLO3-CE1/CE4-AHU(01-08)) | 18-Jun-2025 | 20-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-AHU(01-08) | CLAYCO | #EE5A1C | Y11 | A3310 | MODIFIED | L2 QA/QC FOD (COLO3-CE1/CE4-AHU(01-08)) | 21-Jun-2025 | 23-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-AHU(01-08) | MSFT | #3DCD3A | CX12 | A3320 | MODIFIED | IVC (COLO3-CE1/CE4-AHU(01-08)) | 24-Jun-2025 | 26-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-AHU(01-08) | MSFT | #3DCD3A | CX16 | A3330 | MODIFIED | Yellow Tag (COLO3-CE1/CE4-AHU(01-08)) | 27-Jun-2025 | 28-Jun-2025
Commissioning | COLO 3 | COLO3-CE1-AHU(01-08) | MSFT | #3DCD3A | CX17 | A3340 | MODIFIED | Energization (COLO3-CE1/CE4-AHU(01-08)) | 09-Jul-2025 | 10-Jul-2025
Commissioning | COLO 3 | COLO3-CE1-AHU(01-08) | CLAYCO | #EE5A1C | Y9 | A3360 | MODIFIED | L3 Startup (COLO3-CE1/CE4-AHU(01-08)) (Using NPW TEMP SKID) | 11-Jul-2025 | 17-Jul-2025
Commissioning | COLO 3 | COLO3-CE1-AHU(01-08) | MSFT | #3DCD3A | CX24 | A3370 | MODIFIED | BAS SAT & TAB (COLO3-CE1/CE4-AHU(01-08)) | 18-Jul-2025 | 23-Jul-2025
Commissioning | COLO 3 | COLO3-CE1-AHU(01-08) | CLAYCO | #EE5A1C | Y10 | A3380 | MODIFIED | L3 PFC (COLO3-CE1/CE4-AHU(01-08)) | 01-Aug-2025 | 04-Aug-2025
Commissioning | COLO 3 | COLO3-CE1-AHU(01-08) | MSFT | #3DCD3A | CX22 | A3390 | MODIFIED | Green Tag (COLO3-CE1/CE4-AHU(01-08)) | 05-Aug-2025 | 07-Aug-2025
Commissioning | COLO 3 | COLO3-Control Panel and CC | MSFT | #3DCD3A | CX7 | CX3620 | MODIFIED | MEP Test/Pre Startup Installer (COLO3-Control Panel and CC) | 18-Mar-2025 | 05-Jun-2025
Commissioning | COLO 3 | COLO3-Control Panel and CC | MSFT | #3DCD3A | CX10 | CX3640 | MODIFIED | FOD Clean (COLO3-Control Panel and CC) | 07-Jun-2025 | 09-Jun-2025
Commissioning | COLO 3 | COLO3-Control Panel and CC | CLAYCO | #EE5A1C | Y11 | CX3650 | MODIFIED | L2 QA/QC FOD (COLO3-Control Panel and CC) | 10-Jun-2025 | 11-Jun-2025
Commissioning | COLO 3 | COLO3-Control Panel and CC | MSFT | #3DCD3A | CX12 | CX3660 | MODIFIED | IVC (COLO3-Control Panel and CC) | 12-Jun-2025 | 13-Jun-2025
Commissioning | COLO 3 | COLO3-Control Panel and CC | MSFT | #3DCD3A | CX16 | CX3670 | MODIFIED | Yellow Tag (COLO3-Control Panel and CC) | 16-Jun-2025 | 17-Jun-2025
Commissioning | COLO 3 | COLO3-Control Panel and CC | MSFT | #3DCD3A | CX17 | CX3680 | MODIFIED | Energization (COLO3-Control Panel and CC) | 25-Jun-2025 | 26-Jun-2025
Commissioning | COLO 3 | COLO3-Control Panel and CC | MSFT | #3DCD3A | CX25 | CX3690 | MODIFIED | BAS SAT (COLO3-Control Panel and CC) | 27-Jun-2025 | 30-Jun-2025
Commissioning | COLO 3 | CHI11-COLO3-AC/CU(01-02) | MSFT | #3DCD3A | CX7 | CX3730 | MODIFIED | MEP Test/Pre Startup Installer (CHI11-COLO3-AC/CU(01-02)) | 15-May-2025 | 23-Jun-2025
Commissioning | COLO 3 | CHI11-COLO3-AC/CU(01-02) | MSFT | #3DCD3A | CX10 | CX3740 | MODIFIED | FOD Clean (CHI11-COLO3-AC/CU(01-02)) | 24-Jun-2025 | 25-Jun-2025
Commissioning | COLO 3 | CHI11-COLO3-AC/CU(01-02) | CLAYCO | #EE5A1C | Y11 | CX3750 | MODIFIED | L2 QA/QC FOD (CHI11-COLO3-AC/CU(01-02)) | 26-Jun-2025 | 27-Jun-2025
Commissioning | COLO 3 | CHI11-COLO3-AC/CU(01-02) | MSFT | #3DCD3A | CX12 | CX3760 | MODIFIED | IVC (CHI11-COLO3-AC/CU(01-02)) | 28-Jun-2025 | 30-Jun-2025
Commissioning | COLO 3 | CHI11-COLO3-AC/CU(01-02) | MSFT | #3DCD3A | CX16 | CX3770 | MODIFIED | Yellow Tag (CHI11-COLO3-AC/CU(01-02)) | 01-Jul-2025 | 02-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-AC/CU(01-02) | MSFT | #3DCD3A | CX17 | CX3780 | MODIFIED | Energization (CHI11-COLO3-AC/CU(01-02)) | 17-Jul-2025 | 17-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-AC/CU(01-02) | CLAYCO | #EE5A1C | Y9 | CX3790 | MODIFIED | L3 Startup (CHI11-COLO3-AC/CU(01-02)) | 18-Jul-2025 | 21-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-AC/CU(01-02) | MSFT | #3DCD3A | CX25 | CX3800 | MODIFIED | BAS SAT (CHI11-COLO3-AC/CU(01-02)) | 22-Jul-2025 | 23-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-AC/CU(01-02) | MSFT | #3DCD3A | CX22 | CX3810 | MODIFIED | Green Tag (CHI11-COLO3-AC/CU(01-02)) | 24-Jul-2025 | 28-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE2/CE3-UH01 | MSFT | #3DCD3A | CX7 | CX3820 | MODIFIED | MEP Test/Pre Startup Installer (CHI11-COLO3-CE2/CE3-UH01) | 11-Jun-2025 | 07-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE2/CE3-UH01 | MSFT | #3DCD3A | CX10 | CX3830 | MODIFIED | FOD Clean (CHI11-COLO3-CE2/CE3-UH01) | 08-Jul-2025 | 08-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE2/CE3-UH01 | CLAYCO | #EE5A1C | Y11 | CX3840 | MODIFIED | L2 QA/QC FOD (CHI11-COLO3-CE2/CE3-UH01) | 09-Jul-2025 | 09-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE2/CE3-UH01 | MSFT | #3DCD3A | CX12 | CX3850 | MODIFIED | IVC (CHI11-COLO3-CE2/CE3-UH01) | 10-Jul-2025 | 12-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE2/CE3-UH01 | MSFT | #3DCD3A | CX16 | CX3860 | MODIFIED | Yellow Tag (CHI11-COLO3-CE2/CE3-UH01) | 14-Jul-2025 | 14-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE2/CE3-UH01 | MSFT | #3DCD3A | CX17 | CX3870 | MODIFIED | Energization (CHI11-COLO3-CE2/CE3-UH01) | 17-Jul-2025 | 17-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE2/CE3-UH01 | CLAYCO | #EE5A1C | Y9 | CX3880 | MODIFIED | L3 Startup (CHI11-COLO3-CE2/CE3-UH01) | 18-Jul-2025 | 23-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE2/CE3-UH01 | MSFT | #3DCD3A | CX22 | CX3900 | MODIFIED | Green Tag (CHI11-COLO3-CE2/CE3-UH01) | 24-Jul-2025 | 24-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE1/CE4-BP01 | MSFT | #3DCD3A | CX7 | CX3910 | MODIFIED | MEP Test/Pre Startup Installer (CH11-PUMPHOUSEE-BP01) | 12-Jul-2025 | 24-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE1/CE4-BP01 | MSFT | #3DCD3A | CX10 | CX3920 | MODIFIED | FOD Clean (CH11-PUMPHOUSEE-BP01) | 25-Jul-2025 | 25-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE1/CE4-BP01 | CLAYCO | #EE5A1C | Y11 | CX3930 | MODIFIED | L2 QA/QC FOD (CH11-PUMPHOUSEE-BP01) | 28-Jul-2025 | 29-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE1/CE4-BP01 | MSFT | #3DCD3A | CX12 | CX3940 | MODIFIED | IVC (CH11-PUMPHOUSEE-BP01) | 30-Jul-2025 | 30-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE1/CE4-BP01 | MSFT | #3DCD3A | CX16 | CX3950 | MODIFIED | Yellow Tag (CH11-PUMPHOUSEE-BP01) | 31-Jul-2025 | 31-Jul-2025
Commissioning | COLO 3 | CHI11-COLO3-CE1/CE4-BP01 | MSFT | #3DCD3A | CX17 | CX3960 | MODIFIED | Energization (CH11-PUMPHOUSEE-BP01) | 01-Aug-2025 | 01-Aug-2025
Commissioning | COLO 3 | CHI11-COLO3-CE1/CE4-BP01 | CLAYCO | #EE5A1C | Y9 | CX3970 | MODIFIED | L3 Startup (CH11-PUMPHOUSEE-BP01) | 02-Aug-2025 | 07-Aug-2025
Commissioning | COLO 3 | CHI11-COLO3-CE1/CE4-BP01 | MSFT | #3DCD3A | CX25 | CX3980 | MODIFIED | BAS SAT (CH11-PUMPHOUSEE-BP01) | 08-Aug-2025 | 08-Aug-2025
Commissioning | COLO 3 | CHI11-COLO3-CE1/CE4-BP01 | MSFT | #3DCD3A | CX22 | CX3990 | MODIFIED | Green Tag (CH11-PUMPHOUSEE-BP01) | 09-Aug-2025 | 11-Aug-2025
Commissioning | COLO 3 | CHI11-PUMPHOUSE-BP01 | MSFT | #3DCD3A | CX7 | CX4000 | MODIFIED | MEP Test/Pre Startup Installer (CH11-COLO3-CE1/CE4-BP01) | 12-Jul-2025 | 28-Jul-2025
Commissioning | COLO 3 | CHI11-PUMPHOUSE-BP01 | MSFT | #3DCD3A | CX10 | CX4010 | MODIFIED | FOD Clean (CH11-COLO3-CE1/CE4-BP01) | 30-Jul-2025 | 30-Jul-2025
Commissioning | COLO 3 | CHI11-PUMPHOUSE-BP01 | CLAYCO | #EE5A1C | Y11 | CX4020 | MODIFIED | L2 QA/QC FOD (CH11-COLO3-CE1/CE4-BP01) | 31-Jul-2025 | 01-Aug-2025
Commissioning | COLO 3 | CHI11-PUMPHOUSE-BP01 | MSFT | #3DCD3A | CX12 | CX4030 | MODIFIED | IVC (CH11-COLO3-CE1/CE4-BP01) | 02-Aug-2025 | 02-Aug-2025
Commissioning | COLO 3 | CHI11-PUMPHOUSE-BP01 | MSFT | #3DCD3A | CX16 | CX4040 | MODIFIED | Yellow Tag (CH11-COLO3-CE1/CE4-BP01) | 04-Aug-2025 | 04-Aug-2025
Commissioning | COLO 3 | CHI11-PUMPHOUSE-BP01 | MSFT | #3DCD3A | CX17 | CX4050 | MODIFIED | Energization (CH11-COLO3-CE1/CE4-BP01) | 05-Aug-2025 | 05-Aug-2025
Commissioning | COLO 3 | CHI11-PUMPHOUSE-BP01 | CLAYCO | #EE5A1C | Y9 | CX4060 | MODIFIED | L3 Startup (CH11-COLO3-CE1/CE4-BP01) | 06-Aug-2025 | 11-Aug-2025
Commissioning | COLO 3 | CHI11-PUMPHOUSE-BP01 | MSFT | #3DCD3A | CX25 | CX4070 | MODIFIED | BAS SAT (CH11-COLO3-CE1/CE4-BP01) | 12-Aug-2025 | 12-Aug-2025
Commissioning | COLO 3 | CHI11-PUMPHOUSE-BP01 | MSFT | #3DCD3A | CX22 | CX4080 | MODIFIED | Green Tag (CH11-COLO3-CE1/CE4-BP01) | 13-Aug-2025 | 14-Aug-2025
Commissioning | COLO 3 | COLO3-CE1/CE4-PRV01-02 | MSFT | #3DCD3A | CX7 | CX4090 | MODIFIED | MEP Test/Pre Startup Installer (CH11-PUMPHOUSEE-BP01) | 17-Jul-2025 | 28-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE4-PRV01-02 | MSFT | #3DCD3A | CX10 | CX4100 | MODIFIED | FOD Clean (CH11-PUMPHOUSEE-BP01) | 29-Jul-2025 | 30-Jul-2025
Commissioning | COLO 3 | COLO3-CE1/CE4-PRV01-02 | CLAYCO | #EE5A1C | Y11 | CX4110 | MODIFIED | L2 QA/QC FOD (CH11-PUMPHOUSEE-BP01) | 31-Jul-2025 | 01-Aug-2025
Commissioning | COLO 3 | COLO3-CE1/CE4-PRV01-02 | MSFT | #3DCD3A | CX16 | CX4130 | MODIFIED | Yellow Tag (CH11-PUMPHOUSEE-BP01) | 02-Aug-2025 | 02-Aug-2025
Commissioning | COLO 3 | COLO3-CE1/CE4-PRV01-02 | MSFT | #3DCD3A | CX17 | CX4140 | MODIFIED | Energization (CH11-PUMPHOUSEE-BP01) | 04-Aug-2025 | 04-Aug-2025
Commissioning | COLO 3 | COLO3-CE1/CE4-PRV01-02 | CLAYCO | #EE5A1C | Y9 | CX4150 | MODIFIED | L3 Startup (CH11-PUMPHOUSEE-BP01) | 05-Aug-2025 | 12-Aug-2025
Commissioning | COLO 3 | COLO3-CE1/CE4-PRV01-02 | MSFT | #3DCD3A | CX22 | CX4170 | MODIFIED | Green Tag (CH11-PUMPHOUSEE-BP01) | 13-Aug-2025 | 13-Aug-2025
Commissioning | COLO 3 | CHI11-1A/B-HTP01 | MSFT | #3DCD3A | CX7 | CX4180 | MODIFIED | MEP Test/Pre Startup Installer (CHI11-1A/B-HTP01) | 08-Jul-2025 | 11-Jul-2025
Commissioning | COLO 3 | CHI11-1A/B-HTP01 | MSFT | #3DCD3A | CX10 | CX4190 | MODIFIED | FOD Clean (CHI11-1A/B-HTP01) | 12-Jul-2025 | 14-Jul-2025
Commissioning | COLO 3 | CHI11-1A/B-HTP01 | CLAYCO | #EE5A1C | Y11 | CX4200 | MODIFIED | L2 QA/QC FOD (CHI11-1A/B-HTP01) | 15-Jul-2025 | 16-Jul-2025
Commissioning | COLO 3 | CHI11-1A/B-HTP01 | MSFT | #3DCD3A | CX12 | CX4210 | MODIFIED | IVC (CHI11-1A/B-HTP01) | 17-Jul-2025 | 19-Jul-2025
Commissioning | COLO 3 | CHI11-1A/B-HTP01 | MSFT | #3DCD3A | CX16 | CX4220 | MODIFIED | Yellow Tag (CHI11-1A/B-HTP01) | 21-Jul-2025 | 22-Jul-2025
Commissioning | COLO 3 | CHI11-1A/B-HTP01 | MSFT | #3DCD3A | CX17 | CX4230 | MODIFIED | Energization (CHI11-1A/B-HTP01) | 23-Jul-2025 | 23-Jul-2025
Commissioning | COLO 3 | CHI11-1A/B-HTP01 | CLAYCO | #EE5A1C | Y9 | CX4240 | MODIFIED | L3 Startup (CHI11-1A/B-HTP01) | 24-Jul-2025 | 29-Jul-2025
Commissioning | COLO 3 | CHI11-1A/B-HTP01 | MSFT | #3DCD3A | CX25 | CX4250 | MODIFIED | BAS SAT (CHI11-1A/B-HTP01) | 30-Jul-2025 | 04-Aug-2025
Commissioning | COLO 3 | CHI11-1A/B-HTP01 | MSFT | #3DCD3A | CX22 | CX4260 | MODIFIED | Green Tag (CHI11-1A/B-HTP01) | 05-Aug-2025 | 05-Aug-2025
Commissioning | COLO 3 | CHI11-FP/JP-01 | MSFT | #3DCD3A | CX7 | CX4270 | MODIFIED | MEP Test/Pre Startup Installer (CH11-FP/JP-01) | 17-Jul-2025 | 28-Jul-2025
Commissioning | COLO 3 | CHI11-FP/JP-01 | MSFT | #3DCD3A | CX17 | CX4320 | MODIFIED | Energization (CH11-FP/JP-01) | 02-Aug-2025 | 02-Aug-2025
Commissioning | COLO 3 | CHI11-FP/JP-01 | CLAYCO | #EE5A1C | Y9 | CX4330 | MODIFIED | L3 Startup (CH11-FP/JP-01) | 04-Aug-2025 | 06-Aug-2025
Commissioning | COLO 3 | CHI11-FP/JP-01 | MSFT | #3DCD3A | CX22 | CX4350 | MODIFIED | Green Tag (CH11-FP/JP-01) | 07-Aug-2025 | 07-Aug-2025
Commissioning | COLO 4 | COLO4 UPM | MSFT | #3DCD3A | CX8 | CX5140 | MODIFIED | Pre Startup Vendor (COLO4 UPM) | 02-Jun-2025 | 07-Jun-2025
Commissioning | COLO 4 | COLO4 UPM | MSFT | #3DCD3A | CX9 | CX5240 | MODIFIED | Control Checks (COLO4 UPM) | 12-Jun-2025 | 13-Jun-2025
Commissioning | COLO 4 | COLO4 UPM | MSFT | #3DCD3A | CX10 | CX5160 | MODIFIED | FOD Clean (COLO4 UPM) | 16-Jun-2025 | 17-Jun-2025
Commissioning | COLO 4 | COLO4 UPM | CLAYCO | #EE5A1C | Y11 | CX5170 | MODIFIED | L2 QA/QC FOD (COLO4 UPM) | 18-Jun-2025 | 19-Jun-2025
Commissioning | COLO 4 | COLO4 UPM | MSFT | #3DCD3A | CX12 | CX5180 | MODIFIED | IVC (COLO4 UPM) | 20-Jun-2025 | 21-Jun-2025
Commissioning | COLO 4 | COLO4 UPM | MSFT | #3DCD3A | CX16 | CX5190 | MODIFIED | Yellow Tag (COLO4 UPM) | 24-Jun-2025 | 25-Jun-2025
Commissioning | COLO 4 | COLO4 UPM | MSFT | #3DCD3A | CX17 | CX5200 | MODIFIED | Energization (COLO4 UPM) | 26-Jun-2025 | 26-Jun-2025
Commissioning | COLO 4 | COLO4 UPM | CLAYCO | #EE5A1C | Y9 | CX5250 | MODIFIED | L3 Startup (COLO4 UPM) | 27-Jun-2025 | 02-Jul-2025
Commissioning | COLO 4 | COLO4 UPM | MSFT | #3DCD3A | CX19 | CX5210 | MODIFIED | IR Scans (COLO4 UPM) | 03-Jul-2025 | 03-Jul-2025
Commissioning | COLO 4 | COLO4 UPM | MSFT | #3DCD3A | CX20 | CX5260 | MODIFIED | EPMS SAT (COLO4 UPM) | 03-Jul-2025 | 08-Jul-2025
Commissioning | COLO 4 | COLO4 UPM | CLAYCO | #EE5A1C | Y10 | CX5220 | MODIFIED | L3 PFC (COLO4 UPM) | 09-Jul-2025 | 10-Jul-2025
Commissioning | COLO 4 | COLO4 UPM | MSFT | #3DCD3A | CX22 | CX5150 | MODIFIED | Green Tag (COLO4 UPM) | 11-Jul-2025 | 11-Jul-2025
Commissioning | COLO 4 | COLO4 XFM01 | MSFT | #3DCD3A | CX7 | CX5360 | MODIFIED | MEP Test/Pre Startup Installer (COLO4 XFM01) | 24-Apr-2025 | 07-Jun-2025
Commissioning | COLO 4 | COLO4 XFM01 | MSFT | #3DCD3A | CX8 | CX5270 | MODIFIED | Pre Startup Vendor (COLO4 XFM01) | 12-Jun-2025 | 13-Jun-2025
Commissioning | COLO 4 | COLO4 XFM01 | MSFT | #3DCD3A | CX10 | CX5370 | MODIFIED | FOD Clean (COLO4 XFM01) | 16-Jun-2025 | 17-Jun-2025
Commissioning | COLO 4 | COLO4 XFM01 | CLAYCO | #EE5A1C | Y11 | CX5290 | MODIFIED | L2 QA/QC (COLO4 XFM01) | 18-Jun-2025 | 19-Jun-2025
Commissioning | COLO 4 | COLO4 XFM01 | MSFT | #3DCD3A | CX12 | CX5300 | MODIFIED | IVC (COLO4 XFM01) | 20-Jun-2025 | 23-Jun-2025
Commissioning | COLO 4 | COLO4 XFM01 | MSFT | #3DCD3A | CX16 | CX5310 | MODIFIED | Yellow Tag (COLO4 XFM01) | 24-Jun-2025 | 25-Jun-2025
Commissioning | COLO 4 | COLO4 XFM01 | MSFT | #3DCD3A | CX17 | CX5330 | MODIFIED | Energization (COLO4 XFM01) | 27-Jun-2025 | 27-Jun-2025
Commissioning | COLO 4 | COLO4 XFM01 | CLAYCO | #EE5A1C | Y9 | CX5380 | MODIFIED | L3 Startup (COLO4 XFM01) | 28-Jun-2025 | 02-Jul-2025
Commissioning | COLO 4 | COLO4 XFM01 | MSFT | #3DCD3A | CX20 | CX5340 | MODIFIED | EPMS SAT (COLO4 XFM01) | 03-Jul-2025 | 07-Jul-2025
Commissioning | COLO 4 | COLO4 XFM01 | MSFT | #3DCD3A | CX19 | CX5390 | MODIFIED | IR SCANS (COLO4 XFM01) | 03-Jul-2025 | 03-Jul-2025
Commissioning | COLO 4 | COLO4 XFM01 | CLAYCO | #EE5A1C | Y10 | CX5350 | MODIFIED | L3 PFC (COLO4 XFM01) | 08-Jul-2025 | 09-Jul-2025
Commissioning | COLO 4 | COLO4 XFM01 | MSFT | #3DCD3A | CX22 | CX5280 | MODIFIED | Green Tag (COLO4 XFM01) | 10-Jul-2025 | 10-Jul-2025
Commissioning | COLO 4 | COLO4 PNL02 | MSFT | #3DCD3A | CX7 | CX5610 | MODIFIED | MEP Test/Pre Startup Installer (COLO4-PNL02) | 06-Jun-2025 | 10-Jun-2025
Commissioning | COLO 4 | COLO4 PNL02 | MSFT | #3DCD3A | CX10 | CX5540 | MODIFIED | FOD Clean (COLO4-PNL02) | 08-Jul-2025 | 09-Jul-2025
Commissioning | COLO 4 | COLO4 PNL02 | CLAYCO | #EE5A1C | Y11 | CX5550 | MODIFIED | L2 QA/QC FOD (COLO4-PNL02) | 10-Jul-2025 | 11-Jul-2025
Commissioning | COLO 4 | COLO4 PNL02 | MSFT | #3DCD3A | CX12 | CX5560 | MODIFIED | IVC (COLO4-PNL02) | 12-Jul-2025 | 15-Jul-2025
Commissioning | COLO 4 | COLO4 PNL02 | MSFT | #3DCD3A | CX16 | CX5570 | MODIFIED | Yellow Tag (COLO4-PNL02) | 16-Jul-2025 | 17-Jul-2025
Commissioning | COLO 4 | COLO4 PNL02 | MSFT | #3DCD3A | CX17 | CX5580 | MODIFIED | Energization (COLO4-PNL02) | 18-Jul-2025 | 19-Jul-2025
Commissioning | COLO 4 | COLO4 PNL02 | CLAYCO | #EE5A1C | Y9 | CX5620 | MODIFIED | L3 Startup (COLO4-PNL02) | 21-Jul-2025 | 25-Jul-2025
Commissioning | COLO 4 | COLO4 PNL02 | MSFT | #3DCD3A | CX21 | CX5600 | MODIFIED | L3 PFC (COLO4-PNL02) | 28-Jul-2025 | 28-Jul-2025
Commissioning | COLO 4 | COLO4 PNL02 | MSFT | #3DCD3A | CX22 | CX5530 | MODIFIED | Green Tag (COLO4-PNL02) | 29-Jul-2025 | 29-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX12 | CX5760 | MODIFIED | IVC (COLO4-CE1/CE2-MSB01 and TCP01) | 27-Jun-2025 | 30-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX16 | CX5770 | MODIFIED | Yellow Tag (COLO4-CE1/CE2-MSB01 and TCP01) | 01-Jul-2025 | 02-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX17 | CX5780 | MODIFIED | Energization (COLO4-CE1/CE2-MSB01 and TCP01) | 03-Jul-2025 | 03-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX18 | CX5820 | MODIFIED | L3 Startup (COLO4-CE1/CE2-MSB01 and TCP01) | 07-Jul-2025 | 10-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX19 | CX5790 | MODIFIED | IR Scans (COLO4-CE1/CE2-MSB01 and TCP01) | 11-Jul-2025 | 11-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX20 | CX5830 | MODIFIED | EPMS SAT (COLO4-CE1/CE2-MSB01 and TCP01) | 11-Jul-2025 | 11-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-MSB01 and TCP01 | CLAYCO | #EE5A1C | Y10 | CX5800 | MODIFIED | L3 PFC (COLO4-CE1/CE2-MSB01 and TCP01) | 12-Jul-2025 | 12-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX22 | CX5730 | MODIFIED | Green Tag (COLO4-CE1/CE2-MSB01 and TCP01) | 14-Jul-2025 | 14-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX8 | CX5970 | MODIFIED | Pre Startup Vendor (COLO4-CE3/CE4-MSB01 and TCP01) | 21-Jun-2025 | 23-Jun-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX9 | CX5980 | MODIFIED | Control Checks (COLO4-CE3/CE4-MSB01 and TCP01) | 24-Jun-2025 | 26-Jun-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX10 | CX5870 | MODIFIED | FOD Clean (COLO4-CE3/CE4-MSB01 and TCP01) | 28-Jun-2025 | 30-Jun-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-MSB01 and TCP01 | CLAYCO | #EE5A1C | Y11 | CX5880 | MODIFIED | L2 QA/QC FOD (COLO4-CE3/CE4-MSB01 and TCP01) | 01-Jul-2025 | 02-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX12 | CX5890 | MODIFIED | IVC (COLO4-CE3/CE4-MSB01 and TCP01) | 03-Jul-2025 | 08-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX16 | CX5900 | MODIFIED | Yellow Tag (COLO4-CE3/CE4-MSB01 and TCP01) | 09-Jul-2025 | 10-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX17 | CX5910 | MODIFIED | Energization (COLO4-CE3/CE4-MSB01 and TCP01) | 11-Jul-2025 | 12-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-MSB01 and TCP01 | CLAYCO | #EE5A1C | Y9 | CX5950 | MODIFIED | L3 Startup (COLO4-CE3/CE4-MSB01 and TCP01) | 14-Jul-2025 | 17-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX19 | CX5920 | MODIFIED | IR Scans (COLO4-CE3/CE4-MSB01 and TCP01) | 18-Jul-2025 | 18-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX20 | CX5960 | MODIFIED | EPMS SAT (COLO4-CE3/CE4-MSB01 and TCP01) | 18-Jul-2025 | 18-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-MSB01 and TCP01 | CLAYCO | #EE5A1C | Y10 | CX5930 | MODIFIED | L3 PFC (COLO4-CE3/CE4-MSB01 and TCP01) | 19-Jul-2025 | 19-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX22 | CX5860 | MODIFIED | Green Tag (COLO4-CE3/CE4-MSB01 and TCP01) | 21-Jul-2025 | 21-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX9 | CX6110 | MODIFIED | Control Checks (COLO4-CE1/CE2-ADP01) | 08-Jul-2025 | 08-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX17 | CX6040 | MODIFIED | Energization (COLO4-CE1/CE2-ADP01) | 09-Jul-2025 | 10-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ADP01 | CLAYCO | #EE5A1C | Y9 | CX6080 | MODIFIED | L3 Startup (COLO4-CE1/CE2-ADP01) | 12-Jul-2025 | 14-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX19 | CX6050 | MODIFIED | IR Scans (COLO4-CE1/CE2-ADP01) | 15-Jul-2025 | 15-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX20 | CX6090 | MODIFIED | EPMS SAT (COLO4-CE1/CE2-ADP01) | 15-Jul-2025 | 15-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ADP01 | CLAYCO | #EE5A1C | Y10 | CX6060 | MODIFIED | L3 PFC (COLO4-CE1/CE2-ADP01) | 16-Jul-2025 | 18-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX22 | CX5990 | MODIFIED | Green Tag (COLO4-CE1/CE2-ADP01) | 19-Jul-2025 | 22-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX7 | CX6200 | MODIFIED | MEP Test/Pre Startup Installer (COLO4-CE3/CE4-ADP01) | 24-Apr-2025 | 28-Jun-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX9 | CX6240 | MODIFIED | Control Checks (COLO4-CE3/CE4-ADP01) | 15-Jul-2025 | 15-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX17 | CX6170 | MODIFIED | Energization (COLO4-CE3/CE4-ADP01) | 16-Jul-2025 | 17-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-ADP01 | CLAYCO | #EE5A1C | Y9 | CX6210 | MODIFIED | L3 Startup (COLO4-CE3/CE4-ADP01) | 18-Jul-2025 | 19-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX19 | CX6180 | MODIFIED | IR Scans (COLO4-CE3/CE4-ADP01) | 21-Jul-2025 | 21-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX20 | CX6220 | MODIFIED | EPMS SAT (COLO4-CE3/CE4-ADP01) | 21-Jul-2025 | 21-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-ADP01 | CLAYCO | #EE5A1C | Y10 | CX6190 | MODIFIED | L3 PFC (COLO4-CE3/CE4-ADP01) | 22-Jul-2025 | 24-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX22 | CX6120 | MODIFIED | Green Tag (COLO4-CE3/CE4-ADP01) | 25-Jul-2025 | 28-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX7 | CX6330 | MODIFIED | MEP Test/Pre Startup Installer (COLO4-CE1/CE2(UPS01-02)) | 01-May-2025 | 28-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX12 | CX6280 | MODIFIED | IVC (COLO4-CE1/CE2(UPS01-02)) | 12-Jul-2025 | 14-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX16 | CX6290 | MODIFIED | Yellow Tag (COLO4-CE1/CE2(UPS01-02)) | 15-Jul-2025 | 16-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX9 | CX6370 | MODIFIED | Control Checks (COLO4-CE1/CE2(UPS01-02)) | 18-Jul-2025 | 19-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX17 | CX6300 | MODIFIED | Energization (COLO4-CE1/CE2(UPS01-02)) | 21-Jul-2025 | 22-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2(UPS01-02) | CLAYCO | #EE5A1C | Y9 | CX6340 | MODIFIED | L3 Startup (COLO4-CE1/CE2(UPS01-02)) | 23-Jul-2025 | 28-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX20 | CX6350 | MODIFIED | EPMS SAT (COLO4-CE1/CE2(UPS01-02)) | 29-Jul-2025 | 30-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX19 | CX6310 | MODIFIED | IR Scans (COLO4-CE1/CE2(UPS01-02)) | 06-Aug-2025 | 07-Aug-2025
Commissioning | COLO 4 | COLO4-CE1/CE2(UPS01-02) | CLAYCO | #EE5A1C | Y10 | CX6320 | MODIFIED | L3 PFC (COLO4-CE1/CE2(UPS01-02)) | 08-Aug-2025 | 11-Aug-2025
Commissioning | COLO 4 | COLO4-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX10 | CX6390 | MODIFIED | FOD Clean (COLO4-CE3/CE4(UPS01-02)) | 12-Jul-2025 | 14-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4(UPS01-02) | CLAYCO | #EE5A1C | Y11 | CX6400 | MODIFIED | L2 QA/QC FOD (COLO4-CE3/CE4(UPS01-02)) | 15-Jul-2025 | 16-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX12 | CX6410 | MODIFIED | IVC (COLO4-CE3/CE4(UPS01-02)) | 17-Jul-2025 | 18-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX16 | CX6420 | MODIFIED | Yellow Tag (COLO4-CE3/CE4(UPS01-02)) | 19-Jul-2025 | 21-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX9 | CX6500 | MODIFIED | Control Checks (COLO4-CE3/CE4(UPS01-02)) | 23-Jul-2025 | 24-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX17 | CX6430 | MODIFIED | Energization (COLO4-CE3/CE4(UPS01-02)) | 25-Jul-2025 | 28-Jul-2025
Commissioning | COLO 4 | COLO4-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX18 | CX6470 | MODIFIED | L3 Startup (COLO4-CE3/CE4(UPS01-02)) | 29-Jul-2025 | 01-Aug-2025
Commissioning | COLO 4 | COLO4-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX19 | CX6440 | MODIFIED | IR Scans (COLO4-CE3/CE4(UPS01-02)) | 02-Aug-2025 | 04-Aug-2025
Commissioning | COLO 4 | COLO4-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX20 | CX6480 | MODIFIED | EPMS SAT (COLO4-CE3/CE4(UPS01-02)) | 02-Aug-2025 | 04-Aug-2025
Commissioning | COLO 4 | COLO4-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX7 | CX6590 | MODIFIED | MEP Test/Pre Startup Installer (COLO4-CE1/CE2-PDU(01-06)) | 12-May-2025 | 28-Jun-2025
Commissioning | COLO 4 | COLO4-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX8 | CX6610 | MODIFIED | Pre Startup Vendor (COLO4-CE1/CE2-PDU(01-06)) | 30-Jun-2025 | 02-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX10 | CX6520 | MODIFIED | FOD Clean (COLO4-CE1/CE2-PDU(01-06)) | 03-Jul-2025 | 07-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y11 | CX6530 | MODIFIED | L2 QA/QC FOD (COLO4-CE1/CE2-PDU(01-06)) | 08-Jul-2025 | 09-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX12 | CX6540 | MODIFIED | IVC (COLO4-CE1/CE2-PDU(01-06)) | 10-Jul-2025 | 14-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX16 | CX6550 | MODIFIED | Yellow Tag (COLO4-CE1/CE2-PDU(01-06)) | 15-Jul-2025 | 16-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX9 | CX6620 | MODIFIED | Control Checks (COLO4-CE1/CE2-PDU(01-06)) | 18-Jul-2025 | 22-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX17 | CX6560 | MODIFIED | Energization (COLO4-CE1/CE2-PDU(01-06)) | 23-Jul-2025 | 23-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX19 | CX6570 | MODIFIED | IR Scans (COLO4-CE1/CE2-PDU(01-06)) | 24-Jul-2025 | 28-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX20 | CX6600 | MODIFIED | EPMS SAT (COLO4-CE1/CE2-PDU(01-06)) | 31-Jul-2025 | 02-Aug-2025
Commissioning | COLO 4 | COLO4-CE1-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y10 | CX6580 | MODIFIED | L3 PFC (COLO4-CE1/CE2-PDU(01-06)) | 04-Aug-2025 | 06-Aug-2025
Commissioning | COLO 4 | COLO4-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX22 | CX6510 | MODIFIED | Green Tag (COLO4-CE1/CE2-PDU(01-06)) | 07-Aug-2025 | 09-Aug-2025
Commissioning | COLO 4 | COLO4-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX7 | CX6830 | MODIFIED | MEP Test/Pre Startup Installer (COLO4-CE3/CE4-PDU(01-06)) | 14-May-2025 | 12-Jul-2025
Commissioning | COLO 4 | COLO4-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX8 | CX6850 | MODIFIED | Pre Startup Vendor (COLO4-CE3/CE4-PDU(01-06)) | 14-Jul-2025 | 16-Jul-2025
Commissioning | COLO 4 | COLO4-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX10 | CX6760 | MODIFIED | FOD Clean (COLO4-CE3/CE4-PDU(01-06)) | 17-Jul-2025 | 18-Jul-2025
Commissioning | COLO 4 | COLO4-CE3-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y11 | CX6770 | MODIFIED | L2 QA/QC FOD (COLO4-CE3/CE4-PDU(01-06)) | 19-Jul-2025 | 21-Jul-2025
Commissioning | COLO 4 | COLO4-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX12 | CX6780 | MODIFIED | IVC (COLO4-CE3/CE4-PDU(01-06)) | 22-Jul-2025 | 25-Jul-2025
Commissioning | COLO 4 | COLO4-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX16 | CX6790 | MODIFIED | Yellow Tag (COLO4-CE3/CE4-PDU(01-06)) | 28-Jul-2025 | 29-Jul-2025
Commissioning | COLO 4 | COLO4-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX9 | CX6860 | MODIFIED | Control Checks (COLO4-CE3/CE4-PDU(01-06)) | 30-Jul-2025 | 04-Aug-2025
Commissioning | COLO 4 | COLO4-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX17 | CX6800 | MODIFIED | Energization (COLO4-CE3/CE4-PDU(01-06)) | 05-Aug-2025 | 05-Aug-2025
Commissioning | COLO 4 | COLO4-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX19 | CX6810 | MODIFIED | IR Scans (COLO4-CE3/CE4-PDU(01-06)) | 06-Aug-2025 | 09-Aug-2025
Commissioning | COLO 4 | COLO4-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX20 | CX6840 | MODIFIED | EPMS SAT (COLO4-CE3/CE4-PDU(01-06)) | 13-Aug-2025 | 15-Aug-2025
Commissioning | COLO 4 | COLO4-CE3-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y10 | CX6820 | MODIFIED | L3 PFC (COLO3-CE3/CE4-PDU(01-06)) | 18-Aug-2025 | 20-Aug-2025
Commissioning | COLO 4 | COLO4-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX22 | CX6750 | MODIFIED | Green Tag (COLO3-CE3/CE4-PDU(01-06)) | 21-Aug-2025 | 23-Aug-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX7 | CX7070 | MODIFIED | MEP Test/Pre Startup Installer (COLO4-CE1/CE2-GPC01) | 22-Apr-2025 | 21-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX8 | CX7090 | MODIFIED | Pre Startup Vendor (COLO4-CE1/CE2-GPC01) | 23-Jun-2025 | 27-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX9 | CX7100 | MODIFIED | Control Checks (COLO4-CE1/CE2-GPC01) | 28-Jun-2025 | 30-Jun-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX10 | CX7000 | MODIFIED | FOD Clean (COLO4-CE1/CE2-GPC01) | 01-Jul-2025 | 02-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | CLAYCO | #EE5A1C | Y11 | CX7010 | MODIFIED | L2 QA/QC FOD (COLO4-CE1/CE2-GPC01) | 03-Jul-2025 | 07-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX12 | CX7020 | MODIFIED | IVC (COLO4-CE1/CE2-GPC01) | 08-Jul-2025 | 10-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX16 | CX7030 | MODIFIED | Yellow Tag (COLO4-CE1/CE2-GPC01) | 11-Jul-2025 | 12-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX17 | CX7040 | MODIFIED | Energization (COLO4-CE1/CE2-GPC01) | 14-Jul-2025 | 14-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | CLAYCO | #EE5A1C | Y9 | CX7050 | MODIFIED | L3 Startup (COLO4-CE1/CE2-GPC01) | 15-Jul-2025 | 16-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX19 | CX7060 | MODIFIED | IR SCANS (COLO4-CE1/CE2-GPC01) | 17-Jul-2025 | 21-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX23 | CX7080 | MODIFIED | Load Banking (COLO4-CE1/CE2-GPC01) | 17-Jul-2025 | 21-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX20 | CX6990 | MODIFIED | EPMS SAT (COLO4-CE1/CE2-GPC01) | 22-Jul-2025 | 25-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | CLAYCO | #EE5A1C | Y10 | CX7110 | MODIFIED | L3 PFC (COLO4-CE1/CE2-GPC01) | 28-Jul-2025 | 30-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX22 | CX7120 | MODIFIED | Green Tag (COLO4-CE1/CE2-GPC01) | 31-Jul-2025 | 02-Aug-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX7 | CX7210 | MODIFIED | MEP Test/Pre Startup Installer (COLO4-CE3/CE4-GPC01) | 25-Apr-2025 | 28-Jun-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX8 | CX7230 | MODIFIED | Pre Startup Vendor (COLO4-CE3/CE4-GPC01) | 30-Jun-2025 | 07-Jul-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX9 | CX7240 | MODIFIED | Control Checks (COLO4-CE3/CE4-GPC01) | 08-Jul-2025 | 09-Jul-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX10 | CX7140 | MODIFIED | FOD Clean (COLO4-CE3/CE4-GPC01) | 10-Jul-2025 | 11-Jul-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | CLAYCO | #EE5A1C | Y11 | CX7150 | MODIFIED | L2 QA/QC FOD (COLO4-CE3/CE4-GPC01) | 12-Jul-2025 | 14-Jul-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX12 | CX7160 | MODIFIED | IVC (COLO4-CE3/CE4-GPC01) | 15-Jul-2025 | 17-Jul-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX16 | CX7170 | MODIFIED | Yellow Tag (COLO4-CE3/CE4-GPC01) | 18-Jul-2025 | 19-Jul-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX19 | CX7200 | MODIFIED | IR SCANS (COLO4-CE3/CE4-GPC01) | 22-Jul-2025 | 25-Jul-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX23 | CX7220 | MODIFIED | Load Banking (COLO4-CE3/CE4-GPC01) | 22-Jul-2025 | 25-Jul-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX20 | CX7130 | MODIFIED | EPMS SAT (COLO4-CE3/CE4-GPC01) | 28-Jul-2025 | 31-Jul-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | CLAYCO | #EE5A1C | Y10 | CX7250 | MODIFIED | L3 PFC (COLO4-CE3/CE4-GPC01) | 01-Aug-2025 | 04-Aug-2025
Commissioning | COLO 4 | COLO4-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX22 | CX7260 | MODIFIED | Green Tag (COLO4-CE3/CE4-GPC01) | 06-Aug-2025 | 08-Aug-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX7 | CX7360 | MODIFIED | MEP Test/Pre Startup Installer (CHI11-COLO4-CE3-LBP01/LBT01) | 16-Jun-2025 | 28-Jun-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX8 | CX7270 | MODIFIED | Pre Startup Vendor (CHI11-COLO4-CE3-LBP01/LBT01) | 30-Jun-2025 | 01-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX10 | CX7290 | MODIFIED | FOD Clean (CHI11-COLO4-CE3-LBP01/LBT01) | 02-Jul-2025 | 02-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3-LBP01/LBT01 | CLAYCO | #EE5A1C | Y11 | CX7300 | MODIFIED | L2 QA/QC FOD (CHI11-COLO4-CE3-LBP01/LBT01) | 03-Jul-2025 | 07-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX12 | CX7310 | MODIFIED | IVC (CHI11-COLO4-CE3-LBP01/LBT01) | 08-Jul-2025 | 09-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX16 | CX7320 | MODIFIED | Yellow Tag (CHI11-COLO4-CE3-LBP01/LBT01) | 10-Jul-2025 | 11-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX7 | CX7480 | MODIFIED | MEP Test/Pre Startup Installer (COLO4-CE1/CE4-ATS(01-06)) | 07-May-2025 | 07-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX8 | CX7390 | MODIFIED | Pre Startup Vendor (COLO4-CE1/CE4-ATS(01-06)) | 08-Jul-2025 | 14-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX10 | CX7410 | MODIFIED | FOD Clean (COLO4-CE1/CE4-ATS(01-06)) | 15-Jul-2025 | 17-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ATS(01-06) | CLAYCO | #EE5A1C | Y11 | CX7420 | MODIFIED | L2 QA/QC FOD (COLO4-CE1/CE4-ATS(01-06)) | 18-Jul-2025 | 21-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX12 | CX7430 | MODIFIED | IVC (COLO4-CE1/CE4-ATS(01-06)) | 22-Jul-2025 | 24-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX16 | CX7440 | MODIFIED | Yellow Tag (COLO4-CE1/CE4-ATS(01-06)) | 25-Jul-2025 | 28-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX17 | CX7450 | MODIFIED | Energization (COLO4-CE1/CE4-ATS(01-06)) | 05-Aug-2025 | 06-Aug-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX19 | CX7460 | MODIFIED | IR Scans (COLO4-CE1/CE4-ATS(01-06)) | 07-Aug-2025 | 11-Aug-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ATS(01-06) | CLAYCO | #EE5A1C | Y9 | CX7490 | MODIFIED | L3 Startup (COLO4-CE1/CE4-ATS(01-06)) | 07-Aug-2025 | 13-Aug-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX20 | CX7500 | MODIFIED | EPMS SAT (COLO4-CE1/CE4-ATS(01-06)) | 14-Aug-2025 | 18-Aug-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ATS(01-06) | CLAYCO | #EE5A1C | Y10 | CX7470 | MODIFIED | L3 PFC (COLO4-CE1/CE4-ATS(01-06)) | 19-Aug-2025 | 22-Aug-2025
Commissioning | COLO 4 | COLO4-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX22 | CX7400 | MODIFIED | Green Tag (COLO4-CE1/CE4-ATS(01-06)) | 23-Aug-2025 | 27-Aug-2025
Commissioning | COLO 4 | COLO4-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX7 | CX7710 | MODIFIED | MEP Test/Pre Startup Installer (COLO4-CE1/CE4 LV Panel and XFM) | 09-May-2025 | 07-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX10 | CX7640 | MODIFIED | FOD Clean (COLO4-CE1/CE4 LV Panel and XFM) | 08-Jul-2025 | 09-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2 LV Panel and XFM | CLAYCO | #EE5A1C | Y11 | CX7650 | MODIFIED | L2 QA/QC FOD (COLO4-CE1/CE4 LV Panel and XFM) | 10-Jul-2025 | 11-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX12 | CX7660 | MODIFIED | IVC (COLO4-CE1/CE4 LV Panel and XFM) | 12-Jul-2025 | 15-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX16 | CX7670 | MODIFIED | Yellow Tag (COLO4-CE1/CE4 LV Panel and XFM) | 16-Jul-2025 | 17-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX17 | CX7680 | MODIFIED | Energization (COLO4-CE1/CE4 LV Panel and XFM) | 18-Jul-2025 | 19-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX19 | CX7690 | MODIFIED | IR Scans (COLO4-CE1/CE4 LV Panel and XFM) | 21-Jul-2025 | 25-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2 LV Panel and XFM | CLAYCO | #EE5A1C | Y9 | CX7720 | MODIFIED | L3 Startup (COLO4-CE1/CE4 LV Panel and XFM) | 21-Jul-2025 | 25-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2 LV Panel and XFM | CLAYCO | #EE5A1C | Y10 | CX7700 | MODIFIED | L3 PFC (COLO4-CE1/CE4 LV Panel and XFM) | 28-Jul-2025 | 28-Jul-2025
Commissioning | COLO 4 | COLO4-CE1/CE2 LV Panel and XFM | MSFT | #3DCD3A | CX22 | CX7630 | MODIFIED | Green Tag (COLO4-CE1/CE4 LV Panel and XFM) | 29-Jul-2025 | 29-Jul-2025
Commissioning | COLO 4 | COLO4-Loadbank Busway | CLAYCO | #EE5A1C | Y11 | CX7860 | MODIFIED | L2 QA/QC FOD (COLO4-CE1/CE2-ATS(01-06)) | 20-May-2025 | 22-May-2025
Commissioning | COLO 4 | COLO4-Loadbank Busway | MSFT | #3DCD3A | CX12 | CX7870 | MODIFIED | IVC (COLO4-CE1/CE2-ATS(01-06)) | 23-May-2025 | 28-May-2025
Commissioning | COLO 4 | COLO4-Loadbank Busway | MSFT | #3DCD3A | CX16 | CX7880 | MODIFIED | Yellow Tag (COLO4-CE1/CE2-ATS(01-06)) | 02-Jun-2025 | 06-Jun-2025
Commissioning | COLO 4 | COLO4-Loadbank Busway | MSFT | #3DCD3A | CX17 | CX7890 | MODIFIED | Energization (COLO4-CE1/CE2-ATS(01-06)) | 15-Jul-2025 | 15-Jul-2025
Commissioning | COLO 4 | COLO4-Loadbank Busway | MSFT | #3DCD3A | CX19 | CX7900 | MODIFIED | IR Scans (COLO4-CE1/CE2-ATS(01-06)) | 16-Jul-2025 | 17-Jul-2025
Commissioning | COLO 4 | COLO4-Loadbank Busway | CLAYCO | #EE5A1C | Y9 | CX7930 | MODIFIED | L3 Startup (COLO4-CE1/CE2-ATS(01-06)) | 16-Jul-2025 | 21-Jul-2025
Commissioning | COLO 4 | COLO4-Loadbank Busway | CLAYCO | #EE5A1C | Y10 | CX7910 | MODIFIED | L3 PFC (COLO4-CE1/CE2-ATS(01-06)) | 22-Jul-2025 | 22-Jul-2025
Commissioning | COLO 4 | COLO4-Loadbank Busway | MSFT | #3DCD3A | CX22 | CX7840 | MODIFIED | Green Tag (COLO4-CE1/CE2-ATS(01-06)) | 23-Jul-2025 | 25-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-AHU(01-08) | MSFT | #3DCD3A | CX7 | CX8030 | MODIFIED | MEP Test/Pre Startup Installer (COLO4-CE1-AHU(01-08)) | 18-Apr-2025 | 08-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-AHU(01-08) | MSFT | #3DCD3A | CX8 | CX7950 | MODIFIED | Pre Startup Vendor (COLO4-CE1-AHU(01-08)) (Using NPW TEMP SKID) | 09-Jul-2025 | 17-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-AHU(01-08) | MSFT | #3DCD3A | CX10 | CX7970 | MODIFIED | FOD Clean (COLO4-CE1-AHU(01-08)) | 18-Jul-2025 | 21-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-AHU(01-08) | CLAYCO | #EE5A1C | Y11 | CX7980 | MODIFIED | L2 QA/QC FOD (COLO4-CE1-AHU(01-08)) | 22-Jul-2025 | 23-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-AHU(01-08) | MSFT | #3DCD3A | CX12 | CX7990 | MODIFIED | IVC (COLO4-CE1-AHU(01-08)) | 24-Jul-2025 | 28-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-AHU(01-08) | MSFT | #3DCD3A | CX16 | CX8000 | MODIFIED | Yellow Tag (COLO4-CE1-AHU(01-08)) | 29-Jul-2025 | 30-Jul-2025
Commissioning | COLO 4 | COLO4-CE1-AHU(01-08) | MSFT | #3DCD3A | CX17 | CX8010 | MODIFIED | Energization (COLO4-CE1-AHU(01-08)) | 05-Aug-2025 | 06-Aug-2025
Commissioning | COLO 4 | COLO4-CE1-AHU(01-08) | CLAYCO | #EE5A1C | Y9 | CX8040 | MODIFIED | L3 Startup (COLO4-CE1-AHU(01-08)) (Using NPW TEMP SKID) | 07-Aug-2025 | 12-Aug-2025
Commissioning | COLO 4 | COLO4-CE1-AHU(01-08) | MSFT | #3DCD3A | CX24 | CX8050 | MODIFIED | BAS SAT & TAB (COLO4-CE1-AHU(01-08)) | 13-Aug-2025 | 18-Aug-2025
Commissioning | COLO 4 | COLO4-CE1-AHU(01-08) | CLAYCO | #EE5A1C | Y10 | CX8020 | MODIFIED | L3 PFC (COLO4-CE1-AHU(01-08)) | 27-Aug-2025 | 29-Aug-2025
Commissioning | COLO 4 | COLO4-CE1-AHU(01-08) | MSFT | #3DCD3A | CX22 | CX7960 | MODIFIED | Green Tag (COLO4-CE1-AHU(01-08)) | 30-Aug-2025 | 03-Sep-2025
Commissioning | COLO 4 | COLO4-Control Panel and CC | MSFT | #3DCD3A | CX7 | CX8450 | MODIFIED | MEP Test/Pre Startup Installer (COLO4-Control Panel and CC) | 22-Apr-2025 | 21-Jun-2025
Commissioning | COLO 4 | COLO4-Control Panel and CC | MSFT | #3DCD3A | CX10 | CX8400 | MODIFIED | FOD Clean (COLO4-Control Panel and CC) | 23-Jun-2025 | 25-Jun-2025
Commissioning | COLO 4 | COLO4-Control Panel and CC | CLAYCO | #EE5A1C | Y11 | CX8410 | MODIFIED | L2 QA/QC FOD (COLO4-Control Panel and CC) | 26-Jun-2025 | 28-Jun-2025
Commissioning | COLO 4 | COLO4-Control Panel and CC | MSFT | #3DCD3A | CX12 | CX8420 | MODIFIED | IVC (COLO4-Control Panel and CC) | 30-Jun-2025 | 02-Jul-2025
Commissioning | COLO 4 | COLO4-Control Panel and CC | MSFT | #3DCD3A | CX16 | CX8430 | MODIFIED | Yellow Tag (COLO4-Control Panel and CC) | 03-Jul-2025 | 08-Jul-2025
Commissioning | COLO 4 | COLO4-Control Panel and CC | MSFT | #3DCD3A | CX17 | CX8440 | MODIFIED | Energization (COLO4-Control Panel and CC) | 17-Jul-2025 | 18-Jul-2025
Commissioning | COLO 4 | COLO4-Control Panel and CC | MSFT | #3DCD3A | CX25 | CX8460 | MODIFIED | BAS SAT (COLO4-Control Panel and CC) | 19-Jul-2025 | 22-Jul-2025
Commissioning | COLO 4 | COLO4-Control Panel and CC | MSFT | #3DCD3A | CX22 | CX8390 | MODIFIED | Green Tag (COLO4-Control Panel and CC) | 23-Jul-2025 | 23-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-AC/CU(01-02) | MSFT | #3DCD3A | CX7 | CX8530 | MODIFIED | MEP Test/Pre Startup Installer (CHI11-COLO4-AC/CU(01-02)) | 28-Jun-2025 | 22-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-AC/CU(01-02) | MSFT | #3DCD3A | CX10 | CX8480 | MODIFIED | FOD Clean (CHI11-COLO4-AC/CU(01-02)) | 23-Jul-2025 | 24-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-AC/CU(01-02) | CLAYCO | #EE5A1C | Y11 | CX8490 | MODIFIED | L2 QA/QC FOD (CHI11-COLO4-AC/CU(01-02)) | 25-Jul-2025 | 28-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-AC/CU(01-02) | MSFT | #3DCD3A | CX12 | CX8500 | MODIFIED | IVC (CHI11-COLO4-AC/CU(01-02)) | 29-Jul-2025 | 30-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-AC/CU(01-02) | MSFT | #3DCD3A | CX16 | CX8510 | MODIFIED | Yellow Tag (CHI11-COLO4-AC/CU(01-02)) | 31-Jul-2025 | 01-Aug-2025
Commissioning | COLO 4 | CHI11-COLO4-AC/CU(01-02) | MSFT | #3DCD3A | CX17 | CX8520 | MODIFIED | Energization (CHI11-COLO4-AC/CU(01-02)) | 02-Aug-2025 | 02-Aug-2025
Commissioning | COLO 4 | CHI11-COLO4-AC/CU(01-02) | CLAYCO | #EE5A1C | Y9 | CX8540 | MODIFIED | L3 Startup (CHI11-COLO4-AC/CU(01-02)) | 04-Aug-2025 | 09-Aug-2025
Commissioning | COLO 4 | CHI11-COLO4-AC/CU(01-02) | MSFT | #3DCD3A | CX25 | CX8470 | MODIFIED | BAS SAT (CHI11-COLO4-AC/CU(01-02)) | 11-Aug-2025 | 12-Aug-2025
Commissioning | COLO 4 | CHI11-COLO4-AC/CU(01-02) | MSFT | #3DCD3A | CX22 | CX8550 | MODIFIED | Green Tag (CHI11-COLO4-AC/CU(01-02)) | 13-Aug-2025 | 18-Aug-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | MSFT | #3DCD3A | CX7 | CX8610 | MODIFIED | MEP Test/Pre Startup Installer (CHI11-COLO4-CE2/CE4-UH01) | 10-Jun-2025 | 26-Jun-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | MSFT | #3DCD3A | CX10 | CX8560 | MODIFIED | FOD Clean (CHI11-COLO4-CE2/CE4-UH01) | 27-Jun-2025 | 27-Jun-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | CLAYCO | #EE5A1C | Y11 | CX8570 | MODIFIED | L2 QA/QC FOD (CHI11-COLO4-CE2/CE4-UH01) | 28-Jun-2025 | 28-Jun-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | MSFT | #3DCD3A | CX12 | CX8580 | MODIFIED | IVC (CHI11-COLO4-CE2/CE4-UH01) | 30-Jun-2025 | 02-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | MSFT | #3DCD3A | CX16 | CX8590 | MODIFIED | Yellow Tag (CHI11-COLO4-CE2/CE4-UH01) | 03-Jul-2025 | 03-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | MSFT | #3DCD3A | CX17 | CX8600 | MODIFIED | Energization (CHI11-COLO4-CE2/CE4-UH01) | 24-Jul-2025 | 24-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | CLAYCO | #EE5A1C | Y10 | CX8620 | MODIFIED | L3 Startup (CHI11-COLO4-CE2/CE4-UH01) | 25-Jul-2025 | 30-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | MSFT | #3DCD3A | CX22 | CX8630 | MODIFIED | Green Tag (CHI11-COLO4-CE2/CE4-UH01) | 31-Jul-2025 | 31-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | MSFT | #3DCD3A | CX17 | CX8690 | MODIFIED | Energization (CH11-COLO4-Water Heater) | 28-Jul-2025 | 28-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | CLAYCO | #EE5A1C | Y9 | CX8710 | MODIFIED | L3 Startup (CH11-COLO4-Water Heater) | 29-Jul-2025 | 02-Aug-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | MSFT | #3DCD3A | CX25 | CX8640 | MODIFIED | BAS SAT (CH11-COLO4-Water Heater) | 04-Aug-2025 | 04-Aug-2025
Commissioning | COLO 4 | CHI11-COLO4-CE2/CE4-UH01 | MSFT | #3DCD3A | CX22 | CX8720 | MODIFIED | Green Tag (CH11-COLO4-Water Heater) | 05-Aug-2025 | 06-Aug-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3/CE4-EF01 | MSFT | #3DCD3A | CX7 | CX8790 | MODIFIED | MEP Test/Pre Startup Installer (COLO4-CE1/CE4-PRV01-02) | 21-May-2025 | 10-Jun-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3/CE4-EF01 | MSFT | #3DCD3A | CX10 | CX8740 | MODIFIED | FOD Clean (COLO4-CE1/CE4-PRV01-02) | 11-Jun-2025 | 12-Jun-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3/CE4-EF01 | CLAYCO | #EE5A1C | Y11 | CX8750 | MODIFIED | L2 QA/QC FOD (COLO4-CE1/CE4-PRV01-02) | 13-Jun-2025 | 13-Jun-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3/CE4-EF01 | MSFT | #3DCD3A | CX16 | CX8770 | MODIFIED | Yellow Tag (COLO4-CE1/CE4-PRV01-02) | 16-Jun-2025 | 16-Jun-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3/CE4-EF01 | MSFT | #3DCD3A | CX17 | CX8780 | MODIFIED | Energization (COLO4-CE1/CE4-PRV01-02) | 28-Jul-2025 | 28-Jul-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3/CE4-EF01 | CLAYCO | #EE5A1C | Y10 | CX8810 | MODIFIED | L3 Startup (COLO4-CE1/CE4-PRV01-02) | 29-Jul-2025 | 08-Aug-2025
Commissioning | COLO 4 | CHI11-COLO4-CE3/CE4-EF01 | MSFT | #3DCD3A | CX22 | CX8811 | MODIFIED | Green Tag (COLO4-CE1/CE4-PRV01-02) | 09-Aug-2025 | 09-Aug-2025
Commissioning | COLO 4 | COLO4-CHI11-NEG-01 | MSFT | #3DCD3A | CX7 | CX8860 | MODIFIED | MEP Test/Pre Startup Installer (CH11-N2G-01) | 06-Jun-2025 | 13-Jun-2025
Commissioning | COLO 4 | COLO4-CHI11-NEG-01 | MSFT | #3DCD3A | CX10 | CX8820 | MODIFIED | FOD Clean (CH11-N2G-01) | 16-Jun-2025 | 16-Jun-2025
Commissioning | COLO 4 | COLO4-CHI11-NEG-01 | CLAYCO | #EE5A1C | Y11 | CX8830 | MODIFIED | L2 QA/QC FOD (CH11-N2G-01) | 17-Jun-2025 | 18-Jun-2025
Commissioning | COLO 4 | COLO4-CHI11-NEG-01 | MSFT | #3DCD3A | CX12 | CX8840 | MODIFIED | IVC (CH11-N2G-01) | 19-Jun-2025 | 20-Jun-2025
Commissioning | COLO 4 | COLO4-CHI11-NEG-01 | MSFT | #3DCD3A | CX16 | CX8850 | MODIFIED | Yellow Tag (CH11-N2G-01) | 21-Jun-2025 | 23-Jun-2025
Commissioning | COLO 4 | COLO4-CHI11-NEG-01 | MSFT | #3DCD3A | CX17 | CX8870 | MODIFIED | Energization (CH11-N2G-01) | 28-Jul-2025 | 28-Jul-2025
Commissioning | COLO 4 | COLO4-CHI11-NEG-01 | CLAYCO | #EE5A1C | Y9 | CX8880 | MODIFIED | L3 Startup (CH11-N2G-01) | 29-Jul-2025 | 29-Jul-2025
Commissioning | COLO 4 | COLO4-CHI11-NEG-01 | MSFT | #3DCD3A | CX25 | CX9060 | MODIFIED | BAS SAT (CH11-N2G-01) | 30-Jul-2025 | 30-Jul-2025
Commissioning | COLO 4 | COLO4-CHI11-NEG-01 | MSFT | #3DCD3A | CX22 | CX9070 | MODIFIED | Green Tag (CH11-N2G-01) | 31-Jul-2025 | 01-Aug-2025
Commissioning | COLO 4 | CHI11-AC-01/02 | MSFT | #3DCD3A | CX7 | CX9030 | MODIFIED | MEP Test/Pre Startup Installer COLO4 (CH11-AC-01/02) | 06-Jun-2025 | 13-Jun-2025
Commissioning | COLO 4 | CHI11-AC-01/02 | MSFT | #3DCD3A | CX10 | CX8980 | MODIFIED | FOD Clean COLO4 (CH11-AC-01/02) | 16-Jun-2025 | 16-Jun-2025
Commissioning | COLO 4 | CHI11-AC-01/02 | CLAYCO | #EE5A1C | Y11 | CX8990 | MODIFIED | L2 QA/QC COLO4 (CH11-AC-01/02) | 17-Jun-2025 | 18-Jun-2025
Commissioning | COLO 4 | CHI11-AC-01/02 | MSFT | #3DCD3A | CX12 | CX9000 | MODIFIED | IVC COLO4 (CH11-AC-01/02) | 19-Jun-2025 | 20-Jun-2025
Commissioning | COLO 4 | CHI11-AC-01/02 | MSFT | #3DCD3A | CX16 | CX9010 | MODIFIED | Yellow Tag COLO4 (CH11-AC-01/02) | 21-Jun-2025 | 23-Jun-2025
Commissioning | COLO 4 | CHI11-AC-01/02 | MSFT | #3DCD3A | CX17 | CX9020 | MODIFIED | Energization COLO4 (CH11-AC-01/02) | 28-Jul-2025 | 28-Jul-2025
Commissioning | COLO 4 | CHI11-AC-01/02 | CLAYCO | #EE5A1C | Y9 | CX9040 | MODIFIED | L3 Startup COLO4 (CH11-AC-01/02) | 29-Jul-2025 | 29-Jul-2025
Commissioning | COLO 4 | CHI11-AC-01/02 | MSFT | #3DCD3A | CX22 | CX9050 | MODIFIED | Green Tag COLO4 (CH11-AC-01/02) | 31-Jul-2025 | 01-Aug-2025
Commissioning | COLO 4 | CHI11-2A/B-HTP02 | MSFT | #3DCD3A | CX7 | CX8950 | MODIFIED | MEP Test/Pre Startup Installer (CHI11-2A/B-HTP02) | 08-Jul-2025 | 08-Jul-2025
Commissioning | COLO 4 | CHI11-2A/B-HTP02 | MSFT | #3DCD3A | CX10 | CX8900 | MODIFIED | FOD Clean (CHI11-2A/B-HTP02) | 09-Jul-2025 | 10-Jul-2025
Commissioning | COLO 4 | CHI11-2A/B-HTP02 | CLAYCO | #EE5A1C | Y11 | CX8910 | MODIFIED | L2 QA/QC FOD (CHI11-2A/B-HTP02) | 11-Jul-2025 | 12-Jul-2025
Commissioning | COLO 4 | CHI11-2A/B-HTP02 | MSFT | #3DCD3A | CX12 | CX8920 | MODIFIED | IVC (CHI11-2A/B-HTP02) | 14-Jul-2025 | 15-Jul-2025
Commissioning | COLO 4 | CHI11-2A/B-HTP02 | MSFT | #3DCD3A | CX16 | CX8930 | MODIFIED | Yellow Tag (CHI11-2A/B-HTP02) | 16-Jul-2025 | 17-Jul-2025
Commissioning | COLO 4 | CHI11-2A/B-HTP02 | MSFT | #3DCD3A | CX17 | CX8940 | MODIFIED | Energization (CHI11-2A/B-HTP02) | 31-Jul-2025 | 31-Jul-2025
Commissioning | COLO 4 | CHI11-2A/B-HTP02 | CLAYCO | #EE5A1C | Y9 | CX8960 | MODIFIED | L3 Startup (CHI11-2A/B-HTP02) | 01-Aug-2025 | 06-Aug-2025
Commissioning | COLO 4 | CHI11-2A/B-HTP02 | MSFT | #3DCD3A | CX25 | CX8890 | MODIFIED | BAS SAT (CHI11-2A/B-HTP02) | 07-Aug-2025 | 13-Aug-2025
Commissioning | COLO 4 | CHI11-2A/B-HTP02 | MSFT | #3DCD3A | CX22 | CX8970 | MODIFIED | Green Tag (CHI11-2A/B-HTP02) | 14-Aug-2025 | 14-Aug-2025
Commissioning | COLO 5 | COLO5 UPM | MSFT | #3DCD3A | CX7 | CX9170 | MODIFIED | MEP Test/Pre Startup Installer (COLO5 UPM) | 06-Jun-2025 | 28-Jun-2025
Commissioning | COLO 5 | COLO5 UPM | MSFT | #3DCD3A | CX8 | CX9080 | MODIFIED | Pre Startup Vendor (COLO5 UPM) | 30-Jun-2025 | 08-Jul-2025
Commissioning | COLO 5 | COLO5 UPM | MSFT | #3DCD3A | CX9 | CX9180 | MODIFIED | Control Checks (COLO5 UPM) | 03-Jul-2025 | 08-Jul-2025
Commissioning | COLO 5 | COLO5 UPM | MSFT | #3DCD3A | CX10 | CX9100 | MODIFIED | FOD Clean (COLO5 UPM) | 09-Jul-2025 | 10-Jul-2025
Commissioning | COLO 5 | COLO5 UPM | CLAYCO | #EE5A1C | Y11 | CX9110 | MODIFIED | L2 QA/QC FOD (COLO5 UPM) | 11-Jul-2025 | 12-Jul-2025
Commissioning | COLO 5 | COLO5 UPM | MSFT | #3DCD3A | CX17 | CX9140 | MODIFIED | Energization (COLO5 UPM) | 19-Jul-2025 | 19-Jul-2025
Commissioning | COLO 5 | COLO5 UPM | MSFT | #3DCD3A | CX21 | CX9190 | MODIFIED | L3 Startup (COLO5 UPM) | 21-Jul-2025 | 25-Jul-2025
Commissioning | COLO 5 | COLO5 UPM | MSFT | #3DCD3A | CX19 | CX9150 | MODIFIED | IR Scans (COLO5 UPM) | 28-Jul-2025 | 28-Jul-2025
Commissioning | COLO 5 | COLO5 UPM | MSFT | #3DCD3A | CX20 | CX9200 | MODIFIED | EPMS SAT (COLO5 UPM) | 28-Jul-2025 | 30-Jul-2025
Commissioning | COLO 5 | COLO5 UPM | CLAYCO | #EE5A1C | Y10 | CX9160 | MODIFIED | L3 PFC (COLO5 UPM) | 31-Jul-2025 | 01-Aug-2025
Commissioning | COLO 5 | COLO5 UPM | MSFT | #3DCD3A | CX22 | CX9090 | MODIFIED | Green Tag (COLO5 UPM) | 02-Aug-2025 | 02-Aug-2025
Commissioning | COLO 5 | COLO5 XFM01 | MSFT | #3DCD3A | CX7 | CX9300 | MODIFIED | MEP Test/Pre Startup Installer (COLO5 XFM01) | 23-May-2025 | 28-Jun-2025
Commissioning | COLO 5 | COLO5 XFM01 | MSFT | #3DCD3A | CX8 | CX9210 | MODIFIED | Pre Startup Vendor (COLO5 XFM01) | 01-Jul-2025 | 02-Jul-2025
Commissioning | COLO 5 | COLO5 XFM01 | MSFT | #3DCD3A | CX10 | CX9310 | MODIFIED | FOD Clean (COLO5 XFM01) | 03-Jul-2025 | 07-Jul-2025
Commissioning | COLO 5 | COLO5 XFM01 | CLAYCO | #EE5A1C | Y11 | CX9230 | MODIFIED | L2 QA/QC (COLO5 XFM01) | 08-Jul-2025 | 10-Jul-2025
Commissioning | COLO 5 | COLO5 XFM01 | MSFT | #3DCD3A | CX12 | CX9240 | MODIFIED | IVC (COLO5 XFM01) | 11-Jul-2025 | 12-Jul-2025
Commissioning | COLO 5 | COLO5 XFM01 | MSFT | #3DCD3A | CX16 | CX9250 | MODIFIED | Yellow Tag (COLO5 XFM01) | 14-Jul-2025 | 15-Jul-2025
Commissioning | COLO 5 | COLO5 XFM01 | MSFT | #3DCD3A | CX17 | CX9270 | MODIFIED | Energization (COLO5 XFM01) | 19-Jul-2025 | 19-Jul-2025
Commissioning | COLO 5 | COLO5 XFM01 | CLAYCO | #EE5A1C | Y9 | CX9320 | MODIFIED | L3 Startup (COLO5 XFM01) | 21-Jul-2025 | 24-Jul-2025
Commissioning | COLO 5 | COLO5 XFM01 | MSFT | #3DCD3A | CX20 | CX9280 | MODIFIED | EPMS SAT (COLO5 XFM01) | 25-Jul-2025 | 28-Jul-2025
Commissioning | COLO 5 | COLO5 XFM01 | MSFT | #3DCD3A | CX19 | CX9330 | MODIFIED | IR SCANS (COLO5 XFM01) | 25-Jul-2025 | 25-Jul-2025
Commissioning | COLO 5 | COLO5 XFM01 | CLAYCO | #EE5A1C | Y10 | CX9290 | MODIFIED | L3 PFC (COLO5 XFM01) | 29-Jul-2025 | 30-Jul-2025
Commissioning | COLO 5 | COLO5 XFM01 | MSFT | #3DCD3A | CX22 | CX9220 | MODIFIED | Green Tag (COLO5 XFM01) | 01-Aug-2025 | 01-Aug-2025
Commissioning | COLO 5 | COLO5 PNL02/XFM04/TCP01 | MSFT | #3DCD3A | CX7 | CX9410 | MODIFIED | MEP Test/Pre Startup Installer COLO5 PNL02 | 18-Jun-2025 | 28-Jun-2025
Commissioning | COLO 5 | COLO5 PNL02/XFM04/TCP01 | MSFT | #3DCD3A | CX10 | CX9350 | MODIFIED | FOD Clean COLO5 PNL02 | 30-Jun-2025 | 01-Jul-2025
Commissioning | COLO 5 | COLO5 PNL02/XFM04/TCP01 | CLAYCO | #EE5A1C | Y11 | CX9360 | MODIFIED | L2 QA/QC COLO5 PNL02 | 02-Jul-2025 | 03-Jul-2025
Commissioning | COLO 5 | COLO5 PNL02/XFM04/TCP01 | MSFT | #3DCD3A | CX12 | CX9370 | MODIFIED | IVC COLO5 PNL02 | 07-Jul-2025 | 09-Jul-2025
Commissioning | COLO 5 | COLO5 PNL02/XFM04/TCP01 | MSFT | #3DCD3A | CX16 | CX9380 | MODIFIED | Yellow Tag COLO5 PNL02 | 10-Jul-2025 | 11-Jul-2025
Commissioning | COLO 5 | COLO5 PNL02/XFM04/TCP01 | MSFT | #3DCD3A | CX17 | CX9390 | MODIFIED | Energization COLO5 PNL02 | 12-Jul-2025 | 14-Jul-2025
Commissioning | COLO 5 | COLO5 PNL02/XFM04/TCP01 | MSFT | #3DCD3A | CX26 | CX9420 | MODIFIED | L3 Startup & IR Scans COLO5 PNL02 | 15-Jul-2025 | 19-Jul-2025
Commissioning | COLO 5 | COLO5 PNL02/XFM04/TCP01 | CLAYCO | #EE5A1C | Y10 | CX9400 | MODIFIED | L3 PFC COLO5 PNL02 | 21-Jul-2025 | 21-Jul-2025
Commissioning | COLO 5 | COLO5 PNL02/XFM04/TCP01 | MSFT | #3DCD3A | CX22 | CX9340 | MODIFIED | Green Tag COLO5 PNL02 | 22-Jul-2025 | 22-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-MSB01 | MSFT | #3DCD3A | CX7 | CX9510 | MODIFIED | MEP Test/Pre Startup Installer (COLO5-CE1/CE2-MSB01 and TCP01) | 30-May-2025 | 12-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-MSB01 | MSFT | #3DCD3A | CX10 | CX9440 | MODIFIED | FOD Clean (COLO5-CE1/CE2-MSB01 and TCP01) | 19-Jul-2025 | 21-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-MSB01 | CLAYCO | #EE5A1C | Y11 | CX9450 | MODIFIED | L2 QA/QC FOD (COLO5-CE1/CE2-MSB01 and TCP01) | 22-Jul-2025 | 23-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-MSB01 | MSFT | #3DCD3A | CX12 | CX9460 | MODIFIED | IVC (COLO5-CE1/CE2-MSB01 and TCP01) | 24-Jul-2025 | 28-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-MSB01 | MSFT | #3DCD3A | CX16 | CX9470 | MODIFIED | Yellow Tag (COLO5-CE1/CE2-MSB01 and TCP01) | 29-Jul-2025 | 30-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-MSB01 | MSFT | #3DCD3A | CX17 | CX9480 | MODIFIED | Energization (COLO5-CE1/CE2-MSB01 and TCP01) | 31-Jul-2025 | 02-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-MSB01 | CLAYCO | #EE5A1C | Y9 | CX9520 | MODIFIED | L3 Startup (COLO5-CE1/CE2-MSB01 and TCP01) | 04-Aug-2025 | 06-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-MSB01 | MSFT | #3DCD3A | CX19 | CX9490 | MODIFIED | IR Scans (COLO5-CE1/CE2-MSB01 and TCP01) | 07-Aug-2025 | 07-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-MSB01 | MSFT | #3DCD3A | CX20 | CX9530 | MODIFIED | EPMS SAT (COLO5-CE1/CE2-MSB01 and TCP01) | 07-Aug-2025 | 07-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-MSB01 | CLAYCO | #EE5A1C | Y10 | CX9500 | MODIFIED | L3 PFC (COLO5-CE1/CE2-MSB01 and TCP01) | 08-Aug-2025 | 08-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-MSB01 | MSFT | #3DCD3A | CX22 | CX9430 | MODIFIED | Green Tag (COLO5-CE1/CE2-MSB01 and TCP01) | 09-Aug-2025 | 09-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-MSB01 | MSFT | #3DCD3A | CX7 | CX9640 | MODIFIED | MEP Test/Pre Startup Installer (COLO5-CE3/CE4-MSB01 and TCP01) | 30-May-2025 | 18-Jul-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-MSB01 | MSFT | #3DCD3A | CX8 | CX9670 | MODIFIED | Pre Startup Vendor (COLO5-CE3/CE4-MSB01 and TCP01) | 19-Jul-2025 | 21-Jul-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-MSB01 | MSFT | #3DCD3A | CX9 | CX9680 | MODIFIED | Control Checks (COLO5-CE3/CE4-MSB01 and TCP01) | 22-Jul-2025 | 24-Jul-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-MSB01 | MSFT | #3DCD3A | CX10 | CX9570 | MODIFIED | FOD Clean (COLO5-CE3/CE4-MSB01 and TCP01) | 25-Jul-2025 | 28-Jul-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-MSB01 | CLAYCO | #EE5A1C | Y11 | CX9580 | MODIFIED | L2 QA/QC FOD (COLO5-CE3/CE4-MSB01 and TCP01) | 29-Jul-2025 | 30-Jul-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-MSB01 | MSFT | #3DCD3A | CX12 | CX9590 | MODIFIED | IVC (COLO5-CE3/CE4-MSB01 and TCP01) | 31-Jul-2025 | 02-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-MSB01 | MSFT | #3DCD3A | CX16 | CX9600 | MODIFIED | Yellow Tag (COLO5-CE3/CE4-MSB01 and TCP01) | 04-Aug-2025 | 05-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-MSB01 | MSFT | #3DCD3A | CX17 | CX9610 | MODIFIED | Energization (COLO5-CE3/CE4-MSB01 and TCP01) | 06-Aug-2025 | 07-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-MSB01 | CLAYCO | #EE5A1C | Y9 | CX9650 | MODIFIED | L3 Startup (COLO5-CE3/CE4-MSB01 and TCP01) | 08-Aug-2025 | 12-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-MSB01 | MSFT | #3DCD3A | CX19 | CX9620 | MODIFIED | IR Scans (COLO5-CE3/CE4-MSB01 and TCP01) | 13-Aug-2025 | 13-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-MSB01 | MSFT | #3DCD3A | CX20 | CX9660 | MODIFIED | EPMS SAT (COLO5-CE3/CE4-MSB01 and TCP01) | 13-Aug-2025 | 13-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-MSB01 | CLAYCO | #EE5A1C | Y10 | CX9630 | MODIFIED | L3 PFC (COLO5-CE3/CE4-MSB01 and TCP01) | 14-Aug-2025 | 14-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-MSB01 | MSFT | #3DCD3A | CX22 | CX9560 | MODIFIED | Green Tag (COLO5-CE3/CE4-MSB01 and TCP01) | 15-Aug-2025 | 15-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX7 | CX9770 | MODIFIED | MEP Test/Pre Startup Installer (COLO5-CE1/CE2-ADP01) | 02-Jun-2025 | 19-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX9 | CX9810 | MODIFIED | Control Checks (COLO5-CE1/CE2-ADP01) | 02-Aug-2025 | 02-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX17 | CX9740 | MODIFIED | Energization (COLO5-CE1/CE2-ADP01) | 04-Aug-2025 | 05-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ADP01 | CLAYCO | #EE5A1C | Y9 | CX9780 | MODIFIED | L3 Startup (COLO5-CE1/CE2-ADP01) | 06-Aug-2025 | 08-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX19 | CX9750 | MODIFIED | IR Scans (COLO5-CE1/CE2-ADP01) | 09-Aug-2025 | 09-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX20 | CX9790 | MODIFIED | EPMS SAT (COLO5-CE1/CE2-ADP01) | 09-Aug-2025 | 09-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ADP01 | CLAYCO | #EE5A1C | Y10 | CX9760 | MODIFIED | L3 PFC (COLO5-CE1/CE2-ADP01) | 11-Aug-2025 | 13-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ADP01 | MSFT | #3DCD3A | CX22 | CX9690 | MODIFIED | Green Tag (COLO5-CE1/CE2-ADP01) | 14-Aug-2025 | 18-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX7 | CX9900 | MODIFIED | MEP Test/Pre Startup Installer (COLO5-CE3/CE4-ADP01) | 30-May-2025 | 25-Jul-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX9 | CX9940 | MODIFIED | Control Checks (COLO5-CE3/CE4-ADP01) | 09-Aug-2025 | 09-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX17 | CX9870 | MODIFIED | Energization (COLO5-CE3/CE4-ADP01) | 11-Aug-2025 | 12-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-ADP01 | CLAYCO | #EE5A1C | Y9 | CX9910 | MODIFIED | L3 Startup (COLO5-CE3/CE4-ADP01) | 13-Aug-2025 | 14-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX19 | CX9880 | MODIFIED | IR Scans (COLO5-CE3/CE4-ADP01) | 15-Aug-2025 | 15-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX20 | CX9920 | MODIFIED | EPMS SAT (COLO5-CE3/CE4-ADP01) | 15-Aug-2025 | 15-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-ADP01 | CLAYCO | #EE5A1C | Y10 | CX9890 | MODIFIED | L3 PFC (COLO5-CE3/CE4-ADP01) | 18-Aug-2025 | 20-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4-ADP01 | MSFT | #3DCD3A | CX22 | CX9820 | MODIFIED | Green Tag (COLO5-CE3/CE4-ADP01) | 21-Aug-2025 | 23-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX7 | CX10030 | MODIFIED | MEP Test/Pre Startup Installer (COLO5-CE1/CE2(UPS01-02)) | 06-Jun-2025 | 25-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX10 | CX9960 | MODIFIED | FOD Clean (COLO5-CE1/CE2(UPS01-02)) | 02-Aug-2025 | 04-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2(UPS01-02) | CLAYCO | #EE5A1C | Y11 | CX9970 | MODIFIED | L2 QA/QC FOD (COLO5-CE1/CE2(UPS01-02)) | 05-Aug-2025 | 06-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX12 | CX9980 | MODIFIED | IVC (COLO5-CE1/CE2(UPS01-02)) | 08-Aug-2025 | 09-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX16 | CX9990 | MODIFIED | Yellow Tag (COLO5-CE1/CE2(UPS01-02)) | 11-Aug-2025 | 12-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX9 | CX10070 | MODIFIED | Control Checks (COLO5-CE1/CE2(UPS01-02)) | 14-Aug-2025 | 15-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX17 | CX10000 | MODIFIED | Energization (COLO5-CE1/CE2(UPS01-02)) | 18-Aug-2025 | 19-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2(UPS01-02) | CLAYCO | #EE5A1C | Y9 | CX10040 | MODIFIED | L3 Startup (COLO5-CE1/CE2(UPS01-02)) | 20-Aug-2025 | 25-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX20 | CX10050 | MODIFIED | EPMS SAT (COLO5-CE1/CE2(UPS01-02)) | 26-Aug-2025 | 27-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX19 | CX10010 | MODIFIED | IR Scans (COLO5-CE1/CE2(UPS01-02)) | 05-Sep-2025 | 08-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE2(UPS01-02) | CLAYCO | #EE5A1C | Y10 | CX10020 | MODIFIED | L3 PFC (COLO5-CE1/CE2(UPS01-02)) | 09-Sep-2025 | 10-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE2(UPS01-02) | MSFT | #3DCD3A | CX22 | CX9950 | MODIFIED | Green Tag (COLO5-CE1/CE2(UPS01-02)) | 11-Sep-2025 | 13-Sep-2025
Commissioning | COLO 5 | COLO5-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX7 | CX10160 | MODIFIED | MEP Test/Pre Startup Installer (COLO5-CE3/CE4(UPS01-02)) | 06-Jun-2025 | 02-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX8 | CX10190 | MODIFIED | Pre Startup Vendor (COLO5-CE3/CE4(UPS01-02)) | 05-Aug-2025 | 09-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX10 | CX10090 | MODIFIED | FOD Clean (COLO5-CE3/CE4(UPS01-02)) | 12-Aug-2025 | 13-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4(UPS01-02) | CLAYCO | #EE5A1C | Y11 | CX10100 | MODIFIED | L2 QA/QC FOD (COLO5-CE3/CE4(UPS01-02)) | 14-Aug-2025 | 15-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX12 | CX10110 | MODIFIED | IVC (COLO5-CE3/CE4(UPS01-02)) | 18-Aug-2025 | 19-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX16 | CX10120 | MODIFIED | Yellow Tag (COLO5-CE3/CE4(UPS01-02)) | 20-Aug-2025 | 21-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX9 | CX10200 | MODIFIED | Control Checks (COLO5-CE3/CE4(UPS01-02)) | 23-Aug-2025 | 26-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX17 | CX10130 | MODIFIED | Energization (COLO5-CE3/CE4(UPS01-02)) | 27-Aug-2025 | 28-Aug-2025
Commissioning | COLO 5 | COLO5-CE3/CE4(UPS01-02) | CLAYCO | #EE5A1C | Y9 | CX10170 | MODIFIED | L3 Startup (COLO5-CE3/CE4(UPS01-02)) | 29-Aug-2025 | 04-Sep-2025
Commissioning | COLO 5 | COLO5-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX20 | CX10180 | MODIFIED | EPMS SAT (COLO5-CE3/CE4(UPS01-02)) | 05-Sep-2025 | 08-Sep-2025
Commissioning | COLO 5 | COLO5-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX19 | CX10140 | MODIFIED | IR Scans (COLO5-CE3/CE4(UPS01-02)) | 08-Sep-2025 | 09-Sep-2025
Commissioning | COLO 5 | COLO5-CE3/CE4(UPS01-02) | CLAYCO | #EE5A1C | Y10 | CX10150 | MODIFIED | L3 PFC (COLO5-CE3/CE4(UPS01-02)) | 10-Sep-2025 | 12-Sep-2025
Commissioning | COLO 5 | COLO5-CE3/CE4(UPS01-02) | MSFT | #3DCD3A | CX22 | CX10080 | MODIFIED | Green Tag (COLO5-CE3/CE4(UPS01-02)) | 13-Sep-2025 | 17-Sep-2025
Commissioning | COLO 5 | COLO5-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX7 | CX10290 | MODIFIED | MEP Test/Pre Startup Installer (COLO5-CE1-PDU(01-06)) | 06-Jun-2025 | 02-Aug-2025
Commissioning | COLO 5 | COLO5-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX8 | CX10310 | MODIFIED | Pre Startup Vendor (COLO5-CE1-PDU(01-06)) | 04-Aug-2025 | 06-Aug-2025
Commissioning | COLO 5 | COLO5-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX10 | CX10220 | MODIFIED | FOD Clean (COLO5-CE1-PDU(01-06)) | 07-Aug-2025 | 08-Aug-2025
Commissioning | COLO 5 | COLO5-CE1-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y11 | CX10230 | MODIFIED | L2 QA/QC FOD (COLO5-CE1-PDU(01-06)) | 09-Aug-2025 | 11-Aug-2025
Commissioning | COLO 5 | COLO5-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX12 | CX10240 | MODIFIED | IVC (COLO5-CE1-PDU(01-06)) | 12-Aug-2025 | 18-Aug-2025
Commissioning | COLO 5 | COLO5-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX16 | CX10250 | MODIFIED | Yellow Tag (COLO5-CE1-PDU(01-06)) | 19-Aug-2025 | 20-Aug-2025
Commissioning | COLO 5 | COLO5-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX9 | CX10320 | MODIFIED | Control Checks (COLO5-CE1-PDU(01-06)) | 21-Aug-2025 | 23-Aug-2025
Commissioning | COLO 5 | COLO5-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX17 | CX10260 | MODIFIED | Energization (COLO5-CE1-PDU(01-06)) | 25-Aug-2025 | 25-Aug-2025
Commissioning | COLO 5 | COLO5-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX19 | CX10270 | MODIFIED | IR Scans (COLO5-CE1-PDU(01-06)) | 26-Aug-2025 | 28-Aug-2025
Commissioning | COLO 5 | COLO5-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX20 | CX10300 | MODIFIED | EPMS SAT (COLO5-CE1-PDU(01-06)) | 30-Aug-2025 | 02-Sep-2025
Commissioning | COLO 5 | COLO5-CE1-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y10 | CX10280 | MODIFIED | L3 PFC (COLO5-CE1-PDU(01-06)) | 04-Sep-2025 | 05-Sep-2025
Commissioning | COLO 5 | COLO5-CE1-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX22 | CX10210 | MODIFIED | Green Tag (COLO5-CE1-PDU(01-06)) | 08-Sep-2025 | 10-Sep-2025
Commissioning | COLO 5 | COLO5-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX7 | CX10530 | MODIFIED | MEP Test/Pre Startup Installer (COLO5-CE3-PDU(01-06)) | 17-Jun-2025 | 09-Aug-2025
Commissioning | COLO 5 | COLO5-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX8 | CX10550 | MODIFIED | Pre Startup Vendor (COLO5-CE3-PDU(01-06)) | 11-Aug-2025 | 13-Aug-2025
Commissioning | COLO 5 | COLO5-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX10 | CX10460 | MODIFIED | FOD Clean (COLO5-CE3-PDU(01-06)) | 14-Aug-2025 | 15-Aug-2025
Commissioning | COLO 5 | COLO5-CE3-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y11 | CX10470 | MODIFIED | L2 QA/QC FOD (COLO5-CE3-PDU(01-06)) | 18-Aug-2025 | 19-Aug-2025
Commissioning | COLO 5 | COLO5-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX12 | CX10480 | MODIFIED | IVC (COLO5-CE3-PDU(01-06)) | 20-Aug-2025 | 22-Aug-2025
Commissioning | COLO 5 | COLO5-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX16 | CX10490 | MODIFIED | Yellow Tag (COLO5-CE3-PDU(01-06)) | 23-Aug-2025 | 25-Aug-2025
Commissioning | COLO 5 | COLO5-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX9 | CX10560 | MODIFIED | Control Checks (COLO5-CE3-PDU(01-06)) | 26-Aug-2025 | 28-Aug-2025
Commissioning | COLO 5 | COLO5-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX17 | CX10500 | MODIFIED | Energization (COLO5-CE3-PDU(01-06)) | 29-Aug-2025 | 29-Aug-2025
Commissioning | COLO 5 | COLO5-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX19 | CX10510 | MODIFIED | IR Scans (COLO5-CE3-PDU(01-06)) | 30-Aug-2025 | 03-Sep-2025
Commissioning | COLO 5 | COLO5-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX20 | CX10540 | MODIFIED | EPMS SAT (COLO5-CE3-PDU(01-06)) | 04-Sep-2025 | 08-Sep-2025
Commissioning | COLO 5 | COLO5-CE3-PDU(01-06)-BSW(01-04) | CLAYCO | #EE5A1C | Y10 | CX10520 | MODIFIED | L3 PFC (COLO5-CE3-PDU(01-06)) | 09-Sep-2025 | 11-Sep-2025
Commissioning | COLO 5 | COLO5-CE3-PDU(01-06)-BSW(01-04) | MSFT | #3DCD3A | CX22 | CX10450 | MODIFIED | Green Tag (COLO5-CE3-PDU(01-06)) | 12-Sep-2025 | 15-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX7 | CX10770 | MODIFIED | MEP Test/Pre Startup Installer (COLO5-CE1/CE3-GPC01) | 06-Jun-2025 | 12-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX8 | CX10790 | MODIFIED | Pre Startup Vendor (COLO5-CE1/CE3-GPC01) | 14-Jul-2025 | 18-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX9 | CX10800 | MODIFIED | Control Checks (COLO5-CE1/CE3-GPC01) | 19-Jul-2025 | 21-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX10 | CX10700 | MODIFIED | FOD Clean (COLO5-CE1/CE3-GPC01) | 22-Jul-2025 | 23-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | CLAYCO | #EE5A1C | Y11 | CX10710 | MODIFIED | L2 QA/QC FOD (COLO5-CE1/CE3-GPC01) | 24-Jul-2025 | 25-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX12 | CX10720 | MODIFIED | IVC (COLO5-CE1/CE3-GPC01) | 28-Jul-2025 | 30-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX16 | CX10730 | MODIFIED | Yellow Tag (COLO5-CE1/CE3-GPC01) | 31-Jul-2025 | 01-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX17 | CX10740 | MODIFIED | Energization (COLO5-CE1/CE3-GPC01) | 07-Aug-2025 | 07-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | CLAYCO | #EE5A1C | Y9 | CX10750 | MODIFIED | L3 Startup (COLO5-CE1/CE3-GPC01) | 08-Aug-2025 | 09-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX19 | CX10760 | MODIFIED | IR SCANS (COLO5-CE1/CE3-GPC01) | 11-Aug-2025 | 13-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX23 | CX10780 | MODIFIED | Load Banking (COLO5-CE1/CE3-GPC01) | 11-Aug-2025 | 13-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX20 | CX10690 | MODIFIED | EPMS SAT (COLO5-CE1/CE3-GPC01) | 14-Aug-2025 | 19-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | CLAYCO | #EE5A1C | Y10 | CX10810 | MODIFIED | L3 PFC (COLO5-CE1/CE3-GPC01) | 20-Aug-2025 | 22-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE3-GPC01 | MSFT | #3DCD3A | CX22 | CX10820 | MODIFIED | Green Tag (COLO5-CE1/CE3-GPC01) | 23-Aug-2025 | 26-Aug-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX7 | CX10910 | MODIFIED | MEP Test/Pre Startup Installer (COLO5-CE2/CE4-GPC01) | 06-Jun-2025 | 18-Jul-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX8 | CX10930 | MODIFIED | Pre Startup Vendor (COLO5-CE2/CE4-GPC01) | 19-Jul-2025 | 23-Jul-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX9 | CX10940 | MODIFIED | Control Checks (COLO5-CE2/CE4-GPC01) | 24-Jul-2025 | 25-Jul-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX10 | CX10840 | MODIFIED | FOD Clean (COLO5-CE2/CE4-GPC01) | 28-Jul-2025 | 29-Jul-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | CLAYCO | #EE5A1C | Y11 | CX10850 | MODIFIED | L2 QA/QC FOD (COLO5-CE2/CE4-GPC01) | 30-Jul-2025 | 31-Jul-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX12 | CX10860 | MODIFIED | IVC (COLO5-CE2/CE4-GPC01) | 01-Aug-2025 | 04-Aug-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX16 | CX10870 | MODIFIED | Yellow Tag (COLO5-CE2/CE4-GPC01) | 06-Aug-2025 | 07-Aug-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX17 | CX10880 | MODIFIED | Energization (COLO5-CE2/CE4-GPC01) | 12-Aug-2025 | 12-Aug-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | CLAYCO | #EE5A1C | Y9 | CX10890 | MODIFIED | L3 Startup (COLO5-CE2/CE4-GPC01) | 12-Aug-2025 | 13-Aug-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX19 | CX10900 | MODIFIED | IR SCANS (COLO5-CE2/CE4-GPC01) | 14-Aug-2025 | 19-Aug-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX23 | CX10920 | MODIFIED | Load Banking (COLO5-CE2/CE4-GPC01) | 14-Aug-2025 | 19-Aug-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX20 | CX10830 | MODIFIED | EPMS SAT (COLO5-CE2/CE4-GPC01) | 20-Aug-2025 | 23-Aug-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | CLAYCO | #EE5A1C | Y10 | CX10950 | MODIFIED | L3 PFC (COLO5-CE2/CE4-GPC01) | 25-Aug-2025 | 27-Aug-2025
Commissioning | COLO 5 | COLO5-CE2/CE4-GPC01 | MSFT | #3DCD3A | CX22 | CX10960 | MODIFIED | Green Tag (COLO5-CE2/CE4-GPC01) | 28-Aug-2025 | 30-Aug-2025
Commissioning | COLO 5 | CHI11-COLO5-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX17 | CX11030 | MODIFIED | Energization (CHI11-COLO5-CE3-LBP01/LBT01) | 13-Aug-2025 | 13-Aug-2025
Commissioning | COLO 5 | CHI11-COLO5-CE3-LBP01/LBT01 | CLAYCO | #EE5A1C | Y9 | CX11070 | MODIFIED | L3 Startup (CHI11-COLO5-CE3-LBP01/LBT01) | 14-Aug-2025 | 14-Aug-2025
Commissioning | COLO 5 | CHI11-COLO5-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX20 | CX11080 | MODIFIED | EPMS SAT (CHI11-COLO5-CE3-LBP01/LBT01) | 15-Aug-2025 | 15-Aug-2025
Commissioning | COLO 5 | CHI11-COLO5-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX19 | CX11040 | MODIFIED | IR Scans (CHI11-COLO5-CE3-LBP01/LBT01) | 18-Aug-2025 | 18-Aug-2025
Commissioning | COLO 5 | CHI11-COLO5-CE3-LBP01/LBT01 | CLAYCO | #EE5A1C | Y10 | CX11050 | MODIFIED | L3 PFC (CHI11-COLO5-CE3-LBP01/LBT01) | 19-Aug-2025 | 21-Aug-2025
Commissioning | COLO 5 | CHI11-COLO5-CE3-LBP01/LBT01 | MSFT | #3DCD3A | CX22 | CX10980 | MODIFIED | Green Tag (CHI11-COLO5-CE3-LBP01/LBT01) | 22-Aug-2025 | 23-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX7 | CX11180 | MODIFIED | MEP Test/Pre Startup Installer (COLO5-CE1/CE2-ATS(01-06)) | 21-Jun-2025 | 08-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX8 | CX11090 | MODIFIED | Pre Startup Vendor (COLO5-CE1/CE2-ATS(01-06)) | 09-Aug-2025 | 15-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX10 | CX11110 | MODIFIED | FOD Clean (COLO5-CE1/CE2-ATS(01-06)) | 18-Aug-2025 | 20-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ATS(01-06) | CLAYCO | #EE5A1C | Y11 | CX11120 | MODIFIED | L2 QA/QC FOD (COLO5-CE1/CE2-ATS(01-06)) | 21-Aug-2025 | 25-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX12 | CX11130 | MODIFIED | IVC (COLO5-CE1/CE2-ATS(01-06)) | 26-Aug-2025 | 02-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX16 | CX11140 | MODIFIED | Yellow Tag (COLO5-CE1/CE2-ATS(01-06)) | 03-Sep-2025 | 05-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX17 | CX11150 | MODIFIED | Energization (COLO5-CE1/CE2-ATS(01-06)) | 08-Sep-2025 | 09-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX19 | CX11160 | MODIFIED | IR Scans (COLO5-CE1/CE2-ATS(01-06)) | 10-Sep-2025 | 15-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ATS(01-06) | CLAYCO | #EE5A1C | Y9 | CX11190 | MODIFIED | L3 Startup (COLO5-CE1/CE2-ATS(01-06)) | 10-Sep-2025 | 15-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX20 | CX11200 | MODIFIED | EPMS SAT (COLO5-CE1/CE2-ATS(01-06)) | 16-Sep-2025 | 19-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ATS(01-06) | CLAYCO | #EE5A1C | Y10 | CX11170 | MODIFIED | L3 PFC (COLO5-CE1/CE2-ATS(01-06)) | 20-Sep-2025 | 24-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-ATS(01-06) | MSFT | #3DCD3A | CX22 | CX11100 | MODIFIED | Green Tag (COLO5-CE1/CE2-ATS(01-06)) | 25-Sep-2025 | 30-Sep-2025
Commissioning | COLO 5 | COLO5 LV Panel and XFM | MSFT | #3DCD3A | CX7 | CX11410 | MODIFIED | MEP Test/Pre Startup Installer (COLO5- LV Panel and XFM) | 06-Jun-2025 | 23-Jul-2025
Commissioning | COLO 5 | COLO5 LV Panel and XFM | MSFT | #3DCD3A | CX17 | CX11380 | MODIFIED | Energization (COLO5-LV Panel and XFM) | 10-Sep-2025 | 11-Sep-2025
Commissioning | COLO 5 | COLO5 LV Panel and XFM | MSFT | #3DCD3A | CX19 | CX11390 | MODIFIED | IR Scans (COLO5- LV Panel and XFM) | 12-Sep-2025 | 17-Sep-2025
Commissioning | COLO 5 | COLO5 LV Panel and XFM | CLAYCO | #EE5A1C | Y9 | CX11420 | MODIFIED | L3 Startup (COLO5- LV Panel and XFM) | 12-Sep-2025 | 17-Sep-2025
Commissioning | COLO 5 | COLO5 LV Panel and XFM | CLAYCO | #EE5A1C | Y10 | CX11400 | MODIFIED | L3 PFC (COLO5- LV Panel and XFM) | 19-Sep-2025 | 19-Sep-2025
Commissioning | COLO 5 | COLO5 LV Panel and XFM | MSFT | #3DCD3A | CX22 | CX11330 | MODIFIED | Green Tag (COLO5- LV Panel and XFM) | 20-Sep-2025 | 20-Sep-2025
Commissioning | COLO 5 | COLO5-Loadbank Busway | MSFT | #3DCD3A | CX7 | CX11620 | MODIFIED | MEP Test/Pre Startup InstalleR (COLO5-LBBSW) | 11-Jun-2025 | 30-Jun-2025
Commissioning | COLO 5 | COLO5-Loadbank Busway | MSFT | #3DCD3A | CX8 | CX11530 | MODIFIED | Pre Startup Vendor (COLO5-LBBSW) | 02-Jul-2025 | 07-Jul-2025
Commissioning | COLO 5 | COLO5-Loadbank Busway | MSFT | #3DCD3A | CX10 | CX11550 | MODIFIED | FOD Clean (COLO5-LBBSW) | 08-Jul-2025 | 09-Jul-2025
Commissioning | COLO 5 | COLO5-Loadbank Busway | CLAYCO | #EE5A1C | Y11 | CX11560 | MODIFIED | L2 QA/QC FOD (COLO5-LBBSW) | 11-Jul-2025 | 14-Jul-2025
Commissioning | COLO 5 | COLO5-Loadbank Busway | MSFT | #3DCD3A | CX12 | CX11570 | MODIFIED | IVC (COLO5-LBBSW) | 15-Jul-2025 | 17-Jul-2025
Commissioning | COLO 5 | COLO5-Loadbank Busway | MSFT | #3DCD3A | CX16 | CX11580 | MODIFIED | Yellow Tag (COLO5-LBBSW) | 18-Jul-2025 | 21-Jul-2025
Commissioning | COLO 5 | COLO5-Loadbank Busway | MSFT | #3DCD3A | CX17 | CX11590 | MODIFIED | Energization (COLO5-LBBSW) | 09-Aug-2025 | 09-Aug-2025
Commissioning | COLO 5 | COLO5-Loadbank Busway | MSFT | #3DCD3A | CX19 | CX11600 | MODIFIED | IR Scans (COLO5-LBBSW) | 11-Aug-2025 | 12-Aug-2025
Commissioning | COLO 5 | COLO5-Loadbank Busway | CLAYCO | #EE5A1C | Y9 | CX11630 | MODIFIED | L3 Startup (COLO5-LBBSW) | 11-Aug-2025 | 15-Aug-2025
Commissioning | COLO 5 | COLO5-Loadbank Busway | CLAYCO | #EE5A1C | Y10 | CX11610 | MODIFIED | L3 PFC (COLO5-LBBSW) | 18-Aug-2025 | 18-Aug-2025
Commissioning | COLO 5 | COLO5-Loadbank Busway | MSFT | #3DCD3A | CX22 | CX11540 | MODIFIED | Green Tag (COLO5-LBBSW) | 19-Aug-2025 | 21-Aug-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-AHU(01-08) | MSFT | #3DCD3A | CX7 | CX11720 | MODIFIED | MEP Test/Pre Startup Installer (COLO5-CE1/CE2-AHU(01-08)) | 06-Jun-2025 | 22-Jul-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-AHU(01-08) | MSFT | #3DCD3A | CX17 | CX11700 | MODIFIED | Energization (COLO5-CE1/CE2-AHU(01-08)) | 08-Sep-2025 | 09-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-AHU(01-08) | CLAYCO | #EE5A1C | Y9 | CX11730 | MODIFIED | L3 Startup (COLO5-CE1/CE2-AHU(01-08)) | 10-Sep-2025 | 15-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-AHU(01-08) | MSFT | #3DCD3A | CX25 | CX11740 | MODIFIED | BAS SAT & TAB (COLO5-CE1/CE2-AHU(01-08)) | 16-Sep-2025 | 23-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-AHU(01-08) | CLAYCO | #EE5A1C | Y10 | CX11710 | MODIFIED | L3 PFC (COLO5-CE1/CE2-AHU(01-08)) | 24-Sep-2025 | 29-Sep-2025
Commissioning | COLO 5 | COLO5-CE1/CE2-AHU(01-08) | MSFT | #3DCD3A | CX22 | CX11650 | MODIFIED | Green Tag (COLO5-CE1/CE2-AHU(01-08)) | 30-Sep-2025 | 02-Oct-2025
Commissioning | COLO 5 | COLO5-Control Panel and CC | MSFT | #3DCD3A | CX7 | CX12140 | MODIFIED | MEP Test/Pre Startup Installer (COLO5-Control Panel and CC) | 21-Apr-2025 | 19-Jul-2025
Commissioning | COLO 5 | COLO5-Control Panel and CC | MSFT | #3DCD3A | CX10 | CX12090 | MODIFIED | FOD Clean (COLO5-Control Panel and CC) | 21-Jul-2025 | 24-Jul-2025
Commissioning | COLO 5 | COLO5-Control Panel and CC | CLAYCO | #EE5A1C | Y11 | CX12100 | MODIFIED | L2 QA/QC FOD (COLO5-Control Panel and CC) | 25-Jul-2025 | 29-Jul-2025
Commissioning | COLO 5 | COLO5-Control Panel and CC | MSFT | #3DCD3A | CX12 | CX12110 | MODIFIED | IVC (COLO5-Control Panel and CC) | 30-Jul-2025 | 01-Aug-2025
Commissioning | COLO 5 | COLO5-Control Panel and CC | MSFT | #3DCD3A | CX16 | CX12120 | MODIFIED | Yellow Tag (COLO5-Control Panel and CC) | 02-Aug-2025 | 06-Aug-2025
Commissioning | COLO 5 | COLO5-Control Panel and CC | MSFT | #3DCD3A | CX17 | CX12130 | MODIFIED | Energization (COLO5-Control Panel and CC) | 12-Aug-2025 | 13-Aug-2025
Commissioning | COLO 5 | COLO5-Control Panel and CC | MSFT | #3DCD3A | CX25 | CX12150 | MODIFIED | BAS SAT (COLO5-Control Panel and CC) | 14-Aug-2025 | 15-Aug-2025
Commissioning | COLO 5 | COLO5-Control Panel and CC | MSFT | #3DCD3A | CX22 | CX12080 | MODIFIED | Green Tag (COLO5-Control Panel and CC) | 19-Aug-2025 | 19-Aug-2025
Commissioning | COLO 5 | CHI11-COLO5-AC/CU(01-02) | MSFT | #3DCD3A | CX10 | CX12170 | MODIFIED | FOD Clean (CHI11-COLO5-AC/CU(01-02)) | 25-Jul-2025 | 28-Jul-2025
Commissioning | COLO 5 | CHI11-COLO5-AC/CU(01-02) | MSFT | #3DCD3A | CX7 | CX12220 | MODIFIED | MEP Test/Pre Startup Installer (CHI11-COLO5-AC/CU(01-02)) | 25-Jul-2025 | 25-Jul-2025
Commissioning | COLO 5 | CHI11-COLO5-AC/CU(01-02) | CLAYCO | #EE5A1C | Y11 | CX12180 | MODIFIED | L2 QA/QC FOD (CHI11-COLO5-AC/CU(01-02)) | 29-Jul-2025 | 30-Jul-2025
Commissioning | COLO 5 | CHI11-COLO5-AC/CU(01-02) | MSFT | #3DCD3A | CX12 | CX12190 | MODIFIED | IVC (CHI11-COLO5-AC/CU(01-02)) | 01-Aug-2025 | 02-Aug-2025
Commissioning | COLO 5 | CHI11-COLO5-AC/CU(01-02) | MSFT | #3DCD3A | CX16 | CX12200 | MODIFIED | Yellow Tag (CHI11-COLO5-AC/CU(01-02)) | 04-Aug-2025 | 05-Aug-2025
Commissioning | COLO 5 | CHI11-COLO5-AC/CU(01-02) | MSFT | #3DCD3A | CX17 | CX12210 | MODIFIED | Energization (CHI11-COLO5-AC/CU(01-02)) | 17-Sep-2025 | 17-Sep-2025
Commissioning | COLO 5 | CHI11-COLO5-AC/CU(01-02) | CLAYCO | #EE5A1C | Y9 | CX12230 | MODIFIED | L3 Startup (CHI11-COLO5-AC/CU(01-02)) | 18-Sep-2025 | 23-Sep-2025
Commissioning | COLO 5 | CHI11-COLO5-AC/CU(01-02) | MSFT | #3DCD3A | CX25 | CX12160 | MODIFIED | BAS SAT (CHI11-COLO5-AC/CU(01-02)) | 24-Sep-2025 | 24-Sep-2025
Commissioning | COLO 5 | CHI11-COLO5-AC/CU(01-02) | MSFT | #3DCD3A | CX22 | CX12240 | MODIFIED | Green Tag (CHI11-COLO5-AC/CU(01-02)) | 25-Sep-2025 | 29-Sep-2025
Commissioning | COLO 5 | CHI11-3A/B-HTP03 | MSFT | #3DCD3A | CX10 | CX12560 | MODIFIED | FOD Clean (CHI11-3A/B-HTP03) | 30-Jul-2025 | 31-Jul-2025
Commissioning | COLO 5 | CHI11-3A/B-HTP03 | MSFT | #3DCD3A | CX7 | CX12610 | MODIFIED | MEP Test/Pre Startup Installer (CHI11-3A/B-HTP03) | 30-Jul-2025 | 30-Jul-2025
Commissioning | COLO 5 | CHI11-3A/B-HTP03 | CLAYCO | #EE5A1C | Y11 | CX12570 | MODIFIED | L2 QA/QC FOD (CHI11-3A/B-HTP03) | 01-Aug-2025 | 02-Aug-2025
Commissioning | COLO 5 | CHI11-3A/B-HTP03 | MSFT | #3DCD3A | CX12 | CX12580 | MODIFIED | IVC (CHI11-3A/B-HTP03) | 04-Aug-2025 | 05-Aug-2025
Commissioning | COLO 5 | CHI11-3A/B-HTP03 | MSFT | #3DCD3A | CX16 | CX12590 | MODIFIED | Yellow Tag (CHI11-3A/B-HTP03) | 06-Aug-2025 | 07-Aug-2025
Commissioning | COLO 5 | CHI11-3A/B-HTP03 | MSFT | #3DCD3A | CX17 | CX12600 | MODIFIED | Energization (CHI11-3A/B-HTP03) | 19-Sep-2025 | 19-Sep-2025
Commissioning | COLO 5 | CHI11-3A/B-HTP03 | CLAYCO | #EE5A1C | Y9 | CX12620 | MODIFIED | L3 Startup (CHI11-3A/B-HTP03) | 20-Sep-2025 | 24-Sep-2025
Commissioning | COLO 5 | CHI11-3A/B-HTP03 | MSFT | #3DCD3A | CX25 | CX12550 | MODIFIED | BAS SAT (CHI11-3A/B-HTP03) | 25-Sep-2025 | 30-Sep-2025
Commissioning | COLO 5 | CHI11-3A/B-HTP03 | MSFT | #3DCD3A | CX22 | CX12630 | MODIFIED | Green Tag (CHI11-3A/B-HTP03) | 01-Oct-2025 | 01-Oct-2025
Commissioning | Admin | ADMIN-PNL04 | MSFT | #3DCD3A | CX28 | CX13680 | NEW | CYT (ADMIN-PNL04) | 12-May-2025 | 12-May-2025
Commissioning | Admin | ADMIN-PNL04 | MSFT | #3DCD3A | CX27 | CX12680 | NEW | Conditional Energization (ADMIN-PNL04) | 12-May-2025 | 12-May-2025
Commissioning | Admin | ADMIN-MSB01 | MSFT | #3DCD3A | CX28 | CX13690 | NEW | CYT (ADMIN-MSB01) | 30-May-2025 | 30-May-2025
Commissioning | Admin | ADMIN-MSB02 | MSFT | #3DCD3A | CX27 | CX13700 | NEW | Conditional Energization (ADMIN-MSB01) | 30-May-2025 | 30-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | MSFT | #3DCD3A | CX28 | A3620 | NEW | CYT (COLO3-CE3/CE4-XFM01) | 14-May-2025 | 15-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-XFM01 | MSFT | #3DCD3A | CX27 | A3630 | NEW | Conditional Energization (COLO3-CE3/CE4-XFM01) | 14-May-2025 | 15-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-PNL02 | MSFT | #3DCD3A | CX28 | A3640 | NEW | CYT (COLO3-CE1/CE2-PNL02) | 12-May-2025 | 12-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-PNL02 | MSFT | #3DCD3A | CX27 | A3650 | NEW | Conditional Energization (COLO3-CE1/CE2-PNL02) | 12-May-2025 | 12-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-PNL02 | MSFT | #3DCD3A | CX28 | A3660 | NEW | CYT (COLO3-CE3/CE4-PNL02) | 14-May-2025 | 15-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-PNL02 | MSFT | #3DCD3A | CX27 | A3670 | NEW | Conditional Energization (COLO3-CE3/CE4-PNL02) | 14-May-2025 | 15-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX28 | CX12640 | NEW | CYT (COLO3-CE1/CE2-MSB01 and TCP01) | 22-May-2025 | 27-May-2025
Commissioning | COLO 3 | COLO3-CE1/CE2-MSB01 and TCP01 | MSFT | #3DCD3A | CX27 | CX12650 | NEW | Conditional Energization (COLO3-CE1/CE2-MSB01 and TCP01) | 22-May-2025 | 27-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX28 | CX12660 | NEW | CYT (COLO3-CE3/CE4-MSB01 and TCP01) | 30-May-2025 | 30-May-2025
Commissioning | COLO 3 | COLO3-CE3/CE4-MSB01 and TCP01 | MSFT | #3DCD3A | CX27 | CX12670 | NEW | Conditional Energization (COLO3-CE3/CE4-MSB01 and TCP01) | 30-May-2025 | 30-May-2025
Commissioning | COLO 4 | COLO4 UPM | MSFT | #3DCD3A | CX28 | CX13710 | NEW | CYT (COLO4 UPM) | 28-Apr-2025 | 29-Apr-2025
Commissioning | COLO 4 | COLO4 UPM | MSFT | #3DCD3A | CX27 | CX13720 | NEW | Conditional Energization (COLO4 UPM) | 28-Apr-2025 | 29-Apr-2025