## Sheet1
Phase | Area | Trade | Color | Act Code | Act Name | Start | Finish
General | General | Landscaping | #000000 | G1 | Site Paving & Parking | 2025-05-28 | 2025-06-24
General | General | Landscaping | #000000 | G2 | Hardscape and Landscape | 2025-10-24 | 2026-02-18
Site Work | Initial Site / Earthwork / Utilities | Utilities | #F5B731 | S1 | GPRS Site | 2025-07-21 | 2025-07-24
Site Work | Initial Site / Earthwork / Utilities | Utilities | #F5B731 | S2 | SWPPP & Security Fencing | 2025-07-25 | 2025-07-31
Site Work | Initial Site / Earthwork / Utilities | Utilities | #F5B731 | S3 | Mobilization | 2025-08-01 | 2025-08-14
Site Work | Initial Site / Earthwork / Utilities | Utilities | #F5B731 | S4 | Concrete Demo & Selective Demo | 2025-08-01 | 2025-09-05
Site Work | Initial Site / Earthwork / Utilities | Utilities | #F5B731 | S5 | Strip Topsoil & Mass Grading 72" & Recondition Soil | 2025-09-08 | 2025-10-03
Site Work | Initial Site / Earthwork / Utilities | Utilities | #F5B731 | S6 | Excavate FRP Tower Crane Foundations | 2025-10-06 | 2025-10-10
Site Work | Initial Site / Earthwork / Utilities | Utilities | #F5B731 | S7 | Set Crane Embed | 2025-10-09 | 2025-10-09
Site Work | Initial Site / Earthwork / Utilities | Utilities | #F5B731 | S8 | Site Underground Utilities | 2025-10-16 | 2025-11-26
Foundations | Chiller | Foundations | #8F6F56 | F1 | Excavate & FRP Footings | 2025-10-20 | 2025-11-14
Foundations | Chiller | Foundations | #8F6F56 | F2 | Electrical U/G Rough In | 2025-11-03 | 2025-11-21
Foundations | Chiller | Foundations | #8F6F56 | F3 | Mechanical U/G Rough In | 2025-11-03 | 2025-11-21
Foundations | Chiller | Foundations | #8F6F56 | F4 | Plumbing U/G Rough In | 2025-11-03 | 2025-11-21
Foundations | Chiller | Foundations | #8F6F56 | F5 | Electrical & Fiber U/G Rough In | 2025-11-03 | 2025-11-21
Foundations | Chiller | Foundations | #8F6F56 | F6 | FRP Chiller Slab on Grade | 2025-12-01 | 2025-12-12
Foundations | Chiller | Foundations | #8F6F56 | F7 | SOG Cure Time (Cal Days) | 2025-12-13 | 2025-12-26
Foundations | Chiller | Foundations | #8F6F56 | F8 | Install CMU Block | 2025-12-29 | 2026-02-16
Foundations | Area A | Foundations | #8F6F56 | F9 | Excavate & FRP Footings & Elevator Pits | 2025-11-17 | 2025-12-09
Foundations | Area A | Foundations | #8F6F56 | F10 | FRP Stem Walls | 2025-11-24 | 2025-12-31
Foundations | Area A | Foundations | #8F6F56 | F2 | Electrical U/G Rough In | 2025-12-10 | 2026-01-08
Foundations | Area A | Foundations | #8F6F56 | F3 | Mechanical U/G Rough In | 2025-12-10 | 2026-01-08
Foundations | Area A | Foundations | #8F6F56 | F4 | Plumbing U/G Rough In | 2025-12-10 | 2026-01-08
Foundations | Area A | Foundations | #8F6F56 | F11 | Waterproof Footings | 2026-01-02 | 2026-01-13
Foundations | Area A | Foundations | #8F6F56 | F12 | Waterproof Inspections | 2026-01-14 | 2026-01-14
Foundations | Area A | Foundations | #8F6F56 | F13 | Backfill Footings | 2026-01-15 | 2026-01-19
Foundations | Area A | Foundations | #8F6F56 | F14 | FRP Slab On Grade | 2026-01-20 | 2026-02-02
Foundations | Area A | Foundations | #8F6F56 | F15 | SOG Cure Time (Cure Time) | 2026-02-03 | 2026-02-09
Foundations | Podium (Middle Section) | Foundations | #8F6F56 | F1 | Excavate & FRP Footings | 2025-12-10 | 2026-01-08
Foundations | Podium (Middle Section) | Foundations | #8F6F56 | F10 | FRP Stem Walls | 2025-12-24 | 2026-02-12
Foundations | Podium (Middle Section) | Foundations | #8F6F56 | F2 | Electrical U/G Rough In | 2026-01-09 | 2026-02-05
Foundations | Podium (Middle Section) | Foundations | #8F6F56 | F3 | Mechanical U/G Rough In | 2026-01-09 | 2026-02-05
Foundations | Podium (Middle Section) | Foundations | #8F6F56 | F4 | Plumbing U/G Rough In | 2026-01-09 | 2026-02-05
Foundations | Podium (Middle Section) | Foundations | #8F6F56 | F11 | Waterproof Footings | 2026-02-13 | 2026-02-26
Foundations | Podium (Middle Section) | Foundations | #8F6F56 | F12 | Waterproof Inspections | 2026-02-27 | 2026-02-27
Foundations | Podium (Middle Section) | Foundations | #8F6F56 | F13 | Backfill Footings | 2026-03-02 | 2026-03-06
Foundations | Podium (Middle Section) | Foundations | #8F6F56 | F14 | FRP Slab On Grade | 2026-03-09 | 2026-03-20
Foundations | Podium (Middle Section) | Foundations | #8F6F56 | F15 | SOG Cure Time (Cure Time) | 2026-03-21 | 2026-03-27
Foundations | Area B | Foundations | #8F6F56 | F9 | Excavate & FRP Footings & Elevator Pits | 2026-01-09 | 2026-01-29
Foundations | Area B | Foundations | #8F6F56 | F10 | FRP Stem Walls | 2026-01-16 | 2026-02-19
Foundations | Area B | Foundations | #8F6F56 | F2 | Electrical U/G Rough In | 2026-01-30 | 2026-02-26
Foundations | Area B | Foundations | #8F6F56 | F3 | Mechanical U/G Rough In | 2026-01-30 | 2026-02-26
Foundations | Area B | Foundations | #8F6F56 | F4 | Plumbing U/G Rough In | 2026-01-30 | 2026-02-26
Foundations | Area B | Foundations | #8F6F56 | F11 | Waterproof Footings | 2026-02-20 | 2026-03-03
Foundations | Area B | Foundations | #8F6F56 | F12 | Waterproof Inspections | 2026-03-04 | 2026-03-04
Foundations | Area B | Foundations | #8F6F56 | F13 | Backfill Footings | 2026-03-05 | 2026-03-09
Foundations | Area B | Foundations | #8F6F56 | F14 | FRP Slab On Grade | 2026-03-10 | 2026-03-23
Foundations | Area B | Foundations | #8F6F56 | F15 | SOG Cure Time (Cure Time) | 2026-03-24 | 2026-03-30
Structure | Area A - Lvl 1 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-02-10 | 2026-02-23
Structure | Area A - Lvl 1 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-02-24 | 2026-03-02
Structure | Area A - Lvl 1 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-02-24 | 2026-03-09
Structure | Area A - Lvl 1 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-03-03 | 2026-03-09
Structure | Area A - Lvl 1 | Structure | #ACB9CA | T5 | FRP SOMD | 2026-03-10 | 2026-03-23
Structure | Area A - Lvl 2 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-03-24 | 2026-04-06
Structure | Area A - Lvl 2 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-04-07 | 2026-04-13
Structure | Area A - Lvl 2 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-04-07 | 2026-04-20
Structure | Area A - Lvl 2 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-04-14 | 2026-04-20
Structure | Area A - Lvl 2 | Structure | #ACB9CA | T5 | FRP SOMD | 2026-04-21 | 2026-05-04
Structure | Area A - Lvl 3 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-05-05 | 2026-05-18
Structure | Area A - Lvl 3 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-05-19 | 2026-05-26
Structure | Area A - Lvl 3 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-05-19 | 2026-06-02
Structure | Area A - Lvl 3 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-05-27 | 2026-06-02
Structure | Area A - Lvl 3 | Structure | #ACB9CA | T5 | FRP SOMD | 2026-06-03 | 2026-06-16
Structure | Area A - Lvl 4 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-06-17 | 2026-06-30
Structure | Area A - Lvl 4 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-07-01 | 2026-07-08
Structure | Area A - Lvl 4 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-07-01 | 2026-07-15
Structure | Area A - Lvl 4 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-07-09 | 2026-07-15
Structure | Area A - Lvl 4 | Structure | #ACB9CA | T5 | FRP SOMD | 2026-07-16 | 2026-07-29
Structure | Area A - Lvl 5 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-07-30 | 2026-08-12
Structure | Area A - Lvl 5 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-08-13 | 2026-08-19
Structure | Area A - Lvl 5 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-08-13 | 2026-08-26
Structure | Area A - Lvl 5 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-08-20 | 2026-08-26
Structure | Area A - Lvl 5 | Structure | #ACB9CA | T6 | FRP SOMD Attic | 2026-08-27 | 2026-09-10
Structure | Area A - Attic | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-09-11 | 2026-09-24
Structure | Area A - Attic | Structure | #ACB9CA | T7 | Install Attic Equipment | 2026-09-25 | 2026-10-01
Structure | Area A - Attic | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-09-25 | 2026-10-01
Structure | Area A - Attic | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-09-25 | 2026-10-08
Structure | Area A - Attic | Structure | #ACB9CA | T8 | Install Metal Trusses | 2026-10-09 | 2026-11-05
Structure | Podium - Lvl 1 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-03-30 | 2026-04-10
Structure | Podium - Lvl 1 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-04-13 | 2026-04-17
Structure | Podium - Lvl 1 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-04-13 | 2026-04-24
Structure | Podium - Lvl 1 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-04-20 | 2026-04-24
Structure | Podium - Lvl 1 | Structure | #ACB9CA | T5 | FRP SOMD | 2026-04-27 | 2026-05-08
Structure | Podium - Lvl 2 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-05-11 | 2026-05-22
Structure | Podium - Lvl 2 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-05-26 | 2026-06-01
Structure | Podium - Lvl 2 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-05-26 | 2026-06-08
Structure | Podium - Lvl 2 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-06-02 | 2026-06-08
Structure | Podium - Lvl 2 | Structure | #ACB9CA | T5 | FRP SOMD | 2026-06-09 | 2026-06-22
Structure | Podium - Lvl 3 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-06-23 | 2026-07-07
Structure | Podium - Lvl 3 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-07-08 | 2026-07-14
Structure | Podium - Lvl 3 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-07-08 | 2026-07-21
Structure | Podium - Lvl 3 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-07-15 | 2026-07-21
Structure | Podium - Lvl 3 | Structure | #ACB9CA | T5 | FRP SOMD | 2026-07-22 | 2026-08-04
Structure | Podium - Lvl 4 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-08-05 | 2026-08-18
Structure | Podium - Lvl 4 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-08-19 | 2026-08-25
Structure | Podium - Lvl 4 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-08-19 | 2026-09-01
Structure | Podium - Lvl 4 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-08-26 | 2026-09-01
Structure | Podium - Lvl 4 | Structure | #ACB9CA | T5 | FRP SOMD | 2026-09-02 | 2026-09-16
Structure | Podium - Lvl 5 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-09-17 | 2026-09-30
Structure | Podium - Lvl 5 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-10-01 | 2026-10-07
Structure | Podium - Lvl 5 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-10-01 | 2026-10-14
Structure | Podium - Lvl 5 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-10-08 | 2026-10-14
Structure | Podium - Lvl 5 | Structure | #ACB9CA | T6 | FRP SOMD Attic | 2026-10-15 | 2026-10-28
Structure | Podium - Attic | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-10-29 | 2026-11-11
Structure | Podium - Attic | Structure | #ACB9CA | T7 | Install Attic Equipment | 2026-11-12 | 2026-11-18
Structure | Podium - Attic | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-11-12 | 2026-11-18
Structure | Podium - Attic | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-11-12 | 2026-11-25
Structure | Podium - Attic | Structure | #ACB9CA | T8 | Install Metal Trusses | 2026-11-30 | 2027-01-12
Structure | Area B - Lvl 1 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-04-13 | 2026-04-24
Structure | Area B - Lvl 1 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-04-27 | 2026-05-01
Structure | Area B - Lvl 1 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-04-27 | 2026-05-08
Structure | Area B - Lvl 1 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-05-04 | 2026-05-08
Structure | Area B - Lvl 1 | Structure | #ACB9CA | T5 | FRP SOMD | 2026-05-11 | 2026-05-22
Structure | Area B - Lvl 2 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-05-26 | 2026-06-08
Structure | Area B - Lvl 2 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-06-09 | 2026-06-15
Structure | Area B - Lvl 2 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-06-09 | 2026-06-22
Structure | Area B - Lvl 2 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-06-16 | 2026-06-22
Structure | Area B - Lvl 2 | Structure | #ACB9CA | T5 | FRP SOMD | 2026-06-23 | 2026-07-07
Structure | Area B - Lvl 3 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-07-08 | 2026-07-21
Structure | Area B - Lvl 3 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-07-22 | 2026-07-28
Structure | Area B - Lvl 3 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-07-22 | 2026-08-04
Structure | Area B - Lvl 3 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-07-29 | 2026-08-04
Structure | Area B - Lvl 3 | Structure | #ACB9CA | T5 | FRP SOMD | 2026-08-05 | 2026-08-18
Structure | Area B - Lvl 4 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-08-19 | 2026-09-01
Structure | Area B - Lvl 4 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-09-02 | 2026-09-09
Structure | Area B - Lvl 4 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-09-02 | 2026-09-16
Structure | Area B - Lvl 4 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-09-10 | 2026-09-16
Structure | Area B - Lvl 4 | Structure | #ACB9CA | T5 | FRP SOMD | 2026-09-17 | 2026-09-30
Structure | Area B - Lvl 5 | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-10-15 | 2026-10-28
Structure | Area B - Lvl 5 | Structure | #ACB9CA | T2 | Install Metal Decking | 2026-10-29 | 2026-11-04
Structure | Area B - Lvl 5 | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-10-29 | 2026-11-11
Structure | Area B - Lvl 5 | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-11-05 | 2026-11-11
Structure | Area B - Lvl 5 | Structure | #ACB9CA | T6 | FRP SOMD Attic | 2026-11-12 | 2026-11-25
Structure | Area B - Attic | Structure | #ACB9CA | T1 | Frame Structural Walls & Joists | 2026-11-30 | 2026-12-11
Structure | Area B - Attic | Structure | #ACB9CA | T7 | Install Attic Equipment | 2026-12-14 | 2026-12-18
Structure | Area B - Attic | Structure | #ACB9CA | T4 | Install Metal Edge Detailing | 2026-12-14 | 2026-12-18
Structure | Area B - Attic | Structure | #ACB9CA | T3 | Complete Fire Wall Installation | 2026-12-14 | 2026-12-28
Structure | Area B - Attic | Structure | #ACB9CA | T8 | Install Metal Trusses | 2026-12-29 | 2027-01-26
Building Envelope | West Elevation | Exterior envelope | #C6E0B4 | E1 | Exterior Framing Completion | 2027-01-27 | 2027-02-09
Building Envelope | West Elevation | Exterior envelope | #C6E0B4 | E2 | Exterior Sheathing | 2027-02-03 | 2027-02-16
Building Envelope | West Elevation | Exterior envelope | #C6E0B4 | E3 | Waterproofing & Flashing | 2027-02-10 | 2027-02-23
Building Envelope | West Elevation | Exterior envelope | #C6E0B4 | E4 | Waterproof Inspections | 2027-02-24 | 2027-02-26
Building Envelope | West Elevation | Exterior envelope | #C6E0B4 | E5 | Plumbing Rough In | 2027-03-01 | 2027-03-12
Building Envelope | West Elevation | Exterior envelope | #C6E0B4 | E6 | Electrical Rough In | 2027-03-01 | 2027-03-12
Building Envelope | West Elevation | Exterior envelope | #C6E0B4 | E7 | Install Brick Masonry | 2027-03-15 | 2027-04-16
Building Envelope | West Elevation | Exterior envelope | #C6E0B4 | E8 | Waterproofing Around Window Opening / Caulking & Flashing | 2027-04-19 | 2027-04-23
Building Envelope | West Elevation | Exterior envelope | #C6E0B4 | E9 | Install Stucco | 2027-04-26 | 2027-05-28
Building Envelope | West Elevation | Exterior envelope | #C6E0B4 | E10 | Install Windows | 2027-06-01 | 2027-06-21
Building Envelope | West Elevation | Exterior envelope | #C6E0B4 | E11 | Final Waterproofing & Caulking | 2027-06-22 | 2027-06-28
Building Envelope | West Elevation | Exterior envelope | #C6E0B4 | E12 | Waterproofing Cure Time | 2027-06-29 | 2027-07-01
Building Envelope | North Elevation | Exterior envelope | #C6E0B4 | E1 | Exterior Framing Completion | 2027-02-01 | 2027-02-12
Building Envelope | North Elevation | Exterior envelope | #C6E0B4 | E2 | Exterior Sheathing | 2027-02-08 | 2027-02-19
Building Envelope | North Elevation | Exterior envelope | #C6E0B4 | E3 | Waterproofing & Flashing | 2027-02-15 | 2027-02-26
Building Envelope | North Elevation | Exterior envelope | #C6E0B4 | E4 | Waterproof Inspections | 2027-03-01 | 2027-03-03
Building Envelope | North Elevation | Exterior envelope | #C6E0B4 | E5 | Plumbing Rough In | 2027-03-04 | 2027-03-17
Building Envelope | North Elevation | Exterior envelope | #C6E0B4 | E6 | Electrical Rough In | 2027-03-04 | 2027-03-17
Building Envelope | North Elevation | Exterior envelope | #C6E0B4 | E7 | Install Brick Masonry | 2027-03-18 | 2027-04-14
Building Envelope | North Elevation | Exterior envelope | #C6E0B4 | E8 | Waterproofing Around Window Opening / Caulking & Flashing | 2027-04-15 | 2027-04-21
Building Envelope | North Elevation | Exterior envelope | #C6E0B4 | E9 | Install Stucco | 2027-04-22 | 2027-05-26
Building Envelope | North Elevation | Exterior envelope | #C6E0B4 | E10 | Install Windows | 2027-05-27 | 2027-06-17
Building Envelope | North Elevation | Exterior envelope | #C6E0B4 | E11 | Final Waterproofing & Caulking | 2027-06-18 | 2027-06-24
Building Envelope | North Elevation | Exterior envelope | #C6E0B4 | E12 | Waterproofing Cure Time | 2027-06-25 | 2027-06-27
Building Envelope | East Elevation | Exterior envelope | #C6E0B4 | E1 | Exterior Framing Completion | 2027-02-04 | 2027-02-17
Building Envelope | East Elevation | Exterior envelope | #C6E0B4 | E2 | Exterior Sheathing | 2027-02-11 | 2027-02-24
Building Envelope | East Elevation | Exterior envelope | #C6E0B4 | E3 | Waterproofing & Flashing | 2027-02-18 | 2027-03-03
Building Envelope | East Elevation | Exterior envelope | #C6E0B4 | E4 | Waterproof Inspections | 2027-03-04 | 2027-03-08
Building Envelope | East Elevation | Exterior envelope | #C6E0B4 | E5 | Plumbing Rough In | 2027-03-09 | 2027-03-22
Building Envelope | East Elevation | Exterior envelope | #C6E0B4 | E6 | Electrical Rough In | 2027-03-09 | 2027-03-22
Building Envelope | East Elevation | Exterior envelope | #C6E0B4 | E7 | Install Brick Masonry | 2027-03-23 | 2027-04-26
Building Envelope | East Elevation | Exterior envelope | #C6E0B4 | E8 | Waterproofing Around Window Opening / Caulking & Flashing | 2027-04-27 | 2027-05-03
Building Envelope | East Elevation | Exterior envelope | #C6E0B4 | E9 | Install Stucco | 2027-05-04 | 2027-06-08
Building Envelope | East Elevation | Exterior envelope | #C6E0B4 | E10 | Install Windows | 2027-06-09 | 2027-06-29
Building Envelope | East Elevation | Exterior envelope | #C6E0B4 | E11 | Final Waterproofing & Caulking | 2027-06-30 | 2027-07-07
Building Envelope | East Elevation | Exterior envelope | #C6E0B4 | E12 | Waterproofing Cure Time | 2027-07-08 | 2027-07-10
Building Envelope | South Elevation | Exterior envelope | #C6E0B4 | E1 | Exterior Framing Completion | 2027-02-09 | 2027-02-22
Building Envelope | South Elevation | Exterior envelope | #C6E0B4 | E2 | Exterior Sheathing | 2027-02-16 | 2027-03-01
Building Envelope | South Elevation | Exterior envelope | #C6E0B4 | E3 | Waterproofing & Flashing | 2027-02-23 | 2027-03-08
Building Envelope | South Elevation | Exterior envelope | #C6E0B4 | E4 | Waterproof Inspections | 2027-03-09 | 2027-03-11
Building Envelope | South Elevation | Exterior envelope | #C6E0B4 | E5 | Plumbing Rough In | 2027-03-12 | 2027-03-25
Building Envelope | South Elevation | Exterior envelope | #C6E0B4 | E6 | Electrical Rough In | 2027-03-12 | 2027-03-25
Building Envelope | South Elevation | Exterior envelope | #C6E0B4 | E7 | Install Brick Masonry | 2027-03-26 | 2027-04-22
Building Envelope | South Elevation | Exterior envelope | #C6E0B4 | E8 | Waterproofing Around Window Opening / Caulking & Flashing | 2027-04-23 | 2027-04-29
Building Envelope | South Elevation | Exterior envelope | #C6E0B4 | E9 | Install Stucco | 2027-04-30 | 2027-06-04
Building Envelope | South Elevation | Exterior envelope | #C6E0B4 | E10 | Install Windows | 2027-06-07 | 2027-06-25
Building Envelope | South Elevation | Exterior envelope | #C6E0B4 | E11 | Final Waterproofing & Caulking | 2027-06-28 | 2027-07-02
Building Envelope | South Elevation | Exterior envelope | #C6E0B4 | E12 | Waterproofing Cure Time | 2027-07-03 | 2027-07-05
Building Envelope | Roof Area A | Roof | #C6E0B4 | R1 | Install Gypsum Roof Sheathing | 2026-11-06 | 2026-11-19
Building Envelope | Roof Area A | Roof | #C6E0B4 | R2 | Install Roofing Membrane | 2026-11-20 | 2026-12-07
Building Envelope | Roof Area A | Roof | #C6E0B4 | R3 | Install Asphalt Roof Shingles | 2026-12-08 | 2026-12-14
Building Envelope | Roof Area A | Roof | #C6E0B4 | R4 | Roof Finishes & Guttering | 2026-12-15 | 2026-12-29
Building Envelope | Roof Podium (Middle Section) | Roof | #C6E0B4 | R1 | Install Gypsum Roof Sheathing | 2027-01-13 | 2027-01-28
Building Envelope | Roof Podium (Middle Section) | Roof | #C6E0B4 | R2 | Install Roofing Membrane | 2027-01-29 | 2027-02-11
Building Envelope | Roof Podium (Middle Section) | Roof | #C6E0B4 | R3 | Install Asphalt Roof Shingles | 2027-02-12 | 2027-02-25
Building Envelope | Roof Podium (Middle Section) | Roof | #C6E0B4 | R4 | Roof Finishes & Guttering | 2027-02-26 | 2027-03-11
Building Envelope | Roof Area B | Roof | #C6E0B4 | R1 | Install Gypsum Roof Sheathing | 2027-01-29 | 2027-02-11
Building Envelope | Roof Area B | Roof | #C6E0B4 | R2 | Install Roofing Membrane | 2027-02-12 | 2027-02-25
Building Envelope | Roof Area B | Roof | #C6E0B4 | R3 | Install Asphalt Roof Shingles | 2027-02-26 | 2027-03-04
Building Envelope | Roof Area B | Roof | #C6E0B4 | R4 | Roof Finishes & Guttering | 2027-03-12 | 2027-03-25
Vertical Transportation | Elevators | Elevators | #BFBFBF | V1 | Install Elevator #1 & 2 | 2027-03-02 | 2027-03-29
Vertical Transportation | Elevators | Elevators | #BFBFBF | V1 | Install Elevators #3 & #4 | 2027-03-02 | 2027-03-29
Vertical Transportation | Stairs | Stairs | #BFBFBF | V2 | Install Stairs #001 | 2025-05-28 | 2025-05-28
Vertical Transportation | Stairs | Stairs | #BFBFBF | V2 | Install Stairs #002 | 2025-05-28 | 2025-05-28
Vertical Transportation | Stairs | Stairs | #BFBFBF | V2 | Install Stairs #003 | 2025-05-28 | 2025-05-28
Vertical Transportation | Stairs | Stairs | #BFBFBF | V2 | Install Stairs #004 | 2025-05-28 | 2025-05-28
Vertical Transportation | Stairs | Stairs | #BFBFBF | V2 | Install Stairs #005 | 2025-05-28 | 2025-05-28
Vertical Transportation | Stairs | Stairs | #BFBFBF | V2 | Install Stairs #006 | 2025-05-28 | 2025-05-28
Interior Finishes | Area A - Lvl 1 | MEP | #006064 | I1 | Mechanical O/H Rough In | 2026-06-17 | 2026-07-08
Interior Finishes | Area A - Lvl 1 | MEP | #006064 | I2 | Electrical O/H Rough In | 2026-06-17 | 2026-07-08
Interior Finishes | Area A - Lvl 1 | MEP | #006064 | I3 | Plumbing O/H Rough In | 2026-06-17 | 2026-07-08
Interior Finishes | Area A - Lvl 1 | MEP | #006064 | I4 | Low Voltage O/H Rough In | 2026-06-17 | 2026-07-08
Interior Finishes | Area A - Lvl 1 | Fire Supression | #006064 | I5 | Fire Suppression O/H Rough In | 2026-07-01 | 2026-07-15
Interior Finishes | Area A - Lvl 1 | Walls | #006064 | I6 | Install Remaining Walls | 2026-07-09 | 2026-07-15
Interior Finishes | Area A - Lvl 1 | MEP | #006064 | I7 | Mechanical In Wall Rough In | 2026-07-16 | 2026-08-05
Interior Finishes | Area A - Lvl 1 | MEP | #006064 | I8 | Electrical In Wall Rough In | 2026-07-16 | 2026-08-05
Interior Finishes | Area A - Lvl 1 | MEP | #006064 | I9 | Low Voltage In Wall Rough In | 2026-07-16 | 2026-08-05
Interior Finishes | Area A - Lvl 1 | MEP | #006064 | I10 | Plumbing In Wall Rough In | 2026-07-16 | 2026-08-05
Interior Finishes | Area A - Lvl 1 | MEP | #006064 | I11 | MEP Inspections | 2026-08-06 | 2026-08-06
Interior Finishes | Area A - Lvl 1 | Walls | #006064 | I12 | Drywall Wall | 2026-08-07 | 2026-08-20
Interior Finishes | Area A - Lvl 1 | Walls | #006064 | I13 | Tape / Bed / Float Walls | 2026-08-21 | 2026-09-03
Interior Finishes | Area A - Lvl 1 | Walls | #006064 | I14 | Prime & Paint Walls | 2026-09-04 | 2026-09-11
Interior Finishes | No value assigned | MEP | #006064 | I15 | Install MEP Rough-in | 2025-05-28 | 2026-01-14
Interior Finishes | No value assigned | Walls | #006064 | I16 | Install Interior Framing | 2026-04-21 | 2027-02-03
Interior Finishes | No value assigned | MEP | #006064 | I17 | Install HVAC Systems & Chillers | 2026-11-11 | 2027-02-08
Interior Finishes | No value assigned | MEP | #006064 | I18 | MEP Systems | 2027-01-19 | 2027-06-08
Interior Finishes | No value assigned | Finishes | #006064 | I19 | Interiors Finishes | 2027-03-23 | 2028-01-05
COMMISSIONING | Elevator | COMMISSIONING | #E57373 | C1 | Elevator Commissioning | 2027-03-30 | 2027-04-19
COMMISSIONING | MEP Systems | COMMISSIONING | #E57373 | C2 | Commissioning - MEP Systems | 2027-06-09 | 2028-01-05
COMMISSIONING | Punchlist | COMMISSIONING | #E57373 | C3 | Design Team Punchlist / Owner Punchlist | 2028-01-06 | 2028-01-26
COMMISSIONING | Substantial completion | COMMISSIONING | #E57373 | C4 | TCO Substantial Completion |  | 2028-01-26
COMMISSIONING | Close Out | COMMISSIONING | #E57373 | C5 | Close Out | 2028-01-27 | 2028-02-16