## Sheet1
Phase | Location | Trade | Color | Act Code | Act Name | Start | Finish
Construction | General | Casework | #0097A7 | N1 | Casework | 2025-08-05 | 2025-09-02
Construction | General | Casework | #0097A7 | N2 | Casework - Piping | 2025-08-28 | 2025-09-04
Construction | General | Casework | #0097A7 | N3 | Casework - Electrical | 2025-09-02 | 2025-09-08
Construction | General | Concrete | #A6A6A6 | C1 | Sawcut - Underslab Plumbing | 2025-02-26 | 2025-02-27
Construction | General | Concrete | #A6A6A6 | C2 | Underslab Plumbing | 2025-02-28 | 2025-03-10
Construction | General | Concrete | #A6A6A6 | C3 | Slab Pourback | 2025-03-11 | 2025-03-17
Construction | General | Demolition | #0D47A1 | B1 | Demo - Framing & Ceilings | 2025-01-24 | 2025-01-30
Construction | General | Demolition | #0D47A1 | B2 | Demo - Electrical | 2025-01-31 | 2025-02-13
Construction | General | Demolition | #0D47A1 | B3 | Demo - Mechanical | 2025-02-05 | 2025-02-18
Construction | General | Demolition | #0D47A1 | B4 | Demo - Plumbing & Piping | 2025-02-12 | 2025-02-25
Construction | General | Doors | #687E88 | L1 | Doors & Hardware | 2025-09-18 | 2025-09-19
Construction | General | Drywall | #9C27B0 | D1 | Drywall/Tape/Finish | 2025-06-24 | 2025-06-30
Construction | General | Drywall | #9C27B0 | D2 | Ceiling Grid Install | 2025-07-09 | 2025-07-15
Construction | General | Drywall | #9C27B0 | D3 | Drop Ceiling | 2025-08-13 | 2025-08-19
Construction | General | Electrical | #F57F17 | E1 | Rough-In - Electrical | 2025-05-19 | 2025-06-09
Construction | General | Electrical | #F57F17 | E2 | Ceiling - Light Fixtures | 2025-07-16 | 2025-07-22
Construction | General | Equipment | #4DD0E1 | O1 | Fume Hood/Lab Equipment Installation/Connection | 2025-09-09 | 2025-09-29
Construction | General | Equipment | #4DD0E1 | O2 | Owner Provided Equipment Installation/Connection | 2025-09-30 | 2025-10-27
Construction | General | Equipment | #4DD0E1 | O3 | Equipment Startup | 2025-10-28 | 2025-11-10
Construction | General | Fire Protection | #E57373 | K1 | Rough-In - Fire Protection | 2025-05-27 | 2025-06-02
Construction | General | Fire Protection | #E57373 | K2 | Ceiling - Drop Sprinklers | 2025-07-16 | 2025-07-21
Construction | General | Flooring | #827717 | G1 | Rubber Flooring | 2025-07-29 | 2025-08-04
Construction | General | Framing | #BA68C8 | F1 | Framing + HM Frames | 2025-03-18 | 2025-03-24
Construction | General | Framing | #BA68C8 | F2 | Framing - Backing/Blocking | 2025-03-21 | 2025-04-03
Construction | General | Mechanical | #1B5E20 | M1 | Rough-in - Mechanical | 2025-04-07 | 2025-05-09
Construction | General | Mechanical | #1B5E20 | M2 | Ceiling - Drop GRD's | 2025-07-22 | 2025-07-28
Construction | General | MEP | #A9D08E | J1 | Ceiling - Service Panels (Electrical & Piping) | 2025-07-23 | 2025-08-12
Construction | General | MEP | #A9D08E | J2 | Finishes - Trim MEP, Casework, Arch | 2025-09-09 | 2025-09-17
Construction | General | Painiting | #5B9BD5 | H2 | Final Paint | 2025-09-19 | 2025-09-25
Construction | General | Painting | #5B9BD5 | H1 | Painting - Prime/1st Coat | 2025-07-01 | 2025-07-08
Construction | General | Plumbing | #0000FF | P1 | Rough-In - In Wall Plumbing | 2025-04-28 | 2025-05-16
Construction | General | Plumbing | #0000FF | P2 | Rough-In - Piping | 2025-05-05 | 2025-06-02
Construction | General | Plumbing | #0000FF | P3 | Solder Piping | 2025-05-27 | 2025-06-02
Construction | General | Plumbing | #0000FF | P4 | Orbital Weld Piping | 2025-05-27 | 2025-06-23
Construction | General | Prep | #FBC02D | A1 | Mobilization / Barriers & Signage | 2025-01-13 | 2025-01-16
Construction | General | Prep | #FBC02D | A2 | Utility Safe-Off | 2025-01-17 | 2025-01-23
Commissioning | General | Punchlist | #C00000 | Z1 | Final Inspections | 2025-11-11 | 2025-11-12
Commissioning | General | Punchlist | #C00000 | Z2 | Test & Balance | 2025-11-13 | 2025-11-26
Commissioning | General | Punchlist | #C00000 | Z3 | Commissioning | 2025-12-15 | 2025-12-19
Commissioning | General | Punchlist | #C00000 | Z4 | Punch List | 2025-11-13 | 2025-11-13
Commissioning | General | Punchlist | #C00000 | Z5 | Complete Punch List | 2025-11-14 | 2025-12-01
Commissioning | General | Punchlist | #C00000 | Z6 | TAB Repairs | 2025-12-01 | 2025-12-12
Commissioning | General | Punchlist | #C00000 | Z7 | Project Closeout | 2025-11-13 | 2025-12-05

## CFA - Schedule
2025
|  |  | Jan | [18 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec
|  |  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
phase | location | area | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Construction | General | N/A | A1 | A1 | A1 | A1 | A2 | A2 | A2 | A2 | A2 | A2 | A2 | B1 | B1 | B1 | B1 | B1 | B1 | B1 | B2 | B2 | B2 | B2 | B2 | B2 | B2 | B2 | B2 | B2 | B2 | B2 | B2 | B2 | [12 empty] | C1 | C1 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | [13 empty] | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | [9 empty] | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | [14 empty] | D1 | D1 | D1 | D1 | D1 | D1 | D1 | H1 | H1 | H1 | H1 | H1 | H1 | H1 | H1 | D2 | D2 | D2 | D2 | D2 | D2 | D2 | K2 | K2 | K2 | K2 | K2 | K2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | G1 | G1 | G1 | G1 | G1 | G1 | G1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | N1 | [6 empty] | J2 | J2 | J2 | J2 | J2 | J2 | J2 | J2 | J2 | L1 | L1 | [10 empty] | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O3 | O3 | O3 | O3 | O3 | O3 | O3 | O3 | O3 | O3 | O3 | O3 | O3 | O3
Commissioning | General | N/A | Nov 11: Z1; Nov 12: Z1; Nov 13: Z4; Nov 14: Z5; Nov 15: Z5; Nov 16: Z5; Nov 17: Z5; Nov 18: Z5; Nov 19: Z5; Nov 20: Z5; Nov 21: Z5; Nov 22: Z5; Nov 23: Z5; Nov 24: Z5; Nov 25: Z5; Nov 26: Z5; Nov 27: Z5; Nov 28: Z5; Nov 29: Z5; Nov 30: Z5; Dec 01: Z5; Dec 15: Z3; Dec 16: Z3; Dec 17: Z3; Dec 18: Z3; Dec 19: Z3
Note on D5: Activity Name: Mobilization / Barriers & Signage Phase: Construction Location: General Trade: Prep Start Date: 13-Jan-2025 End Date: 16-Jan-2025
Note on H5: Activity Name: Utility Safe-Off Phase: Construction Location: General Trade: Prep Start Date: 17-Jan-2025 End Date: 23-Jan-2025
Note on O5: Activity Name: Demo - Framing & Ceilings Phase: Construction Location: General Trade: Demolition Start Date: 24-Jan-2025 End Date: 30-Jan-2025
Note on V5: Activity Name: Demo - Electrical Phase: Construction Location: General Trade: Demolition Start Date: 31-Jan-2025 End Date: 13-Feb-2025
Note on AV5: Activity Name: Sawcut - Underslab Plumbing Phase: Construction Location: General Trade: Concrete Start Date: 26-Feb-2025 End Date: 27-Feb-2025
Note on AX5: Activity Name: Underslab Plumbing Phase: Construction Location: General Trade: Concrete Start Date: 28-Feb-2025 End Date: 10-Mar-2025
Note on BI5: Activity Name: Slab Pourback Phase: Construction Location: General Trade: Concrete Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on BP5: Activity Name: Framing + HM Frames Phase: Construction Location: General Trade: Framing Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on CJ5: Activity Name: Rough-in - Mechanical Phase: Construction Location: General Trade: Mechanical Start Date: 07-Apr-2025 End Date: 09-May-2025
Note on DZ5: Activity Name: Rough-In - Electrical Phase: Construction Location: General Trade: Electrical Start Date: 19-May-2025 End Date: 09-Jun-2025
Note on FJ5: Activity Name: Drywall/Tape/Finish Phase: Construction Location: General Trade: Drywall Start Date: 24-Jun-2025 End Date: 30-Jun-2025
Note on FQ5: Activity Name: Painting - Prime/1st Coat Phase: Construction Location: General Trade: Painting Start Date: 01-Jul-2025 End Date: 08-Jul-2025
Note on FY5: Activity Name: Ceiling Grid Install Phase: Construction Location: General Trade: Drywall Start Date: 09-Jul-2025 End Date: 15-Jul-2025
Note on GF5: Activity Name: Ceiling - Drop Sprinklers Phase: Construction Location: General Trade: Fire Protection Start Date: 16-Jul-2025 End Date: 21-Jul-2025
Note on GL5: Activity Name: Ceiling - Drop GRD's Phase: Construction Location: General Trade: Mechanical Start Date: 22-Jul-2025 End Date: 28-Jul-2025
Note on GS5: Activity Name: Rubber Flooring Phase: Construction Location: General Trade: Flooring Start Date: 29-Jul-2025 End Date: 04-Aug-2025
Note on GZ5: Activity Name: Casework Phase: Construction Location: General Trade: Casework Start Date: 05-Aug-2025 End Date: 02-Sep-2025
Note on II5: Activity Name: Finishes - Trim MEP, Casework, Arch Phase: Construction Location: General Trade: MEP Start Date: 09-Sep-2025 End Date: 17-Sep-2025
Note on IR5: Activity Name: Doors & Hardware Phase: Construction Location: General Trade: Doors Start Date: 18-Sep-2025 End Date: 19-Sep-2025
Note on JD5: Activity Name: Owner Provided Equipment Installation/Connection Phase: Construction Location: General Trade: Equipment Start Date: 30-Sep-2025 End Date: 27-Oct-2025
Note on KF5: Activity Name: Equipment Startup Phase: Construction Location: General Trade: Equipment Start Date: 28-Oct-2025 End Date: 10-Nov-2025
Note on KT6: Activity Name: Final Inspections Phase: Commissioning Location: General Trade: Punchlist Start Date: 11-Nov-2025 End Date: 12-Nov-2025
Note on KV6: Activity Name: Punch List Phase: Commissioning Location: General Trade: Punchlist Start Date: 13-Nov-2025 End Date: 13-Nov-2025
Note on KW6: Activity Name: Complete Punch List Phase: Commissioning Location: General Trade: Punchlist Start Date: 14-Nov-2025 End Date: 01-Dec-2025
Note on MB6: Activity Name: Commissioning Phase: Commissioning Location: General Trade: Punchlist Start Date: 15-Dec-2025 End Date: 19-Dec-2025

## CFA - Legends
Commissioning |  | Construction
Punchlist |  | Casework
Z1 | Final Inspections | N1 | Casework
Z2 | Test & Balance | N2 | Casework - Piping
Z3 | Commissioning | N3 | Casework - Electrical
Z4 | Punch List
Z5 | Complete Punch List | Concrete
Z6 | TAB Repairs | C1 | Sawcut - Underslab Plumbing
Z7 | Project Closeout | C2 | Underslab Plumbing
|  | C3 | Slab Pourback
Demolition
|  | B1 | Demo - Framing & Ceilings
|  | B2 | Demo - Electrical
|  | B3 | Demo - Mechanical
|  | B4 | Demo - Plumbing & Piping
Doors
|  | L1 | Doors & Hardware
Drywall
|  | D1 | Drywall/Tape/Finish
|  | D2 | Ceiling Grid Install
|  | D3 | Drop Ceiling
Electrical
|  | E1 | Rough-In - Electrical
|  | E2 | Ceiling - Light Fixtures
Equipment
|  | O1 | Fume Hood/Lab Equipment Installation/Connection
|  | O2 | Owner Provided Equipment Installation/Connection
|  | O3 | Equipment Startup
Fire Protection
|  | K1 | Rough-In - Fire Protection
|  | K2 | Ceiling - Drop Sprinklers
Flooring
|  | G1 | Rubber Flooring
Framing
|  | F1 | Framing + HM Frames
|  | F2 | Framing - Backing/Blocking
MEP
|  | J1 | Ceiling - Service Panels (Electrical & Piping)
|  | J2 | Finishes - Trim MEP, Casework, Arch
Mechanical
|  | M1 | Rough-in - Mechanical
|  | M2 | Ceiling - Drop GRD's
Painiting
|  | H2 | Final Paint
Painting
|  | H1 | Painting - Prime/1st Coat
Plumbing
|  | P1 | Rough-In - In Wall Plumbing
|  | P2 | Rough-In - Piping
|  | P3 | Solder Piping
|  | P4 | Orbital Weld Piping
Prep
|  | A1 | Mobilization / Barriers & Signage
|  | A2 | Utility Safe-Off