## Sheet1
CPM | [6 empty] | 2024 | 2024
[7 empty] | Sep | Sep | [23 empty] | Oct
PM | LT | PM | LT | PM | PM | PM | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
Phase | Location | Trade | Activity Code | Activity Name | Start | Finish | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Phase 1 | Zone 1 | Trade 1 | 1A | Activity 1 | 6-Sep-24 | 20-Sep-24 | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | [9 empty] | 1B | 1B | 1B | 1B | 1B | 1B |  | 1E | 1E | 1E | 1E | 1E | 1E
Phase 1 | Zone 1 | Trade 2 | 2A | Activity 1 | 9-Sep-24 | 15-Sep-24 |  |  |  | 2A | 2A | 2A | 2A | 2A | 2A | 2A | 2B | 2B | 2B | 2B | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C |  |  |  |  | 2C | 2C | 2C | 2C | 2C | 2E | 2E | 2E
Phase 1 | Zone 1 | Trade 1 | 1B | Activity 2 | 30-Sep-24 | 5-Oct-24 | [22 empty] | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D
Phase 1 | Zone 1 | Trade 2 | 2B | Activity 2 | 16-Sep-24 | 19-Sep-24 | [29 empty] | 2D | 2D | 2D
Phase 1 | Zone 1 | Trade 1 | 1C | Activity 3 | 20-Sep-24 | 30-Sep-24
Phase 1 | Zone 1 | Trade 2 | 2C | Activity 3 | 5-Oct-24 | 9-Oct-24
Phase 1 | Zone 1 | Trade 1 | 1D | Activity 4 | 28-Sep-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | 2D | Activity 4 | 5-Oct-24 | 7-Oct-24
Phase 1 | Zone 1 | Trade 1 | 1E | Activity 5 | 7-Oct-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | 2E | Activity 5 | 10-Oct-24 | 12-Oct-24
phase | trade | activity_code | activity_name
Phase 1 | Trade 1 | 1A | Activity 1
|  | 1B | Activity 2
|  | 1C | Activity 3
|  | 1D | Activity 4
|  | 1E | Activity 5
| Trade 2 | 2A | Activity 1
|  | 2B | Activity 2
|  | 2C | Activity 3
|  | 2D | Activity 4
|  | 2E | Activity 5

## Sheet2
CPM | [7 empty] | 2024 | 2024
[8 empty] | Sep | Sep | [23 empty] | Oct
PM | LT | PM |  | LT | PM | PM | PM | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1A | Activity 1 | 6-Sep-24 | 20-Sep-24 | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | [9 empty] | 1B | 1B | 1B | 1B | 1B | 1B |  | 1E | 1E | 1E | 1E | 1E | 1E
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2A | Activity 1 | 9-Sep-24 | 15-Sep-24 |  |  |  | 2A | 2A | 2A | 2A | 2A | 2A | 2A | 2B | 2B | 2B | 2B | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C |  |  |  |  | 2C | 2C | 2C | 2C | 2C | 2E | 2E | 2E
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1B | Activity 2 | 30-Sep-24 | 5-Oct-24 | [22 empty] | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2B | Activity 2 | 16-Sep-24 | 19-Sep-24 | [29 empty] | 2D | 2D | 2D
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1C | Activity 3 | 20-Sep-24 | 30-Sep-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2C | Activity 3 | 5-Oct-24 | 9-Oct-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1D | Activity 4 | 28-Sep-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2D | Activity 4 | 5-Oct-24 | 7-Oct-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1E | Activity 5 | 7-Oct-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2E | Activity 5 | 10-Oct-24 | 12-Oct-24
phase | trade | activity_code | activity_name
Phase 1 | Trade 1 | 1A | Activity 1
|  | 1B | Activity 2
|  | 1C | Activity 3
|  | 1D | Activity 4
|  | 1E | Activity 5
| Trade 2 | 2A | Activity 1
|  | 2B | Activity 2
|  | 2C | Activity 3
|  | 2D | Activity 4
|  | 2E | Activity 5

## Test Dani
CPM | [7 empty] | 2024 | 2024
[8 empty] | Sep | Sep | [23 empty] | Oct
PM | LT | PM |  | LT | PM | PM | PM | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1A | Activity 1 | 6-Sep-24 | 20-Sep-24 | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | [9 empty] | 1B | 1B | 1B | 1B | 1B | 1B |  | 1E | 1E | 1E | 1E | 1E | 1E
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2A | Activity 1 | 9-Sep-24 | 15-Sep-24 |  |  |  | 2A | 2A | 2A | 2A | 2A | 2A | 2A | 2B | 2B | 2B | 2B | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C |  |  |  |  | 2C | 2C | 2C | 2C | 2C | 2E | 2E | 2E
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1B | Activity 2 | 30-Sep-24 | 5-Oct-24 | [22 empty] | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2B | Activity 2 | 16-Sep-24 | 19-Sep-24 | [29 empty] | 2D | 2D | 2D
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1C | Activity 3 | 20-Sep-24 | 30-Sep-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2C | Activity 3 | 5-Oct-24 | 9-Oct-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1D | Activity 4 | 28-Sep-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2D | Activity 4 | 5-Oct-24 | 7-Oct-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1E | Activity 5 | 7-Oct-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2E | Activity 5 | 10-Oct-24 | 12-Oct-24
Phase 1
Trade 1
1A | Activity 1
1B | Activity 2
1C | Activity 3
1D | Activity 4
1E | Activity 5
Trade 2
2A | Activity 1
2B | Activity 2
2C | Activity 3
2D | Activity 4
2E | Activity 5

## Test 2 Dani
CPM | [7 empty] | 2024 | 2024 | [84 empty] | 2025
[8 empty] | Oct | Oct | [23 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr
CPM | LT | CPM | LT | LT | CPM | CPM | CPM | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG | 7-Oct-24 | 11-Oct-24 | MG1 | MG1 | MG1 | MG1 | MG1 |  |  |  |  | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG4 | MG4 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG7 | [6 empty] | MG6 | MG6 | MG6 | MG6 | MG6 |  |  | ER6 | ER6 | ER6 | ER6 | ER6 | ER6 | ER6 | [5 empty] | MG9 | MG9 | MG9 |  |  |  |  | MG11 | MG11 | MG11 | MG11 | MG11 | MG11 | MG11 | MG11 | MG11 |  |  |  | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | [7 empty] | DH12 | DH12 | DH12 | DH12 | DH12 | DH12 | DH12 | C12 | C12 | C12 | C12 | C12 | C12 | C12 | [14 empty] | C8 | C8 | C8 | C8 | C8 | C8 | C8 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C10 | C10 | C10 | C10 | C10 | C10 | C10 | C12 | C12 | C12 | C12 | C12 | C12 | C12 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C16 | C16 | C16 | C16 | C16 | C16 | C16 | C17 | C17 | C17 | C17 | C17 | C17 | C17 | C19 | C19 | C19 | C19 | C19 | C19 | C19 | C18 | C18 | C18 | C18 | C18 | C18 | C18
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 1 - MG | 9-Oct-24 | 15-Oct-24 |  |  | MG2 | MG2 | MG2 | MG2 | MG2 | MG2 | MG2 | ER3 | ER3 | ER3 | ER3 | ER3 | ER3 | ER3 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER4 | ER4 | ER4 |  |  |  |  | MG4 | MG4 | DH6 | DH6 | DH6 | DH6 | DH6 | DH2 | DH2 | DH2 |  |  |  | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 |  | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 |  |  |  | DH12 | DH12 | DH12 | DH12 | DH12 | DH12 | DH12 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | [14 empty] | C20 | C20 | C20 | C20 | C20 | C20 | C20 | C21 | C21 | C21 | C21 | C21 | C21 | C21 | C14 | C14 | C14 | C14 | C14 | C14 | C14 | C13 | C13 | C13 | C13 | C13 | C13 | C13 | C15 | C15 | C15 | C15 | C15 | C15 | C15 | ER7 | ER7 | ER7 | ER7 | ER7 | ER7 | ER7 | C21 | C21 | C21 | C21 | C21 | C21 | C21 | C20 | C20 | C20 | C20 | C20 | C20 | C20 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG3 | Overhead MEP Installation - COLO2 Cell 1 - MG | 16-Oct-24 | 29-Oct-24 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | [7 empty] | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 |  |  | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 |  |  | MG6 | MG6 | MG6 | DH8 | DH8 | DH8 | DH8 | DH8 | DH8 | DH8 | DH4 | DH4 | DH4 | DH4 | DH4 | DH4 | DH4 | DH4 | [6 empty] | C1 | C2 |  |  | C3 | C5 | C4 |  | ER11 | ER11 | ER11 | ER11 | ER11 | ER11 | ER11 | [53 empty] | ER1 | ER1 | ER1 | ER1 | ER1 | ER1 | ER1 | ER3 | ER3 | ER3 | ER3 | ER3 | ER3 | ER3 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | [7 empty] | ER8 | ER8 | ER8 | ER8 | ER8 | ER8 | ER8 | ER10 | ER10 | ER10 | ER10 | ER10 | ER10 | ER10
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG4 | Deliver AHU into Mech. Gallery - COLO2 Cell 1 - MG | 30-Oct-24 | 31-Oct-24 | ER1 | ER1 | ER1 | ER1 | ER1 | ER1 | ER1 | ER1 | ER1 | ER1 | ER1 | ER1 |  |  | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 |  |  |  |  | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH7 | DH7 | DH7 | DH7 | DH7 | DH7 | DH7 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH11 | DH11 | DH11 | DH11 | DH11 | DH11 | DH11 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 |  |  | C7 | C6 | C16 |  | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | [39 empty] | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER4 | ER4 | ER4 | ER4 | ER4 | ER4 | ER4 | ER6 | ER6 | ER6 | ER6 | ER6 | ER6 | ER6 | [7 empty] | ER12 | ER12 | ER12 | ER12 | ER12 | ER12 | ER12 | ER11 | ER11 | ER11 | ER11 | ER11 | ER11 | ER11
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG5 | Install Walls and Primer Paint - COLO2 Cell 1 - MG | 1-Nov-24 | 14-Nov-24 | [7 empty] | MG1 | MG1 | MG1 | MG1 | MG1 | [11 empty] | DH4 | DH4 | DH4 | DH4 | DH4 | DH4 | DH4 | [13 empty] | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER7 | ER7 | ER7 | ER7 | ER7 | ER7 | ER7 | DH8 | DH8 | DH8 | DH8 | DH8 | DH8 | DH8 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 |  |  |  | C10 | C10 | C10 | C10 | C10 | C10 | C10 | C10 | C10 | C10 | C10 | C10
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG6 | Placing the AHU - COLO2 Cell 1 - MG | 22-Nov-24 | 26-Nov-24 | [9 empty] | MG2 | MG2 | MG2 | MG2 | MG2 | MG2 | MG2 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | [7 empty] | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 |  |  | MG7 | ER8 | ER8 | ER8 | ER8 | ER8 | ER8 | ER8 |  | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | [6 empty] | C13 | ER10 | ER10 | ER10 | ER10 | ER10 | ER10 | ER10
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG7 | Layout Ceiling and install Pencile Rod - COLO2 Cell 1 - MG | 15-Nov-24 | 15-Nov-24 | [53 empty] | ER12 | ER12 | ER12 | ER12 | ER12 | ER12 | ER12 | DH7 | DH7 | DH7 | DH7 | DH7 | DH7 | DH7 | [13 empty] | MG9 | MG9 | MG9 | MG9 | MG9 |  |  |  | MG11 | MG11 | MG11 | MG11 | MG11 | MG11 | MG11 | MG11
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG8 | Piping and Electrical Termination to AHUs - COLO2 Cell 1 - MG | 26-Nov-24 | 11-Dec-24 | [56 empty] | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | [9 empty] | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG9 | Pipe Testing - COLO2 Cell 1 - MG | 11-Dec-24 | 13-Dec-24 | [58 empty] | DH6 | DH6 | DH6 | DH6 | DH6 | DH6 | DH6 | DH6 | DH6 | DH6 | DH6 | DH6 | DH6 | DH6 | [16 empty] | DH11 | DH11 | DH11 | DH11 | DH11 | DH11 | DH11
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG10 | Install ceiling and Light Fittings - COLO2 Cell 1 - MG | 13-Dec-24 | 26-Dec-24 | [56 empty] | C6 | C6 | C6 | [5 empty] | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | [10 empty] | C8 | C8 | C8 | C8 | C8 | C8 | C8 | C8 |  |  | C4 | C4 | C4 | C4 | C4
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG11 | Trim out MEP - COLO2 Cell 1 - MG | 18-Dec-24 | 26-Dec-24 | [60 empty] | C1 | C1 | C1 | C1 | C1 | C1 | C1 | [14 empty] | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 |  |  | C5 | C5 | C5 | C5 | C5 | C5 | C5 | C5 | C5 | C5 | C5 | C5
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG12 | Post Wall Overhead MEP - COLO2 Cell 1 - MG | 15-Nov-24 | 6-Dec-24 | [59 empty] | C7 | C7 | C7 | C7 | C7 | C7 | C7 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | [7 empty] | C14 |  |  | C15 | C17
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH5 | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH | 30-Dec-24 | 20-Jan-25 | [91 empty] | C19 | C18
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH3 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 1 - DH | 7-Oct-24 | 22-Oct-24
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH4 | HAC install and Rise - COLO2 Cell 1 - DH | 19-Dec-24 | 26-Dec-24
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH2 | Termination at PDU & Busway- COLO2 Cell 1 - DH | 19-Dec-24 | 3-Jan-25
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH6 | Security Screen Installation - COLO2 Cell 1 - DH | 15-Nov-24 | 19-Nov-24
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH7 | Ceiling Grid and Tile - COLO2 Cell 1 - DH | 20-Nov-24 | 26-Nov-24
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH8 | Install PDU's - COLO2 Cell 1 - DH | 12-Dec-24 | 18-Dec-24
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH9 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 1 - DH | 27-Nov-24 | 11-Dec-24
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH10 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 1 - DH | 27-Dec-24 | 10-Jan-25
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH11 | HAC Placing - COLO2 Cell 1 - DH | 12-Dec-24 | 18-Dec-24
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH12 | Finishes and Signage - COLO2 Cell 1 - DH | 14-Jan-25 | 20-Jan-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C1 | Interior - L1 UPS - COLO2 Cell 1 | 2-Jan-25 | 2-Jan-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C2 | Interior - L1 MSB - COLO2 Cell 1 | 3-Jan-25 | 3-Jan-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C3 | Interior - L1 PDUs - COLO2 Cell 1 | 6-Jan-25 | 6-Jan-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C4 | Interior - L1 AHUs - COLO2 Cell 1 | 8-Jan-25 | 8-Jan-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C5 | Interior - L1 ATSs - COLO2 Cell 1 | 7-Jan-25 | 7-Jan-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C6 | Interior - L1 Busway - COLO2 Cell 1 | 7-Jan-25 | 7-Jan-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C7 | Interior - L1 ADP - COLO2 Cell 1 | 6-Jan-25 | 6-Jan-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C8 | Interior - L2 UPS - COLO2 Cell 1 | 25-Feb-25 | 3-Mar-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C9 | Interior - L2 MSB - COLO2 Cell 1 | 4-Mar-25 | 10-Mar-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C10 | Interior - L2 PDUs - COLO2 Cell 1 | 11-Mar-25 | 17-Mar-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C11 | Interior - L2 AHUs - COLO2 Cell 1 | 25-Mar-25 | 31-Mar-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C12 | Interior - L2 ATSs - COLO2 Cell 1 | 18-Mar-25 | 24-Mar-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C13 | Interior - L2 Busway - COLO2 Cell 1 | 18-Mar-25 | 24-Mar-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C14 | Interior - L2 ADP - COLO2 Cell 1 | 11-Mar-25 | 17-Mar-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C15 | Interior - L3 UPS - COLO2 Cell 1 | 25-Mar-25 | 31-Mar-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C16 | Interior - L3 MSB - COLO2 Cell 1 | 1-Apr-25 | 7-Apr-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C17 | Interior - L3 PDUs - COLO2 Cell 1 | 8-Apr-25 | 14-Apr-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C18 | Interior - L3 AHUs - COLO2 Cell 1 | 22-Apr-25 | 28-Apr-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C19 | Interior - L3 ATSs - COLO2 Cell 1 | 15-Apr-25 | 21-Apr-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C20 | Interior - L3 Busway - COLO2 Cell 1 | 15-Apr-25 | 21-Apr-25
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C21 | Interior - L3 ADP - COLO2 Cell 1 | 8-Apr-25 | 14-Apr-25
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER1 | Install Walls and Primer Paint - COLO2 Cell 1 - ER | 7-Oct-24 | 18-Oct-24
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER2 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 1 - ER | 23-Oct-24 | 5-Nov-24
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER3 | Install Upper Screens - COLO2 Cell 1 - ER | 16-Oct-24 | 22-Oct-24
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER4 | Install Ceiling - COLO2 Cell 1 - ER | 6-Nov-24 | 8-Nov-24
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER5 | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER | 19-Nov-24 | 3-Dec-24
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER6 | Installation of ADP & ATS - COLO2 Cell 1 - ER | 29-Nov-24 | 5-Dec-24
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER7 | Installation of UPS Equipment - COLO2 Cell 1 - ER | 4-Dec-24 | 10-Dec-24
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER8 | Connet to Cable tray and conduit equipment - COLO2 Cell 1 - ER | 3-Dec-24 | 9-Dec-24
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER9 | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | 18-Dec-24 | 9-Jan-25
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER10 | Door Frame Installation - COLO2 Cell 1 - ER | 3-Jan-25 | 9-Jan-25
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER11 | Finishes and Signage - COLO2 Cell 1 - ER | 10-Jan-25 | 16-Jan-25
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER12 | Installation of MSB - COLO2 Cell 1 - ER | 29-Nov-24 | 5-Dec-24
Fitout | COLO 2 Cell 1 Cx L4 | Trade 5 | #FFFFFF | L4 | COLO2 Cx LEV4 - COLO2 | 1-May-25 | 4-Jun-25
Fitout | COLO 2 Cell 1 Cx L5 | Trade 5 | #FFFFFF | L5 | COLO2 Cx LEV5 / IST - COLO2 | 5-Jun-25 | 6-Jun-25
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 2 - MG | 14-Oct-24 | 18-Oct-24
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 2 - MG | 16-Oct-24 | 22-Oct-24
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG3 | Overhead MEP Installation - COLO2 Cell 2 - MG | 30-Oct-24 | 12-Nov-24
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG4 | Deliver AHU into Mech. Gallery - COLO2 Cell 2 - MG | 13-Nov-24 | 14-Nov-24
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG5 | Install Walls and Primer Paint - COLO2 Cell 2 - MG | 15-Nov-24 | 29-Nov-24
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG6 | Placing the AHU - COLO2 Cell 2 - MG | 9-Dec-24 | 11-Dec-24
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG7 | Layout Ceiling and install Pencile Rod - COLO2 Cell 2 - MG | 2-Dec-24 | 2-Dec-24
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG8 | Piping and Electrical Termination to AHUs - COLO2 Cell 2 - MG | 11-Dec-24 | 26-Dec-24
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG9 | Pipe Testing - COLO2 Cell 2 - MG | 26-Dec-24 | 30-Dec-24
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG10 | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | 30-Dec-24 | 10-Jan-25
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG11 | Trim out MEP - COLO2 Cell 2 - MG | 3-Jan-25 | 10-Jan-25
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG12 | Post Wall Overhead MEP - COLO2 Cell 2 - MG | 2-Dec-24 | 20-Dec-24
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH5 | Install Walls and Primer Paint - COLO2 Cell 2 - ER | 21-Oct-24 | 1-Nov-24
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH3 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 2 - ER | 6-Nov-24 | 19-Nov-24
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH4 | Install Upper Screens - COLO2 Cell 2 - ER | 30-Oct-24 | 5-Nov-24
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH2 | Install Ceiling - COLO2 Cell 2 - ER | 20-Nov-24 | 22-Nov-24
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH6 | Below Ceiling MEP Rough In - COLO2 Cell 2 - ER | 4-Dec-24 | 17-Dec-24
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH7 | Installation of ADP & ATS - COLO2 Cell 2 - ER | 6-Dec-24 | 12-Dec-24
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH8 | Installation of UPS Equipment - COLO2 Cell 2 - ER | 11-Dec-24 | 17-Dec-24
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH9 | Connet to Cable tray and conduit equipment - COLO2 Cell 2 - ER | 10-Dec-24 | 16-Dec-24
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH10 | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | 10-Jan-25 | 30-Jan-25
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH11 | Door Frame Installation - COLO2 Cell 2 - ER | 3-Jan-25 | 9-Jan-25
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH12 | Finishes and Signage - COLO2 Cell 2 - ER | 28-Jan-25 | 3-Feb-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C1 | Installation of MSB - COLO2 Cell 2 - ER | 6-Dec-24 | 12-Dec-24
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C2 | Termination at PDU & Busway - COLO2 Cell 2 - DH | 21-Jan-25 | 10-Feb-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C3 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 2 - DH | 23-Oct-24 | 7-Nov-24
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C4 | HAC install and Rise - COLO2 Cell 2 - DH | 6-Jan-25 | 10-Jan-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C5 | Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH | 6-Jan-25 | 17-Jan-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C6 | Security Screen Installation - COLO2 Cell 2 - DH | 2-Dec-24 | 4-Dec-24
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C7 | Ceiling Grid and Tile - COLO2 Cell 2 - DH | 5-Dec-24 | 11-Dec-24
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C8 | Install PDU's - COLO2 Cell 2 - DH | 27-Dec-24 | 3-Jan-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C9 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 2 - DH | 12-Dec-24 | 26-Dec-24
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C10 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 2 - DH | 13-Jan-25 | 24-Jan-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C11 | HAC Placing - COLO2 Cell 2 - DH | 27-Dec-24 | 3-Jan-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C12 | Finishes and Signage - COLO2 Cell 2 - DH | 4-Feb-25 | 10-Feb-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C13 | Interior - L1 UPS - COLO2 Cell 2 | 2-Jan-25 | 2-Jan-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C14 | Interior - L1 MSB - COLO2 Cell 2 | 3-Jan-25 | 3-Jan-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C15 | Interior - L1 PDUs - COLO2 Cell 2 | 6-Jan-25 | 6-Jan-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C16 | Interior - L1 AHUs - COLO2 Cell 2 | 8-Jan-25 | 8-Jan-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C17 | Interior - L1 ATSs - COLO2 Cell 2 | 7-Jan-25 | 7-Jan-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C18 | Interior - L1 Busway - COLO2 Cell 2 | 7-Jan-25 | 7-Jan-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C19 | Interior - L1 ADP - COLO2 Cell 2 | 6-Jan-25 | 6-Jan-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C20 | Interior - L2 UPS - COLO2 Cell 2 | 25-Feb-25 | 3-Mar-25
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C21 | Interior - L2 MSB - COLO2 Cell 2 | 4-Mar-25 | 10-Mar-25
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER1 | Interior - L2 PDUs - COLO2 Cell 2 | 11-Mar-25 | 17-Mar-25
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER2 | Interior - L2 AHUs - COLO2 Cell 2 | 25-Mar-25 | 31-Mar-25
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER3 | Interior - L2 ATSs - COLO2 Cell 2 | 18-Mar-25 | 24-Mar-25
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER4 | Interior - L2 Busway - COLO2 Cell 2 | 18-Mar-25 | 24-Mar-25
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER5 | Interior - L2 ADP - COLO2 Cell 2 | 11-Mar-25 | 17-Mar-25
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER6 | Interior - L3 UPS - COLO2 Cell 2 | 25-Mar-25 | 31-Mar-25
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER7 | Interior - L3 MSB - COLO2 Cell 2 | 1-Apr-25 | 7-Apr-25
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER8 | Interior - L3 PDUs - COLO2 Cell 2 | 8-Apr-25 | 14-Apr-25
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER9 | Interior - L3 AHUs - COLO2 Cell 2 | 22-Apr-25 | 28-Apr-25
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER10 | Interior - L3 ATSs - COLO2 Cell 2 | 15-Apr-25 | 21-Apr-25
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER11 | Interior - L3 Busway - COLO2 Cell 2 | 15-Apr-25 | 21-Apr-25
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER12 | Interior - L3 ADP - COLO2 Cell 2 | 8-Apr-25 | 14-Apr-25
Fitout
Trade 1
MG1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG
MG10 | Install ceiling and Light Fittings - COLO2 Cell 1 - MG
MG11 | Trim out MEP - COLO2 Cell 1 - MG
MG12 | Post Wall Overhead MEP - COLO2 Cell 1 - MG
MG2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 1 - MG
MG3 | Overhead MEP Installation - COLO2 Cell 1 - MG
MG4 | Deliver AHU into Mech. Gallery - COLO2 Cell 1 - MG
MG5 | Install Walls and Primer Paint - COLO2 Cell 1 - MG
MG6 | Placing the AHU - COLO2 Cell 1 - MG
MG7 | Layout Ceiling and install Pencile Rod - COLO2 Cell 1 - MG
MG8 | Piping and Electrical Termination to AHUs - COLO2 Cell 1 - MG
MG9 | Pipe Testing - COLO2 Cell 1 - MG
Trade 2
DH10 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 1 - DH
DH11 | HAC Placing - COLO2 Cell 1 - DH
DH12 | Finishes and Signage - COLO2 Cell 1 - DH
DH2 | Termination at PDU & Busway- COLO2 Cell 1 - DH
DH3 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 1 - DH
DH4 | HAC install and Rise - COLO2 Cell 1 - DH
DH5 | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH
DH6 | Security Screen Installation - COLO2 Cell 1 - DH
DH7 | Ceiling Grid and Tile - COLO2 Cell 1 - DH
DH8 | Install PDU's - COLO2 Cell 1 - DH
DH9 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 1 - DH
Trade 3
C1 | Interior - L1 UPS - COLO2 Cell 1
C10 | Interior - L2 PDUs - COLO2 Cell 1
C11 | Interior - L2 AHUs - COLO2 Cell 1
C12 | Interior - L2 ATSs - COLO2 Cell 1
C13 | Interior - L2 Busway - COLO2 Cell 1
C14 | Interior - L2 ADP - COLO2 Cell 1
C15 | Interior - L3 UPS - COLO2 Cell 1
C16 | Interior - L3 MSB - COLO2 Cell 1
C17 | Interior - L3 PDUs - COLO2 Cell 1
C18 | Interior - L3 AHUs - COLO2 Cell 1
C19 | Interior - L3 ATSs - COLO2 Cell 1
C2 | Interior - L1 MSB - COLO2 Cell 1
C20 | Interior - L3 Busway - COLO2 Cell 1
C21 | Interior - L3 ADP - COLO2 Cell 1
C3 | Interior - L1 PDUs - COLO2 Cell 1
C4 | Interior - L1 AHUs - COLO2 Cell 1
C5 | Interior - L1 ATSs - COLO2 Cell 1
C6 | Interior - L1 Busway - COLO2 Cell 1
C7 | Interior - L1 ADP - COLO2 Cell 1
C8 | Interior - L2 UPS - COLO2 Cell 1
C9 | Interior - L2 MSB - COLO2 Cell 1
Trade 4
ER1 | Install Walls and Primer Paint - COLO2 Cell 1 - ER
ER10 | Door Frame Installation - COLO2 Cell 1 - ER
ER11 | Finishes and Signage - COLO2 Cell 1 - ER
ER12 | Installation of MSB - COLO2 Cell 1 - ER
ER2 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 1 - ER
ER3 | Install Upper Screens - COLO2 Cell 1 - ER
ER4 | Install Ceiling - COLO2 Cell 1 - ER
ER5 | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER
ER6 | Installation of ADP & ATS - COLO2 Cell 1 - ER
ER7 | Installation of UPS Equipment - COLO2 Cell 1 - ER
ER8 | Connet to Cable tray and conduit equipment - COLO2 Cell 1 - ER
ER9 | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER
Trade 5
L4 | COLO2 Cx LEV4 - COLO2
L5 | COLO2 Cx LEV5 / IST - COLO2

## Sheet2
CPM
CPM | LT | CPM | LT | LT | CPM | CPM | CPM
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG | 2024-10-07 08:00 | 2024-10-11 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 1 - MG | 2024-10-09 08:00 | 2024-10-15 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG3 | Overhead MEP Installation - COLO2 Cell 1 - MG | 2024-10-16 08:00 | 2024-10-29 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG4 | Deliver AHU into Mech. Gallery - COLO2 Cell 1 - MG | 2024-10-30 08:00 | 2024-10-31 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG5 | Install Walls and Primer Paint - COLO2 Cell 1 - MG | 2024-11-01 08:00 | 2024-11-14 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG6 | Placing the AHU - COLO2 Cell 1 - MG | 2024-11-22 08:00 | 2024-11-26 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG7 | Layout Ceiling and install Pencile Rod - COLO2 Cell 1 - MG | 2024-11-15 08:00 | 2024-11-15 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG8 | Piping and Electrical Termination to AHUs - COLO2 Cell 1 - MG | 2024-11-26 13:00 | 2024-12-11 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG9 | Pipe Testing - COLO2 Cell 1 - MG | 2024-12-11 13:00 | 2024-12-13 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG10 | Install ceiling and Light Fittings - COLO2 Cell 1 - MG | 2024-12-13 13:00 | 2024-12-26 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG11 | Trim out MEP - COLO2 Cell 1 - MG | 2024-12-18 13:00 | 2024-12-26 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG12 | Post Wall Overhead MEP - COLO2 Cell 1 - MG | 2024-11-15 08:00 | 2024-12-06 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH5 | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH | 2024-12-30 08:00 | 2025-01-20 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH3 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 1 - DH | 2024-10-07 08:00 | 2024-10-22 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH4 | HAC install and Rise - COLO2 Cell 1 - DH | 2024-12-19 08:00 | 2024-12-26 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH2 | Termination at PDU & Busway- COLO2 Cell 1 - DH | 2024-12-19 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH6 | Security Screen Installation - COLO2 Cell 1 - DH | 2024-11-15 08:00 | 2024-11-19 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH7 | Ceiling Grid and Tile - COLO2 Cell 1 - DH | 2024-11-20 08:00 | 2024-11-26 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH8 | Install PDU's - COLO2 Cell 1 - DH | 2024-12-12 08:00 | 2024-12-18 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH9 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 1 - DH | 2024-11-27 08:00 | 2024-12-11 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH10 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 1 - DH | 2024-12-27 08:00 | 2025-01-10 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH11 | HAC Placing - COLO2 Cell 1 - DH | 2024-12-12 08:00 | 2024-12-18 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH12 | Finishes and Signage - COLO2 Cell 1 - DH | 2025-01-14 08:00 | 2025-01-20 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C1 | Interior - L1 UPS - COLO2 Cell 1 | 2025-01-02 08:00 | 2025-01-02 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C2 | Interior - L1 MSB - COLO2 Cell 1 | 2025-01-03 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C3 | Interior - L1 PDUs - COLO2 Cell 1 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C4 | Interior - L1 AHUs - COLO2 Cell 1 | 2025-01-08 08:00 | 2025-01-08 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C5 | Interior - L1 ATSs - COLO2 Cell 1 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C6 | Interior - L1 Busway - COLO2 Cell 1 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C7 | Interior - L1 ADP - COLO2 Cell 1 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C8 | Interior - L2 UPS - COLO2 Cell 1 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C9 | Interior - L2 MSB - COLO2 Cell 1 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C10 | Interior - L2 PDUs - COLO2 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C11 | Interior - L2 AHUs - COLO2 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C12 | Interior - L2 ATSs - COLO2 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C13 | Interior - L2 Busway - COLO2 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C14 | Interior - L2 ADP - COLO2 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C15 | Interior - L3 UPS - COLO2 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C16 | Interior - L3 MSB - COLO2 Cell 1 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C17 | Interior - L3 PDUs - COLO2 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C18 | Interior - L3 AHUs - COLO2 Cell 1 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C19 | Interior - L3 ATSs - COLO2 Cell 1 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C20 | Interior - L3 Busway - COLO2 Cell 1 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C21 | Interior - L3 ADP - COLO2 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER1 | Install Walls and Primer Paint - COLO2 Cell 1 - ER | 2024-10-07 08:00 | 2024-10-18 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER2 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 1 - ER | 2024-10-23 08:00 | 2024-11-05 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER3 | Install Upper Screens - COLO2 Cell 1 - ER | 2024-10-16 08:00 | 2024-10-22 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER4 | Install Ceiling - COLO2 Cell 1 - ER | 2024-11-06 08:00 | 2024-11-08 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER5 | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER | 2024-11-19 08:00 | 2024-12-03 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER6 | Installation of ADP & ATS - COLO2 Cell 1 - ER | 2024-11-29 08:00 | 2024-12-05 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER7 | Installation of UPS Equipment - COLO2 Cell 1 - ER | 2024-12-04 08:00 | 2024-12-10 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER8 | Connet to Cable tray and conduit equipment - COLO2 Cell 1 - ER | 2024-12-03 08:00 | 2024-12-09 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER9 | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | 2024-12-18 08:00 | 2025-01-09 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER10 | Door Frame Installation - COLO2 Cell 1 - ER | 2025-01-03 08:00 | 2025-01-09 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER11 | Finishes and Signage - COLO2 Cell 1 - ER | 2025-01-10 08:00 | 2025-01-16 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER12 | Installation of MSB - COLO2 Cell 1 - ER | 2024-11-29 08:00 | 2024-12-05 17:00
Fitout | COLO 2 Cell 1 Cx L4 | Trade 5 | #FFFFFF | L4 | COLO2 Cx LEV4 - COLO2 | 2025-05-01 08:00 | 2025-06-04 17:00
Fitout | COLO 2 Cell 1 Cx L5 | Trade 5 | #FFFFFF | L5 | COLO2 Cx LEV5 / IST - COLO2 | 2025-06-05 08:00 | 2025-06-06 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 2 - MG | 2024-10-14 08:00 | 2024-10-18 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 2 - MG | 2024-10-16 08:00 | 2024-10-22 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG3 | Overhead MEP Installation - COLO2 Cell 2 - MG | 2024-10-30 08:00 | 2024-11-12 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG4 | Deliver AHU into Mech. Gallery - COLO2 Cell 2 - MG | 2024-11-13 08:00 | 2024-11-14 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG5 | Install Walls and Primer Paint - COLO2 Cell 2 - MG | 2024-11-15 08:00 | 2024-11-29 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG6 | Placing the AHU - COLO2 Cell 2 - MG | 2024-12-09 08:00 | 2024-12-11 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG7 | Layout Ceiling and install Pencile Rod - COLO2 Cell 2 - MG | 2024-12-02 08:00 | 2024-12-02 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG8 | Piping and Electrical Termination to AHUs - COLO2 Cell 2 - MG | 2024-12-11 13:00 | 2024-12-26 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG9 | Pipe Testing - COLO2 Cell 2 - MG | 2024-12-26 13:00 | 2024-12-30 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG10 | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | 2024-12-30 13:00 | 2025-01-10 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG11 | Trim out MEP - COLO2 Cell 2 - MG | 2025-01-03 13:00 | 2025-01-10 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG12 | Post Wall Overhead MEP - COLO2 Cell 2 - MG | 2024-12-02 08:00 | 2024-12-20 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH5 | Install Walls and Primer Paint - COLO2 Cell 2 - ER | 2024-10-21 08:00 | 2024-11-01 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH3 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 2 - ER | 2024-11-06 08:00 | 2024-11-19 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH4 | Install Upper Screens - COLO2 Cell 2 - ER | 2024-10-30 08:00 | 2024-11-05 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH2 | Install Ceiling - COLO2 Cell 2 - ER | 2024-11-20 08:00 | 2024-11-22 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH6 | Below Ceiling MEP Rough In - COLO2 Cell 2 - ER | 2024-12-04 08:00 | 2024-12-17 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH7 | Installation of ADP & ATS - COLO2 Cell 2 - ER | 2024-12-06 08:00 | 2024-12-12 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH8 | Installation of UPS Equipment - COLO2 Cell 2 - ER | 2024-12-11 08:00 | 2024-12-17 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH9 | Connet to Cable tray and conduit equipment - COLO2 Cell 2 - ER | 2024-12-10 08:00 | 2024-12-16 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH10 | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | 2025-01-10 08:00 | 2025-01-30 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH11 | Door Frame Installation - COLO2 Cell 2 - ER | 2025-01-03 08:00 | 2025-01-09 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH12 | Finishes and Signage - COLO2 Cell 2 - ER | 2025-01-28 08:00 | 2025-02-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C1 | Installation of MSB - COLO2 Cell 2 - ER | 2024-12-06 08:00 | 2024-12-12 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C2 | Termination at PDU & Busway - COLO2 Cell 2 - DH | 2025-01-21 08:00 | 2025-02-10 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C3 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 2 - DH | 2024-10-23 08:00 | 2024-11-07 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C4 | HAC install and Rise - COLO2 Cell 2 - DH | 2025-01-06 08:00 | 2025-01-10 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C5 | Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH | 2025-01-06 08:00 | 2025-01-17 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C6 | Security Screen Installation - COLO2 Cell 2 - DH | 2024-12-02 08:00 | 2024-12-04 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C7 | Ceiling Grid and Tile - COLO2 Cell 2 - DH | 2024-12-05 08:00 | 2024-12-11 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C8 | Install PDU's - COLO2 Cell 2 - DH | 2024-12-27 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C9 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 2 - DH | 2024-12-12 08:00 | 2024-12-26 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C10 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 2 - DH | 2025-01-13 08:00 | 2025-01-24 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C11 | HAC Placing - COLO2 Cell 2 - DH | 2024-12-27 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C12 | Finishes and Signage - COLO2 Cell 2 - DH | 2025-02-04 08:00 | 2025-02-10 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C13 | Interior - L1 UPS - COLO2 Cell 2 | 2025-01-02 08:00 | 2025-01-02 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C14 | Interior - L1 MSB - COLO2 Cell 2 | 2025-01-03 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C15 | Interior - L1 PDUs - COLO2 Cell 2 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C16 | Interior - L1 AHUs - COLO2 Cell 2 | 2025-01-08 08:00 | 2025-01-08 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C17 | Interior - L1 ATSs - COLO2 Cell 2 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C18 | Interior - L1 Busway - COLO2 Cell 2 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C19 | Interior - L1 ADP - COLO2 Cell 2 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C20 | Interior - L2 UPS - COLO2 Cell 2 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C21 | Interior - L2 MSB - COLO2 Cell 2 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER1 | Interior - L2 PDUs - COLO2 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER2 | Interior - L2 AHUs - COLO2 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER3 | Interior - L2 ATSs - COLO2 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER4 | Interior - L2 Busway - COLO2 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER5 | Interior - L2 ADP - COLO2 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER6 | Interior - L3 UPS - COLO2 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER7 | Interior - L3 MSB - COLO2 Cell 2 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER8 | Interior - L3 PDUs - COLO2 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER9 | Interior - L3 AHUs - COLO2 Cell 2 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER10 | Interior - L3 ATSs - COLO2 Cell 2 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER11 | Interior - L3 Busway - COLO2 Cell 2 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER12 | Interior - L3 ADP - COLO2 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00

## Framework
CPM | [7 empty] | Gantt
PM | LT | PM | LT | PM | PM | PM
Phase | Location | Trade | Activity Code | Activity Name | Start | Finish |  | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12
Phase 1 | Zone 1 | Trade 1 | 1A | Activity 1 | 2024-09-06 | 2024-09-20 | bar: 2024-09-06 to 2024-09-20
Phase 1 | Zone 1 | Trade 2 | 2A | Activity 1 | 2024-09-09 | 2024-09-15 | bar: 2024-09-09 to 2024-09-15
Phase 1 | Zone 1 | Trade 1 | 1B | Activity 2 | 2024-09-30 | 2024-10-05 | bar: 2024-09-30 to 2024-10-05
Phase 1 | Zone 1 | Trade 2 | 2B | Activity 2 | 2024-09-16 | 2024-09-19 | bar: 2024-09-16 to 2024-09-19
Phase 1 | Zone 1 | Trade 1 | 1C | Activity 3 | 2024-09-20 | 2024-09-30 | bar: 2024-09-20 to 2024-09-30
Phase 1 | Zone 1 | Trade 2 | 2C | Activity 3 | 2024-10-05 | 2024-10-09 | bar: 2024-10-05 to 2024-10-09
Phase 1 | Zone 1 | Trade 1 | 1D | Activity 4 | 2024-09-28 | 2024-10-12 | bar: 2024-09-28 to 2024-10-12
Phase 1 | Zone 1 | Trade 2 | 2D | Activity 4 | 2024-10-05 | 2024-10-07 | bar: 2024-10-05 to 2024-10-07
Phase 1 | Zone 1 | Trade 1 | 1E | Activity 5 | 2024-10-07 | 2024-10-12 | bar: 2024-10-07 to 2024-10-12
Phase 1 | Zone 1 | Trade 2 | 2E | Activity 5 | 2024-10-10 | 2024-10-12 | bar: 2024-10-10 to 2024-10-12
Will be there | Might be there | Not there | Not there | Will be there | Will be there | Will be there
looking for unique and looking same activities done by same trade
Flow Analysis
Legend
[6 empty] | Trade 1 |  | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12
[6 empty] | 1A | Activity 1 | bar: 2024-09-06 to 2024-09-20; 2024-09-28 to 2024-10-12
[6 empty] | 1B | Activity 2 |  |  |  | 2A | 2A | 2A | 2A | 2A | 2A | 2A | 2B | 2B | 2B | 2B | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C |  |  |  |  | 2C | 2C | 2C | 2C | 2C | 2E | 2E | 2E
[6 empty] | 1C | Activity 3 | bar: 2024-09-30 to 2024-10-05; 2024-10-07 to 2024-10-12
[6 empty] | 1D | Activity 4 | bar: 2024-10-05 to 2024-10-07
[6 empty] | 1E | Activity 5
Trade 2
[6 empty] | 2A | Activity 1
[6 empty] | 2B | Activity 2
[6 empty] | 2C | Activity 3
[6 empty] | 2D | Activity 4
[6 empty] | 2E | Activity 5

## Test 2 Dani - WBS
[7 empty] | 2024 | 2024 | [84 empty] | 2025
[7 empty] | Oct | Oct | [23 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr
[7 empty] | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
phase | location | activity_code | color | activity_ins | start | finish | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
Fitout | COLO 2 Cell 1 Commissioning | C1 | #F59CA6 | 0 | 2-Jan-25 | 2-Jan-25 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | DH3 | [7 empty] | MG4 | MG4 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | MG5 | DH6 | DH6 | DH6 | DH6 | DH6 | DH7 | DH7 | DH7 | DH7 | DH7 | DH7 | DH7 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH11 | DH11 | DH11 | DH11 | DH11 | DH11 | DH11 | DH4 | DH4 | DH4 | DH4 | DH4 | DH4 | DH4 | DH4 | [6 empty] | C1 | C2 |  |  | C3 | C5 | C4 | [5 empty] | DH12 | DH12 | DH12 | DH12 | DH12 | DH12 | DH12 | [7 empty] | DH12 | DH12 | DH12 | DH12 | DH12 | DH12 | DH12 | C12 | C12 | C12 | C12 | C12 | C12 | C12 | [14 empty] | C8 | C8 | C8 | C8 | C8 | C8 | C8 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C10 | C10 | C10 | C10 | C10 | C10 | C10 | C12 | C12 | C12 | C12 | C12 | C12 | C12 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C16 | C16 | C16 | C16 | C16 | C16 | C16 | C17 | C17 | C17 | C17 | C17 | C17 | C17 | C19 | C19 | C19 | C19 | C19 | C19 | C19 | C18 | C18 | C18 | C18 | C18 | C18 | C18
|  | C10 | #F59CA6 | 0 | 11-Mar-25 | 17-Mar-25 | MG1 | MG1 | MG1 | MG1 | MG1 |  |  |  |  | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | MG3 | DH4 | DH4 | DH4 | DH4 | DH4 | DH4 | DH4 | ER4 | ER4 | ER4 |  |  |  |  | MG4 | MG4 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 | MG12 |  |  | MG6 | MG6 | MG6 | DH8 | DH8 | DH8 | DH8 | DH8 | DH8 | DH8 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 |  |  | C7 | C6 | C16 |  | ER11 | ER11 | ER11 | ER11 | ER11 | ER11 | ER11 |  |  |  |  | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | [14 empty] | C20 | C20 | C20 | C20 | C20 | C20 | C20 | C21 | C21 | C21 | C21 | C21 | C21 | C21 | C14 | C14 | C14 | C14 | C14 | C14 | C14 | C13 | C13 | C13 | C13 | C13 | C13 | C13 | C15 | C15 | C15 | C15 | C15 | C15 | C15 | ER7 | ER7 | ER7 | ER7 | ER7 | ER7 | ER7 | C21 | C21 | C21 | C21 | C21 | C21 | C21 | C20 | C20 | C20 | C20 | C20 | C20 | C20 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9
|  | C11 | #F59CA6 | 0 | 25-Mar-25 | 31-Mar-25 |  |  | MG2 | MG2 | MG2 | MG2 | MG2 | MG2 | MG2 | ER3 | ER3 | ER3 | ER3 | ER3 | ER3 | ER3 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | [9 empty] | MG7 | [6 empty] | MG6 | MG6 | MG6 | MG6 | MG6 |  |  | ER12 | ER12 | ER12 | ER12 | ER12 | ER12 | ER12 | C1 | C1 | C1 | C1 | C1 | C1 | C1 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | MG10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 | DH10 |  |  | C10 | C10 | C10 | C10 | C10 | C10 | C10 | C10 | C10 | C10 | C10 | C10 | [45 empty] | ER1 | ER1 | ER1 | ER1 | ER1 | ER1 | ER1 | ER3 | ER3 | ER3 | ER3 | ER3 | ER3 | ER3 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | ER2 | [7 empty] | ER12 | ER12 | ER12 | ER12 | ER12 | ER12 | ER12 | ER10 | ER10 | ER10 | ER10 | ER10 | ER10 | ER10
|  | C12 | #F59CA6 | 0 | 18-Mar-25 | 24-Mar-25 | Oct 07: ER1; Oct 08: ER1; Oct 09: ER1; Oct 10: ER1; Oct 11: ER1; Oct 12: ER1; Oct 13: ER1; Oct 14: ER1; Oct 15: ER1; Oct 16: ER1; Oct 17: ER1; Oct 18: ER1; Oct 23: C3; Oct 24: C3; Oct 25: C3; Oct 26: C3; Oct 27: C3; Oct 28: C3; Oct 29: C3; Oct 30: C3; Oct 31: C3; Nov 01: C3; Nov 02: C3; Nov 03: C3; Nov 04: C3; Nov 05: C3; Nov 06: C3; Nov 07: C3; Nov 20: DH2; Nov 21: DH2; Nov 22: DH2; Nov 26: MG8; Nov 27: MG8; Nov 28: MG8; Nov 29: MG8; Nov 30: MG8; Dec 01: MG8; Dec 02: MG8; Dec 03: MG8; Dec 04: MG8; Dec 05: MG8; Dec 06: MG8; Dec 07: MG8; Dec 08: MG8; Dec 09: MG8; Dec 10: MG8; Dec 11: MG8; Dec 18: MG11; Dec 19: MG11; Dec 20: MG11; Dec 21: MG11; Dec 22: MG11; Dec 23: MG11; Dec 24: MG11; Dec 25: MG11; Dec 26: MG11; Dec 30: DH5; Dec 31: DH5; Jan 01: DH5; Jan 02: DH5; Jan 03: DH5; Jan 04: DH5; Jan 05: DH5; Jan 06: DH5; Jan 07: DH5; Jan 08: DH5; Jan 09: DH5; Jan 10: DH5; Jan 11: DH5; Jan 12: DH5; Jan 13: DH5; Jan 14: DH5; Jan 15: DH5; Jan 16: DH5; Jan 17: DH5; Jan 18: DH5; Jan 19: DH5; Jan 20: DH5; Mar 11: ER5; Mar 12: ER5; Mar 13: ER5; Mar 14: ER5; Mar 15: ER5; Mar 16: ER5; Mar 17: ER5; Mar 18: ER4; Mar 19: ER4; Mar 20: ER4; Mar 21: ER4; Mar 22: ER4; Mar 23: ER4; Mar 24: ER4; Mar 25: ER6; Mar 26: ER6; Mar 27: ER6; Mar 28: ER6; Mar 29: ER6; Mar 30: ER6; Mar 31: ER6; Apr 08: ER8; Apr 09: ER8; Apr 10: ER8; Apr 11: ER8; Apr 12: ER8; Apr 13: ER8; Apr 14: ER8; Apr 15: ER11; Apr 16: ER11; Apr 17: ER11; Apr 18: ER11; Apr 19: ER11; Apr 20: ER11; Apr 21: ER11
|  | C13 | #F59CA6 | 0 | 18-Mar-25 | 24-Mar-25 | Oct 14: MG1; Oct 15: MG1; Oct 16: MG1; Oct 17: MG1; Oct 18: MG1; Oct 21: DH5; Oct 22: DH5; Oct 23: DH5; Oct 24: DH5; Oct 25: DH5; Oct 26: DH5; Oct 27: DH5; Oct 28: DH5; Oct 29: DH5; Oct 30: DH5; Oct 31: DH5; Nov 01: DH5; Nov 19: ER5; Nov 20: ER5; Nov 21: ER5; Nov 22: ER5; Nov 23: ER5; Nov 24: ER5; Nov 25: ER5; Nov 26: ER5; Nov 27: ER5; Nov 28: ER5; Nov 29: ER5; Nov 30: ER5; Dec 01: ER5; Dec 02: ER5; Dec 03: ER5; Dec 04: ER7; Dec 05: ER7; Dec 06: ER7; Dec 07: ER7; Dec 08: ER7; Dec 09: ER7; Dec 10: ER7; Dec 11: MG9; Dec 12: MG9; Dec 13: MG9; Dec 26: MG9; Dec 27: MG9; Dec 28: MG9; Dec 29: MG9; Dec 30: MG9; Jan 02: C13; Jan 03: ER10; Jan 04: ER10; Jan 05: ER10; Jan 06: ER10; Jan 07: ER10; Jan 08: ER10; Jan 09: ER10; Jan 10: DH10; Jan 11: DH10; Jan 12: DH10; Jan 13: DH10; Jan 14: DH10; Jan 15: DH10; Jan 16: DH10; Jan 17: DH10; Jan 18: DH10; Jan 19: DH10; Jan 20: DH10; Jan 21: DH10; Jan 22: DH10; Jan 23: DH10; Jan 24: DH10; Jan 25: DH10; Jan 26: DH10; Jan 27: DH10; Jan 28: DH10; Jan 29: DH10; Jan 30: DH10
|  | C14 | #F59CA6 | 0 | 11-Mar-25 | 17-Mar-25 | Oct 16: MG2; Oct 17: MG2; Oct 18: MG2; Oct 19: MG2; Oct 20: MG2; Oct 21: MG2; Oct 22: MG2; Nov 06: DH3; Nov 07: DH3; Nov 08: DH3; Nov 09: DH3; Nov 10: DH3; Nov 11: DH3; Nov 12: DH3; Nov 13: DH3; Nov 14: DH3; Nov 15: DH3; Nov 16: DH3; Nov 17: DH3; Nov 18: DH3; Nov 19: DH3; Nov 29: ER6; Nov 30: ER6; Dec 01: ER6; Dec 02: ER6; Dec 03: ER6; Dec 04: ER6; Dec 05: ER6; Dec 06: DH7; Dec 07: DH7; Dec 08: DH7; Dec 09: DH7; Dec 10: DH7; Dec 11: DH7; Dec 12: DH7; Dec 18: ER9; Dec 19: ER9; Dec 20: ER9; Dec 21: ER9; Dec 22: ER9; Dec 23: ER9; Dec 24: ER9; Dec 25: ER9; Dec 26: ER9; Dec 27: ER9; Dec 28: ER9; Dec 29: ER9; Dec 30: ER9; Dec 31: ER9; Jan 01: ER9; Jan 02: ER9; Jan 03: ER9; Jan 04: ER9; Jan 05: ER9; Jan 06: ER9; Jan 07: ER9; Jan 08: ER9; Jan 09: ER9
|  | C15 | #F59CA6 | 0 | 25-Mar-25 | 31-Mar-25 | Oct 30: MG3; Oct 31: MG3; Nov 01: MG3; Nov 02: MG3; Nov 03: MG3; Nov 04: MG3; Nov 05: MG3; Nov 06: MG3; Nov 07: MG3; Nov 08: MG3; Nov 09: MG3; Nov 10: MG3; Nov 11: MG3; Nov 12: MG3; Nov 15: MG5; Nov 16: MG5; Nov 17: MG5; Nov 18: MG5; Nov 19: MG5; Nov 20: MG5; Nov 21: MG5; Nov 22: MG5; Nov 23: MG5; Nov 24: MG5; Nov 25: MG5; Nov 26: MG5; Nov 27: MG5; Nov 28: MG5; Nov 29: MG5; Dec 02: MG7; Dec 03: ER8; Dec 04: ER8; Dec 05: ER8; Dec 06: ER8; Dec 07: ER8; Dec 08: ER8; Dec 09: ER8; Dec 12: C9; Dec 13: C9; Dec 14: C9; Dec 15: C9; Dec 16: C9; Dec 17: C9; Dec 18: C9; Dec 19: C9; Dec 20: C9; Dec 21: C9; Dec 22: C9; Dec 23: C9; Dec 24: C9; Dec 25: C9; Dec 26: C9; Dec 27: C11; Dec 28: C11; Dec 29: C11; Dec 30: C11; Dec 31: C11; Jan 01: C11; Jan 02: C11; Jan 03: C11; Jan 06: C15; Jan 07: C17
|  | C16 | #F59CA6 | 0 | 1-Apr-25 | 7-Apr-25 | Dec 02: C6; Dec 03: C6; Dec 04: C6; Dec 05: C7; Dec 06: C7; Dec 07: C7; Dec 08: C7; Dec 09: C7; Dec 10: C7; Dec 11: C7; Jan 03: C14; Jan 06: C19; Jan 07: C18
|  | C17 | #F59CA6 | 0 | 8-Apr-25 | 14-Apr-25 | Dec 04: DH6; Dec 05: DH6; Dec 06: DH6; Dec 07: DH6; Dec 08: DH6; Dec 09: DH6; Dec 10: DH6; Dec 11: DH6; Dec 12: DH6; Dec 13: DH6; Dec 14: DH6; Dec 15: DH6; Dec 16: DH6; Dec 17: DH6; Dec 27: C8; Dec 28: C8; Dec 29: C8; Dec 30: C8; Dec 31: C8; Jan 01: C8; Jan 02: C8; Jan 03: C8; Jan 06: C4; Jan 07: C4; Jan 08: C4; Jan 09: C4; Jan 10: C4
|  | C18 | #F59CA6 | 0 | 22-Apr-25 | 28-Apr-25 | Dec 11: DH8; Dec 12: DH8; Dec 13: DH8; Dec 14: DH8; Dec 15: DH8; Dec 16: DH8; Dec 17: DH8; Jan 06: C5; Jan 07: C5; Jan 08: C5; Jan 09: C5; Jan 10: C5; Jan 11: C5; Jan 12: C5; Jan 13: C5; Jan 14: C5; Jan 15: C5; Jan 16: C5; Jan 17: C5
|  | C19 | #F59CA6 | 0 | 15-Apr-25 | 21-Apr-25 | Dec 10: DH9; Dec 11: DH9; Dec 12: DH9; Dec 13: DH9; Dec 14: DH9; Dec 15: DH9; Dec 16: DH9; Jan 03: DH11; Jan 04: DH11; Jan 05: DH11; Jan 06: DH11; Jan 07: DH11; Jan 08: DH11; Jan 09: DH11
|  | C2 | #F59CA6 | 0 | 3-Jan-25 | 3-Jan-25 | Dec 02: MG12; Dec 03: MG12; Dec 04: MG12; Dec 05: MG12; Dec 06: MG12; Dec 07: MG12; Dec 08: MG12; Dec 09: MG12; Dec 10: MG12; Dec 11: MG12; Dec 12: MG12; Dec 13: MG12; Dec 14: MG12; Dec 15: MG12; Dec 16: MG12; Dec 17: MG12; Dec 18: MG12; Dec 19: MG12; Dec 20: MG12; Dec 30: MG10; Dec 31: MG10; Jan 01: MG10; Jan 02: MG10; Jan 03: MG10; Jan 04: MG10; Jan 05: MG10; Jan 06: MG10; Jan 07: MG10; Jan 08: MG10; Jan 09: MG10; Jan 10: MG10
|  | C20 | #F59CA6 | 0 | 15-Apr-25 | 21-Apr-25 | Dec 11: MG8; Dec 12: MG8; Dec 13: MG8; Dec 14: MG8; Dec 15: MG8; Dec 16: MG8; Dec 17: MG8; Dec 18: MG8; Dec 19: MG8; Dec 20: MG8; Dec 21: MG8; Dec 22: MG8; Dec 23: MG8; Dec 24: MG8; Dec 25: MG8; Dec 26: MG8; Jan 03: MG11; Jan 04: MG11; Jan 05: MG11; Jan 06: MG11; Jan 07: MG11; Jan 08: MG11; Jan 09: MG11; Jan 10: MG11
|  | C21 | #F59CA6 | 0 | 8-Apr-25 | 14-Apr-25
|  | C3 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C4 | #F59CA6 | 0 | 8-Jan-25 | 8-Jan-25
|  | C5 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C6 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C7 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C8 | #F59CA6 | 0 | 25-Feb-25 | 3-Mar-25
|  | C9 | #F59CA6 | 0 | 4-Mar-25 | 10-Mar-25
| COLO 2 Cell 1 Data Hall | DH10 | #C5E5A6 | 0 | 27-Dec-24 | 10-Jan-25
|  | DH11 | #C5E5A6 | 0 | 12-Dec-24 | 18-Dec-24
|  | DH12 | #C5E5A6 | 0 | 14-Jan-25 | 20-Jan-25
|  | DH2 | #C5E5A6 | 0 | 19-Dec-24 | 3-Jan-25
|  | DH3 | #C5E5A6 | 0 | 7-Oct-24 | 22-Oct-24
|  | DH4 | #C5E5A6 | 0 | 19-Dec-24 | 26-Dec-24
|  | DH5 | #C5E5A6 | 0 | 30-Dec-24 | 20-Jan-25
|  | DH6 | #C5E5A6 | 0 | 15-Nov-24 | 19-Nov-24
|  | DH7 | #C5E5A6 | 0 | 20-Nov-24 | 26-Nov-24
|  | DH8 | #C5E5A6 | 0 | 12-Dec-24 | 18-Dec-24
|  | DH9 | #C5E5A6 | 0 | 27-Nov-24 | 11-Dec-24
| COLO 2 Cell 1 Mech Gallery | MG1 | #96CEFF | 0 | 7-Oct-24 | 11-Oct-24
|  | MG10 | #96CEFF | 0 | 13-Dec-24 | 26-Dec-24
|  | MG11 | #96CEFF | 0 | 18-Dec-24 | 26-Dec-24
|  | MG12 | #96CEFF | 0 | 15-Nov-24 | 6-Dec-24
|  | MG2 | #96CEFF | 0 | 9-Oct-24 | 15-Oct-24
|  | MG3 | #96CEFF | 0 | 16-Oct-24 | 29-Oct-24
|  | MG4 | #96CEFF | 0 | 30-Oct-24 | 31-Oct-24
|  | MG5 | #96CEFF | 0 | 1-Nov-24 | 14-Nov-24
|  | MG6 | #96CEFF | 0 | 22-Nov-24 | 26-Nov-24
|  | MG7 | #96CEFF | 0 | 15-Nov-24 | 15-Nov-24
|  | MG8 | #96CEFF | 0 | 26-Nov-24 | 11-Dec-24
|  | MG9 | #96CEFF | 0 | 11-Dec-24 | 13-Dec-24
| COLO 2 Cell 1 Cx L4 | L4 | #FFFFFF | 0 | 1-May-25 | 4-Jun-25
| COLO 2 Cell 1 Cx L5 | L5 | #FFFFFF | 0 | 5-Jun-25 | 6-Jun-25
| COLO 2 Cell 1 Electrical Room | ER1 | #FFC000 | 0 | 7-Oct-24 | 18-Oct-24
|  | ER10 | #FFC000 | 0 | 3-Jan-25 | 9-Jan-25
|  | ER11 | #FFC000 | 0 | 10-Jan-25 | 16-Jan-25
|  | ER12 | #FFC000 | 0 | 29-Nov-24 | 5-Dec-24
|  | ER2 | #FFC000 | 0 | 23-Oct-24 | 5-Nov-24
|  | ER3 | #FFC000 | 0 | 16-Oct-24 | 22-Oct-24
|  | ER4 | #FFC000 | 0 | 6-Nov-24 | 8-Nov-24
|  | ER5 | #FFC000 | 0 | 19-Nov-24 | 3-Dec-24
|  | ER6 | #FFC000 | 0 | 29-Nov-24 | 5-Dec-24
|  | ER7 | #FFC000 | 0 | 4-Dec-24 | 10-Dec-24
|  | ER8 | #FFC000 | 0 | 3-Dec-24 | 9-Dec-24
|  | ER9 | #FFC000 | 0 | 18-Dec-24 | 9-Jan-25
| COLO 2 Cell 2 Commissioning | C1 | #F59CA6 | 0 | 6-Dec-24 | 12-Dec-24
|  | C10 | #F59CA6 | 0 | 13-Jan-25 | 24-Jan-25
|  | C11 | #F59CA6 | 0 | 27-Dec-24 | 3-Jan-25
|  | C12 | #F59CA6 | 0 | 4-Feb-25 | 10-Feb-25
|  | C13 | #F59CA6 | 0 | 2-Jan-25 | 2-Jan-25
|  | C14 | #F59CA6 | 0 | 3-Jan-25 | 3-Jan-25
|  | C15 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C16 | #F59CA6 | 0 | 8-Jan-25 | 8-Jan-25
|  | C17 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C18 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C19 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C2 | #F59CA6 | 0 | 21-Jan-25 | 10-Feb-25
|  | C20 | #F59CA6 | 0 | 25-Feb-25 | 3-Mar-25
|  | C21 | #F59CA6 | 0 | 4-Mar-25 | 10-Mar-25
|  | C3 | #F59CA6 | 0 | 23-Oct-24 | 7-Nov-24
|  | C4 | #F59CA6 | 0 | 6-Jan-25 | 10-Jan-25
|  | C5 | #F59CA6 | 0 | 6-Jan-25 | 17-Jan-25
|  | C6 | #F59CA6 | 0 | 2-Dec-24 | 4-Dec-24
|  | C7 | #F59CA6 | 0 | 5-Dec-24 | 11-Dec-24
|  | C8 | #F59CA6 | 0 | 27-Dec-24 | 3-Jan-25
|  | C9 | #F59CA6 | 0 | 12-Dec-24 | 26-Dec-24
| COLO 2 Cell 2 Data Hall | DH10 | #C5E5A6 | 0 | 10-Jan-25 | 30-Jan-25
|  | DH11 | #C5E5A6 | 0 | 3-Jan-25 | 9-Jan-25
|  | DH12 | #C5E5A6 | 0 | 28-Jan-25 | 3-Feb-25
|  | DH2 | #C5E5A6 | 0 | 20-Nov-24 | 22-Nov-24
|  | DH3 | #C5E5A6 | 0 | 6-Nov-24 | 19-Nov-24
|  | DH4 | #C5E5A6 | 0 | 30-Oct-24 | 5-Nov-24
|  | DH5 | #C5E5A6 | 0 | 21-Oct-24 | 1-Nov-24
|  | DH6 | #C5E5A6 | 0 | 4-Dec-24 | 17-Dec-24
|  | DH7 | #C5E5A6 | 0 | 6-Dec-24 | 12-Dec-24
|  | DH8 | #C5E5A6 | 0 | 11-Dec-24 | 17-Dec-24
|  | DH9 | #C5E5A6 | 0 | 10-Dec-24 | 16-Dec-24
| COLO 2 Cell 2 Electrical Room | ER1 | #FFC000 | 0 | 11-Mar-25 | 17-Mar-25
|  | ER10 | #FFC000 | 0 | 15-Apr-25 | 21-Apr-25
|  | ER11 | #FFC000 | 0 | 15-Apr-25 | 21-Apr-25
|  | ER12 | #FFC000 | 0 | 8-Apr-25 | 14-Apr-25
|  | ER2 | #FFC000 | 0 | 25-Mar-25 | 31-Mar-25
|  | ER3 | #FFC000 | 0 | 18-Mar-25 | 24-Mar-25
|  | ER4 | #FFC000 | 0 | 18-Mar-25 | 24-Mar-25
|  | ER5 | #FFC000 | 0 | 11-Mar-25 | 17-Mar-25
|  | ER6 | #FFC000 | 0 | 25-Mar-25 | 31-Mar-25
|  | ER7 | #FFC000 | 0 | 1-Apr-25 | 7-Apr-25
|  | ER8 | #FFC000 | 0 | 8-Apr-25 | 14-Apr-25
|  | ER9 | #FFC000 | 0 | 22-Apr-25 | 28-Apr-25
| COLO 2 Cell 2 Mech Gallery | MG1 | #96CEFF | 0 | 14-Oct-24 | 18-Oct-24
|  | MG10 | #96CEFF | 0 | 30-Dec-24 | 10-Jan-25
|  | MG11 | #96CEFF | 0 | 3-Jan-25 | 10-Jan-25
|  | MG12 | #96CEFF | 0 | 2-Dec-24 | 20-Dec-24
|  | MG2 | #96CEFF | 0 | 16-Oct-24 | 22-Oct-24
|  | MG3 | #96CEFF | 0 | 30-Oct-24 | 12-Nov-24
|  | MG4 | #96CEFF | 0 | 13-Nov-24 | 14-Nov-24
|  | MG5 | #96CEFF | 0 | 15-Nov-24 | 29-Nov-24
|  | MG6 | #96CEFF | 0 | 9-Dec-24 | 11-Dec-24
|  | MG7 | #96CEFF | 0 | 2-Dec-24 | 2-Dec-24
|  | MG8 | #96CEFF | 0 | 11-Dec-24 | 26-Dec-24
|  | MG9 | #96CEFF | 0 | 26-Dec-24 | 30-Dec-24

## Test 2 Dani - WBS 2
[7 empty] | 2024 | 2024 | [84 empty] | 2025
[7 empty] | Oct | Oct | [23 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr
[7 empty] | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
phase | location | activity_code | color | activity_ins | start | finish | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
Fitout | COLO 2 Cell 1 Commissioning | C1 | #F59CA6 | 0 | 2-Jan-25 | 2-Jan-25 | bar: Jan 02
|  | C10 | #F59CA6 | 0 | 11-Mar-25 | 17-Mar-25 | Mar 11: C10; Mar 12: C10; Mar 13: C10; Mar 14: C10; Mar 15: C10; Mar 16: C10; Mar 17: C10
|  | C11 | #F59CA6 | 0 | 25-Mar-25 | 31-Mar-25 | Mar 25: C11; Mar 26: C11; Mar 27: C11; Mar 28: C11; Mar 29: C11; Mar 30: C11; Mar 31: C11
|  | C12 | #F59CA6 | 0 | 18-Mar-25 | 24-Mar-25 | Mar 18: C12; Mar 19: C12; Mar 20: C12; Mar 21: C12; Mar 22: C12; Mar 23: C12; Mar 24: C12
|  | C13 | #F59CA6 | 0 | 18-Mar-25 | 24-Mar-25 | Mar 18: C13; Mar 19: C13; Mar 20: C13; Mar 21: C13; Mar 22: C13; Mar 23: C13; Mar 24: C13
|  | C14 | #F59CA6 | 0 | 11-Mar-25 | 17-Mar-25 | Mar 11: C14; Mar 12: C14; Mar 13: C14; Mar 14: C14; Mar 15: C14; Mar 16: C14; Mar 17: C14
|  | C15 | #F59CA6 | 0 | 25-Mar-25 | 31-Mar-25 | Mar 25: C15; Mar 26: C15; Mar 27: C15; Mar 28: C15; Mar 29: C15; Mar 30: C15; Mar 31: C15
|  | C16 | #F59CA6 | 0 | 1-Apr-25 | 7-Apr-25 | Apr 01: C16; Apr 02: C16; Apr 03: C16; Apr 04: C16; Apr 05: C16; Apr 06: C16; Apr 07: C16
|  | C17 | #F59CA6 | 0 | 8-Apr-25 | 14-Apr-25 | Apr 08: C17; Apr 09: C17; Apr 10: C17; Apr 11: C17; Apr 12: C17; Apr 13: C17; Apr 14: C17
|  | C18 | #F59CA6 | 0 | 22-Apr-25 | 28-Apr-25 | Apr 22: C18; Apr 23: C18; Apr 24: C18; Apr 25: C18; Apr 26: C18; Apr 27: C18; Apr 28: C18
|  | C19 | #F59CA6 | 0 | 15-Apr-25 | 21-Apr-25 | Apr 15: C19; Apr 16: C19; Apr 17: C19; Apr 18: C19; Apr 19: C19; Apr 20: C19; Apr 21: C19
|  | C2 | #F59CA6 | 0 | 3-Jan-25 | 3-Jan-25 | bar: Jan 03
|  | C20 | #F59CA6 | 0 | 15-Apr-25 | 21-Apr-25 | Apr 15: C20; Apr 16: C20; Apr 17: C20; Apr 18: C20; Apr 19: C20; Apr 20: C20; Apr 21: C20
|  | C21 | #F59CA6 | 0 | 8-Apr-25 | 14-Apr-25 | Apr 08: C21; Apr 09: C21; Apr 10: C21; Apr 11: C21; Apr 12: C21; Apr 13: C21; Apr 14: C21
|  | C3 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25 | bar: Jan 06
|  | C4 | #F59CA6 | 0 | 8-Jan-25 | 8-Jan-25 | bar: Jan 08
|  | C5 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25 | bar: Jan 07
|  | C6 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25 | bar: Jan 07
|  | C7 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25 | bar: Jan 06
|  | C8 | #F59CA6 | 0 | 25-Feb-25 | 3-Mar-25 | bar: Feb 25 to Mar 03
|  | C9 | #F59CA6 | 0 | 4-Mar-25 | 10-Mar-25 | bar: Mar 04 to Mar 10
| COLO 2 Cell 1 Data Hall | DH10 | #C5E5A6 | 0 | 27-Dec-24 | 10-Jan-25 | Dec 27: DH10; Dec 28: DH10; Dec 29: DH10; Dec 30: DH10; Dec 31: DH10; Jan 01: DH10; Jan 02: DH10; Jan 03: DH10; Jan 04: DH10; Jan 05: DH10; Jan 06: DH10; Jan 07: DH10; Jan 08: DH10; Jan 09: DH10; Jan 10: DH10
|  | DH11 | #C5E5A6 | 0 | 12-Dec-24 | 18-Dec-24 | Dec 12: DH11; Dec 13: DH11; Dec 14: DH11; Dec 15: DH11; Dec 16: DH11; Dec 17: DH11; Dec 18: DH11
|  | DH12 | #C5E5A6 | 0 | 14-Jan-25 | 20-Jan-25 | Jan 14: DH12; Jan 15: DH12; Jan 16: DH12; Jan 17: DH12; Jan 18: DH12; Jan 19: DH12; Jan 20: DH12
|  | DH2 | #C5E5A6 | 0 | 19-Dec-24 | 3-Jan-25 | Dec 19: DH2; Dec 20: DH2; Dec 21: DH2; Dec 22: DH2; Dec 23: DH2; Dec 24: DH2; Dec 25: DH2; Dec 26: DH2; Dec 27: DH2; Dec 28: DH2; Dec 29: DH2; Dec 30: DH2; Dec 31: DH2; Jan 01: DH2; Jan 02: DH2; Jan 03: DH2
|  | DH3 | #C5E5A6 | 0 | 7-Oct-24 | 22-Oct-24 | Oct 07: DH3; Oct 08: DH3; Oct 09: DH3; Oct 10: DH3; Oct 11: DH3; Oct 12: DH3; Oct 13: DH3; Oct 14: DH3; Oct 15: DH3; Oct 16: DH3; Oct 17: DH3; Oct 18: DH3; Oct 19: DH3; Oct 20: DH3; Oct 21: DH3; Oct 22: DH3
|  | DH4 | #C5E5A6 | 0 | 19-Dec-24 | 26-Dec-24 | Dec 19: DH4; Dec 20: DH4; Dec 21: DH4; Dec 22: DH4; Dec 23: DH4; Dec 24: DH4; Dec 25: DH4; Dec 26: DH4
|  | DH5 | #C5E5A6 | 0 | 30-Dec-24 | 20-Jan-25 | Dec 30: DH5; Dec 31: DH5; Jan 01: DH5; Jan 02: DH5; Jan 03: DH5; Jan 04: DH5; Jan 05: DH5; Jan 06: DH5; Jan 07: DH5; Jan 08: DH5; Jan 09: DH5; Jan 10: DH5; Jan 11: DH5; Jan 12: DH5; Jan 13: DH5; Jan 14: DH5; Jan 15: DH5; Jan 16: DH5; Jan 17: DH5; Jan 18: DH5; Jan 19: DH5; Jan 20: DH5
|  | DH6 | #C5E5A6 | 0 | 15-Nov-24 | 19-Nov-24 | Nov 15: DH6; Nov 16: DH6; Nov 17: DH6; Nov 18: DH6; Nov 19: DH6
|  | DH7 | #C5E5A6 | 0 | 20-Nov-24 | 26-Nov-24 | Nov 20: DH7; Nov 21: DH7; Nov 22: DH7; Nov 23: DH7; Nov 24: DH7; Nov 25: DH7; Nov 26: DH7
|  | DH8 | #C5E5A6 | 0 | 12-Dec-24 | 18-Dec-24 | Dec 12: DH8; Dec 13: DH8; Dec 14: DH8; Dec 15: DH8; Dec 16: DH8; Dec 17: DH8; Dec 18: DH8
|  | DH9 | #C5E5A6 | 0 | 27-Nov-24 | 11-Dec-24 | Nov 27: DH9; Nov 28: DH9; Nov 29: DH9; Nov 30: DH9; Dec 01: DH9; Dec 02: DH9; Dec 03: DH9; Dec 04: DH9; Dec 05: DH9; Dec 06: DH9; Dec 07: DH9; Dec 08: DH9; Dec 09: DH9; Dec 10: DH9; Dec 11: DH9
| COLO 2 Cell 1 Mech Gallery | MG1 | #96CEFF | 0 | 7-Oct-24 | 11-Oct-24 | Oct 07: MG1; Oct 08: MG1; Oct 09: MG1; Oct 10: MG1; Oct 11: MG1
|  | MG10 | #96CEFF | 0 | 13-Dec-24 | 26-Dec-24 | Dec 13: MG10; Dec 14: MG10; Dec 15: MG10; Dec 16: MG10; Dec 17: MG10; Dec 18: MG10; Dec 19: MG10; Dec 20: MG10; Dec 21: MG10; Dec 22: MG10; Dec 23: MG10; Dec 24: MG10; Dec 25: MG10; Dec 26: MG10
|  | MG11 | #96CEFF | 0 | 18-Dec-24 | 26-Dec-24 | Dec 18: MG11; Dec 19: MG11; Dec 20: MG11; Dec 21: MG11; Dec 22: MG11; Dec 23: MG11; Dec 24: MG11; Dec 25: MG11; Dec 26: MG11
|  | MG12 | #96CEFF | 0 | 15-Nov-24 | 6-Dec-24 | Nov 15: MG12; Nov 16: MG12; Nov 17: MG12; Nov 18: MG12; Nov 19: MG12; Nov 20: MG12; Nov 21: MG12; Nov 22: MG12; Nov 23: MG12; Nov 24: MG12; Nov 25: MG12; Nov 26: MG12; Nov 27: MG12; Nov 28: MG12; Nov 29: MG12; Nov 30: MG12; Dec 01: MG12; Dec 02: MG12; Dec 03: MG12; Dec 04: MG12; Dec 05: MG12; Dec 06: MG12
|  | MG2 | #96CEFF | 0 | 9-Oct-24 | 15-Oct-24 | Oct 09: MG2; Oct 10: MG2; Oct 11: MG2; Oct 12: MG2; Oct 13: MG2; Oct 14: MG2; Oct 15: MG2
|  | MG3 | #96CEFF | 0 | 16-Oct-24 | 29-Oct-24 | Oct 16: MG3; Oct 17: MG3; Oct 18: MG3; Oct 19: MG3; Oct 20: MG3; Oct 21: MG3; Oct 22: MG3; Oct 23: MG3; Oct 24: MG3; Oct 25: MG3; Oct 26: MG3; Oct 27: MG3; Oct 28: MG3; Oct 29: MG3
|  | MG4 | #96CEFF | 0 | 30-Oct-24 | 31-Oct-24 | Oct 30: MG4; Oct 31: MG4
|  | MG5 | #96CEFF | 0 | 1-Nov-24 | 14-Nov-24 | Nov 01: MG5; Nov 02: MG5; Nov 03: MG5; Nov 04: MG5; Nov 05: MG5; Nov 06: MG5; Nov 07: MG5; Nov 08: MG5; Nov 09: MG5; Nov 10: MG5; Nov 11: MG5; Nov 12: MG5; Nov 13: MG5; Nov 14: MG5
|  | MG6 | #96CEFF | 0 | 22-Nov-24 | 26-Nov-24 | Nov 22: MG6; Nov 23: MG6; Nov 24: MG6; Nov 25: MG6; Nov 26: MG6
|  | MG7 | #96CEFF | 0 | 15-Nov-24 | 15-Nov-24 | Nov 15: MG7
|  | MG8 | #96CEFF | 0 | 26-Nov-24 | 11-Dec-24 | Nov 26: MG8; Nov 27: MG8; Nov 28: MG8; Nov 29: MG8; Nov 30: MG8; Dec 01: MG8; Dec 02: MG8; Dec 03: MG8; Dec 04: MG8; Dec 05: MG8; Dec 06: MG8; Dec 07: MG8; Dec 08: MG8; Dec 09: MG8; Dec 10: MG8; Dec 11: MG8
|  | MG9 | #96CEFF | 0 | 11-Dec-24 | 13-Dec-24 | Dec 11: MG9; Dec 12: MG9; Dec 13: MG9
| COLO 2 Cell 1 Cx L4 | L4 | #FFFFFF | 0 | 1-May-25 | 4-Jun-25
| COLO 2 Cell 1 Cx L5 | L5 | #FFFFFF | 0 | 5-Jun-25 | 6-Jun-25
| COLO 2 Cell 1 Electrical Room | ER1 | #FFC000 | 0 | 7-Oct-24 | 18-Oct-24 | Oct 07: ER1; Oct 08: ER1; Oct 09: ER1; Oct 10: ER1; Oct 11: ER1; Oct 12: ER1; Oct 13: ER1; Oct 14: ER1; Oct 15: ER1; Oct 16: ER1; Oct 17: ER1; Oct 18: ER1
|  | ER10 | #FFC000 | 0 | 3-Jan-25 | 9-Jan-25 | Jan 03: ER10; Jan 04: ER10; Jan 05: ER10; Jan 06: ER10; Jan 07: ER10; Jan 08: ER10; Jan 09: ER10
|  | ER11 | #FFC000 | 0 | 10-Jan-25 | 16-Jan-25 | Jan 10: ER11; Jan 11: ER11; Jan 12: ER11; Jan 13: ER11; Jan 14: ER11; Jan 15: ER11; Jan 16: ER11
|  | ER12 | #FFC000 | 0 | 29-Nov-24 | 5-Dec-24 | Nov 29: ER12; Nov 30: ER12; Dec 01: ER12; Dec 02: ER12; Dec 03: ER12; Dec 04: ER12; Dec 05: ER12
|  | ER2 | #FFC000 | 0 | 23-Oct-24 | 5-Nov-24 | Oct 23: ER2; Oct 24: ER2; Oct 25: ER2; Oct 26: ER2; Oct 27: ER2; Oct 28: ER2; Oct 29: ER2; Oct 30: ER2; Oct 31: ER2; Nov 01: ER2; Nov 02: ER2; Nov 03: ER2; Nov 04: ER2; Nov 05: ER2
|  | ER3 | #FFC000 | 0 | 16-Oct-24 | 22-Oct-24 | Oct 16: ER3; Oct 17: ER3; Oct 18: ER3; Oct 19: ER3; Oct 20: ER3; Oct 21: ER3; Oct 22: ER3
|  | ER4 | #FFC000 | 0 | 6-Nov-24 | 8-Nov-24 | Nov 06: ER4; Nov 07: ER4; Nov 08: ER4
|  | ER5 | #FFC000 | 0 | 19-Nov-24 | 3-Dec-24 | Nov 19: ER5; Nov 20: ER5; Nov 21: ER5; Nov 22: ER5; Nov 23: ER5; Nov 24: ER5; Nov 25: ER5; Nov 26: ER5; Nov 27: ER5; Nov 28: ER5; Nov 29: ER5; Nov 30: ER5; Dec 01: ER5; Dec 02: ER5; Dec 03: ER5
|  | ER6 | #FFC000 | 0 | 29-Nov-24 | 5-Dec-24 | Nov 29: ER6; Nov 30: ER6; Dec 01: ER6; Dec 02: ER6; Dec 03: ER6; Dec 04: ER6; Dec 05: ER6
|  | ER7 | #FFC000 | 0 | 4-Dec-24 | 10-Dec-24 | Dec 04: ER7; Dec 05: ER7; Dec 06: ER7; Dec 07: ER7; Dec 08: ER7; Dec 09: ER7; Dec 10: ER7
|  | ER8 | #FFC000 | 0 | 3-Dec-24 | 9-Dec-24 | Dec 03: ER8; Dec 04: ER8; Dec 05: ER8; Dec 06: ER8; Dec 07: ER8; Dec 08: ER8; Dec 09: ER8
|  | ER9 | #FFC000 | 0 | 18-Dec-24 | 9-Jan-25 | Dec 18: ER9; Dec 19: ER9; Dec 20: ER9; Dec 21: ER9; Dec 22: ER9; Dec 23: ER9; Dec 24: ER9; Dec 25: ER9; Dec 26: ER9; Dec 27: ER9; Dec 28: ER9; Dec 29: ER9; Dec 30: ER9; Dec 31: ER9; Jan 01: ER9; Jan 02: ER9; Jan 03: ER9; Jan 04: ER9; Jan 05: ER9; Jan 06: ER9; Jan 07: ER9; Jan 08: ER9; Jan 09: ER9
| COLO 2 Cell 2 Commissioning | C1 | #F59CA6 | 0 | 6-Dec-24 | 12-Dec-24 | bar: Dec 06 to Dec 12
|  | C10 | #F59CA6 | 0 | 13-Jan-25 | 24-Jan-25 | Jan 13: C10; Jan 14: C10; Jan 15: C10; Jan 16: C10; Jan 17: C10; Jan 18: C10; Jan 19: C10; Jan 20: C10; Jan 21: C10; Jan 22: C10; Jan 23: C10; Jan 24: C10
|  | C11 | #F59CA6 | 0 | 27-Dec-24 | 3-Jan-25 | Dec 27: C11; Dec 28: C11; Dec 29: C11; Dec 30: C11; Dec 31: C11; Jan 01: C11; Jan 02: C11; Jan 03: C11
|  | C12 | #F59CA6 | 0 | 4-Feb-25 | 10-Feb-25 | Feb 04: C12; Feb 05: C12; Feb 06: C12; Feb 07: C12; Feb 08: C12; Feb 09: C12; Feb 10: C12
|  | C13 | #F59CA6 | 0 | 2-Jan-25 | 2-Jan-25 | Jan 02: C13
|  | C14 | #F59CA6 | 0 | 3-Jan-25 | 3-Jan-25 | Jan 03: C14
|  | C15 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25 | Jan 06: C15
|  | C16 | #F59CA6 | 0 | 8-Jan-25 | 8-Jan-25 | Jan 08: C16
|  | C17 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25 | Jan 07: C17
|  | C18 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25 | Jan 07: C18
|  | C19 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25 | Jan 06: C19
|  | C2 | #F59CA6 | 0 | 21-Jan-25 | 10-Feb-25 | bar: Jan 21 to Feb 10
|  | C20 | #F59CA6 | 0 | 25-Feb-25 | 3-Mar-25 | Feb 25: C20; Feb 26: C20; Feb 27: C20; Feb 28: C20; Mar 01: C20; Mar 02: C20; Mar 03: C20
|  | C21 | #F59CA6 | 0 | 4-Mar-25 | 10-Mar-25 | Mar 04: C21; Mar 05: C21; Mar 06: C21; Mar 07: C21; Mar 08: C21; Mar 09: C21; Mar 10: C21
|  | C3 | #F59CA6 | 0 | 23-Oct-24 | 7-Nov-24 | bar: Oct 23 to Nov 07
|  | C4 | #F59CA6 | 0 | 6-Jan-25 | 10-Jan-25 | bar: Jan 06 to Jan 10
|  | C5 | #F59CA6 | 0 | 6-Jan-25 | 17-Jan-25 | bar: Jan 06 to Jan 17
|  | C6 | #F59CA6 | 0 | 2-Dec-24 | 4-Dec-24 | bar: Dec 02 to Dec 04
|  | C7 | #F59CA6 | 0 | 5-Dec-24 | 11-Dec-24 | bar: Dec 05 to Dec 11
|  | C8 | #F59CA6 | 0 | 27-Dec-24 | 3-Jan-25 | bar: Dec 27 to Jan 03
|  | C9 | #F59CA6 | 0 | 12-Dec-24 | 26-Dec-24 | bar: Dec 12 to Dec 26
| COLO 2 Cell 2 Data Hall | DH10 | #C5E5A6 | 0 | 10-Jan-25 | 30-Jan-25 | Jan 10: DH10; Jan 11: DH10; Jan 12: DH10; Jan 13: DH10; Jan 14: DH10; Jan 15: DH10; Jan 16: DH10; Jan 17: DH10; Jan 18: DH10; Jan 19: DH10; Jan 20: DH10; Jan 21: DH10; Jan 22: DH10; Jan 23: DH10; Jan 24: DH10; Jan 25: DH10; Jan 26: DH10; Jan 27: DH10; Jan 28: DH10; Jan 29: DH10; Jan 30: DH10
|  | DH11 | #C5E5A6 | 0 | 3-Jan-25 | 9-Jan-25 | Jan 03: DH11; Jan 04: DH11; Jan 05: DH11; Jan 06: DH11; Jan 07: DH11; Jan 08: DH11; Jan 09: DH11
|  | DH12 | #C5E5A6 | 0 | 28-Jan-25 | 3-Feb-25 | Jan 28: DH12; Jan 29: DH12; Jan 30: DH12; Jan 31: DH12; Feb 01: DH12; Feb 02: DH12; Feb 03: DH12
|  | DH2 | #C5E5A6 | 0 | 20-Nov-24 | 22-Nov-24 | Nov 20: DH2; Nov 21: DH2; Nov 22: DH2
|  | DH3 | #C5E5A6 | 0 | 6-Nov-24 | 19-Nov-24 | Nov 06: DH3; Nov 07: DH3; Nov 08: DH3; Nov 09: DH3; Nov 10: DH3; Nov 11: DH3; Nov 12: DH3; Nov 13: DH3; Nov 14: DH3; Nov 15: DH3; Nov 16: DH3; Nov 17: DH3; Nov 18: DH3; Nov 19: DH3
|  | DH4 | #C5E5A6 | 0 | 30-Oct-24 | 5-Nov-24 | Oct 30: DH4; Oct 31: DH4; Nov 01: DH4; Nov 02: DH4; Nov 03: DH4; Nov 04: DH4; Nov 05: DH4
|  | DH5 | #C5E5A6 | 0 | 21-Oct-24 | 1-Nov-24 | Oct 21: DH5; Oct 22: DH5; Oct 23: DH5; Oct 24: DH5; Oct 25: DH5; Oct 26: DH5; Oct 27: DH5; Oct 28: DH5; Oct 29: DH5; Oct 30: DH5; Oct 31: DH5; Nov 01: DH5
|  | DH6 | #C5E5A6 | 0 | 4-Dec-24 | 17-Dec-24 | Dec 04: DH6; Dec 05: DH6; Dec 06: DH6; Dec 07: DH6; Dec 08: DH6; Dec 09: DH6; Dec 10: DH6; Dec 11: DH6; Dec 12: DH6; Dec 13: DH6; Dec 14: DH6; Dec 15: DH6; Dec 16: DH6; Dec 17: DH6
|  | DH7 | #C5E5A6 | 0 | 6-Dec-24 | 12-Dec-24 | Dec 06: DH7; Dec 07: DH7; Dec 08: DH7; Dec 09: DH7; Dec 10: DH7; Dec 11: DH7; Dec 12: DH7
|  | DH8 | #C5E5A6 | 0 | 11-Dec-24 | 17-Dec-24 | Dec 11: DH8; Dec 12: DH8; Dec 13: DH8; Dec 14: DH8; Dec 15: DH8; Dec 16: DH8; Dec 17: DH8
|  | DH9 | #C5E5A6 | 0 | 10-Dec-24 | 16-Dec-24 | Dec 10: DH9; Dec 11: DH9; Dec 12: DH9; Dec 13: DH9; Dec 14: DH9; Dec 15: DH9; Dec 16: DH9
| COLO 2 Cell 2 Electrical Room | ER1 | #FFC000 | 0 | 11-Mar-25 | 17-Mar-25 | Mar 11: ER1; Mar 12: ER1; Mar 13: ER1; Mar 14: ER1; Mar 15: ER1; Mar 16: ER1; Mar 17: ER1
|  | ER10 | #FFC000 | 0 | 15-Apr-25 | 21-Apr-25 | Apr 15: ER10; Apr 16: ER10; Apr 17: ER10; Apr 18: ER10; Apr 19: ER10; Apr 20: ER10; Apr 21: ER10
|  | ER11 | #FFC000 | 0 | 15-Apr-25 | 21-Apr-25 | Apr 15: ER11; Apr 16: ER11; Apr 17: ER11; Apr 18: ER11; Apr 19: ER11; Apr 20: ER11; Apr 21: ER11
|  | ER12 | #FFC000 | 0 | 8-Apr-25 | 14-Apr-25 | Apr 08: ER12; Apr 09: ER12; Apr 10: ER12; Apr 11: ER12; Apr 12: ER12; Apr 13: ER12; Apr 14: ER12
|  | ER2 | #FFC000 | 0 | 25-Mar-25 | 31-Mar-25 | Mar 25: ER2; Mar 26: ER2; Mar 27: ER2; Mar 28: ER2; Mar 29: ER2; Mar 30: ER2; Mar 31: ER2
|  | ER3 | #FFC000 | 0 | 18-Mar-25 | 24-Mar-25 | Mar 18: ER3; Mar 19: ER3; Mar 20: ER3; Mar 21: ER3; Mar 22: ER3; Mar 23: ER3; Mar 24: ER3
|  | ER4 | #FFC000 | 0 | 18-Mar-25 | 24-Mar-25 | Mar 18: ER4; Mar 19: ER4; Mar 20: ER4; Mar 21: ER4; Mar 22: ER4; Mar 23: ER4; Mar 24: ER4
|  | ER5 | #FFC000 | 0 | 11-Mar-25 | 17-Mar-25 | Mar 11: ER5; Mar 12: ER5; Mar 13: ER5; Mar 14: ER5; Mar 15: ER5; Mar 16: ER5; Mar 17: ER5
|  | ER6 | #FFC000 | 0 | 25-Mar-25 | 31-Mar-25 | Mar 25: ER6; Mar 26: ER6; Mar 27: ER6; Mar 28: ER6; Mar 29: ER6; Mar 30: ER6; Mar 31: ER6
|  | ER7 | #FFC000 | 0 | 1-Apr-25 | 7-Apr-25 | Apr 01: ER7; Apr 02: ER7; Apr 03: ER7; Apr 04: ER7; Apr 05: ER7; Apr 06: ER7; Apr 07: ER7
|  | ER8 | #FFC000 | 0 | 8-Apr-25 | 14-Apr-25 | Apr 08: ER8; Apr 09: ER8; Apr 10: ER8; Apr 11: ER8; Apr 12: ER8; Apr 13: ER8; Apr 14: ER8
|  | ER9 | #FFC000 | 0 | 22-Apr-25 | 28-Apr-25 | Apr 22: ER9; Apr 23: ER9; Apr 24: ER9; Apr 25: ER9; Apr 26: ER9; Apr 27: ER9; Apr 28: ER9
| COLO 2 Cell 2 Mech Gallery | MG1 | #96CEFF | 0 | 14-Oct-24 | 18-Oct-24 | Oct 14: MG1; Oct 15: MG1; Oct 16: MG1; Oct 17: MG1; Oct 18: MG1
|  | MG10 | #96CEFF | 0 | 30-Dec-24 | 10-Jan-25 | Dec 30: MG10; Dec 31: MG10; Jan 01: MG10; Jan 02: MG10; Jan 03: MG10; Jan 04: MG10; Jan 05: MG10; Jan 06: MG10; Jan 07: MG10; Jan 08: MG10; Jan 09: MG10; Jan 10: MG10
|  | MG11 | #96CEFF | 0 | 3-Jan-25 | 10-Jan-25 | Jan 03: MG11; Jan 04: MG11; Jan 05: MG11; Jan 06: MG11; Jan 07: MG11; Jan 08: MG11; Jan 09: MG11; Jan 10: MG11
|  | MG12 | #96CEFF | 0 | 2-Dec-24 | 20-Dec-24 | Dec 02: MG12; Dec 03: MG12; Dec 04: MG12; Dec 05: MG12; Dec 06: MG12; Dec 07: MG12; Dec 08: MG12; Dec 09: MG12; Dec 10: MG12; Dec 11: MG12; Dec 12: MG12; Dec 13: MG12; Dec 14: MG12; Dec 15: MG12; Dec 16: MG12; Dec 17: MG12; Dec 18: MG12; Dec 19: MG12; Dec 20: MG12
|  | MG2 | #96CEFF | 0 | 16-Oct-24 | 22-Oct-24 | Oct 16: MG2; Oct 17: MG2; Oct 18: MG2; Oct 19: MG2; Oct 20: MG2; Oct 21: MG2; Oct 22: MG2
|  | MG3 | #96CEFF | 0 | 30-Oct-24 | 12-Nov-24 | Oct 30: MG3; Oct 31: MG3; Nov 01: MG3; Nov 02: MG3; Nov 03: MG3; Nov 04: MG3; Nov 05: MG3; Nov 06: MG3; Nov 07: MG3; Nov 08: MG3; Nov 09: MG3; Nov 10: MG3; Nov 11: MG3; Nov 12: MG3
|  | MG4 | #96CEFF | 0 | 13-Nov-24 | 14-Nov-24 | Nov 13: MG4; Nov 14: MG4
|  | MG5 | #96CEFF | 0 | 15-Nov-24 | 29-Nov-24 | Nov 15: MG5; Nov 16: MG5; Nov 17: MG5; Nov 18: MG5; Nov 19: MG5; Nov 20: MG5; Nov 21: MG5; Nov 22: MG5; Nov 23: MG5; Nov 24: MG5; Nov 25: MG5; Nov 26: MG5; Nov 27: MG5; Nov 28: MG5; Nov 29: MG5
|  | MG6 | #96CEFF | 0 | 9-Dec-24 | 11-Dec-24 | Dec 09: MG6; Dec 10: MG6; Dec 11: MG6
|  | MG7 | #96CEFF | 0 | 2-Dec-24 | 2-Dec-24 | Dec 02: MG7
|  | MG8 | #96CEFF | 0 | 11-Dec-24 | 26-Dec-24 | Dec 11: MG8; Dec 12: MG8; Dec 13: MG8; Dec 14: MG8; Dec 15: MG8; Dec 16: MG8; Dec 17: MG8; Dec 18: MG8; Dec 19: MG8; Dec 20: MG8; Dec 21: MG8; Dec 22: MG8; Dec 23: MG8; Dec 24: MG8; Dec 25: MG8; Dec 26: MG8
|  | MG9 | #96CEFF | 0 | 26-Dec-24 | 30-Dec-24 | Dec 26: MG9; Dec 27: MG9; Dec 28: MG9; Dec 29: MG9; Dec 30: MG9

## Test 2 Dani - WBS 3
[7 empty] | 2024 | 2024 | [84 empty] | 2025
[7 empty] | Oct | Oct | [23 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun
[7 empty] | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06
phase | location | activity_code | color | activity_ins | start | finish | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Fitout | COLO 2 Cell 1 Commissioning | C1 | #F59CA6 | 0 | 2-Jan-25 | 2-Jan-25 | bar: Jan 02
|  | C10 | #F59CA6 | 0 | 11-Mar-25 | 17-Mar-25 | Jan 03: C2; Jan 06: C3; Jan 07: C5; Jan 08: C4; Feb 25: C8; Feb 26: C8; Feb 27: C8; Feb 28: C8; Mar 01: C8; Mar 02: C8; Mar 03: C8; Mar 11: C10; Mar 12: C10; Mar 13: C10; Mar 14: C10; Mar 15: C10; Mar 16: C10; Mar 17: C10; Mar 18: C12; Mar 19: C12; Mar 20: C12; Mar 21: C12; Mar 22: C12; Mar 23: C12; Mar 24: C12; Mar 25: C11; Mar 26: C11; Mar 27: C11; Mar 28: C11; Mar 29: C11; Mar 30: C11; Mar 31: C11; Apr 01: C16; Apr 02: C16; Apr 03: C16; Apr 04: C16; Apr 05: C16; Apr 06: C16; Apr 07: C16; Apr 08: C17; Apr 09: C17; Apr 10: C17; Apr 11: C17; Apr 12: C17; Apr 13: C17; Apr 14: C17; Apr 15: C19; Apr 16: C19; Apr 17: C19; Apr 18: C19; Apr 19: C19; Apr 20: C19; Apr 21: C19; Apr 22: C18; Apr 23: C18; Apr 24: C18; Apr 25: C18; Apr 26: C18; Apr 27: C18; Apr 28: C18
|  | C11 | #F59CA6 | 0 | 25-Mar-25 | 31-Mar-25 | Jan 06: C7; Jan 07: C6; Mar 11: C14; Mar 12: C14; Mar 13: C14; Mar 14: C14; Mar 15: C14; Mar 16: C14; Mar 17: C14; Mar 18: C13; Mar 19: C13; Mar 20: C13; Mar 21: C13; Mar 22: C13; Mar 23: C13; Mar 24: C13; Mar 25: C15; Mar 26: C15; Mar 27: C15; Mar 28: C15; Mar 29: C15; Mar 30: C15; Mar 31: C15; Apr 08: C21; Apr 09: C21; Apr 10: C21; Apr 11: C21; Apr 12: C21; Apr 13: C21; Apr 14: C21; Apr 15: C20; Apr 16: C20; Apr 17: C20; Apr 18: C20; Apr 19: C20; Apr 20: C20; Apr 21: C20
|  | C12 | #F59CA6 | 0 | 18-Mar-25 | 24-Mar-25
|  | C13 | #F59CA6 | 0 | 18-Mar-25 | 24-Mar-25
|  | C14 | #F59CA6 | 0 | 11-Mar-25 | 17-Mar-25
|  | C15 | #F59CA6 | 0 | 25-Mar-25 | 31-Mar-25
|  | C16 | #F59CA6 | 0 | 1-Apr-25 | 7-Apr-25
|  | C17 | #F59CA6 | 0 | 8-Apr-25 | 14-Apr-25
|  | C18 | #F59CA6 | 0 | 22-Apr-25 | 28-Apr-25
|  | C19 | #F59CA6 | 0 | 15-Apr-25 | 21-Apr-25
|  | C2 | #F59CA6 | 0 | 3-Jan-25 | 3-Jan-25
|  | C20 | #F59CA6 | 0 | 15-Apr-25 | 21-Apr-25
|  | C21 | #F59CA6 | 0 | 8-Apr-25 | 14-Apr-25
|  | C3 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C4 | #F59CA6 | 0 | 8-Jan-25 | 8-Jan-25
|  | C5 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C6 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C7 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C8 | #F59CA6 | 0 | 25-Feb-25 | 3-Mar-25
|  | C9 | #F59CA6 | 0 | 4-Mar-25 | 10-Mar-25 | bar: Mar 04 to Mar 10
| COLO 2 Cell 1 Data Hall | DH10 | #C5E5A6 | 0 | 27-Dec-24 | 10-Jan-25 | Dec 27: DH10; Dec 28: DH10; Dec 29: DH10; Dec 30: DH10; Dec 31: DH10; Jan 01: DH10; Jan 02: DH10; Jan 03: DH10; Jan 04: DH10; Jan 05: DH10; Jan 06: DH10; Jan 07: DH10; Jan 08: DH10; Jan 09: DH10; Jan 10: DH10
|  | DH11 | #C5E5A6 | 0 | 12-Dec-24 | 18-Dec-24 | Oct 07: DH3; Oct 08: DH3; Oct 09: DH3; Oct 10: DH3; Oct 11: DH3; Oct 12: DH3; Oct 13: DH3; Oct 14: DH3; Oct 15: DH3; Oct 16: DH3; Oct 17: DH3; Oct 18: DH3; Oct 19: DH3; Oct 20: DH3; Oct 21: DH3; Oct 22: DH3; Nov 15: DH6; Nov 16: DH6; Nov 17: DH6; Nov 18: DH6; Nov 19: DH6; Nov 20: DH7; Nov 21: DH7; Nov 22: DH7; Nov 23: DH7; Nov 24: DH7; Nov 25: DH7; Nov 26: DH7; Dec 12: DH11; Dec 13: DH11; Dec 14: DH11; Dec 15: DH11; Dec 16: DH11; Dec 17: DH11; Dec 18: DH11; Dec 19: DH2; Dec 20: DH2; Dec 21: DH2; Dec 22: DH2; Dec 23: DH2; Dec 24: DH2; Dec 25: DH2; Dec 26: DH2; Dec 27: DH2; Dec 28: DH2; Dec 29: DH2; Dec 30: DH2; Dec 31: DH2; Jan 01: DH2; Jan 02: DH2; Jan 03: DH2; Jan 14: DH12; Jan 15: DH12; Jan 16: DH12; Jan 17: DH12; Jan 18: DH12; Jan 19: DH12; Jan 20: DH12
|  | DH12 | #C5E5A6 | 0 | 14-Jan-25 | 20-Jan-25 | Dec 12: DH8; Dec 13: DH8; Dec 14: DH8; Dec 15: DH8; Dec 16: DH8; Dec 17: DH8; Dec 18: DH8; Dec 19: DH4; Dec 20: DH4; Dec 21: DH4; Dec 22: DH4; Dec 23: DH4; Dec 24: DH4; Dec 25: DH4; Dec 26: DH4; Dec 30: DH5; Dec 31: DH5; Jan 01: DH5; Jan 02: DH5; Jan 03: DH5; Jan 04: DH5; Jan 05: DH5; Jan 06: DH5; Jan 07: DH5; Jan 08: DH5; Jan 09: DH5; Jan 10: DH5; Jan 11: DH5; Jan 12: DH5; Jan 13: DH5; Jan 14: DH5; Jan 15: DH5; Jan 16: DH5; Jan 17: DH5; Jan 18: DH5; Jan 19: DH5; Jan 20: DH5
|  | DH2 | #C5E5A6 | 0 | 19-Dec-24 | 3-Jan-25
|  | DH3 | #C5E5A6 | 0 | 7-Oct-24 | 22-Oct-24
|  | DH4 | #C5E5A6 | 0 | 19-Dec-24 | 26-Dec-24
|  | DH5 | #C5E5A6 | 0 | 30-Dec-24 | 20-Jan-25
|  | DH6 | #C5E5A6 | 0 | 15-Nov-24 | 19-Nov-24
|  | DH7 | #C5E5A6 | 0 | 20-Nov-24 | 26-Nov-24
|  | DH8 | #C5E5A6 | 0 | 12-Dec-24 | 18-Dec-24
|  | DH9 | #C5E5A6 | 0 | 27-Nov-24 | 11-Dec-24 | Nov 27: DH9; Nov 28: DH9; Nov 29: DH9; Nov 30: DH9; Dec 01: DH9; Dec 02: DH9; Dec 03: DH9; Dec 04: DH9; Dec 05: DH9; Dec 06: DH9; Dec 07: DH9; Dec 08: DH9; Dec 09: DH9; Dec 10: DH9; Dec 11: DH9
| COLO 2 Cell 1 Mech Gallery | MG1 | #96CEFF | 0 | 7-Oct-24 | 11-Oct-24 | Oct 07: MG1; Oct 08: MG1; Oct 09: MG1; Oct 10: MG1; Oct 11: MG1
|  | MG10 | #96CEFF | 0 | 13-Dec-24 | 26-Dec-24 | Oct 09: MG2; Oct 10: MG2; Oct 11: MG2; Oct 12: MG2; Oct 13: MG2; Oct 14: MG2; Oct 15: MG2; Oct 16: MG3; Oct 17: MG3; Oct 18: MG3; Oct 19: MG3; Oct 20: MG3; Oct 21: MG3; Oct 22: MG3; Oct 23: MG3; Oct 24: MG3; Oct 25: MG3; Oct 26: MG3; Oct 27: MG3; Oct 28: MG3; Oct 29: MG3; Oct 30: MG4; Oct 31: MG4; Nov 01: MG5; Nov 02: MG5; Nov 03: MG5; Nov 04: MG5; Nov 05: MG5; Nov 06: MG5; Nov 07: MG5; Nov 08: MG5; Nov 09: MG5; Nov 10: MG5; Nov 11: MG5; Nov 12: MG5; Nov 13: MG5; Nov 14: MG5; Nov 15: MG12; Nov 16: MG12; Nov 17: MG12; Nov 18: MG12; Nov 19: MG12; Nov 20: MG12; Nov 21: MG12; Nov 22: MG12; Nov 23: MG12; Nov 24: MG12; Nov 25: MG12; Nov 26: MG12; Nov 27: MG12; Nov 28: MG12; Nov 29: MG12; Nov 30: MG12; Dec 01: MG12; Dec 02: MG12; Dec 03: MG12; Dec 04: MG12; Dec 05: MG12; Dec 06: MG12; Dec 13: MG10; Dec 14: MG10; Dec 15: MG10; Dec 16: MG10; Dec 17: MG10; Dec 18: MG10; Dec 19: MG10; Dec 20: MG10; Dec 21: MG10; Dec 22: MG10; Dec 23: MG10; Dec 24: MG10; Dec 25: MG10; Dec 26: MG10
|  | MG11 | #96CEFF | 0 | 18-Dec-24 | 26-Dec-24 | Nov 15: MG7; Nov 22: MG6; Nov 23: MG6; Nov 24: MG6; Nov 25: MG6; Nov 26: MG6; Dec 18: MG11; Dec 19: MG11; Dec 20: MG11; Dec 21: MG11; Dec 22: MG11; Dec 23: MG11; Dec 24: MG11; Dec 25: MG11; Dec 26: MG11
|  | MG12 | #96CEFF | 0 | 15-Nov-24 | 6-Dec-24 | Nov 26: MG8; Nov 27: MG8; Nov 28: MG8; Nov 29: MG8; Nov 30: MG8; Dec 01: MG8; Dec 02: MG8; Dec 03: MG8; Dec 04: MG8; Dec 05: MG8; Dec 06: MG8; Dec 07: MG8; Dec 08: MG8; Dec 09: MG8; Dec 10: MG8; Dec 11: MG8
|  | MG2 | #96CEFF | 0 | 9-Oct-24 | 15-Oct-24
|  | MG3 | #96CEFF | 0 | 16-Oct-24 | 29-Oct-24
|  | MG4 | #96CEFF | 0 | 30-Oct-24 | 31-Oct-24
|  | MG5 | #96CEFF | 0 | 1-Nov-24 | 14-Nov-24
|  | MG6 | #96CEFF | 0 | 22-Nov-24 | 26-Nov-24
|  | MG7 | #96CEFF | 0 | 15-Nov-24 | 15-Nov-24
|  | MG8 | #96CEFF | 0 | 26-Nov-24 | 11-Dec-24
|  | MG9 | #96CEFF | 0 | 11-Dec-24 | 13-Dec-24 | Dec 11: MG9; Dec 12: MG9; Dec 13: MG9
| COLO 2 Cell 1 Cx L4 | L4 | #FFFFFF | 0 | 1-May-25 | 4-Jun-25 | bar: May 01 to Jun 04
| COLO 2 Cell 1 Cx L5 | L5 | #FFFFFF | 0 | 5-Jun-25 | 6-Jun-25 | bar: Jun 05 to Jun 06
| COLO 2 Cell 1 Electrical Room | ER1 | #FFC000 | 0 | 7-Oct-24 | 18-Oct-24 | Oct 07: ER1; Oct 08: ER1; Oct 09: ER1; Oct 10: ER1; Oct 11: ER1; Oct 12: ER1; Oct 13: ER1; Oct 14: ER1; Oct 15: ER1; Oct 16: ER1; Oct 17: ER1; Oct 18: ER1
|  | ER10 | #FFC000 | 0 | 3-Jan-25 | 9-Jan-25 | Oct 16: ER3; Oct 17: ER3; Oct 18: ER3; Oct 19: ER3; Oct 20: ER3; Oct 21: ER3; Oct 22: ER3; Oct 23: ER2; Oct 24: ER2; Oct 25: ER2; Oct 26: ER2; Oct 27: ER2; Oct 28: ER2; Oct 29: ER2; Oct 30: ER2; Oct 31: ER2; Nov 01: ER2; Nov 02: ER2; Nov 03: ER2; Nov 04: ER2; Nov 05: ER2; Nov 06: ER4; Nov 07: ER4; Nov 08: ER4; Nov 29: ER12; Nov 30: ER12; Dec 01: ER12; Dec 02: ER12; Dec 03: ER12; Dec 04: ER12; Dec 05: ER12; Jan 03: ER10; Jan 04: ER10; Jan 05: ER10; Jan 06: ER10; Jan 07: ER10; Jan 08: ER10; Jan 09: ER10; Jan 10: ER11; Jan 11: ER11; Jan 12: ER11; Jan 13: ER11; Jan 14: ER11; Jan 15: ER11; Jan 16: ER11
|  | ER11 | #FFC000 | 0 | 10-Jan-25 | 16-Jan-25 | Nov 19: ER5; Nov 20: ER5; Nov 21: ER5; Nov 22: ER5; Nov 23: ER5; Nov 24: ER5; Nov 25: ER5; Nov 26: ER5; Nov 27: ER5; Nov 28: ER5; Nov 29: ER5; Nov 30: ER5; Dec 01: ER5; Dec 02: ER5; Dec 03: ER5; Dec 04: ER7; Dec 05: ER7; Dec 06: ER7; Dec 07: ER7; Dec 08: ER7; Dec 09: ER7; Dec 10: ER7
|  | ER12 | #FFC000 | 0 | 29-Nov-24 | 5-Dec-24 | Nov 29: ER6; Nov 30: ER6; Dec 01: ER6; Dec 02: ER6; Dec 03: ER6; Dec 04: ER6; Dec 05: ER6
|  | ER2 | #FFC000 | 0 | 23-Oct-24 | 5-Nov-24 | Dec 03: ER8; Dec 04: ER8; Dec 05: ER8; Dec 06: ER8; Dec 07: ER8; Dec 08: ER8; Dec 09: ER8
|  | ER3 | #FFC000 | 0 | 16-Oct-24 | 22-Oct-24
|  | ER4 | #FFC000 | 0 | 6-Nov-24 | 8-Nov-24
|  | ER5 | #FFC000 | 0 | 19-Nov-24 | 3-Dec-24
|  | ER6 | #FFC000 | 0 | 29-Nov-24 | 5-Dec-24
|  | ER7 | #FFC000 | 0 | 4-Dec-24 | 10-Dec-24
|  | ER8 | #FFC000 | 0 | 3-Dec-24 | 9-Dec-24
|  | ER9 | #FFC000 | 0 | 18-Dec-24 | 9-Jan-25 | Dec 18: ER9; Dec 19: ER9; Dec 20: ER9; Dec 21: ER9; Dec 22: ER9; Dec 23: ER9; Dec 24: ER9; Dec 25: ER9; Dec 26: ER9; Dec 27: ER9; Dec 28: ER9; Dec 29: ER9; Dec 30: ER9; Dec 31: ER9; Jan 01: ER9; Jan 02: ER9; Jan 03: ER9; Jan 04: ER9; Jan 05: ER9; Jan 06: ER9; Jan 07: ER9; Jan 08: ER9; Jan 09: ER9
| COLO 2 Cell 2 Commissioning | C1 | #F59CA6 | 0 | 6-Dec-24 | 12-Dec-24 | bar: Dec 06 to Dec 12
|  | C10 | #F59CA6 | 0 | 13-Jan-25 | 24-Jan-25 | Oct 23: C3; Oct 24: C3; Oct 25: C3; Oct 26: C3; Oct 27: C3; Oct 28: C3; Oct 29: C3; Oct 30: C3; Oct 31: C3; Nov 01: C3; Nov 02: C3; Nov 03: C3; Nov 04: C3; Nov 05: C3; Nov 06: C3; Nov 07: C3; Dec 02: C6; Dec 03: C6; Dec 04: C6; Dec 05: C7; Dec 06: C7; Dec 07: C7; Dec 08: C7; Dec 09: C7; Dec 10: C7; Dec 11: C7; Dec 27: C11; Dec 28: C11; Dec 29: C11; Dec 30: C11; Dec 31: C11; Jan 01: C11; Jan 02: C11; Jan 03: C11; Jan 06: C15; Jan 07: C17; Jan 08: C16; Jan 13: C10; Jan 14: C10; Jan 15: C10; Jan 16: C10; Jan 17: C10; Jan 18: C10; Jan 19: C10; Jan 20: C10; Jan 21: C10; Jan 22: C10; Jan 23: C10; Jan 24: C10; Feb 04: C12; Feb 05: C12; Feb 06: C12; Feb 07: C12; Feb 08: C12; Feb 09: C12; Feb 10: C12; Feb 25: C20; Feb 26: C20; Feb 27: C20; Feb 28: C20; Mar 01: C20; Mar 02: C20; Mar 03: C20; Mar 04: C21; Mar 05: C21; Mar 06: C21; Mar 07: C21; Mar 08: C21; Mar 09: C21; Mar 10: C21
|  | C11 | #F59CA6 | 0 | 27-Dec-24 | 3-Jan-25 | Jan 02: C13; Jan 03: C14; Jan 06: C19; Jan 07: C18; Jan 21: C2; Jan 22: C2; Jan 23: C2; Jan 24: C2; Jan 25: C2; Jan 26: C2; Jan 27: C2; Jan 28: C2; Jan 29: C2; Jan 30: C2; Jan 31: C2; Feb 01: C2; Feb 02: C2; Feb 03: C2; Feb 04: C2; Feb 05: C2; Feb 06: C2; Feb 07: C2; Feb 08: C2; Feb 09: C2; Feb 10: C2
|  | C12 | #F59CA6 | 0 | 4-Feb-25 | 10-Feb-25 | bar: Dec 27 to Jan 03; Jan 06 to Jan 10
|  | C13 | #F59CA6 | 0 | 2-Jan-25 | 2-Jan-25 | bar: Jan 06 to Jan 17
|  | C14 | #F59CA6 | 0 | 3-Jan-25 | 3-Jan-25
|  | C15 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C16 | #F59CA6 | 0 | 8-Jan-25 | 8-Jan-25
|  | C17 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C18 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C19 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C2 | #F59CA6 | 0 | 21-Jan-25 | 10-Feb-25
|  | C20 | #F59CA6 | 0 | 25-Feb-25 | 3-Mar-25
|  | C21 | #F59CA6 | 0 | 4-Mar-25 | 10-Mar-25
|  | C3 | #F59CA6 | 0 | 23-Oct-24 | 7-Nov-24
|  | C4 | #F59CA6 | 0 | 6-Jan-25 | 10-Jan-25
|  | C5 | #F59CA6 | 0 | 6-Jan-25 | 17-Jan-25
|  | C6 | #F59CA6 | 0 | 2-Dec-24 | 4-Dec-24
|  | C7 | #F59CA6 | 0 | 5-Dec-24 | 11-Dec-24
|  | C8 | #F59CA6 | 0 | 27-Dec-24 | 3-Jan-25
|  | C9 | #F59CA6 | 0 | 12-Dec-24 | 26-Dec-24 | bar: Dec 12 to Dec 26
| COLO 2 Cell 2 Data Hall | DH10 | #C5E5A6 | 0 | 10-Jan-25 | 30-Jan-25 | Jan 10: DH10; Jan 11: DH10; Jan 12: DH10; Jan 13: DH10; Jan 14: DH10; Jan 15: DH10; Jan 16: DH10; Jan 17: DH10; Jan 18: DH10; Jan 19: DH10; Jan 20: DH10; Jan 21: DH10; Jan 22: DH10; Jan 23: DH10; Jan 24: DH10; Jan 25: DH10; Jan 26: DH10; Jan 27: DH10; Jan 28: DH10; Jan 29: DH10; Jan 30: DH10
|  | DH11 | #C5E5A6 | 0 | 3-Jan-25 | 9-Jan-25 | Oct 30: DH4; Oct 31: DH4; Nov 01: DH4; Nov 02: DH4; Nov 03: DH4; Nov 04: DH4; Nov 05: DH4; Nov 06: DH3; Nov 07: DH3; Nov 08: DH3; Nov 09: DH3; Nov 10: DH3; Nov 11: DH3; Nov 12: DH3; Nov 13: DH3; Nov 14: DH3; Nov 15: DH3; Nov 16: DH3; Nov 17: DH3; Nov 18: DH3; Nov 19: DH3; Nov 20: DH2; Nov 21: DH2; Nov 22: DH2; Dec 04: DH6; Dec 05: DH6; Dec 06: DH6; Dec 07: DH6; Dec 08: DH6; Dec 09: DH6; Dec 10: DH6; Dec 11: DH6; Dec 12: DH6; Dec 13: DH6; Dec 14: DH6; Dec 15: DH6; Dec 16: DH6; Dec 17: DH6; Jan 03: DH11; Jan 04: DH11; Jan 05: DH11; Jan 06: DH11; Jan 07: DH11; Jan 08: DH11; Jan 09: DH11; Jan 28: DH12; Jan 29: DH12; Jan 30: DH12; Jan 31: DH12; Feb 01: DH12; Feb 02: DH12; Feb 03: DH12
|  | DH12 | #C5E5A6 | 0 | 28-Jan-25 | 3-Feb-25 | Oct 21: DH5; Oct 22: DH5; Oct 23: DH5; Oct 24: DH5; Oct 25: DH5; Oct 26: DH5; Oct 27: DH5; Oct 28: DH5; Oct 29: DH5; Oct 30: DH5; Oct 31: DH5; Nov 01: DH5; Dec 06: DH7; Dec 07: DH7; Dec 08: DH7; Dec 09: DH7; Dec 10: DH7; Dec 11: DH7; Dec 12: DH7
|  | DH2 | #C5E5A6 | 0 | 20-Nov-24 | 22-Nov-24 | Dec 11: DH8; Dec 12: DH8; Dec 13: DH8; Dec 14: DH8; Dec 15: DH8; Dec 16: DH8; Dec 17: DH8
|  | DH3 | #C5E5A6 | 0 | 6-Nov-24 | 19-Nov-24
|  | DH4 | #C5E5A6 | 0 | 30-Oct-24 | 5-Nov-24
|  | DH5 | #C5E5A6 | 0 | 21-Oct-24 | 1-Nov-24
|  | DH6 | #C5E5A6 | 0 | 4-Dec-24 | 17-Dec-24
|  | DH7 | #C5E5A6 | 0 | 6-Dec-24 | 12-Dec-24
|  | DH8 | #C5E5A6 | 0 | 11-Dec-24 | 17-Dec-24
|  | DH9 | #C5E5A6 | 0 | 10-Dec-24 | 16-Dec-24 | Dec 10: DH9; Dec 11: DH9; Dec 12: DH9; Dec 13: DH9; Dec 14: DH9; Dec 15: DH9; Dec 16: DH9
| COLO 2 Cell 2 Electrical Room | ER1 | #FFC000 | 0 | 11-Mar-25 | 17-Mar-25 | Mar 11: ER1; Mar 12: ER1; Mar 13: ER1; Mar 14: ER1; Mar 15: ER1; Mar 16: ER1; Mar 17: ER1
|  | ER10 | #FFC000 | 0 | 15-Apr-25 | 21-Apr-25 | Mar 11: ER5; Mar 12: ER5; Mar 13: ER5; Mar 14: ER5; Mar 15: ER5; Mar 16: ER5; Mar 17: ER5; Mar 18: ER3; Mar 19: ER3; Mar 20: ER3; Mar 21: ER3; Mar 22: ER3; Mar 23: ER3; Mar 24: ER3; Mar 25: ER2; Mar 26: ER2; Mar 27: ER2; Mar 28: ER2; Mar 29: ER2; Mar 30: ER2; Mar 31: ER2; Apr 01: ER7; Apr 02: ER7; Apr 03: ER7; Apr 04: ER7; Apr 05: ER7; Apr 06: ER7; Apr 07: ER7; Apr 08: ER12; Apr 09: ER12; Apr 10: ER12; Apr 11: ER12; Apr 12: ER12; Apr 13: ER12; Apr 14: ER12; Apr 15: ER10; Apr 16: ER10; Apr 17: ER10; Apr 18: ER10; Apr 19: ER10; Apr 20: ER10; Apr 21: ER10
|  | ER11 | #FFC000 | 0 | 15-Apr-25 | 21-Apr-25 | Mar 18: ER4; Mar 19: ER4; Mar 20: ER4; Mar 21: ER4; Mar 22: ER4; Mar 23: ER4; Mar 24: ER4; Mar 25: ER6; Mar 26: ER6; Mar 27: ER6; Mar 28: ER6; Mar 29: ER6; Mar 30: ER6; Mar 31: ER6; Apr 08: ER8; Apr 09: ER8; Apr 10: ER8; Apr 11: ER8; Apr 12: ER8; Apr 13: ER8; Apr 14: ER8; Apr 15: ER11; Apr 16: ER11; Apr 17: ER11; Apr 18: ER11; Apr 19: ER11; Apr 20: ER11; Apr 21: ER11
|  | ER12 | #FFC000 | 0 | 8-Apr-25 | 14-Apr-25
|  | ER2 | #FFC000 | 0 | 25-Mar-25 | 31-Mar-25
|  | ER3 | #FFC000 | 0 | 18-Mar-25 | 24-Mar-25
|  | ER4 | #FFC000 | 0 | 18-Mar-25 | 24-Mar-25
|  | ER5 | #FFC000 | 0 | 11-Mar-25 | 17-Mar-25
|  | ER6 | #FFC000 | 0 | 25-Mar-25 | 31-Mar-25
|  | ER7 | #FFC000 | 0 | 1-Apr-25 | 7-Apr-25
|  | ER8 | #FFC000 | 0 | 8-Apr-25 | 14-Apr-25
|  | ER9 | #FFC000 | 0 | 22-Apr-25 | 28-Apr-25 | Apr 22: ER9; Apr 23: ER9; Apr 24: ER9; Apr 25: ER9; Apr 26: ER9; Apr 27: ER9; Apr 28: ER9
| COLO 2 Cell 2 Mech Gallery | MG1 | #96CEFF | 0 | 14-Oct-24 | 18-Oct-24 | Oct 14: MG1; Oct 15: MG1; Oct 16: MG1; Oct 17: MG1; Oct 18: MG1
|  | MG10 | #96CEFF | 0 | 30-Dec-24 | 10-Jan-25 | Oct 16: MG2; Oct 17: MG2; Oct 18: MG2; Oct 19: MG2; Oct 20: MG2; Oct 21: MG2; Oct 22: MG2; Oct 30: MG3; Oct 31: MG3; Nov 01: MG3; Nov 02: MG3; Nov 03: MG3; Nov 04: MG3; Nov 05: MG3; Nov 06: MG3; Nov 07: MG3; Nov 08: MG3; Nov 09: MG3; Nov 10: MG3; Nov 11: MG3; Nov 12: MG3; Nov 13: MG4; Nov 14: MG4; Nov 15: MG5; Nov 16: MG5; Nov 17: MG5; Nov 18: MG5; Nov 19: MG5; Nov 20: MG5; Nov 21: MG5; Nov 22: MG5; Nov 23: MG5; Nov 24: MG5; Nov 25: MG5; Nov 26: MG5; Nov 27: MG5; Nov 28: MG5; Nov 29: MG5; Dec 02: MG12; Dec 03: MG12; Dec 04: MG12; Dec 05: MG12; Dec 06: MG12; Dec 07: MG12; Dec 08: MG12; Dec 09: MG12; Dec 10: MG12; Dec 11: MG12; Dec 12: MG12; Dec 13: MG12; Dec 14: MG12; Dec 15: MG12; Dec 16: MG12; Dec 17: MG12; Dec 18: MG12; Dec 19: MG12; Dec 20: MG12; Dec 30: MG10; Dec 31: MG10; Jan 01: MG10; Jan 02: MG10; Jan 03: MG10; Jan 04: MG10; Jan 05: MG10; Jan 06: MG10; Jan 07: MG10; Jan 08: MG10; Jan 09: MG10; Jan 10: MG10
|  | MG11 | #96CEFF | 0 | 3-Jan-25 | 10-Jan-25 | Dec 02: MG7; Dec 09: MG6; Dec 10: MG6; Dec 11: MG6; Jan 03: MG11; Jan 04: MG11; Jan 05: MG11; Jan 06: MG11; Jan 07: MG11; Jan 08: MG11; Jan 09: MG11; Jan 10: MG11
|  | MG12 | #96CEFF | 0 | 2-Dec-24 | 20-Dec-24 | Dec 11: MG8; Dec 12: MG8; Dec 13: MG8; Dec 14: MG8; Dec 15: MG8; Dec 16: MG8; Dec 17: MG8; Dec 18: MG8; Dec 19: MG8; Dec 20: MG8; Dec 21: MG8; Dec 22: MG8; Dec 23: MG8; Dec 24: MG8; Dec 25: MG8; Dec 26: MG8
|  | MG2 | #96CEFF | 0 | 16-Oct-24 | 22-Oct-24
|  | MG3 | #96CEFF | 0 | 30-Oct-24 | 12-Nov-24
|  | MG4 | #96CEFF | 0 | 13-Nov-24 | 14-Nov-24
|  | MG5 | #96CEFF | 0 | 15-Nov-24 | 29-Nov-24
|  | MG6 | #96CEFF | 0 | 9-Dec-24 | 11-Dec-24
|  | MG7 | #96CEFF | 0 | 2-Dec-24 | 2-Dec-24
|  | MG8 | #96CEFF | 0 | 11-Dec-24 | 26-Dec-24
|  | MG9 | #96CEFF | 0 | 26-Dec-24 | 30-Dec-24 | Dec 26: MG9; Dec 27: MG9; Dec 28: MG9; Dec 29: MG9; Dec 30: MG9

## Test 2 Dani - WBS 4
[7 empty] | 2024 | 2024 | [84 empty] | 2025
[7 empty] | Oct | Oct | [23 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun
[7 empty] | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06
phase | location | activity_code | color | activity_ins | start | finish | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Fitout | COLO 2 Cell 1 Commissioning | C1 | #F59CA6 | 0 | 2-Jan-25 | 2-Jan-25 | bar: Jan 02
|  | C10 | #F59CA6 | 0 | 11-Mar-25 | 17-Mar-25 | Jan 03: C2; Jan 06: C3; Jan 07: C5; Jan 08: C4; Feb 25: C8; Feb 26: C8; Feb 27: C8; Feb 28: C8; Mar 01: C8; Mar 02: C8; Mar 03: C8; Mar 11: C10; Mar 12: C10; Mar 13: C10; Mar 14: C10; Mar 15: C10; Mar 16: C10; Mar 17: C10; Mar 18: C12; Mar 19: C12; Mar 20: C12; Mar 21: C12; Mar 22: C12; Mar 23: C12; Mar 24: C12; Mar 25: C11; Mar 26: C11; Mar 27: C11; Mar 28: C11; Mar 29: C11; Mar 30: C11; Mar 31: C11; Apr 01: C16; Apr 02: C16; Apr 03: C16; Apr 04: C16; Apr 05: C16; Apr 06: C16; Apr 07: C16; Apr 08: C17; Apr 09: C17; Apr 10: C17; Apr 11: C17; Apr 12: C17; Apr 13: C17; Apr 14: C17; Apr 15: C19; Apr 16: C19; Apr 17: C19; Apr 18: C19; Apr 19: C19; Apr 20: C19; Apr 21: C19; Apr 22: C18; Apr 23: C18; Apr 24: C18; Apr 25: C18; Apr 26: C18; Apr 27: C18; Apr 28: C18
|  | C11 | #F59CA6 | 0 | 25-Mar-25 | 31-Mar-25 | Jan 06: C7; Jan 07: C6; Mar 11: C14; Mar 12: C14; Mar 13: C14; Mar 14: C14; Mar 15: C14; Mar 16: C14; Mar 17: C14; Mar 18: C13; Mar 19: C13; Mar 20: C13; Mar 21: C13; Mar 22: C13; Mar 23: C13; Mar 24: C13; Mar 25: C15; Mar 26: C15; Mar 27: C15; Mar 28: C15; Mar 29: C15; Mar 30: C15; Mar 31: C15; Apr 08: C21; Apr 09: C21; Apr 10: C21; Apr 11: C21; Apr 12: C21; Apr 13: C21; Apr 14: C21; Apr 15: C20; Apr 16: C20; Apr 17: C20; Apr 18: C20; Apr 19: C20; Apr 20: C20; Apr 21: C20
|  | C12 | #F59CA6 | 0 | 18-Mar-25 | 24-Mar-25
|  | C13 | #F59CA6 | 0 | 18-Mar-25 | 24-Mar-25
|  | C14 | #F59CA6 | 0 | 11-Mar-25 | 17-Mar-25
|  | C15 | #F59CA6 | 0 | 25-Mar-25 | 31-Mar-25
|  | C16 | #F59CA6 | 0 | 1-Apr-25 | 7-Apr-25
|  | C17 | #F59CA6 | 0 | 8-Apr-25 | 14-Apr-25
|  | C18 | #F59CA6 | 0 | 22-Apr-25 | 28-Apr-25
|  | C19 | #F59CA6 | 0 | 15-Apr-25 | 21-Apr-25
|  | C2 | #F59CA6 | 0 | 3-Jan-25 | 3-Jan-25
|  | C20 | #F59CA6 | 0 | 15-Apr-25 | 21-Apr-25
|  | C21 | #F59CA6 | 0 | 8-Apr-25 | 14-Apr-25
|  | C3 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C4 | #F59CA6 | 0 | 8-Jan-25 | 8-Jan-25
|  | C5 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C6 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C7 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C8 | #F59CA6 | 0 | 25-Feb-25 | 3-Mar-25
|  | C9 | #F59CA6 | 0 | 4-Mar-25 | 10-Mar-25 | bar: Mar 04 to Mar 10
| COLO 2 Cell 1 Data Hall | DH10 | #C5E5A6 | 0 | 27-Dec-24 | 10-Jan-25 | Dec 27: DH10; Dec 28: DH10; Dec 29: DH10; Dec 30: DH10; Dec 31: DH10; Jan 01: DH10; Jan 02: DH10; Jan 03: DH10; Jan 04: DH10; Jan 05: DH10; Jan 06: DH10; Jan 07: DH10; Jan 08: DH10; Jan 09: DH10; Jan 10: DH10
|  | DH11 | #C5E5A6 | 0 | 12-Dec-24 | 18-Dec-24 | Oct 07: DH3; Oct 08: DH3; Oct 09: DH3; Oct 10: DH3; Oct 11: DH3; Oct 12: DH3; Oct 13: DH3; Oct 14: DH3; Oct 15: DH3; Oct 16: DH3; Oct 17: DH3; Oct 18: DH3; Oct 19: DH3; Oct 20: DH3; Oct 21: DH3; Oct 22: DH3; Nov 15: DH6; Nov 16: DH6; Nov 17: DH6; Nov 18: DH6; Nov 19: DH6; Nov 20: DH7; Nov 21: DH7; Nov 22: DH7; Nov 23: DH7; Nov 24: DH7; Nov 25: DH7; Nov 26: DH7; Dec 12: DH11; Dec 13: DH11; Dec 14: DH11; Dec 15: DH11; Dec 16: DH11; Dec 17: DH11; Dec 18: DH11; Dec 19: DH2; Dec 20: DH2; Dec 21: DH2; Dec 22: DH2; Dec 23: DH2; Dec 24: DH2; Dec 25: DH2; Dec 26: DH2; Dec 27: DH2; Dec 28: DH2; Dec 29: DH2; Dec 30: DH2; Dec 31: DH2; Jan 01: DH2; Jan 02: DH2; Jan 03: DH2; Jan 14: DH12; Jan 15: DH12; Jan 16: DH12; Jan 17: DH12; Jan 18: DH12; Jan 19: DH12; Jan 20: DH12
|  | DH12 | #C5E5A6 | 0 | 14-Jan-25 | 20-Jan-25 | Dec 12: DH8; Dec 13: DH8; Dec 14: DH8; Dec 15: DH8; Dec 16: DH8; Dec 17: DH8; Dec 18: DH8; Dec 19: DH4; Dec 20: DH4; Dec 21: DH4; Dec 22: DH4; Dec 23: DH4; Dec 24: DH4; Dec 25: DH4; Dec 26: DH4; Dec 30: DH5; Dec 31: DH5; Jan 01: DH5; Jan 02: DH5; Jan 03: DH5; Jan 04: DH5; Jan 05: DH5; Jan 06: DH5; Jan 07: DH5; Jan 08: DH5; Jan 09: DH5; Jan 10: DH5; Jan 11: DH5; Jan 12: DH5; Jan 13: DH5; Jan 14: DH5; Jan 15: DH5; Jan 16: DH5; Jan 17: DH5; Jan 18: DH5; Jan 19: DH5; Jan 20: DH5
|  | DH2 | #C5E5A6 | 0 | 19-Dec-24 | 3-Jan-25
|  | DH3 | #C5E5A6 | 0 | 7-Oct-24 | 22-Oct-24
|  | DH4 | #C5E5A6 | 0 | 19-Dec-24 | 26-Dec-24
|  | DH5 | #C5E5A6 | 0 | 30-Dec-24 | 20-Jan-25
|  | DH6 | #C5E5A6 | 0 | 15-Nov-24 | 19-Nov-24
|  | DH7 | #C5E5A6 | 0 | 20-Nov-24 | 26-Nov-24
|  | DH8 | #C5E5A6 | 0 | 12-Dec-24 | 18-Dec-24
|  | DH9 | #C5E5A6 | 0 | 27-Nov-24 | 11-Dec-24 | Nov 27: DH9; Nov 28: DH9; Nov 29: DH9; Nov 30: DH9; Dec 01: DH9; Dec 02: DH9; Dec 03: DH9; Dec 04: DH9; Dec 05: DH9; Dec 06: DH9; Dec 07: DH9; Dec 08: DH9; Dec 09: DH9; Dec 10: DH9; Dec 11: DH9
| COLO 2 Cell 1 Mech Gallery | MG1 | #96CEFF | 0 | 7-Oct-24 | 11-Oct-24 | Oct 07: MG1; Oct 08: MG1; Oct 09: MG1; Oct 10: MG1; Oct 11: MG1
|  | MG10 | #96CEFF | 0 | 13-Dec-24 | 26-Dec-24 | Oct 09: MG2; Oct 10: MG2; Oct 11: MG2; Oct 12: MG2; Oct 13: MG2; Oct 14: MG2; Oct 15: MG2; Oct 16: MG3; Oct 17: MG3; Oct 18: MG3; Oct 19: MG3; Oct 20: MG3; Oct 21: MG3; Oct 22: MG3; Oct 23: MG3; Oct 24: MG3; Oct 25: MG3; Oct 26: MG3; Oct 27: MG3; Oct 28: MG3; Oct 29: MG3; Oct 30: MG4; Oct 31: MG4; Nov 01: MG5; Nov 02: MG5; Nov 03: MG5; Nov 04: MG5; Nov 05: MG5; Nov 06: MG5; Nov 07: MG5; Nov 08: MG5; Nov 09: MG5; Nov 10: MG5; Nov 11: MG5; Nov 12: MG5; Nov 13: MG5; Nov 14: MG5; Nov 15: MG12; Nov 16: MG12; Nov 17: MG12; Nov 18: MG12; Nov 19: MG12; Nov 20: MG12; Nov 21: MG12; Nov 22: MG12; Nov 23: MG12; Nov 24: MG12; Nov 25: MG12; Nov 26: MG12; Nov 27: MG12; Nov 28: MG12; Nov 29: MG12; Nov 30: MG12; Dec 01: MG12; Dec 02: MG12; Dec 03: MG12; Dec 04: MG12; Dec 05: MG12; Dec 06: MG12; Dec 13: MG10; Dec 14: MG10; Dec 15: MG10; Dec 16: MG10; Dec 17: MG10; Dec 18: MG10; Dec 19: MG10; Dec 20: MG10; Dec 21: MG10; Dec 22: MG10; Dec 23: MG10; Dec 24: MG10; Dec 25: MG10; Dec 26: MG10
|  | MG11 | #96CEFF | 0 | 18-Dec-24 | 26-Dec-24 | Nov 15: MG7; Nov 22: MG6; Nov 23: MG6; Nov 24: MG6; Nov 25: MG6; Nov 26: MG6; Dec 18: MG11; Dec 19: MG11; Dec 20: MG11; Dec 21: MG11; Dec 22: MG11; Dec 23: MG11; Dec 24: MG11; Dec 25: MG11; Dec 26: MG11
|  | MG12 | #96CEFF | 0 | 15-Nov-24 | 6-Dec-24 | Nov 26: MG8; Nov 27: MG8; Nov 28: MG8; Nov 29: MG8; Nov 30: MG8; Dec 01: MG8; Dec 02: MG8; Dec 03: MG8; Dec 04: MG8; Dec 05: MG8; Dec 06: MG8; Dec 07: MG8; Dec 08: MG8; Dec 09: MG8; Dec 10: MG8; Dec 11: MG8
|  | MG2 | #96CEFF | 0 | 9-Oct-24 | 15-Oct-24
|  | MG3 | #96CEFF | 0 | 16-Oct-24 | 29-Oct-24
|  | MG4 | #96CEFF | 0 | 30-Oct-24 | 31-Oct-24
|  | MG5 | #96CEFF | 0 | 1-Nov-24 | 14-Nov-24
|  | MG6 | #96CEFF | 0 | 22-Nov-24 | 26-Nov-24
|  | MG7 | #96CEFF | 0 | 15-Nov-24 | 15-Nov-24
|  | MG8 | #96CEFF | 0 | 26-Nov-24 | 11-Dec-24
|  | MG9 | #96CEFF | 0 | 11-Dec-24 | 13-Dec-24 | Dec 11: MG9; Dec 12: MG9; Dec 13: MG9
| COLO 2 Cell 1 Cx L4 | L4 | #FFFFFF | 0 | 1-May-25 | 4-Jun-25 | bar: May 01 to Jun 04
| COLO 2 Cell 1 Cx L5 | L5 | #FFFFFF | 0 | 5-Jun-25 | 6-Jun-25 | bar: Jun 05 to Jun 06
| COLO 2 Cell 1 Electrical Room | ER1 | #FFC000 | 0 | 7-Oct-24 | 18-Oct-24 | Oct 07: ER1; Oct 08: ER1; Oct 09: ER1; Oct 10: ER1; Oct 11: ER1; Oct 12: ER1; Oct 13: ER1; Oct 14: ER1; Oct 15: ER1; Oct 16: ER1; Oct 17: ER1; Oct 18: ER1
|  | ER10 | #FFC000 | 0 | 3-Jan-25 | 9-Jan-25 | Oct 16: ER3; Oct 17: ER3; Oct 18: ER3; Oct 19: ER3; Oct 20: ER3; Oct 21: ER3; Oct 22: ER3; Oct 23: ER2; Oct 24: ER2; Oct 25: ER2; Oct 26: ER2; Oct 27: ER2; Oct 28: ER2; Oct 29: ER2; Oct 30: ER2; Oct 31: ER2; Nov 01: ER2; Nov 02: ER2; Nov 03: ER2; Nov 04: ER2; Nov 05: ER2; Nov 06: ER4; Nov 07: ER4; Nov 08: ER4; Nov 29: ER12; Nov 30: ER12; Dec 01: ER12; Dec 02: ER12; Dec 03: ER12; Dec 04: ER12; Dec 05: ER12; Jan 03: ER10; Jan 04: ER10; Jan 05: ER10; Jan 06: ER10; Jan 07: ER10; Jan 08: ER10; Jan 09: ER10; Jan 10: ER11; Jan 11: ER11; Jan 12: ER11; Jan 13: ER11; Jan 14: ER11; Jan 15: ER11; Jan 16: ER11
|  | ER11 | #FFC000 | 0 | 10-Jan-25 | 16-Jan-25 | Nov 19: ER5; Nov 20: ER5; Nov 21: ER5; Nov 22: ER5; Nov 23: ER5; Nov 24: ER5; Nov 25: ER5; Nov 26: ER5; Nov 27: ER5; Nov 28: ER5; Nov 29: ER5; Nov 30: ER5; Dec 01: ER5; Dec 02: ER5; Dec 03: ER5; Dec 04: ER7; Dec 05: ER7; Dec 06: ER7; Dec 07: ER7; Dec 08: ER7; Dec 09: ER7; Dec 10: ER7
|  | ER12 | #FFC000 | 0 | 29-Nov-24 | 5-Dec-24 | Nov 29: ER6; Nov 30: ER6; Dec 01: ER6; Dec 02: ER6; Dec 03: ER6; Dec 04: ER6; Dec 05: ER6
|  | ER2 | #FFC000 | 0 | 23-Oct-24 | 5-Nov-24 | Dec 03: ER8; Dec 04: ER8; Dec 05: ER8; Dec 06: ER8; Dec 07: ER8; Dec 08: ER8; Dec 09: ER8
|  | ER3 | #FFC000 | 0 | 16-Oct-24 | 22-Oct-24
|  | ER4 | #FFC000 | 0 | 6-Nov-24 | 8-Nov-24
|  | ER5 | #FFC000 | 0 | 19-Nov-24 | 3-Dec-24
|  | ER6 | #FFC000 | 0 | 29-Nov-24 | 5-Dec-24
|  | ER7 | #FFC000 | 0 | 4-Dec-24 | 10-Dec-24
|  | ER8 | #FFC000 | 0 | 3-Dec-24 | 9-Dec-24
|  | ER9 | #FFC000 | 0 | 18-Dec-24 | 9-Jan-25 | Dec 18: ER9; Dec 19: ER9; Dec 20: ER9; Dec 21: ER9; Dec 22: ER9; Dec 23: ER9; Dec 24: ER9; Dec 25: ER9; Dec 26: ER9; Dec 27: ER9; Dec 28: ER9; Dec 29: ER9; Dec 30: ER9; Dec 31: ER9; Jan 01: ER9; Jan 02: ER9; Jan 03: ER9; Jan 04: ER9; Jan 05: ER9; Jan 06: ER9; Jan 07: ER9; Jan 08: ER9; Jan 09: ER9
| COLO 2 Cell 2 Commissioning | C1 | #F59CA6 | 0 | 6-Dec-24 | 12-Dec-24 | bar: Dec 06 to Dec 12
|  | C10 | #F59CA6 | 0 | 13-Jan-25 | 24-Jan-25 | Oct 23: C3; Oct 24: C3; Oct 25: C3; Oct 26: C3; Oct 27: C3; Oct 28: C3; Oct 29: C3; Oct 30: C3; Oct 31: C3; Nov 01: C3; Nov 02: C3; Nov 03: C3; Nov 04: C3; Nov 05: C3; Nov 06: C3; Nov 07: C3; Dec 02: C6; Dec 03: C6; Dec 04: C6; Dec 05: C7; Dec 06: C7; Dec 07: C7; Dec 08: C7; Dec 09: C7; Dec 10: C7; Dec 11: C7; Dec 27: C11; Dec 28: C11; Dec 29: C11; Dec 30: C11; Dec 31: C11; Jan 01: C11; Jan 02: C11; Jan 03: C11; Jan 06: C15; Jan 07: C17; Jan 08: C16; Jan 13: C10; Jan 14: C10; Jan 15: C10; Jan 16: C10; Jan 17: C10; Jan 18: C10; Jan 19: C10; Jan 20: C10; Jan 21: C10; Jan 22: C10; Jan 23: C10; Jan 24: C10; Feb 04: C12; Feb 05: C12; Feb 06: C12; Feb 07: C12; Feb 08: C12; Feb 09: C12; Feb 10: C12; Feb 25: C20; Feb 26: C20; Feb 27: C20; Feb 28: C20; Mar 01: C20; Mar 02: C20; Mar 03: C20; Mar 04: C21; Mar 05: C21; Mar 06: C21; Mar 07: C21; Mar 08: C21; Mar 09: C21; Mar 10: C21
|  | C11 | #F59CA6 | 0 | 27-Dec-24 | 3-Jan-25 | Jan 02: C13; Jan 03: C14; Jan 06: C19; Jan 07: C18; Jan 21: C2; Jan 22: C2; Jan 23: C2; Jan 24: C2; Jan 25: C2; Jan 26: C2; Jan 27: C2; Jan 28: C2; Jan 29: C2; Jan 30: C2; Jan 31: C2; Feb 01: C2; Feb 02: C2; Feb 03: C2; Feb 04: C2; Feb 05: C2; Feb 06: C2; Feb 07: C2; Feb 08: C2; Feb 09: C2; Feb 10: C2
|  | C12 | #F59CA6 | 0 | 4-Feb-25 | 10-Feb-25 | bar: Dec 27 to Jan 03; Jan 06 to Jan 10
|  | C13 | #F59CA6 | 0 | 2-Jan-25 | 2-Jan-25 | bar: Jan 06 to Jan 17
|  | C14 | #F59CA6 | 0 | 3-Jan-25 | 3-Jan-25
|  | C15 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C16 | #F59CA6 | 0 | 8-Jan-25 | 8-Jan-25
|  | C17 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C18 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C19 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C2 | #F59CA6 | 0 | 21-Jan-25 | 10-Feb-25
|  | C20 | #F59CA6 | 0 | 25-Feb-25 | 3-Mar-25
|  | C21 | #F59CA6 | 0 | 4-Mar-25 | 10-Mar-25
|  | C3 | #F59CA6 | 0 | 23-Oct-24 | 7-Nov-24
|  | C4 | #F59CA6 | 0 | 6-Jan-25 | 10-Jan-25
|  | C5 | #F59CA6 | 0 | 6-Jan-25 | 17-Jan-25
|  | C6 | #F59CA6 | 0 | 2-Dec-24 | 4-Dec-24
|  | C7 | #F59CA6 | 0 | 5-Dec-24 | 11-Dec-24
|  | C8 | #F59CA6 | 0 | 27-Dec-24 | 3-Jan-25
|  | C9 | #F59CA6 | 0 | 12-Dec-24 | 26-Dec-24 | bar: Dec 12 to Dec 26
| COLO 2 Cell 2 Data Hall | DH10 | #C5E5A6 | 0 | 10-Jan-25 | 30-Jan-25 | Jan 10: DH10; Jan 11: DH10; Jan 12: DH10; Jan 13: DH10; Jan 14: DH10; Jan 15: DH10; Jan 16: DH10; Jan 17: DH10; Jan 18: DH10; Jan 19: DH10; Jan 20: DH10; Jan 21: DH10; Jan 22: DH10; Jan 23: DH10; Jan 24: DH10; Jan 25: DH10; Jan 26: DH10; Jan 27: DH10; Jan 28: DH10; Jan 29: DH10; Jan 30: DH10
|  | DH11 | #C5E5A6 | 0 | 3-Jan-25 | 9-Jan-25 | Oct 30: DH4; Oct 31: DH4; Nov 01: DH4; Nov 02: DH4; Nov 03: DH4; Nov 04: DH4; Nov 05: DH4; Nov 06: DH3; Nov 07: DH3; Nov 08: DH3; Nov 09: DH3; Nov 10: DH3; Nov 11: DH3; Nov 12: DH3; Nov 13: DH3; Nov 14: DH3; Nov 15: DH3; Nov 16: DH3; Nov 17: DH3; Nov 18: DH3; Nov 19: DH3; Nov 20: DH2; Nov 21: DH2; Nov 22: DH2; Dec 04: DH6; Dec 05: DH6; Dec 06: DH6; Dec 07: DH6; Dec 08: DH6; Dec 09: DH6; Dec 10: DH6; Dec 11: DH6; Dec 12: DH6; Dec 13: DH6; Dec 14: DH6; Dec 15: DH6; Dec 16: DH6; Dec 17: DH6; Jan 03: DH11; Jan 04: DH11; Jan 05: DH11; Jan 06: DH11; Jan 07: DH11; Jan 08: DH11; Jan 09: DH11; Jan 28: DH12; Jan 29: DH12; Jan 30: DH12; Jan 31: DH12; Feb 01: DH12; Feb 02: DH12; Feb 03: DH12
|  | DH12 | #C5E5A6 | 0 | 28-Jan-25 | 3-Feb-25 | Oct 21: DH5; Oct 22: DH5; Oct 23: DH5; Oct 24: DH5; Oct 25: DH5; Oct 26: DH5; Oct 27: DH5; Oct 28: DH5; Oct 29: DH5; Oct 30: DH5; Oct 31: DH5; Nov 01: DH5; Dec 06: DH7; Dec 07: DH7; Dec 08: DH7; Dec 09: DH7; Dec 10: DH7; Dec 11: DH7; Dec 12: DH7
|  | DH2 | #C5E5A6 | 0 | 20-Nov-24 | 22-Nov-24 | Dec 11: DH8; Dec 12: DH8; Dec 13: DH8; Dec 14: DH8; Dec 15: DH8; Dec 16: DH8; Dec 17: DH8
|  | DH3 | #C5E5A6 | 0 | 6-Nov-24 | 19-Nov-24
|  | DH4 | #C5E5A6 | 0 | 30-Oct-24 | 5-Nov-24
|  | DH5 | #C5E5A6 | 0 | 21-Oct-24 | 1-Nov-24
|  | DH6 | #C5E5A6 | 0 | 4-Dec-24 | 17-Dec-24
|  | DH7 | #C5E5A6 | 0 | 6-Dec-24 | 12-Dec-24
|  | DH8 | #C5E5A6 | 0 | 11-Dec-24 | 17-Dec-24
|  | DH9 | #C5E5A6 | 0 | 10-Dec-24 | 16-Dec-24 | Dec 10: DH9; Dec 11: DH9; Dec 12: DH9; Dec 13: DH9; Dec 14: DH9; Dec 15: DH9; Dec 16: DH9
| COLO 2 Cell 2 Electrical Room | ER1 | #FFC000 | 0 | 11-Mar-25 | 17-Mar-25 | Mar 11: ER1; Mar 12: ER1; Mar 13: ER1; Mar 14: ER1; Mar 15: ER1; Mar 16: ER1; Mar 17: ER1
|  | ER10 | #FFC000 | 0 | 15-Apr-25 | 21-Apr-25 | Mar 11: ER5; Mar 12: ER5; Mar 13: ER5; Mar 14: ER5; Mar 15: ER5; Mar 16: ER5; Mar 17: ER5; Mar 18: ER3; Mar 19: ER3; Mar 20: ER3; Mar 21: ER3; Mar 22: ER3; Mar 23: ER3; Mar 24: ER3; Mar 25: ER2; Mar 26: ER2; Mar 27: ER2; Mar 28: ER2; Mar 29: ER2; Mar 30: ER2; Mar 31: ER2; Apr 01: ER7; Apr 02: ER7; Apr 03: ER7; Apr 04: ER7; Apr 05: ER7; Apr 06: ER7; Apr 07: ER7; Apr 08: ER12; Apr 09: ER12; Apr 10: ER12; Apr 11: ER12; Apr 12: ER12; Apr 13: ER12; Apr 14: ER12; Apr 15: ER10; Apr 16: ER10; Apr 17: ER10; Apr 18: ER10; Apr 19: ER10; Apr 20: ER10; Apr 21: ER10
|  | ER11 | #FFC000 | 0 | 15-Apr-25 | 21-Apr-25 | Mar 18: ER4; Mar 19: ER4; Mar 20: ER4; Mar 21: ER4; Mar 22: ER4; Mar 23: ER4; Mar 24: ER4; Mar 25: ER6; Mar 26: ER6; Mar 27: ER6; Mar 28: ER6; Mar 29: ER6; Mar 30: ER6; Mar 31: ER6; Apr 08: ER8; Apr 09: ER8; Apr 10: ER8; Apr 11: ER8; Apr 12: ER8; Apr 13: ER8; Apr 14: ER8; Apr 15: ER11; Apr 16: ER11; Apr 17: ER11; Apr 18: ER11; Apr 19: ER11; Apr 20: ER11; Apr 21: ER11
|  | ER12 | #FFC000 | 0 | 8-Apr-25 | 14-Apr-25
|  | ER2 | #FFC000 | 0 | 25-Mar-25 | 31-Mar-25
|  | ER3 | #FFC000 | 0 | 18-Mar-25 | 24-Mar-25
|  | ER4 | #FFC000 | 0 | 18-Mar-25 | 24-Mar-25
|  | ER5 | #FFC000 | 0 | 11-Mar-25 | 17-Mar-25
|  | ER6 | #FFC000 | 0 | 25-Mar-25 | 31-Mar-25
|  | ER7 | #FFC000 | 0 | 1-Apr-25 | 7-Apr-25
|  | ER8 | #FFC000 | 0 | 8-Apr-25 | 14-Apr-25
|  | ER9 | #FFC000 | 0 | 22-Apr-25 | 28-Apr-25 | Apr 22: ER9; Apr 23: ER9; Apr 24: ER9; Apr 25: ER9; Apr 26: ER9; Apr 27: ER9; Apr 28: ER9
| COLO 2 Cell 2 Mech Gallery | MG1 | #96CEFF | 0 | 14-Oct-24 | 18-Oct-24 | Oct 14: MG1; Oct 15: MG1; Oct 16: MG1; Oct 17: MG1; Oct 18: MG1
|  | MG10 | #96CEFF | 0 | 30-Dec-24 | 10-Jan-25 | Oct 16: MG2; Oct 17: MG2; Oct 18: MG2; Oct 19: MG2; Oct 20: MG2; Oct 21: MG2; Oct 22: MG2; Oct 30: MG3; Oct 31: MG3; Nov 01: MG3; Nov 02: MG3; Nov 03: MG3; Nov 04: MG3; Nov 05: MG3; Nov 06: MG3; Nov 07: MG3; Nov 08: MG3; Nov 09: MG3; Nov 10: MG3; Nov 11: MG3; Nov 12: MG3; Nov 13: MG4; Nov 14: MG4; Nov 15: MG5; Nov 16: MG5; Nov 17: MG5; Nov 18: MG5; Nov 19: MG5; Nov 20: MG5; Nov 21: MG5; Nov 22: MG5; Nov 23: MG5; Nov 24: MG5; Nov 25: MG5; Nov 26: MG5; Nov 27: MG5; Nov 28: MG5; Nov 29: MG5; Dec 02: MG12; Dec 03: MG12; Dec 04: MG12; Dec 05: MG12; Dec 06: MG12; Dec 07: MG12; Dec 08: MG12; Dec 09: MG12; Dec 10: MG12; Dec 11: MG12; Dec 12: MG12; Dec 13: MG12; Dec 14: MG12; Dec 15: MG12; Dec 16: MG12; Dec 17: MG12; Dec 18: MG12; Dec 19: MG12; Dec 20: MG12; Dec 30: MG10; Dec 31: MG10; Jan 01: MG10; Jan 02: MG10; Jan 03: MG10; Jan 04: MG10; Jan 05: MG10; Jan 06: MG10; Jan 07: MG10; Jan 08: MG10; Jan 09: MG10; Jan 10: MG10
|  | MG11 | #96CEFF | 0 | 3-Jan-25 | 10-Jan-25 | Dec 02: MG7; Dec 09: MG6; Dec 10: MG6; Dec 11: MG6; Jan 03: MG11; Jan 04: MG11; Jan 05: MG11; Jan 06: MG11; Jan 07: MG11; Jan 08: MG11; Jan 09: MG11; Jan 10: MG11
|  | MG12 | #96CEFF | 0 | 2-Dec-24 | 20-Dec-24 | Dec 11: MG8; Dec 12: MG8; Dec 13: MG8; Dec 14: MG8; Dec 15: MG8; Dec 16: MG8; Dec 17: MG8; Dec 18: MG8; Dec 19: MG8; Dec 20: MG8; Dec 21: MG8; Dec 22: MG8; Dec 23: MG8; Dec 24: MG8; Dec 25: MG8; Dec 26: MG8
|  | MG2 | #96CEFF | 0 | 16-Oct-24 | 22-Oct-24
|  | MG3 | #96CEFF | 0 | 30-Oct-24 | 12-Nov-24
|  | MG4 | #96CEFF | 0 | 13-Nov-24 | 14-Nov-24
|  | MG5 | #96CEFF | 0 | 15-Nov-24 | 29-Nov-24
|  | MG6 | #96CEFF | 0 | 9-Dec-24 | 11-Dec-24
|  | MG7 | #96CEFF | 0 | 2-Dec-24 | 2-Dec-24
|  | MG8 | #96CEFF | 0 | 11-Dec-24 | 26-Dec-24
|  | MG9 | #96CEFF | 0 | 26-Dec-24 | 30-Dec-24 | Dec 26: MG9; Dec 27: MG9; Dec 28: MG9; Dec 29: MG9; Dec 30: MG9

## Test 2 Dani - WBS 5
[7 empty] | 2024 | 2024 | [84 empty] | 2025
[7 empty] | Oct | Oct | [23 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun
[7 empty] | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06
phase | location | activity_code | color | activity_ins | start | finish | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Fitout | COLO 2 Cell 1 Commissioning | C1 | #F59CA6 | 0 | 2-Jan-25 | 2-Jan-25 | bar: Jan 02
|  | C10 | #F59CA6 | 0 | 11-Mar-25 | 17-Mar-25 | Jan 03: C2; Jan 06: C3; Jan 07: C5; Jan 08: C4; Feb 25: C8; Feb 26: C8; Feb 27: C8; Feb 28: C8; Mar 01: C8; Mar 02: C8; Mar 03: C8; Mar 11: C10; Mar 12: C10; Mar 13: C10; Mar 14: C10; Mar 15: C10; Mar 16: C10; Mar 17: C10; Mar 18: C12; Mar 19: C12; Mar 20: C12; Mar 21: C12; Mar 22: C12; Mar 23: C12; Mar 24: C12; Mar 25: C11; Mar 26: C11; Mar 27: C11; Mar 28: C11; Mar 29: C11; Mar 30: C11; Mar 31: C11; Apr 01: C16; Apr 02: C16; Apr 03: C16; Apr 04: C16; Apr 05: C16; Apr 06: C16; Apr 07: C16; Apr 08: C17; Apr 09: C17; Apr 10: C17; Apr 11: C17; Apr 12: C17; Apr 13: C17; Apr 14: C17; Apr 15: C19; Apr 16: C19; Apr 17: C19; Apr 18: C19; Apr 19: C19; Apr 20: C19; Apr 21: C19; Apr 22: C18; Apr 23: C18; Apr 24: C18; Apr 25: C18; Apr 26: C18; Apr 27: C18; Apr 28: C18
|  | C11 | #F59CA6 | 0 | 25-Mar-25 | 31-Mar-25 | Jan 06: C7; Jan 07: C6; Mar 11: C14; Mar 12: C14; Mar 13: C14; Mar 14: C14; Mar 15: C14; Mar 16: C14; Mar 17: C14; Mar 18: C13; Mar 19: C13; Mar 20: C13; Mar 21: C13; Mar 22: C13; Mar 23: C13; Mar 24: C13; Mar 25: C15; Mar 26: C15; Mar 27: C15; Mar 28: C15; Mar 29: C15; Mar 30: C15; Mar 31: C15; Apr 08: C21; Apr 09: C21; Apr 10: C21; Apr 11: C21; Apr 12: C21; Apr 13: C21; Apr 14: C21; Apr 15: C20; Apr 16: C20; Apr 17: C20; Apr 18: C20; Apr 19: C20; Apr 20: C20; Apr 21: C20
|  | C12 | #F59CA6 | 0 | 18-Mar-25 | 24-Mar-25
|  | C13 | #F59CA6 | 0 | 18-Mar-25 | 24-Mar-25
|  | C14 | #F59CA6 | 0 | 11-Mar-25 | 17-Mar-25
|  | C15 | #F59CA6 | 0 | 25-Mar-25 | 31-Mar-25
|  | C16 | #F59CA6 | 0 | 1-Apr-25 | 7-Apr-25
|  | C17 | #F59CA6 | 0 | 8-Apr-25 | 14-Apr-25
|  | C18 | #F59CA6 | 0 | 22-Apr-25 | 28-Apr-25
|  | C19 | #F59CA6 | 0 | 15-Apr-25 | 21-Apr-25
|  | C2 | #F59CA6 | 0 | 3-Jan-25 | 3-Jan-25
|  | C20 | #F59CA6 | 0 | 15-Apr-25 | 21-Apr-25
|  | C21 | #F59CA6 | 0 | 8-Apr-25 | 14-Apr-25
|  | C3 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C4 | #F59CA6 | 0 | 8-Jan-25 | 8-Jan-25
|  | C5 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C6 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C7 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C8 | #F59CA6 | 0 | 25-Feb-25 | 3-Mar-25
|  | C9 | #F59CA6 | 0 | 4-Mar-25 | 10-Mar-25 | bar: Mar 04 to Mar 10
| COLO 2 Cell 1 Data Hall | DH10 | #C5E5A6 | 0 | 27-Dec-24 | 10-Jan-25 | Dec 27: DH10; Dec 28: DH10; Dec 29: DH10; Dec 30: DH10; Dec 31: DH10; Jan 01: DH10; Jan 02: DH10; Jan 03: DH10; Jan 04: DH10; Jan 05: DH10; Jan 06: DH10; Jan 07: DH10; Jan 08: DH10; Jan 09: DH10; Jan 10: DH10
|  | DH11 | #C5E5A6 | 0 | 12-Dec-24 | 18-Dec-24 | Oct 07: DH3; Oct 08: DH3; Oct 09: DH3; Oct 10: DH3; Oct 11: DH3; Oct 12: DH3; Oct 13: DH3; Oct 14: DH3; Oct 15: DH3; Oct 16: DH3; Oct 17: DH3; Oct 18: DH3; Oct 19: DH3; Oct 20: DH3; Oct 21: DH3; Oct 22: DH3; Nov 15: DH6; Nov 16: DH6; Nov 17: DH6; Nov 18: DH6; Nov 19: DH6; Nov 20: DH7; Nov 21: DH7; Nov 22: DH7; Nov 23: DH7; Nov 24: DH7; Nov 25: DH7; Nov 26: DH7; Dec 12: DH11; Dec 13: DH11; Dec 14: DH11; Dec 15: DH11; Dec 16: DH11; Dec 17: DH11; Dec 18: DH11; Dec 19: DH2; Dec 20: DH2; Dec 21: DH2; Dec 22: DH2; Dec 23: DH2; Dec 24: DH2; Dec 25: DH2; Dec 26: DH2; Dec 27: DH2; Dec 28: DH2; Dec 29: DH2; Dec 30: DH2; Dec 31: DH2; Jan 01: DH2; Jan 02: DH2; Jan 03: DH2; Jan 14: DH12; Jan 15: DH12; Jan 16: DH12; Jan 17: DH12; Jan 18: DH12; Jan 19: DH12; Jan 20: DH12
|  | DH12 | #C5E5A6 | 0 | 14-Jan-25 | 20-Jan-25 | Dec 12: DH8; Dec 13: DH8; Dec 14: DH8; Dec 15: DH8; Dec 16: DH8; Dec 17: DH8; Dec 18: DH8; Dec 19: DH4; Dec 20: DH4; Dec 21: DH4; Dec 22: DH4; Dec 23: DH4; Dec 24: DH4; Dec 25: DH4; Dec 26: DH4; Dec 30: DH5; Dec 31: DH5; Jan 01: DH5; Jan 02: DH5; Jan 03: DH5; Jan 04: DH5; Jan 05: DH5; Jan 06: DH5; Jan 07: DH5; Jan 08: DH5; Jan 09: DH5; Jan 10: DH5; Jan 11: DH5; Jan 12: DH5; Jan 13: DH5; Jan 14: DH5; Jan 15: DH5; Jan 16: DH5; Jan 17: DH5; Jan 18: DH5; Jan 19: DH5; Jan 20: DH5
|  | DH2 | #C5E5A6 | 0 | 19-Dec-24 | 3-Jan-25
|  | DH3 | #C5E5A6 | 0 | 7-Oct-24 | 22-Oct-24
|  | DH4 | #C5E5A6 | 0 | 19-Dec-24 | 26-Dec-24
|  | DH5 | #C5E5A6 | 0 | 30-Dec-24 | 20-Jan-25
|  | DH6 | #C5E5A6 | 0 | 15-Nov-24 | 19-Nov-24
|  | DH7 | #C5E5A6 | 0 | 20-Nov-24 | 26-Nov-24
|  | DH8 | #C5E5A6 | 0 | 12-Dec-24 | 18-Dec-24
|  | DH9 | #C5E5A6 | 0 | 27-Nov-24 | 11-Dec-24 | Nov 27: DH9; Nov 28: DH9; Nov 29: DH9; Nov 30: DH9; Dec 01: DH9; Dec 02: DH9; Dec 03: DH9; Dec 04: DH9; Dec 05: DH9; Dec 06: DH9; Dec 07: DH9; Dec 08: DH9; Dec 09: DH9; Dec 10: DH9; Dec 11: DH9
| COLO 2 Cell 1 Mech Gallery | MG1 | #96CEFF | 0 | 7-Oct-24 | 11-Oct-24 | Oct 07: MG1; Oct 08: MG1; Oct 09: MG1; Oct 10: MG1; Oct 11: MG1
|  | MG10 | #96CEFF | 0 | 13-Dec-24 | 26-Dec-24 | Oct 09: MG2; Oct 10: MG2; Oct 11: MG2; Oct 12: MG2; Oct 13: MG2; Oct 14: MG2; Oct 15: MG2; Oct 16: MG3; Oct 17: MG3; Oct 18: MG3; Oct 19: MG3; Oct 20: MG3; Oct 21: MG3; Oct 22: MG3; Oct 23: MG3; Oct 24: MG3; Oct 25: MG3; Oct 26: MG3; Oct 27: MG3; Oct 28: MG3; Oct 29: MG3; Oct 30: MG4; Oct 31: MG4; Nov 01: MG5; Nov 02: MG5; Nov 03: MG5; Nov 04: MG5; Nov 05: MG5; Nov 06: MG5; Nov 07: MG5; Nov 08: MG5; Nov 09: MG5; Nov 10: MG5; Nov 11: MG5; Nov 12: MG5; Nov 13: MG5; Nov 14: MG5; Nov 15: MG12; Nov 16: MG12; Nov 17: MG12; Nov 18: MG12; Nov 19: MG12; Nov 20: MG12; Nov 21: MG12; Nov 22: MG12; Nov 23: MG12; Nov 24: MG12; Nov 25: MG12; Nov 26: MG12; Nov 27: MG12; Nov 28: MG12; Nov 29: MG12; Nov 30: MG12; Dec 01: MG12; Dec 02: MG12; Dec 03: MG12; Dec 04: MG12; Dec 05: MG12; Dec 06: MG12; Dec 13: MG10; Dec 14: MG10; Dec 15: MG10; Dec 16: MG10; Dec 17: MG10; Dec 18: MG10; Dec 19: MG10; Dec 20: MG10; Dec 21: MG10; Dec 22: MG10; Dec 23: MG10; Dec 24: MG10; Dec 25: MG10; Dec 26: MG10
|  | MG11 | #96CEFF | 0 | 18-Dec-24 | 26-Dec-24 | Nov 15: MG7; Nov 22: MG6; Nov 23: MG6; Nov 24: MG6; Nov 25: MG6; Nov 26: MG6; Dec 18: MG11; Dec 19: MG11; Dec 20: MG11; Dec 21: MG11; Dec 22: MG11; Dec 23: MG11; Dec 24: MG11; Dec 25: MG11; Dec 26: MG11
|  | MG12 | #96CEFF | 0 | 15-Nov-24 | 6-Dec-24 | Nov 26: MG8; Nov 27: MG8; Nov 28: MG8; Nov 29: MG8; Nov 30: MG8; Dec 01: MG8; Dec 02: MG8; Dec 03: MG8; Dec 04: MG8; Dec 05: MG8; Dec 06: MG8; Dec 07: MG8; Dec 08: MG8; Dec 09: MG8; Dec 10: MG8; Dec 11: MG8
|  | MG2 | #96CEFF | 0 | 9-Oct-24 | 15-Oct-24
|  | MG3 | #96CEFF | 0 | 16-Oct-24 | 29-Oct-24
|  | MG4 | #96CEFF | 0 | 30-Oct-24 | 31-Oct-24
|  | MG5 | #96CEFF | 0 | 1-Nov-24 | 14-Nov-24
|  | MG6 | #96CEFF | 0 | 22-Nov-24 | 26-Nov-24
|  | MG7 | #96CEFF | 0 | 15-Nov-24 | 15-Nov-24
|  | MG8 | #96CEFF | 0 | 26-Nov-24 | 11-Dec-24
|  | MG9 | #96CEFF | 0 | 11-Dec-24 | 13-Dec-24 | Dec 11: MG9; Dec 12: MG9; Dec 13: MG9
| COLO 2 Cell 1 Cx L4 | L4 | #FFFFFF | 0 | 1-May-25 | 4-Jun-25 | bar: May 01 to Jun 04
| COLO 2 Cell 1 Cx L5 | L5 | #FFFFFF | 0 | 5-Jun-25 | 6-Jun-25 | bar: Jun 05 to Jun 06
| COLO 2 Cell 1 Electrical Room | ER1 | #FFC000 | 0 | 7-Oct-24 | 18-Oct-24 | Oct 07: ER1; Oct 08: ER1; Oct 09: ER1; Oct 10: ER1; Oct 11: ER1; Oct 12: ER1; Oct 13: ER1; Oct 14: ER1; Oct 15: ER1; Oct 16: ER1; Oct 17: ER1; Oct 18: ER1
|  | ER10 | #FFC000 | 0 | 3-Jan-25 | 9-Jan-25 | Oct 16: ER3; Oct 17: ER3; Oct 18: ER3; Oct 19: ER3; Oct 20: ER3; Oct 21: ER3; Oct 22: ER3; Oct 23: ER2; Oct 24: ER2; Oct 25: ER2; Oct 26: ER2; Oct 27: ER2; Oct 28: ER2; Oct 29: ER2; Oct 30: ER2; Oct 31: ER2; Nov 01: ER2; Nov 02: ER2; Nov 03: ER2; Nov 04: ER2; Nov 05: ER2; Nov 06: ER4; Nov 07: ER4; Nov 08: ER4; Nov 29: ER12; Nov 30: ER12; Dec 01: ER12; Dec 02: ER12; Dec 03: ER12; Dec 04: ER12; Dec 05: ER12; Jan 03: ER10; Jan 04: ER10; Jan 05: ER10; Jan 06: ER10; Jan 07: ER10; Jan 08: ER10; Jan 09: ER10; Jan 10: ER11; Jan 11: ER11; Jan 12: ER11; Jan 13: ER11; Jan 14: ER11; Jan 15: ER11; Jan 16: ER11
|  | ER11 | #FFC000 | 0 | 10-Jan-25 | 16-Jan-25 | Nov 19: ER5; Nov 20: ER5; Nov 21: ER5; Nov 22: ER5; Nov 23: ER5; Nov 24: ER5; Nov 25: ER5; Nov 26: ER5; Nov 27: ER5; Nov 28: ER5; Nov 29: ER5; Nov 30: ER5; Dec 01: ER5; Dec 02: ER5; Dec 03: ER5; Dec 04: ER7; Dec 05: ER7; Dec 06: ER7; Dec 07: ER7; Dec 08: ER7; Dec 09: ER7; Dec 10: ER7
|  | ER12 | #FFC000 | 0 | 29-Nov-24 | 5-Dec-24 | Nov 29: ER6; Nov 30: ER6; Dec 01: ER6; Dec 02: ER6; Dec 03: ER6; Dec 04: ER6; Dec 05: ER6
|  | ER2 | #FFC000 | 0 | 23-Oct-24 | 5-Nov-24 | Dec 03: ER8; Dec 04: ER8; Dec 05: ER8; Dec 06: ER8; Dec 07: ER8; Dec 08: ER8; Dec 09: ER8
|  | ER3 | #FFC000 | 0 | 16-Oct-24 | 22-Oct-24
|  | ER4 | #FFC000 | 0 | 6-Nov-24 | 8-Nov-24
|  | ER5 | #FFC000 | 0 | 19-Nov-24 | 3-Dec-24
|  | ER6 | #FFC000 | 0 | 29-Nov-24 | 5-Dec-24
|  | ER7 | #FFC000 | 0 | 4-Dec-24 | 10-Dec-24
|  | ER8 | #FFC000 | 0 | 3-Dec-24 | 9-Dec-24
|  | ER9 | #FFC000 | 0 | 18-Dec-24 | 9-Jan-25 | Dec 18: ER9; Dec 19: ER9; Dec 20: ER9; Dec 21: ER9; Dec 22: ER9; Dec 23: ER9; Dec 24: ER9; Dec 25: ER9; Dec 26: ER9; Dec 27: ER9; Dec 28: ER9; Dec 29: ER9; Dec 30: ER9; Dec 31: ER9; Jan 01: ER9; Jan 02: ER9; Jan 03: ER9; Jan 04: ER9; Jan 05: ER9; Jan 06: ER9; Jan 07: ER9; Jan 08: ER9; Jan 09: ER9
| COLO 2 Cell 2 Commissioning | C1 | #F59CA6 | 0 | 6-Dec-24 | 12-Dec-24 | bar: Dec 06 to Dec 12
|  | C10 | #F59CA6 | 0 | 13-Jan-25 | 24-Jan-25 | Oct 23: C3; Oct 24: C3; Oct 25: C3; Oct 26: C3; Oct 27: C3; Oct 28: C3; Oct 29: C3; Oct 30: C3; Oct 31: C3; Nov 01: C3; Nov 02: C3; Nov 03: C3; Nov 04: C3; Nov 05: C3; Nov 06: C3; Nov 07: C3; Dec 02: C6; Dec 03: C6; Dec 04: C6; Dec 05: C7; Dec 06: C7; Dec 07: C7; Dec 08: C7; Dec 09: C7; Dec 10: C7; Dec 11: C7; Dec 27: C11; Dec 28: C11; Dec 29: C11; Dec 30: C11; Dec 31: C11; Jan 01: C11; Jan 02: C11; Jan 03: C11; Jan 06: C15; Jan 07: C17; Jan 08: C16; Jan 13: C10; Jan 14: C10; Jan 15: C10; Jan 16: C10; Jan 17: C10; Jan 18: C10; Jan 19: C10; Jan 20: C10; Jan 21: C10; Jan 22: C10; Jan 23: C10; Jan 24: C10; Feb 04: C12; Feb 05: C12; Feb 06: C12; Feb 07: C12; Feb 08: C12; Feb 09: C12; Feb 10: C12; Feb 25: C20; Feb 26: C20; Feb 27: C20; Feb 28: C20; Mar 01: C20; Mar 02: C20; Mar 03: C20; Mar 04: C21; Mar 05: C21; Mar 06: C21; Mar 07: C21; Mar 08: C21; Mar 09: C21; Mar 10: C21
|  | C11 | #F59CA6 | 0 | 27-Dec-24 | 3-Jan-25 | Jan 02: C13; Jan 03: C14; Jan 06: C19; Jan 07: C18; Jan 21: C2; Jan 22: C2; Jan 23: C2; Jan 24: C2; Jan 25: C2; Jan 26: C2; Jan 27: C2; Jan 28: C2; Jan 29: C2; Jan 30: C2; Jan 31: C2; Feb 01: C2; Feb 02: C2; Feb 03: C2; Feb 04: C2; Feb 05: C2; Feb 06: C2; Feb 07: C2; Feb 08: C2; Feb 09: C2; Feb 10: C2
|  | C12 | #F59CA6 | 0 | 4-Feb-25 | 10-Feb-25 | bar: Dec 27 to Jan 03; Jan 06 to Jan 10
|  | C13 | #F59CA6 | 0 | 2-Jan-25 | 2-Jan-25 | bar: Jan 06 to Jan 17
|  | C14 | #F59CA6 | 0 | 3-Jan-25 | 3-Jan-25
|  | C15 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C16 | #F59CA6 | 0 | 8-Jan-25 | 8-Jan-25
|  | C17 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C18 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C19 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C2 | #F59CA6 | 0 | 21-Jan-25 | 10-Feb-25
|  | C20 | #F59CA6 | 0 | 25-Feb-25 | 3-Mar-25
|  | C21 | #F59CA6 | 0 | 4-Mar-25 | 10-Mar-25
|  | C3 | #F59CA6 | 0 | 23-Oct-24 | 7-Nov-24
|  | C4 | #F59CA6 | 0 | 6-Jan-25 | 10-Jan-25
|  | C5 | #F59CA6 | 0 | 6-Jan-25 | 17-Jan-25
|  | C6 | #F59CA6 | 0 | 2-Dec-24 | 4-Dec-24
|  | C7 | #F59CA6 | 0 | 5-Dec-24 | 11-Dec-24
|  | C8 | #F59CA6 | 0 | 27-Dec-24 | 3-Jan-25
|  | C9 | #F59CA6 | 0 | 12-Dec-24 | 26-Dec-24 | bar: Dec 12 to Dec 26
| COLO 2 Cell 2 Data Hall | DH10 | #C5E5A6 | 0 | 10-Jan-25 | 30-Jan-25 | Jan 10: DH10; Jan 11: DH10; Jan 12: DH10; Jan 13: DH10; Jan 14: DH10; Jan 15: DH10; Jan 16: DH10; Jan 17: DH10; Jan 18: DH10; Jan 19: DH10; Jan 20: DH10; Jan 21: DH10; Jan 22: DH10; Jan 23: DH10; Jan 24: DH10; Jan 25: DH10; Jan 26: DH10; Jan 27: DH10; Jan 28: DH10; Jan 29: DH10; Jan 30: DH10
|  | DH11 | #C5E5A6 | 0 | 3-Jan-25 | 9-Jan-25 | Oct 30: DH4; Oct 31: DH4; Nov 01: DH4; Nov 02: DH4; Nov 03: DH4; Nov 04: DH4; Nov 05: DH4; Nov 06: DH3; Nov 07: DH3; Nov 08: DH3; Nov 09: DH3; Nov 10: DH3; Nov 11: DH3; Nov 12: DH3; Nov 13: DH3; Nov 14: DH3; Nov 15: DH3; Nov 16: DH3; Nov 17: DH3; Nov 18: DH3; Nov 19: DH3; Nov 20: DH2; Nov 21: DH2; Nov 22: DH2; Dec 04: DH6; Dec 05: DH6; Dec 06: DH6; Dec 07: DH6; Dec 08: DH6; Dec 09: DH6; Dec 10: DH6; Dec 11: DH6; Dec 12: DH6; Dec 13: DH6; Dec 14: DH6; Dec 15: DH6; Dec 16: DH6; Dec 17: DH6; Jan 03: DH11; Jan 04: DH11; Jan 05: DH11; Jan 06: DH11; Jan 07: DH11; Jan 08: DH11; Jan 09: DH11; Jan 28: DH12; Jan 29: DH12; Jan 30: DH12; Jan 31: DH12; Feb 01: DH12; Feb 02: DH12; Feb 03: DH12
|  | DH12 | #C5E5A6 | 0 | 28-Jan-25 | 3-Feb-25 | Oct 21: DH5; Oct 22: DH5; Oct 23: DH5; Oct 24: DH5; Oct 25: DH5; Oct 26: DH5; Oct 27: DH5; Oct 28: DH5; Oct 29: DH5; Oct 30: DH5; Oct 31: DH5; Nov 01: DH5; Dec 06: DH7; Dec 07: DH7; Dec 08: DH7; Dec 09: DH7; Dec 10: DH7; Dec 11: DH7; Dec 12: DH7
|  | DH2 | #C5E5A6 | 0 | 20-Nov-24 | 22-Nov-24 | Dec 11: DH8; Dec 12: DH8; Dec 13: DH8; Dec 14: DH8; Dec 15: DH8; Dec 16: DH8; Dec 17: DH8
|  | DH3 | #C5E5A6 | 0 | 6-Nov-24 | 19-Nov-24
|  | DH4 | #C5E5A6 | 0 | 30-Oct-24 | 5-Nov-24
|  | DH5 | #C5E5A6 | 0 | 21-Oct-24 | 1-Nov-24
|  | DH6 | #C5E5A6 | 0 | 4-Dec-24 | 17-Dec-24
|  | DH7 | #C5E5A6 | 0 | 6-Dec-24 | 12-Dec-24
|  | DH8 | #C5E5A6 | 0 | 11-Dec-24 | 17-Dec-24
|  | DH9 | #C5E5A6 | 0 | 10-Dec-24 | 16-Dec-24 | Dec 10: DH9; Dec 11: DH9; Dec 12: DH9; Dec 13: DH9; Dec 14: DH9; Dec 15: DH9; Dec 16: DH9
| COLO 2 Cell 2 Electrical Room | ER1 | #FFC000 | 0 | 11-Mar-25 | 17-Mar-25 | Mar 11: ER1; Mar 12: ER1; Mar 13: ER1; Mar 14: ER1; Mar 15: ER1; Mar 16: ER1; Mar 17: ER1
|  | ER10 | #FFC000 | 0 | 15-Apr-25 | 21-Apr-25 | Mar 11: ER5; Mar 12: ER5; Mar 13: ER5; Mar 14: ER5; Mar 15: ER5; Mar 16: ER5; Mar 17: ER5; Mar 18: ER3; Mar 19: ER3; Mar 20: ER3; Mar 21: ER3; Mar 22: ER3; Mar 23: ER3; Mar 24: ER3; Mar 25: ER2; Mar 26: ER2; Mar 27: ER2; Mar 28: ER2; Mar 29: ER2; Mar 30: ER2; Mar 31: ER2; Apr 01: ER7; Apr 02: ER7; Apr 03: ER7; Apr 04: ER7; Apr 05: ER7; Apr 06: ER7; Apr 07: ER7; Apr 08: ER12; Apr 09: ER12; Apr 10: ER12; Apr 11: ER12; Apr 12: ER12; Apr 13: ER12; Apr 14: ER12; Apr 15: ER10; Apr 16: ER10; Apr 17: ER10; Apr 18: ER10; Apr 19: ER10; Apr 20: ER10; Apr 21: ER10
|  | ER11 | #FFC000 | 0 | 15-Apr-25 | 21-Apr-25 | Mar 18: ER4; Mar 19: ER4; Mar 20: ER4; Mar 21: ER4; Mar 22: ER4; Mar 23: ER4; Mar 24: ER4; Mar 25: ER6; Mar 26: ER6; Mar 27: ER6; Mar 28: ER6; Mar 29: ER6; Mar 30: ER6; Mar 31: ER6; Apr 08: ER8; Apr 09: ER8; Apr 10: ER8; Apr 11: ER8; Apr 12: ER8; Apr 13: ER8; Apr 14: ER8; Apr 15: ER11; Apr 16: ER11; Apr 17: ER11; Apr 18: ER11; Apr 19: ER11; Apr 20: ER11; Apr 21: ER11
|  | ER12 | #FFC000 | 0 | 8-Apr-25 | 14-Apr-25
|  | ER2 | #FFC000 | 0 | 25-Mar-25 | 31-Mar-25
|  | ER3 | #FFC000 | 0 | 18-Mar-25 | 24-Mar-25
|  | ER4 | #FFC000 | 0 | 18-Mar-25 | 24-Mar-25
|  | ER5 | #FFC000 | 0 | 11-Mar-25 | 17-Mar-25
|  | ER6 | #FFC000 | 0 | 25-Mar-25 | 31-Mar-25
|  | ER7 | #FFC000 | 0 | 1-Apr-25 | 7-Apr-25
|  | ER8 | #FFC000 | 0 | 8-Apr-25 | 14-Apr-25
|  | ER9 | #FFC000 | 0 | 22-Apr-25 | 28-Apr-25 | Apr 22: ER9; Apr 23: ER9; Apr 24: ER9; Apr 25: ER9; Apr 26: ER9; Apr 27: ER9; Apr 28: ER9
| COLO 2 Cell 2 Mech Gallery | MG1 | #96CEFF | 0 | 14-Oct-24 | 18-Oct-24 | Oct 14: MG1; Oct 15: MG1; Oct 16: MG1; Oct 17: MG1; Oct 18: MG1
|  | MG10 | #96CEFF | 0 | 30-Dec-24 | 10-Jan-25 | Oct 16: MG2; Oct 17: MG2; Oct 18: MG2; Oct 19: MG2; Oct 20: MG2; Oct 21: MG2; Oct 22: MG2; Oct 30: MG3; Oct 31: MG3; Nov 01: MG3; Nov 02: MG3; Nov 03: MG3; Nov 04: MG3; Nov 05: MG3; Nov 06: MG3; Nov 07: MG3; Nov 08: MG3; Nov 09: MG3; Nov 10: MG3; Nov 11: MG3; Nov 12: MG3; Nov 13: MG4; Nov 14: MG4; Nov 15: MG5; Nov 16: MG5; Nov 17: MG5; Nov 18: MG5; Nov 19: MG5; Nov 20: MG5; Nov 21: MG5; Nov 22: MG5; Nov 23: MG5; Nov 24: MG5; Nov 25: MG5; Nov 26: MG5; Nov 27: MG5; Nov 28: MG5; Nov 29: MG5; Dec 02: MG12; Dec 03: MG12; Dec 04: MG12; Dec 05: MG12; Dec 06: MG12; Dec 07: MG12; Dec 08: MG12; Dec 09: MG12; Dec 10: MG12; Dec 11: MG12; Dec 12: MG12; Dec 13: MG12; Dec 14: MG12; Dec 15: MG12; Dec 16: MG12; Dec 17: MG12; Dec 18: MG12; Dec 19: MG12; Dec 20: MG12; Dec 30: MG10; Dec 31: MG10; Jan 01: MG10; Jan 02: MG10; Jan 03: MG10; Jan 04: MG10; Jan 05: MG10; Jan 06: MG10; Jan 07: MG10; Jan 08: MG10; Jan 09: MG10; Jan 10: MG10
|  | MG11 | #96CEFF | 0 | 3-Jan-25 | 10-Jan-25 | Dec 02: MG7; Dec 09: MG6; Dec 10: MG6; Dec 11: MG6; Jan 03: MG11; Jan 04: MG11; Jan 05: MG11; Jan 06: MG11; Jan 07: MG11; Jan 08: MG11; Jan 09: MG11; Jan 10: MG11
|  | MG12 | #96CEFF | 0 | 2-Dec-24 | 20-Dec-24 | Dec 11: MG8; Dec 12: MG8; Dec 13: MG8; Dec 14: MG8; Dec 15: MG8; Dec 16: MG8; Dec 17: MG8; Dec 18: MG8; Dec 19: MG8; Dec 20: MG8; Dec 21: MG8; Dec 22: MG8; Dec 23: MG8; Dec 24: MG8; Dec 25: MG8; Dec 26: MG8
|  | MG2 | #96CEFF | 0 | 16-Oct-24 | 22-Oct-24
|  | MG3 | #96CEFF | 0 | 30-Oct-24 | 12-Nov-24
|  | MG4 | #96CEFF | 0 | 13-Nov-24 | 14-Nov-24
|  | MG5 | #96CEFF | 0 | 15-Nov-24 | 29-Nov-24
|  | MG6 | #96CEFF | 0 | 9-Dec-24 | 11-Dec-24
|  | MG7 | #96CEFF | 0 | 2-Dec-24 | 2-Dec-24
|  | MG8 | #96CEFF | 0 | 11-Dec-24 | 26-Dec-24
|  | MG9 | #96CEFF | 0 | 26-Dec-24 | 30-Dec-24 | Dec 26: MG9; Dec 27: MG9; Dec 28: MG9; Dec 29: MG9; Dec 30: MG9

## Sheet4
[7 empty] | 2024 | 2024 | [84 empty] | 2025
[7 empty] | Oct | Oct | [23 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun
[7 empty] | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06
phase | location | activity_code | color | activity_ins | start | finish | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Fitout | COLO 2 Cell 1 Commissioning | C1 | #F59CA6 | 0 | 2-Jan-25 | 2-Jan-25 | Jan 02: C1; Jan 03: C2; Jan 06: C3; Jan 07: C5; Jan 08: C4; Feb 25: C8; Feb 26: C8; Feb 27: C8; Feb 28: C8; Mar 01: C8; Mar 02: C8; Mar 03: C8; Mar 04: C9; Mar 05: C9; Mar 06: C9; Mar 07: C9; Mar 08: C9; Mar 09: C9; Mar 10: C9; Mar 11: C10; Mar 12: C10; Mar 13: C10; Mar 14: C10; Mar 15: C10; Mar 16: C10; Mar 17: C10; Mar 18: C12; Mar 19: C12; Mar 20: C12; Mar 21: C12; Mar 22: C12; Mar 23: C12; Mar 24: C12; Mar 25: C11; Mar 26: C11; Mar 27: C11; Mar 28: C11; Mar 29: C11; Mar 30: C11; Mar 31: C11; Apr 01: C16; Apr 02: C16; Apr 03: C16; Apr 04: C16; Apr 05: C16; Apr 06: C16; Apr 07: C16; Apr 08: C17; Apr 09: C17; Apr 10: C17; Apr 11: C17; Apr 12: C17; Apr 13: C17; Apr 14: C17; Apr 15: C19; Apr 16: C19; Apr 17: C19; Apr 18: C19; Apr 19: C19; Apr 20: C19; Apr 21: C19; Apr 22: C18; Apr 23: C18; Apr 24: C18; Apr 25: C18; Apr 26: C18; Apr 27: C18; Apr 28: C18
|  | C10 | #F59CA6 | 0 | 11-Mar-25 | 17-Mar-25 | Jan 06: C7; Jan 07: C6; Mar 11: C14; Mar 12: C14; Mar 13: C14; Mar 14: C14; Mar 15: C14; Mar 16: C14; Mar 17: C14; Mar 18: C13; Mar 19: C13; Mar 20: C13; Mar 21: C13; Mar 22: C13; Mar 23: C13; Mar 24: C13; Mar 25: C15; Mar 26: C15; Mar 27: C15; Mar 28: C15; Mar 29: C15; Mar 30: C15; Mar 31: C15; Apr 08: C21; Apr 09: C21; Apr 10: C21; Apr 11: C21; Apr 12: C21; Apr 13: C21; Apr 14: C21; Apr 15: C20; Apr 16: C20; Apr 17: C20; Apr 18: C20; Apr 19: C20; Apr 20: C20; Apr 21: C20
|  | C11 | #F59CA6 | 0 | 25-Mar-25 | 31-Mar-25
|  | C12 | #F59CA6 | 0 | 18-Mar-25 | 24-Mar-25
|  | C13 | #F59CA6 | 0 | 18-Mar-25 | 24-Mar-25
|  | C14 | #F59CA6 | 0 | 11-Mar-25 | 17-Mar-25
|  | C15 | #F59CA6 | 0 | 25-Mar-25 | 31-Mar-25
|  | C16 | #F59CA6 | 0 | 1-Apr-25 | 7-Apr-25
|  | C17 | #F59CA6 | 0 | 8-Apr-25 | 14-Apr-25
|  | C18 | #F59CA6 | 0 | 22-Apr-25 | 28-Apr-25
|  | C19 | #F59CA6 | 0 | 15-Apr-25 | 21-Apr-25
|  | C2 | #F59CA6 | 0 | 3-Jan-25 | 3-Jan-25
|  | C20 | #F59CA6 | 0 | 15-Apr-25 | 21-Apr-25
|  | C21 | #F59CA6 | 0 | 8-Apr-25 | 14-Apr-25
|  | C3 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C4 | #F59CA6 | 0 | 8-Jan-25 | 8-Jan-25
|  | C5 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C6 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C7 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C8 | #F59CA6 | 0 | 25-Feb-25 | 3-Mar-25
|  | C9 | #F59CA6 | 0 | 4-Mar-25 | 10-Mar-25
| COLO 2 Cell 1 Data Hall | DH10 | #C5E5A6 | 0 | 27-Dec-24 | 10-Jan-25 | Oct 07: DH3; Oct 08: DH3; Oct 09: DH3; Oct 10: DH3; Oct 11: DH3; Oct 12: DH3; Oct 13: DH3; Oct 14: DH3; Oct 15: DH3; Oct 16: DH3; Oct 17: DH3; Oct 18: DH3; Oct 19: DH3; Oct 20: DH3; Oct 21: DH3; Oct 22: DH3; Nov 15: DH6; Nov 16: DH6; Nov 17: DH6; Nov 18: DH6; Nov 19: DH6; Nov 20: DH7; Nov 21: DH7; Nov 22: DH7; Nov 23: DH7; Nov 24: DH7; Nov 25: DH7; Nov 26: DH7; Nov 27: DH9; Nov 28: DH9; Nov 29: DH9; Nov 30: DH9; Dec 01: DH9; Dec 02: DH9; Dec 03: DH9; Dec 04: DH9; Dec 05: DH9; Dec 06: DH9; Dec 07: DH9; Dec 08: DH9; Dec 09: DH9; Dec 10: DH9; Dec 11: DH9; Dec 12: DH11; Dec 13: DH11; Dec 14: DH11; Dec 15: DH11; Dec 16: DH11; Dec 17: DH11; Dec 18: DH11; Dec 19: DH4; Dec 20: DH4; Dec 21: DH4; Dec 22: DH4; Dec 23: DH4; Dec 24: DH4; Dec 25: DH4; Dec 26: DH4; Dec 27: DH10; Dec 28: DH10; Dec 29: DH10; Dec 30: DH10; Dec 31: DH10; Jan 01: DH10; Jan 02: DH10; Jan 03: DH10; Jan 04: DH10; Jan 05: DH10; Jan 06: DH10; Jan 07: DH10; Jan 08: DH10; Jan 09: DH10; Jan 10: DH10; Jan 14: DH12; Jan 15: DH12; Jan 16: DH12; Jan 17: DH12; Jan 18: DH12; Jan 19: DH12; Jan 20: DH12
|  | DH11 | #C5E5A6 | 0 | 12-Dec-24 | 18-Dec-24 | Dec 12: DH8; Dec 13: DH8; Dec 14: DH8; Dec 15: DH8; Dec 16: DH8; Dec 17: DH8; Dec 18: DH8; Dec 19: DH2; Dec 20: DH2; Dec 21: DH2; Dec 22: DH2; Dec 23: DH2; Dec 24: DH2; Dec 25: DH2; Dec 26: DH2; Dec 27: DH2; Dec 28: DH2; Dec 29: DH2; Dec 30: DH2; Dec 31: DH2; Jan 01: DH2; Jan 02: DH2; Jan 03: DH2
|  | DH12 | #C5E5A6 | 0 | 14-Jan-25 | 20-Jan-25 | Dec 30: DH5; Dec 31: DH5; Jan 01: DH5; Jan 02: DH5; Jan 03: DH5; Jan 04: DH5; Jan 05: DH5; Jan 06: DH5; Jan 07: DH5; Jan 08: DH5; Jan 09: DH5; Jan 10: DH5; Jan 11: DH5; Jan 12: DH5; Jan 13: DH5; Jan 14: DH5; Jan 15: DH5; Jan 16: DH5; Jan 17: DH5; Jan 18: DH5; Jan 19: DH5; Jan 20: DH5
|  | DH2 | #C5E5A6 | 0 | 19-Dec-24 | 3-Jan-25
|  | DH3 | #C5E5A6 | 0 | 7-Oct-24 | 22-Oct-24
|  | DH4 | #C5E5A6 | 0 | 19-Dec-24 | 26-Dec-24
|  | DH5 | #C5E5A6 | 0 | 30-Dec-24 | 20-Jan-25
|  | DH6 | #C5E5A6 | 0 | 15-Nov-24 | 19-Nov-24
|  | DH7 | #C5E5A6 | 0 | 20-Nov-24 | 26-Nov-24
|  | DH8 | #C5E5A6 | 0 | 12-Dec-24 | 18-Dec-24
|  | DH9 | #C5E5A6 | 0 | 27-Nov-24 | 11-Dec-24
| COLO 2 Cell 1 Mech Gallery | MG1 | #96CEFF | 0 | 7-Oct-24 | 11-Oct-24 | Oct 07: MG1; Oct 08: MG1; Oct 09: MG1; Oct 10: MG1; Oct 11: MG1; Oct 16: MG3; Oct 17: MG3; Oct 18: MG3; Oct 19: MG3; Oct 20: MG3; Oct 21: MG3; Oct 22: MG3; Oct 23: MG3; Oct 24: MG3; Oct 25: MG3; Oct 26: MG3; Oct 27: MG3; Oct 28: MG3; Oct 29: MG3; Oct 30: MG4; Oct 31: MG4; Nov 01: MG5; Nov 02: MG5; Nov 03: MG5; Nov 04: MG5; Nov 05: MG5; Nov 06: MG5; Nov 07: MG5; Nov 08: MG5; Nov 09: MG5; Nov 10: MG5; Nov 11: MG5; Nov 12: MG5; Nov 13: MG5; Nov 14: MG5; Nov 15: MG12; Nov 16: MG12; Nov 17: MG12; Nov 18: MG12; Nov 19: MG12; Nov 20: MG12; Nov 21: MG12; Nov 22: MG12; Nov 23: MG12; Nov 24: MG12; Nov 25: MG12; Nov 26: MG12; Nov 27: MG12; Nov 28: MG12; Nov 29: MG12; Nov 30: MG12; Dec 01: MG12; Dec 02: MG12; Dec 03: MG12; Dec 04: MG12; Dec 05: MG12; Dec 06: MG12; Dec 13: MG10; Dec 14: MG10; Dec 15: MG10; Dec 16: MG10; Dec 17: MG10; Dec 18: MG10; Dec 19: MG10; Dec 20: MG10; Dec 21: MG10; Dec 22: MG10; Dec 23: MG10; Dec 24: MG10; Dec 25: MG10; Dec 26: MG10
|  | MG10 | #96CEFF | 0 | 13-Dec-24 | 26-Dec-24 | Oct 09: MG2; Oct 10: MG2; Oct 11: MG2; Oct 12: MG2; Oct 13: MG2; Oct 14: MG2; Oct 15: MG2; Nov 15: MG7; Nov 22: MG6; Nov 23: MG6; Nov 24: MG6; Nov 25: MG6; Nov 26: MG6; Dec 11: MG9; Dec 12: MG9; Dec 13: MG9; Dec 18: MG11; Dec 19: MG11; Dec 20: MG11; Dec 21: MG11; Dec 22: MG11; Dec 23: MG11; Dec 24: MG11; Dec 25: MG11; Dec 26: MG11
|  | MG11 | #96CEFF | 0 | 18-Dec-24 | 26-Dec-24 | Nov 26: MG8; Nov 27: MG8; Nov 28: MG8; Nov 29: MG8; Nov 30: MG8; Dec 01: MG8; Dec 02: MG8; Dec 03: MG8; Dec 04: MG8; Dec 05: MG8; Dec 06: MG8; Dec 07: MG8; Dec 08: MG8; Dec 09: MG8; Dec 10: MG8; Dec 11: MG8
|  | MG12 | #96CEFF | 0 | 15-Nov-24 | 6-Dec-24
|  | MG2 | #96CEFF | 0 | 9-Oct-24 | 15-Oct-24
|  | MG3 | #96CEFF | 0 | 16-Oct-24 | 29-Oct-24
|  | MG4 | #96CEFF | 0 | 30-Oct-24 | 31-Oct-24
|  | MG5 | #96CEFF | 0 | 1-Nov-24 | 14-Nov-24
|  | MG6 | #96CEFF | 0 | 22-Nov-24 | 26-Nov-24
|  | MG7 | #96CEFF | 0 | 15-Nov-24 | 15-Nov-24
|  | MG8 | #96CEFF | 0 | 26-Nov-24 | 11-Dec-24
|  | MG9 | #96CEFF | 0 | 11-Dec-24 | 13-Dec-24
| COLO 2 Cell 1 Cx L4 | L4 | #FFFFFF | 0 | 1-May-25 | 4-Jun-25 | bar: May 01 to Jun 04
| COLO 2 Cell 1 Cx L5 | L5 | #FFFFFF | 0 | 5-Jun-25 | 6-Jun-25 | bar: Jun 05 to Jun 06
| COLO 2 Cell 1 Electrical Room | ER1 | #FFC000 | 0 | 7-Oct-24 | 18-Oct-24 | Oct 07: ER1; Oct 08: ER1; Oct 09: ER1; Oct 10: ER1; Oct 11: ER1; Oct 12: ER1; Oct 13: ER1; Oct 14: ER1; Oct 15: ER1; Oct 16: ER1; Oct 17: ER1; Oct 18: ER1; Oct 23: ER2; Oct 24: ER2; Oct 25: ER2; Oct 26: ER2; Oct 27: ER2; Oct 28: ER2; Oct 29: ER2; Oct 30: ER2; Oct 31: ER2; Nov 01: ER2; Nov 02: ER2; Nov 03: ER2; Nov 04: ER2; Nov 05: ER2; Nov 06: ER4; Nov 07: ER4; Nov 08: ER4; Nov 29: ER12; Nov 30: ER12; Dec 01: ER12; Dec 02: ER12; Dec 03: ER12; Dec 04: ER12; Dec 05: ER12; Jan 03: ER10; Jan 04: ER10; Jan 05: ER10; Jan 06: ER10; Jan 07: ER10; Jan 08: ER10; Jan 09: ER10; Jan 10: ER11; Jan 11: ER11; Jan 12: ER11; Jan 13: ER11; Jan 14: ER11; Jan 15: ER11; Jan 16: ER11
|  | ER10 | #FFC000 | 0 | 3-Jan-25 | 9-Jan-25 | Oct 16: ER3; Oct 17: ER3; Oct 18: ER3; Oct 19: ER3; Oct 20: ER3; Oct 21: ER3; Oct 22: ER3; Nov 19: ER5; Nov 20: ER5; Nov 21: ER5; Nov 22: ER5; Nov 23: ER5; Nov 24: ER5; Nov 25: ER5; Nov 26: ER5; Nov 27: ER5; Nov 28: ER5; Nov 29: ER5; Nov 30: ER5; Dec 01: ER5; Dec 02: ER5; Dec 03: ER5; Dec 04: ER7; Dec 05: ER7; Dec 06: ER7; Dec 07: ER7; Dec 08: ER7; Dec 09: ER7; Dec 10: ER7; Dec 18: ER9; Dec 19: ER9; Dec 20: ER9; Dec 21: ER9; Dec 22: ER9; Dec 23: ER9; Dec 24: ER9; Dec 25: ER9; Dec 26: ER9; Dec 27: ER9; Dec 28: ER9; Dec 29: ER9; Dec 30: ER9; Dec 31: ER9; Jan 01: ER9; Jan 02: ER9; Jan 03: ER9; Jan 04: ER9; Jan 05: ER9; Jan 06: ER9; Jan 07: ER9; Jan 08: ER9; Jan 09: ER9
|  | ER11 | #FFC000 | 0 | 10-Jan-25 | 16-Jan-25 | Nov 29: ER6; Nov 30: ER6; Dec 01: ER6; Dec 02: ER6; Dec 03: ER6; Dec 04: ER6; Dec 05: ER6
|  | ER12 | #FFC000 | 0 | 29-Nov-24 | 5-Dec-24 | Dec 03: ER8; Dec 04: ER8; Dec 05: ER8; Dec 06: ER8; Dec 07: ER8; Dec 08: ER8; Dec 09: ER8
|  | ER2 | #FFC000 | 0 | 23-Oct-24 | 5-Nov-24
|  | ER3 | #FFC000 | 0 | 16-Oct-24 | 22-Oct-24
|  | ER4 | #FFC000 | 0 | 6-Nov-24 | 8-Nov-24
|  | ER5 | #FFC000 | 0 | 19-Nov-24 | 3-Dec-24
|  | ER6 | #FFC000 | 0 | 29-Nov-24 | 5-Dec-24
|  | ER7 | #FFC000 | 0 | 4-Dec-24 | 10-Dec-24
|  | ER8 | #FFC000 | 0 | 3-Dec-24 | 9-Dec-24
|  | ER9 | #FFC000 | 0 | 18-Dec-24 | 9-Jan-25
| COLO 2 Cell 2 Commissioning | C1 | #F59CA6 | 0 | 6-Dec-24 | 12-Dec-24 | Oct 23: C3; Oct 24: C3; Oct 25: C3; Oct 26: C3; Oct 27: C3; Oct 28: C3; Oct 29: C3; Oct 30: C3; Oct 31: C3; Nov 01: C3; Nov 02: C3; Nov 03: C3; Nov 04: C3; Nov 05: C3; Nov 06: C3; Nov 07: C3; Dec 02: C6; Dec 03: C6; Dec 04: C6; Dec 06: C1; Dec 07: C1; Dec 08: C1; Dec 09: C1; Dec 10: C1; Dec 11: C1; Dec 12: C1; Dec 27: C11; Dec 28: C11; Dec 29: C11; Dec 30: C11; Dec 31: C11; Jan 01: C11; Jan 02: C11; Jan 03: C11; Jan 06: C15; Jan 07: C17; Jan 08: C16; Jan 13: C10; Jan 14: C10; Jan 15: C10; Jan 16: C10; Jan 17: C10; Jan 18: C10; Jan 19: C10; Jan 20: C10; Jan 21: C10; Jan 22: C10; Jan 23: C10; Jan 24: C10; Feb 04: C12; Feb 05: C12; Feb 06: C12; Feb 07: C12; Feb 08: C12; Feb 09: C12; Feb 10: C12; Feb 25: C20; Feb 26: C20; Feb 27: C20; Feb 28: C20; Mar 01: C20; Mar 02: C20; Mar 03: C20; Mar 04: C21; Mar 05: C21; Mar 06: C21; Mar 07: C21; Mar 08: C21; Mar 09: C21; Mar 10: C21
|  | C10 | #F59CA6 | 0 | 13-Jan-25 | 24-Jan-25 | Dec 05: C7; Dec 06: C7; Dec 07: C7; Dec 08: C7; Dec 09: C7; Dec 10: C7; Dec 11: C7; Dec 12: C9; Dec 13: C9; Dec 14: C9; Dec 15: C9; Dec 16: C9; Dec 17: C9; Dec 18: C9; Dec 19: C9; Dec 20: C9; Dec 21: C9; Dec 22: C9; Dec 23: C9; Dec 24: C9; Dec 25: C9; Dec 26: C9; Jan 02: C13; Jan 03: C14; Jan 06: C19; Jan 07: C18; Jan 21: C2; Jan 22: C2; Jan 23: C2; Jan 24: C2; Jan 25: C2; Jan 26: C2; Jan 27: C2; Jan 28: C2; Jan 29: C2; Jan 30: C2; Jan 31: C2; Feb 01: C2; Feb 02: C2; Feb 03: C2; Feb 04: C2; Feb 05: C2; Feb 06: C2; Feb 07: C2; Feb 08: C2; Feb 09: C2; Feb 10: C2
|  | C11 | #F59CA6 | 0 | 27-Dec-24 | 3-Jan-25 | bar: Dec 27 to Jan 03; Jan 06 to Jan 10
|  | C12 | #F59CA6 | 0 | 4-Feb-25 | 10-Feb-25 | bar: Jan 06 to Jan 17
|  | C13 | #F59CA6 | 0 | 2-Jan-25 | 2-Jan-25
|  | C14 | #F59CA6 | 0 | 3-Jan-25 | 3-Jan-25
|  | C15 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C16 | #F59CA6 | 0 | 8-Jan-25 | 8-Jan-25
|  | C17 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C18 | #F59CA6 | 0 | 7-Jan-25 | 7-Jan-25
|  | C19 | #F59CA6 | 0 | 6-Jan-25 | 6-Jan-25
|  | C2 | #F59CA6 | 0 | 21-Jan-25 | 10-Feb-25
|  | C20 | #F59CA6 | 0 | 25-Feb-25 | 3-Mar-25
|  | C21 | #F59CA6 | 0 | 4-Mar-25 | 10-Mar-25
|  | C3 | #F59CA6 | 0 | 23-Oct-24 | 7-Nov-24
|  | C4 | #F59CA6 | 0 | 6-Jan-25 | 10-Jan-25
|  | C5 | #F59CA6 | 0 | 6-Jan-25 | 17-Jan-25
|  | C6 | #F59CA6 | 0 | 2-Dec-24 | 4-Dec-24
|  | C7 | #F59CA6 | 0 | 5-Dec-24 | 11-Dec-24
|  | C8 | #F59CA6 | 0 | 27-Dec-24 | 3-Jan-25
|  | C9 | #F59CA6 | 0 | 12-Dec-24 | 26-Dec-24
| COLO 2 Cell 2 Data Hall | DH10 | #C5E5A6 | 0 | 10-Jan-25 | 30-Jan-25 | Oct 30: DH4; Oct 31: DH4; Nov 01: DH4; Nov 02: DH4; Nov 03: DH4; Nov 04: DH4; Nov 05: DH4; Nov 06: DH3; Nov 07: DH3; Nov 08: DH3; Nov 09: DH3; Nov 10: DH3; Nov 11: DH3; Nov 12: DH3; Nov 13: DH3; Nov 14: DH3; Nov 15: DH3; Nov 16: DH3; Nov 17: DH3; Nov 18: DH3; Nov 19: DH3; Nov 20: DH2; Nov 21: DH2; Nov 22: DH2; Dec 04: DH6; Dec 05: DH6; Dec 06: DH6; Dec 07: DH6; Dec 08: DH6; Dec 09: DH6; Dec 10: DH6; Dec 11: DH6; Dec 12: DH6; Dec 13: DH6; Dec 14: DH6; Dec 15: DH6; Dec 16: DH6; Dec 17: DH6; Jan 03: DH11; Jan 04: DH11; Jan 05: DH11; Jan 06: DH11; Jan 07: DH11; Jan 08: DH11; Jan 09: DH11; Jan 10: DH10; Jan 11: DH10; Jan 12: DH10; Jan 13: DH10; Jan 14: DH10; Jan 15: DH10; Jan 16: DH10; Jan 17: DH10; Jan 18: DH10; Jan 19: DH10; Jan 20: DH10; Jan 21: DH10; Jan 22: DH10; Jan 23: DH10; Jan 24: DH10; Jan 25: DH10; Jan 26: DH10; Jan 27: DH10; Jan 28: DH10; Jan 29: DH10; Jan 30: DH10
|  | DH11 | #C5E5A6 | 0 | 3-Jan-25 | 9-Jan-25 | Oct 21: DH5; Oct 22: DH5; Oct 23: DH5; Oct 24: DH5; Oct 25: DH5; Oct 26: DH5; Oct 27: DH5; Oct 28: DH5; Oct 29: DH5; Oct 30: DH5; Oct 31: DH5; Nov 01: DH5; Dec 06: DH7; Dec 07: DH7; Dec 08: DH7; Dec 09: DH7; Dec 10: DH7; Dec 11: DH7; Dec 12: DH7; Jan 28: DH12; Jan 29: DH12; Jan 30: DH12; Jan 31: DH12; Feb 01: DH12; Feb 02: DH12; Feb 03: DH12
|  | DH12 | #C5E5A6 | 0 | 28-Jan-25 | 3-Feb-25 | Dec 11: DH8; Dec 12: DH8; Dec 13: DH8; Dec 14: DH8; Dec 15: DH8; Dec 16: DH8; Dec 17: DH8
|  | DH2 | #C5E5A6 | 0 | 20-Nov-24 | 22-Nov-24 | Dec 10: DH9; Dec 11: DH9; Dec 12: DH9; Dec 13: DH9; Dec 14: DH9; Dec 15: DH9; Dec 16: DH9
|  | DH3 | #C5E5A6 | 0 | 6-Nov-24 | 19-Nov-24
|  | DH4 | #C5E5A6 | 0 | 30-Oct-24 | 5-Nov-24
|  | DH5 | #C5E5A6 | 0 | 21-Oct-24 | 1-Nov-24
|  | DH6 | #C5E5A6 | 0 | 4-Dec-24 | 17-Dec-24
|  | DH7 | #C5E5A6 | 0 | 6-Dec-24 | 12-Dec-24
|  | DH8 | #C5E5A6 | 0 | 11-Dec-24 | 17-Dec-24
|  | DH9 | #C5E5A6 | 0 | 10-Dec-24 | 16-Dec-24
| COLO 2 Cell 2 Electrical Room | ER1 | #FFC000 | 0 | 11-Mar-25 | 17-Mar-25 | Mar 11: ER1; Mar 12: ER1; Mar 13: ER1; Mar 14: ER1; Mar 15: ER1; Mar 16: ER1; Mar 17: ER1; Mar 18: ER3; Mar 19: ER3; Mar 20: ER3; Mar 21: ER3; Mar 22: ER3; Mar 23: ER3; Mar 24: ER3; Mar 25: ER2; Mar 26: ER2; Mar 27: ER2; Mar 28: ER2; Mar 29: ER2; Mar 30: ER2; Mar 31: ER2; Apr 01: ER7; Apr 02: ER7; Apr 03: ER7; Apr 04: ER7; Apr 05: ER7; Apr 06: ER7; Apr 07: ER7; Apr 08: ER12; Apr 09: ER12; Apr 10: ER12; Apr 11: ER12; Apr 12: ER12; Apr 13: ER12; Apr 14: ER12; Apr 15: ER10; Apr 16: ER10; Apr 17: ER10; Apr 18: ER10; Apr 19: ER10; Apr 20: ER10; Apr 21: ER10; Apr 22: ER9; Apr 23: ER9; Apr 24: ER9; Apr 25: ER9; Apr 26: ER9; Apr 27: ER9; Apr 28: ER9
|  | ER10 | #FFC000 | 0 | 15-Apr-25 | 21-Apr-25 | Mar 11: ER5; Mar 12: ER5; Mar 13: ER5; Mar 14: ER5; Mar 15: ER5; Mar 16: ER5; Mar 17: ER5; Mar 18: ER4; Mar 19: ER4; Mar 20: ER4; Mar 21: ER4; Mar 22: ER4; Mar 23: ER4; Mar 24: ER4; Mar 25: ER6; Mar 26: ER6; Mar 27: ER6; Mar 28: ER6; Mar 29: ER6; Mar 30: ER6; Mar 31: ER6; Apr 08: ER8; Apr 09: ER8; Apr 10: ER8; Apr 11: ER8; Apr 12: ER8; Apr 13: ER8; Apr 14: ER8; Apr 15: ER11; Apr 16: ER11; Apr 17: ER11; Apr 18: ER11; Apr 19: ER11; Apr 20: ER11; Apr 21: ER11
|  | ER11 | #FFC000 | 0 | 15-Apr-25 | 21-Apr-25
|  | ER12 | #FFC000 | 0 | 8-Apr-25 | 14-Apr-25
|  | ER2 | #FFC000 | 0 | 25-Mar-25 | 31-Mar-25
|  | ER3 | #FFC000 | 0 | 18-Mar-25 | 24-Mar-25
|  | ER4 | #FFC000 | 0 | 18-Mar-25 | 24-Mar-25
|  | ER5 | #FFC000 | 0 | 11-Mar-25 | 17-Mar-25
|  | ER6 | #FFC000 | 0 | 25-Mar-25 | 31-Mar-25
|  | ER7 | #FFC000 | 0 | 1-Apr-25 | 7-Apr-25
|  | ER8 | #FFC000 | 0 | 8-Apr-25 | 14-Apr-25
|  | ER9 | #FFC000 | 0 | 22-Apr-25 | 28-Apr-25
| COLO 2 Cell 2 Mech Gallery | MG1 | #96CEFF | 0 | 14-Oct-24 | 18-Oct-24 | Oct 14: MG1; Oct 15: MG1; Oct 16: MG1; Oct 17: MG1; Oct 18: MG1; Oct 30: MG3; Oct 31: MG3; Nov 01: MG3; Nov 02: MG3; Nov 03: MG3; Nov 04: MG3; Nov 05: MG3; Nov 06: MG3; Nov 07: MG3; Nov 08: MG3; Nov 09: MG3; Nov 10: MG3; Nov 11: MG3; Nov 12: MG3; Nov 13: MG4; Nov 14: MG4; Nov 15: MG5; Nov 16: MG5; Nov 17: MG5; Nov 18: MG5; Nov 19: MG5; Nov 20: MG5; Nov 21: MG5; Nov 22: MG5; Nov 23: MG5; Nov 24: MG5; Nov 25: MG5; Nov 26: MG5; Nov 27: MG5; Nov 28: MG5; Nov 29: MG5; Dec 02: MG12; Dec 03: MG12; Dec 04: MG12; Dec 05: MG12; Dec 06: MG12; Dec 07: MG12; Dec 08: MG12; Dec 09: MG12; Dec 10: MG12; Dec 11: MG12; Dec 12: MG12; Dec 13: MG12; Dec 14: MG12; Dec 15: MG12; Dec 16: MG12; Dec 17: MG12; Dec 18: MG12; Dec 19: MG12; Dec 20: MG12; Dec 30: MG10; Dec 31: MG10; Jan 01: MG10; Jan 02: MG10; Jan 03: MG10; Jan 04: MG10; Jan 05: MG10; Jan 06: MG10; Jan 07: MG10; Jan 08: MG10; Jan 09: MG10; Jan 10: MG10
|  | MG10 | #96CEFF | 0 | 30-Dec-24 | 10-Jan-25 | Oct 16: MG2; Oct 17: MG2; Oct 18: MG2; Oct 19: MG2; Oct 20: MG2; Oct 21: MG2; Oct 22: MG2; Dec 02: MG7; Dec 09: MG6; Dec 10: MG6; Dec 11: MG6; Dec 26: MG9; Dec 27: MG9; Dec 28: MG9; Dec 29: MG9; Dec 30: MG9; Jan 03: MG11; Jan 04: MG11; Jan 05: MG11; Jan 06: MG11; Jan 07: MG11; Jan 08: MG11; Jan 09: MG11; Jan 10: MG11
|  | MG11 | #96CEFF | 0 | 3-Jan-25 | 10-Jan-25 | Dec 11: MG8; Dec 12: MG8; Dec 13: MG8; Dec 14: MG8; Dec 15: MG8; Dec 16: MG8; Dec 17: MG8; Dec 18: MG8; Dec 19: MG8; Dec 20: MG8; Dec 21: MG8; Dec 22: MG8; Dec 23: MG8; Dec 24: MG8; Dec 25: MG8; Dec 26: MG8
|  | MG12 | #96CEFF | 0 | 2-Dec-24 | 20-Dec-24
|  | MG2 | #96CEFF | 0 | 16-Oct-24 | 22-Oct-24
|  | MG3 | #96CEFF | 0 | 30-Oct-24 | 12-Nov-24
|  | MG4 | #96CEFF | 0 | 13-Nov-24 | 14-Nov-24
|  | MG5 | #96CEFF | 0 | 15-Nov-24 | 29-Nov-24
|  | MG6 | #96CEFF | 0 | 9-Dec-24 | 11-Dec-24
|  | MG7 | #96CEFF | 0 | 2-Dec-24 | 2-Dec-24
|  | MG8 | #96CEFF | 0 | 11-Dec-24 | 26-Dec-24
|  | MG9 | #96CEFF | 0 | 26-Dec-24 | 30-Dec-24