## Sheet1
CPM
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG | 2024-10-07 08:00 | 2024-10-11 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 1 - MG | 2024-10-09 08:00 | 2024-10-15 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG3 | Overhead MEP Installation - COLO2 Cell 1 - MG | 2024-10-16 08:00 | 2024-10-29 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG4 | Deliver AHU into Mech. Gallery - COLO2 Cell 1 - MG | 2024-10-30 08:00 | 2024-10-31 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG5 | Install Walls and Primer Paint - COLO2 Cell 1 - MG | 2024-11-01 08:00 | 2024-11-14 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG6 | Placing the AHU - COLO2 Cell 1 - MG | 2024-11-22 08:00 | 2024-11-26 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG7 | Layout Ceiling and install Pencile Rod - COLO2 Cell 1 - MG | 2024-11-15 08:00 | 2024-11-15 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG8 | Piping and Electrical Termination to AHUs - COLO2 Cell 1 - MG | 2024-11-26 13:00 | 2024-12-11 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG9 | Pipe Testing - COLO2 Cell 1 - MG | 2024-12-11 13:00 | 2024-12-13 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG10 | Install ceiling and Light Fittings - COLO2 Cell 1 - MG | 2024-12-13 13:00 | 2024-12-26 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG11 | Trim out MEP - COLO2 Cell 1 - MG | 2024-12-18 13:00 | 2024-12-26 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG12 | Post Wall Overhead MEP - COLO2 Cell 1 - MG | 2024-11-15 08:00 | 2024-12-06 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH5 | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH | 2024-12-30 08:00 | 2025-01-20 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH3 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 1 - DH | 2024-10-07 08:00 | 2024-10-22 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH4 | HAC install and Rise - COLO2 Cell 1 - DH | 2024-12-19 08:00 | 2024-12-26 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH2 | Termination at PDU & Busway- COLO2 Cell 1 - DH | 2024-12-19 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH6 | Security Screen Installation - COLO2 Cell 1 - DH | 2024-11-15 08:00 | 2024-11-19 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH7 | Ceiling Grid and Tile - COLO2 Cell 1 - DH | 2024-11-20 08:00 | 2024-11-26 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH8 | Install PDU's - COLO2 Cell 1 - DH | 2024-12-12 08:00 | 2024-12-18 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH9 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 1 - DH | 2024-11-27 08:00 | 2024-12-11 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH10 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 1 - DH | 2024-12-27 08:00 | 2025-01-10 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH11 | HAC Placing - COLO2 Cell 1 - DH | 2024-12-12 08:00 | 2024-12-18 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH12 | Finishes and Signage - COLO2 Cell 1 - DH | 2025-01-14 08:00 | 2025-01-20 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C1 | Interior - L1 UPS - COLO2 Cell 1 | 2025-01-02 08:00 | 2025-01-02 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C2 | Interior - L1 MSB - COLO2 Cell 1 | 2025-01-03 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C3 | Interior - L1 PDUs - COLO2 Cell 1 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C4 | Interior - L1 AHUs - COLO2 Cell 1 | 2025-01-08 08:00 | 2025-01-08 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C5 | Interior - L1 ATSs - COLO2 Cell 1 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C6 | Interior - L1 Busway - COLO2 Cell 1 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C7 | Interior - L1 ADP - COLO2 Cell 1 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C8 | Interior - L2 UPS - COLO2 Cell 1 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C9 | Interior - L2 MSB - COLO2 Cell 1 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C10 | Interior - L2 PDUs - COLO2 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C11 | Interior - L2 AHUs - COLO2 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C12 | Interior - L2 ATSs - COLO2 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C13 | Interior - L2 Busway - COLO2 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C14 | Interior - L2 ADP - COLO2 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C15 | Interior - L3 UPS - COLO2 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C16 | Interior - L3 MSB - COLO2 Cell 1 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C17 | Interior - L3 PDUs - COLO2 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C18 | Interior - L3 AHUs - COLO2 Cell 1 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C19 | Interior - L3 ATSs - COLO2 Cell 1 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C20 | Interior - L3 Busway - COLO2 Cell 1 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C21 | Interior - L3 ADP - COLO2 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER1 | Install Walls and Primer Paint - COLO2 Cell 1 - ER | 2024-10-07 08:00 | 2024-10-18 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER2 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 1 - ER | 2024-10-23 08:00 | 2024-11-05 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER3 | Install Upper Screens - COLO2 Cell 1 - ER | 2024-10-16 08:00 | 2024-10-22 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER4 | Install Ceiling - COLO2 Cell 1 - ER | 2024-11-06 08:00 | 2024-11-08 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER5 | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER | 2024-11-19 08:00 | 2024-12-03 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER6 | Installation of ADP & ATS - COLO2 Cell 1 - ER | 2024-11-29 08:00 | 2024-12-05 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER7 | Installation of UPS Equipment - COLO2 Cell 1 - ER | 2024-12-04 08:00 | 2024-12-10 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER8 | Connet to Cable tray and conduit equipment - COLO2 Cell 1 - ER | 2024-12-03 08:00 | 2024-12-09 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER9 | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | 2024-12-18 08:00 | 2025-01-09 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER10 | Door Frame Installation - COLO2 Cell 1 - ER | 2025-01-03 08:00 | 2025-01-09 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER11 | Finishes and Signage - COLO2 Cell 1 - ER | 2025-01-10 08:00 | 2025-01-16 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER12 | Installation of MSB - COLO2 Cell 1 - ER | 2024-11-29 08:00 | 2024-12-05 17:00
Fitout | COLO 2 Cell 1 Cx L4 | Trade 5 | #FFFFFF | L4 | COLO2 Cx LEV4 - COLO2 | 2025-05-01 08:00 | 2025-06-04 17:00
Fitout | COLO 2 Cell 1 Cx L5 | Trade 5 | #FFFFFF | L5 | COLO2 Cx LEV5 / IST - COLO2 | 2025-06-05 08:00 | 2025-06-06 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 2 - MG | 2024-10-14 08:00 | 2024-10-18 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 2 - MG | 2024-10-16 08:00 | 2024-10-22 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG3 | Overhead MEP Installation - COLO2 Cell 2 - MG | 2024-10-30 08:00 | 2024-11-12 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG4 | Deliver AHU into Mech. Gallery - COLO2 Cell 2 - MG | 2024-11-13 08:00 | 2024-11-14 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG5 | Install Walls and Primer Paint - COLO2 Cell 2 - MG | 2024-11-15 08:00 | 2024-11-29 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG6 | Placing the AHU - COLO2 Cell 2 - MG | 2024-12-09 08:00 | 2024-12-11 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG7 | Layout Ceiling and install Pencile Rod - COLO2 Cell 2 - MG | 2024-12-02 08:00 | 2024-12-02 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG8 | Piping and Electrical Termination to AHUs - COLO2 Cell 2 - MG | 2024-12-11 13:00 | 2024-12-26 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG9 | Pipe Testing - COLO2 Cell 2 - MG | 2024-12-26 13:00 | 2024-12-30 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG10 | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | 2024-12-30 13:00 | 2025-01-10 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG11 | Trim out MEP - COLO2 Cell 2 - MG | 2025-01-03 13:00 | 2025-01-10 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG12 | Post Wall Overhead MEP - COLO2 Cell 2 - MG | 2024-12-02 08:00 | 2024-12-20 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH5 | Install Walls and Primer Paint - COLO2 Cell 2 - ER | 2024-10-21 08:00 | 2024-11-01 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH3 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 2 - ER | 2024-11-06 08:00 | 2024-11-19 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH4 | Install Upper Screens - COLO2 Cell 2 - ER | 2024-10-30 08:00 | 2024-11-05 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH2 | Install Ceiling - COLO2 Cell 2 - ER | 2024-11-20 08:00 | 2024-11-22 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH6 | Below Ceiling MEP Rough In - COLO2 Cell 2 - ER | 2024-12-04 08:00 | 2024-12-17 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH7 | Installation of ADP & ATS - COLO2 Cell 2 - ER | 2024-12-06 08:00 | 2024-12-12 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH8 | Installation of UPS Equipment - COLO2 Cell 2 - ER | 2024-12-11 08:00 | 2024-12-17 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH9 | Connet to Cable tray and conduit equipment - COLO2 Cell 2 - ER | 2024-12-10 08:00 | 2024-12-16 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH10 | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | 2025-01-10 08:00 | 2025-01-30 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH11 | Door Frame Installation - COLO2 Cell 2 - ER | 2025-01-03 08:00 | 2025-01-09 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH12 | Finishes and Signage - COLO2 Cell 2 - ER | 2025-01-28 08:00 | 2025-02-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C1 | Installation of MSB - COLO2 Cell 2 - ER | 2024-12-06 08:00 | 2024-12-12 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C2 | Termination at PDU & Busway - COLO2 Cell 2 - DH | 2025-01-21 08:00 | 2025-02-10 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C3 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 2 - DH | 2024-10-23 08:00 | 2024-11-07 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C4 | HAC install and Rise - COLO2 Cell 2 - DH | 2025-01-06 08:00 | 2025-01-10 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C5 | Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH | 2025-01-06 08:00 | 2025-01-17 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C6 | Security Screen Installation - COLO2 Cell 2 - DH | 2024-12-02 08:00 | 2024-12-04 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C7 | Ceiling Grid and Tile - COLO2 Cell 2 - DH | 2024-12-05 08:00 | 2024-12-11 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C8 | Install PDU's - COLO2 Cell 2 - DH | 2024-12-27 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C9 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 2 - DH | 2024-12-12 08:00 | 2024-12-26 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C10 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 2 - DH | 2025-01-13 08:00 | 2025-01-24 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C11 | HAC Placing - COLO2 Cell 2 - DH | 2024-12-27 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C12 | Finishes and Signage - COLO2 Cell 2 - DH | 2025-02-04 08:00 | 2025-02-10 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C13 | Interior - L1 UPS - COLO2 Cell 2 | 2025-01-02 08:00 | 2025-01-02 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C14 | Interior - L1 MSB - COLO2 Cell 2 | 2025-01-03 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C15 | Interior - L1 PDUs - COLO2 Cell 2 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C16 | Interior - L1 AHUs - COLO2 Cell 2 | 2025-01-08 08:00 | 2025-01-08 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C17 | Interior - L1 ATSs - COLO2 Cell 2 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C18 | Interior - L1 Busway - COLO2 Cell 2 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C19 | Interior - L1 ADP - COLO2 Cell 2 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C20 | Interior - L2 UPS - COLO2 Cell 2 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C21 | Interior - L2 MSB - COLO2 Cell 2 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER1 | Interior - L2 PDUs - COLO2 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER2 | Interior - L2 AHUs - COLO2 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER3 | Interior - L2 ATSs - COLO2 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER4 | Interior - L2 Busway - COLO2 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER5 | Interior - L2 ADP - COLO2 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER6 | Interior - L3 UPS - COLO2 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER7 | Interior - L3 MSB - COLO2 Cell 2 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER8 | Interior - L3 PDUs - COLO2 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER9 | Interior - L3 AHUs - COLO2 Cell 2 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER10 | Interior - L3 ATSs - COLO2 Cell 2 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER11 | Interior - L3 Busway - COLO2 Cell 2 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER12 | Interior - L3 ADP - COLO2 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00

## CFA - Schedule
|  | 2024 | 2024 | [82 empty] | 2025
|  | Oct | Oct | [21 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun
|  | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06
phase | location | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Fitout | COLO 2 Cell 1 Commissioning | Jan 02: C1; Jan 03: C2; Jan 06: C3; Jan 07: C5; Jan 08: C4; Feb 25: C8; Feb 26: C8; Feb 27: C8; Feb 28: C8; Mar 01: C8; Mar 02: C8; Mar 03: C8; Mar 04: C9; Mar 05: C9; Mar 06: C9; Mar 07: C9; Mar 08: C9; Mar 09: C9; Mar 10: C9; Mar 11: C10; Mar 12: C10; Mar 13: C10; Mar 14: C10; Mar 15: C10; Mar 16: C10; Mar 17: C10; Mar 18: C12; Mar 19: C12; Mar 20: C12; Mar 21: C12; Mar 22: C12; Mar 23: C12; Mar 24: C12; Mar 25: C11; Mar 26: C11; Mar 27: C11; Mar 28: C11; Mar 29: C11; Mar 30: C11; Mar 31: C11; Apr 01: C16; Apr 02: C16; Apr 03: C16; Apr 04: C16; Apr 05: C16; Apr 06: C16; Apr 07: C16; Apr 08: C17; Apr 09: C17; Apr 10: C17; Apr 11: C17; Apr 12: C17; Apr 13: C17; Apr 14: C17; Apr 15: C19; Apr 16: C19; Apr 17: C19; Apr 18: C19; Apr 19: C19; Apr 20: C19; Apr 21: C19; Apr 22: C18; Apr 23: C18; Apr 24: C18; Apr 25: C18; Apr 26: C18; Apr 27: C18; Apr 28: C18
[91 empty] | C7 | C6 | [62 empty] | C14 | C14 | C14 | C14 | C14 | C14 | C14 | C13 | C13 | C13 | C13 | C13 | C13 | C13 | C15 | C15 | C15 | C15 | C15 | C15 | C15 | [7 empty] | C21 | C21 | C21 | C21 | C21 | C21 | C21 | C20 | C20 | C20 | C20 | C20 | C20 | C20
| COLO 2 Cell 1 Data Hall | Oct 09: DH3; Oct 10: DH3; Oct 11: DH3; Oct 12: DH3; Oct 13: DH3; Oct 14: DH3; Oct 15: DH3; Oct 16: DH3; Oct 17: DH3; Oct 18: DH3; Oct 19: DH3; Oct 20: DH3; Oct 21: DH3; Oct 22: DH3; Nov 15: DH6; Nov 16: DH6; Nov 17: DH6; Nov 18: DH6; Nov 19: DH6; Nov 20: DH7; Nov 21: DH7; Nov 22: DH7; Nov 23: DH7; Nov 24: DH7; Nov 25: DH7; Nov 26: DH7; Nov 27: DH9; Nov 28: DH9; Nov 29: DH9; Nov 30: DH9; Dec 01: DH9; Dec 02: DH9; Dec 03: DH9; Dec 04: DH9; Dec 05: DH9; Dec 06: DH9; Dec 07: DH9; Dec 08: DH9; Dec 09: DH9; Dec 10: DH9; Dec 11: DH9; Dec 12: DH11; Dec 13: DH11; Dec 14: DH11; Dec 15: DH11; Dec 16: DH11; Dec 17: DH11; Dec 18: DH11; Dec 19: DH4; Dec 20: DH4; Dec 21: DH4; Dec 22: DH4; Dec 23: DH4; Dec 24: DH4; Dec 25: DH4; Dec 26: DH4; Dec 27: DH10; Dec 28: DH10; Dec 29: DH10; Dec 30: DH10; Dec 31: DH10; Jan 01: DH10; Jan 02: DH10; Jan 03: DH10; Jan 04: DH10; Jan 05: DH10; Jan 06: DH10; Jan 07: DH10; Jan 08: DH10; Jan 09: DH10; Jan 10: DH10; Jan 14: DH12; Jan 15: DH12; Jan 16: DH12; Jan 17: DH12; Jan 18: DH12; Jan 19: DH12; Jan 20: DH12
[66 empty] | DH8 | DH8 | DH8 | DH8 | DH8 | DH8 | DH8 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2 | DH2
[84 empty] | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5
| COLO 2 Cell 1 Mech Gallery | Oct 09: MG1; Oct 10: MG1; Oct 11: MG1; Oct 16: MG3; Oct 17: MG3; Oct 18: MG3; Oct 19: MG3; Oct 20: MG3; Oct 21: MG3; Oct 22: MG3; Oct 23: MG3; Oct 24: MG3; Oct 25: MG3; Oct 26: MG3; Oct 27: MG3; Oct 28: MG3; Oct 29: MG3; Oct 30: MG4; Oct 31: MG4; Nov 01: MG5; Nov 02: MG5; Nov 03: MG5; Nov 04: MG5; Nov 05: MG5; Nov 06: MG5; Nov 07: MG5; Nov 08: MG5; Nov 09: MG5; Nov 10: MG5; Nov 11: MG5; Nov 12: MG5; Nov 13: MG5; Nov 14: MG5; Nov 15: MG12; Nov 16: MG12; Nov 17: MG12; Nov 18: MG12; Nov 19: MG12; Nov 20: MG12; Nov 21: MG12; Nov 22: MG12; Nov 23: MG12; Nov 24: MG12; Nov 25: MG12; Nov 26: MG12; Nov 27: MG12; Nov 28: MG12; Nov 29: MG12; Nov 30: MG12; Dec 01: MG12; Dec 02: MG12; Dec 03: MG12; Dec 04: MG12; Dec 05: MG12; Dec 06: MG12; Dec 13: MG10; Dec 14: MG10; Dec 15: MG10; Dec 16: MG10; Dec 17: MG10; Dec 18: MG10; Dec 19: MG10; Dec 20: MG10; Dec 21: MG10; Dec 22: MG10; Dec 23: MG10; Dec 24: MG10; Dec 25: MG10; Dec 26: MG10
|  | MG2 | MG2 | MG2 | MG2 | MG2 | MG2 | MG2 | [30 empty] | MG7 | [6 empty] | MG6 | MG6 | MG6 | MG6 | MG6 | [14 empty] | MG9 | MG9 | MG9 |  |  |  |  | MG11 | MG11 | MG11 | MG11 | MG11 | MG11 | MG11 | MG11 | MG11
[50 empty] | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8
COLO 2 Cell 1 Cx L4 | bar: May 01 to Jun 04
COLO 2 Cell 1 Cx L5 | bar: Jun 05 to Jun 06
| COLO 2 Cell 1 Electrical Room | Oct 09: ER1; Oct 10: ER1; Oct 11: ER1; Oct 12: ER1; Oct 13: ER1; Oct 14: ER1; Oct 15: ER1; Oct 16: ER1; Oct 17: ER1; Oct 18: ER1; Oct 23: ER2; Oct 24: ER2; Oct 25: ER2; Oct 26: ER2; Oct 27: ER2; Oct 28: ER2; Oct 29: ER2; Oct 30: ER2; Oct 31: ER2; Nov 01: ER2; Nov 02: ER2; Nov 03: ER2; Nov 04: ER2; Nov 05: ER2; Nov 06: ER4; Nov 07: ER4; Nov 08: ER4; Nov 29: ER12; Nov 30: ER12; Dec 01: ER12; Dec 02: ER12; Dec 03: ER12; Dec 04: ER12; Dec 05: ER12; Jan 03: ER10; Jan 04: ER10; Jan 05: ER10; Jan 06: ER10; Jan 07: ER10; Jan 08: ER10; Jan 09: ER10; Jan 10: ER11; Jan 11: ER11; Jan 12: ER11; Jan 13: ER11; Jan 14: ER11; Jan 15: ER11; Jan 16: ER11
[9 empty] | ER3 | ER3 | ER3 | ER3 | ER3 | ER3 | ER3 | [27 empty] | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER7 | ER7 | ER7 | ER7 | ER7 | ER7 | ER7 | [7 empty] | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9 | ER9
[53 empty] | ER6 | ER6 | ER6 | ER6 | ER6 | ER6 | ER6
[57 empty] | ER8 | ER8 | ER8 | ER8 | ER8 | ER8 | ER8
| COLO 2 Cell 2 Commissioning | Oct 23: C3; Oct 24: C3; Oct 25: C3; Oct 26: C3; Oct 27: C3; Oct 28: C3; Oct 29: C3; Oct 30: C3; Oct 31: C3; Nov 01: C3; Nov 02: C3; Nov 03: C3; Nov 04: C3; Nov 05: C3; Nov 06: C3; Nov 07: C3; Dec 02: C6; Dec 03: C6; Dec 04: C6; Dec 06: C1; Dec 07: C1; Dec 08: C1; Dec 09: C1; Dec 10: C1; Dec 11: C1; Dec 12: C1; Dec 27: C11; Dec 28: C11; Dec 29: C11; Dec 30: C11; Dec 31: C11; Jan 01: C11; Jan 02: C11; Jan 03: C11; Jan 06: C15; Jan 07: C17; Jan 08: C16; Jan 13: C10; Jan 14: C10; Jan 15: C10; Jan 16: C10; Jan 17: C10; Jan 18: C10; Jan 19: C10; Jan 20: C10; Jan 21: C10; Jan 22: C10; Jan 23: C10; Jan 24: C10; Feb 04: C12; Feb 05: C12; Feb 06: C12; Feb 07: C12; Feb 08: C12; Feb 09: C12; Feb 10: C12; Feb 25: C20; Feb 26: C20; Feb 27: C20; Feb 28: C20; Mar 01: C20; Mar 02: C20; Mar 03: C20; Mar 04: C21; Mar 05: C21; Mar 06: C21; Mar 07: C21; Mar 08: C21; Mar 09: C21; Mar 10: C21
[59 empty] | C7 | C7 | C7 | C7 | C7 | C7 | C7 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | C9 | [6 empty] | C13 | C14 |  |  | C19 | C18 | [13 empty] | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2
[81 empty] | C8 | C8 | C8 | C8 | C8 | C8 | C8 | C8 |  |  | C4 | C4 | C4 | C4 | C4
[91 empty] | C5 | C5 | C5 | C5 | C5 | C5 | C5 | C5 | C5 | C5 | C5 | C5
| COLO 2 Cell 2 Data Hall | Oct 30: DH4; Oct 31: DH4; Nov 01: DH4; Nov 02: DH4; Nov 03: DH4; Nov 04: DH4; Nov 05: DH4; Nov 06: DH3; Nov 07: DH3; Nov 08: DH3; Nov 09: DH3; Nov 10: DH3; Nov 11: DH3; Nov 12: DH3; Nov 13: DH3; Nov 14: DH3; Nov 15: DH3; Nov 16: DH3; Nov 17: DH3; Nov 18: DH3; Nov 19: DH3; Nov 20: DH2; Nov 21: DH2; Nov 22: DH2; Dec 04: DH6; Dec 05: DH6; Dec 06: DH6; Dec 07: DH6; Dec 08: DH6; Dec 09: DH6; Dec 10: DH6; Dec 11: DH6; Dec 12: DH6; Dec 13: DH6; Dec 14: DH6; Dec 15: DH6; Dec 16: DH6; Dec 17: DH6; Jan 03: DH11; Jan 04: DH11; Jan 05: DH11; Jan 06: DH11; Jan 07: DH11; Jan 08: DH11; Jan 09: DH11; Jan 10: DH10; Jan 11: DH10; Jan 12: DH10; Jan 13: DH10; Jan 14: DH10; Jan 15: DH10; Jan 16: DH10; Jan 17: DH10; Jan 18: DH10; Jan 19: DH10; Jan 20: DH10; Jan 21: DH10; Jan 22: DH10; Jan 23: DH10; Jan 24: DH10; Jan 25: DH10; Jan 26: DH10; Jan 27: DH10; Jan 28: DH10; Jan 29: DH10; Jan 30: DH10
[14 empty] | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | DH5 | [34 empty] | DH7 | DH7 | DH7 | DH7 | DH7 | DH7 | DH7 | [46 empty] | DH12 | DH12 | DH12 | DH12 | DH12 | DH12 | DH12
[65 empty] | DH8 | DH8 | DH8 | DH8 | DH8 | DH8 | DH8
[64 empty] | DH9 | DH9 | DH9 | DH9 | DH9 | DH9 | DH9
| COLO 2 Cell 2 Electrical Room | Mar 11: ER1; Mar 12: ER1; Mar 13: ER1; Mar 14: ER1; Mar 15: ER1; Mar 16: ER1; Mar 17: ER1; Mar 18: ER3; Mar 19: ER3; Mar 20: ER3; Mar 21: ER3; Mar 22: ER3; Mar 23: ER3; Mar 24: ER3; Mar 25: ER2; Mar 26: ER2; Mar 27: ER2; Mar 28: ER2; Mar 29: ER2; Mar 30: ER2; Mar 31: ER2; Apr 01: ER7; Apr 02: ER7; Apr 03: ER7; Apr 04: ER7; Apr 05: ER7; Apr 06: ER7; Apr 07: ER7; Apr 08: ER12; Apr 09: ER12; Apr 10: ER12; Apr 11: ER12; Apr 12: ER12; Apr 13: ER12; Apr 14: ER12; Apr 15: ER10; Apr 16: ER10; Apr 17: ER10; Apr 18: ER10; Apr 19: ER10; Apr 20: ER10; Apr 21: ER10; Apr 22: ER9; Apr 23: ER9; Apr 24: ER9; Apr 25: ER9; Apr 26: ER9; Apr 27: ER9; Apr 28: ER9
[155 empty] | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER5 | ER4 | ER4 | ER4 | ER4 | ER4 | ER4 | ER4 | ER6 | ER6 | ER6 | ER6 | ER6 | ER6 | ER6 | [7 empty] | ER8 | ER8 | ER8 | ER8 | ER8 | ER8 | ER8 | ER11 | ER11 | ER11 | ER11 | ER11 | ER11 | ER11
| COLO 2 Cell 2 Mech Gallery | Oct 14: MG1; Oct 15: MG1; Oct 16: MG1; Oct 17: MG1; Oct 18: MG1; Oct 30: MG3; Oct 31: MG3; Nov 01: MG3; Nov 02: MG3; Nov 03: MG3; Nov 04: MG3; Nov 05: MG3; Nov 06: MG3; Nov 07: MG3; Nov 08: MG3; Nov 09: MG3; Nov 10: MG3; Nov 11: MG3; Nov 12: MG3; Nov 13: MG4; Nov 14: MG4; Nov 15: MG5; Nov 16: MG5; Nov 17: MG5; Nov 18: MG5; Nov 19: MG5; Nov 20: MG5; Nov 21: MG5; Nov 22: MG5; Nov 23: MG5; Nov 24: MG5; Nov 25: MG5; Nov 26: MG5; Nov 27: MG5; Nov 28: MG5; Nov 29: MG5; Dec 02: MG12; Dec 03: MG12; Dec 04: MG12; Dec 05: MG12; Dec 06: MG12; Dec 07: MG12; Dec 08: MG12; Dec 09: MG12; Dec 10: MG12; Dec 11: MG12; Dec 12: MG12; Dec 13: MG12; Dec 14: MG12; Dec 15: MG12; Dec 16: MG12; Dec 17: MG12; Dec 18: MG12; Dec 19: MG12; Dec 20: MG12; Dec 30: MG10; Dec 31: MG10; Jan 01: MG10; Jan 02: MG10; Jan 03: MG10; Jan 04: MG10; Jan 05: MG10; Jan 06: MG10; Jan 07: MG10; Jan 08: MG10; Jan 09: MG10; Jan 10: MG10
[9 empty] | MG2 | MG2 | MG2 | MG2 | MG2 | MG2 | MG2 | [40 empty] | MG7 | [6 empty] | MG6 | MG6 | MG6 | [14 empty] | MG9 | MG9 | MG9 | MG9 | MG9 |  |  |  | MG11 | MG11 | MG11 | MG11 | MG11 | MG11 | MG11 | MG11
[65 empty] | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8 | MG8

## CFA - Legends
Fitout
Trade 1
MG1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG
MG10 | Install ceiling and Light Fittings - COLO2 Cell 1 - MG
MG11 | Trim out MEP - COLO2 Cell 1 - MG
MG12 | Post Wall Overhead MEP - COLO2 Cell 1 - MG
MG2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 1 - MG
MG3 | Overhead MEP Installation - COLO2 Cell 1 - MG
MG4 | Deliver AHU into Mech. Gallery - COLO2 Cell 1 - MG
MG5 | Install Walls and Primer Paint - COLO2 Cell 1 - MG
MG6 | Placing the AHU - COLO2 Cell 1 - MG
MG7 | Layout Ceiling and install Pencile Rod - COLO2 Cell 1 - MG
MG8 | Piping and Electrical Termination to AHUs - COLO2 Cell 1 - MG
MG9 | Pipe Testing - COLO2 Cell 1 - MG
Trade 2
DH10 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 1 - DH
DH11 | HAC Placing - COLO2 Cell 1 - DH
DH12 | Finishes and Signage - COLO2 Cell 1 - DH
DH2 | Termination at PDU & Busway- COLO2 Cell 1 - DH
DH3 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 1 - DH
DH4 | HAC install and Rise - COLO2 Cell 1 - DH
DH5 | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH
DH6 | Security Screen Installation - COLO2 Cell 1 - DH
DH7 | Ceiling Grid and Tile - COLO2 Cell 1 - DH
DH8 | Install PDU's - COLO2 Cell 1 - DH
DH9 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 1 - DH
Trade 3
C1 | Interior - L1 UPS - COLO2 Cell 1
C10 | Interior - L2 PDUs - COLO2 Cell 1
C11 | Interior - L2 AHUs - COLO2 Cell 1
C12 | Interior - L2 ATSs - COLO2 Cell 1
C13 | Interior - L2 Busway - COLO2 Cell 1
C14 | Interior - L2 ADP - COLO2 Cell 1
C15 | Interior - L3 UPS - COLO2 Cell 1
C16 | Interior - L3 MSB - COLO2 Cell 1
C17 | Interior - L3 PDUs - COLO2 Cell 1
C18 | Interior - L3 AHUs - COLO2 Cell 1
C19 | Interior - L3 ATSs - COLO2 Cell 1
C2 | Interior - L1 MSB - COLO2 Cell 1
C20 | Interior - L3 Busway - COLO2 Cell 1
C21 | Interior - L3 ADP - COLO2 Cell 1
C3 | Interior - L1 PDUs - COLO2 Cell 1
C4 | Interior - L1 AHUs - COLO2 Cell 1
C5 | Interior - L1 ATSs - COLO2 Cell 1
C6 | Interior - L1 Busway - COLO2 Cell 1
C7 | Interior - L1 ADP - COLO2 Cell 1
C8 | Interior - L2 UPS - COLO2 Cell 1
C9 | Interior - L2 MSB - COLO2 Cell 1
Trade 4
ER1 | Install Walls and Primer Paint - COLO2 Cell 1 - ER
ER10 | Door Frame Installation - COLO2 Cell 1 - ER
ER11 | Finishes and Signage - COLO2 Cell 1 - ER
ER12 | Installation of MSB - COLO2 Cell 1 - ER
ER2 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 1 - ER
ER3 | Install Upper Screens - COLO2 Cell 1 - ER
ER4 | Install Ceiling - COLO2 Cell 1 - ER
ER5 | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER
ER6 | Installation of ADP & ATS - COLO2 Cell 1 - ER
ER7 | Installation of UPS Equipment - COLO2 Cell 1 - ER
ER8 | Connet to Cable tray and conduit equipment - COLO2 Cell 1 - ER
ER9 | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER
Trade 5
L4 | COLO2 Cx LEV4 - COLO2
L5 | COLO2 Cx LEV5 / IST - COLO2