## Sheet1
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish
Sitework | Sitework | Sitework | #F2CEEF | SW | Sitework and Building Prep | 2025-01-06 | 2025-05-01
Structure & Exteriors | Structure & Exteriors | Structure & Exteriors | #F7C7AC | SE | Structure & Exteriors | 2025-05-02 | 2025-01-07
Vertical | Vertical | Vertical | #94DCF8 | VER | Electrical Service Gear, Elevator and Generator | 2024-12-18 | 2026-02-13
Interior | 1st Floor | Interior | #FF7550 | IN | Interior | 2025-05-02 | 2025-11-25
Interior | 2nd Floor | Interior | #FF7550 | IN | Interior | 2025-06-10 | 2025-12-18
Interior | 3rd Floor | Interior | #FF7550 | IN | Interior | 2025-08-14 | 2026-01-18
Interior | 4th Floor | Interior | #FF7550 | IN | Interior | 2025-10-15 | 2026-06-23
Tornover | BLDG | Breeden | #104861 | BT | Building Turnover | 2025-12-06 | 2026-08-06

## CFA - Schedule
|  | 2024 | [13 empty] | 2025 | [364 empty] | 2026
|  | Dec | [13 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06
phase | location | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu
Sitework | Sitework | bar: Jan 06 Mon to May 01 Thu
Structure & Exteriors | Structure & Exteriors
Vertical | Vertical | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER | VER
Interior | 1st Floor | bar: May 02 Fri to Nov 25 Tue
2nd Floor | bar: Jun 10 Tue to Dec 18 Thu
3rd Floor | bar: Aug 14 Thu to Jan 18 Sun
4th Floor | bar: Oct 15 Wed to Jun 23 Tue
Tornover | BLDG | bar: Dec 06 Sat to Aug 06 Thu
Note on V5: Activity Name: Sitework and Building Prep Phase: Sitework Location: Sitework Trade: Sitework Start Date: 06-Jan-2025 End Date: 01-May-2025
Note on C7: Activity Name: Electrical Service Gear, Elevator and Generator Phase: Vertical Location: Vertical Trade: Vertical Start Date: 18-Dec-2024 End Date: 13-Feb-2026
Note on EH8: Activity Name: Interior Phase: Interior Location: 1st Floor Trade: Interior Start Date: 02-May-2025 End Date: 25-Nov-2025
Note on FU9: Activity Name: Interior Phase: Interior Location: 2nd Floor Trade: Interior Start Date: 10-Jun-2025 End Date: 18-Dec-2025
Note on IH10: Activity Name: Interior Phase: Interior Location: 3rd Floor Trade: Interior Start Date: 14-Aug-2025 End Date: 18-Jan-2026
Note on KR11: Activity Name: Interior Phase: Interior Location: 4th Floor Trade: Interior Start Date: 15-Oct-2025 End Date: 23-Jun-2026
Note on MR12: Activity Name: Building Turnover Phase: Tornover Location: BLDG Trade: Breeden Start Date: 06-Dec-2025 End Date: 06-Aug-2026

## CFA - Legends
Sitework |  | Structure & Exteriors |  | Vertical |  | Interior |  | Tornover
Sitework |  | Structure & Exteriors |  | Vertical |  | Interior |  | Breeden
SW | Sitework and Building Prep | SE | Structure & Exteriors | VER | Electrical Service Gear, Elevator and Generator | IN | Interior | BT | Building Turnover