## Metadata
Field | Value
document_id | 4874
document_title | SWA DEN GUB
document_subtitle | INTERNAL Remaining Activities REV 10-3 Startup
issue_date | 2023-09-25T00:00:00Z
created_at | 2024-08-14T14:38:32.147068

## Project Content
parent_id | id | name | duration | start | finish | total_float | scope_of_work | phase | trade | company
N/A | SWA GUB DEN | SWA GUB DEN | 601d | 17-Feb-23 | 16-Jun-25 | 0d
N/A | GUB | GUB | 601d | 17-Feb-23 | 16-Jun-25 | 0d
N/A | Summary | Summary | 533d | 08-May-23 | 16-Jun-25 | 0d
Summary | SUM-DUR-B | Summary - Construction (Calendar Days) | 680d | 08-May-23 | 11-Apr-25 | -43d
Summary | G-MIL-1010 | *Milestone: Construction Substantial Completion (68 0 Calendar Days from Mobilization) | 0d | 11-Apr-25 |  | -31d
Summary | G-SUM-DUR-B10 | Summary - Construction (Work Days) | 472d | 08-May-23 | 11-Apr-25 | -31d
Summary | G-CON-6870 | *Milestone: Beneficial Occupancy | 0d | 02-May-25 |  | 30d
Summary | G-CON-6880 | *Milestone: Final Completion | 0d | 16-Jun-25 |  | 0d
N/A | Milestones | Milestones | 275d | 23-Oct-23 | 20-Nov-24 | 20d
Milestones | G-MIL-2000 | *Milestone: Building Pad Certified Complete / Ready for Drilled Piers | 0d | 23-Oct-23 |  | -14d
Milestones | G-MIL-3010 | *Milestone: Drilled Pier Start | 0d | 24-Oct-23 |  | -25d
Milestones | G-MIL-3020 | *Milestone: Grade Beam Start | 0d | 16-Nov-23 |  | -30d
Milestones | G-MIL-3030 | *Milestone: SOG Start | 0d | 19-Dec-23 |  | -24d
Milestones | G-MIL-3040 | *Milestone: Tilt Wall Start | 0d | 23-Jan-24 |  | -25d
Milestones | G-MIL-2020 | *Milestone: Tilt Complete (Last Panel Erection) | 0d | 10-May-24 |  | -25d
Milestones | G-MIL-3050 | *Milestone: Structural Steel Start | 0d | 15-May-24 |  | -27d
Milestones | G-MIL-2040 | *Milestone: Steel Complete | 0d | 04-Jun-24 |  | -5d
Milestones | G-MIL-3060 | *Milestone: Interior Fit-Out Start | 0d | 17-Jun-24 |  | -1d
Milestones | G-MIL-2030 | *Milestone: Building Dry-In | 0d | 27-Aug-24 |  | 4d
Milestones | G-MIL-2010 | *Milestone: SOGs Complete | 0d | 03-Sep-24 |  | -6d
Milestones | G-MIL-2060 | *Milestone: Permanent Power Established | 0d | 20-Nov-24 |  | 20d
N/A | Preconstruction & Design | Preconstruction & Design | 463d | 17-Feb-23 | 27-Nov-24 | 21d
N/A | Design | Design | 395d | 02-May-23 | 27-Nov-24 | 21d
Design | G-PRECN-1180 | Ghafari - Design - 100% (After Permit Review) | 10d | 09-Oct-23 | 20-Oct-23 | 12d
N/A | FRAGNET 02 - Drawing Release 07 & 16 | FRAGNET 02 - Drawing Release 07 & 16 | 26d | 22-Sep-23 | 30-Oct-23 | 195d
FRAGNET 02 - Drawing Release 07 & 16 | G-FRG-02-1020 | Owner Review and Approval - DR 07 & 16 | 15d | 22-Sep-23 | 26-Sep-23 | 209d
FRAGNET 02 - Drawing Release 07 & 16 | G-FRG-02-1030 | Additional Site Storm Drain - DR 07 & 16 | 10d | 17-Oct-23 | 30-Oct-23 | 195d
N/A | FRAGNET 05 - Drawing Release 11 | FRAGNET 05 - Drawing Release 11 | 313d | 04-May-23 | 02-Aug-24 | -14d
FRAGNET 05 - Drawing Release 11 | G-FRG-05-1010 | McCarthy Develop Pricing - DR 11 | 20d | 04-May-23 | 28-Sep-23 | 160d
FRAGNET 05 - Drawing Release 11 | G-FRG-05-1020 | Owner Review and Approval - DR 11 | 15d | 29-Sep-23 | 19-Oct-23 | 160d
FRAGNET 05 - Drawing Release 11 | G-FRG-05-1030 | Additional Electrical Overhead Conduit - DR 11 | 5d | 09-Jul-24 | 15-Jul-24 | -21d
FRAGNET 05 - Drawing Release 11 | G-FRG-05-1040 | Additional Electrical In-Wall Conduit - DR 11 | 5d | 29-Jul-24 | 02-Aug-24 | -14d
N/A | FRAGNET 04 - Drawing Release 10 | FRAGNET 04 - Drawing Release 10 | 113d | 02-May-23 | 19-Oct-23 | -5d
FRAGNET 04 - Drawing Release 10 | G-FRG-04-1010 | McCarthy Develop Pricing - DR 10 | 20d | 02-May-23 | 28-Sep-23 | -5d
FRAGNET 04 - Drawing Release 10 | G-FRG-04-1020 | Owner Review and Approval - DR 10 | 15d | 29-Sep-23 | 19-Oct-23 | -5d
N/A | FRAGNET 06 - Drawing Release 12 | FRAGNET 06 - Drawing Release 12 | 393d | 15-May-23 | 27-Nov-24 | 21d
FRAGNET 06 - Drawing Release 12 | G-FRG-06-1010 | McCarthy Develop Pricing - DR 12 | 20d | 15-May-23 | 03-Oct-23 | -10d
FRAGNET 06 - Drawing Release 12 | G-FRG-06-1020 | Owner Review and Approval - DR 12 | 15d | 04-Oct-23 | 24-Oct-23 | -10d
FRAGNET 06 - Drawing Release 12 | G-FRG-06-1030 | Additional Tilt Panel Shop Drawings - DR 12 | 15d | 25-Oct-23 | 14-Nov-23 | -10d
FRAGNET 06 - Drawing Release 12 | G-FRG-06-1040 | Additional Tilt Panel Embeds - DR 12 | 2d | 23-Feb-24 | 26-Feb-24 | 8d
FRAGNET 06 - Drawing Release 12 | G-FRG-06-1050 | Additional Steel Erection - DR 12 | 2d | 22-May-24 | 23-May-24 | -29d
FRAGNET 06 - Drawing Release 12 | G-FRG-06-1080 | Additional Framing in Adim / Entry - DR 12 | 3d | 29-Jul-24 | 31-Jul-24 | -23d
FRAGNET 06 - Drawing Release 12 | G-FRG-06-1060 | Additional Time for Exterior Doors - DR 12 | 2d | 18-Sep-24 | 19-Sep-24 | 35d
FRAGNET 06 - Drawing Release 12 | G-FRG-06-1070 | Additional Time for Stair Erection - DR 12 | 2d | 26-Nov-24 | 27-Nov-24 | 21d
N/A | FRAGNET 08 - Drawing Release 15 | FRAGNET 08 - Drawing Release 15 | 15d | 22-Sep-23 | 26-Sep-23 | 38d
FRAGNET 08 - Drawing Release 15 | G-FRG-08-1020 | Owner Review and Approval - DR 15 | 15d | 22-Sep-23 | 26-Sep-23 | 38d
N/A | GMP | GMP | 25d | 23-Oct-23 | 28-Nov-23 | 12d
N/A | Final GMP | Final GMP | 25d | 23-Oct-23 | 28-Nov-23 | 12d
Final GMP | G-PRECN-1130 | Pricing Confirmation After 100% | 25d | 23-Oct-23 | 28-Nov-23 | 12d
N/A | Permitting | Permitting | 180d | 17-Feb-23 | 18-Oct-23 | 14d
N/A | Water | Water | 170d | 17-Feb-23 | 04-Oct-23 | 14d
Water | G-PRECN-1240 | Denver Water - Permit - Water (Includes DFD) (Neede d by 8/15/23) | 90d | 17-Feb-23 | 29-Sep-23 | 14d
Water | G-PRECN-6230 | DEN - LNTP (Water) | 3d | 02-Oct-23 | 04-Oct-23 | 14d
N/A | FRAGNET 10 - Water Permit | FRAGNET 10 - Water Permit | 10d | 15-Aug-23 | 29-Sep-23 | 14d
FRAGNET 10 - Water Permit | FRG-10-1010 | Additional Time for Water Permit - Driving Construc tion Install | 10d | 15-Aug-23 | 29-Sep-23 | 14d
N/A | Building | Building | 40d | 04-Aug-23 | 18-Oct-23 | 14d
Building | G-PRECN-1070 | CCD / DEN - Permit - 90% CDs - Building Permit (Nee ded by 9/5/23) | 40d | 04-Aug-23 | 13-Oct-23 | -6d
Building | G-PRECN-6280 | DOTI - Permit - SUDP (Building) (Needed by 9/5/23) | 40d | 04-Aug-23 | 13-Oct-23 | -6d
Building | G-PRECN-6250 | DEN - FNTP | 3d | 16-Oct-23 | 18-Oct-23 | 14d
N/A | Procurement | Procurement | 383d | 28-Apr-23 | 29-Oct-24 | 46d
N/A | Subcontracts | Subcontracts | 60d | 28-Apr-23 | 13-Oct-23 | 133d
N/A | Priority 1 | Priority 1 | 30d | 28-Apr-23 | 06-Oct-23 | 77d
Priority 1 | G-SUB-1050 | Contract - Glass / Storefront | 20d | 28-Apr-23 | 06-Oct-23 | 77d
Priority 1 | G-SUB-1160 | Contract - Paint Booth | 30d | 28-Apr-23 | 06-Oct-23 | 11d
Priority 1 | G-SUB-1360 | Contract - Eaton Fluid System | 30d | 28-Apr-23 | 06-Oct-23 | 29d
N/A | Priority 2 | Priority 2 | 40d | 28-Apr-23 | 06-Oct-23 | 138d
Priority 2 | G-SUB-1300 | Contract - Doors & Hardware | 40d | 28-Apr-23 | 25-Sep-23 | 29d
Priority 2 | G-SUB-1290 | Contract - Warehouse Racking | 40d | 28-Apr-23 | 06-Oct-23 | 138d
N/A | Priority 3 | Priority 3 | 60d | 28-Apr-23 | 13-Oct-23 | 102d
Priority 3 | G-SUB-1350 | Contract - Illuminated Signage | 60d | 28-Apr-23 | 13-Oct-23 | 102d
N/A | Submittals | Submittals | 372d | 30-May-23 | 29-Oct-24 | 46d
N/A | VFDs | VFDs | 162d | 21-Jul-23 | 11-Mar-24 | 43d
VFDs | G-PR-23-1040 | Submittal Prep - VFDs | 60d | 21-Jul-23 | 14-Nov-23 | 32d
VFDs | G-PR-23-1050 | McC Review - VFDs | 5d | 15-Nov-23 | 21-Nov-23 | 32d
VFDs | G-PR-23-1060 | A/E Review & Approve - VFDs | 10d | 22-Nov-23 | 07-Dec-23 | 32d
VFDs | G-PR-23-1070 | Fab & Deliver - VFDs | 65d | 08-Dec-23 | 11-Mar-24 | 43d
N/A | Mechanical - AHUs - Aaon | Mechanical - AHUs - Aaon | 272d | 21-Jul-23 | 14-Aug-24 | -1d
Mechanical - AHUs - Aaon | G-PR-23-1000 | Submittal Prep - AHUs - Aaon | 60d | 21-Jul-23 | 14-Nov-23 | -1d
Mechanical - AHUs - Aaon | G-PR-23-1010 | McC Review - AHUs - Aaon | 5d | 15-Nov-23 | 21-Nov-23 | -1d
Mechanical - AHUs - Aaon | G-PR-23-1020 | A/E Review & Approve - AHUs - Aaon | 10d | 22-Nov-23 | 07-Dec-23 | -1d
Mechanical - AHUs - Aaon | G-PR-23-1030 | Fab & Deliver - AHUs - Aaon | 175d | 08-Dec-23 | 14-Aug-24 | -1d
N/A | Mechanical - AHUs - Rapid Engineering | Mechanical - AHUs - Rapid Engineering | 248d | 23-Jun-23 | 26-Jun-24 | 33d
Mechanical - AHUs - Rapid Engineering | G-PR-23-1460 | Submittal Prep - AHUs - Rapid Engineering | 10d | 23-Jun-23 | 30-Jan-24 | 33d
Mechanical - AHUs - Rapid Engineering | G-PR-23-1470 | McC Review - AHUs - Rapid Engineering | 5d | 31-Jan-24 | 06-Feb-24 | 33d
Mechanical - AHUs - Rapid Engineering | G-PR-23-1480 | A/E Review & Approve - AHUs - Rapid Engineering | 10d | 07-Feb-24 | 20-Feb-24 | 33d
Mechanical - AHUs - Rapid Engineering | G-PR-23-1450 | Fab & Deliver - AHUs - Rapid Engineering | 90d | 21-Feb-24 | 26-Jun-24 | 33d
N/A | Mechanical - Computer AC Units | Mechanical - Computer AC Units | 250d | 21-Jul-23 | 15-Jul-24 | 37d
Mechanical - Computer AC Units | G-PR-23-1210 | Submittal Prep - Computer AC Units | 50d | 21-Jul-23 | 13-Oct-23 | 37d
Mechanical - Computer AC Units | G-PR-23-1220 | McC Review - Computer AC Units | 5d | 16-Oct-23 | 20-Oct-23 | 37d
Mechanical - Computer AC Units | G-PR-23-1230 | A/E Review & Approve - Computer AC Units | 10d | 23-Oct-23 | 03-Nov-23 | 37d
Mechanical - Computer AC Units | G-PR-23-1200 | Fab & Deliver - Computer AC Units | 175d | 06-Nov-23 | 15-Jul-24 | 37d
N/A | Mechanical - Gas Fired Boiler | Mechanical - Gas Fired Boiler | 125d | 21-Jul-23 | 18-Jan-24 | 74d
Mechanical - Gas Fired Boiler | G-PR-23-1330 | Submittal Prep - Gas Fired Boiler | 60d | 21-Jul-23 | 20-Oct-23 | 49d
Mechanical - Gas Fired Boiler | G-PR-23-1340 | McC Review - Gas Fired Boiler | 5d | 23-Oct-23 | 27-Oct-23 | 49d
Mechanical - Gas Fired Boiler | G-PR-23-1350 | A/E Review & Approve - Gas Fired Boiler | 10d | 30-Oct-23 | 10-Nov-23 | 49d
Mechanical - Gas Fired Boiler | G-PR-23-1320 | Fab & Deliver - Gas Fired Boiler | 45d | 13-Nov-23 | 18-Jan-24 | 74d
N/A | Mechanical - Roof Fans | Mechanical - Roof Fans | 185d | 21-Jul-23 | 11-Apr-24 | 86d
Mechanical - Roof Fans | G-PR-23-1500 | Submittal Prep - Roof Fans | 60d | 21-Jul-23 | 05-Dec-23 | 86d
Mechanical - Roof Fans | G-PR-23-1510 | McC Review - Roof Fans | 5d | 06-Dec-23 | 12-Dec-23 | 86d
Mechanical - Roof Fans | G-PR-23-1520 | A/E Review & Approve - Roof Fans | 10d | 13-Dec-23 | 27-Dec-23 | 86d
Mechanical - Roof Fans | G-PR-23-1490 | Fab & Deliver - Roof Fans | 75d | 28-Dec-23 | 11-Apr-24 | 86d
N/A | Controls | Controls | 183d | 21-Jul-23 | 09-Apr-24 | 22d
Controls | G-PR-22-1000 | Submittal Prep - Controls | 60d | 21-Jul-23 | 22-Nov-23 | 22d
Controls | G-PR-22-1010 | McC Review - Controls | 5d | 27-Nov-23 | 01-Dec-23 | 22d
Controls | G-PR-22-1020 | A/E Review & Approve - Controls | 10d | 04-Dec-23 | 15-Dec-23 | 22d
Controls | G-PR-22-1030 | Fab & Deliver - Controls | 80d | 18-Dec-23 | 09-Apr-24 | 22d
N/A | Utilities - Concrete Manholes & Inlets | Utilities - Concrete Manholes & Inlets | 25d | 05-Sep-23 | 29-Sep-23 | 14d
Utilities - Concrete Manholes & Inlets | G-PR-31-2310 | Fab & Deliver - Utilities - Concrete Manholes & Inl ets | 25d | 05-Sep-23 | 29-Sep-23 | 14d
N/A | Utilities - Water | Utilities - Water | 5d | 02-Oct-23 | 06-Oct-23 | 27d
Utilities - Water | G-PR-31-1030 | Fab & Deliver - Underground Utilities - Water | 5d | 02-Oct-23 | 06-Oct-23 | 27d
N/A | Utilities - Storm / Sewer / Fire / Etc. | Utilities - Storm / Sewer / Fire / Etc. | 15d | 05-Sep-23 | 29-Sep-23 | 8d
Utilities - Storm / Sewer / Fire / Etc. | G-PR-31-1280 | Fab & Deliver - Underground Utilities - Storm / Sew er | 15d | 05-Sep-23 | 29-Sep-23 | 8d
N/A | Electrical - SWB | Electrical - SWB | 270d | 01-Jun-23 | 28-Jun-24 | 77d
Electrical - SWB | G-PR-26-1030 | Fab & Deliver - Electrical - SCC-101 (Connection to Xcel) | 270d | 01-Jun-23 | 28-Jun-24 | 77d
N/A | Electrical - SWB 3000A | Electrical - SWB 3000A | 300d | 01-Jun-23 | 12-Aug-24 | 28d
Electrical - SWB 3000A | G-PR-26-1450 | Fab & Deliver - Electrical - Emergency Switchboard EDP-2M-101 | 270d | 01-Jun-23 | 28-Jun-24 | 58d
Electrical - SWB 3000A | G-PR-26-1120 | Fab & Deliver - Electrical - SWB-2M-101 3000A Main | 300d | 01-Jun-23 | 12-Aug-24 | 23d
N/A | Electrical - Panels | Electrical - Panels | 270d | 01-Jun-23 | 21-Jun-24 | 58d
Electrical - Panels | G-PR-26-1160 | Fab & Deliver - Electrical - Panels | 150d | 01-Jun-23 | 04-Jan-24 | 178d
Electrical - Panels | G-PR-26-1540 | Fab & Deliver - Electrical - Emergency Panels | 270d | 01-Jun-23 | 21-Jun-24 | 58d
N/A | Electrical - Transformers | Electrical - Transformers | 45d | 01-Jun-23 | 23-Oct-23 | 227d
Electrical - Transformers | G-PR-26-1200 | Fab & Deliver - Electrical - Transformers | 45d | 01-Jun-23 | 23-Oct-23 | 227d
N/A | Electrical - Transformer Vault | Electrical - Transformer Vault | 60d | 25-Sep-23 | 19-Dec-23 | 207d
Electrical - Transformer Vault | G-PR-26-1570 | McC Review - Electrical - Transformer Vault | 5d | 25-Sep-23 | 29-Sep-23 | 207d
Electrical - Transformer Vault | G-PR-26-1580 | A/E Review & Approve - Electrical - Transformer Vau lt | 10d | 02-Oct-23 | 13-Oct-23 | 207d
Electrical - Transformer Vault | G-PR-26-1550 | Fab & Deliver - Electrical - Transformer Vault | 45d | 16-Oct-23 | 19-Dec-23 | 207d
N/A | Electrical - Generator | Electrical - Generator | 300d | 30-May-23 | 01-Aug-24 | 88d
Electrical - Generator | G-PR-26-1240 | Fab & Deliver - Electrical - Generator (Tier 4 - 58 Weeks) | 300d | 30-May-23 | 01-Aug-24 | 88d
N/A | Electrical - ATS Switch Cabinet | Electrical - ATS Switch Cabinet | 300d | 01-Jun-23 | 05-Aug-24 | 86d
Electrical - ATS Switch Cabinet | G-PR-26-1320 | Fab & Deliver - Electrical - ATS / MTS Switches | 300d | 01-Jun-23 | 05-Aug-24 | 86d
N/A | Electrical - Distribution Board | Electrical - Distribution Board | 270d | 01-Jun-23 | 21-Jun-24 | 63d
Electrical - Distribution Board | G-PR-26-1360 | Fab & Deliver - Electrical - Distribution Board DP- 2D-101 | 270d | 01-Jun-23 | 21-Jun-24 | 63d
Electrical - Distribution Board | G-PR-26-1400 | Fab & Deliver - Electrical - Distribution Board DP- 16M-101 | 270d | 01-Jun-23 | 21-Jun-24 | 63d
N/A | Electrical Conduit & Wire | Electrical Conduit & Wire | 105d | 21-Jul-23 | 19-Dec-23 | 160d
Electrical Conduit & Wire | G-PR-26-1050 | Submittal Prep - Interior Conduit & Wire | 60d | 21-Jul-23 | 27-Oct-23 | 160d
Electrical Conduit & Wire | G-PR-26-1060 | McC Review - Interior Conduit & Wire | 5d | 30-Oct-23 | 03-Nov-23 | 160d
Electrical Conduit & Wire | G-PR-26-1070 | A/E Review & Approve - Interior Conduit & Wire | 10d | 06-Nov-23 | 17-Nov-23 | 160d
Electrical Conduit & Wire | G-PR-26-1040 | Fab & Deliver - Interior Conduit & Wire | 20d | 20-Nov-23 | 19-Dec-23 | 160d
N/A | Electrical Underground Conduit & Wire | Electrical Underground Conduit & Wire | 80d | 23-Jun-23 | 24-Oct-23 | -27d
Electrical Underground Conduit & Wire | G-PR-26-1300 | McC Review - Underground Conduit & Wire | 5d | 23-Jun-23 | 26-Sep-23 | -27d
Electrical Underground Conduit & Wire | G-PR-26-1310 | A/E Review & Approve - Underground Conduit & Wire | 10d | 27-Sep-23 | 10-Oct-23 | -27d
Electrical Underground Conduit & Wire | G-PR-26-1280 | Fab & Deliver - Underground Conduit & Wire | 10d | 11-Oct-23 | 24-Oct-23 | -27d
N/A | Warehouse Lighting | Warehouse Lighting | 45d | 25-Sep-23 | 28-Nov-23 | 188d
Warehouse Lighting | G-PR-26-1610 | McC Review - Warehouse Lighting | 5d | 25-Sep-23 | 29-Sep-23 | 188d
Warehouse Lighting | G-PR-26-1620 | A/E Review & Approve - Warehouse Lighting | 10d | 02-Oct-23 | 13-Oct-23 | 188d
Warehouse Lighting | G-PR-26-1590 | Fab & Deliver - Warehouse Lighting | 30d | 16-Oct-23 | 28-Nov-23 | 188d
N/A | Security / Low Voltage / Comms | Security / Low Voltage / Comms | 312d | 21-Jul-23 | 10-Oct-24 | 6d
Security / Low Voltage / Comms | G-PR-31-1930 | Submittal Prep - Security - DEN (Servitech) | 35d | 21-Jul-23 | 10-Oct-23 | 6d
Security / Low Voltage / Comms | G-PR-31-1940 | McC Review - Security - DEN (Servitech) | 5d | 11-Oct-23 | 17-Oct-23 | 6d
Security / Low Voltage / Comms | G-PR-31-1950 | A/E Review & Approve - Security - DEN (Servitech) | 10d | 18-Oct-23 | 31-Oct-23 | 6d
Security / Low Voltage / Comms | G-PR-31-1920 | Fab & Deliver - Security - DEN (Servitech) | 240d | 01-Nov-23 | 10-Oct-24 | 6d
N/A | Underground Plumbing Pipe | Underground Plumbing Pipe | 20d | 27-Oct-23 | 27-Nov-23 | -30d
Underground Plumbing Pipe | G-PR-26-1080 | Fab & Deliver - Underground Plumbing Pipe | 20d | 27-Oct-23 | 27-Nov-23 | -30d
N/A | Security - Card Readers | Security - Card Readers | 215d | 25-Sep-23 | 29-Jul-24 | 47d
Security - Card Readers | G-PR-31-2270 | McC Review - Security - SWA (Convergent) | 5d | 25-Sep-23 | 29-Sep-23 | 47d
Security - Card Readers | G-PR-31-2280 | A/E Review & Approve - Security - SWA (Convergent) | 10d | 02-Oct-23 | 13-Oct-23 | 47d
Security - Card Readers | G-PR-31-2290 | Fab & Deliver - Security - SWA (Convergent) | 200d | 16-Oct-23 | 29-Jul-24 | 47d
N/A | Fire Supression | Fire Supression | 203d | 14-Jul-23 | 30-Apr-24 | 1d
Fire Supression | G-PR-23-1360 | BIM - Fire Supression | 30d | 14-Jul-23 | 22-Nov-23 | 1d
Fire Supression | G-PR-23-1090 | Submittal Prep - Fire Supression | 25d | 27-Nov-23 | 02-Jan-24 | 1d
Fire Supression | G-PR-23-1100 | McC Review - Fire Supression | 5d | 03-Jan-24 | 09-Jan-24 | 1d
Fire Supression | G-PR-23-1110 | A/E Review & Approve - Fire Supression | 10d | 10-Jan-24 | 23-Jan-24 | 1d
Fire Supression | G-PRECN-6400 | Deferred Submittal - Fire Supression | 60d | 24-Jan-24 | 16-Apr-24 | 1d
Fire Supression | G-PR-23-1080 | Fab & Deliver - Fire Supression | 10d | 17-Apr-24 | 30-Apr-24 | 1d
N/A | Fire Pump | Fire Pump | 160d | 15-Aug-23 | 01-Apr-24 | 122d
Fire Pump | G-PR-23-1380 | Submittal Prep - Fire Pump | 35d | 15-Aug-23 | 17-Oct-23 | -7d
Fire Pump | G-PR-23-1390 | McC Review - Fire Pump | 5d | 18-Oct-23 | 24-Oct-23 | 122d
Fire Pump | G-PR-23-1400 | A/E Review & Approve - Fire Pump | 10d | 25-Oct-23 | 07-Nov-23 | 122d
Fire Pump | G-PR-23-1370 | Fab & Deliver - Fire Pump | 100d | 08-Nov-23 | 01-Apr-24 | 122d
N/A | ZRF Fire Sprinkler Head | ZRF Fire Sprinkler Head | 179d | 15-Aug-23 | 26-Apr-24 | 84d
ZRF Fire Sprinkler Head | G-PR-23-1420 | Submittal Prep - ZRF Fire Sprinkler Head | 60d | 15-Aug-23 | 13-Dec-23 | 84d
ZRF Fire Sprinkler Head | G-PR-23-1430 | McC Review - ZRF Fire Sprinkler Head | 5d | 14-Dec-23 | 20-Dec-23 | 84d
ZRF Fire Sprinkler Head | G-PR-23-1440 | A/E Review & Approve - ZRF Fire Sprinkler Head | 10d | 21-Dec-23 | 05-Jan-24 | 84d
ZRF Fire Sprinkler Head | G-PR-23-1410 | Fab & Deliver - ZRF Fire Sprinkler Head | 80d | 08-Jan-24 | 26-Apr-24 | 84d
N/A | Fire Alarm | Fire Alarm | 205d | 21-Jul-23 | 09-May-24 | 110d
Fire Alarm | G-PR-23-1130 | Submittal Prep - Fire Alarm | 60d | 21-Jul-23 | 27-Oct-23 | 110d
Fire Alarm | G-PR-23-1140 | McC Review - Fire Alarm | 5d | 30-Oct-23 | 03-Nov-23 | 110d
Fire Alarm | G-PR-23-1150 | A/E Review & Approve - Fire Alarm | 10d | 06-Nov-23 | 17-Nov-23 | 110d
Fire Alarm | G-PRECN-6420 | Deferred Submittal - Fire Alarm & Signaling | 60d | 20-Nov-23 | 15-Feb-24 | 110d
Fire Alarm | G-PRECN-6430 | Deferred Submittal - Fire Alarm & Signaling: Zinwav e (Radio Enhansement System) | 60d | 20-Nov-23 | 15-Feb-24 | 110d
Fire Alarm | G-PR-23-1120 | Fab & Deliver - Fire Alarm | 60d | 16-Feb-24 | 09-May-24 | 110d
N/A | Concrete Mix Design - Grade Beams & Pier Caps | Concrete Mix Design - Grade Beams & Pier Caps | 41d | 30-Aug-23 | 26-Oct-23 | -17d
Concrete Mix Design - Grade Beams & Pier Caps | G-PR-31-1140 | McC Review - Concrete Mix Design - Grade Beams & Pi er Caps | 3d | 30-Aug-23 | 05-Oct-23 | -17d
Concrete Mix Design - Grade Beams & Pier Caps | G-PR-31-1150 | A/E Review & Approve - Concrete Mix Design - Grade Beams & Pier Caps | 10d | 06-Oct-23 | 19-Oct-23 | -17d
Concrete Mix Design - Grade Beams & Pier Caps | G-PR-31-1120 | Fab & Deliver - Concrete - Grade Beams & Pier Caps | 5d | 20-Oct-23 | 26-Oct-23 | -17d
N/A | Concrete Mix Design - SOG / SOD | Concrete Mix Design - SOG / SOD | 41d | 30-Aug-23 | 26-Oct-23 | 28d
Concrete Mix Design - SOG / SOD | G-PR-31-2660 | McC Review - Concrete Mix Design - SOG / SOD | 3d | 30-Aug-23 | 05-Oct-23 | 28d
Concrete Mix Design - SOG / SOD | G-PR-31-2670 | A/E Review & Approve - Concrete Mix Design - SOG / SOD | 10d | 06-Oct-23 | 19-Oct-23 | 28d
Concrete Mix Design - SOG / SOD | G-PR-31-2640 | Fab & Deliver - Concrete - SOG / SOD | 5d | 20-Oct-23 | 26-Oct-23 | 28d
N/A | Concrete Mix Design - Tilt Panels | Concrete Mix Design - Tilt Panels | 41d | 30-Aug-23 | 26-Oct-23 | 31d
Concrete Mix Design - Tilt Panels | G-PR-31-2700 | McC Review - Concrete Mix Design - Tilt Panels | 3d | 30-Aug-23 | 05-Oct-23 | 31d
Concrete Mix Design - Tilt Panels | G-PR-31-2710 | A/E Review & Approve - Concrete Mix Design - Tilt P anels | 10d | 06-Oct-23 | 19-Oct-23 | 31d
Concrete Mix Design - Tilt Panels | G-PR-31-2680 | Fab & Deliver - Concrete - Tilt Panels | 5d | 20-Oct-23 | 26-Oct-23 | 31d
N/A | Drilled Piers | Drilled Piers | 10d | 06-Oct-23 | 19-Oct-23 | -31d
Drilled Piers | G-PR-31-2200 | Fab & Deliver - Drilled Piers | 10d | 06-Oct-23 | 19-Oct-23 | -31d
N/A | Rebar Shop Dwgs - Grade Beams | Rebar Shop Dwgs - Grade Beams | 50d | 24-Aug-23 | 02-Nov-23 | -22d
Rebar Shop Dwgs - Grade Beams | G-PR-31-1180 | McC Review - Rebar Shop Dwgs - Grade Beams | 5d | 24-Aug-23 | 05-Oct-23 | -22d
Rebar Shop Dwgs - Grade Beams | G-PR-31-1190 | A/E Review & Approve - Rebar Shop Dwgs - Grade Beam s | 10d | 06-Oct-23 | 19-Oct-23 | -22d
Rebar Shop Dwgs - Grade Beams | G-PR-31-1160 | Fab & Deliver - Rebar - Grade Beams | 10d | 20-Oct-23 | 02-Nov-23 | -22d
N/A | Tilt Panels | Tilt Panels | 10d | 21-Sep-23 | 06-Oct-23 | 17d
Tilt Panels | G-PR-31-2470 | A/E Review & Approve - Tilt Panels (Product Data) | 10d | 21-Sep-23 | 06-Oct-23 | 17d
N/A | SOG & Grade Beams - Anchor Bolts & Embeds | SOG & Grade Beams - Anchor Bolts & Embeds | 45d | 21-Jul-23 | 17-Nov-23 | 5d
SOG & Grade Beams - Anchor Bolts & Embeds | G-PR-05-1320 | Fab & Deliver - SOG & Grade Beams Anchor Bolts & Em beds | 45d | 21-Jul-23 | 17-Nov-23 | 5d
N/A | Tilt Panel - Embeds | Tilt Panel - Embeds | 45d | 15-Aug-23 | 01-Dec-23 | 9d
Tilt Panel - Embeds | G-PR-05-1360 | Fab & Deliver - Tilt Panels Embeds | 45d | 15-Aug-23 | 01-Dec-23 | 9d
N/A | Structural Steel - Joists & Decking | Structural Steel - Joists & Decking | 155d | 21-Jul-23 | 29-Feb-24 | 26d
Structural Steel - Joists & Decking | G-PR-05-1010 | McC Review - Steel Joists & Decking | 6d | 21-Jul-23 | 20-Oct-23 | -23d
Structural Steel - Joists & Decking | G-PR-05-1020 | A/E Review & Approve - Steel Joists & Decking | 10d | 23-Oct-23 | 03-Nov-23 | -23d
Structural Steel - Joists & Decking | G-PR-05-1030 | Fab & Deliver - Steel Joists & Decking | 80d | 06-Nov-23 | 29-Feb-24 | 26d
N/A | Structural Steel - Columns & Beams | Structural Steel - Columns & Beams | 113d | 22-Sep-23 | 29-Feb-24 | 20d
Structural Steel - Columns & Beams | G-PR-05-1250 | McC Review - Columns & Beams | 10d | 22-Sep-23 | 20-Oct-23 | 20d
Structural Steel - Columns & Beams | G-PR-05-1260 | A/E Review & Approve - Columns & Beams | 10d | 23-Oct-23 | 03-Nov-23 | 20d
Structural Steel - Columns & Beams | G-PR-05-1270 | Fab & Deliver - Columns & Beams | 80d | 06-Nov-23 | 29-Feb-24 | 20d
N/A | Insulated Core Metal Panels | Insulated Core Metal Panels | 134d | 28-Aug-23 | 07-Mar-24 | 100d
Insulated Core Metal Panels | G-PR-05-1090 | Submittal Prep - Insulated Core Metal Panels | 50d | 28-Aug-23 | 13-Oct-23 | 86d
Insulated Core Metal Panels | G-PR-05-1100 | McC Review - Insulated Core Metal Panels | 5d | 16-Oct-23 | 20-Oct-23 | 86d
Insulated Core Metal Panels | G-PR-05-1110 | A/E Review & Approve - Insulated Core Metal Panels | 10d | 23-Oct-23 | 03-Nov-23 | 86d
Insulated Core Metal Panels | G-PR-05-1160 | Fab & Deliver - Insulated Core Metal Panels | 85d | 06-Nov-23 | 07-Mar-24 | 100d
N/A | Masonry | Masonry | 135d | 25-Sep-23 | 04-Apr-24 | 70d
Masonry | G-PR-05-1200 | Submittal Prep - Masonry | 60d | 25-Sep-23 | 19-Dec-23 | 70d
Masonry | G-PR-05-1210 | McC Review - Masonry | 5d | 20-Dec-23 | 27-Dec-23 | 70d
Masonry | G-PR-05-1220 | A/E Review & Approve - Masonry | 10d | 28-Dec-23 | 11-Jan-24 | 70d
Masonry | G-PR-05-1190 | Fab & Deliver - Masonry | 60d | 12-Jan-24 | 04-Apr-24 | 70d
N/A | Roofing Material | Roofing Material | 20d | 24-May-24 | 21-Jun-24 | -15d
Roofing Material | G-PR-07-1030 | Fab & Deliver - Roofing Material | 20d | 24-May-24 | 21-Jun-24 | -15d
N/A | Roofing Shop Dwgs | Roofing Shop Dwgs | 55d | 15-Aug-23 | 31-Oct-23 | 148d
Roofing Shop Dwgs | G-PR-07-1050 | Submittal Prep - Roofing Shop Dwgs | 30d | 15-Aug-23 | 10-Oct-23 | 148d
Roofing Shop Dwgs | G-PR-07-1060 | McC Review - Roofing Shop Dwgs | 5d | 11-Oct-23 | 17-Oct-23 | 148d
Roofing Shop Dwgs | G-PR-07-1070 | A/E Review & Approve - Roofing Shop Dwgs | 10d | 18-Oct-23 | 31-Oct-23 | 148d
N/A | Glass / Aluminum Storefront | Glass / Aluminum Storefront | 88d | 09-Oct-23 | 13-Feb-24 | 77d
Glass / Aluminum Storefront | G-PR-08-1000 | Submittal Prep - Glass / Aluminum Storefront | 15d | 09-Oct-23 | 27-Oct-23 | 77d
Glass / Aluminum Storefront | G-PR-08-1010 | McC Review - Glass / Aluminum Storefront | 5d | 26-Oct-23 | 01-Nov-23 | 77d
Glass / Aluminum Storefront | G-PR-08-1020 | A/E Review & Approve - Glass / Aluminum Storefront | 10d | 02-Nov-23 | 15-Nov-23 | 77d
Glass / Aluminum Storefront | G-PR-08-1030 | Fab & Deliver - Glass / Aluminum Storefront | 60d | 16-Nov-23 | 13-Feb-24 | 77d
Glass / Aluminum Storefront | G-PRECN-6410 | Deferred Submittal - Exterior Window Wall System | 60d | 16-Nov-23 | 13-Feb-24 | 77d
N/A | Illuminated Signage | Illuminated Signage | 195d | 16-Oct-23 | 22-Jul-24 | 102d
Illuminated Signage | G-PRCR-9020 | Submittal Prep - Illuminated Signage | 60d | 16-Oct-23 | 11-Jan-24 | 102d
Illuminated Signage | G-PRCR-9030 | McC Review - Illuminated Signage | 5d | 12-Jan-24 | 18-Jan-24 | 102d
Illuminated Signage | G-PRCR-9040 | A/E Review & Approve - Illuminated Signage | 10d | 19-Jan-24 | 01-Feb-24 | 102d
Illuminated Signage | G-PRCR-9010 | Fab & Deliver - Illuminated Signage | 120d | 02-Feb-24 | 22-Jul-24 | 102d
N/A | Custom Coiling Doors | Custom Coiling Doors | 238d | 21-Jul-23 | 02-Aug-24 | 45d
Custom Coiling Doors | G-PR-31-1760 | Design Custom Coiling Doors | 125d | 21-Jul-23 | 17-Jan-24 | 45d
Custom Coiling Doors | G-PR-31-1560 | Wind Load Testing | 10d | 18-Jan-24 | 31-Jan-24 | 45d
Custom Coiling Doors | G-PR-31-1050 | Submittal Prep - Custom Coiling Doors | 15d | 01-Feb-24 | 21-Feb-24 | 45d
Custom Coiling Doors | G-PR-31-1060 | McC Review - Custom Coiling Doors | 5d | 22-Feb-24 | 28-Feb-24 | 45d
Custom Coiling Doors | G-PR-31-1070 | A/E Review & Approve - Custom Coiling Doors | 10d | 29-Feb-24 | 13-Mar-24 | 45d
Custom Coiling Doors | G-PR-31-2530 | Fab & Deliver - Custom Coiling Doors | 100d | 14-Mar-24 | 02-Aug-24 | 45d
N/A | Coiling Doors | Coiling Doors | 224d | 01-Aug-23 | 18-Jul-24 | 26d
Coiling Doors | G-PR-31-2750 | McC Review - Coiling Doors | 5d | 01-Aug-23 | 22-Dec-23 | 26d
Coiling Doors | G-PR-31-2760 | A/E Review & Approve - Coiling Doors | 10d | 26-Dec-23 | 09-Jan-24 | 26d
Coiling Doors | G-PR-31-2730 | Fab & Deliver - Coiling Doors | 135d | 10-Jan-24 | 18-Jul-24 | 26d
N/A | High Speed Fabric Doors | High Speed Fabric Doors | 149d | 01-Aug-23 | 02-Apr-24 | 101d
High Speed Fabric Doors | G-PR-31-2800 | McC Review - High Speed Fabric Doors | 5d | 01-Aug-23 | 22-Dec-23 | 101d
High Speed Fabric Doors | G-PR-31-2810 | A/E Review & Approve - High Speed Fabric Doors | 10d | 26-Dec-23 | 09-Jan-24 | 101d
High Speed Fabric Doors | G-PR-31-2780 | Fab & Deliver - High Speed Fabric Doors | 60d | 10-Jan-24 | 02-Apr-24 | 101d
N/A | Bridge Crane | Bridge Crane | 153d | 25-Sep-23 | 30-Apr-24 | 106d
Bridge Crane | G-PR-31-1100 | McC Review - Bridge Crane | 63d | 25-Sep-23 | 22-Dec-23 | 11d
Bridge Crane | G-PR-31-1110 | A/E Review & Approve - Bridge Crane | 10d | 26-Dec-23 | 09-Jan-24 | 11d
Bridge Crane | G-PR-31-1080 | Fab & Deliver - Bridge Crane | 80d | 10-Jan-24 | 30-Apr-24 | 106d
N/A | Freezer / Cooler | Freezer / Cooler | 220d | 10-Aug-23 | 21-Aug-24 | -4d
Freezer / Cooler | G-PR-31-1220 | McC Review - Freezer / Cooler | 5d | 10-Aug-23 | 30-Nov-23 | -4d
Freezer / Cooler | G-PR-31-1230 | A/E Review & Approve - Freezer / Cooler | 10d | 01-Dec-23 | 14-Dec-23 | -4d
Freezer / Cooler | G-PR-31-1200 | Fab & Deliver - Freezer / Cooler | 175d | 15-Dec-23 | 21-Aug-24 | -4d
N/A | Ice Machine | Ice Machine | 192d | 12-Jun-23 | 21-Mar-24 | 103d
Ice Machine | G-PR-31-2410 | Submittal Prep - Ice Machine | 20d | 12-Jun-23 | 06-Oct-23 | 0d
Ice Machine | G-PR-31-2420 | McC Review - Ice Machine | 5d | 09-Oct-23 | 13-Oct-23 | 59d
Ice Machine | G-PR-31-2430 | A/E Review & Approve - Ice Machine | 10d | 16-Oct-23 | 27-Oct-23 | 59d
Ice Machine | G-PR-31-2400 | Fab & Deliver - Ice Machine | 100d | 30-Oct-23 | 21-Mar-24 | 103d
N/A | Paint Booth | Paint Booth | 270d | 09-Oct-23 | 29-Oct-24 | 11d
Paint Booth | G-PR-31-1250 | Submittal Prep - Paint Booth | 15d | 09-Oct-23 | 27-Oct-23 | 11d
Paint Booth | G-PR-31-1260 | McC Review - Paint Booth | 5d | 30-Oct-23 | 03-Nov-23 | 11d
Paint Booth | G-PR-31-1270 | A/E Review & Approve - Paint Booth | 10d | 06-Nov-23 | 17-Nov-23 | 11d
Paint Booth | G-PR-31-1240 | Fab & Deliver - Paint Booth | 240d | 20-Nov-23 | 29-Oct-24 | 11d
N/A | Auto Lifts | Auto Lifts | 222d | 25-Aug-23 | 11-Jul-24 | 66d
Auto Lifts | G-PR-31-1980 | McC Review - Auto Lifts | 15d | 25-Aug-23 | 22-Dec-23 | 11d
Auto Lifts | G-PR-31-1990 | A/E Review & Approve - Auto Lifts | 10d | 26-Dec-23 | 09-Jan-24 | 11d
Auto Lifts | G-PR-31-1960 | Fab & Deliver - Auto Lifts | 130d | 10-Jan-24 | 11-Jul-24 | 66d
N/A | BP Fluid Systems | BP Fluid Systems | 145d | 09-Oct-23 | 02-May-24 | 109d
BP Fluid Systems | G-PR-31-2170 | Submittal Prep - Eaton Fluid Systems | 30d | 09-Oct-23 | 17-Nov-23 | 29d
BP Fluid Systems | G-PR-31-2180 | McC Review - Eaton Fluid Systems | 5d | 20-Nov-23 | 28-Nov-23 | 29d
BP Fluid Systems | G-PR-31-2190 | A/E Review & Approve - Eaton Fluid Systems | 10d | 29-Nov-23 | 12-Dec-23 | 29d
BP Fluid Systems | G-PR-31-2160 | Fab & Deliver - Eaton Fluid Systems | 100d | 13-Dec-23 | 02-May-24 | 109d
N/A | Warehouse Racking | Warehouse Racking | 148d | 09-Oct-23 | 07-May-24 | 138d
Warehouse Racking | G-PR-31-1810 | Submittal Prep - Warehouse Racking | 53d | 09-Oct-23 | 22-Dec-23 | 138d
Warehouse Racking | G-PR-31-1820 | McC Review - Warehouse Racking | 5d | 26-Dec-23 | 02-Jan-24 | 138d
Warehouse Racking | G-PR-31-1830 | A/E Review & Approve - Warehouse Racking | 10d | 03-Jan-24 | 16-Jan-24 | 138d
Warehouse Racking | G-PR-31-1800 | Fab & Deliver - Warehouse Racking | 80d | 17-Jan-24 | 07-May-24 | 138d
N/A | Lockers | Lockers | 138d | 25-Sep-23 | 09-Apr-24 | 138d
Lockers | G-PR-31-1330 | Submittal Prep - Lockers | 63d | 25-Sep-23 | 22-Dec-23 | 138d
Lockers | G-PR-31-1340 | McC Review - Lockers | 5d | 26-Dec-23 | 02-Jan-24 | 138d
Lockers | G-PR-31-1350 | A/E Review & Approve - Lockers | 10d | 03-Jan-24 | 16-Jan-24 | 138d
Lockers | G-PR-31-1320 | Fab & Deliver - Lockers | 60d | 17-Jan-24 | 09-Apr-24 | 138d
N/A | Tile | Tile | 193d | 21-Jul-23 | 23-Apr-24 | 92d
Tile | G-PR-31-1490 | Submittal Prep - Tile | 60d | 21-Jul-23 | 22-Dec-23 | 92d
Tile | G-PR-31-1500 | McC Review - Tile | 5d | 26-Dec-23 | 02-Jan-24 | 92d
Tile | G-PR-31-1510 | A/E Review & Approve - Tile | 10d | 03-Jan-24 | 16-Jan-24 | 92d
Tile | G-PR-31-1480 | Fab & Deliver - Tile | 70d | 17-Jan-24 | 23-Apr-24 | 92d
N/A | Carpet | Carpet | 203d | 21-Jul-23 | 07-May-24 | 119d
Carpet | G-PR-31-1530 | Submittal Prep - Carpet | 60d | 21-Jul-23 | 22-Dec-23 | 119d
Carpet | G-PR-31-1540 | McC Review - Carpet | 5d | 26-Dec-23 | 02-Jan-24 | 119d
Carpet | G-PR-31-1550 | A/E Review & Approve - Carpet | 10d | 03-Jan-24 | 16-Jan-24 | 119d
Carpet | G-PR-31-1520 | Fab & Deliver - Carpet | 80d | 17-Jan-24 | 07-May-24 | 119d
N/A | Concrete Seal | Concrete Seal | 100d | 21-Jul-23 | 12-Dec-23 | 261d
Concrete Seal | G-PR-31-1570 | Submittal Prep - Concrete Seal | 60d | 21-Jul-23 | 27-Oct-23 | 261d
Concrete Seal | G-PR-31-1580 | McC Review - Concrete Seal | 5d | 30-Oct-23 | 03-Nov-23 | 261d
Concrete Seal | G-PR-31-1590 | A/E Review & Approve - Concrete Seal | 10d | 06-Nov-23 | 17-Nov-23 | 261d
Concrete Seal | G-PR-31-2040 | Fab & Deliver - Concrete Seal | 15d | 20-Nov-23 | 12-Dec-23 | 261d
N/A | Misc Metals | Misc Metals | 125d | 21-Jul-23 | 18-Jan-24 | 232d
Misc Metals | G-PR-31-1610 | Submittal Prep - Misc Metals | 60d | 21-Jul-23 | 27-Oct-23 | 232d
Misc Metals | G-PR-31-1620 | McC Review - Misc Metals | 5d | 30-Oct-23 | 03-Nov-23 | 232d
Misc Metals | G-PR-31-1630 | A/E Review & Approve - Misc Metals | 10d | 06-Nov-23 | 17-Nov-23 | 232d
Misc Metals | G-PR-31-1600 | Fab & Deliver - Misc Metals | 40d | 20-Nov-23 | 18-Jan-24 | 232d
N/A | Interior Fencing | Interior Fencing | 130d | 21-Jul-23 | 25-Jan-24 | 241d
Interior Fencing | G-PR-31-2070 | Submittal Prep - Interior Fencing | 60d | 21-Jul-23 | 03-Nov-23 | 241d
Interior Fencing | G-PR-31-2080 | McC Review - Interior Fencing | 5d | 06-Nov-23 | 10-Nov-23 | 241d
Interior Fencing | G-PR-31-2090 | A/E Review & Approve - Interior Fencing | 10d | 13-Nov-23 | 28-Nov-23 | 241d
Interior Fencing | G-PR-31-2060 | Fab & Deliver - Interior Fencing | 40d | 29-Nov-23 | 25-Jan-24 | 241d
N/A | AOA / Exterior Fencing | AOA / Exterior Fencing | 125d | 21-Jul-23 | 18-Jan-24 | 227d
AOA / Exterior Fencing | G-PR-31-2830 | Submittal Prep - AOA / Exterior Fencing | 60d | 21-Jul-23 | 27-Oct-23 | 227d
AOA / Exterior Fencing | G-PR-31-2840 | McC Review - AOA / Exterior Fencing | 5d | 30-Oct-23 | 03-Nov-23 | 227d
AOA / Exterior Fencing | G-PR-31-2850 | A/E Review & Approve - AOA / Exterior Fencing | 10d | 06-Nov-23 | 17-Nov-23 | 227d
AOA / Exterior Fencing | G-PR-31-2820 | Fab & Deliver - AOA / Exterior Fencing | 40d | 20-Nov-23 | 18-Jan-24 | 227d
N/A | Specialties | Specialties | 148d | 25-Sep-23 | 23-Apr-24 | 107d
Specialties | G-PR-31-1690 | Submittal Prep - Specialties | 63d | 25-Sep-23 | 22-Dec-23 | 107d
Specialties | G-PR-31-1700 | McC Review - Specialties | 5d | 26-Dec-23 | 02-Jan-24 | 107d
Specialties | G-PR-31-1710 | A/E Review & Approve - Specialties | 10d | 03-Jan-24 | 16-Jan-24 | 107d
Specialties | G-PR-31-1680 | Fab & Deliver - Specialties | 70d | 17-Jan-24 | 23-Apr-24 | 107d
N/A | Millwork / Cabinets | Millwork / Cabinets | 148d | 25-Sep-23 | 23-Apr-24 | 97d
Millwork / Cabinets | G-PR-31-1730 | Submittal Prep - Millwork / Cabinets | 63d | 25-Sep-23 | 22-Dec-23 | 97d
Millwork / Cabinets | G-PR-31-1740 | McC Review - Millwork / Cabinets | 5d | 26-Dec-23 | 02-Jan-24 | 97d
Millwork / Cabinets | G-PR-31-1750 | A/E Review & Approve - Millwork / Cabinets | 10d | 03-Jan-24 | 16-Jan-24 | 97d
Millwork / Cabinets | G-PR-31-1720 | Fab & Deliver - Millwork / Cabinets | 70d | 17-Jan-24 | 23-Apr-24 | 97d
N/A | Doors & Hardware | Doors & Hardware | 177d | 26-Sep-23 | 05-Jun-24 | 81d
Doors & Hardware | G-PR-31-1850 | Submittal Prep - Doors & Hardware | 62d | 26-Sep-23 | 22-Dec-23 | 81d
Doors & Hardware | G-PR-31-1860 | McC Review - Doors & Hardware | 5d | 26-Dec-23 | 02-Jan-24 | 81d
Doors & Hardware | G-PR-31-1870 | A/E Review & Approve - Doors & Hardware | 10d | 03-Jan-24 | 16-Jan-24 | 81d
Doors & Hardware | G-PR-31-1840 | Fab & Deliver - Doors & Hardware | 100d | 17-Jan-24 | 05-Jun-24 | 81d
N/A | Door Frames | Door Frames | 157d | 26-Sep-23 | 07-May-24 | 29d
Door Frames | G-PR-31-1890 | Submittal Prep - Door Frames | 62d | 26-Sep-23 | 22-Dec-23 | 29d
Door Frames | G-PR-31-1900 | McC Review - Door Frames | 5d | 26-Dec-23 | 02-Jan-24 | 29d
Door Frames | G-PR-31-1910 | A/E Review & Approve - Door Frames | 10d | 03-Jan-24 | 16-Jan-24 | 29d
Door Frames | G-PR-31-1880 | Fab & Deliver - Door Frames | 80d | 17-Jan-24 | 07-May-24 | 29d
N/A | Dock Levelers | Dock Levelers | 246d | 06-Jun-23 | 23-May-24 | 116d
Dock Levelers | G-PR-31-2010 | Submittal Prep - Dock Levelers | 20d | 06-Jun-23 | 20-Oct-23 | -10d
Dock Levelers | G-PR-31-2020 | McC Review - Dock Levelers | 10d | 23-Oct-23 | 03-Nov-23 | 116d
Dock Levelers | G-PR-31-2030 | A/E Review & Approve - Dock Levelers | 10d | 06-Nov-23 | 17-Nov-23 | 116d
Dock Levelers | G-PR-31-2000 | Fab & Deliver - Dock Levelers | 130d | 20-Nov-23 | 23-May-24 | 116d
N/A | Asphalt | Asphalt | 105d | 21-Jul-23 | 19-Dec-23 | 231d
Asphalt | G-PR-31-1370 | Submittal Prep - Asphalt | 60d | 21-Jul-23 | 27-Oct-23 | 231d
Asphalt | G-PR-31-1380 | McC Review - Asphalt | 5d | 30-Oct-23 | 03-Nov-23 | 231d
Asphalt | G-PR-31-1390 | A/E Review & Approve - Asphalt | 10d | 06-Nov-23 | 17-Nov-23 | 231d
Asphalt | G-PR-31-1360 | Fab & Deliver - Asphalt | 20d | 20-Nov-23 | 19-Dec-23 | 231d
N/A | Striping | Striping | 165d | 21-Jul-23 | 14-Mar-24 | 171d
Striping | G-PR-31-1650 | Submittal Prep - Striping | 60d | 21-Jul-23 | 27-Oct-23 | 171d
Striping | G-PR-31-1660 | McC Review - Striping | 5d | 30-Oct-23 | 03-Nov-23 | 171d
Striping | G-PR-31-1670 | A/E Review & Approve - Striping | 10d | 06-Nov-23 | 17-Nov-23 | 171d
Striping | G-PR-31-1640 | Fab & Deliver - Striping | 80d | 20-Nov-23 | 14-Mar-24 | 171d
N/A | Site Concrete | Site Concrete | 115d | 21-Jul-23 | 04-Jan-24 | 216d
Site Concrete | G-PR-31-1410 | Submittal Prep - Site Concrete | 60d | 21-Jul-23 | 27-Oct-23 | 216d
Site Concrete | G-PR-31-1420 | McC Review - Site Concrete | 5d | 30-Oct-23 | 03-Nov-23 | 216d
Site Concrete | G-PR-31-1430 | A/E Review & Approve - Site Concrete | 10d | 06-Nov-23 | 17-Nov-23 | 216d
Site Concrete | G-PR-31-1400 | Fab & Deliver - Site Concrete | 30d | 20-Nov-23 | 04-Jan-24 | 216d
N/A | Landscaping | Landscaping | 135d | 25-Sep-23 | 04-Apr-24 | 186d
Landscaping | G-PR-31-1450 | Submittal Prep - Landscaping | 60d | 25-Sep-23 | 19-Dec-23 | 186d
Landscaping | G-PR-31-1460 | McC Review - Landscaping | 5d | 20-Dec-23 | 27-Dec-23 | 186d
Landscaping | G-PR-31-1470 | A/E Review & Approve - Landscaping | 10d | 28-Dec-23 | 11-Jan-24 | 186d
Landscaping | G-PR-31-1440 | Fab & Deliver - Landscaping | 60d | 12-Jan-24 | 04-Apr-24 | 186d
N/A | VDC Modeling | VDC Modeling | 167d | 21-Aug-23 | 16-Apr-24 | 11d
N/A | SOG | SOG | 30d | 09-Oct-23 | 17-Nov-23 | -10d
SOG | G-VDC-1040 | Incorporate Approved Material into SOG Model (Pipe, Fittings, Etc.) | 10d | 09-Oct-23 | 20-Oct-23 | -10d
SOG | G-VDC-1050 | Finalize Model / Develop Shop Dwgs for SOG | 10d | 23-Oct-23 | 03-Nov-23 | -10d
SOG | G-VDC-1140 | A/E Review & Approve Shop Dwgs for SOG | 10d | 06-Nov-23 | 17-Nov-23 | -10d
N/A | Tilt Panels | Tilt Panels | 104d | 21-Aug-23 | 18-Jan-24 | -23d
Tilt Panels | G-PR-31-2720 | Rebar Shop Dwgs for Tilt Panels | 14d | 21-Aug-23 | 05-Oct-23 | -2d
Tilt Panels | G-VDC-1220 | Incorporate Approved Material into Tilt Panels Mode l | 10d | 06-Nov-23 | 17-Nov-23 | -23d
Tilt Panels | G-VDC-1230 | Finalize Model / Develop Shop Dwgs for Tilt Panels | 10d | 20-Nov-23 | 05-Dec-23 | -23d
Tilt Panels | G-VDC-1240 | A/E Review & Approve Shop Dwgs for Tilt Panels | 10d | 06-Dec-23 | 19-Dec-23 | -23d
Tilt Panels | G-PR-31-2520 | Fab & Deliver - Tilt Panel Rebar / Insulation / Acc essories | 20d | 20-Dec-23 | 18-Jan-24 | -23d
N/A | Interior Fitout | Interior Fitout | 70d | 10-Jan-24 | 16-Apr-24 | 11d
Interior Fitout | G-VDC-1100 | Incorporate Approved Material into Model for Interi or Fitout | 40d | 10-Jan-24 | 05-Mar-24 | 11d
Interior Fitout | G-VDC-1120 | Clash Coordination w/ Trades for Interior Fitout | 10d | 06-Mar-24 | 19-Mar-24 | 11d
Interior Fitout | G-VDC-1110 | Finalize Model / Develop Shop Dwgs for Interior Fit out | 10d | 20-Mar-24 | 02-Apr-24 | 11d
Interior Fitout | G-VDC-1160 | A/E Review & Approve Shop Dwgs for Interior Fitout | 10d | 03-Apr-24 | 16-Apr-24 | 11d
N/A | Construction | Construction | 449d | 12-Jun-23 | 02-May-25 | 30d
N/A | Earthwork | Earthwork | 71d | 12-Jun-23 | 06-Nov-23 | 206d
Earthwork | G-CON-6250 | North Building Underdrain - Lift 2 - 524 LF (Grid J -A) | 6d | 22-Sep-23 | 28-Sep-23 | -28d
Earthwork | G-CON-7800 | Plumbing Sleeves at Underdrain - Building South | 10d | 18-Sep-23 | 29-Sep-23 | -22d
Earthwork | G-CON-6930 | Plumbing Sleeves at Underdrain - Building North | 5d | 29-Sep-23 | 05-Oct-23 | -7d
Earthwork | G-CON-1470 | Fill from Stockpile South Fill 2 Building & Region 7 - 1,900 CY's - Building Pad | 1d | 17-Oct-23 | 17-Oct-23 | -15d
Earthwork | G-CON-1480 | Certify Building Pad - North & Parking Areas | 4d | 18-Oct-23 | 23-Oct-23 | -15d
N/A | FRAGNET 01 - New Geo-Technical Requirements | FRAGNET 01 - New Geo-Technical Requirements | 71d | 12-Jun-23 | 06-Nov-23 | 206d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1280 | Cut Region 8 to 6 - 7,900 CY's | 4d | 21-Sep-23 | 25-Sep-23 | -31d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1430 | Jviation & GEG Coordinate for Direction at Failed A reas | 10d | 22-Sep-23 | 25-Sep-23 | -25d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1180 | Take Swell T est #2 of Stockpile South (South Ribbon ) after 10K CY's Place and Processed | 10d | 28-Aug-23 | 26-Sep-23 | -31d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1390 | Region 7 Cut to Fill 3 - 2,400 CY's | 1d | 26-Sep-23 | 26-Sep-23 | -31d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1230 | South Building Underdrain - Lift 2 - 1335 LF - (Gri d J-R) | 8d | 14-Sep-23 | 29-Sep-23 | -30d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1050 | Owner Review and Approval Pricing - New Geo Tech Re quirements | 15d | 21-Jul-23 | 02-Oct-23 | 31d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1250 | Region 8 Cut to Fill 3 - 9,400 CY's (Region South) | 5d | 27-Sep-23 | 03-Oct-23 | -31d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1420 | Rework Top 2 Ft of Area 1B & Region 2 | 3d | 29-Sep-23 | 03-Oct-23 | -28d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1220 | Fill from Stockpile South to Fill 1 Building - 16,5 00 CY's - Building Pad | 7d | 04-Oct-23 | 12-Oct-23 | -31d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1400 | Fill from Stockpile South to Fill 2 Building - 2,90 0 CY's - N Building Pad | 2d | 13-Oct-23 | 16-Oct-23 | -15d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1340 | Cut Region 8 to Fill 7 - 2,100 CY's | 1d | 18-Oct-23 | 18-Oct-23 | 15d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1300 | Certify Building Pad - South & Parking Area | 5d | 13-Oct-23 | 19-Oct-23 | -31d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1060 | Additional Earthwork - Stockpile & Over Excavation & Fill Site | 31d | 12-Jun-23 | 24-Oct-23 | 15d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1350 | Cut Region 9 to Fill 7 - 9,500 CY's | 4d | 19-Oct-23 | 24-Oct-23 | 15d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1290 | Cut Region 9 & 10 to Export / Stockpile - 7,600 CY' s | 3d | 25-Oct-23 | 27-Oct-23 | 208d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1360 | Pond Cut to Fill Region NW - 10,866 CY's | 5d | 25-Oct-23 | 31-Oct-23 | 206d
FRAGNET 01 - New Geo-Technical Requirements | G-FRG-01-1370 | Pond/Trac t to Stockpile or Cargo - 7,290 CY's | 4d | 01-Nov-23 | 06-Nov-23 | 206d
N/A | Site Utilities | Site Utilities | 289d | 04-Oct-23 | 20-Nov-24 | 143d
N/A | Storm / Sewer / Water | Storm / Sewer / Water | 192d | 04-Oct-23 | 05-Jul-24 | 240d
N/A | Sanitary Sewer | Sanitary Sewer | 18d | 04-Oct-23 | 27-Oct-23 | 414d
Sanitary Sewer | G-CON-5125 | Sanitary EX MH-1 to MH6 - 92LF+CTE+MH | 2d | 04-Oct-23 | 05-Oct-23 | 6d
Sanitary Sewer | G-CON-5145 | Sanitary MH6 to MH3 - 327LF+OWS+3MH | 4d | 17-Oct-23 | 20-Oct-23 | 6d
Sanitary Sewer | G-CON-8390 | Sanitary MH3 to MH1 - 406LF + MH | 3d | 23-Oct-23 | 25-Oct-23 | 6d
Sanitary Sewer | G-CON-8400 | Sanitary Testing | 2d | 26-Oct-23 | 27-Oct-23 | 414d
N/A | Storm Sewer | Storm Sewer | 55d | 06-Oct-23 | 26-Dec-23 | 173d
Storm Sewer | G-CON-5135 | Storm SDG South 1 - MH 1 to MH3 - 498LF+4MH | 4d | 06-Oct-23 | 11-Oct-23 | 6d
Storm Sewer | G-CON-5070 | Storm SDG South 1 - Laterals - 172LF+MH+3INLET | 3d | 12-Oct-23 | 16-Oct-23 | 6d
Storm Sewer | G-CON-5270 | Storm SDG West 1 - MH1 to MH13 - 253LF+4MH | 4d | 26-Oct-23 | 31-Oct-23 | 6d
Storm Sewer | G-CON-7790 | Storm SDG North 3 - MH13 to MH27 - 456LF+4MH | 4d | 01-Nov-23 | 06-Nov-23 | 6d
Storm Sewer | G-CON-5155 | Storm SDG North 1 - MH5 to IN10 - 390LF+2MH+2INLET | 3d | 07-Nov-23 | 09-Nov-23 | 6d
Storm Sewer | G-CON-5165 | Storm SDG East 1 - MH16 to MH18 - 234LF+2MH | 2d | 10-Nov-23 | 13-Nov-23 | 173d
Storm Sewer | G-CON-5175 | Storm SDG East 2 - IN7 to IN6 - 168LF+2INLET | 2d | 14-Nov-23 | 15-Nov-23 | 173d
Storm Sewer | G-CON-8410 | Storm SDG East 3 - IN9 to MH20 - 168LF+2MH+INLET | 2d | 16-Nov-23 | 17-Nov-23 | 173d
Storm Sewer | G-CON-8420 | Storm SDG West 1 - MH13 to FES - 252LF+2MH+FES | 3d | 20-Nov-23 | 22-Nov-23 | 173d
Storm Sewer | G-CON-8430 | Storm SDG West 3 - OS to EX IN - 366LF+2MH | 4d | 27-Nov-23 | 30-Nov-23 | 173d
Storm Sewer | G-CON-8440 | Storm SDG South 1 - MH3 to FES - 340LF+MH+FES | 3d | 01-Dec-23 | 05-Dec-23 | 173d
Storm Sewer | G-CON-8450 | Storm SGD North 1 - IN16 to MH5 - 328LF+4MH+INLET | 3d | 06-Dec-23 | 08-Dec-23 | 173d
Storm Sewer | G-CON-8460 | Storm SDG West 2 - IN14 to IN15 - 100LF+2INLET | 1d | 11-Dec-23 | 11-Dec-23 | 173d
Storm Sewer | G-CON-8470 | Storm SDG West 6 & SDG North 2 - 32LF+2INLET | 1d | 12-Dec-23 | 12-Dec-23 | 173d
Storm Sewer | G-CON-8480 | Storm SDG West 4 & SDG West 5 - 232LF+8FES | 3d | 13-Dec-23 | 15-Dec-23 | 173d
Storm Sewer | G-CON-8490 | Storm SDG West 1 - Laterals - 81LF+2INLET | 1d | 18-Dec-23 | 18-Dec-23 | 173d
Storm Sewer | G-CON-8500 | Storm Testing | 5d | 19-Dec-23 | 26-Dec-23 | 173d
N/A | Water Main | Water Main | 36d | 09-Oct-23 | 29-Nov-23 | 6d
Water Main | G-CON-5090 | Water STA 0+00 to 4+00 - 400LF+CTE+3 LOWER | 4d | 09-Oct-23 | 12-Oct-23 | 38d
Water Main | G-CON-5860 | Water STA 4+00 to 6+50 - 250LF+2 LOWER | 3d | 01-Nov-23 | 03-Nov-23 | 10d
Water Main | G-CON-5220 | Water STA 6+50 to 13+00 - 650LF+3 LOWER | 5d | 10-Nov-23 | 16-Nov-23 | 6d
Water Main | G-CON-8530 | Water STA 13+00 to 17+52 - 450LF+CTE+3 LOWER | 5d | 17-Nov-23 | 27-Nov-23 | 6d
Water Main | G-CON-8540 | Water 3" & 3/4" Building Services | 1d | 28-Nov-23 | 28-Nov-23 | 6d
Water Main | G-CON-8550 | Water Test | 1d | 29-Nov-23 | 29-Nov-23 | 6d
N/A | Gas Ex/BF | Gas Ex/BF | 22d | 05-Jun-24 | 05-Jul-24 | 38d
Gas Ex/BF | G-CON-8510 | Excavate Gas Main - 1000LF | 6d | 05-Jun-24 | 12-Jun-24 | 38d
Gas Ex/BF | G-CON-8520 | Backfill Gas Main - 1000LF | 6d | 27-Jun-24 | 05-Jul-24 | 38d
N/A | Electrical / Gas | Electrical / Gas | 274d | 25-Oct-23 | 20-Nov-24 | -15d
Electrical / Gas | G-CON-5160 | Electrical Ductbank (from Xcel Tie-in) | 15d | 25-Oct-23 | 14-Nov-23 | -10d
Electrical / Gas | G-CON-5150 | Telecom Ductbank for Fiber Optic Line | 20d | 15-Nov-23 | 14-Dec-23 | -10d
Electrical / Gas | G-CON-5140 | Xcel - Gas Line Install | 10d | 13-Jun-24 | 26-Jun-24 | 38d
Electrical / Gas | G-CON-6760 | Set Transformer Vault & F/R/P Electrical Gear Pad f or SCC-101 | 5d | 24-Jun-24 | 28-Jun-24 | 77d
Electrical / Gas | G-CON-5130 | Xcel - Electrical MV Ductbank Install | 25d | 07-Aug-24 | 11-Sep-24 | 26d
Electrical / Gas | G-CON-6750 | Install SCC-101 (Feed from Xcel) | 2d | 12-Sep-24 | 13-Sep-24 | 26d
Electrical / Gas | G-CON-5170 | Xcel Transformer - Set & Pull Wire | 5d | 16-Sep-24 | 20-Sep-24 | 26d
Electrical / Gas | G-CON-5180 | Xcel Set Meter - After Electrical Final Interiors | 2d | 19-Nov-24 | 20-Nov-24 | -15d
N/A | Structure | Structure | 268d | 15-Aug-23 | 03-Sep-24 | -5d
N/A | Mockup | Mockup | 94d | 25-Sep-23 | 07-Feb-24 | 86d
N/A | Mockup Procurement | Mockup Procurement | 90d | 25-Sep-23 | 01-Feb-24 | 87d
Mockup Procurement | MU-1070 | MU Procure - Framing | 5d | 09-Oct-23 | 13-Oct-23 | 22d
Mockup Procurement | MU-1090 | MU Procure - Paint | 5d | 09-Oct-23 | 13-Oct-23 | 22d
Mockup Procurement | MU-1040 | MU Procure - Formwork | 10d | 09-Oct-23 | 20-Oct-23 | 17d
Mockup Procurement | MU-1020 | MU Procure - Rebar | 10d | 20-Oct-23 | 02-Nov-23 | 8d
Mockup Procurement | MU-1110 | MU Procure - Roofing | 35d | 25-Sep-23 | 10-Nov-23 | 2d
Mockup Procurement | MU-1060 | MU Procure - Metal Panels & Coping Cap | 10d | 06-Nov-23 | 17-Nov-23 | 136d
Mockup Procurement | MU-1030 | MU Procure - Steel | 15d | 06-Nov-23 | 28-Nov-23 | 1d
Mockup Procurement | MU-1100 | MU Procure - Plumbing | 54d | 25-Sep-23 | 11-Dec-23 | -10d
Mockup Procurement | MU-1050 | MU Procure - Glazing | 40d | 16-Nov-23 | 16-Jan-24 | 99d
Mockup Procurement | MU-1080 | MU Procure - Translucent Panels | 60d | 06-Nov-23 | 01-Feb-24 | 86d
N/A | Mockup Construction | Mockup Construction | 59d | 13-Nov-23 | 07-Feb-24 | 86d
Mockup Construction | MU-1010 | MU - Excavate and Grade for footing/SOG | 2d | 13-Nov-23 | 14-Nov-23 | 2d
Mockup Construction | MU-1120 | MU - Install Rebar and Place Embeds for Grade Beam/ SOG (Pre-Pour Inspection) | 2d | 15-Nov-23 | 16-Nov-23 | 2d
Mockup Construction | MU-1130 | MU - P/F/C GB/SOG/Waste Slab | 1d | 16-Nov-23 | 16-Nov-23 | 2d
Mockup Construction | MU-1140 | MU - Strip, Clean, and Prep Slabs | 1d | 17-Nov-23 | 17-Nov-23 | 2d
Mockup Construction | MU-1150 | MU - Layout and Form up Tilt Panels | 2d | 20-Nov-23 | 21-Nov-23 | 2d
Mockup Construction | MU-1160 | MU - Place WWF and MEP Rough-in (Pre-Pour Inspectio n) | 1d | 12-Dec-23 | 12-Dec-23 | -10d
Mockup Construction | MU-1170 | MU - P/F Architectural Pour 1 and Insulation/Pins | 1d | 13-Dec-23 | 13-Dec-23 | -10d
Mockup Construction | MU-1180 | MU - Install Rebar, Embeds, and Pick Points for Pou r 2 (Pre-Pour Inspection | 2d | 14-Dec-23 | 15-Dec-23 | -10d
Mockup Construction | MU-1190 | MU - P/F/C Pour 2 | 3d | 15-Dec-23 | 19-Dec-23 | -10d
Mockup Construction | MU-1200 | MU - Weld Connections (Inspect Welds) | 1d | 19-Dec-23 | 19-Dec-23 | -10d
Mockup Construction | MU-1210 | MU - Install Bracing for Tilt Panels | 1d | 20-Dec-23 | 20-Dec-23 | -10d
Mockup Construction | MU-1220 | MU - Tilt Crane Mob (Assembly Inspection) | 1d | 21-Dec-23 | 21-Dec-23 | -10d
Mockup Construction | MU-1230 | MU - Place Rigging and Erect Tilt Panels | 1d | 21-Dec-23 | 21-Dec-23 | -10d
Mockup Construction | MU-1250 | MU - Demob Crane | 1d | 21-Dec-23 | 21-Dec-23 | -10d
Mockup Construction | MU-1240 | MU - Weld Connections (Inspect Welds) | 1d | 22-Dec-23 | 22-Dec-23 | -10d
Mockup Construction | MU-1260 | MU - AE Review and Sign Off on Concrete | 1d | 26-Dec-23 | 26-Dec-23 | -10d
Mockup Construction | MU-1270 | MU - Backfill Pour Back Strip | 1d | 27-Dec-23 | 27-Dec-23 | -10d
Mockup Construction | MU-1280 | MU - Bulkhead Pour Back Strip and P/F/C pour back ( Pre-Pour Inspection) | 2d | 27-Dec-23 | 28-Dec-23 | -10d
Mockup Construction | MU-1290 | MU - Exterior Caulking | 1d | 29-Dec-23 | 29-Dec-23 | 105d
Mockup Construction | MU-1370 | MU - AE Review and Sign Off on Tilt Mockup | 1d | 29-Dec-23 | 29-Dec-23 | -10d
Mockup Construction | MU-1300 | MU - Place Exterior Coating | 1d | 02-Jan-24 | 02-Jan-24 | 105d
Mockup Construction | MU-1310 | MU - AE Review and Sign Off on Coating | 1d | 03-Jan-24 | 03-Jan-24 | 110d
Mockup Construction | MU-1320 | MU - Install Canopy Framing and Metal Decking | 2d | 03-Jan-24 | 04-Jan-24 | 105d
Mockup Construction | MU-1330 | MU - Install Roof Drain Piping (Close-in Inspection ) | 1d | 04-Jan-24 | 04-Jan-24 | 105d
Mockup Construction | MU-1340 | MU - Install Sheathing/Roofing System at Canopy, Tr im Out Drain and Scupper | 1d | 05-Jan-24 | 05-Jan-24 | 105d
Mockup Construction | MU-1350 | MU - Install Metal Panels and Coping Cap | 2d | 02-Feb-24 | 05-Feb-24 | 86d
Mockup Construction | MU-1360 | MU - Install Glazing and Translucent Panel | 2d | 05-Feb-24 | 06-Feb-24 | 86d
Mockup Construction | MU-1380 | MU - AE Review and Sign Off on Mockup w/ Exterior F inishes | 1d | 07-Feb-24 | 07-Feb-24 | 86d
N/A | Foundations & SOG | Foundations & SOG | 268d | 15-Aug-23 | 03-Sep-24 | -6d
N/A | Drilled Piers | Drilled Piers | 74d | 15-Aug-23 | 29-Nov-23 | -17d
Drilled Piers | G-CON-5060 | Pre-Mob Prep for Drilled Piers (7460 Review with DE N) | 20d | 15-Aug-23 | 09-Oct-23 | -23d
Drilled Piers | G-CON-5010 | Mobilize Equipment for Drilled Piers | 2d | 20-Oct-23 | 23-Oct-23 | -31d
Drilled Piers | G-CON-5870 | Drilled Piers Sequence W1 - Grid 5-14, M-N - Orange | 5d | 24-Oct-23 | 30-Oct-23 | -31d
Drilled Piers | G-CON-5880 | Drilled Piers Sequence W2 - Grid 10-15, M-R - Blue | 5d | 31-Oct-23 | 06-Nov-23 | -30d
Drilled Piers | G-CON-5890 | Drilled Piers Sequence W3 - Grid 8-16, J-R - Green | 5d | 07-Nov-23 | 13-Nov-23 | -30d
Drilled Piers | G-CON-5900 | Drilled Piers Sequence W4 - Grid 3-14, A-L Red | 5d | 14-Nov-23 | 20-Nov-23 | -30d
Drilled Piers | G-CON-5910 | Drilled Piers Sequence W5 - Grid 1-4, A-Q Magenta | 5d | 21-Nov-23 | 29-Nov-23 | -17d
N/A | Earthwork for Grade Beams | Earthwork for Grade Beams | 48d | 31-Oct-23 | 10-Jan-24 | -27d
Earthwork for Grade Beams | G-CON-6350 | Underground Electrical & Telecomm Ductbank Under Gr ade Beams | 5d | 31-Oct-23 | 06-Nov-23 | -31d
Earthwork for Grade Beams | G-CON-5920 | Exc / Grade 1:1 & Place ABC for GB - Drilled Piers Sequence W1 - Orange | 7d | 07-Nov-23 | 15-Nov-23 | -31d
Earthwork for Grade Beams | G-CON-6790 | Underground Plumbing Under Grade Beams (West to Eas t) | 5d | 17-Nov-23 | 27-Nov-23 | -30d
Earthwork for Grade Beams | G-CON-5930 | Exc / Grade 1:1 & Place ABC for GB - Drilled Piers Sequence W2 - Blue | 7d | 16-Nov-23 | 28-Nov-23 | -31d
Earthwork for Grade Beams | G-CON-5940 | Exc / Grade 1:1 & Place ABC for GB - Drilled Piers Sequence W3 - Green | 7d | 29-Nov-23 | 07-Dec-23 | -31d
Earthwork for Grade Beams | G-CON-6150 | Underground Plumbing for SOG 1 Grid L-Q, 10-15 | 8d | 28-Nov-23 | 07-Dec-23 | -30d
Earthwork for Grade Beams | G-CON-5950 | Exc / Grade 1:1 & Place ABC for GB - Drilled Piers Sequence W4 - Red | 7d | 08-Dec-23 | 18-Dec-23 | -31d
Earthwork for Grade Beams | G-CON-8000 | Underground Electrical for SOG 1 Grid L-Q, 10-15 | 10d | 05-Dec-23 | 18-Dec-23 | -30d
Earthwork for Grade Beams | G-CON-7770 | Underground Plumbing for SOG 2 Grid L-Q, 10-1 | 8d | 08-Dec-23 | 19-Dec-23 | -28d
Earthwork for Grade Beams | G-CON-5960 | Exc / Grade 1:1 & Place ABC for GB - Drilled Piers Sequence W5 - Magenta | 7d | 19-Dec-23 | 28-Dec-23 | -30d
Earthwork for Grade Beams | G-CON-7780 | Underground Plumbing for SOG 3 Grid Grid L-A, 6-1 | 8d | 20-Dec-23 | 02-Jan-24 | -23d
Earthwork for Grade Beams | G-CON-8010 | Underground Electrical for SOG 2 Grid L-Q, 10-1 | 10d | 19-Dec-23 | 03-Jan-24 | -30d
Earthwork for Grade Beams | G-CON-8020 | Underground Electrical for SOG 3 Grid Grid L-A, 6-1 | 5d | 04-Jan-24 | 10-Jan-24 | -27d
N/A | Grade Beams | Grade Beams | 49d | 16-Nov-23 | 29-Jan-24 | 102d
N/A | Crew 1 - Grade Beams | Crew 1 - Grade Beams | 49d | 16-Nov-23 | 29-Jan-24 | 102d
N/A | GB2 - Grid Q, 5-12 | GB2 - Grid Q, 5-12 | 9d | 16-Nov-23 | 30-Nov-23 | -22d
GB2 - Grid Q, 5-12 | G-CON-1060 | GB2 Layout Grade Beams - Grid Q, 5-12 | 1d | 16-Nov-23 | 16-Nov-23 | -31d
GB2 - Grid Q, 5-12 | G-CON-5210 | GB2 Form One Side of GB & Install Void Form - Grid Q, 5-12 | 1d | 17-Nov-23 | 17-Nov-23 | -31d
GB2 - Grid Q, 5-12 | G-CON-5230 | GB2 Install Rebar for GB - Grid Q, 5-12 | 2d | 20-Nov-23 | 21-Nov-23 | -24d
GB2 - Grid Q, 5-12 | G-CON-5970 | GB2 Close Form for GB - Grid Q, 5-12 | 2d | 21-Nov-23 | 22-Nov-23 | -24d
GB2 - Grid Q, 5-12 | G-CON-5980 | GB2 Install Anchor Bolts/ Clean Up - Grid Q, 5-12 | 2d | 21-Nov-23 | 22-Nov-23 | -24d
GB2 - Grid Q, 5-12 | G-CON-5990 | GB2 Inspection - Grid Q, 5-12 | 1d | 22-Nov-23 | 22-Nov-23 | -24d
GB2 - Grid Q, 5-12 | G-CON-5240 | GB2 Set and Pour GB - Grid Q, 5-12 | 3d | 27-Nov-23 | 29-Nov-23 | -22d
GB2 - Grid Q, 5-12 | G-CON-5260 | GB2 Strip, Clean, & Move Formwork - Grid Q, 5-12 | 1d | 30-Nov-23 | 30-Nov-23 | -22d
N/A | GB4 - Grid Q-P, 12-15 | GB4 - Grid Q-P, 12-15 | 9d | 28-Nov-23 | 08-Dec-23 | -26d
GB4 - Grid Q-P, 12-15 | G-CON-5480 | GB4 Layout Grade Beams - Grid Q-P, 12-15 | 1d | 28-Nov-23 | 28-Nov-23 | -26d
GB4 - Grid Q-P, 12-15 | G-CON-5250 | GB4 Form One Side of GB & Install Void Form - Grid Q-P, 12-15 | 1d | 29-Nov-23 | 29-Nov-23 | -26d
GB4 - Grid Q-P, 12-15 | G-CON-5280 | GB4 Install Rebar for GB - Grid Q-P, 12-15 | 2d | 30-Nov-23 | 01-Dec-23 | -26d
GB4 - Grid Q-P, 12-15 | G-CON-6000 | GB4 Close Form for GB - Grid Q-P, 12-15 | 2d | 01-Dec-23 | 04-Dec-23 | -26d
GB4 - Grid Q-P, 12-15 | G-CON-6010 | GB4 Install Anchor Bolts/ Clean Up - Grid Q-P, 12-1 5 | 2d | 01-Dec-23 | 04-Dec-23 | -26d
GB4 - Grid Q-P, 12-15 | G-CON-6020 | GB4 Inspection - Grid Q-P, 12-15 | 1d | 04-Dec-23 | 04-Dec-23 | -26d
GB4 - Grid Q-P, 12-15 | G-CON-5290 | GB4 Set and Pour GB - Grid Q-P, 12-15 | 3d | 05-Dec-23 | 07-Dec-23 | -26d
GB4 - Grid Q-P, 12-15 | G-CON-5660 | GB4 Strip, Clean, & Move Formwork - Grid Q-P, 12-1 5 | 1d | 08-Dec-23 | 08-Dec-23 | -26d
N/A | GB6 - Grid L-N, 13-15 | GB6 - Grid L-N, 13-15 | 19d | 01-Dec-23 | 28-Dec-23 | -31d
GB6 - Grid L-N, 13-15 | G-CON-5490 | GB6 Layout Grade Beams - Grid L-N, 13-15 | 1d | 01-Dec-23 | 01-Dec-23 | -22d
GB6 - Grid L-N, 13-15 | G-CON-5300 | GB6 Form One Side of GB & Install Void Form - Grid L-N, 13-15 | 1d | 08-Dec-23 | 08-Dec-23 | -26d
GB6 - Grid L-N, 13-15 | G-CON-5320 | GB6 nstall Rebar for GB - Grid L-N, 13-15 | 2d | 11-Dec-23 | 12-Dec-23 | -25d
GB6 - Grid L-N, 13-15 | G-CON-5310 | GB6 Close Form for GB - Grid L-N, 13-15 | 2d | 20-Dec-23 | 21-Dec-23 | -31d
GB6 - Grid L-N, 13-15 | G-CON-5350 | GB6 Install Anchor Bolts/ Clean Up - Grid L-N, 13-1 5 | 2d | 20-Dec-23 | 21-Dec-23 | -31d
GB6 - Grid L-N, 13-15 | G-CON-5400 | GB6 Inspection - Grid L-N, 13-15 | 1d | 21-Dec-23 | 21-Dec-23 | -31d
GB6 - Grid L-N, 13-15 | G-CON-5340 | GB6 Set and Pour GB - Grid L-N, 13-15 | 3d | 22-Dec-23 | 27-Dec-23 | -31d
GB6 - Grid L-N, 13-15 | G-CON-5370 | GB6 Strip, Clean, & Move Formwork - Grid L-N, 13-1 5 | 1d | 28-Dec-23 | 28-Dec-23 | -31d
N/A | GB8 - Grid L, 7-13 | GB8 - Grid L, 7-13 | 15d | 11-Dec-23 | 02-Jan-24 | -31d
GB8 - Grid L, 7-13 | G-CON-7250 | GB8 Layout Grade Beams - Grid L, 7-13 | 1d | 11-Dec-23 | 11-Dec-23 | -26d
GB8 - Grid L, 7-13 | G-CON-5330 | GB8 Form One Side of GB & Install Void Form - Grid L, 7-13 | 1d | 19-Dec-23 | 19-Dec-23 | -31d
GB8 - Grid L, 7-13 | G-CON-5360 | GB8 Install Rebar for GB - Grid L, 7-13 | 2d | 20-Dec-23 | 21-Dec-23 | -30d
GB8 - Grid L, 7-13 | G-CON-5440 | GB8 Close Form for GB - Grid L, 7-13 | 2d | 22-Dec-23 | 26-Dec-23 | -31d
GB8 - Grid L, 7-13 | G-CON-6030 | GB8 Install Anchor Bolts/ Clean Up - Grid L, 7-13 | 2d | 22-Dec-23 | 26-Dec-23 | -31d
GB8 - Grid L, 7-13 | G-CON-6040 | GB8 Inspection - Grid L, 7-13 | 1d | 26-Dec-23 | 26-Dec-23 | -31d
GB8 - Grid L, 7-13 | G-CON-5380 | GB8 Set and Pour GB - Grid L, 7-13 | 3d | 27-Dec-23 | 29-Dec-23 | -31d
GB8 - Grid L, 7-13 | G-CON-5670 | GB8 Strip, Clean, & Move Formwork - Grid L, 7-13 | 1d | 02-Jan-24 | 02-Jan-24 | -31d
N/A | GB10 - Grid C-L, 6-8 | GB10 - Grid C-L, 6-8 | 10d | 29-Dec-23 | 12-Jan-24 | -30d
GB10 - Grid C-L, 6-8 | G-CON-5500 | GB10 Layout Grade Beams - Grid C-L, 6-8 | 1d | 29-Dec-23 | 29-Dec-23 | -31d
GB10 - Grid C-L, 6-8 | G-CON-5390 | GB10 Form One Side of GB & Install Void Form - Grid C-L, 6-8 | 1d | 02-Jan-24 | 02-Jan-24 | -31d
GB10 - Grid C-L, 6-8 | G-CON-5410 | GB10 Install Rebar for GB - Grid C-L, 6-8 | 2d | 03-Jan-24 | 04-Jan-24 | -30d
GB10 - Grid C-L, 6-8 | G-CON-6050 | GB10 Close Form for GB - Grid C-L, 6-8 | 2d | 05-Jan-24 | 08-Jan-24 | -31d
GB10 - Grid C-L, 6-8 | G-CON-6060 | GB10 Install Anchor Bolts/ Clean Up - Grid C-L, 6-8 | 2d | 05-Jan-24 | 08-Jan-24 | -30d
GB10 - Grid C-L, 6-8 | G-CON-6070 | GB10 Inspection - Grid C-L, 6-8 | 1d | 08-Jan-24 | 08-Jan-24 | -30d
GB10 - Grid C-L, 6-8 | G-CON-5430 | GB10 Set and Pour GB - Grid C-L, 6-8 | 3d | 09-Jan-24 | 11-Jan-24 | -30d
GB10 - Grid C-L, 6-8 | G-CON-5460 | GB10 Strip, Clean, & Move Formwork - Grid C-L, 6-8 | 1d | 12-Jan-24 | 12-Jan-24 | -30d
N/A | GB12 - Grid A-C, 1-6 | GB12 - Grid A-C, 1-6 | 10d | 03-Jan-24 | 16-Jan-24 | -31d
GB12 - Grid A-C, 1-6 | G-CON-7260 | GB12 Layout Grade Beams - Grid A-C, 1-6 | 1d | 03-Jan-24 | 03-Jan-24 | -31d
GB12 - Grid A-C, 1-6 | G-CON-5420 | GB12 Form One Side of GB & Install Void Form - Grid A-C, 1-6 | 1d | 04-Jan-24 | 04-Jan-24 | -31d
GB12 - Grid A-C, 1-6 | G-CON-5450 | GB12 Install Rebar for GB - Grid A-C, 1-6 | 2d | 05-Jan-24 | 08-Jan-24 | -30d
GB12 - Grid A-C, 1-6 | G-CON-6080 | GB12 Close Form for GB - Grid A-C, 1-6 | 2d | 09-Jan-24 | 10-Jan-24 | -31d
GB12 - Grid A-C, 1-6 | G-CON-6090 | GB12 Install Anchor Bolts/ Clean Up - Grid A-C, 1-6 | 2d | 09-Jan-24 | 10-Jan-24 | -31d
GB12 - Grid A-C, 1-6 | G-CON-6100 | GB12 Inspection - Grid A-C, 1-6 | 1d | 10-Jan-24 | 10-Jan-24 | -31d
GB12 - Grid A-C, 1-6 | G-CON-5470 | GB12 Set and Pour GB - Grid A-C, 1-6 | 3d | 11-Jan-24 | 15-Jan-24 | -31d
GB12 - Grid A-C, 1-6 | G-CON-5680 | GB12 Strip, Clean, & Move Formwork - Grid A-C, 1-6 | 1d | 16-Jan-24 | 16-Jan-24 | -31d
N/A | GB14 - Grid C-M, 1 | GB14 - Grid C-M, 1 | 9d | 15-Jan-24 | 25-Jan-24 | 104d
GB14 - Grid C-M, 1 | G-CON-7580 | GB14 Layout Grade Beams - Grid C-M, 1 | 1d | 15-Jan-24 | 15-Jan-24 | 102d
GB14 - Grid C-M, 1 | G-CON-7510 | GB14 Form One Side of GB & Install Void Form - Grid C-M, 1 | 1d | 16-Jan-24 | 16-Jan-24 | 102d
GB14 - Grid C-M, 1 | G-CON-7520 | GB14 Install Rebar for GB - Grid C-M, 1 | 2d | 17-Jan-24 | 18-Jan-24 | 102d
GB14 - Grid C-M, 1 | G-CON-7550 | GB14 Close Form for GB - Grid C-M, 1 | 2d | 18-Jan-24 | 19-Jan-24 | 102d
GB14 - Grid C-M, 1 | G-CON-7560 | GB14 Install Anchor Bolts/ Clean Up - Grid C-M, 1 | 2d | 18-Jan-24 | 19-Jan-24 | 104d
GB14 - Grid C-M, 1 | G-CON-7570 | GB14 Inspection - Grid C-M, 1 | 1d | 19-Jan-24 | 19-Jan-24 | 104d
GB14 - Grid C-M, 1 | G-CON-7530 | GB14 Set and Pour GB - Grid C-M, 1 | 3d | 22-Jan-24 | 24-Jan-24 | 104d
GB14 - Grid C-M, 1 | G-CON-7540 | GB14 Strip, Clean, & Move Formwork - Grid C-M, 1 | 1d | 25-Jan-24 | 25-Jan-24 | 104d
N/A | GB15 - Grid M-Q, 1-5 | GB15 - Grid M-Q, 1-5 | 10d | 16-Jan-24 | 29-Jan-24 | 102d
GB15 - Grid M-Q, 1-5 | G-CON-7660 | GB15 Layout Grade Beams - Grid M-Q, 1-5 | 1d | 16-Jan-24 | 16-Jan-24 | 102d
GB15 - Grid M-Q, 1-5 | G-CON-7590 | GB15 Form One Side of GB & Install Void Form - Grid M-Q, 1-5 | 1d | 17-Jan-24 | 17-Jan-24 | 102d
GB15 - Grid M-Q, 1-5 | G-CON-7600 | GB15 Install Rebar for GB - Grid M-Q, 1-5 | 2d | 18-Jan-24 | 19-Jan-24 | 103d
GB15 - Grid M-Q, 1-5 | G-CON-7630 | GB15 Close Form for GB - Grid M-Q, 1-5 | 2d | 22-Jan-24 | 23-Jan-24 | 102d
GB15 - Grid M-Q, 1-5 | G-CON-7640 | GB15 Install Anchor Bolts/ Clean Up - Grid M-Q, 1-5 | 2d | 22-Jan-24 | 23-Jan-24 | 102d
GB15 - Grid M-Q, 1-5 | G-CON-7650 | GB15 Inspection - Grid M-Q, 1-5 | 1d | 23-Jan-24 | 23-Jan-24 | 102d
GB15 - Grid M-Q, 1-5 | G-CON-7610 | GB15 Set and Pour GB - Grid M-Q, 1-5 | 3d | 24-Jan-24 | 26-Jan-24 | 102d
GB15 - Grid M-Q, 1-5 | G-CON-7620 | GB15 Strip, Clean, & Move Formwork - Grid M-Q, 1-5 | 1d | 29-Jan-24 | 29-Jan-24 | 102d
N/A | Crew 2 - Grade Beams & Pier Caps | Crew 2 - Grade Beams & Pier Caps | 36d | 20-Nov-23 | 12-Jan-24 | -29d
N/A | PC1 - Grid M-N,5-14 | PC1 - Grid M-N,5-14 | 7d | 20-Nov-23 | 30-Nov-23 | -17d
PC1 - Grid M-N,5-14 | G-CON-7030 | PC1 Layout Pier Caps - Grid M-N, 5-14 | 1d | 20-Nov-23 | 20-Nov-23 | -31d
PC1 - Grid M-N,5-14 | G-CON-7040 | PC1 Formwork Pier Caps & Install Void Form - Grid M -N, 5-14 | 1d | 21-Nov-23 | 21-Nov-23 | -31d
PC1 - Grid M-N,5-14 | G-CON-7050 | PC1 Install Rebar for Pier Caps - Grid M-N, 5-14 | 1d | 22-Nov-23 | 22-Nov-23 | -17d
PC1 - Grid M-N,5-14 | G-CON-7070 | PC1 Install Anchor Bolts/ Clean Up - Grid M-N, 5-14 | 1d | 27-Nov-23 | 27-Nov-23 | -17d
PC1 - Grid M-N,5-14 | G-CON-7080 | PC1 Inspection - Grid M-N, 5-14 | 1d | 28-Nov-23 | 28-Nov-23 | -17d
PC1 - Grid M-N,5-14 | G-CON-7090 | PC1 Set and Pour Pier Caps - Grid M-N, 5-14 | 1d | 29-Nov-23 | 29-Nov-23 | -17d
PC1 - Grid M-N,5-14 | G-CON-7100 | PC1 Strip, Clean, & Move Pier Caps Formwork - Grid M-N, 5-14 | 1d | 30-Nov-23 | 30-Nov-23 | -17d
N/A | GB3 - Grid R, 10-14 | GB3 - Grid R, 10-14 | 9d | 22-Nov-23 | 06-Dec-23 | -31d
GB3 - Grid R, 10-14 | G-CON-7340 | GB3 Layout Grade Beams - Grid R, 10-14 | 1d | 22-Nov-23 | 22-Nov-23 | -31d
GB3 - Grid R, 10-14 | G-CON-7270 | GB3 Form One Side of GB & Install Void Form - Grid R, 10-14 | 1d | 27-Nov-23 | 27-Nov-23 | -31d
GB3 - Grid R, 10-14 | G-CON-7280 | GB3 Install Rebar for GB - Grid R, 10-14 | 2d | 28-Nov-23 | 29-Nov-23 | -31d
GB3 - Grid R, 10-14 | G-CON-7310 | GB3 Close Form for GB - Grid R, 10-14 | 2d | 29-Nov-23 | 30-Nov-23 | -31d
GB3 - Grid R, 10-14 | G-CON-7320 | GB3 Install Anchor Bolts/ Clean Up - Grid R, 10-14 | 2d | 29-Nov-23 | 30-Nov-23 | -31d
GB3 - Grid R, 10-14 | G-CON-7330 | GB3 Inspection - Grid R, 10-14 | 1d | 30-Nov-23 | 30-Nov-23 | -31d
GB3 - Grid R, 10-14 | G-CON-7290 | GB3 Set and Pour GB - Grid R, 10-14 | 3d | 01-Dec-23 | 05-Dec-23 | -31d
GB3 - Grid R, 10-14 | G-CON-7300 | GB3 Strip, Clean, & Move Formwork - Grid R, 10-14 | 1d | 06-Dec-23 | 06-Dec-23 | -31d
N/A | GB5 - Grid N-R, 14-16 | GB5 - Grid N-R, 14-16 | 10d | 27-Nov-23 | 08-Dec-23 | -29d
GB5 - Grid N-R, 14-16 | G-CON-7420 | GB5 Layout Grade Beams - Grid N-R, 14-16 | 1d | 27-Nov-23 | 27-Nov-23 | -31d
GB5 - Grid N-R, 14-16 | G-CON-7350 | GB5 Form One Side of GB & Install Void Form - Grid N-R, 14-16 | 1d | 28-Nov-23 | 28-Nov-23 | -31d
GB5 - Grid N-R, 14-16 | G-CON-7360 | GB5 Install Rebar for GB - Grid N-R, 14-16 | 2d | 29-Nov-23 | 30-Nov-23 | -28d
GB5 - Grid N-R, 14-16 | G-CON-7390 | GB5 Close Form for GB - Grid N-R, 14-16 | 2d | 01-Dec-23 | 04-Dec-23 | -29d
GB5 - Grid N-R, 14-16 | G-CON-7400 | GB5 Install Anchor Bolts/ Clean Up - Grid N-R, 14-1 6 | 2d | 01-Dec-23 | 04-Dec-23 | -29d
GB5 - Grid N-R, 14-16 | G-CON-7410 | GB5 Inspection - Grid N-R, 14-16 | 1d | 04-Dec-23 | 04-Dec-23 | -29d
GB5 - Grid N-R, 14-16 | G-CON-7370 | GB5 Set and Pour GB - Grid N-R, 14-16 | 3d | 05-Dec-23 | 07-Dec-23 | -29d
GB5 - Grid N-R, 14-16 | G-CON-7380 | GB5 Strip, Clean, & Move Formwork - Grid N-R, 14-1 6 | 1d | 08-Dec-23 | 08-Dec-23 | -29d
N/A | GB7 - Grid J.1-P , 14-16 | GB7 - Grid J.1-P , 14-16 | 9d | 07-Dec-23 | 19-Dec-23 | -28d
GB7 - Grid J.1-P , 14-16 | G-CON-7500 | GB7 Layout Grade Beams - Grid J.1-P, 14-16 | 1d | 07-Dec-23 | 07-Dec-23 | -31d
GB7 - Grid J.1-P , 14-16 | G-CON-7430 | GB7 Form One Side of GB & Install Void Form - Grid J.1-P, 14-16 | 1d | 08-Dec-23 | 08-Dec-23 | -31d
GB7 - Grid J.1-P , 14-16 | G-CON-7440 | GB7 Install Rebar for GB - Grid J.1-P , 14-16 | 2d | 11-Dec-23 | 12-Dec-23 | -31d
GB7 - Grid J.1-P , 14-16 | G-CON-7470 | GB7 Close Form for GB - Grid J.1-P, 14-16 | 2d | 12-Dec-23 | 13-Dec-23 | -31d
GB7 - Grid J.1-P , 14-16 | G-CON-7480 | GB7 Install Anchor Bolts/ Clean Up - Grid J.1-P, 14 -16 | 2d | 12-Dec-23 | 13-Dec-23 | -28d
GB7 - Grid J.1-P , 14-16 | G-CON-7490 | GB7 Inspection - Grid J.1-P, 14-16 | 1d | 13-Dec-23 | 13-Dec-23 | -28d
GB7 - Grid J.1-P , 14-16 | G-CON-7450 | GB7 Set and Pour GB - Grid J.1-P, 14-16 | 3d | 14-Dec-23 | 18-Dec-23 | -28d
GB7 - Grid J.1-P , 14-16 | G-CON-7460 | GB7 Strip, Clean, & Move Formwork - Grid J.1-P, 14 -16 | 1d | 19-Dec-23 | 19-Dec-23 | -28d
N/A | GB9 - Grid J.1-L, 10-14 | GB9 - Grid J.1-L, 10-14 | 11d | 11-Dec-23 | 26-Dec-23 | -31d
GB9 - Grid J.1-L, 10-14 | G-CON-7740 | GB9 Layout Grade Beams - Grid J.1-L, 10-14 | 1d | 11-Dec-23 | 11-Dec-23 | -29d
GB9 - Grid J.1-L, 10-14 | G-CON-7670 | GB9 Form One Side of GB & Install Void Form - Grid J.1-L, 10-14 | 1d | 14-Dec-23 | 14-Dec-23 | -31d
GB9 - Grid J.1-L, 10-14 | G-CON-7680 | GB9 Install Rebar for GB - Grid J.1-L, 10-14 | 2d | 15-Dec-23 | 18-Dec-23 | -31d
GB9 - Grid J.1-L, 10-14 | G-CON-7710 | GB9 Close Form for GB - Grid J.1-L, 10-14 | 2d | 18-Dec-23 | 19-Dec-23 | -31d
GB9 - Grid J.1-L, 10-14 | G-CON-7720 | GB9 Install Anchor Bolts/ Clean Up - Grid J.1-L, 10 -14 | 2d | 18-Dec-23 | 19-Dec-23 | -31d
GB9 - Grid J.1-L, 10-14 | G-CON-7730 | GB9 Inspection - Grid J.1-L, 10-14 | 1d | 19-Dec-23 | 19-Dec-23 | -31d
GB9 - Grid J.1-L, 10-14 | G-CON-7690 | GB9 Set and Pour GB - Grid J.1-L, 10-14 | 3d | 20-Dec-23 | 22-Dec-23 | -31d
GB9 - Grid J.1-L, 10-14 | G-CON-7700 | GB9 Strip, Clean, & Move Formwork - Grid J.1-L, 10 -14 | 1d | 26-Dec-23 | 26-Dec-23 | -31d
N/A | PC11 - Grid B-L, 3-5 | PC11 - Grid B-L, 3-5 | 7d | 26-Dec-23 | 04-Jan-24 | -31d
PC11 - Grid B-L, 3-5 | G-CON-7110 | PC11 Layout Pier Caps - Grid B-L, 3-5 | 1d | 26-Dec-23 | 26-Dec-23 | -31d
PC11 - Grid B-L, 3-5 | G-CON-7120 | PC11 Formwork Pier Caps & Install Void Form - Grid B-L, 3-5 | 1d | 27-Dec-23 | 27-Dec-23 | -31d
PC11 - Grid B-L, 3-5 | G-CON-7130 | PC11 Install Rebar for Pier Caps - Grid B-L, 3-5 | 1d | 28-Dec-23 | 28-Dec-23 | -31d
PC11 - Grid B-L, 3-5 | G-CON-7140 | PC11 Install Anchor Bolts/ Clean Up - Grid B-L, 3-5 | 1d | 29-Dec-23 | 29-Dec-23 | -31d
PC11 - Grid B-L, 3-5 | G-CON-7150 | PC11 Inspection - Grid B-L, 3-5 | 1d | 02-Jan-24 | 02-Jan-24 | -31d
PC11 - Grid B-L, 3-5 | G-CON-7160 | PC11 Set and Pour Pier Caps - Grid B-L, 3-5 | 1d | 03-Jan-24 | 03-Jan-24 | -31d
PC11 - Grid B-L, 3-5 | G-CON-7170 | PC11 Strip, Clean, & Move Pier Caps Formwork - Grid B-L, 3-5 | 1d | 04-Jan-24 | 04-Jan-24 | -31d
N/A | PC13 - Grid L-N, 2-4 | PC13 - Grid L-N, 2-4 | 7d | 04-Jan-24 | 12-Jan-24 | -29d
PC13 - Grid L-N, 2-4 | G-CON-7180 | PC13 Layout Pier Caps - Grid L-N, 2-4 | 1d | 04-Jan-24 | 04-Jan-24 | -29d
PC13 - Grid L-N, 2-4 | G-CON-7190 | PC13 Formwork Pier Caps & Install Void Form - Grid L-N, 2-4 | 1d | 05-Jan-24 | 05-Jan-24 | -29d
PC13 - Grid L-N, 2-4 | G-CON-7200 | PC13 Install Rebar for Pier Caps - Grid L-N, 2-4 | 1d | 08-Jan-24 | 08-Jan-24 | -29d
PC13 - Grid L-N, 2-4 | G-CON-7210 | PC13 Install Anchor Bolts/ Clean Up - Grid L-N, 2-4 | 1d | 09-Jan-24 | 09-Jan-24 | -29d
PC13 - Grid L-N, 2-4 | G-CON-7220 | PC13 Inspection - Grid L-N, 2-4 | 1d | 10-Jan-24 | 10-Jan-24 | -29d
PC13 - Grid L-N, 2-4 | G-CON-7230 | PC13 Set and Pour Pier Caps - Grid L-N, 2-4 | 1d | 11-Jan-24 | 11-Jan-24 | -29d
PC13 - Grid L-N, 2-4 | G-CON-7240 | PC13 Strip, Clean, & Move Pier Caps Formwork - Grid L-N, 2-4 | 1d | 12-Jan-24 | 12-Jan-24 | -29d
N/A | SOG | SOG | 181d | 19-Dec-23 | 03-Sep-24 | -6d
N/A | SOG Pour #1 Grid L-Q, 10-15 | SOG Pour #1 Grid L-Q, 10-15 | 23d | 19-Dec-23 | 22-Jan-24 | -27d
SOG Pour #1 Grid L-Q, 10-15 | G-CON-6110 | Backfill & Rough Grade - SOG 1 - Grid L-Q, 10-15 | 5d | 19-Dec-23 | 26-Dec-23 | -29d
SOG Pour #1 Grid L-Q, 10-15 | G-CON-6160 | Granular Fill - SOG 1 - Grid L-Q, 10-15 | 4d | 27-Dec-23 | 02-Jan-24 | -29d
SOG Pour #1 Grid L-Q, 10-15 | G-CON-1610 | Electrical in Slab - SOG 1 - Grid L-Q, 10-15 | 3d | 03-Jan-24 | 05-Jan-24 | -27d
SOG Pour #1 Grid L-Q, 10-15 | G-CON-6800 | Plumbing in Slab - SOG 1 - Grid L-Q, 10-15 | 3d | 03-Jan-24 | 05-Jan-24 | -27d
SOG Pour #1 Grid L-Q, 10-15 | G-CON-1070 | Install Vapor Barrier - SOG 1 - Grid L-Q, 10-15 | 4d | 08-Jan-24 | 11-Jan-24 | -27d
SOG Pour #1 Grid L-Q, 10-15 | G-CON-1550 | Set Edge Form < 1' & Column Blockouts - SOG 1 - Gri d L-Q, 10-15 | 5d | 09-Jan-24 | 15-Jan-24 | -27d
SOG Pour #1 Grid L-Q, 10-15 | G-CON-1560 | Install Rebar & Slip Dowels - SOG 1 - Grid L-Q, 10- 15 | 4d | 12-Jan-24 | 17-Jan-24 | -27d
SOG Pour #1 Grid L-Q, 10-15 | G-CON-1570 | Install Hanging Form & Depressions - SOG 1 - Grid L -Q, 10-15 | 3d | 16-Jan-24 | 18-Jan-24 | -27d
SOG Pour #1 Grid L-Q, 10-15 | G-CON-1580 | Inspection & Clean Up - SOG 1 - Grid L-Q, 10-15 | 1d | 18-Jan-24 | 18-Jan-24 | -27d
SOG Pour #1 Grid L-Q, 10-15 | G-CON-1590 | Pour SOG - SOG 1 - Grid L-Q, 10-15 | 1d | 19-Jan-24 | 19-Jan-24 | -27d
SOG Pour #1 Grid L-Q, 10-15 | G-CON-1240 | Pour Waste Slab for Tilt - South & West | 1d | 22-Jan-24 | 22-Jan-24 | -27d
SOG Pour #1 Grid L-Q, 10-15 | G-CON-1600 | Strip/ Clean C.J. & Patch Vapor Barrier - SOG 1 - G rid L-Q, 10-15 | 1d | 22-Jan-24 | 22-Jan-24 | -27d
N/A | SOG Pour #2 Grid L-A, 6-1 | SOG Pour #2 Grid L-A, 6-1 | 26d | 05-Jan-24 | 09-Feb-24 | -30d
SOG Pour #2 Grid L-A, 6-1 | G-CON-6120 | Backfill & Rough Grade - SOG 2 - Grid L-A, 6-1 | 5d | 05-Jan-24 | 11-Jan-24 | -31d
SOG Pour #2 Grid L-A, 6-1 | G-CON-1040 | Granular Fill - SOG 2 - Grid L-A, 6-1 | 4d | 12-Jan-24 | 17-Jan-24 | -31d
SOG Pour #2 Grid L-A, 6-1 | G-CON-6650 | Electrical in Slab - SOG 2 - Grid L-A, 6-1 | 3d | 18-Jan-24 | 22-Jan-24 | -31d
SOG Pour #2 Grid L-A, 6-1 | G-CON-6810 | Plumbing in Slab - SOG 2 - Grid L-A, 6-1 | 3d | 18-Jan-24 | 22-Jan-24 | -31d
SOG Pour #2 Grid L-A, 6-1 | G-CON-6170 | Install Vapor Barrier - SOG 2 - Grid L-A, 6-1 | 4d | 23-Jan-24 | 26-Jan-24 | -31d
SOG Pour #2 Grid L-A, 6-1 | G-CON-6180 | Set Edge Form < 1' & Column Blockouts - SOG 2 - Gri d L-A, 6-1 | 5d | 26-Jan-24 | 01-Feb-24 | -31d
SOG Pour #2 Grid L-A, 6-1 | G-CON-6190 | Install Rebar & Slip Dowels - SOG 2 - Grid L-A, 6-1 | 4d | 31-Jan-24 | 05-Feb-24 | -31d
SOG Pour #2 Grid L-A, 6-1 | G-CON-6200 | Install Hanging Form & Depressions - SOG 2 - Grid L -A, 6-1 | 3d | 02-Feb-24 | 06-Feb-24 | -31d
SOG Pour #2 Grid L-A, 6-1 | G-CON-6210 | Inspection & Clean Up - SOG 2 - Grid L-A, 6-1 | 1d | 06-Feb-24 | 06-Feb-24 | -31d
SOG Pour #2 Grid L-A, 6-1 | G-CON-6220 | Pour SOG - SOG 2 - Grid L-A, 6-1 | 1d | 07-Feb-24 | 07-Feb-24 | -31d
SOG Pour #2 Grid L-A, 6-1 | G-CON-6240 | Pour Waste Slab for Tilt - Northwest | 1d | 08-Feb-24 | 08-Feb-24 | -31d
SOG Pour #2 Grid L-A, 6-1 | G-CON-6230 | Strip/ Clean C.J. & Patch Vapor Barrier - SOG 2 - G rid L-A, 6-1 | 2d | 08-Feb-24 | 09-Feb-24 | -30d
N/A | SOG Pour #3 Grid L-Q, 10-1 | SOG Pour #3 Grid L-Q, 10-1 | 28d | 17-Jan-24 | 23-Feb-24 | -31d
SOG Pour #3 Grid L-Q, 10-1 | G-CON-6130 | Backfill & Rough Grade - SOG 3 - Grid L-Q, 10-1 | 5d | 17-Jan-24 | 23-Jan-24 | -31d
SOG Pour #3 Grid L-Q, 10-1 | G-CON-7760 | Granular Fill - SOG 3 - Grid L-Q, 10-1 | 4d | 24-Jan-24 | 29-Jan-24 | -31d
SOG Pour #3 Grid L-Q, 10-1 | G-CON-6670 | Electrical in Slab - SOG 3 - Grid L-Q, 10-1 | 3d | 30-Jan-24 | 01-Feb-24 | -31d
SOG Pour #3 Grid L-Q, 10-1 | G-CON-6820 | Plumbing in Slab - SOG 3 - Grid L-Q, 10-1 | 3d | 30-Jan-24 | 01-Feb-24 | -31d
SOG Pour #3 Grid L-Q, 10-1 | G-CON-6260 | Install Vapor Barrier - SOG 3 - Grid L-Q, 10-1 | 5d | 02-Feb-24 | 08-Feb-24 | -31d
SOG Pour #3 Grid L-Q, 10-1 | G-CON-6270 | Set Edge Form < 1' & Column Blockouts - SOG 3 - Gri d L-Q, 10-1 | 7d | 07-Feb-24 | 15-Feb-24 | -31d
SOG Pour #3 Grid L-Q, 10-1 | G-CON-6280 | Install Rebar & Slip Dowels - SOG 3 - Grid L-Q, 10- 1 | 6d | 12-Feb-24 | 19-Feb-24 | -31d
SOG Pour #3 Grid L-Q, 10-1 | G-CON-6290 | Install Hanging Form & Depressions - SOG 3 - Grid L -Q, 10-1 | 4d | 14-Feb-24 | 19-Feb-24 | -31d
SOG Pour #3 Grid L-Q, 10-1 | G-CON-6300 | Inspection & Clean Up - SOG 3 - Grid L-Q, 10-1 | 1d | 19-Feb-24 | 19-Feb-24 | -31d
SOG Pour #3 Grid L-Q, 10-1 | G-CON-6310 | Pour SOG - SOG 3 - Grid L-Q, 10-1 | 1d | 20-Feb-24 | 20-Feb-24 | -31d
SOG Pour #3 Grid L-Q, 10-1 | G-CON-6330 | Pour Waste Slab for Tilt - North | 1d | 21-Feb-24 | 21-Feb-24 | -31d
SOG Pour #3 Grid L-Q, 10-1 | G-CON-6320 | Strip/ Clean C.J. & Patch Vapor Barrier - SOG 3 - G rid L-Q, 10-1 | 3d | 21-Feb-24 | 23-Feb-24 | -31d
N/A | SOG Pour #4 (After Steel) | SOG Pour #4 (After Steel) | 25d | 23-Jul-24 | 26-Aug-24 | -2d
SOG Pour #4 (After Steel) | G-CON-7810 | Plumbing Perimeter Trench Drain - Pour 4 | 6d | 23-Jul-24 | 30-Jul-24 | -6d
SOG Pour #4 (After Steel) | G-CON-7830 | Backfill Perimeter Trench Drain - Pour 4 | 3d | 31-Jul-24 | 02-Aug-24 | -4d
SOG Pour #4 (After Steel) | G-CON-6850 | Plumbing in Slab - Pour 4 | 4d | 06-Aug-24 | 09-Aug-24 | -5d
SOG Pour #4 (After Steel) | G-CON-6510 | Install Vapor Barrier - Pour 4 | 4d | 12-Aug-24 | 15-Aug-24 | -5d
SOG Pour #4 (After Steel) | G-CON-6520 | Set Edge Form < 1' & Column Blockouts - Pour 4 | 4d | 13-Aug-24 | 16-Aug-24 | -5d
SOG Pour #4 (After Steel) | G-CON-6530 | Install Rebar & Slip Dowels - Pour 4 | 4d | 16-Aug-24 | 21-Aug-24 | -5d
SOG Pour #4 (After Steel) | G-CON-6540 | Install Hanging Form & Depressions - Pour 4 | 3d | 20-Aug-24 | 22-Aug-24 | -4d
SOG Pour #4 (After Steel) | G-CON-6550 | Inspection & Clean Up - Pour 4 | 1d | 22-Aug-24 | 22-Aug-24 | -2d
SOG Pour #4 (After Steel) | G-CON-6560 | Pour SOG - Pour 4 | 1d | 23-Aug-24 | 23-Aug-24 | -2d
SOG Pour #4 (After Steel) | G-CON-6570 | Strip/ Clean C.J. & Patch Vapor Barrier - Pour 4 | 1d | 26-Aug-24 | 26-Aug-24 | -2d
N/A | SOG Pour #5 (After Steel) | SOG Pour #5 (After Steel) | 24d | 31-Jul-24 | 03-Sep-24 | -6d
SOG Pour #5 (After Steel) | G-CON-7820 | Plumbing Perimeter Trench Drain - Pour 5 | 6d | 31-Jul-24 | 07-Aug-24 | -6d
SOG Pour #5 (After Steel) | G-CON-7840 | Backfill Perimeter Trench Drain - Pour 5 | 3d | 08-Aug-24 | 12-Aug-24 | -6d
SOG Pour #5 (After Steel) | G-CON-6860 | Plumbing in Slab - Pour 5 | 4d | 13-Aug-24 | 16-Aug-24 | -6d
SOG Pour #5 (After Steel) | G-CON-6580 | Install Vapor Barrier - Pour 5 | 4d | 19-Aug-24 | 22-Aug-24 | -6d
SOG Pour #5 (After Steel) | G-CON-6590 | Set Edge Form < 1' & Column Blockouts - Pour 5 | 4d | 20-Aug-24 | 23-Aug-24 | -6d
SOG Pour #5 (After Steel) | G-CON-6600 | Install Rebar & Slip Dowels - Pour 5 | 4d | 23-Aug-24 | 28-Aug-24 | -6d
SOG Pour #5 (After Steel) | G-CON-6610 | Install Hanging Form & Depressions - Pour 5 | 3d | 27-Aug-24 | 29-Aug-24 | -6d
SOG Pour #5 (After Steel) | G-CON-6620 | Inspection & Clean Up - Pour 5 | 1d | 29-Aug-24 | 29-Aug-24 | -6d
SOG Pour #5 (After Steel) | G-CON-6630 | Pour SOG - Pour 5 | 1d | 30-Aug-24 | 30-Aug-24 | -6d
SOG Pour #5 (After Steel) | G-CON-6640 | Strip/ Clean C.J. & Patch Vapor Barrier - Pour 5 | 1d | 03-Sep-24 | 03-Sep-24 | -6d
N/A | Tilt Structure | Tilt Structure | 148d | 23-Jan-24 | 19-Aug-24 | 5d
N/A | Tilt Pour #01 Panels 1-21 | Tilt Pour #01 Panels 1-21 | 31d | 23-Jan-24 | 05-Mar-24 | 9d
Tilt Pour #01 Panels 1-21 | G-STRT-1000 | Layout Tilt Wall Panels - Panels 1-21 | 3d | 23-Jan-24 | 25-Jan-24 | -27d
Tilt Pour #01 Panels 1-21 | G-CON-1250 | Form Tilt Wall Panels - Panels 1-21 | 8d | 25-Jan-24 | 05-Feb-24 | -27d
Tilt Pour #01 Panels 1-21 | G-CON-1630 | Prep Slab & Install Embeds - Panels 1-21 | 5d | 30-Jan-24 | 05-Feb-24 | 8d
Tilt Pour #01 Panels 1-21 | G-STRT-1020 | Install Wire Mesh Arch Panel - Panels 1-21 | 3d | 06-Feb-24 | 08-Feb-24 | 8d
Tilt Pour #01 Panels 1-21 | G-STRT-1080 | Pour Arch Panel Install Insulation - Panels 1-21 | 1d | 09-Feb-24 | 09-Feb-24 | 8d
Tilt Pour #01 Panels 1-21 | G-STRT-1090 | Rebar Struct Panel - Panels 1-21 | 8d | 12-Feb-24 | 21-Feb-24 | 8d
Tilt Pour #01 Panels 1-21 | G-STRT-1030 | MEP/Embeds/Pick Inserts/ Brace Inserts - Panels 1-2 1 | 7d | 14-Feb-24 | 22-Feb-24 | 8d
Tilt Pour #01 Panels 1-21 | G-STRT-1040 | Pour Struct Panel - Panels 1-21 | 1d | 27-Feb-24 | 27-Feb-24 | 8d
Tilt Pour #01 Panels 1-21 | G-STRT-1050 | Cure Tilt Wall Panels - Panels 1-21 | 5d | 28-Feb-24 | 05-Mar-24 | 9d
N/A | Tilt Pour #02 Panels 22-41 | Tilt Pour #02 Panels 22-41 | 28d | 09-Feb-24 | 19-Mar-24 | -1d
Tilt Pour #02 Panels 22-41 | G-CON-6255 | Layout Tilt Wall Panels - Panels 22-41 | 3d | 09-Feb-24 | 13-Feb-24 | -31d
Tilt Pour #02 Panels 22-41 | G-CON-5810 | Form Tilt Wall Panels - Panels 22-41 | 8d | 13-Feb-24 | 22-Feb-24 | -31d
Tilt Pour #02 Panels 22-41 | G-CON-6340 | Prep Slab & Install Embeds - Panels 22-41 | 5d | 16-Feb-24 | 22-Feb-24 | -1d
Tilt Pour #02 Panels 22-41 | G-STRT-1100 | Install Wire Mesh Arch Panel - Panels 22-41 | 2d | 23-Feb-24 | 26-Feb-24 | -1d
Tilt Pour #02 Panels 22-41 | G-STRT-1110 | Pour Arch Panel Install Insulation - Panels 22-41 | 1d | 27-Feb-24 | 27-Feb-24 | -1d
Tilt Pour #02 Panels 22-41 | G-STRT-1120 | Rebar Struct Panel - Panels 22-41 | 8d | 28-Feb-24 | 08-Mar-24 | -1d
Tilt Pour #02 Panels 22-41 | G-STRT-1130 | MEP/Embeds/Pick Inserts/ Brace Inserts - Panels 22- 41 | 7d | 01-Mar-24 | 11-Mar-24 | -1d
Tilt Pour #02 Panels 22-41 | G-STRT-1060 | Pour Struct Panel - Panels 22-41 | 1d | 12-Mar-24 | 12-Mar-24 | -1d
Tilt Pour #02 Panels 22-41 | G-STRT-1070 | Cure Tilt Wall Panels - Panels 22-41 | 5d | 13-Mar-24 | 19-Mar-24 | -1d
N/A | Tilt Pour #03 Panels 42-62 | Tilt Pour #03 Panels 42-62 | 29d | 22-Feb-24 | 02-Apr-24 | -11d
Tilt Pour #03 Panels 42-62 | G-CON-6950 | Layout Tilt Wall Panels - Panels 42-62 | 3d | 22-Feb-24 | 26-Feb-24 | -31d
Tilt Pour #03 Panels 42-62 | G-CON-5820 | Form Tilt Wall Panels - Panels 42-62 | 8d | 26-Feb-24 | 06-Mar-24 | -31d
Tilt Pour #03 Panels 42-62 | G-CON-6960 | Prep Slab & Install Embeds - Panels 42-62 | 5d | 29-Feb-24 | 06-Mar-24 | -11d
Tilt Pour #03 Panels 42-62 | G-STRT-1140 | Install Wire Mesh Arch Panel - Panels 42-62 | 3d | 07-Mar-24 | 11-Mar-24 | -11d
Tilt Pour #03 Panels 42-62 | G-STRT-1150 | Pour Arch Panel Install Insulation - Panels 42-62 | 1d | 12-Mar-24 | 12-Mar-24 | -11d
Tilt Pour #03 Panels 42-62 | G-STRT-1160 | Rebar Struct Panel - Panels 42-62 | 8d | 13-Mar-24 | 22-Mar-24 | -11d
Tilt Pour #03 Panels 42-62 | G-STRT-1170 | MEP/Embeds/Pick Inserts/ Brace Inserts - Panels 42- 62 | 7d | 15-Mar-24 | 25-Mar-24 | -11d
Tilt Pour #03 Panels 42-62 | G-STRT-1180 | Pour Struct Panel - Panels 42-62 | 1d | 26-Mar-24 | 26-Mar-24 | -11d
Tilt Pour #03 Panels 42-62 | G-STRT-1190 | Cure Tilt Wall Panels - Panels 42-62 | 5d | 27-Mar-24 | 02-Apr-24 | -11d
N/A | Tilt Pour #04 Panels 63-81 | Tilt Pour #04 Panels 63-81 | 29d | 06-Mar-24 | 15-Apr-24 | -20d
Tilt Pour #04 Panels 63-81 | G-CON-6970 | Layout Tilt Wall Panels - Panels 63-81 | 3d | 06-Mar-24 | 08-Mar-24 | -31d
Tilt Pour #04 Panels 63-81 | G-CON-5830 | Form Tilt Wall Panels - Panels 63-81 | 8d | 08-Mar-24 | 19-Mar-24 | -31d
Tilt Pour #04 Panels 63-81 | G-CON-6980 | Prep Slab & Install Embeds - Panels 63-81 | 5d | 13-Mar-24 | 19-Mar-24 | -20d
Tilt Pour #04 Panels 63-81 | G-STRT-1200 | Install Wire Mesh Arch Panel - Panels 63-81 | 3d | 20-Mar-24 | 22-Mar-24 | -20d
Tilt Pour #04 Panels 63-81 | G-STRT-1210 | Pour Arch Panel Install Insulation - Panels 63-81 | 1d | 25-Mar-24 | 25-Mar-24 | -20d
Tilt Pour #04 Panels 63-81 | G-STRT-1220 | Rebar Struct Panel - Panels 63-81 | 8d | 26-Mar-24 | 04-Apr-24 | -20d
Tilt Pour #04 Panels 63-81 | G-STRT-1230 | MEP/Embeds/Pick Inserts/ Brace Inserts - Panels 63- 81 | 7d | 28-Mar-24 | 05-Apr-24 | -20d
Tilt Pour #04 Panels 63-81 | G-STRT-1240 | Pour Struct Panel - Panels 63-81 | 1d | 08-Apr-24 | 08-Apr-24 | -20d
Tilt Pour #04 Panels 63-81 | G-STRT-1250 | Cure Tilt Wall Panels - Panels 63-81 | 5d | 09-Apr-24 | 15-Apr-24 | -20d
N/A | Tilt Pour #05 Panels 82-100 | Tilt Pour #05 Panels 82-100 | 30d | 19-Mar-24 | 29-Apr-24 | -29d
Tilt Pour #05 Panels 82-100 | G-CON-6990 | Layout Tilt Wall Panels - Panels 82-100 | 3d | 19-Mar-24 | 21-Mar-24 | -31d
Tilt Pour #05 Panels 82-100 | G-CON-5840 | Form Tilt Wall Panels - Panels 82-100 | 8d | 22-Mar-24 | 02-Apr-24 | -31d
Tilt Pour #05 Panels 82-100 | G-CON-7000 | Prep Slab & Install Embeds - Panels 82-100 | 5d | 27-Mar-24 | 02-Apr-24 | -29d
Tilt Pour #05 Panels 82-100 | G-STRT-1260 | Install Wire Mesh Arch Panel - Panels 82-100 | 3d | 03-Apr-24 | 05-Apr-24 | -29d
Tilt Pour #05 Panels 82-100 | G-STRT-1270 | Pour Arch Panel Install Insulation - Panels 82-100 | 1d | 08-Apr-24 | 08-Apr-24 | -29d
Tilt Pour #05 Panels 82-100 | G-STRT-1280 | Rebar Struct Panel - Panels 82-100 | 8d | 09-Apr-24 | 18-Apr-24 | -29d
Tilt Pour #05 Panels 82-100 | G-STRT-1290 | MEP/Embeds/Pick Inserts/ Brace Inserts - Panels 82- 100 | 7d | 11-Apr-24 | 19-Apr-24 | -29d
Tilt Pour #05 Panels 82-100 | G-STRT-1300 | Pour Struct Panel - Panels 82-100 | 1d | 22-Apr-24 | 22-Apr-24 | -29d
Tilt Pour #05 Panels 82-100 | G-STRT-1310 | Cure Tilt Wall Panels - Panels 82-100 | 5d | 23-Apr-24 | 29-Apr-24 | -29d
N/A | Tilt Pour #06 Panels 101-106 | Tilt Pour #06 Panels 101-106 | 19d | 02-Apr-24 | 26-Apr-24 | -29d
Tilt Pour #06 Panels 101-106 | G-CON-7010 | Layout Tilt Wall Panels - Panels 101-106 | 1d | 02-Apr-24 | 02-Apr-24 | -31d
Tilt Pour #06 Panels 101-106 | G-CON-5850 | Form Tilt Wall Panels - Panels 101-106 | 3d | 03-Apr-24 | 05-Apr-24 | -31d
Tilt Pour #06 Panels 101-106 | G-CON-7020 | Prep Slab & Install Embeds - Panels 101-106 | 2d | 05-Apr-24 | 08-Apr-24 | -31d
Tilt Pour #06 Panels 101-106 | G-STRT-1320 | Install Wire Mesh Arch Panel - Panels 101-106 | 2d | 09-Apr-24 | 10-Apr-24 | -31d
Tilt Pour #06 Panels 101-106 | G-STRT-1330 | Pour Arch Panel Install Insulation - Panels 101-106 | 1d | 11-Apr-24 | 11-Apr-24 | -31d
Tilt Pour #06 Panels 101-106 | G-STRT-1340 | Rebar Struct Panel - Panels 101-106 | 3d | 12-Apr-24 | 16-Apr-24 | -31d
Tilt Pour #06 Panels 101-106 | G-STRT-1350 | MEP/Embeds/Pick Inserts/ Brace Inserts - Panels 101 -106 | 3d | 16-Apr-24 | 18-Apr-24 | -31d
Tilt Pour #06 Panels 101-106 | G-STRT-1360 | Pour Struct Panel - Panels 101-106 | 1d | 19-Apr-24 | 19-Apr-24 | -31d
Tilt Pour #06 Panels 101-106 | G-STRT-1370 | Cure Tilt Wall Panels - Panels 101-106 | 5d | 22-Apr-24 | 26-Apr-24 | -29d
N/A | Tilt Structure | Tilt Structure | 84d | 22-Apr-24 | 19-Aug-24 | 5d
Tilt Structure | G-CON-1680 | Prep for Tilt Erection | 5d | 22-Apr-24 | 26-Apr-24 | -31d
Tilt Structure | G-CON-1690 | Mobilize & Assemble Crane | 2d | 29-Apr-24 | 30-Apr-24 | -31d
Tilt Structure | G-CON-1360 | Erect Tilt Panels | 8d | 01-May-24 | 10-May-24 | -31d
Tilt Structure | G-CON-1700 | Disassemble & Mob-Out Crane | 2d | 13-May-24 | 14-May-24 | -15d
Tilt Structure | G-CON-1410 | Layout Walls & MEP Main Runs | 5d | 13-May-24 | 17-May-24 | 39d
Tilt Structure | G-CON-7750 | Electrical Rough-in in Pour Back Strips | 5d | 01-Jul-24 | 08-Jul-24 | -11d
Tilt Structure | G-CON-1370 | Backfill & Base Perimeter Strip | 15d | 24-Jun-24 | 15-Jul-24 | -21d
Tilt Structure | G-CON-1720 | Plumbing Rough-in in Pour Back Strips | 15d | 01-Jul-24 | 22-Jul-24 | -21d
Tilt Structure | G-CON-1260 | F/R/P/S Perimeter SOG Pour Back & Column Diamonds | 10d | 23-Jul-24 | 05-Aug-24 | -21d
Tilt Structure | G-CON-1110 | Masonry Walls ( Incld Door Frames) | 15d | 30-Jul-24 | 19-Aug-24 | -10d
Tilt Structure | G-CON-5020 | MEP Rough-in CMU Walls | 15d | 30-Jul-24 | 19-Aug-24 | 5d
N/A | Structural Steel | Structural Steel | 59d | 13-May-24 | 05-Aug-24 | 92d
N/A | Steel - Lot 1 Grid 1-10, Q-N | Steel - Lot 1 Grid 1-10, Q-N | 16d | 13-May-24 | 04-Jun-24 | -31d
Steel - Lot 1 Grid 1-10, Q-N | G-CON-1440 | Steel - Set Crane | 2d | 13-May-24 | 14-May-24 | -31d
Steel - Lot 1 Grid 1-10, Q-N | G-CON-1980 | Steel - Enabling Work - Lot 1 Grid 1-10, Q-N | 3d | 13-May-24 | 15-May-24 | -31d
Steel - Lot 1 Grid 1-10, Q-N | G-CON-1280 | Steel - Erect Columns & Framing - Lot 1 Grid 1-10, Q-N | 5d | 15-May-24 | 21-May-24 | -31d
Steel - Lot 1 Grid 1-10, Q-N | G-CON-1090 | Steel - Decking & Detailing - Lot 1 Grid 1-10, Q-N | 10d | 21-May-24 | 04-Jun-24 | -31d
N/A | Steel - Lot 2 Grid 10-16, R-N | Steel - Lot 2 Grid 10-16, R-N | 21d | 16-May-24 | 14-Jun-24 | -31d
Steel - Lot 2 Grid 10-16, R-N | G-CON-8090 | Steel - Enabling Work - Lot 2 Grid 10-16, R-N | 3d | 16-May-24 | 20-May-24 | -26d
Steel - Lot 2 Grid 10-16, R-N | G-CON-8100 | Steel - Erect Columns & Framing - Lot 2 Grid 10-16, R-N | 5d | 22-May-24 | 29-May-24 | -28d
Steel - Lot 2 Grid 10-16, R-N | G-CON-8110 | Steel - Decking & Detailing - Lot 2 Grid 10-16, R-N | 10d | 03-Jun-24 | 14-Jun-24 | -31d
N/A | Steel - Lot 3 Grid 16-10, N-J | Steel - Lot 3 Grid 16-10, N-J | 20d | 21-May-24 | 18-Jun-24 | -31d
Steel - Lot 3 Grid 16-10, N-J | G-CON-8120 | Steel - Enabling Work - Lot 3 Grid 16-10, N-J | 3d | 21-May-24 | 23-May-24 | -24d
Steel - Lot 3 Grid 16-10, N-J | G-CON-8140 | Steel - Erect Columns & Framing - Lot 3 Grid 16-10, N-J | 3d | 30-May-24 | 03-Jun-24 | -28d
Steel - Lot 3 Grid 16-10, N-J | G-CON-8160 | Steel - Decking & Detailing - Lot 3 Grid 16-10, N-J | 7d | 10-Jun-24 | 18-Jun-24 | -31d
N/A | Steel - Mezzanine - Lot 8 Grid 4-1, N-L | Steel - Mezzanine - Lot 8 Grid 4-1, N-L | 35d | 04-Jun-24 | 23-Jul-24 | -29d
Steel - Mezzanine - Lot 8 Grid 4-1, N-L | G-CON-5100 | Steel - Mezzanine Columns & Framing - Lot 8 Grid 4- 1, N-L | 3d | 04-Jun-24 | 06-Jun-24 | -28d
Steel - Mezzanine - Lot 8 Grid 4-1, N-L | G-CON-8240 | Steel - Mezzanine Decking & Detailing - Lot 8 Grid 4-1, N-L | 6d | 09-Jul-24 | 16-Jul-24 | -29d
Steel - Mezzanine - Lot 8 Grid 4-1, N-L | G-CON-8290 | Concrete - Rebar & Pour Mezzanine | 5d | 17-Jul-24 | 23-Jul-24 | -29d
N/A | Steel - Lot 4 Grid 10-3, N-L | Steel - Lot 4 Grid 10-3, N-L | 22d | 24-May-24 | 25-Jun-24 | -31d
Steel - Lot 4 Grid 10-3, N-L | G-CON-8130 | Steel - Enabling Work - Lot 4 Grid 10-3, N-L | 3d | 24-May-24 | 29-May-24 | -21d
Steel - Lot 4 Grid 10-3, N-L | G-CON-8150 | Steel - Erect Columns & Framing - Lot 4 Grid 10-3, N-L | 3d | 07-Jun-24 | 11-Jun-24 | -28d
Steel - Lot 4 Grid 10-3, N-L | G-CON-8170 | Steel - Decking & Detailing - Lot 4 Grid 10-3, N-L | 7d | 17-Jun-24 | 25-Jun-24 | -31d
N/A | Steel - Lot 5 Grid L-A, 6-3 | Steel - Lot 5 Grid L-A, 6-3 | 24d | 30-May-24 | 02-Jul-24 | -29d
Steel - Lot 5 Grid L-A, 6-3 | G-CON-8180 | Steel - Enabling Work - Lot 5 Grid L-A, 6-3 | 3d | 30-May-24 | 03-Jun-24 | -17d
Steel - Lot 5 Grid L-A, 6-3 | G-CON-8200 | Steel - Erect Columns & Framing - Lot 5 Grid 6-3, L -A | 3d | 12-Jun-24 | 14-Jun-24 | -24d
Steel - Lot 5 Grid L-A, 6-3 | G-CON-8220 | Steel - Decking & Detailing - Lot 5 Grid L-A, 6-3 | 7d | 24-Jun-24 | 02-Jul-24 | -29d
N/A | Steel - Lot 6 Grid 3-1, M-A | Steel - Lot 6 Grid 3-1, M-A | 26d | 04-Jun-24 | 10-Jul-24 | -29d
Steel - Lot 6 Grid 3-1, M-A | G-CON-8190 | Steel - Enabling Work - Lot 6 Grid 3-1, M-A | 3d | 04-Jun-24 | 06-Jun-24 | -15d
Steel - Lot 6 Grid 3-1, M-A | G-CON-8210 | Steel - Erect Columns & Framing - Lot 6 Grid 3-1, M -A | 3d | 17-Jun-24 | 19-Jun-24 | -22d
Steel - Lot 6 Grid 3-1, M-A | G-CON-8230 | Steel - Decking & Detailing - Lot 6 Grid 3-1, M-A | 7d | 01-Jul-24 | 10-Jul-24 | -29d
N/A | Steel - Eyebrow - Lot 7 Grid 10-3, N-L | Steel - Eyebrow - Lot 7 Grid 10-3, N-L | 41d | 07-Jun-24 | 05-Aug-24 | 92d
Steel - Eyebrow - Lot 7 Grid 10-3, N-L | G-CON-8250 | Steel - Enabling Work - Eyebrow - Lot 7 Grid 10-3, N-L | 4d | 07-Jun-24 | 12-Jun-24 | 113d
Steel - Eyebrow - Lot 7 Grid 10-3, N-L | G-CON-8260 | Steel - Erect Columns & Framing - Eyebrow - Lot 7 G rid 10-3, N-L | 5d | 20-Jun-24 | 26-Jun-24 | 106d
Steel - Eyebrow - Lot 7 Grid 10-3, N-L | G-CON-8270 | Steel - Decking & Detailing - Eyebrow - Lot 7 Grid 10-3, N-L | 15d | 16-Jul-24 | 05-Aug-24 | 92d
N/A | Roof / Skin Finishes | Roof / Skin Finishes | 73d | 05-Jun-24 | 17-Sep-24 | 86d
N/A | Roof - Zone 1 Grid 16-12 | Roof - Zone 1 Grid 16-12 | 42d | 19-Jun-24 | 16-Aug-24 | -1d
Roof - Zone 1 Grid 16-12 | G-CON-5120 | Elect - Stubups (Incld Lightning Protection) - Z1 G rids 16-12 | 2d | 19-Jun-24 | 20-Jun-24 | -14d
Roof - Zone 1 Grid 16-12 | G-CON-5080 | HVAC - Set Roof Curbs - Z1 Grids 16-12 | 3d | 19-Jun-24 | 21-Jun-24 | -15d
Roof - Zone 1 Grid 16-12 | G-CON-5110 | Plumb Stub Ups - Z1 Grids 16-12 | 3d | 19-Jun-24 | 21-Jun-24 | -15d
Roof - Zone 1 Grid 16-12 | G-CON-1100 | Roofing - Z1 Grids 16-12 | 10d | 24-Jun-24 | 08-Jul-24 | -15d
Roof - Zone 1 Grid 16-12 | G-CON-5040 | Set HVAC Gear - Z1 Grids 16-12 | 2d | 15-Aug-24 | 16-Aug-24 | -1d
N/A | Roof - Zone 2 Grid 12-7 | Roof - Zone 2 Grid 12-7 | 39d | 26-Jun-24 | 20-Aug-24 | -1d
Roof - Zone 2 Grid 12-7 | G-CON-7860 | Elect - Stubups (Incld Lightning Protection)- Z2 Gr id 12-7 | 2d | 26-Jun-24 | 27-Jun-24 | -9d
Roof - Zone 2 Grid 12-7 | G-CON-7850 | HVAC - Set Roof Curbs - Z2 Grid 12-7 | 3d | 26-Jun-24 | 28-Jun-24 | -10d
Roof - Zone 2 Grid 12-7 | G-CON-7870 | Plumb Stub Ups - Z2 Grid 12-7 | 3d | 26-Jun-24 | 28-Jun-24 | -10d
Roof - Zone 2 Grid 12-7 | G-CON-8350 | Roofing - Z2 Grid 12-7 | 10d | 09-Jul-24 | 22-Jul-24 | -15d
Roof - Zone 2 Grid 12-7 | G-CON-7880 | Set HVAC Gear - Z2 Grid 12-7 | 2d | 19-Aug-24 | 20-Aug-24 | -1d
N/A | Roof - Zone 3 Grid 7-1 | Roof - Zone 3 Grid 7-1 | 31d | 11-Jul-24 | 22-Aug-24 | -1d
Roof - Zone 3 Grid 7-1 | G-CON-7890 | HVAC - Set Roof Curbs - Z3 Grid 7-1 | 2d | 11-Jul-24 | 12-Jul-24 | -9d
Roof - Zone 3 Grid 7-1 | G-CON-7910 | Plumb Stub Ups - Z3 Grid 7-1 | 2d | 11-Jul-24 | 12-Jul-24 | -9d
Roof - Zone 3 Grid 7-1 | G-CON-7900 | Elect - Stubups (Incld Lightning Protection)- Z3 Gr id 7-1 | 2d | 11-Jul-24 | 12-Jul-24 | -9d
Roof - Zone 3 Grid 7-1 | G-CON-8360 | Roofing - Z3 Grid 7-1 | 11d | 23-Jul-24 | 06-Aug-24 | -15d
Roof - Zone 3 Grid 7-1 | G-CON-7920 | Set HVAC Gear - Z3 Grid 7-1 | 2d | 21-Aug-24 | 22-Aug-24 | -1d
N/A | Roof - Zone 4 Grid J-A | Roof - Zone 4 Grid J-A | 59d | 05-Jun-24 | 27-Aug-24 | -1d
Roof - Zone 4 Grid J-A | G-CON-7970 | Paint Booth Exhaust / Roof Stub Ups - Z4 Grid J-A | 3d | 05-Jun-24 | 07-Jun-24 | 41d
Roof - Zone 4 Grid J-A | G-CON-7950 | Plumb Stub Ups - Z4 Grid J-A | 2d | 15-Jul-24 | 16-Jul-24 | 15d
Roof - Zone 4 Grid J-A | G-CON-7940 | Elect - Stubups (Incld Lightning Protection)- Z4 Gr id J-A | 2d | 15-Jul-24 | 16-Jul-24 | 15d
Roof - Zone 4 Grid J-A | G-CON-7930 | HVAC - Set Roof Curbs - Z4 Grid J-A | 4d | 15-Jul-24 | 18-Jul-24 | 13d
Roof - Zone 4 Grid J-A | G-CON-8370 | Roofing - Z4 Grid J-A | 11d | 07-Aug-24 | 21-Aug-24 | 0d
Roof - Zone 4 Grid J-A | G-CON-7960 | Set HVAC Gear - Z4 Grid J-A | 3d | 23-Aug-24 | 27-Aug-24 | -1d
N/A | Roof / Skin Finishes | Roof / Skin Finishes | 73d | 05-Jun-24 | 17-Sep-24 | 86d
Roof / Skin Finishes | G-CON-1350 | Exterior Framing / Support Steel for Insulated Core Metal Panels at Entry & Strips to West & North | 15d | 05-Jun-24 | 25-Jun-24 | 3d
Roof / Skin Finishes | G-CON-1620 | Electrical Rough-in at Storefront | 4d | 26-Jun-24 | 01-Jul-24 | 4d
Roof / Skin Finishes | G-CON-1330 | Strorefront (Includes Entry Doors with Card Readers ) | 15d | 02-Jul-24 | 23-Jul-24 | 4d
Roof / Skin Finishes | G-CON-1390 | Exterior Coating | 20d | 16-Jul-24 | 12-Aug-24 | 5d
Roof / Skin Finishes | G-CON-1310 | Insulated Core Metal Panels | 15d | 24-Jul-24 | 13-Aug-24 | 4d
Roof / Skin Finishes | G-CON-1400 | Glass / Glazing in Wall Panels | 10d | 14-Aug-24 | 27-Aug-24 | 4d
Roof / Skin Finishes | G-CON-8030 | Electrical Exterior Trim & Lighting | 15d | 13-Aug-24 | 03-Sep-24 | 72d
Roof / Skin Finishes | G-CON-8280 | Steel - Stairs & Bollards | 8d | 04-Sep-24 | 13-Sep-24 | 88d
Roof / Skin Finishes | G-CON-1320 | Illuminated Signage | 10d | 04-Sep-24 | 17-Sep-24 | 72d
N/A | Interior Buildout | Interior Buildout | 156d | 17-Jun-24 | 28-Jan-25 | -5d
N/A | Rough-in | Rough-in | 124d | 17-Jun-24 | 11-Dec-24 | 13d
N/A | Rough-in - Zone 1 Grid 16-12 | Rough-in - Zone 1 Grid 16-12 | 123d | 17-Jun-24 | 10-Dec-24 | 14d
N/A | Rough-in - Zone 1 Grid 16-12 | Rough-in - Zone 1 Grid 16-12 | 72d | 17-Jun-24 | 26-Sep-24 | -4d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1000 | Fire Sprinkler Overhead Rough-in - Mains / Homeruns | 6d | 17-Jun-24 | 24-Jun-24 | -31d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1020 | HVAC Duct Overhead Rough-in | 7d | 25-Jun-24 | 03-Jul-24 | -31d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1010 | Electrical Overhead Rough-in - Mains / Homeruns | 15d | 17-Jun-24 | 08-Jul-24 | -28d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1130 | Fire Sprinkler Overhead Rough-in - Branches | 12d | 25-Jun-24 | 11-Jul-24 | -9d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1050 | Frame Priority Rooms ER, IDF, PPE (1116, 1115, 1120 ) | 3d | 16-Jul-24 | 18-Jul-24 | -21d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1060 | Hang Drywall Priority Rooms ER, IDF, PPE (1116, 111 5, 1120) | 2d | 19-Jul-24 | 22-Jul-24 | 4d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1030 | HVAC Pipe Overhead Rough-in | 14d | 02-Jul-24 | 22-Jul-24 | -31d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1040 | Plumbing Overhead Rough-in - Drains / Vents / Water | 12d | 05-Jul-24 | 22-Jul-24 | -24d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1090 | Frame Walls (Including Door Frames) | 4d | 23-Jul-24 | 26-Jul-24 | -23d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1070 | Tape & Finish Priority Rooms ER, IDF, PPE (1116, 11 15, 1120) | 4d | 23-Jul-24 | 26-Jul-24 | 4d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1140 | HVAC Duct & PipeTesting | 5d | 23-Jul-24 | 29-Jul-24 | -17d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1080 | Prime & First Coat Paint Priority Rooms ER, IDF, PP E (1116, 1115, 1120) | 2d | 29-Jul-24 | 30-Jul-24 | 4d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1410 | Plumbing Overhead Rough-in - Gas - Including Loadin g Bay Perimeter | 10d | 23-Jul-24 | 05-Aug-24 | -22d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1100 | I/W Plumbing Rough-in | 4d | 01-Aug-24 | 06-Aug-24 | -23d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1430 | Plumbing Pipe Testing | 5d | 07-Aug-24 | 13-Aug-24 | -21d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1160 | Prime & 1st Coat Paint - Structural, MEP | 7d | 06-Aug-24 | 14-Aug-24 | -22d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1170 | Hang Drywall | 4d | 15-Aug-24 | 20-Aug-24 | -22d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1120 | HVAC - Equipment (Hose Kits, IR Heaters, Unit Heate rs, Etc - Inlcd Loading Dock) | 10d | 15-Aug-24 | 28-Aug-24 | -14d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1180 | Tape & Finish Drywall | 8d | 21-Aug-24 | 30-Aug-24 | -22d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1190 | Prime & 1st Coat Paint - Walls & Finis hes | 8d | 03-Sep-24 | 12-Sep-24 | -19d
Rough-in - Zone 1 Grid 16-12 | G-RI-P-1200 | Electrical Branch / Surface Mount (Incld Fire Alarm ) | 10d | 13-Sep-24 | 26-Sep-24 | -4d
N/A | Provo ER - West Electrical Room 16M - GUB-01-1116 | Provo ER - West Electrical Room 16M - GUB-01-1116 | 82d | 31-Jul-24 | 22-Nov-24 | -15d
Provo ER - West Electrical Room 16M - GUB-01-1116 | G-RI-ER116-1000 | Set Equipment - GUB-01-1116 | 4d | 31-Jul-24 | 05-Aug-24 | 4d
Provo ER - West Electrical Room 16M - GUB-01-1116 | G-RI-ER116-1010 | Rough-in Conduit - GUB-01-1116 | 10d | 06-Aug-24 | 19-Aug-24 | 8d
Provo ER - West Electrical Room 16M - GUB-01-1116 | G-RI-ER116-1020 | Pull & T erm Wire - GUB-01-1116 | 10d | 20-Aug-24 | 03-Sep-24 | 8d
Provo ER - West Electrical Room 16M - GUB-01-1116 | G-RI-ER116-1030 | Testing & Energization - GUB-01-1116 | 1d | 22-Nov-24 | 22-Nov-24 | -15d
N/A | Provo PPE - PPE Storage Room - GUB-01-3C-1120 | Provo PPE - PPE Storage Room - GUB-01-3C-1120 | 82d | 31-Jul-24 | 22-Nov-24 | -15d
Provo PPE - PPE Storage Room - GUB-01-3C-1120 | G-RI-ER116-1040 | Set Equipment - GUB-01-3C-1120 | 4d | 31-Jul-24 | 05-Aug-24 | 4d
Provo PPE - PPE Storage Room - GUB-01-3C-1120 | G-RI-ER116-1050 | Rough-in Conduit - GUB-01-3C-1120 | 10d | 06-Aug-24 | 19-Aug-24 | 8d
Provo PPE - PPE Storage Room - GUB-01-3C-1120 | G-RI-ER116-1060 | Pull & T erm Wire - GUB-01-3C-1120 | 10d | 20-Aug-24 | 03-Sep-24 | 8d
Provo PPE - PPE Storage Room - GUB-01-3C-1120 | G-RI-ER116-1070 | Testing & Energization - GUB-01-3C-1120 | 1d | 22-Nov-24 | 22-Nov-24 | -15d
N/A | Provo - IDF Room GUB-01-1115 | Provo - IDF Room GUB-01-1115 | 88d | 06-Aug-24 | 10-Dec-24 | 14d
Provo - IDF Room GUB-01-1115 | G-RI-ER115-1000 | Set Equipment - GUB-01-1115 | 4d | 06-Aug-24 | 09-Aug-24 | 4d
Provo - IDF Room GUB-01-1115 | G-RI-ER115-1010 | Rough-in Conduit - GUB-01-1115 | 10d | 12-Aug-24 | 23-Aug-24 | 4d
Provo - IDF Room GUB-01-1115 | G-RI-ER115-1020 | Pull & T erm Wire - GUB-01-1115 | 10d | 26-Aug-24 | 09-Sep-24 | 4d
Provo - IDF Room GUB-01-1115 | G-RI-ER115-1030 | Testing & Energization - GUB-01-1115 | 1d | 02-Dec-24 | 02-Dec-24 | -15d
Provo - IDF Room GUB-01-1115 | G-CON-8580 | Startup Splits - GUB-01-1115 | 3d | 03-Dec-24 | 05-Dec-24 | 0d
Provo - IDF Room GUB-01-1115 | G-RI-ER115-1040 | Owner IT Equip - GUB-01-1115 | 3d | 06-Dec-24 | 10-Dec-24 | 14d
N/A | Rough-in - Zone 2 Grid 12-7 | Rough-in - Zone 2 Grid 12-7 | 88d | 28-Jun-24 | 31-Oct-24 | -19d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1210 | Fire Sprinkler Overhead Rough-in - Mains / Homeruns | 6d | 28-Jun-24 | 08-Jul-24 | -31d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1280 | Electrical Overhead Rough-in - Mains / Homeruns | 15d | 09-Jul-24 | 29-Jul-24 | -28d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1330 | HVAC Duct Overhead Rough-in | 15d | 09-Jul-24 | 29-Jul-24 | -31d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1400 | Fire Sprinkler Overhead Rough-in - Branches | 12d | 12-Jul-24 | 29-Jul-24 | -9d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1340 | HVAC Pipe Overhead Rough-in | 10d | 23-Jul-24 | 05-Aug-24 | -31d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1390 | HVAC Duct & PipeTesting | 5d | 06-Aug-24 | 12-Aug-24 | -19d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1350 | Plumbing Overhead Rough-in - Drains / Vents / Water | 12d | 30-Jul-24 | 14-Aug-24 | -29d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1420 | Plumbing Overhead Rough-in - Gas | 10d | 06-Aug-24 | 19-Aug-24 | -24d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1240 | Frame Walls (Including Door Frames) | 11d | 06-Aug-24 | 20-Aug-24 | -29d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1470 | Frame Ceilings | 2d | 21-Aug-24 | 22-Aug-24 | -20d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1250 | I/W Electrical Rough-in | 5d | 21-Aug-24 | 27-Aug-24 | -23d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1230 | Prime & 1st Coat Paint - Structural, MEP | 7d | 20-Aug-24 | 28-Aug-24 | -24d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1360 | I/W Plumbing Rough-in | 10d | 15-Aug-24 | 28-Aug-24 | -29d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1440 | Plumbing Pipe Testing | 5d | 29-Aug-24 | 05-Sep-24 | -29d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1380 | HVAC - Equipment (Hose Kits, IR Heaters, Unit Heate rs, Etc - Inlcd Loading Dock) | 10d | 29-Aug-24 | 12-Sep-24 | -14d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1260 | Hang Drywall Walls | 8d | 06-Sep-24 | 17-Sep-24 | -29d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1480 | Hang Drywall Ceilings | 2d | 18-Sep-24 | 19-Sep-24 | -13d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1270 | Tape & Finish Drywall Walls | 15d | 12-Sep-24 | 02-Oct-24 | -29d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1490 | Tape & Finish Drywall Ceilings | 3d | 03-Oct-24 | 07-Oct-24 | -22d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1220 | Prime & 1st Coat Paint - Walls & Ceilings | 11d | 03-Oct-24 | 17-Oct-24 | -25d
Rough-in - Zone 2 Grid 12-7 | G-RI-P-1370 | Electrical Branch / Surface Mount | 10d | 18-Oct-24 | 31-Oct-24 | -19d
N/A | Rough-in - Zone 3 Grid 7-1 | Rough-in - Zone 3 Grid 7-1 | 106d | 12-Jul-24 | 11-Dec-24 | 13d
N/A | Rough-in - Zone 3 Grid 7-1 | Rough-in - Zone 3 Grid 7-1 | 83d | 12-Jul-24 | 06-Nov-24 | -31d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1010 | Fire Sprinkler Overhead Rough-in - Mains / Homeruns | 10d | 12-Jul-24 | 25-Jul-24 | -29d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1060 | Frame Priority Rooms ER, MDF, IDF (1011, 1013, 1223 ) | 5d | 26-Jul-24 | 01-Aug-24 | -14d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1080 | Fire Sprinkler Overhead Rough-in - Branches | 8d | 30-Jul-24 | 08-Aug-24 | 0d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1090 | Hang Drywall Priority Rooms ER, MDF, IDF (1011, 101 3, 1223) | 4d | 07-Aug-24 | 12-Aug-24 | -15d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1000 | Electrical Overhead Rough-in - Mains / Homeruns | 12d | 30-Jul-24 | 14-Aug-24 | -28d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1020 | HVAC Equipment & Duct Overhead Rough-in | 15d | 30-Jul-24 | 19-Aug-24 | -31d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1030 | HVAC Pipe Overhead Rough-in - Mains | 10d | 06-Aug-24 | 19-Aug-24 | -31d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1130 | Tape & Finish Priority Rooms ER, MDF , IDF (1011, 10 13, 1223) | 8d | 13-Aug-24 | 22-Aug-24 | -15d
Rough-in - Zone 3 Grid 7-1 | G-RI-P-1450 | HVAC Duct & PipeTesting | 5d | 20-Aug-24 | 26-Aug-24 | -12d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1310 | Frame Priority Rooms Fire Pump, Mech (1017, 1014) | 5d | 20-Aug-24 | 26-Aug-24 | -31d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1160 | Prime & First Coat Paint Priority Rooms ER, MDF, ID F (1011, 1013, 1223) | 4d | 23-Aug-24 | 28-Aug-24 | -15d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1040 | Plumbing Overhead Rough-in - Drains / Vents / Water | 12d | 15-Aug-24 | 30-Aug-24 | -29d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1320 | Hang Drywall Priority Rooms Fire Pump, Mech (1017, 1014) | 4d | 27-Aug-24 | 30-Aug-24 | 2d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1100 | Plumbing Overhead Rough-in - Gas | 10d | 20-Aug-24 | 03-Sep-24 | -17d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1200 | HVAC Pipe Overhead Rough-in - Branches | 10d | 20-Aug-24 | 03-Sep-24 | -20d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1110 | Prime & 1st Coat Paint - Structural, MEP | 2d | 04-Sep-24 | 05-Sep-24 | -17d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1120 | Frame Walls (Including Door Frames) | 10d | 27-Aug-24 | 10-Sep-24 | -31d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1330 | Tape & Finish Priority Rooms Fire Pump, Mech (1017 , 1014) | 8d | 03-Sep-24 | 12-Sep-24 | 2d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1150 | I/W Electrical Rough-in | 10d | 04-Sep-24 | 17-Sep-24 | -25d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1140 | I/W Plumbing Rough-in | 10d | 05-Sep-24 | 18-Sep-24 | -31d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1340 | Prime & First Coat Paint Priority Rooms Fire Pump, Mech (1017, 1014) | 4d | 13-Sep-24 | 18-Sep-24 | 2d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1350 | Frame Ceilings | 6d | 11-Sep-24 | 18-Sep-24 | -13d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1050 | HVAC - Equipment (Hose Kits, IR Heaters, Unit Heate rs, Etc) | 8d | 13-Sep-24 | 24-Sep-24 | -3d
Rough-in - Zone 3 Grid 7-1 | G-RI-P-1460 | Plumbing Pipe Testing | 5d | 19-Sep-24 | 25-Sep-24 | -31d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1170 | Hang Drywall Walls | 12d | 26-Sep-24 | 11-Oct-24 | -31d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1360 | Hang Drywall Ceilings | 6d | 14-Oct-24 | 21-Oct-24 | -30d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1180 | Tape & Finish Drywall Walls | 12d | 07-Oct-24 | 22-Oct-24 | -31d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1370 | Tape & Finish Drywall Ceilings | 3d | 23-Oct-24 | 25-Oct-24 | -31d
Rough-in - Zone 3 Grid 7-1 | G-RI-A-1190 | Prime & 1st Coat Paint - Walls & Ceilings | 8d | 28-Oct-24 | 06-Nov-24 | -31d
N/A | Admin ER - Main Electrical Room 2M - GUB-01-1011 | Admin ER - Main Electrical Room 2M - GUB-01-1011 | 60d | 29-Aug-24 | 21-Nov-24 | -15d
Admin ER - Main Electrical Room 2M - GUB-01-1011 | G-RI-ER1011-1010 | Set Gear / Panels (SWB 3000A) - GUB-01-1011 | 5d | 29-Aug-24 | 05-Sep-24 | 11d
Admin ER - Main Electrical Room 2M - GUB-01-1011 | G-RI-ER1011-1000 | Set Equipment - GUB-01-1011 | 20d | 29-Aug-24 | 26-Sep-24 | -15d
Admin ER - Main Electrical Room 2M - GUB-01-1011 | G-RI-ER1011-1020 | Rough-in Conduit - GUB-01-1011 | 15d | 27-Sep-24 | 17-Oct-24 | -14d
Admin ER - Main Electrical Room 2M - GUB-01-1011 | G-RI-ER1011-1030 | Pull & T erm Wire - Elec t Room - GUB-01-1011 | 20d | 18-Oct-24 | 14-Nov-24 | -14d
Admin ER - Main Electrical Room 2M - GUB-01-1011 | G-RI-ER1011-1040 | Testing & Energization - GUB-01-1011 | 1d | 21-Nov-24 | 21-Nov-24 | -15d
N/A | Mechanical Room GUB-01-1014 | Mechanical Room GUB-01-1014 | 48d | 19-Sep-24 | 25-Nov-24 | 6d
Mechanical Room GUB-01-1014 | G-RI-A-1210 | Layout & Install Hangers & Supports | 3d | 19-Sep-24 | 23-Sep-24 | 2d
Mechanical Room GUB-01-1014 | G-RI-A-1220 | Mechanical Piping | 7d | 24-Sep-24 | 02-Oct-24 | 2d
Mechanical Room GUB-01-1014 | G-RI-A-1230 | Set HVAC Equipment - UH-118, ACU-108, ACU-109 | 4d | 03-Oct-24 | 08-Oct-24 | 2d
Mechanical Room GUB-01-1014 | G-RI-A-1300 | Electrical Rough-in - Conduit / Wire / Disconnects | 7d | 03-Oct-24 | 11-Oct-24 | 3d
Mechanical Room GUB-01-1014 | G-RI-A-1240 | Plumbing Rough-in - Water / Gas | 4d | 09-Oct-24 | 14-Oct-24 | 2d
Mechanical Room GUB-01-1014 | G-RI-A-1250 | Pour Housekeeping Pads | 2d | 15-Oct-24 | 16-Oct-24 | 2d
Mechanical Room GUB-01-1014 | G-RI-A-1260 | Cure Housekeeping Pads | 3d | 17-Oct-24 | 21-Oct-24 | 2d
Mechanical Room GUB-01-1014 | G-RI-A-1270 | Set Pumps - HHWB-101&102, HHWP-101&102, ET-101 | 5d | 22-Oct-24 | 28-Oct-24 | 2d
Mechanical Room GUB-01-1014 | G-RI-A-1280 | Mech - Final Equipment Connections | 5d | 29-Oct-24 | 04-Nov-24 | 2d
Mechanical Room GUB-01-1014 | G-RI-A-1290 | Electrical - Final Equipment Connections | 5d | 29-Oct-24 | 04-Nov-24 | 2d
Mechanical Room GUB-01-1014 | G-CON-8570 | Startup Splits - GUB-01-1014 | 3d | 21-Nov-24 | 25-Nov-24 | 6d
N/A | Admin - MDF Room GUB-01-1013 | Admin - MDF Room GUB-01-1013 | 50d | 27-Sep-24 | 09-Dec-24 | 15d
Admin - MDF Room GUB-01-1013 | G-RI-MDF1013-1000 | Set Equipment - GUB-01-1013 | 4d | 27-Sep-24 | 02-Oct-24 | -15d
Admin - MDF Room GUB-01-1013 | G-RI-MDF1013-1010 | Rough-in Conduit - GUB-01-1013 | 10d | 03-Oct-24 | 16-Oct-24 | -3d
Admin - MDF Room GUB-01-1013 | G-RI-MDF1013-1020 | Pull & T erm Wire - GUB-01-1013 | 10d | 17-Oct-24 | 30-Oct-24 | -3d
Admin - MDF Room GUB-01-1013 | G-RI-MDF1013-1030 | Testing & Energization - GUB-01-1013 | 1d | 27-Nov-24 | 27-Nov-24 | -15d
Admin - MDF Room GUB-01-1013 | G-CON-1820 | Startup CRACs | 3d | 02-Dec-24 | 04-Dec-24 | 1d
Admin - MDF Room GUB-01-1013 | G-RI-MDF1013-1040 | Owner IT Equip - GUB-01-1013 | 3d | 05-Dec-24 | 09-Dec-24 | 15d
N/A | Admin - Fire Pump Room GUB-01-1017 | Admin - Fire Pump Room GUB-01-1017 | 73d | 15-Aug-24 | 26-Nov-24 | -15d
Admin - Fire Pump Room GUB-01-1017 | G-RI-FP1017-1000 | Install Fire Pump | 4d | 15-Aug-24 | 20-Aug-24 | 27d
Admin - Fire Pump Room GUB-01-1017 | G-RI-FP1017-1010 | Set Equipment - GUB-01-1017 | 4d | 03-Oct-24 | 08-Oct-24 | -15d
Admin - Fire Pump Room GUB-01-1017 | G-RI-FP1017-1020 | Rough-in Conduit - GUB-01-1017 | 10d | 09-Oct-24 | 22-Oct-24 | -7d
Admin - Fire Pump Room GUB-01-1017 | G-RI-FP1017-1030 | Pull & T erm Wire - GUB-01-1017 | 10d | 23-Oct-24 | 05-Nov-24 | -7d
Admin - Fire Pump Room GUB-01-1017 | G-RI-FP1017-1040 | Testing & Energization - GUB-01-1017 | 1d | 26-Nov-24 | 26-Nov-24 | -15d
N/A | GSE - IDF Room GUB-01-1223 | GSE - IDF Room GUB-01-1223 | 44d | 09-Oct-24 | 11-Dec-24 | 13d
GSE - IDF Room GUB-01-1223 | G-RI-ER1223-1000 | Set Equipment - GUB-01-1223 | 4d | 09-Oct-24 | 14-Oct-24 | -15d
GSE - IDF Room GUB-01-1223 | G-RI-ER1223-1010 | Rough-in Conduit - GUB-01-1223 | 10d | 15-Oct-24 | 28-Oct-24 | -11d
GSE - IDF Room GUB-01-1223 | G-RI-ER1223-1020 | Pull & T erm Wire - GUB-01-1223 | 10d | 29-Oct-24 | 11-Nov-24 | -11d
GSE - IDF Room GUB-01-1223 | G-RI-ER1223-1030 | Testing & Energization - GUB-01-1223 | 1d | 03-Dec-24 | 03-Dec-24 | -15d
GSE - IDF Room GUB-01-1223 | G-CON-1830 | Startup Splits - GUB-01-1223 | 3d | 04-Dec-24 | 06-Dec-24 | -1d
GSE - IDF Room GUB-01-1223 | G-RI-ER1223-1040 | Owner IT Equp - GUB-01-1223 | 3d | 09-Dec-24 | 11-Dec-24 | 13d
N/A | Rough-in - Zone 4 Grid J-A | Rough-in - Zone 4 Grid J-A | 86d | 26-Jul-24 | 25-Nov-24 | -15d
N/A | Rough-in - Zone 4 Grid J-A | Rough-in - Zone 4 Grid J-A | 83d | 26-Jul-24 | 20-Nov-24 | -12d
Rough-in - Zone 4 Grid J-A | G-RI-G-1010 | Fire Sprinkler Overhead Rough-in - Mains / Homeruns | 12d | 26-Jul-24 | 12-Aug-24 | -15d
Rough-in - Zone 4 Grid J-A | G-RI-G-1000 | Electrical Overhead Rough-in - Mains / Homeruns | 15d | 08-Aug-24 | 28-Aug-24 | -2d
Rough-in - Zone 4 Grid J-A | G-RI-G-1120 | Fire Sprinkler Overhead Rough-in - Branches | 12d | 13-Aug-24 | 28-Aug-24 | 3d
Rough-in - Zone 4 Grid J-A | G-RI-G-1020 | HVAC Duct Overhead Rough-in (Including Paint Booth Duct) | 15d | 20-Aug-24 | 10-Sep-24 | -20d
Rough-in - Zone 4 Grid J-A | G-RI-G-1030 | HVAC Pipe Overhead Rough-in | 5d | 04-Sep-24 | 10-Sep-24 | -20d
Rough-in - Zone 4 Grid J-A | G-RI-G-1040 | Plumbing Overhead Rough-in - Drains / Vents / Water | 10d | 11-Sep-24 | 24-Sep-24 | -20d
Rough-in - Zone 4 Grid J-A | G-RI-G-1140 | Plumbing Overhead Rough-in - Gas | 10d | 11-Sep-24 | 24-Sep-24 | -15d
Rough-in - Zone 4 Grid J-A | G-RI-G-1050 | Frame Priority Rooms ER & IDF (1216) | 2d | 25-Sep-24 | 26-Sep-24 | -20d
Rough-in - Zone 4 Grid J-A | G-RI-G-1060 | Hang Drywall Priority Rooms ER & IDF (1216, 1223) | 2d | 27-Sep-24 | 30-Sep-24 | -11d
Rough-in - Zone 4 Grid J-A | G-RI-G-1090 | Frame Walls (Including Door Frames) | 3d | 27-Sep-24 | 01-Oct-24 | -20d
Rough-in - Zone 4 Grid J-A | G-RI-G-1210 | Plumbing Overhead Rough-in - Compressed Air | 15d | 11-Sep-24 | 01-Oct-24 | -20d
Rough-in - Zone 4 Grid J-A | G-RI-G-1220 | Frame Ceilings | 2d | 02-Oct-24 | 03-Oct-24 | -11d
Rough-in - Zone 4 Grid J-A | G-RI-G-1070 | Tape & Finish Priority Rooms ER & IDF (1216, 1223) | 4d | 01-Oct-24 | 04-Oct-24 | -11d
Rough-in - Zone 4 Grid J-A | G-RI-G-1160 | Prime & 1st Coat Paint - Structural, MEP | 5d | 02-Oct-24 | 08-Oct-24 | -20d
Rough-in - Zone 4 Grid J-A | G-RI-G-1080 | Prime & First Coat Paint Priority Rooms ER & IDF (1 216, 1223) | 2d | 07-Oct-24 | 08-Oct-24 | -11d
Rough-in - Zone 4 Grid J-A | G-RI-G-1150 | I/W Plumbing Rough-in | 5d | 02-Oct-24 | 08-Oct-24 | -20d
Rough-in - Zone 4 Grid J-A | G-RI-G-1170 | Hang Drywall Walls | 4d | 14-Oct-24 | 17-Oct-24 | -23d
Rough-in - Zone 4 Grid J-A | G-RI-G-1230 | Hang Drywall Ceilings | 2d | 18-Oct-24 | 21-Oct-24 | -21d
Rough-in - Zone 4 Grid J-A | G-RI-G-1100 | HVAC - Equipment (Hose Kits, IR Heaters, Unit Heate rs, Etc) | 12d | 09-Oct-24 | 24-Oct-24 | -13d
Rough-in - Zone 4 Grid J-A | G-RI-G-1180 | Tape & Finish Drywall Walls | 6d | 23-Oct-24 | 30-Oct-24 | -25d
Rough-in - Zone 4 Grid J-A | G-RI-G-1240 | Tape & Finish Drywall Ceilings | 3d | 31-Oct-24 | 04-Nov-24 | -25d
Rough-in - Zone 4 Grid J-A | G-RI-G-1190 | Prime & 1st Coat Paint - Walls & Finis hes | 5d | 07-Nov-24 | 13-Nov-24 | -27d
Rough-in - Zone 4 Grid J-A | G-RI-G-1200 | Electrical Branch / Surface Mount | 5d | 14-Nov-24 | 20-Nov-24 | -12d
N/A | GSE ER - North Electrical Room 2D - GUB-01-1216 | GSE ER - North Electrical Room 2D - GUB-01-1216 | 30d | 15-Oct-24 | 25-Nov-24 | -15d
GSE ER - North Electrical Room 2D - GUB-01-1216 | G-RI-ER1216-1000 | Set Equipment - GUB-01-1216 | 4d | 15-Oct-24 | 18-Oct-24 | -15d
GSE ER - North Electrical Room 2D - GUB-01-1216 | G-RI-ER1216-1010 | Rough-in Conduit - GUB-01-1216 | 10d | 21-Oct-24 | 01-Nov-24 | -15d
GSE ER - North Electrical Room 2D - GUB-01-1216 | G-RI-ER1216-1020 | Pull & T erm Wire - GUB-01-1216 | 10d | 04-Nov-24 | 15-Nov-24 | -15d
GSE ER - North Electrical Room 2D - GUB-01-1216 | G-RI-ER1216-1030 | Testing & Energization - GUB-01-1216 | 1d | 25-Nov-24 | 25-Nov-24 | -15d
N/A | Finishes - Zone 1 Grid 16-12 | Finishes - Zone 1 Grid 16-12 | 58d | 03-Sep-24 | 21-Nov-24 | 34d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1000 | Doors - Exterior (with Card Readers) | 3d | 13-Sep-24 | 17-Sep-24 | 12d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1010 | Chain Link | 5d | 13-Sep-24 | 19-Sep-24 | 79d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1040 | Tile | 15d | 03-Sep-24 | 23-Sep-24 | 1d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1020 | Ceiling Grid | 7d | 13-Sep-24 | 23-Sep-24 | -19d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1130 | HVAC Trim / Ceiling Devices - GRDs | 2d | 24-Sep-24 | 25-Sep-24 | -1d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1030 | Freezer | 10d | 13-Sep-24 | 26-Sep-24 | -19d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1050 | Casework | 10d | 13-Sep-24 | 26-Sep-24 | -2d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1060 | Doors - Interior (No Card Readers) | 3d | 24-Sep-24 | 26-Sep-24 | 30d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1070 | Install Baler & Misc Equipment | 10d | 13-Sep-24 | 26-Sep-24 | -9d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1090 | Warehous e Racking | 15d | 13-Sep-24 | 03-Oct-24 | 49d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1100 | Electrical Warehouse Lighting | 15d | 13-Sep-24 | 03-Oct-24 | -14d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1110 | Ice Machines | 10d | 27-Sep-24 | 10-Oct-24 | -19d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1120 | Door Hardware | 10d | 27-Sep-24 | 10-Oct-24 | 30d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1150 | Fire Sprinkler Ceiling Devices | 15d | 24-Sep-24 | 14-Oct-24 | -19d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1080 | Coiling Doors | 30d | 04-Sep-24 | 15-Oct-24 | -6d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1160 | Overhead MEP Inspection (Final Prior to White Out) | 2d | 15-Oct-24 | 16-Oct-24 | -14d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1170 | Lockers (200) | 25d | 13-Sep-24 | 17-Oct-24 | 29d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1180 | Specialties | 15d | 27-Sep-24 | 17-Oct-24 | -2d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1190 | Drop Ceiling Tiles | 5d | 17-Oct-24 | 23-Oct-24 | -14d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1210 | Carpet / LVT | 5d | 24-Oct-24 | 30-Oct-24 | 1d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1260 | Plumbing Trim | 5d | 24-Oct-24 | 30-Oct-24 | 1d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1580 | Fire Alarm Trim | 5d | 24-Oct-24 | 30-Oct-24 | 1d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1200 | Electrical Wire & Term Equipment | 15d | 11-Oct-24 | 31-Oct-24 | -19d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1240 | Clean / Polish Concrete | 10d | 24-Oct-24 | 06-Nov-24 | 40d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1250 | Security Trim / Card Readers | 10d | 24-Oct-24 | 06-Nov-24 | -14d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1230 | Electrical Trim | 5d | 01-Nov-24 | 07-Nov-24 | -9d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1220 | Dock Bumpers / Levelers | 20d | 16-Oct-24 | 12-Nov-24 | 16d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1270 | Final Paint | 5d | 08-Nov-24 | 14-Nov-24 | -5d
Finishes - Zone 1 Grid 16-12 | G-FN-P-1280 | Signage | 5d | 15-Nov-24 | 21-Nov-24 | 24d
N/A | Finishes - Zone 2 Grid 12-7 | Finishes - Zone 2 Grid 12-7 | 80d | 18-Sep-24 | 13-Jan-25 | 6d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1520 | Doors - Exterior (with Card Readers) | 3d | 18-Sep-24 | 20-Sep-24 | 44d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1410 | Ceiling Grid | 7d | 24-Sep-24 | 02-Oct-24 | -11d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1390 | Doors - Interior (No Card Readers) | 3d | 03-Oct-24 | 07-Oct-24 | 33d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1430 | HVAC Trim / Ceiling Devices - GRDs | 4d | 03-Oct-24 | 08-Oct-24 | 0d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1560 | Electrical Ceiling Devices - Lighting | 4d | 03-Oct-24 | 08-Oct-24 | 0d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1360 | Casework | 10d | 27-Sep-24 | 10-Oct-24 | 3d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1470 | Install Baler & Misc Equipment | 10d | 27-Sep-24 | 10-Oct-24 | -4d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1340 | Tile | 15d | 24-Sep-24 | 14-Oct-24 | 1d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1540 | Electrical Warehouse Lighting | 8d | 04-Oct-24 | 15-Oct-24 | -7d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1310 | Warehous e Racking | 15d | 04-Oct-24 | 24-Oct-24 | 49d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1400 | Door Hardware | 10d | 11-Oct-24 | 24-Oct-24 | 30d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1570 | Fire Sprinkler Ceiling Devices | 15d | 15-Oct-24 | 04-Nov-24 | -19d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1510 | Overhead MEP Inspection (Final Prior to White Out) | 2d | 05-Nov-24 | 06-Nov-24 | -19d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1480 | Specialties | 15d | 18-Oct-24 | 07-Nov-24 | -2d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1420 | Drop Ceiling Tiles | 5d | 07-Nov-24 | 13-Nov-24 | -19d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1590 | Fire Alarm Trim | 4d | 14-Nov-24 | 19-Nov-24 | -8d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1350 | Carpet / LVT | 5d | 14-Nov-24 | 20-Nov-24 | -9d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1500 | Plumbing Trim | 5d | 14-Nov-24 | 20-Nov-24 | -9d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1330 | Lockers (200) | 25d | 18-Oct-24 | 21-Nov-24 | 29d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1530 | Electrical Wire & Term Equipment | 15d | 01-Nov-24 | 21-Nov-24 | -19d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1290 | Coiling Doors | 30d | 16-Oct-24 | 26-Nov-24 | 6d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1490 | Security Trim / Card Readers | 10d | 14-Nov-24 | 27-Nov-24 | -19d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1550 | Electrical Trim | 4d | 22-Nov-24 | 27-Nov-24 | -19d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1460 | Final Paint | 5d | 02-Dec-24 | 06-Dec-24 | -14d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1380 | Signage | 5d | 09-Dec-24 | 13-Dec-24 | 15d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1440 | Chain Link | 5d | 09-Dec-24 | 13-Dec-24 | 25d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1370 | Dock Bumpers / Levelers | 20d | 27-Nov-24 | 27-Dec-24 | 6d
Finishes - Zone 2 Grid 12-7 | G-FN-P-1450 | Clean / Polish Concrete | 10d | 30-Dec-24 | 13-Jan-25 | 6d
N/A | Finishes - Zone 3 Grid 7-1 | Finishes - Zone 3 Grid 7-1 | 69d | 11-Oct-24 | 21-Jan-25 | 0d
Finishes - Zone 3 Grid 7-1 | G-FN-P-1600 | Electrical Warehouse Lighting | 5d | 16-Oct-24 | 22-Oct-24 | 11d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1000 | Casework | 10d | 11-Oct-24 | 24-Oct-24 | 8d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1030 | Doors - Interior (No Card Readers) | 5d | 25-Oct-24 | 31-Oct-24 | 25d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1020 | Tile | 15d | 15-Oct-24 | 04-Nov-24 | 1d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1050 | Door Hardware | 10d | 01-Nov-24 | 14-Nov-24 | 25d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1010 | Ceiling Grid | 10d | 07-Nov-24 | 20-Nov-24 | -31d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1190 | Electrical Wire & Term Equipment | 5d | 15-Nov-24 | 21-Nov-24 | -9d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1060 | HVAC Trim / Ceiling Devices - GRDs | 5d | 21-Nov-24 | 27-Nov-24 | -26d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1070 | Electrical Ceiling Devices - Lighting | 5d | 21-Nov-24 | 27-Nov-24 | -26d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1090 | Specialties | 15d | 08-Nov-24 | 02-Dec-24 | -2d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1080 | Fire Sprinkler Ceiling Devices | 10d | 21-Nov-24 | 06-Dec-24 | -31d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1040 | Lockers (50) | 10d | 22-Nov-24 | 09-Dec-24 | 29d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1100 | Overhead MEP Inspection | 2d | 09-Dec-24 | 10-Dec-24 | -31d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1110 | Drop Ceiling Tiles | 5d | 11-Dec-24 | 17-Dec-24 | -31d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1120 | Carpet / LVT | 5d | 18-Dec-24 | 24-Dec-24 | -26d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1130 | Plumbing Trim | 5d | 18-Dec-24 | 24-Dec-24 | -26d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1140 | Security Trim / Card Readers | 10d | 18-Dec-24 | 02-Jan-25 | -31d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1150 | Electrical Trim | 10d | 18-Dec-24 | 02-Jan-25 | -31d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1180 | Fire Alarm Trim | 10d | 18-Dec-24 | 02-Jan-25 | -31d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1160 | Final Paint | 8d | 03-Jan-25 | 14-Jan-25 | -31d
Finishes - Zone 3 Grid 7-1 | G-FN-A-1170 | Signage | 5d | 15-Jan-25 | 21-Jan-25 | -5d
N/A | Finishes - Zone 4 Grid J-A | Finishes - Zone 4 Grid J-A | 109d | 22-Aug-24 | 28-Jan-25 | -5d
Finishes - Zone 4 Grid J-A | G-FN-G-1130 | Bridge Crane (x3) | 25d | 22-Aug-24 | 26-Sep-24 | 27d
Finishes - Zone 4 Grid J-A | G-FN-P-1610 | Electrical Warehouse Lighting | 10d | 25-Oct-24 | 07-Nov-24 | 9d
Finishes - Zone 4 Grid J-A | G-FN-G-1070 | Coiling Doors | 20d | 16-Oct-24 | 12-Nov-24 | -6d
Finishes - Zone 4 Grid J-A | G-FN-G-1010 | Tile | 3d | 14-Nov-24 | 18-Nov-24 | 2d
Finishes - Zone 4 Grid J-A | G-FN-G-1020 | Doors - Exterior (with Card Readers) | 3d | 14-Nov-24 | 18-Nov-24 | 1d
Finishes - Zone 4 Grid J-A | G-FN-G-1040 | Warehous e Racking | 5d | 14-Nov-24 | 20-Nov-24 | 40d
Finishes - Zone 4 Grid J-A | G-FN-G-1050 | Chain Link | 5d | 14-Nov-24 | 20-Nov-24 | 40d
Finishes - Zone 4 Grid J-A | G-FN-G-1060 | Casework | 3d | 19-Nov-24 | 21-Nov-24 | 2d
Finishes - Zone 4 Grid J-A | G-FN-G-1090 | Specialties | 1d | 22-Nov-24 | 22-Nov-24 | 2d
Finishes - Zone 4 Grid J-A | G-FN-G-1030 | Steel - Handrail | 8d | 14-Nov-24 | 25-Nov-24 | 21d
Finishes - Zone 4 Grid J-A | G-FN-G-1000 | Doors - Interior (No Card Readers) | 3d | 21-Nov-24 | 25-Nov-24 | 18d
Finishes - Zone 4 Grid J-A | G-FN-G-1100 | Door Hardware | 5d | 26-Nov-24 | 04-Dec-24 | 18d
Finishes - Zone 4 Grid J-A | G-FN-G-1140 | HVAC Trim / Ceiling Devices - GRDs | 3d | 02-Dec-24 | 04-Dec-24 | -7d
Finishes - Zone 4 Grid J-A | G-FN-G-1110 | Auto Lifts | 15d | 14-Nov-24 | 06-Dec-24 | -22d
Finishes - Zone 4 Grid J-A | G-FN-G-1120 | BP Fuild Systems Install | 20d | 14-Nov-24 | 13-Dec-24 | -27d
Finishes - Zone 4 Grid J-A | G-FN-G-1150 | Electrical Ceiling Devices - Lighting | 10d | 02-Dec-24 | 13-Dec-24 | -15d
Finishes - Zone 4 Grid J-A | G-FN-G-1080 | Paint Booth | 35d | 30-Oct-24 | 19-Dec-24 | 11d
Finishes - Zone 4 Grid J-A | G-FN-G-1250 | Electrical Wire & Term - Paint Booth Equipment | 3d | 20-Dec-24 | 24-Dec-24 | 11d
Finishes - Zone 4 Grid J-A | G-FN-G-1160 | Fire Sprinkler Ceiling Devices | 15d | 09-Dec-24 | 30-Dec-24 | -24d
Finishes - Zone 4 Grid J-A | G-FN-G-1220 | Electrical Wire & Term Equipment | 12d | 16-Dec-24 | 02-Jan-25 | -27d
Finishes - Zone 4 Grid J-A | G-FN-G-1170 | Clean / Polish Concrete | 10d | 20-Dec-24 | 06-Jan-25 | 11d
Finishes - Zone 4 Grid J-A | G-FN-G-1180 | Plumbing Trim | 3d | 03-Jan-25 | 07-Jan-25 | -26d
Finishes - Zone 4 Grid J-A | G-FN-G-1200 | Electrical Trim | 4d | 03-Jan-25 | 08-Jan-25 | -27d
Finishes - Zone 4 Grid J-A | G-FN-G-1240 | Fire Alarm Trim | 4d | 03-Jan-25 | 08-Jan-25 | -27d
Finishes - Zone 4 Grid J-A | G-FN-G-1190 | Security Trim / Card Readers | 5d | 03-Jan-25 | 09-Jan-25 | -28d
Finishes - Zone 4 Grid J-A | G-FN-G-1210 | Final Paint | 5d | 15-Jan-25 | 21-Jan-25 | -31d
Finishes - Zone 4 Grid J-A | G-FN-G-1230 | Signage | 5d | 22-Jan-25 | 28-Jan-25 | -5d
N/A | Sitework | Sitework | 115d | 05-Jun-24 | 14-Nov-24 | 44d
Sitework | G-CON-1430 | Demo Waste Slabs | 3d | 05-Jun-24 | 07-Jun-24 | 33d
Sitework | G-CON-1710 | Drilled Piers at Utility Yard | 4d | 10-Jun-24 | 13-Jun-24 | 33d
Sitework | G-CON-1270 | Site Walls (~1800 LF) | 20d | 14-Jun-24 | 12-Jul-24 | 33d
Sitework | G-CON-1300 | Bollards / Light Poles Bases / Misc Site Items | 20d | 14-Jun-24 | 12-Jul-24 | 72d
Sitework | G-CON-1130 | Install New AOA Fence | 5d | 29-Jul-24 | 02-Aug-24 | 88d
Sitework | G-CON-1120 | Site Grading | 10d | 24-Jul-24 | 06-Aug-24 | 26d
Sitework | G-CON-5030 | Sleeves | 5d | 07-Aug-24 | 13-Aug-24 | 60d
Sitework | G-CON-1960 | Site Lighting | 15d | 07-Aug-24 | 27-Aug-24 | 40d
Sitework | G-CON-1340 | AOA Entries | 15d | 14-Aug-24 | 04-Sep-24 | 81d
Sitework | G-CON-1140 | Curbs & Gutters | 15d | 12-Sep-24 | 02-Oct-24 | 30d
Sitework | G-CON-5050 | Concrete Paving | 20d | 12-Sep-24 | 09-Oct-24 | 40d
Sitework | G-CON-1380 | Asphalt Paving | 15d | 03-Oct-24 | 23-Oct-24 | 30d
Sitework | G-CON-1500 | Set Generator | 1d | 24-Oct-24 | 24-Oct-24 | 30d
Sitework | G-CON-5190 | Generator - Pull / Term | 10d | 25-Oct-24 | 07-Nov-24 | 30d
Sitework | G-CON-1150 | Landscape | 15d | 24-Oct-24 | 13-Nov-24 | 45d
Sitework | G-CON-5200 | Generator - Test | 5d | 08-Nov-24 | 14-Nov-24 | 30d
N/A | Startup & Commissioning | Startup & Commissioning | 79d | 18-Nov-24 | 12-Mar-25 | 37d
N/A | Equip Startup | Equip Startup | 40d | 18-Nov-24 | 16-Jan-25 | 56d
Equip Startup | G-CON-1950 | Partial Final Electrical Inspection - ER / IDF / MD F | 1d | 18-Nov-24 | 18-Nov-24 | -15d
Equip Startup | G-CON-1490 | *Milestone: Permanent Power Established from Xcel t o Site | 0d | 20-Nov-24 |  | -10d
Equip Startup | G-CON-1860 | Startup Pumps | 2d | 22-Nov-24 | 25-Nov-24 | -11d
Equip Startup | G-CON-1920 | Startup HVLV Big Fans | 2d | 25-Nov-24 | 26-Nov-24 | 89d
Equip Startup | G-CON-1970 | Startup Electrical - Generator / ATS / MTS | 5d | 22-Nov-24 | 02-Dec-24 | 25d
Equip Startup | G-CON-1510 | *Milestone: Ready for Permanent Power in Building | 0d | 03-Dec-24 |  | 19d
Equip Startup | G-CON-1900 | Startup Air Compressors (by Manufacturer) | 2d | 04-Dec-24 | 05-Dec-24 | 84d
Equip Startup | G-CON-1850 | Startup Exhaust Fans | 3d | 04-Dec-24 | 06-Dec-24 | 7d
Equip Startup | G-CON-1870 | Startup Boilers (by Manufacturer) | 3d | 04-Dec-24 | 06-Dec-24 | -6d
Equip Startup | G-CON-1810 | Startup AHUs (by Manufacturer) | 5d | 04-Dec-24 | 10-Dec-24 | -1d
Equip Startup | G-CON-1840 | Startup HVU / HRHVU & IR Heaters (by Manufacturer) | 5d | 04-Dec-24 | 10-Dec-24 | -1d
Equip Startup | G-CON-1910 | Startup VAVs | 10d | 04-Dec-24 | 17-Dec-24 | -15d
Equip Startup | G-CON-8560 | Startup Paint Booth (by Manufacturer) | 2d | 26-Dec-24 | 27-Dec-24 | 11d
Equip Startup | G-CON-8080 | Start-up Misc Equip (Paint Booth / Auto Lift / Etc) | 15d | 09-Dec-24 | 30-Dec-24 | 10d
Equip Startup | G-CON-1880 | Startup HWU Heaters | 2d | 03-Jan-25 | 06-Jan-25 | -25d
Equip Startup | G-CON-8060 | Start-up Fire Sprinkler | 5d | 31-Dec-24 | 07-Jan-25 | 5d
Equip Startup | G-CON-1890 | Startup EU Heaters | 2d | 07-Jan-25 | 08-Jan-25 | 62d
Equip Startup | G-CON-1160 | Start-up Security | 5d | 10-Jan-25 | 16-Jan-25 | -6d
N/A | Life Safety | Life Safety | 54d | 03-Dec-24 | 18-Feb-25 | -25d
Life Safety | G-CON-8620 | Life Safety - Generator / ATS | 1d | 03-Dec-24 | 03-Dec-24 | 25d
Life Safety | G-CON-8610 | Life Safety - Fire Sprinkler | 1d | 31-Dec-24 | 31-Dec-24 | 6d
Life Safety | G-CON-8070 | Final Electrical Inspection - Entire Building | 1d | 09-Jan-25 | 09-Jan-25 | 3d
Life Safety | G-CON-8590 | Life Safety - Doors / Egress Signage Testing & Insp ection | 1d | 17-Jan-25 | 17-Jan-25 | -6d
Life Safety | G-CON-2000 | Life Safety - Duct Detector DP T esting | 2d | 03-Feb-25 | 04-Feb-25 | -25d
Life Safety | G-CON-8600 | Life Safety - Mechanical Dampers / Unit Shunt Trip | 1d | 05-Feb-25 | 05-Feb-25 | -19d
Life Safety | G-CON-8050 | Life Safety - Final Fire Alarm Inspection | 1d | 13-Feb-25 | 13-Feb-25 | -25d
Life Safety | G-CON-8040 | Life Safety - Final Building | 3d | 14-Feb-25 | 18-Feb-25 | -25d
N/A | Test & Balance | Test & Balance | 27d | 07-Jan-25 | 12-Feb-25 | -31d
Test & Balance | G-CON-1760 | Test & Balance - Wet (Entire Building) Pumps, Boile rs, HW U | 5d | 07-Jan-25 | 13-Jan-25 | -25d
Test & Balance | G-CON-1770 | Test & Balance - Air - CRAC & Split Units | 2d | 22-Jan-25 | 23-Jan-25 | -31d
Test & Balance | G-CON-1780 | Test & Balance - Air - AHU, HVU, HRHVU, VAVs | 6d | 24-Jan-25 | 31-Jan-25 | -31d
Test & Balance | G-CON-1790 | Test & Balance - Air - Exhaust Fans | 6d | 03-Feb-25 | 10-Feb-25 | -31d
Test & Balance | G-CON-1800 | Test & Balance - Final Building Balance | 2d | 11-Feb-25 | 12-Feb-25 | -31d
N/A | Commissioning | Commissioning | 20d | 13-Feb-25 | 12-Mar-25 | 37d
Commissioning | G-CON-1990 | HVAC Submit & Review Test & Balance Report | 10d | 13-Feb-25 | 26-Feb-25 | -31d
Commissioning | G-CON-1940 | Sequence of Operations / Final Commissioning | 20d | 13-Feb-25 | 12-Mar-25 | 37d
N/A | Substantial Completion | Substantial Completion | 47d | 27-Feb-25 | 02-May-25 | 0d
Substantial Completion | G-CON-1170 | Final Inspections (TCO) | 5d | 27-Feb-25 | 05-Mar-25 | -31d
Substantial Completion | G-CON-1180 | Punchlist & Corrections | 10d | 06-Mar-25 | 19-Mar-25 | -31d
Substantial Completion | G-CON-1190 | Removal of Temp AOA | 2d | 20-Mar-25 | 21-Mar-25 | -31d
Substantial Completion | G-CON-1420 | Owner Supplied Furniture & Office Equipment - Insta ll | 10d | 20-Mar-25 | 02-Apr-25 | 22d
Substantial Completion | G-CON-1200 | Weather | 15d | 24-Mar-25 | 11-Apr-25 | -31d
Substantial Completion | G-CON-1210 | *Milestone: Substantial Completion | 0d | 11-Apr-25 |  | -31d
Substantial Completion | G-CON-1530 | Owner Move-in, Finalize & Prep for Beneficial Occup ancy | 15d | 14-Apr-25 | 02-May-25 | 0d
Substantial Completion | G-CON-1540 | *Milestone: Beneficial Occupancy | 0d | 02-May-25 |  | 0d
N/A | Close Out | Close Out | 30d | 05-May-25 | 16-Jun-25 | 0d
N/A | Final Closeout | Final Closeout | 30d | 05-May-25 | 16-Jun-25 | 0d
Final Closeout | G-CON-1220 | Closeout / Final Completion | 30d | 05-May-25 | 16-Jun-25 | 0d

## Gantt Schedule
23 | 23 | [316 empty] | 24 | [365 empty] | 25
Feb | Feb | [10 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [28 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun
17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16