## Sheet1
CPM | [6 empty] | 2024 | 2024
[7 empty] | Sep | Sep | [23 empty] | Oct
PM | LT | PM | LT | PM | PM | PM | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
Phase | Location | Trade | Activity Code | Activity Name | Start | Finish | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Phase 1 | Zone 1 | Trade 1 | 1A | Activity 1 | 6-Sep-24 | 20-Sep-24 | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | [9 empty] | 1B | 1B | 1B | 1B | 1B | 1B |  | 1E | 1E | 1E | 1E | 1E | 1E
Phase 1 | Zone 1 | Trade 2 | 2A | Activity 1 | 9-Sep-24 | 15-Sep-24 |  |  |  | 2A | 2A | 2A | 2A | 2A | 2A | 2A | 2B | 2B | 2B | 2B | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C |  |  |  |  | 2C | 2C | 2C | 2C | 2C | 2E | 2E | 2E
Phase 1 | Zone 1 | Trade 1 | 1B | Activity 2 | 30-Sep-24 | 5-Oct-24 | [22 empty] | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D
Phase 1 | Zone 1 | Trade 2 | 2B | Activity 2 | 16-Sep-24 | 19-Sep-24 | [29 empty] | 2D | 2D | 2D
Phase 1 | Zone 1 | Trade 1 | 1C | Activity 3 | 20-Sep-24 | 30-Sep-24
Phase 1 | Zone 1 | Trade 2 | 2C | Activity 3 | 5-Oct-24 | 9-Oct-24
Phase 1 | Zone 1 | Trade 1 | 1D | Activity 4 | 28-Sep-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | 2D | Activity 4 | 5-Oct-24 | 7-Oct-24
Phase 1 | Zone 1 | Trade 1 | 1E | Activity 5 | 7-Oct-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | 2E | Activity 5 | 10-Oct-24 | 12-Oct-24
phase | trade | activity_code | activity_name
Phase 1 | Trade 1 | 1A | Activity 1
|  | 1B | Activity 2
|  | 1C | Activity 3
|  | 1D | Activity 4
|  | 1E | Activity 5
| Trade 2 | 2A | Activity 1
|  | 2B | Activity 2
|  | 2C | Activity 3
|  | 2D | Activity 4
|  | 2E | Activity 5

## Sheet2
CPM | [7 empty] | 2024 | 2024
[8 empty] | Sep | Sep | [23 empty] | Oct
PM | LT | PM |  | LT | PM | PM | PM | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1A | Activity 1 | 6-Sep-24 | 20-Sep-24 | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | [9 empty] | 1B | 1B | 1B | 1B | 1B | 1B |  | 1E | 1E | 1E | 1E | 1E | 1E
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2A | Activity 1 | 9-Sep-24 | 15-Sep-24 |  |  |  | 2A | 2A | 2A | 2A | 2A | 2A | 2A | 2B | 2B | 2B | 2B | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C |  |  |  |  | 2C | 2C | 2C | 2C | 2C | 2E | 2E | 2E
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1B | Activity 2 | 30-Sep-24 | 5-Oct-24 | [22 empty] | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2B | Activity 2 | 16-Sep-24 | 19-Sep-24 | [29 empty] | 2D | 2D | 2D
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1C | Activity 3 | 20-Sep-24 | 30-Sep-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2C | Activity 3 | 5-Oct-24 | 9-Oct-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1D | Activity 4 | 28-Sep-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2D | Activity 4 | 5-Oct-24 | 7-Oct-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1E | Activity 5 | 7-Oct-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2E | Activity 5 | 10-Oct-24 | 12-Oct-24
phase | trade | activity_code | activity_name
Phase 1 | Trade 1 | 1A | Activity 1
|  | 1B | Activity 2
|  | 1C | Activity 3
|  | 1D | Activity 4
|  | 1E | Activity 5
| Trade 2 | 2A | Activity 1
|  | 2B | Activity 2
|  | 2C | Activity 3
|  | 2D | Activity 4
|  | 2E | Activity 5

## Test Dani
CPM | [7 empty] | 2024 | 2024
[8 empty] | Sep | Sep | [23 empty] | Oct
PM | LT | PM |  | LT | PM | PM | PM | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1A | Activity 1 | 6-Sep-24 | 20-Sep-24 | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | [9 empty] | 1B | 1B | 1B | 1B | 1B | 1B |  | 1E | 1E | 1E | 1E | 1E | 1E
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2A | Activity 1 | 9-Sep-24 | 15-Sep-24 |  |  |  | 2A | 2A | 2A | 2A | 2A | 2A | 2A | 2B | 2B | 2B | 2B | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C |  |  |  |  | 2C | 2C | 2C | 2C | 2C | 2E | 2E | 2E
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1B | Activity 2 | 30-Sep-24 | 5-Oct-24 | [22 empty] | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2B | Activity 2 | 16-Sep-24 | 19-Sep-24 | [29 empty] | 2D | 2D | 2D
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1C | Activity 3 | 20-Sep-24 | 30-Sep-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2C | Activity 3 | 5-Oct-24 | 9-Oct-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1D | Activity 4 | 28-Sep-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2D | Activity 4 | 5-Oct-24 | 7-Oct-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1E | Activity 5 | 7-Oct-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2E | Activity 5 | 10-Oct-24 | 12-Oct-24

## Test 2 Dani
CPM
CPM | LT | CPM | LT | LT | CPM | CPM | CPM
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG | 2024-10-07 08:00 | 2024-10-11 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 1 - MG | 2024-10-09 08:00 | 2024-10-15 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG3 | Overhead MEP Installation - COLO2 Cell 1 - MG | 2024-10-16 08:00 | 2024-10-29 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG4 | Deliver AHU into Mech. Gallery - COLO2 Cell 1 - MG | 2024-10-30 08:00 | 2024-10-31 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG5 | Install Walls and Primer Paint - COLO2 Cell 1 - MG | 2024-11-01 08:00 | 2024-11-14 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG6 | Placing the AHU - COLO2 Cell 1 - MG | 2024-11-22 08:00 | 2024-11-26 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG7 | Layout Ceiling and install Pencile Rod - COLO2 Cell 1 - MG | 2024-11-15 08:00 | 2024-11-15 17:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG8 | Piping and Electrical Termination to AHUs - COLO2 Cell 1 - MG | 2024-11-26 13:00 | 2024-12-11 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG9 | Pipe Testing - COLO2 Cell 1 - MG | 2024-12-11 13:00 | 2024-12-13 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG10 | Install ceiling and Light Fittings - COLO2 Cell 1 - MG | 2024-12-13 13:00 | 2024-12-26 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG11 | Trim out MEP - COLO2 Cell 1 - MG | 2024-12-18 13:00 | 2024-12-26 12:00
Fitout | COLO 2 Cell 1 Mech Gallery | Trade 1 | #96CEFF | MG12 | Post Wall Overhead MEP - COLO2 Cell 1 - MG | 2024-11-15 08:00 | 2024-12-06 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH5 | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH | 2024-12-30 08:00 | 2025-01-20 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH3 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 1 - DH | 2024-10-07 08:00 | 2024-10-22 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH4 | HAC install and Rise - COLO2 Cell 1 - DH | 2024-12-19 08:00 | 2024-12-26 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH2 | Termination at PDU & Busway- COLO2 Cell 1 - DH | 2024-12-19 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH6 | Security Screen Installation - COLO2 Cell 1 - DH | 2024-11-15 08:00 | 2024-11-19 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH7 | Ceiling Grid and Tile - COLO2 Cell 1 - DH | 2024-11-20 08:00 | 2024-11-26 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH8 | Install PDU's - COLO2 Cell 1 - DH | 2024-12-12 08:00 | 2024-12-18 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH9 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 1 - DH | 2024-11-27 08:00 | 2024-12-11 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH10 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 1 - DH | 2024-12-27 08:00 | 2025-01-10 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH11 | HAC Placing - COLO2 Cell 1 - DH | 2024-12-12 08:00 | 2024-12-18 17:00
Fitout | COLO 2 Cell 1 Data Hall | Trade 2 | #C5E5A6 | DH12 | Finishes and Signage - COLO2 Cell 1 - DH | 2025-01-14 08:00 | 2025-01-20 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C1 | Interior - L1 UPS - COLO2 Cell 1 | 2025-01-02 08:00 | 2025-01-02 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C2 | Interior - L1 MSB - COLO2 Cell 1 | 2025-01-03 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C3 | Interior - L1 PDUs - COLO2 Cell 1 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C4 | Interior - L1 AHUs - COLO2 Cell 1 | 2025-01-08 08:00 | 2025-01-08 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C5 | Interior - L1 ATSs - COLO2 Cell 1 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C6 | Interior - L1 Busway - COLO2 Cell 1 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C7 | Interior - L1 ADP - COLO2 Cell 1 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C8 | Interior - L2 UPS - COLO2 Cell 1 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C9 | Interior - L2 MSB - COLO2 Cell 1 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C10 | Interior - L2 PDUs - COLO2 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C11 | Interior - L2 AHUs - COLO2 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C12 | Interior - L2 ATSs - COLO2 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C13 | Interior - L2 Busway - COLO2 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C14 | Interior - L2 ADP - COLO2 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C15 | Interior - L3 UPS - COLO2 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C16 | Interior - L3 MSB - COLO2 Cell 1 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C17 | Interior - L3 PDUs - COLO2 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C18 | Interior - L3 AHUs - COLO2 Cell 1 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C19 | Interior - L3 ATSs - COLO2 Cell 1 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C20 | Interior - L3 Busway - COLO2 Cell 1 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 2 Cell 1 Commissioning | Trade 3 | #F59CA6 | C21 | Interior - L3 ADP - COLO2 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER1 | Install Walls and Primer Paint - COLO2 Cell 1 - ER | 2024-10-07 08:00 | 2024-10-18 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER2 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 1 - ER | 2024-10-23 08:00 | 2024-11-05 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER3 | Install Upper Screens - COLO2 Cell 1 - ER | 2024-10-16 08:00 | 2024-10-22 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER4 | Install Ceiling - COLO2 Cell 1 - ER | 2024-11-06 08:00 | 2024-11-08 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER5 | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER | 2024-11-19 08:00 | 2024-12-03 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER6 | Installation of ADP & ATS - COLO2 Cell 1 - ER | 2024-11-29 08:00 | 2024-12-05 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER7 | Installation of UPS Equipment - COLO2 Cell 1 - ER | 2024-12-04 08:00 | 2024-12-10 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER8 | Connet to Cable tray and conduit equipment - COLO2 Cell 1 - ER | 2024-12-03 08:00 | 2024-12-09 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER9 | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | 2024-12-18 08:00 | 2025-01-09 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER10 | Door Frame Installation - COLO2 Cell 1 - ER | 2025-01-03 08:00 | 2025-01-09 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER11 | Finishes and Signage - COLO2 Cell 1 - ER | 2025-01-10 08:00 | 2025-01-16 17:00
Fitout | COLO 2 Cell 1 Electrical Room | Trade 4 | #FFC000 | ER12 | Installation of MSB - COLO2 Cell 1 - ER | 2024-11-29 08:00 | 2024-12-05 17:00
Fitout | COLO 2 Cell 1 Cx L4 | Trade 5 | #FFFFFF | L4 | COLO2 Cx LEV4 - COLO2 | 2025-05-01 08:00 | 2025-06-04 17:00
Fitout | COLO 2 Cell 1 Cx L5 | Trade 5 | #FFFFFF | L5 | COLO2 Cx LEV5 / IST - COLO2 | 2025-06-05 08:00 | 2025-06-06 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 2 - MG | 2024-10-14 08:00 | 2024-10-18 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 2 - MG | 2024-10-16 08:00 | 2024-10-22 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG3 | Overhead MEP Installation - COLO2 Cell 2 - MG | 2024-10-30 08:00 | 2024-11-12 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG4 | Deliver AHU into Mech. Gallery - COLO2 Cell 2 - MG | 2024-11-13 08:00 | 2024-11-14 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG5 | Install Walls and Primer Paint - COLO2 Cell 2 - MG | 2024-11-15 08:00 | 2024-11-29 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG6 | Placing the AHU - COLO2 Cell 2 - MG | 2024-12-09 08:00 | 2024-12-11 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG7 | Layout Ceiling and install Pencile Rod - COLO2 Cell 2 - MG | 2024-12-02 08:00 | 2024-12-02 17:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG8 | Piping and Electrical Termination to AHUs - COLO2 Cell 2 - MG | 2024-12-11 13:00 | 2024-12-26 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG9 | Pipe Testing - COLO2 Cell 2 - MG | 2024-12-26 13:00 | 2024-12-30 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG10 | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | 2024-12-30 13:00 | 2025-01-10 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG11 | Trim out MEP - COLO2 Cell 2 - MG | 2025-01-03 13:00 | 2025-01-10 12:00
Fitout | COLO 2 Cell 2 Mech Gallery | Trade 1 | #96CEFF | MG12 | Post Wall Overhead MEP - COLO2 Cell 2 - MG | 2024-12-02 08:00 | 2024-12-20 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH5 | Install Walls and Primer Paint - COLO2 Cell 2 - ER | 2024-10-21 08:00 | 2024-11-01 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH3 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 2 - ER | 2024-11-06 08:00 | 2024-11-19 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH4 | Install Upper Screens - COLO2 Cell 2 - ER | 2024-10-30 08:00 | 2024-11-05 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH2 | Install Ceiling - COLO2 Cell 2 - ER | 2024-11-20 08:00 | 2024-11-22 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH6 | Below Ceiling MEP Rough In - COLO2 Cell 2 - ER | 2024-12-04 08:00 | 2024-12-17 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH7 | Installation of ADP & ATS - COLO2 Cell 2 - ER | 2024-12-06 08:00 | 2024-12-12 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH8 | Installation of UPS Equipment - COLO2 Cell 2 - ER | 2024-12-11 08:00 | 2024-12-17 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH9 | Connet to Cable tray and conduit equipment - COLO2 Cell 2 - ER | 2024-12-10 08:00 | 2024-12-16 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH10 | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | 2025-01-10 08:00 | 2025-01-30 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH11 | Door Frame Installation - COLO2 Cell 2 - ER | 2025-01-03 08:00 | 2025-01-09 17:00
Fitout | COLO 2 Cell 2 Data Hall | Trade 2 | #C5E5A6 | DH12 | Finishes and Signage - COLO2 Cell 2 - ER | 2025-01-28 08:00 | 2025-02-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C1 | Installation of MSB - COLO2 Cell 2 - ER | 2024-12-06 08:00 | 2024-12-12 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C2 | Termination at PDU & Busway - COLO2 Cell 2 - DH | 2025-01-21 08:00 | 2025-02-10 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C3 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 2 - DH | 2024-10-23 08:00 | 2024-11-07 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C4 | HAC install and Rise - COLO2 Cell 2 - DH | 2025-01-06 08:00 | 2025-01-10 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C5 | Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH | 2025-01-06 08:00 | 2025-01-17 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C6 | Security Screen Installation - COLO2 Cell 2 - DH | 2024-12-02 08:00 | 2024-12-04 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C7 | Ceiling Grid and Tile - COLO2 Cell 2 - DH | 2024-12-05 08:00 | 2024-12-11 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C8 | Install PDU's - COLO2 Cell 2 - DH | 2024-12-27 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C9 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 2 - DH | 2024-12-12 08:00 | 2024-12-26 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C10 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 2 - DH | 2025-01-13 08:00 | 2025-01-24 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C11 | HAC Placing - COLO2 Cell 2 - DH | 2024-12-27 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C12 | Finishes and Signage - COLO2 Cell 2 - DH | 2025-02-04 08:00 | 2025-02-10 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C13 | Interior - L1 UPS - COLO2 Cell 2 | 2025-01-02 08:00 | 2025-01-02 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C14 | Interior - L1 MSB - COLO2 Cell 2 | 2025-01-03 08:00 | 2025-01-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C15 | Interior - L1 PDUs - COLO2 Cell 2 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C16 | Interior - L1 AHUs - COLO2 Cell 2 | 2025-01-08 08:00 | 2025-01-08 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C17 | Interior - L1 ATSs - COLO2 Cell 2 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C18 | Interior - L1 Busway - COLO2 Cell 2 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C19 | Interior - L1 ADP - COLO2 Cell 2 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C20 | Interior - L2 UPS - COLO2 Cell 2 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 2 Cell 2 Commissioning | Trade 3 | #F59CA6 | C21 | Interior - L2 MSB - COLO2 Cell 2 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER1 | Interior - L2 PDUs - COLO2 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER2 | Interior - L2 AHUs - COLO2 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER3 | Interior - L2 ATSs - COLO2 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER4 | Interior - L2 Busway - COLO2 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER5 | Interior - L2 ADP - COLO2 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER6 | Interior - L3 UPS - COLO2 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER7 | Interior - L3 MSB - COLO2 Cell 2 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER8 | Interior - L3 PDUs - COLO2 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER9 | Interior - L3 AHUs - COLO2 Cell 2 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER10 | Interior - L3 ATSs - COLO2 Cell 2 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER11 | Interior - L3 Busway - COLO2 Cell 2 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 2 Cell 2 Electrical Room | Trade 4 | #FFC000 | ER12 | Interior - L3 ADP - COLO2 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00

## Framework
CPM | [7 empty] | Gantt
PM | LT | PM | LT | PM | PM | PM
Phase | Location | Trade | Activity Code | Activity Name | Start | Finish |  | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12
Phase 1 | Zone 1 | Trade 1 | 1A | Activity 1 | 2024-09-06 | 2024-09-20 | bar: 2024-09-06 to 2024-09-20
Phase 1 | Zone 1 | Trade 2 | 2A | Activity 1 | 2024-09-09 | 2024-09-15 | bar: 2024-09-09 to 2024-09-15
Phase 1 | Zone 1 | Trade 1 | 1B | Activity 2 | 2024-09-30 | 2024-10-05 | bar: 2024-09-30 to 2024-10-05
Phase 1 | Zone 1 | Trade 2 | 2B | Activity 2 | 2024-09-16 | 2024-09-19 | bar: 2024-09-16 to 2024-09-19
Phase 1 | Zone 1 | Trade 1 | 1C | Activity 3 | 2024-09-20 | 2024-09-30 | bar: 2024-09-20 to 2024-09-30
Phase 1 | Zone 1 | Trade 2 | 2C | Activity 3 | 2024-10-05 | 2024-10-09 | bar: 2024-10-05 to 2024-10-09
Phase 1 | Zone 1 | Trade 1 | 1D | Activity 4 | 2024-09-28 | 2024-10-12 | bar: 2024-09-28 to 2024-10-12
Phase 1 | Zone 1 | Trade 2 | 2D | Activity 4 | 2024-10-05 | 2024-10-07 | bar: 2024-10-05 to 2024-10-07
Phase 1 | Zone 1 | Trade 1 | 1E | Activity 5 | 2024-10-07 | 2024-10-12 | bar: 2024-10-07 to 2024-10-12
Phase 1 | Zone 1 | Trade 2 | 2E | Activity 5 | 2024-10-10 | 2024-10-12 | bar: 2024-10-10 to 2024-10-12
Will be there | Might be there | Not there | Not there | Will be there | Will be there | Will be there
looking for unique and looking same activities done by same trade
Flow Analysis
Legend
[6 empty] | Trade 1 |  | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12
[6 empty] | 1A | Activity 1 | bar: 2024-09-06 to 2024-09-20; 2024-09-28 to 2024-10-12
[6 empty] | 1B | Activity 2 |  |  |  | 2A | 2A | 2A | 2A | 2A | 2A | 2A | 2B | 2B | 2B | 2B | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C |  |  |  |  | 2C | 2C | 2C | 2C | 2C | 2E | 2E | 2E
[6 empty] | 1C | Activity 3 | bar: 2024-09-30 to 2024-10-05; 2024-10-07 to 2024-10-12
[6 empty] | 1D | Activity 4 | bar: 2024-10-05 to 2024-10-07
[6 empty] | 1E | Activity 5
Trade 2
[6 empty] | 2A | Activity 1
[6 empty] | 2B | Activity 2
[6 empty] | 2C | Activity 3
[6 empty] | 2D | Activity 4
[6 empty] | 2E | Activity 5