## Sheet1
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML0 | Cx L5 IST Complete (White Tag) | 2025-09-18 | 2025-09-18
Commissioning | COLO 3 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-05 | 2025-05-28
Commissioning | COLO 3 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-15 | 2025-06-07
Commissioning | COLO 3 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-06-09 | 2025-07-02
Commissioning | COLO 3 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-27 | 2025-06-18
Commissioning | COLO 4 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-06 | 2025-05-29
Commissioning | COLO 4 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-31 | 2025-06-24
Commissioning | COLO 4 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-07-22 | 2025-08-14
Commissioning | COLO 4 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-06-27 | 2025-07-22
Commissioning | COLO 5 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-06-05 | 2025-06-28
Commissioning | COLO 5 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-06-28 | 2025-07-23
Commissioning | COLO 5 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-08-09 | 2025-09-03
Commissioning | COLO 5 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-07-15 | 2025-08-07
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- EPMS Point to Point Checks | 2025-06-13 | 2025-06-23
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- FTE Energizations [480v] | 2025-06-24 | 2025-06-27
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- Install Metering Cabinet [Prior to Energization] | 2025-06-12 | 2025-06-18
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- Loadbanking | 2025-07-15 | 2025-07-18
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- Startups | 2025-06-28 | 2025-07-14
Commissioning | COLO 3 | Microsoft | #196B24 | 4&5 | 4Cx- Testing <MSFT Duration> | 2025-08-15 | 2025-09-15
Commissioning | COLO 4 | Microsoft | #196B24 | 4&5 | 4Cx- Testing <MSFT Duration> | 2025-09-20 | 2025-10-16
Commissioning | COLO 5 | Microsoft | #196B24 | 4&5 | 4Cx- Testing <MSFT Duration> | 2025-10-17 | 2025-11-15
Commissioning | COLO 3 | Microsoft | #196B24 | 4&5 | 5Cx- Testing <MSFT Duration> | 2025-09-16 | 2025-09-18
Commissioning | COLO 4 | Microsoft | #196B24 | 4&5 | 5Cx- Testing <MSFT Duration> | 2025-10-17 | 2025-10-20
Commissioning | COLO 5 | Microsoft | #196B24 | 4&5 | 5Cx- Testing <MSFT Duration> | 2025-11-17 | 2025-11-19
Milestones | Milestone | Milestone | #808080 | ML1 | Admin & COLO3-5 Fitout Complete | 2025-10-01 | 2025-10-01
Fitout | COLO 3 - CELL 1 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-02-22 | 2025-02-27
Fitout | COLO 3 - CELL 2 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-03-04 | 2025-03-08
Fitout | COLO 3 - CELL 3 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-03-27 | 2025-04-01
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-03-14 | 2025-03-19
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-03-29 | 2025-04-03
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-04-07 | 2025-04-11
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-04-30 | 2025-05-06
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-04-18 | 2025-04-23
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-05-02 | 2025-05-08
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-05-12 | 2025-05-16
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-06-04 | 2025-06-09
Fitout | CELL 4 Data Hall Fitout Activities | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-05-22 | 2025-05-28
Site Utilities | Under Building Pad | Earthwork | #7E350E | EW1 | Backfill after UG work (MV / Telecom) | 2024-11-07 | 2024-11-08
Fitout | Punchlist | Punchlist | #A02B93 | PU1 | Beneficial Rooms PunchList | 2025-05-06 | 2025-05-09
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML1 | Beneficial Use | 2025-08-14 | 2025-08-14
Milestones | COLO 4 | Milestone | #000000 | ML2 | Beneficial Use | 2025-09-19 | 2025-09-19
Milestones | COLO 5 | Milestone | #000000 | ML3 | Beneficial Use | 2025-10-11 | 2025-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML4 | Beneficial Use - All Facility & Network Telecom Access/ Devices etc. | 2025-10-01 | 2025-10-01
Milestones | COLO 4 | Milestone | #000000 | ML5 | Beneficial Use - Distrbuted Antenna System (DAS) | 2025-09-19 | 2025-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML6 | Beneficial Use - Distributed Antenna System (DAS) | 2025-08-14 | 2025-08-14
Milestones | COLO 5 | Milestone | #000000 | ML7 | Beneficial Use - Distributed Antenna System (DAS) | 2025-10-11 | 2025-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML8 | Beneficial Use - Facility Cable Room (FCR) | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML9 | Beneficial Use - Meet Me Room or Entry Rooms (MMR/ER) | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML10 | Beneficial Use - Middle of Row (MOR) Cabinets | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML11 | Beneficial Use - Radio Over Internet Protocol (RoIP) | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML12 | Beneficial Use - Secure & High Value Storage Rooms | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML13 | Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets | 2025-08-14 | 2025-08-14
Milestones | COLO 4 | Milestone | #000000 | ML14 | Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets | 2025-09-19 | 2025-09-19
Milestones | COLO 5 | Milestone | #000000 | ML15 | Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets | 2025-10-11 | 2025-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML16 | Beneficial Use - Security Equipment Room (SER) | 2025-08-14 | 2025-08-14
Milestones | COLO 5 | Milestone | #000000 | ML17 | Beneficial Use - Security Low Voltage (SLV) System | 2025-10-11 | 2025-10-11
Milestones | COLO 4 | Milestone | #000000 | ML18 | Beneficial Use - Security Low Voltage (SLV) Systems | 2025-09-19 | 2025-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML19 | Beneficial Use (IDF#1,#2,#3 & #4) | 2025-08-14 | 2025-08-14
Milestones | COLO 5 | Milestone | #000000 | ML20 | Beneficial Use (IDF#1,#2,#3 & #4) | 2025-10-11 | 2025-10-11
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use Facility Cable Room (FCR) | 2025-10-11 | 2025-10-11
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use Meet Me Room or Entry Rooms (MMR/ER) | 2025-10-11 | 2025-10-11
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE29 | Beneficial Use Rooms | 2025-01-20 | 2025-05-09
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use Secure & High Value Storage Rooms | 2025-10-11 | 2025-10-11
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- (IDF#1,#2,#3 & #4) | 2025-09-19 | 2025-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Beneficial Use- Facilities Operations Center (FOC) | 2025-08-14 | 2025-08-14
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Facilities Operations Center (FOC) | 2025-09-19 | 2025-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Facility Cable Room (FCR) | 2025-09-19 | 2025-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Meet Me Room or Entry Rooms (MMR/ER) | 2025-09-19 | 2025-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Middle of Row (MOR) Cabinets | 2025-09-19 | 2025-09-19
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use- Middle of Row (MOR) Cabinets | 2025-10-11 | 2025-10-11
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Radio OVer Internet Protocol (RoIP) | 2025-09-19 | 2025-09-19
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use- Radio Over Internet Protocol (RoIP) | 2025-10-11 | 2025-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Beneficial Use- Regional Network Gateway (RNG) | 2025-08-14 | 2025-08-14
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Secure & High Value Storage Rooms | 2025-09-19 | 2025-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Beneficial Use- Security Low Voltage (SLV) System | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Beneficial Use- Security Operations Center (SOC) | 2025-08-14 | 2025-08-14
BIM | BIM | BIM | #DAE9F8 | BIM | BIM- Above ground BIM Co-ordination | 2024-09-06 | 2024-10-12
BIM | BIM | BIM | #DAE9F8 | BIM | BIM- BIM Kickoff | 2024-07-18 | 2024-07-18
BIM | BIM | BIM | #DAE9F8 | BIM | BIM- UG BIM Co-ordination | 2024-07-19 | 2024-08-17
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | EE30 | Build Equipment Pads for Generators | 2025-02-20 | 2025-03-03
Electrical Yard | COLO 4 | Electrical | #F2F09E | EE30 | Build Equipment Pads for Generators | 2025-03-27 | 2025-04-05
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE30 | Build Equipment Pads for Generators | 2025-04-30 | 2025-05-10
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UMSs | 2025-02-10 | 2025-02-19
Electrical Yard | COLO 4 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UMSs | 2025-03-15 | 2025-03-26
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UMSs | 2025-04-19 | 2025-04-29
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UPMs | 2025-01-29 | 2025-02-07
Electrical Yard | COLO 4 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UPMs | 2025-03-05 | 2025-03-14
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UPMs | 2025-04-08 | 2025-04-18
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | EE31 | Build Equipment Pads for XFMs | 2025-01-17 | 2025-01-28
Electrical Yard | COLO 4 | Electrical | #F2F09E | EE31 | Build Equipment Pads for XFMs | 2025-02-21 | 2025-03-04
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE31 | Build Equipment Pads for XFMs | 2025-03-28 | 2025-04-07
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Building Footprint Pad Ready | 2024-09-30 | 2024-09-30
Fitout | Electrical Room | Electrical | #F2F09E | EE28 | Cable Tray / Ceiling Steel Height | 2025-02-04 | 2025-02-04
Fitout | Fire Riser Room | Framing | #3598FE | J17 | Ceiling Grid & Tile | 2025-02-18 | 2025-02-21
Fitout | Restrooms & Janitor Room | Framing | #3598FE | J17 | Ceiling Grid & Tile | 2025-02-18 | 2025-02-21
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- Cable Bus Fabrication/ Lead Time | 2024-10-31 | 2025-03-03
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- HACs Fabrication/ Lead Time | 2024-10-31 | 2024-12-05
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- MV Cables Fabrication/ Lead Time | 2024-08-22 | 2025-04-29
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- MV Metering Cabinet - *Not Used* [65 Weeks] - Not Tied | 2024-08-21 | 2025-11-30
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- MV Metering Cabinet - Substitute [43 Weeks] | 2024-08-21 | 2025-06-25
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Building Pad Ready | 2024-09-05 | 2024-09-05
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Closeout Complete | 2026-01-22 | 2026-01-22
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Commissioning Complete | 2025-11-19 | 2025-11-19
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Construction Start | 2024-08-21 | 2024-08-21
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Electrical Service Available | 2025-05-05 | 2025-05-05
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Enclosure Complete | 2025-01-15 | 2025-01-15
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Final Completion (SC+40d) | 2026-01-22 | 2026-01-22
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Foundations Complete | 2024-11-12 | 2024-11-12
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Roofing Complete | 2024-12-31 | 2024-12-31
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Structure Complete | 2024-12-03 | 2024-12-03
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Structure Start | 2024-09-10 | 2024-09-10
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Substantial Completion | 2025-12-02 | 2025-12-02
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Utilities Available to Owner (Gas Service N/A) | 2024-12-26 | 2024-12-26
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Clayco Proposal Due date | 2024-10-11 | 2024-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete BAS Testing | 2025-08-30 | 2025-08-30
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete CX L3 (Green Tag) | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete EPMS Testing | 2025-08-30 | 2025-08-30
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Fire Alarm | 2025-08-30 | 2025-08-30
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete L1 Cx (All Red Tags/ ROJ) | 2025-06-04 | 2025-06-04
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete L2 Cx (Yellow Tag) | 2025-07-02 | 2025-07-02
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete L4 Cx (Blue Tag) | 2025-09-15 | 2025-09-15
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Last ROJ | 2025-03-08 | 2025-03-08
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete SOG | 2024-12-27 | 2024-12-27
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Superstructure | 2024-12-14 | 2024-12-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete U/G Utilities (No Elec) | 2024-12-14 | 2024-12-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete U/G Utilities/ MV UG Electrical | 2024-12-14 | 2024-12-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Utility Power- On | 2025-05-05 | 2025-05-05
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Weather Tight | 2025-01-16 | 2025-01-16
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete BAS Testing | 2025-09-30 | 2025-09-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete BAS Testing | 2025-10-31 | 2025-10-31
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Earthwork & U/G Site Utilities | 2024-12-26 | 2024-12-26
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete EPMS Testing | 2025-09-30 | 2025-09-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete EPMS Testing | 2025-10-31 | 2025-10-31
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Fire Alarm | 2025-09-30 | 2025-09-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Fire Alarm | 2025-10-31 | 2025-10-31
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Foundation | 2024-09-19 | 2024-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Foundation | 2024-10-31 | 2024-10-31
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Foundation | 2024-11-12 | 2024-11-12
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete L1 Cx (All Red Tags/ ROJ) | 2025-07-19 | 2025-07-19
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete L1 Cx (All Red Tags/ ROJ) | 2025-08-05 | 2025-08-05
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete L2 Cx (Yellow Tag) | 2025-08-14 | 2025-08-14
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete L2 Cx (Yellow Tag) | 2025-09-03 | 2025-09-03
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete L4 Cx (Blue Tag) | 2025-10-16 | 2025-10-16
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete L4 Cx (Blue Tag) | 2025-11-15 | 2025-11-15
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Landscaping/ Hardscaping | 2025-11-19 | 2025-11-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Last ROJ | 2025-03-30 | 2025-03-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Last ROJ | 2025-03-31 | 2025-03-31
Fitout | Fire Riser Room | Fire Protection | #D85234 | GSA | Complete Pipe/ Valves | 2025-02-22 | 2025-02-24
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete SOG | 2025-01-10 | 2025-01-10
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete SOG | 2025-01-25 | 2025-01-25
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Superstructure | 2024-12-31 | 2024-12-31
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Superstructure | 2025-01-15 | 2025-01-15
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete U/G Utilities/ MV UG Electric | 2024-12-27 | 2024-12-27
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete U/G Utilities/ MV UG Electric | 2025-01-13 | 2025-01-13
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Utility Power- On | 2025-05-05 | 2025-05-05
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Utility Power- On | 2025-05-05 | 2025-05-05
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-03-11 | 2025-03-13
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-03-19 | 2025-03-21
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-04-11 | 2025-04-15
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-03-31 | 2025-04-02
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-04-15 | 2025-04-17
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-04-23 | 2025-04-25
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-16 | 2025-05-19
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-05 | 2025-05-07
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-19 | 2025-05-21
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-28 | 2025-05-30
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-06-20 | 2025-06-23
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-06-07 | 2025-06-10
Commissioning | COLO 3 - CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-04 | 2025-06-12
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-09 | 2025-06-18
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-24 | 2025-07-07
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-13 | 2025-06-23
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-20 | 2025-06-28
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-25 | 2025-07-03
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-08-06 | 2025-08-14
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-07-18 | 2025-07-28
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-07-19 | 2025-07-29
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-07-24 | 2025-08-02
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-08-25 | 2025-09-03
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-08-04 | 2025-08-12
Milestones | COLO 4 | Milestone | #000000 | ML21 | CX L3 Complete | 2025-09-19 | 2025-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Cx L5 IST Complete | 2025-10-20 | 2025-10-20
Milestones | COLO 5 | Milestone | #000000 | ML21 | CX Level 3 Complete | 2025-10-11 | 2025-10-11
Milestones | COLO 5 | Milestone | #000000 | ML21 | Cx Level 5 IST Complete | 2025-11-19 | 2025-11-19
Fitout | COLO 3 - CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-03-11 | 2025-03-14
Fitout | COLO 3 - CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-03-19 | 2025-03-24
Fitout | COLO 3 - CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-04-11 | 2025-04-16
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-03-31 | 2025-04-03
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-04-15 | 2025-04-18
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-04-23 | 2025-04-26
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-05-16 | 2025-05-20
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-05-05 | 2025-05-08
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-05-19 | 2025-05-22
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-05-28 | 2025-05-31
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-06-20 | 2025-06-24
Fitout | CELL 4 Data Hall Fitout Activities | HAC's | #FED8E8 | S2 | Detail HACs | 2025-06-07 | 2025-06-11
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-06 | 2025-02-07
Fitout | COLO 3 - CELL 1 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-15 | 2025-02-15
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-06 | 2025-03-06
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-13 | 2025-02-13
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-04 | 2025-03-04
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-08 | 2025-03-10
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-08 | 2025-03-08
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-27 | 2025-03-27
Fitout | CELL 4 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-24 | 2025-02-25
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-24 | 2025-02-24
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-14 | 2025-03-14
Fitout | CELL 1 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-11 | 2025-03-12
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-11 | 2025-03-11
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-29 | 2025-03-29
Fitout | CELL 2 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-19 | 2025-03-20
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-19 | 2025-03-19
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-07 | 2025-04-07
Fitout | CELL 3 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-11 | 2025-04-14
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-11 | 2025-04-11
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-30 | 2025-04-30
Fitout | CELL 4 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-31 | 2025-04-01
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-31 | 2025-03-31
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-18 | 2025-04-18
Fitout | CELL 1 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-15 | 2025-04-16
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-15 | 2025-04-15
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-02 | 2025-05-02
Fitout | CELL 2 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-23 | 2025-04-24
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-23 | 2025-04-23
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-12 | 2025-05-12
Fitout | CELL 3 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-16 | 2025-05-17
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-16 | 2025-05-16
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-06-04 | 2025-06-04
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-05 | 2025-05-06
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-05 | 2025-05-05
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-22 | 2025-05-22
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Earthworks & U/G Utilities Start | 2025-03-05 | 2025-03-05
Milestones | COLO 5 | Milestone | #000000 | ML21 | Entire Building | 2025-02-14 | 2025-02-14
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-06-19 | 2025-06-27
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-07-08 | 2025-07-18
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-06-24 | 2025-07-02
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-06-30 | 2025-07-10
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-07-07 | 2025-07-15
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-08-15 | 2025-08-25
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-07-29 | 2025-08-06
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-07-30 | 2025-08-07
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-08-04 | 2025-08-12
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-09-04 | 2025-09-13
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-08-13 | 2025-08-22
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Final Completion/ Turnover to Operations | 2025-10-02 | 2025-10-02
Milestones | COLO 4 | Milestone | #000000 | ML21 | Final Completion/ Turnover to Operations | 2025-11-06 | 2025-11-06
Milestones | COLO 5 | Milestone | #000000 | ML21 | Final Completion/Turnover to Operations | 2025-12-04 | 2025-12-04
Site Prep/ Mobilization | Milestone | Milestone | #000000 | ML21 | Fine Grading Building Pad | 2024-08-19 | 2024-09-04
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-01 | 2025-02-04
Fitout | COLO 3 - CELL 1 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-22 | 2025-03-04
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-06 | 2025-03-07
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-11 | 2025-02-13
Fitout | COLO 3 - CELL 2 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-04 | 2025-03-05
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-06 | 2025-03-08
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-08 | 2025-03-10
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-27 | 2025-03-28
Fitout | CELL 4 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-21 | 2025-02-24
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-24 | 2025-02-25
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-14 | 2025-03-15
Fitout | CELL 1 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-08 | 2025-03-11
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-11 | 2025-03-12
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-29 | 2025-03-31
Fitout | CELL 2 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-17 | 2025-03-19
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-19 | 2025-03-20
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-07 | 2025-04-08
Fitout | CELL 3 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-09 | 2025-04-11
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-11 | 2025-04-14
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-30 | 2025-05-01
Fitout | CELL 4 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-28 | 2025-03-31
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-31 | 2025-04-01
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-18 | 2025-04-19
Fitout | CELL 1 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-11 | 2025-04-15
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-15 | 2025-04-16
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-02 | 2025-05-05
Fitout | CELL 2 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-21 | 2025-04-23
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-23 | 2025-04-24
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-12 | 2025-05-13
Fitout | CELL 3 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-14 | 2025-05-16
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-16 | 2025-05-17
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-06-04 | 2025-06-05
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-01 | 2025-05-05
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-05 | 2025-05-06
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-22 | 2025-05-23
Fitout | Fire Riser Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-12 | 2025-02-13
Fitout | Loading Dock | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-15 | 2025-02-17
Fitout | Restrooms & Janitor Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-13 | 2025-02-14
Fitout | SER (Security Equipment Room) | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-06 | 2025-02-07
Fitout | STORAGE (High Value & Secure) Rooms | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-26 | 2025-03-03
Fitout | Electrical Room | Framing | #3598FE | J13 | Finsh Drywall and Wall Protection | 2025-01-28 | 2025-01-31
Fitout | Entry Room 1 | Framing | #3598FE | J13 | Finsh Drywall and Wall Protection | 2025-01-30 | 2025-02-03
Fitout | Entry Room 2 | Framing | #3598FE | J13 | Finsh Drywall and Wall Protection | 2025-02-01 | 2025-02-05
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | J13 | Finsh Drywall and Wall Protection | 2025-02-04 | 2025-02-07
Fitout | Electrical Room | Framing | #3598FE | J13 | Fire Protection OH R/I | 2025-01-20 | 2025-01-20
Fitout | Entry Room 1 | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-21 | 2025-01-21
Fitout | Entry Room 2 | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-22 | 2025-01-22
Fitout | FCR (Facilities Control Room) | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-23 | 2025-01-23
Fitout | Fire Riser Room | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-27 | 2025-01-27
Fitout | Loading Dock | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-29 | 2025-01-29
Fitout | Restrooms & Janitor Room | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-28 | 2025-01-28
Fitout | SER (Security Equipment Room) | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-24 | 2025-01-24
Fitout | STORAGE (High Value & Secure) Rooms | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-25 | 2025-01-25
Fitout | STORAGE (High Value & Secure) Rooms | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-03-06 | 2025-03-17
Milestones | COLO 4 | Milestone | #000000 | ML21 | Foundation Start | 2024-09-16 | 2024-09-16
Milestones | COLO 5 | Milestone | #000000 | ML21 | Foundation Start | 2024-09-09 | 2024-09-09
Milestones | Milestone | Milestone | #000000 | ML21 | Foundations / Stem Walls (100% Complete) | 2024-10-10 | 2024-11-02
Milestones | Milestone | Milestone | #000000 | ML21 | Foundations / Stem Walls (50% Complete) | 2024-09-09 | 2024-10-09
Fitout | Electrical Room | Framing | #3598FE | J11 | Framing | 2025-01-21 | 2025-01-21
Fitout | Entry Room 1 | Framing | #3598FE | J11 | Framing | 2025-01-22 | 2025-01-22
Fitout | Entry Room 2 | Framing | #3598FE | J11 | Framing | 2025-01-23 | 2025-01-23
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | J11 | Framing | 2025-01-24 | 2025-01-24
Fitout | Fire Riser Room | Framing | #3598FE | J11 | Framing | 2025-01-28 | 2025-01-28
Fitout | Loading Dock | Framing | #3598FE | J11 | Framing | 2025-01-30 | 2025-01-30
Fitout | Restrooms & Janitor Room | Framing | #3598FE | J11 | Framing | 2025-01-29 | 2025-01-29
Fitout | SER (Security Equipment Room) | Framing | #3598FE | J11 | Framing | 2025-01-25 | 2025-01-25
Fitout | STORAGE (High Value & Secure) Rooms | Framing | #3598FE | J11 | Framing | 2025-01-27 | 2025-01-27
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-06-28 | 2025-07-02
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-07-19 | 2025-07-24
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-07-03 | 2025-07-09
Commissioning | CELL 1 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-07-11 | 2025-07-15
Commissioning | CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-07-16 | 2025-07-19
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-26 | 2025-08-29
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-07 | 2025-08-11
Commissioning | CELL 1 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-08 | 2025-08-12
Commissioning | CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-13 | 2025-08-18
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-09-15 | 2025-09-19
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-23 | 2025-08-27
Milestones | General | Milestone | #000000 | ML21 | GC Mobilization Finish/ Site Secured | 2024-09-16 | 2024-09-16
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | GC Mobilization Start | 2025-02-25 | 2025-02-25
Fitout | COLO 3 - CELL 1 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-02-18 | 2025-02-18
Fitout | COLO 3 - CELL 1 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-07 | 2025-03-07
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-11 | 2025-03-13
Fitout | COLO 3 - CELL 2 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-02-26 | 2025-02-26
Fitout | COLO 3 - CELL 2 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-02-18 | 2025-02-18
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-08 | 2025-03-11
Fitout | COLO 3 - CELL 3 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-21 | 2025-03-21
Fitout | CELL 3 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-13 | 2025-03-13
Fitout | CELL 3 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-01 | 2025-04-03
Fitout | CELL 4 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-10 | 2025-03-10
Fitout | CELL 4 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-02-28 | 2025-02-28
Fitout | CELL 4 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-19 | 2025-03-21
Fitout | CELL 1 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-25 | 2025-03-25
Fitout | CELL 1 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-15 | 2025-03-15
Fitout | CELL 1 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-03 | 2025-04-05
Fitout | CELL 2 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-02 | 2025-04-02
Fitout | CELL 2 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-25 | 2025-03-25
Fitout | CELL 2 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-11 | 2025-04-15
Fitout | CELL 3 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-25 | 2025-04-25
Fitout | CELL 3 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-17 | 2025-04-17
Fitout | CELL 3 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-06 | 2025-05-08
Fitout | CELL 4 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-14 | 2025-04-14
Fitout | CELL 4 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-04 | 2025-04-04
Fitout | CELL 4 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-23 | 2025-04-25
Fitout | CELL 1 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-28 | 2025-04-28
Fitout | CELL 1 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-19 | 2025-04-19
Fitout | CELL 1 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-08 | 2025-05-10
Fitout | CELL 2 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-07 | 2025-05-07
Fitout | CELL 2 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-28 | 2025-04-28
Fitout | CELL 2 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-16 | 2025-05-19
Fitout | CELL 3 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-30 | 2025-05-30
Fitout | CELL 3 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-21 | 2025-05-21
Fitout | CELL 3 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-06-09 | 2025-06-11
Fitout | CELL 4 Data Hall Fitout Activities | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-17 | 2025-05-17
Fitout | CELL 4 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-09 | 2025-05-09
Fitout | CELL 4 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-28 | 2025-05-30
Milestones | COLO 4 | Milestone | #000000 | ML21 | Generator Ready for Fuel | 2025-04-24 | 2025-04-24
Milestones | COLO 5 | Milestone | #000000 | ML21 | Generator Ready for Fuel | 2025-05-31 | 2025-05-31
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Generator Ready for Fuel (Exterior Yard) | 2025-03-15 | 2025-03-15
Fitout | CELL 1 Data Hall | Framing | #3598FE | J3 | IInstall Framing | 2025-02-25 | 2025-02-27
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-01-25 | 2025-01-28
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-01-31 | 2025-02-10
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-03 | 2025-02-05
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-05 | 2025-02-06
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-26 | 2025-02-28
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-28 | 2025-03-03
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-14 | 2025-02-17
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-17 | 2025-02-18
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-28 | 2025-03-04
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-04 | 2025-03-05
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-10 | 2025-03-12
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-12 | 2025-03-13
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-02 | 2025-04-04
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-04 | 2025-04-05
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-20 | 2025-03-24
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-24 | 2025-03-25
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-04 | 2025-04-07
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-07 | 2025-04-08
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-14 | 2025-04-16
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-16 | 2025-04-17
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-05-07 | 2025-05-09
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-05-09 | 2025-05-10
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-24 | 2025-04-26
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-26 | 2025-04-28
Fitout | COLO 3 - CELL 1 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-03-12 | 2025-03-24
Fitout | COLO 3 - CELL 2 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-03-10 | 2025-03-20
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-04-02 | 2025-04-14
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-03-20 | 2025-04-01
Fitout | CELL 1 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-04-04 | 2025-04-16
Fitout | CELL 2 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-04-14 | 2025-04-24
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-05-07 | 2025-05-17
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-04-24 | 2025-05-06
Fitout | CELL 1 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-05-09 | 2025-05-20
Fitout | CELL 2 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-05-17 | 2025-05-29
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-06-10 | 2025-06-21
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-05-29 | 2025-06-09
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-02-25 | 2025-03-03
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-03-06 | 2025-03-11
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-03-29 | 2025-04-03
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-03-17 | 2025-03-21
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-04-01 | 2025-04-05
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-04-09 | 2025-04-15
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-05-02 | 2025-05-08
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-04-21 | 2025-04-25
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-05-06 | 2025-05-10
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-05-14 | 2025-05-19
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-06-06 | 2025-06-11
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-05-27 | 2025-05-30
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-02-17 | 2025-02-18
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-12 | 2025-03-13
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-02-14 | 2025-02-15
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-10 | 2025-03-11
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-10 | 2025-03-11
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-02 | 2025-04-03
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-02-25 | 2025-02-26
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-20 | 2025-03-21
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-12 | 2025-03-13
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-04 | 2025-04-05
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-20 | 2025-03-21
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-14 | 2025-04-15
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-14 | 2025-04-15
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-07 | 2025-05-08
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-01 | 2025-04-02
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-24 | 2025-04-25
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-16 | 2025-04-17
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-09 | 2025-05-10
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-24 | 2025-04-25
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-17 | 2025-05-19
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-17 | 2025-05-19
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-06-10 | 2025-06-11
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-06 | 2025-05-07
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-29 | 2025-05-30
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-02-18 | 2025-02-21
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-02-26 | 2025-03-03
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-03-21 | 2025-03-26
Fitout | CELL 4 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-03-10 | 2025-03-13
Fitout | CELL 1 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-03-25 | 2025-03-28
Fitout | CELL 2 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-04-02 | 2025-04-05
Fitout | CELL 3 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-04-25 | 2025-04-29
Fitout | CELL 4 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-04-14 | 2025-04-17
Fitout | CELL 1 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-04-28 | 2025-05-01
Fitout | CELL 2 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-05-07 | 2025-05-10
Fitout | CELL 3 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-05-30 | 2025-06-03
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-05-17 | 2025-05-21
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-07 | 2025-03-11
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-05 | 2025-03-08
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-28 | 2025-04-01
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-15 | 2025-03-19
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-31 | 2025-04-03
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-04-08 | 2025-04-11
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-05-01 | 2025-05-06
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-04-19 | 2025-04-23
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-05-05 | 2025-05-08
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-05-13 | 2025-05-16
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-06-05 | 2025-06-09
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-05-23 | 2025-05-28
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-03-14 | 2025-03-17
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-03-24 | 2025-03-26
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-04-16 | 2025-04-18
Fitout | CELL 4 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-04-03 | 2025-04-05
Fitout | CELL 1 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-04-18 | 2025-04-21
Fitout | CELL 2 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-04-26 | 2025-04-29
Fitout | CELL 3 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-05-20 | 2025-05-22
Fitout | CELL 4 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-05-08 | 2025-05-10
Fitout | CELL 1 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-05-22 | 2025-05-23
Fitout | CELL 2 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-05-31 | 2025-06-03
Fitout | CELL 3 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-06-24 | 2025-06-26
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-06-11 | 2025-06-13
Site Utilities | Overall | Framing | #3598FE | J22 | Install Deep Telecom | 2024-09-23 | 2024-10-21
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-02-27 | 2025-02-28
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-03-08 | 2025-03-10
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-04-01 | 2025-04-02
Fitout | CELL 4 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-03-19 | 2025-03-20
Fitout | CELL 1 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-04-03 | 2025-04-04
Fitout | CELL 2 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-04-11 | 2025-04-14
Fitout | CELL 3 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-05-06 | 2025-05-07
Fitout | CELL 4 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-04-23 | 2025-04-24
Fitout | CELL 1 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-05-08 | 2025-05-09
Fitout | CELL 2 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-05-16 | 2025-05-17
Fitout | CELL 3 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-06-09 | 2025-06-10
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J23 | Install Device Tiles | 2025-05-28 | 2025-05-29
Fitout | Admin | Framing | #3598FE | J24 | Install Doors | 2025-02-22 | 2025-02-26
Fitout | Fire Riser Room | Framing | #3598FE | J30 | Install downcomers | 2025-01-31 | 2025-01-31
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-01-29 | 2025-01-31
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-02-06 | 2025-02-10
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-03-03 | 2025-03-05
Fitout | CELL 4 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-02-18 | 2025-02-20
Fitout | CELL 1 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-03-05 | 2025-03-07
Fitout | CELL 2 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-03-13 | 2025-03-15
Fitout | CELL 3 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-04-05 | 2025-04-08
Fitout | CELL 4 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-03-25 | 2025-03-27
Fitout | CELL 1 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-04-08 | 2025-04-10
Fitout | CELL 2 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-04-17 | 2025-04-19
Fitout | CELL 3 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-05-10 | 2025-05-13
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-04-28 | 2025-04-30
Fitout | COLO 3 - CELL 1 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-02-11 | 2025-02-21
Fitout | COLO 3 - CELL 2 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-02-07 | 2025-02-12
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-03-04 | 2025-03-07
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-02-19 | 2025-02-22
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-03-06 | 2025-03-10
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-03-14 | 2025-03-18
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-04-07 | 2025-04-10
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-03-26 | 2025-03-29
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-04-09 | 2025-04-14
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-04-18 | 2025-04-22
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-05-12 | 2025-05-15
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-04-29 | 2025-05-02
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-03-04 | 2025-03-05
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-02-28 | 2025-03-03
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-03-25 | 2025-03-26
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-03-12 | 2025-03-13
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-03-27 | 2025-03-28
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-04-04 | 2025-04-05
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-04-28 | 2025-04-29
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-04-16 | 2025-04-17
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-04-30 | 2025-05-01
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-05-09 | 2025-05-10
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-06-02 | 2025-06-03
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-05-20 | 2025-05-21
Fitout | Fire Riser Room | Framing | #3598FE | J31 | Install Duct Work | 2025-01-29 | 2025-01-30
Fitout | Loading Dock | Framing | #3598FE | J31 | Install Ductwork | 2025-01-29 | 2025-02-15
Fitout | Loading Dock | Framing | #3598FE | J31 | Install Ductwork (Remaining Rooms, Corridor) | 2025-01-30 | 2025-02-17
Fitout | STORAGE (High Value & Secure) Rooms | Framing | #3598FE | J31 | Install Ductwork and Cracs | 2025-02-07 | 2025-02-25
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J32 | Install Exterior Wall Panels | 2024-11-30 | 2024-12-14
Core & Shell | COLO 4 | Framing | #3598FE | J32 | Install Exterior Wall Panels | 2024-12-16 | 2024-12-31
Core & Shell | COLO 5 | Framing | #3598FE | J32 | Install Exterior Wall Panels | 2025-01-02 | 2025-01-15
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-02-27 | 2025-03-05
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-03-08 | 2025-03-13
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-01 | 2025-04-05
Fitout | CELL 4 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-03-19 | 2025-03-25
Fitout | CELL 1 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-03 | 2025-04-08
Fitout | CELL 2 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-11 | 2025-04-17
Fitout | CELL 3 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-06 | 2025-05-10
Fitout | CELL 4 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-23 | 2025-04-28
Fitout | CELL 1 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-08 | 2025-05-13
Fitout | CELL 2 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-16 | 2025-05-21
Fitout | CELL 3 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-06-09 | 2025-06-13
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-28 | 2025-06-02
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-01-20 | 2025-01-24
Fitout | COLO 3 - CELL 1 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-01-25 | 2025-01-30
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-01-30 | 2025-02-01
Fitout | COLO 3 - CELL 2 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-02-03 | 2025-02-04
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-02-22 | 2025-02-25
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-02-26 | 2025-02-27
Fitout | CELL 4 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-02-11 | 2025-02-13
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-02-14 | 2025-02-15
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-02-28 | 2025-03-03
Fitout | CELL 2 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-03-06 | 2025-03-08
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-03-10 | 2025-03-11
Fitout | CELL 3 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-03-29 | 2025-04-01
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-04-02 | 2025-04-03
Fitout | CELL 4 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-03-17 | 2025-03-19
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-03-20 | 2025-03-21
Fitout | CELL 1 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-04-01 | 2025-04-03
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-04-04 | 2025-04-05
Fitout | CELL 2 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-04-09 | 2025-04-11
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-04-14 | 2025-04-15
Fitout | CELL 3 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-05-02 | 2025-05-06
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-05-07 | 2025-05-08
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J3 | Install Framing | 2025-04-21 | 2025-04-23
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-04-24 | 2025-04-25
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E34 | Install Generators | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F2F09E | E34 | Install Generators | 2025-04-11 | 2025-04-24
Electrical Yard | COLO 5 | Electrical | #F2F09E | E34 | Install Generators | 2025-05-19 | 2025-05-31
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J34 | Install Louvers & Dampers | 2024-12-16 | 2025-01-06
Core & Shell | COLO 4 | Framing | #3598FE | J34 | Install Louvers & Dampers | 2025-01-07 | 2025-01-25
Core & Shell | COLO 5 | Framing | #3598FE | J34 | Install Louvers & Dampers | 2025-01-27 | 2025-02-14
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J35 | Install Misc. Metals (Trims, Gutters, Catwalks) | 2024-12-30 | 2025-01-17
Core & Shell | COLO 4 | Framing | #3598FE | J35 | Install Misc. Metals (Trims, Gutters, Catwalks) | 2025-01-11 | 2025-01-30
Core & Shell | COLO 5 | Framing | #3598FE | J35 | Install Misc. Metals (Trims, Gutters, Catwalks) | 2025-01-27 | 2025-02-14
Site Utilities | Overall | Framing | #3598FE | J36 | Install MV Ductbanks | 2024-10-04 | 2024-11-18
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-02-22 | 2025-02-26
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-03-04 | 2025-03-07
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-03-27 | 2025-03-31
Fitout | CELL 4 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-03-14 | 2025-03-18
Fitout | CELL 1 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-03-29 | 2025-04-02
Fitout | CELL 2 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-04-07 | 2025-04-10
Fitout | CELL 3 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-04-30 | 2025-05-05
Fitout | CELL 4 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-04-18 | 2025-04-22
Fitout | CELL 1 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-05-02 | 2025-05-07
Fitout | CELL 2 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-05-12 | 2025-05-15
Fitout | CELL 3 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-06-04 | 2025-06-07
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-05-22 | 2025-05-27
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J38 | Install Primary Steel | 2024-10-21 | 2024-11-07
Core & Shell | COLO 4 | Framing | #3598FE | J38 | Install Primary Steel | 2024-11-02 | 2024-11-20
Core & Shell | COLO 5 | Framing | #3598FE | J38 | Install Primary Steel | 2024-11-14 | 2024-12-03
Fitout | Entry Room 1 | Framing | #3598FE | J39 | Install Raceway | 2025-02-06 | 2025-02-10
Fitout | Entry Room 2 | Framing | #3598FE | J39 | Install Raceway | 2025-02-10 | 2025-02-12
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | J39 | Install Raceway | 2025-02-12 | 2025-02-14
Fitout | SER (Security Equipment Room) | Framing | #3598FE | J39 | Install Raceway | 2025-02-12 | 2025-02-14
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J40 | Install Roof Panels | 2024-11-08 | 2024-11-29
Core & Shell | COLO 4 | Framing | #3598FE | J40 | Install Roof Panels | 2024-11-21 | 2024-12-14
Core & Shell | COLO 5 | Framing | #3598FE | J40 | Install Roof Panels | 2024-12-04 | 2024-12-31
Site Utilities | Overall | Framing | #3598FE | J41 | Install Sanitary Lines | 2024-11-04 | 2024-12-03
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-02-10 | 2025-02-12
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-02-18 | 2025-02-20
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-03-13 | 2025-03-15
Fitout | CELL 4 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-02-28 | 2025-03-04
Fitout | CELL 1 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-03-15 | 2025-03-18
Fitout | CELL 2 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-03-25 | 2025-03-27
Fitout | CELL 3 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-04-17 | 2025-04-19
Fitout | CELL 4 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-04-04 | 2025-04-07
Fitout | CELL 1 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-04-19 | 2025-04-22
Fitout | CELL 2 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-04-28 | 2025-04-30
Fitout | CELL 3 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-05-21 | 2025-05-23
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-05-09 | 2025-05-12
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-02-21 | 2025-02-22
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-03-17 | 2025-03-18
Fitout | CELL 4 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-03-05 | 2025-03-06
Fitout | CELL 1 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-03-19 | 2025-03-20
Fitout | CELL 2 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-03-28 | 2025-03-29
Fitout | CELL 3 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-04-21 | 2025-04-22
Fitout | CELL 4 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-04-08 | 2025-04-09
Fitout | CELL 1 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-04-23 | 2025-04-24
Fitout | CELL 2 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-05-01 | 2025-05-02
Fitout | CELL 3 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-05-27 | 2025-05-27
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J42 | Install Secondary Steel | 2025-05-13 | 2025-05-14
Site Utilities | Overall | Framing | #3598FE | J43 | Install Storm Lines | 2024-11-09 | 2024-12-17
Site Utilities | Under Building Pad | Electrical | #F2F09E | EE36 | Install UG Electrical / UPM Crossing (under Building Pad) | 2024-09-30 | 2024-10-30
Site Utilities | Under Building Pad | Electrical | #F2F09E | EE37 | Install UG Telecom (under Building Pad) | 2024-09-18 | 2024-10-04
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E28 | Install UMSs | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F2F09E | E28 | Install UMSs | 2025-04-02 | 2025-04-15
Electrical Yard | COLO 5 | Electrical | #F2F09E | E28 | Install UMSs | 2025-05-16 | 2025-05-29
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E30 | Install UPMs | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F2F09E | E30 | Install UPMs | 2025-04-02 | 2025-04-15
Electrical Yard | COLO 5 | Electrical | #F2F09E | E30 | Install UPMs | 2025-05-14 | 2025-05-27
Site Utilities | Overall | Electrical | #F2F09E | E38 | Install Water Line | 2024-11-15 | 2024-12-26
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E39 | Install XFMs | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F2F09E | E39 | Install XFMs | 2025-04-02 | 2025-04-15
Electrical Yard | COLO 5 | Electrical | #F2F09E | E39 | Install XFMs | 2025-05-12 | 2025-05-23
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-01-17 | 2025-01-17
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-01-29 | 2025-01-29
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-02-21 | 2025-02-21
Fitout | CELL 4 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-02-10 | 2025-02-10
Fitout | CELL 1 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-02-24 | 2025-02-24
Fitout | CELL 2 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-03-05 | 2025-03-05
Fitout | CELL 3 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-03-28 | 2025-03-28
Fitout | CELL 4 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-03-15 | 2025-03-15
Fitout | CELL 1 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-03-31 | 2025-03-31
Fitout | CELL 2 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-04-08 | 2025-04-08
Fitout | CELL 3 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-05-01 | 2025-05-01
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J1 | Layout Framing | 2025-04-19 | 2025-04-19
Fitout | Admin | Electrical | #F2F09E | EEA | Light Fixtures Installation | 2025-02-27 | 2025-03-11
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-07-19 | 2025-07-23
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-08-09 | 2025-08-14
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-07-24 | 2025-07-29
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-07-31 | 2025-08-04
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-08-05 | 2025-08-08
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-09-16 | 2025-09-19
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-08-27 | 2025-08-30
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-08-28 | 2025-09-02
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-09-03 | 2025-09-08
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-10-06 | 2025-10-11
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-09-13 | 2025-09-17
Fitout | Electrical Room | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-22 | 2025-01-23
Fitout | Entry Room 1 | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-24 | 2025-01-25
Fitout | Entry Room 2 | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-27 | 2025-01-28
Fitout | FCR (Facilities Control Room) | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-29 | 2025-01-30
Fitout | Fire Riser Room | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-02-05 | 2025-02-06
Fitout | Loading Dock | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-02-11 | 2025-02-12
Fitout | Restrooms & Janitor Room | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-02-07 | 2025-02-10
Fitout | SER (Security Equipment Room) | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-31 | 2025-02-01
Fitout | STORAGE (High Value & Secure) Rooms | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-02-03 | 2025-02-04
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 1 | 2025-04-25 | 2025-05-05
Electrical Yard | COLO 4 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 1 | 2025-04-25 | 2025-05-05
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 2 | 2025-05-06 | 2025-05-14
Electrical Yard | COLO 4 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 2 | 2025-05-06 | 2025-05-14
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 3 | 2025-05-27 | 2025-06-03
Electrical Yard | COLO 4 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 3 | 2025-05-27 | 2025-06-04
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 4 | 2025-05-15 | 2025-05-23
Electrical Yard | COLO 4 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 4 | 2025-05-15 | 2025-05-23
Electrical Yard | COLO 5 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating(To Junction Box) to Cell 1 | 2025-05-02 | 2025-05-12
Electrical Yard | COLO 5 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating(To Junction Box) to Cell 2 | 2025-05-13 | 2025-05-21
Electrical Yard | COLO 5 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating(To Junction Box) to Cell 3 | 2025-06-02 | 2025-06-10
Electrical Yard | COLO 5 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating(To Junction Box) to Cell 4 | 2025-05-22 | 2025-05-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ1 | OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/04/24) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ2 | OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/9/24) | 2024-09-09 | 2024-09-09
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ3 | OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date- 3/8/2025) | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ4 | OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 4/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ5 | OFCI- Receive Auxillary (Mech) Power Distribution Panels (ADP) (Del Date- 3/8/2025) | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ6 | OFCI- Air Handling Units (AHU) (Stulz) Delivered | 2025-03-13 | 2025-03-13
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ7 | OFCI- Air Handling Units (AHU) (Stulz) Delivered | 2025-04-05 | 2025-04-05
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ8 | OFCI- Air Handling Units (AHU) (Stulz) Delivered | 2025-05-11 | 2025-05-11
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ9 | OFCI- Air Handling Units (AHU) (Stulz) Shipped/ROJ | 2025-03-09 | 2025-03-13
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ10 | OFCI- Air Handling Units (AHU) (Stulz) Shipping/ ROJ | 2025-04-01 | 2025-04-05
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ11 | OFCI- Air Handling Units (AHU) (Stulz) Shipping/ROJ | 2025-05-11 | 2025-05-11
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ12 | OFCI- Auto Transfer Control Panel (TCP) Delivered | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ13 | OFCI- Auto Transfer Control Panel (TCP) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ14 | OFCI- Auto Transfer Control Panel (TCP) Delivered | 2025-04-04 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ15 | OFCI- Auto Transfer Control Panel (TCP) Shipping/ ROJ | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ16 | OFCI- Auto Transfer Control Panel (TCP) Shipping/ROJ | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ17 | OFCI- Auto Transfer Control Panel (TCP) Shipping/ROJ | 2025-03-30 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ18 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ19 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ20 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered | 2025-04-20 | 2025-04-20
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ21 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ22 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ23 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ | 2025-04-20 | 2025-04-20
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ24 | OFCI- Auxillary (Mech) Power Distribution Panels (ADP) Delivered | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ25 | OFCI- Auxillary (Mech) Power Distribution Panels (ADP) Shipping/ ROJ | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ26 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Delivered | 2025-01-04 | 2025-01-04
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ27 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Delivered | 2025-02-02 | 2025-02-02
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ28 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ | 2024-12-29 | 2025-01-04
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ29 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ | 2025-01-28 | 2025-02-02
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ30 | OFCI- Building Automation System (BAS) (ALC) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ31 | OFCI- Building Automation System (BAS) (ALC) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ32 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ33 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Delivered | 2025-05-03 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ34 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ35 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ | 2025-04-29 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ36 | OFCI- Busway / Busplugs (Starline Holding) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ37 | OFCI- Busway / Busplugs (Starline Holding) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ38 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ39 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ40 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (Schneider) Delivered | 2025-04-20 | 2025-04-20
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ41 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (Schneider) Shipping/ROJ | 2025-04-20 | 2025-04-20
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ42 | OFCI- Elec. Performance Monitoring System (EPMS) (Schneider) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ43 | OFCI- Elec. Performance Monitoring System (EPMS) (Schneider) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ44 | OFCI- HAC/Racking (Tate Access) Delivered | 2025-02-21 | 2025-02-21
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ45 | OFCI- HAC/Racking (Tate Access) Delivered | 2025-03-28 | 2025-03-28
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ46 | OFCI- HAC/Racking (Tate Access) Delivered | 2025-04-28 | 2025-04-28
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ47 | OFCI- HAC/Racking (Tate Access) Shipping/ ROJ | 2025-02-19 | 2025-02-21
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ48 | OFCI- HAC/Racking (Tate Access) Shipping/ROJ | 2025-03-26 | 2025-03-28
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ49 | OFCI- HAC/Racking (Tate Access) Shipping/ROJ | 2025-04-25 | 2025-04-28
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ50 | OFCI- LV Switchgear (Eaton) Delivered | 2025-03-02 | 2025-03-02
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ51 | OFCI- LV Switchgear (Eaton) Delivered | 2025-04-03 | 2025-04-03
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ52 | OFCI- LV Switchgear (Eaton) Shipping/ROJ | 2025-02-28 | 2025-03-02
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ53 | OFCI- LV Switchgear (Eaton) Shipping/ROJ | 2025-03-30 | 2025-04-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ54 | OFCI- LV Switchgear (LVS) (Eaton) Delivered | 2025-03-04 | 2025-03-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ55 | OFCI- LV Switchgear (LVS) (Eaton) Shipping/ ROJ | 2025-02-28 | 2025-03-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ56 | OFCI- Main LV Switch Board (MSB) Delivered | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ57 | OFCI- Main LV Switch Board (MSB) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ58 | OFCI- Main LV Switch Board (MSB) Delivered | 2025-04-04 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ59 | OFCI- Main LV Switch Board (MSB) Shipping/ ROJ | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ60 | OFCI- Main LV Switch Board (MSB) Shipping/ROJ | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ61 | OFCI- Main LV Switch Board (MSB) Shipping/ROJ | 2025-03-30 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ62 | OFCI- Mech Power Distribution Panels (ADP) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ63 | OFCI- Mech Power Distribution Panels (ADP) Delivered | 2025-04-04 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ64 | OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ65 | OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ | 2025-03-30 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ66 | OFCI- Medium Voltage Switchgear (JDC Power Sys) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ67 | OFCI- Medium Voltage Switchgear (JDC Power Sys) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ68 | OFCI- Medium Voltage Switchgear (MVS) (JD Power Sys) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ69 | OFCI- Medium Voltage Switchgear (MVS) (JD Power Sys) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ70 | OFCI- Medium Voltage Switchgear (MVS) (JDC Power Sys) Delivered | 2025-05-03 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ71 | OFCI- Medium Voltage Switchgear (MVS) (JDC Power Sys) Shipping/ROJ | 2025-04-29 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ72 | OFCI- Packaged Diesel Generator Set (CAT Holt) Delivered | 2025-02-24 | 2025-02-24
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ73 | OFCI- Packaged Diesel Generator Set (CAT Holt) Shipping/ ROJ | 2025-02-20 | 2025-02-24
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ74 | OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Delivered | 2025-04-10 | 2025-04-10
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ75 | OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ | 2025-04-06 | 2025-04-10
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ76 | OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Delivered | 2025-05-15 | 2025-05-15
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ77 | OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ | 2025-05-11 | 2025-05-15
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ78 | OFCI- Pad Mounted Transformers (XFM-TX) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ79 | OFCI- Pad Mounted Transformers (XFM-TX) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ80 | OFCI- Pad Mounted Transformers (XMF) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ81 | OFCI- Pad Mounted Transformers (XMF) Delivered | 2025-05-03 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ82 | OFCI- Pad Mounted Transformers (XMF) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ83 | OFCI- Pad Mounted Transformers (XMF) Shipping/ROJ | 2025-04-29 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 3-5 | ROJ | #747474 | ROJ84 | OFCI- PEMB Procurement (1st Del) (Nucor) Delivered | 2024-10-25 | 2024-10-25
MSFT OFCI ROJ Dates | COLO 3-5 | ROJ | #747474 | ROJ85 | OFCI- PEMB Procurement (1st Del) (Nucor) Shipping/ ROJ | 2024-10-21 | 2024-10-25
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ86 | OFCI- Power Distribution Units (PDU) (ABB) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ87 | OFCI- Power Distribution Units (PDU) (ABB) Delivered | 2025-05-07 | 2025-05-07
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ88 | OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ89 | OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ | 2025-05-03 | 2025-05-07
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ90 | OFCI- Power Distribution Units (PDU) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ91 | OFCI- Power Distribution Units (PDU) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ92 | OFCI- Receive Elec. Performance Monitoring System (EPMS) (Schneider) (SOW Del Date- 4/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ93 | OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/16/24) | 2024-09-16 | 2024-09-16
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ94 | OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ95 | OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date-3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ96 | OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 6/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ97 | OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 8/31/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ98 | OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 1/28/25) | 2025-01-28 | 2025-01-28
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ99 | OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 12/29/24) | 2024-12-29 | 2024-12-29
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ100 | OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 11/28/24) | 2024-11-30 | 2024-11-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ101 | OFCI- Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 2/23/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ102 | OFCI- Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 4/23/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ103 | OFCI- Receive Busway / Busplugs (Starline Holding) (Del Date- 1/25/24) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ104 | OFCI- Receive Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) (SOW Del Date- 6/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ105 | OFCI- Receive Elec. Performance Monitoring Syst. (EPMS) (Schneider) (SOW Del Date- 8/31/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ106 | OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 5/17/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ107 | OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 6/18/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ108 | OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 7/3/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ109 | OFCI- Receive LV Switchgear (Eaton) (SOW Del Date- 2/28/25) | 2025-02-28 | 2025-02-28
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ110 | OFCI- Receive LV Switchgear (Eaton) (SOW Del Date- 3/30/25) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ111 | OFCI- Receive LV Switchgear (LVS) (Eaton) (SOW Del Date- 2/28/25) | 2025-02-28 | 2025-02-28
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ112 | OFCI- Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ113 | OFCI- Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ114 | OFCI- Receive Main LV Switch Board (MSB) (SOW Del Date- 3/8/2025) | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ115 | OFCI- Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ116 | OFCI- Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ117 | OFCI- Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 7/30/24) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ118 | OFCI- Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 8/30/24) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ119 | OFCI- Receive Medium Voltage Switchgear (MVS) (JDC Power Sys) (SOW Del Date- 10/30/24) | 2024-10-30 | 2024-10-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ120 | OFCI- Receive Packaged Diesel Generator Set (CAT Holt) (SOW Del Date- 5/14/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ121 | OFCI- Receive Packaged Diesel Generator Set (GEN) (CAT Holt) (SOW Del Date- 6/4/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ122 | OFCI- Receive Packaged Diesel Generator Set (GPC) (CAT Holt) (SOW Del Date- 6/26/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ123 | OFCI- Receive Pad Mounted Transformers (XFM-TX) (Del Date- 7/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ124 | OFCI- Receive Pad Mounted Transformers (XMF) (Del Date 10/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3-5 | ROJ | #747474 | ROJ125 | OFCI- Receive PEMB Procurement (1st Del) (Nucor) (SOW Del Date-10/3/24) | 2024-10-03 | 2024-10-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ126 | OFCI- Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 4/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ127 | OFCI- Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 9/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ128 | OFCI- Receive Utility Pad Mount Switchgear (Del Date- 7/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ129 | OFCI- Receive Utility Pad Mount Switchgear (UPM) (Del Date 10/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ130 | OFCI- Receive Utility Pad Mount Switchgear (UPM) (Del Date 8/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ131 | OFCI- Received SUB Warehouse 11/23/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 11/11/23) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ132 | OFCI- Received SUB Warehouse 12/28/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 12/11/23) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ133 | OFCI- Received SUB Warehouse 9/28/2023 UPS System w/ Battery (UPS) (Eaton) (SOW Del Date- 8/13/23) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ134 | OFCI- Reveive Pad Mounted Transformers (XMF) (Del Date 8/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ135 | OFCI- Reveive Power Distribution Units (PDU) (ABB) (SOW Del Date- 7/12/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ136 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ137 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ138 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ139 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ140 | OFCI- UPS System w/ Battery (UPS) (Eaton) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ141 | OFCI- UPS System w/ Battery (UPS) (Eaton) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ142 | OFCI- Utility Pad Mount Switchgear (UPM) Delivered | 2025-02-24 | 2025-02-28
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ143 | OFCI- Utility Pad Mount Switchgear (UPM) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ144 | OFCI- Utility Pad Mount Switchgear (UPM) Delivered | 2025-05-03 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ145 | OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ146 | OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ147 | OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ | 2025-04-29 | 2025-05-03
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-01 | 2025-02-05
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-13 | 2025-02-15
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-15 | 2025-02-18
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-11 | 2025-02-14
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-11 | 2025-02-13
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-13 | 2025-02-15
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-06 | 2025-03-10
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-06 | 2025-03-08
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-08 | 2025-03-11
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-21 | 2025-02-25
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-21 | 2025-02-24
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-24 | 2025-02-26
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-08 | 2025-03-12
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-08 | 2025-03-11
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-11 | 2025-03-13
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-17 | 2025-03-20
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-17 | 2025-03-19
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-19 | 2025-03-21
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-09 | 2025-04-14
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-09 | 2025-04-11
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-11 | 2025-04-15
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-28 | 2025-04-01
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-28 | 2025-03-31
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-31 | 2025-04-02
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-11 | 2025-04-16
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-11 | 2025-04-15
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-15 | 2025-04-17
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-21 | 2025-04-24
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-21 | 2025-04-23
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-23 | 2025-04-25
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-14 | 2025-05-17
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-14 | 2025-05-16
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-16 | 2025-05-19
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-01 | 2025-05-06
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-01 | 2025-05-05
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-05 | 2025-05-07
Fitout | COLO 3 - CELL 1 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-01 | 2025-02-04
Fitout | COLO 3 - CELL 1 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-15 | 2025-02-17
Fitout | COLO 3 - CELL 2 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-11 | 2025-02-13
Fitout | COLO 3 - CELL 2 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-11 | 2025-02-12
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 3 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-06 | 2025-03-08
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-06 | 2025-03-07
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-08 | 2025-03-10
Fitout | CELL 4 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-21 | 2025-02-24
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-21 | 2025-02-22
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-24 | 2025-02-25
Fitout | CELL 1 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-08 | 2025-03-11
Fitout | CELL 1 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-08 | 2025-03-10
Fitout | CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-11 | 2025-03-12
Fitout | CELL 2 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-17 | 2025-03-19
Fitout | CELL 2 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-17 | 2025-03-18
Fitout | CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-19 | 2025-03-20
Fitout | CELL 3 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-09 | 2025-04-11
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-09 | 2025-04-10
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-11 | 2025-04-14
Fitout | CELL 4 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-28 | 2025-03-31
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-28 | 2025-03-29
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-31 | 2025-04-01
Fitout | CELL 1 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-11 | 2025-04-15
Fitout | CELL 1 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-11 | 2025-04-14
Fitout | CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-15 | 2025-04-16
Fitout | CELL 2 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-21 | 2025-04-23
Fitout | CELL 2 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-21 | 2025-04-22
Fitout | CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-23 | 2025-04-24
Fitout | CELL 3 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-14 | 2025-05-16
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-14 | 2025-05-15
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-16 | 2025-05-17
Fitout | CELL 4 Data Hall Fitout Activities | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-01 | 2025-05-05
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-01 | 2025-05-02
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-05 | 2025-05-06
Fitout | COLO 3 - CELL 1 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-01-29 | 2025-01-31
Fitout | COLO 3 - CELL 1 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-11 | 2025-02-12
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-06 | 2025-02-10
Fitout | COLO 3 - CELL 2 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-07 | 2025-02-10
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-11 | 2025-02-12
Fitout | COLO 3 - CELL 3 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-03 | 2025-03-05
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-04 | 2025-03-05
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-06 | 2025-03-07
Fitout | CELL 4 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-18 | 2025-02-20
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-19 | 2025-02-20
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-21 | 2025-02-22
Fitout | CELL 1 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-05 | 2025-03-07
Fitout | CELL 1 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-06 | 2025-03-07
Fitout | CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-08 | 2025-03-10
Fitout | CELL 2 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-13 | 2025-03-15
Fitout | CELL 2 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-14 | 2025-03-15
Fitout | CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-17 | 2025-03-18
Fitout | CELL 3 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-05 | 2025-04-08
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-07 | 2025-04-08
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-09 | 2025-04-10
Fitout | CELL 4 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-25 | 2025-03-27
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-26 | 2025-03-27
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-28 | 2025-03-29
Fitout | CELL 1 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-08 | 2025-04-10
Fitout | CELL 1 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-09 | 2025-04-10
Fitout | CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-11 | 2025-04-14
Fitout | CELL 2 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-17 | 2025-04-19
Fitout | CELL 2 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-18 | 2025-04-19
Fitout | CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-21 | 2025-04-22
Fitout | CELL 3 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-05-10 | 2025-05-13
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-05-12 | 2025-05-13
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-05-14 | 2025-05-15
Fitout | CELL 4 Data Hall Fitout Activities | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-28 | 2025-04-30
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-29 | 2025-04-30
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-05-01 | 2025-05-02
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-04 | 2025-02-05
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-19 | 2025-02-25
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-17 | 2025-02-22
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-08 | 2025-03-10
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-12 | 2025-03-18
Fitout | CELL 4 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-24 | 2025-02-25
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-27 | 2025-03-06
Fitout | CELL 1 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-11 | 2025-03-12
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-14 | 2025-03-20
Fitout | CELL 2 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-19 | 2025-03-20
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-24 | 2025-03-29
Fitout | CELL 3 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-11 | 2025-04-14
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-16 | 2025-04-22
Fitout | CELL 4 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-31 | 2025-04-01
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-03 | 2025-04-09
Fitout | CELL 1 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-15 | 2025-04-16
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-18 | 2025-04-24
Fitout | CELL 2 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-23 | 2025-04-24
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-26 | 2025-05-02
Fitout | CELL 3 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-05-16 | 2025-05-17
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-05-20 | 2025-05-27
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-05-05 | 2025-05-06
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-05-08 | 2025-05-14
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-02-26 | 2025-03-05
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-02-24 | 2025-03-03
Fitout | CELL 3 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-03-19 | 2025-03-26
Fitout | CELL 4 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-03-07 | 2025-03-13
Fitout | CELL 1 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-03-21 | 2025-03-28
Fitout | CELL 2 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-03-31 | 2025-04-05
Fitout | CELL 3 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-04-23 | 2025-04-29
Fitout | CELL 4 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-04-10 | 2025-04-17
Fitout | CELL 1 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-04-25 | 2025-05-01
Fitout | CELL 2 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-05-05 | 2025-05-10
Fitout | CELL 3 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-05-28 | 2025-06-03
Fitout | CELL 4 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-05-15 | 2025-05-21
Fitout | Electrical Room | Paiting | #D6F2FF | T2 | Paint | 2025-02-01 | 2025-02-03
Fitout | Entry Room 1 | Paiting | #D6F2FF | T2 | Paint | 2025-02-04 | 2025-02-05
Fitout | Entry Room 2 | Paiting | #D6F2FF | T2 | Paint | 2025-02-06 | 2025-02-07
Fitout | FCR (Facilities Control Room) | Paiting | #D6F2FF | T2 | Paint | 2025-02-10 | 2025-02-11
Fitout | Fire Riser Room | Paiting | #D6F2FF | T2 | Paint | 2025-02-14 | 2025-02-15
Fitout | Loading Dock | Paiting | #D6F2FF | T2 | Paint | 2025-02-18 | 2025-02-19
Fitout | Restrooms & Janitor Room | Paiting | #D6F2FF | T2 | Paint | 2025-02-15 | 2025-02-17
Fitout | SER (Security Equipment Room) | Paiting | #D6F2FF | T2 | Paint | 2025-02-10 | 2025-02-11
Fitout | STORAGE (High Value & Secure) Rooms | Paiting | #D6F2FF | T2 | Paint | 2025-03-04 | 2025-03-05
Fitout | COLO 3 - CELL 1 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-05 | 2025-02-07
Fitout | COLO 3 - CELL 1 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-05 | 2025-03-06
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-08 | 2025-03-10
Fitout | COLO 3 - CELL 2 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-14 | 2025-02-17
Fitout | COLO 3 - CELL 2 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-15 | 2025-02-17
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-06 | 2025-03-07
Fitout | COLO 3 - CELL 3 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-10 | 2025-03-12
Fitout | CELL 3 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-11 | 2025-03-12
Fitout | CELL 3 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-29 | 2025-03-31
Fitout | CELL 4 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-25 | 2025-02-27
Fitout | CELL 4 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-26 | 2025-02-27
Fitout | CELL 4 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-17 | 2025-03-18
Fitout | CELL 1 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-12 | 2025-03-14
Fitout | CELL 1 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-13 | 2025-03-14
Fitout | CELL 1 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-01 | 2025-04-02
Fitout | CELL 2 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-20 | 2025-03-24
Fitout | CELL 2 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-21 | 2025-03-24
Fitout | CELL 2 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-09 | 2025-04-10
Fitout | CELL 3 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-14 | 2025-04-16
Fitout | CELL 3 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-15 | 2025-04-16
Fitout | CELL 3 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-02 | 2025-05-05
Fitout | CELL 4 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-01 | 2025-04-03
Fitout | CELL 4 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-02 | 2025-04-03
Fitout | CELL 4 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-21 | 2025-04-22
Fitout | CELL 1 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-16 | 2025-04-18
Fitout | CELL 1 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-17 | 2025-04-18
Fitout | CELL 1 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-06 | 2025-05-07
Fitout | CELL 2 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-24 | 2025-04-26
Fitout | CELL 2 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-25 | 2025-04-26
Fitout | CELL 2 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-14 | 2025-05-15
Fitout | CELL 3 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-17 | 2025-05-20
Fitout | CELL 3 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-19 | 2025-05-20
Fitout | CELL 3 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-06-06 | 2025-06-07
Fitout | CELL 4 Data Hall Fitout Activities | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-06 | 2025-05-08
Fitout | CELL 4 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-07 | 2025-05-08
Fitout | CELL 4 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-27 | 2025-05-27
Fitout | COLO 3 - CELL 1 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-02-15 | 2025-02-17
Fitout | COLO 3 - CELL 2 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-02-24 | 2025-02-25
Fitout | COLO 3 - CELL 3 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-03-19 | 2025-03-20
Fitout | CELL 4 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-03-07 | 2025-03-08
Fitout | CELL 1 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-03-21 | 2025-03-24
Fitout | CELL 2 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-03-31 | 2025-04-01
Fitout | CELL 3 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-04-23 | 2025-04-24
Fitout | CELL 4 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-04-10 | 2025-04-11
Fitout | CELL 1 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-04-25 | 2025-04-26
Fitout | CELL 2 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-05-05 | 2025-05-06
Fitout | CELL 3 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-05-28 | 2025-05-29
Fitout | CELL 4 Data Hall Fitout Activities | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-05-15 | 2025-05-16
Site Utilities | Overall | Milestone | #000000 | MLPP | Permanent Power (Need by Date) | 2025-05-05 | 2025-05-05
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Phase 1 Security Pre-Testing Complete | 2025-08-30 | 2025-08-30
Milestones | COLO 4 | Milestone | #000000 | ML21 | Phase 1 Security Pre-Testing Complete | 2025-09-30 | 2025-09-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Phase 1 Security Pre-Testing Complete | 2025-10-31 | 2025-10-31
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Phase 2 Security Pre-Testing Complete | 2025-09-04 | 2025-09-04
Milestones | COLO 4 | Milestone | #000000 | ML21 | Phase 2 Security Pre-Testing Complete | 2025-10-04 | 2025-10-04
Milestones | COLO 5 | Milestone | #000000 | ML21 | Phase 2 Security Pre-Testing Complete | 2025-11-03 | 2025-11-03
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Phase 3 Security Pre-Testing Complete | 2025-09-25 | 2025-09-25
Milestones | COLO 4 | Milestone | #000000 | ML21 | Phase 3 Security Pre-Testing Complete | 2025-10-23 | 2025-10-23
Milestones | COLO 5 | Milestone | #000000 | ML21 | Phase 3 Security Pre-Testing Complete | 2025-11-26 | 2025-11-26
Fitout | Loading Dock | Plumbing | #2A4D4F | GPB | Plumbing | 2025-02-20 | 2025-03-10
Core & Shell | Admin/ COLO 3 | Concrete | #80804A | SOG | Prep / Place SOG | 2024-12-16 | 2024-12-27
Core & Shell | COLO 4 | Concrete | #80804A | SOG | Prep / Place SOG | 2024-12-30 | 2025-01-10
Core & Shell | COLO 5 | Concrete | #80804A | SOG | Prep / Place SOG | 2025-01-14 | 2025-01-25
Early Awards | Milestone | Milestone | #000000 | ML21 | PROCUREMENT- ARL & Subcontractor Awards | 2024-07-16 | 2024-09-27
Early Awards | Milestone | Milestone | #000000 | ML21 | PROCUREMENT- Buyouts & Early Procurement | 2024-07-16 | 2024-09-27
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | PSR (Contract) Executed | 2024-09-30 | 2024-09-30
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | E39 | Pull & Terminate BAS Equipments | 2025-03-25 | 2025-04-02
Fitout | COLO 3 - CELL 2 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-03-21 | 2025-03-31
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-04-15 | 2025-04-23
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-04-02 | 2025-04-10
Fitout | CELL 1 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-04-17 | 2025-04-25
Fitout | CELL 2 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-04-25 | 2025-05-05
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-05-19 | 2025-05-28
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-05-07 | 2025-05-15
Fitout | CELL 1 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-05-21 | 2025-05-30
Fitout | CELL 2 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-05-30 | 2025-06-07
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-06-23 | 2025-07-01
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-06-10 | 2025-06-19
Fitout | Electrical Room | Electrical | #F2F09E | EE24 | Pull Branches From Admin | 2025-03-29 | 2025-04-11
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-03-17 | 2025-03-29
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-04-14 | 2025-04-25
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-04-04 | 2025-04-17
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-05-01 | 2025-05-14
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-05-02 | 2025-05-15
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-05-30 | 2025-06-11
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-05-10 | 2025-05-22
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-03-07 | 2025-03-19
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-06-24 | 2025-07-08
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-05-28 | 2025-06-09
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-07-11 | 2025-07-23
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-06-12 | 2025-06-25
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-03-19 | 2025-04-02
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-03-17 | 2025-03-31
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-04-09 | 2025-04-23
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-03-28 | 2025-04-10
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-04-11 | 2025-04-25
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-04-21 | 2025-05-05
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-14 | 2025-05-28
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-01 | 2025-05-15
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-16 | 2025-05-30
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-27 | 2025-06-07
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-06-18 | 2025-07-01
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-06-05 | 2025-06-19
Fitout | Loading Dock | Electrical | #F2F09E | EE43 | Pull Cables | 2025-03-11 | 2025-03-13
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE44 | Pull Copper for BAS VLAN | 2025-03-21 | 2025-04-04
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE45 | Pull Copper for EPMS VLAN | 2025-02-20 | 2025-03-06
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE46 | Pull Copper for Tahuya VLAN | 2025-03-07 | 2025-03-20
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-03-31 | 2025-04-11
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-04-26 | 2025-05-08
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-04-18 | 2025-04-30
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-05-15 | 2025-05-27
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-05-16 | 2025-05-29
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-06-12 | 2025-06-24
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-05-23 | 2025-06-04
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-04-26 | 2025-05-09
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-07-09 | 2025-07-19
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-06-10 | 2025-06-23
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-07-24 | 2025-08-05
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-06-26 | 2025-07-10
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-03-18 | 2025-03-24
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-03-27 | 2025-04-01
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-04-19 | 2025-04-24
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-04-07 | 2025-04-11
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-04-22 | 2025-04-26
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-04-30 | 2025-05-06
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-05-23 | 2025-05-29
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-05-12 | 2025-05-16
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-05-27 | 2025-05-31
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-06-04 | 2025-06-09
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-06-27 | 2025-07-02
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-06-16 | 2025-06-20
Fitout | Electrical Room | Electrical | #F2F09E | EE29 | Pull Feeders to Admin | 2025-03-12 | 2025-03-28
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE48 | Pull Fiber For BAS VLAN | 2025-03-21 | 2025-04-04
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE49 | Pull Fiber For CEI Network | 2025-04-21 | 2025-05-05
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE50 | Pull Fiber For EPMS VLAN | 2025-02-20 | 2025-03-06
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE51 | Pull Fiber For Tahuya VLAN | 2025-03-07 | 2025-03-20
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE52 | Pull Fiber/Copper For CORPNET Network | 2025-04-05 | 2025-04-19
Fitout | COLO 3 - CELL 2 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-05-13 | 2025-05-23
Fitout | CELL 3 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-06-09 | 2025-06-20
Fitout | CELL 4 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-05-10 | 2025-05-21
Fitout | CELL 1 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-04-17 | 2025-04-28
Fitout | CELL 1 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-05-06 | 2025-05-16
Fitout | CELL 2 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-05-31 | 2025-06-11
Fitout | CELL 3 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-07-22 | 2025-08-02
Fitout | CELL 4 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-06-27 | 2025-07-10
Fitout | CELL 1 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-06-05 | 2025-06-17
Fitout | CELL 2 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-06-28 | 2025-07-11
Fitout | CELL 3 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-08-09 | 2025-08-21
Fitout | CELL 4 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-07-15 | 2025-07-25
Fitout | COLO 3 - CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-03-06 | 2025-03-10
Fitout | COLO 3 - CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-03-14 | 2025-03-18
Fitout | COLO 3 - CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-04-07 | 2025-04-10
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-03-26 | 2025-03-29
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-04-09 | 2025-04-14
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-04-18 | 2025-04-22
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-05-12 | 2025-05-15
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-04-29 | 2025-05-02
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-05-14 | 2025-05-17
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-05-22 | 2025-05-27
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-06-16 | 2025-06-19
Fitout | CELL 4 Data Hall Fitout Activities | HAC's | #FED8E8 | S2 | Raise HACs | 2025-06-03 | 2025-06-06
Milestones | COLO 4 | Milestone | #000000 | ML21 | Ready for Network Install | 2025-09-24 | 2025-09-24
Milestones | COLO 5 | Milestone | #000000 | ML21 | Ready for Network Install | 2025-10-17 | 2025-10-17
Fitout | Admin | Clayco | #C9392A | CL | Remaining Area Punchlist | 2025-03-12 | 2025-03-17
Fitout | Punchlist | Punchlist | #A02B93 | PU1 | Remaining Rooms | 2025-01-27 | 2025-03-17
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- Microsoft Awards CHI11 | 2024-05-06 | 2024-05-10
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- Microsoft Reviews Proposals | 2024-04-15 | 2024-05-02
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- PSR Executed (Early Works) | 2024-06-06 | 2024-06-06
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- PSR Executed (Full GMP) | 2024-09-30 | 2024-09-30
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- RFP Issued (Revised 3.21.24) and Proposal Due to MSFT | 2024-03-25 | 2024-04-12
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | RNI | 2025-08-20 | 2025-08-20
Fitout | Loading Dock | Milestone | #000000 | ML21 | Rough-in | 2025-01-31 | 2025-01-31
Fitout | Electrical Room | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-01-27 | 2025-01-27
Fitout | Entry Room 1 | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-01-29 | 2025-01-29
Fitout | Entry Room 2 | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-01-31 | 2025-01-31
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-02-03 | 2025-02-03
Fitout | Fire Riser Room | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-02-11 | 2025-02-11
Fitout | SER (Security Equipment Room) | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-02-05 | 2025-02-05
Milestones | COLO 5 | Milestone | #000000 | ML21 | Secuirty Lockdown | 2025-12-04 | 2025-12-04
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Security Lockdown | 2025-10-02 | 2025-10-02
Milestones | COLO 4 | Milestone | #000000 | ML21 | Security Lockdown | 2025-11-06 | 2025-11-06
Fitout | Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipment in Admin | 2025-03-03 | 2025-03-11
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-10 | 2025-03-15
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-17 | 2025-03-20
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-14 | 2025-03-18
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-03 | 2025-03-06
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-31 | 2025-04-03
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-26 | 2025-03-29
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-04-18 | 2025-04-22
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-04-05 | 2025-04-09
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-04-21 | 2025-05-01
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-04-29 | 2025-05-02
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-05-22 | 2025-05-27
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-05-10 | 2025-05-14
Fitout | Entry Room 1 | Electrical | #F2F09E | EE54 | Set ER-1 Equipment | 2025-02-11 | 2025-02-14
Fitout | Entry Room 2 | Electrical | #F2F09E | EE55 | Set ER-2 Equipment | 2025-02-13 | 2025-02-17
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE56 | Set FCR Equipment | 2025-02-15 | 2025-02-19
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-03-14 | 2025-03-18
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-03-12 | 2025-03-15
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-04-04 | 2025-04-08
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-03-24 | 2025-03-27
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-04-07 | 2025-04-10
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-04-16 | 2025-04-19
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-05-09 | 2025-05-13
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-04-26 | 2025-04-30
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-05-12 | 2025-05-15
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-05-20 | 2025-05-23
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-06-12 | 2025-06-17
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-05-31 | 2025-06-04
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-02-27 | 2025-03-04
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-03-08 | 2025-03-12
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-04-01 | 2025-04-04
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-03-19 | 2025-03-24
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-04-03 | 2025-04-07
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-04-11 | 2025-04-16
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-05-06 | 2025-05-09
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-04-23 | 2025-04-26
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-05-08 | 2025-05-12
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-05-16 | 2025-05-20
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-06-09 | 2025-06-12
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE7 | Set PDUs | 2025-05-28 | 2025-05-31
Fitout | SER (Security Equipment Room) | HAC's | #FED8E8 | S3 | Set SER Room Equipment | 2025-02-15 | 2025-02-19
Site Prep/ Mobilization | Milestone | Milestone | #000000 | ML21 | Set-Up Trailers & Install Temp Utilities | 2024-07-25 | 2024-08-08
Site Prep/ Mobilization | Milestone | Milestone | #000000 | ML21 | Site Mobilization | 2024-07-24 | 2024-07-24
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start First ROJ - CLAYCO Took over Storage 9/2/2024 | 2024-09-05 | 2024-09-05
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start First ROJ CLAYCO Took over Storage 9/2/2024 | 2024-09-05 | 2024-09-05
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start First ROJ CLAYCO Took over Storage 9/2/2024 | 2024-09-05 | 2024-09-05
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start Foundation | 2024-09-19 | 2024-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L1 CX | 2025-04-09 | 2025-04-09
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L1 CX | 2025-04-23 | 2025-04-23
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L1 CX | 2025-04-21 | 2025-04-21
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L2 CX (Yellow Tag) | 2025-05-05 | 2025-05-05
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L2 CX (Yellow Tag) | 2025-05-06 | 2025-05-06
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L2 CX (Yellow Tag) | 2025-06-05 | 2025-06-05
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L3 CX | 2025-06-20 | 2025-06-20
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L3 CX | 2025-07-19 | 2025-07-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L3 CX (Green Tag) | 2025-06-04 | 2025-06-04
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L4 Cx (Blue Tag) | 2025-08-15 | 2025-08-15
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L4 Cx (Blue Tag) | 2025-09-20 | 2025-09-20
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L4 Cx (Blue Tag) | 2025-10-17 | 2025-10-17
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L5 Cx (White Tag) | 2025-09-16 | 2025-09-16
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L5 Cx (White Tag) | 2025-10-17 | 2025-10-17
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L5 Cx (White Tag) | 2025-11-17 | 2025-11-17
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start Superstructure | 2024-09-19 | 2024-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start Superstructure | 2024-11-02 | 2024-11-02
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start Superstructure | 2024-11-14 | 2024-11-14
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-03 | 2025-07-18
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-25 | 2025-08-08
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-10 | 2025-07-23
Commissioning | CELL 1 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-16 | 2025-07-30
Commissioning | CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-21 | 2025-08-04
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-30 | 2025-09-15
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-12 | 2025-08-26
Commissioning | CELL 1 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-13 | 2025-08-27
Commissioning | CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-19 | 2025-09-02
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-09-20 | 2025-10-04
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-28 | 2025-09-12
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Substantial Completion | 2025-10-01 | 2025-10-01
Milestones | COLO 4 | Milestone | #000000 | ML21 | Substantial Completion | 2025-10-29 | 2025-10-29
Milestones | COLO 5 | Milestone | #000000 | ML21 | Substantial Completion | 2025-12-02 | 2025-12-02
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | TCO / C of O | 2025-09-30 | 2025-09-30
Milestones | COLO 4 | Milestone | #000000 | ML21 | TCO / C of O | 2025-10-29 | 2025-10-29
Milestones | COLO 5 | Milestone | #000000 | ML21 | TCO / C of O | 2025-12-02 | 2025-12-02
Fitout | Electrical Room | Electrical | #F2F09E | EE58 | Terminate Electrical / Mechanical Equipment | 2025-04-14 | 2025-04-17
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-03-31 | 2025-04-03
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-04-26 | 2025-04-30
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-05-23 | 2025-05-28
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-03-20 | 2025-03-25
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-04-18 | 2025-04-22
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-05-15 | 2025-05-19
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-07-09 | 2025-07-12
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-06-10 | 2025-06-13
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-05-16 | 2025-05-20
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-06-12 | 2025-06-17
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-07-24 | 2025-07-29
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-06-26 | 2025-06-30
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-03 | 2025-04-07
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-01 | 2025-04-04
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-24 | 2025-04-28
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-11 | 2025-04-16
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-26 | 2025-04-30
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-05-06 | 2025-05-09
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-05-29 | 2025-06-02
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-05-16 | 2025-05-20
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-05-31 | 2025-06-04
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-06-09 | 2025-06-12
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-07-02 | 2025-07-08
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-06-20 | 2025-06-24
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE61 | Terminate MV Gear - Cell 1 | 2025-05-30 | 2025-06-03
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE61 | Terminate MV Gear - Cell 2 | 2025-06-04 | 2025-06-07
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE61 | Terminate MV Gear - Cell 3 | 2025-06-13 | 2025-06-18
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE61 | Terminate MV Gear - Cell 4 | 2025-06-09 | 2025-06-12
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-04-14 | 2025-04-16
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-05-09 | 2025-05-12
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-06-05 | 2025-06-07
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-05-10 | 2025-05-13
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-05-01 | 2025-05-05
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-05-28 | 2025-05-30
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-07-18 | 2025-07-21
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-06-24 | 2025-06-26
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-06-02 | 2025-06-04
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-06-25 | 2025-06-27
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-08-06 | 2025-08-08
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-07-11 | 2025-07-14
Fitout | Electrical Room | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-01-24 | 2025-01-25
Fitout | Entry Room 1 | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-01-27 | 2025-01-28
Fitout | Entry Room 2 | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-01-29 | 2025-01-30
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-01-31 | 2025-02-01
Fitout | Fire Riser Room | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-07 | 2025-02-10
Fitout | Loading Dock | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-13 | 2025-02-14
Fitout | Restrooms & Janitor Room | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-11 | 2025-02-12
Fitout | SER (Security Equipment Room) | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-03 | 2025-02-04
Fitout | STORAGE (High Value & Secure) Rooms | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-05 | 2025-02-06
Core & Shell | Admin/ COLO 3 | Plumbing | #2A4D4F | GPC | UG MEP Work (Plumbing) | 2024-11-14 | 2024-12-14
Core & Shell | COLO 4 | Plumbing | #2A4D4F | GPC | UG MEP Work (Plumbing) | 2024-12-04 | 2024-12-27
Core & Shell | COLO 5 | Plumbing | #2A4D4F | GPC | UG MEP Work (Plumbing) | 2024-12-17 | 2025-01-13
Core & Shell | Admin/ COLO 3 | Plumbing | #2A4D4F | GPD | Weather Days | 2024-12-30 | 2025-01-16
Milestones | COLO 4 | Milestone | #000000 | ML21 | Weather Tight | 2025-01-30 | 2025-01-30
Milestones | Key Milestone | Milestone | #000000 | ML21 | TBD | 2024-03-25 | 2024-09-30

## Sheet2
phase | location | entry | activity_code | color | start | finish
Milestones | Admin/ COLO 3 | 1 | ML0 | #000000 | 18-Sep-25 | 18-Sep-25
|  | 40 | ML1 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 43 | ML4 | #000000 | 01-Oct-25 | 01-Oct-25
|  | 45 | ML6 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 47 | ML8 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 48 | ML9 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 49 | ML10 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 50 | ML11 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 51 | ML12 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 52 | ML13 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 55 | ML16 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 58 | ML19 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 65 | ML21 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 73 | ML21 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 75 | ML21 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 76 | ML21 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 92 | ML21 | #000000 | 30-Sep-24 | 30-Sep-24
|  | 114 | ML21 | #000000 | 11-Oct-24 | 11-Oct-24
|  | 115 | ML21 | #000000 | 30-Aug-25 | 30-Aug-25
|  | 116 | ML21 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 117 | ML21 | #000000 | 30-Aug-25 | 30-Aug-25
|  | 118 | ML21 | #000000 | 30-Aug-25 | 30-Aug-25
|  | 119 | ML21 | #000000 | 04-Jun-25 | 04-Jun-25
|  | 120 | ML21 | #000000 | 02-Jul-25 | 02-Jul-25
|  | 121 | ML21 | #000000 | 15-Sep-25 | 15-Sep-25
|  | 122 | ML21 | #000000 | 08-Mar-25 | 08-Mar-25
|  | 123 | ML21 | #000000 | 27-Dec-24 | 27-Dec-24
|  | 124 | ML21 | #000000 | 14-Dec-24 | 14-Dec-24
|  | 125 | ML21 | #000000 | 14-Dec-24 | 14-Dec-24
|  | 126 | ML21 | #000000 | 14-Dec-24 | 14-Dec-24
|  | 127 | ML21 | #000000 | 05-May-25 | 05-May-25
|  | 128 | ML21 | #000000 | 16-Jan-25 | 16-Jan-25
|  | 131 | ML21 | #000000 | 26-Dec-24 | 26-Dec-24
|  | 136 | ML21 | #000000 | 19-Sep-24 | 19-Sep-24
|  | 145 | ML21 | #000000 | 19-Nov-25 | 19-Nov-25
|  | 233 | ML21 | #000000 | 05-Mar-25 | 05-Mar-25
|  | 246 | ML21 | #000000 | 02-Oct-25 | 02-Oct-25
|  | 330 | ML21 | #000000 | 25-Feb-25 | 25-Feb-25
|  | 369 | ML21 | #000000 | 15-Mar-25 | 15-Mar-25
|  | 1036 | ML21 | #000000 | 30-Aug-25 | 30-Aug-25
|  | 1039 | ML21 | #000000 | 04-Sep-25 | 04-Sep-25
|  | 1042 | ML21 | #000000 | 25-Sep-25 | 25-Sep-25
|  | 1051 | ML21 | #000000 | 30-Sep-24 | 30-Sep-24
|  | 1156 | ML21 | #000000 | 20-Aug-25 | 20-Aug-25
|  | 1165 | ML21 | #000000 | 02-Oct-25 | 02-Oct-25
|  | 1211 | ML21 | #000000 | 05-Sep-24 | 05-Sep-24
|  | 1213 | ML21 | #000000 | 19-Sep-24 | 19-Sep-24
|  | 1214 | ML21 | #000000 | 09-Apr-25 | 09-Apr-25
|  | 1217 | ML21 | #000000 | 05-May-25 | 05-May-25
|  | 1222 | ML21 | #000000 | 04-Jun-25 | 04-Jun-25
|  | 1223 | ML21 | #000000 | 15-Aug-25 | 15-Aug-25
|  | 1226 | ML21 | #000000 | 16-Sep-25 | 16-Sep-25
|  | 1229 | ML21 | #000000 | 19-Sep-24 | 19-Sep-24
|  | 1243 | ML21 | #000000 | 01-Oct-25 | 01-Oct-25
|  | 1246 | ML21 | #000000 | 30-Sep-25 | 30-Sep-25
| COLO 4 | 41 | ML2 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 44 | ML5 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 53 | ML14 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 57 | ML18 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 64 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 66 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 67 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 68 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 69 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 71 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 74 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 129 | ML21 | #000000 | 30-Sep-25 | 30-Sep-25
|  | 132 | ML21 | #000000 | 30-Sep-25 | 30-Sep-25
|  | 134 | ML21 | #000000 | 30-Sep-25 | 30-Sep-25
|  | 137 | ML21 | #000000 | 31-Oct-24 | 31-Oct-24
|  | 139 | ML21 | #000000 | 19-Jul-25 | 19-Jul-25
|  | 141 | ML21 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 143 | ML21 | #000000 | 16-Oct-25 | 16-Oct-25
|  | 146 | ML21 | #000000 | 30-Mar-25 | 30-Mar-25
|  | 149 | ML21 | #000000 | 10-Jan-25 | 10-Jan-25
|  | 151 | ML21 | #000000 | 31-Dec-24 | 31-Dec-24
|  | 153 | ML21 | #000000 | 27-Dec-24 | 27-Dec-24
|  | 155 | ML21 | #000000 | 05-May-25 | 05-May-25
|  | 181 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 182 | ML21 | #000000 | 20-Oct-25 | 20-Oct-25
|  | 247 | ML21 | #000000 | 06-Nov-25 | 06-Nov-25
|  | 305 | ML21 | #000000 | 16-Sep-24 | 16-Sep-24
|  | 367 | ML21 | #000000 | 24-Apr-25 | 24-Apr-25
|  | 1037 | ML21 | #000000 | 30-Sep-25 | 30-Sep-25
|  | 1040 | ML21 | #000000 | 04-Oct-25 | 04-Oct-25
|  | 1043 | ML21 | #000000 | 23-Oct-25 | 23-Oct-25
|  | 1147 | ML21 | #000000 | 24-Sep-25 | 24-Sep-25
|  | 1166 | ML21 | #000000 | 06-Nov-25 | 06-Nov-25
|  | 1212 | ML21 | #000000 | 05-Sep-24 | 05-Sep-24
|  | 1215 | ML21 | #000000 | 23-Apr-25 | 23-Apr-25
|  | 1218 | ML21 | #000000 | 06-May-25 | 06-May-25
|  | 1220 | ML21 | #000000 | 20-Jun-25 | 20-Jun-25
|  | 1224 | ML21 | #000000 | 20-Sep-25 | 20-Sep-25
|  | 1227 | ML21 | #000000 | 17-Oct-25 | 17-Oct-25
|  | 1230 | ML21 | #000000 | 02-Nov-24 | 02-Nov-24
|  | 1244 | ML21 | #000000 | 29-Oct-25 | 29-Oct-25
|  | 1247 | ML21 | #000000 | 29-Oct-25 | 29-Oct-25
|  | 1303 | ML21 | #000000 | 30-Jan-25 | 30-Jan-25
| COLO 5 | 42 | ML3 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 46 | ML7 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 54 | ML15 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 56 | ML17 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 59 | ML20 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 60 | ML21 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 61 | ML21 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 63 | ML21 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 70 | ML21 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 72 | ML21 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 130 | ML21 | #000000 | 31-Oct-25 | 31-Oct-25
|  | 133 | ML21 | #000000 | 31-Oct-25 | 31-Oct-25
|  | 135 | ML21 | #000000 | 31-Oct-25 | 31-Oct-25
|  | 138 | ML21 | #000000 | 12-Nov-24 | 12-Nov-24
|  | 140 | ML21 | #000000 | 05-Aug-25 | 05-Aug-25
|  | 142 | ML21 | #000000 | 03-Sep-25 | 03-Sep-25
|  | 144 | ML21 | #000000 | 15-Nov-25 | 15-Nov-25
|  | 147 | ML21 | #000000 | 31-Mar-25 | 31-Mar-25
|  | 150 | ML21 | #000000 | 25-Jan-25 | 25-Jan-25
|  | 152 | ML21 | #000000 | 15-Jan-25 | 15-Jan-25
|  | 154 | ML21 | #000000 | 13-Jan-25 | 13-Jan-25
|  | 156 | ML21 | #000000 | 05-May-25 | 05-May-25
|  | 183 | ML21 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 184 | ML21 | #000000 | 19-Nov-25 | 19-Nov-25
|  | 234 | ML21 | #000000 | 14-Feb-25 | 14-Feb-25
|  | 248 | ML21 | #000000 | 04-Dec-25 | 04-Dec-25
|  | 306 | ML21 | #000000 | 09-Sep-24 | 09-Sep-24
|  | 368 | ML21 | #000000 | 31-May-25 | 31-May-25
|  | 1038 | ML21 | #000000 | 31-Oct-25 | 31-Oct-25
|  | 1041 | ML21 | #000000 | 03-Nov-25 | 03-Nov-25
|  | 1044 | ML21 | #000000 | 26-Nov-25 | 26-Nov-25
|  | 1148 | ML21 | #000000 | 17-Oct-25 | 17-Oct-25
|  | 1164 | ML21 | #000000 | 04-Dec-25 | 04-Dec-25
|  | 1210 | ML21 | #000000 | 05-Sep-24 | 05-Sep-24
|  | 1216 | ML21 | #000000 | 21-Apr-25 | 21-Apr-25
|  | 1219 | ML21 | #000000 | 05-Jun-25 | 05-Jun-25
|  | 1221 | ML21 | #000000 | 19-Jul-25 | 19-Jul-25
|  | 1225 | ML21 | #000000 | 17-Oct-25 | 17-Oct-25
|  | 1228 | ML21 | #000000 | 17-Nov-25 | 17-Nov-25
|  | 1231 | ML21 | #000000 | 14-Nov-24 | 14-Nov-24
|  | 1245 | ML21 | #000000 | 02-Dec-25 | 02-Dec-25
|  | 1248 | ML21 | #000000 | 02-Dec-25 | 02-Dec-25
| General | 329 | ML21 | #000000 | 16-Sep-24 | 16-Sep-24
| Key Milestone | 101 | ML21 | #000000 | 05-Sep-24 | 05-Sep-24
|  | 102 | ML21 | #000000 | 22-Jan-26 | 22-Jan-26
|  | 103 | ML21 | #000000 | 19-Nov-25 | 19-Nov-25
|  | 104 | ML21 | #000000 | 21-Aug-24 | 21-Aug-24
|  | 105 | ML21 | #000000 | 05-May-25 | 05-May-25
|  | 106 | ML21 | #000000 | 15-Jan-25 | 15-Jan-25
|  | 107 | ML21 | #000000 | 22-Jan-26 | 22-Jan-26
|  | 108 | ML21 | #000000 | 12-Nov-24 | 12-Nov-24
|  | 109 | ML21 | #000000 | 31-Dec-24 | 31-Dec-24
|  | 110 | ML21 | #000000 | 03-Dec-24 | 03-Dec-24
|  | 111 | ML21 | #000000 | 10-Sep-24 | 10-Sep-24
|  | 112 | ML21 | #000000 | 02-Dec-25 | 02-Dec-25
|  | 113 | ML21 | #000000 | 26-Dec-24 | 26-Dec-24
|  | 1304 | ML21 | #000000 | 25-Mar-24 | 30-Sep-24
| Milestone | 25 | ML1 | #808080 | 01-Oct-25 | 01-Oct-25
|  | 307 | ML21 | #000000 | 10-Oct-24 | 02-Nov-24
|  | 308 | ML21 | #000000 | 09-Sep-24 | 09-Oct-24
BIM | BIM | 77 | BIM | #DAE9F8 | 06-Sep-24 | 12-Oct-24
|  | 78 | BIM | #DAE9F8 | 18-Jul-24 | 18-Jul-24
|  | 79 | BIM | #DAE9F8 | 19-Jul-24 | 17-Aug-24
CFCI Procurement | CFCI | 96 | CFCI | #F7C7AC | 31-Oct-24 | 03-Mar-25
|  | 97 | CFCI | #F7C7AC | 31-Oct-24 | 05-Dec-24
|  | 98 | CFCI | #F7C7AC | 22-Aug-24 | 29-Apr-25
|  | 99 | CFCI | #F7C7AC | 21-Aug-24 | 30-Nov-25
|  | 100 | CFCI | #F7C7AC | 21-Aug-24 | 25-Jun-25
Commissioning | CELL 1 Energizations & Startups (Level 3) | 173 | EE33 | #F2F09E | 20-Jun-25 | 28-Jun-25
|  | 177 | EE33 | #F2F09E | 19-Jul-25 | 29-Jul-25
|  | 238 | EE34 | #F2F09E | 30-Jun-25 | 10-Jul-25
|  | 242 | EE34 | #F2F09E | 30-Jul-25 | 07-Aug-25
|  | 321 | Cx1 | #8ED973 | 11-Jul-25 | 15-Jul-25
|  | 325 | Cx1 | #8ED973 | 08-Aug-25 | 12-Aug-25
|  | 658 | E39 | #F2F09E | 31-Jul-25 | 04-Aug-25
|  | 662 | E39 | #F2F09E | 28-Aug-25 | 02-Sep-25
|  | 1235 | Cx3 | #8ED973 | 16-Jul-25 | 30-Jul-25
|  | 1239 | Cx3 | #8ED973 | 13-Aug-25 | 27-Aug-25
| CELL 2 Energizations & Startups (Level 3) | 174 | EE33 | #F2F09E | 25-Jun-25 | 03-Jul-25
|  | 178 | EE33 | #F2F09E | 24-Jul-25 | 02-Aug-25
|  | 239 | EE34 | #F2F09E | 07-Jul-25 | 15-Jul-25
|  | 243 | EE34 | #F2F09E | 04-Aug-25 | 12-Aug-25
|  | 322 | Cx1 | #8ED973 | 16-Jul-25 | 19-Jul-25
|  | 326 | Cx1 | #8ED973 | 13-Aug-25 | 18-Aug-25
|  | 659 | E39 | #F2F09E | 05-Aug-25 | 08-Aug-25
|  | 663 | E39 | #F2F09E | 03-Sep-25 | 08-Sep-25
|  | 1236 | Cx3 | #8ED973 | 21-Jul-25 | 04-Aug-25
|  | 1240 | Cx3 | #8ED973 | 19-Aug-25 | 02-Sep-25
| CELL 3 Energizations & Startups (Level 3) | 171 | EE33 | #F2F09E | 24-Jun-25 | 07-Jul-25
|  | 175 | EE33 | #F2F09E | 06-Aug-25 | 14-Aug-25
|  | 179 | EE33 | #F2F09E | 25-Aug-25 | 03-Sep-25
|  | 236 | EE34 | #F2F09E | 08-Jul-25 | 18-Jul-25
|  | 240 | EE34 | #F2F09E | 15-Aug-25 | 25-Aug-25
|  | 244 | EE34 | #F2F09E | 04-Sep-25 | 13-Sep-25
|  | 319 | Cx1 | #8ED973 | 19-Jul-25 | 24-Jul-25
|  | 323 | Cx1 | #8ED973 | 26-Aug-25 | 29-Aug-25
|  | 327 | Cx1 | #8ED973 | 15-Sep-25 | 19-Sep-25
|  | 656 | E39 | #F2F09E | 09-Aug-25 | 14-Aug-25
|  | 660 | E39 | #F2F09E | 16-Sep-25 | 19-Sep-25
|  | 664 | E39 | #F2F09E | 06-Oct-25 | 11-Oct-25
|  | 1233 | Cx3 | #8ED973 | 25-Jul-25 | 08-Aug-25
|  | 1237 | Cx3 | #8ED973 | 30-Aug-25 | 15-Sep-25
|  | 1241 | Cx3 | #8ED973 | 20-Sep-25 | 04-Oct-25
| CELL 4 Energizations & Startups (Level 3) | 172 | EE33 | #F2F09E | 13-Jun-25 | 23-Jun-25
|  | 176 | EE33 | #F2F09E | 18-Jul-25 | 28-Jul-25
|  | 180 | EE33 | #F2F09E | 04-Aug-25 | 12-Aug-25
|  | 237 | EE34 | #F2F09E | 24-Jun-25 | 02-Jul-25
|  | 241 | EE34 | #F2F09E | 29-Jul-25 | 06-Aug-25
|  | 245 | EE34 | #F2F09E | 13-Aug-25 | 22-Aug-25
|  | 320 | Cx1 | #8ED973 | 03-Jul-25 | 09-Jul-25
|  | 324 | Cx1 | #8ED973 | 07-Aug-25 | 11-Aug-25
|  | 328 | Cx1 | #8ED973 | 23-Aug-25 | 27-Aug-25
|  | 657 | E39 | #F2F09E | 24-Jul-25 | 29-Jul-25
|  | 661 | E39 | #F2F09E | 27-Aug-25 | 30-Aug-25
|  | 665 | E39 | #F2F09E | 13-Sep-25 | 17-Sep-25
|  | 1234 | Cx3 | #8ED973 | 10-Jul-25 | 23-Jul-25
|  | 1238 | Cx3 | #8ED973 | 12-Aug-25 | 26-Aug-25
|  | 1242 | Cx3 | #8ED973 | 28-Aug-25 | 12-Sep-25
| COLO 3 | 2 | L2 | #196B24 | 05-May-25 | 28-May-25
|  | 3 | L2 | #196B24 | 15-May-25 | 07-Jun-25
|  | 4 | L2 | #196B24 | 09-Jun-25 | 02-Jul-25
|  | 5 | L2 | #196B24 | 27-May-25 | 18-Jun-25
|  | 14 | L3 | #196B24 | 13-Jun-25 | 23-Jun-25
|  | 15 | L3 | #196B24 | 24-Jun-25 | 27-Jun-25
|  | 16 | L3 | #196B24 | 12-Jun-25 | 18-Jun-25
|  | 17 | L3 | #196B24 | 15-Jul-25 | 18-Jul-25
|  | 18 | L3 | #196B24 | 28-Jun-25 | 14-Jul-25
|  | 19 | 4&5 | #196B24 | 15-Aug-25 | 15-Sep-25
|  | 22 | 4&5 | #196B24 | 16-Sep-25 | 18-Sep-25
| COLO 3 - CELL 1 Energizations & Startups (Level 3) | 169 | EE33 | #F2F09E | 04-Jun-25 | 12-Jun-25
| COLO 3 - CELL 2 Energizations & Startups (Level 3) | 170 | EE33 | #F2F09E | 09-Jun-25 | 18-Jun-25
|  | 235 | EE34 | #F2F09E | 19-Jun-25 | 27-Jun-25
|  | 318 | Cx1 | #8ED973 | 28-Jun-25 | 02-Jul-25
|  | 655 | E39 | #F2F09E | 19-Jul-25 | 23-Jul-25
|  | 1232 | Cx3 | #8ED973 | 03-Jul-25 | 18-Jul-25
| COLO 4 | 6 | L2 | #196B24 | 06-May-25 | 29-May-25
|  | 7 | L2 | #196B24 | 31-May-25 | 24-Jun-25
|  | 8 | L2 | #196B24 | 22-Jul-25 | 14-Aug-25
|  | 9 | L2 | #196B24 | 27-Jun-25 | 22-Jul-25
|  | 20 | 4&5 | #196B24 | 20-Sep-25 | 16-Oct-25
|  | 23 | 4&5 | #196B24 | 17-Oct-25 | 20-Oct-25
| COLO 5 | 10 | L2 | #196B24 | 05-Jun-25 | 28-Jun-25
|  | 11 | L2 | #196B24 | 28-Jun-25 | 23-Jul-25
|  | 12 | L2 | #196B24 | 09-Aug-25 | 03-Sep-25
|  | 13 | L2 | #196B24 | 15-Jul-25 | 07-Aug-25
|  | 21 | 4&5 | #196B24 | 17-Oct-25 | 15-Nov-25
|  | 24 | 4&5 | #196B24 | 17-Nov-25 | 19-Nov-25
Core & Shell | Admin/ COLO 3 | 534 | J32 | #3598FE | 30-Nov-24 | 14-Dec-24
|  | 575 | J34 | #3598FE | 16-Dec-24 | 06-Jan-25
|  | 578 | J35 | #3598FE | 30-Dec-24 | 17-Jan-25
|  | 594 | J38 | #3598FE | 21-Oct-24 | 07-Nov-24
|  | 601 | J40 | #3598FE | 08-Nov-24 | 29-Nov-24
|  | 1046 | SOG | #80804A | 16-Dec-24 | 27-Dec-24
|  | 1299 | GPC | #2A4D4F | 14-Nov-24 | 14-Dec-24
|  | 1302 | GPD | #2A4D4F | 30-Dec-24 | 16-Jan-25
| COLO 4 | 535 | J32 | #3598FE | 16-Dec-24 | 31-Dec-24
|  | 576 | J34 | #3598FE | 07-Jan-25 | 25-Jan-25
|  | 579 | J35 | #3598FE | 11-Jan-25 | 30-Jan-25
|  | 595 | J38 | #3598FE | 02-Nov-24 | 20-Nov-24
|  | 602 | J40 | #3598FE | 21-Nov-24 | 14-Dec-24
|  | 1047 | SOG | #80804A | 30-Dec-24 | 10-Jan-25
|  | 1300 | GPC | #2A4D4F | 04-Dec-24 | 27-Dec-24
| COLO 5 | 536 | J32 | #3598FE | 02-Jan-25 | 15-Jan-25
|  | 577 | J34 | #3598FE | 27-Jan-25 | 14-Feb-25
|  | 580 | J35 | #3598FE | 27-Jan-25 | 14-Feb-25
|  | 596 | J38 | #3598FE | 14-Nov-24 | 03-Dec-24
|  | 603 | J40 | #3598FE | 04-Dec-24 | 31-Dec-24
|  | 1048 | SOG | #80804A | 14-Jan-25 | 25-Jan-25
|  | 1301 | GPC | #2A4D4F | 17-Dec-24 | 13-Jan-25
Early Awards | Milestone | 1049 | ML21 | #000000 | 16-Jul-24 | 27-Sep-24
|  | 1050 | ML21 | #000000 | 16-Jul-24 | 27-Sep-24
Electrical Yard | Admin/ COLO 3 | 80 | EE30 | #F2F09E | 20-Feb-25 | 03-Mar-25
|  | 83 | EE31 | #F2F09E | 10-Feb-25 | 19-Feb-25
|  | 86 | EE31 | #F2F09E | 29-Jan-25 | 07-Feb-25
|  | 89 | EE31 | #F2F09E | 17-Jan-25 | 28-Jan-25
|  | 572 | E34 | #F2F09E | 04-Mar-25 | 15-Mar-25
|  | 632 | E28 | #F2F09E | 04-Mar-25 | 15-Mar-25
|  | 635 | E30 | #F2F09E | 04-Mar-25 | 15-Mar-25
|  | 639 | E39 | #F2F09E | 04-Mar-25 | 15-Mar-25
|  | 675 | E35 | #F2F09E | 25-Apr-25 | 05-May-25
|  | 677 | E35 | #F2F09E | 06-May-25 | 14-May-25
|  | 679 | E35 | #F2F09E | 27-May-25 | 03-Jun-25
|  | 681 | E35 | #F2F09E | 15-May-25 | 23-May-25
| COLO 4 | 81 | EE30 | #F2F09E | 27-Mar-25 | 05-Apr-25
|  | 84 | EE31 | #F2F09E | 15-Mar-25 | 26-Mar-25
|  | 87 | EE31 | #F2F09E | 05-Mar-25 | 14-Mar-25
|  | 90 | EE31 | #F2F09E | 21-Feb-25 | 04-Mar-25
|  | 573 | E34 | #F2F09E | 11-Apr-25 | 24-Apr-25
|  | 633 | E28 | #F2F09E | 02-Apr-25 | 15-Apr-25
|  | 636 | E30 | #F2F09E | 02-Apr-25 | 15-Apr-25
|  | 640 | E39 | #F2F09E | 02-Apr-25 | 15-Apr-25
|  | 676 | E35 | #F2F09E | 25-Apr-25 | 05-May-25
|  | 678 | E35 | #F2F09E | 06-May-25 | 14-May-25
|  | 680 | E35 | #F2F09E | 27-May-25 | 04-Jun-25
|  | 682 | E35 | #F2F09E | 15-May-25 | 23-May-25
| COLO 5 | 62 | EE29 | #F2F09E | 20-Jan-25 | 09-May-25
|  | 82 | EE30 | #F2F09E | 30-Apr-25 | 10-May-25
|  | 85 | EE31 | #F2F09E | 19-Apr-25 | 29-Apr-25
|  | 88 | EE31 | #F2F09E | 08-Apr-25 | 18-Apr-25
|  | 91 | EE31 | #F2F09E | 28-Mar-25 | 07-Apr-25
|  | 574 | E34 | #F2F09E | 19-May-25 | 31-May-25
|  | 634 | E28 | #F2F09E | 16-May-25 | 29-May-25
|  | 637 | E30 | #F2F09E | 14-May-25 | 27-May-25
|  | 641 | E39 | #F2F09E | 12-May-25 | 23-May-25
|  | 683 | E35 | #F2F09E | 02-May-25 | 12-May-25
|  | 684 | E35 | #F2F09E | 13-May-25 | 21-May-25
|  | 685 | E35 | #F2F09E | 02-Jun-25 | 10-Jun-25
|  | 686 | E35 | #F2F09E | 22-May-25 | 31-May-25
|  | 1274 | EE61 | #F2F09E | 30-May-25 | 03-Jun-25
|  | 1275 | EE61 | #F2F09E | 04-Jun-25 | 07-Jun-25
|  | 1276 | EE61 | #F2F09E | 13-Jun-25 | 18-Jun-25
|  | 1277 | EE61 | #F2F09E | 09-Jun-25 | 12-Jun-25
Fitout | Admin | 492 | J24 | #3598FE | 22-Feb-25 | 26-Feb-25
|  | 654 | EEA | #F2F09E | 27-Feb-25 | 11-Mar-25
|  | 1149 | CL | #C9392A | 12-Mar-25 | 17-Mar-25
| CELL 1 Data Hall | 30 | S1 | #FED8E8 | 29-Mar-25 | 03-Apr-25
|  | 34 | S1 | #FED8E8 | 02-May-25 | 08-May-25
|  | 161 | EE32 | #F2F09E | 15-Apr-25 | 17-Apr-25
|  | 165 | EE32 | #F2F09E | 19-May-25 | 21-May-25
|  | 189 | S2 | #FED8E8 | 15-Apr-25 | 18-Apr-25
|  | 193 | S2 | #FED8E8 | 19-May-25 | 22-May-25
|  | 209 | J5 | #3598FE | 11-Mar-25 | 12-Mar-25
|  | 221 | J5 | #3598FE | 15-Apr-25 | 16-Apr-25
|  | 262 | J5 | #3598FE | 08-Mar-25 | 11-Mar-25
|  | 274 | J5 | #3598FE | 11-Apr-25 | 15-Apr-25
|  | 343 | Cx2 | #8ED973 | 25-Mar-25 | 25-Mar-25
|  | 355 | Cx2 | #8ED973 | 28-Apr-25 | 28-Apr-25
|  | 370 | J3 | #3598FE | 25-Feb-25 | 27-Feb-25
|  | 379 | EE2 | #F2F09E | 28-Feb-25 | 04-Mar-25
|  | 387 | EE2 | #F2F09E | 04-Apr-25 | 07-Apr-25
|  | 411 | EE10 | #F2F09E | 01-Apr-25 | 05-Apr-25
|  | 415 | EE10 | #F2F09E | 06-May-25 | 10-May-25
|  | 447 | J16 | #3598FE | 25-Mar-25 | 28-Mar-25
|  | 451 | J16 | #3598FE | 28-Apr-25 | 01-May-25
|  | 471 | J21 | #3598FE | 18-Apr-25 | 21-Apr-25
|  | 475 | J21 | #3598FE | 22-May-25 | 23-May-25
|  | 484 | J23 | #3598FE | 03-Apr-25 | 04-Apr-25
|  | 488 | J23 | #3598FE | 08-May-25 | 09-May-25
|  | 498 | J4 | #3598FE | 05-Mar-25 | 07-Mar-25
|  | 502 | J4 | #3598FE | 08-Apr-25 | 10-Apr-25
|  | 541 | J33 | #3598FE | 03-Apr-25 | 08-Apr-25
|  | 545 | J33 | #3598FE | 08-May-25 | 13-May-25
|  | 564 | J3 | #3598FE | 01-Apr-25 | 03-Apr-25
|  | 586 | J37 | #3598FE | 29-Mar-25 | 02-Apr-25
|  | 590 | J37 | #3598FE | 02-May-25 | 07-May-25
|  | 609 | J6 | #3598FE | 15-Mar-25 | 18-Mar-25
|  | 613 | J6 | #3598FE | 19-Apr-25 | 22-Apr-25
|  | 621 | J42 | #3598FE | 19-Mar-25 | 20-Mar-25
|  | 625 | J42 | #3598FE | 23-Apr-25 | 24-Apr-25
|  | 646 | J1 | #3598FE | 24-Feb-25 | 24-Feb-25
|  | 650 | J1 | #3598FE | 31-Mar-25 | 31-Mar-25
|  | 846 | EE1 | #F2F09E | 08-Mar-25 | 12-Mar-25
|  | 858 | EE1 | #F2F09E | 11-Apr-25 | 16-Apr-25
|  | 882 | GSC | #D85234 | 08-Mar-25 | 11-Mar-25
|  | 894 | GSC | #D85234 | 11-Apr-25 | 15-Apr-25
|  | 918 | GSD | #D85234 | 05-Mar-25 | 07-Mar-25
|  | 930 | GSD | #D85234 | 08-Apr-25 | 10-Apr-25
|  | 950 | J44 | #3598FE | 11-Mar-25 | 12-Mar-25
|  | 958 | J44 | #3598FE | 15-Apr-25 | 16-Apr-25
|  | 999 | T1 | #D6F2FF | 12-Mar-25 | 14-Mar-25
|  | 1011 | T1 | #D6F2FF | 16-Apr-25 | 18-Apr-25
|  | 1027 | T3 | #D6F2FF | 21-Mar-25 | 24-Mar-25
|  | 1031 | T3 | #D6F2FF | 25-Apr-25 | 26-Apr-25
|  | 1109 | EE17 | #F2F09E | 22-Apr-25 | 26-Apr-25
|  | 1113 | EE17 | #F2F09E | 27-May-25 | 31-May-25
|  | 1139 | S2 | #FED8E8 | 09-Apr-25 | 14-Apr-25
|  | 1143 | S2 | #FED8E8 | 14-May-25 | 17-May-25
|  | 1199 | EE7 | #F2F09E | 03-Apr-25 | 07-Apr-25
|  | 1203 | EE7 | #F2F09E | 08-May-25 | 12-May-25
|  | 1282 | EE19 | #F2F09E | 01-May-25 | 05-May-25
|  | 1286 | EE19 | #F2F09E | 02-Jun-25 | 04-Jun-25
| CELL 1 Electrical Room | 210 | J5 | #3598FE | 11-Mar-25 | 11-Mar-25
|  | 222 | J5 | #3598FE | 15-Apr-25 | 15-Apr-25
|  | 263 | J5 | #3598FE | 11-Mar-25 | 12-Mar-25
|  | 275 | J5 | #3598FE | 15-Apr-25 | 16-Apr-25
|  | 344 | Cx2 | #8ED973 | 15-Mar-25 | 15-Mar-25
|  | 356 | Cx2 | #8ED973 | 19-Apr-25 | 19-Apr-25
|  | 380 | EE2 | #F2F09E | 04-Mar-25 | 05-Mar-25
|  | 388 | EE2 | #F2F09E | 07-Apr-25 | 08-Apr-25
|  | 427 | EE35 | #F2F09E | 12-Mar-25 | 13-Mar-25
|  | 435 | EE35 | #F2F09E | 16-Apr-25 | 17-Apr-25
|  | 510 | J4 | #3598FE | 06-Mar-25 | 10-Mar-25
|  | 514 | J4 | #3598FE | 09-Apr-25 | 14-Apr-25
|  | 557 | J3 | #3598FE | 28-Feb-25 | 03-Mar-25
|  | 565 | J3 | #3598FE | 04-Apr-25 | 05-Apr-25
|  | 847 | EE1 | #F2F09E | 08-Mar-25 | 11-Mar-25
|  | 859 | EE1 | #F2F09E | 11-Apr-25 | 15-Apr-25
|  | 883 | GSC | #D85234 | 08-Mar-25 | 10-Mar-25
|  | 895 | GSC | #D85234 | 11-Apr-25 | 14-Apr-25
|  | 919 | GSD | #D85234 | 06-Mar-25 | 07-Mar-25
|  | 931 | GSD | #D85234 | 09-Apr-25 | 10-Apr-25
|  | 1000 | T1 | #D6F2FF | 13-Mar-25 | 14-Mar-25
|  | 1012 | T1 | #D6F2FF | 17-Apr-25 | 18-Apr-25
|  | 1067 | EE29 | #F2F09E | 04-Apr-25 | 17-Apr-25
|  | 1069 | EE29 | #F2F09E | 02-May-25 | 15-May-25
|  | 1095 | EE47 | #F2F09E | 18-Apr-25 | 30-Apr-25
|  | 1097 | EE47 | #F2F09E | 16-May-25 | 29-May-25
|  | 1172 | EE53 | #F2F09E | 31-Mar-25 | 03-Apr-25
|  | 1176 | EE53 | #F2F09E | 21-Apr-25 | 01-May-25
|  | 1254 | EE59 | #F2F09E | 18-Apr-25 | 22-Apr-25
|  | 1258 | EE59 | #F2F09E | 16-May-25 | 20-May-25
| CELL 1 Mechanical Gallery | 211 | J5 | #3598FE | 29-Mar-25 | 29-Mar-25
|  | 223 | J5 | #3598FE | 02-May-25 | 02-May-25
|  | 264 | J5 | #3598FE | 29-Mar-25 | 31-Mar-25
|  | 276 | J5 | #3598FE | 02-May-25 | 05-May-25
|  | 345 | Cx2 | #8ED973 | 03-Apr-25 | 05-Apr-25
|  | 357 | Cx2 | #8ED973 | 08-May-25 | 10-May-25
|  | 399 | GBA | #2F3452 | 04-Apr-25 | 16-Apr-25
|  | 403 | GBA | #2F3452 | 09-May-25 | 20-May-25
|  | 428 | EE35 | #F2F09E | 04-Apr-25 | 05-Apr-25
|  | 436 | EE35 | #F2F09E | 09-May-25 | 10-May-25
|  | 459 | J20 | #3598FE | 31-Mar-25 | 03-Apr-25
|  | 463 | J20 | #3598FE | 05-May-25 | 08-May-25
|  | 522 | J4 | #3598FE | 27-Mar-25 | 28-Mar-25
|  | 526 | J4 | #3598FE | 30-Apr-25 | 01-May-25
|  | 848 | EE1 | #F2F09E | 11-Mar-25 | 13-Mar-25
|  | 860 | EE1 | #F2F09E | 15-Apr-25 | 17-Apr-25
|  | 884 | GSC | #D85234 | 11-Mar-25 | 12-Mar-25
|  | 896 | GSC | #D85234 | 15-Apr-25 | 16-Apr-25
|  | 920 | GSD | #D85234 | 08-Mar-25 | 10-Mar-25
|  | 932 | GSD | #D85234 | 11-Apr-25 | 14-Apr-25
|  | 951 | J44 | #3598FE | 14-Mar-25 | 20-Mar-25
|  | 959 | J44 | #3598FE | 18-Apr-25 | 24-Apr-25
|  | 970 | GPA | #2A4D4F | 21-Mar-25 | 28-Mar-25
|  | 974 | GPA | #2A4D4F | 25-Apr-25 | 01-May-25
|  | 1001 | T1 | #D6F2FF | 01-Apr-25 | 02-Apr-25
|  | 1013 | T1 | #D6F2FF | 06-May-25 | 07-May-25
|  | 1056 | GBB | #2F3452 | 17-Apr-25 | 25-Apr-25
|  | 1060 | GBB | #2F3452 | 21-May-25 | 30-May-25
|  | 1081 | EE42 | #F2F09E | 11-Apr-25 | 25-Apr-25
|  | 1085 | EE42 | #F2F09E | 16-May-25 | 30-May-25
|  | 1187 | EE57 | #F2F09E | 07-Apr-25 | 10-Apr-25
|  | 1191 | EE57 | #F2F09E | 12-May-25 | 15-May-25
|  | 1266 | EE60 | #F2F09E | 26-Apr-25 | 30-Apr-25
|  | 1270 | EE60 | #F2F09E | 31-May-25 | 04-Jun-25
| CELL 1 Punchlist | 1126 | PU1 | #A02B93 | 17-Apr-25 | 28-Apr-25
|  | 1127 | PU1 | #A02B93 | 06-May-25 | 16-May-25
|  | 1131 | PU1 | #A02B93 | 05-Jun-25 | 17-Jun-25
| CELL 2 Data Hall | 31 | S1 | #FED8E8 | 07-Apr-25 | 11-Apr-25
|  | 35 | S1 | #FED8E8 | 12-May-25 | 16-May-25
|  | 162 | EE32 | #F2F09E | 23-Apr-25 | 25-Apr-25
|  | 166 | EE32 | #F2F09E | 28-May-25 | 30-May-25
|  | 190 | S2 | #FED8E8 | 23-Apr-25 | 26-Apr-25
|  | 194 | S2 | #FED8E8 | 28-May-25 | 31-May-25
|  | 212 | J5 | #3598FE | 19-Mar-25 | 20-Mar-25
|  | 224 | J5 | #3598FE | 23-Apr-25 | 24-Apr-25
|  | 265 | J5 | #3598FE | 17-Mar-25 | 19-Mar-25
|  | 277 | J5 | #3598FE | 21-Apr-25 | 23-Apr-25
|  | 346 | Cx2 | #8ED973 | 02-Apr-25 | 02-Apr-25
|  | 358 | Cx2 | #8ED973 | 07-May-25 | 07-May-25
|  | 381 | EE2 | #F2F09E | 10-Mar-25 | 12-Mar-25
|  | 389 | EE2 | #F2F09E | 14-Apr-25 | 16-Apr-25
|  | 412 | EE10 | #F2F09E | 09-Apr-25 | 15-Apr-25
|  | 416 | EE10 | #F2F09E | 14-May-25 | 19-May-25
|  | 448 | J16 | #3598FE | 02-Apr-25 | 05-Apr-25
|  | 452 | J16 | #3598FE | 07-May-25 | 10-May-25
|  | 472 | J21 | #3598FE | 26-Apr-25 | 29-Apr-25
|  | 476 | J21 | #3598FE | 31-May-25 | 03-Jun-25
|  | 485 | J23 | #3598FE | 11-Apr-25 | 14-Apr-25
|  | 489 | J23 | #3598FE | 16-May-25 | 17-May-25
|  | 499 | J4 | #3598FE | 13-Mar-25 | 15-Mar-25
|  | 503 | J4 | #3598FE | 17-Apr-25 | 19-Apr-25
|  | 542 | J33 | #3598FE | 11-Apr-25 | 17-Apr-25
|  | 546 | J33 | #3598FE | 16-May-25 | 21-May-25
|  | 558 | J3 | #3598FE | 06-Mar-25 | 08-Mar-25
|  | 566 | J3 | #3598FE | 09-Apr-25 | 11-Apr-25
|  | 587 | J37 | #3598FE | 07-Apr-25 | 10-Apr-25
|  | 591 | J37 | #3598FE | 12-May-25 | 15-May-25
|  | 610 | J6 | #3598FE | 25-Mar-25 | 27-Mar-25
|  | 614 | J6 | #3598FE | 28-Apr-25 | 30-Apr-25
|  | 622 | J42 | #3598FE | 28-Mar-25 | 29-Mar-25
|  | 626 | J42 | #3598FE | 01-May-25 | 02-May-25
|  | 647 | J1 | #3598FE | 05-Mar-25 | 05-Mar-25
|  | 651 | J1 | #3598FE | 08-Apr-25 | 08-Apr-25
|  | 849 | EE1 | #F2F09E | 17-Mar-25 | 20-Mar-25
|  | 861 | EE1 | #F2F09E | 21-Apr-25 | 24-Apr-25
|  | 885 | GSC | #D85234 | 17-Mar-25 | 19-Mar-25
|  | 897 | GSC | #D85234 | 21-Apr-25 | 23-Apr-25
|  | 921 | GSD | #D85234 | 13-Mar-25 | 15-Mar-25
|  | 933 | GSD | #D85234 | 17-Apr-25 | 19-Apr-25
|  | 952 | J44 | #3598FE | 19-Mar-25 | 20-Mar-25
|  | 960 | J44 | #3598FE | 23-Apr-25 | 24-Apr-25
|  | 1002 | T1 | #D6F2FF | 20-Mar-25 | 24-Mar-25
|  | 1014 | T1 | #D6F2FF | 24-Apr-25 | 26-Apr-25
|  | 1028 | T3 | #D6F2FF | 31-Mar-25 | 01-Apr-25
|  | 1032 | T3 | #D6F2FF | 05-May-25 | 06-May-25
|  | 1110 | EE17 | #F2F09E | 30-Apr-25 | 06-May-25
|  | 1114 | EE17 | #F2F09E | 04-Jun-25 | 09-Jun-25
|  | 1140 | S2 | #FED8E8 | 18-Apr-25 | 22-Apr-25
|  | 1144 | S2 | #FED8E8 | 22-May-25 | 27-May-25
|  | 1200 | EE7 | #F2F09E | 11-Apr-25 | 16-Apr-25
|  | 1204 | EE7 | #F2F09E | 16-May-25 | 20-May-25
|  | 1283 | EE19 | #F2F09E | 28-May-25 | 30-May-25
|  | 1287 | EE19 | #F2F09E | 25-Jun-25 | 27-Jun-25
| CELL 2 Electrical Room | 213 | J5 | #3598FE | 19-Mar-25 | 19-Mar-25
|  | 225 | J5 | #3598FE | 23-Apr-25 | 23-Apr-25
|  | 266 | J5 | #3598FE | 19-Mar-25 | 20-Mar-25
|  | 278 | J5 | #3598FE | 23-Apr-25 | 24-Apr-25
|  | 347 | Cx2 | #8ED973 | 25-Mar-25 | 25-Mar-25
|  | 359 | Cx2 | #8ED973 | 28-Apr-25 | 28-Apr-25
|  | 382 | EE2 | #F2F09E | 12-Mar-25 | 13-Mar-25
|  | 390 | EE2 | #F2F09E | 16-Apr-25 | 17-Apr-25
|  | 429 | EE35 | #F2F09E | 20-Mar-25 | 21-Mar-25
|  | 437 | EE35 | #F2F09E | 24-Apr-25 | 25-Apr-25
|  | 511 | J4 | #3598FE | 14-Mar-25 | 18-Mar-25
|  | 515 | J4 | #3598FE | 18-Apr-25 | 22-Apr-25
|  | 559 | J3 | #3598FE | 10-Mar-25 | 11-Mar-25
|  | 567 | J3 | #3598FE | 14-Apr-25 | 15-Apr-25
|  | 850 | EE1 | #F2F09E | 17-Mar-25 | 19-Mar-25
|  | 862 | EE1 | #F2F09E | 21-Apr-25 | 23-Apr-25
|  | 886 | GSC | #D85234 | 17-Mar-25 | 18-Mar-25
|  | 898 | GSC | #D85234 | 21-Apr-25 | 22-Apr-25
|  | 922 | GSD | #D85234 | 14-Mar-25 | 15-Mar-25
|  | 934 | GSD | #D85234 | 18-Apr-25 | 19-Apr-25
|  | 1003 | T1 | #D6F2FF | 21-Mar-25 | 24-Mar-25
|  | 1015 | T1 | #D6F2FF | 25-Apr-25 | 26-Apr-25
|  | 1068 | EE29 | #F2F09E | 01-May-25 | 14-May-25
|  | 1070 | EE29 | #F2F09E | 30-May-25 | 11-Jun-25
|  | 1096 | EE47 | #F2F09E | 15-May-25 | 27-May-25
|  | 1098 | EE47 | #F2F09E | 12-Jun-25 | 24-Jun-25
|  | 1173 | EE53 | #F2F09E | 26-Mar-25 | 29-Mar-25
|  | 1177 | EE53 | #F2F09E | 29-Apr-25 | 02-May-25
|  | 1255 | EE59 | #F2F09E | 15-May-25 | 19-May-25
|  | 1259 | EE59 | #F2F09E | 12-Jun-25 | 17-Jun-25
| CELL 2 Mechanical Gallery | 214 | J5 | #3598FE | 07-Apr-25 | 07-Apr-25
|  | 226 | J5 | #3598FE | 12-May-25 | 12-May-25
|  | 267 | J5 | #3598FE | 07-Apr-25 | 08-Apr-25
|  | 279 | J5 | #3598FE | 12-May-25 | 13-May-25
|  | 348 | Cx2 | #8ED973 | 11-Apr-25 | 15-Apr-25
|  | 360 | Cx2 | #8ED973 | 16-May-25 | 19-May-25
|  | 400 | GBA | #2F3452 | 14-Apr-25 | 24-Apr-25
|  | 404 | GBA | #2F3452 | 17-May-25 | 29-May-25
|  | 430 | EE35 | #F2F09E | 14-Apr-25 | 15-Apr-25
|  | 438 | EE35 | #F2F09E | 17-May-25 | 19-May-25
|  | 460 | J20 | #3598FE | 08-Apr-25 | 11-Apr-25
|  | 464 | J20 | #3598FE | 13-May-25 | 16-May-25
|  | 523 | J4 | #3598FE | 04-Apr-25 | 05-Apr-25
|  | 527 | J4 | #3598FE | 09-May-25 | 10-May-25
|  | 851 | EE1 | #F2F09E | 19-Mar-25 | 21-Mar-25
|  | 863 | EE1 | #F2F09E | 23-Apr-25 | 25-Apr-25
|  | 887 | GSC | #D85234 | 19-Mar-25 | 20-Mar-25
|  | 899 | GSC | #D85234 | 23-Apr-25 | 24-Apr-25
|  | 923 | GSD | #D85234 | 17-Mar-25 | 18-Mar-25
|  | 935 | GSD | #D85234 | 21-Apr-25 | 22-Apr-25
|  | 953 | J44 | #3598FE | 24-Mar-25 | 29-Mar-25
|  | 961 | J44 | #3598FE | 26-Apr-25 | 02-May-25
|  | 971 | GPA | #2A4D4F | 31-Mar-25 | 05-Apr-25
|  | 975 | GPA | #2A4D4F | 05-May-25 | 10-May-25
|  | 1004 | T1 | #D6F2FF | 09-Apr-25 | 10-Apr-25
|  | 1016 | T1 | #D6F2FF | 14-May-25 | 15-May-25
|  | 1057 | GBB | #2F3452 | 25-Apr-25 | 05-May-25
|  | 1061 | GBB | #2F3452 | 30-May-25 | 07-Jun-25
|  | 1082 | EE42 | #F2F09E | 21-Apr-25 | 05-May-25
|  | 1086 | EE42 | #F2F09E | 27-May-25 | 07-Jun-25
|  | 1188 | EE57 | #F2F09E | 16-Apr-25 | 19-Apr-25
|  | 1192 | EE57 | #F2F09E | 20-May-25 | 23-May-25
|  | 1267 | EE60 | #F2F09E | 06-May-25 | 09-May-25
|  | 1271 | EE60 | #F2F09E | 09-Jun-25 | 12-Jun-25
| CELL 2 Punchlist | 1128 | PU1 | #A02B93 | 31-May-25 | 11-Jun-25
|  | 1132 | PU1 | #A02B93 | 28-Jun-25 | 11-Jul-25
| CELL 3 Data Hall | 32 | S1 | #FED8E8 | 30-Apr-25 | 06-May-25
|  | 36 | S1 | #FED8E8 | 04-Jun-25 | 09-Jun-25
|  | 163 | EE32 | #F2F09E | 16-May-25 | 19-May-25
|  | 167 | EE32 | #F2F09E | 20-Jun-25 | 23-Jun-25
|  | 191 | S2 | #FED8E8 | 16-May-25 | 20-May-25
|  | 195 | S2 | #FED8E8 | 20-Jun-25 | 24-Jun-25
|  | 215 | J5 | #3598FE | 11-Apr-25 | 14-Apr-25
|  | 227 | J5 | #3598FE | 16-May-25 | 17-May-25
|  | 268 | J5 | #3598FE | 09-Apr-25 | 11-Apr-25
|  | 280 | J5 | #3598FE | 14-May-25 | 16-May-25
|  | 349 | Cx2 | #8ED973 | 25-Apr-25 | 25-Apr-25
|  | 361 | Cx2 | #8ED973 | 30-May-25 | 30-May-25
|  | 383 | EE2 | #F2F09E | 02-Apr-25 | 04-Apr-25
|  | 391 | EE2 | #F2F09E | 07-May-25 | 09-May-25
|  | 413 | EE10 | #F2F09E | 02-May-25 | 08-May-25
|  | 417 | EE10 | #F2F09E | 06-Jun-25 | 11-Jun-25
|  | 449 | J16 | #3598FE | 25-Apr-25 | 29-Apr-25
|  | 453 | J16 | #3598FE | 30-May-25 | 03-Jun-25
|  | 473 | J21 | #3598FE | 20-May-25 | 22-May-25
|  | 477 | J21 | #3598FE | 24-Jun-25 | 26-Jun-25
|  | 486 | J23 | #3598FE | 06-May-25 | 07-May-25
|  | 490 | J23 | #3598FE | 09-Jun-25 | 10-Jun-25
|  | 500 | J4 | #3598FE | 05-Apr-25 | 08-Apr-25
|  | 504 | J4 | #3598FE | 10-May-25 | 13-May-25
|  | 543 | J33 | #3598FE | 06-May-25 | 10-May-25
|  | 547 | J33 | #3598FE | 09-Jun-25 | 13-Jun-25
|  | 560 | J3 | #3598FE | 29-Mar-25 | 01-Apr-25
|  | 568 | J3 | #3598FE | 02-May-25 | 06-May-25
|  | 588 | J37 | #3598FE | 30-Apr-25 | 05-May-25
|  | 592 | J37 | #3598FE | 04-Jun-25 | 07-Jun-25
|  | 611 | J6 | #3598FE | 17-Apr-25 | 19-Apr-25
|  | 615 | J6 | #3598FE | 21-May-25 | 23-May-25
|  | 623 | J42 | #3598FE | 21-Apr-25 | 22-Apr-25
|  | 627 | J42 | #3598FE | 27-May-25 | 27-May-25
|  | 648 | J1 | #3598FE | 28-Mar-25 | 28-Mar-25
|  | 652 | J1 | #3598FE | 01-May-25 | 01-May-25
|  | 852 | EE1 | #F2F09E | 09-Apr-25 | 14-Apr-25
|  | 864 | EE1 | #F2F09E | 14-May-25 | 17-May-25
|  | 888 | GSC | #D85234 | 09-Apr-25 | 11-Apr-25
|  | 900 | GSC | #D85234 | 14-May-25 | 16-May-25
|  | 924 | GSD | #D85234 | 05-Apr-25 | 08-Apr-25
|  | 936 | GSD | #D85234 | 10-May-25 | 13-May-25
|  | 954 | J44 | #3598FE | 11-Apr-25 | 14-Apr-25
|  | 962 | J44 | #3598FE | 16-May-25 | 17-May-25
|  | 1005 | T1 | #D6F2FF | 14-Apr-25 | 16-Apr-25
|  | 1017 | T1 | #D6F2FF | 17-May-25 | 20-May-25
|  | 1029 | T3 | #D6F2FF | 23-Apr-25 | 24-Apr-25
|  | 1033 | T3 | #D6F2FF | 28-May-25 | 29-May-25
|  | 1111 | EE17 | #F2F09E | 23-May-25 | 29-May-25
|  | 1115 | EE17 | #F2F09E | 27-Jun-25 | 02-Jul-25
|  | 1141 | S2 | #FED8E8 | 12-May-25 | 15-May-25
|  | 1145 | S2 | #FED8E8 | 16-Jun-25 | 19-Jun-25
|  | 1201 | EE7 | #F2F09E | 06-May-25 | 09-May-25
|  | 1205 | EE7 | #F2F09E | 09-Jun-25 | 12-Jun-25
|  | 1284 | EE19 | #F2F09E | 18-Jul-25 | 21-Jul-25
|  | 1288 | EE19 | #F2F09E | 06-Aug-25 | 08-Aug-25
| CELL 3 Electrical Room | 204 | J5 | #3598FE | 08-Mar-25 | 08-Mar-25
|  | 216 | J5 | #3598FE | 11-Apr-25 | 11-Apr-25
|  | 228 | J5 | #3598FE | 16-May-25 | 16-May-25
|  | 257 | J5 | #3598FE | 08-Mar-25 | 10-Mar-25
|  | 269 | J5 | #3598FE | 11-Apr-25 | 14-Apr-25
|  | 281 | J5 | #3598FE | 16-May-25 | 17-May-25
|  | 338 | Cx2 | #8ED973 | 13-Mar-25 | 13-Mar-25
|  | 350 | Cx2 | #8ED973 | 17-Apr-25 | 17-Apr-25
|  | 362 | Cx2 | #8ED973 | 21-May-25 | 21-May-25
|  | 376 | EE2 | #F2F09E | 28-Feb-25 | 03-Mar-25
|  | 384 | EE2 | #F2F09E | 04-Apr-25 | 05-Apr-25
|  | 392 | EE2 | #F2F09E | 09-May-25 | 10-May-25
|  | 423 | EE35 | #F2F09E | 10-Mar-25 | 11-Mar-25
|  | 431 | EE35 | #F2F09E | 14-Apr-25 | 15-Apr-25
|  | 439 | EE35 | #F2F09E | 17-May-25 | 19-May-25
|  | 508 | J4 | #3598FE | 04-Mar-25 | 07-Mar-25
|  | 512 | J4 | #3598FE | 07-Apr-25 | 10-Apr-25
|  | 516 | J4 | #3598FE | 12-May-25 | 15-May-25
|  | 554 | J3 | #3598FE | 26-Feb-25 | 27-Feb-25
|  | 561 | J3 | #3598FE | 02-Apr-25 | 03-Apr-25
|  | 569 | J3 | #3598FE | 07-May-25 | 08-May-25
|  | 841 | EE1 | #F2F09E | 06-Mar-25 | 08-Mar-25
|  | 853 | EE1 | #F2F09E | 09-Apr-25 | 11-Apr-25
|  | 865 | EE1 | #F2F09E | 14-May-25 | 16-May-25
|  | 877 | GSC | #D85234 | 06-Mar-25 | 07-Mar-25
|  | 889 | GSC | #D85234 | 09-Apr-25 | 10-Apr-25
|  | 901 | GSC | #D85234 | 14-May-25 | 15-May-25
|  | 913 | GSD | #D85234 | 04-Mar-25 | 05-Mar-25
|  | 925 | GSD | #D85234 | 07-Apr-25 | 08-Apr-25
|  | 937 | GSD | #D85234 | 12-May-25 | 13-May-25
|  | 994 | T1 | #D6F2FF | 11-Mar-25 | 12-Mar-25
|  | 1006 | T1 | #D6F2FF | 15-Apr-25 | 16-Apr-25
|  | 1018 | T1 | #D6F2FF | 19-May-25 | 20-May-25
|  | 1071 | EE29 | #F2F09E | 10-May-25 | 22-May-25
|  | 1073 | EE29 | #F2F09E | 24-Jun-25 | 08-Jul-25
|  | 1075 | EE29 | #F2F09E | 11-Jul-25 | 23-Jul-25
|  | 1099 | EE47 | #F2F09E | 23-May-25 | 04-Jun-25
|  | 1101 | EE47 | #F2F09E | 09-Jul-25 | 19-Jul-25
|  | 1103 | EE47 | #F2F09E | 24-Jul-25 | 05-Aug-25
|  | 1170 | EE53 | #F2F09E | 14-Mar-25 | 18-Mar-25
|  | 1174 | EE53 | #F2F09E | 18-Apr-25 | 22-Apr-25
|  | 1178 | EE53 | #F2F09E | 22-May-25 | 27-May-25
|  | 1252 | EE59 | #F2F09E | 23-May-25 | 28-May-25
|  | 1256 | EE59 | #F2F09E | 09-Jul-25 | 12-Jul-25
|  | 1260 | EE59 | #F2F09E | 24-Jul-25 | 29-Jul-25
| CELL 3 Mechanical Gallery | 205 | J5 | #3598FE | 27-Mar-25 | 27-Mar-25
|  | 217 | J5 | #3598FE | 30-Apr-25 | 30-Apr-25
|  | 229 | J5 | #3598FE | 04-Jun-25 | 04-Jun-25
|  | 258 | J5 | #3598FE | 27-Mar-25 | 28-Mar-25
|  | 270 | J5 | #3598FE | 30-Apr-25 | 01-May-25
|  | 282 | J5 | #3598FE | 04-Jun-25 | 05-Jun-25
|  | 339 | Cx2 | #8ED973 | 01-Apr-25 | 03-Apr-25
|  | 351 | Cx2 | #8ED973 | 06-May-25 | 08-May-25
|  | 363 | Cx2 | #8ED973 | 09-Jun-25 | 11-Jun-25
|  | 397 | GBA | #2F3452 | 02-Apr-25 | 14-Apr-25
|  | 401 | GBA | #2F3452 | 07-May-25 | 17-May-25
|  | 405 | GBA | #2F3452 | 10-Jun-25 | 21-Jun-25
|  | 424 | EE35 | #F2F09E | 02-Apr-25 | 03-Apr-25
|  | 432 | EE35 | #F2F09E | 07-May-25 | 08-May-25
|  | 440 | EE35 | #F2F09E | 10-Jun-25 | 11-Jun-25
|  | 457 | J20 | #3598FE | 28-Mar-25 | 01-Apr-25
|  | 461 | J20 | #3598FE | 01-May-25 | 06-May-25
|  | 465 | J20 | #3598FE | 05-Jun-25 | 09-Jun-25
|  | 520 | J4 | #3598FE | 25-Mar-25 | 26-Mar-25
|  | 524 | J4 | #3598FE | 28-Apr-25 | 29-Apr-25
|  | 528 | J4 | #3598FE | 02-Jun-25 | 03-Jun-25
|  | 842 | EE1 | #F2F09E | 08-Mar-25 | 11-Mar-25
|  | 854 | EE1 | #F2F09E | 11-Apr-25 | 15-Apr-25
|  | 866 | EE1 | #F2F09E | 16-May-25 | 19-May-25
|  | 878 | GSC | #D85234 | 08-Mar-25 | 10-Mar-25
|  | 890 | GSC | #D85234 | 11-Apr-25 | 14-Apr-25
|  | 902 | GSC | #D85234 | 16-May-25 | 17-May-25
|  | 914 | GSD | #D85234 | 06-Mar-25 | 07-Mar-25
|  | 926 | GSD | #D85234 | 09-Apr-25 | 10-Apr-25
|  | 938 | GSD | #D85234 | 14-May-25 | 15-May-25
|  | 947 | J44 | #3598FE | 12-Mar-25 | 18-Mar-25
|  | 955 | J44 | #3598FE | 16-Apr-25 | 22-Apr-25
|  | 963 | J44 | #3598FE | 20-May-25 | 27-May-25
|  | 968 | GPA | #2A4D4F | 19-Mar-25 | 26-Mar-25
|  | 972 | GPA | #2A4D4F | 23-Apr-25 | 29-Apr-25
|  | 976 | GPA | #2A4D4F | 28-May-25 | 03-Jun-25
|  | 995 | T1 | #D6F2FF | 29-Mar-25 | 31-Mar-25
|  | 1007 | T1 | #D6F2FF | 02-May-25 | 05-May-25
|  | 1019 | T1 | #D6F2FF | 06-Jun-25 | 07-Jun-25
|  | 1054 | GBB | #2F3452 | 15-Apr-25 | 23-Apr-25
|  | 1058 | GBB | #2F3452 | 19-May-25 | 28-May-25
|  | 1062 | GBB | #2F3452 | 23-Jun-25 | 01-Jul-25
|  | 1079 | EE42 | #F2F09E | 09-Apr-25 | 23-Apr-25
|  | 1083 | EE42 | #F2F09E | 14-May-25 | 28-May-25
|  | 1087 | EE42 | #F2F09E | 18-Jun-25 | 01-Jul-25
|  | 1185 | EE57 | #F2F09E | 04-Apr-25 | 08-Apr-25
|  | 1189 | EE57 | #F2F09E | 09-May-25 | 13-May-25
|  | 1193 | EE57 | #F2F09E | 12-Jun-25 | 17-Jun-25
|  | 1264 | EE60 | #F2F09E | 24-Apr-25 | 28-Apr-25
|  | 1268 | EE60 | #F2F09E | 29-May-25 | 02-Jun-25
|  | 1272 | EE60 | #F2F09E | 02-Jul-25 | 08-Jul-25
| CELL 3 Punchlist | 1124 | PU1 | #A02B93 | 09-Jun-25 | 20-Jun-25
|  | 1129 | PU1 | #A02B93 | 22-Jul-25 | 02-Aug-25
|  | 1133 | PU1 | #A02B93 | 09-Aug-25 | 21-Aug-25
| CELL 4 Data Hall | 29 | S1 | #FED8E8 | 14-Mar-25 | 19-Mar-25
|  | 33 | S1 | #FED8E8 | 18-Apr-25 | 23-Apr-25
|  | 160 | EE32 | #F2F09E | 31-Mar-25 | 02-Apr-25
|  | 164 | EE32 | #F2F09E | 05-May-25 | 07-May-25
|  | 188 | S2 | #FED8E8 | 31-Mar-25 | 03-Apr-25
|  | 192 | S2 | #FED8E8 | 05-May-25 | 08-May-25
|  | 206 | J5 | #3598FE | 24-Feb-25 | 25-Feb-25
|  | 218 | J5 | #3598FE | 31-Mar-25 | 01-Apr-25
|  | 259 | J5 | #3598FE | 21-Feb-25 | 24-Feb-25
|  | 271 | J5 | #3598FE | 28-Mar-25 | 31-Mar-25
|  | 340 | Cx2 | #8ED973 | 10-Mar-25 | 10-Mar-25
|  | 352 | Cx2 | #8ED973 | 14-Apr-25 | 14-Apr-25
|  | 377 | EE2 | #F2F09E | 14-Feb-25 | 17-Feb-25
|  | 385 | EE2 | #F2F09E | 20-Mar-25 | 24-Mar-25
|  | 410 | EE10 | #F2F09E | 17-Mar-25 | 21-Mar-25
|  | 414 | EE10 | #F2F09E | 21-Apr-25 | 25-Apr-25
|  | 446 | J16 | #3598FE | 10-Mar-25 | 13-Mar-25
|  | 450 | J16 | #3598FE | 14-Apr-25 | 17-Apr-25
|  | 470 | J21 | #3598FE | 03-Apr-25 | 05-Apr-25
|  | 474 | J21 | #3598FE | 08-May-25 | 10-May-25
|  | 483 | J23 | #3598FE | 19-Mar-25 | 20-Mar-25
|  | 487 | J23 | #3598FE | 23-Apr-25 | 24-Apr-25
|  | 497 | J4 | #3598FE | 18-Feb-25 | 20-Feb-25
|  | 501 | J4 | #3598FE | 25-Mar-25 | 27-Mar-25
|  | 540 | J33 | #3598FE | 19-Mar-25 | 25-Mar-25
|  | 544 | J33 | #3598FE | 23-Apr-25 | 28-Apr-25
|  | 555 | J3 | #3598FE | 11-Feb-25 | 13-Feb-25
|  | 562 | J3 | #3598FE | 17-Mar-25 | 19-Mar-25
|  | 585 | J37 | #3598FE | 14-Mar-25 | 18-Mar-25
|  | 589 | J37 | #3598FE | 18-Apr-25 | 22-Apr-25
|  | 608 | J6 | #3598FE | 28-Feb-25 | 04-Mar-25
|  | 612 | J6 | #3598FE | 04-Apr-25 | 07-Apr-25
|  | 620 | J42 | #3598FE | 05-Mar-25 | 06-Mar-25
|  | 624 | J42 | #3598FE | 08-Apr-25 | 09-Apr-25
|  | 645 | J1 | #3598FE | 10-Feb-25 | 10-Feb-25
|  | 649 | J1 | #3598FE | 15-Mar-25 | 15-Mar-25
|  | 843 | EE1 | #F2F09E | 21-Feb-25 | 25-Feb-25
|  | 855 | EE1 | #F2F09E | 28-Mar-25 | 01-Apr-25
|  | 879 | GSC | #D85234 | 21-Feb-25 | 24-Feb-25
|  | 891 | GSC | #D85234 | 28-Mar-25 | 31-Mar-25
|  | 915 | GSD | #D85234 | 18-Feb-25 | 20-Feb-25
|  | 927 | GSD | #D85234 | 25-Mar-25 | 27-Mar-25
|  | 948 | J44 | #3598FE | 24-Feb-25 | 25-Feb-25
|  | 956 | J44 | #3598FE | 31-Mar-25 | 01-Apr-25
|  | 996 | T1 | #D6F2FF | 25-Feb-25 | 27-Feb-25
|  | 1008 | T1 | #D6F2FF | 01-Apr-25 | 03-Apr-25
|  | 1026 | T3 | #D6F2FF | 07-Mar-25 | 08-Mar-25
|  | 1030 | T3 | #D6F2FF | 10-Apr-25 | 11-Apr-25
|  | 1108 | EE17 | #F2F09E | 07-Apr-25 | 11-Apr-25
|  | 1112 | EE17 | #F2F09E | 12-May-25 | 16-May-25
|  | 1138 | S2 | #FED8E8 | 26-Mar-25 | 29-Mar-25
|  | 1142 | S2 | #FED8E8 | 29-Apr-25 | 02-May-25
|  | 1198 | EE7 | #F2F09E | 19-Mar-25 | 24-Mar-25
|  | 1202 | EE7 | #F2F09E | 23-Apr-25 | 26-Apr-25
|  | 1281 | EE19 | #F2F09E | 10-May-25 | 13-May-25
|  | 1285 | EE19 | #F2F09E | 24-Jun-25 | 26-Jun-25
| CELL 4 Data Hall Fitout Activities | 37 | S1 | #FED8E8 | 22-May-25 | 28-May-25
|  | 168 | EE32 | #F2F09E | 07-Jun-25 | 10-Jun-25
|  | 196 | S2 | #FED8E8 | 07-Jun-25 | 11-Jun-25
|  | 230 | J5 | #3598FE | 05-May-25 | 06-May-25
|  | 283 | J5 | #3598FE | 01-May-25 | 05-May-25
|  | 364 | Cx2 | #8ED973 | 17-May-25 | 17-May-25
|  | 393 | EE2 | #F2F09E | 24-Apr-25 | 26-Apr-25
|  | 418 | EE10 | #F2F09E | 27-May-25 | 30-May-25
|  | 454 | J16 | #3598FE | 17-May-25 | 21-May-25
|  | 478 | J21 | #3598FE | 11-Jun-25 | 13-Jun-25
|  | 491 | J23 | #3598FE | 28-May-25 | 29-May-25
|  | 505 | J4 | #3598FE | 28-Apr-25 | 30-Apr-25
|  | 548 | J33 | #3598FE | 28-May-25 | 02-Jun-25
|  | 570 | J3 | #3598FE | 21-Apr-25 | 23-Apr-25
|  | 593 | J37 | #3598FE | 22-May-25 | 27-May-25
|  | 616 | J6 | #3598FE | 09-May-25 | 12-May-25
|  | 628 | J42 | #3598FE | 13-May-25 | 14-May-25
|  | 653 | J1 | #3598FE | 19-Apr-25 | 19-Apr-25
|  | 867 | EE1 | #F2F09E | 01-May-25 | 06-May-25
|  | 903 | GSC | #D85234 | 01-May-25 | 05-May-25
|  | 939 | GSD | #D85234 | 28-Apr-25 | 30-Apr-25
|  | 964 | J44 | #3598FE | 05-May-25 | 06-May-25
|  | 1020 | T1 | #D6F2FF | 06-May-25 | 08-May-25
|  | 1034 | T3 | #D6F2FF | 15-May-25 | 16-May-25
|  | 1116 | EE17 | #F2F09E | 16-Jun-25 | 20-Jun-25
|  | 1146 | S2 | #FED8E8 | 03-Jun-25 | 06-Jun-25
|  | 1206 | EE7 | #F2F09E | 28-May-25 | 31-May-25
|  | 1289 | EE19 | #F2F09E | 11-Jul-25 | 14-Jul-25
| CELL 4 Electrical Room | 207 | J5 | #3598FE | 24-Feb-25 | 24-Feb-25
|  | 219 | J5 | #3598FE | 31-Mar-25 | 31-Mar-25
|  | 231 | J5 | #3598FE | 05-May-25 | 05-May-25
|  | 260 | J5 | #3598FE | 24-Feb-25 | 25-Feb-25
|  | 272 | J5 | #3598FE | 31-Mar-25 | 01-Apr-25
|  | 284 | J5 | #3598FE | 05-May-25 | 06-May-25
|  | 341 | Cx2 | #8ED973 | 28-Feb-25 | 28-Feb-25
|  | 353 | Cx2 | #8ED973 | 04-Apr-25 | 04-Apr-25
|  | 365 | Cx2 | #8ED973 | 09-May-25 | 09-May-25
|  | 378 | EE2 | #F2F09E | 17-Feb-25 | 18-Feb-25
|  | 386 | EE2 | #F2F09E | 24-Mar-25 | 25-Mar-25
|  | 394 | EE2 | #F2F09E | 26-Apr-25 | 28-Apr-25
|  | 425 | EE35 | #F2F09E | 25-Feb-25 | 26-Feb-25
|  | 433 | EE35 | #F2F09E | 01-Apr-25 | 02-Apr-25
|  | 441 | EE35 | #F2F09E | 06-May-25 | 07-May-25
|  | 509 | J4 | #3598FE | 19-Feb-25 | 22-Feb-25
|  | 513 | J4 | #3598FE | 26-Mar-25 | 29-Mar-25
|  | 517 | J4 | #3598FE | 29-Apr-25 | 02-May-25
|  | 556 | J3 | #3598FE | 14-Feb-25 | 15-Feb-25
|  | 563 | J3 | #3598FE | 20-Mar-25 | 21-Mar-25
|  | 571 | J3 | #3598FE | 24-Apr-25 | 25-Apr-25
|  | 844 | EE1 | #F2F09E | 21-Feb-25 | 24-Feb-25
|  | 856 | EE1 | #F2F09E | 28-Mar-25 | 31-Mar-25
|  | 868 | EE1 | #F2F09E | 01-May-25 | 05-May-25
|  | 880 | GSC | #D85234 | 21-Feb-25 | 22-Feb-25
|  | 892 | GSC | #D85234 | 28-Mar-25 | 29-Mar-25
|  | 904 | GSC | #D85234 | 01-May-25 | 02-May-25
|  | 916 | GSD | #D85234 | 19-Feb-25 | 20-Feb-25
|  | 928 | GSD | #D85234 | 26-Mar-25 | 27-Mar-25
|  | 940 | GSD | #D85234 | 29-Apr-25 | 30-Apr-25
|  | 997 | T1 | #D6F2FF | 26-Feb-25 | 27-Feb-25
|  | 1009 | T1 | #D6F2FF | 02-Apr-25 | 03-Apr-25
|  | 1021 | T1 | #D6F2FF | 07-May-25 | 08-May-25
|  | 1072 | EE29 | #F2F09E | 07-Mar-25 | 19-Mar-25
|  | 1074 | EE29 | #F2F09E | 28-May-25 | 09-Jun-25
|  | 1076 | EE29 | #F2F09E | 12-Jun-25 | 25-Jun-25
|  | 1100 | EE47 | #F2F09E | 26-Apr-25 | 09-May-25
|  | 1102 | EE47 | #F2F09E | 10-Jun-25 | 23-Jun-25
|  | 1104 | EE47 | #F2F09E | 26-Jun-25 | 10-Jul-25
|  | 1171 | EE53 | #F2F09E | 03-Mar-25 | 06-Mar-25
|  | 1175 | EE53 | #F2F09E | 05-Apr-25 | 09-Apr-25
|  | 1179 | EE53 | #F2F09E | 10-May-25 | 14-May-25
|  | 1253 | EE59 | #F2F09E | 20-Mar-25 | 25-Mar-25
|  | 1257 | EE59 | #F2F09E | 10-Jun-25 | 13-Jun-25
|  | 1261 | EE59 | #F2F09E | 26-Jun-25 | 30-Jun-25
| CELL 4 Mechanical Gallery | 208 | J5 | #3598FE | 14-Mar-25 | 14-Mar-25
|  | 220 | J5 | #3598FE | 18-Apr-25 | 18-Apr-25
|  | 232 | J5 | #3598FE | 22-May-25 | 22-May-25
|  | 261 | J5 | #3598FE | 14-Mar-25 | 15-Mar-25
|  | 273 | J5 | #3598FE | 18-Apr-25 | 19-Apr-25
|  | 285 | J5 | #3598FE | 22-May-25 | 23-May-25
|  | 342 | Cx2 | #8ED973 | 19-Mar-25 | 21-Mar-25
|  | 354 | Cx2 | #8ED973 | 23-Apr-25 | 25-Apr-25
|  | 366 | Cx2 | #8ED973 | 28-May-25 | 30-May-25
|  | 398 | GBA | #2F3452 | 20-Mar-25 | 01-Apr-25
|  | 402 | GBA | #2F3452 | 24-Apr-25 | 06-May-25
|  | 406 | GBA | #2F3452 | 29-May-25 | 09-Jun-25
|  | 426 | EE35 | #F2F09E | 20-Mar-25 | 21-Mar-25
|  | 434 | EE35 | #F2F09E | 24-Apr-25 | 25-Apr-25
|  | 442 | EE35 | #F2F09E | 29-May-25 | 30-May-25
|  | 458 | J20 | #3598FE | 15-Mar-25 | 19-Mar-25
|  | 462 | J20 | #3598FE | 19-Apr-25 | 23-Apr-25
|  | 466 | J20 | #3598FE | 23-May-25 | 28-May-25
|  | 521 | J4 | #3598FE | 12-Mar-25 | 13-Mar-25
|  | 525 | J4 | #3598FE | 16-Apr-25 | 17-Apr-25
|  | 529 | J4 | #3598FE | 20-May-25 | 21-May-25
|  | 845 | EE1 | #F2F09E | 24-Feb-25 | 26-Feb-25
|  | 857 | EE1 | #F2F09E | 31-Mar-25 | 02-Apr-25
|  | 869 | EE1 | #F2F09E | 05-May-25 | 07-May-25
|  | 881 | GSC | #D85234 | 24-Feb-25 | 25-Feb-25
|  | 893 | GSC | #D85234 | 31-Mar-25 | 01-Apr-25
|  | 905 | GSC | #D85234 | 05-May-25 | 06-May-25
|  | 917 | GSD | #D85234 | 21-Feb-25 | 22-Feb-25
|  | 929 | GSD | #D85234 | 28-Mar-25 | 29-Mar-25
|  | 941 | GSD | #D85234 | 01-May-25 | 02-May-25
|  | 949 | J44 | #3598FE | 27-Feb-25 | 06-Mar-25
|  | 957 | J44 | #3598FE | 03-Apr-25 | 09-Apr-25
|  | 965 | J44 | #3598FE | 08-May-25 | 14-May-25
|  | 969 | GPA | #2A4D4F | 07-Mar-25 | 13-Mar-25
|  | 973 | GPA | #2A4D4F | 10-Apr-25 | 17-Apr-25
|  | 977 | GPA | #2A4D4F | 15-May-25 | 21-May-25
|  | 998 | T1 | #D6F2FF | 17-Mar-25 | 18-Mar-25
|  | 1010 | T1 | #D6F2FF | 21-Apr-25 | 22-Apr-25
|  | 1022 | T1 | #D6F2FF | 27-May-25 | 27-May-25
|  | 1055 | GBB | #2F3452 | 02-Apr-25 | 10-Apr-25
|  | 1059 | GBB | #2F3452 | 07-May-25 | 15-May-25
|  | 1063 | GBB | #2F3452 | 10-Jun-25 | 19-Jun-25
|  | 1080 | EE42 | #F2F09E | 28-Mar-25 | 10-Apr-25
|  | 1084 | EE42 | #F2F09E | 01-May-25 | 15-May-25
|  | 1088 | EE42 | #F2F09E | 05-Jun-25 | 19-Jun-25
|  | 1186 | EE57 | #F2F09E | 24-Mar-25 | 27-Mar-25
|  | 1190 | EE57 | #F2F09E | 26-Apr-25 | 30-Apr-25
|  | 1194 | EE57 | #F2F09E | 31-May-25 | 04-Jun-25
|  | 1265 | EE60 | #F2F09E | 11-Apr-25 | 16-Apr-25
|  | 1269 | EE60 | #F2F09E | 16-May-25 | 20-May-25
|  | 1273 | EE60 | #F2F09E | 20-Jun-25 | 24-Jun-25
| CELL 4 Punchlist | 1125 | PU1 | #A02B93 | 10-May-25 | 21-May-25
|  | 1130 | PU1 | #A02B93 | 27-Jun-25 | 10-Jul-25
|  | 1134 | PU1 | #A02B93 | 15-Jul-25 | 25-Jul-25
| COLO 3 - CELL 1 Data Hall | 26 | S1 | #FED8E8 | 22-Feb-25 | 27-Feb-25
|  | 157 | EE32 | #F2F09E | 11-Mar-25 | 13-Mar-25
|  | 185 | S2 | #FED8E8 | 11-Mar-25 | 14-Mar-25
|  | 197 | J5 | #3598FE | 06-Feb-25 | 07-Feb-25
|  | 250 | J5 | #3598FE | 01-Feb-25 | 04-Feb-25
|  | 331 | Cx2 | #8ED973 | 18-Feb-25 | 18-Feb-25
|  | 371 | EE2 | #F2F09E | 25-Jan-25 | 28-Jan-25
|  | 407 | EE10 | #F2F09E | 25-Feb-25 | 03-Mar-25
|  | 443 | J16 | #3598FE | 18-Feb-25 | 21-Feb-25
|  | 467 | J21 | #3598FE | 14-Mar-25 | 17-Mar-25
|  | 480 | J23 | #3598FE | 27-Feb-25 | 28-Feb-25
|  | 494 | J4 | #3598FE | 29-Jan-25 | 31-Jan-25
|  | 537 | J33 | #3598FE | 27-Feb-25 | 05-Mar-25
|  | 549 | J3 | #3598FE | 20-Jan-25 | 24-Jan-25
|  | 582 | J37 | #3598FE | 22-Feb-25 | 26-Feb-25
|  | 605 | J6 | #3598FE | 10-Feb-25 | 12-Feb-25
|  | 617 | J42 | #3598FE | 13-Feb-25 | 14-Feb-25
|  | 642 | J1 | #3598FE | 17-Jan-25 | 17-Jan-25
|  | 834 | EE1 | #F2F09E | 01-Feb-25 | 05-Feb-25
|  | 870 | GSC | #D85234 | 01-Feb-25 | 04-Feb-25
|  | 906 | GSD | #D85234 | 29-Jan-25 | 31-Jan-25
|  | 942 | J44 | #3598FE | 04-Feb-25 | 05-Feb-25
|  | 987 | T1 | #D6F2FF | 05-Feb-25 | 07-Feb-25
|  | 1023 | T3 | #D6F2FF | 15-Feb-25 | 17-Feb-25
|  | 1105 | EE17 | #F2F09E | 18-Mar-25 | 24-Mar-25
|  | 1135 | S2 | #FED8E8 | 06-Mar-25 | 10-Mar-25
|  | 1195 | EE7 | #F2F09E | 27-Feb-25 | 04-Mar-25
|  | 1278 | EE19 | #F2F09E | 14-Apr-25 | 16-Apr-25
| COLO 3 - CELL 1 Electrical Room | 198 | J5 | #3598FE | 15-Feb-25 | 15-Feb-25
|  | 251 | J5 | #3598FE | 22-Feb-25 | 04-Mar-25
|  | 332 | Cx2 | #8ED973 | 07-Mar-25 | 07-Mar-25
|  | 372 | EE2 | #F2F09E | 31-Jan-25 | 10-Feb-25
|  | 419 | EE35 | #F2F09E | 17-Feb-25 | 18-Feb-25
|  | 506 | J4 | #3598FE | 11-Feb-25 | 21-Feb-25
|  | 550 | J3 | #3598FE | 25-Jan-25 | 30-Jan-25
|  | 835 | EE1 | #F2F09E | 13-Feb-25 | 15-Feb-25
|  | 871 | GSC | #D85234 | 13-Feb-25 | 14-Feb-25
|  | 907 | GSD | #D85234 | 11-Feb-25 | 12-Feb-25
|  | 988 | T1 | #D6F2FF | 05-Mar-25 | 06-Mar-25
|  | 1065 | EE29 | #F2F09E | 17-Mar-25 | 29-Mar-25
|  | 1093 | EE47 | #F2F09E | 31-Mar-25 | 11-Apr-25
|  | 1168 | EE53 | #F2F09E | 10-Mar-25 | 15-Mar-25
|  | 1250 | EE59 | #F2F09E | 31-Mar-25 | 03-Apr-25
| COLO 3 - CELL 1 Mechanical Gallery | 199 | J5 | #3598FE | 06-Mar-25 | 06-Mar-25
|  | 252 | J5 | #3598FE | 06-Mar-25 | 07-Mar-25
|  | 333 | Cx2 | #8ED973 | 11-Mar-25 | 13-Mar-25
|  | 395 | GBA | #2F3452 | 12-Mar-25 | 24-Mar-25
|  | 420 | EE35 | #F2F09E | 12-Mar-25 | 13-Mar-25
|  | 455 | J20 | #3598FE | 07-Mar-25 | 11-Mar-25
|  | 518 | J4 | #3598FE | 04-Mar-25 | 05-Mar-25
|  | 836 | EE1 | #F2F09E | 15-Feb-25 | 18-Feb-25
|  | 872 | GSC | #D85234 | 15-Feb-25 | 17-Feb-25
|  | 908 | GSD | #D85234 | 13-Feb-25 | 14-Feb-25
|  | 943 | J44 | #3598FE | 19-Feb-25 | 25-Feb-25
|  | 966 | GPA | #2A4D4F | 26-Feb-25 | 05-Mar-25
|  | 989 | T1 | #D6F2FF | 08-Mar-25 | 10-Mar-25
|  | 1052 | E39 | #F2F09E | 25-Mar-25 | 02-Apr-25
|  | 1077 | EE42 | #F2F09E | 19-Mar-25 | 02-Apr-25
|  | 1183 | EE57 | #F2F09E | 14-Mar-25 | 18-Mar-25
|  | 1262 | EE60 | #F2F09E | 03-Apr-25 | 07-Apr-25
| COLO 3 - CELL 2 Data Hall | 27 | S1 | #FED8E8 | 04-Mar-25 | 08-Mar-25
|  | 158 | EE32 | #F2F09E | 19-Mar-25 | 21-Mar-25
|  | 186 | S2 | #FED8E8 | 19-Mar-25 | 24-Mar-25
|  | 200 | J5 | #3598FE | 13-Feb-25 | 14-Feb-25
|  | 253 | J5 | #3598FE | 11-Feb-25 | 13-Feb-25
|  | 334 | Cx2 | #8ED973 | 26-Feb-25 | 26-Feb-25
|  | 373 | EE2 | #F2F09E | 03-Feb-25 | 05-Feb-25
|  | 408 | EE10 | #F2F09E | 06-Mar-25 | 11-Mar-25
|  | 444 | J16 | #3598FE | 26-Feb-25 | 03-Mar-25
|  | 468 | J21 | #3598FE | 24-Mar-25 | 26-Mar-25
|  | 481 | J23 | #3598FE | 08-Mar-25 | 10-Mar-25
|  | 495 | J4 | #3598FE | 06-Feb-25 | 10-Feb-25
|  | 538 | J33 | #3598FE | 08-Mar-25 | 13-Mar-25
|  | 551 | J3 | #3598FE | 30-Jan-25 | 01-Feb-25
|  | 583 | J37 | #3598FE | 04-Mar-25 | 07-Mar-25
|  | 606 | J6 | #3598FE | 18-Feb-25 | 20-Feb-25
|  | 618 | J42 | #3598FE | 21-Feb-25 | 22-Feb-25
|  | 643 | J1 | #3598FE | 29-Jan-25 | 29-Jan-25
|  | 837 | EE1 | #F2F09E | 11-Feb-25 | 14-Feb-25
|  | 873 | GSC | #D85234 | 11-Feb-25 | 13-Feb-25
|  | 909 | GSD | #D85234 | 06-Feb-25 | 10-Feb-25
|  | 944 | J44 | #3598FE | 13-Feb-25 | 14-Feb-25
|  | 990 | T1 | #D6F2FF | 14-Feb-25 | 17-Feb-25
|  | 1024 | T3 | #D6F2FF | 24-Feb-25 | 25-Feb-25
|  | 1106 | EE17 | #F2F09E | 27-Mar-25 | 01-Apr-25
|  | 1136 | S2 | #FED8E8 | 14-Mar-25 | 18-Mar-25
|  | 1196 | EE7 | #F2F09E | 08-Mar-25 | 12-Mar-25
|  | 1279 | EE19 | #F2F09E | 09-May-25 | 12-May-25
| COLO 3 - CELL 2 Electrical Room | 201 | J5 | #3598FE | 13-Feb-25 | 13-Feb-25
|  | 254 | J5 | #3598FE | 13-Feb-25 | 14-Feb-25
|  | 335 | Cx2 | #8ED973 | 18-Feb-25 | 18-Feb-25
|  | 374 | EE2 | #F2F09E | 05-Feb-25 | 06-Feb-25
|  | 421 | EE35 | #F2F09E | 14-Feb-25 | 15-Feb-25
|  | 507 | J4 | #3598FE | 07-Feb-25 | 12-Feb-25
|  | 552 | J3 | #3598FE | 03-Feb-25 | 04-Feb-25
|  | 838 | EE1 | #F2F09E | 11-Feb-25 | 13-Feb-25
|  | 874 | GSC | #D85234 | 11-Feb-25 | 12-Feb-25
|  | 910 | GSD | #D85234 | 07-Feb-25 | 10-Feb-25
|  | 991 | T1 | #D6F2FF | 15-Feb-25 | 17-Feb-25
|  | 1066 | EE29 | #F2F09E | 14-Apr-25 | 25-Apr-25
|  | 1094 | EE47 | #F2F09E | 26-Apr-25 | 08-May-25
|  | 1169 | EE53 | #F2F09E | 17-Mar-25 | 20-Mar-25
|  | 1251 | EE59 | #F2F09E | 26-Apr-25 | 30-Apr-25
| COLO 3 - CELL 2 Mechanical Gallery | 202 | J5 | #3598FE | 04-Mar-25 | 04-Mar-25
|  | 255 | J5 | #3598FE | 04-Mar-25 | 05-Mar-25
|  | 336 | Cx2 | #8ED973 | 08-Mar-25 | 11-Mar-25
|  | 396 | GBA | #2F3452 | 10-Mar-25 | 20-Mar-25
|  | 422 | EE35 | #F2F09E | 10-Mar-25 | 11-Mar-25
|  | 456 | J20 | #3598FE | 05-Mar-25 | 08-Mar-25
|  | 519 | J4 | #3598FE | 28-Feb-25 | 03-Mar-25
|  | 839 | EE1 | #F2F09E | 13-Feb-25 | 15-Feb-25
|  | 875 | GSC | #D85234 | 13-Feb-25 | 14-Feb-25
|  | 911 | GSD | #D85234 | 11-Feb-25 | 12-Feb-25
|  | 945 | J44 | #3598FE | 17-Feb-25 | 22-Feb-25
|  | 967 | GPA | #2A4D4F | 24-Feb-25 | 03-Mar-25
|  | 992 | T1 | #D6F2FF | 06-Mar-25 | 07-Mar-25
|  | 1053 | GBB | #2F3452 | 21-Mar-25 | 31-Mar-25
|  | 1078 | EE42 | #F2F09E | 17-Mar-25 | 31-Mar-25
|  | 1184 | EE57 | #F2F09E | 12-Mar-25 | 15-Mar-25
|  | 1263 | EE60 | #F2F09E | 01-Apr-25 | 04-Apr-25
| COLO 3 - CELL 2 Punchlist | 1123 | PU1 | #A02B93 | 13-May-25 | 23-May-25
| COLO 3 - CELL 3 Data Hall | 28 | S1 | #FED8E8 | 27-Mar-25 | 01-Apr-25
|  | 159 | EE32 | #F2F09E | 11-Apr-25 | 15-Apr-25
|  | 187 | S2 | #FED8E8 | 11-Apr-25 | 16-Apr-25
|  | 203 | J5 | #3598FE | 08-Mar-25 | 10-Mar-25
|  | 256 | J5 | #3598FE | 06-Mar-25 | 08-Mar-25
|  | 337 | Cx2 | #8ED973 | 21-Mar-25 | 21-Mar-25
|  | 375 | EE2 | #F2F09E | 26-Feb-25 | 28-Feb-25
|  | 409 | EE10 | #F2F09E | 29-Mar-25 | 03-Apr-25
|  | 445 | J16 | #3598FE | 21-Mar-25 | 26-Mar-25
|  | 469 | J21 | #3598FE | 16-Apr-25 | 18-Apr-25
|  | 482 | J23 | #3598FE | 01-Apr-25 | 02-Apr-25
|  | 496 | J4 | #3598FE | 03-Mar-25 | 05-Mar-25
|  | 539 | J33 | #3598FE | 01-Apr-25 | 05-Apr-25
|  | 553 | J3 | #3598FE | 22-Feb-25 | 25-Feb-25
|  | 584 | J37 | #3598FE | 27-Mar-25 | 31-Mar-25
|  | 607 | J6 | #3598FE | 13-Mar-25 | 15-Mar-25
|  | 619 | J42 | #3598FE | 17-Mar-25 | 18-Mar-25
|  | 644 | J1 | #3598FE | 21-Feb-25 | 21-Feb-25
|  | 840 | EE1 | #F2F09E | 06-Mar-25 | 10-Mar-25
|  | 876 | GSC | #D85234 | 06-Mar-25 | 08-Mar-25
|  | 912 | GSD | #D85234 | 03-Mar-25 | 05-Mar-25
|  | 946 | J44 | #3598FE | 08-Mar-25 | 10-Mar-25
|  | 993 | T1 | #D6F2FF | 10-Mar-25 | 12-Mar-25
|  | 1025 | T3 | #D6F2FF | 19-Mar-25 | 20-Mar-25
|  | 1107 | EE17 | #F2F09E | 19-Apr-25 | 24-Apr-25
|  | 1137 | S2 | #FED8E8 | 07-Apr-25 | 10-Apr-25
|  | 1197 | EE7 | #F2F09E | 01-Apr-25 | 04-Apr-25
|  | 1280 | EE19 | #F2F09E | 05-Jun-25 | 07-Jun-25
| Electrical Room | 93 | EE28 | #F2F09E | 04-Feb-25 | 04-Feb-25
|  | 291 | J13 | #3598FE | 28-Jan-25 | 31-Jan-25
|  | 295 | J13 | #3598FE | 20-Jan-25 | 20-Jan-25
|  | 309 | J11 | #3598FE | 21-Jan-25 | 21-Jan-25
|  | 666 | MEP1 | #D86DCD | 22-Jan-25 | 23-Jan-25
|  | 978 | T2 | #D6F2FF | 01-Feb-25 | 03-Feb-25
|  | 1064 | EE24 | #F2F09E | 29-Mar-25 | 11-Apr-25
|  | 1117 | EE29 | #F2F09E | 12-Mar-25 | 28-Mar-25
|  | 1158 | JA | #3598FE | 27-Jan-25 | 27-Jan-25
|  | 1167 | EE53 | #F2F09E | 03-Mar-25 | 11-Mar-25
|  | 1249 | EE58 | #F2F09E | 14-Apr-25 | 17-Apr-25
|  | 1290 | JC | #3598FE | 24-Jan-25 | 25-Jan-25
| Entry Room 1 | 292 | J13 | #3598FE | 30-Jan-25 | 03-Feb-25
|  | 296 | GSB | #D85234 | 21-Jan-25 | 21-Jan-25
|  | 310 | J11 | #3598FE | 22-Jan-25 | 22-Jan-25
|  | 597 | J39 | #3598FE | 06-Feb-25 | 10-Feb-25
|  | 667 | MEP1 | #D86DCD | 24-Jan-25 | 25-Jan-25
|  | 979 | T2 | #D6F2FF | 04-Feb-25 | 05-Feb-25
|  | 1159 | JA | #3598FE | 29-Jan-25 | 29-Jan-25
|  | 1180 | EE54 | #F2F09E | 11-Feb-25 | 14-Feb-25
|  | 1291 | JC | #3598FE | 27-Jan-25 | 28-Jan-25
| Entry Room 2 | 293 | J13 | #3598FE | 01-Feb-25 | 05-Feb-25
|  | 297 | GSB | #D85234 | 22-Jan-25 | 22-Jan-25
|  | 311 | J11 | #3598FE | 23-Jan-25 | 23-Jan-25
|  | 598 | J39 | #3598FE | 10-Feb-25 | 12-Feb-25
|  | 668 | MEP1 | #D86DCD | 27-Jan-25 | 28-Jan-25
|  | 980 | T2 | #D6F2FF | 06-Feb-25 | 07-Feb-25
|  | 1160 | JA | #3598FE | 31-Jan-25 | 31-Jan-25
|  | 1181 | EE55 | #F2F09E | 13-Feb-25 | 17-Feb-25
|  | 1292 | JC | #3598FE | 29-Jan-25 | 30-Jan-25
| FCR (Facilities Control Room) | 294 | J13 | #3598FE | 04-Feb-25 | 07-Feb-25
|  | 298 | GSB | #D85234 | 23-Jan-25 | 23-Jan-25
|  | 312 | J11 | #3598FE | 24-Jan-25 | 24-Jan-25
|  | 599 | J39 | #3598FE | 12-Feb-25 | 14-Feb-25
|  | 669 | MEP1 | #D86DCD | 29-Jan-25 | 30-Jan-25
|  | 981 | T2 | #D6F2FF | 10-Feb-25 | 11-Feb-25
|  | 1090 | EE44 | #F2F09E | 21-Mar-25 | 04-Apr-25
|  | 1091 | EE45 | #F2F09E | 20-Feb-25 | 06-Mar-25
|  | 1092 | EE46 | #F2F09E | 07-Mar-25 | 20-Mar-25
|  | 1118 | EE48 | #F2F09E | 21-Mar-25 | 04-Apr-25
|  | 1119 | EE49 | #F2F09E | 21-Apr-25 | 05-May-25
|  | 1120 | EE50 | #F2F09E | 20-Feb-25 | 06-Mar-25
|  | 1121 | EE51 | #F2F09E | 07-Mar-25 | 20-Mar-25
|  | 1122 | EE52 | #F2F09E | 05-Apr-25 | 19-Apr-25
|  | 1161 | JA | #3598FE | 03-Feb-25 | 03-Feb-25
|  | 1182 | EE56 | #F2F09E | 15-Feb-25 | 19-Feb-25
|  | 1293 | JC | #3598FE | 31-Jan-25 | 01-Feb-25
| Fire Riser Room | 94 | J17 | #3598FE | 18-Feb-25 | 21-Feb-25
|  | 148 | GSA | #D85234 | 22-Feb-25 | 24-Feb-25
|  | 286 | J5 | #3598FE | 12-Feb-25 | 13-Feb-25
|  | 299 | GSB | #D85234 | 27-Jan-25 | 27-Jan-25
|  | 313 | J11 | #3598FE | 28-Jan-25 | 28-Jan-25
|  | 493 | J30 | #3598FE | 31-Jan-25 | 31-Jan-25
|  | 530 | J31 | #3598FE | 29-Jan-25 | 30-Jan-25
|  | 670 | MEP1 | #D86DCD | 05-Feb-25 | 06-Feb-25
|  | 982 | T2 | #D6F2FF | 14-Feb-25 | 15-Feb-25
|  | 1162 | JA | #3598FE | 11-Feb-25 | 11-Feb-25
|  | 1294 | JC | #3598FE | 07-Feb-25 | 10-Feb-25
| Loading Dock | 287 | J5 | #3598FE | 15-Feb-25 | 17-Feb-25
|  | 300 | GSB | #D85234 | 29-Jan-25 | 29-Jan-25
|  | 314 | J11 | #3598FE | 30-Jan-25 | 30-Jan-25
|  | 531 | J31 | #3598FE | 29-Jan-25 | 15-Feb-25
|  | 532 | J31 | #3598FE | 30-Jan-25 | 17-Feb-25
|  | 671 | MEP1 | #D86DCD | 11-Feb-25 | 12-Feb-25
|  | 983 | T2 | #D6F2FF | 18-Feb-25 | 19-Feb-25
|  | 1045 | GPB | #2A4D4F | 20-Feb-25 | 10-Mar-25
|  | 1089 | EE43 | #F2F09E | 11-Mar-25 | 13-Mar-25
|  | 1157 | ML21 | #000000 | 31-Jan-25 | 31-Jan-25
|  | 1295 | JC | #3598FE | 13-Feb-25 | 14-Feb-25
| Punchlist | 39 | PU1 | #A02B93 | 06-May-25 | 09-May-25
|  | 1150 | PU1 | #A02B93 | 27-Jan-25 | 17-Mar-25
| Restrooms & Janitor Room | 95 | J17 | #3598FE | 18-Feb-25 | 21-Feb-25
|  | 288 | J5 | #3598FE | 13-Feb-25 | 14-Feb-25
|  | 301 | GSB | #D85234 | 28-Jan-25 | 28-Jan-25
|  | 315 | J11 | #3598FE | 29-Jan-25 | 29-Jan-25
|  | 672 | MEP1 | #D86DCD | 07-Feb-25 | 10-Feb-25
|  | 984 | T2 | #D6F2FF | 15-Feb-25 | 17-Feb-25
|  | 1296 | JC | #3598FE | 11-Feb-25 | 12-Feb-25
| SER (Security Equipment Room) | 289 | J5 | #3598FE | 06-Feb-25 | 07-Feb-25
|  | 302 | GSB | #D85234 | 24-Jan-25 | 24-Jan-25
|  | 316 | J11 | #3598FE | 25-Jan-25 | 25-Jan-25
|  | 600 | J39 | #3598FE | 12-Feb-25 | 14-Feb-25
|  | 673 | MEP1 | #D86DCD | 31-Jan-25 | 01-Feb-25
|  | 985 | T2 | #D6F2FF | 10-Feb-25 | 11-Feb-25
|  | 1163 | JA | #3598FE | 05-Feb-25 | 05-Feb-25
|  | 1207 | S3 | #FED8E8 | 15-Feb-25 | 19-Feb-25
|  | 1297 | JC | #3598FE | 03-Feb-25 | 04-Feb-25
| STORAGE (High Value & Secure) Rooms | 290 | J5 | #3598FE | 26-Feb-25 | 03-Mar-25
|  | 303 | GSB | #D85234 | 25-Jan-25 | 25-Jan-25
|  | 304 | GSB | #D85234 | 06-Mar-25 | 17-Mar-25
|  | 317 | J11 | #3598FE | 27-Jan-25 | 27-Jan-25
|  | 533 | J31 | #3598FE | 07-Feb-25 | 25-Feb-25
|  | 674 | MEP1 | #D86DCD | 03-Feb-25 | 04-Feb-25
|  | 986 | T2 | #D6F2FF | 04-Mar-25 | 05-Mar-25
|  | 1298 | JC | #3598FE | 05-Feb-25 | 06-Feb-25
MSFT OFCI ROJ Dates | COLO 3 | 687 | ROJ1 | #747474 | 05-Sep-24 | 05-Sep-24
|  | 689 | ROJ3 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 690 | ROJ4 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 691 | ROJ5 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 692 | ROJ6 | #747474 | 13-Mar-25 | 13-Mar-25
|  | 695 | ROJ9 | #747474 | 09-Mar-25 | 13-Mar-25
|  | 698 | ROJ12 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 701 | ROJ15 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 704 | ROJ18 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 707 | ROJ21 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 710 | ROJ24 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 711 | ROJ25 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 716 | ROJ30 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 717 | ROJ31 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 722 | ROJ36 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 723 | ROJ37 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 728 | ROJ42 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 729 | ROJ43 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 730 | ROJ44 | #747474 | 21-Feb-25 | 21-Feb-25
|  | 733 | ROJ47 | #747474 | 19-Feb-25 | 21-Feb-25
|  | 740 | ROJ54 | #747474 | 04-Mar-25 | 04-Mar-25
|  | 741 | ROJ55 | #747474 | 28-Feb-25 | 04-Mar-25
|  | 742 | ROJ56 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 745 | ROJ59 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 754 | ROJ68 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 755 | ROJ69 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 758 | ROJ72 | #747474 | 24-Feb-25 | 24-Feb-25
|  | 759 | ROJ73 | #747474 | 20-Feb-25 | 24-Feb-25
|  | 764 | ROJ78 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 765 | ROJ79 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 776 | ROJ90 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 777 | ROJ91 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 778 | ROJ92 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 786 | ROJ100 | #747474 | 30-Nov-24 | 30-Nov-24
|  | 789 | ROJ103 | #747474 | 05-Sep-24 | 05-Sep-24
|  | 792 | ROJ106 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 797 | ROJ111 | #747474 | 28-Feb-25 | 28-Feb-25
|  | 800 | ROJ114 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 803 | ROJ117 | #747474 | 05-Sep-24 | 05-Sep-24
|  | 806 | ROJ120 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 809 | ROJ123 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 812 | ROJ126 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 814 | ROJ128 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 819 | ROJ133 | #747474 | 05-Sep-24 | 05-Sep-24
|  | 826 | ROJ140 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 827 | ROJ141 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 828 | ROJ142 | #747474 | 24-Feb-25 | 28-Feb-25
|  | 831 | ROJ145 | #747474 | 19-Feb-25 | 23-Feb-25
| COLO 3-5 | 770 | ROJ84 | #747474 | 25-Oct-24 | 25-Oct-24
|  | 771 | ROJ85 | #747474 | 21-Oct-24 | 25-Oct-24
|  | 811 | ROJ125 | #747474 | 03-Oct-24 | 03-Oct-24
| COLO 4 | 688 | ROJ2 | #747474 | 09-Sep-24 | 09-Sep-24
|  | 693 | ROJ7 | #747474 | 05-Apr-25 | 05-Apr-25
|  | 696 | ROJ10 | #747474 | 01-Apr-25 | 05-Apr-25
|  | 699 | ROJ13 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 702 | ROJ16 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 705 | ROJ19 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 708 | ROJ22 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 712 | ROJ26 | #747474 | 04-Jan-25 | 04-Jan-25
|  | 714 | ROJ28 | #747474 | 29-Dec-24 | 04-Jan-25
|  | 718 | ROJ32 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 720 | ROJ34 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 724 | ROJ38 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 725 | ROJ39 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 731 | ROJ45 | #747474 | 28-Mar-25 | 28-Mar-25
|  | 734 | ROJ48 | #747474 | 26-Mar-25 | 28-Mar-25
|  | 736 | ROJ50 | #747474 | 02-Mar-25 | 02-Mar-25
|  | 738 | ROJ52 | #747474 | 28-Feb-25 | 02-Mar-25
|  | 743 | ROJ57 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 746 | ROJ60 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 748 | ROJ62 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 750 | ROJ64 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 752 | ROJ66 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 753 | ROJ67 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 760 | ROJ74 | #747474 | 10-Apr-25 | 10-Apr-25
|  | 761 | ROJ75 | #747474 | 06-Apr-25 | 10-Apr-25
|  | 766 | ROJ80 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 768 | ROJ82 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 772 | ROJ86 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 774 | ROJ88 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 781 | ROJ95 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 782 | ROJ96 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 785 | ROJ99 | #747474 | 29-Dec-24 | 29-Dec-24
|  | 787 | ROJ101 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 790 | ROJ104 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 793 | ROJ107 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 795 | ROJ109 | #747474 | 28-Feb-25 | 28-Feb-25
|  | 798 | ROJ112 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 801 | ROJ115 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 804 | ROJ118 | #747474 | 05-Sep-24 | 05-Sep-24
|  | 807 | ROJ121 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 816 | ROJ130 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 817 | ROJ131 | #747474 | 05-Sep-24 | 05-Sep-24
|  | 820 | ROJ134 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 821 | ROJ135 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 822 | ROJ136 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 824 | ROJ138 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 829 | ROJ143 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 832 | ROJ146 | #747474 | 26-Mar-25 | 30-Mar-25
| COLO 5 | 694 | ROJ8 | #747474 | 11-May-25 | 11-May-25
|  | 697 | ROJ11 | #747474 | 11-May-25 | 11-May-25
|  | 700 | ROJ14 | #747474 | 04-Apr-25 | 04-Apr-25
|  | 703 | ROJ17 | #747474 | 30-Mar-25 | 04-Apr-25
|  | 706 | ROJ20 | #747474 | 20-Apr-25 | 20-Apr-25
|  | 709 | ROJ23 | #747474 | 20-Apr-25 | 20-Apr-25
|  | 713 | ROJ27 | #747474 | 02-Feb-25 | 02-Feb-25
|  | 715 | ROJ29 | #747474 | 28-Jan-25 | 02-Feb-25
|  | 719 | ROJ33 | #747474 | 03-May-25 | 03-May-25
|  | 721 | ROJ35 | #747474 | 29-Apr-25 | 03-May-25
|  | 726 | ROJ40 | #747474 | 20-Apr-25 | 20-Apr-25
|  | 727 | ROJ41 | #747474 | 20-Apr-25 | 20-Apr-25
|  | 732 | ROJ46 | #747474 | 28-Apr-25 | 28-Apr-25
|  | 735 | ROJ49 | #747474 | 25-Apr-25 | 28-Apr-25
|  | 737 | ROJ51 | #747474 | 03-Apr-25 | 03-Apr-25
|  | 739 | ROJ53 | #747474 | 30-Mar-25 | 03-Apr-25
|  | 744 | ROJ58 | #747474 | 04-Apr-25 | 04-Apr-25
|  | 747 | ROJ61 | #747474 | 30-Mar-25 | 04-Apr-25
|  | 749 | ROJ63 | #747474 | 04-Apr-25 | 04-Apr-25
|  | 751 | ROJ65 | #747474 | 30-Mar-25 | 04-Apr-25
|  | 756 | ROJ70 | #747474 | 03-May-25 | 03-May-25
|  | 757 | ROJ71 | #747474 | 29-Apr-25 | 03-May-25
|  | 762 | ROJ76 | #747474 | 15-May-25 | 15-May-25
|  | 763 | ROJ77 | #747474 | 11-May-25 | 15-May-25
|  | 767 | ROJ81 | #747474 | 03-May-25 | 03-May-25
|  | 769 | ROJ83 | #747474 | 29-Apr-25 | 03-May-25
|  | 773 | ROJ87 | #747474 | 07-May-25 | 07-May-25
|  | 775 | ROJ89 | #747474 | 03-May-25 | 07-May-25
|  | 779 | ROJ93 | #747474 | 16-Sep-24 | 16-Sep-24
|  | 780 | ROJ94 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 783 | ROJ97 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 784 | ROJ98 | #747474 | 28-Jan-25 | 28-Jan-25
|  | 788 | ROJ102 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 791 | ROJ105 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 794 | ROJ108 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 796 | ROJ110 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 799 | ROJ113 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 802 | ROJ116 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 805 | ROJ119 | #747474 | 30-Oct-24 | 30-Oct-24
|  | 808 | ROJ122 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 810 | ROJ124 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 813 | ROJ127 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 815 | ROJ129 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 818 | ROJ132 | #747474 | 05-Sep-24 | 05-Sep-24
|  | 823 | ROJ137 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 825 | ROJ139 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 830 | ROJ144 | #747474 | 03-May-25 | 03-May-25
|  | 833 | ROJ147 | #747474 | 29-Apr-25 | 03-May-25
RFP / PSR | Milestone | 1151 | ML21 | #000000 | 06-May-24 | 10-May-24
|  | 1152 | ML21 | #000000 | 15-Apr-24 | 02-May-24
|  | 1153 | ML21 | #000000 | 06-Jun-24 | 06-Jun-24
|  | 1154 | ML21 | #000000 | 30-Sep-24 | 30-Sep-24
|  | 1155 | ML21 | #000000 | 25-Mar-24 | 12-Apr-24
Site Prep/ Mobilization | Milestone | 249 | ML21 | #000000 | 19-Aug-24 | 04-Sep-24
|  | 1208 | ML21 | #000000 | 25-Jul-24 | 08-Aug-24
|  | 1209 | ML21 | #000000 | 24-Jul-24 | 24-Jul-24
Site Utilities | Overall | 479 | J22 | #3598FE | 23-Sep-24 | 21-Oct-24
|  | 581 | J36 | #3598FE | 04-Oct-24 | 18-Nov-24
|  | 604 | J41 | #3598FE | 04-Nov-24 | 03-Dec-24
|  | 629 | J43 | #3598FE | 09-Nov-24 | 17-Dec-24
|  | 638 | E38 | #F2F09E | 15-Nov-24 | 26-Dec-24
|  | 1035 | MLPP | #000000 | 05-May-25 | 05-May-25
| Under Building Pad | 38 | EW1 | #7E350E | 07-Nov-24 | 08-Nov-24
|  | 630 | EE36 | #F2F09E | 30-Sep-24 | 30-Oct-24
|  | 631 | EE37 | #F2F09E | 18-Sep-24 | 04-Oct-24