## Sheet1
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish
Interiors | Commissioning | All | #C4BD97 | CX-1 | Commissioning All Systems | 2026-10-07 | 2027-03-03
Interiors | Testing | All | #C4BD97 | CX-2 | Testing All Systems | 2026-08-25 | 2026-11-17
Interiors | Weather Days | All | #C4BD97 | CX-3 | Weather Days (3 days per month) | 2026-09-25 | 2027-01-04
Structure/Foundations | Structural Foundations | All Structurals Subs | #595959 | STRUC-1 | Structural Foundations - Entire Site | 2025-07-18 | 2025-09-12
Interiors | Finishes - Zone 1 | Ceiling | #C5D9F1 | C-1 | Ceiling Trim Out - Zone 1 | 2026-06-22 | 2026-06-30
Interiors | Finishes - Zone 3 | Ceiling | #C5D9F1 | C-1 | Ceiling Trim Out - Zone 1 | 2026-07-21 | 2026-07-29
Interiors | Finishes - Zone 1 | Ceiling | #C5D9F1 | C-2 | Close Ceiling - Zone 1 | 2026-07-02 | 2026-07-07
Interiors | Finishes - Zone 3 | Ceiling | #C5D9F1 | C-2 | Close Ceilings - Zone 3 | 2026-07-31 | 2026-08-04
Interiors | Finishes - Zone 2 | Ceiling | #C5D9F1 | C-3 | Install ACT Ceilings - Zone 2 | 2026-06-29 | 2026-07-01
Interiors | Finishes - Zone 4 | Ceiling | #C5D9F1 | C-3 | Install ACT Ceilings - Zone 4 | 2026-07-28 | 2026-07-30
Interiors | Finishes - Zone 5 | Ceiling | #C5D9F1 | C-3 | Install ACT Ceilings - Zone 5 | 2026-08-11 | 2026-08-13
Interiors | Finishes - Zone 6 | Ceiling | #C5D9F1 | C-4 | Install Ceilings - Zone 6 | 2026-08-25 | 2026-08-27
Interiors | Finishes - Zone 2 | Ceiling | #C5D9F1 | C-5 | Install Hard Ceiling - Zone 2 | 2026-07-02 | 2026-07-28
Interiors | Finishes - Zone 4 | Ceiling | #C5D9F1 | C-5 | Install Hard Ceilings - Zone 4 | 2026-07-31 | 2026-08-25
Interiors | Finishes - Zone 5 | Ceiling | #C5D9F1 | C-6 | Install Hard Lid Ceilings - Zone 5 | 2026-08-14 | 2026-09-09
Interiors | Finishes - Zone 6 | Ceiling | #C5D9F1 | C-6 | Install Hard Lid Ceilings - Zone 6 | 2026-08-28 | 2026-09-23
Foundations | Slabs - Zone 1 | Concrete | #7F0060 | FOUN-1 | F/R/P Slab on Grade - Zone 1 | 2025-09-15 | 2025-10-03
Foundations | Slabs - Zone 2 | Concrete | #7F0060 | FOUN-1 | F/R/P Slab on Grade - Zone 2 | 2025-10-14 | 2025-11-03
Foundations | Slabs - Zone 3 | Concrete | #7F0060 | FOUN-1 | F/R/P Slab on Grade - Zone 3 | 2025-11-11 | 2025-11-24
Foundations | Slabs - Zone 4 | Concrete | #7F0060 | FOUN-1 | F/R/P Slab on Grade - Zone 4 | 2025-12-11 | 2025-12-29
Foundations | Slabs - Zone 5 | Concrete | #7F0060 | FOUN-1 | F/R/P Slab on Grade - Zone 5 | 2026-01-30 | 2026-02-19
Foundations | Slabs - Zone 6 | Concrete | #7F0060 | FOUN-1 | F/R/P Slab on Grade - Zone 6 | 2026-03-13 | 2026-04-02
Interiors | Finishes - Mechanical Room | Concrete | #262626 | CO-1 | Cure Concrete Pad Sally Port - Mechanical Yard | 2026-01-30 | 2026-03-12
Interiors | Finishes - Mechanical Room | Concrete | #262626 | CO-1 | Cure Concrete Pads - Mechanical Yard | 2025-12-18 | 2025-12-29
Interiors | Finishes - Mechanical Room | Concrete | #262626 | CO-2 | F/R/P Concrete Pad Sally Port - Mechanical Yard | 2025-12-18 | 2026-01-29
Interiors | Finishes - Mechanical Room | Concrete | #262626 | CO-2 | F/R/P Concrete Pads - Mechanical Yard | 2025-11-04 | 2025-12-17
Interiors | FF&E | Concrete | #262626 | CO-3 | FF&E | 2027-02-05 | 2027-04-08
Interiors | Finishes - Zone 1 | Drywall | #FFFF80 | F-1 | Frame Walls & Ceilings - Zone 1 | 2026-04-02 | 2026-04-16
Interiors | Finishes - Zone 2 | Drywall | #FFFF80 | F-1 | Frame Walls & Ceilings - Zone 2 | 2026-04-17 | 2026-04-30
Interiors | Finishes - Zone 3 | Drywall | #FFFF80 | F-1 | Frame Walls & Ceilings - Zone 3 | 2026-05-01 | 2026-05-14
Interiors | Finishes - Zone 4 | Drywall | #FFFF80 | F-1 | Frame Walls & Ceilings - Zone 4 | 2026-05-15 | 2026-05-29
Interiors | Finishes - Zone 5 | Drywall | #FFFF80 | F-1 | Frame Walls & Ceilings - Zone 5 | 2026-06-01 | 2026-06-12
Interiors | Finishes - Zone 6 | Drywall | #FFFF80 | F-1 | Frame Walls & Ceilings - Zone 6 | 2026-06-15 | 2026-06-26
Interiors | Finishes - Zone 1 | Drywall | #FFFF80 | F-2 | Tape & Float - Zone 1 | 2026-06-01 | 2026-06-12
Interiors | Finishes - Zone 2 | Drywall | #FFFF80 | F-2 | Tape & Float - Zone 2 | 2026-06-15 | 2026-06-26
Interiors | Finishes - Zone 3 | Drywall | #FFFF80 | F-2 | Tape & Float - Zone 3 | 2026-06-29 | 2026-07-13
Interiors | Finishes - Zone 4 | Drywall | #FFFF80 | F-2 | Tape & Float - Zone 4 | 2026-07-14 | 2026-07-27
Interiors | Finishes - Zone 5 | Drywall | #FFFF80 | F-2 | Tape & Float - Zone 5 | 2026-07-28 | 2026-08-10
Interiors | Finishes - Zone 6 | Drywall | #FFFF80 | F-2 | Tape & Float - Zone 6 | 2026-08-11 | 2026-08-24
Interiors | Finishes - Zone 1 | Drywall | #FFFF80 | F-3 | Two Side Walls - Zone 1 | 2026-05-20 | 2026-05-29
Interiors | Finishes - Zone 2 | Drywall | #FFFF80 | F-3 | Two Side Walls - Zone 2 | 2026-06-04 | 2026-06-12
Interiors | Finishes - Zone 3 | Drywall | #FFFF80 | F-3 | Two Side Walls - Zone 3 | 2026-06-18 | 2026-06-26
Interiors | Finishes - Zone 4 | Drywall | #FFFF80 | F-3 | Two Side Walls - Zone 4 | 2026-07-02 | 2026-07-13
Interiors | Finishes - Zone 5 | Drywall | #FFFF80 | F-3 | Two Side Walls - Zone 5 | 2026-07-17 | 2026-07-27
Interiors | Finishes - Zone 6 | Drywall | #FFFF80 | F-3 | Two Side Walls - Zone 6 | 2026-07-31 | 2026-08-10
Interiors | Rough-In - Mechanical Room | Electrical | #F79646 | E-1 | Install Electrical Switchgear - Zone 1 Mechanical Room | 2026-06-15 | 2026-07-06
Interiors | Finishes - Mechanical Room | Electrical | #F79646 | E-2 | Set Generator - Mechanical Yard | 2026-05-14 | 2026-05-15
Interiors | Testing | Electrical | #F79646 | E-3 | Test & Balance | 2026-04-10 | 2026-09-29
Exteriors | North Elevation | Exterior Sub | #31E69B | FINISH-1 | Exterior Finishes - North Elevation | 2025-12-17 | 2026-02-25
Exteriors | West Elevation | Exterior Sub | #31E69B | FINISH-1 | Exterior Finishes - West Elevation | 2025-12-17 | 2026-02-25
Exteriors | South Elevation | Exterior Sub | #31E69B | FINISH-1 | Exterior Finishes - South Elevation | 2026-01-15 | 2026-03-18
Exteriors | East Elevation | Exterior Sub | #31E69B | FINISH-1 | Exterior Finishes - East Elevation | 2025-11-17 | 2026-01-28
Interiors | Finishes - Zone 1 | Finishes | #8064A2 | FI-1 | Finishes - Zone 1 | 2026-07-08 | 2026-08-25
Interiors | Finishes - Zone 2 | Finishes | #8064A2 | FI-1 | Finishes - Zone 2 | 2026-07-29 | 2026-09-09
Interiors | Finishes - Zone 3 | Finishes | #8064A2 | FI-1 | Finishes - Zone 3 | 2026-08-05 | 2026-09-23
Interiors | Finishes - Zone 4 | Finishes | #8064A2 | FI-1 | Finishes - Zone 4 | 2026-08-26 | 2026-10-07
Interiors | Finishes - Zone 5 | Finishes | #8064A2 | FI-1 | Finishes - Zone 5 | 2026-09-10 | 2026-10-21
Interiors | Finishes - Zone 6 | Finishes | #8064A2 | FI-1 | Finishes - Zone 6 | 2026-09-24 | 2026-11-04
Interiors | Finishes - Zone 7A | Finishes | #8064A2 | FI-1 | Finishes In Courtyard - Zone 7A | 2026-08-12 | 2027-02-04
Interiors | Finishes - Zone 7B | Finishes | #8064A2 | FI-1 | Finishes In Courtyard - Zone 7B | 2026-02-20 | 2026-08-11
Interiors | Finishes - Zone 1 | Inspector | #C00000 | IN-1 | Ceiling Inspection - Zone 1 | 2026-07-01 | 2026-07-01
Interiors | Finishes - Zone 3 | Inspector | #C00000 | IN-1 | Ceiling Inspection - Zone 1 | 2026-07-30 | 2026-07-30
Interiors | Rough-In - Zone 1 | Inspector | #C00000 | IN-2 | In-wall MEP Inspections - Zone 1 | 2026-05-15 | 2026-05-15
Interiors | Rough-In - Zone 2 | Inspector | #C00000 | IN-2 | In-wall MEP Inspections - Zone 2 | 2026-06-01 | 2026-06-01
Interiors | Rough-In - Zone 3 | Inspector | #C00000 | IN-2 | In-wall MEP Inspections - Zone 3 | 2026-06-15 | 2026-06-15
Interiors | Rough-In - Zone 4 | Inspector | #C00000 | IN-2 | In-wall MEP Inspections - Zone 4 | 2026-06-29 | 2026-06-29
Interiors | Rough-In - Zone 5 | Inspector | #C00000 | IN-2 | In-wall MEP Inspections - Zone 5 | 2026-07-14 | 2026-07-14
Interiors | Rough-In - Zone 6 | Inspector | #C00000 | IN-2 | In-wall MEP Inspections - Zone 6 | 2026-07-28 | 2026-07-28
Interiors | Rough-In - Zone 1 | Inspector | #C00000 | IN-3 | OH MEPF Inspections - Zone 1 | 2026-05-15 | 2026-05-15
Interiors | Rough-In - Zone 2 | Inspector | #C00000 | IN-3 | OH MEPF Inspections - Zone 2 | 2026-06-01 | 2026-06-01
Interiors | Rough-In - Zone 3 | Inspector | #C00000 | IN-3 | OH MEPF Inspections - Zone 3 | 2026-06-15 | 2026-06-15
Interiors | Rough-In - Zone 4 | Inspector | #C00000 | IN-3 | OH MEPF Inspections - Zone 4 | 2026-06-29 | 2026-06-29
Interiors | Rough-In - Zone 5 | Inspector | #C00000 | IN-3 | OH MEPF Inspections - Zone 5 | 2026-07-14 | 2026-07-14
Interiors | Rough-In - Zone 6 | Inspector | #C00000 | IN-3 | OH MEPF Inspections - Zone 6 | 2026-07-28 | 2026-07-28
Interiors | Finishes - Kitchen | Kitchen | #C0504D | K-1 | Install Kitchen Equipment | 2026-06-01 | 2026-08-24
Milestones | General Milestone | McGough | #808080 | SC | Substantial Completion |  | 2027-04-08
Milestones | General Milestone | McGough | #808080 | GMP | GMP Issued | 2025-03-04 | 2025-03-07
Milestones | General Milestone | McGough | #D9D9D9 | MOB | Mobilization | 2025-04-03 | 2025-04-16
Design | Design Milestone | McGough | #D9D9D9 | DM-1 | DD 1 Safety & Risk Assessment | 2024-09-04 | 2024-09-05
Design | Design Milestone | McGough | #D9D9D9 | DM-2 | DD 2 | 2024-09-19 | 2024-09-19
Design | Design Milestone | McGough | #D9D9D9 | DM-3 | DD 3 | 2024-10-17 | 2024-10-17
Design | Design Milestone | McGough | #D9D9D9 | DM-4 | DD 4 | 2024-11-14 | 2024-11-14
Design | Design Milestone | McGough | #D9D9D9 | DM-5 | DD Package Submission Owner & Cost Estimator | 2024-12-11 | 2024-12-18
Design | Design Milestone | McGough | #D9D9D9 | DM-6 | Early Site Utility, Grading, Foundation Package | 2024-12-19 | 2025-04-02
Design | Design Milestone | McGough | #D9D9D9 | DM-7 | Start CD Package | 2024-12-19 | 2024-12-19
Design | Design Milestone | McGough | #D9D9D9 | DM-8 | DD Cost Estimate Due | 2024-12-20 | 2025-01-29
Design | Design Milestone | McGough | #D9D9D9 | DM-9 | DD Final Page Turn & Owner Sign-off | 2025-01-30 | 2025-01-30
Design | Design Milestone | McGough | #D9D9D9 | DM-10 | Cost Reconciliation | 2025-01-30 | 2025-02-12
Design | Design Milestone | McGough | #D9D9D9 | DM-11 | Owner Comments Due | 2025-01-30 | 2025-02-12
Design | Design Milestone | McGough | #D9D9D9 | DM-12 | Owner DD & GMP Signoff | 2025-02-13 | 2025-03-03
Design | Design Milestone | McGough | #D9D9D9 | DM-13 | Issue Complete CD Package | 2025-04-03 | 2025-06-02
Subcontractor Procurement | Pre-Qual | McGough | #DAEEF3 | PRE-1 | Pre-Qual Curtainwall Sub | 2024-09-04 | 2024-09-10
Subcontractor Procurement | Pre-Qual | McGough | #DAEEF3 | PRE-2 | Pre-Qual Store Fronts Sub | 2024-09-04 | 2024-09-10
Subcontractor Procurement | Pre-Qual | McGough | #DAEEF3 | PRE-3 | Pre-Qual Structural Steel Sub | 2024-09-04 | 2024-09-10
Subcontractor Procurement | Pre-Qual | McGough | #DAEEF3 | PRE-4 | Pre-Qual Security Glazing Sub | 2024-09-04 | 2024-09-10
Subcontractor Procurement | Pre-Qual | McGough | #DAEEF3 | PRE-5 | Pre-Qual Overhead Door Sub | 2024-09-04 | 2024-09-10
Subcontractor Procurement | Pre-Qual | McGough | #DAEEF3 | PRE-6 | Pre-Qual Mechanical Sub | 2024-09-04 | 2024-09-10
Subcontractor Procurement | Pre-Qual | McGough | #DAEEF3 | PRE-7 | Pre-Qual Electrical Sub | 2024-09-04 | 2024-09-10
Subcontractor Procurement | Pre-Qual | McGough | #DAEEF3 | PRE-8 | Pre-Qual Kitchen Equipment Sub | 2024-09-04 | 2024-09-10
Subcontractor Procurement | Pre-Qual | McGough | #DAEEF3 | PRE-9 | Pre-Qual Antiligature Door Hardware/Kingsway Kits Sub | 2024-09-04 | 2024-09-10
Subcontractor Procurement | Contracts | McGough | #FDE9D9 | CONT-1 | Issue Contract to Curtainwall Sub | 2025-03-10 | 2025-04-04
Subcontractor Procurement | Contracts | McGough | #FDE9D9 | CONT-2 | Issue Contract to Store Fronts Sub | 2025-03-10 | 2025-04-04
Subcontractor Procurement | Contracts | McGough | #FDE9D9 | CONT-3 | Issue Contract to Structural Steel Sub | 2025-03-10 | 2025-04-04
Subcontractor Procurement | Contracts | McGough | #FDE9D9 | CONT-4 | Issue Contract to Security Glazing Sub | 2025-03-10 | 2025-04-04
Subcontractor Procurement | Contracts | McGough | #FDE9D9 | CONT-5 | Issue Contract to Overhead Door Sub | 2025-03-10 | 2025-04-04
Subcontractor Procurement | Contracts | McGough | #FDE9D9 | CONT-6 | Issue Contract to Mechanical Sub | 2025-03-10 | 2025-04-04
Subcontractor Procurement | Contracts | McGough | #FDE9D9 | CONT-7 | Issue Contract to Electrical Sub | 2025-03-10 | 2025-04-04
Subcontractor Procurement | Contracts | McGough | #FDE9D9 | CONT-8 | Issue Contract to Kitchen Equipment Sub | 2025-03-10 | 2025-04-04
Subcontractor Procurement | Contracts | McGough | #FDE9D9 | CONT-9 | Issue Contract to Antiligature Door Hardware/Kingsway Kits Sub | 2025-03-10 | 2025-04-04
Material Procurement | Material | McGough | #002060 | PROCU-1 | Procure Transformer (by others) | 2024-09-04 | 2025-04-25
Material Procurement | Material | McGough | #002060 | PROCU-2 | Procure & Fabricate Generator | 2025-04-29 | 2026-05-13
Material Procurement | Material | McGough | #002060 | PROCU-3 | Procure & Fabricate Electrical Switchgear | 2025-04-29 | 2026-05-13
Material Procurement | Material | McGough | #002060 | PROCU-4 | Procure & Fabricate ATS | 2025-04-29 | 2026-05-13
Material Procurement | Material | McGough | #002060 | PROCU-5 | Procure & Fabricate AHU's | 2025-04-29 | 2026-02-17
Material Procurement | Material | McGough | #002060 | PROCU-6 | Procure & Fabricate Chillers | 2025-04-29 | 2026-02-17
Material Procurement | Material | McGough | #002060 | PROCU-7 | Procure & Fabricate Structural Steel | 2025-04-29 | 2025-07-23
Material Procurement | Material | McGough | #002060 | PROCU-8 | Procure & Fabricate Curtainwall | 2025-04-29 | 2025-09-18
Material Procurement | Material | McGough | #002060 | PROCU-9 | Procure & Fabricate Store Fronts | 2025-04-29 | 2025-09-18
Material Procurement | Material | McGough | #002060 | PROCU-10 | Procure & Fabricate Security Glazing | 2025-06-03 | 2025-09-24
Material Procurement | Material | McGough | #002060 | PROCU-11 | Procure & Fabricate Overhead Door (6) | 2025-06-03 | 2025-10-08
Material Procurement | Material | McGough | #002060 | PROCU-12 | Procure & Fabricate Boilers | 2025-07-28 | 2026-05-15
Material Procurement | Material | McGough | #002060 | PROCU-13 | Procure & Fabricate Antiligature Door Hardware/Kingsway Kits | 2026-01-28 | 2026-06-18
Material Procurement | Material | McGough | #002060 | PROCU-14 | Procure & Fabricate Kitchen Equipment | 2026-02-02 | 2026-04-27
Submittals | Shop Drawings | McGough | #215967 | SUBM-1 | Submit Curtainwall Shop Drawings | 2025-04-07 | 2025-04-21
Submittals | Shop Drawings | McGough | #215967 | SUBM-2 | Submit Store Front Shop Drawings | 2025-04-07 | 2025-04-21
Submittals | Shop Drawings | McGough | #215967 | SUBM-3 | Submit Security Glazing Shop Drawings | 2025-04-07 | 2025-04-21
Submittals | Shop Drawings | McGough | #215967 | SUBM-4 | Submit Steel Structure Shop Drawings | 2025-04-07 | 2025-04-21
Submittals | Shop Drawings | McGough | #215967 | SUBM-5 | Submit Overhead Door Shop Drawings | 2025-04-07 | 2025-04-21
Submittals | Shop Drawings | McGough | #215967 | SUBM-6 | Submit Chiller Shop Drawings | 2025-04-07 | 2025-04-21
Submittals | Shop Drawings | McGough | #215967 | SUBM-7 | Submit AHU Shop Drawings | 2025-04-07 | 2025-04-21
Submittals | Shop Drawings | McGough | #215967 | SUBM-8 | Submit Generator Shop Drawings | 2025-04-07 | 2025-04-21
Submittals | Shop Drawings | McGough | #215967 | SUBM-9 | Submit Kitchen Equipment Shop Drawings | 2025-04-07 | 2025-04-21
Submittals | Shop Drawings | McGough | #215967 | SUBM-10 | Submit Electrical Switchgear Shop Drawings | 2025-04-07 | 2025-04-21
Submittals | Product Data | McGough | #963634 | SUBM-11 | Submit ATS Shop Drawings | 2025-04-07 | 2025-04-21
Submittals | Product Data | McGough | #963634 | SUBM-12 | Submit Boilers Shop Drawings | 2025-04-07 | 2025-04-21
Submittals | Product Data | McGough | #963634 | SUBM-13 | Submit Antiligature Door Hardware/Kingsway Kits Shop Drawings | 2025-04-07 | 2025-04-21
Submittals | Product Data | McGough | #963634 | SUBM-14 | Owner Approve Curtainwall Shop Drawings | 2025-04-22 | 2025-04-28
Submittals | Product Data | McGough | #963634 | SUBM-15 | Owner Approve Store Front Shop Drawings | 2025-04-22 | 2025-04-28
Submittals | Product Data | McGough | #963634 | SUBM-16 | Owner Approve Security Glazing Shop Drawings | 2025-04-22 | 2025-04-28
Submittals | Product Data | McGough | #963634 | SUBM-17 | Owner Approve Steel Structure Shop Drawings | 2025-04-22 | 2025-04-28
Submittals | Product Data | McGough | #963634 | SUBM-18 | Owner Approve Overhead Door Shop Drawings | 2025-04-22 | 2025-04-28
Submittals | Product Data | McGough | #963634 | SUBM-19 | Owner Approve Chiller Shop Drawings | 2025-04-22 | 2025-04-28
Submittals | Product Data | McGough | #963634 | SUBM-20 | Owner Approve AHU Shop Drawings | 2025-04-22 | 2025-04-28
Submittals | Product Data | McGough | #963634 | SUBM-21 | Owner Approve Generator Shop Drawings | 2025-04-22 | 2025-04-28
Submittals | Product Data | McGough | #963634 | SUBM-22 | Owner Approve Kitchen Equipment Shop Drawings | 2025-04-22 | 2025-04-28
Submittals | Product Data | McGough | #963634 | SUBM-23 | Owner Approve Electrical Switchgear Shop Drawings | 2025-04-22 | 2025-04-28
Submittals | Product Data | McGough | #963634 | SUBM-24 | Owner Approve ATS Shop Drawings | 2025-04-22 | 2025-04-28
Submittals | Product Data | McGough | #963634 | SUBM-25 | Owner Approve Boilers Shop Drawings | 2025-04-22 | 2025-04-28
Submittals | Product Data | McGough | #963634 | SUBM-26 | Owner Approve Antiligature Door Hardware/Kingsway Kits Shop Drawings | 2025-04-22 | 2025-04-28
Permitting | Permits | McGough | #494529 | PERM-1 | Permitting - TXDot | 2025-01-15 | 2025-05-21
Interiors | Finishes - Mechanical Room | Mechanical | #4BACC6 | M-1 | Hook-up/Final Connections Chillers - Mechanical Yard | 2026-02-25 | 2026-03-17
Interiors | Finishes - Mechanical Room | Mechanical | #4BACC6 | M-2 | Hook-up/Final Connections Generator - Mechanical Yard | 2026-05-18 | 2026-05-22
Interiors | Finishes - Zone 1 | Mechanical | #4BACC6 | M-3 | In-wall Blocking - Zone 1 | 2026-05-18 | 2026-05-19
Interiors | Finishes - Zone 2 | Mechanical | #4BACC6 | M-3 | In-wall Blocking - Zone 2 | 2026-06-02 | 2026-06-03
Interiors | Finishes - Zone 3 | Mechanical | #4BACC6 | M-3 | In-wall Blocking - Zone 3 | 2026-06-16 | 2026-06-17
Interiors | Finishes - Zone 4 | Mechanical | #4BACC6 | M-3 | In-wall Blocking - Zone 4 | 2026-06-30 | 2026-07-01
Interiors | Finishes - Zone 5 | Mechanical | #4BACC6 | M-3 | In-wall Blocking - Zone 5 | 2026-07-15 | 2026-07-16
Interiors | Finishes - Zone 6 | Mechanical | #4BACC6 | M-3 | In-wall Blocking - Zone 6 | 2026-07-29 | 2026-07-30
Interiors | Finishes - Zone 1 | Mechanical | #4BACC6 | M-4 | Install ACT Grid - Zone 1 | 2026-06-15 | 2026-06-19
Interiors | Finishes - Zone 3 | Mechanical | #4BACC6 | M-4 | Install ACT Grid - Zone 1 | 2026-07-14 | 2026-07-20
Interiors | Rough-In - Zone 5 | Mechanical | #4BACC6 | M-5 | Install AHU 1 (Roof) - Zone 5 | 2026-05-04 | 2026-05-08
Interiors | Rough-In - Zone 6 | Mechanical | #4BACC6 | M-5 | Install AHU 2 (Roof) - Zone 6 | 2026-05-11 | 2026-05-15
Interiors | Rough-In - Zone 4 | Mechanical | #4BACC6 | M-5 | Install AHU 3 & 4 (Roof) - Zone 4 | 2026-04-24 | 2026-05-01
Interiors | Rough-In - Zone 3 | Mechanical | #4BACC6 | M-5 | Install AHU 5 (Roof) - Zone 3 | 2026-04-17 | 2026-04-23
Interiors | Rough-In - Zone 2 | Mechanical | #4BACC6 | M-5 | Install AHU 6 (Roof) - Zone 2 | 2026-04-10 | 2026-04-16
Interiors | Rough-In - Zone 1 | Mechanical | #4BACC6 | M-5 | Install AHU 7 (Roof) - Zone 1 | 2026-04-02 | 2026-04-09
Interiors | Rough-In - Mechanical Room | Mechanical | #4BACC6 | M-6 | Install ATS - Zone 1 Mechanical Room | 2026-06-15 | 2026-06-26
Interiors | Rough-In - Mechanical Room | Mechanical | #4BACC6 | M-7 | Install Boilers - Zone 1 Mechanical Room | 2026-06-15 | 2026-06-26
Interiors | Finishes - Mechanical Room | Mechanical | #4BACC6 | M-8 | Install CMU Walls - Mechanical Yard | 2026-03-19 | 2026-04-30
Interiors | Rough-In - Mechanical Room | Mechanical | #4BACC6 | M-9 | Install Housekeeping Pads - Zone 1 Mechanical Room | 2025-09-29 | 2025-10-03
Interiors | Finishes - Mechanical Room | Mechanical | #4BACC6 | M-10 | Set Chillers (3) - Mechanical Yard | 2026-02-18 | 2026-02-24
Interiors | Finishes - Mechanical Room | Mechanical | #4BACC6 | M-11 | Set Fuel Tank - Mechanical Yard | 2026-05-18 | 2026-05-22
Interiors | Rough-In - Mechanical Room | Mechanical | #4BACC6 | M-12 | Set/Install CHWP (3) - Zone 1 Mechanical Room | 2026-06-29 | 2026-07-20
Interiors | Rough-In - Mechanical Room | Mechanical | #4BACC6 | M-13 | Set/Install HWP (3) - Zone 1 Mechanical Room | 2026-06-29 | 2026-07-20
Interiors | Rough-In - Mechanical Room | Mechanical | #4BACC6 | M-14 | Set/Install VFD's - Zone 1 Mechanical Room | 2026-07-21 | 2026-08-17
Foundations | Underground Structures- Zone 1 | MEP | #7F0060 | FOUND-2 | Underground MEP - Zone 1 | 2025-07-21 | 2025-08-29
Foundations | Underground Structures- Mechanical Yard | MEP | #7F0060 | FOUND-2 | Underground MEP - Mechanical Yard | 2025-07-21 | 2025-10-13
Foundations | Underground Structures- Zone 2 | MEP | #7F0060 | FOUND-2 | Underground MEP - Zone 2 | 2025-09-02 | 2025-10-13
Foundations | Underground Structures- Zone 3 | MEP | #7F0060 | FOUND-2 | Underground MEP - Zone 3 | 2025-10-14 | 2025-11-10
Foundations | Underground Structures- Zone 4 | MEP | #7F0060 | FOUND-2 | Underground MEP - Zone 4 | 2025-11-11 | 2025-12-10
Foundations | Underground Structures- Zone 5 | MEP | #7F0060 | FOUND-2 | Underground MEP - Zone 5 | 2025-12-11 | 2026-01-29
Foundations | Underground Structures- Zone 6 | MEP | #7F0060 | FOUND-2 | Underground MEP - Zone 6 | 2026-01-30 | 2026-03-12
Foundations | Underground Structures- Zone 7A | MEP | #7F0060 | FOUND-2 | Underground MEP - Zone 7A | 2026-03-13 | 2026-04-02
Foundations | Underground Structures- Zone 7B | MEP | #7F0060 | FOUND-2 | Underground MEP - Zone 7B | 2026-04-06 | 2026-04-24
Interiors | Rough-In - Zone 1 | MEP | #4F6228 | MEP-1 | In-wall MEP Rough-in - Zone 1 | 2026-04-17 | 2026-05-14
Interiors | Rough-In - Zone 2 | MEP | #4F6228 | MEP-1 | In-wall MEP Rough-in - Zone 2 | 2026-05-01 | 2026-05-29
Interiors | Rough-In - Zone 3 | MEP | #4F6228 | MEP-1 | In-wall MEP Rough-in - Zone 3 | 2026-05-15 | 2026-06-12
Interiors | Rough-In - Zone 4 | MEP | #4F6228 | MEP-1 | In-wall MEP Rough-in - Zone 4 | 2026-06-01 | 2026-06-26
Interiors | Rough-In - Zone 5 | MEP | #4F6228 | MEP-1 | In-wall MEP Rough-in - Zone 5 | 2026-06-15 | 2026-07-13
Interiors | Rough-In - Zone 6 | MEP | #4F6228 | MEP-1 | In-wall MEP Rough-in - Zone 6 | 2026-06-29 | 2026-07-27
Interiors | Rough-In - Zone 1 | MEPF | #C4D79B | MEPF-1 | OH MEPF Rough-in - Zone 1 | 2026-04-17 | 2026-05-14
Interiors | Rough-In - Zone 2 | MEPF | #C4D79B | MEPF-1 | OH MEPF Rough-in - Zone 2 | 2026-05-01 | 2026-05-29
Interiors | Rough-In - Zone 3 | MEPF | #C4D79B | MEPF-1 | OH MEPF Rough-in - Zone 3 | 2026-05-15 | 2026-06-12
Interiors | Rough-In - Zone 4 | MEPF | #C4D79B | MEPF-1 | OH MEPF Rough-in - Zone 4 | 2026-06-01 | 2026-06-26
Interiors | Rough-In - Zone 5 | MEPF | #C4D79B | MEPF-1 | OH MEPF Rough-in - Zone 5 | 2026-06-15 | 2026-07-13
Interiors | Rough-In - Zone 6 | MEPF | #C4D79B | MEPF-1 | OH MEPF Rough-in - Zone 6 | 2026-06-29 | 2026-07-27
Interiors | Testing | Owner | #000000 | OW-1 | Owner Test & Balance | 2027-04-09 | 2027-07-02
Exteriors | Roofing | Roof Sub | #31E69B | FINISH-2 | Install Roofing | 2026-01-08 | 2026-04-01
Sitework | Clear & Grub | Site Sub | #682F13 | SITE-1 | Clear & Grub - Building Foot Print | 2025-04-17 | 2025-05-22
Sitework | Excavation | Site Sub | #682F13 | SITE-2 | Excavate - Entire Site | 2025-05-23 | 2025-07-28
Sitework | Site Utilities | Site Sub | #682F13 | SITE-3 | Install All Site Utilities | 2025-04-03 | 2025-07-18
Sitework | Site Paving | Site Sub | #682F13 | SITE-4 | Site Paving | 2025-05-23 | 2025-12-30
Sitework | Hardscape/Landscaping | Site Sub | #682F13 | SITE-5 | Hardscape/Landscaping | 2026-07-06 | 2026-12-23
Structure | Above Grade Structures- Zone 1 | Steel | #595959 | STRUC-2 | Steel Framing & Decking - Zone 1 | 2025-10-06 | 2025-10-17
Structure | Above Grade Structures- Zone 2 | Steel | #595959 | STRUC-2 | Steel Framing & Decking - Zone 2 | 2025-10-20 | 2025-10-31
Structure | Above Grade Structures- Zone 3 | Steel | #595959 | STRUC-2 | Steel Framing & Decking - Zone 3 | 2025-11-03 | 2025-11-14
Structure | Above Grade Structures- Zone 4 | Steel | #595959 | STRUC-2 | Steel Framing & Decking - Zone 4 | 2025-11-17 | 2025-12-02
Structure | Above Grade Structures- Zone 5 | Steel | #595959 | STRUC-2 | Steel Framing & Decking - Zone 5 | 2025-12-03 | 2025-12-16
Structure | Above Grade Structures- Zone 6 | Steel | #595959 | STRUC-2 | Steel Framing & Decking - Zone 6 | 2025-12-17 | 2026-01-07
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-1 | Demolition | 2024-09-04 | 2024-09-04
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-2 | Earthworks and Support of Excavation | 2024-09-04 | 2024-09-04
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-3 | Deep Foundations | 2024-09-04 | 2024-09-04
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-4 | Structural Foundations/Footings | 2024-09-04 | 2024-09-04
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-5 | Below Grade Structure | 2024-09-04 | 2024-09-04
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-6 | Above Grade Structure | 2024-09-04 | 2024-09-04
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-7 | Vertical Transportation | 2024-09-04 | 2024-09-04
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-8 | Rough-In | 2024-09-04 | 2024-09-04
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-9 | Finishes | 2024-09-04 | 2024-09-04
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-10 | Masonry | 2024-09-04 | 2024-09-04
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-11 | Hardscape and Landscaping | 2024-09-04 | 2024-09-04
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-12 | Subcontract Procurement | 2024-11-25 | 2025-05-23
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-13 | Site Utilities | 2025-04-03 | 2025-07-18
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-14 | Building Enclosure | 2025-11-17 | 2026-04-01
McGough Standards | Executive Summary | Exec | #7D0B19 | MCG-15 | Testing and Commissioning | 2026-08-25 | 2027-03-03
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-16 | Notice to Proceed | 2025-02-10
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-17 | Below Grade Structure Start | 2025-02-10
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-18 | Below Grade Structure Complete |  | 2025-02-10
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-19 | Vertical Transportation Start | 2025-02-10
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-20 | Temp Power |  | 2025-05-12
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-21 | Excavation Start | 2025-05-23
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-22 | Excavation Complete |  | 2025-07-28
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-23 | Above Grade Structure Start | 2025-10-20
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-24 | Building Temporarily Enclosed | 2025-10-27
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-25 | Above Grade Structure Complete |  | 2026-01-07
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-26 | Building Envelope Start | 2026-01-29
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-27 | Building Envelope Complete |  | 2026-04-09
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-28 | MEP Rough-In Start | 2026-05-15
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-29 | Permanent Power | 2026-05-26
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-30 | Start Drywall | 2026-06-01
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-31 | Courtyard Start | 2026-08-12
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-32 | Building Finishes Start | 2026-08-26
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-33 | Drywall Complete |  | 2026-09-23
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-34 | Courtyard Finish |  | 2027-02-04
McGough Standards | Key Milestones | McGough | #7D0B19 | MCG-35 | Final Acceptance |  | 2027-05-20
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-36 | Subcontractor Procurement Start | 2024-11-25
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-37 | Material Purchase Start | 2024-11-25
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-38 | Mobilization Key Activity | 2025-02-10
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-39 | Demolition Start | 2025-02-10
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-40 | Demolition Complete |  | 2025-02-10
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-41 | Deep Structural Foundations Start | 2025-02-10
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-42 | Deep Structural Foundations Complete |  | 2025-02-10
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-43 | Vertical Transportation Start | 2025-02-10
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-44 | Vertical Transportation Complete | 2025-02-10
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-45 | Site Survey Start | 2025-02-17
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-46 | Utilities Start | 2025-03-03
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-47 | Utilities Start | 2025-03-03
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-48 | Site Survey Finish |  | 2025-03-10
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-49 | Mobilization Start | 2025-04-03
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-50 | Mobilization Finish |  | 2025-04-16
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-51 | Utilities Complete |  | 2025-05-16
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-52 | Permitting Finish |  | 2025-05-21
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-53 | Permitting Start | 2025-05-22
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-54 | Excavation Start | 2025-05-23
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-55 | Subcontractor Procurement Finish |  | 2025-05-27
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-56 | Structural Foundations Start | 2025-07-18
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-57 | Underground Structures Start Rough In | 2025-07-21
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-58 | Excavation Complete |  | 2025-07-28
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-59 | Structural Foundations Complete |  | 2025-09-12
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-60 | Above Grade Structures Start | 2025-09-15
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-61 | Building Temporarily Enclosed |  | 2025-10-24
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-62 | Building Envelope Start | 2025-11-17
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-63 | Masonry Start | 2025-12-17
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-64 | Above Grade Structures Complete |  | 2026-01-07
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-65 | Material Purchase Finish |  | 2026-01-16
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-66 | Building Envelope Complete |  | 2026-04-01
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-67 | Masonry Complete |  | 2026-04-09
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-68 | Rough-In Start | 2026-04-17
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-69 | Underground Structures Complete Rough In |  | 2026-04-24
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-70 | Finishes Start | 2026-07-08
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-71 | Rough-In Complete |  | 2026-07-27
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-72 | Commissioning Start | 2026-10-07
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-73 | Finishes Complete |  | 2026-11-04
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-74 | Testing Complete |  | 2026-11-17
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-75 | Building Water Testing | 2026-11-18
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-76 | Testing Start | 2026-11-20
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-77 | Equipment Startup | 2026-11-20
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-78 | Sitework(Land/Hardscape) Start | 2026-11-30
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-79 | Sitework(Land/Hardscape) Complete |  | 2026-12-18
McGough Standards | McGough Tracking | Tracking | #7D0B19 | MCG-80 | Commissioning Complete |  | 2027-03-03

## CFA - Schedule
|  | 2024 | [118 empty] | 2025 | [364 empty] | 2026 | [364 empty] | 2027
|  | Sep | [26 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul
|  | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02
phase | location | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Subcontractor Procurement | Contracts | Mar 10: CONT-1; Mar 11: CONT-1; Mar 12: CONT-1; Mar 13: CONT-1; Mar 14: CONT-1; Mar 15: CONT-1; Mar 16: CONT-1; Mar 17: CONT-1; Mar 18: CONT-1; Mar 19: CONT-1; Mar 20: CONT-1; Mar 21: CONT-1; Mar 22: CONT-1; Mar 23: CONT-1; Mar 24: CONT-1; Mar 25: CONT-1; Mar 26: CONT-1; Mar 27: CONT-1; Mar 28: CONT-1; Mar 29: CONT-1; Mar 30: CONT-1; Mar 31: CONT-1; Apr 01: CONT-1; Apr 02: CONT-1; Apr 03: CONT-1; Apr 04: CONT-1
[189 empty] | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2 | CONT-2
[189 empty] | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3 | CONT-3
[189 empty] | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4 | CONT-4
[189 empty] | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5 | CONT-5
[189 empty] | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6 | CONT-6
[189 empty] | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7 | CONT-7
[189 empty] | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8 | CONT-8
[189 empty] | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9 | CONT-9
| Pre-Qual | Sep 04: PRE-1; Sep 05: PRE-1; Sep 06: PRE-1; Sep 07: PRE-1; Sep 08: PRE-1; Sep 09: PRE-1; Sep 10: PRE-1
|  | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2
|  | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3
|  | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4
|  | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5
|  | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6
|  | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7
|  | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8
|  | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9
Material Procurement | Material | Sep 04: PROCU-1; Sep 05: PROCU-1; Sep 06: PROCU-1; Sep 07: PROCU-1; Sep 08: PROCU-1; Sep 09: PROCU-1; Sep 10: PROCU-1; Sep 11: PROCU-1; Sep 12: PROCU-1; Sep 13: PROCU-1; Sep 14: PROCU-1; Sep 15: PROCU-1; Sep 16: PROCU-1; Sep 17: PROCU-1; Sep 18: PROCU-1; Sep 19: PROCU-1; Sep 20: PROCU-1; Sep 21: PROCU-1; Sep 22: PROCU-1; Sep 23: PROCU-1; Sep 24: PROCU-1; Sep 25: PROCU-1; Sep 26: PROCU-1; Sep 27: PROCU-1; Sep 28: PROCU-1; Sep 29: PROCU-1; Sep 30: PROCU-1; Oct 01: PROCU-1; Oct 02: PROCU-1; Oct 03: PROCU-1; Oct 04: PROCU-1; Oct 05: PROCU-1; Oct 06: PROCU-1; Oct 07: PROCU-1; Oct 08: PROCU-1; Oct 09: PROCU-1; Oct 10: PROCU-1; Oct 11: PROCU-1; Oct 12: PROCU-1; Oct 13: PROCU-1; Oct 14: PROCU-1; Oct 15: PROCU-1; Oct 16: PROCU-1; Oct 17: PROCU-1; Oct 18: PROCU-1; Oct 19: PROCU-1; Oct 20: PROCU-1; Oct 21: PROCU-1; Oct 22: PROCU-1; Oct 23: PROCU-1; Oct 24: PROCU-1; Oct 25: PROCU-1; Oct 26: PROCU-1; Oct 27: PROCU-1; Oct 28: PROCU-1; Oct 29: PROCU-1; Oct 30: PROCU-1; Oct 31: PROCU-1; Nov 01: PROCU-1; Nov 02: PROCU-1; Nov 03: PROCU-1; Nov 04: PROCU-1; Nov 05: PROCU-1; Nov 06: PROCU-1; Nov 07: PROCU-1; Nov 08: PROCU-1; Nov 09: PROCU-1; Nov 10: PROCU-1; Nov 11: PROCU-1; Nov 12: PROCU-1; Nov 13: PROCU-1; Nov 14: PROCU-1; Nov 15: PROCU-1; Nov 16: PROCU-1; Nov 17: PROCU-1; Nov 18: PROCU-1; Nov 19: PROCU-1; Nov 20: PROCU-1; Nov 21: PROCU-1; Nov 22: PROCU-1; Nov 23: PROCU-1; Nov 24: PROCU-1; Nov 25: PROCU-1; Nov 26: PROCU-1; Nov 27: PROCU-1; Nov 28: PROCU-1; Nov 29: PROCU-1; Nov 30: PROCU-1; Dec 01: PROCU-1; Dec 02: PROCU-1; Dec 03: PROCU-1; Dec 04: PROCU-1; Dec 05: PROCU-1; Dec 06: PROCU-1; Dec 07: PROCU-1; Dec 08: PROCU-1; Dec 09: PROCU-1; Dec 10: PROCU-1; Dec 11: PROCU-1; Dec 12: PROCU-1; Dec 13: PROCU-1; Dec 14: PROCU-1; Dec 15: PROCU-1; Dec 16: PROCU-1; Dec 17: PROCU-1; Dec 18: PROCU-1; Dec 19: PROCU-1; Dec 20: PROCU-1; Dec 21: PROCU-1; Dec 22: PROCU-1; Dec 23: PROCU-1; Dec 24: PROCU-1; Dec 25: PROCU-1; Dec 26: PROCU-1; Dec 27: PROCU-1; Dec 28: PROCU-1; Dec 29: PROCU-1; Dec 30: PROCU-1; Dec 31: PROCU-1; Jan 01: PROCU-1; Jan 02: PROCU-1; Jan 03: PROCU-1; Jan 04: PROCU-1; Jan 05: PROCU-1; Jan 06: PROCU-1; Jan 07: PROCU-1; Jan 08: PROCU-1; Jan 09: PROCU-1; Jan 10: PROCU-1; Jan 11: PROCU-1; Jan 12: PROCU-1; Jan 13: PROCU-1; Jan 14: PROCU-1; Jan 15: PROCU-1; Jan 16: PROCU-1; Jan 17: PROCU-1; Jan 18: PROCU-1; Jan 19: PROCU-1; Jan 20: PROCU-1; Jan 21: PROCU-1; Jan 22: PROCU-1; Jan 23: PROCU-1; Jan 24: PROCU-1; Jan 25: PROCU-1; Jan 26: PROCU-1; Jan 27: PROCU-1; Jan 28: PROCU-1; Jan 29: PROCU-1; Jan 30: PROCU-1; Jan 31: PROCU-1; Feb 01: PROCU-1; Feb 02: PROCU-1; Feb 03: PROCU-1; Feb 04: PROCU-1; Feb 05: PROCU-1; Feb 06: PROCU-1; Feb 07: PROCU-1; Feb 08: PROCU-1; Feb 09: PROCU-1; Feb 10: PROCU-1; Feb 11: PROCU-1; Feb 12: PROCU-1; Feb 13: PROCU-1; Feb 14: PROCU-1; Feb 15: PROCU-1; Feb 16: PROCU-1; Feb 17: PROCU-1; Feb 18: PROCU-1; Feb 19: PROCU-1; Feb 20: PROCU-1; Feb 21: PROCU-1; Feb 22: PROCU-1; Feb 23: PROCU-1; Feb 24: PROCU-1; Feb 25: PROCU-1; Feb 26: PROCU-1; Feb 27: PROCU-1; Feb 28: PROCU-1; Mar 01: PROCU-1; Mar 02: PROCU-1; Mar 03: PROCU-1; Mar 04: PROCU-1; Mar 05: PROCU-1; Mar 06: PROCU-1; Mar 07: PROCU-1; Mar 08: PROCU-1; Mar 09: PROCU-1; Mar 10: PROCU-1; Mar 11: PROCU-1; Mar 12: PROCU-1; Mar 13: PROCU-1; Mar 14: PROCU-1; Mar 15: PROCU-1; Mar 16: PROCU-1; Mar 17: PROCU-1; Mar 18: PROCU-1; Mar 19: PROCU-1; Mar 20: PROCU-1; Mar 21: PROCU-1; Mar 22: PROCU-1; Mar 23: PROCU-1; Mar 24: PROCU-1; Mar 25: PROCU-1; Mar 26: PROCU-1; Mar 27: PROCU-1; Mar 28: PROCU-1; Mar 29: PROCU-1; Mar 30: PROCU-1; Mar 31: PROCU-1; Apr 01: PROCU-1; Apr 02: PROCU-1; Apr 03: PROCU-1; Apr 04: PROCU-1; Apr 05: PROCU-1; Apr 06: PROCU-1; Apr 07: PROCU-1; Apr 08: PROCU-1; Apr 09: PROCU-1; Apr 10: PROCU-1; Apr 11: PROCU-1; Apr 12: PROCU-1; Apr 13: PROCU-1; Apr 14: PROCU-1; Apr 15: PROCU-1; Apr 16: PROCU-1; Apr 17: PROCU-1; Apr 18: PROCU-1; Apr 19: PROCU-1; Apr 20: PROCU-1; Apr 21: PROCU-1; Apr 22: PROCU-1; Apr 23: PROCU-1; Apr 24: PROCU-1; Apr 25: PROCU-1; Apr 29: PROCU-7; Apr 30: PROCU-7; May 01: PROCU-7; May 02: PROCU-7; May 03: PROCU-7; May 04: PROCU-7; May 05: PROCU-7; May 06: PROCU-7; May 07: PROCU-7; May 08: PROCU-7; May 09: PROCU-7; May 10: PROCU-7; May 11: PROCU-7; May 12: PROCU-7; May 13: PROCU-7; May 14: PROCU-7; May 15: PROCU-7; May 16: PROCU-7; May 17: PROCU-7; May 18: PROCU-7; May 19: PROCU-7; May 20: PROCU-7; May 21: PROCU-7; May 22: PROCU-7; May 23: PROCU-7; May 24: PROCU-7; May 25: PROCU-7; May 26: PROCU-7; May 27: PROCU-7; May 28: PROCU-7; May 29: PROCU-7; May 30: PROCU-7; May 31: PROCU-7; Jun 01: PROCU-7; Jun 02: PROCU-7; Jun 03: PROCU-7; Jun 04: PROCU-7; Jun 05: PROCU-7; Jun 06: PROCU-7; Jun 07: PROCU-7; Jun 08: PROCU-7; Jun 09: PROCU-7; Jun 10: PROCU-7; Jun 11: PROCU-7; Jun 12: PROCU-7; Jun 13: PROCU-7; Jun 14: PROCU-7; Jun 15: PROCU-7; Jun 16: PROCU-7; Jun 17: PROCU-7; Jun 18: PROCU-7; Jun 19: PROCU-7; Jun 20: PROCU-7; Jun 21: PROCU-7; Jun 22: PROCU-7; Jun 23: PROCU-7; Jun 24: PROCU-7; Jun 25: PROCU-7; Jun 26: PROCU-7; Jun 27: PROCU-7; Jun 28: PROCU-7; Jun 29: PROCU-7; Jun 30: PROCU-7; Jul 01: PROCU-7; Jul 02: PROCU-7; Jul 03: PROCU-7; Jul 04: PROCU-7; Jul 05: PROCU-7; Jul 06: PROCU-7; Jul 07: PROCU-7; Jul 08: PROCU-7; Jul 09: PROCU-7; Jul 10: PROCU-7; Jul 11: PROCU-7; Jul 12: PROCU-7; Jul 13: PROCU-7; Jul 14: PROCU-7; Jul 15: PROCU-7; Jul 16: PROCU-7; Jul 17: PROCU-7; Jul 18: PROCU-7; Jul 19: PROCU-7; Jul 20: PROCU-7; Jul 21: PROCU-7; Jul 22: PROCU-7; Jul 23: PROCU-7; Jul 28: PROCU-12; Jul 29: PROCU-12; Jul 30: PROCU-12; Jul 31: PROCU-12; Aug 01: PROCU-12; Aug 02: PROCU-12; Aug 03: PROCU-12; Aug 04: PROCU-12; Aug 05: PROCU-12; Aug 06: PROCU-12; Aug 07: PROCU-12; Aug 08: PROCU-12; Aug 09: PROCU-12; Aug 10: PROCU-12; Aug 11: PROCU-12; Aug 12: PROCU-12; Aug 13: PROCU-12; Aug 14: PROCU-12; Aug 15: PROCU-12; Aug 16: PROCU-12; Aug 17: PROCU-12; Aug 18: PROCU-12; Aug 19: PROCU-12; Aug 20: PROCU-12; Aug 21: PROCU-12; Aug 22: PROCU-12; Aug 23: PROCU-12; Aug 24: PROCU-12; Aug 25: PROCU-12; Aug 26: PROCU-12; Aug 27: PROCU-12; Aug 28: PROCU-12; Aug 29: PROCU-12; Aug 30: PROCU-12; Aug 31: PROCU-12; Sep 01: PROCU-12; Sep 02: PROCU-12; Sep 03: PROCU-12; Sep 04: PROCU-12; Sep 05: PROCU-12; Sep 06: PROCU-12; Sep 07: PROCU-12; Sep 08: PROCU-12; Sep 09: PROCU-12; Sep 10: PROCU-12; Sep 11: PROCU-12; Sep 12: PROCU-12; Sep 13: PROCU-12; Sep 14: PROCU-12; Sep 15: PROCU-12; Sep 16: PROCU-12; Sep 17: PROCU-12; Sep 18: PROCU-12; Sep 19: PROCU-12; Sep 20: PROCU-12; Sep 21: PROCU-12; Sep 22: PROCU-12; Sep 23: PROCU-12; Sep 24: PROCU-12; Sep 25: PROCU-12; Sep 26: PROCU-12; Sep 27: PROCU-12; Sep 28: PROCU-12; Sep 29: PROCU-12; Sep 30: PROCU-12; Oct 01: PROCU-12; Oct 02: PROCU-12; Oct 03: PROCU-12; Oct 04: PROCU-12; Oct 05: PROCU-12; Oct 06: PROCU-12; Oct 07: PROCU-12; Oct 08: PROCU-12; Oct 09: PROCU-12; Oct 10: PROCU-12; Oct 11: PROCU-12; Oct 12: PROCU-12; Oct 13: PROCU-12; Oct 14: PROCU-12; Oct 15: PROCU-12; Oct 16: PROCU-12; Oct 17: PROCU-12; Oct 18: PROCU-12; Oct 19: PROCU-12; Oct 20: PROCU-12; Oct 21: PROCU-12; Oct 22: PROCU-12; Oct 23: PROCU-12; Oct 24: PROCU-12; Oct 25: PROCU-12; Oct 26: PROCU-12; Oct 27: PROCU-12; Oct 28: PROCU-12; Oct 29: PROCU-12; Oct 30: PROCU-12; Oct 31: PROCU-12; Nov 01: PROCU-12; Nov 02: PROCU-12; Nov 03: PROCU-12; Nov 04: PROCU-12; Nov 05: PROCU-12; Nov 06: PROCU-12; Nov 07: PROCU-12; Nov 08: PROCU-12; Nov 09: PROCU-12; Nov 10: PROCU-12; Nov 11: PROCU-12; Nov 12: PROCU-12; Nov 13: PROCU-12; Nov 14: PROCU-12; Nov 15: PROCU-12; Nov 16: PROCU-12; Nov 17: PROCU-12; Nov 18: PROCU-12; Nov 19: PROCU-12; Nov 20: PROCU-12; Nov 21: PROCU-12; Nov 22: PROCU-12; Nov 23: PROCU-12; Nov 24: PROCU-12; Nov 25: PROCU-12; Nov 26: PROCU-12; Nov 27: PROCU-12; Nov 28: PROCU-12; Nov 29: PROCU-12; Nov 30: PROCU-12; Dec 01: PROCU-12; Dec 02: PROCU-12; Dec 03: PROCU-12; Dec 04: PROCU-12; Dec 05: PROCU-12; Dec 06: PROCU-12; Dec 07: PROCU-12; Dec 08: PROCU-12; Dec 09: PROCU-12; Dec 10: PROCU-12; Dec 11: PROCU-12; Dec 12: PROCU-12; Dec 13: PROCU-12; Dec 14: PROCU-12; Dec 15: PROCU-12; Dec 16: PROCU-12; Dec 17: PROCU-12; Dec 18: PROCU-12; Dec 19: PROCU-12; Dec 20: PROCU-12; Dec 21: PROCU-12; Dec 22: PROCU-12; Dec 23: PROCU-12; Dec 24: PROCU-12; Dec 25: PROCU-12; Dec 26: PROCU-12; Dec 27: PROCU-12; Dec 28: PROCU-12; Dec 29: PROCU-12; Dec 30: PROCU-12; Dec 31: PROCU-12; Jan 01: PROCU-12; Jan 02: PROCU-12; Jan 03: PROCU-12; Jan 04: PROCU-12; Jan 05: PROCU-12; Jan 06: PROCU-12; Jan 07: PROCU-12; Jan 08: PROCU-12; Jan 09: PROCU-12; Jan 10: PROCU-12; Jan 11: PROCU-12; Jan 12: PROCU-12; Jan 13: PROCU-12; Jan 14: PROCU-12; Jan 15: PROCU-12; Jan 16: PROCU-12; Jan 17: PROCU-12; Jan 18: PROCU-12; Jan 19: PROCU-12; Jan 20: PROCU-12; Jan 21: PROCU-12; Jan 22: PROCU-12; Jan 23: PROCU-12; Jan 24: PROCU-12; Jan 25: PROCU-12; Jan 26: PROCU-12; Jan 27: PROCU-12; Jan 28: PROCU-12; Jan 29: PROCU-12; Jan 30: PROCU-12; Jan 31: PROCU-12; Feb 01: PROCU-12; Feb 02: PROCU-12; Feb 03: PROCU-12; Feb 04: PROCU-12; Feb 05: PROCU-12; Feb 06: PROCU-12; Feb 07: PROCU-12; Feb 08: PROCU-12; Feb 09: PROCU-12; Feb 10: PROCU-12; Feb 11: PROCU-12; Feb 12: PROCU-12; Feb 13: PROCU-12; Feb 14: PROCU-12; Feb 15: PROCU-12; Feb 16: PROCU-12; Feb 17: PROCU-12; Feb 18: PROCU-12; Feb 19: PROCU-12; Feb 20: PROCU-12; Feb 21: PROCU-12; Feb 22: PROCU-12; Feb 23: PROCU-12; Feb 24: PROCU-12; Feb 25: PROCU-12; Feb 26: PROCU-12; Feb 27: PROCU-12; Feb 28: PROCU-12; Mar 01: PROCU-12; Mar 02: PROCU-12; Mar 03: PROCU-12; Mar 04: PROCU-12; Mar 05: PROCU-12; Mar 06: PROCU-12; Mar 07: PROCU-12; Mar 08: PROCU-12; Mar 09: PROCU-12; Mar 10: PROCU-12; Mar 11: PROCU-12; Mar 12: PROCU-12; Mar 13: PROCU-12; Mar 14: PROCU-12; Mar 15: PROCU-12; Mar 16: PROCU-12; Mar 17: PROCU-12; Mar 18: PROCU-12; Mar 19: PROCU-12; Mar 20: PROCU-12; Mar 21: PROCU-12; Mar 22: PROCU-12; Mar 23: PROCU-12; Mar 24: PROCU-12; Mar 25: PROCU-12; Mar 26: PROCU-12; Mar 27: PROCU-12; Mar 28: PROCU-12; Mar 29: PROCU-12; Mar 30: PROCU-12; Mar 31: PROCU-12; Apr 01: PROCU-12; Apr 02: PROCU-12; Apr 03: PROCU-12; Apr 04: PROCU-12; Apr 05: PROCU-12; Apr 06: PROCU-12; Apr 07: PROCU-12; Apr 08: PROCU-12; Apr 09: PROCU-12; Apr 10: PROCU-12; Apr 11: PROCU-12; Apr 12: PROCU-12; Apr 13: PROCU-12; Apr 14: PROCU-12; Apr 15: PROCU-12; Apr 16: PROCU-12; Apr 17: PROCU-12; Apr 18: PROCU-12; Apr 19: PROCU-12; Apr 20: PROCU-12; Apr 21: PROCU-12; Apr 22: PROCU-12; Apr 23: PROCU-12; Apr 24: PROCU-12; Apr 25: PROCU-12; Apr 26: PROCU-12; Apr 27: PROCU-12; Apr 28: PROCU-12; Apr 29: PROCU-12; Apr 30: PROCU-12; May 01: PROCU-12; May 02: PROCU-12; May 03: PROCU-12; May 04: PROCU-12; May 05: PROCU-12; May 06: PROCU-12; May 07: PROCU-12; May 08: PROCU-12; May 09: PROCU-12; May 10: PROCU-12; May 11: PROCU-12; May 12: PROCU-12; May 13: PROCU-12; May 14: PROCU-12; May 15: PROCU-12
[239 empty] | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | PROCU-8 | [131 empty] | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13 | PROCU-13
[239 empty] | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | PROCU-9 | [136 empty] | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14 | PROCU-14
[239 empty] | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5 | PROCU-5
[239 empty] | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6 | PROCU-6
[239 empty] | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2 | PROCU-2
[239 empty] | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3 | PROCU-3
[239 empty] | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4 | PROCU-4
[274 empty] | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10 | PROCU-10
[274 empty] | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11 | PROCU-11
Milestones | General Milestone | Mar 04: GMP; Mar 05: GMP; Mar 06: GMP; Mar 07: GMP; Apr 03: MOB; Apr 04: MOB; Apr 05: MOB; Apr 06: MOB; Apr 07: MOB; Apr 08: MOB; Apr 09: MOB; Apr 10: MOB; Apr 11: MOB; Apr 12: MOB; Apr 13: MOB; Apr 14: MOB; Apr 15: MOB; Apr 16: MOB; Apr 08: SC
McGough Standards | Executive Summary | Sep 04: MCG-1; Nov 25: MCG-12; Nov 26: MCG-12; Nov 27: MCG-12; Nov 28: MCG-12; Nov 29: MCG-12; Nov 30: MCG-12; Dec 01: MCG-12; Dec 02: MCG-12; Dec 03: MCG-12; Dec 04: MCG-12; Dec 05: MCG-12; Dec 06: MCG-12; Dec 07: MCG-12; Dec 08: MCG-12; Dec 09: MCG-12; Dec 10: MCG-12; Dec 11: MCG-12; Dec 12: MCG-12; Dec 13: MCG-12; Dec 14: MCG-12; Dec 15: MCG-12; Dec 16: MCG-12; Dec 17: MCG-12; Dec 18: MCG-12; Dec 19: MCG-12; Dec 20: MCG-12; Dec 21: MCG-12; Dec 22: MCG-12; Dec 23: MCG-12; Dec 24: MCG-12; Dec 25: MCG-12; Dec 26: MCG-12; Dec 27: MCG-12; Dec 28: MCG-12; Dec 29: MCG-12; Dec 30: MCG-12; Dec 31: MCG-12; Jan 01: MCG-12; Jan 02: MCG-12; Jan 03: MCG-12; Jan 04: MCG-12; Jan 05: MCG-12; Jan 06: MCG-12; Jan 07: MCG-12; Jan 08: MCG-12; Jan 09: MCG-12; Jan 10: MCG-12; Jan 11: MCG-12; Jan 12: MCG-12; Jan 13: MCG-12; Jan 14: MCG-12; Jan 15: MCG-12; Jan 16: MCG-12; Jan 17: MCG-12; Jan 18: MCG-12; Jan 19: MCG-12; Jan 20: MCG-12; Jan 21: MCG-12; Jan 22: MCG-12; Jan 23: MCG-12; Jan 24: MCG-12; Jan 25: MCG-12; Jan 26: MCG-12; Jan 27: MCG-12; Jan 28: MCG-12; Jan 29: MCG-12; Jan 30: MCG-12; Jan 31: MCG-12; Feb 01: MCG-12; Feb 02: MCG-12; Feb 03: MCG-12; Feb 04: MCG-12; Feb 05: MCG-12; Feb 06: MCG-12; Feb 07: MCG-12; Feb 08: MCG-12; Feb 09: MCG-12; Feb 10: MCG-12; Feb 11: MCG-12; Feb 12: MCG-12; Feb 13: MCG-12; Feb 14: MCG-12; Feb 15: MCG-12; Feb 16: MCG-12; Feb 17: MCG-12; Feb 18: MCG-12; Feb 19: MCG-12; Feb 20: MCG-12; Feb 21: MCG-12; Feb 22: MCG-12; Feb 23: MCG-12; Feb 24: MCG-12; Feb 25: MCG-12; Feb 26: MCG-12; Feb 27: MCG-12; Feb 28: MCG-12; Mar 01: MCG-12; Mar 02: MCG-12; Mar 03: MCG-12; Mar 04: MCG-12; Mar 05: MCG-12; Mar 06: MCG-12; Mar 07: MCG-12; Mar 08: MCG-12; Mar 09: MCG-12; Mar 10: MCG-12; Mar 11: MCG-12; Mar 12: MCG-12; Mar 13: MCG-12; Mar 14: MCG-12; Mar 15: MCG-12; Mar 16: MCG-12; Mar 17: MCG-12; Mar 18: MCG-12; Mar 19: MCG-12; Mar 20: MCG-12; Mar 21: MCG-12; Mar 22: MCG-12; Mar 23: MCG-12; Mar 24: MCG-12; Mar 25: MCG-12; Mar 26: MCG-12; Mar 27: MCG-12; Mar 28: MCG-12; Mar 29: MCG-12; Mar 30: MCG-12; Mar 31: MCG-12; Apr 01: MCG-12; Apr 02: MCG-12; Apr 03: MCG-12; Apr 04: MCG-12; Apr 05: MCG-12; Apr 06: MCG-12; Apr 07: MCG-12; Apr 08: MCG-12; Apr 09: MCG-12; Apr 10: MCG-12; Apr 11: MCG-12; Apr 12: MCG-12; Apr 13: MCG-12; Apr 14: MCG-12; Apr 15: MCG-12; Apr 16: MCG-12; Apr 17: MCG-12; Apr 18: MCG-12; Apr 19: MCG-12; Apr 20: MCG-12; Apr 21: MCG-12; Apr 22: MCG-12; Apr 23: MCG-12; Apr 24: MCG-12; Apr 25: MCG-12; Apr 26: MCG-12; Apr 27: MCG-12; Apr 28: MCG-12; Apr 29: MCG-12; Apr 30: MCG-12; May 01: MCG-12; May 02: MCG-12; May 03: MCG-12; May 04: MCG-12; May 05: MCG-12; May 06: MCG-12; May 07: MCG-12; May 08: MCG-12; May 09: MCG-12; May 10: MCG-12; May 11: MCG-12; May 12: MCG-12; May 13: MCG-12; May 14: MCG-12; May 15: MCG-12; May 16: MCG-12; May 17: MCG-12; May 18: MCG-12; May 19: MCG-12; May 20: MCG-12; May 21: MCG-12; May 22: MCG-12; May 23: MCG-12; Nov 17: MCG-14; Nov 18: MCG-14; Nov 19: MCG-14; Nov 20: MCG-14; Nov 21: MCG-14; Nov 22: MCG-14; Nov 23: MCG-14; Nov 24: MCG-14; Nov 25: MCG-14; Nov 26: MCG-14; Nov 27: MCG-14; Nov 28: MCG-14; Nov 29: MCG-14; Nov 30: MCG-14; Dec 01: MCG-14; Dec 02: MCG-14; Dec 03: MCG-14; Dec 04: MCG-14; Dec 05: MCG-14; Dec 06: MCG-14; Dec 07: MCG-14; Dec 08: MCG-14; Dec 09: MCG-14; Dec 10: MCG-14; Dec 11: MCG-14; Dec 12: MCG-14; Dec 13: MCG-14; Dec 14: MCG-14; Dec 15: MCG-14; Dec 16: MCG-14; Dec 17: MCG-14; Dec 18: MCG-14; Dec 19: MCG-14; Dec 20: MCG-14; Dec 21: MCG-14; Dec 22: MCG-14; Dec 23: MCG-14; Dec 24: MCG-14; Dec 25: MCG-14; Dec 26: MCG-14; Dec 27: MCG-14; Dec 28: MCG-14; Dec 29: MCG-14; Dec 30: MCG-14; Dec 31: MCG-14; Jan 01: MCG-14; Jan 02: MCG-14; Jan 03: MCG-14; Jan 04: MCG-14; Jan 05: MCG-14; Jan 06: MCG-14; Jan 07: MCG-14; Jan 08: MCG-14; Jan 09: MCG-14; Jan 10: MCG-14; Jan 11: MCG-14; Jan 12: MCG-14; Jan 13: MCG-14; Jan 14: MCG-14; Jan 15: MCG-14; Jan 16: MCG-14; Jan 17: MCG-14; Jan 18: MCG-14; Jan 19: MCG-14; Jan 20: MCG-14; Jan 21: MCG-14; Jan 22: MCG-14; Jan 23: MCG-14; Jan 24: MCG-14; Jan 25: MCG-14; Jan 26: MCG-14; Jan 27: MCG-14; Jan 28: MCG-14; Jan 29: MCG-14; Jan 30: MCG-14; Jan 31: MCG-14; Feb 01: MCG-14; Feb 02: MCG-14; Feb 03: MCG-14; Feb 04: MCG-14; Feb 05: MCG-14; Feb 06: MCG-14; Feb 07: MCG-14; Feb 08: MCG-14; Feb 09: MCG-14; Feb 10: MCG-14; Feb 11: MCG-14; Feb 12: MCG-14; Feb 13: MCG-14; Feb 14: MCG-14; Feb 15: MCG-14; Feb 16: MCG-14; Feb 17: MCG-14; Feb 18: MCG-14; Feb 19: MCG-14; Feb 20: MCG-14; Feb 21: MCG-14; Feb 22: MCG-14; Feb 23: MCG-14; Feb 24: MCG-14; Feb 25: MCG-14; Feb 26: MCG-14; Feb 27: MCG-14; Feb 28: MCG-14; Mar 01: MCG-14; Mar 02: MCG-14; Mar 03: MCG-14; Mar 04: MCG-14; Mar 05: MCG-14; Mar 06: MCG-14; Mar 07: MCG-14; Mar 08: MCG-14; Mar 09: MCG-14; Mar 10: MCG-14; Mar 11: MCG-14; Mar 12: MCG-14; Mar 13: MCG-14; Mar 14: MCG-14; Mar 15: MCG-14; Mar 16: MCG-14; Mar 17: MCG-14; Mar 18: MCG-14; Mar 19: MCG-14; Mar 20: MCG-14; Mar 21: MCG-14; Mar 22: MCG-14; Mar 23: MCG-14; Mar 24: MCG-14; Mar 25: MCG-14; Mar 26: MCG-14; Mar 27: MCG-14; Mar 28: MCG-14; Mar 29: MCG-14; Mar 30: MCG-14; Mar 31: MCG-14; Apr 01: MCG-14; Aug 25: MCG-15; Aug 26: MCG-15; Aug 27: MCG-15; Aug 28: MCG-15; Aug 29: MCG-15; Aug 30: MCG-15; Aug 31: MCG-15; Sep 01: MCG-15; Sep 02: MCG-15; Sep 03: MCG-15; Sep 04: MCG-15; Sep 05: MCG-15; Sep 06: MCG-15; Sep 07: MCG-15; Sep 08: MCG-15; Sep 09: MCG-15; Sep 10: MCG-15; Sep 11: MCG-15; Sep 12: MCG-15; Sep 13: MCG-15; Sep 14: MCG-15; Sep 15: MCG-15; Sep 16: MCG-15; Sep 17: MCG-15; Sep 18: MCG-15; Sep 19: MCG-15; Sep 20: MCG-15; Sep 21: MCG-15; Sep 22: MCG-15; Sep 23: MCG-15; Sep 24: MCG-15; Sep 25: MCG-15; Sep 26: MCG-15; Sep 27: MCG-15; Sep 28: MCG-15; Sep 29: MCG-15; Sep 30: MCG-15; Oct 01: MCG-15; Oct 02: MCG-15; Oct 03: MCG-15; Oct 04: MCG-15; Oct 05: MCG-15; Oct 06: MCG-15; Oct 07: MCG-15; Oct 08: MCG-15; Oct 09: MCG-15; Oct 10: MCG-15; Oct 11: MCG-15; Oct 12: MCG-15; Oct 13: MCG-15; Oct 14: MCG-15; Oct 15: MCG-15; Oct 16: MCG-15; Oct 17: MCG-15; Oct 18: MCG-15; Oct 19: MCG-15; Oct 20: MCG-15; Oct 21: MCG-15; Oct 22: MCG-15; Oct 23: MCG-15; Oct 24: MCG-15; Oct 25: MCG-15; Oct 26: MCG-15; Oct 27: MCG-15; Oct 28: MCG-15; Oct 29: MCG-15; Oct 30: MCG-15; Oct 31: MCG-15; Nov 01: MCG-15; Nov 02: MCG-15; Nov 03: MCG-15; Nov 04: MCG-15; Nov 05: MCG-15; Nov 06: MCG-15; Nov 07: MCG-15; Nov 08: MCG-15; Nov 09: MCG-15; Nov 10: MCG-15; Nov 11: MCG-15; Nov 12: MCG-15; Nov 13: MCG-15; Nov 14: MCG-15; Nov 15: MCG-15; Nov 16: MCG-15; Nov 17: MCG-15; Nov 18: MCG-15; Nov 19: MCG-15; Nov 20: MCG-15; Nov 21: MCG-15; Nov 22: MCG-15; Nov 23: MCG-15; Nov 24: MCG-15; Nov 25: MCG-15; Nov 26: MCG-15; Nov 27: MCG-15; Nov 28: MCG-15; Nov 29: MCG-15; Nov 30: MCG-15; Dec 01: MCG-15; Dec 02: MCG-15; Dec 03: MCG-15; Dec 04: MCG-15; Dec 05: MCG-15; Dec 06: MCG-15; Dec 07: MCG-15; Dec 08: MCG-15; Dec 09: MCG-15; Dec 10: MCG-15; Dec 11: MCG-15; Dec 12: MCG-15; Dec 13: MCG-15; Dec 14: MCG-15; Dec 15: MCG-15; Dec 16: MCG-15; Dec 17: MCG-15; Dec 18: MCG-15; Dec 19: MCG-15; Dec 20: MCG-15; Dec 21: MCG-15; Dec 22: MCG-15; Dec 23: MCG-15; Dec 24: MCG-15; Dec 25: MCG-15; Dec 26: MCG-15; Dec 27: MCG-15; Dec 28: MCG-15; Dec 29: MCG-15; Dec 30: MCG-15; Dec 31: MCG-15; Jan 01: MCG-15; Jan 02: MCG-15; Jan 03: MCG-15; Jan 04: MCG-15; Jan 05: MCG-15; Jan 06: MCG-15; Jan 07: MCG-15; Jan 08: MCG-15; Jan 09: MCG-15; Jan 10: MCG-15; Jan 11: MCG-15; Jan 12: MCG-15; Jan 13: MCG-15; Jan 14: MCG-15; Jan 15: MCG-15; Jan 16: MCG-15; Jan 17: MCG-15; Jan 18: MCG-15; Jan 19: MCG-15; Jan 20: MCG-15; Jan 21: MCG-15; Jan 22: MCG-15; Jan 23: MCG-15; Jan 24: MCG-15; Jan 25: MCG-15; Jan 26: MCG-15; Jan 27: MCG-15; Jan 28: MCG-15; Jan 29: MCG-15; Jan 30: MCG-15; Jan 31: MCG-15; Feb 01: MCG-15; Feb 02: MCG-15; Feb 03: MCG-15; Feb 04: MCG-15; Feb 05: MCG-15; Feb 06: MCG-15; Feb 07: MCG-15; Feb 08: MCG-15; Feb 09: MCG-15; Feb 10: MCG-15; Feb 11: MCG-15; Feb 12: MCG-15; Feb 13: MCG-15; Feb 14: MCG-15; Feb 15: MCG-15; Feb 16: MCG-15; Feb 17: MCG-15; Feb 18: MCG-15; Feb 19: MCG-15; Feb 20: MCG-15; Feb 21: MCG-15; Feb 22: MCG-15; Feb 23: MCG-15; Feb 24: MCG-15; Feb 25: MCG-15; Feb 26: MCG-15; Feb 27: MCG-15; Feb 28: MCG-15; Mar 01: MCG-15; Mar 02: MCG-15; Mar 03: MCG-15
|  | MCG-2 | [210 empty] | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13 | MCG-13
MCG-3
MCG-4
MCG-5
MCG-6
MCG-7
MCG-8
MCG-9
MCG-10
MCG-11
| Key Milestones | Feb 10: MCG-16; May 12: MCG-20; May 23: MCG-21; Jul 28: MCG-22; Oct 20: MCG-23; Oct 27: MCG-24; Jan 07: MCG-25; Jan 29: MCG-26; Apr 09: MCG-27; May 15: MCG-28; May 26: MCG-29; Jun 01: MCG-30; Aug 12: MCG-31; Aug 26: MCG-32; Sep 23: MCG-33; Feb 04: MCG-34; May 20: MCG-35
MCG-17
MCG-18
MCG-19
| McGough Tracking | Nov 25: MCG-36; Feb 10: MCG-38; Feb 17: MCG-45; Mar 03: MCG-46; Mar 10: MCG-48; Apr 03: MCG-49; Apr 16: MCG-50; May 16: MCG-51; May 21: MCG-52; May 22: MCG-53; May 23: MCG-54; May 27: MCG-55; Jul 18: MCG-56; Jul 21: MCG-57; Jul 28: MCG-58; Sep 12: MCG-59; Sep 15: MCG-60; Oct 24: MCG-61; Nov 17: MCG-62; Dec 17: MCG-63; Jan 07: MCG-64; Jan 16: MCG-65; Apr 01: MCG-66; Apr 09: MCG-67; Apr 17: MCG-68; Apr 24: MCG-69; Jul 08: MCG-70; Jul 27: MCG-71; Oct 07: MCG-72; Nov 04: MCG-73; Nov 17: MCG-74; Nov 18: MCG-75; Nov 20: MCG-76; Nov 30: MCG-78; Dec 18: MCG-79; Mar 03: MCG-80
[84 empty] | MCG-37 | [76 empty] | MCG-39 | [20 empty] | MCG-47 | [626 empty] | MCG-77
MCG-40
MCG-41
MCG-42
MCG-43
MCG-44
Design | Design Milestone | Sep 04: DM-1; Sep 05: DM-1; Sep 19: DM-2; Oct 17: DM-3; Nov 14: DM-4; Dec 11: DM-5; Dec 12: DM-5; Dec 13: DM-5; Dec 14: DM-5; Dec 15: DM-5; Dec 16: DM-5; Dec 17: DM-5; Dec 18: DM-5; Dec 19: DM-7; Dec 20: DM-8; Dec 21: DM-8; Dec 22: DM-8; Dec 23: DM-8; Dec 24: DM-8; Dec 25: DM-8; Dec 26: DM-8; Dec 27: DM-8; Dec 28: DM-8; Dec 29: DM-8; Dec 30: DM-8; Dec 31: DM-8; Jan 01: DM-8; Jan 02: DM-8; Jan 03: DM-8; Jan 04: DM-8; Jan 05: DM-8; Jan 06: DM-8; Jan 07: DM-8; Jan 08: DM-8; Jan 09: DM-8; Jan 10: DM-8; Jan 11: DM-8; Jan 12: DM-8; Jan 13: DM-8; Jan 14: DM-8; Jan 15: DM-8; Jan 16: DM-8; Jan 17: DM-8; Jan 18: DM-8; Jan 19: DM-8; Jan 20: DM-8; Jan 21: DM-8; Jan 22: DM-8; Jan 23: DM-8; Jan 24: DM-8; Jan 25: DM-8; Jan 26: DM-8; Jan 27: DM-8; Jan 28: DM-8; Jan 29: DM-8; Jan 30: DM-9; Feb 13: DM-12; Feb 14: DM-12; Feb 15: DM-12; Feb 16: DM-12; Feb 17: DM-12; Feb 18: DM-12; Feb 19: DM-12; Feb 20: DM-12; Feb 21: DM-12; Feb 22: DM-12; Feb 23: DM-12; Feb 24: DM-12; Feb 25: DM-12; Feb 26: DM-12; Feb 27: DM-12; Feb 28: DM-12; Mar 01: DM-12; Mar 02: DM-12; Mar 03: DM-12; Apr 03: DM-13; Apr 04: DM-13; Apr 05: DM-13; Apr 06: DM-13; Apr 07: DM-13; Apr 08: DM-13; Apr 09: DM-13; Apr 10: DM-13; Apr 11: DM-13; Apr 12: DM-13; Apr 13: DM-13; Apr 14: DM-13; Apr 15: DM-13; Apr 16: DM-13; Apr 17: DM-13; Apr 18: DM-13; Apr 19: DM-13; Apr 20: DM-13; Apr 21: DM-13; Apr 22: DM-13; Apr 23: DM-13; Apr 24: DM-13; Apr 25: DM-13; Apr 26: DM-13; Apr 27: DM-13; Apr 28: DM-13; Apr 29: DM-13; Apr 30: DM-13; May 01: DM-13; May 02: DM-13; May 03: DM-13; May 04: DM-13; May 05: DM-13; May 06: DM-13; May 07: DM-13; May 08: DM-13; May 09: DM-13; May 10: DM-13; May 11: DM-13; May 12: DM-13; May 13: DM-13; May 14: DM-13; May 15: DM-13; May 16: DM-13; May 17: DM-13; May 18: DM-13; May 19: DM-13; May 20: DM-13; May 21: DM-13; May 22: DM-13; May 23: DM-13; May 24: DM-13; May 25: DM-13; May 26: DM-13; May 27: DM-13; May 28: DM-13; May 29: DM-13; May 30: DM-13; May 31: DM-13; Jun 01: DM-13; Jun 02: DM-13
[108 empty] | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6 | DM-6
[150 empty] | DM-10 | DM-10 | DM-10 | DM-10 | DM-10 | DM-10 | DM-10 | DM-10 | DM-10 | DM-10 | DM-10 | DM-10 | DM-10 | DM-10
[150 empty] | DM-11 | DM-11 | DM-11 | DM-11 | DM-11 | DM-11 | DM-11 | DM-11 | DM-11 | DM-11 | DM-11 | DM-11 | DM-11 | DM-11
Permitting | Permits | Jan 15: PERM-1; Jan 16: PERM-1; Jan 17: PERM-1; Jan 18: PERM-1; Jan 19: PERM-1; Jan 20: PERM-1; Jan 21: PERM-1; Jan 22: PERM-1; Jan 23: PERM-1; Jan 24: PERM-1; Jan 25: PERM-1; Jan 26: PERM-1; Jan 27: PERM-1; Jan 28: PERM-1; Jan 29: PERM-1; Jan 30: PERM-1; Jan 31: PERM-1; Feb 01: PERM-1; Feb 02: PERM-1; Feb 03: PERM-1; Feb 04: PERM-1; Feb 05: PERM-1; Feb 06: PERM-1; Feb 07: PERM-1; Feb 08: PERM-1; Feb 09: PERM-1; Feb 10: PERM-1; Feb 11: PERM-1; Feb 12: PERM-1; Feb 13: PERM-1; Feb 14: PERM-1; Feb 15: PERM-1; Feb 16: PERM-1; Feb 17: PERM-1; Feb 18: PERM-1; Feb 19: PERM-1; Feb 20: PERM-1; Feb 21: PERM-1; Feb 22: PERM-1; Feb 23: PERM-1; Feb 24: PERM-1; Feb 25: PERM-1; Feb 26: PERM-1; Feb 27: PERM-1; Feb 28: PERM-1; Mar 01: PERM-1; Mar 02: PERM-1; Mar 03: PERM-1; Mar 04: PERM-1; Mar 05: PERM-1; Mar 06: PERM-1; Mar 07: PERM-1; Mar 08: PERM-1; Mar 09: PERM-1; Mar 10: PERM-1; Mar 11: PERM-1; Mar 12: PERM-1; Mar 13: PERM-1; Mar 14: PERM-1; Mar 15: PERM-1; Mar 16: PERM-1; Mar 17: PERM-1; Mar 18: PERM-1; Mar 19: PERM-1; Mar 20: PERM-1; Mar 21: PERM-1; Mar 22: PERM-1; Mar 23: PERM-1; Mar 24: PERM-1; Mar 25: PERM-1; Mar 26: PERM-1; Mar 27: PERM-1; Mar 28: PERM-1; Mar 29: PERM-1; Mar 30: PERM-1; Mar 31: PERM-1; Apr 01: PERM-1; Apr 02: PERM-1; Apr 03: PERM-1; Apr 04: PERM-1; Apr 05: PERM-1; Apr 06: PERM-1; Apr 07: PERM-1; Apr 08: PERM-1; Apr 09: PERM-1; Apr 10: PERM-1; Apr 11: PERM-1; Apr 12: PERM-1; Apr 13: PERM-1; Apr 14: PERM-1; Apr 15: PERM-1; Apr 16: PERM-1; Apr 17: PERM-1; Apr 18: PERM-1; Apr 19: PERM-1; Apr 20: PERM-1; Apr 21: PERM-1; Apr 22: PERM-1; Apr 23: PERM-1; Apr 24: PERM-1; Apr 25: PERM-1; Apr 26: PERM-1; Apr 27: PERM-1; Apr 28: PERM-1; Apr 29: PERM-1; Apr 30: PERM-1; May 01: PERM-1; May 02: PERM-1; May 03: PERM-1; May 04: PERM-1; May 05: PERM-1; May 06: PERM-1; May 07: PERM-1; May 08: PERM-1; May 09: PERM-1; May 10: PERM-1; May 11: PERM-1; May 12: PERM-1; May 13: PERM-1; May 14: PERM-1; May 15: PERM-1; May 16: PERM-1; May 17: PERM-1; May 18: PERM-1; May 19: PERM-1; May 20: PERM-1; May 21: PERM-1
Submittals | Product Data | Apr 07: SUBM-11; Apr 08: SUBM-11; Apr 09: SUBM-11; Apr 10: SUBM-11; Apr 11: SUBM-11; Apr 12: SUBM-11; Apr 13: SUBM-11; Apr 14: SUBM-11; Apr 15: SUBM-11; Apr 16: SUBM-11; Apr 17: SUBM-11; Apr 18: SUBM-11; Apr 19: SUBM-11; Apr 20: SUBM-11; Apr 21: SUBM-11; Apr 22: SUBM-14; Apr 23: SUBM-14; Apr 24: SUBM-14; Apr 25: SUBM-14; Apr 26: SUBM-14; Apr 27: SUBM-14; Apr 28: SUBM-14
[217 empty] | SUBM-12 | SUBM-12 | SUBM-12 | SUBM-12 | SUBM-12 | SUBM-12 | SUBM-12 | SUBM-12 | SUBM-12 | SUBM-12 | SUBM-12 | SUBM-12 | SUBM-12 | SUBM-12 | SUBM-12 | SUBM-15 | SUBM-15 | SUBM-15 | SUBM-15 | SUBM-15 | SUBM-15 | SUBM-15
[217 empty] | SUBM-13 | SUBM-13 | SUBM-13 | SUBM-13 | SUBM-13 | SUBM-13 | SUBM-13 | SUBM-13 | SUBM-13 | SUBM-13 | SUBM-13 | SUBM-13 | SUBM-13 | SUBM-13 | SUBM-13 | SUBM-16 | SUBM-16 | SUBM-16 | SUBM-16 | SUBM-16 | SUBM-16 | SUBM-16
[232 empty] | SUBM-17 | SUBM-17 | SUBM-17 | SUBM-17 | SUBM-17 | SUBM-17 | SUBM-17
[232 empty] | SUBM-18 | SUBM-18 | SUBM-18 | SUBM-18 | SUBM-18 | SUBM-18 | SUBM-18
[232 empty] | SUBM-19 | SUBM-19 | SUBM-19 | SUBM-19 | SUBM-19 | SUBM-19 | SUBM-19
[232 empty] | SUBM-20 | SUBM-20 | SUBM-20 | SUBM-20 | SUBM-20 | SUBM-20 | SUBM-20
[232 empty] | SUBM-21 | SUBM-21 | SUBM-21 | SUBM-21 | SUBM-21 | SUBM-21 | SUBM-21
[232 empty] | SUBM-22 | SUBM-22 | SUBM-22 | SUBM-22 | SUBM-22 | SUBM-22 | SUBM-22
[232 empty] | SUBM-23 | SUBM-23 | SUBM-23 | SUBM-23 | SUBM-23 | SUBM-23 | SUBM-23
[232 empty] | SUBM-24 | SUBM-24 | SUBM-24 | SUBM-24 | SUBM-24 | SUBM-24 | SUBM-24
[232 empty] | SUBM-25 | SUBM-25 | SUBM-25 | SUBM-25 | SUBM-25 | SUBM-25 | SUBM-25
[232 empty] | SUBM-26 | SUBM-26 | SUBM-26 | SUBM-26 | SUBM-26 | SUBM-26 | SUBM-26
| Shop Drawings | Apr 07: SUBM-1; Apr 08: SUBM-1; Apr 09: SUBM-1; Apr 10: SUBM-1; Apr 11: SUBM-1; Apr 12: SUBM-1; Apr 13: SUBM-1; Apr 14: SUBM-1; Apr 15: SUBM-1; Apr 16: SUBM-1; Apr 17: SUBM-1; Apr 18: SUBM-1; Apr 19: SUBM-1; Apr 20: SUBM-1; Apr 21: SUBM-1
[217 empty] | SUBM-2 | SUBM-2 | SUBM-2 | SUBM-2 | SUBM-2 | SUBM-2 | SUBM-2 | SUBM-2 | SUBM-2 | SUBM-2 | SUBM-2 | SUBM-2 | SUBM-2 | SUBM-2 | SUBM-2
[217 empty] | SUBM-3 | SUBM-3 | SUBM-3 | SUBM-3 | SUBM-3 | SUBM-3 | SUBM-3 | SUBM-3 | SUBM-3 | SUBM-3 | SUBM-3 | SUBM-3 | SUBM-3 | SUBM-3 | SUBM-3
[217 empty] | SUBM-4 | SUBM-4 | SUBM-4 | SUBM-4 | SUBM-4 | SUBM-4 | SUBM-4 | SUBM-4 | SUBM-4 | SUBM-4 | SUBM-4 | SUBM-4 | SUBM-4 | SUBM-4 | SUBM-4
[217 empty] | SUBM-5 | SUBM-5 | SUBM-5 | SUBM-5 | SUBM-5 | SUBM-5 | SUBM-5 | SUBM-5 | SUBM-5 | SUBM-5 | SUBM-5 | SUBM-5 | SUBM-5 | SUBM-5 | SUBM-5
[217 empty] | SUBM-6 | SUBM-6 | SUBM-6 | SUBM-6 | SUBM-6 | SUBM-6 | SUBM-6 | SUBM-6 | SUBM-6 | SUBM-6 | SUBM-6 | SUBM-6 | SUBM-6 | SUBM-6 | SUBM-6
[217 empty] | SUBM-7 | SUBM-7 | SUBM-7 | SUBM-7 | SUBM-7 | SUBM-7 | SUBM-7 | SUBM-7 | SUBM-7 | SUBM-7 | SUBM-7 | SUBM-7 | SUBM-7 | SUBM-7 | SUBM-7
[217 empty] | SUBM-8 | SUBM-8 | SUBM-8 | SUBM-8 | SUBM-8 | SUBM-8 | SUBM-8 | SUBM-8 | SUBM-8 | SUBM-8 | SUBM-8 | SUBM-8 | SUBM-8 | SUBM-8 | SUBM-8
[217 empty] | SUBM-9 | SUBM-9 | SUBM-9 | SUBM-9 | SUBM-9 | SUBM-9 | SUBM-9 | SUBM-9 | SUBM-9 | SUBM-9 | SUBM-9 | SUBM-9 | SUBM-9 | SUBM-9 | SUBM-9
[217 empty] | SUBM-10 | SUBM-10 | SUBM-10 | SUBM-10 | SUBM-10 | SUBM-10 | SUBM-10 | SUBM-10 | SUBM-10 | SUBM-10 | SUBM-10 | SUBM-10 | SUBM-10 | SUBM-10 | SUBM-10
Structure/Foundations | Structural Foundations | Jul 18: STRUC-1; Jul 19: STRUC-1; Jul 20: STRUC-1; Jul 21: STRUC-1; Jul 22: STRUC-1; Jul 23: STRUC-1; Jul 24: STRUC-1; Jul 25: STRUC-1; Jul 26: STRUC-1; Jul 27: STRUC-1; Jul 28: STRUC-1; Jul 29: STRUC-1; Jul 30: STRUC-1; Jul 31: STRUC-1; Aug 01: STRUC-1; Aug 02: STRUC-1; Aug 03: STRUC-1; Aug 04: STRUC-1; Aug 05: STRUC-1; Aug 06: STRUC-1; Aug 07: STRUC-1; Aug 08: STRUC-1; Aug 09: STRUC-1; Aug 10: STRUC-1; Aug 11: STRUC-1; Aug 12: STRUC-1; Aug 13: STRUC-1; Aug 14: STRUC-1; Aug 15: STRUC-1; Aug 16: STRUC-1; Aug 17: STRUC-1; Aug 18: STRUC-1; Aug 19: STRUC-1; Aug 20: STRUC-1; Aug 21: STRUC-1; Aug 22: STRUC-1; Aug 23: STRUC-1; Aug 24: STRUC-1; Aug 25: STRUC-1; Aug 26: STRUC-1; Aug 27: STRUC-1; Aug 28: STRUC-1; Aug 29: STRUC-1; Aug 30: STRUC-1; Aug 31: STRUC-1; Sep 01: STRUC-1; Sep 02: STRUC-1; Sep 03: STRUC-1; Sep 04: STRUC-1; Sep 05: STRUC-1; Sep 06: STRUC-1; Sep 07: STRUC-1; Sep 08: STRUC-1; Sep 09: STRUC-1; Sep 10: STRUC-1; Sep 11: STRUC-1; Sep 12: STRUC-1
Interiors | Commissioning | Oct 07: CX-1; Oct 08: CX-1; Oct 09: CX-1; Oct 10: CX-1; Oct 11: CX-1; Oct 12: CX-1; Oct 13: CX-1; Oct 14: CX-1; Oct 15: CX-1; Oct 16: CX-1; Oct 17: CX-1; Oct 18: CX-1; Oct 19: CX-1; Oct 20: CX-1; Oct 21: CX-1; Oct 22: CX-1; Oct 23: CX-1; Oct 24: CX-1; Oct 25: CX-1; Oct 26: CX-1; Oct 27: CX-1; Oct 28: CX-1; Oct 29: CX-1; Oct 30: CX-1; Oct 31: CX-1; Nov 01: CX-1; Nov 02: CX-1; Nov 03: CX-1; Nov 04: CX-1; Nov 05: CX-1; Nov 06: CX-1; Nov 07: CX-1; Nov 08: CX-1; Nov 09: CX-1; Nov 10: CX-1; Nov 11: CX-1; Nov 12: CX-1; Nov 13: CX-1; Nov 14: CX-1; Nov 15: CX-1; Nov 16: CX-1; Nov 17: CX-1; Nov 18: CX-1; Nov 19: CX-1; Nov 20: CX-1; Nov 21: CX-1; Nov 22: CX-1; Nov 23: CX-1; Nov 24: CX-1; Nov 25: CX-1; Nov 26: CX-1; Nov 27: CX-1; Nov 28: CX-1; Nov 29: CX-1; Nov 30: CX-1; Dec 01: CX-1; Dec 02: CX-1; Dec 03: CX-1; Dec 04: CX-1; Dec 05: CX-1; Dec 06: CX-1; Dec 07: CX-1; Dec 08: CX-1; Dec 09: CX-1; Dec 10: CX-1; Dec 11: CX-1; Dec 12: CX-1; Dec 13: CX-1; Dec 14: CX-1; Dec 15: CX-1; Dec 16: CX-1; Dec 17: CX-1; Dec 18: CX-1; Dec 19: CX-1; Dec 20: CX-1; Dec 21: CX-1; Dec 22: CX-1; Dec 23: CX-1; Dec 24: CX-1; Dec 25: CX-1; Dec 26: CX-1; Dec 27: CX-1; Dec 28: CX-1; Dec 29: CX-1; Dec 30: CX-1; Dec 31: CX-1; Jan 01: CX-1; Jan 02: CX-1; Jan 03: CX-1; Jan 04: CX-1; Jan 05: CX-1; Jan 06: CX-1; Jan 07: CX-1; Jan 08: CX-1; Jan 09: CX-1; Jan 10: CX-1; Jan 11: CX-1; Jan 12: CX-1; Jan 13: CX-1; Jan 14: CX-1; Jan 15: CX-1; Jan 16: CX-1; Jan 17: CX-1; Jan 18: CX-1; Jan 19: CX-1; Jan 20: CX-1; Jan 21: CX-1; Jan 22: CX-1; Jan 23: CX-1; Jan 24: CX-1; Jan 25: CX-1; Jan 26: CX-1; Jan 27: CX-1; Jan 28: CX-1; Jan 29: CX-1; Jan 30: CX-1; Jan 31: CX-1; Feb 01: CX-1; Feb 02: CX-1; Feb 03: CX-1; Feb 04: CX-1; Feb 05: CX-1; Feb 06: CX-1; Feb 07: CX-1; Feb 08: CX-1; Feb 09: CX-1; Feb 10: CX-1; Feb 11: CX-1; Feb 12: CX-1; Feb 13: CX-1; Feb 14: CX-1; Feb 15: CX-1; Feb 16: CX-1; Feb 17: CX-1; Feb 18: CX-1; Feb 19: CX-1; Feb 20: CX-1; Feb 21: CX-1; Feb 22: CX-1; Feb 23: CX-1; Feb 24: CX-1; Feb 25: CX-1; Feb 26: CX-1; Feb 27: CX-1; Feb 28: CX-1; Mar 01: CX-1; Mar 02: CX-1; Mar 03: CX-1
| FF&E | Feb 05: CO-3; Feb 06: CO-3; Feb 07: CO-3; Feb 08: CO-3; Feb 09: CO-3; Feb 10: CO-3; Feb 11: CO-3; Feb 12: CO-3; Feb 13: CO-3; Feb 14: CO-3; Feb 15: CO-3; Feb 16: CO-3; Feb 17: CO-3; Feb 18: CO-3; Feb 19: CO-3; Feb 20: CO-3; Feb 21: CO-3; Feb 22: CO-3; Feb 23: CO-3; Feb 24: CO-3; Feb 25: CO-3; Feb 26: CO-3; Feb 27: CO-3; Feb 28: CO-3; Mar 01: CO-3; Mar 02: CO-3; Mar 03: CO-3; Mar 04: CO-3; Mar 05: CO-3; Mar 06: CO-3; Mar 07: CO-3; Mar 08: CO-3; Mar 09: CO-3; Mar 10: CO-3; Mar 11: CO-3; Mar 12: CO-3; Mar 13: CO-3; Mar 14: CO-3; Mar 15: CO-3; Mar 16: CO-3; Mar 17: CO-3; Mar 18: CO-3; Mar 19: CO-3; Mar 20: CO-3; Mar 21: CO-3; Mar 22: CO-3; Mar 23: CO-3; Mar 24: CO-3; Mar 25: CO-3; Mar 26: CO-3; Mar 27: CO-3; Mar 28: CO-3; Mar 29: CO-3; Mar 30: CO-3; Mar 31: CO-3; Apr 01: CO-3; Apr 02: CO-3; Apr 03: CO-3; Apr 04: CO-3; Apr 05: CO-3; Apr 06: CO-3; Apr 07: CO-3; Apr 08: CO-3
| Finishes - Kitchen | Jun 01: K-1; Jun 02: K-1; Jun 03: K-1; Jun 04: K-1; Jun 05: K-1; Jun 06: K-1; Jun 07: K-1; Jun 08: K-1; Jun 09: K-1; Jun 10: K-1; Jun 11: K-1; Jun 12: K-1; Jun 13: K-1; Jun 14: K-1; Jun 15: K-1; Jun 16: K-1; Jun 17: K-1; Jun 18: K-1; Jun 19: K-1; Jun 20: K-1; Jun 21: K-1; Jun 22: K-1; Jun 23: K-1; Jun 24: K-1; Jun 25: K-1; Jun 26: K-1; Jun 27: K-1; Jun 28: K-1; Jun 29: K-1; Jun 30: K-1; Jul 01: K-1; Jul 02: K-1; Jul 03: K-1; Jul 04: K-1; Jul 05: K-1; Jul 06: K-1; Jul 07: K-1; Jul 08: K-1; Jul 09: K-1; Jul 10: K-1; Jul 11: K-1; Jul 12: K-1; Jul 13: K-1; Jul 14: K-1; Jul 15: K-1; Jul 16: K-1; Jul 17: K-1; Jul 18: K-1; Jul 19: K-1; Jul 20: K-1; Jul 21: K-1; Jul 22: K-1; Jul 23: K-1; Jul 24: K-1; Jul 25: K-1; Jul 26: K-1; Jul 27: K-1; Jul 28: K-1; Jul 29: K-1; Jul 30: K-1; Jul 31: K-1; Aug 01: K-1; Aug 02: K-1; Aug 03: K-1; Aug 04: K-1; Aug 05: K-1; Aug 06: K-1; Aug 07: K-1; Aug 08: K-1; Aug 09: K-1; Aug 10: K-1; Aug 11: K-1; Aug 12: K-1; Aug 13: K-1; Aug 14: K-1; Aug 15: K-1; Aug 16: K-1; Aug 17: K-1; Aug 18: K-1; Aug 19: K-1; Aug 20: K-1; Aug 21: K-1; Aug 22: K-1; Aug 23: K-1; Aug 24: K-1
| Finishes - Mechanical Room | Nov 04: CO-2; Nov 05: CO-2; Nov 06: CO-2; Nov 07: CO-2; Nov 08: CO-2; Nov 09: CO-2; Nov 10: CO-2; Nov 11: CO-2; Nov 12: CO-2; Nov 13: CO-2; Nov 14: CO-2; Nov 15: CO-2; Nov 16: CO-2; Nov 17: CO-2; Nov 18: CO-2; Nov 19: CO-2; Nov 20: CO-2; Nov 21: CO-2; Nov 22: CO-2; Nov 23: CO-2; Nov 24: CO-2; Nov 25: CO-2; Nov 26: CO-2; Nov 27: CO-2; Nov 28: CO-2; Nov 29: CO-2; Nov 30: CO-2; Dec 01: CO-2; Dec 02: CO-2; Dec 03: CO-2; Dec 04: CO-2; Dec 05: CO-2; Dec 06: CO-2; Dec 07: CO-2; Dec 08: CO-2; Dec 09: CO-2; Dec 10: CO-2; Dec 11: CO-2; Dec 12: CO-2; Dec 13: CO-2; Dec 14: CO-2; Dec 15: CO-2; Dec 16: CO-2; Dec 17: CO-2; Dec 18: CO-1; Dec 19: CO-1; Dec 20: CO-1; Dec 21: CO-1; Dec 22: CO-1; Dec 23: CO-1; Dec 24: CO-1; Dec 25: CO-1; Dec 26: CO-1; Dec 27: CO-1; Dec 28: CO-1; Dec 29: CO-1; Jan 30: CO-1; Jan 31: CO-1; Feb 01: CO-1; Feb 02: CO-1; Feb 03: CO-1; Feb 04: CO-1; Feb 05: CO-1; Feb 06: CO-1; Feb 07: CO-1; Feb 08: CO-1; Feb 09: CO-1; Feb 10: CO-1; Feb 11: CO-1; Feb 12: CO-1; Feb 13: CO-1; Feb 14: CO-1; Feb 15: CO-1; Feb 16: CO-1; Feb 17: CO-1; Feb 18: CO-1; Feb 19: CO-1; Feb 20: CO-1; Feb 21: CO-1; Feb 22: CO-1; Feb 23: CO-1; Feb 24: CO-1; Feb 25: CO-1; Feb 26: CO-1; Feb 27: CO-1; Feb 28: CO-1; Mar 01: CO-1; Mar 02: CO-1; Mar 03: CO-1; Mar 04: CO-1; Mar 05: CO-1; Mar 06: CO-1; Mar 07: CO-1; Mar 08: CO-1; Mar 09: CO-1; Mar 10: CO-1; Mar 11: CO-1; Mar 12: CO-1; Mar 19: M-8; Mar 20: M-8; Mar 21: M-8; Mar 22: M-8; Mar 23: M-8; Mar 24: M-8; Mar 25: M-8; Mar 26: M-8; Mar 27: M-8; Mar 28: M-8; Mar 29: M-8; Mar 30: M-8; Mar 31: M-8; Apr 01: M-8; Apr 02: M-8; Apr 03: M-8; Apr 04: M-8; Apr 05: M-8; Apr 06: M-8; Apr 07: M-8; Apr 08: M-8; Apr 09: M-8; Apr 10: M-8; Apr 11: M-8; Apr 12: M-8; Apr 13: M-8; Apr 14: M-8; Apr 15: M-8; Apr 16: M-8; Apr 17: M-8; Apr 18: M-8; Apr 19: M-8; Apr 20: M-8; Apr 21: M-8; Apr 22: M-8; Apr 23: M-8; Apr 24: M-8; Apr 25: M-8; Apr 26: M-8; Apr 27: M-8; Apr 28: M-8; Apr 29: M-8; Apr 30: M-8; May 14: E-2; May 15: E-2; May 18: M-2; May 19: M-2; May 20: M-2; May 21: M-2; May 22: M-2
[472 empty] | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | CO-2 | [19 empty] | M-10 | M-10 | M-10 | M-10 | M-10 | M-10 | M-10 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | M-1 | [61 empty] | M-11 | M-11 | M-11 | M-11 | M-11
| Finishes - Zone 1 | Apr 02: F-1; Apr 03: F-1; Apr 04: F-1; Apr 05: F-1; Apr 06: F-1; Apr 07: F-1; Apr 08: F-1; Apr 09: F-1; Apr 10: F-1; Apr 11: F-1; Apr 12: F-1; Apr 13: F-1; Apr 14: F-1; Apr 15: F-1; Apr 16: F-1; May 18: M-3; May 19: M-3; May 20: F-3; May 21: F-3; May 22: F-3; May 23: F-3; May 24: F-3; May 25: F-3; May 26: F-3; May 27: F-3; May 28: F-3; May 29: F-3; Jun 01: F-2; Jun 02: F-2; Jun 03: F-2; Jun 04: F-2; Jun 05: F-2; Jun 06: F-2; Jun 07: F-2; Jun 08: F-2; Jun 09: F-2; Jun 10: F-2; Jun 11: F-2; Jun 12: F-2; Jun 15: M-4; Jun 16: M-4; Jun 17: M-4; Jun 18: M-4; Jun 19: M-4; Jun 22: C-1; Jun 23: C-1; Jun 24: C-1; Jun 25: C-1; Jun 26: C-1; Jun 27: C-1; Jun 28: C-1; Jun 29: C-1; Jun 30: C-1; Jul 01: IN-1; Jul 02: C-2; Jul 03: C-2; Jul 04: C-2; Jul 05: C-2; Jul 06: C-2; Jul 07: C-2; Jul 08: FI-1; Jul 09: FI-1; Jul 10: FI-1; Jul 11: FI-1; Jul 12: FI-1; Jul 13: FI-1; Jul 14: FI-1; Jul 15: FI-1; Jul 16: FI-1; Jul 17: FI-1; Jul 18: FI-1; Jul 19: FI-1; Jul 20: FI-1; Jul 21: FI-1; Jul 22: FI-1; Jul 23: FI-1; Jul 24: FI-1; Jul 25: FI-1; Jul 26: FI-1; Jul 27: FI-1; Jul 28: FI-1; Jul 29: FI-1; Jul 30: FI-1; Jul 31: FI-1; Aug 01: FI-1; Aug 02: FI-1; Aug 03: FI-1; Aug 04: FI-1; Aug 05: FI-1; Aug 06: FI-1; Aug 07: FI-1; Aug 08: FI-1; Aug 09: FI-1; Aug 10: FI-1; Aug 11: FI-1; Aug 12: FI-1; Aug 13: FI-1; Aug 14: FI-1; Aug 15: FI-1; Aug 16: FI-1; Aug 17: FI-1; Aug 18: FI-1; Aug 19: FI-1; Aug 20: FI-1; Aug 21: FI-1; Aug 22: FI-1; Aug 23: FI-1; Aug 24: FI-1; Aug 25: FI-1
| Finishes - Zone 2 | Apr 17: F-1; Apr 18: F-1; Apr 19: F-1; Apr 20: F-1; Apr 21: F-1; Apr 22: F-1; Apr 23: F-1; Apr 24: F-1; Apr 25: F-1; Apr 26: F-1; Apr 27: F-1; Apr 28: F-1; Apr 29: F-1; Apr 30: F-1; Jun 02: M-3; Jun 03: M-3; Jun 04: F-3; Jun 05: F-3; Jun 06: F-3; Jun 07: F-3; Jun 08: F-3; Jun 09: F-3; Jun 10: F-3; Jun 11: F-3; Jun 12: F-3; Jun 15: F-2; Jun 16: F-2; Jun 17: F-2; Jun 18: F-2; Jun 19: F-2; Jun 20: F-2; Jun 21: F-2; Jun 22: F-2; Jun 23: F-2; Jun 24: F-2; Jun 25: F-2; Jun 26: F-2; Jun 29: C-3; Jun 30: C-3; Jul 01: C-3; Jul 02: C-5; Jul 03: C-5; Jul 04: C-5; Jul 05: C-5; Jul 06: C-5; Jul 07: C-5; Jul 08: C-5; Jul 09: C-5; Jul 10: C-5; Jul 11: C-5; Jul 12: C-5; Jul 13: C-5; Jul 14: C-5; Jul 15: C-5; Jul 16: C-5; Jul 17: C-5; Jul 18: C-5; Jul 19: C-5; Jul 20: C-5; Jul 21: C-5; Jul 22: C-5; Jul 23: C-5; Jul 24: C-5; Jul 25: C-5; Jul 26: C-5; Jul 27: C-5; Jul 28: C-5; Jul 29: FI-1; Jul 30: FI-1; Jul 31: FI-1; Aug 01: FI-1; Aug 02: FI-1; Aug 03: FI-1; Aug 04: FI-1; Aug 05: FI-1; Aug 06: FI-1; Aug 07: FI-1; Aug 08: FI-1; Aug 09: FI-1; Aug 10: FI-1; Aug 11: FI-1; Aug 12: FI-1; Aug 13: FI-1; Aug 14: FI-1; Aug 15: FI-1; Aug 16: FI-1; Aug 17: FI-1; Aug 18: FI-1; Aug 19: FI-1; Aug 20: FI-1; Aug 21: FI-1; Aug 22: FI-1; Aug 23: FI-1; Aug 24: FI-1; Aug 25: FI-1; Aug 26: FI-1; Aug 27: FI-1; Aug 28: FI-1; Aug 29: FI-1; Aug 30: FI-1; Aug 31: FI-1; Sep 01: FI-1; Sep 02: FI-1; Sep 03: FI-1; Sep 04: FI-1; Sep 05: FI-1; Sep 06: FI-1; Sep 07: FI-1; Sep 08: FI-1; Sep 09: FI-1
| Finishes - Zone 3 | May 01: F-1; May 02: F-1; May 03: F-1; May 04: F-1; May 05: F-1; May 06: F-1; May 07: F-1; May 08: F-1; May 09: F-1; May 10: F-1; May 11: F-1; May 12: F-1; May 13: F-1; May 14: F-1; Jun 16: M-3; Jun 17: M-3; Jun 18: F-3; Jun 19: F-3; Jun 20: F-3; Jun 21: F-3; Jun 22: F-3; Jun 23: F-3; Jun 24: F-3; Jun 25: F-3; Jun 26: F-3; Jun 29: F-2; Jun 30: F-2; Jul 01: F-2; Jul 02: F-2; Jul 03: F-2; Jul 04: F-2; Jul 05: F-2; Jul 06: F-2; Jul 07: F-2; Jul 08: F-2; Jul 09: F-2; Jul 10: F-2; Jul 11: F-2; Jul 12: F-2; Jul 13: F-2; Jul 14: M-4; Jul 15: M-4; Jul 16: M-4; Jul 17: M-4; Jul 18: M-4; Jul 19: M-4; Jul 20: M-4; Jul 21: C-1; Jul 22: C-1; Jul 23: C-1; Jul 24: C-1; Jul 25: C-1; Jul 26: C-1; Jul 27: C-1; Jul 28: C-1; Jul 29: C-1; Jul 30: IN-1; Jul 31: C-2; Aug 01: C-2; Aug 02: C-2; Aug 03: C-2; Aug 04: C-2; Aug 05: FI-1; Aug 06: FI-1; Aug 07: FI-1; Aug 08: FI-1; Aug 09: FI-1; Aug 10: FI-1; Aug 11: FI-1; Aug 12: FI-1; Aug 13: FI-1; Aug 14: FI-1; Aug 15: FI-1; Aug 16: FI-1; Aug 17: FI-1; Aug 18: FI-1; Aug 19: FI-1; Aug 20: FI-1; Aug 21: FI-1; Aug 22: FI-1; Aug 23: FI-1; Aug 24: FI-1; Aug 25: FI-1; Aug 26: FI-1; Aug 27: FI-1; Aug 28: FI-1; Aug 29: FI-1; Aug 30: FI-1; Aug 31: FI-1; Sep 01: FI-1; Sep 02: FI-1; Sep 03: FI-1; Sep 04: FI-1; Sep 05: FI-1; Sep 06: FI-1; Sep 07: FI-1; Sep 08: FI-1; Sep 09: FI-1; Sep 10: FI-1; Sep 11: FI-1; Sep 12: FI-1; Sep 13: FI-1; Sep 14: FI-1; Sep 15: FI-1; Sep 16: FI-1; Sep 17: FI-1; Sep 18: FI-1; Sep 19: FI-1; Sep 20: FI-1; Sep 21: FI-1; Sep 22: FI-1; Sep 23: FI-1
| Finishes - Zone 4 | May 15: F-1; May 16: F-1; May 17: F-1; May 18: F-1; May 19: F-1; May 20: F-1; May 21: F-1; May 22: F-1; May 23: F-1; May 24: F-1; May 25: F-1; May 26: F-1; May 27: F-1; May 28: F-1; May 29: F-1; Jun 30: M-3; Jul 01: M-3; Jul 02: F-3; Jul 03: F-3; Jul 04: F-3; Jul 05: F-3; Jul 06: F-3; Jul 07: F-3; Jul 08: F-3; Jul 09: F-3; Jul 10: F-3; Jul 11: F-3; Jul 12: F-3; Jul 13: F-3; Jul 14: F-2; Jul 15: F-2; Jul 16: F-2; Jul 17: F-2; Jul 18: F-2; Jul 19: F-2; Jul 20: F-2; Jul 21: F-2; Jul 22: F-2; Jul 23: F-2; Jul 24: F-2; Jul 25: F-2; Jul 26: F-2; Jul 27: F-2; Jul 28: C-3; Jul 29: C-3; Jul 30: C-3; Jul 31: C-5; Aug 01: C-5; Aug 02: C-5; Aug 03: C-5; Aug 04: C-5; Aug 05: C-5; Aug 06: C-5; Aug 07: C-5; Aug 08: C-5; Aug 09: C-5; Aug 10: C-5; Aug 11: C-5; Aug 12: C-5; Aug 13: C-5; Aug 14: C-5; Aug 15: C-5; Aug 16: C-5; Aug 17: C-5; Aug 18: C-5; Aug 19: C-5; Aug 20: C-5; Aug 21: C-5; Aug 22: C-5; Aug 23: C-5; Aug 24: C-5; Aug 25: C-5; Aug 26: FI-1; Aug 27: FI-1; Aug 28: FI-1; Aug 29: FI-1; Aug 30: FI-1; Aug 31: FI-1; Sep 01: FI-1; Sep 02: FI-1; Sep 03: FI-1; Sep 04: FI-1; Sep 05: FI-1; Sep 06: FI-1; Sep 07: FI-1; Sep 08: FI-1; Sep 09: FI-1; Sep 10: FI-1; Sep 11: FI-1; Sep 12: FI-1; Sep 13: FI-1; Sep 14: FI-1; Sep 15: FI-1; Sep 16: FI-1; Sep 17: FI-1; Sep 18: FI-1; Sep 19: FI-1; Sep 20: FI-1; Sep 21: FI-1; Sep 22: FI-1; Sep 23: FI-1; Sep 24: FI-1; Sep 25: FI-1; Sep 26: FI-1; Sep 27: FI-1; Sep 28: FI-1; Sep 29: FI-1; Sep 30: FI-1; Oct 01: FI-1; Oct 02: FI-1; Oct 03: FI-1; Oct 04: FI-1; Oct 05: FI-1; Oct 06: FI-1; Oct 07: FI-1
| Finishes - Zone 5 | Jun 01: F-1; Jun 02: F-1; Jun 03: F-1; Jun 04: F-1; Jun 05: F-1; Jun 06: F-1; Jun 07: F-1; Jun 08: F-1; Jun 09: F-1; Jun 10: F-1; Jun 11: F-1; Jun 12: F-1; Jul 15: M-3; Jul 16: M-3; Jul 17: F-3; Jul 18: F-3; Jul 19: F-3; Jul 20: F-3; Jul 21: F-3; Jul 22: F-3; Jul 23: F-3; Jul 24: F-3; Jul 25: F-3; Jul 26: F-3; Jul 27: F-3; Jul 28: F-2; Jul 29: F-2; Jul 30: F-2; Jul 31: F-2; Aug 01: F-2; Aug 02: F-2; Aug 03: F-2; Aug 04: F-2; Aug 05: F-2; Aug 06: F-2; Aug 07: F-2; Aug 08: F-2; Aug 09: F-2; Aug 10: F-2; Aug 11: C-3; Aug 12: C-3; Aug 13: C-3; Aug 14: C-6; Aug 15: C-6; Aug 16: C-6; Aug 17: C-6; Aug 18: C-6; Aug 19: C-6; Aug 20: C-6; Aug 21: C-6; Aug 22: C-6; Aug 23: C-6; Aug 24: C-6; Aug 25: C-6; Aug 26: C-6; Aug 27: C-6; Aug 28: C-6; Aug 29: C-6; Aug 30: C-6; Aug 31: C-6; Sep 01: C-6; Sep 02: C-6; Sep 03: C-6; Sep 04: C-6; Sep 05: C-6; Sep 06: C-6; Sep 07: C-6; Sep 08: C-6; Sep 09: C-6; Sep 10: FI-1; Sep 11: FI-1; Sep 12: FI-1; Sep 13: FI-1; Sep 14: FI-1; Sep 15: FI-1; Sep 16: FI-1; Sep 17: FI-1; Sep 18: FI-1; Sep 19: FI-1; Sep 20: FI-1; Sep 21: FI-1; Sep 22: FI-1; Sep 23: FI-1; Sep 24: FI-1; Sep 25: FI-1; Sep 26: FI-1; Sep 27: FI-1; Sep 28: FI-1; Sep 29: FI-1; Sep 30: FI-1; Oct 01: FI-1; Oct 02: FI-1; Oct 03: FI-1; Oct 04: FI-1; Oct 05: FI-1; Oct 06: FI-1; Oct 07: FI-1; Oct 08: FI-1; Oct 09: FI-1; Oct 10: FI-1; Oct 11: FI-1; Oct 12: FI-1; Oct 13: FI-1; Oct 14: FI-1; Oct 15: FI-1; Oct 16: FI-1; Oct 17: FI-1; Oct 18: FI-1; Oct 19: FI-1; Oct 20: FI-1; Oct 21: FI-1
| Finishes - Zone 6 | Jun 15: F-1; Jun 16: F-1; Jun 17: F-1; Jun 18: F-1; Jun 19: F-1; Jun 20: F-1; Jun 21: F-1; Jun 22: F-1; Jun 23: F-1; Jun 24: F-1; Jun 25: F-1; Jun 26: F-1; Jul 29: M-3; Jul 30: M-3; Jul 31: F-3; Aug 01: F-3; Aug 02: F-3; Aug 03: F-3; Aug 04: F-3; Aug 05: F-3; Aug 06: F-3; Aug 07: F-3; Aug 08: F-3; Aug 09: F-3; Aug 10: F-3; Aug 11: F-2; Aug 12: F-2; Aug 13: F-2; Aug 14: F-2; Aug 15: F-2; Aug 16: F-2; Aug 17: F-2; Aug 18: F-2; Aug 19: F-2; Aug 20: F-2; Aug 21: F-2; Aug 22: F-2; Aug 23: F-2; Aug 24: F-2; Aug 25: C-4; Aug 26: C-4; Aug 27: C-4; Aug 28: C-6; Aug 29: C-6; Aug 30: C-6; Aug 31: C-6; Sep 01: C-6; Sep 02: C-6; Sep 03: C-6; Sep 04: C-6; Sep 05: C-6; Sep 06: C-6; Sep 07: C-6; Sep 08: C-6; Sep 09: C-6; Sep 10: C-6; Sep 11: C-6; Sep 12: C-6; Sep 13: C-6; Sep 14: C-6; Sep 15: C-6; Sep 16: C-6; Sep 17: C-6; Sep 18: C-6; Sep 19: C-6; Sep 20: C-6; Sep 21: C-6; Sep 22: C-6; Sep 23: C-6; Sep 24: FI-1; Sep 25: FI-1; Sep 26: FI-1; Sep 27: FI-1; Sep 28: FI-1; Sep 29: FI-1; Sep 30: FI-1; Oct 01: FI-1; Oct 02: FI-1; Oct 03: FI-1; Oct 04: FI-1; Oct 05: FI-1; Oct 06: FI-1; Oct 07: FI-1; Oct 08: FI-1; Oct 09: FI-1; Oct 10: FI-1; Oct 11: FI-1; Oct 12: FI-1; Oct 13: FI-1; Oct 14: FI-1; Oct 15: FI-1; Oct 16: FI-1; Oct 17: FI-1; Oct 18: FI-1; Oct 19: FI-1; Oct 20: FI-1; Oct 21: FI-1; Oct 22: FI-1; Oct 23: FI-1; Oct 24: FI-1; Oct 25: FI-1; Oct 26: FI-1; Oct 27: FI-1; Oct 28: FI-1; Oct 29: FI-1; Oct 30: FI-1; Oct 31: FI-1; Nov 01: FI-1; Nov 02: FI-1; Nov 03: FI-1; Nov 04: FI-1
| Finishes - Zone 7A | Aug 12: FI-1; Aug 13: FI-1; Aug 14: FI-1; Aug 15: FI-1; Aug 16: FI-1; Aug 17: FI-1; Aug 18: FI-1; Aug 19: FI-1; Aug 20: FI-1; Aug 21: FI-1; Aug 22: FI-1; Aug 23: FI-1; Aug 24: FI-1; Aug 25: FI-1; Aug 26: FI-1; Aug 27: FI-1; Aug 28: FI-1; Aug 29: FI-1; Aug 30: FI-1; Aug 31: FI-1; Sep 01: FI-1; Sep 02: FI-1; Sep 03: FI-1; Sep 04: FI-1; Sep 05: FI-1; Sep 06: FI-1; Sep 07: FI-1; Sep 08: FI-1; Sep 09: FI-1; Sep 10: FI-1; Sep 11: FI-1; Sep 12: FI-1; Sep 13: FI-1; Sep 14: FI-1; Sep 15: FI-1; Sep 16: FI-1; Sep 17: FI-1; Sep 18: FI-1; Sep 19: FI-1; Sep 20: FI-1; Sep 21: FI-1; Sep 22: FI-1; Sep 23: FI-1; Sep 24: FI-1; Sep 25: FI-1; Sep 26: FI-1; Sep 27: FI-1; Sep 28: FI-1; Sep 29: FI-1; Sep 30: FI-1; Oct 01: FI-1; Oct 02: FI-1; Oct 03: FI-1; Oct 04: FI-1; Oct 05: FI-1; Oct 06: FI-1; Oct 07: FI-1; Oct 08: FI-1; Oct 09: FI-1; Oct 10: FI-1; Oct 11: FI-1; Oct 12: FI-1; Oct 13: FI-1; Oct 14: FI-1; Oct 15: FI-1; Oct 16: FI-1; Oct 17: FI-1; Oct 18: FI-1; Oct 19: FI-1; Oct 20: FI-1; Oct 21: FI-1; Oct 22: FI-1; Oct 23: FI-1; Oct 24: FI-1; Oct 25: FI-1; Oct 26: FI-1; Oct 27: FI-1; Oct 28: FI-1; Oct 29: FI-1; Oct 30: FI-1; Oct 31: FI-1; Nov 01: FI-1; Nov 02: FI-1; Nov 03: FI-1; Nov 04: FI-1; Nov 05: FI-1; Nov 06: FI-1; Nov 07: FI-1; Nov 08: FI-1; Nov 09: FI-1; Nov 10: FI-1; Nov 11: FI-1; Nov 12: FI-1; Nov 13: FI-1; Nov 14: FI-1; Nov 15: FI-1; Nov 16: FI-1; Nov 17: FI-1; Nov 18: FI-1; Nov 19: FI-1; Nov 20: FI-1; Nov 21: FI-1; Nov 22: FI-1; Nov 23: FI-1; Nov 24: FI-1; Nov 25: FI-1; Nov 26: FI-1; Nov 27: FI-1; Nov 28: FI-1; Nov 29: FI-1; Nov 30: FI-1; Dec 01: FI-1; Dec 02: FI-1; Dec 03: FI-1; Dec 04: FI-1; Dec 05: FI-1; Dec 06: FI-1; Dec 07: FI-1; Dec 08: FI-1; Dec 09: FI-1; Dec 10: FI-1; Dec 11: FI-1; Dec 12: FI-1; Dec 13: FI-1; Dec 14: FI-1; Dec 15: FI-1; Dec 16: FI-1; Dec 17: FI-1; Dec 18: FI-1; Dec 19: FI-1; Dec 20: FI-1; Dec 21: FI-1; Dec 22: FI-1; Dec 23: FI-1; Dec 24: FI-1; Dec 25: FI-1; Dec 26: FI-1; Dec 27: FI-1; Dec 28: FI-1; Dec 29: FI-1; Dec 30: FI-1; Dec 31: FI-1; Jan 01: FI-1; Jan 02: FI-1; Jan 03: FI-1; Jan 04: FI-1; Jan 05: FI-1; Jan 06: FI-1; Jan 07: FI-1; Jan 08: FI-1; Jan 09: FI-1; Jan 10: FI-1; Jan 11: FI-1; Jan 12: FI-1; Jan 13: FI-1; Jan 14: FI-1; Jan 15: FI-1; Jan 16: FI-1; Jan 17: FI-1; Jan 18: FI-1; Jan 19: FI-1; Jan 20: FI-1; Jan 21: FI-1; Jan 22: FI-1; Jan 23: FI-1; Jan 24: FI-1; Jan 25: FI-1; Jan 26: FI-1; Jan 27: FI-1; Jan 28: FI-1; Jan 29: FI-1; Jan 30: FI-1; Jan 31: FI-1; Feb 01: FI-1; Feb 02: FI-1; Feb 03: FI-1; Feb 04: FI-1
| Finishes - Zone 7B | Feb 20: FI-1; Feb 21: FI-1; Feb 22: FI-1; Feb 23: FI-1; Feb 24: FI-1; Feb 25: FI-1; Feb 26: FI-1; Feb 27: FI-1; Feb 28: FI-1; Mar 01: FI-1; Mar 02: FI-1; Mar 03: FI-1; Mar 04: FI-1; Mar 05: FI-1; Mar 06: FI-1; Mar 07: FI-1; Mar 08: FI-1; Mar 09: FI-1; Mar 10: FI-1; Mar 11: FI-1; Mar 12: FI-1; Mar 13: FI-1; Mar 14: FI-1; Mar 15: FI-1; Mar 16: FI-1; Mar 17: FI-1; Mar 18: FI-1; Mar 19: FI-1; Mar 20: FI-1; Mar 21: FI-1; Mar 22: FI-1; Mar 23: FI-1; Mar 24: FI-1; Mar 25: FI-1; Mar 26: FI-1; Mar 27: FI-1; Mar 28: FI-1; Mar 29: FI-1; Mar 30: FI-1; Mar 31: FI-1; Apr 01: FI-1; Apr 02: FI-1; Apr 03: FI-1; Apr 04: FI-1; Apr 05: FI-1; Apr 06: FI-1; Apr 07: FI-1; Apr 08: FI-1; Apr 09: FI-1; Apr 10: FI-1; Apr 11: FI-1; Apr 12: FI-1; Apr 13: FI-1; Apr 14: FI-1; Apr 15: FI-1; Apr 16: FI-1; Apr 17: FI-1; Apr 18: FI-1; Apr 19: FI-1; Apr 20: FI-1; Apr 21: FI-1; Apr 22: FI-1; Apr 23: FI-1; Apr 24: FI-1; Apr 25: FI-1; Apr 26: FI-1; Apr 27: FI-1; Apr 28: FI-1; Apr 29: FI-1; Apr 30: FI-1; May 01: FI-1; May 02: FI-1; May 03: FI-1; May 04: FI-1; May 05: FI-1; May 06: FI-1; May 07: FI-1; May 08: FI-1; May 09: FI-1; May 10: FI-1; May 11: FI-1; May 12: FI-1; May 13: FI-1; May 14: FI-1; May 15: FI-1; May 16: FI-1; May 17: FI-1; May 18: FI-1; May 19: FI-1; May 20: FI-1; May 21: FI-1; May 22: FI-1; May 23: FI-1; May 24: FI-1; May 25: FI-1; May 26: FI-1; May 27: FI-1; May 28: FI-1; May 29: FI-1; May 30: FI-1; May 31: FI-1; Jun 01: FI-1; Jun 02: FI-1; Jun 03: FI-1; Jun 04: FI-1; Jun 05: FI-1; Jun 06: FI-1; Jun 07: FI-1; Jun 08: FI-1; Jun 09: FI-1; Jun 10: FI-1; Jun 11: FI-1; Jun 12: FI-1; Jun 13: FI-1; Jun 14: FI-1; Jun 15: FI-1; Jun 16: FI-1; Jun 17: FI-1; Jun 18: FI-1; Jun 19: FI-1; Jun 20: FI-1; Jun 21: FI-1; Jun 22: FI-1; Jun 23: FI-1; Jun 24: FI-1; Jun 25: FI-1; Jun 26: FI-1; Jun 27: FI-1; Jun 28: FI-1; Jun 29: FI-1; Jun 30: FI-1; Jul 01: FI-1; Jul 02: FI-1; Jul 03: FI-1; Jul 04: FI-1; Jul 05: FI-1; Jul 06: FI-1; Jul 07: FI-1; Jul 08: FI-1; Jul 09: FI-1; Jul 10: FI-1; Jul 11: FI-1; Jul 12: FI-1; Jul 13: FI-1; Jul 14: FI-1; Jul 15: FI-1; Jul 16: FI-1; Jul 17: FI-1; Jul 18: FI-1; Jul 19: FI-1; Jul 20: FI-1; Jul 21: FI-1; Jul 22: FI-1; Jul 23: FI-1; Jul 24: FI-1; Jul 25: FI-1; Jul 26: FI-1; Jul 27: FI-1; Jul 28: FI-1; Jul 29: FI-1; Jul 30: FI-1; Jul 31: FI-1; Aug 01: FI-1; Aug 02: FI-1; Aug 03: FI-1; Aug 04: FI-1; Aug 05: FI-1; Aug 06: FI-1; Aug 07: FI-1; Aug 08: FI-1; Aug 09: FI-1; Aug 10: FI-1; Aug 11: FI-1
| Rough-In - Mechanical Room | Sep 29: M-9; Sep 30: M-9; Oct 01: M-9; Oct 02: M-9; Oct 03: M-9; Jun 15: M-6; Jun 16: M-6; Jun 17: M-6; Jun 18: M-6; Jun 19: M-6; Jun 20: M-6; Jun 21: M-6; Jun 22: M-6; Jun 23: M-6; Jun 24: M-6; Jun 25: M-6; Jun 26: M-6; Jun 29: M-12; Jun 30: M-12; Jul 01: M-12; Jul 02: M-12; Jul 03: M-12; Jul 04: M-12; Jul 05: M-12; Jul 06: M-12; Jul 07: M-12; Jul 08: M-12; Jul 09: M-12; Jul 10: M-12; Jul 11: M-12; Jul 12: M-12; Jul 13: M-12; Jul 14: M-12; Jul 15: M-12; Jul 16: M-12; Jul 17: M-12; Jul 18: M-12; Jul 19: M-12; Jul 20: M-12; Jul 21: M-14; Jul 22: M-14; Jul 23: M-14; Jul 24: M-14; Jul 25: M-14; Jul 26: M-14; Jul 27: M-14; Jul 28: M-14; Jul 29: M-14; Jul 30: M-14; Jul 31: M-14; Aug 01: M-14; Aug 02: M-14; Aug 03: M-14; Aug 04: M-14; Aug 05: M-14; Aug 06: M-14; Aug 07: M-14; Aug 08: M-14; Aug 09: M-14; Aug 10: M-14; Aug 11: M-14; Aug 12: M-14; Aug 13: M-14; Aug 14: M-14; Aug 15: M-14; Aug 16: M-14; Aug 17: M-14
[651 empty] | M-7 | M-7 | M-7 | M-7 | M-7 | M-7 | M-7 | M-7 | M-7 | M-7 | M-7 | M-7 |  |  | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13 | M-13
[651 empty] | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1 | E-1
| Rough-In - Zone 1 | Apr 02: M-5; Apr 03: M-5; Apr 04: M-5; Apr 05: M-5; Apr 06: M-5; Apr 07: M-5; Apr 08: M-5; Apr 09: M-5; Apr 17: MEP-1; Apr 18: MEP-1; Apr 19: MEP-1; Apr 20: MEP-1; Apr 21: MEP-1; Apr 22: MEP-1; Apr 23: MEP-1; Apr 24: MEP-1; Apr 25: MEP-1; Apr 26: MEP-1; Apr 27: MEP-1; Apr 28: MEP-1; Apr 29: MEP-1; Apr 30: MEP-1; May 01: MEP-1; May 02: MEP-1; May 03: MEP-1; May 04: MEP-1; May 05: MEP-1; May 06: MEP-1; May 07: MEP-1; May 08: MEP-1; May 09: MEP-1; May 10: MEP-1; May 11: MEP-1; May 12: MEP-1; May 13: MEP-1; May 14: MEP-1; May 15: IN-2
[592 empty] | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | IN-3
| Rough-In - Zone 2 | Apr 10: M-5; Apr 11: M-5; Apr 12: M-5; Apr 13: M-5; Apr 14: M-5; Apr 15: M-5; Apr 16: M-5; May 01: MEP-1; May 02: MEP-1; May 03: MEP-1; May 04: MEP-1; May 05: MEP-1; May 06: MEP-1; May 07: MEP-1; May 08: MEP-1; May 09: MEP-1; May 10: MEP-1; May 11: MEP-1; May 12: MEP-1; May 13: MEP-1; May 14: MEP-1; May 15: MEP-1; May 16: MEP-1; May 17: MEP-1; May 18: MEP-1; May 19: MEP-1; May 20: MEP-1; May 21: MEP-1; May 22: MEP-1; May 23: MEP-1; May 24: MEP-1; May 25: MEP-1; May 26: MEP-1; May 27: MEP-1; May 28: MEP-1; May 29: MEP-1; Jun 01: IN-2
[606 empty] | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 |  |  | IN-3
| Rough-In - Zone 3 | Apr 17: M-5; Apr 18: M-5; Apr 19: M-5; Apr 20: M-5; Apr 21: M-5; Apr 22: M-5; Apr 23: M-5; May 15: MEP-1; May 16: MEP-1; May 17: MEP-1; May 18: MEP-1; May 19: MEP-1; May 20: MEP-1; May 21: MEP-1; May 22: MEP-1; May 23: MEP-1; May 24: MEP-1; May 25: MEP-1; May 26: MEP-1; May 27: MEP-1; May 28: MEP-1; May 29: MEP-1; May 30: MEP-1; May 31: MEP-1; Jun 01: MEP-1; Jun 02: MEP-1; Jun 03: MEP-1; Jun 04: MEP-1; Jun 05: MEP-1; Jun 06: MEP-1; Jun 07: MEP-1; Jun 08: MEP-1; Jun 09: MEP-1; Jun 10: MEP-1; Jun 11: MEP-1; Jun 12: MEP-1; Jun 15: IN-2
[620 empty] | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 |  |  | IN-3
| Rough-In - Zone 4 | Apr 24: M-5; Apr 25: M-5; Apr 26: M-5; Apr 27: M-5; Apr 28: M-5; Apr 29: M-5; Apr 30: M-5; May 01: M-5; Jun 01: MEP-1; Jun 02: MEP-1; Jun 03: MEP-1; Jun 04: MEP-1; Jun 05: MEP-1; Jun 06: MEP-1; Jun 07: MEP-1; Jun 08: MEP-1; Jun 09: MEP-1; Jun 10: MEP-1; Jun 11: MEP-1; Jun 12: MEP-1; Jun 13: MEP-1; Jun 14: MEP-1; Jun 15: MEP-1; Jun 16: MEP-1; Jun 17: MEP-1; Jun 18: MEP-1; Jun 19: MEP-1; Jun 20: MEP-1; Jun 21: MEP-1; Jun 22: MEP-1; Jun 23: MEP-1; Jun 24: MEP-1; Jun 25: MEP-1; Jun 26: MEP-1; Jun 29: IN-2
[637 empty] | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 |  |  | IN-3
| Rough-In - Zone 5 | May 04: M-5; May 05: M-5; May 06: M-5; May 07: M-5; May 08: M-5; Jun 15: MEP-1; Jun 16: MEP-1; Jun 17: MEP-1; Jun 18: MEP-1; Jun 19: MEP-1; Jun 20: MEP-1; Jun 21: MEP-1; Jun 22: MEP-1; Jun 23: MEP-1; Jun 24: MEP-1; Jun 25: MEP-1; Jun 26: MEP-1; Jun 27: MEP-1; Jun 28: MEP-1; Jun 29: MEP-1; Jun 30: MEP-1; Jul 01: MEP-1; Jul 02: MEP-1; Jul 03: MEP-1; Jul 04: MEP-1; Jul 05: MEP-1; Jul 06: MEP-1; Jul 07: MEP-1; Jul 08: MEP-1; Jul 09: MEP-1; Jul 10: MEP-1; Jul 11: MEP-1; Jul 12: MEP-1; Jul 13: MEP-1; Jul 14: IN-2
[651 empty] | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | IN-3
| Rough-In - Zone 6 | May 11: M-5; May 12: M-5; May 13: M-5; May 14: M-5; May 15: M-5; Jun 29: MEP-1; Jun 30: MEP-1; Jul 01: MEP-1; Jul 02: MEP-1; Jul 03: MEP-1; Jul 04: MEP-1; Jul 05: MEP-1; Jul 06: MEP-1; Jul 07: MEP-1; Jul 08: MEP-1; Jul 09: MEP-1; Jul 10: MEP-1; Jul 11: MEP-1; Jul 12: MEP-1; Jul 13: MEP-1; Jul 14: MEP-1; Jul 15: MEP-1; Jul 16: MEP-1; Jul 17: MEP-1; Jul 18: MEP-1; Jul 19: MEP-1; Jul 20: MEP-1; Jul 21: MEP-1; Jul 22: MEP-1; Jul 23: MEP-1; Jul 24: MEP-1; Jul 25: MEP-1; Jul 26: MEP-1; Jul 27: MEP-1; Jul 28: IN-2
[665 empty] | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | IN-3
| Testing | Apr 10: E-3; Apr 11: E-3; Apr 12: E-3; Apr 13: E-3; Apr 14: E-3; Apr 15: E-3; Apr 16: E-3; Apr 17: E-3; Apr 18: E-3; Apr 19: E-3; Apr 20: E-3; Apr 21: E-3; Apr 22: E-3; Apr 23: E-3; Apr 24: E-3; Apr 25: E-3; Apr 26: E-3; Apr 27: E-3; Apr 28: E-3; Apr 29: E-3; Apr 30: E-3; May 01: E-3; May 02: E-3; May 03: E-3; May 04: E-3; May 05: E-3; May 06: E-3; May 07: E-3; May 08: E-3; May 09: E-3; May 10: E-3; May 11: E-3; May 12: E-3; May 13: E-3; May 14: E-3; May 15: E-3; May 16: E-3; May 17: E-3; May 18: E-3; May 19: E-3; May 20: E-3; May 21: E-3; May 22: E-3; May 23: E-3; May 24: E-3; May 25: E-3; May 26: E-3; May 27: E-3; May 28: E-3; May 29: E-3; May 30: E-3; May 31: E-3; Jun 01: E-3; Jun 02: E-3; Jun 03: E-3; Jun 04: E-3; Jun 05: E-3; Jun 06: E-3; Jun 07: E-3; Jun 08: E-3; Jun 09: E-3; Jun 10: E-3; Jun 11: E-3; Jun 12: E-3; Jun 13: E-3; Jun 14: E-3; Jun 15: E-3; Jun 16: E-3; Jun 17: E-3; Jun 18: E-3; Jun 19: E-3; Jun 20: E-3; Jun 21: E-3; Jun 22: E-3; Jun 23: E-3; Jun 24: E-3; Jun 25: E-3; Jun 26: E-3; Jun 27: E-3; Jun 28: E-3; Jun 29: E-3; Jun 30: E-3; Jul 01: E-3; Jul 02: E-3; Jul 03: E-3; Jul 04: E-3; Jul 05: E-3; Jul 06: E-3; Jul 07: E-3; Jul 08: E-3; Jul 09: E-3; Jul 10: E-3; Jul 11: E-3; Jul 12: E-3; Jul 13: E-3; Jul 14: E-3; Jul 15: E-3; Jul 16: E-3; Jul 17: E-3; Jul 18: E-3; Jul 19: E-3; Jul 20: E-3; Jul 21: E-3; Jul 22: E-3; Jul 23: E-3; Jul 24: E-3; Jul 25: E-3; Jul 26: E-3; Jul 27: E-3; Jul 28: E-3; Jul 29: E-3; Jul 30: E-3; Jul 31: E-3; Aug 01: E-3; Aug 02: E-3; Aug 03: E-3; Aug 04: E-3; Aug 05: E-3; Aug 06: E-3; Aug 07: E-3; Aug 08: E-3; Aug 09: E-3; Aug 10: E-3; Aug 11: E-3; Aug 12: E-3; Aug 13: E-3; Aug 14: E-3; Aug 15: E-3; Aug 16: E-3; Aug 17: E-3; Aug 18: E-3; Aug 19: E-3; Aug 20: E-3; Aug 21: E-3; Aug 22: E-3; Aug 23: E-3; Aug 24: E-3; Aug 25: E-3; Aug 26: E-3; Aug 27: E-3; Aug 28: E-3; Aug 29: E-3; Aug 30: E-3; Aug 31: E-3; Sep 01: E-3; Sep 02: E-3; Sep 03: E-3; Sep 04: E-3; Sep 05: E-3; Sep 06: E-3; Sep 07: E-3; Sep 08: E-3; Sep 09: E-3; Sep 10: E-3; Sep 11: E-3; Sep 12: E-3; Sep 13: E-3; Sep 14: E-3; Sep 15: E-3; Sep 16: E-3; Sep 17: E-3; Sep 18: E-3; Sep 19: E-3; Sep 20: E-3; Sep 21: E-3; Sep 22: E-3; Sep 23: E-3; Sep 24: E-3; Sep 25: E-3; Sep 26: E-3; Sep 27: E-3; Sep 28: E-3; Sep 29: E-3; Apr 09: OW-1; Apr 10: OW-1; Apr 11: OW-1; Apr 12: OW-1; Apr 13: OW-1; Apr 14: OW-1; Apr 15: OW-1; Apr 16: OW-1; Apr 17: OW-1; Apr 18: OW-1; Apr 19: OW-1; Apr 20: OW-1; Apr 21: OW-1; Apr 22: OW-1; Apr 23: OW-1; Apr 24: OW-1; Apr 25: OW-1; Apr 26: OW-1; Apr 27: OW-1; Apr 28: OW-1; Apr 29: OW-1; Apr 30: OW-1; May 01: OW-1; May 02: OW-1; May 03: OW-1; May 04: OW-1; May 05: OW-1; May 06: OW-1; May 07: OW-1; May 08: OW-1; May 09: OW-1; May 10: OW-1; May 11: OW-1; May 12: OW-1; May 13: OW-1; May 14: OW-1; May 15: OW-1; May 16: OW-1; May 17: OW-1; May 18: OW-1; May 19: OW-1; May 20: OW-1; May 21: OW-1; May 22: OW-1; May 23: OW-1; May 24: OW-1; May 25: OW-1; May 26: OW-1; May 27: OW-1; May 28: OW-1; May 29: OW-1; May 30: OW-1; May 31: OW-1; Jun 01: OW-1; Jun 02: OW-1; Jun 03: OW-1; Jun 04: OW-1; Jun 05: OW-1; Jun 06: OW-1; Jun 07: OW-1; Jun 08: OW-1; Jun 09: OW-1; Jun 10: OW-1; Jun 11: OW-1; Jun 12: OW-1; Jun 13: OW-1; Jun 14: OW-1; Jun 15: OW-1; Jun 16: OW-1; Jun 17: OW-1; Jun 18: OW-1; Jun 19: OW-1; Jun 20: OW-1; Jun 21: OW-1; Jun 22: OW-1; Jun 23: OW-1; Jun 24: OW-1; Jun 25: OW-1; Jun 26: OW-1; Jun 27: OW-1; Jun 28: OW-1; Jun 29: OW-1; Jun 30: OW-1; Jul 01: OW-1; Jul 02: OW-1
[722 empty] | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2
| Weather Days | Sep 25: CX-3; Sep 26: CX-3; Sep 27: CX-3; Sep 28: CX-3; Sep 29: CX-3; Sep 30: CX-3; Oct 01: CX-3; Oct 02: CX-3; Oct 03: CX-3; Oct 04: CX-3; Oct 05: CX-3; Oct 06: CX-3; Oct 07: CX-3; Oct 08: CX-3; Oct 09: CX-3; Oct 10: CX-3; Oct 11: CX-3; Oct 12: CX-3; Oct 13: CX-3; Oct 14: CX-3; Oct 15: CX-3; Oct 16: CX-3; Oct 17: CX-3; Oct 18: CX-3; Oct 19: CX-3; Oct 20: CX-3; Oct 21: CX-3; Oct 22: CX-3; Oct 23: CX-3; Oct 24: CX-3; Oct 25: CX-3; Oct 26: CX-3; Oct 27: CX-3; Oct 28: CX-3; Oct 29: CX-3; Oct 30: CX-3; Oct 31: CX-3; Nov 01: CX-3; Nov 02: CX-3; Nov 03: CX-3; Nov 04: CX-3; Nov 05: CX-3; Nov 06: CX-3; Nov 07: CX-3; Nov 08: CX-3; Nov 09: CX-3; Nov 10: CX-3; Nov 11: CX-3; Nov 12: CX-3; Nov 13: CX-3; Nov 14: CX-3; Nov 15: CX-3; Nov 16: CX-3; Nov 17: CX-3; Nov 18: CX-3; Nov 19: CX-3; Nov 20: CX-3; Nov 21: CX-3; Nov 22: CX-3; Nov 23: CX-3; Nov 24: CX-3; Nov 25: CX-3; Nov 26: CX-3; Nov 27: CX-3; Nov 28: CX-3; Nov 29: CX-3; Nov 30: CX-3; Dec 01: CX-3; Dec 02: CX-3; Dec 03: CX-3; Dec 04: CX-3; Dec 05: CX-3; Dec 06: CX-3; Dec 07: CX-3; Dec 08: CX-3; Dec 09: CX-3; Dec 10: CX-3; Dec 11: CX-3; Dec 12: CX-3; Dec 13: CX-3; Dec 14: CX-3; Dec 15: CX-3; Dec 16: CX-3; Dec 17: CX-3; Dec 18: CX-3; Dec 19: CX-3; Dec 20: CX-3; Dec 21: CX-3; Dec 22: CX-3; Dec 23: CX-3; Dec 24: CX-3; Dec 25: CX-3; Dec 26: CX-3; Dec 27: CX-3; Dec 28: CX-3; Dec 29: CX-3; Dec 30: CX-3; Dec 31: CX-3; Jan 01: CX-3; Jan 02: CX-3; Jan 03: CX-3; Jan 04: CX-3
Structure | Above Grade Structures- Zone 1 | Oct 06: STRUC-2; Oct 07: STRUC-2; Oct 08: STRUC-2; Oct 09: STRUC-2; Oct 10: STRUC-2; Oct 11: STRUC-2; Oct 12: STRUC-2; Oct 13: STRUC-2; Oct 14: STRUC-2; Oct 15: STRUC-2; Oct 16: STRUC-2; Oct 17: STRUC-2
| Above Grade Structures- Zone 2 | Oct 20: STRUC-2; Oct 21: STRUC-2; Oct 22: STRUC-2; Oct 23: STRUC-2; Oct 24: STRUC-2; Oct 25: STRUC-2; Oct 26: STRUC-2; Oct 27: STRUC-2; Oct 28: STRUC-2; Oct 29: STRUC-2; Oct 30: STRUC-2; Oct 31: STRUC-2
| Above Grade Structures- Zone 3 | Nov 03: STRUC-2; Nov 04: STRUC-2; Nov 05: STRUC-2; Nov 06: STRUC-2; Nov 07: STRUC-2; Nov 08: STRUC-2; Nov 09: STRUC-2; Nov 10: STRUC-2; Nov 11: STRUC-2; Nov 12: STRUC-2; Nov 13: STRUC-2; Nov 14: STRUC-2
| Above Grade Structures- Zone 4 | Nov 17: STRUC-2; Nov 18: STRUC-2; Nov 19: STRUC-2; Nov 20: STRUC-2; Nov 21: STRUC-2; Nov 22: STRUC-2; Nov 23: STRUC-2; Nov 24: STRUC-2; Nov 25: STRUC-2; Nov 26: STRUC-2; Nov 27: STRUC-2; Nov 28: STRUC-2; Nov 29: STRUC-2; Nov 30: STRUC-2; Dec 01: STRUC-2; Dec 02: STRUC-2
| Above Grade Structures- Zone 5 | Dec 03: STRUC-2; Dec 04: STRUC-2; Dec 05: STRUC-2; Dec 06: STRUC-2; Dec 07: STRUC-2; Dec 08: STRUC-2; Dec 09: STRUC-2; Dec 10: STRUC-2; Dec 11: STRUC-2; Dec 12: STRUC-2; Dec 13: STRUC-2; Dec 14: STRUC-2; Dec 15: STRUC-2; Dec 16: STRUC-2
| Above Grade Structures- Zone 6 | Dec 17: STRUC-2; Dec 18: STRUC-2; Dec 19: STRUC-2; Dec 20: STRUC-2; Dec 21: STRUC-2; Dec 22: STRUC-2; Dec 23: STRUC-2; Dec 24: STRUC-2; Dec 25: STRUC-2; Dec 26: STRUC-2; Dec 27: STRUC-2; Dec 28: STRUC-2; Dec 29: STRUC-2; Dec 30: STRUC-2; Dec 31: STRUC-2; Jan 01: STRUC-2; Jan 02: STRUC-2; Jan 03: STRUC-2; Jan 04: STRUC-2; Jan 05: STRUC-2; Jan 06: STRUC-2; Jan 07: STRUC-2
Sitework | Clear & Grub | Apr 17: SITE-1; Apr 18: SITE-1; Apr 19: SITE-1; Apr 20: SITE-1; Apr 21: SITE-1; Apr 22: SITE-1; Apr 23: SITE-1; Apr 24: SITE-1; Apr 25: SITE-1; Apr 26: SITE-1; Apr 27: SITE-1; Apr 28: SITE-1; Apr 29: SITE-1; Apr 30: SITE-1; May 01: SITE-1; May 02: SITE-1; May 03: SITE-1; May 04: SITE-1; May 05: SITE-1; May 06: SITE-1; May 07: SITE-1; May 08: SITE-1; May 09: SITE-1; May 10: SITE-1; May 11: SITE-1; May 12: SITE-1; May 13: SITE-1; May 14: SITE-1; May 15: SITE-1; May 16: SITE-1; May 17: SITE-1; May 18: SITE-1; May 19: SITE-1; May 20: SITE-1; May 21: SITE-1; May 22: SITE-1
| Excavation | May 23: SITE-2; May 24: SITE-2; May 25: SITE-2; May 26: SITE-2; May 27: SITE-2; May 28: SITE-2; May 29: SITE-2; May 30: SITE-2; May 31: SITE-2; Jun 01: SITE-2; Jun 02: SITE-2; Jun 03: SITE-2; Jun 04: SITE-2; Jun 05: SITE-2; Jun 06: SITE-2; Jun 07: SITE-2; Jun 08: SITE-2; Jun 09: SITE-2; Jun 10: SITE-2; Jun 11: SITE-2; Jun 12: SITE-2; Jun 13: SITE-2; Jun 14: SITE-2; Jun 15: SITE-2; Jun 16: SITE-2; Jun 17: SITE-2; Jun 18: SITE-2; Jun 19: SITE-2; Jun 20: SITE-2; Jun 21: SITE-2; Jun 22: SITE-2; Jun 23: SITE-2; Jun 24: SITE-2; Jun 25: SITE-2; Jun 26: SITE-2; Jun 27: SITE-2; Jun 28: SITE-2; Jun 29: SITE-2; Jun 30: SITE-2; Jul 01: SITE-2; Jul 02: SITE-2; Jul 03: SITE-2; Jul 04: SITE-2; Jul 05: SITE-2; Jul 06: SITE-2; Jul 07: SITE-2; Jul 08: SITE-2; Jul 09: SITE-2; Jul 10: SITE-2; Jul 11: SITE-2; Jul 12: SITE-2; Jul 13: SITE-2; Jul 14: SITE-2; Jul 15: SITE-2; Jul 16: SITE-2; Jul 17: SITE-2; Jul 18: SITE-2; Jul 19: SITE-2; Jul 20: SITE-2; Jul 21: SITE-2; Jul 22: SITE-2; Jul 23: SITE-2; Jul 24: SITE-2; Jul 25: SITE-2; Jul 26: SITE-2; Jul 27: SITE-2; Jul 28: SITE-2
| Hardscape/Landscaping | Jul 06: SITE-5; Jul 07: SITE-5; Jul 08: SITE-5; Jul 09: SITE-5; Jul 10: SITE-5; Jul 11: SITE-5; Jul 12: SITE-5; Jul 13: SITE-5; Jul 14: SITE-5; Jul 15: SITE-5; Jul 16: SITE-5; Jul 17: SITE-5; Jul 18: SITE-5; Jul 19: SITE-5; Jul 20: SITE-5; Jul 21: SITE-5; Jul 22: SITE-5; Jul 23: SITE-5; Jul 24: SITE-5; Jul 25: SITE-5; Jul 26: SITE-5; Jul 27: SITE-5; Jul 28: SITE-5; Jul 29: SITE-5; Jul 30: SITE-5; Jul 31: SITE-5; Aug 01: SITE-5; Aug 02: SITE-5; Aug 03: SITE-5; Aug 04: SITE-5; Aug 05: SITE-5; Aug 06: SITE-5; Aug 07: SITE-5; Aug 08: SITE-5; Aug 09: SITE-5; Aug 10: SITE-5; Aug 11: SITE-5; Aug 12: SITE-5; Aug 13: SITE-5; Aug 14: SITE-5; Aug 15: SITE-5; Aug 16: SITE-5; Aug 17: SITE-5; Aug 18: SITE-5; Aug 19: SITE-5; Aug 20: SITE-5; Aug 21: SITE-5; Aug 22: SITE-5; Aug 23: SITE-5; Aug 24: SITE-5; Aug 25: SITE-5; Aug 26: SITE-5; Aug 27: SITE-5; Aug 28: SITE-5; Aug 29: SITE-5; Aug 30: SITE-5; Aug 31: SITE-5; Sep 01: SITE-5; Sep 02: SITE-5; Sep 03: SITE-5; Sep 04: SITE-5; Sep 05: SITE-5; Sep 06: SITE-5; Sep 07: SITE-5; Sep 08: SITE-5; Sep 09: SITE-5; Sep 10: SITE-5; Sep 11: SITE-5; Sep 12: SITE-5; Sep 13: SITE-5; Sep 14: SITE-5; Sep 15: SITE-5; Sep 16: SITE-5; Sep 17: SITE-5; Sep 18: SITE-5; Sep 19: SITE-5; Sep 20: SITE-5; Sep 21: SITE-5; Sep 22: SITE-5; Sep 23: SITE-5; Sep 24: SITE-5; Sep 25: SITE-5; Sep 26: SITE-5; Sep 27: SITE-5; Sep 28: SITE-5; Sep 29: SITE-5; Sep 30: SITE-5; Oct 01: SITE-5; Oct 02: SITE-5; Oct 03: SITE-5; Oct 04: SITE-5; Oct 05: SITE-5; Oct 06: SITE-5; Oct 07: SITE-5; Oct 08: SITE-5; Oct 09: SITE-5; Oct 10: SITE-5; Oct 11: SITE-5; Oct 12: SITE-5; Oct 13: SITE-5; Oct 14: SITE-5; Oct 15: SITE-5; Oct 16: SITE-5; Oct 17: SITE-5; Oct 18: SITE-5; Oct 19: SITE-5; Oct 20: SITE-5; Oct 21: SITE-5; Oct 22: SITE-5; Oct 23: SITE-5; Oct 24: SITE-5; Oct 25: SITE-5; Oct 26: SITE-5; Oct 27: SITE-5; Oct 28: SITE-5; Oct 29: SITE-5; Oct 30: SITE-5; Oct 31: SITE-5; Nov 01: SITE-5; Nov 02: SITE-5; Nov 03: SITE-5; Nov 04: SITE-5; Nov 05: SITE-5; Nov 06: SITE-5; Nov 07: SITE-5; Nov 08: SITE-5; Nov 09: SITE-5; Nov 10: SITE-5; Nov 11: SITE-5; Nov 12: SITE-5; Nov 13: SITE-5; Nov 14: SITE-5; Nov 15: SITE-5; Nov 16: SITE-5; Nov 17: SITE-5; Nov 18: SITE-5; Nov 19: SITE-5; Nov 20: SITE-5; Nov 21: SITE-5; Nov 22: SITE-5; Nov 23: SITE-5; Nov 24: SITE-5; Nov 25: SITE-5; Nov 26: SITE-5; Nov 27: SITE-5; Nov 28: SITE-5; Nov 29: SITE-5; Nov 30: SITE-5; Dec 01: SITE-5; Dec 02: SITE-5; Dec 03: SITE-5; Dec 04: SITE-5; Dec 05: SITE-5; Dec 06: SITE-5; Dec 07: SITE-5; Dec 08: SITE-5; Dec 09: SITE-5; Dec 10: SITE-5; Dec 11: SITE-5; Dec 12: SITE-5; Dec 13: SITE-5; Dec 14: SITE-5; Dec 15: SITE-5; Dec 16: SITE-5; Dec 17: SITE-5; Dec 18: SITE-5; Dec 19: SITE-5; Dec 20: SITE-5; Dec 21: SITE-5; Dec 22: SITE-5; Dec 23: SITE-5
| Site Paving | May 23: SITE-4; May 24: SITE-4; May 25: SITE-4; May 26: SITE-4; May 27: SITE-4; May 28: SITE-4; May 29: SITE-4; May 30: SITE-4; May 31: SITE-4; Jun 01: SITE-4; Jun 02: SITE-4; Jun 03: SITE-4; Jun 04: SITE-4; Jun 05: SITE-4; Jun 06: SITE-4; Jun 07: SITE-4; Jun 08: SITE-4; Jun 09: SITE-4; Jun 10: SITE-4; Jun 11: SITE-4; Jun 12: SITE-4; Jun 13: SITE-4; Jun 14: SITE-4; Jun 15: SITE-4; Jun 16: SITE-4; Jun 17: SITE-4; Jun 18: SITE-4; Jun 19: SITE-4; Jun 20: SITE-4; Jun 21: SITE-4; Jun 22: SITE-4; Jun 23: SITE-4; Jun 24: SITE-4; Jun 25: SITE-4; Jun 26: SITE-4; Jun 27: SITE-4; Jun 28: SITE-4; Jun 29: SITE-4; Jun 30: SITE-4; Jul 01: SITE-4; Jul 02: SITE-4; Jul 03: SITE-4; Jul 04: SITE-4; Jul 05: SITE-4; Jul 06: SITE-4; Jul 07: SITE-4; Jul 08: SITE-4; Jul 09: SITE-4; Jul 10: SITE-4; Jul 11: SITE-4; Jul 12: SITE-4; Jul 13: SITE-4; Jul 14: SITE-4; Jul 15: SITE-4; Jul 16: SITE-4; Jul 17: SITE-4; Jul 18: SITE-4; Jul 19: SITE-4; Jul 20: SITE-4; Jul 21: SITE-4; Jul 22: SITE-4; Jul 23: SITE-4; Jul 24: SITE-4; Jul 25: SITE-4; Jul 26: SITE-4; Jul 27: SITE-4; Jul 28: SITE-4; Jul 29: SITE-4; Jul 30: SITE-4; Jul 31: SITE-4; Aug 01: SITE-4; Aug 02: SITE-4; Aug 03: SITE-4; Aug 04: SITE-4; Aug 05: SITE-4; Aug 06: SITE-4; Aug 07: SITE-4; Aug 08: SITE-4; Aug 09: SITE-4; Aug 10: SITE-4; Aug 11: SITE-4; Aug 12: SITE-4; Aug 13: SITE-4; Aug 14: SITE-4; Aug 15: SITE-4; Aug 16: SITE-4; Aug 17: SITE-4; Aug 18: SITE-4; Aug 19: SITE-4; Aug 20: SITE-4; Aug 21: SITE-4; Aug 22: SITE-4; Aug 23: SITE-4; Aug 24: SITE-4; Aug 25: SITE-4; Aug 26: SITE-4; Aug 27: SITE-4; Aug 28: SITE-4; Aug 29: SITE-4; Aug 30: SITE-4; Aug 31: SITE-4; Sep 01: SITE-4; Sep 02: SITE-4; Sep 03: SITE-4; Sep 04: SITE-4; Sep 05: SITE-4; Sep 06: SITE-4; Sep 07: SITE-4; Sep 08: SITE-4; Sep 09: SITE-4; Sep 10: SITE-4; Sep 11: SITE-4; Sep 12: SITE-4; Sep 13: SITE-4; Sep 14: SITE-4; Sep 15: SITE-4; Sep 16: SITE-4; Sep 17: SITE-4; Sep 18: SITE-4; Sep 19: SITE-4; Sep 20: SITE-4; Sep 21: SITE-4; Sep 22: SITE-4; Sep 23: SITE-4; Sep 24: SITE-4; Sep 25: SITE-4; Sep 26: SITE-4; Sep 27: SITE-4; Sep 28: SITE-4; Sep 29: SITE-4; Sep 30: SITE-4; Oct 01: SITE-4; Oct 02: SITE-4; Oct 03: SITE-4; Oct 04: SITE-4; Oct 05: SITE-4; Oct 06: SITE-4; Oct 07: SITE-4; Oct 08: SITE-4; Oct 09: SITE-4; Oct 10: SITE-4; Oct 11: SITE-4; Oct 12: SITE-4; Oct 13: SITE-4; Oct 14: SITE-4; Oct 15: SITE-4; Oct 16: SITE-4; Oct 17: SITE-4; Oct 18: SITE-4; Oct 19: SITE-4; Oct 20: SITE-4; Oct 21: SITE-4; Oct 22: SITE-4; Oct 23: SITE-4; Oct 24: SITE-4; Oct 25: SITE-4; Oct 26: SITE-4; Oct 27: SITE-4; Oct 28: SITE-4; Oct 29: SITE-4; Oct 30: SITE-4; Oct 31: SITE-4; Nov 01: SITE-4; Nov 02: SITE-4; Nov 03: SITE-4; Nov 04: SITE-4; Nov 05: SITE-4; Nov 06: SITE-4; Nov 07: SITE-4; Nov 08: SITE-4; Nov 09: SITE-4; Nov 10: SITE-4; Nov 11: SITE-4; Nov 12: SITE-4; Nov 13: SITE-4; Nov 14: SITE-4; Nov 15: SITE-4; Nov 16: SITE-4; Nov 17: SITE-4; Nov 18: SITE-4; Nov 19: SITE-4; Nov 20: SITE-4; Nov 21: SITE-4; Nov 22: SITE-4; Nov 23: SITE-4; Nov 24: SITE-4; Nov 25: SITE-4; Nov 26: SITE-4; Nov 27: SITE-4; Nov 28: SITE-4; Nov 29: SITE-4; Nov 30: SITE-4; Dec 01: SITE-4; Dec 02: SITE-4; Dec 03: SITE-4; Dec 04: SITE-4; Dec 05: SITE-4; Dec 06: SITE-4; Dec 07: SITE-4; Dec 08: SITE-4; Dec 09: SITE-4; Dec 10: SITE-4; Dec 11: SITE-4; Dec 12: SITE-4; Dec 13: SITE-4; Dec 14: SITE-4; Dec 15: SITE-4; Dec 16: SITE-4; Dec 17: SITE-4; Dec 18: SITE-4; Dec 19: SITE-4; Dec 20: SITE-4; Dec 21: SITE-4; Dec 22: SITE-4; Dec 23: SITE-4; Dec 24: SITE-4; Dec 25: SITE-4; Dec 26: SITE-4; Dec 27: SITE-4; Dec 28: SITE-4; Dec 29: SITE-4; Dec 30: SITE-4
| Site Utilities | Apr 03: SITE-3; Apr 04: SITE-3; Apr 05: SITE-3; Apr 06: SITE-3; Apr 07: SITE-3; Apr 08: SITE-3; Apr 09: SITE-3; Apr 10: SITE-3; Apr 11: SITE-3; Apr 12: SITE-3; Apr 13: SITE-3; Apr 14: SITE-3; Apr 15: SITE-3; Apr 16: SITE-3; Apr 17: SITE-3; Apr 18: SITE-3; Apr 19: SITE-3; Apr 20: SITE-3; Apr 21: SITE-3; Apr 22: SITE-3; Apr 23: SITE-3; Apr 24: SITE-3; Apr 25: SITE-3; Apr 26: SITE-3; Apr 27: SITE-3; Apr 28: SITE-3; Apr 29: SITE-3; Apr 30: SITE-3; May 01: SITE-3; May 02: SITE-3; May 03: SITE-3; May 04: SITE-3; May 05: SITE-3; May 06: SITE-3; May 07: SITE-3; May 08: SITE-3; May 09: SITE-3; May 10: SITE-3; May 11: SITE-3; May 12: SITE-3; May 13: SITE-3; May 14: SITE-3; May 15: SITE-3; May 16: SITE-3; May 17: SITE-3; May 18: SITE-3; May 19: SITE-3; May 20: SITE-3; May 21: SITE-3; May 22: SITE-3; May 23: SITE-3; May 24: SITE-3; May 25: SITE-3; May 26: SITE-3; May 27: SITE-3; May 28: SITE-3; May 29: SITE-3; May 30: SITE-3; May 31: SITE-3; Jun 01: SITE-3; Jun 02: SITE-3; Jun 03: SITE-3; Jun 04: SITE-3; Jun 05: SITE-3; Jun 06: SITE-3; Jun 07: SITE-3; Jun 08: SITE-3; Jun 09: SITE-3; Jun 10: SITE-3; Jun 11: SITE-3; Jun 12: SITE-3; Jun 13: SITE-3; Jun 14: SITE-3; Jun 15: SITE-3; Jun 16: SITE-3; Jun 17: SITE-3; Jun 18: SITE-3; Jun 19: SITE-3; Jun 20: SITE-3; Jun 21: SITE-3; Jun 22: SITE-3; Jun 23: SITE-3; Jun 24: SITE-3; Jun 25: SITE-3; Jun 26: SITE-3; Jun 27: SITE-3; Jun 28: SITE-3; Jun 29: SITE-3; Jun 30: SITE-3; Jul 01: SITE-3; Jul 02: SITE-3; Jul 03: SITE-3; Jul 04: SITE-3; Jul 05: SITE-3; Jul 06: SITE-3; Jul 07: SITE-3; Jul 08: SITE-3; Jul 09: SITE-3; Jul 10: SITE-3; Jul 11: SITE-3; Jul 12: SITE-3; Jul 13: SITE-3; Jul 14: SITE-3; Jul 15: SITE-3; Jul 16: SITE-3; Jul 17: SITE-3; Jul 18: SITE-3
Foundations | Slabs - Zone 1 | Sep 15: FOUN-1; Sep 16: FOUN-1; Sep 17: FOUN-1; Sep 18: FOUN-1; Sep 19: FOUN-1; Sep 20: FOUN-1; Sep 21: FOUN-1; Sep 22: FOUN-1; Sep 23: FOUN-1; Sep 24: FOUN-1; Sep 25: FOUN-1; Sep 26: FOUN-1; Sep 27: FOUN-1; Sep 28: FOUN-1; Sep 29: FOUN-1; Sep 30: FOUN-1; Oct 01: FOUN-1; Oct 02: FOUN-1; Oct 03: FOUN-1
| Slabs - Zone 2 | Oct 14: FOUN-1; Oct 15: FOUN-1; Oct 16: FOUN-1; Oct 17: FOUN-1; Oct 18: FOUN-1; Oct 19: FOUN-1; Oct 20: FOUN-1; Oct 21: FOUN-1; Oct 22: FOUN-1; Oct 23: FOUN-1; Oct 24: FOUN-1; Oct 25: FOUN-1; Oct 26: FOUN-1; Oct 27: FOUN-1; Oct 28: FOUN-1; Oct 29: FOUN-1; Oct 30: FOUN-1; Oct 31: FOUN-1; Nov 01: FOUN-1; Nov 02: FOUN-1; Nov 03: FOUN-1
| Slabs - Zone 3 | Nov 11: FOUN-1; Nov 12: FOUN-1; Nov 13: FOUN-1; Nov 14: FOUN-1; Nov 15: FOUN-1; Nov 16: FOUN-1; Nov 17: FOUN-1; Nov 18: FOUN-1; Nov 19: FOUN-1; Nov 20: FOUN-1; Nov 21: FOUN-1; Nov 22: FOUN-1; Nov 23: FOUN-1; Nov 24: FOUN-1
| Slabs - Zone 4 | Dec 11: FOUN-1; Dec 12: FOUN-1; Dec 13: FOUN-1; Dec 14: FOUN-1; Dec 15: FOUN-1; Dec 16: FOUN-1; Dec 17: FOUN-1; Dec 18: FOUN-1; Dec 19: FOUN-1; Dec 20: FOUN-1; Dec 21: FOUN-1; Dec 22: FOUN-1; Dec 23: FOUN-1; Dec 24: FOUN-1; Dec 25: FOUN-1; Dec 26: FOUN-1; Dec 27: FOUN-1; Dec 28: FOUN-1; Dec 29: FOUN-1
| Slabs - Zone 5 | Jan 30: FOUN-1; Jan 31: FOUN-1; Feb 01: FOUN-1; Feb 02: FOUN-1; Feb 03: FOUN-1; Feb 04: FOUN-1; Feb 05: FOUN-1; Feb 06: FOUN-1; Feb 07: FOUN-1; Feb 08: FOUN-1; Feb 09: FOUN-1; Feb 10: FOUN-1; Feb 11: FOUN-1; Feb 12: FOUN-1; Feb 13: FOUN-1; Feb 14: FOUN-1; Feb 15: FOUN-1; Feb 16: FOUN-1; Feb 17: FOUN-1; Feb 18: FOUN-1; Feb 19: FOUN-1
| Slabs - Zone 6 | Mar 13: FOUN-1; Mar 14: FOUN-1; Mar 15: FOUN-1; Mar 16: FOUN-1; Mar 17: FOUN-1; Mar 18: FOUN-1; Mar 19: FOUN-1; Mar 20: FOUN-1; Mar 21: FOUN-1; Mar 22: FOUN-1; Mar 23: FOUN-1; Mar 24: FOUN-1; Mar 25: FOUN-1; Mar 26: FOUN-1; Mar 27: FOUN-1; Mar 28: FOUN-1; Mar 29: FOUN-1; Mar 30: FOUN-1; Mar 31: FOUN-1; Apr 01: FOUN-1; Apr 02: FOUN-1
| Underground Structures- Mechanical Yard | Jul 21: FOUND-2; Jul 22: FOUND-2; Jul 23: FOUND-2; Jul 24: FOUND-2; Jul 25: FOUND-2; Jul 26: FOUND-2; Jul 27: FOUND-2; Jul 28: FOUND-2; Jul 29: FOUND-2; Jul 30: FOUND-2; Jul 31: FOUND-2; Aug 01: FOUND-2; Aug 02: FOUND-2; Aug 03: FOUND-2; Aug 04: FOUND-2; Aug 05: FOUND-2; Aug 06: FOUND-2; Aug 07: FOUND-2; Aug 08: FOUND-2; Aug 09: FOUND-2; Aug 10: FOUND-2; Aug 11: FOUND-2; Aug 12: FOUND-2; Aug 13: FOUND-2; Aug 14: FOUND-2; Aug 15: FOUND-2; Aug 16: FOUND-2; Aug 17: FOUND-2; Aug 18: FOUND-2; Aug 19: FOUND-2; Aug 20: FOUND-2; Aug 21: FOUND-2; Aug 22: FOUND-2; Aug 23: FOUND-2; Aug 24: FOUND-2; Aug 25: FOUND-2; Aug 26: FOUND-2; Aug 27: FOUND-2; Aug 28: FOUND-2; Aug 29: FOUND-2; Aug 30: FOUND-2; Aug 31: FOUND-2; Sep 01: FOUND-2; Sep 02: FOUND-2; Sep 03: FOUND-2; Sep 04: FOUND-2; Sep 05: FOUND-2; Sep 06: FOUND-2; Sep 07: FOUND-2; Sep 08: FOUND-2; Sep 09: FOUND-2; Sep 10: FOUND-2; Sep 11: FOUND-2; Sep 12: FOUND-2; Sep 13: FOUND-2; Sep 14: FOUND-2; Sep 15: FOUND-2; Sep 16: FOUND-2; Sep 17: FOUND-2; Sep 18: FOUND-2; Sep 19: FOUND-2; Sep 20: FOUND-2; Sep 21: FOUND-2; Sep 22: FOUND-2; Sep 23: FOUND-2; Sep 24: FOUND-2; Sep 25: FOUND-2; Sep 26: FOUND-2; Sep 27: FOUND-2; Sep 28: FOUND-2; Sep 29: FOUND-2; Sep 30: FOUND-2; Oct 01: FOUND-2; Oct 02: FOUND-2; Oct 03: FOUND-2; Oct 04: FOUND-2; Oct 05: FOUND-2; Oct 06: FOUND-2; Oct 07: FOUND-2; Oct 08: FOUND-2; Oct 09: FOUND-2; Oct 10: FOUND-2; Oct 11: FOUND-2; Oct 12: FOUND-2; Oct 13: FOUND-2
| Underground Structures- Zone 1 | Jul 21: FOUND-2; Jul 22: FOUND-2; Jul 23: FOUND-2; Jul 24: FOUND-2; Jul 25: FOUND-2; Jul 26: FOUND-2; Jul 27: FOUND-2; Jul 28: FOUND-2; Jul 29: FOUND-2; Jul 30: FOUND-2; Jul 31: FOUND-2; Aug 01: FOUND-2; Aug 02: FOUND-2; Aug 03: FOUND-2; Aug 04: FOUND-2; Aug 05: FOUND-2; Aug 06: FOUND-2; Aug 07: FOUND-2; Aug 08: FOUND-2; Aug 09: FOUND-2; Aug 10: FOUND-2; Aug 11: FOUND-2; Aug 12: FOUND-2; Aug 13: FOUND-2; Aug 14: FOUND-2; Aug 15: FOUND-2; Aug 16: FOUND-2; Aug 17: FOUND-2; Aug 18: FOUND-2; Aug 19: FOUND-2; Aug 20: FOUND-2; Aug 21: FOUND-2; Aug 22: FOUND-2; Aug 23: FOUND-2; Aug 24: FOUND-2; Aug 25: FOUND-2; Aug 26: FOUND-2; Aug 27: FOUND-2; Aug 28: FOUND-2; Aug 29: FOUND-2
| Underground Structures- Zone 2 | Sep 02: FOUND-2; Sep 03: FOUND-2; Sep 04: FOUND-2; Sep 05: FOUND-2; Sep 06: FOUND-2; Sep 07: FOUND-2; Sep 08: FOUND-2; Sep 09: FOUND-2; Sep 10: FOUND-2; Sep 11: FOUND-2; Sep 12: FOUND-2; Sep 13: FOUND-2; Sep 14: FOUND-2; Sep 15: FOUND-2; Sep 16: FOUND-2; Sep 17: FOUND-2; Sep 18: FOUND-2; Sep 19: FOUND-2; Sep 20: FOUND-2; Sep 21: FOUND-2; Sep 22: FOUND-2; Sep 23: FOUND-2; Sep 24: FOUND-2; Sep 25: FOUND-2; Sep 26: FOUND-2; Sep 27: FOUND-2; Sep 28: FOUND-2; Sep 29: FOUND-2; Sep 30: FOUND-2; Oct 01: FOUND-2; Oct 02: FOUND-2; Oct 03: FOUND-2; Oct 04: FOUND-2; Oct 05: FOUND-2; Oct 06: FOUND-2; Oct 07: FOUND-2; Oct 08: FOUND-2; Oct 09: FOUND-2; Oct 10: FOUND-2; Oct 11: FOUND-2; Oct 12: FOUND-2; Oct 13: FOUND-2
| Underground Structures- Zone 3 | Oct 14: FOUND-2; Oct 15: FOUND-2; Oct 16: FOUND-2; Oct 17: FOUND-2; Oct 18: FOUND-2; Oct 19: FOUND-2; Oct 20: FOUND-2; Oct 21: FOUND-2; Oct 22: FOUND-2; Oct 23: FOUND-2; Oct 24: FOUND-2; Oct 25: FOUND-2; Oct 26: FOUND-2; Oct 27: FOUND-2; Oct 28: FOUND-2; Oct 29: FOUND-2; Oct 30: FOUND-2; Oct 31: FOUND-2; Nov 01: FOUND-2; Nov 02: FOUND-2; Nov 03: FOUND-2; Nov 04: FOUND-2; Nov 05: FOUND-2; Nov 06: FOUND-2; Nov 07: FOUND-2; Nov 08: FOUND-2; Nov 09: FOUND-2; Nov 10: FOUND-2
| Underground Structures- Zone 4 | Nov 11: FOUND-2; Nov 12: FOUND-2; Nov 13: FOUND-2; Nov 14: FOUND-2; Nov 15: FOUND-2; Nov 16: FOUND-2; Nov 17: FOUND-2; Nov 18: FOUND-2; Nov 19: FOUND-2; Nov 20: FOUND-2; Nov 21: FOUND-2; Nov 22: FOUND-2; Nov 23: FOUND-2; Nov 24: FOUND-2; Nov 25: FOUND-2; Nov 26: FOUND-2; Nov 27: FOUND-2; Nov 28: FOUND-2; Nov 29: FOUND-2; Nov 30: FOUND-2; Dec 01: FOUND-2; Dec 02: FOUND-2; Dec 03: FOUND-2; Dec 04: FOUND-2; Dec 05: FOUND-2; Dec 06: FOUND-2; Dec 07: FOUND-2; Dec 08: FOUND-2; Dec 09: FOUND-2; Dec 10: FOUND-2
| Underground Structures- Zone 5 | Dec 11: FOUND-2; Dec 12: FOUND-2; Dec 13: FOUND-2; Dec 14: FOUND-2; Dec 15: FOUND-2; Dec 16: FOUND-2; Dec 17: FOUND-2; Dec 18: FOUND-2; Dec 19: FOUND-2; Dec 20: FOUND-2; Dec 21: FOUND-2; Dec 22: FOUND-2; Dec 23: FOUND-2; Dec 24: FOUND-2; Dec 25: FOUND-2; Dec 26: FOUND-2; Dec 27: FOUND-2; Dec 28: FOUND-2; Dec 29: FOUND-2; Dec 30: FOUND-2; Dec 31: FOUND-2; Jan 01: FOUND-2; Jan 02: FOUND-2; Jan 03: FOUND-2; Jan 04: FOUND-2; Jan 05: FOUND-2; Jan 06: FOUND-2; Jan 07: FOUND-2; Jan 08: FOUND-2; Jan 09: FOUND-2; Jan 10: FOUND-2; Jan 11: FOUND-2; Jan 12: FOUND-2; Jan 13: FOUND-2; Jan 14: FOUND-2; Jan 15: FOUND-2; Jan 16: FOUND-2; Jan 17: FOUND-2; Jan 18: FOUND-2; Jan 19: FOUND-2; Jan 20: FOUND-2; Jan 21: FOUND-2; Jan 22: FOUND-2; Jan 23: FOUND-2; Jan 24: FOUND-2; Jan 25: FOUND-2; Jan 26: FOUND-2; Jan 27: FOUND-2; Jan 28: FOUND-2; Jan 29: FOUND-2
| Underground Structures- Zone 6 | Jan 30: FOUND-2; Jan 31: FOUND-2; Feb 01: FOUND-2; Feb 02: FOUND-2; Feb 03: FOUND-2; Feb 04: FOUND-2; Feb 05: FOUND-2; Feb 06: FOUND-2; Feb 07: FOUND-2; Feb 08: FOUND-2; Feb 09: FOUND-2; Feb 10: FOUND-2; Feb 11: FOUND-2; Feb 12: FOUND-2; Feb 13: FOUND-2; Feb 14: FOUND-2; Feb 15: FOUND-2; Feb 16: FOUND-2; Feb 17: FOUND-2; Feb 18: FOUND-2; Feb 19: FOUND-2; Feb 20: FOUND-2; Feb 21: FOUND-2; Feb 22: FOUND-2; Feb 23: FOUND-2; Feb 24: FOUND-2; Feb 25: FOUND-2; Feb 26: FOUND-2; Feb 27: FOUND-2; Feb 28: FOUND-2; Mar 01: FOUND-2; Mar 02: FOUND-2; Mar 03: FOUND-2; Mar 04: FOUND-2; Mar 05: FOUND-2; Mar 06: FOUND-2; Mar 07: FOUND-2; Mar 08: FOUND-2; Mar 09: FOUND-2; Mar 10: FOUND-2; Mar 11: FOUND-2; Mar 12: FOUND-2
| Underground Structures- Zone 7A | Mar 13: FOUND-2; Mar 14: FOUND-2; Mar 15: FOUND-2; Mar 16: FOUND-2; Mar 17: FOUND-2; Mar 18: FOUND-2; Mar 19: FOUND-2; Mar 20: FOUND-2; Mar 21: FOUND-2; Mar 22: FOUND-2; Mar 23: FOUND-2; Mar 24: FOUND-2; Mar 25: FOUND-2; Mar 26: FOUND-2; Mar 27: FOUND-2; Mar 28: FOUND-2; Mar 29: FOUND-2; Mar 30: FOUND-2; Mar 31: FOUND-2; Apr 01: FOUND-2; Apr 02: FOUND-2
| Underground Structures- Zone 7B | Apr 06: FOUND-2; Apr 07: FOUND-2; Apr 08: FOUND-2; Apr 09: FOUND-2; Apr 10: FOUND-2; Apr 11: FOUND-2; Apr 12: FOUND-2; Apr 13: FOUND-2; Apr 14: FOUND-2; Apr 15: FOUND-2; Apr 16: FOUND-2; Apr 17: FOUND-2; Apr 18: FOUND-2; Apr 19: FOUND-2; Apr 20: FOUND-2; Apr 21: FOUND-2; Apr 22: FOUND-2; Apr 23: FOUND-2; Apr 24: FOUND-2
Exteriors | East Elevation | Nov 17: FINISH-1; Nov 18: FINISH-1; Nov 19: FINISH-1; Nov 20: FINISH-1; Nov 21: FINISH-1; Nov 22: FINISH-1; Nov 23: FINISH-1; Nov 24: FINISH-1; Nov 25: FINISH-1; Nov 26: FINISH-1; Nov 27: FINISH-1; Nov 28: FINISH-1; Nov 29: FINISH-1; Nov 30: FINISH-1; Dec 01: FINISH-1; Dec 02: FINISH-1; Dec 03: FINISH-1; Dec 04: FINISH-1; Dec 05: FINISH-1; Dec 06: FINISH-1; Dec 07: FINISH-1; Dec 08: FINISH-1; Dec 09: FINISH-1; Dec 10: FINISH-1; Dec 11: FINISH-1; Dec 12: FINISH-1; Dec 13: FINISH-1; Dec 14: FINISH-1; Dec 15: FINISH-1; Dec 16: FINISH-1; Dec 17: FINISH-1; Dec 18: FINISH-1; Dec 19: FINISH-1; Dec 20: FINISH-1; Dec 21: FINISH-1; Dec 22: FINISH-1; Dec 23: FINISH-1; Dec 24: FINISH-1; Dec 25: FINISH-1; Dec 26: FINISH-1; Dec 27: FINISH-1; Dec 28: FINISH-1; Dec 29: FINISH-1; Dec 30: FINISH-1; Dec 31: FINISH-1; Jan 01: FINISH-1; Jan 02: FINISH-1; Jan 03: FINISH-1; Jan 04: FINISH-1; Jan 05: FINISH-1; Jan 06: FINISH-1; Jan 07: FINISH-1; Jan 08: FINISH-1; Jan 09: FINISH-1; Jan 10: FINISH-1; Jan 11: FINISH-1; Jan 12: FINISH-1; Jan 13: FINISH-1; Jan 14: FINISH-1; Jan 15: FINISH-1; Jan 16: FINISH-1; Jan 17: FINISH-1; Jan 18: FINISH-1; Jan 19: FINISH-1; Jan 20: FINISH-1; Jan 21: FINISH-1; Jan 22: FINISH-1; Jan 23: FINISH-1; Jan 24: FINISH-1; Jan 25: FINISH-1; Jan 26: FINISH-1; Jan 27: FINISH-1; Jan 28: FINISH-1
| North Elevation | Dec 17: FINISH-1; Dec 18: FINISH-1; Dec 19: FINISH-1; Dec 20: FINISH-1; Dec 21: FINISH-1; Dec 22: FINISH-1; Dec 23: FINISH-1; Dec 24: FINISH-1; Dec 25: FINISH-1; Dec 26: FINISH-1; Dec 27: FINISH-1; Dec 28: FINISH-1; Dec 29: FINISH-1; Dec 30: FINISH-1; Dec 31: FINISH-1; Jan 01: FINISH-1; Jan 02: FINISH-1; Jan 03: FINISH-1; Jan 04: FINISH-1; Jan 05: FINISH-1; Jan 06: FINISH-1; Jan 07: FINISH-1; Jan 08: FINISH-1; Jan 09: FINISH-1; Jan 10: FINISH-1; Jan 11: FINISH-1; Jan 12: FINISH-1; Jan 13: FINISH-1; Jan 14: FINISH-1; Jan 15: FINISH-1; Jan 16: FINISH-1; Jan 17: FINISH-1; Jan 18: FINISH-1; Jan 19: FINISH-1; Jan 20: FINISH-1; Jan 21: FINISH-1; Jan 22: FINISH-1; Jan 23: FINISH-1; Jan 24: FINISH-1; Jan 25: FINISH-1; Jan 26: FINISH-1; Jan 27: FINISH-1; Jan 28: FINISH-1; Jan 29: FINISH-1; Jan 30: FINISH-1; Jan 31: FINISH-1; Feb 01: FINISH-1; Feb 02: FINISH-1; Feb 03: FINISH-1; Feb 04: FINISH-1; Feb 05: FINISH-1; Feb 06: FINISH-1; Feb 07: FINISH-1; Feb 08: FINISH-1; Feb 09: FINISH-1; Feb 10: FINISH-1; Feb 11: FINISH-1; Feb 12: FINISH-1; Feb 13: FINISH-1; Feb 14: FINISH-1; Feb 15: FINISH-1; Feb 16: FINISH-1; Feb 17: FINISH-1; Feb 18: FINISH-1; Feb 19: FINISH-1; Feb 20: FINISH-1; Feb 21: FINISH-1; Feb 22: FINISH-1; Feb 23: FINISH-1; Feb 24: FINISH-1; Feb 25: FINISH-1
| Roofing | Jan 08: FINISH-2; Jan 09: FINISH-2; Jan 10: FINISH-2; Jan 11: FINISH-2; Jan 12: FINISH-2; Jan 13: FINISH-2; Jan 14: FINISH-2; Jan 15: FINISH-2; Jan 16: FINISH-2; Jan 17: FINISH-2; Jan 18: FINISH-2; Jan 19: FINISH-2; Jan 20: FINISH-2; Jan 21: FINISH-2; Jan 22: FINISH-2; Jan 23: FINISH-2; Jan 24: FINISH-2; Jan 25: FINISH-2; Jan 26: FINISH-2; Jan 27: FINISH-2; Jan 28: FINISH-2; Jan 29: FINISH-2; Jan 30: FINISH-2; Jan 31: FINISH-2; Feb 01: FINISH-2; Feb 02: FINISH-2; Feb 03: FINISH-2; Feb 04: FINISH-2; Feb 05: FINISH-2; Feb 06: FINISH-2; Feb 07: FINISH-2; Feb 08: FINISH-2; Feb 09: FINISH-2; Feb 10: FINISH-2; Feb 11: FINISH-2; Feb 12: FINISH-2; Feb 13: FINISH-2; Feb 14: FINISH-2; Feb 15: FINISH-2; Feb 16: FINISH-2; Feb 17: FINISH-2; Feb 18: FINISH-2; Feb 19: FINISH-2; Feb 20: FINISH-2; Feb 21: FINISH-2; Feb 22: FINISH-2; Feb 23: FINISH-2; Feb 24: FINISH-2; Feb 25: FINISH-2; Feb 26: FINISH-2; Feb 27: FINISH-2; Feb 28: FINISH-2; Mar 01: FINISH-2; Mar 02: FINISH-2; Mar 03: FINISH-2; Mar 04: FINISH-2; Mar 05: FINISH-2; Mar 06: FINISH-2; Mar 07: FINISH-2; Mar 08: FINISH-2; Mar 09: FINISH-2; Mar 10: FINISH-2; Mar 11: FINISH-2; Mar 12: FINISH-2; Mar 13: FINISH-2; Mar 14: FINISH-2; Mar 15: FINISH-2; Mar 16: FINISH-2; Mar 17: FINISH-2; Mar 18: FINISH-2; Mar 19: FINISH-2; Mar 20: FINISH-2; Mar 21: FINISH-2; Mar 22: FINISH-2; Mar 23: FINISH-2; Mar 24: FINISH-2; Mar 25: FINISH-2; Mar 26: FINISH-2; Mar 27: FINISH-2; Mar 28: FINISH-2; Mar 29: FINISH-2; Mar 30: FINISH-2; Mar 31: FINISH-2; Apr 01: FINISH-2
| South Elevation | Jan 15: FINISH-1; Jan 16: FINISH-1; Jan 17: FINISH-1; Jan 18: FINISH-1; Jan 19: FINISH-1; Jan 20: FINISH-1; Jan 21: FINISH-1; Jan 22: FINISH-1; Jan 23: FINISH-1; Jan 24: FINISH-1; Jan 25: FINISH-1; Jan 26: FINISH-1; Jan 27: FINISH-1; Jan 28: FINISH-1; Jan 29: FINISH-1; Jan 30: FINISH-1; Jan 31: FINISH-1; Feb 01: FINISH-1; Feb 02: FINISH-1; Feb 03: FINISH-1; Feb 04: FINISH-1; Feb 05: FINISH-1; Feb 06: FINISH-1; Feb 07: FINISH-1; Feb 08: FINISH-1; Feb 09: FINISH-1; Feb 10: FINISH-1; Feb 11: FINISH-1; Feb 12: FINISH-1; Feb 13: FINISH-1; Feb 14: FINISH-1; Feb 15: FINISH-1; Feb 16: FINISH-1; Feb 17: FINISH-1; Feb 18: FINISH-1; Feb 19: FINISH-1; Feb 20: FINISH-1; Feb 21: FINISH-1; Feb 22: FINISH-1; Feb 23: FINISH-1; Feb 24: FINISH-1; Feb 25: FINISH-1; Feb 26: FINISH-1; Feb 27: FINISH-1; Feb 28: FINISH-1; Mar 01: FINISH-1; Mar 02: FINISH-1; Mar 03: FINISH-1; Mar 04: FINISH-1; Mar 05: FINISH-1; Mar 06: FINISH-1; Mar 07: FINISH-1; Mar 08: FINISH-1; Mar 09: FINISH-1; Mar 10: FINISH-1; Mar 11: FINISH-1; Mar 12: FINISH-1; Mar 13: FINISH-1; Mar 14: FINISH-1; Mar 15: FINISH-1; Mar 16: FINISH-1; Mar 17: FINISH-1; Mar 18: FINISH-1
| West Elevation | Dec 17: FINISH-1; Dec 18: FINISH-1; Dec 19: FINISH-1; Dec 20: FINISH-1; Dec 21: FINISH-1; Dec 22: FINISH-1; Dec 23: FINISH-1; Dec 24: FINISH-1; Dec 25: FINISH-1; Dec 26: FINISH-1; Dec 27: FINISH-1; Dec 28: FINISH-1; Dec 29: FINISH-1; Dec 30: FINISH-1; Dec 31: FINISH-1; Jan 01: FINISH-1; Jan 02: FINISH-1; Jan 03: FINISH-1; Jan 04: FINISH-1; Jan 05: FINISH-1; Jan 06: FINISH-1; Jan 07: FINISH-1; Jan 08: FINISH-1; Jan 09: FINISH-1; Jan 10: FINISH-1; Jan 11: FINISH-1; Jan 12: FINISH-1; Jan 13: FINISH-1; Jan 14: FINISH-1; Jan 15: FINISH-1; Jan 16: FINISH-1; Jan 17: FINISH-1; Jan 18: FINISH-1; Jan 19: FINISH-1; Jan 20: FINISH-1; Jan 21: FINISH-1; Jan 22: FINISH-1; Jan 23: FINISH-1; Jan 24: FINISH-1; Jan 25: FINISH-1; Jan 26: FINISH-1; Jan 27: FINISH-1; Jan 28: FINISH-1; Jan 29: FINISH-1; Jan 30: FINISH-1; Jan 31: FINISH-1; Feb 01: FINISH-1; Feb 02: FINISH-1; Feb 03: FINISH-1; Feb 04: FINISH-1; Feb 05: FINISH-1; Feb 06: FINISH-1; Feb 07: FINISH-1; Feb 08: FINISH-1; Feb 09: FINISH-1; Feb 10: FINISH-1; Feb 11: FINISH-1; Feb 12: FINISH-1; Feb 13: FINISH-1; Feb 14: FINISH-1; Feb 15: FINISH-1; Feb 16: FINISH-1; Feb 17: FINISH-1; Feb 18: FINISH-1; Feb 19: FINISH-1; Feb 20: FINISH-1; Feb 21: FINISH-1; Feb 22: FINISH-1; Feb 23: FINISH-1; Feb 24: FINISH-1; Feb 25: FINISH-1
Note on GH5: Activity Name: Issue Contract to Curtainwall Sub Phase: Subcontractor Procurement Location: Contracts Trade: McGough Start Date: 10-Mar-2025 End Date: 04-Apr-2025
Note on GH6: Activity Name: Issue Contract to Store Fronts Sub Phase: Subcontractor Procurement Location: Contracts Trade: McGough Start Date: 10-Mar-2025 End Date: 04-Apr-2025
Note on GH7: Activity Name: Issue Contract to Structural Steel Sub Phase: Subcontractor Procurement Location: Contracts Trade: McGough Start Date: 10-Mar-2025 End Date: 04-Apr-2025
Note on GH8: Activity Name: Issue Contract to Security Glazing Sub Phase: Subcontractor Procurement Location: Contracts Trade: McGough Start Date: 10-Mar-2025 End Date: 04-Apr-2025
Note on GH9: Activity Name: Issue Contract to Overhead Door Sub Phase: Subcontractor Procurement Location: Contracts Trade: McGough Start Date: 10-Mar-2025 End Date: 04-Apr-2025
Note on GH10: Activity Name: Issue Contract to Mechanical Sub Phase: Subcontractor Procurement Location: Contracts Trade: McGough Start Date: 10-Mar-2025 End Date: 04-Apr-2025
Note on GH11: Activity Name: Issue Contract to Electrical Sub Phase: Subcontractor Procurement Location: Contracts Trade: McGough Start Date: 10-Mar-2025 End Date: 04-Apr-2025
Note on GH12: Activity Name: Issue Contract to Kitchen Equipment Sub Phase: Subcontractor Procurement Location: Contracts Trade: McGough Start Date: 10-Mar-2025 End Date: 04-Apr-2025
Note on GH13: Activity Name: Issue Contract to Antiligature Door Hardware/Kingsway Kits Sub Phase: Subcontractor Procurement Location: Contracts Trade: McGough Start Date: 10-Mar-2025 End Date: 04-Apr-2025
Note on C14: Activity Name: Pre-Qual Curtainwall Sub Phase: Subcontractor Procurement Location: Pre-Qual Trade: McGough Start Date: 04-Sep-2024 End Date: 10-Sep-2024
Note on C15: Activity Name: Pre-Qual Store Fronts Sub Phase: Subcontractor Procurement Location: Pre-Qual Trade: McGough Start Date: 04-Sep-2024 End Date: 10-Sep-2024
Note on C16: Activity Name: Pre-Qual Structural Steel Sub Phase: Subcontractor Procurement Location: Pre-Qual Trade: McGough Start Date: 04-Sep-2024 End Date: 10-Sep-2024
Note on C17: Activity Name: Pre-Qual Security Glazing Sub Phase: Subcontractor Procurement Location: Pre-Qual Trade: McGough Start Date: 04-Sep-2024 End Date: 10-Sep-2024
Note on C18: Activity Name: Pre-Qual Overhead Door Sub Phase: Subcontractor Procurement Location: Pre-Qual Trade: McGough Start Date: 04-Sep-2024 End Date: 10-Sep-2024
Note on C19: Activity Name: Pre-Qual Mechanical Sub Phase: Subcontractor Procurement Location: Pre-Qual Trade: McGough Start Date: 04-Sep-2024 End Date: 10-Sep-2024
Note on C20: Activity Name: Pre-Qual Electrical Sub Phase: Subcontractor Procurement Location: Pre-Qual Trade: McGough Start Date: 04-Sep-2024 End Date: 10-Sep-2024
Note on C21: Activity Name: Pre-Qual Kitchen Equipment Sub Phase: Subcontractor Procurement Location: Pre-Qual Trade: McGough Start Date: 04-Sep-2024 End Date: 10-Sep-2024
Note on C22: Activity Name: Pre-Qual Antiligature Door Hardware/Kingsway Kits Sub Phase: Subcontractor Procurement Location: Pre-Qual Trade: McGough Start Date: 04-Sep-2024 End Date: 10-Sep-2024
Note on C23: Activity Name: Procure Transformer (by others) Phase: Material Procurement Location: Material Trade: McGough Start Date: 04-Sep-2024 End Date: 25-Apr-2025
Note on IF23: Activity Name: Procure & Fabricate Structural Steel Phase: Material Procurement Location: Material Trade: McGough Start Date: 29-Apr-2025 End Date: 23-Jul-2025
Note on LR23: Activity Name: Procure & Fabricate Boilers Phase: Material Procurement Location: Material Trade: McGough Start Date: 28-Jul-2025 End Date: 15-May-2026
Note on IF24: Activity Name: Procure & Fabricate Curtainwall Phase: Material Procurement Location: Material Trade: McGough Start Date: 29-Apr-2025 End Date: 18-Sep-2025
Note on ST24: Activity Name: Procure & Fabricate Antiligature Door Hardware/Kingsway Kits Phase: Material Procurement Location: Material Trade: McGough Start Date: 28-Jan-2026 End Date: 18-Jun-2026
Note on IF25: Activity Name: Procure & Fabricate Store Fronts Phase: Material Procurement Location: Material Trade: McGough Start Date: 29-Apr-2025 End Date: 18-Sep-2025
Note on SY25: Activity Name: Procure & Fabricate Kitchen Equipment Phase: Material Procurement Location: Material Trade: McGough Start Date: 02-Feb-2026 End Date: 27-Apr-2026
Note on IF26: Activity Name: Procure & Fabricate AHU's Phase: Material Procurement Location: Material Trade: McGough Start Date: 29-Apr-2025 End Date: 17-Feb-2026
Note on IF27: Activity Name: Procure & Fabricate Chillers Phase: Material Procurement Location: Material Trade: McGough Start Date: 29-Apr-2025 End Date: 17-Feb-2026
Note on IF28: Activity Name: Procure & Fabricate Generator Phase: Material Procurement Location: Material Trade: McGough Start Date: 29-Apr-2025 End Date: 13-May-2026
Note on IF29: Activity Name: Procure & Fabricate Electrical Switchgear Phase: Material Procurement Location: Material Trade: McGough Start Date: 29-Apr-2025 End Date: 13-May-2026
Note on IF30: Activity Name: Procure & Fabricate ATS Phase: Material Procurement Location: Material Trade: McGough Start Date: 29-Apr-2025 End Date: 13-May-2026
Note on JO31: Activity Name: Procure & Fabricate Security Glazing Phase: Material Procurement Location: Material Trade: McGough Start Date: 03-Jun-2025 End Date: 24-Sep-2025
Note on JO32: Activity Name: Procure & Fabricate Overhead Door (6) Phase: Material Procurement Location: Material Trade: McGough Start Date: 03-Jun-2025 End Date: 08-Oct-2025
Note on GB36: Activity Name: GMP Issued Phase: Milestones Location: General Milestone Trade: McGough Start Date: 04-Mar-2025 End Date: 07-Mar-2025
Note on HF36: Activity Name: Mobilization Phase: Milestones Location: General Milestone Trade: McGough Start Date: 03-Apr-2025 End Date: 16-Apr-2025
Note on AJM36: Activity Name: Substantial Completion Phase: Milestones Location: General Milestone Trade: McGough Start Date: 08-Apr-2027 End Date: 08-Apr-2027
Note on C39: Activity Name: Demolition Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on CG39: Activity Name: Subcontract Procurement Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 25-Nov-2024 End Date: 23-May-2025
Note on PZ39: Activity Name: Building Enclosure Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 17-Nov-2025 End Date: 01-Apr-2026
Note on AAU39: Activity Name: Testing and Commissioning Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 25-Aug-2026 End Date: 03-Mar-2027
Note on C40: Activity Name: Earthworks and Support of Excavation Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on HF40: Activity Name: Site Utilities Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 03-Apr-2025 End Date: 18-Jul-2025
Note on C41: Activity Name: Deep Foundations Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on C42: Activity Name: Structural Foundations/Footings Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on C43: Activity Name: Below Grade Structure Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on C44: Activity Name: Above Grade Structure Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on C45: Activity Name: Vertical Transportation Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on C46: Activity Name: Rough-In Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on C47: Activity Name: Finishes Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on C48: Activity Name: Masonry Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on C49: Activity Name: Hardscape and Landscaping Phase: McGough Standards Location: Executive Summary Trade: Exec Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on FF53: Activity Name: Notice to Proceed Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on IS53: Activity Name: Temp Power Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 12-May-2025 End Date: 12-May-2025
Note on JD53: Activity Name: Excavation Start Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 23-May-2025 End Date: 23-May-2025
Note on LR53: Activity Name: Excavation Complete Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 28-Jul-2025 End Date: 28-Jul-2025
Note on OX53: Activity Name: Above Grade Structure Start Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 20-Oct-2025 End Date: 20-Oct-2025
Note on PE53: Activity Name: Building Temporarily Enclosed Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 27-Oct-2025 End Date: 27-Oct-2025
Note on RY53: Activity Name: Above Grade Structure Complete Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 07-Jan-2026 End Date: 07-Jan-2026
Note on SU53: Activity Name: Building Envelope Start Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 29-Jan-2026 End Date: 29-Jan-2026
Note on VM53: Activity Name: Building Envelope Complete Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 09-Apr-2026 End Date: 09-Apr-2026
Note on WW53: Activity Name: MEP Rough-In Start Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 15-May-2026 End Date: 15-May-2026
Note on XH53: Activity Name: Permanent Power Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 26-May-2026 End Date: 26-May-2026
Note on XN53: Activity Name: Start Drywall Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 01-Jun-2026 End Date: 01-Jun-2026
Note on AAH53: Activity Name: Courtyard Start Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 12-Aug-2026 End Date: 12-Aug-2026
Note on AAV53: Activity Name: Building Finishes Start Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 26-Aug-2026 End Date: 26-Aug-2026
Note on ABX53: Activity Name: Drywall Complete Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 23-Sep-2026 End Date: 23-Sep-2026
Note on AHB53: Activity Name: Courtyard Finish Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 04-Feb-2027 End Date: 04-Feb-2027
Note on ALC53: Activity Name: Final Acceptance Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 20-May-2027 End Date: 20-May-2027
Note on FF54: Activity Name: Below Grade Structure Start Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on FF55: Activity Name: Below Grade Structure Complete Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on FF56: Activity Name: Vertical Transportation Start Phase: McGough Standards Location: Key Milestones Trade: McGough Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on CG60: Activity Name: Subcontractor Procurement Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 25-Nov-2024 End Date: 25-Nov-2024
Note on FF60: Activity Name: Mobilization Key Activity Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on FM60: Activity Name: Site Survey Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on GA60: Activity Name: Utilities Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on GH60: Activity Name: Site Survey Finish Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 10-Mar-2025 End Date: 10-Mar-2025
Note on HF60: Activity Name: Mobilization Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 03-Apr-2025 End Date: 03-Apr-2025
Note on HS60: Activity Name: Mobilization Finish Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 16-Apr-2025 End Date: 16-Apr-2025
Note on IW60: Activity Name: Utilities Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 16-May-2025 End Date: 16-May-2025
Note on JB60: Activity Name: Permitting Finish Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 21-May-2025 End Date: 21-May-2025
Note on JC60: Activity Name: Permitting Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 22-May-2025 End Date: 22-May-2025
Note on JD60: Activity Name: Excavation Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 23-May-2025 End Date: 23-May-2025
Note on JH60: Activity Name: Subcontractor Procurement Finish Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 27-May-2025 End Date: 27-May-2025
Note on LH60: Activity Name: Structural Foundations Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 18-Jul-2025 End Date: 18-Jul-2025
Note on LK60: Activity Name: Underground Structures Start Rough In Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 21-Jul-2025 End Date: 21-Jul-2025
Note on LR60: Activity Name: Excavation Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 28-Jul-2025 End Date: 28-Jul-2025
Note on NL60: Activity Name: Structural Foundations Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 12-Sep-2025 End Date: 12-Sep-2025
Note on NO60: Activity Name: Above Grade Structures Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 15-Sep-2025 End Date: 15-Sep-2025
Note on PB60: Activity Name: Building Temporarily Enclosed Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 24-Oct-2025 End Date: 24-Oct-2025
Note on PZ60: Activity Name: Building Envelope Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 17-Nov-2025 End Date: 17-Nov-2025
Note on RD60: Activity Name: Masonry Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 17-Dec-2025 End Date: 17-Dec-2025
Note on RY60: Activity Name: Above Grade Structures Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 07-Jan-2026 End Date: 07-Jan-2026
Note on SH60: Activity Name: Material Purchase Finish Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 16-Jan-2026 End Date: 16-Jan-2026
Note on VE60: Activity Name: Building Envelope Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 01-Apr-2026 End Date: 01-Apr-2026
Note on VM60: Activity Name: Masonry Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 09-Apr-2026 End Date: 09-Apr-2026
Note on VU60: Activity Name: Rough-In Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 17-Apr-2026 End Date: 17-Apr-2026
Note on WB60: Activity Name: Underground Structures Complete Rough In Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 24-Apr-2026 End Date: 24-Apr-2026
Note on YY60: Activity Name: Finishes Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 08-Jul-2026 End Date: 08-Jul-2026
Note on ZR60: Activity Name: Rough-In Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 27-Jul-2026 End Date: 27-Jul-2026
Note on ACL60: Activity Name: Commissioning Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 07-Oct-2026 End Date: 07-Oct-2026
Note on ADN60: Activity Name: Finishes Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 04-Nov-2026 End Date: 04-Nov-2026
Note on AEA60: Activity Name: Testing Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 17-Nov-2026 End Date: 17-Nov-2026
Note on AEB60: Activity Name: Building Water Testing Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 18-Nov-2026 End Date: 18-Nov-2026
Note on AED60: Activity Name: Testing Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 20-Nov-2026 End Date: 20-Nov-2026
Note on AEN60: Activity Name: Sitework(Land/Hardscape) Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 30-Nov-2026 End Date: 30-Nov-2026
Note on AFF60: Activity Name: Sitework(Land/Hardscape) Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 18-Dec-2026 End Date: 18-Dec-2026
Note on AIC60: Activity Name: Commissioning Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 03-Mar-2027 End Date: 03-Mar-2027
Note on CG61: Activity Name: Material Purchase Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 25-Nov-2024 End Date: 25-Nov-2024
Note on FF61: Activity Name: Demolition Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on GA61: Activity Name: Utilities Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on AED61: Activity Name: Equipment Startup Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 20-Nov-2026 End Date: 20-Nov-2026
Note on FF62: Activity Name: Demolition Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on FF63: Activity Name: Deep Structural Foundations Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on FF64: Activity Name: Deep Structural Foundations Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on FF65: Activity Name: Vertical Transportation Start Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on FF66: Activity Name: Vertical Transportation Complete Phase: McGough Standards Location: McGough Tracking Trade: Tracking Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on C70: Activity Name: DD 1 Safety & Risk Assessment Phase: Design Location: Design Milestone Trade: McGough Start Date: 04-Sep-2024 End Date: 05-Sep-2024
Note on R70: Activity Name: DD 2 Phase: Design Location: Design Milestone Trade: McGough Start Date: 19-Sep-2024 End Date: 19-Sep-2024
Note on AT70: Activity Name: DD 3 Phase: Design Location: Design Milestone Trade: McGough Start Date: 17-Oct-2024 End Date: 17-Oct-2024
Note on BV70: Activity Name: DD 4 Phase: Design Location: Design Milestone Trade: McGough Start Date: 14-Nov-2024 End Date: 14-Nov-2024
Note on CW70: Activity Name: DD Package Submission Owner & Cost Estimator Phase: Design Location: Design Milestone Trade: McGough Start Date: 11-Dec-2024 End Date: 18-Dec-2024
Note on DE70: Activity Name: Start CD Package Phase: Design Location: Design Milestone Trade: McGough Start Date: 19-Dec-2024 End Date: 19-Dec-2024
Note on DF70: Activity Name: DD Cost Estimate Due Phase: Design Location: Design Milestone Trade: McGough Start Date: 20-Dec-2024 End Date: 29-Jan-2025
Note on EU70: Activity Name: DD Final Page Turn & Owner Sign-off Phase: Design Location: Design Milestone Trade: McGough Start Date: 30-Jan-2025 End Date: 30-Jan-2025
Note on FI70: Activity Name: Owner DD & GMP Signoff Phase: Design Location: Design Milestone Trade: McGough Start Date: 13-Feb-2025 End Date: 03-Mar-2025
Note on HF70: Activity Name: Issue Complete CD Package Phase: Design Location: Design Milestone Trade: McGough Start Date: 03-Apr-2025 End Date: 02-Jun-2025
Note on DE71: Activity Name: Early Site Utility, Grading, Foundation Package Phase: Design Location: Design Milestone Trade: McGough Start Date: 19-Dec-2024 End Date: 02-Apr-2025
Note on EU72: Activity Name: Cost Reconciliation Phase: Design Location: Design Milestone Trade: McGough Start Date: 30-Jan-2025 End Date: 12-Feb-2025
Note on EU73: Activity Name: Owner Comments Due Phase: Design Location: Design Milestone Trade: McGough Start Date: 30-Jan-2025 End Date: 12-Feb-2025
Note on EF77: Activity Name: Permitting - TXDot Phase: Permitting Location: Permits Trade: McGough Start Date: 15-Jan-2025 End Date: 21-May-2025
Note on HJ78: Activity Name: Submit ATS Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 07-Apr-2025 End Date: 21-Apr-2025
Note on HY78: Activity Name: Owner Approve Curtainwall Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on HJ79: Activity Name: Submit Boilers Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 07-Apr-2025 End Date: 21-Apr-2025
Note on HY79: Activity Name: Owner Approve Store Front Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on HJ80: Activity Name: Submit Antiligature Door Hardware/Kingsway Kits Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 07-Apr-2025 End Date: 21-Apr-2025
Note on HY80: Activity Name: Owner Approve Security Glazing Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on HY81: Activity Name: Owner Approve Steel Structure Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on HY82: Activity Name: Owner Approve Overhead Door Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on HY83: Activity Name: Owner Approve Chiller Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on HY84: Activity Name: Owner Approve AHU Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on HY85: Activity Name: Owner Approve Generator Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on HY86: Activity Name: Owner Approve Kitchen Equipment Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on HY87: Activity Name: Owner Approve Electrical Switchgear Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on HY88: Activity Name: Owner Approve ATS Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on HY89: Activity Name: Owner Approve Boilers Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on HY90: Activity Name: Owner Approve Antiligature Door Hardware/Kingsway Kits Shop Drawings Phase: Submittals Location: Product Data Trade: McGough Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on HJ94: Activity Name: Submit Curtainwall Shop Drawings Phase: Submittals Location: Shop Drawings Trade: McGough Start Date: 07-Apr-2025 End Date: 21-Apr-2025
Note on HJ95: Activity Name: Submit Store Front Shop Drawings Phase: Submittals Location: Shop Drawings Trade: McGough Start Date: 07-Apr-2025 End Date: 21-Apr-2025
Note on HJ96: Activity Name: Submit Security Glazing Shop Drawings Phase: Submittals Location: Shop Drawings Trade: McGough Start Date: 07-Apr-2025 End Date: 21-Apr-2025
Note on HJ97: Activity Name: Submit Steel Structure Shop Drawings Phase: Submittals Location: Shop Drawings Trade: McGough Start Date: 07-Apr-2025 End Date: 21-Apr-2025
Note on HJ98: Activity Name: Submit Overhead Door Shop Drawings Phase: Submittals Location: Shop Drawings Trade: McGough Start Date: 07-Apr-2025 End Date: 21-Apr-2025
Note on HJ99: Activity Name: Submit Chiller Shop Drawings Phase: Submittals Location: Shop Drawings Trade: McGough Start Date: 07-Apr-2025 End Date: 21-Apr-2025
Note on HJ100: Activity Name: Submit AHU Shop Drawings Phase: Submittals Location: Shop Drawings Trade: McGough Start Date: 07-Apr-2025 End Date: 21-Apr-2025
Note on HJ101: Activity Name: Submit Generator Shop Drawings Phase: Submittals Location: Shop Drawings Trade: McGough Start Date: 07-Apr-2025 End Date: 21-Apr-2025
Note on HJ102: Activity Name: Submit Kitchen Equipment Shop Drawings Phase: Submittals Location: Shop Drawings Trade: McGough Start Date: 07-Apr-2025 End Date: 21-Apr-2025
Note on HJ103: Activity Name: Submit Electrical Switchgear Shop Drawings Phase: Submittals Location: Shop Drawings Trade: McGough Start Date: 07-Apr-2025 End Date: 21-Apr-2025
Note on LH104: Activity Name: Structural Foundations - Entire Site Phase: Structure/Foundations Location: Structural Foundations Trade: All Structurals Subs Start Date: 18-Jul-2025 End Date: 12-Sep-2025
Note on ACL105: Activity Name: Commissioning All Systems Phase: Interiors Location: Commissioning Trade: All Start Date: 07-Oct-2026 End Date: 03-Mar-2027
Note on AHC106: Activity Name: FF&E Phase: Interiors Location: FF&E Trade: Concrete Start Date: 05-Feb-2027 End Date: 08-Apr-2027
Note on XN107: Activity Name: Install Kitchen Equipment Phase: Interiors Location: Finishes - Kitchen Trade: Kitchen Start Date: 01-Jun-2026 End Date: 24-Aug-2026
Note on PM108: Activity Name: F/R/P Concrete Pads - Mechanical Yard Phase: Interiors Location: Finishes - Mechanical Room Trade: Concrete Start Date: 04-Nov-2025 End Date: 17-Dec-2025
Note on RE108: Activity Name: Cure Concrete Pads - Mechanical Yard Phase: Interiors Location: Finishes - Mechanical Room Trade: Concrete Start Date: 18-Dec-2025 End Date: 29-Dec-2025
Note on SV108: Activity Name: Cure Concrete Pad Sally Port - Mechanical Yard Phase: Interiors Location: Finishes - Mechanical Room Trade: Concrete Start Date: 30-Jan-2026 End Date: 12-Mar-2026
Note on UR108: Activity Name: Install CMU Walls - Mechanical Yard Phase: Interiors Location: Finishes - Mechanical Room Trade: Mechanical Start Date: 19-Mar-2026 End Date: 30-Apr-2026
Note on WV108: Activity Name: Set Generator - Mechanical Yard Phase: Interiors Location: Finishes - Mechanical Room Trade: Electrical Start Date: 14-May-2026 End Date: 15-May-2026
Note on WZ108: Activity Name: Hook-up/Final Connections Generator - Mechanical Yard Phase: Interiors Location: Finishes - Mechanical Room Trade: Mechanical Start Date: 18-May-2026 End Date: 22-May-2026
Note on RE109: Activity Name: F/R/P Concrete Pad Sally Port - Mechanical Yard Phase: Interiors Location: Finishes - Mechanical Room Trade: Concrete Start Date: 18-Dec-2025 End Date: 29-Jan-2026
Note on TO109: Activity Name: Set Chillers (3) - Mechanical Yard Phase: Interiors Location: Finishes - Mechanical Room Trade: Mechanical Start Date: 18-Feb-2026 End Date: 24-Feb-2026
Note on TV109: Activity Name: Hook-up/Final Connections Chillers - Mechanical Yard Phase: Interiors Location: Finishes - Mechanical Room Trade: Mechanical Start Date: 25-Feb-2026 End Date: 17-Mar-2026
Note on WZ109: Activity Name: Set Fuel Tank - Mechanical Yard Phase: Interiors Location: Finishes - Mechanical Room Trade: Mechanical Start Date: 18-May-2026 End Date: 22-May-2026
Note on VF113: Activity Name: Frame Walls & Ceilings - Zone 1 Phase: Interiors Location: Finishes - Zone 1 Trade: Drywall Start Date: 02-Apr-2026 End Date: 16-Apr-2026
Note on WZ113: Activity Name: In-wall Blocking - Zone 1 Phase: Interiors Location: Finishes - Zone 1 Trade: Mechanical Start Date: 18-May-2026 End Date: 19-May-2026
Note on XB113: Activity Name: Two Side Walls - Zone 1 Phase: Interiors Location: Finishes - Zone 1 Trade: Drywall Start Date: 20-May-2026 End Date: 29-May-2026
Note on XN113: Activity Name: Tape & Float - Zone 1 Phase: Interiors Location: Finishes - Zone 1 Trade: Drywall Start Date: 01-Jun-2026 End Date: 12-Jun-2026
Note on YB113: Activity Name: Install ACT Grid - Zone 1 Phase: Interiors Location: Finishes - Zone 1 Trade: Mechanical Start Date: 15-Jun-2026 End Date: 19-Jun-2026
Note on YI113: Activity Name: Ceiling Trim Out - Zone 1 Phase: Interiors Location: Finishes - Zone 1 Trade: Ceiling Start Date: 22-Jun-2026 End Date: 30-Jun-2026
Note on YR113: Activity Name: Ceiling Inspection - Zone 1 Phase: Interiors Location: Finishes - Zone 1 Trade: Inspector Start Date: 01-Jul-2026 End Date: 01-Jul-2026
Note on YS113: Activity Name: Close Ceiling - Zone 1 Phase: Interiors Location: Finishes - Zone 1 Trade: Ceiling Start Date: 02-Jul-2026 End Date: 07-Jul-2026
Note on YY113: Activity Name: Finishes - Zone 1 Phase: Interiors Location: Finishes - Zone 1 Trade: Finishes Start Date: 08-Jul-2026 End Date: 25-Aug-2026
Note on VU117: Activity Name: Frame Walls & Ceilings - Zone 2 Phase: Interiors Location: Finishes - Zone 2 Trade: Drywall Start Date: 17-Apr-2026 End Date: 30-Apr-2026
Note on XO117: Activity Name: In-wall Blocking - Zone 2 Phase: Interiors Location: Finishes - Zone 2 Trade: Mechanical Start Date: 02-Jun-2026 End Date: 03-Jun-2026
Note on XQ117: Activity Name: Two Side Walls - Zone 2 Phase: Interiors Location: Finishes - Zone 2 Trade: Drywall Start Date: 04-Jun-2026 End Date: 12-Jun-2026
Note on YB117: Activity Name: Tape & Float - Zone 2 Phase: Interiors Location: Finishes - Zone 2 Trade: Drywall Start Date: 15-Jun-2026 End Date: 26-Jun-2026
Note on YP117: Activity Name: Install ACT Ceilings - Zone 2 Phase: Interiors Location: Finishes - Zone 2 Trade: Ceiling Start Date: 29-Jun-2026 End Date: 01-Jul-2026
Note on YS117: Activity Name: Install Hard Ceiling - Zone 2 Phase: Interiors Location: Finishes - Zone 2 Trade: Ceiling Start Date: 02-Jul-2026 End Date: 28-Jul-2026
Note on ZT117: Activity Name: Finishes - Zone 2 Phase: Interiors Location: Finishes - Zone 2 Trade: Finishes Start Date: 29-Jul-2026 End Date: 09-Sep-2026
Note on WI121: Activity Name: Frame Walls & Ceilings - Zone 3 Phase: Interiors Location: Finishes - Zone 3 Trade: Drywall Start Date: 01-May-2026 End Date: 14-May-2026
Note on YC121: Activity Name: In-wall Blocking - Zone 3 Phase: Interiors Location: Finishes - Zone 3 Trade: Mechanical Start Date: 16-Jun-2026 End Date: 17-Jun-2026
Note on YE121: Activity Name: Two Side Walls - Zone 3 Phase: Interiors Location: Finishes - Zone 3 Trade: Drywall Start Date: 18-Jun-2026 End Date: 26-Jun-2026
Note on YP121: Activity Name: Tape & Float - Zone 3 Phase: Interiors Location: Finishes - Zone 3 Trade: Drywall Start Date: 29-Jun-2026 End Date: 13-Jul-2026
Note on ZE121: Activity Name: Install ACT Grid - Zone 1 Phase: Interiors Location: Finishes - Zone 3 Trade: Mechanical Start Date: 14-Jul-2026 End Date: 20-Jul-2026
Note on ZL121: Activity Name: Ceiling Trim Out - Zone 1 Phase: Interiors Location: Finishes - Zone 3 Trade: Ceiling Start Date: 21-Jul-2026 End Date: 29-Jul-2026
Note on ZU121: Activity Name: Ceiling Inspection - Zone 1 Phase: Interiors Location: Finishes - Zone 3 Trade: Inspector Start Date: 30-Jul-2026 End Date: 30-Jul-2026
Note on ZV121: Activity Name: Close Ceilings - Zone 3 Phase: Interiors Location: Finishes - Zone 3 Trade: Ceiling Start Date: 31-Jul-2026 End Date: 04-Aug-2026
Note on AAA121: Activity Name: Finishes - Zone 3 Phase: Interiors Location: Finishes - Zone 3 Trade: Finishes Start Date: 05-Aug-2026 End Date: 23-Sep-2026
Note on WW125: Activity Name: Frame Walls & Ceilings - Zone 4 Phase: Interiors Location: Finishes - Zone 4 Trade: Drywall Start Date: 15-May-2026 End Date: 29-May-2026
Note on YQ125: Activity Name: In-wall Blocking - Zone 4 Phase: Interiors Location: Finishes - Zone 4 Trade: Mechanical Start Date: 30-Jun-2026 End Date: 01-Jul-2026
Note on YS125: Activity Name: Two Side Walls - Zone 4 Phase: Interiors Location: Finishes - Zone 4 Trade: Drywall Start Date: 02-Jul-2026 End Date: 13-Jul-2026
Note on ZE125: Activity Name: Tape & Float - Zone 4 Phase: Interiors Location: Finishes - Zone 4 Trade: Drywall Start Date: 14-Jul-2026 End Date: 27-Jul-2026
Note on ZS125: Activity Name: Install ACT Ceilings - Zone 4 Phase: Interiors Location: Finishes - Zone 4 Trade: Ceiling Start Date: 28-Jul-2026 End Date: 30-Jul-2026
Note on ZV125: Activity Name: Install Hard Ceilings - Zone 4 Phase: Interiors Location: Finishes - Zone 4 Trade: Ceiling Start Date: 31-Jul-2026 End Date: 25-Aug-2026
Note on AAV125: Activity Name: Finishes - Zone 4 Phase: Interiors Location: Finishes - Zone 4 Trade: Finishes Start Date: 26-Aug-2026 End Date: 07-Oct-2026
Note on XN129: Activity Name: Frame Walls & Ceilings - Zone 5 Phase: Interiors Location: Finishes - Zone 5 Trade: Drywall Start Date: 01-Jun-2026 End Date: 12-Jun-2026
Note on ZF129: Activity Name: In-wall Blocking - Zone 5 Phase: Interiors Location: Finishes - Zone 5 Trade: Mechanical Start Date: 15-Jul-2026 End Date: 16-Jul-2026
Note on ZH129: Activity Name: Two Side Walls - Zone 5 Phase: Interiors Location: Finishes - Zone 5 Trade: Drywall Start Date: 17-Jul-2026 End Date: 27-Jul-2026
Note on ZS129: Activity Name: Tape & Float - Zone 5 Phase: Interiors Location: Finishes - Zone 5 Trade: Drywall Start Date: 28-Jul-2026 End Date: 10-Aug-2026
Note on AAG129: Activity Name: Install ACT Ceilings - Zone 5 Phase: Interiors Location: Finishes - Zone 5 Trade: Ceiling Start Date: 11-Aug-2026 End Date: 13-Aug-2026
Note on AAJ129: Activity Name: Install Hard Lid Ceilings - Zone 5 Phase: Interiors Location: Finishes - Zone 5 Trade: Ceiling Start Date: 14-Aug-2026 End Date: 09-Sep-2026
Note on ABK129: Activity Name: Finishes - Zone 5 Phase: Interiors Location: Finishes - Zone 5 Trade: Finishes Start Date: 10-Sep-2026 End Date: 21-Oct-2026
Note on YB133: Activity Name: Frame Walls & Ceilings - Zone 6 Phase: Interiors Location: Finishes - Zone 6 Trade: Drywall Start Date: 15-Jun-2026 End Date: 26-Jun-2026
Note on ZT133: Activity Name: In-wall Blocking - Zone 6 Phase: Interiors Location: Finishes - Zone 6 Trade: Mechanical Start Date: 29-Jul-2026 End Date: 30-Jul-2026
Note on ZV133: Activity Name: Two Side Walls - Zone 6 Phase: Interiors Location: Finishes - Zone 6 Trade: Drywall Start Date: 31-Jul-2026 End Date: 10-Aug-2026
Note on AAG133: Activity Name: Tape & Float - Zone 6 Phase: Interiors Location: Finishes - Zone 6 Trade: Drywall Start Date: 11-Aug-2026 End Date: 24-Aug-2026
Note on AAU133: Activity Name: Install Ceilings - Zone 6 Phase: Interiors Location: Finishes - Zone 6 Trade: Ceiling Start Date: 25-Aug-2026 End Date: 27-Aug-2026
Note on AAX133: Activity Name: Install Hard Lid Ceilings - Zone 6 Phase: Interiors Location: Finishes - Zone 6 Trade: Ceiling Start Date: 28-Aug-2026 End Date: 23-Sep-2026
Note on ABY133: Activity Name: Finishes - Zone 6 Phase: Interiors Location: Finishes - Zone 6 Trade: Finishes Start Date: 24-Sep-2026 End Date: 04-Nov-2026
Note on AAH137: Activity Name: Finishes In Courtyard - Zone 7A Phase: Interiors Location: Finishes - Zone 7A Trade: Finishes Start Date: 12-Aug-2026 End Date: 04-Feb-2027
Note on TQ138: Activity Name: Finishes In Courtyard - Zone 7B Phase: Interiors Location: Finishes - Zone 7B Trade: Finishes Start Date: 20-Feb-2026 End Date: 11-Aug-2026
Note on OC139: Activity Name: Install Housekeeping Pads - Zone 1 Mechanical Room Phase: Interiors Location: Rough-In - Mechanical Room Trade: Mechanical Start Date: 29-Sep-2025 End Date: 03-Oct-2025
Note on YB139: Activity Name: Install ATS - Zone 1 Mechanical Room Phase: Interiors Location: Rough-In - Mechanical Room Trade: Mechanical Start Date: 15-Jun-2026 End Date: 26-Jun-2026
Note on YP139: Activity Name: Set/Install CHWP (3) - Zone 1 Mechanical Room Phase: Interiors Location: Rough-In - Mechanical Room Trade: Mechanical Start Date: 29-Jun-2026 End Date: 20-Jul-2026
Note on ZL139: Activity Name: Set/Install VFD's - Zone 1 Mechanical Room Phase: Interiors Location: Rough-In - Mechanical Room Trade: Mechanical Start Date: 21-Jul-2026 End Date: 17-Aug-2026
Note on YB140: Activity Name: Install Boilers - Zone 1 Mechanical Room Phase: Interiors Location: Rough-In - Mechanical Room Trade: Mechanical Start Date: 15-Jun-2026 End Date: 26-Jun-2026
Note on YP140: Activity Name: Set/Install HWP (3) - Zone 1 Mechanical Room Phase: Interiors Location: Rough-In - Mechanical Room Trade: Mechanical Start Date: 29-Jun-2026 End Date: 20-Jul-2026
Note on YB141: Activity Name: Install Electrical Switchgear - Zone 1 Mechanical Room Phase: Interiors Location: Rough-In - Mechanical Room Trade: Electrical Start Date: 15-Jun-2026 End Date: 06-Jul-2026
Note on VF145: Activity Name: Install AHU 7 (Roof) - Zone 1 Phase: Interiors Location: Rough-In - Zone 1 Trade: Mechanical Start Date: 02-Apr-2026 End Date: 09-Apr-2026
Note on VU145: Activity Name: In-wall MEP Rough-in - Zone 1 Phase: Interiors Location: Rough-In - Zone 1 Trade: MEP Start Date: 17-Apr-2026 End Date: 14-May-2026
Note on WW145: Activity Name: In-wall MEP Inspections - Zone 1 Phase: Interiors Location: Rough-In - Zone 1 Trade: Inspector Start Date: 15-May-2026 End Date: 15-May-2026
Note on VU146: Activity Name: OH MEPF Rough-in - Zone 1 Phase: Interiors Location: Rough-In - Zone 1 Trade: MEPF Start Date: 17-Apr-2026 End Date: 14-May-2026
Note on WW146: Activity Name: OH MEPF Inspections - Zone 1 Phase: Interiors Location: Rough-In - Zone 1 Trade: Inspector Start Date: 15-May-2026 End Date: 15-May-2026
Note on VN150: Activity Name: Install AHU 6 (Roof) - Zone 2 Phase: Interiors Location: Rough-In - Zone 2 Trade: Mechanical Start Date: 10-Apr-2026 End Date: 16-Apr-2026
Note on WI150: Activity Name: In-wall MEP Rough-in - Zone 2 Phase: Interiors Location: Rough-In - Zone 2 Trade: MEP Start Date: 01-May-2026 End Date: 29-May-2026
Note on XN150: Activity Name: In-wall MEP Inspections - Zone 2 Phase: Interiors Location: Rough-In - Zone 2 Trade: Inspector Start Date: 01-Jun-2026 End Date: 01-Jun-2026
Note on WI151: Activity Name: OH MEPF Rough-in - Zone 2 Phase: Interiors Location: Rough-In - Zone 2 Trade: MEPF Start Date: 01-May-2026 End Date: 29-May-2026
Note on XN151: Activity Name: OH MEPF Inspections - Zone 2 Phase: Interiors Location: Rough-In - Zone 2 Trade: Inspector Start Date: 01-Jun-2026 End Date: 01-Jun-2026
Note on VU155: Activity Name: Install AHU 5 (Roof) - Zone 3 Phase: Interiors Location: Rough-In - Zone 3 Trade: Mechanical Start Date: 17-Apr-2026 End Date: 23-Apr-2026
Note on WW155: Activity Name: In-wall MEP Rough-in - Zone 3 Phase: Interiors Location: Rough-In - Zone 3 Trade: MEP Start Date: 15-May-2026 End Date: 12-Jun-2026
Note on YB155: Activity Name: In-wall MEP Inspections - Zone 3 Phase: Interiors Location: Rough-In - Zone 3 Trade: Inspector Start Date: 15-Jun-2026 End Date: 15-Jun-2026
Note on WW156: Activity Name: OH MEPF Rough-in - Zone 3 Phase: Interiors Location: Rough-In - Zone 3 Trade: MEPF Start Date: 15-May-2026 End Date: 12-Jun-2026
Note on YB156: Activity Name: OH MEPF Inspections - Zone 3 Phase: Interiors Location: Rough-In - Zone 3 Trade: Inspector Start Date: 15-Jun-2026 End Date: 15-Jun-2026
Note on WB160: Activity Name: Install AHU 3 & 4 (Roof) - Zone 4 Phase: Interiors Location: Rough-In - Zone 4 Trade: Mechanical Start Date: 24-Apr-2026 End Date: 01-May-2026
Note on XN160: Activity Name: In-wall MEP Rough-in - Zone 4 Phase: Interiors Location: Rough-In - Zone 4 Trade: MEP Start Date: 01-Jun-2026 End Date: 26-Jun-2026
Note on YP160: Activity Name: In-wall MEP Inspections - Zone 4 Phase: Interiors Location: Rough-In - Zone 4 Trade: Inspector Start Date: 29-Jun-2026 End Date: 29-Jun-2026
Note on XN161: Activity Name: OH MEPF Rough-in - Zone 4 Phase: Interiors Location: Rough-In - Zone 4 Trade: MEPF Start Date: 01-Jun-2026 End Date: 26-Jun-2026
Note on YP161: Activity Name: OH MEPF Inspections - Zone 4 Phase: Interiors Location: Rough-In - Zone 4 Trade: Inspector Start Date: 29-Jun-2026 End Date: 29-Jun-2026
Note on WL165: Activity Name: Install AHU 1 (Roof) - Zone 5 Phase: Interiors Location: Rough-In - Zone 5 Trade: Mechanical Start Date: 04-May-2026 End Date: 08-May-2026
Note on YB165: Activity Name: In-wall MEP Rough-in - Zone 5 Phase: Interiors Location: Rough-In - Zone 5 Trade: MEP Start Date: 15-Jun-2026 End Date: 13-Jul-2026
Note on ZE165: Activity Name: In-wall MEP Inspections - Zone 5 Phase: Interiors Location: Rough-In - Zone 5 Trade: Inspector Start Date: 14-Jul-2026 End Date: 14-Jul-2026
Note on YB166: Activity Name: OH MEPF Rough-in - Zone 5 Phase: Interiors Location: Rough-In - Zone 5 Trade: MEPF Start Date: 15-Jun-2026 End Date: 13-Jul-2026
Note on ZE166: Activity Name: OH MEPF Inspections - Zone 5 Phase: Interiors Location: Rough-In - Zone 5 Trade: Inspector Start Date: 14-Jul-2026 End Date: 14-Jul-2026
Note on WS170: Activity Name: Install AHU 2 (Roof) - Zone 6 Phase: Interiors Location: Rough-In - Zone 6 Trade: Mechanical Start Date: 11-May-2026 End Date: 15-May-2026
Note on YP170: Activity Name: In-wall MEP Rough-in - Zone 6 Phase: Interiors Location: Rough-In - Zone 6 Trade: MEP Start Date: 29-Jun-2026 End Date: 27-Jul-2026
Note on ZS170: Activity Name: In-wall MEP Inspections - Zone 6 Phase: Interiors Location: Rough-In - Zone 6 Trade: Inspector Start Date: 28-Jul-2026 End Date: 28-Jul-2026
Note on YP171: Activity Name: OH MEPF Rough-in - Zone 6 Phase: Interiors Location: Rough-In - Zone 6 Trade: MEPF Start Date: 29-Jun-2026 End Date: 27-Jul-2026
Note on ZS171: Activity Name: OH MEPF Inspections - Zone 6 Phase: Interiors Location: Rough-In - Zone 6 Trade: Inspector Start Date: 28-Jul-2026 End Date: 28-Jul-2026
Note on VN175: Activity Name: Test & Balance Phase: Interiors Location: Testing Trade: Electrical Start Date: 10-Apr-2026 End Date: 29-Sep-2026
Note on AJN175: Activity Name: Owner Test & Balance Phase: Interiors Location: Testing Trade: Owner Start Date: 09-Apr-2027 End Date: 02-Jul-2027
Note on AAU176: Activity Name: Testing All Systems Phase: Interiors Location: Testing Trade: All Start Date: 25-Aug-2026 End Date: 17-Nov-2026
Note on ABZ178: Activity Name: Weather Days (3 days per month) Phase: Interiors Location: Weather Days Trade: All Start Date: 25-Sep-2026 End Date: 04-Jan-2027
Note on OJ179: Activity Name: Steel Framing & Decking - Zone 1 Phase: Structure Location: Above Grade Structures- Zone 1 Trade: Steel Start Date: 06-Oct-2025 End Date: 17-Oct-2025
Note on OX180: Activity Name: Steel Framing & Decking - Zone 2 Phase: Structure Location: Above Grade Structures- Zone 2 Trade: Steel Start Date: 20-Oct-2025 End Date: 31-Oct-2025
Note on PL181: Activity Name: Steel Framing & Decking - Zone 3 Phase: Structure Location: Above Grade Structures- Zone 3 Trade: Steel Start Date: 03-Nov-2025 End Date: 14-Nov-2025
Note on PZ182: Activity Name: Steel Framing & Decking - Zone 4 Phase: Structure Location: Above Grade Structures- Zone 4 Trade: Steel Start Date: 17-Nov-2025 End Date: 02-Dec-2025
Note on QP183: Activity Name: Steel Framing & Decking - Zone 5 Phase: Structure Location: Above Grade Structures- Zone 5 Trade: Steel Start Date: 03-Dec-2025 End Date: 16-Dec-2025
Note on RD184: Activity Name: Steel Framing & Decking - Zone 6 Phase: Structure Location: Above Grade Structures- Zone 6 Trade: Steel Start Date: 17-Dec-2025 End Date: 07-Jan-2026
Note on HT185: Activity Name: Clear & Grub - Building Foot Print Phase: Sitework Location: Clear & Grub Trade: Site Sub Start Date: 17-Apr-2025 End Date: 22-May-2025
Note on JD186: Activity Name: Excavate - Entire Site Phase: Sitework Location: Excavation Trade: Site Sub Start Date: 23-May-2025 End Date: 28-Jul-2025
Note on YW187: Activity Name: Hardscape/Landscaping Phase: Sitework Location: Hardscape/Landscaping Trade: Site Sub Start Date: 06-Jul-2026 End Date: 23-Dec-2026
Note on JD188: Activity Name: Site Paving Phase: Sitework Location: Site Paving Trade: Site Sub Start Date: 23-May-2025 End Date: 30-Dec-2025
Note on HF189: Activity Name: Install All Site Utilities Phase: Sitework Location: Site Utilities Trade: Site Sub Start Date: 03-Apr-2025 End Date: 18-Jul-2025
Note on NO190: Activity Name: F/R/P Slab on Grade - Zone 1 Phase: Foundations Location: Slabs - Zone 1 Trade: Concrete Start Date: 15-Sep-2025 End Date: 03-Oct-2025
Note on OR191: Activity Name: F/R/P Slab on Grade - Zone 2 Phase: Foundations Location: Slabs - Zone 2 Trade: Concrete Start Date: 14-Oct-2025 End Date: 03-Nov-2025
Note on PT192: Activity Name: F/R/P Slab on Grade - Zone 3 Phase: Foundations Location: Slabs - Zone 3 Trade: Concrete Start Date: 11-Nov-2025 End Date: 24-Nov-2025
Note on QX193: Activity Name: F/R/P Slab on Grade - Zone 4 Phase: Foundations Location: Slabs - Zone 4 Trade: Concrete Start Date: 11-Dec-2025 End Date: 29-Dec-2025
Note on SV194: Activity Name: F/R/P Slab on Grade - Zone 5 Phase: Foundations Location: Slabs - Zone 5 Trade: Concrete Start Date: 30-Jan-2026 End Date: 19-Feb-2026
Note on UL195: Activity Name: F/R/P Slab on Grade - Zone 6 Phase: Foundations Location: Slabs - Zone 6 Trade: Concrete Start Date: 13-Mar-2026 End Date: 02-Apr-2026
Note on LK196: Activity Name: Underground MEP - Mechanical Yard Phase: Foundations Location: Underground Structures- Mechanical Yard Trade: MEP Start Date: 21-Jul-2025 End Date: 13-Oct-2025
Note on LK197: Activity Name: Underground MEP - Zone 1 Phase: Foundations Location: Underground Structures- Zone 1 Trade: MEP Start Date: 21-Jul-2025 End Date: 29-Aug-2025
Note on NB198: Activity Name: Underground MEP - Zone 2 Phase: Foundations Location: Underground Structures- Zone 2 Trade: MEP Start Date: 02-Sep-2025 End Date: 13-Oct-2025
Note on OR199: Activity Name: Underground MEP - Zone 3 Phase: Foundations Location: Underground Structures- Zone 3 Trade: MEP Start Date: 14-Oct-2025 End Date: 10-Nov-2025
Note on PT200: Activity Name: Underground MEP - Zone 4 Phase: Foundations Location: Underground Structures- Zone 4 Trade: MEP Start Date: 11-Nov-2025 End Date: 10-Dec-2025
Note on QX201: Activity Name: Underground MEP - Zone 5 Phase: Foundations Location: Underground Structures- Zone 5 Trade: MEP Start Date: 11-Dec-2025 End Date: 29-Jan-2026
Note on SV202: Activity Name: Underground MEP - Zone 6 Phase: Foundations Location: Underground Structures- Zone 6 Trade: MEP Start Date: 30-Jan-2026 End Date: 12-Mar-2026
Note on UL203: Activity Name: Underground MEP - Zone 7A Phase: Foundations Location: Underground Structures- Zone 7A Trade: MEP Start Date: 13-Mar-2026 End Date: 02-Apr-2026
Note on VJ204: Activity Name: Underground MEP - Zone 7B Phase: Foundations Location: Underground Structures- Zone 7B Trade: MEP Start Date: 06-Apr-2026 End Date: 24-Apr-2026
Note on PZ205: Activity Name: Exterior Finishes - East Elevation Phase: Exteriors Location: East Elevation Trade: Exterior Sub Start Date: 17-Nov-2025 End Date: 28-Jan-2026
Note on RD206: Activity Name: Exterior Finishes - North Elevation Phase: Exteriors Location: North Elevation Trade: Exterior Sub Start Date: 17-Dec-2025 End Date: 25-Feb-2026
Note on RZ207: Activity Name: Install Roofing Phase: Exteriors Location: Roofing Trade: Roof Sub Start Date: 08-Jan-2026 End Date: 01-Apr-2026
Note on SG208: Activity Name: Exterior Finishes - South Elevation Phase: Exteriors Location: South Elevation Trade: Exterior Sub Start Date: 15-Jan-2026 End Date: 18-Mar-2026
Note on RD209: Activity Name: Exterior Finishes - West Elevation Phase: Exteriors Location: West Elevation Trade: Exterior Sub Start Date: 17-Dec-2025 End Date: 25-Feb-2026

## CFA - Legends
Design |  | Exteriors |  | Foundations |  | Interiors |  | Material Procurement |  | McGough Standards |  | Milestones |  | Permitting |  | Sitework |  | Structure |  | Structure/Foundations |  | Subcontractor Procurement |  | Submittals
[14 empty] | PERM-1 | Permitting - TXDot | [8 empty] | SUBM-1 | Submit Curtainwall Shop Drawings
McGough |  | Exterior Sub |  | Concrete |  | All |  | McGough |  | Exec |  | McGough |  |  |  | Site Sub |  | Steel |  | All Structurals Subs |  | McGough |  | SUBM-10 | Submit Electrical Switchgear Shop Drawings
DM-1 | DD 1 Safety & Risk Assessment | FINISH-1 | Exterior Finishes - North Elevation | FOUN-1 | F/R/P Slab on Grade - Zone 1 | CX-1 | Commissioning All Systems | PROCU-1 | Procure Transformer (by others) | MCG-1 | Demolition | GMP | GMP Issued |  |  | SITE-1 | Clear & Grub - Building Foot Print | STRUC-2 | Steel Framing & Decking - Zone 1 | STRUC-1 | Structural Foundations - Entire Site | CONT-1 | Issue Contract to Curtainwall Sub | SUBM-11 | Submit ATS Shop Drawings
DM-10 | Cost Reconciliation |  |  |  |  | CX-2 | Testing All Systems | PROCU-10 | Procure & Fabricate Security Glazing | MCG-10 | Masonry | MOB | Mobilization |  |  | SITE-2 | Excavate - Entire Site |  |  |  |  | CONT-2 | Issue Contract to Store Fronts Sub | SUBM-12 | Submit Boilers Shop Drawings
DM-11 | Owner Comments Due | Roof Sub |  | MEP |  | CX-3 | Weather Days (3 days per month) | PROCU-11 | Procure & Fabricate Overhead Door (6) | MCG-11 | Hardscape and Landscaping | SC | Substantial Completion |  |  | SITE-3 | Install All Site Utilities |  |  |  |  | CONT-3 | Issue Contract to Structural Steel Sub | SUBM-13 | Submit Antiligature Door Hardware/Kingsway Kits Shop Drawings
DM-12 | Owner DD & GMP Signoff | FINISH-2 | Install Roofing | FOUND-2 | Underground MEP - Zone 1 |  |  | PROCU-12 | Procure & Fabricate Boilers | MCG-12 | Subcontract Procurement |  |  |  |  | SITE-4 | Site Paving |  |  |  |  | CONT-4 | Issue Contract to Security Glazing Sub | SUBM-14 | Owner Approve Curtainwall Shop Drawings
DM-13 | Issue Complete CD Package |  |  |  |  | Ceiling |  | PROCU-13 | Procure & Fabricate Antiligature Door Hardware/Kingsway Kits | MCG-13 | Site Utilities |  |  |  |  | SITE-5 | Hardscape/Landscaping |  |  |  |  | CONT-5 | Issue Contract to Overhead Door Sub | SUBM-15 | Owner Approve Store Front Shop Drawings
DM-2 | DD 2 |  |  |  |  | C-1 | Ceiling Trim Out - Zone 1 | PROCU-14 | Procure & Fabricate Kitchen Equipment | MCG-14 | Building Enclosure | [10 empty] | CONT-6 | Issue Contract to Mechanical Sub | SUBM-16 | Owner Approve Security Glazing Shop Drawings
DM-3 | DD 3 |  |  |  |  | C-2 | Close Ceiling - Zone 1 | PROCU-2 | Procure & Fabricate Generator | MCG-15 | Testing and Commissioning | [10 empty] | CONT-7 | Issue Contract to Electrical Sub | SUBM-17 | Owner Approve Steel Structure Shop Drawings
DM-4 | DD 4 |  |  |  |  | C-3 | Install ACT Ceilings - Zone 2 | PROCU-3 | Procure & Fabricate Electrical Switchgear | MCG-2 | Earthworks and Support of Excavation | [10 empty] | CONT-8 | Issue Contract to Kitchen Equipment Sub | SUBM-18 | Owner Approve Overhead Door Shop Drawings
DM-5 | DD Package Submission Owner & Cost Estimator |  |  |  |  | C-4 | Install Ceilings - Zone 6 | PROCU-4 | Procure & Fabricate ATS | MCG-3 | Deep Foundations | [10 empty] | CONT-9 | Issue Contract to Antiligature Door Hardware/Kingsway Kits Sub | SUBM-19 | Owner Approve Chiller Shop Drawings
DM-6 | Early Site Utility, Grading, Foundation Package |  |  |  |  | C-5 | Install Hard Ceiling - Zone 2 | PROCU-5 | Procure & Fabricate AHU's | MCG-4 | Structural Foundations/Footings | [10 empty] | PRE-1 | Pre-Qual Curtainwall Sub | SUBM-2 | Submit Store Front Shop Drawings
DM-7 | Start CD Package |  |  |  |  | C-6 | Install Hard Lid Ceilings - Zone 5 | PROCU-6 | Procure & Fabricate Chillers | MCG-5 | Below Grade Structure | [10 empty] | PRE-2 | Pre-Qual Store Fronts Sub | SUBM-20 | Owner Approve AHU Shop Drawings
DM-8 | DD Cost Estimate Due | [6 empty] | PROCU-7 | Procure & Fabricate Structural Steel | MCG-6 | Above Grade Structure | [10 empty] | PRE-3 | Pre-Qual Structural Steel Sub | SUBM-21 | Owner Approve Generator Shop Drawings
DM-9 | DD Final Page Turn & Owner Sign-off |  |  |  |  | Concrete |  | PROCU-8 | Procure & Fabricate Curtainwall | MCG-7 | Vertical Transportation | [10 empty] | PRE-4 | Pre-Qual Security Glazing Sub | SUBM-22 | Owner Approve Kitchen Equipment Shop Drawings
[6 empty] | CO-1 | Cure Concrete Pad Sally Port - Mechanical Yard | PROCU-9 | Procure & Fabricate Store Fronts | MCG-8 | Rough-In | [10 empty] | PRE-5 | Pre-Qual Overhead Door Sub | SUBM-23 | Owner Approve Electrical Switchgear Shop Drawings
[6 empty] | CO-2 | F/R/P Concrete Pad Sally Port - Mechanical Yard |  |  | MCG-9 | Finishes | [10 empty] | PRE-6 | Pre-Qual Mechanical Sub | SUBM-24 | Owner Approve ATS Shop Drawings
[6 empty] | CO-3 | FF&E | [14 empty] | PRE-7 | Pre-Qual Electrical Sub | SUBM-25 | Owner Approve Boilers Shop Drawings
[10 empty] | McGough | [11 empty] | PRE-8 | Pre-Qual Kitchen Equipment Sub | SUBM-26 | Owner Approve Antiligature Door Hardware/Kingsway Kits Shop Drawings
[6 empty] | Drywall |  |  |  | MCG-16 | Notice to Proceed | [10 empty] | PRE-9 | Pre-Qual Antiligature Door Hardware/Kingsway Kits Sub | SUBM-3 | Submit Security Glazing Shop Drawings
[6 empty] | F-1 | Frame Walls & Ceilings - Zone 1 |  |  | MCG-17 | Below Grade Structure Start | [12 empty] | SUBM-4 | Submit Steel Structure Shop Drawings
[6 empty] | F-2 | Tape & Float - Zone 1 |  |  | MCG-18 | Below Grade Structure Complete | [12 empty] | SUBM-5 | Submit Overhead Door Shop Drawings
[6 empty] | F-3 | Two Side Walls - Zone 1 |  |  | MCG-19 | Vertical Transportation Start | [12 empty] | SUBM-6 | Submit Chiller Shop Drawings
[10 empty] | MCG-20 | Temp Power | [12 empty] | SUBM-7 | Submit AHU Shop Drawings
[6 empty] | Electrical |  |  |  | MCG-21 | Excavation Start | [12 empty] | SUBM-8 | Submit Generator Shop Drawings
[6 empty] | E-1 | Install Electrical Switchgear - Zone 1 Mechanical Room |  |  | MCG-22 | Excavation Complete | [12 empty] | SUBM-9 | Submit Kitchen Equipment Shop Drawings
[6 empty] | E-2 | Set Generator - Mechanical Yard |  |  | MCG-23 | Above Grade Structure Start
[6 empty] | E-3 | Test & Balance |  |  | MCG-24 | Building Temporarily Enclosed
[10 empty] | MCG-25 | Above Grade Structure Complete
[6 empty] | Finishes |  |  |  | MCG-26 | Building Envelope Start
[6 empty] | FI-1 | Finishes - Zone 1 |  |  | MCG-27 | Building Envelope Complete
[10 empty] | MCG-28 | MEP Rough-In Start
[6 empty] | Inspector |  |  |  | MCG-29 | Permanent Power
[6 empty] | IN-1 | Ceiling Inspection - Zone 1 |  |  | MCG-30 | Start Drywall
[6 empty] | IN-2 | In-wall MEP Inspections - Zone 1 |  |  | MCG-31 | Courtyard Start
[6 empty] | IN-3 | OH MEPF Inspections - Zone 1 |  |  | MCG-32 | Building Finishes Start
[10 empty] | MCG-33 | Drywall Complete
[6 empty] | Kitchen |  |  |  | MCG-34 | Courtyard Finish
[6 empty] | K-1 | Install Kitchen Equipment |  |  | MCG-35 | Final Acceptance
[6 empty] | MEP |  |  |  | Tracking
[6 empty] | MEP-1 | In-wall MEP Rough-in - Zone 1 |  |  | MCG-36 | Subcontractor Procurement Start
[10 empty] | MCG-37 | Material Purchase Start
[6 empty] | MEPF |  |  |  | MCG-38 | Mobilization Key Activity
[6 empty] | MEPF-1 | OH MEPF Rough-in - Zone 1 |  |  | MCG-39 | Demolition Start
[10 empty] | MCG-40 | Demolition Complete
[6 empty] | Mechanical |  |  |  | MCG-41 | Deep Structural Foundations Start
[6 empty] | M-1 | Hook-up/Final Connections Chillers - Mechanical Yard |  |  | MCG-42 | Deep Structural Foundations Complete
[6 empty] | M-10 | Set Chillers (3) - Mechanical Yard |  |  | MCG-43 | Vertical Transportation Start
[6 empty] | M-11 | Set Fuel Tank - Mechanical Yard |  |  | MCG-44 | Vertical Transportation Complete
[6 empty] | M-12 | Set/Install CHWP (3) - Zone 1 Mechanical Room |  |  | MCG-45 | Site Survey Start
[6 empty] | M-13 | Set/Install HWP (3) - Zone 1 Mechanical Room |  |  | MCG-46 | Utilities Start
[6 empty] | M-14 | Set/Install VFD's - Zone 1 Mechanical Room |  |  | MCG-47 | Utilities Start
[6 empty] | M-2 | Hook-up/Final Connections Generator - Mechanical Yard |  |  | MCG-48 | Site Survey Finish
[6 empty] | M-3 | In-wall Blocking - Zone 1 |  |  | MCG-49 | Mobilization Start
[6 empty] | M-4 | Install ACT Grid - Zone 1 |  |  | MCG-50 | Mobilization Finish
[6 empty] | M-5 | Install AHU 7 (Roof) - Zone 1 |  |  | MCG-51 | Utilities Complete
[6 empty] | M-6 | Install ATS - Zone 1 Mechanical Room |  |  | MCG-52 | Permitting Finish
[6 empty] | M-7 | Install Boilers - Zone 1 Mechanical Room |  |  | MCG-53 | Permitting Start
[6 empty] | M-8 | Install CMU Walls - Mechanical Yard |  |  | MCG-54 | Excavation Start
[6 empty] | M-9 | Install Housekeeping Pads - Zone 1 Mechanical Room |  |  | MCG-55 | Subcontractor Procurement Finish
[10 empty] | MCG-56 | Structural Foundations Start
[6 empty] | Owner |  |  |  | MCG-57 | Underground Structures Start Rough In
[6 empty] | OW-1 | Owner Test & Balance |  |  | MCG-58 | Excavation Complete
[10 empty] | MCG-59 | Structural Foundations Complete
[10 empty] | MCG-60 | Above Grade Structures Start
[10 empty] | MCG-61 | Building Temporarily Enclosed
[10 empty] | MCG-62 | Building Envelope Start
[10 empty] | MCG-63 | Masonry Start
[10 empty] | MCG-64 | Above Grade Structures Complete
[10 empty] | MCG-65 | Material Purchase Finish
[10 empty] | MCG-66 | Building Envelope Complete
[10 empty] | MCG-67 | Masonry Complete
[10 empty] | MCG-68 | Rough-In Start
[10 empty] | MCG-69 | Underground Structures Complete Rough In
[10 empty] | MCG-70 | Finishes Start
[10 empty] | MCG-71 | Rough-In Complete
[10 empty] | MCG-72 | Commissioning Start
[10 empty] | MCG-73 | Finishes Complete
[10 empty] | MCG-74 | Testing Complete
[10 empty] | MCG-75 | Building Water Testing
[10 empty] | MCG-76 | Testing Start
[10 empty] | MCG-77 | Equipment Startup
[10 empty] | MCG-78 | Sitework(Land/Hardscape) Start
[10 empty] | MCG-79 | Sitework(Land/Hardscape) Complete
[10 empty] | MCG-80 | Commissioning Complete