## TASK
Activity ID | Activity Status | WBS Code | Activity Name | (*)Start | (*)Finish | (*)Total Float(d)
CHI05-05-FC-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,1 | Site Secured Finish (August 04, 2025) |  | 2025-08-04 17:00 | 0
CHI05-05-NTP-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,1 | Notice To Proceed | 2024-10-02 08:00 |  | 0
CHI05-03-L1CX-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Start L1 CX (Red Tag) for Colo 3 | 2025-01-22 08:00 |  | 95
CHI05-03-ROJ-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Complete Last ROJ Arrival for Colo 3 |  | 2025-01-02 17:00 | 119
CHI05-03-L2CX-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Start L2 CX (Yellow Tag) for Colo 3 | 2025-02-18 08:00 |  | 77
CHI05-03-L1CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Complete L1 Cx (All Red Tags/ROJ) for Colo 3 |  | 2025-03-07 17:00 | 63
CHI05-03-L2CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Complete L2 CX (Yellow Tag) for Colo 3 |  | 2025-05-06 17:00 | 52
CHI05-03-POW-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Power-ON Utility for Colo 3 |  | 2025-02-28 17:00 | 51
CHI05-03-L3CX-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Start L3 Cx (Green tag) for Colo 3 | 2025-03-26 08:00 |  | 56
CHI05-03-SSC-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Complete Phase 3 Security System Test for Colo 3 |  | 2025-07-10 17:00 | 17
CHI05-03-MEQ-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Start-up Mechanical Equipment for Colo 3 | 2025-01-22 08:00 |  | 72
CHI05-03-CSA-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Interior Finishes/CSA Complete for Colo 3 |  | 2025-03-25 17:00 | 56
CHI05-03-GEN-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Generators Ready Fuel for Colo 3 |  | 2024-10-02 17:00 | 109
CHI05-03-MEP-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | MEP Rough-in Complete for Colo 3 |  | 2025-02-11 17:00 | 76
CHI05-03-L3CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Complete L3 CX (Green Tag) for Colo 3 |  | 2025-05-27 17:00 | 38
CHI05-03-BAS-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Complete BAS SAT for Colo 3 |  | 2025-03-25 17:00 | 56
CHI05-03-EPMS-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Complete EPMS SAT for Colo 3 |  | 2025-03-25 17:00 | 56
CHI05-03-FIRE-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Complete Fire Alarm for Colo 3 |  | 2025-03-25 17:00 | 56
CHI05-03-L4CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Complete L4 Cx (Blue Tag) for Colo 3 |  | 2025-06-30 17:00 | 17
CHI05-03-L5CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Complete L5/IST (White Tag) for Colo 3 |  | 2025-07-02 17:00 | 17
CHI05-03-RNI-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Complete Ready for Network Install (RNI) For Colo 3 |  | 2025-06-03 17:00 | 38
CHI05-03-CO-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,2 | Complete CorpNet For Colo 3 |  | 2025-05-27 17:00 | 48
CHI05-05-ROJ-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Complete Last ROJ Arrival for Colo 5 |  | 2025-01-02 17:00 | 119
CHI05-05-L2CX-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Start L2 CX (Yellow Tag) for Colo 5 | 2025-02-18 08:00 |  | 77
CHI05-05-L1CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Complete L1 Cx (All Red Tags/ROJ) for Colo 5 |  | 2025-02-25 17:00 | 49
CHI05-05-L2CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Complete L2 CX (Yellow Tag) for Colo 5 |  | 2025-04-17 17:00 | 39
CHI05-05-POW-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Power-ON Utility for Colo 5 |  | 2025-02-28 17:00 | 73
CHI05-05-L3CX-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Start L3 Cx (Green tag) for Colo 5 | 2025-03-03 08:00 |  | 73
CHI05-05-MEQ-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Start-up Mechanical Equipment for Colo 5 | 2024-12-26 08:00 |  | 97
CHI05-05-CSA-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Interior Finishes/CSA Complete for Colo 5 |  | 2025-03-13 17:00 | 64
CHI05-05-GEN-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Generators Ready Fuel for Colo 5 |  | 2024-10-08 17:00 | 112
CHI05-05-MEP-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | MEP Rough-in Complete for Colo 5 |  | 2025-01-08 17:00 | 100
CHI05-05-L3CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Complete L3 CX (Green Tag) for Colo 5 |  | 2025-04-30 17:00 | 35
CHI05-05-BAS-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Complete BAS SAT for Colo 5 |  | 2025-03-24 17:00 | 57
CHI05-05-EPMS-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Complete EPMS SAT for Colo 5 |  | 2025-03-24 17:00 | 57
CHI05-05-FIR-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Complete Fire Alarm for Colo 5 |  | 2025-03-24 17:00 | 57
CHI05-05-SSC-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Complete Phase 3 Security System Test for Colo 5 |  | 2025-06-13 17:00 | 35
CHI05-05-L4CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Complete L4 Cx (Blue Tag) for Colo 5 |  | 2025-06-04 17:00 | 35
CHI05-05-L5CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Complete L5/IST (White Tag) for Colo 5 |  | 2025-06-06 17:00 | 35
CHI05-05-L1CX-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Start L1 CX (Red Tag) for Colo 5 | 2025-01-21 08:00 |  | 74
CHI05-05-RNI-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Complete Ready for Network Install (RNI) For Colo 5 |  | 2025-05-07 17:00 | 56
CHI05-05-CO-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,3 | Complete CorpNet For Colo 5 |  | 2025-04-30 17:00 | 66
CHI05-04-ROJ-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Complete Last ROJ Arrival for Colo 4 |  | 2025-01-06 17:00 | 122
CHI05-04-L2CX-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Start L2 CX (Yellow Tag) for Colo 4 | 2025-02-18 08:00 |  | 82
CHI05-04-L1CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Complete L1 Cx (All Red Tags/ROJ) for Colo 4 |  | 2025-04-14 17:00 | 14
CHI05-04-L2CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Complete L2 CX (Yellow Tag) for Colo 4 |  | 2025-06-05 17:00 | 15
CHI05-04-POW-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Power-ON Utility for Colo 4 |  | 2025-02-28 17:00 | 58
CHI05-04-L3CX-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Start L3 Cx (Green tag) for Colo 4 | 2025-05-12 08:00 |  | 28
CHI05-04-SSC-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Complete Phase 3 Security System Test for Colo 4 |  | 2025-08-11 17:00 | 0
CHI05-04-MEQ-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Start-up Mechanical Equipment for Colo 4 | 2025-04-10 08:00 |  | 22
CHI05-04-CSA-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Interior Finishes/CSA Complete for Colo 4 |  | 2025-04-30 17:00 | 35
CHI05-04-GEN-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Generators Ready Fuel for Colo 4 |  | 2024-10-04 17:00 | 113
CHI05-04-MEP-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | MEP Rough-in Complete for Colo 4 |  | 2025-04-04 17:00 | 43
CHI05-04-L3CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Complete L3 CX (Green Tag) for Colo 4 |  | 2025-06-26 17:00 | 0
CHI05-04-BAS-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Complete BAS SAT for Colo 4 |  | 2025-05-09 17:00 | 28
CHI05-04-EPMS-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Complete EPMS SAT for Colo 4 |  | 2025-05-09 17:00 | 28
CHI05-04-FIRE-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Complete Fire Alarm for Colo 4 |  | 2025-05-09 17:00 | 28
CHI05-04-L4CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Complete L4 Cx (Blue Tag) for Colo 4 |  | 2025-07-31 17:00 | 0
CHI05-04-L5CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Complete L5/IST (White Tag) for Colo 4 |  | 2025-08-04 17:00 | 0
CHI05-04-L1CX-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Start L1 CX (Red Tag) for Colo 4 | 2025-01-22 08:00 |  | 72
CHI05-04-RNI-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Complete Ready for Network Install (RNI) For Colo 4 |  | 2025-07-03 17:00 | 21
CHI05-04-CO-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,4 | Complete CorpNet For Colo 4 |  | 2025-06-26 17:00 | 26
CHI05-02-L1CX-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Start L1 CX (Red Tag) for Colo 2 | 2025-01-22 08:00 |  | 95
CHI05-02-ROJ-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Complete Last ROJ Arrival for Colo 2 |  | 2025-02-10 17:00 | 92
CHI05-02-L2CX-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Start L2 CX (Yellow Tag) for Colo 2 | 2025-02-18 08:00 |  | 77
CHI05-02-L1CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Complete L1 Cx (All Red Tags/ROJ) for Colo 2 |  | 2025-02-05 17:00 | 90
CHI05-02-L2CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Complete L2 CX (Yellow Tag) for Colo 2 |  | 2025-04-14 17:00 | 47
CHI05-02-POW-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Power-ON Utility for Colo 2 |  | 2025-02-28 17:00 | 29
CHI05-02-L3CX-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Start L3 Cx (Green tag) for Colo 2 | 2025-03-03 08:00 |  | 73
CHI05-02-MEQ-S | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Start-up Mechanical Equipment for Colo 2 | 2024-12-27 08:00 |  | 96
CHI05-02-CSA-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Interior Finishes/CSA Complete for Colo 2 |  | 2025-02-21 17:00 | 78
CHI05-02-GEN-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Generators Ready Fuel for Colo 2 |  | 2024-09-30 17:00 | 122
CHI05-02-MEP-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | MEP Rough-in Complete for Colo 2 |  | 2025-01-16 17:00 | 94
CHI05-02-L3CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Complete L3 CX (Green Tag) for Colo 2 |  | 2025-04-30 17:00 | 35
CHI05-02-BAS-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Complete BAS SAT for Colo 2 |  | 2025-03-24 17:00 | 57
CHI05-02-EPMS-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Complete EPMS SAT for Colo 2 |  | 2025-03-24 17:00 | 57
CHI05-02-FIRE-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Complete Fire Alarm for Colo 2 |  | 2025-03-24 17:00 | 57
CHI05-02-SSC-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Complete Phase 3 Security System Test for Colo 2 |  | 2025-06-13 17:00 | 35
CHI05-02-L4CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Complete L4 Cx (Blue Tag) for Colo 2 |  | 2025-06-04 17:00 | 35
CHI05-02-L5CX-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Complete L5/IST (White Tag) for Colo 2 |  | 2025-06-06 17:00 | 35
CHI05-02-RNI-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Complete Ready for Network Install (RNI) For Colo 2 |  | 2025-05-07 17:00 | 56
CHI05-02-CO-F | Not Started | CHI05-PH2-FIT-BL-D5,2,2,5 | Complete CorpNet For Colo 2 |  | 2025-04-30 17:00 | 66
CHI05-02-01-MG-1000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG | 2024-10-07 08:00 | 2024-10-11 17:00 | 0
CHI05-02-01-MG-1010 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 1 - MG | 2024-10-09 08:00 | 2024-10-15 17:00 | 0
CHI05-02-01-MG-1020 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 | Overhead MEP Installation - COLO2 Cell 1 - MG | 2024-10-16 08:00 | 2024-10-29 17:00 | 48
CHI05-02-01-MG-1030 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 | Deliver AHU into Mech. Gallery - COLO2 Cell 1 - MG | 2024-10-30 08:00 | 2024-10-31 17:00 | 48
CHI05-02-01-MG-1040 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 | Install Walls and Primer Paint - COLO2 Cell 1 - MG | 2024-11-01 08:00 | 2024-11-14 17:00 | 48
CHI05-02-01-MG-1060 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 | Placing the AHU - COLO2 Cell 1 - MG | 2024-11-22 08:00 | 2024-11-26 12:00 | 94
CHI05-02-01-MG-1050 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 | Layout Ceiling and install Pencile Rod - COLO2 Cell 1 - MG | 2024-11-15 08:00 | 2024-11-15 17:00 | 98
CHI05-02-01-MG-1070 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 | Piping and Electrical Termination to AHUs - COLO2 Cell 1 - MG | 2024-11-26 13:00 | 2024-12-11 12:00 | 94
CHI05-02-01-MG-1080 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 | Pipe Testing - COLO2 Cell 1 - MG | 2024-12-11 13:00 | 2024-12-13 12:00 | 100
CHI05-02-01-MG-1090 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 | Install ceiling and Light Fittings - COLO2 Cell 1 - MG | 2024-12-13 13:00 | 2024-12-26 12:00 | 100
CHI05-02-01-MG-1100 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 | Trim out MEP - COLO2 Cell 1 - MG | 2024-12-18 13:00 | 2024-12-26 12:00 | 109
CHI05-02-01-MG-1045 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 | Post Wall Overhead MEP - COLO2 Cell 1 - MG | 2024-11-15 08:00 | 2024-12-06 17:00 | 94
CHI05-02-01-DH-1050 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH | 2024-12-30 08:00 | 2025-01-20 17:00 | 42
CHI05-02-01-DH-1000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 1 - DH | 2024-10-07 08:00 | 2024-10-22 17:00 | 68
CHI05-02-01-DH-1060 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 | HAC install and Rise - COLO2 Cell 1 - DH | 2024-12-19 08:00 | 2024-12-26 17:00 | 78
CHI05-02-01-DH-1070 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 | Termination at PDU & Busway- COLO2 Cell 1 - DH | 2024-12-19 08:00 | 2025-01-03 17:00 | 53
CHI05-02-01-DH-1010 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 | Security Screen Installation - COLO2 Cell 1 - DH | 2024-11-15 08:00 | 2024-11-19 17:00 | 48
CHI05-02-01-DH-1020 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 | Ceiling Grid and Tile - COLO2 Cell 1 - DH | 2024-11-20 08:00 | 2024-11-26 17:00 | 48
CHI05-02-01-DH-1040 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 | Install PDU's - COLO2 Cell 1 - DH | 2024-12-12 08:00 | 2024-12-18 17:00 | 48
CHI05-02-01-DH-1030 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 1 - DH | 2024-11-27 08:00 | 2024-12-11 17:00 | 48
CHI05-02-01-DH-1080 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 1 - DH | 2024-12-27 08:00 | 2025-01-10 17:00 | 78
CHI05-02-01-DH-1035 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 | HAC Placing - COLO2 Cell 1 - DH | 2024-12-12 08:00 | 2024-12-18 17:00 | 78
CHI05-02-01-DH-1090 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 | Finishes and Signage - COLO2 Cell 1 - DH | 2025-01-14 08:00 | 2025-01-20 17:00 | 123
CHI05-02-01-L1-1140 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 | Interior - L1 UPS - COLO2 Cell 1 | 2025-01-02 08:00 | 2025-01-02 17:00 | 87
CHI05-02-01-L1-1150 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 | Interior - L1 MSB - COLO2 Cell 1 | 2025-01-03 08:00 | 2025-01-03 17:00 | 93
CHI05-02-01-L1-1160 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 | Interior - L1 PDUs - COLO2 Cell 1 | 2025-01-06 08:00 | 2025-01-06 17:00 | 97
CHI05-02-01-L1-1170 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 | Interior - L1 AHUs - COLO2 Cell 1 | 2025-01-08 08:00 | 2025-01-08 17:00 | 105
CHI05-02-01-L1-1180 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 | Interior - L1 ATSs - COLO2 Cell 1 | 2025-01-07 08:00 | 2025-01-07 17:00 | 101
CHI05-02-01-L1-1190 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 | Interior - L1 Busway - COLO2 Cell 1 | 2025-01-07 08:00 | 2025-01-07 17:00 | 101
CHI05-02-01-L1-1250 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 | Interior - L1 ADP - COLO2 Cell 1 | 2025-01-06 08:00 | 2025-01-06 17:00 | 97
CHI05-02-01-L2-1260 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 | Interior - L2 UPS - COLO2 Cell 1 | 2025-02-25 08:00 | 2025-03-03 17:00 | 52
CHI05-02-01-L2-1270 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 | Interior - L2 MSB - COLO2 Cell 1 | 2025-03-04 08:00 | 2025-03-10 17:00 | 52
CHI05-02-01-L2-1280 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 | Interior - L2 PDUs - COLO2 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00 | 52
CHI05-02-01-L2-1290 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 | Interior - L2 AHUs - COLO2 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00 | 52
CHI05-02-01-L2-1300 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 | Interior - L2 ATSs - COLO2 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00 | 52
CHI05-02-01-L2-1310 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 | Interior - L2 Busway - COLO2 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00 | 52
CHI05-02-01-L2-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 | Interior - L2 ADP - COLO2 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00 | 52
CHI05-02-01-L3-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 | Interior - L3 UPS - COLO2 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00 | 37
CHI05-02-01-L3-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 | Interior - L3 MSB - COLO2 Cell 1 | 2025-04-01 08:00 | 2025-04-07 17:00 | 37
CHI05-02-01-L3-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 | Interior - L3 PDUs - COLO2 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00 | 42
CHI05-02-01-L3-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 | Interior - L3 AHUs - COLO2 Cell 1 | 2025-04-22 08:00 | 2025-04-28 17:00 | 37
CHI05-02-01-L3-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 | Interior - L3 ATSs - COLO2 Cell 1 | 2025-04-15 08:00 | 2025-04-21 17:00 | 37
CHI05-02-01-L3-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 | Interior - L3 Busway - COLO2 Cell 1 | 2025-04-15 08:00 | 2025-04-21 17:00 | 42
CHI05-02-01-L3-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 | Interior - L3 ADP - COLO2 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00 | 37
CHI05-02-01-ER-1000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 | Install Walls and Primer Paint - COLO2 Cell 1 - ER | 2024-10-07 08:00 | 2024-10-18 17:00 | 46
CHI05-02-01-ER-1020 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 1 - ER | 2024-10-23 08:00 | 2024-11-05 17:00 | 46
CHI05-02-01-ER-1010 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 | Install Upper Screens - COLO2 Cell 1 - ER | 2024-10-16 08:00 | 2024-10-22 17:00 | 46
CHI05-02-01-ER-1030 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 | Install Ceiling - COLO2 Cell 1 - ER | 2024-11-06 08:00 | 2024-11-08 17:00 | 46
CHI05-02-01-ER-1040 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER | 2024-11-19 08:00 | 2024-12-03 17:00 | 40
CHI05-02-01-ER-1050 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 | Installation of ADP & ATS - COLO2 Cell 1 - ER | 2024-11-29 08:00 | 2024-12-05 17:00 | 94
CHI05-02-01-ER-1070 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 | Installation of UPS Equipment - COLO2 Cell 1 - ER | 2024-12-04 08:00 | 2024-12-10 17:00 | 55
CHI05-02-01-ER-1060 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 | Connet to Cable tray and conduit equipment - COLO2 Cell 1 - ER | 2024-12-03 08:00 | 2024-12-09 17:00 | 104
CHI05-02-01-ER-1080 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | 2024-12-18 08:00 | 2025-01-09 17:00 | 98
CHI05-02-01-ER-1090 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 | Door Frame Installation - COLO2 Cell 1 - ER | 2025-01-03 08:00 | 2025-01-09 17:00 | 67
CHI05-02-01-ER-1100 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 | Finishes and Signage - COLO2 Cell 1 - ER | 2025-01-10 08:00 | 2025-01-16 17:00 | 125
CHI05-02-01-ER-1055 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 | Installation of MSB - COLO2 Cell 1 - ER | 2024-11-29 08:00 | 2024-12-05 17:00 | 94
CHI05-02-04-L4-1000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,5,1 | COLO2 Cx LEV4 - COLO2 | 2025-05-01 08:00 | 2025-06-04 17:00 | 35
CHI05-02-04-L5-1000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,5,2 | COLO2 Cx LEV5 / IST - COLO2 | 2025-06-05 08:00 | 2025-06-06 17:00 | 35
CHI05-02-02-MG-1110 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 2 - MG | 2024-10-14 08:00 | 2024-10-18 17:00 | 0
CHI05-02-02-MG-1120 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 2 - MG | 2024-10-16 08:00 | 2024-10-22 17:00 | 0
CHI05-02-02-MG-1130 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 | Overhead MEP Installation - COLO2 Cell 2 - MG | 2024-10-30 08:00 | 2024-11-12 17:00 | 53
CHI05-02-02-MG-1140 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 | Deliver AHU into Mech. Gallery - COLO2 Cell 2 - MG | 2024-11-13 08:00 | 2024-11-14 17:00 | 53
CHI05-02-02-MG-1150 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 | Install Walls and Primer Paint - COLO2 Cell 2 - MG | 2024-11-15 08:00 | 2024-11-29 17:00 | 53
CHI05-02-02-MG-1160 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 | Placing the AHU - COLO2 Cell 2 - MG | 2024-12-09 08:00 | 2024-12-11 12:00 | 94
CHI05-02-02-MG-1170 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 | Layout Ceiling and install Pencile Rod - COLO2 Cell 2 - MG | 2024-12-02 08:00 | 2024-12-02 17:00 | 98
CHI05-02-02-MG-1180 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 | Piping and Electrical Termination to AHUs - COLO2 Cell 2 - MG | 2024-12-11 13:00 | 2024-12-26 12:00 | 94
CHI05-02-02-MG-1190 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 | Pipe Testing - COLO2 Cell 2 - MG | 2024-12-26 13:00 | 2024-12-30 12:00 | 98
CHI05-02-02-MG-1200 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | 2024-12-30 13:00 | 2025-01-10 12:00 | 98
CHI05-02-02-MG-1210 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 | Trim out MEP - COLO2 Cell 2 - MG | 2025-01-03 13:00 | 2025-01-10 12:00 | 104
CHI05-02-02-MG-1155 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 | Post Wall Overhead MEP - COLO2 Cell 2 - MG | 2024-12-02 08:00 | 2024-12-20 17:00 | 94
CHI05-02-02-ER-1110 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 | Install Walls and Primer Paint - COLO2 Cell 2 - ER | 2024-10-21 08:00 | 2024-11-01 17:00 | 46
CHI05-02-02-ER-1120 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 2 - ER | 2024-11-06 08:00 | 2024-11-19 17:00 | 46
CHI05-02-02-ER-1130 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 | Install Upper Screens - COLO2 Cell 2 - ER | 2024-10-30 08:00 | 2024-11-05 17:00 | 46
CHI05-02-02-ER-1140 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 | Install Ceiling - COLO2 Cell 2 - ER | 2024-11-20 08:00 | 2024-11-22 17:00 | 46
CHI05-02-02-ER-1150 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 | Below Ceiling MEP Rough In - COLO2 Cell 2 - ER | 2024-12-04 08:00 | 2024-12-17 17:00 | 40
CHI05-02-02-ER-1160 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 | Installation of ADP & ATS - COLO2 Cell 2 - ER | 2024-12-06 08:00 | 2024-12-12 17:00 | 99
CHI05-02-02-ER-1170 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 | Installation of UPS Equipment - COLO2 Cell 2 - ER | 2024-12-11 08:00 | 2024-12-17 17:00 | 55
CHI05-02-02-ER-1180 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 | Connet to Cable tray and conduit equipment - COLO2 Cell 2 - ER | 2024-12-10 08:00 | 2024-12-16 17:00 | 114
CHI05-02-02-ER-1190 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | 2025-01-10 08:00 | 2025-01-30 17:00 | 98
CHI05-02-02-ER-1200 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 | Door Frame Installation - COLO2 Cell 2 - ER | 2025-01-03 08:00 | 2025-01-09 17:00 | 67
CHI05-02-02-ER-1210 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 | Finishes and Signage - COLO2 Cell 2 - ER | 2025-01-28 08:00 | 2025-02-03 17:00 | 118
CHI05-02-02-ER-1165 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 | Installation of MSB - COLO2 Cell 2 - ER | 2024-12-06 08:00 | 2024-12-12 17:00 | 94
CHI05-02-02-DH-1100 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 | Termination at PDU & Busway - COLO2 Cell 2 - DH | 2025-01-21 08:00 | 2025-02-10 17:00 | 42
CHI05-02-02-DH-1110 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 2 - DH | 2024-10-23 08:00 | 2024-11-07 17:00 | 71
CHI05-02-02-DH-1120 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 | HAC install and Rise - COLO2 Cell 2 - DH | 2025-01-06 08:00 | 2025-01-10 17:00 | 78
CHI05-02-02-DH-1130 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 | Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH | 2025-01-06 08:00 | 2025-01-17 17:00 | 58
CHI05-02-02-DH-1140 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 | Security Screen Installation - COLO2 Cell 2 - DH | 2024-12-02 08:00 | 2024-12-04 17:00 | 53
CHI05-02-02-DH-1150 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 | Ceiling Grid and Tile - COLO2 Cell 2 - DH | 2024-12-05 08:00 | 2024-12-11 17:00 | 53
CHI05-02-02-DH-1160 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 | Install PDU's - COLO2 Cell 2 - DH | 2024-12-27 08:00 | 2025-01-03 17:00 | 53
CHI05-02-02-DH-1170 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 2 - DH | 2024-12-12 08:00 | 2024-12-26 17:00 | 53
CHI05-02-02-DH-1180 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 2 - DH | 2025-01-13 08:00 | 2025-01-24 17:00 | 78
CHI05-02-02-DH-1190 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 | HAC Placing - COLO2 Cell 2 - DH | 2024-12-27 08:00 | 2025-01-03 17:00 | 78
CHI05-02-02-DH-1200 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 | Finishes and Signage - COLO2 Cell 2 - DH | 2025-02-04 08:00 | 2025-02-10 17:00 | 113
CHI05-02-02-L1-1260 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 | Interior - L1 UPS - COLO2 Cell 2 | 2025-01-02 08:00 | 2025-01-02 17:00 | 87
CHI05-02-02-L1-1270 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 | Interior - L1 MSB - COLO2 Cell 2 | 2025-01-03 08:00 | 2025-01-03 17:00 | 93
CHI05-02-02-L1-1280 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 | Interior - L1 PDUs - COLO2 Cell 2 | 2025-01-06 08:00 | 2025-01-06 17:00 | 97
CHI05-02-02-L1-1290 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 | Interior - L1 AHUs - COLO2 Cell 2 | 2025-01-08 08:00 | 2025-01-08 17:00 | 105
CHI05-02-02-L1-1300 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 | Interior - L1 ATSs - COLO2 Cell 2 | 2025-01-07 08:00 | 2025-01-07 17:00 | 101
CHI05-02-02-L1-1310 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 | Interior - L1 Busway - COLO2 Cell 2 | 2025-01-07 08:00 | 2025-01-07 17:00 | 101
CHI05-02-02-L1-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 | Interior - L1 ADP - COLO2 Cell 2 | 2025-01-06 08:00 | 2025-01-06 17:00 | 97
CHI05-02-02-L2-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 | Interior - L2 UPS - COLO2 Cell 2 | 2025-02-25 08:00 | 2025-03-03 17:00 | 52
CHI05-02-02-L2-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 | Interior - L2 MSB - COLO2 Cell 2 | 2025-03-04 08:00 | 2025-03-10 17:00 | 52
CHI05-02-02-L2-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 | Interior - L2 PDUs - COLO2 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00 | 52
CHI05-02-02-L2-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 | Interior - L2 AHUs - COLO2 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00 | 52
CHI05-02-02-L2-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 | Interior - L2 ATSs - COLO2 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00 | 52
CHI05-02-02-L2-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 | Interior - L2 Busway - COLO2 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00 | 52
CHI05-02-02-L2-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 | Interior - L2 ADP - COLO2 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00 | 52
CHI05-02-02-L3-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 | Interior - L3 UPS - COLO2 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00 | 37
CHI05-02-02-L3-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 | Interior - L3 MSB - COLO2 Cell 2 | 2025-04-01 08:00 | 2025-04-07 17:00 | 37
CHI05-02-02-L3-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 | Interior - L3 PDUs - COLO2 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00 | 37
CHI05-02-02-L3-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 | Interior - L3 AHUs - COLO2 Cell 2 | 2025-04-22 08:00 | 2025-04-28 17:00 | 37
CHI05-02-02-L3-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 | Interior - L3 ATSs - COLO2 Cell 2 | 2025-04-15 08:00 | 2025-04-21 17:00 | 42
CHI05-02-02-L3-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 | Interior - L3 Busway - COLO2 Cell 2 | 2025-04-15 08:00 | 2025-04-21 17:00 | 37
CHI05-02-02-L3-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 | Interior - L3 ADP - COLO2 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00 | 42
CHI05-02-03-MG-1220 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 3 - MG | 2024-10-21 08:00 | 2024-10-25 17:00 | 0
CHI05-02-03-MG-1230 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 3 - MG | 2024-10-23 08:00 | 2024-10-29 17:00 | 0
CHI05-02-03-MG-1240 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 | Overhead MEP Installation - COLO2 Cell 3 - MG | 2024-11-13 08:00 | 2024-11-26 17:00 | 58
CHI05-02-03-MG-1250 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 | Deliver AHU into Mech. Gallery - COLO2 Cell 3 - MG | 2024-11-27 08:00 | 2024-11-29 17:00 | 58
CHI05-02-03-MG-1260 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 | Install Walls and Primer Paint - COLO2 Cell 3 - MG | 2024-12-02 08:00 | 2024-12-13 17:00 | 58
CHI05-02-03-MG-1270 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 | Placing the AHU - COLO2 Cell 3 - MG | 2024-12-23 08:00 | 2024-12-26 12:00 | 94
CHI05-02-03-MG-1280 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 | Layout Ceiling and install Pencile Rod - COLO2 Cell 3 - MG | 2024-12-16 08:00 | 2024-12-16 17:00 | 98
CHI05-02-03-MG-1290 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 | Piping and Electrical Termination to AHUs - COLO2 Cell 3 - MG | 2024-12-26 13:00 | 2025-01-10 12:00 | 94
CHI05-02-03-MG-1300 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 | Pipe Testing - COLO2 Cell 3 - MG | 2025-01-10 13:00 | 2025-01-14 12:00 | 96
CHI05-02-03-MG-1310 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 | Install ceiling and Light Fittings - COLO2 Cell 3 - MG | 2025-01-14 13:00 | 2025-01-24 12:00 | 96
CHI05-02-03-MG-1320 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 | Trim out MEP - COLO2 Cell 3 - MG | 2025-01-17 13:00 | 2025-01-24 12:00 | 99
CHI05-02-03-MG-1265 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 | Post Wall Overhead MEP - COLO2 Cell 3 - MG | 2024-12-16 08:00 | 2025-01-07 17:00 | 94
CHI05-02-03-ER-1220 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 | Install Walls and Primer Paint - COLO2 Cell 3 - ER | 2024-11-04 08:00 | 2024-11-15 17:00 | 46
CHI05-02-03-ER-1230 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 3 - ER | 2024-11-20 08:00 | 2024-12-04 17:00 | 46
CHI05-02-03-ER-1240 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 | Install Upper Screens - COLO2 Cell 3 - ER | 2024-11-13 08:00 | 2024-11-19 17:00 | 46
CHI05-02-03-ER-1250 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 | Install Ceiling - COLO2 Cell 3 - ER | 2024-12-05 08:00 | 2024-12-09 17:00 | 46
CHI05-02-03-ER-1260 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 | Below Ceiling MEP Rough In - COLO2 Cell 3 - ER | 2024-12-18 08:00 | 2025-01-02 17:00 | 40
CHI05-02-03-ER-1270 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 | Installation of ADP & ATS - COLO2 Cell 3 - ER | 2024-12-20 08:00 | 2024-12-27 17:00 | 94
CHI05-02-03-ER-1280 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 | Installation of UPS Equipment - COLO2 Cell 3 - ER | 2025-01-03 08:00 | 2025-01-09 17:00 | 45
CHI05-02-03-ER-1290 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 | Connet to Cable tray and conduit equipment - COLO2 Cell 3 - ER | 2024-12-24 08:00 | 2024-12-31 17:00 | 119
CHI05-02-03-ER-1300 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 | Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER | 2025-01-31 08:00 | 2025-02-20 17:00 | 98
CHI05-02-03-ER-1310 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 | Door Frame Installation - COLO2 Cell 3 - ER | 2025-01-10 08:00 | 2025-01-16 17:00 | 62
CHI05-02-03-ER-1320 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 | Finishes and Signage - COLO2 Cell 3 - ER | 2025-02-18 08:00 | 2025-02-24 17:00 | 108
CHI05-02-03-ER-1275 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 | Installation of MSB - COLO2 Cell 3 - ER | 2024-12-20 08:00 | 2024-12-27 17:00 | 89
CHI05-02-03-DH-1210 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 | Termination at PDU & Busway - COLO2 Cell 3 - DH | 2025-02-11 08:00 | 2025-03-03 17:00 | 42
CHI05-02-03-DH-1220 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 3 - DH | 2024-11-08 08:00 | 2024-11-25 17:00 | 74
CHI05-02-03-DH-1230 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 | HAC install and Rise - COLO2 Cell 3 - DH | 2025-01-20 08:00 | 2025-01-24 17:00 | 78
CHI05-02-03-DH-1240 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 | Cable Pulling at PDU & Busway- COLO2 Cell 3 - DH | 2025-01-20 08:00 | 2025-01-31 17:00 | 63
CHI05-02-03-DH-1250 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 | Security Screen Installation - COLO2 Cell 3 - DH | 2024-12-16 08:00 | 2024-12-18 17:00 | 58
CHI05-02-03-DH-1260 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 | Ceiling Grid and Tile - COLO2 Cell 3 - DH | 2024-12-19 08:00 | 2024-12-26 17:00 | 58
CHI05-02-03-DH-1270 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 | Install PDU's - COLO2 Cell 3 - DH | 2025-01-13 08:00 | 2025-01-17 17:00 | 58
CHI05-02-03-DH-1280 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 3 - DH | 2024-12-27 08:00 | 2025-01-10 17:00 | 58
CHI05-02-03-DH-1290 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH | 2025-01-27 08:00 | 2025-02-07 17:00 | 78
CHI05-02-03-DH-1300 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 | HAC Placing - COLO2 Cell 3 - DH | 2025-01-13 08:00 | 2025-01-17 17:00 | 78
CHI05-02-03-DH-1310 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 | Finishes and Signage - COLO2 Cell 3 - DH | 2025-02-25 08:00 | 2025-03-03 17:00 | 103
CHI05-02-03-L1-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 | Interior - L1 UPS - COLO2 Cell 3 | 2025-01-02 08:00 | 2025-01-02 17:00 | 87
CHI05-02-03-L1-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 | Interior - L1 MSB - COLO2 Cell 3 | 2025-01-03 08:00 | 2025-01-03 17:00 | 93
CHI05-02-03-L1-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 | Interior - L1 PDUs - COLO2 Cell 3 | 2025-01-20 08:00 | 2025-01-20 17:00 | 87
CHI05-02-03-L1-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 | Interior - L1 AHUs - COLO2 Cell 3 | 2025-01-22 08:00 | 2025-01-22 17:00 | 95
CHI05-02-03-L1-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 | Interior - L1 ATSs - COLO2 Cell 3 | 2025-01-07 08:00 | 2025-01-07 17:00 | 101
CHI05-02-03-L1-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 | Interior - L1 Busway - COLO2 Cell 3 | 2025-01-21 08:00 | 2025-01-21 17:00 | 91
CHI05-02-03-L1-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 | Interior - L1 ADP - COLO2 Cell 3 | 2025-01-06 08:00 | 2025-01-06 17:00 | 97
CHI05-02-03-L2-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 | Interior - L2 UPS - COLO2 Cell 3 | 2025-02-25 08:00 | 2025-03-03 17:00 | 52
CHI05-02-03-L2-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 | Interior - L2 MSB - COLO2 Cell 3 | 2025-03-04 08:00 | 2025-03-10 17:00 | 52
CHI05-02-03-L2-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 | Interior - L2 PDUs - COLO2 Cell 3 | 2025-03-11 08:00 | 2025-03-17 17:00 | 52
CHI05-02-03-L2-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 | Interior - L2 AHUs - COLO2 Cell 3 | 2025-03-25 08:00 | 2025-03-31 17:00 | 52
CHI05-02-03-L2-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 | Interior - L2 ATSs - COLO2 Cell 3 | 2025-03-18 08:00 | 2025-03-24 17:00 | 52
CHI05-02-03-L2-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 | Interior - L2 Busway - COLO2 Cell 3 | 2025-03-18 08:00 | 2025-03-24 17:00 | 52
CHI05-02-03-L2-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 | Interior - L2 ADP - COLO2 Cell 3 | 2025-03-11 08:00 | 2025-03-17 17:00 | 52
CHI05-02-03-L3-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 | Interior - L3 UPS - COLO2 Cell 3 | 2025-03-25 08:00 | 2025-03-31 17:00 | 37
CHI05-02-03-L3-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 | Interior - L3 MSB - COLO2 Cell 3 | 2025-04-01 08:00 | 2025-04-07 17:00 | 37
CHI05-02-03-L3-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 | Interior - L3 PDUs - COLO2 Cell 3 | 2025-04-08 08:00 | 2025-04-14 17:00 | 37
CHI05-02-03-L3-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 | Interior - L3 AHUs - COLO2 Cell 3 | 2025-04-22 08:00 | 2025-04-28 17:00 | 37
CHI05-02-03-L3-1660 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 | Interior - L3 ATSs - COLO2 Cell 3 | 2025-04-15 08:00 | 2025-04-21 17:00 | 37
CHI05-02-03-L3-1670 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 | Interior - L3 Busway - COLO2 Cell 3 | 2025-04-15 08:00 | 2025-04-21 17:00 | 37
CHI05-02-03-L3-1730 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 | Interior - L3 ADP - COLO2 Cell 3 | 2025-04-08 08:00 | 2025-04-14 17:00 | 37
CHI05-02-04-MG-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 4 - MG | 2024-10-28 08:00 | 2024-11-01 17:00 | 0
CHI05-02-04-MG-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 4 - MG | 2024-10-30 08:00 | 2024-11-05 17:00 | 0
CHI05-02-04-MG-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 | Overhead MEP Installation - COLO2 Cell 4 - MG | 2024-11-27 08:00 | 2024-12-11 17:00 | 63
CHI05-02-04-MG-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 | Deliver AHU into Mech. Gallery - COLO2 Cell 4 - MG | 2024-12-12 08:00 | 2024-12-13 17:00 | 63
CHI05-02-04-MG-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 | Install Walls and Primer Paint - COLO2 Cell 4 - MG | 2024-12-16 08:00 | 2024-12-30 17:00 | 63
CHI05-02-04-MG-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 | Placing the AHU - COLO2 Cell 4 - MG | 2025-01-08 08:00 | 2025-01-10 12:00 | 94
CHI05-02-04-MG-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 | Layout Ceiling and install Pencile Rod - COLO2 Cell 4 - MG | 2024-12-31 08:00 | 2024-12-31 17:00 | 98
CHI05-02-04-MG-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 | Piping and Electrical Termination to AHUs - COLO2 Cell 4 - MG | 2025-01-10 13:00 | 2025-01-24 12:00 | 94
CHI05-02-04-MG-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 | Pipe Testing - COLO2 Cell 4 - MG | 2025-01-24 13:00 | 2025-01-28 12:00 | 94
CHI05-02-04-MG-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 | Install ceiling and Light Fittings - COLO2 Cell 4 - MG | 2025-01-28 13:00 | 2025-02-07 12:00 | 94
CHI05-02-04-MG-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 | Trim out MEP - COLO2 Cell 4 - MG | 2025-01-31 13:00 | 2025-02-07 12:00 | 94
CHI05-02-04-MG-1375 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 | Post Wall Overhead MEP - COLO2 Cell 4 - MG | 2024-12-31 08:00 | 2025-01-21 17:00 | 94
CHI05-02-04-ER-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 | Install Walls and Primer Paint - COLO2 Cell 4 - ER | 2024-11-18 08:00 | 2024-12-02 17:00 | 46
CHI05-02-04-ER-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 4 - ER | 2024-12-05 08:00 | 2024-12-18 17:00 | 46
CHI05-02-04-ER-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 | Install Upper Screens - COLO2 Cell 4 - ER | 2024-11-27 08:00 | 2024-12-04 17:00 | 46
CHI05-02-04-ER-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 | Install Ceiling - COLO2 Cell 4 - ER | 2024-12-19 08:00 | 2024-12-23 17:00 | 46
CHI05-02-04-ER-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 | Below Ceiling MEP Rough In - COLO2 Cell 4 - ER | 2025-01-03 08:00 | 2025-01-16 17:00 | 40
CHI05-02-04-ER-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 | Installation of ADP & ATS - COLO2 Cell 4 - ER | 2025-01-07 08:00 | 2025-01-13 17:00 | 89
CHI05-02-04-ER-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 | Installation of UPS Equipment - COLO2 Cell 4 - ER | 2025-01-17 08:00 | 2025-01-23 17:00 | 40
CHI05-02-04-ER-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 | Connet to Cable tray and conduit equipment - COLO2 Cell 4 - ER | 2025-01-09 08:00 | 2025-01-15 17:00 | 124
CHI05-02-04-ER-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 | Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER | 2025-02-21 08:00 | 2025-03-13 17:00 | 98
CHI05-02-04-ER-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 | Door Frame Installation - COLO2 Cell 4 - ER | 2025-01-24 08:00 | 2025-01-30 17:00 | 52
CHI05-02-04-ER-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 | Finishes and Signage - COLO2 Cell 4 - ER | 2025-03-11 08:00 | 2025-03-17 17:00 | 98
CHI05-02-04-ER-1385 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 | Installation of MSB - COLO2 Cell 4 - ER | 2025-01-07 08:00 | 2025-01-13 17:00 | 84
CHI05-02-04-DH-1320 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 | Termination at PDU & Busway - COLO2 Cell 4 - DH | 2025-03-04 08:00 | 2025-03-24 17:00 | 42
CHI05-02-04-DH-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 4 - DH | 2024-11-26 08:00 | 2024-12-12 17:00 | 77
CHI05-02-04-DH-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 | HAC install and Rise - COLO2 Cell 4 - DH | 2025-02-03 08:00 | 2025-02-07 17:00 | 78
CHI05-02-04-DH-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 | Cable Pulling at PDU & Busway- COLO2 Cell 4 - DH | 2025-02-03 08:00 | 2025-02-14 17:00 | 68
CHI05-02-04-DH-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 | Security Screen Installation - COLO2 Cell 4 - DH | 2024-12-31 08:00 | 2025-01-03 17:00 | 63
CHI05-02-04-DH-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 | Ceiling Grid and Tile - COLO2 Cell 4 - DH | 2025-01-06 08:00 | 2025-01-10 17:00 | 63
CHI05-02-04-DH-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 | Install PDU's - COLO2 Cell 4 - DH | 2025-01-27 08:00 | 2025-01-31 17:00 | 63
CHI05-02-04-DH-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 4 - DH | 2025-01-13 08:00 | 2025-01-24 17:00 | 63
CHI05-02-04-DH-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH | 2025-02-10 08:00 | 2025-02-21 17:00 | 78
CHI05-02-04-DH-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 | HAC Placing - COLO2 Cell 4 - DH | 2025-01-27 08:00 | 2025-01-31 17:00 | 78
CHI05-02-04-DH-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 | Finishes and Signage - COLO2 Cell 4 - DH | 2025-03-25 08:00 | 2025-03-31 17:00 | 88
CHI05-02-04-L1-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 | Interior - L1 UPS - COLO2 Cell 4 | 2025-01-24 08:00 | 2025-01-24 17:00 | 71
CHI05-02-04-L1-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 | Interior - L1 MSB - COLO2 Cell 4 | 2025-01-27 08:00 | 2025-01-27 17:00 | 75
CHI05-02-04-L1-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 | Interior - L1 PDUs - COLO2 Cell 4 | 2025-02-03 08:00 | 2025-02-03 17:00 | 77
CHI05-02-04-L1-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 | Interior - L1 AHUs - COLO2 Cell 4 | 2025-02-05 08:00 | 2025-02-05 17:00 | 85
CHI05-02-04-L1-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 | Interior - L1 ATSs - COLO2 Cell 4 | 2025-01-29 08:00 | 2025-01-29 17:00 | 83
CHI05-02-04-L1-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 | Interior - L1 Busway - COLO2 Cell 4 | 2025-02-04 08:00 | 2025-02-04 17:00 | 81
CHI05-02-04-L1-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 | Interior - L1 ADP - COLO2 Cell 4 | 2025-01-28 08:00 | 2025-01-28 17:00 | 79
CHI05-02-04-L2-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 | Interior - L2 UPS - COLO2 Cell 4 | 2025-02-25 08:00 | 2025-03-03 17:00 | 50
CHI05-02-04-L2-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 | Interior - L2 MSB - COLO2 Cell 4 | 2025-03-04 08:00 | 2025-03-10 17:00 | 50
CHI05-02-04-L2-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 | Interior - L2 PDUs - COLO2 Cell 4 | 2025-03-25 08:00 | 2025-03-31 17:00 | 42
CHI05-02-04-L2-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 | Interior - L2 AHUs - COLO2 Cell 4 | 2025-04-08 08:00 | 2025-04-14 17:00 | 42
CHI05-02-04-L2-1660 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 | Interior - L2 ATSs - COLO2 Cell 4 | 2025-03-18 08:00 | 2025-03-24 17:00 | 50
CHI05-02-04-L2-1670 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 | Interior - L2 Busway - COLO2 Cell 4 | 2025-04-01 08:00 | 2025-04-07 17:00 | 42
CHI05-02-04-L2-1730 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 | Interior - L2 ADP - COLO2 Cell 4 | 2025-03-11 08:00 | 2025-03-17 17:00 | 50
CHI05-02-04-L3-1740 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 | Interior - L3 UPS - COLO2 Cell 4 | 2025-03-25 08:00 | 2025-03-31 17:00 | 35
CHI05-02-04-L3-1750 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 | Interior - L3 MSB - COLO2 Cell 4 | 2025-04-01 08:00 | 2025-04-07 17:00 | 35
CHI05-02-04-L3-1760 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 | Interior - L3 PDUs - COLO2 Cell 4 | 2025-04-08 08:00 | 2025-04-14 17:00 | 40
CHI05-02-04-L3-1770 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 | Interior - L3 AHUs - COLO2 Cell 4 | 2025-04-24 08:00 | 2025-04-30 17:00 | 35
CHI05-02-04-L3-1780 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 | Interior - L3 ATSs - COLO2 Cell 4 | 2025-04-15 08:00 | 2025-04-21 17:00 | 35
CHI05-02-04-L3-1790 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 | Interior - L3 Busway - COLO2 Cell 4 | 2025-04-22 08:00 | 2025-04-28 17:00 | 35
CHI05-02-04-L3-1850 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 | Interior - L3 ADP - COLO2 Cell 4 | 2025-04-08 08:00 | 2025-04-14 17:00 | 35
CHI05-YARD-2000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,1 | Set the Generator - Colo 2 - North | 2024-10-22 08:00 | 2024-10-28 17:00 | 65
CHI05-YARD-2040 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,1 | Install MEP raceway conduit and piping - Colo 2 - North | 2024-10-10 08:00 | 2024-10-30 17:00 | 116
CHI05-YARD-2140 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,1 | Wire pulling and termination for MSB - Colo 2 - North | 2024-11-26 08:00 | 2024-12-17 17:00 | 98
CHI05-YARD-2360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,1 | Install screen wall - Colo 2 - North | 2024-12-18 08:00 | 2025-01-16 17:00 | 140
CHI05-YARD-2030 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,1 | Install Generator - Colo 2 - North | 2024-11-19 08:00 | 2024-11-25 17:00 | 82
CHI05-YARD-2210 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,1 | Installation of Mech. Piping and testing - Colo 2 - North | 2024-11-26 08:00 | 2024-12-17 17:00 | 140
CHI05-YARD-2560 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,1 | Set the MV Gear - Colo 2 - North | 2024-10-24 08:00 | 2024-10-30 17:00 | 63
CHI05-YARD-2570 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,1 | Install MV Gear - Colo 2 - North | 2024-10-31 08:00 | 2024-11-06 17:00 | 90
CHI05-YARD-2120 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,2 | Set the Generator - Colo 2 - South | 2024-10-01 08:00 | 2024-10-07 17:00 | 65
CHI05-YARD-2300 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,2 | Install MEP raceway conduit and piping - Colo 2 - South | 2024-09-19 08:00 | 2024-10-09 17:00 | 131
CHI05-YARD-2350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,2 | Wire pulling and termination for MSB - Colo 2 - South | 2024-11-26 08:00 | 2024-12-17 17:00 | 98
CHI05-YARD-2450 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,2 | Install screen wall - Colo 2 - South | 2025-01-10 08:00 | 2025-02-06 17:00 | 125
CHI05-YARD-2130 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,2 | Install Generator - Colo 2 - South | 2024-11-19 08:00 | 2024-11-25 17:00 | 82
CHI05-YARD-2390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,2 | Installation of Mech. Piping and testing - Colo 2 - South | 2024-12-18 08:00 | 2025-01-09 17:00 | 125
CHI05-YARD-2500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,2 | Set the MV Gear - Colo 2 - South | 2024-10-03 08:00 | 2024-10-09 17:00 | 63
CHI05-YARD-2510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,2 | Install MV Gear - Colo 2 - South | 2024-10-10 08:00 | 2024-10-16 17:00 | 105
CHI05-YARD-2010 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,4 | Set the MV Gear - Colo 5 - West | 2024-11-14 08:00 | 2024-11-20 17:00 | 63
CHI05-YARD-2050 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,4 | Install MEP raceway conduit and piping - Colo 5 - West | 2024-10-31 08:00 | 2024-11-20 17:00 | 68
CHI05-YARD-2150 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,4 | Wire pulling and termination for MSB - Colo 5 - West | 2024-12-17 08:00 | 2025-01-08 17:00 | 51
CHI05-YARD-2250 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,4 | Install screen wall - Colo 5 - West | 2025-01-09 08:00 | 2025-02-05 17:00 | 126
CHI05-YARD-2020 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,4 | Install MV Gear - Colo 5 - West | 2024-11-21 08:00 | 2024-11-27 17:00 | 63
CHI05-YARD-2200 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,4 | Installation of Mech. Piping and testing - Colo 5 - West | 2024-12-17 08:00 | 2025-01-08 17:00 | 126
CHI05-YARD-2620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,4 | Set the Generator - Colo 5 - West | 2024-11-12 08:00 | 2024-11-18 17:00 | 65
CHI05-YARD-2630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,4 | Install Generator - Colo 5 - West | 2024-12-10 08:00 | 2024-12-16 17:00 | 51
CHI05-YARD-2060 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,5 | Set the Generator - Colo 3 - North | 2024-10-29 08:00 | 2024-11-04 17:00 | 65
CHI05-YARD-2160 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,5 | Install MEP raceway conduit and piping - Colo 3 - North | 2024-10-17 08:00 | 2024-11-06 17:00 | 111
CHI05-YARD-2260 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,5 | Wire pulling and termination for MSB - Colo 3 - North | 2024-12-03 08:00 | 2024-12-23 17:00 | 94
CHI05-YARD-2400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,5 | Install screen wall - Colo 3 - North | 2024-12-24 08:00 | 2025-01-22 17:00 | 136
CHI05-YARD-2090 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,5 | Install Generator - Colo 3 - North | 2024-11-25 08:00 | 2024-12-02 17:00 | 71
CHI05-YARD-2290 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,5 | Installation of Mech. Piping and testing - Colo 3 - North | 2024-12-03 08:00 | 2024-12-23 17:00 | 136
CHI05-YARD-2580 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,5 | Set the MV Gear - Colo 3 - North | 2024-10-31 08:00 | 2024-11-06 17:00 | 63
CHI05-YARD-2590 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,5 | Install MV Gear - Colo 3 - North | 2024-11-07 08:00 | 2024-11-13 17:00 | 78
CHI05-YARD-2100 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,6 | Set the MV Gear - Colo 4 - North | 2024-11-07 08:00 | 2024-11-13 17:00 | 63
CHI05-YARD-2240 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,6 | Install MEP raceway conduit and piping - Colo 4 - North | 2024-10-24 08:00 | 2024-11-13 17:00 | 69
CHI05-YARD-2310 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,6 | Wire pulling and termination for MSB - Colo 4 - North | 2024-12-17 08:00 | 2025-01-08 17:00 | 47
CHI05-YARD-2430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,6 | Install screen wall - Colo 4 - North | 2025-01-09 08:00 | 2025-02-05 17:00 | 126
CHI05-YARD-2110 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,6 | Install MV Gear - Colo 4 - North | 2024-11-14 08:00 | 2024-11-20 17:00 | 64
CHI05-YARD-2330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,6 | Installation of Mech. Piping and testing - Colo 4 - North | 2024-12-17 08:00 | 2025-01-08 17:00 | 126
CHI05-YARD-2600 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,6 | Set the Generator - Colo 4 - North | 2024-11-05 08:00 | 2024-11-11 17:00 | 65
CHI05-YARD-2610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,6 | Install Generator - Colo 4 - North | 2024-12-10 08:00 | 2024-12-16 17:00 | 47
CHI05-YARD-2170 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,7 | Set the MV Gear - Colo 3 - South | 2024-10-10 08:00 | 2024-10-16 17:00 | 63
CHI05-YARD-2340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,7 | Install MEP raceway conduit and piping - Colo 3 - South | 2024-09-26 08:00 | 2024-10-16 17:00 | 126
CHI05-YARD-2380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,7 | Wire pulling and termination for MSB - Colo 3 - South | 2024-12-03 08:00 | 2024-12-23 17:00 | 94
CHI05-YARD-2460 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,7 | Install screen wall - Colo 3 - South | 2024-12-24 08:00 | 2025-01-22 17:00 | 136
CHI05-YARD-2190 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,7 | Install MV Gear - Colo 3 - South | 2024-10-17 08:00 | 2024-10-23 17:00 | 93
CHI05-YARD-2410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,7 | Installation of Mech. Piping and testing - Colo 3 - South | 2024-12-03 08:00 | 2024-12-23 17:00 | 136
CHI05-YARD-2520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,7 | Set the Generator - Colo 3 - South | 2024-10-08 08:00 | 2024-10-14 17:00 | 65
CHI05-YARD-2530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,7 | Install Generator - Colo 3 - South | 2024-11-25 08:00 | 2024-12-02 17:00 | 71
CHI05-YARD-2220 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,8 | Set the MV Gear - Colo 4 - South | 2024-10-17 08:00 | 2024-10-23 17:00 | 63
CHI05-YARD-2370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,8 | Install MEP raceway conduit and piping - Colo 4 - South | 2024-10-03 08:00 | 2024-10-23 17:00 | 84
CHI05-YARD-2420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,8 | Wire pulling and termination for MSB - Colo 4 - South | 2024-12-17 08:00 | 2025-01-08 17:00 | 47
CHI05-YARD-2470 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,8 | Install screen wall - Colo 4 - South | 2025-01-09 08:00 | 2025-02-05 17:00 | 126
CHI05-YARD-2230 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,8 | Install MV Gear - Colo 4 - South | 2024-10-24 08:00 | 2024-10-30 17:00 | 79
CHI05-YARD-2440 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,8 | Installation of Mech. Piping and testing - Colo 4 - South | 2024-12-17 08:00 | 2025-01-08 17:00 | 126
CHI05-YARD-2540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,8 | Set the Generator - Colo 4 - South | 2024-10-15 08:00 | 2024-10-21 17:00 | 65
CHI05-YARD-2550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,8 | Install Generator - Colo 4 - South | 2024-12-10 08:00 | 2024-12-16 17:00 | 47
CHI05-YARD-2070 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,9 | Set the MV Gear - Colo 5 - East | 2024-09-24 08:00 | 2024-09-30 17:00 | 65
CHI05-YARD-2180 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,9 | Install MEP raceway conduit and piping - Colo 5 - East | 2024-09-10 08:00 | 2024-09-30 17:00 | 105
CHI05-YARD-2270 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,9 | Wire pulling and termination for MSB - Colo 5 - East | 2024-12-17 08:00 | 2025-01-08 17:00 | 51
CHI05-YARD-2320 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,9 | Install screen wall - Colo 5 - East | 2025-01-09 08:00 | 2025-02-05 17:00 | 126
CHI05-YARD-2080 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,9 | Install MV Gear - Colo 5 - East | 2024-10-09 08:00 | 2024-10-15 17:00 | 94
CHI05-YARD-2280 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,9 | Installation of Mech. Piping and testing - Colo 5 - Eest | 2024-12-17 08:00 | 2025-01-08 17:00 | 126
CHI05-YARD-2480 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,9 | Set the Generator - Colo 5 - East | 2024-09-20 08:00 | 2024-09-26 17:00 | 67
CHI05-YARD-2490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,4,9 | Install Generator - Colo 5 - East | 2024-12-10 08:00 | 2024-12-16 17:00 | 51
CHI05-03-01-MG-1110 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 1 - MG | 2024-11-06 08:00 | 2024-11-12 17:00 | 0
CHI05-03-01-MG-1120 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 1 - MG | 2024-11-08 08:00 | 2024-11-14 17:00 | 17
CHI05-03-01-MG-1130 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 | Overhead MEP Installation - COLO3 Cell 1 - MG | 2024-11-15 08:00 | 2024-11-29 17:00 | 17
CHI05-03-01-MG-1140 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 | Deliver AHU into Mech. Gallery - COLO3 Cell 1 - MG | 2024-12-02 08:00 | 2024-12-03 17:00 | 17
CHI05-03-01-MG-1150 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 | Install Walls and Primer Paint - COLO3 Cell 1 - MG | 2024-12-04 08:00 | 2024-12-17 17:00 | 17
CHI05-03-01-MG-1160 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 | Placing the AHU - COLO3 Cell 1 - MG | 2024-12-26 08:00 | 2024-12-30 12:00 | 72
CHI05-03-01-MG-1170 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 | Layout Ceiling and install Pencile Rod - COLO3 Cell 1 - MG | 2024-12-18 08:00 | 2024-12-18 17:00 | 76
CHI05-03-01-MG-1180 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 | Piping and Electrical Termination to AHUs - COLO3 Cell 1 - MG | 2024-12-30 13:00 | 2025-01-14 12:00 | 72
CHI05-03-01-MG-1190 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 | Pipe Testing - COLO3 Cell 1 - MG | 2025-01-14 13:00 | 2025-01-16 12:00 | 78
CHI05-03-01-MG-1200 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 | Install ceiling and Light Fittings - COLO3 Cell 1 - MG | 2025-01-16 13:00 | 2025-01-28 12:00 | 78
CHI05-03-01-MG-1210 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 | Trim out MEP - COLO3 Cell 1 - MG | 2025-01-21 13:00 | 2025-01-28 12:00 | 87
CHI05-03-01-MG-1155 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 | Post Wall Overhead MEP - COLO3 Cell 1 - MG | 2024-12-18 08:00 | 2025-01-09 17:00 | 72
CHI05-03-01-ER-1110 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 | Install Walls and Primer Paint - COLO3 Cell 1 - ER | 2024-11-06 08:00 | 2024-11-19 17:00 | 0
CHI05-03-01-ER-1120 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 1 - ER | 2024-11-22 08:00 | 2024-12-06 17:00 | 29
CHI05-03-01-ER-1130 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 | Install Upper Screens - COLO3 Cell 1 - ER | 2024-11-15 08:00 | 2024-11-21 17:00 | 29
CHI05-03-01-ER-1140 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 | Install Ceiling - COLO3 Cell 1 - ER | 2024-12-09 08:00 | 2024-12-11 17:00 | 29
CHI05-03-01-ER-1150 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 | Below Ceiling MEP Rough In - COLO3 Cell 1 - ER | 2024-12-16 08:00 | 2024-12-30 17:00 | 27
CHI05-03-01-ER-1160 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 | Installation of ADP & ATS - COLO3 Cell 1 - ER | 2025-01-02 08:00 | 2025-01-08 17:00 | 78
CHI05-03-01-ER-1170 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 | Installation of UPS Equipment - COLO3 Cell 1 - ER | 2025-01-24 08:00 | 2025-01-30 17:00 | 40
CHI05-03-01-ER-1180 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 | Connet to Cable tray and conduit equipment - COLO3 Cell 1 - ER | 2025-01-06 08:00 | 2025-01-10 17:00 | 82
CHI05-03-01-ER-1190 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 | Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER | 2025-01-13 08:00 | 2025-01-31 17:00 | 82
CHI05-03-01-ER-1200 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 | Door Frame Installation - COLO3 Cell 1 - ER | 2025-01-31 08:00 | 2025-02-06 17:00 | 40
CHI05-03-01-ER-1210 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 | Finishes and Signage - COLO3 Cell 1 - ER | 2025-02-07 08:00 | 2025-02-13 17:00 | 105
CHI05-03-01-ER-1155 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 | Installation of MSB - COLO3 Cell 1 - ER | 2024-12-18 08:00 | 2024-12-24 17:00 | 77
CHI05-03-01-DH-1100 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 | Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH | 2025-01-22 08:00 | 2025-02-11 17:00 | 17
CHI05-03-01-DH-1110 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 1 - DH | 2024-11-06 08:00 | 2024-11-21 17:00 | 37
CHI05-03-01-DH-1120 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 | HAC install and Rise - COLO3 Cell 1 - DH | 2025-01-22 08:00 | 2025-01-28 17:00 | 56
CHI05-03-01-DH-1130 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 | Termination at PDU & Busway- COLO3 Cell 1 - DH | 2025-01-22 08:00 | 2025-02-04 17:00 | 22
CHI05-03-01-DH-1140 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 | Security Screen Installation - COLO3 Cell 1 - DH | 2024-12-18 08:00 | 2024-12-20 17:00 | 17
CHI05-03-01-DH-1150 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 | Ceiling Grid and Tile - COLO3 Cell 1 - DH | 2024-12-23 08:00 | 2024-12-30 17:00 | 17
CHI05-03-01-DH-1160 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 | Install PDU's - COLO3 Cell 1 - DH | 2025-01-15 08:00 | 2025-01-21 17:00 | 17
CHI05-03-01-DH-1170 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 1 - DH | 2024-12-31 08:00 | 2025-01-14 17:00 | 17
CHI05-03-01-DH-1180 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH | 2025-01-29 08:00 | 2025-02-11 17:00 | 56
CHI05-03-01-DH-1190 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 | HAC Placing - COLO3 Cell 1 - DH | 2025-01-15 08:00 | 2025-01-21 17:00 | 56
CHI05-03-01-DH-1200 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 | Finishes and Signage - COLO3 Cell 1 - DH | 2025-02-12 08:00 | 2025-02-18 17:00 | 102
CHI05-03-01-L1-1260 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 | Interior - L1 UPS - COLO3 Cell 1 | 2025-01-31 08:00 | 2025-01-31 17:00 | 58
CHI05-03-01-L1-1270 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 | Interior - L1 MSB - COLO3 Cell 1 | 2025-02-03 08:00 | 2025-02-03 17:00 | 70
CHI05-03-01-L1-1280 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 | Interior - L1 PDUs - COLO3 Cell 1 | 2025-02-04 08:00 | 2025-02-04 17:00 | 74
CHI05-03-01-L1-1290 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 | Interior - L1 AHUs - COLO3 Cell 1 | 2025-02-06 08:00 | 2025-02-06 17:00 | 87
CHI05-03-01-L1-1300 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 | Interior - L1 ATSs - COLO3 Cell 1 | 2025-02-05 08:00 | 2025-02-05 17:00 | 83
CHI05-03-01-L1-1310 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 | Interior - L1 Busway - COLO3 Cell 1 | 2025-02-05 08:00 | 2025-02-05 17:00 | 83
CHI05-03-01-L1-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 | Interior - L1 ADP - COLO3 Cell 1 | 2025-02-04 08:00 | 2025-02-04 17:00 | 79
CHI05-03-01-L2-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 | Interior - L2 UPS - COLO3 Cell 1 | 2025-02-25 08:00 | 2025-03-03 17:00 | 50
CHI05-03-01-L2-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 | Interior - L2 MSB - COLO3 Cell 1 | 2025-03-04 08:00 | 2025-03-10 17:00 | 50
CHI05-03-01-L2-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 | Interior - L2 PDUs - COLO3 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00 | 50
CHI05-03-01-L2-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 | Interior - L2 AHUs - COLO3 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00 | 55
CHI05-03-01-L2-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 | Interior - L2 ATSs - COLO3 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00 | 55
CHI05-03-01-L2-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 | Interior - L2 Busway - COLO3 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00 | 55
CHI05-03-01-L2-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 | Interior - L2 ADP - COLO3 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00 | 55
CHI05-03-01-L3-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 | Interior - L3 UPS - COLO3 Cell 1 | 2025-03-26 08:00 | 2025-04-01 17:00 | 34
CHI05-03-01-L3-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 | Interior - L3 MSB - COLO3 Cell 1 | 2025-04-02 08:00 | 2025-04-08 17:00 | 34
CHI05-03-01-L3-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 | Interior - L3 PDUs - COLO3 Cell 1 | 2025-04-09 08:00 | 2025-04-15 17:00 | 34
CHI05-03-01-L3-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 | Interior - L3 AHUs - COLO3 Cell 1 | 2025-04-30 08:00 | 2025-05-06 17:00 | 34
CHI05-03-01-L3-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 | Interior - L3 ATSs - COLO3 Cell 1 | 2025-04-23 08:00 | 2025-04-29 17:00 | 34
CHI05-03-01-L3-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 | Interior - L3 Busway - COLO3 Cell 1 | 2025-04-30 08:00 | 2025-05-06 17:00 | 34
CHI05-03-01-L3-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 | Interior - L3 ADP - COLO3 Cell 1 | 2025-04-16 08:00 | 2025-04-22 17:00 | 34
CHI05-03-02-MG-1220 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 2 - MG | 2024-11-13 08:00 | 2024-11-19 17:00 | 4
CHI05-03-02-MG-1230 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 2 - MG | 2024-11-15 08:00 | 2024-11-21 17:00 | 27
CHI05-03-02-MG-1240 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 | Overhead MEP Installation - COLO3 Cell 2 - MG | 2024-12-02 08:00 | 2024-12-13 17:00 | 22
CHI05-03-02-MG-1250 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 | Deliver AHU into Mech. Gallery - COLO3 Cell 2 - MG | 2024-12-16 08:00 | 2024-12-17 17:00 | 22
CHI05-03-02-MG-1260 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 | Install Walls and Primer Paint - COLO3 Cell 2 - MG | 2024-12-18 08:00 | 2025-01-02 17:00 | 22
CHI05-03-02-MG-1270 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 | Placing the AHU - COLO3 Cell 2 - MG | 2025-01-10 08:00 | 2025-01-14 12:00 | 72
CHI05-03-02-MG-1280 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 | Layout Ceiling and install Pencile Rod - COLO3 Cell 2 - MG | 2025-01-03 08:00 | 2025-01-03 17:00 | 76
CHI05-03-02-MG-1290 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 | Piping and Electrical Termination to AHUs - COLO3 Cell 2 - MG | 2025-01-14 13:00 | 2025-01-28 12:00 | 72
CHI05-03-02-MG-1300 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 | Pipe Testing - COLO3 Cell 2 - MG | 2025-01-28 13:00 | 2025-01-30 12:00 | 76
CHI05-03-02-MG-1310 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 | Install ceiling and Light Fittings - COLO3 Cell 2 - MG | 2025-01-30 13:00 | 2025-02-11 12:00 | 76
CHI05-03-02-MG-1320 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 | Trim out MEP - COLO3 Cell 2 - MG | 2025-02-04 13:00 | 2025-02-11 12:00 | 82
CHI05-03-02-MG-1265 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 | Post Wall Overhead MEP - COLO3 Cell 2 - MG | 2025-01-03 08:00 | 2025-01-23 17:00 | 72
CHI05-03-02-ER-1220 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 | Install Walls and Primer Paint - COLO3 Cell 2 - ER | 2024-11-20 08:00 | 2024-12-04 17:00 | 0
CHI05-03-02-ER-1230 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 2 - ER | 2024-12-09 08:00 | 2024-12-20 17:00 | 29
CHI05-03-02-ER-1240 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 | Install Upper Screens - COLO3 Cell 2 - ER | 2024-12-02 08:00 | 2024-12-06 17:00 | 29
CHI05-03-02-ER-1250 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 | Install Ceiling - COLO3 Cell 2 - ER | 2024-12-23 08:00 | 2024-12-26 17:00 | 29
CHI05-03-02-ER-1260 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | 2024-12-31 08:00 | 2025-01-14 17:00 | 27
CHI05-03-02-ER-1270 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 | Installation of ADP & ATS - COLO3 Cell 2 - ER | 2025-01-09 08:00 | 2025-01-15 17:00 | 78
CHI05-03-02-ER-1280 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 | Installation of UPS Equipment - COLO3 Cell 2 - ER | 2025-01-15 08:00 | 2025-01-21 17:00 | 37
CHI05-03-02-ER-1290 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 | Connet to Cable tray and conduit equipment - COLO3 Cell 2 - ER | 2025-01-13 08:00 | 2025-01-17 17:00 | 92
CHI05-03-02-ER-1300 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 | Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER | 2025-02-03 08:00 | 2025-02-21 17:00 | 82
CHI05-03-02-ER-1310 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 | Door Frame Installation - COLO3 Cell 2 - ER | 2025-01-22 08:00 | 2025-01-28 17:00 | 47
CHI05-03-02-ER-1320 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 | Finishes and Signage - COLO3 Cell 2 - ER | 2025-02-19 08:00 | 2025-02-25 17:00 | 102
CHI05-03-02-ER-1265 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 | Installation of MSB - COLO3 Cell 2 - ER | 2025-01-03 08:00 | 2025-01-09 17:00 | 72
CHI05-03-02-DH-1210 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 | Termination at PDU & Busway - COLO3 Cell 2 - DH | 2025-02-12 08:00 | 2025-03-04 17:00 | 17
CHI05-03-02-DH-1220 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 2 - DH | 2024-11-22 08:00 | 2024-12-10 17:00 | 40
CHI05-03-02-DH-1230 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 | HAC install and Rise - COLO3 Cell 2 - DH | 2025-02-05 08:00 | 2025-02-11 17:00 | 56
CHI05-03-02-DH-1240 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 | Cable Pulling at PDU & Busway- COLO3 Cell 2 - DH | 2025-02-05 08:00 | 2025-02-18 17:00 | 27
CHI05-03-02-DH-1250 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 | Security Screen Installation - COLO3 Cell 2 - DH | 2025-01-03 08:00 | 2025-01-07 17:00 | 22
CHI05-03-02-DH-1260 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 | Ceiling Grid and Tile - COLO3 Cell 2 - DH | 2025-01-08 08:00 | 2025-01-14 17:00 | 22
CHI05-03-02-DH-1270 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 | Install PDU's - COLO3 Cell 2 - DH | 2025-01-29 08:00 | 2025-02-04 17:00 | 22
CHI05-03-02-DH-1280 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH | 2025-01-15 08:00 | 2025-01-28 17:00 | 22
CHI05-03-02-DH-1290 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 2 - DH | 2025-02-12 08:00 | 2025-02-25 17:00 | 56
CHI05-03-02-DH-1300 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 | HAC Placing - COLO3 Cell 2 - DH | 2025-01-29 08:00 | 2025-02-04 17:00 | 56
CHI05-03-02-DH-1310 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 | Finishes and Signage - COLO3 Cell 2 - DH | 2025-02-26 08:00 | 2025-03-04 17:00 | 97
CHI05-03-02-L1-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 | Interior - L1 UPS - COLO3 Cell 2 | 2025-02-03 08:00 | 2025-02-03 17:00 | 58
CHI05-03-02-L1-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 | Interior - L1 MSB - COLO3 Cell 2 | 2025-02-04 08:00 | 2025-02-04 17:00 | 69
CHI05-03-02-L1-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 | Interior - L1 PDUs - COLO3 Cell 2 | 2025-02-05 08:00 | 2025-02-05 17:00 | 73
CHI05-03-02-L1-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 | Interior - L1 AHUs - COLO3 Cell 2 | 2025-02-07 08:00 | 2025-02-07 17:00 | 86
CHI05-03-02-L1-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 | Interior - L1 ATSs - COLO3 Cell 2 | 2025-02-06 08:00 | 2025-02-06 17:00 | 82
CHI05-03-02-L1-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 | Interior - L1 Busway - COLO3 Cell 2 | 2025-02-06 08:00 | 2025-02-06 17:00 | 82
CHI05-03-02-L1-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 | Interior - L1 ADP - COLO3 Cell 2 | 2025-02-05 08:00 | 2025-02-05 17:00 | 78
CHI05-03-02-L2-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 | Interior - L2 UPS - COLO3 Cell 2 | 2025-02-25 08:00 | 2025-03-03 17:00 | 50
CHI05-03-02-L2-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 | Interior - L2 MSB - COLO3 Cell 2 | 2025-03-04 08:00 | 2025-03-10 17:00 | 50
CHI05-03-02-L2-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 | Interior - L2 PDUs - COLO3 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00 | 50
CHI05-03-02-L2-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 | Interior - L2 AHUs - COLO3 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00 | 55
CHI05-03-02-L2-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 | Interior - L2 ATSs - COLO3 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00 | 55
CHI05-03-02-L2-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 | Interior - L2 Busway - COLO3 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00 | 55
CHI05-03-02-L2-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 | Interior - L2 ADP - COLO3 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00 | 55
CHI05-03-02-L3-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 | Interior - L3 UPS - COLO3 Cell 2 | 2025-03-26 08:00 | 2025-04-01 17:00 | 34
CHI05-03-02-L3-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 | Interior - L3 MSB - COLO3 Cell 2 | 2025-04-02 08:00 | 2025-04-08 17:00 | 34
CHI05-03-02-L3-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 | Interior - L3 PDUs - COLO3 Cell 2 | 2025-04-09 08:00 | 2025-04-15 17:00 | 34
CHI05-03-02-L3-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 | Interior - L3 AHUs - COLO3 Cell 2 | 2025-04-30 08:00 | 2025-05-06 17:00 | 34
CHI05-03-02-L3-1660 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 | Interior - L3 ATSs - COLO3 Cell 2 | 2025-04-23 08:00 | 2025-04-29 17:00 | 34
CHI05-03-02-L3-1670 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 | Interior - L3 Busway - COLO3 Cell 2 | 2025-04-30 08:00 | 2025-05-06 17:00 | 34
CHI05-03-02-L3-1730 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 | Interior - L3 ADP - COLO3 Cell 2 | 2025-04-16 08:00 | 2025-04-22 17:00 | 34
CHI05-03-03-MG-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 3 - MG | 2024-11-20 08:00 | 2024-11-26 17:00 | 4
CHI05-03-03-MG-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 3 - MG | 2024-11-22 08:00 | 2024-11-29 17:00 | 37
CHI05-03-03-MG-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 | Overhead MEP Installation - COLO3 Cell 3 - MG | 2024-12-16 08:00 | 2024-12-30 17:00 | 27
CHI05-03-03-MG-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 | Deliver AHU into Mech. Gallery - COLO3 Cell 3 - MG | 2024-12-31 08:00 | 2025-01-02 17:00 | 27
CHI05-03-03-MG-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 | Install Walls and Primer Paint - COLO3 Cell 3 - MG | 2025-01-03 08:00 | 2025-01-16 17:00 | 27
CHI05-03-03-MG-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 | Placing the AHU - COLO3 Cell 3 - MG | 2025-01-24 08:00 | 2025-01-28 12:00 | 72
CHI05-03-03-MG-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 | Layout Ceiling and install Pencile Rod - COLO3 Cell 3 - MG | 2025-01-17 08:00 | 2025-01-17 17:00 | 76
CHI05-03-03-MG-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 | Piping and Electrical Termination to AHUs - COLO3 Cell 3 - MG | 2025-01-28 13:00 | 2025-02-11 12:00 | 72
CHI05-03-03-MG-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 | Pipe Testing - COLO3 Cell 3 - MG | 2025-02-11 13:00 | 2025-02-13 12:00 | 74
CHI05-03-03-MG-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 | Install ceiling and Light Fittings - COLO3 Cell 3 - MG | 2025-02-13 13:00 | 2025-02-25 12:00 | 74
CHI05-03-03-MG-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 | Trim out MEP - COLO3 Cell 3 - MG | 2025-02-18 13:00 | 2025-02-25 12:00 | 77
CHI05-03-03-MG-1375 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 | Post Wall Overhead MEP - COLO3 Cell 3 - MG | 2025-01-17 08:00 | 2025-02-06 17:00 | 72
CHI05-03-03-ER-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 | Install Walls and Primer Paint - COLO3 Cell 3 - ER | 2024-12-05 08:00 | 2024-12-18 17:00 | 0
CHI05-03-03-ER-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 3 - ER | 2024-12-23 08:00 | 2025-01-07 17:00 | 29
CHI05-03-03-ER-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 | Install Upper Screens - COLO3 Cell 3 - ER | 2024-12-16 08:00 | 2024-12-20 17:00 | 29
CHI05-03-03-ER-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 | Install Ceiling - COLO3 Cell 3 - ER | 2025-01-08 08:00 | 2025-01-10 17:00 | 29
CHI05-03-03-ER-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | 2025-01-15 08:00 | 2025-01-28 17:00 | 27
CHI05-03-03-ER-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 | Installation of ADP & ATS - COLO3 Cell 3 - ER | 2025-01-17 08:00 | 2025-01-23 17:00 | 77
CHI05-03-03-ER-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 | Installation of UPS Equipment - COLO3 Cell 3 - ER | 2025-01-29 08:00 | 2025-02-04 17:00 | 32
CHI05-03-03-ER-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 | Connet to Cable tray and conduit equipment - COLO3 Cell 3 - ER | 2025-01-21 08:00 | 2025-01-27 17:00 | 101
CHI05-03-03-ER-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 | Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER | 2025-02-24 08:00 | 2025-03-14 17:00 | 82
CHI05-03-03-ER-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 | Door Frame Installation - COLO3 Cell 3 - ER | 2025-02-05 08:00 | 2025-02-11 17:00 | 37
CHI05-03-03-ER-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 | Finishes and Signage - COLO3 Cell 3 - ER | 2025-03-12 08:00 | 2025-03-18 17:00 | 92
CHI05-03-03-ER-1385 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 | Installation of MSB - COLO3 Cell 3 - ER | 2025-01-17 08:00 | 2025-01-23 17:00 | 67
CHI05-03-03-DH-1320 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 | Termination at PDU & Busway - COLO3 Cell 3 - DH | 2025-03-05 08:00 | 2025-03-25 17:00 | 17
CHI05-03-03-DH-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 3 - DH | 2024-12-11 08:00 | 2024-12-27 17:00 | 43
CHI05-03-03-DH-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 | HAC install and Rise - COLO3 Cell 3 - DH | 2025-02-19 08:00 | 2025-02-25 17:00 | 56
CHI05-03-03-DH-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 | Cable Pulling at PDU & Busway- COLO3 Cell 3 - DH | 2025-02-19 08:00 | 2025-03-04 17:00 | 32
CHI05-03-03-DH-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 | Security Screen Installation - COLO3 Cell 3 - DH | 2025-01-17 08:00 | 2025-01-21 17:00 | 27
CHI05-03-03-DH-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 | Ceiling Grid and Tile - COLO3 Cell 3 - DH | 2025-01-22 08:00 | 2025-01-28 17:00 | 27
CHI05-03-03-DH-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 | Install PDU's - COLO3 Cell 3 - DH | 2025-02-12 08:00 | 2025-02-18 17:00 | 27
CHI05-03-03-DH-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH | 2025-01-29 08:00 | 2025-02-11 17:00 | 27
CHI05-03-03-DH-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 3 - DH | 2025-02-26 08:00 | 2025-03-11 17:00 | 56
CHI05-03-03-DH-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 | HAC Placing - COLO3 Cell 3 - DH | 2025-02-12 08:00 | 2025-02-18 17:00 | 56
CHI05-03-03-DH-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 | Finishes and Signage - COLO3 Cell 3 - DH | 2025-03-19 08:00 | 2025-03-25 17:00 | 87
CHI05-03-03-L1-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 | Interior - L1 UPS - COLO3 Cell 3 | 2025-02-04 08:00 | 2025-02-04 17:00 | 58
CHI05-03-03-L1-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 | Interior - L1 MSB - COLO3 Cell 3 | 2025-02-05 08:00 | 2025-02-05 17:00 | 87
CHI05-03-03-L1-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 | Interior - L1 PDUs - COLO3 Cell 3 | 2025-02-19 08:00 | 2025-02-19 17:00 | 78
CHI05-03-03-L1-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 | Interior - L1 AHUs - COLO3 Cell 3 | 2025-02-21 08:00 | 2025-02-21 17:00 | 78
CHI05-03-03-L1-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 | Interior - L1 ATSs - COLO3 Cell 3 | 2025-02-07 08:00 | 2025-02-07 17:00 | 87
CHI05-03-03-L1-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 | Interior - L1 Busway - COLO3 Cell 3 | 2025-02-20 08:00 | 2025-02-20 17:00 | 78
CHI05-03-03-L1-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 | Interior - L1 ADP - COLO3 Cell 3 | 2025-02-06 08:00 | 2025-02-06 17:00 | 87
CHI05-03-03-L2-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 | Interior - L2 UPS - COLO3 Cell 3 | 2025-02-25 08:00 | 2025-03-03 17:00 | 52
CHI05-03-03-L2-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 | Interior - L2 MSB - COLO3 Cell 3 | 2025-03-04 08:00 | 2025-03-10 17:00 | 52
CHI05-03-03-L2-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 | Interior - L2 PDUs - COLO3 Cell 3 | 2025-03-26 08:00 | 2025-04-01 17:00 | 41
CHI05-03-03-L2-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 | Interior - L2 AHUs - COLO3 Cell 3 | 2025-04-09 08:00 | 2025-04-15 17:00 | 41
CHI05-03-03-L2-1660 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 | Interior - L2 ATSs - COLO3 Cell 3 | 2025-03-18 08:00 | 2025-03-24 17:00 | 52
CHI05-03-03-L2-1670 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 | Interior - L2 Busway - COLO3 Cell 3 | 2025-04-02 08:00 | 2025-04-08 17:00 | 41
CHI05-03-03-L2-1730 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 | Interior - L2 ADP - COLO3 Cell 3 | 2025-03-11 08:00 | 2025-03-17 17:00 | 52
CHI05-03-03-L3-1740 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 | Interior - L3 UPS - COLO3 Cell 3 | 2025-03-26 08:00 | 2025-04-01 17:00 | 36
CHI05-03-03-L3-1750 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 | Interior - L3 MSB - COLO3 Cell 3 | 2025-04-02 08:00 | 2025-04-08 17:00 | 36
CHI05-03-03-L3-1760 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 | Interior - L3 PDUs - COLO3 Cell 3 | 2025-04-09 08:00 | 2025-04-15 17:00 | 36
CHI05-03-03-L3-1770 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 | Interior - L3 AHUs - COLO3 Cell 3 | 2025-04-23 08:00 | 2025-04-29 17:00 | 36
CHI05-03-03-L3-1780 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 | Interior - L3 ATSs - COLO3 Cell 3 | 2025-04-23 08:00 | 2025-04-29 17:00 | 36
CHI05-03-03-L3-1790 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 | Interior - L3 Busway - COLO3 Cell 3 | 2025-04-23 08:00 | 2025-04-29 17:00 | 36
CHI05-03-03-L3-1850 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 | Interior - L3 ADP - COLO3 Cell 3 | 2025-04-16 08:00 | 2025-04-22 17:00 | 36
CHI05-03-04-MG-1440 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 4 - MG | 2024-11-27 08:00 | 2024-12-04 17:00 | 4
CHI05-03-04-MG-1450 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 4 - MG | 2024-12-02 08:00 | 2024-12-06 17:00 | 47
CHI05-03-04-MG-1460 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 | Overhead MEP Installation - COLO3 Cell 4 - MG | 2024-12-31 08:00 | 2025-01-14 17:00 | 32
CHI05-03-04-MG-1470 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 | Deliver AHU into Mech. Gallery - COLO3 Cell 4 - MG | 2025-01-15 08:00 | 2025-01-16 17:00 | 32
CHI05-03-04-MG-1480 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 | Install Walls and Primer Paint - COLO3 Cell 4 - MG | 2025-01-17 08:00 | 2025-01-30 17:00 | 32
CHI05-03-04-MG-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 | Placing the AHU - COLO3 Cell 4 - MG | 2025-02-07 08:00 | 2025-02-11 12:00 | 72
CHI05-03-04-MG-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 | Layout Ceiling and install Pencile Rod - COLO3 Cell 4 - MG | 2025-01-31 08:00 | 2025-01-31 17:00 | 76
CHI05-03-04-MG-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 | Piping and Electrical Termination to AHUs - COLO3 Cell 4 - MG | 2025-02-11 13:00 | 2025-02-25 12:00 | 72
CHI05-03-04-MG-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 | Pipe Testing - COLO3 Cell 4 - MG | 2025-02-25 13:00 | 2025-02-27 12:00 | 72
CHI05-03-04-MG-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 | Install ceiling and Light Fittings - COLO3 Cell 4 - MG | 2025-02-27 13:00 | 2025-03-11 12:00 | 72
CHI05-03-04-MG-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 | Trim out MEP - COLO3 Cell 4 - MG | 2025-03-04 13:00 | 2025-03-11 12:00 | 72
CHI05-03-04-MG-1485 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 | Post Wall Overhead MEP - COLO3 Cell 4 - MG | 2025-01-31 08:00 | 2025-02-20 17:00 | 72
CHI05-03-04-ER-1440 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 | Install Walls and Primer Paint - COLO3 Cell 4 - ER | 2024-12-19 08:00 | 2025-01-03 17:00 | 0
CHI05-03-04-ER-1450 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 4 - ER | 2025-01-08 08:00 | 2025-01-21 17:00 | 29
CHI05-03-04-ER-1460 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 | Install Upper Screens - COLO3 Cell 4 - ER | 2024-12-31 08:00 | 2025-01-07 17:00 | 29
CHI05-03-04-ER-1470 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 | Install Ceiling - COLO3 Cell 4 - ER | 2025-01-22 08:00 | 2025-01-24 17:00 | 29
CHI05-03-04-ER-1480 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | 2025-01-29 08:00 | 2025-02-11 17:00 | 27
CHI05-03-04-ER-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 | Installation of ADP & ATS - COLO3 Cell 4 - ER | 2025-01-31 08:00 | 2025-02-06 17:00 | 69
CHI05-03-04-ER-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 | Installation of UPS Equipment - COLO3 Cell 4 - ER | 2025-02-12 08:00 | 2025-02-18 17:00 | 27
CHI05-03-04-ER-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 | Connet to Cable tray and conduit equipment - COLO3 Cell 4 - ER | 2025-02-04 08:00 | 2025-02-10 17:00 | 106
CHI05-03-04-ER-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 | Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER | 2025-03-17 08:00 | 2025-04-04 17:00 | 82
CHI05-03-04-ER-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 | Door Frame Installation - COLO3 Cell 4 - ER | 2025-02-19 08:00 | 2025-02-25 17:00 | 27
CHI05-03-04-ER-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 | Finishes and Signage - COLO3 Cell 4 - ER | 2025-04-02 08:00 | 2025-04-08 17:00 | 82
CHI05-03-04-ER-1495 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 | Installation of MSB - COLO3 Cell 4 - ER | 2025-01-31 08:00 | 2025-02-06 17:00 | 59
CHI05-03-04-DH-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 | Termination at PDU & Busway - COLO3 Cell 4 - DH | 2025-03-26 08:00 | 2025-04-15 17:00 | 17
CHI05-03-04-DH-1440 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 4 - DH | 2024-12-30 08:00 | 2025-01-15 17:00 | 46
CHI05-03-04-DH-1450 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 | HAC install and Rise - COLO3 Cell 4 - DH | 2025-03-05 08:00 | 2025-03-11 17:00 | 56
CHI05-03-04-DH-1460 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 | Cable Pulling at PDU & Busway- COLO3 Cell 4 - DH | 2025-03-05 08:00 | 2025-03-18 17:00 | 37
CHI05-03-04-DH-1470 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 | Security Screen Installation - COLO3 Cell 4 - DH | 2025-01-31 08:00 | 2025-02-04 17:00 | 32
CHI05-03-04-DH-1480 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 | Ceiling Grid and Tile - COLO3 Cell 4 - DH | 2025-02-05 08:00 | 2025-02-11 17:00 | 32
CHI05-03-04-DH-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 | Install PDU's - COLO3 Cell 4 - DH | 2025-02-26 08:00 | 2025-03-04 17:00 | 32
CHI05-03-04-DH-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 4 - DH | 2025-02-12 08:00 | 2025-02-25 17:00 | 32
CHI05-03-04-DH-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH | 2025-03-12 08:00 | 2025-03-25 17:00 | 56
CHI05-03-04-DH-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 | HAC Placing - COLO3 Cell 4 - DH | 2025-02-26 08:00 | 2025-03-04 17:00 | 56
CHI05-03-04-DH-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 | Finishes and Signage - COLO3 Cell 4 - DH | 2025-04-09 08:00 | 2025-04-15 17:00 | 77
CHI05-03-04-L1-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 | Interior - L1 UPS - COLO3 Cell 4 | 2025-02-12 08:00 | 2025-02-12 17:00 | 52
CHI05-03-04-L1-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 | Interior - L1 MSB - COLO3 Cell 4 | 2025-02-13 08:00 | 2025-02-13 17:00 | 55
CHI05-03-04-L1-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 | Interior - L1 PDUs - COLO3 Cell 4 | 2025-03-05 08:00 | 2025-03-05 17:00 | 46
CHI05-03-04-L1-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 | Interior - L1 AHUs - COLO3 Cell 4 | 2025-03-07 08:00 | 2025-03-07 17:00 | 63
CHI05-03-04-L1-1660 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 | Interior - L1 ATSs - COLO3 Cell 4 | 2025-02-17 08:00 | 2025-02-17 17:00 | 68
CHI05-03-04-L1-1670 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 | Interior - L1 Busway - COLO3 Cell 4 | 2025-03-06 08:00 | 2025-03-06 17:00 | 59
CHI05-03-04-L1-1730 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 | Interior - L1 ADP - COLO3 Cell 4 | 2025-02-14 08:00 | 2025-02-14 17:00 | 64
CHI05-03-04-L2-1740 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 | Interior - L2 UPS - COLO3 Cell 4 | 2025-02-25 08:00 | 2025-03-03 17:00 | 43
CHI05-03-04-L2-1750 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 | Interior - L2 MSB - COLO3 Cell 4 | 2025-03-04 08:00 | 2025-03-10 17:00 | 43
CHI05-03-04-L2-1760 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 | Interior - L2 PDUs - COLO3 Cell 4 | 2025-04-16 08:00 | 2025-04-22 17:00 | 17
CHI05-03-04-L2-1770 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 | Interior - L2 AHUs - COLO3 Cell 4 | 2025-04-30 08:00 | 2025-05-06 17:00 | 26
CHI05-03-04-L2-1780 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 | Interior - L2 ATSs - COLO3 Cell 4 | 2025-03-18 08:00 | 2025-03-24 17:00 | 48
CHI05-03-04-L2-1790 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 | Interior - L2 Busway - COLO3 Cell 4 | 2025-04-23 08:00 | 2025-04-29 17:00 | 26
CHI05-03-04-L2-1850 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 | Interior - L2 ADP - COLO3 Cell 4 | 2025-03-11 08:00 | 2025-03-17 17:00 | 48
CHI05-03-04-L3-1860 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 | Interior - L3 UPS - COLO3 Cell 4 | 2025-03-26 08:00 | 2025-04-01 17:00 | 27
CHI05-03-04-L3-1870 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 | Interior - L3 MSB - COLO3 Cell 4 | 2025-04-02 08:00 | 2025-04-08 17:00 | 27
CHI05-03-04-L3-1880 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 | Interior - L3 PDUs - COLO3 Cell 4 | 2025-04-23 08:00 | 2025-04-29 17:00 | 17
CHI05-03-04-L3-1890 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 | Interior - L3 AHUs - COLO3 Cell 4 | 2025-05-20 08:00 | 2025-05-27 17:00 | 17
CHI05-03-04-L3-1900 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 | Interior - L3 ATSs - COLO3 Cell 4 | 2025-05-07 08:00 | 2025-05-13 17:00 | 17
CHI05-03-04-L3-1910 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 | Interior - L3 Busway - COLO3 Cell 4 | 2025-05-14 08:00 | 2025-05-20 17:00 | 17
CHI05-03-04-L3-1970 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 | Interior - L3 ADP - COLO3 Cell 4 | 2025-04-30 08:00 | 2025-05-06 17:00 | 17
CHI05-03-04-L4-1000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,5,1 | Cx LEV4 - COLO3 | 2025-05-28 08:00 | 2025-06-30 17:00 | 17
CHI05-03-04-L5-1000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,1,5,2 | Cx LEV5 / IST - COLO3 | 2025-07-01 08:00 | 2025-07-02 17:00 | 17
CHI05-04-01-MG-1220 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 1 - MG | 2024-12-05 08:00 | 2024-12-11 17:00 | 4
CHI05-04-01-MG-1230 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 1 - MG | 2024-12-06 08:00 | 2024-12-12 17:00 | 4
CHI05-04-01-MG-1240 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 | Overhead MEP Installation - COLO4 Cell 1 - MG | 2024-12-13 08:00 | 2024-12-27 17:00 | 4
CHI05-04-01-MG-1250 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 | Deliver AHU into Mech. Gallery - COLO4 Cell 1 - MG | 2024-12-30 08:00 | 2024-12-31 17:00 | 4
CHI05-04-01-MG-1260 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 | Install Walls and Primer Paint - COLO4 Cell 1 - MG | 2025-01-02 08:00 | 2025-01-15 17:00 | 4
CHI05-04-01-MG-1270 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 | Placing the AHU - COLO4 Cell 1 - MG | 2025-01-23 08:00 | 2025-01-27 12:00 | 58
CHI05-04-01-MG-1280 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 | Layout Ceiling and install Pencile Rod - COLO4 Cell 1 - MG | 2025-01-16 08:00 | 2025-01-16 17:00 | 62
CHI05-04-01-MG-1290 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 | Piping and Electrical Termination to AHUs - COLO4 Cell 1 - MG | 2025-01-27 13:00 | 2025-02-10 12:00 | 58
CHI05-04-01-MG-1300 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 | Pipe Testing - COLO4 Cell 1 - MG | 2025-02-10 13:00 | 2025-02-12 12:00 | 64
CHI05-04-01-MG-1310 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 | Install ceiling and Light Fittings - COLO4 Cell 1 - MG | 2025-02-12 13:00 | 2025-02-24 12:00 | 64
CHI05-04-01-MG-1320 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 | Trim out MEP - COLO4 Cell 1 - MG | 2025-02-17 13:00 | 2025-02-24 12:00 | 73
CHI05-04-01-MG-1265 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 | Post Wall Overhead MEP - COLO4 Cell 1 - MG | 2025-01-16 08:00 | 2025-02-05 17:00 | 58
CHI05-04-01-ER-1220 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 | Install Walls and Primer Paint - COLO4 Cell 1 - ER | 2025-01-06 08:00 | 2025-01-17 17:00 | 0
CHI05-04-01-ER-1230 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 1 - ER | 2025-01-20 08:00 | 2025-01-31 17:00 | 2
CHI05-04-01-ER-1240 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 | Install Upper Screens - COLO4 Cell 1 - ER | 2025-01-13 08:00 | 2025-01-17 17:00 | 2
CHI05-04-01-ER-1250 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 | Install Ceiling - COLO4 Cell 1 - ER | 2025-02-03 08:00 | 2025-02-05 17:00 | 2
CHI05-04-01-ER-1260 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 | Below Ceiling MEP Rough In - COLO4 Cell 1 - ER | 2025-02-06 08:00 | 2025-02-19 17:00 | 2
CHI05-04-01-ER-1270 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 | Installation of ADP & ATS - COLO4 Cell 1 - ER | 2025-02-10 08:00 | 2025-02-14 17:00 | 36
CHI05-04-01-ER-1280 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 | Installation of UPS Equipment - COLO4 Cell 1 - ER | 2025-02-13 08:00 | 2025-02-19 17:00 | 17
CHI05-04-01-ER-1290 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 | Connet to Cable tray and conduit equipment - COLO4 Cell 1 - ER | 2025-02-12 08:00 | 2025-02-18 17:00 | 57
CHI05-04-01-ER-1300 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 | Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER | 2025-02-19 08:00 | 2025-03-11 17:00 | 57
CHI05-04-01-ER-1310 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 | Door Frame Installation - COLO4 Cell 1 - ER | 2025-02-20 08:00 | 2025-02-26 17:00 | 32
CHI05-04-01-ER-1320 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 | Finishes and Signage - COLO4 Cell 1 - ER | 2025-03-07 08:00 | 2025-03-13 17:00 | 85
CHI05-04-01-ER-1285 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 | Installation of MSB - COLO4 Cell 1 - ER | 2025-02-10 08:00 | 2025-02-14 17:00 | 36
CHI05-04-01-DH-1210 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 | Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH | 2025-02-20 08:00 | 2025-03-12 17:00 | 2
CHI05-04-01-DH-1220 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 1 - DH | 2025-01-06 08:00 | 2025-01-21 17:00 | 3
CHI05-04-01-DH-1230 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 | HAC install and Rise - COLO4 Cell 1 - DH | 2025-02-20 08:00 | 2025-02-26 17:00 | 40
CHI05-04-01-DH-1240 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 | Termination at PDU & Busway- COLO4 Cell 1 - DH | 2025-02-20 08:00 | 2025-03-05 17:00 | 7
CHI05-04-01-DH-1250 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 | Security Screen Installation - COLO4 Cell 1 - DH | 2025-01-20 08:00 | 2025-01-22 17:00 | 2
CHI05-04-01-DH-1260 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 | Ceiling Grid and Tile - COLO4 Cell 1 - DH | 2025-01-23 08:00 | 2025-01-29 17:00 | 2
CHI05-04-01-DH-1270 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 | Install PDU's - COLO4 Cell 1 - DH | 2025-02-13 08:00 | 2025-02-19 17:00 | 2
CHI05-04-01-DH-1280 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 1 - DH | 2025-01-30 08:00 | 2025-02-12 17:00 | 2
CHI05-04-01-DH-1290 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH | 2025-02-27 08:00 | 2025-03-12 17:00 | 40
CHI05-04-01-DH-1300 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 | HAC Placing - COLO4 Cell 1 - DH | 2025-02-13 08:00 | 2025-02-19 17:00 | 40
CHI05-04-01-DH-1310 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 | Finishes and Signage - COLO4 Cell 1 - DH | 2025-03-13 08:00 | 2025-03-19 17:00 | 81
CHI05-04-01-L1-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 | Interior - L1 UPS - COLO4 Cell 1 | 2025-02-20 08:00 | 2025-02-20 17:00 | 46
CHI05-04-01-L1-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 | Interior - L1 MSB - COLO4 Cell 1 | 2025-02-21 08:00 | 2025-02-21 17:00 | 63
CHI05-04-01-L1-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 | Interior - L1 PDUs - COLO4 Cell 1 | 2025-02-24 08:00 | 2025-02-24 17:00 | 67
CHI05-04-01-L1-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 | Interior - L1 AHUs - COLO4 Cell 1 | 2025-02-26 08:00 | 2025-02-26 17:00 | 75
CHI05-04-01-L1-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 | Interior - L1 ATSs - COLO4 Cell 1 | 2025-02-25 08:00 | 2025-02-25 17:00 | 71
CHI05-04-01-L1-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 | Interior - L1 Busway - COLO4 Cell 1 | 2025-02-25 08:00 | 2025-02-25 17:00 | 71
CHI05-04-01-L1-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 | Interior - L1 ADP - COLO4 Cell 1 | 2025-02-24 08:00 | 2025-02-24 17:00 | 67
CHI05-04-01-L2-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 | Interior - L2 UPS - COLO4 Cell 1 | 2025-02-25 08:00 | 2025-03-03 17:00 | 57
CHI05-04-01-L2-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 | Interior - L2 MSB - COLO4 Cell 1 | 2025-03-04 08:00 | 2025-03-10 17:00 | 57
CHI05-04-01-L2-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 | Interior - L2 PDUs - COLO4 Cell 1 | 2025-03-13 08:00 | 2025-03-19 17:00 | 55
CHI05-04-01-L2-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 | Interior - L2 AHUs - COLO4 Cell 1 | 2025-03-27 08:00 | 2025-04-02 17:00 | 55
CHI05-04-01-L2-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 | Interior - L2 ATSs - COLO4 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00 | 57
CHI05-04-01-L2-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 | Interior - L2 Busway - COLO4 Cell 1 | 2025-03-20 08:00 | 2025-03-26 17:00 | 55
CHI05-04-01-L2-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 | Interior - L2 ADP - COLO4 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00 | 57
CHI05-04-01-L3-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 | Interior - L3 UPS - COLO4 Cell 1 | 2025-05-12 08:00 | 2025-05-16 17:00 | 8
CHI05-04-01-L3-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 | Interior - L3 MSB - COLO4 Cell 1 | 2025-05-19 08:00 | 2025-05-23 17:00 | 8
CHI05-04-01-L3-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 | Interior - L3 PDUs - COLO4 Cell 1 | 2025-05-27 08:00 | 2025-06-02 17:00 | 8
CHI05-04-01-L3-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 | Interior - L3 AHUs - COLO4 Cell 1 | 2025-06-10 08:00 | 2025-06-16 17:00 | 8
CHI05-04-01-L3-1660 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 | Interior - L3 ATSs - COLO4 Cell 1 | 2025-06-03 08:00 | 2025-06-09 17:00 | 8
CHI05-04-01-L3-1670 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 | Interior - L3 Busway - COLO4 Cell 1 | 2025-06-10 08:00 | 2025-06-16 17:00 | 8
CHI05-04-01-L3-1730 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 | Interior - L3 ADP - COLO4 Cell 1 | 2025-05-27 08:00 | 2025-06-02 17:00 | 8
CHI05-04-02-MG-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 2 - MG | 2024-12-12 08:00 | 2024-12-18 17:00 | 13
CHI05-04-02-MG-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 2 - MG | 2024-12-16 08:00 | 2024-12-20 17:00 | 13
CHI05-04-02-MG-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 | Overhead MEP Installation - COLO4 Cell 2 - MG | 2024-12-30 08:00 | 2025-01-13 17:00 | 9
CHI05-04-02-MG-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 | Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG | 2025-01-14 08:00 | 2025-01-15 17:00 | 9
CHI05-04-02-MG-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 | Install Walls and Primer Paint - COLO4 Cell 2 - MG | 2025-01-16 08:00 | 2025-01-29 17:00 | 9
CHI05-04-02-MG-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 | Placing the AHU - COLO4 Cell 2 - MG | 2025-02-06 08:00 | 2025-02-10 12:00 | 56
CHI05-04-02-MG-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 | Layout Ceiling and install Pencile Rod - COLO4 Cell 2 - MG | 2025-01-30 08:00 | 2025-01-30 17:00 | 60
CHI05-04-02-MG-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 | Piping and Electrical Termination to AHUs - COLO4 Cell 2 - MG | 2025-02-10 13:00 | 2025-02-24 12:00 | 58
CHI05-04-02-MG-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 | Pipe Testing - COLO4 Cell 2 - MG | 2025-02-24 13:00 | 2025-02-26 12:00 | 62
CHI05-04-02-MG-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 | Install ceiling and Light Fittings - COLO4 Cell 2 - MG | 2025-02-26 13:00 | 2025-03-10 12:00 | 62
CHI05-04-02-MG-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 | Trim out MEP - COLO4 Cell 2 - MG | 2025-03-03 13:00 | 2025-03-10 12:00 | 68
CHI05-04-02-MG-1375 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 | Post Wall Overhead MEP - COLO4 Cell 2 - MG | 2025-01-30 08:00 | 2025-02-19 17:00 | 56
CHI05-04-02-ER-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 | Install Walls and Primer Paint - COLO4 Cell 2 - ER | 2025-01-20 08:00 | 2025-01-31 17:00 | 0
CHI05-04-02-ER-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 2 - ER | 2025-02-05 08:00 | 2025-02-18 17:00 | 0
CHI05-04-02-ER-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 | Install Upper Screens - COLO4 Cell 2 - ER | 2025-01-29 08:00 | 2025-02-04 17:00 | 0
CHI05-04-02-ER-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 | Install Ceiling - COLO4 Cell 2 - ER | 2025-02-19 08:00 | 2025-02-21 17:00 | 0
CHI05-04-02-ER-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | 2025-02-24 08:00 | 2025-03-07 17:00 | 0
CHI05-04-02-ER-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 | Installation of ADP & ATS - COLO4 Cell 2 - ER | 2025-02-26 08:00 | 2025-03-04 17:00 | 29
CHI05-04-02-ER-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 | Installation of UPS Equipment - COLO4 Cell 2 - ER | 2025-03-03 08:00 | 2025-03-07 17:00 | 10
CHI05-04-02-ER-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 | Connet to Cable tray and conduit equipment - COLO4 Cell 2 - ER | 2025-02-28 08:00 | 2025-03-06 17:00 | 60
CHI05-04-02-ER-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 | Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER | 2025-03-12 08:00 | 2025-04-01 17:00 | 57
CHI05-04-02-ER-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 | Door Frame Installation - COLO4 Cell 2 - ER | 2025-03-10 08:00 | 2025-03-14 17:00 | 48
CHI05-04-02-ER-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 | Finishes and Signage - COLO4 Cell 2 - ER | 2025-03-28 08:00 | 2025-04-03 17:00 | 75
CHI05-04-02-ER-1385 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 | Installation of MSB - COLO4 Cell 2 - ER | 2025-02-26 08:00 | 2025-03-04 17:00 | 29
CHI05-04-02-DH-1320 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 | Termination at PDU & Busway - COLO4 Cell 2 - DH | 2025-03-13 08:00 | 2025-04-02 17:00 | 2
CHI05-04-02-DH-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH | 2025-01-22 08:00 | 2025-02-06 17:00 | 6
CHI05-04-02-DH-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 | HAC install and Rise - COLO4 Cell 2 - DH | 2025-03-10 08:00 | 2025-03-14 17:00 | 38
CHI05-04-02-DH-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 | Cable Pulling at PDU & Busway- COLO4 Cell 2 - DH | 2025-03-10 08:00 | 2025-03-21 17:00 | 10
CHI05-04-02-DH-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 | Security Screen Installation - COLO4 Cell 2 - DH | 2025-02-05 08:00 | 2025-02-07 17:00 | 5
CHI05-04-02-DH-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 | Ceiling Grid and Tile - COLO4 Cell 2 - DH | 2025-02-10 08:00 | 2025-02-14 17:00 | 5
CHI05-04-02-DH-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 | Install PDU's - COLO4 Cell 2 - DH | 2025-03-03 08:00 | 2025-03-07 17:00 | 5
CHI05-04-02-DH-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH | 2025-02-17 08:00 | 2025-02-28 17:00 | 5
CHI05-04-02-DH-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 2 - DH | 2025-03-17 08:00 | 2025-03-28 17:00 | 38
CHI05-04-02-DH-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 | HAC Placing - COLO4 Cell 2 - DH | 2025-03-03 08:00 | 2025-03-07 17:00 | 35
CHI05-04-02-DH-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 | Finishes and Signage - COLO4 Cell 2 - DH | 2025-03-31 08:00 | 2025-04-04 17:00 | 74
CHI05-04-02-L1-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 | Interior - L1 UPS - COLO4 Cell 2 | 2025-03-10 08:00 | 2025-03-10 17:00 | 35
CHI05-04-02-L1-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 | Interior - L1 MSB - COLO4 Cell 2 | 2025-03-11 08:00 | 2025-03-11 17:00 | 45
CHI05-04-02-L1-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 | Interior - L1 PDUs - COLO4 Cell 2 | 2025-03-12 08:00 | 2025-03-12 17:00 | 55
CHI05-04-02-L1-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 | Interior - L1 AHUs - COLO4 Cell 2 | 2025-03-14 08:00 | 2025-03-14 17:00 | 63
CHI05-04-02-L1-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 | Interior - L1 ATSs - COLO4 Cell 2 | 2025-03-13 08:00 | 2025-03-13 17:00 | 59
CHI05-04-02-L1-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 | Interior - L1 Busway - COLO4 Cell 2 | 2025-03-13 08:00 | 2025-03-13 17:00 | 59
CHI05-04-02-L1-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 | Interior - L1 ADP - COLO4 Cell 2 | 2025-03-12 08:00 | 2025-03-12 17:00 | 45
CHI05-04-02-L2-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 | Interior - L2 UPS - COLO4 Cell 2 | 2025-03-13 08:00 | 2025-03-19 17:00 | 45
CHI05-04-02-L2-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 | Interior - L2 MSB - COLO4 Cell 2 | 2025-03-20 08:00 | 2025-03-26 17:00 | 45
CHI05-04-02-L2-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 | Interior - L2 PDUs - COLO4 Cell 2 | 2025-04-03 08:00 | 2025-04-09 17:00 | 40
CHI05-04-02-L2-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 | Interior - L2 AHUs - COLO4 Cell 2 | 2025-04-17 08:00 | 2025-04-23 17:00 | 40
CHI05-04-02-L2-1660 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 | Interior - L2 ATSs - COLO4 Cell 2 | 2025-04-03 08:00 | 2025-04-09 17:00 | 45
CHI05-04-02-L2-1670 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 | Interior - L2 Busway - COLO4 Cell 2 | 2025-04-10 08:00 | 2025-04-16 17:00 | 40
CHI05-04-02-L2-1730 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 | Interior - L2 ADP - COLO4 Cell 2 | 2025-03-27 08:00 | 2025-04-02 17:00 | 45
CHI05-04-02-L3-1740 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 | Interior - L3 UPS - COLO4 Cell 2 | 2025-03-17 08:00 | 2025-03-21 17:00 | 48
CHI05-04-02-L3-1750 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 | Interior - L3 MSB - COLO4 Cell 2 | 2025-05-12 08:00 | 2025-05-16 17:00 | 13
CHI05-04-02-L3-1760 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 | Interior - L3 PDUs - COLO4 Cell 2 | 2025-05-19 08:00 | 2025-05-23 17:00 | 18
CHI05-04-02-L3-1770 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 | Interior - L3 AHUs - COLO4 Cell 2 | 2025-06-03 08:00 | 2025-06-09 17:00 | 13
CHI05-04-02-L3-1780 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 | Interior - L3 ATSs - COLO4 Cell 2 | 2025-05-27 08:00 | 2025-06-02 17:00 | 13
CHI05-04-02-L3-1790 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 | Interior - L3 Busway - COLO4 Cell 2 | 2025-06-03 08:00 | 2025-06-09 17:00 | 13
CHI05-04-02-L3-1850 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 | Interior - L3 ADP - COLO4 Cell 2 | 2025-05-19 08:00 | 2025-05-23 17:00 | 13
CHI05-04-03-MG-1440 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 3 - MG | 2024-12-19 08:00 | 2024-12-26 17:00 | 23
CHI05-04-03-MG-1450 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 3 - MG | 2024-12-23 08:00 | 2024-12-30 17:00 | 23
CHI05-04-03-MG-1460 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 | Overhead MEP Installation - COLO4 Cell 3 - MG | 2025-01-14 08:00 | 2025-01-27 17:00 | 14
CHI05-04-03-MG-1470 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 | Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG | 2025-01-28 08:00 | 2025-01-29 17:00 | 14
CHI05-04-03-MG-1480 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 | Install Walls and Primer Paint - COLO4 Cell 3 - MG | 2025-01-30 08:00 | 2025-02-12 17:00 | 14
CHI05-04-03-MG-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 | Placing the AHU - COLO4 Cell 3 - MG | 2025-02-20 08:00 | 2025-02-24 12:00 | 49
CHI05-04-03-MG-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 | Layout Ceiling and install Pencile Rod - COLO4 Cell 3 - MG | 2025-02-13 08:00 | 2025-02-13 17:00 | 53
CHI05-04-03-MG-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 | Piping and Electrical Termination to AHUs - COLO4 Cell 3 - MG | 2025-02-24 13:00 | 2025-03-10 12:00 | 58
CHI05-04-03-MG-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 | Pipe Testing - COLO4 Cell 3 - MG | 2025-03-10 13:00 | 2025-03-12 12:00 | 60
CHI05-04-03-MG-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 | Install ceiling and Light Fittings - COLO4 Cell 3 - MG | 2025-03-12 13:00 | 2025-03-24 12:00 | 60
CHI05-04-03-MG-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 | Trim out MEP - COLO4 Cell 3 - MG | 2025-03-17 13:00 | 2025-03-24 12:00 | 63
CHI05-04-03-MG-1485 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 | Post Wall Overhead MEP - COLO4 Cell 3 - MG | 2025-02-13 08:00 | 2025-03-05 17:00 | 49
CHI05-04-03-ER-1440 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 | Install Walls and Primer Paint - COLO4 Cell 3 - ER | 2025-02-03 08:00 | 2025-02-14 17:00 | 0
CHI05-04-03-ER-1450 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 3 - ER | 2025-02-19 08:00 | 2025-03-04 17:00 | 0
CHI05-04-03-ER-1460 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 | Install Upper Screens - COLO4 Cell 3 - ER | 2025-02-12 08:00 | 2025-02-18 17:00 | 0
CHI05-04-03-ER-1470 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 | Install Ceiling - COLO4 Cell 3 - ER | 2025-03-05 08:00 | 2025-03-07 17:00 | 0
CHI05-04-03-ER-1480 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | 2025-03-10 08:00 | 2025-03-21 17:00 | 0
CHI05-04-03-ER-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 | Installation of ADP & ATS - COLO4 Cell 3 - ER | 2025-03-12 08:00 | 2025-03-18 17:00 | 24
CHI05-04-03-ER-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 | Installation of UPS Equipment - COLO4 Cell 3 - ER | 2025-03-17 08:00 | 2025-03-21 17:00 | 5
CHI05-04-03-ER-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 | Connet to Cable tray and conduit equipment - COLO4 Cell 3 - ER | 2025-03-14 08:00 | 2025-03-20 17:00 | 65
CHI05-04-03-ER-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 | Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER | 2025-04-02 08:00 | 2025-04-22 17:00 | 57
CHI05-04-03-ER-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 | Door Frame Installation - COLO4 Cell 3 - ER | 2025-03-24 08:00 | 2025-03-28 17:00 | 10
CHI05-04-03-ER-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 | Finishes and Signage - COLO4 Cell 3 - ER | 2025-04-18 08:00 | 2025-04-24 17:00 | 65
CHI05-04-03-ER-1495 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 | Installation of MSB - COLO4 Cell 3 - ER | 2025-03-12 08:00 | 2025-03-18 17:00 | 24
CHI05-04-03-DH-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 | Termination at PDU & Busway - COLO4 Cell 3 - DH | 2025-04-03 08:00 | 2025-04-23 17:00 | 2
CHI05-04-03-DH-1440 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH | 2025-02-07 08:00 | 2025-02-24 17:00 | 9
CHI05-04-03-DH-1450 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 | HAC install and Rise - COLO4 Cell 3 - DH | 2025-03-25 08:00 | 2025-03-31 17:00 | 37
CHI05-04-03-DH-1460 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 | Cable Pulling at PDU & Busway- COLO4 Cell 3 - DH | 2025-03-25 08:00 | 2025-04-07 17:00 | 14
CHI05-04-03-DH-1470 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 | Security Screen Installation - COLO4 Cell 3 - DH | 2025-02-19 08:00 | 2025-02-21 17:00 | 10
CHI05-04-03-DH-1480 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 | Ceiling Grid and Tile - COLO4 Cell 3 - DH | 2025-02-25 08:00 | 2025-03-03 17:00 | 9
CHI05-04-03-DH-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 | Install PDU's - COLO4 Cell 3 - DH | 2025-03-18 08:00 | 2025-03-24 17:00 | 9
CHI05-04-03-DH-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH | 2025-03-04 08:00 | 2025-03-17 17:00 | 9
CHI05-04-03-DH-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 3 - DH | 2025-04-01 08:00 | 2025-04-14 17:00 | 37
CHI05-04-03-DH-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 | HAC Placing - COLO4 Cell 3 - DH | 2025-03-18 08:00 | 2025-03-24 17:00 | 29
CHI05-04-03-DH-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 | Finishes and Signage - COLO4 Cell 3 - DH | 2025-04-17 08:00 | 2025-04-23 17:00 | 66
CHI05-04-03-L1-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 | Interior - L1 UPS - COLO4 Cell 3 | 2025-03-24 08:00 | 2025-03-24 17:00 | 26
CHI05-04-03-L1-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 | Interior - L1 MSB - COLO4 Cell 3 | 2025-03-25 08:00 | 2025-03-25 17:00 | 33
CHI05-04-03-L1-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 | Interior - L1 PDUs - COLO4 Cell 3 | 2025-03-26 08:00 | 2025-03-26 17:00 | 33
CHI05-04-03-L1-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 | Interior - L1 AHUs - COLO4 Cell 3 | 2025-03-28 08:00 | 2025-03-28 17:00 | 33
CHI05-04-03-L1-1660 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 | Interior - L1 ATSs - COLO4 Cell 3 | 2025-03-27 08:00 | 2025-03-27 17:00 | 33
CHI05-04-03-L1-1670 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 | Interior - L1 Busway - COLO4 Cell 3 | 2025-03-27 08:00 | 2025-03-27 17:00 | 33
CHI05-04-03-L1-1730 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 | Interior - L1 ADP - COLO4 Cell 3 | 2025-03-26 08:00 | 2025-03-26 17:00 | 33
CHI05-04-03-L2-1740 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 | Interior - L2 UPS - COLO4 Cell 3 | 2025-03-31 08:00 | 2025-04-04 17:00 | 33
CHI05-04-03-L2-1750 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 | Interior - L2 MSB - COLO4 Cell 3 | 2025-04-07 08:00 | 2025-04-11 17:00 | 33
CHI05-04-03-L2-1760 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 | Interior - L2 PDUs - COLO4 Cell 3 | 2025-04-24 08:00 | 2025-04-30 17:00 | 25
CHI05-04-03-L2-1770 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 | Interior - L2 AHUs - COLO4 Cell 3 | 2025-05-08 08:00 | 2025-05-14 17:00 | 25
CHI05-04-03-L2-1780 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 | Interior - L2 ATSs - COLO4 Cell 3 | 2025-04-21 08:00 | 2025-04-25 17:00 | 33
CHI05-04-03-L2-1790 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 | Interior - L2 Busway - COLO4 Cell 3 | 2025-05-01 08:00 | 2025-05-07 17:00 | 25
CHI05-04-03-L2-1850 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 | Interior - L2 ADP - COLO4 Cell 3 | 2025-04-14 08:00 | 2025-04-18 17:00 | 33
CHI05-04-03-L3-1860 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 | Interior - L3 UPS - COLO4 Cell 3 | 2025-03-31 08:00 | 2025-04-04 17:00 | 38
CHI05-04-03-L3-1870 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 | Interior - L3 MSB - COLO4 Cell 3 | 2025-05-12 08:00 | 2025-05-16 17:00 | 13
CHI05-04-03-L3-1880 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 | Interior - L3 PDUs - COLO4 Cell 3 | 2025-05-19 08:00 | 2025-05-23 17:00 | 18
CHI05-04-03-L3-1890 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 | Interior - L3 AHUs - COLO4 Cell 3 | 2025-06-03 08:00 | 2025-06-09 17:00 | 13
CHI05-04-03-L3-1900 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 | Interior - L3 ATSs - COLO4 Cell 3 | 2025-05-27 08:00 | 2025-06-02 17:00 | 13
CHI05-04-03-L3-1910 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 | Interior - L3 Busway - COLO4 Cell 3 | 2025-06-03 08:00 | 2025-06-09 17:00 | 13
CHI05-04-03-L3-1970 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 | Interior - L3 ADP - COLO4 Cell 3 | 2025-05-19 08:00 | 2025-05-23 17:00 | 13
CHI05-04-04-MG-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 4 - MG | 2024-12-27 08:00 | 2025-01-03 17:00 | 33
CHI05-04-04-MG-1560 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG | 2024-12-31 08:00 | 2025-01-07 17:00 | 33
CHI05-04-04-MG-1570 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 | Overhead MEP Installation - COLO4 Cell 4 - MG | 2025-01-28 08:00 | 2025-02-10 17:00 | 19
CHI05-04-04-MG-1580 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 | Deliver AHU into Mech. Gallery - COLO4 Cell 4 - MG | 2025-02-11 08:00 | 2025-02-12 17:00 | 19
CHI05-04-04-MG-1590 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 | Install Walls and Primer Paint - COLO4 Cell 4 - MG | 2025-02-13 08:00 | 2025-02-26 17:00 | 19
CHI05-04-04-MG-1600 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 | Placing the AHU - COLO4 Cell 4 - MG | 2025-03-06 08:00 | 2025-03-10 12:00 | 41
CHI05-04-04-MG-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 | Layout Ceiling and install Pencile Rod - COLO4 Cell 4 - MG | 2025-02-27 08:00 | 2025-02-27 17:00 | 45
CHI05-04-04-MG-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 | Piping and Electrical Termination to AHUs - COLO4 Cell 4 - MG | 2025-03-10 13:00 | 2025-03-24 12:00 | 58
CHI05-04-04-MG-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 | Pipe Testing - COLO4 Cell 4 - MG | 2025-03-24 13:00 | 2025-03-26 12:00 | 58
CHI05-04-04-MG-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 | Install ceiling and Light Fittings - COLO4 Cell 4 - MG | 2025-03-26 13:00 | 2025-04-07 12:00 | 58
CHI05-04-04-MG-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 | Trim out MEP - COLO4 Cell 4 - MG | 2025-03-31 13:00 | 2025-04-07 12:00 | 58
CHI05-04-04-MG-1595 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 | Post Wall Overhead MEP - COLO4 Cell 4 - MG | 2025-02-27 08:00 | 2025-03-19 17:00 | 41
CHI05-04-04-ER-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 | Install Walls and Primer Paint - COLO4 Cell 4 - ER | 2025-02-17 08:00 | 2025-02-28 17:00 | 0
CHI05-04-04-ER-1560 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 4 - ER | 2025-03-05 08:00 | 2025-03-18 17:00 | 0
CHI05-04-04-ER-1570 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 | Install Upper Screens - COLO4 Cell 4 - ER | 2025-02-26 08:00 | 2025-03-04 17:00 | 0
CHI05-04-04-ER-1580 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 | Install Ceiling - COLO4 Cell 4 - ER | 2025-03-19 08:00 | 2025-03-21 17:00 | 0
CHI05-04-04-ER-1590 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | 2025-03-24 08:00 | 2025-04-04 17:00 | 0
CHI05-04-04-ER-1600 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 | Installation of ADP & ATS - COLO4 Cell 4 - ER | 2025-03-24 08:00 | 2025-03-28 17:00 | 23
CHI05-04-04-ER-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 | Installation of UPS Equipment - COLO4 Cell 4 - ER | 2025-03-31 08:00 | 2025-04-04 17:00 | 0
CHI05-04-04-ER-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 | Connet to Cable tray and conduit equipment - COLO4 Cell 4 - ER | 2025-03-24 08:00 | 2025-03-28 17:00 | 74
CHI05-04-04-ER-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 | Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER | 2025-04-23 08:00 | 2025-05-13 17:00 | 57
CHI05-04-04-ER-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 | Door Frame Installation - COLO4 Cell 4 - ER | 2025-04-07 08:00 | 2025-04-11 17:00 | 0
CHI05-04-04-ER-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 | Finishes and Signage - COLO4 Cell 4 - ER | 2025-05-07 08:00 | 2025-05-13 17:00 | 57
CHI05-04-04-ER-1625 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 | Installation of MSB - COLO4 Cell 4 - ER | 2025-03-24 08:00 | 2025-03-28 17:00 | 21
CHI05-04-04-DH-1635 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 | Closing Construction Access Door - COLO4 Cell 4 - DH | 2025-04-10 08:00 | 2025-04-30 17:00 | 40
CHI05-04-04-DH-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 | Termination at PDU & Busway - COLO4 Cell 4 - DH | 2025-04-24 08:00 | 2025-05-14 17:00 | 2
CHI05-04-04-DH-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 4 - DH | 2025-02-25 08:00 | 2025-03-12 17:00 | 12
CHI05-04-04-DH-1560 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 | HAC install and Rise - COLO4 Cell 4 - DH | 2025-04-10 08:00 | 2025-04-16 17:00 | 35
CHI05-04-04-DH-1570 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 | Cable Pulling at PDU & Busway- COLO4 Cell 4 - DH | 2025-04-10 08:00 | 2025-04-23 17:00 | 17
CHI05-04-04-DH-1580 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 | Security Screen Installation - COLO4 Cell 4 - DH | 2025-03-05 08:00 | 2025-03-07 17:00 | 15
CHI05-04-04-DH-1590 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 | Ceiling Grid and Tile - COLO4 Cell 4 - DH | 2025-03-13 08:00 | 2025-03-19 17:00 | 12
CHI05-04-04-DH-1600 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 | Install PDU's - COLO4 Cell 4 - DH | 2025-04-03 08:00 | 2025-04-09 17:00 | 12
CHI05-04-04-DH-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 4 - DH | 2025-03-20 08:00 | 2025-04-02 17:00 | 12
CHI05-04-04-DH-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH | 2025-04-17 08:00 | 2025-04-30 17:00 | 35
CHI05-04-04-DH-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 | HAC Placing - COLO4 Cell 4 - DH | 2025-04-03 08:00 | 2025-04-09 17:00 | 22
CHI05-04-04-DH-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 | Finishes and Signage - COLO4 Cell 4 - DH | 2025-05-08 08:00 | 2025-05-14 17:00 | 56
CHI05-04-04-L1-1740 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 | Interior - L1 UPS - COLO4 Cell 4 | 2025-04-07 08:00 | 2025-04-07 17:00 | 16
CHI05-04-04-L1-1750 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 | Interior - L1 MSB - COLO4 Cell 4 | 2025-04-07 08:00 | 2025-04-07 17:00 | 16
CHI05-04-04-L1-1760 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 | Interior - L1 PDUs - COLO4 Cell 4 | 2025-04-10 08:00 | 2025-04-10 17:00 | 14
CHI05-04-04-L1-1770 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 | Interior - L1 AHUs - COLO4 Cell 4 | 2025-04-14 08:00 | 2025-04-14 17:00 | 14
CHI05-04-04-L1-1780 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 | Interior - L1 ATSs - COLO4 Cell 4 | 2025-04-08 08:00 | 2025-04-08 17:00 | 17
CHI05-04-04-L1-1790 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 | Interior - L1 Busway - COLO4 Cell 4 | 2025-04-11 08:00 | 2025-04-11 17:00 | 14
CHI05-04-04-L1-1850 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 | Interior - L1 ADP - COLO4 Cell 4 | 2025-04-08 08:00 | 2025-04-08 17:00 | 17
CHI05-04-04-L2-1860 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 | Interior - L2 UPS - COLO4 Cell 4 | 2025-04-15 08:00 | 2025-04-21 17:00 | 14
CHI05-04-04-L2-1870 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 | Interior - L2 MSB - COLO4 Cell 4 | 2025-04-22 08:00 | 2025-04-28 17:00 | 14
CHI05-04-04-L2-1880 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 | Interior - L2 PDUs - COLO4 Cell 4 | 2025-05-15 08:00 | 2025-05-21 17:00 | 2
CHI05-04-04-L2-1890 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 | Interior - L2 AHUs - COLO4 Cell 4 | 2025-05-30 08:00 | 2025-06-05 17:00 | 10
CHI05-04-04-L2-1900 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 | Interior - L2 ATSs - COLO4 Cell 4 | 2025-05-06 08:00 | 2025-05-12 17:00 | 19
CHI05-04-04-L2-1910 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 | Interior - L2 Busway - COLO4 Cell 4 | 2025-05-22 08:00 | 2025-05-29 17:00 | 10
CHI05-04-04-L2-1970 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 | Interior - L2 ADP - COLO4 Cell 4 | 2025-04-29 08:00 | 2025-05-05 17:00 | 19
CHI05-04-04-L3-1980 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 | Interior - L3 UPS - COLO4 Cell 4 | 2025-05-12 08:00 | 2025-05-16 17:00 | 0
CHI05-04-04-L3-1990 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 | Interior - L3 MSB - COLO4 Cell 4 | 2025-05-19 08:00 | 2025-05-23 17:00 | 0
CHI05-04-04-L3-2000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 | Interior - L3 PDUs - COLO4 Cell 4 | 2025-05-27 08:00 | 2025-06-02 17:00 | 0
CHI05-04-04-L3-2010 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 | Interior - L3 AHUs - COLO4 Cell 4 | 2025-06-20 08:00 | 2025-06-26 17:00 | 0
CHI05-04-04-L3-2020 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 | Interior - L3 ATSs - COLO4 Cell 4 | 2025-06-10 08:00 | 2025-06-16 17:00 | 0
CHI05-04-04-L3-2030 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 | Interior - L3 Busway - COLO4 Cell 4 | 2025-06-17 08:00 | 2025-06-23 17:00 | 0
CHI05-04-04-L3-2090 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 | Interior - L3 ADP - COLO4 Cell 4 | 2025-06-03 08:00 | 2025-06-09 17:00 | 0
CHI05-04-04-L4-1000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 | Cx LEV4 - COLO4 | 2025-06-27 08:00 | 2025-07-31 17:00 | 0
CHI05-04-04-L5-1000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,2,5,2 | Cx LEV5 / IST - COLO4 | 2025-08-01 08:00 | 2025-08-04 17:00 | 0
CHI05-05-01-MG-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 1 - MG | 2024-10-07 08:00 | 2024-10-11 17:00 | 0
CHI05-05-01-MG-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 1 - MG | 2024-10-09 08:00 | 2024-10-15 17:00 | 53
CHI05-05-01-MG-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 | Overhead MEP Installation - COLO5 Cell 1 - MG | 2024-10-16 08:00 | 2024-10-29 17:00 | 53
CHI05-05-01-MG-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 | Deliver AHU into Mech. Gallery - COLO5 Cell 1 - MG | 2024-11-19 08:00 | 2024-11-20 17:00 | 39
CHI05-05-01-MG-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 | Install Walls and Primer Paint - COLO5 Cell 1 - MG | 2024-11-21 08:00 | 2024-12-05 17:00 | 39
CHI05-05-01-MG-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 | Placing the AHU - COLO5 Cell 1 - MG | 2024-12-13 08:00 | 2024-12-19 17:00 | 77
CHI05-05-01-MG-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 | Layout Ceiling and install Pencile Rod - COLO5 Cell 1 - MG | 2024-12-06 08:00 | 2024-12-06 17:00 | 81
CHI05-05-01-MG-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 | Piping and Electrical Termination to AHUs - COLO5 Cell 1 - MG | 2024-12-20 08:00 | 2025-01-06 17:00 | 77
CHI05-05-01-MG-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 | Pipe Testing - COLO5 Cell 1 - MG | 2025-01-07 08:00 | 2025-01-08 17:00 | 83
CHI05-05-01-MG-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 | Install ceiling and Light Fittings - COLO5 Cell 1 - MG | 2025-01-09 08:00 | 2025-01-20 17:00 | 83
CHI05-05-01-MG-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 | Trim out MEP - COLO5 Cell 1 - MG | 2025-01-21 08:00 | 2025-01-27 17:00 | 87
CHI05-05-01-MG-1375 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 | Post Wall Overhead MEP - COLO5 Cell 1 - MG | 2024-12-06 08:00 | 2024-12-27 17:00 | 77
CHI05-05-01-MG-1425 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 | Install Damper in Ceiling (RAD) - COLO 5 Cell 1 - MG | 2025-01-21 08:00 | 2025-01-27 17:00 | 87
CHI05-05-01-ER-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 | Install Walls and Primer Paint - COLO5 Cell 1 - ER | 2024-10-02 08:00 | 2024-10-15 17:00 | 58
CHI05-05-01-ER-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 1 - ER | 2024-10-23 08:00 | 2024-11-05 17:00 | 58
CHI05-05-01-ER-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 | Install Upper Screens - COLO5 Cell 1 - ER | 2024-10-16 08:00 | 2024-10-22 17:00 | 58
CHI05-05-01-ER-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 | Install Ceiling - COLO5 Cell 1 - ER | 2024-11-06 08:00 | 2024-11-08 17:00 | 58
CHI05-05-01-ER-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 | Below Ceiling MEP Rough In - COLO5 Cell 1 - ER | 2024-11-11 08:00 | 2024-11-22 17:00 | 58
CHI05-05-01-ER-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 | Installation of ADP & ATS - COLO5 Cell 1 - ER | 2024-11-29 08:00 | 2024-12-05 17:00 | 87
CHI05-05-01-ER-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 | Installation of UPS Equipment - COLO5 Cell 1 - ER | 2024-11-25 08:00 | 2024-12-02 17:00 | 73
CHI05-05-01-ER-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 | Connet to Cable tray and conduit equipment - COLO5 Cell 1 - ER | 2024-12-10 08:00 | 2024-12-16 17:00 | 94
CHI05-05-01-ER-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 | Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER | 2024-12-17 08:00 | 2025-01-08 17:00 | 94
CHI05-05-01-ER-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 | Door Frame Installation - COLO5 Cell 1 - ER | 2024-12-03 08:00 | 2024-12-09 17:00 | 88
CHI05-05-01-ER-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 | Finishes and Signage - COLO5 Cell 1 - ER | 2025-01-06 08:00 | 2025-01-10 17:00 | 109
CHI05-05-01-ER-1385 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 | Installation of MSB - COLO5 Cell 1 - ER | 2024-12-06 08:00 | 2024-12-12 17:00 | 81
CHI05-05-01-DH-1320 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 | Cable Pulling at PDU & Busway - COLO5 Cell 1 - DH | 2024-12-26 08:00 | 2025-01-16 17:00 | 44
CHI05-05-01-DH-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 1 - DH | 2024-10-02 08:00 | 2024-10-29 17:00 | 63
CHI05-05-01-DH-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 | HAC install and Rise - COLO5 Cell 1 - DH | 2024-12-26 08:00 | 2025-01-02 17:00 | 74
CHI05-05-01-DH-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 | Termination at PDU & Busway- COLO5 Cell 1 - DH | 2024-12-26 08:00 | 2025-01-09 17:00 | 49
CHI05-05-01-DH-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 | Security Screen Installation - COLO5 Cell 1 - DH | 2024-11-21 08:00 | 2024-11-25 17:00 | 44
CHI05-05-01-DH-1370 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 | Ceiling Grid and Tile - COLO5 Cell 1 - DH | 2024-11-26 08:00 | 2024-12-03 17:00 | 44
CHI05-05-01-DH-1380 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 | Install PDU's - COLO5 Cell 1 - DH | 2024-12-18 08:00 | 2024-12-24 17:00 | 44
CHI05-05-01-DH-1390 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 1 - DH | 2024-12-04 08:00 | 2024-12-17 17:00 | 44
CHI05-05-01-DH-1400 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 1 - DH | 2025-01-03 08:00 | 2025-01-16 17:00 | 74
CHI05-05-01-DH-1410 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 | HAC Placing - COLO5 Cell 1 - DH | 2024-12-18 08:00 | 2024-12-24 17:00 | 74
CHI05-05-01-DH-1420 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 | Finishes and Signage - COLO5 Cell 1 - DH | 2025-01-17 08:00 | 2025-01-23 17:00 | 105
CHI05-05-01-L1-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 | Interior - L1 UPS - COLO5 Cell 1 | 2024-12-03 08:00 | 2024-12-03 17:00 | 103
CHI05-05-01-L1-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 | Interior - L1 MSB - COLO5 Cell 1 | 2024-12-13 08:00 | 2024-12-13 17:00 | 106
CHI05-05-01-L1-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 | Interior - L1 PDUs - COLO5 Cell 1 | 2024-12-26 08:00 | 2024-12-26 17:00 | 103
CHI05-05-01-L1-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 | Interior - L1 AHUs - COLO5 Cell 1 | 2025-01-03 08:00 | 2025-01-03 17:00 | 108
CHI05-05-01-L1-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 | Interior - L1 ATSs - COLO5 Cell 1 | 2024-12-17 08:00 | 2024-12-17 17:00 | 114
CHI05-05-01-L1-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 | Interior - L1 Busway - COLO5 Cell 1 | 2024-12-27 08:00 | 2024-12-27 17:00 | 107
CHI05-05-01-L1-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 | Interior - L1 ADP - COLO5 Cell 1 | 2024-12-16 08:00 | 2024-12-16 17:00 | 110
CHI05-05-01-L2-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 | Interior - L2 UPS - COLO5 Cell 1 | 2025-02-25 08:00 | 2025-03-03 17:00 | 52
CHI05-05-01-L2-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 | Interior - L2 MSB - COLO5 Cell 1 | 2025-03-04 08:00 | 2025-03-10 17:00 | 52
CHI05-05-01-L2-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 | Interior - L2 PDUs - COLO5 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00 | 52
CHI05-05-01-L2-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 | Interior - L2 AHUs - COLO5 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00 | 52
CHI05-05-01-L2-1660 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 | Interior - L2 ATSs - COLO5 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00 | 52
CHI05-05-01-L2-1670 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 | Interior - L2 Busway - COLO5 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00 | 52
CHI05-05-01-L2-1730 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 | Interior - L2 ADP - COLO5 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00 | 52
CHI05-05-01-L3-1740 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 | Interior - L3 UPS - COLO5 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00 | 37
CHI05-05-01-L3-1750 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 | Interior - L3 MSB - COLO5 Cell 1 | 2025-04-01 08:00 | 2025-04-07 17:00 | 37
CHI05-05-01-L3-1760 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 | Interior - L3 PDUs - COLO5 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00 | 37
CHI05-05-01-L3-1770 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 | Interior - L3 AHUs - COLO5 Cell 1 | 2025-04-22 08:00 | 2025-04-28 17:00 | 37
CHI05-05-01-L3-1780 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 | Interior - L3 ATSs - COLO5 Cell 1 | 2025-04-15 08:00 | 2025-04-21 17:00 | 37
CHI05-05-01-L3-1790 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 | Interior - L3 Busway - COLO5 Cell 1 | 2025-04-15 08:00 | 2025-04-21 17:00 | 37
CHI05-05-01-L3-1850 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 | Interior - L3 ADP - COLO5 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00 | 37
CHI05-05-02-MG-1440 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 2 - MG | 2024-10-14 08:00 | 2024-10-18 17:00 | 58
CHI05-05-02-MG-1450 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 2 - MG | 2024-10-16 08:00 | 2024-10-22 17:00 | 58
CHI05-05-02-MG-1460 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 | Overhead MEP Installation - COLO5 Cell 2 - MG | 2024-10-30 08:00 | 2024-11-12 17:00 | 53
CHI05-05-02-MG-1470 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 | Deliver AHU into Mech. Gallery - COLO5 Cell 2 - MG | 2024-11-21 08:00 | 2024-11-22 17:00 | 47
CHI05-05-02-MG-1480 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 | Install Walls and Primer Paint - COLO5 Cell 2 - MG | 2024-12-06 08:00 | 2024-12-19 17:00 | 39
CHI02-05-02-MG-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 | Placing the AHU - COLO5 Cell 2 - MG | 2024-12-30 08:00 | 2025-01-02 12:00 | 80
CHI02-05-02-MG-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 | Layout Ceiling and install Pencile Rod - COLO5 Cell 2 - MG | 2024-12-20 08:00 | 2024-12-20 17:00 | 84
CHI02-05-02-MG-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 | Piping and Electrical Termination to AHUs - COLO5 Cell 2 - MG | 2025-01-07 08:00 | 2025-01-20 17:00 | 77
CHI05-05-02-MG-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 | Pipe Testing - COLO5 Cell 2 - MG | 2025-01-21 08:00 | 2025-01-22 17:00 | 81
CHI05-05-02-MG-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 | Install ceiling and Light Fittings - COLO5 Cell 2 - MG | 2025-01-23 08:00 | 2025-02-03 17:00 | 81
CHI05-05-02-MG-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 | Trim out MEP - COLO5 Cell 2 - MG | 2025-01-28 08:00 | 2025-02-03 17:00 | 87
CHI05-05-02-MG-1485 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 | Post Wall Overhead MEP - COLO5 Cell 2 - MG | 2024-12-20 08:00 | 2025-01-13 17:00 | 80
CHI05-05-02-ER-1440 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 | Install Walls and Primer Paint - COLO5 Cell 2 - ER | 2024-10-16 08:00 | 2024-10-29 17:00 | 61
CHI05-05-02-ER-1450 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 2 - ER | 2024-11-06 08:00 | 2024-11-19 17:00 | 58
CHI02-05-02-ER-1460 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 | Install Upper Screens - COLO5 Cell 2 - ER | 2024-10-25 08:00 | 2024-10-31 17:00 | 61
CHI05-05-02-ER-1470 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 | Install Ceiling - COLO5 Cell 2 - ER | 2024-11-20 08:00 | 2024-11-22 17:00 | 58
CHI05-05-02-ER-1480 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 | Below Ceiling MEP Rough In - COLO5 Cell 2 - ER | 2024-11-25 08:00 | 2024-12-09 17:00 | 58
CHI05-05-02-ER-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 | Installation of ADP & ATS - COLO5 Cell 2 - ER | 2024-12-06 08:00 | 2024-12-12 17:00 | 87
CHI05-05-02-ER-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 | Installation of UPS Equipment - COLO5 Cell 2 - ER | 2024-12-10 08:00 | 2024-12-16 17:00 | 68
CHI05-05-02-ER-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 | Connet to Cable tray and conduit equipment - COLO5 Cell 2 - ER | 2024-12-17 08:00 | 2024-12-23 17:00 | 104
CHI05-05-02-ER-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 | Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER | 2025-01-09 08:00 | 2025-01-29 17:00 | 94
CHI05-05-02-ER-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 | Door Frame Installation - COLO5 Cell 2 - ER | 2025-01-03 08:00 | 2025-01-09 17:00 | 67
CHI05-05-02-ER-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 | Finishes and Signage - COLO5 Cell 2 - ER | 2025-01-27 08:00 | 2025-01-31 17:00 | 104
CHI05-05-02-ER-1495 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 | Installation of MSB - COLO5 Cell 2 - ER | 2024-12-13 08:00 | 2024-12-19 17:00 | 81
CHI05-05-02-DH-1430 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 | Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH | 2025-01-24 08:00 | 2025-02-13 17:00 | 39
CHI05-05-02-DH-1440 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 2 - DH | 2024-10-30 08:00 | 2024-11-14 17:00 | 66
CHI05-05-02-DH-1450 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 | HAC install and Rise - COLO5 Cell 2 - DH | 2025-01-24 08:00 | 2025-01-30 17:00 | 64
CHI05-05-02-DH-1460 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 | Termination at PDU & Busway- COLO5 Cell 2 - DH | 2025-02-14 08:00 | 2025-02-27 17:00 | 85
CHI05-05-02-DH-1470 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 | Security Screen Installation - COLO5 Cell 2 - DH | 2024-12-20 08:00 | 2024-12-24 17:00 | 39
CHI05-05-02-DH-1480 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 | Ceiling Grid and Tile - COLO5 Cell 2 - DH | 2024-12-26 08:00 | 2025-01-02 17:00 | 39
CHI05-05-02-DH-1490 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 | Install PDU's - COLO5 Cell 2 - DH | 2025-01-17 08:00 | 2025-01-23 17:00 | 39
CHI05-05-02-DH-1500 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 2 - DH | 2025-01-03 08:00 | 2025-01-16 17:00 | 39
CHI05-05-02-DH-1510 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH | 2025-01-31 08:00 | 2025-02-13 17:00 | 64
CHI05-05-02-DH-1520 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 | HAC Placing - COLO5 Cell 2 - DH | 2025-01-17 08:00 | 2025-01-23 17:00 | 64
CHI05-05-02-DH-1530 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 | Finishes and Signage - COLO5 Cell 2 - DH | 2025-02-28 08:00 | 2025-03-06 17:00 | 85
CHI05-05-02-L1-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 | Interior - L1 UPS - COLO5 Cell 2 | 2024-12-17 08:00 | 2024-12-17 17:00 | 93
CHI05-05-02-L1-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 | Interior - L1 MSB - COLO5 Cell 2 | 2024-12-20 08:00 | 2024-12-20 17:00 | 101
CHI05-05-02-L1-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 | Interior - L1 PDUs - COLO5 Cell 2 | 2025-01-24 08:00 | 2025-01-24 17:00 | 83
CHI05-05-02-L1-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 | Interior - L1 AHUs - COLO5 Cell 2 | 2025-01-28 08:00 | 2025-01-28 17:00 | 91
CHI05-05-02-L1-1660 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 | Interior - L1 ATSs - COLO5 Cell 2 | 2024-12-24 08:00 | 2024-12-24 17:00 | 109
CHI05-05-02-L1-1670 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 | Interior - L1 Busway - COLO5 Cell 2 | 2025-01-27 08:00 | 2025-01-27 17:00 | 87
CHI05-05-02-L1-1730 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 | Interior - L1 ADP - COLO5 Cell 2 | 2024-12-23 08:00 | 2024-12-23 17:00 | 105
CHI05-05-02-L2-1740 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 | Interior - L2 UPS - COLO5 Cell 2 | 2025-02-25 08:00 | 2025-03-03 17:00 | 52
CHI05-05-02-L2-1750 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 | Interior - L2 MSB - COLO5 Cell 2 | 2025-03-04 08:00 | 2025-03-10 17:00 | 52
CHI05-05-02-L2-1760 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 | Interior - L2 PDUs - COLO5 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00 | 52
CHI05-05-02-L2-1770 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 | Interior - L2 AHUs - COLO5 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00 | 52
CHI05-05-02-L2-1780 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 | Interior - L2 ATSs - COLO5 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00 | 52
CHI05-05-02-L2-1790 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 | Interior - L2 Busway - COLO5 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00 | 52
CHI05-05-02-L2-1850 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 | Interior - L2 ADP - COLO5 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00 | 52
CHI05-05-02-L3-1860 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 | Interior - L3 UPS - COLO5 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00 | 37
CHI05-05-02-L3-1870 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 | Interior - L3 MSB - COLO5 Cell 2 | 2025-04-01 08:00 | 2025-04-07 17:00 | 37
CHI05-05-02-L3-1880 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 | Interior - L3 PDUs - COLO5 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00 | 37
CHI05-05-02-L3-1890 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 | Interior - L3 AHUs - COLO5 Cell 2 | 2025-04-22 08:00 | 2025-04-28 17:00 | 37
CHI05-05-02-L3-1900 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 | Interior - L3 ATSs - COLO5 Cell 2 | 2025-04-15 08:00 | 2025-04-21 17:00 | 37
CHI05-05-02-L3-1910 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 | Interior - L3 Busway - COLO5 Cell 2 | 2025-04-15 08:00 | 2025-04-21 17:00 | 37
CHI05-05-02-L3-1970 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 | Interior - L3 ADP - COLO5 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00 | 37
CHI05-05-03-MG-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 3 - MG | 2024-10-21 08:00 | 2024-10-25 17:00 | 68
CHI05-05-03-MG-1560 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 3 - MG | 2024-10-23 08:00 | 2024-10-29 17:00 | 68
CHI05-05-03-MG-1570 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 | Overhead MEP Installation - COLO5 Cell 3 - MG | 2024-11-13 08:00 | 2024-11-26 17:00 | 58
CHI05-05-03-MG-1580 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 | Deliver AHU into Mech. Gallery - COLO5 Cell 3 - MG | 2024-11-27 08:00 | 2024-11-29 17:00 | 58
CHI05-05-03-MG-1590 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 | Install Walls and Primer Paint - COLO5 Cell 3 - MG | 2024-12-20 08:00 | 2025-01-06 17:00 | 44
CHI05-05-03-MG-1600 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 | Placing the AHU - COLO5 Cell 3 - MG | 2025-01-14 08:00 | 2025-01-16 12:00 | 77
CHI05-05-03-MG-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 | Layout Ceiling and install Pencile Rod - COLO5 Cell 3 - MG | 2025-01-07 08:00 | 2025-01-07 17:00 | 81
CHI05-05-03-MG-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 | Piping and Electrical Termination to AHUs - COLO5 Cell 3 - MG | 2025-01-21 08:00 | 2025-02-03 17:00 | 77
CHI05-05-03-MG-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 | Pipe Testing - COLO5 Cell 3 - MG | 2025-02-04 08:00 | 2025-02-05 17:00 | 79
CHI05-05-03-MG-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 | Install ceiling and Light Fittings - COLO5 Cell 3 - MG | 2025-02-06 08:00 | 2025-02-17 17:00 | 79
CHI05-05-03-MG-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 | Trim out MEP - COLO5 Cell 3 - MG | 2025-02-11 08:00 | 2025-02-17 17:00 | 82
CHI05-05-03-MG-1595 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 | Post Wall Overhead MEP - COLO5 Cell 3 - MG | 2025-01-07 08:00 | 2025-01-27 17:00 | 77
CHI05-05-03-ER-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 | Install Walls and Primer Paint - COLO5 Cell 3 - ER | 2024-10-30 08:00 | 2024-11-12 17:00 | 61
CHI05-05-03-ER-1560 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 3 - ER | 2024-11-20 08:00 | 2024-12-04 17:00 | 58
CHI05-05-03-ER-1570 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 | Install Upper Screens - COLO5 Cell 3 - ER | 2024-11-08 08:00 | 2024-11-14 17:00 | 61
CHI05-05-03-ER-1580 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 | Install Ceiling - COLO5 Cell 3 - ER | 2024-12-05 08:00 | 2024-12-09 17:00 | 58
CHI05-05-03-ER-1590 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 | Below Ceiling MEP Rough In - COLO5 Cell 3 - ER | 2024-12-10 08:00 | 2024-12-23 17:00 | 58
CHI05-05-03-ER-1600 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 | Installation of ADP & ATS - COLO5 Cell 3 - ER | 2024-12-13 08:00 | 2024-12-19 17:00 | 87
CHI05-05-03-ER-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 | Installation of UPS Equipment - COLO5 Cell 3 - ER | 2024-12-24 08:00 | 2024-12-31 17:00 | 63
CHI05-05-03-ER-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 | Connet to Cable tray and conduit equipment - COLO5 Cell 3 - ER | 2024-12-24 08:00 | 2024-12-31 17:00 | 114
CHI05-05-03-ER-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 | Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER | 2025-01-30 08:00 | 2025-02-19 17:00 | 94
CHI05-05-03-ER-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 | Door Frame Installation - COLO5 Cell 3 - ER | 2025-01-03 08:00 | 2025-01-09 17:00 | 67
CHI05-05-03-ER-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 | Finishes and Signage - COLO5 Cell 3 - ER | 2025-03-07 08:00 | 2025-03-13 17:00 | 85
CHI05-05-03-ER-1605 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 | Installation of MSB - COLO5 Cell 3 - ER | 2024-12-20 08:00 | 2024-12-27 17:00 | 81
CHI05-05-03-DH-1540 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 | Termination at PDU & Busway - COLO5 Cell 3 - DH | 2025-02-14 08:00 | 2025-03-06 17:00 | 39
CHI05-05-03-DH-1550 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 3 - DH | 2024-11-15 08:00 | 2024-12-03 17:00 | 69
CHI05-05-03-DH-1560 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 | HAC install and Rise - COLO5 Cell 3 - DH | 2025-02-07 08:00 | 2025-02-13 17:00 | 64
CHI05-05-03-DH-1570 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 | Cable Pulling at PDU & Busway- COLO5 Cell 3 - DH | 2025-02-07 08:00 | 2025-02-20 17:00 | 49
CHI05-05-03-DH-1580 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 | Security Screen Installation - COLO5 Cell 3 - DH | 2025-01-07 08:00 | 2025-01-09 17:00 | 44
CHI05-05-03-DH-1590 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 | Ceiling Grid and Tile - COLO5 Cell 3 - DH | 2025-01-10 08:00 | 2025-01-16 17:00 | 44
CHI05-05-03-DH-1600 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 | Install PDU's - COLO5 Cell 3 - DH | 2025-01-31 08:00 | 2025-02-06 17:00 | 44
CHI05-05-03-DH-1610 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 3 - DH | 2025-01-17 08:00 | 2025-01-30 17:00 | 44
CHI05-05-03-DH-1620 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 3 - DH | 2025-02-14 08:00 | 2025-02-27 17:00 | 64
CHI05-05-03-DH-1630 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 | HAC Placing - COLO5 Cell 3 - DH | 2025-01-31 08:00 | 2025-02-06 17:00 | 64
CHI05-05-03-DH-1640 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 | Finishes and Signage - COLO5 Cell 3 - DH | 2025-03-14 08:00 | 2025-03-20 17:00 | 85
CHI05-05-03-L1-1740 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 | Interior - L1 UPS - COLO5 Cell 3 | 2025-01-02 08:00 | 2025-01-02 17:00 | 83
CHI05-05-03-L1-1750 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 | Interior - L1 MSB - COLO5 Cell 3 | 2025-01-03 08:00 | 2025-01-03 17:00 | 93
CHI05-05-03-L1-1760 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 | Interior - L1 PDUs - COLO5 Cell 3 | 2025-02-07 08:00 | 2025-02-07 17:00 | 73
CHI05-05-03-L1-1770 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 | Interior - L1 AHUs - COLO5 Cell 3 | 2025-02-11 08:00 | 2025-02-11 17:00 | 81
CHI05-05-03-L1-1780 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 | Interior - L1 ATSs - COLO5 Cell 3 | 2025-01-07 08:00 | 2025-01-07 17:00 | 101
CHI05-05-03-L1-1790 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 | Interior - L1 Busway - COLO5 Cell 3 | 2025-02-10 08:00 | 2025-02-10 17:00 | 77
CHI05-05-03-L1-1850 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 | Interior - L1 ADP - COLO5 Cell 3 | 2025-01-06 08:00 | 2025-01-06 17:00 | 97
CHI05-05-03-L2-1860 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 | Interior - L2 UPS - COLO5 Cell 3 | 2025-02-25 08:00 | 2025-03-03 17:00 | 52
CHI05-05-03-L2-1870 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 | Interior - L2 MSB - COLO5 Cell 3 | 2025-03-04 08:00 | 2025-03-10 17:00 | 52
CHI05-05-03-L2-1880 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 | Interior - L2 PDUs - COLO5 Cell 3 | 2025-03-11 08:00 | 2025-03-17 17:00 | 52
CHI05-05-03-L2-1890 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 | Interior - L2 AHUs - COLO5 Cell 3 | 2025-03-25 08:00 | 2025-03-31 17:00 | 52
CHI05-05-03-L2-1900 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 | Interior - L2 ATSs - COLO5 Cell 3 | 2025-03-18 08:00 | 2025-03-24 17:00 | 52
CHI05-05-03-L2-1910 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 | Interior - L2 Busway - COLO5 Cell 3 | 2025-03-18 08:00 | 2025-03-24 17:00 | 52
CHI05-05-03-L2-1970 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 | Interior - L2 ADP - COLO5 Cell 3 | 2025-03-11 08:00 | 2025-03-17 17:00 | 52
CHI05-05-03-L3-1980 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 | Interior - L3 UPS - COLO5 Cell 3 | 2025-03-25 08:00 | 2025-03-31 17:00 | 37
CHI05-05-03-L3-1990 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 | Interior - L3 MSB - COLO5 Cell 3 | 2025-04-01 08:00 | 2025-04-07 17:00 | 37
CHI05-05-03-L3-2000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 | Interior - L3 PDUs - COLO5 Cell 3 | 2025-04-08 08:00 | 2025-04-14 17:00 | 37
CHI05-05-03-L3-2010 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 | Interior - L3 AHUs - COLO5 Cell 3 | 2025-04-22 08:00 | 2025-04-28 17:00 | 37
CHI05-05-03-L3-2020 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 | Interior - L3 ATSs - COLO5 Cell 3 | 2025-04-15 08:00 | 2025-04-21 17:00 | 37
CHI05-05-03-L3-2030 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 | Interior - L3 Busway - COLO5 Cell 3 | 2025-04-15 08:00 | 2025-04-21 17:00 | 37
CHI05-05-03-L3-2090 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 | Interior - L3 ADP - COLO5 Cell 3 | 2025-04-08 08:00 | 2025-04-14 17:00 | 37
CHI05-05-04-MG-1660 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 4 - MG | 2024-10-28 08:00 | 2024-11-01 17:00 | 73
CHI05-05-04-MG-1670 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 4 - MG | 2024-10-30 08:00 | 2024-11-05 17:00 | 78
CHI05-05-04-MG-1680 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 | Overhead MEP Installation - COLO5 Cell 4 - MG | 2024-11-27 08:00 | 2024-12-11 17:00 | 63
CHI05-05-04-MG-1690 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 | Deliver AHU into Mech. Gallery - COLO5 Cell 4 - MG | 2024-12-12 08:00 | 2024-12-13 17:00 | 63
CHI05-05-04-MG-1700 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 | Install Walls and Primer Paint - COLO5 Cell 4 - MG | 2025-01-07 08:00 | 2025-01-20 17:00 | 49
CHI05-05-04-MG-1710 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 | Placing the AHU - COLO5 Cell 4 - MG | 2025-01-28 08:00 | 2025-01-30 12:00 | 69
CHI05-05-04-MG-1720 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 | Layout Ceiling and install Pencile Rod - COLO5 Cell 4 - MG | 2025-01-21 08:00 | 2025-01-21 17:00 | 73
CHI05-05-04-MG-1730 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 | Piping and Electrical Termination to AHUs - COLO5 Cell 4 - MG | 2025-02-04 08:00 | 2025-02-17 17:00 | 77
CHI05-05-04-MG-1740 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 | Pipe Testing - COLO5 Cell 4 - MG | 2025-02-18 08:00 | 2025-02-19 17:00 | 77
CHI05-05-04-MG-1750 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 | Install ceiling and Light Fittings - COLO5 Cell 4 - MG | 2025-02-20 08:00 | 2025-03-03 17:00 | 77
CHI05-05-04-MG-1760 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 | Trim out MEP - COLO5 Cell 4 - MG | 2025-02-25 08:00 | 2025-03-03 17:00 | 77
CHI05-05-04-MG-1705 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 | Post Wall Overhead MEP - COLO5 Cell 4 - MG | 2025-01-21 08:00 | 2025-02-10 17:00 | 69
CHI05-05-04-ER-1660 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 | Install Walls and Primer Paint - COLO5 Cell 4 - ER | 2024-11-13 08:00 | 2024-11-26 17:00 | 61
CHI05-05-04-ER-1670 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 4 - ER | 2024-12-05 08:00 | 2024-12-18 17:00 | 58
CHI05-05-04-ER-1680 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 | Install Upper Screens - COLO5 Cell 4 - ER | 2024-11-22 08:00 | 2024-11-29 17:00 | 61
CHI05-05-04-ER-1690 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 | Install Ceiling - COLO5 Cell 4 - ER | 2024-12-19 08:00 | 2024-12-23 17:00 | 58
CHI05-05-04-ER-1700 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 | Below Ceiling MEP Rough In - COLO5 Cell 4 - ER | 2024-12-24 08:00 | 2025-01-08 17:00 | 58
CHI05-05-04-ER-1710 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 | Installation of ADP & ATS - COLO5 Cell 4 - ER | 2024-12-27 08:00 | 2025-01-03 17:00 | 83
CHI05-05-04-ER-1720 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 | Installation of UPS Equipment - COLO5 Cell 4 - ER | 2025-01-09 08:00 | 2025-01-15 17:00 | 58
CHI05-05-04-ER-1730 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 | Connet to Cable tray and conduit equipment - COLO5 Cell 4 - ER | 2025-01-02 08:00 | 2025-01-08 17:00 | 124
CHI05-05-04-ER-1740 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 | Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER | 2025-02-20 08:00 | 2025-03-12 17:00 | 94
CHI05-05-04-ER-1750 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 | Door Frame Installation - COLO5 Cell 4 - ER | 2025-01-16 08:00 | 2025-01-22 17:00 | 58
CHI05-05-04-ER-1760 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 | Finishes and Signage - COLO5 Cell 4 - ER | 2025-03-21 08:00 | 2025-03-27 17:00 | 85
CHI05-05-04-ER-1715 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 | Installation of MSB - COLO5 Cell 4 - ER | 2024-12-30 08:00 | 2025-01-06 17:00 | 81
CHI05-05-04-DH-1745 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 | Closing Construction Access Door - COLO5 Cell 4 - DH | 2025-02-21 08:00 | 2025-03-13 17:00 | 69
CHI05-05-04-DH-1650 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 | Termination at PDU & Busway - COLO5 Cell 4 - DH | 2025-03-07 08:00 | 2025-03-27 17:00 | 39
CHI05-05-04-DH-1660 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 4 - DH | 2024-12-04 08:00 | 2024-12-19 17:00 | 72
CHI05-05-04-DH-1670 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 | HAC install and Rise - COLO5 Cell 4 - DH | 2025-02-21 08:00 | 2025-02-27 17:00 | 64
CHI05-05-04-DH-1680 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 | Cable Pulling at PDU & Busway- COLO5 Cell 4 - DH | 2025-02-21 08:00 | 2025-03-06 17:00 | 54
CHI05-05-04-DH-1690 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 | Security Screen Installation - COLO5 Cell 4 - DH | 2025-01-21 08:00 | 2025-01-23 17:00 | 49
CHI05-05-04-DH-1700 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 | Ceiling Grid and Tile - COLO5 Cell 4 - DH | 2025-01-24 08:00 | 2025-01-30 17:00 | 49
CHI05-05-04-DH-1710 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 | Install PDU's - COLO5 Cell 4 - DH | 2025-02-14 08:00 | 2025-02-20 17:00 | 49
CHI05-05-04-DH-1720 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 4 - DH | 2025-01-31 08:00 | 2025-02-13 17:00 | 49
CHI05-05-04-DH-1730 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH | 2025-02-28 08:00 | 2025-03-13 17:00 | 64
CHI05-05-04-DH-1740 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 | HAC Placing - COLO5 Cell 4 - DH | 2025-02-14 08:00 | 2025-02-20 17:00 | 64
CHI05-05-04-DH-1750 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 | Finishes and Signage - COLO5 Cell 4 - DH | 2025-03-28 08:00 | 2025-04-03 17:00 | 85
CHI05-05-04-L1-1860 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 | Interior - L1 UPS - COLO5 Cell 4 | 2025-01-02 08:00 | 2025-01-02 17:00 | 83
CHI05-05-04-L1-1870 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 | Interior - L1 MSB - COLO5 Cell 4 | 2025-01-07 08:00 | 2025-01-07 17:00 | 81
CHI05-05-04-L1-1880 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 | Interior - L1 PDUs - COLO5 Cell 4 | 2025-02-21 08:00 | 2025-02-21 17:00 | 49
CHI05-05-04-L1-1890 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 | Interior - L1 AHUs - COLO5 Cell 4 | 2025-02-25 08:00 | 2025-02-25 17:00 | 49
CHI05-05-04-L1-1900 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 | Interior - L1 ATSs - COLO5 Cell 4 | 2025-01-09 08:00 | 2025-01-09 17:00 | 81
CHI05-05-04-L1-1910 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 | Interior - L1 Busway - COLO5 Cell 4 | 2025-02-24 08:00 | 2025-02-24 17:00 | 49
CHI05-05-04-L1-1970 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 | Interior - L1 ADP - COLO5 Cell 4 | 2025-01-08 08:00 | 2025-01-08 17:00 | 81
CHI05-05-04-L2-1980 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 | Interior - L2 UPS - COLO5 Cell 4 | 2025-02-26 08:00 | 2025-03-04 17:00 | 49
CHI05-05-04-L2-1990 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 | Interior - L2 MSB - COLO5 Cell 4 | 2025-03-05 08:00 | 2025-03-11 17:00 | 49
CHI05-05-04-L2-2000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 | Interior - L2 PDUs - COLO5 Cell 4 | 2025-03-28 08:00 | 2025-04-03 17:00 | 39
CHI05-05-04-L2-2010 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 | Interior - L2 AHUs - COLO5 Cell 4 | 2025-04-11 08:00 | 2025-04-17 17:00 | 39
CHI05-05-04-L2-2020 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 | Interior - L2 ATSs - COLO5 Cell 4 | 2025-03-19 08:00 | 2025-03-25 17:00 | 49
CHI05-05-04-L2-2030 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 | Interior - L2 Busway - COLO5 Cell 4 | 2025-04-04 08:00 | 2025-04-10 17:00 | 39
CHI05-05-04-L2-2090 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 | Interior - L2 ADP - COLO5 Cell 4 | 2025-03-12 08:00 | 2025-03-18 17:00 | 49
CHI05-05-04-L3-2100 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 | Interior - L3 UPS - COLO5 Cell 4 | 2025-03-25 08:00 | 2025-03-31 17:00 | 35
CHI05-05-04-L3-2110 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 | Interior - L3 MSB - COLO5 Cell 4 | 2025-04-01 08:00 | 2025-04-07 17:00 | 35
CHI05-05-04-L3-2120 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 | Interior - L3 PDUs - COLO5 Cell 4 | 2025-04-08 08:00 | 2025-04-14 17:00 | 40
CHI05-05-04-L3-2130 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 | Interior - L3 AHUs - COLO5 Cell 4 | 2025-04-24 08:00 | 2025-04-30 17:00 | 35
CHI05-05-04-L3-2140 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 | Interior - L3 ATSs - COLO5 Cell 4 | 2025-04-15 08:00 | 2025-04-21 17:00 | 35
CHI05-05-04-L3-2150 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 | Interior - L3 Busway - COLO5 Cell 4 | 2025-04-22 08:00 | 2025-04-28 17:00 | 35
CHI05-05-04-L3-2210 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 | Interior - L3 ADP - COLO5 Cell 4 | 2025-04-08 08:00 | 2025-04-14 17:00 | 35
CHI05-05-04-L4-1000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 | COLO5 Cx LEV4 - COLO5 | 2025-05-01 08:00 | 2025-06-04 17:00 | 35
CHI05-05-04-L5-1000 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,3,5,2 | COLO5 Cx LEV5 / IST - COLO5 | 2025-06-05 08:00 | 2025-06-06 17:00 | 35
CHI05-02-01-L1-1220 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 UPM - COLO2 | 2024-11-22 08:00 | 2024-11-27 17:00 | 75
CHI05-02-01-L1-1230 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 XFMR - MV- COLO2 | 2024-10-31 08:00 | 2024-11-05 17:00 | 96
CHI05-02-01-L1-1240 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 GEN - COLO2 | 2024-11-25 08:00 | 2024-11-29 17:00 | 83
CHI05-03-01-L1-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 UPM - COLO3 | 2024-11-22 08:00 | 2024-11-27 17:00 | 68
CHI05-03-01-L1-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 XFMR - MV- COLO3 | 2024-11-07 08:00 | 2024-11-12 17:00 | 84
CHI05-03-01-L1-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 GEN - COLO3 | 2024-11-05 08:00 | 2024-11-08 17:00 | 86
CHI05-04-01-L1-1460 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 UPM - COLO4 | 2024-11-22 08:00 | 2024-11-27 17:00 | 74
CHI05-04-01-L1-1470 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 XFMR - MV- COLO4 | 2024-11-14 08:00 | 2024-11-19 17:00 | 85
CHI05-04-01-L1-1480 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 GEN - COLO4 | 2024-11-12 08:00 | 2024-11-15 17:00 | 87
CHI05-05-01-L1-1580 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 UPM - COLO5 | 2024-11-22 08:00 | 2024-11-27 17:00 | 75
CHI05-05-01-L1-1590 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 XFMR - MV- COLO5 | 2024-11-21 08:00 | 2024-11-26 17:00 | 81
CHI05-05-01-L1-1600 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 GEN - COLO5 | 2024-11-19 08:00 | 2024-11-22 17:00 | 83
CHI05-02-01-L1-1200 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 UTS / UTSR - Site | 2025-01-21 08:00 | 2025-01-21 17:00 | 42
CHI05-02-01-L1-1210 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 UMS 04 - COLO 3 | 2024-11-14 08:00 | 2024-11-14 17:00 | 73
CHI05-02-02-L1-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 UMS 03 - COLO 3 | 2024-11-14 08:00 | 2024-11-14 17:00 | 73
CHI05-02-03-L1-1450 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 UMS 01 - COLO 5 | 2024-11-21 08:00 | 2024-11-21 17:00 | 68
CHI05-02-04-L1-1570 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,1 | L1 URS 01 - COLO 5 | 2024-11-21 08:00 | 2024-11-21 17:00 | 68
CHI05-02-01-L2-1340 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 UPM - COLO2 | 2025-01-28 08:00 | 2025-02-24 17:00 | 35
CHI05-02-01-L2-1350 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 XFMR - COLO2 | 2025-01-28 08:00 | 2025-02-24 17:00 | 40
CHI05-02-01-L2-1360 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 GEN - COLO2 | 2025-01-28 08:00 | 2025-02-24 17:00 | 40
CHI05-03-01-L2-1460 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 UPM - COLO3 | 2025-01-28 08:00 | 2025-02-24 17:00 | 28
CHI05-03-01-L2-1470 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 XFMR - COLO3 | 2025-01-28 08:00 | 2025-02-24 17:00 | 33
CHI05-03-01-L2-1480 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 GEN - COLO3 | 2025-01-28 08:00 | 2025-02-24 17:00 | 33
CHI05-04-01-L2-1580 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 UPM - COLO4 | 2025-01-28 08:00 | 2025-02-24 17:00 | 34
CHI05-04-01-L2-1590 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 XFMR - COLO4 | 2025-01-28 08:00 | 2025-02-24 17:00 | 39
CHI05-04-01-L2-1600 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 GEN - COLO4 | 2025-01-28 08:00 | 2025-02-24 17:00 | 39
CHI05-05-01-L2-1700 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 UPM - COLO5 | 2025-01-28 08:00 | 2025-02-24 17:00 | 35
CHI05-05-01-L2-1710 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 XFMR - COLO5 | 2025-01-28 08:00 | 2025-02-24 17:00 | 40
CHI05-05-01-L2-1720 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 GEN - COLO5 | 2025-01-28 08:00 | 2025-02-24 17:00 | 40
CHI05-02-01-L2-1330 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 URS 01 - COLO 5 | 2025-02-11 08:00 | 2025-02-17 17:00 | 33
CHI05-02-02-L2-1450 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 UMS 03 - COLO 3 | 2025-02-18 08:00 | 2025-02-24 17:00 | 28
CHI05-02-03-L2-1570 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 UMS 04 - COLO 3 | 2025-02-18 08:00 | 2025-02-24 17:00 | 28
CHI05-02-04-L2-1690 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 UMS 01 - COLO 5 | 2025-02-18 08:00 | 2025-02-24 17:00 | 28
CHI05-05-01-L2-1680 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,2 | L2 UTS / UTSR - Site | 2025-02-11 08:00 | 2025-02-17 17:00 | 28
CHI05-02-01-L3-1460 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 UPM - COLO2 | 2025-02-25 08:00 | 2025-03-24 17:00 | 35
CHI05-02-01-L3-1470 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 XFMR - COLO2 | 2025-02-25 08:00 | 2025-03-24 17:00 | 40
CHI05-02-01-L3-1480 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 GEN - COLO2 | 2025-02-25 08:00 | 2025-03-24 17:00 | 40
CHI05-03-01-L3-1580 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 UPM - COLO3 | 2025-02-26 08:00 | 2025-03-25 17:00 | 27
CHI05-03-01-L3-1590 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 XFMR - COLO3 | 2025-02-26 08:00 | 2025-03-25 17:00 | 32
CHI05-03-01-L3-1600 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 GEN - COLO3 | 2025-02-26 08:00 | 2025-03-25 17:00 | 32
CHI05-04-01-L3-1700 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 UPM - COLO4 | 2025-04-14 08:00 | 2025-05-09 17:00 | 0
CHI05-04-01-L3-1710 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 XFMR - COLO4 | 2025-04-14 08:00 | 2025-05-09 17:00 | 5
CHI05-04-01-L3-1720 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 GEN - COLO4 | 2025-04-14 08:00 | 2025-05-09 17:00 | 5
CHI05-05-01-L3-1820 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 UPM - COLO5 | 2025-02-25 08:00 | 2025-03-24 17:00 | 35
CHI05-05-01-L3-1830 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 XFMR - COLO5 | 2025-02-25 08:00 | 2025-03-24 17:00 | 40
CHI05-05-01-L3-1840 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 GEN - COLO5 | 2025-02-25 08:00 | 2025-03-24 17:00 | 40
CHI05-02-01-L3-1440 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 UTS / UTSR - Site | 2025-03-03 08:00 | 2025-03-07 17:00 | 29
CHI05-02-01-L3-1450 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 UMS 04 - COLO 3 | 2025-03-17 08:00 | 2025-03-21 17:00 | 29
CHI05-02-02-L3-1570 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 UMS 03 - COLO 3 | 2025-03-17 08:00 | 2025-03-21 17:00 | 29
CHI05-02-03-L3-1690 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 URS 01 - COLO 5 | 2025-03-10 08:00 | 2025-03-14 17:00 | 29
CHI05-02-04-L3-1810 | Not Started | CHI05-PH2-FIT-BL-D5,3,3,6,3 | L3 UMS 01 - COLO 5 | 2025-03-10 08:00 | 2025-03-14 17:00 | 29
CHI05-CON-1020 | Not Started | CHI05-PH2-FIT-BL-D5,3,2 | (3) UTS - Install and Terminate (1 wk/ea) | 2025-01-21 08:00 | 2025-02-10 17:00 | 28
CHI05-CON-1050 | Not Started | CHI05-PH2-FIT-BL-D5,3,2 | Permanent Power Live |  | 2025-02-28 17:00 | 0
CHI05-CON-1030 | Not Started | CHI05-PH2-FIT-BL-D5,3,2 | Installation and Termiation of MV Cable | 2025-01-21 08:00 | 2025-02-24 17:00 | 28
CHI05-CFCI-1020 | Completed | CHI05-PH2-FIT-BL-D5,4,2,1 | HAC's - Submittal Preparation | 2024-06-03 08:00 | 2024-06-07 17:00
CHI05-CFCI-1080 | Completed | CHI05-PH2-FIT-BL-D5,4,2,1 | HAC's - Submittal Review | 2024-06-10 08:00 | 2024-06-10 17:00
CHI05-CFCI-1090 | In Progress | CHI05-PH2-FIT-BL-D5,4,2,1 | HAC's - Lead Time | 2024-06-11 08:00 | 2024-09-13 17:00 | 140
CHI05-CFCI-1140 | In Progress | CHI05-PH2-FIT-BL-D5,4,2,9 | Doors/Frames/Hardware - Submittal Preparation | 2024-06-19 08:00 | 2024-08-09 17:00 | 60
CHI05-CFCI-1160 | In Progress | CHI05-PH2-FIT-BL-D5,4,2,9 | Doors/Frames/Hardware - Submittal Review | 2024-06-28 08:00 | 2024-08-09 17:00 | 60
CHI05-CFCI-1220 | Not Started | CHI05-PH2-FIT-BL-D5,4,2,9 | Doors/Frames/Hardware - Lead Time | 2024-08-12 08:00 | 2025-01-02 17:00 | 60
CHI05-CFCI-1000 | Completed | CHI05-PH2-FIT-BL-D5,4,2,4 | DX Split Units - Submittal Preparation | 2024-05-21 08:00 | 2024-06-11 17:00
CHI05-CFCI-1120 | Completed | CHI05-PH2-FIT-BL-D5,4,2,4 | DX Split Units - Submittal Review | 2024-06-12 08:00 | 2024-06-28 17:00
CHI05-CFCI-1170 | In Progress | CHI05-PH2-FIT-BL-D5,4,2,4 | DX Split Units - Lead Time | 2024-07-01 08:00 | 2024-10-21 17:00 | 57
CHI05-CFCI-1030 | Completed | CHI05-PH2-FIT-BL-D5,4,2,6 | AHU (Admin) - Submittal Preparation | 2024-06-03 08:00 | 2024-06-21 17:00
CHI05-CFCI-1150 | Completed | CHI05-PH2-FIT-BL-D5,4,2,6 | AHU (Admin) - Submittal Review | 2024-06-24 08:00 | 2024-07-08 17:00
CHI05-CFCI-1200 | In Progress | CHI05-PH2-FIT-BL-D5,4,2,6 | AHU (Admin) - Lead Time | 2024-07-09 08:00 | 2024-11-18 17:00 | 39
CHI05-CFCI-1050 | Completed | CHI05-PH2-FIT-BL-D5,4,2,8 | Overhead Cable Bus - Submittal Preparation | 2024-06-06 08:00 | 2024-06-06 17:00
CHI05-CFCI-1070 | Completed | CHI05-PH2-FIT-BL-D5,4,2,8 | Overhead Cable Bus - Submittal Review | 2024-06-07 08:00 | 2024-06-10 17:00
CHI05-CFCI-1100 | In Progress | CHI05-PH2-FIT-BL-D5,4,2,8 | Overhead Cable Bus - Lead Time | 2024-06-11 08:00 | 2024-11-18 17:00 | 40
CHI05-CFCI-1180 | Completed | CHI05-PH2-FIT-BL-D5,4,2,3 | Medium Voltage Cabling - Submittal Preparation | 2024-07-03 08:00 | 2024-07-09 17:00
CHI05-CFCI-1190 | In Progress | CHI05-PH2-FIT-BL-D5,4,2,3 | Medium Voltage Cabling - Submittal Review | 2024-07-04 08:00 | 2024-08-09 17:00 | 33
CHI05-CFCI-1210 | In Progress | CHI05-PH2-FIT-BL-D5,4,2,3 | Medium Voltage Cabling - Lead Time | 2024-07-10 08:00 | 2024-12-27 17:00 | 33
CHI05-CFCI-1040 | Completed | CHI05-PH2-FIT-BL-D5,4,2,5 | Elec. Distribution System - Submittal Preparation | 2024-06-03 08:00 | 2024-06-07 17:00
CHI05-CFCI-1110 | Completed | CHI05-PH2-FIT-BL-D5,4,2,5 | Elec. Distribution System - Submittal Review | 2024-06-11 08:00 | 2024-06-11 17:00
CHI05-CFCI-1130 | In Progress | CHI05-PH2-FIT-BL-D5,4,2,5 | Elec. Distribution System - Lead Time | 2024-06-12 08:00 | 2024-09-26 17:00 | 186
CHI05-CFCI-1010 | In Progress | CHI05-PH2-FIT-BL-D5,4,2,7 | Light Fixture - Submittal Preparation | 2024-05-27 08:00 | 2024-08-09 17:00 | 130
CHI05-CFCI-1060 | In Progress | CHI05-PH2-FIT-BL-D5,4,2,7 | Light Fixture - Submittal Review | 2024-06-06 08:00 | 2024-08-09 17:00 | 130
CHI05-CFCI-1230 | Not Started | CHI05-PH2-FIT-BL-D5,4,2,7 | Light Fixture - Lead Time | 2024-08-12 08:00 | 2024-12-03 17:00 | 130
CHI05-CFCI-1240 | Not Started | CHI05-PH2-FIT-BL-D5,4,2,2 | Damper Assembly and Delivery | 2024-10-02 08:00 | 2024-10-04 17:00 | 0
CHI05-OFCI-1000 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,1,1 | AHU - COLO 2 - In Storage | 2024-10-02 08:00 | 2024-10-08 17:00 | 49
CHI05-OFCI-1450 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,1,2 | AHU - COLO 3 - In Storage | 2024-10-09 08:00 | 2024-10-15 17:00 | 49
CHI05-OFCI-1460 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,1,3 | AHU - COLO 4 - Start ROJ | 2024-10-09 08:00 |  | 55
CHI05-OFCI-1470 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,1,3 | AHU - COLO 4 - ROJ | 2024-10-09 08:00 | 2024-10-15 17:00 | 55
CHI05-OFCI-1480 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,1,3 | AHU - COLO 4 - Finish ROJ |  | 2024-10-15 17:00 | 55
CHI05-OFCI-1010 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,1,5 | AHU - COLO 5 - Start ROJ | 2024-10-02 08:00 |  | 63
CHI05-OFCI-1020 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,1,5 | AHU - COLO 5 - ROJ | 2024-10-02 08:00 | 2024-10-15 17:00 | 63
CHI05-OFCI-1490 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,1,5 | AHU - COLO 5 - Finish ROJ |  | 2024-10-15 17:00 | 63
CHI05-OFCI-1860 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,2,1 | ATS - COLO 2 - Start ROJ | 2024-11-14 08:00 |  | 0
CHI05-OFCI-1870 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,2,1 | ATS - COLO 2 - ROJ | 2024-11-14 08:00 | 2024-11-27 17:00 | 94
CHI05-OFCI-1970 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,2,1 | ATS - COLO 2 - Finish ROJ |  | 2024-11-27 17:00 | 94
CHI05-OFCI-2140 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,2,2 | ATS - COLO 3 - Start ROJ | 2024-12-16 08:00 |  | 78
CHI05-OFCI-2150 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,2,2 | ATS - COLO 3 - ROJ | 2024-12-16 08:00 | 2024-12-31 17:00 | 78
CHI05-OFCI-2270 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,2,2 | ATS - COLO 3 - Finish ROJ |  | 2024-12-31 17:00 | 78
CHI05-OFCI-1590 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,2,3 | ATS - COLO 4 - Start ROJ | 2024-10-28 08:00 |  | 64
CHI05-OFCI-1600 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,2,3 | ATS - COLO 4 - ROJ | 2024-10-28 08:00 | 2024-11-27 17:00 | 64
CHI05-OFCI-1980 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,2,3 | ATS - COLO 4 - Finish ROJ |  | 2024-11-27 17:00 | 64
CHI05-OFCI-1030 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,2,5 | ATS - COLO 5 - Start ROJ | 2024-10-02 08:00 |  | 118
CHI05-OFCI-1040 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,2,5 | ATS - COLO 5 - ROJ | 2024-10-02 08:00 | 2024-10-15 17:00 | 118
CHI05-OFCI-1500 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,2,5 | ATS - COLO 5 - Finish ROJ |  | 2024-10-15 17:00 | 118
CHI05-OFCI-1050 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,6,1 | BAS - COLO 2 - Start ROJ | 2024-10-02 08:00 |  | 27
CHI05-OFCI-1060 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,6,1 | BAS - COLO 2 - ROJ | 2024-10-02 08:00 | 2024-10-29 17:00 | 27
CHI05-OFCI-1650 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,6,1 | BAS - COLO 2 - Finish ROJ |  | 2024-10-29 17:00 | 27
CHI05-OFCI-1680 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,6,2 | BAS - COLO 3 - Start ROJ | 2024-10-30 08:00 |  | 27
CHI05-OFCI-1690 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,6,2 | BAS - COLO 3 - ROJ | 2024-10-30 08:00 | 2024-12-30 17:00 | 27
CHI05-OFCI-2230 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,6,2 | BAS - COLO 3 - Finish ROJ |  | 2024-12-30 17:00 | 27
CHI05-OFCI-1700 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,6,3 | BAS - COLO 4 - Start ROJ | 2024-10-30 08:00 |  | 38
CHI05-OFCI-1710 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,6,3 | BAS - COLO 4 - ROJ | 2024-10-30 08:00 | 2024-12-30 17:00 | 38
CHI05-OFCI-2240 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,6,3 | BAS - COLO 4 - Finish ROJ |  | 2024-12-30 17:00 | 38
CHI05-OFCI-1070 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,6,5 | BAS - COLO 5 - Start ROJ | 2024-10-02 08:00 |  | 76
CHI05-OFCI-1080 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,6,5 | BAS - COLO 5 - ROJ | 2024-10-02 08:00 | 2024-10-29 17:00 | 76
CHI05-OFCI-1660 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,6,5 | BAS - COLO 5 - Finish ROJ |  | 2024-10-29 17:00 | 76
CHI05-OFCI-1090 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,3,1 | Busway/Bus Plugs - COLO 2 - In Storage | 2024-10-02 08:00 | 2024-10-16 17:00 | 31
CHI05-OFCI-2020 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,3,2 | Busway/Bus Plugs - COLO 3 - Start ROJ | 2024-12-02 08:00 |  | 0
CHI05-OFCI-2030 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,3,2 | Busway/Bus Plugs - COLO 3 - ROJ | 2024-12-02 08:00 | 2024-12-30 17:00 | 85
CHI05-OFCI-2250 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,3,2 | Busway/Bus Plugs - COLO 3 - Finish ROJ |  | 2024-12-30 17:00 | 85
CHI05-OFCI-2040 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,3,3 | Busway/Bus Plugs - COLO 4 - Start ROJ | 2024-12-02 08:00 |  | 87
CHI05-OFCI-2050 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,3,3 | Busway/Bus Plugs - COLO 4 - ROJ | 2024-12-02 08:00 | 2024-12-30 17:00 | 87
CHI05-OFCI-2260 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,3,3 | Busway/Bus Plugs - COLO 4 - Finish ROJ |  | 2024-12-30 17:00 | 87
CHI05-OFCI-1100 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,3,5 | Busway/Bus Plugs - COLO 5 - Start ROJ | 2024-10-02 08:00 |  | 122
CHI05-OFCI-1110 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,3,5 | Busway/Bus Plugs - COLO 5 - ROJ | 2024-10-02 08:00 | 2024-10-29 17:00 | 122
CHI05-OFCI-1670 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,3,5 | Busway/Bus Plugs - COLO 5 - Finish ROJ |  | 2024-10-29 17:00 | 122
CHI05-OFCI-1120 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,4,1 | EPMS - COLO 2 | 2024-10-02 08:00 | 2024-10-02 17:00 | 103
CHI05-OFCI-1440 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,4,2 | EPMS - COLO 3 | 2024-10-03 08:00 | 2024-10-16 17:00 | 103
CHI05-OFCI-1570 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,4,3 | EPMS - COLO 4 | 2024-10-17 08:00 | 2024-10-31 17:00 | 103
CHI05-OFCI-1730 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,4,5 | EPMS - COLO 5 | 2024-11-01 08:00 | 2024-11-15 17:00 | 103
CHI05-OFCI-1130 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,5,1 | GENS - COLO 2 - In Storage | 2024-09-20 08:00 | 2024-09-30 17:00 | 0
CHI05-OFCI-1140 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,5,2 | GENS - COLO 3 - In Storage | 2024-09-20 08:00 | 2024-10-02 17:00 | 67
CHI05-OFCI-1150 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,5,3 | GENS - COLO 4 - In Storage | 2024-09-20 08:00 | 2024-10-04 17:00 | 67
CHI05-OFCI-1160 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,5,5 | GENS - COLO 5 - In Storage | 2024-09-20 08:00 | 2024-10-08 17:00 | 67
CHI05-OFCI-1840 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,7,1 | LVS - COLO 2 - Start ROJ | 2024-11-13 08:00 |  | 0
CHI05-OFCI-1850 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,7,1 | LVS - COLO 2 - ROJ | 2024-11-13 08:00 | 2024-11-27 17:00 | 0
CHI05-OFCI-1990 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,7,1 | LVS - COLO 2 - Finish ROJ |  | 2024-11-27 17:00 | 94
CHI05-OFCI-1930 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,7,2 | LVS - COLO 3 - Start ROJ | 2024-11-21 08:00 |  | 87
CHI05-OFCI-1940 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,7,2 | LVS - COLO 3 - ROJ | 2024-11-21 08:00 | 2024-12-05 17:00 | 95
CHI05-OFCI-2100 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,7,2 | LVS - COLO 3 - Finish ROJ |  | 2024-12-05 17:00 | 95
CHI05-OFCI-2180 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,7,3 | LVS - COLO 4 - Start ROJ | 2024-12-23 08:00 |  | 0
CHI05-OFCI-2190 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,7,3 | LVS - COLO 4 - ROJ | 2024-12-23 08:00 | 2025-01-06 17:00 | 60
CHI05-OFCI-2280 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,7,3 | LVS - COLO 4 - Finish ROJ |  | 2025-01-06 17:00 | 60
CHI05-OFCI-1950 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,7,5 | LVS - COLO 5 - Start ROJ | 2024-11-21 08:00 |  | 87
CHI05-OFCI-1960 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,7,5 | LVS - COLO 5 - ROJ | 2024-11-21 08:00 | 2024-12-05 17:00 | 87
CHI05-OFCI-2110 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,7,5 | LVS - COLO 5 - Finish ROJ |  | 2024-12-05 17:00 | 87
CHI05-OFCI-1170 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,8,1 | MVS (UPM) - COLO 2 - Start ROJ | 2024-10-02 08:00 |  | 173
CHI05-OFCI-1180 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,8,1 | MVS (UPM) - COLO 2 - ROJ | 2024-10-02 08:00 | 2024-10-15 17:00 | 173
CHI05-OFCI-1530 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,8,1 | MVS (UPM) - COLO 2 - Finish ROJ |  | 2024-10-15 17:00 | 173
CHI05-OFCI-1190 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,8,2 | MVS (UPM) - COLO 3 - Start ROJ | 2024-10-02 08:00 |  | 173
CHI05-OFCI-1200 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,8,2 | MVS (UPM) - COLO 3 - ROJ | 2024-10-02 08:00 | 2024-10-15 17:00 | 173
CHI05-OFCI-1510 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,8,2 | MVS (UPM) - COLO 3 - Finish ROJ |  | 2024-10-15 17:00 | 173
CHI05-OFCI-1210 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,8,3 | MVS (UPM) - COLO 4 - Start ROJ | 2024-10-02 08:00 |  | 178
CHI05-OFCI-1220 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,8,3 | MVS (UPM) - COLO 4 - ROJ | 2024-10-02 08:00 | 2024-10-15 17:00 | 178
CHI05-OFCI-1520 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,8,3 | MVS (UPM) - COLO 4 - Finish ROJ |  | 2024-10-15 17:00 | 178
CHI05-OFCI-1230 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,8,5 | MVS (UPM) - COLO 5 - Start ROJ | 2024-10-02 08:00 |  | 89
CHI05-OFCI-1240 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,8,5 | MVS (UPM) - COLO 5 - ROJ | 2024-10-02 08:00 | 2024-10-15 17:00 | 89
CHI05-OFCI-1540 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,8,5 | MVS (UPM) - COLO 5 - Finish ROJ |  | 2024-10-15 17:00 | 89
CHI05-OFCI-1250 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,9,1 | MVS (XFMR) - COLO 2 - In storage | 2024-10-02 08:00 | 2024-10-02 17:00 | 63
CHI05-OFCI-1260 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,9,2 | MVS (XFMR) - COLO 3 - In storage | 2024-10-02 08:00 | 2024-10-02 17:00 | 68
CHI05-OFCI-1270 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,9,3 | MVS (XFMR) - COLO 4 - In storage | 2024-10-02 08:00 | 2024-10-02 17:00 | 73
CHI05-OFCI-1280 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,9,5 | MVS (XFMR) - COLO 5 - Start ROJ | 2024-09-23 08:00 |  | 0
CHI05-OFCI-1290 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,9,5 | MVS (XFMR) - COLO 5 - ROJ | 2024-09-23 08:00 | 2024-09-23 17:00 | 65
CHI05-OFCI-1550 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,9,5 | MVS (XFMR) - COLO 5 - Finish ROJ |  | 2024-09-23 17:00 | 65
CHI05-OFCI-1300 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,10,1 | UMS & URS - COLO 2 - In storage, needs modifications | 2024-10-02 08:00 | 2024-10-02 17:00 | 63
CHI05-OFCI-1580 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,10,2 | UMS & URS - COLO 3 - In storage, needs modifications | 2024-10-02 08:00 | 2024-10-02 17:00 | 68
CHI05-OFCI-1720 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,10,3 | UMS & URS - COLO 4 - In storage, needs modifications | 2024-10-02 08:00 | 2024-10-02 17:00 | 73
CHI05-OFCI-1880 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,10,5 | UMS & URS - COLO 5 - In storage, needs modifications | 2024-09-23 08:00 | 2024-09-23 17:00 | 0
CHI05-OFCI-1610 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,11,1 | PDU - COLO 2 - Start ROJ | 2024-10-28 08:00 |  | 0
CHI05-OFCI-1620 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,11,1 | PDU - COLO 2 - ROJ | 2024-10-28 08:00 | 2024-11-11 17:00 | 13
CHI05-OFCI-1820 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,11,1 | PDU - COLO 2 - Finish ROJ |  | 2024-11-11 17:00 | 13
CHI05-OFCI-2060 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,11,2 | PDU - COLO 3 - Start ROJ | 2024-12-02 08:00 |  | 0
CHI05-OFCI-2070 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,11,2 | PDU - COLO 3 - ROJ | 2024-12-02 08:00 | 2024-12-16 17:00 | 36
CHI05-OFCI-2160 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,11,2 | PDU - COLO 3 - Finish ROJ |  | 2024-12-16 17:00 | 36
CHI05-OFCI-2080 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,11,3 | PDU - COLO 4 - Start ROJ | 2024-12-02 08:00 |  | 42
CHI05-OFCI-2090 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,11,3 | PDU - COLO 4 - ROJ | 2024-12-02 08:00 | 2024-12-16 17:00 | 42
CHI05-OFCI-2170 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,11,3 | PDU - COLO 4 - Finish ROJ |  | 2024-12-16 17:00 | 42
CHI05-OFCI-1630 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,11,5 | PDU - COLO 5 - Start ROJ | 2024-10-28 08:00 |  | 69
CHI05-OFCI-1640 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,11,5 | PDU - COLO 5 - ROJ | 2024-10-28 08:00 | 2024-11-11 17:00 | 69
CHI05-OFCI-1830 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,11,5 | PDU - COLO 5 - Finish ROJ |  | 2024-11-11 17:00 | 69
CHI05-OFCI-1310 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,12,1 | UPS - COLO 2 - In storage | 2024-10-02 08:00 | 2024-10-15 17:00 | 89
CHI05-OFCI-1320 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,12,2 | UPS - COLO 3 - In storage | 2024-10-02 08:00 | 2024-10-15 17:00 | 99
CHI05-OFCI-1330 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,12,3 | UPS - COLO 4 - In storage | 2024-10-02 08:00 | 2024-10-15 17:00 | 100
CHI05-OFCI-1340 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,12,5 | UPS - COLO 5 - Start ROJ | 2024-10-02 08:00 |  | 101
CHI05-OFCI-1350 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,12,5 | UPS - COLO 5 - ROJ | 2024-10-02 08:00 | 2024-10-15 17:00 | 101
CHI05-OFCI-1560 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,12,5 | UPS - COLO 5 - Finish ROJ |  | 2024-10-15 17:00 | 101
CHI05-OFCI-2000 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,13,1 | UTS - Site - Start ROJ | 2024-11-29 08:00 |  | 0
CHI05-OFCI-2010 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,13,1 | UTS - Site - ROJ | 2024-11-29 08:00 | 2025-01-20 17:00 | 28
CHI05-OFCI-2130 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,13,1 | UTS - Site - Finish ROJ |  | 2025-01-20 17:00 | 28
CHI05-OFCI-1360 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,14,1 | MVS (UPM) Terminators/Lighting Arrestors - COLO 2 - Start ROJ | 2024-10-02 08:00 |  | 130
CHI05-OFCI-1370 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,14,1 | MVS (UPM) Terminators/Lighting Arrestors - COLO 2 - ROJ | 2024-10-02 08:00 | 2024-12-16 17:00 | 130
CHI05-OFCI-2120 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,14,1 | MVS (UPM) Terminators/Lighting Arrestors - COLO 2 - Finish ROJ |  | 2024-12-16 17:00 | 130
CHI05-OFCI-1380 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,14,2 | MVS (UPM) Terminators/Lighting Arrestors - COLO 3 - Start ROJ | 2024-10-02 08:00 |  | 130
CHI05-OFCI-1390 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,14,2 | MVS (UPM) Terminators/Lighting Arrestors - COLO 3 - ROJ | 2024-10-02 08:00 | 2024-12-16 17:00 | 130
CHI05-OFCI-2200 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,14,2 | MVS (UPM) Terminators/Lighting Arrestors - COLO 3 - Finish ROJ |  | 2024-12-16 17:00 | 130
CHI05-OFCI-1400 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,14,3 | MVS (UPM) Terminators/Lighting Arrestors - COLO 4 - Start ROJ | 2024-10-02 08:00 |  | 135
CHI05-OFCI-1410 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,14,3 | MVS (UPM) Terminators/Lighting Arrestors - COLO 4 - ROJ | 2024-10-02 08:00 | 2024-12-16 17:00 | 135
CHI05-OFCI-2210 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,14,3 | MVS (UPM) Terminators/Lighting Arrestors - COLO 4 - Finish ROJ |  | 2024-12-16 17:00 | 135
CHI05-OFCI-1420 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,14,5 | MVS (UPM) Terminators/Lighting Arrestors - COLO 5 - Start ROJ | 2024-10-02 08:00 |  | 130
CHI05-OFCI-1430 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,14,5 | MVS (UPM) Terminators/Lighting Arrestors - COLO 5 - ROJ | 2024-10-02 08:00 | 2024-12-16 17:00 | 130
CHI05-OFCI-2220 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,14,5 | MVS (UPM) Terminators/Lighting Arrestors - COLO 5 - Finish ROJ |  | 2024-12-16 17:00 | 130
CHI05-OFCI-1740 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,15,1 | Mufflers - COLO 2 - Start ROJ | 2024-10-02 08:00 |  | 47
CHI05-OFCI-1750 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,15,1 | Mufflers - COLO 2 - ROJ | 2024-10-02 08:00 | 2024-11-25 17:00 | 82
CHI05-OFCI-1890 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,15,1 | Mufflers - COLO 2 - Finish ROJ |  | 2024-11-25 17:00 | 82
CHI05-OFCI-1760 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,15,2 | Mufflers - COLO 3 - Start ROJ | 2024-10-02 08:00 |  | 47
CHI05-OFCI-1770 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,15,2 | Mufflers - COLO 3 - ROJ | 2024-10-02 08:00 | 2024-12-02 17:00 | 47
CHI05-OFCI-1900 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,15,2 | Mufflers - COLO 3 - Finish ROJ |  | 2024-12-02 17:00 | 47
CHI05-OFCI-1780 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,15,3 | Mufflers - COLO 4 - Start ROJ | 2024-12-03 08:00 |  | 47
CHI05-OFCI-1790 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,15,3 | Mufflers - COLO 4 - ROJ | 2024-12-03 08:00 | 2024-12-09 17:00 | 47
CHI05-OFCI-1910 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,15,3 | Mufflers - COLO 4 - Finish ROJ |  | 2024-12-09 17:00 | 47
CHI05-OFCI-1800 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,15,5 | Mufflers - COLO 5 - Start ROJ | 2024-10-02 08:00 |  | 51
CHI05-OFCI-1810 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,15,5 | Mufflers - COLO 5 - ROJ | 2024-10-02 08:00 | 2024-12-16 17:00 | 51
CHI05-OFCI-1920 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,15,5 | Mufflers - COLO 5 - Finish ROJ |  | 2024-12-16 17:00 | 51
A1000 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,16,1 | MSB - COLO 2 - ROJ | 2024-10-02 08:00 | 2024-11-27 17:00 | 60
A1010 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,16,2 | MSB - COLO 3 - ROJ | 2024-11-29 08:00 | 2024-12-05 17:00 | 60
A1020 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,16,3 | MSB - COLO 4 - ROJ | 2024-12-06 08:00 | 2025-01-06 17:00 | 60
A1040 | Not Started | CHI05-PH2-FIT-BL-D5,4,1,16,5 | MSB - COLO 5 - ROJ | 2024-11-29 08:00 | 2024-12-05 17:00 | 81

## TASKPRED
pred_task_id | task_id | pred_type | PREDTASK__status_code | TASK__status_code | pred_proj_id | proj_id | predtask__projwbs__wbs_full_name | task__projwbs__wbs_full_name | predtask__task_name | task__task_name | lag_hr_cnt | predtask__rsrc_id | task__rsrc_id | delete_record_flag
Predecessor | Successor | Relationship Type | (*)Predecessor Activity Status | (*)Successor Activity Status | (*)Predecessor Project | (*)Successor Project | (*)Predecessor WBS | (*)Successor WBS | (*)Predecessor Activity Name | (*)Successor Activity Name | Lag(d) | (*)Predecessor Primary Resource | (*)Successor Primary Resource | Delete This Row
CHI05-CFCI-1020 | CHI05-CFCI-1080 | SS | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | HAC's - Submittal Preparation | HAC's - Submittal Review | 0
CHI05-CFCI-1080 | CHI05-CFCI-1090 | FS | Completed | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | HAC's - Submittal Review | HAC's - Lead Time | 0
CHI05-CFCI-1140 | CHI05-CFCI-1160 | SS | In Progress | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | Doors/Frames/Hardware - Submittal Preparation | Doors/Frames/Hardware - Submittal Review | 0
CHI05-CFCI-1160 | CHI05-CFCI-1220 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | Doors/Frames/Hardware - Submittal Review | Doors/Frames/Hardware - Lead Time | 0
CHI05-CFCI-1000 | CHI05-CFCI-1120 | SS | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | DX Split Units - Submittal Preparation | DX Split Units - Submittal Review | 0
CHI05-CFCI-1120 | CHI05-CFCI-1170 | FS | Completed | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | DX Split Units - Submittal Review | DX Split Units - Lead Time | 0
CHI05-CFCI-1030 | CHI05-CFCI-1150 | SS | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | AHU (Admin) - Submittal Preparation | AHU (Admin) - Submittal Review | 0
CHI05-CFCI-1150 | CHI05-CFCI-1200 | FS | Completed | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | AHU (Admin) - Submittal Review | AHU (Admin) - Lead Time | 0
CHI05-CFCI-1050 | CHI05-CFCI-1070 | SS | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | Overhead Cable Bus - Submittal Preparation | Overhead Cable Bus - Submittal Review | 0
CHI05-CFCI-1070 | CHI05-CFCI-1100 | FS | Completed | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | Overhead Cable Bus - Submittal Review | Overhead Cable Bus - Lead Time | 0
CHI05-05-L5CX-F | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Complete L5/IST (White Tag) for Colo 5 | Site Secured Finish (August 04, 2025) | 0
CHI05-03-L5CX-F | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Complete L5/IST (White Tag) for Colo 3 | Site Secured Finish (August 04, 2025) | 0
CHI05-04-L5CX-F | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Complete L5/IST (White Tag) for Colo 4 | Site Secured Finish (August 04, 2025) | 0
CHI05-CFCI-1180 | CHI05-CFCI-1190 | SS | Completed | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | Medium Voltage Cabling - Submittal Preparation | Medium Voltage Cabling - Submittal Review | 0
CHI05-CFCI-1190 | CHI05-CFCI-1210 | SS | In Progress | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | Medium Voltage Cabling - Submittal Review | Medium Voltage Cabling - Lead Time | 0
CHI05-CFCI-1040 | CHI05-CFCI-1110 | SS | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,5 Elec. Distribution System | CHI05-PH2-FIT-BL-D5,4,2,5 Elec. Distribution System | Elec. Distribution System - Submittal Preparation | Elec. Distribution System - Submittal Review | 0
CHI05-CFCI-1110 | CHI05-CFCI-1130 | FS | Completed | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,5 Elec. Distribution System | CHI05-PH2-FIT-BL-D5,4,2,5 Elec. Distribution System | Elec. Distribution System - Submittal Review | Elec. Distribution System - Lead Time | 0
CHI05-CFCI-1010 | CHI05-CFCI-1060 | SS | In Progress | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | Light Fixture - Submittal Preparation | Light Fixture - Submittal Review | 0
CHI05-CFCI-1060 | CHI05-CFCI-1230 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | Light Fixture - Submittal Review | Light Fixture - Lead Time | 0
CHI05-CFCI-1090 | CHI05-03-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | HAC's - Lead Time | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-CFCI-1220 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Doors/Frames/Hardware - Lead Time | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-CFCI-1170 | CHI05-03-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | DX Split Units - Lead Time | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-CFCI-1200 | CHI05-03-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | AHU (Admin) - Lead Time | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-CFCI-1100 | CHI05-03-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Overhead Cable Bus - Lead Time | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-CFCI-1210 | CHI05-03-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Medium Voltage Cabling - Lead Time | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-CFCI-1130 | CHI05-03-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,5 Elec. Distribution System | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Elec. Distribution System - Lead Time | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-CFCI-1230 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Light Fixture - Lead Time | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-CFCI-1230 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Light Fixture - Lead Time | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-CFCI-1130 | CHI05-04-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,5 Elec. Distribution System | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Elec. Distribution System - Lead Time | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-CFCI-1210 | CHI05-04-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Medium Voltage Cabling - Lead Time | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-CFCI-1100 | CHI05-04-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Overhead Cable Bus - Lead Time | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-CFCI-1200 | CHI05-04-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | AHU (Admin) - Lead Time | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-CFCI-1170 | CHI05-04-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | DX Split Units - Lead Time | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-CFCI-1220 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Doors/Frames/Hardware - Lead Time | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-CFCI-1090 | CHI05-04-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | HAC's - Lead Time | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-CFCI-1090 | CHI05-05-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | HAC's - Lead Time | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-CFCI-1220 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Doors/Frames/Hardware - Lead Time | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-CFCI-1170 | CHI05-05-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | DX Split Units - Lead Time | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-CFCI-1200 | CHI05-05-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | AHU (Admin) - Lead Time | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-CFCI-1100 | CHI05-05-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Overhead Cable Bus - Lead Time | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-CFCI-1210 | CHI05-05-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Medium Voltage Cabling - Lead Time | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-CFCI-1130 | CHI05-05-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,5 Elec. Distribution System | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Elec. Distribution System - Lead Time | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-CFCI-1230 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Light Fixture - Lead Time | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-02-L5CX-F | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Complete L5/IST (White Tag) for Colo 2 | Site Secured Finish (August 04, 2025) | 0
CHI05-CFCI-1090 | CHI05-02-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | HAC's - Lead Time | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-CFCI-1220 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Doors/Frames/Hardware - Lead Time | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-CFCI-1170 | CHI05-02-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | DX Split Units - Lead Time | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-CFCI-1200 | CHI05-02-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | AHU (Admin) - Lead Time | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-CFCI-1100 | CHI05-02-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Overhead Cable Bus - Lead Time | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-CFCI-1210 | CHI05-02-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Medium Voltage Cabling - Lead Time | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-CFCI-1130 | CHI05-02-ROJ-F | FF | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,5 Elec. Distribution System | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Elec. Distribution System - Lead Time | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-CFCI-1230 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Light Fixture - Lead Time | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-CON-1050 | CHI05-03-POW-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Permanent Power Live | Power-ON Utility for Colo 3 | 0
CHI05-CON-1050 | CHI05-04-POW-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Permanent Power Live | Power-ON Utility for Colo 4 | 0
CHI05-CON-1050 | CHI05-05-POW-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Permanent Power Live | Power-ON Utility for Colo 5 | 0
CHI05-OFCI-1460 | CHI05-OFCI-1470 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,3 AHU - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,1,3 AHU - COLO 4 | AHU - COLO 4 - Start ROJ | AHU - COLO 4 - ROJ | 0
CHI05-OFCI-1470 | CHI05-OFCI-1480 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,3 AHU - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,1,3 AHU - COLO 4 | AHU - COLO 4 - ROJ | AHU - COLO 4 - Finish ROJ | 0
CHI05-OFCI-1010 | CHI05-OFCI-1020 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,5 AHU - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,1,5 AHU - COLO 5 | AHU - COLO 5 - Start ROJ | AHU - COLO 5 - ROJ | 0
CHI05-OFCI-1020 | CHI05-OFCI-1490 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,5 AHU - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,1,5 AHU - COLO 5 | AHU - COLO 5 - ROJ | AHU - COLO 5 - Finish ROJ | 0
CHI05-OFCI-1590 | CHI05-OFCI-1600 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,3 ATS - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,2,3 ATS - COLO 4 | ATS - COLO 4 - Start ROJ | ATS - COLO 4 - ROJ | 0
CHI05-OFCI-1600 | CHI05-OFCI-1980 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,3 ATS - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,2,3 ATS - COLO 4 | ATS - COLO 4 - ROJ | ATS - COLO 4 - Finish ROJ | 0
CHI05-OFCI-1030 | CHI05-OFCI-1040 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,5 ATS - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,2,5 ATS - COLO 5 | ATS - COLO 5 - Start ROJ | ATS - COLO 5 - ROJ | 0
CHI05-OFCI-1040 | CHI05-OFCI-1500 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,5 ATS - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,2,5 ATS - COLO 5 | ATS - COLO 5 - ROJ | ATS - COLO 5 - Finish ROJ | 0
CHI05-OFCI-1860 | CHI05-OFCI-1870 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,1 ATS - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,2,1 ATS - COLO 2 | ATS - COLO 2 - Start ROJ | ATS - COLO 2 - ROJ | 0
CHI05-OFCI-1870 | CHI05-OFCI-1970 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,1 ATS - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,2,1 ATS - COLO 2 | ATS - COLO 2 - ROJ | ATS - COLO 2 - Finish ROJ | 0
CHI05-OFCI-2140 | CHI05-OFCI-2150 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,2 ATS - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,2,2 ATS - COLO 3 | ATS - COLO 3 - Start ROJ | ATS - COLO 3 - ROJ | 0
CHI05-OFCI-2150 | CHI05-OFCI-2270 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,2 ATS - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,2,2 ATS - COLO 3 | ATS - COLO 3 - ROJ | ATS - COLO 3 - Finish ROJ | 0
CHI05-OFCI-1700 | CHI05-OFCI-1710 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,3 BAS - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,6,3 BAS - COLO 4 | BAS - COLO 4 - Start ROJ | BAS - COLO 4 - ROJ | 0
CHI05-OFCI-1710 | CHI05-OFCI-2240 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,3 BAS - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,6,3 BAS - COLO 4 | BAS - COLO 4 - ROJ | BAS - COLO 4 - Finish ROJ | 0
CHI05-OFCI-1070 | CHI05-OFCI-1080 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,5 BAS - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,6,5 BAS - COLO 5 | BAS - COLO 5 - Start ROJ | BAS - COLO 5 - ROJ | 0
CHI05-OFCI-1080 | CHI05-OFCI-1660 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,5 BAS - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,6,5 BAS - COLO 5 | BAS - COLO 5 - ROJ | BAS - COLO 5 - Finish ROJ | 0
CHI05-OFCI-1050 | CHI05-OFCI-1060 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,1 BAS - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,6,1 BAS - COLO 2 | BAS - COLO 2 - Start ROJ | BAS - COLO 2 - ROJ | 0
CHI05-OFCI-1060 | CHI05-OFCI-1650 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,1 BAS - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,6,1 BAS - COLO 2 | BAS - COLO 2 - ROJ | BAS - COLO 2 - Finish ROJ | 0
CHI05-OFCI-1680 | CHI05-OFCI-1690 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,2 BAS - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,6,2 BAS - COLO 3 | BAS - COLO 3 - Start ROJ | BAS - COLO 3 - ROJ | 0
CHI05-OFCI-1690 | CHI05-OFCI-2230 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,2 BAS - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,6,2 BAS - COLO 3 | BAS - COLO 3 - ROJ | BAS - COLO 3 - Finish ROJ | 0
CHI05-OFCI-2040 | CHI05-OFCI-2050 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,3 Busway/Bus Plugs - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,3,3 Busway/Bus Plugs - COLO 4 | Busway/Bus Plugs - COLO 4 - Start ROJ | Busway/Bus Plugs - COLO 4 - ROJ | 0
CHI05-OFCI-2050 | CHI05-OFCI-2260 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,3 Busway/Bus Plugs - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,3,3 Busway/Bus Plugs - COLO 4 | Busway/Bus Plugs - COLO 4 - ROJ | Busway/Bus Plugs - COLO 4 - Finish ROJ | 0
CHI05-OFCI-1100 | CHI05-OFCI-1110 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,5 Busway/Bus Plugs - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,3,5 Busway/Bus Plugs - COLO 5 | Busway/Bus Plugs - COLO 5 - Start ROJ | Busway/Bus Plugs - COLO 5 - ROJ | 0
CHI05-OFCI-1110 | CHI05-OFCI-1670 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,5 Busway/Bus Plugs - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,3,5 Busway/Bus Plugs - COLO 5 | Busway/Bus Plugs - COLO 5 - ROJ | Busway/Bus Plugs - COLO 5 - Finish ROJ | 0
CHI05-OFCI-2020 | CHI05-OFCI-2030 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,2 Busway/Bus Plugs - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,3,2 Busway/Bus Plugs - COLO 3 | Busway/Bus Plugs - COLO 3 - Start ROJ | Busway/Bus Plugs - COLO 3 - ROJ | 0
CHI05-OFCI-2030 | CHI05-OFCI-2250 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,2 Busway/Bus Plugs - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,3,2 Busway/Bus Plugs - COLO 3 | Busway/Bus Plugs - COLO 3 - ROJ | Busway/Bus Plugs - COLO 3 - Finish ROJ | 0
CHI05-OFCI-2180 | CHI05-OFCI-2190 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,3 LVS - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,7,3 LVS - COLO 4 | LVS - COLO 4 - Start ROJ | LVS - COLO 4 - ROJ | 0
CHI05-OFCI-2190 | CHI05-OFCI-2280 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,3 LVS - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,7,3 LVS - COLO 4 | LVS - COLO 4 - ROJ | LVS - COLO 4 - Finish ROJ | 0
CHI05-OFCI-1950 | CHI05-OFCI-1960 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,5 LVS - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,7,5 LVS - COLO 5 | LVS - COLO 5 - Start ROJ | LVS - COLO 5 - ROJ | 0
CHI05-OFCI-1960 | CHI05-OFCI-2110 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,5 LVS - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,7,5 LVS - COLO 5 | LVS - COLO 5 - ROJ | LVS - COLO 5 - Finish ROJ | 0
CHI05-OFCI-1840 | CHI05-OFCI-1850 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,1 LVS - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,7,1 LVS - COLO 2 | LVS - COLO 2 - Start ROJ | LVS - COLO 2 - ROJ | 0
CHI05-OFCI-1850 | CHI05-OFCI-1990 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,1 LVS - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,7,1 LVS - COLO 2 | LVS - COLO 2 - ROJ | LVS - COLO 2 - Finish ROJ | 0
CHI05-OFCI-1930 | CHI05-OFCI-1940 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,2 LVS - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,7,2 LVS - COLO 3 | LVS - COLO 3 - Start ROJ | LVS - COLO 3 - ROJ | 0
CHI05-OFCI-1940 | CHI05-OFCI-2100 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,2 LVS - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,7,2 LVS - COLO 3 | LVS - COLO 3 - ROJ | LVS - COLO 3 - Finish ROJ | 0
CHI05-OFCI-1210 | CHI05-OFCI-1220 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,3 MVS (UPM) - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,8,3 MVS (UPM) - COLO 4 | MVS (UPM) - COLO 4 - Start ROJ | MVS (UPM) - COLO 4 - ROJ | 0
CHI05-OFCI-1220 | CHI05-OFCI-1520 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,3 MVS (UPM) - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,8,3 MVS (UPM) - COLO 4 | MVS (UPM) - COLO 4 - ROJ | MVS (UPM) - COLO 4 - Finish ROJ | 0
CHI05-OFCI-1230 | CHI05-OFCI-1240 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,5 MVS (UPM) - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,8,5 MVS (UPM) - COLO 5 | MVS (UPM) - COLO 5 - Start ROJ | MVS (UPM) - COLO 5 - ROJ | 0
CHI05-OFCI-1240 | CHI05-OFCI-1540 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,5 MVS (UPM) - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,8,5 MVS (UPM) - COLO 5 | MVS (UPM) - COLO 5 - ROJ | MVS (UPM) - COLO 5 - Finish ROJ | 0
CHI05-OFCI-1170 | CHI05-OFCI-1180 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,1 MVS (UPM) - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,8,1 MVS (UPM) - COLO 2 | MVS (UPM) - COLO 2 - Start ROJ | MVS (UPM) - COLO 2 - ROJ | 0
CHI05-OFCI-1180 | CHI05-OFCI-1530 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,1 MVS (UPM) - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,8,1 MVS (UPM) - COLO 2 | MVS (UPM) - COLO 2 - ROJ | MVS (UPM) - COLO 2 - Finish ROJ | 0
CHI05-OFCI-1190 | CHI05-OFCI-1200 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,2 MVS (UPM) - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,8,2 MVS (UPM) - COLO 3 | MVS (UPM) - COLO 3 - Start ROJ | MVS (UPM) - COLO 3 - ROJ | 0
CHI05-OFCI-1200 | CHI05-OFCI-1510 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,2 MVS (UPM) - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,8,2 MVS (UPM) - COLO 3 | MVS (UPM) - COLO 3 - ROJ | MVS (UPM) - COLO 3 - Finish ROJ | 0
CHI05-OFCI-1280 | CHI05-OFCI-1290 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,5 MVS (XFMR) - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,9,5 MVS (XFMR) - COLO 5 | MVS (XFMR) - COLO 5 - Start ROJ | MVS (XFMR) - COLO 5 - ROJ | 0
CHI05-OFCI-1290 | CHI05-OFCI-1550 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,5 MVS (XFMR) - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,9,5 MVS (XFMR) - COLO 5 | MVS (XFMR) - COLO 5 - ROJ | MVS (XFMR) - COLO 5 - Finish ROJ | 0
CHI05-OFCI-2080 | CHI05-OFCI-2090 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,3 PDU - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,11,3 PDU - COLO 4 | PDU - COLO 4 - Start ROJ | PDU - COLO 4 - ROJ | 0
CHI05-OFCI-2090 | CHI05-OFCI-2170 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,3 PDU - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,11,3 PDU - COLO 4 | PDU - COLO 4 - ROJ | PDU - COLO 4 - Finish ROJ | 0
CHI05-OFCI-1630 | CHI05-OFCI-1640 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,5 PDU - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,11,5 PDU - COLO 5 | PDU - COLO 5 - Start ROJ | PDU - COLO 5 - ROJ | 0
CHI05-OFCI-1640 | CHI05-OFCI-1830 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,5 PDU - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,11,5 PDU - COLO 5 | PDU - COLO 5 - ROJ | PDU - COLO 5 - Finish ROJ | 0
CHI05-OFCI-1610 | CHI05-OFCI-1620 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,1 PDU - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,11,1 PDU - COLO 2 | PDU - COLO 2 - Start ROJ | PDU - COLO 2 - ROJ | 0
CHI05-OFCI-1620 | CHI05-OFCI-1820 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,1 PDU - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,11,1 PDU - COLO 2 | PDU - COLO 2 - ROJ | PDU - COLO 2 - Finish ROJ | 0
CHI05-OFCI-2070 | CHI05-OFCI-2160 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,2 PDU - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,11,2 PDU - COLO 3 | PDU - COLO 3 - ROJ | PDU - COLO 3 - Finish ROJ | 0
CHI05-OFCI-1340 | CHI05-OFCI-1350 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,5 UPS - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,12,5 UPS - COLO 5 | UPS - COLO 5 - Start ROJ | UPS - COLO 5 - ROJ | 0
CHI05-OFCI-1350 | CHI05-OFCI-1560 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,5 UPS - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,12,5 UPS - COLO 5 | UPS - COLO 5 - ROJ | UPS - COLO 5 - Finish ROJ | 0
CHI05-OFCI-2000 | CHI05-OFCI-2010 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,13,1 UTS - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,13,1 UTS - COLO 2 | UTS - Site - Start ROJ | UTS - Site - ROJ | 0
CHI05-OFCI-2010 | CHI05-OFCI-2130 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,13,1 UTS - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,13,1 UTS - COLO 2 | UTS - Site - ROJ | UTS - Site - Finish ROJ | 0
CHI05-CON-1020 | CHI05-CON-1030 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | (3) UTS - Install and Terminate (1 wk/ea) | Installation and Termiation of MV Cable | 0
CHI05-OFCI-1000 | CHI05-OFCI-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,1 AHU - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,1,2 AHU - COLO 3 | AHU - COLO 2 - In Storage | AHU - COLO 3 - In Storage | 0
CHI05-OFCI-1090 | CHI05-OFCI-2020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,1 Busway/Bus Plugs - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,3,2 Busway/Bus Plugs - COLO 3 | Busway/Bus Plugs - COLO 2 - In Storage | Busway/Bus Plugs - COLO 3 - Start ROJ | 0
CHI05-OFCI-1120 | CHI05-OFCI-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,4,1 EPMS - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,4,2 EPMS - COLO 3 | EPMS - COLO 2 | EPMS - COLO 3 | 0
CHI05-OFCI-1440 | CHI05-OFCI-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,4,2 EPMS - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,4,3 EPMS - COLO 4 | EPMS - COLO 3 | EPMS - COLO 4 | 0
CHI05-OFCI-1570 | CHI05-OFCI-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,4,3 EPMS - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,4,5 EPMS - COLO 5 | EPMS - COLO 4 | EPMS - COLO 5 | 0
CHI05-05-NTP-S | CHI05-OFCI-1000 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,1,1 AHU - COLO 2 | Notice To Proceed | AHU - COLO 2 - In Storage | 0
CHI05-OFCI-1000 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,1 AHU - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | AHU - COLO 2 - In Storage | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-OFCI-1450 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,2 AHU - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | AHU - COLO 3 - In Storage | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-OFCI-1480 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,3 AHU - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | AHU - COLO 4 - Finish ROJ | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-OFCI-1490 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,5 AHU - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | AHU - COLO 5 - Finish ROJ | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-05-NTP-S | CHI05-OFCI-1860 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,2,1 ATS - COLO 2 | Notice To Proceed | ATS - COLO 2 - Start ROJ | 0
CHI05-OFCI-1970 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,1 ATS - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | ATS - COLO 2 - Finish ROJ | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-05-NTP-S | CHI05-OFCI-2140 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,2,2 ATS - COLO 3 | Notice To Proceed | ATS - COLO 3 - Start ROJ | 0
CHI05-OFCI-2270 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,2 ATS - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | ATS - COLO 3 - Finish ROJ | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-05-NTP-S | CHI05-OFCI-1590 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,2,3 ATS - COLO 4 | Notice To Proceed | ATS - COLO 4 - Start ROJ | 0
CHI05-OFCI-1980 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,3 ATS - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | ATS - COLO 4 - Finish ROJ | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-05-NTP-S | CHI05-OFCI-1050 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,6,1 BAS - COLO 2 | Notice To Proceed | BAS - COLO 2 - Start ROJ | 0
CHI05-OFCI-1650 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,1 BAS - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | BAS - COLO 2 - Finish ROJ | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-05-NTP-S | CHI05-OFCI-1680 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,6,2 BAS - COLO 3 | Notice To Proceed | BAS - COLO 3 - Start ROJ | 0
CHI05-OFCI-2230 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,2 BAS - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | BAS - COLO 3 - Finish ROJ | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-05-NTP-S | CHI05-OFCI-1700 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,6,3 BAS - COLO 4 | Notice To Proceed | BAS - COLO 4 - Start ROJ | 0
CHI05-OFCI-2240 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,3 BAS - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | BAS - COLO 4 - Finish ROJ | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-05-NTP-S | CHI05-OFCI-1070 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,6,5 BAS - COLO 5 | Notice To Proceed | BAS - COLO 5 - Start ROJ | 0
CHI05-OFCI-1660 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,5 BAS - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | BAS - COLO 5 - Finish ROJ | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-05-NTP-S | CHI05-OFCI-1090 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,3,1 Busway/Bus Plugs - COLO 2 | Notice To Proceed | Busway/Bus Plugs - COLO 2 - In Storage | 0
CHI05-OFCI-1090 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,1 Busway/Bus Plugs - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Busway/Bus Plugs - COLO 2 - In Storage | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-OFCI-2250 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,2 Busway/Bus Plugs - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Busway/Bus Plugs - COLO 3 - Finish ROJ | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-05-NTP-S | CHI05-OFCI-2040 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,3,3 Busway/Bus Plugs - COLO 4 | Notice To Proceed | Busway/Bus Plugs - COLO 4 - Start ROJ | 0
CHI05-OFCI-2260 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,3 Busway/Bus Plugs - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Busway/Bus Plugs - COLO 4 - Finish ROJ | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-05-NTP-S | CHI05-OFCI-1100 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,3,5 Busway/Bus Plugs - COLO 5 | Notice To Proceed | Busway/Bus Plugs - COLO 5 - Start ROJ | 0
CHI05-OFCI-1670 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,5 Busway/Bus Plugs - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Busway/Bus Plugs - COLO 5 - Finish ROJ | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-05-NTP-S | CHI05-OFCI-1120 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,4,1 EPMS - COLO 2 | Notice To Proceed | EPMS - COLO 2 | 0
CHI05-05-NTP-S | CHI05-OFCI-1440 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,4,2 EPMS - COLO 3 | Notice To Proceed | EPMS - COLO 3 | 0
CHI05-05-NTP-S | CHI05-OFCI-1570 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,4,3 EPMS - COLO 4 | Notice To Proceed | EPMS - COLO 4 | 0
CHI05-05-NTP-S | CHI05-OFCI-1730 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,4,5 EPMS - COLO 5 | Notice To Proceed | EPMS - COLO 5 | 0
CHI05-OFCI-1120 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,4,1 EPMS - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | EPMS - COLO 2 | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-OFCI-1440 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,4,2 EPMS - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | EPMS - COLO 3 | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-OFCI-1570 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,4,3 EPMS - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | EPMS - COLO 4 | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-OFCI-1730 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,4,5 EPMS - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | EPMS - COLO 5 | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-OFCI-1130 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,1 GENS - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | GENS - COLO 2 - In Storage | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-OFCI-1140 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,2 GENS - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | GENS - COLO 3 - In Storage | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-OFCI-1150 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,3 GENS - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | GENS - COLO 4 - In Storage | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-OFCI-1160 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,5 GENS - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | GENS - COLO 5 - In Storage | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-05-NTP-S | CHI05-OFCI-1840 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,7,1 LVS - COLO 2 | Notice To Proceed | LVS - COLO 2 - Start ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-1930 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,7,2 LVS - COLO 3 | Notice To Proceed | LVS - COLO 3 - Start ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-2180 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,7,3 LVS - COLO 4 | Notice To Proceed | LVS - COLO 4 - Start ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-1950 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,7,5 LVS - COLO 5 | Notice To Proceed | LVS - COLO 5 - Start ROJ | 0
CHI05-OFCI-1990 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,1 LVS - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | LVS - COLO 2 - Finish ROJ | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-OFCI-2100 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,2 LVS - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | LVS - COLO 3 - Finish ROJ | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-OFCI-2280 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,3 LVS - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | LVS - COLO 4 - Finish ROJ | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-OFCI-2110 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,5 LVS - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | LVS - COLO 5 - Finish ROJ | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-05-NTP-S | CHI05-OFCI-1170 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,8,1 MVS (UPM) - COLO 2 | Notice To Proceed | MVS (UPM) - COLO 2 - Start ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-1190 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,8,2 MVS (UPM) - COLO 3 | Notice To Proceed | MVS (UPM) - COLO 3 - Start ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-1210 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,8,3 MVS (UPM) - COLO 4 | Notice To Proceed | MVS (UPM) - COLO 4 - Start ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-1230 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,8,5 MVS (UPM) - COLO 5 | Notice To Proceed | MVS (UPM) - COLO 5 - Start ROJ | 0
CHI05-OFCI-1530 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,1 MVS (UPM) - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | MVS (UPM) - COLO 2 - Finish ROJ | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-OFCI-1510 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,2 MVS (UPM) - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | MVS (UPM) - COLO 3 - Finish ROJ | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-OFCI-1520 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,3 MVS (UPM) - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | MVS (UPM) - COLO 4 - Finish ROJ | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-OFCI-1540 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,5 MVS (UPM) - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | MVS (UPM) - COLO 5 - Finish ROJ | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-05-NTP-S | CHI05-OFCI-1250 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,9,1 MVS (XFMR)- COLO 2 | Notice To Proceed | MVS (XFMR) - COLO 2 - In storage | 0
CHI05-05-NTP-S | CHI05-OFCI-1260 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,9,2 MVS (XFMR) - COLO 3 | Notice To Proceed | MVS (XFMR) - COLO 3 - In storage | 0
CHI05-05-NTP-S | CHI05-OFCI-1270 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,9,3 MVS (XFMR) - COLO 4 | Notice To Proceed | MVS (XFMR) - COLO 4 - In storage | 0
CHI05-OFCI-1250 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,1 MVS (XFMR)- COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | MVS (XFMR) - COLO 2 - In storage | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-OFCI-1260 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,2 MVS (XFMR) - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | MVS (XFMR) - COLO 3 - In storage | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-OFCI-1270 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,3 MVS (XFMR) - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | MVS (XFMR) - COLO 4 - In storage | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-OFCI-1550 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,5 MVS (XFMR) - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | MVS (XFMR) - COLO 5 - Finish ROJ | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-05-NTP-S | CHI05-OFCI-1300 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,10,1 UMS & URS- COLO 2 | Notice To Proceed | UMS & URS - COLO 2 - In storage, needs modifications | 0
CHI05-OFCI-1300 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,10,1 UMS & URS- COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | UMS & URS - COLO 2 - In storage, needs modifications | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-OFCI-1720 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,10,3 UMS & URS - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | UMS & URS - COLO 4 - In storage, needs modifications | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-OFCI-1880 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,10,5 UMS & URS - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | UMS & URS - COLO 5 - In storage, needs modifications | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-05-NTP-S | CHI05-OFCI-1610 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,11,1 PDU - COLO 2 | Notice To Proceed | PDU - COLO 2 - Start ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-2060 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,11,2 PDU - COLO 3 | Notice To Proceed | PDU - COLO 3 - Start ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-1630 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,11,5 PDU - COLO 5 | Notice To Proceed | PDU - COLO 5 - Start ROJ | 0
CHI05-OFCI-1820 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,1 PDU - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | PDU - COLO 2 - Finish ROJ | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-OFCI-2160 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,2 PDU - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | PDU - COLO 3 - Finish ROJ | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-OFCI-2170 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,3 PDU - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | PDU - COLO 4 - Finish ROJ | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-OFCI-1830 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,5 PDU - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | PDU - COLO 5 - Finish ROJ | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-05-NTP-S | CHI05-OFCI-1310 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,12,1 UPS - COLO 2 | Notice To Proceed | UPS - COLO 2 - In storage | 0
CHI05-05-NTP-S | CHI05-OFCI-1320 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,12,2 UPS - COLO 3 | Notice To Proceed | UPS - COLO 3 - In storage | 0
CHI05-05-NTP-S | CHI05-OFCI-1330 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,12,3 UPS - COLO 4 | Notice To Proceed | UPS - COLO 4 - In storage | 0
CHI05-OFCI-1310 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,1 UPS - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | UPS - COLO 2 - In storage | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-OFCI-1320 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,2 UPS - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | UPS - COLO 3 - In storage | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-OFCI-1330 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,3 UPS - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | UPS - COLO 4 - In storage | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-OFCI-1560 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,5 UPS - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | UPS - COLO 5 - Finish ROJ | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-05-NTP-S | CHI05-OFCI-1340 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,12,5 UPS - COLO 5 | Notice To Proceed | UPS - COLO 5 - Start ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-2000 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,13,1 UTS - COLO 2 | Notice To Proceed | UTS - Site - Start ROJ | 0
CHI05-OFCI-2130 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,13,1 UTS - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | UTS - Site - Finish ROJ | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-05-NTP-S | CHI05-OFCI-1030 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,2,5 ATS - COLO 5 | Notice To Proceed | ATS - COLO 5 - Start ROJ | 0
CHI05-OFCI-1500 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,5 ATS - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | ATS - COLO 5 - Finish ROJ | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-OFCI-1980 | CHI05-CON-1050 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,3 ATS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | ATS - COLO 4 - Finish ROJ | Permanent Power Live | 0
CHI05-OFCI-1600 | CHI05-CON-1050 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,3 ATS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | ATS - COLO 4 - ROJ | Permanent Power Live | 0
CHI05-CFCI-1020 | CHI05-CFCI-1080 | FF | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | HAC's - Submittal Preparation | HAC's - Submittal Review | 0
CHI05-CFCI-1140 | CHI05-CFCI-1160 | FF | In Progress | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | Doors/Frames/Hardware - Submittal Preparation | Doors/Frames/Hardware - Submittal Review | 0
CHI05-CFCI-1010 | CHI05-CFCI-1060 | FF | In Progress | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | Light Fixture - Submittal Preparation | Light Fixture - Submittal Review | 0
CHI05-CFCI-1040 | CHI05-CFCI-1110 | FF | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,5 Elec. Distribution System | CHI05-PH2-FIT-BL-D5,4,2,5 Elec. Distribution System | Elec. Distribution System - Submittal Preparation | Elec. Distribution System - Submittal Review | 0
CHI05-CFCI-1180 | CHI05-CFCI-1190 | FF | Completed | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | Medium Voltage Cabling - Submittal Preparation | Medium Voltage Cabling - Submittal Review | 0
CHI05-CFCI-1050 | CHI05-CFCI-1070 | FF | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | Overhead Cable Bus - Submittal Preparation | Overhead Cable Bus - Submittal Review | 0
CHI05-CFCI-1030 | CHI05-CFCI-1150 | FF | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | AHU (Admin) - Submittal Preparation | AHU (Admin) - Submittal Review | 0
CHI05-CFCI-1000 | CHI05-CFCI-1120 | FF | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | DX Split Units - Submittal Preparation | DX Split Units - Submittal Review | 0
CHI05-02-04-L4-1000 | CHI05-02-04-L5-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,5,1 Level 4 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,5,2 Level 5 Cx / IST - Colo 2 | COLO2 Cx LEV4 - COLO2 | COLO2 Cx LEV5 / IST - COLO2 | 0
CHI05-02-01-MG-1020 | CHI05-02-01-MG-1030 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Overhead MEP Installation - COLO2 Cell 1 - MG | Deliver AHU into Mech. Gallery - COLO2 Cell 1 - MG | 0
CHI05-02-01-MG-1030 | CHI05-02-01-MG-1040 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO2 Cell 1 - MG | Install Walls and Primer Paint - COLO2 Cell 1 - MG | 0
CHI05-02-01-MG-1040 | CHI05-02-01-MG-1050 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Install Walls and Primer Paint - COLO2 Cell 1 - MG | Layout Ceiling and install Pencile Rod - COLO2 Cell 1 - MG | 0
CHI05-02-01-MG-1050 | CHI05-02-01-MG-1060 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO2 Cell 1 - MG | Placing the AHU - COLO2 Cell 1 - MG | 0
CHI05-02-01-MG-1060 | CHI05-02-01-MG-1070 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Placing the AHU - COLO2 Cell 1 - MG | Piping and Electrical Termination to AHUs - COLO2 Cell 1 - MG | 0
CHI05-02-01-MG-1070 | CHI05-02-01-MG-1080 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO2 Cell 1 - MG | Pipe Testing - COLO2 Cell 1 - MG | 0
CHI05-02-01-MG-1080 | CHI05-02-01-MG-1090 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Pipe Testing - COLO2 Cell 1 - MG | Install ceiling and Light Fittings - COLO2 Cell 1 - MG | 0
CHI05-02-01-MG-1090 | CHI05-02-01-MG-1100 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Install ceiling and Light Fittings - COLO2 Cell 1 - MG | Trim out MEP - COLO2 Cell 1 - MG | 0
CHI05-02-01-MG-1010 | CHI05-02-01-MG-1020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 1 - MG | Overhead MEP Installation - COLO2 Cell 1 - MG | 0
CHI05-02-01-ER-1010 | CHI05-02-01-ER-1020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Install Upper Screens - COLO2 Cell 1 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 1 - ER | 0
CHI05-02-01-ER-1020 | CHI05-02-01-ER-1030 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 1 - ER | Install Ceiling - COLO2 Cell 1 - ER | 0
CHI05-02-01-ER-1030 | CHI05-02-01-ER-1040 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Install Ceiling - COLO2 Cell 1 - ER | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER | 0
CHI05-02-01-ER-1040 | CHI05-02-01-ER-1050 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER | Installation of ADP & ATS - COLO2 Cell 1 - ER | 2
CHI05-02-01-ER-1060 | CHI05-02-01-ER-1080 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO2 Cell 1 - ER | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | 0
CHI05-02-01-DH-1000 | CHI05-02-01-DH-1020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 1 - DH | Ceiling Grid and Tile - COLO2 Cell 1 - DH | 0
CHI05-02-01-DH-1020 | CHI05-02-01-DH-1030 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Ceiling Grid and Tile - COLO2 Cell 1 - DH | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 1 - DH | 0
CHI05-02-01-DH-1030 | CHI05-02-01-DH-1040 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 1 - DH | Install PDU's - COLO2 Cell 1 - DH | 0
CHI05-02-01-DH-1040 | CHI05-02-01-DH-1050 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Install PDU's - COLO2 Cell 1 - DH | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH | 0
CHI05-02-01-DH-1060 | CHI05-02-01-DH-1080 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | HAC install and Rise - COLO2 Cell 1 - DH | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 1 - DH | 0
CHI05-02-01-DH-1000 | CHI05-02-01-DH-1010 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 1 - DH | Security Screen Installation - COLO2 Cell 1 - DH | 6
CHI05-02-01-DH-1010 | CHI05-02-01-DH-1020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Security Screen Installation - COLO2 Cell 1 - DH | Ceiling Grid and Tile - COLO2 Cell 1 - DH | 0
CHI05-02-01-DH-1040 | CHI05-02-01-DH-1060 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Install PDU's - COLO2 Cell 1 - DH | HAC install and Rise - COLO2 Cell 1 - DH | 0
CHI05-02-01-ER-1010 | CHI05-02-01-DH-1010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Install Upper Screens - COLO2 Cell 1 - ER | Security Screen Installation - COLO2 Cell 1 - DH | 0
CHI05-02-01-MG-1000 | CHI05-02-01-MG-1010 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 1 - MG | 2
CHI05-02-01-MG-1000 | CHI05-02-01-MG-1010 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 1 - MG | 0
CHI05-02-01-ER-1000 | CHI05-02-01-ER-1010 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO2 Cell 1 - ER | Install Upper Screens - COLO2 Cell 1 - ER | 2
CHI05-02-01-ER-1050 | CHI05-02-01-ER-1060 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Installation of ADP & ATS - COLO2 Cell 1 - ER | Connet to Cable tray and conduit equipment - COLO2 Cell 1 - ER | 2
CHI05-02-01-DH-1035 | CHI05-02-01-DH-1060 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | HAC Placing - COLO2 Cell 1 - DH | HAC install and Rise - COLO2 Cell 1 - DH | 0
CHI05-02-01-DH-1030 | CHI05-02-01-DH-1035 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 1 - DH | HAC Placing - COLO2 Cell 1 - DH | 0
CHI05-02-01-DH-1050 | CHI05-02-01-DH-1090 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH | Finishes and Signage - COLO2 Cell 1 - DH | 0
CHI05-02-01-ER-1070 | CHI05-02-01-ER-1090 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Installation of UPS Equipment - COLO2 Cell 1 - ER | Door Frame Installation - COLO2 Cell 1 - ER | 0
CHI05-02-01-ER-1080 | CHI05-02-01-ER-1100 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | Finishes and Signage - COLO2 Cell 1 - ER | 2
CHI05-02-01-ER-1090 | CHI05-02-01-ER-1100 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Door Frame Installation - COLO2 Cell 1 - ER | Finishes and Signage - COLO2 Cell 1 - ER | 0
CHI05-02-01-L1-1210 | CHI05-02-01-L1-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 UMS 04 - COLO 3 | L1 UPM - COLO2 | 0
CHI05-02-01-L1-1230 | CHI05-02-01-L1-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | L1 XFMR - MV- COLO2 | Interior - L1 MSB - COLO2 Cell 1 | 0
CHI05-02-01-L1-1140 | CHI05-02-01-L1-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Interior - L1 UPS - COLO2 Cell 1 | Interior - L1 MSB - COLO2 Cell 1 | 0
CHI05-02-01-L1-1150 | CHI05-02-01-L1-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Interior - L1 MSB - COLO2 Cell 1 | Interior - L1 ADP - COLO2 Cell 1 | 0
CHI05-02-01-L1-1150 | CHI05-02-01-L1-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Interior - L1 MSB - COLO2 Cell 1 | Interior - L1 PDUs - COLO2 Cell 1 | 0
CHI05-02-01-L1-1250 | CHI05-02-01-L1-1180 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Interior - L1 ADP - COLO2 Cell 1 | Interior - L1 ATSs - COLO2 Cell 1 | 0
CHI05-02-01-L1-1180 | CHI05-02-01-L1-1170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Interior - L1 ATSs - COLO2 Cell 1 | Interior - L1 AHUs - COLO2 Cell 1 | 0
CHI05-02-01-L1-1160 | CHI05-02-01-L1-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Interior - L1 PDUs - COLO2 Cell 1 | Interior - L1 Busway - COLO2 Cell 1 | 0
CHI05-OFCI-1310 | CHI05-02-01-L1-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,1 UPS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | UPS - COLO 2 - In storage | Interior - L1 UPS - COLO2 Cell 1 | 0
CHI05-OFCI-1130 | CHI05-02-01-L1-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,1 GENS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | GENS - COLO 2 - In Storage | L1 GEN - COLO2 | 0
CHI05-02-01-L1-1240 | CHI05-02-01-L1-1150 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | L1 GEN - COLO2 | Interior - L1 MSB - COLO2 Cell 1 | 0
CHI05-02-01-L2-1330 | CHI05-02-01-L2-1340 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 URS 01 - COLO 5 | L2 UPM - COLO2 | 0
CHI05-02-01-L2-1340 | CHI05-02-01-L2-1350 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UPM - COLO2 | L2 XFMR - COLO2 | 0
CHI05-02-01-L2-1350 | CHI05-02-01-L2-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | L2 XFMR - COLO2 | Interior - L2 MSB - COLO2 Cell 1 | 0
CHI05-02-01-L2-1260 | CHI05-02-01-L2-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L2 UPS - COLO2 Cell 1 | Interior - L2 MSB - COLO2 Cell 1 | 0
CHI05-02-01-L2-1270 | CHI05-02-01-L2-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L2 MSB - COLO2 Cell 1 | Interior - L2 ADP - COLO2 Cell 1 | 0
CHI05-02-01-L2-1270 | CHI05-02-01-L2-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L2 MSB - COLO2 Cell 1 | Interior - L2 PDUs - COLO2 Cell 1 | 0
CHI05-02-01-L2-1370 | CHI05-02-01-L2-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L2 ADP - COLO2 Cell 1 | Interior - L2 ATSs - COLO2 Cell 1 | 0
CHI05-02-01-L2-1300 | CHI05-02-01-L2-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L2 ATSs - COLO2 Cell 1 | Interior - L2 AHUs - COLO2 Cell 1 | 0
CHI05-02-01-L2-1280 | CHI05-02-01-L2-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L2 PDUs - COLO2 Cell 1 | Interior - L2 Busway - COLO2 Cell 1 | 0
CHI05-02-01-L2-1360 | CHI05-02-01-L2-1270 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | L2 GEN - COLO2 | Interior - L2 MSB - COLO2 Cell 1 | 0
CHI05-02-01-L3-1440 | CHI05-02-01-L3-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UTS / UTSR - Site | L3 UMS 04 - COLO 3 | 0
CHI05-02-01-L3-1460 | CHI05-02-01-L3-1470 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UPM - COLO2 | L3 XFMR - COLO2 | 0
CHI05-02-01-L3-1470 | CHI05-02-01-L3-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | L3 XFMR - COLO2 | Interior - L3 MSB - COLO2 Cell 1 | 0
CHI05-02-01-L3-1380 | CHI05-02-01-L3-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L3 UPS - COLO2 Cell 1 | Interior - L3 MSB - COLO2 Cell 1 | 0
CHI05-02-01-L3-1390 | CHI05-02-01-L3-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L3 MSB - COLO2 Cell 1 | Interior - L3 ADP - COLO2 Cell 1 | 0
CHI05-02-01-L3-1390 | CHI05-02-01-L3-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L3 MSB - COLO2 Cell 1 | Interior - L3 PDUs - COLO2 Cell 1 | 0
CHI05-02-01-L3-1490 | CHI05-02-01-L3-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L3 ADP - COLO2 Cell 1 | Interior - L3 ATSs - COLO2 Cell 1 | 0
CHI05-02-01-L3-1400 | CHI05-02-01-L3-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L3 PDUs - COLO2 Cell 1 | Interior - L3 Busway - COLO2 Cell 1 | 0
CHI05-02-01-L3-1480 | CHI05-02-01-L3-1390 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | L3 GEN - COLO2 | Interior - L3 MSB - COLO2 Cell 1 | 0
CHI05-02-01-L1-1140 | CHI05-02-01-L2-1260 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L1 UPS - COLO2 Cell 1 | Interior - L2 UPS - COLO2 Cell 1 | 0
CHI05-02-01-L2-1260 | CHI05-02-01-L3-1380 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L2 UPS - COLO2 Cell 1 | Interior - L3 UPS - COLO2 Cell 1 | 0
CHI05-02-01-DH-1040 | CHI05-02-01-DH-1070 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Install PDU's - COLO2 Cell 1 - DH | Termination at PDU & Busway- COLO2 Cell 1 - DH | 0
CHI05-02-01-DH-1070 | CHI05-02-01-DH-1050 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Termination at PDU & Busway- COLO2 Cell 1 - DH | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH | 0
CHI05-02-01-MG-1060 | CHI05-02-01-L1-1170 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Placing the AHU - COLO2 Cell 1 - MG | Interior - L1 AHUs - COLO2 Cell 1 | 0
CHI05-02-01-L3-1410 | CHI05-02-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,5,1 Level 4 Cx - Colo 2 | Interior - L3 AHUs - COLO2 Cell 1 | COLO2 Cx LEV4 - COLO2 | 0
CHI05-02-02-MG-1130 | CHI05-02-02-MG-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Overhead MEP Installation - COLO2 Cell 2 - MG | Deliver AHU into Mech. Gallery - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1140 | CHI05-02-02-MG-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO2 Cell 2 - MG | Install Walls and Primer Paint - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1150 | CHI05-02-02-MG-1170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Install Walls and Primer Paint - COLO2 Cell 2 - MG | Layout Ceiling and install Pencile Rod - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1170 | CHI05-02-02-MG-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO2 Cell 2 - MG | Placing the AHU - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1160 | CHI05-02-02-MG-1180 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Placing the AHU - COLO2 Cell 2 - MG | Piping and Electrical Termination to AHUs - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1180 | CHI05-02-02-MG-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO2 Cell 2 - MG | Pipe Testing - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1190 | CHI05-02-02-MG-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Pipe Testing - COLO2 Cell 2 - MG | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1200 | CHI05-02-02-MG-1210 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | Trim out MEP - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1120 | CHI05-02-02-MG-1130 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 2 - MG | Overhead MEP Installation - COLO2 Cell 2 - MG | 0
CHI05-02-02-ER-1130 | CHI05-02-02-ER-1120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Install Upper Screens - COLO2 Cell 2 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1120 | CHI05-02-02-ER-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 2 - ER | Install Ceiling - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1140 | CHI05-02-02-ER-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Install Ceiling - COLO2 Cell 2 - ER | Below Ceiling MEP Rough In - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1150 | CHI05-02-02-ER-1160 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 2 - ER | Installation of ADP & ATS - COLO2 Cell 2 - ER | 2
CHI05-02-02-ER-1180 | CHI05-02-02-ER-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO2 Cell 2 - ER | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | 0
CHI05-02-02-DH-1110 | CHI05-02-02-DH-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 2 - DH | Ceiling Grid and Tile - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1150 | CHI05-02-02-DH-1170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Ceiling Grid and Tile - COLO2 Cell 2 - DH | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1170 | CHI05-02-02-DH-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 2 - DH | Install PDU's - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1160 | CHI05-02-02-DH-1100 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Install PDU's - COLO2 Cell 2 - DH | Termination at PDU & Busway - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1120 | CHI05-02-02-DH-1180 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | HAC install and Rise - COLO2 Cell 2 - DH | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1110 | CHI05-02-02-DH-1140 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 2 - DH | Security Screen Installation - COLO2 Cell 2 - DH | 6
CHI05-02-02-DH-1140 | CHI05-02-02-DH-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Security Screen Installation - COLO2 Cell 2 - DH | Ceiling Grid and Tile - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1160 | CHI05-02-02-DH-1120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Install PDU's - COLO2 Cell 2 - DH | HAC install and Rise - COLO2 Cell 2 - DH | 0
CHI05-02-02-ER-1130 | CHI05-02-02-DH-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Install Upper Screens - COLO2 Cell 2 - ER | Security Screen Installation - COLO2 Cell 2 - DH | 0
CHI05-02-02-MG-1110 | CHI05-02-02-MG-1120 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 2 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 2 - MG | 2
CHI05-02-02-MG-1110 | CHI05-02-02-MG-1120 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 2 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 2 - MG | 0
CHI05-02-02-ER-1110 | CHI05-02-02-ER-1130 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO2 Cell 2 - ER | Install Upper Screens - COLO2 Cell 2 - ER | 2
CHI05-02-02-ER-1160 | CHI05-02-02-ER-1180 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Installation of ADP & ATS - COLO2 Cell 2 - ER | Connet to Cable tray and conduit equipment - COLO2 Cell 2 - ER | 2
CHI05-02-02-DH-1190 | CHI05-02-02-DH-1120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | HAC Placing - COLO2 Cell 2 - DH | HAC install and Rise - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1170 | CHI05-02-02-DH-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 2 - DH | HAC Placing - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1100 | CHI05-02-02-DH-1200 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Termination at PDU & Busway - COLO2 Cell 2 - DH | Finishes and Signage - COLO2 Cell 2 - DH | 0
CHI05-02-02-ER-1170 | CHI05-02-02-ER-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Installation of UPS Equipment - COLO2 Cell 2 - ER | Door Frame Installation - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1190 | CHI05-02-02-ER-1210 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | Finishes and Signage - COLO2 Cell 2 - ER | 2
CHI05-02-02-ER-1200 | CHI05-02-02-ER-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Door Frame Installation - COLO2 Cell 2 - ER | Finishes and Signage - COLO2 Cell 2 - ER | 0
CHI05-02-02-L1-1260 | CHI05-02-02-L1-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Interior - L1 UPS - COLO2 Cell 2 | Interior - L1 MSB - COLO2 Cell 2 | 0
CHI05-02-02-L1-1270 | CHI05-02-02-L1-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Interior - L1 MSB - COLO2 Cell 2 | Interior - L1 ADP - COLO2 Cell 2 | 0
CHI05-02-02-L1-1270 | CHI05-02-02-L1-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Interior - L1 MSB - COLO2 Cell 2 | Interior - L1 PDUs - COLO2 Cell 2 | 0
CHI05-02-02-L1-1370 | CHI05-02-02-L1-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Interior - L1 ADP - COLO2 Cell 2 | Interior - L1 ATSs - COLO2 Cell 2 | 0
CHI05-02-02-L1-1300 | CHI05-02-02-L1-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Interior - L1 ATSs - COLO2 Cell 2 | Interior - L1 AHUs - COLO2 Cell 2 | 0
CHI05-02-02-L1-1280 | CHI05-02-02-L1-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Interior - L1 PDUs - COLO2 Cell 2 | Interior - L1 Busway - COLO2 Cell 2 | 0
CHI05-02-02-L2-1380 | CHI05-02-02-L2-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L2 UPS - COLO2 Cell 2 | Interior - L2 MSB - COLO2 Cell 2 | 0
CHI05-02-02-L2-1390 | CHI05-02-02-L2-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L2 MSB - COLO2 Cell 2 | Interior - L2 ADP - COLO2 Cell 2 | 0
CHI05-02-02-L2-1390 | CHI05-02-02-L2-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L2 MSB - COLO2 Cell 2 | Interior - L2 PDUs - COLO2 Cell 2 | 0
CHI05-02-02-L2-1490 | CHI05-02-02-L2-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L2 ADP - COLO2 Cell 2 | Interior - L2 ATSs - COLO2 Cell 2 | 0
CHI05-02-02-L2-1420 | CHI05-02-02-L2-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L2 ATSs - COLO2 Cell 2 | Interior - L2 AHUs - COLO2 Cell 2 | 0
CHI05-02-02-L2-1400 | CHI05-02-02-L2-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L2 PDUs - COLO2 Cell 2 | Interior - L2 Busway - COLO2 Cell 2 | 0
CHI05-02-02-L3-1500 | CHI05-02-02-L3-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L3 UPS - COLO2 Cell 2 | Interior - L3 MSB - COLO2 Cell 2 | 0
CHI05-02-02-L3-1510 | CHI05-02-02-L3-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L3 MSB - COLO2 Cell 2 | Interior - L3 ADP - COLO2 Cell 2 | 0
CHI05-02-02-L3-1510 | CHI05-02-02-L3-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L3 MSB - COLO2 Cell 2 | Interior - L3 PDUs - COLO2 Cell 2 | 0
CHI05-02-02-L3-1610 | CHI05-02-02-L3-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L3 ADP - COLO2 Cell 2 | Interior - L3 ATSs - COLO2 Cell 2 | 0
CHI05-02-02-L3-1540 | CHI05-02-02-L3-1530 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L3 ATSs - COLO2 Cell 2 | Interior - L3 AHUs - COLO2 Cell 2 | 0
CHI05-02-02-L3-1520 | CHI05-02-02-L3-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L3 PDUs - COLO2 Cell 2 | Interior - L3 Busway - COLO2 Cell 2 | 0
CHI05-02-02-L1-1260 | CHI05-02-02-L2-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L1 UPS - COLO2 Cell 2 | Interior - L2 UPS - COLO2 Cell 2 | 0
CHI05-02-02-L2-1380 | CHI05-02-02-L3-1500 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L2 UPS - COLO2 Cell 2 | Interior - L3 UPS - COLO2 Cell 2 | 0
CHI05-02-02-DH-1160 | CHI05-02-02-DH-1130 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Install PDU's - COLO2 Cell 2 - DH | Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1130 | CHI05-02-02-DH-1100 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH | Termination at PDU & Busway - COLO2 Cell 2 - DH | 0
CHI05-02-02-MG-1160 | CHI05-02-02-L1-1290 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Placing the AHU - COLO2 Cell 2 - MG | Interior - L1 AHUs - COLO2 Cell 2 | 0
CHI05-02-03-MG-1240 | CHI05-02-03-MG-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Overhead MEP Installation - COLO2 Cell 3 - MG | Deliver AHU into Mech. Gallery - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1250 | CHI05-02-03-MG-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO2 Cell 3 - MG | Install Walls and Primer Paint - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1260 | CHI05-02-03-MG-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Install Walls and Primer Paint - COLO2 Cell 3 - MG | Layout Ceiling and install Pencile Rod - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1280 | CHI05-02-03-MG-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO2 Cell 3 - MG | Placing the AHU - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1270 | CHI05-02-03-MG-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Placing the AHU - COLO2 Cell 3 - MG | Piping and Electrical Termination to AHUs - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1290 | CHI05-02-03-MG-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO2 Cell 3 - MG | Pipe Testing - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1300 | CHI05-02-03-MG-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Pipe Testing - COLO2 Cell 3 - MG | Install ceiling and Light Fittings - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1310 | CHI05-02-03-MG-1320 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Install ceiling and Light Fittings - COLO2 Cell 3 - MG | Trim out MEP - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1230 | CHI05-02-03-MG-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 3 - MG | Overhead MEP Installation - COLO2 Cell 3 - MG | 0
CHI05-02-03-ER-1240 | CHI05-02-03-ER-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Install Upper Screens - COLO2 Cell 3 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1230 | CHI05-02-03-ER-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 3 - ER | Install Ceiling - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1250 | CHI05-02-03-ER-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Install Ceiling - COLO2 Cell 3 - ER | Below Ceiling MEP Rough In - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1260 | CHI05-02-03-ER-1270 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 3 - ER | Installation of ADP & ATS - COLO2 Cell 3 - ER | 2
CHI05-02-03-ER-1290 | CHI05-02-03-ER-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO2 Cell 3 - ER | Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER | 0
CHI05-02-03-DH-1220 | CHI05-02-03-DH-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 3 - DH | Ceiling Grid and Tile - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1260 | CHI05-02-03-DH-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Ceiling Grid and Tile - COLO2 Cell 3 - DH | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1280 | CHI05-02-03-DH-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 3 - DH | Install PDU's - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1270 | CHI05-02-03-DH-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Install PDU's - COLO2 Cell 3 - DH | Termination at PDU & Busway - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1230 | CHI05-02-03-DH-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | HAC install and Rise - COLO2 Cell 3 - DH | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1220 | CHI05-02-03-DH-1250 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 3 - DH | Security Screen Installation - COLO2 Cell 3 - DH | 6
CHI05-02-03-DH-1250 | CHI05-02-03-DH-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Security Screen Installation - COLO2 Cell 3 - DH | Ceiling Grid and Tile - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1270 | CHI05-02-03-DH-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Install PDU's - COLO2 Cell 3 - DH | HAC install and Rise - COLO2 Cell 3 - DH | 0
CHI05-02-03-ER-1240 | CHI05-02-03-DH-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Install Upper Screens - COLO2 Cell 3 - ER | Security Screen Installation - COLO2 Cell 3 - DH | 0
CHI05-02-03-MG-1220 | CHI05-02-03-MG-1230 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 3 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 3 - MG | 2
CHI05-02-03-MG-1220 | CHI05-02-03-MG-1230 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 3 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 3 - MG | 0
CHI05-02-03-ER-1220 | CHI05-02-03-ER-1240 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO2 Cell 3 - ER | Install Upper Screens - COLO2 Cell 3 - ER | 2
CHI05-02-03-ER-1270 | CHI05-02-03-ER-1290 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Installation of ADP & ATS - COLO2 Cell 3 - ER | Connet to Cable tray and conduit equipment - COLO2 Cell 3 - ER | 2
CHI05-02-03-DH-1300 | CHI05-02-03-DH-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | HAC Placing - COLO2 Cell 3 - DH | HAC install and Rise - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1280 | CHI05-02-03-DH-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 3 - DH | HAC Placing - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1210 | CHI05-02-03-DH-1310 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Termination at PDU & Busway - COLO2 Cell 3 - DH | Finishes and Signage - COLO2 Cell 3 - DH | 0
CHI05-02-03-ER-1280 | CHI05-02-03-ER-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Installation of UPS Equipment - COLO2 Cell 3 - ER | Door Frame Installation - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1300 | CHI05-02-03-ER-1320 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER | Finishes and Signage - COLO2 Cell 3 - ER | 2
CHI05-02-03-ER-1310 | CHI05-02-03-ER-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Door Frame Installation - COLO2 Cell 3 - ER | Finishes and Signage - COLO2 Cell 3 - ER | 0
CHI05-02-03-L1-1380 | CHI05-02-03-L1-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Interior - L1 UPS - COLO2 Cell 3 | Interior - L1 MSB - COLO2 Cell 3 | 0
CHI05-02-03-L1-1390 | CHI05-02-03-L1-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Interior - L1 MSB - COLO2 Cell 3 | Interior - L1 ADP - COLO2 Cell 3 | 0
CHI05-02-03-L1-1390 | CHI05-02-03-L1-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Interior - L1 MSB - COLO2 Cell 3 | Interior - L1 PDUs - COLO2 Cell 3 | 0
CHI05-02-03-L1-1490 | CHI05-02-03-L1-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Interior - L1 ADP - COLO2 Cell 3 | Interior - L1 ATSs - COLO2 Cell 3 | 0
CHI05-02-03-L1-1420 | CHI05-02-03-L1-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Interior - L1 ATSs - COLO2 Cell 3 | Interior - L1 AHUs - COLO2 Cell 3 | 0
CHI05-02-03-L1-1400 | CHI05-02-03-L1-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Interior - L1 PDUs - COLO2 Cell 3 | Interior - L1 Busway - COLO2 Cell 3 | 0
CHI05-02-03-L2-1500 | CHI05-02-03-L2-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L2 UPS - COLO2 Cell 3 | Interior - L2 MSB - COLO2 Cell 3 | 0
CHI05-02-03-L2-1510 | CHI05-02-03-L2-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L2 MSB - COLO2 Cell 3 | Interior - L2 ADP - COLO2 Cell 3 | 0
CHI05-02-03-L2-1510 | CHI05-02-03-L2-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L2 MSB - COLO2 Cell 3 | Interior - L2 PDUs - COLO2 Cell 3 | 0
CHI05-02-03-L2-1610 | CHI05-02-03-L2-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L2 ADP - COLO2 Cell 3 | Interior - L2 ATSs - COLO2 Cell 3 | 0
CHI05-02-03-L2-1540 | CHI05-02-03-L2-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L2 ATSs - COLO2 Cell 3 | Interior - L2 AHUs - COLO2 Cell 3 | 0
CHI05-02-03-L2-1520 | CHI05-02-03-L2-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L2 PDUs - COLO2 Cell 3 | Interior - L2 Busway - COLO2 Cell 3 | 0
CHI05-02-03-L3-1620 | CHI05-02-03-L3-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L3 UPS - COLO2 Cell 3 | Interior - L3 MSB - COLO2 Cell 3 | 0
CHI05-02-03-L3-1630 | CHI05-02-03-L3-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L3 MSB - COLO2 Cell 3 | Interior - L3 ADP - COLO2 Cell 3 | 0
CHI05-02-03-L3-1630 | CHI05-02-03-L3-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L3 MSB - COLO2 Cell 3 | Interior - L3 PDUs - COLO2 Cell 3 | 0
CHI05-02-03-L3-1730 | CHI05-02-03-L3-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L3 ADP - COLO2 Cell 3 | Interior - L3 ATSs - COLO2 Cell 3 | 0
CHI05-02-03-L3-1660 | CHI05-02-03-L3-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L3 ATSs - COLO2 Cell 3 | Interior - L3 AHUs - COLO2 Cell 3 | 0
CHI05-02-03-L3-1640 | CHI05-02-03-L3-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L3 PDUs - COLO2 Cell 3 | Interior - L3 Busway - COLO2 Cell 3 | 0
CHI05-02-03-L1-1380 | CHI05-02-03-L2-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L1 UPS - COLO2 Cell 3 | Interior - L2 UPS - COLO2 Cell 3 | 0
CHI05-02-03-L2-1500 | CHI05-02-03-L3-1620 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L2 UPS - COLO2 Cell 3 | Interior - L3 UPS - COLO2 Cell 3 | 0
CHI05-02-03-DH-1270 | CHI05-02-03-DH-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Install PDU's - COLO2 Cell 3 - DH | Cable Pulling at PDU & Busway- COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1240 | CHI05-02-03-DH-1210 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Cable Pulling at PDU & Busway- COLO2 Cell 3 - DH | Termination at PDU & Busway - COLO2 Cell 3 - DH | 0
CHI05-02-03-MG-1270 | CHI05-02-03-L1-1410 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Placing the AHU - COLO2 Cell 3 - MG | Interior - L1 AHUs - COLO2 Cell 3 | 0
CHI05-02-04-MG-1350 | CHI05-02-04-MG-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Overhead MEP Installation - COLO2 Cell 4 - MG | Deliver AHU into Mech. Gallery - COLO2 Cell 4 - MG | 0
CHI05-02-04-MG-1360 | CHI05-02-04-MG-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO2 Cell 4 - MG | Install Walls and Primer Paint - COLO2 Cell 4 - MG | 0
CHI05-02-04-MG-1370 | CHI05-02-04-MG-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Install Walls and Primer Paint - COLO2 Cell 4 - MG | Layout Ceiling and install Pencile Rod - COLO2 Cell 4 - MG | 0
CHI05-02-04-MG-1390 | CHI05-02-04-MG-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO2 Cell 4 - MG | Placing the AHU - COLO2 Cell 4 - MG | 0
CHI05-02-04-MG-1380 | CHI05-02-04-MG-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Placing the AHU - COLO2 Cell 4 - MG | Piping and Electrical Termination to AHUs - COLO2 Cell 4 - MG | 0
CHI05-02-04-MG-1400 | CHI05-02-04-MG-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO2 Cell 4 - MG | Pipe Testing - COLO2 Cell 4 - MG | 0
CHI05-02-04-MG-1410 | CHI05-02-04-MG-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Pipe Testing - COLO2 Cell 4 - MG | Install ceiling and Light Fittings - COLO2 Cell 4 - MG | 0
CHI05-02-04-MG-1420 | CHI05-02-04-MG-1430 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Install ceiling and Light Fittings - COLO2 Cell 4 - MG | Trim out MEP - COLO2 Cell 4 - MG | 0
CHI05-02-04-MG-1340 | CHI05-02-04-MG-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 4 - MG | Overhead MEP Installation - COLO2 Cell 4 - MG | 0
CHI05-02-04-ER-1350 | CHI05-02-04-ER-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Install Upper Screens - COLO2 Cell 4 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 4 - ER | 0
CHI05-02-04-ER-1340 | CHI05-02-04-ER-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 4 - ER | Install Ceiling - COLO2 Cell 4 - ER | 0
CHI05-02-04-ER-1360 | CHI05-02-04-ER-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Install Ceiling - COLO2 Cell 4 - ER | Below Ceiling MEP Rough In - COLO2 Cell 4 - ER | 0
CHI05-02-04-ER-1370 | CHI05-02-04-ER-1380 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 4 - ER | Installation of ADP & ATS - COLO2 Cell 4 - ER | 2
CHI05-02-04-ER-1400 | CHI05-02-04-ER-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO2 Cell 4 - ER | Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER | 0
CHI05-02-04-DH-1330 | CHI05-02-04-DH-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 4 - DH | Ceiling Grid and Tile - COLO2 Cell 4 - DH | 0
CHI05-02-04-DH-1370 | CHI05-02-04-DH-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Ceiling Grid and Tile - COLO2 Cell 4 - DH | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 4 - DH | 0
CHI05-02-04-DH-1390 | CHI05-02-04-DH-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 4 - DH | Install PDU's - COLO2 Cell 4 - DH | 0
CHI05-02-04-DH-1380 | CHI05-02-04-DH-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Install PDU's - COLO2 Cell 4 - DH | Termination at PDU & Busway - COLO2 Cell 4 - DH | 0
CHI05-02-04-DH-1340 | CHI05-02-04-DH-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | HAC install and Rise - COLO2 Cell 4 - DH | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH | 0
CHI05-02-04-DH-1330 | CHI05-02-04-DH-1360 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 4 - DH | Security Screen Installation - COLO2 Cell 4 - DH | 6
CHI05-02-04-DH-1360 | CHI05-02-04-DH-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Security Screen Installation - COLO2 Cell 4 - DH | Ceiling Grid and Tile - COLO2 Cell 4 - DH | 0
CHI05-02-04-DH-1380 | CHI05-02-04-DH-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Install PDU's - COLO2 Cell 4 - DH | HAC install and Rise - COLO2 Cell 4 - DH | 0
CHI05-02-04-ER-1350 | CHI05-02-04-DH-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Install Upper Screens - COLO2 Cell 4 - ER | Security Screen Installation - COLO2 Cell 4 - DH | 0
CHI05-02-04-MG-1330 | CHI05-02-04-MG-1340 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 4 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 4 - MG | 2
CHI05-02-04-MG-1330 | CHI05-02-04-MG-1340 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 4 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 4 - MG | 0
CHI05-02-04-ER-1330 | CHI05-02-04-ER-1350 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO2 Cell 4 - ER | Install Upper Screens - COLO2 Cell 4 - ER | 2
CHI05-02-04-ER-1380 | CHI05-02-04-ER-1400 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Installation of ADP & ATS - COLO2 Cell 4 - ER | Connet to Cable tray and conduit equipment - COLO2 Cell 4 - ER | 2
CHI05-02-04-DH-1410 | CHI05-02-04-DH-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | HAC Placing - COLO2 Cell 4 - DH | HAC install and Rise - COLO2 Cell 4 - DH | 0
CHI05-02-04-DH-1390 | CHI05-02-04-DH-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 4 - DH | HAC Placing - COLO2 Cell 4 - DH | 0
CHI05-02-04-DH-1320 | CHI05-02-04-DH-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Termination at PDU & Busway - COLO2 Cell 4 - DH | Finishes and Signage - COLO2 Cell 4 - DH | 0
CHI05-02-04-ER-1390 | CHI05-02-04-ER-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Installation of UPS Equipment - COLO2 Cell 4 - ER | Door Frame Installation - COLO2 Cell 4 - ER | 0
CHI05-02-04-ER-1410 | CHI05-02-04-ER-1430 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER | Finishes and Signage - COLO2 Cell 4 - ER | 2
CHI05-02-04-ER-1420 | CHI05-02-04-ER-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Door Frame Installation - COLO2 Cell 4 - ER | Finishes and Signage - COLO2 Cell 4 - ER | 0
CHI05-02-04-L1-1500 | CHI05-02-04-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Interior - L1 UPS - COLO2 Cell 4 | Interior - L1 MSB - COLO2 Cell 4 | 0
CHI05-02-04-L1-1510 | CHI05-02-04-L1-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Interior - L1 MSB - COLO2 Cell 4 | Interior - L1 ADP - COLO2 Cell 4 | 0
CHI05-02-04-L1-1510 | CHI05-02-04-L1-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Interior - L1 MSB - COLO2 Cell 4 | Interior - L1 PDUs - COLO2 Cell 4 | 0
CHI05-02-04-L1-1610 | CHI05-02-04-L1-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Interior - L1 ADP - COLO2 Cell 4 | Interior - L1 ATSs - COLO2 Cell 4 | 0
CHI05-02-04-L1-1540 | CHI05-02-04-L1-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Interior - L1 ATSs - COLO2 Cell 4 | Interior - L1 AHUs - COLO2 Cell 4 | 0
CHI05-02-04-L1-1520 | CHI05-02-04-L1-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Interior - L1 PDUs - COLO2 Cell 4 | Interior - L1 Busway - COLO2 Cell 4 | 0
CHI05-02-04-L2-1620 | CHI05-02-04-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L2 UPS - COLO2 Cell 4 | Interior - L2 MSB - COLO2 Cell 4 | 0
CHI05-02-04-L2-1630 | CHI05-02-04-L2-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L2 MSB - COLO2 Cell 4 | Interior - L2 ADP - COLO2 Cell 4 | 0
CHI05-02-04-L2-1630 | CHI05-02-04-L2-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L2 MSB - COLO2 Cell 4 | Interior - L2 PDUs - COLO2 Cell 4 | 0
CHI05-02-04-L2-1730 | CHI05-02-04-L2-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L2 ADP - COLO2 Cell 4 | Interior - L2 ATSs - COLO2 Cell 4 | 0
CHI05-02-04-L2-1660 | CHI05-02-04-L2-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L2 ATSs - COLO2 Cell 4 | Interior - L2 AHUs - COLO2 Cell 4 | 0
CHI05-02-04-L2-1640 | CHI05-02-04-L2-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L2 PDUs - COLO2 Cell 4 | Interior - L2 Busway - COLO2 Cell 4 | 0
CHI05-02-04-L3-1740 | CHI05-02-04-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L3 UPS - COLO2 Cell 4 | Interior - L3 MSB - COLO2 Cell 4 | 0
CHI05-02-04-L3-1750 | CHI05-02-04-L3-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L3 MSB - COLO2 Cell 4 | Interior - L3 ADP - COLO2 Cell 4 | 0
CHI05-02-04-L3-1750 | CHI05-02-04-L3-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L3 MSB - COLO2 Cell 4 | Interior - L3 PDUs - COLO2 Cell 4 | 0
CHI05-02-04-L3-1850 | CHI05-02-04-L3-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L3 ADP - COLO2 Cell 4 | Interior - L3 ATSs - COLO2 Cell 4 | 0
CHI05-02-04-L3-1780 | CHI05-02-04-L3-1770 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L3 ATSs - COLO2 Cell 4 | Interior - L3 AHUs - COLO2 Cell 4 | 0
CHI05-02-04-L3-1760 | CHI05-02-04-L3-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L3 PDUs - COLO2 Cell 4 | Interior - L3 Busway - COLO2 Cell 4 | 0
CHI05-02-04-L1-1500 | CHI05-02-04-L2-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L1 UPS - COLO2 Cell 4 | Interior - L2 UPS - COLO2 Cell 4 | 0
CHI05-02-04-L2-1620 | CHI05-02-04-L3-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L2 UPS - COLO2 Cell 4 | Interior - L3 UPS - COLO2 Cell 4 | 0
CHI05-02-04-DH-1380 | CHI05-02-04-DH-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Install PDU's - COLO2 Cell 4 - DH | Cable Pulling at PDU & Busway- COLO2 Cell 4 - DH | 0
CHI05-02-04-DH-1350 | CHI05-02-04-DH-1320 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Cable Pulling at PDU & Busway- COLO2 Cell 4 - DH | Termination at PDU & Busway - COLO2 Cell 4 - DH | 0
CHI05-02-04-MG-1380 | CHI05-02-04-L1-1530 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Placing the AHU - COLO2 Cell 4 - MG | Interior - L1 AHUs - COLO2 Cell 4 | 0
CHI05-02-01-MG-1000 | CHI05-02-01-ER-1000 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG | Install Walls and Primer Paint - COLO2 Cell 1 - ER | 0
CHI05-02-01-ER-1000 | CHI05-02-01-DH-1000 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Install Walls and Primer Paint - COLO2 Cell 1 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 1 - DH | 0
CHI05-02-02-MG-1110 | CHI05-02-02-ER-1110 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 2 - MG | Install Walls and Primer Paint - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1110 | CHI05-02-02-DH-1110 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Install Walls and Primer Paint - COLO2 Cell 2 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 2 - DH | 0
CHI05-02-03-MG-1220 | CHI05-02-03-ER-1220 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 3 - MG | Install Walls and Primer Paint - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1220 | CHI05-02-03-DH-1220 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Install Walls and Primer Paint - COLO2 Cell 3 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 3 - DH | 0
CHI05-02-04-MG-1330 | CHI05-02-04-ER-1330 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 4 - MG | Install Walls and Primer Paint - COLO2 Cell 4 - ER | 0
CHI05-02-04-ER-1330 | CHI05-02-04-DH-1330 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Install Walls and Primer Paint - COLO2 Cell 4 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 4 - DH | 0
CHI05-02-03-MG-1220 | CHI05-02-04-MG-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 3 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 4 - MG | 0
CHI05-02-02-MG-1110 | CHI05-02-03-MG-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 2 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 3 - MG | 0
CHI05-02-01-MG-1000 | CHI05-02-02-MG-1110 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 2 - MG | 0
CHI05-02-04-L3-1770 | CHI05-02-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,5,1 Level 4 Cx - Colo 2 | Interior - L3 AHUs - COLO2 Cell 4 | COLO2 Cx LEV4 - COLO2 | 0
CHI05-02-02-L3-1530 | CHI05-02-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,5,1 Level 4 Cx - Colo 2 | Interior - L3 AHUs - COLO2 Cell 2 | COLO2 Cx LEV4 - COLO2 | 0
CHI05-02-03-L3-1650 | CHI05-02-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,5,1 Level 4 Cx - Colo 2 | Interior - L3 AHUs - COLO2 Cell 3 | COLO2 Cx LEV4 - COLO2 | 0
CHI05-03-04-L4-1000 | CHI05-03-04-L5-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,5,1 Level 4 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,5,2 Level 5 Cx / IST - Colo 3 | Cx LEV4 - COLO3 | Cx LEV5 / IST - COLO3 | 0
CHI05-03-01-MG-1130 | CHI05-03-01-MG-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Overhead MEP Installation - COLO3 Cell 1 - MG | Deliver AHU into Mech. Gallery - COLO3 Cell 1 - MG | 0
CHI05-03-01-MG-1140 | CHI05-03-01-MG-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO3 Cell 1 - MG | Install Walls and Primer Paint - COLO3 Cell 1 - MG | 0
CHI05-03-01-MG-1150 | CHI05-03-01-MG-1170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Install Walls and Primer Paint - COLO3 Cell 1 - MG | Layout Ceiling and install Pencile Rod - COLO3 Cell 1 - MG | 0
CHI05-03-01-MG-1170 | CHI05-03-01-MG-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO3 Cell 1 - MG | Placing the AHU - COLO3 Cell 1 - MG | 0
CHI05-03-01-MG-1160 | CHI05-03-01-MG-1180 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Placing the AHU - COLO3 Cell 1 - MG | Piping and Electrical Termination to AHUs - COLO3 Cell 1 - MG | 0
CHI05-03-01-MG-1180 | CHI05-03-01-MG-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO3 Cell 1 - MG | Pipe Testing - COLO3 Cell 1 - MG | 0
CHI05-03-01-MG-1190 | CHI05-03-01-MG-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Pipe Testing - COLO3 Cell 1 - MG | Install ceiling and Light Fittings - COLO3 Cell 1 - MG | 0
CHI05-03-01-MG-1200 | CHI05-03-01-MG-1210 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Install ceiling and Light Fittings - COLO3 Cell 1 - MG | Trim out MEP - COLO3 Cell 1 - MG | 0
CHI05-03-01-MG-1120 | CHI05-03-01-MG-1130 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 1 - MG | Overhead MEP Installation - COLO3 Cell 1 - MG | 0
CHI05-03-01-ER-1130 | CHI05-03-01-ER-1120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Install Upper Screens - COLO3 Cell 1 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 1 - ER | 0
CHI05-03-01-ER-1120 | CHI05-03-01-ER-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 1 - ER | Install Ceiling - COLO3 Cell 1 - ER | 0
CHI05-03-01-ER-1140 | CHI05-03-01-ER-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Install Ceiling - COLO3 Cell 1 - ER | Below Ceiling MEP Rough In - COLO3 Cell 1 - ER | 0
CHI05-03-01-ER-1150 | CHI05-03-01-ER-1160 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 1 - ER | Installation of ADP & ATS - COLO3 Cell 1 - ER | 2
CHI05-03-01-ER-1180 | CHI05-03-01-ER-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO3 Cell 1 - ER | Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER | 0
CHI05-03-01-DH-1110 | CHI05-03-01-DH-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 1 - DH | Ceiling Grid and Tile - COLO3 Cell 1 - DH | 0
CHI05-03-01-DH-1150 | CHI05-03-01-DH-1170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Ceiling Grid and Tile - COLO3 Cell 1 - DH | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 1 - DH | 0
CHI05-03-01-DH-1170 | CHI05-03-01-DH-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 1 - DH | Install PDU's - COLO3 Cell 1 - DH | 0
CHI05-03-01-DH-1160 | CHI05-03-01-DH-1100 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Install PDU's - COLO3 Cell 1 - DH | Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH | 0
CHI05-03-01-DH-1120 | CHI05-03-01-DH-1180 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | HAC install and Rise - COLO3 Cell 1 - DH | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH | 0
CHI05-03-01-DH-1110 | CHI05-03-01-DH-1140 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 1 - DH | Security Screen Installation - COLO3 Cell 1 - DH | 6
CHI05-03-01-DH-1140 | CHI05-03-01-DH-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Security Screen Installation - COLO3 Cell 1 - DH | Ceiling Grid and Tile - COLO3 Cell 1 - DH | 0
CHI05-03-01-DH-1160 | CHI05-03-01-DH-1120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Install PDU's - COLO3 Cell 1 - DH | HAC install and Rise - COLO3 Cell 1 - DH | 0
CHI05-03-01-ER-1130 | CHI05-03-01-DH-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Install Upper Screens - COLO3 Cell 1 - ER | Security Screen Installation - COLO3 Cell 1 - DH | 0
CHI05-03-01-MG-1110 | CHI05-03-01-MG-1120 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 1 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 1 - MG | 2
CHI05-03-01-MG-1110 | CHI05-03-01-MG-1120 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 1 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 1 - MG | 0
CHI05-03-01-ER-1110 | CHI05-03-01-ER-1130 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO3 Cell 1 - ER | Install Upper Screens - COLO3 Cell 1 - ER | 2
CHI05-03-01-ER-1160 | CHI05-03-01-ER-1180 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Installation of ADP & ATS - COLO3 Cell 1 - ER | Connet to Cable tray and conduit equipment - COLO3 Cell 1 - ER | 2
CHI05-03-01-DH-1190 | CHI05-03-01-DH-1120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | HAC Placing - COLO3 Cell 1 - DH | HAC install and Rise - COLO3 Cell 1 - DH | 0
CHI05-03-01-DH-1170 | CHI05-03-01-DH-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 1 - DH | HAC Placing - COLO3 Cell 1 - DH | 0
CHI05-03-01-DH-1100 | CHI05-03-01-DH-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH | Finishes and Signage - COLO3 Cell 1 - DH | 0
CHI05-03-01-ER-1170 | CHI05-03-01-ER-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Installation of UPS Equipment - COLO3 Cell 1 - ER | Door Frame Installation - COLO3 Cell 1 - ER | 0
CHI05-03-01-ER-1190 | CHI05-03-01-ER-1210 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER | Finishes and Signage - COLO3 Cell 1 - ER | 2
CHI05-03-01-ER-1200 | CHI05-03-01-ER-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Door Frame Installation - COLO3 Cell 1 - ER | Finishes and Signage - COLO3 Cell 1 - ER | 0
CHI05-03-01-L1-1350 | CHI05-03-01-L1-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | L1 XFMR - MV- COLO3 | Interior - L1 MSB - COLO3 Cell 1 | 0
CHI05-03-01-L1-1260 | CHI05-03-01-L1-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Interior - L1 UPS - COLO3 Cell 1 | Interior - L1 MSB - COLO3 Cell 1 | 0
CHI05-03-01-L1-1270 | CHI05-03-01-L1-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Interior - L1 MSB - COLO3 Cell 1 | Interior - L1 ADP - COLO3 Cell 1 | 0
CHI05-03-01-L1-1270 | CHI05-03-01-L1-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Interior - L1 MSB - COLO3 Cell 1 | Interior - L1 PDUs - COLO3 Cell 1 | 0
CHI05-03-01-L1-1370 | CHI05-03-01-L1-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Interior - L1 ADP - COLO3 Cell 1 | Interior - L1 ATSs - COLO3 Cell 1 | 0
CHI05-03-01-L1-1300 | CHI05-03-01-L1-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Interior - L1 ATSs - COLO3 Cell 1 | Interior - L1 AHUs - COLO3 Cell 1 | 0
CHI05-03-01-L1-1280 | CHI05-03-01-L1-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Interior - L1 PDUs - COLO3 Cell 1 | Interior - L1 Busway - COLO3 Cell 1 | 0
CHI05-03-01-L1-1360 | CHI05-03-01-L1-1270 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | L1 GEN - COLO3 | Interior - L1 MSB - COLO3 Cell 1 | 0
CHI05-03-01-L2-1460 | CHI05-03-01-L2-1470 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UPM - COLO3 | L2 XFMR - COLO3 | 0
CHI05-03-01-L2-1470 | CHI05-03-01-L2-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | L2 XFMR - COLO3 | Interior - L2 MSB - COLO3 Cell 1 | 0
CHI05-03-01-L2-1380 | CHI05-03-01-L2-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L2 UPS - COLO3 Cell 1 | Interior - L2 MSB - COLO3 Cell 1 | 0
CHI05-03-01-L2-1390 | CHI05-03-01-L2-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L2 MSB - COLO3 Cell 1 | Interior - L2 ADP - COLO3 Cell 1 | 0
CHI05-03-01-L2-1390 | CHI05-03-01-L2-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L2 MSB - COLO3 Cell 1 | Interior - L2 PDUs - COLO3 Cell 1 | 0
CHI05-03-01-L2-1490 | CHI05-03-01-L2-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L2 ADP - COLO3 Cell 1 | Interior - L2 ATSs - COLO3 Cell 1 | 0
CHI05-03-01-L2-1420 | CHI05-03-01-L2-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L2 ATSs - COLO3 Cell 1 | Interior - L2 AHUs - COLO3 Cell 1 | 0
CHI05-03-01-L2-1400 | CHI05-03-01-L2-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L2 PDUs - COLO3 Cell 1 | Interior - L2 Busway - COLO3 Cell 1 | 0
CHI05-03-01-L2-1480 | CHI05-03-01-L2-1390 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | L2 GEN - COLO3 | Interior - L2 MSB - COLO3 Cell 1 | 0
CHI05-03-01-L3-1580 | CHI05-03-01-L3-1590 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UPM - COLO3 | L3 XFMR - COLO3 | 0
CHI05-03-01-L3-1590 | CHI05-03-01-L3-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | L3 XFMR - COLO3 | Interior - L3 MSB - COLO3 Cell 1 | 0
CHI05-03-01-L3-1500 | CHI05-03-01-L3-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L3 UPS - COLO3 Cell 1 | Interior - L3 MSB - COLO3 Cell 1 | 0
CHI05-03-01-L3-1510 | CHI05-03-01-L3-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L3 MSB - COLO3 Cell 1 | Interior - L3 ADP - COLO3 Cell 1 | 0
CHI05-03-01-L3-1510 | CHI05-03-01-L3-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L3 MSB - COLO3 Cell 1 | Interior - L3 PDUs - COLO3 Cell 1 | 0
CHI05-03-01-L3-1610 | CHI05-03-01-L3-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L3 ADP - COLO3 Cell 1 | Interior - L3 ATSs - COLO3 Cell 1 | 0
CHI05-03-01-L3-1540 | CHI05-03-01-L3-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L3 ATSs - COLO3 Cell 1 | Interior - L3 AHUs - COLO3 Cell 1 | 0
CHI05-03-01-L3-1520 | CHI05-03-01-L3-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L3 PDUs - COLO3 Cell 1 | Interior - L3 Busway - COLO3 Cell 1 | 0
CHI05-03-01-L1-1260 | CHI05-03-01-L2-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L1 UPS - COLO3 Cell 1 | Interior - L2 UPS - COLO3 Cell 1 | 0
CHI05-03-01-L2-1380 | CHI05-03-01-L3-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L2 UPS - COLO3 Cell 1 | Interior - L3 UPS - COLO3 Cell 1 | 0
CHI05-03-01-DH-1160 | CHI05-03-01-DH-1130 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Install PDU's - COLO3 Cell 1 - DH | Termination at PDU & Busway- COLO3 Cell 1 - DH | 0
CHI05-03-01-DH-1130 | CHI05-03-01-DH-1100 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Termination at PDU & Busway- COLO3 Cell 1 - DH | Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH | 0
CHI05-03-01-MG-1160 | CHI05-03-01-L1-1290 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Placing the AHU - COLO3 Cell 1 - MG | Interior - L1 AHUs - COLO3 Cell 1 | 0
CHI05-03-01-L1-1360 | CHI05-03-01-L2-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L1 GEN - COLO3 | L2 GEN - COLO3 | 0
CHI05-03-01-L2-1480 | CHI05-03-01-L3-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L2 GEN - COLO3 | L3 GEN - COLO3 | 0
CHI05-03-01-L3-1530 | CHI05-03-04-L4-1000 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,5,1 Level 4 Cx - Colo 3 | Interior - L3 AHUs - COLO3 Cell 1 | Cx LEV4 - COLO3 | 2
CHI05-03-02-MG-1240 | CHI05-03-02-MG-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Overhead MEP Installation - COLO3 Cell 2 - MG | Deliver AHU into Mech. Gallery - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1250 | CHI05-03-02-MG-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO3 Cell 2 - MG | Install Walls and Primer Paint - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1260 | CHI05-03-02-MG-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Install Walls and Primer Paint - COLO3 Cell 2 - MG | Layout Ceiling and install Pencile Rod - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1280 | CHI05-03-02-MG-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO3 Cell 2 - MG | Placing the AHU - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1270 | CHI05-03-02-MG-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Placing the AHU - COLO3 Cell 2 - MG | Piping and Electrical Termination to AHUs - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1290 | CHI05-03-02-MG-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO3 Cell 2 - MG | Pipe Testing - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1300 | CHI05-03-02-MG-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Pipe Testing - COLO3 Cell 2 - MG | Install ceiling and Light Fittings - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1310 | CHI05-03-02-MG-1320 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Install ceiling and Light Fittings - COLO3 Cell 2 - MG | Trim out MEP - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1230 | CHI05-03-02-MG-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 2 - MG | Overhead MEP Installation - COLO3 Cell 2 - MG | 0
CHI05-03-02-ER-1240 | CHI05-03-02-ER-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Install Upper Screens - COLO3 Cell 2 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1230 | CHI05-03-02-ER-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 2 - ER | Install Ceiling - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1250 | CHI05-03-02-ER-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Install Ceiling - COLO3 Cell 2 - ER | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1260 | CHI05-03-02-ER-1270 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | Installation of ADP & ATS - COLO3 Cell 2 - ER | 2
CHI05-03-02-ER-1290 | CHI05-03-02-ER-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO3 Cell 2 - ER | Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER | 0
CHI05-03-02-DH-1220 | CHI05-03-02-DH-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 2 - DH | Ceiling Grid and Tile - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1260 | CHI05-03-02-DH-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Ceiling Grid and Tile - COLO3 Cell 2 - DH | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1280 | CHI05-03-02-DH-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH | Install PDU's - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1270 | CHI05-03-02-DH-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Install PDU's - COLO3 Cell 2 - DH | Termination at PDU & Busway - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1230 | CHI05-03-02-DH-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | HAC install and Rise - COLO3 Cell 2 - DH | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1220 | CHI05-03-02-DH-1250 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 2 - DH | Security Screen Installation - COLO3 Cell 2 - DH | 6
CHI05-03-02-DH-1250 | CHI05-03-02-DH-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Security Screen Installation - COLO3 Cell 2 - DH | Ceiling Grid and Tile - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1270 | CHI05-03-02-DH-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Install PDU's - COLO3 Cell 2 - DH | HAC install and Rise - COLO3 Cell 2 - DH | 0
CHI05-03-02-ER-1240 | CHI05-03-02-DH-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Install Upper Screens - COLO3 Cell 2 - ER | Security Screen Installation - COLO3 Cell 2 - DH | 0
CHI05-03-02-MG-1220 | CHI05-03-02-MG-1230 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 2 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 2 - MG | 2
CHI05-03-02-MG-1220 | CHI05-03-02-MG-1230 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 2 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 2 - MG | 0
CHI05-03-02-ER-1220 | CHI05-03-02-ER-1240 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO3 Cell 2 - ER | Install Upper Screens - COLO3 Cell 2 - ER | 2
CHI05-03-02-ER-1270 | CHI05-03-02-ER-1290 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Installation of ADP & ATS - COLO3 Cell 2 - ER | Connet to Cable tray and conduit equipment - COLO3 Cell 2 - ER | 2
CHI05-03-02-DH-1300 | CHI05-03-02-DH-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | HAC Placing - COLO3 Cell 2 - DH | HAC install and Rise - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1280 | CHI05-03-02-DH-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH | HAC Placing - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1210 | CHI05-03-02-DH-1310 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Termination at PDU & Busway - COLO3 Cell 2 - DH | Finishes and Signage - COLO3 Cell 2 - DH | 0
CHI05-03-02-ER-1280 | CHI05-03-02-ER-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Installation of UPS Equipment - COLO3 Cell 2 - ER | Door Frame Installation - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1300 | CHI05-03-02-ER-1320 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER | Finishes and Signage - COLO3 Cell 2 - ER | 2
CHI05-03-02-ER-1310 | CHI05-03-02-ER-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Door Frame Installation - COLO3 Cell 2 - ER | Finishes and Signage - COLO3 Cell 2 - ER | 0
CHI05-03-02-L1-1380 | CHI05-03-02-L1-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Interior - L1 UPS - COLO3 Cell 2 | Interior - L1 MSB - COLO3 Cell 2 | 0
CHI05-03-02-L1-1390 | CHI05-03-02-L1-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Interior - L1 MSB - COLO3 Cell 2 | Interior - L1 ADP - COLO3 Cell 2 | 0
CHI05-03-02-L1-1390 | CHI05-03-02-L1-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Interior - L1 MSB - COLO3 Cell 2 | Interior - L1 PDUs - COLO3 Cell 2 | 0
CHI05-03-02-L1-1490 | CHI05-03-02-L1-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Interior - L1 ADP - COLO3 Cell 2 | Interior - L1 ATSs - COLO3 Cell 2 | 0
CHI05-03-02-L1-1420 | CHI05-03-02-L1-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Interior - L1 ATSs - COLO3 Cell 2 | Interior - L1 AHUs - COLO3 Cell 2 | 0
CHI05-03-02-L1-1400 | CHI05-03-02-L1-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Interior - L1 PDUs - COLO3 Cell 2 | Interior - L1 Busway - COLO3 Cell 2 | 0
CHI05-03-02-L2-1500 | CHI05-03-02-L2-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L2 UPS - COLO3 Cell 2 | Interior - L2 MSB - COLO3 Cell 2 | 0
CHI05-03-02-L2-1510 | CHI05-03-02-L2-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L2 MSB - COLO3 Cell 2 | Interior - L2 ADP - COLO3 Cell 2 | 0
CHI05-03-02-L2-1510 | CHI05-03-02-L2-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L2 MSB - COLO3 Cell 2 | Interior - L2 PDUs - COLO3 Cell 2 | 0
CHI05-03-02-L2-1610 | CHI05-03-02-L2-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L2 ADP - COLO3 Cell 2 | Interior - L2 ATSs - COLO3 Cell 2 | 0
CHI05-03-02-L2-1540 | CHI05-03-02-L2-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L2 ATSs - COLO3 Cell 2 | Interior - L2 AHUs - COLO3 Cell 2 | 0
CHI05-03-02-L2-1520 | CHI05-03-02-L2-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L2 PDUs - COLO3 Cell 2 | Interior - L2 Busway - COLO3 Cell 2 | 0
CHI05-03-02-L3-1620 | CHI05-03-02-L3-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L3 UPS - COLO3 Cell 2 | Interior - L3 MSB - COLO3 Cell 2 | 0
CHI05-03-02-L3-1630 | CHI05-03-02-L3-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L3 MSB - COLO3 Cell 2 | Interior - L3 ADP - COLO3 Cell 2 | 0
CHI05-03-02-L3-1630 | CHI05-03-02-L3-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L3 MSB - COLO3 Cell 2 | Interior - L3 PDUs - COLO3 Cell 2 | 0
CHI05-03-02-L3-1730 | CHI05-03-02-L3-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L3 ADP - COLO3 Cell 2 | Interior - L3 ATSs - COLO3 Cell 2 | 0
CHI05-03-02-L3-1660 | CHI05-03-02-L3-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L3 ATSs - COLO3 Cell 2 | Interior - L3 AHUs - COLO3 Cell 2 | 0
CHI05-03-02-L3-1640 | CHI05-03-02-L3-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L3 PDUs - COLO3 Cell 2 | Interior - L3 Busway - COLO3 Cell 2 | 0
CHI05-03-02-L1-1380 | CHI05-03-02-L2-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L1 UPS - COLO3 Cell 2 | Interior - L2 UPS - COLO3 Cell 2 | 0
CHI05-03-02-L2-1500 | CHI05-03-02-L3-1620 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L2 UPS - COLO3 Cell 2 | Interior - L3 UPS - COLO3 Cell 2 | 0
CHI05-03-02-DH-1270 | CHI05-03-02-DH-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Install PDU's - COLO3 Cell 2 - DH | Cable Pulling at PDU & Busway- COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1240 | CHI05-03-02-DH-1210 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Cable Pulling at PDU & Busway- COLO3 Cell 2 - DH | Termination at PDU & Busway - COLO3 Cell 2 - DH | 0
CHI05-03-02-MG-1270 | CHI05-03-02-L1-1410 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Placing the AHU - COLO3 Cell 2 - MG | Interior - L1 AHUs - COLO3 Cell 2 | 0
CHI05-03-03-MG-1350 | CHI05-03-03-MG-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Overhead MEP Installation - COLO3 Cell 3 - MG | Deliver AHU into Mech. Gallery - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1360 | CHI05-03-03-MG-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO3 Cell 3 - MG | Install Walls and Primer Paint - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1370 | CHI05-03-03-MG-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Install Walls and Primer Paint - COLO3 Cell 3 - MG | Layout Ceiling and install Pencile Rod - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1390 | CHI05-03-03-MG-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO3 Cell 3 - MG | Placing the AHU - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1380 | CHI05-03-03-MG-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Placing the AHU - COLO3 Cell 3 - MG | Piping and Electrical Termination to AHUs - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1400 | CHI05-03-03-MG-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO3 Cell 3 - MG | Pipe Testing - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1410 | CHI05-03-03-MG-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Pipe Testing - COLO3 Cell 3 - MG | Install ceiling and Light Fittings - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1420 | CHI05-03-03-MG-1430 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Install ceiling and Light Fittings - COLO3 Cell 3 - MG | Trim out MEP - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1340 | CHI05-03-03-MG-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 3 - MG | Overhead MEP Installation - COLO3 Cell 3 - MG | 0
CHI05-03-03-ER-1350 | CHI05-03-03-ER-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Install Upper Screens - COLO3 Cell 3 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1340 | CHI05-03-03-ER-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 3 - ER | Install Ceiling - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1360 | CHI05-03-03-ER-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Install Ceiling - COLO3 Cell 3 - ER | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1370 | CHI05-03-03-ER-1380 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | Installation of ADP & ATS - COLO3 Cell 3 - ER | 2
CHI05-03-03-ER-1400 | CHI05-03-03-ER-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO3 Cell 3 - ER | Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER | 0
CHI05-03-03-DH-1330 | CHI05-03-03-DH-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 3 - DH | Ceiling Grid and Tile - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1370 | CHI05-03-03-DH-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Ceiling Grid and Tile - COLO3 Cell 3 - DH | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1390 | CHI05-03-03-DH-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH | Install PDU's - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1380 | CHI05-03-03-DH-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Install PDU's - COLO3 Cell 3 - DH | Termination at PDU & Busway - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1340 | CHI05-03-03-DH-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | HAC install and Rise - COLO3 Cell 3 - DH | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1330 | CHI05-03-03-DH-1360 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 3 - DH | Security Screen Installation - COLO3 Cell 3 - DH | 6
CHI05-03-03-DH-1360 | CHI05-03-03-DH-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Security Screen Installation - COLO3 Cell 3 - DH | Ceiling Grid and Tile - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1380 | CHI05-03-03-DH-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Install PDU's - COLO3 Cell 3 - DH | HAC install and Rise - COLO3 Cell 3 - DH | 0
CHI05-03-03-ER-1350 | CHI05-03-03-DH-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Install Upper Screens - COLO3 Cell 3 - ER | Security Screen Installation - COLO3 Cell 3 - DH | 0
CHI05-03-03-MG-1330 | CHI05-03-03-MG-1340 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 3 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 3 - MG | 2
CHI05-03-03-MG-1330 | CHI05-03-03-MG-1340 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 3 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 3 - MG | 0
CHI05-03-03-ER-1330 | CHI05-03-03-ER-1350 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO3 Cell 3 - ER | Install Upper Screens - COLO3 Cell 3 - ER | 2
CHI05-03-03-ER-1380 | CHI05-03-03-ER-1400 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Installation of ADP & ATS - COLO3 Cell 3 - ER | Connet to Cable tray and conduit equipment - COLO3 Cell 3 - ER | 2
CHI05-03-03-DH-1410 | CHI05-03-03-DH-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | HAC Placing - COLO3 Cell 3 - DH | HAC install and Rise - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1390 | CHI05-03-03-DH-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH | HAC Placing - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1320 | CHI05-03-03-DH-1420 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Termination at PDU & Busway - COLO3 Cell 3 - DH | Finishes and Signage - COLO3 Cell 3 - DH | 0
CHI05-03-03-ER-1390 | CHI05-03-03-ER-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Installation of UPS Equipment - COLO3 Cell 3 - ER | Door Frame Installation - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1410 | CHI05-03-03-ER-1430 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER | Finishes and Signage - COLO3 Cell 3 - ER | 2
CHI05-03-03-ER-1420 | CHI05-03-03-ER-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Door Frame Installation - COLO3 Cell 3 - ER | Finishes and Signage - COLO3 Cell 3 - ER | 0
CHI05-03-03-L1-1500 | CHI05-03-03-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | Interior - L1 UPS - COLO3 Cell 3 | Interior - L1 MSB - COLO3 Cell 3 | 0
CHI05-03-03-L1-1510 | CHI05-03-03-L1-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | Interior - L1 MSB - COLO3 Cell 3 | Interior - L1 ADP - COLO3 Cell 3 | 0
CHI05-03-03-L1-1510 | CHI05-03-03-L1-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | Interior - L1 MSB - COLO3 Cell 3 | Interior - L1 PDUs - COLO3 Cell 3 | 0
CHI05-03-03-L1-1610 | CHI05-03-03-L1-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | Interior - L1 ADP - COLO3 Cell 3 | Interior - L1 ATSs - COLO3 Cell 3 | 0
CHI05-03-03-L1-1540 | CHI05-03-03-L1-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | Interior - L1 ATSs - COLO3 Cell 3 | Interior - L1 AHUs - COLO3 Cell 3 | 0
CHI05-03-03-L1-1520 | CHI05-03-03-L1-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | Interior - L1 PDUs - COLO3 Cell 3 | Interior - L1 Busway - COLO3 Cell 3 | 0
CHI05-03-03-L2-1620 | CHI05-03-03-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | Interior - L2 UPS - COLO3 Cell 3 | Interior - L2 MSB - COLO3 Cell 3 | 0
CHI05-03-03-L2-1630 | CHI05-03-03-L2-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | Interior - L2 MSB - COLO3 Cell 3 | Interior - L2 ADP - COLO3 Cell 3 | 0
CHI05-03-03-L2-1630 | CHI05-03-03-L2-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | Interior - L2 MSB - COLO3 Cell 3 | Interior - L2 PDUs - COLO3 Cell 3 | 0
CHI05-03-03-L2-1730 | CHI05-03-03-L2-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | Interior - L2 ADP - COLO3 Cell 3 | Interior - L2 ATSs - COLO3 Cell 3 | 0
CHI05-03-03-L2-1660 | CHI05-03-03-L2-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | Interior - L2 ATSs - COLO3 Cell 3 | Interior - L2 AHUs - COLO3 Cell 3 | 0
CHI05-03-03-L2-1640 | CHI05-03-03-L2-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | Interior - L2 PDUs - COLO3 Cell 3 | Interior - L2 Busway - COLO3 Cell 3 | 0
CHI05-03-03-L3-1740 | CHI05-03-03-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | Interior - L3 UPS - COLO3 Cell 3 | Interior - L3 MSB - COLO3 Cell 3 | 0
CHI05-03-03-L3-1750 | CHI05-03-03-L3-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | Interior - L3 MSB - COLO3 Cell 3 | Interior - L3 ADP - COLO3 Cell 3 | 0
CHI05-03-03-L3-1750 | CHI05-03-03-L3-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | Interior - L3 MSB - COLO3 Cell 3 | Interior - L3 PDUs - COLO3 Cell 3 | 0
CHI05-03-03-L3-1850 | CHI05-03-03-L3-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | Interior - L3 ADP - COLO3 Cell 3 | Interior - L3 ATSs - COLO3 Cell 3 | 0
CHI05-03-03-L3-1780 | CHI05-03-03-L3-1770 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | Interior - L3 ATSs - COLO3 Cell 3 | Interior - L3 AHUs - COLO3 Cell 3 | 0
CHI05-03-03-L3-1760 | CHI05-03-03-L3-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | Interior - L3 PDUs - COLO3 Cell 3 | Interior - L3 Busway - COLO3 Cell 3 | 0
CHI05-03-03-L1-1500 | CHI05-03-03-L2-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | Interior - L1 UPS - COLO3 Cell 3 | Interior - L2 UPS - COLO3 Cell 3 | 0
CHI05-03-03-L2-1620 | CHI05-03-03-L3-1740 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | Interior - L2 UPS - COLO3 Cell 3 | Interior - L3 UPS - COLO3 Cell 3 | 0
CHI05-03-03-DH-1380 | CHI05-03-03-DH-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Install PDU's - COLO3 Cell 3 - DH | Cable Pulling at PDU & Busway- COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1350 | CHI05-03-03-DH-1320 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Cable Pulling at PDU & Busway- COLO3 Cell 3 - DH | Termination at PDU & Busway - COLO3 Cell 3 - DH | 0
CHI05-03-03-MG-1380 | CHI05-03-03-L1-1530 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | Placing the AHU - COLO3 Cell 3 - MG | Interior - L1 AHUs - COLO3 Cell 3 | 0
CHI05-03-04-MG-1460 | CHI05-03-04-MG-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Overhead MEP Installation - COLO3 Cell 4 - MG | Deliver AHU into Mech. Gallery - COLO3 Cell 4 - MG | 0
CHI05-03-04-MG-1470 | CHI05-03-04-MG-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO3 Cell 4 - MG | Install Walls and Primer Paint - COLO3 Cell 4 - MG | 0
CHI05-03-04-MG-1480 | CHI05-03-04-MG-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Install Walls and Primer Paint - COLO3 Cell 4 - MG | Layout Ceiling and install Pencile Rod - COLO3 Cell 4 - MG | 0
CHI05-03-04-MG-1500 | CHI05-03-04-MG-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO3 Cell 4 - MG | Placing the AHU - COLO3 Cell 4 - MG | 0
CHI05-03-04-MG-1490 | CHI05-03-04-MG-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Placing the AHU - COLO3 Cell 4 - MG | Piping and Electrical Termination to AHUs - COLO3 Cell 4 - MG | 0
CHI05-03-04-MG-1510 | CHI05-03-04-MG-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO3 Cell 4 - MG | Pipe Testing - COLO3 Cell 4 - MG | 0
CHI05-03-04-MG-1520 | CHI05-03-04-MG-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Pipe Testing - COLO3 Cell 4 - MG | Install ceiling and Light Fittings - COLO3 Cell 4 - MG | 0
CHI05-03-04-MG-1530 | CHI05-03-04-MG-1540 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Install ceiling and Light Fittings - COLO3 Cell 4 - MG | Trim out MEP - COLO3 Cell 4 - MG | 0
CHI05-03-04-MG-1450 | CHI05-03-04-MG-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 4 - MG | Overhead MEP Installation - COLO3 Cell 4 - MG | 0
CHI05-03-04-ER-1460 | CHI05-03-04-ER-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Install Upper Screens - COLO3 Cell 4 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 4 - ER | 0
CHI05-03-04-ER-1450 | CHI05-03-04-ER-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 4 - ER | Install Ceiling - COLO3 Cell 4 - ER | 0
CHI05-03-04-ER-1470 | CHI05-03-04-ER-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Install Ceiling - COLO3 Cell 4 - ER | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | 0
CHI05-03-04-ER-1480 | CHI05-03-04-ER-1490 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | Installation of ADP & ATS - COLO3 Cell 4 - ER | 2
CHI05-03-04-ER-1510 | CHI05-03-04-ER-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO3 Cell 4 - ER | Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER | 0
CHI05-03-04-DH-1440 | CHI05-03-04-DH-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 4 - DH | Ceiling Grid and Tile - COLO3 Cell 4 - DH | 0
CHI05-03-04-DH-1480 | CHI05-03-04-DH-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Ceiling Grid and Tile - COLO3 Cell 4 - DH | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 4 - DH | 0
CHI05-03-04-DH-1500 | CHI05-03-04-DH-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 4 - DH | Install PDU's - COLO3 Cell 4 - DH | 0
CHI05-03-04-DH-1490 | CHI05-03-04-DH-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Install PDU's - COLO3 Cell 4 - DH | Termination at PDU & Busway - COLO3 Cell 4 - DH | 0
CHI05-03-04-DH-1450 | CHI05-03-04-DH-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | HAC install and Rise - COLO3 Cell 4 - DH | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH | 0
CHI05-03-04-DH-1440 | CHI05-03-04-DH-1470 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 4 - DH | Security Screen Installation - COLO3 Cell 4 - DH | 6
CHI05-03-04-DH-1470 | CHI05-03-04-DH-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Security Screen Installation - COLO3 Cell 4 - DH | Ceiling Grid and Tile - COLO3 Cell 4 - DH | 0
CHI05-03-04-DH-1490 | CHI05-03-04-DH-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Install PDU's - COLO3 Cell 4 - DH | HAC install and Rise - COLO3 Cell 4 - DH | 0
CHI05-03-04-ER-1460 | CHI05-03-04-DH-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Install Upper Screens - COLO3 Cell 4 - ER | Security Screen Installation - COLO3 Cell 4 - DH | 0
CHI05-03-04-MG-1440 | CHI05-03-04-MG-1450 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 4 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 4 - MG | 2
CHI05-03-04-MG-1440 | CHI05-03-04-MG-1450 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 4 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 4 - MG | 0
CHI05-03-04-ER-1440 | CHI05-03-04-ER-1460 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO3 Cell 4 - ER | Install Upper Screens - COLO3 Cell 4 - ER | 2
CHI05-03-04-ER-1490 | CHI05-03-04-ER-1510 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Installation of ADP & ATS - COLO3 Cell 4 - ER | Connet to Cable tray and conduit equipment - COLO3 Cell 4 - ER | 2
CHI05-03-04-DH-1520 | CHI05-03-04-DH-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | HAC Placing - COLO3 Cell 4 - DH | HAC install and Rise - COLO3 Cell 4 - DH | 0
CHI05-03-04-DH-1500 | CHI05-03-04-DH-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 4 - DH | HAC Placing - COLO3 Cell 4 - DH | 0
CHI05-03-04-DH-1430 | CHI05-03-04-DH-1530 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Termination at PDU & Busway - COLO3 Cell 4 - DH | Finishes and Signage - COLO3 Cell 4 - DH | 0
CHI05-03-04-ER-1500 | CHI05-03-04-ER-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Installation of UPS Equipment - COLO3 Cell 4 - ER | Door Frame Installation - COLO3 Cell 4 - ER | 0
CHI05-03-04-ER-1520 | CHI05-03-04-ER-1540 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER | Finishes and Signage - COLO3 Cell 4 - ER | 2
CHI05-03-04-ER-1530 | CHI05-03-04-ER-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Door Frame Installation - COLO3 Cell 4 - ER | Finishes and Signage - COLO3 Cell 4 - ER | 0
CHI05-03-04-L1-1620 | CHI05-03-04-L1-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Interior - L1 UPS - COLO3 Cell 4 | Interior - L1 MSB - COLO3 Cell 4 | 0
CHI05-03-04-L1-1630 | CHI05-03-04-L1-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Interior - L1 MSB - COLO3 Cell 4 | Interior - L1 ADP - COLO3 Cell 4 | 0
CHI05-03-04-L1-1630 | CHI05-03-04-L1-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Interior - L1 MSB - COLO3 Cell 4 | Interior - L1 PDUs - COLO3 Cell 4 | 0
CHI05-03-04-L1-1730 | CHI05-03-04-L1-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Interior - L1 ADP - COLO3 Cell 4 | Interior - L1 ATSs - COLO3 Cell 4 | 0
CHI05-03-04-L1-1660 | CHI05-03-04-L1-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Interior - L1 ATSs - COLO3 Cell 4 | Interior - L1 AHUs - COLO3 Cell 4 | 0
CHI05-03-04-L1-1640 | CHI05-03-04-L1-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Interior - L1 PDUs - COLO3 Cell 4 | Interior - L1 Busway - COLO3 Cell 4 | 0
CHI05-03-04-L2-1740 | CHI05-03-04-L2-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L2 UPS - COLO3 Cell 4 | Interior - L2 MSB - COLO3 Cell 4 | 0
CHI05-03-04-L2-1750 | CHI05-03-04-L2-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L2 MSB - COLO3 Cell 4 | Interior - L2 ADP - COLO3 Cell 4 | 0
CHI05-03-04-L2-1750 | CHI05-03-04-L2-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L2 MSB - COLO3 Cell 4 | Interior - L2 PDUs - COLO3 Cell 4 | 0
CHI05-03-04-L2-1850 | CHI05-03-04-L2-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L2 ADP - COLO3 Cell 4 | Interior - L2 ATSs - COLO3 Cell 4 | 0
CHI05-03-04-L2-1780 | CHI05-03-04-L2-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L2 ATSs - COLO3 Cell 4 | Interior - L2 AHUs - COLO3 Cell 4 | 0
CHI05-03-04-L2-1760 | CHI05-03-04-L2-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L2 PDUs - COLO3 Cell 4 | Interior - L2 Busway - COLO3 Cell 4 | 0
CHI05-03-04-L3-1860 | CHI05-03-04-L3-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L3 UPS - COLO3 Cell 4 | Interior - L3 MSB - COLO3 Cell 4 | 0
CHI05-03-04-L3-1870 | CHI05-03-04-L3-1970 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L3 MSB - COLO3 Cell 4 | Interior - L3 ADP - COLO3 Cell 4 | 0
CHI05-03-04-L3-1870 | CHI05-03-04-L3-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L3 MSB - COLO3 Cell 4 | Interior - L3 PDUs - COLO3 Cell 4 | 0
CHI05-03-04-L3-1970 | CHI05-03-04-L3-1900 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L3 ADP - COLO3 Cell 4 | Interior - L3 ATSs - COLO3 Cell 4 | 0
CHI05-03-04-L3-1900 | CHI05-03-04-L3-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L3 ATSs - COLO3 Cell 4 | Interior - L3 AHUs - COLO3 Cell 4 | 0
CHI05-03-04-L3-1880 | CHI05-03-04-L3-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L3 PDUs - COLO3 Cell 4 | Interior - L3 Busway - COLO3 Cell 4 | 0
CHI05-03-04-L1-1620 | CHI05-03-04-L2-1740 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L1 UPS - COLO3 Cell 4 | Interior - L2 UPS - COLO3 Cell 4 | 0
CHI05-03-04-L2-1740 | CHI05-03-04-L3-1860 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L2 UPS - COLO3 Cell 4 | Interior - L3 UPS - COLO3 Cell 4 | 0
CHI05-03-04-DH-1490 | CHI05-03-04-DH-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Install PDU's - COLO3 Cell 4 - DH | Cable Pulling at PDU & Busway- COLO3 Cell 4 - DH | 0
CHI05-03-04-DH-1460 | CHI05-03-04-DH-1430 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Cable Pulling at PDU & Busway- COLO3 Cell 4 - DH | Termination at PDU & Busway - COLO3 Cell 4 - DH | 0
CHI05-03-04-MG-1490 | CHI05-03-04-L1-1650 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Placing the AHU - COLO3 Cell 4 - MG | Interior - L1 AHUs - COLO3 Cell 4 | 0
CHI05-03-01-MG-1110 | CHI05-03-01-ER-1110 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 1 - MG | Install Walls and Primer Paint - COLO3 Cell 1 - ER | 0
CHI05-03-01-ER-1110 | CHI05-03-01-DH-1110 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Install Walls and Primer Paint - COLO3 Cell 1 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 1 - DH | 0
CHI05-03-02-MG-1220 | CHI05-03-02-ER-1220 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 2 - MG | Install Walls and Primer Paint - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1220 | CHI05-03-02-DH-1220 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Install Walls and Primer Paint - COLO3 Cell 2 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 2 - DH | 0
CHI05-03-03-MG-1330 | CHI05-03-03-ER-1330 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 3 - MG | Install Walls and Primer Paint - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1330 | CHI05-03-03-DH-1330 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Install Walls and Primer Paint - COLO3 Cell 3 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 3 - DH | 0
CHI05-03-04-MG-1440 | CHI05-03-04-ER-1440 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 4 - MG | Install Walls and Primer Paint - COLO3 Cell 4 - ER | 0
CHI05-03-04-ER-1440 | CHI05-03-04-DH-1440 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Install Walls and Primer Paint - COLO3 Cell 4 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 4 - DH | 0
CHI05-03-03-MG-1330 | CHI05-03-04-MG-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 3 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 4 - MG | 0
CHI05-03-02-MG-1220 | CHI05-03-03-MG-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 2 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 3 - MG | 0
CHI05-03-01-MG-1110 | CHI05-03-02-MG-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 1 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 2 - MG | 0
CHI05-03-04-L3-1890 | CHI05-03-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,5,1 Level 4 Cx - Colo 3 | Interior - L3 AHUs - COLO3 Cell 4 | Cx LEV4 - COLO3 | 0
CHI05-03-02-L3-1650 | CHI05-03-04-L4-1000 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,5,1 Level 4 Cx - Colo 3 | Interior - L3 AHUs - COLO3 Cell 2 | Cx LEV4 - COLO3 | 2
CHI05-03-03-L3-1770 | CHI05-03-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,5,1 Level 4 Cx - Colo 3 | Interior - L3 AHUs - COLO3 Cell 3 | Cx LEV4 - COLO3 | 0
CHI05-04-04-L4-1000 | CHI05-04-04-L5-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 Level 4 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,5,2 Level 5 Cx / IST - Colo 4 | Cx LEV4 - COLO4 | Cx LEV5 / IST - COLO4 | 0
CHI05-04-01-MG-1240 | CHI05-04-01-MG-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Overhead MEP Installation - COLO4 Cell 1 - MG | Deliver AHU into Mech. Gallery - COLO4 Cell 1 - MG | 0
CHI05-04-01-MG-1250 | CHI05-04-01-MG-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO4 Cell 1 - MG | Install Walls and Primer Paint - COLO4 Cell 1 - MG | 0
CHI05-04-01-MG-1260 | CHI05-04-01-MG-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Install Walls and Primer Paint - COLO4 Cell 1 - MG | Layout Ceiling and install Pencile Rod - COLO4 Cell 1 - MG | 0
CHI05-04-01-MG-1280 | CHI05-04-01-MG-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO4 Cell 1 - MG | Placing the AHU - COLO4 Cell 1 - MG | 0
CHI05-04-01-MG-1270 | CHI05-04-01-MG-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Placing the AHU - COLO4 Cell 1 - MG | Piping and Electrical Termination to AHUs - COLO4 Cell 1 - MG | 0
CHI05-04-01-MG-1290 | CHI05-04-01-MG-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO4 Cell 1 - MG | Pipe Testing - COLO4 Cell 1 - MG | 0
CHI05-04-01-MG-1300 | CHI05-04-01-MG-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Pipe Testing - COLO4 Cell 1 - MG | Install ceiling and Light Fittings - COLO4 Cell 1 - MG | 0
CHI05-04-01-MG-1310 | CHI05-04-01-MG-1320 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Install ceiling and Light Fittings - COLO4 Cell 1 - MG | Trim out MEP - COLO4 Cell 1 - MG | 0
CHI05-04-01-MG-1230 | CHI05-04-01-MG-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 1 - MG | Overhead MEP Installation - COLO4 Cell 1 - MG | 0
CHI05-04-01-ER-1240 | CHI05-04-01-ER-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Install Upper Screens - COLO4 Cell 1 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 1 - ER | 0
CHI05-04-01-ER-1230 | CHI05-04-01-ER-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 1 - ER | Install Ceiling - COLO4 Cell 1 - ER | 0
CHI05-04-01-ER-1250 | CHI05-04-01-ER-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Install Ceiling - COLO4 Cell 1 - ER | Below Ceiling MEP Rough In - COLO4 Cell 1 - ER | 0
CHI05-04-01-ER-1260 | CHI05-04-01-ER-1270 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 1 - ER | Installation of ADP & ATS - COLO4 Cell 1 - ER | 2
CHI05-04-01-ER-1290 | CHI05-04-01-ER-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO4 Cell 1 - ER | Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER | 0
CHI05-04-01-DH-1220 | CHI05-04-01-DH-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 1 - DH | Ceiling Grid and Tile - COLO4 Cell 1 - DH | 0
CHI05-04-01-DH-1260 | CHI05-04-01-DH-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Ceiling Grid and Tile - COLO4 Cell 1 - DH | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 1 - DH | 0
CHI05-04-01-DH-1280 | CHI05-04-01-DH-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 1 - DH | Install PDU's - COLO4 Cell 1 - DH | 0
CHI05-04-01-DH-1270 | CHI05-04-01-DH-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Install PDU's - COLO4 Cell 1 - DH | Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH | 0
CHI05-04-01-DH-1230 | CHI05-04-01-DH-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | HAC install and Rise - COLO4 Cell 1 - DH | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH | 0
CHI05-04-01-DH-1220 | CHI05-04-01-DH-1250 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 1 - DH | Security Screen Installation - COLO4 Cell 1 - DH | 6
CHI05-04-01-DH-1250 | CHI05-04-01-DH-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Security Screen Installation - COLO4 Cell 1 - DH | Ceiling Grid and Tile - COLO4 Cell 1 - DH | 0
CHI05-04-01-DH-1270 | CHI05-04-01-DH-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Install PDU's - COLO4 Cell 1 - DH | HAC install and Rise - COLO4 Cell 1 - DH | 0
CHI05-04-01-ER-1240 | CHI05-04-01-DH-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Install Upper Screens - COLO4 Cell 1 - ER | Security Screen Installation - COLO4 Cell 1 - DH | 0
CHI05-04-01-MG-1220 | CHI05-04-01-MG-1230 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 1 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 1 - MG | 1
CHI05-04-01-MG-1220 | CHI05-04-01-MG-1230 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 1 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 1 - MG | 0
CHI05-04-01-ER-1220 | CHI05-04-01-ER-1240 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO4 Cell 1 - ER | Install Upper Screens - COLO4 Cell 1 - ER | 0
CHI05-04-01-ER-1270 | CHI05-04-01-ER-1290 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Installation of ADP & ATS - COLO4 Cell 1 - ER | Connet to Cable tray and conduit equipment - COLO4 Cell 1 - ER | 2
CHI05-04-01-DH-1300 | CHI05-04-01-DH-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | HAC Placing - COLO4 Cell 1 - DH | HAC install and Rise - COLO4 Cell 1 - DH | 0
CHI05-04-01-DH-1280 | CHI05-04-01-DH-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 1 - DH | HAC Placing - COLO4 Cell 1 - DH | 0
CHI05-04-01-DH-1210 | CHI05-04-01-DH-1310 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH | Finishes and Signage - COLO4 Cell 1 - DH | 0
CHI05-04-01-ER-1280 | CHI05-04-01-ER-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Installation of UPS Equipment - COLO4 Cell 1 - ER | Door Frame Installation - COLO4 Cell 1 - ER | 0
CHI05-04-01-ER-1300 | CHI05-04-01-ER-1320 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER | Finishes and Signage - COLO4 Cell 1 - ER | 2
CHI05-04-01-ER-1310 | CHI05-04-01-ER-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Door Frame Installation - COLO4 Cell 1 - ER | Finishes and Signage - COLO4 Cell 1 - ER | 0
CHI05-04-01-L1-1470 | CHI05-04-01-L1-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | L1 XFMR - MV- COLO4 | Interior - L1 MSB - COLO4 Cell 1 | 0
CHI05-04-01-L1-1380 | CHI05-04-01-L1-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Interior - L1 UPS - COLO4 Cell 1 | Interior - L1 MSB - COLO4 Cell 1 | 0
CHI05-04-01-L1-1390 | CHI05-04-01-L1-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Interior - L1 MSB - COLO4 Cell 1 | Interior - L1 ADP - COLO4 Cell 1 | 0
CHI05-04-01-L1-1390 | CHI05-04-01-L1-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Interior - L1 MSB - COLO4 Cell 1 | Interior - L1 PDUs - COLO4 Cell 1 | 0
CHI05-04-01-L1-1490 | CHI05-04-01-L1-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Interior - L1 ADP - COLO4 Cell 1 | Interior - L1 ATSs - COLO4 Cell 1 | 0
CHI05-04-01-L1-1420 | CHI05-04-01-L1-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Interior - L1 ATSs - COLO4 Cell 1 | Interior - L1 AHUs - COLO4 Cell 1 | 0
CHI05-04-01-L1-1400 | CHI05-04-01-L1-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Interior - L1 PDUs - COLO4 Cell 1 | Interior - L1 Busway - COLO4 Cell 1 | 0
CHI05-04-01-L1-1480 | CHI05-04-01-L1-1390 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | L1 GEN - COLO4 | Interior - L1 MSB - COLO4 Cell 1 | 0
CHI05-04-01-L2-1580 | CHI05-04-01-L2-1590 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UPM - COLO4 | L2 XFMR - COLO4 | 0
CHI05-04-01-L2-1590 | CHI05-04-01-L2-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | L2 XFMR - COLO4 | Interior - L2 MSB - COLO4 Cell 1 | 0
CHI05-04-01-L2-1500 | CHI05-04-01-L2-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L2 UPS - COLO4 Cell 1 | Interior - L2 MSB - COLO4 Cell 1 | 0
CHI05-04-01-L2-1510 | CHI05-04-01-L2-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L2 MSB - COLO4 Cell 1 | Interior - L2 ADP - COLO4 Cell 1 | 0
CHI05-04-01-L2-1510 | CHI05-04-01-L2-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L2 MSB - COLO4 Cell 1 | Interior - L2 PDUs - COLO4 Cell 1 | 0
CHI05-04-01-L2-1610 | CHI05-04-01-L2-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L2 ADP - COLO4 Cell 1 | Interior - L2 ATSs - COLO4 Cell 1 | 0
CHI05-04-01-L2-1540 | CHI05-04-01-L2-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L2 ATSs - COLO4 Cell 1 | Interior - L2 AHUs - COLO4 Cell 1 | 0
CHI05-04-01-L2-1520 | CHI05-04-01-L2-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L2 PDUs - COLO4 Cell 1 | Interior - L2 Busway - COLO4 Cell 1 | 0
CHI05-04-01-L2-1600 | CHI05-04-01-L2-1510 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | L2 GEN - COLO4 | Interior - L2 MSB - COLO4 Cell 1 | 0
CHI05-04-01-L3-1700 | CHI05-04-01-L3-1710 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UPM - COLO4 | L3 XFMR - COLO4 | 0
CHI05-04-01-L3-1710 | CHI05-04-01-L3-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | L3 XFMR - COLO4 | Interior - L3 MSB - COLO4 Cell 1 | 0
CHI05-04-01-L3-1620 | CHI05-04-01-L3-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L3 UPS - COLO4 Cell 1 | Interior - L3 MSB - COLO4 Cell 1 | 0
CHI05-04-01-L3-1630 | CHI05-04-01-L3-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L3 MSB - COLO4 Cell 1 | Interior - L3 ADP - COLO4 Cell 1 | 0
CHI05-04-01-L3-1630 | CHI05-04-01-L3-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L3 MSB - COLO4 Cell 1 | Interior - L3 PDUs - COLO4 Cell 1 | 0
CHI05-04-01-L3-1730 | CHI05-04-01-L3-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L3 ADP - COLO4 Cell 1 | Interior - L3 ATSs - COLO4 Cell 1 | 0
CHI05-04-01-L3-1660 | CHI05-04-01-L3-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L3 ATSs - COLO4 Cell 1 | Interior - L3 AHUs - COLO4 Cell 1 | 0
CHI05-04-01-L1-1380 | CHI05-04-01-L2-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L1 UPS - COLO4 Cell 1 | Interior - L2 UPS - COLO4 Cell 1 | 0
CHI05-04-01-L2-1500 | CHI05-04-01-L3-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L2 UPS - COLO4 Cell 1 | Interior - L3 UPS - COLO4 Cell 1 | 0
CHI05-04-01-DH-1270 | CHI05-04-01-DH-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Install PDU's - COLO4 Cell 1 - DH | Termination at PDU & Busway- COLO4 Cell 1 - DH | 0
CHI05-04-01-DH-1240 | CHI05-04-01-DH-1210 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Termination at PDU & Busway- COLO4 Cell 1 - DH | Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH | 0
CHI05-04-01-MG-1270 | CHI05-04-01-L1-1410 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Placing the AHU - COLO4 Cell 1 - MG | Interior - L1 AHUs - COLO4 Cell 1 | 0
CHI05-04-01-L1-1480 | CHI05-04-01-L2-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L1 GEN - COLO4 | L2 GEN - COLO4 | 0
CHI05-04-01-L2-1600 | CHI05-04-01-L3-1720 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L2 GEN - COLO4 | L3 GEN - COLO4 | 0
CHI05-04-01-L3-1650 | CHI05-04-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 Level 4 Cx - Colo 4 | Interior - L3 AHUs - COLO4 Cell 1 | Cx LEV4 - COLO4 | 0
CHI05-04-02-MG-1350 | CHI05-04-02-MG-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Overhead MEP Installation - COLO4 Cell 2 - MG | Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1360 | CHI05-04-02-MG-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG | Install Walls and Primer Paint - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1370 | CHI05-04-02-MG-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Install Walls and Primer Paint - COLO4 Cell 2 - MG | Layout Ceiling and install Pencile Rod - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1390 | CHI05-04-02-MG-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO4 Cell 2 - MG | Placing the AHU - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1380 | CHI05-04-02-MG-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Placing the AHU - COLO4 Cell 2 - MG | Piping and Electrical Termination to AHUs - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1400 | CHI05-04-02-MG-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO4 Cell 2 - MG | Pipe Testing - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1410 | CHI05-04-02-MG-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Pipe Testing - COLO4 Cell 2 - MG | Install ceiling and Light Fittings - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1420 | CHI05-04-02-MG-1430 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Install ceiling and Light Fittings - COLO4 Cell 2 - MG | Trim out MEP - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1340 | CHI05-04-02-MG-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 2 - MG | Overhead MEP Installation - COLO4 Cell 2 - MG | 0
CHI05-04-02-ER-1350 | CHI05-04-02-ER-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Install Upper Screens - COLO4 Cell 2 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1340 | CHI05-04-02-ER-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 2 - ER | Install Ceiling - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1360 | CHI05-04-02-ER-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Install Ceiling - COLO4 Cell 2 - ER | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1370 | CHI05-04-02-ER-1380 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | Installation of ADP & ATS - COLO4 Cell 2 - ER | 2
CHI05-04-02-ER-1400 | CHI05-04-02-ER-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO4 Cell 2 - ER | Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER | 0
CHI05-04-02-DH-1330 | CHI05-04-02-DH-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH | Ceiling Grid and Tile - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1370 | CHI05-04-02-DH-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Ceiling Grid and Tile - COLO4 Cell 2 - DH | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1390 | CHI05-04-02-DH-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH | Install PDU's - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1380 | CHI05-04-02-DH-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Install PDU's - COLO4 Cell 2 - DH | Termination at PDU & Busway - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1340 | CHI05-04-02-DH-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | HAC install and Rise - COLO4 Cell 2 - DH | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1330 | CHI05-04-02-DH-1360 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH | Security Screen Installation - COLO4 Cell 2 - DH | 6
CHI05-04-02-DH-1360 | CHI05-04-02-DH-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Security Screen Installation - COLO4 Cell 2 - DH | Ceiling Grid and Tile - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1380 | CHI05-04-02-DH-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Install PDU's - COLO4 Cell 2 - DH | HAC install and Rise - COLO4 Cell 2 - DH | 0
CHI05-04-02-ER-1350 | CHI05-04-02-DH-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Install Upper Screens - COLO4 Cell 2 - ER | Security Screen Installation - COLO4 Cell 2 - DH | 0
CHI05-04-02-MG-1330 | CHI05-04-02-MG-1340 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 2 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 2 - MG | 2
CHI05-04-02-MG-1330 | CHI05-04-02-MG-1340 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 2 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 2 - MG | 0
CHI05-04-02-ER-1330 | CHI05-04-02-ER-1350 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO4 Cell 2 - ER | Install Upper Screens - COLO4 Cell 2 - ER | 2
CHI05-04-02-ER-1380 | CHI05-04-02-ER-1400 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Installation of ADP & ATS - COLO4 Cell 2 - ER | Connet to Cable tray and conduit equipment - COLO4 Cell 2 - ER | 2
CHI05-04-02-DH-1410 | CHI05-04-02-DH-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | HAC Placing - COLO4 Cell 2 - DH | HAC install and Rise - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1390 | CHI05-04-02-DH-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH | HAC Placing - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1320 | CHI05-04-02-DH-1420 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Termination at PDU & Busway - COLO4 Cell 2 - DH | Finishes and Signage - COLO4 Cell 2 - DH | 0
CHI05-04-02-ER-1390 | CHI05-04-02-ER-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Installation of UPS Equipment - COLO4 Cell 2 - ER | Door Frame Installation - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1410 | CHI05-04-02-ER-1430 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER | Finishes and Signage - COLO4 Cell 2 - ER | 2
CHI05-04-02-ER-1420 | CHI05-04-02-ER-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Door Frame Installation - COLO4 Cell 2 - ER | Finishes and Signage - COLO4 Cell 2 - ER | 0
CHI05-04-02-L1-1500 | CHI05-04-02-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Interior - L1 UPS - COLO4 Cell 2 | Interior - L1 MSB - COLO4 Cell 2 | 0
CHI05-04-02-L1-1510 | CHI05-04-02-L1-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Interior - L1 MSB - COLO4 Cell 2 | Interior - L1 ADP - COLO4 Cell 2 | 0
CHI05-04-02-L1-1510 | CHI05-04-02-L1-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Interior - L1 MSB - COLO4 Cell 2 | Interior - L1 PDUs - COLO4 Cell 2 | 0
CHI05-04-02-L1-1610 | CHI05-04-02-L1-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Interior - L1 ADP - COLO4 Cell 2 | Interior - L1 ATSs - COLO4 Cell 2 | 0
CHI05-04-02-L1-1540 | CHI05-04-02-L1-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Interior - L1 ATSs - COLO4 Cell 2 | Interior - L1 AHUs - COLO4 Cell 2 | 0
CHI05-04-02-L1-1520 | CHI05-04-02-L1-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Interior - L1 PDUs - COLO4 Cell 2 | Interior - L1 Busway - COLO4 Cell 2 | 0
CHI05-04-02-L2-1620 | CHI05-04-02-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L2 UPS - COLO4 Cell 2 | Interior - L2 MSB - COLO4 Cell 2 | 0
CHI05-04-02-L2-1630 | CHI05-04-02-L2-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L2 MSB - COLO4 Cell 2 | Interior - L2 ADP - COLO4 Cell 2 | 0
CHI05-04-02-L2-1630 | CHI05-04-02-L2-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L2 MSB - COLO4 Cell 2 | Interior - L2 PDUs - COLO4 Cell 2 | 0
CHI05-04-02-L2-1730 | CHI05-04-02-L2-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L2 ADP - COLO4 Cell 2 | Interior - L2 ATSs - COLO4 Cell 2 | 0
CHI05-04-02-L2-1660 | CHI05-04-02-L2-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L2 ATSs - COLO4 Cell 2 | Interior - L2 AHUs - COLO4 Cell 2 | 0
CHI05-04-02-L2-1640 | CHI05-04-02-L2-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L2 PDUs - COLO4 Cell 2 | Interior - L2 Busway - COLO4 Cell 2 | 0
CHI05-04-02-L3-1740 | CHI05-04-02-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L3 UPS - COLO4 Cell 2 | Interior - L3 MSB - COLO4 Cell 2 | 0
CHI05-04-02-L3-1750 | CHI05-04-02-L3-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L3 MSB - COLO4 Cell 2 | Interior - L3 ADP - COLO4 Cell 2 | 0
CHI05-04-02-L3-1750 | CHI05-04-02-L3-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L3 MSB - COLO4 Cell 2 | Interior - L3 PDUs - COLO4 Cell 2 | 0
CHI05-04-02-L3-1850 | CHI05-04-02-L3-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L3 ADP - COLO4 Cell 2 | Interior - L3 ATSs - COLO4 Cell 2 | 0
CHI05-04-02-L3-1780 | CHI05-04-02-L3-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L3 ATSs - COLO4 Cell 2 | Interior - L3 AHUs - COLO4 Cell 2 | 0
CHI05-04-02-L3-1760 | CHI05-04-02-L3-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L3 PDUs - COLO4 Cell 2 | Interior - L3 Busway - COLO4 Cell 2 | 0
CHI05-04-02-L1-1500 | CHI05-04-02-L2-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L1 UPS - COLO4 Cell 2 | Interior - L2 UPS - COLO4 Cell 2 | 0
CHI05-04-02-L2-1620 | CHI05-04-02-L3-1740 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L2 UPS - COLO4 Cell 2 | Interior - L3 UPS - COLO4 Cell 2 | 0
CHI05-04-02-DH-1380 | CHI05-04-02-DH-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Install PDU's - COLO4 Cell 2 - DH | Cable Pulling at PDU & Busway- COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1350 | CHI05-04-02-DH-1320 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Cable Pulling at PDU & Busway- COLO4 Cell 2 - DH | Termination at PDU & Busway - COLO4 Cell 2 - DH | 0
CHI05-04-02-MG-1380 | CHI05-04-02-L1-1530 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Placing the AHU - COLO4 Cell 2 - MG | Interior - L1 AHUs - COLO4 Cell 2 | 0
CHI05-04-03-MG-1460 | CHI05-04-03-MG-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Overhead MEP Installation - COLO4 Cell 3 - MG | Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1470 | CHI05-04-03-MG-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG | Install Walls and Primer Paint - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1480 | CHI05-04-03-MG-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Install Walls and Primer Paint - COLO4 Cell 3 - MG | Layout Ceiling and install Pencile Rod - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1500 | CHI05-04-03-MG-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO4 Cell 3 - MG | Placing the AHU - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1490 | CHI05-04-03-MG-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Placing the AHU - COLO4 Cell 3 - MG | Piping and Electrical Termination to AHUs - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1510 | CHI05-04-03-MG-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO4 Cell 3 - MG | Pipe Testing - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1520 | CHI05-04-03-MG-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Pipe Testing - COLO4 Cell 3 - MG | Install ceiling and Light Fittings - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1530 | CHI05-04-03-MG-1540 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Install ceiling and Light Fittings - COLO4 Cell 3 - MG | Trim out MEP - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1450 | CHI05-04-03-MG-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 3 - MG | Overhead MEP Installation - COLO4 Cell 3 - MG | 0
CHI05-04-03-ER-1460 | CHI05-04-03-ER-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Install Upper Screens - COLO4 Cell 3 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1450 | CHI05-04-03-ER-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 3 - ER | Install Ceiling - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1470 | CHI05-04-03-ER-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Install Ceiling - COLO4 Cell 3 - ER | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1480 | CHI05-04-03-ER-1490 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | Installation of ADP & ATS - COLO4 Cell 3 - ER | 2
CHI05-04-03-ER-1510 | CHI05-04-03-ER-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO4 Cell 3 - ER | Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER | 0
CHI05-04-03-DH-1440 | CHI05-04-03-DH-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH | Ceiling Grid and Tile - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1480 | CHI05-04-03-DH-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Ceiling Grid and Tile - COLO4 Cell 3 - DH | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1500 | CHI05-04-03-DH-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH | Install PDU's - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1490 | CHI05-04-03-DH-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Install PDU's - COLO4 Cell 3 - DH | Termination at PDU & Busway - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1450 | CHI05-04-03-DH-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | HAC install and Rise - COLO4 Cell 3 - DH | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1440 | CHI05-04-03-DH-1470 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH | Security Screen Installation - COLO4 Cell 3 - DH | 6
CHI05-04-03-DH-1470 | CHI05-04-03-DH-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Security Screen Installation - COLO4 Cell 3 - DH | Ceiling Grid and Tile - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1490 | CHI05-04-03-DH-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Install PDU's - COLO4 Cell 3 - DH | HAC install and Rise - COLO4 Cell 3 - DH | 0
CHI05-04-03-ER-1460 | CHI05-04-03-DH-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Install Upper Screens - COLO4 Cell 3 - ER | Security Screen Installation - COLO4 Cell 3 - DH | 0
CHI05-04-03-MG-1440 | CHI05-04-03-MG-1450 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 3 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 3 - MG | 2
CHI05-04-03-MG-1440 | CHI05-04-03-MG-1450 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 3 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 3 - MG | 0
CHI05-04-03-ER-1440 | CHI05-04-03-ER-1460 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO4 Cell 3 - ER | Install Upper Screens - COLO4 Cell 3 - ER | 2
CHI05-04-03-ER-1490 | CHI05-04-03-ER-1510 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Installation of ADP & ATS - COLO4 Cell 3 - ER | Connet to Cable tray and conduit equipment - COLO4 Cell 3 - ER | 2
CHI05-04-03-DH-1520 | CHI05-04-03-DH-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | HAC Placing - COLO4 Cell 3 - DH | HAC install and Rise - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1500 | CHI05-04-03-DH-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH | HAC Placing - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1430 | CHI05-04-03-DH-1530 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Termination at PDU & Busway - COLO4 Cell 3 - DH | Finishes and Signage - COLO4 Cell 3 - DH | 0
CHI05-04-03-ER-1500 | CHI05-04-03-ER-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Installation of UPS Equipment - COLO4 Cell 3 - ER | Door Frame Installation - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1520 | CHI05-04-03-ER-1540 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER | Finishes and Signage - COLO4 Cell 3 - ER | 2
CHI05-04-03-ER-1530 | CHI05-04-03-ER-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Door Frame Installation - COLO4 Cell 3 - ER | Finishes and Signage - COLO4 Cell 3 - ER | 0
CHI05-04-03-L1-1620 | CHI05-04-03-L1-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Interior - L1 UPS - COLO4 Cell 3 | Interior - L1 MSB - COLO4 Cell 3 | 0
CHI05-04-03-L1-1630 | CHI05-04-03-L1-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Interior - L1 MSB - COLO4 Cell 3 | Interior - L1 ADP - COLO4 Cell 3 | 0
CHI05-04-03-L1-1630 | CHI05-04-03-L1-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Interior - L1 MSB - COLO4 Cell 3 | Interior - L1 PDUs - COLO4 Cell 3 | 0
CHI05-04-03-L1-1730 | CHI05-04-03-L1-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Interior - L1 ADP - COLO4 Cell 3 | Interior - L1 ATSs - COLO4 Cell 3 | 0
CHI05-04-03-L1-1660 | CHI05-04-03-L1-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Interior - L1 ATSs - COLO4 Cell 3 | Interior - L1 AHUs - COLO4 Cell 3 | 0
CHI05-04-03-L1-1640 | CHI05-04-03-L1-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Interior - L1 PDUs - COLO4 Cell 3 | Interior - L1 Busway - COLO4 Cell 3 | 0
CHI05-04-03-L2-1740 | CHI05-04-03-L2-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L2 UPS - COLO4 Cell 3 | Interior - L2 MSB - COLO4 Cell 3 | 0
CHI05-04-03-L2-1750 | CHI05-04-03-L2-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L2 MSB - COLO4 Cell 3 | Interior - L2 ADP - COLO4 Cell 3 | 0
CHI05-04-03-L2-1750 | CHI05-04-03-L2-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L2 MSB - COLO4 Cell 3 | Interior - L2 PDUs - COLO4 Cell 3 | 0
CHI05-04-03-L2-1850 | CHI05-04-03-L2-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L2 ADP - COLO4 Cell 3 | Interior - L2 ATSs - COLO4 Cell 3 | 0
CHI05-04-03-L2-1780 | CHI05-04-03-L2-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L2 ATSs - COLO4 Cell 3 | Interior - L2 AHUs - COLO4 Cell 3 | 0
CHI05-04-03-L2-1760 | CHI05-04-03-L2-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L2 PDUs - COLO4 Cell 3 | Interior - L2 Busway - COLO4 Cell 3 | 0
CHI05-04-03-L3-1860 | CHI05-04-03-L3-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L3 UPS - COLO4 Cell 3 | Interior - L3 MSB - COLO4 Cell 3 | 0
CHI05-04-03-L3-1870 | CHI05-04-03-L3-1970 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L3 MSB - COLO4 Cell 3 | Interior - L3 ADP - COLO4 Cell 3 | 0
CHI05-04-03-L3-1870 | CHI05-04-03-L3-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L3 MSB - COLO4 Cell 3 | Interior - L3 PDUs - COLO4 Cell 3 | 0
CHI05-04-03-L3-1970 | CHI05-04-03-L3-1900 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L3 ADP - COLO4 Cell 3 | Interior - L3 ATSs - COLO4 Cell 3 | 0
CHI05-04-03-L3-1880 | CHI05-04-03-L3-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L3 PDUs - COLO4 Cell 3 | Interior - L3 Busway - COLO4 Cell 3 | 0
CHI05-04-03-L1-1620 | CHI05-04-03-L2-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L1 UPS - COLO4 Cell 3 | Interior - L2 UPS - COLO4 Cell 3 | 0
CHI05-04-03-L2-1740 | CHI05-04-03-L3-1860 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L2 UPS - COLO4 Cell 3 | Interior - L3 UPS - COLO4 Cell 3 | 0
CHI05-04-03-DH-1490 | CHI05-04-03-DH-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Install PDU's - COLO4 Cell 3 - DH | Cable Pulling at PDU & Busway- COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1460 | CHI05-04-03-DH-1430 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Cable Pulling at PDU & Busway- COLO4 Cell 3 - DH | Termination at PDU & Busway - COLO4 Cell 3 - DH | 0
CHI05-04-03-MG-1490 | CHI05-04-03-L1-1650 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Placing the AHU - COLO4 Cell 3 - MG | Interior - L1 AHUs - COLO4 Cell 3 | 0
CHI05-04-04-MG-1570 | CHI05-04-04-MG-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Overhead MEP Installation - COLO4 Cell 4 - MG | Deliver AHU into Mech. Gallery - COLO4 Cell 4 - MG | 0
CHI05-04-04-MG-1580 | CHI05-04-04-MG-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO4 Cell 4 - MG | Install Walls and Primer Paint - COLO4 Cell 4 - MG | 0
CHI05-04-04-MG-1590 | CHI05-04-04-MG-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Install Walls and Primer Paint - COLO4 Cell 4 - MG | Layout Ceiling and install Pencile Rod - COLO4 Cell 4 - MG | 0
CHI05-04-04-MG-1610 | CHI05-04-04-MG-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO4 Cell 4 - MG | Placing the AHU - COLO4 Cell 4 - MG | 0
CHI05-04-04-MG-1600 | CHI05-04-04-MG-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Placing the AHU - COLO4 Cell 4 - MG | Piping and Electrical Termination to AHUs - COLO4 Cell 4 - MG | 0
CHI05-04-04-MG-1620 | CHI05-04-04-MG-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO4 Cell 4 - MG | Pipe Testing - COLO4 Cell 4 - MG | 0
CHI05-04-04-MG-1630 | CHI05-04-04-MG-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Pipe Testing - COLO4 Cell 4 - MG | Install ceiling and Light Fittings - COLO4 Cell 4 - MG | 0
CHI05-04-04-MG-1640 | CHI05-04-04-MG-1650 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Install ceiling and Light Fittings - COLO4 Cell 4 - MG | Trim out MEP - COLO4 Cell 4 - MG | 0
CHI05-04-04-MG-1560 | CHI05-04-04-MG-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG | Overhead MEP Installation - COLO4 Cell 4 - MG | 0
CHI05-04-04-ER-1570 | CHI05-04-04-ER-1560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Install Upper Screens - COLO4 Cell 4 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 4 - ER | 0
CHI05-04-04-ER-1560 | CHI05-04-04-ER-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 4 - ER | Install Ceiling - COLO4 Cell 4 - ER | 0
CHI05-04-04-ER-1580 | CHI05-04-04-ER-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Install Ceiling - COLO4 Cell 4 - ER | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | 0
CHI05-04-04-ER-1590 | CHI05-04-04-ER-1600 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | Installation of ADP & ATS - COLO4 Cell 4 - ER | 0
CHI05-04-04-ER-1620 | CHI05-04-04-ER-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO4 Cell 4 - ER | Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER | 0
CHI05-04-04-DH-1550 | CHI05-04-04-DH-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 4 - DH | Ceiling Grid and Tile - COLO4 Cell 4 - DH | 0
CHI05-04-04-DH-1590 | CHI05-04-04-DH-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Ceiling Grid and Tile - COLO4 Cell 4 - DH | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 4 - DH | 0
CHI05-04-04-DH-1610 | CHI05-04-04-DH-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 4 - DH | Install PDU's - COLO4 Cell 4 - DH | 0
CHI05-04-04-DH-1600 | CHI05-04-04-DH-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Install PDU's - COLO4 Cell 4 - DH | Termination at PDU & Busway - COLO4 Cell 4 - DH | 0
CHI05-04-04-DH-1560 | CHI05-04-04-DH-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | HAC install and Rise - COLO4 Cell 4 - DH | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH | 0
CHI05-04-04-DH-1550 | CHI05-04-04-DH-1580 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 4 - DH | Security Screen Installation - COLO4 Cell 4 - DH | 0
CHI05-04-04-DH-1580 | CHI05-04-04-DH-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Security Screen Installation - COLO4 Cell 4 - DH | Ceiling Grid and Tile - COLO4 Cell 4 - DH | 0
CHI05-04-04-DH-1600 | CHI05-04-04-DH-1560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Install PDU's - COLO4 Cell 4 - DH | HAC install and Rise - COLO4 Cell 4 - DH | 0
CHI05-04-04-ER-1570 | CHI05-04-04-DH-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Install Upper Screens - COLO4 Cell 4 - ER | Security Screen Installation - COLO4 Cell 4 - DH | 0
CHI05-04-04-MG-1550 | CHI05-04-04-MG-1560 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 4 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG | 2
CHI05-04-04-MG-1550 | CHI05-04-04-MG-1560 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 4 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG | 0
CHI05-04-04-ER-1550 | CHI05-04-04-ER-1570 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO4 Cell 4 - ER | Install Upper Screens - COLO4 Cell 4 - ER | 2
CHI05-04-04-ER-1600 | CHI05-04-04-ER-1620 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Installation of ADP & ATS - COLO4 Cell 4 - ER | Connet to Cable tray and conduit equipment - COLO4 Cell 4 - ER | 0
CHI05-04-04-DH-1630 | CHI05-04-04-DH-1560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | HAC Placing - COLO4 Cell 4 - DH | HAC install and Rise - COLO4 Cell 4 - DH | 0
CHI05-04-04-DH-1610 | CHI05-04-04-DH-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 4 - DH | HAC Placing - COLO4 Cell 4 - DH | 0
CHI05-04-04-DH-1540 | CHI05-04-04-DH-1640 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Termination at PDU & Busway - COLO4 Cell 4 - DH | Finishes and Signage - COLO4 Cell 4 - DH | 0
CHI05-04-04-ER-1610 | CHI05-04-04-ER-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Installation of UPS Equipment - COLO4 Cell 4 - ER | Door Frame Installation - COLO4 Cell 4 - ER | 0
CHI05-04-04-ER-1630 | CHI05-04-04-ER-1650 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER | Finishes and Signage - COLO4 Cell 4 - ER | 0
CHI05-04-04-ER-1640 | CHI05-04-04-ER-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Door Frame Installation - COLO4 Cell 4 - ER | Finishes and Signage - COLO4 Cell 4 - ER | 0
CHI05-04-04-L1-1740 | CHI05-04-04-L1-1750 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Interior - L1 UPS - COLO4 Cell 4 | Interior - L1 MSB - COLO4 Cell 4 | 0
CHI05-04-04-L1-1750 | CHI05-04-04-L1-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Interior - L1 MSB - COLO4 Cell 4 | Interior - L1 ADP - COLO4 Cell 4 | 0
CHI05-04-04-L1-1750 | CHI05-04-04-L1-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Interior - L1 MSB - COLO4 Cell 4 | Interior - L1 PDUs - COLO4 Cell 4 | 0
CHI05-04-04-L1-1850 | CHI05-04-04-L1-1780 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Interior - L1 ADP - COLO4 Cell 4 | Interior - L1 ATSs - COLO4 Cell 4 | 0
CHI05-04-04-L1-1780 | CHI05-04-04-L1-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Interior - L1 ATSs - COLO4 Cell 4 | Interior - L1 AHUs - COLO4 Cell 4 | 0
CHI05-04-04-L1-1760 | CHI05-04-04-L1-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Interior - L1 PDUs - COLO4 Cell 4 | Interior - L1 Busway - COLO4 Cell 4 | 0
CHI05-04-04-L2-1860 | CHI05-04-04-L2-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L2 UPS - COLO4 Cell 4 | Interior - L2 MSB - COLO4 Cell 4 | 0
CHI05-04-04-L2-1870 | CHI05-04-04-L2-1970 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L2 MSB - COLO4 Cell 4 | Interior - L2 ADP - COLO4 Cell 4 | 0
CHI05-04-04-L2-1870 | CHI05-04-04-L2-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L2 MSB - COLO4 Cell 4 | Interior - L2 PDUs - COLO4 Cell 4 | 0
CHI05-04-04-L2-1970 | CHI05-04-04-L2-1900 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L2 ADP - COLO4 Cell 4 | Interior - L2 ATSs - COLO4 Cell 4 | 0
CHI05-04-04-L2-1900 | CHI05-04-04-L2-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L2 ATSs - COLO4 Cell 4 | Interior - L2 AHUs - COLO4 Cell 4 | 0
CHI05-04-04-L2-1880 | CHI05-04-04-L2-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L2 PDUs - COLO4 Cell 4 | Interior - L2 Busway - COLO4 Cell 4 | 0
CHI05-04-04-L3-1980 | CHI05-04-04-L3-1990 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L3 UPS - COLO4 Cell 4 | Interior - L3 MSB - COLO4 Cell 4 | 0
CHI05-04-04-L3-1990 | CHI05-04-04-L3-2090 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L3 MSB - COLO4 Cell 4 | Interior - L3 ADP - COLO4 Cell 4 | 0
CHI05-04-04-L3-1990 | CHI05-04-04-L3-2000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L3 MSB - COLO4 Cell 4 | Interior - L3 PDUs - COLO4 Cell 4 | 0
CHI05-04-04-L3-2090 | CHI05-04-04-L3-2020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L3 ADP - COLO4 Cell 4 | Interior - L3 ATSs - COLO4 Cell 4 | 0
CHI05-04-04-L3-2000 | CHI05-04-04-L3-2030 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L3 PDUs - COLO4 Cell 4 | Interior - L3 Busway - COLO4 Cell 4 | 0
CHI05-04-04-L1-1740 | CHI05-04-04-L2-1860 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L1 UPS - COLO4 Cell 4 | Interior - L2 UPS - COLO4 Cell 4 | 0
CHI05-04-04-L2-1860 | CHI05-04-04-L3-1980 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L2 UPS - COLO4 Cell 4 | Interior - L3 UPS - COLO4 Cell 4 | 0
CHI05-04-04-DH-1600 | CHI05-04-04-DH-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Install PDU's - COLO4 Cell 4 - DH | Cable Pulling at PDU & Busway- COLO4 Cell 4 - DH | 0
CHI05-04-04-DH-1570 | CHI05-04-04-DH-1540 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Cable Pulling at PDU & Busway- COLO4 Cell 4 - DH | Termination at PDU & Busway - COLO4 Cell 4 - DH | 0
CHI05-04-04-MG-1600 | CHI05-04-04-L1-1770 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Placing the AHU - COLO4 Cell 4 - MG | Interior - L1 AHUs - COLO4 Cell 4 | 0
CHI05-04-01-MG-1220 | CHI05-04-01-ER-1220 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 1 - MG | Install Walls and Primer Paint - COLO4 Cell 1 - ER | 0
CHI05-04-01-ER-1220 | CHI05-04-01-DH-1220 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Install Walls and Primer Paint - COLO4 Cell 1 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 1 - DH | 0
CHI05-04-02-MG-1330 | CHI05-04-02-ER-1330 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 2 - MG | Install Walls and Primer Paint - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1330 | CHI05-04-02-DH-1330 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Install Walls and Primer Paint - COLO4 Cell 2 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH | 0
CHI05-04-03-MG-1440 | CHI05-04-03-ER-1440 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 3 - MG | Install Walls and Primer Paint - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1440 | CHI05-04-03-DH-1440 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Install Walls and Primer Paint - COLO4 Cell 3 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH | 0
CHI05-04-04-MG-1550 | CHI05-04-04-ER-1550 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 4 - MG | Install Walls and Primer Paint - COLO4 Cell 4 - ER | 0
CHI05-04-04-ER-1550 | CHI05-04-04-DH-1550 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Install Walls and Primer Paint - COLO4 Cell 4 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 4 - DH | 0
CHI05-04-03-MG-1440 | CHI05-04-04-MG-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 3 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 4 - MG | 0
CHI05-04-02-MG-1330 | CHI05-04-03-MG-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 2 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 3 - MG | 0
CHI05-04-01-MG-1220 | CHI05-04-02-MG-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 1 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 2 - MG | 0
CHI05-04-04-L3-2010 | CHI05-04-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 Level 4 Cx - Colo 4 | Interior - L3 AHUs - COLO4 Cell 4 | Cx LEV4 - COLO4 | 0
CHI05-04-02-L3-1770 | CHI05-04-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 Level 4 Cx - Colo 4 | Interior - L3 AHUs - COLO4 Cell 2 | Cx LEV4 - COLO4 | 0
CHI05-04-03-L3-1890 | CHI05-04-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 Level 4 Cx - Colo 4 | Interior - L3 AHUs - COLO4 Cell 3 | Cx LEV4 - COLO4 | 0
CHI05-05-04-L4-1000 | CHI05-05-04-L5-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 Level 4 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,5,2 Level 5 Cx / IST - Colo 5 | COLO5 Cx LEV4 - COLO5 | COLO5 Cx LEV5 / IST - COLO5 | 0
CHI05-05-01-MG-1350 | CHI05-05-01-MG-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Overhead MEP Installation - COLO5 Cell 1 - MG | Deliver AHU into Mech. Gallery - COLO5 Cell 1 - MG | 0
CHI05-05-01-MG-1360 | CHI05-05-01-MG-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO5 Cell 1 - MG | Install Walls and Primer Paint - COLO5 Cell 1 - MG | 0
CHI05-05-01-MG-1370 | CHI05-05-01-MG-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Install Walls and Primer Paint - COLO5 Cell 1 - MG | Layout Ceiling and install Pencile Rod - COLO5 Cell 1 - MG | 0
CHI05-05-01-MG-1390 | CHI05-05-01-MG-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO5 Cell 1 - MG | Placing the AHU - COLO5 Cell 1 - MG | 0
CHI05-05-01-MG-1380 | CHI05-05-01-MG-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Placing the AHU - COLO5 Cell 1 - MG | Piping and Electrical Termination to AHUs - COLO5 Cell 1 - MG | 0
CHI05-05-01-MG-1400 | CHI05-05-01-MG-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO5 Cell 1 - MG | Pipe Testing - COLO5 Cell 1 - MG | 0
CHI05-05-01-MG-1410 | CHI05-05-01-MG-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Pipe Testing - COLO5 Cell 1 - MG | Install ceiling and Light Fittings - COLO5 Cell 1 - MG | 0
CHI05-05-01-MG-1420 | CHI05-05-01-MG-1430 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Install ceiling and Light Fittings - COLO5 Cell 1 - MG | Trim out MEP - COLO5 Cell 1 - MG | 0
CHI05-05-01-MG-1340 | CHI05-05-01-MG-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 1 - MG | Overhead MEP Installation - COLO5 Cell 1 - MG | 0
CHI05-05-01-ER-1350 | CHI05-05-01-ER-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Install Upper Screens - COLO5 Cell 1 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 1 - ER | 0
CHI05-05-01-ER-1340 | CHI05-05-01-ER-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 1 - ER | Install Ceiling - COLO5 Cell 1 - ER | 0
CHI05-05-01-ER-1360 | CHI05-05-01-ER-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Install Ceiling - COLO5 Cell 1 - ER | Below Ceiling MEP Rough In - COLO5 Cell 1 - ER | 0
CHI05-05-01-ER-1370 | CHI05-05-01-ER-1380 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 1 - ER | Installation of ADP & ATS - COLO5 Cell 1 - ER | 2
CHI05-05-01-ER-1400 | CHI05-05-01-ER-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO5 Cell 1 - ER | Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER | 0
CHI05-05-01-DH-1330 | CHI05-05-01-DH-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 1 - DH | Ceiling Grid and Tile - COLO5 Cell 1 - DH | 0
CHI05-05-01-DH-1370 | CHI05-05-01-DH-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Ceiling Grid and Tile - COLO5 Cell 1 - DH | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 1 - DH | 0
CHI05-05-01-DH-1390 | CHI05-05-01-DH-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 1 - DH | Install PDU's - COLO5 Cell 1 - DH | 0
CHI05-05-01-DH-1380 | CHI05-05-01-DH-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Install PDU's - COLO5 Cell 1 - DH | Cable Pulling at PDU & Busway - COLO5 Cell 1 - DH | 0
CHI05-05-01-DH-1340 | CHI05-05-01-DH-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | HAC install and Rise - COLO5 Cell 1 - DH | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 1 - DH | 0
CHI05-05-01-DH-1330 | CHI05-05-01-DH-1360 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 1 - DH | Security Screen Installation - COLO5 Cell 1 - DH | 6
CHI05-05-01-DH-1360 | CHI05-05-01-DH-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Security Screen Installation - COLO5 Cell 1 - DH | Ceiling Grid and Tile - COLO5 Cell 1 - DH | 0
CHI05-05-01-DH-1380 | CHI05-05-01-DH-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Install PDU's - COLO5 Cell 1 - DH | HAC install and Rise - COLO5 Cell 1 - DH | 0
CHI05-05-01-ER-1350 | CHI05-05-01-DH-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Install Upper Screens - COLO5 Cell 1 - ER | Security Screen Installation - COLO5 Cell 1 - DH | 0
CHI05-05-01-MG-1330 | CHI05-05-01-MG-1340 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 1 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 1 - MG | 2
CHI05-05-01-MG-1330 | CHI05-05-01-MG-1340 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 1 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 1 - MG | 0
CHI05-05-01-ER-1330 | CHI05-05-01-ER-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO5 Cell 1 - ER | Install Upper Screens - COLO5 Cell 1 - ER | 0
CHI05-05-01-ER-1380 | CHI05-05-01-ER-1400 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Installation of ADP & ATS - COLO5 Cell 1 - ER | Connet to Cable tray and conduit equipment - COLO5 Cell 1 - ER | 2
CHI05-05-01-DH-1410 | CHI05-05-01-DH-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | HAC Placing - COLO5 Cell 1 - DH | HAC install and Rise - COLO5 Cell 1 - DH | 0
CHI05-05-01-DH-1390 | CHI05-05-01-DH-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 1 - DH | HAC Placing - COLO5 Cell 1 - DH | 0
CHI05-05-01-DH-1320 | CHI05-05-01-DH-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Cable Pulling at PDU & Busway - COLO5 Cell 1 - DH | Finishes and Signage - COLO5 Cell 1 - DH | 0
CHI05-05-01-ER-1390 | CHI05-05-01-ER-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Installation of UPS Equipment - COLO5 Cell 1 - ER | Door Frame Installation - COLO5 Cell 1 - ER | 0
CHI05-05-01-ER-1410 | CHI05-05-01-ER-1430 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER | Finishes and Signage - COLO5 Cell 1 - ER | 2
CHI05-05-01-ER-1420 | CHI05-05-01-ER-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Door Frame Installation - COLO5 Cell 1 - ER | Finishes and Signage - COLO5 Cell 1 - ER | 0
CHI05-05-01-L1-1590 | CHI05-05-01-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | L1 XFMR - MV- COLO5 | Interior - L1 MSB - COLO5 Cell 1 | 0
CHI05-05-01-L1-1500 | CHI05-05-01-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Interior - L1 UPS - COLO5 Cell 1 | Interior - L1 MSB - COLO5 Cell 1 | 0
CHI05-05-01-L1-1510 | CHI05-05-01-L1-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Interior - L1 MSB - COLO5 Cell 1 | Interior - L1 ADP - COLO5 Cell 1 | 0
CHI05-05-01-L1-1510 | CHI05-05-01-L1-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Interior - L1 MSB - COLO5 Cell 1 | Interior - L1 PDUs - COLO5 Cell 1 | 0
CHI05-05-01-L1-1610 | CHI05-05-01-L1-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Interior - L1 ADP - COLO5 Cell 1 | Interior - L1 ATSs - COLO5 Cell 1 | 0
CHI05-05-01-L1-1540 | CHI05-05-01-L1-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Interior - L1 ATSs - COLO5 Cell 1 | Interior - L1 AHUs - COLO5 Cell 1 | 0
CHI05-05-01-L1-1520 | CHI05-05-01-L1-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Interior - L1 PDUs - COLO5 Cell 1 | Interior - L1 Busway - COLO5 Cell 1 | 0
CHI05-05-01-L1-1600 | CHI05-05-01-L1-1510 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | L1 GEN - COLO5 | Interior - L1 MSB - COLO5 Cell 1 | 0
CHI05-05-01-L2-1700 | CHI05-05-01-L2-1710 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UPM - COLO5 | L2 XFMR - COLO5 | 0
CHI05-05-01-L2-1710 | CHI05-05-01-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | L2 XFMR - COLO5 | Interior - L2 MSB - COLO5 Cell 1 | 0
CHI05-05-01-L2-1620 | CHI05-05-01-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L2 UPS - COLO5 Cell 1 | Interior - L2 MSB - COLO5 Cell 1 | 0
CHI05-05-01-L2-1630 | CHI05-05-01-L2-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L2 MSB - COLO5 Cell 1 | Interior - L2 ADP - COLO5 Cell 1 | 0
CHI05-05-01-L2-1630 | CHI05-05-01-L2-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L2 MSB - COLO5 Cell 1 | Interior - L2 PDUs - COLO5 Cell 1 | 0
CHI05-05-01-L2-1730 | CHI05-05-01-L2-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L2 ADP - COLO5 Cell 1 | Interior - L2 ATSs - COLO5 Cell 1 | 0
CHI05-05-01-L2-1660 | CHI05-05-01-L2-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L2 ATSs - COLO5 Cell 1 | Interior - L2 AHUs - COLO5 Cell 1 | 0
CHI05-05-01-L2-1640 | CHI05-05-01-L2-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L2 PDUs - COLO5 Cell 1 | Interior - L2 Busway - COLO5 Cell 1 | 0
CHI05-05-01-L2-1720 | CHI05-05-01-L2-1630 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | L2 GEN - COLO5 | Interior - L2 MSB - COLO5 Cell 1 | 0
CHI05-05-01-L3-1820 | CHI05-05-01-L3-1830 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UPM - COLO5 | L3 XFMR - COLO5 | 0
CHI05-05-01-L3-1830 | CHI05-05-01-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | L3 XFMR - COLO5 | Interior - L3 MSB - COLO5 Cell 1 | 0
CHI05-05-01-L3-1740 | CHI05-05-01-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L3 UPS - COLO5 Cell 1 | Interior - L3 MSB - COLO5 Cell 1 | 0
CHI05-05-01-L3-1750 | CHI05-05-01-L3-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L3 MSB - COLO5 Cell 1 | Interior - L3 ADP - COLO5 Cell 1 | 0
CHI05-05-01-L3-1750 | CHI05-05-01-L3-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L3 MSB - COLO5 Cell 1 | Interior - L3 PDUs - COLO5 Cell 1 | 0
CHI05-05-01-L3-1850 | CHI05-05-01-L3-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L3 ADP - COLO5 Cell 1 | Interior - L3 ATSs - COLO5 Cell 1 | 0
CHI05-05-01-L3-1780 | CHI05-05-01-L3-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L3 ATSs - COLO5 Cell 1 | Interior - L3 AHUs - COLO5 Cell 1 | 0
CHI05-05-01-L3-1760 | CHI05-05-01-L3-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L3 PDUs - COLO5 Cell 1 | Interior - L3 Busway - COLO5 Cell 1 | 0
CHI05-05-01-L3-1840 | CHI05-05-01-L3-1750 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | L3 GEN - COLO5 | Interior - L3 MSB - COLO5 Cell 1 | 0
CHI05-05-01-L1-1500 | CHI05-05-01-L2-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L1 UPS - COLO5 Cell 1 | Interior - L2 UPS - COLO5 Cell 1 | 0
CHI05-05-01-DH-1380 | CHI05-05-01-DH-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Install PDU's - COLO5 Cell 1 - DH | Termination at PDU & Busway- COLO5 Cell 1 - DH | 0
CHI05-05-01-DH-1350 | CHI05-05-01-DH-1320 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Termination at PDU & Busway- COLO5 Cell 1 - DH | Cable Pulling at PDU & Busway - COLO5 Cell 1 - DH | 0
CHI05-05-01-MG-1380 | CHI05-05-01-L1-1530 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Placing the AHU - COLO5 Cell 1 - MG | Interior - L1 AHUs - COLO5 Cell 1 | 0
CHI05-05-01-DH-1380 | CHI05-05-01-L1-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Install PDU's - COLO5 Cell 1 - DH | Interior - L1 PDUs - COLO5 Cell 1 | 0
CHI05-05-01-L1-1600 | CHI05-05-01-L2-1720 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L1 GEN - COLO5 | L2 GEN - COLO5 | 0
CHI05-05-01-L3-1770 | CHI05-05-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 Level 4 Cx - Colo 5 | Interior - L3 AHUs - COLO5 Cell 1 | COLO5 Cx LEV4 - COLO5 | 0
CHI05-05-02-MG-1460 | CHI05-05-02-MG-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Overhead MEP Installation - COLO5 Cell 2 - MG | Deliver AHU into Mech. Gallery - COLO5 Cell 2 - MG | 0
CHI05-05-02-MG-1470 | CHI05-05-02-MG-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO5 Cell 2 - MG | Install Walls and Primer Paint - COLO5 Cell 2 - MG | 0
CHI05-05-02-MG-1480 | CHI02-05-02-MG-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Install Walls and Primer Paint - COLO5 Cell 2 - MG | Layout Ceiling and install Pencile Rod - COLO5 Cell 2 - MG | 0
CHI02-05-02-MG-1500 | CHI02-05-02-MG-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO5 Cell 2 - MG | Placing the AHU - COLO5 Cell 2 - MG | 0
CHI02-05-02-MG-1490 | CHI02-05-02-MG-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Placing the AHU - COLO5 Cell 2 - MG | Piping and Electrical Termination to AHUs - COLO5 Cell 2 - MG | 0
CHI02-05-02-MG-1510 | CHI05-05-02-MG-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO5 Cell 2 - MG | Pipe Testing - COLO5 Cell 2 - MG | 0
CHI05-05-02-MG-1520 | CHI05-05-02-MG-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Pipe Testing - COLO5 Cell 2 - MG | Install ceiling and Light Fittings - COLO5 Cell 2 - MG | 0
CHI05-05-02-MG-1530 | CHI05-05-02-MG-1540 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Install ceiling and Light Fittings - COLO5 Cell 2 - MG | Trim out MEP - COLO5 Cell 2 - MG | 0
CHI05-05-02-MG-1450 | CHI05-05-02-MG-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 2 - MG | Overhead MEP Installation - COLO5 Cell 2 - MG | 0
CHI02-05-02-ER-1460 | CHI05-05-02-ER-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Install Upper Screens - COLO5 Cell 2 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1450 | CHI05-05-02-ER-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 2 - ER | Install Ceiling - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1470 | CHI05-05-02-ER-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Install Ceiling - COLO5 Cell 2 - ER | Below Ceiling MEP Rough In - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1480 | CHI05-05-02-ER-1490 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 2 - ER | Installation of ADP & ATS - COLO5 Cell 2 - ER | 2
CHI05-05-02-ER-1510 | CHI05-05-02-ER-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO5 Cell 2 - ER | Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER | 0
CHI05-05-02-DH-1440 | CHI05-05-02-DH-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 2 - DH | Ceiling Grid and Tile - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1480 | CHI05-05-02-DH-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Ceiling Grid and Tile - COLO5 Cell 2 - DH | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1500 | CHI05-05-02-DH-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 2 - DH | Install PDU's - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1490 | CHI05-05-02-DH-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Install PDU's - COLO5 Cell 2 - DH | Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1450 | CHI05-05-02-DH-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | HAC install and Rise - COLO5 Cell 2 - DH | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1440 | CHI05-05-02-DH-1470 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 2 - DH | Security Screen Installation - COLO5 Cell 2 - DH | 6
CHI05-05-02-DH-1470 | CHI05-05-02-DH-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Security Screen Installation - COLO5 Cell 2 - DH | Ceiling Grid and Tile - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1490 | CHI05-05-02-DH-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Install PDU's - COLO5 Cell 2 - DH | HAC install and Rise - COLO5 Cell 2 - DH | 0
CHI02-05-02-ER-1460 | CHI05-05-02-DH-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Install Upper Screens - COLO5 Cell 2 - ER | Security Screen Installation - COLO5 Cell 2 - DH | 0
CHI05-05-02-MG-1440 | CHI05-05-02-MG-1450 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 2 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 2 - MG | 2
CHI05-05-02-MG-1440 | CHI05-05-02-MG-1450 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 2 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 2 - MG | 0
CHI05-05-02-ER-1440 | CHI02-05-02-ER-1460 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO5 Cell 2 - ER | Install Upper Screens - COLO5 Cell 2 - ER | 2
CHI05-05-02-ER-1490 | CHI05-05-02-ER-1510 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Installation of ADP & ATS - COLO5 Cell 2 - ER | Connet to Cable tray and conduit equipment - COLO5 Cell 2 - ER | 2
CHI05-05-02-DH-1520 | CHI05-05-02-DH-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | HAC Placing - COLO5 Cell 2 - DH | HAC install and Rise - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1500 | CHI05-05-02-DH-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 2 - DH | HAC Placing - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1430 | CHI05-05-02-DH-1530 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH | Finishes and Signage - COLO5 Cell 2 - DH | 0
CHI05-05-02-ER-1500 | CHI05-05-02-ER-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Installation of UPS Equipment - COLO5 Cell 2 - ER | Door Frame Installation - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1520 | CHI05-05-02-ER-1540 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER | Finishes and Signage - COLO5 Cell 2 - ER | 2
CHI05-05-02-ER-1530 | CHI05-05-02-ER-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Door Frame Installation - COLO5 Cell 2 - ER | Finishes and Signage - COLO5 Cell 2 - ER | 0
CHI05-05-02-L1-1620 | CHI05-05-02-L1-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Interior - L1 UPS - COLO5 Cell 2 | Interior - L1 MSB - COLO5 Cell 2 | 0
CHI05-05-02-L1-1630 | CHI05-05-02-L1-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Interior - L1 MSB - COLO5 Cell 2 | Interior - L1 ADP - COLO5 Cell 2 | 0
CHI05-05-02-L1-1630 | CHI05-05-02-L1-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Interior - L1 MSB - COLO5 Cell 2 | Interior - L1 PDUs - COLO5 Cell 2 | 0
CHI05-05-02-L1-1730 | CHI05-05-02-L1-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Interior - L1 ADP - COLO5 Cell 2 | Interior - L1 ATSs - COLO5 Cell 2 | 0
CHI05-05-02-L1-1660 | CHI05-05-02-L1-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Interior - L1 ATSs - COLO5 Cell 2 | Interior - L1 AHUs - COLO5 Cell 2 | 0
CHI05-05-02-L1-1640 | CHI05-05-02-L1-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Interior - L1 PDUs - COLO5 Cell 2 | Interior - L1 Busway - COLO5 Cell 2 | 0
CHI05-05-02-L2-1740 | CHI05-05-02-L2-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L2 UPS - COLO5 Cell 2 | Interior - L2 MSB - COLO5 Cell 2 | 0
CHI05-05-02-L2-1750 | CHI05-05-02-L2-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L2 MSB - COLO5 Cell 2 | Interior - L2 ADP - COLO5 Cell 2 | 0
CHI05-05-02-L2-1750 | CHI05-05-02-L2-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L2 MSB - COLO5 Cell 2 | Interior - L2 PDUs - COLO5 Cell 2 | 0
CHI05-05-02-L2-1850 | CHI05-05-02-L2-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L2 ADP - COLO5 Cell 2 | Interior - L2 ATSs - COLO5 Cell 2 | 0
CHI05-05-02-L2-1780 | CHI05-05-02-L2-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L2 ATSs - COLO5 Cell 2 | Interior - L2 AHUs - COLO5 Cell 2 | 0
CHI05-05-02-L2-1760 | CHI05-05-02-L2-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L2 PDUs - COLO5 Cell 2 | Interior - L2 Busway - COLO5 Cell 2 | 0
CHI05-05-02-L3-1860 | CHI05-05-02-L3-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L3 UPS - COLO5 Cell 2 | Interior - L3 MSB - COLO5 Cell 2 | 0
CHI05-05-02-L3-1870 | CHI05-05-02-L3-1970 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L3 MSB - COLO5 Cell 2 | Interior - L3 ADP - COLO5 Cell 2 | 0
CHI05-05-02-L3-1870 | CHI05-05-02-L3-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L3 MSB - COLO5 Cell 2 | Interior - L3 PDUs - COLO5 Cell 2 | 0
CHI05-05-02-L3-1970 | CHI05-05-02-L3-1900 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L3 ADP - COLO5 Cell 2 | Interior - L3 ATSs - COLO5 Cell 2 | 0
CHI05-05-02-L3-1900 | CHI05-05-02-L3-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L3 ATSs - COLO5 Cell 2 | Interior - L3 AHUs - COLO5 Cell 2 | 0
CHI05-05-02-L3-1880 | CHI05-05-02-L3-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L3 PDUs - COLO5 Cell 2 | Interior - L3 Busway - COLO5 Cell 2 | 0
CHI05-05-02-L1-1620 | CHI05-05-02-L2-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L1 UPS - COLO5 Cell 2 | Interior - L2 UPS - COLO5 Cell 2 | 0
CHI05-05-02-L2-1740 | CHI05-05-02-L3-1860 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L2 UPS - COLO5 Cell 2 | Interior - L3 UPS - COLO5 Cell 2 | 0
CHI05-05-02-DH-1490 | CHI05-05-02-DH-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Install PDU's - COLO5 Cell 2 - DH | Termination at PDU & Busway- COLO5 Cell 2 - DH | 0
CHI02-05-02-MG-1490 | CHI05-05-02-L1-1650 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Placing the AHU - COLO5 Cell 2 - MG | Interior - L1 AHUs - COLO5 Cell 2 | 0
CHI05-05-03-MG-1570 | CHI05-05-03-MG-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Overhead MEP Installation - COLO5 Cell 3 - MG | Deliver AHU into Mech. Gallery - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1580 | CHI05-05-03-MG-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO5 Cell 3 - MG | Install Walls and Primer Paint - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1590 | CHI05-05-03-MG-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Install Walls and Primer Paint - COLO5 Cell 3 - MG | Layout Ceiling and install Pencile Rod - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1610 | CHI05-05-03-MG-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO5 Cell 3 - MG | Placing the AHU - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1600 | CHI05-05-03-MG-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Placing the AHU - COLO5 Cell 3 - MG | Piping and Electrical Termination to AHUs - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1620 | CHI05-05-03-MG-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO5 Cell 3 - MG | Pipe Testing - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1630 | CHI05-05-03-MG-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Pipe Testing - COLO5 Cell 3 - MG | Install ceiling and Light Fittings - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1640 | CHI05-05-03-MG-1650 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Install ceiling and Light Fittings - COLO5 Cell 3 - MG | Trim out MEP - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1560 | CHI05-05-03-MG-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 3 - MG | Overhead MEP Installation - COLO5 Cell 3 - MG | 0
CHI05-05-03-ER-1570 | CHI05-05-03-ER-1560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Install Upper Screens - COLO5 Cell 3 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1560 | CHI05-05-03-ER-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 3 - ER | Install Ceiling - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1580 | CHI05-05-03-ER-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Install Ceiling - COLO5 Cell 3 - ER | Below Ceiling MEP Rough In - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1590 | CHI05-05-03-ER-1600 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 3 - ER | Installation of ADP & ATS - COLO5 Cell 3 - ER | 2
CHI05-05-03-ER-1620 | CHI05-05-03-ER-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO5 Cell 3 - ER | Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER | 0
CHI05-05-03-DH-1550 | CHI05-05-03-DH-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 3 - DH | Ceiling Grid and Tile - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1590 | CHI05-05-03-DH-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Ceiling Grid and Tile - COLO5 Cell 3 - DH | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1610 | CHI05-05-03-DH-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 3 - DH | Install PDU's - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1600 | CHI05-05-03-DH-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Install PDU's - COLO5 Cell 3 - DH | Termination at PDU & Busway - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1560 | CHI05-05-03-DH-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | HAC install and Rise - COLO5 Cell 3 - DH | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1550 | CHI05-05-03-DH-1580 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 3 - DH | Security Screen Installation - COLO5 Cell 3 - DH | 6
CHI05-05-03-DH-1580 | CHI05-05-03-DH-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Security Screen Installation - COLO5 Cell 3 - DH | Ceiling Grid and Tile - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1600 | CHI05-05-03-DH-1560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Install PDU's - COLO5 Cell 3 - DH | HAC install and Rise - COLO5 Cell 3 - DH | 0
CHI05-05-03-ER-1570 | CHI05-05-03-DH-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Install Upper Screens - COLO5 Cell 3 - ER | Security Screen Installation - COLO5 Cell 3 - DH | 0
CHI05-05-03-MG-1550 | CHI05-05-03-MG-1560 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 3 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 3 - MG | 2
CHI05-05-03-MG-1550 | CHI05-05-03-MG-1560 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 3 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 3 - MG | 0
CHI05-05-03-ER-1550 | CHI05-05-03-ER-1570 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO5 Cell 3 - ER | Install Upper Screens - COLO5 Cell 3 - ER | 2
CHI05-05-03-ER-1600 | CHI05-05-03-ER-1620 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Installation of ADP & ATS - COLO5 Cell 3 - ER | Connet to Cable tray and conduit equipment - COLO5 Cell 3 - ER | 2
CHI05-05-03-DH-1630 | CHI05-05-03-DH-1560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | HAC Placing - COLO5 Cell 3 - DH | HAC install and Rise - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1610 | CHI05-05-03-DH-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 3 - DH | HAC Placing - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1540 | CHI05-05-03-DH-1640 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Termination at PDU & Busway - COLO5 Cell 3 - DH | Finishes and Signage - COLO5 Cell 3 - DH | 0
CHI05-05-03-ER-1610 | CHI05-05-03-ER-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Installation of UPS Equipment - COLO5 Cell 3 - ER | Door Frame Installation - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1630 | CHI05-05-03-ER-1650 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER | Finishes and Signage - COLO5 Cell 3 - ER | 2
CHI05-05-03-ER-1640 | CHI05-05-03-ER-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Door Frame Installation - COLO5 Cell 3 - ER | Finishes and Signage - COLO5 Cell 3 - ER | 0
CHI05-05-03-L1-1740 | CHI05-05-03-L1-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Interior - L1 UPS - COLO5 Cell 3 | Interior - L1 MSB - COLO5 Cell 3 | 0
CHI05-05-03-L1-1750 | CHI05-05-03-L1-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Interior - L1 MSB - COLO5 Cell 3 | Interior - L1 ADP - COLO5 Cell 3 | 0
CHI05-05-03-L1-1750 | CHI05-05-03-L1-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Interior - L1 MSB - COLO5 Cell 3 | Interior - L1 PDUs - COLO5 Cell 3 | 0
CHI05-05-03-L1-1850 | CHI05-05-03-L1-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Interior - L1 ADP - COLO5 Cell 3 | Interior - L1 ATSs - COLO5 Cell 3 | 0
CHI05-05-03-L1-1780 | CHI05-05-03-L1-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Interior - L1 ATSs - COLO5 Cell 3 | Interior - L1 AHUs - COLO5 Cell 3 | 0
CHI05-05-03-L1-1760 | CHI05-05-03-L1-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Interior - L1 PDUs - COLO5 Cell 3 | Interior - L1 Busway - COLO5 Cell 3 | 0
CHI05-05-03-L2-1860 | CHI05-05-03-L2-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L2 UPS - COLO5 Cell 3 | Interior - L2 MSB - COLO5 Cell 3 | 0
CHI05-05-03-L2-1870 | CHI05-05-03-L2-1970 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L2 MSB - COLO5 Cell 3 | Interior - L2 ADP - COLO5 Cell 3 | 0
CHI05-05-03-L2-1870 | CHI05-05-03-L2-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L2 MSB - COLO5 Cell 3 | Interior - L2 PDUs - COLO5 Cell 3 | 0
CHI05-05-03-L2-1970 | CHI05-05-03-L2-1900 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L2 ADP - COLO5 Cell 3 | Interior - L2 ATSs - COLO5 Cell 3 | 0
CHI05-05-03-L2-1900 | CHI05-05-03-L2-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L2 ATSs - COLO5 Cell 3 | Interior - L2 AHUs - COLO5 Cell 3 | 0
CHI05-05-03-L2-1880 | CHI05-05-03-L2-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L2 PDUs - COLO5 Cell 3 | Interior - L2 Busway - COLO5 Cell 3 | 0
CHI05-05-03-L3-1980 | CHI05-05-03-L3-1990 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L3 UPS - COLO5 Cell 3 | Interior - L3 MSB - COLO5 Cell 3 | 0
CHI05-05-03-L3-1990 | CHI05-05-03-L3-2090 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L3 MSB - COLO5 Cell 3 | Interior - L3 ADP - COLO5 Cell 3 | 0
CHI05-05-03-L3-1990 | CHI05-05-03-L3-2000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L3 MSB - COLO5 Cell 3 | Interior - L3 PDUs - COLO5 Cell 3 | 0
CHI05-05-03-L3-2090 | CHI05-05-03-L3-2020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L3 ADP - COLO5 Cell 3 | Interior - L3 ATSs - COLO5 Cell 3 | 0
CHI05-05-03-L3-2020 | CHI05-05-03-L3-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L3 ATSs - COLO5 Cell 3 | Interior - L3 AHUs - COLO5 Cell 3 | 0
CHI05-05-03-L3-2000 | CHI05-05-03-L3-2030 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L3 PDUs - COLO5 Cell 3 | Interior - L3 Busway - COLO5 Cell 3 | 0
CHI05-05-03-L1-1740 | CHI05-05-03-L2-1860 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L1 UPS - COLO5 Cell 3 | Interior - L2 UPS - COLO5 Cell 3 | 0
CHI05-05-03-L2-1860 | CHI05-05-03-L3-1980 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L2 UPS - COLO5 Cell 3 | Interior - L3 UPS - COLO5 Cell 3 | 0
CHI05-05-03-DH-1600 | CHI05-05-03-DH-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Install PDU's - COLO5 Cell 3 - DH | Cable Pulling at PDU & Busway- COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1570 | CHI05-05-03-DH-1540 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Cable Pulling at PDU & Busway- COLO5 Cell 3 - DH | Termination at PDU & Busway - COLO5 Cell 3 - DH | 0
CHI05-05-03-MG-1600 | CHI05-05-03-L1-1770 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Placing the AHU - COLO5 Cell 3 - MG | Interior - L1 AHUs - COLO5 Cell 3 | 0
CHI05-05-04-MG-1680 | CHI05-05-04-MG-1690 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Overhead MEP Installation - COLO5 Cell 4 - MG | Deliver AHU into Mech. Gallery - COLO5 Cell 4 - MG | 0
CHI05-05-04-MG-1690 | CHI05-05-04-MG-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO5 Cell 4 - MG | Install Walls and Primer Paint - COLO5 Cell 4 - MG | 0
CHI05-05-04-MG-1700 | CHI05-05-04-MG-1720 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Install Walls and Primer Paint - COLO5 Cell 4 - MG | Layout Ceiling and install Pencile Rod - COLO5 Cell 4 - MG | 0
CHI05-05-04-MG-1720 | CHI05-05-04-MG-1710 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO5 Cell 4 - MG | Placing the AHU - COLO5 Cell 4 - MG | 0
CHI05-05-04-MG-1710 | CHI05-05-04-MG-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Placing the AHU - COLO5 Cell 4 - MG | Piping and Electrical Termination to AHUs - COLO5 Cell 4 - MG | 0
CHI05-05-04-MG-1730 | CHI05-05-04-MG-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO5 Cell 4 - MG | Pipe Testing - COLO5 Cell 4 - MG | 0
CHI05-05-04-MG-1740 | CHI05-05-04-MG-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Pipe Testing - COLO5 Cell 4 - MG | Install ceiling and Light Fittings - COLO5 Cell 4 - MG | 0
CHI05-05-04-MG-1750 | CHI05-05-04-MG-1760 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Install ceiling and Light Fittings - COLO5 Cell 4 - MG | Trim out MEP - COLO5 Cell 4 - MG | 0
CHI05-05-04-MG-1670 | CHI05-05-04-MG-1680 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 4 - MG | Overhead MEP Installation - COLO5 Cell 4 - MG | 0
CHI05-05-04-ER-1680 | CHI05-05-04-ER-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Install Upper Screens - COLO5 Cell 4 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 4 - ER | 0
CHI05-05-04-ER-1670 | CHI05-05-04-ER-1690 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 4 - ER | Install Ceiling - COLO5 Cell 4 - ER | 0
CHI05-05-04-ER-1690 | CHI05-05-04-ER-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Install Ceiling - COLO5 Cell 4 - ER | Below Ceiling MEP Rough In - COLO5 Cell 4 - ER | 0
CHI05-05-04-ER-1700 | CHI05-05-04-ER-1710 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 4 - ER | Installation of ADP & ATS - COLO5 Cell 4 - ER | 2
CHI05-05-04-ER-1730 | CHI05-05-04-ER-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO5 Cell 4 - ER | Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER | 0
CHI05-05-04-DH-1660 | CHI05-05-04-DH-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 4 - DH | Ceiling Grid and Tile - COLO5 Cell 4 - DH | 0
CHI05-05-04-DH-1700 | CHI05-05-04-DH-1720 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Ceiling Grid and Tile - COLO5 Cell 4 - DH | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 4 - DH | 0
CHI05-05-04-DH-1720 | CHI05-05-04-DH-1710 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 4 - DH | Install PDU's - COLO5 Cell 4 - DH | 0
CHI05-05-04-DH-1710 | CHI05-05-04-DH-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Install PDU's - COLO5 Cell 4 - DH | Termination at PDU & Busway - COLO5 Cell 4 - DH | 0
CHI05-05-04-DH-1670 | CHI05-05-04-DH-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | HAC install and Rise - COLO5 Cell 4 - DH | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH | 0
CHI05-05-04-DH-1660 | CHI05-05-04-DH-1690 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 4 - DH | Security Screen Installation - COLO5 Cell 4 - DH | 6
CHI05-05-04-DH-1690 | CHI05-05-04-DH-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Security Screen Installation - COLO5 Cell 4 - DH | Ceiling Grid and Tile - COLO5 Cell 4 - DH | 0
CHI05-05-04-DH-1710 | CHI05-05-04-DH-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Install PDU's - COLO5 Cell 4 - DH | HAC install and Rise - COLO5 Cell 4 - DH | 0
CHI05-05-04-ER-1680 | CHI05-05-04-DH-1690 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Install Upper Screens - COLO5 Cell 4 - ER | Security Screen Installation - COLO5 Cell 4 - DH | 0
CHI05-05-04-MG-1660 | CHI05-05-04-MG-1670 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 4 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 4 - MG | 2
CHI05-05-04-MG-1660 | CHI05-05-04-MG-1670 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 4 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 4 - MG | 0
CHI05-05-04-ER-1660 | CHI05-05-04-ER-1680 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO5 Cell 4 - ER | Install Upper Screens - COLO5 Cell 4 - ER | 2
CHI05-05-04-ER-1710 | CHI05-05-04-ER-1730 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Installation of ADP & ATS - COLO5 Cell 4 - ER | Connet to Cable tray and conduit equipment - COLO5 Cell 4 - ER | 2
CHI05-05-04-DH-1740 | CHI05-05-04-DH-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | HAC Placing - COLO5 Cell 4 - DH | HAC install and Rise - COLO5 Cell 4 - DH | 0
CHI05-05-04-DH-1720 | CHI05-05-04-DH-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 4 - DH | HAC Placing - COLO5 Cell 4 - DH | 0
CHI05-05-04-DH-1650 | CHI05-05-04-DH-1750 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Termination at PDU & Busway - COLO5 Cell 4 - DH | Finishes and Signage - COLO5 Cell 4 - DH | 0
CHI05-05-04-ER-1720 | CHI05-05-04-ER-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Installation of UPS Equipment - COLO5 Cell 4 - ER | Door Frame Installation - COLO5 Cell 4 - ER | 0
CHI05-05-04-ER-1740 | CHI05-05-04-ER-1760 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER | Finishes and Signage - COLO5 Cell 4 - ER | 2
CHI05-05-04-ER-1750 | CHI05-05-04-ER-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Door Frame Installation - COLO5 Cell 4 - ER | Finishes and Signage - COLO5 Cell 4 - ER | 0
CHI05-05-04-L1-1860 | CHI05-05-04-L1-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Interior - L1 UPS - COLO5 Cell 4 | Interior - L1 MSB - COLO5 Cell 4 | 0
CHI05-05-04-L1-1870 | CHI05-05-04-L1-1970 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Interior - L1 MSB - COLO5 Cell 4 | Interior - L1 ADP - COLO5 Cell 4 | 0
CHI05-05-04-L1-1870 | CHI05-05-04-L1-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Interior - L1 MSB - COLO5 Cell 4 | Interior - L1 PDUs - COLO5 Cell 4 | 0
CHI05-05-04-L1-1970 | CHI05-05-04-L1-1900 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Interior - L1 ADP - COLO5 Cell 4 | Interior - L1 ATSs - COLO5 Cell 4 | 0
CHI05-05-04-L1-1900 | CHI05-05-04-L1-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Interior - L1 ATSs - COLO5 Cell 4 | Interior - L1 AHUs - COLO5 Cell 4 | 0
CHI05-05-04-L1-1880 | CHI05-05-04-L1-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Interior - L1 PDUs - COLO5 Cell 4 | Interior - L1 Busway - COLO5 Cell 4 | 0
CHI05-05-04-L2-1980 | CHI05-05-04-L2-1990 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L2 UPS - COLO5 Cell 4 | Interior - L2 MSB - COLO5 Cell 4 | 0
CHI05-05-04-L2-1990 | CHI05-05-04-L2-2090 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L2 MSB - COLO5 Cell 4 | Interior - L2 ADP - COLO5 Cell 4 | 0
CHI05-05-04-L2-1990 | CHI05-05-04-L2-2000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L2 MSB - COLO5 Cell 4 | Interior - L2 PDUs - COLO5 Cell 4 | 0
CHI05-05-04-L2-2090 | CHI05-05-04-L2-2020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L2 ADP - COLO5 Cell 4 | Interior - L2 ATSs - COLO5 Cell 4 | 0
CHI05-05-04-L2-2020 | CHI05-05-04-L2-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L2 ATSs - COLO5 Cell 4 | Interior - L2 AHUs - COLO5 Cell 4 | 0
CHI05-05-04-L2-2000 | CHI05-05-04-L2-2030 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L2 PDUs - COLO5 Cell 4 | Interior - L2 Busway - COLO5 Cell 4 | 0
CHI05-05-04-L3-2100 | CHI05-05-04-L3-2110 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L3 UPS - COLO5 Cell 4 | Interior - L3 MSB - COLO5 Cell 4 | 0
CHI05-05-04-L3-2110 | CHI05-05-04-L3-2210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L3 MSB - COLO5 Cell 4 | Interior - L3 ADP - COLO5 Cell 4 | 0
CHI05-05-04-L3-2110 | CHI05-05-04-L3-2120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L3 MSB - COLO5 Cell 4 | Interior - L3 PDUs - COLO5 Cell 4 | 0
CHI05-05-04-L3-2210 | CHI05-05-04-L3-2140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L3 ADP - COLO5 Cell 4 | Interior - L3 ATSs - COLO5 Cell 4 | 0
CHI05-05-04-L3-2140 | CHI05-05-04-L3-2130 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L3 ATSs - COLO5 Cell 4 | Interior - L3 AHUs - COLO5 Cell 4 | 0
CHI05-05-04-L3-2120 | CHI05-05-04-L3-2150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L3 PDUs - COLO5 Cell 4 | Interior - L3 Busway - COLO5 Cell 4 | 0
CHI05-05-04-L1-1860 | CHI05-05-04-L2-1980 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L1 UPS - COLO5 Cell 4 | Interior - L2 UPS - COLO5 Cell 4 | 0
CHI05-05-04-L2-1980 | CHI05-05-04-L3-2100 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L2 UPS - COLO5 Cell 4 | Interior - L3 UPS - COLO5 Cell 4 | 0
CHI05-05-04-DH-1710 | CHI05-05-04-DH-1680 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Install PDU's - COLO5 Cell 4 - DH | Cable Pulling at PDU & Busway- COLO5 Cell 4 - DH | 0
CHI05-05-04-DH-1680 | CHI05-05-04-DH-1650 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Cable Pulling at PDU & Busway- COLO5 Cell 4 - DH | Termination at PDU & Busway - COLO5 Cell 4 - DH | 0
CHI05-05-04-MG-1710 | CHI05-05-04-L1-1890 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Placing the AHU - COLO5 Cell 4 - MG | Interior - L1 AHUs - COLO5 Cell 4 | 0
CHI05-05-01-ER-1330 | CHI05-05-01-DH-1330 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Install Walls and Primer Paint - COLO5 Cell 1 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 1 - DH | 0
CHI05-05-02-MG-1440 | CHI05-05-02-ER-1440 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 2 - MG | Install Walls and Primer Paint - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1440 | CHI05-05-02-DH-1440 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Install Walls and Primer Paint - COLO5 Cell 2 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 2 - DH | 0
CHI05-05-03-MG-1550 | CHI05-05-03-ER-1550 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 3 - MG | Install Walls and Primer Paint - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1550 | CHI05-05-03-DH-1550 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Install Walls and Primer Paint - COLO5 Cell 3 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 3 - DH | 0
CHI05-05-04-MG-1660 | CHI05-05-04-ER-1660 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 4 - MG | Install Walls and Primer Paint - COLO5 Cell 4 - ER | 0
CHI05-05-04-ER-1660 | CHI05-05-04-DH-1660 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Install Walls and Primer Paint - COLO5 Cell 4 - ER | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 4 - DH | 0
CHI05-05-03-MG-1550 | CHI05-05-04-MG-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 3 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 4 - MG | 0
CHI05-05-02-MG-1440 | CHI05-05-03-MG-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 2 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 3 - MG | 0
CHI05-05-01-MG-1330 | CHI05-05-02-MG-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 1 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 2 - MG | 0
CHI05-05-04-L3-2130 | CHI05-05-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 Level 4 Cx - Colo 5 | Interior - L3 AHUs - COLO5 Cell 4 | COLO5 Cx LEV4 - COLO5 | 0
CHI05-05-02-L3-1890 | CHI05-05-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 Level 4 Cx - Colo 5 | Interior - L3 AHUs - COLO5 Cell 2 | COLO5 Cx LEV4 - COLO5 | 0
CHI05-05-03-L3-2010 | CHI05-05-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 Level 4 Cx - Colo 5 | Interior - L3 AHUs - COLO5 Cell 3 | COLO5 Cx LEV4 - COLO5 | 0
CHI05-02-04-MG-1340 | CHI05-03-01-MG-1110 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 4 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 1 - MG | 0
CHI05-03-04-MG-1440 | CHI05-04-01-MG-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 4 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 1 - MG | 0
CHI05-04-04-DH-1570 | CHI05-04-04-DH-1635 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Cable Pulling at PDU & Busway- COLO4 Cell 4 - DH | Closing Construction Access Door - COLO4 Cell 4 - DH | 0
CHI05-05-04-DH-1680 | CHI05-05-04-DH-1745 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Cable Pulling at PDU & Busway- COLO5 Cell 4 - DH | Closing Construction Access Door - COLO5 Cell 4 - DH | 0
CHI05-02-01-L3-1430 | CHI05-02-01-L3-1410 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L3 Busway - COLO2 Cell 1 | Interior - L3 AHUs - COLO2 Cell 1 | 0
CHI05-02-01-L2-1310 | CHI05-02-01-L2-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L2 Busway - COLO2 Cell 1 | Interior - L2 AHUs - COLO2 Cell 1 | 0
CHI05-02-01-L1-1190 | CHI05-02-01-L1-1170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Interior - L1 Busway - COLO2 Cell 1 | Interior - L1 AHUs - COLO2 Cell 1 | 0
CHI05-02-04-L3-1780 | CHI05-02-04-L3-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L3 ATSs - COLO2 Cell 4 | Interior - L3 Busway - COLO2 Cell 4 | 0
CHI05-02-04-L3-1790 | CHI05-02-04-L3-1770 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L3 Busway - COLO2 Cell 4 | Interior - L3 AHUs - COLO2 Cell 4 | 2
CHI05-04-01-L3-1670 | CHI05-04-01-L3-1650 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L3 Busway - COLO4 Cell 1 | Interior - L3 AHUs - COLO4 Cell 1 | 0
CHI05-04-03-L1-1650 | CHI05-04-03-L2-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L1 AHUs - COLO4 Cell 3 | Interior - L2 UPS - COLO4 Cell 3 | 0
CHI05-04-04-L3-2030 | CHI05-04-04-L3-2010 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L3 Busway - COLO4 Cell 4 | Interior - L3 AHUs - COLO4 Cell 4 | 3
CHI05-04-04-L2-1910 | CHI05-04-04-L2-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L2 Busway - COLO4 Cell 4 | Interior - L2 AHUs - COLO4 Cell 4 | 0
CHI05-04-04-L1-1790 | CHI05-04-04-L1-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Interior - L1 Busway - COLO4 Cell 4 | Interior - L1 AHUs - COLO4 Cell 4 | 0
CHI05-05-NTP-S | CHI05-CFCI-1240 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | Notice To Proceed | Damper Assembly and Delivery | 0
CHI05-OFCI-2130 | CHI05-CON-1020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,13,1 UTS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | UTS - Site - Finish ROJ | (3) UTS - Install and Terminate (1 wk/ea) | 0
CHI05-02-04-L1-1530 | CHI05-02-L1CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Interior - L1 AHUs - COLO2 Cell 4 | Complete L1 Cx (All Red Tags/ROJ) for Colo 2 | 0
CHI05-OFCI-1130 | CHI05-02-GEN-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,1 GENS - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | GENS - COLO 2 - In Storage | Generators Ready Fuel for Colo 2 | 0
CHI05-OFCI-1140 | CHI05-03-GEN-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,2 GENS - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | GENS - COLO 3 - In Storage | Generators Ready Fuel for Colo 3 | 0
CHI05-OFCI-1150 | CHI05-04-GEN-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,3 GENS - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | GENS - COLO 4 - In Storage | Generators Ready Fuel for Colo 4 | 0
CHI05-OFCI-1160 | CHI05-05-GEN-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,5 GENS - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | GENS - COLO 5 - In Storage | Generators Ready Fuel for Colo 5 | 0
CHI05-02-04-L3-1770 | CHI05-02-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Interior - L3 AHUs - COLO2 Cell 4 | Complete L3 CX (Green Tag) for Colo 2 | 0
CHI05-02-04-L4-1000 | CHI05-02-L4CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,5,1 Level 4 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | COLO2 Cx LEV4 - COLO2 | Complete L4 Cx (Blue Tag) for Colo 2 | 0
CHI05-02-04-L5-1000 | CHI05-02-L5CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,5,2 Level 5 Cx / IST - Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | COLO2 Cx LEV5 / IST - COLO2 | Complete L5/IST (White Tag) for Colo 2 | 0
CHI05-03-04-L1-1650 | CHI05-03-L1CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Interior - L1 AHUs - COLO3 Cell 4 | Complete L1 Cx (All Red Tags/ROJ) for Colo 3 | 0
CHI05-03-04-L2-1770 | CHI05-03-L2CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Interior - L2 AHUs - COLO3 Cell 4 | Complete L2 CX (Yellow Tag) for Colo 3 | 0
CHI05-03-04-L4-1000 | CHI05-03-L4CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,5,1 Level 4 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Cx LEV4 - COLO3 | Complete L4 Cx (Blue Tag) for Colo 3 | 0
CHI05-03-04-L5-1000 | CHI05-03-L5CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,5,2 Level 5 Cx / IST - Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Cx LEV5 / IST - COLO3 | Complete L5/IST (White Tag) for Colo 3 | 0
CHI05-04-04-L1-1770 | CHI05-04-L1CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Interior - L1 AHUs - COLO4 Cell 4 | Complete L1 Cx (All Red Tags/ROJ) for Colo 4 | 0
CHI05-04-04-L2-1890 | CHI05-04-L2CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Interior - L2 AHUs - COLO4 Cell 4 | Complete L2 CX (Yellow Tag) for Colo 4 | 0
CHI05-04-04-L3-2010 | CHI05-04-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Interior - L3 AHUs - COLO4 Cell 4 | Complete L3 CX (Green Tag) for Colo 4 | 0
CHI05-04-04-L4-1000 | CHI05-04-L4CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 Level 4 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Cx LEV4 - COLO4 | Complete L4 Cx (Blue Tag) for Colo 4 | 0
CHI05-04-04-L5-1000 | CHI05-04-L5CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,5,2 Level 5 Cx / IST - Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Cx LEV5 / IST - COLO4 | Complete L5/IST (White Tag) for Colo 4 | 0
CHI05-05-04-L1-1890 | CHI05-05-L1CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Interior - L1 AHUs - COLO5 Cell 4 | Complete L1 Cx (All Red Tags/ROJ) for Colo 5 | 0
CHI05-05-04-L2-2010 | CHI05-05-L2CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Interior - L2 AHUs - COLO5 Cell 4 | Complete L2 CX (Yellow Tag) for Colo 5 | 0
CHI05-05-04-L3-2130 | CHI05-05-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Interior - L3 AHUs - COLO5 Cell 4 | Complete L3 CX (Green Tag) for Colo 5 | 0
CHI05-05-04-L4-1000 | CHI05-05-L4CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 Level 4 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | COLO5 Cx LEV4 - COLO5 | Complete L4 Cx (Blue Tag) for Colo 5 | 0
CHI05-05-04-L5-1000 | CHI05-05-L5CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,5,2 Level 5 Cx / IST - Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | COLO5 Cx LEV5 / IST - COLO5 | Complete L5/IST (White Tag) for Colo 5 | 0
CHI05-CON-1050 | CHI05-02-POW-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Permanent Power Live | Power-ON Utility for Colo 2 | 0
CHI05-02-04-DH-1400 | CHI05-02-CSA-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH | Interior Finishes/CSA Complete for Colo 2 | 0
CHI05-02-04-DH-1400 | CHI05-02-BAS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH | Complete BAS SAT for Colo 2 | 0
CHI05-02-04-DH-1400 | CHI05-02-EPMS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH | Complete EPMS SAT for Colo 2 | 0
CHI05-02-04-DH-1400 | CHI05-02-FIRE-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH | Complete Fire Alarm for Colo 2 | 0
CHI05-03-04-DH-1510 | CHI05-03-CSA-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH | Interior Finishes/CSA Complete for Colo 3 | 0
CHI05-03-04-DH-1510 | CHI05-03-EPMS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH | Complete EPMS SAT for Colo 3 | 0
CHI05-03-04-DH-1510 | CHI05-03-BAS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH | Complete BAS SAT for Colo 3 | 0
CHI05-03-04-DH-1510 | CHI05-03-FIRE-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH | Complete Fire Alarm for Colo 3 | 0
CHI05-03-04-L3-1890 | CHI05-03-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Interior - L3 AHUs - COLO3 Cell 4 | Complete L3 CX (Green Tag) for Colo 3 | 0
CHI05-04-04-DH-1620 | CHI05-04-CSA-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH | Interior Finishes/CSA Complete for Colo 4 | 0
CHI05-04-04-DH-1620 | CHI05-04-BAS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH | Complete BAS SAT for Colo 4 | 0
CHI05-04-04-DH-1620 | CHI05-04-EPMS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH | Complete EPMS SAT for Colo 4 | 0
CHI05-04-04-DH-1620 | CHI05-04-FIRE-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH | Complete Fire Alarm for Colo 4 | 0
CHI05-05-04-DH-1730 | CHI05-05-CSA-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH | Interior Finishes/CSA Complete for Colo 5 | 0
CHI05-05-04-DH-1730 | CHI05-05-BAS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH | Complete BAS SAT for Colo 5 | 0
CHI05-05-04-DH-1730 | CHI05-05-EPMS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH | Complete EPMS SAT for Colo 5 | 0
CHI05-05-04-DH-1730 | CHI05-05-FIR-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH | Complete Fire Alarm for Colo 5 | 0
CHI05-02-GEN-F | CHI05-02-01-L1-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Generators Ready Fuel for Colo 2 | L1 GEN - COLO2 | 0
CHI05-03-GEN-F | CHI05-03-01-L1-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Generators Ready Fuel for Colo 3 | L1 GEN - COLO3 | 0
CHI05-04-GEN-F | CHI05-04-01-L1-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Generators Ready Fuel for Colo 4 | L1 GEN - COLO4 | 0
CHI05-05-GEN-F | CHI05-05-01-L1-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Generators Ready Fuel for Colo 5 | L1 GEN - COLO5 | 0
CHI05-02-04-ER-1370 | CHI05-02-MEP-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Below Ceiling MEP Rough In - COLO2 Cell 4 - ER | MEP Rough-in Complete for Colo 2 | 0
CHI05-03-04-ER-1480 | CHI05-03-MEP-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | MEP Rough-in Complete for Colo 3 | 0
CHI05-04-04-ER-1590 | CHI05-04-MEP-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | MEP Rough-in Complete for Colo 4 | 0
CHI05-05-04-ER-1700 | CHI05-05-MEP-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Below Ceiling MEP Rough In - COLO5 Cell 4 - ER | MEP Rough-in Complete for Colo 5 | 0
CHI05-02-MEP-F | CHI05-02-04-DH-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | MEP Rough-in Complete for Colo 2 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH | 0
CHI05-03-MEP-F | CHI05-03-04-DH-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | MEP Rough-in Complete for Colo 3 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH | 0
CHI05-04-MEP-F | CHI05-04-04-DH-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | MEP Rough-in Complete for Colo 4 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH | 0
CHI05-05-MEP-F | CHI05-05-04-DH-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | MEP Rough-in Complete for Colo 5 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH | 0
CHI05-02-L1CX-S | CHI05-02-04-L1-1530 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Start L1 CX (Red Tag) for Colo 2 | Interior - L1 AHUs - COLO2 Cell 4 | 0
CHI05-03-L1CX-S | CHI05-03-04-L1-1650 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Start L1 CX (Red Tag) for Colo 3 | Interior - L1 AHUs - COLO3 Cell 4 | 0
CHI05-04-L1CX-S | CHI05-04-04-L1-1770 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Start L1 CX (Red Tag) for Colo 4 | Interior - L1 AHUs - COLO4 Cell 4 | 0
CHI05-05-L1CX-S | CHI05-05-04-L1-1890 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Start L1 CX (Red Tag) for Colo 5 | Interior - L1 AHUs - COLO5 Cell 4 | 0
CHI05-04-L2CX-S | CHI05-04-04-L2-1890 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Start L2 CX (Yellow Tag) for Colo 4 | Interior - L2 AHUs - COLO4 Cell 4 | 0
CHI05-03-L2CX-S | CHI05-03-04-L2-1770 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Start L2 CX (Yellow Tag) for Colo 3 | Interior - L2 AHUs - COLO3 Cell 4 | 0
CHI05-02-L2CX-S | CHI05-02-04-L2-1650 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Start L2 CX (Yellow Tag) for Colo 2 | Interior - L2 AHUs - COLO2 Cell 4 | 0
CHI05-05-L2CX-S | CHI05-05-04-L2-2010 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Start L2 CX (Yellow Tag) for Colo 5 | Interior - L2 AHUs - COLO5 Cell 4 | 0
CHI05-05-L3CX-S | CHI05-05-04-L3-2130 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Start L3 Cx (Green tag) for Colo 5 | Interior - L3 AHUs - COLO5 Cell 4 | 0
CHI05-04-L3CX-S | CHI05-04-04-L3-2010 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Start L3 Cx (Green tag) for Colo 4 | Interior - L3 AHUs - COLO4 Cell 4 | 0
CHI05-03-L3CX-S | CHI05-03-04-L3-1890 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Start L3 Cx (Green tag) for Colo 3 | Interior - L3 AHUs - COLO3 Cell 4 | 0
CHI05-02-L3CX-S | CHI05-02-04-L3-1770 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Start L3 Cx (Green tag) for Colo 2 | Interior - L3 AHUs - COLO2 Cell 4 | 0
CHI05-02-L3CX-F | CHI05-02-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,5,1 Level 4 Cx - Colo 2 | Complete L3 CX (Green Tag) for Colo 2 | COLO2 Cx LEV4 - COLO2 | 0
CHI05-02-L4CX-F | CHI05-02-04-L5-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,5,2 Level 5 Cx / IST - Colo 2 | Complete L4 Cx (Blue Tag) for Colo 2 | COLO2 Cx LEV5 / IST - COLO2 | 0
CHI05-02-CSA-F | CHI05-02-04-L3-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior Finishes/CSA Complete for Colo 2 | Interior - L3 AHUs - COLO2 Cell 4 | 0
CHI05-02-BAS-F | CHI05-02-04-L3-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Complete BAS SAT for Colo 2 | Interior - L3 AHUs - COLO2 Cell 4 | 0
CHI05-02-EPMS-F | CHI05-02-04-L3-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Complete EPMS SAT for Colo 2 | Interior - L3 AHUs - COLO2 Cell 4 | 0
CHI05-02-FIRE-F | CHI05-02-04-L3-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Complete Fire Alarm for Colo 2 | Interior - L3 AHUs - COLO2 Cell 4 | 0
CHI05-03-CSA-F | CHI05-03-04-L3-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior Finishes/CSA Complete for Colo 3 | Interior - L3 AHUs - COLO3 Cell 4 | 0
CHI05-03-BAS-F | CHI05-03-04-L3-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Complete BAS SAT for Colo 3 | Interior - L3 AHUs - COLO3 Cell 4 | 0
CHI05-03-EPMS-F | CHI05-03-04-L3-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Complete EPMS SAT for Colo 3 | Interior - L3 AHUs - COLO3 Cell 4 | 0
CHI05-03-FIRE-F | CHI05-03-04-L3-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Complete Fire Alarm for Colo 3 | Interior - L3 AHUs - COLO3 Cell 4 | 0
CHI05-03-L4CX-F | CHI05-03-04-L5-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,5,2 Level 5 Cx / IST - Colo 3 | Complete L4 Cx (Blue Tag) for Colo 3 | Cx LEV5 / IST - COLO3 | 0
CHI05-03-ROJ-F | CHI05-03-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,5,1 Level 4 Cx - Colo 3 | Complete Last ROJ Arrival for Colo 3 | Cx LEV4 - COLO3 | 0
CHI05-02-ROJ-F | CHI05-02-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,5,1 Level 4 Cx - Colo 2 | Complete Last ROJ Arrival for Colo 2 | COLO2 Cx LEV4 - COLO2 | 0
CHI05-04-BAS-F | CHI05-04-04-L3-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Complete BAS SAT for Colo 4 | Interior - L3 AHUs - COLO4 Cell 4 | 0
CHI05-04-EPMS-F | CHI05-04-04-L3-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Complete EPMS SAT for Colo 4 | Interior - L3 AHUs - COLO4 Cell 4 | 0
CHI05-04-FIRE-F | CHI05-04-04-L3-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Complete Fire Alarm for Colo 4 | Interior - L3 AHUs - COLO4 Cell 4 | 0
CHI05-04-L1CX-F | CHI05-04-04-L2-1860 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Complete L1 Cx (All Red Tags/ROJ) for Colo 4 | Interior - L2 UPS - COLO4 Cell 4 | 0
CHI05-04-L3CX-F | CHI05-04-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 Level 4 Cx - Colo 4 | Complete L3 CX (Green Tag) for Colo 4 | Cx LEV4 - COLO4 | 0
CHI05-04-L4CX-F | CHI05-04-04-L5-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,5,2 Level 5 Cx / IST - Colo 4 | Complete L4 Cx (Blue Tag) for Colo 4 | Cx LEV5 / IST - COLO4 | 0
CHI05-05-CSA-F | CHI05-05-04-L3-2130 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior Finishes/CSA Complete for Colo 5 | Interior - L3 AHUs - COLO5 Cell 4 | 0
CHI05-05-BAS-F | CHI05-05-04-L3-2130 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Complete BAS SAT for Colo 5 | Interior - L3 AHUs - COLO5 Cell 4 | 0
CHI05-05-EPMS-F | CHI05-05-04-L3-2130 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Complete EPMS SAT for Colo 5 | Interior - L3 AHUs - COLO5 Cell 4 | 0
CHI05-05-FIR-F | CHI05-05-04-L3-2130 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Complete Fire Alarm for Colo 5 | Interior - L3 AHUs - COLO5 Cell 4 | 0
CHI05-05-L1CX-F | CHI05-05-04-L2-1980 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Complete L1 Cx (All Red Tags/ROJ) for Colo 5 | Interior - L2 UPS - COLO5 Cell 4 | 0
CHI05-05-L3CX-F | CHI05-05-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 Level 4 Cx - Colo 5 | Complete L3 CX (Green Tag) for Colo 5 | COLO5 Cx LEV4 - COLO5 | 0
CHI05-05-L4CX-F | CHI05-05-04-L5-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,5,2 Level 5 Cx / IST - Colo 5 | Complete L4 Cx (Blue Tag) for Colo 5 | COLO5 Cx LEV5 / IST - COLO5 | 0
CHI05-04-POW-F | CHI05-04-01-L3-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Power-ON Utility for Colo 4 | Interior - L3 UPS - COLO4 Cell 1 | 0
CHI05-03-POW-F | CHI05-03-01-L3-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Power-ON Utility for Colo 3 | Interior - L3 UPS - COLO3 Cell 1 | 0
CHI05-02-CO-F | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Complete CorpNet For Colo 2 | Site Secured Finish (August 04, 2025) | 0
CHI05-03-CO-F | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Complete CorpNet For Colo 3 | Site Secured Finish (August 04, 2025) | 0
CHI05-04-CSA-F | CHI05-04-04-L3-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior Finishes/CSA Complete for Colo 4 | Interior - L3 AHUs - COLO4 Cell 4 | 0
CHI05-04-ROJ-F | CHI05-04-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 Level 4 Cx - Colo 4 | Complete Last ROJ Arrival for Colo 4 | Cx LEV4 - COLO4 | 0
CHI05-05-ROJ-F | CHI05-05-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 Level 4 Cx - Colo 5 | Complete Last ROJ Arrival for Colo 5 | COLO5 Cx LEV4 - COLO5 | 0
CHI05-CON-1030 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | CHI05-PH2-FIT-BL-D5,2,2,1 General | Installation and Termiation of MV Cable | Site Secured Finish (August 04, 2025) | 0
CHI05-OFCI-1580 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,10,2 UMS & URS - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | UMS & URS - COLO 3 - In storage, needs modifications | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-02-01-DH-1090 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO2 Cell 1 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-02-01-ER-1100 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO2 Cell 1 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-02-02-DH-1200 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO2 Cell 2 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-02-02-ER-1210 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO2 Cell 2 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-02-03-ER-1320 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO2 Cell 3 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-02-03-DH-1310 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO2 Cell 3 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-02-04-ER-1430 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO2 Cell 4 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-02-04-DH-1420 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO2 Cell 4 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-03-01-ER-1210 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO3 Cell 1 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-03-01-DH-1200 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO3 Cell 1 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-03-02-ER-1320 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO3 Cell 2 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-03-02-DH-1310 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO3 Cell 2 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-03-03-ER-1430 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO3 Cell 3 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-03-03-DH-1420 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO3 Cell 3 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-03-04-ER-1540 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO3 Cell 4 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-03-04-DH-1530 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO3 Cell 4 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-04-01-ER-1320 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO4 Cell 1 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-04-01-DH-1310 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO4 Cell 1 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-04-02-ER-1430 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO4 Cell 2 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-04-02-DH-1420 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO4 Cell 2 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-04-03-ER-1540 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO4 Cell 3 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-04-03-DH-1530 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO4 Cell 3 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-04-04-ER-1650 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO4 Cell 4 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-04-04-DH-1640 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO4 Cell 4 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-05-01-ER-1430 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO5 Cell 1 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-05-01-DH-1420 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO5 Cell 1 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-05-02-ER-1540 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO5 Cell 2 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-05-02-DH-1530 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO5 Cell 2 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-05-03-ER-1650 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO5 Cell 3 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-05-03-DH-1640 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO5 Cell 3 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-05-04-ER-1760 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO5 Cell 4 - ER | Site Secured Finish (August 04, 2025) | 0
CHI05-05-04-DH-1750 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,1 General | Finishes and Signage - COLO5 Cell 4 - DH | Site Secured Finish (August 04, 2025) | 0
CHI05-02-02-L1-1310 | CHI05-02-02-L1-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Interior - L1 Busway - COLO2 Cell 2 | Interior - L1 AHUs - COLO2 Cell 2 | 0
CHI05-02-02-L2-1430 | CHI05-02-02-L2-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L2 Busway - COLO2 Cell 2 | Interior - L2 AHUs - COLO2 Cell 2 | 0
CHI05-02-02-L3-1550 | CHI05-02-02-L3-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L3 Busway - COLO2 Cell 2 | Interior - L3 AHUs - COLO2 Cell 2 | 0
CHI05-02-03-L1-1430 | CHI05-02-03-L1-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Interior - L1 Busway - COLO2 Cell 3 | Interior - L1 AHUs - COLO2 Cell 3 | 0
CHI05-02-03-L2-1550 | CHI05-02-03-L2-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L2 Busway - COLO2 Cell 3 | Interior - L2 AHUs - COLO2 Cell 3 | 0
CHI05-02-03-L3-1670 | CHI05-02-03-L3-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L3 Busway - COLO2 Cell 3 | Interior - L3 AHUs - COLO2 Cell 3 | 0
CHI05-02-04-L1-1550 | CHI05-02-04-L1-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Interior - L1 Busway - COLO2 Cell 4 | Interior - L1 AHUs - COLO2 Cell 4 | 0
CHI05-02-04-L2-1670 | CHI05-02-04-L2-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L2 Busway - COLO2 Cell 4 | Interior - L2 AHUs - COLO2 Cell 4 | 0
CHI05-03-01-L1-1310 | CHI05-03-01-L1-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Interior - L1 Busway - COLO3 Cell 1 | Interior - L1 AHUs - COLO3 Cell 1 | 0
CHI05-03-01-L2-1430 | CHI05-03-01-L2-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L2 Busway - COLO3 Cell 1 | Interior - L2 AHUs - COLO3 Cell 1 | 0
CHI05-03-01-L3-1550 | CHI05-03-01-L3-1530 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L3 Busway - COLO3 Cell 1 | Interior - L3 AHUs - COLO3 Cell 1 | 0
CHI05-03-02-L1-1430 | CHI05-03-02-L1-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Interior - L1 Busway - COLO3 Cell 2 | Interior - L1 AHUs - COLO3 Cell 2 | 0
CHI05-03-02-L2-1550 | CHI05-03-02-L2-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L2 Busway - COLO3 Cell 2 | Interior - L2 AHUs - COLO3 Cell 2 | 0
CHI05-03-02-L3-1670 | CHI05-03-02-L3-1650 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L3 Busway - COLO3 Cell 2 | Interior - L3 AHUs - COLO3 Cell 2 | 0
CHI05-03-03-L1-1550 | CHI05-03-03-L1-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | Interior - L1 Busway - COLO3 Cell 3 | Interior - L1 AHUs - COLO3 Cell 3 | 0
CHI05-03-03-L2-1670 | CHI05-03-03-L2-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | Interior - L2 Busway - COLO3 Cell 3 | Interior - L2 AHUs - COLO3 Cell 3 | 0
CHI05-03-04-L1-1670 | CHI05-03-04-L1-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Interior - L1 Busway - COLO3 Cell 4 | Interior - L1 AHUs - COLO3 Cell 4 | 0
CHI05-03-04-L2-1790 | CHI05-03-04-L2-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L2 Busway - COLO3 Cell 4 | Interior - L2 AHUs - COLO3 Cell 4 | 0
CHI05-03-04-L3-1910 | CHI05-03-04-L3-1890 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L3 Busway - COLO3 Cell 4 | Interior - L3 AHUs - COLO3 Cell 4 | 4
CHI05-04-01-L1-1430 | CHI05-04-01-L1-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Interior - L1 Busway - COLO4 Cell 1 | Interior - L1 AHUs - COLO4 Cell 1 | 0
CHI05-04-01-L2-1550 | CHI05-04-01-L2-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L2 Busway - COLO4 Cell 1 | Interior - L2 AHUs - COLO4 Cell 1 | 0
CHI05-04-02-L1-1550 | CHI05-04-02-L1-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Interior - L1 Busway - COLO4 Cell 2 | Interior - L1 AHUs - COLO4 Cell 2 | 0
CHI05-04-02-L2-1670 | CHI05-04-02-L2-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L2 Busway - COLO4 Cell 2 | Interior - L2 AHUs - COLO4 Cell 2 | 0
CHI05-04-02-L3-1790 | CHI05-04-02-L3-1770 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L3 Busway - COLO4 Cell 2 | Interior - L3 AHUs - COLO4 Cell 2 | 0
CHI05-04-03-L1-1670 | CHI05-04-03-L1-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Interior - L1 Busway - COLO4 Cell 3 | Interior - L1 AHUs - COLO4 Cell 3 | 0
CHI05-04-03-L2-1790 | CHI05-04-03-L2-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L2 Busway - COLO4 Cell 3 | Interior - L2 AHUs - COLO4 Cell 3 | 0
CHI05-04-03-L3-1910 | CHI05-04-03-L3-1890 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L3 Busway - COLO4 Cell 3 | Interior - L3 AHUs - COLO4 Cell 3 | 0
CHI05-05-01-L1-1550 | CHI05-05-01-L1-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Interior - L1 Busway - COLO5 Cell 1 | Interior - L1 AHUs - COLO5 Cell 1 | 0
CHI05-05-01-L2-1670 | CHI05-05-01-L2-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L2 Busway - COLO5 Cell 1 | Interior - L2 AHUs - COLO5 Cell 1 | 0
CHI05-05-01-L3-1790 | CHI05-05-01-L3-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L3 Busway - COLO5 Cell 1 | Interior - L3 AHUs - COLO5 Cell 1 | 0
CHI05-05-02-L1-1670 | CHI05-05-02-L1-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Interior - L1 Busway - COLO5 Cell 2 | Interior - L1 AHUs - COLO5 Cell 2 | 0
CHI05-05-02-L2-1790 | CHI05-05-02-L2-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L2 Busway - COLO5 Cell 2 | Interior - L2 AHUs - COLO5 Cell 2 | 0
CHI05-05-02-L3-1910 | CHI05-05-02-L3-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L3 Busway - COLO5 Cell 2 | Interior - L3 AHUs - COLO5 Cell 2 | 0
CHI05-05-03-L1-1790 | CHI05-05-03-L1-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Interior - L1 Busway - COLO5 Cell 3 | Interior - L1 AHUs - COLO5 Cell 3 | 0
CHI05-05-03-L2-1910 | CHI05-05-03-L2-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L2 Busway - COLO5 Cell 3 | Interior - L2 AHUs - COLO5 Cell 3 | 0
CHI05-05-03-L3-2030 | CHI05-05-03-L3-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L3 Busway - COLO5 Cell 3 | Interior - L3 AHUs - COLO5 Cell 3 | 0
CHI05-05-04-L1-1910 | CHI05-05-04-L1-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Interior - L1 Busway - COLO5 Cell 4 | Interior - L1 AHUs - COLO5 Cell 4 | 0
CHI05-05-04-L2-2030 | CHI05-05-04-L2-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L2 Busway - COLO5 Cell 4 | Interior - L2 AHUs - COLO5 Cell 4 | 0
CHI05-05-04-L3-2150 | CHI05-05-04-L3-2130 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L3 Busway - COLO5 Cell 4 | Interior - L3 AHUs - COLO5 Cell 4 | 2
CHI05-02-01-MG-1100 | CHI05-02-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,5,1 Level 4 Cx - Colo 2 | Trim out MEP - COLO2 Cell 1 - MG | COLO2 Cx LEV4 - COLO2 | 0
CHI05-02-02-MG-1210 | CHI05-02-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,5,1 Level 4 Cx - Colo 2 | Trim out MEP - COLO2 Cell 2 - MG | COLO2 Cx LEV4 - COLO2 | 0
CHI05-02-03-MG-1320 | CHI05-02-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,5,1 Level 4 Cx - Colo 2 | Trim out MEP - COLO2 Cell 3 - MG | COLO2 Cx LEV4 - COLO2 | 0
CHI05-02-04-MG-1430 | CHI05-02-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,5,1 Level 4 Cx - Colo 2 | Trim out MEP - COLO2 Cell 4 - MG | COLO2 Cx LEV4 - COLO2 | 0
CHI05-03-01-MG-1210 | CHI05-03-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,5,1 Level 4 Cx - Colo 3 | Trim out MEP - COLO3 Cell 1 - MG | Cx LEV4 - COLO3 | 0
CHI05-03-02-MG-1320 | CHI05-03-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,5,1 Level 4 Cx - Colo 3 | Trim out MEP - COLO3 Cell 2 - MG | Cx LEV4 - COLO3 | 0
CHI05-03-03-MG-1430 | CHI05-03-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,5,1 Level 4 Cx - Colo 3 | Trim out MEP - COLO3 Cell 3 - MG | Cx LEV4 - COLO3 | 0
CHI05-03-04-MG-1540 | CHI05-03-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,5,1 Level 4 Cx - Colo 3 | Trim out MEP - COLO3 Cell 4 - MG | Cx LEV4 - COLO3 | 0
CHI05-04-01-MG-1320 | CHI05-04-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 Level 4 Cx - Colo 4 | Trim out MEP - COLO4 Cell 1 - MG | Cx LEV4 - COLO4 | 0
CHI05-04-02-MG-1430 | CHI05-04-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 Level 4 Cx - Colo 4 | Trim out MEP - COLO4 Cell 2 - MG | Cx LEV4 - COLO4 | 0
CHI05-04-03-MG-1540 | CHI05-04-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 Level 4 Cx - Colo 4 | Trim out MEP - COLO4 Cell 3 - MG | Cx LEV4 - COLO4 | 0
CHI05-04-04-MG-1650 | CHI05-04-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 Level 4 Cx - Colo 4 | Trim out MEP - COLO4 Cell 4 - MG | Cx LEV4 - COLO4 | 0
CHI05-05-01-MG-1430 | CHI05-05-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 Level 4 Cx - Colo 5 | Trim out MEP - COLO5 Cell 1 - MG | COLO5 Cx LEV4 - COLO5 | 0
CHI05-05-02-MG-1540 | CHI05-05-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 Level 4 Cx - Colo 5 | Trim out MEP - COLO5 Cell 2 - MG | COLO5 Cx LEV4 - COLO5 | 0
CHI05-05-03-MG-1650 | CHI05-05-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 Level 4 Cx - Colo 5 | Trim out MEP - COLO5 Cell 3 - MG | COLO5 Cx LEV4 - COLO5 | 0
CHI05-05-04-MG-1760 | CHI05-05-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 Level 4 Cx - Colo 5 | Trim out MEP - COLO5 Cell 4 - MG | COLO5 Cx LEV4 - COLO5 | 0
CHI05-04-04-DH-1635 | CHI05-04-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,5,1 Level 4 Cx - Colo 4 | Closing Construction Access Door - COLO4 Cell 4 - DH | Cx LEV4 - COLO4 | 0
CHI05-05-04-DH-1745 | CHI05-05-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,5,1 Level 4 Cx - Colo 5 | Closing Construction Access Door - COLO5 Cell 4 - DH | COLO5 Cx LEV4 - COLO5 | 0
CHI05-OFCI-1620 | CHI05-OFCI-2070 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,1 PDU - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,11,2 PDU - COLO 3 | PDU - COLO 2 - ROJ | PDU - COLO 3 - ROJ | 0
CHI05-OFCI-1820 | CHI05-OFCI-2060 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,1 PDU - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,11,2 PDU - COLO 3 | PDU - COLO 2 - Finish ROJ | PDU - COLO 3 - Start ROJ | 0
CHI05-02-01-DH-1060 | CHI05-02-MEQ-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | HAC install and Rise - COLO2 Cell 1 - DH | Start-up Mechanical Equipment for Colo 2 | 0
CHI05-03-01-DH-1190 | CHI05-03-MEQ-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | HAC Placing - COLO3 Cell 1 - DH | Start-up Mechanical Equipment for Colo 3 | 0
CHI05-04-04-DH-1630 | CHI05-04-MEQ-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | HAC Placing - COLO4 Cell 4 - DH | Start-up Mechanical Equipment for Colo 4 | 0
CHI05-05-01-DH-1410 | CHI05-05-MEQ-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | HAC Placing - COLO5 Cell 1 - DH | Start-up Mechanical Equipment for Colo 5 | 0
CHI05-05-MEQ-S | CHI05-05-04-L3-2100 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Start-up Mechanical Equipment for Colo 5 | Interior - L3 UPS - COLO5 Cell 4 | 0
CHI05-04-MEQ-S | CHI05-04-04-L3-1980 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Start-up Mechanical Equipment for Colo 4 | Interior - L3 UPS - COLO4 Cell 4 | 0
CHI05-03-MEQ-S | CHI05-03-04-L3-1860 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Start-up Mechanical Equipment for Colo 3 | Interior - L3 UPS - COLO3 Cell 4 | 0
CHI05-02-MEQ-S | CHI05-02-04-L3-1740 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Start-up Mechanical Equipment for Colo 2 | Interior - L3 UPS - COLO2 Cell 4 | 0
CHI05-CFCI-1200 | CHI05-05-02-MG-1470 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | AHU (Admin) - Lead Time | Deliver AHU into Mech. Gallery - COLO5 Cell 2 - MG | 0
CHI05-CFCI-1200 | CHI05-05-03-MG-1580 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | AHU (Admin) - Lead Time | Deliver AHU into Mech. Gallery - COLO5 Cell 3 - MG | 0
CHI05-CFCI-1200 | CHI05-05-04-MG-1690 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | AHU (Admin) - Lead Time | Deliver AHU into Mech. Gallery - COLO5 Cell 4 - MG | 0
CHI05-CFCI-1220 | CHI05-02-01-ER-1090 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO2 Cell 1 - ER | 0
CHI05-CFCI-1220 | CHI05-02-02-ER-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO2 Cell 2 - ER | 0
CHI05-CFCI-1220 | CHI05-02-03-ER-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO2 Cell 3 - ER | 0
CHI05-CFCI-1220 | CHI05-02-04-ER-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO2 Cell 4 - ER | 0
CHI05-CFCI-1220 | CHI05-03-01-ER-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO3 Cell 1 - ER | 0
CHI05-CFCI-1220 | CHI05-03-02-ER-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO3 Cell 2 - ER | 0
CHI05-CFCI-1220 | CHI05-03-03-ER-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO3 Cell 3 - ER | 0
CHI05-CFCI-1220 | CHI05-03-04-ER-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO3 Cell 4 - ER | 0
CHI05-CFCI-1220 | CHI05-04-01-ER-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO4 Cell 1 - ER | 0
CHI05-CFCI-1220 | CHI05-04-02-ER-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO4 Cell 2 - ER | 0
CHI05-CFCI-1220 | CHI05-04-03-ER-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO4 Cell 3 - ER | 0
CHI05-CFCI-1220 | CHI05-04-04-ER-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO4 Cell 4 - ER | 0
CHI05-CFCI-1220 | CHI05-05-02-ER-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO5 Cell 2 - ER | 0
CHI05-CFCI-1220 | CHI05-05-03-ER-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO5 Cell 3 - ER | 0
CHI05-CFCI-1220 | CHI05-05-04-ER-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Doors/Frames/Hardware - Lead Time | Door Frame Installation - COLO5 Cell 4 - ER | 0
CHI05-CFCI-1100 | CHI05-02-01-ER-1040 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER | 0
CHI05-CFCI-1100 | CHI05-02-02-ER-1150 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO2 Cell 2 - ER | 0
CHI05-CFCI-1100 | CHI05-02-03-ER-1260 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO2 Cell 3 - ER | 0
CHI05-CFCI-1100 | CHI05-02-04-ER-1370 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO2 Cell 4 - ER | 0
CHI05-CFCI-1100 | CHI05-03-01-ER-1150 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO3 Cell 1 - ER | 0
CHI05-CFCI-1100 | CHI05-03-02-ER-1260 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | 0
CHI05-CFCI-1100 | CHI05-03-03-ER-1370 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | 0
CHI05-CFCI-1100 | CHI05-03-04-ER-1480 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | 0
CHI05-CFCI-1100 | CHI05-04-01-ER-1260 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO4 Cell 1 - ER | 0
CHI05-CFCI-1100 | CHI05-04-02-ER-1370 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | 0
CHI05-CFCI-1100 | CHI05-04-03-ER-1480 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | 0
CHI05-CFCI-1100 | CHI05-04-04-ER-1590 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | 0
CHI05-CFCI-1100 | CHI05-05-02-ER-1480 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO5 Cell 2 - ER | 0
CHI05-CFCI-1100 | CHI05-05-03-ER-1590 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO5 Cell 3 - ER | 0
CHI05-CFCI-1100 | CHI05-05-04-ER-1700 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Overhead Cable Bus - Lead Time | Below Ceiling MEP Rough In - COLO5 Cell 4 - ER | 0
CHI05-CFCI-1210 | CHI05-02-01-DH-1050 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Medium Voltage Cabling - Lead Time | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH | 0
CHI05-CFCI-1210 | CHI05-02-02-DH-1100 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Medium Voltage Cabling - Lead Time | Termination at PDU & Busway - COLO2 Cell 2 - DH | 0
CHI05-CFCI-1210 | CHI05-02-03-DH-1210 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Medium Voltage Cabling - Lead Time | Termination at PDU & Busway - COLO2 Cell 3 - DH | 0
CHI05-CFCI-1210 | CHI05-02-04-DH-1320 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Medium Voltage Cabling - Lead Time | Termination at PDU & Busway - COLO2 Cell 4 - DH | 0
CHI05-CFCI-1210 | CHI05-03-01-DH-1100 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Medium Voltage Cabling - Lead Time | Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH | 0
CHI05-CFCI-1210 | CHI05-03-02-DH-1210 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Medium Voltage Cabling - Lead Time | Termination at PDU & Busway - COLO3 Cell 2 - DH | 0
CHI05-CFCI-1210 | CHI05-03-03-DH-1320 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Medium Voltage Cabling - Lead Time | Termination at PDU & Busway - COLO3 Cell 3 - DH | 0
CHI05-CFCI-1210 | CHI05-03-04-DH-1430 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Medium Voltage Cabling - Lead Time | Termination at PDU & Busway - COLO3 Cell 4 - DH | 0
CHI05-CFCI-1210 | CHI05-04-01-DH-1210 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Medium Voltage Cabling - Lead Time | Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH | 0
CHI05-CFCI-1210 | CHI05-04-02-DH-1320 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Medium Voltage Cabling - Lead Time | Termination at PDU & Busway - COLO4 Cell 2 - DH | 0
CHI05-CFCI-1210 | CHI05-04-03-DH-1430 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Medium Voltage Cabling - Lead Time | Termination at PDU & Busway - COLO4 Cell 3 - DH | 0
CHI05-CFCI-1210 | CHI05-04-04-DH-1540 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Medium Voltage Cabling - Lead Time | Termination at PDU & Busway - COLO4 Cell 4 - DH | 0
CHI05-CFCI-1210 | CHI05-05-02-DH-1430 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Medium Voltage Cabling - Lead Time | Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH | 0
CHI05-CFCI-1210 | CHI05-05-03-DH-1540 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Medium Voltage Cabling - Lead Time | Termination at PDU & Busway - COLO5 Cell 3 - DH | 0
CHI05-CFCI-1210 | CHI05-05-04-DH-1650 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Medium Voltage Cabling - Lead Time | Termination at PDU & Busway - COLO5 Cell 4 - DH | 0
CHI05-CFCI-1230 | CHI05-02-01-DH-1090 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO2 Cell 1 - DH | 0
CHI05-CFCI-1230 | CHI05-02-01-ER-1100 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO2 Cell 1 - ER | 0
CHI05-CFCI-1230 | CHI05-02-02-DH-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO2 Cell 2 - DH | 0
CHI05-CFCI-1230 | CHI05-02-02-ER-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO2 Cell 2 - ER | 0
CHI05-CFCI-1230 | CHI05-02-03-DH-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO2 Cell 3 - DH | 0
CHI05-CFCI-1230 | CHI05-02-03-ER-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO2 Cell 3 - ER | 0
CHI05-CFCI-1230 | CHI05-02-04-DH-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO2 Cell 4 - DH | 0
CHI05-CFCI-1230 | CHI05-02-04-ER-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO2 Cell 4 - ER | 0
CHI05-CFCI-1230 | CHI05-03-01-DH-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO3 Cell 1 - DH | 0
CHI05-CFCI-1230 | CHI05-03-01-ER-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO3 Cell 1 - ER | 0
CHI05-CFCI-1230 | CHI05-03-02-DH-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO3 Cell 2 - DH | 0
CHI05-CFCI-1230 | CHI05-03-02-ER-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO3 Cell 2 - ER | 0
CHI05-CFCI-1230 | CHI05-03-03-DH-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO3 Cell 3 - DH | 0
CHI05-CFCI-1230 | CHI05-03-03-ER-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO3 Cell 3 - ER | 0
CHI05-CFCI-1230 | CHI05-03-04-DH-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO3 Cell 4 - DH | 0
CHI05-CFCI-1230 | CHI05-03-04-ER-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO3 Cell 4 - ER | 0
CHI05-CFCI-1230 | CHI05-04-01-DH-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO4 Cell 1 - DH | 0
CHI05-CFCI-1230 | CHI05-04-01-ER-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO4 Cell 1 - ER | 0
CHI05-CFCI-1230 | CHI05-04-02-DH-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO4 Cell 2 - DH | 0
CHI05-CFCI-1230 | CHI05-04-02-ER-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO4 Cell 2 - ER | 0
CHI05-CFCI-1230 | CHI05-04-03-DH-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO4 Cell 3 - DH | 0
CHI05-CFCI-1230 | CHI05-04-03-ER-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO4 Cell 3 - ER | 0
CHI05-CFCI-1230 | CHI05-04-04-DH-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO4 Cell 4 - DH | 0
CHI05-CFCI-1230 | CHI05-04-04-ER-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO4 Cell 4 - ER | 0
CHI05-CFCI-1230 | CHI05-05-01-DH-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO5 Cell 1 - DH | 0
CHI05-CFCI-1230 | CHI05-05-01-ER-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO5 Cell 1 - ER | 0
CHI05-CFCI-1230 | CHI05-05-02-DH-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO5 Cell 2 - DH | 0
CHI05-CFCI-1230 | CHI05-05-02-ER-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO5 Cell 2 - ER | 0
CHI05-CFCI-1230 | CHI05-05-03-DH-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO5 Cell 3 - DH | 0
CHI05-CFCI-1230 | CHI05-05-03-ER-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO5 Cell 3 - ER | 0
CHI05-CFCI-1230 | CHI05-05-04-DH-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Light Fixture - Lead Time | Finishes and Signage - COLO5 Cell 4 - DH | 0
CHI05-CFCI-1230 | CHI05-05-04-ER-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Light Fixture - Lead Time | Finishes and Signage - COLO5 Cell 4 - ER | 0
CHI05-CFCI-1090 | CHI05-02-01-DH-1035 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | HAC's - Lead Time | HAC Placing - COLO2 Cell 1 - DH | 0
CHI05-CFCI-1090 | CHI05-02-02-DH-1190 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | HAC's - Lead Time | HAC Placing - COLO2 Cell 2 - DH | 0
CHI05-CFCI-1090 | CHI05-02-03-DH-1300 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | HAC's - Lead Time | HAC Placing - COLO2 Cell 3 - DH | 0
CHI05-CFCI-1090 | CHI05-02-04-DH-1410 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | HAC's - Lead Time | HAC Placing - COLO2 Cell 4 - DH | 0
CHI05-CFCI-1090 | CHI05-03-01-DH-1190 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | HAC's - Lead Time | HAC Placing - COLO3 Cell 1 - DH | 0
CHI05-CFCI-1090 | CHI05-03-02-DH-1300 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | HAC's - Lead Time | HAC Placing - COLO3 Cell 2 - DH | 0
CHI05-CFCI-1090 | CHI05-03-03-DH-1410 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | HAC's - Lead Time | HAC Placing - COLO3 Cell 3 - DH | 0
CHI05-CFCI-1090 | CHI05-03-04-DH-1520 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | HAC's - Lead Time | HAC Placing - COLO3 Cell 4 - DH | 0
CHI05-CFCI-1090 | CHI05-04-01-DH-1300 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | HAC's - Lead Time | HAC Placing - COLO4 Cell 1 - DH | 0
CHI05-CFCI-1090 | CHI05-04-02-DH-1410 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | HAC's - Lead Time | HAC Placing - COLO4 Cell 2 - DH | 0
CHI05-CFCI-1090 | CHI05-04-03-DH-1520 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | HAC's - Lead Time | HAC Placing - COLO4 Cell 3 - DH | 0
CHI05-CFCI-1090 | CHI05-04-04-DH-1630 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | HAC's - Lead Time | HAC Placing - COLO4 Cell 4 - DH | 0
CHI05-CFCI-1090 | CHI05-05-01-DH-1410 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | HAC's - Lead Time | HAC Placing - COLO5 Cell 1 - DH | 0
CHI05-CFCI-1090 | CHI05-05-02-DH-1520 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | HAC's - Lead Time | HAC Placing - COLO5 Cell 2 - DH | 0
CHI05-CFCI-1090 | CHI05-05-03-DH-1630 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | HAC's - Lead Time | HAC Placing - COLO5 Cell 3 - DH | 0
CHI05-CFCI-1090 | CHI05-05-04-DH-1740 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | HAC's - Lead Time | HAC Placing - COLO5 Cell 4 - DH | 0
CHI05-CFCI-1020 | CHI05-05-NTP-S | FS | Completed | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,2,2,1 General | HAC's - Submittal Preparation | Notice To Proceed | 0
CHI05-CFCI-1000 | CHI05-CFCI-1140 | FS | Completed | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,4,2,9 Doors/Frames/Hardware | DX Split Units - Submittal Preparation | Doors/Frames/Hardware - Submittal Preparation | 0
CHI05-CFCI-1000 | CHI05-CFCI-1030 | SS | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | DX Split Units - Submittal Preparation | AHU (Admin) - Submittal Preparation | 0
CHI05-CFCI-1000 | CHI05-CFCI-1050 | SS | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | DX Split Units - Submittal Preparation | Overhead Cable Bus - Submittal Preparation | 0
CHI05-CFCI-1000 | CHI05-CFCI-1040 | SS | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,4,2,5 Elec. Distribution System | DX Split Units - Submittal Preparation | Elec. Distribution System - Submittal Preparation | 0
CHI05-CFCI-1000 | CHI05-CFCI-1010 | SS | Completed | In Progress | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,4,2,7 Light Fixture | DX Split Units - Submittal Preparation | Light Fixture - Submittal Preparation | 0
CHI05-CFCI-1000 | CHI05-CFCI-1020 | SS | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | DX Split Units - Submittal Preparation | HAC's - Submittal Preparation | 0
CHI05-OFCI-2060 | CHI05-OFCI-2070 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,2 PDU - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,11,2 PDU - COLO 3 | PDU - COLO 3 - Start ROJ | PDU - COLO 3 - ROJ | 0
CHI05-CFCI-1050 | CHI05-CFCI-1180 | FS | Completed | Completed | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,8 Overhead Cable Bus | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | Overhead Cable Bus - Submittal Preparation | Medium Voltage Cabling - Submittal Preparation | 0
CHI05-OFCI-1130 | CHI05-YARD-2000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,1 GENS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | GENS - COLO 2 - In Storage | Set the Generator - Colo 2 - North | 0
CHI05-YARD-2000 | CHI05-YARD-2040 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | Set the Generator - Colo 2 - North | Install MEP raceway conduit and piping - Colo 2 - North | 0
CHI05-YARD-2040 | CHI05-YARD-2140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | Install MEP raceway conduit and piping - Colo 2 - North | Wire pulling and termination for MSB - Colo 2 - North | 0
CHI05-OFCI-1130 | CHI05-OFCI-1140 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,1 GENS - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,5,2 GENS - COLO 3 | GENS - COLO 2 - In Storage | GENS - COLO 3 - In Storage | 0
CHI05-OFCI-1140 | CHI05-OFCI-1150 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,2 GENS - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,5,3 GENS - COLO 4 | GENS - COLO 3 - In Storage | GENS - COLO 4 - In Storage | 0
CHI05-OFCI-1150 | CHI05-OFCI-1160 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,3 GENS - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,5,5 GENS - COLO 5 | GENS - COLO 4 - In Storage | GENS - COLO 5 - In Storage | 0
CHI05-YARD-2060 | CHI05-YARD-2160 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | Set the Generator - Colo 3 - North | Install MEP raceway conduit and piping - Colo 3 - North | 0
CHI05-YARD-2160 | CHI05-YARD-2260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | Install MEP raceway conduit and piping - Colo 3 - North | Wire pulling and termination for MSB - Colo 3 - North | 0
CHI05-YARD-2100 | CHI05-YARD-2240 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | Set the MV Gear - Colo 4 - North | Install MEP raceway conduit and piping - Colo 4 - North | 0
CHI05-YARD-2240 | CHI05-YARD-2310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | Install MEP raceway conduit and piping - Colo 4 - North | Wire pulling and termination for MSB - Colo 4 - North | 0
CHI05-YARD-2300 | CHI05-YARD-2350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | Install MEP raceway conduit and piping - Colo 2 - South | Wire pulling and termination for MSB - Colo 2 - South | 0
CHI05-YARD-2170 | CHI05-YARD-2340 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | Set the MV Gear - Colo 3 - South | Install MEP raceway conduit and piping - Colo 3 - South | 0
CHI05-YARD-2340 | CHI05-YARD-2380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | Install MEP raceway conduit and piping - Colo 3 - South | Wire pulling and termination for MSB - Colo 3 - South | 0
CHI05-YARD-2220 | CHI05-YARD-2370 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | Set the MV Gear - Colo 4 - South | Install MEP raceway conduit and piping - Colo 4 - South | 0
CHI05-YARD-2370 | CHI05-YARD-2420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | Install MEP raceway conduit and piping - Colo 4 - South | Wire pulling and termination for MSB - Colo 4 - South | 0
CHI05-YARD-2070 | CHI05-YARD-2180 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | Set the MV Gear - Colo 5 - East | Install MEP raceway conduit and piping - Colo 5 - East | 0
CHI05-YARD-2180 | CHI05-YARD-2270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | Install MEP raceway conduit and piping - Colo 5 - East | Wire pulling and termination for MSB - Colo 5 - East | 0
CHI05-YARD-2010 | CHI05-YARD-2050 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | Set the MV Gear - Colo 5 - West | Install MEP raceway conduit and piping - Colo 5 - West | 0
CHI05-YARD-2050 | CHI05-YARD-2150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | Install MEP raceway conduit and piping - Colo 5 - West | Wire pulling and termination for MSB - Colo 5 - West | 0
CHI05-YARD-2140 | CHI05-YARD-2360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | Wire pulling and termination for MSB - Colo 2 - North | Install screen wall - Colo 2 - North | 0
CHI05-02-03-L1-1410 | CHI05-02-L1CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Interior - L1 AHUs - COLO2 Cell 3 | Complete L1 Cx (All Red Tags/ROJ) for Colo 2 | 0
CHI05-02-02-L1-1290 | CHI05-02-L1CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Interior - L1 AHUs - COLO2 Cell 2 | Complete L1 Cx (All Red Tags/ROJ) for Colo 2 | 0
CHI05-02-01-L1-1170 | CHI05-02-L1CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Interior - L1 AHUs - COLO2 Cell 1 | Complete L1 Cx (All Red Tags/ROJ) for Colo 2 | 0
CHI05-02-01-L2-1290 | CHI05-02-L2CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Interior - L2 AHUs - COLO2 Cell 1 | Complete L2 CX (Yellow Tag) for Colo 2 | 0
CHI05-02-02-L2-1410 | CHI05-02-L2CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Interior - L2 AHUs - COLO2 Cell 2 | Complete L2 CX (Yellow Tag) for Colo 2 | 0
CHI05-02-03-L2-1530 | CHI05-02-L2CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Interior - L2 AHUs - COLO2 Cell 3 | Complete L2 CX (Yellow Tag) for Colo 2 | 0
CHI05-CFCI-1000 | CHI05-OFCI-1130 | FS | Completed | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,4,1,5,1 GENS - COLO 2 | DX Split Units - Submittal Preparation | GENS - COLO 2 - In Storage | 0
CHI05-YARD-2150 | CHI05-YARD-2250 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | Wire pulling and termination for MSB - Colo 5 - West | Install screen wall - Colo 5 - West | 5
CHI05-YARD-2430 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Install screen wall - Colo 4 - North | Site Secured Finish (August 04, 2025) | 0
CHI05-03-01-L2-1410 | CHI05-03-01-L3-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L2 AHUs - COLO3 Cell 1 | Interior - L3 AHUs - COLO3 Cell 1 | 0
CHI05-05-04-ER-1720 | CHI05-03-02-L3-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Installation of UPS Equipment - COLO5 Cell 4 - ER | Interior - L3 UPS - COLO3 Cell 2 | 0
CHI05-03-02-L2-1530 | CHI05-03-02-L3-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L2 AHUs - COLO3 Cell 2 | Interior - L3 AHUs - COLO3 Cell 2 | 0
CHI05-03-03-L1-1530 | CHI05-03-03-L3-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | Interior - L1 AHUs - COLO3 Cell 3 | Interior - L3 AHUs - COLO3 Cell 3 | 0
CHI05-03-03-L2-1650 | CHI05-03-03-L3-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | Interior - L2 AHUs - COLO3 Cell 3 | Interior - L3 AHUs - COLO3 Cell 3 | 0
CHI05-03-04-L1-1650 | CHI05-03-04-L2-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L1 AHUs - COLO3 Cell 4 | Interior - L2 AHUs - COLO3 Cell 4 | 0
CHI05-03-04-L2-1770 | CHI05-03-04-L3-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L2 AHUs - COLO3 Cell 4 | Interior - L3 AHUs - COLO3 Cell 4 | 0
CHI05-04-01-L2-1530 | CHI05-04-01-L3-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L2 AHUs - COLO4 Cell 1 | Interior - L3 AHUs - COLO4 Cell 1 | 0
CHI05-04-02-L1-1610 | CHI05-04-02-L2-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L1 ADP - COLO4 Cell 2 | Interior - L2 UPS - COLO4 Cell 2 | 0
CHI05-03-02-L1-1410 | CHI05-03-02-L2-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L1 AHUs - COLO3 Cell 2 | Interior - L2 AHUs - COLO3 Cell 2 | 0
CHI05-04-02-L1-1530 | CHI05-04-02-L2-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L1 AHUs - COLO4 Cell 2 | Interior - L2 AHUs - COLO4 Cell 2 | 0
CHI05-05-01-L1-1530 | CHI05-05-01-L2-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L1 AHUs - COLO5 Cell 1 | Interior - L2 AHUs - COLO5 Cell 1 | 0
CHI05-05-01-L2-1650 | CHI05-05-01-L3-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L2 AHUs - COLO5 Cell 1 | Interior - L3 AHUs - COLO5 Cell 1 | 0
CHI05-05-01-L1-1500 | CHI05-05-02-L1-1620 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Interior - L1 UPS - COLO5 Cell 1 | Interior - L1 UPS - COLO5 Cell 2 | 0
CHI05-05-02-L1-1650 | CHI05-05-02-L2-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L1 AHUs - COLO5 Cell 2 | Interior - L2 AHUs - COLO5 Cell 2 | 0
CHI05-05-02-L2-1770 | CHI05-05-02-L3-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L2 AHUs - COLO5 Cell 2 | Interior - L3 AHUs - COLO5 Cell 2 | 0
CHI05-05-03-L1-1770 | CHI05-05-03-L2-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L1 AHUs - COLO5 Cell 3 | Interior - L2 AHUs - COLO5 Cell 3 | 0
CHI05-05-03-L2-1890 | CHI05-05-03-L3-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L2 AHUs - COLO5 Cell 3 | Interior - L3 AHUs - COLO5 Cell 3 | 0
CHI05-05-02-L1-1620 | CHI05-05-03-L1-1740 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Interior - L1 UPS - COLO5 Cell 2 | Interior - L1 UPS - COLO5 Cell 3 | 0
CHI05-05-04-L1-1890 | CHI05-05-04-L2-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L1 AHUs - COLO5 Cell 4 | Interior - L2 AHUs - COLO5 Cell 4 | 0
CHI05-05-04-L2-2010 | CHI05-05-04-L3-2130 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L2 AHUs - COLO5 Cell 4 | Interior - L3 AHUs - COLO5 Cell 4 | 0
CHI05-05-03-L1-1740 | CHI05-05-04-L1-1860 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Interior - L1 UPS - COLO5 Cell 3 | Interior - L1 UPS - COLO5 Cell 4 | 0
CHI05-05-04-L1-1860 | CHI05-02-01-L1-1140 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Interior - L1 UPS - COLO5 Cell 4 | Interior - L1 UPS - COLO2 Cell 1 | 0
CHI05-02-01-L1-1170 | CHI05-02-01-L2-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L1 AHUs - COLO2 Cell 1 | Interior - L2 AHUs - COLO2 Cell 1 | 0
CHI05-02-01-L2-1290 | CHI05-02-01-L3-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L2 AHUs - COLO2 Cell 1 | Interior - L3 AHUs - COLO2 Cell 1 | 0
CHI05-02-01-L1-1140 | CHI05-02-02-L1-1260 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Interior - L1 UPS - COLO2 Cell 1 | Interior - L1 UPS - COLO2 Cell 2 | 0
CHI05-02-02-L1-1260 | CHI05-02-03-L1-1380 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Interior - L1 UPS - COLO2 Cell 2 | Interior - L1 UPS - COLO2 Cell 3 | 0
CHI05-02-03-L1-1380 | CHI05-02-04-L1-1500 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Interior - L1 UPS - COLO2 Cell 3 | Interior - L1 UPS - COLO2 Cell 4 | 0
CHI05-03-01-L1-1290 | CHI05-03-01-L2-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L1 AHUs - COLO3 Cell 1 | Interior - L2 AHUs - COLO3 Cell 1 | 0
CHI05-03-01-L1-1260 | CHI05-03-02-L1-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Interior - L1 UPS - COLO3 Cell 1 | Interior - L1 UPS - COLO3 Cell 2 | 0
CHI05-03-02-L1-1380 | CHI05-03-03-L1-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | Interior - L1 UPS - COLO3 Cell 2 | Interior - L1 UPS - COLO3 Cell 3 | 0
CHI05-03-03-L1-1500 | CHI05-03-04-L1-1620 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Interior - L1 UPS - COLO3 Cell 3 | Interior - L1 UPS - COLO3 Cell 4 | 0
CHI05-04-01-L1-1410 | CHI05-04-01-L2-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L1 AHUs - COLO4 Cell 1 | Interior - L2 AHUs - COLO4 Cell 1 | 0
CHI05-04-01-L3-1640 | CHI05-04-01-L3-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L3 PDUs - COLO4 Cell 1 | Interior - L3 ATSs - COLO4 Cell 1 | 0
CHI05-04-01-L3-1660 | CHI05-04-01-L3-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L3 ATSs - COLO4 Cell 1 | Interior - L3 Busway - COLO4 Cell 1 | 0
CHI05-04-02-L2-1650 | CHI05-04-02-L3-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L2 AHUs - COLO4 Cell 2 | Interior - L3 AHUs - COLO4 Cell 2 | 0
CHI05-04-03-L3-1900 | CHI05-04-03-L3-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L3 ATSs - COLO4 Cell 3 | Interior - L3 Busway - COLO4 Cell 3 | 0
CHI05-04-04-L3-2020 | CHI05-04-04-L3-2030 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L3 ATSs - COLO4 Cell 4 | Interior - L3 Busway - COLO4 Cell 4 | 0
CHI05-03-L1CX-F | CHI05-03-04-L2-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Complete L1 Cx (All Red Tags/ROJ) for Colo 3 | Interior - L2 AHUs - COLO3 Cell 4 | 0
CHI05-03-L2CX-F | CHI05-03-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Complete L2 CX (Yellow Tag) for Colo 3 | Complete L3 CX (Green Tag) for Colo 3 | 0
CHI05-03-L3CX-F | CHI05-03-L4CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Complete L3 CX (Green Tag) for Colo 3 | Complete L4 Cx (Blue Tag) for Colo 3 | 0
CHI05-04-L2CX-F | CHI05-04-04-L3-2010 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Complete L2 CX (Yellow Tag) for Colo 4 | Interior - L3 AHUs - COLO4 Cell 4 | 0
CHI05-05-L2CX-F | CHI05-05-04-L3-2130 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Complete L2 CX (Yellow Tag) for Colo 5 | Interior - L3 AHUs - COLO5 Cell 4 | 0
CHI05-05-01-MG-1330 | CHI05-02-01-MG-1000 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 1 - MG | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG | 0
CHI05-YARD-2120 | CHI05-YARD-2300 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | Set the Generator - Colo 2 - South | Install MEP raceway conduit and piping - Colo 2 - South | 0
CHI05-YARD-2420 | CHI05-YARD-2470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | Wire pulling and termination for MSB - Colo 4 - South | Install screen wall - Colo 4 - South | 0
CHI05-YARD-2470 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Install screen wall - Colo 4 - South | Site Secured Finish (August 04, 2025) | 0
CHI05-04-01-L1-1380 | CHI05-04-02-L1-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Interior - L1 UPS - COLO4 Cell 1 | Interior - L1 UPS - COLO4 Cell 2 | 0
CHI05-04-02-L1-1500 | CHI05-04-03-L1-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Interior - L1 UPS - COLO4 Cell 2 | Interior - L1 UPS - COLO4 Cell 3 | 0
CHI05-04-03-L1-1620 | CHI05-04-04-L1-1740 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Interior - L1 UPS - COLO4 Cell 3 | Interior - L1 UPS - COLO4 Cell 4 | 0
CHI05-YARD-2270 | CHI05-YARD-2320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | Wire pulling and termination for MSB - Colo 5 - East | Install screen wall - Colo 5 - East | 0
CHI05-OFCI-1000 | CHI05-02-01-MG-1030 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,1 AHU - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | AHU - COLO 2 - In Storage | Deliver AHU into Mech. Gallery - COLO2 Cell 1 - MG | 0
CHI05-OFCI-1000 | CHI05-02-02-MG-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,1 AHU - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | AHU - COLO 2 - In Storage | Deliver AHU into Mech. Gallery - COLO2 Cell 2 - MG | 0
CHI05-OFCI-1000 | CHI05-02-03-MG-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,1 AHU - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | AHU - COLO 2 - In Storage | Deliver AHU into Mech. Gallery - COLO2 Cell 3 - MG | 0
CHI05-OFCI-1000 | CHI05-02-04-MG-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,1 AHU - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | AHU - COLO 2 - In Storage | Deliver AHU into Mech. Gallery - COLO2 Cell 4 - MG | 0
CHI05-OFCI-1450 | CHI05-03-01-MG-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,2 AHU - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | AHU - COLO 3 - In Storage | Deliver AHU into Mech. Gallery - COLO3 Cell 1 - MG | 0
CHI05-OFCI-1450 | CHI05-03-02-MG-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,2 AHU - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | AHU - COLO 3 - In Storage | Deliver AHU into Mech. Gallery - COLO3 Cell 2 - MG | 0
CHI05-OFCI-1450 | CHI05-03-03-MG-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,2 AHU - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | AHU - COLO 3 - In Storage | Deliver AHU into Mech. Gallery - COLO3 Cell 3 - MG | 0
CHI05-OFCI-1450 | CHI05-03-04-MG-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,2 AHU - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | AHU - COLO 3 - In Storage | Deliver AHU into Mech. Gallery - COLO3 Cell 4 - MG | 0
CHI05-OFCI-1480 | CHI05-04-01-MG-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,3 AHU - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | AHU - COLO 4 - Finish ROJ | Deliver AHU into Mech. Gallery - COLO4 Cell 1 - MG | 0
CHI05-OFCI-1480 | CHI05-04-02-MG-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,3 AHU - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | AHU - COLO 4 - Finish ROJ | Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG | 0
CHI05-OFCI-1480 | CHI05-04-03-MG-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,3 AHU - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | AHU - COLO 4 - Finish ROJ | Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG | 0
CHI05-OFCI-1480 | CHI05-04-04-MG-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,3 AHU - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | AHU - COLO 4 - Finish ROJ | Deliver AHU into Mech. Gallery - COLO4 Cell 4 - MG | 0
CHI05-OFCI-1490 | CHI05-05-01-MG-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,5 AHU - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | AHU - COLO 5 - Finish ROJ | Deliver AHU into Mech. Gallery - COLO5 Cell 1 - MG | 0
CHI05-OFCI-1490 | CHI05-05-02-MG-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,5 AHU - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | AHU - COLO 5 - Finish ROJ | Deliver AHU into Mech. Gallery - COLO5 Cell 2 - MG | 0
CHI05-OFCI-1490 | CHI05-05-03-MG-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,5 AHU - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | AHU - COLO 5 - Finish ROJ | Deliver AHU into Mech. Gallery - COLO5 Cell 3 - MG | 0
CHI05-OFCI-1490 | CHI05-05-04-MG-1690 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,5 AHU - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | AHU - COLO 5 - Finish ROJ | Deliver AHU into Mech. Gallery - COLO5 Cell 4 - MG | 0
CHI05-OFCI-1970 | CHI05-02-01-ER-1050 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,1 ATS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | ATS - COLO 2 - Finish ROJ | Installation of ADP & ATS - COLO2 Cell 1 - ER | 0
CHI05-OFCI-1970 | CHI05-02-02-ER-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,1 ATS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | ATS - COLO 2 - Finish ROJ | Installation of ADP & ATS - COLO2 Cell 2 - ER | 0
CHI05-OFCI-1970 | CHI05-02-03-ER-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,1 ATS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | ATS - COLO 2 - Finish ROJ | Installation of ADP & ATS - COLO2 Cell 3 - ER | 0
CHI05-OFCI-1970 | CHI05-02-04-ER-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,1 ATS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | ATS - COLO 2 - Finish ROJ | Installation of ADP & ATS - COLO2 Cell 4 - ER | 0
CHI05-OFCI-1140 | CHI05-03-01-L1-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,2 GENS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | GENS - COLO 3 - In Storage | L1 GEN - COLO3 | 0
CHI05-OFCI-1150 | CHI05-04-01-L1-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,3 GENS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | GENS - COLO 4 - In Storage | L1 GEN - COLO4 | 0
CHI05-OFCI-1160 | CHI05-05-01-L1-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,5 GENS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | GENS - COLO 5 - In Storage | L1 GEN - COLO5 | 0
CHI05-OFCI-1990 | CHI05-02-01-ER-1050 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,1 LVS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | LVS - COLO 2 - Finish ROJ | Installation of ADP & ATS - COLO2 Cell 1 - ER | 0
CHI05-OFCI-1990 | CHI05-02-02-ER-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,1 LVS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | LVS - COLO 2 - Finish ROJ | Installation of ADP & ATS - COLO2 Cell 2 - ER | 0
CHI05-OFCI-1990 | CHI05-02-03-ER-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,1 LVS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | LVS - COLO 2 - Finish ROJ | Installation of ADP & ATS - COLO2 Cell 3 - ER | 0
CHI05-OFCI-1990 | CHI05-02-04-ER-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,1 LVS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | LVS - COLO 2 - Finish ROJ | Installation of ADP & ATS - COLO2 Cell 4 - ER | 0
CHI05-OFCI-2100 | CHI05-03-01-ER-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,2 LVS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | LVS - COLO 3 - Finish ROJ | Installation of ADP & ATS - COLO3 Cell 1 - ER | 0
CHI05-OFCI-2100 | CHI05-03-02-ER-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,2 LVS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | LVS - COLO 3 - Finish ROJ | Installation of ADP & ATS - COLO3 Cell 2 - ER | 0
CHI05-OFCI-2100 | CHI05-03-03-ER-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,2 LVS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | LVS - COLO 3 - Finish ROJ | Installation of ADP & ATS - COLO3 Cell 3 - ER | 0
CHI05-OFCI-2100 | CHI05-03-04-ER-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,2 LVS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | LVS - COLO 3 - Finish ROJ | Installation of ADP & ATS - COLO3 Cell 4 - ER | 0
CHI05-OFCI-2280 | CHI05-04-01-ER-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,3 LVS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | LVS - COLO 4 - Finish ROJ | Installation of ADP & ATS - COLO4 Cell 1 - ER | 0
CHI05-OFCI-2280 | CHI05-04-02-ER-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,3 LVS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | LVS - COLO 4 - Finish ROJ | Installation of ADP & ATS - COLO4 Cell 2 - ER | 0
CHI05-OFCI-2280 | CHI05-04-03-ER-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,3 LVS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | LVS - COLO 4 - Finish ROJ | Installation of ADP & ATS - COLO4 Cell 3 - ER | 0
CHI05-OFCI-2280 | CHI05-04-04-ER-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,3 LVS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | LVS - COLO 4 - Finish ROJ | Installation of ADP & ATS - COLO4 Cell 4 - ER | 0
CHI05-OFCI-2110 | CHI05-05-01-ER-1380 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,5 LVS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | LVS - COLO 5 - Finish ROJ | Installation of ADP & ATS - COLO5 Cell 1 - ER | 0
CHI05-OFCI-2110 | CHI05-05-02-ER-1490 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,5 LVS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | LVS - COLO 5 - Finish ROJ | Installation of ADP & ATS - COLO5 Cell 2 - ER | 0
CHI05-OFCI-2110 | CHI05-05-03-ER-1600 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,5 LVS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | LVS - COLO 5 - Finish ROJ | Installation of ADP & ATS - COLO5 Cell 3 - ER | 0
CHI05-OFCI-2110 | CHI05-05-04-ER-1710 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,5 LVS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | LVS - COLO 5 - Finish ROJ | Installation of ADP & ATS - COLO5 Cell 4 - ER | 0
CHI05-OFCI-1820 | CHI05-02-01-DH-1040 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,1 PDU - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | PDU - COLO 2 - Finish ROJ | Install PDU's - COLO2 Cell 1 - DH | 0
CHI05-OFCI-1820 | CHI05-02-02-DH-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,1 PDU - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | PDU - COLO 2 - Finish ROJ | Install PDU's - COLO2 Cell 2 - DH | 0
CHI05-OFCI-1820 | CHI05-02-03-DH-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,1 PDU - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | PDU - COLO 2 - Finish ROJ | Install PDU's - COLO2 Cell 3 - DH | 0
CHI05-OFCI-1820 | CHI05-02-04-DH-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,1 PDU - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | PDU - COLO 2 - Finish ROJ | Install PDU's - COLO2 Cell 4 - DH | 0
CHI05-OFCI-2160 | CHI05-03-01-DH-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,2 PDU - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | PDU - COLO 3 - Finish ROJ | Install PDU's - COLO3 Cell 1 - DH | 0
CHI05-OFCI-2160 | CHI05-03-02-DH-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,2 PDU - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | PDU - COLO 3 - Finish ROJ | Install PDU's - COLO3 Cell 2 - DH | 0
CHI05-OFCI-2160 | CHI05-03-03-DH-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,2 PDU - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | PDU - COLO 3 - Finish ROJ | Install PDU's - COLO3 Cell 3 - DH | 0
CHI05-OFCI-2160 | CHI05-03-04-DH-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,2 PDU - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | PDU - COLO 3 - Finish ROJ | Install PDU's - COLO3 Cell 4 - DH | 0
CHI05-OFCI-2170 | CHI05-04-01-DH-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,3 PDU - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | PDU - COLO 4 - Finish ROJ | Install PDU's - COLO4 Cell 1 - DH | 0
CHI05-OFCI-2170 | CHI05-04-02-DH-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,3 PDU - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | PDU - COLO 4 - Finish ROJ | Install PDU's - COLO4 Cell 2 - DH | 0
CHI05-OFCI-2170 | CHI05-04-03-DH-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,3 PDU - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | PDU - COLO 4 - Finish ROJ | Install PDU's - COLO4 Cell 3 - DH | 0
CHI05-OFCI-2170 | CHI05-04-04-DH-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,3 PDU - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | PDU - COLO 4 - Finish ROJ | Install PDU's - COLO4 Cell 4 - DH | 0
CHI05-OFCI-1830 | CHI05-05-01-DH-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,5 PDU - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | PDU - COLO 5 - Finish ROJ | Install PDU's - COLO5 Cell 1 - DH | 0
CHI05-OFCI-1830 | CHI05-05-02-DH-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,5 PDU - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | PDU - COLO 5 - Finish ROJ | Install PDU's - COLO5 Cell 2 - DH | 0
CHI05-OFCI-1830 | CHI05-05-03-DH-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,5 PDU - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | PDU - COLO 5 - Finish ROJ | Install PDU's - COLO5 Cell 3 - DH | 0
CHI05-OFCI-1830 | CHI05-05-04-DH-1710 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,5 PDU - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | PDU - COLO 5 - Finish ROJ | Install PDU's - COLO5 Cell 4 - DH | 0
CHI05-OFCI-1310 | CHI05-02-01-ER-1070 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,1 UPS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | UPS - COLO 2 - In storage | Installation of UPS Equipment - COLO2 Cell 1 - ER | 0
CHI05-OFCI-1310 | CHI05-02-02-ER-1170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,1 UPS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | UPS - COLO 2 - In storage | Installation of UPS Equipment - COLO2 Cell 2 - ER | 0
CHI05-OFCI-1310 | CHI05-02-03-ER-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,1 UPS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | UPS - COLO 2 - In storage | Installation of UPS Equipment - COLO2 Cell 3 - ER | 0
CHI05-OFCI-1310 | CHI05-02-04-ER-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,1 UPS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | UPS - COLO 2 - In storage | Installation of UPS Equipment - COLO2 Cell 4 - ER | 0
CHI05-OFCI-1320 | CHI05-03-01-ER-1170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,2 UPS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | UPS - COLO 3 - In storage | Installation of UPS Equipment - COLO3 Cell 1 - ER | 0
CHI05-OFCI-1320 | CHI05-03-02-ER-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,2 UPS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | UPS - COLO 3 - In storage | Installation of UPS Equipment - COLO3 Cell 2 - ER | 0
CHI05-OFCI-1320 | CHI05-03-03-ER-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,2 UPS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | UPS - COLO 3 - In storage | Installation of UPS Equipment - COLO3 Cell 3 - ER | 0
CHI05-OFCI-1320 | CHI05-03-04-ER-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,2 UPS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | UPS - COLO 3 - In storage | Installation of UPS Equipment - COLO3 Cell 4 - ER | 0
CHI05-OFCI-1330 | CHI05-04-01-ER-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,3 UPS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | UPS - COLO 4 - In storage | Installation of UPS Equipment - COLO4 Cell 1 - ER | 0
CHI05-OFCI-1330 | CHI05-04-02-ER-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,3 UPS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | UPS - COLO 4 - In storage | Installation of UPS Equipment - COLO4 Cell 2 - ER | 0
CHI05-OFCI-1330 | CHI05-04-03-ER-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,3 UPS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | UPS - COLO 4 - In storage | Installation of UPS Equipment - COLO4 Cell 3 - ER | 0
CHI05-OFCI-1330 | CHI05-04-04-ER-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,3 UPS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | UPS - COLO 4 - In storage | Installation of UPS Equipment - COLO4 Cell 4 - ER | 0
CHI05-OFCI-1560 | CHI05-05-01-ER-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,5 UPS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | UPS - COLO 5 - Finish ROJ | Installation of UPS Equipment - COLO5 Cell 1 - ER | 0
CHI05-OFCI-1560 | CHI05-05-02-ER-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,5 UPS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | UPS - COLO 5 - Finish ROJ | Installation of UPS Equipment - COLO5 Cell 2 - ER | 0
CHI05-OFCI-1560 | CHI05-05-03-ER-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,5 UPS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | UPS - COLO 5 - Finish ROJ | Installation of UPS Equipment - COLO5 Cell 3 - ER | 0
CHI05-OFCI-1560 | CHI05-05-04-ER-1720 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,12,5 UPS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | UPS - COLO 5 - Finish ROJ | Installation of UPS Equipment - COLO5 Cell 4 - ER | 0
CHI05-OFCI-1650 | CHI05-02-01-ER-1040 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,1 BAS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | BAS - COLO 2 - Finish ROJ | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER | 0
CHI05-OFCI-1650 | CHI05-02-02-ER-1150 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,1 BAS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | BAS - COLO 2 - Finish ROJ | Below Ceiling MEP Rough In - COLO2 Cell 2 - ER | 0
CHI05-OFCI-1650 | CHI05-02-03-ER-1260 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,1 BAS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | BAS - COLO 2 - Finish ROJ | Below Ceiling MEP Rough In - COLO2 Cell 3 - ER | 0
CHI05-OFCI-1650 | CHI05-02-04-ER-1370 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,1 BAS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | BAS - COLO 2 - Finish ROJ | Below Ceiling MEP Rough In - COLO2 Cell 4 - ER | 0
CHI05-OFCI-2230 | CHI05-03-01-ER-1150 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,2 BAS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | BAS - COLO 3 - Finish ROJ | Below Ceiling MEP Rough In - COLO3 Cell 1 - ER | 0
CHI05-OFCI-2230 | CHI05-03-02-ER-1260 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,2 BAS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | BAS - COLO 3 - Finish ROJ | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | 0
CHI05-OFCI-2230 | CHI05-03-03-ER-1370 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,2 BAS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | BAS - COLO 3 - Finish ROJ | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | 0
CHI05-OFCI-2230 | CHI05-03-04-ER-1480 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,2 BAS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | BAS - COLO 3 - Finish ROJ | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | 0
CHI05-OFCI-2240 | CHI05-04-01-ER-1260 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,3 BAS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | BAS - COLO 4 - Finish ROJ | Below Ceiling MEP Rough In - COLO4 Cell 1 - ER | 0
CHI05-OFCI-2240 | CHI05-04-02-ER-1370 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,3 BAS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | BAS - COLO 4 - Finish ROJ | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | 0
CHI05-OFCI-2240 | CHI05-04-03-ER-1480 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,3 BAS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | BAS - COLO 4 - Finish ROJ | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | 0
CHI05-OFCI-2240 | CHI05-04-04-ER-1590 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,3 BAS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | BAS - COLO 4 - Finish ROJ | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | 0
CHI05-OFCI-1660 | CHI05-05-01-ER-1370 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,5 BAS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | BAS - COLO 5 - Finish ROJ | Below Ceiling MEP Rough In - COLO5 Cell 1 - ER | 0
CHI05-OFCI-1660 | CHI05-05-02-ER-1480 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,5 BAS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | BAS - COLO 5 - Finish ROJ | Below Ceiling MEP Rough In - COLO5 Cell 2 - ER | 0
CHI05-OFCI-1660 | CHI05-05-03-ER-1590 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,5 BAS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | BAS - COLO 5 - Finish ROJ | Below Ceiling MEP Rough In - COLO5 Cell 3 - ER | 0
CHI05-OFCI-1660 | CHI05-05-04-ER-1700 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,5 BAS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | BAS - COLO 5 - Finish ROJ | Below Ceiling MEP Rough In - COLO5 Cell 4 - ER | 0
CHI05-05-01-L1-1580 | CHI05-05-01-L1-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | L1 UPM - COLO5 | Interior - L1 UPS - COLO5 Cell 1 | 0
CHI05-05-01-L2-1700 | CHI05-05-01-L2-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | L2 UPM - COLO5 | Interior - L2 UPS - COLO5 Cell 1 | 0
CHI05-02-01-L2-1340 | CHI05-02-01-L2-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | L2 UPM - COLO2 | Interior - L2 UPS - COLO2 Cell 1 | 0
CHI05-03-01-L1-1340 | CHI05-03-01-L1-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | L1 UPM - COLO3 | Interior - L1 UPS - COLO3 Cell 1 | 0
CHI05-03-01-L2-1460 | CHI05-03-01-L2-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | L2 UPM - COLO3 | Interior - L2 UPS - COLO3 Cell 1 | 0
CHI05-04-01-L1-1460 | CHI05-04-01-L1-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | L1 UPM - COLO4 | Interior - L1 UPS - COLO4 Cell 1 | 0
CHI05-04-01-L2-1580 | CHI05-04-01-L2-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | L2 UPM - COLO4 | Interior - L2 UPS - COLO4 Cell 1 | 0
CHI05-05-01-L2-1680 | CHI05-05-L2CX-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | L2 UTS / UTSR - Site | Start L2 CX (Yellow Tag) for Colo 5 | 0
CHI05-02-01-L3-1440 | CHI05-02-L3CX-S | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | L3 UTS / UTSR - Site | Start L3 Cx (Green tag) for Colo 2 | 0
CHI05-02-01-L1-1200 | CHI05-02-L1CX-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | L1 UTS / UTSR - Site | Start L1 CX (Red Tag) for Colo 2 | 0
CHI05-OFCI-1650 | CHI05-02-BAS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,1 BAS - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | BAS - COLO 2 - Finish ROJ | Complete BAS SAT for Colo 2 | 0
CHI05-OFCI-1120 | CHI05-02-EPMS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,4,1 EPMS - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | EPMS - COLO 2 | Complete EPMS SAT for Colo 2 | 0
CHI05-OFCI-2020 | CHI05-OFCI-2040 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,2 Busway/Bus Plugs - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,3,3 Busway/Bus Plugs - COLO 4 | Busway/Bus Plugs - COLO 3 - Start ROJ | Busway/Bus Plugs - COLO 4 - Start ROJ | 0
CHI05-04-04-MG-1590 | CHI05-04-04-DH-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Install Walls and Primer Paint - COLO4 Cell 4 - MG | Security Screen Installation - COLO4 Cell 4 - DH | 0
CHI05-05-01-MG-1370 | CHI05-05-01-DH-1360 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Install Walls and Primer Paint - COLO5 Cell 1 - MG | Security Screen Installation - COLO5 Cell 1 - DH | 0
CHI05-05-02-MG-1480 | CHI05-05-02-DH-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Install Walls and Primer Paint - COLO5 Cell 2 - MG | Security Screen Installation - COLO5 Cell 2 - DH | 0
CHI05-05-03-MG-1590 | CHI05-05-03-DH-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Install Walls and Primer Paint - COLO5 Cell 3 - MG | Security Screen Installation - COLO5 Cell 3 - DH | 0
CHI05-05-04-MG-1700 | CHI05-05-04-DH-1690 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Install Walls and Primer Paint - COLO5 Cell 4 - MG | Security Screen Installation - COLO5 Cell 4 - DH | 0
CHI05-02-01-MG-1040 | CHI05-02-01-DH-1010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Install Walls and Primer Paint - COLO2 Cell 1 - MG | Security Screen Installation - COLO2 Cell 1 - DH | 0
CHI05-02-02-MG-1150 | CHI05-02-02-DH-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Install Walls and Primer Paint - COLO2 Cell 2 - MG | Security Screen Installation - COLO2 Cell 2 - DH | 0
CHI05-02-03-MG-1260 | CHI05-02-03-DH-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Install Walls and Primer Paint - COLO2 Cell 3 - MG | Security Screen Installation - COLO2 Cell 3 - DH | 0
CHI05-02-04-MG-1370 | CHI05-02-04-DH-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Install Walls and Primer Paint - COLO2 Cell 4 - MG | Security Screen Installation - COLO2 Cell 4 - DH | 0
CHI05-03-01-MG-1150 | CHI05-03-01-DH-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Install Walls and Primer Paint - COLO3 Cell 1 - MG | Security Screen Installation - COLO3 Cell 1 - DH | 0
CHI05-03-02-MG-1260 | CHI05-03-02-DH-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Install Walls and Primer Paint - COLO3 Cell 2 - MG | Security Screen Installation - COLO3 Cell 2 - DH | 0
CHI05-03-03-MG-1370 | CHI05-03-03-DH-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Install Walls and Primer Paint - COLO3 Cell 3 - MG | Security Screen Installation - COLO3 Cell 3 - DH | 0
CHI05-03-04-MG-1480 | CHI05-03-04-DH-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Install Walls and Primer Paint - COLO3 Cell 4 - MG | Security Screen Installation - COLO3 Cell 4 - DH | 0
CHI05-04-01-MG-1260 | CHI05-04-01-DH-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Install Walls and Primer Paint - COLO4 Cell 1 - MG | Security Screen Installation - COLO4 Cell 1 - DH | 0
CHI05-04-02-MG-1370 | CHI05-04-02-DH-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Install Walls and Primer Paint - COLO4 Cell 2 - MG | Security Screen Installation - COLO4 Cell 2 - DH | 0
CHI05-04-03-MG-1480 | CHI05-04-03-DH-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Install Walls and Primer Paint - COLO4 Cell 3 - MG | Security Screen Installation - COLO4 Cell 3 - DH | 0
CHI05-OFCI-1000 | CHI05-OFCI-1010 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,1 AHU - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,1,5 AHU - COLO 5 | AHU - COLO 2 - In Storage | AHU - COLO 5 - Start ROJ | 0
CHI05-OFCI-1650 | CHI05-OFCI-1680 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,1 BAS - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,6,2 BAS - COLO 3 | BAS - COLO 2 - Finish ROJ | BAS - COLO 3 - Start ROJ | 0
CHI05-OFCI-1680 | CHI05-OFCI-1700 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,6,2 BAS - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,6,3 BAS - COLO 4 | BAS - COLO 3 - Start ROJ | BAS - COLO 4 - Start ROJ | 0
CHI05-OFCI-1840 | CHI05-OFCI-1930 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,1 LVS - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,7,2 LVS - COLO 3 | LVS - COLO 2 - Start ROJ | LVS - COLO 3 - Start ROJ | 6
CHI05-OFCI-1930 | CHI05-OFCI-1950 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,2 LVS - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,7,5 LVS - COLO 5 | LVS - COLO 3 - Start ROJ | LVS - COLO 5 - Start ROJ | 0
CHI05-OFCI-2060 | CHI05-OFCI-2080 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,2 PDU - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,11,3 PDU - COLO 4 | PDU - COLO 3 - Start ROJ | PDU - COLO 4 - Start ROJ | 0
CHI05-OFCI-1610 | CHI05-OFCI-1630 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,11,1 PDU - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,11,5 PDU - COLO 5 | PDU - COLO 2 - Start ROJ | PDU - COLO 5 - Start ROJ | 0
CHI05-OFCI-1400 | CHI05-OFCI-1410 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,14,3 MVS (UPM) Terminators/Lighting Arrestors - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,14,3 MVS (UPM) Terminators/Lighting Arrestors - COLO 4 | MVS (UPM) Terminators/Lighting Arrestors - COLO 4 - Start ROJ | MVS (UPM) Terminators/Lighting Arrestors - COLO 4 - ROJ | 0
CHI05-OFCI-1410 | CHI05-OFCI-2210 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,14,3 MVS (UPM) Terminators/Lighting Arrestors - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,14,3 MVS (UPM) Terminators/Lighting Arrestors - COLO 4 | MVS (UPM) Terminators/Lighting Arrestors - COLO 4 - ROJ | MVS (UPM) Terminators/Lighting Arrestors - COLO 4 - Finish ROJ | 0
CHI05-OFCI-1420 | CHI05-OFCI-1430 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,14,5 MVS (UPM) Terminators/Lighting Arrestors - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,14,5 MVS (UPM) Terminators/Lighting Arrestors - COLO 5 | MVS (UPM) Terminators/Lighting Arrestors - COLO 5 - Start ROJ | MVS (UPM) Terminators/Lighting Arrestors - COLO 5 - ROJ | 0
CHI05-OFCI-1430 | CHI05-OFCI-2220 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,14,5 MVS (UPM) Terminators/Lighting Arrestors - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,14,5 MVS (UPM) Terminators/Lighting Arrestors - COLO 5 | MVS (UPM) Terminators/Lighting Arrestors - COLO 5 - ROJ | MVS (UPM) Terminators/Lighting Arrestors - COLO 5 - Finish ROJ | 0
CHI05-OFCI-1360 | CHI05-OFCI-1370 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,14,1 MVS (UPM) Terminators/Lighting Arrestors - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,14,1 MVS (UPM) Terminators/Lighting Arrestors - COLO 2 | MVS (UPM) Terminators/Lighting Arrestors - COLO 2 - Start ROJ | MVS (UPM) Terminators/Lighting Arrestors - COLO 2 - ROJ | 0
CHI05-OFCI-1370 | CHI05-OFCI-2120 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,14,1 MVS (UPM) Terminators/Lighting Arrestors - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,14,1 MVS (UPM) Terminators/Lighting Arrestors - COLO 2 | MVS (UPM) Terminators/Lighting Arrestors - COLO 2 - ROJ | MVS (UPM) Terminators/Lighting Arrestors - COLO 2 - Finish ROJ | 0
CHI05-OFCI-1380 | CHI05-OFCI-1390 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,14,2 MVS (UPM) Terminators/Lighting Arrestors - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,14,2 MVS (UPM) Terminators/Lighting Arrestors - COLO 3 | MVS (UPM) Terminators/Lighting Arrestors - COLO 3 - Start ROJ | MVS (UPM) Terminators/Lighting Arrestors - COLO 3 - ROJ | 0
CHI05-OFCI-1390 | CHI05-OFCI-2200 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,14,2 MVS (UPM) Terminators/Lighting Arrestors - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,14,2 MVS (UPM) Terminators/Lighting Arrestors - COLO 3 | MVS (UPM) Terminators/Lighting Arrestors - COLO 3 - ROJ | MVS (UPM) Terminators/Lighting Arrestors - COLO 3 - Finish ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-1420 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,14,5 MVS (UPM) Terminators/Lighting Arrestors - COLO 5 | Notice To Proceed | MVS (UPM) Terminators/Lighting Arrestors - COLO 5 - Start ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-1400 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,14,3 MVS (UPM) Terminators/Lighting Arrestors - COLO 4 | Notice To Proceed | MVS (UPM) Terminators/Lighting Arrestors - COLO 4 - Start ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-1380 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,14,2 MVS (UPM) Terminators/Lighting Arrestors - COLO 3 | Notice To Proceed | MVS (UPM) Terminators/Lighting Arrestors - COLO 3 - Start ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-1360 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,14,1 MVS (UPM) Terminators/Lighting Arrestors - COLO 2 | Notice To Proceed | MVS (UPM) Terminators/Lighting Arrestors - COLO 2 - Start ROJ | 0
CHI05-OFCI-1780 | CHI05-OFCI-1790 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,3 Mufflers - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,15,3 Mufflers - COLO 4 | Mufflers - COLO 4 - Start ROJ | Mufflers - COLO 4 - ROJ | 0
CHI05-OFCI-1790 | CHI05-OFCI-1910 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,3 Mufflers - COLO 4 | CHI05-PH2-FIT-BL-D5,4,1,15,3 Mufflers - COLO 4 | Mufflers - COLO 4 - ROJ | Mufflers - COLO 4 - Finish ROJ | 0
CHI05-OFCI-1810 | CHI05-OFCI-1920 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,5 Mufflers - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,15,5 Mufflers - COLO 5 | Mufflers - COLO 5 - ROJ | Mufflers - COLO 5 - Finish ROJ | 0
CHI05-OFCI-1740 | CHI05-OFCI-1750 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,1 Mufflers - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,15,1 Mufflers - COLO 2 | Mufflers - COLO 2 - Start ROJ | Mufflers - COLO 2 - ROJ | 0
CHI05-OFCI-1750 | CHI05-OFCI-1890 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,1 Mufflers - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,15,1 Mufflers - COLO 2 | Mufflers - COLO 2 - ROJ | Mufflers - COLO 2 - Finish ROJ | 0
CHI05-OFCI-1760 | CHI05-OFCI-1770 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,2 Mufflers - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,15,2 Mufflers - COLO 3 | Mufflers - COLO 3 - Start ROJ | Mufflers - COLO 3 - ROJ | 0
CHI05-OFCI-1770 | CHI05-OFCI-1900 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,2 Mufflers - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,15,2 Mufflers - COLO 3 | Mufflers - COLO 3 - ROJ | Mufflers - COLO 3 - Finish ROJ | 0
CHI05-OFCI-1760 | CHI05-OFCI-1780 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,2 Mufflers - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,15,3 Mufflers - COLO 4 | Mufflers - COLO 3 - Start ROJ | Mufflers - COLO 4 - Start ROJ | 0
CHI05-OFCI-1740 | CHI05-OFCI-1760 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,1 Mufflers - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,15,2 Mufflers - COLO 3 | Mufflers - COLO 2 - Start ROJ | Mufflers - COLO 3 - Start ROJ | 0
CHI05-OFCI-2120 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,14,1 MVS (UPM) Terminators/Lighting Arrestors - COLO 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | MVS (UPM) Terminators/Lighting Arrestors - COLO 2 - Finish ROJ | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-OFCI-2200 | CHI05-03-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,14,2 MVS (UPM) Terminators/Lighting Arrestors - COLO 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | MVS (UPM) Terminators/Lighting Arrestors - COLO 3 - Finish ROJ | Complete Last ROJ Arrival for Colo 3 | 0
CHI05-OFCI-2210 | CHI05-04-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,14,3 MVS (UPM) Terminators/Lighting Arrestors - COLO 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | MVS (UPM) Terminators/Lighting Arrestors - COLO 4 - Finish ROJ | Complete Last ROJ Arrival for Colo 4 | 0
CHI05-OFCI-2220 | CHI05-05-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,14,5 MVS (UPM) Terminators/Lighting Arrestors - COLO 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | MVS (UPM) Terminators/Lighting Arrestors - COLO 5 - Finish ROJ | Complete Last ROJ Arrival for Colo 5 | 0
CHI05-OFCI-1890 | CHI05-02-01-L3-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,1 Mufflers - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Mufflers - COLO 2 - Finish ROJ | L3 GEN - COLO2 | 0
CHI05-OFCI-1900 | CHI05-03-01-L3-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,2 Mufflers - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Mufflers - COLO 3 - Finish ROJ | L3 GEN - COLO3 | 0
CHI05-OFCI-1910 | CHI05-04-01-L3-1720 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,3 Mufflers - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Mufflers - COLO 4 - Finish ROJ | L3 GEN - COLO4 | 0
CHI05-OFCI-1920 | CHI05-05-01-L3-1840 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,5 Mufflers - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Mufflers - COLO 5 - Finish ROJ | L3 GEN - COLO5 | 0
CHI05-05-NTP-S | CHI05-OFCI-1740 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,15,1 Mufflers - COLO 2 | Notice To Proceed | Mufflers - COLO 2 - Start ROJ | 0
CHI05-05-01-DH-1400 | CHI05-05-01-DH-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 1 - DH | Finishes and Signage - COLO5 Cell 1 - DH | 0
CHI05-YARD-2150 | CHI05-05-01-L2-1680 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Wire pulling and termination for MSB - Colo 5 - West | L2 UTS / UTSR - Site | 0
CHI05-YARD-2270 | CHI05-05-01-L2-1680 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Wire pulling and termination for MSB - Colo 5 - East | L2 UTS / UTSR - Site | 0
CHI05-05-01-L2-1700 | CHI05-05-01-L2-1720 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UPM - COLO5 | L2 GEN - COLO5 | 0
CHI05-05-01-L3-1820 | CHI05-05-01-L3-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | L3 UPM - COLO5 | Interior - L3 UPS - COLO5 Cell 1 | 0
CHI05-05-01-L3-1820 | CHI05-05-01-L3-1840 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UPM - COLO5 | L3 GEN - COLO5 | 0
CHI05-02-01-L1-1220 | CHI05-02-01-L1-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | L1 UPM - COLO2 | Interior - L1 UPS - COLO2 Cell 1 | 0
CHI05-02-01-L2-1340 | CHI05-02-01-L2-1360 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UPM - COLO2 | L2 GEN - COLO2 | 0
CHI05-02-POW-F | CHI05-02-01-L3-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Power-ON Utility for Colo 2 | L3 UTS / UTSR - Site | 0
CHI05-02-01-L3-1460 | CHI05-02-01-L3-1480 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UPM - COLO2 | L3 GEN - COLO2 | 0
CHI05-02-01-L3-1460 | CHI05-02-01-L3-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | L3 UPM - COLO2 | Interior - L3 UPS - COLO2 Cell 1 | 0
CHI05-02-01-L3-1420 | CHI05-02-01-L3-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L3 ATSs - COLO2 Cell 1 | Interior - L3 AHUs - COLO2 Cell 1 | 0
CHI05-03-01-L2-1460 | CHI05-03-01-L2-1480 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UPM - COLO3 | L2 GEN - COLO3 | 0
CHI05-03-01-L3-1540 | CHI05-03-01-L3-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L3 ATSs - COLO3 Cell 1 | Interior - L3 Busway - COLO3 Cell 1 | 0
CHI05-03-02-L3-1660 | CHI05-03-02-L3-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L3 ATSs - COLO3 Cell 2 | Interior - L3 Busway - COLO3 Cell 2 | 0
CHI05-04-01-L2-1580 | CHI05-04-01-L2-1600 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UPM - COLO4 | L2 GEN - COLO4 | 0
CHI05-04-02-L3-1780 | CHI05-04-02-L3-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L3 ATSs - COLO4 Cell 2 | Interior - L3 Busway - COLO4 Cell 2 | 0
CHI05-05-04-L3-2140 | CHI05-05-04-L3-2150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L3 ATSs - COLO5 Cell 4 | Interior - L3 Busway - COLO5 Cell 4 | 0
CHI05-05-02-DH-1510 | CHI05-05-02-DH-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH | Finishes and Signage - COLO5 Cell 2 - DH | 0
CHI05-05-03-DH-1620 | CHI05-05-03-DH-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 3 - DH | Finishes and Signage - COLO5 Cell 3 - DH | 0
CHI05-02-01-DH-1080 | CHI05-02-01-DH-1090 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 1 - DH | Finishes and Signage - COLO2 Cell 1 - DH | 0
CHI05-02-02-DH-1180 | CHI05-02-02-DH-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 2 - DH | Finishes and Signage - COLO2 Cell 2 - DH | 0
CHI05-02-03-DH-1290 | CHI05-02-03-DH-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH | Finishes and Signage - COLO2 Cell 3 - DH | 0
CHI05-03-01-DH-1180 | CHI05-03-01-DH-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH | Finishes and Signage - COLO3 Cell 1 - DH | 0
CHI05-03-02-DH-1290 | CHI05-03-02-DH-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 2 - DH | Finishes and Signage - COLO3 Cell 2 - DH | 0
CHI05-03-03-DH-1400 | CHI05-03-03-DH-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 3 - DH | Finishes and Signage - COLO3 Cell 3 - DH | 0
CHI05-04-01-DH-1290 | CHI05-04-01-DH-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH | Finishes and Signage - COLO4 Cell 1 - DH | 0
CHI05-04-02-DH-1400 | CHI05-04-02-DH-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 2 - DH | Finishes and Signage - COLO4 Cell 2 - DH | 0
CHI05-04-03-DH-1510 | CHI05-04-03-DH-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 3 - DH | Finishes and Signage - COLO4 Cell 3 - DH | 0
CHI05-02-01-L1-1200 | CHI05-03-L1CX-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | L1 UTS / UTSR - Site | Start L1 CX (Red Tag) for Colo 3 | 0
CHI05-02-01-L1-1200 | CHI05-04-L1CX-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | L1 UTS / UTSR - Site | Start L1 CX (Red Tag) for Colo 4 | 0
CHI05-02-01-L1-1200 | CHI05-05-L1CX-S | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | L1 UTS / UTSR - Site | Start L1 CX (Red Tag) for Colo 5 | 0
CHI05-OFCI-2130 | CHI05-02-01-L1-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,13,1 UTS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | UTS - Site - Finish ROJ | L1 UTS / UTSR - Site | 0
CHI05-05-01-L2-1680 | CHI05-02-01-L3-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L2 UTS / UTSR - Site | L3 UTS / UTSR - Site | 0
CHI05-05-01-L2-1680 | CHI05-02-L2CX-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | L2 UTS / UTSR - Site | Start L2 CX (Yellow Tag) for Colo 2 | 0
CHI05-05-01-L2-1680 | CHI05-02-01-L2-1330 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UTS / UTSR - Site | L2 URS 01 - COLO 5 | 0
CHI05-05-01-L2-1680 | CHI05-02-04-L2-1690 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UTS / UTSR - Site | L2 UMS 01 - COLO 5 | 0
CHI05-05-01-L2-1680 | CHI05-02-02-L2-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UTS / UTSR - Site | L2 UMS 03 - COLO 3 | 0
CHI05-05-01-L2-1680 | CHI05-02-03-L2-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UTS / UTSR - Site | L2 UMS 04 - COLO 3 | 0
CHI05-05-01-L2-1680 | CHI05-04-03-L2-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | L2 UTS / UTSR - Site | Interior - L2 UPS - COLO4 Cell 3 | 0
CHI05-05-01-L2-1680 | CHI05-03-L2CX-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | L2 UTS / UTSR - Site | Start L2 CX (Yellow Tag) for Colo 3 | 0
CHI05-05-01-L2-1680 | CHI05-04-L2CX-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | L2 UTS / UTSR - Site | Start L2 CX (Yellow Tag) for Colo 4 | 0
CHI05-05-01-L2-1680 | CHI05-04-02-L2-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | L2 UTS / UTSR - Site | Interior - L2 UPS - COLO4 Cell 2 | 0
CHI05-05-01-L2-1680 | CHI05-04-04-L2-1860 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | L2 UTS / UTSR - Site | Interior - L2 UPS - COLO4 Cell 4 | 0
CHI05-02-01-L3-1440 | CHI05-02-02-L3-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | L3 UTS / UTSR - Site | Interior - L3 UPS - COLO2 Cell 2 | 0
CHI05-02-01-L3-1440 | CHI05-02-02-L3-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UTS / UTSR - Site | L3 UMS 03 - COLO 3 | 0
CHI05-02-01-L3-1440 | CHI05-02-03-L3-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | L3 UTS / UTSR - Site | Interior - L3 UPS - COLO2 Cell 3 | 0
CHI05-02-01-L3-1440 | CHI05-02-03-L3-1690 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UTS / UTSR - Site | L3 URS 01 - COLO 5 | 0
CHI05-02-01-L3-1440 | CHI05-02-04-L3-1810 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UTS / UTSR - Site | L3 UMS 01 - COLO 5 | 0
CHI05-02-01-L3-1440 | CHI05-03-L3CX-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | L3 UTS / UTSR - Site | Start L3 Cx (Green tag) for Colo 3 | 0
CHI05-02-01-L3-1440 | CHI05-03-01-L3-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | L3 UTS / UTSR - Site | Interior - L3 UPS - COLO3 Cell 1 | 0
CHI05-02-01-L3-1440 | CHI05-04-L3CX-S | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | L3 UTS / UTSR - Site | Start L3 Cx (Green tag) for Colo 4 | 0
CHI05-02-01-L3-1440 | CHI05-05-L3CX-S | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | L3 UTS / UTSR - Site | Start L3 Cx (Green tag) for Colo 5 | 0
CHI05-02-01-L3-1440 | CHI05-05-02-L3-1860 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | L3 UTS / UTSR - Site | Interior - L3 UPS - COLO5 Cell 2 | 0
CHI05-02-01-L3-1440 | CHI05-05-03-L3-1980 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | L3 UTS / UTSR - Site | Interior - L3 UPS - COLO5 Cell 3 | 0
CHI05-02-01-L1-1210 | CHI05-03-01-L1-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 UMS 04 - COLO 3 | L1 UPM - COLO3 | 0
CHI05-02-01-L1-1210 | CHI05-04-01-L1-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 UMS 04 - COLO 3 | L1 UPM - COLO4 | 0
CHI05-02-01-L1-1210 | CHI05-05-01-L1-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 UMS 04 - COLO 3 | L1 UPM - COLO5 | 0
CHI05-02-02-L1-1330 | CHI05-02-01-L1-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 UMS 03 - COLO 3 | L1 UPM - COLO2 | 0
CHI05-02-02-L1-1330 | CHI05-03-01-L1-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 UMS 03 - COLO 3 | L1 UPM - COLO3 | 0
CHI05-02-02-L1-1330 | CHI05-04-01-L1-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 UMS 03 - COLO 3 | L1 UPM - COLO4 | 0
CHI05-02-02-L1-1330 | CHI05-05-01-L1-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 UMS 03 - COLO 3 | L1 UPM - COLO5 | 0
CHI05-02-03-L1-1450 | CHI05-02-01-L1-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 UMS 01 - COLO 5 | L1 UPM - COLO2 | 0
CHI05-02-03-L1-1450 | CHI05-03-01-L1-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 UMS 01 - COLO 5 | L1 UPM - COLO3 | 0
CHI05-02-03-L1-1450 | CHI05-04-01-L1-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 UMS 01 - COLO 5 | L1 UPM - COLO4 | 0
CHI05-02-03-L1-1450 | CHI05-05-01-L1-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 UMS 01 - COLO 5 | L1 UPM - COLO5 | 0
CHI05-02-04-L1-1570 | CHI05-02-01-L1-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 URS 01 - COLO 5 | L1 UPM - COLO2 | 0
CHI05-02-04-L1-1570 | CHI05-03-01-L1-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 URS 01 - COLO 5 | L1 UPM - COLO3 | 0
CHI05-02-04-L1-1570 | CHI05-04-01-L1-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 URS 01 - COLO 5 | L1 UPM - COLO4 | 0
CHI05-02-01-L2-1330 | CHI05-03-01-L2-1460 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 URS 01 - COLO 5 | L2 UPM - COLO3 | 0
CHI05-02-01-L2-1330 | CHI05-04-01-L2-1580 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 URS 01 - COLO 5 | L2 UPM - COLO4 | 0
CHI05-02-01-L2-1330 | CHI05-05-01-L2-1700 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 URS 01 - COLO 5 | L2 UPM - COLO5 | 0
CHI05-02-02-L2-1450 | CHI05-02-01-L2-1340 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UMS 03 - COLO 3 | L2 UPM - COLO2 | 0
CHI05-02-02-L2-1450 | CHI05-03-01-L2-1460 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UMS 03 - COLO 3 | L2 UPM - COLO3 | 0
CHI05-02-02-L2-1450 | CHI05-04-01-L2-1580 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UMS 03 - COLO 3 | L2 UPM - COLO4 | 0
CHI05-02-02-L2-1450 | CHI05-05-01-L2-1700 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UMS 03 - COLO 3 | L2 UPM - COLO5 | 0
CHI05-02-03-L2-1570 | CHI05-02-01-L2-1340 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UMS 04 - COLO 3 | L2 UPM - COLO2 | 0
CHI05-02-03-L2-1570 | CHI05-03-01-L2-1460 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UMS 04 - COLO 3 | L2 UPM - COLO3 | 0
CHI05-02-03-L2-1570 | CHI05-04-01-L2-1580 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UMS 04 - COLO 3 | L2 UPM - COLO4 | 0
CHI05-02-03-L2-1570 | CHI05-05-01-L2-1700 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UMS 04 - COLO 3 | L2 UPM - COLO5 | 0
CHI05-02-04-L2-1690 | CHI05-02-01-L2-1340 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UMS 01 - COLO 5 | L2 UPM - COLO2 | 0
CHI05-02-04-L2-1690 | CHI05-03-01-L2-1460 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UMS 01 - COLO 5 | L2 UPM - COLO3 | 0
CHI05-02-04-L2-1690 | CHI05-04-01-L2-1580 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UMS 01 - COLO 5 | L2 UPM - COLO4 | 0
CHI05-02-04-L2-1690 | CHI05-05-01-L2-1700 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L2 UMS 01 - COLO 5 | L2 UPM - COLO5 | 0
CHI05-02-01-L3-1450 | CHI05-03-01-L3-1580 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UMS 04 - COLO 3 | L3 UPM - COLO3 | 0
CHI05-02-01-L3-1450 | CHI05-04-01-L3-1700 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UMS 04 - COLO 3 | L3 UPM - COLO4 | 0
CHI05-02-02-L3-1570 | CHI05-03-01-L3-1580 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UMS 03 - COLO 3 | L3 UPM - COLO3 | 0
CHI05-02-02-L3-1570 | CHI05-04-01-L3-1700 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UMS 03 - COLO 3 | L3 UPM - COLO4 | 0
CHI05-02-03-L3-1690 | CHI05-02-01-L3-1460 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 URS 01 - COLO 5 | L3 UPM - COLO2 | 0
CHI05-02-03-L3-1690 | CHI05-03-01-L3-1580 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 URS 01 - COLO 5 | L3 UPM - COLO3 | 0
CHI05-02-03-L3-1690 | CHI05-04-01-L3-1700 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 URS 01 - COLO 5 | L3 UPM - COLO4 | 0
CHI05-02-03-L3-1690 | CHI05-05-01-L3-1820 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 URS 01 - COLO 5 | L3 UPM - COLO5 | 0
CHI05-02-04-L3-1810 | CHI05-02-01-L3-1460 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UMS 01 - COLO 5 | L3 UPM - COLO2 | 0
CHI05-02-04-L3-1810 | CHI05-03-01-L3-1580 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UMS 01 - COLO 5 | L3 UPM - COLO3 | 0
CHI05-02-04-L3-1810 | CHI05-04-01-L3-1700 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UMS 01 - COLO 5 | L3 UPM - COLO4 | 0
CHI05-02-04-L3-1810 | CHI05-05-01-L3-1820 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UMS 01 - COLO 5 | L3 UPM - COLO5 | 0
CHI05-04-04-L3-2000 | CHI05-04-04-L3-2090 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L3 PDUs - COLO4 Cell 4 | Interior - L3 ADP - COLO4 Cell 4 | 0
CHI05-02-03-L3-1690 | CHI05-02-01-L3-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 URS 01 - COLO 5 | L3 UMS 04 - COLO 3 | 0
CHI05-02-04-L3-1810 | CHI05-02-02-L3-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UMS 01 - COLO 5 | L3 UMS 03 - COLO 3 | 0
CHI05-03-04-L3-1900 | CHI05-03-04-L3-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L3 ATSs - COLO3 Cell 4 | Interior - L3 Busway - COLO3 Cell 4 | 0
CHI05-03-04-L3-1880 | CHI05-03-04-L3-1970 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L3 PDUs - COLO3 Cell 4 | Interior - L3 ADP - COLO3 Cell 4 | 0
CHI05-03-03-L3-1780 | CHI05-03-03-L3-1790 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | Interior - L3 ATSs - COLO3 Cell 3 | Interior - L3 Busway - COLO3 Cell 3 | 0
CHI05-03-03-L3-1760 | CHI05-03-03-L3-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | Interior - L3 PDUs - COLO3 Cell 3 | Interior - L3 ADP - COLO3 Cell 3 | 0
CHI05-03-02-L3-1640 | CHI05-03-02-L3-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L3 PDUs - COLO3 Cell 2 | Interior - L3 ADP - COLO3 Cell 2 | 0
CHI05-03-01-L3-1580 | CHI05-03-01-L3-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | L3 UPM - COLO3 | Interior - L3 UPS - COLO3 Cell 1 | 0
CHI05-03-01-L3-1600 | CHI05-03-01-L3-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | L3 GEN - COLO3 | Interior - L3 MSB - COLO3 Cell 1 | 0
CHI05-03-01-L3-1520 | CHI05-03-01-L3-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L3 PDUs - COLO3 Cell 1 | Interior - L3 ADP - COLO3 Cell 1 | 0
CHI05-04-01-L3-1700 | CHI05-04-01-L3-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | L3 UPM - COLO4 | Interior - L3 UPS - COLO4 Cell 1 | 0
CHI05-04-01-L3-1720 | CHI05-04-01-L3-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | L3 GEN - COLO4 | Interior - L3 MSB - COLO4 Cell 1 | 0
CHI05-YARD-2420 | CHI05-04-01-L2-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Wire pulling and termination for MSB - Colo 4 - South | L2 UPM - COLO4 | 0
CHI05-YARD-2310 | CHI05-04-01-L2-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Wire pulling and termination for MSB - Colo 4 - North | L2 UPM - COLO4 | 0
CHI05-04-01-L2-1580 | CHI05-04-01-L3-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L2 UPM - COLO4 | L3 UPM - COLO4 | 0
CHI05-05-POW-F | CHI05-05-L3CX-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Power-ON Utility for Colo 5 | Start L3 Cx (Green tag) for Colo 5 | 0
CHI05-03-03-L3-1790 | CHI05-03-04-L4-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,5,1 Level 4 Cx - Colo 3 | Interior - L3 Busway - COLO3 Cell 3 | Cx LEV4 - COLO3 | 0
CHI05-05-CO-F | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Complete CorpNet For Colo 5 | Site Secured Finish (August 04, 2025) | 0
CHI05-OFCI-2270 | CHI05-03-01-ER-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,2 ATS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | ATS - COLO 3 - Finish ROJ | Installation of ADP & ATS - COLO3 Cell 1 - ER | 0
CHI05-OFCI-2270 | CHI05-03-02-ER-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,2 ATS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | ATS - COLO 3 - Finish ROJ | Installation of ADP & ATS - COLO3 Cell 2 - ER | 0
CHI05-OFCI-2270 | CHI05-03-03-ER-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,2 ATS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | ATS - COLO 3 - Finish ROJ | Installation of ADP & ATS - COLO3 Cell 3 - ER | 0
CHI05-OFCI-2270 | CHI05-03-04-ER-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,2 ATS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | ATS - COLO 3 - Finish ROJ | Installation of ADP & ATS - COLO3 Cell 4 - ER | 0
CHI05-OFCI-1980 | CHI05-04-01-ER-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,3 ATS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | ATS - COLO 4 - Finish ROJ | Installation of ADP & ATS - COLO4 Cell 1 - ER | 0
CHI05-OFCI-1980 | CHI05-04-02-ER-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,3 ATS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | ATS - COLO 4 - Finish ROJ | Installation of ADP & ATS - COLO4 Cell 2 - ER | 0
CHI05-OFCI-1980 | CHI05-04-03-ER-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,3 ATS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | ATS - COLO 4 - Finish ROJ | Installation of ADP & ATS - COLO4 Cell 3 - ER | 0
CHI05-OFCI-1980 | CHI05-04-04-ER-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,3 ATS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | ATS - COLO 4 - Finish ROJ | Installation of ADP & ATS - COLO4 Cell 4 - ER | 0
CHI05-OFCI-1500 | CHI05-05-01-ER-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,5 ATS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | ATS - COLO 5 - Finish ROJ | Installation of ADP & ATS - COLO5 Cell 1 - ER | 0
CHI05-OFCI-1500 | CHI05-05-02-ER-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,5 ATS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | ATS - COLO 5 - Finish ROJ | Installation of ADP & ATS - COLO5 Cell 2 - ER | 0
CHI05-OFCI-1500 | CHI05-05-03-ER-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,5 ATS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | ATS - COLO 5 - Finish ROJ | Installation of ADP & ATS - COLO5 Cell 3 - ER | 0
CHI05-OFCI-1500 | CHI05-05-04-ER-1710 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,5 ATS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | ATS - COLO 5 - Finish ROJ | Installation of ADP & ATS - COLO5 Cell 4 - ER | 0
CHI05-OFCI-1670 | CHI05-05-01-ER-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,5 Busway/Bus Plugs - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 5 - Finish ROJ | Connet to Cable tray and conduit equipment - COLO5 Cell 1 - ER | 0
CHI05-OFCI-1670 | CHI05-05-02-ER-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,5 Busway/Bus Plugs - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 5 - Finish ROJ | Connet to Cable tray and conduit equipment - COLO5 Cell 2 - ER | 0
CHI05-OFCI-1670 | CHI05-05-03-ER-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,5 Busway/Bus Plugs - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 5 - Finish ROJ | Connet to Cable tray and conduit equipment - COLO5 Cell 3 - ER | 0
CHI05-OFCI-1670 | CHI05-05-04-ER-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,5 Busway/Bus Plugs - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 5 - Finish ROJ | Connet to Cable tray and conduit equipment - COLO5 Cell 4 - ER | 0
CHI05-OFCI-2260 | CHI05-04-01-ER-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,3 Busway/Bus Plugs - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 4 - Finish ROJ | Connet to Cable tray and conduit equipment - COLO4 Cell 1 - ER | 0
CHI05-OFCI-2260 | CHI05-04-02-ER-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,3 Busway/Bus Plugs - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 4 - Finish ROJ | Connet to Cable tray and conduit equipment - COLO4 Cell 2 - ER | 0
CHI05-OFCI-2260 | CHI05-04-03-ER-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,3 Busway/Bus Plugs - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 4 - Finish ROJ | Connet to Cable tray and conduit equipment - COLO4 Cell 3 - ER | 0
CHI05-OFCI-2260 | CHI05-04-04-ER-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,3 Busway/Bus Plugs - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 4 - Finish ROJ | Connet to Cable tray and conduit equipment - COLO4 Cell 4 - ER | 0
CHI05-OFCI-2250 | CHI05-03-01-ER-1180 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,2 Busway/Bus Plugs - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 3 - Finish ROJ | Connet to Cable tray and conduit equipment - COLO3 Cell 1 - ER | 0
CHI05-OFCI-2250 | CHI05-03-02-ER-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,2 Busway/Bus Plugs - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 3 - Finish ROJ | Connet to Cable tray and conduit equipment - COLO3 Cell 2 - ER | 0
CHI05-OFCI-2250 | CHI05-03-03-ER-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,2 Busway/Bus Plugs - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 3 - Finish ROJ | Connet to Cable tray and conduit equipment - COLO3 Cell 3 - ER | 0
CHI05-OFCI-2250 | CHI05-03-04-ER-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,2 Busway/Bus Plugs - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 3 - Finish ROJ | Connet to Cable tray and conduit equipment - COLO3 Cell 4 - ER | 0
CHI05-OFCI-1090 | CHI05-02-01-ER-1060 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,1 Busway/Bus Plugs - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 2 - In Storage | Connet to Cable tray and conduit equipment - COLO2 Cell 1 - ER | 0
CHI05-OFCI-1090 | CHI05-02-02-ER-1180 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,1 Busway/Bus Plugs - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 2 - In Storage | Connet to Cable tray and conduit equipment - COLO2 Cell 2 - ER | 0
CHI05-OFCI-1090 | CHI05-02-03-ER-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,1 Busway/Bus Plugs - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 2 - In Storage | Connet to Cable tray and conduit equipment - COLO2 Cell 3 - ER | 0
CHI05-OFCI-1090 | CHI05-02-04-ER-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,3,1 Busway/Bus Plugs - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Busway/Bus Plugs - COLO 2 - In Storage | Connet to Cable tray and conduit equipment - COLO2 Cell 4 - ER | 0
CHI05-02-L3CX-F | CHI05-02-RNI-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Complete L3 CX (Green Tag) for Colo 2 | Complete Ready for Network Install (RNI) For Colo 2 | 5
CHI05-03-L3CX-F | CHI05-03-RNI-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Complete L3 CX (Green Tag) for Colo 3 | Complete Ready for Network Install (RNI) For Colo 3 | 5
CHI05-04-CO-F | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Complete CorpNet For Colo 4 | Site Secured Finish (August 04, 2025) | 0
CHI05-05-L3CX-F | CHI05-05-RNI-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Complete L3 CX (Green Tag) for Colo 5 | Complete Ready for Network Install (RNI) For Colo 5 | 5
CHI05-05-L5CX-F | CHI05-05-SSC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Complete L5/IST (White Tag) for Colo 5 | Complete Phase 3 Security System Test for Colo 5 | 5
CHI05-05-SSC-F | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Complete Phase 3 Security System Test for Colo 5 | Site Secured Finish (August 04, 2025) | 0
CHI05-05-L3CX-F | CHI05-05-CO-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Complete L3 CX (Green Tag) for Colo 5 | Complete CorpNet For Colo 5 | 0
CHI05-02-L5CX-F | CHI05-02-SSC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Complete L5/IST (White Tag) for Colo 2 | Complete Phase 3 Security System Test for Colo 2 | 5
CHI05-02-SSC-F | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Complete Phase 3 Security System Test for Colo 2 | Site Secured Finish (August 04, 2025) | 0
CHI05-02-L3CX-F | CHI05-02-CO-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Complete L3 CX (Green Tag) for Colo 2 | Complete CorpNet For Colo 2 | 0
CHI05-03-L5CX-F | CHI05-03-SSC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Complete L5/IST (White Tag) for Colo 3 | Complete Phase 3 Security System Test for Colo 3 | 5
CHI05-03-SSC-F | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Complete Phase 3 Security System Test for Colo 3 | Site Secured Finish (August 04, 2025) | 0
CHI05-03-L3CX-F | CHI05-03-CO-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Complete L3 CX (Green Tag) for Colo 3 | Complete CorpNet For Colo 3 | 0
CHI05-04-L5CX-F | CHI05-04-SSC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Complete L5/IST (White Tag) for Colo 4 | Complete Phase 3 Security System Test for Colo 4 | 5
CHI05-04-L3CX-F | CHI05-04-RNI-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Complete L3 CX (Green Tag) for Colo 4 | Complete Ready for Network Install (RNI) For Colo 4 | 5
CHI05-04-L3CX-F | CHI05-04-CO-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Complete L3 CX (Green Tag) for Colo 4 | Complete CorpNet For Colo 4 | 0
CHI05-03-RNI-F | CHI05-03-L5CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Complete Ready for Network Install (RNI) For Colo 3 | Complete L5/IST (White Tag) for Colo 3 | 0
CHI05-04-RNI-F | CHI05-04-L5CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Complete Ready for Network Install (RNI) For Colo 4 | Complete L5/IST (White Tag) for Colo 4 | 0
CHI05-02-RNI-F | CHI05-02-L5CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Complete Ready for Network Install (RNI) For Colo 2 | Complete L5/IST (White Tag) for Colo 2 | 0
CHI05-05-RNI-F | CHI05-05-L5CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Complete Ready for Network Install (RNI) For Colo 5 | Complete L5/IST (White Tag) for Colo 5 | 0
CHI05-OFCI-1540 | CHI05-YARD-2020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,5 MVS (UPM) - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | MVS (UPM) - COLO 5 - Finish ROJ | Install MV Gear - Colo 5 - West | 0
CHI05-OFCI-1540 | CHI05-YARD-2080 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,8,5 MVS (UPM) - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | MVS (UPM) - COLO 5 - Finish ROJ | Install MV Gear - Colo 5 - East | 0
CHI05-YARD-2010 | CHI05-YARD-2020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | Set the MV Gear - Colo 5 - West | Install MV Gear - Colo 5 - West | 0
CHI05-YARD-2070 | CHI05-YARD-2080 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | Set the MV Gear - Colo 5 - East | Install MV Gear - Colo 5 - East | 0
CHI05-YARD-2000 | CHI05-YARD-2030 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | Set the Generator - Colo 2 - North | Install Generator - Colo 2 - North | 0
CHI05-YARD-2060 | CHI05-YARD-2090 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | Set the Generator - Colo 3 - North | Install Generator - Colo 3 - North | 0
CHI05-YARD-2100 | CHI05-YARD-2110 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | Set the MV Gear - Colo 4 - North | Install MV Gear - Colo 4 - North | 0
CHI05-YARD-2120 | CHI05-YARD-2130 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | Set the Generator - Colo 2 - South | Install Generator - Colo 2 - South | 0
CHI05-YARD-2170 | CHI05-YARD-2190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | Set the MV Gear - Colo 3 - South | Install MV Gear - Colo 3 - South | 0
CHI05-YARD-2220 | CHI05-YARD-2230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | Set the MV Gear - Colo 4 - South | Install MV Gear - Colo 4 - South | 0
CHI05-YARD-2150 | CHI05-YARD-2200 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | Wire pulling and termination for MSB - Colo 5 - West | Installation of Mech. Piping and testing - Colo 5 - West | 0
CHI05-YARD-2270 | CHI05-YARD-2280 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | Wire pulling and termination for MSB - Colo 5 - East | Installation of Mech. Piping and testing - Colo 5 - Eest | 0
CHI05-YARD-2140 | CHI05-YARD-2210 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | Wire pulling and termination for MSB - Colo 2 - North | Installation of Mech. Piping and testing - Colo 2 - North | 0
CHI05-YARD-2260 | CHI05-YARD-2290 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | Wire pulling and termination for MSB - Colo 3 - North | Installation of Mech. Piping and testing - Colo 3 - North | 0
CHI05-YARD-2310 | CHI05-YARD-2330 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | Wire pulling and termination for MSB - Colo 4 - North | Installation of Mech. Piping and testing - Colo 4 - North | 0
CHI05-YARD-2350 | CHI05-YARD-2390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | Wire pulling and termination for MSB - Colo 2 - South | Installation of Mech. Piping and testing - Colo 2 - South | 0
CHI05-YARD-2380 | CHI05-YARD-2410 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | Wire pulling and termination for MSB - Colo 3 - South | Installation of Mech. Piping and testing - Colo 3 - South | 0
CHI05-YARD-2420 | CHI05-YARD-2440 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | Wire pulling and termination for MSB - Colo 4 - South | Installation of Mech. Piping and testing - Colo 4 - South | 0
CHI05-05-BAS-F | CHI05-05-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Complete BAS SAT for Colo 5 | Complete L3 CX (Green Tag) for Colo 5 | 0
CHI05-05-EPMS-F | CHI05-05-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Complete EPMS SAT for Colo 5 | Complete L3 CX (Green Tag) for Colo 5 | 0
CHI05-05-FIR-F | CHI05-05-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | Complete Fire Alarm for Colo 5 | Complete L3 CX (Green Tag) for Colo 5 | 0
CHI05-02-BAS-F | CHI05-02-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Complete BAS SAT for Colo 2 | Complete L3 CX (Green Tag) for Colo 2 | 0
CHI05-02-EPMS-F | CHI05-02-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Complete EPMS SAT for Colo 2 | Complete L3 CX (Green Tag) for Colo 2 | 0
CHI05-02-FIRE-F | CHI05-02-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Complete Fire Alarm for Colo 2 | Complete L3 CX (Green Tag) for Colo 2 | 0
CHI05-03-BAS-F | CHI05-03-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Complete BAS SAT for Colo 3 | Complete L3 CX (Green Tag) for Colo 3 | 0
CHI05-03-EPMS-F | CHI05-03-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Complete EPMS SAT for Colo 3 | Complete L3 CX (Green Tag) for Colo 3 | 0
CHI05-03-FIRE-F | CHI05-03-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | Complete Fire Alarm for Colo 3 | Complete L3 CX (Green Tag) for Colo 3 | 0
CHI05-04-BAS-F | CHI05-04-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Complete BAS SAT for Colo 4 | Complete L3 CX (Green Tag) for Colo 4 | 0
CHI05-04-EPMS-F | CHI05-04-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Complete EPMS SAT for Colo 4 | Complete L3 CX (Green Tag) for Colo 4 | 0
CHI05-04-FIRE-F | CHI05-04-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Complete Fire Alarm for Colo 4 | Complete L3 CX (Green Tag) for Colo 4 | 0
CHI05-05-01-DH-1320 | CHI05-05-01-L2-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Cable Pulling at PDU & Busway - COLO5 Cell 1 - DH | Interior - L2 PDUs - COLO5 Cell 1 | 0
CHI05-05-02-DH-1430 | CHI05-05-02-L2-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH | Interior - L2 PDUs - COLO5 Cell 2 | 0
CHI05-05-03-DH-1540 | CHI05-05-03-L2-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Termination at PDU & Busway - COLO5 Cell 3 - DH | Interior - L2 PDUs - COLO5 Cell 3 | 0
CHI05-05-04-DH-1650 | CHI05-05-04-L2-2000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Termination at PDU & Busway - COLO5 Cell 4 - DH | Interior - L2 PDUs - COLO5 Cell 4 | 0
CHI05-02-01-DH-1050 | CHI05-02-01-L2-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH | Interior - L2 PDUs - COLO2 Cell 1 | 0
CHI05-02-02-DH-1100 | CHI05-02-02-L2-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Termination at PDU & Busway - COLO2 Cell 2 - DH | Interior - L2 PDUs - COLO2 Cell 2 | 0
CHI05-02-03-DH-1210 | CHI05-02-03-L2-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Termination at PDU & Busway - COLO2 Cell 3 - DH | Interior - L2 PDUs - COLO2 Cell 3 | 0
CHI05-02-04-DH-1320 | CHI05-02-04-L2-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Termination at PDU & Busway - COLO2 Cell 4 - DH | Interior - L2 PDUs - COLO2 Cell 4 | 0
CHI05-03-01-DH-1100 | CHI05-03-01-L2-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH | Interior - L2 PDUs - COLO3 Cell 1 | 0
CHI05-03-02-DH-1210 | CHI05-03-02-L2-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Termination at PDU & Busway - COLO3 Cell 2 - DH | Interior - L2 PDUs - COLO3 Cell 2 | 0
CHI05-03-03-DH-1320 | CHI05-03-03-L2-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | Termination at PDU & Busway - COLO3 Cell 3 - DH | Interior - L2 PDUs - COLO3 Cell 3 | 0
CHI05-03-04-DH-1430 | CHI05-03-04-L2-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Termination at PDU & Busway - COLO3 Cell 4 - DH | Interior - L2 PDUs - COLO3 Cell 4 | 0
CHI05-04-01-DH-1210 | CHI05-04-01-L2-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH | Interior - L2 PDUs - COLO4 Cell 1 | 0
CHI05-04-02-DH-1320 | CHI05-04-02-L2-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Termination at PDU & Busway - COLO4 Cell 2 - DH | Interior - L2 PDUs - COLO4 Cell 2 | 0
CHI05-04-03-DH-1430 | CHI05-04-03-L2-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Termination at PDU & Busway - COLO4 Cell 3 - DH | Interior - L2 PDUs - COLO4 Cell 3 | 0
CHI05-04-04-DH-1540 | CHI05-04-04-L2-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Termination at PDU & Busway - COLO4 Cell 4 - DH | Interior - L2 PDUs - COLO4 Cell 4 | 0
CHI05-YARD-2280 | CHI05-YARD-2320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | Installation of Mech. Piping and testing - Colo 5 - Eest | Install screen wall - Colo 5 - East | 0
CHI05-YARD-2440 | CHI05-YARD-2470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | Installation of Mech. Piping and testing - Colo 4 - South | Install screen wall - Colo 4 - South | 0
CHI05-05-FC-F | CHI05-04-SSC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | Site Secured Finish (August 04, 2025) | Complete Phase 3 Security System Test for Colo 4 | 0
CHI05-05-01-ER-1390 | CHI05-05-01-L1-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Installation of UPS Equipment - COLO5 Cell 1 - ER | Interior - L1 UPS - COLO5 Cell 1 | 0
CHI05-05-01-ER-1380 | CHI05-05-01-L1-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Installation of ADP & ATS - COLO5 Cell 1 - ER | Interior - L1 ADP - COLO5 Cell 1 | 0
CHI05-05-01-ER-1380 | CHI05-05-01-L1-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Installation of ADP & ATS - COLO5 Cell 1 - ER | Interior - L1 ATSs - COLO5 Cell 1 | 0
CHI05-05-01-ER-1380 | CHI05-05-01-L1-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Installation of ADP & ATS - COLO5 Cell 1 - ER | Interior - L1 Busway - COLO5 Cell 1 | 0
CHI05-05-01-DH-1340 | CHI05-05-01-L1-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | HAC install and Rise - COLO5 Cell 1 - DH | Interior - L1 AHUs - COLO5 Cell 1 | 0
CHI05-05-01-L1-1580 | CHI05-05-01-L2-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L1 UPM - COLO5 | L2 UPM - COLO5 | 0
CHI05-05-01-L1-1590 | CHI05-05-01-L2-1710 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L1 XFMR - MV- COLO5 | L2 XFMR - COLO5 | 0
CHI05-05-01-L1-1510 | CHI05-05-01-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L1 MSB - COLO5 Cell 1 | Interior - L2 MSB - COLO5 Cell 1 | 0
CHI05-05-01-L1-1520 | CHI05-05-01-L2-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L1 PDUs - COLO5 Cell 1 | Interior - L2 PDUs - COLO5 Cell 1 | 0
CHI05-05-01-L1-1610 | CHI05-05-01-L2-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L1 ADP - COLO5 Cell 1 | Interior - L2 ADP - COLO5 Cell 1 | 0
CHI05-05-01-L1-1540 | CHI05-05-01-L2-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L1 ATSs - COLO5 Cell 1 | Interior - L2 ATSs - COLO5 Cell 1 | 0
CHI05-05-01-L1-1550 | CHI05-05-01-L2-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | Interior - L1 Busway - COLO5 Cell 1 | Interior - L2 Busway - COLO5 Cell 1 | 0
CHI05-05-01-L2-1700 | CHI05-05-01-L3-1820 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L2 UPM - COLO5 | L3 UPM - COLO5 | 0
CHI05-05-01-L2-1620 | CHI05-05-01-L3-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L2 UPS - COLO5 Cell 1 | Interior - L3 UPS - COLO5 Cell 1 | 0
CHI05-05-01-L2-1710 | CHI05-05-01-L3-1830 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L2 XFMR - COLO5 | L3 XFMR - COLO5 | 0
CHI05-05-01-L2-1720 | CHI05-05-01-L3-1840 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L2 GEN - COLO5 | L3 GEN - COLO5 | 0
CHI05-05-01-L2-1630 | CHI05-05-01-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L2 MSB - COLO5 Cell 1 | Interior - L3 MSB - COLO5 Cell 1 | 0
CHI05-05-01-L2-1640 | CHI05-05-01-L3-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L2 PDUs - COLO5 Cell 1 | Interior - L3 PDUs - COLO5 Cell 1 | 0
CHI05-05-01-L2-1730 | CHI05-05-01-L3-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L2 ADP - COLO5 Cell 1 | Interior - L3 ADP - COLO5 Cell 1 | 0
CHI05-05-01-L2-1660 | CHI05-05-01-L3-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L2 ATSs - COLO5 Cell 1 | Interior - L3 ATSs - COLO5 Cell 1 | 0
CHI05-05-01-L2-1670 | CHI05-05-01-L3-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,3 Level 3 Cx - Colo 5 | Interior - L2 Busway - COLO5 Cell 1 | Interior - L3 Busway - COLO5 Cell 1 | 0
CHI05-05-02-L1-1630 | CHI05-05-02-L2-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L1 MSB - COLO5 Cell 2 | Interior - L2 MSB - COLO5 Cell 2 | 0
CHI05-05-02-L2-1750 | CHI05-05-02-L3-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L2 MSB - COLO5 Cell 2 | Interior - L3 MSB - COLO5 Cell 2 | 0
CHI05-05-02-L1-1640 | CHI05-05-02-L2-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L1 PDUs - COLO5 Cell 2 | Interior - L2 PDUs - COLO5 Cell 2 | 0
CHI05-05-02-L2-1760 | CHI05-05-02-L3-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L2 PDUs - COLO5 Cell 2 | Interior - L3 PDUs - COLO5 Cell 2 | 0
CHI05-05-02-L1-1730 | CHI05-05-02-L2-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L1 ADP - COLO5 Cell 2 | Interior - L2 ADP - COLO5 Cell 2 | 0
CHI05-05-02-L2-1850 | CHI05-05-02-L3-1970 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L2 ADP - COLO5 Cell 2 | Interior - L3 ADP - COLO5 Cell 2 | 0
CHI05-05-02-L1-1660 | CHI05-05-02-L2-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L1 ATSs - COLO5 Cell 2 | Interior - L2 ATSs - COLO5 Cell 2 | 0
CHI05-05-02-L2-1780 | CHI05-05-02-L3-1900 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L2 ATSs - COLO5 Cell 2 | Interior - L3 ATSs - COLO5 Cell 2 | 0
CHI05-05-02-L1-1670 | CHI05-05-02-L2-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | Interior - L1 Busway - COLO5 Cell 2 | Interior - L2 Busway - COLO5 Cell 2 | 0
CHI05-05-02-L2-1790 | CHI05-05-02-L3-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | Interior - L2 Busway - COLO5 Cell 2 | Interior - L3 Busway - COLO5 Cell 2 | 0
CHI05-05-02-ER-1500 | CHI05-05-02-L1-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Installation of UPS Equipment - COLO5 Cell 2 - ER | Interior - L1 UPS - COLO5 Cell 2 | 0
CHI05-05-02-DH-1490 | CHI05-05-02-L1-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Install PDU's - COLO5 Cell 2 - DH | Interior - L1 PDUs - COLO5 Cell 2 | 0
CHI05-05-02-ER-1490 | CHI05-05-02-L1-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Installation of ADP & ATS - COLO5 Cell 2 - ER | Interior - L1 ADP - COLO5 Cell 2 | 0
CHI05-05-02-ER-1490 | CHI05-05-02-L1-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Installation of ADP & ATS - COLO5 Cell 2 - ER | Interior - L1 ATSs - COLO5 Cell 2 | 0
CHI05-05-02-ER-1490 | CHI05-05-02-L1-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Installation of ADP & ATS - COLO5 Cell 2 - ER | Interior - L1 Busway - COLO5 Cell 2 | 0
CHI05-05-03-L1-1750 | CHI05-05-03-L2-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L1 MSB - COLO5 Cell 3 | Interior - L2 MSB - COLO5 Cell 3 | 0
CHI05-05-03-L2-1870 | CHI05-05-03-L3-1990 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L2 MSB - COLO5 Cell 3 | Interior - L3 MSB - COLO5 Cell 3 | 0
CHI05-05-03-L1-1760 | CHI05-05-03-L2-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L1 PDUs - COLO5 Cell 3 | Interior - L2 PDUs - COLO5 Cell 3 | 0
CHI05-05-03-L2-1880 | CHI05-05-03-L3-2000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L2 PDUs - COLO5 Cell 3 | Interior - L3 PDUs - COLO5 Cell 3 | 0
CHI05-05-03-L1-1850 | CHI05-05-03-L2-1970 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L1 ADP - COLO5 Cell 3 | Interior - L2 ADP - COLO5 Cell 3 | 0
CHI05-05-03-L2-1970 | CHI05-05-03-L3-2090 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L2 ADP - COLO5 Cell 3 | Interior - L3 ADP - COLO5 Cell 3 | 0
CHI05-05-03-L1-1780 | CHI05-05-03-L2-1900 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L1 ATSs - COLO5 Cell 3 | Interior - L2 ATSs - COLO5 Cell 3 | 0
CHI05-05-03-L2-1900 | CHI05-05-03-L3-2020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L2 ATSs - COLO5 Cell 3 | Interior - L3 ATSs - COLO5 Cell 3 | 0
CHI05-05-03-L1-1790 | CHI05-05-03-L2-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | Interior - L1 Busway - COLO5 Cell 3 | Interior - L2 Busway - COLO5 Cell 3 | 0
CHI05-05-03-L2-1910 | CHI05-05-03-L3-2030 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | Interior - L2 Busway - COLO5 Cell 3 | Interior - L3 Busway - COLO5 Cell 3 | 0
CHI05-05-03-ER-1610 | CHI05-05-03-L1-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Installation of UPS Equipment - COLO5 Cell 3 - ER | Interior - L1 UPS - COLO5 Cell 3 | 0
CHI05-05-03-DH-1600 | CHI05-05-03-L1-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Install PDU's - COLO5 Cell 3 - DH | Interior - L1 PDUs - COLO5 Cell 3 | 0
CHI05-05-03-ER-1600 | CHI05-05-03-L1-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Installation of ADP & ATS - COLO5 Cell 3 - ER | Interior - L1 ADP - COLO5 Cell 3 | 0
CHI05-05-03-ER-1600 | CHI05-05-03-L1-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Installation of ADP & ATS - COLO5 Cell 3 - ER | Interior - L1 ATSs - COLO5 Cell 3 | 0
CHI05-05-03-ER-1600 | CHI05-05-03-L1-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Installation of ADP & ATS - COLO5 Cell 3 - ER | Interior - L1 Busway - COLO5 Cell 3 | 0
CHI05-05-04-L1-1870 | CHI05-05-04-L2-1990 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L1 MSB - COLO5 Cell 4 | Interior - L2 MSB - COLO5 Cell 4 | 0
CHI05-05-04-L2-1990 | CHI05-05-04-L3-2110 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L2 MSB - COLO5 Cell 4 | Interior - L3 MSB - COLO5 Cell 4 | 0
CHI05-05-04-L1-1880 | CHI05-05-04-L2-2000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L1 PDUs - COLO5 Cell 4 | Interior - L2 PDUs - COLO5 Cell 4 | 0
CHI05-05-04-L2-2000 | CHI05-05-04-L3-2120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L2 PDUs - COLO5 Cell 4 | Interior - L3 PDUs - COLO5 Cell 4 | 0
CHI05-05-04-L1-1970 | CHI05-05-04-L2-2090 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L1 ADP - COLO5 Cell 4 | Interior - L2 ADP - COLO5 Cell 4 | 0
CHI05-05-04-L2-2090 | CHI05-05-04-L3-2210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L2 ADP - COLO5 Cell 4 | Interior - L3 ADP - COLO5 Cell 4 | 0
CHI05-05-04-L1-1900 | CHI05-05-04-L2-2020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L1 ATSs - COLO5 Cell 4 | Interior - L2 ATSs - COLO5 Cell 4 | 0
CHI05-05-04-L2-2020 | CHI05-05-04-L3-2140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L2 ATSs - COLO5 Cell 4 | Interior - L3 ATSs - COLO5 Cell 4 | 0
CHI05-05-04-L1-1910 | CHI05-05-04-L2-2030 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | Interior - L1 Busway - COLO5 Cell 4 | Interior - L2 Busway - COLO5 Cell 4 | 0
CHI05-05-04-L2-2030 | CHI05-05-04-L3-2150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | Interior - L2 Busway - COLO5 Cell 4 | Interior - L3 Busway - COLO5 Cell 4 | 0
CHI05-05-01-ER-1390 | CHI05-05-04-L1-1860 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Installation of UPS Equipment - COLO5 Cell 1 - ER | Interior - L1 UPS - COLO5 Cell 4 | 0
CHI05-02-01-L1-1220 | CHI05-02-01-L2-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L1 UPM - COLO2 | L2 UPM - COLO2 | 0
CHI05-02-01-L1-1230 | CHI05-02-01-L2-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L1 XFMR - MV- COLO2 | L2 XFMR - COLO2 | 0
CHI05-02-01-L2-1350 | CHI05-02-01-L3-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L2 XFMR - COLO2 | L3 XFMR - COLO2 | 0
CHI05-02-01-L1-1150 | CHI05-02-01-L2-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L1 MSB - COLO2 Cell 1 | Interior - L2 MSB - COLO2 Cell 1 | 0
CHI05-02-01-L2-1270 | CHI05-02-01-L3-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L2 MSB - COLO2 Cell 1 | Interior - L3 MSB - COLO2 Cell 1 | 0
CHI05-02-01-L1-1160 | CHI05-02-01-L2-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L1 PDUs - COLO2 Cell 1 | Interior - L2 PDUs - COLO2 Cell 1 | 0
CHI05-02-01-L2-1280 | CHI05-02-01-L3-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L2 PDUs - COLO2 Cell 1 | Interior - L3 PDUs - COLO2 Cell 1 | 0
CHI05-02-01-L1-1250 | CHI05-02-01-L2-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L1 ADP - COLO2 Cell 1 | Interior - L2 ADP - COLO2 Cell 1 | 0
CHI05-02-01-L2-1370 | CHI05-02-01-L3-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L2 ADP - COLO2 Cell 1 | Interior - L3 ADP - COLO2 Cell 1 | 0
CHI05-02-01-L1-1180 | CHI05-02-01-L2-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L1 ATSs - COLO2 Cell 1 | Interior - L2 ATSs - COLO2 Cell 1 | 0
CHI05-02-01-L2-1300 | CHI05-02-01-L3-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L2 ATSs - COLO2 Cell 1 | Interior - L3 ATSs - COLO2 Cell 1 | 0
CHI05-02-01-L1-1190 | CHI05-02-01-L2-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | Interior - L1 Busway - COLO2 Cell 1 | Interior - L2 Busway - COLO2 Cell 1 | 0
CHI05-02-01-L2-1310 | CHI05-02-01-L3-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,3 Level 3 Cx - Colo 2 | Interior - L2 Busway - COLO2 Cell 1 | Interior - L3 Busway - COLO2 Cell 1 | 0
CHI05-YARD-2000 | CHI05-02-01-L1-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the Generator - Colo 2 - North | L1 GEN - COLO2 | 0
CHI05-YARD-2120 | CHI05-02-01-L1-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the Generator - Colo 2 - South | L1 GEN - COLO2 | 0
CHI05-02-01-ER-1070 | CHI05-02-01-L1-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Installation of UPS Equipment - COLO2 Cell 1 - ER | Interior - L1 UPS - COLO2 Cell 1 | 0
CHI05-02-01-DH-1040 | CHI05-02-01-L1-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Install PDU's - COLO2 Cell 1 - DH | Interior - L1 PDUs - COLO2 Cell 1 | 0
CHI05-02-01-ER-1050 | CHI05-02-01-L1-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Installation of ADP & ATS - COLO2 Cell 1 - ER | Interior - L1 ADP - COLO2 Cell 1 | 0
CHI05-02-01-ER-1050 | CHI05-02-01-L1-1180 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Installation of ADP & ATS - COLO2 Cell 1 - ER | Interior - L1 ATSs - COLO2 Cell 1 | 0
CHI05-02-01-ER-1050 | CHI05-02-01-L1-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Installation of ADP & ATS - COLO2 Cell 1 - ER | Interior - L1 Busway - COLO2 Cell 1 | 0
CHI05-02-02-L1-1270 | CHI05-02-02-L2-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L1 MSB - COLO2 Cell 2 | Interior - L2 MSB - COLO2 Cell 2 | 0
CHI05-02-02-L2-1390 | CHI05-02-02-L3-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L2 MSB - COLO2 Cell 2 | Interior - L3 MSB - COLO2 Cell 2 | 0
CHI05-02-02-L1-1280 | CHI05-02-02-L2-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L1 PDUs - COLO2 Cell 2 | Interior - L2 PDUs - COLO2 Cell 2 | 0
CHI05-02-02-L2-1400 | CHI05-02-02-L3-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L2 PDUs - COLO2 Cell 2 | Interior - L3 PDUs - COLO2 Cell 2 | 0
CHI05-02-02-L1-1370 | CHI05-02-02-L2-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L1 ADP - COLO2 Cell 2 | Interior - L2 ADP - COLO2 Cell 2 | 0
CHI05-02-02-L2-1490 | CHI05-02-02-L3-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L2 ADP - COLO2 Cell 2 | Interior - L3 ADP - COLO2 Cell 2 | 0
CHI05-02-02-L1-1300 | CHI05-02-02-L2-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L1 ATSs - COLO2 Cell 2 | Interior - L2 ATSs - COLO2 Cell 2 | 0
CHI05-02-02-L2-1420 | CHI05-02-02-L3-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L2 ATSs - COLO2 Cell 2 | Interior - L3 ATSs - COLO2 Cell 2 | 0
CHI05-02-02-L1-1310 | CHI05-02-02-L2-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L1 Busway - COLO2 Cell 2 | Interior - L2 Busway - COLO2 Cell 2 | 0
CHI05-02-02-L2-1430 | CHI05-02-02-L3-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L2 Busway - COLO2 Cell 2 | Interior - L3 Busway - COLO2 Cell 2 | 0
CHI05-02-02-L1-1290 | CHI05-02-02-L2-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | Interior - L1 AHUs - COLO2 Cell 2 | Interior - L2 AHUs - COLO2 Cell 2 | 0
CHI05-02-02-L2-1410 | CHI05-02-02-L3-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | Interior - L2 AHUs - COLO2 Cell 2 | Interior - L3 AHUs - COLO2 Cell 2 | 0
CHI05-02-02-ER-1160 | CHI05-02-02-L1-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Installation of ADP & ATS - COLO2 Cell 2 - ER | Interior - L1 ADP - COLO2 Cell 2 | 0
CHI05-02-02-ER-1160 | CHI05-02-02-L1-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Installation of ADP & ATS - COLO2 Cell 2 - ER | Interior - L1 ATSs - COLO2 Cell 2 | 0
CHI05-02-02-ER-1160 | CHI05-02-02-L1-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Installation of ADP & ATS - COLO2 Cell 2 - ER | Interior - L1 Busway - COLO2 Cell 2 | 0
CHI05-02-02-DH-1160 | CHI05-02-02-L1-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Install PDU's - COLO2 Cell 2 - DH | Interior - L1 PDUs - COLO2 Cell 2 | 0
CHI05-02-02-ER-1170 | CHI05-02-02-L1-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Installation of UPS Equipment - COLO2 Cell 2 - ER | Interior - L1 UPS - COLO2 Cell 2 | 0
CHI05-02-03-L1-1390 | CHI05-02-03-L2-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L1 MSB - COLO2 Cell 3 | Interior - L2 MSB - COLO2 Cell 3 | 0
CHI05-02-03-L2-1510 | CHI05-02-03-L3-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L2 MSB - COLO2 Cell 3 | Interior - L3 MSB - COLO2 Cell 3 | 0
CHI05-02-03-L1-1400 | CHI05-02-03-L2-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L1 PDUs - COLO2 Cell 3 | Interior - L2 PDUs - COLO2 Cell 3 | 0
CHI05-02-03-L2-1520 | CHI05-02-03-L3-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L2 PDUs - COLO2 Cell 3 | Interior - L3 PDUs - COLO2 Cell 3 | 0
CHI05-02-03-L1-1490 | CHI05-02-03-L2-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L1 ADP - COLO2 Cell 3 | Interior - L2 ADP - COLO2 Cell 3 | 0
CHI05-02-03-L2-1610 | CHI05-02-03-L3-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L2 ADP - COLO2 Cell 3 | Interior - L3 ADP - COLO2 Cell 3 | 0
CHI05-02-03-L1-1420 | CHI05-02-03-L2-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L1 ATSs - COLO2 Cell 3 | Interior - L2 ATSs - COLO2 Cell 3 | 0
CHI05-02-03-L2-1540 | CHI05-02-03-L3-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L2 ATSs - COLO2 Cell 3 | Interior - L3 ATSs - COLO2 Cell 3 | 0
CHI05-02-03-L1-1430 | CHI05-02-03-L2-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L1 Busway - COLO2 Cell 3 | Interior - L2 Busway - COLO2 Cell 3 | 0
CHI05-02-03-L2-1550 | CHI05-02-03-L3-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L2 Busway - COLO2 Cell 3 | Interior - L3 Busway - COLO2 Cell 3 | 0
CHI05-02-03-L1-1410 | CHI05-02-03-L2-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | Interior - L1 AHUs - COLO2 Cell 3 | Interior - L2 AHUs - COLO2 Cell 3 | 0
CHI05-02-03-L2-1530 | CHI05-02-03-L3-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | Interior - L2 AHUs - COLO2 Cell 3 | Interior - L3 AHUs - COLO2 Cell 3 | 0
CHI05-05-01-ER-1390 | CHI05-02-03-L1-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Installation of UPS Equipment - COLO5 Cell 1 - ER | Interior - L1 UPS - COLO2 Cell 3 | 0
CHI05-02-04-L1-1510 | CHI05-02-04-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L1 MSB - COLO2 Cell 4 | Interior - L2 MSB - COLO2 Cell 4 | 0
CHI05-02-04-L2-1630 | CHI05-02-04-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L2 MSB - COLO2 Cell 4 | Interior - L3 MSB - COLO2 Cell 4 | 0
CHI05-02-04-L1-1520 | CHI05-02-04-L2-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L1 PDUs - COLO2 Cell 4 | Interior - L2 PDUs - COLO2 Cell 4 | 0
CHI05-02-04-L2-1640 | CHI05-02-04-L3-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L2 PDUs - COLO2 Cell 4 | Interior - L3 PDUs - COLO2 Cell 4 | 0
CHI05-02-04-L1-1610 | CHI05-02-04-L2-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L1 ADP - COLO2 Cell 4 | Interior - L2 ADP - COLO2 Cell 4 | 0
CHI05-02-04-L2-1730 | CHI05-02-04-L3-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L2 ADP - COLO2 Cell 4 | Interior - L3 ADP - COLO2 Cell 4 | 0
CHI05-02-04-L1-1540 | CHI05-02-04-L2-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L1 ATSs - COLO2 Cell 4 | Interior - L2 ATSs - COLO2 Cell 4 | 0
CHI05-02-04-L2-1660 | CHI05-02-04-L3-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L2 ATSs - COLO2 Cell 4 | Interior - L3 ATSs - COLO2 Cell 4 | 0
CHI05-02-04-L1-1550 | CHI05-02-04-L2-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L1 Busway - COLO2 Cell 4 | Interior - L2 Busway - COLO2 Cell 4 | 0
CHI05-02-04-L2-1670 | CHI05-02-04-L3-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L2 Busway - COLO2 Cell 4 | Interior - L3 Busway - COLO2 Cell 4 | 0
CHI05-02-04-L1-1530 | CHI05-02-04-L2-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | Interior - L1 AHUs - COLO2 Cell 4 | Interior - L2 AHUs - COLO2 Cell 4 | 0
CHI05-02-04-L2-1650 | CHI05-02-04-L3-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | Interior - L2 AHUs - COLO2 Cell 4 | Interior - L3 AHUs - COLO2 Cell 4 | 0
CHI05-02-04-ER-1390 | CHI05-02-04-L1-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Installation of UPS Equipment - COLO2 Cell 4 - ER | Interior - L1 UPS - COLO2 Cell 4 | 0
CHI05-02-04-DH-1380 | CHI05-02-04-L1-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Install PDU's - COLO2 Cell 4 - DH | Interior - L1 PDUs - COLO2 Cell 4 | 0
CHI05-02-04-ER-1380 | CHI05-02-04-L1-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Installation of ADP & ATS - COLO2 Cell 4 - ER | Interior - L1 ADP - COLO2 Cell 4 | 0
CHI05-02-04-ER-1380 | CHI05-02-04-L1-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Installation of ADP & ATS - COLO2 Cell 4 - ER | Interior - L1 ATSs - COLO2 Cell 4 | 0
CHI05-02-04-ER-1380 | CHI05-02-04-L1-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Installation of ADP & ATS - COLO2 Cell 4 - ER | Interior - L1 Busway - COLO2 Cell 4 | 0
CHI05-03-01-L1-1340 | CHI05-03-01-L2-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L1 UPM - COLO3 | L2 UPM - COLO3 | 0
CHI05-03-01-L2-1460 | CHI05-03-01-L3-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L2 UPM - COLO3 | L3 UPM - COLO3 | 0
CHI05-03-01-L1-1350 | CHI05-03-01-L2-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L1 XFMR - MV- COLO3 | L2 XFMR - COLO3 | 0
CHI05-03-01-L2-1470 | CHI05-03-01-L3-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L2 XFMR - COLO3 | L3 XFMR - COLO3 | 0
CHI05-03-01-L1-1270 | CHI05-03-01-L2-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L1 MSB - COLO3 Cell 1 | Interior - L2 MSB - COLO3 Cell 1 | 0
CHI05-03-01-L2-1390 | CHI05-03-01-L3-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L2 MSB - COLO3 Cell 1 | Interior - L3 MSB - COLO3 Cell 1 | 0
CHI05-03-01-L1-1280 | CHI05-03-01-L2-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L1 PDUs - COLO3 Cell 1 | Interior - L2 PDUs - COLO3 Cell 1 | 0
CHI05-03-01-L2-1400 | CHI05-03-01-L3-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L2 PDUs - COLO3 Cell 1 | Interior - L3 PDUs - COLO3 Cell 1 | 0
CHI05-03-01-L1-1370 | CHI05-03-01-L2-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L1 ADP - COLO3 Cell 1 | Interior - L2 ADP - COLO3 Cell 1 | 0
CHI05-03-01-L2-1490 | CHI05-03-01-L3-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L2 ADP - COLO3 Cell 1 | Interior - L3 ADP - COLO3 Cell 1 | 0
CHI05-03-01-L1-1300 | CHI05-03-01-L2-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L1 ATSs - COLO3 Cell 1 | Interior - L2 ATSs - COLO3 Cell 1 | 0
CHI05-03-01-L2-1420 | CHI05-03-01-L3-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L2 ATSs - COLO3 Cell 1 | Interior - L3 ATSs - COLO3 Cell 1 | 0
CHI05-03-01-L1-1310 | CHI05-03-01-L2-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | Interior - L1 Busway - COLO3 Cell 1 | Interior - L2 Busway - COLO3 Cell 1 | 0
CHI05-03-01-L2-1430 | CHI05-03-01-L3-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,3 Level 3 Cx - Colo 3 | Interior - L2 Busway - COLO3 Cell 1 | Interior - L3 Busway - COLO3 Cell 1 | 0
CHI05-YARD-2060 | CHI05-03-01-L1-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the Generator - Colo 3 - North | L1 GEN - COLO3 | 0
CHI05-03-02-L1-1390 | CHI05-03-02-L2-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L1 MSB - COLO3 Cell 2 | Interior - L2 MSB - COLO3 Cell 2 | 0
CHI05-03-02-L2-1510 | CHI05-03-02-L3-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L2 MSB - COLO3 Cell 2 | Interior - L3 MSB - COLO3 Cell 2 | 0
CHI05-03-02-L1-1400 | CHI05-03-02-L2-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L1 PDUs - COLO3 Cell 2 | Interior - L2 PDUs - COLO3 Cell 2 | 0
CHI05-03-02-L2-1520 | CHI05-03-02-L3-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L2 PDUs - COLO3 Cell 2 | Interior - L3 PDUs - COLO3 Cell 2 | 0
CHI05-03-02-L1-1490 | CHI05-03-02-L2-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L1 ADP - COLO3 Cell 2 | Interior - L2 ADP - COLO3 Cell 2 | 0
CHI05-03-02-L2-1610 | CHI05-03-02-L3-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L2 ADP - COLO3 Cell 2 | Interior - L3 ADP - COLO3 Cell 2 | 0
CHI05-03-02-L1-1420 | CHI05-03-02-L2-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L1 ATSs - COLO3 Cell 2 | Interior - L2 ATSs - COLO3 Cell 2 | 0
CHI05-03-02-L2-1540 | CHI05-03-02-L3-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L2 ATSs - COLO3 Cell 2 | Interior - L3 ATSs - COLO3 Cell 2 | 0
CHI05-03-02-L1-1430 | CHI05-03-02-L2-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | Interior - L1 Busway - COLO3 Cell 2 | Interior - L2 Busway - COLO3 Cell 2 | 0
CHI05-03-02-L2-1550 | CHI05-03-02-L3-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | Interior - L2 Busway - COLO3 Cell 2 | Interior - L3 Busway - COLO3 Cell 2 | 0
CHI05-03-02-ER-1270 | CHI05-03-02-L1-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Installation of ADP & ATS - COLO3 Cell 2 - ER | Interior - L1 ADP - COLO3 Cell 2 | 0
CHI05-03-02-ER-1270 | CHI05-03-02-L1-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Installation of ADP & ATS - COLO3 Cell 2 - ER | Interior - L1 ATSs - COLO3 Cell 2 | 0
CHI05-03-02-ER-1270 | CHI05-03-02-L1-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Installation of ADP & ATS - COLO3 Cell 2 - ER | Interior - L1 Busway - COLO3 Cell 2 | 0
CHI05-03-02-ER-1280 | CHI05-03-02-L1-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Installation of UPS Equipment - COLO3 Cell 2 - ER | Interior - L1 UPS - COLO3 Cell 2 | 0
CHI05-03-02-DH-1270 | CHI05-03-02-L1-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Install PDU's - COLO3 Cell 2 - DH | Interior - L1 PDUs - COLO3 Cell 2 | 0
CHI05-03-01-ER-1160 | CHI05-03-01-L1-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Installation of ADP & ATS - COLO3 Cell 1 - ER | Interior - L1 ADP - COLO3 Cell 1 | 0
CHI05-03-01-ER-1160 | CHI05-03-01-L1-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Installation of ADP & ATS - COLO3 Cell 1 - ER | Interior - L1 ATSs - COLO3 Cell 1 | 0
CHI05-03-01-ER-1160 | CHI05-03-01-L1-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Installation of ADP & ATS - COLO3 Cell 1 - ER | Interior - L1 Busway - COLO3 Cell 1 | 0
CHI05-03-04-L1-1630 | CHI05-03-04-L2-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L1 MSB - COLO3 Cell 4 | Interior - L2 MSB - COLO3 Cell 4 | 0
CHI05-03-04-L2-1750 | CHI05-03-04-L3-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L2 MSB - COLO3 Cell 4 | Interior - L3 MSB - COLO3 Cell 4 | 0
CHI05-03-04-L1-1640 | CHI05-03-04-L2-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L1 PDUs - COLO3 Cell 4 | Interior - L2 PDUs - COLO3 Cell 4 | 0
CHI05-03-04-L2-1760 | CHI05-03-04-L3-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L2 PDUs - COLO3 Cell 4 | Interior - L3 PDUs - COLO3 Cell 4 | 0
CHI05-03-04-L1-1730 | CHI05-03-04-L2-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L1 ADP - COLO3 Cell 4 | Interior - L2 ADP - COLO3 Cell 4 | 0
CHI05-03-04-L2-1850 | CHI05-03-04-L3-1970 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L2 ADP - COLO3 Cell 4 | Interior - L3 ADP - COLO3 Cell 4 | 0
CHI05-03-04-L1-1660 | CHI05-03-04-L2-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L1 ATSs - COLO3 Cell 4 | Interior - L2 ATSs - COLO3 Cell 4 | 0
CHI05-03-04-L2-1780 | CHI05-03-04-L3-1900 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L2 ATSs - COLO3 Cell 4 | Interior - L3 ATSs - COLO3 Cell 4 | 0
CHI05-03-04-L1-1670 | CHI05-03-04-L2-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | Interior - L1 Busway - COLO3 Cell 4 | Interior - L2 Busway - COLO3 Cell 4 | 0
CHI05-03-04-L2-1790 | CHI05-03-04-L3-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | Interior - L2 Busway - COLO3 Cell 4 | Interior - L3 Busway - COLO3 Cell 4 | 0
CHI05-03-04-ER-1490 | CHI05-03-04-L1-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Installation of ADP & ATS - COLO3 Cell 4 - ER | Interior - L1 ADP - COLO3 Cell 4 | 0
CHI05-03-04-ER-1490 | CHI05-03-04-L1-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Installation of ADP & ATS - COLO3 Cell 4 - ER | Interior - L1 ATSs - COLO3 Cell 4 | 0
CHI05-03-04-ER-1490 | CHI05-03-04-L1-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Installation of ADP & ATS - COLO3 Cell 4 - ER | Interior - L1 Busway - COLO3 Cell 4 | 0
CHI05-03-04-ER-1500 | CHI05-03-04-L1-1620 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Installation of UPS Equipment - COLO3 Cell 4 - ER | Interior - L1 UPS - COLO3 Cell 4 | 0
CHI05-03-04-DH-1490 | CHI05-03-04-L1-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Install PDU's - COLO3 Cell 4 - DH | Interior - L1 PDUs - COLO3 Cell 4 | 0
CHI05-04-01-L1-1460 | CHI05-04-01-L2-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L1 UPM - COLO4 | L2 UPM - COLO4 | 0
CHI05-04-01-L1-1470 | CHI05-04-01-L2-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L1 XFMR - MV- COLO4 | L2 XFMR - COLO4 | 0
CHI05-04-01-L2-1590 | CHI05-04-01-L3-1710 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L2 XFMR - COLO4 | L3 XFMR - COLO4 | 0
CHI05-04-01-L1-1390 | CHI05-04-01-L2-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L1 MSB - COLO4 Cell 1 | Interior - L2 MSB - COLO4 Cell 1 | 0
CHI05-04-01-L2-1510 | CHI05-04-01-L3-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L2 MSB - COLO4 Cell 1 | Interior - L3 MSB - COLO4 Cell 1 | 0
CHI05-04-01-L1-1400 | CHI05-04-01-L2-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L1 PDUs - COLO4 Cell 1 | Interior - L2 PDUs - COLO4 Cell 1 | 0
CHI05-04-01-L2-1520 | CHI05-04-01-L3-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L2 PDUs - COLO4 Cell 1 | Interior - L3 PDUs - COLO4 Cell 1 | 0
CHI05-04-01-L1-1490 | CHI05-04-01-L2-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L1 ADP - COLO4 Cell 1 | Interior - L2 ADP - COLO4 Cell 1 | 0
CHI05-04-01-L2-1610 | CHI05-04-01-L3-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L2 ADP - COLO4 Cell 1 | Interior - L3 ADP - COLO4 Cell 1 | 0
CHI05-04-01-L1-1420 | CHI05-04-01-L2-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L1 ATSs - COLO4 Cell 1 | Interior - L2 ATSs - COLO4 Cell 1 | 0
CHI05-04-01-L2-1540 | CHI05-04-01-L3-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L2 ATSs - COLO4 Cell 1 | Interior - L3 ATSs - COLO4 Cell 1 | 0
CHI05-04-01-L1-1430 | CHI05-04-01-L2-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | Interior - L1 Busway - COLO4 Cell 1 | Interior - L2 Busway - COLO4 Cell 1 | 0
CHI05-04-01-L2-1550 | CHI05-04-01-L3-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,3 Level 3 Cx - Colo 4 | Interior - L2 Busway - COLO4 Cell 1 | Interior - L3 Busway - COLO4 Cell 1 | 0
CHI05-04-01-ER-1280 | CHI05-04-01-L1-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Installation of UPS Equipment - COLO4 Cell 1 - ER | Interior - L1 UPS - COLO4 Cell 1 | 0
CHI05-04-01-ER-1270 | CHI05-04-01-L1-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Installation of ADP & ATS - COLO4 Cell 1 - ER | Interior - L1 ADP - COLO4 Cell 1 | 0
CHI05-04-01-ER-1270 | CHI05-04-01-L1-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Installation of ADP & ATS - COLO4 Cell 1 - ER | Interior - L1 ATSs - COLO4 Cell 1 | 0
CHI05-04-01-ER-1270 | CHI05-04-01-L1-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Installation of ADP & ATS - COLO4 Cell 1 - ER | Interior - L1 Busway - COLO4 Cell 1 | 0
CHI05-04-01-DH-1270 | CHI05-04-01-L1-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Install PDU's - COLO4 Cell 1 - DH | Interior - L1 PDUs - COLO4 Cell 1 | 0
CHI05-04-02-L1-1510 | CHI05-04-02-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L1 MSB - COLO4 Cell 2 | Interior - L2 MSB - COLO4 Cell 2 | 0
CHI05-04-02-L2-1630 | CHI05-04-02-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L2 MSB - COLO4 Cell 2 | Interior - L3 MSB - COLO4 Cell 2 | 0
CHI05-04-02-L1-1520 | CHI05-04-02-L2-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L1 PDUs - COLO4 Cell 2 | Interior - L2 PDUs - COLO4 Cell 2 | 0
CHI05-04-02-L2-1640 | CHI05-04-02-L3-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L2 PDUs - COLO4 Cell 2 | Interior - L3 PDUs - COLO4 Cell 2 | 0
CHI05-04-02-L1-1610 | CHI05-04-02-L2-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L1 ADP - COLO4 Cell 2 | Interior - L2 ADP - COLO4 Cell 2 | 0
CHI05-04-02-L2-1730 | CHI05-04-02-L3-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L2 ADP - COLO4 Cell 2 | Interior - L3 ADP - COLO4 Cell 2 | 0
CHI05-04-02-L1-1540 | CHI05-04-02-L2-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L1 ATSs - COLO4 Cell 2 | Interior - L2 ATSs - COLO4 Cell 2 | 0
CHI05-04-02-L2-1660 | CHI05-04-02-L3-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L2 ATSs - COLO4 Cell 2 | Interior - L3 ATSs - COLO4 Cell 2 | 0
CHI05-04-02-L1-1550 | CHI05-04-02-L2-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | Interior - L1 Busway - COLO4 Cell 2 | Interior - L2 Busway - COLO4 Cell 2 | 0
CHI05-04-02-L2-1670 | CHI05-04-02-L3-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Interior - L2 Busway - COLO4 Cell 2 | Interior - L3 Busway - COLO4 Cell 2 | 0
CHI05-04-02-ER-1390 | CHI05-04-02-L1-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Installation of UPS Equipment - COLO4 Cell 2 - ER | Interior - L1 UPS - COLO4 Cell 2 | 0
CHI05-04-02-DH-1380 | CHI05-04-02-L1-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Install PDU's - COLO4 Cell 2 - DH | Interior - L1 PDUs - COLO4 Cell 2 | 0
CHI05-04-02-ER-1380 | CHI05-04-02-L1-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Installation of ADP & ATS - COLO4 Cell 2 - ER | Interior - L1 ADP - COLO4 Cell 2 | 0
CHI05-04-02-ER-1380 | CHI05-04-02-L1-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Installation of ADP & ATS - COLO4 Cell 2 - ER | Interior - L1 ATSs - COLO4 Cell 2 | 0
CHI05-04-02-ER-1380 | CHI05-04-02-L1-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Installation of ADP & ATS - COLO4 Cell 2 - ER | Interior - L1 Busway - COLO4 Cell 2 | 0
CHI05-04-03-L1-1630 | CHI05-04-03-L2-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L1 MSB - COLO4 Cell 3 | Interior - L2 MSB - COLO4 Cell 3 | 0
CHI05-04-03-L2-1750 | CHI05-04-03-L3-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L2 MSB - COLO4 Cell 3 | Interior - L3 MSB - COLO4 Cell 3 | 0
CHI05-04-03-L1-1640 | CHI05-04-03-L2-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L1 PDUs - COLO4 Cell 3 | Interior - L2 PDUs - COLO4 Cell 3 | 0
CHI05-04-03-L2-1760 | CHI05-04-03-L3-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L2 PDUs - COLO4 Cell 3 | Interior - L3 PDUs - COLO4 Cell 3 | 0
CHI05-04-03-L1-1730 | CHI05-04-03-L2-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L1 ADP - COLO4 Cell 3 | Interior - L2 ADP - COLO4 Cell 3 | 0
CHI05-04-03-L2-1850 | CHI05-04-03-L3-1970 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L2 ADP - COLO4 Cell 3 | Interior - L3 ADP - COLO4 Cell 3 | 0
CHI05-04-03-L1-1660 | CHI05-04-03-L2-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L1 ATSs - COLO4 Cell 3 | Interior - L2 ATSs - COLO4 Cell 3 | 0
CHI05-04-03-L2-1780 | CHI05-04-03-L3-1900 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L2 ATSs - COLO4 Cell 3 | Interior - L3 ATSs - COLO4 Cell 3 | 0
CHI05-04-03-L1-1670 | CHI05-04-03-L2-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L1 Busway - COLO4 Cell 3 | Interior - L2 Busway - COLO4 Cell 3 | 0
CHI05-04-03-L2-1790 | CHI05-04-03-L3-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L2 Busway - COLO4 Cell 3 | Interior - L3 Busway - COLO4 Cell 3 | 0
CHI05-04-03-L1-1650 | CHI05-04-03-L2-1770 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | Interior - L1 AHUs - COLO4 Cell 3 | Interior - L2 AHUs - COLO4 Cell 3 | 0
CHI05-04-03-L2-1770 | CHI05-04-03-L3-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | Interior - L2 AHUs - COLO4 Cell 3 | Interior - L3 AHUs - COLO4 Cell 3 | 0
CHI05-04-03-ER-1500 | CHI05-04-03-L1-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Installation of UPS Equipment - COLO4 Cell 3 - ER | Interior - L1 UPS - COLO4 Cell 3 | 0
CHI05-04-03-ER-1490 | CHI05-04-03-L1-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Installation of ADP & ATS - COLO4 Cell 3 - ER | Interior - L1 ADP - COLO4 Cell 3 | 0
CHI05-04-03-ER-1490 | CHI05-04-03-L1-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Installation of ADP & ATS - COLO4 Cell 3 - ER | Interior - L1 ATSs - COLO4 Cell 3 | 0
CHI05-04-03-ER-1490 | CHI05-04-03-L1-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Installation of ADP & ATS - COLO4 Cell 3 - ER | Interior - L1 Busway - COLO4 Cell 3 | 0
CHI05-04-03-DH-1490 | CHI05-04-03-L1-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Install PDU's - COLO4 Cell 3 - DH | Interior - L1 PDUs - COLO4 Cell 3 | 0
CHI05-04-04-L1-1750 | CHI05-04-04-L2-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L1 MSB - COLO4 Cell 4 | Interior - L2 MSB - COLO4 Cell 4 | 0
CHI05-04-04-L2-1870 | CHI05-04-04-L3-1990 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L2 MSB - COLO4 Cell 4 | Interior - L3 MSB - COLO4 Cell 4 | 0
CHI05-04-04-L1-1760 | CHI05-04-04-L2-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L1 PDUs - COLO4 Cell 4 | Interior - L2 PDUs - COLO4 Cell 4 | 0
CHI05-04-04-L2-1880 | CHI05-04-04-L3-2000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L2 PDUs - COLO4 Cell 4 | Interior - L3 PDUs - COLO4 Cell 4 | 0
CHI05-04-04-L1-1850 | CHI05-04-04-L2-1970 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L1 ADP - COLO4 Cell 4 | Interior - L2 ADP - COLO4 Cell 4 | 0
CHI05-04-04-L2-1970 | CHI05-04-04-L3-2090 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L2 ADP - COLO4 Cell 4 | Interior - L3 ADP - COLO4 Cell 4 | 0
CHI05-04-04-L1-1780 | CHI05-04-04-L2-1900 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L1 ATSs - COLO4 Cell 4 | Interior - L2 ATSs - COLO4 Cell 4 | 0
CHI05-04-04-L2-1900 | CHI05-04-04-L3-2020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L2 ATSs - COLO4 Cell 4 | Interior - L3 ATSs - COLO4 Cell 4 | 0
CHI05-04-04-L1-1790 | CHI05-04-04-L2-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L1 Busway - COLO4 Cell 4 | Interior - L2 Busway - COLO4 Cell 4 | 0
CHI05-04-04-L2-1910 | CHI05-04-04-L3-2030 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L2 Busway - COLO4 Cell 4 | Interior - L3 Busway - COLO4 Cell 4 | 0
CHI05-04-04-L1-1770 | CHI05-04-04-L2-1890 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | Interior - L1 AHUs - COLO4 Cell 4 | Interior - L2 AHUs - COLO4 Cell 4 | 0
CHI05-04-04-L2-1890 | CHI05-04-04-L3-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | Interior - L2 AHUs - COLO4 Cell 4 | Interior - L3 AHUs - COLO4 Cell 4 | 0
CHI05-04-04-ER-1600 | CHI05-04-04-L1-1850 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Installation of ADP & ATS - COLO4 Cell 4 - ER | Interior - L1 ADP - COLO4 Cell 4 | 0
CHI05-04-04-ER-1600 | CHI05-04-04-L1-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Installation of ADP & ATS - COLO4 Cell 4 - ER | Interior - L1 ATSs - COLO4 Cell 4 | 0
CHI05-04-04-ER-1600 | CHI05-04-04-L1-1790 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Installation of ADP & ATS - COLO4 Cell 4 - ER | Interior - L1 Busway - COLO4 Cell 4 | 0
CHI05-04-04-ER-1610 | CHI05-04-04-L1-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Installation of UPS Equipment - COLO4 Cell 4 - ER | Interior - L1 UPS - COLO4 Cell 4 | 0
CHI05-04-04-DH-1600 | CHI05-04-04-L1-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Install PDU's - COLO4 Cell 4 - DH | Interior - L1 PDUs - COLO4 Cell 4 | 0
CHI05-02-04-L2-1650 | CHI05-02-L2CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Interior - L2 AHUs - COLO2 Cell 4 | Complete L2 CX (Yellow Tag) for Colo 2 | 0
CHI05-02-L1CX-F | CHI05-02-BAS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Complete L1 Cx (All Red Tags/ROJ) for Colo 2 | Complete BAS SAT for Colo 2 | 0
CHI05-02-L2CX-F | CHI05-02-L3CX-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | Complete L2 CX (Yellow Tag) for Colo 2 | Complete L3 CX (Green Tag) for Colo 2 | 0
CHI05-05-04-DH-1710 | CHI05-05-04-L1-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Install PDU's - COLO5 Cell 4 - DH | Interior - L1 PDUs - COLO5 Cell 4 | 0
CHI05-02-03-DH-1270 | CHI05-02-03-L1-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Install PDU's - COLO2 Cell 3 - DH | Interior - L1 PDUs - COLO2 Cell 3 | 0
CHI05-03-01-DH-1160 | CHI05-03-01-L1-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Install PDU's - COLO3 Cell 1 - DH | Interior - L1 PDUs - COLO3 Cell 1 | 0
CHI05-03-03-DH-1380 | CHI05-03-03-L1-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | Install PDU's - COLO3 Cell 3 - DH | Interior - L1 PDUs - COLO3 Cell 3 | 0
CHI05-05-01-DH-1380 | CHI05-05-02-DH-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Install PDU's - COLO5 Cell 1 - DH | Install PDU's - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1490 | CHI05-05-03-DH-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Install PDU's - COLO5 Cell 2 - DH | Install PDU's - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1600 | CHI05-05-04-DH-1710 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Install PDU's - COLO5 Cell 3 - DH | Install PDU's - COLO5 Cell 4 - DH | 0
CHI05-02-01-DH-1040 | CHI05-02-02-DH-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Install PDU's - COLO2 Cell 1 - DH | Install PDU's - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1160 | CHI05-02-03-DH-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Install PDU's - COLO2 Cell 2 - DH | Install PDU's - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1270 | CHI05-02-04-DH-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Install PDU's - COLO2 Cell 3 - DH | Install PDU's - COLO2 Cell 4 - DH | 0
CHI05-03-01-DH-1160 | CHI05-03-02-DH-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Install PDU's - COLO3 Cell 1 - DH | Install PDU's - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1270 | CHI05-03-03-DH-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Install PDU's - COLO3 Cell 2 - DH | Install PDU's - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1380 | CHI05-03-04-DH-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Install PDU's - COLO3 Cell 3 - DH | Install PDU's - COLO3 Cell 4 - DH | 0
CHI05-04-01-DH-1270 | CHI05-04-02-DH-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Install PDU's - COLO4 Cell 1 - DH | Install PDU's - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1380 | CHI05-04-03-DH-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Install PDU's - COLO4 Cell 2 - DH | Install PDU's - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1490 | CHI05-04-04-DH-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Install PDU's - COLO4 Cell 3 - DH | Install PDU's - COLO4 Cell 4 - DH | 0
CHI05-05-01-MG-1340 | CHI05-05-02-MG-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 1 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 2 - MG | 0
CHI05-05-02-MG-1450 | CHI05-05-03-MG-1560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 2 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1560 | CHI05-05-04-MG-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 3 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 4 - MG | 0
CHI05-02-01-MG-1010 | CHI05-02-02-MG-1120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 1 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1120 | CHI05-02-03-MG-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 2 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1230 | CHI05-02-04-MG-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 3 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 4 - MG | 0
CHI05-03-01-MG-1120 | CHI05-03-02-MG-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 1 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1230 | CHI05-03-03-MG-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 2 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1340 | CHI05-03-04-MG-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 3 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 4 - MG | 0
CHI05-04-01-MG-1230 | CHI05-04-02-MG-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 1 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1340 | CHI05-04-03-MG-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 2 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1450 | CHI05-04-04-MG-1560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 3 - MG | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG | 0
CHI05-05-01-MG-1350 | CHI05-05-02-MG-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Overhead MEP Installation - COLO5 Cell 1 - MG | Overhead MEP Installation - COLO5 Cell 2 - MG | 0
CHI05-05-02-MG-1460 | CHI05-05-03-MG-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Overhead MEP Installation - COLO5 Cell 2 - MG | Overhead MEP Installation - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1570 | CHI05-05-04-MG-1680 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Overhead MEP Installation - COLO5 Cell 3 - MG | Overhead MEP Installation - COLO5 Cell 4 - MG | 0
CHI05-02-01-MG-1020 | CHI05-02-02-MG-1130 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Overhead MEP Installation - COLO2 Cell 1 - MG | Overhead MEP Installation - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1130 | CHI05-02-03-MG-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Overhead MEP Installation - COLO2 Cell 2 - MG | Overhead MEP Installation - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1240 | CHI05-02-04-MG-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Overhead MEP Installation - COLO2 Cell 3 - MG | Overhead MEP Installation - COLO2 Cell 4 - MG | 0
CHI05-03-01-MG-1130 | CHI05-03-02-MG-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Overhead MEP Installation - COLO3 Cell 1 - MG | Overhead MEP Installation - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1240 | CHI05-03-03-MG-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Overhead MEP Installation - COLO3 Cell 2 - MG | Overhead MEP Installation - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1350 | CHI05-03-04-MG-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Overhead MEP Installation - COLO3 Cell 3 - MG | Overhead MEP Installation - COLO3 Cell 4 - MG | 0
CHI05-04-01-MG-1240 | CHI05-04-02-MG-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Overhead MEP Installation - COLO4 Cell 1 - MG | Overhead MEP Installation - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1350 | CHI05-04-03-MG-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Overhead MEP Installation - COLO4 Cell 2 - MG | Overhead MEP Installation - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1460 | CHI05-04-04-MG-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Overhead MEP Installation - COLO4 Cell 3 - MG | Overhead MEP Installation - COLO4 Cell 4 - MG | 0
CHI05-05-01-DH-1390 | CHI05-05-02-DH-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 1 - DH | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1500 | CHI05-05-03-DH-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 2 - DH | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1610 | CHI05-05-04-DH-1720 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 3 - DH | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 4 - DH | 0
CHI05-02-01-DH-1030 | CHI05-02-02-DH-1170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 1 - DH | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1170 | CHI05-02-03-DH-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 2 - DH | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1280 | CHI05-02-04-DH-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 3 - DH | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 4 - DH | 0
CHI05-03-01-DH-1170 | CHI05-03-02-DH-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 1 - DH | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1280 | CHI05-03-03-DH-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1390 | CHI05-03-04-DH-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 4 - DH | 0
CHI05-04-01-DH-1280 | CHI05-04-02-DH-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 1 - DH | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1390 | CHI05-04-03-DH-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1500 | CHI05-04-04-DH-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 4 - DH | 0
CHI05-05-01-DH-1410 | CHI05-05-02-DH-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | HAC Placing - COLO5 Cell 1 - DH | HAC Placing - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1520 | CHI05-05-03-DH-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | HAC Placing - COLO5 Cell 2 - DH | HAC Placing - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1630 | CHI05-05-04-DH-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | HAC Placing - COLO5 Cell 3 - DH | HAC Placing - COLO5 Cell 4 - DH | 0
CHI05-02-01-DH-1035 | CHI05-02-02-DH-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | HAC Placing - COLO2 Cell 1 - DH | HAC Placing - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1190 | CHI05-02-03-DH-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | HAC Placing - COLO2 Cell 2 - DH | HAC Placing - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1300 | CHI05-02-04-DH-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | HAC Placing - COLO2 Cell 3 - DH | HAC Placing - COLO2 Cell 4 - DH | 0
CHI05-03-01-DH-1190 | CHI05-03-02-DH-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | HAC Placing - COLO3 Cell 1 - DH | HAC Placing - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1300 | CHI05-03-03-DH-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | HAC Placing - COLO3 Cell 2 - DH | HAC Placing - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1410 | CHI05-03-04-DH-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | HAC Placing - COLO3 Cell 3 - DH | HAC Placing - COLO3 Cell 4 - DH | 0
CHI05-04-01-DH-1300 | CHI05-04-02-DH-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | HAC Placing - COLO4 Cell 1 - DH | HAC Placing - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1410 | CHI05-04-03-DH-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | HAC Placing - COLO4 Cell 2 - DH | HAC Placing - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1520 | CHI05-04-04-DH-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | HAC Placing - COLO4 Cell 3 - DH | HAC Placing - COLO4 Cell 4 - DH | 0
CHI05-05-01-MG-1360 | CHI05-05-02-MG-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO5 Cell 1 - MG | Deliver AHU into Mech. Gallery - COLO5 Cell 2 - MG | 0
CHI05-05-02-MG-1470 | CHI05-05-03-MG-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO5 Cell 2 - MG | Deliver AHU into Mech. Gallery - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1580 | CHI05-05-04-MG-1690 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO5 Cell 3 - MG | Deliver AHU into Mech. Gallery - COLO5 Cell 4 - MG | 0
CHI05-02-01-MG-1030 | CHI05-02-02-MG-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO2 Cell 1 - MG | Deliver AHU into Mech. Gallery - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1140 | CHI05-02-03-MG-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO2 Cell 2 - MG | Deliver AHU into Mech. Gallery - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1250 | CHI05-02-04-MG-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO2 Cell 3 - MG | Deliver AHU into Mech. Gallery - COLO2 Cell 4 - MG | 0
CHI05-03-01-MG-1140 | CHI05-03-02-MG-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO3 Cell 1 - MG | Deliver AHU into Mech. Gallery - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1250 | CHI05-03-03-MG-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO3 Cell 2 - MG | Deliver AHU into Mech. Gallery - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1360 | CHI05-03-04-MG-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO3 Cell 3 - MG | Deliver AHU into Mech. Gallery - COLO3 Cell 4 - MG | 0
CHI05-04-01-MG-1250 | CHI05-04-02-MG-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO4 Cell 1 - MG | Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1360 | CHI05-04-03-MG-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG | Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1470 | CHI05-04-04-MG-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG | Deliver AHU into Mech. Gallery - COLO4 Cell 4 - MG | 0
CHI05-05-01-MG-1370 | CHI05-05-02-MG-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Install Walls and Primer Paint - COLO5 Cell 1 - MG | Install Walls and Primer Paint - COLO5 Cell 2 - MG | 0
CHI05-05-02-MG-1480 | CHI05-05-03-MG-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Install Walls and Primer Paint - COLO5 Cell 2 - MG | Install Walls and Primer Paint - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1590 | CHI05-05-04-MG-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Install Walls and Primer Paint - COLO5 Cell 3 - MG | Install Walls and Primer Paint - COLO5 Cell 4 - MG | 0
CHI05-02-01-MG-1040 | CHI05-02-02-MG-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Install Walls and Primer Paint - COLO2 Cell 1 - MG | Install Walls and Primer Paint - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1150 | CHI05-02-03-MG-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Install Walls and Primer Paint - COLO2 Cell 2 - MG | Install Walls and Primer Paint - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1260 | CHI05-02-04-MG-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Install Walls and Primer Paint - COLO2 Cell 3 - MG | Install Walls and Primer Paint - COLO2 Cell 4 - MG | 0
CHI05-03-01-MG-1150 | CHI05-03-02-MG-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Install Walls and Primer Paint - COLO3 Cell 1 - MG | Install Walls and Primer Paint - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1260 | CHI05-03-03-MG-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Install Walls and Primer Paint - COLO3 Cell 2 - MG | Install Walls and Primer Paint - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1370 | CHI05-03-04-MG-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Install Walls and Primer Paint - COLO3 Cell 3 - MG | Install Walls and Primer Paint - COLO3 Cell 4 - MG | 0
CHI05-04-01-MG-1260 | CHI05-04-02-MG-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Install Walls and Primer Paint - COLO4 Cell 1 - MG | Install Walls and Primer Paint - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1370 | CHI05-04-03-MG-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Install Walls and Primer Paint - COLO4 Cell 2 - MG | Install Walls and Primer Paint - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1480 | CHI05-04-04-MG-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Install Walls and Primer Paint - COLO4 Cell 3 - MG | Install Walls and Primer Paint - COLO4 Cell 4 - MG | 0
CHI05-05-01-ER-1330 | CHI05-05-02-ER-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO5 Cell 1 - ER | Install Walls and Primer Paint - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1440 | CHI05-05-03-ER-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO5 Cell 2 - ER | Install Walls and Primer Paint - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1550 | CHI05-05-04-ER-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO5 Cell 3 - ER | Install Walls and Primer Paint - COLO5 Cell 4 - ER | 0
CHI05-02-01-ER-1000 | CHI05-02-02-ER-1110 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO2 Cell 1 - ER | Install Walls and Primer Paint - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1110 | CHI05-02-03-ER-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO2 Cell 2 - ER | Install Walls and Primer Paint - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1220 | CHI05-02-04-ER-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO2 Cell 3 - ER | Install Walls and Primer Paint - COLO2 Cell 4 - ER | 0
CHI05-03-01-ER-1110 | CHI05-03-02-ER-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO3 Cell 1 - ER | Install Walls and Primer Paint - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1220 | CHI05-03-03-ER-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO3 Cell 2 - ER | Install Walls and Primer Paint - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1330 | CHI05-03-04-ER-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO3 Cell 3 - ER | Install Walls and Primer Paint - COLO3 Cell 4 - ER | 0
CHI05-04-01-ER-1220 | CHI05-04-02-ER-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO4 Cell 1 - ER | Install Walls and Primer Paint - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1330 | CHI05-04-03-ER-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO4 Cell 2 - ER | Install Walls and Primer Paint - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1440 | CHI05-04-04-ER-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO4 Cell 3 - ER | Install Walls and Primer Paint - COLO4 Cell 4 - ER | 0
CHI05-05-01-MG-1390 | CHI02-05-02-MG-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO5 Cell 1 - MG | Layout Ceiling and install Pencile Rod - COLO5 Cell 2 - MG | 0
CHI02-05-02-MG-1500 | CHI05-05-03-MG-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO5 Cell 2 - MG | Layout Ceiling and install Pencile Rod - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1610 | CHI05-05-04-MG-1720 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO5 Cell 3 - MG | Layout Ceiling and install Pencile Rod - COLO5 Cell 4 - MG | 0
CHI05-02-01-MG-1050 | CHI05-02-02-MG-1170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO2 Cell 1 - MG | Layout Ceiling and install Pencile Rod - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1170 | CHI05-02-03-MG-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO2 Cell 2 - MG | Layout Ceiling and install Pencile Rod - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1280 | CHI05-02-04-MG-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO2 Cell 3 - MG | Layout Ceiling and install Pencile Rod - COLO2 Cell 4 - MG | 0
CHI05-03-01-MG-1170 | CHI05-03-02-MG-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO3 Cell 1 - MG | Layout Ceiling and install Pencile Rod - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1280 | CHI05-03-03-MG-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO3 Cell 2 - MG | Layout Ceiling and install Pencile Rod - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1390 | CHI05-03-04-MG-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO3 Cell 3 - MG | Layout Ceiling and install Pencile Rod - COLO3 Cell 4 - MG | 0
CHI05-04-01-MG-1280 | CHI05-04-02-MG-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO4 Cell 1 - MG | Layout Ceiling and install Pencile Rod - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1390 | CHI05-04-03-MG-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO4 Cell 2 - MG | Layout Ceiling and install Pencile Rod - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1500 | CHI05-04-04-MG-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Layout Ceiling and install Pencile Rod - COLO4 Cell 3 - MG | Layout Ceiling and install Pencile Rod - COLO4 Cell 4 - MG | 0
CHI05-05-01-MG-1380 | CHI02-05-02-MG-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Placing the AHU - COLO5 Cell 1 - MG | Placing the AHU - COLO5 Cell 2 - MG | 0
CHI02-05-02-MG-1490 | CHI05-05-03-MG-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Placing the AHU - COLO5 Cell 2 - MG | Placing the AHU - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1600 | CHI05-05-04-MG-1710 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Placing the AHU - COLO5 Cell 3 - MG | Placing the AHU - COLO5 Cell 4 - MG | 0
CHI05-02-01-MG-1060 | CHI05-02-02-MG-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Placing the AHU - COLO2 Cell 1 - MG | Placing the AHU - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1160 | CHI05-02-03-MG-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Placing the AHU - COLO2 Cell 2 - MG | Placing the AHU - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1270 | CHI05-02-04-MG-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Placing the AHU - COLO2 Cell 3 - MG | Placing the AHU - COLO2 Cell 4 - MG | 0
CHI05-03-01-MG-1160 | CHI05-03-02-MG-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Placing the AHU - COLO3 Cell 1 - MG | Placing the AHU - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1270 | CHI05-03-03-MG-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Placing the AHU - COLO3 Cell 2 - MG | Placing the AHU - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1380 | CHI05-03-04-MG-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Placing the AHU - COLO3 Cell 3 - MG | Placing the AHU - COLO3 Cell 4 - MG | 0
CHI05-04-01-MG-1270 | CHI05-04-02-MG-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Placing the AHU - COLO4 Cell 1 - MG | Placing the AHU - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1380 | CHI05-04-03-MG-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Placing the AHU - COLO4 Cell 2 - MG | Placing the AHU - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1490 | CHI05-04-04-MG-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Placing the AHU - COLO4 Cell 3 - MG | Placing the AHU - COLO4 Cell 4 - MG | 0
CHI05-05-01-MG-1400 | CHI02-05-02-MG-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO5 Cell 1 - MG | Piping and Electrical Termination to AHUs - COLO5 Cell 2 - MG | 0
CHI02-05-02-MG-1510 | CHI05-05-03-MG-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO5 Cell 2 - MG | Piping and Electrical Termination to AHUs - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1620 | CHI05-05-04-MG-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO5 Cell 3 - MG | Piping and Electrical Termination to AHUs - COLO5 Cell 4 - MG | 0
CHI05-02-01-MG-1070 | CHI05-02-02-MG-1180 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO2 Cell 1 - MG | Piping and Electrical Termination to AHUs - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1180 | CHI05-02-03-MG-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO2 Cell 2 - MG | Piping and Electrical Termination to AHUs - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1290 | CHI05-02-04-MG-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO2 Cell 3 - MG | Piping and Electrical Termination to AHUs - COLO2 Cell 4 - MG | 0
CHI05-03-01-MG-1180 | CHI05-03-02-MG-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO3 Cell 1 - MG | Piping and Electrical Termination to AHUs - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1290 | CHI05-03-03-MG-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO3 Cell 2 - MG | Piping and Electrical Termination to AHUs - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1400 | CHI05-03-04-MG-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO3 Cell 3 - MG | Piping and Electrical Termination to AHUs - COLO3 Cell 4 - MG | 0
CHI05-04-01-MG-1290 | CHI05-04-02-MG-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO4 Cell 1 - MG | Piping and Electrical Termination to AHUs - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1400 | CHI05-04-03-MG-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO4 Cell 2 - MG | Piping and Electrical Termination to AHUs - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1510 | CHI05-04-04-MG-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Piping and Electrical Termination to AHUs - COLO4 Cell 3 - MG | Piping and Electrical Termination to AHUs - COLO4 Cell 4 - MG | 0
CHI05-05-01-MG-1410 | CHI05-05-02-MG-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Pipe Testing - COLO5 Cell 1 - MG | Pipe Testing - COLO5 Cell 2 - MG | 0
CHI05-05-02-MG-1520 | CHI05-05-03-MG-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Pipe Testing - COLO5 Cell 2 - MG | Pipe Testing - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1630 | CHI05-05-04-MG-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Pipe Testing - COLO5 Cell 3 - MG | Pipe Testing - COLO5 Cell 4 - MG | 0
CHI05-02-01-MG-1080 | CHI05-02-02-MG-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Pipe Testing - COLO2 Cell 1 - MG | Pipe Testing - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1190 | CHI05-02-03-MG-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Pipe Testing - COLO2 Cell 2 - MG | Pipe Testing - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1300 | CHI05-02-04-MG-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Pipe Testing - COLO2 Cell 3 - MG | Pipe Testing - COLO2 Cell 4 - MG | 0
CHI05-03-01-MG-1190 | CHI05-03-02-MG-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Pipe Testing - COLO3 Cell 1 - MG | Pipe Testing - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1300 | CHI05-03-03-MG-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Pipe Testing - COLO3 Cell 2 - MG | Pipe Testing - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1410 | CHI05-03-04-MG-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Pipe Testing - COLO3 Cell 3 - MG | Pipe Testing - COLO3 Cell 4 - MG | 0
CHI05-04-01-MG-1300 | CHI05-04-02-MG-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Pipe Testing - COLO4 Cell 1 - MG | Pipe Testing - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1410 | CHI05-04-03-MG-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Pipe Testing - COLO4 Cell 2 - MG | Pipe Testing - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1520 | CHI05-04-04-MG-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Pipe Testing - COLO4 Cell 3 - MG | Pipe Testing - COLO4 Cell 4 - MG | 0
CHI05-05-01-MG-1420 | CHI05-05-02-MG-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Install ceiling and Light Fittings - COLO5 Cell 1 - MG | Install ceiling and Light Fittings - COLO5 Cell 2 - MG | 0
CHI05-05-02-MG-1530 | CHI05-05-03-MG-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Install ceiling and Light Fittings - COLO5 Cell 2 - MG | Install ceiling and Light Fittings - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1640 | CHI05-05-04-MG-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Install ceiling and Light Fittings - COLO5 Cell 3 - MG | Install ceiling and Light Fittings - COLO5 Cell 4 - MG | 0
CHI05-02-01-MG-1090 | CHI05-02-02-MG-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Install ceiling and Light Fittings - COLO2 Cell 1 - MG | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1200 | CHI05-02-03-MG-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | Install ceiling and Light Fittings - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1310 | CHI05-02-04-MG-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Install ceiling and Light Fittings - COLO2 Cell 3 - MG | Install ceiling and Light Fittings - COLO2 Cell 4 - MG | 0
CHI05-03-01-MG-1200 | CHI05-03-02-MG-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Install ceiling and Light Fittings - COLO3 Cell 1 - MG | Install ceiling and Light Fittings - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1310 | CHI05-03-03-MG-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Install ceiling and Light Fittings - COLO3 Cell 2 - MG | Install ceiling and Light Fittings - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1420 | CHI05-03-04-MG-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Install ceiling and Light Fittings - COLO3 Cell 3 - MG | Install ceiling and Light Fittings - COLO3 Cell 4 - MG | 0
CHI05-04-01-MG-1310 | CHI05-04-02-MG-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Install ceiling and Light Fittings - COLO4 Cell 1 - MG | Install ceiling and Light Fittings - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1420 | CHI05-04-03-MG-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Install ceiling and Light Fittings - COLO4 Cell 2 - MG | Install ceiling and Light Fittings - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1530 | CHI05-04-04-MG-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Install ceiling and Light Fittings - COLO4 Cell 3 - MG | Install ceiling and Light Fittings - COLO4 Cell 4 - MG | 0
CHI05-05-01-MG-1430 | CHI05-05-02-MG-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Trim out MEP - COLO5 Cell 1 - MG | Trim out MEP - COLO5 Cell 2 - MG | 0
CHI05-05-02-MG-1540 | CHI05-05-03-MG-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Trim out MEP - COLO5 Cell 2 - MG | Trim out MEP - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1650 | CHI05-05-04-MG-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Trim out MEP - COLO5 Cell 3 - MG | Trim out MEP - COLO5 Cell 4 - MG | 0
CHI05-02-01-MG-1100 | CHI05-02-02-MG-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Trim out MEP - COLO2 Cell 1 - MG | Trim out MEP - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1210 | CHI05-02-03-MG-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Trim out MEP - COLO2 Cell 2 - MG | Trim out MEP - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1320 | CHI05-02-04-MG-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Trim out MEP - COLO2 Cell 3 - MG | Trim out MEP - COLO2 Cell 4 - MG | 0
CHI05-03-01-MG-1210 | CHI05-03-02-MG-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Trim out MEP - COLO3 Cell 1 - MG | Trim out MEP - COLO3 Cell 2 - MG | 0
CHI05-03-02-MG-1320 | CHI05-03-03-MG-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Trim out MEP - COLO3 Cell 2 - MG | Trim out MEP - COLO3 Cell 3 - MG | 0
CHI05-03-03-MG-1430 | CHI05-03-04-MG-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Trim out MEP - COLO3 Cell 3 - MG | Trim out MEP - COLO3 Cell 4 - MG | 0
CHI05-04-01-MG-1320 | CHI05-04-02-MG-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Trim out MEP - COLO4 Cell 1 - MG | Trim out MEP - COLO4 Cell 2 - MG | 0
CHI05-04-02-MG-1430 | CHI05-04-03-MG-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Trim out MEP - COLO4 Cell 2 - MG | Trim out MEP - COLO4 Cell 3 - MG | 0
CHI05-04-03-MG-1540 | CHI05-04-04-MG-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Trim out MEP - COLO4 Cell 3 - MG | Trim out MEP - COLO4 Cell 4 - MG | 0
CHI05-05-01-ER-1350 | CHI02-05-02-ER-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Install Upper Screens - COLO5 Cell 1 - ER | Install Upper Screens - COLO5 Cell 2 - ER | 0
CHI02-05-02-ER-1460 | CHI05-05-03-ER-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Install Upper Screens - COLO5 Cell 2 - ER | Install Upper Screens - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1570 | CHI05-05-04-ER-1680 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Install Upper Screens - COLO5 Cell 3 - ER | Install Upper Screens - COLO5 Cell 4 - ER | 0
CHI05-02-01-ER-1010 | CHI05-02-02-ER-1130 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Install Upper Screens - COLO2 Cell 1 - ER | Install Upper Screens - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1130 | CHI05-02-03-ER-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Install Upper Screens - COLO2 Cell 2 - ER | Install Upper Screens - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1240 | CHI05-02-04-ER-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Install Upper Screens - COLO2 Cell 3 - ER | Install Upper Screens - COLO2 Cell 4 - ER | 0
CHI05-03-01-ER-1130 | CHI05-03-02-ER-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Install Upper Screens - COLO3 Cell 1 - ER | Install Upper Screens - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1240 | CHI05-03-03-ER-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Install Upper Screens - COLO3 Cell 2 - ER | Install Upper Screens - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1350 | CHI05-03-04-ER-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Install Upper Screens - COLO3 Cell 3 - ER | Install Upper Screens - COLO3 Cell 4 - ER | 0
CHI05-04-01-ER-1240 | CHI05-04-02-ER-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Install Upper Screens - COLO4 Cell 1 - ER | Install Upper Screens - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1350 | CHI05-04-03-ER-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Install Upper Screens - COLO4 Cell 2 - ER | Install Upper Screens - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1460 | CHI05-04-04-ER-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Install Upper Screens - COLO4 Cell 3 - ER | Install Upper Screens - COLO4 Cell 4 - ER | 0
CHI05-05-01-ER-1340 | CHI05-05-02-ER-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 1 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1450 | CHI05-05-03-ER-1560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 2 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1560 | CHI05-05-04-ER-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 3 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 4 - ER | 0
CHI05-02-01-ER-1020 | CHI05-02-02-ER-1120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 1 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1120 | CHI05-02-03-ER-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 2 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1230 | CHI05-02-04-ER-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 3 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 4 - ER | 0
CHI05-03-01-ER-1120 | CHI05-03-02-ER-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 1 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1230 | CHI05-03-03-ER-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 2 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1340 | CHI05-03-04-ER-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 3 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 4 - ER | 0
CHI05-04-01-ER-1230 | CHI05-04-02-ER-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 1 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1340 | CHI05-04-03-ER-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 2 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1450 | CHI05-04-04-ER-1560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 3 - ER | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 4 - ER | 0
CHI05-05-01-ER-1360 | CHI05-05-02-ER-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Install Ceiling - COLO5 Cell 1 - ER | Install Ceiling - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1470 | CHI05-05-03-ER-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Install Ceiling - COLO5 Cell 2 - ER | Install Ceiling - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1580 | CHI05-05-04-ER-1690 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Install Ceiling - COLO5 Cell 3 - ER | Install Ceiling - COLO5 Cell 4 - ER | 0
CHI05-02-01-ER-1030 | CHI05-02-02-ER-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Install Ceiling - COLO2 Cell 1 - ER | Install Ceiling - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1140 | CHI05-02-03-ER-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Install Ceiling - COLO2 Cell 2 - ER | Install Ceiling - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1250 | CHI05-02-04-ER-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Install Ceiling - COLO2 Cell 3 - ER | Install Ceiling - COLO2 Cell 4 - ER | 0
CHI05-03-01-ER-1140 | CHI05-03-02-ER-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Install Ceiling - COLO3 Cell 1 - ER | Install Ceiling - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1250 | CHI05-03-03-ER-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Install Ceiling - COLO3 Cell 2 - ER | Install Ceiling - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1360 | CHI05-03-04-ER-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Install Ceiling - COLO3 Cell 3 - ER | Install Ceiling - COLO3 Cell 4 - ER | 0
CHI05-04-01-ER-1250 | CHI05-04-02-ER-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Install Ceiling - COLO4 Cell 1 - ER | Install Ceiling - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1360 | CHI05-04-03-ER-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Install Ceiling - COLO4 Cell 2 - ER | Install Ceiling - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1470 | CHI05-04-04-ER-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Install Ceiling - COLO4 Cell 3 - ER | Install Ceiling - COLO4 Cell 4 - ER | 0
CHI05-05-01-ER-1370 | CHI05-05-02-ER-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 1 - ER | Below Ceiling MEP Rough In - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1480 | CHI05-05-03-ER-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 2 - ER | Below Ceiling MEP Rough In - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1590 | CHI05-05-04-ER-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 3 - ER | Below Ceiling MEP Rough In - COLO5 Cell 4 - ER | 0
CHI05-02-01-ER-1040 | CHI05-02-02-ER-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER | Below Ceiling MEP Rough In - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1150 | CHI05-02-03-ER-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 2 - ER | Below Ceiling MEP Rough In - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1260 | CHI05-02-04-ER-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 3 - ER | Below Ceiling MEP Rough In - COLO2 Cell 4 - ER | 0
CHI05-03-01-ER-1150 | CHI05-03-02-ER-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 1 - ER | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1260 | CHI05-03-03-ER-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1370 | CHI05-03-04-ER-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | 0
CHI05-04-01-ER-1260 | CHI05-04-02-ER-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 1 - ER | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1370 | CHI05-04-03-ER-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1480 | CHI05-04-04-ER-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | 0
CHI05-05-02-ER-1490 | CHI05-05-03-ER-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Installation of ADP & ATS - COLO5 Cell 2 - ER | Installation of ADP & ATS - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1600 | CHI05-05-04-ER-1710 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Installation of ADP & ATS - COLO5 Cell 3 - ER | Installation of ADP & ATS - COLO5 Cell 4 - ER | 0
CHI05-02-01-ER-1050 | CHI05-02-02-ER-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Installation of ADP & ATS - COLO2 Cell 1 - ER | Installation of ADP & ATS - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1160 | CHI05-02-03-ER-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Installation of ADP & ATS - COLO2 Cell 2 - ER | Installation of ADP & ATS - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1270 | CHI05-02-04-ER-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Installation of ADP & ATS - COLO2 Cell 3 - ER | Installation of ADP & ATS - COLO2 Cell 4 - ER | 0
CHI05-03-01-ER-1160 | CHI05-03-02-ER-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Installation of ADP & ATS - COLO3 Cell 1 - ER | Installation of ADP & ATS - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1270 | CHI05-03-03-ER-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Installation of ADP & ATS - COLO3 Cell 2 - ER | Installation of ADP & ATS - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1380 | CHI05-03-04-ER-1490 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Installation of ADP & ATS - COLO3 Cell 3 - ER | Installation of ADP & ATS - COLO3 Cell 4 - ER | 2
CHI05-04-01-ER-1270 | CHI05-04-02-ER-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Installation of ADP & ATS - COLO4 Cell 1 - ER | Installation of ADP & ATS - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1380 | CHI05-04-03-ER-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Installation of ADP & ATS - COLO4 Cell 2 - ER | Installation of ADP & ATS - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1490 | CHI05-04-04-ER-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Installation of ADP & ATS - COLO4 Cell 3 - ER | Installation of ADP & ATS - COLO4 Cell 4 - ER | 0
CHI05-05-01-ER-1400 | CHI05-05-02-ER-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO5 Cell 1 - ER | Connet to Cable tray and conduit equipment - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1510 | CHI05-05-03-ER-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO5 Cell 2 - ER | Connet to Cable tray and conduit equipment - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1620 | CHI05-05-04-ER-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO5 Cell 3 - ER | Connet to Cable tray and conduit equipment - COLO5 Cell 4 - ER | 0
CHI05-02-01-ER-1060 | CHI05-02-02-ER-1180 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO2 Cell 1 - ER | Connet to Cable tray and conduit equipment - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1180 | CHI05-02-03-ER-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO2 Cell 2 - ER | Connet to Cable tray and conduit equipment - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1290 | CHI05-02-04-ER-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO2 Cell 3 - ER | Connet to Cable tray and conduit equipment - COLO2 Cell 4 - ER | 0
CHI05-03-01-ER-1180 | CHI05-03-02-ER-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO3 Cell 1 - ER | Connet to Cable tray and conduit equipment - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1290 | CHI05-03-03-ER-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO3 Cell 2 - ER | Connet to Cable tray and conduit equipment - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1400 | CHI05-03-04-ER-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO3 Cell 3 - ER | Connet to Cable tray and conduit equipment - COLO3 Cell 4 - ER | 0
CHI05-04-01-ER-1290 | CHI05-04-02-ER-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO4 Cell 1 - ER | Connet to Cable tray and conduit equipment - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1400 | CHI05-04-03-ER-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO4 Cell 2 - ER | Connet to Cable tray and conduit equipment - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1510 | CHI05-04-04-ER-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Connet to Cable tray and conduit equipment - COLO4 Cell 3 - ER | Connet to Cable tray and conduit equipment - COLO4 Cell 4 - ER | 0
CHI05-CFCI-1210 | CHI05-CON-1030 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,3 Medium Voltage Cabling | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | Medium Voltage Cabling - Lead Time | Installation and Termiation of MV Cable | 0
CHI05-CON-1020 | CHI05-02-ROJ-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | (3) UTS - Install and Terminate (1 wk/ea) | Complete Last ROJ Arrival for Colo 2 | 0
CHI05-02-01-ER-1070 | CHI05-02-02-ER-1170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Installation of UPS Equipment - COLO2 Cell 1 - ER | Installation of UPS Equipment - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1170 | CHI05-02-03-ER-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Installation of UPS Equipment - COLO2 Cell 2 - ER | Installation of UPS Equipment - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1280 | CHI05-02-04-ER-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Installation of UPS Equipment - COLO2 Cell 3 - ER | Installation of UPS Equipment - COLO2 Cell 4 - ER | 0
CHI05-03-02-ER-1280 | CHI05-03-03-ER-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Installation of UPS Equipment - COLO3 Cell 2 - ER | Installation of UPS Equipment - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1390 | CHI05-03-04-ER-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Installation of UPS Equipment - COLO3 Cell 3 - ER | Installation of UPS Equipment - COLO3 Cell 4 - ER | 0
CHI05-04-01-ER-1280 | CHI05-04-02-ER-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Installation of UPS Equipment - COLO4 Cell 1 - ER | Installation of UPS Equipment - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1390 | CHI05-04-03-ER-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Installation of UPS Equipment - COLO4 Cell 2 - ER | Installation of UPS Equipment - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1500 | CHI05-04-04-ER-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Installation of UPS Equipment - COLO4 Cell 3 - ER | Installation of UPS Equipment - COLO4 Cell 4 - ER | 0
CHI05-05-01-ER-1390 | CHI05-05-02-ER-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Installation of UPS Equipment - COLO5 Cell 1 - ER | Installation of UPS Equipment - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1500 | CHI05-05-03-ER-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Installation of UPS Equipment - COLO5 Cell 2 - ER | Installation of UPS Equipment - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1610 | CHI05-05-04-ER-1720 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Installation of UPS Equipment - COLO5 Cell 3 - ER | Installation of UPS Equipment - COLO5 Cell 4 - ER | 0
CHI05-05-01-ER-1410 | CHI05-05-02-ER-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER | Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1520 | CHI05-05-03-ER-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER | Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1630 | CHI05-05-04-ER-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER | Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER | 0
CHI05-02-01-ER-1080 | CHI05-02-02-ER-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1190 | CHI05-02-03-ER-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1300 | CHI05-02-04-ER-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER | Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER | 0
CHI05-03-01-ER-1190 | CHI05-03-02-ER-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER | Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1300 | CHI05-03-03-ER-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER | Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1410 | CHI05-03-04-ER-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER | Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER | 0
CHI05-04-01-ER-1300 | CHI05-04-02-ER-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER | Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1410 | CHI05-04-03-ER-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER | Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1520 | CHI05-04-04-ER-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER | Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER | 0
CHI05-05-01-ER-1430 | CHI05-05-01-DH-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | Finishes and Signage - COLO5 Cell 1 - ER | Finishes and Signage - COLO5 Cell 1 - DH | 0
CHI05-05-01-DH-1420 | CHI05-05-02-ER-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Finishes and Signage - COLO5 Cell 1 - DH | Finishes and Signage - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1540 | CHI05-05-02-DH-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Finishes and Signage - COLO5 Cell 2 - ER | Finishes and Signage - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1530 | CHI05-05-03-ER-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Finishes and Signage - COLO5 Cell 2 - DH | Finishes and Signage - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1650 | CHI05-05-03-DH-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Finishes and Signage - COLO5 Cell 3 - ER | Finishes and Signage - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1640 | CHI05-05-04-ER-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Finishes and Signage - COLO5 Cell 3 - DH | Finishes and Signage - COLO5 Cell 4 - ER | 0
CHI05-05-04-ER-1760 | CHI05-05-04-DH-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Finishes and Signage - COLO5 Cell 4 - ER | Finishes and Signage - COLO5 Cell 4 - DH | 0
CHI05-05-01-ER-1430 | CHI05-05-02-ER-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Finishes and Signage - COLO5 Cell 1 - ER | Finishes and Signage - COLO5 Cell 2 - ER | 0
CHI05-05-02-ER-1540 | CHI05-05-03-ER-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Finishes and Signage - COLO5 Cell 2 - ER | Finishes and Signage - COLO5 Cell 3 - ER | 0
CHI05-05-03-ER-1650 | CHI05-05-04-ER-1760 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Finishes and Signage - COLO5 Cell 3 - ER | Finishes and Signage - COLO5 Cell 4 - ER | 0
CHI05-05-01-DH-1420 | CHI05-05-02-DH-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Finishes and Signage - COLO5 Cell 1 - DH | Finishes and Signage - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1530 | CHI05-05-03-DH-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Finishes and Signage - COLO5 Cell 2 - DH | Finishes and Signage - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1640 | CHI05-05-04-DH-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Finishes and Signage - COLO5 Cell 3 - DH | Finishes and Signage - COLO5 Cell 4 - DH | 0
CHI05-02-01-ER-1100 | CHI05-02-02-ER-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Finishes and Signage - COLO2 Cell 1 - ER | Finishes and Signage - COLO2 Cell 2 - ER | 0
CHI05-02-02-ER-1210 | CHI05-02-03-ER-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Finishes and Signage - COLO2 Cell 2 - ER | Finishes and Signage - COLO2 Cell 3 - ER | 0
CHI05-02-03-ER-1320 | CHI05-02-04-ER-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Finishes and Signage - COLO2 Cell 3 - ER | Finishes and Signage - COLO2 Cell 4 - ER | 0
CHI05-02-01-DH-1090 | CHI05-02-02-DH-1200 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Finishes and Signage - COLO2 Cell 1 - DH | Finishes and Signage - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1200 | CHI05-02-03-DH-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Finishes and Signage - COLO2 Cell 2 - DH | Finishes and Signage - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1310 | CHI05-02-04-DH-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Finishes and Signage - COLO2 Cell 3 - DH | Finishes and Signage - COLO2 Cell 4 - DH | 0
CHI05-03-01-ER-1210 | CHI05-03-02-ER-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Finishes and Signage - COLO3 Cell 1 - ER | Finishes and Signage - COLO3 Cell 2 - ER | 0
CHI05-03-02-ER-1320 | CHI05-03-03-ER-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Finishes and Signage - COLO3 Cell 2 - ER | Finishes and Signage - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1430 | CHI05-03-04-ER-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Finishes and Signage - COLO3 Cell 3 - ER | Finishes and Signage - COLO3 Cell 4 - ER | 0
CHI05-03-01-DH-1200 | CHI05-03-02-DH-1310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Finishes and Signage - COLO3 Cell 1 - DH | Finishes and Signage - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1310 | CHI05-03-03-DH-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Finishes and Signage - COLO3 Cell 2 - DH | Finishes and Signage - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1420 | CHI05-03-04-DH-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Finishes and Signage - COLO3 Cell 3 - DH | Finishes and Signage - COLO3 Cell 4 - DH | 0
CHI05-04-01-ER-1320 | CHI05-04-02-ER-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Finishes and Signage - COLO4 Cell 1 - ER | Finishes and Signage - COLO4 Cell 2 - ER | 0
CHI05-04-02-ER-1430 | CHI05-04-03-ER-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Finishes and Signage - COLO4 Cell 2 - ER | Finishes and Signage - COLO4 Cell 3 - ER | 0
CHI05-04-03-ER-1540 | CHI05-04-04-ER-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Finishes and Signage - COLO4 Cell 3 - ER | Finishes and Signage - COLO4 Cell 4 - ER | 0
CHI05-04-01-DH-1310 | CHI05-04-02-DH-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Finishes and Signage - COLO4 Cell 1 - DH | Finishes and Signage - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1420 | CHI05-04-03-DH-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Finishes and Signage - COLO4 Cell 2 - DH | Finishes and Signage - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1530 | CHI05-04-04-DH-1640 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Finishes and Signage - COLO4 Cell 3 - DH | Finishes and Signage - COLO4 Cell 4 - DH | 0
CHI05-05-01-DH-1330 | CHI05-05-02-DH-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 1 - DH | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1440 | CHI05-05-03-DH-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 2 - DH | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1550 | CHI05-05-04-DH-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 3 - DH | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 4 - DH | 0
CHI05-02-01-DH-1000 | CHI05-02-02-DH-1110 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 1 - DH | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1110 | CHI05-02-03-DH-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 2 - DH | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1220 | CHI05-02-04-DH-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 3 - DH | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 4 - DH | 0
CHI05-03-01-DH-1110 | CHI05-03-02-DH-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 1 - DH | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1220 | CHI05-03-03-DH-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 2 - DH | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1330 | CHI05-03-04-DH-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 3 - DH | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 4 - DH | 0
CHI05-04-01-DH-1220 | CHI05-04-02-DH-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 1 - DH | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1330 | CHI05-04-03-DH-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1440 | CHI05-04-04-DH-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 4 - DH | 0
CHI05-05-01-DH-1360 | CHI05-05-02-DH-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Security Screen Installation - COLO5 Cell 1 - DH | Security Screen Installation - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1470 | CHI05-05-03-DH-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Security Screen Installation - COLO5 Cell 2 - DH | Security Screen Installation - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1580 | CHI05-05-04-DH-1690 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Security Screen Installation - COLO5 Cell 3 - DH | Security Screen Installation - COLO5 Cell 4 - DH | 0
CHI05-02-01-DH-1010 | CHI05-02-02-DH-1140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Security Screen Installation - COLO2 Cell 1 - DH | Security Screen Installation - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1140 | CHI05-02-03-DH-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Security Screen Installation - COLO2 Cell 2 - DH | Security Screen Installation - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1250 | CHI05-02-04-DH-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Security Screen Installation - COLO2 Cell 3 - DH | Security Screen Installation - COLO2 Cell 4 - DH | 0
CHI05-03-01-DH-1140 | CHI05-03-02-DH-1250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Security Screen Installation - COLO3 Cell 1 - DH | Security Screen Installation - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1250 | CHI05-03-03-DH-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Security Screen Installation - COLO3 Cell 2 - DH | Security Screen Installation - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1360 | CHI05-03-04-DH-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Security Screen Installation - COLO3 Cell 3 - DH | Security Screen Installation - COLO3 Cell 4 - DH | 0
CHI05-04-01-DH-1250 | CHI05-04-02-DH-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Security Screen Installation - COLO4 Cell 1 - DH | Security Screen Installation - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1360 | CHI05-04-03-DH-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Security Screen Installation - COLO4 Cell 2 - DH | Security Screen Installation - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1470 | CHI05-04-04-DH-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Security Screen Installation - COLO4 Cell 3 - DH | Security Screen Installation - COLO4 Cell 4 - DH | 0
CHI05-05-01-DH-1370 | CHI05-05-02-DH-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Ceiling Grid and Tile - COLO5 Cell 1 - DH | Ceiling Grid and Tile - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1480 | CHI05-05-03-DH-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Ceiling Grid and Tile - COLO5 Cell 2 - DH | Ceiling Grid and Tile - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1590 | CHI05-05-04-DH-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Ceiling Grid and Tile - COLO5 Cell 3 - DH | Ceiling Grid and Tile - COLO5 Cell 4 - DH | 0
CHI05-02-01-DH-1020 | CHI05-02-02-DH-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Ceiling Grid and Tile - COLO2 Cell 1 - DH | Ceiling Grid and Tile - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1150 | CHI05-02-03-DH-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Ceiling Grid and Tile - COLO2 Cell 2 - DH | Ceiling Grid and Tile - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1260 | CHI05-02-04-DH-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Ceiling Grid and Tile - COLO2 Cell 3 - DH | Ceiling Grid and Tile - COLO2 Cell 4 - DH | 0
CHI05-03-01-DH-1150 | CHI05-03-02-DH-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Ceiling Grid and Tile - COLO3 Cell 1 - DH | Ceiling Grid and Tile - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1260 | CHI05-03-03-DH-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Ceiling Grid and Tile - COLO3 Cell 2 - DH | Ceiling Grid and Tile - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1370 | CHI05-03-04-DH-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Ceiling Grid and Tile - COLO3 Cell 3 - DH | Ceiling Grid and Tile - COLO3 Cell 4 - DH | 0
CHI05-04-01-DH-1260 | CHI05-04-02-DH-1370 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Ceiling Grid and Tile - COLO4 Cell 1 - DH | Ceiling Grid and Tile - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1370 | CHI05-04-03-DH-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Ceiling Grid and Tile - COLO4 Cell 2 - DH | Ceiling Grid and Tile - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1480 | CHI05-04-04-DH-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Ceiling Grid and Tile - COLO4 Cell 3 - DH | Ceiling Grid and Tile - COLO4 Cell 4 - DH | 0
CHI05-05-01-DH-1320 | CHI05-05-02-DH-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Cable Pulling at PDU & Busway - COLO5 Cell 1 - DH | Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1430 | CHI05-05-03-DH-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH | Termination at PDU & Busway - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1540 | CHI05-05-04-DH-1650 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Termination at PDU & Busway - COLO5 Cell 3 - DH | Termination at PDU & Busway - COLO5 Cell 4 - DH | 0
CHI05-02-01-DH-1050 | CHI05-02-02-DH-1100 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH | Termination at PDU & Busway - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1100 | CHI05-02-03-DH-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Termination at PDU & Busway - COLO2 Cell 2 - DH | Termination at PDU & Busway - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1210 | CHI05-02-04-DH-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Termination at PDU & Busway - COLO2 Cell 3 - DH | Termination at PDU & Busway - COLO2 Cell 4 - DH | 0
CHI05-03-01-DH-1100 | CHI05-03-02-DH-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH | Termination at PDU & Busway - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1210 | CHI05-03-03-DH-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Termination at PDU & Busway - COLO3 Cell 2 - DH | Termination at PDU & Busway - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1320 | CHI05-03-04-DH-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Termination at PDU & Busway - COLO3 Cell 3 - DH | Termination at PDU & Busway - COLO3 Cell 4 - DH | 0
CHI05-04-01-DH-1210 | CHI05-04-02-DH-1320 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH | Termination at PDU & Busway - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1320 | CHI05-04-03-DH-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Termination at PDU & Busway - COLO4 Cell 2 - DH | Termination at PDU & Busway - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1430 | CHI05-04-04-DH-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Termination at PDU & Busway - COLO4 Cell 3 - DH | Termination at PDU & Busway - COLO4 Cell 4 - DH | 0
CHI05-05-01-DH-1400 | CHI05-05-02-DH-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,1 COLO 5 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 1 - DH | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1510 | CHI05-05-03-DH-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 3 - DH | 0
CHI05-05-03-DH-1620 | CHI05-05-04-DH-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,1 COLO 5 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,2,1 COLO 5 Cell 4 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 3 - DH | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH | 0
CHI05-02-01-DH-1080 | CHI05-02-02-DH-1180 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,1 COLO 2 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 1 - DH | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 2 - DH | 0
CHI05-02-02-DH-1180 | CHI05-02-03-DH-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,1 COLO 2 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 2 - DH | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH | 0
CHI05-02-03-DH-1290 | CHI05-02-04-DH-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,1 COLO 2 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,5,2,1 COLO 2 Cell 4 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH | 0
CHI05-03-01-DH-1180 | CHI05-03-02-DH-1290 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,1 COLO 3 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 2 - DH | 0
CHI05-03-02-DH-1290 | CHI05-03-03-DH-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,1 COLO 3 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 2 - DH | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 3 - DH | 0
CHI05-03-03-DH-1400 | CHI05-03-04-DH-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,1 COLO 3 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,1,2,1 COLO 3 Cell 4 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 3 - DH | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH | 0
CHI05-04-01-DH-1290 | CHI05-04-02-DH-1400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,1 COLO 4 Cell 1 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 2 - DH | 0
CHI05-04-02-DH-1400 | CHI05-04-03-DH-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,1 COLO 4 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 2 - DH | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 3 - DH | 0
CHI05-04-03-DH-1510 | CHI05-04-04-DH-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,1 COLO 4 Cell 3 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,2,2,1 COLO 4 Cell 4 Data Hall | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 3 - DH | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH | 0
CHI05-03-01-ER-1170 | CHI05-03-01-L1-1260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Installation of UPS Equipment - COLO3 Cell 1 - ER | Interior - L1 UPS - COLO3 Cell 1 | 0
CHI05-05-01-MG-1370 | CHI05-05-01-MG-1375 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Install Walls and Primer Paint - COLO5 Cell 1 - MG | Post Wall Overhead MEP - COLO5 Cell 1 - MG | 0
CHI05-05-01-MG-1375 | CHI05-05-01-MG-1380 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Post Wall Overhead MEP - COLO5 Cell 1 - MG | Placing the AHU - COLO5 Cell 1 - MG | 5
CHI05-05-02-MG-1480 | CHI05-05-02-MG-1485 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Install Walls and Primer Paint - COLO5 Cell 2 - MG | Post Wall Overhead MEP - COLO5 Cell 2 - MG | 0
CHI05-05-02-MG-1485 | CHI02-05-02-MG-1490 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Post Wall Overhead MEP - COLO5 Cell 2 - MG | Placing the AHU - COLO5 Cell 2 - MG | 5
CHI05-YARD-2010 | CHI05-02-03-L1-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 5 - West | L1 UMS 01 - COLO 5 | 0
CHI05-YARD-2010 | CHI05-02-04-L1-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 5 - West | L1 URS 01 - COLO 5 | 0
CHI05-YARD-2070 | CHI05-02-03-L1-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 5 - East | L1 UMS 01 - COLO 5 | 0
CHI05-YARD-2070 | CHI05-02-04-L1-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 5 - East | L1 URS 01 - COLO 5 | 0
CHI05-YARD-2100 | CHI05-02-01-L1-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 4 - North | L1 UMS 04 - COLO 3 | 0
CHI05-YARD-2170 | CHI05-02-01-L1-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 3 - South | L1 UMS 04 - COLO 3 | 0
CHI05-YARD-2220 | CHI05-02-01-L1-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 4 - South | L1 UMS 04 - COLO 3 | 0
CHI05-YARD-2100 | CHI05-02-02-L1-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 4 - North | L1 UMS 03 - COLO 3 | 0
CHI05-YARD-2170 | CHI05-02-02-L1-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 3 - South | L1 UMS 03 - COLO 3 | 0
CHI05-YARD-2220 | CHI05-02-02-L1-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 4 - South | L1 UMS 03 - COLO 3 | 0
CHI05-02-01-L1-1200 | CHI05-05-01-L2-1680 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L1 UTS / UTSR - Site | L2 UTS / UTSR - Site | 0
CHI05-05-03-MG-1590 | CHI05-05-03-MG-1595 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Install Walls and Primer Paint - COLO5 Cell 3 - MG | Post Wall Overhead MEP - COLO5 Cell 3 - MG | 0
CHI05-05-03-MG-1595 | CHI05-05-03-MG-1600 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Post Wall Overhead MEP - COLO5 Cell 3 - MG | Placing the AHU - COLO5 Cell 3 - MG | 5
CHI05-05-04-MG-1700 | CHI05-05-04-MG-1705 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Install Walls and Primer Paint - COLO5 Cell 4 - MG | Post Wall Overhead MEP - COLO5 Cell 4 - MG | 0
CHI05-05-04-MG-1705 | CHI05-05-04-MG-1710 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Post Wall Overhead MEP - COLO5 Cell 4 - MG | Placing the AHU - COLO5 Cell 4 - MG | 5
CHI05-02-01-MG-1040 | CHI05-02-01-MG-1045 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Install Walls and Primer Paint - COLO2 Cell 1 - MG | Post Wall Overhead MEP - COLO2 Cell 1 - MG | 0
CHI05-02-01-MG-1045 | CHI05-02-01-MG-1060 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Post Wall Overhead MEP - COLO2 Cell 1 - MG | Placing the AHU - COLO2 Cell 1 - MG | 5
CHI05-02-02-MG-1150 | CHI05-02-02-MG-1155 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Install Walls and Primer Paint - COLO2 Cell 2 - MG | Post Wall Overhead MEP - COLO2 Cell 2 - MG | 0
CHI05-02-02-MG-1155 | CHI05-02-02-MG-1160 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Post Wall Overhead MEP - COLO2 Cell 2 - MG | Placing the AHU - COLO2 Cell 2 - MG | 5
CHI05-02-03-MG-1260 | CHI05-02-03-MG-1265 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Install Walls and Primer Paint - COLO2 Cell 3 - MG | Post Wall Overhead MEP - COLO2 Cell 3 - MG | 0
CHI05-02-03-MG-1265 | CHI05-02-03-MG-1270 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Post Wall Overhead MEP - COLO2 Cell 3 - MG | Placing the AHU - COLO2 Cell 3 - MG | 5
CHI05-02-04-MG-1370 | CHI05-02-04-MG-1375 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Install Walls and Primer Paint - COLO2 Cell 4 - MG | Post Wall Overhead MEP - COLO2 Cell 4 - MG | 0
CHI05-02-04-MG-1375 | CHI05-02-04-MG-1380 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Post Wall Overhead MEP - COLO2 Cell 4 - MG | Placing the AHU - COLO2 Cell 4 - MG | 5
CHI05-03-01-MG-1150 | CHI05-03-01-MG-1155 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Install Walls and Primer Paint - COLO3 Cell 1 - MG | Post Wall Overhead MEP - COLO3 Cell 1 - MG | 0
CHI05-03-02-MG-1260 | CHI05-03-02-MG-1265 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Install Walls and Primer Paint - COLO3 Cell 2 - MG | Post Wall Overhead MEP - COLO3 Cell 2 - MG | 0
CHI05-03-03-MG-1370 | CHI05-03-03-MG-1375 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Install Walls and Primer Paint - COLO3 Cell 3 - MG | Post Wall Overhead MEP - COLO3 Cell 3 - MG | 0
CHI05-03-04-MG-1480 | CHI05-03-04-MG-1485 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Install Walls and Primer Paint - COLO3 Cell 4 - MG | Post Wall Overhead MEP - COLO3 Cell 4 - MG | 0
CHI05-04-01-MG-1260 | CHI05-04-01-MG-1265 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Install Walls and Primer Paint - COLO4 Cell 1 - MG | Post Wall Overhead MEP - COLO4 Cell 1 - MG | 0
CHI05-04-02-MG-1370 | CHI05-04-02-MG-1375 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Install Walls and Primer Paint - COLO4 Cell 2 - MG | Post Wall Overhead MEP - COLO4 Cell 2 - MG | 0
CHI05-04-03-MG-1480 | CHI05-04-03-MG-1485 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Install Walls and Primer Paint - COLO4 Cell 3 - MG | Post Wall Overhead MEP - COLO4 Cell 3 - MG | 0
CHI05-04-04-MG-1590 | CHI05-04-04-MG-1595 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Install Walls and Primer Paint - COLO4 Cell 4 - MG | Post Wall Overhead MEP - COLO4 Cell 4 - MG | 0
CHI05-03-01-MG-1155 | CHI05-03-01-MG-1160 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Post Wall Overhead MEP - COLO3 Cell 1 - MG | Placing the AHU - COLO3 Cell 1 - MG | 5
CHI05-03-02-MG-1265 | CHI05-03-02-MG-1270 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Post Wall Overhead MEP - COLO3 Cell 2 - MG | Placing the AHU - COLO3 Cell 2 - MG | 5
CHI05-03-03-MG-1375 | CHI05-03-03-MG-1380 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Post Wall Overhead MEP - COLO3 Cell 3 - MG | Placing the AHU - COLO3 Cell 3 - MG | 5
CHI05-03-04-MG-1485 | CHI05-03-04-MG-1490 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Post Wall Overhead MEP - COLO3 Cell 4 - MG | Placing the AHU - COLO3 Cell 4 - MG | 5
CHI05-04-01-MG-1265 | CHI05-04-01-MG-1270 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Post Wall Overhead MEP - COLO4 Cell 1 - MG | Placing the AHU - COLO4 Cell 1 - MG | 5
CHI05-04-02-MG-1375 | CHI05-04-02-MG-1380 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Post Wall Overhead MEP - COLO4 Cell 2 - MG | Placing the AHU - COLO4 Cell 2 - MG | 5
CHI05-04-03-MG-1485 | CHI05-04-03-MG-1490 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Post Wall Overhead MEP - COLO4 Cell 3 - MG | Placing the AHU - COLO4 Cell 3 - MG | 5
CHI05-04-04-MG-1595 | CHI05-04-04-MG-1600 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Post Wall Overhead MEP - COLO4 Cell 4 - MG | Placing the AHU - COLO4 Cell 4 - MG | 5
CHI05-YARD-2170 | CHI05-YARD-2220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | Set the MV Gear - Colo 3 - South | Set the MV Gear - Colo 4 - South | 0
CHI05-YARD-2000 | CHI05-YARD-2060 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | Set the Generator - Colo 2 - North | Set the Generator - Colo 3 - North | 0
CHI05-YARD-2100 | CHI05-YARD-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | Set the MV Gear - Colo 4 - North | Set the MV Gear - Colo 5 - West | 0
CHI05-YARD-2210 | CHI05-YARD-2360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | Installation of Mech. Piping and testing - Colo 2 - North | Install screen wall - Colo 2 - North | 0
CHI05-YARD-2290 | CHI05-YARD-2400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | Installation of Mech. Piping and testing - Colo 3 - North | Install screen wall - Colo 3 - North | 0
CHI05-YARD-2330 | CHI05-YARD-2430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | Installation of Mech. Piping and testing - Colo 4 - North | Install screen wall - Colo 4 - North | 0
CHI05-YARD-2390 | CHI05-YARD-2450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | Installation of Mech. Piping and testing - Colo 2 - South | Install screen wall - Colo 2 - South | 0
CHI05-YARD-2200 | CHI05-YARD-2250 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | Installation of Mech. Piping and testing - Colo 5 - West | Install screen wall - Colo 5 - West | 0
CHI05-YARD-2260 | CHI05-YARD-2400 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | Wire pulling and termination for MSB - Colo 3 - North | Install screen wall - Colo 3 - North | 0
CHI05-YARD-2310 | CHI05-YARD-2430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | Wire pulling and termination for MSB - Colo 4 - North | Install screen wall - Colo 4 - North | 0
CHI05-YARD-2350 | CHI05-YARD-2450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | Wire pulling and termination for MSB - Colo 2 - South | Install screen wall - Colo 2 - South | 0
CHI05-YARD-2380 | CHI05-YARD-2460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | Wire pulling and termination for MSB - Colo 3 - South | Install screen wall - Colo 3 - South | 0
CHI05-YARD-2410 | CHI05-YARD-2460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | Installation of Mech. Piping and testing - Colo 3 - South | Install screen wall - Colo 3 - South | 0
CHI05-YARD-2460 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Install screen wall - Colo 3 - South | Site Secured Finish (August 04, 2025) | 0
CHI05-YARD-2450 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Install screen wall - Colo 2 - South | Site Secured Finish (August 04, 2025) | 0
CHI05-YARD-2400 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Install screen wall - Colo 3 - North | Site Secured Finish (August 04, 2025) | 0
CHI05-YARD-2360 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Install screen wall - Colo 2 - North | Site Secured Finish (August 04, 2025) | 0
CHI05-YARD-2320 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Install screen wall - Colo 5 - East | Site Secured Finish (August 04, 2025) | 0
CHI05-YARD-2250 | CHI05-05-FC-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | Install screen wall - Colo 5 - West | Site Secured Finish (August 04, 2025) | 0
CHI05-OFCI-1730 | CHI05-05-01-L3-1820 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,4,5 EPMS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | EPMS - COLO 5 | L3 UPM - COLO5 | 0
CHI05-OFCI-1120 | CHI05-02-01-L3-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,4,1 EPMS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | EPMS - COLO 2 | L3 UPM - COLO2 | 0
CHI05-OFCI-1440 | CHI05-03-01-L3-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,4,2 EPMS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | EPMS - COLO 3 | L3 UPM - COLO3 | 0
CHI05-OFCI-1570 | CHI05-04-01-L3-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,4,3 EPMS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | EPMS - COLO 4 | L3 UPM - COLO4 | 0
CHI05-OFCI-1570 | CHI05-04-02-L3-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,4,3 EPMS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | EPMS - COLO 4 | Interior - L3 UPS - COLO4 Cell 2 | 0
CHI05-05-01-ER-1420 | CHI05-05-01-L3-1820 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO5 Cell 1 - ER | L3 UPM - COLO5 | 0
CHI05-02-01-ER-1090 | CHI05-02-01-L3-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO2 Cell 1 - ER | L3 UPM - COLO2 | 0
CHI05-03-01-ER-1200 | CHI05-03-01-L3-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO3 Cell 1 - ER | L3 UPM - COLO3 | 0
CHI05-04-01-ER-1310 | CHI05-04-01-L3-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO4 Cell 1 - ER | L3 UPM - COLO4 | 0
CHI05-04-02-ER-1420 | CHI05-04-02-L3-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | Door Frame Installation - COLO4 Cell 2 - ER | Interior - L3 UPS - COLO4 Cell 2 | 0
CHI05-YARD-2150 | CHI05-05-01-ER-1410 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 5 - West | Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER | 0
CHI05-YARD-2150 | CHI05-05-02-ER-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 5 - West | Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER | 0
CHI05-YARD-2150 | CHI05-05-03-ER-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 5 - West | Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER | 0
CHI05-YARD-2150 | CHI05-05-04-ER-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 5 - West | Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER | 0
CHI05-YARD-2270 | CHI05-05-01-ER-1410 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 5 - East | Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER | 0
CHI05-YARD-2270 | CHI05-05-02-ER-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 5 - East | Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER | 0
CHI05-YARD-2270 | CHI05-05-03-ER-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 5 - East | Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER | 0
CHI05-YARD-2270 | CHI05-05-04-ER-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 5 - East | Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER | 0
CHI05-YARD-2350 | CHI05-02-01-ER-1080 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 2 - South | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | 0
CHI05-YARD-2350 | CHI05-02-02-ER-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 2 - South | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | 0
CHI05-YARD-2350 | CHI05-02-03-ER-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 2 - South | Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER | 0
CHI05-YARD-2350 | CHI05-02-04-ER-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 2 - South | Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER | 0
CHI05-YARD-2140 | CHI05-02-04-ER-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 2 - North | Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER | 0
CHI05-YARD-2140 | CHI05-02-01-ER-1080 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 2 - North | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | 0
CHI05-YARD-2140 | CHI05-02-02-ER-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 2 - North | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | 0
CHI05-YARD-2140 | CHI05-02-03-ER-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 2 - North | Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER | 0
CHI05-YARD-2380 | CHI05-03-01-ER-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 3 - South | Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER | 0
CHI05-YARD-2380 | CHI05-03-02-ER-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 3 - South | Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER | 0
CHI05-YARD-2380 | CHI05-03-03-ER-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 3 - South | Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER | 0
CHI05-YARD-2380 | CHI05-03-04-ER-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 3 - South | Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER | 0
CHI05-YARD-2260 | CHI05-03-03-ER-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 3 - North | Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER | 0
CHI05-YARD-2260 | CHI05-03-04-ER-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 3 - North | Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER | 0
CHI05-YARD-2260 | CHI05-03-02-ER-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 3 - North | Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER | 0
CHI05-YARD-2260 | CHI05-03-01-ER-1190 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 3 - North | Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER | 0
CHI05-YARD-2420 | CHI05-04-01-ER-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 4 - South | Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER | 0
CHI05-YARD-2420 | CHI05-04-02-ER-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 4 - South | Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER | 0
CHI05-YARD-2420 | CHI05-04-03-ER-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 4 - South | Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER | 0
CHI05-YARD-2420 | CHI05-04-04-ER-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 4 - South | Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER | 0
CHI05-YARD-2310 | CHI05-04-01-ER-1300 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 4 - North | Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER | 0
CHI05-YARD-2310 | CHI05-04-04-ER-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 4 - North | Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER | 0
CHI05-YARD-2310 | CHI05-04-02-ER-1410 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 4 - North | Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER | 0
CHI05-YARD-2310 | CHI05-04-03-ER-1520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Wire pulling and termination for MSB - Colo 4 - North | Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER | 0
CHI05-OFCI-1900 | CHI05-OFCI-1780 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,2 Mufflers - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,15,3 Mufflers - COLO 4 | Mufflers - COLO 3 - Finish ROJ | Mufflers - COLO 4 - Start ROJ | 0
CHI05-CON-1030 | CHI05-05-01-L3-1820 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Installation and Termiation of MV Cable | L3 UPM - COLO5 | 0
CHI05-05-NTP-S | A1000 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,16,1 MSB - COLO 2 | Notice To Proceed | MSB - COLO 2 - ROJ | 0
CHI05-05-NTP-S | A1010 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,16,2 MSB - COLO 3 | Notice To Proceed | MSB - COLO 3 - ROJ | 0
CHI05-05-NTP-S | A1020 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,16,3 MSB - COLO 4 | Notice To Proceed | MSB - COLO 4 - ROJ | 0
CHI05-05-NTP-S | A1040 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,16,5 MSB - COLO 5 | Notice To Proceed | MSB - COLO 5 - ROJ | 0
A1000 | A1010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,1 MSB - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,16,2 MSB - COLO 3 | MSB - COLO 2 - ROJ | MSB - COLO 3 - ROJ | 0
A1010 | A1020 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,2 MSB - COLO 3 | CHI05-PH2-FIT-BL-D5,4,1,16,3 MSB - COLO 4 | MSB - COLO 3 - ROJ | MSB - COLO 4 - ROJ | 0
A1000 | A1040 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,1 MSB - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,16,5 MSB - COLO 5 | MSB - COLO 2 - ROJ | MSB - COLO 5 - ROJ | 0
A1020 | CHI05-04-03-ER-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,3 MSB - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | MSB - COLO 4 - ROJ | Installation of ADP & ATS - COLO4 Cell 3 - ER | 0
A1000 | CHI05-02-02-ER-1160 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,1 MSB - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | MSB - COLO 2 - ROJ | Installation of ADP & ATS - COLO2 Cell 2 - ER | 0
CHI05-05-01-ER-1370 | CHI05-05-01-ER-1385 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 1 - ER | Installation of MSB - COLO5 Cell 1 - ER | 2
CHI05-05-01-ER-1385 | CHI05-05-01-ER-1400 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Installation of MSB - COLO5 Cell 1 - ER | Connet to Cable tray and conduit equipment - COLO5 Cell 1 - ER | 2
CHI05-05-01-ER-1385 | CHI05-05-01-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Installation of MSB - COLO5 Cell 1 - ER | Interior - L1 MSB - COLO5 Cell 1 | 0
CHI05-05-01-ER-1385 | CHI05-05-01-L1-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Installation of MSB - COLO5 Cell 1 - ER | Interior - L1 ADP - COLO5 Cell 1 | 0
CHI05-05-01-ER-1385 | CHI05-05-01-L1-1540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Installation of MSB - COLO5 Cell 1 - ER | Interior - L1 ATSs - COLO5 Cell 1 | 0
CHI05-05-01-ER-1385 | CHI05-05-01-L1-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,4,1 Level 1 Cx - Colo 5 | Installation of MSB - COLO5 Cell 1 - ER | Interior - L1 Busway - COLO5 Cell 1 | 0
A1040 | CHI05-05-01-ER-1385 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,5 MSB - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | MSB - COLO 5 - ROJ | Installation of MSB - COLO5 Cell 1 - ER | 0
CHI05-05-02-ER-1480 | CHI05-05-02-ER-1495 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 2 - ER | Installation of MSB - COLO5 Cell 2 - ER | 2
CHI05-05-02-ER-1495 | CHI05-05-02-ER-1510 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Installation of MSB - COLO5 Cell 2 - ER | Connet to Cable tray and conduit equipment - COLO5 Cell 2 - ER | 2
CHI05-05-02-ER-1495 | CHI05-05-02-L1-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Installation of MSB - COLO5 Cell 2 - ER | Interior - L1 MSB - COLO5 Cell 2 | 0
CHI05-05-02-ER-1495 | CHI05-05-02-L1-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Installation of MSB - COLO5 Cell 2 - ER | Interior - L1 ADP - COLO5 Cell 2 | 0
CHI05-05-02-ER-1495 | CHI05-05-02-L1-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Installation of MSB - COLO5 Cell 2 - ER | Interior - L1 ATSs - COLO5 Cell 2 | 0
CHI05-05-02-ER-1495 | CHI05-05-02-L1-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | Installation of MSB - COLO5 Cell 2 - ER | Interior - L1 Busway - COLO5 Cell 2 | 0
A1040 | CHI05-05-02-ER-1495 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,5 MSB - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | MSB - COLO 5 - ROJ | Installation of MSB - COLO5 Cell 2 - ER | 0
CHI05-05-01-ER-1385 | CHI05-05-02-ER-1495 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Installation of MSB - COLO5 Cell 1 - ER | Installation of MSB - COLO5 Cell 2 - ER | 0
CHI05-05-01-ER-1380 | CHI05-05-02-ER-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Installation of ADP & ATS - COLO5 Cell 1 - ER | Installation of ADP & ATS - COLO5 Cell 2 - ER | 0
CHI05-05-03-ER-1590 | CHI05-05-03-ER-1605 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 3 - ER | Installation of MSB - COLO5 Cell 3 - ER | 2
CHI05-05-03-ER-1605 | CHI05-05-03-ER-1620 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Installation of MSB - COLO5 Cell 3 - ER | Connet to Cable tray and conduit equipment - COLO5 Cell 3 - ER | 2
CHI05-05-03-ER-1605 | CHI05-05-03-L1-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | Installation of MSB - COLO5 Cell 3 - ER | Interior - L1 MSB - COLO5 Cell 3 | 0
A1040 | CHI05-05-03-ER-1605 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,5 MSB - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | MSB - COLO 5 - ROJ | Installation of MSB - COLO5 Cell 3 - ER | 0
CHI05-05-02-ER-1495 | CHI05-05-03-ER-1605 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Installation of MSB - COLO5 Cell 2 - ER | Installation of MSB - COLO5 Cell 3 - ER | 0
CHI05-05-04-ER-1700 | CHI05-05-04-ER-1715 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 4 - ER | Installation of MSB - COLO5 Cell 4 - ER | 2
CHI05-05-04-ER-1715 | CHI05-05-04-ER-1730 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Installation of MSB - COLO5 Cell 4 - ER | Connet to Cable tray and conduit equipment - COLO5 Cell 4 - ER | 2
A1040 | CHI05-05-04-ER-1715 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,5 MSB - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | MSB - COLO 5 - ROJ | Installation of MSB - COLO5 Cell 4 - ER | 0
CHI05-05-03-ER-1605 | CHI05-05-04-ER-1715 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Installation of MSB - COLO5 Cell 3 - ER | Installation of MSB - COLO5 Cell 4 - ER | 0
CHI05-05-04-ER-1710 | CHI05-05-04-L1-1970 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Installation of ADP & ATS - COLO5 Cell 4 - ER | Interior - L1 ADP - COLO5 Cell 4 | 0
CHI05-05-04-ER-1710 | CHI05-05-04-L1-1900 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Installation of ADP & ATS - COLO5 Cell 4 - ER | Interior - L1 ATSs - COLO5 Cell 4 | 0
CHI05-05-04-ER-1710 | CHI05-05-04-L1-1880 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Installation of ADP & ATS - COLO5 Cell 4 - ER | Interior - L1 PDUs - COLO5 Cell 4 | 0
CHI05-05-04-ER-1710 | CHI05-05-04-L1-1910 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Installation of ADP & ATS - COLO5 Cell 4 - ER | Interior - L1 Busway - COLO5 Cell 4 | 0
CHI05-05-04-ER-1715 | CHI05-05-04-L1-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | Installation of MSB - COLO5 Cell 4 - ER | Interior - L1 MSB - COLO5 Cell 4 | 0
CHI05-02-01-ER-1040 | CHI05-02-01-ER-1055 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER | Installation of MSB - COLO2 Cell 1 - ER | 2
CHI05-02-01-ER-1055 | CHI05-02-01-ER-1060 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Installation of MSB - COLO2 Cell 1 - ER | Connet to Cable tray and conduit equipment - COLO2 Cell 1 - ER | 2
CHI05-02-01-ER-1055 | CHI05-02-01-L1-1150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,4,1 Level 1 Cx - Colo 2 | Installation of MSB - COLO2 Cell 1 - ER | Interior - L1 MSB - COLO2 Cell 1 | 0
A1000 | CHI05-02-01-ER-1055 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,1 MSB - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | MSB - COLO 2 - ROJ | Installation of MSB - COLO2 Cell 1 - ER | 0
CHI05-02-02-ER-1150 | CHI05-02-02-ER-1165 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 2 - ER | Installation of MSB - COLO2 Cell 2 - ER | 2
CHI05-02-02-ER-1165 | CHI05-02-02-ER-1180 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Installation of MSB - COLO2 Cell 2 - ER | Connet to Cable tray and conduit equipment - COLO2 Cell 2 - ER | 2
CHI05-02-02-ER-1165 | CHI05-02-02-L1-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | Installation of MSB - COLO2 Cell 2 - ER | Interior - L1 MSB - COLO2 Cell 2 | 0
CHI05-02-01-ER-1050 | CHI05-02-02-ER-1165 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Installation of ADP & ATS - COLO2 Cell 1 - ER | Installation of MSB - COLO2 Cell 2 - ER | 0
A1000 | CHI05-02-02-ER-1165 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,1 MSB - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | MSB - COLO 2 - ROJ | Installation of MSB - COLO2 Cell 2 - ER | 0
CHI05-02-01-ER-1055 | CHI05-02-02-ER-1165 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | Installation of MSB - COLO2 Cell 1 - ER | Installation of MSB - COLO2 Cell 2 - ER | 0
CHI05-02-03-ER-1260 | CHI05-02-03-ER-1275 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 3 - ER | Installation of MSB - COLO2 Cell 3 - ER | 2
CHI05-02-03-ER-1275 | CHI05-02-03-ER-1290 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Installation of MSB - COLO2 Cell 3 - ER | Connet to Cable tray and conduit equipment - COLO2 Cell 3 - ER | 2
CHI05-OFCI-1970 | CHI05-02-03-ER-1275 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,2,1 ATS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | ATS - COLO 2 - Finish ROJ | Installation of MSB - COLO2 Cell 3 - ER | 0
CHI05-OFCI-1990 | CHI05-02-03-ER-1275 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,7,1 LVS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | LVS - COLO 2 - Finish ROJ | Installation of MSB - COLO2 Cell 3 - ER | 0
A1000 | CHI05-02-03-ER-1275 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,1 MSB - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | MSB - COLO 2 - ROJ | Installation of MSB - COLO2 Cell 3 - ER | 0
CHI05-02-02-ER-1165 | CHI05-02-03-ER-1275 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Installation of MSB - COLO2 Cell 2 - ER | Installation of MSB - COLO2 Cell 3 - ER | 0
CHI05-02-04-ER-1370 | CHI05-02-04-ER-1385 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 4 - ER | Installation of MSB - COLO2 Cell 4 - ER | 2
CHI05-02-04-ER-1385 | CHI05-02-04-ER-1400 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Installation of MSB - COLO2 Cell 4 - ER | Connet to Cable tray and conduit equipment - COLO2 Cell 4 - ER | 2
CHI05-02-04-ER-1385 | CHI05-02-04-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | Installation of MSB - COLO2 Cell 4 - ER | Interior - L1 MSB - COLO2 Cell 4 | 0
A1000 | CHI05-02-04-ER-1385 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,1 MSB - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | MSB - COLO 2 - ROJ | Installation of MSB - COLO2 Cell 4 - ER | 0
CHI05-02-03-ER-1275 | CHI05-02-04-ER-1385 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Installation of MSB - COLO2 Cell 3 - ER | Installation of MSB - COLO2 Cell 4 - ER | 0
CHI05-02-03-ER-1270 | CHI05-02-03-L1-1420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Installation of ADP & ATS - COLO2 Cell 3 - ER | Interior - L1 ATSs - COLO2 Cell 3 | 0
CHI05-02-03-ER-1270 | CHI05-02-03-L1-1430 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Installation of ADP & ATS - COLO2 Cell 3 - ER | Interior - L1 Busway - COLO2 Cell 3 | 0
CHI05-02-03-ER-1270 | CHI05-02-03-L1-1490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Installation of ADP & ATS - COLO2 Cell 3 - ER | Interior - L1 ADP - COLO2 Cell 3 | 0
CHI05-02-03-ER-1275 | CHI05-02-03-L1-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | Installation of MSB - COLO2 Cell 3 - ER | Interior - L1 MSB - COLO2 Cell 3 | 0
CHI05-03-01-ER-1150 | CHI05-03-01-ER-1155 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 1 - ER | Installation of MSB - COLO3 Cell 1 - ER | 2
CHI05-03-01-ER-1155 | CHI05-03-01-ER-1180 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Installation of MSB - COLO3 Cell 1 - ER | Connet to Cable tray and conduit equipment - COLO3 Cell 1 - ER | 2
CHI05-03-01-ER-1155 | CHI05-03-01-L1-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,4,1 Level 1 Cx - Colo 3 | Installation of MSB - COLO3 Cell 1 - ER | Interior - L1 MSB - COLO3 Cell 1 | 0
A1010 | CHI05-03-01-ER-1155 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,2 MSB - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | MSB - COLO 3 - ROJ | Installation of MSB - COLO3 Cell 1 - ER | 0
CHI05-03-02-ER-1260 | CHI05-03-02-ER-1265 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | Installation of MSB - COLO3 Cell 2 - ER | 2
CHI05-03-02-ER-1265 | CHI05-03-02-ER-1290 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Installation of MSB - COLO3 Cell 2 - ER | Connet to Cable tray and conduit equipment - COLO3 Cell 2 - ER | 2
CHI05-03-02-ER-1265 | CHI05-03-02-L1-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | Installation of MSB - COLO3 Cell 2 - ER | Interior - L1 MSB - COLO3 Cell 2 | 0
A1010 | CHI05-03-02-ER-1265 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,2 MSB - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | MSB - COLO 3 - ROJ | Installation of MSB - COLO3 Cell 2 - ER | 0
CHI05-03-01-ER-1155 | CHI05-03-02-ER-1265 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Installation of MSB - COLO3 Cell 1 - ER | Installation of MSB - COLO3 Cell 2 - ER | 0
CHI05-03-03-ER-1370 | CHI05-03-03-ER-1385 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | Installation of MSB - COLO3 Cell 3 - ER | 2
CHI05-03-03-ER-1385 | CHI05-03-03-ER-1400 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Installation of MSB - COLO3 Cell 3 - ER | Connet to Cable tray and conduit equipment - COLO3 Cell 3 - ER | 2
A1010 | CHI05-03-03-ER-1385 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,2 MSB - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | MSB - COLO 3 - ROJ | Installation of MSB - COLO3 Cell 3 - ER | 0
CHI05-03-02-ER-1265 | CHI05-03-03-ER-1385 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Installation of MSB - COLO3 Cell 2 - ER | Installation of MSB - COLO3 Cell 3 - ER | 0
CHI05-03-03-ER-1380 | CHI05-03-04-L1-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Installation of ADP & ATS - COLO3 Cell 3 - ER | Interior - L1 ATSs - COLO3 Cell 4 | 0
CHI05-03-03-ER-1380 | CHI05-03-04-L1-1730 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Installation of ADP & ATS - COLO3 Cell 3 - ER | Interior - L1 ADP - COLO3 Cell 4 | 0
CHI05-03-03-ER-1380 | CHI05-03-04-L1-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Installation of ADP & ATS - COLO3 Cell 3 - ER | Interior - L1 Busway - COLO3 Cell 4 | 0
CHI05-03-03-ER-1385 | CHI05-03-03-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | Installation of MSB - COLO3 Cell 3 - ER | Interior - L1 MSB - COLO3 Cell 3 | 0
CHI05-03-04-ER-1480 | CHI05-03-04-ER-1495 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | Installation of MSB - COLO3 Cell 4 - ER | 2
CHI05-03-04-ER-1495 | CHI05-03-04-ER-1510 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Installation of MSB - COLO3 Cell 4 - ER | Connet to Cable tray and conduit equipment - COLO3 Cell 4 - ER | 2
CHI05-03-04-ER-1495 | CHI05-03-04-L1-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | Installation of MSB - COLO3 Cell 4 - ER | Interior - L1 MSB - COLO3 Cell 4 | 0
A1010 | CHI05-03-04-ER-1495 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,2 MSB - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | MSB - COLO 3 - ROJ | Installation of MSB - COLO3 Cell 4 - ER | 0
CHI05-03-03-ER-1385 | CHI05-03-04-ER-1495 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Installation of MSB - COLO3 Cell 3 - ER | Installation of MSB - COLO3 Cell 4 - ER | 2
CHI05-04-01-ER-1260 | CHI05-04-01-ER-1285 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 1 - ER | Installation of MSB - COLO4 Cell 1 - ER | 2
CHI05-04-01-ER-1285 | CHI05-04-01-ER-1290 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Installation of MSB - COLO4 Cell 1 - ER | Connet to Cable tray and conduit equipment - COLO4 Cell 1 - ER | 2
CHI05-04-01-ER-1285 | CHI05-04-01-L1-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,4,1 Level 1 Cx - Colo 4 | Installation of MSB - COLO4 Cell 1 - ER | Interior - L1 MSB - COLO4 Cell 1 | 0
A1020 | CHI05-04-01-ER-1285 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,3 MSB - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | MSB - COLO 4 - ROJ | Installation of MSB - COLO4 Cell 1 - ER | 0
CHI05-04-02-ER-1370 | CHI05-04-02-ER-1385 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | Installation of MSB - COLO4 Cell 2 - ER | 2
CHI05-04-02-ER-1385 | CHI05-04-02-ER-1400 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Installation of MSB - COLO4 Cell 2 - ER | Connet to Cable tray and conduit equipment - COLO4 Cell 2 - ER | 2
CHI05-04-02-ER-1385 | CHI05-04-02-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | Installation of MSB - COLO4 Cell 2 - ER | Interior - L1 MSB - COLO4 Cell 2 | 0
A1020 | CHI05-04-02-ER-1385 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,3 MSB - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | MSB - COLO 4 - ROJ | Installation of MSB - COLO4 Cell 2 - ER | 0
CHI05-04-01-ER-1285 | CHI05-04-02-ER-1385 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Installation of MSB - COLO4 Cell 1 - ER | Installation of MSB - COLO4 Cell 2 - ER | 0
CHI05-04-03-ER-1480 | CHI05-04-03-ER-1495 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | Installation of MSB - COLO4 Cell 3 - ER | 2
CHI05-04-03-ER-1495 | CHI05-04-03-ER-1510 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Installation of MSB - COLO4 Cell 3 - ER | Connet to Cable tray and conduit equipment - COLO4 Cell 3 - ER | 2
CHI05-04-03-ER-1495 | CHI05-04-03-L1-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | Installation of MSB - COLO4 Cell 3 - ER | Interior - L1 MSB - COLO4 Cell 3 | 0
CHI05-04-02-ER-1380 | CHI05-04-03-ER-1495 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Installation of ADP & ATS - COLO4 Cell 2 - ER | Installation of MSB - COLO4 Cell 3 - ER | 0
A1020 | CHI05-04-03-ER-1495 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,3 MSB - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | MSB - COLO 4 - ROJ | Installation of MSB - COLO4 Cell 3 - ER | 0
CHI05-04-02-ER-1385 | CHI05-04-03-ER-1495 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Installation of MSB - COLO4 Cell 2 - ER | Installation of MSB - COLO4 Cell 3 - ER | 0
CHI05-04-04-ER-1590 | CHI05-04-04-ER-1625 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | Installation of MSB - COLO4 Cell 4 - ER | 0
CHI05-04-04-ER-1625 | CHI05-04-04-ER-1620 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Installation of MSB - COLO4 Cell 4 - ER | Connet to Cable tray and conduit equipment - COLO4 Cell 4 - ER | 0
CHI05-04-04-ER-1625 | CHI05-04-04-L1-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | Installation of MSB - COLO4 Cell 4 - ER | Interior - L1 MSB - COLO4 Cell 4 | 0
CHI05-04-03-ER-1490 | CHI05-04-04-ER-1625 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Installation of ADP & ATS - COLO4 Cell 3 - ER | Installation of MSB - COLO4 Cell 4 - ER | 0
A1020 | CHI05-04-04-ER-1625 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,16,3 MSB - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | MSB - COLO 4 - ROJ | Installation of MSB - COLO4 Cell 4 - ER | 0
CHI05-04-03-ER-1495 | CHI05-04-04-ER-1625 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Installation of MSB - COLO4 Cell 3 - ER | Installation of MSB - COLO4 Cell 4 - ER | 0
CHI05-05-NTP-S | CHI05-05-01-ER-1330 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Notice To Proceed | Install Walls and Primer Paint - COLO5 Cell 1 - ER | 0
CHI05-03-04-ER-1440 | CHI05-04-01-ER-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Install Walls and Primer Paint - COLO3 Cell 4 - ER | Install Walls and Primer Paint - COLO4 Cell 1 - ER | 0
CHI05-02-04-ER-1390 | CHI05-03-01-ER-1170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Installation of UPS Equipment - COLO2 Cell 4 - ER | Installation of UPS Equipment - COLO3 Cell 1 - ER | 0
CHI05-CFCI-1240 | CHI05-02-01-MG-1000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG | 0
CHI05-CFCI-1240 | CHI05-02-01-MG-1010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,5,6,2 COLO 2 Cell 1 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 1 - MG | 0
CHI05-CFCI-1240 | CHI05-02-02-MG-1110 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 2 - MG | 0
CHI05-CFCI-1240 | CHI05-02-02-MG-1120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,5,1,2 COLO 2 Cell 2 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 2 - MG | 0
CHI05-CFCI-1240 | CHI05-02-03-MG-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 3 - MG | 0
CHI05-CFCI-1240 | CHI05-02-03-MG-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,5,3,2 COLO 2 Cell 3 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 3 - MG | 0
CHI05-CFCI-1240 | CHI05-02-04-MG-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 4 - MG | 0
CHI05-CFCI-1240 | CHI05-02-04-MG-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,5,2,2 COLO 2 Cell 4 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 4 - MG | 0
CHI05-CFCI-1240 | CHI05-03-01-MG-1110 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 1 - MG | 0
CHI05-CFCI-1240 | CHI05-03-01-MG-1120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,1,6,2 COLO 3 Cell 1 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 1 - MG | 0
CHI05-CFCI-1240 | CHI05-03-02-MG-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 2 - MG | 0
CHI05-CFCI-1240 | CHI05-03-02-MG-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,1,1,2 COLO 3 Cell 2 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 2 - MG | 0
CHI05-CFCI-1240 | CHI05-03-03-MG-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 3 - MG | 0
CHI05-CFCI-1240 | CHI05-03-03-MG-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,1,3,2 COLO 3 Cell 3 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 3 - MG | 0
CHI05-CFCI-1240 | CHI05-03-04-MG-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 4 - MG | 0
CHI05-CFCI-1240 | CHI05-03-04-MG-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,1,2,2 COLO 3 Cell 4 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 4 - MG | 0
CHI05-CFCI-1240 | CHI05-04-01-MG-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 1 - MG | 0
CHI05-CFCI-1240 | CHI05-04-01-MG-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,2,6,2 COLO 4 Cell 1 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 1 - MG | 0
CHI05-CFCI-1240 | CHI05-04-02-MG-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 2 - MG | 0
CHI05-CFCI-1240 | CHI05-04-02-MG-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,2,1,2 COLO 4 Cell 2 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 2 - MG | 0
CHI05-CFCI-1240 | CHI05-04-03-MG-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 3 - MG | 0
CHI05-CFCI-1240 | CHI05-04-03-MG-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,2,3,2 COLO 4 Cell 3 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 3 - MG | 0
CHI05-CFCI-1240 | CHI05-04-04-MG-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 4 - MG | 0
CHI05-CFCI-1240 | CHI05-04-04-MG-1560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,2,2,2 COLO 4 Cell 4 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG | 0
CHI05-CFCI-1240 | CHI05-05-01-MG-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 1 - MG | 0
CHI05-CFCI-1240 | CHI05-05-01-MG-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 1 - MG | 0
CHI05-CFCI-1240 | CHI05-05-02-MG-1440 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 2 - MG | 0
CHI05-CFCI-1240 | CHI05-05-02-MG-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,3,1,2 COLO 5 Cell 2 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 2 - MG | 0
CHI05-CFCI-1240 | CHI05-05-03-MG-1550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 3 - MG | 0
CHI05-CFCI-1240 | CHI05-05-03-MG-1560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,3,3,2 COLO 5 Cell 3 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 3 - MG | 0
CHI05-CFCI-1240 | CHI05-05-04-MG-1660 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 4 - MG | 0
CHI05-CFCI-1240 | CHI05-05-04-MG-1670 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,2 Dampers | CHI05-PH2-FIT-BL-D5,3,3,3,2,2 COLO 5 Cell 4 Mechanical Gallery | Damper Assembly and Delivery | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 4 - MG | 0
CHI05-CON-1030 | CHI05-03-01-L3-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Installation and Termiation of MV Cable | L3 UPM - COLO3 | 0
CHI05-CON-1030 | CHI05-04-01-L3-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Installation and Termiation of MV Cable | L3 UPM - COLO4 | 0
CHI05-05-02-DH-1430 | CHI05-05-02-DH-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH | Termination at PDU & Busway- COLO5 Cell 2 - DH | 0
CHI05-05-02-DH-1460 | CHI05-05-02-DH-1530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | CHI05-PH2-FIT-BL-D5,3,3,3,1,1 COLO 5 Cell 2 Data Hall | Termination at PDU & Busway- COLO5 Cell 2 - DH | Finishes and Signage - COLO5 Cell 2 - DH | 0
CHI05-CFCI-1170 | CHI05-02-01-ER-1030 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO2 Cell 1 - ER | 0
CHI05-CFCI-1170 | CHI05-02-02-ER-1140 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO2 Cell 2 - ER | 0
CHI05-CFCI-1170 | CHI05-02-03-ER-1250 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO2 Cell 3 - ER | 0
CHI05-CFCI-1170 | CHI05-02-04-ER-1360 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO2 Cell 4 - ER | 0
CHI05-CFCI-1170 | CHI05-03-01-ER-1140 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO3 Cell 1 - ER | 0
CHI05-CFCI-1170 | CHI05-03-02-ER-1250 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO3 Cell 2 - ER | 0
CHI05-CFCI-1170 | CHI05-03-03-ER-1360 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO3 Cell 3 - ER | 0
CHI05-CFCI-1170 | CHI05-03-04-ER-1470 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO3 Cell 4 - ER | 0
CHI05-CFCI-1170 | CHI05-04-01-ER-1250 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO4 Cell 1 - ER | 0
CHI05-CFCI-1170 | CHI05-04-02-ER-1360 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO4 Cell 2 - ER | 0
CHI05-CFCI-1170 | CHI05-04-03-ER-1470 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO4 Cell 3 - ER | 0
CHI05-CFCI-1170 | CHI05-04-04-ER-1580 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO4 Cell 4 - ER | 0
CHI05-CFCI-1170 | CHI05-05-01-ER-1360 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO5 Cell 1 - ER | 0
CHI05-CFCI-1170 | CHI05-05-02-ER-1470 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO5 Cell 2 - ER | 0
CHI05-CFCI-1170 | CHI05-05-03-ER-1580 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO5 Cell 3 - ER | 0
CHI05-CFCI-1170 | CHI05-05-04-ER-1690 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,4 DX Split Units | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | DX Split Units - Lead Time | Install Ceiling - COLO5 Cell 4 - ER | 0
CHI05-CFCI-1200 | CHI05-05-01-MG-1360 | FS | In Progress | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,6 AHU | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | AHU (Admin) - Lead Time | Deliver AHU into Mech. Gallery - COLO5 Cell 1 - MG | 0
CHI05-OFCI-1130 | CHI05-YARD-2120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,1 GENS - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | GENS - COLO 2 - In Storage | Set the Generator - Colo 2 - South | 0
CHI05-OFCI-1140 | CHI05-YARD-2060 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,2 GENS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | GENS - COLO 3 - In Storage | Set the Generator - Colo 3 - North | 0
CHI05-05-01-MG-1420 | CHI05-05-01-MG-1425 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Install ceiling and Light Fittings - COLO5 Cell 1 - MG | Install Damper in Ceiling (RAD) - COLO 5 Cell 1 - MG | 0
CHI05-05-01-MG-1425 | CHI05-05-01-MG-1430 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | CHI05-PH2-FIT-BL-D5,3,3,3,6,2 COLO 5 Cell 1 Mechanical Gallery | Install Damper in Ceiling (RAD) - COLO 5 Cell 1 - MG | Trim out MEP - COLO5 Cell 1 - MG | 0
CHI05-05-NTP-S | CHI05-OFCI-1800 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,15,5 Mufflers - COLO 5 | Notice To Proceed | Mufflers - COLO 5 - Start ROJ | 0
CHI05-05-NTP-S | CHI05-OFCI-1810 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,15,5 Mufflers - COLO 5 | Notice To Proceed | Mufflers - COLO 5 - ROJ | 0
CHI05-OFCI-1800 | CHI05-OFCI-1810 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,5 Mufflers - COLO 5 | CHI05-PH2-FIT-BL-D5,4,1,15,5 Mufflers - COLO 5 | Mufflers - COLO 5 - Start ROJ | Mufflers - COLO 5 - ROJ | 0
CHI05-OFCI-1160 | CHI05-YARD-2480 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,5 GENS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | GENS - COLO 5 - In Storage | Set the Generator - Colo 5 - East | 0
CHI05-YARD-2480 | CHI05-05-01-L1-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the Generator - Colo 5 - East | L1 GEN - COLO5 | 0
CHI05-YARD-2480 | CHI05-YARD-2120 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | Set the Generator - Colo 5 - East | Set the Generator - Colo 2 - South | 0
CHI05-YARD-2480 | CHI05-YARD-2180 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | Set the Generator - Colo 5 - East | Install MEP raceway conduit and piping - Colo 5 - East | 0
CHI05-YARD-2480 | CHI05-YARD-2490 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | Set the Generator - Colo 5 - East | Install Generator - Colo 5 - East | 0
CHI05-YARD-2500 | CHI05-YARD-2300 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | Set the MV Gear - Colo 2 - South | Install MEP raceway conduit and piping - Colo 2 - South | 0
CHI05-YARD-2500 | CHI05-02-03-L1-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 2 - South | L1 UMS 01 - COLO 5 | 0
CHI05-YARD-2500 | CHI05-02-04-L1-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 2 - South | L1 URS 01 - COLO 5 | 0
CHI05-YARD-2070 | CHI05-YARD-2500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | Set the MV Gear - Colo 5 - East | Set the MV Gear - Colo 2 - South | 0
CHI05-YARD-2500 | CHI05-YARD-2170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | Set the MV Gear - Colo 2 - South | Set the MV Gear - Colo 3 - South | 0
CHI05-YARD-2500 | CHI05-YARD-2510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | Set the MV Gear - Colo 2 - South | Install MV Gear - Colo 2 - South | 0
CHI05-YARD-2520 | CHI05-YARD-2340 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | Set the Generator - Colo 3 - South | Install MEP raceway conduit and piping - Colo 3 - South | 0
CHI05-YARD-2520 | CHI05-YARD-2530 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | Set the Generator - Colo 3 - South | Install Generator - Colo 3 - South | 0
CHI05-YARD-2520 | CHI05-03-01-L1-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the Generator - Colo 3 - South | L1 GEN - COLO3 | 0
CHI05-YARD-2120 | CHI05-YARD-2520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | Set the Generator - Colo 2 - South | Set the Generator - Colo 3 - South | 0
CHI05-OFCI-1140 | CHI05-YARD-2520 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,2 GENS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | GENS - COLO 3 - In Storage | Set the Generator - Colo 3 - South | 0
CHI05-YARD-2540 | CHI05-YARD-2370 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | Set the Generator - Colo 4 - South | Install MEP raceway conduit and piping - Colo 4 - South | 0
CHI05-YARD-2540 | CHI05-YARD-2550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | Set the Generator - Colo 4 - South | Install Generator - Colo 4 - South | 0
CHI05-YARD-2540 | CHI05-04-01-L1-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the Generator - Colo 4 - South | L1 GEN - COLO4 | 0
CHI05-YARD-2540 | CHI05-YARD-2000 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | Set the Generator - Colo 4 - South | Set the Generator - Colo 2 - North | 0
CHI05-OFCI-1150 | CHI05-YARD-2540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,3 GENS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | GENS - COLO 4 - In Storage | Set the Generator - Colo 4 - South | 0
CHI05-YARD-2520 | CHI05-YARD-2540 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | Set the Generator - Colo 3 - South | Set the Generator - Colo 4 - South | 0
CHI05-YARD-2560 | CHI05-YARD-2040 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | Set the MV Gear - Colo 2 - North | Install MEP raceway conduit and piping - Colo 2 - North | 0
CHI05-YARD-2560 | CHI05-YARD-2570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | Set the MV Gear - Colo 2 - North | Install MV Gear - Colo 2 - North | 0
CHI05-YARD-2560 | CHI05-02-03-L1-1450 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 2 - North | L1 UMS 01 - COLO 5 | 0
CHI05-YARD-2560 | CHI05-02-04-L1-1570 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 2 - North | L1 URS 01 - COLO 5 | 0
CHI05-YARD-2220 | CHI05-YARD-2560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | Set the MV Gear - Colo 4 - South | Set the MV Gear - Colo 2 - North | 0
CHI05-YARD-2580 | CHI05-YARD-2160 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | Set the MV Gear - Colo 3 - North | Install MEP raceway conduit and piping - Colo 3 - North | 0
CHI05-YARD-2580 | CHI05-YARD-2100 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | Set the MV Gear - Colo 3 - North | Set the MV Gear - Colo 4 - North | 0
CHI05-YARD-2580 | CHI05-YARD-2590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | Set the MV Gear - Colo 3 - North | Install MV Gear - Colo 3 - North | 0
CHI05-YARD-2580 | CHI05-02-01-L1-1210 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 3 - North | L1 UMS 04 - COLO 3 | 0
CHI05-YARD-2580 | CHI05-02-02-L1-1330 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 3 - North | L1 UMS 03 - COLO 3 | 0
CHI05-YARD-2560 | CHI05-YARD-2580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | Set the MV Gear - Colo 2 - North | Set the MV Gear - Colo 3 - North | 0
CHI05-YARD-2600 | CHI05-YARD-2240 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | Set the Generator - Colo 4 - North | Install MEP raceway conduit and piping - Colo 4 - North | 0
CHI05-YARD-2060 | CHI05-YARD-2600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | Set the Generator - Colo 3 - North | Set the Generator - Colo 4 - North | 0
CHI05-YARD-2600 | CHI05-YARD-2610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | Set the Generator - Colo 4 - North | Install Generator - Colo 4 - North | 0
CHI05-YARD-2600 | CHI05-04-01-L1-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the Generator - Colo 4 - North | L1 GEN - COLO4 | 0
CHI05-OFCI-1150 | CHI05-YARD-2600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,3 GENS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | GENS - COLO 4 - In Storage | Set the Generator - Colo 4 - North | 0
CHI05-YARD-2620 | CHI05-YARD-2050 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | Set the Generator - Colo 5 - West | Install MEP raceway conduit and piping - Colo 5 - West | 0
CHI05-OFCI-1160 | CHI05-YARD-2620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,5,5 GENS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | GENS - COLO 5 - In Storage | Set the Generator - Colo 5 - West | 0
CHI05-YARD-2620 | CHI05-YARD-2630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | Set the Generator - Colo 5 - West | Install Generator - Colo 5 - West | 0
CHI05-YARD-2600 | CHI05-YARD-2620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | Set the Generator - Colo 4 - North | Set the Generator - Colo 5 - West | 0
CHI05-YARD-2490 | CHI05-05-01-L2-1720 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install Generator - Colo 5 - East | L2 GEN - COLO5 | 0
CHI05-YARD-2080 | CHI05-05-01-L2-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install MV Gear - Colo 5 - East | L2 UPM - COLO5 | 0
CHI05-YARD-2130 | CHI05-02-01-L2-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install Generator - Colo 2 - South | L2 GEN - COLO2 | 0
CHI05-YARD-2510 | CHI05-02-01-L2-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install MV Gear - Colo 2 - South | L2 UPM - COLO2 | 0
CHI05-YARD-2190 | CHI05-03-01-L2-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install MV Gear - Colo 3 - South | L2 UPM - COLO3 | 0
CHI05-YARD-2530 | CHI05-03-01-L2-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install Generator - Colo 3 - South | L2 GEN - COLO3 | 0
CHI05-YARD-2030 | CHI05-02-01-L2-1360 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install Generator - Colo 2 - North | L2 GEN - COLO2 | 0
CHI05-YARD-2550 | CHI05-04-01-L2-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install Generator - Colo 4 - South | L2 GEN - COLO4 | 0
CHI05-YARD-2090 | CHI05-03-01-L2-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install Generator - Colo 3 - North | L2 GEN - COLO3 | 0
CHI05-YARD-2610 | CHI05-04-01-L2-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install Generator - Colo 4 - North | L2 GEN - COLO4 | 0
CHI05-YARD-2630 | CHI05-05-01-L2-1720 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install Generator - Colo 5 - West | L2 GEN - COLO5 | 0
CHI05-YARD-2230 | CHI05-04-01-L2-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install MV Gear - Colo 4 - South | L2 UPM - COLO4 | 0
CHI05-YARD-2570 | CHI05-02-01-L2-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install MV Gear - Colo 2 - North | L2 UPM - COLO2 | 0
CHI05-YARD-2590 | CHI05-03-01-L2-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install MV Gear - Colo 3 - North | L2 UPM - COLO3 | 0
CHI05-YARD-2110 | CHI05-04-01-L2-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install MV Gear - Colo 4 - North | L2 UPM - COLO4 | 0
CHI05-YARD-2020 | CHI05-05-01-L2-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | Install MV Gear - Colo 5 - West | L2 UPM - COLO5 | 0
CHI05-02-01-L1-1220 | CHI05-02-03-L1-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | L1 UPM - COLO2 | Interior - L1 UPS - COLO2 Cell 3 | 0
CHI05-02-01-L1-1220 | CHI05-02-04-L1-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | L1 UPM - COLO2 | Interior - L1 UPS - COLO2 Cell 4 | 0
CHI05-05-01-L1-1580 | CHI05-05-02-L1-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | L1 UPM - COLO5 | Interior - L1 UPS - COLO5 Cell 2 | 0
CHI05-02-01-L1-1230 | CHI05-02-02-L1-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | L1 XFMR - MV- COLO2 | Interior - L1 MSB - COLO2 Cell 2 | 0
CHI05-02-01-L1-1230 | CHI05-02-03-L1-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | L1 XFMR - MV- COLO2 | Interior - L1 MSB - COLO2 Cell 3 | 0
CHI05-02-01-L1-1230 | CHI05-02-04-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | L1 XFMR - MV- COLO2 | Interior - L1 MSB - COLO2 Cell 4 | 0
CHI05-03-01-L1-1350 | CHI05-03-02-L1-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | L1 XFMR - MV- COLO3 | Interior - L1 MSB - COLO3 Cell 2 | 0
CHI05-03-01-L1-1350 | CHI05-03-03-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | L1 XFMR - MV- COLO3 | Interior - L1 MSB - COLO3 Cell 3 | 0
CHI05-03-01-L1-1350 | CHI05-03-04-L1-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | L1 XFMR - MV- COLO3 | Interior - L1 MSB - COLO3 Cell 4 | 0
CHI05-04-01-L1-1470 | CHI05-04-02-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | L1 XFMR - MV- COLO4 | Interior - L1 MSB - COLO4 Cell 2 | 0
CHI05-04-01-L1-1470 | CHI05-04-03-L1-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | L1 XFMR - MV- COLO4 | Interior - L1 MSB - COLO4 Cell 3 | 0
CHI05-04-01-L1-1470 | CHI05-04-04-L1-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | L1 XFMR - MV- COLO4 | Interior - L1 MSB - COLO4 Cell 4 | 0
CHI05-05-01-L1-1590 | CHI05-05-02-L1-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | L1 XFMR - MV- COLO5 | Interior - L1 MSB - COLO5 Cell 2 | 0
CHI05-05-01-L1-1590 | CHI05-05-03-L1-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | L1 XFMR - MV- COLO5 | Interior - L1 MSB - COLO5 Cell 3 | 0
CHI05-05-01-L1-1590 | CHI05-05-04-L1-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | L1 XFMR - MV- COLO5 | Interior - L1 MSB - COLO5 Cell 4 | 0
CHI05-02-01-L1-1240 | CHI05-02-02-L1-1270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,1 Level 1 Cx - Colo 2 | L1 GEN - COLO2 | Interior - L1 MSB - COLO2 Cell 2 | 0
CHI05-02-01-L1-1240 | CHI05-02-03-L1-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,1 Level 1 Cx - Colo 2 | L1 GEN - COLO2 | Interior - L1 MSB - COLO2 Cell 3 | 0
CHI05-02-01-L1-1240 | CHI05-02-04-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,1 Level 1 Cx - Colo 2 | L1 GEN - COLO2 | Interior - L1 MSB - COLO2 Cell 4 | 0
CHI05-03-01-L1-1360 | CHI05-03-02-L1-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,1 Level 1 Cx - Colo 3 | L1 GEN - COLO3 | Interior - L1 MSB - COLO3 Cell 2 | 0
CHI05-03-01-L1-1360 | CHI05-03-03-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,1 Level 1 Cx - Colo 3 | L1 GEN - COLO3 | Interior - L1 MSB - COLO3 Cell 3 | 0
CHI05-03-01-L1-1360 | CHI05-03-04-L1-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,1 Level 1 Cx - Colo 3 | L1 GEN - COLO3 | Interior - L1 MSB - COLO3 Cell 4 | 0
CHI05-04-01-L1-1480 | CHI05-04-02-L1-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,1 Level 1 Cx - Colo 4 | L1 GEN - COLO4 | Interior - L1 MSB - COLO4 Cell 2 | 0
CHI05-04-01-L1-1480 | CHI05-04-03-L1-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,1 Level 1 Cx - Colo 4 | L1 GEN - COLO4 | Interior - L1 MSB - COLO4 Cell 3 | 0
CHI05-04-01-L1-1480 | CHI05-04-04-L1-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,1 Level 1 Cx - Colo 4 | L1 GEN - COLO4 | Interior - L1 MSB - COLO4 Cell 4 | 0
CHI05-YARD-2620 | CHI05-05-01-L1-1600 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the Generator - Colo 5 - West | L1 GEN - COLO5 | 0
CHI05-05-01-L1-1600 | CHI05-05-02-L1-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,1 Level 1 Cx - Colo 5 | L1 GEN - COLO5 | Interior - L1 MSB - COLO5 Cell 2 | 0
CHI05-05-01-L1-1600 | CHI05-05-03-L1-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,1 Level 1 Cx - Colo 5 | L1 GEN - COLO5 | Interior - L1 MSB - COLO5 Cell 3 | 0
CHI05-05-01-L1-1600 | CHI05-02-01-L1-1240 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | L1 GEN - COLO5 | L1 GEN - COLO2 | 0
CHI05-05-01-L1-1600 | CHI05-05-04-L1-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,1 Level 1 Cx - Colo 5 | L1 GEN - COLO5 | Interior - L1 MSB - COLO5 Cell 4 | 0
CHI05-02-01-L1-1240 | CHI05-02-01-L2-1360 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | L1 GEN - COLO2 | L2 GEN - COLO2 | 0
CHI05-02-01-L2-1360 | CHI05-02-02-L2-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | L2 GEN - COLO2 | Interior - L2 MSB - COLO2 Cell 2 | 0
CHI05-02-01-L2-1360 | CHI05-02-03-L2-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | L2 GEN - COLO2 | Interior - L2 MSB - COLO2 Cell 3 | 0
CHI05-02-01-L2-1360 | CHI05-02-04-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | L2 GEN - COLO2 | Interior - L2 MSB - COLO2 Cell 4 | 0
CHI05-03-01-L2-1480 | CHI05-03-02-L2-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | L2 GEN - COLO3 | Interior - L2 MSB - COLO3 Cell 2 | 0
CHI05-03-01-L2-1480 | CHI05-03-03-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | L2 GEN - COLO3 | Interior - L2 MSB - COLO3 Cell 3 | 0
CHI05-03-01-L2-1480 | CHI05-03-04-L2-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | L2 GEN - COLO3 | Interior - L2 MSB - COLO3 Cell 4 | 0
CHI05-04-01-L2-1600 | CHI05-04-02-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | L2 GEN - COLO4 | Interior - L2 MSB - COLO4 Cell 2 | 0
CHI05-04-01-L2-1600 | CHI05-04-03-L2-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | L2 GEN - COLO4 | Interior - L2 MSB - COLO4 Cell 3 | 0
CHI05-04-01-L2-1600 | CHI05-04-04-L2-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | L2 GEN - COLO4 | Interior - L2 MSB - COLO4 Cell 4 | 0
CHI05-05-01-L2-1720 | CHI05-05-02-L2-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | L2 GEN - COLO5 | Interior - L2 MSB - COLO5 Cell 2 | 0
CHI05-05-01-L2-1720 | CHI05-05-03-L2-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | L2 GEN - COLO5 | Interior - L2 MSB - COLO5 Cell 3 | 0
CHI05-05-01-L2-1720 | CHI05-05-04-L2-1990 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | L2 GEN - COLO5 | Interior - L2 MSB - COLO5 Cell 4 | 0
CHI05-02-01-L2-1340 | CHI05-02-02-L2-1380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | L2 UPM - COLO2 | Interior - L2 UPS - COLO2 Cell 2 | 0
CHI05-02-01-L2-1340 | CHI05-02-03-L2-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | L2 UPM - COLO2 | Interior - L2 UPS - COLO2 Cell 3 | 0
CHI05-02-01-L2-1340 | CHI05-02-04-L2-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | L2 UPM - COLO2 | Interior - L2 UPS - COLO2 Cell 4 | 0
CHI05-03-01-L2-1460 | CHI05-03-02-L2-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | L2 UPM - COLO3 | Interior - L2 UPS - COLO3 Cell 2 | 0
CHI05-03-01-L2-1460 | CHI05-03-03-L2-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | L2 UPM - COLO3 | Interior - L2 UPS - COLO3 Cell 3 | 0
CHI05-03-01-L2-1460 | CHI05-03-04-L2-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | L2 UPM - COLO3 | Interior - L2 UPS - COLO3 Cell 4 | 0
CHI05-04-01-L2-1580 | CHI05-04-02-L2-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | L2 UPM - COLO4 | Interior - L2 UPS - COLO4 Cell 2 | 0
CHI05-04-01-L2-1580 | CHI05-04-03-L2-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | L2 UPM - COLO4 | Interior - L2 UPS - COLO4 Cell 3 | 0
CHI05-04-01-L2-1580 | CHI05-04-04-L2-1860 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | L2 UPM - COLO4 | Interior - L2 UPS - COLO4 Cell 4 | 0
CHI05-05-01-L2-1700 | CHI05-05-02-L2-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | L2 UPM - COLO5 | Interior - L2 UPS - COLO5 Cell 2 | 0
CHI05-05-01-L2-1700 | CHI05-05-03-L2-1860 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | L2 UPM - COLO5 | Interior - L2 UPS - COLO5 Cell 3 | 0
CHI05-05-01-L2-1700 | CHI05-05-04-L2-1980 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | L2 UPM - COLO5 | Interior - L2 UPS - COLO5 Cell 4 | 0
CHI05-02-01-L2-1350 | CHI05-02-02-L2-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,2 Level 2 Cx - Colo 2 | L2 XFMR - COLO2 | Interior - L2 MSB - COLO2 Cell 2 | 0
CHI05-02-01-L2-1350 | CHI05-02-03-L2-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,2 Level 2 Cx - Colo 2 | L2 XFMR - COLO2 | Interior - L2 MSB - COLO2 Cell 3 | 0
CHI05-02-01-L2-1350 | CHI05-02-04-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,2 Level 2 Cx - Colo 2 | L2 XFMR - COLO2 | Interior - L2 MSB - COLO2 Cell 4 | 0
CHI05-03-01-L2-1470 | CHI05-03-02-L2-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,2 Level 2 Cx - Colo 3 | L2 XFMR - COLO3 | Interior - L2 MSB - COLO3 Cell 2 | 0
CHI05-03-01-L2-1470 | CHI05-03-03-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,2 Level 2 Cx - Colo 3 | L2 XFMR - COLO3 | Interior - L2 MSB - COLO3 Cell 3 | 0
CHI05-03-01-L2-1470 | CHI05-03-04-L2-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,2 Level 2 Cx - Colo 3 | L2 XFMR - COLO3 | Interior - L2 MSB - COLO3 Cell 4 | 0
CHI05-04-01-L2-1590 | CHI05-04-02-L2-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,2 Level 2 Cx - Colo 4 | L2 XFMR - COLO4 | Interior - L2 MSB - COLO4 Cell 2 | 0
CHI05-04-01-L2-1590 | CHI05-04-03-L2-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,2 Level 2 Cx - Colo 4 | L2 XFMR - COLO4 | Interior - L2 MSB - COLO4 Cell 3 | 0
CHI05-04-01-L2-1590 | CHI05-04-04-L2-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,2 Level 2 Cx - Colo 4 | L2 XFMR - COLO4 | Interior - L2 MSB - COLO4 Cell 4 | 0
CHI05-05-01-L2-1710 | CHI05-05-02-L2-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,2 Level 2 Cx - Colo 5 | L2 XFMR - COLO5 | Interior - L2 MSB - COLO5 Cell 2 | 0
CHI05-05-01-L2-1710 | CHI05-05-03-L2-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,2 Level 2 Cx - Colo 5 | L2 XFMR - COLO5 | Interior - L2 MSB - COLO5 Cell 3 | 0
CHI05-05-01-L2-1710 | CHI05-05-04-L2-1990 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,2 Level 2 Cx - Colo 5 | L2 XFMR - COLO5 | Interior - L2 MSB - COLO5 Cell 4 | 0
CHI05-02-01-L2-1360 | CHI05-02-01-L3-1480 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L2 GEN - COLO2 | L3 GEN - COLO2 | 0
CHI05-02-01-L3-1480 | CHI05-02-02-L3-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | L3 GEN - COLO2 | Interior - L3 MSB - COLO2 Cell 2 | 0
CHI05-02-01-L3-1480 | CHI05-02-03-L3-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | L3 GEN - COLO2 | Interior - L3 MSB - COLO2 Cell 3 | 0
CHI05-02-01-L3-1480 | CHI05-02-04-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | L3 GEN - COLO2 | Interior - L3 MSB - COLO2 Cell 4 | 0
CHI05-03-01-L3-1600 | CHI05-03-02-L3-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | L3 GEN - COLO3 | Interior - L3 MSB - COLO3 Cell 2 | 0
CHI05-03-01-L3-1600 | CHI05-03-03-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | L3 GEN - COLO3 | Interior - L3 MSB - COLO3 Cell 3 | 0
CHI05-03-01-L3-1600 | CHI05-03-04-L3-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | L3 GEN - COLO3 | Interior - L3 MSB - COLO3 Cell 4 | 0
CHI05-04-01-L3-1720 | CHI05-04-02-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | L3 GEN - COLO4 | Interior - L3 MSB - COLO4 Cell 2 | 0
CHI05-04-01-L3-1720 | CHI05-04-03-L3-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | L3 GEN - COLO4 | Interior - L3 MSB - COLO4 Cell 3 | 0
CHI05-04-01-L3-1720 | CHI05-04-04-L3-1990 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | L3 GEN - COLO4 | Interior - L3 MSB - COLO4 Cell 4 | 0
CHI05-05-01-L3-1840 | CHI05-05-02-L3-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | L3 GEN - COLO5 | Interior - L3 MSB - COLO5 Cell 2 | 0
CHI05-05-01-L3-1840 | CHI05-05-03-L3-1990 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | L3 GEN - COLO5 | Interior - L3 MSB - COLO5 Cell 3 | 0
CHI05-05-01-L3-1840 | CHI05-05-04-L3-2110 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | L3 GEN - COLO5 | Interior - L3 MSB - COLO5 Cell 4 | 0
CHI05-05-01-L3-1840 | CHI05-05-04-L3-2140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | L3 GEN - COLO5 | Interior - L3 ATSs - COLO5 Cell 4 | 0
CHI05-02-02-ER-1200 | CHI05-02-01-L3-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,1,5 COLO 2 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO2 Cell 2 - ER | L3 UPM - COLO2 | 0
CHI05-CON-1030 | CHI05-02-01-L3-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Installation and Termiation of MV Cable | L3 UPM - COLO2 | 0
CHI05-02-01-L3-1460 | CHI05-02-02-L3-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | L3 UPM - COLO2 | Interior - L3 UPS - COLO2 Cell 2 | 0
CHI05-02-03-ER-1310 | CHI05-02-01-L3-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO2 Cell 3 - ER | L3 UPM - COLO2 | 0
CHI05-02-01-L3-1460 | CHI05-02-03-L3-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | L3 UPM - COLO2 | Interior - L3 UPS - COLO2 Cell 3 | 0
CHI05-02-04-ER-1420 | CHI05-02-01-L3-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO2 Cell 4 - ER | L3 UPM - COLO2 | 0
CHI05-02-01-L3-1460 | CHI05-02-BAS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | L3 UPM - COLO2 | Complete BAS SAT for Colo 2 | 0
CHI05-02-01-L3-1460 | CHI05-02-EPMS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | L3 UPM - COLO2 | Complete EPMS SAT for Colo 2 | 0
CHI05-02-01-L3-1460 | CHI05-02-FIRE-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,5 Colo 2 | L3 UPM - COLO2 | Complete Fire Alarm for Colo 2 | 0
CHI05-02-01-L3-1460 | CHI05-02-04-L3-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | L3 UPM - COLO2 | Interior - L3 UPS - COLO2 Cell 4 | 0
CHI05-03-02-ER-1310 | CHI05-03-01-L3-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO3 Cell 2 - ER | L3 UPM - COLO3 | 0
CHI05-03-01-L3-1580 | CHI05-03-02-L3-1620 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | L3 UPM - COLO3 | Interior - L3 UPS - COLO3 Cell 2 | 0
CHI05-03-03-ER-1420 | CHI05-03-01-L3-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO3 Cell 3 - ER | L3 UPM - COLO3 | 0
CHI05-03-01-L3-1580 | CHI05-03-03-L3-1740 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | L3 UPM - COLO3 | Interior - L3 UPS - COLO3 Cell 3 | 0
CHI05-03-01-L3-1580 | CHI05-03-01-L3-1600 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UPM - COLO3 | L3 GEN - COLO3 | 0
CHI05-03-04-ER-1530 | CHI05-03-01-L3-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO3 Cell 4 - ER | L3 UPM - COLO3 | 0
CHI05-03-01-L3-1580 | CHI05-03-L3CX-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | L3 UPM - COLO3 | Start L3 Cx (Green tag) for Colo 3 | 0
CHI05-03-01-L3-1580 | CHI05-03-BAS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | L3 UPM - COLO3 | Complete BAS SAT for Colo 3 | 0
CHI05-03-01-L3-1580 | CHI05-03-EPMS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | L3 UPM - COLO3 | Complete EPMS SAT for Colo 3 | 0
CHI05-03-01-L3-1580 | CHI05-03-FIRE-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,2 Colo 3 | L3 UPM - COLO3 | Complete Fire Alarm for Colo 3 | 0
CHI05-03-01-L3-1580 | CHI05-03-04-L3-1860 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | L3 UPM - COLO3 | Interior - L3 UPS - COLO3 Cell 4 | 0
CHI05-04-03-ER-1530 | CHI05-04-01-L3-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO4 Cell 3 - ER | L3 UPM - COLO4 | 0
CHI05-04-04-ER-1640 | CHI05-04-01-L3-1700 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO4 Cell 4 - ER | L3 UPM - COLO4 | 0
CHI05-04-01-L3-1700 | CHI05-04-L3CX-S | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | L3 UPM - COLO4 | Start L3 Cx (Green tag) for Colo 4 | 0
CHI05-04-01-L3-1700 | CHI05-04-BAS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | L3 UPM - COLO4 | Complete BAS SAT for Colo 4 | 0
CHI05-04-01-L3-1700 | CHI05-04-EPMS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | L3 UPM - COLO4 | Complete EPMS SAT for Colo 4 | 0
CHI05-04-01-L3-1700 | CHI05-04-FIRE-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,4 Colo 4 | L3 UPM - COLO4 | Complete Fire Alarm for Colo 4 | 0
CHI05-04-01-L3-1700 | CHI05-04-04-L3-1980 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | L3 UPM - COLO4 | Interior - L3 UPS - COLO4 Cell 4 | 0
CHI05-04-01-L3-1700 | CHI05-04-01-L3-1720 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L3 UPM - COLO4 | L3 GEN - COLO4 | 0
CHI05-05-02-ER-1530 | CHI05-05-01-L3-1820 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO5 Cell 2 - ER | L3 UPM - COLO5 | 0
CHI05-05-01-L3-1820 | CHI05-05-02-L3-1860 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | L3 UPM - COLO5 | Interior - L3 UPS - COLO5 Cell 2 | 0
CHI05-05-03-ER-1640 | CHI05-05-01-L3-1820 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO5 Cell 3 - ER | L3 UPM - COLO5 | 0
CHI05-05-01-L3-1820 | CHI05-05-03-L3-1980 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | L3 UPM - COLO5 | Interior - L3 UPS - COLO5 Cell 3 | 0
CHI05-05-04-ER-1750 | CHI05-05-01-L3-1820 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | Door Frame Installation - COLO5 Cell 4 - ER | L3 UPM - COLO5 | 0
CHI05-05-01-L3-1820 | CHI05-05-BAS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | L3 UPM - COLO5 | Complete BAS SAT for Colo 5 | 0
CHI05-05-01-L3-1820 | CHI05-05-EPMS-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | L3 UPM - COLO5 | Complete EPMS SAT for Colo 5 | 0
CHI05-05-01-L3-1820 | CHI05-05-FIR-F | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,2,2,3 Colo 5 | L3 UPM - COLO5 | Complete Fire Alarm for Colo 5 | 0
CHI05-05-01-L3-1820 | CHI05-05-04-L3-2100 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | L3 UPM - COLO5 | Interior - L3 UPS - COLO5 Cell 4 | 0
CHI05-02-01-L3-1470 | CHI05-02-02-L3-1510 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,1,4,3 Level 3 Cx - Colo 2 | L3 XFMR - COLO2 | Interior - L3 MSB - COLO2 Cell 2 | 0
CHI05-02-01-L3-1470 | CHI05-02-03-L3-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,3,4,3 Level 3 Cx - Colo 2 | L3 XFMR - COLO2 | Interior - L3 MSB - COLO2 Cell 3 | 0
CHI05-02-01-L3-1470 | CHI05-02-04-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,5,2,4,3 Level 3 Cx - Colo 2 | L3 XFMR - COLO2 | Interior - L3 MSB - COLO2 Cell 4 | 0
CHI05-03-01-L3-1590 | CHI05-03-02-L3-1630 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,1,4,3 Level 3 Cx - Colo 3 | L3 XFMR - COLO3 | Interior - L3 MSB - COLO3 Cell 2 | 0
CHI05-03-01-L3-1590 | CHI05-03-03-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,3,4,3 Level 3 Cx - Colo 3 | L3 XFMR - COLO3 | Interior - L3 MSB - COLO3 Cell 3 | 0
CHI05-03-01-L3-1590 | CHI05-03-04-L3-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,1,2,4,3 Level 3 Cx - Colo 3 | L3 XFMR - COLO3 | Interior - L3 MSB - COLO3 Cell 4 | 0
CHI05-04-01-L3-1710 | CHI05-04-02-L3-1750 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,1,4,3 Level 3 Cx - Colo 4 | L3 XFMR - COLO4 | Interior - L3 MSB - COLO4 Cell 2 | 0
CHI05-04-01-L3-1710 | CHI05-04-03-L3-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,3,4,3 Level 3 Cx - Colo 4 | L3 XFMR - COLO4 | Interior - L3 MSB - COLO4 Cell 3 | 0
CHI05-04-01-L3-1710 | CHI05-04-04-L3-1990 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,2,2,4,3 Level 3 Cx - Colo 4 | L3 XFMR - COLO4 | Interior - L3 MSB - COLO4 Cell 4 | 0
CHI05-05-01-L3-1830 | CHI05-05-02-L3-1870 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,1,4,3 Level 3 Cx - Colo 5 | L3 XFMR - COLO5 | Interior - L3 MSB - COLO5 Cell 2 | 0
CHI05-05-01-L3-1830 | CHI05-05-03-L3-1990 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,3,4,3 Level 3 Cx - Colo 5 | L3 XFMR - COLO5 | Interior - L3 MSB - COLO5 Cell 3 | 0
CHI05-05-01-L3-1830 | CHI05-05-04-L3-2110 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | CHI05-PH2-FIT-BL-D5,3,3,3,2,4,3 Level 3 Cx - Colo 5 | L3 XFMR - COLO5 | Interior - L3 MSB - COLO5 Cell 4 | 0
CHI05-02-01-L2-1340 | CHI05-02-01-L3-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | CHI05-PH2-FIT-BL-D5,3,3,6,3 Level 3 Cx | L2 UPM - COLO2 | L3 UPM - COLO2 | 0
CHI05-YARD-2080 | CHI05-YARD-2270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | Install MV Gear - Colo 5 - East | Wire pulling and termination for MSB - Colo 5 - East | 0
CHI05-YARD-2490 | CHI05-YARD-2270 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | Install Generator - Colo 5 - East | Wire pulling and termination for MSB - Colo 5 - East | 0
CHI05-YARD-2130 | CHI05-YARD-2350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | Install Generator - Colo 2 - South | Wire pulling and termination for MSB - Colo 2 - South | 0
CHI05-YARD-2510 | CHI05-YARD-2350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | Install MV Gear - Colo 2 - South | Wire pulling and termination for MSB - Colo 2 - South | 0
CHI05-YARD-2530 | CHI05-YARD-2380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | Install Generator - Colo 3 - South | Wire pulling and termination for MSB - Colo 3 - South | 0
CHI05-YARD-2190 | CHI05-YARD-2380 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | Install MV Gear - Colo 3 - South | Wire pulling and termination for MSB - Colo 3 - South | 0
CHI05-YARD-2230 | CHI05-YARD-2420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | Install MV Gear - Colo 4 - South | Wire pulling and termination for MSB - Colo 4 - South | 0
CHI05-YARD-2550 | CHI05-YARD-2420 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | Install Generator - Colo 4 - South | Wire pulling and termination for MSB - Colo 4 - South | 0
CHI05-YARD-2030 | CHI05-YARD-2140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | Install Generator - Colo 2 - North | Wire pulling and termination for MSB - Colo 2 - North | 0
CHI05-YARD-2570 | CHI05-YARD-2140 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | Install MV Gear - Colo 2 - North | Wire pulling and termination for MSB - Colo 2 - North | 0
CHI05-YARD-2090 | CHI05-YARD-2260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | Install Generator - Colo 3 - North | Wire pulling and termination for MSB - Colo 3 - North | 0
CHI05-YARD-2590 | CHI05-YARD-2260 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | Install MV Gear - Colo 3 - North | Wire pulling and termination for MSB - Colo 3 - North | 0
CHI05-YARD-2110 | CHI05-YARD-2310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | Install MV Gear - Colo 4 - North | Wire pulling and termination for MSB - Colo 4 - North | 0
CHI05-YARD-2610 | CHI05-YARD-2310 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | Install Generator - Colo 4 - North | Wire pulling and termination for MSB - Colo 4 - North | 0
CHI05-YARD-2020 | CHI05-YARD-2150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | Install MV Gear - Colo 5 - West | Wire pulling and termination for MSB - Colo 5 - West | 0
CHI05-YARD-2630 | CHI05-YARD-2150 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | Install Generator - Colo 5 - West | Wire pulling and termination for MSB - Colo 5 - West | 0
CHI05-OFCI-1000 | CHI05-OFCI-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,1,1 AHU - COLO 2 | CHI05-PH2-FIT-BL-D5,4,1,1,3 AHU - COLO 4 | AHU - COLO 2 - In Storage | AHU - COLO 4 - Start ROJ | 0
CHI05-OFCI-1880 | CHI05-YARD-2070 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,10,5 UMS & URS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | UMS & URS - COLO 5 - In storage, needs modifications | Set the MV Gear - Colo 5 - East | 0
CHI05-OFCI-1880 | CHI05-YARD-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,10,5 UMS & URS - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | UMS & URS - COLO 5 - In storage, needs modifications | Set the MV Gear - Colo 5 - West | 0
CHI05-OFCI-1300 | CHI05-YARD-2500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,10,1 UMS & URS- COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | UMS & URS - COLO 2 - In storage, needs modifications | Set the MV Gear - Colo 2 - South | 0
CHI05-OFCI-1300 | CHI05-YARD-2560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,10,1 UMS & URS- COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | UMS & URS - COLO 2 - In storage, needs modifications | Set the MV Gear - Colo 2 - North | 0
CHI05-OFCI-1580 | CHI05-YARD-2170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,10,2 UMS & URS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | UMS & URS - COLO 3 - In storage, needs modifications | Set the MV Gear - Colo 3 - South | 0
CHI05-OFCI-1580 | CHI05-YARD-2580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,10,2 UMS & URS - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | UMS & URS - COLO 3 - In storage, needs modifications | Set the MV Gear - Colo 3 - North | 0
CHI05-OFCI-1720 | CHI05-YARD-2220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,10,3 UMS & URS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | UMS & URS - COLO 4 - In storage, needs modifications | Set the MV Gear - Colo 4 - South | 0
CHI05-OFCI-1720 | CHI05-YARD-2100 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,10,3 UMS & URS - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | UMS & URS - COLO 4 - In storage, needs modifications | Set the MV Gear - Colo 4 - North | 0
CHI05-05-NTP-S | CHI05-OFCI-1580 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,10,2 UMS & URS - COLO 3 | Notice To Proceed | UMS & URS - COLO 3 - In storage, needs modifications | 0
CHI05-05-NTP-S | CHI05-OFCI-1720 | SS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,2,2,1 General | CHI05-PH2-FIT-BL-D5,4,1,10,3 UMS & URS - COLO 4 | Notice To Proceed | UMS & URS - COLO 4 - In storage, needs modifications | 0
CHI05-OFCI-1250 | CHI05-YARD-2560 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,1 MVS (XFMR)- COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | MVS (XFMR) - COLO 2 - In storage | Set the MV Gear - Colo 2 - North | 0
CHI05-OFCI-1250 | CHI05-YARD-2500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,1 MVS (XFMR)- COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | MVS (XFMR) - COLO 2 - In storage | Set the MV Gear - Colo 2 - South | 0
CHI05-OFCI-1260 | CHI05-YARD-2170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,2 MVS (XFMR) - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | MVS (XFMR) - COLO 3 - In storage | Set the MV Gear - Colo 3 - South | 0
CHI05-OFCI-1260 | CHI05-YARD-2580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,2 MVS (XFMR) - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | MVS (XFMR) - COLO 3 - In storage | Set the MV Gear - Colo 3 - North | 0
CHI05-OFCI-1270 | CHI05-YARD-2220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,3 MVS (XFMR) - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | MVS (XFMR) - COLO 4 - In storage | Set the MV Gear - Colo 4 - South | 0
CHI05-OFCI-1270 | CHI05-YARD-2100 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,3 MVS (XFMR) - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | MVS (XFMR) - COLO 4 - In storage | Set the MV Gear - Colo 4 - North | 0
CHI05-OFCI-1550 | CHI05-YARD-2070 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,5 MVS (XFMR) - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | MVS (XFMR) - COLO 5 - Finish ROJ | Set the MV Gear - Colo 5 - East | 0
CHI05-OFCI-1550 | CHI05-YARD-2010 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,9,5 MVS (XFMR) - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | MVS (XFMR) - COLO 5 - Finish ROJ | Set the MV Gear - Colo 5 - West | 0
CHI05-CFCI-1020 | CHI05-OFCI-1880 | FS | Completed | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,4,1,10,5 UMS & URS - COLO 5 | HAC's - Submittal Preparation | UMS & URS - COLO 5 - In storage, needs modifications | 0
CHI05-CFCI-1020 | CHI05-OFCI-1280 | FS | Completed | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,2,1 HAC's | CHI05-PH2-FIT-BL-D5,4,1,9,5 MVS (XFMR) - COLO 5 | HAC's - Submittal Preparation | MVS (XFMR) - COLO 5 - Start ROJ | 0
CHI05-YARD-2500 | CHI05-02-01-L1-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 2 - South | L1 UPM - COLO2 | 0
CHI05-YARD-2560 | CHI05-02-01-L1-1220 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 2 - North | L1 UPM - COLO2 | 0
CHI05-YARD-2170 | CHI05-03-01-L1-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 3 - South | L1 UPM - COLO3 | 0
CHI05-YARD-2580 | CHI05-03-01-L1-1340 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 3 - North | L1 UPM - COLO3 | 0
CHI05-YARD-2220 | CHI05-04-01-L1-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 4 - South | L1 UPM - COLO4 | 0
CHI05-YARD-2100 | CHI05-04-01-L1-1460 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 4 - North | L1 UPM - COLO4 | 0
CHI05-YARD-2070 | CHI05-05-01-L1-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 5 - East | L1 UPM - COLO5 | 0
CHI05-YARD-2010 | CHI05-05-01-L1-1580 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 5 - West | L1 UPM - COLO5 | 0
CHI05-YARD-2070 | CHI05-05-01-L1-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 5 - East | L1 XFMR - MV- COLO5 | 0
CHI05-YARD-2500 | CHI05-02-01-L1-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 2 - South | L1 XFMR - MV- COLO2 | 0
CHI05-YARD-2560 | CHI05-02-01-L1-1230 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 2 - North | L1 XFMR - MV- COLO2 | 0
CHI05-YARD-2580 | CHI05-03-01-L1-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 3 - North | L1 XFMR - MV- COLO3 | 0
CHI05-YARD-2170 | CHI05-03-01-L1-1350 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 3 - South | L1 XFMR - MV- COLO3 | 0
CHI05-YARD-2010 | CHI05-05-01-L1-1590 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 5 - West | L1 XFMR - MV- COLO5 | 0
CHI05-YARD-2100 | CHI05-04-01-L1-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 4 - North | L1 XFMR - MV- COLO4 | 0
CHI05-YARD-2220 | CHI05-04-01-L1-1470 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | CHI05-PH2-FIT-BL-D5,3,3,6,1 Level 1 Cx | Set the MV Gear - Colo 4 - South | L1 XFMR - MV- COLO4 | 0
CHI05-OFCI-1890 | CHI05-YARD-2030 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,1 Mufflers - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,4,1 North Yard - Colo 2 | Mufflers - COLO 2 - Finish ROJ | Install Generator - Colo 2 - North | 0
CHI05-OFCI-1890 | CHI05-YARD-2130 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,1 Mufflers - COLO 2 | CHI05-PH2-FIT-BL-D5,3,3,4,2 South Yard - Colo 2 | Mufflers - COLO 2 - Finish ROJ | Install Generator - Colo 2 - South | 0
CHI05-OFCI-1900 | CHI05-YARD-2530 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,2 Mufflers - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,4,7 South Yard - Colo 3 | Mufflers - COLO 3 - Finish ROJ | Install Generator - Colo 3 - South | 0
CHI05-OFCI-1900 | CHI05-YARD-2090 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,2 Mufflers - COLO 3 | CHI05-PH2-FIT-BL-D5,3,3,4,5 North Yard - Colo 3 | Mufflers - COLO 3 - Finish ROJ | Install Generator - Colo 3 - North | 0
CHI05-OFCI-1910 | CHI05-YARD-2610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,3 Mufflers - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,4,6 North Yard - Colo 4 | Mufflers - COLO 4 - Finish ROJ | Install Generator - Colo 4 - North | 0
CHI05-OFCI-1910 | CHI05-YARD-2550 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,3 Mufflers - COLO 4 | CHI05-PH2-FIT-BL-D5,3,3,4,8 South Yard - Colo 4 | Mufflers - COLO 4 - Finish ROJ | Install Generator - Colo 4 - South | 0
CHI05-OFCI-1920 | CHI05-YARD-2490 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,5 Mufflers - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,4,9 East Yard - Colo 5 | Mufflers - COLO 5 - Finish ROJ | Install Generator - Colo 5 - East | 0
CHI05-OFCI-1920 | CHI05-YARD-2630 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,4,1,15,5 Mufflers - COLO 5 | CHI05-PH2-FIT-BL-D5,3,3,4,4 West Yard - Colo 5 | Mufflers - COLO 5 - Finish ROJ | Install Generator - Colo 5 - West | 0
CHI05-CON-1020 | CHI05-05-01-L2-1680 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,2 Utility Power Distribution | CHI05-PH2-FIT-BL-D5,3,3,6,2 Level 2 Cx | (3) UTS - Install and Terminate (1 wk/ea) | L2 UTS / UTSR - Site | 0
CHI05-05-01-ER-1370 | CHI05-05-01-ER-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,6,5 COLO 5 Cell 1 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 1 - ER | Installation of UPS Equipment - COLO5 Cell 1 - ER | 0
CHI05-05-02-ER-1480 | CHI05-05-02-ER-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,1,5 COLO 5 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 2 - ER | Installation of UPS Equipment - COLO5 Cell 2 - ER | 0
CHI05-05-03-ER-1590 | CHI05-05-03-ER-1610 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,3,5 COLO 5 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 3 - ER | Installation of UPS Equipment - COLO5 Cell 3 - ER | 0
CHI05-05-04-ER-1700 | CHI05-05-04-ER-1720 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,3,2,5 COLO 5 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO5 Cell 4 - ER | Installation of UPS Equipment - COLO5 Cell 4 - ER | 0
CHI05-02-01-ER-1040 | CHI05-02-01-ER-1070 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,6,5 COLO 2 Cell 1 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER | Installation of UPS Equipment - COLO2 Cell 1 - ER | 0
CHI05-02-03-ER-1260 | CHI05-02-03-ER-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,3,5 COLO 2 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 3 - ER | Installation of UPS Equipment - COLO2 Cell 3 - ER | 0
CHI05-02-04-ER-1370 | CHI05-02-04-ER-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,5,2,5 COLO 2 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO2 Cell 4 - ER | Installation of UPS Equipment - COLO2 Cell 4 - ER | 0
CHI05-03-01-ER-1150 | CHI05-03-01-ER-1170 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,6,5 COLO 3 Cell 1 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 1 - ER | Installation of UPS Equipment - COLO3 Cell 1 - ER | 0
CHI05-03-02-ER-1260 | CHI05-03-02-ER-1280 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,1,5 COLO 3 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | Installation of UPS Equipment - COLO3 Cell 2 - ER | 0
CHI05-03-03-ER-1370 | CHI05-03-03-ER-1390 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,3,5 COLO 3 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | Installation of UPS Equipment - COLO3 Cell 3 - ER | 0
CHI05-03-04-ER-1480 | CHI05-03-04-ER-1500 | FS | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,1,2,5 COLO 3 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | Installation of UPS Equipment - COLO3 Cell 4 - ER | 0
CHI05-04-01-ER-1260 | CHI05-04-01-ER-1280 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,6,5 COLO 4 Cell 1 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 1 - ER | Installation of UPS Equipment - COLO4 Cell 1 - ER | 0
CHI05-04-02-ER-1370 | CHI05-04-02-ER-1390 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,1,5 COLO 4 Cell 2 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | Installation of UPS Equipment - COLO4 Cell 2 - ER | 0
CHI05-04-03-ER-1480 | CHI05-04-03-ER-1500 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,3,5 COLO 4 Cell 3 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | Installation of UPS Equipment - COLO4 Cell 3 - ER | 0
CHI05-04-04-ER-1590 | CHI05-04-04-ER-1610 | FF | Not Started | Not Started | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5 | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | CHI05-PH2-FIT-BL-D5,3,3,2,2,5 COLO 4 Cell 4 Electrical And UPS Rooms | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | Installation of UPS Equipment - COLO4 Cell 4 - ER | 0

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=m/d/yyyy CurrencyFormat=Dollar