## Sheet1
PHASE | LOCATION | ZONE | TRADE | ACT NAME | COLOR | ACT CODE | START | FINISH
MAJOR MILESTONES | All | All | Manhattan | Notice to Proceed For Construction | #FFFF00 | MM | 02/03/25
MAJOR MILESTONES | East | East | Manhattan | East Building & Canopy Construction | #FFFF00 | MM | 02/18/25 | 07/28/26
MAJOR MILESTONES | East | East | Manhattan | Start of East Construction | #FFFF00 | MM | 02/18/25
MAJOR MILESTONES | West | West | Manhattan | Start of West Construction | #FFFF00 | MM | 05/18/26
MAJOR MILESTONES | West | West | Manhattan | West Building & Canopy Construction | #FFFF00 | MM | 05/18/26 | 12/01/27
MAJOR MILESTONES | East | East | Manhattan | East Side TCO | #FFFF00 | MM |  | 06/30/26
MAJOR MILESTONES | Phase 1 | Phase 1 | Manhattan | Phase 1 Substantial Completion | #FFFF00 | MM |  | 06/30/26
MAJOR MILESTONES | North | North | Manhattan | Start of North Construction | #FFFF00 | MM | 07/22/26
MAJOR MILESTONES | North | North | Manhattan | North Ticket Construction | #FFFF00 | MM | 07/22/26 | 11/29/27
MAJOR MILESTONES | North | North | Manhattan | North Endzone Completion | #FFFF00 | MM |  | 11/29/27
MAJOR MILESTONES | West | West | Manhattan | West Side TCO | #FFFF00 | MM |  | 12/01/27
MAJOR MILESTONES | Phase 2 | Phase 2 | Manhattan | Phase 2 Substantial Completion | #FFFF00 | MM |  | 12/01/27
MAJOR MILESTONES | All | All | Manhattan | Close-out & Final Billings | #FFFF00 | MM | 12/02/27 | 02/04/28
MAJOR MILESTONES | All | All | Manhattan | Final Completion | #FFFF00 | MM |  | 02/04/28
SCHEMATIC DESIGN | Design | Design | Architect | Schematic Design-Full Project (Architecture and Structure) | #153D64 | SC | 11/27/23A | 04/01/24A
SCHEMATIC DESIGN | Design | Design | Architect | SDs Pricing and Budget Reviews | #153D64 | SC | 04/02/24A | 04/08/24A
DESIGN DEVELOPMENT | Design | Design | Architect | Design Development 50% | #153D64 | DD | 04/09/24A | 04/26/24A
DESIGN DEVELOPMENT | Design | Design | Architect | Design Development 50% Pricing to Review | #153D64 | DD | 04/29/24A | 05/17/24A
DESIGN DEVELOPMENT | Design | Design | Architect | Design Development 100% | #153D64 | DD | 04/29/24A | 06/21/24A
DESIGN DEVELOPMENT | Design | Design | Architect | Preliminary SteelTonnage Package | #153D64 | DD | 04/29/24A | 06/21/24A
DESIGN DEVELOPMENT | Design | Design | Architect | SteelTonnage Package | #153D64 | DD | 06/24/24A | 08/30/24A
DESIGN DEVELOPMENT | Design | Design | Architect | DDs Pricing and Budget Reviews | #153D64 | DD | 06/24/24A | 07/22/24A
PERMIT PACKAGE | Steel | Steel | Manhattan | SteelPackage (Primary Structural Framing) | #FFFF00 | PP | 05/31/24A | 08/30/24A
PERMIT PACKAGE | Canopy | Canopy | Manhattan | Canopy Structure SteelPackage | #FFFF00 | PP | 05/31/24A | 08/30/24A
PERMIT PACKAGE | Foundations | Foundations | Manhattan | Foundations Package (West and Northwest Building) Permit | #FFFF00 | PP | 05/31/24A | 08/30/24A
PERMIT PACKAGE | Civil | Civil | Manhattan | Civil Package (includes duct bank, fire lane, site perimeter u | #FFFF00 | PP | 05/31/24A | 08/30/24A
PERMIT PACKAGE | Permit | Permit | Manhattan | Early Permit Packages - Never Issued, Merged with C&S Pac | #FFFF00 | PP | 09/02/24A | 11/01/24
CONSTRUCTION DOCUMENTS | Documents | Documents | Manhattan | Core and Shell / Permit / Demolition Package | #FFFF00 | CD | 06/24/24A | 11/01/24
CONSTRUCTION DOCUMENTS | Documents | Documents | Manhattan | CoServ Relocation Designs & Approvals (Elect & Gas) | #FFFF00 | CD | 11/04/24 | 01/30/25
CONSTRUCTION DOCUMENTS | Documents | Documents | Manhattan | Interiors Finish Out Package | #FFFF00 | CD | 11/04/24 | 01/31/25
CONSTRUCTION DOCUMENTS | Documents | Documents | Manhattan | ASI-01 Issued | #FFFF00 | CD | 11/15/24 | 11/15/24
CONSTRUCTION DOCUMENTS | Documents | Documents | Manhattan | ASI-02 Issued | #FFFF00 | CD | 11/22/24 | 11/22/24
CONSTRUCTION DOCUMENTS | Documents | Documents | Manhattan | ASI-03 Issued | #FFFF00 | CD | 12/18/24 | 12/18/24
CONSTRUCTION DOCUMENTS | Documents | Documents | Manhattan | ASI-04 Issued | #FFFF00 | CD | 01/09/25 | 01/09/25
CONSTRUCTION DOCUMENTS | Documents | Documents | Manhattan | ASI-05 Issued | #FFFF00 | CD | 01/13/25 | 01/13/25
PERMITS | East | East | Manhattan | East-North Site Plans - City Review | #FFFF00 | PT | 09/09/24A | 11/04/24
PERMITS | East | East | Manhattan | East-North LS Plans - City Review | #FFFF00 | PT | 09/10/24A | 11/04/24
PERMITS | East | East | Manhattan | East-North Civil - City Engineering Review | #FFFF00 | PT | 11/11/24 | 12/11/24
PERMITS | West | West | Manhattan | West Site & LS Plans - Submittal Package for City Review | #FFFF00 | PT | 11/11/24 | 12/16/24
PERMITS | Facade | Facade | Manhattan | Facade - Submittal Package for City Review | #FFFF00 | PT | 11/11/24 | 12/16/24
PERMITS | East | East | Manhattan | East-North Civil - Comment Review & Resubmittal | #FFFF00 | PT | 12/12/24 | 12/17/24
PERMITS | West | West | Manhattan | West Site & LS Plans - City Review | #FFFF00 | PT | 12/16/24 | 12/23/24
PERMITS | Facade | Facade | Manhattan | Facade (all sides) - City Review | #FFFF00 | PT | 12/16/24 | 12/23/24
PERMITS | East | East | Manhattan | East-North Civil - City Engineering Re-Review | #FFFF00 | PT | 12/18/24 | 01/09/25
PERMITS | West | West | Manhattan | West Site & LS Plans - Comment Review & Resubmittal | #FFFF00 | PT | 12/24/24 | 01/14/25
PERMITS | Facade | Facade | Manhattan | Facade (all sides) - Comment Review & Resubmittal | #FFFF00 | PT | 12/24/24 | 01/14/25
PERMITS | East | East | Manhattan | East-North Civil - Comment Review & Resubmittal 2 | #FFFF00 | PT | 01/10/25 | 01/21/25
PERMITS | All | All | Manhattan | Building Permit (East Demo) - Review & Approval | #FFFF00 | PT | 01/13/25 | 01/14/25
PERMITS | West | West | Manhattan | West Site & LS Plans - City Re-Review | #FFFF00 | PT | 01/15/25 | 01/28/25
PERMITS | Facade | Facade | Manhattan | Facade (all sides) - City Re-Review | #FFFF00 | PT | 01/15/25 | 01/28/25
PERMITS | East | East | Manhattan | East-North Civil - City Engineering Re-Review 2 | #FFFF00 | PT | 01/22/25 | 02/11/25
PERMITS | West | West | Manhattan | West Civil - Submittal Package for City Engineering Review | #FFFF00 | PT | 01/29/25 | 02/04/25
PERMITS | West | West | Manhattan | West Civil - City Engineering Review | #FFFF00 | PT | 02/05/25 | 02/18/25
PERMITS | East | East | Manhattan | Building Permit (East) - Review & Approval | #FFFF00 | PT | 02/05/25 | 02/25/25
PERMITS | West | West | Manhattan | Building Permit (West) - Review & Approval | #FFFF00 | PT | 02/26/25 | 03/18/25
Procurement | Material | Material | Manhattan | Core & Shell Bid Package Prep | #FFFF00 | PR | 11/04/24 | 11/08/24
Procurement | Material | Material | Manhattan | Canopy Bidding | #FFFF00 | PR | 11/11/24 | 01/06/25
Procurement | Material | Material | Manhattan | Foundations Bidding | #FFFF00 | PR | 11/11/24 | 01/06/25
Procurement | Material | Material | Manhattan | Structural SteelBidding | #FFFF00 | PR | 11/11/24 | 01/06/25
Procurement | Material | Material | Manhattan | Remaining Core & Shell Bidding | #FFFF00 | PR | 11/11/24 | 01/06/25
Procurement | Material | Material | Manhattan | Bid Day pushed by HSG (Impact) | #FFFF00 | PR | 01/07/25 | 01/15/25
Procurement | Material | Material | Manhattan | Bid Opening pushed by HSG & COF (Impact) | #FFFF00 | PR | 01/16/25 | 01/21/25
Procurement | Material | Material | Manhattan | Bid Review and Leveling | #FFFF00 | PR | 01/22/25 | 01/27/25
Procurement | Material | Material | Manhattan | Review/Award CMaR | #FFFF00 | PR | 01/28/25 | 01/31/25
Procurement | Material | Material | Manhattan | Canopy Contract Award | #FFFF00 | PR | 02/03/25 | 02/07/25
Procurement | Material | Material | Manhattan | Foundations Contract Award | #FFFF00 | PR | 02/03/25 | 02/07/25
Procurement | Material | Material | Manhattan | Structural Steel | #FFFF00 | PR | 02/03/25 | 02/07/25
Procurement | Material | Material | Manhattan | MEP Make-Safe Contract Award | #FFFF00 | PR | 02/03/25 | 02/14/25
Procurement | Material | Material | Manhattan | Demo Contract Award | #FFFF00 | PR | 02/03/25 | 02/14/25
Procurement | Material | Material | Manhattan | Interior Finishes Bidding | #FFFF00 | PR | 02/03/25 | 02/18/25
Procurement | Material | Material | Manhattan | Execute Core & Shell Contracts | #FFFF00 | PR | 02/03/25 | 02/28/25
Procurement | Material | Material | Manhattan | Execute Elevator Subcontract | #FFFF00 | PR | 02/03/25 | 02/21/25
Procurement | Material | Material | Manhattan | Issue LNTPs for Demo/Foundations/Steel/Canopies/MEP | #FFFF00 | PR | 02/03/25 | 02/04/25
Procurement | Material | Material | Manhattan | FGMP Submittal & Amendment | #FFFF00 | PR | 02/19/25 | 02/21/25
Procurement | Material | Material | Manhattan | Execute Finish Subcontracts | #FFFF00 | PR | 02/24/25 | 04/25/25
Procurement | Foundations | Foundations | Manhattan | Submit Shop Drawings for Review | #FFFF00 | PR | 02/05/25 | 03/04/25
Procurement | Foundations | Foundations | Manhattan | Review Shop Drawings for Approval | #FFFF00 | PR | 03/05/25 | 03/18/25
Procurement | Foundations | Foundations | Manhattan | Fabrication/Delivery | #FFFF00 | PR | 03/19/25 | 04/08/25
Procurement | Structural Steel | Structural Steel | Manhattan | Submit Shop Drawings for Review | #FFFF00 | PR | 02/05/25 | 04/15/25
Procurement | Structural Steel | Structural Steel | Manhattan | Structural SteelProcurement | #FFFF00 | PR | 02/12/25 | 05/20/25
Procurement | Structural Steel | Structural Steel | Manhattan | Metal Decking Procurement | #FFFF00 | PR | 02/12/25 | 05/28/25
Procurement | Structural Steel | Structural Steel | Manhattan | Review Shop Drawings for Approval | #FFFF00 | PR | 04/16/25 | 05/06/25
Procurement | Structural Steel | Structural Steel | Manhattan | Fabrication/Delivery | #FFFF00 | PR | 05/21/25 | 07/31/25
Procurement | Canopies | Canopies | Manhattan | Canopy Submittals by Trade Partner | #FFFF00 | PR | 04/16/25 | 06/11/25
Procurement | Canopies | Canopies | Manhattan | Review Shop Drawings for Approval | #FFFF00 | PR | 06/12/25 | 07/02/25
Procurement | Canopies | Canopies | Manhattan | PTFE Fabrication Drawings | #FFFF00 | PR | 07/03/25 | 09/26/25
Procurement | Canopies | Canopies | Manhattan | PTFE Procurement | #FFFF00 | PR | 07/03/25 | 09/26/25
Procurement | Canopies | Canopies | Manhattan | PTFE Frabrication | #FFFF00 | PR | 09/29/25 | 03/20/26
Procurement | Canopies | Canopies | Manhattan | Start of Shipping PTFE Fabric to Site | #FFFF00 | PR | 03/23/26 | 04/17/26
Procurement | Vertical | Vertical | Manhattan | Elevator Shop Drawings Submittal | #FFFF00 | PR | 02/24/25 | 04/04/25
Procurement | Vertical | Vertical | Manhattan | West Elevator Shop Drawings Submittal | #FFFF00 | PR | 01/23/26 | 03/05/26
Procurement | Vertical | Vertical | Manhattan | Review Shop Drawings for Approval | #FFFF00 | PR | 03/06/26 | 03/26/26
Procurement | Vertical | Vertical | Manhattan | Fabrication/Delivery | #FFFF00 | PR | 03/27/26 | 10/27/26
Procurement | MEP/LV | MEP/LV | Manhattan | Sports Lighting Shop Drawings Submittal | #FFFF00 | PR | 03/03/25 | 05/02/25
Procurement | MEP/LV | MEP/LV | Manhattan | Generator Submittals | #FFFF00 | PR | 03/03/25 | 03/21/25
Procurement | MEP/LV | MEP/LV | Manhattan | Generator Submittal Review | #FFFF00 | PR | 03/24/25 | 04/11/25
Procurement | MEP/LV | MEP/LV | Manhattan | Generator Procurement | #FFFF00 | PR | 04/14/25 | 08/05/25
Procurement | MEP/LV | MEP/LV | Manhattan | Sports Lighting Submittal Review | #FFFF00 | PR | 05/05/25 | 05/23/25
Procurement | MEP/LV | MEP/LV | Manhattan | Sports Lighting Procurement | #FFFF00 | PR | 05/27/25 | 08/19/25
Procurement | Interiors | Interiors | Manhattan | Stone/Tile Submittals | #FFFF00 | PR | 04/28/25 | 06/09/25
Procurement | Interiors | Interiors | Manhattan | Stone/Tile Procurement | #FFFF00 | PR | 06/10/25 | 09/02/25
Procurement | Interiors | Interiors | Manhattan | Monumental Stair - Field Measure & Fabricate | #FFFF00 | PR | 10/28/26 | 01/04/27
MILESTONES/HAMMOCKS | Structure | Structure | Manhattan | East Structure Complete | #FFFF00 | M/H |  | 10/02/25
MILESTONES/HAMMOCKS | Dry-in | Dry-in | Manhattan | East Building Dry-in | #FFFF00 | M/H |  | 11/06/25
MILESTONES/HAMMOCKS | Conditioned Air | Conditioned Air | Manhattan | East Building Conditioned Air | #FFFF00 | M/H |  | 01/21/26
MILESTONES/HAMMOCKS | TCO | TCO | Manhattan | East Building TCO (excluding Canopy) | #FFFF00 | M/H |  | 06/30/26
MILESTONES/HAMMOCKS | Canopy | Canopy | Manhattan | East Canopy Installation Complete | #FFFF00 | M/H |  | 07/28/26
CIVIL/SITE | East | East | Underground Utilities | Site Utilities | #C36CEE | U1 | 04/07/25 | 06/16/25
CIVIL/SITE | East | East | Underground Utilities | Relocate Existing CoServ Lines | #C36CEE | U2 | 05/19/25 | 06/16/25
CIVIL/SITE | East | East | Paving | Install Fire Lane Base Course | #83CCEB | A1 | 06/17/25 | 07/15/25
CIVIL/SITE | East | East | Hardscape/Landscape | Hardscape/Landscape | #F29744 | HL1 | 11/20/25 | 03/11/26
DEMOLITION | East | East | Telecommunications | FC Dallas IT & Cell/DAS Equipment Removed/Relocated | #7030A0 | T1 | 01/07/25 | 02/03/25
DEMOLITION | East | East | Manhattan | Project Mobilization | #FFFF00 | MH1 | 02/04/25 | 02/17/25
DEMOLITION | East | East | MEP | Trace/Tag/Make Safe MEP Systems | #7CEE2E | I1 | 02/26/25 | 03/11/25
DEMOLITION | East | East | Demolition | Precision Demo & Temp Protection | #000000 | O1 | 03/05/25 | 03/18/25
DEMOLITION | East | East | Demolition | Mass Demolition-Excavation | #000000 | O2 | 03/17/25 | 04/04/25
FOUNDATIONS | Main building - Concourse Level | SEQ.1 | Concrete | Drilled Piers | #595959 | C1 | 04/15/25 | 04/17/25
FOUNDATIONS | Main building - Concourse Level | SEQ.1 | Concrete | Pier Caps - Excavate/FRP | #595959 | C2 | 04/18/25 | 04/23/25
FOUNDATIONS | Main building - Concourse Level | SEQ.1 | Concrete | Grade Beams - Excavate/FRP | #595959 | C3 | 04/18/25 | 04/24/25
FOUNDATIONS | Main building - Concourse Level | SEQ.1 | Steel | Camera Platform | #DBD997 | S1 | 04/25/25 | 05/07/25
FOUNDATIONS | Main building - Concourse Level | SEQ.1 | Plumbing | Plumbing Underground | #90EE90 | P1 | 04/25/25 | 05/01/25
FOUNDATIONS | Main building - Concourse Level | SEQ.1 | Electrical | Electrical Underground | #0000FF | E1 | 05/02/25 | 05/08/25
FOUNDATIONS | Main building - Concourse Level | SEQ.1 | Concrete | Seating Bowl Infill | #595959 | C4 | 05/08/25 | 05/14/25
FOUNDATIONS | Main building - Concourse Level | SEQ.1 | Concrete | Slab on Grade - Flex Cap/Fine Grade | #595959 | C5 | 05/09/25 | 05/15/25
FOUNDATIONS | Main building - Concourse Level | SEQ.1 | Concrete | Slab on Grade - FRP | #595959 | C6 | 05/16/25 | 05/22/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Concrete | Drilled Piers | #595959 | C1 | 04/18/25 | 04/24/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Concrete | Elevator Pit - Excavate/FRP | #595959 | C7 | 04/25/25 | 05/06/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Concrete | Pier Caps - Excavate/FRP | #595959 | C2 | 04/25/25 | 04/30/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Concrete | Grade Beams - Excavate/FRP | #595959 | C3 | 04/28/25 | 05/07/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Waterproofing | Elevator Pit - Waterproofing | #742264 | W1 | 05/07/25 | 05/08/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Plumbing | Plumbing Underground | #90EE90 | P1 | 05/08/25 | 05/14/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Earthworks | Elevator Pit - Subsoil/Backfill | #ADADAD | K1 | 05/09/25 | 05/13/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Electrical | Electrical Underground | #0000FF | E1 | 05/09/25 | 05/15/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Concrete | Seating Bowl Infill | #595959 | C4 | 05/15/25 | 05/21/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Concrete | Slab on Grade - Flex Cap/Fine Grade | #595959 | C5 | 05/16/25 | 05/22/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Concrete | Slab on Grade - FRP | #595959 | C6 | 05/23/25 | 05/30/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Concrete | Drilled Piers | #595959 | C1 | 04/25/25 | 04/30/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Concrete | Grade Beams - Excavate/FRP | #595959 | C3 | 05/08/25 | 05/16/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Concrete | Pier Caps - Excavate/FRP | #595959 | C2 | 05/13/25 | 05/16/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Plumbing | Plumbing Underground | #90EE90 | P1 | 05/19/25 | 05/23/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Concrete | Seating Bowl Infill | #595959 | C4 | 05/22/25 | 05/29/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Electrical | Electrical Underground | #0000FF | E1 | 05/27/25 | 06/02/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Concrete | Slab on Grade - Flex Cap/Fine Grade | #595959 | C5 | 06/03/25 | 06/09/25
FOUNDATIONS | Main building - Concourse Level | SEQ.2 | Concrete | Slab on Grade - FRP | #595959 | C6 | 06/10/25 | 06/16/25
FOUNDATIONS | Main building - Concourse Level | SEQ.3 | Concrete | Drilled Piers | #595959 | C1 | 05/01/25 | 05/07/25
FOUNDATIONS | Main building - Concourse Level | SEQ.3 | Concrete | Elevator Pit - Excavate/FRP | #595959 | C7 | 05/19/25 | 05/29/25
FOUNDATIONS | Main building - Concourse Level | SEQ.3 | Concrete | Pier Caps - Excavate/FRP | #595959 | C2 | 05/19/25 | 05/22/25
FOUNDATIONS | Main building - Concourse Level | SEQ.3 | Concrete | Grade Beams - Excavate/FRP | #595959 | C3 | 05/20/25 | 05/30/25
FOUNDATIONS | Main building - Concourse Level | SEQ.3 | Waterproofing | Elevator Pit - Waterproofing | #742264 | W1 | 05/30/25 | 06/02/25
FOUNDATIONS | Main building - Concourse Level | SEQ.3 | Concrete | Seating Bowl Infill | #595959 | C4 | 06/02/25 | 06/06/25
FOUNDATIONS | Main building - Concourse Level | SEQ.3 | Plumbing | Plumbing Underground | #90EE90 | P1 | 06/02/25 | 06/06/25
FOUNDATIONS | Main building - Concourse Level | SEQ.3 | Earthworks | Elevator Pit - Subsoil/Backfill | #ADADAD | K1 | 06/03/25 | 06/05/25
FOUNDATIONS | Main building - Concourse Level | SEQ.3 | Electrical | Electrical Underground | #0000FF | E1 | 06/09/25 | 06/13/25
FOUNDATIONS | Main building - Concourse Level | SEQ.3 | Concrete | Slab on Grade - Flex Cap/Fine Grade | #595959 | C5 | 06/16/25 | 06/20/25
FOUNDATIONS | Main building - Concourse Level | SEQ.3 | Concrete | Slab on Grade - FRP | #595959 | C6 | 06/23/25 | 06/27/25
FOUNDATIONS | Main building - Concourse Level | SEQ.4 | Concrete | Drilled Piers | #595959 | C1 | 05/08/25 | 05/09/25
FOUNDATIONS | Main building - Concourse Level | SEQ.4 | Concrete | Pier Caps - Excavate/FRP | #595959 | C2 | 05/30/25 | 06/04/25
FOUNDATIONS | Main building - Concourse Level | SEQ.4 | Concrete | Grade Beams - Excavate/FRP | #595959 | C3 | 06/02/25 | 06/05/25
FOUNDATIONS | Main building - Concourse Level | SEQ.4 | Steel | Camera Platform | #DBD997 | S1 | 06/06/25 | 06/18/25
FOUNDATIONS | Main building - Concourse Level | SEQ.4 | Plumbing | Plumbing Underground | #90EE90 | P1 | 06/09/25 | 06/13/25
FOUNDATIONS | Main building - Concourse Level | SEQ.4 | Electrical | Electrical Underground | #0000FF | E1 | 06/16/25 | 06/20/25
FOUNDATIONS | Main building - Concourse Level | SEQ.4 | Concrete | Seating Bowl Infill | #595959 | C4 | 06/19/25 | 06/25/25
FOUNDATIONS | Main building - Concourse Level | SEQ.4 | Concrete | Slab on Grade - Flex Cap/Fine Grade | #595959 | C5 | 06/23/25 | 06/27/25
FOUNDATIONS | Main building - Concourse Level | SEQ.4 | Concrete | Slab on Grade - FRP | #595959 | C6 | 06/30/25 | 07/07/25
FOUNDATIONS | Concession Wings | Concession Wings | Concrete | Drilled Piers | #595959 | C1 | 05/12/25 | 05/16/25
FOUNDATIONS | Concession Wings | Concession Wings | Concrete | Grade Beams - Excavate/FRP | #595959 | C3 | 05/19/25 | 06/09/25
FOUNDATIONS | Concession Wings | Concession Wings | Concrete | Drilled Piers | #595959 | C1 | 05/19/25 | 05/23/25
FOUNDATIONS | Concession Wings | Concession Wings | Plumbing | Plumbing Underground | #90EE90 | P1 | 06/10/25 | 06/23/25
FOUNDATIONS | Concession Wings | Concession Wings | Concrete | Grade Beams - Excavate/FRP | #595959 | C3 | 06/10/25 | 07/03/25
FOUNDATIONS | Concession Wings | Concession Wings | Electrical | Electrical Underground | #0000FF | E1 | 06/17/25 | 06/30/25
FOUNDATIONS | Concession Wings | Concession Wings | Concrete | Slab on Grade - Rock/Fine Grade/FRP | #595959 | C5 | 07/01/25 | 07/22/25
FOUNDATIONS | Concession Wings | Concession Wings | Plumbing | Plumbing Underground | #90EE90 | P1 | 07/07/25 | 07/18/25
FOUNDATIONS | Concession Wings | Concession Wings | Electrical | Electrical Underground | #0000FF | E1 | 07/14/25 | 07/25/25
FOUNDATIONS | Concession Wings | Concession Wings | Concrete | Slab on Grade - Rock/Fine Grade/FRP | #595959 | C6 | 07/28/25 | 08/15/25
FOUNDATIONS | Northeast | Northeast | Earthworks | Excavate NE building footprint | #ADADAD | K2 | 07/01/25 | 07/03/25
FOUNDATIONS | Northeast | Northeast | Concrete | Lower Grade Beam at Piers | #595959 | C8 | 07/07/25 | 07/11/25
FOUNDATIONS | Northeast | Northeast | Concrete | South Grade Beam | #595959 | C8 | 07/14/25 | 07/18/25
FOUNDATIONS | Northeast | Northeast | Concrete | FRP Walls & Pilasters | #595959 | C9 | 07/21/25 | 07/25/25
FOUNDATIONS | Northeast | Northeast | Concrete | Upper Grade Beam | #595959 | C8 | 07/28/25 | 08/04/25
FOUNDATIONS | Northeast | Northeast | Geofom | Geofoam Install | #FFC000 | G1 | 08/05/25 | 08/11/25
FOUNDATIONS | Northeast | Northeast | MEP | MEP Underground | #7CEE2E | I2 | 08/12/25 | 08/21/25
FOUNDATIONS | Northeast | Northeast | Concrete | FRP Slab on Grade | #595959 | C6 | 08/22/25 | 08/26/25
STRUCTURE | Main building - All | SEQ. 1E | Steel | Erect Structural Steel | #DBD997 | S2 | 07/03/25 | 07/09/25
STRUCTURE | Main building - All | SEQ. 1E | Decking | Detailing & Decking Steel | #F836B7 | D1 | 07/14/25 | 07/17/25
STRUCTURE | Main building - All | SEQ. 2E | Steel | Erect Structural Steel | #DBD997 | S2 | 07/09/25 | 07/16/25
STRUCTURE | Main building - All | SEQ. 2E | Decking | Detailing & Decking Steel | #F836B7 | D1 | 07/18/25 | 07/25/25
STRUCTURE | Main building - All | SEQ. 3E | Steel | Erect Structural Steel | #DBD997 | S2 | 07/16/25 | 07/23/25
STRUCTURE | Main building - All | SEQ. 3E | Decking | Detailing & Decking Steel | #F836B7 | D1 | 07/28/25 | 08/04/25
STRUCTURE | Main building - All | SEQ. 4E | Steel | Erect Structural Steel | #DBD997 | S2 | 07/23/25 | 07/30/25
STRUCTURE | Main building - All | SEQ. 4E | Decking | Detailing & Decking Steel | #F836B7 | D1 | 08/05/25 | 08/12/25
STRUCTURE | Main building - All | SEQ. 5E | Steel | Erect Structural Steel | #DBD997 | S2 | 07/30/25 | 08/04/25
STRUCTURE | Main building - All | SEQ. 5E | Decking | Detailing & Decking Steel | #F836B7 | D1 | 08/13/25 | 08/18/25
STRUCTURE | Main building - Lower Suite Level | SEQ. 1E | MEP | MEP In-slab Rough-in | #7CEE2E | I3 | 07/21/25 | 07/25/25
STRUCTURE | Main building - Lower Suite Level | SEQ. 1E | Concrete | FRP SOMD | #595959 | C10 | 07/28/25 | 08/01/25
STRUCTURE | Main building - Lower Suite Level | SEQ. 2E | MEP | MEP In-slab Rough-in | #7CEE2E | I3 | 07/28/25 | 08/01/25
STRUCTURE | Main building - Lower Suite Level | SEQ. 2E | Concrete | FRP SOMD | #595959 | C10 | 08/04/25 | 08/08/25
STRUCTURE | Main building - Lower Suite Level | SEQ. 3E | MEP | MEP In-slab Rough-in | #7CEE2E | I3 | 08/05/25 | 08/11/25
STRUCTURE | Main building - Lower Suite Level | SEQ. 3E | Concrete | FRP SOMD | #595959 | C10 | 08/12/25 | 08/19/25
STRUCTURE | Main building - Lower Suite Level | SEQ. 4E | MEP | MEP In-slab Rough-in | #7CEE2E | I3 | 08/13/25 | 08/19/25
STRUCTURE | Main building - Lower Suite Level | SEQ. 4E | Concrete | FRP SOMD | #595959 | C10 | 08/20/25 | 08/27/25
STRUCTURE | Main building - Lower Suite Level | SEQ. 5E | MEP | MEP In-slab Rough-in | #7CEE2E | I3 | 08/20/25 | 08/26/25
STRUCTURE | Main building - Lower Suite Level | SEQ. 5E | Concrete | FRP SOMD | #595959 | C10 | 08/28/25 | 09/03/25
STRUCTURE | Main building - Roof Level | SEQ. 1E | Steel | Erect Canopy Steel | #DBD997 | S3 | 08/07/25 | 08/18/25
STRUCTURE | Main building - Roof Level | SEQ. 2E | Steel | Erect Canopy Steel | #DBD997 | S3 | 08/19/25 | 08/28/25
STRUCTURE | Main building - Roof Level | SEQ. 3E | MEP | MEP In-slab Rough-in | #7CEE2E | I3 | 08/05/25 | 08/11/25
STRUCTURE | Main building - Roof Level | SEQ. 3E | Steel | Erect Canopy Steel | #DBD997 | S3 | 08/29/25 | 09/10/25
STRUCTURE | Main building - Roof Level | SEQ. 4E | Steel | Erect Canopy Steel | #DBD997 | S3 | 09/11/25 | 09/22/25
STRUCTURE | Main building - Roof Level | SEQ. 5E | Steel | Erect Canopy Steel | #DBD997 | S3 | 09/23/25 | 10/02/25
STRUCTURE | Concession Wings | North | Steel | Concession Building Steel(Steel/Joist/Deck) - North | #DBD997 | S4 | 08/05/25 | 08/18/25
STRUCTURE | Concession Wings | South | Steel | Concession Building Steel(Steel/Joist/Deck) - South | #DBD997 | S4 | 08/19/25 | 09/01/25
STRUCTURE | Northeast | Northeast | Steel | Erect NE Concourse Structure | #DBD997 | S5 | 09/02/25 | 09/04/25
STRUCTURE | Northeast | Northeast | Steel | Detail/Misc Steel- NE | #DBD997 | S6 | 09/05/25 | 09/16/25
CANOPIES | Main building | Main building | Electrical | Install Bowl Speakers/Stadium Lights | #0000FF | E2 | 10/03/25 | 12/30/25
CANOPIES | Main building | Main building | Steel | Install Canopy Fabric | #DBD997 | S7 | 04/20/26 | 06/29/26
CANOPIES | Main building | Main building | Steel | Canopy Punch/Closeout | #DBD997 | S8 | 06/30/26 | 07/28/26
EXTERIORS | Main building | Main building | Manhattan | MCC Completion List - Prepare/Distribute/Complete | #FFFF00 | MH2 | 03/11/26 | 03/24/26
EXTERIORS | Main building | Main building | Manhattan | Design Team Punchlist - Prepare/Distribute/Complete | #FFFF00 | MH3 | 03/25/26 | 04/07/26
EXTERIORS | Concourse Level | South | Framing | Exterior Framing and Sheathing - South | #8B4513 | F1 | 09/04/25 | 09/18/25
EXTERIORS | Concourse Level | South | Specialty | Install Stainless Counters | #26EAB2 | Y1 | 09/19/25 | 09/22/25
EXTERIORS | Concourse Level | South | Waterproofing | Install Air/Water Barrier | #742264 | W2 | 09/19/25 | 09/23/25
EXTERIORS | Concourse Level | South | Masonry | Install Masonry Veneer | #E52F2F | R1 | 09/24/25 | 10/28/25
EXTERIORS | Concourse Level | South | Glazing | Install Curtainwall | #C1F0C8 | Z1 | 10/24/25 | 11/06/25
EXTERIORS | Concourse Level | South | Glazing | Install Storefront (Bowl side) | #C1F0C8 | Z2 | 11/07/25 | 11/13/25
EXTERIORS | Concourse Level | South | Carpentry | Frame Soffit | #4F9EDF | T1 | 11/14/25 | 12/01/25
EXTERIORS | Concourse Level | South | Fire Sprinkler | Install Fire Sprinkler | #AD1DC1 | H1 | 12/02/25 | 12/08/25
EXTERIORS | Concourse Level | South | Electrical | Install Electrical/LV | #0000FF | E3 | 12/02/25 | 12/15/25
EXTERIORS | Concourse Level | South | Insulation | Spray Insulation | #BE5014 | J1 | 12/16/25 | 12/26/25
EXTERIORS | Concourse Level | South | Carpentry | Close Soffit | #4F9EDF | T2 | 12/29/25 | 01/05/26
EXTERIORS | Concourse Level | South | Metal Panels | Install Soffit Metal Panels | #EB7994 | MP1 | 02/04/26 | 03/03/26
EXTERIORS | Concourse Level | South | Electrical | Trim-out Devices | #0000FF | E4 | 03/04/26 | 03/10/26
EXTERIORS | Concourse Level | North | Framing | Exterior Framing and Sheathing - North | #8B4513 | F1 | 08/11/25 | 08/22/25
EXTERIORS | Concourse Level | North | Specialty | Install Stainless Counters | #26EAB2 | Y1 | 08/25/25 | 08/26/25
EXTERIORS | Concourse Level | North | Waterproofing | Install Air/Water Barrier | #742264 | W2 | 08/25/25 | 08/27/25
EXTERIORS | Concourse Level | North | Masonry | Install Masonry Veneer | #E52F2F | R1 | 08/28/25 | 10/02/25
EXTERIORS | Concourse Level | North | Glazing | Install Storefront (Bowl side) | #C1F0C8 | Z2 | 10/03/25 | 10/09/25
EXTERIORS | Concourse Level | North | Carpentry | Frame Soffit | #4F9EDF | T1 | 10/10/25 | 10/23/25
EXTERIORS | Concourse Level | North | Glazing | Install Curtainwall | #C1F0C8 | Z1 | 10/10/25 | 10/23/25
EXTERIORS | Concourse Level | North | Fire Sprinkler | Install Fire Sprinkler | #AD1DC1 | H1 | 10/24/25 | 10/30/25
EXTERIORS | Concourse Level | North | Electrical | Install Electrical/LV | #0000FF | E3 | 10/24/25 | 11/06/25
EXTERIORS | Concourse Level | North | Insulation | Spray Insulation | #BE5014 | J1 | 11/07/25 | 11/18/25
EXTERIORS | Concourse Level | North | Carpentry | Close Soffit | #4F9EDF | T2 | 11/19/25 | 11/25/25
EXTERIORS | Concourse Level | North | Metal Panels | Install Soffit Metal Panels | #EB7994 | MP1 | 12/31/25 | 01/29/26
EXTERIORS | Concourse Level | North | Electrical | Trim-out Devices | #0000FF | E4 | 01/30/26 | 02/05/26
EXTERIORS | Lower Suite Level | South | Roofing | Install Roof Curbs/Rails | #FFD78F | RG1 | 09/04/25 | 09/04/25
EXTERIORS | Lower Suite Level | South | Concrete | Concrete Cure Time | #595959 | C11 | 09/04/25 | 10/01/25
EXTERIORS | Lower Suite Level | South | Framing | Exterior Framing and Sheathing - South | #8B4513 | F1 | 09/18/25 | 10/01/25
EXTERIORS | Lower Suite Level | South | Waterproofing | Install Air/Water Barrier | #742264 | W2 | 10/02/25 | 10/08/25
EXTERIORS | Lower Suite Level | South | Roofing | Install Roofing Membrane | #FFD78F | RG2 | 10/02/25 | 10/15/25
EXTERIORS | Lower Suite Level | South | Metal Panels | Install Metal Panels | #EB7994 | MP2 | 10/30/25 | 11/26/25
EXTERIORS | Lower Suite Level | South | Mechanical | Install Mechanical Equipment | #008000 | M1 | 11/06/25 | 11/12/25
EXTERIORS | Lower Suite Level | North | Concrete | Concrete Cure Time | #595959 | C11 | 08/09/25 | 09/05/25
EXTERIORS | Lower Suite Level | North | Roofing | Install Roof Curbs/Rails | #FFD78F | RG1 | 08/11/25 | 08/11/25
EXTERIORS | Lower Suite Level | North | Framing | Exterior Framing and Sheathing - North | #8B4513 | F1 | 08/20/25 | 09/02/25
EXTERIORS | Lower Suite Level | North | Waterproofing | Install Air/Water Barrier | #742264 | W2 | 09/03/25 | 09/10/25
EXTERIORS | Lower Suite Level | North | Roofing | Install Roofing Membrane | #FFD78F | RG2 | 09/11/25 | 09/24/25
EXTERIORS | Lower Suite Level | North | Metal Panels | Install Metal Panels | #EB7994 | MP2 | 10/02/25 | 10/29/25
EXTERIORS | Lower Suite Level | North | Mechanical | Install Mechanical Equipment | #008000 | M1 | 10/23/25 | 11/05/25
EXTERIORS | Roof Level | Roof Level | Roofing | Install Roofing Membrane | #FFD78F | RG2 | 10/16/25 | 10/22/25
EXTERIORS | Concession Wings - Concourse Level | NEC | Framing | Exterior Framing and Sheathing - North | #8B4513 | F1 | 08/19/25 | 09/01/25
EXTERIORS | Concession Wings - Concourse Level | NEC | Waterproofing | Install Air/Water Barrier | #742264 | W2 | 09/02/25 | 09/05/25
EXTERIORS | Concession Wings - Concourse Level | NEC | Masonry | Install Masonry Veneer | #E52F2F | R1 | 09/09/25 | 10/28/25
EXTERIORS | Concession Wings - Concourse Level | NEC | Metal Panels | Install Metal Panel Fascias & Soffits | #EB7994 | MP3 | 10/30/25 | 11/19/25
EXTERIORS | Concession Wings - Concourse Level | NEC | Electrical | Install Linear Soffit Lights | #0000FF | E6 | 11/20/25 | 11/26/25
EXTERIORS | Concession Wings - Concourse Level | SEC | Framing | Exterior Framing and Sheathing - South | #8B4513 | F1 | 09/02/25 | 09/16/25
EXTERIORS | Concession Wings - Concourse Level | SEC | Waterproofing | Install Air/Water Barrier | #742264 | W2 | 09/17/25 | 09/19/25
EXTERIORS | Concession Wings - Concourse Level | SEC | Masonry | Install Masonry Veneer | #E52F2F | R1 | 09/22/25 | 10/21/25
EXTERIORS | Concession Wings - Concourse Level | SEC | Glazing | Install Storefront System | #C1F0C8 | Z2 | 10/22/25 | 11/04/25
EXTERIORS | Concession Wings - Concourse Level | SEC | Metal Panels | Install Metal Panel Fascias & Soffits | #EB7994 | MP3 | 12/01/25 | 12/19/25
EXTERIORS | Concession Wings - Concourse Level | SEC | Electrical | Install Linear Soffit Lights | #0000FF | E6 | 12/22/25 | 12/29/25
EXTERIORS | Roof Level | NEC | Roofing | Install Roof Curbs/Rails | #FFD78F | RG1 | 08/19/25 | 08/20/25
EXTERIORS | Roof Level | NEC | Roofing | Install Roofing Membrane | #FFD78F | RG2 | 09/02/25 | 09/09/25
EXTERIORS | Roof Level | NEC | Mechanical | Install Mechanical Equipment | #008000 | M1 | 09/10/25 | 09/30/25
EXTERIORS | Roof Level | SEC | Roofing | Install Roof Curbs/Rails | #FFD78F | RG1 | 09/02/25 | 09/03/25
EXTERIORS | Roof Level | SEC | Roofing | Install Roofing Membrane | #FFD78F | RG2 | 09/25/25 | 10/01/25
EXTERIORS | Roof Level | SEC | Mechanical | Install Mechanical Equipment | #008000 | M1 | 10/02/25 | 10/22/25
EXTERIORS | Northeast - Concourse Level | NE | Framing | Exterior Framing and Sheathing - Northeast | #8B4513 | F1 | 10/03/25 | 10/16/25
EXTERIORS | Northeast - Concourse Level | NE | Specialty | Install SS Serving Counters | #26EAB2 | Y2 | 10/17/25 | 10/20/25
EXTERIORS | Northeast - Concourse Level | NE | Waterproofing | Install Air/Water Barrier | #742264 | W2 | 10/17/25 | 10/23/25
EXTERIORS | Northeast - Concourse Level | NE | Masonry | Install Masonry Veneer | #E52F2F | R1 | 10/24/25 | 12/01/25
EXTERIORS | Northeast - Concourse Level | NE | Metal Panels | Install Metal Panel Fascia | #EB7994 | MP3 | 01/30/26 | 02/12/26
EXTERIORS | Northeast - Roof Level | NE | Roofing | Install Roof Curbs/Rails | #FFD78F | RG1 | 09/17/25 | 09/18/25
EXTERIORS | Northeast - Roof Level | NE | Roofing | Install Roofing Membrane | #FFD78F | RG2 | 10/23/25 | 10/29/25
EXTERIORS | Northeast - Roof Level | NE | Mechanical | Install Mechanical Equipment | #008000 | M1 | 11/13/25 | 11/19/25
EXTERIORS | Entry | Concourse level | Steel | Install Entry Main Canopy | #DBD997 | S9 | 12/22/25 | 01/21/26
EXTERIORS | Entry | Concourse level | Steel | Install Secondary Entry Canopy | #DBD997 | S10 | 01/22/26 | 02/04/26
EXTERIORS | Entry | Concourse level | Miscellaneous | Install Entry Gates | #B8EE0C | MS1 | 02/05/26 | 02/18/26
EXTERIORS | Entry | Concourse level | Miscellaneous | Install Entry Gates | #B8EE0C | MS1 | 02/19/26 | 02/25/26
EXTERIORS | Entry | Concourse level | Signage | Install Entry Signage | #E65200 | SG1 | 02/26/26 | 03/04/26
INTERIORS | Main building - Concourse level | Food service | Framing | Partition Layout & Top Track | #8B4513 | F2 | 09/04/25 | 09/10/25
INTERIORS | Main building - Concourse level | Food service | Mechanical | Mechanical Overhead & Riser Rough-in | #008000 | M2 | 09/11/25 | 09/16/25
INTERIORS | Main building - Concourse level | Food service | Fire Sprinkler | Fire Protection Overhead | #AD1DC1 | H2 | 09/11/25 | 09/16/25
INTERIORS | Main building - Concourse level | Food service | Plumbing | Plumbing/Piping Overhead & Riser Rough-in | #90EE90 | P2 | 09/17/25 | 09/24/25
INTERIORS | Main building - Concourse level | Food service | Framing | Frame & One-side Walls | #8B4513 | F3 | 09/25/25 | 09/30/25
INTERIORS | Main building - Concourse level | Food service | Electrical | Elect/LV Rough-in | #0000FF | E7 | 09/30/25 | 10/06/25
INTERIORS | Main building - Concourse level | Food service | Plumbing | Plumbing In-wall Rough-in | #90EE90 | P3 | 10/07/25 | 10/13/25
INTERIORS | Main building - Concourse level | Food service | Inspection | In-Wall QC Check | #59672B | IS1 | 10/14/25 | 10/14/25
INTERIORS | Main building - Concourse level | Food service | Inspection | COF In-Wall Inspection | #59672B | IS2 | 10/15/25 | 10/15/25
INTERIORS | Main building - Concourse level | Food service | Drywall | Insulate & Close Walls | #81FFFF | DW1 | 10/16/25 | 10/22/25
INTERIORS | Main building - Concourse level | Food service | Drywall | Tape/Bed/Prime/ 1st Coat Walls | #81FFFF | DW2 | 10/21/25 | 10/29/25
INTERIORS | Main building - Concourse level | Food service | Specialty | Install Counter Shutters | #26EAB2 | Y3 | 10/30/25 | 10/31/25
INTERIORS | Main building - Concourse level | Food service | Concrete | FRP MEP Pads | #595959 | C12 | 10/30/25 | 10/31/25
INTERIORS | Main building - Concourse level | Food service | Mechanical | Install Kitchen Hoods | #008000 |  | 11/03/25 | 11/07/25
INTERIORS | Main building - Concourse level | Food service | Mechanical | Grease Duct Tie-in/Insulate | #008000 | M3 | 11/10/25 | 11/21/25
INTERIORS | Main building - Concourse level | Food service | Refrigeration | Install Walk-in Cooler/Freezer | #920000 | RF1 | 11/13/25 | 11/19/25
INTERIORS | Main building - Concourse level | Food service | Electrical | Build-out Electrical Room | #0000FF | E8 | 11/14/25 | 11/20/25
INTERIORS | Main building - Concourse level | Food service | Drywall | Seal MEP Rooms | #81FFFF | DW5 | 11/21/25 | 11/24/25
INTERIORS | Main building - Concourse level | Food service | Paint | Final Paint Storage | #F0C8EC | PT1 | 11/25/25 | 12/01/25
INTERIORS | Main building - Concourse level | Food service | Ceiling | Install ACT Grid | #B2B202 | Q1 | 11/25/25 | 12/03/25
INTERIORS | Main building - Concourse level | Food service | Electrical | Build-out IDF Room | #0000FF | E9 | 12/02/25 | 12/08/25
INTERIORS | Main building - Concourse level | Food service | Mechanical | Install Mechanical Devices | #008000 | M4 | 12/04/25 | 12/09/25
INTERIORS | Main building - Concourse level | Food service | Electrical | Install Light Fixtures | #0000FF | E10 | 12/09/25 | 12/12/25
INTERIORS | Main building - Concourse level | Food service | Fire Sprinkler | Drop Sprinkler Heads | #AD1DC1 | H3 | 12/15/25 | 12/16/25
INTERIORS | Main building - Concourse level | Food service | Inspection | Overhead QC Inspection | #59672B | IS3 | 12/17/25 | 12/17/25
INTERIORS | Main building - Concourse level | Food service | Inspection | COF Overhead Inspections | #59672B | IS4 | 12/18/25 | 12/18/25
INTERIORS | Main building - Concourse level | Food service | Flooring | Install Epoxy Flooring/Base | #EB0F87 | FO1 | 12/19/25 | 01/05/26
INTERIORS | Main building - Concourse level | Food service | Specialty | Install Concession Wall Finish | #26EAB2 | Y4 | 01/06/26 | 02/03/26
INTERIORS | Main building - Concourse level | Food service | Plumbing | Install Plumbing Fixtures | #90EE90 | P4 | 02/04/26 | 02/06/26
INTERIORS | Main building - Concourse level | Food service | Mechanical | Install Mechanical Wall Units/Air Curtains | #008000 | M5 | 02/04/26 | 02/06/26
INTERIORS | Main building - Concourse level | Food service | Equipment | Install Food Service Equipment | #7500F6 | EQ1 | 02/25/26 | 03/10/26
INTERIORS | Main building - Concourse level | Food service | Equipment | Install Doors & Hardware | #7500F6 | EQ2 | 03/11/26 | 03/12/26
INTERIORS | Main building - Concourse level | Food service | Plumbing | Plumbing Trim-out | #90EE90 | P5 | 03/11/26 | 03/17/26
INTERIORS | Main building - Concourse level | Food service | Electrical | Electrical/FA Trim-out | #0000FF | E11 | 03/13/26 | 03/19/26
INTERIORS | Main building - Concourse level | Food service | Mechanical | Kitchen Hood Testing | #008000 | M6 | 03/20/26 | 03/20/26
INTERIORS | Main building - Concourse level | Food service | Electrical | LV Trim-out | #0000FF | E12 | 03/20/26 | 03/24/26
INTERIORS | Main building - Concourse level | Food service | Ceiling | Install ACT Tile | #B2B202 | Q1 | 03/25/26 | 03/31/26
INTERIORS | Main building - Concourse level | Food service | Clean | Construction Rough Clean | #FDFFB7 | CN1 | 04/01/26 | 04/07/26
INTERIORS | Main building - Concourse level | Food service | Manhattan | MCC Completion List - Prepare/Distribute/Complete | #FFFF00 | MH2 | 04/08/26 | 04/21/26
INTERIORS | Main building - Concourse level | Food service | Manhattan | Design Team Punch List & Completion | #FFFF00 | MH3 | 04/22/26 | 05/05/26
INTERIORS | Main building - Concourse level | Food service | Clean | Final Clean | #FDFFB7 | CN2 | 05/06/26 | 05/08/26
INTERIORS | Main building - Concourse level | Restrooms | Framing | Partition Layout & Top Track | #8B4513 | F2 | 09/11/25 | 09/15/25
INTERIORS | Main building - Concourse level | Restrooms | Mechanical | Mechanical Overhead & Riser Rough-in | #008000 | M2 | 09/17/25 | 09/19/25
INTERIORS | Main building - Concourse level | Restrooms | Fire Sprinkler | Fire Protection Overhead | #AD1DC1 | H2 | 09/17/25 | 09/22/25
INTERIORS | Main building - Concourse level | Restrooms | Plumbing | Plumbing/Piping Overhead & Riser Rough-in | #90EE90 | P2 | 09/22/25 | 09/26/25
INTERIORS | Main building - Concourse level | Restrooms | Framing | Frame & One-side Walls | #8B4513 | F3 | 10/01/25 | 10/06/25
INTERIORS | Main building - Concourse level | Restrooms | Carpentry | Install Vanity Supports | #4F9EDF | T3 | 10/07/25 | 10/09/25
INTERIORS | Main building - Concourse level | Restrooms | Plumbing | Plumbing In-wall Rough-in | #90EE90 | P3 | 10/07/25 | 10/10/25
INTERIORS | Main building - Concourse level | Restrooms | Electrical | Elect/LV Rough-in | #0000FF | E7 | 10/08/25 | 10/13/25
INTERIORS | Main building - Concourse level | Restrooms | Inspection | In-Wall QC Check | #59672B | IS1 | 10/14/25 | 10/14/25
INTERIORS | Main building - Concourse level | Restrooms | Inspection | COF In-Wall Inspection | #59672B | IS2 | 10/15/25 | 10/15/25
INTERIORS | Main building - Concourse level | Restrooms | Drywall | Insulate & Close Walls | #81FFFF | DW1 | 10/16/25 | 10/22/25
INTERIORS | Main building - Concourse level | Restrooms | Drywall | Tape/Bed/Prime/ 1st Coat Walls | #81FFFF | DW2 | 10/23/25 | 11/05/25
INTERIORS | Main building - Concourse level | Restrooms | Framing | Frame Hard Ceilings/Soffits | #8B4513 | F4 | 11/06/25 | 11/12/25
INTERIORS | Main building - Concourse level | Restrooms | Mechanical | Install Mechanical Devices | #008000 | M4 | 11/13/25 | 11/18/25
INTERIORS | Main building - Concourse level | Restrooms | Electrical | Install Light Fixtures | #0000FF | E10 | 11/19/25 | 11/24/25
INTERIORS | Main building - Concourse level | Restrooms | Electrical | Install FA/LV Pathway | #0000FF | E13 | 11/19/25 | 11/21/25
INTERIORS | Main building - Concourse level | Restrooms | Fire Sprinkler | Drop Sprinkler Heads | #AD1DC1 | H3 | 11/26/25 | 12/01/25
INTERIORS | Main building - Concourse level | Restrooms | Inspection | Overhead QC Inspection | #59672B | IS3 | 12/02/25 | 12/02/25
INTERIORS | Main building - Concourse level | Restrooms | Inspection | COF Overhead Inspections | #59672B | IS4 | 12/03/25 | 12/03/25
INTERIORS | Main building - Concourse level | Restrooms | Drywall | Close Hard Ceilings/Soffits | #81FFFF | DW3 | 12/04/25 | 12/10/25
INTERIORS | Main building - Concourse level | Restrooms | Drywall | Tape/Bed/Paint Ceilings | #81FFFF | DW2 | 12/11/25 | 12/24/25
INTERIORS | Main building - Concourse level | Restrooms | Tile | Install Restroom Wall Tile & Base | #5A8787 | TE1 | 12/26/25 | 01/26/26
INTERIORS | Main building - Concourse level | Restrooms | Paint | Final Paint Janitor Closet | #F0C8EC | PT2 | 12/31/25 | 01/05/26
INTERIORS | Main building - Concourse level | Restrooms | Plumbing | Install Plumbing Fixtures | #90EE90 | P4 | 01/27/26 | 02/09/26
INTERIORS | Main building - Concourse level | Restrooms | Specialty | Install Countertops | #26EAB2 | Y5 | 02/10/26 | 02/13/26
INTERIORS | Main building - Concourse level | Restrooms | Plumbing | Plumbing Trim-out | #90EE90 | P5 | 02/16/26 | 02/17/26
INTERIORS | Main building - Concourse level | Restrooms | Specialty | Install Toilet Partitions | #26EAB2 | Y6 | 02/18/26 | 02/24/26
INTERIORS | Main building - Concourse level | Restrooms | Specialty | Install Toilet Accessories | #26EAB2 | Y7 | 02/25/26 | 03/03/26
INTERIORS | Main building - Concourse level | Restrooms | Equipment | Install Doors & Hardware | #7500F6 | EQ2 | 03/04/26 | 03/05/26
INTERIORS | Main building - Concourse level | Restrooms | Electrical | LV Trim-out | #0000FF | E12 | 03/06/26 | 03/10/26
INTERIORS | Main building - Concourse level | Restrooms | Electrical | Electrical/FA Trim-out | #0000FF | E11 | 03/06/26 | 03/12/26
INTERIORS | Main building - Concourse level | Restrooms | Clean | Construction Rough Clean | #FDFFB7 | CN1 | 03/16/26 | 03/20/26
INTERIORS | Main building - Concourse level | Restrooms | Manhattan | MCC Completion List - Prepare/Distribute/Complete | #FFFF00 | MH2 | 03/23/26 | 04/03/26
INTERIORS | Main building - Concourse level | Restrooms | Manhattan | Design Team Punch List & Completion | #FFFF00 | MH3 | 04/06/26 | 04/17/26
INTERIORS | Main building - Concourse level | Restrooms | Clean | Final Clean | #FDFFB7 | CN2 | 04/20/26 | 04/22/26
INTERIORS | Main building - Concourse level | South Concessions | Framing | Partition Layout & Top Track | #8B4513 | F2 | 09/22/25 | 09/23/25
INTERIORS | Main building - Concourse level | South Concessions | Fire Sprinkler | Fire Protection Overhead | #AD1DC1 | H2 | 09/24/25 | 09/25/25
INTERIORS | Main building - Concourse level | South Concessions | Mechanical | Mechanical Overhead & Riser Rough-in | #008000 | M2 | 09/24/25 | 09/26/25
INTERIORS | Main building - Concourse level | South Concessions | Plumbing | Plumbing/Piping Overhead & Riser Rough-in | #90EE90 | P2 | 09/29/25 | 10/03/25
INTERIORS | Main building - Concourse level | South Concessions | Framing | Frame & One-side Walls | #8B4513 | F3 | 10/07/25 | 10/09/25
INTERIORS | Main building - Concourse level | South Concessions | Plumbing | Plumbing In-wall Rough-in | #90EE90 | P3 | 10/13/25 | 10/16/25
INTERIORS | Main building - Concourse level | South Concessions | Electrical | Elect/LV Rough-in | #0000FF | E7 | 10/14/25 | 10/17/25
INTERIORS | Main building - Concourse level | South Concessions | Inspection | In-Wall QC Check | #59672B | IS1 | 10/20/25 | 10/20/25
INTERIORS | Main building - Concourse level | South Concessions | Inspection | COF In-Wall Inspection | #59672B | IS2 | 10/21/25 | 10/21/25
INTERIORS | Main building - Concourse level | South Concessions | Drywall | Insulate & Close Walls | #81FFFF | DW1 | 10/23/25 | 10/24/25
INTERIORS | Main building - Concourse level | South Concessions | Drywall | Tape/Bed/Prime/ 1st Coat Walls | #81FFFF | DW2 | 10/27/25 | 11/04/25
INTERIORS | Main building - Concourse level | South Concessions | Drywall | Seal MEP Rooms | #81FFFF | DW5 | 11/05/25 | 11/05/25
INTERIORS | Main building - Concourse level | South Concessions | Specialty | Install Counter Shutters | #26EAB2 | Y3 | 11/05/25 | 11/06/25
INTERIORS | Main building - Concourse level | South Concessions | Mechanical | Install Kitchen Hoods | #008000 | M7 | 11/06/25 | 11/07/25
INTERIORS | Main building - Concourse level | South Concessions | Paint | Final Paint MEP | #F0C8EC | PT3 | 11/06/25 | 11/07/25
INTERIORS | Main building - Concourse level | South Concessions | Refrigeration | Install Walk-in Cooler/Freezer | #920000 | RF1 | 11/10/25 | 11/12/25
INTERIORS | Main building - Concourse level | South Concessions | Mechanical | Grease Duct Tie-in/Insulate | #008000 | M3 | 11/13/25 | 11/19/25
INTERIORS | Main building - Concourse level | South Concessions | Ceiling | Install ACT Grid | #B2B202 | Q2 | 11/20/25 | 11/24/25
INTERIORS | Main building - Concourse level | South Concessions | Electrical | Build-out Electrical Room | #0000FF | E8 | 11/21/25 | 12/01/25
INTERIORS | Main building - Concourse level | South Concessions | Mechanical | Install Mechanical Devices | #008000 | M4 | 11/25/25 | 11/26/25
INTERIORS | Main building - Concourse level | South Concessions | Fire Sprinkler | Drop Sprinkler Heads | #AD1DC1 | H3 | 12/01/25 | 12/01/25
INTERIORS | Main building - Concourse level | South Concessions | Electrical | Install FA/LV Pathway | #0000FF | E13 | 12/02/25 | 12/03/25
INTERIORS | Main building - Concourse level | South Concessions | Electrical | Install Light Fixtures | #0000FF | E10 | 12/04/25 | 12/08/25
INTERIORS | Main building - Concourse level | South Concessions | Inspection | Overhead QC Inspection | #59672B | IS3 | 12/09/25 | 12/09/25
INTERIORS | Main building - Concourse level | South Concessions | Inspection | COF Overhead Inspections | #59672B | IS4 | 12/10/25 | 12/10/25
INTERIORS | Main building - Concourse level | South Concessions | Flooring | Install Epoxy Flooring/Base | #EB0F87 | FO1 | 12/11/25 | 12/17/25
INTERIORS | Main building - Concourse level | South Concessions | Specialty | Install Concession Wall Finish | #26EAB2 | Y4 | 12/18/25 | 01/02/26
INTERIORS | Main building - Concourse level | South Concessions | Plumbing | Install Plumbing Fixtures | #90EE90 | P4 | 01/05/26 | 01/06/26
INTERIORS | Main building - Concourse level | South Concessions | Mechanical | Install Mechanical Wall Units/Air Curtains | #008000 | M5 | 01/05/26 | 01/07/26
INTERIORS | Main building - Concourse level | South Concessions | Equipment | Install Food Service Equipment | #7500F6 | EQ1 | 01/08/26 | 01/15/26
INTERIORS | Main building - Concourse level | South Concessions | Plumbing | Plumbing Trim-out | #90EE90 | P5 | 01/16/26 | 01/20/26
INTERIORS | Main building - Concourse level | South Concessions | Electrical | Electrical/FA Trim-out | #0000FF | E11 | 01/16/26 | 01/22/26
INTERIORS | Main building - Concourse level | South Concessions | Mechanical | Kitchen Hood Testing | #008000 | M6 | 01/23/26 | 01/23/26
INTERIORS | Main building - Concourse level | South Concessions | Equipment | Install Doors & Hardware | #7500F6 | EQ2 | 01/23/26 | 01/26/26
INTERIORS | Main building - Concourse level | South Concessions | Electrical | LV Trim-out | #0000FF | E12 | 01/30/26 | 02/02/26
INTERIORS | Main building - Concourse level | South Concessions | Ceiling | Install ACT Tile | #B2B202 | Q1 | 02/03/26 | 02/04/26
INTERIORS | Main building - Concourse level | South Concessions | Clean | Construction Rough Clean | #FDFFB7 | CN1 | 02/05/26 | 02/11/26
INTERIORS | Main building - Concourse level | South Concessions | Manhattan | MCC Completion List - Prepare/Distribute/Complete | #FFFF00 | MH2 | 02/12/26 | 02/25/26
INTERIORS | Main building - Concourse level | South Concessions | Manhattan | Design Team Punch List & Completion | #FFFF00 | MH3 | 02/26/26 | 03/11/26
INTERIORS | Main building - Concourse level | South Concessions | Clean | Final Clean | #FDFFB7 | CN2 | 03/12/26 | 03/16/26
INTERIORS | Main building - Concourse level | Burn Club | Framing | Partition Layout & Top Track | #8B4513 | F2 | 09/16/25 | 09/19/25
INTERIORS | Main building - Concourse level | Burn Club | Mechanical | Mechanical Overhead & Riser Rough-in | #008000 | M2 | 09/22/25 | 10/01/25
INTERIORS | Main building - Concourse level | Burn Club | Fire Sprinkler | Fire Protection Overhead | #AD1DC1 | H2 | 09/23/25 | 10/02/25
INTERIORS | Main building - Concourse level | Burn Club | Plumbing | Plumbing/Piping Overhead & Riser Rough-in | #90EE90 | P2 | 10/03/25 | 10/09/25
INTERIORS | Main building - Concourse level | Burn Club | Framing | Frame & One-side Walls | #8B4513 | F3 | 10/10/25 | 10/14/25
INTERIORS | Main building - Concourse level | Burn Club | Electrical | Elect/LV Rough-in | #0000FF | E7 | 10/15/25 | 10/21/25
INTERIORS | Main building - Concourse level | Burn Club | Plumbing | Plumbing In-wall Rough-in | #90EE90 | P3 | 10/16/25 | 10/22/25
INTERIORS | Main building - Concourse level | Burn Club | Inspection | In-Wall QC Check | #59672B | IS1 | 10/23/25 | 10/24/25
INTERIORS | Main building - Concourse level | Burn Club | Inspection | COF In-Wall Inspection | #59672B | IS2 | 10/27/25 | 10/27/25
INTERIORS | Main building - Concourse level | Burn Club | Drywall | Insulate & Close Walls | #81FFFF | DW1 | 10/28/25 | 10/31/25
INTERIORS | Main building - Concourse level | Burn Club | Drywall | Tape/Bed/Prime/ 1st Coat Walls | #81FFFF | DW2 | 11/03/25 | 11/14/25
INTERIORS | Main building - Concourse level | Burn Club | Specialty | Install Interior Storefront | #26EAB2 | Y8 | 11/17/25 | 12/02/25
INTERIORS | Main building - Concourse level | Burn Club | Framing | Frame Hard Ceilings/Furrdowns | #8B4513 | F4 | 11/17/25 | 12/04/25
INTERIORS | Main building - Concourse level | Burn Club | Electrical | Install Light Fixtures | #0000FF |  | 12/05/25 | 12/18/25
INTERIORS | Main building - Concourse level | Burn Club | Mechanical | Install Mechanical Devices | #008000 | M4 | 12/10/25 | 12/16/25
INTERIORS | Main building - Concourse level | Burn Club | Electrical | Install FA/LV Pathway | #0000FF | E13 | 12/17/25 | 12/24/25
INTERIORS | Main building - Concourse level | Burn Club | Fire Sprinkler | Drop Sprinkler Heads | #AD1DC1 | H3 | 12/19/25 | 12/24/25
INTERIORS | Main building - Concourse level | Burn Club | Inspection | Overhead QC Inspection | #59672B | IS3 | 12/26/25 | 12/29/25
INTERIORS | Main building - Concourse level | Burn Club | Inspection | COF Overhead Inspections | #59672B | IS4 | 12/30/25 | 12/30/25
INTERIORS | Main building - Concourse level | Burn Club | Ceiling | Close Ceilings/Furrdowns | #B2B202 | Q2 | 12/31/25 | 01/15/26
INTERIORS | Main building - Concourse level | Burn Club | Drywall | Tape/Bed/Paint Ceilings | #81FFFF | DW2 | 01/12/26 | 01/30/26
INTERIORS | Main building - Concourse level | Burn Club | Masonry | Install Brick Veneer | #E52F2F | R2 | 01/16/26 | 02/19/26
INTERIORS | Main building - Concourse level | Burn Club | Millwork | Install Wood Ceiling & Bar Soffit | #D7B4FE | ML1 | 01/28/26 | 03/02/26
INTERIORS | Main building - Concourse level | Burn Club | Millwork | Install Drink Rail Supports | #D7B4FE | ML2 | 02/20/26 | 02/24/26
INTERIORS | Main building - Concourse level | Burn Club | Mechanical | Trim Out Mechanical Devices | #008000 | M8 | 03/03/26 | 03/06/26
INTERIORS | Main building - Concourse level | Burn Club | Fire Sprinkler | Trim Out Sprinklers | #AD1DC1 | H4 | 03/03/26 | 03/06/26
INTERIORS | Main building - Concourse level | Burn Club | Millwork | Install Bar Die Walls | #D7B4FE | ML3 | 03/03/26 | 03/09/26
INTERIORS | Main building - Concourse level | Burn Club | Electrical | Lights Trim-out | #0000FF | E14 | 03/03/26 | 03/10/26
INTERIORS | Main building - Concourse level | Burn Club | Flooring | Install Epoxy Flooring/Base | #EB0F87 | FO1 | 03/10/26 | 03/16/26
INTERIORS | Main building - Concourse level | Burn Club | Tile | Install Tile Floor | #5A8787 | TE2 | 03/11/26 | 04/21/26
INTERIORS | Main building - Concourse level | Burn Club | Millwork | Install Bar Fronts & Columns | #D7B4FE | ML4 | 03/17/26 | 03/23/26
INTERIORS | Main building - Concourse level | Burn Club | Millwork | Install Bar Tops | #D7B4FE | ML5 | 03/24/26 | 03/30/26
INTERIORS | Main building - Concourse level | Burn Club | Equipment | Install Bar Equipment | #7500F6 | EQ3 | 03/31/26 | 04/06/26
INTERIORS | Main building - Concourse level | Burn Club | Plumbing | Plumbing Trim-out | #90EE90 | P5 | 04/07/26 | 04/13/26
INTERIORS | Main building - Concourse level | Burn Club | Millwork | Install Millwork/Glass Panel Columns | #D7B4FE | ML6 | 04/15/26 | 05/12/26
INTERIORS | Main building - Concourse level | Burn Club | Millwork | Install Drink Rail Tops | #D7B4FE | ML7 | 04/22/26 | 04/28/26
INTERIORS | Main building - Concourse level | Burn Club | Millwork | Install Wainscot & Base | #D7B4FE | ML8 | 04/22/26 | 04/28/26
INTERIORS | Main building - Concourse level | Burn Club | Millwork | Install Locker Wall/Millwork | #D7B4FE | ML9 | 04/29/26 | 05/05/26
INTERIORS | Main building - Concourse level | Burn Club | Millwork | Install Wallcovering | #D7B4FE | ML10 | 04/29/26 | 05/05/26
INTERIORS | Main building - Concourse level | Burn Club | Specialty | Install Ceiling Scarves | #26EAB2 | Y9 | 05/06/26 | 05/12/26
INTERIORS | Main building - Concourse level | Burn Club | Electrical | Electric/FA/LV Trim-out & Specialty Lights | #0000FF | E11 | 05/13/26 | 05/20/26
INTERIORS | Main building - Concourse level | Burn Club | Clean | Construction Rough Clean | #FDFFB7 | CN1 | 05/21/26 | 05/28/26
INTERIORS | Main building - Concourse level | Burn Club | Manhattan | MCC Completion List - Prepare/Distribute/Complete | #FFFF00 | MH2 | 05/29/26 | 06/11/26
INTERIORS | Main building - Concourse level | Burn Club | Manhattan | Design Team Punch List & Completion | #FFFF00 | MH3 | 06/12/26 | 06/25/26
INTERIORS | Main building - Concourse level | Burn Club | Clean | Final Clean | #FDFFB7 | CN2 | 06/26/26 | 06/30/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Framing | Partition Layout & Top Track | #8B4513 | F2 | 10/01/25 | 10/03/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Mechanical | Mechanical Overhead & Riser Rough-in | #008000 | M2 | 10/06/25 | 10/07/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Fire Sprinkler | Fire Protection Overhead | #AD1DC1 | H2 | 10/07/25 | 10/09/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Plumbing | Plumbing/Piping Overhead | #90EE90 | P6 | 10/15/25 | 10/21/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Framing | Frame & One-side Walls | #8B4513 | F3 | 10/20/25 | 10/24/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Electrical | Elect/LV Rough-in | #0000FF | E7 | 10/29/25 | 11/04/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Plumbing | Plumbing In-wall Rough-in | #90EE90 | P3 | 10/29/25 | 11/04/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Inspection | In-Wall QC Check | #59672B | IS1 | 11/05/25 | 11/05/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Inspection | COF In-Wall Inspection | #59672B | IS2 | 11/06/25 | 11/06/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Drywall | Insulate & Close Walls | #81FFFF | DW1 | 11/07/25 | 11/11/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Drywall | Tape/Bed/Prime/ 1st Coat Walls | #81FFFF | DW2 | 11/12/25 | 11/18/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Framing | Frame Hard Ceilings/Soffits | #8B4513 | F4 | 11/19/25 | 11/19/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Ceiling | Install ACT Grid | #B2B202 | Q3 | 11/25/25 | 11/26/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Mechanical | Install Mechanical Devices | #008000 | M4 | 12/01/25 | 12/01/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Electrical | Install FA/LV Pathway | #0000FF | E13 | 12/01/25 | 12/02/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Fire Sprinkler | Drop Sprinkler Heads | #AD1DC1 | H3 | 12/02/25 | 12/02/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Electrical | Install Light Fixtures | #0000FF | E10 | 12/09/25 | 12/11/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Inspection | Overhead QC Inspection | #59672B | IS3 | 12/18/25 | 12/18/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Inspection | COF Overhead Inspections | #59672B | IS4 | 12/19/25 | 12/19/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Drywall | Close Hard Ceilings/Soffits | #81FFFF | DW3 | 12/22/25 | 12/22/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Drywall | Tape/Bed/Paint Ceilings | #81FFFF | DW2 | 12/23/25 | 12/30/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Flooring | Seal Janitor Closet Floor | #EB0F87 | FO2 | 12/31/25 | 12/31/25
INTERIORS | Concession Wings - Concourse level | South Restrooms | Paint | Final Paint Janitor Closet | #F0C8EC | PT2 | 01/12/26 | 01/13/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Flooring | Install Epoxy Flooring/Base | #EB0F87 | FO1 | 01/14/26 | 01/20/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Tile | Install Restroom Wall Tile & Base | #5A8787 | TE1 | 01/21/26 | 02/03/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Plumbing | Plumbing Trim-out | #90EE90 | P5 | 02/04/26 | 02/05/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Plumbing | Install Plumbing Fixtures | #90EE90 | P4 | 02/04/26 | 02/10/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Specialty | Install Toilet Partitions | #26EAB2 | Y10 | 02/11/26 | 02/17/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Specialty | Install Toilet Accessories | #26EAB2 | Y7 | 02/18/26 | 02/18/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Equipment | Install Doors & Hardware | #7500F6 | EQ2 | 02/18/26 | 02/19/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Electrical | Electrical/FA Trim-out | #0000FF | E11 | 02/19/26 | 02/23/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Electrical | LV Trim-out | #0000FF | E12 | 02/24/26 | 02/25/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Ceiling | Install ACT Tile | #B2B202 | Q1 | 02/26/26 | 02/27/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Clean | Construction Rough Clean | #FDFFB7 | CN1 | 03/02/26 | 03/06/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Manhattan | MCC Completion List - Prepare/Distribute/Complete | #FFFF00 | MH2 | 03/09/26 | 03/20/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Manhattan | Design Team Punch List & Completion | #FFFF00 | MH3 | 03/23/26 | 04/03/26
INTERIORS | Concession Wings - Concourse level | South Restrooms | Clean | Final Clean | #FDFFB7 | CN2 | 04/06/26 | 04/07/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Framing | Partition Layout & Top Track | #8B4513 | F2 | 10/06/25 | 10/07/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Mechanical | Mechanical Overhead & Riser Rough-in | #008000 | M2 | 10/08/25 | 10/09/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Fire Sprinkler | Fire Protection Overhead | #AD1DC1 | H2 | 10/10/25 | 10/14/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Plumbing | Plumbing/Piping Overhead | #90EE90 | P6 | 10/22/25 | 10/28/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Framing | Frame & One-side Walls | #8B4513 | F3 | 10/29/25 | 10/30/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Electrical | Elect/LV Rough-in | #0000FF | E7 | 11/05/25 | 11/11/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Plumbing | Plumbing In-wall Rough-in | #90EE90 | P3 | 11/05/25 | 11/11/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Inspection | In-Wall QC Check | #59672B | IS1 | 11/12/25 | 11/12/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Inspection | COF In-Wall Inspection | #59672B | IS2 | 11/13/25 | 11/13/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Drywall | Insulate & Close Walls | #81FFFF | DW1 | 11/14/25 | 11/18/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Drywall | Tape/Bed/Prime/ 1st Coat Walls | #81FFFF | DW2 | 11/19/25 | 12/01/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Mechanical | Install Kitchen Hoods | #008000 | M7 | 12/03/25 | 12/04/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Mechanical | Grease Duct Tie-in/Insulate | #008000 | M3 | 12/05/25 | 12/10/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Ceiling | Install ACT Grid | #B2B202 | Q3 | 12/11/25 | 12/12/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Electrical | Install FA/LV Pathway | #0000FF | E13 | 12/16/25 | 12/18/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Mechanical | Install Mechanical Devices | #008000 | M4 | 12/17/25 | 12/18/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Electrical | Install Light Fixtures | #0000FF | E10 | 12/19/25 | 12/23/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Fire Sprinkler | Drop Sprinkler Heads | #AD1DC1 | H3 | 12/19/25 | 12/19/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Inspection | Overhead QC Inspection | #59672B | IS3 | 12/24/25 | 12/24/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Inspection | COF Overhead Inspections | #59672B | IS4 | 12/26/25 | 12/26/25
INTERIORS | Concession Wings - Concourse level | South Concessions | Flooring | Install Epoxy Flooring/Base | #EB0F87 | FO1 | 01/05/26 | 01/12/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Specialty | Install Concession Wall Finish | #26EAB2 | Y4 | 02/04/26 | 02/17/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Mechanical | Install Mechanical Wall Units/Air Curtains | #008000 | M5 | 02/18/26 | 02/20/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Equipment | Install Food Service Equipment | #7500F6 | EQ1 | 02/18/26 | 02/24/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Equipment | Install Doors & Hardware | #7500F6 | EQ2 | 02/25/26 | 02/26/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Plumbing | Plumbing Trim-out | #90EE90 | P5 | 02/25/26 | 02/27/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Electrical | Electrical/FA Trim-out | #0000FF | E11 | 02/25/26 | 02/27/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Electrical | LV Trim-out | #0000FF | E12 | 03/02/26 | 03/03/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Mechanical | Kitchen Hood Testing | #008000 | M6 | 03/04/26 | 03/04/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Ceiling | Install ACT Tile | #B2B202 | Q1 | 03/05/26 | 03/06/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Clean | Construction Rough Clean | #FDFFB7 | CN1 | 03/09/26 | 03/13/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Manhattan | MCC Completion List - Prepare/Distribute/Complete | #FFFF00 | MH2 | 03/16/26 | 03/27/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Manhattan | Design Team Punch List & Completion | #FFFF00 | MH3 | 03/30/26 | 04/10/26
INTERIORS | Concession Wings - Concourse level | South Concessions | Clean | Final Clean | #FDFFB7 | CN2 | 04/13/26 | 04/14/26
INTERIORS | Concession Wings - Concourse level | Team Store | Framing | Partition Layout & Top Track | #8B4513 | F2 | 10/08/25 | 10/08/25
INTERIORS | Concession Wings - Concourse level | Team Store | Mechanical | Mechanical Overhead & Riser Rough-in | #008000 | M2 | 10/10/25 | 10/10/25
INTERIORS | Concession Wings - Concourse level | Team Store | Fire Sprinkler | Fire Protection Overhead | #AD1DC1 | H2 | 10/23/25 | 10/24/25
INTERIORS | Concession Wings - Concourse level | Team Store | Plumbing | Plumbing/Piping Overhead | #90EE90 | P6 | 10/27/25 | 10/31/25
INTERIORS | Concession Wings - Concourse level | Team Store | Framing | Frame & One-side Walls | #8B4513 | F3 | 11/03/25 | 11/03/25
INTERIORS | Concession Wings - Concourse level | Team Store | Electrical | Elect/LV Rough-in | #0000FF | E7 | 11/12/25 | 11/13/25
INTERIORS | Concession Wings - Concourse level | Team Store | Inspection | In-Wall QC Check | #59672B | IS1 | 11/14/25 | 11/14/25
INTERIORS | Concession Wings - Concourse level | Team Store | Inspection | COF In-Wall Inspection | #59672B | IS2 | 11/17/25 | 11/17/25
INTERIORS | Concession Wings - Concourse level | Team Store | Drywall | Insulate & Close Walls | #81FFFF | DW1 | 11/19/25 | 11/19/25
INTERIORS | Concession Wings - Concourse level | Team Store | Drywall | Tape/Bed/Prime/ 1st Coat Walls | #81FFFF | DW2 | 11/21/25 | 12/01/25
INTERIORS | Concession Wings - Concourse level | Team Store | Flooring | Seal IDF Floor | #EB0F87 | FO3 | 12/02/25 | 12/02/25
INTERIORS | Concession Wings - Concourse level | Team Store | Mechanical | Install Mechanical Devices | #008000 | M4 | 12/02/25 | 12/02/25
INTERIORS | Concession Wings - Concourse level | Team Store | Electrical | Electrical/FA Trim-out | #0000FF | E11 | 12/03/25 | 12/04/25
INTERIORS | Concession Wings - Concourse level | Team Store | Electrical | Install Light Fixtures | #0000FF | E10 | 12/17/25 | 12/18/25
INTERIORS | Concession Wings - Concourse level | Team Store | Clean | Construction Rough Clean | #FDFFB7 | CN1 | 12/26/25 | 12/30/25
INTERIORS | Concession Wings - Concourse level | Team Store | Manhattan | MCC Completion List - Prepare/Distribute/Complete | #FFFF00 | MH2 | 12/31/25 | 01/15/26
INTERIORS | Concession Wings - Concourse level | Team Store | Manhattan | Design Team Punch List & Completion | #FFFF00 | MH3 | 01/16/26 | 01/29/26
INTERIORS | Concession Wings - Concourse level | Team Store | Clean | Final Clean | #FDFFB7 | CN2 | 01/30/26 | 01/30/26
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Framing | Partition Layout & Top Track | #8B4513 | F2 | 09/02/25 | 09/03/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Mechanical | Mechanical Overhead & Riser Rough-in | #008000 | M2 | 09/04/25 | 09/05/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Plumbing | Plumbing/Piping Overhead | #90EE90 | P6 | 09/09/25 | 09/10/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Fire Sprinkler | Fire Protection Overhead | #AD1DC1 | H2 | 09/09/25 | 09/10/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Framing | Frame & One-side Walls | #8B4513 | F3 | 09/11/25 | 09/15/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Electrical | Elect/LV Rough-in | #0000FF | E7 | 09/16/25 | 09/22/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Inspection | In-Wall QC Check | #59672B | IS1 | 09/23/25 | 09/23/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Inspection | COF In-Wall Inspection | #59672B | IS2 | 09/24/25 | 09/24/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Drywall | Insulate & Close Walls | #81FFFF | DW1 | 09/25/25 | 09/29/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Drywall | Tape/Bed/Prime/ 1st Coat Walls | #81FFFF | DW2 | 09/30/25 | 10/08/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Mechanical | Trim Mechanical Devices | #008000 | M8 | 10/09/25 | 10/09/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Electrical | Install Light Fixtures | #0000FF | E10 | 10/09/25 | 10/10/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Concrete | FRP Equipment Pads | #595959 | C13 | 10/09/25 | 10/13/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Electrical | Electrical/FA Trim-out | #0000FF | E11 | 10/09/25 | 10/15/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Drywall | Seal MEP/Storage Rooms | #81FFFF | DW4 | 10/14/25 | 10/14/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Equipment | Install Doors & Hardware | #7500F6 | EQ2 | 10/15/25 | 10/16/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Electrical | LV Trim-out | #0000FF | E12 | 10/17/25 | 10/20/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Electrical | Build-out Elecrtical Room | #0000FF | E5 | 10/17/25 | 11/13/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Clean | Construction Rough Clean | #FDFFB7 | CN1 | 11/14/25 | 11/20/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Manhattan | MCC Completion List - Prepare/Distribute/Complete | #FFFF00 | MH2 | 11/21/25 | 12/08/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Manhattan | Design Team Punch List & Completion | #FFFF00 | MH3 | 12/09/25 | 12/22/25
INTERIORS | Concession Wings - Concourse level | MEP/LV Rooms | Clean | Final Clean | #FDFFB7 | CN2 | 12/23/25 | 12/24/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Framing | Partition Layout & Top Track | #8B4513 | F2 | 09/24/25 | 09/26/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Mechanical | Mechanical Overhead & Riser Rough-in | #008000 | M2 | 09/29/25 | 09/30/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Fire Sprinkler | Fire Protection Overhead | #AD1DC1 | H2 | 09/29/25 | 10/01/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Plumbing | Plumbing/Piping Overhead | #90EE90 | P6 | 10/01/25 | 10/07/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Framing | Frame & One-side Walls | #8B4513 | F3 | 10/06/25 | 10/10/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Electrical | Elect/LV Rough-in | #0000FF | E7 | 10/14/25 | 10/20/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Plumbing | Plumbing In-wall Rough-in | #90EE90 | P3 | 10/14/25 | 10/20/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Inspection | In-Wall QC Check | #59672B | IS1 | 10/21/25 | 10/21/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Inspection | COF In-Wall Inspection | #59672B | IS2 | 10/22/25 | 10/22/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Drywall | Insulate & Close Walls | #81FFFF | DW1 | 10/23/25 | 10/27/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Drywall | Tape/Bed/Prime/ 1st Coat Walls | #81FFFF | DW2 | 10/28/25 | 11/03/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Ceiling | Install ACT Grid | #B2B202 | Q3 | 11/04/25 | 11/06/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Framing | Frame Hard Ceilings/Soffits | #8B4513 | F4 | 11/06/25 | 11/06/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Mechanical | Install Mechanical Devices | #008000 | M4 | 11/07/25 | 11/07/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Electrical | Install FA/LV Pathway | #0000FF | E13 | 11/07/25 | 11/10/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Fire Sprinkler | Drop Sprinkler Heads | #AD1DC1 | H3 | 11/10/25 | 11/10/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Electrical | Install Light Fixtures | #0000FF | E10 | 11/14/25 | 11/18/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Inspection | Overhead QC Inspection | #59672B | IS3 | 11/19/25 | 11/19/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Inspection | COF Overhead Inspections | #59672B | IS4 | 11/20/25 | 11/20/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Drywall | Close Hard Ceilings/Soffits | #81FFFF | DW3 | 11/21/25 | 11/21/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Drywall | Tape/Bed/Paint Ceilings | #81FFFF | DW2 | 11/24/25 | 11/26/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Flooring | Install Epoxy Flooring/Base | #EB0F87 | FO1 | 12/01/25 | 12/05/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Tile | Install Restroom Wall Tile & Base | #5A8787 | TE1 | 12/08/25 | 12/19/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Plumbing | Install Plumbing Fixtures | #90EE90 | P4 | 12/22/25 | 12/29/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Plumbing | Plumbing Trim-out | #90EE90 | P5 | 12/30/25 | 12/31/25
INTERIORS | Concession Wings - Concourse level | North Restrooms | Specialty | Install Toilet Partitions | #26EAB2 | Y10 | 01/02/26 | 01/16/26
INTERIORS | Concession Wings - Concourse level | North Restrooms | Specialty | Install Toilet Accessories | #26EAB2 | Y7 | 01/19/26 | 01/19/26
INTERIORS | Concession Wings - Concourse level | North Restrooms | Equipment | Install Doors & Hardware | #7500F6 | EQ2 | 01/19/26 | 01/20/26
INTERIORS | Concession Wings - Concourse level | North Restrooms | Electrical | Electrical/FA Trim-out | #0000FF | E11 | 01/23/26 | 01/27/26
INTERIORS | Concession Wings - Concourse level | North Restrooms | Electrical | LV Trim-out | #0000FF | E12 | 01/28/26 | 01/29/26
INTERIORS | Concession Wings - Concourse level | North Restrooms | Ceiling | Install ACT Tile | #B2B202 | Q1 | 01/30/26 | 02/02/26
INTERIORS | Concession Wings - Concourse level | North Restrooms | Clean | Construction Rough Clean | #FDFFB7 | CN1 | 02/03/26 | 02/09/26
INTERIORS | Concession Wings - Concourse level | North Restrooms | Manhattan | MCC Completion List - Prepare/Distribute/Complete | #FFFF00 | MH2 | 02/10/26 | 02/23/26
INTERIORS | Concession Wings - Concourse level | North Restrooms | Manhattan | Design Team Punch List & Completion | #FFFF00 | MH3 | 02/24/26 | 03/09/26
INTERIORS | Concession Wings - Concourse level | North Restrooms | Clean | Final Clean | #FDFFB7 | CN2 | 03/10/26 | 03/11/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Framing | Partition Layout & Top Track | #8B4513 | F2 | 09/29/25 | 09/30/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Mechanical | Mechanical Overhead & Riser Rough-in | #008000 | M2 | 10/01/25 | 10/02/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Fire Sprinkler | Fire Protection Overhead | #AD1DC1 | H2 | 10/02/25 | 10/06/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Plumbing | Plumbing/Piping Overhead | #90EE90 | P6 | 10/08/25 | 10/14/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Framing | Frame & One-side Walls | #8B4513 | F3 | 10/13/25 | 10/17/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Plumbing | Plumbing In-wall Rough-in | #90EE90 | P3 | 10/21/25 | 10/27/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Electrical | Elect/LV Rough-in | #0000FF | E7 | 10/22/25 | 10/28/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Inspection | In-Wall QC Check | #59672B | IS1 | 10/29/25 | 10/29/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Inspection | COF In-Wall Inspection | #59672B | IS2 | 10/30/25 | 10/30/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Drywall | Insulate & Close Walls | #81FFFF | DW1 | 10/31/25 | 11/06/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Drywall | Tape/Bed/Prime/ 1st Coat Walls | #81FFFF | DW2 | 11/07/25 | 11/17/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Framing | Frame Hard Ceilings/Soffits | #8B4513 | F4 | 11/18/25 | 11/18/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Mechanical | Install Kitchen Hoods | #008000 | M7 | 11/18/25 | 11/19/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Refrigeration | Install Walk-in Cooler/Freezer | #920000 | RF1 | 11/20/25 | 11/24/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Mechanical | Grease Duct Tie-in/Insulate | #008000 | M3 | 11/20/25 | 11/25/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Ceiling | Install ACT Grid | #B2B202 | Q3 | 11/26/25 | 12/02/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Mechanical | Install Mechanical Devices | #008000 | M4 | 12/03/25 | 12/03/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Electrical | Install FA/LV Pathway | #0000FF | E13 | 12/03/25 | 12/05/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Fire Sprinkler | Drop Sprinkler Heads | #AD1DC1 | H3 | 12/04/25 | 12/04/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Electrical | Install Light Fixtures | #0000FF | E10 | 12/12/25 | 12/16/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Inspection | Overhead QC Inspection | #59672B | IS3 | 12/17/25 | 12/17/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Inspection | COF Overhead Inspections | #59672B | IS4 | 12/18/25 | 12/18/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Drywall | Close Hard Ceilings/Soffits | #81FFFF | DW3 | 12/19/25 | 12/19/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Drywall | Tape/Bed/Paint Ceilings | #81FFFF | DW2 | 12/22/25 | 12/24/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Paint | Final Paint Storage | #F0C8EC | PT1 | 12/26/25 | 12/30/25
INTERIORS | Concession Wings - Concourse level | North Concessions | Flooring | Install Epoxy Flooring/Base | #EB0F87 | FO1 | 12/26/25 | 01/02/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Drywall | Seal Storage Room | #81FFFF | DW4 | 01/02/26 | 01/02/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Specialty | Install Concession Wall Finish | #26EAB2 | Y4 | 01/05/26 | 01/19/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Mechanical | Install Mechanical Wall Units/Air Curtains | #008000 | M5 | 01/20/26 | 01/20/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Equipment | Install Food Service Equipment | #7500F6 | EQ1 | 01/20/26 | 01/26/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Equipment | Install Doors & Hardware | #7500F6 | EQ2 | 01/27/26 | 01/28/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Plumbing | Plumbing Trim-out | #90EE90 | P5 | 01/27/26 | 01/29/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Electrical | Electrical/FA Trim-out | #0000FF | E11 | 01/28/26 | 01/30/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Mechanical | Kitchen Hood Testing | #008000 | M6 | 02/02/26 | 02/02/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Electrical | LV Trim-out | #0000FF | E12 | 02/03/26 | 02/04/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Ceiling | Install ACT Tile | #B2B202 | Q1 | 02/05/26 | 02/06/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Clean | Construction Rough Clean | #FDFFB7 | CN1 | 02/10/26 | 02/12/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Manhattan | MCC Completion List - Prepare/Distribute/Complete | #FFFF00 | MH2 | 02/13/26 | 02/26/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Manhattan | Design Team Punch List & Completion | #FFFF00 | MH3 | 02/27/26 | 03/12/26
INTERIORS | Concession Wings - Concourse level | North Concessions | Clean | Final Clean | #FDFFB7 | CN2 | 03/13/26 | 03/16/26
INTERIORS | Northeast | Concourse Level | Framing | Partition Layout & Top Track | #8B4513 | F2 | 10/17/25 | 10/21/25
INTERIORS | Northeast | Concourse Level | Mechanical | Mechanical Overhead & Riser Rough-in | #008000 | M2 | 10/22/25 | 10/24/25
INTERIORS | Northeast | Concourse Level | Fire Sprinkler | Fire Protection Overhead | #AD1DC1 | H2 | 10/22/25 | 10/24/25
INTERIORS | Northeast | Concourse Level | Plumbing | Plumbing/Piping Overhead | #90EE90 | P6 | 11/03/25 | 11/07/25
INTERIORS | Northeast | Concourse Level | Framing | Frame & One-side Walls | #8B4513 | F3 | 11/04/25 | 11/05/25
INTERIORS | Northeast | Concourse Level | Electrical | Elect/LV Rough-in | #0000FF | E7 | 11/06/25 | 11/11/25
INTERIORS | Northeast | Concourse Level | Inspection | In-Wall QC Check | #59672B | IS1 | 11/12/25 | 11/12/25
INTERIORS | Northeast | Concourse Level | Inspection | COF In-Wall Inspection | #59672B | IS2 | 11/13/25 | 11/13/25
INTERIORS | Northeast | Concourse Level | Drywall | Insulate & Close Walls | #81FFFF | DW1 | 11/14/25 | 11/18/25
INTERIORS | Northeast | Concourse Level | Drywall | Tape/Bed/Prime/ 1st Coat Walls | #81FFFF | DW2 | 11/19/25 | 12/01/25
INTERIORS | Northeast | Concourse Level | Mechanical | Install Kitchen Hoods | #008000 | M7 | 12/02/25 | 12/02/25
INTERIORS | Northeast | Concourse Level | Framing | Frame Hard Ceilings/Soffits | #8B4513 | F4 | 12/02/25 | 12/02/25
INTERIORS | Northeast | Concourse Level | Specialty | Install Counter Shutters | #26EAB2 | Y3 | 12/02/25 | 12/08/25
INTERIORS | Northeast | Concourse Level | Mechanical | Grease Duct Tie-in/Insulate | #008000 | M3 | 12/03/25 | 12/08/25
INTERIORS | Northeast | Concourse Level | Refrigeration | Install Walk-in Cooler/Freezer | #920000 | RF1 | 12/03/25 | 12/08/25
INTERIORS | Northeast | Concourse Level | Ceiling | Install ACT Grid | #B2B202 | Q3 | 12/09/25 | 12/11/25
INTERIORS | Northeast | Concourse Level | Mechanical | Install Mechanical Devices | #008000 | M4 | 12/12/25 | 12/15/25
INTERIORS | Northeast | Concourse Level | Electrical | Install FA/LV Pathway | #0000FF | E13 | 12/12/25 | 12/15/25
INTERIORS | Northeast | Concourse Level | Electrical | Install Light Fixtures | #0000FF | E10 | 12/12/25 | 12/16/25
INTERIORS | Northeast | Concourse Level | Fire Sprinkler | Drop Sprinkler Heads | #AD1DC1 | H3 | 12/16/25 | 12/16/25
INTERIORS | Northeast | Concourse Level | Inspection | Overhead QC Inspection | #59672B | IS3 | 12/17/25 | 12/17/25
INTERIORS | Northeast | Concourse Level | Inspection | COF Overhead Inspections | #59672B | IS4 | 12/18/25 | 12/18/25
INTERIORS | Northeast | Concourse Level | Drywall | Close Hard Ceilings/Soffits | #81FFFF | DW3 | 12/19/25 | 12/19/25
INTERIORS | Northeast | Concourse Level | Drywall | Tape/Bed/Paint Ceilings | #81FFFF | DW2 | 12/22/25 | 12/29/25
INTERIORS | Northeast | Concourse Level | Paint | Final Paint Storage | #F0C8EC | PT1 | 01/06/26 | 01/08/26
INTERIORS | Northeast | Concourse Level | Flooring | Install Epoxy Flooring/Base | #EB0F87 | FO1 | 01/06/26 | 01/13/26
INTERIORS | Northeast | Concourse Level | Drywall | Seal MEP/Storage Rooms | #81FFFF | DW4 | 01/14/26 | 01/14/26
INTERIORS | Northeast | Concourse Level | Tile | Install Restroom Wall Tile | #5A8787 | TE1 | 01/14/26 | 01/19/26
INTERIORS | Northeast | Concourse Level | Specialty | Install Concession Wall Finish | #26EAB2 | Y4 | 01/14/26 | 01/29/26
INTERIORS | Northeast | Concourse Level | Plumbing | Install Plumbing Fixtures | #90EE90 | P4 | 01/20/26 | 01/23/26
INTERIORS | Northeast | Concourse Level | Specialty | Install Toilet Partions | #26EAB2 | Y10 | 01/26/26 | 01/30/26
INTERIORS | Northeast | Concourse Level | Specialty | Install Toilet Accessories | #26EAB2 | Y7 | 01/29/26 | 01/30/26
INTERIORS | Northeast | Concourse Level | Equipment | Install Food Service Equipment | #7500F6 | EQ1 | 01/30/26 | 02/03/26
INTERIORS | Northeast | Concourse Level | Mechanical | Install Mechanical Wall Units/Air Curtains | #008000 | M5 | 01/30/26 | 02/03/26
INTERIORS | Northeast | Concourse Level | Equipment | Install Doors & Hardware | #7500F6 | EQ2 | 02/04/26 | 02/05/26
INTERIORS | Northeast | Concourse Level | Electrical | Electrical/FA Trim-out | #0000FF | E11 | 02/04/26 | 02/06/26
INTERIORS | Northeast | Concourse Level | Plumbing | Plumbing Trim-out | #90EE90 | P5 | 02/06/26 | 02/09/26
INTERIORS | Northeast | Concourse Level | Mechanical | Kitchen Hood Testing | #008000 | M6 | 02/09/26 | 02/09/26
INTERIORS | Northeast | Concourse Level | Electrical | LV Trim-out | #0000FF | E12 | 02/09/26 | 02/10/26
INTERIORS | Northeast | Concourse Level | Ceiling | Install ACT Tile | #B2B202 | Q1 | 02/11/26 | 02/12/26
INTERIORS | Northeast | Concourse Level | Clean | Construction Rough Clean | #FDFFB7 | CN1 | 02/13/26 | 02/19/26
INTERIORS | Northeast | Concourse Level | Manhattan | MCC Completion List - Prepare/Distribute/Complete | #FFFF00 | MH2 | 02/20/26 | 03/05/26
INTERIORS | Northeast | Concourse Level | Manhattan | Design Team Punch List & Completion | #FFFF00 | MH3 | 03/06/26 | 03/19/26
INTERIORS | Northeast | Concourse Level | Clean | Final Clean | #FDFFB7 | CN2 | 03/20/26 | 03/23/26
INTERIORS | Seating Bowl - Main Building | Concourse Level | Concrete | Pour Bowl Steps | #595959 | C14 | 03/04/26 | 03/25/26
INTERIORS | Seating Bowl - Main Building | Concourse Level | Miscellaneous | Install Bowl Rails | #B8EE0C | MS2 | 03/26/26 | 04/08/26
INTERIORS | Seating Bowl - Main Building | Concourse Level | Equipment | Install Stadium Seats | #7500F6 | EQ4 | 04/09/26 | 05/13/26
INTERIORS | Seating Bowl - Main Building | Concourse Level | Clean | Construction Rough Clean | #FDFFB7 | CN1 | 05/14/26 | 05/28/26
INTERIORS | Seating Bowl - Main Building | Concourse Level | Manhattan | MCC Completion List | #FFFF00 | MH2 | 05/29/26 | 06/11/26
INTERIORS | Seating Bowl - Main Building | Concourse Level | Manhattan | Design Team Punch List & Complete | #FFFF00 | MH3 | 06/12/26 | 06/25/26
INTERIORS | Seating Bowl - Main Building | Concourse Level | Clean | Final Clean | #FDFFB7 | CN2 | 06/26/26 | 06/29/26
INTERIORS | Closeout/Commissioning | Closeout/Commissioning | MEP | Closeout/Commissioning | #7CEE2E | I4 | 04/08/26 | 06/30/26
INTERIORS | Hositing | Tower Crane 1 | Concrete | Drill Tower Crane Piers | #595959 | C1 | 04/11/25 | 04/14/25
INTERIORS | Hositing | Tower Crane 1 | Concrete | Install Tower Crane Foundations | #595959 | C15 | 04/15/25 | 05/05/25
INTERIORS | Hositing | Tower Crane 1 | Crane | Tower Crane Erection | #4202A0 | R1 | 05/06/25 | 05/12/25
INTERIORS | Hositing | Tower Crane 1 | Crane | Tower Crane Duration | #4202A0 | R2 | 05/06/25 | 05/01/26
INTERIORS | Hositing | Tower Crane 1 | Crane | Tower Crane Dismantle | #4202A0 | R3 | 04/27/26 | 05/01/26
INTERIORS | Hositing | Tower Crane 2 | Concrete | Drill Tower Crane Piers | #595959 | C1 | 04/09/25 | 04/10/25
INTERIORS | Hositing | Tower Crane 2 | Concrete | Install Tower Crane Foundations | #595959 | C15 | 04/11/25 | 05/01/25
INTERIORS | Hositing | Tower Crane 2 | Crane | Tower Crane Erection | #4202A0 | R1 | 05/02/25 | 05/08/25
INTERIORS | Hositing | Tower Crane 2 | Crane | Tower Crane Duration | #4202A0 | R2 | 05/02/25 | 05/08/26
INTERIORS | Hositing | Tower Crane 2 | Crane | Tower Crane Dismantle | #4202A0 | R3 | 05/04/26 | 05/08/26
South HOF | South | South | Electrical | Relocate HOF transformer | #0000FF | E15 | 08/20/25 | 09/02/25
South HOF | Main Building | Roof Level | Steel | Open Roof for Steel& Sleeves | #DBD997 | S11 | 07/03/25 | 07/03/25
South HOF | Main Building | Roof Level | Steel | Added Roof Steel | #DBD997 | S12 | 07/07/25 | 07/09/25
South HOF | Main Building | Roof Level | Roofing | Repair Roofing System | #FFD78F | SG | 07/10/25 | 07/11/25
South HOF | Main Building | Field Level | Equipment | Install Field Tunnel Cameras | #7500F6 | EQ5 | 10/21/25 | 10/27/25
South HOF | Main Building | Concourse Level | Demolition | Slab Demo & Removal for gas line | #000000 | O3 | 03/12/25 | 03/13/25
South HOF | Main Building | Concourse Level | Plumbing | Install new gas line | #90EE90 | P7 | 03/14/25 | 03/18/25
South HOF | Main Building | Roof Level | Plumbing | Install new gas line | #90EE90 | P7 | 03/19/25 | 03/21/25
South HOF | Main Building | Roof Level | Electrical | Install Generator | #0000FF | E16 | 08/06/25 | 08/12/25
South HOF | Main Building | Roof Level | Audovisual | Install New Bowl Speakers | #CDE2FF | AV1 | 12/31/25 | 01/15/26
South HOF | Main Building | Roof Level | Electrical | Generator Start-up & Commissioning | #0000FF | E17 | 08/13/25 | 08/19/25

## CFA - Schedule
|  |  | 2023 | [6 empty] | 2023 | [6 empty] | 2023 | [6 empty] | 2023 | [6 empty] | 2023 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 | [6 empty] | 2024 |  | 2025 |  |  |  |  | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 | [6 empty] | 2025 |  |  | 2026 |  |  |  | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 | [6 empty] | 2026 |  |  |  | 2027 |  |  | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 | [6 empty] | 2027 |  |  |  |  | 2028 |  | 2028 | [6 empty] | 2028 | [6 empty] | 2028 | [6 empty] | 2028 | [6 empty] | 2028
|  |  | Nov |  |  |  | Dec |  |  | Dec | [6 empty] | Dec | [6 empty] | Dec | [6 empty] | Dec | [6 empty] | Jan | [6 empty] | Jan | [6 empty] | Jan | [6 empty] | Jan | [6 empty] | Jan |  |  | Feb |  |  |  | Feb | [6 empty] | Feb | [6 empty] | Feb | [6 empty] | Feb |  |  |  | Mar |  |  | Mar | [6 empty] | Mar | [6 empty] | Mar | [6 empty] | Mar | [6 empty] | Apr | [6 empty] | Apr | [6 empty] | Apr | [6 empty] | Apr | [6 empty] | Apr |  | May |  |  |  |  | May | [6 empty] | May | [6 empty] | May | [6 empty] | May |  |  |  |  | Jun |  | Jun | [6 empty] | Jun | [6 empty] | Jun | [6 empty] | Jun | [6 empty] | Jul | [6 empty] | Jul | [6 empty] | Jul | [6 empty] | Jul | [6 empty] | Jul |  |  | Aug |  |  |  | Aug | [6 empty] | Aug | [6 empty] | Aug | [6 empty] | Aug | [5 empty] | Sep | Sep | [6 empty] | Sep | [6 empty] | Sep | [6 empty] | Sep | [6 empty] | Sep | Oct | [5 empty] | Oct | [6 empty] | Oct | [6 empty] | Oct | [6 empty] | Oct |  |  |  | Nov |  |  | Nov | [6 empty] | Nov | [6 empty] | Nov | [6 empty] | Nov | [5 empty] | Dec | Dec | [6 empty] | Dec | [6 empty] | Dec | [6 empty] | Dec | [6 empty] | Dec |  | Jan |  |  |  |  | Jan | [6 empty] | Jan | [6 empty] | Jan | [6 empty] | Jan |  |  |  |  | Feb |  | Feb | [6 empty] | Feb | [6 empty] | Feb | [6 empty] | Feb |  |  |  |  | Mar |  | Mar | [6 empty] | Mar | [6 empty] | Mar | [6 empty] | Mar | [6 empty] | Mar | Apr | [5 empty] | Apr | [6 empty] | Apr | [6 empty] | Apr | [6 empty] | Apr |  |  | May |  |  |  | May | [6 empty] | May | [6 empty] | May | [6 empty] | May | [5 empty] | Jun | Jun | [6 empty] | Jun | [6 empty] | Jun | [6 empty] | Jun | [6 empty] | Jun | Jul | [5 empty] | Jul | [6 empty] | Jul | [6 empty] | Jul | [6 empty] | Jul |  |  |  | Aug |  |  | Aug | [6 empty] | Aug | [6 empty] | Aug | [6 empty] | Aug | [6 empty] | Sep | [6 empty] | Sep | [6 empty] | Sep | [6 empty] | Sep | [6 empty] | Sep |  | Oct |  |  |  |  | Oct | [6 empty] | Oct | [6 empty] | Oct | [6 empty] | Oct |  |  |  |  | Nov |  | Nov | [6 empty] | Nov | [6 empty] | Nov | [6 empty] | Nov | [6 empty] | Dec | [6 empty] | Dec | [6 empty] | Dec | [6 empty] | Dec | [6 empty] | Dec |  |  | Jan |  |  |  | Jan | [6 empty] | Jan | [6 empty] | Jan | [6 empty] | Jan | [5 empty] | Feb | Feb | [6 empty] | Feb | [6 empty] | Feb | [6 empty] | Feb | [5 empty] | Mar | Mar | [6 empty] | Mar | [6 empty] | Mar | [6 empty] | Mar | [6 empty] | Mar |  | Apr |  |  |  |  | Apr | [6 empty] | Apr | [6 empty] | Apr | [6 empty] | Apr |  |  |  | May |  |  | May | [6 empty] | May | [6 empty] | May | [6 empty] | May | [6 empty] | Jun | [6 empty] | Jun | [6 empty] | Jun | [6 empty] | Jun | [6 empty] | Jun |  | Jul |  |  |  |  | Jul | [6 empty] | Jul | [6 empty] | Jul | [6 empty] | Jul |  |  |  |  | Aug |  | Aug | [6 empty] | Aug | [6 empty] | Aug | [6 empty] | Aug | [6 empty] | Aug | Sep | [5 empty] | Sep | [6 empty] | Sep | [6 empty] | Sep | [6 empty] | Sep |  |  | Oct |  |  |  | Oct | [6 empty] | Oct | [6 empty] | Oct | [6 empty] | Oct | [5 empty] | Nov | Nov | [6 empty] | Nov | [6 empty] | Nov | [6 empty] | Nov | [6 empty] | Nov | Dec | [5 empty] | Dec | [6 empty] | Dec | [6 empty] | Dec | [6 empty] | Dec |  |  |  | Jan |  |  | Jan | [6 empty] | Jan | [6 empty] | Jan | [6 empty] | Jan | [6 empty] | Feb | [6 empty] | Feb | [6 empty] | Feb | [6 empty] | Feb | [6 empty] | Mar | [6 empty] | Mar | [6 empty] | Mar | [6 empty] | Mar | [6 empty] | Mar |  |  | Apr |  |  |  | Apr | [6 empty] | Apr | [6 empty] | Apr | [6 empty] | Apr |  |  |  |  | May |  | May | [6 empty] | May | [6 empty] | May | [6 empty] | May | [6 empty] | May | Jun | [5 empty] | Jun | [6 empty] | Jun | [6 empty] | Jun | [6 empty] | Jun |  |  | Jul |  |  |  | Jul | [6 empty] | Jul | [6 empty] | Jul | [6 empty] | Jul | [5 empty] | Aug | Aug | [6 empty] | Aug | [6 empty] | Aug | [6 empty] | Aug | [6 empty] | Aug |  | Sep |  |  |  |  | Sep | [6 empty] | Sep | [6 empty] | Sep | [6 empty] | Sep |  |  |  | Oct |  |  | Oct | [6 empty] | Oct | [6 empty] | Oct | [6 empty] | Oct | [6 empty] | Nov | [6 empty] | Nov | [6 empty] | Nov | [6 empty] | Nov | [6 empty] | Nov |  | Dec |  |  |  |  | Dec | [6 empty] | Dec | [6 empty] | Dec | [6 empty] | Dec |  |  |  |  | Jan |  | Jan | [6 empty] | Jan | [6 empty] | Jan | [6 empty] | Jan | [6 empty] | Jan | Feb
|  |  | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04
phase | location | area | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Procurement | Canopies | Canopies | bar: Apr 16 to Sep 26; Sep 29 to Mar 20; Mar 23 to Apr 17
[587 empty] | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR
| Foundations | Foundations | bar: Feb 05 to Apr 08
| Interiors | Interiors | bar: Apr 28 to Sep 02; Oct 28 to Jan 04
| MEP/LV | MEP/LV | bar: Mar 03 to Mar 21; Mar 24 to Apr 11; Apr 14 to Aug 05
[465 empty] | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR |  |  | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR |  |  |  | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR
| Material | Material | bar: Nov 04 to Nov 08; Nov 11 to Jan 31; Feb 03 to Feb 04; Feb 19 to Feb 21; Feb 24 to Apr 25
[353 empty] | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | [27 empty] | PR | PR | PR | PR | PR
[353 empty] | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | [27 empty] | PR | PR | PR | PR | PR
[353 empty] | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | [27 empty] | PR | PR | PR | PR | PR
[437 empty] | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR
[437 empty] | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR
[437 empty] | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR
[437 empty] | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR
[437 empty] | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR
| Structural Steel | Structural Steel | bar: Feb 05 to May 06; May 21 to Jul 31
[446 empty] | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR
[446 empty] | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR | PR
| Vertical | Vertical | bar: Feb 24 to Apr 04; Jan 23 to Oct 27
MILESTONES/HAMMOCKS | Canopy | Canopy | Jul 28: M/H
| Conditioned Air | Conditioned Air | Jan 21: M/H
| Dry-in | Dry-in | Nov 06: M/H
| Structure | Structure | Oct 02: M/H
| TCO | TCO | Jun 30: M/H
MAJOR MILESTONES | All | All | bar: Feb 03; Dec 02 to Feb 04
MM
| East | East | bar: Feb 18; Jun 30
[452 empty] | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM
| North | North | bar: Jul 22; Nov 29
[971 empty] | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM
| Phase 1 | Phase 1 | bar: Jun 30
| Phase 2 | Phase 2 | bar: Dec 01
| West | West | bar: May 18; Dec 01
[906 empty] | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM | MM
SCHEMATIC DESIGN | Design | Design | bar: Nov 27 to Apr 08
DESIGN DEVELOPMENT | Design | Design | bar: Apr 09 to Apr 26; Apr 29 to May 17; Jun 24 to Jul 22
[157 empty] | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD |  |  | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD
[157 empty] | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD | DD
PERMIT PACKAGE | Canopy | Canopy | bar: May 31 to Aug 30
| Civil | Civil | bar: May 31 to Aug 30
| Foundations | Foundations | bar: May 31 to Aug 30
| Permit | Permit | bar: Sep 02 to Nov 01
| Steel | Steel | bar: May 31 to Aug 30
CONSTRUCTION DOCUMENTS | Documents | Documents | bar: Jun 24 to Nov 01; Nov 04 to Jan 30
[346 empty] | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD | CD
[357 empty] | CD | [6 empty] | CD | [25 empty] | CD | [21 empty] | CD |  |  |  | CD
PERMITS | All | All | bar: Jan 13 to Jan 14
| East | East | bar: Sep 09 to Nov 04; Nov 11 to Feb 11
[291 empty] | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | [92 empty] | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT | PT
| Facade | Facade | bar: Nov 11 to Dec 16; Dec 24 to Jan 28
[388 empty] | PT | PT | PT | PT | PT | PT | PT | PT
| West | West | bar: Nov 11 to Dec 16; Dec 24 to Feb 18; Feb 26 to Mar 18
[388 empty] | PT | PT | PT | PT | PT | PT | PT | PT
DEMOLITION | East | East | Jan 07: T1; Jan 08: T1; Jan 09: T1; Jan 10: T1; Jan 11: T1; Jan 12: T1; Jan 13: T1; Jan 14: T1; Jan 15: T1; Jan 16: T1; Jan 17: T1; Jan 18: T1; Jan 19: T1; Jan 20: T1; Jan 21: T1; Jan 22: T1; Jan 23: T1; Jan 24: T1; Jan 25: T1; Jan 26: T1; Jan 27: T1; Jan 28: T1; Jan 29: T1; Jan 30: T1; Jan 31: T1; Feb 01: T1; Feb 02: T1; Feb 03: T1; Feb 04: MH1; Feb 05: MH1; Feb 06: MH1; Feb 07: MH1; Feb 08: MH1; Feb 09: MH1; Feb 10: MH1; Feb 11: MH1; Feb 12: MH1; Feb 13: MH1; Feb 14: MH1; Feb 15: MH1; Feb 16: MH1; Feb 17: MH1; Feb 26: I1; Feb 27: I1; Feb 28: I1; Mar 01: I1; Mar 02: I1; Mar 03: I1; Mar 04: I1; Mar 05: I1; Mar 06: I1; Mar 07: I1; Mar 08: I1; Mar 09: I1; Mar 10: I1; Mar 11: I1; Mar 17: O2; Mar 18: O2; Mar 19: O2; Mar 20: O2; Mar 21: O2; Mar 22: O2; Mar 23: O2; Mar 24: O2; Mar 25: O2; Mar 26: O2; Mar 27: O2; Mar 28: O2; Mar 29: O2; Mar 30: O2; Mar 31: O2; Apr 01: O2; Apr 02: O2; Apr 03: O2; Apr 04: O2
[467 empty] | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1
FOUNDATIONS | Concession Wings | Concession Wings | May 12: C1; May 13: C1; May 14: C1; May 15: C1; May 16: C1; May 19: C1; May 20: C1; May 21: C1; May 22: C1; May 23: C1; Jun 10: P1; Jun 11: P1; Jun 12: P1; Jun 13: P1; Jun 14: P1; Jun 15: P1; Jun 16: P1; Jun 17: P1; Jun 18: P1; Jun 19: P1; Jun 20: P1; Jun 21: P1; Jun 22: P1; Jun 23: P1; Jul 01: C5; Jul 02: C5; Jul 03: C5; Jul 04: C5; Jul 05: C5; Jul 06: C5; Jul 07: C5; Jul 08: C5; Jul 09: C5; Jul 10: C5; Jul 11: C5; Jul 12: C5; Jul 13: C5; Jul 14: C5; Jul 15: C5; Jul 16: C5; Jul 17: C5; Jul 18: C5; Jul 19: C5; Jul 20: C5; Jul 21: C5; Jul 22: C5; Jul 28: C6; Jul 29: C6; Jul 30: C6; Jul 31: C6; Aug 01: C6; Aug 02: C6; Aug 03: C6; Aug 04: C6; Aug 05: C6; Aug 06: C6; Aug 07: C6; Aug 08: C6; Aug 09: C6; Aug 10: C6; Aug 11: C6; Aug 12: C6; Aug 13: C6; Aug 14: C6; Aug 15: C6
[542 empty] | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 |  |  |  | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1
[571 empty] | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | [13 empty] | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1
| Main building - Concourse Level | SEQ.1 | Apr 15: C1; Apr 16: C1; Apr 17: C1; Apr 18: C2; Apr 19: C2; Apr 20: C2; Apr 21: C2; Apr 22: C2; Apr 23: C2; Apr 25: P1; Apr 26: P1; Apr 27: P1; Apr 28: P1; Apr 29: P1; Apr 30: P1; May 01: P1; May 02: E1; May 03: E1; May 04: E1; May 05: E1; May 06: E1; May 07: E1; May 08: E1; May 09: C5; May 10: C5; May 11: C5; May 12: C5; May 13: C5; May 14: C5; May 15: C5; May 16: C6; May 17: C6; May 18: C6; May 19: C6; May 20: C6; May 21: C6; May 22: C6
[511 empty] | C3 | C3 | C3 | C3 | C3 | C3 | C3 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | C4 | C4 | C4 | C4 | C4 | C4 | C4
|  | SEQ.2 | Apr 18: C1; Apr 19: C1; Apr 20: C1; Apr 21: C1; Apr 22: C1; Apr 23: C1; Apr 24: C1; Apr 25: C1; Apr 26: C1; Apr 27: C1; Apr 28: C1; Apr 29: C1; Apr 30: C1; May 07: W1; May 08: W1; May 09: K1; May 10: K1; May 11: K1; May 12: K1; May 13: K1; May 15: C4; May 16: C4; May 17: C4; May 18: C4; May 19: C4; May 20: C4; May 21: C4; May 22: C4; May 23: C4; May 24: C4; May 25: C4; May 26: C4; May 27: C4; May 28: C4; May 29: C4; Jun 03: C5; Jun 04: C5; Jun 05: C5; Jun 06: C5; Jun 07: C5; Jun 08: C5; Jun 09: C5; Jun 10: C6; Jun 11: C6; Jun 12: C6; Jun 13: C6; Jun 14: C6; Jun 15: C6; Jun 16: C6
[518 empty] | C2 | C2 | C2 | C2 | C2 | C2 | [7 empty] | P1 | P1 | P1 | P1 | P1 | P1 | P1 |  | C5 | C5 | C5 | C5 | C5 | C5 | C5 | C6 | C6 | C6 | C6 | C6 | C6 | C6 | C6
[518 empty] | C7 | C7 | C7 | C7 | C7 | C7 | C7 | C7 | C7 | C7 | C7 | C7 |  | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 |  |  | P1 | P1 | P1 | P1 | P1 |  |  |  | E1 | E1 | E1 | E1 | E1 | E1 | E1
[521 empty] | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 |  | E1 | E1 | E1 | E1 | E1 | E1 | E1
[536 empty] | C2 | C2 | C2 | C2
|  | SEQ.3 | May 01: C1; May 02: C1; May 03: C1; May 04: C1; May 05: C1; May 06: C1; May 07: C1; May 19: C2; May 20: C2; May 21: C2; May 22: C2; May 30: W1; May 31: W1; Jun 01: W1; Jun 02: W1; Jun 03: K1; Jun 04: K1; Jun 05: K1; Jun 09: E1; Jun 10: E1; Jun 11: E1; Jun 12: E1; Jun 13: E1; Jun 16: C5; Jun 17: C5; Jun 18: C5; Jun 19: C5; Jun 20: C5; Jun 23: C6; Jun 24: C6; Jun 25: C6; Jun 26: C6; Jun 27: C6
[542 empty] | C7 | C7 | C7 | C7 | C7 | C7 | C7 | C7 | C7 | C7 | C7 |  |  |  | C4 | C4 | C4 | C4 | C4
[543 empty] | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 | C3 |  |  | P1 | P1 | P1 | P1 | P1
|  | SEQ.4 | May 08: C1; May 09: C1; May 30: C2; May 31: C2; Jun 01: C2; Jun 02: C2; Jun 03: C2; Jun 04: C2; Jun 06: S1; Jun 07: S1; Jun 08: S1; Jun 09: S1; Jun 10: S1; Jun 11: S1; Jun 12: S1; Jun 13: S1; Jun 14: S1; Jun 15: S1; Jun 16: S1; Jun 17: S1; Jun 18: S1; Jun 19: C4; Jun 20: C4; Jun 21: C4; Jun 22: C4; Jun 23: C4; Jun 24: C4; Jun 25: C4; Jun 30: C6; Jul 01: C6; Jul 02: C6; Jul 03: C6; Jul 04: C6; Jul 05: C6; Jul 06: C6; Jul 07: C6
[556 empty] | C3 | C3 | C3 | C3 |  |  |  | P1 | P1 | P1 | P1 | P1 |  |  | E1 | E1 | E1 | E1 | E1 |  |  | C5 | C5 | C5 | C5 | C5
| Northeast | Northeast | Jul 01: K2; Jul 02: K2; Jul 03: K2; Jul 07: C8; Jul 08: C8; Jul 09: C8; Jul 10: C8; Jul 11: C8; Jul 14: C8; Jul 15: C8; Jul 16: C8; Jul 17: C8; Jul 18: C8; Jul 21: C9; Jul 22: C9; Jul 23: C9; Jul 24: C9; Jul 25: C9; Jul 28: C8; Jul 29: C8; Jul 30: C8; Jul 31: C8; Aug 01: C8; Aug 02: C8; Aug 03: C8; Aug 04: C8; Aug 05: G1; Aug 06: G1; Aug 07: G1; Aug 08: G1; Aug 09: G1; Aug 10: G1; Aug 11: G1; Aug 12: I2; Aug 13: I2; Aug 14: I2; Aug 15: I2; Aug 16: I2; Aug 17: I2; Aug 18: I2; Aug 19: I2; Aug 20: I2; Aug 21: I2; Aug 22: C6; Aug 23: C6; Aug 24: C6; Aug 25: C6; Aug 26: C6
South HOF | Main Building | Concourse Level | bar: Mar 12 to Mar 18
|  | Field Level | Oct 21: EQ5; Oct 22: EQ5; Oct 23: EQ5; Oct 24: EQ5; Oct 25: EQ5; Oct 26: EQ5; Oct 27: EQ5
|  | Roof Level | Mar 19: P7; Mar 20: P7; Mar 21: P7; Jul 03: S11; Jul 07: S12; Jul 08: S12; Jul 09: S12; Jul 10: SG; Jul 11: SG; Aug 06: E16; Aug 07: E16; Aug 08: E16; Aug 09: E16; Aug 10: E16; Aug 11: E16; Aug 12: E16; Aug 13: E17; Aug 14: E17; Aug 15: E17; Aug 16: E17; Aug 17: E17; Aug 18: E17; Aug 19: E17; Dec 31: AV1; Jan 01: AV1; Jan 02: AV1; Jan 03: AV1; Jan 04: AV1; Jan 05: AV1; Jan 06: AV1; Jan 07: AV1; Jan 08: AV1; Jan 09: AV1; Jan 10: AV1; Jan 11: AV1; Jan 12: AV1; Jan 13: AV1; Jan 14: AV1; Jan 15: AV1
| South | South | Aug 20: E15; Aug 21: E15; Aug 22: E15; Aug 23: E15; Aug 24: E15; Aug 25: E15; Aug 26: E15; Aug 27: E15; Aug 28: E15; Aug 29: E15; Aug 30: E15; Aug 31: E15; Sep 01: E15; Sep 02: E15
STRUCTURE | Concession Wings | North | bar: Aug 05 to Aug 18
South | bar: Aug 19 to Sep 01
| Main building - All | SEQ. 1E | bar: Jul 03 to Jul 09; Jul 14 to Jul 17
SEQ. 2E | bar: Jul 09 to Jul 16; Jul 18 to Jul 25
SEQ. 3E | bar: Jul 16 to Jul 23; Jul 28 to Aug 04
SEQ. 4E | bar: Jul 23 to Jul 30; Aug 05 to Aug 12
SEQ. 5E | bar: Jul 30 to Aug 04; Aug 13 to Aug 18
| Main building - Lower Suite Level | SEQ. 1E | Jul 21: I3; Jul 22: I3; Jul 23: I3; Jul 24: I3; Jul 25: I3; Jul 28: C10; Jul 29: C10; Jul 30: C10; Jul 31: C10; Aug 01: C10
|  | SEQ. 2E | Jul 28: I3; Jul 29: I3; Jul 30: I3; Jul 31: I3; Aug 01: I3; Aug 04: C10; Aug 05: C10; Aug 06: C10; Aug 07: C10; Aug 08: C10
|  | SEQ. 3E | Aug 05: I3; Aug 06: I3; Aug 07: I3; Aug 08: I3; Aug 09: I3; Aug 10: I3; Aug 11: I3; Aug 12: C10; Aug 13: C10; Aug 14: C10; Aug 15: C10; Aug 16: C10; Aug 17: C10; Aug 18: C10; Aug 19: C10
|  | SEQ. 4E | Aug 13: I3; Aug 14: I3; Aug 15: I3; Aug 16: I3; Aug 17: I3; Aug 18: I3; Aug 19: I3; Aug 20: C10; Aug 21: C10; Aug 22: C10; Aug 23: C10; Aug 24: C10; Aug 25: C10; Aug 26: C10; Aug 27: C10
|  | SEQ. 5E | Aug 20: I3; Aug 21: I3; Aug 22: I3; Aug 23: I3; Aug 24: I3; Aug 25: I3; Aug 26: I3; Aug 28: C10; Aug 29: C10; Aug 30: C10; Aug 31: C10; Sep 01: C10; Sep 02: C10; Sep 03: C10
| Main building - Roof Level | SEQ. 1E | bar: Aug 07 to Aug 18
SEQ. 2E | bar: Aug 19 to Aug 28
SEQ. 3E | bar: Aug 05 to Aug 11; Aug 29 to Sep 10
SEQ. 4E | bar: Sep 11 to Sep 22
SEQ. 5E | bar: Sep 23 to Oct 02
| Northeast | Northeast | bar: Sep 02 to Sep 16
EXTERIORS | Concession Wings - Concourse Level | NEC | Aug 19: F1; Aug 20: F1; Aug 21: F1; Aug 22: F1; Aug 23: F1; Aug 24: F1; Aug 25: F1; Aug 26: F1; Aug 27: F1; Aug 28: F1; Aug 29: F1; Aug 30: F1; Aug 31: F1; Sep 01: F1; Sep 02: W2; Sep 03: W2; Sep 04: W2; Sep 05: W2; Sep 09: R1; Sep 10: R1; Sep 11: R1; Sep 12: R1; Sep 13: R1; Sep 14: R1; Sep 15: R1; Sep 16: R1; Sep 17: R1; Sep 18: R1; Sep 19: R1; Sep 20: R1; Sep 21: R1; Sep 22: R1; Sep 23: R1; Sep 24: R1; Sep 25: R1; Sep 26: R1; Sep 27: R1; Sep 28: R1; Sep 29: R1; Sep 30: R1; Oct 01: R1; Oct 02: R1; Oct 03: R1; Oct 04: R1; Oct 05: R1; Oct 06: R1; Oct 07: R1; Oct 08: R1; Oct 09: R1; Oct 10: R1; Oct 11: R1; Oct 12: R1; Oct 13: R1; Oct 14: R1; Oct 15: R1; Oct 16: R1; Oct 17: R1; Oct 18: R1; Oct 19: R1; Oct 20: R1; Oct 21: R1; Oct 22: R1; Oct 23: R1; Oct 24: R1; Oct 25: R1; Oct 26: R1; Oct 27: R1; Oct 28: R1; Oct 30: MP3; Oct 31: MP3; Nov 01: MP3; Nov 02: MP3; Nov 03: MP3; Nov 04: MP3; Nov 05: MP3; Nov 06: MP3; Nov 07: MP3; Nov 08: MP3; Nov 09: MP3; Nov 10: MP3; Nov 11: MP3; Nov 12: MP3; Nov 13: MP3; Nov 14: MP3; Nov 15: MP3; Nov 16: MP3; Nov 17: MP3; Nov 18: MP3; Nov 19: MP3; Nov 20: E6; Nov 21: E6; Nov 22: E6; Nov 23: E6; Nov 24: E6; Nov 25: E6; Nov 26: E6
|  | SEC | Sep 02: F1; Sep 03: F1; Sep 04: F1; Sep 05: F1; Sep 06: F1; Sep 07: F1; Sep 08: F1; Sep 09: F1; Sep 10: F1; Sep 11: F1; Sep 12: F1; Sep 13: F1; Sep 14: F1; Sep 15: F1; Sep 16: F1; Sep 17: W2; Sep 18: W2; Sep 19: W2; Sep 22: R1; Sep 23: R1; Sep 24: R1; Sep 25: R1; Sep 26: R1; Sep 27: R1; Sep 28: R1; Sep 29: R1; Sep 30: R1; Oct 01: R1; Oct 02: R1; Oct 03: R1; Oct 04: R1; Oct 05: R1; Oct 06: R1; Oct 07: R1; Oct 08: R1; Oct 09: R1; Oct 10: R1; Oct 11: R1; Oct 12: R1; Oct 13: R1; Oct 14: R1; Oct 15: R1; Oct 16: R1; Oct 17: R1; Oct 18: R1; Oct 19: R1; Oct 20: R1; Oct 21: R1; Oct 22: Z2; Oct 23: Z2; Oct 24: Z2; Oct 25: Z2; Oct 26: Z2; Oct 27: Z2; Oct 28: Z2; Oct 29: Z2; Oct 30: Z2; Oct 31: Z2; Nov 01: Z2; Nov 02: Z2; Nov 03: Z2; Nov 04: Z2; Dec 01: MP3; Dec 02: MP3; Dec 03: MP3; Dec 04: MP3; Dec 05: MP3; Dec 06: MP3; Dec 07: MP3; Dec 08: MP3; Dec 09: MP3; Dec 10: MP3; Dec 11: MP3; Dec 12: MP3; Dec 13: MP3; Dec 14: MP3; Dec 15: MP3; Dec 16: MP3; Dec 17: MP3; Dec 18: MP3; Dec 19: MP3; Dec 22: E6; Dec 23: E6; Dec 24: E6; Dec 25: E6; Dec 26: E6; Dec 27: E6; Dec 28: E6; Dec 29: E6
| Concourse Level | North | Aug 11: F1; Aug 12: F1; Aug 13: F1; Aug 14: F1; Aug 15: F1; Aug 16: F1; Aug 17: F1; Aug 18: F1; Aug 19: F1; Aug 20: F1; Aug 21: F1; Aug 22: F1; Aug 25: Y1; Aug 26: Y1; Aug 28: R1; Aug 29: R1; Aug 30: R1; Aug 31: R1; Sep 01: R1; Sep 02: R1; Sep 03: R1; Sep 04: R1; Sep 05: R1; Sep 06: R1; Sep 07: R1; Sep 08: R1; Sep 09: R1; Sep 10: R1; Sep 11: R1; Sep 12: R1; Sep 13: R1; Sep 14: R1; Sep 15: R1; Sep 16: R1; Sep 17: R1; Sep 18: R1; Sep 19: R1; Sep 20: R1; Sep 21: R1; Sep 22: R1; Sep 23: R1; Sep 24: R1; Sep 25: R1; Sep 26: R1; Sep 27: R1; Sep 28: R1; Sep 29: R1; Sep 30: R1; Oct 01: R1; Oct 02: R1; Oct 03: Z2; Oct 04: Z2; Oct 05: Z2; Oct 06: Z2; Oct 07: Z2; Oct 08: Z2; Oct 09: Z2; Oct 10: Z1; Oct 11: Z1; Oct 12: Z1; Oct 13: Z1; Oct 14: Z1; Oct 15: Z1; Oct 16: Z1; Oct 17: Z1; Oct 18: Z1; Oct 19: Z1; Oct 20: Z1; Oct 21: Z1; Oct 22: Z1; Oct 23: Z1; Oct 24: H1; Oct 25: H1; Oct 26: H1; Oct 27: H1; Oct 28: H1; Oct 29: H1; Oct 30: H1; Nov 07: J1; Nov 08: J1; Nov 09: J1; Nov 10: J1; Nov 11: J1; Nov 12: J1; Nov 13: J1; Nov 14: J1; Nov 15: J1; Nov 16: J1; Nov 17: J1; Nov 18: J1; Nov 19: T2; Nov 20: T2; Nov 21: T2; Nov 22: T2; Nov 23: T2; Nov 24: T2; Nov 25: T2; Dec 31: MP1; Jan 01: MP1; Jan 02: MP1; Jan 03: MP1; Jan 04: MP1; Jan 05: MP1; Jan 06: MP1; Jan 07: MP1; Jan 08: MP1; Jan 09: MP1; Jan 10: MP1; Jan 11: MP1; Jan 12: MP1; Jan 13: MP1; Jan 14: MP1; Jan 15: MP1; Jan 16: MP1; Jan 17: MP1; Jan 18: MP1; Jan 19: MP1; Jan 20: MP1; Jan 21: MP1; Jan 22: MP1; Jan 23: MP1; Jan 24: MP1; Jan 25: MP1; Jan 26: MP1; Jan 27: MP1; Jan 28: MP1; Jan 29: MP1; Jan 30: E4; Jan 31: E4; Feb 01: E4; Feb 02: E4; Feb 03: E4; Feb 04: E4; Feb 05: E4
[640 empty] | W2 | W2 | W2 | [43 empty] | T1 | T1 | T1 | T1 | T1 | T1 | T1 | T1 | T1 | T1 | T1 | T1 | T1 | T1 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3
|  | South | Sep 04: F1; Sep 05: F1; Sep 06: F1; Sep 07: F1; Sep 08: F1; Sep 09: F1; Sep 10: F1; Sep 11: F1; Sep 12: F1; Sep 13: F1; Sep 14: F1; Sep 15: F1; Sep 16: F1; Sep 17: F1; Sep 18: F1; Sep 19: Y1; Sep 20: Y1; Sep 21: Y1; Sep 22: Y1; Sep 24: R1; Sep 25: R1; Sep 26: R1; Sep 27: R1; Sep 28: R1; Sep 29: R1; Sep 30: R1; Oct 01: R1; Oct 02: R1; Oct 03: R1; Oct 04: R1; Oct 05: R1; Oct 06: R1; Oct 07: R1; Oct 08: R1; Oct 09: R1; Oct 10: R1; Oct 11: R1; Oct 12: R1; Oct 13: R1; Oct 14: R1; Oct 15: R1; Oct 16: R1; Oct 17: R1; Oct 18: R1; Oct 19: R1; Oct 20: R1; Oct 21: R1; Oct 22: R1; Oct 23: R1; Oct 24: R1; Oct 25: R1; Oct 26: R1; Oct 27: R1; Oct 28: R1; Nov 07: Z2; Nov 08: Z2; Nov 09: Z2; Nov 10: Z2; Nov 11: Z2; Nov 12: Z2; Nov 13: Z2; Nov 14: T1; Nov 15: T1; Nov 16: T1; Nov 17: T1; Nov 18: T1; Nov 19: T1; Nov 20: T1; Nov 21: T1; Nov 22: T1; Nov 23: T1; Nov 24: T1; Nov 25: T1; Nov 26: T1; Nov 27: T1; Nov 28: T1; Nov 29: T1; Nov 30: T1; Dec 01: T1; Dec 02: H1; Dec 03: H1; Dec 04: H1; Dec 05: H1; Dec 06: H1; Dec 07: H1; Dec 08: H1; Dec 16: J1; Dec 17: J1; Dec 18: J1; Dec 19: J1; Dec 20: J1; Dec 21: J1; Dec 22: J1; Dec 23: J1; Dec 24: J1; Dec 25: J1; Dec 26: J1; Dec 29: T2; Dec 30: T2; Dec 31: T2; Jan 01: T2; Jan 02: T2; Jan 03: T2; Jan 04: T2; Jan 05: T2; Feb 04: MP1; Feb 05: MP1; Feb 06: MP1; Feb 07: MP1; Feb 08: MP1; Feb 09: MP1; Feb 10: MP1; Feb 11: MP1; Feb 12: MP1; Feb 13: MP1; Feb 14: MP1; Feb 15: MP1; Feb 16: MP1; Feb 17: MP1; Feb 18: MP1; Feb 19: MP1; Feb 20: MP1; Feb 21: MP1; Feb 22: MP1; Feb 23: MP1; Feb 24: MP1; Feb 25: MP1; Feb 26: MP1; Feb 27: MP1; Feb 28: MP1; Mar 01: MP1; Mar 02: MP1; Mar 03: MP1; Mar 04: E4; Mar 05: E4; Mar 06: E4; Mar 07: E4; Mar 08: E4; Mar 09: E4; Mar 10: E4
[665 empty] | W2 | W2 | W2 | W2 | W2 | [30 empty] | Z1 | Z1 | Z1 | Z1 | Z1 | Z1 | Z1 | Z1 | Z1 | Z1 | Z1 | Z1 | Z1 | Z1 | [25 empty] | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E3
| Entry | Concourse level | Dec 22: S9; Dec 23: S9; Dec 24: S9; Dec 25: S9; Dec 26: S9; Dec 27: S9; Dec 28: S9; Dec 29: S9; Dec 30: S9; Dec 31: S9; Jan 01: S9; Jan 02: S9; Jan 03: S9; Jan 04: S9; Jan 05: S9; Jan 06: S9; Jan 07: S9; Jan 08: S9; Jan 09: S9; Jan 10: S9; Jan 11: S9; Jan 12: S9; Jan 13: S9; Jan 14: S9; Jan 15: S9; Jan 16: S9; Jan 17: S9; Jan 18: S9; Jan 19: S9; Jan 20: S9; Jan 21: S9; Jan 22: S10; Jan 23: S10; Jan 24: S10; Jan 25: S10; Jan 26: S10; Jan 27: S10; Jan 28: S10; Jan 29: S10; Jan 30: S10; Jan 31: S10; Feb 01: S10; Feb 02: S10; Feb 03: S10; Feb 04: S10; Feb 05: MS1; Feb 06: MS1; Feb 07: MS1; Feb 08: MS1; Feb 09: MS1; Feb 10: MS1; Feb 11: MS1; Feb 12: MS1; Feb 13: MS1; Feb 14: MS1; Feb 15: MS1; Feb 16: MS1; Feb 17: MS1; Feb 18: MS1; Feb 19: MS1; Feb 20: MS1; Feb 21: MS1; Feb 22: MS1; Feb 23: MS1; Feb 24: MS1; Feb 25: MS1; Feb 26: SG1; Feb 27: SG1; Feb 28: SG1; Mar 01: SG1; Mar 02: SG1; Mar 03: SG1; Mar 04: SG1
| Lower Suite Level | North | Aug 09: C11; Aug 10: C11; Aug 11: C11; Aug 12: C11; Aug 13: C11; Aug 14: C11; Aug 15: C11; Aug 16: C11; Aug 17: C11; Aug 18: C11; Aug 19: C11; Aug 20: C11; Aug 21: C11; Aug 22: C11; Aug 23: C11; Aug 24: C11; Aug 25: C11; Aug 26: C11; Aug 27: C11; Aug 28: C11; Aug 29: C11; Aug 30: C11; Aug 31: C11; Sep 01: C11; Sep 02: C11; Sep 03: C11; Sep 04: C11; Sep 05: C11; Sep 11: RG2; Sep 12: RG2; Sep 13: RG2; Sep 14: RG2; Sep 15: RG2; Sep 16: RG2; Sep 17: RG2; Sep 18: RG2; Sep 19: RG2; Sep 20: RG2; Sep 21: RG2; Sep 22: RG2; Sep 23: RG2; Sep 24: RG2; Oct 02: MP2; Oct 03: MP2; Oct 04: MP2; Oct 05: MP2; Oct 06: MP2; Oct 07: MP2; Oct 08: MP2; Oct 09: MP2; Oct 10: MP2; Oct 11: MP2; Oct 12: MP2; Oct 13: MP2; Oct 14: MP2; Oct 15: MP2; Oct 16: MP2; Oct 17: MP2; Oct 18: MP2; Oct 19: MP2; Oct 20: MP2; Oct 21: MP2; Oct 22: MP2; Oct 23: MP2; Oct 24: MP2; Oct 25: MP2; Oct 26: MP2; Oct 27: MP2; Oct 28: MP2; Oct 29: MP2
[626 empty] | RG1 | [8 empty] | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | W2 | W2 | W2 | W2 | W2 | W2 | W2 | W2 | [42 empty] | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1
|  | South | Sep 04: RG1; Sep 18: F1; Sep 19: F1; Sep 20: F1; Sep 21: F1; Sep 22: F1; Sep 23: F1; Sep 24: F1; Sep 25: F1; Sep 26: F1; Sep 27: F1; Sep 28: F1; Sep 29: F1; Sep 30: F1; Oct 01: F1; Oct 02: W2; Oct 03: W2; Oct 04: W2; Oct 05: W2; Oct 06: W2; Oct 07: W2; Oct 08: W2; Oct 30: MP2; Oct 31: MP2; Nov 01: MP2; Nov 02: MP2; Nov 03: MP2; Nov 04: MP2; Nov 05: MP2; Nov 06: MP2; Nov 07: MP2; Nov 08: MP2; Nov 09: MP2; Nov 10: MP2; Nov 11: MP2; Nov 12: MP2; Nov 13: MP2; Nov 14: MP2; Nov 15: MP2; Nov 16: MP2; Nov 17: MP2; Nov 18: MP2; Nov 19: MP2; Nov 20: MP2; Nov 21: MP2; Nov 22: MP2; Nov 23: MP2; Nov 24: MP2; Nov 25: MP2; Nov 26: MP2
[650 empty] | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | C11 | RG2 | RG2 | RG2 | RG2 | RG2 | RG2 | RG2 | RG2 | RG2 | RG2 | RG2 | RG2 | RG2 | RG2 | [21 empty] | M1 | M1 | M1 | M1 | M1 | M1 | M1
| Main building | Main building | Mar 11: MH2; Mar 12: MH2; Mar 13: MH2; Mar 14: MH2; Mar 15: MH2; Mar 16: MH2; Mar 17: MH2; Mar 18: MH2; Mar 19: MH2; Mar 20: MH2; Mar 21: MH2; Mar 22: MH2; Mar 23: MH2; Mar 24: MH2; Mar 25: MH3; Mar 26: MH3; Mar 27: MH3; Mar 28: MH3; Mar 29: MH3; Mar 30: MH3; Mar 31: MH3; Apr 01: MH3; Apr 02: MH3; Apr 03: MH3; Apr 04: MH3; Apr 05: MH3; Apr 06: MH3; Apr 07: MH3
| Northeast - Concourse Level | NE | Oct 03: F1; Oct 04: F1; Oct 05: F1; Oct 06: F1; Oct 07: F1; Oct 08: F1; Oct 09: F1; Oct 10: F1; Oct 11: F1; Oct 12: F1; Oct 13: F1; Oct 14: F1; Oct 15: F1; Oct 16: F1; Oct 17: Y2; Oct 18: Y2; Oct 19: Y2; Oct 20: Y2; Oct 24: R1; Oct 25: R1; Oct 26: R1; Oct 27: R1; Oct 28: R1; Oct 29: R1; Oct 30: R1; Oct 31: R1; Nov 01: R1; Nov 02: R1; Nov 03: R1; Nov 04: R1; Nov 05: R1; Nov 06: R1; Nov 07: R1; Nov 08: R1; Nov 09: R1; Nov 10: R1; Nov 11: R1; Nov 12: R1; Nov 13: R1; Nov 14: R1; Nov 15: R1; Nov 16: R1; Nov 17: R1; Nov 18: R1; Nov 19: R1; Nov 20: R1; Nov 21: R1; Nov 22: R1; Nov 23: R1; Nov 24: R1; Nov 25: R1; Nov 26: R1; Nov 27: R1; Nov 28: R1; Nov 29: R1; Nov 30: R1; Dec 01: R1; Jan 30: MP3; Jan 31: MP3; Feb 01: MP3; Feb 02: MP3; Feb 03: MP3; Feb 04: MP3; Feb 05: MP3; Feb 06: MP3; Feb 07: MP3; Feb 08: MP3; Feb 09: MP3; Feb 10: MP3; Feb 11: MP3; Feb 12: MP3
[693 empty] | W2 | W2 | W2 | W2 | W2 | W2 | W2
| Northeast - Roof Level | NE | Sep 17: RG1; Sep 18: RG1; Oct 23: RG2; Oct 24: RG2; Oct 25: RG2; Oct 26: RG2; Oct 27: RG2; Oct 28: RG2; Oct 29: RG2; Nov 13: M1; Nov 14: M1; Nov 15: M1; Nov 16: M1; Nov 17: M1; Nov 18: M1; Nov 19: M1
| Roof Level | NEC | Aug 19: RG1; Aug 20: RG1; Sep 02: RG2; Sep 03: RG2; Sep 04: RG2; Sep 05: RG2; Sep 06: RG2; Sep 07: RG2; Sep 08: RG2; Sep 09: RG2; Sep 10: M1; Sep 11: M1; Sep 12: M1; Sep 13: M1; Sep 14: M1; Sep 15: M1; Sep 16: M1; Sep 17: M1; Sep 18: M1; Sep 19: M1; Sep 20: M1; Sep 21: M1; Sep 22: M1; Sep 23: M1; Sep 24: M1; Sep 25: M1; Sep 26: M1; Sep 27: M1; Sep 28: M1; Sep 29: M1; Sep 30: M1
|  | Roof Level | Oct 16: RG2; Oct 17: RG2; Oct 18: RG2; Oct 19: RG2; Oct 20: RG2; Oct 21: RG2; Oct 22: RG2
|  | SEC | Sep 02: RG1; Sep 03: RG1; Sep 25: RG2; Sep 26: RG2; Sep 27: RG2; Sep 28: RG2; Sep 29: RG2; Sep 30: RG2; Oct 01: RG2; Oct 02: M1; Oct 03: M1; Oct 04: M1; Oct 05: M1; Oct 06: M1; Oct 07: M1; Oct 08: M1; Oct 09: M1; Oct 10: M1; Oct 11: M1; Oct 12: M1; Oct 13: M1; Oct 14: M1; Oct 15: M1; Oct 16: M1; Oct 17: M1; Oct 18: M1; Oct 19: M1; Oct 20: M1; Oct 21: M1; Oct 22: M1
CIVIL/SITE | East | East | Apr 07: U1; Apr 08: U1; Apr 09: U1; Apr 10: U1; Apr 11: U1; Apr 12: U1; Apr 13: U1; Apr 14: U1; Apr 15: U1; Apr 16: U1; Apr 17: U1; Apr 18: U1; Apr 19: U1; Apr 20: U1; Apr 21: U1; Apr 22: U1; Apr 23: U1; Apr 24: U1; Apr 25: U1; Apr 26: U1; Apr 27: U1; Apr 28: U1; Apr 29: U1; Apr 30: U1; May 01: U1; May 02: U1; May 03: U1; May 04: U1; May 05: U1; May 06: U1; May 07: U1; May 08: U1; May 09: U1; May 10: U1; May 11: U1; May 12: U1; May 13: U1; May 14: U1; May 15: U1; May 16: U1; May 17: U1; May 18: U1; May 19: U1; May 20: U1; May 21: U1; May 22: U1; May 23: U1; May 24: U1; May 25: U1; May 26: U1; May 27: U1; May 28: U1; May 29: U1; May 30: U1; May 31: U1; Jun 01: U1; Jun 02: U1; Jun 03: U1; Jun 04: U1; Jun 05: U1; Jun 06: U1; Jun 07: U1; Jun 08: U1; Jun 09: U1; Jun 10: U1; Jun 11: U1; Jun 12: U1; Jun 13: U1; Jun 14: U1; Jun 15: U1; Jun 16: U1; Jun 17: A1; Jun 18: A1; Jun 19: A1; Jun 20: A1; Jun 21: A1; Jun 22: A1; Jun 23: A1; Jun 24: A1; Jun 25: A1; Jun 26: A1; Jun 27: A1; Jun 28: A1; Jun 29: A1; Jun 30: A1; Jul 01: A1; Jul 02: A1; Jul 03: A1; Jul 04: A1; Jul 05: A1; Jul 06: A1; Jul 07: A1; Jul 08: A1; Jul 09: A1; Jul 10: A1; Jul 11: A1; Jul 12: A1; Jul 13: A1; Jul 14: A1; Jul 15: A1; Nov 20: HL1; Nov 21: HL1; Nov 22: HL1; Nov 23: HL1; Nov 24: HL1; Nov 25: HL1; Nov 26: HL1; Nov 27: HL1; Nov 28: HL1; Nov 29: HL1; Nov 30: HL1; Dec 01: HL1; Dec 02: HL1; Dec 03: HL1; Dec 04: HL1; Dec 05: HL1; Dec 06: HL1; Dec 07: HL1; Dec 08: HL1; Dec 09: HL1; Dec 10: HL1; Dec 11: HL1; Dec 12: HL1; Dec 13: HL1; Dec 14: HL1; Dec 15: HL1; Dec 16: HL1; Dec 17: HL1; Dec 18: HL1; Dec 19: HL1; Dec 20: HL1; Dec 21: HL1; Dec 22: HL1; Dec 23: HL1; Dec 24: HL1; Dec 25: HL1; Dec 26: HL1; Dec 27: HL1; Dec 28: HL1; Dec 29: HL1; Dec 30: HL1; Dec 31: HL1; Jan 01: HL1; Jan 02: HL1; Jan 03: HL1; Jan 04: HL1; Jan 05: HL1; Jan 06: HL1; Jan 07: HL1; Jan 08: HL1; Jan 09: HL1; Jan 10: HL1; Jan 11: HL1; Jan 12: HL1; Jan 13: HL1; Jan 14: HL1; Jan 15: HL1; Jan 16: HL1; Jan 17: HL1; Jan 18: HL1; Jan 19: HL1; Jan 20: HL1; Jan 21: HL1; Jan 22: HL1; Jan 23: HL1; Jan 24: HL1; Jan 25: HL1; Jan 26: HL1; Jan 27: HL1; Jan 28: HL1; Jan 29: HL1; Jan 30: HL1; Jan 31: HL1; Feb 01: HL1; Feb 02: HL1; Feb 03: HL1; Feb 04: HL1; Feb 05: HL1; Feb 06: HL1; Feb 07: HL1; Feb 08: HL1; Feb 09: HL1; Feb 10: HL1; Feb 11: HL1; Feb 12: HL1; Feb 13: HL1; Feb 14: HL1; Feb 15: HL1; Feb 16: HL1; Feb 17: HL1; Feb 18: HL1; Feb 19: HL1; Feb 20: HL1; Feb 21: HL1; Feb 22: HL1; Feb 23: HL1; Feb 24: HL1; Feb 25: HL1; Feb 26: HL1; Feb 27: HL1; Feb 28: HL1; Mar 01: HL1; Mar 02: HL1; Mar 03: HL1; Mar 04: HL1; Mar 05: HL1; Mar 06: HL1; Mar 07: HL1; Mar 08: HL1; Mar 09: HL1; Mar 10: HL1; Mar 11: HL1
[542 empty] | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2
CANOPIES | Main building | Main building | Oct 03: E2; Oct 04: E2; Oct 05: E2; Oct 06: E2; Oct 07: E2; Oct 08: E2; Oct 09: E2; Oct 10: E2; Oct 11: E2; Oct 12: E2; Oct 13: E2; Oct 14: E2; Oct 15: E2; Oct 16: E2; Oct 17: E2; Oct 18: E2; Oct 19: E2; Oct 20: E2; Oct 21: E2; Oct 22: E2; Oct 23: E2; Oct 24: E2; Oct 25: E2; Oct 26: E2; Oct 27: E2; Oct 28: E2; Oct 29: E2; Oct 30: E2; Oct 31: E2; Nov 01: E2; Nov 02: E2; Nov 03: E2; Nov 04: E2; Nov 05: E2; Nov 06: E2; Nov 07: E2; Nov 08: E2; Nov 09: E2; Nov 10: E2; Nov 11: E2; Nov 12: E2; Nov 13: E2; Nov 14: E2; Nov 15: E2; Nov 16: E2; Nov 17: E2; Nov 18: E2; Nov 19: E2; Nov 20: E2; Nov 21: E2; Nov 22: E2; Nov 23: E2; Nov 24: E2; Nov 25: E2; Nov 26: E2; Nov 27: E2; Nov 28: E2; Nov 29: E2; Nov 30: E2; Dec 01: E2; Dec 02: E2; Dec 03: E2; Dec 04: E2; Dec 05: E2; Dec 06: E2; Dec 07: E2; Dec 08: E2; Dec 09: E2; Dec 10: E2; Dec 11: E2; Dec 12: E2; Dec 13: E2; Dec 14: E2; Dec 15: E2; Dec 16: E2; Dec 17: E2; Dec 18: E2; Dec 19: E2; Dec 20: E2; Dec 21: E2; Dec 22: E2; Dec 23: E2; Dec 24: E2; Dec 25: E2; Dec 26: E2; Dec 27: E2; Dec 28: E2; Dec 29: E2; Dec 30: E2; Apr 20: S7; Apr 21: S7; Apr 22: S7; Apr 23: S7; Apr 24: S7; Apr 25: S7; Apr 26: S7; Apr 27: S7; Apr 28: S7; Apr 29: S7; Apr 30: S7; May 01: S7; May 02: S7; May 03: S7; May 04: S7; May 05: S7; May 06: S7; May 07: S7; May 08: S7; May 09: S7; May 10: S7; May 11: S7; May 12: S7; May 13: S7; May 14: S7; May 15: S7; May 16: S7; May 17: S7; May 18: S7; May 19: S7; May 20: S7; May 21: S7; May 22: S7; May 23: S7; May 24: S7; May 25: S7; May 26: S7; May 27: S7; May 28: S7; May 29: S7; May 30: S7; May 31: S7; Jun 01: S7; Jun 02: S7; Jun 03: S7; Jun 04: S7; Jun 05: S7; Jun 06: S7; Jun 07: S7; Jun 08: S7; Jun 09: S7; Jun 10: S7; Jun 11: S7; Jun 12: S7; Jun 13: S7; Jun 14: S7; Jun 15: S7; Jun 16: S7; Jun 17: S7; Jun 18: S7; Jun 19: S7; Jun 20: S7; Jun 21: S7; Jun 22: S7; Jun 23: S7; Jun 24: S7; Jun 25: S7; Jun 26: S7; Jun 27: S7; Jun 28: S7; Jun 29: S7; Jun 30: S8; Jul 01: S8; Jul 02: S8; Jul 03: S8; Jul 04: S8; Jul 05: S8; Jul 06: S8; Jul 07: S8; Jul 08: S8; Jul 09: S8; Jul 10: S8; Jul 11: S8; Jul 12: S8; Jul 13: S8; Jul 14: S8; Jul 15: S8; Jul 16: S8; Jul 17: S8; Jul 18: S8; Jul 19: S8; Jul 20: S8; Jul 21: S8; Jul 22: S8; Jul 23: S8; Jul 24: S8; Jul 25: S8; Jul 26: S8; Jul 27: S8; Jul 28: S8
INTERIORS | Closeout/Commissioning | Closeout/Commissioning | bar: Apr 08 to Jun 30
| Concession Wings - Concourse level | MEP/LV Rooms | Sep 02: F2; Sep 03: F2; Sep 04: M2; Sep 05: M2; Sep 09: P6; Sep 10: P6; Sep 11: F3; Sep 12: F3; Sep 13: F3; Sep 14: F3; Sep 15: F3; Sep 16: E7; Sep 17: E7; Sep 18: E7; Sep 19: E7; Sep 20: E7; Sep 21: E7; Sep 22: E7; Sep 23: IS1; Sep 24: IS2; Sep 25: DW1; Sep 26: DW1; Sep 27: DW1; Sep 28: DW1; Sep 29: DW1; Sep 30: DW2; Oct 01: DW2; Oct 02: DW2; Oct 03: DW2; Oct 04: DW2; Oct 05: DW2; Oct 06: DW2; Oct 07: DW2; Oct 08: DW2; Oct 09: M8; Oct 14: DW4; Oct 15: EQ2; Oct 16: EQ2; Oct 17: E12; Oct 18: E12; Oct 19: E12; Oct 20: E12; Nov 14: CN1; Nov 15: CN1; Nov 16: CN1; Nov 17: CN1; Nov 18: CN1; Nov 19: CN1; Nov 20: CN1; Nov 21: MH2; Nov 22: MH2; Nov 23: MH2; Nov 24: MH2; Nov 25: MH2; Nov 26: MH2; Nov 27: MH2; Nov 28: MH2; Nov 29: MH2; Nov 30: MH2; Dec 01: MH2; Dec 02: MH2; Dec 03: MH2; Dec 04: MH2; Dec 05: MH2; Dec 06: MH2; Dec 07: MH2; Dec 08: MH2; Dec 09: MH3; Dec 10: MH3; Dec 11: MH3; Dec 12: MH3; Dec 13: MH3; Dec 14: MH3; Dec 15: MH3; Dec 16: MH3; Dec 17: MH3; Dec 18: MH3; Dec 19: MH3; Dec 20: MH3; Dec 21: MH3; Dec 22: MH3; Dec 23: CN2; Dec 24: CN2
[655 empty] | H2 | H2 | [28 empty] | E10 | E10 | [6 empty] | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | E5
[685 empty] | C13 | C13 | C13 | C13 | C13
[685 empty] | E11 | E11 | E11 | E11 | E11 | E11 | E11
|  | North Concessions | Sep 29: F2; Sep 30: F2; Oct 01: M2; Oct 02: M2; Oct 08: P6; Oct 09: P6; Oct 10: P6; Oct 11: P6; Oct 12: P6; Oct 13: P6; Oct 14: P6; Oct 21: P3; Oct 22: P3; Oct 23: P3; Oct 24: P3; Oct 25: P3; Oct 26: P3; Oct 27: P3; Oct 29: IS1; Oct 30: IS2; Oct 31: DW1; Nov 01: DW1; Nov 02: DW1; Nov 03: DW1; Nov 04: DW1; Nov 05: DW1; Nov 06: DW1; Nov 07: DW2; Nov 08: DW2; Nov 09: DW2; Nov 10: DW2; Nov 11: DW2; Nov 12: DW2; Nov 13: DW2; Nov 14: DW2; Nov 15: DW2; Nov 16: DW2; Nov 17: DW2; Nov 18: F4; Nov 20: RF1; Nov 21: RF1; Nov 22: RF1; Nov 23: RF1; Nov 24: RF1; Nov 26: Q3; Nov 27: Q3; Nov 28: Q3; Nov 29: Q3; Nov 30: Q3; Dec 01: Q3; Dec 02: Q3; Dec 03: M4; Dec 04: H3; Dec 12: E10; Dec 13: E10; Dec 14: E10; Dec 15: E10; Dec 16: E10; Dec 17: IS3; Dec 18: IS4; Dec 19: DW3; Dec 22: DW2; Dec 23: DW2; Dec 24: DW2; Dec 26: PT1; Dec 27: PT1; Dec 28: PT1; Dec 29: PT1; Dec 30: PT1; Jan 02: DW4; Jan 05: Y4; Jan 06: Y4; Jan 07: Y4; Jan 08: Y4; Jan 09: Y4; Jan 10: Y4; Jan 11: Y4; Jan 12: Y4; Jan 13: Y4; Jan 14: Y4; Jan 15: Y4; Jan 16: Y4; Jan 17: Y4; Jan 18: Y4; Jan 19: Y4; Jan 20: M5; Jan 27: EQ2; Jan 28: EQ2; Feb 02: M6; Feb 03: E12; Feb 04: E12; Feb 05: Q1; Feb 06: Q1; Feb 10: CN1; Feb 11: CN1; Feb 12: CN1; Feb 13: MH2; Feb 14: MH2; Feb 15: MH2; Feb 16: MH2; Feb 17: MH2; Feb 18: MH2; Feb 19: MH2; Feb 20: MH2; Feb 21: MH2; Feb 22: MH2; Feb 23: MH2; Feb 24: MH2; Feb 25: MH2; Feb 26: MH2; Feb 27: MH3; Feb 28: MH3; Mar 01: MH3; Mar 02: MH3; Mar 03: MH3; Mar 04: MH3; Mar 05: MH3; Mar 06: MH3; Mar 07: MH3; Mar 08: MH3; Mar 09: MH3; Mar 10: MH3; Mar 11: MH3; Mar 12: MH3; Mar 13: CN2; Mar 14: CN2; Mar 15: CN2; Mar 16: CN2
[678 empty] | H2 | H2 | H2 | H2 | H2 | [6 empty] | F3 | F3 | F3 | F3 | F3 |  |  |  |  | E7 | E7 | E7 | E7 | E7 | E7 | E7 | [20 empty] | M7 | M7 | M3 | M3 | M3 | M3 | M3 | M3 | [7 empty] | E13 | E13 | E13 | [20 empty] | FO1 | FO1 | FO1 | FO1 | FO1 | FO1 | FO1 | FO1 | [17 empty] | EQ1 | EQ1 | EQ1 | EQ1 | EQ1 | EQ1 | EQ1 | P5 | P5 | P5
[796 empty] | E11 | E11 | E11
|  | North Restrooms | Sep 24: F2; Sep 25: F2; Sep 26: F2; Sep 29: M2; Sep 30: M2; Oct 01: P6; Oct 02: P6; Oct 03: P6; Oct 04: P6; Oct 05: P6; Oct 06: P6; Oct 07: P6; Oct 14: P3; Oct 15: P3; Oct 16: P3; Oct 17: P3; Oct 18: P3; Oct 19: P3; Oct 20: P3; Oct 21: IS1; Oct 22: IS2; Oct 23: DW1; Oct 24: DW1; Oct 25: DW1; Oct 26: DW1; Oct 27: DW1; Oct 28: DW2; Oct 29: DW2; Oct 30: DW2; Oct 31: DW2; Nov 01: DW2; Nov 02: DW2; Nov 03: DW2; Nov 04: Q3; Nov 05: Q3; Nov 06: Q3; Nov 07: M4; Nov 10: H3; Nov 14: E10; Nov 15: E10; Nov 16: E10; Nov 17: E10; Nov 18: E10; Nov 19: IS3; Nov 20: IS4; Nov 21: DW3; Nov 24: DW2; Nov 25: DW2; Nov 26: DW2; Dec 01: FO1; Dec 02: FO1; Dec 03: FO1; Dec 04: FO1; Dec 05: FO1; Dec 08: TE1; Dec 09: TE1; Dec 10: TE1; Dec 11: TE1; Dec 12: TE1; Dec 13: TE1; Dec 14: TE1; Dec 15: TE1; Dec 16: TE1; Dec 17: TE1; Dec 18: TE1; Dec 19: TE1; Dec 22: P4; Dec 23: P4; Dec 24: P4; Dec 25: P4; Dec 26: P4; Dec 27: P4; Dec 28: P4; Dec 29: P4; Dec 30: P5; Dec 31: P5; Jan 02: Y10; Jan 03: Y10; Jan 04: Y10; Jan 05: Y10; Jan 06: Y10; Jan 07: Y10; Jan 08: Y10; Jan 09: Y10; Jan 10: Y10; Jan 11: Y10; Jan 12: Y10; Jan 13: Y10; Jan 14: Y10; Jan 15: Y10; Jan 16: Y10; Jan 19: Y7; Jan 23: E11; Jan 24: E11; Jan 25: E11; Jan 26: E11; Jan 27: E11; Jan 28: E12; Jan 29: E12; Jan 30: Q1; Jan 31: Q1; Feb 01: Q1; Feb 02: Q1; Feb 03: CN1; Feb 04: CN1; Feb 05: CN1; Feb 06: CN1; Feb 07: CN1; Feb 08: CN1; Feb 09: CN1; Feb 10: MH2; Feb 11: MH2; Feb 12: MH2; Feb 13: MH2; Feb 14: MH2; Feb 15: MH2; Feb 16: MH2; Feb 17: MH2; Feb 18: MH2; Feb 19: MH2; Feb 20: MH2; Feb 21: MH2; Feb 22: MH2; Feb 23: MH2; Feb 24: MH3; Feb 25: MH3; Feb 26: MH3; Feb 27: MH3; Feb 28: MH3; Mar 01: MH3; Mar 02: MH3; Mar 03: MH3; Mar 04: MH3; Mar 05: MH3; Mar 06: MH3; Mar 07: MH3; Mar 08: MH3; Mar 09: MH3; Mar 10: CN2; Mar 11: CN2
[675 empty] | H2 | H2 | H2 |  |  |  |  | F3 | F3 | F3 | F3 | F3 |  |  |  | E7 | E7 | E7 | E7 | E7 | E7 | E7 | [16 empty] | F4 | E13 | E13 | E13 | E13 | [69 empty] | EQ2 | EQ2
|  | South Concessions | Oct 06: F2; Oct 07: F2; Oct 08: M2; Oct 09: M2; Oct 10: H2; Oct 11: H2; Oct 12: H2; Oct 13: H2; Oct 14: H2; Oct 22: P6; Oct 23: P6; Oct 24: P6; Oct 25: P6; Oct 26: P6; Oct 27: P6; Oct 28: P6; Oct 29: F3; Oct 30: F3; Nov 05: P3; Nov 06: P3; Nov 07: P3; Nov 08: P3; Nov 09: P3; Nov 10: P3; Nov 11: P3; Nov 12: IS1; Nov 13: IS2; Nov 14: DW1; Nov 15: DW1; Nov 16: DW1; Nov 17: DW1; Nov 18: DW1; Nov 19: DW2; Nov 20: DW2; Nov 21: DW2; Nov 22: DW2; Nov 23: DW2; Nov 24: DW2; Nov 25: DW2; Nov 26: DW2; Nov 27: DW2; Nov 28: DW2; Nov 29: DW2; Nov 30: DW2; Dec 01: DW2; Dec 03: M7; Dec 04: M7; Dec 05: M3; Dec 06: M3; Dec 07: M3; Dec 08: M3; Dec 09: M3; Dec 10: M3; Dec 11: Q3; Dec 12: Q3; Dec 16: E13; Dec 17: E13; Dec 18: E13; Dec 19: H3; Dec 24: IS3; Dec 26: IS4; Jan 05: FO1; Jan 06: FO1; Jan 07: FO1; Jan 08: FO1; Jan 09: FO1; Jan 10: FO1; Jan 11: FO1; Jan 12: FO1; Feb 04: Y4; Feb 05: Y4; Feb 06: Y4; Feb 07: Y4; Feb 08: Y4; Feb 09: Y4; Feb 10: Y4; Feb 11: Y4; Feb 12: Y4; Feb 13: Y4; Feb 14: Y4; Feb 15: Y4; Feb 16: Y4; Feb 17: Y4; Feb 18: M5; Feb 19: M5; Feb 20: M5; Feb 25: EQ2; Feb 26: EQ2; Mar 02: E12; Mar 03: E12; Mar 04: M6; Mar 05: Q1; Mar 06: Q1; Mar 09: CN1; Mar 10: CN1; Mar 11: CN1; Mar 12: CN1; Mar 13: CN1; Mar 16: MH2; Mar 17: MH2; Mar 18: MH2; Mar 19: MH2; Mar 20: MH2; Mar 21: MH2; Mar 22: MH2; Mar 23: MH2; Mar 24: MH2; Mar 25: MH2; Mar 26: MH2; Mar 27: MH2; Mar 30: MH3; Mar 31: MH3; Apr 01: MH3; Apr 02: MH3; Apr 03: MH3; Apr 04: MH3; Apr 05: MH3; Apr 06: MH3; Apr 07: MH3; Apr 08: MH3; Apr 09: MH3; Apr 10: MH3; Apr 13: CN2; Apr 14: CN2
[712 empty] | E7 | E7 | E7 | E7 | E7 | E7 | E7 | [35 empty] | M4 | M4 | E10 | E10 | E10 | E10 | E10 | [56 empty] | EQ1 | EQ1 | EQ1 | EQ1 | EQ1 | EQ1 | EQ1 | P5 | P5 | P5
[824 empty] | E11 | E11 | E11
|  | South Restrooms | Oct 01: F2; Oct 02: F2; Oct 03: F2; Oct 06: M2; Oct 07: M2; Oct 15: P6; Oct 16: P6; Oct 17: P6; Oct 18: P6; Oct 19: P6; Oct 20: P6; Oct 21: P6; Oct 29: P3; Oct 30: P3; Oct 31: P3; Nov 01: P3; Nov 02: P3; Nov 03: P3; Nov 04: P3; Nov 05: IS1; Nov 06: IS2; Nov 07: DW1; Nov 08: DW1; Nov 09: DW1; Nov 10: DW1; Nov 11: DW1; Nov 12: DW2; Nov 13: DW2; Nov 14: DW2; Nov 15: DW2; Nov 16: DW2; Nov 17: DW2; Nov 18: DW2; Nov 19: F4; Nov 25: Q3; Nov 26: Q3; Dec 01: M4; Dec 02: H3; Dec 09: E10; Dec 10: E10; Dec 11: E10; Dec 18: IS3; Dec 19: IS4; Dec 22: DW3; Dec 23: DW2; Dec 24: DW2; Dec 25: DW2; Dec 26: DW2; Dec 27: DW2; Dec 28: DW2; Dec 29: DW2; Dec 30: DW2; Dec 31: FO2; Jan 12: PT2; Jan 13: PT2; Jan 14: FO1; Jan 15: FO1; Jan 16: FO1; Jan 17: FO1; Jan 18: FO1; Jan 19: FO1; Jan 20: FO1; Jan 21: TE1; Jan 22: TE1; Jan 23: TE1; Jan 24: TE1; Jan 25: TE1; Jan 26: TE1; Jan 27: TE1; Jan 28: TE1; Jan 29: TE1; Jan 30: TE1; Jan 31: TE1; Feb 01: TE1; Feb 02: TE1; Feb 03: TE1; Feb 04: P5; Feb 05: P5; Feb 11: Y10; Feb 12: Y10; Feb 13: Y10; Feb 14: Y10; Feb 15: Y10; Feb 16: Y10; Feb 17: Y10; Feb 18: Y7; Feb 19: E11; Feb 20: E11; Feb 21: E11; Feb 22: E11; Feb 23: E11; Feb 24: E12; Feb 25: E12; Feb 26: Q1; Feb 27: Q1; Mar 02: CN1; Mar 03: CN1; Mar 04: CN1; Mar 05: CN1; Mar 06: CN1; Mar 09: MH2; Mar 10: MH2; Mar 11: MH2; Mar 12: MH2; Mar 13: MH2; Mar 14: MH2; Mar 15: MH2; Mar 16: MH2; Mar 17: MH2; Mar 18: MH2; Mar 19: MH2; Mar 20: MH2; Mar 23: MH3; Mar 24: MH3; Mar 25: MH3; Mar 26: MH3; Mar 27: MH3; Mar 28: MH3; Mar 29: MH3; Mar 30: MH3; Mar 31: MH3; Apr 01: MH3; Apr 02: MH3; Apr 03: MH3; Apr 06: CN2; Apr 07: CN2
[683 empty] | H2 | H2 | H2 | [10 empty] | F3 | F3 | F3 | F3 | F3 |  |  |  |  | E7 | E7 | E7 | E7 | E7 | E7 | E7 | [26 empty] | E13 | E13 | [63 empty] | P4 | P4 | P4 | P4 | P4 | P4 | P4 | [7 empty] | EQ2 | EQ2
|  | Team Store | Oct 08: F2; Oct 10: M2; Oct 23: H2; Oct 24: H2; Oct 27: P6; Oct 28: P6; Oct 29: P6; Oct 30: P6; Oct 31: P6; Nov 03: F3; Nov 12: E7; Nov 13: E7; Nov 14: IS1; Nov 17: IS2; Nov 19: DW1; Nov 21: DW2; Nov 22: DW2; Nov 23: DW2; Nov 24: DW2; Nov 25: DW2; Nov 26: DW2; Nov 27: DW2; Nov 28: DW2; Nov 29: DW2; Nov 30: DW2; Dec 01: DW2; Dec 02: M4; Dec 03: E11; Dec 04: E11; Dec 17: E10; Dec 18: E10; Dec 26: CN1; Dec 27: CN1; Dec 28: CN1; Dec 29: CN1; Dec 30: CN1; Dec 31: MH2; Jan 01: MH2; Jan 02: MH2; Jan 03: MH2; Jan 04: MH2; Jan 05: MH2; Jan 06: MH2; Jan 07: MH2; Jan 08: MH2; Jan 09: MH2; Jan 10: MH2; Jan 11: MH2; Jan 12: MH2; Jan 13: MH2; Jan 14: MH2; Jan 15: MH2; Jan 16: MH3; Jan 17: MH3; Jan 18: MH3; Jan 19: MH3; Jan 20: MH3; Jan 21: MH3; Jan 22: MH3; Jan 23: MH3; Jan 24: MH3; Jan 25: MH3; Jan 26: MH3; Jan 27: MH3; Jan 28: MH3; Jan 29: MH3; Jan 30: CN2
FO3
| Hositing | Tower Crane 1 | Apr 11: C1; Apr 12: C1; Apr 13: C1; Apr 14: C1; Apr 15: C15; Apr 16: C15; Apr 17: C15; Apr 18: C15; Apr 19: C15; Apr 20: C15; Apr 21: C15; Apr 22: C15; Apr 23: C15; Apr 24: C15; Apr 25: C15; Apr 26: C15; Apr 27: C15; Apr 28: C15; Apr 29: C15; Apr 30: C15; May 01: C15; May 02: C15; May 03: C15; May 04: C15; May 05: C15; May 06: R1; May 07: R1; May 08: R1; May 09: R1; May 10: R1; May 11: R1; May 12: R1; Apr 27: R3; Apr 28: R3; Apr 29: R3; Apr 30: R3; May 01: R3
[529 empty] | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2
|  | Tower Crane 2 | Apr 09: C1; Apr 10: C1; Apr 11: C15; Apr 12: C15; Apr 13: C15; Apr 14: C15; Apr 15: C15; Apr 16: C15; Apr 17: C15; Apr 18: C15; Apr 19: C15; Apr 20: C15; Apr 21: C15; Apr 22: C15; Apr 23: C15; Apr 24: C15; Apr 25: C15; Apr 26: C15; Apr 27: C15; Apr 28: C15; Apr 29: C15; Apr 30: C15; May 01: C15; May 02: R1; May 03: R1; May 04: R1; May 05: R1; May 06: R1; May 07: R1; May 08: R1; May 04: R3; May 05: R3; May 06: R3; May 07: R3; May 08: R3
[525 empty] | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2 | R2
| Main building - Concourse level | Burn Club | Sep 16: F2; Sep 17: F2; Sep 18: F2; Sep 19: F2; Sep 22: M2; Sep 23: M2; Sep 24: M2; Sep 25: M2; Sep 26: M2; Sep 27: M2; Sep 28: M2; Sep 29: M2; Sep 30: M2; Oct 01: M2; Oct 03: P2; Oct 04: P2; Oct 05: P2; Oct 06: P2; Oct 07: P2; Oct 08: P2; Oct 09: P2; Oct 10: F3; Oct 11: F3; Oct 12: F3; Oct 13: F3; Oct 14: F3; Oct 15: E7; Oct 16: E7; Oct 17: E7; Oct 18: E7; Oct 19: E7; Oct 20: E7; Oct 21: E7; Oct 23: IS1; Oct 24: IS1; Oct 27: IS2; Oct 28: DW1; Oct 29: DW1; Oct 30: DW1; Oct 31: DW1; Nov 03: DW2; Nov 04: DW2; Nov 05: DW2; Nov 06: DW2; Nov 07: DW2; Nov 08: DW2; Nov 09: DW2; Nov 10: DW2; Nov 11: DW2; Nov 12: DW2; Nov 13: DW2; Nov 14: DW2; Nov 17: Y8; Nov 18: Y8; Nov 19: Y8; Nov 20: Y8; Nov 21: Y8; Nov 22: Y8; Nov 23: Y8; Nov 24: Y8; Nov 25: Y8; Nov 26: Y8; Nov 27: Y8; Nov 28: Y8; Nov 29: Y8; Nov 30: Y8; Dec 01: Y8; Dec 02: Y8; Dec 05: NaN; Dec 06: NaN; Dec 07: NaN; Dec 08: NaN; Dec 09: NaN; Dec 10: NaN; Dec 11: NaN; Dec 12: NaN; Dec 13: NaN; Dec 14: NaN; Dec 15: NaN; Dec 16: NaN; Dec 17: NaN; Dec 18: NaN; Dec 19: H3; Dec 20: H3; Dec 21: H3; Dec 22: H3; Dec 23: H3; Dec 24: H3; Dec 26: IS3; Dec 27: IS3; Dec 28: IS3; Dec 29: IS3; Dec 30: IS4; Dec 31: Q2; Jan 01: Q2; Jan 02: Q2; Jan 03: Q2; Jan 04: Q2; Jan 05: Q2; Jan 06: Q2; Jan 07: Q2; Jan 08: Q2; Jan 09: Q2; Jan 10: Q2; Jan 11: Q2; Jan 12: Q2; Jan 13: Q2; Jan 14: Q2; Jan 15: Q2; Jan 16: R2; Jan 17: R2; Jan 18: R2; Jan 19: R2; Jan 20: R2; Jan 21: R2; Jan 22: R2; Jan 23: R2; Jan 24: R2; Jan 25: R2; Jan 26: R2; Jan 27: R2; Jan 28: R2; Jan 29: R2; Jan 30: R2; Jan 31: R2; Feb 01: R2; Feb 02: R2; Feb 03: R2; Feb 04: R2; Feb 05: R2; Feb 06: R2; Feb 07: R2; Feb 08: R2; Feb 09: R2; Feb 10: R2; Feb 11: R2; Feb 12: R2; Feb 13: R2; Feb 14: R2; Feb 15: R2; Feb 16: R2; Feb 17: R2; Feb 18: R2; Feb 19: R2; Feb 20: ML2; Feb 21: ML2; Feb 22: ML2; Feb 23: ML2; Feb 24: ML2; Mar 03: M8; Mar 04: M8; Mar 05: M8; Mar 06: M8; Mar 10: FO1; Mar 11: FO1; Mar 12: FO1; Mar 13: FO1; Mar 14: FO1; Mar 15: FO1; Mar 16: FO1; Mar 17: ML4; Mar 18: ML4; Mar 19: ML4; Mar 20: ML4; Mar 21: ML4; Mar 22: ML4; Mar 23: ML4; Mar 24: ML5; Mar 25: ML5; Mar 26: ML5; Mar 27: ML5; Mar 28: ML5; Mar 29: ML5; Mar 30: ML5; Mar 31: EQ3; Apr 01: EQ3; Apr 02: EQ3; Apr 03: EQ3; Apr 04: EQ3; Apr 05: EQ3; Apr 06: EQ3; Apr 07: P5; Apr 08: P5; Apr 09: P5; Apr 10: P5; Apr 11: P5; Apr 12: P5; Apr 13: P5; Apr 15: ML6; Apr 16: ML6; Apr 17: ML6; Apr 18: ML6; Apr 19: ML6; Apr 20: ML6; Apr 21: ML6; Apr 22: ML6; Apr 23: ML6; Apr 24: ML6; Apr 25: ML6; Apr 26: ML6; Apr 27: ML6; Apr 28: ML6; Apr 29: ML6; Apr 30: ML6; May 01: ML6; May 02: ML6; May 03: ML6; May 04: ML6; May 05: ML6; May 06: ML6; May 07: ML6; May 08: ML6; May 09: ML6; May 10: ML6; May 11: ML6; May 12: ML6; May 13: E11; May 14: E11; May 15: E11; May 16: E11; May 17: E11; May 18: E11; May 19: E11; May 20: E11; May 21: CN1; May 22: CN1; May 23: CN1; May 24: CN1; May 25: CN1; May 26: CN1; May 27: CN1; May 28: CN1; May 29: MH2; May 30: MH2; May 31: MH2; Jun 01: MH2; Jun 02: MH2; Jun 03: MH2; Jun 04: MH2; Jun 05: MH2; Jun 06: MH2; Jun 07: MH2; Jun 08: MH2; Jun 09: MH2; Jun 10: MH2; Jun 11: MH2; Jun 12: MH3; Jun 13: MH3; Jun 14: MH3; Jun 15: MH3; Jun 16: MH3; Jun 17: MH3; Jun 18: MH3; Jun 19: MH3; Jun 20: MH3; Jun 21: MH3; Jun 22: MH3; Jun 23: MH3; Jun 24: MH3; Jun 25: MH3; Jun 26: CN2; Jun 27: CN2; Jun 28: CN2; Jun 29: CN2; Jun 30: CN2
[669 empty] | H2 | H2 | H2 | H2 | H2 | H2 | H2 | H2 | H2 | H2 | [13 empty] | P3 | P3 | P3 | P3 | P3 | P3 | P3 | [25 empty] | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | [5 empty] | M4 | M4 | M4 | M4 | M4 | M4 | M4 | E13 | E13 | E13 | E13 | E13 | E13 | E13 | E13 | [18 empty] | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | [31 empty] | H4 | H4 | H4 | H4 |  |  |  |  | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | TE2 | ML7 | ML7 | ML7 | ML7 | ML7 | ML7 | ML7 | ML9 | ML9 | ML9 | ML9 | ML9 | ML9 | ML9 | Y9 | Y9 | Y9 | Y9 | Y9 | Y9 | Y9
[796 empty] | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML1 | ML3 | ML3 | ML3 | ML3 | ML3 | ML3 | ML3 | [43 empty] | ML8 | ML8 | ML8 | ML8 | ML8 | ML8 | ML8 | ML10 | ML10 | ML10 | ML10 | ML10 | ML10 | ML10
[830 empty] | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14
|  | Food service | Sep 04: F2; Sep 05: F2; Sep 06: F2; Sep 07: F2; Sep 08: F2; Sep 09: F2; Sep 10: F2; Sep 11: M2; Sep 12: M2; Sep 13: M2; Sep 14: M2; Sep 15: M2; Sep 16: M2; Sep 17: P2; Sep 18: P2; Sep 19: P2; Sep 20: P2; Sep 21: P2; Sep 22: P2; Sep 23: P2; Sep 24: P2; Sep 25: F3; Sep 26: F3; Sep 27: F3; Sep 28: F3; Sep 29: F3; Sep 30: F3; Oct 07: P3; Oct 08: P3; Oct 09: P3; Oct 10: P3; Oct 11: P3; Oct 12: P3; Oct 13: P3; Oct 14: IS1; Oct 15: IS2; Oct 16: DW1; Oct 17: DW1; Oct 18: DW1; Oct 19: DW1; Oct 20: DW1; Oct 21: DW1; Oct 22: DW1; Oct 30: Y3; Oct 31: Y3; Nov 03: NaN; Nov 04: NaN; Nov 05: NaN; Nov 06: NaN; Nov 07: NaN; Nov 10: M3; Nov 11: M3; Nov 12: M3; Nov 13: M3; Nov 14: M3; Nov 15: M3; Nov 16: M3; Nov 17: M3; Nov 18: M3; Nov 19: M3; Nov 20: M3; Nov 21: M3; Nov 25: PT1; Nov 26: PT1; Nov 27: PT1; Nov 28: PT1; Nov 29: PT1; Nov 30: PT1; Dec 01: PT1; Dec 02: E9; Dec 03: E9; Dec 04: E9; Dec 05: E9; Dec 06: E9; Dec 07: E9; Dec 08: E9; Dec 09: E10; Dec 10: E10; Dec 11: E10; Dec 12: E10; Dec 15: H3; Dec 16: H3; Dec 17: IS3; Dec 18: IS4; Dec 19: FO1; Dec 20: FO1; Dec 21: FO1; Dec 22: FO1; Dec 23: FO1; Dec 24: FO1; Dec 25: FO1; Dec 26: FO1; Dec 27: FO1; Dec 28: FO1; Dec 29: FO1; Dec 30: FO1; Dec 31: FO1; Jan 01: FO1; Jan 02: FO1; Jan 03: FO1; Jan 04: FO1; Jan 05: FO1; Jan 06: Y4; Jan 07: Y4; Jan 08: Y4; Jan 09: Y4; Jan 10: Y4; Jan 11: Y4; Jan 12: Y4; Jan 13: Y4; Jan 14: Y4; Jan 15: Y4; Jan 16: Y4; Jan 17: Y4; Jan 18: Y4; Jan 19: Y4; Jan 20: Y4; Jan 21: Y4; Jan 22: Y4; Jan 23: Y4; Jan 24: Y4; Jan 25: Y4; Jan 26: Y4; Jan 27: Y4; Jan 28: Y4; Jan 29: Y4; Jan 30: Y4; Jan 31: Y4; Feb 01: Y4; Feb 02: Y4; Feb 03: Y4; Feb 04: M5; Feb 05: M5; Feb 06: M5; Feb 25: EQ1; Feb 26: EQ1; Feb 27: EQ1; Feb 28: EQ1; Mar 01: EQ1; Mar 02: EQ1; Mar 03: EQ1; Mar 04: EQ1; Mar 05: EQ1; Mar 06: EQ1; Mar 07: EQ1; Mar 08: EQ1; Mar 09: EQ1; Mar 10: EQ1; Mar 11: EQ2; Mar 12: EQ2; Mar 13: E11; Mar 14: E11; Mar 15: E11; Mar 16: E11; Mar 17: E11; Mar 18: E11; Mar 19: E11; Mar 20: M6; Mar 25: Q1; Mar 26: Q1; Mar 27: Q1; Mar 28: Q1; Mar 29: Q1; Mar 30: Q1; Mar 31: Q1; Apr 01: CN1; Apr 02: CN1; Apr 03: CN1; Apr 04: CN1; Apr 05: CN1; Apr 06: CN1; Apr 07: CN1; Apr 08: MH2; Apr 09: MH2; Apr 10: MH2; Apr 11: MH2; Apr 12: MH2; Apr 13: MH2; Apr 14: MH2; Apr 15: MH2; Apr 16: MH2; Apr 17: MH2; Apr 18: MH2; Apr 19: MH2; Apr 20: MH2; Apr 21: MH2; Apr 22: MH3; Apr 23: MH3; Apr 24: MH3; Apr 25: MH3; Apr 26: MH3; Apr 27: MH3; Apr 28: MH3; Apr 29: MH3; Apr 30: MH3; May 01: MH3; May 02: MH3; May 03: MH3; May 04: MH3; May 05: MH3; May 06: CN2; May 07: CN2; May 08: CN2
[657 empty] | H2 | H2 | H2 | H2 | H2 | H2 | [13 empty] | E7 | E7 | E7 | E7 | E7 | E7 | E7 | [14 empty] | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | DW2 | C12 | C12 | [12 empty] | RF1 | RF1 | RF1 | RF1 | RF1 | RF1 | RF1 |  | DW5 | DW5 | DW5 | DW5 | Q1 | Q1 | Q1 | Q1 | Q1 | Q1 | Q1 | Q1 | Q1 | M4 | M4 | M4 | M4 | M4 | M4 | [56 empty] | P4 | P4 | P4 | [32 empty] | P5 | P5 | P5 | P5 | P5 | P5 | P5 |  |  | E12 | E12 | E12 | E12 | E12
[721 empty] | E8 | E8 | E8 | E8 | E8 | E8 | E8
|  | Restrooms | Sep 11: F2; Sep 12: F2; Sep 13: F2; Sep 14: F2; Sep 15: F2; Sep 17: M2; Sep 18: M2; Sep 19: M2; Sep 22: P2; Sep 23: P2; Sep 24: P2; Sep 25: P2; Sep 26: P2; Oct 01: F3; Oct 02: F3; Oct 03: F3; Oct 04: F3; Oct 05: F3; Oct 06: F3; Oct 07: T3; Oct 08: T3; Oct 09: T3; Oct 14: IS1; Oct 15: IS2; Oct 16: DW1; Oct 17: DW1; Oct 18: DW1; Oct 19: DW1; Oct 20: DW1; Oct 21: DW1; Oct 22: DW1; Oct 23: DW2; Oct 24: DW2; Oct 25: DW2; Oct 26: DW2; Oct 27: DW2; Oct 28: DW2; Oct 29: DW2; Oct 30: DW2; Oct 31: DW2; Nov 01: DW2; Nov 02: DW2; Nov 03: DW2; Nov 04: DW2; Nov 05: DW2; Nov 06: F4; Nov 07: F4; Nov 08: F4; Nov 09: F4; Nov 10: F4; Nov 11: F4; Nov 12: F4; Nov 13: M4; Nov 14: M4; Nov 15: M4; Nov 16: M4; Nov 17: M4; Nov 18: M4; Nov 19: E13; Nov 20: E13; Nov 21: E13; Nov 26: H3; Nov 27: H3; Nov 28: H3; Nov 29: H3; Nov 30: H3; Dec 01: H3; Dec 02: IS3; Dec 03: IS4; Dec 04: DW3; Dec 05: DW3; Dec 06: DW3; Dec 07: DW3; Dec 08: DW3; Dec 09: DW3; Dec 10: DW3; Dec 11: DW2; Dec 12: DW2; Dec 13: DW2; Dec 14: DW2; Dec 15: DW2; Dec 16: DW2; Dec 17: DW2; Dec 18: DW2; Dec 19: DW2; Dec 20: DW2; Dec 21: DW2; Dec 22: DW2; Dec 23: DW2; Dec 24: DW2; Dec 26: TE1; Dec 27: TE1; Dec 28: TE1; Dec 29: TE1; Dec 30: TE1; Dec 31: TE1; Jan 01: TE1; Jan 02: TE1; Jan 03: TE1; Jan 04: TE1; Jan 05: TE1; Jan 06: TE1; Jan 07: TE1; Jan 08: TE1; Jan 09: TE1; Jan 10: TE1; Jan 11: TE1; Jan 12: TE1; Jan 13: TE1; Jan 14: TE1; Jan 15: TE1; Jan 16: TE1; Jan 17: TE1; Jan 18: TE1; Jan 19: TE1; Jan 20: TE1; Jan 21: TE1; Jan 22: TE1; Jan 23: TE1; Jan 24: TE1; Jan 25: TE1; Jan 26: TE1; Jan 27: P4; Jan 28: P4; Jan 29: P4; Jan 30: P4; Jan 31: P4; Feb 01: P4; Feb 02: P4; Feb 03: P4; Feb 04: P4; Feb 05: P4; Feb 06: P4; Feb 07: P4; Feb 08: P4; Feb 09: P4; Feb 10: Y5; Feb 11: Y5; Feb 12: Y5; Feb 13: Y5; Feb 16: P5; Feb 17: P5; Feb 18: Y6; Feb 19: Y6; Feb 20: Y6; Feb 21: Y6; Feb 22: Y6; Feb 23: Y6; Feb 24: Y6; Feb 25: Y7; Feb 26: Y7; Feb 27: Y7; Feb 28: Y7; Mar 01: Y7; Mar 02: Y7; Mar 03: Y7; Mar 04: EQ2; Mar 05: EQ2; Mar 06: E12; Mar 07: E12; Mar 08: E12; Mar 09: E12; Mar 10: E12; Mar 16: CN1; Mar 17: CN1; Mar 18: CN1; Mar 19: CN1; Mar 20: CN1; Mar 23: MH2; Mar 24: MH2; Mar 25: MH2; Mar 26: MH2; Mar 27: MH2; Mar 28: MH2; Mar 29: MH2; Mar 30: MH2; Mar 31: MH2; Apr 01: MH2; Apr 02: MH2; Apr 03: MH2; Apr 06: MH3; Apr 07: MH3; Apr 08: MH3; Apr 09: MH3; Apr 10: MH3; Apr 11: MH3; Apr 12: MH3; Apr 13: MH3; Apr 14: MH3; Apr 15: MH3; Apr 16: MH3; Apr 17: MH3; Apr 20: CN2; Apr 21: CN2; Apr 22: CN2
[663 empty] | H2 | H2 | H2 | H2 | H2 | H2 | [14 empty] | P3 | P3 | P3 | P3 | [39 empty] | E10 | E10 | E10 | E10 | E10 | E10 | [36 empty] | PT2 | PT2 | PT2 | PT2 | PT2 | PT2 | [59 empty] | E11 | E11 | E11 | E11 | E11 | E11 | E11
[684 empty] | E7 | E7 | E7 | E7 | E7 | E7
|  | South Concessions | Sep 22: F2; Sep 23: F2; Sep 24: H2; Sep 25: H2; Sep 29: P2; Sep 30: P2; Oct 01: P2; Oct 02: P2; Oct 03: P2; Oct 07: F3; Oct 08: F3; Oct 09: F3; Oct 13: P3; Oct 14: P3; Oct 15: P3; Oct 16: P3; Oct 20: IS1; Oct 21: IS2; Oct 23: DW1; Oct 24: DW1; Oct 27: DW2; Oct 28: DW2; Oct 29: DW2; Oct 30: DW2; Oct 31: DW2; Nov 01: DW2; Nov 02: DW2; Nov 03: DW2; Nov 04: DW2; Nov 05: DW5; Nov 06: M7; Nov 07: M7; Nov 10: RF1; Nov 11: RF1; Nov 12: RF1; Nov 13: M3; Nov 14: M3; Nov 15: M3; Nov 16: M3; Nov 17: M3; Nov 18: M3; Nov 19: M3; Nov 20: Q2; Nov 21: Q2; Nov 22: Q2; Nov 23: Q2; Nov 24: Q2; Nov 25: M4; Nov 26: M4; Dec 01: H3; Dec 02: E13; Dec 03: E13; Dec 04: E10; Dec 05: E10; Dec 06: E10; Dec 07: E10; Dec 08: E10; Dec 09: IS3; Dec 10: IS4; Dec 11: FO1; Dec 12: FO1; Dec 13: FO1; Dec 14: FO1; Dec 15: FO1; Dec 16: FO1; Dec 17: FO1; Dec 18: Y4; Dec 19: Y4; Dec 20: Y4; Dec 21: Y4; Dec 22: Y4; Dec 23: Y4; Dec 24: Y4; Dec 25: Y4; Dec 26: Y4; Dec 27: Y4; Dec 28: Y4; Dec 29: Y4; Dec 30: Y4; Dec 31: Y4; Jan 01: Y4; Jan 02: Y4; Jan 05: P4; Jan 06: P4; Jan 08: EQ1; Jan 09: EQ1; Jan 10: EQ1; Jan 11: EQ1; Jan 12: EQ1; Jan 13: EQ1; Jan 14: EQ1; Jan 15: EQ1; Jan 16: P5; Jan 17: P5; Jan 18: P5; Jan 19: P5; Jan 20: P5; Jan 23: M6; Jan 30: E12; Jan 31: E12; Feb 01: E12; Feb 02: E12; Feb 03: Q1; Feb 04: Q1; Feb 05: CN1; Feb 06: CN1; Feb 07: CN1; Feb 08: CN1; Feb 09: CN1; Feb 10: CN1; Feb 11: CN1; Feb 12: MH2; Feb 13: MH2; Feb 14: MH2; Feb 15: MH2; Feb 16: MH2; Feb 17: MH2; Feb 18: MH2; Feb 19: MH2; Feb 20: MH2; Feb 21: MH2; Feb 22: MH2; Feb 23: MH2; Feb 24: MH2; Feb 25: MH2; Feb 26: MH3; Feb 27: MH3; Feb 28: MH3; Mar 01: MH3; Mar 02: MH3; Mar 03: MH3; Mar 04: MH3; Mar 05: MH3; Mar 06: MH3; Mar 07: MH3; Mar 08: MH3; Mar 09: MH3; Mar 10: MH3; Mar 11: MH3; Mar 12: CN2; Mar 13: CN2; Mar 14: CN2; Mar 15: CN2; Mar 16: CN2
[670 empty] | M2 | M2 | M2 | [17 empty] | E7 | E7 | E7 | E7 | [18 empty] | Y3 | Y3 | [14 empty] | E8 | E8 | E8 | E8 | E8 | E8 | E8 | E8 | E8 | E8 | E8 | [34 empty] | M5 | M5 | M5 | [8 empty] | E11 | E11 | E11 | E11 | E11 | E11 | E11 | EQ2 | EQ2 | EQ2 | EQ2
[713 empty] | PT3 | PT3
| Northeast | Concourse Level | Oct 17: F2; Oct 18: F2; Oct 19: F2; Oct 20: F2; Oct 21: F2; Oct 22: M2; Oct 23: M2; Oct 24: M2; Nov 03: P6; Nov 04: P6; Nov 05: P6; Nov 06: P6; Nov 07: P6; Nov 12: IS1; Nov 13: IS2; Nov 14: DW1; Nov 15: DW1; Nov 16: DW1; Nov 17: DW1; Nov 18: DW1; Nov 19: DW2; Nov 20: DW2; Nov 21: DW2; Nov 22: DW2; Nov 23: DW2; Nov 24: DW2; Nov 25: DW2; Nov 26: DW2; Nov 27: DW2; Nov 28: DW2; Nov 29: DW2; Nov 30: DW2; Dec 01: DW2; Dec 02: F4; Dec 03: M3; Dec 04: M3; Dec 05: M3; Dec 06: M3; Dec 07: M3; Dec 08: M3; Dec 09: Q3; Dec 10: Q3; Dec 11: Q3; Dec 12: M4; Dec 13: M4; Dec 14: M4; Dec 15: M4; Dec 16: H3; Dec 17: IS3; Dec 18: IS4; Dec 19: DW3; Dec 22: DW2; Dec 23: DW2; Dec 24: DW2; Dec 25: DW2; Dec 26: DW2; Dec 27: DW2; Dec 28: DW2; Dec 29: DW2; Jan 06: PT1; Jan 07: PT1; Jan 08: PT1; Jan 14: DW4; Jan 20: P4; Jan 21: P4; Jan 22: P4; Jan 23: P4; Jan 26: Y10; Jan 27: Y10; Jan 28: Y10; Jan 29: Y10; Jan 30: Y10; Feb 04: EQ2; Feb 05: EQ2; Feb 06: P5; Feb 07: P5; Feb 08: P5; Feb 09: P5; Feb 11: Q1; Feb 12: Q1; Feb 13: CN1; Feb 14: CN1; Feb 15: CN1; Feb 16: CN1; Feb 17: CN1; Feb 18: CN1; Feb 19: CN1; Feb 20: MH2; Feb 21: MH2; Feb 22: MH2; Feb 23: MH2; Feb 24: MH2; Feb 25: MH2; Feb 26: MH2; Feb 27: MH2; Feb 28: MH2; Mar 01: MH2; Mar 02: MH2; Mar 03: MH2; Mar 04: MH2; Mar 05: MH2; Mar 06: MH3; Mar 07: MH3; Mar 08: MH3; Mar 09: MH3; Mar 10: MH3; Mar 11: MH3; Mar 12: MH3; Mar 13: MH3; Mar 14: MH3; Mar 15: MH3; Mar 16: MH3; Mar 17: MH3; Mar 18: MH3; Mar 19: MH3; Mar 20: CN2; Mar 21: CN2; Mar 22: CN2; Mar 23: CN2
[698 empty] | H2 | H2 | H2 | [10 empty] | F3 | F3 | E7 | E7 | E7 | E7 | E7 | E7 | [20 empty] | M7 | RF1 | RF1 | RF1 | RF1 | RF1 | RF1 |  |  |  | E13 | E13 | E13 | E13 | [21 empty] | FO1 | FO1 | FO1 | FO1 | FO1 | FO1 | FO1 | FO1 | TE1 | TE1 | TE1 | TE1 | TE1 | TE1 | [9 empty] | Y7 | Y7 |  |  |  |  | E11 | E11 | E11 |  |  | M6
[739 empty] | Y3 | Y3 | Y3 | Y3 | Y3 | Y3 | Y3 |  |  |  | E10 | E10 | E10 | E10 | E10 | [28 empty] | Y4 | Y4 | Y4 | Y4 | Y4 | Y4 | Y4 | Y4 | Y4 | Y4 | Y4 | Y4 | Y4 | Y4 | Y4 | Y4 | M5 | M5 | M5 | M5 | M5 | [5 empty] | E12 | E12
[798 empty] | EQ1 | EQ1 | EQ1 | EQ1 | EQ1
| Seating Bowl - Main Building | Concourse Level | Mar 04: C14; Mar 05: C14; Mar 06: C14; Mar 07: C14; Mar 08: C14; Mar 09: C14; Mar 10: C14; Mar 11: C14; Mar 12: C14; Mar 13: C14; Mar 14: C14; Mar 15: C14; Mar 16: C14; Mar 17: C14; Mar 18: C14; Mar 19: C14; Mar 20: C14; Mar 21: C14; Mar 22: C14; Mar 23: C14; Mar 24: C14; Mar 25: C14; Mar 26: MS2; Mar 27: MS2; Mar 28: MS2; Mar 29: MS2; Mar 30: MS2; Mar 31: MS2; Apr 01: MS2; Apr 02: MS2; Apr 03: MS2; Apr 04: MS2; Apr 05: MS2; Apr 06: MS2; Apr 07: MS2; Apr 08: MS2; Apr 09: EQ4; Apr 10: EQ4; Apr 11: EQ4; Apr 12: EQ4; Apr 13: EQ4; Apr 14: EQ4; Apr 15: EQ4; Apr 16: EQ4; Apr 17: EQ4; Apr 18: EQ4; Apr 19: EQ4; Apr 20: EQ4; Apr 21: EQ4; Apr 22: EQ4; Apr 23: EQ4; Apr 24: EQ4; Apr 25: EQ4; Apr 26: EQ4; Apr 27: EQ4; Apr 28: EQ4; Apr 29: EQ4; Apr 30: EQ4; May 01: EQ4; May 02: EQ4; May 03: EQ4; May 04: EQ4; May 05: EQ4; May 06: EQ4; May 07: EQ4; May 08: EQ4; May 09: EQ4; May 10: EQ4; May 11: EQ4; May 12: EQ4; May 13: EQ4; May 14: CN1; May 15: CN1; May 16: CN1; May 17: CN1; May 18: CN1; May 19: CN1; May 20: CN1; May 21: CN1; May 22: CN1; May 23: CN1; May 24: CN1; May 25: CN1; May 26: CN1; May 27: CN1; May 28: CN1; May 29: MH2; May 30: MH2; May 31: MH2; Jun 01: MH2; Jun 02: MH2; Jun 03: MH2; Jun 04: MH2; Jun 05: MH2; Jun 06: MH2; Jun 07: MH2; Jun 08: MH2; Jun 09: MH2; Jun 10: MH2; Jun 11: MH2; Jun 12: MH3; Jun 13: MH3; Jun 14: MH3; Jun 15: MH3; Jun 16: MH3; Jun 17: MH3; Jun 18: MH3; Jun 19: MH3; Jun 20: MH3; Jun 21: MH3; Jun 22: MH3; Jun 23: MH3; Jun 24: MH3; Jun 25: MH3; Jun 26: CN2; Jun 27: CN2; Jun 28: CN2; Jun 29: CN2
Note on SP5: Activity Name: Canopy Submittals by Trade Partner Phase: Procurement Location: Canopies Trade: Manhattan Start Date: 16-Apr-2025 End Date: 11-Jun-2025
Note on UU5: Activity Name: Review Shop Drawings for Approval Phase: Procurement Location: Canopies Trade: Manhattan Start Date: 12-Jun-2025 End Date: 02-Jul-2025
Note on VP5: Activity Name: PTFE Fabrication Drawings Phase: Procurement Location: Canopies Trade: Manhattan Start Date: 03-Jul-2025 End Date: 26-Sep-2025
Note on YZ5: Activity Name: PTFE Frabrication Phase: Procurement Location: Canopies Trade: Manhattan Start Date: 29-Sep-2025 End Date: 20-Mar-2026
Note on AFS5: Activity Name: Start of Shipping PTFE Fabric to Site Phase: Procurement Location: Canopies Trade: Manhattan Start Date: 23-Mar-2026 End Date: 17-Apr-2026
Note on VP6: Activity Name: PTFE Procurement Phase: Procurement Location: Canopies Trade: Manhattan Start Date: 03-Jul-2025 End Date: 26-Sep-2025
Note on PX10: Activity Name: Submit Shop Drawings for Review Phase: Procurement Location: Foundations Trade: Manhattan Start Date: 05-Feb-2025 End Date: 04-Mar-2025
Note on QZ10: Activity Name: Review Shop Drawings for Approval Phase: Procurement Location: Foundations Trade: Manhattan Start Date: 05-Mar-2025 End Date: 18-Mar-2025
Note on RN10: Activity Name: Fabrication/Delivery Phase: Procurement Location: Foundations Trade: Manhattan Start Date: 19-Mar-2025 End Date: 08-Apr-2025
Note on TB13: Activity Name: Stone/Tile Submittals Phase: Procurement Location: Interiors Trade: Manhattan Start Date: 28-Apr-2025 End Date: 09-Jun-2025
Note on US13: Activity Name: Stone/Tile Procurement Phase: Procurement Location: Interiors Trade: Manhattan Start Date: 10-Jun-2025 End Date: 02-Sep-2025
Note on AOD13: Activity Name: Monumental Stair - Field Measure & Fabricate Phase: Procurement Location: Interiors Trade: Manhattan Start Date: 28-Oct-2026 End Date: 04-Jan-2027
Note on QX16: Activity Name: Generator Submittals Phase: Procurement Location: MEP/LV Trade: Manhattan Start Date: 03-Mar-2025 End Date: 21-Mar-2025
Note on RS16: Activity Name: Generator Submittal Review Phase: Procurement Location: MEP/LV Trade: Manhattan Start Date: 24-Mar-2025 End Date: 11-Apr-2025
Note on SN16: Activity Name: Generator Procurement Phase: Procurement Location: MEP/LV Trade: Manhattan Start Date: 14-Apr-2025 End Date: 05-Aug-2025
Note on QX17: Activity Name: Sports Lighting Shop Drawings Submittal Phase: Procurement Location: MEP/LV Trade: Manhattan Start Date: 03-Mar-2025 End Date: 02-May-2025
Note on TI17: Activity Name: Sports Lighting Submittal Review Phase: Procurement Location: MEP/LV Trade: Manhattan Start Date: 05-May-2025 End Date: 23-May-2025
Note on UE17: Activity Name: Sports Lighting Procurement Phase: Procurement Location: MEP/LV Trade: Manhattan Start Date: 27-May-2025 End Date: 19-Aug-2025
Note on MI21: Activity Name: Core & Shell Bid Package Prep Phase: Procurement Location: Material Trade: Manhattan Start Date: 04-Nov-2024 End Date: 08-Nov-2024
Note on MP21: Activity Name: Canopy Bidding Phase: Procurement Location: Material Trade: Manhattan Start Date: 11-Nov-2024 End Date: 06-Jan-2025
Note on OU21: Activity Name: Bid Day pushed by HSG (Impact) Phase: Procurement Location: Material Trade: Manhattan Start Date: 07-Jan-2025 End Date: 15-Jan-2025
Note on PD21: Activity Name: Bid Opening pushed by HSG & COF (Impact) Phase: Procurement Location: Material Trade: Manhattan Start Date: 16-Jan-2025 End Date: 21-Jan-2025
Note on PJ21: Activity Name: Bid Review and Leveling Phase: Procurement Location: Material Trade: Manhattan Start Date: 22-Jan-2025 End Date: 27-Jan-2025
Note on PP21: Activity Name: Review/Award CMaR Phase: Procurement Location: Material Trade: Manhattan Start Date: 28-Jan-2025 End Date: 31-Jan-2025
Note on PV21: Activity Name: Issue LNTPs for Demo/Foundations/Steel/Canopies/MEP Phase: Procurement Location: Material Trade: Manhattan Start Date: 03-Feb-2025 End Date: 04-Feb-2025
Note on QL21: Activity Name: FGMP Submittal & Amendment Phase: Procurement Location: Material Trade: Manhattan Start Date: 19-Feb-2025 End Date: 21-Feb-2025
Note on QQ21: Activity Name: Execute Finish Subcontracts Phase: Procurement Location: Material Trade: Manhattan Start Date: 24-Feb-2025 End Date: 25-Apr-2025
Note on MP22: Activity Name: Foundations Bidding Phase: Procurement Location: Material Trade: Manhattan Start Date: 11-Nov-2024 End Date: 06-Jan-2025
Note on PV22: Activity Name: Canopy Contract Award Phase: Procurement Location: Material Trade: Manhattan Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on MP23: Activity Name: Structural SteelBidding Phase: Procurement Location: Material Trade: Manhattan Start Date: 11-Nov-2024 End Date: 06-Jan-2025
Note on PV23: Activity Name: Foundations Contract Award Phase: Procurement Location: Material Trade: Manhattan Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on MP24: Activity Name: Remaining Core & Shell Bidding Phase: Procurement Location: Material Trade: Manhattan Start Date: 11-Nov-2024 End Date: 06-Jan-2025
Note on PV24: Activity Name: Structural Steel Phase: Procurement Location: Material Trade: Manhattan Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on PV25: Activity Name: MEP Make-Safe Contract Award Phase: Procurement Location: Material Trade: Manhattan Start Date: 03-Feb-2025 End Date: 14-Feb-2025
Note on PV26: Activity Name: Demo Contract Award Phase: Procurement Location: Material Trade: Manhattan Start Date: 03-Feb-2025 End Date: 14-Feb-2025
Note on PV27: Activity Name: Interior Finishes Bidding Phase: Procurement Location: Material Trade: Manhattan Start Date: 03-Feb-2025 End Date: 18-Feb-2025
Note on PV28: Activity Name: Execute Elevator Subcontract Phase: Procurement Location: Material Trade: Manhattan Start Date: 03-Feb-2025 End Date: 21-Feb-2025
Note on PV29: Activity Name: Execute Core & Shell Contracts Phase: Procurement Location: Material Trade: Manhattan Start Date: 03-Feb-2025 End Date: 28-Feb-2025
Note on PX33: Activity Name: Submit Shop Drawings for Review Phase: Procurement Location: Structural Steel Trade: Manhattan Start Date: 05-Feb-2025 End Date: 15-Apr-2025
Note on SP33: Activity Name: Review Shop Drawings for Approval Phase: Procurement Location: Structural Steel Trade: Manhattan Start Date: 16-Apr-2025 End Date: 06-May-2025
Note on TY33: Activity Name: Fabrication/Delivery Phase: Procurement Location: Structural Steel Trade: Manhattan Start Date: 21-May-2025 End Date: 31-Jul-2025
Note on QE34: Activity Name: Structural SteelProcurement Phase: Procurement Location: Structural Steel Trade: Manhattan Start Date: 12-Feb-2025 End Date: 20-May-2025
Note on QE35: Activity Name: Metal Decking Procurement Phase: Procurement Location: Structural Steel Trade: Manhattan Start Date: 12-Feb-2025 End Date: 28-May-2025
Note on QQ38: Activity Name: Elevator Shop Drawings Submittal Phase: Procurement Location: Vertical Trade: Manhattan Start Date: 24-Feb-2025 End Date: 04-Apr-2025
Note on ADL38: Activity Name: West Elevator Shop Drawings Submittal Phase: Procurement Location: Vertical Trade: Manhattan Start Date: 23-Jan-2026 End Date: 05-Mar-2026
Note on AFB38: Activity Name: Review Shop Drawings for Approval Phase: Procurement Location: Vertical Trade: Manhattan Start Date: 06-Mar-2026 End Date: 26-Mar-2026
Note on AFW38: Activity Name: Fabrication/Delivery Phase: Procurement Location: Vertical Trade: Manhattan Start Date: 27-Mar-2026 End Date: 27-Oct-2026
Note on AKP42: Activity Name: East Canopy Installation Complete Phase: MILESTONES/HAMMOCKS Location: Canopy Trade: Manhattan Start Date: 28-Jul-2026 End Date: 28-Jul-2026
Note on ADJ43: Activity Name: East Building Conditioned Air Phase: MILESTONES/HAMMOCKS Location: Conditioned Air Trade: Manhattan Start Date: 21-Jan-2026 End Date: 21-Jan-2026
Note on AAL44: Activity Name: East Building Dry-in Phase: MILESTONES/HAMMOCKS Location: Dry-in Trade: Manhattan Start Date: 06-Nov-2025 End Date: 06-Nov-2025
Note on ZC45: Activity Name: East Structure Complete Phase: MILESTONES/HAMMOCKS Location: Structure Trade: Manhattan Start Date: 02-Oct-2025 End Date: 02-Oct-2025
Note on AJN46: Activity Name: East Building TCO (excluding Canopy) Phase: MILESTONES/HAMMOCKS Location: TCO Trade: Manhattan Start Date: 30-Jun-2026 End Date: 30-Jun-2026
Note on PV47: Activity Name: Notice to Proceed For Construction Phase: MAJOR MILESTONES Location: All Trade: Manhattan Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on BDN47: Activity Name: Close-out & Final Billings Phase: MAJOR MILESTONES Location: All Trade: Manhattan Start Date: 02-Dec-2027 End Date: 04-Feb-2028
Note on BFZ48: Activity Name: Final Completion Phase: MAJOR MILESTONES Location: All Trade: Manhattan Start Date: 04-Feb-2028 End Date: 04-Feb-2028
Note on QK50: Activity Name: Start of East Construction Phase: MAJOR MILESTONES Location: East Trade: Manhattan Start Date: 18-Feb-2025 End Date: 18-Feb-2025
Note on AJN50: Activity Name: East Side TCO Phase: MAJOR MILESTONES Location: East Trade: Manhattan Start Date: 30-Jun-2026 End Date: 30-Jun-2026
Note on QK51: Activity Name: East Building & Canopy Construction Phase: MAJOR MILESTONES Location: East Trade: Manhattan Start Date: 18-Feb-2025 End Date: 28-Jul-2026
Note on AKJ53: Activity Name: Start of North Construction Phase: MAJOR MILESTONES Location: North Trade: Manhattan Start Date: 22-Jul-2026 End Date: 22-Jul-2026
Note on BDK53: Activity Name: North Endzone Completion Phase: MAJOR MILESTONES Location: North Trade: Manhattan Start Date: 29-Nov-2027 End Date: 29-Nov-2027
Note on AKJ54: Activity Name: North Ticket Construction Phase: MAJOR MILESTONES Location: North Trade: Manhattan Start Date: 22-Jul-2026 End Date: 29-Nov-2027
Note on AJN56: Activity Name: Phase 1 Substantial Completion Phase: MAJOR MILESTONES Location: Phase 1 Trade: Manhattan Start Date: 30-Jun-2026 End Date: 30-Jun-2026
Note on BDM57: Activity Name: Phase 2 Substantial Completion Phase: MAJOR MILESTONES Location: Phase 2 Trade: Manhattan Start Date: 01-Dec-2027 End Date: 01-Dec-2027
Note on AHW58: Activity Name: Start of West Construction Phase: MAJOR MILESTONES Location: West Trade: Manhattan Start Date: 18-May-2026 End Date: 18-May-2026
Note on BDM58: Activity Name: West Side TCO Phase: MAJOR MILESTONES Location: West Trade: Manhattan Start Date: 01-Dec-2027 End Date: 01-Dec-2027
Note on AHW59: Activity Name: West Building & Canopy Construction Phase: MAJOR MILESTONES Location: West Trade: Manhattan Start Date: 18-May-2026 End Date: 01-Dec-2027
Note on D61: Activity Name: Schematic Design-Full Project (Architecture and Structure) Phase: SCHEMATIC DESIGN Location: Design Trade: Architect Start Date: 27-Nov-2023 End Date: 01-Apr-2024
Note on EA61: Activity Name: SDs Pricing and Budget Reviews Phase: SCHEMATIC DESIGN Location: Design Trade: Architect Start Date: 02-Apr-2024 End Date: 08-Apr-2024
Note on EH63: Activity Name: Design Development 50% Phase: DESIGN DEVELOPMENT Location: Design Trade: Architect Start Date: 09-Apr-2024 End Date: 26-Apr-2024
Note on FB63: Activity Name: Design Development 50% Pricing to Review Phase: DESIGN DEVELOPMENT Location: Design Trade: Architect Start Date: 29-Apr-2024 End Date: 17-May-2024
Note on HF63: Activity Name: DDs Pricing and Budget Reviews Phase: DESIGN DEVELOPMENT Location: Design Trade: Architect Start Date: 24-Jun-2024 End Date: 22-Jul-2024
Note on FB64: Activity Name: Design Development 100% Phase: DESIGN DEVELOPMENT Location: Design Trade: Architect Start Date: 29-Apr-2024 End Date: 21-Jun-2024
Note on HF64: Activity Name: SteelTonnage Package Phase: DESIGN DEVELOPMENT Location: Design Trade: Architect Start Date: 24-Jun-2024 End Date: 30-Aug-2024
Note on FB65: Activity Name: Preliminary SteelTonnage Package Phase: DESIGN DEVELOPMENT Location: Design Trade: Architect Start Date: 29-Apr-2024 End Date: 21-Jun-2024
Note on GH69: Activity Name: Canopy Structure SteelPackage Phase: PERMIT PACKAGE Location: Canopy Trade: Manhattan Start Date: 31-May-2024 End Date: 30-Aug-2024
Note on GH70: Activity Name: Civil Package (includes duct bank, fire lane, site perimeter u Phase: PERMIT PACKAGE Location: Civil Trade: Manhattan Start Date: 31-May-2024 End Date: 30-Aug-2024
Note on GH71: Activity Name: Foundations Package (West and Northwest Building) Permit Phase: PERMIT PACKAGE Location: Foundations Trade: Manhattan Start Date: 31-May-2024 End Date: 30-Aug-2024
Note on JX72: Activity Name: Early Permit Packages - Never Issued, Merged with C&S Pac Phase: PERMIT PACKAGE Location: Permit Trade: Manhattan Start Date: 02-Sep-2024 End Date: 01-Nov-2024
Note on GH73: Activity Name: SteelPackage (Primary Structural Framing) Phase: PERMIT PACKAGE Location: Steel Trade: Manhattan Start Date: 31-May-2024 End Date: 30-Aug-2024
Note on HF74: Activity Name: Core and Shell / Permit / Demolition Package Phase: CONSTRUCTION DOCUMENTS Location: Documents Trade: Manhattan Start Date: 24-Jun-2024 End Date: 01-Nov-2024
Note on MI74: Activity Name: CoServ Relocation Designs & Approvals (Elect & Gas) Phase: CONSTRUCTION DOCUMENTS Location: Documents Trade: Manhattan Start Date: 04-Nov-2024 End Date: 30-Jan-2025
Note on MI75: Activity Name: Interiors Finish Out Package Phase: CONSTRUCTION DOCUMENTS Location: Documents Trade: Manhattan Start Date: 04-Nov-2024 End Date: 31-Jan-2025
Note on MT76: Activity Name: ASI-01 Issued Phase: CONSTRUCTION DOCUMENTS Location: Documents Trade: Manhattan Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on NA76: Activity Name: ASI-02 Issued Phase: CONSTRUCTION DOCUMENTS Location: Documents Trade: Manhattan Start Date: 22-Nov-2024 End Date: 22-Nov-2024
Note on OA76: Activity Name: ASI-03 Issued Phase: CONSTRUCTION DOCUMENTS Location: Documents Trade: Manhattan Start Date: 18-Dec-2024 End Date: 18-Dec-2024
Note on OW76: Activity Name: ASI-04 Issued Phase: CONSTRUCTION DOCUMENTS Location: Documents Trade: Manhattan Start Date: 09-Jan-2025 End Date: 09-Jan-2025
Note on PA76: Activity Name: ASI-05 Issued Phase: CONSTRUCTION DOCUMENTS Location: Documents Trade: Manhattan Start Date: 13-Jan-2025 End Date: 13-Jan-2025
Note on PA80: Activity Name: Building Permit (East Demo) - Review & Approval Phase: PERMITS Location: All Trade: Manhattan Start Date: 13-Jan-2025 End Date: 14-Jan-2025
Note on KE81: Activity Name: East-North Site Plans - City Review Phase: PERMITS Location: East Trade: Manhattan Start Date: 09-Sep-2024 End Date: 04-Nov-2024
Note on MP81: Activity Name: East-North Civil - City Engineering Review Phase: PERMITS Location: East Trade: Manhattan Start Date: 11-Nov-2024 End Date: 11-Dec-2024
Note on NU81: Activity Name: East-North Civil - Comment Review & Resubmittal Phase: PERMITS Location: East Trade: Manhattan Start Date: 12-Dec-2024 End Date: 17-Dec-2024
Note on OA81: Activity Name: East-North Civil - City Engineering Re-Review Phase: PERMITS Location: East Trade: Manhattan Start Date: 18-Dec-2024 End Date: 09-Jan-2025
Note on OX81: Activity Name: East-North Civil - Comment Review & Resubmittal 2 Phase: PERMITS Location: East Trade: Manhattan Start Date: 10-Jan-2025 End Date: 21-Jan-2025
Note on PJ81: Activity Name: East-North Civil - City Engineering Re-Review 2 Phase: PERMITS Location: East Trade: Manhattan Start Date: 22-Jan-2025 End Date: 11-Feb-2025
Note on KF82: Activity Name: East-North LS Plans - City Review Phase: PERMITS Location: East Trade: Manhattan Start Date: 10-Sep-2024 End Date: 04-Nov-2024
Note on PX82: Activity Name: Building Permit (East) - Review & Approval Phase: PERMITS Location: East Trade: Manhattan Start Date: 05-Feb-2025 End Date: 25-Feb-2025
Note on MP86: Activity Name: Facade - Submittal Package for City Review Phase: PERMITS Location: Facade Trade: Manhattan Start Date: 11-Nov-2024 End Date: 16-Dec-2024
Note on OG86: Activity Name: Facade (all sides) - Comment Review & Resubmittal Phase: PERMITS Location: Facade Trade: Manhattan Start Date: 24-Dec-2024 End Date: 14-Jan-2025
Note on PC86: Activity Name: Facade (all sides) - City Re-Review Phase: PERMITS Location: Facade Trade: Manhattan Start Date: 15-Jan-2025 End Date: 28-Jan-2025
Note on NY87: Activity Name: Facade (all sides) - City Review Phase: PERMITS Location: Facade Trade: Manhattan Start Date: 16-Dec-2024 End Date: 23-Dec-2024
Note on MP90: Activity Name: West Site & LS Plans - Submittal Package for City Review Phase: PERMITS Location: West Trade: Manhattan Start Date: 11-Nov-2024 End Date: 16-Dec-2024
Note on OG90: Activity Name: West Site & LS Plans - Comment Review & Resubmittal Phase: PERMITS Location: West Trade: Manhattan Start Date: 24-Dec-2024 End Date: 14-Jan-2025
Note on PC90: Activity Name: West Site & LS Plans - City Re-Review Phase: PERMITS Location: West Trade: Manhattan Start Date: 15-Jan-2025 End Date: 28-Jan-2025
Note on PQ90: Activity Name: West Civil - Submittal Package for City Engineering Review Phase: PERMITS Location: West Trade: Manhattan Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on PX90: Activity Name: West Civil - City Engineering Review Phase: PERMITS Location: West Trade: Manhattan Start Date: 05-Feb-2025 End Date: 18-Feb-2025
Note on QS90: Activity Name: Building Permit (West) - Review & Approval Phase: PERMITS Location: West Trade: Manhattan Start Date: 26-Feb-2025 End Date: 18-Mar-2025
Note on NY91: Activity Name: West Site & LS Plans - City Review Phase: PERMITS Location: West Trade: Manhattan Start Date: 16-Dec-2024 End Date: 23-Dec-2024
Note on OU95: Activity Name: FC Dallas IT & Cell/DAS Equipment Removed/Relocated Phase: DEMOLITION Location: East Trade: Telecommunications Start Date: 07-Jan-2025 End Date: 03-Feb-2025
Note on PW95: Activity Name: Project Mobilization Phase: DEMOLITION Location: East Trade: Manhattan Start Date: 04-Feb-2025 End Date: 17-Feb-2025
Note on QS95: Activity Name: Trace/Tag/Make Safe MEP Systems Phase: DEMOLITION Location: East Trade: MEP Start Date: 26-Feb-2025 End Date: 11-Mar-2025
Note on RL95: Activity Name: Mass Demolition-Excavation Phase: DEMOLITION Location: East Trade: Demolition Start Date: 17-Mar-2025 End Date: 04-Apr-2025
Note on QZ96: Activity Name: Precision Demo & Temp Protection Phase: DEMOLITION Location: East Trade: Demolition Start Date: 05-Mar-2025 End Date: 18-Mar-2025
Note on TP100: Activity Name: Drilled Piers Phase: FOUNDATIONS Location: Concession Wings Trade: Concrete Start Date: 12-May-2025 End Date: 16-May-2025
Note on TW100: Activity Name: Drilled Piers Phase: FOUNDATIONS Location: Concession Wings Trade: Concrete Start Date: 19-May-2025 End Date: 23-May-2025
Note on US100: Activity Name: Plumbing Underground Phase: FOUNDATIONS Location: Concession Wings Trade: Plumbing Start Date: 10-Jun-2025 End Date: 23-Jun-2025
Note on VN100: Activity Name: Slab on Grade - Rock/Fine Grade/FRP Phase: FOUNDATIONS Location: Concession Wings Trade: Concrete Start Date: 01-Jul-2025 End Date: 22-Jul-2025
Note on WO100: Activity Name: Slab on Grade - Rock/Fine Grade/FRP Phase: FOUNDATIONS Location: Concession Wings Trade: Concrete Start Date: 28-Jul-2025 End Date: 15-Aug-2025
Note on TW101: Activity Name: Grade Beams - Excavate/FRP Phase: FOUNDATIONS Location: Concession Wings Trade: Concrete Start Date: 19-May-2025 End Date: 09-Jun-2025
Note on US101: Activity Name: Grade Beams - Excavate/FRP Phase: FOUNDATIONS Location: Concession Wings Trade: Concrete Start Date: 10-Jun-2025 End Date: 03-Jul-2025
Note on VT101: Activity Name: Plumbing Underground Phase: FOUNDATIONS Location: Concession Wings Trade: Plumbing Start Date: 07-Jul-2025 End Date: 18-Jul-2025
Note on UZ102: Activity Name: Electrical Underground Phase: FOUNDATIONS Location: Concession Wings Trade: Electrical Start Date: 17-Jun-2025 End Date: 30-Jun-2025
Note on WA102: Activity Name: Electrical Underground Phase: FOUNDATIONS Location: Concession Wings Trade: Electrical Start Date: 14-Jul-2025 End Date: 25-Jul-2025
Note on SO106: Activity Name: Drilled Piers Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 15-Apr-2025 End Date: 17-Apr-2025
Note on SR106: Activity Name: Pier Caps - Excavate/FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 18-Apr-2025 End Date: 23-Apr-2025
Note on SY106: Activity Name: Plumbing Underground Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Plumbing Start Date: 25-Apr-2025 End Date: 01-May-2025
Note on TF106: Activity Name: Electrical Underground Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Electrical Start Date: 02-May-2025 End Date: 08-May-2025
Note on TM106: Activity Name: Slab on Grade - Flex Cap/Fine Grade Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 09-May-2025 End Date: 15-May-2025
Note on TT106: Activity Name: Slab on Grade - FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 16-May-2025 End Date: 22-May-2025
Note on SR107: Activity Name: Grade Beams - Excavate/FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 18-Apr-2025 End Date: 24-Apr-2025
Note on SY107: Activity Name: Camera Platform Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Steel Start Date: 25-Apr-2025 End Date: 07-May-2025
Note on TL107: Activity Name: Seating Bowl Infill Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 08-May-2025 End Date: 14-May-2025
Note on SR111: Activity Name: Drilled Piers Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 18-Apr-2025 End Date: 24-Apr-2025
Note on SY111: Activity Name: Drilled Piers Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 25-Apr-2025 End Date: 30-Apr-2025
Note on TK111: Activity Name: Elevator Pit - Waterproofing Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Waterproofing Start Date: 07-May-2025 End Date: 08-May-2025
Note on TM111: Activity Name: Elevator Pit - Subsoil/Backfill Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Earthworks Start Date: 09-May-2025 End Date: 13-May-2025
Note on TS111: Activity Name: Seating Bowl Infill Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 15-May-2025 End Date: 21-May-2025
Note on TZ111: Activity Name: Seating Bowl Infill Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 22-May-2025 End Date: 29-May-2025
Note on UL111: Activity Name: Slab on Grade - Flex Cap/Fine Grade Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 03-Jun-2025 End Date: 09-Jun-2025
Note on US111: Activity Name: Slab on Grade - FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 10-Jun-2025 End Date: 16-Jun-2025
Note on SY112: Activity Name: Pier Caps - Excavate/FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 25-Apr-2025 End Date: 30-Apr-2025
Note on TL112: Activity Name: Plumbing Underground Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Plumbing Start Date: 08-May-2025 End Date: 14-May-2025
Note on TT112: Activity Name: Slab on Grade - Flex Cap/Fine Grade Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 16-May-2025 End Date: 22-May-2025
Note on UA112: Activity Name: Slab on Grade - FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 23-May-2025 End Date: 30-May-2025
Note on SY113: Activity Name: Elevator Pit - Excavate/FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 25-Apr-2025 End Date: 06-May-2025
Note on TL113: Activity Name: Grade Beams - Excavate/FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 08-May-2025 End Date: 16-May-2025
Note on TW113: Activity Name: Plumbing Underground Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Plumbing Start Date: 19-May-2025 End Date: 23-May-2025
Note on UE113: Activity Name: Electrical Underground Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Electrical Start Date: 27-May-2025 End Date: 02-Jun-2025
Note on TB114: Activity Name: Grade Beams - Excavate/FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 28-Apr-2025 End Date: 07-May-2025
Note on TM114: Activity Name: Electrical Underground Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Electrical Start Date: 09-May-2025 End Date: 15-May-2025
Note on TQ115: Activity Name: Pier Caps - Excavate/FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 13-May-2025 End Date: 16-May-2025
Note on TE116: Activity Name: Drilled Piers Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 01-May-2025 End Date: 07-May-2025
Note on TW116: Activity Name: Pier Caps - Excavate/FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 19-May-2025 End Date: 22-May-2025
Note on UH116: Activity Name: Elevator Pit - Waterproofing Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Waterproofing Start Date: 30-May-2025 End Date: 02-Jun-2025
Note on UL116: Activity Name: Elevator Pit - Subsoil/Backfill Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Earthworks Start Date: 03-Jun-2025 End Date: 05-Jun-2025
Note on UR116: Activity Name: Electrical Underground Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Electrical Start Date: 09-Jun-2025 End Date: 13-Jun-2025
Note on UY116: Activity Name: Slab on Grade - Flex Cap/Fine Grade Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 16-Jun-2025 End Date: 20-Jun-2025
Note on VF116: Activity Name: Slab on Grade - FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 23-Jun-2025 End Date: 27-Jun-2025
Note on TW117: Activity Name: Elevator Pit - Excavate/FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 19-May-2025 End Date: 29-May-2025
Note on UK117: Activity Name: Seating Bowl Infill Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 02-Jun-2025 End Date: 06-Jun-2025
Note on TX118: Activity Name: Grade Beams - Excavate/FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 20-May-2025 End Date: 30-May-2025
Note on UK118: Activity Name: Plumbing Underground Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Plumbing Start Date: 02-Jun-2025 End Date: 06-Jun-2025
Note on TL120: Activity Name: Drilled Piers Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 08-May-2025 End Date: 09-May-2025
Note on UH120: Activity Name: Pier Caps - Excavate/FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 30-May-2025 End Date: 04-Jun-2025
Note on UO120: Activity Name: Camera Platform Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Steel Start Date: 06-Jun-2025 End Date: 18-Jun-2025
Note on VB120: Activity Name: Seating Bowl Infill Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 19-Jun-2025 End Date: 25-Jun-2025
Note on VM120: Activity Name: Slab on Grade - FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 30-Jun-2025 End Date: 07-Jul-2025
Note on UK121: Activity Name: Grade Beams - Excavate/FRP Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 02-Jun-2025 End Date: 05-Jun-2025
Note on UR121: Activity Name: Plumbing Underground Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Plumbing Start Date: 09-Jun-2025 End Date: 13-Jun-2025
Note on UY121: Activity Name: Electrical Underground Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Electrical Start Date: 16-Jun-2025 End Date: 20-Jun-2025
Note on VF121: Activity Name: Slab on Grade - Flex Cap/Fine Grade Phase: FOUNDATIONS Location: Main building - Concourse Level Trade: Concrete Start Date: 23-Jun-2025 End Date: 27-Jun-2025
Note on VN124: Activity Name: Excavate NE building footprint Phase: FOUNDATIONS Location: Northeast Trade: Earthworks Start Date: 01-Jul-2025 End Date: 03-Jul-2025
Note on VT124: Activity Name: Lower Grade Beam at Piers Phase: FOUNDATIONS Location: Northeast Trade: Concrete Start Date: 07-Jul-2025 End Date: 11-Jul-2025
Note on WA124: Activity Name: South Grade Beam Phase: FOUNDATIONS Location: Northeast Trade: Concrete Start Date: 14-Jul-2025 End Date: 18-Jul-2025
Note on WH124: Activity Name: FRP Walls & Pilasters Phase: FOUNDATIONS Location: Northeast Trade: Concrete Start Date: 21-Jul-2025 End Date: 25-Jul-2025
Note on WO124: Activity Name: Upper Grade Beam Phase: FOUNDATIONS Location: Northeast Trade: Concrete Start Date: 28-Jul-2025 End Date: 04-Aug-2025
Note on WW124: Activity Name: Geofoam Install Phase: FOUNDATIONS Location: Northeast Trade: Geofom Start Date: 05-Aug-2025 End Date: 11-Aug-2025
Note on XD124: Activity Name: MEP Underground Phase: FOUNDATIONS Location: Northeast Trade: MEP Start Date: 12-Aug-2025 End Date: 21-Aug-2025
Note on XN124: Activity Name: FRP Slab on Grade Phase: FOUNDATIONS Location: Northeast Trade: Concrete Start Date: 22-Aug-2025 End Date: 26-Aug-2025
Note on RG128: Activity Name: Slab Demo & Removal for gas line Phase: South HOF Location: Main Building Trade: Demolition Start Date: 12-Mar-2025 End Date: 13-Mar-2025
Note on RI128: Activity Name: Install new gas line Phase: South HOF Location: Main Building Trade: Plumbing Start Date: 14-Mar-2025 End Date: 18-Mar-2025
Note on ZV130: Activity Name: Install Field Tunnel Cameras Phase: South HOF Location: Main Building Trade: Equipment Start Date: 21-Oct-2025 End Date: 27-Oct-2025
Note on RN131: Activity Name: Install new gas line Phase: South HOF Location: Main Building Trade: Plumbing Start Date: 19-Mar-2025 End Date: 21-Mar-2025
Note on VP131: Activity Name: Open Roof for Steel& Sleeves Phase: South HOF Location: Main Building Trade: Steel Start Date: 03-Jul-2025 End Date: 03-Jul-2025
Note on VT131: Activity Name: Added Roof Steel Phase: South HOF Location: Main Building Trade: Steel Start Date: 07-Jul-2025 End Date: 09-Jul-2025
Note on VW131: Activity Name: Repair Roofing System Phase: South HOF Location: Main Building Trade: Roofing Start Date: 10-Jul-2025 End Date: 11-Jul-2025
Note on WX131: Activity Name: Install Generator Phase: South HOF Location: Main Building Trade: Electrical Start Date: 06-Aug-2025 End Date: 12-Aug-2025
Note on XE131: Activity Name: Generator Start-up & Commissioning Phase: South HOF Location: Main Building Trade: Electrical Start Date: 13-Aug-2025 End Date: 19-Aug-2025
Note on ACO131: Activity Name: Install New Bowl Speakers Phase: South HOF Location: Main Building Trade: Audovisual Start Date: 31-Dec-2025 End Date: 15-Jan-2026
Note on XL135: Activity Name: Relocate HOF transformer Phase: South HOF Location: South Trade: Electrical Start Date: 20-Aug-2025 End Date: 02-Sep-2025
Note on WW136: Activity Name: Concession Building Steel(Steel/Joist/Deck) - North Phase: STRUCTURE Location: Concession Wings Trade: Steel Start Date: 05-Aug-2025 End Date: 18-Aug-2025
Note on XK137: Activity Name: Concession Building Steel(Steel/Joist/Deck) - South Phase: STRUCTURE Location: Concession Wings Trade: Steel Start Date: 19-Aug-2025 End Date: 01-Sep-2025
Note on VP138: Activity Name: Erect Structural Steel Phase: STRUCTURE Location: Main building - All Trade: Steel Start Date: 03-Jul-2025 End Date: 09-Jul-2025
Note on WA138: Activity Name: Detailing & Decking Steel Phase: STRUCTURE Location: Main building - All Trade: Decking Start Date: 14-Jul-2025 End Date: 17-Jul-2025
Note on VV140: Activity Name: Erect Structural Steel Phase: STRUCTURE Location: Main building - All Trade: Steel Start Date: 09-Jul-2025 End Date: 16-Jul-2025
Note on WE140: Activity Name: Detailing & Decking Steel Phase: STRUCTURE Location: Main building - All Trade: Decking Start Date: 18-Jul-2025 End Date: 25-Jul-2025
Note on WC142: Activity Name: Erect Structural Steel Phase: STRUCTURE Location: Main building - All Trade: Steel Start Date: 16-Jul-2025 End Date: 23-Jul-2025
Note on WO142: Activity Name: Detailing & Decking Steel Phase: STRUCTURE Location: Main building - All Trade: Decking Start Date: 28-Jul-2025 End Date: 04-Aug-2025
Note on WJ144: Activity Name: Erect Structural Steel Phase: STRUCTURE Location: Main building - All Trade: Steel Start Date: 23-Jul-2025 End Date: 30-Jul-2025
Note on WW144: Activity Name: Detailing & Decking Steel Phase: STRUCTURE Location: Main building - All Trade: Decking Start Date: 05-Aug-2025 End Date: 12-Aug-2025
Note on WQ146: Activity Name: Erect Structural Steel Phase: STRUCTURE Location: Main building - All Trade: Steel Start Date: 30-Jul-2025 End Date: 04-Aug-2025
Note on XE146: Activity Name: Detailing & Decking Steel Phase: STRUCTURE Location: Main building - All Trade: Decking Start Date: 13-Aug-2025 End Date: 18-Aug-2025
Note on WH148: Activity Name: MEP In-slab Rough-in Phase: STRUCTURE Location: Main building - Lower Suite Level Trade: MEP Start Date: 21-Jul-2025 End Date: 25-Jul-2025
Note on WO148: Activity Name: FRP SOMD Phase: STRUCTURE Location: Main building - Lower Suite Level Trade: Concrete Start Date: 28-Jul-2025 End Date: 01-Aug-2025
Note on WO150: Activity Name: MEP In-slab Rough-in Phase: STRUCTURE Location: Main building - Lower Suite Level Trade: MEP Start Date: 28-Jul-2025 End Date: 01-Aug-2025
Note on WV150: Activity Name: FRP SOMD Phase: STRUCTURE Location: Main building - Lower Suite Level Trade: Concrete Start Date: 04-Aug-2025 End Date: 08-Aug-2025
Note on WW152: Activity Name: MEP In-slab Rough-in Phase: STRUCTURE Location: Main building - Lower Suite Level Trade: MEP Start Date: 05-Aug-2025 End Date: 11-Aug-2025
Note on XD152: Activity Name: FRP SOMD Phase: STRUCTURE Location: Main building - Lower Suite Level Trade: Concrete Start Date: 12-Aug-2025 End Date: 19-Aug-2025
Note on XE154: Activity Name: MEP In-slab Rough-in Phase: STRUCTURE Location: Main building - Lower Suite Level Trade: MEP Start Date: 13-Aug-2025 End Date: 19-Aug-2025
Note on XL154: Activity Name: FRP SOMD Phase: STRUCTURE Location: Main building - Lower Suite Level Trade: Concrete Start Date: 20-Aug-2025 End Date: 27-Aug-2025
Note on XL156: Activity Name: MEP In-slab Rough-in Phase: STRUCTURE Location: Main building - Lower Suite Level Trade: MEP Start Date: 20-Aug-2025 End Date: 26-Aug-2025
Note on XT156: Activity Name: FRP SOMD Phase: STRUCTURE Location: Main building - Lower Suite Level Trade: Concrete Start Date: 28-Aug-2025 End Date: 03-Sep-2025
Note on WY158: Activity Name: Erect Canopy Steel Phase: STRUCTURE Location: Main building - Roof Level Trade: Steel Start Date: 07-Aug-2025 End Date: 18-Aug-2025
Note on XK159: Activity Name: Erect Canopy Steel Phase: STRUCTURE Location: Main building - Roof Level Trade: Steel Start Date: 19-Aug-2025 End Date: 28-Aug-2025
Note on WW160: Activity Name: MEP In-slab Rough-in Phase: STRUCTURE Location: Main building - Roof Level Trade: MEP Start Date: 05-Aug-2025 End Date: 11-Aug-2025
Note on XU160: Activity Name: Erect Canopy Steel Phase: STRUCTURE Location: Main building - Roof Level Trade: Steel Start Date: 29-Aug-2025 End Date: 10-Sep-2025
Note on YH162: Activity Name: Erect Canopy Steel Phase: STRUCTURE Location: Main building - Roof Level Trade: Steel Start Date: 11-Sep-2025 End Date: 22-Sep-2025
Note on YT163: Activity Name: Erect Canopy Steel Phase: STRUCTURE Location: Main building - Roof Level Trade: Steel Start Date: 23-Sep-2025 End Date: 02-Oct-2025
Note on XY164: Activity Name: Erect NE Concourse Structure Phase: STRUCTURE Location: Northeast Trade: Steel Start Date: 02-Sep-2025 End Date: 04-Sep-2025
Note on YB164: Activity Name: Detail/Misc Steel- NE Phase: STRUCTURE Location: Northeast Trade: Steel Start Date: 05-Sep-2025 End Date: 16-Sep-2025
Note on XK166: Activity Name: Exterior Framing and Sheathing - North Phase: EXTERIORS Location: Concession Wings - Concourse Level Trade: Framing Start Date: 19-Aug-2025 End Date: 01-Sep-2025
Note on XY166: Activity Name: Install Air/Water Barrier Phase: EXTERIORS Location: Concession Wings - Concourse Level Trade: Waterproofing Start Date: 02-Sep-2025 End Date: 05-Sep-2025
Note on YF166: Activity Name: Install Masonry Veneer Phase: EXTERIORS Location: Concession Wings - Concourse Level Trade: Masonry Start Date: 09-Sep-2025 End Date: 28-Oct-2025
Note on AAE166: Activity Name: Install Metal Panel Fascias & Soffits Phase: EXTERIORS Location: Concession Wings - Concourse Level Trade: Metal Panels Start Date: 30-Oct-2025 End Date: 19-Nov-2025
Note on AAZ166: Activity Name: Install Linear Soffit Lights Phase: EXTERIORS Location: Concession Wings - Concourse Level Trade: Electrical Start Date: 20-Nov-2025 End Date: 26-Nov-2025
Note on XY170: Activity Name: Exterior Framing and Sheathing - South Phase: EXTERIORS Location: Concession Wings - Concourse Level Trade: Framing Start Date: 02-Sep-2025 End Date: 16-Sep-2025
Note on YN170: Activity Name: Install Air/Water Barrier Phase: EXTERIORS Location: Concession Wings - Concourse Level Trade: Waterproofing Start Date: 17-Sep-2025 End Date: 19-Sep-2025
Note on YS170: Activity Name: Install Masonry Veneer Phase: EXTERIORS Location: Concession Wings - Concourse Level Trade: Masonry Start Date: 22-Sep-2025 End Date: 21-Oct-2025
Note on ZW170: Activity Name: Install Storefront System Phase: EXTERIORS Location: Concession Wings - Concourse Level Trade: Glazing Start Date: 22-Oct-2025 End Date: 04-Nov-2025
Note on ABK170: Activity Name: Install Metal Panel Fascias & Soffits Phase: EXTERIORS Location: Concession Wings - Concourse Level Trade: Metal Panels Start Date: 01-Dec-2025 End Date: 19-Dec-2025
Note on ACF170: Activity Name: Install Linear Soffit Lights Phase: EXTERIORS Location: Concession Wings - Concourse Level Trade: Electrical Start Date: 22-Dec-2025 End Date: 29-Dec-2025
Note on XC174: Activity Name: Exterior Framing and Sheathing - North Phase: EXTERIORS Location: Concourse Level Trade: Framing Start Date: 11-Aug-2025 End Date: 22-Aug-2025
Note on XQ174: Activity Name: Install Stainless Counters Phase: EXTERIORS Location: Concourse Level Trade: Specialty Start Date: 25-Aug-2025 End Date: 26-Aug-2025
Note on XT174: Activity Name: Install Masonry Veneer Phase: EXTERIORS Location: Concourse Level Trade: Masonry Start Date: 28-Aug-2025 End Date: 02-Oct-2025
Note on ZD174: Activity Name: Install Storefront (Bowl side) Phase: EXTERIORS Location: Concourse Level Trade: Glazing Start Date: 03-Oct-2025 End Date: 09-Oct-2025
Note on ZK174: Activity Name: Install Curtainwall Phase: EXTERIORS Location: Concourse Level Trade: Glazing Start Date: 10-Oct-2025 End Date: 23-Oct-2025
Note on ZY174: Activity Name: Install Fire Sprinkler Phase: EXTERIORS Location: Concourse Level Trade: Fire Sprinkler Start Date: 24-Oct-2025 End Date: 30-Oct-2025
Note on AAM174: Activity Name: Spray Insulation Phase: EXTERIORS Location: Concourse Level Trade: Insulation Start Date: 07-Nov-2025 End Date: 18-Nov-2025
Note on AAY174: Activity Name: Close Soffit Phase: EXTERIORS Location: Concourse Level Trade: Carpentry Start Date: 19-Nov-2025 End Date: 25-Nov-2025
Note on ACO174: Activity Name: Install Soffit Metal Panels Phase: EXTERIORS Location: Concourse Level Trade: Metal Panels Start Date: 31-Dec-2025 End Date: 29-Jan-2026
Note on ADS174: Activity Name: Trim-out Devices Phase: EXTERIORS Location: Concourse Level Trade: Electrical Start Date: 30-Jan-2026 End Date: 05-Feb-2026
Note on XQ175: Activity Name: Install Air/Water Barrier Phase: EXTERIORS Location: Concourse Level Trade: Waterproofing Start Date: 25-Aug-2025 End Date: 27-Aug-2025
Note on ZK175: Activity Name: Frame Soffit Phase: EXTERIORS Location: Concourse Level Trade: Carpentry Start Date: 10-Oct-2025 End Date: 23-Oct-2025
Note on ZY175: Activity Name: Install Electrical/LV Phase: EXTERIORS Location: Concourse Level Trade: Electrical Start Date: 24-Oct-2025 End Date: 06-Nov-2025
Note on YA179: Activity Name: Exterior Framing and Sheathing - South Phase: EXTERIORS Location: Concourse Level Trade: Framing Start Date: 04-Sep-2025 End Date: 18-Sep-2025
Note on YP179: Activity Name: Install Stainless Counters Phase: EXTERIORS Location: Concourse Level Trade: Specialty Start Date: 19-Sep-2025 End Date: 22-Sep-2025
Note on YU179: Activity Name: Install Masonry Veneer Phase: EXTERIORS Location: Concourse Level Trade: Masonry Start Date: 24-Sep-2025 End Date: 28-Oct-2025
Note on AAM179: Activity Name: Install Storefront (Bowl side) Phase: EXTERIORS Location: Concourse Level Trade: Glazing Start Date: 07-Nov-2025 End Date: 13-Nov-2025
Note on AAT179: Activity Name: Frame Soffit Phase: EXTERIORS Location: Concourse Level Trade: Carpentry Start Date: 14-Nov-2025 End Date: 01-Dec-2025
Note on ABL179: Activity Name: Install Fire Sprinkler Phase: EXTERIORS Location: Concourse Level Trade: Fire Sprinkler Start Date: 02-Dec-2025 End Date: 08-Dec-2025
Note on ABZ179: Activity Name: Spray Insulation Phase: EXTERIORS Location: Concourse Level Trade: Insulation Start Date: 16-Dec-2025 End Date: 26-Dec-2025
Note on ACM179: Activity Name: Close Soffit Phase: EXTERIORS Location: Concourse Level Trade: Carpentry Start Date: 29-Dec-2025 End Date: 05-Jan-2026
Note on ADX179: Activity Name: Install Soffit Metal Panels Phase: EXTERIORS Location: Concourse Level Trade: Metal Panels Start Date: 04-Feb-2026 End Date: 03-Mar-2026
Note on AEZ179: Activity Name: Trim-out Devices Phase: EXTERIORS Location: Concourse Level Trade: Electrical Start Date: 04-Mar-2026 End Date: 10-Mar-2026
Note on YP180: Activity Name: Install Air/Water Barrier Phase: EXTERIORS Location: Concourse Level Trade: Waterproofing Start Date: 19-Sep-2025 End Date: 23-Sep-2025
Note on ZY180: Activity Name: Install Curtainwall Phase: EXTERIORS Location: Concourse Level Trade: Glazing Start Date: 24-Oct-2025 End Date: 06-Nov-2025
Note on ABL180: Activity Name: Install Electrical/LV Phase: EXTERIORS Location: Concourse Level Trade: Electrical Start Date: 02-Dec-2025 End Date: 15-Dec-2025
Note on ACF183: Activity Name: Install Entry Main Canopy Phase: EXTERIORS Location: Entry Trade: Steel Start Date: 22-Dec-2025 End Date: 21-Jan-2026
Note on ADK183: Activity Name: Install Secondary Entry Canopy Phase: EXTERIORS Location: Entry Trade: Steel Start Date: 22-Jan-2026 End Date: 04-Feb-2026
Note on ADY183: Activity Name: Install Entry Gates Phase: EXTERIORS Location: Entry Trade: Miscellaneous Start Date: 05-Feb-2026 End Date: 18-Feb-2026
Note on AEM183: Activity Name: Install Entry Gates Phase: EXTERIORS Location: Entry Trade: Miscellaneous Start Date: 19-Feb-2026 End Date: 25-Feb-2026
Note on AET183: Activity Name: Install Entry Signage Phase: EXTERIORS Location: Entry Trade: Signage Start Date: 26-Feb-2026 End Date: 04-Mar-2026
Note on XA187: Activity Name: Concrete Cure Time Phase: EXTERIORS Location: Lower Suite Level Trade: Concrete Start Date: 09-Aug-2025 End Date: 05-Sep-2025
Note on YH187: Activity Name: Install Roofing Membrane Phase: EXTERIORS Location: Lower Suite Level Trade: Roofing Start Date: 11-Sep-2025 End Date: 24-Sep-2025
Note on ZC187: Activity Name: Install Metal Panels Phase: EXTERIORS Location: Lower Suite Level Trade: Metal Panels Start Date: 02-Oct-2025 End Date: 29-Oct-2025
Note on XC188: Activity Name: Install Roof Curbs/Rails Phase: EXTERIORS Location: Lower Suite Level Trade: Roofing Start Date: 11-Aug-2025 End Date: 11-Aug-2025
Note on XL188: Activity Name: Exterior Framing and Sheathing - North Phase: EXTERIORS Location: Lower Suite Level Trade: Framing Start Date: 20-Aug-2025 End Date: 02-Sep-2025
Note on XZ188: Activity Name: Install Air/Water Barrier Phase: EXTERIORS Location: Lower Suite Level Trade: Waterproofing Start Date: 03-Sep-2025 End Date: 10-Sep-2025
Note on ZX188: Activity Name: Install Mechanical Equipment Phase: EXTERIORS Location: Lower Suite Level Trade: Mechanical Start Date: 23-Oct-2025 End Date: 05-Nov-2025
Note on YA191: Activity Name: Install Roof Curbs/Rails Phase: EXTERIORS Location: Lower Suite Level Trade: Roofing Start Date: 04-Sep-2025 End Date: 04-Sep-2025
Note on YO191: Activity Name: Exterior Framing and Sheathing - South Phase: EXTERIORS Location: Lower Suite Level Trade: Framing Start Date: 18-Sep-2025 End Date: 01-Oct-2025
Note on ZC191: Activity Name: Install Air/Water Barrier Phase: EXTERIORS Location: Lower Suite Level Trade: Waterproofing Start Date: 02-Oct-2025 End Date: 08-Oct-2025
Note on AAE191: Activity Name: Install Metal Panels Phase: EXTERIORS Location: Lower Suite Level Trade: Metal Panels Start Date: 30-Oct-2025 End Date: 26-Nov-2025
Note on YA192: Activity Name: Concrete Cure Time Phase: EXTERIORS Location: Lower Suite Level Trade: Concrete Start Date: 04-Sep-2025 End Date: 01-Oct-2025
Note on ZC192: Activity Name: Install Roofing Membrane Phase: EXTERIORS Location: Lower Suite Level Trade: Roofing Start Date: 02-Oct-2025 End Date: 15-Oct-2025
Note on AAL192: Activity Name: Install Mechanical Equipment Phase: EXTERIORS Location: Lower Suite Level Trade: Mechanical Start Date: 06-Nov-2025 End Date: 12-Nov-2025
Note on AFG195: Activity Name: MCC Completion List - Prepare/Distribute/Complete Phase: EXTERIORS Location: Main building Trade: Manhattan Start Date: 11-Mar-2026 End Date: 24-Mar-2026
Note on AFU195: Activity Name: Design Team Punchlist - Prepare/Distribute/Complete Phase: EXTERIORS Location: Main building Trade: Manhattan Start Date: 25-Mar-2026 End Date: 07-Apr-2026
Note on ZD197: Activity Name: Exterior Framing and Sheathing - Northeast Phase: EXTERIORS Location: Northeast - Concourse Level Trade: Framing Start Date: 03-Oct-2025 End Date: 16-Oct-2025
Note on ZR197: Activity Name: Install SS Serving Counters Phase: EXTERIORS Location: Northeast - Concourse Level Trade: Specialty Start Date: 17-Oct-2025 End Date: 20-Oct-2025
Note on ZY197: Activity Name: Install Masonry Veneer Phase: EXTERIORS Location: Northeast - Concourse Level Trade: Masonry Start Date: 24-Oct-2025 End Date: 01-Dec-2025
Note on ADS197: Activity Name: Install Metal Panel Fascia Phase: EXTERIORS Location: Northeast - Concourse Level Trade: Metal Panels Start Date: 30-Jan-2026 End Date: 12-Feb-2026
Note on ZR198: Activity Name: Install Air/Water Barrier Phase: EXTERIORS Location: Northeast - Concourse Level Trade: Waterproofing Start Date: 17-Oct-2025 End Date: 23-Oct-2025
Note on YN202: Activity Name: Install Roof Curbs/Rails Phase: EXTERIORS Location: Northeast - Roof Level Trade: Roofing Start Date: 17-Sep-2025 End Date: 18-Sep-2025
Note on ZX202: Activity Name: Install Roofing Membrane Phase: EXTERIORS Location: Northeast - Roof Level Trade: Roofing Start Date: 23-Oct-2025 End Date: 29-Oct-2025
Note on AAS202: Activity Name: Install Mechanical Equipment Phase: EXTERIORS Location: Northeast - Roof Level Trade: Mechanical Start Date: 13-Nov-2025 End Date: 19-Nov-2025
Note on XK205: Activity Name: Install Roof Curbs/Rails Phase: EXTERIORS Location: Roof Level Trade: Roofing Start Date: 19-Aug-2025 End Date: 20-Aug-2025
Note on XY205: Activity Name: Install Roofing Membrane Phase: EXTERIORS Location: Roof Level Trade: Roofing Start Date: 02-Sep-2025 End Date: 09-Sep-2025
Note on YG205: Activity Name: Install Mechanical Equipment Phase: EXTERIORS Location: Roof Level Trade: Mechanical Start Date: 10-Sep-2025 End Date: 30-Sep-2025
Note on ZQ208: Activity Name: Install Roofing Membrane Phase: EXTERIORS Location: Roof Level Trade: Roofing Start Date: 16-Oct-2025 End Date: 22-Oct-2025
Note on XY209: Activity Name: Install Roof Curbs/Rails Phase: EXTERIORS Location: Roof Level Trade: Roofing Start Date: 02-Sep-2025 End Date: 03-Sep-2025
Note on YV209: Activity Name: Install Roofing Membrane Phase: EXTERIORS Location: Roof Level Trade: Roofing Start Date: 25-Sep-2025 End Date: 01-Oct-2025
Note on ZC209: Activity Name: Install Mechanical Equipment Phase: EXTERIORS Location: Roof Level Trade: Mechanical Start Date: 02-Oct-2025 End Date: 22-Oct-2025
Note on SG212: Activity Name: Site Utilities Phase: CIVIL/SITE Location: East Trade: Underground Utilities Start Date: 07-Apr-2025 End Date: 16-Jun-2025
Note on UZ212: Activity Name: Install Fire Lane Base Course Phase: CIVIL/SITE Location: East Trade: Paving Start Date: 17-Jun-2025 End Date: 15-Jul-2025
Note on AAZ212: Activity Name: Hardscape/Landscape Phase: CIVIL/SITE Location: East Trade: Hardscape/Landscape Start Date: 20-Nov-2025 End Date: 11-Mar-2026
Note on TW213: Activity Name: Relocate Existing CoServ Lines Phase: CIVIL/SITE Location: East Trade: Underground Utilities Start Date: 19-May-2025 End Date: 16-Jun-2025
Note on ZD216: Activity Name: Install Bowl Speakers/Stadium Lights Phase: CANOPIES Location: Main building Trade: Electrical Start Date: 03-Oct-2025 End Date: 30-Dec-2025
Note on AGU216: Activity Name: Install Canopy Fabric Phase: CANOPIES Location: Main building Trade: Steel Start Date: 20-Apr-2026 End Date: 29-Jun-2026
Note on AJN216: Activity Name: Canopy Punch/Closeout Phase: CANOPIES Location: Main building Trade: Steel Start Date: 30-Jun-2026 End Date: 28-Jul-2026
Note on AGI219: Activity Name: Closeout/Commissioning Phase: INTERIORS Location: Closeout/Commissioning Trade: MEP Start Date: 08-Apr-2026 End Date: 30-Jun-2026
Note on XY220: Activity Name: Partition Layout & Top Track Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 02-Sep-2025 End Date: 03-Sep-2025
Note on YA220: Activity Name: Mechanical Overhead & Riser Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 04-Sep-2025 End Date: 05-Sep-2025
Note on YF220: Activity Name: Plumbing/Piping Overhead Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 09-Sep-2025 End Date: 10-Sep-2025
Note on YH220: Activity Name: Frame & One-side Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 11-Sep-2025 End Date: 15-Sep-2025
Note on YM220: Activity Name: Elect/LV Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 16-Sep-2025 End Date: 22-Sep-2025
Note on YT220: Activity Name: In-Wall QC Check Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 23-Sep-2025 End Date: 23-Sep-2025
Note on YU220: Activity Name: COF In-Wall Inspection Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 24-Sep-2025 End Date: 24-Sep-2025
Note on YV220: Activity Name: Insulate & Close Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 25-Sep-2025 End Date: 29-Sep-2025
Note on ZA220: Activity Name: Tape/Bed/Prime/ 1st Coat Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 30-Sep-2025 End Date: 08-Oct-2025
Note on ZJ220: Activity Name: Trim Mechanical Devices Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 09-Oct-2025 End Date: 09-Oct-2025
Note on ZO220: Activity Name: Seal MEP/Storage Rooms Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 14-Oct-2025 End Date: 14-Oct-2025
Note on ZP220: Activity Name: Install Doors & Hardware Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Equipment Start Date: 15-Oct-2025 End Date: 16-Oct-2025
Note on ZR220: Activity Name: LV Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 17-Oct-2025 End Date: 20-Oct-2025
Note on AAT220: Activity Name: Construction Rough Clean Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Clean Start Date: 14-Nov-2025 End Date: 20-Nov-2025
Note on ABA220: Activity Name: MCC Completion List - Prepare/Distribute/Complete Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Manhattan Start Date: 21-Nov-2025 End Date: 08-Dec-2025
Note on ABS220: Activity Name: Design Team Punch List & Completion Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Manhattan Start Date: 09-Dec-2025 End Date: 22-Dec-2025
Note on ACG220: Activity Name: Final Clean Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Clean Start Date: 23-Dec-2025 End Date: 24-Dec-2025
Note on YF221: Activity Name: Fire Protection Overhead Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Fire Sprinkler Start Date: 09-Sep-2025 End Date: 10-Sep-2025
Note on ZJ221: Activity Name: Install Light Fixtures Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 09-Oct-2025 End Date: 10-Oct-2025
Note on ZR221: Activity Name: Build-out Elecrtical Room Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 17-Oct-2025 End Date: 13-Nov-2025
Note on ZJ222: Activity Name: FRP Equipment Pads Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Concrete Start Date: 09-Oct-2025 End Date: 13-Oct-2025
Note on ZJ223: Activity Name: Electrical/FA Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 09-Oct-2025 End Date: 15-Oct-2025
Note on YZ225: Activity Name: Partition Layout & Top Track Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 29-Sep-2025 End Date: 30-Sep-2025
Note on ZB225: Activity Name: Mechanical Overhead & Riser Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 01-Oct-2025 End Date: 02-Oct-2025
Note on ZI225: Activity Name: Plumbing/Piping Overhead Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 08-Oct-2025 End Date: 14-Oct-2025
Note on ZV225: Activity Name: Plumbing In-wall Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 21-Oct-2025 End Date: 27-Oct-2025
Note on AAD225: Activity Name: In-Wall QC Check Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 29-Oct-2025 End Date: 29-Oct-2025
Note on AAE225: Activity Name: COF In-Wall Inspection Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 30-Oct-2025 End Date: 30-Oct-2025
Note on AAF225: Activity Name: Insulate & Close Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 31-Oct-2025 End Date: 06-Nov-2025
Note on AAM225: Activity Name: Tape/Bed/Prime/ 1st Coat Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 07-Nov-2025 End Date: 17-Nov-2025
Note on AAX225: Activity Name: Frame Hard Ceilings/Soffits Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 18-Nov-2025 End Date: 18-Nov-2025
Note on AAZ225: Activity Name: Install Walk-in Cooler/Freezer Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Refrigeration Start Date: 20-Nov-2025 End Date: 24-Nov-2025
Note on ABF225: Activity Name: Install ACT Grid Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Ceiling Start Date: 26-Nov-2025 End Date: 02-Dec-2025
Note on ABM225: Activity Name: Install Mechanical Devices Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 03-Dec-2025 End Date: 03-Dec-2025
Note on ABN225: Activity Name: Drop Sprinkler Heads Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Fire Sprinkler Start Date: 04-Dec-2025 End Date: 04-Dec-2025
Note on ABV225: Activity Name: Install Light Fixtures Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 12-Dec-2025 End Date: 16-Dec-2025
Note on ACA225: Activity Name: Overhead QC Inspection Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 17-Dec-2025 End Date: 17-Dec-2025
Note on ACB225: Activity Name: COF Overhead Inspections Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 18-Dec-2025 End Date: 18-Dec-2025
Note on ACC225: Activity Name: Close Hard Ceilings/Soffits Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 19-Dec-2025 End Date: 19-Dec-2025
Note on ACF225: Activity Name: Tape/Bed/Paint Ceilings Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 22-Dec-2025 End Date: 24-Dec-2025
Note on ACJ225: Activity Name: Final Paint Storage Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Paint Start Date: 26-Dec-2025 End Date: 30-Dec-2025
Note on ACQ225: Activity Name: Seal Storage Room Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 02-Jan-2026 End Date: 02-Jan-2026
Note on ACT225: Activity Name: Install Concession Wall Finish Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Specialty Start Date: 05-Jan-2026 End Date: 19-Jan-2026
Note on ADI225: Activity Name: Install Mechanical Wall Units/Air Curtains Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 20-Jan-2026 End Date: 20-Jan-2026
Note on ADP225: Activity Name: Install Doors & Hardware Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Equipment Start Date: 27-Jan-2026 End Date: 28-Jan-2026
Note on ADV225: Activity Name: Kitchen Hood Testing Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 02-Feb-2026 End Date: 02-Feb-2026
Note on ADW225: Activity Name: LV Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 03-Feb-2026 End Date: 04-Feb-2026
Note on ADY225: Activity Name: Install ACT Tile Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Ceiling Start Date: 05-Feb-2026 End Date: 06-Feb-2026
Note on AED225: Activity Name: Construction Rough Clean Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Clean Start Date: 10-Feb-2026 End Date: 12-Feb-2026
Note on AEG225: Activity Name: MCC Completion List - Prepare/Distribute/Complete Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Manhattan Start Date: 13-Feb-2026 End Date: 26-Feb-2026
Note on AEU225: Activity Name: Design Team Punch List & Completion Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Manhattan Start Date: 27-Feb-2026 End Date: 12-Mar-2026
Note on AFI225: Activity Name: Final Clean Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Clean Start Date: 13-Mar-2026 End Date: 16-Mar-2026
Note on ZC226: Activity Name: Fire Protection Overhead Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Fire Sprinkler Start Date: 02-Oct-2025 End Date: 06-Oct-2025
Note on ZN226: Activity Name: Frame & One-side Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 13-Oct-2025 End Date: 17-Oct-2025
Note on ZW226: Activity Name: Elect/LV Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 22-Oct-2025 End Date: 28-Oct-2025
Note on AAX226: Activity Name: Install Kitchen Hoods Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 18-Nov-2025 End Date: 19-Nov-2025
Note on AAZ226: Activity Name: Grease Duct Tie-in/Insulate Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 20-Nov-2025 End Date: 25-Nov-2025
Note on ABM226: Activity Name: Install FA/LV Pathway Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 03-Dec-2025 End Date: 05-Dec-2025
Note on ACJ226: Activity Name: Install Epoxy Flooring/Base Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Flooring Start Date: 26-Dec-2025 End Date: 02-Jan-2026
Note on ADI226: Activity Name: Install Food Service Equipment Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Equipment Start Date: 20-Jan-2026 End Date: 26-Jan-2026
Note on ADP226: Activity Name: Plumbing Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 27-Jan-2026 End Date: 29-Jan-2026
Note on ADQ227: Activity Name: Electrical/FA Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 28-Jan-2026 End Date: 30-Jan-2026
Note on YU229: Activity Name: Partition Layout & Top Track Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 24-Sep-2025 End Date: 26-Sep-2025
Note on YZ229: Activity Name: Mechanical Overhead & Riser Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 29-Sep-2025 End Date: 30-Sep-2025
Note on ZB229: Activity Name: Plumbing/Piping Overhead Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 01-Oct-2025 End Date: 07-Oct-2025
Note on ZO229: Activity Name: Plumbing In-wall Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 14-Oct-2025 End Date: 20-Oct-2025
Note on ZV229: Activity Name: In-Wall QC Check Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 21-Oct-2025 End Date: 21-Oct-2025
Note on ZW229: Activity Name: COF In-Wall Inspection Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 22-Oct-2025 End Date: 22-Oct-2025
Note on ZX229: Activity Name: Insulate & Close Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 23-Oct-2025 End Date: 27-Oct-2025
Note on AAC229: Activity Name: Tape/Bed/Prime/ 1st Coat Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 28-Oct-2025 End Date: 03-Nov-2025
Note on AAJ229: Activity Name: Install ACT Grid Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Ceiling Start Date: 04-Nov-2025 End Date: 06-Nov-2025
Note on AAM229: Activity Name: Install Mechanical Devices Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 07-Nov-2025 End Date: 07-Nov-2025
Note on AAP229: Activity Name: Drop Sprinkler Heads Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Fire Sprinkler Start Date: 10-Nov-2025 End Date: 10-Nov-2025
Note on AAT229: Activity Name: Install Light Fixtures Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 14-Nov-2025 End Date: 18-Nov-2025
Note on AAY229: Activity Name: Overhead QC Inspection Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 19-Nov-2025 End Date: 19-Nov-2025
Note on AAZ229: Activity Name: COF Overhead Inspections Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 20-Nov-2025 End Date: 20-Nov-2025
Note on ABA229: Activity Name: Close Hard Ceilings/Soffits Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 21-Nov-2025 End Date: 21-Nov-2025
Note on ABD229: Activity Name: Tape/Bed/Paint Ceilings Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 24-Nov-2025 End Date: 26-Nov-2025
Note on ABK229: Activity Name: Install Epoxy Flooring/Base Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Flooring Start Date: 01-Dec-2025 End Date: 05-Dec-2025
Note on ABR229: Activity Name: Install Restroom Wall Tile & Base Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Tile Start Date: 08-Dec-2025 End Date: 19-Dec-2025
Note on ACF229: Activity Name: Install Plumbing Fixtures Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 22-Dec-2025 End Date: 29-Dec-2025
Note on ACN229: Activity Name: Plumbing Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 30-Dec-2025 End Date: 31-Dec-2025
Note on ACQ229: Activity Name: Install Toilet Partitions Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Specialty Start Date: 02-Jan-2026 End Date: 16-Jan-2026
Note on ADH229: Activity Name: Install Toilet Accessories Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Specialty Start Date: 19-Jan-2026 End Date: 19-Jan-2026
Note on ADL229: Activity Name: Electrical/FA Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 23-Jan-2026 End Date: 27-Jan-2026
Note on ADQ229: Activity Name: LV Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 28-Jan-2026 End Date: 29-Jan-2026
Note on ADS229: Activity Name: Install ACT Tile Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Ceiling Start Date: 30-Jan-2026 End Date: 02-Feb-2026
Note on ADW229: Activity Name: Construction Rough Clean Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Clean Start Date: 03-Feb-2026 End Date: 09-Feb-2026
Note on AED229: Activity Name: MCC Completion List - Prepare/Distribute/Complete Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Manhattan Start Date: 10-Feb-2026 End Date: 23-Feb-2026
Note on AER229: Activity Name: Design Team Punch List & Completion Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Manhattan Start Date: 24-Feb-2026 End Date: 09-Mar-2026
Note on AFF229: Activity Name: Final Clean Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Clean Start Date: 10-Mar-2026 End Date: 11-Mar-2026
Note on YZ230: Activity Name: Fire Protection Overhead Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Fire Sprinkler Start Date: 29-Sep-2025 End Date: 01-Oct-2025
Note on ZG230: Activity Name: Frame & One-side Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 06-Oct-2025 End Date: 10-Oct-2025
Note on ZO230: Activity Name: Elect/LV Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 14-Oct-2025 End Date: 20-Oct-2025
Note on AAL230: Activity Name: Frame Hard Ceilings/Soffits Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 06-Nov-2025 End Date: 06-Nov-2025
Note on AAM230: Activity Name: Install FA/LV Pathway Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 07-Nov-2025 End Date: 10-Nov-2025
Note on ADH230: Activity Name: Install Doors & Hardware Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Equipment Start Date: 19-Jan-2026 End Date: 20-Jan-2026
Note on ZG233: Activity Name: Partition Layout & Top Track Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 06-Oct-2025 End Date: 07-Oct-2025
Note on ZI233: Activity Name: Mechanical Overhead & Riser Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 08-Oct-2025 End Date: 09-Oct-2025
Note on ZK233: Activity Name: Fire Protection Overhead Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Fire Sprinkler Start Date: 10-Oct-2025 End Date: 14-Oct-2025
Note on ZW233: Activity Name: Plumbing/Piping Overhead Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 22-Oct-2025 End Date: 28-Oct-2025
Note on AAD233: Activity Name: Frame & One-side Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 29-Oct-2025 End Date: 30-Oct-2025
Note on AAK233: Activity Name: Plumbing In-wall Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 05-Nov-2025 End Date: 11-Nov-2025
Note on AAR233: Activity Name: In-Wall QC Check Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 12-Nov-2025 End Date: 12-Nov-2025
Note on AAS233: Activity Name: COF In-Wall Inspection Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 13-Nov-2025 End Date: 13-Nov-2025
Note on AAT233: Activity Name: Insulate & Close Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 14-Nov-2025 End Date: 18-Nov-2025
Note on AAY233: Activity Name: Tape/Bed/Prime/ 1st Coat Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 19-Nov-2025 End Date: 01-Dec-2025
Note on ABM233: Activity Name: Install Kitchen Hoods Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 03-Dec-2025 End Date: 04-Dec-2025
Note on ABO233: Activity Name: Grease Duct Tie-in/Insulate Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 05-Dec-2025 End Date: 10-Dec-2025
Note on ABU233: Activity Name: Install ACT Grid Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Ceiling Start Date: 11-Dec-2025 End Date: 12-Dec-2025
Note on ABZ233: Activity Name: Install FA/LV Pathway Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 16-Dec-2025 End Date: 18-Dec-2025
Note on ACC233: Activity Name: Drop Sprinkler Heads Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Fire Sprinkler Start Date: 19-Dec-2025 End Date: 19-Dec-2025
Note on ACH233: Activity Name: Overhead QC Inspection Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 24-Dec-2025 End Date: 24-Dec-2025
Note on ACJ233: Activity Name: COF Overhead Inspections Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 26-Dec-2025 End Date: 26-Dec-2025
Note on ACT233: Activity Name: Install Epoxy Flooring/Base Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Flooring Start Date: 05-Jan-2026 End Date: 12-Jan-2026
Note on ADX233: Activity Name: Install Concession Wall Finish Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Specialty Start Date: 04-Feb-2026 End Date: 17-Feb-2026
Note on AEL233: Activity Name: Install Mechanical Wall Units/Air Curtains Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 18-Feb-2026 End Date: 20-Feb-2026
Note on AES233: Activity Name: Install Doors & Hardware Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Equipment Start Date: 25-Feb-2026 End Date: 26-Feb-2026
Note on AEX233: Activity Name: LV Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 02-Mar-2026 End Date: 03-Mar-2026
Note on AEZ233: Activity Name: Kitchen Hood Testing Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 04-Mar-2026 End Date: 04-Mar-2026
Note on AFA233: Activity Name: Install ACT Tile Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Ceiling Start Date: 05-Mar-2026 End Date: 06-Mar-2026
Note on AFE233: Activity Name: Construction Rough Clean Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Clean Start Date: 09-Mar-2026 End Date: 13-Mar-2026
Note on AFL233: Activity Name: MCC Completion List - Prepare/Distribute/Complete Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Manhattan Start Date: 16-Mar-2026 End Date: 27-Mar-2026
Note on AFZ233: Activity Name: Design Team Punch List & Completion Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Manhattan Start Date: 30-Mar-2026 End Date: 10-Apr-2026
Note on AGN233: Activity Name: Final Clean Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Clean Start Date: 13-Apr-2026 End Date: 14-Apr-2026
Note on AAK234: Activity Name: Elect/LV Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 05-Nov-2025 End Date: 11-Nov-2025
Note on ACA234: Activity Name: Install Mechanical Devices Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 17-Dec-2025 End Date: 18-Dec-2025
Note on ACC234: Activity Name: Install Light Fixtures Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 19-Dec-2025 End Date: 23-Dec-2025
Note on AEL234: Activity Name: Install Food Service Equipment Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Equipment Start Date: 18-Feb-2026 End Date: 24-Feb-2026
Note on AES234: Activity Name: Plumbing Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 25-Feb-2026 End Date: 27-Feb-2026
Note on AES235: Activity Name: Electrical/FA Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 25-Feb-2026 End Date: 27-Feb-2026
Note on ZB237: Activity Name: Partition Layout & Top Track Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 01-Oct-2025 End Date: 03-Oct-2025
Note on ZG237: Activity Name: Mechanical Overhead & Riser Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 06-Oct-2025 End Date: 07-Oct-2025
Note on ZP237: Activity Name: Plumbing/Piping Overhead Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 15-Oct-2025 End Date: 21-Oct-2025
Note on AAD237: Activity Name: Plumbing In-wall Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 29-Oct-2025 End Date: 04-Nov-2025
Note on AAK237: Activity Name: In-Wall QC Check Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 05-Nov-2025 End Date: 05-Nov-2025
Note on AAL237: Activity Name: COF In-Wall Inspection Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 06-Nov-2025 End Date: 06-Nov-2025
Note on AAM237: Activity Name: Insulate & Close Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 07-Nov-2025 End Date: 11-Nov-2025
Note on AAR237: Activity Name: Tape/Bed/Prime/ 1st Coat Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 12-Nov-2025 End Date: 18-Nov-2025
Note on AAY237: Activity Name: Frame Hard Ceilings/Soffits Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 19-Nov-2025 End Date: 19-Nov-2025
Note on ABE237: Activity Name: Install ACT Grid Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Ceiling Start Date: 25-Nov-2025 End Date: 26-Nov-2025
Note on ABK237: Activity Name: Install Mechanical Devices Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 01-Dec-2025 End Date: 01-Dec-2025
Note on ABL237: Activity Name: Drop Sprinkler Heads Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Fire Sprinkler Start Date: 02-Dec-2025 End Date: 02-Dec-2025
Note on ABS237: Activity Name: Install Light Fixtures Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 09-Dec-2025 End Date: 11-Dec-2025
Note on ACB237: Activity Name: Overhead QC Inspection Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 18-Dec-2025 End Date: 18-Dec-2025
Note on ACC237: Activity Name: COF Overhead Inspections Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 19-Dec-2025 End Date: 19-Dec-2025
Note on ACF237: Activity Name: Close Hard Ceilings/Soffits Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 22-Dec-2025 End Date: 22-Dec-2025
Note on ACG237: Activity Name: Tape/Bed/Paint Ceilings Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 23-Dec-2025 End Date: 30-Dec-2025
Note on ACO237: Activity Name: Seal Janitor Closet Floor Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Flooring Start Date: 31-Dec-2025 End Date: 31-Dec-2025
Note on ADA237: Activity Name: Final Paint Janitor Closet Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Paint Start Date: 12-Jan-2026 End Date: 13-Jan-2026
Note on ADC237: Activity Name: Install Epoxy Flooring/Base Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Flooring Start Date: 14-Jan-2026 End Date: 20-Jan-2026
Note on ADJ237: Activity Name: Install Restroom Wall Tile & Base Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Tile Start Date: 21-Jan-2026 End Date: 03-Feb-2026
Note on ADX237: Activity Name: Plumbing Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 04-Feb-2026 End Date: 05-Feb-2026
Note on AEE237: Activity Name: Install Toilet Partitions Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Specialty Start Date: 11-Feb-2026 End Date: 17-Feb-2026
Note on AEL237: Activity Name: Install Toilet Accessories Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Specialty Start Date: 18-Feb-2026 End Date: 18-Feb-2026
Note on AEM237: Activity Name: Electrical/FA Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 19-Feb-2026 End Date: 23-Feb-2026
Note on AER237: Activity Name: LV Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 24-Feb-2026 End Date: 25-Feb-2026
Note on AET237: Activity Name: Install ACT Tile Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Ceiling Start Date: 26-Feb-2026 End Date: 27-Feb-2026
Note on AEX237: Activity Name: Construction Rough Clean Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Clean Start Date: 02-Mar-2026 End Date: 06-Mar-2026
Note on AFE237: Activity Name: MCC Completion List - Prepare/Distribute/Complete Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Manhattan Start Date: 09-Mar-2026 End Date: 20-Mar-2026
Note on AFS237: Activity Name: Design Team Punch List & Completion Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Manhattan Start Date: 23-Mar-2026 End Date: 03-Apr-2026
Note on AGG237: Activity Name: Final Clean Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Clean Start Date: 06-Apr-2026 End Date: 07-Apr-2026
Note on ZH238: Activity Name: Fire Protection Overhead Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Fire Sprinkler Start Date: 07-Oct-2025 End Date: 09-Oct-2025
Note on ZU238: Activity Name: Frame & One-side Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 20-Oct-2025 End Date: 24-Oct-2025
Note on AAD238: Activity Name: Elect/LV Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 29-Oct-2025 End Date: 04-Nov-2025
Note on ABK238: Activity Name: Install FA/LV Pathway Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 01-Dec-2025 End Date: 02-Dec-2025
Note on ADX238: Activity Name: Install Plumbing Fixtures Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 04-Feb-2026 End Date: 10-Feb-2026
Note on AEL238: Activity Name: Install Doors & Hardware Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Equipment Start Date: 18-Feb-2026 End Date: 19-Feb-2026
Note on ZI241: Activity Name: Partition Layout & Top Track Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 08-Oct-2025 End Date: 08-Oct-2025
Note on ZK241: Activity Name: Mechanical Overhead & Riser Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 10-Oct-2025 End Date: 10-Oct-2025
Note on ZX241: Activity Name: Fire Protection Overhead Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Fire Sprinkler Start Date: 23-Oct-2025 End Date: 24-Oct-2025
Note on AAB241: Activity Name: Plumbing/Piping Overhead Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Plumbing Start Date: 27-Oct-2025 End Date: 31-Oct-2025
Note on AAI241: Activity Name: Frame & One-side Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Framing Start Date: 03-Nov-2025 End Date: 03-Nov-2025
Note on AAR241: Activity Name: Elect/LV Rough-in Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 12-Nov-2025 End Date: 13-Nov-2025
Note on AAT241: Activity Name: In-Wall QC Check Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 14-Nov-2025 End Date: 14-Nov-2025
Note on AAW241: Activity Name: COF In-Wall Inspection Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Inspection Start Date: 17-Nov-2025 End Date: 17-Nov-2025
Note on AAY241: Activity Name: Insulate & Close Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 19-Nov-2025 End Date: 19-Nov-2025
Note on ABA241: Activity Name: Tape/Bed/Prime/ 1st Coat Walls Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Drywall Start Date: 21-Nov-2025 End Date: 01-Dec-2025
Note on ABL241: Activity Name: Install Mechanical Devices Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Mechanical Start Date: 02-Dec-2025 End Date: 02-Dec-2025
Note on ABM241: Activity Name: Electrical/FA Trim-out Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 03-Dec-2025 End Date: 04-Dec-2025
Note on ACA241: Activity Name: Install Light Fixtures Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Electrical Start Date: 17-Dec-2025 End Date: 18-Dec-2025
Note on ACJ241: Activity Name: Construction Rough Clean Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Clean Start Date: 26-Dec-2025 End Date: 30-Dec-2025
Note on ACO241: Activity Name: MCC Completion List - Prepare/Distribute/Complete Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Manhattan Start Date: 31-Dec-2025 End Date: 15-Jan-2026
Note on ADE241: Activity Name: Design Team Punch List & Completion Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Manhattan Start Date: 16-Jan-2026 End Date: 29-Jan-2026
Note on ADS241: Activity Name: Final Clean Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Clean Start Date: 30-Jan-2026 End Date: 30-Jan-2026
Note on ABL242: Activity Name: Seal IDF Floor Phase: INTERIORS Location: Concession Wings - Concourse level Trade: Flooring Start Date: 02-Dec-2025 End Date: 02-Dec-2025
Note on SK245: Activity Name: Drill Tower Crane Piers Phase: INTERIORS Location: Hositing Trade: Concrete Start Date: 11-Apr-2025 End Date: 14-Apr-2025
Note on SO245: Activity Name: Install Tower Crane Foundations Phase: INTERIORS Location: Hositing Trade: Concrete Start Date: 15-Apr-2025 End Date: 05-May-2025
Note on TJ245: Activity Name: Tower Crane Erection Phase: INTERIORS Location: Hositing Trade: Crane Start Date: 06-May-2025 End Date: 12-May-2025
Note on AHB245: Activity Name: Tower Crane Dismantle Phase: INTERIORS Location: Hositing Trade: Crane Start Date: 27-Apr-2026 End Date: 01-May-2026
Note on TJ246: Activity Name: Tower Crane Duration Phase: INTERIORS Location: Hositing Trade: Crane Start Date: 06-May-2025 End Date: 01-May-2026
Note on SI249: Activity Name: Drill Tower Crane Piers Phase: INTERIORS Location: Hositing Trade: Concrete Start Date: 09-Apr-2025 End Date: 10-Apr-2025
Note on SK249: Activity Name: Install Tower Crane Foundations Phase: INTERIORS Location: Hositing Trade: Concrete Start Date: 11-Apr-2025 End Date: 01-May-2025
Note on TF249: Activity Name: Tower Crane Erection Phase: INTERIORS Location: Hositing Trade: Crane Start Date: 02-May-2025 End Date: 08-May-2025
Note on AHI249: Activity Name: Tower Crane Dismantle Phase: INTERIORS Location: Hositing Trade: Crane Start Date: 04-May-2026 End Date: 08-May-2026
Note on TF250: Activity Name: Tower Crane Duration Phase: INTERIORS Location: Hositing Trade: Crane Start Date: 02-May-2025 End Date: 08-May-2026
Note on YM253: Activity Name: Partition Layout & Top Track Phase: INTERIORS Location: Main building - Concourse level Trade: Framing Start Date: 16-Sep-2025 End Date: 19-Sep-2025
Note on YS253: Activity Name: Mechanical Overhead & Riser Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 22-Sep-2025 End Date: 01-Oct-2025
Note on ZD253: Activity Name: Plumbing/Piping Overhead & Riser Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 03-Oct-2025 End Date: 09-Oct-2025
Note on ZK253: Activity Name: Frame & One-side Walls Phase: INTERIORS Location: Main building - Concourse level Trade: Framing Start Date: 10-Oct-2025 End Date: 14-Oct-2025
Note on ZP253: Activity Name: Elect/LV Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 15-Oct-2025 End Date: 21-Oct-2025
Note on ZX253: Activity Name: In-Wall QC Check Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 23-Oct-2025 End Date: 24-Oct-2025
Note on AAB253: Activity Name: COF In-Wall Inspection Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 27-Oct-2025 End Date: 27-Oct-2025
Note on AAC253: Activity Name: Insulate & Close Walls Phase: INTERIORS Location: Main building - Concourse level Trade: Drywall Start Date: 28-Oct-2025 End Date: 31-Oct-2025
Note on AAI253: Activity Name: Tape/Bed/Prime/ 1st Coat Walls Phase: INTERIORS Location: Main building - Concourse level Trade: Drywall Start Date: 03-Nov-2025 End Date: 14-Nov-2025
Note on AAW253: Activity Name: Install Interior Storefront Phase: INTERIORS Location: Main building - Concourse level Trade: Specialty Start Date: 17-Nov-2025 End Date: 02-Dec-2025
Note on ABO253: Activity Name: Install Light Fixtures Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 05-Dec-2025 End Date: 18-Dec-2025
Note on ACC253: Activity Name: Drop Sprinkler Heads Phase: INTERIORS Location: Main building - Concourse level Trade: Fire Sprinkler Start Date: 19-Dec-2025 End Date: 24-Dec-2025
Note on ACJ253: Activity Name: Overhead QC Inspection Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 26-Dec-2025 End Date: 29-Dec-2025
Note on ACN253: Activity Name: COF Overhead Inspections Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 30-Dec-2025 End Date: 30-Dec-2025
Note on ACO253: Activity Name: Close Ceilings/Furrdowns Phase: INTERIORS Location: Main building - Concourse level Trade: Ceiling Start Date: 31-Dec-2025 End Date: 15-Jan-2026
Note on ADE253: Activity Name: Install Brick Veneer Phase: INTERIORS Location: Main building - Concourse level Trade: Masonry Start Date: 16-Jan-2026 End Date: 19-Feb-2026
Note on AEN253: Activity Name: Install Drink Rail Supports Phase: INTERIORS Location: Main building - Concourse level Trade: Millwork Start Date: 20-Feb-2026 End Date: 24-Feb-2026
Note on AEY253: Activity Name: Trim Out Mechanical Devices Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 03-Mar-2026 End Date: 06-Mar-2026
Note on AFF253: Activity Name: Install Epoxy Flooring/Base Phase: INTERIORS Location: Main building - Concourse level Trade: Flooring Start Date: 10-Mar-2026 End Date: 16-Mar-2026
Note on AFM253: Activity Name: Install Bar Fronts & Columns Phase: INTERIORS Location: Main building - Concourse level Trade: Millwork Start Date: 17-Mar-2026 End Date: 23-Mar-2026
Note on AFT253: Activity Name: Install Bar Tops Phase: INTERIORS Location: Main building - Concourse level Trade: Millwork Start Date: 24-Mar-2026 End Date: 30-Mar-2026
Note on AGA253: Activity Name: Install Bar Equipment Phase: INTERIORS Location: Main building - Concourse level Trade: Equipment Start Date: 31-Mar-2026 End Date: 06-Apr-2026
Note on AGH253: Activity Name: Plumbing Trim-out Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 07-Apr-2026 End Date: 13-Apr-2026
Note on AGP253: Activity Name: Install Millwork/Glass Panel Columns Phase: INTERIORS Location: Main building - Concourse level Trade: Millwork Start Date: 15-Apr-2026 End Date: 12-May-2026
Note on AHR253: Activity Name: Electric/FA/LV Trim-out & Specialty Lights Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 13-May-2026 End Date: 20-May-2026
Note on AHZ253: Activity Name: Construction Rough Clean Phase: INTERIORS Location: Main building - Concourse level Trade: Clean Start Date: 21-May-2026 End Date: 28-May-2026
Note on AIH253: Activity Name: MCC Completion List - Prepare/Distribute/Complete Phase: INTERIORS Location: Main building - Concourse level Trade: Manhattan Start Date: 29-May-2026 End Date: 11-Jun-2026
Note on AIV253: Activity Name: Design Team Punch List & Completion Phase: INTERIORS Location: Main building - Concourse level Trade: Manhattan Start Date: 12-Jun-2026 End Date: 25-Jun-2026
Note on AJJ253: Activity Name: Final Clean Phase: INTERIORS Location: Main building - Concourse level Trade: Clean Start Date: 26-Jun-2026 End Date: 30-Jun-2026
Note on YT254: Activity Name: Fire Protection Overhead Phase: INTERIORS Location: Main building - Concourse level Trade: Fire Sprinkler Start Date: 23-Sep-2025 End Date: 02-Oct-2025
Note on ZQ254: Activity Name: Plumbing In-wall Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 16-Oct-2025 End Date: 22-Oct-2025
Note on AAW254: Activity Name: Frame Hard Ceilings/Furrdowns Phase: INTERIORS Location: Main building - Concourse level Trade: Framing Start Date: 17-Nov-2025 End Date: 04-Dec-2025
Note on ABT254: Activity Name: Install Mechanical Devices Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 10-Dec-2025 End Date: 16-Dec-2025
Note on ACA254: Activity Name: Install FA/LV Pathway Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 17-Dec-2025 End Date: 24-Dec-2025
Note on ADA254: Activity Name: Tape/Bed/Paint Ceilings Phase: INTERIORS Location: Main building - Concourse level Trade: Drywall Start Date: 12-Jan-2026 End Date: 30-Jan-2026
Note on AEY254: Activity Name: Trim Out Sprinklers Phase: INTERIORS Location: Main building - Concourse level Trade: Fire Sprinkler Start Date: 03-Mar-2026 End Date: 06-Mar-2026
Note on AFG254: Activity Name: Install Tile Floor Phase: INTERIORS Location: Main building - Concourse level Trade: Tile Start Date: 11-Mar-2026 End Date: 21-Apr-2026
Note on AGW254: Activity Name: Install Drink Rail Tops Phase: INTERIORS Location: Main building - Concourse level Trade: Millwork Start Date: 22-Apr-2026 End Date: 28-Apr-2026
Note on AHD254: Activity Name: Install Locker Wall/Millwork Phase: INTERIORS Location: Main building - Concourse level Trade: Millwork Start Date: 29-Apr-2026 End Date: 05-May-2026
Note on AHK254: Activity Name: Install Ceiling Scarves Phase: INTERIORS Location: Main building - Concourse level Trade: Specialty Start Date: 06-May-2026 End Date: 12-May-2026
Note on ADQ255: Activity Name: Install Wood Ceiling & Bar Soffit Phase: INTERIORS Location: Main building - Concourse level Trade: Millwork Start Date: 28-Jan-2026 End Date: 02-Mar-2026
Note on AEY255: Activity Name: Install Bar Die Walls Phase: INTERIORS Location: Main building - Concourse level Trade: Millwork Start Date: 03-Mar-2026 End Date: 09-Mar-2026
Note on AGW255: Activity Name: Install Wainscot & Base Phase: INTERIORS Location: Main building - Concourse level Trade: Millwork Start Date: 22-Apr-2026 End Date: 28-Apr-2026
Note on AHD255: Activity Name: Install Wallcovering Phase: INTERIORS Location: Main building - Concourse level Trade: Millwork Start Date: 29-Apr-2026 End Date: 05-May-2026
Note on AEY256: Activity Name: Lights Trim-out Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 03-Mar-2026 End Date: 10-Mar-2026
Note on YA257: Activity Name: Partition Layout & Top Track Phase: INTERIORS Location: Main building - Concourse level Trade: Framing Start Date: 04-Sep-2025 End Date: 10-Sep-2025
Note on YH257: Activity Name: Mechanical Overhead & Riser Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 11-Sep-2025 End Date: 16-Sep-2025
Note on YN257: Activity Name: Plumbing/Piping Overhead & Riser Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 17-Sep-2025 End Date: 24-Sep-2025
Note on YV257: Activity Name: Frame & One-side Walls Phase: INTERIORS Location: Main building - Concourse level Trade: Framing Start Date: 25-Sep-2025 End Date: 30-Sep-2025
Note on ZH257: Activity Name: Plumbing In-wall Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 07-Oct-2025 End Date: 13-Oct-2025
Note on ZO257: Activity Name: In-Wall QC Check Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 14-Oct-2025 End Date: 14-Oct-2025
Note on ZP257: Activity Name: COF In-Wall Inspection Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 15-Oct-2025 End Date: 15-Oct-2025
Note on ZQ257: Activity Name: Insulate & Close Walls Phase: INTERIORS Location: Main building - Concourse level Trade: Drywall Start Date: 16-Oct-2025 End Date: 22-Oct-2025
Note on AAE257: Activity Name: Install Counter Shutters Phase: INTERIORS Location: Main building - Concourse level Trade: Specialty Start Date: 30-Oct-2025 End Date: 31-Oct-2025
Note on AAI257: Activity Name: Install Kitchen Hoods Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 03-Nov-2025 End Date: 07-Nov-2025
Note on AAP257: Activity Name: Grease Duct Tie-in/Insulate Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 10-Nov-2025 End Date: 21-Nov-2025
Note on ABE257: Activity Name: Final Paint Storage Phase: INTERIORS Location: Main building - Concourse level Trade: Paint Start Date: 25-Nov-2025 End Date: 01-Dec-2025
Note on ABL257: Activity Name: Build-out IDF Room Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 02-Dec-2025 End Date: 08-Dec-2025
Note on ABS257: Activity Name: Install Light Fixtures Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 09-Dec-2025 End Date: 12-Dec-2025
Note on ABY257: Activity Name: Drop Sprinkler Heads Phase: INTERIORS Location: Main building - Concourse level Trade: Fire Sprinkler Start Date: 15-Dec-2025 End Date: 16-Dec-2025
Note on ACA257: Activity Name: Overhead QC Inspection Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 17-Dec-2025 End Date: 17-Dec-2025
Note on ACB257: Activity Name: COF Overhead Inspections Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 18-Dec-2025 End Date: 18-Dec-2025
Note on ACC257: Activity Name: Install Epoxy Flooring/Base Phase: INTERIORS Location: Main building - Concourse level Trade: Flooring Start Date: 19-Dec-2025 End Date: 05-Jan-2026
Note on ACU257: Activity Name: Install Concession Wall Finish Phase: INTERIORS Location: Main building - Concourse level Trade: Specialty Start Date: 06-Jan-2026 End Date: 03-Feb-2026
Note on ADX257: Activity Name: Install Mechanical Wall Units/Air Curtains Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 04-Feb-2026 End Date: 06-Feb-2026
Note on AES257: Activity Name: Install Food Service Equipment Phase: INTERIORS Location: Main building - Concourse level Trade: Equipment Start Date: 25-Feb-2026 End Date: 10-Mar-2026
Note on AFG257: Activity Name: Install Doors & Hardware Phase: INTERIORS Location: Main building - Concourse level Trade: Equipment Start Date: 11-Mar-2026 End Date: 12-Mar-2026
Note on AFI257: Activity Name: Electrical/FA Trim-out Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 13-Mar-2026 End Date: 19-Mar-2026
Note on AFP257: Activity Name: Kitchen Hood Testing Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 20-Mar-2026 End Date: 20-Mar-2026
Note on AFU257: Activity Name: Install ACT Tile Phase: INTERIORS Location: Main building - Concourse level Trade: Ceiling Start Date: 25-Mar-2026 End Date: 31-Mar-2026
Note on AGB257: Activity Name: Construction Rough Clean Phase: INTERIORS Location: Main building - Concourse level Trade: Clean Start Date: 01-Apr-2026 End Date: 07-Apr-2026
Note on AGI257: Activity Name: MCC Completion List - Prepare/Distribute/Complete Phase: INTERIORS Location: Main building - Concourse level Trade: Manhattan Start Date: 08-Apr-2026 End Date: 21-Apr-2026
Note on AGW257: Activity Name: Design Team Punch List & Completion Phase: INTERIORS Location: Main building - Concourse level Trade: Manhattan Start Date: 22-Apr-2026 End Date: 05-May-2026
Note on AHK257: Activity Name: Final Clean Phase: INTERIORS Location: Main building - Concourse level Trade: Clean Start Date: 06-May-2026 End Date: 08-May-2026
Note on YH258: Activity Name: Fire Protection Overhead Phase: INTERIORS Location: Main building - Concourse level Trade: Fire Sprinkler Start Date: 11-Sep-2025 End Date: 16-Sep-2025
Note on ZA258: Activity Name: Elect/LV Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 30-Sep-2025 End Date: 06-Oct-2025
Note on ZV258: Activity Name: Tape/Bed/Prime/ 1st Coat Walls Phase: INTERIORS Location: Main building - Concourse level Trade: Drywall Start Date: 21-Oct-2025 End Date: 29-Oct-2025
Note on AAE258: Activity Name: FRP MEP Pads Phase: INTERIORS Location: Main building - Concourse level Trade: Concrete Start Date: 30-Oct-2025 End Date: 31-Oct-2025
Note on AAS258: Activity Name: Install Walk-in Cooler/Freezer Phase: INTERIORS Location: Main building - Concourse level Trade: Refrigeration Start Date: 13-Nov-2025 End Date: 19-Nov-2025
Note on ABA258: Activity Name: Seal MEP Rooms Phase: INTERIORS Location: Main building - Concourse level Trade: Drywall Start Date: 21-Nov-2025 End Date: 24-Nov-2025
Note on ABE258: Activity Name: Install ACT Grid Phase: INTERIORS Location: Main building - Concourse level Trade: Ceiling Start Date: 25-Nov-2025 End Date: 03-Dec-2025
Note on ABN258: Activity Name: Install Mechanical Devices Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 04-Dec-2025 End Date: 09-Dec-2025
Note on ADX258: Activity Name: Install Plumbing Fixtures Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 04-Feb-2026 End Date: 06-Feb-2026
Note on AFG258: Activity Name: Plumbing Trim-out Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 11-Mar-2026 End Date: 17-Mar-2026
Note on AFP258: Activity Name: LV Trim-out Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 20-Mar-2026 End Date: 24-Mar-2026
Note on AAT259: Activity Name: Build-out Electrical Room Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 14-Nov-2025 End Date: 20-Nov-2025
Note on YH261: Activity Name: Partition Layout & Top Track Phase: INTERIORS Location: Main building - Concourse level Trade: Framing Start Date: 11-Sep-2025 End Date: 15-Sep-2025
Note on YN261: Activity Name: Mechanical Overhead & Riser Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 17-Sep-2025 End Date: 19-Sep-2025
Note on YS261: Activity Name: Plumbing/Piping Overhead & Riser Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 22-Sep-2025 End Date: 26-Sep-2025
Note on ZB261: Activity Name: Frame & One-side Walls Phase: INTERIORS Location: Main building - Concourse level Trade: Framing Start Date: 01-Oct-2025 End Date: 06-Oct-2025
Note on ZH261: Activity Name: Install Vanity Supports Phase: INTERIORS Location: Main building - Concourse level Trade: Carpentry Start Date: 07-Oct-2025 End Date: 09-Oct-2025
Note on ZO261: Activity Name: In-Wall QC Check Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 14-Oct-2025 End Date: 14-Oct-2025
Note on ZP261: Activity Name: COF In-Wall Inspection Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 15-Oct-2025 End Date: 15-Oct-2025
Note on ZQ261: Activity Name: Insulate & Close Walls Phase: INTERIORS Location: Main building - Concourse level Trade: Drywall Start Date: 16-Oct-2025 End Date: 22-Oct-2025
Note on ZX261: Activity Name: Tape/Bed/Prime/ 1st Coat Walls Phase: INTERIORS Location: Main building - Concourse level Trade: Drywall Start Date: 23-Oct-2025 End Date: 05-Nov-2025
Note on AAL261: Activity Name: Frame Hard Ceilings/Soffits Phase: INTERIORS Location: Main building - Concourse level Trade: Framing Start Date: 06-Nov-2025 End Date: 12-Nov-2025
Note on AAS261: Activity Name: Install Mechanical Devices Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 13-Nov-2025 End Date: 18-Nov-2025
Note on AAY261: Activity Name: Install FA/LV Pathway Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 19-Nov-2025 End Date: 21-Nov-2025
Note on ABF261: Activity Name: Drop Sprinkler Heads Phase: INTERIORS Location: Main building - Concourse level Trade: Fire Sprinkler Start Date: 26-Nov-2025 End Date: 01-Dec-2025
Note on ABL261: Activity Name: Overhead QC Inspection Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 02-Dec-2025 End Date: 02-Dec-2025
Note on ABM261: Activity Name: COF Overhead Inspections Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 03-Dec-2025 End Date: 03-Dec-2025
Note on ABN261: Activity Name: Close Hard Ceilings/Soffits Phase: INTERIORS Location: Main building - Concourse level Trade: Drywall Start Date: 04-Dec-2025 End Date: 10-Dec-2025
Note on ABU261: Activity Name: Tape/Bed/Paint Ceilings Phase: INTERIORS Location: Main building - Concourse level Trade: Drywall Start Date: 11-Dec-2025 End Date: 24-Dec-2025
Note on ACJ261: Activity Name: Install Restroom Wall Tile & Base Phase: INTERIORS Location: Main building - Concourse level Trade: Tile Start Date: 26-Dec-2025 End Date: 26-Jan-2026
Note on ADP261: Activity Name: Install Plumbing Fixtures Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 27-Jan-2026 End Date: 09-Feb-2026
Note on AED261: Activity Name: Install Countertops Phase: INTERIORS Location: Main building - Concourse level Trade: Specialty Start Date: 10-Feb-2026 End Date: 13-Feb-2026
Note on AEJ261: Activity Name: Plumbing Trim-out Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 16-Feb-2026 End Date: 17-Feb-2026
Note on AEL261: Activity Name: Install Toilet Partitions Phase: INTERIORS Location: Main building - Concourse level Trade: Specialty Start Date: 18-Feb-2026 End Date: 24-Feb-2026
Note on AES261: Activity Name: Install Toilet Accessories Phase: INTERIORS Location: Main building - Concourse level Trade: Specialty Start Date: 25-Feb-2026 End Date: 03-Mar-2026
Note on AEZ261: Activity Name: Install Doors & Hardware Phase: INTERIORS Location: Main building - Concourse level Trade: Equipment Start Date: 04-Mar-2026 End Date: 05-Mar-2026
Note on AFB261: Activity Name: LV Trim-out Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 06-Mar-2026 End Date: 10-Mar-2026
Note on AFL261: Activity Name: Construction Rough Clean Phase: INTERIORS Location: Main building - Concourse level Trade: Clean Start Date: 16-Mar-2026 End Date: 20-Mar-2026
Note on AFS261: Activity Name: MCC Completion List - Prepare/Distribute/Complete Phase: INTERIORS Location: Main building - Concourse level Trade: Manhattan Start Date: 23-Mar-2026 End Date: 03-Apr-2026
Note on AGG261: Activity Name: Design Team Punch List & Completion Phase: INTERIORS Location: Main building - Concourse level Trade: Manhattan Start Date: 06-Apr-2026 End Date: 17-Apr-2026
Note on AGU261: Activity Name: Final Clean Phase: INTERIORS Location: Main building - Concourse level Trade: Clean Start Date: 20-Apr-2026 End Date: 22-Apr-2026
Note on YN262: Activity Name: Fire Protection Overhead Phase: INTERIORS Location: Main building - Concourse level Trade: Fire Sprinkler Start Date: 17-Sep-2025 End Date: 22-Sep-2025
Note on ZH262: Activity Name: Plumbing In-wall Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 07-Oct-2025 End Date: 10-Oct-2025
Note on AAY262: Activity Name: Install Light Fixtures Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 19-Nov-2025 End Date: 24-Nov-2025
Note on ACO262: Activity Name: Final Paint Janitor Closet Phase: INTERIORS Location: Main building - Concourse level Trade: Paint Start Date: 31-Dec-2025 End Date: 05-Jan-2026
Note on AFB262: Activity Name: Electrical/FA Trim-out Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 06-Mar-2026 End Date: 12-Mar-2026
Note on ZI263: Activity Name: Elect/LV Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 08-Oct-2025 End Date: 13-Oct-2025
Note on YS265: Activity Name: Partition Layout & Top Track Phase: INTERIORS Location: Main building - Concourse level Trade: Framing Start Date: 22-Sep-2025 End Date: 23-Sep-2025
Note on YU265: Activity Name: Fire Protection Overhead Phase: INTERIORS Location: Main building - Concourse level Trade: Fire Sprinkler Start Date: 24-Sep-2025 End Date: 25-Sep-2025
Note on YZ265: Activity Name: Plumbing/Piping Overhead & Riser Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 29-Sep-2025 End Date: 03-Oct-2025
Note on ZH265: Activity Name: Frame & One-side Walls Phase: INTERIORS Location: Main building - Concourse level Trade: Framing Start Date: 07-Oct-2025 End Date: 09-Oct-2025
Note on ZN265: Activity Name: Plumbing In-wall Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 13-Oct-2025 End Date: 16-Oct-2025
Note on ZU265: Activity Name: In-Wall QC Check Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 20-Oct-2025 End Date: 20-Oct-2025
Note on ZV265: Activity Name: COF In-Wall Inspection Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 21-Oct-2025 End Date: 21-Oct-2025
Note on ZX265: Activity Name: Insulate & Close Walls Phase: INTERIORS Location: Main building - Concourse level Trade: Drywall Start Date: 23-Oct-2025 End Date: 24-Oct-2025
Note on AAB265: Activity Name: Tape/Bed/Prime/ 1st Coat Walls Phase: INTERIORS Location: Main building - Concourse level Trade: Drywall Start Date: 27-Oct-2025 End Date: 04-Nov-2025
Note on AAK265: Activity Name: Seal MEP Rooms Phase: INTERIORS Location: Main building - Concourse level Trade: Drywall Start Date: 05-Nov-2025 End Date: 05-Nov-2025
Note on AAL265: Activity Name: Install Kitchen Hoods Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 06-Nov-2025 End Date: 07-Nov-2025
Note on AAP265: Activity Name: Install Walk-in Cooler/Freezer Phase: INTERIORS Location: Main building - Concourse level Trade: Refrigeration Start Date: 10-Nov-2025 End Date: 12-Nov-2025
Note on AAS265: Activity Name: Grease Duct Tie-in/Insulate Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 13-Nov-2025 End Date: 19-Nov-2025
Note on AAZ265: Activity Name: Install ACT Grid Phase: INTERIORS Location: Main building - Concourse level Trade: Ceiling Start Date: 20-Nov-2025 End Date: 24-Nov-2025
Note on ABE265: Activity Name: Install Mechanical Devices Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 25-Nov-2025 End Date: 26-Nov-2025
Note on ABK265: Activity Name: Drop Sprinkler Heads Phase: INTERIORS Location: Main building - Concourse level Trade: Fire Sprinkler Start Date: 01-Dec-2025 End Date: 01-Dec-2025
Note on ABL265: Activity Name: Install FA/LV Pathway Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 02-Dec-2025 End Date: 03-Dec-2025
Note on ABN265: Activity Name: Install Light Fixtures Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 04-Dec-2025 End Date: 08-Dec-2025
Note on ABS265: Activity Name: Overhead QC Inspection Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 09-Dec-2025 End Date: 09-Dec-2025
Note on ABT265: Activity Name: COF Overhead Inspections Phase: INTERIORS Location: Main building - Concourse level Trade: Inspection Start Date: 10-Dec-2025 End Date: 10-Dec-2025
Note on ABU265: Activity Name: Install Epoxy Flooring/Base Phase: INTERIORS Location: Main building - Concourse level Trade: Flooring Start Date: 11-Dec-2025 End Date: 17-Dec-2025
Note on ACB265: Activity Name: Install Concession Wall Finish Phase: INTERIORS Location: Main building - Concourse level Trade: Specialty Start Date: 18-Dec-2025 End Date: 02-Jan-2026
Note on ACT265: Activity Name: Install Plumbing Fixtures Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 05-Jan-2026 End Date: 06-Jan-2026
Note on ACW265: Activity Name: Install Food Service Equipment Phase: INTERIORS Location: Main building - Concourse level Trade: Equipment Start Date: 08-Jan-2026 End Date: 15-Jan-2026
Note on ADE265: Activity Name: Plumbing Trim-out Phase: INTERIORS Location: Main building - Concourse level Trade: Plumbing Start Date: 16-Jan-2026 End Date: 20-Jan-2026
Note on ADL265: Activity Name: Kitchen Hood Testing Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 23-Jan-2026 End Date: 23-Jan-2026
Note on ADS265: Activity Name: LV Trim-out Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 30-Jan-2026 End Date: 02-Feb-2026
Note on ADW265: Activity Name: Install ACT Tile Phase: INTERIORS Location: Main building - Concourse level Trade: Ceiling Start Date: 03-Feb-2026 End Date: 04-Feb-2026
Note on ADY265: Activity Name: Construction Rough Clean Phase: INTERIORS Location: Main building - Concourse level Trade: Clean Start Date: 05-Feb-2026 End Date: 11-Feb-2026
Note on AEF265: Activity Name: MCC Completion List - Prepare/Distribute/Complete Phase: INTERIORS Location: Main building - Concourse level Trade: Manhattan Start Date: 12-Feb-2026 End Date: 25-Feb-2026
Note on AET265: Activity Name: Design Team Punch List & Completion Phase: INTERIORS Location: Main building - Concourse level Trade: Manhattan Start Date: 26-Feb-2026 End Date: 11-Mar-2026
Note on AFH265: Activity Name: Final Clean Phase: INTERIORS Location: Main building - Concourse level Trade: Clean Start Date: 12-Mar-2026 End Date: 16-Mar-2026
Note on YU266: Activity Name: Mechanical Overhead & Riser Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 24-Sep-2025 End Date: 26-Sep-2025
Note on ZO266: Activity Name: Elect/LV Rough-in Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 14-Oct-2025 End Date: 17-Oct-2025
Note on AAK266: Activity Name: Install Counter Shutters Phase: INTERIORS Location: Main building - Concourse level Trade: Specialty Start Date: 05-Nov-2025 End Date: 06-Nov-2025
Note on ABA266: Activity Name: Build-out Electrical Room Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 21-Nov-2025 End Date: 01-Dec-2025
Note on ACT266: Activity Name: Install Mechanical Wall Units/Air Curtains Phase: INTERIORS Location: Main building - Concourse level Trade: Mechanical Start Date: 05-Jan-2026 End Date: 07-Jan-2026
Note on ADE266: Activity Name: Electrical/FA Trim-out Phase: INTERIORS Location: Main building - Concourse level Trade: Electrical Start Date: 16-Jan-2026 End Date: 22-Jan-2026
Note on ADL266: Activity Name: Install Doors & Hardware Phase: INTERIORS Location: Main building - Concourse level Trade: Equipment Start Date: 23-Jan-2026 End Date: 26-Jan-2026
Note on AAL267: Activity Name: Final Paint MEP Phase: INTERIORS Location: Main building - Concourse level Trade: Paint Start Date: 06-Nov-2025 End Date: 07-Nov-2025
Note on ZR270: Activity Name: Partition Layout & Top Track Phase: INTERIORS Location: Northeast Trade: Framing Start Date: 17-Oct-2025 End Date: 21-Oct-2025
Note on ZW270: Activity Name: Mechanical Overhead & Riser Rough-in Phase: INTERIORS Location: Northeast Trade: Mechanical Start Date: 22-Oct-2025 End Date: 24-Oct-2025
Note on AAI270: Activity Name: Plumbing/Piping Overhead Phase: INTERIORS Location: Northeast Trade: Plumbing Start Date: 03-Nov-2025 End Date: 07-Nov-2025
Note on AAR270: Activity Name: In-Wall QC Check Phase: INTERIORS Location: Northeast Trade: Inspection Start Date: 12-Nov-2025 End Date: 12-Nov-2025
Note on AAS270: Activity Name: COF In-Wall Inspection Phase: INTERIORS Location: Northeast Trade: Inspection Start Date: 13-Nov-2025 End Date: 13-Nov-2025
Note on AAT270: Activity Name: Insulate & Close Walls Phase: INTERIORS Location: Northeast Trade: Drywall Start Date: 14-Nov-2025 End Date: 18-Nov-2025
Note on AAY270: Activity Name: Tape/Bed/Prime/ 1st Coat Walls Phase: INTERIORS Location: Northeast Trade: Drywall Start Date: 19-Nov-2025 End Date: 01-Dec-2025
Note on ABL270: Activity Name: Frame Hard Ceilings/Soffits Phase: INTERIORS Location: Northeast Trade: Framing Start Date: 02-Dec-2025 End Date: 02-Dec-2025
Note on ABM270: Activity Name: Grease Duct Tie-in/Insulate Phase: INTERIORS Location: Northeast Trade: Mechanical Start Date: 03-Dec-2025 End Date: 08-Dec-2025
Note on ABS270: Activity Name: Install ACT Grid Phase: INTERIORS Location: Northeast Trade: Ceiling Start Date: 09-Dec-2025 End Date: 11-Dec-2025
Note on ABV270: Activity Name: Install Mechanical Devices Phase: INTERIORS Location: Northeast Trade: Mechanical Start Date: 12-Dec-2025 End Date: 15-Dec-2025
Note on ABZ270: Activity Name: Drop Sprinkler Heads Phase: INTERIORS Location: Northeast Trade: Fire Sprinkler Start Date: 16-Dec-2025 End Date: 16-Dec-2025
Note on ACA270: Activity Name: Overhead QC Inspection Phase: INTERIORS Location: Northeast Trade: Inspection Start Date: 17-Dec-2025 End Date: 17-Dec-2025
Note on ACB270: Activity Name: COF Overhead Inspections Phase: INTERIORS Location: Northeast Trade: Inspection Start Date: 18-Dec-2025 End Date: 18-Dec-2025
Note on ACC270: Activity Name: Close Hard Ceilings/Soffits Phase: INTERIORS Location: Northeast Trade: Drywall Start Date: 19-Dec-2025 End Date: 19-Dec-2025
Note on ACF270: Activity Name: Tape/Bed/Paint Ceilings Phase: INTERIORS Location: Northeast Trade: Drywall Start Date: 22-Dec-2025 End Date: 29-Dec-2025
Note on ACU270: Activity Name: Final Paint Storage Phase: INTERIORS Location: Northeast Trade: Paint Start Date: 06-Jan-2026 End Date: 08-Jan-2026
Note on ADC270: Activity Name: Seal MEP/Storage Rooms Phase: INTERIORS Location: Northeast Trade: Drywall Start Date: 14-Jan-2026 End Date: 14-Jan-2026
Note on ADI270: Activity Name: Install Plumbing Fixtures Phase: INTERIORS Location: Northeast Trade: Plumbing Start Date: 20-Jan-2026 End Date: 23-Jan-2026
Note on ADO270: Activity Name: Install Toilet Partions Phase: INTERIORS Location: Northeast Trade: Specialty Start Date: 26-Jan-2026 End Date: 30-Jan-2026
Note on ADX270: Activity Name: Install Doors & Hardware Phase: INTERIORS Location: Northeast Trade: Equipment Start Date: 04-Feb-2026 End Date: 05-Feb-2026
Note on ADZ270: Activity Name: Plumbing Trim-out Phase: INTERIORS Location: Northeast Trade: Plumbing Start Date: 06-Feb-2026 End Date: 09-Feb-2026
Note on AEE270: Activity Name: Install ACT Tile Phase: INTERIORS Location: Northeast Trade: Ceiling Start Date: 11-Feb-2026 End Date: 12-Feb-2026
Note on AEG270: Activity Name: Construction Rough Clean Phase: INTERIORS Location: Northeast Trade: Clean Start Date: 13-Feb-2026 End Date: 19-Feb-2026
Note on AEN270: Activity Name: MCC Completion List - Prepare/Distribute/Complete Phase: INTERIORS Location: Northeast Trade: Manhattan Start Date: 20-Feb-2026 End Date: 05-Mar-2026
Note on AFB270: Activity Name: Design Team Punch List & Completion Phase: INTERIORS Location: Northeast Trade: Manhattan Start Date: 06-Mar-2026 End Date: 19-Mar-2026
Note on AFP270: Activity Name: Final Clean Phase: INTERIORS Location: Northeast Trade: Clean Start Date: 20-Mar-2026 End Date: 23-Mar-2026
Note on ZW271: Activity Name: Fire Protection Overhead Phase: INTERIORS Location: Northeast Trade: Fire Sprinkler Start Date: 22-Oct-2025 End Date: 24-Oct-2025
Note on AAJ271: Activity Name: Frame & One-side Walls Phase: INTERIORS Location: Northeast Trade: Framing Start Date: 04-Nov-2025 End Date: 05-Nov-2025
Note on AAL271: Activity Name: Elect/LV Rough-in Phase: INTERIORS Location: Northeast Trade: Electrical Start Date: 06-Nov-2025 End Date: 11-Nov-2025
Note on ABL271: Activity Name: Install Kitchen Hoods Phase: INTERIORS Location: Northeast Trade: Mechanical Start Date: 02-Dec-2025 End Date: 02-Dec-2025
Note on ABM271: Activity Name: Install Walk-in Cooler/Freezer Phase: INTERIORS Location: Northeast Trade: Refrigeration Start Date: 03-Dec-2025 End Date: 08-Dec-2025
Note on ABV271: Activity Name: Install FA/LV Pathway Phase: INTERIORS Location: Northeast Trade: Electrical Start Date: 12-Dec-2025 End Date: 15-Dec-2025
Note on ACU271: Activity Name: Install Epoxy Flooring/Base Phase: INTERIORS Location: Northeast Trade: Flooring Start Date: 06-Jan-2026 End Date: 13-Jan-2026
Note on ADC271: Activity Name: Install Restroom Wall Tile Phase: INTERIORS Location: Northeast Trade: Tile Start Date: 14-Jan-2026 End Date: 19-Jan-2026
Note on ADR271: Activity Name: Install Toilet Accessories Phase: INTERIORS Location: Northeast Trade: Specialty Start Date: 29-Jan-2026 End Date: 30-Jan-2026
Note on ADX271: Activity Name: Electrical/FA Trim-out Phase: INTERIORS Location: Northeast Trade: Electrical Start Date: 04-Feb-2026 End Date: 06-Feb-2026
Note on AEC271: Activity Name: Kitchen Hood Testing Phase: INTERIORS Location: Northeast Trade: Mechanical Start Date: 09-Feb-2026 End Date: 09-Feb-2026
Note on ABL272: Activity Name: Install Counter Shutters Phase: INTERIORS Location: Northeast Trade: Specialty Start Date: 02-Dec-2025 End Date: 08-Dec-2025
Note on ABV272: Activity Name: Install Light Fixtures Phase: INTERIORS Location: Northeast Trade: Electrical Start Date: 12-Dec-2025 End Date: 16-Dec-2025
Note on ADC272: Activity Name: Install Concession Wall Finish Phase: INTERIORS Location: Northeast Trade: Specialty Start Date: 14-Jan-2026 End Date: 29-Jan-2026
Note on ADS272: Activity Name: Install Mechanical Wall Units/Air Curtains Phase: INTERIORS Location: Northeast Trade: Mechanical Start Date: 30-Jan-2026 End Date: 03-Feb-2026
Note on AEC272: Activity Name: LV Trim-out Phase: INTERIORS Location: Northeast Trade: Electrical Start Date: 09-Feb-2026 End Date: 10-Feb-2026
Note on ADS273: Activity Name: Install Food Service Equipment Phase: INTERIORS Location: Northeast Trade: Equipment Start Date: 30-Jan-2026 End Date: 03-Feb-2026
Note on AEZ274: Activity Name: Pour Bowl Steps Phase: INTERIORS Location: Seating Bowl - Main Building Trade: Concrete Start Date: 04-Mar-2026 End Date: 25-Mar-2026
Note on AFV274: Activity Name: Install Bowl Rails Phase: INTERIORS Location: Seating Bowl - Main Building Trade: Miscellaneous Start Date: 26-Mar-2026 End Date: 08-Apr-2026
Note on AGJ274: Activity Name: Install Stadium Seats Phase: INTERIORS Location: Seating Bowl - Main Building Trade: Equipment Start Date: 09-Apr-2026 End Date: 13-May-2026
Note on AHS274: Activity Name: Construction Rough Clean Phase: INTERIORS Location: Seating Bowl - Main Building Trade: Clean Start Date: 14-May-2026 End Date: 28-May-2026
Note on AIH274: Activity Name: MCC Completion List Phase: INTERIORS Location: Seating Bowl - Main Building Trade: Manhattan Start Date: 29-May-2026 End Date: 11-Jun-2026
Note on AIV274: Activity Name: Design Team Punch List & Complete Phase: INTERIORS Location: Seating Bowl - Main Building Trade: Manhattan Start Date: 12-Jun-2026 End Date: 25-Jun-2026
Note on AJJ274: Activity Name: Final Clean Phase: INTERIORS Location: Seating Bowl - Main Building Trade: Clean Start Date: 26-Jun-2026 End Date: 29-Jun-2026

## CFA - Legends
Procurement |  | MILESTONES/HAMMOCKS |  | MAJOR MILESTONES |  | SCHEMATIC DESIGN |  | DESIGN DEVELOPMENT |  | PERMIT PACKAGE |  | CONSTRUCTION DOCUMENTS |  | PERMITS |  | DEMOLITION |  | FOUNDATIONS |  | South HOF |  | STRUCTURE |  | EXTERIORS |  | CIVIL/SITE |  | CANOPIES |  | INTERIORS
|  | M/H | East Canopy Installation Complete | MM | Notice to Proceed For Construction |  |  | DD | Design Development 50% |  |  | CD | Core and Shell / Permit / Demolition Package | PT | Building Permit (East Demo) - Review & Approval
Manhattan | [5 empty] | Architect |  |  |  | Manhattan | [5 empty] | Demolition |  | Concrete |  | Audovisual |  | Concrete |  | Carpentry |  | Hardscape/Landscape |  | Electrical |  | Carpentry
PR | Canopy Submittals by Trade Partner |  |  |  |  | SC | Schematic Design-Full Project (Architecture and Structure) |  |  | PP | Canopy Structure SteelPackage |  |  |  |  | O1 | Precision Demo & Temp Protection | C1 | Drilled Piers | AV1 | Install New Bowl Speakers | C10 | FRP SOMD | T1 | Frame Soffit | HL1 | Hardscape/Landscape | E2 | Install Bowl Speakers/Stadium Lights | T3 | Install Vanity Supports
[16 empty] | MEP |  | Earthworks |  | Demolition |  | Decking |  | Concrete |  | Paving |  | Steel |  | Ceiling
[16 empty] | I1 | Trace/Tag/Make Safe MEP Systems | K1 | Elevator Pit - Subsoil/Backfill | O3 | Slab Demo & Removal for gas line | D1 | Detailing & Decking Steel | C11 | Concrete Cure Time | A1 | Install Fire Lane Base Course | S7 | Install Canopy Fabric | Q3 | Install ACT Grid
[16 empty] | Manhattan |  | Electrical |  | Electrical |  | MEP |  | Electrical |  | Underground Utilities |  |  |  | Clean
[16 empty] | MH1 | Project Mobilization | E1 | Electrical Underground | E16 | Install Generator | I3 | MEP In-slab Rough-in | E6 | Install Linear Soffit Lights | U1 | Site Utilities |  |  | CN1 | Construction Rough Clean
[16 empty] | Telecommunications |  | Geofom |  | Equipment |  | Steel |  | Fire Sprinkler | [5 empty] | Concrete
[16 empty] | T1 | FC Dallas IT & Cell/DAS Equipment Removed/Relocated | G1 | Geofoam Install | EQ5 | Install Field Tunnel Cameras | S4 | Concession Building Steel(Steel/Joist/Deck) - North | H1 | Install Fire Sprinkler |  |  |  |  | C13 | FRP Equipment Pads
[18 empty] | MEP |  | Plumbing |  |  |  | Framing | [5 empty] | Crane
[18 empty] | I2 | MEP Underground | P7 | Install new gas line |  |  | F1 | Exterior Framing and Sheathing - North |  |  |  |  | R1 | Tower Crane Erection
[18 empty] | Plumbing |  | Roofing |  |  |  | Glazing | [5 empty] | Drywall
[18 empty] | P1 | Plumbing Underground | SG | Repair Roofing System |  |  | Z2 | Install Storefront System |  |  |  |  | DW1 | Insulate & Close Walls
[18 empty] | Steel |  | Steel |  |  |  | Insulation | [5 empty] | Electrical
[18 empty] | S1 | Camera Platform | S11 | Open Roof for Steel& Sleeves |  |  | J1 | Spray Insulation |  |  |  |  | E7 | Elect/LV Rough-in
[18 empty] | Waterproofing | [5 empty] | Manhattan | [5 empty] | Equipment
[18 empty] | W1 | Elevator Pit - Waterproofing |  |  |  |  | MH2 | MCC Completion List - Prepare/Distribute/Complete |  |  |  |  | EQ2 | Install Doors & Hardware
[24 empty] | Masonry | [5 empty] | Fire Sprinkler
[24 empty] | R1 | Install Masonry Veneer |  |  |  |  | H2 | Fire Protection Overhead
[24 empty] | Mechanical | [5 empty] | Flooring
[24 empty] | M1 | Install Mechanical Equipment |  |  |  |  | FO1 | Install Epoxy Flooring/Base
[24 empty] | Metal Panels | [5 empty] | Framing
[24 empty] | MP3 | Install Metal Panel Fascias & Soffits |  |  |  |  | F2 | Partition Layout & Top Track
[24 empty] | Miscellaneous | [5 empty] | Inspection
[24 empty] | MS1 | Install Entry Gates |  |  |  |  | IS1 | In-Wall QC Check
[24 empty] | Roofing | [5 empty] | MEP
[24 empty] | RG1 | Install Roof Curbs/Rails |  |  |  |  | I4 | Closeout/Commissioning
[24 empty] | Signage | [5 empty] | Manhattan
[24 empty] | SG1 | Install Entry Signage |  |  |  |  | MH2 | MCC Completion List - Prepare/Distribute/Complete
[24 empty] | Specialty | [5 empty] | Masonry
[24 empty] | Y1 | Install Stainless Counters |  |  |  |  | R2 | Install Brick Veneer
[24 empty] | Steel | [5 empty] | Mechanical
[24 empty] | S9 | Install Entry Main Canopy |  |  |  |  | M2 | Mechanical Overhead & Riser Rough-in
[24 empty] | Waterproofing | [5 empty] | Millwork
[24 empty] | W2 | Install Air/Water Barrier |  |  |  |  | ML1 | Install Wood Ceiling & Bar Soffit
Miscellaneous
[30 empty] | MS2 | Install Bowl Rails
Paint
[30 empty] | PT1 | Final Paint Storage
Plumbing
[30 empty] | P6 | Plumbing/Piping Overhead
Refrigeration
[30 empty] | RF1 | Install Walk-in Cooler/Freezer
Specialty
[30 empty] | Y4 | Install Concession Wall Finish
Tile
[30 empty] | TE1 | Install Restroom Wall Tile & Base