## Sheet1
Phase | Location | Trade | Activity Name | Color | Activity Code | Start | Finish
Pre-Construction | Precon | Precon Team | 28. Assign Pre excavation checklist | #632523 | PREC-1 | 2024-01-08 | 2024-01-08
Pre-Construction | Precon | Precon Team | 3.0 Pre construction and mobilization | #632523 | PREC-2 | 2023-09-28 | 2023-12-20
Pre-Construction | Precon | Precon Team | 3.0, 4.0. 5.0 pre, during and post construction total job | #632523 | PREC-3 | 2023-09-28 | 2025-05-05
Pre-Construction | Precon | Precon Team | Assign conrete pour checklist | #632523 | PREC-4 | 2024-09-09 | 2024-09-09
Mobilization | Mobilization | Mobilization Team | Assign Mobilization check list | #637B23 | MOB-1 | 2023-09-28 | 2023-12-20
Pre-Construction | Precon | Precon Team | Assign Equipment & Tools check list | #632523 | PREC-5 | 2023-09-28 | 2023-12-20
Pre-Construction | Precon | Precon Team | Assign exterior wall pre board inspection check list | #632523 | PREC-6 | 2024-11-08 | 2024-11-08
Pre-Construction | Precon | Precon Team | Assign Final Building Checklist | #632523 | PREC-7 | 2025-03-03 | 2025-03-03
Mobilization | Mobilization | Mobilization Team | Assign Site Services Planning check list | #637B23 | MOB-2 | 2023-09-28 | 2023-12-20
Mobilization | Mobilization | Mobilization Team | Assign Sub Contractor planning checklist | #637B23 | MOB-3 | 2023-09-28 | 2023-12-20
Pre-Construction | Precon | Precon Team | Assign framing check list | #632523 | PREC-8 | 2024-05-14 | 2024-05-14
Pre-Construction | Precon | Precon Team | Assign framing checklist | #632523 | PREC-8 | 2024-04-16 | 2024-04-16
Pre-Construction | Precon | Precon Team | Assign framing checklist | #632523 | PREC-8 | 2024-06-10 | 2024-06-10
Pre-Construction | Precon | Precon Team | Assign framing checklist | #632523 | PREC-8 | 2024-07-08 | 2024-07-08
Pre-Construction | Precon | Precon Team | Assign gypcrete pour checklist | #632523 | PREC-8 | 2024-11-25 | 2024-11-25
Sitework | Site | Site Sub | 4.1 Site Services & Foundation Work | #8064A2 | SIT- | 2023-12-21 | 2024-03-25
Sitework | Site | Site Sub | Site Preparation | #8064A2 | SIT- | 2023-12-21 | 2024-01-05
Sitework | Site | Site Sub | 18. Assign site prep check list (First) | #8064A2 | SIT- | 2023-12-28 | 2023-12-28
Foundation | Interior Bldg | Concrete | Assign hollow core erection checklist | #974706 | CON-1 | 2024-05-27 | 2024-05-27
Foundation | Interior Bldg | Concrete | Assign pre back fill check list | #974706 | CON-1 | 2024-03-01 | 2024-03-01
Pre-Construction | Precon | Precon Team | Assign Health and Safety checklist | #632523 | PREC-8 | 2023-09-28 | 2023-12-20
Foundation | Interior Bldg | Concrete | Assign pre concrete pour checklist | #974706 | CON-1 | 2024-02-27 | 2024-02-27
Pre-Construction | Precon | Precon Team | Assign hollow core checklist | #632523 | PREC-8 | 2024-06-13 | 2024-06-13
Foundation | Interior Bldg | Concrete | Assign pre concrete pour checklist | #974706 | CON-1 | 2024-07-08 | 2024-07-08
Sitework | Site | Site Sub | Strip site | #8064A2 | SIT- | 2023-12-29 | 2024-01-04
Foundation | Interior Bldg | Concrete | Assign pre concrete pour checklist | #974706 | CON-1 | 2024-12-12 | 2024-12-16
Foundation | Parkade | Concrete | Back fill and level parkade | #974706 | CON-2 | 2024-06-20 | 2024-06-26
Pre-Construction | Precon | Precon Team | Assign hollow core erection checklist | #632523 | PREC-8 | 2024-04-19 | 2024-04-19
Foundation | Interior Bldg | Concrete | Back fill exterior grade beam | #974706 | CON-2 | 2024-03-06 | 2024-03-07
Foundation | Interior Bldg | Concrete | Back fill foundation | #974706 | CON-2 | 2024-03-01 | 2024-03-14
Structure | Level 4 | Inspection | 4th floor framing inspection | #C00000 | INS-1 | 2024-11-04 | 2024-11-04
Foundation | Parkade | Concrete | Back fill interior parkade | #974706 | CON-2 | 2024-03-08 | 2024-03-14
Foundation | Interior Bldg | Concrete | Build templates for Anchor bolts | #974706 | CON-3 | 2024-02-15 | 2024-02-15
Foundation | Interior Bldg | Concrete | Deliver pakade slab rebar | #974706 | CON-4 | 2024-06-19 | 2024-06-19
Finishes | Interior Bldg | Inspection | Architectural walk throughs | #C00000 | INS-2 | 2025-02-19 | 2025-02-20
Pre-Construction | Precon | Precon Team | Assign hollow core ordering checklist | #632523 | PREC-8 | 2023-09-28 | 2023-09-28
Foundation | Interior Bldg | Concrete | deliver rebar (footings and gradebeam only) | #974706 | CON-5 | 2023-12-21 | 2023-12-21
Foundation | Parkade | Concrete | Dig footing and parkade foot print | #974706 | CON-6 | 2024-01-08 | 2024-01-16
Foundation | Interior Bldg | Concrete | Ensure Sleeves for electrical are run in the grade beam prior to pouring | #974706 | CON-7 | 2024-02-06 | 2024-02-06
Foundation | Interior Bldg | Concrete | Excavate areas | #974706 | CON-8 | 2024-08-26 | 2024-08-27
Foundation | Interior Bldg | Concrete | Excavation | #974706 | CON-8 | 2024-01-08 | 2024-01-18
Foundation | Interior Bldg | Concrete | Exterior concrete works | #974706 | CON-9 | 2024-08-26 | 2024-12-19
Finishes | Interior Bldg | Inspection | Building inspector walk throughs | #C00000 | INS-3 | 2025-02-21 | 2025-02-24
Foundation | Interior Bldg | Concrete | Form footings | #974706 | CON-10 | 2024-01-19 | 2024-01-24
Foundation | Interior Bldg | Concrete | Form grade beam | #974706 | CON-11 | 2024-02-06 | 2024-02-14
Foundation | Interior Bldg | Concrete | Foundation | #974706 | CON-12 | 2024-01-19 | 2024-02-29
Foundation | Level 2 | Concrete | Hollowcore 2nd floor | #974706 | CON-13 | 2024-04-16 | 2024-06-17
Foundation | Level 3 | Concrete | Hollowcore 3rd floor | #974706 | CON-13 | 2024-05-23 | 2024-05-28
Foundation | Level 4 | Concrete | Hollowcore 4th floor | #974706 | CON-13 | 2024-06-11 | 2024-06-13
Sitework | Site | Site Sub | Site services W/S/S install | #8064A2 | SIT- | 2024-03-15 | 2024-03-25
Pre-Construction | Precon | Precon Team | Assign parkade slab rough in checklist | #632523 | PREC-8 | 2024-06-27 | 2024-06-27
Sitework | Site | Site Sub | Install water and sewer | #8064A2 | SIT- | 2024-03-18 | 2024-03-22
Finishes | Interior Bldg | CX | Assign water and sewer commissioning checklist | #000000 | CX- | 2024-03-25 | 2024-03-25
Finishes | Interior Bldg | CX | Commision Water/sewer/storm | #000000 | CX- | 2024-03-25 | 2024-03-25
Structure | Interior Bldg | Steel | Strucutral Steel | #A02B93 | STL-1 | 2024-03-15 | 2024-03-21
Pre-Construction | Precon | Precon Team | Assign Permits check list | #632523 | PREC-8 | 2023-09-28 | 2023-12-20
Sitework | Site | Site Sub | Structural steel delivered and sorted onsite | #8064A2 | SIT- | 2024-03-18 | 2024-03-18
Structure | Interior Bldg | Steel | Structural steel erection | #A02B93 | STL-2 | 2024-03-20 | 2024-03-21
Structure | Interior Bldg | Framing | 4.2 Framing | #F79646 | FRA- | 2024-04-11 | 2025-01-03
Rough-Ins | Parkade | Rough-In (General) | Rough in parkade slab | #948A54 | RI-1 | 2024-06-12 | 2024-06-26
Rough-Ins | Interior Bldg | Mechanical | Mechanical rough in in slab | #4D93D9 | MCH-1 | 2024-06-12 | 2024-06-18
Rough-Ins | Interior Bldg | Electrical | Electrical rough in in slab | #ECD76A | ELE-1 | 2024-06-12 | 2024-06-18
Foundation | Interior Bldg | Concrete | Install balcony piles | #974706 | CON-14 | 2023-12-25 | 2023-12-27
Foundation | Level 3 | Concrete | Install hollow core 3rd floor, Install backer rod & grout | #974706 | CON-15 | 2024-05-23 | 2024-05-28
Foundation | Level 4 | Concrete | Install hollow core 4th floor and grout | #974706 | CON-15 | 2024-06-11 | 2024-06-12
Pre-Construction | Precon | Precon Team | Assign post decking install check list | #632523 | PREC-8 | 2024-09-17 | 2024-09-17
Sitework | Site | Site Sub | Radon rock install | #8064A2 | SIT-1 | 2024-06-28 | 2024-07-01
Sitework | Site | Site Sub | Install poly | #8064A2 | SIT-2 | 2024-07-02 | 2024-07-02
Foundation | Level 2 | Concrete | Install hollowcore 2nd floor , Install backer rod & Grout 2nd floor | #974706 | CON-15 | 2024-04-16 | 2024-04-18
Foundation | Interior Bldg | Concrete | Install underground insulation | #E9F132 | INSU-1 | 2024-03-04 | 2024-03-05
Foundation | Interior Bldg | Concrete | Measure corner offsets for excavation | #974706 | CON-16 | 2024-01-05 | 2024-01-05
Structure | Parkade | Framing | Framing parkade | #F79646 | FRA- | 2024-04-11 | 2024-04-16
Structure | Parkade | Framing | Frame parkade level | #F79646 | FRA- | 2024-04-11 | 2024-04-15
Pre-Construction | Precon | Precon Team | Assign post landscaping checklist | #632523 | PREC-8 | 2025-05-02 | 2025-05-02
Foundation | Interior Bldg | Concrete | Order all Anchor bolts | #974706 | CON-17 | 2023-12-21 | 2023-12-21
Foundation | Interior Bldg | Concrete | Pour exterior pads | #974706 | CON-18 | 2024-09-10 | 2024-09-10
Pre-Construction | Precon | Precon Team | Assign pre-pour checklist | #632523 | PREC-8 | 2024-02-02 | 2024-02-02
Finishes | Parkade | Paint | Paint underside of ceiling in parkade | #59F3FF | PAI-1 | 2024-06-17 | 2024-06-17
Structure | Level 2 | Framing | Framing 2nd floor | #F79646 | FRA- | 2024-04-19 | 2024-05-14
Structure | Level 2 | Framing | Frame 2nd floor | #F79646 | FRA- | 2024-04-19 | 2024-05-13
Pre-Construction | Precon | Precon Team | Assign Procurement Plan check list | #632523 | PREC-8 | 2023-09-28 | 2023-12-20
Foundation | Interior Bldg | Concrete | Pour exterior sidewalks | #974706 | CON-19 | 2024-12-17 | 2024-12-19
Foundation | Interior Bldg | Concrete | Pour footings | #974706 | CON-20 | 2024-02-05 | 2024-02-05
Foundation | Interior Bldg | Concrete | Pour grade beam | #974706 | CON-21 | 2024-02-29 | 2024-02-29
Structure | Level 3 | Framing | Framing 3rd floor | #F79646 | FRA- | 2024-05-28 | 2024-07-26
Structure | Level 3 | Framing | Frame 3rd floor | #F79646 | FRA- | 2024-05-28 | 2024-06-07
Pre-Construction | Precon | Precon Team | Assign Project Team | #632523 | PREC-8 | 2023-09-28 | 2023-12-20
Rough-Ins | Interior Bldg | Drywall | 4.3 Rough In, Steel Stud Drywall | #F2F3B1 | DRY-1 | 2024-08-05 | 2025-01-23
Finishes | Level 2 | Flooring | 2nd floor - Taper do the rectification of deficiences | #F9503A | FLO-2 | 2024-12-23 | 2024-12-23
Foundation | Interior Bldg | Concrete | Pour Gypcrete | #A6A6A6 | GYP-1 | 2024-11-25 | 2024-11-26
Foundation | Parkade | Concrete | Pour parakde slab | #974706 | CON-22 | 2024-06-27 | 2024-07-10
Pre-Construction | Precon | Precon Team | Assign roofing and water proofing checklist | #632523 | PREC-8 | 2024-08-07 | 2024-08-07
Structure | Level 4 | Framing | Framing 4th floor | #F79646 | FRA- | 2024-06-19 | 2024-07-31
Structure | Level 4 | Framing | Frame 4th floor | #F79646 | FRA- | 2024-06-19 | 2024-07-05
Pre-Construction | Precon | Precon Team | Assign Safety Equipment and Materials checklist | #632523 | PREC-8 | 2023-09-28 | 2023-12-20
Structure | Level 3 | Framing | Layout suites on 3rd floor | #F79646 | FRA- | 2024-07-23 | 2024-07-26
Finishes | Level 2 | Flooring | 2nd floor counter top measurement for template | #F9503A | FLO-3 | 2025-01-16 | 2025-01-20
Structure | Roof | Framing | Roof trusses install | #F79646 | FRA- | 2024-07-09 | 2024-08-20
Structure | Roof | Framing | Install roof trusses and sheeting and towers | #F79646 | FRA- | 2024-07-09 | 2024-08-06
Structure | Roof | Framing | Assign roof trusses framing checklist | #F79646 | FRA- | 2024-08-07 | 2024-08-07
Finishes | Interior Bldg | Inspection | Call for Electrical and Mechanical Inspection | #C00000 | INS-4 | 2025-01-23 | 2025-01-23
Finishes | Level 2 | Flooring | 2nd floor finishing | #F9503A | FLO-4 | 2024-12-16 | 2025-02-28
Finishes | Level 3 | Flooring | 3rd floor - Taper do the rectification of deficiencies | #F9503A | FLO-2 | 2024-12-10 | 2024-12-10
Exteriors | Outside Bldg | Windows | install windows and doors | #DAE9F8 | WIN-1 | 2024-07-08 | 2024-11-26
Rough-Ins | Interior Bldg | Plumbing | Deliver tubs & showers to suites / checklist | #F7C7AC | PLU-1 | 2024-07-17 | 2024-07-18
Pre-Construction | Precon | Precon Team | Assign structural steel checklist | #632523 | PREC-8 | 2024-03-15 | 2024-03-15
Finishes | Level 3 | Flooring | 3rd floor counter top measurement for template | #F9503A | FLO- | 2025-01-08 | 2025-01-10
Rough-Ins | Interior Bldg | Vertical Flow | Install stairs | #FFF2FF | VF-1 | 2024-07-30 | 2024-07-30
Finishes | Interior Bldg | Inspection | Call for Electrical and Mechanical inspection | #C00000 | INS-4 | 2024-10-31 | 2024-10-31
Exteriors | Outside Bldg | Exteriors | Roofing and water proofing | #4BACC6 | EXT-1 | 2024-08-07 | 2024-08-23
Pre-Construction | Precon | Precon Team | Assign taping inspection checklist | #632523 | PREC-8 | 2024-12-23 | 2024-12-23
Exteriors | Outside Bldg | Exteriors | Install roofing and water proofing | #4BACC6 | EXT-2 | 2024-08-12 | 2024-08-23
Exteriors | Outside Bldg | Siding | Soffit & Tower Siding | #747474 | SID-1 | 2024-09-03 | 2025-01-03
Exteriors | Outside Bldg | Exteriors | Building paper the whole building | #4BACC6 | EXT-3 | 2024-09-03 | 2024-11-25
Finishes | Level 3 | Flooring | 3rd floor finishing | #F9503A | FLO-3 | 2024-12-02 | 2025-02-18
Pre-Construction | Precon | Precon Team | Assign taping inspection checklist | #632523 | PREC-8 | 2024-10-07 | 2024-10-07
Exteriors | Outside Bldg | Siding | Siding towers | #747474 | SID-2 | 2024-11-27 | 2024-12-16
Rough-Ins | Interior Bldg | Vertical Flow | Delivery of Elevator & Install | #FFF2FF | VF-2 | 2024-10-14 | 2025-01-03
Foundation | Parkade | Concrete | Pour parkade floor | #974706 | CON-22 | 2024-07-09 | 2024-07-10
Foundation | Interior Bldg | Concrete | Rebar exterior sidewalks | #974706 | CON-23 | 2024-12-09 | 2024-12-11
Sitework | Site | Site Sub | Form exterior pads | #8064A2 | SIT-3 | 2024-08-28 | 2024-09-03
Foundation | Interior Bldg | Concrete | Survey for balcony piles | #974706 | CON-24 | 2023-12-21 | 2023-12-22
Pre-Construction | Precon | Precon Team | Assign taping inspection checklist | #632523 | PREC-8 | 2024-12-19 | 2024-12-19
Foundation | Interior Bldg | Concrete | Survey offsets, and footings | #974706 | CON-25 | 2024-01-17 | 2024-01-17
Sitework | Site | Site Sub | Excatae exterior sidewalks | #8064A2 | SIT-4 | 2024-09-11 | 2024-12-03
Sitework | Site | Site Sub | Form exterior sidewalks | #8064A2 | SIT-5 | 2024-12-04 | 2024-12-06
Foundation | Interior Bldg | Concrete | Tie footing rebar | #974706 | CON-26 | 2024-01-25 | 2024-01-31
Foundation | Interior Bldg | Concrete | Tie Grade beam rebar | #974706 | CON-27 | 2024-02-16 | 2024-02-26
Foundation | Parkade | Concrete | Tie parkade rebar | #974706 | CON-28 | 2024-07-03 | 2024-07-05
Finishes | Level 2 | Cleaning | Construction clean 2nd floor | #4F81BD | CL-1 | 2025-02-24 | 2025-02-27
Finishes | Level 1 | Cleaning | Construction clean on 1 | #4F81BD | CL-1 | 2025-02-14 | 2025-02-18
Finishes | Level 3 | Cleaning | Construction clean on 3rd | #4F81BD | CL-1 | 2025-02-11 | 2025-02-17
Finishes | Level 4 | Cleaning | Construction clean on 4th | #4F81BD | CL-1 | 2025-02-03 | 2025-02-07
Finishes | Interior Bldg | Cleaning | Final suite clean | #4F81BD | CL-2 | 2025-02-27 | 2025-02-28
Finishes | Level 1 | Cleaning | Final suite clean on 1 | #4F81BD | CL-2 | 2025-02-20 | 2025-02-24
Finishes | Level 3 | Cleaning | Final suite clean on 3rd | #4F81BD | CL-2 | 2025-02-17 | 2025-02-18
Finishes | Level 4 | Cleaning | Final suite clean on 4th | #4F81BD | CL-2 | 2025-02-07 | 2025-02-10
Finishes | Level 2 | CX | Assign Unit Commissioning Inspection list 2nd floor | #000000 | CX- | 2025-02-27 | 2025-02-27
Finishes | Level 1 | CX | Assign Unit Commissioning Inspection list on 1 | #000000 | CX- | 2025-02-19 | 2025-02-19
Finishes | Level 3 | CX | Assign Unit Commissioning Inspection list on 3rd | #000000 | CX- | 2025-02-17 | 2025-02-17
Finishes | Level 4 | Flooring | 4th floor - Taper do the rectification of deficiencies | #F9503A | FLO-2 | 2024-12-02 | 2024-12-03
Finishes | Level 4 | Flooring | 4th floor counter top measurements for template | #F9503A | FLO-4 | 2024-12-17 | 2024-12-19
Finishes | Level 3 | Flooring | Core floor beings at 3rd floor | #F9503A | FLO-5 | 2024-07-29 | 2024-07-31
Finishes | Interior Bldg | Inspection | Call for envelope reviewer inspection | #C00000 | INS-5 | 2024-11-26 | 2024-11-26
Rough-Ins | Interior Bldg | Drywall | Assign Corridor & Stairwell pre board inspection checklist | #F2F3B1 | DRY-2 | 2024-11-28 | 2024-11-28
Rough-Ins | Interior Bldg | Drywall | Assign corridor & stairwell pre board inspection checklist | #F2F3B1 | DRY-2 | 2024-11-12 | 2024-11-12
Rough-Ins | Interior Bldg | Drywall | Assign Corridor & Stairwell pre board inspection checklist | #F2F3B1 | DRY-2 | 2024-11-08 | 2024-11-08
Rough-Ins | Interior Bldg | Drywall | Assign pre board inspection check list | #F2F3B1 | DRY-3 | 2024-11-28 | 2024-11-28
Rough-Ins | Interior Bldg | Drywall | Assign pre board inspection check list | #F2F3B1 | DRY-3 | 2024-11-15 | 2024-11-15
Rough-Ins | Interior Bldg | Drywall | Assign pre board inspection checklist | #F2F3B1 | DRY-3 | 2025-01-22 | 2025-01-22
Rough-Ins | Interior Bldg | Drywall | Assign pre board inspection checklist | #F2F3B1 | DRY-3 | 2025-01-22 | 2025-01-22
Rough-Ins | Interior Bldg | Drywall | Assign pre board interior walls checklist | #F2F3B1 | DRY-3 | 2024-11-28 | 2024-11-28
Rough-Ins | Interior Bldg | Drywall | Assign pre board interior walls checklist | #F2F3B1 | DRY-3 | 2024-11-15 | 2024-11-15
Rough-Ins | Interior Bldg | Drywall | Assign pre board interior walls checklist | #F2F3B1 | DRY-3 | 2024-11-08 | 2024-11-08
Exteriors | Outside Bldg | Siding | Assign siding checklist | #747474 | SID-3 | 2024-12-24 | 2024-12-24
Exteriors | Outside Bldg | Siding | Assign siding checklist | #747474 | SID-3 | 2024-12-10 | 2024-12-10
Exteriors | Outside Bldg | Siding | Assign siding checklist | #747474 | SID-3 | 2024-11-22 | 2024-11-22
Exteriors | Outside Bldg | Siding | Assign siding checklist | #747474 | SID-3 | 2024-11-06 | 2024-11-06
Pre-Construction | Precon | Precon Team | Assign taping inspection checklist | #632523 | PREC-8 | 2024-12-05 | 2024-12-05
Pre-Construction | Precon | Precon Team | Assign taping inspection checklist | #632523 | PREC-8 | 2024-11-15 | 2024-11-15
Pre-Construction | Precon | Precon Team | Assign taping inspection checklist | #632523 | PREC-8 | 2024-11-28 | 2024-11-28
Pre-Construction | Precon | Precon Team | Assign taping inspection checklist for suites | #632523 | PREC-8 | 2024-12-19 | 2024-12-19
Pre-Construction | Precon | Precon Team | Assign taping inspection checklist for suites | #632523 | PREC-8 | 2024-12-05 | 2024-12-05
Pre-Construction | Precon | Precon Team | Assign tower siding checklist | #632523 | PREC-8 | 2024-11-26 | 2024-11-26
Pre-Construction | Precon | Precon Team | Assign water and sewer and storm checklist | #632523 | PREC-8 | 2024-03-15 | 2024-03-15
Pre-Construction | Precon | Precon Team | Assign window & door installation checklist | #632523 | PREC-8 | 2024-07-08 | 2024-07-08
Structure | Level 2 | Framing | Back framing on 2nd | #F79646 | FRA-1 | 2024-08-21 | 2024-08-27
Structure | Level 3 | Framing | Back framing on 3rd | #F79646 | FRA-1 | 2024-09-10 | 2024-09-16
Structure | Level 4 | Framing | Back framing on 4th | #F79646 | FRA-1 | 2024-09-23 | 2024-09-27
Rough-Ins | Level 2 | Drywall | Board 2nd floor hallways and stairwells | #F2F3B1 | DRY-4 | 2024-11-28 | 2024-12-04
Rough-Ins | Level 2 | Drywall | Board 2nd floor walls | #F2F3B1 | DRY-4 | 2024-11-28 | 2024-12-04
Rough-Ins | Interior Bldg | Drywall | Board and prepare electrical/mechanical room | #F2F3B1 | DRY-4 | 2024-12-06 | 2024-12-10
Exteriors | Level 2 | Exteriors | Board exterior walls on 2nd and sheds | #4BACC6 | EXT-4 | 2024-11-28 | 2024-12-04
Exteriors | Parkade | Exteriors | Board parkade exterior walls and sheds | #4BACC6 | EXT-5 | 2024-12-09 | 2024-12-09
Exteriors | Parkade | Exteriors | Board Parkade interior walls | #4BACC6 | EXT-6 | 2024-12-10 | 2024-12-13
Rough-Ins | Level 3 | Drywall | Board upper 16" strips in common area & all suites on 3rd | #F2F3B1 | DRY-4 | 2024-09-11 | 2024-09-16
Rough-Ins | Level 2 | Drywall | Board upper 16" strips in common area and all suites on 2nd | #F2F3B1 | DRY-4 | 2024-08-30 | 2024-09-04
Rough-Ins | Level 4 | Drywall | Board upper 16" strips in common area and all suites on 4th | #F2F3B1 | DRY-4 | 2024-09-27 | 2024-10-02
Rough-Ins | Level 2 | Drywall | Fire tape / Fire caulk upper strips on 2nd | #F2F3B1 | DRY-5 | 2024-11-25 | 2024-11-25
Rough-Ins | Level 3 | Drywall | Fire tape / Fire caulk upper strips on 3rd | #F2F3B1 | DRY-5 | 2024-11-11 | 2024-11-11
Rough-Ins | Level 4 | Drywall | Fire tape / Fire caulk upper strips on 4th | #F2F3B1 | DRY-5 | 2024-11-01 | 2024-11-01
Structure | Parkade | Framing | Frame and board Parkade beams | #F79646 | FRA-2 | 2024-12-16 | 2024-12-20
Structure | Level 2 | Framing | Frame drops on 2nd | #F79646 | FRA-3 | 2024-11-26 | 2024-12-02
Structure | Level 3 | Framing | Frame drops on 3rd | #F79646 | FRA-3 | 2024-11-12 | 2024-11-18
Structure | Level 4 | Framing | Frame drops on 4th | #F79646 | FRA-3 | 2024-11-29 | 2024-12-05
Structure | Parkade | Framing | Frame interior parkade walls | #F79646 | FRA-4 | 2024-08-19 | 2024-08-23
Rough-Ins | Level 4 | Drywall | Install drywall on 4th floor ceiling | #F2F3B1 | DRY-6 | 2024-09-11 | 2024-09-17
Pre-Construction | Precon | Precon Team | Building close out check list | #632523 | PREC-9 | 2025-03-04 | 2025-03-04
Rough-Ins | Interior Bldg | Gypcrete | Gypcrete | #A6A6A6 | GYP-1 | 2024-11-25 | 2024-11-26
Foundation | Interior Bldg | Concrete | Tie rebar exterior pads | #974706 | CON-29 | 2024-09-04 | 2024-09-06
Finishes | Level 4 | Flooring | Core floor beings at 4th floor | #F9503A | FLO-5 | 2024-08-01 | 2024-08-02
Finishes | Level 2 | Flooring | Core floors begin at 2nd | #F9503A | FLO-5 | 2024-07-24 | 2024-07-26
Finishes | Level 2 | Carpentry | Install cabinets 2nd floor | #964100 | CAR-6 | 2025-01-13 | 2025-01-17
Finishes | Level 4 | Flooring | Install fascia and soffit 4th floor | #F9503A | FLO-6 | 2024-11-15 | 2024-11-25
Rough-Ins | Level 2 | Drywall | Layout suites on 2nd floor | #F2F3B1 | DRY-7 | 2024-07-18 | 2024-07-22
Finishes | Interior Bldg | Finishing | 4.4 Finishing | #4EB8A4 | FIN-1 | 2024-08-09 | 2025-05-05
Finishes | Level 2 | Flooring | Install flooring 2nd floor | #F9503A | FLO-7 | 2025-01-08 | 2025-01-16
Pre-Construction | Precon | Precon Team | Building handover (PM to SM) checklist | #632523 | PREC-10 | 2025-03-04 | 2025-03-10
Exteriors | Outside Bldg | Exteriors | Blow in attic insulation | #4BACC6 | EXT-7 | 2024-09-18 | 2024-09-20
Finishes | Interior Bldg | Inspection | Call for Mechanical & Electrical inspection of attic | #C00000 | INS-6 | 2024-09-04 | 2024-09-04
Finishes | Interior Bldg | Inspection | Call for Mechanical and Electrical inspection | #C00000 | INS-6 | 2024-11-25 | 2024-11-25
Finishes | Interior Bldg | Inspection | Call for Mechanical and Electrical Inspection | #C00000 | INS-6 | 2024-11-12 | 2024-11-12
Finishes | Interior Bldg | Inspection | Call for structural inspection | #C00000 | INS-7 | 2024-08-20 | 2024-08-20
Finishes | Interior Bldg | Inspection | Contact Canada Post to get the address's created | #C00000 | INS-8 | 2025-02-14 | 2025-02-14
Sitework | Site | Site Sub | Call the surveyor to measure for condo plan | #8064A2 | SIT-6 | 2024-10-29 | 2024-10-31
Finishes | Level 1 | Finishing | Ceiling texture on 1 | #4EB8A4 | FIN-2 | 2025-01-02 | 2025-01-03
Finishes | Level 2 | Finishing | Ceiling texture on 2nd | #4EB8A4 | FIN-2 | 2024-12-16 | 2024-12-17
Finishes | Level 3 | Finishing | Ceiling texture on 3rd | #4EB8A4 | FIN-2 | 2024-12-02 | 2024-12-03
Finishes | Level 4 | Finishing | Ceiling texture on 4th | #4EB8A4 | FIN-2 | 2024-11-26 | 2024-11-27
Rough-Ins | Level 2 | Electrical | Electrical finishing 2nd floor | #ECD76A | ELE-2 | 2025-02-07 | 2025-02-13
Rough-Ins | Level 1 | Electrical | Electrical finishing on 1 | #ECD76A | ELE-2 | 2025-02-11 | 2025-02-13
Rough-Ins | Level 3 | Electrical | Electrical finishing on 3rd | #ECD76A | ELE-2 | 2025-01-29 | 2025-02-04
Rough-Ins | Level 4 | Electrical | Electrical finishing on 4th | #ECD76A | ELE-2 | 2025-01-21 | 2025-01-27
Rough-Ins | Level 2 | Electrical | Electrical rough in hallways & stairwells on 2nd | #ECD76A | ELE-3 | 2024-11-08 | 2024-11-22
Rough-Ins | Level 3 | Electrical | Electrical rough in hallways & stairwells on 3rd | #ECD76A | ELE-3 | 2024-10-28 | 2024-11-08
Rough-Ins | Level 4 | Electrical | Electrical rough in hallways stairwells on 4th | #ECD76A | ELE-3 | 2024-10-21 | 2024-10-31
Rough-Ins | Interior Bldg | Electrical | Electrical rough in in ceiling | #ECD76A | ELE-3 | 2024-08-26 | 2024-09-03
Rough-Ins | Level 2 | Electrical | Electrical rough in on 2nd | #ECD76A | ELE-3 | 2024-11-08 | 2024-11-22
Rough-Ins | Level 3 | Electrical | Electrical rough in on 3rd | #ECD76A | ELE-3 | 2024-10-28 | 2024-11-08
Rough-Ins | Level 4 | Electrical | Electrical rough in on 4th | #ECD76A | ELE-3 | 2024-10-21 | 2024-10-31
Finishes | Interior Bldg | Paint | Final coat of paint | #59F3FF | PAI-2 | 2025-02-13 | 2025-02-25
Finishes | Interior Bldg | Paint | Final coat of paint | #59F3FF | PAI-2 | 2025-02-03 | 2025-02-13
Finishes | Interior Bldg | Paint | Final coat of paint | #59F3FF | PAI-2 | 2025-01-24 | 2025-02-05
Finishes | Level 4 | Finishing | finishing on 4th | #4EB8A4 | FIN-3 | 2024-11-26 | 2025-02-10
Finishes | Level 1 | Finishing | finishing parkade level 1 | #4EB8A4 | FIN-3 | 2025-01-02 | 2025-02-24
Finishes | Level 2 | Carpentry | Install base and hardware 2nd floor | #964100 | CAR-1 | 2025-01-17 | 2025-01-24
Finishes | Level 3 | Carpentry | Install base and hardware on 3rd | #964100 | CAR-1 | 2025-01-08 | 2025-01-13
Finishes | Level 4 | Carpentry | Install base and hardware on 4th | #964100 | CAR-1 | 2024-12-20 | 2025-01-03
Finishes | Level 1 | Flooring | Install flooring on 1 | #F9503A | FLO-7 | 2025-01-15 | 2025-01-16
Finishes | Level 1 | Carpentry | Install cabinets on 1 | #964100 | CAR-2 | 2025-01-17 | 2025-01-20
Finishes | Level 3 | Carpentry | Install cabinets on 3rd | #964100 | CAR-2 | 2024-12-18 | 2025-01-10
Finishes | Level 4 | Carpentry | Install cabinets on 4th | #964100 | CAR-2 | 2024-12-11 | 2024-12-18
Finishes | Level 1 | Carpentry | Install countertops on 1 | #964100 | CAR-3 | 2025-02-10 | 2025-02-10
Finishes | Level 3 | Flooring | Install flooring on 3rd | #F9503A | FLO-7 | 2024-12-17 | 2025-01-07
Finishes | Level 4 | Flooring | Install flooring on 4th | #F9503A | FLO-7 | 2024-12-09 | 2024-12-16
Finishes | Interior Bldg | Flooring | Install railings on all floors | #F9503A | FLO-8 | 2025-01-20 | 2025-02-06
Finishes | Level 4 | Flooring | Install sound bar 4th floor | #F9503A | FLO-9 | 2024-09-09 | 2024-09-10
Finishes | Level 1 | Carpentry | Install interior doors and case on 1 | #964100 | CAR-4 | 2025-01-08 | 2025-01-09
Finishes | Level 2 | Carpentry | Install interior doors and case on 2nd | #964100 | CAR-4 | 2024-12-23 | 2025-01-03
Finishes | Level 3 | Carpentry | Install interior doors and case on 3rd | #964100 | CAR-4 | 2024-12-09 | 2024-12-13
Finishes | Level 4 | Carpentry | Install interior doors and case on 4th | #964100 | CAR-4 | 2024-12-02 | 2024-12-06
Structure | Interior Bldg | Framing | Install metal doors and frames | #F79646 | FRA-5 | 2024-12-24 | 2025-01-06
Structure | Interior Bldg | Framing | Install pocket door frames | #F79646 | FRA-6 | 2024-09-06 | 2024-09-12
Structure | Interior Bldg | Framing | Install pocket door frames | #F79646 | FRA-6 | 2024-09-20 | 2024-09-26
Structure | Interior Bldg | Framing | Install pocket foor frame | #F79646 | FRA-6 | 2024-08-28 | 2024-09-03
Finishes | Interior Bldg | Flooring | Install windows & doors all floors | #F9503A | FLO-10 | 2024-08-01 | 2024-08-13
Structure | Level 1 | Framing | Install suite entry doors and frames and Interior doors, trims and jambs | #F79646 | FRA-7 | 2024-12-23 | 2025-01-03
Structure | Level 1 | Framing | Install suite entry doors and frames and Interior doors, trims and jambs | #F79646 | FRA-7 | 2024-12-09 | 2024-12-13
Structure | Level 1 | Framing | Install suite entry doors and frames and Interior doors, trims and jambs | #F79646 | FRA-7 | 2024-12-02 | 2024-12-06
Rough-Ins | Interior Bldg | Plumbing | Install tubs and showers | #F7C7AC | PLU-2 | 2024-08-30 | 2024-09-04
Rough-Ins | Interior Bldg | Plumbing | Install tubs and showers | #F7C7AC | PLU-2 | 2024-09-06 | 2024-09-11
Rough-Ins | Interior Bldg | Plumbing | Install tubs and showers | #F7C7AC | PLU-2 | 2024-09-26 | 2024-09-27
Rough-Ins | Level 3 | Drywall | Load boards on floor and Board 3rd floor walls | #F2F3B1 | DRY-8 | 2024-11-15 | 2024-11-22
Rough-Ins | Level 3 | Drywall | Load boards on floor and Board exterior walls on 3rd and sheds | #F2F3B1 | DRY-8 | 2024-11-15 | 2024-11-22
Rough-Ins | Level 3 | Drywall | Load the board on floor and Board 3rd floor hallways and stairwells | #F2F3B1 | DRY-8 | 2024-11-15 | 2024-11-22
Rough-Ins | Level 4 | Drywall | Load the board on floor and Board 4th floor hallways and stairwells | #F2F3B1 | DRY-8 | 2024-11-08 | 2024-11-15
Rough-Ins | Level 4 | Drywall | Load the board on floor and Board 4th floor walls | #F2F3B1 | DRY-8 | 2024-11-08 | 2024-11-15
Rough-Ins | Level 4 | Drywall | Load the board on floor and Board exterior walls on 4th and sheds | #F2F3B1 | DRY-8 | 2024-11-08 | 2024-11-15
Rough-Ins | Interior Bldg | Electrical | Main service electrical room install | #ECD76A | ELE-4 | 2024-11-28 | 2024-12-26
Rough-Ins | Interior Bldg | Mechanical | Main service mechanical room install | #4D93D9 | MCH-2 | 2024-11-28 | 2025-01-22
Finishes | Level 2 | Carpentry | Manufacturing and Install countertops 2nd floor | #964100 | CAR-5 | 2025-01-21 | 2025-02-07
Finishes | Level 3 | Carpentry | Manufacturing and Install countertops on 3rd | #964100 | CAR-5 | 2025-01-10 | 2025-01-29
Finishes | Level 4 | Carpentry | manufacturing and Install countertops on 4th | #964100 | CAR-5 | 2025-01-02 | 2025-01-21
Rough-Ins | Level 2 | Mechanical | Mechanical finishing 2nd floor | #4D93D9 | MCH-3 | 2025-02-07 | 2025-02-13
Rough-Ins | Level 1 | Mechanical | Mechanical finishing on 1 | #4D93D9 | MCH-3 | 2025-02-11 | 2025-02-13
Rough-Ins | Level 3 | Mechanical | Mechanical finishing on 3rd | #4D93D9 | MCH-3 | 2025-01-29 | 2025-02-04
Rough-Ins | Level 4 | Mechanical | Mechanical finishing on 4th | #4D93D9 | MCH-3 | 2025-01-21 | 2025-01-27
Rough-Ins | Level 2 | Mechanical | Mechanical rough in hallways & stairwells on 2nd | #4D93D9 | MCH-4 | 2024-11-01 | 2024-11-15
Rough-Ins | Level 3 | Mechanical | Mechanical rough in hallways & stairwells on 3rd | #4D93D9 | MCH-4 | 2024-10-28 | 2024-11-07
Rough-Ins | Level 4 | Mechanical | Mechanical rough in hallways stairwells on 4th | #4D93D9 | MCH-4 | 2024-10-21 | 2024-10-25
Rough-Ins | Interior Bldg | Mechanical | Mechanical rough in in ceiling | #4D93D9 | MCH-4 | 2024-08-05 | 2024-08-14
Rough-Ins | Level 2 | Mechanical | Mechanical rough in on 2nd | #4D93D9 | MCH-4 | 2024-11-01 | 2024-11-15
Rough-Ins | Level 3 | Mechanical | Mechanical rough in on 3rd | #4D93D9 | MCH-4 | 2024-10-28 | 2024-11-07
Rough-Ins | Level 4 | Mechanical | Mechanical rough in on 4th | #4D93D9 | MCH-4 | 2024-10-21 | 2024-10-25
Finishes | Level 1 | Paint | Paint 1rst coat of color on 1 | #59F3FF | PAI-3 | 2025-01-10 | 2025-01-16
Finishes | Level 2 | Paint | Paint 1st coat of color 2nd floor | #59F3FF | PAI-3 | 2024-12-27 | 2025-01-03
Finishes | Level 3 | Paint | Paint 1st coat of color on 3rd | #59F3FF | PAI-3 | 2024-12-12 | 2024-12-17
Finishes | Level 4 | Paint | Paint 1st coat of color on 4th | #59F3FF | PAI-3 | 2024-12-05 | 2024-12-10
Sitework | Parkade | Site Sub | Parkade - Measurement for template | #8064A2 | SIT-7 | 2025-01-21 | 2025-01-21
Sitework | Parkade | Site Sub | Parkade - Taper to rectify deficiencies | #8064A2 | SIT-8 | 2025-01-07 | 2025-01-07
Finishes | Level 4 | Flooring | Layout suites 4th floor | #F9503A | FLO-11 | 2024-07-29 | 2024-08-01
Exteriors | Level 2 | Insulation | Poly and insulate on 2nd exterior walls | #E9F132 | INSU-1 | 2024-11-25 | 2024-11-28
Exteriors | Level 3 | Insulation | Poly and insulate on 3rd exterior walls | #E9F132 | INSU-1 | 2024-11-12 | 2024-11-15
Exteriors | Level 4 | Insulation | Poly and insulate on 4th exterior walls | #E9F132 | INSU-1 | 2024-11-05 | 2024-11-07
Exteriors | Parkade | Insulation | Poly and insulate parkade exterior walls | #E9F132 | INSU-2 | 2024-08-22 | 2024-08-23
Finishes | Level 1 | Paint | Prime paint on 1 | #59F3FF | PAI-4 | 2025-01-03 | 2025-01-07
Finishes | Level 2 | Paint | Prime paint on 2nd | #59F3FF | PAI-4 | 2024-12-18 | 2024-12-23
Finishes | Level 3 | Paint | Prime paint on 3rd | #59F3FF | PAI-4 | 2024-12-05 | 2024-12-10
Finishes | Level 4 | Paint | Prime paint on 4th | #59F3FF | PAI-4 | 2024-11-28 | 2024-12-03
Finishes | Level 2 | Rough-In (General) | Rough in 2nd floor | #948A54 | RI-1 | 2024-08-12 | 2025-01-03
Finishes | Level 3 | Rough-In (General) | Rough in 3rd floor | #948A54 | RI-1 | 2024-08-19 | 2024-12-13
Finishes | Level 4 | Rough-In (General) | Rough in 4th floor | #948A54 | RI-1 | 2024-08-19 | 2024-12-06
Finishes | Level 4 | Rough-In (General) | Rough in 4th floor ceiling | #948A54 | RI-1 | 2024-08-05 | 2024-10-07
Exteriors | Parkade | Rough-In (General) | Rough in exterior walls - parkade and sheds | #948A54 | RI-2 | 2024-11-18 | 2024-12-06
Exteriors | Level 2 | Rough-In (General) | Rough in exterior walls on 2nd and sheds | #948A54 | RI-2 | 2024-11-08 | 2024-11-21
Exteriors | Level 3 | Rough-In (General) | Rough in exterior walls on 3rd and sheds | #948A54 | RI-2 | 2024-10-28 | 2024-11-08
Rough-Ins | Level 4 | Rough-In (General) | Rough in exterior walls on 4th and sheds | #948A54 | RI-2 | 2024-10-21 | 2024-10-31
Rough-Ins | Interior Bldg | Rough-In (General) | Rough in interior walls | #948A54 | RI-3 | 2024-11-21 | 2024-12-04
Exteriors | Parkade | Rough-In (General) | Rough in Parkade | #948A54 | RI-4 | 2024-08-19 | 2025-01-23
Exteriors | Level 2 | Siding | Siding 2nd floor | #747474 | SID-4 | 2024-11-22 | 2024-12-09
Exteriors | Level 3 | Siding | Siding 3rd floor | #747474 | SID-4 | 2024-11-06 | 2024-11-21
Exteriors | Level 4 | Siding | Siding 4th floor | #747474 | SID-4 | 2024-10-21 | 2024-11-05
Exteriors | Parkade | Siding | Siding parkade level | #747474 | SID-4 | 2024-12-10 | 2024-12-23
Finishes | Level 1 | Carpentry | Spray out closet interiors and trim on 1 | #964100 | CAR-6 | 2025-01-10 | 2025-01-10
Finishes | Level 3 | Carpentry | Spray out closet interiors and trim on 3rd | #964100 | CAR-6 | 2024-12-12 | 2024-12-17
Finishes | Level 4 | Carpentry | Spray out closet interiors and trim on 4th | #964100 | CAR-6 | 2024-12-05 | 2024-12-10
Rough-Ins | Level 2 | Sprinkler | Sprinkler finishing 2nd floor | #B5E6A2 | SPR-1 | 2025-02-07 | 2025-02-13
Rough-Ins | Level 1 | Sprinkler | Sprinkler finishing on 1 | #B5E6A2 | SPR-1 | 2025-02-11 | 2025-02-13
Rough-Ins | Level 3 | Sprinkler | Sprinkler finishing on 3rd | #B5E6A2 | SPR-1 | 2025-01-29 | 2025-02-04
Rough-Ins | Level 4 | Sprinkler | Sprinkler finishing on 4th | #B5E6A2 | SPR-1 | 2025-01-21 | 2025-01-27
Rough-Ins | Interior Bldg | Sprinkler | Sprinkler install in attic | #B5E6A2 | SPR-2 | 2024-08-07 | 2024-08-21
Rough-Ins | Level 2 | Sprinkler | Sprinkler rough in corridor & stairwells on 2nd | #B5E6A2 | SPR-3 | 2024-08-26 | 2024-09-06
Rough-Ins | Level 3 | Sprinkler | Sprinkler rough in hallways & stairwells on 3rd | #B5E6A2 | SPR-3 | 2024-09-09 | 2024-09-20
Finishes | Level 4 | CX | Assign Unit Commissioning Inspection list on 4th | #000000 | CX- | 2025-02-07 | 2025-02-07
Rough-Ins | Level 4 | Sprinkler | Sprinkler rough in hallways stairwells on 4th | #B5E6A2 | SPR-3 | 2024-09-23 | 2024-09-30
Rough-Ins | Level 2 | Sprinkler | Sprinkler rough in on 2nd | #B5E6A2 | SPR-3 | 2024-08-26 | 2024-09-06
Rough-Ins | Level 3 | Sprinkler | Sprinkler rough in on 3rd | #B5E6A2 | SPR-3 | 2024-09-09 | 2024-09-20
Rough-Ins | Level 4 | Sprinkler | Sprinkler rough in on 4th | #B5E6A2 | SPR-3 | 2024-09-23 | 2024-09-30
Rough-Ins | Level 2 | Drywall | Steel stud install on 2nd & drywall behind the tubs including fire wall taping if it is a fire wall | #F2F3B1 | DRY-9 | 2024-08-12 | 2024-08-29
Rough-Ins | Level 3 | Drywall | Steel stud install on 3rd & drywall behind the tubs including fire wall taping if it is a fire wall | #F2F3B1 | DRY-9 | 2024-08-30 | 2024-09-05
Rough-Ins | Level 4 | Drywall | Steel stud install on 4th & drywall behind the tubs including fire wall taping if it is a fire wall | #F2F3B1 | DRY-9 | 2024-09-18 | 2024-09-26
Finishes | Level 2 | Drywall | Tape 2nd floor hallways and stair wells | #F2F3B1 | DRY-11 | 2024-12-05 | 2024-12-19
Finishes | Level 3 | Drywall | Tape 3rd floor hallways and stair wells | #F2F3B1 | DRY-11 | 2024-11-22 | 2024-12-05
Finishes | Level 4 | Drywall | Tape 4th floor ceiling | #F2F3B1 | DRY-11 | 2024-09-23 | 2024-10-04
Finishes | Level 4 | Drywall | Tape 4th floor hallways and stair wells | #F2F3B1 | DRY-11 | 2024-11-15 | 2024-11-28
Rough-Ins | Parkade | Drywall | Tape parkade interior and exterior walls | #F2F3B1 | DRY-10 | 2024-12-13 | 2024-12-23
Rough-Ins | Level 2 | Drywall | Tape suites on 2nd | #F2F3B1 | DRY-10 | 2024-12-05 | 2024-12-19
Rough-Ins | Level 3 | Drywall | Tape suites on 3rd | #F2F3B1 | DRY-10 | 2024-11-22 | 2024-12-05
Rough-Ins | Level 4 | Drywall | Tape suites on 4th | #F2F3B1 | DRY-10 | 2024-11-15 | 2024-11-28
Finishes | Level 2 | Plumbing | Water dams 2nd floor | #F7C7AC | PLU-3 | 2024-08-19 | 2024-08-23
Finishes | Level 3 | Plumbing | Water dams 3rd floor | #F7C7AC | PLU-3 | 2024-08-19 | 2024-08-23
Finishes | Level 4 | Plumbing | Water dams 4th floor | #F7C7AC | PLU-3 | 2024-08-19 | 2024-08-23
Exteriors | Outside Bldg | Exteriors | Exterior | #4BACC6 | EXT-8 | 2024-08-09 | 2025-05-05
Exteriors | Outside Bldg | Exteriors | Grind all balconys smooth | #4BACC6 | EXT-9 | 2024-08-09 | 2024-08-22
Finishes | Interior Bldg | Exteriors | Install exterior decking all floors | #4BACC6 | EXT-11 | 2024-09-03 | 2024-09-16
Pre-Construction | Precon | Precon Team | De mobilization (checklist) | #632523 | PREC-11 | 2025-03-05 | 2025-03-11
Finishes | Level 4 | Flooring | Poly 4th floor ceiling | #F9503A | FLO-12 | 2024-09-05 | 2024-09-06
Sitework | Landscaping | Site Sub | Rough grade landscaping | #8064A2 | SIT-9 | 2025-04-04 | 2025-04-10
Rough-Ins | Interior Bldg | Sprinkler | Install underground sprinklers | #B5E6A2 | SPR-4 | 2025-04-11 | 2025-04-17
Sitework | Landscaping | Site Sub | Install landscaping | #8064A2 | SIT-10 | 2025-04-18 | 2025-05-01
Finishes | Interior Bldg | CX | Commision landscaping | #000000 | CX- | 2025-05-02 | 2025-05-05
Sitework | Landscaping | Site Sub | Install building signage | #8064A2 | SIT-11 | 2025-02-28 | 2025-02-28
Pre-Construction | Precon | Precon Team | Hold Pre Kick-Off meeting with Engineers and Trades people | #632523 | PREC-12 | 2023-09-28 | 2023-10-02
Finishes | Interior Bldg | CX | Final commissioning and deficiency | #000000 | CX- | 2025-02-14 | 2025-03-03
Finishes | Interior Bldg | Inspection | Enginering walk throughs | #C00000 | INS-9 | 2025-02-19 | 2025-02-20
Finishes | Interior Bldg | Inspection | Fire alarm verification | #C00000 | INS-10 | 2025-02-14 | 2025-02-17
Foundation | Interior Bldg | Inspection | Geo Tech Engineer inspection | #C00000 | INS-11 | 2024-01-18 | 2024-01-18
Exteriors | Level 3 | Exteriors | Organize 3rd party building exterior review, including roof, siding and flashings | #4BACC6 | EXT-10 | 2025-02-19 | 2025-02-19
Foundation | Interior Bldg | Inspection | Rebar Inspection Structural Engineer | #C00000 | INS-12 | 2024-02-01 | 2024-02-01
Foundation | Interior Bldg | Inspection | Rebar inspection Structural Engineer | #C00000 | INS-12 | 2024-02-28 | 2024-02-28
Finishes | Interior Bldg | Inspection | Sprinkler testing | #C00000 | INS-13 | 2025-02-14 | 2025-02-17
Finishes | Interior Bldg | CX | Elevator commissioning | #000000 | CX- | 2025-02-14 | 2025-02-17
Finishes | Interior Bldg | COO | Prepare occupancy paperwork | #D9D9D9 | COO-1 | 2025-02-25 | 2025-02-26
Finishes | Interior Bldg | COO | Receive occupancy | #D9D9D9 | COO-2 | 2025-02-27 | 2025-02-28
Finishes | Interior Bldg | COO | Move in dates confirmed | #D9D9D9 | COO-3 | 2025-03-03 | 2025-03-03
Pre-Construction | Precon | Precon Team | Order Rebar (30 days before site delivery date required) | #632523 | PREC-13 | 2023-12-08 | 2023-12-08
Finishes | Interior Bldg | COO | 5.0 Sales, Occupancy, Closings | #D9D9D9 | COO-4 | 2025-03-03 | 2025-05-01
Finishes | Interior Bldg | COO | Pre sale move in dates confirmed | #D9D9D9 | COO-5 | 2025-03-03 | 2025-03-03
Finishes | Interior Bldg | CX | Finalize home owner extras | #000000 | CX-1 | 2025-03-04 | 2025-03-10
Finishes | Interior Bldg | CX | Load home owners into copper | #000000 | CX-2 | 2025-03-04 | 2025-03-04
Finishes | Interior Bldg | CX | Move in binders created | #000000 | CX-3 | 2025-03-04 | 2025-03-10
Finishes | Interior Bldg | CX | Update home owner permissions in Construction online | #000000 | CX-4 | 2025-03-04 | 2025-03-04
Finishes | Interior Bldg | CX | Unit Commissioning Inspection list | #000000 | CX-5 | 2025-03-04 | 2025-03-10
Finishes | Interior Bldg | Cleaning | Unit Commissioning deficiency clean up confirmed | #4F81BD | CL-3 | 2025-03-11 | 2025-03-17
Pre-Construction | Precon | Precon Team | Organize site team to have training and certificates | #632523 | PREC-14 | 2023-09-28 | 2023-09-28
Finishes | Interior Bldg | Cleaning | Building close out cleanup deficiencies confirmed | #4F81BD | CL-4 | 2025-03-05 | 2025-03-11
Pre-Construction | Precon | Precon Team | Schedule locates to be done | #632523 | PREC-15 | 2023-12-21 | 2023-12-27
Pre-Construction | Precon | Precon Team | Schedule Pile contractor | #632523 | PREC-16 | 2023-12-21 | 2023-12-21
Finishes | Interior Bldg | CX | Keys and gift cards and welcome package created | #000000 | CX-6 | 2025-03-04 | 2025-03-10
Finishes | Interior Bldg | CX | Home owner walk through and punch list | #000000 | CX-7 | 2025-03-11 | 2025-03-11
Finishes | Interior Bldg | Cleaning | Home owner walk through punch list clean up | #4F81BD | CL-5 | 2025-03-12 | 2025-03-18
Finishes | Interior Bldg | CX | New move ins and warranty through service manager | #000000 | CX-8 | 2025-03-04 | 2025-05-01
Finishes | Interior Bldg | CX | Send out contractor surveys | #000000 | CX-9 | 2025-03-05 | 2025-03-05
Finishes | Interior Bldg | CX | Schedule 1 on 1 contractor review meetings | #000000 | CX-10 | 2025-03-06 | 2025-03-12
Finishes | Interior Bldg | CX | Schedule contractor group meeting to review survey results | #000000 | CX-11 | 2025-03-06 | 2025-03-12
Finishes | Interior Bldg | CX | Project post mordem internal | #000000 | CX-12 | 2025-03-13 | 2025-03-13
Finishes | Interior Bldg | CX | Move info to Dev co work flow 1.0, 2.0, 6.0 | #000000 | CX-13 | 2025-03-18 | 2025-03-18

## CFA - Schedule
|  | 2023 | [94 empty] | 2024 | [365 empty] | 2025
|  | Sep |  |  | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [28 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May
|  | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05
phase | location | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
Mobilization | Mobilization | Sep 28: MOB-1; Sep 29: MOB-1; Sep 30: MOB-1; Oct 01: MOB-1; Oct 02: MOB-1; Oct 03: MOB-1; Oct 04: MOB-1; Oct 05: MOB-1; Oct 06: MOB-1; Oct 07: MOB-1; Oct 08: MOB-1; Oct 09: MOB-1; Oct 10: MOB-1; Oct 11: MOB-1; Oct 12: MOB-1; Oct 13: MOB-1; Oct 14: MOB-1; Oct 15: MOB-1; Oct 16: MOB-1; Oct 17: MOB-1; Oct 18: MOB-1; Oct 19: MOB-1; Oct 20: MOB-1; Oct 21: MOB-1; Oct 22: MOB-1; Oct 23: MOB-1; Oct 24: MOB-1; Oct 25: MOB-1; Oct 26: MOB-1; Oct 27: MOB-1; Oct 28: MOB-1; Oct 29: MOB-1; Oct 30: MOB-1; Oct 31: MOB-1; Nov 01: MOB-1; Nov 02: MOB-1; Nov 03: MOB-1; Nov 04: MOB-1; Nov 05: MOB-1; Nov 06: MOB-1; Nov 07: MOB-1; Nov 08: MOB-1; Nov 09: MOB-1; Nov 10: MOB-1; Nov 11: MOB-1; Nov 12: MOB-1; Nov 13: MOB-1; Nov 14: MOB-1; Nov 15: MOB-1; Nov 16: MOB-1; Nov 17: MOB-1; Nov 18: MOB-1; Nov 19: MOB-1; Nov 20: MOB-1; Nov 21: MOB-1; Nov 22: MOB-1; Nov 23: MOB-1; Nov 24: MOB-1; Nov 25: MOB-1; Nov 26: MOB-1; Nov 27: MOB-1; Nov 28: MOB-1; Nov 29: MOB-1; Nov 30: MOB-1; Dec 01: MOB-1; Dec 02: MOB-1; Dec 03: MOB-1; Dec 04: MOB-1; Dec 05: MOB-1; Dec 06: MOB-1; Dec 07: MOB-1; Dec 08: MOB-1; Dec 09: MOB-1; Dec 10: MOB-1; Dec 11: MOB-1; Dec 12: MOB-1; Dec 13: MOB-1; Dec 14: MOB-1; Dec 15: MOB-1; Dec 16: MOB-1; Dec 17: MOB-1; Dec 18: MOB-1; Dec 19: MOB-1; Dec 20: MOB-1
|  | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2
|  | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3
Foundation | Interior Bldg | Dec 21: CON-5; Dec 25: CON-14; Dec 26: CON-14; Dec 27: CON-14; Jan 05: CON-16; Jan 08: CON-8; Jan 09: CON-8; Jan 10: CON-8; Jan 11: CON-8; Jan 12: CON-8; Jan 13: CON-8; Jan 14: CON-8; Jan 15: CON-8; Jan 16: CON-8; Jan 17: CON-8; Jan 18: CON-8; Jan 19: CON-10; Jan 20: CON-10; Jan 21: CON-10; Jan 22: CON-10; Jan 23: CON-10; Jan 24: CON-10; Jan 25: CON-26; Jan 26: CON-26; Jan 27: CON-26; Jan 28: CON-26; Jan 29: CON-26; Jan 30: CON-26; Jan 31: CON-26; Feb 01: INS-12; Feb 05: CON-20; Feb 06: CON-7; Feb 15: CON-3; Feb 16: CON-27; Feb 17: CON-27; Feb 18: CON-27; Feb 19: CON-27; Feb 20: CON-27; Feb 21: CON-27; Feb 22: CON-27; Feb 23: CON-27; Feb 24: CON-27; Feb 25: CON-27; Feb 26: CON-27; Feb 27: CON-1; Feb 28: INS-12; Feb 29: CON-21; Mar 01: CON-1; Mar 04: INSU-1; Mar 05: INSU-1; Mar 06: CON-2; Mar 07: CON-2; May 27: CON-1; Jun 19: CON-4; Jul 08: CON-1; Aug 26: CON-8; Aug 27: CON-8; Sep 04: CON-29; Sep 05: CON-29; Sep 06: CON-29; Sep 10: CON-18; Nov 25: GYP-1; Nov 26: GYP-1; Dec 09: CON-23; Dec 10: CON-23; Dec 11: CON-23; Dec 12: CON-1; Dec 13: CON-1; Dec 14: CON-1; Dec 15: CON-1; Dec 16: CON-1; Dec 17: CON-19; Dec 18: CON-19; Dec 19: CON-19
[86 empty] | CON-17 | [26 empty] | CON-25 | INS-11 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | [164 empty] | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9
[86 empty] | CON-24 | CON-24 | [45 empty] | CON-11 | CON-11 | CON-11 | CON-11 | CON-11 | CON-11 | CON-11 | CON-11 | CON-11
| Level 2 | Apr 16: CON-15; Apr 17: CON-15; Apr 18: CON-15
[203 empty] | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13
| Level 3 | May 23: CON-13; May 24: CON-13; May 25: CON-13; May 26: CON-13; May 27: CON-13; May 28: CON-13
[240 empty] | CON-15 | CON-15 | CON-15 | CON-15 | CON-15 | CON-15
| Level 4 | Jun 11: CON-15; Jun 12: CON-15
[259 empty] | CON-13 | CON-13 | CON-13
| Parkade | Jan 08: CON-6; Jan 09: CON-6; Jan 10: CON-6; Jan 11: CON-6; Jan 12: CON-6; Jan 13: CON-6; Jan 14: CON-6; Jan 15: CON-6; Jan 16: CON-6; Mar 08: CON-2; Mar 09: CON-2; Mar 10: CON-2; Mar 11: CON-2; Mar 12: CON-2; Mar 13: CON-2; Mar 14: CON-2; Jun 20: CON-2; Jun 21: CON-2; Jun 22: CON-2; Jun 23: CON-2; Jun 24: CON-2; Jun 25: CON-2; Jun 26: CON-2; Jun 27: CON-22; Jun 28: CON-22; Jun 29: CON-22; Jun 30: CON-22; Jul 01: CON-22; Jul 02: CON-22; Jul 03: CON-22; Jul 04: CON-22; Jul 05: CON-22; Jul 06: CON-22; Jul 07: CON-22; Jul 08: CON-22; Jul 09: CON-22; Jul 10: CON-22
[281 empty] | CON-28 | CON-28 | CON-28 |  |  |  | CON-22 | CON-22
Pre-Construction | Precon | Sep 28: PREC-8; Dec 08: PREC-13; Dec 21: PREC-16; Jan 08: PREC-1; Feb 02: PREC-8; Mar 15: PREC-8; Apr 16: PREC-8; Apr 19: PREC-8; May 14: PREC-8; Jun 10: PREC-8; Jun 13: PREC-8; Jun 27: PREC-8; Jul 08: PREC-8; Aug 07: PREC-8; Sep 09: PREC-4; Sep 17: PREC-8; Oct 07: PREC-8; Nov 08: PREC-6; Nov 15: PREC-8; Nov 25: PREC-8; Nov 26: PREC-8; Nov 28: PREC-8; Dec 05: PREC-8; Dec 19: PREC-8; Dec 23: PREC-8; Mar 03: PREC-7; Mar 04: PREC-9; Mar 05: PREC-11; Mar 06: PREC-11; Mar 07: PREC-11; Mar 08: PREC-11; Mar 09: PREC-11; Mar 10: PREC-11; Mar 11: PREC-11; May 02: PREC-8
|  | PREC-14 | [83 empty] | PREC-15 | PREC-15 | PREC-15 | PREC-15 | PREC-15 | PREC-15 | PREC-15 | [78 empty] | PREC-8 | [114 empty] | PREC-8 | [149 empty] | PREC-8 | [13 empty] | PREC-8 | [74 empty] | PREC-10 | PREC-10 | PREC-10 | PREC-10 | PREC-10 | PREC-10 | PREC-10
|  | PREC-12 | PREC-12 | PREC-12 | PREC-12 | PREC-12
|  | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2
|  | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5
|  | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8
|  | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8
|  | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8
|  | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8
|  | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8
|  | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3 | PREC-3
Sitework | Landscaping | Feb 28: SIT-11; Apr 04: SIT-9; Apr 05: SIT-9; Apr 06: SIT-9; Apr 07: SIT-9; Apr 08: SIT-9; Apr 09: SIT-9; Apr 10: SIT-9; Apr 18: SIT-10; Apr 19: SIT-10; Apr 20: SIT-10; Apr 21: SIT-10; Apr 22: SIT-10; Apr 23: SIT-10; Apr 24: SIT-10; Apr 25: SIT-10; Apr 26: SIT-10; Apr 27: SIT-10; Apr 28: SIT-10; Apr 29: SIT-10; Apr 30: SIT-10; May 01: SIT-10
| Parkade | Jan 07: SIT-8; Jan 21: SIT-7
| Site | Dec 21: SIT-; Dec 22: SIT-; Dec 23: SIT-; Dec 24: SIT-; Dec 25: SIT-; Dec 26: SIT-; Dec 27: SIT-; Dec 28: SIT-; Dec 29: SIT-; Dec 30: SIT-; Dec 31: SIT-; Jan 01: SIT-; Jan 02: SIT-; Jan 03: SIT-; Jan 04: SIT-; Jan 05: SIT-; Mar 15: SIT-; Mar 16: SIT-; Mar 17: SIT-; Mar 18: SIT-; Mar 19: SIT-; Mar 20: SIT-; Mar 21: SIT-; Mar 22: SIT-; Mar 23: SIT-; Mar 24: SIT-; Mar 25: SIT-; Jun 28: SIT-1; Jun 29: SIT-1; Jun 30: SIT-1; Jul 01: SIT-1; Jul 02: SIT-2; Aug 28: SIT-3; Aug 29: SIT-3; Aug 30: SIT-3; Aug 31: SIT-3; Sep 01: SIT-3; Sep 02: SIT-3; Sep 03: SIT-3; Sep 11: SIT-4; Sep 12: SIT-4; Sep 13: SIT-4; Sep 14: SIT-4; Sep 15: SIT-4; Sep 16: SIT-4; Sep 17: SIT-4; Sep 18: SIT-4; Sep 19: SIT-4; Sep 20: SIT-4; Sep 21: SIT-4; Sep 22: SIT-4; Sep 23: SIT-4; Sep 24: SIT-4; Sep 25: SIT-4; Sep 26: SIT-4; Sep 27: SIT-4; Sep 28: SIT-4; Sep 29: SIT-4; Sep 30: SIT-4; Oct 01: SIT-4; Oct 02: SIT-4; Oct 03: SIT-4; Oct 04: SIT-4; Oct 05: SIT-4; Oct 06: SIT-4; Oct 07: SIT-4; Oct 08: SIT-4; Oct 09: SIT-4; Oct 10: SIT-4; Oct 11: SIT-4; Oct 12: SIT-4; Oct 13: SIT-4; Oct 14: SIT-4; Oct 15: SIT-4; Oct 16: SIT-4; Oct 17: SIT-4; Oct 18: SIT-4; Oct 19: SIT-4; Oct 20: SIT-4; Oct 21: SIT-4; Oct 22: SIT-4; Oct 23: SIT-4; Oct 24: SIT-4; Oct 25: SIT-4; Oct 26: SIT-4; Oct 27: SIT-4; Oct 28: SIT-4; Oct 29: SIT-4; Oct 30: SIT-4; Oct 31: SIT-4; Nov 01: SIT-4; Nov 02: SIT-4; Nov 03: SIT-4; Nov 04: SIT-4; Nov 05: SIT-4; Nov 06: SIT-4; Nov 07: SIT-4; Nov 08: SIT-4; Nov 09: SIT-4; Nov 10: SIT-4; Nov 11: SIT-4; Nov 12: SIT-4; Nov 13: SIT-4; Nov 14: SIT-4; Nov 15: SIT-4; Nov 16: SIT-4; Nov 17: SIT-4; Nov 18: SIT-4; Nov 19: SIT-4; Nov 20: SIT-4; Nov 21: SIT-4; Nov 22: SIT-4; Nov 23: SIT-4; Nov 24: SIT-4; Nov 25: SIT-4; Nov 26: SIT-4; Nov 27: SIT-4; Nov 28: SIT-4; Nov 29: SIT-4; Nov 30: SIT-4; Dec 01: SIT-4; Dec 02: SIT-4; Dec 03: SIT-4; Dec 04: SIT-5; Dec 05: SIT-5; Dec 06: SIT-5
[86 empty] | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | [217 empty] | SIT-6 | SIT-6 | SIT-6
[93 empty] | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | [73 empty] | SIT-
[174 empty] | SIT- | SIT- | SIT- | SIT- | SIT-
Structure | Interior Bldg | Mar 15: STL-1; Mar 16: STL-1; Mar 17: STL-1; Mar 18: STL-1; Mar 19: STL-1; Mar 20: STL-1; Mar 21: STL-1; Apr 11: FRA-; Apr 12: FRA-; Apr 13: FRA-; Apr 14: FRA-; Apr 15: FRA-; Apr 16: FRA-; Apr 17: FRA-; Apr 18: FRA-; Apr 19: FRA-; Apr 20: FRA-; Apr 21: FRA-; Apr 22: FRA-; Apr 23: FRA-; Apr 24: FRA-; Apr 25: FRA-; Apr 26: FRA-; Apr 27: FRA-; Apr 28: FRA-; Apr 29: FRA-; Apr 30: FRA-; May 01: FRA-; May 02: FRA-; May 03: FRA-; May 04: FRA-; May 05: FRA-; May 06: FRA-; May 07: FRA-; May 08: FRA-; May 09: FRA-; May 10: FRA-; May 11: FRA-; May 12: FRA-; May 13: FRA-; May 14: FRA-; May 15: FRA-; May 16: FRA-; May 17: FRA-; May 18: FRA-; May 19: FRA-; May 20: FRA-; May 21: FRA-; May 22: FRA-; May 23: FRA-; May 24: FRA-; May 25: FRA-; May 26: FRA-; May 27: FRA-; May 28: FRA-; May 29: FRA-; May 30: FRA-; May 31: FRA-; Jun 01: FRA-; Jun 02: FRA-; Jun 03: FRA-; Jun 04: FRA-; Jun 05: FRA-; Jun 06: FRA-; Jun 07: FRA-; Jun 08: FRA-; Jun 09: FRA-; Jun 10: FRA-; Jun 11: FRA-; Jun 12: FRA-; Jun 13: FRA-; Jun 14: FRA-; Jun 15: FRA-; Jun 16: FRA-; Jun 17: FRA-; Jun 18: FRA-; Jun 19: FRA-; Jun 20: FRA-; Jun 21: FRA-; Jun 22: FRA-; Jun 23: FRA-; Jun 24: FRA-; Jun 25: FRA-; Jun 26: FRA-; Jun 27: FRA-; Jun 28: FRA-; Jun 29: FRA-; Jun 30: FRA-; Jul 01: FRA-; Jul 02: FRA-; Jul 03: FRA-; Jul 04: FRA-; Jul 05: FRA-; Jul 06: FRA-; Jul 07: FRA-; Jul 08: FRA-; Jul 09: FRA-; Jul 10: FRA-; Jul 11: FRA-; Jul 12: FRA-; Jul 13: FRA-; Jul 14: FRA-; Jul 15: FRA-; Jul 16: FRA-; Jul 17: FRA-; Jul 18: FRA-; Jul 19: FRA-; Jul 20: FRA-; Jul 21: FRA-; Jul 22: FRA-; Jul 23: FRA-; Jul 24: FRA-; Jul 25: FRA-; Jul 26: FRA-; Jul 27: FRA-; Jul 28: FRA-; Jul 29: FRA-; Jul 30: FRA-; Jul 31: FRA-; Aug 01: FRA-; Aug 02: FRA-; Aug 03: FRA-; Aug 04: FRA-; Aug 05: FRA-; Aug 06: FRA-; Aug 07: FRA-; Aug 08: FRA-; Aug 09: FRA-; Aug 10: FRA-; Aug 11: FRA-; Aug 12: FRA-; Aug 13: FRA-; Aug 14: FRA-; Aug 15: FRA-; Aug 16: FRA-; Aug 17: FRA-; Aug 18: FRA-; Aug 19: FRA-; Aug 20: FRA-; Aug 21: FRA-; Aug 22: FRA-; Aug 23: FRA-; Aug 24: FRA-; Aug 25: FRA-; Aug 26: FRA-; Aug 27: FRA-; Aug 28: FRA-; Aug 29: FRA-; Aug 30: FRA-; Aug 31: FRA-; Sep 01: FRA-; Sep 02: FRA-; Sep 03: FRA-; Sep 04: FRA-; Sep 05: FRA-; Sep 06: FRA-; Sep 07: FRA-; Sep 08: FRA-; Sep 09: FRA-; Sep 10: FRA-; Sep 11: FRA-; Sep 12: FRA-; Sep 13: FRA-; Sep 14: FRA-; Sep 15: FRA-; Sep 16: FRA-; Sep 17: FRA-; Sep 18: FRA-; Sep 19: FRA-; Sep 20: FRA-; Sep 21: FRA-; Sep 22: FRA-; Sep 23: FRA-; Sep 24: FRA-; Sep 25: FRA-; Sep 26: FRA-; Sep 27: FRA-; Sep 28: FRA-; Sep 29: FRA-; Sep 30: FRA-; Oct 01: FRA-; Oct 02: FRA-; Oct 03: FRA-; Oct 04: FRA-; Oct 05: FRA-; Oct 06: FRA-; Oct 07: FRA-; Oct 08: FRA-; Oct 09: FRA-; Oct 10: FRA-; Oct 11: FRA-; Oct 12: FRA-; Oct 13: FRA-; Oct 14: FRA-; Oct 15: FRA-; Oct 16: FRA-; Oct 17: FRA-; Oct 18: FRA-; Oct 19: FRA-; Oct 20: FRA-; Oct 21: FRA-; Oct 22: FRA-; Oct 23: FRA-; Oct 24: FRA-; Oct 25: FRA-; Oct 26: FRA-; Oct 27: FRA-; Oct 28: FRA-; Oct 29: FRA-; Oct 30: FRA-; Oct 31: FRA-; Nov 01: FRA-; Nov 02: FRA-; Nov 03: FRA-; Nov 04: FRA-; Nov 05: FRA-; Nov 06: FRA-; Nov 07: FRA-; Nov 08: FRA-; Nov 09: FRA-; Nov 10: FRA-; Nov 11: FRA-; Nov 12: FRA-; Nov 13: FRA-; Nov 14: FRA-; Nov 15: FRA-; Nov 16: FRA-; Nov 17: FRA-; Nov 18: FRA-; Nov 19: FRA-; Nov 20: FRA-; Nov 21: FRA-; Nov 22: FRA-; Nov 23: FRA-; Nov 24: FRA-; Nov 25: FRA-; Nov 26: FRA-; Nov 27: FRA-; Nov 28: FRA-; Nov 29: FRA-; Nov 30: FRA-; Dec 01: FRA-; Dec 02: FRA-; Dec 03: FRA-; Dec 04: FRA-; Dec 05: FRA-; Dec 06: FRA-; Dec 07: FRA-; Dec 08: FRA-; Dec 09: FRA-; Dec 10: FRA-; Dec 11: FRA-; Dec 12: FRA-; Dec 13: FRA-; Dec 14: FRA-; Dec 15: FRA-; Dec 16: FRA-; Dec 17: FRA-; Dec 18: FRA-; Dec 19: FRA-; Dec 20: FRA-; Dec 21: FRA-; Dec 22: FRA-; Dec 23: FRA-; Dec 24: FRA-; Dec 25: FRA-; Dec 26: FRA-; Dec 27: FRA-; Dec 28: FRA-; Dec 29: FRA-; Dec 30: FRA-; Dec 31: FRA-; Jan 01: FRA-; Jan 02: FRA-; Jan 03: FRA-
[176 empty] | STL-2 | STL-2 | [159 empty] | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 |  |  | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | [7 empty] | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | [88 empty] | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5
| Level 1 | Dec 02: FRA-7; Dec 03: FRA-7; Dec 04: FRA-7; Dec 05: FRA-7; Dec 06: FRA-7; Dec 09: FRA-7; Dec 10: FRA-7; Dec 11: FRA-7; Dec 12: FRA-7; Dec 13: FRA-7; Dec 23: FRA-7; Dec 24: FRA-7; Dec 25: FRA-7; Dec 26: FRA-7; Dec 27: FRA-7; Dec 28: FRA-7; Dec 29: FRA-7; Dec 30: FRA-7; Dec 31: FRA-7; Jan 01: FRA-7; Jan 02: FRA-7; Jan 03: FRA-7
| Level 2 | Apr 19: FRA-; Apr 20: FRA-; Apr 21: FRA-; Apr 22: FRA-; Apr 23: FRA-; Apr 24: FRA-; Apr 25: FRA-; Apr 26: FRA-; Apr 27: FRA-; Apr 28: FRA-; Apr 29: FRA-; Apr 30: FRA-; May 01: FRA-; May 02: FRA-; May 03: FRA-; May 04: FRA-; May 05: FRA-; May 06: FRA-; May 07: FRA-; May 08: FRA-; May 09: FRA-; May 10: FRA-; May 11: FRA-; May 12: FRA-; May 13: FRA-; Aug 21: FRA-1; Aug 22: FRA-1; Aug 23: FRA-1; Aug 24: FRA-1; Aug 25: FRA-1; Aug 26: FRA-1; Aug 27: FRA-1; Nov 26: FRA-3; Nov 27: FRA-3; Nov 28: FRA-3; Nov 29: FRA-3; Nov 30: FRA-3; Dec 01: FRA-3; Dec 02: FRA-3
[206 empty] | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA-
| Level 3 | May 28: FRA-; May 29: FRA-; May 30: FRA-; May 31: FRA-; Jun 01: FRA-; Jun 02: FRA-; Jun 03: FRA-; Jun 04: FRA-; Jun 05: FRA-; Jun 06: FRA-; Jun 07: FRA-; Jul 23: FRA-; Jul 24: FRA-; Jul 25: FRA-; Jul 26: FRA-; Sep 10: FRA-1; Sep 11: FRA-1; Sep 12: FRA-1; Sep 13: FRA-1; Sep 14: FRA-1; Sep 15: FRA-1; Sep 16: FRA-1; Nov 12: FRA-3; Nov 13: FRA-3; Nov 14: FRA-3; Nov 15: FRA-3; Nov 16: FRA-3; Nov 17: FRA-3; Nov 18: FRA-3
[245 empty] | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA-
| Level 4 | Jun 19: FRA-; Jun 20: FRA-; Jun 21: FRA-; Jun 22: FRA-; Jun 23: FRA-; Jun 24: FRA-; Jun 25: FRA-; Jun 26: FRA-; Jun 27: FRA-; Jun 28: FRA-; Jun 29: FRA-; Jun 30: FRA-; Jul 01: FRA-; Jul 02: FRA-; Jul 03: FRA-; Jul 04: FRA-; Jul 05: FRA-; Sep 23: FRA-1; Sep 24: FRA-1; Sep 25: FRA-1; Sep 26: FRA-1; Sep 27: FRA-1; Nov 04: INS-1; Nov 29: FRA-3; Nov 30: FRA-3; Dec 01: FRA-3; Dec 02: FRA-3; Dec 03: FRA-3; Dec 04: FRA-3; Dec 05: FRA-3
[267 empty] | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA-
| Parkade | Apr 11: FRA-; Apr 12: FRA-; Apr 13: FRA-; Apr 14: FRA-; Apr 15: FRA-; Aug 19: FRA-4; Aug 20: FRA-4; Aug 21: FRA-4; Aug 22: FRA-4; Aug 23: FRA-4; Dec 16: FRA-2; Dec 17: FRA-2; Dec 18: FRA-2; Dec 19: FRA-2; Dec 20: FRA-2
[198 empty] | FRA- | FRA- | FRA- | FRA- | FRA- | FRA-
| Roof | Jul 09: FRA-; Jul 10: FRA-; Jul 11: FRA-; Jul 12: FRA-; Jul 13: FRA-; Jul 14: FRA-; Jul 15: FRA-; Jul 16: FRA-; Jul 17: FRA-; Jul 18: FRA-; Jul 19: FRA-; Jul 20: FRA-; Jul 21: FRA-; Jul 22: FRA-; Jul 23: FRA-; Jul 24: FRA-; Jul 25: FRA-; Jul 26: FRA-; Jul 27: FRA-; Jul 28: FRA-; Jul 29: FRA-; Jul 30: FRA-; Jul 31: FRA-; Aug 01: FRA-; Aug 02: FRA-; Aug 03: FRA-; Aug 04: FRA-; Aug 05: FRA-; Aug 06: FRA-; Aug 07: FRA-
[287 empty] | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA-
Rough-Ins | Interior Bldg | Jun 12: MCH-1; Jun 13: MCH-1; Jun 14: MCH-1; Jun 15: MCH-1; Jun 16: MCH-1; Jun 17: MCH-1; Jun 18: MCH-1; Jul 17: PLU-1; Jul 18: PLU-1; Jul 30: VF-1; Aug 05: MCH-4; Aug 06: MCH-4; Aug 07: MCH-4; Aug 08: MCH-4; Aug 09: MCH-4; Aug 10: MCH-4; Aug 11: MCH-4; Aug 12: MCH-4; Aug 13: MCH-4; Aug 14: MCH-4; Aug 26: ELE-3; Aug 27: ELE-3; Aug 28: ELE-3; Aug 29: ELE-3; Aug 30: ELE-3; Aug 31: ELE-3; Sep 01: ELE-3; Sep 02: ELE-3; Sep 03: ELE-3; Sep 06: PLU-2; Sep 07: PLU-2; Sep 08: PLU-2; Sep 09: PLU-2; Sep 10: PLU-2; Sep 11: PLU-2; Sep 26: PLU-2; Sep 27: PLU-2; Oct 14: VF-2; Oct 15: VF-2; Oct 16: VF-2; Oct 17: VF-2; Oct 18: VF-2; Oct 19: VF-2; Oct 20: VF-2; Oct 21: VF-2; Oct 22: VF-2; Oct 23: VF-2; Oct 24: VF-2; Oct 25: VF-2; Oct 26: VF-2; Oct 27: VF-2; Oct 28: VF-2; Oct 29: VF-2; Oct 30: VF-2; Oct 31: VF-2; Nov 01: VF-2; Nov 02: VF-2; Nov 03: VF-2; Nov 04: VF-2; Nov 05: VF-2; Nov 06: VF-2; Nov 07: VF-2; Nov 08: VF-2; Nov 09: VF-2; Nov 10: VF-2; Nov 11: VF-2; Nov 12: VF-2; Nov 13: VF-2; Nov 14: VF-2; Nov 15: VF-2; Nov 16: VF-2; Nov 17: VF-2; Nov 18: VF-2; Nov 19: VF-2; Nov 20: VF-2; Nov 21: VF-2; Nov 22: VF-2; Nov 23: VF-2; Nov 24: VF-2; Nov 25: VF-2; Nov 26: VF-2; Nov 27: VF-2; Nov 28: VF-2; Nov 29: VF-2; Nov 30: VF-2; Dec 01: VF-2; Dec 02: VF-2; Dec 03: VF-2; Dec 04: VF-2; Dec 05: VF-2; Dec 06: VF-2; Dec 07: VF-2; Dec 08: VF-2; Dec 09: VF-2; Dec 10: VF-2; Dec 11: VF-2; Dec 12: VF-2; Dec 13: VF-2; Dec 14: VF-2; Dec 15: VF-2; Dec 16: VF-2; Dec 17: VF-2; Dec 18: VF-2; Dec 19: VF-2; Dec 20: VF-2; Dec 21: VF-2; Dec 22: VF-2; Dec 23: VF-2; Dec 24: VF-2; Dec 25: VF-2; Dec 26: VF-2; Dec 27: VF-2; Dec 28: VF-2; Dec 29: VF-2; Dec 30: VF-2; Dec 31: VF-2; Jan 01: VF-2; Jan 02: VF-2; Jan 03: VF-2; Jan 22: DRY-3; Apr 11: SPR-4; Apr 12: SPR-4; Apr 13: SPR-4; Apr 14: SPR-4; Apr 15: SPR-4; Apr 16: SPR-4; Apr 17: SPR-4
[260 empty] | ELE-1 | ELE-1 | ELE-1 | ELE-1 | ELE-1 | ELE-1 | ELE-1 | [47 empty] | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1
[316 empty] | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | [8 empty] | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | [64 empty] | DRY-2 |  |  |  | DRY-2 |  |  | DRY-3 | [5 empty] | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 |  | DRY-4 | DRY-4 | DRY-4 | DRY-4 | DRY-4 | [42 empty] | DRY-3
[409 empty] | DRY-3 | [6 empty] | DRY-3 | [9 empty] | GYP-1 | GYP-1 |  | DRY-2
DRY-3
DRY-3
[429 empty] | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4
[429 empty] | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2
| Level 1 | Feb 11: ELE-2; Feb 12: ELE-2; Feb 13: ELE-2
[504 empty] | MCH-3 | MCH-3 | MCH-3
[504 empty] | SPR-1 | SPR-1 | SPR-1
| Level 2 | Jul 18: DRY-7; Jul 19: DRY-7; Jul 20: DRY-7; Jul 21: DRY-7; Jul 22: DRY-7; Aug 12: DRY-9; Aug 13: DRY-9; Aug 14: DRY-9; Aug 15: DRY-9; Aug 16: DRY-9; Aug 17: DRY-9; Aug 18: DRY-9; Aug 19: DRY-9; Aug 20: DRY-9; Aug 21: DRY-9; Aug 22: DRY-9; Aug 23: DRY-9; Aug 24: DRY-9; Aug 25: DRY-9; Aug 26: DRY-9; Aug 27: DRY-9; Aug 28: DRY-9; Aug 29: DRY-9; Aug 30: DRY-4; Aug 31: DRY-4; Sep 01: DRY-4; Sep 02: DRY-4; Sep 03: DRY-4; Sep 04: DRY-4; Nov 01: MCH-4; Nov 02: MCH-4; Nov 03: MCH-4; Nov 04: MCH-4; Nov 05: MCH-4; Nov 06: MCH-4; Nov 07: MCH-4; Nov 08: MCH-4; Nov 09: MCH-4; Nov 10: MCH-4; Nov 11: MCH-4; Nov 12: MCH-4; Nov 13: MCH-4; Nov 14: MCH-4; Nov 15: MCH-4; Nov 25: DRY-5; Nov 28: DRY-4; Nov 29: DRY-4; Nov 30: DRY-4; Dec 01: DRY-4; Dec 02: DRY-4; Dec 03: DRY-4; Dec 04: DRY-4; Dec 05: DRY-10; Dec 06: DRY-10; Dec 07: DRY-10; Dec 08: DRY-10; Dec 09: DRY-10; Dec 10: DRY-10; Dec 11: DRY-10; Dec 12: DRY-10; Dec 13: DRY-10; Dec 14: DRY-10; Dec 15: DRY-10; Dec 16: DRY-10; Dec 17: DRY-10; Dec 18: DRY-10; Dec 19: DRY-10; Feb 07: ELE-2; Feb 08: ELE-2; Feb 09: ELE-2; Feb 10: ELE-2; Feb 11: ELE-2; Feb 12: ELE-2; Feb 13: ELE-2
[335 empty] | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | [55 empty] | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | [12 empty] | DRY-4 | DRY-4 | DRY-4 | DRY-4 | DRY-4 | DRY-4 | DRY-4 | [64 empty] | MCH-3 | MCH-3 | MCH-3 | MCH-3 | MCH-3 | MCH-3 | MCH-3
[335 empty] | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | [62 empty] | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | [76 empty] | SPR-1 | SPR-1 | SPR-1 | SPR-1 | SPR-1 | SPR-1 | SPR-1
[409 empty] | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3
| Level 3 | Aug 30: DRY-9; Aug 31: DRY-9; Sep 01: DRY-9; Sep 02: DRY-9; Sep 03: DRY-9; Sep 04: DRY-9; Sep 05: DRY-9; Sep 09: SPR-3; Sep 10: SPR-3; Sep 11: SPR-3; Sep 12: SPR-3; Sep 13: SPR-3; Sep 14: SPR-3; Sep 15: SPR-3; Sep 16: SPR-3; Sep 17: SPR-3; Sep 18: SPR-3; Sep 19: SPR-3; Sep 20: SPR-3; Oct 28: MCH-4; Oct 29: MCH-4; Oct 30: MCH-4; Oct 31: MCH-4; Nov 01: MCH-4; Nov 02: MCH-4; Nov 03: MCH-4; Nov 04: MCH-4; Nov 05: MCH-4; Nov 06: MCH-4; Nov 07: MCH-4; Nov 11: DRY-5; Nov 15: DRY-8; Nov 16: DRY-8; Nov 17: DRY-8; Nov 18: DRY-8; Nov 19: DRY-8; Nov 20: DRY-8; Nov 21: DRY-8; Nov 22: DRY-8; Jan 29: ELE-2; Jan 30: ELE-2; Jan 31: ELE-2; Feb 01: ELE-2; Feb 02: ELE-2; Feb 03: ELE-2; Feb 04: ELE-2
[349 empty] | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | [37 empty] | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | [7 empty] | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | [67 empty] | MCH-3 | MCH-3 | MCH-3 | MCH-3 | MCH-3 | MCH-3 | MCH-3
[351 empty] | DRY-4 | DRY-4 | DRY-4 | DRY-4 | DRY-4 | DRY-4 | [41 empty] | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | [6 empty] | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | [67 empty] | SPR-1 | SPR-1 | SPR-1 | SPR-1 | SPR-1 | SPR-1 | SPR-1
[398 empty] | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | [13 empty] | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10
| Level 4 | Sep 11: DRY-6; Sep 12: DRY-6; Sep 13: DRY-6; Sep 14: DRY-6; Sep 15: DRY-6; Sep 16: DRY-6; Sep 17: DRY-6; Sep 18: DRY-9; Sep 19: DRY-9; Sep 20: DRY-9; Sep 21: DRY-9; Sep 22: DRY-9; Sep 23: DRY-9; Sep 24: DRY-9; Sep 25: DRY-9; Sep 26: DRY-9; Sep 27: DRY-4; Sep 28: DRY-4; Sep 29: DRY-4; Sep 30: DRY-4; Oct 01: DRY-4; Oct 02: DRY-4; Oct 21: MCH-4; Oct 22: MCH-4; Oct 23: MCH-4; Oct 24: MCH-4; Oct 25: MCH-4; Nov 01: DRY-5; Nov 08: DRY-8; Nov 09: DRY-8; Nov 10: DRY-8; Nov 11: DRY-8; Nov 12: DRY-8; Nov 13: DRY-8; Nov 14: DRY-8; Nov 15: DRY-8; Jan 21: ELE-2; Jan 22: ELE-2; Jan 23: ELE-2; Jan 24: ELE-2; Jan 25: ELE-2; Jan 26: ELE-2; Jan 27: ELE-2
[363 empty] | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | [20 empty] | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | [13 empty] | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | [66 empty] | MCH-3 | MCH-3 | MCH-3 | MCH-3 | MCH-3 | MCH-3 | MCH-3
[363 empty] | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | [20 empty] | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | [7 empty] | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | [66 empty] | SPR-1 | SPR-1 | SPR-1 | SPR-1 | SPR-1 | SPR-1 | SPR-1
[391 empty] | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | [14 empty] | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10
[391 empty] | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2
| Parkade | Jun 12: RI-1; Jun 13: RI-1; Jun 14: RI-1; Jun 15: RI-1; Jun 16: RI-1; Jun 17: RI-1; Jun 18: RI-1; Jun 19: RI-1; Jun 20: RI-1; Jun 21: RI-1; Jun 22: RI-1; Jun 23: RI-1; Jun 24: RI-1; Jun 25: RI-1; Jun 26: RI-1; Dec 13: DRY-10; Dec 14: DRY-10; Dec 15: DRY-10; Dec 16: DRY-10; Dec 17: DRY-10; Dec 18: DRY-10; Dec 19: DRY-10; Dec 20: DRY-10; Dec 21: DRY-10; Dec 22: DRY-10; Dec 23: DRY-10
Exteriors | Level 2 | Nov 08: RI-2; Nov 09: RI-2; Nov 10: RI-2; Nov 11: RI-2; Nov 12: RI-2; Nov 13: RI-2; Nov 14: RI-2; Nov 15: RI-2; Nov 16: RI-2; Nov 17: RI-2; Nov 18: RI-2; Nov 19: RI-2; Nov 20: RI-2; Nov 21: RI-2; Nov 22: SID-4; Nov 23: SID-4; Nov 24: SID-4; Nov 25: SID-4; Nov 26: SID-4; Nov 27: SID-4; Nov 28: SID-4; Nov 29: SID-4; Nov 30: SID-4; Dec 01: SID-4; Dec 02: SID-4; Dec 03: SID-4; Dec 04: SID-4; Dec 05: SID-4; Dec 06: SID-4; Dec 07: SID-4; Dec 08: SID-4; Dec 09: SID-4
[426 empty] | INSU-1 | INSU-1 | INSU-1 | INSU-1
[429 empty] | EXT-4 | EXT-4 | EXT-4 | EXT-4 | EXT-4 | EXT-4 | EXT-4
| Level 3 | Oct 28: RI-2; Oct 29: RI-2; Oct 30: RI-2; Oct 31: RI-2; Nov 01: RI-2; Nov 02: RI-2; Nov 03: RI-2; Nov 04: RI-2; Nov 05: RI-2; Nov 06: RI-2; Nov 07: RI-2; Nov 08: RI-2; Nov 12: INSU-1; Nov 13: INSU-1; Nov 14: INSU-1; Nov 15: INSU-1; Feb 19: EXT-10
[407 empty] | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4
| Level 4 | Oct 21: SID-4; Oct 22: SID-4; Oct 23: SID-4; Oct 24: SID-4; Oct 25: SID-4; Oct 26: SID-4; Oct 27: SID-4; Oct 28: SID-4; Oct 29: SID-4; Oct 30: SID-4; Oct 31: SID-4; Nov 01: SID-4; Nov 02: SID-4; Nov 03: SID-4; Nov 04: SID-4; Nov 05: SID-4
[406 empty] | INSU-1 | INSU-1 | INSU-1
| Outside Bldg | Jul 08: WIN-1; Jul 09: WIN-1; Jul 10: WIN-1; Jul 11: WIN-1; Jul 12: WIN-1; Jul 13: WIN-1; Jul 14: WIN-1; Jul 15: WIN-1; Jul 16: WIN-1; Jul 17: WIN-1; Jul 18: WIN-1; Jul 19: WIN-1; Jul 20: WIN-1; Jul 21: WIN-1; Jul 22: WIN-1; Jul 23: WIN-1; Jul 24: WIN-1; Jul 25: WIN-1; Jul 26: WIN-1; Jul 27: WIN-1; Jul 28: WIN-1; Jul 29: WIN-1; Jul 30: WIN-1; Jul 31: WIN-1; Aug 01: WIN-1; Aug 02: WIN-1; Aug 03: WIN-1; Aug 04: WIN-1; Aug 05: WIN-1; Aug 06: WIN-1; Aug 07: WIN-1; Aug 08: WIN-1; Aug 09: WIN-1; Aug 10: WIN-1; Aug 11: WIN-1; Aug 12: WIN-1; Aug 13: WIN-1; Aug 14: WIN-1; Aug 15: WIN-1; Aug 16: WIN-1; Aug 17: WIN-1; Aug 18: WIN-1; Aug 19: WIN-1; Aug 20: WIN-1; Aug 21: WIN-1; Aug 22: WIN-1; Aug 23: WIN-1; Aug 24: WIN-1; Aug 25: WIN-1; Aug 26: WIN-1; Aug 27: WIN-1; Aug 28: WIN-1; Aug 29: WIN-1; Aug 30: WIN-1; Aug 31: WIN-1; Sep 01: WIN-1; Sep 02: WIN-1; Sep 03: WIN-1; Sep 04: WIN-1; Sep 05: WIN-1; Sep 06: WIN-1; Sep 07: WIN-1; Sep 08: WIN-1; Sep 09: WIN-1; Sep 10: WIN-1; Sep 11: WIN-1; Sep 12: WIN-1; Sep 13: WIN-1; Sep 14: WIN-1; Sep 15: WIN-1; Sep 16: WIN-1; Sep 17: WIN-1; Sep 18: WIN-1; Sep 19: WIN-1; Sep 20: WIN-1; Sep 21: WIN-1; Sep 22: WIN-1; Sep 23: WIN-1; Sep 24: WIN-1; Sep 25: WIN-1; Sep 26: WIN-1; Sep 27: WIN-1; Sep 28: WIN-1; Sep 29: WIN-1; Sep 30: WIN-1; Oct 01: WIN-1; Oct 02: WIN-1; Oct 03: WIN-1; Oct 04: WIN-1; Oct 05: WIN-1; Oct 06: WIN-1; Oct 07: WIN-1; Oct 08: WIN-1; Oct 09: WIN-1; Oct 10: WIN-1; Oct 11: WIN-1; Oct 12: WIN-1; Oct 13: WIN-1; Oct 14: WIN-1; Oct 15: WIN-1; Oct 16: WIN-1; Oct 17: WIN-1; Oct 18: WIN-1; Oct 19: WIN-1; Oct 20: WIN-1; Oct 21: WIN-1; Oct 22: WIN-1; Oct 23: WIN-1; Oct 24: WIN-1; Oct 25: WIN-1; Oct 26: WIN-1; Oct 27: WIN-1; Oct 28: WIN-1; Oct 29: WIN-1; Oct 30: WIN-1; Oct 31: WIN-1; Nov 01: WIN-1; Nov 02: WIN-1; Nov 03: WIN-1; Nov 04: WIN-1; Nov 05: WIN-1; Nov 06: WIN-1; Nov 07: WIN-1; Nov 08: WIN-1; Nov 09: WIN-1; Nov 10: WIN-1; Nov 11: WIN-1; Nov 12: WIN-1; Nov 13: WIN-1; Nov 14: WIN-1; Nov 15: WIN-1; Nov 16: WIN-1; Nov 17: WIN-1; Nov 18: WIN-1; Nov 19: WIN-1; Nov 20: WIN-1; Nov 21: WIN-1; Nov 22: WIN-1; Nov 23: WIN-1; Nov 24: WIN-1; Nov 25: WIN-1; Nov 26: WIN-1; Nov 27: SID-2; Nov 28: SID-2; Nov 29: SID-2; Nov 30: SID-2; Dec 01: SID-2; Dec 02: SID-2; Dec 03: SID-2; Dec 04: SID-2; Dec 05: SID-2; Dec 06: SID-2; Dec 07: SID-2; Dec 08: SID-2; Dec 09: SID-2; Dec 10: SID-2; Dec 11: SID-2; Dec 12: SID-2; Dec 13: SID-2; Dec 14: SID-2; Dec 15: SID-2; Dec 16: SID-2; Dec 24: SID-3
[316 empty] | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | [10 empty] | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | [14 empty] | SID-3
[318 empty] | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | [11 empty] | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1
[318 empty] | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8 | EXT-8
[321 empty] | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | [25 empty] | EXT-7 | EXT-7 | EXT-7 | [46 empty] | SID-3 | [15 empty] | SID-3
| Parkade | Aug 19: RI-4; Aug 20: RI-4; Aug 21: RI-4; Aug 22: RI-4; Aug 23: RI-4; Aug 24: RI-4; Aug 25: RI-4; Aug 26: RI-4; Aug 27: RI-4; Aug 28: RI-4; Aug 29: RI-4; Aug 30: RI-4; Aug 31: RI-4; Sep 01: RI-4; Sep 02: RI-4; Sep 03: RI-4; Sep 04: RI-4; Sep 05: RI-4; Sep 06: RI-4; Sep 07: RI-4; Sep 08: RI-4; Sep 09: RI-4; Sep 10: RI-4; Sep 11: RI-4; Sep 12: RI-4; Sep 13: RI-4; Sep 14: RI-4; Sep 15: RI-4; Sep 16: RI-4; Sep 17: RI-4; Sep 18: RI-4; Sep 19: RI-4; Sep 20: RI-4; Sep 21: RI-4; Sep 22: RI-4; Sep 23: RI-4; Sep 24: RI-4; Sep 25: RI-4; Sep 26: RI-4; Sep 27: RI-4; Sep 28: RI-4; Sep 29: RI-4; Sep 30: RI-4; Oct 01: RI-4; Oct 02: RI-4; Oct 03: RI-4; Oct 04: RI-4; Oct 05: RI-4; Oct 06: RI-4; Oct 07: RI-4; Oct 08: RI-4; Oct 09: RI-4; Oct 10: RI-4; Oct 11: RI-4; Oct 12: RI-4; Oct 13: RI-4; Oct 14: RI-4; Oct 15: RI-4; Oct 16: RI-4; Oct 17: RI-4; Oct 18: RI-4; Oct 19: RI-4; Oct 20: RI-4; Oct 21: RI-4; Oct 22: RI-4; Oct 23: RI-4; Oct 24: RI-4; Oct 25: RI-4; Oct 26: RI-4; Oct 27: RI-4; Oct 28: RI-4; Oct 29: RI-4; Oct 30: RI-4; Oct 31: RI-4; Nov 01: RI-4; Nov 02: RI-4; Nov 03: RI-4; Nov 04: RI-4; Nov 05: RI-4; Nov 06: RI-4; Nov 07: RI-4; Nov 08: RI-4; Nov 09: RI-4; Nov 10: RI-4; Nov 11: RI-4; Nov 12: RI-4; Nov 13: RI-4; Nov 14: RI-4; Nov 15: RI-4; Nov 16: RI-4; Nov 17: RI-4; Nov 18: RI-4; Nov 19: RI-4; Nov 20: RI-4; Nov 21: RI-4; Nov 22: RI-4; Nov 23: RI-4; Nov 24: RI-4; Nov 25: RI-4; Nov 26: RI-4; Nov 27: RI-4; Nov 28: RI-4; Nov 29: RI-4; Nov 30: RI-4; Dec 01: RI-4; Dec 02: RI-4; Dec 03: RI-4; Dec 04: RI-4; Dec 05: RI-4; Dec 06: RI-4; Dec 07: RI-4; Dec 08: RI-4; Dec 09: RI-4; Dec 10: RI-4; Dec 11: RI-4; Dec 12: RI-4; Dec 13: RI-4; Dec 14: RI-4; Dec 15: RI-4; Dec 16: RI-4; Dec 17: RI-4; Dec 18: RI-4; Dec 19: RI-4; Dec 20: RI-4; Dec 21: RI-4; Dec 22: RI-4; Dec 23: RI-4; Dec 24: RI-4; Dec 25: RI-4; Dec 26: RI-4; Dec 27: RI-4; Dec 28: RI-4; Dec 29: RI-4; Dec 30: RI-4; Dec 31: RI-4; Jan 01: RI-4; Jan 02: RI-4; Jan 03: RI-4; Jan 04: RI-4; Jan 05: RI-4; Jan 06: RI-4; Jan 07: RI-4; Jan 08: RI-4; Jan 09: RI-4; Jan 10: RI-4; Jan 11: RI-4; Jan 12: RI-4; Jan 13: RI-4; Jan 14: RI-4; Jan 15: RI-4; Jan 16: RI-4; Jan 17: RI-4; Jan 18: RI-4; Jan 19: RI-4; Jan 20: RI-4; Jan 21: RI-4; Jan 22: RI-4; Jan 23: RI-4
[331 empty] | INSU-2 | INSU-2 | [86 empty] | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 | RI-2 |  |  | EXT-5 | EXT-6 | EXT-6 | EXT-6 | EXT-6
[441 empty] | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4
Finishes | Interior Bldg | Mar 25: CX-; Aug 01: FLO-10; Aug 02: FLO-10; Aug 03: FLO-10; Aug 04: FLO-10; Aug 05: FLO-10; Aug 06: FLO-10; Aug 07: FLO-10; Aug 08: FLO-10; Aug 09: FLO-10; Aug 10: FLO-10; Aug 11: FLO-10; Aug 12: FLO-10; Aug 13: FLO-10; Aug 20: INS-7; Sep 03: EXT-11; Sep 04: EXT-11; Sep 05: EXT-11; Sep 06: EXT-11; Sep 07: EXT-11; Sep 08: EXT-11; Sep 09: EXT-11; Sep 10: EXT-11; Sep 11: EXT-11; Sep 12: EXT-11; Sep 13: EXT-11; Sep 14: EXT-11; Sep 15: EXT-11; Sep 16: EXT-11; Oct 31: INS-4; Nov 12: INS-6; Nov 25: INS-6; Nov 26: INS-5; Jan 20: FLO-8; Jan 21: FLO-8; Jan 22: FLO-8; Jan 23: FLO-8; Jan 24: FLO-8; Jan 25: FLO-8; Jan 26: FLO-8; Jan 27: FLO-8; Jan 28: FLO-8; Jan 29: FLO-8; Jan 30: FLO-8; Jan 31: FLO-8; Feb 01: FLO-8; Feb 02: FLO-8; Feb 03: FLO-8; Feb 04: FLO-8; Feb 05: FLO-8; Feb 06: FLO-8; Feb 13: PAI-2; Feb 14: PAI-2; Feb 15: PAI-2; Feb 16: PAI-2; Feb 17: PAI-2; Feb 18: PAI-2; Feb 19: PAI-2; Feb 20: PAI-2; Feb 21: PAI-2; Feb 22: PAI-2; Feb 23: PAI-2; Feb 24: PAI-2; Feb 25: PAI-2; Feb 27: CL-2; Feb 28: CL-2; Mar 03: COO-3; Mar 04: CX-2; Mar 05: CX-9; Mar 06: CX-10; Mar 07: CX-10; Mar 08: CX-10; Mar 09: CX-10; Mar 10: CX-10; Mar 11: CX-10; Mar 12: CX-10; Mar 13: CX-12; Mar 18: CX-13; May 02: CX-; May 03: CX-; May 04: CX-; May 05: CX-
[181 empty] | CX- | [136 empty] | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1
[344 empty] | INS-6 | [140 empty] | INS-4 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | [8 empty] | INS-8 |  |  |  |  | INS-2 | INS-2 | INS-3 | INS-3 | INS-3 | INS-3 | COO-1 | COO-1 | COO-2 | COO-2 |  |  | COO-5 | CX-4 | CL-4 | CL-4 | CL-4 | CL-4 | CL-4 | CL-4 | CL-4 | CL-5 | CL-5 | CL-5 | CL-5 | CL-5 | CL-5 | CL-5
[496 empty] | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | INS-10 | INS-10 | INS-10 | INS-10 |  | INS-9 | INS-9 | [10 empty] | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4
[507 empty] | INS-13 | INS-13 | INS-13 | INS-13 | [14 empty] | CX-1 | CX-1 | CX-1 | CX-1 | CX-1 | CX-1 | CX-1 | CX-7
[507 empty] | CX- | CX- | CX- | CX- | [14 empty] | CX-3 | CX-3 | CX-3 | CX-3 | CX-3 | CX-3 | CX-3 | CL-3 | CL-3 | CL-3 | CL-3 | CL-3 | CL-3 | CL-3
[507 empty] | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX-5 | CX-5 | CX-5 | CX-5 | CX-5 | CX-5 | CX-5
[525 empty] | CX-6 | CX-6 | CX-6 | CX-6 | CX-6 | CX-6 | CX-6
[525 empty] | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8
[527 empty] | CX-11 | CX-11 | CX-11 | CX-11 | CX-11 | CX-11 | CX-11
| Level 1 | Jan 02: FIN-2; Jan 03: FIN-2; Jan 08: CAR-4; Jan 09: CAR-4; Jan 10: CAR-6; Jan 15: FLO-7; Jan 16: FLO-7; Jan 17: CAR-2; Jan 18: CAR-2; Jan 19: CAR-2; Jan 20: CAR-2; Feb 10: CAR-3; Feb 14: CL-1; Feb 15: CL-1; Feb 16: CL-1; Feb 17: CL-1; Feb 18: CL-1; Feb 19: CX-; Feb 20: CL-2; Feb 21: CL-2; Feb 22: CL-2; Feb 23: CL-2; Feb 24: CL-2
[464 empty] | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3
[465 empty] | PAI-4 | PAI-4 | PAI-4 | PAI-4 | PAI-4 |  |  | PAI-3 | PAI-3 | PAI-3 | PAI-3 | PAI-3 | PAI-3 | PAI-3
| Level 2 | Jul 24: FLO-5; Jul 25: FLO-5; Jul 26: FLO-5; Aug 12: RI-1; Aug 13: RI-1; Aug 14: RI-1; Aug 15: RI-1; Aug 16: RI-1; Aug 17: RI-1; Aug 18: RI-1; Aug 19: RI-1; Aug 20: RI-1; Aug 21: RI-1; Aug 22: RI-1; Aug 23: RI-1; Aug 24: RI-1; Aug 25: RI-1; Aug 26: RI-1; Aug 27: RI-1; Aug 28: RI-1; Aug 29: RI-1; Aug 30: RI-1; Aug 31: RI-1; Sep 01: RI-1; Sep 02: RI-1; Sep 03: RI-1; Sep 04: RI-1; Sep 05: RI-1; Sep 06: RI-1; Sep 07: RI-1; Sep 08: RI-1; Sep 09: RI-1; Sep 10: RI-1; Sep 11: RI-1; Sep 12: RI-1; Sep 13: RI-1; Sep 14: RI-1; Sep 15: RI-1; Sep 16: RI-1; Sep 17: RI-1; Sep 18: RI-1; Sep 19: RI-1; Sep 20: RI-1; Sep 21: RI-1; Sep 22: RI-1; Sep 23: RI-1; Sep 24: RI-1; Sep 25: RI-1; Sep 26: RI-1; Sep 27: RI-1; Sep 28: RI-1; Sep 29: RI-1; Sep 30: RI-1; Oct 01: RI-1; Oct 02: RI-1; Oct 03: RI-1; Oct 04: RI-1; Oct 05: RI-1; Oct 06: RI-1; Oct 07: RI-1; Oct 08: RI-1; Oct 09: RI-1; Oct 10: RI-1; Oct 11: RI-1; Oct 12: RI-1; Oct 13: RI-1; Oct 14: RI-1; Oct 15: RI-1; Oct 16: RI-1; Oct 17: RI-1; Oct 18: RI-1; Oct 19: RI-1; Oct 20: RI-1; Oct 21: RI-1; Oct 22: RI-1; Oct 23: RI-1; Oct 24: RI-1; Oct 25: RI-1; Oct 26: RI-1; Oct 27: RI-1; Oct 28: RI-1; Oct 29: RI-1; Oct 30: RI-1; Oct 31: RI-1; Nov 01: RI-1; Nov 02: RI-1; Nov 03: RI-1; Nov 04: RI-1; Nov 05: RI-1; Nov 06: RI-1; Nov 07: RI-1; Nov 08: RI-1; Nov 09: RI-1; Nov 10: RI-1; Nov 11: RI-1; Nov 12: RI-1; Nov 13: RI-1; Nov 14: RI-1; Nov 15: RI-1; Nov 16: RI-1; Nov 17: RI-1; Nov 18: RI-1; Nov 19: RI-1; Nov 20: RI-1; Nov 21: RI-1; Nov 22: RI-1; Nov 23: RI-1; Nov 24: RI-1; Nov 25: RI-1; Nov 26: RI-1; Nov 27: RI-1; Nov 28: RI-1; Nov 29: RI-1; Nov 30: RI-1; Dec 01: RI-1; Dec 02: RI-1; Dec 03: RI-1; Dec 04: RI-1; Dec 05: RI-1; Dec 06: RI-1; Dec 07: RI-1; Dec 08: RI-1; Dec 09: RI-1; Dec 10: RI-1; Dec 11: RI-1; Dec 12: RI-1; Dec 13: RI-1; Dec 14: RI-1; Dec 15: RI-1; Dec 16: RI-1; Dec 17: RI-1; Dec 18: RI-1; Dec 19: RI-1; Dec 20: RI-1; Dec 21: RI-1; Dec 22: RI-1; Dec 23: RI-1; Dec 24: RI-1; Dec 25: RI-1; Dec 26: RI-1; Dec 27: RI-1; Dec 28: RI-1; Dec 29: RI-1; Dec 30: RI-1; Dec 31: RI-1; Jan 01: RI-1; Jan 02: RI-1; Jan 03: RI-1; Jan 08: FLO-7; Jan 09: FLO-7; Jan 10: FLO-7; Jan 11: FLO-7; Jan 12: FLO-7; Jan 13: FLO-7; Jan 14: FLO-7; Jan 15: FLO-7; Jan 16: FLO-7; Jan 17: CAR-1; Jan 18: CAR-1; Jan 19: CAR-1; Jan 20: CAR-1; Jan 21: CAR-1; Jan 22: CAR-1; Jan 23: CAR-1; Jan 24: CAR-1; Feb 24: CL-1; Feb 25: CL-1; Feb 26: CL-1; Feb 27: CL-1
[328 empty] | PLU-3 | PLU-3 | PLU-3 | PLU-3 | PLU-3 | [103 empty] | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 |  |  |  | FLO-2 |  |  |  | PAI-3 | PAI-3 | PAI-3 | PAI-3 | PAI-3 | PAI-3 | PAI-3 | PAI-3 | [9 empty] | CAR-6 | CAR-6 | CAR-6 | CAR-6 | CAR-6 |  |  |  | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | [19 empty] | CX-
[447 empty] | FIN-2 | FIN-2 | PAI-4 | PAI-4 | PAI-4 | PAI-4 | PAI-4 | PAI-4 | [23 empty] | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3
[447 empty] | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4 | FLO-4
[454 empty] | CAR-4 | CAR-4 | CAR-4 | CAR-4 | CAR-4 | CAR-4 | CAR-4 | CAR-4 | CAR-4 | CAR-4 | CAR-4 | CAR-4
| Level 3 | Jul 29: FLO-5; Jul 30: FLO-5; Jul 31: FLO-5; Aug 19: PLU-3; Aug 20: PLU-3; Aug 21: PLU-3; Aug 22: PLU-3; Aug 23: PLU-3; Nov 22: DRY-11; Nov 23: DRY-11; Nov 24: DRY-11; Nov 25: DRY-11; Nov 26: DRY-11; Nov 27: DRY-11; Nov 28: DRY-11; Nov 29: DRY-11; Nov 30: DRY-11; Dec 01: DRY-11; Dec 02: DRY-11; Dec 03: DRY-11; Dec 04: DRY-11; Dec 05: DRY-11; Dec 09: CAR-4; Dec 10: CAR-4; Dec 11: CAR-4; Dec 12: CAR-4; Dec 13: CAR-4; Dec 17: FLO-7; Dec 18: FLO-7; Dec 19: FLO-7; Dec 20: FLO-7; Dec 21: FLO-7; Dec 22: FLO-7; Dec 23: FLO-7; Dec 24: FLO-7; Dec 25: FLO-7; Dec 26: FLO-7; Dec 27: FLO-7; Dec 28: FLO-7; Dec 29: FLO-7; Dec 30: FLO-7; Dec 31: FLO-7; Jan 01: FLO-7; Jan 02: FLO-7; Jan 03: FLO-7; Jan 04: FLO-7; Jan 05: FLO-7; Jan 06: FLO-7; Jan 07: FLO-7; Jan 08: FLO-; Jan 09: FLO-; Jan 10: FLO-; Feb 11: CL-1; Feb 12: CL-1; Feb 13: CL-1; Feb 14: CL-1; Feb 15: CL-1; Feb 16: CL-1; Feb 17: CL-1
[328 empty] | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 |  |  |  |  | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | CAR-2 | [37 empty] | CX-
[433 empty] | FIN-2 | FIN-2 |  | PAI-4 | PAI-4 | PAI-4 | PAI-4 | PAI-4 | PAI-4 |  | CAR-6 | CAR-6 | CAR-6 | CAR-6 | CAR-6 | CAR-6 | [21 empty] | CAR-1 | CAR-1 | CAR-1 | CAR-1 | CAR-1 | CAR-1 | [34 empty] | CL-2 | CL-2
[433 empty] | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3 | FLO-3
[441 empty] | FLO-2 |  | PAI-3 | PAI-3 | PAI-3 | PAI-3 | PAI-3 | PAI-3 | [23 empty] | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5
| Level 4 | Jul 29: FLO-11; Jul 30: FLO-11; Jul 31: FLO-11; Aug 01: FLO-11; Aug 05: RI-1; Aug 06: RI-1; Aug 07: RI-1; Aug 08: RI-1; Aug 09: RI-1; Aug 10: RI-1; Aug 11: RI-1; Aug 12: RI-1; Aug 13: RI-1; Aug 14: RI-1; Aug 15: RI-1; Aug 16: RI-1; Aug 17: RI-1; Aug 18: RI-1; Aug 19: RI-1; Aug 20: RI-1; Aug 21: RI-1; Aug 22: RI-1; Aug 23: RI-1; Aug 24: RI-1; Aug 25: RI-1; Aug 26: RI-1; Aug 27: RI-1; Aug 28: RI-1; Aug 29: RI-1; Aug 30: RI-1; Aug 31: RI-1; Sep 01: RI-1; Sep 02: RI-1; Sep 03: RI-1; Sep 04: RI-1; Sep 05: RI-1; Sep 06: RI-1; Sep 07: RI-1; Sep 08: RI-1; Sep 09: RI-1; Sep 10: RI-1; Sep 11: RI-1; Sep 12: RI-1; Sep 13: RI-1; Sep 14: RI-1; Sep 15: RI-1; Sep 16: RI-1; Sep 17: RI-1; Sep 18: RI-1; Sep 19: RI-1; Sep 20: RI-1; Sep 21: RI-1; Sep 22: RI-1; Sep 23: RI-1; Sep 24: RI-1; Sep 25: RI-1; Sep 26: RI-1; Sep 27: RI-1; Sep 28: RI-1; Sep 29: RI-1; Sep 30: RI-1; Oct 01: RI-1; Oct 02: RI-1; Oct 03: RI-1; Oct 04: RI-1; Oct 05: RI-1; Oct 06: RI-1; Oct 07: RI-1; Nov 15: FLO-6; Nov 16: FLO-6; Nov 17: FLO-6; Nov 18: FLO-6; Nov 19: FLO-6; Nov 20: FLO-6; Nov 21: FLO-6; Nov 22: FLO-6; Nov 23: FLO-6; Nov 24: FLO-6; Nov 25: FLO-6; Nov 26: FIN-2; Nov 27: FIN-2; Nov 28: PAI-4; Nov 29: PAI-4; Nov 30: PAI-4; Dec 01: PAI-4; Dec 02: PAI-4; Dec 03: PAI-4; Dec 05: CAR-6; Dec 06: CAR-6; Dec 07: CAR-6; Dec 08: CAR-6; Dec 09: CAR-6; Dec 10: CAR-6; Dec 11: CAR-2; Dec 12: CAR-2; Dec 13: CAR-2; Dec 14: CAR-2; Dec 15: CAR-2; Dec 16: CAR-2; Dec 17: CAR-2; Dec 18: CAR-2; Dec 20: CAR-1; Dec 21: CAR-1; Dec 22: CAR-1; Dec 23: CAR-1; Dec 24: CAR-1; Dec 25: CAR-1; Dec 26: CAR-1; Dec 27: CAR-1; Dec 28: CAR-1; Dec 29: CAR-1; Dec 30: CAR-1; Dec 31: CAR-1; Jan 01: CAR-1; Jan 02: CAR-1; Jan 03: CAR-1; Feb 03: CL-1; Feb 04: CL-1; Feb 05: CL-1; Feb 06: CL-1; Feb 07: CL-1
[310 empty] | FLO-5 | FLO-5 | [16 empty] | PLU-3 | PLU-3 | PLU-3 | PLU-3 | PLU-3 | [12 empty] | FLO-12 | FLO-12 |  |  | FLO-9 | FLO-9 | [12 empty] | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | [41 empty] | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 |  |  |  | FLO-2 | FLO-2 |  | PAI-3 | PAI-3 | PAI-3 | PAI-3 | PAI-3 | PAI-3 | [6 empty] | FLO-4 | FLO-4 | FLO-4 | [13 empty] | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | [16 empty] | CX-
[328 empty] | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 | RI-1 |  |  | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | [52 empty] | CL-2 | CL-2 | CL-2 | CL-2
[427 empty] | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3
[433 empty] | CAR-4 | CAR-4 | CAR-4 | CAR-4 | CAR-4
| Parkade | Jun 17: PAI-1
Note on C5: Activity Name: Assign Mobilization check list Phase: Mobilization Location: Mobilization Trade: Mobilization Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C6: Activity Name: Assign Site Services Planning check list Phase: Mobilization Location: Mobilization Trade: Mobilization Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C7: Activity Name: Assign Sub Contractor planning checklist Phase: Mobilization Location: Mobilization Trade: Mobilization Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on CI8: Activity Name: deliver rebar (footings and gradebeam only) Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 21-Dec-2023 End Date: 21-Dec-2023
Note on CM8: Activity Name: Install balcony piles Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 25-Dec-2023 End Date: 27-Dec-2023
Note on CX8: Activity Name: Measure corner offsets for excavation Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 05-Jan-2024 End Date: 05-Jan-2024
Note on DA8: Activity Name: Excavation Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 08-Jan-2024 End Date: 18-Jan-2024
Note on DL8: Activity Name: Form footings Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 19-Jan-2024 End Date: 24-Jan-2024
Note on DR8: Activity Name: Tie footing rebar Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 25-Jan-2024 End Date: 31-Jan-2024
Note on DY8: Activity Name: Rebar Inspection Structural Engineer Phase: Foundation Location: Interior Bldg Trade: Inspection Start Date: 01-Feb-2024 End Date: 01-Feb-2024
Note on EC8: Activity Name: Pour footings Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 05-Feb-2024 End Date: 05-Feb-2024
Note on ED8: Activity Name: Ensure Sleeves for electrical are run in the grade beam prior to pouring Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 06-Feb-2024 End Date: 06-Feb-2024
Note on EM8: Activity Name: Build templates for Anchor bolts Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 15-Feb-2024 End Date: 15-Feb-2024
Note on EN8: Activity Name: Tie Grade beam rebar Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 16-Feb-2024 End Date: 26-Feb-2024
Note on EY8: Activity Name: Assign pre concrete pour checklist Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 27-Feb-2024 End Date: 27-Feb-2024
Note on EZ8: Activity Name: Rebar inspection Structural Engineer Phase: Foundation Location: Interior Bldg Trade: Inspection Start Date: 28-Feb-2024 End Date: 28-Feb-2024
Note on FA8: Activity Name: Pour grade beam Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 29-Feb-2024 End Date: 29-Feb-2024
Note on FB8: Activity Name: Assign pre back fill check list Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 01-Mar-2024 End Date: 01-Mar-2024
Note on FE8: Activity Name: Install underground insulation Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 04-Mar-2024 End Date: 05-Mar-2024
Note on FG8: Activity Name: Back fill exterior grade beam Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 06-Mar-2024 End Date: 07-Mar-2024
Note on IK8: Activity Name: Assign hollow core erection checklist Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 27-May-2024 End Date: 27-May-2024
Note on JH8: Activity Name: Deliver pakade slab rebar Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 19-Jun-2024 End Date: 19-Jun-2024
Note on KA8: Activity Name: Assign pre concrete pour checklist Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 08-Jul-2024 End Date: 08-Jul-2024
Note on LX8: Activity Name: Excavate areas Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 26-Aug-2024 End Date: 27-Aug-2024
Note on MG8: Activity Name: Tie rebar exterior pads Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 04-Sep-2024 End Date: 06-Sep-2024
Note on MM8: Activity Name: Pour exterior pads Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 10-Sep-2024 End Date: 10-Sep-2024
Note on PK8: Activity Name: Pour Gypcrete Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 25-Nov-2024 End Date: 26-Nov-2024
Note on PY8: Activity Name: Rebar exterior sidewalks Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 09-Dec-2024 End Date: 11-Dec-2024
Note on QB8: Activity Name: Assign pre concrete pour checklist Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 12-Dec-2024 End Date: 16-Dec-2024
Note on QG8: Activity Name: Pour exterior sidewalks Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 17-Dec-2024 End Date: 19-Dec-2024
Note on CI9: Activity Name: Order all Anchor bolts Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 21-Dec-2023 End Date: 21-Dec-2023
Note on DJ9: Activity Name: Survey offsets, and footings Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 17-Jan-2024 End Date: 17-Jan-2024
Note on DK9: Activity Name: Geo Tech Engineer inspection Phase: Foundation Location: Interior Bldg Trade: Inspection Start Date: 18-Jan-2024 End Date: 18-Jan-2024
Note on DL9: Activity Name: Foundation Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 19-Jan-2024 End Date: 29-Feb-2024
Note on FB9: Activity Name: Back fill foundation Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 01-Mar-2024 End Date: 14-Mar-2024
Note on LX9: Activity Name: Exterior concrete works Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 26-Aug-2024 End Date: 19-Dec-2024
Note on CI10: Activity Name: Survey for balcony piles Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 21-Dec-2023 End Date: 22-Dec-2023
Note on ED10: Activity Name: Form grade beam Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 06-Feb-2024 End Date: 14-Feb-2024
Note on GV14: Activity Name: Install hollowcore 2nd floor , Install backer rod & Grout 2nd floor Phase: Foundation Location: Level 2 Trade: Concrete Start Date: 16-Apr-2024 End Date: 18-Apr-2024
Note on GV15: Activity Name: Hollowcore 2nd floor Phase: Foundation Location: Level 2 Trade: Concrete Start Date: 16-Apr-2024 End Date: 17-Jun-2024
Note on IG16: Activity Name: Hollowcore 3rd floor Phase: Foundation Location: Level 3 Trade: Concrete Start Date: 23-May-2024 End Date: 28-May-2024
Note on IG17: Activity Name: Install hollow core 3rd floor, Install backer rod & grout Phase: Foundation Location: Level 3 Trade: Concrete Start Date: 23-May-2024 End Date: 28-May-2024
Note on IZ18: Activity Name: Install hollow core 4th floor and grout Phase: Foundation Location: Level 4 Trade: Concrete Start Date: 11-Jun-2024 End Date: 12-Jun-2024
Note on IZ19: Activity Name: Hollowcore 4th floor Phase: Foundation Location: Level 4 Trade: Concrete Start Date: 11-Jun-2024 End Date: 13-Jun-2024
Note on DA20: Activity Name: Dig footing and parkade foot print Phase: Foundation Location: Parkade Trade: Concrete Start Date: 08-Jan-2024 End Date: 16-Jan-2024
Note on FI20: Activity Name: Back fill interior parkade Phase: Foundation Location: Parkade Trade: Concrete Start Date: 08-Mar-2024 End Date: 14-Mar-2024
Note on JI20: Activity Name: Back fill and level parkade Phase: Foundation Location: Parkade Trade: Concrete Start Date: 20-Jun-2024 End Date: 26-Jun-2024
Note on JP20: Activity Name: Pour parakde slab Phase: Foundation Location: Parkade Trade: Concrete Start Date: 27-Jun-2024 End Date: 10-Jul-2024
Note on JV21: Activity Name: Tie parkade rebar Phase: Foundation Location: Parkade Trade: Concrete Start Date: 03-Jul-2024 End Date: 05-Jul-2024
Note on KB21: Activity Name: Pour parkade floor Phase: Foundation Location: Parkade Trade: Concrete Start Date: 09-Jul-2024 End Date: 10-Jul-2024
Note on C25: Activity Name: Assign hollow core ordering checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 28-Sep-2023
Note on BV25: Activity Name: Order Rebar (30 days before site delivery date required) Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 08-Dec-2023 End Date: 08-Dec-2023
Note on CI25: Activity Name: Schedule Pile contractor Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 21-Dec-2023 End Date: 21-Dec-2023
Note on DA25: Activity Name: 28. Assign Pre excavation checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 08-Jan-2024 End Date: 08-Jan-2024
Note on DZ25: Activity Name: Assign pre-pour checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 02-Feb-2024 End Date: 02-Feb-2024
Note on FP25: Activity Name: Assign structural steel checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 15-Mar-2024 End Date: 15-Mar-2024
Note on GV25: Activity Name: Assign framing checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 16-Apr-2024 End Date: 16-Apr-2024
Note on GY25: Activity Name: Assign hollow core erection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 19-Apr-2024 End Date: 19-Apr-2024
Note on HX25: Activity Name: Assign framing check list Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 14-May-2024 End Date: 14-May-2024
Note on IY25: Activity Name: Assign framing checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 10-Jun-2024 End Date: 10-Jun-2024
Note on JB25: Activity Name: Assign hollow core checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 13-Jun-2024 End Date: 13-Jun-2024
Note on JP25: Activity Name: Assign parkade slab rough in checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 27-Jun-2024 End Date: 27-Jun-2024
Note on KA25: Activity Name: Assign framing checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 08-Jul-2024 End Date: 08-Jul-2024
Note on LE25: Activity Name: Assign roofing and water proofing checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 07-Aug-2024 End Date: 07-Aug-2024
Note on ML25: Activity Name: Assign conrete pour checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 09-Sep-2024 End Date: 09-Sep-2024
Note on MT25: Activity Name: Assign post decking install check list Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 17-Sep-2024 End Date: 17-Sep-2024
Note on NN25: Activity Name: Assign taping inspection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 07-Oct-2024 End Date: 07-Oct-2024
Note on OT25: Activity Name: Assign exterior wall pre board inspection check list Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 08-Nov-2024 End Date: 08-Nov-2024
Note on PA25: Activity Name: Assign taping inspection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on PK25: Activity Name: Assign gypcrete pour checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 25-Nov-2024 End Date: 25-Nov-2024
Note on PL25: Activity Name: Assign tower siding checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 26-Nov-2024 End Date: 26-Nov-2024
Note on PN25: Activity Name: Assign taping inspection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Nov-2024 End Date: 28-Nov-2024
Note on PU25: Activity Name: Assign taping inspection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 05-Dec-2024 End Date: 05-Dec-2024
Note on QI25: Activity Name: Assign taping inspection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 19-Dec-2024 End Date: 19-Dec-2024
Note on QM25: Activity Name: Assign taping inspection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 23-Dec-2024 End Date: 23-Dec-2024
Note on TE25: Activity Name: Assign Final Building Checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on TF25: Activity Name: Building close out check list Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 04-Mar-2025 End Date: 04-Mar-2025
Note on TG25: Activity Name: De mobilization (checklist) Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on VM25: Activity Name: Assign post landscaping checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 02-May-2025 End Date: 02-May-2025
Note on C26: Activity Name: Organize site team to have training and certificates Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 28-Sep-2023
Note on CI26: Activity Name: Schedule locates to be done Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 21-Dec-2023 End Date: 27-Dec-2023
Note on FP26: Activity Name: Assign water and sewer and storm checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 15-Mar-2024 End Date: 15-Mar-2024
Note on KA26: Activity Name: Assign window & door installation checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 08-Jul-2024 End Date: 08-Jul-2024
Note on PU26: Activity Name: Assign taping inspection checklist for suites Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 05-Dec-2024 End Date: 05-Dec-2024
Note on QI26: Activity Name: Assign taping inspection checklist for suites Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 19-Dec-2024 End Date: 19-Dec-2024
Note on TF26: Activity Name: Building handover (PM to SM) checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on C27: Activity Name: Hold Pre Kick-Off meeting with Engineers and Trades people Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 02-Oct-2023
Note on C28: Activity Name: 3.0 Pre construction and mobilization Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C29: Activity Name: Assign Equipment & Tools check list Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C30: Activity Name: Assign Health and Safety checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C31: Activity Name: Assign Permits check list Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C32: Activity Name: Assign Procurement Plan check list Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C33: Activity Name: Assign Project Team Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C34: Activity Name: Assign Safety Equipment and Materials checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C35: Activity Name: 3.0, 4.0. 5.0 pre, during and post construction total job Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 05-May-2025
Note on TB39: Activity Name: Install building signage Phase: Sitework Location: Landscaping Trade: Site Sub Start Date: 28-Feb-2025 End Date: 28-Feb-2025
Note on UK39: Activity Name: Rough grade landscaping Phase: Sitework Location: Landscaping Trade: Site Sub Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on UY39: Activity Name: Install landscaping Phase: Sitework Location: Landscaping Trade: Site Sub Start Date: 18-Apr-2025 End Date: 01-May-2025
Note on RB42: Activity Name: Parkade - Taper to rectify deficiencies Phase: Sitework Location: Parkade Trade: Site Sub Start Date: 07-Jan-2025 End Date: 07-Jan-2025
Note on RP42: Activity Name: Parkade - Measurement for template Phase: Sitework Location: Parkade Trade: Site Sub Start Date: 21-Jan-2025 End Date: 21-Jan-2025
Note on CI44: Activity Name: Site Preparation Phase: Sitework Location: Site Trade: Site Sub Start Date: 21-Dec-2023 End Date: 05-Jan-2024
Note on FP44: Activity Name: Site services W/S/S install Phase: Sitework Location: Site Trade: Site Sub Start Date: 15-Mar-2024 End Date: 25-Mar-2024
Note on JQ44: Activity Name: Radon rock install Phase: Sitework Location: Site Trade: Site Sub Start Date: 28-Jun-2024 End Date: 01-Jul-2024
Note on JU44: Activity Name: Install poly Phase: Sitework Location: Site Trade: Site Sub Start Date: 02-Jul-2024 End Date: 02-Jul-2024
Note on LZ44: Activity Name: Form exterior pads Phase: Sitework Location: Site Trade: Site Sub Start Date: 28-Aug-2024 End Date: 03-Sep-2024
Note on MN44: Activity Name: Excatae exterior sidewalks Phase: Sitework Location: Site Trade: Site Sub Start Date: 11-Sep-2024 End Date: 03-Dec-2024
Note on PT44: Activity Name: Form exterior sidewalks Phase: Sitework Location: Site Trade: Site Sub Start Date: 04-Dec-2024 End Date: 06-Dec-2024
Note on CI45: Activity Name: 4.1 Site Services & Foundation Work Phase: Sitework Location: Site Trade: Site Sub Start Date: 21-Dec-2023 End Date: 25-Mar-2024
Note on OJ45: Activity Name: Call the surveyor to measure for condo plan Phase: Sitework Location: Site Trade: Site Sub Start Date: 29-Oct-2024 End Date: 31-Oct-2024
Note on CP46: Activity Name: 18. Assign site prep check list (First) Phase: Sitework Location: Site Trade: Site Sub Start Date: 28-Dec-2023 End Date: 28-Dec-2023
Note on CQ46: Activity Name: Strip site Phase: Sitework Location: Site Trade: Site Sub Start Date: 29-Dec-2023 End Date: 04-Jan-2024
Note on FS46: Activity Name: Structural steel delivered and sorted onsite Phase: Sitework Location: Site Trade: Site Sub Start Date: 18-Mar-2024 End Date: 18-Mar-2024
Note on FS47: Activity Name: Install water and sewer Phase: Sitework Location: Site Trade: Site Sub Start Date: 18-Mar-2024 End Date: 22-Mar-2024
Note on FP51: Activity Name: Strucutral Steel Phase: Structure Location: Interior Bldg Trade: Steel Start Date: 15-Mar-2024 End Date: 21-Mar-2024
Note on GQ51: Activity Name: 4.2 Framing Phase: Structure Location: Interior Bldg Trade: Framing Start Date: 11-Apr-2024 End Date: 03-Jan-2025
Note on FU52: Activity Name: Structural steel erection Phase: Structure Location: Interior Bldg Trade: Steel Start Date: 20-Mar-2024 End Date: 21-Mar-2024
Note on LZ52: Activity Name: Install pocket foor frame Phase: Structure Location: Interior Bldg Trade: Framing Start Date: 28-Aug-2024 End Date: 03-Sep-2024
Note on MI52: Activity Name: Install pocket door frames Phase: Structure Location: Interior Bldg Trade: Framing Start Date: 06-Sep-2024 End Date: 12-Sep-2024
Note on MW52: Activity Name: Install pocket door frames Phase: Structure Location: Interior Bldg Trade: Framing Start Date: 20-Sep-2024 End Date: 26-Sep-2024
Note on QN52: Activity Name: Install metal doors and frames Phase: Structure Location: Interior Bldg Trade: Framing Start Date: 24-Dec-2024 End Date: 06-Jan-2025
Note on PR56: Activity Name: Install suite entry doors and frames and Interior doors, trims and jambs Phase: Structure Location: Level 1 Trade: Framing Start Date: 02-Dec-2024 End Date: 06-Dec-2024
Note on PY56: Activity Name: Install suite entry doors and frames and Interior doors, trims and jambs Phase: Structure Location: Level 1 Trade: Framing Start Date: 09-Dec-2024 End Date: 13-Dec-2024
Note on QM56: Activity Name: Install suite entry doors and frames and Interior doors, trims and jambs Phase: Structure Location: Level 1 Trade: Framing Start Date: 23-Dec-2024 End Date: 03-Jan-2025
Note on GY59: Activity Name: Frame 2nd floor Phase: Structure Location: Level 2 Trade: Framing Start Date: 19-Apr-2024 End Date: 13-May-2024
Note on LS59: Activity Name: Back framing on 2nd Phase: Structure Location: Level 2 Trade: Framing Start Date: 21-Aug-2024 End Date: 27-Aug-2024
Note on PL59: Activity Name: Frame drops on 2nd Phase: Structure Location: Level 2 Trade: Framing Start Date: 26-Nov-2024 End Date: 02-Dec-2024
Note on GY60: Activity Name: Framing 2nd floor Phase: Structure Location: Level 2 Trade: Framing Start Date: 19-Apr-2024 End Date: 14-May-2024
Note on IL63: Activity Name: Frame 3rd floor Phase: Structure Location: Level 3 Trade: Framing Start Date: 28-May-2024 End Date: 07-Jun-2024
Note on KP63: Activity Name: Layout suites on 3rd floor Phase: Structure Location: Level 3 Trade: Framing Start Date: 23-Jul-2024 End Date: 26-Jul-2024
Note on MM63: Activity Name: Back framing on 3rd Phase: Structure Location: Level 3 Trade: Framing Start Date: 10-Sep-2024 End Date: 16-Sep-2024
Note on OX63: Activity Name: Frame drops on 3rd Phase: Structure Location: Level 3 Trade: Framing Start Date: 12-Nov-2024 End Date: 18-Nov-2024
Note on IL64: Activity Name: Framing 3rd floor Phase: Structure Location: Level 3 Trade: Framing Start Date: 28-May-2024 End Date: 26-Jul-2024
Note on JH68: Activity Name: Frame 4th floor Phase: Structure Location: Level 4 Trade: Framing Start Date: 19-Jun-2024 End Date: 05-Jul-2024
Note on MZ68: Activity Name: Back framing on 4th Phase: Structure Location: Level 4 Trade: Framing Start Date: 23-Sep-2024 End Date: 27-Sep-2024
Note on OP68: Activity Name: 4th floor framing inspection Phase: Structure Location: Level 4 Trade: Inspection Start Date: 04-Nov-2024 End Date: 04-Nov-2024
Note on PO68: Activity Name: Frame drops on 4th Phase: Structure Location: Level 4 Trade: Framing Start Date: 29-Nov-2024 End Date: 05-Dec-2024
Note on JH69: Activity Name: Framing 4th floor Phase: Structure Location: Level 4 Trade: Framing Start Date: 19-Jun-2024 End Date: 31-Jul-2024
Note on GQ73: Activity Name: Frame parkade level Phase: Structure Location: Parkade Trade: Framing Start Date: 11-Apr-2024 End Date: 15-Apr-2024
Note on LQ73: Activity Name: Frame interior parkade walls Phase: Structure Location: Parkade Trade: Framing Start Date: 19-Aug-2024 End Date: 23-Aug-2024
Note on QF73: Activity Name: Frame and board Parkade beams Phase: Structure Location: Parkade Trade: Framing Start Date: 16-Dec-2024 End Date: 20-Dec-2024
Note on GQ74: Activity Name: Framing parkade Phase: Structure Location: Parkade Trade: Framing Start Date: 11-Apr-2024 End Date: 16-Apr-2024
Note on KB77: Activity Name: Install roof trusses and sheeting and towers Phase: Structure Location: Roof Trade: Framing Start Date: 09-Jul-2024 End Date: 06-Aug-2024
Note on LE77: Activity Name: Assign roof trusses framing checklist Phase: Structure Location: Roof Trade: Framing Start Date: 07-Aug-2024 End Date: 07-Aug-2024
Note on KB78: Activity Name: Roof trusses install Phase: Structure Location: Roof Trade: Framing Start Date: 09-Jul-2024 End Date: 20-Aug-2024
Note on JA80: Activity Name: Mechanical rough in in slab Phase: Rough-Ins Location: Interior Bldg Trade: Mechanical Start Date: 12-Jun-2024 End Date: 18-Jun-2024
Note on KJ80: Activity Name: Deliver tubs & showers to suites / checklist Phase: Rough-Ins Location: Interior Bldg Trade: Plumbing Start Date: 17-Jul-2024 End Date: 18-Jul-2024
Note on KW80: Activity Name: Install stairs Phase: Rough-Ins Location: Interior Bldg Trade: Vertical Flow Start Date: 30-Jul-2024 End Date: 30-Jul-2024
Note on LC80: Activity Name: Mechanical rough in in ceiling Phase: Rough-Ins Location: Interior Bldg Trade: Mechanical Start Date: 05-Aug-2024 End Date: 14-Aug-2024
Note on LX80: Activity Name: Electrical rough in in ceiling Phase: Rough-Ins Location: Interior Bldg Trade: Electrical Start Date: 26-Aug-2024 End Date: 03-Sep-2024
Note on MI80: Activity Name: Install tubs and showers Phase: Rough-Ins Location: Interior Bldg Trade: Plumbing Start Date: 06-Sep-2024 End Date: 11-Sep-2024
Note on NC80: Activity Name: Install tubs and showers Phase: Rough-Ins Location: Interior Bldg Trade: Plumbing Start Date: 26-Sep-2024 End Date: 27-Sep-2024
Note on NU80: Activity Name: Delivery of Elevator & Install Phase: Rough-Ins Location: Interior Bldg Trade: Vertical Flow Start Date: 14-Oct-2024 End Date: 03-Jan-2025
Note on RQ80: Activity Name: Assign pre board inspection checklist Phase: Rough-Ins Location: Interior Bldg Trade: Drywall Start Date: 22-Jan-2025 End Date: 22-Jan-2025
Note on UR80: Activity Name: Install underground sprinklers Phase: Rough-Ins Location: Interior Bldg Trade: Sprinkler Start Date: 11-Apr-2025 End Date: 17-Apr-2025
Note on JA81: Activity Name: Electrical rough in in slab Phase: Rough-Ins Location: Interior Bldg Trade: Electrical Start Date: 12-Jun-2024 End Date: 18-Jun-2024
Note on LC81: Activity Name: 4.3 Rough In, Steel Stud Drywall Phase: Rough-Ins Location: Interior Bldg Trade: Drywall Start Date: 05-Aug-2024 End Date: 23-Jan-2025
Note on LE82: Activity Name: Sprinkler install in attic Phase: Rough-Ins Location: Interior Bldg Trade: Sprinkler Start Date: 07-Aug-2024 End Date: 21-Aug-2024
Note on MB82: Activity Name: Install tubs and showers Phase: Rough-Ins Location: Interior Bldg Trade: Plumbing Start Date: 30-Aug-2024 End Date: 04-Sep-2024
Note on OT82: Activity Name: Assign Corridor & Stairwell pre board inspection checklist Phase: Rough-Ins Location: Interior Bldg Trade: Drywall Start Date: 08-Nov-2024 End Date: 08-Nov-2024
Note on OX82: Activity Name: Assign corridor & stairwell pre board inspection checklist Phase: Rough-Ins Location: Interior Bldg Trade: Drywall Start Date: 12-Nov-2024 End Date: 12-Nov-2024
Note on PA82: Activity Name: Assign pre board inspection check list Phase: Rough-Ins Location: Interior Bldg Trade: Drywall Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on PG82: Activity Name: Rough in interior walls Phase: Rough-Ins Location: Interior Bldg Trade: Rough-In (General) Start Date: 21-Nov-2024 End Date: 04-Dec-2024
Note on PV82: Activity Name: Board and prepare electrical/mechanical room Phase: Rough-Ins Location: Interior Bldg Trade: Drywall Start Date: 06-Dec-2024 End Date: 10-Dec-2024
Note on RQ82: Activity Name: Assign pre board inspection checklist Phase: Rough-Ins Location: Interior Bldg Trade: Drywall Start Date: 22-Jan-2025 End Date: 22-Jan-2025
Note on OT83: Activity Name: Assign pre board interior walls checklist Phase: Rough-Ins Location: Interior Bldg Trade: Drywall Start Date: 08-Nov-2024 End Date: 08-Nov-2024
Note on PA83: Activity Name: Assign pre board interior walls checklist Phase: Rough-Ins Location: Interior Bldg Trade: Drywall Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on PK83: Activity Name: Gypcrete Phase: Rough-Ins Location: Interior Bldg Trade: Gypcrete Start Date: 25-Nov-2024 End Date: 26-Nov-2024
Note on PN83: Activity Name: Assign Corridor & Stairwell pre board inspection checklist Phase: Rough-Ins Location: Interior Bldg Trade: Drywall Start Date: 28-Nov-2024 End Date: 28-Nov-2024
Note on PN84: Activity Name: Assign pre board inspection check list Phase: Rough-Ins Location: Interior Bldg Trade: Drywall Start Date: 28-Nov-2024 End Date: 28-Nov-2024
Note on PN85: Activity Name: Assign pre board interior walls checklist Phase: Rough-Ins Location: Interior Bldg Trade: Drywall Start Date: 28-Nov-2024 End Date: 28-Nov-2024
Note on PN86: Activity Name: Main service electrical room install Phase: Rough-Ins Location: Interior Bldg Trade: Electrical Start Date: 28-Nov-2024 End Date: 26-Dec-2024
Note on PN87: Activity Name: Main service mechanical room install Phase: Rough-Ins Location: Interior Bldg Trade: Mechanical Start Date: 28-Nov-2024 End Date: 22-Jan-2025
Note on SK91: Activity Name: Electrical finishing on 1 Phase: Rough-Ins Location: Level 1 Trade: Electrical Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on SK92: Activity Name: Mechanical finishing on 1 Phase: Rough-Ins Location: Level 1 Trade: Mechanical Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on SK93: Activity Name: Sprinkler finishing on 1 Phase: Rough-Ins Location: Level 1 Trade: Sprinkler Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on KK94: Activity Name: Layout suites on 2nd floor Phase: Rough-Ins Location: Level 2 Trade: Drywall Start Date: 18-Jul-2024 End Date: 22-Jul-2024
Note on LJ94: Activity Name: Steel stud install on 2nd & drywall behind the tubs including fire wall taping if it is a fire wall Phase: Rough-Ins Location: Level 2 Trade: Drywall Start Date: 12-Aug-2024 End Date: 29-Aug-2024
Note on MB94: Activity Name: Board upper 16" strips in common area and all suites on 2nd Phase: Rough-Ins Location: Level 2 Trade: Drywall Start Date: 30-Aug-2024 End Date: 04-Sep-2024
Note on OM94: Activity Name: Mechanical rough in hallways & stairwells on 2nd Phase: Rough-Ins Location: Level 2 Trade: Mechanical Start Date: 01-Nov-2024 End Date: 15-Nov-2024
Note on PK94: Activity Name: Fire tape / Fire caulk upper strips on 2nd Phase: Rough-Ins Location: Level 2 Trade: Drywall Start Date: 25-Nov-2024 End Date: 25-Nov-2024
Note on PN94: Activity Name: Board 2nd floor hallways and stairwells Phase: Rough-Ins Location: Level 2 Trade: Drywall Start Date: 28-Nov-2024 End Date: 04-Dec-2024
Note on PU94: Activity Name: Tape suites on 2nd Phase: Rough-Ins Location: Level 2 Trade: Drywall Start Date: 05-Dec-2024 End Date: 19-Dec-2024
Note on SG94: Activity Name: Electrical finishing 2nd floor Phase: Rough-Ins Location: Level 2 Trade: Electrical Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on LX95: Activity Name: Sprinkler rough in corridor & stairwells on 2nd Phase: Rough-Ins Location: Level 2 Trade: Sprinkler Start Date: 26-Aug-2024 End Date: 06-Sep-2024
Note on OM95: Activity Name: Mechanical rough in on 2nd Phase: Rough-Ins Location: Level 2 Trade: Mechanical Start Date: 01-Nov-2024 End Date: 15-Nov-2024
Note on PN95: Activity Name: Board 2nd floor walls Phase: Rough-Ins Location: Level 2 Trade: Drywall Start Date: 28-Nov-2024 End Date: 04-Dec-2024
Note on SG95: Activity Name: Mechanical finishing 2nd floor Phase: Rough-Ins Location: Level 2 Trade: Mechanical Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on LX96: Activity Name: Sprinkler rough in on 2nd Phase: Rough-Ins Location: Level 2 Trade: Sprinkler Start Date: 26-Aug-2024 End Date: 06-Sep-2024
Note on OT96: Activity Name: Electrical rough in hallways & stairwells on 2nd Phase: Rough-Ins Location: Level 2 Trade: Electrical Start Date: 08-Nov-2024 End Date: 22-Nov-2024
Note on SG96: Activity Name: Sprinkler finishing 2nd floor Phase: Rough-Ins Location: Level 2 Trade: Sprinkler Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on OT97: Activity Name: Electrical rough in on 2nd Phase: Rough-Ins Location: Level 2 Trade: Electrical Start Date: 08-Nov-2024 End Date: 22-Nov-2024
Note on MB99: Activity Name: Steel stud install on 3rd & drywall behind the tubs including fire wall taping if it is a fire wall Phase: Rough-Ins Location: Level 3 Trade: Drywall Start Date: 30-Aug-2024 End Date: 05-Sep-2024
Note on ML99: Activity Name: Sprinkler rough in hallways & stairwells on 3rd Phase: Rough-Ins Location: Level 3 Trade: Sprinkler Start Date: 09-Sep-2024 End Date: 20-Sep-2024
Note on OI99: Activity Name: Mechanical rough in hallways & stairwells on 3rd Phase: Rough-Ins Location: Level 3 Trade: Mechanical Start Date: 28-Oct-2024 End Date: 07-Nov-2024
Note on OW99: Activity Name: Fire tape / Fire caulk upper strips on 3rd Phase: Rough-Ins Location: Level 3 Trade: Drywall Start Date: 11-Nov-2024 End Date: 11-Nov-2024
Note on PA99: Activity Name: Load boards on floor and Board 3rd floor walls Phase: Rough-Ins Location: Level 3 Trade: Drywall Start Date: 15-Nov-2024 End Date: 22-Nov-2024
Note on RX99: Activity Name: Electrical finishing on 3rd Phase: Rough-Ins Location: Level 3 Trade: Electrical Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on ML100: Activity Name: Sprinkler rough in on 3rd Phase: Rough-Ins Location: Level 3 Trade: Sprinkler Start Date: 09-Sep-2024 End Date: 20-Sep-2024
Note on OI100: Activity Name: Mechanical rough in on 3rd Phase: Rough-Ins Location: Level 3 Trade: Mechanical Start Date: 28-Oct-2024 End Date: 07-Nov-2024
Note on PA100: Activity Name: Load boards on floor and Board exterior walls on 3rd and sheds Phase: Rough-Ins Location: Level 3 Trade: Drywall Start Date: 15-Nov-2024 End Date: 22-Nov-2024
Note on RX100: Activity Name: Mechanical finishing on 3rd Phase: Rough-Ins Location: Level 3 Trade: Mechanical Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on MN101: Activity Name: Board upper 16" strips in common area & all suites on 3rd Phase: Rough-Ins Location: Level 3 Trade: Drywall Start Date: 11-Sep-2024 End Date: 16-Sep-2024
Note on OI101: Activity Name: Electrical rough in hallways & stairwells on 3rd Phase: Rough-Ins Location: Level 3 Trade: Electrical Start Date: 28-Oct-2024 End Date: 08-Nov-2024
Note on PA101: Activity Name: Load the board on floor and Board 3rd floor hallways and stairwells Phase: Rough-Ins Location: Level 3 Trade: Drywall Start Date: 15-Nov-2024 End Date: 22-Nov-2024
Note on RX101: Activity Name: Sprinkler finishing on 3rd Phase: Rough-Ins Location: Level 3 Trade: Sprinkler Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on OI102: Activity Name: Electrical rough in on 3rd Phase: Rough-Ins Location: Level 3 Trade: Electrical Start Date: 28-Oct-2024 End Date: 08-Nov-2024
Note on PH102: Activity Name: Tape suites on 3rd Phase: Rough-Ins Location: Level 3 Trade: Drywall Start Date: 22-Nov-2024 End Date: 05-Dec-2024
Note on MN104: Activity Name: Install drywall on 4th floor ceiling Phase: Rough-Ins Location: Level 4 Trade: Drywall Start Date: 11-Sep-2024 End Date: 17-Sep-2024
Note on MU104: Activity Name: Steel stud install on 4th & drywall behind the tubs including fire wall taping if it is a fire wall Phase: Rough-Ins Location: Level 4 Trade: Drywall Start Date: 18-Sep-2024 End Date: 26-Sep-2024
Note on ND104: Activity Name: Board upper 16" strips in common area and all suites on 4th Phase: Rough-Ins Location: Level 4 Trade: Drywall Start Date: 27-Sep-2024 End Date: 02-Oct-2024
Note on OB104: Activity Name: Mechanical rough in hallways stairwells on 4th Phase: Rough-Ins Location: Level 4 Trade: Mechanical Start Date: 21-Oct-2024 End Date: 25-Oct-2024
Note on OM104: Activity Name: Fire tape / Fire caulk upper strips on 4th Phase: Rough-Ins Location: Level 4 Trade: Drywall Start Date: 01-Nov-2024 End Date: 01-Nov-2024
Note on OT104: Activity Name: Load the board on floor and Board 4th floor hallways and stairwells Phase: Rough-Ins Location: Level 4 Trade: Drywall Start Date: 08-Nov-2024 End Date: 15-Nov-2024
Note on RP104: Activity Name: Electrical finishing on 4th Phase: Rough-Ins Location: Level 4 Trade: Electrical Start Date: 21-Jan-2025 End Date: 27-Jan-2025
Note on MZ105: Activity Name: Sprinkler rough in hallways stairwells on 4th Phase: Rough-Ins Location: Level 4 Trade: Sprinkler Start Date: 23-Sep-2024 End Date: 30-Sep-2024
Note on OB105: Activity Name: Mechanical rough in on 4th Phase: Rough-Ins Location: Level 4 Trade: Mechanical Start Date: 21-Oct-2024 End Date: 25-Oct-2024
Note on OT105: Activity Name: Load the board on floor and Board 4th floor walls Phase: Rough-Ins Location: Level 4 Trade: Drywall Start Date: 08-Nov-2024 End Date: 15-Nov-2024
Note on RP105: Activity Name: Mechanical finishing on 4th Phase: Rough-Ins Location: Level 4 Trade: Mechanical Start Date: 21-Jan-2025 End Date: 27-Jan-2025
Note on MZ106: Activity Name: Sprinkler rough in on 4th Phase: Rough-Ins Location: Level 4 Trade: Sprinkler Start Date: 23-Sep-2024 End Date: 30-Sep-2024
Note on OB106: Activity Name: Electrical rough in hallways stairwells on 4th Phase: Rough-Ins Location: Level 4 Trade: Electrical Start Date: 21-Oct-2024 End Date: 31-Oct-2024
Note on OT106: Activity Name: Load the board on floor and Board exterior walls on 4th and sheds Phase: Rough-Ins Location: Level 4 Trade: Drywall Start Date: 08-Nov-2024 End Date: 15-Nov-2024
Note on RP106: Activity Name: Sprinkler finishing on 4th Phase: Rough-Ins Location: Level 4 Trade: Sprinkler Start Date: 21-Jan-2025 End Date: 27-Jan-2025
Note on OB107: Activity Name: Electrical rough in on 4th Phase: Rough-Ins Location: Level 4 Trade: Electrical Start Date: 21-Oct-2024 End Date: 31-Oct-2024
Note on PA107: Activity Name: Tape suites on 4th Phase: Rough-Ins Location: Level 4 Trade: Drywall Start Date: 15-Nov-2024 End Date: 28-Nov-2024
Note on OB108: Activity Name: Rough in exterior walls on 4th and sheds Phase: Rough-Ins Location: Level 4 Trade: Rough-In (General) Start Date: 21-Oct-2024 End Date: 31-Oct-2024
Note on JA109: Activity Name: Rough in parkade slab Phase: Rough-Ins Location: Parkade Trade: Rough-In (General) Start Date: 12-Jun-2024 End Date: 26-Jun-2024
Note on QC109: Activity Name: Tape parkade interior and exterior walls Phase: Rough-Ins Location: Parkade Trade: Drywall Start Date: 13-Dec-2024 End Date: 23-Dec-2024
Note on OT111: Activity Name: Rough in exterior walls on 2nd and sheds Phase: Exteriors Location: Level 2 Trade: Rough-In (General) Start Date: 08-Nov-2024 End Date: 21-Nov-2024
Note on PH111: Activity Name: Siding 2nd floor Phase: Exteriors Location: Level 2 Trade: Siding Start Date: 22-Nov-2024 End Date: 09-Dec-2024
Note on PK112: Activity Name: Poly and insulate on 2nd exterior walls Phase: Exteriors Location: Level 2 Trade: Insulation Start Date: 25-Nov-2024 End Date: 28-Nov-2024
Note on PN113: Activity Name: Board exterior walls on 2nd and sheds Phase: Exteriors Location: Level 2 Trade: Exteriors Start Date: 28-Nov-2024 End Date: 04-Dec-2024
Note on OI115: Activity Name: Rough in exterior walls on 3rd and sheds Phase: Exteriors Location: Level 3 Trade: Rough-In (General) Start Date: 28-Oct-2024 End Date: 08-Nov-2024
Note on OX115: Activity Name: Poly and insulate on 3rd exterior walls Phase: Exteriors Location: Level 3 Trade: Insulation Start Date: 12-Nov-2024 End Date: 15-Nov-2024
Note on SS115: Activity Name: Organize 3rd party building exterior review, including roof, siding and flashings Phase: Exteriors Location: Level 3 Trade: Exteriors Start Date: 19-Feb-2025 End Date: 19-Feb-2025
Note on OR116: Activity Name: Siding 3rd floor Phase: Exteriors Location: Level 3 Trade: Siding Start Date: 06-Nov-2024 End Date: 21-Nov-2024
Note on OB119: Activity Name: Siding 4th floor Phase: Exteriors Location: Level 4 Trade: Siding Start Date: 21-Oct-2024 End Date: 05-Nov-2024
Note on OQ120: Activity Name: Poly and insulate on 4th exterior walls Phase: Exteriors Location: Level 4 Trade: Insulation Start Date: 05-Nov-2024 End Date: 07-Nov-2024
Note on KA121: Activity Name: install windows and doors Phase: Exteriors Location: Outside Bldg Trade: Windows Start Date: 08-Jul-2024 End Date: 26-Nov-2024
Note on PM121: Activity Name: Siding towers Phase: Exteriors Location: Outside Bldg Trade: Siding Start Date: 27-Nov-2024 End Date: 16-Dec-2024
Note on QN121: Activity Name: Assign siding checklist Phase: Exteriors Location: Outside Bldg Trade: Siding Start Date: 24-Dec-2024 End Date: 24-Dec-2024
Note on LE122: Activity Name: Roofing and water proofing Phase: Exteriors Location: Outside Bldg Trade: Exteriors Start Date: 07-Aug-2024 End Date: 23-Aug-2024
Note on MF122: Activity Name: Building paper the whole building Phase: Exteriors Location: Outside Bldg Trade: Exteriors Start Date: 03-Sep-2024 End Date: 25-Nov-2024
Note on PZ122: Activity Name: Assign siding checklist Phase: Exteriors Location: Outside Bldg Trade: Siding Start Date: 10-Dec-2024 End Date: 10-Dec-2024
Note on LG123: Activity Name: Grind all balconys smooth Phase: Exteriors Location: Outside Bldg Trade: Exteriors Start Date: 09-Aug-2024 End Date: 22-Aug-2024
Note on MF123: Activity Name: Soffit & Tower Siding Phase: Exteriors Location: Outside Bldg Trade: Siding Start Date: 03-Sep-2024 End Date: 03-Jan-2025
Note on LG124: Activity Name: Exterior Phase: Exteriors Location: Outside Bldg Trade: Exteriors Start Date: 09-Aug-2024 End Date: 05-May-2025
Note on LJ125: Activity Name: Install roofing and water proofing Phase: Exteriors Location: Outside Bldg Trade: Exteriors Start Date: 12-Aug-2024 End Date: 23-Aug-2024
Note on MU125: Activity Name: Blow in attic insulation Phase: Exteriors Location: Outside Bldg Trade: Exteriors Start Date: 18-Sep-2024 End Date: 20-Sep-2024
Note on OR125: Activity Name: Assign siding checklist Phase: Exteriors Location: Outside Bldg Trade: Siding Start Date: 06-Nov-2024 End Date: 06-Nov-2024
Note on PH125: Activity Name: Assign siding checklist Phase: Exteriors Location: Outside Bldg Trade: Siding Start Date: 22-Nov-2024 End Date: 22-Nov-2024
Note on LQ129: Activity Name: Rough in Parkade Phase: Exteriors Location: Parkade Trade: Rough-In (General) Start Date: 19-Aug-2024 End Date: 23-Jan-2025
Note on LT130: Activity Name: Poly and insulate parkade exterior walls Phase: Exteriors Location: Parkade Trade: Insulation Start Date: 22-Aug-2024 End Date: 23-Aug-2024
Note on PD130: Activity Name: Rough in exterior walls - parkade and sheds Phase: Exteriors Location: Parkade Trade: Rough-In (General) Start Date: 18-Nov-2024 End Date: 06-Dec-2024
Note on PY130: Activity Name: Board parkade exterior walls and sheds Phase: Exteriors Location: Parkade Trade: Exteriors Start Date: 09-Dec-2024 End Date: 09-Dec-2024
Note on PZ130: Activity Name: Board Parkade interior walls Phase: Exteriors Location: Parkade Trade: Exteriors Start Date: 10-Dec-2024 End Date: 13-Dec-2024
Note on PZ131: Activity Name: Siding parkade level Phase: Exteriors Location: Parkade Trade: Siding Start Date: 10-Dec-2024 End Date: 23-Dec-2024
Note on FZ135: Activity Name: Assign water and sewer commissioning checklist Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 25-Mar-2024 End Date: 25-Mar-2024
Note on KY135: Activity Name: Install windows & doors all floors Phase: Finishes Location: Interior Bldg Trade: Flooring Start Date: 01-Aug-2024 End Date: 13-Aug-2024
Note on LR135: Activity Name: Call for structural inspection Phase: Finishes Location: Interior Bldg Trade: Inspection Start Date: 20-Aug-2024 End Date: 20-Aug-2024
Note on MF135: Activity Name: Install exterior decking all floors Phase: Finishes Location: Interior Bldg Trade: Exteriors Start Date: 03-Sep-2024 End Date: 16-Sep-2024
Note on OL135: Activity Name: Call for Electrical and Mechanical inspection Phase: Finishes Location: Interior Bldg Trade: Inspection Start Date: 31-Oct-2024 End Date: 31-Oct-2024
Note on OX135: Activity Name: Call for Mechanical and Electrical Inspection Phase: Finishes Location: Interior Bldg Trade: Inspection Start Date: 12-Nov-2024 End Date: 12-Nov-2024
Note on PK135: Activity Name: Call for Mechanical and Electrical inspection Phase: Finishes Location: Interior Bldg Trade: Inspection Start Date: 25-Nov-2024 End Date: 25-Nov-2024
Note on PL135: Activity Name: Call for envelope reviewer inspection Phase: Finishes Location: Interior Bldg Trade: Inspection Start Date: 26-Nov-2024 End Date: 26-Nov-2024
Note on RO135: Activity Name: Install railings on all floors Phase: Finishes Location: Interior Bldg Trade: Flooring Start Date: 20-Jan-2025 End Date: 06-Feb-2025
Note on SM135: Activity Name: Final coat of paint Phase: Finishes Location: Interior Bldg Trade: Paint Start Date: 13-Feb-2025 End Date: 25-Feb-2025
Note on TA135: Activity Name: Final suite clean Phase: Finishes Location: Interior Bldg Trade: Cleaning Start Date: 27-Feb-2025 End Date: 28-Feb-2025
Note on TE135: Activity Name: Move in dates confirmed Phase: Finishes Location: Interior Bldg Trade: COO Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on TF135: Activity Name: Load home owners into copper Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 04-Mar-2025
Note on TG135: Activity Name: Send out contractor surveys Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 05-Mar-2025 End Date: 05-Mar-2025
Note on TH135: Activity Name: Schedule 1 on 1 contractor review meetings Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 06-Mar-2025 End Date: 12-Mar-2025
Note on TO135: Activity Name: Project post mordem internal Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 13-Mar-2025 End Date: 13-Mar-2025
Note on TT135: Activity Name: Move info to Dev co work flow 1.0, 2.0, 6.0 Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 18-Mar-2025 End Date: 18-Mar-2025
Note on VM135: Activity Name: Commision landscaping Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 02-May-2025 End Date: 05-May-2025
Note on FZ136: Activity Name: Commision Water/sewer/storm Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 25-Mar-2024 End Date: 25-Mar-2024
Note on LG136: Activity Name: 4.4 Finishing Phase: Finishes Location: Interior Bldg Trade: Finishing Start Date: 09-Aug-2024 End Date: 05-May-2025
Note on MG137: Activity Name: Call for Mechanical & Electrical inspection of attic Phase: Finishes Location: Interior Bldg Trade: Inspection Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on RR137: Activity Name: Call for Electrical and Mechanical Inspection Phase: Finishes Location: Interior Bldg Trade: Inspection Start Date: 23-Jan-2025 End Date: 23-Jan-2025
Note on RS137: Activity Name: Final coat of paint Phase: Finishes Location: Interior Bldg Trade: Paint Start Date: 24-Jan-2025 End Date: 05-Feb-2025
Note on SN137: Activity Name: Contact Canada Post to get the address's created Phase: Finishes Location: Interior Bldg Trade: Inspection Start Date: 14-Feb-2025 End Date: 14-Feb-2025
Note on SS137: Activity Name: Architectural walk throughs Phase: Finishes Location: Interior Bldg Trade: Inspection Start Date: 19-Feb-2025 End Date: 20-Feb-2025
Note on SU137: Activity Name: Building inspector walk throughs Phase: Finishes Location: Interior Bldg Trade: Inspection Start Date: 21-Feb-2025 End Date: 24-Feb-2025
Note on SY137: Activity Name: Prepare occupancy paperwork Phase: Finishes Location: Interior Bldg Trade: COO Start Date: 25-Feb-2025 End Date: 26-Feb-2025
Note on TA137: Activity Name: Receive occupancy Phase: Finishes Location: Interior Bldg Trade: COO Start Date: 27-Feb-2025 End Date: 28-Feb-2025
Note on TE137: Activity Name: Pre sale move in dates confirmed Phase: Finishes Location: Interior Bldg Trade: COO Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on TF137: Activity Name: Update home owner permissions in Construction online Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 04-Mar-2025
Note on TG137: Activity Name: Building close out cleanup deficiencies confirmed Phase: Finishes Location: Interior Bldg Trade: Cleaning Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on TN137: Activity Name: Home owner walk through punch list clean up Phase: Finishes Location: Interior Bldg Trade: Cleaning Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on SC138: Activity Name: Final coat of paint Phase: Finishes Location: Interior Bldg Trade: Paint Start Date: 03-Feb-2025 End Date: 13-Feb-2025
Note on SN138: Activity Name: Fire alarm verification Phase: Finishes Location: Interior Bldg Trade: Inspection Start Date: 14-Feb-2025 End Date: 17-Feb-2025
Note on SS138: Activity Name: Enginering walk throughs Phase: Finishes Location: Interior Bldg Trade: Inspection Start Date: 19-Feb-2025 End Date: 20-Feb-2025
Note on TE138: Activity Name: 5.0 Sales, Occupancy, Closings Phase: Finishes Location: Interior Bldg Trade: COO Start Date: 03-Mar-2025 End Date: 01-May-2025
Note on SN139: Activity Name: Sprinkler testing Phase: Finishes Location: Interior Bldg Trade: Inspection Start Date: 14-Feb-2025 End Date: 17-Feb-2025
Note on TF139: Activity Name: Finalize home owner extras Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on TM139: Activity Name: Home owner walk through and punch list Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 11-Mar-2025 End Date: 11-Mar-2025
Note on SN140: Activity Name: Elevator commissioning Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 14-Feb-2025 End Date: 17-Feb-2025
Note on TF140: Activity Name: Move in binders created Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on TM140: Activity Name: Unit Commissioning deficiency clean up confirmed Phase: Finishes Location: Interior Bldg Trade: Cleaning Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on SN141: Activity Name: Final commissioning and deficiency Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 14-Feb-2025 End Date: 03-Mar-2025
Note on TF141: Activity Name: Unit Commissioning Inspection list Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on TF142: Activity Name: Keys and gift cards and welcome package created Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on TF143: Activity Name: New move ins and warranty through service manager Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 01-May-2025
Note on TH144: Activity Name: Schedule contractor group meeting to review survey results Phase: Finishes Location: Interior Bldg Trade: CX Start Date: 06-Mar-2025 End Date: 12-Mar-2025
Note on QW148: Activity Name: Ceiling texture on 1 Phase: Finishes Location: Level 1 Trade: Finishing Start Date: 02-Jan-2025 End Date: 03-Jan-2025
Note on RC148: Activity Name: Install interior doors and case on 1 Phase: Finishes Location: Level 1 Trade: Carpentry Start Date: 08-Jan-2025 End Date: 09-Jan-2025
Note on RE148: Activity Name: Spray out closet interiors and trim on 1 Phase: Finishes Location: Level 1 Trade: Carpentry Start Date: 10-Jan-2025 End Date: 10-Jan-2025
Note on RJ148: Activity Name: Install flooring on 1 Phase: Finishes Location: Level 1 Trade: Flooring Start Date: 15-Jan-2025 End Date: 16-Jan-2025
Note on RL148: Activity Name: Install cabinets on 1 Phase: Finishes Location: Level 1 Trade: Carpentry Start Date: 17-Jan-2025 End Date: 20-Jan-2025
Note on SJ148: Activity Name: Install countertops on 1 Phase: Finishes Location: Level 1 Trade: Carpentry Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on SN148: Activity Name: Construction clean on 1 Phase: Finishes Location: Level 1 Trade: Cleaning Start Date: 14-Feb-2025 End Date: 18-Feb-2025
Note on SS148: Activity Name: Assign Unit Commissioning Inspection list on 1 Phase: Finishes Location: Level 1 Trade: CX Start Date: 19-Feb-2025 End Date: 19-Feb-2025
Note on ST148: Activity Name: Final suite clean on 1 Phase: Finishes Location: Level 1 Trade: Cleaning Start Date: 20-Feb-2025 End Date: 24-Feb-2025
Note on QW149: Activity Name: finishing parkade level 1 Phase: Finishes Location: Level 1 Trade: Finishing Start Date: 02-Jan-2025 End Date: 24-Feb-2025
Note on QX150: Activity Name: Prime paint on 1 Phase: Finishes Location: Level 1 Trade: Paint Start Date: 03-Jan-2025 End Date: 07-Jan-2025
Note on RE150: Activity Name: Paint 1rst coat of color on 1 Phase: Finishes Location: Level 1 Trade: Paint Start Date: 10-Jan-2025 End Date: 16-Jan-2025
Note on KQ152: Activity Name: Core floors begin at 2nd Phase: Finishes Location: Level 2 Trade: Flooring Start Date: 24-Jul-2024 End Date: 26-Jul-2024
Note on LJ152: Activity Name: Rough in 2nd floor Phase: Finishes Location: Level 2 Trade: Rough-In (General) Start Date: 12-Aug-2024 End Date: 03-Jan-2025
Note on RC152: Activity Name: Install flooring 2nd floor Phase: Finishes Location: Level 2 Trade: Flooring Start Date: 08-Jan-2025 End Date: 16-Jan-2025
Note on RL152: Activity Name: Install base and hardware 2nd floor Phase: Finishes Location: Level 2 Trade: Carpentry Start Date: 17-Jan-2025 End Date: 24-Jan-2025
Note on SX152: Activity Name: Construction clean 2nd floor Phase: Finishes Location: Level 2 Trade: Cleaning Start Date: 24-Feb-2025 End Date: 27-Feb-2025
Note on LQ153: Activity Name: Water dams 2nd floor Phase: Finishes Location: Level 2 Trade: Plumbing Start Date: 19-Aug-2024 End Date: 23-Aug-2024
Note on PU153: Activity Name: Tape 2nd floor hallways and stair wells Phase: Finishes Location: Level 2 Trade: Drywall Start Date: 05-Dec-2024 End Date: 19-Dec-2024
Note on QM153: Activity Name: 2nd floor - Taper do the rectification of deficiences Phase: Finishes Location: Level 2 Trade: Flooring Start Date: 23-Dec-2024 End Date: 23-Dec-2024
Note on QQ153: Activity Name: Paint 1st coat of color 2nd floor Phase: Finishes Location: Level 2 Trade: Paint Start Date: 27-Dec-2024 End Date: 03-Jan-2025
Note on RH153: Activity Name: Install cabinets 2nd floor Phase: Finishes Location: Level 2 Trade: Carpentry Start Date: 13-Jan-2025 End Date: 17-Jan-2025
Note on RP153: Activity Name: Manufacturing and Install countertops 2nd floor Phase: Finishes Location: Level 2 Trade: Carpentry Start Date: 21-Jan-2025 End Date: 07-Feb-2025
Note on TA153: Activity Name: Assign Unit Commissioning Inspection list 2nd floor Phase: Finishes Location: Level 2 Trade: CX Start Date: 27-Feb-2025 End Date: 27-Feb-2025
Note on QF154: Activity Name: Ceiling texture on 2nd Phase: Finishes Location: Level 2 Trade: Finishing Start Date: 16-Dec-2024 End Date: 17-Dec-2024
Note on QH154: Activity Name: Prime paint on 2nd Phase: Finishes Location: Level 2 Trade: Paint Start Date: 18-Dec-2024 End Date: 23-Dec-2024
Note on RK154: Activity Name: 2nd floor counter top measurement for template Phase: Finishes Location: Level 2 Trade: Flooring Start Date: 16-Jan-2025 End Date: 20-Jan-2025
Note on QF155: Activity Name: 2nd floor finishing Phase: Finishes Location: Level 2 Trade: Flooring Start Date: 16-Dec-2024 End Date: 28-Feb-2025
Note on QM156: Activity Name: Install interior doors and case on 2nd Phase: Finishes Location: Level 2 Trade: Carpentry Start Date: 23-Dec-2024 End Date: 03-Jan-2025
Note on KV159: Activity Name: Core floor beings at 3rd floor Phase: Finishes Location: Level 3 Trade: Flooring Start Date: 29-Jul-2024 End Date: 31-Jul-2024
Note on LQ159: Activity Name: Water dams 3rd floor Phase: Finishes Location: Level 3 Trade: Plumbing Start Date: 19-Aug-2024 End Date: 23-Aug-2024
Note on PH159: Activity Name: Tape 3rd floor hallways and stair wells Phase: Finishes Location: Level 3 Trade: Drywall Start Date: 22-Nov-2024 End Date: 05-Dec-2024
Note on PY159: Activity Name: Install interior doors and case on 3rd Phase: Finishes Location: Level 3 Trade: Carpentry Start Date: 09-Dec-2024 End Date: 13-Dec-2024
Note on QG159: Activity Name: Install flooring on 3rd Phase: Finishes Location: Level 3 Trade: Flooring Start Date: 17-Dec-2024 End Date: 07-Jan-2025
Note on RC159: Activity Name: 3rd floor counter top measurement for template Phase: Finishes Location: Level 3 Trade: Flooring Start Date: 08-Jan-2025 End Date: 10-Jan-2025
Note on SK159: Activity Name: Construction clean on 3rd Phase: Finishes Location: Level 3 Trade: Cleaning Start Date: 11-Feb-2025 End Date: 17-Feb-2025
Note on LQ160: Activity Name: Rough in 3rd floor Phase: Finishes Location: Level 3 Trade: Rough-In (General) Start Date: 19-Aug-2024 End Date: 13-Dec-2024
Note on QH160: Activity Name: Install cabinets on 3rd Phase: Finishes Location: Level 3 Trade: Carpentry Start Date: 18-Dec-2024 End Date: 10-Jan-2025
Note on SQ160: Activity Name: Assign Unit Commissioning Inspection list on 3rd Phase: Finishes Location: Level 3 Trade: CX Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on PR161: Activity Name: Ceiling texture on 3rd Phase: Finishes Location: Level 3 Trade: Finishing Start Date: 02-Dec-2024 End Date: 03-Dec-2024
Note on PU161: Activity Name: Prime paint on 3rd Phase: Finishes Location: Level 3 Trade: Paint Start Date: 05-Dec-2024 End Date: 10-Dec-2024
Note on QB161: Activity Name: Spray out closet interiors and trim on 3rd Phase: Finishes Location: Level 3 Trade: Carpentry Start Date: 12-Dec-2024 End Date: 17-Dec-2024
Note on RC161: Activity Name: Install base and hardware on 3rd Phase: Finishes Location: Level 3 Trade: Carpentry Start Date: 08-Jan-2025 End Date: 13-Jan-2025
Note on SQ161: Activity Name: Final suite clean on 3rd Phase: Finishes Location: Level 3 Trade: Cleaning Start Date: 17-Feb-2025 End Date: 18-Feb-2025
Note on PR162: Activity Name: 3rd floor finishing Phase: Finishes Location: Level 3 Trade: Flooring Start Date: 02-Dec-2024 End Date: 18-Feb-2025
Note on PZ163: Activity Name: 3rd floor - Taper do the rectification of deficiencies Phase: Finishes Location: Level 3 Trade: Flooring Start Date: 10-Dec-2024 End Date: 10-Dec-2024
Note on QB163: Activity Name: Paint 1st coat of color on 3rd Phase: Finishes Location: Level 3 Trade: Paint Start Date: 12-Dec-2024 End Date: 17-Dec-2024
Note on RE163: Activity Name: Manufacturing and Install countertops on 3rd Phase: Finishes Location: Level 3 Trade: Carpentry Start Date: 10-Jan-2025 End Date: 29-Jan-2025
Note on KV166: Activity Name: Layout suites 4th floor Phase: Finishes Location: Level 4 Trade: Flooring Start Date: 29-Jul-2024 End Date: 01-Aug-2024
Note on LC166: Activity Name: Rough in 4th floor ceiling Phase: Finishes Location: Level 4 Trade: Rough-In (General) Start Date: 05-Aug-2024 End Date: 07-Oct-2024
Note on PA166: Activity Name: Install fascia and soffit 4th floor Phase: Finishes Location: Level 4 Trade: Flooring Start Date: 15-Nov-2024 End Date: 25-Nov-2024
Note on PL166: Activity Name: Ceiling texture on 4th Phase: Finishes Location: Level 4 Trade: Finishing Start Date: 26-Nov-2024 End Date: 27-Nov-2024
Note on PN166: Activity Name: Prime paint on 4th Phase: Finishes Location: Level 4 Trade: Paint Start Date: 28-Nov-2024 End Date: 03-Dec-2024
Note on PU166: Activity Name: Spray out closet interiors and trim on 4th Phase: Finishes Location: Level 4 Trade: Carpentry Start Date: 05-Dec-2024 End Date: 10-Dec-2024
Note on QA166: Activity Name: Install cabinets on 4th Phase: Finishes Location: Level 4 Trade: Carpentry Start Date: 11-Dec-2024 End Date: 18-Dec-2024
Note on QJ166: Activity Name: Install base and hardware on 4th Phase: Finishes Location: Level 4 Trade: Carpentry Start Date: 20-Dec-2024 End Date: 03-Jan-2025
Note on SC166: Activity Name: Construction clean on 4th Phase: Finishes Location: Level 4 Trade: Cleaning Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on KY167: Activity Name: Core floor beings at 4th floor Phase: Finishes Location: Level 4 Trade: Flooring Start Date: 01-Aug-2024 End Date: 02-Aug-2024
Note on LQ167: Activity Name: Water dams 4th floor Phase: Finishes Location: Level 4 Trade: Plumbing Start Date: 19-Aug-2024 End Date: 23-Aug-2024
Note on MH167: Activity Name: Poly 4th floor ceiling Phase: Finishes Location: Level 4 Trade: Flooring Start Date: 05-Sep-2024 End Date: 06-Sep-2024
Note on ML167: Activity Name: Install sound bar 4th floor Phase: Finishes Location: Level 4 Trade: Flooring Start Date: 09-Sep-2024 End Date: 10-Sep-2024
Note on MZ167: Activity Name: Tape 4th floor ceiling Phase: Finishes Location: Level 4 Trade: Drywall Start Date: 23-Sep-2024 End Date: 04-Oct-2024
Note on PA167: Activity Name: Tape 4th floor hallways and stair wells Phase: Finishes Location: Level 4 Trade: Drywall Start Date: 15-Nov-2024 End Date: 28-Nov-2024
Note on PR167: Activity Name: 4th floor - Taper do the rectification of deficiencies Phase: Finishes Location: Level 4 Trade: Flooring Start Date: 02-Dec-2024 End Date: 03-Dec-2024
Note on PU167: Activity Name: Paint 1st coat of color on 4th Phase: Finishes Location: Level 4 Trade: Paint Start Date: 05-Dec-2024 End Date: 10-Dec-2024
Note on QG167: Activity Name: 4th floor counter top measurements for template Phase: Finishes Location: Level 4 Trade: Flooring Start Date: 17-Dec-2024 End Date: 19-Dec-2024
Note on QW167: Activity Name: manufacturing and Install countertops on 4th Phase: Finishes Location: Level 4 Trade: Carpentry Start Date: 02-Jan-2025 End Date: 21-Jan-2025
Note on SG167: Activity Name: Assign Unit Commissioning Inspection list on 4th Phase: Finishes Location: Level 4 Trade: CX Start Date: 07-Feb-2025 End Date: 07-Feb-2025
Note on LQ168: Activity Name: Rough in 4th floor Phase: Finishes Location: Level 4 Trade: Rough-In (General) Start Date: 19-Aug-2024 End Date: 06-Dec-2024
Note on PY168: Activity Name: Install flooring on 4th Phase: Finishes Location: Level 4 Trade: Flooring Start Date: 09-Dec-2024 End Date: 16-Dec-2024
Note on SG168: Activity Name: Final suite clean on 4th Phase: Finishes Location: Level 4 Trade: Cleaning Start Date: 07-Feb-2025 End Date: 10-Feb-2025
Note on PL169: Activity Name: finishing on 4th Phase: Finishes Location: Level 4 Trade: Finishing Start Date: 26-Nov-2024 End Date: 10-Feb-2025
Note on PR170: Activity Name: Install interior doors and case on 4th Phase: Finishes Location: Level 4 Trade: Carpentry Start Date: 02-Dec-2024 End Date: 06-Dec-2024
Note on JF174: Activity Name: Paint underside of ceiling in parkade Phase: Finishes Location: Parkade Trade: Paint Start Date: 17-Jun-2024 End Date: 17-Jun-2024

## CFA - Legends
Exteriors |  | Finishes |  | Foundation |  | Mobilization |  | Pre-Construction |  | Rough-Ins |  | Sitework |  | Structure
Exteriors |  | COO |  | Concrete |  | Mobilization Team |  | Precon Team |  | Drywall |  | Site Sub |  | Framing
EXT-1 | Roofing and water proofing | COO-1 | Prepare occupancy paperwork | CON-1 | Assign hollow core erection checklist | MOB-1 | Assign Mobilization check list | PREC-1 | 28. Assign Pre excavation checklist | DRY-1 | 4.3 Rough In, Steel Stud Drywall | SIT- | 4.1 Site Services & Foundation Work | FRA- | Framing 4th floor
EXT-10 | Organize 3rd party building exterior review, including roof, siding and flashings | COO-2 | Receive occupancy | CON-10 | Form footings | MOB-2 | Assign Site Services Planning check list | PREC-10 | Building handover (PM to SM) checklist | DRY-10 | Tape parkade interior and exterior walls | SIT-1 | Radon rock install | FRA-1 | Back framing on 4th
EXT-2 | Install roofing and water proofing | COO-3 | Move in dates confirmed | CON-11 | Form grade beam | MOB-3 | Assign Sub Contractor planning checklist | PREC-11 | De mobilization (checklist) | DRY-2 | Assign Corridor & Stairwell pre board inspection checklist | SIT-10 | Install landscaping | FRA-2 | Frame and board Parkade beams
EXT-3 | Building paper the whole building | COO-4 | 5.0 Sales, Occupancy, Closings | CON-12 | Foundation |  |  | PREC-12 | Hold Pre Kick-Off meeting with Engineers and Trades people | DRY-3 | Assign pre board inspection check list | SIT-11 | Install building signage | FRA-3 | Frame drops on 4th
EXT-4 | Board exterior walls on 2nd and sheds | COO-5 | Pre sale move in dates confirmed | CON-13 | Hollowcore 2nd floor |  |  | PREC-13 | Order Rebar (30 days before site delivery date required) | DRY-4 | Board and prepare electrical/mechanical room | SIT-2 | Install poly | FRA-4 | Frame interior parkade walls
EXT-5 | Board parkade exterior walls and sheds |  |  | CON-14 | Install balcony piles |  |  | PREC-14 | Organize site team to have training and certificates | DRY-5 | Fire tape / Fire caulk upper strips on 2nd | SIT-3 | Form exterior pads | FRA-5 | Install metal doors and frames
EXT-6 | Board Parkade interior walls | CX |  | CON-15 | Install hollowcore 2nd floor , Install backer rod & Grout 2nd floor |  |  | PREC-15 | Schedule locates to be done | DRY-6 | Install drywall on 4th floor ceiling | SIT-4 | Excatae exterior sidewalks | FRA-6 | Install pocket door frames
EXT-7 | Blow in attic insulation | CX- | Assign water and sewer commissioning checklist | CON-16 | Measure corner offsets for excavation |  |  | PREC-16 | Schedule Pile contractor | DRY-7 | Layout suites on 2nd floor | SIT-5 | Form exterior sidewalks | FRA-7 | Install suite entry doors and frames and Interior doors, trims and jambs
EXT-8 | Exterior | CX-1 | Finalize home owner extras | CON-17 | Order all Anchor bolts |  |  | PREC-2 | 3.0 Pre construction and mobilization | DRY-8 | Load boards on floor and Board 3rd floor walls | SIT-6 | Call the surveyor to measure for condo plan
EXT-9 | Grind all balconys smooth | CX-10 | Schedule 1 on 1 contractor review meetings | CON-18 | Pour exterior pads |  |  | PREC-3 | 3.0, 4.0. 5.0 pre, during and post construction total job | DRY-9 | Steel stud install on 2nd & drywall behind the tubs including fire wall taping if it is a fire wall | SIT-7 | Parkade - Measurement for template | Inspection
|  | CX-11 | Schedule contractor group meeting to review survey results | CON-19 | Pour exterior sidewalks |  |  | PREC-4 | Assign conrete pour checklist |  |  | SIT-8 | Parkade - Taper to rectify deficiencies | INS-1 | 4th floor framing inspection
Insulation |  | CX-12 | Project post mordem internal | CON-2 | Back fill exterior grade beam |  |  | PREC-5 | Assign Equipment & Tools check list | Electrical |  | SIT-9 | Rough grade landscaping
INSU-1 | Poly and insulate on 2nd exterior walls | CX-13 | Move info to Dev co work flow 1.0, 2.0, 6.0 | CON-20 | Pour footings |  |  | PREC-6 | Assign exterior wall pre board inspection check list | ELE-1 | Electrical rough in in slab |  |  | Steel
INSU-2 | Poly and insulate parkade exterior walls | CX-2 | Load home owners into copper | CON-21 | Pour grade beam |  |  | PREC-7 | Assign Final Building Checklist | ELE-2 | Electrical finishing 2nd floor |  |  | STL-1 | Strucutral Steel
|  | CX-3 | Move in binders created | CON-22 | Pour parakde slab |  |  | PREC-8 | Assign framing check list | ELE-3 | Electrical rough in in ceiling |  |  | STL-2 | Structural steel erection
Rough-In (General) |  | CX-4 | Update home owner permissions in Construction online | CON-23 | Rebar exterior sidewalks |  |  | PREC-9 | Building close out check list | ELE-4 | Main service electrical room install
RI-2 | Rough in exterior walls on 2nd and sheds | CX-5 | Unit Commissioning Inspection list | CON-24 | Survey for balcony piles
RI-4 | Rough in Parkade | CX-6 | Keys and gift cards and welcome package created | CON-25 | Survey offsets, and footings |  |  |  |  | Gypcrete
|  | CX-7 | Home owner walk through and punch list | CON-26 | Tie footing rebar |  |  |  |  | GYP-1 | Gypcrete
Siding |  | CX-8 | New move ins and warranty through service manager | CON-27 | Tie Grade beam rebar
SID-1 | Soffit & Tower Siding | CX-9 | Send out contractor surveys | CON-28 | Tie parkade rebar |  |  |  |  | Mechanical
SID-2 | Siding towers |  |  | CON-29 | Tie rebar exterior pads |  |  |  |  | MCH-1 | Mechanical rough in in slab
SID-3 | Assign siding checklist | Carpentry |  | CON-3 | Build templates for Anchor bolts |  |  |  |  | MCH-2 | Main service mechanical room install
SID-4 | Siding 2nd floor | CAR-1 | Install base and hardware 2nd floor | CON-4 | Deliver pakade slab rebar |  |  |  |  | MCH-3 | Mechanical finishing 2nd floor
|  | CAR-2 | Install cabinets on 3rd | CON-5 | deliver rebar (footings and gradebeam only) |  |  |  |  | MCH-4 | Mechanical rough in in ceiling
Windows |  | CAR-3 | Install countertops on 1 | CON-6 | Dig footing and parkade foot print
WIN-1 | install windows and doors | CAR-4 | Install interior doors and case on 2nd | CON-7 | Ensure Sleeves for electrical are run in the grade beam prior to pouring |  |  |  |  | Plumbing
|  | CAR-5 | Manufacturing and Install countertops 2nd floor | CON-8 | Excavate areas |  |  |  |  | PLU-1 | Deliver tubs & showers to suites / checklist
|  | CAR-6 | Install cabinets 2nd floor | CON-9 | Exterior concrete works |  |  |  |  | PLU-2 | Install tubs and showers
|  |  |  | GYP-1 | Pour Gypcrete
|  | Cleaning |  | INSU-1 | Install underground insulation |  |  |  |  | Rough-In (General)
|  | CL-1 | Construction clean 2nd floor | [6 empty] | RI-1 | Rough in parkade slab
|  | CL-2 | Final suite clean | Inspection | [5 empty] | RI-2 | Rough in exterior walls on 4th and sheds
|  | CL-3 | Unit Commissioning deficiency clean up confirmed | INS-11 | Geo Tech Engineer inspection |  |  |  |  | RI-3 | Rough in interior walls
|  | CL-4 | Building close out cleanup deficiencies confirmed | INS-12 | Rebar Inspection Structural Engineer
|  | CL-5 | Home owner walk through punch list clean up | [6 empty] | Sprinkler
[10 empty] | SPR-1 | Sprinkler finishing 2nd floor
|  | Drywall | [7 empty] | SPR-2 | Sprinkler install in attic
|  | DRY-11 | Tape 2nd floor hallways and stair wells | [6 empty] | SPR-3 | Sprinkler rough in corridor & stairwells on 2nd
[10 empty] | SPR-4 | Install underground sprinklers
Exteriors
|  | EXT-11 | Install exterior decking all floors | [6 empty] | Vertical Flow
[10 empty] | VF-1 | Install stairs
|  | Finishing | [7 empty] | VF-2 | Delivery of Elevator & Install
|  | FIN-1 | 4.4 Finishing
|  | FIN-2 | Ceiling texture on 2nd
|  | FIN-3 | finishing parkade level 1
Flooring
|  | FLO- | 3rd floor counter top measurement for template
|  | FLO-10 | Install windows & doors all floors
|  | FLO-11 | Layout suites 4th floor
|  | FLO-12 | Poly 4th floor ceiling
|  | FLO-2 | 2nd floor - Taper do the rectification of deficiences
|  | FLO-3 | 2nd floor counter top measurement for template
|  | FLO-4 | 2nd floor finishing
|  | FLO-5 | Core floors begin at 2nd
|  | FLO-6 | Install fascia and soffit 4th floor
|  | FLO-7 | Install flooring 2nd floor
|  | FLO-8 | Install railings on all floors
|  | FLO-9 | Install sound bar 4th floor
Inspection
|  | INS-10 | Fire alarm verification
|  | INS-13 | Sprinkler testing
|  | INS-2 | Architectural walk throughs
|  | INS-3 | Building inspector walk throughs
|  | INS-4 | Call for Electrical and Mechanical Inspection
|  | INS-5 | Call for envelope reviewer inspection
|  | INS-6 | Call for Mechanical & Electrical inspection of attic
|  | INS-7 | Call for structural inspection
|  | INS-8 | Contact Canada Post to get the address's created
|  | INS-9 | Enginering walk throughs
Paint
|  | PAI-1 | Paint underside of ceiling in parkade
|  | PAI-2 | Final coat of paint
|  | PAI-3 | Paint 1st coat of color 2nd floor
|  | PAI-4 | Prime paint on 2nd
Plumbing
|  | PLU-3 | Water dams 2nd floor
Rough-In (General)
|  | RI-1 | Rough in 2nd floor