## Sheet1
Phase | Area | Zone | Trade | Color | Act Code | Act Name | Start | Finish
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 11 | Concrete | #A9A9A9 | C1 | Form, Reinforce, and Prep SOMD | 2026-01-29 | 2026-02-02
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 06 | Concrete | #A9A9A9 | C1 | Form, Reinforce, and Prep SOMD | 2025-12-11 | 2025-12-15
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 08 | Concrete | #A9A9A9 | C1 | Form, Reinforce, and Prep SOMD | 2025-12-23 | 2025-12-26
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 09 | Concrete | #A9A9A9 | C1 | Form, Reinforce, and Prep SOMD | 2026-01-22 | 2026-01-26
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 10 | Concrete | #A9A9A9 | C1 | Form, Reinforce, and Prep SOMD | 2026-01-29 | 2026-02-02
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 06 | Concrete | #A1A1A1 | C2 | Place and Finish SOMD Pour SUPER VOMS LEVEL SLAB | 2025-12-16 | 2025-12-16
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 08 | Concrete | #A1A1A1 | C2 | Place and Finish SOMD Pour CLUB LEVEL SLAB | 2025-12-29 | 2025-12-29
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 09 | Concrete | #A1A1A1 | C2 | Place and Finish SOMD Pour SUITE LEVEL SLAB | 2026-01-27 | 2026-01-27
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 10 | Concrete | #A1A1A1 | C2 | Place and Finish SOMD Pour PRESS LEVEL SLAB | 2026-02-03 | 2026-02-03
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 11 | Concrete | #A1A1A1 | C2 | Place and Finish SOMD Pour PARTY LEVEL SLAB | 2026-02-03 | 2026-02-03
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 06 | MEP | #20B2AA | M1 | Install MEP Anchors | 2025-12-08 | 2025-12-08
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 08 - Level 09 | MEP | #20B2AA | M1 | Install MEP Anchors | 2026-01-16 | 2026-01-19
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 08 | MEP | #20B2AA | M1 | Install MEP Anchors | 2025-12-18 | 2025-12-18
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 09 - Level 10 | MEP | #20B2AA | M1 | Install MEP Anchors | 2026-01-23 | 2026-01-26
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 10 - Level 11 | MEP | #20B2AA | M1 | Install MEP Anchors | 2026-01-23 | 2026-01-26
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 11 - Level 12 | MEP | #20B2AA | M1 | Install MEP Anchors | 2026-01-23 | 2026-01-26
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 06 | Other | #D3D3D3 | O1 | Install Misc. Embeds | 2025-12-09 | 2025-12-10
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 08 - Level 09 | Other | #D3D3D3 | O1 | Install Misc. Embeds | 2026-01-20 | 2026-01-21
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 08 | Other | #D3D3D3 | O1 | Install Misc. Embeds | 2025-12-19 | 2025-12-22
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 09 - Level 10 | Other | #D3D3D3 | O1 | Install Misc. Embeds | 2026-01-27 | 2026-01-28
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 10 - Level 11 | Other | #D3D3D3 | O1 | Install Misc. Embeds | 2026-01-27 | 2026-01-28
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 02/03 - Level 08 | Steel | #4682B4 | T1 | Install Structural Steel | 2025-10-07 | 2025-10-29
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 08 - Level 09 | Steel | #4682B4 | T1 | Install Structural Steel | 2025-10-30 | 2025-11-11
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 09 - Level 10 | Steel | #4682B4 | T1 | Install Structural Steel | 2025-11-12 | 2025-11-20
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 10 - Level 11 | Steel | #4682B4 | T1 | Install Structural Steel | 2025-11-21 | 2025-12-04
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 11 - Level 12 | Steel | #4682B4 | T1 | Install Structural Steel | 2025-12-05 | 2025-12-11
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 02/03 - Level 08 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2025-10-23 | 2025-11-21
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 08 - Level 09 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2025-11-24 | 2025-12-09
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 09 - Level 10 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2025-12-10 | 2025-12-18
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 10 - Level 11 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2025-12-19 | 2026-01-05
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 11 - Level 12 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-01-06 | 2026-01-15
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 09 | Steel | #3F75A2 | T3 | Install Slab Edge Deck Bent Plate | 2025-11-12 | 2025-11-13
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 10 | Steel | #3F75A2 | T3 | Install Slab Edge Deck Bent Plate | 2025-11-21 | 2025-11-24
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 11 | Steel | #3F75A2 | T3 | Install Slab Edge Deck Bent Plate | 2025-12-05 | 2025-12-08
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 06 | Steel | #3F75A2 | T3 | Install Slab Edge Deck Bent Plate | 2025-10-30 | 2025-10-31
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 08 | Steel | #3F75A2 | T3 | Install Slab Edge Deck Bent Plate | 2025-11-03 | 2025-11-04
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 06 | Steel | #3C6E99 | T4 | Install Roof Frames and Penetration Support Steel | 2025-11-03 | 2025-11-04
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 08 | Steel | #3C6E99 | T4 | Install Roof Frames and Penetration Support Steel | 2025-11-05 | 2025-11-06
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 06 | Steel | #386890 | T5 | Install Decking | 2025-11-24 | 2025-12-05
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 08 | Steel | #386890 | T5 | Install Decking | 2025-12-08 | 2025-12-17
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 09 | Steel | #386890 | T5 | Install Decking Level | 2025-12-08 | 2025-12-16
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 10 | Steel | #386890 | T5 | Install Decking Level | 2025-12-17 | 2025-12-29
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 11 | Steel | #386890 | T5 | Install Decking Level | 2026-01-06 | 2026-01-15
Structure Stadium / Tower / SPC - South Quadrant | Area 1: Tower East | Level 12 | Steel | #386890 | T5 | Install Decking Level | 2026-01-16 | 2026-01-22
Structure Stadium - North Quadrant | Area 10: Stadium North | Level 06 - Level 07 | Concrete | #909090 | C4 | Cure Time | 2026-04-02 | 2026-04-08
Structure Stadium - North Quadrant | Area 10: Stadium North | Level 06 - Level 07 | Concrete | #878787 | C5 | Install Concrete Sealer | 2026-04-09 | 2026-04-14
Structure Stadium - North Quadrant | Area 10: Stadium North | Level 06 - Level 07 | MEP | #20B2AA | M1 | Install MEP Anchors | 2026-03-25 | 2026-03-25
Structure Stadium - North Quadrant | Area 10: Stadium North | Level 06 - Level 07 | Other | #B3B3B3 | O3 | Install Misc. Embeds | 2026-03-26 | 2026-03-26
Structure Stadium - North Quadrant | Area 10: Stadium North | Level 06 - Level 07 | Other | #9E9E9E | O4 | FRP SOMD Concourse Roof | 2026-03-27 | 2026-04-01
Structure Stadium - North Quadrant | Area 10: Stadium North | Level 06 - Level 07 | Steel | #4682B4 | T1 | Install Structural Steel | 2026-01-22 | 2026-01-30
Structure Stadium - North Quadrant | Area 10: Stadium North | Level 06 - Level 07 | Steel | #274763 | T7 | Install Slab Edge Bent Plate | 2026-02-02 | 2026-02-03
Structure Stadium - North Quadrant | Area 10: Stadium North | Level 06 - Level 07 | Steel | #0E1A24 | T8 | Install Metal Decking | 2026-03-18 | 2026-03-24
Structure Stadium - North Quadrant | Area 10: Stadium North | Level 06 - Level 07 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-03-04 | 2026-03-17
Structure Stadium - North Quadrant | Area 11: Stadium North | Level 06 - Level 07 | Concrete | #909090 | C4 | Cure Time | 2026-05-06 | 2026-05-12
Structure Stadium - North Quadrant | Area 11: Stadium North | Level 06 - Level 07 | Concrete | #878787 | C5 | Install Concrete Sealer | 2026-05-13 | 2026-05-18
Structure Stadium - North Quadrant | Area 11: Stadium North | Level 06 - Level 07 | MEP | #20B2AA | M1 | Install MEP Anchors | 2026-04-28 | 2026-04-28
Structure Stadium - North Quadrant | Area 11: Stadium North | Level 06 - Level 07 | Other | #B3B3B3 | O3 | Install Misc. Embeds | 2026-04-29 | 2026-04-29
Structure Stadium - North Quadrant | Area 11: Stadium North | Level 06 - Level 07 | Other | #9E9E9E | O4 | FRP SOMD | 2026-04-30 | 2026-05-05
Structure Stadium - North Quadrant | Area 11: Stadium North | Level 06 - Level 07 | Steel | #4682B4 | T1 | Install Structural Steel | 2026-02-02 | 2026-02-12
Structure Stadium - North Quadrant | Area 11: Stadium North | Level 06 - Level 07 | Steel | #0E1A24 | T8 | Install Metal Decking | 2026-04-16 | 2026-04-27
Structure Stadium - North Quadrant | Area 11: Stadium North | Level 06 - Level 07 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-03-18 | 2026-04-06
Structure Stadium - North Quadrant | Area 11: Stadium North | Level 06 - Level 07 | Steel | #3F75A2 | T3 | Install Slab Edge Deck Bent Plate | 2026-02-13 | 2026-02-16
Structure Stadium - North Quadrant | Area 12: Stadium North | Level 06 - Level 07 | Concrete | #909090 | C4 | Cure Time | 2026-05-16 | 2026-05-22
Structure Stadium - North Quadrant | Area 12: Stadium North | Level 06 - Level 07 | Concrete | #878787 | C5 | Install Concrete Sealer | 2026-05-26 | 2026-05-29
Structure Stadium - North Quadrant | Area 12: Stadium North | Level 06 - Level 07 | MEP | #20B2AA | M1 | Install MEP Anchors | 2026-05-08 | 2026-05-08
Structure Stadium - North Quadrant | Area 12: Stadium North | Level 06 - Level 07 | Other | #B3B3B3 | O3 | Install Misc. Embeds | 2026-05-11 | 2026-05-11
Structure Stadium - North Quadrant | Area 12: Stadium North | Level 06 - Level 07 | Other | #9E9E9E | O4 | FRP SOMD | 2026-05-12 | 2026-05-15
Structure Stadium - North Quadrant | Area 12: Stadium North | Level 06 - Level 07 | Steel | #4682B4 | T1 | Install Structural Steel | 2026-02-03 | 2026-02-12
Structure Stadium - North Quadrant | Area 12: Stadium North | Level 06 - Level 07 | Steel | #0E1A24 | T8 | Install Metal Decking | 2026-04-28 | 2026-05-07
Structure Stadium - North Quadrant | Area 12: Stadium North | Level 06 - Level 07 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-04-07 | 2026-04-21
Structure Stadium - North Quadrant | Area 12: Stadium North | Level 06 - Level 07 | Steel | #3F75A2 | T3 | Install Slab Edge Deck Bent Plate | 2026-02-13 | 2026-02-16
Structure Stadium - North Quadrant | Area 13: Stadium North | Level 06 - Level 07 | Concrete | #909090 | C4 | Cure Time | 2026-06-02 | 2026-06-08
Structure Stadium - North Quadrant | Area 13: Stadium North | Level 06 - Level 07 | Concrete | #878787 | C5 | Install Concrete Sealer | 2026-06-09 | 2026-06-11
Structure Stadium - North Quadrant | Area 13: Stadium North | Level 06 - Level 07 | MEP | #20B2AA | M1 | Install MEP Anchors | 2026-05-22 | 2026-05-22
Structure Stadium - North Quadrant | Area 13: Stadium North | Level 06 - Level 07 | Other | #B3B3B3 | O3 | Install Misc. Embeds | 2026-05-26 | 2026-05-26
Structure Stadium - North Quadrant | Area 13: Stadium North | Level 06 - Level 07 | Other | #9E9E9E | O4 | FRP SOMD | 2026-05-27 | 2026-06-01
Structure Stadium - North Quadrant | Area 13: Stadium North | Level 06 - Level 07 | Steel | #4682B4 | T1 | Install Structural Steel | 2026-01-20 | 2026-02-02
Structure Stadium - North Quadrant | Area 13: Stadium North | Level 06 - Level 07 | Steel | #0E1A24 | T8 | Install Metal Decking | 2026-05-08 | 2026-05-21
Structure Stadium - North Quadrant | Area 13: Stadium North | Level 06 - Level 07 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-04-22 | 2026-05-12
Structure Stadium - North Quadrant | Area 13: Stadium North | Level 06 - Level 07 | Steel | #3F75A2 | T3 | Install Slab Edge Deck Bent Plate | 2026-02-03 | 2026-02-04
Structure Stadium - East Quadrant | Area 14 Team Store & Ticketing | General | MEP | #1A8E88 | M3 | Install Roof Top Equipment and Penetration Support Frames | 2026-06-01 | 2026-06-01
Structure Stadium - East Quadrant | Area 14 Team Store & Ticketing | General | Steel | #4682B4 | T1 | Install Structural Steel | 2026-02-12 | 2026-02-25
Structure Stadium - East Quadrant | Area 14 Team Store & Ticketing | General | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-04-30 | 2026-05-14
Structure Stadium - East Quadrant | Area 14 Team Store & Ticketing | General | Steel | #386890 | T5 | Install Decking Area A and Area B | 2026-05-15 | 2026-05-29
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 06 | Concrete | #A9A9A9 | C1 | Form, Reinforce, and Prep SOMD Pour | 2026-01-02 | 2026-01-06
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 08 | Concrete | #A9A9A9 | C1 | Form, Reinforce, and Prep SOMD Pour | 2026-01-16 | 2026-01-20
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 09 | Concrete | #A9A9A9 | C1 | Form, Reinforce, and Prep SOMD Pour | 2026-01-28 | 2026-01-30
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 10 | Concrete | #A9A9A9 | C1 | Form, Reinforce, and Prep SOMD Pour | 2026-02-09 | 2026-02-11
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 11 | Concrete | #A9A9A9 | C1 | Form, Reinforce, and Prep SOMD Pour | 2026-02-19 | 2026-02-23
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 11 | Concrete | #A1A1A1 | C2 | Place and Finish SOMD Pour | 2026-02-24 | 2026-02-25
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 06 | Concrete | #A1A1A1 | C2 | Place and Finish SOMD Pour | 2026-01-07 | 2026-01-08
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 08 | Concrete | #A1A1A1 | C2 | Place and Finish SOMD Pour | 2026-01-21 | 2026-01-22
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 09 | Concrete | #A1A1A1 | C2 | Place and Finish SOMD Pour | 2026-02-02 | 2026-02-03
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 10 | Concrete | #A1A1A1 | C2 | Place and Finish SOMD Pour | 2026-02-12 | 2026-02-13
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 06 | MEP | #1EA9A1 | M2 | Install Misc. Anchors | 2025-12-26 | 2025-12-29
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 08 - Level 09 | MEP | #1EA9A1 | M2 | Install Misc. Anchors | 2026-01-22 | 2026-01-23
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 08 | MEP | #1EA9A1 | M2 | Install Misc. Anchors | 2026-01-12 | 2026-01-13
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 09 - Level 10 | MEP | #1EA9A1 | M2 | Install Misc. Anchors | 2026-02-03 | 2026-02-04
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 10 - Level 11 | MEP | #1EA9A1 | M2 | Install Misc. Anchors | 2026-02-13 | 2026-02-16
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 11 - Level 12 | MEP | #1EA9A1 | M2 | Install Misc. Anchors | 2026-02-25 | 2026-02-26
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 06 | Other | #D3D3D3 | O1 | Install Misc. Embeds | 2025-12-30 | 2025-12-31
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 08 - Level 09 | Other | #D3D3D3 | O1 | Install Misc. Embeds | 2026-01-26 | 2026-01-27
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 08 | Other | #D3D3D3 | O1 | Install Misc. Embeds | 2026-01-14 | 2026-01-15
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 09 - Level 10 | Other | #D3D3D3 | O1 | Install Misc. Embeds | 2026-02-05 | 2026-02-06
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 10 - Level 11 | Other | #D3D3D3 | O1 | Install Misc. Embeds | 2026-02-17 | 2026-02-18
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 12 | Other | #BEBEBE | O2 | Install Roof Deck and Detailing | 2026-02-13 | 2026-02-24
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 02/03 - Level 08 | Steel | #4682B4 | T1 | Install Structural Steel | 2025-10-14 | 2025-11-10
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 08 - Level 09 | Steel | #4682B4 | T1 | Install Structural Steel | 2025-11-11 | 2025-11-19
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 09 - Level 10 | Steel | #4682B4 | T1 | Install Structural Steel | 2025-11-20 | 2025-12-01
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 10 - Level 11 | Steel | #4682B4 | T1 | Install Structural Steel | 2025-12-02 | 2025-12-10
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 11 - Level 12 | Steel | #4682B4 | T1 | Install Structural Steel | 2025-12-11 | 2025-12-16
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 02/03 - Level 08 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2025-11-04 | 2025-12-10
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 08 - Level 09 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2025-12-11 | 2025-12-19
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 09 - Level 10 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2025-12-22 | 2025-12-31
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 10 - Level 11 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-01-02 | 2026-01-13
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 11 - Level 12 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-01-14 | 2026-01-21
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 06 | Steel | #3F75A2 | T3 | Install Slab Edge Deck Bent Plate | 2025-11-11 | 2025-11-12
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 08 - Level 09 | Steel | #3F75A2 | T3 | Install Slab Edge Deck Bent Plate | 2025-11-20 | 2025-11-21
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 08 | Steel | #3F75A2 | T3 | Install Slab Edge Deck Bent Plate | 2025-11-13 | 2025-11-14
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 09 - Level 10 | Steel | #3F75A2 | T3 | Install Slab Edge Deck Bent Plate | 2025-12-02 | 2025-12-03
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 11 | Steel | #3F75A2 | T3 | Install Slab Edge Deck Bent Plate | 2025-12-11 | 2025-12-12
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 06 | Steel | #3C6E99 | T4 | Install Roof Frames and Penetration Support Steel | 2025-11-13 | 2025-11-14
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 08 | Steel | #3C6E99 | T4 | Install Roof Frames and Penetration Support Steel | 2025-11-17 | 2025-11-18
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 08 | Steel | #386890 | T5 | Install Decking | 2025-12-26 | 2026-01-09
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 06 | Steel | #386890 | T5 | Install Decking | 2025-12-11 | 2025-12-24
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 09 | Steel | #386890 | T5 | Install Decking | 2026-01-12 | 2026-01-21
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 10 | Steel | #386890 | T5 | Install Decking | 2026-01-22 | 2026-02-02
Structure Stadium / Tower / SPC - South Quadrant | Area 2: Tower West | Level 11 | Steel | #386890 | T5 | Install Decking | 2026-02-03 | 2026-02-12
Structure Stadium / Tower / SPC - South Quadrant | Area 3E: SPC Building East | Level 02 | Concrete | #989898 | C3 | Form, Reinforce, and Prep Composite Slab for Concrete Pour | 2026-01-23 | 2026-01-27
Structure Stadium / Tower / SPC - South Quadrant | Area 3E: SPC Building East | Level 02 | Concrete | #878787 | C6 | Place and Finish L2 SOMD | 2026-01-28 | 2026-01-29
Structure Stadium / Tower / SPC - South Quadrant | Area 3E: SPC Building East | Level 02 | MEP | #20B2AA | M1 | Install MEP Anchors | 2025-12-10 | 2025-12-11
Structure Stadium / Tower / SPC - South Quadrant | Area 3E: SPC Building East | Level 02 | Other | #B3B3B3 | O3 | Install Misc. Embeds | 2025-12-12 | 2025-12-15
Structure Stadium / Tower / SPC - South Quadrant | Area 3E: SPC Building East | Level 02 | Steel | #4682B4 | T1 | Install Structural Steel | 2025-10-23 | 2025-11-04
Structure Stadium / Tower / SPC - South Quadrant | Area 3E: SPC Building East | Level 02 | Steel | #274763 | T7 | Install Slab Edge Bent Plate | 2025-11-05 | 2025-11-06
Structure Stadium / Tower / SPC - South Quadrant | Area 3E: SPC Building East | Level 02 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2025-11-05 | 2025-11-19
Structure Stadium / Tower / SPC - South Quadrant | Area 3E: SPC Building East | Level 02 | Steel | #386890 | T5 | Install Decking | 2025-11-20 | 2025-12-09
Structure Stadium / Tower / SPC - South Quadrant | Area 3E: SPC Building East | Roof | Steel | #386890 | T5 | Install Decking | 2025-12-10 | 2025-12-24
Structure Stadium / Tower / SPC - South Quadrant | Area 3E: SPC Building East | Roof | Steel | #2A4E6C | T6 | Install Roof Penetration Backup Steel | 2025-11-05 | 2025-11-06
Structure Stadium / Tower / SPC - South Quadrant | Area 3W: SPC Building West | Level 02 | Concrete | #989898 | C3 | Form, Reinforce, and Prep Composite Slab for Concrete Pour | 2026-01-20 | 2026-01-22
Structure Stadium / Tower / SPC - South Quadrant | Area 3W: SPC Building West | Level 02 | Concrete | #878787 | C6 | Place and Finish L2 SOMD | 2026-01-23 | 2026-01-26
Structure Stadium / Tower / SPC - South Quadrant | Area 3W: SPC Building West | Level 02 | MEP | #20B2AA | M1 | Install MEP Anchors | 2026-01-14 | 2026-01-15
Structure Stadium / Tower / SPC - South Quadrant | Area 3W: SPC Building West | Level 02 | Other | #B3B3B3 | O3 | Install Misc. Embeds | 2026-01-16 | 2026-01-19
Structure Stadium / Tower / SPC - South Quadrant | Area 3W: SPC Building West | Level 02 | Steel | #4682B4 | T1 | Install Structural Steel | 2025-11-05 | 2025-11-19
Structure Stadium / Tower / SPC - South Quadrant | Area 3W: SPC Building West | Level 02 | Steel | #274763 | T7 | Install Slab Edge Bent Plate | 2025-11-20 | 2025-11-21
Structure Stadium / Tower / SPC - South Quadrant | Area 3W: SPC Building West | Level 02 | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2025-11-20 | 2025-12-10
Structure Stadium / Tower / SPC - South Quadrant | Area 3W: SPC Building West | Level 02 | Steel | #386890 | T5 | Install Decking | 2025-12-26 | 2026-01-13
Structure Stadium / Tower / SPC - South Quadrant | Area 3W: SPC Building West | Roof | Steel | #386890 | T5 | Install Decking | 2026-01-14 | 2026-01-29
Structure Stadium / Tower / SPC - South Quadrant | Area 3W: SPC Building West | Roof | Steel | #2A4E6C | T6 | Install Roof Penetration Backup Steel | 2025-12-11 | 2025-12-12
Structure Stadium / Tower / SPC - South Quadrant | Area 4: OPS Building | General | MEP | #1A8E88 | M3 | Install Roof Top Equipment and Penetration Support Frames | 2026-05-29 | 2026-06-01
Structure Stadium / Tower / SPC - South Quadrant | Area 4: OPS Building | General | Other | #BEBEBE | O2 | Install Roof Deck | 2026-04-30 | 2026-05-28
Structure Stadium / Tower / SPC - South Quadrant | Area 4: OPS Building | General | Steel | #4682B4 | T1 | Install Structural Steel | 2026-01-20 | 2026-02-11
Structure Stadium / Tower / SPC - South Quadrant | Area 4: OPS Building | General | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-04-02 | 2026-04-29
Structure Stadium / Tower / SPC - South Quadrant | Area 5 Weight Room / TGH | General | Steel | #4682B4 | T1 | Install Structural Steel | 2025-12-17 | 2026-01-19
Structure Stadium / Tower / SPC - South Quadrant | Area 5 Weight Room / TGH | General | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-02-25 | 2026-04-01
Structure Stadium / Tower / SPC - South Quadrant | Area 5 Weight Room / TGH | General | Steel | #386890 | T5 | Install Decking | 2026-04-02 | 2026-04-09
Structure Stadium / Tower / SPC - South Quadrant | Area 5 Weight Room / TGH | General | Steel | #386890 | T5 | Install Decking - Roof | 2026-04-10 | 2026-05-01
Structure Stadium - East Quadrant | Area 6 Stadium East | General | Steel | #4682B4 | T1 | Install Structural Steel | 2025-12-12 | 2026-01-05
Structure Stadium - East Quadrant | Area 6 Stadium East | General | Steel | #0E1A24 | T8 | Install Metal Decking | 2026-02-09 | 2026-02-16
Structure Stadium - East Quadrant | Area 6 Stadium East | General | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-01-16 | 2026-02-06
Structure Stadium - West Quadrant | Area 7: Stadium West | General | Steel | #4682B4 | T1 | Install Structural Steel | 2025-12-17 | 2026-01-06
Structure Stadium - West Quadrant | Area 7: Stadium West | General | Steel | #0E1A24 | T8 | Install Metal Decking | 2026-02-18 | 2026-02-25
Structure Stadium - West Quadrant | Area 7: Stadium West | General | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-01-22 | 2026-02-17
Structure Stadium - East Quadrant | Area 8: Stadium East | General | Steel | #4682B4 | T1 | Install Structural Steel | 2026-01-06 | 2026-01-21
Structure Stadium - East Quadrant | Area 8: Stadium East | General | Steel | #0E1A24 | T8 | Install Metal Decking | 2026-03-04 | 2026-03-10
Structure Stadium - East Quadrant | Area 8: Stadium East | General | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-02-09 | 2026-03-03
Structure Stadium - West Quadrant | Area 9: Stadium West | General | Steel | #4682B4 | T1 | Install Structural Steel | 2026-01-07 | 2026-01-19
Structure Stadium - West Quadrant | Area 9: Stadium West | General | Steel | #0E1A24 | T8 | Install Metal Decking | 2026-03-09 | 2026-03-16
Structure Stadium - West Quadrant | Area 9: Stadium West | General | Steel | #437BAB | T2 | Detailing, Bolt Up, and Moment Connections | 2026-02-18 | 2026-03-06