## Sheet1
Phase | Location | Zone | Trade | Activity Name | Color | Activity Code | Start | Finish
Yardwork | COLO 2 | South |  | Wire pulling and termination for TCP/MSB - Colo 2 - South | #FFFDA5 | EE35 | 2024-12-17 | 2025-01-08
Yardwork | COLO 2 | South |  | Install screen wall - Colo 2 - South | #D9D9D9 | RC1 | 2025-01-10 | 2025-01-16
Yardwork | COLO 2 | North |  | Install screen wall - Colo 2 - North | #D9D9D9 | RC1 | 2025-01-10 | 2025-01-30
Yardwork | COLO 5 | East |  | Install screen wall - Colo 5 - East | #D9D9D9 | RC1 | 2025-01-17 | 2025-02-06
Yardwork | COLO 5 | West |  | Install Generator Muffler - Colo 5 - West | #FFFDA5 | EE34 | 2025-02-07 | 2025-02-13
Yardwork | COLO 5 | West |  | Install screen wall - Colo 5 - West | #D9D9D9 | RC1 | 2025-02-13 | 2025-02-19
Yardwork | COLO 3 | South |  | Pull & Terminate Underground Cables (UMS to UPM to XMFR) | #FFFDA5 | EE46 | 2025-01-22 | 2025-01-28
Yardwork | COLO 3 | South |  | Install screen wall - Colo 3 - South | #D9D9D9 | RC1 | 2025-01-22 | 2025-01-28
Yardwork | COLO 3 | North |  | Wire pulling and termination for TCP/MSB - Colo 3 - North | #FFFDA5 | EE35 | 2025-01-22 | 2025-01-28
Yardwork | COLO 3 | North |  | Pull & Terminate Underground Cables (UMS to UPM to XMFR) | #FFFDA5 | EE46 | 2025-01-31 | 2025-02-06
Yardwork | COLO 3 | North |  | Install screen wall - Colo 3 - North | #D9D9D9 | RC1 | 2025-01-31 | 2025-02-06
Yardwork | COLO 4 | South |  | Wire pulling and termination for TCP/MSB - Colo 4 - South | #FFFDA5 | EE46 | 2025-01-31 | 2025-02-06
Yardwork | COLO 4 | South |  | Pull & Terminate Underground Cables (UMS to UPM to XMFR) | #FFFDA5 | EE46 | 2025-03-19 | 2025-03-25
Yardwork | COLO 4 | South |  | Install screen wall - Colo 4 - South | #D9D9D9 | RC1 | 2025-03-26 | 2025-04-01
Yardwork | COLO 4 | North |  | Wire pulling and termination for TCP/MSB - Colo 4 - North | #FFFDA5 | EE35 | 2025-03-26 | 2025-04-01
Yardwork | COLO 4 | North |  | Pull & Terminate Underground Cables (UMS to UPM to XMFR) | #FFFDA5 | EE46 | 2025-03-26 | 2025-04-01
Yardwork | COLO 4 | North |  | Install screen wall - Colo 4 - North | #D9D9D9 | RC1 | 2025-04-02 | 2025-04-08
CX Level 2 | Site | Site |  | L2 UTS / UTSR - Site | #FFFDA5 | EE47 | 2025-04-09 | 2025-04-22
CX Level 2 | COLO 2 | COLO 2 |  | L2 XFMR - COLO2 | #FFFDA5 | EE48 | 2025-04-23 | 2025-04-29
CX Level 2 | COLO 2 | COLO 2 |  | L2 GEN - COLO2 | #FFFDA5 | EE49 | 2025-01-14 | 2025-01-24
CX Level 2 | COLO 2 | COLO 2 |  | L2 UPM - COLO2 | #FFFDA5 | EE50 | 2025-01-24 | 2025-01-31
CX Level 2 | COLO 5 | COLO 5 |  | L2 UMS 01 - COLO 5 | #FFFDA5 | EE51 | 2025-01-09 | 2025-01-29
CX Level 2 | COLO 5 | COLO 5 |  | L2 UMS 02 - COLO 5 | #FFFDA5 | EE52 | 2025-01-30 | 2025-02-05
CX Level 2 | COLO 5 | COLO 5 |  | L2 URS 01 - COLO 5 | #FFFDA5 | EE53 | 2025-01-17 | 2025-01-30
CX Level 2 | COLO 5 | COLO 5 |  | L2 XFMR - COLO5 | #FFFDA5 | EE48 | 2025-01-31 | 2025-02-20
CX Level 2 | COLO 5 | COLO 5 |  | L2 GEN - COLO5 | #FFFDA5 | EE49 | 2025-02-21 | 2025-02-27
CX Level 2 | COLO 5 | COLO 5 |  | L2 UPM - COLO5 (UPM ROJ Driving) | #FFFDA5 | EE50 | 2025-02-13 | 2025-02-19
CX Level 2 | COLO 3 | COLO 3 |  | L2 UMS 03 - COLO 3 | #FFFDA5 | EE54 | 2025-02-20 | 2025-02-26
CX Level 2 | COLO 3 | COLO 3 |  | L2 UMS 04 - COLO 3 | #FFFDA5 | EE55 | 2025-02-20 | 2025-02-26
CX Level 2 | COLO 3 | COLO 3 |  | L2 XFMR - COLO3 | #FFFDA5 | EE48 | 2025-02-20 | 2025-02-26
CX Level 2 | COLO 3 | COLO 3 |  | L2 GEN - COLO3 | #FFFDA5 | EE49 | 2025-02-27 | 2025-03-05
CX Level 2 | COLO 3 | COLO 3 |  | L2 UPM - COLO3 (UPM ROJ Driving) | #FFFDA5 | EE50 | 2025-03-06 | 2025-03-12
CX Level 2 | COLO 4 | COLO 4 |  | L2 XFMR - COLO4 | #FFFDA5 | EE48 | 2025-02-27 | 2025-03-05
CX Level 2 | COLO 4 | COLO 4 |  | L2 GEN - COLO4 | #FFFDA5 | EE49 | 2025-03-19 | 2025-03-25
CX Level 2 | COLO 4 | COLO 4 |  | L2 UPM - COLO4 (UPM ROJ Driving) | #FFFDA5 | EE50 | 2025-03-26 | 2025-04-01
CX Level 3 | Site | Site |  | L3 UTS / UTSR - Site | #FFFDA5 | EE47 | 2025-03-26 | 2025-04-01
CX Level 3 | COLO 2 | Cell 1 |  | L3 GEN - Colo 2 Cell 1 | #FFFDA5 | EE49 | 2025-03-26 | 2025-04-01
CX Level 3 | COLO 2 | Cell 2 |  | L3 GEN - Colo 2 Cell 2 | #FFFDA5 | EE49 | 2025-04-02 | 2025-04-08
CX Level 3 | COLO 2 | Cell 3 |  | L3 GEN - Colo 2 Cell 3 | #FFFDA5 | EE49 | 2025-04-09 | 2025-04-22
CX Level 3 | COLO 2 | All |  | EPMS/BAS Turn-Up | #FFFDA5 | EE56 | 2025-04-23 | 2025-04-29
CX Level 3 | COLO 2 | Cell 1 |  | L3 UPM - Colo 2 Cell 1 | #FFFDA5 | EE50 | 2025-01-24 | 2025-01-28
CX Level 3 | COLO 2 | Cell 4 |  | L3 GEN - Colo 2 Cell 4 | #FFFDA5 | EE49 | 2025-01-28 | 2025-02-07
CX Level 3 | COLO 2 | Cell 2 |  | L3 UPM - Colo 2 Cell 2 | #FFFDA5 | EE50 | 2025-02-07 | 2025-02-14
CX Level 3 | COLO 2 | Cell 3 |  | L3 UPM - Colo 2 Cell 3 | #FFFDA5 | EE50 | 2024-12-19 | 2025-01-10
CX Level 3 | COLO 2 | Cell 4 |  | L3 UPM - Colo 2 Cell 4 | #FFFDA5 | EE50 | 2025-01-10 | 2025-01-16
CX Level 3 | COLO 2 | Cell 1 |  | L3 XFMR - Colo 2 Cell 1 | #FFFDA5 | EE48 | 2025-01-29 | 2025-02-18
CX Level 3 | COLO 2 | Cell 2 |  | L3 XFMR - Colo 2 Cell 2 | #FFFDA5 | EE48 | 2025-02-05 | 2025-02-18
CX Level 3 | COLO 2 | Cell 3 |  | L3 XFMR - Colo 2 Cell 3 | #FFFDA5 | EE48 | 2025-02-28 | 2025-03-06
CX Level 3 | COLO 2 | Cell 4 |  | L3 XFMR - Colo 2 Cell 4 | #FFFDA5 | EE48 | 2025-02-19 | 2025-02-25
CX Level 3 | COLO 5 | All |  | L3 URS 01 - COLO 5 | #FFFDA5 | EE53 | 2025-02-26 | 2025-03-04
CX Level 3 | COLO 5 | All |  | L3 UMS 01 - COLO 5 | #FFFDA5 | EE51 | 2025-02-26 | 2025-03-04
CX Level 3 | COLO 5 | All |  | L3 UMS 02 - COLO 5 | #FFFDA5 | EE52 | 2025-02-19 | 2025-02-25
CX Level 3 | COLO 5 | All |  | EPMS/BAS Turn-Up | #FFFDA5 | EE56 | 2025-02-26 | 2025-03-04
CX Level 3 | COLO 5 | Cell 1 |  | L3 GEN - Cell 1 | #FFFDA5 | EE49 | 2025-03-05 | 2025-03-11
CX Level 3 | COLO 5 | Cell 2 |  | L3 GEN - Cell 2 | #FFFDA5 | EE49 | 2025-03-05 | 2025-03-11
CX Level 3 | COLO 5 | Cell 3 |  | L3 GEN - Cell 3 | #FFFDA5 | EE49 | 2025-03-19 | 2025-03-25
CX Level 3 | COLO 5 | Cell 4 |  | L3 GEN - Cell 4 | #FFFDA5 | EE49 | 2025-03-26 | 2025-04-01
CX Level 3 | COLO 5 | Cell 1 |  | L3 UPM - Cell 1 | #FFFDA5 | EE50 | 2025-03-26 | 2025-04-01
CX Level 3 | COLO 5 | Cell 2 |  | L3 UPM - Cell 2 | #FFFDA5 | EE50 | 2025-03-26 | 2025-04-01
CX Level 3 | COLO 5 | Cell 1 |  | L3 XFMR - Cell 1 | #FFFDA5 | EE48 | 2025-04-02 | 2025-04-08
CX Level 3 | COLO 5 | Cell 3 |  | L3 UPM - Cell 3 | #FFFDA5 | EE50 | 2025-04-09 | 2025-04-22
CX Level 3 | COLO 5 | Cell 4 |  | L3 UPM - Cell 4 | #FFFDA5 | EE50 | 2025-04-23 | 2025-04-29
CX Level 3 | COLO 5 | Cell 2 |  | L3 XFMR - Cell 2 | #FFFDA5 | EE48 | 2025-01-24 | 2025-02-07
CX Level 3 | COLO 5 | Cell 3 |  | L3 XFMR - Cell 3 | #FFFDA5 | EE48 | 2025-02-07 | 2025-02-11
CX Level 3 | COLO 5 | Cell 4 |  | L3 XFMR - Cell 4 | #FFFDA5 | EE48 | 2025-02-11 | 2025-02-21
CX Level 3 | COLO 3 | All |  | L3 UMS 04 - COLO 3 | #FFFDA5 | EE55 | 2025-02-21 | 2025-02-28
CX Level 3 | COLO 3 | All |  | L3 UMS 03 - COLO 3 | #FFFDA5 | EE54 | 2024-12-27 | 2025-01-03
CX Level 3 | COLO 3 | All |  | EPMS/BAS Turn-Up | #FFFDA5 | EE56 | 2025-01-13 | 2025-01-31
CX Level 3 | COLO 3 | Cell 2 |  | L3 GEN - Cell 2 | #FFFDA5 | EE49 | 2025-02-03 | 2025-02-07
CX Level 3 | COLO 3 | Cell 3 |  | L3 GEN - Cell 3 | #FFFDA5 | EE49 | 2025-02-12 | 2025-03-04
CX Level 3 | COLO 3 | Cell 4 |  | L3 GEN - Cell 4 | #FFFDA5 | EE49 | 2025-02-19 | 2025-03-04
CX Level 3 | COLO 3 | Cell 1 |  | L3 GEN - Cell 1 | #FFFDA5 | EE49 | 2025-03-07 | 2025-03-13
CX Level 3 | COLO 3 | Cell 1 |  | L3 UPM - Cell 1 | #FFFDA5 | EE50 | 2025-03-05 | 2025-03-11
CX Level 3 | COLO 3 | Cell 2 |  | L3 UPM - Cell 2 | #FFFDA5 | EE50 | 2025-03-12 | 2025-03-18
CX Level 3 | COLO 3 | Cell 1 |  | L3 XFMR - Cell 1 | #FFFDA5 | EE48 | 2025-03-12 | 2025-03-18
CX Level 3 | COLO 3 | Cell 3 |  | L3 UPM - Cell 3 | #FFFDA5 | EE50 | 2025-03-12 | 2025-03-18
CX Level 3 | COLO 3 | Cell 4 |  | L3 UPM - Cell 4 | #FFFDA5 | EE50 | 2025-03-19 | 2025-03-25
CX Level 3 | COLO 3 | Cell 2 |  | L3 XFMR - Cell 2 | #FFFDA5 | EE48 | 2025-03-19 | 2025-03-25
CX Level 3 | COLO 3 | Cell 3 |  | L3 XFMR - Cell 3 | #FFFDA5 | EE48 | 2025-03-19 | 2025-03-25
CX Level 3 | COLO 3 | Cell 4 |  | L3 XFMR - Cell 4 | #FFFDA5 | EE48 | 2025-03-19 | 2025-03-25
CX Level 3 | COLO 4 | All |  | EPMS/BAS Turn-Up | #FFFDA5 | EE56 | 2025-03-26 | 2025-04-01
CX Level 3 | COLO 4 | Cell 1 |  | L3 GEN - Cell 1 | #FFFDA5 | EE49 | 2025-03-26 | 2025-04-01
CX Level 3 | COLO 4 | Cell 2 |  | L3 GEN - Cell 2 | #FFFDA5 | EE49 | 2025-04-02 | 2025-04-08
CX Level 3 | COLO 4 | Cell 3 |  | L3 GEN - Cell 3 | #FFFDA5 | EE49 | 2025-04-09 | 2025-04-15
CX Level 3 | COLO 4 | Cell 4 |  | L3 GEN - Cell 4 | #FFFDA5 | EE49 | 2025-04-09 | 2025-04-22
CX Level 3 | COLO 4 | Cell 1 |  | L3 UPM - Cell 1 | #FFFDA5 | EE50 | 2025-04-23 | 2025-04-29
CX Level 3 | COLO 4 | Cell 2 |  | L3 UPM - Cell 2 | #FFFDA5 | EE50 | 2025-04-30 | 2025-06-03
CX Level 3 | COLO 4 | Cell 1 |  | L3 XFMR - Cell 1 | #FFFDA5 | EE48 | 2025-06-04 | 2025-06-05
CX Level 3 | COLO 4 | Cell 3 |  | L3 UPM - Cell 3 | #FFFDA5 | EE50 | 2025-02-05 | 2025-02-11
CX Level 3 | COLO 4 | Cell 4 |  | L3 UPM - Cell 4 | #FFFDA5 | EE50 | 2024-12-24 | 2025-01-15
CX Level 3 | COLO 4 | Cell 2 |  | L3 XFMR - Cell 2 | #FFFDA5 | EE48 | 2025-01-13 | 2025-01-17
CX Level 3 | COLO 4 | Cell 3 |  | L3 XFMR - Cell 3 | #FFFDA5 | EE48 | 2025-01-27 | 2025-02-14
CX Level 3 | COLO 4 | Cell 4 |  | L3 XFMR - Cell 4 | #FFFDA5 | EE48 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 1 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | #FFFDA5 | EE29 | 2025-03-04 | 2025-03-10
COLO 2 | Cell 1 | Electrical Room |  | Finishes and Signage - COLO2 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-03-11 | 2025-03-17
COLO 2 | Cell 1 | Data Hall |  | Cable Pulling at PDU to Busway & MSB - COLO2 Cell 1 - DH | #FFFDA5 | EE17 | 2025-03-11 | 2025-03-17
COLO 2 | Cell 1 | Data Hall |  | Termination at PDU to Busway & MSB- COLO2 Cell 1 - DH | #FFFDA5 | EE18 | 2025-03-18 | 2025-03-24
COLO 2 | Cell 1 | Data Hall |  | Finishes and Signage - COLO2 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-03-18 | 2025-03-24
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 TCP/MSB - COLO2 Cell 1 | #FFFDA5 | EE57 | 2025-03-18 | 2025-03-24
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 ADP - COLO2 Cell 1 | #FFFDA5 | EE58 | 2025-03-18 | 2025-03-24
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 AHUs - COLO2 Cell 1 | #FFFDA5 | EE59 | 2025-03-25 | 2025-03-31
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 ATSs - COLO2 Cell 1 | #FFFDA5 | EE60 | 2025-03-25 | 2025-03-31
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 Busway - COLO2 Cell 1 | #FFFDA5 | EE61 | 2025-04-01 | 2025-04-07
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 UPS - COLO2 Cell 1 | #FFFDA5 | EE62 | 2025-03-25 | 2025-03-31
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 PDUs - COLO2 Cell 1 | #FFFDA5 | EE63 | 2025-04-01 | 2025-04-07
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 TCP/MSB - COLO2 Cell 1 | #FFFDA5 | EE57 | 2025-03-27 | 2025-04-09
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 UPS - COLO2 Cell 1 | #FFFDA5 | EE62 | 2025-04-08 | 2025-04-14
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 PDUs - COLO2 Cell 1 | #FFFDA5 | EE63 | 2025-01-31 | 2025-02-11
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 ADP - COLO2 Cell 1 | #FFFDA5 | EE58 | 2025-02-12 | 2025-02-18
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 ATSs - COLO2 Cell 1 | #FFFDA5 | EE60 | 2025-01-16 | 2025-02-05
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 AHUs - COLO2 Cell 1 | #FFFDA5 | EE59 | 2025-02-24 | 2025-02-28
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 Busway - COLO2 Cell 1 | #FFFDA5 | EE61 | 2025-02-03 | 2025-02-21
COLO 2 | Cell 2 | Mech Gallery |  | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | #FFFDA5 | EE35 | 2025-02-10 | 2025-02-21
COLO 2 | Cell 2 | Mech Gallery |  | Trim out MEP - COLO2 Cell 2 - MG | #FFFDA5 | EE36 | 2025-02-24 | 2025-03-14
COLO 2 | Cell 2 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | #FFFDA5 | EE29 | 2025-03-17 | 2025-03-21
COLO 2 | Cell 2 | Electrical Room |  | Finishes and Signage - COLO2 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-03-04 | 2025-03-10
COLO 2 | Cell 2 | Data Hall |  | Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH | #FFFDA5 | EE17 | 2025-03-11 | 2025-03-17
COLO 2 | Cell 2 | Data Hall |  | Termination at PDU & Busway - COLO2 Cell 2 - DH | #FFFDA5 | EE18 | 2025-03-11 | 2025-03-17
COLO 2 | Cell 2 | Data Hall |  | Finishes and Signage - COLO2 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-03-11 | 2025-03-17
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 TCP/MSB - COLO2 Cell 2 | #FFFDA5 | EE57 | 2025-03-18 | 2025-03-24
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 UPS - COLO2 Cell 2 | #FFFDA5 | EE62 | 2025-03-18 | 2025-03-24
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 PDUs - COLO2 Cell 2 | #FFFDA5 | EE63 | 2025-03-18 | 2025-03-24
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 ADP - COLO2 Cell 2 | #FFFDA5 | EE58 | 2025-03-28 | 2025-04-03
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 ATSs - COLO2 Cell 2 | #FFFDA5 | EE60 | 2025-03-28 | 2025-04-03
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 AHUs - COLO2 Cell 2 | #FFFDA5 | EE59 | 2025-03-28 | 2025-04-03
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 Busway - COLO2 Cell 2 | #FFFDA5 | EE61 | 2025-04-04 | 2025-04-10
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 TCP/MSB - COLO2 Cell 2 | #FFFDA5 | EE57 | 2025-04-04 | 2025-04-10
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 UPS - COLO2 Cell 2 | #FFFDA5 | EE62 | 2025-04-11 | 2025-04-24
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 PDUs - COLO2 Cell 2 | #FFFDA5 | EE63 | 2025-04-23 | 2025-04-29
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 ADP - COLO2 Cell 2 | #FFFDA5 | EE58 | 2025-02-12 | 2025-02-13
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 ATSs - COLO2 Cell 2 | #FFFDA5 | EE60 | 2025-02-14 | 2025-02-25
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 AHUs - COLO2 Cell 2 | #FFFDA5 | EE59 | 2025-02-26 | 2025-03-04
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 Busway - COLO2 Cell 2 | #FFFDA5 | EE61 | 2025-01-02 | 2025-01-08
COLO 2 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO2 Cell 3 - MG | #C00000 | I-R | 2025-02-06 | 2025-02-26
COLO 2 | Cell 3 | Mech Gallery |  | Install ceiling and Light Fittings - COLO2 Cell 3 - MG | #FFFDA5 | EE35 | 2025-03-24 | 2025-03-28
COLO 2 | Cell 3 | Mech Gallery |  | Trim out MEP - COLO2 Cell 3 - MG | #FFFDA5 | EE36 | 2025-02-17 | 2025-02-28
COLO 2 | Cell 3 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER | #FFFDA5 | EE29 | 2025-02-24 | 2025-03-14
COLO 2 | Cell 3 | Electrical Room |  | Finishes and Signage - COLO2 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-03-31 | 2025-04-04
COLO 2 | Cell 3 | Data Hall |  | Termination at PDU & Busway - COLO2 Cell 3 - DH | #FFFDA5 | EE18 | 2025-03-10 | 2025-03-14
COLO 2 | Cell 3 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH | #EF9E5B | ET7 | 2025-03-17 | 2025-03-21
COLO 2 | Cell 3 | Data Hall |  | Finishes and Signage - COLO2 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-03-17 | 2025-03-21
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 TCP/MSB - COLO2 Cell 3 | #FFFDA5 | EE57 | 2025-03-17 | 2025-03-21
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 UPS - COLO2 Cell 3 | #FFFDA5 | EE62 | 2025-03-24 | 2025-03-28
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 PDUs - COLO2 Cell 3 | #FFFDA5 | EE63 | 2025-03-24 | 2025-03-28
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 ADP - COLO2 Cell 3 | #FFFDA5 | EE58 | 2025-03-24 | 2025-03-28
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 ATSs - COLO2 Cell 3 | #FFFDA5 | EE60 | 2025-03-28 | 2025-04-03
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 AHUs - COLO2 Cell 3 | #FFFDA5 | EE59 | 2025-03-28 | 2025-04-03
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 Busway - COLO2 Cell 3 | #FFFDA5 | EE61 | 2025-03-28 | 2025-04-03
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 TCP/MSB - COLO2 Cell 3 | #FFFDA5 | EE57 | 2025-04-04 | 2025-04-10
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 UPS - COLO2 Cell 3 | #FFFDA5 | EE62 | 2025-04-04 | 2025-04-10
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 PDUs - COLO2 Cell 3 | #FFFDA5 | EE63 | 2025-04-04 | 2025-04-17
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 ADP - COLO2 Cell 3 | #FFFDA5 | EE58 | 2025-04-16 | 2025-04-22
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 ATSs - COLO2 Cell 3 | #FFFDA5 | EE60 | 2025-02-12 | 2025-02-25
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 AHUs - COLO2 Cell 3 | #FFFDA5 | EE59 | 2025-02-26 | 2025-02-27
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 Busway - COLO2 Cell 3 | #FFFDA5 | EE61 | 2025-02-28 | 2025-03-11
COLO 2 | Cell 4 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO2 Cell 4 - MG | #EF9E5B | ET22 | 2025-03-12 | 2025-03-18
COLO 2 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO2 Cell 4 - MG | #C00000 | I-R | 2025-01-07 | 2025-01-13
COLO 2 | Cell 4 | Mech Gallery |  | Install ceiling and Light Fittings - COLO2 Cell 4 - MG | #FFFDA5 | EE35 | 2025-01-09 | 2025-01-15
COLO 2 | Cell 4 | Mech Gallery |  | Trim out MEP - COLO2 Cell 4 - MG | #FFFDA5 | EE36 | 2025-02-27 | 2025-03-19
COLO 2 | Cell 4 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO2 Cell 4 - ER | #FFFDA5 | EE28 | 2025-04-07 | 2025-04-11
COLO 2 | Cell 4 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER | #FFFDA5 | EE29 | 2025-03-03 | 2025-03-21
COLO 2 | Cell 4 | Electrical Room |  | Finishes and Signage - COLO2 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-03-10 | 2025-03-21
COLO 2 | Cell 4 | Data Hall |  | Termination at PDU & Busway - COLO2 Cell 4 - DH | #FFFDA5 | EE18 | 2025-03-17 | 2025-04-04
COLO 2 | Cell 4 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH | #EF9E5B | ET7 | 2025-04-14 | 2025-04-18
COLO 2 | Cell 4 | Data Hall |  | Finishes and Signage - COLO2 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-03-03 | 2025-03-03
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 TCP/MSB - COLO2 Cell 4 | #FFFDA5 | EE57 | 2025-01-14 | 2025-01-14
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 UPS - COLO2 Cell 4 | #FFFDA5 | EE62 | 2025-01-14 | 2025-01-14
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 PDUs - COLO2 Cell 4 | #FFFDA5 | EE63 | 2025-01-14 | 2025-01-14
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 ADP - COLO2 Cell 4 | #FFFDA5 | EE58 | 2025-03-20 | 2025-03-26
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 ATSs - COLO2 Cell 4 | #FFFDA5 | EE60 | 2025-03-27 | 2025-04-02
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 AHUs - COLO2 Cell 4 | #FFFDA5 | EE59 | 2025-03-31 | 2025-04-04
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 Busway - COLO2 Cell 4 | #FFFDA5 | EE61 | 2025-03-24 | 2025-03-28
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 TCP/MSB - COLO2 Cell 4 | #FFFDA5 | EE57 | 2025-03-24 | 2025-03-28
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 PDUs - COLO2 Cell 4 | #FFFDA5 | EE62 | 2025-03-24 | 2025-03-28
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 ADP - COLO2 Cell 4 | #FFFDA5 | EE63 | 2025-04-03 | 2025-04-09
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 ATSs - COLO2 Cell 4 | #FFFDA5 | EE58 | 2025-03-28 | 2025-04-03
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 UPS - COLO2 Cell 4 | #FFFDA5 | EE60 | 2025-04-07 | 2025-04-11
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 AHUs - COLO2 Cell 4 | #FFFDA5 | EE59 | 2025-04-04 | 2025-04-10
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 Busway - COLO2 Cell 4 | #FFFDA5 | EE61 | 2025-04-11 | 2025-04-17
COLO 2 | All | CX - Microsoft |  | Level 4 Cx - Colo 2 | #000000 | MS1 | 2025-04-11 | 2025-04-17
COLO 2 | All | CX - Microsoft |  | Level 5 Cx / IST - Colo 2 | #000000 | MS2 | 2025-04-04 | 2025-04-17
COLO 5 | Cell 1 | Mech Gallery |  | Trim out MEP - COLO5 Cell 1 - MG | #FFFDA5 | EE36 | 2025-04-18 | 2025-04-24
COLO 5 | Cell 1 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER | #FFFDA5 | EE29 | 2025-04-30 | 2025-06-03
COLO 5 | Cell 1 | Electrical Room |  | Finishes and Signage - COLO5 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-06-04 | 2025-06-05
COLO 5 | Cell 1 | Data Hall |  | Termination at PDU & Busway- COLO5 Cell 1 - DH | #FFFDA5 | EE18 | 2025-01-28 | 2025-02-07
COLO 5 | Cell 1 | Data Hall |  | Finishes and Signage - COLO5 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-02-07 | 2025-02-14
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 TCP/MSB - COLO5 Cell 1 | #FFFDA5 | EE57 | 2025-01-06 | 2025-01-10
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 UPS - COLO5 Cell 1 | #FFFDA5 | EE62 | 2025-01-13 | 2025-01-31
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 ADP - COLO5 Cell 1 | #FFFDA5 | EE58 | 2025-02-03 | 2025-02-07
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 PDUs - COLO5 Cell 1 | #FFFDA5 | EE63 | 2025-02-10 | 2025-02-14
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 AHUs - COLO5 Cell 1 | #FFFDA5 | EE59 | 2025-02-17 | 2025-02-21
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 ATSs - COLO5 Cell 1 | #FFFDA5 | EE60 | 2025-01-27 | 2025-01-31
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 Busway - COLO5 Cell 1 | #FFFDA5 | EE61 | 2025-01-27 | 2025-01-31
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 TCP/MSB - COLO5 Cell 1 | #FFFDA5 | EE57 | 2025-02-03 | 2025-02-07
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 PDUs - COLO5 Cell 1 | #FFFDA5 | EE63 | 2025-01-29 | 2025-02-04
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 UPS - COLO5 Cell 1 | #FFFDA5 | EE62 | 2025-02-03 | 2025-02-21
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 ADP - COLO5 Cell 1 | #FFFDA5 | EE58 | 2025-02-10 | 2025-02-21
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 ATSs - COLO5 Cell 1 | #FFFDA5 | EE60 | 2025-02-10 | 2025-02-28
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 AHUs - COLO5 Cell 1 | #FFFDA5 | EE59 | 2025-03-03 | 2025-03-07
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 Busway - COLO5 Cell 1 | #FFFDA5 | EE61 | 2025-02-03 | 2025-02-03
COLO 5 | Cell 2 | Mech Gallery |  | Install ceiling and Light Fittings - COLO5 Cell 2 - MG | #FFFDA5 | EE35 | 2025-02-10 | 2025-02-10
COLO 5 | Cell 2 | Mech Gallery |  | Trim out MEP - COLO5 Cell 2 - MG | #FFFDA5 | EE36 | 2025-03-18 | 2025-03-24
COLO 5 | Cell 2 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER | #FFFDA5 | EE29 | 2025-03-25 | 2025-03-31
COLO 5 | Cell 2 | Electrical Room |  | Finishes and Signage - COLO5 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-03-25 | 2025-03-31
COLO 5 | Cell 2 | Data Hall |  | Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH | #FFFDA5 | EE18 | 2025-03-25 | 2025-03-31
COLO 5 | Cell 2 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH | #EF9E5B | ET7 | 2025-04-01 | 2025-04-07
COLO 5 | Cell 2 | Data Hall |  | Termination at PDU & Busway- COLO5 Cell 2 - DH | #FFFDA5 | EE19 | 2025-04-01 | 2025-04-07
COLO 5 | Cell 2 | Data Hall |  | Finishes and Signage - COLO5 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-04-08 | 2025-04-14
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 TCP/MSB - COLO5 Cell 2 | #FFFDA5 | EE57 | 2025-05-02 | 2025-05-08
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 UPS - COLO5 Cell 2 | #FFFDA5 | EE62 | 2025-05-09 | 2025-05-15
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 PDUs - COLO5 Cell 2 | #FFFDA5 | EE63 | 2025-05-09 | 2025-05-15
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 ADP - COLO5 Cell 2 | #FFFDA5 | EE58 | 2025-05-09 | 2025-05-15
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 AHUs - COLO5 Cell 2 | #FFFDA5 | EE59 | 2025-05-09 | 2025-05-15
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 ATSs - COLO5 Cell 2 | #FFFDA5 | EE60 | 2025-05-05 | 2025-05-16
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 Busway - COLO5 Cell 2 | #FFFDA5 | EE61 | 2025-05-16 | 2025-05-22
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 TCP/MSB - COLO5 Cell 2 | #FFFDA5 | EE57 | 2025-01-22 | 2025-01-24
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 PDUs - COLO5 Cell 2 | #FFFDA5 | EE63 | 2025-01-15 | 2025-02-04
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 ADP - COLO5 Cell 2 | #FFFDA5 | EE58 | 2025-01-24 | 2025-02-07
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 UPS - COLO5 Cell 2 | #FFFDA5 | EE62 | 2025-02-07 | 2025-02-11
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 ATSs - COLO5 Cell 2 | #FFFDA5 | EE60 | 2025-02-11 | 2025-02-21
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 AHUs - COLO5 Cell 2 | #FFFDA5 | EE59 | 2025-02-21 | 2025-02-28
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 Busway - COLO5 Cell 2 | #FFFDA5 | EE61 | 2025-01-10 | 2025-01-16
COLO 5 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO5 Cell 3 - MG | #C00000 | I-R | 2025-01-13 | 2025-01-17
COLO 5 | Cell 3 | Mech Gallery |  | Install ceiling and Light Fittings - COLO5 Cell 3 - MG | #FFFDA5 | EE35 | 2025-01-13 | 2025-01-17
COLO 5 | Cell 3 | Mech Gallery |  | Trim out MEP - COLO5 Cell 3 - MG | #FFFDA5 | EE36 | 2025-01-13 | 2025-01-17
COLO 5 | Cell 3 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO5 Cell 3 - ER | #FFFDA5 | EE28 | 2025-01-09 | 2025-01-22
COLO 5 | Cell 3 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER | #FFFDA5 | EE18 | 2025-01-20 | 2025-01-24
COLO 5 | Cell 3 | Electrical Room |  | Finishes and Signage - COLO5 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-01-15 | 2025-01-21
COLO 5 | Cell 3 | Data Hall |  | Cable Pulling at PDU & Busway- COLO5 Cell 3 - DH | #FFFDA5 | EE17 | 2025-02-03 | 2025-02-21
COLO 5 | Cell 3 | Data Hall |  | Termination at PDU & Busway - COLO5 Cell 3 - DH | #FFFDA5 | EE18 | 2025-02-24 | 2025-02-28
COLO 5 | Cell 3 | Data Hall |  | Finishes and Signage - COLO5 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-01-20 | 2025-01-24
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 TCP/MSB - COLO5 Cell 3 | #FFFDA5 | EE57 | 2025-01-27 | 2025-02-07
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 UPS - COLO5 Cell 3 | #FFFDA5 | EE62 | 2025-02-10 | 2025-02-14
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 PDUs - COLO5 Cell 3 | #FFFDA5 | EE63 | 2025-02-10 | 2025-02-14
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 ADP - COLO5 Cell 3 | #FFFDA5 | EE58 | 2025-02-12 | 2025-02-18
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 AHUs - COLO5 Cell 3 | #FFFDA5 | EE59 | 2025-02-17 | 2025-02-21
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 ATSs - COLO5 Cell 3 | #FFFDA5 | EE60 | 2025-02-17 | 2025-02-28
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 Busway - COLO5 Cell 3 | #FFFDA5 | EE61 | 2025-02-24 | 2025-03-07
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 TCP/MSB - COLO5 Cell 3 | #FFFDA5 | EE57 | 2025-02-24 | 2025-03-14
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 PDUs - COLO5 Cell 3 | #FFFDA5 | EE63 | 2025-03-10 | 2025-03-14
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 ADP - COLO5 Cell 3 | #FFFDA5 | EE58 | 2025-01-22 | 2025-01-22
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 UPS - COLO5 Cell 3 | #FFFDA5 | EE62 | 2025-01-20 | 2025-01-20
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 ATSs - COLO5 Cell 3 | #FFFDA5 | EE60 | 2025-01-20 | 2025-01-20
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 AHUs - COLO5 Cell 3 | #FFFDA5 | EE59 | 2025-01-20 | 2025-01-20
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 Busway - COLO5 Cell 3 | #FFFDA5 | EE61 | 2025-01-20 | 2025-01-20
COLO 5 | Cell 4 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO5 Cell 4 - MG | #EF9E5B | ET22 | 2025-02-17 | 2025-02-17
COLO 5 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO5 Cell 4 - MG | #C00000 | I-R | 2025-02-11 | 2025-02-11
COLO 5 | Cell 4 | Mech Gallery |  | Install ceiling and Light Fittings - COLO5 Cell 4 - MG | #FFFDA5 | EE35 | 2025-03-18 | 2025-03-24
COLO 5 | Cell 4 | Mech Gallery |  | Trim out MEP - COLO5 Cell 4 - MG | #FFFDA5 | EE36 | 2025-03-25 | 2025-03-31
COLO 5 | Cell 4 | Electrical Room |  | Installation of ADP & ATS - COLO5 Cell 4 - ER | #FFFDA5 | EE27 | 2025-03-25 | 2025-03-31
COLO 5 | Cell 4 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO5 Cell 4 - ER | #FFFDA5 | EE28 | 2025-03-25 | 2025-03-31
COLO 5 | Cell 4 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER | #FFFDA5 | EE17 | 2025-04-01 | 2025-04-07
COLO 5 | Cell 4 | Electrical Room |  | Finishes and Signage - COLO5 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-04-01 | 2025-04-07
COLO 5 | Cell 4 | Data Hall |  | Closing Construction Access Door - COLO5 Cell 4 - DH | #04A261 | W4 | 2025-04-08 | 2025-04-14
COLO 5 | Cell 4 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH | #EF9E5B | ET7 | 2025-05-02 | 2025-05-08
COLO 5 | Cell 4 | Data Hall |  | Termination at PDU & Busway - COLO5 Cell 4 - DH | #FFFDA5 | EE18 | 2025-05-09 | 2025-05-15
COLO 5 | Cell 4 | Data Hall |  | Finishes and Signage - COLO5 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-05-09 | 2025-05-15
COLO 5 | Cell 4 | CX - L1 |  | Interior - L1 PDUs - COLO5 Cell 4 | #FFFDA5 | EE63 | 2025-05-16 | 2025-05-22
COLO 5 | Cell 4 | CX - L1 |  | Interior - L1 ATSs - COLO5 Cell 4 | #FFFDA5 | EE59 | 2025-05-09 | 2025-05-15
COLO 5 | Cell 4 | CX - L1 |  | Interior - L1 Busway - COLO5 Cell 4 | #FFFDA5 | EE61 | 2025-05-05 | 2025-05-16
COLO 5 | Cell 4 | CX - L1 |  | Interior - L1 ADP - COLO5 Cell 4 | #FFFDA5 | EE58 | 2025-05-16 | 2025-05-22
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 TCP/MSB - COLO5 Cell 4 | #FFFDA5 | EE57 | 2025-01-29 | 2025-02-18
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 UPS - COLO5 Cell 4 | #FFFDA5 | EE62 | 2025-02-07 | 2025-02-21
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 PDUs - COLO5 Cell 4 | #FFFDA5 | EE63 | 2025-02-21 | 2025-02-25
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 ADP - COLO5 Cell 4 | #FFFDA5 | EE58 | 2025-02-25 | 2025-03-07
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 AHUs - COLO5 Cell 4 | #FFFDA5 | EE59 | 2025-03-07 | 2025-03-14
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 ATSs - COLO5 Cell 4 | #FFFDA5 | EE60 | 2025-01-24 | 2025-01-30
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 Busway - COLO5 Cell 4 | #FFFDA5 | EE61 | 2025-01-27 | 2025-01-31
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 TCP/MSB - COLO5 Cell 4 | #FFFDA5 | EE57 | 2025-01-27 | 2025-01-31
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 PDUs - COLO5 Cell 4 | #FFFDA5 | EE63 | 2025-01-27 | 2025-01-31
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 ADP - COLO5 Cell 4 | #FFFDA5 | EE58 | 2025-01-23 | 2025-02-05
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 ATSs - COLO5 Cell 4 | #FFFDA5 | EE60 | 2025-02-03 | 2025-02-07
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 UPS - COLO5 Cell 4 | #FFFDA5 | EE62 | 2025-01-29 | 2025-02-04
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 AHUs - COLO5 Cell 4 | #FFFDA5 | EE59 | 2025-02-24 | 2025-03-14
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 Busway - COLO5 Cell 4 | #FFFDA5 | EE61 | 2025-03-12 | 2025-03-18
COLO 5 | All | CX - Microsoft |  | Level 4 Cx - Colo 5 | #000000 | MS1 | 2025-02-03 | 2025-02-07
COLO 5 | All | CX - Microsoft |  | Level 5 Cx / IST - Colo 5 | #000000 | MS2 | 2025-02-10 | 2025-02-21
COLO 3 | Cell 1 | Mech Gallery |  | Install ceiling and Light Fittings - COLO3 Cell 1 - MG | #FFFDA5 | EE35 | 2025-02-24 | 2025-02-28
COLO 3 | Cell 1 | Mech Gallery |  | Trim out MEP - COLO3 Cell 1 - MG | #FFFDA5 | EE36 | 2025-02-24 | 2025-02-28
COLO 3 | Cell 1 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO3 Cell 1 - ER | #FFFDA5 | EE28 | 2025-02-26 | 2025-03-04
COLO 3 | Cell 1 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER | #FFFDA5 | EE29 | 2025-03-03 | 2025-03-07
COLO 3 | Cell 1 | Electrical Room |  | Installation of UPS Equipment - COLO3 Cell 1 - ER | #FFFDA5 | EE23 | 2025-03-03 | 2025-03-14
COLO 3 | Cell 1 | Electrical Room |  | Door Frame Installation - COLO3 Cell 1 - ER | #3399FF | J36 | 2025-03-10 | 2025-03-21
COLO 3 | Cell 1 | Electrical Room |  | Finishes and Signage - COLO3 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-03-17 | 2025-04-04
COLO 3 | Cell 1 | Data Hall |  | Install PDU's - COLO3 Cell 1 - DH | #FFFDA5 | EE7 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 1 | Data Hall |  | Begin HAC Assembly - COLO3 Cell 1 - DH | #FED7E8 | S1 | 2025-02-05 | 2025-02-05
COLO 3 | Cell 1 | Data Hall |  | HAC install and Rise - COLO3 Cell 1 - DH | #FED7E8 | S2 | 2025-02-03 | 2025-02-03
COLO 3 | Cell 1 | Data Hall |  | Install Busway - COLO3 Cell 1 - DH | #FFFDA5 | EE10 | 2025-02-03 | 2025-02-03
COLO 3 | Cell 1 | Data Hall |  | Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH | #FFFDA5 | EE17 | 2025-02-03 | 2025-02-03
COLO 3 | Cell 1 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH | #EF9E5B | ET7 | 2025-02-03 | 2025-02-03
COLO 3 | Cell 1 | Data Hall |  | Termination at PDU & Busway- COLO3 Cell 1 - DH | #FFFDA5 | EE18 | 2025-03-03 | 2025-03-03
COLO 3 | Cell 1 | Data Hall |  | Finishes and Signage - COLO3 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-02-12 | 2025-02-12
COLO 3 | Cell 1 | CX - L1 |  | Interior - L1 PDUs - COLO3 Cell 1 | #FFFDA5 | EE63 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 1 | CX - L1 |  | Interior - L1 UPS - COLO3 Cell 1 | #FFFDA5 | EE62 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 TCP/MSB - COLO3 Cell 1 | #FFFDA5 | EE57 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 UPS - COLO3 Cell 1 | #FFFDA5 | EE62 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 PDUs - COLO3 Cell 1 | #FFFDA5 | EE63 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 ADP - COLO3 Cell 1 | #FFFDA5 | EE58 | 2025-04-07 | 2025-04-11
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 ATSs - COLO3 Cell 1 | #FFFDA5 | EE60 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 Busway - COLO3 Cell 1 | #FFFDA5 | EE61 | 2025-05-02 | 2025-05-08
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 AHUs - COLO3 Cell 1 | #FFFDA5 | EE59 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 TCP/MSB - COLO3 Cell 1 | #FFFDA5 | EE57 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 UPS - COLO3 Cell 1 | #FFFDA5 | EE62 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 PDUs - COLO3 Cell 1 | #FFFDA5 | EE63 | 2025-05-12 | 2025-05-16
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 ADP - COLO3 Cell 1 | #FFFDA5 | EE58 | 2025-05-12 | 2025-05-16
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 ATSs - COLO3 Cell 1 | #FFFDA5 | EE60 | 2025-05-05 | 2025-05-16
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 AHUs - COLO3 Cell 1 | #FFFDA5 | EE59 | 2025-01-27 | 2025-01-28
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 Busway - COLO3 Cell 1 | #FFFDA5 | EE61 | 2025-01-29 | 2025-02-11
COLO 3 | Cell 2 | Mech Gallery |  | Placing the AHU - COLO3 Cell 2 - MG | #CFE741 | GA6 | 2025-02-12 | 2025-02-12
COLO 3 | Cell 2 | Mech Gallery |  | Post Wall Overhead MEP - COLO3 Cell 2 - MG | #FFFDA5 | EE70 | 2025-02-19 | 2025-02-21
COLO 3 | Cell 2 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO3 Cell 2 - MG | #EF9E5B | ET22 | 2025-02-12 | 2025-03-04
COLO 3 | Cell 2 | Mech Gallery | Inspections | Pipe Testing - COLO3 Cell 2 - MG | #C00000 | I-R | 2025-02-21 | 2025-03-07
COLO 3 | Cell 2 | Mech Gallery |  | Install ceiling and Light Fittings - COLO3 Cell 2 - MG | #FFFDA5 | EE35 | 2025-03-07 | 2025-03-11
COLO 3 | Cell 2 | Mech Gallery |  | Trim out MEP - COLO3 Cell 2 - MG | #FFFDA5 | EE36 | 2025-03-11 | 2025-03-21
COLO 3 | Cell 2 | Electrical Room |  | Install DX Split Units - COLO3 Cell 2 - ER | #987655 | GH3 | 2025-03-21 | 2025-03-28
COLO 3 | Cell 2 | Electrical Room |  | Installation of ADP & ATS - COLO3 Cell 2 - ER | #FFFDA5 | EE27 | 2025-01-21 | 2025-02-03
COLO 3 | Cell 2 | Electrical Room |  | Installation of UPS Equipment - COLO3 Cell 2 - ER | #FFFDA5 | EE23 | 2025-02-04 | 2025-02-06
COLO 3 | Cell 2 | Electrical Room |  | Installation of TCP/MSB - COLO3 Cell 2 - ER | #FFFDA5 | EE71 | 2025-02-07 | 2025-02-13
COLO 3 | Cell 2 | Electrical Room |  | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | #FFFDA5 | EE72 | 2025-02-10 | 2025-02-14
COLO 3 | Cell 2 | Electrical Room |  | Door Frame Installation - COLO3 Cell 2 - ER | #3399FF | J36 | 2025-02-10 | 2025-02-14
COLO 3 | Cell 2 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO3 Cell 2 - ER | #FFFDA5 | EE28 | 2025-02-10 | 2025-02-14
COLO 3 | Cell 2 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER | #FFFDA5 | EE29 | 2025-02-12 | 2025-02-18
COLO 3 | Cell 2 | Electrical Room |  | Finishes and Signage - COLO3 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-02-06 | 2025-02-19
COLO 3 | Cell 2 | Data Hall |  | Ceiling Grid and Tile - COLO3 Cell 2 - DH | #3399FF | J7 | 2025-02-17 | 2025-02-21
COLO 3 | Cell 2 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH | #FFFDA5 | EE73 | 2025-03-17 | 2025-04-04
COLO 3 | Cell 2 | Data Hall |  | Install PDU's - COLO3 Cell 2 - DH | #FFFDA5 | EE7 | 2025-04-02 | 2025-04-08
COLO 3 | Cell 2 | Data Hall |  | Begin HAC Assembly - COLO3 Cell 2 - DH | #FED7E8 | S1 | 2025-01-13 | 2025-01-28
COLO 3 | Cell 2 | Data Hall |  | Install Busway - COLO3 Cell 2 - DH | #FFFDA5 | EE10 | 2025-02-12 | 2025-02-14
COLO 3 | Cell 2 | Data Hall |  | HAC install and Rise - COLO3 Cell 2 - DH | #FED7E8 | S2 | 2025-02-17 | 2025-02-21
COLO 3 | Cell 2 | Data Hall |  | Cable Pulling at PDU & Busway- COLO3 Cell 2 - DH | #FFFDA5 | EE17 | 2025-02-24 | 2025-03-07
COLO 3 | Cell 2 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 2 - DH | #EF9E5B | ET7 | 2025-03-10 | 2025-03-14
COLO 3 | Cell 2 | Data Hall |  | Termination at PDU & Busway - COLO3 Cell 2 - DH | #FFFDA5 | EE18 | 2025-03-10 | 2025-03-14
COLO 3 | Cell 2 | Data Hall |  | Finishes and Signage - COLO3 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-03-12 | 2025-03-18
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 AHUs - COLO3 Cell 2 | #FFFDA5 | EE59 | 2025-03-17 | 2025-03-21
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 TCP/MSB - COLO3 Cell 2 | #FFFDA5 | EE57 | 2025-03-24 | 2025-04-04
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 ATSs - COLO3 Cell 2 | #FFFDA5 | EE60 | 2025-03-17 | 2025-03-28
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 Busway - COLO3 Cell 2 | #FFFDA5 | EE61 | 2025-04-07 | 2025-04-25
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 ADP - COLO3 Cell 2 | #FFFDA5 | EE58 | 2025-04-21 | 2025-04-25
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 PDUs - COLO3 Cell 2 | #FFFDA5 | EE63 | 2025-02-19 | 2025-02-19
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 UPS - COLO3 Cell 2 | #FFFDA5 | EE62 | 2025-02-17 | 2025-02-17
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 TCP/MSB - COLO3 Cell 2 | #FFFDA5 | EE57 | 2025-02-17 | 2025-02-17
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 UPS - COLO3 Cell 2 | #FFFDA5 | EE62 | 2025-02-17 | 2025-02-17
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 PDUs - COLO3 Cell 2 | #FFFDA5 | EE63 | 2025-02-17 | 2025-02-17
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 ADP - COLO3 Cell 2 | #FFFDA5 | EE58 | 2025-02-12 | 2025-02-12
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 ATSs - COLO3 Cell 2 | #FFFDA5 | EE60 | 2025-03-17 | 2025-03-17
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 Busway - COLO3 Cell 2 | #FFFDA5 | EE61 | 2025-04-07 | 2025-04-11
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 AHUs - COLO3 Cell 2 | #FFFDA5 | EE59 | 2025-04-14 | 2025-04-18
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 TCP/MSB - COLO3 Cell 2 | #FFFDA5 | EE57 | 2025-04-14 | 2025-04-18
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 UPS - COLO3 Cell 2 | #FFFDA5 | EE62 | 2025-04-21 | 2025-04-25
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 ADP - COLO3 Cell 2 | #FFFDA5 | EE58 | 2025-04-21 | 2025-04-25
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 PDUs - COLO3 Cell 2 | #FFFDA5 | EE63 | 2025-04-28 | 2025-05-02
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 ATSs - COLO3 Cell 2 | #FFFDA5 | EE60 | 2025-04-28 | 2025-05-02
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 AHUs - COLO3 Cell 2 | #FFFDA5 | EE59 | 2025-05-02 | 2025-05-08
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 Busway - COLO3 Cell 2 | #FFFDA5 | EE61 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 3 | Mech Gallery |  | Post Wall Overhead MEP - COLO3 Cell 3 - MG | #FFFDA5 | EE70 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 3 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO3 Cell 3 - MG | #EF9E5B | ET22 | 2025-05-05 | 2025-05-16
COLO 3 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO3 Cell 3 - MG | #C00000 | I-R | 2025-05-12 | 2025-05-16
COLO 3 | Cell 3 | Mech Gallery |  | Install ceiling and Light Fittings - COLO3 Cell 3 - MG | #FFFDA5 | EE35 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 3 | Mech Gallery |  | Trim out MEP - COLO3 Cell 3 - MG | #FFFDA5 | EE36 | 2025-05-19 | 2025-05-23
COLO 3 | Cell 3 | Electrical Room |  | Install DX Split Units - COLO3 Cell 3 - ER | #987655 | GH3 | 2025-05-27 | 2025-06-30
COLO 3 | Cell 3 | Electrical Room |  | Installation of ADP & ATS - COLO3 Cell 3 - ER | #FFFDA5 | EE27 | 2025-07-01 | 2025-07-02
COLO 3 | Cell 3 | Electrical Room |  | Installation of UPS Equipment - COLO3 Cell 3 - ER | #FFFDA5 | EE23 | 2025-01-22 | 2025-01-24
COLO 3 | Cell 3 | Electrical Room |  | Installation of TCP/MSB - COLO3 Cell 3 - ER | #FFFDA5 | EE71 | 2025-01-15 | 2025-02-04
COLO 3 | Cell 3 | Electrical Room |  | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | #FFFDA5 | EE72 | 2025-01-24 | 2025-02-07
COLO 3 | Cell 3 | Electrical Room |  | Door Frame Installation - COLO3 Cell 3 - ER | #3399FF | J36 | 2025-02-07 | 2025-02-11
COLO 3 | Cell 3 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO3 Cell 3 - ER | #FFFDA5 | EE28 | 2025-02-11 | 2025-02-21
COLO 3 | Cell 3 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER | #FFFDA5 | EE29 | 2025-02-21 | 2025-02-28
COLO 3 | Cell 3 | Electrical Room |  | Finishes and Signage - COLO3 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-01-07 | 2025-01-13
COLO 3 | Cell 3 | Data Hall |  | Ceiling Grid and Tile - COLO3 Cell 3 - DH | #3399FF | J7 | 2024-12-24 | 2024-12-31
COLO 3 | Cell 3 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH | #FFFDA5 | EE73 | 2025-01-07 | 2025-01-13
COLO 3 | Cell 3 | Data Hall |  | Install PDU's - COLO3 Cell 3 - DH | #FFFDA5 | EE7 | 2024-12-23 | 2024-12-30
COLO 3 | Cell 3 | Data Hall |  | Begin HAC Assembly - COLO3 Cell 3 - DH | #FED7E8 | S1 | 2024-12-20 | 2025-01-06
COLO 3 | Cell 3 | Data Hall |  | Install Busway - COLO3 Cell 3 - DH | #FFFDA5 | EE10 | 2025-01-03 | 2025-01-09
COLO 3 | Cell 3 | Data Hall |  | HAC install and Rise - COLO3 Cell 3 - DH | #FED7E8 | S2 | 2025-01-09 | 2025-01-15
COLO 3 | Cell 3 | Data Hall |  | Cable Pulling at PDU & Busway- COLO3 Cell 3 - DH | #FFFDA5 | EE17 | 2025-01-16 | 2025-02-05
COLO 3 | Cell 3 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 3 - DH | #EF9E5B | ET7 | 2025-02-03 | 2025-02-07
COLO 3 | Cell 3 | Data Hall |  | Termination at PDU & Busway - COLO3 Cell 3 - DH | #FFFDA5 | EE18 | 2025-01-20 | 2025-01-24
COLO 3 | Cell 3 | Data Hall |  | Finishes and Signage - COLO3 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-01-27 | 2025-02-07
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 AHUs - COLO3 Cell 3 | #FFFDA5 | EE59 | 2025-02-10 | 2025-02-14
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 TCP/MSB - COLO3 Cell 3 | #FFFDA5 | EE57 | 2025-02-10 | 2025-02-14
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 ATSs - COLO3 Cell 3 | #FFFDA5 | EE60 | 2025-02-12 | 2025-02-18
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 Busway - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-02-17 | 2025-02-21
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 ADP - COLO3 Cell 3 | #FFFDA5 | EE58 | 2025-02-17 | 2025-03-07
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 PDUs - COLO3 Cell 3 | #FFFDA5 | EE63 | 2025-02-24 | 2025-03-07
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 UPS - COLO3 Cell 3 | #FFFDA5 | EE62 | 2025-02-24 | 2025-03-14
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 TCP/MSB - COLO3 Cell 3 | #FFFDA5 | EE57 | 2025-03-17 | 2025-03-21
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 ATSs - COLO3 Cell 3 | #FFFDA5 | EE60 | 2025-01-22 | 2025-01-22
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 ADP - COLO3 Cell 3 | #FFFDA5 | EE58 | 2025-01-02 | 2025-01-02
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 UPS - COLO3 Cell 3 | #FFFDA5 | EE62 | 2025-01-14 | 2025-01-14
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 PDUs - COLO3 Cell 3 | #FFFDA5 | EE63 | 2025-01-14 | 2025-01-14
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 Busway - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-01-14 | 2025-01-14
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 AHUs - COLO3 Cell 3 | #FFFDA5 | EE59 | 2025-02-17 | 2025-02-17
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 TCP/MSB - COLO3 Cell 3 | #FFFDA5 | EE57 | 2025-01-14 | 2025-01-14
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 UPS - COLO3 Cell 3 | #FFFDA5 | EE62 | 2025-03-18 | 2025-03-24
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 PDUs - COLO3 Cell 3 | #FFFDA5 | EE63 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 ADP - COLO3 Cell 3 | #FFFDA5 | EE58 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 ATSs - COLO3 Cell 3 | #FFFDA5 | EE60 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 Busway - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-04-01 | 2025-04-07
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 AHUs - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-04-01 | 2025-04-07
COLO 3 | Cell 4 | Mech Gallery |  | Deliver AHU into Mech. Gallery - COLO3 Cell 4 - MG | #CFE741 | GA12 | 2025-04-08 | 2025-04-14
COLO 3 | Cell 4 | Mech Gallery |  | Install Walls and Primer Paint - COLO3 Cell 4 - MG | #D6F2FF | T3 | 2025-04-25 | 2025-05-01
COLO 3 | Cell 4 | Mech Gallery |  | Layout Ceiling and install Pencile Rod - COLO3 Cell 4 - MG | #3399FF | J9 | 2025-05-02 | 2025-05-08
COLO 3 | Cell 4 | Mech Gallery |  | Placing the AHU - COLO3 Cell 4 - MG | #CFE741 | GA6 | 2025-05-02 | 2025-05-08
COLO 3 | Cell 4 | Mech Gallery |  | Post Wall Overhead MEP - COLO3 Cell 4 - MG | #FFFDA5 | EE70 | 2025-05-02 | 2025-05-08
COLO 3 | Cell 4 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO3 Cell 4 - MG | #EF9E5B | ET22 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO3 Cell 4 - MG | #C00000 | I-R | 2025-05-16 | 2025-05-30
COLO 3 | Cell 4 | Mech Gallery |  | Install ceiling and Light Fittings - COLO3 Cell 4 - MG | #FFFDA5 | EE35 | 2025-06-02 | 2025-06-06
COLO 3 | Cell 4 | Mech Gallery |  | Trim out MEP - COLO3 Cell 4 - MG | #FFFDA5 | EE36 | 2025-01-13 | 2025-01-14
COLO 3 | Cell 4 | Electrical Room |  | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 4 - ER | #FFFDA5 | EE1 | 2025-01-15 | 2025-01-28
COLO 3 | Cell 4 | Electrical Room |  | Install Ceiling - COLO3 Cell 4 - ER | #3399FF | J17 | 2025-01-29 | 2025-01-29
COLO 3 | Cell 4 | Electrical Room |  | Install DX Split Units - COLO3 Cell 4 - ER | #987655 | GH3 | 2025-02-05 | 2025-02-07
COLO 3 | Cell 4 | Electrical Room |  | Installation of ADP & ATS - COLO3 Cell 4 - ER | #FFFDA5 | EE27 | 2025-01-29 | 2025-02-18
COLO 3 | Cell 4 | Electrical Room |  | Installation of UPS Equipment - COLO3 Cell 4 - ER | #FFFDA5 | EE23 | 2025-02-07 | 2025-02-21
COLO 3 | Cell 4 | Electrical Room |  | Installation of TCP/MSB - COLO3 Cell 4 - ER | #FFFDA5 | EE71 | 2025-02-21 | 2025-02-25
COLO 3 | Cell 4 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO3 Cell 4 - ER | #FFFDA5 | EE28 | 2025-02-25 | 2025-03-07
COLO 3 | Cell 4 | Electrical Room |  | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | #FFFDA5 | EE72 | 2025-03-07 | 2025-03-14
COLO 3 | Cell 4 | Electrical Room |  | Door Frame Installation - COLO3 Cell 4 - ER | #3399FF | J36 | 2024-12-20 | 2025-01-06
COLO 3 | Cell 4 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER | #FFFDA5 | EE29 | 2025-01-07 | 2025-01-09
COLO 3 | Cell 4 | Electrical Room |  | Finishes and Signage - COLO3 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-01-10 | 2025-01-16
COLO 3 | Cell 4 | Data Hall |  | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 4 - DH | #FFFDA5 | EE74 | 2025-01-14 | 2025-01-20
COLO 3 | Cell 4 | Data Hall |  | Security Screen Installation - COLO3 Cell 4 - DH | #3399FF | J6 | 2025-01-13 | 2025-01-17
COLO 3 | Cell 4 | Data Hall |  | Ceiling Grid and Tile - COLO3 Cell 4 - DH | #3399FF | J7 | 2025-01-14 | 2025-01-20
COLO 3 | Cell 4 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 4 - DH | #FFFDA5 | EE73 | 2025-01-09 | 2025-01-22
COLO 3 | Cell 4 | Data Hall |  | Install PDU's - COLO3 Cell 4 - DH | #FFFDA5 | EE7 | 2025-01-20 | 2025-01-24
COLO 3 | Cell 4 | Data Hall |  | Begin HAC Assembly - COLO3 Cell 4 - DH | #FED7E8 | S1 | 2025-01-16 | 2025-01-22
COLO 3 | Cell 4 | Data Hall |  | Install Busway - COLO3 Cell 4 - DH | #FFFDA5 | EE10 | 2025-02-06 | 2025-02-26
COLO 3 | Cell 4 | Data Hall |  | HAC install and Rise - COLO3 Cell 4 - DH | #FED7E8 | S2 | 2025-02-24 | 2025-02-28
COLO 3 | Cell 4 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH | #EF9E5B | ET7 | 2024-12-06 | 2024-12-23
COLO 3 | Cell 4 | Data Hall |  | Cable Pulling at PDU & Busway- COLO3 Cell 4 - DH | #FFFDA5 | EE17 | 2025-01-29 | 2025-01-31
COLO 3 | Cell 4 | Data Hall |  | Termination at PDU & Busway - COLO3 Cell 4 - DH | #FFFDA5 | EE18 | 2025-02-03 | 2025-02-07
COLO 3 | Cell 4 | Data Hall |  | Finishes and Signage - COLO3 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-02-10 | 2025-02-21
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 AHUs - COLO3 Cell 4 | #FFFDA5 | EE61 | 2025-02-24 | 2025-02-28
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 TCP/MSB - COLO3 Cell 4 | #FFFDA5 | EE57 | 2025-02-24 | 2025-02-28
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 ATSs - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-02-26 | 2025-03-04
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 Busway - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-03-03 | 2025-03-07
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 ADP - COLO3 Cell 4 | #FFFDA5 | EE58 | 2025-03-03 | 2025-03-14
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 UPS - COLO3 Cell 4 | #FFFDA5 | EE62 | 2025-03-10 | 2025-03-21
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 PDUs - COLO3 Cell 4 | #FFFDA5 | EE63 | 2025-03-10 | 2025-03-28
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 TCP/MSB - COLO3 Cell 4 | #FFFDA5 | EE57 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 UPS - COLO3 Cell 4 | #FFFDA5 | EE62 | 2025-01-20 | 2025-01-20
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 ATSs - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-01-21 | 2025-01-21
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 Busway - COLO3 Cell 4 | #FFFDA5 | EE61 | 2025-01-21 | 2025-01-21
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 ADP - COLO3 Cell 4 | #FFFDA5 | EE58 | 2025-01-21 | 2025-01-21
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 PDUs - COLO3 Cell 4 | #FFFDA5 | EE63 | 2025-02-05 | 2025-02-05
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 AHUs - COLO3 Cell 4 | #FFFDA5 | EE59 | 2025-03-03 | 2025-03-03
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 TCP/MSB - COLO3 Cell 4 | #FFFDA5 | EE57 | 2025-01-21 | 2025-01-21
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 PDUs - COLO3 Cell 4 | #FFFDA5 | EE63 | 2025-04-01 | 2025-04-07
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 ADP - COLO3 Cell 4 | #FFFDA5 | EE58 | 2025-04-08 | 2025-04-14
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 AHUs - COLO3 Cell 4 | #FFFDA5 | EE59 | 2025-04-08 | 2025-04-14
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 ATSs - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-04-08 | 2025-04-14
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 UPS - COLO3 Cell 4 | #FFFDA5 | EE62 | 2025-04-15 | 2025-04-21
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 Busway - COLO3 Cell 4 | #FFFDA5 | EE61 | 2025-04-15 | 2025-04-21
COLO 3 | All | CX - Microsoft |  | Level 4 Cx - Colo 3 | #000000 | MS1 | 2025-04-22 | 2025-04-28
COLO 3 | All | CX - Microsoft |  | Level 5 Cx / IST - Colo 3 | #000000 | MS2 | 2025-04-25 | 2025-05-01
COLO 4 | Cell 1 | Mech Gallery |  | Placing the AHU - COLO4 Cell 1 - MG | #CFE741 | GA6 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 1 | Mech Gallery |  | Post Wall Overhead MEP - COLO4 Cell 1 - MG | #FFFDA5 | EE70 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 1 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO4 Cell 1 - MG | #FFFDA5 | EE1 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 1 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 1 - MG | #C00000 | I-R | 2025-05-09 | 2025-05-15
COLO 4 | Cell 1 | Mech Gallery |  | Install ceiling and Light Fittings - COLO4 Cell 1 - MG | #FFFDA5 | EE35 | 2025-05-16 | 2025-05-30
COLO 4 | Cell 1 | Mech Gallery |  | Trim out MEP - COLO4 Cell 1 - MG | #FFFDA5 | EE36 | 2025-06-02 | 2025-06-06
COLO 4 | Cell 1 | Electrical Room |  | Installation of ADP & ATS - COLO4 Cell 1 - ER | #FFFDA5 | EE27 | 2025-01-13 | 2025-01-24
COLO 4 | Cell 1 | Electrical Room |  | Installation of UPS Equipment - COLO4 Cell 1 - ER | #FFFDA5 | EE23 | 2025-01-27 | 2025-01-28
COLO 4 | Cell 1 | Electrical Room |  | Installation of TCP/MSB - COLO4 Cell 1 - ER | #FFFDA5 | EE71 | 2025-01-29 | 2025-02-11
COLO 4 | Cell 1 | Electrical Room |  | Install DX Split Units - COLO4 Cell 1 - ER | #987655 | GH3 | 2025-02-12 | 2025-02-12
COLO 4 | Cell 1 | Electrical Room |  | Below Ceiling MEP Rough In - COLO4 Cell 1 - ER | #FFFDA5 | EE72 | 2025-02-19 | 2025-02-21
COLO 4 | Cell 1 | Electrical Room |  | Door Frame Installation - COLO4 Cell 1 - ER | #3399FF | J36 | 2025-02-12 | 2025-03-04
COLO 4 | Cell 1 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO4 Cell 1 - ER | #FFFDA5 | EE28 | 2025-02-21 | 2025-03-07
COLO 4 | Cell 1 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER | #FFFDA5 | EE29 | 2025-03-07 | 2025-03-11
COLO 4 | Cell 1 | Electrical Room |  | Finishes and Signage - COLO4 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-03-11 | 2025-03-21
COLO 4 | Cell 1 | Data Hall |  | Ceiling Grid and Tile - COLO4 Cell 1 - DH | #3399FF | J7 | 2025-03-21 | 2025-03-28
COLO 4 | Cell 1 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 1 - DH | #FFFDA5 | EE73 | 2025-01-07 | 2025-01-20
COLO 4 | Cell 1 | Data Hall |  | Install PDU's - COLO4 Cell 1 - DH | #FFFDA5 | EE7 | 2025-01-21 | 2025-01-23
COLO 4 | Cell 1 | Data Hall |  | Begin HAC Assembly - COLO4 Cell 1 - DH | #FED7E8 | S1 | 2025-01-24 | 2025-01-30
COLO 4 | Cell 1 | Data Hall |  | Install Busway - COLO4 Cell 1 - DH | #FFFDA5 | EE10 | 2025-01-27 | 2025-01-31
COLO 4 | Cell 1 | Data Hall |  | HAC install and Rise - COLO4 Cell 1 - DH | #FED7E8 | S2 | 2025-01-27 | 2025-01-31
COLO 4 | Cell 1 | Data Hall |  | Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH | #FFFDA5 | EE17 | 2025-01-27 | 2025-01-31
COLO 4 | Cell 1 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH | #EF9E5B | ET22 | 2025-01-23 | 2025-02-05
COLO 4 | Cell 1 | Data Hall |  | Termination at PDU & Busway- COLO4 Cell 1 - DH | #FFFDA5 | EE18 | 2025-02-03 | 2025-02-07
COLO 4 | Cell 1 | Data Hall |  | Finishes and Signage - COLO4 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-01-29 | 2025-02-04
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 AHUs - COLO4 Cell 1 | #FFFDA5 | EE59 | 2025-02-27 | 2025-03-19
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 UPS - COLO4 Cell 1 | #FFFDA5 | EE62 | 2025-03-17 | 2025-03-21
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 TCP/MSB - COLO4 Cell 1 | #FFFDA5 | EE57 | 2024-12-24 | 2025-01-10
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 ATSs - COLO4 Cell 1 | #FFFDA5 | EE60 | 2025-02-12 | 2025-02-14
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 ADP - COLO4 Cell 1 | #FFFDA5 | EE58 | 2025-02-17 | 2025-02-21
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 PDUs - COLO4 Cell 1 | #FFFDA5 | EE63 | 2025-02-24 | 2025-03-07
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 Busway - COLO4 Cell 1 | #FFFDA5 | EE61 | 2025-03-10 | 2025-03-14
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 TCP/MSB - COLO4 Cell 1 | #FFFDA5 | EE57 | 2025-03-10 | 2025-03-14
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 UPS - COLO4 Cell 1 | #FFFDA5 | EE62 | 2025-03-12 | 2025-03-18
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 PDUs - COLO4 Cell 1 | #FFFDA5 | EE63 | 2025-03-17 | 2025-03-21
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 ADP - COLO4 Cell 1 | #FFFDA5 | EE58 | 2025-03-17 | 2025-03-28
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 ATSs - COLO4 Cell 1 | #FFFDA5 | EE60 | 2025-03-24 | 2025-04-04
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 Busway - COLO4 Cell 1 | #FFFDA5 | EE61 | 2025-03-31 | 2025-04-18
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 AHUs - COLO4 Cell 1 | #FFFDA5 | EE59 | 2025-04-14 | 2025-04-18
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 TCP/MSB - COLO4 Cell 1 | #FFFDA5 | EE57 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 UPS - COLO4 Cell 1 | #FFFDA5 | EE62 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 PDUs - COLO4 Cell 1 | #FFFDA5 | EE63 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 ADP - COLO4 Cell 1 | #FFFDA5 | EE58 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 ATSs - COLO4 Cell 1 | #FFFDA5 | EE60 | 2025-02-19 | 2025-02-19
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 AHUs - COLO4 Cell 1 | #FFFDA5 | EE59 | 2025-03-17 | 2025-03-17
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 Busway - COLO4 Cell 1 | #FFFDA5 | EE61 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 2 | Mech Gallery |  | Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG | #CFE741 | GA12 | 2025-04-07 | 2025-04-11
COLO 4 | Cell 2 | Mech Gallery |  | Install Walls and Primer Paint - COLO4 Cell 2 - MG | #D6F2FF | T3 | 2025-04-14 | 2025-04-18
COLO 4 | Cell 2 | Mech Gallery |  | Layout Ceiling and install Pencile Rod - COLO4 Cell 2 - MG | #3399FF | J9 | 2025-04-14 | 2025-04-18
COLO 4 | Cell 2 | Mech Gallery |  | Placing the AHU - COLO4 Cell 2 - MG | #CFE741 | GA6 | 2025-04-14 | 2025-04-18
COLO 4 | Cell 2 | Mech Gallery |  | Post Wall Overhead MEP - COLO4 Cell 2 - MG | #FFFDA5 | EE70 | 2025-04-21 | 2025-04-25
COLO 4 | Cell 2 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO4 Cell 2 - MG | #EF9E5B | ET22 | 2025-04-21 | 2025-04-25
COLO 4 | Cell 2 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 2 - MG | #C00000 | I-R | 2025-04-28 | 2025-05-02
COLO 4 | Cell 2 | Mech Gallery |  | Install ceiling and Light Fittings - COLO4 Cell 2 - MG | #FFFDA5 | EE35 | 2025-04-25 | 2025-05-01
COLO 4 | Cell 2 | Mech Gallery |  | Trim out MEP - COLO4 Cell 2 - MG | #FFFDA5 | EE36 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 2 | Electrical Room |  | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 2 - ER | #FFFDA5 | EE1 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 2 | Electrical Room |  | Install Ceiling - COLO4 Cell 2 - ER | #3399FF | J17 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 2 | Electrical Room |  | Install DX Split Units - COLO4 Cell 2 - ER | #987655 | GH3 | 2025-05-09 | 2025-05-15
COLO 4 | Cell 2 | Electrical Room |  | Installation of ADP & ATS - COLO4 Cell 2 - ER | #FFFDA5 | EE27 | 2025-05-16 | 2025-05-30
COLO 4 | Cell 2 | Electrical Room |  | Installation of UPS Equipment - COLO4 Cell 2 - ER | #FFFDA5 | EE23 | 2025-06-02 | 2025-06-06
COLO 4 | Cell 2 | Electrical Room |  | Installation of TCP/MSB - COLO4 Cell 2 - ER | #FFFDA5 | EE71 | 2025-01-06 | 2025-01-10
COLO 4 | Cell 2 | Electrical Room |  | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | #FFFDA5 | EE72 | 2025-01-27 | 2025-02-07
COLO 4 | Cell 2 | Electrical Room |  | Door Frame Installation - COLO4 Cell 2 - ER | #3399FF | J36 | 2025-02-10 | 2025-02-11
COLO 4 | Cell 2 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO4 Cell 2 - ER | #FFFDA5 | EE28 | 2025-02-12 | 2025-02-25
COLO 4 | Cell 2 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER | #FFFDA5 | EE29 | 2025-02-26 | 2025-02-26
COLO 4 | Cell 2 | Electrical Room |  | Finishes and Signage - COLO4 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-03-05 | 2025-03-07
COLO 4 | Cell 2 | Data Hall |  | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH | #FFFDA5 | EE74 | 2025-02-26 | 2025-03-18
COLO 4 | Cell 2 | Data Hall |  | Security Screen Installation - COLO4 Cell 2 - DH | #3399FF | J6 | 2025-03-07 | 2025-03-21
COLO 4 | Cell 2 | Data Hall |  | Ceiling Grid and Tile - COLO4 Cell 2 - DH | #3399FF | J7 | 2025-03-21 | 2025-03-25
COLO 4 | Cell 2 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH | #FFFDA5 | EE73 | 2025-03-25 | 2025-04-04
COLO 4 | Cell 2 | Data Hall |  | Install PDU's - COLO4 Cell 2 - DH | #FFFDA5 | EE7 | 2025-04-04 | 2025-04-11
COLO 4 | Cell 2 | Data Hall |  | Begin HAC Assembly - COLO4 Cell 2 - DH | #FED7E8 | S1 | 2025-01-03 | 2025-01-16
COLO 4 | Cell 2 | Data Hall |  | Install Busway - COLO4 Cell 2 - DH | #FFFDA5 | EE10 | 2025-01-14 | 2025-01-20
COLO 4 | Cell 2 | Data Hall |  | HAC install and Rise - COLO4 Cell 2 - DH | #FED7E8 | S2 | 2025-01-21 | 2025-02-03
COLO 4 | Cell 2 | Data Hall |  | Cable Pulling at PDU & Busway- COLO4 Cell 2 - DH | #FFFDA5 | EE17 | 2025-02-04 | 2025-02-06
COLO 4 | Cell 2 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 2 - DH | #EF9E5B | ET7 | 2025-02-06 | 2025-02-12
COLO 4 | Cell 2 | Data Hall |  | Termination at PDU & Busway - COLO4 Cell 2 - DH | #FFFDA5 | EE18 | 2025-02-06 | 2025-02-12
COLO 4 | Cell 2 | Data Hall |  | Finishes and Signage - COLO4 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-02-07 | 2025-02-13
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 UPS - COLO4 Cell 2 | #FFFDA5 | EE62 | 2025-02-10 | 2025-02-14
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 TCP/MSB - COLO4 Cell 2 | #FFFDA5 | EE57 | 2025-02-06 | 2025-02-12
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 ATSs - COLO4 Cell 2 | #FFFDA5 | EE60 | 2025-02-06 | 2025-02-19
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 ADP - COLO4 Cell 2 | #FFFDA5 | EE58 | 2025-02-17 | 2025-02-21
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 AHUs - COLO4 Cell 2 | #FFFDA5 | EE59 | 2025-03-20 | 2025-04-09
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 PDUs - COLO4 Cell 2 | #FFFDA5 | EE63 | 2025-04-03 | 2025-04-09
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 Busway - COLO4 Cell 2 | #FFFDA5 | EE61 | 2025-01-13 | 2025-01-28
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 TCP/MSB - COLO4 Cell 2 | #FFFDA5 | EE57 | 2025-02-26 | 2025-02-28
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 UPS - COLO4 Cell 2 | #FFFDA5 | EE62 | 2025-03-03 | 2025-03-07
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 PDUs - COLO4 Cell 2 | #FFFDA5 | EE63 | 2025-03-10 | 2025-03-21
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 ADP - COLO4 Cell 2 | #FFFDA5 | EE58 | 2025-03-24 | 2025-03-28
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 ATSs - COLO4 Cell 2 | #FFFDA5 | EE60 | 2025-03-24 | 2025-03-28
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 Busway - COLO4 Cell 2 | #FFFDA5 | EE61 | 2025-03-26 | 2025-04-01
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 AHUs - COLO4 Cell 2 | #FFFDA5 | EE59 | 2025-03-31 | 2025-04-04
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 TCP/MSB - COLO4 Cell 2 | #FFFDA5 | EE57 | 2025-03-31 | 2025-04-11
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 UPS - COLO4 Cell 2 | #FFFDA5 | EE62 | 2025-03-31 | 2025-04-18
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 PDUs - COLO4 Cell 2 | #FFFDA5 | EE63 | 2025-04-07 | 2025-04-18
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 ADP - COLO4 Cell 2 | #FFFDA5 | EE58 | 2025-04-21 | 2025-05-09
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 ATSs - COLO4 Cell 2 | #FFFDA5 | EE60 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 AHUs - COLO4 Cell 2 | #FFFDA5 | EE59 | 2025-02-13 | 2025-02-13
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 Busway - COLO4 Cell 2 | #FFFDA5 | EE61 | 2025-02-13 | 2025-02-13
COLO 4 | Cell 3 | Mech Gallery |  | Overhead MEP Installation - COLO4 Cell 3 - MG | #FFFDA5 | EE73 | 2025-02-13 | 2025-02-13
COLO 4 | Cell 3 | Mech Gallery |  | Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG | #CFE741 | GA12 | 2025-02-17 | 2025-02-17
COLO 4 | Cell 3 | Mech Gallery |  | Install Walls and Primer Paint - COLO4 Cell 3 - MG | #D6F2FF | T3 | 2025-03-05 | 2025-03-05
COLO 4 | Cell 3 | Mech Gallery |  | Layout Ceiling and install Pencile Rod - COLO4 Cell 3 - MG | #3399FF | J9 | 2025-03-31 | 2025-03-31
COLO 4 | Cell 3 | Mech Gallery |  | Placing the AHU - COLO4 Cell 3 - MG | #CFE741 | GA6 | 2025-02-13 | 2025-02-13
COLO 4 | Cell 3 | Mech Gallery |  | Post Wall Overhead MEP - COLO4 Cell 3 - MG | #FFFDA5 | EE70 | 2025-04-21 | 2025-04-25
COLO 4 | Cell 3 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO4 Cell 3 - MG | #EF9E5B | ET22 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 3 - MG | #C00000 | I-R | 2025-04-28 | 2025-05-02
COLO 4 | Cell 3 | Mech Gallery |  | Install ceiling and Light Fittings - COLO4 Cell 3 - MG | #FFFDA5 | EE35 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 3 | Mech Gallery |  | Trim out MEP - COLO4 Cell 3 - MG | #FFFDA5 | EE36 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 3 | Electrical Room |  | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 3 - ER | #FFFDA5 | EE1 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 3 | Electrical Room |  | Install Ceiling - COLO4 Cell 3 - ER | #3399FF | J17 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 3 | Electrical Room |  | Install DX Split Units - COLO4 Cell 3 - ER | #987655 | GH3 | 2025-05-09 | 2025-05-15
COLO 4 | Cell 3 | Electrical Room |  | Installation of ADP & ATS - COLO4 Cell 3 - ER | #FFFDA5 | EE27 | 2025-06-03 | 2025-06-09
COLO 4 | Cell 3 | Electrical Room |  | Installation of UPS Equipment - COLO4 Cell 3 - ER | #FFFDA5 | EE23 | 2025-05-16 | 2025-05-22
COLO 4 | Cell 3 | Electrical Room |  | Installation of TCP/MSB - COLO4 Cell 3 - ER | #FFFDA5 | EE71 | 2025-05-16 | 2025-05-22
COLO 4 | Cell 3 | Electrical Room |  | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | #FFFDA5 | EE72 | 2025-05-23 | 2025-05-30
COLO 4 | Cell 3 | Electrical Room |  | Door Frame Installation - COLO4 Cell 3 - ER | #3399FF | J36 | 2025-06-03 | 2025-06-16
COLO 4 | Cell 3 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO4 Cell 3 - ER | #FFFDA5 | EE28 | 2025-06-17 | 2025-06-23
COLO 4 | Cell 3 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER | #FFFDA5 | EE29 | 2025-06-25 | 2025-07-30
COLO 4 | Cell 3 | Electrical Room |  | Finishes and Signage - COLO4 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-08-01 | 2025-08-04
COLO 4 | Cell 3 | Data Hall |  | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH | #FFFDA5 | EE74 | 2024-12-24 | 2025-01-10
COLO 4 | Cell 3 | Data Hall |  | Security Screen Installation - COLO4 Cell 3 - DH | #3399FF | J6 | 2025-02-12 | 2025-02-14
COLO 4 | Cell 3 | Data Hall |  | Ceiling Grid and Tile - COLO4 Cell 3 - DH | #3399FF | J7 | 2025-02-17 | 2025-02-21
COLO 4 | Cell 3 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH | #FFFDA5 | EE73 | 2025-02-24 | 2025-03-07
COLO 4 | Cell 3 | Data Hall |  | Install PDU's - COLO4 Cell 3 - DH | #FFFDA5 | EE7 | 2025-03-10 | 2025-03-14
COLO 4 | Cell 3 | Data Hall |  | Begin HAC Assembly - COLO4 Cell 3 - DH | #FED7E8 | S1 | 2025-03-10 | 2025-03-14
COLO 4 | Cell 3 | Data Hall |  | Install Busway - COLO4 Cell 3 - DH | #FFFDA5 | EE10 | 2025-03-12 | 2025-03-18
COLO 4 | Cell 3 | Data Hall |  | HAC install and Rise - COLO4 Cell 3 - DH | #FED7E8 | S2 | 2025-03-17 | 2025-03-21
COLO 4 | Cell 3 | Data Hall |  | Cable Pulling at PDU & Busway- COLO4 Cell 3 - DH | #FFFDA5 | EE17 | 2025-03-17 | 2025-03-28
COLO 4 | Cell 3 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 3 - DH | #EF9E5B | ET7 | 2025-03-24 | 2025-04-04
COLO 4 | Cell 3 | Data Hall |  | Termination at PDU & Busway - COLO4 Cell 3 - DH | #FFFDA5 | EE18 | 2025-03-31 | 2025-04-18
COLO 4 | Cell 3 | Data Hall |  | Finishes and Signage - COLO4 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-04-14 | 2025-04-18
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 UPS - COLO4 Cell 3 | #FFFDA5 | EE62 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 TCP/MSB - COLO4 Cell 3 | #FFFDA5 | EE57 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 ATSs - COLO4 Cell 3 | #FFFDA5 | EE60 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 ADP - COLO4 Cell 3 | #FFFDA5 | EE58 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 AHUs - COLO4 Cell 3 | #FFFDA5 | EE59 | 2025-02-19 | 2025-02-19
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 PDUs - COLO4 Cell 3 | #FFFDA5 | EE63 | 2025-03-17 | 2025-03-17
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 Busway - COLO4 Cell 3 | #FFFDA5 | EE61 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 TCP/MSB - COLO4 Cell 3 | #FFFDA5 | EE57 | 2025-04-07 | 2025-04-11
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 UPS - COLO4 Cell 3 | #FFFDA5 | EE62 | 2025-04-14 | 2025-04-18
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 PDUs - COLO4 Cell 3 | #FFFDA5 | EE63 | 2025-04-14 | 2025-04-18
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 ADP - COLO4 Cell 3 | #FFFDA5 | EE58 | 2025-04-14 | 2025-04-18
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 ATSs - COLO4 Cell 3 | #FFFDA5 | EE60 | 2025-04-21 | 2025-04-25
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 Busway - COLO4 Cell 3 | #FFFDA5 | EE61 | 2025-04-21 | 2025-04-25
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 AHUs - COLO4 Cell 3 | #FFFDA5 | EE59 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 TCP/MSB - COLO4 Cell 3 | #FFFDA5 | EE57 | 2025-04-25 | 2025-05-01
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 UPS - COLO4 Cell 3 | #FFFDA5 | EE62 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 PDUs - COLO4 Cell 3 | #FFFDA5 | EE63 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 ADP - COLO4 Cell 3 | #FFFDA5 | EE58 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 ATSs - COLO4 Cell 3 | #FFFDA5 | EE60 | 2025-05-09 | 2025-05-15
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 AHUs - COLO4 Cell 3 | #FFFDA5 | EE59 | 2025-05-16 | 2025-05-30
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 Busway - COLO4 Cell 3 | #FFFDA5 | EE61 | 2025-06-02 | 2025-06-06
COLO 4 | Cell 4 | Mech Gallery |  | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG | #CFE741 | GA3 | 2025-01-06 | 2025-01-10
COLO 4 | Cell 4 | Mech Gallery |  | Overhead MEP Installation - COLO4 Cell 4 - MG | #FFFDA5 | EE73 | 2025-01-27 | 2025-02-07
COLO 4 | Cell 4 | Mech Gallery |  | Deliver AHU into Mech. Gallery - COLO4 Cell 4 - MG | #CFE741 | GA12 | 2025-02-10 | 2025-02-11
COLO 4 | Cell 4 | Mech Gallery |  | Install Walls and Primer Paint - COLO4 Cell 4 - MG | #D6F2FF | T3 | 2025-02-12 | 2025-02-25
COLO 4 | Cell 4 | Mech Gallery |  | Layout Ceiling and install Pencile Rod - COLO4 Cell 4 - MG | #3399FF | J9 | 2025-02-26 | 2025-02-26
COLO 4 | Cell 4 | Mech Gallery |  | Placing the AHU - COLO4 Cell 4 - MG | #CFE741 | GA6 | 2025-03-05 | 2025-03-07
COLO 4 | Cell 4 | Mech Gallery |  | Post Wall Overhead MEP - COLO4 Cell 4 - MG | #FFFDA5 | EE70 | 2025-02-26 | 2025-03-18
COLO 4 | Cell 4 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO4 Cell 4 - MG | #EF9E5B | ET22 | 2025-03-07 | 2025-03-21
COLO 4 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 4 - MG | #C00000 | I-R | 2025-03-21 | 2025-03-25
COLO 4 | Cell 4 | Mech Gallery |  | Install ceiling and Light Fittings - COLO4 Cell 4 - MG | #FFFDA5 | EE35 | 2025-03-25 | 2025-04-04
COLO 4 | Cell 4 | Mech Gallery |  | Trim out MEP - COLO4 Cell 4 - MG | #FFFDA5 | EE36 | 2025-04-04 | 2025-04-11
COLO 4 | Cell 4 | Electrical Room |  | Install Walls and Primer Paint - COLO4 Cell 4 - ER | #D6F2FF | T3 | 2025-01-03 | 2025-01-16
COLO 4 | Cell 4 | Electrical Room |  | Install Upper Screens - COLO4 Cell 4 - ER | #3399FF | J37 | 2025-01-14 | 2025-01-20
COLO 4 | Cell 4 | Electrical Room |  | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 4 - ER | #FFFDA5 | EE1 | 2025-01-21 | 2025-02-03
COLO 4 | Cell 4 | Electrical Room |  | Install Ceiling - COLO4 Cell 4 - ER | #3399FF | J17 | 2025-02-04 | 2025-02-06
COLO 4 | Cell 4 | Electrical Room |  | Installation of ADP & ATS - COLO4 Cell 4 - ER | #FFFDA5 | EE27 | 2025-02-06 | 2025-02-12
COLO 4 | Cell 4 | Electrical Room |  | Installation of TCP/MSB - COLO4 Cell 4 - ER | #FFFDA5 | EE71 | 2025-02-06 | 2025-02-12
COLO 4 | Cell 4 | Electrical Room |  | Install DX Split Units - COLO4 Cell 4 - ER | #987655 | GH3 | 2025-02-07 | 2025-02-13
COLO 4 | Cell 4 | Electrical Room |  | Installation of UPS Equipment - COLO4 Cell 4 - ER | #FFFDA5 | EE23 | 2025-02-10 | 2025-02-14
COLO 4 | Cell 4 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO4 Cell 4 - ER | #FFFDA5 | EE28 | 2025-02-06 | 2025-02-12
COLO 4 | Cell 4 | Electrical Room |  | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | #FFFDA5 | EE72 | 2025-02-06 | 2025-02-19
COLO 4 | Cell 4 | Electrical Room |  | Door Frame Installation - COLO4 Cell 4 - ER | #3399FF | J36 | 2025-02-17 | 2025-02-21
COLO 4 | Cell 4 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER | #FFFDA5 | EE29 | 2025-03-20 | 2025-04-09
COLO 4 | Cell 4 | Electrical Room |  | Finishes and Signage - COLO4 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-04-03 | 2025-04-09
COLO 4 | Cell 4 | Data Hall |  | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 4 - DH | #FFFDA5 | EE74 | 2025-01-13 | 2025-01-28
COLO 4 | Cell 4 | Data Hall |  | Security Screen Installation - COLO4 Cell 4 - DH | #3399FF | J6 | 2025-02-26 | 2025-02-28
COLO 4 | Cell 4 | Data Hall |  | Ceiling Grid and Tile - COLO4 Cell 4 - DH | #3399FF | J7 | 2025-03-03 | 2025-03-07
COLO 4 | Cell 4 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 4 - DH | #FFFDA5 | EE73 | 2025-03-10 | 2025-03-21
COLO 4 | Cell 4 | Data Hall |  | Install PDU's - COLO4 Cell 4 - DH | #FFFDA5 | EE7 | 2025-03-24 | 2025-03-28
COLO 4 | Cell 4 | Data Hall |  | Begin HAC Assembly - COLO4 Cell 4 - DH | #FED7E8 | S1 | 2025-03-24 | 2025-03-28
COLO 4 | Cell 4 | Data Hall |  | Install Busway - COLO4 Cell 4 - DH | #FFFDA5 | EE10 | 2025-03-26 | 2025-04-01
COLO 4 | Cell 4 | Data Hall |  | HAC install and Rise - COLO4 Cell 4 - DH | #FED7E8 | S2 | 2025-03-31 | 2025-04-04
COLO 4 | Cell 4 | Data Hall |  | Cable Pulling at PDU & Busway- COLO4 Cell 4 - DH | #FFFDA5 | EE17 | 2025-03-31 | 2025-04-11
COLO 4 | Cell 4 | Data Hall |  | Closing Construction Access Door - COLO4 Cell 4 - DH | #04A261 | W4 | 2025-03-31 | 2025-04-18
COLO 4 | Cell 4 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH | #EF9E5B | ET7 | 2025-04-07 | 2025-04-18
COLO 4 | Cell 4 | Data Hall |  | Termination at PDU & Busway - COLO4 Cell 4 - DH | #FFFDA5 | EE18 | 2025-04-21 | 2025-05-09
COLO 4 | Cell 4 | Data Hall |  | Finishes and Signage - COLO4 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 TCP/MSB - COLO4 Cell 4 | #FFFDA5 | EE57 | 2025-02-13 | 2025-02-13
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 ATSs - COLO4 Cell 4 | #FFFDA5 | EE60 | 2025-02-13 | 2025-02-13
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 ADP - COLO4 Cell 4 | #FFFDA5 | EE58 | 2025-02-13 | 2025-02-13
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 UPS - COLO4 Cell 4 | #FFFDA5 | EE62 | 2025-02-17 | 2025-02-17
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 AHUs - COLO4 Cell 4 | #FFFDA5 | EE59 | 2025-03-05 | 2025-03-05
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 PDUs - COLO4 Cell 4 | #FFFDA5 | EE63 | 2025-03-31 | 2025-03-31
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 Busway - COLO4 Cell 4 | #FFFDA5 | EE61 | 2025-02-13 | 2025-02-13
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 TCP/MSB - COLO4 Cell 4 | #FFFDA5 | EE57 | 2025-04-21 | 2025-04-25
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 UPS - COLO4 Cell 4 | #FFFDA5 | EE62 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 PDUs - COLO4 Cell 4 | #FFFDA5 | EE63 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 ADP - COLO4 Cell 4 | #FFFDA5 | EE58 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 ATSs - COLO4 Cell 4 | #FFFDA5 | EE60 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 Busway - COLO4 Cell 4 | #FFFDA5 | EE61 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 AHUs - COLO4 Cell 4 | #FFFDA5 | EE59 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 TCP/MSB - COLO4 Cell 4 | #FFFDA5 | EE57 | 2025-05-09 | 2025-05-15
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 UPS - COLO4 Cell 4 | #FFFDA5 | EE62 | 2025-06-03 | 2025-06-09
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 PDUs - COLO4 Cell 4 | #FFFDA5 | EE63 | 2025-05-16 | 2025-05-22
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 ADP - COLO4 Cell 4 | #FFFDA5 | EE58 | 2025-05-16 | 2025-05-22
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 ATSs - COLO4 Cell 4 | #FFFDA5 | EE60 | 2025-05-23 | 2025-05-30
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 AHUs - COLO4 Cell 4 | #FFFDA5 | EE59 | 2025-06-03 | 2025-06-16
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 Busway - COLO4 Cell 4 | #FFFDA5 | EE61 | 2025-06-17 | 2025-06-23
COLO 4 | All | CX - Microsoft |  | Level 4 Cx - Colo 4 | #000000 | MS1 | 2025-06-25 | 2025-07-30
COLO 4 | All | CX - Microsoft |  | Level 5 Cx / IST - Colo 4 | #000000 | MS2 | 2025-08-01 | 2025-08-04

## CFA - Schedule
|  |  | 2024 | [25 empty] | 2025
|  |  | Dec | [25 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug
|  |  | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04
phase | location | area | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
COLO 3 | All | CX - Microsoft | Apr 22 Tue: MS1; Apr 23 Wed: MS1; Apr 24 Thu: MS1; Apr 25 Fri: MS1; Apr 26 Sat: MS1; Apr 27 Sun: MS1; Apr 28 Mon: MS1
[143 empty] | MS2 | MS2 | MS2 | MS2 | MS2 | MS2 | MS2
| Cell 1 | CX - L1 | Mar 24 Mon: EE63; Mar 25 Tue: EE63; Mar 26 Wed: EE63; Mar 27 Thu: EE63; Mar 28 Fri: EE63
[111 empty] | EE62 | EE62 | EE62 | EE62 | EE62
|  | CX - L2 | Mar 24 Mon: EE57; Mar 25 Tue: EE57; Mar 26 Wed: EE57; Mar 27 Thu: EE57; Mar 28 Fri: EE57; Mar 31 Mon: EE62; Apr 01 Tue: EE62; Apr 02 Wed: EE62; Apr 03 Thu: EE62; Apr 04 Fri: EE62; Apr 07 Mon: EE58; Apr 08 Tue: EE58; Apr 09 Wed: EE58; Apr 10 Thu: EE58; Apr 11 Fri: EE58; May 02 Fri: EE61; May 03 Sat: EE61; May 04 Sun: EE61; May 05 Mon: EE61; May 06 Tue: EE61; May 07 Wed: EE61; May 08 Thu: EE61; May 09 Fri: EE59; May 10 Sat: EE59; May 11 Sun: EE59; May 12 Mon: EE59; May 13 Tue: EE59; May 14 Wed: EE59; May 15 Thu: EE59
[118 empty] | EE63 | EE63 | EE63 | EE63 | EE63
[118 empty] | EE60 | EE60 | EE60 | EE60 | EE60
|  | CX - L3 | Jan 27 Mon: EE59; Jan 28 Tue: EE59; Jan 29 Wed: EE61; Jan 30 Thu: EE61; Jan 31 Fri: EE61; Feb 01 Sat: EE61; Feb 02 Sun: EE61; Feb 03 Mon: EE61; Feb 04 Tue: EE61; Feb 05 Wed: EE61; Feb 06 Thu: EE61; Feb 07 Fri: EE61; Feb 08 Sat: EE61; Feb 09 Sun: EE61; Feb 10 Mon: EE61; Feb 11 Tue: EE61; May 05 Mon: EE60; May 06 Tue: EE60; May 07 Wed: EE60; May 08 Thu: EE60; May 09 Fri: EE60; May 10 Sat: EE60; May 11 Sun: EE60; May 12 Mon: EE60; May 13 Tue: EE60; May 14 Wed: EE60; May 15 Thu: EE60; May 16 Fri: EE60
[157 empty] | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57
[157 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62
[160 empty] | EE63 | EE63 | EE63 | EE63 | EE63
|  | Data Hall | Feb 03 Mon: S2; Feb 05 Wed: S1; Feb 12 Wed: ALL3; Mar 03 Mon: EE18; Mar 31 Mon: EE7; Apr 01 Tue: EE7; Apr 02 Wed: EE7; Apr 03 Thu: EE7; Apr 04 Fri: EE7
EE10
EE17
ET7
|  | Electrical Room | Feb 26 Wed: EE28; Feb 27 Thu: EE28; Feb 28 Fri: EE28; Mar 01 Sat: EE28; Mar 02 Sun: EE28; Mar 03 Mon: EE28; Mar 04 Tue: EE28; Mar 10 Mon: J36; Mar 11 Tue: J36; Mar 12 Wed: J36; Mar 13 Thu: J36; Mar 14 Fri: J36; Mar 15 Sat: J36; Mar 16 Sun: J36; Mar 17 Mon: J36; Mar 18 Tue: J36; Mar 19 Wed: J36; Mar 20 Thu: J36; Mar 21 Fri: J36
[90 empty] | EE29 | EE29 | EE29 | EE29 | EE29 | [9 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[90 empty] | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23
|  | Mech Gallery | Feb 24 Mon: EE35; Feb 25 Tue: EE35; Feb 26 Wed: EE35; Feb 27 Thu: EE35; Feb 28 Fri: EE35
[83 empty] | EE36 | EE36 | EE36 | EE36 | EE36
| Cell 2 | CX - L1 | Feb 17 Mon: EE62; Feb 19 Wed: EE63; Mar 17 Mon: EE59; Mar 18 Tue: EE59; Mar 19 Wed: EE59; Mar 20 Thu: EE59; Mar 21 Fri: EE59; Mar 24 Mon: EE57; Mar 25 Tue: EE57; Mar 26 Wed: EE57; Mar 27 Thu: EE57; Mar 28 Fri: EE57; Mar 29 Sat: EE57; Mar 30 Sun: EE57; Mar 31 Mon: EE57; Apr 01 Tue: EE57; Apr 02 Wed: EE57; Apr 03 Thu: EE57; Apr 04 Fri: EE57; Apr 07 Mon: EE61; Apr 08 Tue: EE61; Apr 09 Wed: EE61; Apr 10 Thu: EE61; Apr 11 Fri: EE61; Apr 12 Sat: EE61; Apr 13 Sun: EE61; Apr 14 Mon: EE61; Apr 15 Tue: EE61; Apr 16 Wed: EE61; Apr 17 Thu: EE61; Apr 18 Fri: EE61; Apr 19 Sat: EE61; Apr 20 Sun: EE61; Apr 21 Mon: EE61; Apr 22 Tue: EE61; Apr 23 Wed: EE61; Apr 24 Thu: EE61; Apr 25 Fri: EE61
[104 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | [23 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L2 | Feb 12 Wed: EE58; Feb 17 Mon: EE57; Mar 17 Mon: EE60; Apr 07 Mon: EE61; Apr 08 Tue: EE61; Apr 09 Wed: EE61; Apr 10 Thu: EE61; Apr 11 Fri: EE61; Apr 14 Mon: EE59; Apr 15 Tue: EE59; Apr 16 Wed: EE59; Apr 17 Thu: EE59; Apr 18 Fri: EE59
EE62
EE63
|  | CX - L3 | Apr 14 Mon: EE57; Apr 15 Tue: EE57; Apr 16 Wed: EE57; Apr 17 Thu: EE57; Apr 18 Fri: EE57; Apr 21 Mon: EE62; Apr 22 Tue: EE62; Apr 23 Wed: EE62; Apr 24 Thu: EE62; Apr 25 Fri: EE62; Apr 28 Mon: EE63; Apr 29 Tue: EE63; Apr 30 Wed: EE63; May 01 Thu: EE63; May 02 Fri: EE63; May 09 Fri: EE61; May 10 Sat: EE61; May 11 Sun: EE61; May 12 Mon: EE61; May 13 Tue: EE61; May 14 Wed: EE61; May 15 Thu: EE61
[139 empty] | EE58 | EE58 | EE58 | EE58 | EE58 |  |  | EE60 | EE60 | EE60 | EE60 | EE60
[150 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | Data Hall | Jan 13 Mon: S1; Jan 14 Tue: S1; Jan 15 Wed: S1; Jan 16 Thu: S1; Jan 17 Fri: S1; Jan 18 Sat: S1; Jan 19 Sun: S1; Jan 20 Mon: S1; Jan 21 Tue: S1; Jan 22 Wed: S1; Jan 23 Thu: S1; Jan 24 Fri: S1; Jan 25 Sat: S1; Jan 26 Sun: S1; Jan 27 Mon: S1; Jan 28 Tue: S1; Feb 12 Wed: EE10; Feb 13 Thu: EE10; Feb 14 Fri: EE10; Feb 17 Mon: J7; Feb 18 Tue: J7; Feb 19 Wed: J7; Feb 20 Thu: J7; Feb 21 Fri: J7; Feb 24 Mon: EE17; Feb 25 Tue: EE17; Feb 26 Wed: EE17; Feb 27 Thu: EE17; Feb 28 Fri: EE17; Mar 01 Sat: EE17; Mar 02 Sun: EE17; Mar 03 Mon: EE17; Mar 04 Tue: EE17; Mar 05 Wed: EE17; Mar 06 Thu: EE17; Mar 07 Fri: EE17; Mar 10 Mon: ET7; Mar 11 Tue: ET7; Mar 12 Wed: ET7; Mar 13 Thu: ET7; Mar 14 Fri: ET7; Mar 17 Mon: EE73; Mar 18 Tue: EE73; Mar 19 Wed: EE73; Mar 20 Thu: EE73; Mar 21 Fri: EE73; Mar 22 Sat: EE73; Mar 23 Sun: EE73; Mar 24 Mon: EE73; Mar 25 Tue: EE73; Mar 26 Wed: EE73; Mar 27 Thu: EE73; Mar 28 Fri: EE73; Mar 29 Sat: EE73; Mar 30 Sun: EE73; Mar 31 Mon: EE73; Apr 01 Tue: EE73; Apr 02 Wed: EE73; Apr 03 Thu: EE73; Apr 04 Fri: EE73
[76 empty] | S2 | S2 | S2 | S2 | S2 | [16 empty] | EE18 | EE18 | EE18 | EE18 | EE18 | [18 empty] | EE7 | EE7 | EE7 | EE7 | EE7 | EE7 | EE7
[99 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
|  | Electrical Room | Jan 21 Tue: EE27; Jan 22 Wed: EE27; Jan 23 Thu: EE27; Jan 24 Fri: EE27; Jan 25 Sat: EE27; Jan 26 Sun: EE27; Jan 27 Mon: EE27; Jan 28 Tue: EE27; Jan 29 Wed: EE27; Jan 30 Thu: EE27; Jan 31 Fri: EE27; Feb 01 Sat: EE27; Feb 02 Sun: EE27; Feb 03 Mon: EE27; Feb 04 Tue: EE23; Feb 05 Wed: EE23; Feb 06 Thu: EE23; Feb 07 Fri: EE71; Feb 08 Sat: EE71; Feb 09 Sun: EE71; Feb 10 Mon: EE71; Feb 11 Tue: EE71; Feb 12 Wed: EE71; Feb 13 Thu: EE71; Mar 21 Fri: GH3; Mar 22 Sat: GH3; Mar 23 Sun: GH3; Mar 24 Mon: GH3; Mar 25 Tue: GH3; Mar 26 Wed: GH3; Mar 27 Thu: GH3; Mar 28 Fri: GH3
[65 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[69 empty] | EE72 | EE72 | EE72 | EE72 | EE72
[69 empty] | J36 | J36 | J36 | J36 | J36
[69 empty] | EE28 | EE28 | EE28 | EE28 | EE28
|  | Mech Gallery | Feb 12 Wed: GA6; Feb 19 Wed: EE70; Feb 20 Thu: EE70; Feb 21 Fri: EE70; Mar 07 Fri: EE35; Mar 08 Sat: EE35; Mar 09 Sun: EE35; Mar 10 Mon: EE35; Mar 11 Tue: EE35
[71 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | [6 empty] | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36
[80 empty] | I-R | I-R | I-R | I-R | I-R | I-R | I-R | I-R | I-R | I-R | I-R | I-R | I-R | I-R | I-R
| Cell 3 | CX - L1 | Feb 10 Mon: EE59; Feb 11 Tue: EE59; Feb 12 Wed: EE59; Feb 13 Thu: EE59; Feb 14 Fri: EE59; Feb 17 Mon: EE61; Feb 18 Tue: EE61; Feb 19 Wed: EE61; Feb 20 Thu: EE61; Feb 21 Fri: EE61; Feb 24 Mon: EE63; Feb 25 Tue: EE63; Feb 26 Wed: EE63; Feb 27 Thu: EE63; Feb 28 Fri: EE63; Mar 01 Sat: EE63; Mar 02 Sun: EE63; Mar 03 Mon: EE63; Mar 04 Tue: EE63; Mar 05 Wed: EE63; Mar 06 Thu: EE63; Mar 07 Fri: EE63
[69 empty] | EE57 | EE57 | EE57 | EE57 | EE57 |  |  | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
[71 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | [5 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62
|  | CX - L2 | Jan 02 Thu: EE58; Jan 14 Tue: EE62; Jan 22 Wed: EE60; Feb 17 Mon: EE59; Mar 17 Mon: EE57; Mar 18 Tue: EE57; Mar 19 Wed: EE57; Mar 20 Thu: EE57; Mar 21 Fri: EE57
EE63
EE61
|  | CX - L3 | Jan 14 Tue: EE57; Mar 18 Tue: EE62; Mar 19 Wed: EE62; Mar 20 Thu: EE62; Mar 21 Fri: EE62; Mar 22 Sat: EE62; Mar 23 Sun: EE62; Mar 24 Mon: EE62; Mar 25 Tue: EE63; Mar 26 Wed: EE63; Mar 27 Thu: EE63; Mar 28 Fri: EE63; Mar 29 Sat: EE63; Mar 30 Sun: EE63; Mar 31 Mon: EE63; Apr 01 Tue: EE61; Apr 02 Wed: EE61; Apr 03 Thu: EE61; Apr 04 Fri: EE61; Apr 05 Sat: EE61; Apr 06 Sun: EE61; Apr 07 Mon: EE61
[112 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[112 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
|  | Data Hall | Dec 20 Fri: S1; Dec 21 Sat: S1; Dec 22 Sun: S1; Dec 23 Mon: S1; Dec 24 Tue: S1; Dec 25 Wed: S1; Dec 26 Thu: S1; Dec 27 Fri: S1; Dec 28 Sat: S1; Dec 29 Sun: S1; Dec 30 Mon: S1; Dec 31 Tue: S1; Jan 01 Wed: S1; Jan 02 Thu: S1; Jan 03 Fri: S1; Jan 04 Sat: S1; Jan 05 Sun: S1; Jan 06 Mon: S1; Jan 07 Tue: EE73; Jan 08 Wed: EE73; Jan 09 Thu: EE73; Jan 10 Fri: EE73; Jan 11 Sat: EE73; Jan 12 Sun: EE73; Jan 13 Mon: EE73; Jan 16 Thu: EE17; Jan 17 Fri: EE17; Jan 18 Sat: EE17; Jan 19 Sun: EE17; Jan 20 Mon: EE17; Jan 21 Tue: EE17; Jan 22 Wed: EE17; Jan 23 Thu: EE17; Jan 24 Fri: EE17; Jan 25 Sat: EE17; Jan 26 Sun: EE17; Jan 27 Mon: EE17; Jan 28 Tue: EE17; Jan 29 Wed: EE17; Jan 30 Thu: EE17; Jan 31 Fri: EE17; Feb 01 Sat: EE17; Feb 02 Sun: EE17; Feb 03 Mon: EE17; Feb 04 Tue: EE17; Feb 05 Wed: EE17
[20 empty] | EE7 | EE7 | EE7 | EE7 | EE7 | EE7 | EE7 | EE7 |  |  |  | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [10 empty] | EE18 | EE18 | EE18 | EE18 | EE18 |  |  | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[21 empty] | J7 | J7 | J7 | J7 | J7 | J7 | J7 | J7 | [8 empty] | S2 | S2 | S2 | S2 | S2 | S2 | S2 | [18 empty] | ET7 | ET7 | ET7 | ET7 | ET7
|  | Electrical Room | Jan 07 Tue: ALL3; Jan 08 Wed: ALL3; Jan 09 Thu: ALL3; Jan 10 Fri: ALL3; Jan 11 Sat: ALL3; Jan 12 Sun: ALL3; Jan 13 Mon: ALL3; Jan 15 Wed: EE71; Jan 16 Thu: EE71; Jan 17 Fri: EE71; Jan 18 Sat: EE71; Jan 19 Sun: EE71; Jan 20 Mon: EE71; Jan 21 Tue: EE71; Jan 22 Wed: EE71; Jan 23 Thu: EE71; Jan 24 Fri: EE71; Jan 25 Sat: EE71; Jan 26 Sun: EE71; Jan 27 Mon: EE71; Jan 28 Tue: EE71; Jan 29 Wed: EE71; Jan 30 Thu: EE71; Jan 31 Fri: EE71; Feb 01 Sat: EE71; Feb 02 Sun: EE71; Feb 03 Mon: EE71; Feb 04 Tue: EE71; Feb 07 Fri: J36; Feb 08 Sat: J36; Feb 09 Sun: J36; Feb 10 Mon: J36; Feb 11 Tue: J36; Feb 21 Fri: EE29; Feb 22 Sat: EE29; Feb 23 Sun: EE29; Feb 24 Mon: EE29; Feb 25 Tue: EE29; Feb 26 Wed: EE29; Feb 27 Thu: EE29; Feb 28 Fri: EE29; May 27 Tue: GH3; May 28 Wed: GH3; May 29 Thu: GH3; May 30 Fri: GH3; May 31 Sat: GH3; Jun 01 Sun: GH3; Jun 02 Mon: GH3; Jun 03 Tue: GH3; Jun 04 Wed: GH3; Jun 05 Thu: GH3; Jun 06 Fri: GH3; Jun 07 Sat: GH3; Jun 08 Sun: GH3; Jun 09 Mon: GH3; Jun 10 Tue: GH3; Jun 11 Wed: GH3; Jun 12 Thu: GH3; Jun 13 Fri: GH3; Jun 14 Sat: GH3; Jun 15 Sun: GH3; Jun 16 Mon: GH3; Jun 17 Tue: GH3; Jun 18 Wed: GH3; Jun 19 Thu: GH3; Jun 20 Fri: GH3; Jun 21 Sat: GH3; Jun 22 Sun: GH3; Jun 23 Mon: GH3; Jun 24 Tue: GH3; Jun 25 Wed: GH3; Jun 26 Thu: GH3; Jun 27 Fri: GH3; Jun 28 Sat: GH3; Jun 29 Sun: GH3; Jun 30 Mon: GH3; Jul 01 Tue: EE27; Jul 02 Wed: EE27
[50 empty] | EE23 | EE23 | EE23 | [17 empty] | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28
[52 empty] | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72
|  | Mech Gallery | May 05 Mon: ET22; May 06 Tue: ET22; May 07 Wed: ET22; May 08 Thu: ET22; May 09 Fri: ET22; May 10 Sat: ET22; May 11 Sun: ET22; May 12 Mon: ET22; May 13 Tue: ET22; May 14 Wed: ET22; May 15 Thu: ET22; May 16 Fri: ET22; May 19 Mon: EE36; May 20 Tue: EE36; May 21 Wed: EE36; May 22 Thu: EE36; May 23 Fri: EE36
[157 empty] | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70
[157 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
[160 empty] | I-R | I-R | I-R | I-R | I-R
| Cell 4 | CX - L1 | Feb 24 Mon: EE61; Feb 25 Tue: EE61; Feb 26 Wed: EE61; Feb 27 Thu: EE61; Feb 28 Fri: EE61; Mar 03 Mon: EE60; Mar 04 Tue: EE60; Mar 05 Wed: EE60; Mar 06 Thu: EE60; Mar 07 Fri: EE60; Mar 10 Mon: EE62; Mar 11 Tue: EE62; Mar 12 Wed: EE62; Mar 13 Thu: EE62; Mar 14 Fri: EE62; Mar 15 Sat: EE62; Mar 16 Sun: EE62; Mar 17 Mon: EE62; Mar 18 Tue: EE62; Mar 19 Wed: EE62; Mar 20 Thu: EE62; Mar 21 Fri: EE62
[83 empty] | EE57 | EE57 | EE57 | EE57 | EE57 |  |  | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
[85 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | [5 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
|  | CX - L2 | Jan 20 Mon: EE62; Jan 21 Tue: EE60; Feb 05 Wed: EE63; Mar 03 Mon: EE59; Mar 24 Mon: EE57; Mar 25 Tue: EE57; Mar 26 Wed: EE57; Mar 27 Thu: EE57; Mar 28 Fri: EE57
EE61
EE58
|  | CX - L3 | Jan 21 Tue: EE57; Apr 01 Tue: EE63; Apr 02 Wed: EE63; Apr 03 Thu: EE63; Apr 04 Fri: EE63; Apr 05 Sat: EE63; Apr 06 Sun: EE63; Apr 07 Mon: EE63; Apr 08 Tue: EE58; Apr 09 Wed: EE58; Apr 10 Thu: EE58; Apr 11 Fri: EE58; Apr 12 Sat: EE58; Apr 13 Sun: EE58; Apr 14 Mon: EE58; Apr 15 Tue: EE62; Apr 16 Wed: EE62; Apr 17 Thu: EE62; Apr 18 Fri: EE62; Apr 19 Sat: EE62; Apr 20 Sun: EE62; Apr 21 Mon: EE62
[126 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[126 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
|  | Data Hall | Dec 06 Fri: ET7; Dec 07 Sat: ET7; Dec 08 Sun: ET7; Dec 09 Mon: ET7; Dec 10 Tue: ET7; Dec 11 Wed: ET7; Dec 12 Thu: ET7; Dec 13 Fri: ET7; Dec 14 Sat: ET7; Dec 15 Sun: ET7; Dec 16 Mon: ET7; Dec 17 Tue: ET7; Dec 18 Wed: ET7; Dec 19 Thu: ET7; Dec 20 Fri: ET7; Dec 21 Sat: ET7; Dec 22 Sun: ET7; Dec 23 Mon: ET7; Jan 09 Thu: EE73; Jan 10 Fri: EE73; Jan 11 Sat: EE73; Jan 12 Sun: EE73; Jan 13 Mon: EE73; Jan 14 Tue: EE73; Jan 15 Wed: EE73; Jan 16 Thu: EE73; Jan 17 Fri: EE73; Jan 18 Sat: EE73; Jan 19 Sun: EE73; Jan 20 Mon: EE73; Jan 21 Tue: EE73; Jan 22 Wed: EE73; Jan 29 Wed: EE17; Jan 30 Thu: EE17; Jan 31 Fri: EE17; Feb 03 Mon: EE18; Feb 04 Tue: EE18; Feb 05 Wed: EE18; Feb 06 Thu: EE18; Feb 07 Fri: EE18; Feb 10 Mon: ALL3; Feb 11 Tue: ALL3; Feb 12 Wed: ALL3; Feb 13 Thu: ALL3; Feb 14 Fri: ALL3; Feb 15 Sat: ALL3; Feb 16 Sun: ALL3; Feb 17 Mon: ALL3; Feb 18 Tue: ALL3; Feb 19 Wed: ALL3; Feb 20 Thu: ALL3; Feb 21 Fri: ALL3; Feb 24 Mon: S2; Feb 25 Tue: S2; Feb 26 Wed: S2; Feb 27 Thu: S2; Feb 28 Fri: S2
[41 empty] | J6 | J6 | J6 | J6 | J6 |  |  | EE7 | EE7 | EE7 | EE7 | EE7 | [12 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10
[42 empty] | EE74 | EE74 | EE74 | EE74 | EE74 | EE74 | EE74
[42 empty] | J7 | J7 | J7 | J7 | J7 | J7 | J7
|  | Electrical Room | Dec 20 Fri: J36; Dec 21 Sat: J36; Dec 22 Sun: J36; Dec 23 Mon: J36; Dec 24 Tue: J36; Dec 25 Wed: J36; Dec 26 Thu: J36; Dec 27 Fri: J36; Dec 28 Sat: J36; Dec 29 Sun: J36; Dec 30 Mon: J36; Dec 31 Tue: J36; Jan 01 Wed: J36; Jan 02 Thu: J36; Jan 03 Fri: J36; Jan 04 Sat: J36; Jan 05 Sun: J36; Jan 06 Mon: J36; Jan 07 Tue: EE29; Jan 08 Wed: EE29; Jan 09 Thu: EE29; Jan 10 Fri: ALL3; Jan 11 Sat: ALL3; Jan 12 Sun: ALL3; Jan 13 Mon: ALL3; Jan 14 Tue: ALL3; Jan 15 Wed: ALL3; Jan 16 Thu: ALL3; Jan 29 Wed: J17; Feb 05 Wed: GH3; Feb 06 Thu: GH3; Feb 07 Fri: GH3; Feb 21 Fri: EE71; Feb 22 Sat: EE71; Feb 23 Sun: EE71; Feb 24 Mon: EE71; Feb 25 Tue: EE71; Mar 07 Fri: EE72; Mar 08 Sat: EE72; Mar 09 Sun: EE72; Mar 10 Mon: EE72; Mar 11 Tue: EE72; Mar 12 Wed: EE72; Mar 13 Thu: EE72; Mar 14 Fri: EE72
[43 empty] | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | [6 empty] | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28
[66 empty] | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23
|  | Mech Gallery | Jan 13 Mon: EE36; Jan 14 Tue: EE36; Apr 08 Tue: GA12; Apr 09 Wed: GA12; Apr 10 Thu: GA12; Apr 11 Fri: GA12; Apr 12 Sat: GA12; Apr 13 Sun: GA12; Apr 14 Mon: GA12; Apr 25 Fri: T3; Apr 26 Sat: T3; Apr 27 Sun: T3; Apr 28 Mon: T3; Apr 29 Tue: T3; Apr 30 Wed: T3; May 01 Thu: T3; May 02 Fri: J9; May 03 Sat: J9; May 04 Sun: J9; May 05 Mon: J9; May 06 Tue: J9; May 07 Wed: J9; May 08 Thu: J9; May 09 Fri: ET22; May 10 Sat: ET22; May 11 Sun: ET22; May 12 Mon: ET22; May 13 Tue: ET22; May 14 Wed: ET22; May 15 Thu: ET22; May 16 Fri: I-R; May 17 Sat: I-R; May 18 Sun: I-R; May 19 Mon: I-R; May 20 Tue: I-R; May 21 Wed: I-R; May 22 Thu: I-R; May 23 Fri: I-R; May 24 Sat: I-R; May 25 Sun: I-R; May 26 Mon: I-R; May 27 Tue: I-R; May 28 Wed: I-R; May 29 Thu: I-R; May 30 Fri: I-R; Jun 02 Mon: EE35; Jun 03 Tue: EE35; Jun 04 Wed: EE35; Jun 05 Thu: EE35; Jun 06 Fri: EE35
[150 empty] | GA6 | GA6 | GA6 | GA6 | GA6 | GA6 | GA6
[150 empty] | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70
COLO 4 | All | CX - Microsoft | Jun 25 Wed: MS1; Jun 26 Thu: MS1; Jun 27 Fri: MS1; Jun 28 Sat: MS1; Jun 29 Sun: MS1; Jun 30 Mon: MS1; Jul 01 Tue: MS1; Jul 02 Wed: MS1; Jul 03 Thu: MS1; Jul 04 Fri: MS1; Jul 05 Sat: MS1; Jul 06 Sun: MS1; Jul 07 Mon: MS1; Jul 08 Tue: MS1; Jul 09 Wed: MS1; Jul 10 Thu: MS1; Jul 11 Fri: MS1; Jul 12 Sat: MS1; Jul 13 Sun: MS1; Jul 14 Mon: MS1; Jul 15 Tue: MS1; Jul 16 Wed: MS1; Jul 17 Thu: MS1; Jul 18 Fri: MS1; Jul 19 Sat: MS1; Jul 20 Sun: MS1; Jul 21 Mon: MS1; Jul 22 Tue: MS1; Jul 23 Wed: MS1; Jul 24 Thu: MS1; Jul 25 Fri: MS1; Jul 26 Sat: MS1; Jul 27 Sun: MS1; Jul 28 Mon: MS1; Jul 29 Tue: MS1; Jul 30 Wed: MS1; Aug 01 Fri: MS2; Aug 02 Sat: MS2; Aug 03 Sun: MS2; Aug 04 Mon: MS2
| Cell 1 | CX - L1 | Dec 24 Tue: EE57; Dec 25 Wed: EE57; Dec 26 Thu: EE57; Dec 27 Fri: EE57; Dec 28 Sat: EE57; Dec 29 Sun: EE57; Dec 30 Mon: EE57; Dec 31 Tue: EE57; Jan 01 Wed: EE57; Jan 02 Thu: EE57; Jan 03 Fri: EE57; Jan 04 Sat: EE57; Jan 05 Sun: EE57; Jan 06 Mon: EE57; Jan 07 Tue: EE57; Jan 08 Wed: EE57; Jan 09 Thu: EE57; Jan 10 Fri: EE57; Feb 12 Wed: EE60; Feb 13 Thu: EE60; Feb 14 Fri: EE60; Feb 17 Mon: EE58; Feb 18 Tue: EE58; Feb 19 Wed: EE58; Feb 20 Thu: EE58; Feb 21 Fri: EE58; Feb 24 Mon: EE63; Feb 25 Tue: EE63; Feb 26 Wed: EE63; Feb 27 Thu: EE63; Feb 28 Fri: EE63; Mar 01 Sat: EE63; Mar 02 Sun: EE63; Mar 03 Mon: EE63; Mar 04 Tue: EE63; Mar 05 Wed: EE63; Mar 06 Thu: EE63; Mar 07 Fri: EE63; Mar 10 Mon: EE61; Mar 11 Tue: EE61; Mar 12 Wed: EE61; Mar 13 Thu: EE61; Mar 14 Fri: EE61; Mar 17 Mon: EE62; Mar 18 Tue: EE62; Mar 19 Wed: EE62; Mar 20 Thu: EE62; Mar 21 Fri: EE62
[86 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | CX - L2 | Mar 10 Mon: EE57; Mar 11 Tue: EE57; Mar 12 Wed: EE57; Mar 13 Thu: EE57; Mar 14 Fri: EE57; Mar 17 Mon: EE63; Mar 18 Tue: EE63; Mar 19 Wed: EE63; Mar 20 Thu: EE63; Mar 21 Fri: EE63; Mar 24 Mon: EE60; Mar 25 Tue: EE60; Mar 26 Wed: EE60; Mar 27 Thu: EE60; Mar 28 Fri: EE60; Mar 29 Sat: EE60; Mar 30 Sun: EE60; Mar 31 Mon: EE60; Apr 01 Tue: EE60; Apr 02 Wed: EE60; Apr 03 Thu: EE60; Apr 04 Fri: EE60; Apr 14 Mon: EE59; Apr 15 Tue: EE59; Apr 16 Wed: EE59; Apr 17 Thu: EE59; Apr 18 Fri: EE59
[99 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | [12 empty] | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[104 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | Feb 03 Mon: EE57; Feb 19 Wed: EE60; Mar 17 Mon: EE59
EE62
EE63
EE58
EE61
|  | Data Hall | Jan 07 Tue: EE73; Jan 08 Wed: EE73; Jan 09 Thu: EE73; Jan 10 Fri: EE73; Jan 11 Sat: EE73; Jan 12 Sun: EE73; Jan 13 Mon: EE73; Jan 14 Tue: EE73; Jan 15 Wed: EE73; Jan 16 Thu: EE73; Jan 17 Fri: EE73; Jan 18 Sat: EE73; Jan 19 Sun: EE73; Jan 20 Mon: EE73; Jan 21 Tue: EE7; Jan 22 Wed: EE7; Jan 23 Thu: EE7; Jan 24 Fri: S1; Jan 25 Sat: S1; Jan 26 Sun: S1; Jan 27 Mon: S1; Jan 28 Tue: S1; Jan 29 Wed: S1; Jan 30 Thu: S1; Feb 03 Mon: EE18; Feb 04 Tue: EE18; Feb 05 Wed: EE18; Feb 06 Thu: EE18; Feb 07 Fri: EE18; Mar 21 Fri: J7; Mar 22 Sat: J7; Mar 23 Sun: J7; Mar 24 Mon: J7; Mar 25 Tue: J7; Mar 26 Wed: J7; Mar 27 Thu: J7; Mar 28 Fri: J7
[51 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22
[55 empty] | EE10 | EE10 | EE10 | EE10 | EE10
[55 empty] | S2 | S2 | S2 | S2 | S2
|  | Electrical Room | Jan 13 Mon: EE27; Jan 14 Tue: EE27; Jan 15 Wed: EE27; Jan 16 Thu: EE27; Jan 17 Fri: EE27; Jan 18 Sat: EE27; Jan 19 Sun: EE27; Jan 20 Mon: EE27; Jan 21 Tue: EE27; Jan 22 Wed: EE27; Jan 23 Thu: EE27; Jan 24 Fri: EE27; Jan 27 Mon: EE23; Jan 28 Tue: EE23; Jan 29 Wed: EE71; Jan 30 Thu: EE71; Jan 31 Fri: EE71; Feb 01 Sat: EE71; Feb 02 Sun: EE71; Feb 03 Mon: EE71; Feb 04 Tue: EE71; Feb 05 Wed: EE71; Feb 06 Thu: EE71; Feb 07 Fri: EE71; Feb 08 Sat: EE71; Feb 09 Sun: EE71; Feb 10 Mon: EE71; Feb 11 Tue: EE71; Feb 12 Wed: GH3; Feb 19 Wed: EE72; Feb 20 Thu: EE72; Feb 21 Fri: EE72; Mar 07 Fri: EE29; Mar 08 Sat: EE29; Mar 09 Sun: EE29; Mar 10 Mon: EE29; Mar 11 Tue: EE29
[71 empty] | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | [6 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[80 empty] | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28
|  | Mech Gallery | May 02 Fri: GA6; May 03 Sat: GA6; May 04 Sun: GA6; May 05 Mon: GA6; May 06 Tue: GA6; May 07 Wed: GA6; May 08 Thu: GA6; May 09 Fri: I-R; May 10 Sat: I-R; May 11 Sun: I-R; May 12 Mon: I-R; May 13 Tue: I-R; May 14 Wed: I-R; May 15 Thu: I-R; May 16 Fri: EE35; May 17 Sat: EE35; May 18 Sun: EE35; May 19 Mon: EE35; May 20 Tue: EE35; May 21 Wed: EE35; May 22 Thu: EE35; May 23 Fri: EE35; May 24 Sat: EE35; May 25 Sun: EE35; May 26 Mon: EE35; May 27 Tue: EE35; May 28 Wed: EE35; May 29 Thu: EE35; May 30 Fri: EE35; Jun 02 Mon: EE36; Jun 03 Tue: EE36; Jun 04 Wed: EE36; Jun 05 Thu: EE36; Jun 06 Fri: EE36
[150 empty] | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70
[150 empty] | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1
| Cell 2 | CX - L1 | Jan 13 Mon: EE61; Jan 14 Tue: EE61; Jan 15 Wed: EE61; Jan 16 Thu: EE61; Jan 17 Fri: EE61; Jan 18 Sat: EE61; Jan 19 Sun: EE61; Jan 20 Mon: EE61; Jan 21 Tue: EE61; Jan 22 Wed: EE61; Jan 23 Thu: EE61; Jan 24 Fri: EE61; Jan 25 Sat: EE61; Jan 26 Sun: EE61; Jan 27 Mon: EE61; Jan 28 Tue: EE61; Feb 06 Thu: EE57; Feb 07 Fri: EE57; Feb 08 Sat: EE57; Feb 09 Sun: EE57; Feb 10 Mon: EE57; Feb 11 Tue: EE57; Feb 12 Wed: EE57; Feb 17 Mon: EE58; Feb 18 Tue: EE58; Feb 19 Wed: EE58; Feb 20 Thu: EE58; Feb 21 Fri: EE58; Mar 20 Thu: EE59; Mar 21 Fri: EE59; Mar 22 Sat: EE59; Mar 23 Sun: EE59; Mar 24 Mon: EE59; Mar 25 Tue: EE59; Mar 26 Wed: EE59; Mar 27 Thu: EE59; Mar 28 Fri: EE59; Mar 29 Sat: EE59; Mar 30 Sun: EE59; Mar 31 Mon: EE59; Apr 01 Tue: EE59; Apr 02 Wed: EE59; Apr 03 Thu: EE59; Apr 04 Fri: EE59; Apr 05 Sat: EE59; Apr 06 Sun: EE59; Apr 07 Mon: EE59; Apr 08 Tue: EE59; Apr 09 Wed: EE59
[65 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | [42 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[69 empty] | EE62 | EE62 | EE62 | EE62 | EE62
|  | CX - L2 | Feb 26 Wed: EE57; Feb 27 Thu: EE57; Feb 28 Fri: EE57; Mar 03 Mon: EE62; Mar 04 Tue: EE62; Mar 05 Wed: EE62; Mar 06 Thu: EE62; Mar 07 Fri: EE62; Mar 10 Mon: EE63; Mar 11 Tue: EE63; Mar 12 Wed: EE63; Mar 13 Thu: EE63; Mar 14 Fri: EE63; Mar 15 Sat: EE63; Mar 16 Sun: EE63; Mar 17 Mon: EE63; Mar 18 Tue: EE63; Mar 19 Wed: EE63; Mar 20 Thu: EE63; Mar 21 Fri: EE63; Mar 24 Mon: EE58; Mar 25 Tue: EE58; Mar 26 Wed: EE58; Mar 27 Thu: EE58; Mar 28 Fri: EE58; Mar 31 Mon: EE59; Apr 01 Tue: EE59; Apr 02 Wed: EE59; Apr 03 Thu: EE59; Apr 04 Fri: EE59
[111 empty] | EE60 | EE60 | EE60 | EE60 | EE60
[113 empty] | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
|  | CX - L3 | Feb 13 Thu: EE59; Mar 31 Mon: EE57; Apr 01 Tue: EE57; Apr 02 Wed: EE57; Apr 03 Thu: EE57; Apr 04 Fri: EE57; Apr 05 Sat: EE57; Apr 06 Sun: EE57; Apr 07 Mon: EE57; Apr 08 Tue: EE57; Apr 09 Wed: EE57; Apr 10 Thu: EE57; Apr 11 Fri: EE57; Apr 21 Mon: EE58; Apr 22 Tue: EE58; Apr 23 Wed: EE58; Apr 24 Thu: EE58; Apr 25 Fri: EE58; Apr 26 Sat: EE58; Apr 27 Sun: EE58; Apr 28 Mon: EE58; Apr 29 Tue: EE58; Apr 30 Wed: EE58; May 01 Thu: EE58; May 02 Fri: EE58; May 03 Sat: EE58; May 04 Sun: EE58; May 05 Mon: EE58; May 06 Tue: EE58; May 07 Wed: EE58; May 08 Thu: EE58; May 09 Fri: EE58
[72 empty] | EE61 | [45 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | [16 empty] | EE60 | EE60 | EE60 | EE60 | EE60
[125 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
|  | Data Hall | Jan 03 Fri: S1; Jan 04 Sat: S1; Jan 05 Sun: S1; Jan 06 Mon: S1; Jan 07 Tue: S1; Jan 08 Wed: S1; Jan 09 Thu: S1; Jan 10 Fri: S1; Jan 11 Sat: S1; Jan 12 Sun: S1; Jan 13 Mon: S1; Jan 14 Tue: S1; Jan 15 Wed: S1; Jan 16 Thu: S1; Jan 21 Tue: S2; Jan 22 Wed: S2; Jan 23 Thu: S2; Jan 24 Fri: S2; Jan 25 Sat: S2; Jan 26 Sun: S2; Jan 27 Mon: S2; Jan 28 Tue: S2; Jan 29 Wed: S2; Jan 30 Thu: S2; Jan 31 Fri: S2; Feb 01 Sat: S2; Feb 02 Sun: S2; Feb 03 Mon: S2; Feb 04 Tue: EE17; Feb 05 Wed: EE17; Feb 06 Thu: EE17; Feb 07 Fri: ALL3; Feb 08 Sat: ALL3; Feb 09 Sun: ALL3; Feb 10 Mon: ALL3; Feb 11 Tue: ALL3; Feb 12 Wed: ALL3; Feb 13 Thu: ALL3; Feb 26 Wed: EE74; Feb 27 Thu: EE74; Feb 28 Fri: EE74; Mar 01 Sat: EE74; Mar 02 Sun: EE74; Mar 03 Mon: EE74; Mar 04 Tue: EE74; Mar 05 Wed: EE74; Mar 06 Thu: EE74; Mar 07 Fri: EE74; Mar 08 Sat: EE74; Mar 09 Sun: EE74; Mar 10 Mon: EE74; Mar 11 Tue: EE74; Mar 12 Wed: EE74; Mar 13 Thu: EE74; Mar 14 Fri: EE74; Mar 15 Sat: EE74; Mar 16 Sun: EE74; Mar 17 Mon: EE74; Mar 18 Tue: EE74; Mar 21 Fri: J7; Mar 22 Sat: J7; Mar 23 Sun: J7; Mar 24 Mon: J7; Mar 25 Tue: J7; Apr 04 Fri: EE7; Apr 05 Sat: EE7; Apr 06 Sun: EE7; Apr 07 Mon: EE7; Apr 08 Tue: EE7; Apr 09 Wed: EE7; Apr 10 Thu: EE7; Apr 11 Fri: EE7
[42 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [16 empty] | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | [22 empty] | J6 | J6 | J6 | J6 | J6 | J6 | J6 | J6 | J6 | J6 | J6 | J6 | J6 | J6 | J6 |  |  |  | EE73 | EE73 | EE73 | EE73 | EE73 | EE73 | EE73 | EE73 | EE73 | EE73 | EE73
[65 empty] | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | Jan 06 Mon: EE71; Jan 07 Tue: EE71; Jan 08 Wed: EE71; Jan 09 Thu: EE71; Jan 10 Fri: EE71; Jan 27 Mon: EE72; Jan 28 Tue: EE72; Jan 29 Wed: EE72; Jan 30 Thu: EE72; Jan 31 Fri: EE72; Feb 01 Sat: EE72; Feb 02 Sun: EE72; Feb 03 Mon: EE72; Feb 04 Tue: EE72; Feb 05 Wed: EE72; Feb 06 Thu: EE72; Feb 07 Fri: EE72; Feb 10 Mon: J36; Feb 11 Tue: J36; Feb 12 Wed: EE28; Feb 13 Thu: EE28; Feb 14 Fri: EE28; Feb 15 Sat: EE28; Feb 16 Sun: EE28; Feb 17 Mon: EE28; Feb 18 Tue: EE28; Feb 19 Wed: EE28; Feb 20 Thu: EE28; Feb 21 Fri: EE28; Feb 22 Sat: EE28; Feb 23 Sun: EE28; Feb 24 Mon: EE28; Feb 25 Tue: EE28; Feb 26 Wed: EE29; Mar 05 Wed: ALL3; Mar 06 Thu: ALL3; Mar 07 Fri: ALL3; May 02 Fri: EE1; May 03 Sat: EE1; May 04 Sun: EE1; May 05 Mon: EE1; May 06 Tue: EE1; May 07 Wed: EE1; May 08 Thu: EE1; May 09 Fri: GH3; May 10 Sat: GH3; May 11 Sun: GH3; May 12 Mon: GH3; May 13 Tue: GH3; May 14 Wed: GH3; May 15 Thu: GH3; May 16 Fri: EE27; May 17 Sat: EE27; May 18 Sun: EE27; May 19 Mon: EE27; May 20 Tue: EE27; May 21 Wed: EE27; May 22 Thu: EE27; May 23 Fri: EE27; May 24 Sat: EE27; May 25 Sun: EE27; May 26 Mon: EE27; May 27 Tue: EE27; May 28 Wed: EE27; May 29 Thu: EE27; May 30 Fri: EE27; Jun 02 Mon: EE23; Jun 03 Tue: EE23; Jun 04 Wed: EE23; Jun 05 Thu: EE23; Jun 06 Fri: EE23
[150 empty] | J17 | J17 | J17 | J17 | J17 | J17 | J17
|  | Mech Gallery | Apr 07 Mon: GA12; Apr 08 Tue: GA12; Apr 09 Wed: GA12; Apr 10 Thu: GA12; Apr 11 Fri: GA12; Apr 14 Mon: T3; Apr 15 Tue: T3; Apr 16 Wed: T3; Apr 17 Thu: T3; Apr 18 Fri: T3; Apr 21 Mon: EE70; Apr 22 Tue: EE70; Apr 23 Wed: EE70; Apr 24 Thu: EE70; Apr 25 Fri: EE70; Apr 28 Mon: I-R; Apr 29 Tue: I-R; Apr 30 Wed: I-R; May 01 Thu: I-R; May 02 Fri: I-R
[132 empty] | J9 | J9 | J9 | J9 | J9 |  |  | ET22 | ET22 | ET22 | ET22 | ET22 | [6 empty] | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36
[132 empty] | GA6 | GA6 | GA6 | GA6 | GA6 | [6 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
| Cell 3 | CX - L1 | Feb 03 Mon: EE62; Feb 19 Wed: EE59; Mar 17 Mon: EE63
EE57
EE60
EE58
|  | CX - L2 | Apr 07 Mon: EE57; Apr 08 Tue: EE57; Apr 09 Wed: EE57; Apr 10 Thu: EE57; Apr 11 Fri: EE57; Apr 14 Mon: EE62; Apr 15 Tue: EE62; Apr 16 Wed: EE62; Apr 17 Thu: EE62; Apr 18 Fri: EE62; Apr 21 Mon: EE60; Apr 22 Tue: EE60; Apr 23 Wed: EE60; Apr 24 Thu: EE60; Apr 25 Fri: EE60; Apr 28 Mon: EE59; Apr 29 Tue: EE59; Apr 30 Wed: EE59; May 01 Thu: EE59; May 02 Fri: EE59
[132 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE61 | EE61 | EE61 | EE61 | EE61
[132 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | Apr 25 Fri: EE57; Apr 26 Sat: EE57; Apr 27 Sun: EE57; Apr 28 Mon: EE57; Apr 29 Tue: EE57; Apr 30 Wed: EE57; May 01 Thu: EE57; May 02 Fri: EE62; May 03 Sat: EE62; May 04 Sun: EE62; May 05 Mon: EE62; May 06 Tue: EE62; May 07 Wed: EE62; May 08 Thu: EE62; May 09 Fri: EE60; May 10 Sat: EE60; May 11 Sun: EE60; May 12 Mon: EE60; May 13 Tue: EE60; May 14 Wed: EE60; May 15 Thu: EE60; May 16 Fri: EE59; May 17 Sat: EE59; May 18 Sun: EE59; May 19 Mon: EE59; May 20 Tue: EE59; May 21 Wed: EE59; May 22 Thu: EE59; May 23 Fri: EE59; May 24 Sat: EE59; May 25 Sun: EE59; May 26 Mon: EE59; May 27 Tue: EE59; May 28 Wed: EE59; May 29 Thu: EE59; May 30 Fri: EE59; Jun 02 Mon: EE61; Jun 03 Tue: EE61; Jun 04 Wed: EE61; Jun 05 Thu: EE61; Jun 06 Fri: EE61
[150 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[150 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | Dec 24 Tue: EE74; Dec 25 Wed: EE74; Dec 26 Thu: EE74; Dec 27 Fri: EE74; Dec 28 Sat: EE74; Dec 29 Sun: EE74; Dec 30 Mon: EE74; Dec 31 Tue: EE74; Jan 01 Wed: EE74; Jan 02 Thu: EE74; Jan 03 Fri: EE74; Jan 04 Sat: EE74; Jan 05 Sun: EE74; Jan 06 Mon: EE74; Jan 07 Tue: EE74; Jan 08 Wed: EE74; Jan 09 Thu: EE74; Jan 10 Fri: EE74; Feb 12 Wed: J6; Feb 13 Thu: J6; Feb 14 Fri: J6; Feb 17 Mon: J7; Feb 18 Tue: J7; Feb 19 Wed: J7; Feb 20 Thu: J7; Feb 21 Fri: J7; Feb 24 Mon: EE73; Feb 25 Tue: EE73; Feb 26 Wed: EE73; Feb 27 Thu: EE73; Feb 28 Fri: EE73; Mar 01 Sat: EE73; Mar 02 Sun: EE73; Mar 03 Mon: EE73; Mar 04 Tue: EE73; Mar 05 Wed: EE73; Mar 06 Thu: EE73; Mar 07 Fri: EE73; Mar 10 Mon: EE7; Mar 11 Tue: EE7; Mar 12 Wed: EE7; Mar 13 Thu: EE7; Mar 14 Fri: EE7; Mar 17 Mon: S2; Mar 18 Tue: S2; Mar 19 Wed: S2; Mar 20 Thu: S2; Mar 21 Fri: S2; Mar 24 Mon: ET7; Mar 25 Tue: ET7; Mar 26 Wed: ET7; Mar 27 Thu: ET7; Mar 28 Fri: ET7; Mar 29 Sat: ET7; Mar 30 Sun: ET7; Mar 31 Mon: ET7; Apr 01 Tue: ET7; Apr 02 Wed: ET7; Apr 03 Thu: ET7; Apr 04 Fri: ET7; Apr 14 Mon: ALL3; Apr 15 Tue: ALL3; Apr 16 Wed: ALL3; Apr 17 Thu: ALL3; Apr 18 Fri: ALL3
[97 empty] | S1 | S1 | S1 | S1 | S1 |  |  | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 |  |  | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
[99 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10
|  | Electrical Room | May 05 Mon: EE1; May 06 Tue: EE1; May 07 Wed: EE1; May 08 Thu: EE1; May 09 Fri: EE1; May 12 Mon: J17; May 13 Tue: J17; May 14 Wed: J17; May 15 Thu: J17; May 16 Fri: J17; May 23 Fri: EE72; May 24 Sat: EE72; May 25 Sun: EE72; May 26 Mon: EE72; May 27 Tue: EE72; May 28 Wed: EE72; May 29 Thu: EE72; May 30 Fri: EE72; Jun 03 Tue: EE27; Jun 04 Wed: EE27; Jun 05 Thu: EE27; Jun 06 Fri: EE27; Jun 07 Sat: EE27; Jun 08 Sun: EE27; Jun 09 Mon: EE27; Jun 17 Tue: EE28; Jun 18 Wed: EE28; Jun 19 Thu: EE28; Jun 20 Fri: EE28; Jun 21 Sat: EE28; Jun 22 Sun: EE28; Jun 23 Mon: EE28; Jun 25 Wed: EE29; Jun 26 Thu: EE29; Jun 27 Fri: EE29; Jun 28 Sat: EE29; Jun 29 Sun: EE29; Jun 30 Mon: EE29; Jul 01 Tue: EE29; Jul 02 Wed: EE29; Jul 03 Thu: EE29; Jul 04 Fri: EE29; Jul 05 Sat: EE29; Jul 06 Sun: EE29; Jul 07 Mon: EE29; Jul 08 Tue: EE29; Jul 09 Wed: EE29; Jul 10 Thu: EE29; Jul 11 Fri: EE29; Jul 12 Sat: EE29; Jul 13 Sun: EE29; Jul 14 Mon: EE29; Jul 15 Tue: EE29; Jul 16 Wed: EE29; Jul 17 Thu: EE29; Jul 18 Fri: EE29; Jul 19 Sat: EE29; Jul 20 Sun: EE29; Jul 21 Mon: EE29; Jul 22 Tue: EE29; Jul 23 Wed: EE29; Jul 24 Thu: EE29; Jul 25 Fri: EE29; Jul 26 Sat: EE29; Jul 27 Sun: EE29; Jul 28 Mon: EE29; Jul 29 Tue: EE29; Jul 30 Wed: EE29; Aug 01 Fri: ALL3; Aug 02 Sat: ALL3; Aug 03 Sun: ALL3; Aug 04 Mon: ALL3
[157 empty] | GH3 | GH3 | GH3 | GH3 | GH3 | GH3 | GH3 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | [11 empty] | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36
[164 empty] | EE71 | EE71 | EE71 | EE71 | EE71 | EE71 | EE71
|  | Mech Gallery | Feb 13 Thu: EE73; Feb 17 Mon: GA12; Mar 05 Wed: T3; Mar 31 Mon: J9; Apr 21 Mon: EE70; Apr 22 Tue: EE70; Apr 23 Wed: EE70; Apr 24 Thu: EE70; Apr 25 Fri: EE70; Apr 28 Mon: ET22; Apr 29 Tue: ET22; Apr 30 Wed: ET22; May 01 Thu: ET22; May 02 Fri: ET22; May 05 Mon: EE36; May 06 Tue: EE36; May 07 Wed: EE36; May 08 Thu: EE36; May 09 Fri: EE36
[72 empty] | GA6 | [73 empty] | I-R | I-R | I-R | I-R | I-R
[146 empty] | EE35 | EE35 | EE35 | EE35 | EE35
| Cell 4 | CX - L1 | Feb 13 Thu: EE57; Feb 17 Mon: EE62; Mar 05 Wed: EE59; Mar 31 Mon: EE63
EE60
EE58
EE61
|  | CX - L2 | Apr 21 Mon: EE57; Apr 22 Tue: EE57; Apr 23 Wed: EE57; Apr 24 Thu: EE57; Apr 25 Fri: EE57; Apr 28 Mon: EE62; Apr 29 Tue: EE62; Apr 30 Wed: EE62; May 01 Thu: EE62; May 02 Fri: EE62; May 05 Mon: EE60; May 06 Tue: EE60; May 07 Wed: EE60; May 08 Thu: EE60; May 09 Fri: EE60; May 12 Mon: EE59; May 13 Tue: EE59; May 14 Wed: EE59; May 15 Thu: EE59; May 16 Fri: EE59
[146 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE61 | EE61 | EE61 | EE61 | EE61
[146 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | May 09 Fri: EE57; May 10 Sat: EE57; May 11 Sun: EE57; May 12 Mon: EE57; May 13 Tue: EE57; May 14 Wed: EE57; May 15 Thu: EE57; May 16 Fri: EE63; May 17 Sat: EE63; May 18 Sun: EE63; May 19 Mon: EE63; May 20 Tue: EE63; May 21 Wed: EE63; May 22 Thu: EE63; May 23 Fri: EE60; May 24 Sat: EE60; May 25 Sun: EE60; May 26 Mon: EE60; May 27 Tue: EE60; May 28 Wed: EE60; May 29 Thu: EE60; May 30 Fri: EE60; Jun 03 Tue: EE62; Jun 04 Wed: EE62; Jun 05 Thu: EE62; Jun 06 Fri: EE62; Jun 07 Sat: EE62; Jun 08 Sun: EE62; Jun 09 Mon: EE62; Jun 17 Tue: EE61; Jun 18 Wed: EE61; Jun 19 Thu: EE61; Jun 20 Fri: EE61; Jun 21 Sat: EE61; Jun 22 Sun: EE61; Jun 23 Mon: EE61
[164 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | [11 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | Data Hall | Jan 13 Mon: EE74; Jan 14 Tue: EE74; Jan 15 Wed: EE74; Jan 16 Thu: EE74; Jan 17 Fri: EE74; Jan 18 Sat: EE74; Jan 19 Sun: EE74; Jan 20 Mon: EE74; Jan 21 Tue: EE74; Jan 22 Wed: EE74; Jan 23 Thu: EE74; Jan 24 Fri: EE74; Jan 25 Sat: EE74; Jan 26 Sun: EE74; Jan 27 Mon: EE74; Jan 28 Tue: EE74; Feb 26 Wed: J6; Feb 27 Thu: J6; Feb 28 Fri: J6; Mar 03 Mon: J7; Mar 04 Tue: J7; Mar 05 Wed: J7; Mar 06 Thu: J7; Mar 07 Fri: J7; Mar 10 Mon: EE73; Mar 11 Tue: EE73; Mar 12 Wed: EE73; Mar 13 Thu: EE73; Mar 14 Fri: EE73; Mar 15 Sat: EE73; Mar 16 Sun: EE73; Mar 17 Mon: EE73; Mar 18 Tue: EE73; Mar 19 Wed: EE73; Mar 20 Thu: EE73; Mar 21 Fri: EE73; Mar 24 Mon: EE7; Mar 25 Tue: EE7; Mar 26 Wed: EE7; Mar 27 Thu: EE7; Mar 28 Fri: EE7; Mar 31 Mon: S2; Apr 01 Tue: S2; Apr 02 Wed: S2; Apr 03 Thu: S2; Apr 04 Fri: S2; Apr 07 Mon: ET7; Apr 08 Tue: ET7; Apr 09 Wed: ET7; Apr 10 Thu: ET7; Apr 11 Fri: ET7; Apr 12 Sat: ET7; Apr 13 Sun: ET7; Apr 14 Mon: ET7; Apr 15 Tue: ET7; Apr 16 Wed: ET7; Apr 17 Thu: ET7; Apr 18 Fri: ET7; Apr 21 Mon: EE18; Apr 22 Tue: EE18; Apr 23 Wed: EE18; Apr 24 Thu: EE18; Apr 25 Fri: EE18; Apr 26 Sat: EE18; Apr 27 Sun: EE18; Apr 28 Mon: EE18; Apr 29 Tue: EE18; Apr 30 Wed: EE18; May 01 Thu: EE18; May 02 Fri: EE18; May 03 Sat: EE18; May 04 Sun: EE18; May 05 Mon: EE18; May 06 Tue: EE18; May 07 Wed: EE18; May 08 Thu: EE18; May 09 Fri: EE18
[111 empty] | S1 | S1 | S1 | S1 | S1 |  |  | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | [23 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[113 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10
[118 empty] | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4
|  | Electrical Room | Jan 03 Fri: T3; Jan 04 Sat: T3; Jan 05 Sun: T3; Jan 06 Mon: T3; Jan 07 Tue: T3; Jan 08 Wed: T3; Jan 09 Thu: T3; Jan 10 Fri: T3; Jan 11 Sat: T3; Jan 12 Sun: T3; Jan 13 Mon: T3; Jan 14 Tue: T3; Jan 15 Wed: T3; Jan 16 Thu: T3; Jan 21 Tue: EE1; Jan 22 Wed: EE1; Jan 23 Thu: EE1; Jan 24 Fri: EE1; Jan 25 Sat: EE1; Jan 26 Sun: EE1; Jan 27 Mon: EE1; Jan 28 Tue: EE1; Jan 29 Wed: EE1; Jan 30 Thu: EE1; Jan 31 Fri: EE1; Feb 01 Sat: EE1; Feb 02 Sun: EE1; Feb 03 Mon: EE1; Feb 04 Tue: J17; Feb 05 Wed: J17; Feb 06 Thu: J17; Feb 07 Fri: GH3; Feb 08 Sat: GH3; Feb 09 Sun: GH3; Feb 10 Mon: GH3; Feb 11 Tue: GH3; Feb 12 Wed: GH3; Feb 13 Thu: GH3; Feb 17 Mon: J36; Feb 18 Tue: J36; Feb 19 Wed: J36; Feb 20 Thu: J36; Feb 21 Fri: J36; Mar 20 Thu: EE29; Mar 21 Fri: EE29; Mar 22 Sat: EE29; Mar 23 Sun: EE29; Mar 24 Mon: EE29; Mar 25 Tue: EE29; Mar 26 Wed: EE29; Mar 27 Thu: EE29; Mar 28 Fri: EE29; Mar 29 Sat: EE29; Mar 30 Sun: EE29; Mar 31 Mon: EE29; Apr 01 Tue: EE29; Apr 02 Wed: EE29; Apr 03 Thu: EE29; Apr 04 Fri: EE29; Apr 05 Sat: EE29; Apr 06 Sun: EE29; Apr 07 Mon: EE29; Apr 08 Tue: EE29; Apr 09 Wed: EE29
[42 empty] | J37 | J37 | J37 | J37 | J37 | J37 | J37 | [16 empty] | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | [49 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[65 empty] | EE71 | EE71 | EE71 | EE71 | EE71 | EE71 | EE71
[65 empty] | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28
|  | Mech Gallery | Jan 06 Mon: GA3; Jan 07 Tue: GA3; Jan 08 Wed: GA3; Jan 09 Thu: GA3; Jan 10 Fri: GA3; Jan 27 Mon: EE73; Jan 28 Tue: EE73; Jan 29 Wed: EE73; Jan 30 Thu: EE73; Jan 31 Fri: EE73; Feb 01 Sat: EE73; Feb 02 Sun: EE73; Feb 03 Mon: EE73; Feb 04 Tue: EE73; Feb 05 Wed: EE73; Feb 06 Thu: EE73; Feb 07 Fri: EE73; Feb 10 Mon: GA12; Feb 11 Tue: GA12; Feb 12 Wed: T3; Feb 13 Thu: T3; Feb 14 Fri: T3; Feb 15 Sat: T3; Feb 16 Sun: T3; Feb 17 Mon: T3; Feb 18 Tue: T3; Feb 19 Wed: T3; Feb 20 Thu: T3; Feb 21 Fri: T3; Feb 22 Sat: T3; Feb 23 Sun: T3; Feb 24 Mon: T3; Feb 25 Tue: T3; Feb 26 Wed: J9; Mar 05 Wed: GA6; Mar 06 Thu: GA6; Mar 07 Fri: GA6; Mar 21 Fri: I-R; Mar 22 Sat: I-R; Mar 23 Sun: I-R; Mar 24 Mon: I-R; Mar 25 Tue: I-R; Apr 04 Fri: EE36; Apr 05 Sat: EE36; Apr 06 Sun: EE36; Apr 07 Mon: EE36; Apr 08 Tue: EE36; Apr 09 Wed: EE36; Apr 10 Thu: EE36; Apr 11 Fri: EE36
[85 empty] | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | [6 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
[94 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22
COLO 5 | All | CX - Microsoft | Feb 03 Mon: MS1; Feb 04 Tue: MS1; Feb 05 Wed: MS1; Feb 06 Thu: MS1; Feb 07 Fri: MS1; Feb 10 Mon: MS2; Feb 11 Tue: MS2; Feb 12 Wed: MS2; Feb 13 Thu: MS2; Feb 14 Fri: MS2; Feb 15 Sat: MS2; Feb 16 Sun: MS2; Feb 17 Mon: MS2; Feb 18 Tue: MS2; Feb 19 Wed: MS2; Feb 20 Thu: MS2; Feb 21 Fri: MS2
| Cell 1 | CX - L2 | Jan 06 Mon: EE57; Jan 07 Tue: EE57; Jan 08 Wed: EE57; Jan 09 Thu: EE57; Jan 10 Fri: EE57; Jan 13 Mon: EE62; Jan 14 Tue: EE62; Jan 15 Wed: EE62; Jan 16 Thu: EE62; Jan 17 Fri: EE62; Jan 18 Sat: EE62; Jan 19 Sun: EE62; Jan 20 Mon: EE62; Jan 21 Tue: EE62; Jan 22 Wed: EE62; Jan 23 Thu: EE62; Jan 24 Fri: EE62; Jan 25 Sat: EE62; Jan 26 Sun: EE62; Jan 27 Mon: EE62; Jan 28 Tue: EE62; Jan 29 Wed: EE62; Jan 30 Thu: EE62; Jan 31 Fri: EE62; Feb 03 Mon: EE58; Feb 04 Tue: EE58; Feb 05 Wed: EE58; Feb 06 Thu: EE58; Feb 07 Fri: EE58; Feb 10 Mon: EE63; Feb 11 Tue: EE63; Feb 12 Wed: EE63; Feb 13 Thu: EE63; Feb 14 Fri: EE63; Feb 17 Mon: EE59; Feb 18 Tue: EE59; Feb 19 Wed: EE59; Feb 20 Thu: EE59; Feb 21 Fri: EE59
[55 empty] | EE60 | EE60 | EE60 | EE60 | EE60
[55 empty] | EE61 | EE61 | EE61 | EE61 | EE61
|  | CX - L3 | Jan 29 Wed: EE63; Jan 30 Thu: EE63; Jan 31 Fri: EE63; Feb 01 Sat: EE63; Feb 02 Sun: EE63; Feb 03 Mon: EE63; Feb 04 Tue: EE63; Feb 10 Mon: EE58; Feb 11 Tue: EE58; Feb 12 Wed: EE58; Feb 13 Thu: EE58; Feb 14 Fri: EE58; Feb 15 Sat: EE58; Feb 16 Sun: EE58; Feb 17 Mon: EE58; Feb 18 Tue: EE58; Feb 19 Wed: EE58; Feb 20 Thu: EE58; Feb 21 Fri: EE58; Mar 03 Mon: EE59; Mar 04 Tue: EE59; Mar 05 Wed: EE59; Mar 06 Thu: EE59; Mar 07 Fri: EE59
[62 empty] | EE61 | [6 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
[62 empty] | EE57 | EE57 | EE57 | EE57 | EE57
[62 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62
|  | Data Hall | Jan 28 Tue: EE18; Jan 29 Wed: EE18; Jan 30 Thu: EE18; Jan 31 Fri: EE18; Feb 01 Sat: EE18; Feb 02 Sun: EE18; Feb 03 Mon: EE18; Feb 04 Tue: EE18; Feb 05 Wed: EE18; Feb 06 Thu: EE18; Feb 07 Fri: EE18
[66 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
|  | Electrical Room | Apr 30 Wed: EE29; May 01 Thu: EE29; May 02 Fri: EE29; May 03 Sat: EE29; May 04 Sun: EE29; May 05 Mon: EE29; May 06 Tue: EE29; May 07 Wed: EE29; May 08 Thu: EE29; May 09 Fri: EE29; May 10 Sat: EE29; May 11 Sun: EE29; May 12 Mon: EE29; May 13 Tue: EE29; May 14 Wed: EE29; May 15 Thu: EE29; May 16 Fri: EE29; May 17 Sat: EE29; May 18 Sun: EE29; May 19 Mon: EE29; May 20 Tue: EE29; May 21 Wed: EE29; May 22 Thu: EE29; May 23 Fri: EE29; May 24 Sat: EE29; May 25 Sun: EE29; May 26 Mon: EE29; May 27 Tue: EE29; May 28 Wed: EE29; May 29 Thu: EE29; May 30 Fri: EE29; May 31 Sat: EE29; Jun 01 Sun: EE29; Jun 02 Mon: EE29; Jun 03 Tue: EE29; Jun 04 Wed: ALL3; Jun 05 Thu: ALL3
|  | Mech Gallery | Apr 18 Fri: EE36; Apr 19 Sat: EE36; Apr 20 Sun: EE36; Apr 21 Mon: EE36; Apr 22 Tue: EE36; Apr 23 Wed: EE36; Apr 24 Thu: EE36
| Cell 2 | CX - L2 | May 02 Fri: EE57; May 03 Sat: EE57; May 04 Sun: EE57; May 05 Mon: EE57; May 06 Tue: EE57; May 07 Wed: EE57; May 08 Thu: EE57; May 09 Fri: EE62; May 10 Sat: EE62; May 11 Sun: EE62; May 12 Mon: EE62; May 13 Tue: EE62; May 14 Wed: EE62; May 15 Thu: EE62; May 16 Fri: EE61; May 17 Sat: EE61; May 18 Sun: EE61; May 19 Mon: EE61; May 20 Tue: EE61; May 21 Wed: EE61; May 22 Thu: EE61
[153 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
[157 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[157 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
[157 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | CX - L3 | Jan 10 Fri: EE61; Jan 11 Sat: EE61; Jan 12 Sun: EE61; Jan 13 Mon: EE61; Jan 14 Tue: EE61; Jan 15 Wed: EE61; Jan 16 Thu: EE61; Jan 22 Wed: EE57; Jan 23 Thu: EE57; Jan 24 Fri: EE57; Feb 07 Fri: EE62; Feb 08 Sat: EE62; Feb 09 Sun: EE62; Feb 10 Mon: EE62; Feb 11 Tue: EE62; Feb 21 Fri: EE59; Feb 22 Sat: EE59; Feb 23 Sun: EE59; Feb 24 Mon: EE59; Feb 25 Tue: EE59; Feb 26 Wed: EE59; Feb 27 Thu: EE59; Feb 28 Fri: EE59
[43 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | [6 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
[52 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | Mar 25 Tue: EE18; Mar 26 Wed: EE18; Mar 27 Thu: EE18; Mar 28 Fri: EE18; Mar 29 Sat: EE18; Mar 30 Sun: EE18; Mar 31 Mon: EE18; Apr 01 Tue: ET7; Apr 02 Wed: ET7; Apr 03 Thu: ET7; Apr 04 Fri: ET7; Apr 05 Sat: ET7; Apr 06 Sun: ET7; Apr 07 Mon: ET7; Apr 08 Tue: ALL3; Apr 09 Wed: ALL3; Apr 10 Thu: ALL3; Apr 11 Fri: ALL3; Apr 12 Sat: ALL3; Apr 13 Sun: ALL3; Apr 14 Mon: ALL3
[119 empty] | EE19 | EE19 | EE19 | EE19 | EE19 | EE19 | EE19
|  | Electrical Room | Mar 25 Tue: EE29; Mar 26 Wed: EE29; Mar 27 Thu: EE29; Mar 28 Fri: EE29; Mar 29 Sat: EE29; Mar 30 Sun: EE29; Mar 31 Mon: EE29
[112 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
|  | Mech Gallery | Feb 10 Mon: EE35; Mar 18 Tue: EE36; Mar 19 Wed: EE36; Mar 20 Thu: EE36; Mar 21 Fri: EE36; Mar 22 Sat: EE36; Mar 23 Sun: EE36; Mar 24 Mon: EE36
| Cell 3 | CX - L2 | Jan 27 Mon: EE57; Jan 28 Tue: EE57; Jan 29 Wed: EE57; Jan 30 Thu: EE57; Jan 31 Fri: EE57; Feb 01 Sat: EE57; Feb 02 Sun: EE57; Feb 03 Mon: EE57; Feb 04 Tue: EE57; Feb 05 Wed: EE57; Feb 06 Thu: EE57; Feb 07 Fri: EE57; Feb 10 Mon: EE62; Feb 11 Tue: EE62; Feb 12 Wed: EE62; Feb 13 Thu: EE62; Feb 14 Fri: EE62; Feb 17 Mon: EE59; Feb 18 Tue: EE59; Feb 19 Wed: EE59; Feb 20 Thu: EE59; Feb 21 Fri: EE59; Feb 24 Mon: EE61; Feb 25 Tue: EE61; Feb 26 Wed: EE61; Feb 27 Thu: EE61; Feb 28 Fri: EE61; Mar 01 Sat: EE61; Mar 02 Sun: EE61; Mar 03 Mon: EE61; Mar 04 Tue: EE61; Mar 05 Wed: EE61; Mar 06 Thu: EE61; Mar 07 Fri: EE61
[69 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
[71 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | Jan 20 Mon: EE62; Jan 22 Wed: EE58; Feb 24 Mon: EE57; Feb 25 Tue: EE57; Feb 26 Wed: EE57; Feb 27 Thu: EE57; Feb 28 Fri: EE57; Mar 01 Sat: EE57; Mar 02 Sun: EE57; Mar 03 Mon: EE57; Mar 04 Tue: EE57; Mar 05 Wed: EE57; Mar 06 Thu: EE57; Mar 07 Fri: EE57; Mar 08 Sat: EE57; Mar 09 Sun: EE57; Mar 10 Mon: EE57; Mar 11 Tue: EE57; Mar 12 Wed: EE57; Mar 13 Thu: EE57; Mar 14 Fri: EE57
[48 empty] | EE60 | [48 empty] | EE63 | EE63 | EE63 | EE63 | EE63
EE59
EE61
|  | Data Hall | Jan 20 Mon: ALL3; Jan 21 Tue: ALL3; Jan 22 Wed: ALL3; Jan 23 Thu: ALL3; Jan 24 Fri: ALL3; Feb 03 Mon: EE17; Feb 04 Tue: EE17; Feb 05 Wed: EE17; Feb 06 Thu: EE17; Feb 07 Fri: EE17; Feb 08 Sat: EE17; Feb 09 Sun: EE17; Feb 10 Mon: EE17; Feb 11 Tue: EE17; Feb 12 Wed: EE17; Feb 13 Thu: EE17; Feb 14 Fri: EE17; Feb 15 Sat: EE17; Feb 16 Sun: EE17; Feb 17 Mon: EE17; Feb 18 Tue: EE17; Feb 19 Wed: EE17; Feb 20 Thu: EE17; Feb 21 Fri: EE17; Feb 24 Mon: EE18; Feb 25 Tue: EE18; Feb 26 Wed: EE18; Feb 27 Thu: EE18; Feb 28 Fri: EE18
|  | Electrical Room | Jan 09 Thu: EE28; Jan 10 Fri: EE28; Jan 11 Sat: EE28; Jan 12 Sun: EE28; Jan 13 Mon: EE28; Jan 14 Tue: EE28; Jan 15 Wed: EE28; Jan 16 Thu: EE28; Jan 17 Fri: EE28; Jan 18 Sat: EE28; Jan 19 Sun: EE28; Jan 20 Mon: EE28; Jan 21 Tue: EE28; Jan 22 Wed: EE28
[43 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[48 empty] | EE18 | EE18 | EE18 | EE18 | EE18
|  | Mech Gallery | Jan 13 Mon: I-R; Jan 14 Tue: I-R; Jan 15 Wed: I-R; Jan 16 Thu: I-R; Jan 17 Fri: I-R
[41 empty] | EE35 | EE35 | EE35 | EE35 | EE35
[41 empty] | EE36 | EE36 | EE36 | EE36 | EE36
| Cell 4 | CX - L1 | May 05 Mon: EE61; May 06 Tue: EE61; May 07 Wed: EE61; May 08 Thu: EE61; May 09 Fri: EE61; May 10 Sat: EE61; May 11 Sun: EE61; May 12 Mon: EE61; May 13 Tue: EE61; May 14 Wed: EE61; May 15 Thu: EE61; May 16 Fri: EE61
[157 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[164 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L2 | Jan 24 Fri: EE60; Jan 25 Sat: EE60; Jan 26 Sun: EE60; Jan 27 Mon: EE60; Jan 28 Tue: EE60; Jan 29 Wed: EE60; Jan 30 Thu: EE60; Feb 07 Fri: EE62; Feb 08 Sat: EE62; Feb 09 Sun: EE62; Feb 10 Mon: EE62; Feb 11 Tue: EE62; Feb 12 Wed: EE62; Feb 13 Thu: EE62; Feb 14 Fri: EE62; Feb 15 Sat: EE62; Feb 16 Sun: EE62; Feb 17 Mon: EE62; Feb 18 Tue: EE62; Feb 19 Wed: EE62; Feb 20 Thu: EE62; Feb 21 Fri: EE62; Feb 25 Tue: EE58; Feb 26 Wed: EE58; Feb 27 Thu: EE58; Feb 28 Fri: EE58; Mar 01 Sat: EE58; Mar 02 Sun: EE58; Mar 03 Mon: EE58; Mar 04 Tue: EE58; Mar 05 Wed: EE58; Mar 06 Thu: EE58; Mar 07 Fri: EE58
[55 empty] | EE61 | EE61 | EE61 | EE61 | EE61 | [20 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | [9 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
[57 empty] | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57
|  | CX - L3 | Jan 23 Thu: EE58; Jan 24 Fri: EE58; Jan 25 Sat: EE58; Jan 26 Sun: EE58; Jan 27 Mon: EE58; Jan 28 Tue: EE58; Jan 29 Wed: EE58; Jan 30 Thu: EE58; Jan 31 Fri: EE58; Feb 01 Sat: EE58; Feb 02 Sun: EE58; Feb 03 Mon: EE58; Feb 04 Tue: EE58; Feb 05 Wed: EE58; Feb 24 Mon: EE59; Feb 25 Tue: EE59; Feb 26 Wed: EE59; Feb 27 Thu: EE59; Feb 28 Fri: EE59; Mar 01 Sat: EE59; Mar 02 Sun: EE59; Mar 03 Mon: EE59; Mar 04 Tue: EE59; Mar 05 Wed: EE59; Mar 06 Thu: EE59; Mar 07 Fri: EE59; Mar 08 Sat: EE59; Mar 09 Sun: EE59; Mar 10 Mon: EE59; Mar 11 Tue: EE59; Mar 12 Wed: EE59; Mar 13 Thu: EE59; Mar 14 Fri: EE59
[55 empty] | EE57 | EE57 | EE57 | EE57 | EE57 |  |  | EE60 | EE60 | EE60 | EE60 | EE60 | [32 empty] | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[55 empty] | EE63 | EE63 | EE63 | EE63 | EE63
[57 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62
|  | Data Hall | Apr 08 Tue: W4; Apr 09 Wed: W4; Apr 10 Thu: W4; Apr 11 Fri: W4; Apr 12 Sat: W4; Apr 13 Sun: W4; Apr 14 Mon: W4; May 02 Fri: ET7; May 03 Sat: ET7; May 04 Sun: ET7; May 05 Mon: ET7; May 06 Tue: ET7; May 07 Wed: ET7; May 08 Thu: ET7; May 09 Fri: EE18; May 10 Sat: EE18; May 11 Sun: EE18; May 12 Mon: EE18; May 13 Tue: EE18; May 14 Wed: EE18; May 15 Thu: EE18
[157 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
|  | Electrical Room | Mar 25 Tue: EE27; Mar 26 Wed: EE27; Mar 27 Thu: EE27; Mar 28 Fri: EE27; Mar 29 Sat: EE27; Mar 30 Sun: EE27; Mar 31 Mon: EE27; Apr 01 Tue: EE17; Apr 02 Wed: EE17; Apr 03 Thu: EE17; Apr 04 Fri: EE17; Apr 05 Sat: EE17; Apr 06 Sun: EE17; Apr 07 Mon: EE17
[112 empty] | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
|  | Mech Gallery | Feb 11 Tue: I-R; Feb 17 Mon: ET22; Mar 18 Tue: EE35; Mar 19 Wed: EE35; Mar 20 Thu: EE35; Mar 21 Fri: EE35; Mar 22 Sat: EE35; Mar 23 Sun: EE35; Mar 24 Mon: EE35; Mar 25 Tue: EE36; Mar 26 Wed: EE36; Mar 27 Thu: EE36; Mar 28 Fri: EE36; Mar 29 Sat: EE36; Mar 30 Sun: EE36; Mar 31 Mon: EE36
CX Level 3 | COLO 2 | All | Apr 23 Wed: EE56; Apr 24 Thu: EE56; Apr 25 Fri: EE56; Apr 26 Sat: EE56; Apr 27 Sun: EE56; Apr 28 Mon: EE56; Apr 29 Tue: EE56
|  | Cell 1 | Jan 24 Fri: EE50; Jan 25 Sat: EE50; Jan 26 Sun: EE50; Jan 27 Mon: EE50; Jan 28 Tue: EE50; Jan 29 Wed: EE48; Jan 30 Thu: EE48; Jan 31 Fri: EE48; Feb 01 Sat: EE48; Feb 02 Sun: EE48; Feb 03 Mon: EE48; Feb 04 Tue: EE48; Feb 05 Wed: EE48; Feb 06 Thu: EE48; Feb 07 Fri: EE48; Feb 08 Sat: EE48; Feb 09 Sun: EE48; Feb 10 Mon: EE48; Feb 11 Tue: EE48; Feb 12 Wed: EE48; Feb 13 Thu: EE48; Feb 14 Fri: EE48; Feb 15 Sat: EE48; Feb 16 Sun: EE48; Feb 17 Mon: EE48; Feb 18 Tue: EE48; Mar 26 Wed: EE49; Mar 27 Thu: EE49; Mar 28 Fri: EE49; Mar 29 Sat: EE49; Mar 30 Sun: EE49; Mar 31 Mon: EE49; Apr 01 Tue: EE49
|  | Cell 2 | Feb 05 Wed: EE48; Feb 06 Thu: EE48; Feb 07 Fri: EE48; Feb 08 Sat: EE48; Feb 09 Sun: EE48; Feb 10 Mon: EE48; Feb 11 Tue: EE48; Feb 12 Wed: EE48; Feb 13 Thu: EE48; Feb 14 Fri: EE48; Feb 15 Sat: EE48; Feb 16 Sun: EE48; Feb 17 Mon: EE48; Feb 18 Tue: EE48; Apr 02 Wed: EE49; Apr 03 Thu: EE49; Apr 04 Fri: EE49; Apr 05 Sat: EE49; Apr 06 Sun: EE49; Apr 07 Mon: EE49; Apr 08 Tue: EE49
[66 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
|  | Cell 3 | Dec 19 Thu: EE50; Dec 20 Fri: EE50; Dec 21 Sat: EE50; Dec 22 Sun: EE50; Dec 23 Mon: EE50; Dec 24 Tue: EE50; Dec 25 Wed: EE50; Dec 26 Thu: EE50; Dec 27 Fri: EE50; Dec 28 Sat: EE50; Dec 29 Sun: EE50; Dec 30 Mon: EE50; Dec 31 Tue: EE50; Jan 01 Wed: EE50; Jan 02 Thu: EE50; Jan 03 Fri: EE50; Jan 04 Sat: EE50; Jan 05 Sun: EE50; Jan 06 Mon: EE50; Jan 07 Tue: EE50; Jan 08 Wed: EE50; Jan 09 Thu: EE50; Jan 10 Fri: EE50; Feb 28 Fri: EE48; Mar 01 Sat: EE48; Mar 02 Sun: EE48; Mar 03 Mon: EE48; Mar 04 Tue: EE48; Mar 05 Wed: EE48; Mar 06 Thu: EE48; Apr 09 Wed: EE49; Apr 10 Thu: EE49; Apr 11 Fri: EE49; Apr 12 Sat: EE49; Apr 13 Sun: EE49; Apr 14 Mon: EE49; Apr 15 Tue: EE49; Apr 16 Wed: EE49; Apr 17 Thu: EE49; Apr 18 Fri: EE49; Apr 19 Sat: EE49; Apr 20 Sun: EE49; Apr 21 Mon: EE49; Apr 22 Tue: EE49
|  | Cell 4 | Jan 10 Fri: EE50; Jan 11 Sat: EE50; Jan 12 Sun: EE50; Jan 13 Mon: EE50; Jan 14 Tue: EE50; Jan 15 Wed: EE50; Jan 16 Thu: EE50; Jan 28 Tue: EE49; Jan 29 Wed: EE49; Jan 30 Thu: EE49; Jan 31 Fri: EE49; Feb 01 Sat: EE49; Feb 02 Sun: EE49; Feb 03 Mon: EE49; Feb 04 Tue: EE49; Feb 05 Wed: EE49; Feb 06 Thu: EE49; Feb 07 Fri: EE49; Feb 19 Wed: EE48; Feb 20 Thu: EE48; Feb 21 Fri: EE48; Feb 22 Sat: EE48; Feb 23 Sun: EE48; Feb 24 Mon: EE48; Feb 25 Tue: EE48
| COLO 3 | All | Dec 27 Fri: EE54; Dec 28 Sat: EE54; Dec 29 Sun: EE54; Dec 30 Mon: EE54; Dec 31 Tue: EE54; Jan 01 Wed: EE54; Jan 02 Thu: EE54; Jan 03 Fri: EE54; Jan 13 Mon: EE56; Jan 14 Tue: EE56; Jan 15 Wed: EE56; Jan 16 Thu: EE56; Jan 17 Fri: EE56; Jan 18 Sat: EE56; Jan 19 Sun: EE56; Jan 20 Mon: EE56; Jan 21 Tue: EE56; Jan 22 Wed: EE56; Jan 23 Thu: EE56; Jan 24 Fri: EE56; Jan 25 Sat: EE56; Jan 26 Sun: EE56; Jan 27 Mon: EE56; Jan 28 Tue: EE56; Jan 29 Wed: EE56; Jan 30 Thu: EE56; Jan 31 Fri: EE56; Feb 21 Fri: EE55; Feb 22 Sat: EE55; Feb 23 Sun: EE55; Feb 24 Mon: EE55; Feb 25 Tue: EE55; Feb 26 Wed: EE55; Feb 27 Thu: EE55; Feb 28 Fri: EE55
|  | Cell 1 | Mar 05 Wed: EE50; Mar 06 Thu: EE50; Mar 07 Fri: EE50; Mar 08 Sat: EE50; Mar 09 Sun: EE50; Mar 10 Mon: EE50; Mar 11 Tue: EE50; Mar 12 Wed: EE48; Mar 13 Thu: EE48; Mar 14 Fri: EE48; Mar 15 Sat: EE48; Mar 16 Sun: EE48; Mar 17 Mon: EE48; Mar 18 Tue: EE48
[94 empty] | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49
|  | Cell 2 | Feb 03 Mon: EE49; Feb 04 Tue: EE49; Feb 05 Wed: EE49; Feb 06 Thu: EE49; Feb 07 Fri: EE49; Mar 12 Wed: EE50; Mar 13 Thu: EE50; Mar 14 Fri: EE50; Mar 15 Sat: EE50; Mar 16 Sun: EE50; Mar 17 Mon: EE50; Mar 18 Tue: EE50; Mar 19 Wed: EE48; Mar 20 Thu: EE48; Mar 21 Fri: EE48; Mar 22 Sat: EE48; Mar 23 Sun: EE48; Mar 24 Mon: EE48; Mar 25 Tue: EE48
|  | Cell 3 | Feb 12 Wed: EE49; Feb 13 Thu: EE49; Feb 14 Fri: EE49; Feb 15 Sat: EE49; Feb 16 Sun: EE49; Feb 17 Mon: EE49; Feb 18 Tue: EE49; Feb 19 Wed: EE49; Feb 20 Thu: EE49; Feb 21 Fri: EE49; Feb 22 Sat: EE49; Feb 23 Sun: EE49; Feb 24 Mon: EE49; Feb 25 Tue: EE49; Feb 26 Wed: EE49; Feb 27 Thu: EE49; Feb 28 Fri: EE49; Mar 01 Sat: EE49; Mar 02 Sun: EE49; Mar 03 Mon: EE49; Mar 04 Tue: EE49; Mar 12 Wed: EE50; Mar 13 Thu: EE50; Mar 14 Fri: EE50; Mar 15 Sat: EE50; Mar 16 Sun: EE50; Mar 17 Mon: EE50; Mar 18 Tue: EE50; Mar 19 Wed: EE48; Mar 20 Thu: EE48; Mar 21 Fri: EE48; Mar 22 Sat: EE48; Mar 23 Sun: EE48; Mar 24 Mon: EE48; Mar 25 Tue: EE48
|  | Cell 4 | Feb 19 Wed: EE49; Feb 20 Thu: EE49; Feb 21 Fri: EE49; Feb 22 Sat: EE49; Feb 23 Sun: EE49; Feb 24 Mon: EE49; Feb 25 Tue: EE49; Feb 26 Wed: EE49; Feb 27 Thu: EE49; Feb 28 Fri: EE49; Mar 01 Sat: EE49; Mar 02 Sun: EE49; Mar 03 Mon: EE49; Mar 04 Tue: EE49; Mar 19 Wed: EE50; Mar 20 Thu: EE50; Mar 21 Fri: EE50; Mar 22 Sat: EE50; Mar 23 Sun: EE50; Mar 24 Mon: EE50; Mar 25 Tue: EE50
[106 empty] | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48
| COLO 4 | All | Mar 26 Wed: EE56; Mar 27 Thu: EE56; Mar 28 Fri: EE56; Mar 29 Sat: EE56; Mar 30 Sun: EE56; Mar 31 Mon: EE56; Apr 01 Tue: EE56
|  | Cell 1 | Mar 26 Wed: EE49; Mar 27 Thu: EE49; Mar 28 Fri: EE49; Mar 29 Sat: EE49; Mar 30 Sun: EE49; Mar 31 Mon: EE49; Apr 01 Tue: EE49; Apr 23 Wed: EE50; Apr 24 Thu: EE50; Apr 25 Fri: EE50; Apr 26 Sat: EE50; Apr 27 Sun: EE50; Apr 28 Mon: EE50; Apr 29 Tue: EE50; Jun 04 Wed: EE48; Jun 05 Thu: EE48
|  | Cell 2 | Jan 13 Mon: EE48; Jan 14 Tue: EE48; Jan 15 Wed: EE48; Jan 16 Thu: EE48; Jan 17 Fri: EE48; Apr 02 Wed: EE49; Apr 03 Thu: EE49; Apr 04 Fri: EE49; Apr 05 Sat: EE49; Apr 06 Sun: EE49; Apr 07 Mon: EE49; Apr 08 Tue: EE49; Apr 30 Wed: EE50; May 01 Thu: EE50; May 02 Fri: EE50; May 03 Sat: EE50; May 04 Sun: EE50; May 05 Mon: EE50; May 06 Tue: EE50; May 07 Wed: EE50; May 08 Thu: EE50; May 09 Fri: EE50; May 10 Sat: EE50; May 11 Sun: EE50; May 12 Mon: EE50; May 13 Tue: EE50; May 14 Wed: EE50; May 15 Thu: EE50; May 16 Fri: EE50; May 17 Sat: EE50; May 18 Sun: EE50; May 19 Mon: EE50; May 20 Tue: EE50; May 21 Wed: EE50; May 22 Thu: EE50; May 23 Fri: EE50; May 24 Sat: EE50; May 25 Sun: EE50; May 26 Mon: EE50; May 27 Tue: EE50; May 28 Wed: EE50; May 29 Thu: EE50; May 30 Fri: EE50; May 31 Sat: EE50; Jun 01 Sun: EE50; Jun 02 Mon: EE50; Jun 03 Tue: EE50
|  | Cell 3 | Jan 27 Mon: EE48; Jan 28 Tue: EE48; Jan 29 Wed: EE48; Jan 30 Thu: EE48; Jan 31 Fri: EE48; Feb 01 Sat: EE48; Feb 02 Sun: EE48; Feb 03 Mon: EE48; Feb 04 Tue: EE48; Feb 05 Wed: EE48; Feb 06 Thu: EE48; Feb 07 Fri: EE48; Feb 08 Sat: EE48; Feb 09 Sun: EE48; Feb 10 Mon: EE48; Feb 11 Tue: EE48; Feb 12 Wed: EE48; Feb 13 Thu: EE48; Feb 14 Fri: EE48; Apr 09 Wed: EE49; Apr 10 Thu: EE49; Apr 11 Fri: EE49; Apr 12 Sat: EE49; Apr 13 Sun: EE49; Apr 14 Mon: EE49; Apr 15 Tue: EE49
[64 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
|  | Cell 4 | Dec 24 Tue: EE50; Dec 25 Wed: EE50; Dec 26 Thu: EE50; Dec 27 Fri: EE50; Dec 28 Sat: EE50; Dec 29 Sun: EE50; Dec 30 Mon: EE50; Dec 31 Tue: EE50; Jan 01 Wed: EE50; Jan 02 Thu: EE50; Jan 03 Fri: EE50; Jan 04 Sat: EE50; Jan 05 Sun: EE50; Jan 06 Mon: EE50; Jan 07 Tue: EE50; Jan 08 Wed: EE50; Jan 09 Thu: EE50; Jan 10 Fri: EE50; Jan 11 Sat: EE50; Jan 12 Sun: EE50; Jan 13 Mon: EE50; Jan 14 Tue: EE50; Jan 15 Wed: EE50; Feb 17 Mon: EE48; Feb 18 Tue: EE48; Feb 19 Wed: EE48; Feb 20 Thu: EE48; Feb 21 Fri: EE48; Apr 09 Wed: EE49; Apr 10 Thu: EE49; Apr 11 Fri: EE49; Apr 12 Sat: EE49; Apr 13 Sun: EE49; Apr 14 Mon: EE49; Apr 15 Tue: EE49; Apr 16 Wed: EE49; Apr 17 Thu: EE49; Apr 18 Fri: EE49; Apr 19 Sat: EE49; Apr 20 Sun: EE49; Apr 21 Mon: EE49; Apr 22 Tue: EE49
| COLO 5 | All | Feb 19 Wed: EE52; Feb 20 Thu: EE52; Feb 21 Fri: EE52; Feb 22 Sat: EE52; Feb 23 Sun: EE52; Feb 24 Mon: EE52; Feb 25 Tue: EE52; Feb 26 Wed: EE53; Feb 27 Thu: EE53; Feb 28 Fri: EE53; Mar 01 Sat: EE53; Mar 02 Sun: EE53; Mar 03 Mon: EE53; Mar 04 Tue: EE53
[85 empty] | EE51 | EE51 | EE51 | EE51 | EE51 | EE51 | EE51
|  | Cell 1 | Mar 05 Wed: EE49; Mar 06 Thu: EE49; Mar 07 Fri: EE49; Mar 08 Sat: EE49; Mar 09 Sun: EE49; Mar 10 Mon: EE49; Mar 11 Tue: EE49; Mar 26 Wed: EE50; Mar 27 Thu: EE50; Mar 28 Fri: EE50; Mar 29 Sat: EE50; Mar 30 Sun: EE50; Mar 31 Mon: EE50; Apr 01 Tue: EE50; Apr 02 Wed: EE48; Apr 03 Thu: EE48; Apr 04 Fri: EE48; Apr 05 Sat: EE48; Apr 06 Sun: EE48; Apr 07 Mon: EE48; Apr 08 Tue: EE48
|  | Cell 2 | Jan 24 Fri: EE48; Jan 25 Sat: EE48; Jan 26 Sun: EE48; Jan 27 Mon: EE48; Jan 28 Tue: EE48; Jan 29 Wed: EE48; Jan 30 Thu: EE48; Jan 31 Fri: EE48; Feb 01 Sat: EE48; Feb 02 Sun: EE48; Feb 03 Mon: EE48; Feb 04 Tue: EE48; Feb 05 Wed: EE48; Feb 06 Thu: EE48; Feb 07 Fri: EE48; Mar 05 Wed: EE49; Mar 06 Thu: EE49; Mar 07 Fri: EE49; Mar 08 Sat: EE49; Mar 09 Sun: EE49; Mar 10 Mon: EE49; Mar 11 Tue: EE49; Mar 26 Wed: EE50; Mar 27 Thu: EE50; Mar 28 Fri: EE50; Mar 29 Sat: EE50; Mar 30 Sun: EE50; Mar 31 Mon: EE50; Apr 01 Tue: EE50
|  | Cell 3 | Feb 07 Fri: EE48; Feb 08 Sat: EE48; Feb 09 Sun: EE48; Feb 10 Mon: EE48; Feb 11 Tue: EE48; Mar 19 Wed: EE49; Mar 20 Thu: EE49; Mar 21 Fri: EE49; Mar 22 Sat: EE49; Mar 23 Sun: EE49; Mar 24 Mon: EE49; Mar 25 Tue: EE49; Apr 09 Wed: EE50; Apr 10 Thu: EE50; Apr 11 Fri: EE50; Apr 12 Sat: EE50; Apr 13 Sun: EE50; Apr 14 Mon: EE50; Apr 15 Tue: EE50; Apr 16 Wed: EE50; Apr 17 Thu: EE50; Apr 18 Fri: EE50; Apr 19 Sat: EE50; Apr 20 Sun: EE50; Apr 21 Mon: EE50; Apr 22 Tue: EE50
|  | Cell 4 | Feb 11 Tue: EE48; Feb 12 Wed: EE48; Feb 13 Thu: EE48; Feb 14 Fri: EE48; Feb 15 Sat: EE48; Feb 16 Sun: EE48; Feb 17 Mon: EE48; Feb 18 Tue: EE48; Feb 19 Wed: EE48; Feb 20 Thu: EE48; Feb 21 Fri: EE48; Mar 26 Wed: EE49; Mar 27 Thu: EE49; Mar 28 Fri: EE49; Mar 29 Sat: EE49; Mar 30 Sun: EE49; Mar 31 Mon: EE49; Apr 01 Tue: EE49; Apr 23 Wed: EE50; Apr 24 Thu: EE50; Apr 25 Fri: EE50; Apr 26 Sat: EE50; Apr 27 Sun: EE50; Apr 28 Mon: EE50; Apr 29 Tue: EE50
| Site | Site | Mar 26 Wed: EE47; Mar 27 Thu: EE47; Mar 28 Fri: EE47; Mar 29 Sat: EE47; Mar 30 Sun: EE47; Mar 31 Mon: EE47; Apr 01 Tue: EE47
Yardwork | COLO 2 | North | Jan 10 Fri: RC1; Jan 11 Sat: RC1; Jan 12 Sun: RC1; Jan 13 Mon: RC1; Jan 14 Tue: RC1; Jan 15 Wed: RC1; Jan 16 Thu: RC1; Jan 17 Fri: RC1; Jan 18 Sat: RC1; Jan 19 Sun: RC1; Jan 20 Mon: RC1; Jan 21 Tue: RC1; Jan 22 Wed: RC1; Jan 23 Thu: RC1; Jan 24 Fri: RC1; Jan 25 Sat: RC1; Jan 26 Sun: RC1; Jan 27 Mon: RC1; Jan 28 Tue: RC1; Jan 29 Wed: RC1; Jan 30 Thu: RC1
|  | South | Dec 17 Tue: EE35; Dec 18 Wed: EE35; Dec 19 Thu: EE35; Dec 20 Fri: EE35; Dec 21 Sat: EE35; Dec 22 Sun: EE35; Dec 23 Mon: EE35; Dec 24 Tue: EE35; Dec 25 Wed: EE35; Dec 26 Thu: EE35; Dec 27 Fri: EE35; Dec 28 Sat: EE35; Dec 29 Sun: EE35; Dec 30 Mon: EE35; Dec 31 Tue: EE35; Jan 01 Wed: EE35; Jan 02 Thu: EE35; Jan 03 Fri: EE35; Jan 04 Sat: EE35; Jan 05 Sun: EE35; Jan 06 Mon: EE35; Jan 07 Tue: EE35; Jan 08 Wed: EE35; Jan 10 Fri: RC1; Jan 11 Sat: RC1; Jan 12 Sun: RC1; Jan 13 Mon: RC1; Jan 14 Tue: RC1; Jan 15 Wed: RC1; Jan 16 Thu: RC1
| COLO 3 | North | Jan 22 Wed: EE35; Jan 23 Thu: EE35; Jan 24 Fri: EE35; Jan 25 Sat: EE35; Jan 26 Sun: EE35; Jan 27 Mon: EE35; Jan 28 Tue: EE35; Jan 31 Fri: EE46; Feb 01 Sat: EE46; Feb 02 Sun: EE46; Feb 03 Mon: EE46; Feb 04 Tue: EE46; Feb 05 Wed: EE46; Feb 06 Thu: EE46
[59 empty] | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1
|  | South | Jan 22 Wed: EE46; Jan 23 Thu: EE46; Jan 24 Fri: EE46; Jan 25 Sat: EE46; Jan 26 Sun: EE46; Jan 27 Mon: EE46; Jan 28 Tue: EE46
[50 empty] | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1
| COLO 4 | North | Mar 26 Wed: EE35; Mar 27 Thu: EE35; Mar 28 Fri: EE35; Mar 29 Sat: EE35; Mar 30 Sun: EE35; Mar 31 Mon: EE35; Apr 01 Tue: EE35; Apr 02 Wed: RC1; Apr 03 Thu: RC1; Apr 04 Fri: RC1; Apr 05 Sat: RC1; Apr 06 Sun: RC1; Apr 07 Mon: RC1; Apr 08 Tue: RC1
[113 empty] | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46
|  | South | Jan 31 Fri: EE46; Feb 01 Sat: EE46; Feb 02 Sun: EE46; Feb 03 Mon: EE46; Feb 04 Tue: EE46; Feb 05 Wed: EE46; Feb 06 Thu: EE46; Mar 19 Wed: EE46; Mar 20 Thu: EE46; Mar 21 Fri: EE46; Mar 22 Sat: EE46; Mar 23 Sun: EE46; Mar 24 Mon: EE46; Mar 25 Tue: EE46; Mar 26 Wed: RC1; Mar 27 Thu: RC1; Mar 28 Fri: RC1; Mar 29 Sat: RC1; Mar 30 Sun: RC1; Mar 31 Mon: RC1; Apr 01 Tue: RC1
| COLO 5 | East | Jan 17 Fri: RC1; Jan 18 Sat: RC1; Jan 19 Sun: RC1; Jan 20 Mon: RC1; Jan 21 Tue: RC1; Jan 22 Wed: RC1; Jan 23 Thu: RC1; Jan 24 Fri: RC1; Jan 25 Sat: RC1; Jan 26 Sun: RC1; Jan 27 Mon: RC1; Jan 28 Tue: RC1; Jan 29 Wed: RC1; Jan 30 Thu: RC1; Jan 31 Fri: RC1; Feb 01 Sat: RC1; Feb 02 Sun: RC1; Feb 03 Mon: RC1; Feb 04 Tue: RC1; Feb 05 Wed: RC1; Feb 06 Thu: RC1
|  | West | Feb 07 Fri: EE34; Feb 08 Sat: EE34; Feb 09 Sun: EE34; Feb 10 Mon: EE34; Feb 11 Tue: EE34; Feb 12 Wed: EE34; Feb 13 Thu: EE34
[72 empty] | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1
CX Level 2 | COLO 2 | COLO 2 | Jan 14 Tue: EE49; Jan 15 Wed: EE49; Jan 16 Thu: EE49; Jan 17 Fri: EE49; Jan 18 Sat: EE49; Jan 19 Sun: EE49; Jan 20 Mon: EE49; Jan 21 Tue: EE49; Jan 22 Wed: EE49; Jan 23 Thu: EE49; Jan 24 Fri: EE49; Apr 23 Wed: EE48; Apr 24 Thu: EE48; Apr 25 Fri: EE48; Apr 26 Sat: EE48; Apr 27 Sun: EE48; Apr 28 Mon: EE48; Apr 29 Tue: EE48
[52 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
| COLO 3 | COLO 3 | Feb 20 Thu: EE54; Feb 21 Fri: EE54; Feb 22 Sat: EE54; Feb 23 Sun: EE54; Feb 24 Mon: EE54; Feb 25 Tue: EE54; Feb 26 Wed: EE54; Feb 27 Thu: EE49; Feb 28 Fri: EE49; Mar 01 Sat: EE49; Mar 02 Sun: EE49; Mar 03 Mon: EE49; Mar 04 Tue: EE49; Mar 05 Wed: EE49; Mar 06 Thu: EE50; Mar 07 Fri: EE50; Mar 08 Sat: EE50; Mar 09 Sun: EE50; Mar 10 Mon: EE50; Mar 11 Tue: EE50; Mar 12 Wed: EE50
[79 empty] | EE55 | EE55 | EE55 | EE55 | EE55 | EE55 | EE55
[79 empty] | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48
| COLO 4 | COLO 4 | Feb 27 Thu: EE48; Feb 28 Fri: EE48; Mar 01 Sat: EE48; Mar 02 Sun: EE48; Mar 03 Mon: EE48; Mar 04 Tue: EE48; Mar 05 Wed: EE48; Mar 19 Wed: EE49; Mar 20 Thu: EE49; Mar 21 Fri: EE49; Mar 22 Sat: EE49; Mar 23 Sun: EE49; Mar 24 Mon: EE49; Mar 25 Tue: EE49; Mar 26 Wed: EE50; Mar 27 Thu: EE50; Mar 28 Fri: EE50; Mar 29 Sat: EE50; Mar 30 Sun: EE50; Mar 31 Mon: EE50; Apr 01 Tue: EE50
| COLO 5 | COLO 5 | Jan 09 Thu: EE51; Jan 10 Fri: EE51; Jan 11 Sat: EE51; Jan 12 Sun: EE51; Jan 13 Mon: EE51; Jan 14 Tue: EE51; Jan 15 Wed: EE51; Jan 16 Thu: EE51; Jan 17 Fri: EE51; Jan 18 Sat: EE51; Jan 19 Sun: EE51; Jan 20 Mon: EE51; Jan 21 Tue: EE51; Jan 22 Wed: EE51; Jan 23 Thu: EE51; Jan 24 Fri: EE51; Jan 25 Sat: EE51; Jan 26 Sun: EE51; Jan 27 Mon: EE51; Jan 28 Tue: EE51; Jan 29 Wed: EE51; Jan 30 Thu: EE52; Jan 31 Fri: EE52; Feb 01 Sat: EE52; Feb 02 Sun: EE52; Feb 03 Mon: EE52; Feb 04 Tue: EE52; Feb 05 Wed: EE52; Feb 13 Thu: EE50; Feb 14 Fri: EE50; Feb 15 Sat: EE50; Feb 16 Sun: EE50; Feb 17 Mon: EE50; Feb 18 Tue: EE50; Feb 19 Wed: EE50; Feb 21 Fri: EE49; Feb 22 Sat: EE49; Feb 23 Sun: EE49; Feb 24 Mon: EE49; Feb 25 Tue: EE49; Feb 26 Wed: EE49; Feb 27 Thu: EE49
[45 empty] | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48
| Site | Site | Apr 09 Wed: EE47; Apr 10 Thu: EE47; Apr 11 Fri: EE47; Apr 12 Sat: EE47; Apr 13 Sun: EE47; Apr 14 Mon: EE47; Apr 15 Tue: EE47; Apr 16 Wed: EE47; Apr 17 Thu: EE47; Apr 18 Fri: EE47; Apr 19 Sat: EE47; Apr 20 Sun: EE47; Apr 21 Mon: EE47; Apr 22 Tue: EE47
COLO 2 | All | CX - Microsoft | Apr 04 Fri: MS2; Apr 05 Sat: MS2; Apr 06 Sun: MS2; Apr 07 Mon: MS2; Apr 08 Tue: MS2; Apr 09 Wed: MS2; Apr 10 Thu: MS2; Apr 11 Fri: MS2; Apr 12 Sat: MS2; Apr 13 Sun: MS2; Apr 14 Mon: MS2; Apr 15 Tue: MS2; Apr 16 Wed: MS2; Apr 17 Thu: MS2
[129 empty] | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1
| Cell 1 | CX - L2 | Mar 18 Tue: EE57; Mar 19 Wed: EE57; Mar 20 Thu: EE57; Mar 21 Fri: EE57; Mar 22 Sat: EE57; Mar 23 Sun: EE57; Mar 24 Mon: EE57; Mar 25 Tue: EE59; Mar 26 Wed: EE59; Mar 27 Thu: EE59; Mar 28 Fri: EE59; Mar 29 Sat: EE59; Mar 30 Sun: EE59; Mar 31 Mon: EE59; Apr 01 Tue: EE61; Apr 02 Wed: EE61; Apr 03 Thu: EE61; Apr 04 Fri: EE61; Apr 05 Sat: EE61; Apr 06 Sun: EE61; Apr 07 Mon: EE61
[105 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[112 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62
|  | CX - L3 | Jan 16 Thu: EE60; Jan 17 Fri: EE60; Jan 18 Sat: EE60; Jan 19 Sun: EE60; Jan 20 Mon: EE60; Jan 21 Tue: EE60; Jan 22 Wed: EE60; Jan 23 Thu: EE60; Jan 24 Fri: EE60; Jan 25 Sat: EE60; Jan 26 Sun: EE60; Jan 27 Mon: EE60; Jan 28 Tue: EE60; Jan 29 Wed: EE60; Jan 30 Thu: EE60; Jan 31 Fri: EE60; Feb 01 Sat: EE60; Feb 02 Sun: EE60; Feb 03 Mon: EE60; Feb 04 Tue: EE60; Feb 05 Wed: EE60; Feb 12 Wed: EE58; Feb 13 Thu: EE58; Feb 14 Fri: EE58; Feb 15 Sat: EE58; Feb 16 Sun: EE58; Feb 17 Mon: EE58; Feb 18 Tue: EE58; Feb 24 Mon: EE59; Feb 25 Tue: EE59; Feb 26 Wed: EE59; Feb 27 Thu: EE59; Feb 28 Fri: EE59; Mar 27 Thu: EE57; Mar 28 Fri: EE57; Mar 29 Sat: EE57; Mar 30 Sun: EE57; Mar 31 Mon: EE57; Apr 01 Tue: EE57; Apr 02 Wed: EE57; Apr 03 Thu: EE57; Apr 04 Fri: EE57; Apr 05 Sat: EE57; Apr 06 Sun: EE57; Apr 07 Mon: EE57; Apr 08 Tue: EE57; Apr 09 Wed: EE57
[59 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | [55 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62
[62 empty] | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
|  | Data Hall | Mar 11 Tue: EE17; Mar 12 Wed: EE17; Mar 13 Thu: EE17; Mar 14 Fri: EE17; Mar 15 Sat: EE17; Mar 16 Sun: EE17; Mar 17 Mon: EE17; Mar 18 Tue: EE18; Mar 19 Wed: EE18; Mar 20 Thu: EE18; Mar 21 Fri: EE18; Mar 22 Sat: EE18; Mar 23 Sun: EE18; Mar 24 Mon: EE18
[105 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
|  | Electrical Room | Mar 04 Tue: EE29; Mar 05 Wed: EE29; Mar 06 Thu: EE29; Mar 07 Fri: EE29; Mar 08 Sat: EE29; Mar 09 Sun: EE29; Mar 10 Mon: EE29; Mar 11 Tue: ALL3; Mar 12 Wed: ALL3; Mar 13 Thu: ALL3; Mar 14 Fri: ALL3; Mar 15 Sat: ALL3; Mar 16 Sun: ALL3; Mar 17 Mon: ALL3
| Cell 2 | CX - L2 | Mar 18 Tue: EE57; Mar 19 Wed: EE57; Mar 20 Thu: EE57; Mar 21 Fri: EE57; Mar 22 Sat: EE57; Mar 23 Sun: EE57; Mar 24 Mon: EE57; Mar 28 Fri: EE58; Mar 29 Sat: EE58; Mar 30 Sun: EE58; Mar 31 Mon: EE58; Apr 01 Tue: EE58; Apr 02 Wed: EE58; Apr 03 Thu: EE58; Apr 04 Fri: EE61; Apr 05 Sat: EE61; Apr 06 Sun: EE61; Apr 07 Mon: EE61; Apr 08 Tue: EE61; Apr 09 Wed: EE61; Apr 10 Thu: EE61
[105 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 |  |  |  | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
[105 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 |  |  |  | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | CX - L3 | Jan 02 Thu: EE61; Jan 03 Fri: EE61; Jan 04 Sat: EE61; Jan 05 Sun: EE61; Jan 06 Mon: EE61; Jan 07 Tue: EE61; Jan 08 Wed: EE61; Feb 12 Wed: EE58; Feb 13 Thu: EE58; Feb 14 Fri: EE60; Feb 15 Sat: EE60; Feb 16 Sun: EE60; Feb 17 Mon: EE60; Feb 18 Tue: EE60; Feb 19 Wed: EE60; Feb 20 Thu: EE60; Feb 21 Fri: EE60; Feb 22 Sat: EE60; Feb 23 Sun: EE60; Feb 24 Mon: EE60; Feb 25 Tue: EE60; Feb 26 Wed: EE59; Feb 27 Thu: EE59; Feb 28 Fri: EE59; Mar 01 Sat: EE59; Mar 02 Sun: EE59; Mar 03 Mon: EE59; Mar 04 Tue: EE59; Apr 04 Fri: EE57; Apr 05 Sat: EE57; Apr 06 Sun: EE57; Apr 07 Mon: EE57; Apr 08 Tue: EE57; Apr 09 Wed: EE57; Apr 10 Thu: EE57; Apr 11 Fri: EE62; Apr 12 Sat: EE62; Apr 13 Sun: EE62; Apr 14 Mon: EE62; Apr 15 Tue: EE62; Apr 16 Wed: EE62; Apr 17 Thu: EE62; Apr 18 Fri: EE62; Apr 19 Sat: EE62; Apr 20 Sun: EE62; Apr 21 Mon: EE62; Apr 22 Tue: EE62; Apr 23 Wed: EE62; Apr 24 Thu: EE62
[141 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
|  | Data Hall | Mar 11 Tue: EE17; Mar 12 Wed: EE17; Mar 13 Thu: EE17; Mar 14 Fri: EE17; Mar 15 Sat: EE17; Mar 16 Sun: EE17; Mar 17 Mon: EE17
[98 empty] | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
[98 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
|  | Electrical Room | Mar 04 Tue: ALL3; Mar 05 Wed: ALL3; Mar 06 Thu: ALL3; Mar 07 Fri: ALL3; Mar 08 Sat: ALL3; Mar 09 Sun: ALL3; Mar 10 Mon: ALL3; Mar 17 Mon: EE29; Mar 18 Tue: EE29; Mar 19 Wed: EE29; Mar 20 Thu: EE29; Mar 21 Fri: EE29
|  | Mech Gallery | Feb 10 Mon: EE35; Feb 11 Tue: EE35; Feb 12 Wed: EE35; Feb 13 Thu: EE35; Feb 14 Fri: EE35; Feb 15 Sat: EE35; Feb 16 Sun: EE35; Feb 17 Mon: EE35; Feb 18 Tue: EE35; Feb 19 Wed: EE35; Feb 20 Thu: EE35; Feb 21 Fri: EE35; Feb 24 Mon: EE36; Feb 25 Tue: EE36; Feb 26 Wed: EE36; Feb 27 Thu: EE36; Feb 28 Fri: EE36; Mar 01 Sat: EE36; Mar 02 Sun: EE36; Mar 03 Mon: EE36; Mar 04 Tue: EE36; Mar 05 Wed: EE36; Mar 06 Thu: EE36; Mar 07 Fri: EE36; Mar 08 Sat: EE36; Mar 09 Sun: EE36; Mar 10 Mon: EE36; Mar 11 Tue: EE36; Mar 12 Wed: EE36; Mar 13 Thu: EE36; Mar 14 Fri: EE36
| Cell 3 | CX - L2 | Mar 17 Mon: EE57; Mar 18 Tue: EE57; Mar 19 Wed: EE57; Mar 20 Thu: EE57; Mar 21 Fri: EE57; Mar 24 Mon: EE62; Mar 25 Tue: EE62; Mar 26 Wed: EE62; Mar 27 Thu: EE62; Mar 28 Fri: EE62
[111 empty] | EE63 | EE63 | EE63 | EE63 | EE63
[111 empty] | EE58 | EE58 | EE58 | EE58 | EE58
[115 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
[115 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
[115 empty] | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
|  | CX - L3 | Feb 12 Wed: EE60; Feb 13 Thu: EE60; Feb 14 Fri: EE60; Feb 15 Sat: EE60; Feb 16 Sun: EE60; Feb 17 Mon: EE60; Feb 18 Tue: EE60; Feb 19 Wed: EE60; Feb 20 Thu: EE60; Feb 21 Fri: EE60; Feb 22 Sat: EE60; Feb 23 Sun: EE60; Feb 24 Mon: EE60; Feb 25 Tue: EE60; Feb 26 Wed: EE59; Feb 27 Thu: EE59; Feb 28 Fri: EE61; Mar 01 Sat: EE61; Mar 02 Sun: EE61; Mar 03 Mon: EE61; Mar 04 Tue: EE61; Mar 05 Wed: EE61; Mar 06 Thu: EE61; Mar 07 Fri: EE61; Mar 08 Sat: EE61; Mar 09 Sun: EE61; Mar 10 Mon: EE61; Mar 11 Tue: EE61; Apr 04 Fri: EE57; Apr 05 Sat: EE57; Apr 06 Sun: EE57; Apr 07 Mon: EE57; Apr 08 Tue: EE57; Apr 09 Wed: EE57; Apr 10 Thu: EE57; Apr 16 Wed: EE58; Apr 17 Thu: EE58; Apr 18 Fri: EE58; Apr 19 Sat: EE58; Apr 20 Sun: EE58; Apr 21 Mon: EE58; Apr 22 Tue: EE58
[122 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62
[122 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
|  | Data Hall | Mar 10 Mon: EE18; Mar 11 Tue: EE18; Mar 12 Wed: EE18; Mar 13 Thu: EE18; Mar 14 Fri: EE18; Mar 17 Mon: ET7; Mar 18 Tue: ET7; Mar 19 Wed: ET7; Mar 20 Thu: ET7; Mar 21 Fri: ET7
[104 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
|  | Electrical Room | Feb 24 Mon: EE29; Feb 25 Tue: EE29; Feb 26 Wed: EE29; Feb 27 Thu: EE29; Feb 28 Fri: EE29; Mar 01 Sat: EE29; Mar 02 Sun: EE29; Mar 03 Mon: EE29; Mar 04 Tue: EE29; Mar 05 Wed: EE29; Mar 06 Thu: EE29; Mar 07 Fri: EE29; Mar 08 Sat: EE29; Mar 09 Sun: EE29; Mar 10 Mon: EE29; Mar 11 Tue: EE29; Mar 12 Wed: EE29; Mar 13 Thu: EE29; Mar 14 Fri: EE29; Mar 31 Mon: ALL3; Apr 01 Tue: ALL3; Apr 02 Wed: ALL3; Apr 03 Thu: ALL3; Apr 04 Fri: ALL3
|  | Mech Gallery | Feb 06 Thu: I-R; Feb 07 Fri: I-R; Feb 08 Sat: I-R; Feb 09 Sun: I-R; Feb 10 Mon: I-R; Feb 11 Tue: I-R; Feb 12 Wed: I-R; Feb 13 Thu: I-R; Feb 14 Fri: I-R; Feb 15 Sat: I-R; Feb 16 Sun: I-R; Feb 17 Mon: I-R; Feb 18 Tue: I-R; Feb 19 Wed: I-R; Feb 20 Thu: I-R; Feb 21 Fri: I-R; Feb 22 Sat: I-R; Feb 23 Sun: I-R; Feb 24 Mon: I-R; Feb 25 Tue: I-R; Feb 26 Wed: I-R; Mar 24 Mon: EE35; Mar 25 Tue: EE35; Mar 26 Wed: EE35; Mar 27 Thu: EE35; Mar 28 Fri: EE35
[76 empty] | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36
| Cell 4 | CX - L2 | Jan 14 Tue: EE57; Mar 20 Thu: EE58; Mar 21 Fri: EE58; Mar 22 Sat: EE58; Mar 23 Sun: EE58; Mar 24 Mon: EE58; Mar 25 Tue: EE58; Mar 26 Wed: EE58; Mar 27 Thu: EE60; Mar 28 Fri: EE60; Mar 29 Sat: EE60; Mar 30 Sun: EE60; Mar 31 Mon: EE60; Apr 01 Tue: EE60; Apr 02 Wed: EE60
[42 empty] | EE62 | [68 empty] | EE61 | EE61 | EE61 | EE61 | EE61 |  |  | EE59 | EE59 | EE59 | EE59 | EE59
EE63
|  | CX - L3 | Mar 24 Mon: EE57; Mar 25 Tue: EE57; Mar 26 Wed: EE57; Mar 27 Thu: EE57; Mar 28 Fri: EE57; Apr 03 Thu: EE63; Apr 04 Fri: EE63; Apr 05 Sat: EE63; Apr 06 Sun: EE63; Apr 07 Mon: EE63; Apr 08 Tue: EE63; Apr 09 Wed: EE63; Apr 11 Fri: EE61; Apr 12 Sat: EE61; Apr 13 Sun: EE61; Apr 14 Mon: EE61; Apr 15 Tue: EE61; Apr 16 Wed: EE61; Apr 17 Thu: EE61
[111 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | [6 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
[115 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 |  |  |  | EE60 | EE60 | EE60 | EE60 | EE60
|  | Data Hall | Mar 03 Mon: ALL3; Mar 17 Mon: EE18; Mar 18 Tue: EE18; Mar 19 Wed: EE18; Mar 20 Thu: EE18; Mar 21 Fri: EE18; Mar 22 Sat: EE18; Mar 23 Sun: EE18; Mar 24 Mon: EE18; Mar 25 Tue: EE18; Mar 26 Wed: EE18; Mar 27 Thu: EE18; Mar 28 Fri: EE18; Mar 29 Sat: EE18; Mar 30 Sun: EE18; Mar 31 Mon: EE18; Apr 01 Tue: EE18; Apr 02 Wed: EE18; Apr 03 Thu: EE18; Apr 04 Fri: EE18; Apr 14 Mon: ET7; Apr 15 Tue: ET7; Apr 16 Wed: ET7; Apr 17 Thu: ET7; Apr 18 Fri: ET7
|  | Electrical Room | Mar 03 Mon: EE29; Mar 04 Tue: EE29; Mar 05 Wed: EE29; Mar 06 Thu: EE29; Mar 07 Fri: EE29; Mar 08 Sat: EE29; Mar 09 Sun: EE29; Mar 10 Mon: EE29; Mar 11 Tue: EE29; Mar 12 Wed: EE29; Mar 13 Thu: EE29; Mar 14 Fri: EE29; Mar 15 Sat: EE29; Mar 16 Sun: EE29; Mar 17 Mon: EE29; Mar 18 Tue: EE29; Mar 19 Wed: EE29; Mar 20 Thu: EE29; Mar 21 Fri: EE29; Apr 07 Mon: EE28; Apr 08 Tue: EE28; Apr 09 Wed: EE28; Apr 10 Thu: EE28; Apr 11 Fri: EE28
[97 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
|  | Mech Gallery | Jan 07 Tue: I-R; Jan 08 Wed: I-R; Jan 09 Thu: I-R; Jan 10 Fri: I-R; Jan 11 Sat: I-R; Jan 12 Sun: I-R; Jan 13 Mon: I-R; Feb 27 Thu: EE36; Feb 28 Fri: EE36; Mar 01 Sat: EE36; Mar 02 Sun: EE36; Mar 03 Mon: EE36; Mar 04 Tue: EE36; Mar 05 Wed: EE36; Mar 06 Thu: EE36; Mar 07 Fri: EE36; Mar 08 Sat: EE36; Mar 09 Sun: EE36; Mar 10 Mon: EE36; Mar 11 Tue: EE36; Mar 12 Wed: EE36; Mar 13 Thu: EE36; Mar 14 Fri: EE36; Mar 15 Sat: EE36; Mar 16 Sun: EE36; Mar 17 Mon: EE36; Mar 18 Tue: EE36; Mar 19 Wed: EE36
[37 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | [55 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22
Note on EK5: Activity Name: Level 4 Cx - Colo 3 Phase: COLO 3 Location: All Trade: None Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on EN6: Activity Name: Level 5 Cx / IST - Colo 3 Phase: COLO 3 Location: All Trade: None Start Date: 25-Apr-2025 End Date: 01-May-2025
Note on DH7: Activity Name: Interior - L1 PDUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DH8: Activity Name: Interior - L1 UPS - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DH9: Activity Name: Interior - L2 TCP/MSB - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DO9: Activity Name: Interior - L2 UPS - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on DV9: Activity Name: Interior - L2 ADP - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on EU9: Activity Name: Interior - L2 Busway - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on FB9: Activity Name: Interior - L2 AHUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on DO10: Activity Name: Interior - L2 PDUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on DO11: Activity Name: Interior - L2 ATSs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on BD13: Activity Name: Interior - L3 AHUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 27-Jan-2025 End Date: 28-Jan-2025
Note on BF13: Activity Name: Interior - L3 Busway - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 29-Jan-2025 End Date: 11-Feb-2025
Note on EX13: Activity Name: Interior - L3 ATSs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 05-May-2025 End Date: 16-May-2025
Note on FB14: Activity Name: Interior - L3 TCP/MSB - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FB15: Activity Name: Interior - L3 UPS - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FE16: Activity Name: Interior - L3 PDUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 12-May-2025 End Date: 16-May-2025
Note on BK17: Activity Name: HAC install and Rise - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on BM17: Activity Name: Begin HAC Assembly - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 05-Feb-2025 End Date: 05-Feb-2025
Note on BT17: Activity Name: Finishes and Signage - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 12-Feb-2025 End Date: 12-Feb-2025
Note on CM17: Activity Name: Termination at PDU & Busway- COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on DO17: Activity Name: Install PDU's - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on BK18: Activity Name: Install Busway - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on BK19: Activity Name: Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on BK20: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on CH24: Activity Name: Connect to Cable tray and conduit equipment - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on CT24: Activity Name: Door Frame Installation - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 10-Mar-2025 End Date: 21-Mar-2025
Note on CM25: Activity Name: Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 03-Mar-2025 End Date: 07-Mar-2025
Note on DA25: Activity Name: Finishes and Signage - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 17-Mar-2025 End Date: 04-Apr-2025
Note on CM26: Activity Name: Installation of UPS Equipment - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 03-Mar-2025 End Date: 14-Mar-2025
Note on CF28: Activity Name: Install ceiling and Light Fittings - COLO3 Cell 1 - MG Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on CF29: Activity Name: Trim out MEP - COLO3 Cell 1 - MG Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on BY30: Activity Name: Interior - L1 UPS - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on CA30: Activity Name: Interior - L1 PDUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 19-Feb-2025 End Date: 19-Feb-2025
Note on DA30: Activity Name: Interior - L1 AHUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on DH30: Activity Name: Interior - L1 TCP/MSB - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 24-Mar-2025 End Date: 04-Apr-2025
Note on DV30: Activity Name: Interior - L1 Busway - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 07-Apr-2025 End Date: 25-Apr-2025
Note on DA31: Activity Name: Interior - L1 ATSs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 17-Mar-2025 End Date: 28-Mar-2025
Note on EJ31: Activity Name: Interior - L1 ADP - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on BT35: Activity Name: Interior - L2 ADP - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 12-Feb-2025 End Date: 12-Feb-2025
Note on BY35: Activity Name: Interior - L2 TCP/MSB - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on DA35: Activity Name: Interior - L2 ATSs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 17-Mar-2025 End Date: 17-Mar-2025
Note on DV35: Activity Name: Interior - L2 Busway - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on EC35: Activity Name: Interior - L2 AHUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on BY36: Activity Name: Interior - L2 UPS - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on BY37: Activity Name: Interior - L2 PDUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on EC41: Activity Name: Interior - L3 TCP/MSB - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on EJ41: Activity Name: Interior - L3 UPS - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on EQ41: Activity Name: Interior - L3 PDUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on FB41: Activity Name: Interior - L3 Busway - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on EJ42: Activity Name: Interior - L3 ADP - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on EQ42: Activity Name: Interior - L3 ATSs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on EU43: Activity Name: Interior - L3 AHUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on AP45: Activity Name: Begin HAC Assembly - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 13-Jan-2025 End Date: 28-Jan-2025
Note on BT45: Activity Name: Install Busway - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 12-Feb-2025 End Date: 14-Feb-2025
Note on BY45: Activity Name: Ceiling Grid and Tile - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on CF45: Activity Name: Cable Pulling at PDU & Busway- COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 24-Feb-2025 End Date: 07-Mar-2025
Note on CT45: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on DA45: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 17-Mar-2025 End Date: 04-Apr-2025
Note on BY46: Activity Name: HAC install and Rise - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on CT46: Activity Name: Termination at PDU & Busway - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on DQ46: Activity Name: Install PDU's - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 02-Apr-2025 End Date: 08-Apr-2025
Note on CV47: Activity Name: Finishes and Signage - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on AX49: Activity Name: Installation of ADP & ATS - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 21-Jan-2025 End Date: 03-Feb-2025
Note on BL49: Activity Name: Installation of UPS Equipment - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 04-Feb-2025 End Date: 06-Feb-2025
Note on BO49: Activity Name: Installation of TCP/MSB - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on DE49: Activity Name: Install DX Split Units - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 21-Mar-2025 End Date: 28-Mar-2025
Note on BN50: Activity Name: Finishes and Signage - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 06-Feb-2025 End Date: 19-Feb-2025
Note on BR51: Activity Name: Below Ceiling MEP Rough In - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on BR52: Activity Name: Door Frame Installation - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on BR53: Activity Name: Connect to Cable tray and conduit equipment - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on BT54: Activity Name: Placing the AHU - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 12-Feb-2025 End Date: 12-Feb-2025
Note on CA54: Activity Name: Post Wall Overhead MEP - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 19-Feb-2025 End Date: 21-Feb-2025
Note on CQ54: Activity Name: Install ceiling and Light Fittings - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 07-Mar-2025 End Date: 11-Mar-2025
Note on BT55: Activity Name: Piping and Electrical Termination to AHUs - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 12-Feb-2025 End Date: 04-Mar-2025
Note on CU55: Activity Name: Trim out MEP - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 11-Mar-2025 End Date: 21-Mar-2025
Note on CC56: Activity Name: Pipe Testing - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: Inspections Start Date: 21-Feb-2025 End Date: 07-Mar-2025
Note on BR59: Activity Name: Interior - L1 AHUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on BY59: Activity Name: Interior - L1 Busway - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on CF59: Activity Name: Interior - L1 PDUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 24-Feb-2025 End Date: 07-Mar-2025
Note on BR60: Activity Name: Interior - L1 TCP/MSB - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on BY60: Activity Name: Interior - L1 ADP - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 17-Feb-2025 End Date: 07-Mar-2025
Note on BT61: Activity Name: Interior - L1 ATSs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 12-Feb-2025 End Date: 18-Feb-2025
Note on CF61: Activity Name: Interior - L1 UPS - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 24-Feb-2025 End Date: 14-Mar-2025
Note on AE63: Activity Name: Interior - L2 ADP - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 02-Jan-2025 End Date: 02-Jan-2025
Note on AQ63: Activity Name: Interior - L2 UPS - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on AY63: Activity Name: Interior - L2 ATSs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 22-Jan-2025 End Date: 22-Jan-2025
Note on BY63: Activity Name: Interior - L2 AHUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on DA63: Activity Name: Interior - L2 TCP/MSB - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on AQ64: Activity Name: Interior - L2 PDUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on AQ65: Activity Name: Interior - L2 Busway - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on AQ67: Activity Name: Interior - L3 TCP/MSB - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on DB67: Activity Name: Interior - L3 UPS - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on DI67: Activity Name: Interior - L3 PDUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on DP67: Activity Name: Interior - L3 Busway - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on DI68: Activity Name: Interior - L3 ADP - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on DP68: Activity Name: Interior - L3 AHUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on DI69: Activity Name: Interior - L3 ATSs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on R74: Activity Name: Begin HAC Assembly - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 20-Dec-2024 End Date: 06-Jan-2025
Note on AJ74: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 07-Jan-2025 End Date: 13-Jan-2025
Note on AS74: Activity Name: Cable Pulling at PDU & Busway- COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 16-Jan-2025 End Date: 05-Feb-2025
Note on U75: Activity Name: Install PDU's - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 23-Dec-2024 End Date: 30-Dec-2024
Note on AF75: Activity Name: Install Busway - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 03-Jan-2025 End Date: 09-Jan-2025
Note on AW75: Activity Name: Termination at PDU & Busway - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 20-Jan-2025 End Date: 24-Jan-2025
Note on BD75: Activity Name: Finishes and Signage - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 27-Jan-2025 End Date: 07-Feb-2025
Note on V76: Activity Name: Ceiling Grid and Tile - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 24-Dec-2024 End Date: 31-Dec-2024
Note on AL76: Activity Name: HAC install and Rise - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 09-Jan-2025 End Date: 15-Jan-2025
Note on BK76: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on AJ78: Activity Name: Finishes and Signage - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 07-Jan-2025 End Date: 13-Jan-2025
Note on AR78: Activity Name: Installation of TCP/MSB - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 15-Jan-2025 End Date: 04-Feb-2025
Note on BO78: Activity Name: Door Frame Installation - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 07-Feb-2025 End Date: 11-Feb-2025
Note on CC78: Activity Name: Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 21-Feb-2025 End Date: 28-Feb-2025
Note on FT78: Activity Name: Install DX Split Units - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 27-May-2025 End Date: 30-Jun-2025
Note on HC78: Activity Name: Installation of ADP & ATS - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 01-Jul-2025 End Date: 02-Jul-2025
Note on AY79: Activity Name: Installation of UPS Equipment - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 22-Jan-2025 End Date: 24-Jan-2025
Note on BS79: Activity Name: Connect to Cable tray and conduit equipment - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 11-Feb-2025 End Date: 21-Feb-2025
Note on BA80: Activity Name: Below Ceiling MEP Rough In - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 24-Jan-2025 End Date: 07-Feb-2025
Note on EX84: Activity Name: Piping and Electrical Termination to AHUs - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 05-May-2025 End Date: 16-May-2025
Note on FL84: Activity Name: Trim out MEP - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 19-May-2025 End Date: 23-May-2025
Note on FB85: Activity Name: Post Wall Overhead MEP - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FB86: Activity Name: Install ceiling and Light Fittings - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FE87: Activity Name: Pipe Testing - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: Inspections Start Date: 12-May-2025 End Date: 16-May-2025
Note on CF88: Activity Name: Interior - L1 AHUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on CM88: Activity Name: Interior - L1 Busway - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 03-Mar-2025 End Date: 07-Mar-2025
Note on CT88: Activity Name: Interior - L1 UPS - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 10-Mar-2025 End Date: 21-Mar-2025
Note on CF89: Activity Name: Interior - L1 TCP/MSB - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on CM89: Activity Name: Interior - L1 ADP - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 03-Mar-2025 End Date: 14-Mar-2025
Note on CH90: Activity Name: Interior - L1 ATSs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on CT90: Activity Name: Interior - L1 PDUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 10-Mar-2025 End Date: 28-Mar-2025
Note on AW92: Activity Name: Interior - L2 UPS - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 20-Jan-2025 End Date: 20-Jan-2025
Note on AX92: Activity Name: Interior - L2 ATSs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 21-Jan-2025 End Date: 21-Jan-2025
Note on BM92: Activity Name: Interior - L2 PDUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 05-Feb-2025 End Date: 05-Feb-2025
Note on CM92: Activity Name: Interior - L2 AHUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on DH92: Activity Name: Interior - L2 TCP/MSB - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on AX93: Activity Name: Interior - L2 Busway - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 21-Jan-2025 End Date: 21-Jan-2025
Note on AX94: Activity Name: Interior - L2 ADP - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 21-Jan-2025 End Date: 21-Jan-2025
Note on AX96: Activity Name: Interior - L3 TCP/MSB - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 21-Jan-2025 End Date: 21-Jan-2025
Note on DP96: Activity Name: Interior - L3 PDUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on DW96: Activity Name: Interior - L3 ADP - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on ED96: Activity Name: Interior - L3 UPS - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 15-Apr-2025 End Date: 21-Apr-2025
Note on DW97: Activity Name: Interior - L3 AHUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on ED97: Activity Name: Interior - L3 Busway - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 15-Apr-2025 End Date: 21-Apr-2025
Note on DW98: Activity Name: Interior - L3 ATSs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on D100: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 06-Dec-2024 End Date: 23-Dec-2024
Note on AL100: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 09-Jan-2025 End Date: 22-Jan-2025
Note on BF100: Activity Name: Cable Pulling at PDU & Busway- COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 29-Jan-2025 End Date: 31-Jan-2025
Note on BK100: Activity Name: Termination at PDU & Busway - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on BR100: Activity Name: Finishes and Signage - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 10-Feb-2025 End Date: 21-Feb-2025
Note on CF100: Activity Name: HAC install and Rise - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on AP101: Activity Name: Security Screen Installation - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 13-Jan-2025 End Date: 17-Jan-2025
Note on AW101: Activity Name: Install PDU's - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 20-Jan-2025 End Date: 24-Jan-2025
Note on BN101: Activity Name: Install Busway - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 06-Feb-2025 End Date: 26-Feb-2025
Note on AQ102: Activity Name: Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 14-Jan-2025 End Date: 20-Jan-2025
Note on AQ103: Activity Name: Ceiling Grid and Tile - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 14-Jan-2025 End Date: 20-Jan-2025
Note on R104: Activity Name: Door Frame Installation - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 20-Dec-2024 End Date: 06-Jan-2025
Note on AJ104: Activity Name: Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 07-Jan-2025 End Date: 09-Jan-2025
Note on AM104: Activity Name: Finishes and Signage - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 10-Jan-2025 End Date: 16-Jan-2025
Note on BF104: Activity Name: Install Ceiling - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 29-Jan-2025 End Date: 29-Jan-2025
Note on BM104: Activity Name: Install DX Split Units - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 05-Feb-2025 End Date: 07-Feb-2025
Note on CC104: Activity Name: Installation of TCP/MSB - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 21-Feb-2025 End Date: 25-Feb-2025
Note on CQ104: Activity Name: Below Ceiling MEP Rough In - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 07-Mar-2025 End Date: 14-Mar-2025
Note on AR105: Activity Name: Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 15-Jan-2025 End Date: 28-Jan-2025
Note on BF105: Activity Name: Installation of ADP & ATS - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 29-Jan-2025 End Date: 18-Feb-2025
Note on CG105: Activity Name: Connect to Cable tray and conduit equipment - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 25-Feb-2025 End Date: 07-Mar-2025
Note on BO106: Activity Name: Installation of UPS Equipment - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 07-Feb-2025 End Date: 21-Feb-2025
Note on AP112: Activity Name: Trim out MEP - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 13-Jan-2025 End Date: 14-Jan-2025
Note on DW112: Activity Name: Deliver AHU into Mech. Gallery - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on EN112: Activity Name: Install Walls and Primer Paint - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 25-Apr-2025 End Date: 01-May-2025
Note on EU112: Activity Name: Layout Ceiling and install Pencile Rod - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on FB112: Activity Name: Piping and Electrical Termination to AHUs - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FI112: Activity Name: Pipe Testing - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: Inspections Start Date: 16-May-2025 End Date: 30-May-2025
Note on FZ112: Activity Name: Install ceiling and Light Fittings - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 02-Jun-2025 End Date: 06-Jun-2025
Note on EU113: Activity Name: Placing the AHU - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on EU114: Activity Name: Post Wall Overhead MEP - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on GW116: Activity Name: Level 4 Cx - Colo 4 Phase: COLO 4 Location: All Trade: None Start Date: 25-Jun-2025 End Date: 30-Jul-2025
Note on IH116: Activity Name: Level 5 Cx / IST - Colo 4 Phase: COLO 4 Location: All Trade: None Start Date: 01-Aug-2025 End Date: 04-Aug-2025
Note on V118: Activity Name: Interior - L1 TCP/MSB - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 24-Dec-2024 End Date: 10-Jan-2025
Note on BT118: Activity Name: Interior - L1 ATSs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 12-Feb-2025 End Date: 14-Feb-2025
Note on BY118: Activity Name: Interior - L1 ADP - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on CF118: Activity Name: Interior - L1 PDUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 24-Feb-2025 End Date: 07-Mar-2025
Note on CT118: Activity Name: Interior - L1 Busway - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on DA118: Activity Name: Interior - L1 UPS - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on CI119: Activity Name: Interior - L1 AHUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 27-Feb-2025 End Date: 19-Mar-2025
Note on CT123: Activity Name: Interior - L2 TCP/MSB - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on DA123: Activity Name: Interior - L2 PDUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on DH123: Activity Name: Interior - L2 ATSs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 24-Mar-2025 End Date: 04-Apr-2025
Note on EC123: Activity Name: Interior - L2 AHUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on CV124: Activity Name: Interior - L2 UPS - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on DO124: Activity Name: Interior - L2 Busway - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 31-Mar-2025 End Date: 18-Apr-2025
Note on DA125: Activity Name: Interior - L2 ADP - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 17-Mar-2025 End Date: 28-Mar-2025
Note on BK129: Activity Name: Interior - L3 TCP/MSB - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on CA129: Activity Name: Interior - L3 ATSs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 19-Feb-2025 End Date: 19-Feb-2025
Note on DA129: Activity Name: Interior - L3 AHUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 17-Mar-2025 End Date: 17-Mar-2025
Note on BK130: Activity Name: Interior - L3 UPS - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on BK131: Activity Name: Interior - L3 PDUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on BK132: Activity Name: Interior - L3 ADP - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on BK133: Activity Name: Interior - L3 Busway - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on AJ135: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 07-Jan-2025 End Date: 20-Jan-2025
Note on AX135: Activity Name: Install PDU's - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 21-Jan-2025 End Date: 23-Jan-2025
Note on BA135: Activity Name: Begin HAC Assembly - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 24-Jan-2025 End Date: 30-Jan-2025
Note on BK135: Activity Name: Termination at PDU & Busway- COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on DE135: Activity Name: Ceiling Grid and Tile - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 21-Mar-2025 End Date: 28-Mar-2025
Note on AZ136: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 23-Jan-2025 End Date: 05-Feb-2025
Note on BD137: Activity Name: Install Busway - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on BD138: Activity Name: HAC install and Rise - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on AP139: Activity Name: Installation of ADP & ATS - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 13-Jan-2025 End Date: 24-Jan-2025
Note on BD139: Activity Name: Installation of UPS Equipment - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 27-Jan-2025 End Date: 28-Jan-2025
Note on BF139: Activity Name: Installation of TCP/MSB - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 29-Jan-2025 End Date: 11-Feb-2025
Note on BT139: Activity Name: Install DX Split Units - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 12-Feb-2025 End Date: 12-Feb-2025
Note on CA139: Activity Name: Below Ceiling MEP Rough In - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 19-Feb-2025 End Date: 21-Feb-2025
Note on CQ139: Activity Name: Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 07-Mar-2025 End Date: 11-Mar-2025
Note on BT140: Activity Name: Door Frame Installation - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 12-Feb-2025 End Date: 04-Mar-2025
Note on CU140: Activity Name: Finishes and Signage - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 11-Mar-2025 End Date: 21-Mar-2025
Note on CC141: Activity Name: Connect to Cable tray and conduit equipment - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 21-Feb-2025 End Date: 07-Mar-2025
Note on EU143: Activity Name: Placing the AHU - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on FB143: Activity Name: Pipe Testing - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: Inspections Start Date: 09-May-2025 End Date: 15-May-2025
Note on FI143: Activity Name: Install ceiling and Light Fittings - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 16-May-2025 End Date: 30-May-2025
Note on FZ143: Activity Name: Trim out MEP - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 02-Jun-2025 End Date: 06-Jun-2025
Note on EU144: Activity Name: Post Wall Overhead MEP - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on EU145: Activity Name: Piping and Electrical Termination to AHUs - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on AP148: Activity Name: Interior - L1 Busway - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 13-Jan-2025 End Date: 28-Jan-2025
Note on BN148: Activity Name: Interior - L1 TCP/MSB - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 06-Feb-2025 End Date: 12-Feb-2025
Note on BY148: Activity Name: Interior - L1 ADP - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on DD148: Activity Name: Interior - L1 AHUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 20-Mar-2025 End Date: 09-Apr-2025
Note on BN149: Activity Name: Interior - L1 ATSs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 06-Feb-2025 End Date: 19-Feb-2025
Note on DR149: Activity Name: Interior - L1 PDUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 03-Apr-2025 End Date: 09-Apr-2025
Note on BR150: Activity Name: Interior - L1 UPS - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on CH152: Activity Name: Interior - L2 TCP/MSB - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 26-Feb-2025 End Date: 28-Feb-2025
Note on CM152: Activity Name: Interior - L2 UPS - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 03-Mar-2025 End Date: 07-Mar-2025
Note on CT152: Activity Name: Interior - L2 PDUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 10-Mar-2025 End Date: 21-Mar-2025
Note on DH152: Activity Name: Interior - L2 ADP - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DO152: Activity Name: Interior - L2 AHUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on DH153: Activity Name: Interior - L2 ATSs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DJ154: Activity Name: Interior - L2 Busway - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on BU156: Activity Name: Interior - L3 AHUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 13-Feb-2025 End Date: 13-Feb-2025
Note on DO156: Activity Name: Interior - L3 TCP/MSB - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 31-Mar-2025 End Date: 11-Apr-2025
Note on EJ156: Activity Name: Interior - L3 ADP - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 21-Apr-2025 End Date: 09-May-2025
Note on BU157: Activity Name: Interior - L3 Busway - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 13-Feb-2025 End Date: 13-Feb-2025
Note on DO157: Activity Name: Interior - L3 UPS - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 31-Mar-2025 End Date: 18-Apr-2025
Note on EX157: Activity Name: Interior - L3 ATSs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 05-May-2025 End Date: 09-May-2025
Note on DV158: Activity Name: Interior - L3 PDUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 07-Apr-2025 End Date: 18-Apr-2025
Note on AF160: Activity Name: Begin HAC Assembly - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 03-Jan-2025 End Date: 16-Jan-2025
Note on AX160: Activity Name: HAC install and Rise - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 21-Jan-2025 End Date: 03-Feb-2025
Note on BL160: Activity Name: Cable Pulling at PDU & Busway- COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 04-Feb-2025 End Date: 06-Feb-2025
Note on BO160: Activity Name: Finishes and Signage - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on CH160: Activity Name: Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 26-Feb-2025 End Date: 18-Mar-2025
Note on DE160: Activity Name: Ceiling Grid and Tile - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 21-Mar-2025 End Date: 25-Mar-2025
Note on DS160: Activity Name: Install PDU's - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 04-Apr-2025 End Date: 11-Apr-2025
Note on AQ161: Activity Name: Install Busway - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 14-Jan-2025 End Date: 20-Jan-2025
Note on BN161: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 06-Feb-2025 End Date: 12-Feb-2025
Note on CQ161: Activity Name: Security Screen Installation - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 07-Mar-2025 End Date: 21-Mar-2025
Note on DI161: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 25-Mar-2025 End Date: 04-Apr-2025
Note on BN162: Activity Name: Termination at PDU & Busway - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 06-Feb-2025 End Date: 12-Feb-2025
Note on AI165: Activity Name: Installation of TCP/MSB - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 06-Jan-2025 End Date: 10-Jan-2025
Note on BD165: Activity Name: Below Ceiling MEP Rough In - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 27-Jan-2025 End Date: 07-Feb-2025
Note on BR165: Activity Name: Door Frame Installation - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 10-Feb-2025 End Date: 11-Feb-2025
Note on BT165: Activity Name: Connect to Cable tray and conduit equipment - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 12-Feb-2025 End Date: 25-Feb-2025
Note on CH165: Activity Name: Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 26-Feb-2025 End Date: 26-Feb-2025
Note on CO165: Activity Name: Finishes and Signage - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 05-Mar-2025 End Date: 07-Mar-2025
Note on EU165: Activity Name: Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on FB165: Activity Name: Install DX Split Units - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FI165: Activity Name: Installation of ADP & ATS - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 16-May-2025 End Date: 30-May-2025
Note on FZ165: Activity Name: Installation of UPS Equipment - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 02-Jun-2025 End Date: 06-Jun-2025
Note on EU166: Activity Name: Install Ceiling - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on DV169: Activity Name: Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on EC169: Activity Name: Install Walls and Primer Paint - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on EJ169: Activity Name: Post Wall Overhead MEP - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on EQ169: Activity Name: Pipe Testing - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: Inspections Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on EC170: Activity Name: Layout Ceiling and install Pencile Rod - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on EJ170: Activity Name: Piping and Electrical Termination to AHUs - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on EU170: Activity Name: Trim out MEP - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on EC171: Activity Name: Placing the AHU - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on EN171: Activity Name: Install ceiling and Light Fittings - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 25-Apr-2025 End Date: 01-May-2025
Note on BK173: Activity Name: Interior - L1 UPS - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on CA173: Activity Name: Interior - L1 AHUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 19-Feb-2025 End Date: 19-Feb-2025
Note on DA173: Activity Name: Interior - L1 PDUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 17-Mar-2025
Note on BK174: Activity Name: Interior - L1 TCP/MSB - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on BK175: Activity Name: Interior - L1 ATSs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on BK176: Activity Name: Interior - L1 ADP - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on DV177: Activity Name: Interior - L2 TCP/MSB - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on EC177: Activity Name: Interior - L2 UPS - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on EJ177: Activity Name: Interior - L2 ATSs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on EQ177: Activity Name: Interior - L2 AHUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on EC178: Activity Name: Interior - L2 PDUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on EJ178: Activity Name: Interior - L2 Busway - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on EC179: Activity Name: Interior - L2 ADP - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on EN181: Activity Name: Interior - L3 TCP/MSB - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 25-Apr-2025 End Date: 01-May-2025
Note on EU181: Activity Name: Interior - L3 UPS - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on FB181: Activity Name: Interior - L3 ATSs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FI181: Activity Name: Interior - L3 AHUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 16-May-2025 End Date: 30-May-2025
Note on FZ181: Activity Name: Interior - L3 Busway - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 02-Jun-2025 End Date: 06-Jun-2025
Note on EU182: Activity Name: Interior - L3 PDUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on EU183: Activity Name: Interior - L3 ADP - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on V187: Activity Name: Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 24-Dec-2024 End Date: 10-Jan-2025
Note on BT187: Activity Name: Security Screen Installation - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 12-Feb-2025 End Date: 14-Feb-2025
Note on BY187: Activity Name: Ceiling Grid and Tile - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on CF187: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 24-Feb-2025 End Date: 07-Mar-2025
Note on CT187: Activity Name: Install PDU's - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on DA187: Activity Name: HAC install and Rise - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on DH187: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 24-Mar-2025 End Date: 04-Apr-2025
Note on EC187: Activity Name: Finishes and Signage - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on CT188: Activity Name: Begin HAC Assembly - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on DA188: Activity Name: Cable Pulling at PDU & Busway- COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 28-Mar-2025
Note on DO188: Activity Name: Termination at PDU & Busway - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 31-Mar-2025 End Date: 18-Apr-2025
Note on CV189: Activity Name: Install Busway - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on EX191: Activity Name: Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 05-May-2025 End Date: 09-May-2025
Note on FE191: Activity Name: Install Ceiling - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 12-May-2025 End Date: 16-May-2025
Note on FP191: Activity Name: Below Ceiling MEP Rough In - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 23-May-2025 End Date: 30-May-2025
Note on GA191: Activity Name: Installation of ADP & ATS - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 03-Jun-2025 End Date: 09-Jun-2025
Note on GO191: Activity Name: Connect to Cable tray and conduit equipment - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 17-Jun-2025 End Date: 23-Jun-2025
Note on GW191: Activity Name: Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 25-Jun-2025 End Date: 30-Jul-2025
Note on IH191: Activity Name: Finishes and Signage - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 01-Aug-2025 End Date: 04-Aug-2025
Note on FB192: Activity Name: Install DX Split Units - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FI192: Activity Name: Installation of UPS Equipment - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 16-May-2025 End Date: 22-May-2025
Note on GA192: Activity Name: Door Frame Installation - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 03-Jun-2025 End Date: 16-Jun-2025
Note on FI193: Activity Name: Installation of TCP/MSB - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 16-May-2025 End Date: 22-May-2025
Note on BU195: Activity Name: Overhead MEP Installation - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 13-Feb-2025 End Date: 13-Feb-2025
Note on BY195: Activity Name: Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on CO195: Activity Name: Install Walls and Primer Paint - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 05-Mar-2025 End Date: 05-Mar-2025
Note on DO195: Activity Name: Layout Ceiling and install Pencile Rod - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 31-Mar-2025 End Date: 31-Mar-2025
Note on EJ195: Activity Name: Post Wall Overhead MEP - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on EQ195: Activity Name: Piping and Electrical Termination to AHUs - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on EX195: Activity Name: Trim out MEP - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 05-May-2025 End Date: 09-May-2025
Note on BU196: Activity Name: Placing the AHU - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 13-Feb-2025 End Date: 13-Feb-2025
Note on EQ196: Activity Name: Pipe Testing - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: Inspections Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on EQ197: Activity Name: Install ceiling and Light Fittings - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on BU199: Activity Name: Interior - L1 TCP/MSB - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 13-Feb-2025 End Date: 13-Feb-2025
Note on BY199: Activity Name: Interior - L1 UPS - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on CO199: Activity Name: Interior - L1 AHUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 05-Mar-2025 End Date: 05-Mar-2025
Note on DO199: Activity Name: Interior - L1 PDUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 31-Mar-2025 End Date: 31-Mar-2025
Note on BU200: Activity Name: Interior - L1 ATSs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 13-Feb-2025 End Date: 13-Feb-2025
Note on BU201: Activity Name: Interior - L1 ADP - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 13-Feb-2025 End Date: 13-Feb-2025
Note on BU202: Activity Name: Interior - L1 Busway - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 13-Feb-2025 End Date: 13-Feb-2025
Note on EJ203: Activity Name: Interior - L2 TCP/MSB - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on EQ203: Activity Name: Interior - L2 UPS - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on EX203: Activity Name: Interior - L2 ATSs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 05-May-2025 End Date: 09-May-2025
Note on FE203: Activity Name: Interior - L2 AHUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 12-May-2025 End Date: 16-May-2025
Note on EQ204: Activity Name: Interior - L2 PDUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on EX204: Activity Name: Interior - L2 Busway - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 05-May-2025 End Date: 09-May-2025
Note on EQ205: Activity Name: Interior - L2 ADP - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on FB207: Activity Name: Interior - L3 TCP/MSB - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FI207: Activity Name: Interior - L3 PDUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 16-May-2025 End Date: 22-May-2025
Note on FP207: Activity Name: Interior - L3 ATSs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 23-May-2025 End Date: 30-May-2025
Note on GA207: Activity Name: Interior - L3 UPS - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 03-Jun-2025 End Date: 09-Jun-2025
Note on GO207: Activity Name: Interior - L3 Busway - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 17-Jun-2025 End Date: 23-Jun-2025
Note on FI208: Activity Name: Interior - L3 ADP - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 16-May-2025 End Date: 22-May-2025
Note on GA208: Activity Name: Interior - L3 AHUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 03-Jun-2025 End Date: 16-Jun-2025
Note on AP211: Activity Name: Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 13-Jan-2025 End Date: 28-Jan-2025
Note on CH211: Activity Name: Security Screen Installation - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 26-Feb-2025 End Date: 28-Feb-2025
Note on CM211: Activity Name: Ceiling Grid and Tile - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 03-Mar-2025 End Date: 07-Mar-2025
Note on CT211: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 10-Mar-2025 End Date: 21-Mar-2025
Note on DH211: Activity Name: Install PDU's - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DO211: Activity Name: HAC install and Rise - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on DV211: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 07-Apr-2025 End Date: 18-Apr-2025
Note on EJ211: Activity Name: Termination at PDU & Busway - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 21-Apr-2025 End Date: 09-May-2025
Note on DH212: Activity Name: Begin HAC Assembly - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DO212: Activity Name: Cable Pulling at PDU & Busway- COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 31-Mar-2025 End Date: 11-Apr-2025
Note on EX212: Activity Name: Finishes and Signage - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 05-May-2025 End Date: 09-May-2025
Note on DJ213: Activity Name: Install Busway - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on DO214: Activity Name: Closing Construction Access Door - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 31-Mar-2025 End Date: 18-Apr-2025
Note on AF216: Activity Name: Install Walls and Primer Paint - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 03-Jan-2025 End Date: 16-Jan-2025
Note on AX216: Activity Name: Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 21-Jan-2025 End Date: 03-Feb-2025
Note on BL216: Activity Name: Install Ceiling - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 04-Feb-2025 End Date: 06-Feb-2025
Note on BO216: Activity Name: Install DX Split Units - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on BY216: Activity Name: Door Frame Installation - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on DD216: Activity Name: Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 20-Mar-2025 End Date: 09-Apr-2025
Note on AQ217: Activity Name: Install Upper Screens - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 14-Jan-2025 End Date: 20-Jan-2025
Note on BN217: Activity Name: Installation of ADP & ATS - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 06-Feb-2025 End Date: 12-Feb-2025
Note on DR217: Activity Name: Finishes and Signage - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 03-Apr-2025 End Date: 09-Apr-2025
Note on BN218: Activity Name: Installation of TCP/MSB - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 06-Feb-2025 End Date: 12-Feb-2025
Note on BN219: Activity Name: Connect to Cable tray and conduit equipment - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 06-Feb-2025 End Date: 12-Feb-2025
Note on AI220: Activity Name: Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 06-Jan-2025 End Date: 10-Jan-2025
Note on BD220: Activity Name: Overhead MEP Installation - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 27-Jan-2025 End Date: 07-Feb-2025
Note on BR220: Activity Name: Deliver AHU into Mech. Gallery - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 10-Feb-2025 End Date: 11-Feb-2025
Note on BT220: Activity Name: Install Walls and Primer Paint - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 12-Feb-2025 End Date: 25-Feb-2025
Note on CH220: Activity Name: Layout Ceiling and install Pencile Rod - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 26-Feb-2025 End Date: 26-Feb-2025
Note on CO220: Activity Name: Placing the AHU - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 05-Mar-2025 End Date: 07-Mar-2025
Note on DE220: Activity Name: Pipe Testing - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: Inspections Start Date: 21-Mar-2025 End Date: 25-Mar-2025
Note on DS220: Activity Name: Trim out MEP - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 04-Apr-2025 End Date: 11-Apr-2025
Note on CH221: Activity Name: Post Wall Overhead MEP - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 26-Feb-2025 End Date: 18-Mar-2025
Note on DI221: Activity Name: Install ceiling and Light Fittings - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 25-Mar-2025 End Date: 04-Apr-2025
Note on CQ222: Activity Name: Piping and Electrical Termination to AHUs - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 07-Mar-2025 End Date: 21-Mar-2025
Note on BK227: Activity Name: Level 4 Cx - Colo 5 Phase: COLO 5 Location: All Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on BR227: Activity Name: Level 5 Cx / IST - Colo 5 Phase: COLO 5 Location: All Trade: None Start Date: 10-Feb-2025 End Date: 21-Feb-2025
Note on AI229: Activity Name: Interior - L2 TCP/MSB - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 06-Jan-2025 End Date: 10-Jan-2025
Note on AP229: Activity Name: Interior - L2 UPS - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 13-Jan-2025 End Date: 31-Jan-2025
Note on BK229: Activity Name: Interior - L2 ADP - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on BR229: Activity Name: Interior - L2 PDUs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on BY229: Activity Name: Interior - L2 AHUs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on BD230: Activity Name: Interior - L2 ATSs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on BD231: Activity Name: Interior - L2 Busway - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on BF233: Activity Name: Interior - L3 PDUs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on BR233: Activity Name: Interior - L3 ADP - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 10-Feb-2025 End Date: 21-Feb-2025
Note on CM233: Activity Name: Interior - L3 AHUs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 03-Mar-2025 End Date: 07-Mar-2025
Note on BK234: Activity Name: Interior - L3 Busway - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on BR234: Activity Name: Interior - L3 ATSs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 10-Feb-2025 End Date: 28-Feb-2025
Note on BK235: Activity Name: Interior - L3 TCP/MSB - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on BK236: Activity Name: Interior - L3 UPS - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 21-Feb-2025
Note on BE237: Activity Name: Termination at PDU & Busway- COLO5 Cell 1 - DH Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 28-Jan-2025 End Date: 07-Feb-2025
Note on BO238: Activity Name: Finishes and Signage - COLO5 Cell 1 - DH Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 07-Feb-2025 End Date: 14-Feb-2025
Note on ES239: Activity Name: Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 30-Apr-2025 End Date: 03-Jun-2025
Note on GB239: Activity Name: Finishes and Signage - COLO5 Cell 1 - ER Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 04-Jun-2025 End Date: 05-Jun-2025
Note on EG241: Activity Name: Trim out MEP - COLO5 Cell 1 - MG Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 18-Apr-2025 End Date: 24-Apr-2025
Note on EU242: Activity Name: Interior - L2 TCP/MSB - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on FB242: Activity Name: Interior - L2 UPS - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FI242: Activity Name: Interior - L2 Busway - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 16-May-2025 End Date: 22-May-2025
Note on EX243: Activity Name: Interior - L2 ATSs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 05-May-2025 End Date: 16-May-2025
Note on FB244: Activity Name: Interior - L2 PDUs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FB245: Activity Name: Interior - L2 ADP - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FB246: Activity Name: Interior - L2 AHUs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on AM248: Activity Name: Interior - L3 Busway - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 10-Jan-2025 End Date: 16-Jan-2025
Note on AY248: Activity Name: Interior - L3 TCP/MSB - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 22-Jan-2025 End Date: 24-Jan-2025
Note on BO248: Activity Name: Interior - L3 UPS - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 07-Feb-2025 End Date: 11-Feb-2025
Note on CC248: Activity Name: Interior - L3 AHUs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 21-Feb-2025 End Date: 28-Feb-2025
Note on AR249: Activity Name: Interior - L3 PDUs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 15-Jan-2025 End Date: 04-Feb-2025
Note on BS249: Activity Name: Interior - L3 ATSs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 11-Feb-2025 End Date: 21-Feb-2025
Note on BA250: Activity Name: Interior - L3 ADP - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 24-Jan-2025 End Date: 07-Feb-2025
Note on DI254: Activity Name: Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on DP254: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on DW254: Activity Name: Finishes and Signage - COLO5 Cell 2 - DH Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on DP255: Activity Name: Termination at PDU & Busway- COLO5 Cell 2 - DH Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on DI258: Activity Name: Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on DI259: Activity Name: Finishes and Signage - COLO5 Cell 2 - ER Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on BR260: Activity Name: Install ceiling and Light Fittings - COLO5 Cell 2 - MG Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on DB260: Activity Name: Trim out MEP - COLO5 Cell 2 - MG Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on BD262: Activity Name: Interior - L2 TCP/MSB - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 27-Jan-2025 End Date: 07-Feb-2025
Note on BR262: Activity Name: Interior - L2 UPS - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on BY262: Activity Name: Interior - L2 AHUs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on CF262: Activity Name: Interior - L2 Busway - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 24-Feb-2025 End Date: 07-Mar-2025
Note on BR263: Activity Name: Interior - L2 PDUs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on BY263: Activity Name: Interior - L2 ATSs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 17-Feb-2025 End Date: 28-Feb-2025
Note on BT264: Activity Name: Interior - L2 ADP - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 12-Feb-2025 End Date: 18-Feb-2025
Note on AW266: Activity Name: Interior - L3 UPS - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 20-Jan-2025 End Date: 20-Jan-2025
Note on AY266: Activity Name: Interior - L3 ADP - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 22-Jan-2025 End Date: 22-Jan-2025
Note on CF266: Activity Name: Interior - L3 TCP/MSB - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 24-Feb-2025 End Date: 14-Mar-2025
Note on AW267: Activity Name: Interior - L3 ATSs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 20-Jan-2025 End Date: 20-Jan-2025
Note on CT267: Activity Name: Interior - L3 PDUs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on AW268: Activity Name: Interior - L3 AHUs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 20-Jan-2025 End Date: 20-Jan-2025
Note on AW269: Activity Name: Interior - L3 Busway - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 20-Jan-2025 End Date: 20-Jan-2025
Note on AW273: Activity Name: Finishes and Signage - COLO5 Cell 3 - DH Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 20-Jan-2025 End Date: 24-Jan-2025
Note on BK273: Activity Name: Cable Pulling at PDU & Busway- COLO5 Cell 3 - DH Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 21-Feb-2025
Note on CF273: Activity Name: Termination at PDU & Busway - COLO5 Cell 3 - DH Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on AL276: Activity Name: Connect to Cable tray and conduit equipment - COLO5 Cell 3 - ER Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 09-Jan-2025 End Date: 22-Jan-2025
Note on AR277: Activity Name: Finishes and Signage - COLO5 Cell 3 - ER Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 15-Jan-2025 End Date: 21-Jan-2025
Note on AW278: Activity Name: Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 20-Jan-2025 End Date: 24-Jan-2025
Note on AP279: Activity Name: Pipe Testing - COLO5 Cell 3 - MG Phase: COLO 5 Location: Cell 3 Trade: Inspections Start Date: 13-Jan-2025 End Date: 17-Jan-2025
Note on AP280: Activity Name: Install ceiling and Light Fittings - COLO5 Cell 3 - MG Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 13-Jan-2025 End Date: 17-Jan-2025
Note on AP281: Activity Name: Trim out MEP - COLO5 Cell 3 - MG Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 13-Jan-2025 End Date: 17-Jan-2025
Note on EX282: Activity Name: Interior - L1 Busway - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 05-May-2025 End Date: 16-May-2025
Note on FB283: Activity Name: Interior - L1 ATSs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FI283: Activity Name: Interior - L1 PDUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 16-May-2025 End Date: 22-May-2025
Note on FI284: Activity Name: Interior - L1 ADP - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 16-May-2025 End Date: 22-May-2025
Note on BA286: Activity Name: Interior - L2 ATSs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 24-Jan-2025 End Date: 30-Jan-2025
Note on BO286: Activity Name: Interior - L2 UPS - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 07-Feb-2025 End Date: 21-Feb-2025
Note on CG286: Activity Name: Interior - L2 ADP - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 25-Feb-2025 End Date: 07-Mar-2025
Note on BD287: Activity Name: Interior - L2 Busway - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on CC287: Activity Name: Interior - L2 PDUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 21-Feb-2025 End Date: 25-Feb-2025
Note on CQ287: Activity Name: Interior - L2 AHUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 07-Mar-2025 End Date: 14-Mar-2025
Note on BF288: Activity Name: Interior - L2 TCP/MSB - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 29-Jan-2025 End Date: 18-Feb-2025
Note on AZ290: Activity Name: Interior - L3 ADP - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 23-Jan-2025 End Date: 05-Feb-2025
Note on CF290: Activity Name: Interior - L3 AHUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 24-Feb-2025 End Date: 14-Mar-2025
Note on BD291: Activity Name: Interior - L3 TCP/MSB - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on BK291: Activity Name: Interior - L3 ATSs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on CV291: Activity Name: Interior - L3 Busway - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on BD292: Activity Name: Interior - L3 PDUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on BF293: Activity Name: Interior - L3 UPS - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on DW294: Activity Name: Closing Construction Access Door - COLO5 Cell 4 - DH Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on EU294: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on FB294: Activity Name: Termination at PDU & Busway - COLO5 Cell 4 - DH Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on FB295: Activity Name: Finishes and Signage - COLO5 Cell 4 - DH Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on DI298: Activity Name: Installation of ADP & ATS - COLO5 Cell 4 - ER Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on DP298: Activity Name: Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on DI299: Activity Name: Connect to Cable tray and conduit equipment - COLO5 Cell 4 - ER Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on DP299: Activity Name: Finishes and Signage - COLO5 Cell 4 - ER Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on BS302: Activity Name: Pipe Testing - COLO5 Cell 4 - MG Phase: COLO 5 Location: Cell 4 Trade: Inspections Start Date: 11-Feb-2025 End Date: 11-Feb-2025
Note on BY302: Activity Name: Piping and Electrical Termination to AHUs - COLO5 Cell 4 - MG Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on DB302: Activity Name: Install ceiling and Light Fittings - COLO5 Cell 4 - MG Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on DI302: Activity Name: Trim out MEP - COLO5 Cell 4 - MG Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on EL306: Activity Name: EPMS/BAS Turn-Up Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 23-Apr-2025 End Date: 29-Apr-2025
Note on BA307: Activity Name: L3 UPM - Colo 2 Cell 1 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 24-Jan-2025 End Date: 28-Jan-2025
Note on BF307: Activity Name: L3 XFMR - Colo 2 Cell 1 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 29-Jan-2025 End Date: 18-Feb-2025
Note on DJ307: Activity Name: L3 GEN - Colo 2 Cell 1 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on BM310: Activity Name: L3 XFMR - Colo 2 Cell 2 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 05-Feb-2025 End Date: 18-Feb-2025
Note on DQ310: Activity Name: L3 GEN - Colo 2 Cell 2 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 02-Apr-2025 End Date: 08-Apr-2025
Note on BO311: Activity Name: L3 UPM - Colo 2 Cell 2 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 07-Feb-2025 End Date: 14-Feb-2025
Note on Q313: Activity Name: L3 UPM - Colo 2 Cell 3 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 19-Dec-2024 End Date: 10-Jan-2025
Note on CJ313: Activity Name: L3 XFMR - Colo 2 Cell 3 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 28-Feb-2025 End Date: 06-Mar-2025
Note on DX313: Activity Name: L3 GEN - Colo 2 Cell 3 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 09-Apr-2025 End Date: 22-Apr-2025
Note on AM316: Activity Name: L3 UPM - Colo 2 Cell 4 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 10-Jan-2025 End Date: 16-Jan-2025
Note on BE316: Activity Name: L3 GEN - Colo 2 Cell 4 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 28-Jan-2025 End Date: 07-Feb-2025
Note on CA316: Activity Name: L3 XFMR - Colo 2 Cell 4 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 19-Feb-2025 End Date: 25-Feb-2025
Note on Y319: Activity Name: L3 UMS 03 - COLO 3 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 27-Dec-2024 End Date: 03-Jan-2025
Note on AP319: Activity Name: EPMS/BAS Turn-Up Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 13-Jan-2025 End Date: 31-Jan-2025
Note on CC319: Activity Name: L3 UMS 04 - COLO 3 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 21-Feb-2025 End Date: 28-Feb-2025
Note on CO322: Activity Name: L3 UPM - Cell 1 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on CV322: Activity Name: L3 XFMR - Cell 1 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on CQ323: Activity Name: L3 GEN - Cell 1 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 07-Mar-2025 End Date: 13-Mar-2025
Note on BK325: Activity Name: L3 GEN - Cell 2 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on CV325: Activity Name: L3 UPM - Cell 2 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on DC325: Activity Name: L3 XFMR - Cell 2 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on BT328: Activity Name: L3 GEN - Cell 3 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 12-Feb-2025 End Date: 04-Mar-2025
Note on CV328: Activity Name: L3 UPM - Cell 3 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on DC328: Activity Name: L3 XFMR - Cell 3 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on CA331: Activity Name: L3 GEN - Cell 4 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 19-Feb-2025 End Date: 04-Mar-2025
Note on DC331: Activity Name: L3 UPM - Cell 4 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on DC332: Activity Name: L3 XFMR - Cell 4 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on DJ334: Activity Name: EPMS/BAS Turn-Up Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on DJ335: Activity Name: L3 GEN - Cell 1 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on EL335: Activity Name: L3 UPM - Cell 1 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 23-Apr-2025 End Date: 29-Apr-2025
Note on GB335: Activity Name: L3 XFMR - Cell 1 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 04-Jun-2025 End Date: 05-Jun-2025
Note on AP338: Activity Name: L3 XFMR - Cell 2 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 13-Jan-2025 End Date: 17-Jan-2025
Note on DQ338: Activity Name: L3 GEN - Cell 2 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 02-Apr-2025 End Date: 08-Apr-2025
Note on ES338: Activity Name: L3 UPM - Cell 2 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 30-Apr-2025 End Date: 03-Jun-2025
Note on BD341: Activity Name: L3 XFMR - Cell 3 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 27-Jan-2025 End Date: 14-Feb-2025
Note on DX341: Activity Name: L3 GEN - Cell 3 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 09-Apr-2025 End Date: 15-Apr-2025
Note on BM342: Activity Name: L3 UPM - Cell 3 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 05-Feb-2025 End Date: 11-Feb-2025
Note on V344: Activity Name: L3 UPM - Cell 4 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 24-Dec-2024 End Date: 15-Jan-2025
Note on BY344: Activity Name: L3 XFMR - Cell 4 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on DX344: Activity Name: L3 GEN - Cell 4 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 09-Apr-2025 End Date: 22-Apr-2025
Note on CA347: Activity Name: L3 UMS 02 - COLO 5 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 19-Feb-2025 End Date: 25-Feb-2025
Note on CH347: Activity Name: L3 URS 01 - COLO 5 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on CH348: Activity Name: L3 UMS 01 - COLO 5 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on CO349: Activity Name: L3 GEN - Cell 1 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on DJ349: Activity Name: L3 UPM - Cell 1 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on DQ349: Activity Name: L3 XFMR - Cell 1 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 02-Apr-2025 End Date: 08-Apr-2025
Note on BA352: Activity Name: L3 XFMR - Cell 2 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 24-Jan-2025 End Date: 07-Feb-2025
Note on CO352: Activity Name: L3 GEN - Cell 2 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on DJ352: Activity Name: L3 UPM - Cell 2 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on BO355: Activity Name: L3 XFMR - Cell 3 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 07-Feb-2025 End Date: 11-Feb-2025
Note on DC355: Activity Name: L3 GEN - Cell 3 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on DX355: Activity Name: L3 UPM - Cell 3 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 09-Apr-2025 End Date: 22-Apr-2025
Note on BS358: Activity Name: L3 XFMR - Cell 4 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 11-Feb-2025 End Date: 21-Feb-2025
Note on DJ358: Activity Name: L3 GEN - Cell 4 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on EL358: Activity Name: L3 UPM - Cell 4 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 23-Apr-2025 End Date: 29-Apr-2025
Note on DJ361: Activity Name: L3 UTS / UTSR - Site Phase: CX Level 3 Location: Site Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on AM362: Activity Name: Install screen wall - Colo 2 - North Phase: Yardwork Location: COLO 2 Trade: None Start Date: 10-Jan-2025 End Date: 30-Jan-2025
Note on O363: Activity Name: Wire pulling and termination for TCP/MSB - Colo 2 - South Phase: Yardwork Location: COLO 2 Trade: None Start Date: 17-Dec-2024 End Date: 08-Jan-2025
Note on AM363: Activity Name: Install screen wall - Colo 2 - South Phase: Yardwork Location: COLO 2 Trade: None Start Date: 10-Jan-2025 End Date: 16-Jan-2025
Note on AY365: Activity Name: Wire pulling and termination for TCP/MSB - Colo 3 - North Phase: Yardwork Location: COLO 3 Trade: None Start Date: 22-Jan-2025 End Date: 28-Jan-2025
Note on BH365: Activity Name: Pull & Terminate Underground Cables (UMS to UPM to XMFR) Phase: Yardwork Location: COLO 3 Trade: None Start Date: 31-Jan-2025 End Date: 06-Feb-2025
Note on BH366: Activity Name: Install screen wall - Colo 3 - North Phase: Yardwork Location: COLO 3 Trade: None Start Date: 31-Jan-2025 End Date: 06-Feb-2025
Note on AY368: Activity Name: Pull & Terminate Underground Cables (UMS to UPM to XMFR) Phase: Yardwork Location: COLO 3 Trade: None Start Date: 22-Jan-2025 End Date: 28-Jan-2025
Note on AY369: Activity Name: Install screen wall - Colo 3 - South Phase: Yardwork Location: COLO 3 Trade: None Start Date: 22-Jan-2025 End Date: 28-Jan-2025
Note on DJ370: Activity Name: Wire pulling and termination for TCP/MSB - Colo 4 - North Phase: Yardwork Location: COLO 4 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on DQ370: Activity Name: Install screen wall - Colo 4 - North Phase: Yardwork Location: COLO 4 Trade: None Start Date: 02-Apr-2025 End Date: 08-Apr-2025
Note on DJ371: Activity Name: Pull & Terminate Underground Cables (UMS to UPM to XMFR) Phase: Yardwork Location: COLO 4 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on BH373: Activity Name: Wire pulling and termination for TCP/MSB - Colo 4 - South Phase: Yardwork Location: COLO 4 Trade: None Start Date: 31-Jan-2025 End Date: 06-Feb-2025
Note on DC373: Activity Name: Pull & Terminate Underground Cables (UMS to UPM to XMFR) Phase: Yardwork Location: COLO 4 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on DJ373: Activity Name: Install screen wall - Colo 4 - South Phase: Yardwork Location: COLO 4 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on AT376: Activity Name: Install screen wall - Colo 5 - East Phase: Yardwork Location: COLO 5 Trade: None Start Date: 17-Jan-2025 End Date: 06-Feb-2025
Note on BO377: Activity Name: Install Generator Muffler - Colo 5 - West Phase: Yardwork Location: COLO 5 Trade: None Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on BU378: Activity Name: Install screen wall - Colo 5 - West Phase: Yardwork Location: COLO 5 Trade: None Start Date: 13-Feb-2025 End Date: 19-Feb-2025
Note on AQ379: Activity Name: L2 GEN - COLO2 Phase: CX Level 2 Location: COLO 2 Trade: None Start Date: 14-Jan-2025 End Date: 24-Jan-2025
Note on EL379: Activity Name: L2 XFMR - COLO2 Phase: CX Level 2 Location: COLO 2 Trade: None Start Date: 23-Apr-2025 End Date: 29-Apr-2025
Note on BA380: Activity Name: L2 UPM - COLO2 Phase: CX Level 2 Location: COLO 2 Trade: None Start Date: 24-Jan-2025 End Date: 31-Jan-2025
Note on CB382: Activity Name: L2 UMS 03 - COLO 3 Phase: CX Level 2 Location: COLO 3 Trade: None Start Date: 20-Feb-2025 End Date: 26-Feb-2025
Note on CI382: Activity Name: L2 GEN - COLO3 Phase: CX Level 2 Location: COLO 3 Trade: None Start Date: 27-Feb-2025 End Date: 05-Mar-2025
Note on CP382: Activity Name: L2 UPM - COLO3 (UPM ROJ Driving) Phase: CX Level 2 Location: COLO 3 Trade: None Start Date: 06-Mar-2025 End Date: 12-Mar-2025
Note on CB383: Activity Name: L2 UMS 04 - COLO 3 Phase: CX Level 2 Location: COLO 3 Trade: None Start Date: 20-Feb-2025 End Date: 26-Feb-2025
Note on CB384: Activity Name: L2 XFMR - COLO3 Phase: CX Level 2 Location: COLO 3 Trade: None Start Date: 20-Feb-2025 End Date: 26-Feb-2025
Note on CI387: Activity Name: L2 XFMR - COLO4 Phase: CX Level 2 Location: COLO 4 Trade: None Start Date: 27-Feb-2025 End Date: 05-Mar-2025
Note on DC387: Activity Name: L2 GEN - COLO4 Phase: CX Level 2 Location: COLO 4 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on DJ387: Activity Name: L2 UPM - COLO4 (UPM ROJ Driving) Phase: CX Level 2 Location: COLO 4 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on AL390: Activity Name: L2 UMS 01 - COLO 5 Phase: CX Level 2 Location: COLO 5 Trade: None Start Date: 09-Jan-2025 End Date: 29-Jan-2025
Note on BG390: Activity Name: L2 UMS 02 - COLO 5 Phase: CX Level 2 Location: COLO 5 Trade: None Start Date: 30-Jan-2025 End Date: 05-Feb-2025
Note on BU390: Activity Name: L2 UPM - COLO5 (UPM ROJ Driving) Phase: CX Level 2 Location: COLO 5 Trade: None Start Date: 13-Feb-2025 End Date: 19-Feb-2025
Note on CC390: Activity Name: L2 GEN - COLO5 Phase: CX Level 2 Location: COLO 5 Trade: None Start Date: 21-Feb-2025 End Date: 27-Feb-2025
Note on AT391: Activity Name: L2 URS 01 - COLO 5 Phase: CX Level 2 Location: COLO 5 Trade: None Start Date: 17-Jan-2025 End Date: 30-Jan-2025
Note on BH391: Activity Name: L2 XFMR - COLO5 Phase: CX Level 2 Location: COLO 5 Trade: None Start Date: 31-Jan-2025 End Date: 20-Feb-2025
Note on DX395: Activity Name: L2 UTS / UTSR - Site Phase: CX Level 2 Location: Site Trade: None Start Date: 09-Apr-2025 End Date: 22-Apr-2025
Note on DS396: Activity Name: Level 5 Cx / IST - Colo 2 Phase: COLO 2 Location: All Trade: None Start Date: 04-Apr-2025 End Date: 17-Apr-2025
Note on DZ397: Activity Name: Level 4 Cx - Colo 2 Phase: COLO 2 Location: All Trade: None Start Date: 11-Apr-2025 End Date: 17-Apr-2025
Note on DB398: Activity Name: Interior - L2 TCP/MSB - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on DI398: Activity Name: Interior - L2 AHUs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on DP398: Activity Name: Interior - L2 Busway - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on DB399: Activity Name: Interior - L2 ADP - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on DI399: Activity Name: Interior - L2 ATSs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on DP399: Activity Name: Interior - L2 PDUs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on DI400: Activity Name: Interior - L2 UPS - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on AS402: Activity Name: Interior - L3 ATSs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 16-Jan-2025 End Date: 05-Feb-2025
Note on BT402: Activity Name: Interior - L3 ADP - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 12-Feb-2025 End Date: 18-Feb-2025
Note on CF402: Activity Name: Interior - L3 AHUs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on DK402: Activity Name: Interior - L3 TCP/MSB - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 27-Mar-2025 End Date: 09-Apr-2025
Note on BH403: Activity Name: Interior - L3 PDUs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 31-Jan-2025 End Date: 11-Feb-2025
Note on DW403: Activity Name: Interior - L3 UPS - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on BK404: Activity Name: Interior - L3 Busway - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 21-Feb-2025
Note on CU406: Activity Name: Cable Pulling at PDU to Busway & MSB - COLO2 Cell 1 - DH Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on DB406: Activity Name: Termination at PDU to Busway & MSB- COLO2 Cell 1 - DH Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on DB407: Activity Name: Finishes and Signage - COLO2 Cell 1 - DH Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on CN409: Activity Name: Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on CU409: Activity Name: Finishes and Signage - COLO2 Cell 1 - ER Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on DB411: Activity Name: Interior - L2 TCP/MSB - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on DL411: Activity Name: Interior - L2 ADP - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on DS411: Activity Name: Interior - L2 Busway - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on DB412: Activity Name: Interior - L2 UPS - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on DL412: Activity Name: Interior - L2 ATSs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on DB413: Activity Name: Interior - L2 PDUs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on DL413: Activity Name: Interior - L2 AHUs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on AE415: Activity Name: Interior - L3 Busway - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 02-Jan-2025 End Date: 08-Jan-2025
Note on BT415: Activity Name: Interior - L3 ADP - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 12-Feb-2025 End Date: 13-Feb-2025
Note on BV415: Activity Name: Interior - L3 ATSs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 14-Feb-2025 End Date: 25-Feb-2025
Note on CH415: Activity Name: Interior - L3 AHUs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on DS415: Activity Name: Interior - L3 TCP/MSB - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on DZ415: Activity Name: Interior - L3 UPS - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 11-Apr-2025 End Date: 24-Apr-2025
Note on EL416: Activity Name: Interior - L3 PDUs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 23-Apr-2025 End Date: 29-Apr-2025
Note on CU420: Activity Name: Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on CU421: Activity Name: Termination at PDU & Busway - COLO2 Cell 2 - DH Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on CU422: Activity Name: Finishes and Signage - COLO2 Cell 2 - DH Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on CN423: Activity Name: Finishes and Signage - COLO2 Cell 2 - ER Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on DA423: Activity Name: Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on BR425: Activity Name: Install ceiling and Light Fittings - COLO2 Cell 2 - MG Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 10-Feb-2025 End Date: 21-Feb-2025
Note on CF425: Activity Name: Trim out MEP - COLO2 Cell 2 - MG Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 24-Feb-2025 End Date: 14-Mar-2025
Note on DA427: Activity Name: Interior - L2 TCP/MSB - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on DH427: Activity Name: Interior - L2 UPS - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DH428: Activity Name: Interior - L2 PDUs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DH429: Activity Name: Interior - L2 ADP - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DL430: Activity Name: Interior - L2 ATSs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on DL431: Activity Name: Interior - L2 AHUs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on DL432: Activity Name: Interior - L2 Busway - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on BT433: Activity Name: Interior - L3 ATSs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 12-Feb-2025 End Date: 25-Feb-2025
Note on CH433: Activity Name: Interior - L3 AHUs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 26-Feb-2025 End Date: 27-Feb-2025
Note on CJ433: Activity Name: Interior - L3 Busway - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 28-Feb-2025 End Date: 11-Mar-2025
Note on DS433: Activity Name: Interior - L3 TCP/MSB - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on EE433: Activity Name: Interior - L3 ADP - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 16-Apr-2025 End Date: 22-Apr-2025
Note on DS434: Activity Name: Interior - L3 UPS - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on DS435: Activity Name: Interior - L3 PDUs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 04-Apr-2025 End Date: 17-Apr-2025
Note on CT438: Activity Name: Termination at PDU & Busway - COLO2 Cell 3 - DH Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on DA438: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on DA439: Activity Name: Finishes and Signage - COLO2 Cell 3 - DH Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on CF441: Activity Name: Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 24-Feb-2025 End Date: 14-Mar-2025
Note on DO441: Activity Name: Finishes and Signage - COLO2 Cell 3 - ER Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on BN443: Activity Name: Pipe Testing - COLO2 Cell 3 - MG Phase: COLO 2 Location: Cell 3 Trade: Inspections Start Date: 06-Feb-2025 End Date: 26-Feb-2025
Note on DH443: Activity Name: Install ceiling and Light Fittings - COLO2 Cell 3 - MG Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on BY444: Activity Name: Trim out MEP - COLO2 Cell 3 - MG Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 17-Feb-2025 End Date: 28-Feb-2025
Note on AQ446: Activity Name: Interior - L2 TCP/MSB - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on DD446: Activity Name: Interior - L2 ADP - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 20-Mar-2025 End Date: 26-Mar-2025
Note on DK446: Activity Name: Interior - L2 ATSs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 27-Mar-2025 End Date: 02-Apr-2025
Note on AQ447: Activity Name: Interior - L2 UPS - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on DH447: Activity Name: Interior - L2 Busway - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DO447: Activity Name: Interior - L2 AHUs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on AQ448: Activity Name: Interior - L2 PDUs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on DH450: Activity Name: Interior - L3 TCP/MSB - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DR450: Activity Name: Interior - L3 ADP - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 03-Apr-2025 End Date: 09-Apr-2025
Note on DZ450: Activity Name: Interior - L3 Busway - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 11-Apr-2025 End Date: 17-Apr-2025
Note on DH451: Activity Name: Interior - L3 PDUs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DS451: Activity Name: Interior - L3 AHUs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on DL452: Activity Name: Interior - L3 ATSs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on DV452: Activity Name: Interior - L3 UPS - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on CM454: Activity Name: Finishes and Signage - COLO2 Cell 4 - DH Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on DA454: Activity Name: Termination at PDU & Busway - COLO2 Cell 4 - DH Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 17-Mar-2025 End Date: 04-Apr-2025
Note on EC454: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on CM457: Activity Name: Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 03-Mar-2025 End Date: 21-Mar-2025
Note on DV457: Activity Name: Connect to Cable tray and conduit equipment - COLO2 Cell 4 - ER Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on CT458: Activity Name: Finishes and Signage - COLO2 Cell 4 - ER Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 10-Mar-2025 End Date: 21-Mar-2025
Note on AJ460: Activity Name: Pipe Testing - COLO2 Cell 4 - MG Phase: COLO 2 Location: Cell 4 Trade: Inspections Start Date: 07-Jan-2025 End Date: 13-Jan-2025
Note on CI460: Activity Name: Trim out MEP - COLO2 Cell 4 - MG Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 27-Feb-2025 End Date: 19-Mar-2025
Note on AL461: Activity Name: Install ceiling and Light Fittings - COLO2 Cell 4 - MG Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 09-Jan-2025 End Date: 15-Jan-2025
Note on CV461: Activity Name: Piping and Electrical Termination to AHUs - COLO2 Cell 4 - MG Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025

## CFA - Legends
COLO 3 |  | COLO 4 |  | COLO 5 |  | CX Level 3 |  | Yardwork |  | CX Level 2 |  | COLO 2
[6 empty] | EE56 | EPMS/BAS Turn-Up | RC1 | Install screen wall - Colo 2 - North | EE49 | L2 GEN - COLO2
Inspections |  | Inspections |  | Inspections |  |  |  | EE35 | Wire pulling and termination for TCP/MSB - Colo 2 - South |  |  | Inspections
I-R | Pipe Testing - COLO3 Cell 2 - MG | I-R | Pipe Testing - COLO4 Cell 1 - MG | I-R | Pipe Testing - COLO5 Cell 3 - MG | [6 empty] | I-R | Pipe Testing - COLO2 Cell 3 - MG
N/A |  | N/A |  | N/A | [7 empty] | N/A
MS1 | Level 4 Cx - Colo 3 | MS1 | Level 4 Cx - Colo 4 | MS1 | Level 4 Cx - Colo 5 | [6 empty] | MS2 | Level 5 Cx / IST - Colo 2
J36 | Door Frame Installation - COLO3 Cell 1 - ER | W4 | Closing Construction Access Door - COLO4 Cell 4 - DH | W4 | Closing Construction Access Door - COLO5 Cell 4 - DH | [6 empty] | ET7 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH
GH3 | Install DX Split Units - COLO3 Cell 2 - ER | J7 | Ceiling Grid and Tile - COLO4 Cell 1 - DH | ET7 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH | [6 empty] | ALL3 | Finishes and Signage - COLO2 Cell 1 - DH
GA6 | Placing the AHU - COLO3 Cell 2 - MG | GH3 | Install DX Split Units - COLO4 Cell 1 - ER | ALL3 | Finishes and Signage - COLO5 Cell 1 - DH | [6 empty] | EE57 | Interior - L2 TCP/MSB - COLO2 Cell 1
T3 | Install Walls and Primer Paint - COLO3 Cell 4 - MG | GA6 | Placing the AHU - COLO4 Cell 1 - MG | EE57 | Interior - L2 TCP/MSB - COLO5 Cell 1
ET7 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH | T3 | Install Walls and Primer Paint - COLO4 Cell 2 - MG
ALL3 | Finishes and Signage - COLO3 Cell 1 - DH | ET22 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH
S2 | HAC install and Rise - COLO3 Cell 1 - DH | ALL3 | Finishes and Signage - COLO4 Cell 1 - DH
EE63 | Interior - L1 PDUs - COLO3 Cell 1 | S1 | Begin HAC Assembly - COLO4 Cell 1 - DH
|  | EE57 | Interior - L1 TCP/MSB - COLO4 Cell 1