## Sheet1
Phase | Location | Zone | Trade | Activity Name | Color | Activity Code | Start | Finish
Yardwork | COLO 2 | South | Gurtz Electric | Wire pulling and termination for TCP/MSB - Colo 2 - South | #FFFDA5 | EE35 | 2024-12-27 | 2025-01-31
Yardwork | COLO 2 | South | Ralph Simpson & Crown Core | Install screen wall - Colo 2 - South | #D9D9D9 | RC1 | 2024-11-11 | 2025-03-07
Yardwork | COLO 2 | North | Ralph Simpson & Crown Core | Install screen wall - Colo 2 - North | #D9D9D9 | RC1 | 2025-02-10 | 2025-03-07
Yardwork | COLO 5 | East | Ralph Simpson & Crown Core | Install screen wall - Colo 5 - East | #D9D9D9 | RC1 | 2024-11-11 | 2025-01-31
Yardwork | COLO 5 | West | Gurtz Electric | Install Generator Muffler - Colo 5 - West | #FFFDA5 | EE34 | 2025-01-17 | 2025-01-21
Yardwork | COLO 5 | West | Ralph Simpson & Crown Core | Install screen wall - Colo 5 - West | #D9D9D9 | RC1 | 2025-02-03 | 2025-02-28
Yardwork | COLO 3 | South | Gurtz Electric | Pull & Terminate Underground Cables (UMS to UPM to XMFR) | #FFFDA5 | EE46 | 2025-01-17 | 2025-02-06
Yardwork | COLO 3 | South | Ralph Simpson & Crown Core | Install screen wall - Colo 3 - South | #D9D9D9 | RC1 | 2024-12-30 | 2025-02-28
Yardwork | COLO 3 | North | Gurtz Electric | Wire pulling and termination for TCP/MSB - Colo 3 - North | #FFFDA5 | EE35 | 2024-12-27 | 2025-01-31
Yardwork | COLO 3 | North | Gurtz Electric | Pull & Terminate Underground Cables (UMS to UPM to XMFR) | #FFFDA5 | EE46 | 2025-01-17 | 2025-02-13
Yardwork | COLO 3 | North | Ralph Simpson & Crown Core | Install screen wall - Colo 3 - North | #D9D9D9 | RC1 | 2024-12-30 | 2025-02-28
Yardwork | COLO 4 | South | Gurtz Electric | Wire pulling and termination for TCP/MSB - Colo 4 - South | #FFFDA5 | EE46 | 2024-12-27 | 2025-01-31
Yardwork | COLO 4 | South | Gurtz Electric | Pull & Terminate Underground Cables (UMS to UPM to XMFR) | #FFFDA5 | EE46 | 2025-02-14 | 2025-03-13
Yardwork | COLO 4 | South | Ralph Simpson & Crown Core | Install screen wall - Colo 4 - South | #D9D9D9 | RC1 | 2025-03-03 | 2025-03-28
Yardwork | COLO 4 | North | Gurtz Electric | Wire pulling and termination for TCP/MSB - Colo 4 - North | #FFFDA5 | EE35 | 2024-12-27 | 2025-01-31
Yardwork | COLO 4 | North | Gurtz Electric | Pull & Terminate Underground Cables (UMS to UPM to XMFR) | #FFFDA5 | EE46 | 2025-02-14 | 2025-03-13
Yardwork | COLO 4 | North | Ralph Simpson & Crown Core | Install screen wall - Colo 4 - North | #D9D9D9 | RC1 | 2025-03-03 | 2025-03-28
CX Level 2 | Site | Site | Gurtz Electric | L2 UTS / UTSR - Site | #FFFDA5 | EE47 | 2025-02-03 | 2025-02-10
CX Level 2 | COLO 2 | COLO 2 | Gurtz Electric | L2 XFMR - COLO2 | #FFFDA5 | EE48 | 2025-02-11 | 2025-03-10
CX Level 2 | COLO 2 | COLO 2 | Gurtz Electric | L2 GEN - COLO2 | #FFFDA5 | EE49 | 2025-02-11 | 2025-03-10
CX Level 2 | COLO 2 | COLO 2 | Gurtz Electric | L2 UPM - COLO2 | #FFFDA5 | EE50 | 2025-02-12 | 2025-03-11
CX Level 2 | COLO 5 | COLO 5 | Gurtz Electric | L2 UMS 01 - COLO 5 | #FFFDA5 | EE51 | 2025-02-11 | 2025-02-17
CX Level 2 | COLO 5 | COLO 5 | Gurtz Electric | L2 UMS 02 - COLO 5 | #FFFDA5 | EE52 | 2025-02-18 | 2025-02-24
CX Level 2 | COLO 5 | COLO 5 | Gurtz Electric | L2 URS 01 - COLO 5 | #FFFDA5 | EE53 | 2025-03-11 | 2025-03-17
CX Level 2 | COLO 5 | COLO 5 | Gurtz Electric | L2 XFMR - COLO5 | #FFFDA5 | EE48 | 2025-03-11 | 2025-04-07
CX Level 2 | COLO 5 | COLO 5 | Gurtz Electric | L2 GEN - COLO5 | #FFFDA5 | EE49 | 2025-03-11 | 2025-04-07
CX Level 2 | COLO 5 | COLO 5 | Gurtz Electric | L2 UPM - COLO5 (UPM ROJ Driving) | #FFFDA5 | EE50 | 2025-06-25 | 2025-07-23
CX Level 2 | COLO 3 | COLO 3 | Gurtz Electric | L2 UMS 03 - COLO 3 | #FFFDA5 | EE54 | 2025-02-25 | 2025-03-03
CX Level 2 | COLO 3 | COLO 3 | Gurtz Electric | L2 UMS 04 - COLO 3 | #FFFDA5 | EE55 | 2025-03-04 | 2025-03-10
CX Level 2 | COLO 3 | COLO 3 | Gurtz Electric | L2 XFMR - COLO3 | #FFFDA5 | EE48 | 2025-04-08 | 2025-05-05
CX Level 2 | COLO 3 | COLO 3 | Gurtz Electric | L2 GEN - COLO3 | #FFFDA5 | EE49 | 2025-04-08 | 2025-05-05
CX Level 2 | COLO 3 | COLO 3 | Gurtz Electric | L2 UPM - COLO3 (UPM ROJ Driving) | #FFFDA5 | EE50 | 2025-07-07 | 2025-08-01
CX Level 2 | COLO 4 | COLO 4 | Gurtz Electric | L2 XFMR - COLO4 | #FFFDA5 | EE48 | 2025-05-06 | 2025-06-03
CX Level 2 | COLO 4 | COLO 4 | Gurtz Electric | L2 GEN - COLO4 | #FFFDA5 | EE49 | 2025-05-06 | 2025-06-03
CX Level 2 | COLO 4 | COLO 4 | Gurtz Electric | L2 UPM - COLO4 (UPM ROJ Driving) | #FFFDA5 | EE50 | 2025-07-16 | 2025-08-12
CX Level 3 | Site | Site | Gurtz Electric | L3 UTS / UTSR - Site | #FFFDA5 | EE47 | 2025-03-14 | 2025-03-20
CX Level 3 | COLO 2 | Cell 1 | Gurtz Electric | L3 GEN - Colo 2 Cell 1 | #FFFDA5 | EE49 | 2025-03-14 | 2025-03-20
CX Level 3 | COLO 2 | Cell 2 | Gurtz Electric | L3 GEN - Colo 2 Cell 2 | #FFFDA5 | EE49 | 2025-03-14 | 2025-03-20
CX Level 3 | COLO 2 | Cell 3 | Gurtz Electric | L3 GEN - Colo 2 Cell 3 | #FFFDA5 | EE49 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 2 | All | Gurtz Electric | EPMS/BAS Turn-Up | #FFFDA5 | EE56 | 2025-03-28 | 2025-03-28
CX Level 3 | COLO 2 | Cell 1 | Gurtz Electric | L3 UPM - Colo 2 Cell 1 | #FFFDA5 | EE50 | 2025-03-28 | 2025-04-03
CX Level 3 | COLO 2 | Cell 4 | Gurtz Electric | L3 GEN - Colo 2 Cell 4 | #FFFDA5 | EE49 | 2025-03-28 | 2025-04-03
CX Level 3 | COLO 2 | Cell 2 | Gurtz Electric | L3 UPM - Colo 2 Cell 2 | #FFFDA5 | EE50 | 2025-03-28 | 2025-04-03
CX Level 3 | COLO 2 | Cell 3 | Gurtz Electric | L3 UPM - Colo 2 Cell 3 | #FFFDA5 | EE50 | 2025-03-28 | 2025-04-03
CX Level 3 | COLO 2 | Cell 4 | Gurtz Electric | L3 UPM - Colo 2 Cell 4 | #FFFDA5 | EE50 | 2025-03-28 | 2025-04-03
CX Level 3 | COLO 2 | Cell 1 | Gurtz Electric | L3 XFMR - Colo 2 Cell 1 | #FFFDA5 | EE48 | 2025-04-04 | 2025-04-10
CX Level 3 | COLO 2 | Cell 2 | Gurtz Electric | L3 XFMR - Colo 2 Cell 2 | #FFFDA5 | EE48 | 2025-04-04 | 2025-04-10
CX Level 3 | COLO 2 | Cell 3 | Gurtz Electric | L3 XFMR - Colo 2 Cell 3 | #FFFDA5 | EE48 | 2025-04-04 | 2025-04-10
CX Level 3 | COLO 2 | Cell 4 | Gurtz Electric | L3 XFMR - Colo 2 Cell 4 | #FFFDA5 | EE48 | 2025-04-04 | 2025-04-10
CX Level 3 | COLO 5 | All | Gurtz Electric | L3 URS 01 - COLO 5 | #FFFDA5 | EE53 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 5 | All | Gurtz Electric | L3 UMS 01 - COLO 5 | #FFFDA5 | EE51 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 5 | All | Gurtz Electric | L3 UMS 02 - COLO 5 | #FFFDA5 | EE52 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 5 | All | Gurtz Electric | EPMS/BAS Turn-Up | #FFFDA5 | EE56 | 2025-04-11 | 2025-04-11
CX Level 3 | COLO 5 | Cell 1 | Gurtz Electric | L3 GEN - Cell 1 | #FFFDA5 | EE49 | 2025-04-08 | 2025-04-14
CX Level 3 | COLO 5 | Cell 2 | Gurtz Electric | L3 GEN - Cell 2 | #FFFDA5 | EE49 | 2025-04-15 | 2025-04-21
CX Level 3 | COLO 5 | Cell 3 | Gurtz Electric | L3 GEN - Cell 3 | #FFFDA5 | EE49 | 2025-04-22 | 2025-04-28
CX Level 3 | COLO 5 | Cell 4 | Gurtz Electric | L3 GEN - Cell 4 | #FFFDA5 | EE49 | 2025-04-29 | 2025-05-05
CX Level 3 | COLO 5 | Cell 1 | Gurtz Electric | L3 UPM - Cell 1 | #FFFDA5 | EE50 | 2025-07-24 | 2025-07-30
CX Level 3 | COLO 5 | Cell 2 | Gurtz Electric | L3 UPM - Cell 2 | #FFFDA5 | EE50 | 2025-07-24 | 2025-07-30
CX Level 3 | COLO 5 | Cell 1 | Gurtz Electric | L3 XFMR - Cell 1 | #FFFDA5 | EE48 | 2025-07-31 | 2025-08-06
CX Level 3 | COLO 5 | Cell 3 | Gurtz Electric | L3 UPM - Cell 3 | #FFFDA5 | EE50 | 2025-07-31 | 2025-08-06
CX Level 3 | COLO 5 | Cell 4 | Gurtz Electric | L3 UPM - Cell 4 | #FFFDA5 | EE50 | 2025-07-31 | 2025-08-06
CX Level 3 | COLO 5 | Cell 2 | Gurtz Electric | L3 XFMR - Cell 2 | #FFFDA5 | EE48 | 2025-07-31 | 2025-08-06
CX Level 3 | COLO 5 | Cell 3 | Gurtz Electric | L3 XFMR - Cell 3 | #FFFDA5 | EE48 | 2025-08-07 | 2025-08-13
CX Level 3 | COLO 5 | Cell 4 | Gurtz Electric | L3 XFMR - Cell 4 | #FFFDA5 | EE48 | 2025-08-07 | 2025-08-13
CX Level 3 | COLO 3 | All | Gurtz Electric | L3 UMS 04 - COLO 3 | #FFFDA5 | EE55 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 3 | All | Gurtz Electric | L3 UMS 03 - COLO 3 | #FFFDA5 | EE54 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 3 | All | Gurtz Electric | EPMS/BAS Turn-Up | #FFFDA5 | EE56 | 2025-04-11 | 2025-04-11
CX Level 3 | COLO 3 | Cell 2 | Gurtz Electric | L3 GEN - Cell 2 | #FFFDA5 | EE49 | 2025-05-06 | 2025-05-12
CX Level 3 | COLO 3 | Cell 3 | Gurtz Electric | L3 GEN - Cell 3 | #FFFDA5 | EE49 | 2025-05-06 | 2025-05-12
CX Level 3 | COLO 3 | Cell 4 | Gurtz Electric | L3 GEN - Cell 4 | #FFFDA5 | EE49 | 2025-05-06 | 2025-05-12
CX Level 3 | COLO 3 | Cell 1 | Gurtz Electric | L3 GEN - Cell 1 | #FFFDA5 | EE49 | 2025-05-07 | 2025-05-13
CX Level 3 | COLO 3 | Cell 1 | Gurtz Electric | L3 UPM - Cell 1 | #FFFDA5 | EE50 | 2025-08-04 | 2025-08-08
CX Level 3 | COLO 3 | Cell 2 | Gurtz Electric | L3 UPM - Cell 2 | #FFFDA5 | EE50 | 2025-08-04 | 2025-08-08
CX Level 3 | COLO 3 | Cell 1 | Gurtz Electric | L3 XFMR - Cell 1 | #FFFDA5 | EE48 | 2025-08-11 | 2025-08-15
CX Level 3 | COLO 3 | Cell 3 | Gurtz Electric | L3 UPM - Cell 3 | #FFFDA5 | EE50 | 2025-08-11 | 2025-08-15
CX Level 3 | COLO 3 | Cell 4 | Gurtz Electric | L3 UPM - Cell 4 | #FFFDA5 | EE50 | 2025-08-11 | 2025-08-15
CX Level 3 | COLO 3 | Cell 2 | Gurtz Electric | L3 XFMR - Cell 2 | #FFFDA5 | EE48 | 2025-08-11 | 2025-08-15
CX Level 3 | COLO 3 | Cell 3 | Gurtz Electric | L3 XFMR - Cell 3 | #FFFDA5 | EE48 | 2025-08-18 | 2025-08-22
CX Level 3 | COLO 3 | Cell 4 | Gurtz Electric | L3 XFMR - Cell 4 | #FFFDA5 | EE48 | 2025-08-18 | 2025-08-22
CX Level 3 | COLO 4 | All | Gurtz Electric | EPMS/BAS Turn-Up | #FFFDA5 | EE56 | 2025-04-25 | 2025-04-25
CX Level 3 | COLO 4 | Cell 1 | Gurtz Electric | L3 GEN - Cell 1 | #FFFDA5 | EE49 | 2025-06-04 | 2025-06-10
CX Level 3 | COLO 4 | Cell 2 | Gurtz Electric | L3 GEN - Cell 2 | #FFFDA5 | EE49 | 2025-06-11 | 2025-06-17
CX Level 3 | COLO 4 | Cell 3 | Gurtz Electric | L3 GEN - Cell 3 | #FFFDA5 | EE49 | 2025-06-18 | 2025-06-24
CX Level 3 | COLO 4 | Cell 4 | Gurtz Electric | L3 GEN - Cell 4 | #FFFDA5 | EE49 | 2025-06-25 | 2025-07-01
CX Level 3 | COLO 4 | Cell 1 | Gurtz Electric | L3 UPM - Cell 1 | #FFFDA5 | EE50 | 2025-08-25 | 2025-08-29
CX Level 3 | COLO 4 | Cell 2 | Gurtz Electric | L3 UPM - Cell 2 | #FFFDA5 | EE50 | 2025-08-25 | 2025-08-29
CX Level 3 | COLO 4 | Cell 1 | Gurtz Electric | L3 XFMR - Cell 1 | #FFFDA5 | EE48 | 2025-09-02 | 2025-09-08
CX Level 3 | COLO 4 | Cell 3 | Gurtz Electric | L3 UPM - Cell 3 | #FFFDA5 | EE50 | 2025-09-02 | 2025-09-08
CX Level 3 | COLO 4 | Cell 4 | Gurtz Electric | L3 UPM - Cell 4 | #FFFDA5 | EE50 | 2025-09-02 | 2025-09-08
CX Level 3 | COLO 4 | Cell 2 | Gurtz Electric | L3 XFMR - Cell 2 | #FFFDA5 | EE48 | 2025-09-02 | 2025-09-08
CX Level 3 | COLO 4 | Cell 3 | Gurtz Electric | L3 XFMR - Cell 3 | #FFFDA5 | EE48 | 2025-09-09 | 2025-09-15
CX Level 3 | COLO 4 | Cell 4 | Gurtz Electric | L3 XFMR - Cell 4 | #FFFDA5 | EE48 | 2025-09-09 | 2025-09-15
COLO 2 | Cell 1 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | #FFFDA5 | EE29 | 2025-01-03 | 2025-01-31
COLO 2 | Cell 1 | Electrical Room | All Trades | Finishes and Signage - COLO2 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-02-03 | 2025-02-07
COLO 2 | Cell 1 | Data Hall | Gurtz Electric | Cable Pulling at PDU to Busway & MSB - COLO2 Cell 1 - DH | #FFFDA5 | EE17 | 2025-01-03 | 2025-01-31
COLO 2 | Cell 1 | Data Hall | Gurtz Electric | Termination at PDU to Busway & MSB- COLO2 Cell 1 - DH | #FFFDA5 | EE18 | 2025-01-10 | 2025-02-07
COLO 2 | Cell 1 | Data Hall | All Trades | Finishes and Signage - COLO2 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO2 Cell 1 | #FFFDA5 | EE57 | 2025-02-03 | 2025-02-07
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO2 Cell 1 | #FFFDA5 | EE58 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO2 Cell 1 | #FFFDA5 | EE59 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO2 Cell 1 | #FFFDA5 | EE60 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO2 Cell 1 | #FFFDA5 | EE61 | 2025-02-24 | 2025-02-28
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO2 Cell 1 | #FFFDA5 | EE62 | 2025-03-12 | 2025-03-18
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO2 Cell 1 | #FFFDA5 | EE63 | 2025-03-12 | 2025-03-18
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO2 Cell 1 | #FFFDA5 | EE57 | 2025-04-08 | 2025-04-14
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO2 Cell 1 | #FFFDA5 | EE62 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO2 Cell 1 | #FFFDA5 | EE63 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO2 Cell 1 | #FFFDA5 | EE58 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO2 Cell 1 | #FFFDA5 | EE60 | 2025-04-22 | 2025-04-28
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO2 Cell 1 | #FFFDA5 | EE59 | 2025-04-29 | 2025-05-12
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO2 Cell 1 | #FFFDA5 | EE61 | 2025-05-13 | 2025-05-19
COLO 2 | Cell 2 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | #FFFDA5 | EE35 | 2025-01-10 | 2025-01-21
COLO 2 | Cell 2 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO2 Cell 2 - MG | #FFFDA5 | EE36 | 2025-01-22 | 2025-01-28
COLO 2 | Cell 2 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | #FFFDA5 | EE29 | 2025-01-03 | 2025-01-31
COLO 2 | Cell 2 | Electrical Room | All Trades | Finishes and Signage - COLO2 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 2 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH | #FFFDA5 | EE17 | 2025-01-03 | 2025-01-23
COLO 2 | Cell 2 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO2 Cell 2 - DH | #FFFDA5 | EE18 | 2025-01-24 | 2025-02-13
COLO 2 | Cell 2 | Data Hall | All Trades | Finishes and Signage - COLO2 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO2 Cell 2 | #FFFDA5 | EE57 | 2025-02-03 | 2025-02-07
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO2 Cell 2 | #FFFDA5 | EE62 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO2 Cell 2 | #FFFDA5 | EE63 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO2 Cell 2 | #FFFDA5 | EE58 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO2 Cell 2 | #FFFDA5 | EE60 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO2 Cell 2 | #FFFDA5 | EE59 | 2025-02-24 | 2025-02-28
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO2 Cell 2 | #FFFDA5 | EE61 | 2025-03-03 | 2025-03-07
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO2 Cell 2 | #FFFDA5 | EE57 | 2025-04-08 | 2025-04-14
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO2 Cell 2 | #FFFDA5 | EE62 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO2 Cell 2 | #FFFDA5 | EE63 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO2 Cell 2 | #FFFDA5 | EE58 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO2 Cell 2 | #FFFDA5 | EE60 | 2025-04-22 | 2025-04-28
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO2 Cell 2 | #FFFDA5 | EE59 | 2025-04-29 | 2025-05-12
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO2 Cell 2 | #FFFDA5 | EE61 | 2025-05-13 | 2025-05-19
COLO 2 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO2 Cell 3 - MG | #C00000 | I-R | 2025-01-17 | 2025-01-20
COLO 2 | Cell 3 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO2 Cell 3 - MG | #FFFDA5 | EE35 | 2025-01-22 | 2025-01-31
COLO 2 | Cell 3 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO2 Cell 3 - MG | #FFFDA5 | EE36 | 2025-02-03 | 2025-02-07
COLO 2 | Cell 3 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER | #FFFDA5 | EE29 | 2025-01-10 | 2025-01-30
COLO 2 | Cell 3 | Electrical Room | All Trades | Finishes and Signage - COLO2 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-01-28 | 2025-02-03
COLO 2 | Cell 3 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO2 Cell 3 - DH | #FFFDA5 | EE18 | 2025-01-10 | 2025-01-30
COLO 2 | Cell 3 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH | #EF9E5B | ET7 | 2025-01-17 | 2025-01-30
COLO 2 | Cell 3 | Data Hall | All Trades | Finishes and Signage - COLO2 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-02-24 | 2025-02-28
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO2 Cell 3 | #FFFDA5 | EE57 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO2 Cell 3 | #FFFDA5 | EE62 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO2 Cell 3 | #FFFDA5 | EE63 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO2 Cell 3 | #FFFDA5 | EE58 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO2 Cell 3 | #FFFDA5 | EE60 | 2025-02-24 | 2025-02-28
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO2 Cell 3 | #FFFDA5 | EE59 | 2025-03-03 | 2025-03-07
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO2 Cell 3 | #FFFDA5 | EE61 | 2025-03-03 | 2025-03-07
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO2 Cell 3 | #FFFDA5 | EE57 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO2 Cell 3 | #FFFDA5 | EE62 | 2025-04-22 | 2025-04-28
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO2 Cell 3 | #FFFDA5 | EE63 | 2025-04-22 | 2025-04-28
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO2 Cell 3 | #FFFDA5 | EE58 | 2025-04-22 | 2025-04-28
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO2 Cell 3 | #FFFDA5 | EE60 | 2025-04-29 | 2025-05-05
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO2 Cell 3 | #FFFDA5 | EE59 | 2025-05-06 | 2025-05-19
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO2 Cell 3 | #FFFDA5 | EE61 | 2025-05-20 | 2025-05-27
COLO 2 | Cell 4 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO2 Cell 4 - MG | #EF9E5B | ET22 | 2025-01-17 | 2025-01-30
COLO 2 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO2 Cell 4 - MG | #C00000 | I-R | 2025-01-31 | 2025-02-03
COLO 2 | Cell 4 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO2 Cell 4 - MG | #FFFDA5 | EE35 | 2025-02-04 | 2025-02-13
COLO 2 | Cell 4 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO2 Cell 4 - MG | #FFFDA5 | EE36 | 2025-02-14 | 2025-02-20
COLO 2 | Cell 4 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO2 Cell 4 - ER | #FFFDA5 | EE28 | 2025-01-14 | 2025-01-20
COLO 2 | Cell 4 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER | #FFFDA5 | EE29 | 2025-01-31 | 2025-02-20
COLO 2 | Cell 4 | Electrical Room | All Trades | Finishes and Signage - COLO2 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-02-21 | 2025-02-27
COLO 2 | Cell 4 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO2 Cell 4 - DH | #FFFDA5 | EE18 | 2025-01-10 | 2025-01-30
COLO 2 | Cell 4 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH | #EF9E5B | ET7 | 2025-01-31 | 2025-02-13
COLO 2 | Cell 4 | Data Hall | All Trades | Finishes and Signage - COLO2 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-03-03 | 2025-03-07
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO2 Cell 4 | #FFFDA5 | EE57 | 2025-02-21 | 2025-02-27
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO2 Cell 4 | #FFFDA5 | EE62 | 2025-02-28 | 2025-03-06
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO2 Cell 4 | #FFFDA5 | EE63 | 2025-02-28 | 2025-03-06
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO2 Cell 4 | #FFFDA5 | EE58 | 2025-02-28 | 2025-03-06
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO2 Cell 4 | #FFFDA5 | EE60 | 2025-03-07 | 2025-03-13
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO2 Cell 4 | #FFFDA5 | EE59 | 2025-03-10 | 2025-03-14
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO2 Cell 4 | #FFFDA5 | EE61 | 2025-03-10 | 2025-03-14
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO2 Cell 4 | #FFFDA5 | EE57 | 2025-04-22 | 2025-04-28
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO2 Cell 4 | #FFFDA5 | EE62 | 2025-04-29 | 2025-05-05
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO2 Cell 4 | #FFFDA5 | EE63 | 2025-04-29 | 2025-05-05
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO2 Cell 4 | #FFFDA5 | EE58 | 2025-05-06 | 2025-05-12
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO2 Cell 4 | #FFFDA5 | EE60 | 2025-05-13 | 2025-05-19
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO2 Cell 4 | #FFFDA5 | EE59 | 2025-05-13 | 2025-05-27
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO2 Cell 4 | #FFFDA5 | EE61 | 2025-05-28 | 2025-06-03
COLO 2 | All | CX - Microsoft | Microsoft | Level 4 Cx - Colo 2 | #000000 | MS1 | 2025-06-04 | 2025-07-01
COLO 2 | All | CX - Microsoft | Microsoft | Level 5 Cx / IST - Colo 2 | #000000 | MS2 | 2025-07-02 | 2025-07-03
COLO 5 | Cell 1 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO5 Cell 1 - MG | #FFFDA5 | EE36 | 2025-01-17 | 2025-01-23
COLO 5 | Cell 1 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER | #FFFDA5 | EE29 | 2024-12-31 | 2025-01-31
COLO 5 | Cell 1 | Electrical Room | All Trades | Finishes and Signage - COLO5 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-01-29 | 2025-02-04
COLO 5 | Cell 1 | Data Hall | Gurtz Electric | Termination at PDU & Busway- COLO5 Cell 1 - DH | #FFFDA5 | EE18 | 2025-01-17 | 2025-02-06
COLO 5 | Cell 1 | Data Hall | All Trades | Finishes and Signage - COLO5 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-02-07 | 2025-02-13
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO5 Cell 1 | #FFFDA5 | EE57 | 2025-03-17 | 2025-03-21
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO5 Cell 1 | #FFFDA5 | EE62 | 2025-03-24 | 2025-03-28
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO5 Cell 1 | #FFFDA5 | EE58 | 2025-03-24 | 2025-03-28
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO5 Cell 1 | #FFFDA5 | EE63 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO5 Cell 1 | #FFFDA5 | EE59 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO5 Cell 1 | #FFFDA5 | EE60 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO5 Cell 1 | #FFFDA5 | EE61 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO5 Cell 1 | #FFFDA5 | EE57 | 2025-08-04 | 2025-08-08
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO5 Cell 1 | #FFFDA5 | EE63 | 2025-08-04 | 2025-08-08
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO5 Cell 1 | #FFFDA5 | EE62 | 2025-08-11 | 2025-08-15
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO5 Cell 1 | #FFFDA5 | EE58 | 2025-08-11 | 2025-08-15
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO5 Cell 1 | #FFFDA5 | EE60 | 2025-08-18 | 2025-08-22
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO5 Cell 1 | #FFFDA5 | EE59 | 2025-08-13 | 2025-08-26
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO5 Cell 1 | #FFFDA5 | EE61 | 2025-08-25 | 2025-08-29
COLO 5 | Cell 2 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO5 Cell 2 - MG | #FFFDA5 | EE35 | 2025-01-10 | 2025-01-21
COLO 5 | Cell 2 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO5 Cell 2 - MG | #FFFDA5 | EE36 | 2025-01-24 | 2025-01-30
COLO 5 | Cell 2 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER | #FFFDA5 | EE29 | 2025-01-21 | 2025-02-03
COLO 5 | Cell 2 | Electrical Room | All Trades | Finishes and Signage - COLO5 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-02-14 | 2025-02-20
COLO 5 | Cell 2 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH | #FFFDA5 | EE18 | 2025-01-17 | 2025-01-30
COLO 5 | Cell 2 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH | #EF9E5B | ET7 | 2025-01-17 | 2025-01-30
COLO 5 | Cell 2 | Data Hall | Gurtz Electric | Termination at PDU & Busway- COLO5 Cell 2 - DH | #FFFDA5 | EE19 | 2025-01-31 | 2025-02-20
COLO 5 | Cell 2 | Data Hall | All Trades | Finishes and Signage - COLO5 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-02-21 | 2025-02-27
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO5 Cell 2 | #FFFDA5 | EE57 | 2025-03-24 | 2025-03-28
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO5 Cell 2 | #FFFDA5 | EE62 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO5 Cell 2 | #FFFDA5 | EE63 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO5 Cell 2 | #FFFDA5 | EE58 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO5 Cell 2 | #FFFDA5 | EE59 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO5 Cell 2 | #FFFDA5 | EE60 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO5 Cell 2 | #FFFDA5 | EE61 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO5 Cell 2 | #FFFDA5 | EE57 | 2025-08-07 | 2025-08-13
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO5 Cell 2 | #FFFDA5 | EE63 | 2025-08-07 | 2025-08-13
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO5 Cell 2 | #FFFDA5 | EE58 | 2025-08-07 | 2025-08-13
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO5 Cell 2 | #FFFDA5 | EE62 | 2025-08-14 | 2025-08-20
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO5 Cell 2 | #FFFDA5 | EE60 | 2025-08-14 | 2025-08-20
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO5 Cell 2 | #FFFDA5 | EE59 | 2025-08-21 | 2025-09-04
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO5 Cell 2 | #FFFDA5 | EE61 | 2025-09-03 | 2025-09-09
COLO 5 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO5 Cell 3 - MG | #C00000 | I-R | 2025-01-17 | 2025-01-20
COLO 5 | Cell 3 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO5 Cell 3 - MG | #FFFDA5 | EE35 | 2025-01-22 | 2025-01-31
COLO 5 | Cell 3 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO5 Cell 3 - MG | #FFFDA5 | EE36 | 2025-02-03 | 2025-02-07
COLO 5 | Cell 3 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO5 Cell 3 - ER | #FFFDA5 | EE28 | 2025-01-14 | 2025-01-20
COLO 5 | Cell 3 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER | #FFFDA5 | EE18 | 2025-01-21 | 2025-02-03
COLO 5 | Cell 3 | Electrical Room | All Trades | Finishes and Signage - COLO5 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-02-28 | 2025-03-06
COLO 5 | Cell 3 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO5 Cell 3 - DH | #FFFDA5 | EE17 | 2025-01-10 | 2025-01-23
COLO 5 | Cell 3 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO5 Cell 3 - DH | #FFFDA5 | EE18 | 2025-01-31 | 2025-02-20
COLO 5 | Cell 3 | Data Hall | All Trades | Finishes and Signage - COLO5 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-03-07 | 2025-03-13
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO5 Cell 3 | #FFFDA5 | EE57 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO5 Cell 3 | #FFFDA5 | EE62 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO5 Cell 3 | #FFFDA5 | EE63 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO5 Cell 3 | #FFFDA5 | EE58 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO5 Cell 3 | #FFFDA5 | EE59 | 2025-04-14 | 2025-04-18
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO5 Cell 3 | #FFFDA5 | EE60 | 2025-04-14 | 2025-04-18
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO5 Cell 3 | #FFFDA5 | EE61 | 2025-04-14 | 2025-04-18
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO5 Cell 3 | #FFFDA5 | EE57 | 2025-08-14 | 2025-08-20
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO5 Cell 3 | #FFFDA5 | EE63 | 2025-08-14 | 2025-08-20
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO5 Cell 3 | #FFFDA5 | EE58 | 2025-08-14 | 2025-08-20
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO5 Cell 3 | #FFFDA5 | EE62 | 2025-08-21 | 2025-08-27
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO5 Cell 3 | #FFFDA5 | EE60 | 2025-08-21 | 2025-08-27
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO5 Cell 3 | #FFFDA5 | EE59 | 2025-08-21 | 2025-09-04
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO5 Cell 3 | #FFFDA5 | EE61 | 2025-09-03 | 2025-09-09
COLO 5 | Cell 4 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO5 Cell 4 - MG | #EF9E5B | ET22 | 2025-01-17 | 2025-01-30
COLO 5 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO5 Cell 4 - MG | #C00000 | I-R | 2025-01-31 | 2025-02-03
COLO 5 | Cell 4 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO5 Cell 4 - MG | #FFFDA5 | EE35 | 2025-02-04 | 2025-02-13
COLO 5 | Cell 4 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO5 Cell 4 - MG | #FFFDA5 | EE36 | 2025-02-14 | 2025-02-20
COLO 5 | Cell 4 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO5 Cell 4 - ER | #FFFDA5 | EE27 | 2025-01-17 | 2025-01-23
COLO 5 | Cell 4 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO5 Cell 4 - ER | #FFFDA5 | EE28 | 2025-01-21 | 2025-01-27
COLO 5 | Cell 4 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER | #FFFDA5 | EE17 | 2025-01-28 | 2025-02-10
COLO 5 | Cell 4 | Electrical Room | All Trades | Finishes and Signage - COLO5 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-03-14 | 2025-03-20
COLO 5 | Cell 4 | Data Hall | WALSH | Closing Construction Access Door - COLO5 Cell 4 - DH | #04A261 | W4 | 2025-01-03 | 2025-01-23
COLO 5 | Cell 4 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH | #EF9E5B | ET7 | 2025-01-31 | 2025-02-13
COLO 5 | Cell 4 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO5 Cell 4 - DH | #FFFDA5 | EE18 | 2025-02-21 | 2025-03-13
COLO 5 | Cell 4 | Data Hall | All Trades | Finishes and Signage - COLO5 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-03-21 | 2025-03-27
COLO 5 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO5 Cell 4 | #FFFDA5 | EE63 | 2025-01-24 | 2025-01-24
COLO 5 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO5 Cell 4 | #FFFDA5 | EE59 | 2025-01-24 | 2025-01-24
COLO 5 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO5 Cell 4 | #FFFDA5 | EE61 | 2025-01-24 | 2025-01-24
COLO 5 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO5 Cell 4 | #FFFDA5 | EE58 | 2025-01-24 | 2025-01-24
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO5 Cell 4 | #FFFDA5 | EE57 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO5 Cell 4 | #FFFDA5 | EE62 | 2025-04-14 | 2025-04-18
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO5 Cell 4 | #FFFDA5 | EE63 | 2025-04-14 | 2025-04-18
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO5 Cell 4 | #FFFDA5 | EE58 | 2025-04-14 | 2025-04-18
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO5 Cell 4 | #FFFDA5 | EE59 | 2025-04-21 | 2025-04-25
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO5 Cell 4 | #FFFDA5 | EE60 | 2025-04-21 | 2025-04-25
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO5 Cell 4 | #FFFDA5 | EE61 | 2025-04-21 | 2025-04-25
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO5 Cell 4 | #FFFDA5 | EE57 | 2025-08-21 | 2025-08-27
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO5 Cell 4 | #FFFDA5 | EE63 | 2025-08-21 | 2025-08-27
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO5 Cell 4 | #FFFDA5 | EE58 | 2025-08-28 | 2025-09-04
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO5 Cell 4 | #FFFDA5 | EE60 | 2025-09-05 | 2025-09-11
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO5 Cell 4 | #FFFDA5 | EE62 | 2025-09-10 | 2025-09-16
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO5 Cell 4 | #FFFDA5 | EE59 | 2025-09-10 | 2025-09-23
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO5 Cell 4 | #FFFDA5 | EE61 | 2025-09-22 | 2025-09-26
COLO 5 | All | CX - Microsoft | Microsoft | Level 4 Cx - Colo 5 | #000000 | MS1 | 2025-09-29 | 2025-10-24
COLO 5 | All | CX - Microsoft | Microsoft | Level 5 Cx / IST - Colo 5 | #000000 | MS2 | 2025-10-27 | 2025-10-28
COLO 3 | Cell 1 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO3 Cell 1 - MG | #FFFDA5 | EE35 | 2025-01-14 | 2025-01-23
COLO 3 | Cell 1 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO3 Cell 1 - MG | #FFFDA5 | EE36 | 2025-01-24 | 2025-01-30
COLO 3 | Cell 1 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO3 Cell 1 - ER | #FFFDA5 | EE28 | 2025-01-27 | 2025-01-31
COLO 3 | Cell 1 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER | #FFFDA5 | EE29 | 2025-02-03 | 2025-02-18
COLO 3 | Cell 1 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO3 Cell 1 - ER | #FFFDA5 | EE23 | 2025-02-19 | 2025-02-25
COLO 3 | Cell 1 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO3 Cell 1 - ER | #3399FF | J36 | 2025-02-26 | 2025-03-04
COLO 3 | Cell 1 | Electrical Room | All Trades | Finishes and Signage - COLO3 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-03-05 | 2025-03-11
COLO 3 | Cell 1 | Data Hall | Gurtz Electric | Install PDU's - COLO3 Cell 1 - DH | #FFFDA5 | EE7 | 2025-01-17 | 2025-01-23
COLO 3 | Cell 1 | Data Hall | Interior System | Begin HAC Assembly - COLO3 Cell 1 - DH | #FED7E8 | S1 | 2025-01-17 | 2025-01-23
COLO 3 | Cell 1 | Data Hall | Interior System | HAC install and Rise - COLO3 Cell 1 - DH | #FED7E8 | S2 | 2025-01-24 | 2025-01-30
COLO 3 | Cell 1 | Data Hall | Gurtz Electric | Install Busway - COLO3 Cell 1 - DH | #FFFDA5 | EE10 | 2025-01-27 | 2025-01-31
COLO 3 | Cell 1 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH | #FFFDA5 | EE17 | 2025-01-24 | 2025-02-13
COLO 3 | Cell 1 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH | #EF9E5B | ET7 | 2025-01-31 | 2025-02-13
COLO 3 | Cell 1 | Data Hall | Gurtz Electric | Termination at PDU & Busway- COLO3 Cell 1 - DH | #FFFDA5 | EE18 | 2025-02-03 | 2025-02-21
COLO 3 | Cell 1 | Data Hall | All Trades | Finishes and Signage - COLO3 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-02-24 | 2025-02-28
COLO 3 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO3 Cell 1 | #FFFDA5 | EE63 | 2025-01-24 | 2025-01-24
COLO 3 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO3 Cell 1 | #FFFDA5 | EE62 | 2025-02-26 | 2025-02-26
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO3 Cell 1 | #FFFDA5 | EE57 | 2025-03-17 | 2025-03-21
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO3 Cell 1 | #FFFDA5 | EE62 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO3 Cell 1 | #FFFDA5 | EE63 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO3 Cell 1 | #FFFDA5 | EE58 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO3 Cell 1 | #FFFDA5 | EE60 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO3 Cell 1 | #FFFDA5 | EE61 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO3 Cell 1 | #FFFDA5 | EE59 | 2025-04-07 | 2025-04-11
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO3 Cell 1 | #FFFDA5 | EE57 | 2025-08-18 | 2025-08-22
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO3 Cell 1 | #FFFDA5 | EE62 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO3 Cell 1 | #FFFDA5 | EE63 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO3 Cell 1 | #FFFDA5 | EE58 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO3 Cell 1 | #FFFDA5 | EE60 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO3 Cell 1 | #FFFDA5 | EE59 | 2025-09-10 | 2025-09-23
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO3 Cell 1 | #FFFDA5 | EE61 | 2025-09-24 | 2025-09-30
COLO 3 | Cell 2 | Mech Gallery | Great Lakes Air Design | Placing the AHU - COLO3 Cell 2 - MG | #CFE741 | GA6 | 2025-01-17 | 2025-01-21
COLO 3 | Cell 2 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO3 Cell 2 - MG | #FFFDA5 | EE70 | 2025-01-10 | 2025-01-30
COLO 3 | Cell 2 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO3 Cell 2 - MG | #EF9E5B | ET22 | 2025-01-21 | 2025-02-04
COLO 3 | Cell 2 | Mech Gallery | Inspections | Pipe Testing - COLO3 Cell 2 - MG | #C00000 | I-R | 2025-02-04 | 2025-02-06
COLO 3 | Cell 2 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO3 Cell 2 - MG | #FFFDA5 | EE35 | 2025-02-06 | 2025-02-18
COLO 3 | Cell 2 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO3 Cell 2 - MG | #FFFDA5 | EE36 | 2025-02-18 | 2025-02-25
COLO 3 | Cell 2 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO3 Cell 2 - ER | #987655 | GH3 | 2025-01-15 | 2025-01-21
COLO 3 | Cell 2 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO3 Cell 2 - ER | #FFFDA5 | EE27 | 2025-01-16 | 2025-01-22
COLO 3 | Cell 2 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO3 Cell 2 - ER | #FFFDA5 | EE23 | 2025-01-16 | 2025-01-22
COLO 3 | Cell 2 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO3 Cell 2 - ER | #FFFDA5 | EE71 | 2025-01-16 | 2025-01-22
COLO 3 | Cell 2 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | #FFFDA5 | EE72 | 2025-01-14 | 2025-01-27
COLO 3 | Cell 2 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO3 Cell 2 - ER | #3399FF | J36 | 2025-01-23 | 2025-01-29
COLO 3 | Cell 2 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO3 Cell 2 - ER | #FFFDA5 | EE28 | 2025-02-03 | 2025-02-07
COLO 3 | Cell 2 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER | #FFFDA5 | EE29 | 2025-02-19 | 2025-03-06
COLO 3 | Cell 2 | Electrical Room | All Trades | Finishes and Signage - COLO3 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-03-12 | 2025-03-18
COLO 3 | Cell 2 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO3 Cell 2 - DH | #3399FF | J7 | 2025-01-15 | 2025-01-21
COLO 3 | Cell 2 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH | #FFFDA5 | EE73 | 2025-01-22 | 2025-02-04
COLO 3 | Cell 2 | Data Hall | Gurtz Electric | Install PDU's - COLO3 Cell 2 - DH | #FFFDA5 | EE7 | 2025-02-05 | 2025-02-11
COLO 3 | Cell 2 | Data Hall | Interior System | Begin HAC Assembly - COLO3 Cell 2 - DH | #FED7E8 | S1 | 2025-02-05 | 2025-02-11
COLO 3 | Cell 2 | Data Hall | Gurtz Electric | Install Busway - COLO3 Cell 2 - DH | #FFFDA5 | EE10 | 2025-02-07 | 2025-02-13
COLO 3 | Cell 2 | Data Hall | Interior System | HAC install and Rise - COLO3 Cell 2 - DH | #FED7E8 | S2 | 2025-02-12 | 2025-02-18
COLO 3 | Cell 2 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO3 Cell 2 - DH | #FFFDA5 | EE17 | 2025-02-12 | 2025-02-25
COLO 3 | Cell 2 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 2 - DH | #EF9E5B | ET7 | 2025-02-19 | 2025-03-04
COLO 3 | Cell 2 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO3 Cell 2 - DH | #FFFDA5 | EE18 | 2025-02-14 | 2025-03-06
COLO 3 | Cell 2 | Data Hall | All Trades | Finishes and Signage - COLO3 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-03-05 | 2025-03-11
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO3 Cell 2 | #FFFDA5 | EE59 | 2025-01-17 | 2025-01-17
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO3 Cell 2 | #FFFDA5 | EE57 | 2025-01-23 | 2025-01-23
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO3 Cell 2 | #FFFDA5 | EE60 | 2025-01-23 | 2025-01-23
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO3 Cell 2 | #FFFDA5 | EE61 | 2025-01-23 | 2025-01-23
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO3 Cell 2 | #FFFDA5 | EE58 | 2025-01-23 | 2025-01-23
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO3 Cell 2 | #FFFDA5 | EE63 | 2025-02-12 | 2025-02-12
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO3 Cell 2 | #FFFDA5 | EE62 | 2025-02-27 | 2025-02-27
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO3 Cell 2 | #FFFDA5 | EE57 | 2025-03-17 | 2025-03-21
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO3 Cell 2 | #FFFDA5 | EE62 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO3 Cell 2 | #FFFDA5 | EE63 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO3 Cell 2 | #FFFDA5 | EE58 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO3 Cell 2 | #FFFDA5 | EE60 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO3 Cell 2 | #FFFDA5 | EE61 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO3 Cell 2 | #FFFDA5 | EE59 | 2025-04-14 | 2025-04-18
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO3 Cell 2 | #FFFDA5 | EE57 | 2025-08-18 | 2025-08-22
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO3 Cell 2 | #FFFDA5 | EE62 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO3 Cell 2 | #FFFDA5 | EE58 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO3 Cell 2 | #FFFDA5 | EE63 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO3 Cell 2 | #FFFDA5 | EE60 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO3 Cell 2 | #FFFDA5 | EE59 | 2025-09-10 | 2025-09-23
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO3 Cell 2 | #FFFDA5 | EE61 | 2025-09-24 | 2025-09-30
COLO 3 | Cell 3 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO3 Cell 3 - MG | #FFFDA5 | EE70 | 2025-01-10 | 2025-01-30
COLO 3 | Cell 3 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO3 Cell 3 - MG | #EF9E5B | ET22 | 2025-02-04 | 2025-02-18
COLO 3 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO3 Cell 3 - MG | #C00000 | I-R | 2025-02-18 | 2025-02-20
COLO 3 | Cell 3 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO3 Cell 3 - MG | #FFFDA5 | EE35 | 2025-02-20 | 2025-03-04
COLO 3 | Cell 3 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO3 Cell 3 - MG | #FFFDA5 | EE36 | 2025-03-04 | 2025-03-11
COLO 3 | Cell 3 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO3 Cell 3 - ER | #987655 | GH3 | 2025-01-17 | 2025-01-23
COLO 3 | Cell 3 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO3 Cell 3 - ER | #FFFDA5 | EE27 | 2025-01-30 | 2025-02-05
COLO 3 | Cell 3 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO3 Cell 3 - ER | #FFFDA5 | EE23 | 2025-01-30 | 2025-02-05
COLO 3 | Cell 3 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO3 Cell 3 - ER | #FFFDA5 | EE71 | 2025-01-30 | 2025-02-05
COLO 3 | Cell 3 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | #FFFDA5 | EE72 | 2025-01-28 | 2025-02-10
COLO 3 | Cell 3 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO3 Cell 3 - ER | #3399FF | J36 | 2025-02-06 | 2025-02-12
COLO 3 | Cell 3 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO3 Cell 3 - ER | #FFFDA5 | EE28 | 2025-02-10 | 2025-02-14
COLO 3 | Cell 3 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER | #FFFDA5 | EE29 | 2025-03-07 | 2025-03-24
COLO 3 | Cell 3 | Electrical Room | All Trades | Finishes and Signage - COLO3 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-03-20 | 2025-03-26
COLO 3 | Cell 3 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO3 Cell 3 - DH | #3399FF | J7 | 2025-01-22 | 2025-01-28
COLO 3 | Cell 3 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH | #FFFDA5 | EE73 | 2025-02-05 | 2025-02-18
COLO 3 | Cell 3 | Data Hall | Gurtz Electric | Install PDU's - COLO3 Cell 3 - DH | #FFFDA5 | EE7 | 2025-02-19 | 2025-02-25
COLO 3 | Cell 3 | Data Hall | Interior System | Begin HAC Assembly - COLO3 Cell 3 - DH | #FED7E8 | S1 | 2025-02-19 | 2025-02-25
COLO 3 | Cell 3 | Data Hall | Gurtz Electric | Install Busway - COLO3 Cell 3 - DH | #FFFDA5 | EE10 | 2025-02-21 | 2025-02-27
COLO 3 | Cell 3 | Data Hall | Interior System | HAC install and Rise - COLO3 Cell 3 - DH | #FED7E8 | S2 | 2025-02-26 | 2025-03-04
COLO 3 | Cell 3 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO3 Cell 3 - DH | #FFFDA5 | EE17 | 2025-02-26 | 2025-03-11
COLO 3 | Cell 3 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 3 - DH | #EF9E5B | ET7 | 2025-03-05 | 2025-03-18
COLO 3 | Cell 3 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO3 Cell 3 - DH | #FFFDA5 | EE18 | 2025-03-12 | 2025-04-01
COLO 3 | Cell 3 | Data Hall | All Trades | Finishes and Signage - COLO3 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-03-26 | 2025-04-01
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO3 Cell 3 | #FFFDA5 | EE59 | 2025-01-21 | 2025-01-22
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO3 Cell 3 | #FFFDA5 | EE57 | 2025-02-06 | 2025-02-06
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO3 Cell 3 | #FFFDA5 | EE60 | 2025-02-06 | 2025-02-06
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-02-06 | 2025-02-06
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO3 Cell 3 | #FFFDA5 | EE58 | 2025-02-06 | 2025-02-06
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO3 Cell 3 | #FFFDA5 | EE63 | 2025-02-26 | 2025-02-26
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO3 Cell 3 | #FFFDA5 | EE62 | 2025-02-28 | 2025-02-28
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO3 Cell 3 | #FFFDA5 | EE57 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO3 Cell 3 | #FFFDA5 | EE60 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO3 Cell 3 | #FFFDA5 | EE58 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO3 Cell 3 | #FFFDA5 | EE62 | 2025-04-01 | 2025-04-07
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO3 Cell 3 | #FFFDA5 | EE63 | 2025-04-01 | 2025-04-07
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-04-08 | 2025-04-14
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO3 Cell 3 | #FFFDA5 | EE59 | 2025-04-21 | 2025-04-25
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO3 Cell 3 | #FFFDA5 | EE57 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO3 Cell 3 | #FFFDA5 | EE62 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO3 Cell 3 | #FFFDA5 | EE63 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO3 Cell 3 | #FFFDA5 | EE58 | 2025-09-09 | 2025-09-15
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO3 Cell 3 | #FFFDA5 | EE60 | 2025-09-17 | 2025-09-23
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-09-24 | 2025-09-30
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-09-24 | 2025-10-07
COLO 3 | Cell 4 | Mech Gallery | Great Lakes Air Design | Deliver AHU into Mech. Gallery - COLO3 Cell 4 - MG | #CFE741 | GA12 | 2025-01-17 | 2025-01-20
COLO 3 | Cell 4 | Mech Gallery | All - Tech | Install Walls and Primer Paint - COLO3 Cell 4 - MG | #D6F2FF | T3 | 2025-01-21 | 2025-02-03
COLO 3 | Cell 4 | Mech Gallery | Anning - Johnson | Layout Ceiling and install Pencile Rod - COLO3 Cell 4 - MG | #3399FF | J9 | 2025-02-04 | 2025-02-04
COLO 3 | Cell 4 | Mech Gallery | Great Lakes Air Design | Placing the AHU - COLO3 Cell 4 - MG | #CFE741 | GA6 | 2025-02-11 | 2025-02-13
COLO 3 | Cell 4 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO3 Cell 4 - MG | #FFFDA5 | EE70 | 2025-02-04 | 2025-02-24
COLO 3 | Cell 4 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO3 Cell 4 - MG | #EF9E5B | ET22 | 2025-02-18 | 2025-03-04
COLO 3 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO3 Cell 4 - MG | #C00000 | I-R | 2025-03-04 | 2025-03-06
COLO 3 | Cell 4 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO3 Cell 4 - MG | #FFFDA5 | EE35 | 2025-03-06 | 2025-03-18
COLO 3 | Cell 4 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO3 Cell 4 - MG | #FFFDA5 | EE36 | 2025-03-18 | 2025-03-25
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 4 - ER | #FFFDA5 | EE1 | 2025-01-13 | 2025-01-24
COLO 3 | Cell 4 | Electrical Room | Anning - Johnson | Install Ceiling - COLO3 Cell 4 - ER | #3399FF | J17 | 2025-01-27 | 2025-01-29
COLO 3 | Cell 4 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO3 Cell 4 - ER | #987655 | GH3 | 2025-01-30 | 2025-02-05
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO3 Cell 4 - ER | #FFFDA5 | EE27 | 2025-02-13 | 2025-02-19
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO3 Cell 4 - ER | #FFFDA5 | EE23 | 2025-02-13 | 2025-02-19
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO3 Cell 4 - ER | #FFFDA5 | EE71 | 2025-02-13 | 2025-02-19
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO3 Cell 4 - ER | #FFFDA5 | EE28 | 2025-02-17 | 2025-02-21
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | #FFFDA5 | EE72 | 2025-02-11 | 2025-02-24
COLO 3 | Cell 4 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO3 Cell 4 - ER | #3399FF | J36 | 2025-02-20 | 2025-02-26
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER | #FFFDA5 | EE29 | 2025-03-04 | 2025-03-24
COLO 3 | Cell 4 | Electrical Room | All Trades | Finishes and Signage - COLO3 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-03-27 | 2025-04-02
COLO 3 | Cell 4 | Data Hall | Gurtz Electric | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 4 - DH | #FFFDA5 | EE74 | 2025-01-10 | 2025-01-27
COLO 3 | Cell 4 | Data Hall | Anning - Johnson | Security Screen Installation - COLO3 Cell 4 - DH | #3399FF | J6 | 2025-02-04 | 2025-02-06
COLO 3 | Cell 4 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO3 Cell 4 - DH | #3399FF | J7 | 2025-02-07 | 2025-02-13
COLO 3 | Cell 4 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 4 - DH | #FFFDA5 | EE73 | 2025-02-19 | 2025-03-04
COLO 3 | Cell 4 | Data Hall | Gurtz Electric | Install PDU's - COLO3 Cell 4 - DH | #FFFDA5 | EE7 | 2025-03-05 | 2025-03-11
COLO 3 | Cell 4 | Data Hall | Interior System | Begin HAC Assembly - COLO3 Cell 4 - DH | #FED7E8 | S1 | 2025-03-05 | 2025-03-11
COLO 3 | Cell 4 | Data Hall | Gurtz Electric | Install Busway - COLO3 Cell 4 - DH | #FFFDA5 | EE10 | 2025-03-07 | 2025-03-13
COLO 3 | Cell 4 | Data Hall | Interior System | HAC install and Rise - COLO3 Cell 4 - DH | #FED7E8 | S2 | 2025-03-12 | 2025-03-18
COLO 3 | Cell 4 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH | #EF9E5B | ET7 | 2025-03-05 | 2025-03-18
COLO 3 | Cell 4 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO3 Cell 4 - DH | #FFFDA5 | EE17 | 2025-03-12 | 2025-03-25
COLO 3 | Cell 4 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO3 Cell 4 - DH | #FFFDA5 | EE18 | 2025-04-02 | 2025-04-15
COLO 3 | Cell 4 | Data Hall | All Trades | Finishes and Signage - COLO3 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-04-09 | 2025-04-15
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO3 Cell 4 | #FFFDA5 | EE61 | 2025-02-11 | 2025-02-11
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO3 Cell 4 | #FFFDA5 | EE57 | 2025-02-20 | 2025-02-20
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-02-20 | 2025-02-20
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-02-20 | 2025-02-20
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO3 Cell 4 | #FFFDA5 | EE58 | 2025-02-20 | 2025-02-20
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO3 Cell 4 | #FFFDA5 | EE62 | 2025-02-28 | 2025-02-28
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO3 Cell 4 | #FFFDA5 | EE63 | 2025-03-12 | 2025-03-12
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO3 Cell 4 | #FFFDA5 | EE57 | 2025-03-25 | 2025-04-01
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO3 Cell 4 | #FFFDA5 | EE62 | 2025-04-01 | 2025-04-08
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-04-01 | 2025-04-08
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO3 Cell 4 | #FFFDA5 | EE61 | 2025-04-08 | 2025-04-15
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO3 Cell 4 | #FFFDA5 | EE58 | 2025-04-08 | 2025-04-15
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO3 Cell 4 | #FFFDA5 | EE63 | 2025-04-16 | 2025-04-22
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO3 Cell 4 | #FFFDA5 | EE59 | 2025-04-21 | 2025-04-25
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO3 Cell 4 | #FFFDA5 | EE57 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO3 Cell 4 | #FFFDA5 | EE63 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO3 Cell 4 | #FFFDA5 | EE58 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO3 Cell 4 | #FFFDA5 | EE59 | 2025-09-03 | 2025-09-16
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-09-10 | 2025-09-16
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO3 Cell 4 | #FFFDA5 | EE62 | 2025-09-24 | 2025-09-30
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO3 Cell 4 | #FFFDA5 | EE61 | 2025-10-01 | 2025-10-07
COLO 3 | All | CX - Microsoft | Microsoft | Level 4 Cx - Colo 3 | #000000 | MS1 | 2025-10-08 | 2025-11-06
COLO 3 | All | CX - Microsoft | Microsoft | Level 5 Cx / IST - Colo 3 | #000000 | MS2 | 2025-10-08 | 2025-11-04
COLO 4 | Cell 1 | Mech Gallery | Great Lakes Air Design | Placing the AHU - COLO4 Cell 1 - MG | #CFE741 | GA6 | 2025-01-17 | 2025-01-21
COLO 4 | Cell 1 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO4 Cell 1 - MG | #FFFDA5 | EE70 | 2025-01-10 | 2025-01-30
COLO 4 | Cell 1 | Mech Gallery | Gurtz Electric | Piping and Electrical Termination to AHUs - COLO4 Cell 1 - MG | #FFFDA5 | EE1 | 2025-01-21 | 2025-02-04
COLO 4 | Cell 1 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 1 - MG | #C00000 | I-R | 2025-02-04 | 2025-02-06
COLO 4 | Cell 1 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO4 Cell 1 - MG | #FFFDA5 | EE35 | 2025-02-06 | 2025-02-18
COLO 4 | Cell 1 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO4 Cell 1 - MG | #FFFDA5 | EE36 | 2025-02-18 | 2025-02-25
COLO 4 | Cell 1 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO4 Cell 1 - ER | #FFFDA5 | EE27 | 2025-01-17 | 2025-01-23
COLO 4 | Cell 1 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO4 Cell 1 - ER | #FFFDA5 | EE23 | 2025-01-17 | 2025-01-23
COLO 4 | Cell 1 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO4 Cell 1 - ER | #FFFDA5 | EE71 | 2025-01-17 | 2025-01-23
COLO 4 | Cell 1 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO4 Cell 1 - ER | #987655 | GH3 | 2025-01-17 | 2025-01-23
COLO 4 | Cell 1 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO4 Cell 1 - ER | #FFFDA5 | EE72 | 2025-01-14 | 2025-01-27
COLO 4 | Cell 1 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO4 Cell 1 - ER | #3399FF | J36 | 2025-01-24 | 2025-01-30
COLO 4 | Cell 1 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO4 Cell 1 - ER | #FFFDA5 | EE28 | 2025-02-11 | 2025-02-17
COLO 4 | Cell 1 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER | #FFFDA5 | EE29 | 2025-02-18 | 2025-03-10
COLO 4 | Cell 1 | Electrical Room | All Trades | Finishes and Signage - COLO4 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-03-06 | 2025-03-12
COLO 4 | Cell 1 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO4 Cell 1 - DH | #3399FF | J7 | 2025-01-17 | 2025-01-23
COLO 4 | Cell 1 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 1 - DH | #FFFDA5 | EE73 | 2025-01-24 | 2025-02-06
COLO 4 | Cell 1 | Data Hall | Gurtz Electric | Install PDU's - COLO4 Cell 1 - DH | #FFFDA5 | EE7 | 2025-02-07 | 2025-02-13
COLO 4 | Cell 1 | Data Hall | Interior System | Begin HAC Assembly - COLO4 Cell 1 - DH | #FED7E8 | S1 | 2025-02-07 | 2025-02-13
COLO 4 | Cell 1 | Data Hall | Gurtz Electric | Install Busway - COLO4 Cell 1 - DH | #FFFDA5 | EE10 | 2025-02-11 | 2025-02-17
COLO 4 | Cell 1 | Data Hall | Interior System | HAC install and Rise - COLO4 Cell 1 - DH | #FED7E8 | S2 | 2025-02-14 | 2025-02-20
COLO 4 | Cell 1 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH | #FFFDA5 | EE17 | 2025-02-14 | 2025-03-06
COLO 4 | Cell 1 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH | #EF9E5B | ET22 | 2025-02-21 | 2025-03-06
COLO 4 | Cell 1 | Data Hall | Gurtz Electric | Termination at PDU & Busway- COLO4 Cell 1 - DH | #FFFDA5 | EE18 | 2025-02-21 | 2025-03-13
COLO 4 | Cell 1 | Data Hall | All Trades | Finishes and Signage - COLO4 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-03-14 | 2025-03-20
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO4 Cell 1 | #FFFDA5 | EE59 | 2025-01-17 | 2025-01-17
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO4 Cell 1 | #FFFDA5 | EE62 | 2025-01-24 | 2025-01-24
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO4 Cell 1 | #FFFDA5 | EE57 | 2025-01-24 | 2025-01-24
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO4 Cell 1 | #FFFDA5 | EE60 | 2025-01-24 | 2025-01-24
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO4 Cell 1 | #FFFDA5 | EE58 | 2025-01-24 | 2025-01-24
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO4 Cell 1 | #FFFDA5 | EE63 | 2025-02-14 | 2025-02-14
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO4 Cell 1 | #FFFDA5 | EE61 | 2025-02-18 | 2025-02-18
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO4 Cell 1 | #FFFDA5 | EE57 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO4 Cell 1 | #FFFDA5 | EE62 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO4 Cell 1 | #FFFDA5 | EE63 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO4 Cell 1 | #FFFDA5 | EE58 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO4 Cell 1 | #FFFDA5 | EE60 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO4 Cell 1 | #FFFDA5 | EE61 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO4 Cell 1 | #FFFDA5 | EE59 | 2025-05-19 | 2025-05-23
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO4 Cell 1 | #FFFDA5 | EE57 | 2025-09-29 | 2025-10-03
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO4 Cell 1 | #FFFDA5 | EE62 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO4 Cell 1 | #FFFDA5 | EE63 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO4 Cell 1 | #FFFDA5 | EE58 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO4 Cell 1 | #FFFDA5 | EE60 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO4 Cell 1 | #FFFDA5 | EE59 | 2025-10-20 | 2025-10-31
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO4 Cell 1 | #FFFDA5 | EE61 | 2025-11-03 | 2025-11-07
COLO 4 | Cell 2 | Mech Gallery | Great Lakes Air Design | Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG | #CFE741 | GA12 | 2025-01-17 | 2025-01-20
COLO 4 | Cell 2 | Mech Gallery | All - Tech | Install Walls and Primer Paint - COLO4 Cell 2 - MG | #D6F2FF | T3 | 2025-01-21 | 2025-02-03
COLO 4 | Cell 2 | Mech Gallery | Anning - Johnson | Layout Ceiling and install Pencile Rod - COLO4 Cell 2 - MG | #3399FF | J9 | 2025-02-04 | 2025-02-04
COLO 4 | Cell 2 | Mech Gallery | Great Lakes Air Design | Placing the AHU - COLO4 Cell 2 - MG | #CFE741 | GA6 | 2025-02-11 | 2025-02-13
COLO 4 | Cell 2 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO4 Cell 2 - MG | #FFFDA5 | EE70 | 2025-02-04 | 2025-02-24
COLO 4 | Cell 2 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO4 Cell 2 - MG | #EF9E5B | ET22 | 2025-02-13 | 2025-02-27
COLO 4 | Cell 2 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 2 - MG | #C00000 | I-R | 2025-02-27 | 2025-03-03
COLO 4 | Cell 2 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO4 Cell 2 - MG | #FFFDA5 | EE35 | 2025-03-03 | 2025-03-13
COLO 4 | Cell 2 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO4 Cell 2 - MG | #FFFDA5 | EE36 | 2025-03-13 | 2025-03-20
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 2 - ER | #FFFDA5 | EE1 | 2025-01-21 | 2025-01-27
COLO 4 | Cell 2 | Electrical Room | Anning - Johnson | Install Ceiling - COLO4 Cell 2 - ER | #3399FF | J17 | 2025-01-28 | 2025-01-30
COLO 4 | Cell 2 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO4 Cell 2 - ER | #987655 | GH3 | 2025-01-31 | 2025-02-06
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO4 Cell 2 - ER | #FFFDA5 | EE27 | 2025-02-03 | 2025-02-07
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO4 Cell 2 - ER | #FFFDA5 | EE23 | 2025-02-03 | 2025-02-07
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO4 Cell 2 - ER | #FFFDA5 | EE71 | 2025-02-03 | 2025-02-07
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | #FFFDA5 | EE72 | 2025-01-30 | 2025-02-12
COLO 4 | Cell 2 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO4 Cell 2 - ER | #3399FF | J36 | 2025-02-10 | 2025-02-14
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO4 Cell 2 - ER | #FFFDA5 | EE28 | 2025-02-18 | 2025-02-24
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER | #FFFDA5 | EE29 | 2025-03-11 | 2025-03-31
COLO 4 | Cell 2 | Electrical Room | All Trades | Finishes and Signage - COLO4 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-03-27 | 2025-04-02
COLO 4 | Cell 2 | Data Hall | Gurtz Electric | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH | #FFFDA5 | EE74 | 2025-01-10 | 2025-01-27
COLO 4 | Cell 2 | Data Hall | Anning - Johnson | Security Screen Installation - COLO4 Cell 2 - DH | #3399FF | J6 | 2025-02-04 | 2025-02-06
COLO 4 | Cell 2 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO4 Cell 2 - DH | #3399FF | J7 | 2025-02-07 | 2025-02-13
COLO 4 | Cell 2 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH | #FFFDA5 | EE73 | 2025-02-14 | 2025-02-27
COLO 4 | Cell 2 | Data Hall | Gurtz Electric | Install PDU's - COLO4 Cell 2 - DH | #FFFDA5 | EE7 | 2025-02-28 | 2025-03-06
COLO 4 | Cell 2 | Data Hall | Interior System | Begin HAC Assembly - COLO4 Cell 2 - DH | #FED7E8 | S1 | 2025-02-28 | 2025-03-06
COLO 4 | Cell 2 | Data Hall | Gurtz Electric | Install Busway - COLO4 Cell 2 - DH | #FFFDA5 | EE10 | 2025-03-04 | 2025-03-10
COLO 4 | Cell 2 | Data Hall | Interior System | HAC install and Rise - COLO4 Cell 2 - DH | #FED7E8 | S2 | 2025-03-07 | 2025-03-13
COLO 4 | Cell 2 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO4 Cell 2 - DH | #FFFDA5 | EE17 | 2025-03-07 | 2025-03-20
COLO 4 | Cell 2 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 2 - DH | #EF9E5B | ET7 | 2025-03-14 | 2025-03-27
COLO 4 | Cell 2 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO4 Cell 2 - DH | #FFFDA5 | EE18 | 2025-03-11 | 2025-03-31
COLO 4 | Cell 2 | Data Hall | All Trades | Finishes and Signage - COLO4 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-03-28 | 2025-04-03
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO4 Cell 2 | #FFFDA5 | EE62 | 2025-02-10 | 2025-02-10
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO4 Cell 2 | #FFFDA5 | EE57 | 2025-02-10 | 2025-02-10
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO4 Cell 2 | #FFFDA5 | EE60 | 2025-02-10 | 2025-02-10
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO4 Cell 2 | #FFFDA5 | EE58 | 2025-02-10 | 2025-02-10
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO4 Cell 2 | #FFFDA5 | EE59 | 2025-02-11 | 2025-02-11
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO4 Cell 2 | #FFFDA5 | EE63 | 2025-03-07 | 2025-03-07
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO4 Cell 2 | #FFFDA5 | EE61 | 2025-03-11 | 2025-03-11
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO4 Cell 2 | #FFFDA5 | EE57 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO4 Cell 2 | #FFFDA5 | EE62 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO4 Cell 2 | #FFFDA5 | EE63 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO4 Cell 2 | #FFFDA5 | EE58 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO4 Cell 2 | #FFFDA5 | EE60 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO4 Cell 2 | #FFFDA5 | EE61 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO4 Cell 2 | #FFFDA5 | EE59 | 2025-05-19 | 2025-05-23
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO4 Cell 2 | #FFFDA5 | EE57 | 2025-09-29 | 2025-10-03
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO4 Cell 2 | #FFFDA5 | EE62 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO4 Cell 2 | #FFFDA5 | EE63 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO4 Cell 2 | #FFFDA5 | EE58 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO4 Cell 2 | #FFFDA5 | EE60 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO4 Cell 2 | #FFFDA5 | EE59 | 2025-10-20 | 2025-10-31
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO4 Cell 2 | #FFFDA5 | EE61 | 2025-11-03 | 2025-11-07
COLO 4 | Cell 3 | Mech Gallery | Gurtz Electric | Overhead MEP Installation - COLO4 Cell 3 - MG | #FFFDA5 | EE73 | 2025-01-10 | 2025-01-23
COLO 4 | Cell 3 | Mech Gallery | Great Lakes Air Design | Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG | #CFE741 | GA12 | 2025-01-24 | 2025-01-27
COLO 4 | Cell 3 | Mech Gallery | All - Tech | Install Walls and Primer Paint - COLO4 Cell 3 - MG | #D6F2FF | T3 | 2025-02-04 | 2025-02-17
COLO 4 | Cell 3 | Mech Gallery | Anning - Johnson | Layout Ceiling and install Pencile Rod - COLO4 Cell 3 - MG | #3399FF | J9 | 2025-02-18 | 2025-02-18
COLO 4 | Cell 3 | Mech Gallery | Great Lakes Air Design | Placing the AHU - COLO4 Cell 3 - MG | #CFE741 | GA6 | 2025-02-25 | 2025-02-27
COLO 4 | Cell 3 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO4 Cell 3 - MG | #FFFDA5 | EE70 | 2025-02-18 | 2025-03-10
COLO 4 | Cell 3 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO4 Cell 3 - MG | #EF9E5B | ET22 | 2025-02-27 | 2025-03-13
COLO 4 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 3 - MG | #C00000 | I-R | 2025-03-13 | 2025-03-17
COLO 4 | Cell 3 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO4 Cell 3 - MG | #FFFDA5 | EE35 | 2025-03-17 | 2025-03-27
COLO 4 | Cell 3 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO4 Cell 3 - MG | #FFFDA5 | EE36 | 2025-03-27 | 2025-04-03
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 3 - ER | #FFFDA5 | EE1 | 2025-01-28 | 2025-02-10
COLO 4 | Cell 3 | Electrical Room | Anning - Johnson | Install Ceiling - COLO4 Cell 3 - ER | #3399FF | J17 | 2025-02-11 | 2025-02-13
COLO 4 | Cell 3 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO4 Cell 3 - ER | #987655 | GH3 | 2025-02-14 | 2025-02-20
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO4 Cell 3 - ER | #FFFDA5 | EE27 | 2025-02-17 | 2025-02-21
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO4 Cell 3 - ER | #FFFDA5 | EE23 | 2025-02-17 | 2025-02-21
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO4 Cell 3 - ER | #FFFDA5 | EE71 | 2025-02-17 | 2025-02-21
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | #FFFDA5 | EE72 | 2025-02-13 | 2025-02-26
COLO 4 | Cell 3 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO4 Cell 3 - ER | #3399FF | J36 | 2025-02-24 | 2025-02-28
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO4 Cell 3 - ER | #FFFDA5 | EE28 | 2025-02-25 | 2025-03-03
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER | #FFFDA5 | EE29 | 2025-04-01 | 2025-04-21
COLO 4 | Cell 3 | Electrical Room | All Trades | Finishes and Signage - COLO4 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-04-17 | 2025-04-23
COLO 4 | Cell 3 | Data Hall | Gurtz Electric | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH | #FFFDA5 | EE74 | 2025-01-28 | 2025-02-12
COLO 4 | Cell 3 | Data Hall | Anning - Johnson | Security Screen Installation - COLO4 Cell 3 - DH | #3399FF | J6 | 2025-02-18 | 2025-02-20
COLO 4 | Cell 3 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO4 Cell 3 - DH | #3399FF | J7 | 2025-02-21 | 2025-02-27
COLO 4 | Cell 3 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH | #FFFDA5 | EE73 | 2025-02-28 | 2025-03-13
COLO 4 | Cell 3 | Data Hall | Gurtz Electric | Install PDU's - COLO4 Cell 3 - DH | #FFFDA5 | EE7 | 2025-03-14 | 2025-03-20
COLO 4 | Cell 3 | Data Hall | Interior System | Begin HAC Assembly - COLO4 Cell 3 - DH | #FED7E8 | S1 | 2025-03-14 | 2025-03-20
COLO 4 | Cell 3 | Data Hall | Gurtz Electric | Install Busway - COLO4 Cell 3 - DH | #FFFDA5 | EE10 | 2025-03-18 | 2025-03-24
COLO 4 | Cell 3 | Data Hall | Interior System | HAC install and Rise - COLO4 Cell 3 - DH | #FED7E8 | S2 | 2025-03-21 | 2025-03-27
COLO 4 | Cell 3 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO4 Cell 3 - DH | #FFFDA5 | EE17 | 2025-03-21 | 2025-04-03
COLO 4 | Cell 3 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 3 - DH | #EF9E5B | ET7 | 2025-03-28 | 2025-04-10
COLO 4 | Cell 3 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO4 Cell 3 - DH | #FFFDA5 | EE18 | 2025-04-01 | 2025-04-21
COLO 4 | Cell 3 | Data Hall | All Trades | Finishes and Signage - COLO4 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-04-15 | 2025-04-21
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO4 Cell 3 | #FFFDA5 | EE62 | 2025-02-24 | 2025-02-24
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO4 Cell 3 | #FFFDA5 | EE57 | 2025-02-24 | 2025-02-24
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO4 Cell 3 | #FFFDA5 | EE60 | 2025-02-24 | 2025-02-24
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO4 Cell 3 | #FFFDA5 | EE58 | 2025-02-24 | 2025-02-24
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO4 Cell 3 | #FFFDA5 | EE59 | 2025-02-25 | 2025-02-25
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO4 Cell 3 | #FFFDA5 | EE63 | 2025-03-21 | 2025-03-21
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO4 Cell 3 | #FFFDA5 | EE61 | 2025-03-25 | 2025-03-25
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO4 Cell 3 | #FFFDA5 | EE57 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO4 Cell 3 | #FFFDA5 | EE62 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO4 Cell 3 | #FFFDA5 | EE63 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO4 Cell 3 | #FFFDA5 | EE58 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO4 Cell 3 | #FFFDA5 | EE60 | 2025-05-19 | 2025-05-23
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO4 Cell 3 | #FFFDA5 | EE61 | 2025-05-19 | 2025-05-23
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO4 Cell 3 | #FFFDA5 | EE59 | 2025-05-27 | 2025-06-02
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO4 Cell 3 | #FFFDA5 | EE57 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO4 Cell 3 | #FFFDA5 | EE62 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO4 Cell 3 | #FFFDA5 | EE63 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO4 Cell 3 | #FFFDA5 | EE58 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO4 Cell 3 | #FFFDA5 | EE60 | 2025-10-20 | 2025-10-24
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO4 Cell 3 | #FFFDA5 | EE59 | 2025-10-27 | 2025-11-07
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO4 Cell 3 | #FFFDA5 | EE61 | 2025-11-10 | 2025-11-14
COLO 4 | Cell 4 | Mech Gallery | Great Lakes Air Design | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG | #CFE741 | GA3 | 2025-01-14 | 2025-01-20
COLO 4 | Cell 4 | Mech Gallery | Gurtz Electric | Overhead MEP Installation - COLO4 Cell 4 - MG | #FFFDA5 | EE73 | 2025-01-24 | 2025-02-06
COLO 4 | Cell 4 | Mech Gallery | Great Lakes Air Design | Deliver AHU into Mech. Gallery - COLO4 Cell 4 - MG | #CFE741 | GA12 | 2025-02-07 | 2025-02-10
COLO 4 | Cell 4 | Mech Gallery | All - Tech | Install Walls and Primer Paint - COLO4 Cell 4 - MG | #D6F2FF | T3 | 2025-02-18 | 2025-03-03
COLO 4 | Cell 4 | Mech Gallery | Anning - Johnson | Layout Ceiling and install Pencile Rod - COLO4 Cell 4 - MG | #3399FF | J9 | 2025-03-04 | 2025-03-04
COLO 4 | Cell 4 | Mech Gallery | Great Lakes Air Design | Placing the AHU - COLO4 Cell 4 - MG | #CFE741 | GA6 | 2025-03-11 | 2025-03-13
COLO 4 | Cell 4 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO4 Cell 4 - MG | #FFFDA5 | EE70 | 2025-03-04 | 2025-03-24
COLO 4 | Cell 4 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO4 Cell 4 - MG | #EF9E5B | ET22 | 2025-03-13 | 2025-03-27
COLO 4 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 4 - MG | #C00000 | I-R | 2025-03-27 | 2025-03-31
COLO 4 | Cell 4 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO4 Cell 4 - MG | #FFFDA5 | EE35 | 2025-03-31 | 2025-04-10
COLO 4 | Cell 4 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO4 Cell 4 - MG | #FFFDA5 | EE36 | 2025-04-10 | 2025-04-17
COLO 4 | Cell 4 | Electrical Room | All - Tech | Install Walls and Primer Paint - COLO4 Cell 4 - ER | #D6F2FF | T3 | 2025-01-10 | 2025-01-23
COLO 4 | Cell 4 | Electrical Room | Anning - Johnson | Install Upper Screens - COLO4 Cell 4 - ER | #3399FF | J37 | 2025-01-21 | 2025-01-27
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 4 - ER | #FFFDA5 | EE1 | 2025-02-11 | 2025-02-24
COLO 4 | Cell 4 | Electrical Room | Anning - Johnson | Install Ceiling - COLO4 Cell 4 - ER | #3399FF | J17 | 2025-02-25 | 2025-02-27
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO4 Cell 4 - ER | #FFFDA5 | EE27 | 2025-02-27 | 2025-03-05
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO4 Cell 4 - ER | #FFFDA5 | EE71 | 2025-02-27 | 2025-03-05
COLO 4 | Cell 4 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO4 Cell 4 - ER | #987655 | GH3 | 2025-02-28 | 2025-03-06
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO4 Cell 4 - ER | #FFFDA5 | EE23 | 2025-03-03 | 2025-03-07
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO4 Cell 4 - ER | #FFFDA5 | EE28 | 2025-03-04 | 2025-03-10
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | #FFFDA5 | EE72 | 2025-02-27 | 2025-03-12
COLO 4 | Cell 4 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO4 Cell 4 - ER | #3399FF | J36 | 2025-03-10 | 2025-03-14
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER | #FFFDA5 | EE29 | 2025-04-22 | 2025-05-12
COLO 4 | Cell 4 | Electrical Room | All Trades | Finishes and Signage - COLO4 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-05-06 | 2025-05-12
COLO 4 | Cell 4 | Data Hall | Gurtz Electric | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 4 - DH | #FFFDA5 | EE74 | 2025-02-13 | 2025-02-28
COLO 4 | Cell 4 | Data Hall | Anning - Johnson | Security Screen Installation - COLO4 Cell 4 - DH | #3399FF | J6 | 2025-03-04 | 2025-03-06
COLO 4 | Cell 4 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO4 Cell 4 - DH | #3399FF | J7 | 2025-03-07 | 2025-03-13
COLO 4 | Cell 4 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 4 - DH | #FFFDA5 | EE73 | 2025-03-14 | 2025-03-27
COLO 4 | Cell 4 | Data Hall | Gurtz Electric | Install PDU's - COLO4 Cell 4 - DH | #FFFDA5 | EE7 | 2025-03-28 | 2025-04-03
COLO 4 | Cell 4 | Data Hall | Interior System | Begin HAC Assembly - COLO4 Cell 4 - DH | #FED7E8 | S1 | 2025-03-28 | 2025-04-03
COLO 4 | Cell 4 | Data Hall | Gurtz Electric | Install Busway - COLO4 Cell 4 - DH | #FFFDA5 | EE10 | 2025-04-01 | 2025-04-07
COLO 4 | Cell 4 | Data Hall | Interior System | HAC install and Rise - COLO4 Cell 4 - DH | #FED7E8 | S2 | 2025-04-04 | 2025-04-10
COLO 4 | Cell 4 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO4 Cell 4 - DH | #FFFDA5 | EE17 | 2025-04-04 | 2025-04-17
COLO 4 | Cell 4 | Data Hall | WALSH | Closing Construction Access Door - COLO4 Cell 4 - DH | #04A261 | W4 | 2025-04-04 | 2025-04-24
COLO 4 | Cell 4 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH | #EF9E5B | ET7 | 2025-04-11 | 2025-04-24
COLO 4 | Cell 4 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO4 Cell 4 - DH | #FFFDA5 | EE18 | 2025-04-22 | 2025-05-12
COLO 4 | Cell 4 | Data Hall | All Trades | Finishes and Signage - COLO4 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-05-06 | 2025-05-12
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO4 Cell 4 | #FFFDA5 | EE57 | 2025-03-06 | 2025-03-10
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO4 Cell 4 | #FFFDA5 | EE60 | 2025-03-06 | 2025-03-10
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO4 Cell 4 | #FFFDA5 | EE58 | 2025-03-06 | 2025-03-10
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO4 Cell 4 | #FFFDA5 | EE62 | 2025-03-10 | 2025-03-12
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO4 Cell 4 | #FFFDA5 | EE59 | 2025-03-11 | 2025-03-13
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO4 Cell 4 | #FFFDA5 | EE63 | 2025-04-04 | 2025-04-08
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO4 Cell 4 | #FFFDA5 | EE61 | 2025-04-08 | 2025-04-10
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO4 Cell 4 | #FFFDA5 | EE57 | 2025-05-13 | 2025-05-19
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO4 Cell 4 | #FFFDA5 | EE62 | 2025-05-20 | 2025-05-27
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO4 Cell 4 | #FFFDA5 | EE63 | 2025-05-20 | 2025-05-27
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO4 Cell 4 | #FFFDA5 | EE58 | 2025-05-20 | 2025-05-27
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO4 Cell 4 | #FFFDA5 | EE60 | 2025-05-28 | 2025-06-03
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO4 Cell 4 | #FFFDA5 | EE61 | 2025-05-28 | 2025-06-03
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO4 Cell 4 | #FFFDA5 | EE59 | 2025-07-16 | 2025-07-23
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO4 Cell 4 | #FFFDA5 | EE57 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO4 Cell 4 | #FFFDA5 | EE62 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO4 Cell 4 | #FFFDA5 | EE63 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO4 Cell 4 | #FFFDA5 | EE58 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO4 Cell 4 | #FFFDA5 | EE60 | 2025-10-20 | 2025-10-24
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO4 Cell 4 | #FFFDA5 | EE59 | 2025-10-27 | 2025-11-07
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO4 Cell 4 | #FFFDA5 | EE61 | 2025-11-10 | 2025-11-14
COLO 4 | All | CX - Microsoft | Microsoft | Level 4 Cx - Colo 4 | #000000 | MS1 | 2025-11-18 | 2025-12-16
COLO 4 | All | CX - Microsoft | Microsoft | Level 5 Cx / IST - Colo 4 | #000000 | MS2 | 2025-12-18 | 2025-12-19
Fiber | All | All | WALSH | MVS Fiber Procurement | #04A261 | W15 | 2024-12-09 | 2025-01-31
Fiber | All | All | WALSH | MVS Fiber Shipping | #04A261 | W16 | 2025-02-03 | 2025-02-14
Fiber | All | All | Gurtz Electric Telecom | Pull, Splice, & Test (3) UTS Fiber | #EF9E5B | ET30 | 2025-02-17 | 2025-03-13
Fiber | All | All | Gurtz Electric Telecom | Pull, Splice, & Test (5) UMS/URS Fiber | #EF9E5B | ET31 | 2025-02-17 | 2025-03-13
Fiber | COLO 2 | All | WALSH | Generator CEI Fiber Shipping Colo 2 | #04A261 | W6 | 2024-12-23 | 2025-01-22
Fiber | COLO 2 | All | WALSH | Backbone CEI Fiber Shipping Colo 2 | #04A261 | W7 | 2025-01-10 | 2025-01-23
Fiber | COLO 2 | All | WALSH | Interior CEI CAT6 Procurement Colo 2 | #04A261 | W9 | 2024-12-09 | 2025-01-28
Fiber | COLO 2 | All | Gurtz Electric | Pull Generator Fiber Colo 2 | #FFFDA5 | EE60 | 2025-01-23 | 2025-01-29
Fiber | COLO 2 | All | Gurtz Electric Telecom | Pull Backbone Fiber Colo 2 (CEI to FCR) | #EF9E5B | ET24 | 2025-01-24 | 2025-02-06
Fiber | COLO 2 | All | WALSH | Interior CEI CAT6 Shipping Colo 2 | #04A261 | W9 | 2025-01-29 | 2025-02-11
Fiber | COLO 2 | All | WALSH | 3456 Fiber Procurement Colo 2 | #04A261 | W12 | 2024-12-02 | 2025-03-05
Fiber | COLO 2 | All | WALSH | 288 Fiber Procurement Colo 2 | #04A261 | W11 | 2024-12-02 | 2025-03-10
Fiber | COLO 2 | All | Gurtz Electric Telecom | Pull Interior CEI CAT6 Colo 2 | #EF9E5B | ET28 | 2025-02-12 | 2025-03-11
Fiber | COLO 2 | All | WALSH | 3456 Fiber Shipping Colo 2 | #04A261 | W14 | 2025-03-06 | 2025-03-19
Fiber | COLO 2 | All | WALSH | 288 Fiber Shipping Colo 2 | #04A261 | W13 | 2025-03-11 | 2025-03-24
Fiber | COLO 2 | All | Gurtz Electric Telecom | Pull, Splice, & Test UPM Fiber Colo 2 | #EF9E5B | ET32 | 2025-03-14 | 2025-03-27
Fiber | COLO 2 | All | Gurtz Electric Telecom | 3456 Fiber Install, Populate, & Test Colo 2 | #EF9E5B | ET9 | 2025-03-20 | 2025-04-23
Fiber | COLO 2 | All | Gurtz Electric Telecom | 288 Fiber Install, Populate, & Test Colo 2 | #EF9E5B | ET11 | 2025-03-25 | 2025-05-19
Fiber | COLO 2 | All | Gurtz Electric Telecom | RNI Colo 2 | #EF9E5B | ET29 | 2025-05-20 | 2025-05-20
Fiber | COLO 3 | All | WALSH | Backbone CEI Fiber Procurement Colo 3 | #04A261 | W5 | 2024-12-09 | 2025-01-23
Fiber | COLO 3 | All | WALSH | Generator CEI Fiber Shipping Colo 3 | #04A261 | W6 | 2025-01-10 | 2025-01-24
Fiber | COLO 3 | All | WALSH | Backbone CEI Fiber Shipping Colo 3 | #04A261 | W7 | 2025-01-16 | 2025-01-29
Fiber | COLO 3 | All | WALSH | Interior CEI CAT6 Procurement Colo 3 | #04A261 | W9 | 2024-12-09 | 2025-02-11
Fiber | COLO 3 | All | Gurtz Electric | Pull Generator Fiber Colo 3 | #FFFDA5 | EE60 | 2025-02-06 | 2025-02-12
Fiber | COLO 3 | All | WALSH | Interior CEI CAT6 Shipping Colo 3 | #04A261 | W10 | 2025-02-12 | 2025-02-25
Fiber | COLO 3 | All | WALSH | 3456 Fiber Procurement Colo 3 | #04A261 | W12 | 2024-12-02 | 2025-03-05
Fiber | COLO 3 | All | Gurtz Electric Telecom | Pull Backbone Fiber Colo 3 (CEI to FCR) | #EF9E5B | ET24 | 2025-02-21 | 2025-03-06
Fiber | COLO 3 | All | WALSH | 3456 Fiber Shipping Colo 3 | #04A261 | W14 | 2025-03-06 | 2025-03-19
Fiber | COLO 3 | All | WALSH | 288 Fiber Procurement Colo 3 | #04A261 | W11 | 2024-12-02 | 2025-03-25
Fiber | COLO 3 | All | Gurtz Electric Telecom | Colo 3 UPM Ready for Fiber (L1 Complete Per Option 1) | #EF9E5B | ET26 | 2025-04-07 | 2025-04-07
Fiber | COLO 3 | All | WALSH | 288 Fiber Shipping Colo 3 | #04A261 | W13 | 2025-03-26 | 2025-04-08
Fiber | COLO 3 | All | Gurtz Electric Telecom | Pull, Splice, & Test UPM Fiber Colo 3 | #EF9E5B | ET32 | 2025-03-28 | 2025-04-10
Fiber | COLO 3 | All | Gurtz Electric Telecom | Pull Interior CEI CAT 6 Colo 3 | #EF9E5B | ET28 | 2025-04-09 | 2025-05-06
Fiber | COLO 3 | All | Gurtz Electric Telecom | Colo 3 UPM Ready for Fiber (L1 Complete Per Option 2) | #EF9E5B | ET27 | 2025-05-30 | 2025-05-30
Fiber | COLO 3 | All | Gurtz Electric Telecom | 3456 Fiber Install, Populate, & Test Colo 3 | #EF9E5B | ET9 | 2025-06-05 | 2025-07-09
Fiber | COLO 3 | All | Gurtz Electric Telecom | 288 Fiber Install, Populate, & Test Colo 3 | #EF9E5B | ET11 | 2025-07-15 | 2025-09-08
Fiber | COLO 3 | All | Gurtz Electric Telecom | RNI Colo 3 | #EF9E5B | ET29 | 2025-09-09 | 2025-09-09
Fiber | COLO 4 | All | WALSH | Backbone CEI Fiber Procurement Colo 4 | #04A261 | W5 | 2024-12-09 | 2025-01-27
Fiber | COLO 4 | All | WALSH | Generator CEI Fiber Procurement Colo 4 | #04A261 | W6 | 2024-12-09 | 2025-02-07
Fiber | COLO 4 | All | WALSH | Backbone CEI Fiber Shipping Colo 4 | #04A261 | W7 | 2025-01-28 | 2025-02-10
Fiber | COLO 4 | All | WALSH | Generator CEI Fiber Shipping Colo 4 | #04A261 | W8 | 2025-02-10 | 2025-02-21
Fiber | COLO 4 | All | WALSH | Interior CEI CAT6 Procurement Colo 4 | #04A261 | W9 | 2024-12-09 | 2025-02-25
Fiber | COLO 4 | All | Gurtz Electric | Pull Generator CAT6 Colo 4 | #FFFDA5 | EE60 | 2025-02-24 | 2025-02-28
Fiber | COLO 4 | All | WALSH | Interior CEI Fiber Shipping Colo 4 | #04A261 | W10 | 2025-02-26 | 2025-03-11
Fiber | COLO 4 | All | Gurtz Electric Telecom | Pull Backbone Fiber Colo 4 (CEI to FCR) | #EF9E5B | ET24 | 2025-03-07 | 2025-03-20
Fiber | COLO 4 | All | WALSH | 288 Fiber Procurement Colo 4 | #04A261 | W11 | 2024-12-02 | 2025-03-24
Fiber | COLO 4 | All | WALSH | 3456 Fiber Procurement Colo 4 | #04A261 | W12 | 2024-12-02 | 2025-03-31
Fiber | COLO 4 | All | WALSH | 288 Fiber Shipping Colo 4 | #04A261 | W13 | 2025-03-25 | 2025-04-07
Fiber | COLO 4 | All | WALSH | 3456 Fiber Shipping Colo 4 | #04A261 | W14 | 2025-04-01 | 2025-04-14
Fiber | COLO 4 | All | Gurtz Electric Telecom | Pull, Splice, & Test UPM Fiber Colo 4 | #EF9E5B | ET25 | 2025-04-11 | 2025-04-24
Fiber | COLO 4 | All | Gurtz Electric Telecom | Colo 4 UPM Ready for Fiber (L1 Complete Option 1) | #EF9E5B | ET26 | 2025-05-08 | 2025-05-08
Fiber | COLO 4 | All | Gurtz Electric Telecom | Colo 4 UPM Ready for Fiber (L1 Complete Option 2) | #EF9E5B | ET27 | 2025-05-30 | 2025-05-30
Fiber | COLO 4 | All | Gurtz Electric Telecom | Pull Interior Fiber Colo 4 | #EF9E5B | ET28 | 2025-05-07 | 2025-06-03
Fiber | COLO 4 | All | Gurtz Electric Telecom | 3456 Fiber Install, Populate, & Test Colo 4 | #EF9E5B | ET9 | 2025-07-10 | 2025-08-13
Fiber | COLO 4 | All | Gurtz Electric Telecom | 288 Fiber Install, Populate, & Test Colo 4 | #EF9E5B | ET11 | 2025-09-09 | 2025-11-03
Fiber | COLO 4 | All | Gurtz Electric Telecom | RNI Colo 4 | #EF9E5B | ET29 | 2025-11-04 | 2025-11-04
Fiber | COLO 5 | All | WALSH | Generator CEI Fiber Shipping Colo 5 | #04A261 | W8 | 2024-12-23 | 2025-01-22
Fiber | COLO 5 | All | WALSH | Backbone CEI Fiber Shipping Colo 5 | #04A261 | W7 | 2025-01-10 | 2025-01-23
Fiber | COLO 5 | All | Gurtz Electric | Pull Generator Fiber Colo 5 | #FFFDA5 | EE60 | 2025-01-30 | 2025-02-05
Fiber | COLO 5 | All | WALSH | Interior CEI Fiber Procurement Colo 5 | #04A261 | W9 | 2024-12-09 | 2025-02-11
Fiber | COLO 5 | All | WALSH | 288 Fiber Procurement Colo 5 | #04A261 | W11 | 2024-12-02 | 2025-02-12
Fiber | COLO 5 | All | Gurtz Electric Telecom | Pull Backbone Fiber Colo 5 (CEI to FCR) | #EF9E5B | ET24 | 2025-02-07 | 2025-02-20
Fiber | COLO 5 | All | WALSH | Interior CEI CAT6 Shipping Colo 5 | #04A261 | W10 | 2025-02-12 | 2025-02-25
Fiber | COLO 5 | All | WALSH | 288 Fiber Shipping Colo 5 | #04A261 | W13 | 2025-02-13 | 2025-02-26
Fiber | COLO 5 | All | WALSH | 3456 Fiber Procurement Colo 5 | #04A261 | W12 | 2024-12-02 | 2025-03-05
Fiber | COLO 5 | All | WALSH | 3456 Fiber Shipping Colo 5 | #04A261 | W14 | 2025-03-06 | 2025-03-19
Fiber | COLO 5 | All | Gurtz Electric Telecom | Pull Interior CAT6 Colo 5 | #EF9E5B | ET28 | 2025-03-12 | 2025-04-08
Fiber | COLO 5 | All | Gurtz Electric Telecom | Pull, Splice, & Test UPM Fiber Colo 5 | #EF9E5B | ET32 | 2025-03-28 | 2025-04-10
Fiber | COLO 5 | All | Gurtz Electric Telecom | Colo 5 UPM Ready for Fiber (L1 Complete Per Option 1) | #EF9E5B | ET26 | 2025-05-29 | 2025-05-29
Fiber | COLO 5 | All | Gurtz Electric Telecom | 3456 Fiber Install, Populate, & Test Colo 5 | #EF9E5B | ET9 | 2025-04-24 | 2025-06-04
Fiber | COLO 5 | All | Gurtz Electric Telecom | Colo 5 UPM Ready for Fiber (L1 Complete Per Option 2) | #EF9E5B | ET27 | 2025-06-17 | 2025-06-17
Fiber | COLO 5 | All | Gurtz Electric Telecom | 288 Fiber Install, Populate, & Test Colo 5 | #EF9E5B | ET11 | 2025-05-20 | 2025-07-14
Fiber | COLO 5 | All | Gurtz Electric Telecom | RNI Colo 5 | #EF9E5B | ET29 | 2025-07-15 | 2025-07-15
UPM | COLO 2 | Site | Gurtz Electric | Relocate 2 UPMs to Colo 2 | #FFFDA5 | EE61 | 2025-01-17 | 2025-01-20
UPM | COLO 2 | Site | Gurtz Electric | Term Wires to Relocated UPMs (2) | #FFFDA5 | EE62 | 2025-01-21 | 2025-02-10
UPM | COLO 2 | Site | Gurtz Electric | Complete L1 on Relocated UPMs | #FFFDA5 | EE63 | 2025-02-11 | 2025-02-11
UPM | COLO 3 | Site | Gurtz Electric | UPM ROJ (Qty: 4) | #FFFDA5 | EE64 | 2025-01-06 | 2025-05-30
UPM | COLO 3 | Site | Gurtz Electric | Install UPM (Total 4) | #FFFDA5 | EE65 | 2025-06-02 | 2025-06-11
UPM | COLO 3 | Site | Gurtz Electric | L1 UPM | #FFFDA5 | EE66 | 2025-06-13 | 2025-06-13
UPM | COLO 3 | Site | Gurtz Electric | Complete Wire Terms | #FFFDA5 | EE67 | 2025-06-16 | 2025-07-04
UPM | COLO 4 | Site | Gurtz Electric | UPM ROJ (Qty: 4) | #FFFDA5 | EE64 | 2025-01-06 | 2025-05-30
UPM | COLO 4 | Site | Gurtz Electric | Install UPM (Total 4) | #FFFDA5 | EE65 | 2025-06-12 | 2025-06-23
UPM | COLO 4 | Site | Gurtz Electric | L1 UPM | #FFFDA5 | EE66 | 2025-06-24 | 2025-06-24
UPM | COLO 4 | Site | Gurtz Electric | Complete Wire Terms | #FFFDA5 | EE67 | 2025-06-25 | 2025-07-15
UPM | COLO 5 | Site | Gurtz Electric | UPM ROJ (Qty: 3) | #FFFDA5 | EE64 | 2025-01-06 | 2025-05-30
UPM | COLO 5 | Site | Gurtz Electric | Install UPM (Total 3) | #FFFDA5 | EE65 | 2025-06-02 | 2025-06-09
UPM | COLO 5 | Site | Gurtz Electric | L1 UPM | #FFFDA5 | EE66 | 2025-06-10 | 2025-06-10
UPM | COLO 5 | Site | Gurtz Electric | Complete Wire Terms | #FFFDA5 | EE67 | 2025-06-11 | 2025-06-24
Exhaust System | Non-Installed Sets | All | WALSH | (8) Sets Returned to Manufacture | #04A261 | W16 | 2025-01-21 | 2025-01-22
Exhaust System | Non-Installed Sets | All | WALSH | (8) Sets Re-Finished | #04A261 | W17 | 2025-01-23 | 2025-02-06
Exhaust System | Non-Installed Sets | All | WALSH | (8) Sets Shipped Back to Jobsite | #04A261 | W18 | 2025-02-07 | 2025-02-08
Exhaust System | Installed Sets | All | Gurtz Electric | (8) Remove Installed Set Off of Generators | #FFFDA5 | EE68 | 2025-01-21 | 2025-02-19
Exhaust System | Installed Sets | All | WALSH | (8) Sets Returned to Manufacture | #04A261 | W16 | 2025-02-20 | 2025-02-21
Exhaust System | Installed Sets | All | WALSH | (8) Sets Re-Finished | #04A261 | W17 | 2025-02-22 | 2025-03-07
Exhaust System | Installed Sets | All | WALSH | (8) Sets Shipped Back to Jobsite | #04A261 | W18 | 2025-03-08 | 2025-03-10
Exhaust System | COLO 2 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SW) | #FFFDA5 | EE69 | 2025-02-17 | 2025-02-19
Exhaust System | COLO 2 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SE) | #FFFDA5 | EE70 | 2025-02-20 | 2025-02-22
Exhaust System | COLO 2 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NE) | #FFFDA5 | EE71 | 2025-02-24 | 2025-02-26
Exhaust System | COLO 2 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NW) | #FFFDA5 | EE72 | 2025-02-27 | 2025-03-01
Exhaust System | COLO 5 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SE) | #FFFDA5 | EE70 | 2025-02-10 | 2025-02-12
Exhaust System | COLO 5 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NE) | #FFFDA5 | EE71 | 2025-02-13 | 2025-02-15
Exhaust System | COLO 5 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NW) | #FFFDA5 | EE72 | 2025-03-03 | 2025-03-05
Exhaust System | COLO 5 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SW) | #FFFDA5 | EE69 | 2025-03-06 | 2025-03-08
Exhaust System | COLO 3 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SW) | #FFFDA5 | EE69 | 2025-03-11 | 2025-03-13
Exhaust System | COLO 3 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SE) | #FFFDA5 | EE70 | 2025-03-14 | 2025-03-17
Exhaust System | COLO 3 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NE) | #FFFDA5 | EE71 | 2025-04-01 | 2025-04-03
Exhaust System | COLO 3 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NW) | #FFFDA5 | EE72 | 2025-04-04 | 2025-04-07
Exhaust System | COLO 4 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SW) | #FFFDA5 | EE69 | 2025-03-18 | 2025-03-20
Exhaust System | COLO 4 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SE) | #FFFDA5 | EE70 | 2025-03-21 | 2025-03-24
Exhaust System | COLO 4 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NE) | #FFFDA5 | EE71 | 2025-03-25 | 2025-03-27
Exhaust System | COLO 4 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NW) | #FFFDA5 | EE72 | 2025-03-28 | 2025-03-31

## CFA - Schedule
|  |  | 2024 | [7 empty] | 2024 | [7 empty] | 2024 | [7 empty] | 2024 | [7 empty] | 2024 | [7 empty] | 2024 | [7 empty] | 2024 | 2024 | 2024 | 2025 |  |  |  |  | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025 | [7 empty] | 2025
|  |  | Nov | [7 empty] | Nov | [7 empty] | Nov | Nov | Nov | Nov | Dec |  |  |  | Dec | [7 empty] | Dec | [7 empty] | Dec | [7 empty] | Dec | Dec | Dec | Jan |  |  |  |  | Jan | [7 empty] | Jan | [7 empty] | Jan | [7 empty] | Jan | Jan | Feb | [5 empty] | Feb | [7 empty] | Feb | [7 empty] | Feb | Feb | Feb | Feb | Feb | Feb | Mar |  | Mar | [7 empty] | Mar | [7 empty] | Mar | [7 empty] | Mar | Mar | Mar | Mar | Mar | Apr |  |  | Apr | [7 empty] | Apr | [7 empty] | Apr | [7 empty] | Apr | Apr | Apr | May |  |  |  |  | May | [7 empty] | May | [7 empty] | May | [7 empty] | May | May | Jun | [5 empty] | Jun | [7 empty] | Jun | [7 empty] | Jun | [7 empty] | Jul | Jul | [6 empty] | Jul | [7 empty] | Jul | [7 empty] | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Aug | Aug | [7 empty] | Aug | [7 empty] | Aug | [7 empty] | Aug | Aug | Aug | Aug | Aug | Aug | Sep |  | Sep | [7 empty] | Sep | [7 empty] | Sep | [7 empty] | Sep | Sep | Sep | Sep | Oct |  |  |  | Oct | [7 empty] | Oct | [7 empty] | Oct | [7 empty] | Oct | Oct | Oct | Nov |  |  |  |  | Nov | [7 empty] | Nov | [7 empty] | Nov | [7 empty] | Nov | Dec | [6 empty] | Dec | [7 empty] | Dec
|  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
phase | location | area | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Fiber | All | All | 09 Mon: W15; 10 Tue: W15; 11 Wed: W15; 12 Thu: W15; 13 Fri: W15; 14 Sat: W15; 15 Sun: W15; 16 Mon: W15; 17 Tue: W15; 18 Wed: W15; 19 Thu: W15; 20 Fri: W15; 21 Sat: W15; 22 Sun: W15; 23 Mon: W15; 24 Tue: W15; 25 Wed: W15; 26 Thu: W15; 27 Fri: W15; 28 Sat: W15; 29 Sun: W15; 30 Mon: W15; 31 Tue: W15; 01 Wed: W15; 02 Thu: W15; 03 Fri: W15; 04 Sat: W15; 05 Sun: W15; 06 Mon: W15; 07 Tue: W15; 08 Wed: W15; 09 Thu: W15; 10 Fri: W15; 11 Sat: W15; 12 Sun: W15; 13 Mon: W15; 14 Tue: W15; 15 Wed: W15; 16 Thu: W15; 17 Fri: W15; 18 Sat: W15; 19 Sun: W15; 20 Mon: W15; 21 Tue: W15; 22 Wed: W15; 23 Thu: W15; 24 Fri: W15; 25 Sat: W15; 26 Sun: W15; 27 Mon: W15; 28 Tue: W15; 29 Wed: W15; 30 Thu: W15; 31 Fri: W15; 03 Mon: W16; 04 Tue: W16; 05 Wed: W16; 06 Thu: W16; 07 Fri: W16; 08 Sat: W16; 09 Sun: W16; 10 Mon: W16; 11 Tue: W16; 12 Wed: W16; 13 Thu: W16; 14 Fri: W16; 17 Mon: ET30; 18 Tue: ET30; 19 Wed: ET30; 20 Thu: ET30; 21 Fri: ET30; 22 Sat: ET30; 23 Sun: ET30; 24 Mon: ET30; 25 Tue: ET30; 26 Wed: ET30; 27 Thu: ET30; 28 Fri: ET30; 01 Sat: ET30; 02 Sun: ET30; 03 Mon: ET30; 04 Tue: ET30; 05 Wed: ET30; 06 Thu: ET30; 07 Fri: ET30; 08 Sat: ET30; 09 Sun: ET30; 10 Mon: ET30; 11 Tue: ET30; 12 Wed: ET30; 13 Thu: ET30
[101 empty] | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31 | ET31
| COLO 2 | All | 02 Mon: W12; 03 Tue: W12; 04 Wed: W12; 05 Thu: W12; 06 Fri: W12; 07 Sat: W12; 08 Sun: W12; 09 Mon: W12; 10 Tue: W12; 11 Wed: W12; 12 Thu: W12; 13 Fri: W12; 14 Sat: W12; 15 Sun: W12; 16 Mon: W12; 17 Tue: W12; 18 Wed: W12; 19 Thu: W12; 20 Fri: W12; 21 Sat: W12; 22 Sun: W12; 23 Mon: W12; 24 Tue: W12; 25 Wed: W12; 26 Thu: W12; 27 Fri: W12; 28 Sat: W12; 29 Sun: W12; 30 Mon: W12; 31 Tue: W12; 01 Wed: W12; 02 Thu: W12; 03 Fri: W12; 04 Sat: W12; 05 Sun: W12; 06 Mon: W12; 07 Tue: W12; 08 Wed: W12; 09 Thu: W12; 10 Fri: W12; 11 Sat: W12; 12 Sun: W12; 13 Mon: W12; 14 Tue: W12; 15 Wed: W12; 16 Thu: W12; 17 Fri: W12; 18 Sat: W12; 19 Sun: W12; 20 Mon: W12; 21 Tue: W12; 22 Wed: W12; 23 Thu: W12; 24 Fri: W12; 25 Sat: W12; 26 Sun: W12; 27 Mon: W12; 28 Tue: W12; 29 Wed: W12; 30 Thu: W12; 31 Fri: W12; 01 Sat: W12; 02 Sun: W12; 03 Mon: W12; 04 Tue: W12; 05 Wed: W12; 06 Thu: W12; 07 Fri: W12; 08 Sat: W12; 09 Sun: W12; 10 Mon: W12; 11 Tue: W12; 12 Wed: W12; 13 Thu: W12; 14 Fri: W12; 15 Sat: W12; 16 Sun: W12; 17 Mon: W12; 18 Tue: W12; 19 Wed: W12; 20 Thu: W12; 21 Fri: W12; 22 Sat: W12; 23 Sun: W12; 24 Mon: W12; 25 Tue: W12; 26 Wed: W12; 27 Thu: W12; 28 Fri: W12; 01 Sat: W12; 02 Sun: W12; 03 Mon: W12; 04 Tue: W12; 05 Wed: W12; 06 Thu: W14; 07 Fri: W14; 08 Sat: W14; 09 Sun: W14; 10 Mon: W14; 11 Tue: W14; 12 Wed: W14; 13 Thu: W14; 14 Fri: W14; 15 Sat: W14; 16 Sun: W14; 17 Mon: W14; 18 Tue: W14; 19 Wed: W14; 20 Thu: ET9; 21 Fri: ET9; 22 Sat: ET9; 23 Sun: ET9; 24 Mon: ET9; 25 Tue: ET9; 26 Wed: ET9; 27 Thu: ET9; 28 Fri: ET9; 29 Sat: ET9; 30 Sun: ET9; 31 Mon: ET9; 01 Tue: ET9; 02 Wed: ET9; 03 Thu: ET9; 04 Fri: ET9; 05 Sat: ET9; 06 Sun: ET9; 07 Mon: ET9; 08 Tue: ET9; 09 Wed: ET9; 10 Thu: ET9; 11 Fri: ET9; 12 Sat: ET9; 13 Sun: ET9; 14 Mon: ET9; 15 Tue: ET9; 16 Wed: ET9; 17 Thu: ET9; 18 Fri: ET9; 19 Sat: ET9; 20 Sun: ET9; 21 Mon: ET9; 22 Tue: ET9; 23 Wed: ET9; 20 Tue: ET29
[24 empty] | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11
[31 empty] | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 |  |  | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32
[45 empty] | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
[63 empty] | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24
| COLO 3 | All | [21 empty] | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | [6 empty] | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | [23 empty] | ET27 | [5 empty] | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | [5 empty] | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET29
[24 empty] | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 |  |  | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32 | ET32
[31 empty] | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | [13 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | [8 empty] | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | [31 empty] | ET26
[31 empty] | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10
[63 empty] | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6
[69 empty] | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7
| COLO 4 | All | [21 empty] | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W11 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 | W13 |  |  |  | ET25 | ET25 | ET25 | ET25 | ET25 | ET25 | ET25 | ET25 | ET25 | ET25 | ET25 | ET25 | ET25 | ET25 | [12 empty] | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | [36 empty] | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | ET9 | [26 empty] | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET29
[24 empty] | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | W14 | [23 empty] | ET26 | [21 empty] | ET27
[31 empty] | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W5 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | [13 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | [6 empty] | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24
[31 empty] | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 | W6 |  |  | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 |  |  |  |  | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10
[31 empty] | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9
| COLO 5 | All | 02 Mon: W11; 03 Tue: W11; 04 Wed: W11; 05 Thu: W11; 06 Fri: W11; 07 Sat: W11; 08 Sun: W11; 09 Mon: W11; 10 Tue: W11; 11 Wed: W11; 12 Thu: W11; 13 Fri: W11; 14 Sat: W11; 15 Sun: W11; 16 Mon: W11; 17 Tue: W11; 18 Wed: W11; 19 Thu: W11; 20 Fri: W11; 21 Sat: W11; 22 Sun: W11; 23 Mon: W11; 24 Tue: W11; 25 Wed: W11; 26 Thu: W11; 27 Fri: W11; 28 Sat: W11; 29 Sun: W11; 30 Mon: W11; 31 Tue: W11; 01 Wed: W11; 02 Thu: W11; 03 Fri: W11; 04 Sat: W11; 05 Sun: W11; 06 Mon: W11; 07 Tue: W11; 08 Wed: W11; 09 Thu: W11; 10 Fri: W11; 11 Sat: W11; 12 Sun: W11; 13 Mon: W11; 14 Tue: W11; 15 Wed: W11; 16 Thu: W11; 17 Fri: W11; 18 Sat: W11; 19 Sun: W11; 20 Mon: W11; 21 Tue: W11; 22 Wed: W11; 23 Thu: W11; 24 Fri: W11; 25 Sat: W11; 26 Sun: W11; 27 Mon: W11; 28 Tue: W11; 29 Wed: W11; 30 Thu: W11; 31 Fri: W11; 01 Sat: W11; 02 Sun: W11; 03 Mon: W11; 04 Tue: W11; 05 Wed: W11; 06 Thu: W11; 07 Fri: W11; 08 Sat: W11; 09 Sun: W11; 10 Mon: W11; 11 Tue: W11; 12 Wed: W11; 13 Thu: W13; 14 Fri: W13; 15 Sat: W13; 16 Sun: W13; 17 Mon: W13; 18 Tue: W13; 19 Wed: W13; 20 Thu: W13; 21 Fri: W13; 22 Sat: W13; 23 Sun: W13; 24 Mon: W13; 25 Tue: W13; 26 Wed: W13; 06 Thu: W14; 07 Fri: W14; 08 Sat: W14; 09 Sun: W14; 10 Mon: W14; 11 Tue: W14; 12 Wed: W14; 13 Thu: W14; 14 Fri: W14; 15 Sat: W14; 16 Sun: W14; 17 Mon: W14; 18 Tue: W14; 19 Wed: W14; 28 Fri: ET32; 29 Sat: ET32; 30 Sun: ET32; 31 Mon: ET32; 01 Tue: ET32; 02 Wed: ET32; 03 Thu: ET32; 04 Fri: ET32; 05 Sat: ET32; 06 Sun: ET32; 07 Mon: ET32; 08 Tue: ET32; 09 Wed: ET32; 10 Thu: ET32; 24 Thu: ET9; 25 Fri: ET9; 26 Sat: ET9; 27 Sun: ET9; 28 Mon: ET9; 29 Tue: ET9; 30 Wed: ET9; 01 Thu: ET9; 02 Fri: ET9; 03 Sat: ET9; 04 Sun: ET9; 05 Mon: ET9; 06 Tue: ET9; 07 Wed: ET9; 08 Thu: ET9; 09 Fri: ET9; 10 Sat: ET9; 11 Sun: ET9; 12 Mon: ET9; 13 Tue: ET9; 14 Wed: ET9; 15 Thu: ET9; 16 Fri: ET9; 17 Sat: ET9; 18 Sun: ET9; 19 Mon: ET9; 20 Tue: ET9; 21 Wed: ET9; 22 Thu: ET9; 23 Fri: ET9; 24 Sat: ET9; 25 Sun: ET9; 26 Mon: ET9; 27 Tue: ET9; 28 Wed: ET9; 29 Thu: ET9; 30 Fri: ET9; 31 Sat: ET9; 01 Sun: ET9; 02 Mon: ET9; 03 Tue: ET9; 04 Wed: ET9; 17 Tue: ET27; 15 Tue: ET29
[24 empty] | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | W12 | [6 empty] | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | ET28 | [41 empty] | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11 | ET11
[31 empty] | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W9 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | W10 | [92 empty] | ET26
[45 empty] | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | W8 | [7 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 |  | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24 | ET24
[63 empty] | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7 | W7
COLO 5 | All | CX - Microsoft | 2025 Aug 29 Mon: MS1; 2025 Aug 30 Tue: MS1; 2025 Aug 01 Wed: MS1; 2025 Aug 02 Thu: MS1; 2025 Aug 03 Fri: MS1; 2025 Aug 04 Sat: MS1; 2025 Aug 05 Sun: MS1; 2025 Aug 06 Mon: MS1; 2025 Aug 07 Tue: MS1; 2025 Aug 08 Wed: MS1; 2025 Aug 09 Thu: MS1; 2025 Aug 10 Fri: MS1; 2025 Aug 11 Sat: MS1; 2025 Aug 12 Sun: MS1; 2025 Aug 13 Mon: MS1; 2025 Aug 14 Tue: MS1; 2025 Aug 15 Wed: MS1; 2025 Aug 16 Thu: MS1; 2025 Aug 17 Fri: MS1; 2025 Aug 18 Sat: MS1; 2025 Aug 19 Sun: MS1; 2025 Aug 20 Mon: MS1; 2025 Aug 21 Tue: MS1; 2025 Aug 22 Wed: MS1; 2025 Aug 23 Thu: MS1; 2025 Aug 24 Fri: MS1; 2025 Aug 27 Mon: MS2; 2025 Aug 28 Tue: MS2
| Cell 1 | CX - L2 | 17 Mon: EE57; 18 Tue: EE57; 19 Wed: EE57; 20 Thu: EE57; 21 Fri: EE57; 24 Mon: EE62; 25 Tue: EE62; 26 Wed: EE62; 27 Thu: EE62; 28 Fri: EE62; 31 Mon: EE63; 01 Tue: EE63; 02 Wed: EE63; 03 Thu: EE63; 04 Fri: EE63
[136 empty] | EE58 | EE58 | EE58 | EE58 | EE58 |  |  | EE59 | EE59 | EE59 | EE59 | EE59
[143 empty] | EE60 | EE60 | EE60 | EE60 | EE60
[143 empty] | EE61 | EE61 | EE61 | EE61 | EE61
|  | CX - L3 | 2025 Aug 04 Mon: EE57; 2025 Aug 05 Tue: EE57; 2025 Aug 06 Wed: EE57; 2025 Aug 07 Thu: EE57; 2025 Aug 08 Fri: EE57; 2025 Aug 11 Mon: EE62; 2025 Aug 12 Tue: EE62; 2025 Aug 13 Wed: EE62; 2025 Aug 14 Thu: EE62; 2025 Aug 15 Fri: EE62; 2025 Aug 18 Mon: EE60; 2025 Aug 19 Tue: EE60; 2025 Aug 20 Wed: EE60; 2025 Aug 21 Thu: EE60; 2025 Aug 22 Fri: EE60; 2025 Aug 25 Mon: EE61; 2025 Aug 26 Tue: EE61; 2025 Aug 27 Wed: EE61; 2025 Aug 28 Thu: EE61; 2025 Aug 29 Fri: EE61
[269 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE58 | EE58 | EE58 | EE58 | EE58
[278 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | Data Hall | 17 Fri: EE18; 18 Sat: EE18; 19 Sun: EE18; 20 Mon: EE18; 21 Tue: EE18; 22 Wed: EE18; 23 Thu: EE18; 24 Fri: EE18; 25 Sat: EE18; 26 Sun: EE18; 27 Mon: EE18; 28 Tue: EE18; 29 Wed: EE18; 30 Thu: EE18; 31 Fri: EE18; 01 Sat: EE18; 02 Sun: EE18; 03 Mon: EE18; 04 Tue: EE18; 05 Wed: EE18; 06 Thu: EE18; 07 Fri: ALL3; 08 Sat: ALL3; 09 Sun: ALL3; 10 Mon: ALL3; 11 Tue: ALL3; 12 Wed: ALL3; 13 Thu: ALL3
|  | Electrical Room | 31 Tue: EE29; 01 Wed: EE29; 02 Thu: EE29; 03 Fri: EE29; 04 Sat: EE29; 05 Sun: EE29; 06 Mon: EE29; 07 Tue: EE29; 08 Wed: EE29; 09 Thu: EE29; 10 Fri: EE29; 11 Sat: EE29; 12 Sun: EE29; 13 Mon: EE29; 14 Tue: EE29; 15 Wed: EE29; 16 Thu: EE29; 17 Fri: EE29; 18 Sat: EE29; 19 Sun: EE29; 20 Mon: EE29; 21 Tue: EE29; 22 Wed: EE29; 23 Thu: EE29; 24 Fri: EE29; 25 Sat: EE29; 26 Sun: EE29; 27 Mon: EE29; 28 Tue: EE29; 29 Wed: EE29; 30 Thu: EE29; 31 Fri: EE29
[82 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
|  | Mech Gallery | 17 Fri: EE36; 18 Sat: EE36; 19 Sun: EE36; 20 Mon: EE36; 21 Tue: EE36; 22 Wed: EE36; 23 Thu: EE36
| Cell 2 | CX - L2 | 24 Mon: EE57; 25 Tue: EE57; 26 Wed: EE57; 27 Thu: EE57; 28 Fri: EE57; 31 Mon: EE62; 01 Tue: EE62; 02 Wed: EE62; 03 Thu: EE62; 04 Fri: EE62; 07 Mon: EE59; 08 Tue: EE59; 09 Wed: EE59; 10 Thu: EE59; 11 Fri: EE59
[143 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE60 | EE60 | EE60 | EE60 | EE60
[143 empty] | EE58 | EE58 | EE58 | EE58 | EE58 |  |  | EE61 | EE61 | EE61 | EE61 | EE61
|  | CX - L3 | 2025 Aug 07 Thu: EE57; 2025 Aug 08 Fri: EE57; 2025 Aug 09 Sat: EE57; 2025 Aug 10 Sun: EE57; 2025 Aug 11 Mon: EE57; 2025 Aug 12 Tue: EE57; 2025 Aug 13 Wed: EE57; 2025 Aug 14 Thu: EE62; 2025 Aug 15 Fri: EE62; 2025 Aug 16 Sat: EE62; 2025 Aug 17 Sun: EE62; 2025 Aug 18 Mon: EE62; 2025 Aug 19 Tue: EE62; 2025 Aug 20 Wed: EE62; 2025 Aug 21 Thu: EE59; 2025 Aug 22 Fri: EE59; 2025 Aug 23 Sat: EE59; 2025 Aug 24 Sun: EE59; 2025 Aug 25 Mon: EE59; 2025 Aug 26 Tue: EE59; 2025 Aug 27 Wed: EE59; 2025 Aug 28 Thu: EE59; 2025 Aug 29 Fri: EE59; 2025 Aug 30 Sat: EE59; 2025 Aug 31 Sun: EE59; 2025 Aug 01 Mon: EE59; 2025 Aug 02 Tue: EE59; 2025 Aug 03 Wed: EE59; 2025 Aug 04 Thu: EE59
[272 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | [13 empty] | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[272 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | 17 Fri: EE18; 18 Sat: EE18; 19 Sun: EE18; 20 Mon: EE18; 21 Tue: EE18; 22 Wed: EE18; 23 Thu: EE18; 24 Fri: EE18; 25 Sat: EE18; 26 Sun: EE18; 27 Mon: EE18; 28 Tue: EE18; 29 Wed: EE18; 30 Thu: EE18; 31 Fri: EE19; 01 Sat: EE19; 02 Sun: EE19; 03 Mon: EE19; 04 Tue: EE19; 05 Wed: EE19; 06 Thu: EE19; 07 Fri: EE19; 08 Sat: EE19; 09 Sun: EE19; 10 Mon: EE19; 11 Tue: EE19; 12 Wed: EE19; 13 Thu: EE19; 14 Fri: EE19; 15 Sat: EE19; 16 Sun: EE19; 17 Mon: EE19; 18 Tue: EE19; 19 Wed: EE19; 20 Thu: EE19; 21 Fri: ALL3; 22 Sat: ALL3; 23 Sun: ALL3; 24 Mon: ALL3; 25 Tue: ALL3; 26 Wed: ALL3; 27 Thu: ALL3
[70 empty] | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7
|  | Electrical Room | 21 Tue: EE29; 22 Wed: EE29; 23 Thu: EE29; 24 Fri: EE29; 25 Sat: EE29; 26 Sun: EE29; 27 Mon: EE29; 28 Tue: EE29; 29 Wed: EE29; 30 Thu: EE29; 31 Fri: EE29; 01 Sat: EE29; 02 Sun: EE29; 03 Mon: EE29; 14 Fri: ALL3; 15 Sat: ALL3; 16 Sun: ALL3; 17 Mon: ALL3; 18 Tue: ALL3; 19 Wed: ALL3; 20 Thu: ALL3
|  | Mech Gallery | 10 Fri: EE35; 11 Sat: EE35; 12 Sun: EE35; 13 Mon: EE35; 14 Tue: EE35; 15 Wed: EE35; 16 Thu: EE35; 17 Fri: EE35; 18 Sat: EE35; 19 Sun: EE35; 20 Mon: EE35; 21 Tue: EE35; 24 Fri: EE36; 25 Sat: EE36; 26 Sun: EE36; 27 Mon: EE36; 28 Tue: EE36; 29 Wed: EE36; 30 Thu: EE36
| Cell 3 | CX - L2 | 31 Mon: EE57; 01 Tue: EE57; 02 Wed: EE57; 03 Thu: EE57; 04 Fri: EE57; 07 Mon: EE62; 08 Tue: EE62; 09 Wed: EE62; 10 Thu: EE62; 11 Fri: EE62; 14 Mon: EE59; 15 Tue: EE59; 16 Wed: EE59; 17 Thu: EE59; 18 Fri: EE59
[150 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE60 | EE60 | EE60 | EE60 | EE60
[150 empty] | EE58 | EE58 | EE58 | EE58 | EE58 |  |  | EE61 | EE61 | EE61 | EE61 | EE61
|  | CX - L3 | 2025 Aug 14 Thu: EE57; 2025 Aug 15 Fri: EE57; 2025 Aug 16 Sat: EE57; 2025 Aug 17 Sun: EE57; 2025 Aug 18 Mon: EE57; 2025 Aug 19 Tue: EE57; 2025 Aug 20 Wed: EE57; 2025 Aug 21 Thu: EE62; 2025 Aug 22 Fri: EE62; 2025 Aug 23 Sat: EE62; 2025 Aug 24 Sun: EE62; 2025 Aug 25 Mon: EE62; 2025 Aug 26 Tue: EE62; 2025 Aug 27 Wed: EE62; 2025 Aug 03 Wed: EE61; 2025 Aug 04 Thu: EE61; 2025 Aug 05 Fri: EE61; 2025 Aug 06 Sat: EE61; 2025 Aug 07 Sun: EE61; 2025 Aug 08 Mon: EE61; 2025 Aug 09 Tue: EE61
[279 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
[279 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | Data Hall | 10 Fri: EE17; 11 Sat: EE17; 12 Sun: EE17; 13 Mon: EE17; 14 Tue: EE17; 15 Wed: EE17; 16 Thu: EE17; 17 Fri: EE17; 18 Sat: EE17; 19 Sun: EE17; 20 Mon: EE17; 21 Tue: EE17; 22 Wed: EE17; 23 Thu: EE17; 31 Fri: EE18; 01 Sat: EE18; 02 Sun: EE18; 03 Mon: EE18; 04 Tue: EE18; 05 Wed: EE18; 06 Thu: EE18; 07 Fri: EE18; 08 Sat: EE18; 09 Sun: EE18; 10 Mon: EE18; 11 Tue: EE18; 12 Wed: EE18; 13 Thu: EE18; 14 Fri: EE18; 15 Sat: EE18; 16 Sun: EE18; 17 Mon: EE18; 18 Tue: EE18; 19 Wed: EE18; 20 Thu: EE18; 07 Fri: ALL3; 08 Sat: ALL3; 09 Sun: ALL3; 10 Mon: ALL3; 11 Tue: ALL3; 12 Wed: ALL3; 13 Thu: ALL3
|  | Electrical Room | 14 Tue: EE28; 15 Wed: EE28; 16 Thu: EE28; 17 Fri: EE28; 18 Sat: EE28; 19 Sun: EE28; 20 Mon: EE28; 21 Tue: EE18; 22 Wed: EE18; 23 Thu: EE18; 24 Fri: EE18; 25 Sat: EE18; 26 Sun: EE18; 27 Mon: EE18; 28 Tue: EE18; 29 Wed: EE18; 30 Thu: EE18; 31 Fri: EE18; 01 Sat: EE18; 02 Sun: EE18; 03 Mon: EE18; 28 Fri: ALL3; 01 Sat: ALL3; 02 Sun: ALL3; 03 Mon: ALL3; 04 Tue: ALL3; 05 Wed: ALL3; 06 Thu: ALL3
|  | Mech Gallery | 17 Fri: I-R; 18 Sat: I-R; 19 Sun: I-R; 20 Mon: I-R; 22 Wed: EE35; 23 Thu: EE35; 24 Fri: EE35; 25 Sat: EE35; 26 Sun: EE35; 27 Mon: EE35; 28 Tue: EE35; 29 Wed: EE35; 30 Thu: EE35; 31 Fri: EE35; 03 Mon: EE36; 04 Tue: EE36; 05 Wed: EE36; 06 Thu: EE36; 07 Fri: EE36
| Cell 4 | CX - L1 | 24 Fri: EE63
EE59
EE61
EE58
|  | CX - L2 | 07 Mon: EE57; 08 Tue: EE57; 09 Wed: EE57; 10 Thu: EE57; 11 Fri: EE57; 14 Mon: EE62; 15 Tue: EE62; 16 Wed: EE62; 17 Thu: EE62; 18 Fri: EE62; 21 Mon: EE59; 22 Tue: EE59; 23 Wed: EE59; 24 Thu: EE59; 25 Fri: EE59
[157 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE60 | EE60 | EE60 | EE60 | EE60
[157 empty] | EE58 | EE58 | EE58 | EE58 | EE58 |  |  | EE61 | EE61 | EE61 | EE61 | EE61
|  | CX - L3 | 2025 Aug 21 Thu: EE57; 2025 Aug 22 Fri: EE57; 2025 Aug 23 Sat: EE57; 2025 Aug 24 Sun: EE57; 2025 Aug 25 Mon: EE57; 2025 Aug 26 Tue: EE57; 2025 Aug 27 Wed: EE57; 2025 Aug 28 Thu: EE58; 2025 Aug 29 Fri: EE58; 2025 Aug 30 Sat: EE58; 2025 Aug 31 Sun: EE58; 2025 Aug 01 Mon: EE58; 2025 Aug 02 Tue: EE58; 2025 Aug 03 Wed: EE58; 2025 Aug 04 Thu: EE58; 2025 Aug 05 Fri: EE60; 2025 Aug 06 Sat: EE60; 2025 Aug 07 Sun: EE60; 2025 Aug 08 Mon: EE60; 2025 Aug 09 Tue: EE60; 2025 Aug 10 Wed: EE60; 2025 Aug 11 Thu: EE60; 2025 Aug 22 Mon: EE61; 2025 Aug 23 Tue: EE61; 2025 Aug 24 Wed: EE61; 2025 Aug 25 Thu: EE61; 2025 Aug 26 Fri: EE61
[286 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | [13 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62
[306 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | Data Hall | 03 Fri: W4; 04 Sat: W4; 05 Sun: W4; 06 Mon: W4; 07 Tue: W4; 08 Wed: W4; 09 Thu: W4; 10 Fri: W4; 11 Sat: W4; 12 Sun: W4; 13 Mon: W4; 14 Tue: W4; 15 Wed: W4; 16 Thu: W4; 17 Fri: W4; 18 Sat: W4; 19 Sun: W4; 20 Mon: W4; 21 Tue: W4; 22 Wed: W4; 23 Thu: W4; 31 Fri: ET7; 01 Sat: ET7; 02 Sun: ET7; 03 Mon: ET7; 04 Tue: ET7; 05 Wed: ET7; 06 Thu: ET7; 07 Fri: ET7; 08 Sat: ET7; 09 Sun: ET7; 10 Mon: ET7; 11 Tue: ET7; 12 Wed: ET7; 13 Thu: ET7; 21 Fri: EE18; 22 Sat: EE18; 23 Sun: EE18; 24 Mon: EE18; 25 Tue: EE18; 26 Wed: EE18; 27 Thu: EE18; 28 Fri: EE18; 01 Sat: EE18; 02 Sun: EE18; 03 Mon: EE18; 04 Tue: EE18; 05 Wed: EE18; 06 Thu: EE18; 07 Fri: EE18; 08 Sat: EE18; 09 Sun: EE18; 10 Mon: EE18; 11 Tue: EE18; 12 Wed: EE18; 13 Thu: EE18; 21 Fri: ALL3; 22 Sat: ALL3; 23 Sun: ALL3; 24 Mon: ALL3; 25 Tue: ALL3; 26 Wed: ALL3; 27 Thu: ALL3
|  | Electrical Room | 17 Fri: EE27; 18 Sat: EE27; 19 Sun: EE27; 20 Mon: EE27; 21 Tue: EE27; 22 Wed: EE27; 23 Thu: EE27; 28 Tue: EE17; 29 Wed: EE17; 30 Thu: EE17; 31 Fri: EE17; 01 Sat: EE17; 02 Sun: EE17; 03 Mon: EE17; 04 Tue: EE17; 05 Wed: EE17; 06 Thu: EE17; 07 Fri: EE17; 08 Sat: EE17; 09 Sun: EE17; 10 Mon: EE17; 14 Fri: ALL3; 15 Sat: ALL3; 16 Sun: ALL3; 17 Mon: ALL3; 18 Tue: ALL3; 19 Wed: ALL3; 20 Thu: ALL3
[74 empty] | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28
|  | Mech Gallery | 17 Fri: ET22; 18 Sat: ET22; 19 Sun: ET22; 20 Mon: ET22; 21 Tue: ET22; 22 Wed: ET22; 23 Thu: ET22; 24 Fri: ET22; 25 Sat: ET22; 26 Sun: ET22; 27 Mon: ET22; 28 Tue: ET22; 29 Wed: ET22; 30 Thu: ET22; 31 Fri: I-R; 01 Sat: I-R; 02 Sun: I-R; 03 Mon: I-R; 04 Tue: EE35; 05 Wed: EE35; 06 Thu: EE35; 07 Fri: EE35; 08 Sat: EE35; 09 Sun: EE35; 10 Mon: EE35; 11 Tue: EE35; 12 Wed: EE35; 13 Thu: EE35; 14 Fri: EE36; 15 Sat: EE36; 16 Sun: EE36; 17 Mon: EE36; 18 Tue: EE36; 19 Wed: EE36; 20 Thu: EE36
COLO 2 | All | CX - Microsoft | 04 Wed: MS1; 05 Thu: MS1; 06 Fri: MS1; 07 Sat: MS1; 08 Sun: MS1; 09 Mon: MS1; 10 Tue: MS1; 11 Wed: MS1; 12 Thu: MS1; 13 Fri: MS1; 14 Sat: MS1; 15 Sun: MS1; 16 Mon: MS1; 17 Tue: MS1; 18 Wed: MS1; 19 Thu: MS1; 20 Fri: MS1; 21 Sat: MS1; 22 Sun: MS1; 23 Mon: MS1; 24 Tue: MS1; 25 Wed: MS1; 26 Thu: MS1; 27 Fri: MS1; 28 Sat: MS1; 29 Sun: MS1; 30 Mon: MS1; 01 Tue: MS1; 02 Wed: MS2; 03 Thu: MS2
| Cell 1 | CX - L2 | 03 Mon: EE57; 04 Tue: EE57; 05 Wed: EE57; 06 Thu: EE57; 07 Fri: EE57; 10 Mon: EE58; 11 Tue: EE58; 12 Wed: EE58; 13 Thu: EE58; 14 Fri: EE58; 17 Mon: EE59; 18 Tue: EE59; 19 Wed: EE59; 20 Thu: EE59; 21 Fri: EE59; 24 Mon: EE61; 25 Tue: EE61; 26 Wed: EE61; 27 Thu: EE61; 28 Fri: EE61; 12 Wed: EE62; 13 Thu: EE62; 14 Fri: EE62; 15 Sat: EE62; 16 Sun: EE62; 17 Mon: EE62; 18 Tue: EE62
[101 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | [18 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
|  | CX - L3 | 08 Tue: EE57; 09 Wed: EE57; 10 Thu: EE57; 11 Fri: EE57; 12 Sat: EE57; 13 Sun: EE57; 14 Mon: EE57; 15 Tue: EE62; 16 Wed: EE62; 17 Thu: EE62; 18 Fri: EE62; 19 Sat: EE62; 20 Sun: EE62; 21 Mon: EE62; 22 Tue: EE60; 23 Wed: EE60; 24 Thu: EE60; 25 Fri: EE60; 26 Sat: EE60; 27 Sun: EE60; 28 Mon: EE60; 29 Tue: EE59; 30 Wed: EE59; 01 Thu: EE59; 02 Fri: EE59; 03 Sat: EE59; 04 Sun: EE59; 05 Mon: EE59; 06 Tue: EE59; 07 Wed: EE59; 08 Thu: EE59; 09 Fri: EE59; 10 Sat: EE59; 11 Sun: EE59; 12 Mon: EE59; 13 Tue: EE61; 14 Wed: EE61; 15 Thu: EE61; 16 Fri: EE61; 17 Sat: EE61; 18 Sun: EE61; 19 Mon: EE61
[158 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[158 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | 03 Fri: EE17; 04 Sat: EE17; 05 Sun: EE17; 06 Mon: EE17; 07 Tue: EE17; 08 Wed: EE17; 09 Thu: EE17; 10 Fri: EE17; 11 Sat: EE17; 12 Sun: EE17; 13 Mon: EE17; 14 Tue: EE17; 15 Wed: EE17; 16 Thu: EE17; 17 Fri: EE17; 18 Sat: EE17; 19 Sun: EE17; 20 Mon: EE17; 21 Tue: EE17; 22 Wed: EE17; 23 Thu: EE17; 24 Fri: EE17; 25 Sat: EE17; 26 Sun: EE17; 27 Mon: EE17; 28 Tue: EE17; 29 Wed: EE17; 30 Thu: EE17; 31 Fri: EE17; 10 Mon: ALL3; 11 Tue: ALL3; 12 Wed: ALL3; 13 Thu: ALL3; 14 Fri: ALL3
[63 empty] | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | 03 Fri: EE29; 04 Sat: EE29; 05 Sun: EE29; 06 Mon: EE29; 07 Tue: EE29; 08 Wed: EE29; 09 Thu: EE29; 10 Fri: EE29; 11 Sat: EE29; 12 Sun: EE29; 13 Mon: EE29; 14 Tue: EE29; 15 Wed: EE29; 16 Thu: EE29; 17 Fri: EE29; 18 Sat: EE29; 19 Sun: EE29; 20 Mon: EE29; 21 Tue: EE29; 22 Wed: EE29; 23 Thu: EE29; 24 Fri: EE29; 25 Sat: EE29; 26 Sun: EE29; 27 Mon: EE29; 28 Tue: EE29; 29 Wed: EE29; 30 Thu: EE29; 31 Fri: EE29; 03 Mon: ALL3; 04 Tue: ALL3; 05 Wed: ALL3; 06 Thu: ALL3; 07 Fri: ALL3
| Cell 2 | CX - L2 | 03 Mon: EE57; 04 Tue: EE57; 05 Wed: EE57; 06 Thu: EE57; 07 Fri: EE57; 10 Mon: EE62; 11 Tue: EE62; 12 Wed: EE62; 13 Thu: EE62; 14 Fri: EE62; 17 Mon: EE60; 18 Tue: EE60; 19 Wed: EE60; 20 Thu: EE60; 21 Fri: EE60; 24 Mon: EE59; 25 Tue: EE59; 26 Wed: EE59; 27 Thu: EE59; 28 Fri: EE59; 03 Mon: EE61; 04 Tue: EE61; 05 Wed: EE61; 06 Thu: EE61; 07 Fri: EE61
[94 empty] | EE63 | EE63 | EE63 | EE63 | EE63
[94 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | 08 Tue: EE57; 09 Wed: EE57; 10 Thu: EE57; 11 Fri: EE57; 12 Sat: EE57; 13 Sun: EE57; 14 Mon: EE57; 15 Tue: EE62; 16 Wed: EE62; 17 Thu: EE62; 18 Fri: EE62; 19 Sat: EE62; 20 Sun: EE62; 21 Mon: EE62; 22 Tue: EE60; 23 Wed: EE60; 24 Thu: EE60; 25 Fri: EE60; 26 Sat: EE60; 27 Sun: EE60; 28 Mon: EE60; 29 Tue: EE59; 30 Wed: EE59; 01 Thu: EE59; 02 Fri: EE59; 03 Sat: EE59; 04 Sun: EE59; 05 Mon: EE59; 06 Tue: EE59; 07 Wed: EE59; 08 Thu: EE59; 09 Fri: EE59; 10 Sat: EE59; 11 Sun: EE59; 12 Mon: EE59; 13 Tue: EE61; 14 Wed: EE61; 15 Thu: EE61; 16 Fri: EE61; 17 Sat: EE61; 18 Sun: EE61; 19 Mon: EE61
[158 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[158 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | 03 Fri: EE17; 04 Sat: EE17; 05 Sun: EE17; 06 Mon: EE17; 07 Tue: EE17; 08 Wed: EE17; 09 Thu: EE17; 10 Fri: EE17; 11 Sat: EE17; 12 Sun: EE17; 13 Mon: EE17; 14 Tue: EE17; 15 Wed: EE17; 16 Thu: EE17; 17 Fri: EE17; 18 Sat: EE17; 19 Sun: EE17; 20 Mon: EE17; 21 Tue: EE17; 22 Wed: EE17; 23 Thu: EE17; 24 Fri: EE18; 25 Sat: EE18; 26 Sun: EE18; 27 Mon: EE18; 28 Tue: EE18; 29 Wed: EE18; 30 Thu: EE18; 31 Fri: EE18; 01 Sat: EE18; 02 Sun: EE18; 03 Mon: EE18; 04 Tue: EE18; 05 Wed: EE18; 06 Thu: EE18; 07 Fri: EE18; 08 Sat: EE18; 09 Sun: EE18; 10 Mon: EE18; 11 Tue: EE18; 12 Wed: EE18; 13 Thu: EE18; 17 Mon: ALL3; 18 Tue: ALL3; 19 Wed: ALL3; 20 Thu: ALL3; 21 Fri: ALL3
|  | Electrical Room | 03 Fri: EE29; 04 Sat: EE29; 05 Sun: EE29; 06 Mon: EE29; 07 Tue: EE29; 08 Wed: EE29; 09 Thu: EE29; 10 Fri: EE29; 11 Sat: EE29; 12 Sun: EE29; 13 Mon: EE29; 14 Tue: EE29; 15 Wed: EE29; 16 Thu: EE29; 17 Fri: EE29; 18 Sat: EE29; 19 Sun: EE29; 20 Mon: EE29; 21 Tue: EE29; 22 Wed: EE29; 23 Thu: EE29; 24 Fri: EE29; 25 Sat: EE29; 26 Sun: EE29; 27 Mon: EE29; 28 Tue: EE29; 29 Wed: EE29; 30 Thu: EE29; 31 Fri: EE29; 10 Mon: ALL3; 11 Tue: ALL3; 12 Wed: ALL3; 13 Thu: ALL3; 14 Fri: ALL3
|  | Mech Gallery | 10 Fri: EE35; 11 Sat: EE35; 12 Sun: EE35; 13 Mon: EE35; 14 Tue: EE35; 15 Wed: EE35; 16 Thu: EE35; 17 Fri: EE35; 18 Sat: EE35; 19 Sun: EE35; 20 Mon: EE35; 21 Tue: EE35; 22 Wed: EE36; 23 Thu: EE36; 24 Fri: EE36; 25 Sat: EE36; 26 Sun: EE36; 27 Mon: EE36; 28 Tue: EE36
| Cell 3 | CX - L2 | 10 Mon: EE57; 11 Tue: EE57; 12 Wed: EE57; 13 Thu: EE57; 14 Fri: EE57; 17 Mon: EE62; 18 Tue: EE62; 19 Wed: EE62; 20 Thu: EE62; 21 Fri: EE62; 24 Mon: EE60; 25 Tue: EE60; 26 Wed: EE60; 27 Thu: EE60; 28 Fri: EE60; 03 Mon: EE59; 04 Tue: EE59; 05 Wed: EE59; 06 Thu: EE59; 07 Fri: EE59
[101 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | [9 empty] | EE61 | EE61 | EE61 | EE61 | EE61
[101 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | 15 Tue: EE57; 16 Wed: EE57; 17 Thu: EE57; 18 Fri: EE57; 19 Sat: EE57; 20 Sun: EE57; 21 Mon: EE57; 22 Tue: EE62; 23 Wed: EE62; 24 Thu: EE62; 25 Fri: EE62; 26 Sat: EE62; 27 Sun: EE62; 28 Mon: EE62; 29 Tue: EE60; 30 Wed: EE60; 01 Thu: EE60; 02 Fri: EE60; 03 Sat: EE60; 04 Sun: EE60; 05 Mon: EE60; 06 Tue: EE59; 07 Wed: EE59; 08 Thu: EE59; 09 Fri: EE59; 10 Sat: EE59; 11 Sun: EE59; 12 Mon: EE59; 13 Tue: EE59; 14 Wed: EE59; 15 Thu: EE59; 16 Fri: EE59; 17 Sat: EE59; 18 Sun: EE59; 19 Mon: EE59; 20 Tue: EE61; 21 Wed: EE61; 22 Thu: EE61; 23 Fri: EE61; 24 Sat: EE61; 25 Sun: EE61; 26 Mon: EE61; 27 Tue: EE61
[165 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[165 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | 10 Fri: EE18; 11 Sat: EE18; 12 Sun: EE18; 13 Mon: EE18; 14 Tue: EE18; 15 Wed: EE18; 16 Thu: EE18; 17 Fri: EE18; 18 Sat: EE18; 19 Sun: EE18; 20 Mon: EE18; 21 Tue: EE18; 22 Wed: EE18; 23 Thu: EE18; 24 Fri: EE18; 25 Sat: EE18; 26 Sun: EE18; 27 Mon: EE18; 28 Tue: EE18; 29 Wed: EE18; 30 Thu: EE18; 24 Mon: ALL3; 25 Tue: ALL3; 26 Wed: ALL3; 27 Thu: ALL3; 28 Fri: ALL3
[70 empty] | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7
|  | Electrical Room | 10 Fri: EE29; 11 Sat: EE29; 12 Sun: EE29; 13 Mon: EE29; 14 Tue: EE29; 15 Wed: EE29; 16 Thu: EE29; 17 Fri: EE29; 18 Sat: EE29; 19 Sun: EE29; 20 Mon: EE29; 21 Tue: EE29; 22 Wed: EE29; 23 Thu: EE29; 24 Fri: EE29; 25 Sat: EE29; 26 Sun: EE29; 27 Mon: EE29; 28 Tue: EE29; 29 Wed: EE29; 30 Thu: EE29
[81 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
|  | Mech Gallery | 17 Fri: I-R; 18 Sat: I-R; 19 Sun: I-R; 20 Mon: I-R; 22 Wed: EE35; 23 Thu: EE35; 24 Fri: EE35; 25 Sat: EE35; 26 Sun: EE35; 27 Mon: EE35; 28 Tue: EE35; 29 Wed: EE35; 30 Thu: EE35; 31 Fri: EE35; 03 Mon: EE36; 04 Tue: EE36; 05 Wed: EE36; 06 Thu: EE36; 07 Fri: EE36
| Cell 4 | CX - L2 | 21 Fri: EE57; 22 Sat: EE57; 23 Sun: EE57; 24 Mon: EE57; 25 Tue: EE57; 26 Wed: EE57; 27 Thu: EE57; 28 Fri: EE62; 01 Sat: EE62; 02 Sun: EE62; 03 Mon: EE62; 04 Tue: EE62; 05 Wed: EE62; 06 Thu: EE62; 07 Fri: EE60; 08 Sat: EE60; 09 Sun: EE60; 10 Mon: EE60; 11 Tue: EE60; 12 Wed: EE60; 13 Thu: EE60
[112 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 |  |  |  | EE59 | EE59 | EE59 | EE59 | EE59
[112 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 |  |  |  | EE61 | EE61 | EE61 | EE61 | EE61
|  | CX - L3 | 22 Tue: EE57; 23 Wed: EE57; 24 Thu: EE57; 25 Fri: EE57; 26 Sat: EE57; 27 Sun: EE57; 28 Mon: EE57; 29 Tue: EE62; 30 Wed: EE62; 01 Thu: EE62; 02 Fri: EE62; 03 Sat: EE62; 04 Sun: EE62; 05 Mon: EE62; 06 Tue: EE58; 07 Wed: EE58; 08 Thu: EE58; 09 Fri: EE58; 10 Sat: EE58; 11 Sun: EE58; 12 Mon: EE58; 13 Tue: EE60; 14 Wed: EE60; 15 Thu: EE60; 16 Fri: EE60; 17 Sat: EE60; 18 Sun: EE60; 19 Mon: EE60; 28 Wed: EE61; 29 Thu: EE61; 30 Fri: EE61; 31 Sat: EE61; 01 Sun: EE61; 02 Mon: EE61; 03 Tue: EE61
[172 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | [7 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | Data Hall | 10 Fri: EE18; 11 Sat: EE18; 12 Sun: EE18; 13 Mon: EE18; 14 Tue: EE18; 15 Wed: EE18; 16 Thu: EE18; 17 Fri: EE18; 18 Sat: EE18; 19 Sun: EE18; 20 Mon: EE18; 21 Tue: EE18; 22 Wed: EE18; 23 Thu: EE18; 24 Fri: EE18; 25 Sat: EE18; 26 Sun: EE18; 27 Mon: EE18; 28 Tue: EE18; 29 Wed: EE18; 30 Thu: EE18; 31 Fri: ET7; 01 Sat: ET7; 02 Sun: ET7; 03 Mon: ET7; 04 Tue: ET7; 05 Wed: ET7; 06 Thu: ET7; 07 Fri: ET7; 08 Sat: ET7; 09 Sun: ET7; 10 Mon: ET7; 11 Tue: ET7; 12 Wed: ET7; 13 Thu: ET7; 03 Mon: ALL3; 04 Tue: ALL3; 05 Wed: ALL3; 06 Thu: ALL3; 07 Fri: ALL3
|  | Electrical Room | 14 Tue: EE28; 15 Wed: EE28; 16 Thu: EE28; 17 Fri: EE28; 18 Sat: EE28; 19 Sun: EE28; 20 Mon: EE28; 31 Fri: EE29; 01 Sat: EE29; 02 Sun: EE29; 03 Mon: EE29; 04 Tue: EE29; 05 Wed: EE29; 06 Thu: EE29; 07 Fri: EE29; 08 Sat: EE29; 09 Sun: EE29; 10 Mon: EE29; 11 Tue: EE29; 12 Wed: EE29; 13 Thu: EE29; 14 Fri: EE29; 15 Sat: EE29; 16 Sun: EE29; 17 Mon: EE29; 18 Tue: EE29; 19 Wed: EE29; 20 Thu: EE29; 21 Fri: ALL3; 22 Sat: ALL3; 23 Sun: ALL3; 24 Mon: ALL3; 25 Tue: ALL3; 26 Wed: ALL3; 27 Thu: ALL3
|  | Mech Gallery | 17 Fri: ET22; 18 Sat: ET22; 19 Sun: ET22; 20 Mon: ET22; 21 Tue: ET22; 22 Wed: ET22; 23 Thu: ET22; 24 Fri: ET22; 25 Sat: ET22; 26 Sun: ET22; 27 Mon: ET22; 28 Tue: ET22; 29 Wed: ET22; 30 Thu: ET22; 31 Fri: I-R; 01 Sat: I-R; 02 Sun: I-R; 03 Mon: I-R; 04 Tue: EE35; 05 Wed: EE35; 06 Thu: EE35; 07 Fri: EE35; 08 Sat: EE35; 09 Sun: EE35; 10 Mon: EE35; 11 Tue: EE35; 12 Wed: EE35; 13 Thu: EE35; 14 Fri: EE36; 15 Sat: EE36; 16 Sun: EE36; 17 Mon: EE36; 18 Tue: EE36; 19 Wed: EE36; 20 Thu: EE36
COLO 3 | All | CX - Microsoft | 2025 Aug 08 Wed: MS2; 2025 Aug 09 Thu: MS2; 2025 Aug 10 Fri: MS2; 2025 Aug 11 Sat: MS2; 2025 Aug 12 Sun: MS2; 2025 Aug 13 Mon: MS2; 2025 Aug 14 Tue: MS2; 2025 Aug 15 Wed: MS2; 2025 Aug 16 Thu: MS2; 2025 Aug 17 Fri: MS2; 2025 Aug 18 Sat: MS2; 2025 Aug 19 Sun: MS2; 2025 Aug 20 Mon: MS2; 2025 Aug 21 Tue: MS2; 2025 Aug 22 Wed: MS2; 2025 Aug 23 Thu: MS2; 2025 Aug 24 Fri: MS2; 2025 Aug 25 Sat: MS2; 2025 Aug 26 Sun: MS2; 2025 Aug 27 Mon: MS2; 2025 Aug 28 Tue: MS2; 2025 Aug 29 Wed: MS2; 2025 Aug 30 Thu: MS2; 2025 Aug 31 Fri: MS2; 2025 Aug 01 Sat: MS2; 2025 Aug 02 Sun: MS2; 2025 Aug 03 Mon: MS2; 2025 Aug 04 Tue: MS2
[334 empty] | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1 | MS1
| Cell 1 | CX - L1 | 24 Fri: EE63; 26 Wed: EE62
|  | CX - L2 | 17 Mon: EE57; 18 Tue: EE57; 19 Wed: EE57; 20 Thu: EE57; 21 Fri: EE57; 24 Mon: EE62; 25 Tue: EE62; 26 Wed: EE62; 27 Thu: EE62; 28 Fri: EE62; 31 Mon: EE60; 01 Tue: EE60; 02 Wed: EE60; 03 Thu: EE60; 04 Fri: EE60; 07 Mon: EE59; 08 Tue: EE59; 09 Wed: EE59; 10 Thu: EE59; 11 Fri: EE59
[136 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE61 | EE61 | EE61 | EE61 | EE61
[136 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | 2025 Aug 18 Mon: EE57; 2025 Aug 19 Tue: EE57; 2025 Aug 20 Wed: EE57; 2025 Aug 21 Thu: EE57; 2025 Aug 22 Fri: EE57; 2025 Aug 25 Mon: EE62; 2025 Aug 26 Tue: EE62; 2025 Aug 27 Wed: EE62; 2025 Aug 28 Thu: EE62; 2025 Aug 29 Fri: EE62; 2025 Aug 02 Tue: EE60; 2025 Aug 03 Wed: EE60; 2025 Aug 04 Thu: EE60; 2025 Aug 05 Fri: EE60; 2025 Aug 06 Sat: EE60; 2025 Aug 07 Sun: EE60; 2025 Aug 08 Mon: EE60; 2025 Aug 10 Wed: EE59; 2025 Aug 11 Thu: EE59; 2025 Aug 12 Fri: EE59; 2025 Aug 13 Sat: EE59; 2025 Aug 14 Sun: EE59; 2025 Aug 15 Mon: EE59; 2025 Aug 16 Tue: EE59; 2025 Aug 17 Wed: EE59; 2025 Aug 18 Thu: EE59; 2025 Aug 19 Fri: EE59; 2025 Aug 20 Sat: EE59; 2025 Aug 21 Sun: EE59; 2025 Aug 22 Mon: EE59; 2025 Aug 23 Tue: EE59; 2025 Aug 24 Wed: EE61; 2025 Aug 25 Thu: EE61; 2025 Aug 26 Fri: EE61; 2025 Aug 27 Sat: EE61; 2025 Aug 28 Sun: EE61; 2025 Aug 29 Mon: EE61; 2025 Aug 30 Tue: EE61
[290 empty] | EE63 | EE63 | EE63 | EE63 | EE63
[290 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | 17 Fri: EE7; 18 Sat: EE7; 19 Sun: EE7; 20 Mon: EE7; 21 Tue: EE7; 22 Wed: EE7; 23 Thu: EE7; 24 Fri: S2; 25 Sat: S2; 26 Sun: S2; 27 Mon: S2; 28 Tue: S2; 29 Wed: S2; 30 Thu: S2; 31 Fri: ET7; 01 Sat: ET7; 02 Sun: ET7; 03 Mon: ET7; 04 Tue: ET7; 05 Wed: ET7; 06 Thu: ET7; 07 Fri: ET7; 08 Sat: ET7; 09 Sun: ET7; 10 Mon: ET7; 11 Tue: ET7; 12 Wed: ET7; 13 Thu: ET7; 24 Mon: ALL3; 25 Tue: ALL3; 26 Wed: ALL3; 27 Thu: ALL3; 28 Fri: ALL3
[70 empty] | S1 | S1 | S1 | S1 | S1 | S1 | S1 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17
[80 empty] | EE10 | EE10 | EE10 | EE10 | EE10 |  |  | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | 27 Mon: EE28; 28 Tue: EE28; 29 Wed: EE28; 30 Thu: EE28; 31 Fri: EE28; 03 Mon: EE29; 04 Tue: EE29; 05 Wed: EE29; 06 Thu: EE29; 07 Fri: EE29; 08 Sat: EE29; 09 Sun: EE29; 10 Mon: EE29; 11 Tue: EE29; 12 Wed: EE29; 13 Thu: EE29; 14 Fri: EE29; 15 Sat: EE29; 16 Sun: EE29; 17 Mon: EE29; 18 Tue: EE29; 19 Wed: EE23; 20 Thu: EE23; 21 Fri: EE23; 22 Sat: EE23; 23 Sun: EE23; 24 Mon: EE23; 25 Tue: EE23; 26 Wed: J36; 27 Thu: J36; 28 Fri: J36; 01 Sat: J36; 02 Sun: J36; 03 Mon: J36; 04 Tue: J36; 05 Wed: ALL3; 06 Thu: ALL3; 07 Fri: ALL3; 08 Sat: ALL3; 09 Sun: ALL3; 10 Mon: ALL3; 11 Tue: ALL3
|  | Mech Gallery | 14 Tue: EE35; 15 Wed: EE35; 16 Thu: EE35; 17 Fri: EE35; 18 Sat: EE35; 19 Sun: EE35; 20 Mon: EE35; 21 Tue: EE35; 22 Wed: EE35; 23 Thu: EE35; 24 Fri: EE36; 25 Sat: EE36; 26 Sun: EE36; 27 Mon: EE36; 28 Tue: EE36; 29 Wed: EE36; 30 Thu: EE36
| Cell 2 | CX - L1 | 17 Fri: EE59; 23 Thu: EE57; 12 Wed: EE63; 27 Thu: EE62
EE60
EE61
EE58
|  | CX - L2 | 17 Mon: EE57; 18 Tue: EE57; 19 Wed: EE57; 20 Thu: EE57; 21 Fri: EE57; 24 Mon: EE62; 25 Tue: EE62; 26 Wed: EE62; 27 Thu: EE62; 28 Fri: EE62; 31 Mon: EE60; 01 Tue: EE60; 02 Wed: EE60; 03 Thu: EE60; 04 Fri: EE60; 14 Mon: EE59; 15 Tue: EE59; 16 Wed: EE59; 17 Thu: EE59; 18 Fri: EE59
[136 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE61 | EE61 | EE61 | EE61 | EE61
[136 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | 2025 Aug 18 Mon: EE57; 2025 Aug 19 Tue: EE57; 2025 Aug 20 Wed: EE57; 2025 Aug 21 Thu: EE57; 2025 Aug 22 Fri: EE57; 2025 Aug 25 Mon: EE62; 2025 Aug 26 Tue: EE62; 2025 Aug 27 Wed: EE62; 2025 Aug 28 Thu: EE62; 2025 Aug 29 Fri: EE62; 2025 Aug 02 Tue: EE63; 2025 Aug 03 Wed: EE63; 2025 Aug 04 Thu: EE63; 2025 Aug 05 Fri: EE63; 2025 Aug 06 Sat: EE63; 2025 Aug 07 Sun: EE63; 2025 Aug 08 Mon: EE63; 2025 Aug 10 Wed: EE59; 2025 Aug 11 Thu: EE59; 2025 Aug 12 Fri: EE59; 2025 Aug 13 Sat: EE59; 2025 Aug 14 Sun: EE59; 2025 Aug 15 Mon: EE59; 2025 Aug 16 Tue: EE59; 2025 Aug 17 Wed: EE59; 2025 Aug 18 Thu: EE59; 2025 Aug 19 Fri: EE59; 2025 Aug 20 Sat: EE59; 2025 Aug 21 Sun: EE59; 2025 Aug 22 Mon: EE59; 2025 Aug 23 Tue: EE59; 2025 Aug 24 Wed: EE61; 2025 Aug 25 Thu: EE61; 2025 Aug 26 Fri: EE61; 2025 Aug 27 Sat: EE61; 2025 Aug 28 Sun: EE61; 2025 Aug 29 Mon: EE61; 2025 Aug 30 Tue: EE61
[290 empty] | EE58 | EE58 | EE58 | EE58 | EE58 |  |  |  | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
|  | Data Hall | 15 Wed: J7; 16 Thu: J7; 17 Fri: J7; 18 Sat: J7; 19 Sun: J7; 20 Mon: J7; 21 Tue: J7; 22 Wed: EE73; 23 Thu: EE73; 24 Fri: EE73; 25 Sat: EE73; 26 Sun: EE73; 27 Mon: EE73; 28 Tue: EE73; 29 Wed: EE73; 30 Thu: EE73; 31 Fri: EE73; 01 Sat: EE73; 02 Sun: EE73; 03 Mon: EE73; 04 Tue: EE73; 05 Wed: EE7; 06 Thu: EE7; 07 Fri: EE7; 08 Sat: EE7; 09 Sun: EE7; 10 Mon: EE7; 11 Tue: EE7; 12 Wed: S2; 13 Thu: S2; 14 Fri: S2; 15 Sat: S2; 16 Sun: S2; 17 Mon: S2; 18 Tue: S2; 19 Wed: ET7; 20 Thu: ET7; 21 Fri: ET7; 22 Sat: ET7; 23 Sun: ET7; 24 Mon: ET7; 25 Tue: ET7; 26 Wed: ET7; 27 Thu: ET7; 28 Fri: ET7; 01 Sat: ET7; 02 Sun: ET7; 03 Mon: ET7; 04 Tue: ET7; 05 Wed: ALL3; 06 Thu: ALL3; 07 Fri: ALL3; 08 Sat: ALL3; 09 Sun: ALL3; 10 Mon: ALL3; 11 Tue: ALL3
[89 empty] | S1 | S1 | S1 | S1 | S1 | S1 | S1 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17
[91 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | 14 Tue: EE72; 15 Wed: EE72; 16 Thu: EE72; 17 Fri: EE72; 18 Sat: EE72; 19 Sun: EE72; 20 Mon: EE72; 21 Tue: EE72; 22 Wed: EE72; 23 Thu: EE72; 24 Fri: EE72; 25 Sat: EE72; 26 Sun: EE72; 27 Mon: EE72; 03 Mon: EE28; 04 Tue: EE28; 05 Wed: EE28; 06 Thu: EE28; 07 Fri: EE28; 19 Wed: EE29; 20 Thu: EE29; 21 Fri: EE29; 22 Sat: EE29; 23 Sun: EE29; 24 Mon: EE29; 25 Tue: EE29; 26 Wed: EE29; 27 Thu: EE29; 28 Fri: EE29; 01 Sat: EE29; 02 Sun: EE29; 03 Mon: EE29; 04 Tue: EE29; 05 Wed: EE29; 06 Thu: EE29; 12 Wed: ALL3; 13 Thu: ALL3; 14 Fri: ALL3; 15 Sat: ALL3; 16 Sun: ALL3; 17 Mon: ALL3; 18 Tue: ALL3
[68 empty] | GH3 | GH3 | GH3 | GH3 | GH3 | GH3 | GH3 |  | J36 | J36 | J36 | J36 | J36 | J36 | J36
[69 empty] | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27
[69 empty] | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23
|  | Mech Gallery | 10 Fri: EE70; 11 Sat: EE70; 12 Sun: EE70; 13 Mon: EE70; 14 Tue: EE70; 15 Wed: EE70; 16 Thu: EE70; 17 Fri: EE70; 18 Sat: EE70; 19 Sun: EE70; 20 Mon: EE70; 21 Tue: EE70; 22 Wed: EE70; 23 Thu: EE70; 24 Fri: EE70; 25 Sat: EE70; 26 Sun: EE70; 27 Mon: EE70; 28 Tue: EE70; 29 Wed: EE70; 30 Thu: EE70; 04 Tue: I-R; 05 Wed: I-R; 06 Thu: I-R; 18 Tue: EE36; 19 Wed: EE36; 20 Thu: EE36; 21 Fri: EE36; 22 Sat: EE36; 23 Sun: EE36; 24 Mon: EE36; 25 Tue: EE36
[70 empty] | GA6 | GA6 | GA6 | GA6 | GA6 | [15 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
[74 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22
| Cell 3 | CX - L1 | 21 Tue: EE59; 22 Wed: EE59; 06 Thu: EE57; 26 Wed: EE63; 28 Fri: EE62
EE60
EE61
EE58
|  | CX - L2 | 25 Tue: EE57; 26 Wed: EE57; 27 Thu: EE57; 28 Fri: EE57; 29 Sat: EE57; 30 Sun: EE57; 31 Mon: EE57; 01 Tue: EE62; 02 Wed: EE62; 03 Thu: EE62; 04 Fri: EE62; 05 Sat: EE62; 06 Sun: EE62; 07 Mon: EE62; 08 Tue: EE61; 09 Wed: EE61; 10 Thu: EE61; 11 Fri: EE61; 12 Sat: EE61; 13 Sun: EE61; 14 Mon: EE61; 21 Mon: EE59; 22 Tue: EE59; 23 Wed: EE59; 24 Thu: EE59; 25 Fri: EE59
[137 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[137 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | 2025 Aug 25 Mon: EE57; 2025 Aug 26 Tue: EE57; 2025 Aug 27 Wed: EE57; 2025 Aug 28 Thu: EE57; 2025 Aug 29 Fri: EE57; 2025 Aug 02 Tue: EE62; 2025 Aug 03 Wed: EE62; 2025 Aug 04 Thu: EE62; 2025 Aug 05 Fri: EE62; 2025 Aug 06 Sat: EE62; 2025 Aug 07 Sun: EE62; 2025 Aug 08 Mon: EE62; 2025 Aug 09 Tue: EE58; 2025 Aug 10 Wed: EE58; 2025 Aug 11 Thu: EE58; 2025 Aug 12 Fri: EE58; 2025 Aug 13 Sat: EE58; 2025 Aug 14 Sun: EE58; 2025 Aug 15 Mon: EE58; 2025 Aug 17 Wed: EE60; 2025 Aug 18 Thu: EE60; 2025 Aug 19 Fri: EE60; 2025 Aug 20 Sat: EE60; 2025 Aug 21 Sun: EE60; 2025 Aug 22 Mon: EE60; 2025 Aug 23 Tue: EE60; 2025 Aug 24 Wed: EE61; 2025 Aug 25 Thu: EE61; 2025 Aug 26 Fri: EE61; 2025 Aug 27 Sat: EE61; 2025 Aug 28 Sun: EE61; 2025 Aug 29 Mon: EE61; 2025 Aug 30 Tue: EE61
[298 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | [15 empty] | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
|  | Data Hall | 22 Wed: J7; 23 Thu: J7; 24 Fri: J7; 25 Sat: J7; 26 Sun: J7; 27 Mon: J7; 28 Tue: J7; 05 Wed: EE73; 06 Thu: EE73; 07 Fri: EE73; 08 Sat: EE73; 09 Sun: EE73; 10 Mon: EE73; 11 Tue: EE73; 12 Wed: EE73; 13 Thu: EE73; 14 Fri: EE73; 15 Sat: EE73; 16 Sun: EE73; 17 Mon: EE73; 18 Tue: EE73; 19 Wed: EE7; 20 Thu: EE7; 21 Fri: EE7; 22 Sat: EE7; 23 Sun: EE7; 24 Mon: EE7; 25 Tue: EE7; 26 Wed: S2; 27 Thu: S2; 28 Fri: S2; 01 Sat: S2; 02 Sun: S2; 03 Mon: S2; 04 Tue: S2; 05 Wed: ET7; 06 Thu: ET7; 07 Fri: ET7; 08 Sat: ET7; 09 Sun: ET7; 10 Mon: ET7; 11 Tue: ET7; 12 Wed: ET7; 13 Thu: ET7; 14 Fri: ET7; 15 Sat: ET7; 16 Sun: ET7; 17 Mon: ET7; 18 Tue: ET7; 26 Wed: ALL3; 27 Thu: ALL3; 28 Fri: ALL3; 29 Sat: ALL3; 30 Sun: ALL3; 31 Mon: ALL3; 01 Tue: ALL3
[103 empty] | S1 | S1 | S1 | S1 | S1 | S1 | S1 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
[105 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10
|  | Electrical Room | 17 Fri: GH3; 18 Sat: GH3; 19 Sun: GH3; 20 Mon: GH3; 21 Tue: GH3; 22 Wed: GH3; 23 Thu: GH3; 28 Tue: EE72; 29 Wed: EE72; 30 Thu: EE72; 31 Fri: EE72; 01 Sat: EE72; 02 Sun: EE72; 03 Mon: EE72; 04 Tue: EE72; 05 Wed: EE72; 06 Thu: EE72; 07 Fri: EE72; 08 Sat: EE72; 09 Sun: EE72; 10 Mon: EE72; 07 Fri: EE29; 08 Sat: EE29; 09 Sun: EE29; 10 Mon: EE29; 11 Tue: EE29; 12 Wed: EE29; 13 Thu: EE29; 14 Fri: EE29; 15 Sat: EE29; 16 Sun: EE29; 17 Mon: EE29; 18 Tue: EE29; 19 Wed: EE29; 20 Thu: EE29; 21 Fri: EE29; 22 Sat: EE29; 23 Sun: EE29; 24 Mon: EE29
[83 empty] | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | [35 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[83 empty] | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 |  |  |  |  | EE28 | EE28 | EE28 | EE28 | EE28
[83 empty] | EE71 | EE71 | EE71 | EE71 | EE71 | EE71 | EE71
|  | Mech Gallery | 10 Fri: EE70; 11 Sat: EE70; 12 Sun: EE70; 13 Mon: EE70; 14 Tue: EE70; 15 Wed: EE70; 16 Thu: EE70; 17 Fri: EE70; 18 Sat: EE70; 19 Sun: EE70; 20 Mon: EE70; 21 Tue: EE70; 22 Wed: EE70; 23 Thu: EE70; 24 Fri: EE70; 25 Sat: EE70; 26 Sun: EE70; 27 Mon: EE70; 28 Tue: EE70; 29 Wed: EE70; 30 Thu: EE70; 04 Tue: ET22; 05 Wed: ET22; 06 Thu: ET22; 07 Fri: ET22; 08 Sat: ET22; 09 Sun: ET22; 10 Mon: ET22; 11 Tue: ET22; 12 Wed: ET22; 13 Thu: ET22; 14 Fri: ET22; 15 Sat: ET22; 16 Sun: ET22; 17 Mon: ET22; 18 Tue: ET22; 20 Thu: EE35; 21 Fri: EE35; 22 Sat: EE35; 23 Sun: EE35; 24 Mon: EE35; 25 Tue: EE35; 26 Wed: EE35; 27 Thu: EE35; 28 Fri: EE35; 01 Sat: EE35; 02 Sun: EE35; 03 Mon: EE35; 04 Tue: EE35
[102 empty] | I-R | I-R | I-R | [11 empty] | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36
| Cell 4 | CX - L1 | 11 Tue: EE61; 20 Thu: EE57; 28 Fri: EE62; 12 Wed: EE63
EE60
EE60
EE58
|  | CX - L2 | 25 Tue: EE57; 26 Wed: EE57; 27 Thu: EE57; 28 Fri: EE57; 29 Sat: EE57; 30 Sun: EE57; 31 Mon: EE57; 01 Tue: EE57; 08 Tue: EE61; 09 Wed: EE61; 10 Thu: EE61; 11 Fri: EE61; 12 Sat: EE61; 13 Sun: EE61; 14 Mon: EE61; 15 Tue: EE61; 16 Wed: EE63; 17 Thu: EE63; 18 Fri: EE63; 19 Sat: EE63; 20 Sun: EE63; 21 Mon: EE63; 22 Tue: EE63
[144 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | [12 empty] | EE59 | EE59 | EE59 | EE59 | EE59
[144 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
[151 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | 2025 Aug 25 Mon: EE57; 2025 Aug 26 Tue: EE57; 2025 Aug 27 Wed: EE57; 2025 Aug 28 Thu: EE57; 2025 Aug 29 Fri: EE57; 2025 Aug 02 Tue: EE63; 2025 Aug 03 Wed: EE63; 2025 Aug 04 Thu: EE63; 2025 Aug 05 Fri: EE63; 2025 Aug 06 Sat: EE63; 2025 Aug 07 Sun: EE63; 2025 Aug 08 Mon: EE63; 2025 Aug 10 Wed: EE60; 2025 Aug 11 Thu: EE60; 2025 Aug 12 Fri: EE60; 2025 Aug 13 Sat: EE60; 2025 Aug 14 Sun: EE60; 2025 Aug 15 Mon: EE60; 2025 Aug 16 Tue: EE60; 2025 Aug 24 Wed: EE62; 2025 Aug 25 Thu: EE62; 2025 Aug 26 Fri: EE62; 2025 Aug 27 Sat: EE62; 2025 Aug 28 Sun: EE62; 2025 Aug 29 Mon: EE62; 2025 Aug 30 Tue: EE62; 2025 Aug 01 Wed: EE61; 2025 Aug 02 Thu: EE61; 2025 Aug 03 Fri: EE61; 2025 Aug 04 Sat: EE61; 2025 Aug 05 Sun: EE61; 2025 Aug 06 Mon: EE61; 2025 Aug 07 Tue: EE61
[298 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
[299 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | Data Hall | 10 Fri: EE74; 11 Sat: EE74; 12 Sun: EE74; 13 Mon: EE74; 14 Tue: EE74; 15 Wed: EE74; 16 Thu: EE74; 17 Fri: EE74; 18 Sat: EE74; 19 Sun: EE74; 20 Mon: EE74; 21 Tue: EE74; 22 Wed: EE74; 23 Thu: EE74; 24 Fri: EE74; 25 Sat: EE74; 26 Sun: EE74; 27 Mon: EE74; 04 Tue: J6; 05 Wed: J6; 06 Thu: J6; 07 Fri: J7; 08 Sat: J7; 09 Sun: J7; 10 Mon: J7; 11 Tue: J7; 12 Wed: J7; 13 Thu: J7; 19 Wed: EE73; 20 Thu: EE73; 21 Fri: EE73; 22 Sat: EE73; 23 Sun: EE73; 24 Mon: EE73; 25 Tue: EE73; 26 Wed: EE73; 27 Thu: EE73; 28 Fri: EE73; 01 Sat: EE73; 02 Sun: EE73; 03 Mon: EE73; 04 Tue: EE73; 05 Wed: EE7; 06 Thu: EE7; 07 Fri: EE7; 08 Sat: EE7; 09 Sun: EE7; 10 Mon: EE7; 11 Tue: EE7; 12 Wed: S2; 13 Thu: S2; 14 Fri: S2; 15 Sat: S2; 16 Sun: S2; 17 Mon: S2; 18 Tue: S2; 02 Wed: EE18; 03 Thu: EE18; 04 Fri: EE18; 05 Sat: EE18; 06 Sun: EE18; 07 Mon: EE18; 08 Tue: EE18; 09 Wed: EE18; 10 Thu: EE18; 11 Fri: EE18; 12 Sat: EE18; 13 Sun: EE18; 14 Mon: EE18; 15 Tue: EE18
[117 empty] | S1 | S1 | S1 | S1 | S1 | S1 | S1 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | [14 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[117 empty] | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7
[119 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10
|  | Electrical Room | 13 Mon: EE1; 14 Tue: EE1; 15 Wed: EE1; 16 Thu: EE1; 17 Fri: EE1; 18 Sat: EE1; 19 Sun: EE1; 20 Mon: EE1; 21 Tue: EE1; 22 Wed: EE1; 23 Thu: EE1; 24 Fri: EE1; 27 Mon: J17; 28 Tue: J17; 29 Wed: J17; 30 Thu: GH3; 31 Fri: GH3; 01 Sat: GH3; 02 Sun: GH3; 03 Mon: GH3; 04 Tue: GH3; 05 Wed: GH3; 11 Tue: EE72; 12 Wed: EE72; 13 Thu: EE72; 14 Fri: EE72; 15 Sat: EE72; 16 Sun: EE72; 17 Mon: EE72; 18 Tue: EE72; 19 Wed: EE72; 20 Thu: EE72; 21 Fri: EE72; 22 Sat: EE72; 23 Sun: EE72; 24 Mon: EE72; 04 Tue: EE29; 05 Wed: EE29; 06 Thu: EE29; 07 Fri: EE29; 08 Sat: EE29; 09 Sun: EE29; 10 Mon: EE29; 11 Tue: EE29; 12 Wed: EE29; 13 Thu: EE29; 14 Fri: EE29; 15 Sat: EE29; 16 Sun: EE29; 17 Mon: EE29; 18 Tue: EE29; 19 Wed: EE29; 20 Thu: EE29; 21 Fri: EE29; 22 Sat: EE29; 23 Sun: EE29; 24 Mon: EE29; 27 Thu: ALL3; 28 Fri: ALL3; 29 Sat: ALL3; 30 Sun: ALL3; 31 Mon: ALL3; 01 Tue: ALL3; 02 Wed: ALL3
[97 empty] | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | J36 | J36 | J36 | J36 | J36 | J36 | J36
[97 empty] | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23
[97 empty] | EE71 | EE71 | EE71 | EE71 | EE71 | EE71 | EE71
|  | Mech Gallery | 17 Fri: GA12; 18 Sat: GA12; 19 Sun: GA12; 20 Mon: GA12; 21 Tue: T3; 22 Wed: T3; 23 Thu: T3; 24 Fri: T3; 25 Sat: T3; 26 Sun: T3; 27 Mon: T3; 28 Tue: T3; 29 Wed: T3; 30 Thu: T3; 31 Fri: T3; 01 Sat: T3; 02 Sun: T3; 03 Mon: T3; 04 Tue: J9; 11 Tue: GA6; 12 Wed: GA6; 13 Thu: GA6; 18 Tue: ET22; 19 Wed: ET22; 20 Thu: ET22; 21 Fri: ET22; 22 Sat: ET22; 23 Sun: ET22; 24 Mon: ET22; 25 Tue: ET22; 26 Wed: ET22; 27 Thu: ET22; 28 Fri: ET22; 01 Sat: ET22; 02 Sun: ET22; 03 Mon: ET22; 04 Tue: ET22; 06 Thu: EE35; 07 Fri: EE35; 08 Sat: EE35; 09 Sun: EE35; 10 Mon: EE35; 11 Tue: EE35; 12 Wed: EE35; 13 Thu: EE35; 14 Fri: EE35; 15 Sat: EE35; 16 Sun: EE35; 17 Mon: EE35; 18 Tue: EE35
[88 empty] | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | [7 empty] | I-R | I-R | I-R | [11 empty] | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36
COLO 4 | All | CX - Microsoft | 2025 Aug 18 Tue: MS1; 2025 Aug 19 Wed: MS1; 2025 Aug 20 Thu: MS1; 2025 Aug 21 Fri: MS1; 2025 Aug 22 Sat: MS1; 2025 Aug 23 Sun: MS1; 2025 Aug 24 Mon: MS1; 2025 Aug 25 Tue: MS1; 2025 Aug 26 Wed: MS1; 2025 Aug 27 Thu: MS1; 2025 Aug 28 Fri: MS1; 2025 Aug 29 Sat: MS1; 2025 Aug 30 Sun: MS1; 2025 Aug 01 Mon: MS1; 2025 Aug 02 Tue: MS1; 2025 Aug 03 Wed: MS1; 2025 Aug 04 Thu: MS1; 2025 Aug 05 Fri: MS1; 2025 Aug 06 Sat: MS1; 2025 Aug 07 Sun: MS1; 2025 Aug 08 Mon: MS1; 2025 Aug 09 Tue: MS1; 2025 Aug 10 Wed: MS1; 2025 Aug 11 Thu: MS1; 2025 Aug 12 Fri: MS1; 2025 Aug 13 Sat: MS1; 2025 Aug 14 Sun: MS1; 2025 Aug 15 Mon: MS1; 2025 Aug 16 Tue: MS1; 2025 Aug 18 Thu: MS2; 2025 Aug 19 Fri: MS2
| Cell 1 | CX - L1 | 17 Fri: EE59; 24 Fri: EE62; 14 Fri: EE63; 18 Tue: EE61
EE57
EE60
EE58
|  | CX - L2 | 28 Mon: EE57; 29 Tue: EE57; 30 Wed: EE57; 01 Thu: EE57; 02 Fri: EE57; 05 Mon: EE62; 06 Tue: EE62; 07 Wed: EE62; 08 Thu: EE62; 09 Fri: EE62; 12 Mon: EE60; 13 Tue: EE60; 14 Wed: EE60; 15 Thu: EE60; 16 Fri: EE60; 19 Mon: EE59; 20 Tue: EE59; 21 Wed: EE59; 22 Thu: EE59; 23 Fri: EE59
[178 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE61 | EE61 | EE61 | EE61 | EE61
[178 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | 2025 Aug 29 Mon: EE57; 2025 Aug 30 Tue: EE57; 2025 Aug 01 Wed: EE57; 2025 Aug 02 Thu: EE57; 2025 Aug 03 Fri: EE57; 2025 Aug 06 Mon: EE62; 2025 Aug 07 Tue: EE62; 2025 Aug 08 Wed: EE62; 2025 Aug 09 Thu: EE62; 2025 Aug 10 Fri: EE62; 2025 Aug 13 Mon: EE60; 2025 Aug 14 Tue: EE60; 2025 Aug 15 Wed: EE60; 2025 Aug 16 Thu: EE60; 2025 Aug 17 Fri: EE60; 2025 Aug 20 Mon: EE59; 2025 Aug 21 Tue: EE59; 2025 Aug 22 Wed: EE59; 2025 Aug 23 Thu: EE59; 2025 Aug 24 Fri: EE59; 2025 Aug 25 Sat: EE59; 2025 Aug 26 Sun: EE59; 2025 Aug 27 Mon: EE59; 2025 Aug 28 Tue: EE59; 2025 Aug 29 Wed: EE59; 2025 Aug 30 Thu: EE59; 2025 Aug 31 Fri: EE59; 2025 Aug 03 Mon: EE61; 2025 Aug 04 Tue: EE61; 2025 Aug 05 Wed: EE61; 2025 Aug 06 Thu: EE61; 2025 Aug 07 Fri: EE61
[332 empty] | EE63 | EE63 | EE63 | EE63 | EE63
[332 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | 17 Fri: J7; 18 Sat: J7; 19 Sun: J7; 20 Mon: J7; 21 Tue: J7; 22 Wed: J7; 23 Thu: J7; 24 Fri: EE73; 25 Sat: EE73; 26 Sun: EE73; 27 Mon: EE73; 28 Tue: EE73; 29 Wed: EE73; 30 Thu: EE73; 31 Fri: EE73; 01 Sat: EE73; 02 Sun: EE73; 03 Mon: EE73; 04 Tue: EE73; 05 Wed: EE73; 06 Thu: EE73; 07 Fri: EE7; 08 Sat: EE7; 09 Sun: EE7; 10 Mon: EE7; 11 Tue: EE7; 12 Wed: EE7; 13 Thu: EE7; 14 Fri: S2; 15 Sat: S2; 16 Sun: S2; 17 Mon: S2; 18 Tue: S2; 19 Wed: S2; 20 Thu: S2; 21 Fri: ET22; 22 Sat: ET22; 23 Sun: ET22; 24 Mon: ET22; 25 Tue: ET22; 26 Wed: ET22; 27 Thu: ET22; 28 Fri: ET22; 01 Sat: ET22; 02 Sun: ET22; 03 Mon: ET22; 04 Tue: ET22; 05 Wed: ET22; 06 Thu: ET22; 14 Fri: ALL3; 15 Sat: ALL3; 16 Sun: ALL3; 17 Mon: ALL3; 18 Tue: ALL3; 19 Wed: ALL3; 20 Thu: ALL3
[91 empty] | S1 | S1 | S1 | S1 | S1 | S1 | S1 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17
[95 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 |  |  |  | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | 14 Tue: EE72; 15 Wed: EE72; 16 Thu: EE72; 17 Fri: EE72; 18 Sat: EE72; 19 Sun: EE72; 20 Mon: EE72; 21 Tue: EE72; 22 Wed: EE72; 23 Thu: EE72; 24 Fri: EE72; 25 Sat: EE72; 26 Sun: EE72; 27 Mon: EE72; 11 Tue: EE28; 12 Wed: EE28; 13 Thu: EE28; 14 Fri: EE28; 15 Sat: EE28; 16 Sun: EE28; 17 Mon: EE28; 18 Tue: EE29; 19 Wed: EE29; 20 Thu: EE29; 21 Fri: EE29; 22 Sat: EE29; 23 Sun: EE29; 24 Mon: EE29; 25 Tue: EE29; 26 Wed: EE29; 27 Thu: EE29; 28 Fri: EE29; 01 Sat: EE29; 02 Sun: EE29; 03 Mon: EE29; 04 Tue: EE29; 05 Wed: EE29; 06 Thu: EE29; 07 Fri: EE29; 08 Sat: EE29; 09 Sun: EE29; 10 Mon: EE29
[70 empty] | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | [34 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[70 empty] | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23
[70 empty] | EE71 | EE71 | EE71 | EE71 | EE71 | EE71 | EE71
|  | Mech Gallery | 10 Fri: EE70; 11 Sat: EE70; 12 Sun: EE70; 13 Mon: EE70; 14 Tue: EE70; 15 Wed: EE70; 16 Thu: EE70; 17 Fri: EE70; 18 Sat: EE70; 19 Sun: EE70; 20 Mon: EE70; 21 Tue: EE70; 22 Wed: EE70; 23 Thu: EE70; 24 Fri: EE70; 25 Sat: EE70; 26 Sun: EE70; 27 Mon: EE70; 28 Tue: EE70; 29 Wed: EE70; 30 Thu: EE70; 04 Tue: I-R; 05 Wed: I-R; 06 Thu: I-R; 18 Tue: EE36; 19 Wed: EE36; 20 Thu: EE36; 21 Fri: EE36; 22 Sat: EE36; 23 Sun: EE36; 24 Mon: EE36; 25 Tue: EE36
[70 empty] | GA6 | GA6 | GA6 | GA6 | GA6 | [15 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
[74 empty] | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1
| Cell 2 | CX - L1 | 10 Mon: EE62; 11 Tue: EE59; 07 Fri: EE63; 11 Tue: EE61
EE57
EE60
EE58
|  | CX - L2 | 28 Mon: EE57; 29 Tue: EE57; 30 Wed: EE57; 01 Thu: EE57; 02 Fri: EE57; 05 Mon: EE62; 06 Tue: EE62; 07 Wed: EE62; 08 Thu: EE62; 09 Fri: EE62; 12 Mon: EE60; 13 Tue: EE60; 14 Wed: EE60; 15 Thu: EE60; 16 Fri: EE60; 19 Mon: EE59; 20 Tue: EE59; 21 Wed: EE59; 22 Thu: EE59; 23 Fri: EE59
[178 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE61 | EE61 | EE61 | EE61 | EE61
[178 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | 2025 Aug 29 Mon: EE57; 2025 Aug 30 Tue: EE57; 2025 Aug 01 Wed: EE57; 2025 Aug 02 Thu: EE57; 2025 Aug 03 Fri: EE57; 2025 Aug 06 Mon: EE62; 2025 Aug 07 Tue: EE62; 2025 Aug 08 Wed: EE62; 2025 Aug 09 Thu: EE62; 2025 Aug 10 Fri: EE62; 2025 Aug 13 Mon: EE60; 2025 Aug 14 Tue: EE60; 2025 Aug 15 Wed: EE60; 2025 Aug 16 Thu: EE60; 2025 Aug 17 Fri: EE60; 2025 Aug 20 Mon: EE59; 2025 Aug 21 Tue: EE59; 2025 Aug 22 Wed: EE59; 2025 Aug 23 Thu: EE59; 2025 Aug 24 Fri: EE59; 2025 Aug 25 Sat: EE59; 2025 Aug 26 Sun: EE59; 2025 Aug 27 Mon: EE59; 2025 Aug 28 Tue: EE59; 2025 Aug 29 Wed: EE59; 2025 Aug 30 Thu: EE59; 2025 Aug 31 Fri: EE59; 2025 Aug 03 Mon: EE61; 2025 Aug 04 Tue: EE61; 2025 Aug 05 Wed: EE61; 2025 Aug 06 Thu: EE61; 2025 Aug 07 Fri: EE61
[332 empty] | EE63 | EE63 | EE63 | EE63 | EE63
[332 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | 10 Fri: EE74; 11 Sat: EE74; 12 Sun: EE74; 13 Mon: EE74; 14 Tue: EE74; 15 Wed: EE74; 16 Thu: EE74; 17 Fri: EE74; 18 Sat: EE74; 19 Sun: EE74; 20 Mon: EE74; 21 Tue: EE74; 22 Wed: EE74; 23 Thu: EE74; 24 Fri: EE74; 25 Sat: EE74; 26 Sun: EE74; 27 Mon: EE74; 04 Tue: J6; 05 Wed: J6; 06 Thu: J6; 07 Fri: J7; 08 Sat: J7; 09 Sun: J7; 10 Mon: J7; 11 Tue: J7; 12 Wed: J7; 13 Thu: J7; 14 Fri: EE73; 15 Sat: EE73; 16 Sun: EE73; 17 Mon: EE73; 18 Tue: EE73; 19 Wed: EE73; 20 Thu: EE73; 21 Fri: EE73; 22 Sat: EE73; 23 Sun: EE73; 24 Mon: EE73; 25 Tue: EE73; 26 Wed: EE73; 27 Thu: EE73; 28 Fri: EE7; 01 Sat: EE7; 02 Sun: EE7; 03 Mon: EE7; 04 Tue: EE7; 05 Wed: EE7; 06 Thu: EE7; 07 Fri: S2; 08 Sat: S2; 09 Sun: S2; 10 Mon: S2; 11 Tue: S2; 12 Wed: S2; 13 Thu: S2; 14 Fri: ET7; 15 Sat: ET7; 16 Sun: ET7; 17 Mon: ET7; 18 Tue: ET7; 19 Wed: ET7; 20 Thu: ET7; 21 Fri: ET7; 22 Sat: ET7; 23 Sun: ET7; 24 Mon: ET7; 25 Tue: ET7; 26 Wed: ET7; 27 Thu: ET7; 28 Fri: ALL3; 29 Sat: ALL3; 30 Sun: ALL3; 31 Mon: ALL3; 01 Tue: ALL3; 02 Wed: ALL3; 03 Thu: ALL3
[112 empty] | S1 | S1 | S1 | S1 | S1 | S1 | S1 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17
[116 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | 21 Tue: EE1; 22 Wed: EE1; 23 Thu: EE1; 24 Fri: EE1; 25 Sat: EE1; 26 Sun: EE1; 27 Mon: EE1; 28 Tue: J17; 29 Wed: J17; 30 Thu: J17; 31 Fri: GH3; 01 Sat: GH3; 02 Sun: GH3; 03 Mon: GH3; 04 Tue: GH3; 05 Wed: GH3; 06 Thu: GH3; 10 Mon: J36; 11 Tue: J36; 12 Wed: J36; 13 Thu: J36; 14 Fri: J36; 18 Tue: EE28; 19 Wed: EE28; 20 Thu: EE28; 21 Fri: EE28; 22 Sat: EE28; 23 Sun: EE28; 24 Mon: EE28; 11 Tue: EE29; 12 Wed: EE29; 13 Thu: EE29; 14 Fri: EE29; 15 Sat: EE29; 16 Sun: EE29; 17 Mon: EE29; 18 Tue: EE29; 19 Wed: EE29; 20 Thu: EE29; 21 Fri: EE29; 22 Sat: EE29; 23 Sun: EE29; 24 Mon: EE29; 25 Tue: EE29; 26 Wed: EE29; 27 Thu: EE29; 28 Fri: EE29; 29 Sat: EE29; 30 Sun: EE29; 31 Mon: EE29
[83 empty] | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | [42 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[87 empty] | EE27 | EE27 | EE27 | EE27 | EE27
[87 empty] | EE23 | EE23 | EE23 | EE23 | EE23
|  | Mech Gallery | 17 Fri: GA12; 18 Sat: GA12; 19 Sun: GA12; 20 Mon: GA12; 21 Tue: T3; 22 Wed: T3; 23 Thu: T3; 24 Fri: T3; 25 Sat: T3; 26 Sun: T3; 27 Mon: T3; 28 Tue: T3; 29 Wed: T3; 30 Thu: T3; 31 Fri: T3; 01 Sat: T3; 02 Sun: T3; 03 Mon: T3; 04 Tue: J9; 11 Tue: GA6; 12 Wed: GA6; 13 Thu: GA6; 27 Thu: I-R; 28 Fri: I-R; 01 Sat: I-R; 02 Sun: I-R; 03 Mon: I-R; 13 Thu: EE36; 14 Fri: EE36; 15 Sat: EE36; 16 Sun: EE36; 17 Mon: EE36; 18 Tue: EE36; 19 Wed: EE36; 20 Thu: EE36
[88 empty] | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | [6 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
[97 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22
| Cell 3 | CX - L1 | 24 Mon: EE62; 25 Tue: EE59; 21 Fri: EE63; 25 Tue: EE61
EE57
EE60
EE58
|  | CX - L2 | 05 Mon: EE57; 06 Tue: EE57; 07 Wed: EE57; 08 Thu: EE57; 09 Fri: EE57; 12 Mon: EE62; 13 Tue: EE62; 14 Wed: EE62; 15 Thu: EE62; 16 Fri: EE62; 19 Mon: EE60; 20 Tue: EE60; 21 Wed: EE60; 22 Thu: EE60; 23 Fri: EE60; 27 Tue: EE59; 28 Wed: EE59; 29 Thu: EE59; 30 Fri: EE59; 31 Sat: EE59; 01 Sun: EE59; 02 Mon: EE59
[185 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE61 | EE61 | EE61 | EE61 | EE61
[185 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | 2025 Aug 06 Mon: EE57; 2025 Aug 07 Tue: EE57; 2025 Aug 08 Wed: EE57; 2025 Aug 09 Thu: EE57; 2025 Aug 10 Fri: EE57; 2025 Aug 13 Mon: EE62; 2025 Aug 14 Tue: EE62; 2025 Aug 15 Wed: EE62; 2025 Aug 16 Thu: EE62; 2025 Aug 17 Fri: EE62; 2025 Aug 20 Mon: EE60; 2025 Aug 21 Tue: EE60; 2025 Aug 22 Wed: EE60; 2025 Aug 23 Thu: EE60; 2025 Aug 24 Fri: EE60; 2025 Aug 27 Mon: EE59; 2025 Aug 28 Tue: EE59; 2025 Aug 29 Wed: EE59; 2025 Aug 30 Thu: EE59; 2025 Aug 31 Fri: EE59; 2025 Aug 01 Sat: EE59; 2025 Aug 02 Sun: EE59; 2025 Aug 03 Mon: EE59; 2025 Aug 04 Tue: EE59; 2025 Aug 05 Wed: EE59; 2025 Aug 06 Thu: EE59; 2025 Aug 07 Fri: EE59; 2025 Aug 10 Mon: EE61; 2025 Aug 11 Tue: EE61; 2025 Aug 12 Wed: EE61; 2025 Aug 13 Thu: EE61; 2025 Aug 14 Fri: EE61
[339 empty] | EE63 | EE63 | EE63 | EE63 | EE63
[339 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | 28 Tue: EE74; 29 Wed: EE74; 30 Thu: EE74; 31 Fri: EE74; 01 Sat: EE74; 02 Sun: EE74; 03 Mon: EE74; 04 Tue: EE74; 05 Wed: EE74; 06 Thu: EE74; 07 Fri: EE74; 08 Sat: EE74; 09 Sun: EE74; 10 Mon: EE74; 11 Tue: EE74; 12 Wed: EE74; 18 Tue: J6; 19 Wed: J6; 20 Thu: J6; 21 Fri: J7; 22 Sat: J7; 23 Sun: J7; 24 Mon: J7; 25 Tue: J7; 26 Wed: J7; 27 Thu: J7; 28 Fri: EE73; 01 Sat: EE73; 02 Sun: EE73; 03 Mon: EE73; 04 Tue: EE73; 05 Wed: EE73; 06 Thu: EE73; 07 Fri: EE73; 08 Sat: EE73; 09 Sun: EE73; 10 Mon: EE73; 11 Tue: EE73; 12 Wed: EE73; 13 Thu: EE73; 14 Fri: EE7; 15 Sat: EE7; 16 Sun: EE7; 17 Mon: EE7; 18 Tue: EE7; 19 Wed: EE7; 20 Thu: EE7; 21 Fri: S2; 22 Sat: S2; 23 Sun: S2; 24 Mon: S2; 25 Tue: S2; 26 Wed: S2; 27 Thu: S2; 28 Fri: ET7; 29 Sat: ET7; 30 Sun: ET7; 31 Mon: ET7; 01 Tue: ET7; 02 Wed: ET7; 03 Thu: ET7; 04 Fri: ET7; 05 Sat: ET7; 06 Sun: ET7; 07 Mon: ET7; 08 Tue: ET7; 09 Wed: ET7; 10 Thu: ET7; 15 Tue: ALL3; 16 Wed: ALL3; 17 Thu: ALL3; 18 Fri: ALL3; 19 Sat: ALL3; 20 Sun: ALL3; 21 Mon: ALL3
[126 empty] | S1 | S1 | S1 | S1 | S1 | S1 | S1 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17
[130 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [7 empty] | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | 28 Tue: EE1; 29 Wed: EE1; 30 Thu: EE1; 31 Fri: EE1; 01 Sat: EE1; 02 Sun: EE1; 03 Mon: EE1; 04 Tue: EE1; 05 Wed: EE1; 06 Thu: EE1; 07 Fri: EE1; 08 Sat: EE1; 09 Sun: EE1; 10 Mon: EE1; 11 Tue: J17; 12 Wed: J17; 13 Thu: J17; 14 Fri: GH3; 15 Sat: GH3; 16 Sun: GH3; 17 Mon: GH3; 18 Tue: GH3; 19 Wed: GH3; 20 Thu: GH3; 24 Mon: J36; 25 Tue: J36; 26 Wed: J36; 27 Thu: J36; 28 Fri: J36; 01 Tue: EE29; 02 Wed: EE29; 03 Thu: EE29; 04 Fri: EE29; 05 Sat: EE29; 06 Sun: EE29; 07 Mon: EE29; 08 Tue: EE29; 09 Wed: EE29; 10 Thu: EE29; 11 Fri: EE29; 12 Sat: EE29; 13 Sun: EE29; 14 Mon: EE29; 15 Tue: EE29; 16 Wed: EE29; 17 Thu: EE29; 18 Fri: EE29; 19 Sat: EE29; 20 Sun: EE29; 21 Mon: EE29
[97 empty] | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | [49 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[101 empty] | EE27 | EE27 | EE27 | EE27 | EE27 |  |  |  | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28
[101 empty] | EE23 | EE23 | EE23 | EE23 | EE23
|  | Mech Gallery | 10 Fri: EE73; 11 Sat: EE73; 12 Sun: EE73; 13 Mon: EE73; 14 Tue: EE73; 15 Wed: EE73; 16 Thu: EE73; 17 Fri: EE73; 18 Sat: EE73; 19 Sun: EE73; 20 Mon: EE73; 21 Tue: EE73; 22 Wed: EE73; 23 Thu: EE73; 24 Fri: GA12; 25 Sat: GA12; 26 Sun: GA12; 27 Mon: GA12; 04 Tue: T3; 05 Wed: T3; 06 Thu: T3; 07 Fri: T3; 08 Sat: T3; 09 Sun: T3; 10 Mon: T3; 11 Tue: T3; 12 Wed: T3; 13 Thu: T3; 14 Fri: T3; 15 Sat: T3; 16 Sun: T3; 17 Mon: T3; 18 Tue: J9; 25 Tue: GA6; 26 Wed: GA6; 27 Thu: GA6; 13 Thu: I-R; 14 Fri: I-R; 15 Sat: I-R; 16 Sun: I-R; 17 Mon: I-R; 27 Thu: EE36; 28 Fri: EE36; 29 Sat: EE36; 30 Sun: EE36; 31 Mon: EE36; 01 Tue: EE36; 02 Wed: EE36; 03 Thu: EE36
[102 empty] | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | [6 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
[111 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22
| Cell 4 | CX - L1 | 06 Thu: EE57; 07 Fri: EE57; 08 Sat: EE57; 09 Sun: EE57; 10 Mon: EE57; 11 Tue: EE59; 12 Wed: EE59; 13 Thu: EE59; 04 Fri: EE63; 05 Sat: EE63; 06 Sun: EE63; 07 Mon: EE63; 08 Tue: EE63
[118 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | [28 empty] | EE61 | EE61 | EE61
[118 empty] | EE58 | EE58 | EE58 | EE58 | EE58
[122 empty] | EE62 | EE62 | EE62
|  | CX - L2 | 13 Tue: EE57; 14 Wed: EE57; 15 Thu: EE57; 16 Fri: EE57; 17 Sat: EE57; 18 Sun: EE57; 19 Mon: EE57; 20 Tue: EE62; 21 Wed: EE62; 22 Thu: EE62; 23 Fri: EE62; 24 Sat: EE62; 25 Sun: EE62; 26 Mon: EE62; 27 Tue: EE62; 28 Wed: EE60; 29 Thu: EE60; 30 Fri: EE60; 31 Sat: EE60; 01 Sun: EE60; 02 Mon: EE60; 03 Tue: EE60; 16 Wed: EE59; 17 Thu: EE59; 18 Fri: EE59; 19 Sat: EE59; 20 Sun: EE59; 21 Mon: EE59; 22 Tue: EE59; 23 Wed: EE59
[193 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[193 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | 2025 Aug 06 Mon: EE57; 2025 Aug 07 Tue: EE57; 2025 Aug 08 Wed: EE57; 2025 Aug 09 Thu: EE57; 2025 Aug 10 Fri: EE57; 2025 Aug 13 Mon: EE62; 2025 Aug 14 Tue: EE62; 2025 Aug 15 Wed: EE62; 2025 Aug 16 Thu: EE62; 2025 Aug 17 Fri: EE62; 2025 Aug 20 Mon: EE60; 2025 Aug 21 Tue: EE60; 2025 Aug 22 Wed: EE60; 2025 Aug 23 Thu: EE60; 2025 Aug 24 Fri: EE60; 2025 Aug 27 Mon: EE59; 2025 Aug 28 Tue: EE59; 2025 Aug 29 Wed: EE59; 2025 Aug 30 Thu: EE59; 2025 Aug 31 Fri: EE59; 2025 Aug 01 Sat: EE59; 2025 Aug 02 Sun: EE59; 2025 Aug 03 Mon: EE59; 2025 Aug 04 Tue: EE59; 2025 Aug 05 Wed: EE59; 2025 Aug 06 Thu: EE59; 2025 Aug 07 Fri: EE59; 2025 Aug 10 Mon: EE61; 2025 Aug 11 Tue: EE61; 2025 Aug 12 Wed: EE61; 2025 Aug 13 Thu: EE61; 2025 Aug 14 Fri: EE61
[339 empty] | EE63 | EE63 | EE63 | EE63 | EE63
[339 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | 13 Thu: EE74; 14 Fri: EE74; 15 Sat: EE74; 16 Sun: EE74; 17 Mon: EE74; 18 Tue: EE74; 19 Wed: EE74; 20 Thu: EE74; 21 Fri: EE74; 22 Sat: EE74; 23 Sun: EE74; 24 Mon: EE74; 25 Tue: EE74; 26 Wed: EE74; 27 Thu: EE74; 28 Fri: EE74; 04 Tue: J6; 05 Wed: J6; 06 Thu: J6; 07 Fri: J7; 08 Sat: J7; 09 Sun: J7; 10 Mon: J7; 11 Tue: J7; 12 Wed: J7; 13 Thu: J7; 14 Fri: EE73; 15 Sat: EE73; 16 Sun: EE73; 17 Mon: EE73; 18 Tue: EE73; 19 Wed: EE73; 20 Thu: EE73; 21 Fri: EE73; 22 Sat: EE73; 23 Sun: EE73; 24 Mon: EE73; 25 Tue: EE73; 26 Wed: EE73; 27 Thu: EE73; 28 Fri: EE7; 29 Sat: EE7; 30 Sun: EE7; 31 Mon: EE7; 01 Tue: EE7; 02 Wed: EE7; 03 Thu: EE7; 04 Fri: S2; 05 Sat: S2; 06 Sun: S2; 07 Mon: S2; 08 Tue: S2; 09 Wed: S2; 10 Thu: S2; 11 Fri: ET7; 12 Sat: ET7; 13 Sun: ET7; 14 Mon: ET7; 15 Tue: ET7; 16 Wed: ET7; 17 Thu: ET7; 18 Fri: ET7; 19 Sat: ET7; 20 Sun: ET7; 21 Mon: ET7; 22 Tue: ET7; 23 Wed: ET7; 24 Thu: ET7; 06 Tue: ALL3; 07 Wed: ALL3; 08 Thu: ALL3; 09 Fri: ALL3; 10 Sat: ALL3; 11 Sun: ALL3; 12 Mon: ALL3
[140 empty] | S1 | S1 | S1 | S1 | S1 | S1 | S1 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 |  |  |  |  | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
[144 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10
[147 empty] | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4
|  | Electrical Room | 10 Fri: T3; 11 Sat: T3; 12 Sun: T3; 13 Mon: T3; 14 Tue: T3; 15 Wed: T3; 16 Thu: T3; 17 Fri: T3; 18 Sat: T3; 19 Sun: T3; 20 Mon: T3; 21 Tue: T3; 22 Wed: T3; 23 Thu: T3; 11 Tue: EE1; 12 Wed: EE1; 13 Thu: EE1; 14 Fri: EE1; 15 Sat: EE1; 16 Sun: EE1; 17 Mon: EE1; 18 Tue: EE1; 19 Wed: EE1; 20 Thu: EE1; 21 Fri: EE1; 22 Sat: EE1; 23 Sun: EE1; 24 Mon: EE1; 25 Tue: J17; 26 Wed: J17; 27 Thu: J17; 28 Fri: GH3; 01 Sat: GH3; 02 Sun: GH3; 03 Mon: GH3; 04 Tue: GH3; 05 Wed: GH3; 06 Thu: GH3; 10 Mon: J36; 11 Tue: J36; 12 Wed: J36; 13 Thu: J36; 14 Fri: J36; 22 Tue: EE29; 23 Wed: EE29; 24 Thu: EE29; 25 Fri: EE29; 26 Sat: EE29; 27 Sun: EE29; 28 Mon: EE29; 29 Tue: EE29; 30 Wed: EE29; 01 Thu: EE29; 02 Fri: EE29; 03 Sat: EE29; 04 Sun: EE29; 05 Mon: EE29; 06 Tue: EE29; 07 Wed: EE29; 08 Thu: EE29; 09 Fri: EE29; 10 Sat: EE29; 11 Sun: EE29; 12 Mon: EE29
[74 empty] | J37 | J37 | J37 | J37 | J37 | J37 | J37 | [30 empty] | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | [61 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[111 empty] | EE71 | EE71 | EE71 | EE71 | EE71 | EE71 | EE71
[111 empty] | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72
|  | Mech Gallery | 14 Tue: GA3; 15 Wed: GA3; 16 Thu: GA3; 17 Fri: GA3; 18 Sat: GA3; 19 Sun: GA3; 20 Mon: GA3; 24 Fri: EE73; 25 Sat: EE73; 26 Sun: EE73; 27 Mon: EE73; 28 Tue: EE73; 29 Wed: EE73; 30 Thu: EE73; 31 Fri: EE73; 01 Sat: EE73; 02 Sun: EE73; 03 Mon: EE73; 04 Tue: EE73; 05 Wed: EE73; 06 Thu: EE73; 07 Fri: GA12; 08 Sat: GA12; 09 Sun: GA12; 10 Mon: GA12; 18 Tue: T3; 19 Wed: T3; 20 Thu: T3; 21 Fri: T3; 22 Sat: T3; 23 Sun: T3; 24 Mon: T3; 25 Tue: T3; 26 Wed: T3; 27 Thu: T3; 28 Fri: T3; 01 Sat: T3; 02 Sun: T3; 03 Mon: T3; 04 Tue: J9; 11 Tue: GA6; 12 Wed: GA6; 13 Thu: GA6; 27 Thu: I-R; 28 Fri: I-R; 29 Sat: I-R; 30 Sun: I-R; 31 Mon: I-R; 10 Thu: EE36; 11 Fri: EE36; 12 Sat: EE36; 13 Sun: EE36; 14 Mon: EE36; 15 Tue: EE36; 16 Wed: EE36; 17 Thu: EE36
[116 empty] | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | [6 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
[125 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22
Yardwork | COLO 2 | North | 10 Mon: RC1; 11 Tue: RC1; 12 Wed: RC1; 13 Thu: RC1; 14 Fri: RC1; 15 Sat: RC1; 16 Sun: RC1; 17 Mon: RC1; 18 Tue: RC1; 19 Wed: RC1; 20 Thu: RC1; 21 Fri: RC1; 22 Sat: RC1; 23 Sun: RC1; 24 Mon: RC1; 25 Tue: RC1; 26 Wed: RC1; 27 Thu: RC1; 28 Fri: RC1; 01 Sat: RC1; 02 Sun: RC1; 03 Mon: RC1; 04 Tue: RC1; 05 Wed: RC1; 06 Thu: RC1; 07 Fri: RC1
|  | South | 11 Mon: RC1; 12 Tue: RC1; 13 Wed: RC1; 14 Thu: RC1; 15 Fri: RC1; 16 Sat: RC1; 17 Sun: RC1; 18 Mon: RC1; 19 Tue: RC1; 20 Wed: RC1; 21 Thu: RC1; 22 Fri: RC1; 23 Sat: RC1; 24 Sun: RC1; 25 Mon: RC1; 26 Tue: RC1; 27 Wed: RC1; 28 Thu: RC1; 29 Fri: RC1; 30 Sat: RC1; 01 Sun: RC1; 02 Mon: RC1; 03 Tue: RC1; 04 Wed: RC1; 05 Thu: RC1; 06 Fri: RC1; 07 Sat: RC1; 08 Sun: RC1; 09 Mon: RC1; 10 Tue: RC1; 11 Wed: RC1; 12 Thu: RC1; 13 Fri: RC1; 14 Sat: RC1; 15 Sun: RC1; 16 Mon: RC1; 17 Tue: RC1; 18 Wed: RC1; 19 Thu: RC1; 20 Fri: RC1; 21 Sat: RC1; 22 Sun: RC1; 23 Mon: RC1; 24 Tue: RC1; 25 Wed: RC1; 26 Thu: RC1; 27 Fri: RC1; 28 Sat: RC1; 29 Sun: RC1; 30 Mon: RC1; 31 Tue: RC1; 01 Wed: RC1; 02 Thu: RC1; 03 Fri: RC1; 04 Sat: RC1; 05 Sun: RC1; 06 Mon: RC1; 07 Tue: RC1; 08 Wed: RC1; 09 Thu: RC1; 10 Fri: RC1; 11 Sat: RC1; 12 Sun: RC1; 13 Mon: RC1; 14 Tue: RC1; 15 Wed: RC1; 16 Thu: RC1; 17 Fri: RC1; 18 Sat: RC1; 19 Sun: RC1; 20 Mon: RC1; 21 Tue: RC1; 22 Wed: RC1; 23 Thu: RC1; 24 Fri: RC1; 25 Sat: RC1; 26 Sun: RC1; 27 Mon: RC1; 28 Tue: RC1; 29 Wed: RC1; 30 Thu: RC1; 31 Fri: RC1; 01 Sat: RC1; 02 Sun: RC1; 03 Mon: RC1; 04 Tue: RC1; 05 Wed: RC1; 06 Thu: RC1; 07 Fri: RC1; 08 Sat: RC1; 09 Sun: RC1; 10 Mon: RC1; 11 Tue: RC1; 12 Wed: RC1; 13 Thu: RC1; 14 Fri: RC1; 15 Sat: RC1; 16 Sun: RC1; 17 Mon: RC1; 18 Tue: RC1; 19 Wed: RC1; 20 Thu: RC1; 21 Fri: RC1; 22 Sat: RC1; 23 Sun: RC1; 24 Mon: RC1; 25 Tue: RC1; 26 Wed: RC1; 27 Thu: RC1; 28 Fri: RC1; 01 Sat: RC1; 02 Sun: RC1; 03 Mon: RC1; 04 Tue: RC1; 05 Wed: RC1; 06 Thu: RC1; 07 Fri: RC1
[49 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
| COLO 3 | North | 27 Fri: EE35; 28 Sat: EE35; 29 Sun: EE35; 30 Mon: EE35; 31 Tue: EE35; 01 Wed: EE35; 02 Thu: EE35; 03 Fri: EE35; 04 Sat: EE35; 05 Sun: EE35; 06 Mon: EE35; 07 Tue: EE35; 08 Wed: EE35; 09 Thu: EE35; 10 Fri: EE35; 11 Sat: EE35; 12 Sun: EE35; 13 Mon: EE35; 14 Tue: EE35; 15 Wed: EE35; 16 Thu: EE35; 17 Fri: EE35; 18 Sat: EE35; 19 Sun: EE35; 20 Mon: EE35; 21 Tue: EE35; 22 Wed: EE35; 23 Thu: EE35; 24 Fri: EE35; 25 Sat: EE35; 26 Sun: EE35; 27 Mon: EE35; 28 Tue: EE35; 29 Wed: EE35; 30 Thu: EE35; 31 Fri: EE35
[52 empty] | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1
[70 empty] | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46
|  | South | 30 Mon: RC1; 31 Tue: RC1; 01 Wed: RC1; 02 Thu: RC1; 03 Fri: RC1; 04 Sat: RC1; 05 Sun: RC1; 06 Mon: RC1; 07 Tue: RC1; 08 Wed: RC1; 09 Thu: RC1; 10 Fri: RC1; 11 Sat: RC1; 12 Sun: RC1; 13 Mon: RC1; 14 Tue: RC1; 15 Wed: RC1; 16 Thu: RC1; 17 Fri: RC1; 18 Sat: RC1; 19 Sun: RC1; 20 Mon: RC1; 21 Tue: RC1; 22 Wed: RC1; 23 Thu: RC1; 24 Fri: RC1; 25 Sat: RC1; 26 Sun: RC1; 27 Mon: RC1; 28 Tue: RC1; 29 Wed: RC1; 30 Thu: RC1; 31 Fri: RC1; 01 Sat: RC1; 02 Sun: RC1; 03 Mon: RC1; 04 Tue: RC1; 05 Wed: RC1; 06 Thu: RC1; 07 Fri: RC1; 08 Sat: RC1; 09 Sun: RC1; 10 Mon: RC1; 11 Tue: RC1; 12 Wed: RC1; 13 Thu: RC1; 14 Fri: RC1; 15 Sat: RC1; 16 Sun: RC1; 17 Mon: RC1; 18 Tue: RC1; 19 Wed: RC1; 20 Thu: RC1; 21 Fri: RC1; 22 Sat: RC1; 23 Sun: RC1; 24 Mon: RC1; 25 Tue: RC1; 26 Wed: RC1; 27 Thu: RC1; 28 Fri: RC1
[70 empty] | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46 | EE46
| COLO 4 | North | 27 Fri: EE35; 28 Sat: EE35; 29 Sun: EE35; 30 Mon: EE35; 31 Tue: EE35; 01 Wed: EE35; 02 Thu: EE35; 03 Fri: EE35; 04 Sat: EE35; 05 Sun: EE35; 06 Mon: EE35; 07 Tue: EE35; 08 Wed: EE35; 09 Thu: EE35; 10 Fri: EE35; 11 Sat: EE35; 12 Sun: EE35; 13 Mon: EE35; 14 Tue: EE35; 15 Wed: EE35; 16 Thu: EE35; 17 Fri: EE35; 18 Sat: EE35; 19 Sun: EE35; 20 Mon: EE35; 21 Tue: EE35; 22 Wed: EE35; 23 Thu: EE35; 24 Fri: EE35; 25 Sat: EE35; 26 Sun: EE35; 27 Mon: EE35; 28 Tue: EE35; 29 Wed: EE35; 30 Thu: EE35; 31 Fri: EE35; 14 Fri: EE46; 15 Sat: EE46; 16 Sun: EE46; 17 Mon: EE46; 18 Tue: EE46; 19 Wed: EE46; 20 Thu: EE46; 21 Fri: EE46; 22 Sat: EE46; 23 Sun: EE46; 24 Mon: EE46; 25 Tue: EE46; 26 Wed: EE46; 27 Thu: EE46; 28 Fri: EE46; 01 Sat: EE46; 02 Sun: EE46; 03 Mon: EE46; 04 Tue: EE46; 05 Wed: EE46; 06 Thu: EE46; 07 Fri: EE46; 08 Sat: EE46; 09 Sun: EE46; 10 Mon: EE46; 11 Tue: EE46; 12 Wed: EE46; 13 Thu: EE46
[115 empty] | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1
|  | South | 27 Fri: EE46; 28 Sat: EE46; 29 Sun: EE46; 30 Mon: EE46; 31 Tue: EE46; 01 Wed: EE46; 02 Thu: EE46; 03 Fri: EE46; 04 Sat: EE46; 05 Sun: EE46; 06 Mon: EE46; 07 Tue: EE46; 08 Wed: EE46; 09 Thu: EE46; 10 Fri: EE46; 11 Sat: EE46; 12 Sun: EE46; 13 Mon: EE46; 14 Tue: EE46; 15 Wed: EE46; 16 Thu: EE46; 17 Fri: EE46; 18 Sat: EE46; 19 Sun: EE46; 20 Mon: EE46; 21 Tue: EE46; 22 Wed: EE46; 23 Thu: EE46; 24 Fri: EE46; 25 Sat: EE46; 26 Sun: EE46; 27 Mon: EE46; 28 Tue: EE46; 29 Wed: EE46; 30 Thu: EE46; 31 Fri: EE46; 14 Fri: EE46; 15 Sat: EE46; 16 Sun: EE46; 17 Mon: EE46; 18 Tue: EE46; 19 Wed: EE46; 20 Thu: EE46; 21 Fri: EE46; 22 Sat: EE46; 23 Sun: EE46; 24 Mon: EE46; 25 Tue: EE46; 26 Wed: EE46; 27 Thu: EE46; 28 Fri: EE46; 01 Sat: EE46; 02 Sun: EE46; 03 Mon: EE46; 04 Tue: EE46; 05 Wed: EE46; 06 Thu: EE46; 07 Fri: EE46; 08 Sat: EE46; 09 Sun: EE46; 10 Mon: EE46; 11 Tue: EE46; 12 Wed: EE46; 13 Thu: EE46
[115 empty] | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1
| COLO 5 | East | 11 Mon: RC1; 12 Tue: RC1; 13 Wed: RC1; 14 Thu: RC1; 15 Fri: RC1; 16 Sat: RC1; 17 Sun: RC1; 18 Mon: RC1; 19 Tue: RC1; 20 Wed: RC1; 21 Thu: RC1; 22 Fri: RC1; 23 Sat: RC1; 24 Sun: RC1; 25 Mon: RC1; 26 Tue: RC1; 27 Wed: RC1; 28 Thu: RC1; 29 Fri: RC1; 30 Sat: RC1; 01 Sun: RC1; 02 Mon: RC1; 03 Tue: RC1; 04 Wed: RC1; 05 Thu: RC1; 06 Fri: RC1; 07 Sat: RC1; 08 Sun: RC1; 09 Mon: RC1; 10 Tue: RC1; 11 Wed: RC1; 12 Thu: RC1; 13 Fri: RC1; 14 Sat: RC1; 15 Sun: RC1; 16 Mon: RC1; 17 Tue: RC1; 18 Wed: RC1; 19 Thu: RC1; 20 Fri: RC1; 21 Sat: RC1; 22 Sun: RC1; 23 Mon: RC1; 24 Tue: RC1; 25 Wed: RC1; 26 Thu: RC1; 27 Fri: RC1; 28 Sat: RC1; 29 Sun: RC1; 30 Mon: RC1; 31 Tue: RC1; 01 Wed: RC1; 02 Thu: RC1; 03 Fri: RC1; 04 Sat: RC1; 05 Sun: RC1; 06 Mon: RC1; 07 Tue: RC1; 08 Wed: RC1; 09 Thu: RC1; 10 Fri: RC1; 11 Sat: RC1; 12 Sun: RC1; 13 Mon: RC1; 14 Tue: RC1; 15 Wed: RC1; 16 Thu: RC1; 17 Fri: RC1; 18 Sat: RC1; 19 Sun: RC1; 20 Mon: RC1; 21 Tue: RC1; 22 Wed: RC1; 23 Thu: RC1; 24 Fri: RC1; 25 Sat: RC1; 26 Sun: RC1; 27 Mon: RC1; 28 Tue: RC1; 29 Wed: RC1; 30 Thu: RC1; 31 Fri: RC1
|  | West | 17 Fri: EE34; 18 Sat: EE34; 19 Sun: EE34; 20 Mon: EE34; 21 Tue: EE34; 03 Mon: RC1; 04 Tue: RC1; 05 Wed: RC1; 06 Thu: RC1; 07 Fri: RC1; 08 Sat: RC1; 09 Sun: RC1; 10 Mon: RC1; 11 Tue: RC1; 12 Wed: RC1; 13 Thu: RC1; 14 Fri: RC1; 15 Sat: RC1; 16 Sun: RC1; 17 Mon: RC1; 18 Tue: RC1; 19 Wed: RC1; 20 Thu: RC1; 21 Fri: RC1; 22 Sat: RC1; 23 Sun: RC1; 24 Mon: RC1; 25 Tue: RC1; 26 Wed: RC1; 27 Thu: RC1; 28 Fri: RC1
Exhaust System | COLO 2 | All | 17 Mon: EE69; 18 Tue: EE69; 19 Wed: EE69; 20 Thu: EE70; 21 Fri: EE70; 22 Sat: EE70; 24 Mon: EE71; 25 Tue: EE71; 26 Wed: EE71; 27 Thu: EE72; 28 Fri: EE72; 01 Sat: EE72
| COLO 3 | All | 11 Tue: EE69; 12 Wed: EE69; 13 Thu: EE69; 14 Fri: EE70; 15 Sat: EE70; 16 Sun: EE70; 17 Mon: EE70; 01 Tue: EE71; 02 Wed: EE71; 03 Thu: EE71; 04 Fri: EE72; 05 Sat: EE72; 06 Sun: EE72; 07 Mon: EE72
| COLO 4 | All | 18 Tue: EE69; 19 Wed: EE69; 20 Thu: EE69; 21 Fri: EE70; 22 Sat: EE70; 23 Sun: EE70; 24 Mon: EE70; 25 Tue: EE71; 26 Wed: EE71; 27 Thu: EE71; 28 Fri: EE72; 29 Sat: EE72; 30 Sun: EE72; 31 Mon: EE72
| COLO 5 | All | 10 Mon: EE70; 11 Tue: EE70; 12 Wed: EE70; 13 Thu: EE71; 14 Fri: EE71; 15 Sat: EE71; 03 Mon: EE72; 04 Tue: EE72; 05 Wed: EE72; 06 Thu: EE69; 07 Fri: EE69; 08 Sat: EE69
| Installed Sets | All | 21 Tue: EE68; 22 Wed: EE68; 23 Thu: EE68; 24 Fri: EE68; 25 Sat: EE68; 26 Sun: EE68; 27 Mon: EE68; 28 Tue: EE68; 29 Wed: EE68; 30 Thu: EE68; 31 Fri: EE68; 01 Sat: EE68; 02 Sun: EE68; 03 Mon: EE68; 04 Tue: EE68; 05 Wed: EE68; 06 Thu: EE68; 07 Fri: EE68; 08 Sat: EE68; 09 Sun: EE68; 10 Mon: EE68; 11 Tue: EE68; 12 Wed: EE68; 13 Thu: EE68; 14 Fri: EE68; 15 Sat: EE68; 16 Sun: EE68; 17 Mon: EE68; 18 Tue: EE68; 19 Wed: EE68; 20 Thu: W16; 21 Fri: W16; 22 Sat: W17; 23 Sun: W17; 24 Mon: W17; 25 Tue: W17; 26 Wed: W17; 27 Thu: W17; 28 Fri: W17; 01 Sat: W17; 02 Sun: W17; 03 Mon: W17; 04 Tue: W17; 05 Wed: W17; 06 Thu: W17; 07 Fri: W17; 08 Sat: W18; 09 Sun: W18; 10 Mon: W18
| Non-Installed Sets | All | 21 Tue: W16; 22 Wed: W16; 23 Thu: W17; 24 Fri: W17; 25 Sat: W17; 26 Sun: W17; 27 Mon: W17; 28 Tue: W17; 29 Wed: W17; 30 Thu: W17; 31 Fri: W17; 01 Sat: W17; 02 Sun: W17; 03 Mon: W17; 04 Tue: W17; 05 Wed: W17; 06 Thu: W17; 07 Fri: W18; 08 Sat: W18
CX Level 2 | COLO 2 | COLO 2 | 11 Tue: EE48; 12 Wed: EE48; 13 Thu: EE48; 14 Fri: EE48; 15 Sat: EE48; 16 Sun: EE48; 17 Mon: EE48; 18 Tue: EE48; 19 Wed: EE48; 20 Thu: EE48; 21 Fri: EE48; 22 Sat: EE48; 23 Sun: EE48; 24 Mon: EE48; 25 Tue: EE48; 26 Wed: EE48; 27 Thu: EE48; 28 Fri: EE48; 01 Sat: EE48; 02 Sun: EE48; 03 Mon: EE48; 04 Tue: EE48; 05 Wed: EE48; 06 Thu: EE48; 07 Fri: EE48; 08 Sat: EE48; 09 Sun: EE48; 10 Mon: EE48
[95 empty] | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49
[96 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
| COLO 3 | COLO 3 | 25 Tue: EE54; 26 Wed: EE54; 27 Thu: EE54; 28 Fri: EE54; 01 Sat: EE54; 02 Sun: EE54; 03 Mon: EE54; 04 Tue: EE55; 05 Wed: EE55; 06 Thu: EE55; 07 Fri: EE55; 08 Sat: EE55; 09 Sun: EE55; 10 Mon: EE55; 08 Tue: EE48; 09 Wed: EE48; 10 Thu: EE48; 11 Fri: EE48; 12 Sat: EE48; 13 Sun: EE48; 14 Mon: EE48; 15 Tue: EE48; 16 Wed: EE48; 17 Thu: EE48; 18 Fri: EE48; 19 Sat: EE48; 20 Sun: EE48; 21 Mon: EE48; 22 Tue: EE48; 23 Wed: EE48; 24 Thu: EE48; 25 Fri: EE48; 26 Sat: EE48; 27 Sun: EE48; 28 Mon: EE48; 29 Tue: EE48; 30 Wed: EE48; 01 Thu: EE48; 02 Fri: EE48; 03 Sat: EE48; 04 Sun: EE48; 05 Mon: EE48; 07 Mon: EE50; 08 Tue: EE50; 09 Wed: EE50; 10 Thu: EE50; 11 Fri: EE50; 12 Sat: EE50; 13 Sun: EE50; 14 Mon: EE50; 15 Tue: EE50; 16 Wed: EE50; 17 Thu: EE50; 18 Fri: EE50; 19 Sat: EE50; 20 Sun: EE50; 21 Mon: EE50; 22 Tue: EE50; 23 Wed: EE50; 24 Thu: EE50; 2025 Jul 25 Fri: EE50; 2025 Jul 26 Sat: EE50; 2025 Jul 27 Sun: EE50; 2025 Jul 28 Mon: EE50; 2025 Jul 29 Tue: EE50; 2025 Jul 30 Wed: EE50; 2025 Jul 31 Thu: EE50; 2025 Aug 01 Fri: EE50
[151 empty] | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49
| COLO 4 | COLO 4 | 06 Tue: EE48; 07 Wed: EE48; 08 Thu: EE48; 09 Fri: EE48; 10 Sat: EE48; 11 Sun: EE48; 12 Mon: EE48; 13 Tue: EE48; 14 Wed: EE48; 15 Thu: EE48; 16 Fri: EE48; 17 Sat: EE48; 18 Sun: EE48; 19 Mon: EE48; 20 Tue: EE48; 21 Wed: EE48; 22 Thu: EE48; 23 Fri: EE48; 24 Sat: EE48; 25 Sun: EE48; 26 Mon: EE48; 27 Tue: EE48; 28 Wed: EE48; 29 Thu: EE48; 30 Fri: EE48; 31 Sat: EE48; 01 Sun: EE48; 02 Mon: EE48; 03 Tue: EE48; 16 Wed: EE50; 17 Thu: EE50; 18 Fri: EE50; 19 Sat: EE50; 20 Sun: EE50; 21 Mon: EE50; 22 Tue: EE50; 23 Wed: EE50; 24 Thu: EE50; 2025 Jul 25 Fri: EE50; 2025 Jul 26 Sat: EE50; 2025 Jul 27 Sun: EE50; 2025 Jul 28 Mon: EE50; 2025 Jul 29 Tue: EE50; 2025 Jul 30 Wed: EE50; 2025 Jul 31 Thu: EE50; 2025 Aug 01 Fri: EE50; 2025 Aug 02 Sat: EE50; 2025 Aug 03 Sun: EE50; 2025 Aug 04 Mon: EE50; 2025 Aug 05 Tue: EE50; 2025 Aug 06 Wed: EE50; 2025 Aug 07 Thu: EE50; 2025 Aug 08 Fri: EE50; 2025 Aug 09 Sat: EE50; 2025 Aug 10 Sun: EE50; 2025 Aug 11 Mon: EE50; 2025 Aug 12 Tue: EE50
[179 empty] | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49
| COLO 5 | COLO 5 | 11 Tue: EE51; 12 Wed: EE51; 13 Thu: EE51; 14 Fri: EE51; 15 Sat: EE51; 16 Sun: EE51; 17 Mon: EE51; 18 Tue: EE52; 19 Wed: EE52; 20 Thu: EE52; 21 Fri: EE52; 22 Sat: EE52; 23 Sun: EE52; 24 Mon: EE52; 11 Tue: EE53; 12 Wed: EE53; 13 Thu: EE53; 14 Fri: EE53; 15 Sat: EE53; 16 Sun: EE53; 17 Mon: EE53; 25 Wed: EE50; 26 Thu: EE50; 27 Fri: EE50; 28 Sat: EE50; 29 Sun: EE50; 30 Mon: EE50; 01 Tue: EE50; 02 Wed: EE50; 03 Thu: EE50; 04 Fri: EE50; 05 Sat: EE50; 06 Sun: EE50; 07 Mon: EE50; 08 Tue: EE50; 09 Wed: EE50; 10 Thu: EE50; 11 Fri: EE50; 12 Sat: EE50; 13 Sun: EE50; 14 Mon: EE50; 15 Tue: EE50; 16 Wed: EE50; 17 Thu: EE50; 18 Fri: EE50; 19 Sat: EE50; 20 Sun: EE50; 21 Mon: EE50; 22 Tue: EE50; 23 Wed: EE50
[123 empty] | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48
[123 empty] | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49
| Site | Site | 03 Mon: EE47; 04 Tue: EE47; 05 Wed: EE47; 06 Thu: EE47; 07 Fri: EE47; 08 Sat: EE47; 09 Sun: EE47; 10 Mon: EE47
CX Level 3 | COLO 2 | All | 28 Fri: EE56
|  | Cell 1 | 14 Fri: EE49; 15 Sat: EE49; 16 Sun: EE49; 17 Mon: EE49; 18 Tue: EE49; 19 Wed: EE49; 20 Thu: EE49; 28 Fri: EE50; 29 Sat: EE50; 30 Sun: EE50; 31 Mon: EE50; 01 Tue: EE50; 02 Wed: EE50; 03 Thu: EE50; 04 Fri: EE48; 05 Sat: EE48; 06 Sun: EE48; 07 Mon: EE48; 08 Tue: EE48; 09 Wed: EE48; 10 Thu: EE48
|  | Cell 2 | 14 Fri: EE49; 15 Sat: EE49; 16 Sun: EE49; 17 Mon: EE49; 18 Tue: EE49; 19 Wed: EE49; 20 Thu: EE49; 28 Fri: EE50; 29 Sat: EE50; 30 Sun: EE50; 31 Mon: EE50; 01 Tue: EE50; 02 Wed: EE50; 03 Thu: EE50; 04 Fri: EE48; 05 Sat: EE48; 06 Sun: EE48; 07 Mon: EE48; 08 Tue: EE48; 09 Wed: EE48; 10 Thu: EE48
|  | Cell 3 | 21 Fri: EE49; 22 Sat: EE49; 23 Sun: EE49; 24 Mon: EE49; 25 Tue: EE49; 26 Wed: EE49; 27 Thu: EE49; 28 Fri: EE50; 29 Sat: EE50; 30 Sun: EE50; 31 Mon: EE50; 01 Tue: EE50; 02 Wed: EE50; 03 Thu: EE50; 04 Fri: EE48; 05 Sat: EE48; 06 Sun: EE48; 07 Mon: EE48; 08 Tue: EE48; 09 Wed: EE48; 10 Thu: EE48
|  | Cell 4 | 28 Fri: EE49; 29 Sat: EE49; 30 Sun: EE49; 31 Mon: EE49; 01 Tue: EE49; 02 Wed: EE49; 03 Thu: EE49; 04 Fri: EE48; 05 Sat: EE48; 06 Sun: EE48; 07 Mon: EE48; 08 Tue: EE48; 09 Wed: EE48; 10 Thu: EE48
[140 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
| COLO 3 | All | 21 Fri: EE55; 22 Sat: EE55; 23 Sun: EE55; 24 Mon: EE55; 25 Tue: EE55; 26 Wed: EE55; 27 Thu: EE55; 11 Fri: EE56
[133 empty] | EE54 | EE54 | EE54 | EE54 | EE54 | EE54 | EE54
|  | Cell 1 | 07 Wed: EE49; 08 Thu: EE49; 09 Fri: EE49; 10 Sat: EE49; 11 Sun: EE49; 12 Mon: EE49; 13 Tue: EE49; 2025 Aug 04 Mon: EE50; 2025 Aug 05 Tue: EE50; 2025 Aug 06 Wed: EE50; 2025 Aug 07 Thu: EE50; 2025 Aug 08 Fri: EE50; 2025 Aug 11 Mon: EE48; 2025 Aug 12 Tue: EE48; 2025 Aug 13 Wed: EE48; 2025 Aug 14 Thu: EE48; 2025 Aug 15 Fri: EE48
|  | Cell 2 | 06 Tue: EE49; 07 Wed: EE49; 08 Thu: EE49; 09 Fri: EE49; 10 Sat: EE49; 11 Sun: EE49; 12 Mon: EE49; 2025 Aug 04 Mon: EE50; 2025 Aug 05 Tue: EE50; 2025 Aug 06 Wed: EE50; 2025 Aug 07 Thu: EE50; 2025 Aug 08 Fri: EE50; 2025 Aug 11 Mon: EE48; 2025 Aug 12 Tue: EE48; 2025 Aug 13 Wed: EE48; 2025 Aug 14 Thu: EE48; 2025 Aug 15 Fri: EE48
|  | Cell 3 | 06 Tue: EE49; 07 Wed: EE49; 08 Thu: EE49; 09 Fri: EE49; 10 Sat: EE49; 11 Sun: EE49; 12 Mon: EE49; 2025 Aug 11 Mon: EE50; 2025 Aug 12 Tue: EE50; 2025 Aug 13 Wed: EE50; 2025 Aug 14 Thu: EE50; 2025 Aug 15 Fri: EE50; 2025 Aug 18 Mon: EE48; 2025 Aug 19 Tue: EE48; 2025 Aug 20 Wed: EE48; 2025 Aug 21 Thu: EE48; 2025 Aug 22 Fri: EE48
|  | Cell 4 | 06 Tue: EE49; 07 Wed: EE49; 08 Thu: EE49; 09 Fri: EE49; 10 Sat: EE49; 11 Sun: EE49; 12 Mon: EE49; 2025 Aug 11 Mon: EE50; 2025 Aug 12 Tue: EE50; 2025 Aug 13 Wed: EE50; 2025 Aug 14 Thu: EE50; 2025 Aug 15 Fri: EE50; 2025 Aug 18 Mon: EE48; 2025 Aug 19 Tue: EE48; 2025 Aug 20 Wed: EE48; 2025 Aug 21 Thu: EE48; 2025 Aug 22 Fri: EE48
| COLO 4 | All | 25 Fri: EE56
|  | Cell 1 | 04 Wed: EE49; 05 Thu: EE49; 06 Fri: EE49; 07 Sat: EE49; 08 Sun: EE49; 09 Mon: EE49; 10 Tue: EE49; 2025 Aug 25 Mon: EE50; 2025 Aug 26 Tue: EE50; 2025 Aug 27 Wed: EE50; 2025 Aug 28 Thu: EE50; 2025 Aug 29 Fri: EE50; 2025 Aug 02 Tue: EE48; 2025 Aug 03 Wed: EE48; 2025 Aug 04 Thu: EE48; 2025 Aug 05 Fri: EE48; 2025 Aug 06 Sat: EE48; 2025 Aug 07 Sun: EE48; 2025 Aug 08 Mon: EE48
|  | Cell 2 | 11 Wed: EE49; 12 Thu: EE49; 13 Fri: EE49; 14 Sat: EE49; 15 Sun: EE49; 16 Mon: EE49; 17 Tue: EE49; 2025 Aug 25 Mon: EE50; 2025 Aug 26 Tue: EE50; 2025 Aug 27 Wed: EE50; 2025 Aug 28 Thu: EE50; 2025 Aug 29 Fri: EE50; 2025 Aug 02 Tue: EE48; 2025 Aug 03 Wed: EE48; 2025 Aug 04 Thu: EE48; 2025 Aug 05 Fri: EE48; 2025 Aug 06 Sat: EE48; 2025 Aug 07 Sun: EE48; 2025 Aug 08 Mon: EE48
|  | Cell 3 | 18 Wed: EE49; 19 Thu: EE49; 20 Fri: EE49; 21 Sat: EE49; 22 Sun: EE49; 23 Mon: EE49; 24 Tue: EE49; 2025 Aug 02 Tue: EE50; 2025 Aug 03 Wed: EE50; 2025 Aug 04 Thu: EE50; 2025 Aug 05 Fri: EE50; 2025 Aug 06 Sat: EE50; 2025 Aug 07 Sun: EE50; 2025 Aug 08 Mon: EE50; 2025 Aug 09 Tue: EE48; 2025 Aug 10 Wed: EE48; 2025 Aug 11 Thu: EE48; 2025 Aug 12 Fri: EE48; 2025 Aug 13 Sat: EE48; 2025 Aug 14 Sun: EE48; 2025 Aug 15 Mon: EE48
|  | Cell 4 | 25 Wed: EE49; 26 Thu: EE49; 27 Fri: EE49; 28 Sat: EE49; 29 Sun: EE49; 30 Mon: EE49; 01 Tue: EE49; 2025 Aug 02 Tue: EE50; 2025 Aug 03 Wed: EE50; 2025 Aug 04 Thu: EE50; 2025 Aug 05 Fri: EE50; 2025 Aug 06 Sat: EE50; 2025 Aug 07 Sun: EE50; 2025 Aug 08 Mon: EE50; 2025 Aug 09 Tue: EE48; 2025 Aug 10 Wed: EE48; 2025 Aug 11 Thu: EE48; 2025 Aug 12 Fri: EE48; 2025 Aug 13 Sat: EE48; 2025 Aug 14 Sun: EE48; 2025 Aug 15 Mon: EE48
| COLO 5 | All | 21 Fri: EE53; 22 Sat: EE53; 23 Sun: EE53; 24 Mon: EE53; 25 Tue: EE53; 26 Wed: EE53; 27 Thu: EE53; 11 Fri: EE56
[133 empty] | EE51 | EE51 | EE51 | EE51 | EE51 | EE51 | EE51
[133 empty] | EE52 | EE52 | EE52 | EE52 | EE52 | EE52 | EE52
|  | Cell 1 | 08 Tue: EE49; 09 Wed: EE49; 10 Thu: EE49; 11 Fri: EE49; 12 Sat: EE49; 13 Sun: EE49; 14 Mon: EE49; 24 Thu: EE50; 2025 Jul 25 Fri: EE50; 2025 Jul 26 Sat: EE50; 2025 Jul 27 Sun: EE50; 2025 Jul 28 Mon: EE50; 2025 Jul 29 Tue: EE50; 2025 Jul 30 Wed: EE50; 2025 Jul 31 Thu: EE48; 2025 Aug 01 Fri: EE48; 2025 Aug 02 Sat: EE48; 2025 Aug 03 Sun: EE48; 2025 Aug 04 Mon: EE48; 2025 Aug 05 Tue: EE48; 2025 Aug 06 Wed: EE48
|  | Cell 2 | 15 Tue: EE49; 16 Wed: EE49; 17 Thu: EE49; 18 Fri: EE49; 19 Sat: EE49; 20 Sun: EE49; 21 Mon: EE49; 24 Thu: EE50; 2025 Jul 25 Fri: EE50; 2025 Jul 26 Sat: EE50; 2025 Jul 27 Sun: EE50; 2025 Jul 28 Mon: EE50; 2025 Jul 29 Tue: EE50; 2025 Jul 30 Wed: EE50; 2025 Jul 31 Thu: EE48; 2025 Aug 01 Fri: EE48; 2025 Aug 02 Sat: EE48; 2025 Aug 03 Sun: EE48; 2025 Aug 04 Mon: EE48; 2025 Aug 05 Tue: EE48; 2025 Aug 06 Wed: EE48
|  | Cell 3 | 22 Tue: EE49; 23 Wed: EE49; 24 Thu: EE49; 25 Fri: EE49; 26 Sat: EE49; 27 Sun: EE49; 28 Mon: EE49; 2025 Jul 31 Thu: EE50; 2025 Aug 01 Fri: EE50; 2025 Aug 02 Sat: EE50; 2025 Aug 03 Sun: EE50; 2025 Aug 04 Mon: EE50; 2025 Aug 05 Tue: EE50; 2025 Aug 06 Wed: EE50; 2025 Aug 07 Thu: EE48; 2025 Aug 08 Fri: EE48; 2025 Aug 09 Sat: EE48; 2025 Aug 10 Sun: EE48; 2025 Aug 11 Mon: EE48; 2025 Aug 12 Tue: EE48; 2025 Aug 13 Wed: EE48
|  | Cell 4 | 29 Tue: EE49; 30 Wed: EE49; 01 Thu: EE49; 02 Fri: EE49; 03 Sat: EE49; 04 Sun: EE49; 05 Mon: EE49; 2025 Jul 31 Thu: EE50; 2025 Aug 01 Fri: EE50; 2025 Aug 02 Sat: EE50; 2025 Aug 03 Sun: EE50; 2025 Aug 04 Mon: EE50; 2025 Aug 05 Tue: EE50; 2025 Aug 06 Wed: EE50; 2025 Aug 07 Thu: EE48; 2025 Aug 08 Fri: EE48; 2025 Aug 09 Sat: EE48; 2025 Aug 10 Sun: EE48; 2025 Aug 11 Mon: EE48; 2025 Aug 12 Tue: EE48; 2025 Aug 13 Wed: EE48
| Site | Site | 14 Fri: EE47; 15 Sat: EE47; 16 Sun: EE47; 17 Mon: EE47; 18 Tue: EE47; 19 Wed: EE47; 20 Thu: EE47
UPM | COLO 2 | Site | 17 Fri: EE61; 18 Sat: EE61; 19 Sun: EE61; 20 Mon: EE61; 21 Tue: EE62; 22 Wed: EE62; 23 Thu: EE62; 24 Fri: EE62; 25 Sat: EE62; 26 Sun: EE62; 27 Mon: EE62; 28 Tue: EE62; 29 Wed: EE62; 30 Thu: EE62; 31 Fri: EE62; 01 Sat: EE62; 02 Sun: EE62; 03 Mon: EE62; 04 Tue: EE62; 05 Wed: EE62; 06 Thu: EE62; 07 Fri: EE62; 08 Sat: EE62; 09 Sun: EE62; 10 Mon: EE62; 11 Tue: EE63
| COLO 3 | Site | 06 Mon: EE64; 07 Tue: EE64; 08 Wed: EE64; 09 Thu: EE64; 10 Fri: EE64; 11 Sat: EE64; 12 Sun: EE64; 13 Mon: EE64; 14 Tue: EE64; 15 Wed: EE64; 16 Thu: EE64; 17 Fri: EE64; 18 Sat: EE64; 19 Sun: EE64; 20 Mon: EE64; 21 Tue: EE64; 22 Wed: EE64; 23 Thu: EE64; 24 Fri: EE64; 25 Sat: EE64; 26 Sun: EE64; 27 Mon: EE64; 28 Tue: EE64; 29 Wed: EE64; 30 Thu: EE64; 31 Fri: EE64; 01 Sat: EE64; 02 Sun: EE64; 03 Mon: EE64; 04 Tue: EE64; 05 Wed: EE64; 06 Thu: EE64; 07 Fri: EE64; 08 Sat: EE64; 09 Sun: EE64; 10 Mon: EE64; 11 Tue: EE64; 12 Wed: EE64; 13 Thu: EE64; 14 Fri: EE64; 15 Sat: EE64; 16 Sun: EE64; 17 Mon: EE64; 18 Tue: EE64; 19 Wed: EE64; 20 Thu: EE64; 21 Fri: EE64; 22 Sat: EE64; 23 Sun: EE64; 24 Mon: EE64; 25 Tue: EE64; 26 Wed: EE64; 27 Thu: EE64; 28 Fri: EE64; 01 Sat: EE64; 02 Sun: EE64; 03 Mon: EE64; 04 Tue: EE64; 05 Wed: EE64; 06 Thu: EE64; 07 Fri: EE64; 08 Sat: EE64; 09 Sun: EE64; 10 Mon: EE64; 11 Tue: EE64; 12 Wed: EE64; 13 Thu: EE64; 14 Fri: EE64; 15 Sat: EE64; 16 Sun: EE64; 17 Mon: EE64; 18 Tue: EE64; 19 Wed: EE64; 20 Thu: EE64; 21 Fri: EE64; 22 Sat: EE64; 23 Sun: EE64; 24 Mon: EE64; 25 Tue: EE64; 26 Wed: EE64; 27 Thu: EE64; 28 Fri: EE64; 29 Sat: EE64; 30 Sun: EE64; 31 Mon: EE64; 01 Tue: EE64; 02 Wed: EE64; 03 Thu: EE64; 04 Fri: EE64; 05 Sat: EE64; 06 Sun: EE64; 07 Mon: EE64; 08 Tue: EE64; 09 Wed: EE64; 10 Thu: EE64; 11 Fri: EE64; 12 Sat: EE64; 13 Sun: EE64; 14 Mon: EE64; 15 Tue: EE64; 16 Wed: EE64; 17 Thu: EE64; 18 Fri: EE64; 19 Sat: EE64; 20 Sun: EE64; 21 Mon: EE64; 22 Tue: EE64; 23 Wed: EE64; 24 Thu: EE64; 25 Fri: EE64; 26 Sat: EE64; 27 Sun: EE64; 28 Mon: EE64; 29 Tue: EE64; 30 Wed: EE64; 01 Thu: EE64; 02 Fri: EE64; 03 Sat: EE64; 04 Sun: EE64; 05 Mon: EE64; 06 Tue: EE64; 07 Wed: EE64; 08 Thu: EE64; 09 Fri: EE64; 10 Sat: EE64; 11 Sun: EE64; 12 Mon: EE64; 13 Tue: EE64; 14 Wed: EE64; 15 Thu: EE64; 16 Fri: EE64; 17 Sat: EE64; 18 Sun: EE64; 19 Mon: EE64; 20 Tue: EE64; 21 Wed: EE64; 22 Thu: EE64; 23 Fri: EE64; 24 Sat: EE64; 25 Sun: EE64; 26 Mon: EE64; 27 Tue: EE64; 28 Wed: EE64; 29 Thu: EE64; 30 Fri: EE64; 02 Mon: EE65; 03 Tue: EE65; 04 Wed: EE65; 05 Thu: EE65; 06 Fri: EE65; 07 Sat: EE65; 08 Sun: EE65; 09 Mon: EE65; 10 Tue: EE65; 11 Wed: EE65; 13 Fri: EE66; 16 Mon: EE67; 17 Tue: EE67; 18 Wed: EE67; 19 Thu: EE67; 20 Fri: EE67; 21 Sat: EE67; 22 Sun: EE67; 23 Mon: EE67; 24 Tue: EE67; 25 Wed: EE67; 26 Thu: EE67; 27 Fri: EE67; 28 Sat: EE67; 29 Sun: EE67; 30 Mon: EE67; 01 Tue: EE67; 02 Wed: EE67; 03 Thu: EE67; 04 Fri: EE67
| COLO 4 | Site | 06 Mon: EE64; 07 Tue: EE64; 08 Wed: EE64; 09 Thu: EE64; 10 Fri: EE64; 11 Sat: EE64; 12 Sun: EE64; 13 Mon: EE64; 14 Tue: EE64; 15 Wed: EE64; 16 Thu: EE64; 17 Fri: EE64; 18 Sat: EE64; 19 Sun: EE64; 20 Mon: EE64; 21 Tue: EE64; 22 Wed: EE64; 23 Thu: EE64; 24 Fri: EE64; 25 Sat: EE64; 26 Sun: EE64; 27 Mon: EE64; 28 Tue: EE64; 29 Wed: EE64; 30 Thu: EE64; 31 Fri: EE64; 01 Sat: EE64; 02 Sun: EE64; 03 Mon: EE64; 04 Tue: EE64; 05 Wed: EE64; 06 Thu: EE64; 07 Fri: EE64; 08 Sat: EE64; 09 Sun: EE64; 10 Mon: EE64; 11 Tue: EE64; 12 Wed: EE64; 13 Thu: EE64; 14 Fri: EE64; 15 Sat: EE64; 16 Sun: EE64; 17 Mon: EE64; 18 Tue: EE64; 19 Wed: EE64; 20 Thu: EE64; 21 Fri: EE64; 22 Sat: EE64; 23 Sun: EE64; 24 Mon: EE64; 25 Tue: EE64; 26 Wed: EE64; 27 Thu: EE64; 28 Fri: EE64; 01 Sat: EE64; 02 Sun: EE64; 03 Mon: EE64; 04 Tue: EE64; 05 Wed: EE64; 06 Thu: EE64; 07 Fri: EE64; 08 Sat: EE64; 09 Sun: EE64; 10 Mon: EE64; 11 Tue: EE64; 12 Wed: EE64; 13 Thu: EE64; 14 Fri: EE64; 15 Sat: EE64; 16 Sun: EE64; 17 Mon: EE64; 18 Tue: EE64; 19 Wed: EE64; 20 Thu: EE64; 21 Fri: EE64; 22 Sat: EE64; 23 Sun: EE64; 24 Mon: EE64; 25 Tue: EE64; 26 Wed: EE64; 27 Thu: EE64; 28 Fri: EE64; 29 Sat: EE64; 30 Sun: EE64; 31 Mon: EE64; 01 Tue: EE64; 02 Wed: EE64; 03 Thu: EE64; 04 Fri: EE64; 05 Sat: EE64; 06 Sun: EE64; 07 Mon: EE64; 08 Tue: EE64; 09 Wed: EE64; 10 Thu: EE64; 11 Fri: EE64; 12 Sat: EE64; 13 Sun: EE64; 14 Mon: EE64; 15 Tue: EE64; 16 Wed: EE64; 17 Thu: EE64; 18 Fri: EE64; 19 Sat: EE64; 20 Sun: EE64; 21 Mon: EE64; 22 Tue: EE64; 23 Wed: EE64; 24 Thu: EE64; 25 Fri: EE64; 26 Sat: EE64; 27 Sun: EE64; 28 Mon: EE64; 29 Tue: EE64; 30 Wed: EE64; 01 Thu: EE64; 02 Fri: EE64; 03 Sat: EE64; 04 Sun: EE64; 05 Mon: EE64; 06 Tue: EE64; 07 Wed: EE64; 08 Thu: EE64; 09 Fri: EE64; 10 Sat: EE64; 11 Sun: EE64; 12 Mon: EE64; 13 Tue: EE64; 14 Wed: EE64; 15 Thu: EE64; 16 Fri: EE64; 17 Sat: EE64; 18 Sun: EE64; 19 Mon: EE64; 20 Tue: EE64; 21 Wed: EE64; 22 Thu: EE64; 23 Fri: EE64; 24 Sat: EE64; 25 Sun: EE64; 26 Mon: EE64; 27 Tue: EE64; 28 Wed: EE64; 29 Thu: EE64; 30 Fri: EE64; 12 Thu: EE65; 13 Fri: EE65; 14 Sat: EE65; 15 Sun: EE65; 16 Mon: EE65; 17 Tue: EE65; 18 Wed: EE65; 19 Thu: EE65; 20 Fri: EE65; 21 Sat: EE65; 22 Sun: EE65; 23 Mon: EE65; 24 Tue: EE66; 25 Wed: EE67; 26 Thu: EE67; 27 Fri: EE67; 28 Sat: EE67; 29 Sun: EE67; 30 Mon: EE67; 01 Tue: EE67; 02 Wed: EE67; 03 Thu: EE67; 04 Fri: EE67; 05 Sat: EE67; 06 Sun: EE67; 07 Mon: EE67; 08 Tue: EE67; 09 Wed: EE67; 10 Thu: EE67; 11 Fri: EE67; 12 Sat: EE67; 13 Sun: EE67; 14 Mon: EE67; 15 Tue: EE67
| COLO 5 | Site | 06 Mon: EE64; 07 Tue: EE64; 08 Wed: EE64; 09 Thu: EE64; 10 Fri: EE64; 11 Sat: EE64; 12 Sun: EE64; 13 Mon: EE64; 14 Tue: EE64; 15 Wed: EE64; 16 Thu: EE64; 17 Fri: EE64; 18 Sat: EE64; 19 Sun: EE64; 20 Mon: EE64; 21 Tue: EE64; 22 Wed: EE64; 23 Thu: EE64; 24 Fri: EE64; 25 Sat: EE64; 26 Sun: EE64; 27 Mon: EE64; 28 Tue: EE64; 29 Wed: EE64; 30 Thu: EE64; 31 Fri: EE64; 01 Sat: EE64; 02 Sun: EE64; 03 Mon: EE64; 04 Tue: EE64; 05 Wed: EE64; 06 Thu: EE64; 07 Fri: EE64; 08 Sat: EE64; 09 Sun: EE64; 10 Mon: EE64; 11 Tue: EE64; 12 Wed: EE64; 13 Thu: EE64; 14 Fri: EE64; 15 Sat: EE64; 16 Sun: EE64; 17 Mon: EE64; 18 Tue: EE64; 19 Wed: EE64; 20 Thu: EE64; 21 Fri: EE64; 22 Sat: EE64; 23 Sun: EE64; 24 Mon: EE64; 25 Tue: EE64; 26 Wed: EE64; 27 Thu: EE64; 28 Fri: EE64; 01 Sat: EE64; 02 Sun: EE64; 03 Mon: EE64; 04 Tue: EE64; 05 Wed: EE64; 06 Thu: EE64; 07 Fri: EE64; 08 Sat: EE64; 09 Sun: EE64; 10 Mon: EE64; 11 Tue: EE64; 12 Wed: EE64; 13 Thu: EE64; 14 Fri: EE64; 15 Sat: EE64; 16 Sun: EE64; 17 Mon: EE64; 18 Tue: EE64; 19 Wed: EE64; 20 Thu: EE64; 21 Fri: EE64; 22 Sat: EE64; 23 Sun: EE64; 24 Mon: EE64; 25 Tue: EE64; 26 Wed: EE64; 27 Thu: EE64; 28 Fri: EE64; 29 Sat: EE64; 30 Sun: EE64; 31 Mon: EE64; 01 Tue: EE64; 02 Wed: EE64; 03 Thu: EE64; 04 Fri: EE64; 05 Sat: EE64; 06 Sun: EE64; 07 Mon: EE64; 08 Tue: EE64; 09 Wed: EE64; 10 Thu: EE64; 11 Fri: EE64; 12 Sat: EE64; 13 Sun: EE64; 14 Mon: EE64; 15 Tue: EE64; 16 Wed: EE64; 17 Thu: EE64; 18 Fri: EE64; 19 Sat: EE64; 20 Sun: EE64; 21 Mon: EE64; 22 Tue: EE64; 23 Wed: EE64; 24 Thu: EE64; 25 Fri: EE64; 26 Sat: EE64; 27 Sun: EE64; 28 Mon: EE64; 29 Tue: EE64; 30 Wed: EE64; 01 Thu: EE64; 02 Fri: EE64; 03 Sat: EE64; 04 Sun: EE64; 05 Mon: EE64; 06 Tue: EE64; 07 Wed: EE64; 08 Thu: EE64; 09 Fri: EE64; 10 Sat: EE64; 11 Sun: EE64; 12 Mon: EE64; 13 Tue: EE64; 14 Wed: EE64; 15 Thu: EE64; 16 Fri: EE64; 17 Sat: EE64; 18 Sun: EE64; 19 Mon: EE64; 20 Tue: EE64; 21 Wed: EE64; 22 Thu: EE64; 23 Fri: EE64; 24 Sat: EE64; 25 Sun: EE64; 26 Mon: EE64; 27 Tue: EE64; 28 Wed: EE64; 29 Thu: EE64; 30 Fri: EE64; 02 Mon: EE65; 03 Tue: EE65; 04 Wed: EE65; 05 Thu: EE65; 06 Fri: EE65; 07 Sat: EE65; 08 Sun: EE65; 09 Mon: EE65; 10 Tue: EE66; 11 Wed: EE67; 12 Thu: EE67; 13 Fri: EE67; 14 Sat: EE67; 15 Sun: EE67; 16 Mon: EE67; 17 Tue: EE67; 18 Wed: EE67; 19 Thu: EE67; 20 Fri: EE67; 21 Sat: EE67; 22 Sun: EE67; 23 Mon: EE67; 24 Tue: EE67
Note on AF5: Activity Name: MVS Fiber Procurement Phase: Fiber Location: All Trade: WALSH Start Date: 09-Dec-2024 End Date: 31-Jan-2025
Note on CJ5: Activity Name: MVS Fiber Shipping Phase: Fiber Location: All Trade: WALSH Start Date: 03-Feb-2025 End Date: 14-Feb-2025
Note on CX5: Activity Name: Pull, Splice, & Test (3) UTS Fiber Phase: Fiber Location: All Trade: Gurtz Electric Telecom Start Date: 17-Feb-2025 End Date: 13-Mar-2025
Note on CX6: Activity Name: Pull, Splice, & Test (5) UMS/URS Fiber Phase: Fiber Location: All Trade: Gurtz Electric Telecom Start Date: 17-Feb-2025 End Date: 13-Mar-2025
Note on Y9: Activity Name: 3456 Fiber Procurement Colo 2 Phase: Fiber Location: COLO 2 Trade: WALSH Start Date: 02-Dec-2024 End Date: 05-Mar-2025
Note on DO9: Activity Name: 3456 Fiber Shipping Colo 2 Phase: Fiber Location: COLO 2 Trade: WALSH Start Date: 06-Mar-2025 End Date: 19-Mar-2025
Note on EC9: Activity Name: 3456 Fiber Install, Populate, & Test Colo 2 Phase: Fiber Location: COLO 2 Trade: Gurtz Electric Telecom Start Date: 20-Mar-2025 End Date: 23-Apr-2025
Note on GL9: Activity Name: RNI Colo 2 Phase: Fiber Location: COLO 2 Trade: Gurtz Electric Telecom Start Date: 20-May-2025 End Date: 20-May-2025
Note on Y10: Activity Name: 288 Fiber Procurement Colo 2 Phase: Fiber Location: COLO 2 Trade: WALSH Start Date: 02-Dec-2024 End Date: 10-Mar-2025
Note on DT10: Activity Name: 288 Fiber Shipping Colo 2 Phase: Fiber Location: COLO 2 Trade: WALSH Start Date: 11-Mar-2025 End Date: 24-Mar-2025
Note on EH10: Activity Name: 288 Fiber Install, Populate, & Test Colo 2 Phase: Fiber Location: COLO 2 Trade: Gurtz Electric Telecom Start Date: 25-Mar-2025 End Date: 19-May-2025
Note on AF11: Activity Name: Interior CEI CAT6 Procurement Colo 2 Phase: Fiber Location: COLO 2 Trade: WALSH Start Date: 09-Dec-2024 End Date: 28-Jan-2025
Note on CE11: Activity Name: Interior CEI CAT6 Shipping Colo 2 Phase: Fiber Location: COLO 2 Trade: WALSH Start Date: 29-Jan-2025 End Date: 11-Feb-2025
Note on CS11: Activity Name: Pull Interior CEI CAT6 Colo 2 Phase: Fiber Location: COLO 2 Trade: Gurtz Electric Telecom Start Date: 12-Feb-2025 End Date: 11-Mar-2025
Note on DW11: Activity Name: Pull, Splice, & Test UPM Fiber Colo 2 Phase: Fiber Location: COLO 2 Trade: Gurtz Electric Telecom Start Date: 14-Mar-2025 End Date: 27-Mar-2025
Note on AT12: Activity Name: Generator CEI Fiber Shipping Colo 2 Phase: Fiber Location: COLO 2 Trade: WALSH Start Date: 23-Dec-2024 End Date: 22-Jan-2025
Note on BY12: Activity Name: Pull Generator Fiber Colo 2 Phase: Fiber Location: COLO 2 Trade: Gurtz Electric Start Date: 23-Jan-2025 End Date: 29-Jan-2025
Note on BL13: Activity Name: Backbone CEI Fiber Shipping Colo 2 Phase: Fiber Location: COLO 2 Trade: WALSH Start Date: 10-Jan-2025 End Date: 23-Jan-2025
Note on BZ13: Activity Name: Pull Backbone Fiber Colo 2 (CEI to FCR) Phase: Fiber Location: COLO 2 Trade: Gurtz Electric Telecom Start Date: 24-Jan-2025 End Date: 06-Feb-2025
Note on Y17: Activity Name: 3456 Fiber Procurement Colo 3 Phase: Fiber Location: COLO 3 Trade: WALSH Start Date: 02-Dec-2024 End Date: 05-Mar-2025
Note on DO17: Activity Name: 3456 Fiber Shipping Colo 3 Phase: Fiber Location: COLO 3 Trade: WALSH Start Date: 06-Mar-2025 End Date: 19-Mar-2025
Note on EI17: Activity Name: 288 Fiber Shipping Colo 3 Phase: Fiber Location: COLO 3 Trade: WALSH Start Date: 26-Mar-2025 End Date: 08-Apr-2025
Note on EW17: Activity Name: Pull Interior CEI CAT 6 Colo 3 Phase: Fiber Location: COLO 3 Trade: Gurtz Electric Telecom Start Date: 09-Apr-2025 End Date: 06-May-2025
Note on GV17: Activity Name: Colo 3 UPM Ready for Fiber (L1 Complete Per Option 2) Phase: Fiber Location: COLO 3 Trade: Gurtz Electric Telecom Start Date: 30-May-2025 End Date: 30-May-2025
Note on HB17: Activity Name: 3456 Fiber Install, Populate, & Test Colo 3 Phase: Fiber Location: COLO 3 Trade: Gurtz Electric Telecom Start Date: 05-Jun-2025 End Date: 09-Jul-2025
Note on IP17: Activity Name: 288 Fiber Install, Populate, & Test Colo 3 Phase: Fiber Location: COLO 3 Trade: Gurtz Electric Telecom Start Date: 15-Jul-2025 End Date: 08-Sep-2025
Note on KT17: Activity Name: RNI Colo 3 Phase: Fiber Location: COLO 3 Trade: Gurtz Electric Telecom Start Date: 09-Sep-2025 End Date: 09-Sep-2025
Note on Y18: Activity Name: 288 Fiber Procurement Colo 3 Phase: Fiber Location: COLO 3 Trade: WALSH Start Date: 02-Dec-2024 End Date: 25-Mar-2025
Note on EK18: Activity Name: Pull, Splice, & Test UPM Fiber Colo 3 Phase: Fiber Location: COLO 3 Trade: Gurtz Electric Telecom Start Date: 28-Mar-2025 End Date: 10-Apr-2025
Note on AF19: Activity Name: Backbone CEI Fiber Procurement Colo 3 Phase: Fiber Location: COLO 3 Trade: WALSH Start Date: 09-Dec-2024 End Date: 23-Jan-2025
Note on CM19: Activity Name: Pull Generator Fiber Colo 3 Phase: Fiber Location: COLO 3 Trade: Gurtz Electric Start Date: 06-Feb-2025 End Date: 12-Feb-2025
Note on DB19: Activity Name: Pull Backbone Fiber Colo 3 (CEI to FCR) Phase: Fiber Location: COLO 3 Trade: Gurtz Electric Telecom Start Date: 21-Feb-2025 End Date: 06-Mar-2025
Note on EU19: Activity Name: Colo 3 UPM Ready for Fiber (L1 Complete Per Option 1) Phase: Fiber Location: COLO 3 Trade: Gurtz Electric Telecom Start Date: 07-Apr-2025 End Date: 07-Apr-2025
Note on AF20: Activity Name: Interior CEI CAT6 Procurement Colo 3 Phase: Fiber Location: COLO 3 Trade: WALSH Start Date: 09-Dec-2024 End Date: 11-Feb-2025
Note on CS20: Activity Name: Interior CEI CAT6 Shipping Colo 3 Phase: Fiber Location: COLO 3 Trade: WALSH Start Date: 12-Feb-2025 End Date: 25-Feb-2025
Note on BL21: Activity Name: Generator CEI Fiber Shipping Colo 3 Phase: Fiber Location: COLO 3 Trade: WALSH Start Date: 10-Jan-2025 End Date: 24-Jan-2025
Note on BR22: Activity Name: Backbone CEI Fiber Shipping Colo 3 Phase: Fiber Location: COLO 3 Trade: WALSH Start Date: 16-Jan-2025 End Date: 29-Jan-2025
Note on Y26: Activity Name: 288 Fiber Procurement Colo 4 Phase: Fiber Location: COLO 4 Trade: WALSH Start Date: 02-Dec-2024 End Date: 24-Mar-2025
Note on EH26: Activity Name: 288 Fiber Shipping Colo 4 Phase: Fiber Location: COLO 4 Trade: WALSH Start Date: 25-Mar-2025 End Date: 07-Apr-2025
Note on EY26: Activity Name: Pull, Splice, & Test UPM Fiber Colo 4 Phase: Fiber Location: COLO 4 Trade: Gurtz Electric Telecom Start Date: 11-Apr-2025 End Date: 24-Apr-2025
Note on FY26: Activity Name: Pull Interior Fiber Colo 4 Phase: Fiber Location: COLO 4 Trade: Gurtz Electric Telecom Start Date: 07-May-2025 End Date: 03-Jun-2025
Note on IK26: Activity Name: 3456 Fiber Install, Populate, & Test Colo 4 Phase: Fiber Location: COLO 4 Trade: Gurtz Electric Telecom Start Date: 10-Jul-2025 End Date: 13-Aug-2025
Note on KT26: Activity Name: 288 Fiber Install, Populate, & Test Colo 4 Phase: Fiber Location: COLO 4 Trade: Gurtz Electric Telecom Start Date: 09-Sep-2025 End Date: 03-Nov-2025
Note on MX26: Activity Name: RNI Colo 4 Phase: Fiber Location: COLO 4 Trade: Gurtz Electric Telecom Start Date: 04-Nov-2025 End Date: 04-Nov-2025
Note on Y27: Activity Name: 3456 Fiber Procurement Colo 4 Phase: Fiber Location: COLO 4 Trade: WALSH Start Date: 02-Dec-2024 End Date: 31-Mar-2025
Note on EO27: Activity Name: 3456 Fiber Shipping Colo 4 Phase: Fiber Location: COLO 4 Trade: WALSH Start Date: 01-Apr-2025 End Date: 14-Apr-2025
Note on FZ27: Activity Name: Colo 4 UPM Ready for Fiber (L1 Complete Option 1) Phase: Fiber Location: COLO 4 Trade: Gurtz Electric Telecom Start Date: 08-May-2025 End Date: 08-May-2025
Note on GV27: Activity Name: Colo 4 UPM Ready for Fiber (L1 Complete Option 2) Phase: Fiber Location: COLO 4 Trade: Gurtz Electric Telecom Start Date: 30-May-2025 End Date: 30-May-2025
Note on AF28: Activity Name: Backbone CEI Fiber Procurement Colo 4 Phase: Fiber Location: COLO 4 Trade: WALSH Start Date: 09-Dec-2024 End Date: 27-Jan-2025
Note on CD28: Activity Name: Backbone CEI Fiber Shipping Colo 4 Phase: Fiber Location: COLO 4 Trade: WALSH Start Date: 28-Jan-2025 End Date: 10-Feb-2025
Note on DE28: Activity Name: Pull Generator CAT6 Colo 4 Phase: Fiber Location: COLO 4 Trade: Gurtz Electric Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on DP28: Activity Name: Pull Backbone Fiber Colo 4 (CEI to FCR) Phase: Fiber Location: COLO 4 Trade: Gurtz Electric Telecom Start Date: 07-Mar-2025 End Date: 20-Mar-2025
Note on AF29: Activity Name: Generator CEI Fiber Procurement Colo 4 Phase: Fiber Location: COLO 4 Trade: WALSH Start Date: 09-Dec-2024 End Date: 07-Feb-2025
Note on CQ29: Activity Name: Generator CEI Fiber Shipping Colo 4 Phase: Fiber Location: COLO 4 Trade: WALSH Start Date: 10-Feb-2025 End Date: 21-Feb-2025
Note on DG29: Activity Name: Interior CEI Fiber Shipping Colo 4 Phase: Fiber Location: COLO 4 Trade: WALSH Start Date: 26-Feb-2025 End Date: 11-Mar-2025
Note on AF30: Activity Name: Interior CEI CAT6 Procurement Colo 4 Phase: Fiber Location: COLO 4 Trade: WALSH Start Date: 09-Dec-2024 End Date: 25-Feb-2025
Note on Y34: Activity Name: 288 Fiber Procurement Colo 5 Phase: Fiber Location: COLO 5 Trade: WALSH Start Date: 02-Dec-2024 End Date: 12-Feb-2025
Note on CT34: Activity Name: 288 Fiber Shipping Colo 5 Phase: Fiber Location: COLO 5 Trade: WALSH Start Date: 13-Feb-2025 End Date: 26-Feb-2025
Note on DO34: Activity Name: 3456 Fiber Shipping Colo 5 Phase: Fiber Location: COLO 5 Trade: WALSH Start Date: 06-Mar-2025 End Date: 19-Mar-2025
Note on EK34: Activity Name: Pull, Splice, & Test UPM Fiber Colo 5 Phase: Fiber Location: COLO 5 Trade: Gurtz Electric Telecom Start Date: 28-Mar-2025 End Date: 10-Apr-2025
Note on FL34: Activity Name: 3456 Fiber Install, Populate, & Test Colo 5 Phase: Fiber Location: COLO 5 Trade: Gurtz Electric Telecom Start Date: 24-Apr-2025 End Date: 04-Jun-2025
Note on HN34: Activity Name: Colo 5 UPM Ready for Fiber (L1 Complete Per Option 2) Phase: Fiber Location: COLO 5 Trade: Gurtz Electric Telecom Start Date: 17-Jun-2025 End Date: 17-Jun-2025
Note on IP34: Activity Name: RNI Colo 5 Phase: Fiber Location: COLO 5 Trade: Gurtz Electric Telecom Start Date: 15-Jul-2025 End Date: 15-Jul-2025
Note on Y35: Activity Name: 3456 Fiber Procurement Colo 5 Phase: Fiber Location: COLO 5 Trade: WALSH Start Date: 02-Dec-2024 End Date: 05-Mar-2025
Note on DU35: Activity Name: Pull Interior CAT6 Colo 5 Phase: Fiber Location: COLO 5 Trade: Gurtz Electric Telecom Start Date: 12-Mar-2025 End Date: 08-Apr-2025
Note on GL35: Activity Name: 288 Fiber Install, Populate, & Test Colo 5 Phase: Fiber Location: COLO 5 Trade: Gurtz Electric Telecom Start Date: 20-May-2025 End Date: 14-Jul-2025
Note on AF36: Activity Name: Interior CEI Fiber Procurement Colo 5 Phase: Fiber Location: COLO 5 Trade: WALSH Start Date: 09-Dec-2024 End Date: 11-Feb-2025
Note on CS36: Activity Name: Interior CEI CAT6 Shipping Colo 5 Phase: Fiber Location: COLO 5 Trade: WALSH Start Date: 12-Feb-2025 End Date: 25-Feb-2025
Note on GU36: Activity Name: Colo 5 UPM Ready for Fiber (L1 Complete Per Option 1) Phase: Fiber Location: COLO 5 Trade: Gurtz Electric Telecom Start Date: 29-May-2025 End Date: 29-May-2025
Note on AT37: Activity Name: Generator CEI Fiber Shipping Colo 5 Phase: Fiber Location: COLO 5 Trade: WALSH Start Date: 23-Dec-2024 End Date: 22-Jan-2025
Note on CF37: Activity Name: Pull Generator Fiber Colo 5 Phase: Fiber Location: COLO 5 Trade: Gurtz Electric Start Date: 30-Jan-2025 End Date: 05-Feb-2025
Note on CN37: Activity Name: Pull Backbone Fiber Colo 5 (CEI to FCR) Phase: Fiber Location: COLO 5 Trade: Gurtz Electric Telecom Start Date: 07-Feb-2025 End Date: 20-Feb-2025
Note on BL38: Activity Name: Backbone CEI Fiber Shipping Colo 5 Phase: Fiber Location: COLO 5 Trade: WALSH Start Date: 10-Jan-2025 End Date: 23-Jan-2025
Note on LN42: Activity Name: Level 4 Cx - Colo 5 Phase: COLO 5 Location: All Trade: Microsoft Start Date: 29-Sep-2025 End Date: 24-Oct-2025
Note on MP42: Activity Name: Level 5 Cx / IST - Colo 5 Phase: COLO 5 Location: All Trade: Microsoft Start Date: 27-Oct-2025 End Date: 28-Oct-2025
Note on DZ44: Activity Name: Interior - L2 TCP/MSB - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on EG44: Activity Name: Interior - L2 UPS - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EN44: Activity Name: Interior - L2 PDUs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on EG45: Activity Name: Interior - L2 ADP - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EN45: Activity Name: Interior - L2 AHUs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on EN46: Activity Name: Interior - L2 ATSs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on EN47: Activity Name: Interior - L2 Busway - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on JJ51: Activity Name: Interior - L3 TCP/MSB - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 04-Aug-2025 End Date: 08-Aug-2025
Note on JQ51: Activity Name: Interior - L3 UPS - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 11-Aug-2025 End Date: 15-Aug-2025
Note on JX51: Activity Name: Interior - L3 ATSs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 18-Aug-2025 End Date: 22-Aug-2025
Note on KE51: Activity Name: Interior - L3 Busway - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 25-Aug-2025 End Date: 29-Aug-2025
Note on JJ52: Activity Name: Interior - L3 PDUs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 04-Aug-2025 End Date: 08-Aug-2025
Note on JQ52: Activity Name: Interior - L3 ADP - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 11-Aug-2025 End Date: 15-Aug-2025
Note on JS53: Activity Name: Interior - L3 AHUs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 13-Aug-2025 End Date: 26-Aug-2025
Note on BS57: Activity Name: Termination at PDU & Busway- COLO5 Cell 1 - DH Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 06-Feb-2025
Note on CN57: Activity Name: Finishes and Signage - COLO5 Cell 1 - DH Phase: COLO 5 Location: Cell 1 Trade: All Trades Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on BB59: Activity Name: Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 31-Dec-2024 End Date: 31-Jan-2025
Note on CE60: Activity Name: Finishes and Signage - COLO5 Cell 1 - ER Phase: COLO 5 Location: Cell 1 Trade: All Trades Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on BS61: Activity Name: Trim out MEP - COLO5 Cell 1 - MG Phase: COLO 5 Location: Cell 1 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 23-Jan-2025
Note on EG62: Activity Name: Interior - L2 TCP/MSB - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EN62: Activity Name: Interior - L2 UPS - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on EU62: Activity Name: Interior - L2 AHUs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on EN63: Activity Name: Interior - L2 PDUs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on EU63: Activity Name: Interior - L2 ATSs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on EN64: Activity Name: Interior - L2 ADP - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on EU64: Activity Name: Interior - L2 Busway - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on JM68: Activity Name: Interior - L3 TCP/MSB - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 07-Aug-2025 End Date: 13-Aug-2025
Note on JT68: Activity Name: Interior - L3 UPS - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 14-Aug-2025 End Date: 20-Aug-2025
Note on KA68: Activity Name: Interior - L3 AHUs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 21-Aug-2025 End Date: 04-Sep-2025
Note on JM69: Activity Name: Interior - L3 PDUs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 07-Aug-2025 End Date: 13-Aug-2025
Note on JT69: Activity Name: Interior - L3 ATSs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 14-Aug-2025 End Date: 20-Aug-2025
Note on KN69: Activity Name: Interior - L3 Busway - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 03-Sep-2025 End Date: 09-Sep-2025
Note on JM70: Activity Name: Interior - L3 ADP - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 07-Aug-2025 End Date: 13-Aug-2025
Note on BS74: Activity Name: Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 30-Jan-2025
Note on CG74: Activity Name: Termination at PDU & Busway- COLO5 Cell 2 - DH Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 31-Jan-2025 End Date: 20-Feb-2025
Note on DB74: Activity Name: Finishes and Signage - COLO5 Cell 2 - DH Phase: COLO 5 Location: Cell 2 Trade: All Trades Start Date: 21-Feb-2025 End Date: 27-Feb-2025
Note on BS75: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Telecom Start Date: 17-Jan-2025 End Date: 30-Jan-2025
Note on BW78: Activity Name: Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 21-Jan-2025 End Date: 03-Feb-2025
Note on CU78: Activity Name: Finishes and Signage - COLO5 Cell 2 - ER Phase: COLO 5 Location: Cell 2 Trade: All Trades Start Date: 14-Feb-2025 End Date: 20-Feb-2025
Note on BL80: Activity Name: Install ceiling and Light Fittings - COLO5 Cell 2 - MG Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 10-Jan-2025 End Date: 21-Jan-2025
Note on BZ80: Activity Name: Trim out MEP - COLO5 Cell 2 - MG Phase: COLO 5 Location: Cell 2 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 30-Jan-2025
Note on EN82: Activity Name: Interior - L2 TCP/MSB - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on EU82: Activity Name: Interior - L2 UPS - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on FB82: Activity Name: Interior - L2 AHUs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on EU83: Activity Name: Interior - L2 PDUs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on FB83: Activity Name: Interior - L2 ATSs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on EU84: Activity Name: Interior - L2 ADP - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on FB84: Activity Name: Interior - L2 Busway - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on JT88: Activity Name: Interior - L3 TCP/MSB - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 14-Aug-2025 End Date: 20-Aug-2025
Note on KA88: Activity Name: Interior - L3 UPS - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 21-Aug-2025 End Date: 27-Aug-2025
Note on KN88: Activity Name: Interior - L3 Busway - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 03-Sep-2025 End Date: 09-Sep-2025
Note on JT89: Activity Name: Interior - L3 PDUs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 14-Aug-2025 End Date: 20-Aug-2025
Note on KA89: Activity Name: Interior - L3 ATSs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 21-Aug-2025 End Date: 27-Aug-2025
Note on JT90: Activity Name: Interior - L3 ADP - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 14-Aug-2025 End Date: 20-Aug-2025
Note on KA90: Activity Name: Interior - L3 AHUs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 21-Aug-2025 End Date: 04-Sep-2025
Note on BL94: Activity Name: Cable Pulling at PDU & Busway- COLO5 Cell 3 - DH Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 10-Jan-2025 End Date: 23-Jan-2025
Note on CG94: Activity Name: Termination at PDU & Busway - COLO5 Cell 3 - DH Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 31-Jan-2025 End Date: 20-Feb-2025
Note on DP94: Activity Name: Finishes and Signage - COLO5 Cell 3 - DH Phase: COLO 5 Location: Cell 3 Trade: All Trades Start Date: 07-Mar-2025 End Date: 13-Mar-2025
Note on BP97: Activity Name: Connect to Cable tray and conduit equipment - COLO5 Cell 3 - ER Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 14-Jan-2025 End Date: 20-Jan-2025
Note on BW97: Activity Name: Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 21-Jan-2025 End Date: 03-Feb-2025
Note on DI97: Activity Name: Finishes and Signage - COLO5 Cell 3 - ER Phase: COLO 5 Location: Cell 3 Trade: All Trades Start Date: 28-Feb-2025 End Date: 06-Mar-2025
Note on BS100: Activity Name: Pipe Testing - COLO5 Cell 3 - MG Phase: COLO 5 Location: Cell 3 Trade: Inspections Start Date: 17-Jan-2025 End Date: 20-Jan-2025
Note on BX100: Activity Name: Install ceiling and Light Fittings - COLO5 Cell 3 - MG Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 22-Jan-2025 End Date: 31-Jan-2025
Note on CJ100: Activity Name: Trim out MEP - COLO5 Cell 3 - MG Phase: COLO 5 Location: Cell 3 Trade: Gurtz Electric Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on BZ103: Activity Name: Interior - L1 PDUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 24-Jan-2025
Note on BZ104: Activity Name: Interior - L1 ATSs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 24-Jan-2025
Note on BZ105: Activity Name: Interior - L1 Busway - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 24-Jan-2025
Note on BZ106: Activity Name: Interior - L1 ADP - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 24-Jan-2025
Note on EU107: Activity Name: Interior - L2 TCP/MSB - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on FB107: Activity Name: Interior - L2 UPS - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on FI107: Activity Name: Interior - L2 AHUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on FB108: Activity Name: Interior - L2 PDUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on FI108: Activity Name: Interior - L2 ATSs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on FB109: Activity Name: Interior - L2 ADP - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on FI109: Activity Name: Interior - L2 Busway - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on KA113: Activity Name: Interior - L3 TCP/MSB - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 21-Aug-2025 End Date: 27-Aug-2025
Note on KH113: Activity Name: Interior - L3 ADP - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 28-Aug-2025 End Date: 04-Sep-2025
Note on KP113: Activity Name: Interior - L3 ATSs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 05-Sep-2025 End Date: 11-Sep-2025
Note on LG113: Activity Name: Interior - L3 Busway - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 22-Sep-2025 End Date: 26-Sep-2025
Note on KA114: Activity Name: Interior - L3 PDUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 21-Aug-2025 End Date: 27-Aug-2025
Note on KU114: Activity Name: Interior - L3 UPS - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 10-Sep-2025 End Date: 16-Sep-2025
Note on KU115: Activity Name: Interior - L3 AHUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 10-Sep-2025 End Date: 23-Sep-2025
Note on BE119: Activity Name: Closing Construction Access Door - COLO5 Cell 4 - DH Phase: COLO 5 Location: Cell 4 Trade: WALSH Start Date: 03-Jan-2025 End Date: 23-Jan-2025
Note on CG119: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Telecom Start Date: 31-Jan-2025 End Date: 13-Feb-2025
Note on DB119: Activity Name: Termination at PDU & Busway - COLO5 Cell 4 - DH Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 21-Feb-2025 End Date: 13-Mar-2025
Note on ED119: Activity Name: Finishes and Signage - COLO5 Cell 4 - DH Phase: COLO 5 Location: Cell 4 Trade: All Trades Start Date: 21-Mar-2025 End Date: 27-Mar-2025
Note on BS123: Activity Name: Installation of ADP & ATS - COLO5 Cell 4 - ER Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 23-Jan-2025
Note on CD123: Activity Name: Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 28-Jan-2025 End Date: 10-Feb-2025
Note on DW123: Activity Name: Finishes and Signage - COLO5 Cell 4 - ER Phase: COLO 5 Location: Cell 4 Trade: All Trades Start Date: 14-Mar-2025 End Date: 20-Mar-2025
Note on BW124: Activity Name: Connect to Cable tray and conduit equipment - COLO5 Cell 4 - ER Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 21-Jan-2025 End Date: 27-Jan-2025
Note on BS127: Activity Name: Piping and Electrical Termination to AHUs - COLO5 Cell 4 - MG Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Telecom Start Date: 17-Jan-2025 End Date: 30-Jan-2025
Note on CG127: Activity Name: Pipe Testing - COLO5 Cell 4 - MG Phase: COLO 5 Location: Cell 4 Trade: Inspections Start Date: 31-Jan-2025 End Date: 03-Feb-2025
Note on CK127: Activity Name: Install ceiling and Light Fittings - COLO5 Cell 4 - MG Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 04-Feb-2025 End Date: 13-Feb-2025
Note on CU127: Activity Name: Trim out MEP - COLO5 Cell 4 - MG Phase: COLO 5 Location: Cell 4 Trade: Gurtz Electric Start Date: 14-Feb-2025 End Date: 20-Feb-2025
Note on HA131: Activity Name: Level 4 Cx - Colo 2 Phase: COLO 2 Location: All Trade: Microsoft Start Date: 04-Jun-2025 End Date: 01-Jul-2025
Note on IC131: Activity Name: Level 5 Cx / IST - Colo 2 Phase: COLO 2 Location: All Trade: Microsoft Start Date: 02-Jul-2025 End Date: 03-Jul-2025
Note on CJ133: Activity Name: Interior - L2 TCP/MSB - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on CQ133: Activity Name: Interior - L2 ADP - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on CX133: Activity Name: Interior - L2 AHUs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on DE133: Activity Name: Interior - L2 Busway - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on DU133: Activity Name: Interior - L2 UPS - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on CX134: Activity Name: Interior - L2 ATSs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on DU134: Activity Name: Interior - L2 PDUs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on EV137: Activity Name: Interior - L3 TCP/MSB - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on FC137: Activity Name: Interior - L3 UPS - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 15-Apr-2025 End Date: 21-Apr-2025
Note on FJ137: Activity Name: Interior - L3 ATSs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on FQ137: Activity Name: Interior - L3 AHUs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 29-Apr-2025 End Date: 12-May-2025
Note on GE137: Activity Name: Interior - L3 Busway - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 13-May-2025 End Date: 19-May-2025
Note on FC138: Activity Name: Interior - L3 PDUs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 15-Apr-2025 End Date: 21-Apr-2025
Note on FC139: Activity Name: Interior - L3 ADP - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 15-Apr-2025 End Date: 21-Apr-2025
Note on BE143: Activity Name: Cable Pulling at PDU to Busway & MSB - COLO2 Cell 1 - DH Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 03-Jan-2025 End Date: 31-Jan-2025
Note on CQ143: Activity Name: Finishes and Signage - COLO2 Cell 1 - DH Phase: COLO 2 Location: Cell 1 Trade: All Trades Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on BL144: Activity Name: Termination at PDU to Busway & MSB- COLO2 Cell 1 - DH Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 10-Jan-2025 End Date: 07-Feb-2025
Note on BE146: Activity Name: Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER Phase: COLO 2 Location: Cell 1 Trade: Gurtz Electric Start Date: 03-Jan-2025 End Date: 31-Jan-2025
Note on CJ146: Activity Name: Finishes and Signage - COLO2 Cell 1 - ER Phase: COLO 2 Location: Cell 1 Trade: All Trades Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on CJ148: Activity Name: Interior - L2 TCP/MSB - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on CQ148: Activity Name: Interior - L2 UPS - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on CX148: Activity Name: Interior - L2 ATSs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on DE148: Activity Name: Interior - L2 AHUs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on DL148: Activity Name: Interior - L2 Busway - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 03-Mar-2025 End Date: 07-Mar-2025
Note on CQ149: Activity Name: Interior - L2 PDUs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on CQ150: Activity Name: Interior - L2 ADP - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on EV153: Activity Name: Interior - L3 TCP/MSB - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on FC153: Activity Name: Interior - L3 UPS - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 15-Apr-2025 End Date: 21-Apr-2025
Note on FJ153: Activity Name: Interior - L3 ATSs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on FQ153: Activity Name: Interior - L3 AHUs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 29-Apr-2025 End Date: 12-May-2025
Note on GE153: Activity Name: Interior - L3 Busway - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 13-May-2025 End Date: 19-May-2025
Note on FC154: Activity Name: Interior - L3 PDUs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 15-Apr-2025 End Date: 21-Apr-2025
Note on FC155: Activity Name: Interior - L3 ADP - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 15-Apr-2025 End Date: 21-Apr-2025
Note on BE159: Activity Name: Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 03-Jan-2025 End Date: 23-Jan-2025
Note on BZ159: Activity Name: Termination at PDU & Busway - COLO2 Cell 2 - DH Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 13-Feb-2025
Note on CX159: Activity Name: Finishes and Signage - COLO2 Cell 2 - DH Phase: COLO 2 Location: Cell 2 Trade: All Trades Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on BE162: Activity Name: Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 03-Jan-2025 End Date: 31-Jan-2025
Note on CQ162: Activity Name: Finishes and Signage - COLO2 Cell 2 - ER Phase: COLO 2 Location: Cell 2 Trade: All Trades Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on BL164: Activity Name: Install ceiling and Light Fittings - COLO2 Cell 2 - MG Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 10-Jan-2025 End Date: 21-Jan-2025
Note on BX164: Activity Name: Trim out MEP - COLO2 Cell 2 - MG Phase: COLO 2 Location: Cell 2 Trade: Gurtz Electric Start Date: 22-Jan-2025 End Date: 28-Jan-2025
Note on CQ166: Activity Name: Interior - L2 TCP/MSB - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on CX166: Activity Name: Interior - L2 UPS - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on DE166: Activity Name: Interior - L2 ATSs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on DL166: Activity Name: Interior - L2 AHUs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 03-Mar-2025 End Date: 07-Mar-2025
Note on CX167: Activity Name: Interior - L2 PDUs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on DL167: Activity Name: Interior - L2 Busway - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 03-Mar-2025 End Date: 07-Mar-2025
Note on CX168: Activity Name: Interior - L2 ADP - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on FC170: Activity Name: Interior - L3 TCP/MSB - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 15-Apr-2025 End Date: 21-Apr-2025
Note on FJ170: Activity Name: Interior - L3 UPS - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on FQ170: Activity Name: Interior - L3 ATSs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 29-Apr-2025 End Date: 05-May-2025
Note on FX170: Activity Name: Interior - L3 AHUs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 06-May-2025 End Date: 19-May-2025
Note on GL170: Activity Name: Interior - L3 Busway - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 20-May-2025 End Date: 27-May-2025
Note on FJ171: Activity Name: Interior - L3 PDUs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on FJ172: Activity Name: Interior - L3 ADP - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on BL176: Activity Name: Termination at PDU & Busway - COLO2 Cell 3 - DH Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 10-Jan-2025 End Date: 30-Jan-2025
Note on DE176: Activity Name: Finishes and Signage - COLO2 Cell 3 - DH Phase: COLO 2 Location: Cell 3 Trade: All Trades Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on BS177: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Telecom Start Date: 17-Jan-2025 End Date: 30-Jan-2025
Note on BL179: Activity Name: Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 10-Jan-2025 End Date: 30-Jan-2025
Note on CD180: Activity Name: Finishes and Signage - COLO2 Cell 3 - ER Phase: COLO 2 Location: Cell 3 Trade: All Trades Start Date: 28-Jan-2025 End Date: 03-Feb-2025
Note on BS181: Activity Name: Pipe Testing - COLO2 Cell 3 - MG Phase: COLO 2 Location: Cell 3 Trade: Inspections Start Date: 17-Jan-2025 End Date: 20-Jan-2025
Note on BX181: Activity Name: Install ceiling and Light Fittings - COLO2 Cell 3 - MG Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 22-Jan-2025 End Date: 31-Jan-2025
Note on CJ181: Activity Name: Trim out MEP - COLO2 Cell 3 - MG Phase: COLO 2 Location: Cell 3 Trade: Gurtz Electric Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on DB184: Activity Name: Interior - L2 TCP/MSB - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 21-Feb-2025 End Date: 27-Feb-2025
Note on DI184: Activity Name: Interior - L2 UPS - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 28-Feb-2025 End Date: 06-Mar-2025
Note on DP184: Activity Name: Interior - L2 ATSs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 07-Mar-2025 End Date: 13-Mar-2025
Note on DI185: Activity Name: Interior - L2 PDUs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 28-Feb-2025 End Date: 06-Mar-2025
Note on DS185: Activity Name: Interior - L2 AHUs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on DI186: Activity Name: Interior - L2 ADP - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 28-Feb-2025 End Date: 06-Mar-2025
Note on DS186: Activity Name: Interior - L2 Busway - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on FJ190: Activity Name: Interior - L3 TCP/MSB - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on FQ190: Activity Name: Interior - L3 PDUs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 29-Apr-2025 End Date: 05-May-2025
Note on FX190: Activity Name: Interior - L3 ATSs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 06-May-2025 End Date: 12-May-2025
Note on GE190: Activity Name: Interior - L3 UPS - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 13-May-2025 End Date: 19-May-2025
Note on GT190: Activity Name: Interior - L3 Busway - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 28-May-2025 End Date: 03-Jun-2025
Note on FQ191: Activity Name: Interior - L3 ADP - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 29-Apr-2025 End Date: 05-May-2025
Note on GE191: Activity Name: Interior - L3 AHUs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 13-May-2025 End Date: 27-May-2025
Note on BL195: Activity Name: Termination at PDU & Busway - COLO2 Cell 4 - DH Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 10-Jan-2025 End Date: 30-Jan-2025
Note on CG195: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Telecom Start Date: 31-Jan-2025 End Date: 13-Feb-2025
Note on DL195: Activity Name: Finishes and Signage - COLO2 Cell 4 - DH Phase: COLO 2 Location: Cell 4 Trade: All Trades Start Date: 03-Mar-2025 End Date: 07-Mar-2025
Note on BP198: Activity Name: Connect to Cable tray and conduit equipment - COLO2 Cell 4 - ER Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 14-Jan-2025 End Date: 20-Jan-2025
Note on CG198: Activity Name: Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 31-Jan-2025 End Date: 20-Feb-2025
Note on DB198: Activity Name: Finishes and Signage - COLO2 Cell 4 - ER Phase: COLO 2 Location: Cell 4 Trade: All Trades Start Date: 21-Feb-2025 End Date: 27-Feb-2025
Note on BS201: Activity Name: Piping and Electrical Termination to AHUs - COLO2 Cell 4 - MG Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Telecom Start Date: 17-Jan-2025 End Date: 30-Jan-2025
Note on CG201: Activity Name: Pipe Testing - COLO2 Cell 4 - MG Phase: COLO 2 Location: Cell 4 Trade: Inspections Start Date: 31-Jan-2025 End Date: 03-Feb-2025
Note on CK201: Activity Name: Install ceiling and Light Fittings - COLO2 Cell 4 - MG Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 04-Feb-2025 End Date: 13-Feb-2025
Note on CU201: Activity Name: Trim out MEP - COLO2 Cell 4 - MG Phase: COLO 2 Location: Cell 4 Trade: Gurtz Electric Start Date: 14-Feb-2025 End Date: 20-Feb-2025
Note on LW205: Activity Name: Level 5 Cx / IST - Colo 3 Phase: COLO 3 Location: All Trade: Microsoft Start Date: 08-Oct-2025 End Date: 04-Nov-2025
Note on LW206: Activity Name: Level 4 Cx - Colo 3 Phase: COLO 3 Location: All Trade: Microsoft Start Date: 08-Oct-2025 End Date: 06-Nov-2025
Note on BZ207: Activity Name: Interior - L1 PDUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 24-Jan-2025
Note on DG207: Activity Name: Interior - L1 UPS - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 26-Feb-2025 End Date: 26-Feb-2025
Note on DZ209: Activity Name: Interior - L2 TCP/MSB - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on EG209: Activity Name: Interior - L2 UPS - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EN209: Activity Name: Interior - L2 ATSs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on EU209: Activity Name: Interior - L2 AHUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on EG210: Activity Name: Interior - L2 PDUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EN210: Activity Name: Interior - L2 Busway - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on EG211: Activity Name: Interior - L2 ADP - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on JX213: Activity Name: Interior - L3 TCP/MSB - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 18-Aug-2025 End Date: 22-Aug-2025
Note on KE213: Activity Name: Interior - L3 UPS - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 25-Aug-2025 End Date: 29-Aug-2025
Note on KM213: Activity Name: Interior - L3 ATSs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 02-Sep-2025 End Date: 08-Sep-2025
Note on KU213: Activity Name: Interior - L3 AHUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 10-Sep-2025 End Date: 23-Sep-2025
Note on LI213: Activity Name: Interior - L3 Busway - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Sep-2025 End Date: 30-Sep-2025
Note on KE214: Activity Name: Interior - L3 PDUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 25-Aug-2025 End Date: 29-Aug-2025
Note on KE215: Activity Name: Interior - L3 ADP - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 25-Aug-2025 End Date: 29-Aug-2025
Note on BS219: Activity Name: Install PDU's - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 23-Jan-2025
Note on BZ219: Activity Name: HAC install and Rise - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: Interior System Start Date: 24-Jan-2025 End Date: 30-Jan-2025
Note on CG219: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Telecom Start Date: 31-Jan-2025 End Date: 13-Feb-2025
Note on DE219: Activity Name: Finishes and Signage - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: All Trades Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on BS220: Activity Name: Begin HAC Assembly - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: Interior System Start Date: 17-Jan-2025 End Date: 23-Jan-2025
Note on BZ220: Activity Name: Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 13-Feb-2025
Note on CC221: Activity Name: Install Busway - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on CJ221: Activity Name: Termination at PDU & Busway- COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 03-Feb-2025 End Date: 21-Feb-2025
Note on CC223: Activity Name: Connect to Cable tray and conduit equipment - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on CJ223: Activity Name: Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 03-Feb-2025 End Date: 18-Feb-2025
Note on CZ223: Activity Name: Installation of UPS Equipment - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 19-Feb-2025 End Date: 25-Feb-2025
Note on DG223: Activity Name: Door Frame Installation - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: Anning - Johnson Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on DN223: Activity Name: Finishes and Signage - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: All Trades Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on BP227: Activity Name: Install ceiling and Light Fittings - COLO3 Cell 1 - MG Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 14-Jan-2025 End Date: 23-Jan-2025
Note on BZ227: Activity Name: Trim out MEP - COLO3 Cell 1 - MG Phase: COLO 3 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 30-Jan-2025
Note on BS229: Activity Name: Interior - L1 AHUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 17-Jan-2025
Note on BY229: Activity Name: Interior - L1 TCP/MSB - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 23-Jan-2025 End Date: 23-Jan-2025
Note on CS229: Activity Name: Interior - L1 PDUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 12-Feb-2025 End Date: 12-Feb-2025
Note on DH229: Activity Name: Interior - L1 UPS - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 27-Feb-2025 End Date: 27-Feb-2025
Note on BY230: Activity Name: Interior - L1 ATSs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 23-Jan-2025 End Date: 23-Jan-2025
Note on BY231: Activity Name: Interior - L1 Busway - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 23-Jan-2025 End Date: 23-Jan-2025
Note on BY232: Activity Name: Interior - L1 ADP - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 23-Jan-2025 End Date: 23-Jan-2025
Note on DZ236: Activity Name: Interior - L2 TCP/MSB - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on EG236: Activity Name: Interior - L2 UPS - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EN236: Activity Name: Interior - L2 ATSs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on FB236: Activity Name: Interior - L2 AHUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on EG237: Activity Name: Interior - L2 PDUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EN237: Activity Name: Interior - L2 Busway - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on EG238: Activity Name: Interior - L2 ADP - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on JX242: Activity Name: Interior - L3 TCP/MSB - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 18-Aug-2025 End Date: 22-Aug-2025
Note on KE242: Activity Name: Interior - L3 UPS - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 25-Aug-2025 End Date: 29-Aug-2025
Note on KM242: Activity Name: Interior - L3 PDUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 02-Sep-2025 End Date: 08-Sep-2025
Note on KU242: Activity Name: Interior - L3 AHUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 10-Sep-2025 End Date: 23-Sep-2025
Note on LI242: Activity Name: Interior - L3 Busway - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 24-Sep-2025 End Date: 30-Sep-2025
Note on KE243: Activity Name: Interior - L3 ADP - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 25-Aug-2025 End Date: 29-Aug-2025
Note on KM243: Activity Name: Interior - L3 ATSs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 02-Sep-2025 End Date: 08-Sep-2025
Note on BQ247: Activity Name: Ceiling Grid and Tile - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: Anning - Johnson Start Date: 15-Jan-2025 End Date: 21-Jan-2025
Note on BX247: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 22-Jan-2025 End Date: 04-Feb-2025
Note on CL247: Activity Name: Install PDU's - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 05-Feb-2025 End Date: 11-Feb-2025
Note on CS247: Activity Name: HAC install and Rise - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: Interior System Start Date: 12-Feb-2025 End Date: 18-Feb-2025
Note on CZ247: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Telecom Start Date: 19-Feb-2025 End Date: 04-Mar-2025
Note on DN247: Activity Name: Finishes and Signage - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: All Trades Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on CL248: Activity Name: Begin HAC Assembly - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: Interior System Start Date: 05-Feb-2025 End Date: 11-Feb-2025
Note on CS248: Activity Name: Cable Pulling at PDU & Busway- COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 12-Feb-2025 End Date: 25-Feb-2025
Note on CN249: Activity Name: Install Busway - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on CU249: Activity Name: Termination at PDU & Busway - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 14-Feb-2025 End Date: 06-Mar-2025
Note on BP251: Activity Name: Below Ceiling MEP Rough In - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 14-Jan-2025 End Date: 27-Jan-2025
Note on CJ251: Activity Name: Connect to Cable tray and conduit equipment - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on CZ251: Activity Name: Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 19-Feb-2025 End Date: 06-Mar-2025
Note on DU251: Activity Name: Finishes and Signage - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: All Trades Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on BQ252: Activity Name: Install DX Split Units - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: Great Lakes HVAC Start Date: 15-Jan-2025 End Date: 21-Jan-2025
Note on BY252: Activity Name: Door Frame Installation - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: Anning - Johnson Start Date: 23-Jan-2025 End Date: 29-Jan-2025
Note on BR253: Activity Name: Installation of ADP & ATS - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 16-Jan-2025 End Date: 22-Jan-2025
Note on BR254: Activity Name: Installation of UPS Equipment - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 16-Jan-2025 End Date: 22-Jan-2025
Note on BL255: Activity Name: Post Wall Overhead MEP - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 10-Jan-2025 End Date: 30-Jan-2025
Note on CK255: Activity Name: Pipe Testing - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: Inspections Start Date: 04-Feb-2025 End Date: 06-Feb-2025
Note on CY255: Activity Name: Trim out MEP - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 18-Feb-2025 End Date: 25-Feb-2025
Note on BS256: Activity Name: Placing the AHU - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: Great Lakes Air Design Start Date: 17-Jan-2025 End Date: 21-Jan-2025
Note on CM256: Activity Name: Install ceiling and Light Fittings - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Start Date: 06-Feb-2025 End Date: 18-Feb-2025
Note on BW257: Activity Name: Piping and Electrical Termination to AHUs - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: Gurtz Electric Telecom Start Date: 21-Jan-2025 End Date: 04-Feb-2025
Note on BW259: Activity Name: Interior - L1 AHUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 21-Jan-2025 End Date: 22-Jan-2025
Note on CM259: Activity Name: Interior - L1 TCP/MSB - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 06-Feb-2025 End Date: 06-Feb-2025
Note on DG259: Activity Name: Interior - L1 PDUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 26-Feb-2025 End Date: 26-Feb-2025
Note on DI259: Activity Name: Interior - L1 UPS - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 28-Feb-2025 End Date: 28-Feb-2025
Note on CM260: Activity Name: Interior - L1 ATSs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 06-Feb-2025 End Date: 06-Feb-2025
Note on CM261: Activity Name: Interior - L1 Busway - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 06-Feb-2025 End Date: 06-Feb-2025
Note on CM262: Activity Name: Interior - L1 ADP - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 06-Feb-2025 End Date: 06-Feb-2025
Note on EH263: Activity Name: Interior - L2 TCP/MSB - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on EO263: Activity Name: Interior - L2 UPS - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on EV263: Activity Name: Interior - L2 Busway - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on FI263: Activity Name: Interior - L2 AHUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on EH264: Activity Name: Interior - L2 ATSs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on EO264: Activity Name: Interior - L2 PDUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on EH265: Activity Name: Interior - L2 ADP - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on KE268: Activity Name: Interior - L3 TCP/MSB - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 25-Aug-2025 End Date: 29-Aug-2025
Note on KM268: Activity Name: Interior - L3 UPS - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 02-Sep-2025 End Date: 08-Sep-2025
Note on KT268: Activity Name: Interior - L3 ADP - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 09-Sep-2025 End Date: 15-Sep-2025
Note on LB268: Activity Name: Interior - L3 ATSs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 17-Sep-2025 End Date: 23-Sep-2025
Note on LI268: Activity Name: Interior - L3 Busway - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 24-Sep-2025 End Date: 30-Sep-2025
Note on KM269: Activity Name: Interior - L3 PDUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 02-Sep-2025 End Date: 08-Sep-2025
Note on LI269: Activity Name: Interior - L3 AHUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 24-Sep-2025 End Date: 07-Oct-2025
Note on BX273: Activity Name: Ceiling Grid and Tile - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: Anning - Johnson Start Date: 22-Jan-2025 End Date: 28-Jan-2025
Note on CL273: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 05-Feb-2025 End Date: 18-Feb-2025
Note on CZ273: Activity Name: Install PDU's - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 19-Feb-2025 End Date: 25-Feb-2025
Note on DG273: Activity Name: HAC install and Rise - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: Interior System Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on DN273: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Telecom Start Date: 05-Mar-2025 End Date: 18-Mar-2025
Note on EI273: Activity Name: Finishes and Signage - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: All Trades Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on CZ274: Activity Name: Begin HAC Assembly - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: Interior System Start Date: 19-Feb-2025 End Date: 25-Feb-2025
Note on DG274: Activity Name: Cable Pulling at PDU & Busway- COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 26-Feb-2025 End Date: 11-Mar-2025
Note on DU274: Activity Name: Termination at PDU & Busway - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 12-Mar-2025 End Date: 01-Apr-2025
Note on DB275: Activity Name: Install Busway - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 21-Feb-2025 End Date: 27-Feb-2025
Note on BS277: Activity Name: Install DX Split Units - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: Great Lakes HVAC Start Date: 17-Jan-2025 End Date: 23-Jan-2025
Note on CD277: Activity Name: Below Ceiling MEP Rough In - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 28-Jan-2025 End Date: 10-Feb-2025
Note on DP277: Activity Name: Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 07-Mar-2025 End Date: 24-Mar-2025
Note on CF278: Activity Name: Installation of ADP & ATS - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 30-Jan-2025 End Date: 05-Feb-2025
Note on CM278: Activity Name: Door Frame Installation - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: Anning - Johnson Start Date: 06-Feb-2025 End Date: 12-Feb-2025
Note on EC278: Activity Name: Finishes and Signage - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: All Trades Start Date: 20-Mar-2025 End Date: 26-Mar-2025
Note on CF279: Activity Name: Installation of UPS Equipment - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 30-Jan-2025 End Date: 05-Feb-2025
Note on CQ279: Activity Name: Connect to Cable tray and conduit equipment - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on CF280: Activity Name: Installation of TCP/MSB - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 30-Jan-2025 End Date: 05-Feb-2025
Note on BL281: Activity Name: Post Wall Overhead MEP - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 10-Jan-2025 End Date: 30-Jan-2025
Note on CK281: Activity Name: Piping and Electrical Termination to AHUs - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Telecom Start Date: 04-Feb-2025 End Date: 18-Feb-2025
Note on DA281: Activity Name: Install ceiling and Light Fittings - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 20-Feb-2025 End Date: 04-Mar-2025
Note on CY282: Activity Name: Pipe Testing - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: Inspections Start Date: 18-Feb-2025 End Date: 20-Feb-2025
Note on DM282: Activity Name: Trim out MEP - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: Gurtz Electric Start Date: 04-Mar-2025 End Date: 11-Mar-2025
Note on CR285: Activity Name: Interior - L1 AHUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 11-Feb-2025 End Date: 11-Feb-2025
Note on DA285: Activity Name: Interior - L1 TCP/MSB - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 20-Feb-2025 End Date: 20-Feb-2025
Note on DI285: Activity Name: Interior - L1 UPS - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 28-Feb-2025 End Date: 28-Feb-2025
Note on DU285: Activity Name: Interior - L1 PDUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 12-Mar-2025 End Date: 12-Mar-2025
Note on DA286: Activity Name: Interior - L1 ATSs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 20-Feb-2025 End Date: 20-Feb-2025
Note on DA287: Activity Name: Interior - L1 Busway - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 20-Feb-2025 End Date: 20-Feb-2025
Note on DA288: Activity Name: Interior - L1 ADP - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 20-Feb-2025 End Date: 20-Feb-2025
Note on EH289: Activity Name: Interior - L2 TCP/MSB - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 25-Mar-2025 End Date: 01-Apr-2025
Note on EV289: Activity Name: Interior - L2 Busway - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 08-Apr-2025 End Date: 15-Apr-2025
Note on FD289: Activity Name: Interior - L2 PDUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 16-Apr-2025 End Date: 22-Apr-2025
Note on EO290: Activity Name: Interior - L2 UPS - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 01-Apr-2025 End Date: 08-Apr-2025
Note on FI290: Activity Name: Interior - L2 AHUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on EO291: Activity Name: Interior - L2 ATSs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 01-Apr-2025 End Date: 08-Apr-2025
Note on EV292: Activity Name: Interior - L2 ADP - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 08-Apr-2025 End Date: 15-Apr-2025
Note on KE295: Activity Name: Interior - L3 TCP/MSB - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 25-Aug-2025 End Date: 29-Aug-2025
Note on KM295: Activity Name: Interior - L3 PDUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 02-Sep-2025 End Date: 08-Sep-2025
Note on KU295: Activity Name: Interior - L3 ATSs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 10-Sep-2025 End Date: 16-Sep-2025
Note on LI295: Activity Name: Interior - L3 UPS - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 24-Sep-2025 End Date: 30-Sep-2025
Note on LP295: Activity Name: Interior - L3 Busway - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 01-Oct-2025 End Date: 07-Oct-2025
Note on KM296: Activity Name: Interior - L3 ADP - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 02-Sep-2025 End Date: 08-Sep-2025
Note on KN297: Activity Name: Interior - L3 AHUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 03-Sep-2025 End Date: 16-Sep-2025
Note on BL301: Activity Name: Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 10-Jan-2025 End Date: 27-Jan-2025
Note on CK301: Activity Name: Security Screen Installation - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: Anning - Johnson Start Date: 04-Feb-2025 End Date: 06-Feb-2025
Note on CN301: Activity Name: Ceiling Grid and Tile - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: Anning - Johnson Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on CZ301: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 19-Feb-2025 End Date: 04-Mar-2025
Note on DN301: Activity Name: Install PDU's - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on DU301: Activity Name: HAC install and Rise - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: Interior System Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on EP301: Activity Name: Termination at PDU & Busway - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 02-Apr-2025 End Date: 15-Apr-2025
Note on DN302: Activity Name: Begin HAC Assembly - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: Interior System Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on DU302: Activity Name: Cable Pulling at PDU & Busway- COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 12-Mar-2025 End Date: 25-Mar-2025
Note on EW302: Activity Name: Finishes and Signage - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: All Trades Start Date: 09-Apr-2025 End Date: 15-Apr-2025
Note on DN303: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Telecom Start Date: 05-Mar-2025 End Date: 18-Mar-2025
Note on DP304: Activity Name: Install Busway - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 07-Mar-2025 End Date: 13-Mar-2025
Note on BO305: Activity Name: Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 13-Jan-2025 End Date: 24-Jan-2025
Note on CC305: Activity Name: Install Ceiling - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: Anning - Johnson Start Date: 27-Jan-2025 End Date: 29-Jan-2025
Note on CF305: Activity Name: Install DX Split Units - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: Great Lakes HVAC Start Date: 30-Jan-2025 End Date: 05-Feb-2025
Note on CR305: Activity Name: Below Ceiling MEP Rough In - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 11-Feb-2025 End Date: 24-Feb-2025
Note on DM305: Activity Name: Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 04-Mar-2025 End Date: 24-Mar-2025
Note on EJ305: Activity Name: Finishes and Signage - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: All Trades Start Date: 27-Mar-2025 End Date: 02-Apr-2025
Note on CT306: Activity Name: Installation of ADP & ATS - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 13-Feb-2025 End Date: 19-Feb-2025
Note on DA306: Activity Name: Door Frame Installation - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: Anning - Johnson Start Date: 20-Feb-2025 End Date: 26-Feb-2025
Note on CT307: Activity Name: Installation of UPS Equipment - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 13-Feb-2025 End Date: 19-Feb-2025
Note on CT308: Activity Name: Installation of TCP/MSB - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 13-Feb-2025 End Date: 19-Feb-2025
Note on BS309: Activity Name: Deliver AHU into Mech. Gallery - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: Great Lakes Air Design Start Date: 17-Jan-2025 End Date: 20-Jan-2025
Note on BW309: Activity Name: Install Walls and Primer Paint - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: All - Tech Start Date: 21-Jan-2025 End Date: 03-Feb-2025
Note on CK309: Activity Name: Layout Ceiling and install Pencile Rod - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: Anning - Johnson Start Date: 04-Feb-2025 End Date: 04-Feb-2025
Note on CR309: Activity Name: Placing the AHU - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: Great Lakes Air Design Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on CY309: Activity Name: Piping and Electrical Termination to AHUs - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Telecom Start Date: 18-Feb-2025 End Date: 04-Mar-2025
Note on DO309: Activity Name: Install ceiling and Light Fittings - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 06-Mar-2025 End Date: 18-Mar-2025
Note on CK310: Activity Name: Post Wall Overhead MEP - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 04-Feb-2025 End Date: 24-Feb-2025
Note on DM310: Activity Name: Pipe Testing - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: Inspections Start Date: 04-Mar-2025 End Date: 06-Mar-2025
Note on EA310: Activity Name: Trim out MEP - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: Gurtz Electric Start Date: 18-Mar-2025 End Date: 25-Mar-2025
Note on NL313: Activity Name: Level 4 Cx - Colo 4 Phase: COLO 4 Location: All Trade: Microsoft Start Date: 18-Nov-2025 End Date: 16-Dec-2025
Note on OP313: Activity Name: Level 5 Cx / IST - Colo 4 Phase: COLO 4 Location: All Trade: Microsoft Start Date: 18-Dec-2025 End Date: 19-Dec-2025
Note on BS315: Activity Name: Interior - L1 AHUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 17-Jan-2025
Note on BZ315: Activity Name: Interior - L1 UPS - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 24-Jan-2025
Note on CU315: Activity Name: Interior - L1 PDUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 14-Feb-2025 End Date: 14-Feb-2025
Note on CY315: Activity Name: Interior - L1 Busway - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 18-Feb-2025 End Date: 18-Feb-2025
Note on BZ316: Activity Name: Interior - L1 TCP/MSB - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 24-Jan-2025
Note on BZ317: Activity Name: Interior - L1 ATSs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 24-Jan-2025
Note on BZ318: Activity Name: Interior - L1 ADP - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 24-Jan-2025
Note on FP319: Activity Name: Interior - L2 TCP/MSB - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on FW319: Activity Name: Interior - L2 UPS - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 05-May-2025 End Date: 09-May-2025
Note on GD319: Activity Name: Interior - L2 ATSs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 12-May-2025 End Date: 16-May-2025
Note on GK319: Activity Name: Interior - L2 AHUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 19-May-2025 End Date: 23-May-2025
Note on FW320: Activity Name: Interior - L2 PDUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 05-May-2025 End Date: 09-May-2025
Note on GD320: Activity Name: Interior - L2 Busway - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 12-May-2025 End Date: 16-May-2025
Note on FW321: Activity Name: Interior - L2 ADP - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 05-May-2025 End Date: 09-May-2025
Note on LN325: Activity Name: Interior - L3 TCP/MSB - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 29-Sep-2025 End Date: 03-Oct-2025
Note on LU325: Activity Name: Interior - L3 UPS - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 06-Oct-2025 End Date: 10-Oct-2025
Note on MB325: Activity Name: Interior - L3 ATSs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 13-Oct-2025 End Date: 17-Oct-2025
Note on MI325: Activity Name: Interior - L3 AHUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 20-Oct-2025 End Date: 31-Oct-2025
Note on MW325: Activity Name: Interior - L3 Busway - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 03-Nov-2025 End Date: 07-Nov-2025
Note on LU326: Activity Name: Interior - L3 PDUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 06-Oct-2025 End Date: 10-Oct-2025
Note on LU327: Activity Name: Interior - L3 ADP - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 06-Oct-2025 End Date: 10-Oct-2025
Note on BS331: Activity Name: Ceiling Grid and Tile - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: Anning - Johnson Start Date: 17-Jan-2025 End Date: 23-Jan-2025
Note on BZ331: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 06-Feb-2025
Note on CN331: Activity Name: Install PDU's - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on CU331: Activity Name: HAC install and Rise - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: Interior System Start Date: 14-Feb-2025 End Date: 20-Feb-2025
Note on DB331: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Telecom Start Date: 21-Feb-2025 End Date: 06-Mar-2025
Note on DW331: Activity Name: Finishes and Signage - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: All Trades Start Date: 14-Mar-2025 End Date: 20-Mar-2025
Note on CN332: Activity Name: Begin HAC Assembly - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: Interior System Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on CU332: Activity Name: Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 14-Feb-2025 End Date: 06-Mar-2025
Note on CR333: Activity Name: Install Busway - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 11-Feb-2025 End Date: 17-Feb-2025
Note on DB333: Activity Name: Termination at PDU & Busway- COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 21-Feb-2025 End Date: 13-Mar-2025
Note on BP335: Activity Name: Below Ceiling MEP Rough In - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 14-Jan-2025 End Date: 27-Jan-2025
Note on CR335: Activity Name: Connect to Cable tray and conduit equipment - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 11-Feb-2025 End Date: 17-Feb-2025
Note on CY335: Activity Name: Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 18-Feb-2025 End Date: 10-Mar-2025
Note on BS336: Activity Name: Installation of ADP & ATS - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 23-Jan-2025
Note on BZ336: Activity Name: Door Frame Installation - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: Anning - Johnson Start Date: 24-Jan-2025 End Date: 30-Jan-2025
Note on DO336: Activity Name: Finishes and Signage - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: All Trades Start Date: 06-Mar-2025 End Date: 12-Mar-2025
Note on BS337: Activity Name: Installation of UPS Equipment - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 23-Jan-2025
Note on BS338: Activity Name: Installation of TCP/MSB - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 23-Jan-2025
Note on BL339: Activity Name: Post Wall Overhead MEP - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 10-Jan-2025 End Date: 30-Jan-2025
Note on CK339: Activity Name: Pipe Testing - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: Inspections Start Date: 04-Feb-2025 End Date: 06-Feb-2025
Note on CY339: Activity Name: Trim out MEP - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 18-Feb-2025 End Date: 25-Feb-2025
Note on BS340: Activity Name: Placing the AHU - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: Great Lakes Air Design Start Date: 17-Jan-2025 End Date: 21-Jan-2025
Note on CM340: Activity Name: Install ceiling and Light Fittings - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 06-Feb-2025 End Date: 18-Feb-2025
Note on BW341: Activity Name: Piping and Electrical Termination to AHUs - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: Gurtz Electric Start Date: 21-Jan-2025 End Date: 04-Feb-2025
Note on CQ343: Activity Name: Interior - L1 UPS - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on CR343: Activity Name: Interior - L1 AHUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 11-Feb-2025 End Date: 11-Feb-2025
Note on DP343: Activity Name: Interior - L1 PDUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 07-Mar-2025 End Date: 07-Mar-2025
Note on DT343: Activity Name: Interior - L1 Busway - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 11-Mar-2025 End Date: 11-Mar-2025
Note on CQ344: Activity Name: Interior - L1 TCP/MSB - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on CQ345: Activity Name: Interior - L1 ATSs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on CQ346: Activity Name: Interior - L1 ADP - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on FP350: Activity Name: Interior - L2 TCP/MSB - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on FW350: Activity Name: Interior - L2 UPS - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 05-May-2025 End Date: 09-May-2025
Note on GD350: Activity Name: Interior - L2 ATSs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 12-May-2025 End Date: 16-May-2025
Note on GK350: Activity Name: Interior - L2 AHUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 19-May-2025 End Date: 23-May-2025
Note on FW351: Activity Name: Interior - L2 PDUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 05-May-2025 End Date: 09-May-2025
Note on GD351: Activity Name: Interior - L2 Busway - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 12-May-2025 End Date: 16-May-2025
Note on FW352: Activity Name: Interior - L2 ADP - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 05-May-2025 End Date: 09-May-2025
Note on LN356: Activity Name: Interior - L3 TCP/MSB - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 29-Sep-2025 End Date: 03-Oct-2025
Note on LU356: Activity Name: Interior - L3 UPS - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 06-Oct-2025 End Date: 10-Oct-2025
Note on MB356: Activity Name: Interior - L3 ATSs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 13-Oct-2025 End Date: 17-Oct-2025
Note on MI356: Activity Name: Interior - L3 AHUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 20-Oct-2025 End Date: 31-Oct-2025
Note on MW356: Activity Name: Interior - L3 Busway - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 03-Nov-2025 End Date: 07-Nov-2025
Note on LU357: Activity Name: Interior - L3 PDUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 06-Oct-2025 End Date: 10-Oct-2025
Note on LU358: Activity Name: Interior - L3 ADP - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 06-Oct-2025 End Date: 10-Oct-2025
Note on BL362: Activity Name: Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 10-Jan-2025 End Date: 27-Jan-2025
Note on CK362: Activity Name: Security Screen Installation - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: Anning - Johnson Start Date: 04-Feb-2025 End Date: 06-Feb-2025
Note on CN362: Activity Name: Ceiling Grid and Tile - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: Anning - Johnson Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on CU362: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 14-Feb-2025 End Date: 27-Feb-2025
Note on DI362: Activity Name: Install PDU's - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 28-Feb-2025 End Date: 06-Mar-2025
Note on DP362: Activity Name: HAC install and Rise - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: Interior System Start Date: 07-Mar-2025 End Date: 13-Mar-2025
Note on DW362: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Telecom Start Date: 14-Mar-2025 End Date: 27-Mar-2025
Note on EK362: Activity Name: Finishes and Signage - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: All Trades Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on DI363: Activity Name: Begin HAC Assembly - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: Interior System Start Date: 28-Feb-2025 End Date: 06-Mar-2025
Note on DP363: Activity Name: Cable Pulling at PDU & Busway- COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 07-Mar-2025 End Date: 20-Mar-2025
Note on DM364: Activity Name: Install Busway - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on DT364: Activity Name: Termination at PDU & Busway - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 11-Mar-2025 End Date: 31-Mar-2025
Note on BW367: Activity Name: Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 21-Jan-2025 End Date: 27-Jan-2025
Note on CD367: Activity Name: Install Ceiling - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: Anning - Johnson Start Date: 28-Jan-2025 End Date: 30-Jan-2025
Note on CG367: Activity Name: Install DX Split Units - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: Great Lakes HVAC Start Date: 31-Jan-2025 End Date: 06-Feb-2025
Note on CQ367: Activity Name: Door Frame Installation - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: Anning - Johnson Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on CY367: Activity Name: Connect to Cable tray and conduit equipment - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 18-Feb-2025 End Date: 24-Feb-2025
Note on DT367: Activity Name: Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 11-Mar-2025 End Date: 31-Mar-2025
Note on CF368: Activity Name: Below Ceiling MEP Rough In - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 30-Jan-2025 End Date: 12-Feb-2025
Note on EJ368: Activity Name: Finishes and Signage - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: All Trades Start Date: 27-Mar-2025 End Date: 02-Apr-2025
Note on CJ369: Activity Name: Installation of ADP & ATS - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on CJ370: Activity Name: Installation of UPS Equipment - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on BS371: Activity Name: Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: Great Lakes Air Design Start Date: 17-Jan-2025 End Date: 20-Jan-2025
Note on BW371: Activity Name: Install Walls and Primer Paint - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: All - Tech Start Date: 21-Jan-2025 End Date: 03-Feb-2025
Note on CK371: Activity Name: Layout Ceiling and install Pencile Rod - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: Anning - Johnson Start Date: 04-Feb-2025 End Date: 04-Feb-2025
Note on CR371: Activity Name: Placing the AHU - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: Great Lakes Air Design Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on DH371: Activity Name: Pipe Testing - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: Inspections Start Date: 27-Feb-2025 End Date: 03-Mar-2025
Note on DV371: Activity Name: Trim out MEP - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 13-Mar-2025 End Date: 20-Mar-2025
Note on CK372: Activity Name: Post Wall Overhead MEP - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 04-Feb-2025 End Date: 24-Feb-2025
Note on DL372: Activity Name: Install ceiling and Light Fittings - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Start Date: 03-Mar-2025 End Date: 13-Mar-2025
Note on CT373: Activity Name: Piping and Electrical Termination to AHUs - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: Gurtz Electric Telecom Start Date: 13-Feb-2025 End Date: 27-Feb-2025
Note on DE375: Activity Name: Interior - L1 UPS - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 24-Feb-2025 End Date: 24-Feb-2025
Note on DF375: Activity Name: Interior - L1 AHUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 25-Feb-2025 End Date: 25-Feb-2025
Note on ED375: Activity Name: Interior - L1 PDUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 21-Mar-2025 End Date: 21-Mar-2025
Note on EH375: Activity Name: Interior - L1 Busway - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 25-Mar-2025 End Date: 25-Mar-2025
Note on DE376: Activity Name: Interior - L1 TCP/MSB - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 24-Feb-2025 End Date: 24-Feb-2025
Note on DE377: Activity Name: Interior - L1 ATSs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 24-Feb-2025 End Date: 24-Feb-2025
Note on DE378: Activity Name: Interior - L1 ADP - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 24-Feb-2025 End Date: 24-Feb-2025
Note on FW379: Activity Name: Interior - L2 TCP/MSB - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 05-May-2025 End Date: 09-May-2025
Note on GD379: Activity Name: Interior - L2 UPS - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 12-May-2025 End Date: 16-May-2025
Note on GK379: Activity Name: Interior - L2 ATSs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 19-May-2025 End Date: 23-May-2025
Note on GS379: Activity Name: Interior - L2 AHUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 27-May-2025 End Date: 02-Jun-2025
Note on GD380: Activity Name: Interior - L2 PDUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 12-May-2025 End Date: 16-May-2025
Note on GK380: Activity Name: Interior - L2 Busway - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 19-May-2025 End Date: 23-May-2025
Note on GD381: Activity Name: Interior - L2 ADP - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 12-May-2025 End Date: 16-May-2025
Note on LU385: Activity Name: Interior - L3 TCP/MSB - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 06-Oct-2025 End Date: 10-Oct-2025
Note on MB385: Activity Name: Interior - L3 UPS - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 13-Oct-2025 End Date: 17-Oct-2025
Note on MI385: Activity Name: Interior - L3 ATSs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 20-Oct-2025 End Date: 24-Oct-2025
Note on MP385: Activity Name: Interior - L3 AHUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 27-Oct-2025 End Date: 07-Nov-2025
Note on ND385: Activity Name: Interior - L3 Busway - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 10-Nov-2025 End Date: 14-Nov-2025
Note on MB386: Activity Name: Interior - L3 PDUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 13-Oct-2025 End Date: 17-Oct-2025
Note on MB387: Activity Name: Interior - L3 ADP - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 13-Oct-2025 End Date: 17-Oct-2025
Note on CD391: Activity Name: Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 28-Jan-2025 End Date: 12-Feb-2025
Note on CY391: Activity Name: Security Screen Installation - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: Anning - Johnson Start Date: 18-Feb-2025 End Date: 20-Feb-2025
Note on DB391: Activity Name: Ceiling Grid and Tile - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: Anning - Johnson Start Date: 21-Feb-2025 End Date: 27-Feb-2025
Note on DI391: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 28-Feb-2025 End Date: 13-Mar-2025
Note on DW391: Activity Name: Install PDU's - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 14-Mar-2025 End Date: 20-Mar-2025
Note on ED391: Activity Name: HAC install and Rise - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: Interior System Start Date: 21-Mar-2025 End Date: 27-Mar-2025
Note on EK391: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Telecom Start Date: 28-Mar-2025 End Date: 10-Apr-2025
Note on FC391: Activity Name: Finishes and Signage - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: All Trades Start Date: 15-Apr-2025 End Date: 21-Apr-2025
Note on DW392: Activity Name: Begin HAC Assembly - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: Interior System Start Date: 14-Mar-2025 End Date: 20-Mar-2025
Note on ED392: Activity Name: Cable Pulling at PDU & Busway- COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 21-Mar-2025 End Date: 03-Apr-2025
Note on EA393: Activity Name: Install Busway - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on EO393: Activity Name: Termination at PDU & Busway - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 01-Apr-2025 End Date: 21-Apr-2025
Note on CD395: Activity Name: Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 28-Jan-2025 End Date: 10-Feb-2025
Note on CR395: Activity Name: Install Ceiling - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: Anning - Johnson Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on CU395: Activity Name: Install DX Split Units - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: Great Lakes HVAC Start Date: 14-Feb-2025 End Date: 20-Feb-2025
Note on DE395: Activity Name: Door Frame Installation - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: Anning - Johnson Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on EO395: Activity Name: Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 01-Apr-2025 End Date: 21-Apr-2025
Note on CT396: Activity Name: Below Ceiling MEP Rough In - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 13-Feb-2025 End Date: 26-Feb-2025
Note on FE396: Activity Name: Finishes and Signage - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: All Trades Start Date: 17-Apr-2025 End Date: 23-Apr-2025
Note on CX397: Activity Name: Installation of ADP & ATS - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on DF397: Activity Name: Connect to Cable tray and conduit equipment - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 25-Feb-2025 End Date: 03-Mar-2025
Note on CX398: Activity Name: Installation of UPS Equipment - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on BL399: Activity Name: Overhead MEP Installation - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 10-Jan-2025 End Date: 23-Jan-2025
Note on BZ399: Activity Name: Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: Great Lakes Air Design Start Date: 24-Jan-2025 End Date: 27-Jan-2025
Note on CK399: Activity Name: Install Walls and Primer Paint - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: All - Tech Start Date: 04-Feb-2025 End Date: 17-Feb-2025
Note on CY399: Activity Name: Layout Ceiling and install Pencile Rod - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: Anning - Johnson Start Date: 18-Feb-2025 End Date: 18-Feb-2025
Note on DF399: Activity Name: Placing the AHU - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: Great Lakes Air Design Start Date: 25-Feb-2025 End Date: 27-Feb-2025
Note on DV399: Activity Name: Pipe Testing - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: Inspections Start Date: 13-Mar-2025 End Date: 17-Mar-2025
Note on EJ399: Activity Name: Trim out MEP - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 27-Mar-2025 End Date: 03-Apr-2025
Note on CY400: Activity Name: Post Wall Overhead MEP - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 18-Feb-2025 End Date: 10-Mar-2025
Note on DZ400: Activity Name: Install ceiling and Light Fittings - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Start Date: 17-Mar-2025 End Date: 27-Mar-2025
Note on DH401: Activity Name: Piping and Electrical Termination to AHUs - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: Gurtz Electric Telecom Start Date: 27-Feb-2025 End Date: 13-Mar-2025
Note on DO403: Activity Name: Interior - L1 TCP/MSB - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 06-Mar-2025 End Date: 10-Mar-2025
Note on DT403: Activity Name: Interior - L1 AHUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 11-Mar-2025 End Date: 13-Mar-2025
Note on ER403: Activity Name: Interior - L1 PDUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 04-Apr-2025 End Date: 08-Apr-2025
Note on DO404: Activity Name: Interior - L1 ATSs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 06-Mar-2025 End Date: 10-Mar-2025
Note on EV404: Activity Name: Interior - L1 Busway - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 08-Apr-2025 End Date: 10-Apr-2025
Note on DO405: Activity Name: Interior - L1 ADP - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 06-Mar-2025 End Date: 10-Mar-2025
Note on DS406: Activity Name: Interior - L1 UPS - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 10-Mar-2025 End Date: 12-Mar-2025
Note on GE407: Activity Name: Interior - L2 TCP/MSB - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 13-May-2025 End Date: 19-May-2025
Note on GL407: Activity Name: Interior - L2 UPS - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 20-May-2025 End Date: 27-May-2025
Note on GT407: Activity Name: Interior - L2 ATSs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 28-May-2025 End Date: 03-Jun-2025
Note on IQ407: Activity Name: Interior - L2 AHUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 16-Jul-2025 End Date: 23-Jul-2025
Note on GL408: Activity Name: Interior - L2 PDUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 20-May-2025 End Date: 27-May-2025
Note on GT408: Activity Name: Interior - L2 Busway - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 28-May-2025 End Date: 03-Jun-2025
Note on GL409: Activity Name: Interior - L2 ADP - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 20-May-2025 End Date: 27-May-2025
Note on LU413: Activity Name: Interior - L3 TCP/MSB - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 06-Oct-2025 End Date: 10-Oct-2025
Note on MB413: Activity Name: Interior - L3 UPS - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 13-Oct-2025 End Date: 17-Oct-2025
Note on MI413: Activity Name: Interior - L3 ATSs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 20-Oct-2025 End Date: 24-Oct-2025
Note on MP413: Activity Name: Interior - L3 AHUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 27-Oct-2025 End Date: 07-Nov-2025
Note on ND413: Activity Name: Interior - L3 Busway - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 10-Nov-2025 End Date: 14-Nov-2025
Note on MB414: Activity Name: Interior - L3 PDUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 13-Oct-2025 End Date: 17-Oct-2025
Note on MB415: Activity Name: Interior - L3 ADP - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 13-Oct-2025 End Date: 17-Oct-2025
Note on CT419: Activity Name: Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 13-Feb-2025 End Date: 28-Feb-2025
Note on DM419: Activity Name: Security Screen Installation - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: Anning - Johnson Start Date: 04-Mar-2025 End Date: 06-Mar-2025
Note on DP419: Activity Name: Ceiling Grid and Tile - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: Anning - Johnson Start Date: 07-Mar-2025 End Date: 13-Mar-2025
Note on DW419: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 14-Mar-2025 End Date: 27-Mar-2025
Note on EK419: Activity Name: Install PDU's - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on ER419: Activity Name: HAC install and Rise - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: Interior System Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on EY419: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Telecom Start Date: 11-Apr-2025 End Date: 24-Apr-2025
Note on FX419: Activity Name: Finishes and Signage - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: All Trades Start Date: 06-May-2025 End Date: 12-May-2025
Note on EK420: Activity Name: Begin HAC Assembly - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: Interior System Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on ER420: Activity Name: Cable Pulling at PDU & Busway- COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 04-Apr-2025 End Date: 17-Apr-2025
Note on FJ420: Activity Name: Termination at PDU & Busway - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 22-Apr-2025 End Date: 12-May-2025
Note on EO421: Activity Name: Install Busway - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on ER422: Activity Name: Closing Construction Access Door - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: WALSH Start Date: 04-Apr-2025 End Date: 24-Apr-2025
Note on BL423: Activity Name: Install Walls and Primer Paint - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: All - Tech Start Date: 10-Jan-2025 End Date: 23-Jan-2025
Note on CR423: Activity Name: Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 11-Feb-2025 End Date: 24-Feb-2025
Note on DF423: Activity Name: Install Ceiling - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: Anning - Johnson Start Date: 25-Feb-2025 End Date: 27-Feb-2025
Note on DI423: Activity Name: Install DX Split Units - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: Great Lakes HVAC Start Date: 28-Feb-2025 End Date: 06-Mar-2025
Note on DS423: Activity Name: Door Frame Installation - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: Anning - Johnson Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on FJ423: Activity Name: Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 22-Apr-2025 End Date: 12-May-2025
Note on BW424: Activity Name: Install Upper Screens - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: Anning - Johnson Start Date: 21-Jan-2025 End Date: 27-Jan-2025
Note on DH424: Activity Name: Installation of ADP & ATS - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 27-Feb-2025 End Date: 05-Mar-2025
Note on FX424: Activity Name: Finishes and Signage - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: All Trades Start Date: 06-May-2025 End Date: 12-May-2025
Note on DH425: Activity Name: Installation of TCP/MSB - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 27-Feb-2025 End Date: 05-Mar-2025
Note on DH426: Activity Name: Below Ceiling MEP Rough In - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 27-Feb-2025 End Date: 12-Mar-2025
Note on BP427: Activity Name: Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: Great Lakes Air Design Start Date: 14-Jan-2025 End Date: 20-Jan-2025
Note on BZ427: Activity Name: Overhead MEP Installation - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 24-Jan-2025 End Date: 06-Feb-2025
Note on CN427: Activity Name: Deliver AHU into Mech. Gallery - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: Great Lakes Air Design Start Date: 07-Feb-2025 End Date: 10-Feb-2025
Note on CY427: Activity Name: Install Walls and Primer Paint - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: All - Tech Start Date: 18-Feb-2025 End Date: 03-Mar-2025
Note on DM427: Activity Name: Layout Ceiling and install Pencile Rod - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: Anning - Johnson Start Date: 04-Mar-2025 End Date: 04-Mar-2025
Note on DT427: Activity Name: Placing the AHU - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: Great Lakes Air Design Start Date: 11-Mar-2025 End Date: 13-Mar-2025
Note on EJ427: Activity Name: Pipe Testing - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: Inspections Start Date: 27-Mar-2025 End Date: 31-Mar-2025
Note on EX427: Activity Name: Trim out MEP - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 10-Apr-2025 End Date: 17-Apr-2025
Note on DM428: Activity Name: Post Wall Overhead MEP - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 04-Mar-2025 End Date: 24-Mar-2025
Note on EN428: Activity Name: Install ceiling and Light Fittings - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Start Date: 31-Mar-2025 End Date: 10-Apr-2025
Note on DV429: Activity Name: Piping and Electrical Termination to AHUs - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: Gurtz Electric Telecom Start Date: 13-Mar-2025 End Date: 27-Mar-2025
Note on CQ431: Activity Name: Install screen wall - Colo 2 - North Phase: Yardwork Location: COLO 2 Trade: Ralph Simpson & Crown Core Start Date: 10-Feb-2025 End Date: 07-Mar-2025
Note on D432: Activity Name: Install screen wall - Colo 2 - South Phase: Yardwork Location: COLO 2 Trade: Ralph Simpson & Crown Core Start Date: 11-Nov-2024 End Date: 07-Mar-2025
Note on AX433: Activity Name: Wire pulling and termination for TCP/MSB - Colo 2 - South Phase: Yardwork Location: COLO 2 Trade: Gurtz Electric Start Date: 27-Dec-2024 End Date: 31-Jan-2025
Note on AX434: Activity Name: Wire pulling and termination for TCP/MSB - Colo 3 - North Phase: Yardwork Location: COLO 3 Trade: Gurtz Electric Start Date: 27-Dec-2024 End Date: 31-Jan-2025
Note on BA435: Activity Name: Install screen wall - Colo 3 - North Phase: Yardwork Location: COLO 3 Trade: Ralph Simpson & Crown Core Start Date: 30-Dec-2024 End Date: 28-Feb-2025
Note on BS436: Activity Name: Pull & Terminate Underground Cables (UMS to UPM to XMFR) Phase: Yardwork Location: COLO 3 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 13-Feb-2025
Note on BA437: Activity Name: Install screen wall - Colo 3 - South Phase: Yardwork Location: COLO 3 Trade: Ralph Simpson & Crown Core Start Date: 30-Dec-2024 End Date: 28-Feb-2025
Note on BS438: Activity Name: Pull & Terminate Underground Cables (UMS to UPM to XMFR) Phase: Yardwork Location: COLO 3 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 06-Feb-2025
Note on AX439: Activity Name: Wire pulling and termination for TCP/MSB - Colo 4 - North Phase: Yardwork Location: COLO 4 Trade: Gurtz Electric Start Date: 27-Dec-2024 End Date: 31-Jan-2025
Note on CU439: Activity Name: Pull & Terminate Underground Cables (UMS to UPM to XMFR) Phase: Yardwork Location: COLO 4 Trade: Gurtz Electric Start Date: 14-Feb-2025 End Date: 13-Mar-2025
Note on DL440: Activity Name: Install screen wall - Colo 4 - North Phase: Yardwork Location: COLO 4 Trade: Ralph Simpson & Crown Core Start Date: 03-Mar-2025 End Date: 28-Mar-2025
Note on AX442: Activity Name: Wire pulling and termination for TCP/MSB - Colo 4 - South Phase: Yardwork Location: COLO 4 Trade: Gurtz Electric Start Date: 27-Dec-2024 End Date: 31-Jan-2025
Note on CU442: Activity Name: Pull & Terminate Underground Cables (UMS to UPM to XMFR) Phase: Yardwork Location: COLO 4 Trade: Gurtz Electric Start Date: 14-Feb-2025 End Date: 13-Mar-2025
Note on DL443: Activity Name: Install screen wall - Colo 4 - South Phase: Yardwork Location: COLO 4 Trade: Ralph Simpson & Crown Core Start Date: 03-Mar-2025 End Date: 28-Mar-2025
Note on D445: Activity Name: Install screen wall - Colo 5 - East Phase: Yardwork Location: COLO 5 Trade: Ralph Simpson & Crown Core Start Date: 11-Nov-2024 End Date: 31-Jan-2025
Note on BS446: Activity Name: Install Generator Muffler - Colo 5 - West Phase: Yardwork Location: COLO 5 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 21-Jan-2025
Note on CJ446: Activity Name: Install screen wall - Colo 5 - West Phase: Yardwork Location: COLO 5 Trade: Ralph Simpson & Crown Core Start Date: 03-Feb-2025 End Date: 28-Feb-2025
Note on CX448: Activity Name: Assemble & Install Exhaust System Set (SW) Phase: Exhaust System Location: COLO 2 Trade: Gurtz Electric Start Date: 17-Feb-2025 End Date: 19-Feb-2025
Note on DA448: Activity Name: Assemble & Install Exhaust System Set (SE) Phase: Exhaust System Location: COLO 2 Trade: Gurtz Electric Start Date: 20-Feb-2025 End Date: 22-Feb-2025
Note on DE448: Activity Name: Assemble & Install Exhaust System Set (NE) Phase: Exhaust System Location: COLO 2 Trade: Gurtz Electric Start Date: 24-Feb-2025 End Date: 26-Feb-2025
Note on DH448: Activity Name: Assemble & Install Exhaust System Set (NW) Phase: Exhaust System Location: COLO 2 Trade: Gurtz Electric Start Date: 27-Feb-2025 End Date: 01-Mar-2025
Note on DT452: Activity Name: Assemble & Install Exhaust System Set (SW) Phase: Exhaust System Location: COLO 3 Trade: Gurtz Electric Start Date: 11-Mar-2025 End Date: 13-Mar-2025
Note on DW452: Activity Name: Assemble & Install Exhaust System Set (SE) Phase: Exhaust System Location: COLO 3 Trade: Gurtz Electric Start Date: 14-Mar-2025 End Date: 17-Mar-2025
Note on EO452: Activity Name: Assemble & Install Exhaust System Set (NE) Phase: Exhaust System Location: COLO 3 Trade: Gurtz Electric Start Date: 01-Apr-2025 End Date: 03-Apr-2025
Note on ER452: Activity Name: Assemble & Install Exhaust System Set (NW) Phase: Exhaust System Location: COLO 3 Trade: Gurtz Electric Start Date: 04-Apr-2025 End Date: 07-Apr-2025
Note on EA456: Activity Name: Assemble & Install Exhaust System Set (SW) Phase: Exhaust System Location: COLO 4 Trade: Gurtz Electric Start Date: 18-Mar-2025 End Date: 20-Mar-2025
Note on ED456: Activity Name: Assemble & Install Exhaust System Set (SE) Phase: Exhaust System Location: COLO 4 Trade: Gurtz Electric Start Date: 21-Mar-2025 End Date: 24-Mar-2025
Note on EH456: Activity Name: Assemble & Install Exhaust System Set (NE) Phase: Exhaust System Location: COLO 4 Trade: Gurtz Electric Start Date: 25-Mar-2025 End Date: 27-Mar-2025
Note on EK456: Activity Name: Assemble & Install Exhaust System Set (NW) Phase: Exhaust System Location: COLO 4 Trade: Gurtz Electric Start Date: 28-Mar-2025 End Date: 31-Mar-2025
Note on CQ460: Activity Name: Assemble & Install Exhaust System Set (SE) Phase: Exhaust System Location: COLO 5 Trade: Gurtz Electric Start Date: 10-Feb-2025 End Date: 12-Feb-2025
Note on CT460: Activity Name: Assemble & Install Exhaust System Set (NE) Phase: Exhaust System Location: COLO 5 Trade: Gurtz Electric Start Date: 13-Feb-2025 End Date: 15-Feb-2025
Note on DL460: Activity Name: Assemble & Install Exhaust System Set (NW) Phase: Exhaust System Location: COLO 5 Trade: Gurtz Electric Start Date: 03-Mar-2025 End Date: 05-Mar-2025
Note on DO460: Activity Name: Assemble & Install Exhaust System Set (SW) Phase: Exhaust System Location: COLO 5 Trade: Gurtz Electric Start Date: 06-Mar-2025 End Date: 08-Mar-2025
Note on BW464: Activity Name: (8) Remove Installed Set Off of Generators Phase: Exhaust System Location: Installed Sets Trade: Gurtz Electric Start Date: 21-Jan-2025 End Date: 19-Feb-2025
Note on DA464: Activity Name: (8) Sets Returned to Manufacture Phase: Exhaust System Location: Installed Sets Trade: WALSH Start Date: 20-Feb-2025 End Date: 21-Feb-2025
Note on DC464: Activity Name: (8) Sets Re-Finished Phase: Exhaust System Location: Installed Sets Trade: WALSH Start Date: 22-Feb-2025 End Date: 07-Mar-2025
Note on DQ464: Activity Name: (8) Sets Shipped Back to Jobsite Phase: Exhaust System Location: Installed Sets Trade: WALSH Start Date: 08-Mar-2025 End Date: 10-Mar-2025
Note on BW468: Activity Name: (8) Sets Returned to Manufacture Phase: Exhaust System Location: Non-Installed Sets Trade: WALSH Start Date: 21-Jan-2025 End Date: 22-Jan-2025
Note on BY468: Activity Name: (8) Sets Re-Finished Phase: Exhaust System Location: Non-Installed Sets Trade: WALSH Start Date: 23-Jan-2025 End Date: 06-Feb-2025
Note on CN468: Activity Name: (8) Sets Shipped Back to Jobsite Phase: Exhaust System Location: Non-Installed Sets Trade: WALSH Start Date: 07-Feb-2025 End Date: 08-Feb-2025
Note on CR471: Activity Name: L2 XFMR - COLO2 Phase: CX Level 2 Location: COLO 2 Trade: Gurtz Electric Start Date: 11-Feb-2025 End Date: 10-Mar-2025
Note on CR472: Activity Name: L2 GEN - COLO2 Phase: CX Level 2 Location: COLO 2 Trade: Gurtz Electric Start Date: 11-Feb-2025 End Date: 10-Mar-2025
Note on CS473: Activity Name: L2 UPM - COLO2 Phase: CX Level 2 Location: COLO 2 Trade: Gurtz Electric Start Date: 12-Feb-2025 End Date: 11-Mar-2025
Note on DF474: Activity Name: L2 UMS 03 - COLO 3 Phase: CX Level 2 Location: COLO 3 Trade: Gurtz Electric Start Date: 25-Feb-2025 End Date: 03-Mar-2025
Note on DM474: Activity Name: L2 UMS 04 - COLO 3 Phase: CX Level 2 Location: COLO 3 Trade: Gurtz Electric Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on EV474: Activity Name: L2 XFMR - COLO3 Phase: CX Level 2 Location: COLO 3 Trade: Gurtz Electric Start Date: 08-Apr-2025 End Date: 05-May-2025
Note on IH474: Activity Name: L2 UPM - COLO3 (UPM ROJ Driving) Phase: CX Level 2 Location: COLO 3 Trade: Gurtz Electric Start Date: 07-Jul-2025 End Date: 01-Aug-2025
Note on EV475: Activity Name: L2 GEN - COLO3 Phase: CX Level 2 Location: COLO 3 Trade: Gurtz Electric Start Date: 08-Apr-2025 End Date: 05-May-2025
Note on FX479: Activity Name: L2 XFMR - COLO4 Phase: CX Level 2 Location: COLO 4 Trade: Gurtz Electric Start Date: 06-May-2025 End Date: 03-Jun-2025
Note on IQ479: Activity Name: L2 UPM - COLO4 (UPM ROJ Driving) Phase: CX Level 2 Location: COLO 4 Trade: Gurtz Electric Start Date: 16-Jul-2025 End Date: 12-Aug-2025
Note on FX480: Activity Name: L2 GEN - COLO4 Phase: CX Level 2 Location: COLO 4 Trade: Gurtz Electric Start Date: 06-May-2025 End Date: 03-Jun-2025
Note on CR482: Activity Name: L2 UMS 01 - COLO 5 Phase: CX Level 2 Location: COLO 5 Trade: Gurtz Electric Start Date: 11-Feb-2025 End Date: 17-Feb-2025
Note on CY482: Activity Name: L2 UMS 02 - COLO 5 Phase: CX Level 2 Location: COLO 5 Trade: Gurtz Electric Start Date: 18-Feb-2025 End Date: 24-Feb-2025
Note on DT482: Activity Name: L2 URS 01 - COLO 5 Phase: CX Level 2 Location: COLO 5 Trade: Gurtz Electric Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on HV482: Activity Name: L2 UPM - COLO5 (UPM ROJ Driving) Phase: CX Level 2 Location: COLO 5 Trade: Gurtz Electric Start Date: 25-Jun-2025 End Date: 23-Jul-2025
Note on DT483: Activity Name: L2 XFMR - COLO5 Phase: CX Level 2 Location: COLO 5 Trade: Gurtz Electric Start Date: 11-Mar-2025 End Date: 07-Apr-2025
Note on DT484: Activity Name: L2 GEN - COLO5 Phase: CX Level 2 Location: COLO 5 Trade: Gurtz Electric Start Date: 11-Mar-2025 End Date: 07-Apr-2025
Note on CJ488: Activity Name: L2 UTS / UTSR - Site Phase: CX Level 2 Location: Site Trade: Gurtz Electric Start Date: 03-Feb-2025 End Date: 10-Feb-2025
Note on EK489: Activity Name: EPMS/BAS Turn-Up Phase: CX Level 3 Location: COLO 2 Trade: Gurtz Electric Start Date: 28-Mar-2025 End Date: 28-Mar-2025
Note on DW490: Activity Name: L3 GEN - Colo 2 Cell 1 Phase: CX Level 3 Location: COLO 2 Trade: Gurtz Electric Start Date: 14-Mar-2025 End Date: 20-Mar-2025
Note on EK490: Activity Name: L3 UPM - Colo 2 Cell 1 Phase: CX Level 3 Location: COLO 2 Trade: Gurtz Electric Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on ER490: Activity Name: L3 XFMR - Colo 2 Cell 1 Phase: CX Level 3 Location: COLO 2 Trade: Gurtz Electric Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on DW493: Activity Name: L3 GEN - Colo 2 Cell 2 Phase: CX Level 3 Location: COLO 2 Trade: Gurtz Electric Start Date: 14-Mar-2025 End Date: 20-Mar-2025
Note on EK493: Activity Name: L3 UPM - Colo 2 Cell 2 Phase: CX Level 3 Location: COLO 2 Trade: Gurtz Electric Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on ER493: Activity Name: L3 XFMR - Colo 2 Cell 2 Phase: CX Level 3 Location: COLO 2 Trade: Gurtz Electric Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on ED496: Activity Name: L3 GEN - Colo 2 Cell 3 Phase: CX Level 3 Location: COLO 2 Trade: Gurtz Electric Start Date: 21-Mar-2025 End Date: 27-Mar-2025
Note on EK496: Activity Name: L3 UPM - Colo 2 Cell 3 Phase: CX Level 3 Location: COLO 2 Trade: Gurtz Electric Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on ER496: Activity Name: L3 XFMR - Colo 2 Cell 3 Phase: CX Level 3 Location: COLO 2 Trade: Gurtz Electric Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on EK499: Activity Name: L3 GEN - Colo 2 Cell 4 Phase: CX Level 3 Location: COLO 2 Trade: Gurtz Electric Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on ER499: Activity Name: L3 XFMR - Colo 2 Cell 4 Phase: CX Level 3 Location: COLO 2 Trade: Gurtz Electric Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on EK500: Activity Name: L3 UPM - Colo 2 Cell 4 Phase: CX Level 3 Location: COLO 2 Trade: Gurtz Electric Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on ED502: Activity Name: L3 UMS 04 - COLO 3 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 21-Mar-2025 End Date: 27-Mar-2025
Note on EY502: Activity Name: EPMS/BAS Turn-Up Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 11-Apr-2025 End Date: 11-Apr-2025
Note on ED503: Activity Name: L3 UMS 03 - COLO 3 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 21-Mar-2025 End Date: 27-Mar-2025
Note on FY505: Activity Name: L3 GEN - Cell 1 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 07-May-2025 End Date: 13-May-2025
Note on JJ505: Activity Name: L3 UPM - Cell 1 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 04-Aug-2025 End Date: 08-Aug-2025
Note on JQ505: Activity Name: L3 XFMR - Cell 1 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 11-Aug-2025 End Date: 15-Aug-2025
Note on FX508: Activity Name: L3 GEN - Cell 2 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 06-May-2025 End Date: 12-May-2025
Note on JJ508: Activity Name: L3 UPM - Cell 2 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 04-Aug-2025 End Date: 08-Aug-2025
Note on JQ508: Activity Name: L3 XFMR - Cell 2 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 11-Aug-2025 End Date: 15-Aug-2025
Note on FX511: Activity Name: L3 GEN - Cell 3 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 06-May-2025 End Date: 12-May-2025
Note on JQ511: Activity Name: L3 UPM - Cell 3 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 11-Aug-2025 End Date: 15-Aug-2025
Note on JX511: Activity Name: L3 XFMR - Cell 3 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 18-Aug-2025 End Date: 22-Aug-2025
Note on FX514: Activity Name: L3 GEN - Cell 4 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 06-May-2025 End Date: 12-May-2025
Note on JQ514: Activity Name: L3 UPM - Cell 4 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 11-Aug-2025 End Date: 15-Aug-2025
Note on JX514: Activity Name: L3 XFMR - Cell 4 Phase: CX Level 3 Location: COLO 3 Trade: Gurtz Electric Start Date: 18-Aug-2025 End Date: 22-Aug-2025
Note on FM517: Activity Name: EPMS/BAS Turn-Up Phase: CX Level 3 Location: COLO 4 Trade: Gurtz Electric Start Date: 25-Apr-2025 End Date: 25-Apr-2025
Note on HA518: Activity Name: L3 GEN - Cell 1 Phase: CX Level 3 Location: COLO 4 Trade: Gurtz Electric Start Date: 04-Jun-2025 End Date: 10-Jun-2025
Note on KE518: Activity Name: L3 UPM - Cell 1 Phase: CX Level 3 Location: COLO 4 Trade: Gurtz Electric Start Date: 25-Aug-2025 End Date: 29-Aug-2025
Note on KM518: Activity Name: L3 XFMR - Cell 1 Phase: CX Level 3 Location: COLO 4 Trade: Gurtz Electric Start Date: 02-Sep-2025 End Date: 08-Sep-2025
Note on HH521: Activity Name: L3 GEN - Cell 2 Phase: CX Level 3 Location: COLO 4 Trade: Gurtz Electric Start Date: 11-Jun-2025 End Date: 17-Jun-2025
Note on KE521: Activity Name: L3 UPM - Cell 2 Phase: CX Level 3 Location: COLO 4 Trade: Gurtz Electric Start Date: 25-Aug-2025 End Date: 29-Aug-2025
Note on KM521: Activity Name: L3 XFMR - Cell 2 Phase: CX Level 3 Location: COLO 4 Trade: Gurtz Electric Start Date: 02-Sep-2025 End Date: 08-Sep-2025
Note on HO524: Activity Name: L3 GEN - Cell 3 Phase: CX Level 3 Location: COLO 4 Trade: Gurtz Electric Start Date: 18-Jun-2025 End Date: 24-Jun-2025
Note on KM524: Activity Name: L3 UPM - Cell 3 Phase: CX Level 3 Location: COLO 4 Trade: Gurtz Electric Start Date: 02-Sep-2025 End Date: 08-Sep-2025
Note on KT524: Activity Name: L3 XFMR - Cell 3 Phase: CX Level 3 Location: COLO 4 Trade: Gurtz Electric Start Date: 09-Sep-2025 End Date: 15-Sep-2025
Note on HV527: Activity Name: L3 GEN - Cell 4 Phase: CX Level 3 Location: COLO 4 Trade: Gurtz Electric Start Date: 25-Jun-2025 End Date: 01-Jul-2025
Note on KM527: Activity Name: L3 UPM - Cell 4 Phase: CX Level 3 Location: COLO 4 Trade: Gurtz Electric Start Date: 02-Sep-2025 End Date: 08-Sep-2025
Note on KT527: Activity Name: L3 XFMR - Cell 4 Phase: CX Level 3 Location: COLO 4 Trade: Gurtz Electric Start Date: 09-Sep-2025 End Date: 15-Sep-2025
Note on ED530: Activity Name: L3 URS 01 - COLO 5 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 21-Mar-2025 End Date: 27-Mar-2025
Note on EY530: Activity Name: EPMS/BAS Turn-Up Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 11-Apr-2025 End Date: 11-Apr-2025
Note on ED531: Activity Name: L3 UMS 01 - COLO 5 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 21-Mar-2025 End Date: 27-Mar-2025
Note on ED532: Activity Name: L3 UMS 02 - COLO 5 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 21-Mar-2025 End Date: 27-Mar-2025
Note on EV534: Activity Name: L3 GEN - Cell 1 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on IY534: Activity Name: L3 UPM - Cell 1 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 24-Jul-2025 End Date: 30-Jul-2025
Note on JF534: Activity Name: L3 XFMR - Cell 1 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 31-Jul-2025 End Date: 06-Aug-2025
Note on FC537: Activity Name: L3 GEN - Cell 2 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 15-Apr-2025 End Date: 21-Apr-2025
Note on IY537: Activity Name: L3 UPM - Cell 2 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 24-Jul-2025 End Date: 30-Jul-2025
Note on JF537: Activity Name: L3 XFMR - Cell 2 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 31-Jul-2025 End Date: 06-Aug-2025
Note on FJ540: Activity Name: L3 GEN - Cell 3 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on JF540: Activity Name: L3 UPM - Cell 3 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 31-Jul-2025 End Date: 06-Aug-2025
Note on JM540: Activity Name: L3 XFMR - Cell 3 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 07-Aug-2025 End Date: 13-Aug-2025
Note on FQ543: Activity Name: L3 GEN - Cell 4 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 29-Apr-2025 End Date: 05-May-2025
Note on JF543: Activity Name: L3 UPM - Cell 4 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 31-Jul-2025 End Date: 06-Aug-2025
Note on JM543: Activity Name: L3 XFMR - Cell 4 Phase: CX Level 3 Location: COLO 5 Trade: Gurtz Electric Start Date: 07-Aug-2025 End Date: 13-Aug-2025
Note on DW546: Activity Name: L3 UTS / UTSR - Site Phase: CX Level 3 Location: Site Trade: Gurtz Electric Start Date: 14-Mar-2025 End Date: 20-Mar-2025
Note on BS547: Activity Name: Relocate 2 UPMs to Colo 2 Phase: UPM Location: COLO 2 Trade: Gurtz Electric Start Date: 17-Jan-2025 End Date: 20-Jan-2025
Note on BW547: Activity Name: Term Wires to Relocated UPMs (2) Phase: UPM Location: COLO 2 Trade: Gurtz Electric Start Date: 21-Jan-2025 End Date: 10-Feb-2025
Note on CR547: Activity Name: Complete L1 on Relocated UPMs Phase: UPM Location: COLO 2 Trade: Gurtz Electric Start Date: 11-Feb-2025 End Date: 11-Feb-2025
Note on BH550: Activity Name: UPM ROJ (Qty: 4) Phase: UPM Location: COLO 3 Trade: Gurtz Electric Start Date: 06-Jan-2025 End Date: 30-May-2025
Note on GY550: Activity Name: Install UPM (Total 4) Phase: UPM Location: COLO 3 Trade: Gurtz Electric Start Date: 02-Jun-2025 End Date: 11-Jun-2025
Note on HJ550: Activity Name: L1 UPM Phase: UPM Location: COLO 3 Trade: Gurtz Electric Start Date: 13-Jun-2025 End Date: 13-Jun-2025
Note on HM550: Activity Name: Complete Wire Terms Phase: UPM Location: COLO 3 Trade: Gurtz Electric Start Date: 16-Jun-2025 End Date: 04-Jul-2025
Note on BH554: Activity Name: UPM ROJ (Qty: 4) Phase: UPM Location: COLO 4 Trade: Gurtz Electric Start Date: 06-Jan-2025 End Date: 30-May-2025
Note on HI554: Activity Name: Install UPM (Total 4) Phase: UPM Location: COLO 4 Trade: Gurtz Electric Start Date: 12-Jun-2025 End Date: 23-Jun-2025
Note on HU554: Activity Name: L1 UPM Phase: UPM Location: COLO 4 Trade: Gurtz Electric Start Date: 24-Jun-2025 End Date: 24-Jun-2025
Note on HV554: Activity Name: Complete Wire Terms Phase: UPM Location: COLO 4 Trade: Gurtz Electric Start Date: 25-Jun-2025 End Date: 15-Jul-2025
Note on BH558: Activity Name: UPM ROJ (Qty: 3) Phase: UPM Location: COLO 5 Trade: Gurtz Electric Start Date: 06-Jan-2025 End Date: 30-May-2025
Note on GY558: Activity Name: Install UPM (Total 3) Phase: UPM Location: COLO 5 Trade: Gurtz Electric Start Date: 02-Jun-2025 End Date: 09-Jun-2025
Note on HG558: Activity Name: L1 UPM Phase: UPM Location: COLO 5 Trade: Gurtz Electric Start Date: 10-Jun-2025 End Date: 10-Jun-2025
Note on HH558: Activity Name: Complete Wire Terms Phase: UPM Location: COLO 5 Trade: Gurtz Electric Start Date: 11-Jun-2025 End Date: 24-Jun-2025

## CFA - Legends
Fiber |  | COLO 5 |  | COLO 2 |  | COLO 3 |  | COLO 4 |  | Yardwork |  | Exhaust System |  | CX Level 2 |  | CX Level 3 |  | UPM
[16 empty] | EE56 | EPMS/BAS Turn-Up | EE61 | Relocate 2 UPMs to Colo 2
Gurtz Electric |  | All Trades |  | All Trades |  | All - Tech |  | All - Tech |  | Gurtz Electric |  | Gurtz Electric |  | Gurtz Electric
EE60 | Pull Generator Fiber Colo 2 | ALL3 | Finishes and Signage - COLO5 Cell 1 - DH | ALL3 | Finishes and Signage - COLO2 Cell 1 - DH | T3 | Install Walls and Primer Paint - COLO3 Cell 4 - MG | T3 | Install Walls and Primer Paint - COLO4 Cell 2 - MG | EE35 | Wire pulling and termination for TCP/MSB - Colo 2 - South | EE69 | Assemble & Install Exhaust System Set (SW) | EE48 | L2 XFMR - COLO2
Gurtz Electric Telecom |  | Gurtz Electric |  | Gurtz Electric |  | All Trades |  | All Trades |  | Ralph Simpson & Crown Core |  | WALSH
ET30 | Pull, Splice, & Test (3) UTS Fiber | EE57 | Interior - L2 TCP/MSB - COLO5 Cell 1 | EE57 | Interior - L2 TCP/MSB - COLO2 Cell 1 | ALL3 | Finishes and Signage - COLO3 Cell 1 - DH | ALL3 | Finishes and Signage - COLO4 Cell 1 - DH | RC1 | Install screen wall - Colo 2 - North | W16 | (8) Sets Returned to Manufacture
WALSH |  | Gurtz Electric Telecom |  | Gurtz Electric Telecom |  | Anning - Johnson |  | Anning - Johnson
W15 | MVS Fiber Procurement | ET7 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH | ET7 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH | J36 | Door Frame Installation - COLO3 Cell 1 - ER | J7 | Ceiling Grid and Tile - COLO4 Cell 1 - DH
|  | Inspections |  | Inspections |  | Great Lakes Air Design |  | Great Lakes Air Design
|  | I-R | Pipe Testing - COLO5 Cell 3 - MG | I-R | Pipe Testing - COLO2 Cell 3 - MG | GA6 | Placing the AHU - COLO3 Cell 2 - MG | GA6 | Placing the AHU - COLO4 Cell 1 - MG
|  | Microsoft |  | Microsoft |  | Great Lakes HVAC |  | Great Lakes HVAC
|  | MS1 | Level 4 Cx - Colo 5 | MS1 | Level 4 Cx - Colo 2 | GH3 | Install DX Split Units - COLO3 Cell 2 - ER | GH3 | Install DX Split Units - COLO4 Cell 1 - ER
|  | WALSH |  |  |  | Gurtz Electric |  | Gurtz Electric
|  | W4 | Closing Construction Access Door - COLO5 Cell 4 - DH |  |  | EE63 | Interior - L1 PDUs - COLO3 Cell 1 | EE59 | Interior - L1 AHUs - COLO4 Cell 1
[6 empty] | Gurtz Electric Telecom |  | Gurtz Electric Telecom
[6 empty] | ET7 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH | ET22 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH
[6 empty] | Inspections |  | Inspections
[6 empty] | I-R | Pipe Testing - COLO3 Cell 2 - MG | I-R | Pipe Testing - COLO4 Cell 1 - MG
[6 empty] | Interior System |  | Interior System
[6 empty] | S1 | Begin HAC Assembly - COLO3 Cell 1 - DH | S1 | Begin HAC Assembly - COLO4 Cell 1 - DH
[6 empty] | Microsoft |  | Microsoft
[6 empty] | MS2 | Level 5 Cx / IST - Colo 3 | MS1 | Level 4 Cx - Colo 4
WALSH
[8 empty] | W4 | Closing Construction Access Door - COLO4 Cell 4 - DH