## Sheet1
Phase | Location | Zone | Trade | Activity Name | Color | Activity Code | Start | Finish
Yardwork | COLO 2 | South |  | Wire pulling and termination for TCP/MSB - Colo 2 - South | #FFFDA5 | EE35 | 2025-01-31 | 2025-02-20
Yardwork | COLO 2 | South |  | Install screen wall - Colo 2 - South | #D9D9D9 | RC1 | 2024-10-30 | 2024-11-26
Yardwork | COLO 2 | North |  | Install screen wall - Colo 2 - North | #D9D9D9 | RC1 | 2024-11-27 | 2024-12-26
Yardwork | COLO 5 | East |  | Install screen wall - Colo 5 - East | #D9D9D9 | RC1 | 2024-11-06 | 2024-12-04
Yardwork | COLO 5 | West |  | Install Generator Muffler - Colo 5 - West | #FFFDA5 | EE34 | 2024-12-11 | 2024-12-17
Yardwork | COLO 5 | West |  | Install screen wall - Colo 5 - West | #D9D9D9 | RC1 | 2024-12-05 | 2025-01-03
Yardwork | COLO 3 | South |  | Install screen wall - Colo 3 - South | #D9D9D9 | RC1 | 2024-11-20 | 2024-12-18
Yardwork | COLO 3 | North |  | Wire pulling and termination for TCP/MSB - Colo 3 - North | #FFFDA5 | EE35 | 2024-12-27 | 2025-01-17
Yardwork | COLO 3 | North |  | Install screen wall - Colo 3 - North | #D9D9D9 | RC1 | 2024-11-27 | 2024-12-26
Yardwork | COLO 4 | South |  | Wire pulling and termination for TCP/MSB - Colo 4 - South | #FFFDA5 | EE46 | 2025-01-06 | 2025-01-24
Yardwork | COLO 4 | South |  | Install screen wall - Colo 4 - South | #D9D9D9 | RC1 | 2024-12-05 | 2025-01-03
Yardwork | COLO 4 | North |  | Wire pulling and termination for TCP/MSB - Colo 4 - North | #FFFDA5 | EE35 | 2025-01-13 | 2025-01-31
Yardwork | COLO 4 | North |  | Install screen wall - Colo 4 - North | #D9D9D9 | RC1 | 2024-12-12 | 2025-01-10
CX Level 2 | Site | Site |  | L2 UTS / UTSR - Site | #FFFDA5 | EE47 | 2025-03-07 | 2025-03-13
CX Level 2 | COLO 2 | COLO 2 |  | L2 XFMR - COLO2 | #FFFDA5 | EE48 | 2025-02-04 | 2025-02-28
CX Level 2 | COLO 2 | COLO 2 |  | L2 GEN - COLO2 | #FFFDA5 | EE49 | 2025-02-04 | 2025-02-28
CX Level 2 | COLO 2 | COLO 2 |  | L2 UPM - COLO2 | #FFFDA5 | EE50 | 2025-02-04 | 2025-02-28
CX Level 2 | COLO 5 | COLO 5 |  | L2 UMS 01 - COLO 5 | #FFFDA5 | EE51 | 2025-01-30 | 2025-02-05
CX Level 2 | COLO 5 | COLO 5 |  | L2 URS 01 - COLO 5 | #FFFDA5 | EE53 | 2025-01-30 | 2025-02-05
CX Level 2 | COLO 5 | COLO 5 |  | L2 XFMR - COLO5 | #FFFDA5 | EE48 | 2025-01-15 | 2025-02-11
CX Level 2 | COLO 5 | COLO 5 |  | L2 GEN - COLO5 | #FFFDA5 | EE49 | 2025-01-15 | 2025-02-11
CX Level 2 | COLO 5 | COLO 5 |  | L2 UPM - COLO5 (UPM ROJ Driving) | #FFFDA5 | EE50 | 2025-01-15 | 2025-02-11
CX Level 2 | COLO 3 | COLO 3 |  | L2 UMS 03 - COLO 3 | #FFFDA5 | EE54 | 2025-03-07 | 2025-03-13
CX Level 2 | COLO 3 | COLO 3 |  | L2 UMS 04 - COLO 3 | #FFFDA5 | EE55 | 2025-03-07 | 2025-03-13
CX Level 2 | COLO 3 | COLO 3 |  | L2 XFMR - COLO3 | #FFFDA5 | EE48 | 2025-03-07 | 2025-04-03
CX Level 2 | COLO 3 | COLO 3 |  | L2 GEN - COLO3 | #FFFDA5 | EE49 | 2025-03-07 | 2025-04-03
CX Level 2 | COLO 3 | COLO 3 |  | L2 UPM - COLO3 (UPM ROJ Driving) | #FFFDA5 | EE50 | 2025-03-07 | 2025-04-03
CX Level 2 | COLO 4 | COLO 4 |  | L2 XFMR - COLO4 | #FFFDA5 | EE48 | 2025-03-07 | 2025-04-03
CX Level 2 | COLO 4 | COLO 4 |  | L2 GEN - COLO4 | #FFFDA5 | EE49 | 2025-03-07 | 2025-04-03
CX Level 2 | COLO 4 | COLO 4 |  | L2 UPM - COLO4 (UPM ROJ Driving) | #FFFDA5 | EE50 | 2025-03-07 | 2025-04-03
CX Level 3 | Site | Site |  | L3 UTS / UTSR - Site | #FFFDA5 | EE47 | 2025-03-14 | 2025-03-20
CX Level 3 | COLO 2 | Cell 1 |  | L3 GEN - Colo 2 Cell 1 | #FFFDA5 | EE49 | 2025-03-03 | 2025-03-21
CX Level 3 | COLO 2 | Cell 1 |  | L3 UPM - Colo 2 Cell 1 | #FFFDA5 | EE50 | 2025-03-03 | 2025-03-28
CX Level 3 | COLO 2 | Cell 1 |  | L3 XFMR - Colo 2 Cell 1 | #FFFDA5 | EE48 | 2025-03-03 | 2025-03-21
CX Level 3 | COLO 5 | All |  | L3 URS 01 - COLO 5 | #FFFDA5 | EE53 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 5 | All |  | L3 UMS 01 - COLO 5 | #FFFDA5 | EE51 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 5 | Cell 1 |  | L3 GEN - Cell 1 | #FFFDA5 | EE49 | 2025-02-28 | 2025-03-20
CX Level 3 | COLO 5 | Cell 1 |  | L3 UPM - Cell 1 | #FFFDA5 | EE50 | 2025-02-28 | 2025-03-27
CX Level 3 | COLO 5 | Cell 1 |  | L3 XFMR - Cell 1 | #FFFDA5 | EE48 | 2025-03-07 | 2025-03-27
CX Level 3 | COLO 3 | All |  | L3 UMS 04 - COLO 3 | #FFFDA5 | EE55 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 3 | All |  | L3 UMS 03 - COLO 3 | #FFFDA5 | EE54 | 2025-03-28 | 2025-04-03
CX Level 3 | COLO 3 | Cell 1 |  | L3 GEN - Cell 1 | #FFFDA5 | EE49 | 2025-04-04 | 2025-04-24
CX Level 3 | COLO 3 | Cell 1 |  | L3 UPM - Cell 1 | #FFFDA5 | EE50 | 2025-04-04 | 2025-05-01
CX Level 3 | COLO 3 | Cell 1 |  | L3 XFMR - Cell 1 | #FFFDA5 | EE48 | 2025-04-11 | 2025-05-01
CX Level 3 | COLO 4 | Cell 1 |  | L3 GEN - Cell 1 | #FFFDA5 | EE49 | 2025-04-04 | 2025-04-24
CX Level 3 | COLO 4 | Cell 1 |  | L3 UPM - Cell 1 | #FFFDA5 | EE50 | 2025-04-04 | 2025-05-01
CX Level 3 | COLO 4 | Cell 1 |  | L3 XFMR - Cell 1 | #FFFDA5 | EE48 | 2025-04-04 | 2025-04-24
COLO 2 | Cell 1 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | #FFFDA5 | EE29 | 2024-12-17 | 2025-01-08
COLO 2 | Cell 1 | Electrical Room |  | Finishes and Signage - COLO2 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-01-10 | 2025-01-16
COLO 2 | Cell 1 | Data Hall |  | Cable Pulling at PDU to Busway & MSB - COLO2 Cell 1 - DH | #FFFDA5 | EE17 | 2025-01-10 | 2025-01-30
COLO 2 | Cell 1 | Data Hall |  | Termination at PDU to Busway & MSB- COLO2 Cell 1 - DH | #FFFDA5 | EE18 | 2025-01-17 | 2025-02-06
COLO 2 | Cell 1 | Data Hall |  | Finishes and Signage - COLO2 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-02-07 | 2025-02-13
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 TCP/MSB - COLO2 Cell 1 | #FFFDA5 | EE57 | 2025-02-13 | 2025-02-19
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 ADP - COLO2 Cell 1 | #FFFDA5 | EE58 | 2025-01-22 | 2025-01-28
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 AHUs - COLO2 Cell 1 | #FFFDA5 | EE59 | 2025-01-22 | 2025-01-28
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 ATSs - COLO2 Cell 1 | #FFFDA5 | EE60 | 2025-01-22 | 2025-01-28
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 Busway - COLO2 Cell 1 | #FFFDA5 | EE61 | 2025-01-31 | 2025-02-06
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 UPS - COLO2 Cell 1 | #FFFDA5 | EE62 | 2025-01-31 | 2025-02-06
COLO 2 | Cell 1 | CX - L2 |  | Interior - L2 PDUs - COLO2 Cell 1 | #FFFDA5 | EE63 | 2025-01-31 | 2025-02-06
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 TCP/MSB - COLO2 Cell 1 | #FFFDA5 | EE57 | 2025-03-19 | 2025-03-25
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 UPS - COLO2 Cell 1 | #FFFDA5 | EE62 | 2025-03-26 | 2025-04-01
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 PDUs - COLO2 Cell 1 | #FFFDA5 | EE63 | 2025-03-26 | 2025-04-01
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 ADP - COLO2 Cell 1 | #FFFDA5 | EE58 | 2025-03-26 | 2025-04-01
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 ATSs - COLO2 Cell 1 | #FFFDA5 | EE60 | 2025-04-02 | 2025-04-08
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 AHUs - COLO2 Cell 1 | #FFFDA5 | EE59 | 2025-04-09 | 2025-04-22
COLO 2 | Cell 1 | CX - L3 |  | Interior - L3 Busway - COLO2 Cell 1 | #FFFDA5 | EE61 | 2025-04-23 | 2025-04-29
COLO 2 | Cell 2 | Mech Gallery |  | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | #FFFDA5 | EE35 | 2025-01-14 | 2025-01-24
COLO 2 | Cell 2 | Mech Gallery |  | Trim out MEP - COLO2 Cell 2 - MG | #FFFDA5 | EE36 | 2025-01-24 | 2025-01-31
COLO 2 | Cell 2 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | #FFFDA5 | EE29 | 2025-01-09 | 2025-01-29
COLO 2 | Cell 2 | Electrical Room |  | Finishes and Signage - COLO2 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-01-30 | 2025-02-05
COLO 2 | Cell 2 | Data Hall |  | Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH | #FFFDA5 | EE17 | 2025-01-17 | 2025-01-30
COLO 2 | Cell 2 | Data Hall |  | Termination at PDU & Busway - COLO2 Cell 2 - DH | #FFFDA5 | EE18 | 2025-01-31 | 2025-02-20
COLO 2 | Cell 2 | Data Hall |  | Finishes and Signage - COLO2 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-02-21 | 2025-02-27
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 TCP/MSB - COLO2 Cell 2 | #FFFDA5 | EE57 | 2025-02-13 | 2025-02-19
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 UPS - COLO2 Cell 2 | #FFFDA5 | EE62 | 2025-02-20 | 2025-02-26
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 PDUs - COLO2 Cell 2 | #FFFDA5 | EE63 | 2025-02-20 | 2025-02-26
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 ADP - COLO2 Cell 2 | #FFFDA5 | EE58 | 2025-02-20 | 2025-02-26
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 ATSs - COLO2 Cell 2 | #FFFDA5 | EE60 | 2025-02-27 | 2025-03-05
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 AHUs - COLO2 Cell 2 | #FFFDA5 | EE59 | 2025-03-06 | 2025-03-12
COLO 2 | Cell 2 | CX - L2 |  | Interior - L2 Busway - COLO2 Cell 2 | #FFFDA5 | EE61 | 2025-02-27 | 2025-03-05
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 TCP/MSB - COLO2 Cell 2 | #FFFDA5 | EE57 | 2025-03-19 | 2025-03-25
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 UPS - COLO2 Cell 2 | #FFFDA5 | EE62 | 2025-03-26 | 2025-04-01
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 PDUs - COLO2 Cell 2 | #FFFDA5 | EE63 | 2025-03-26 | 2025-04-01
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 ADP - COLO2 Cell 2 | #FFFDA5 | EE58 | 2025-03-26 | 2025-04-01
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 ATSs - COLO2 Cell 2 | #FFFDA5 | EE60 | 2025-04-02 | 2025-04-08
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 AHUs - COLO2 Cell 2 | #FFFDA5 | EE59 | 2025-04-09 | 2025-04-22
COLO 2 | Cell 2 | CX - L3 |  | Interior - L3 Busway - COLO2 Cell 2 | #FFFDA5 | EE61 | 2025-04-23 | 2025-04-29
COLO 2 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO2 Cell 3 - MG | #C00000 | I-R | 2025-01-24 | 2025-01-28
COLO 2 | Cell 3 | Mech Gallery |  | Install ceiling and Light Fittings - COLO2 Cell 3 - MG | #FFFDA5 | EE35 | 2025-01-28 | 2025-02-07
COLO 2 | Cell 3 | Mech Gallery |  | Trim out MEP - COLO2 Cell 3 - MG | #FFFDA5 | EE36 | 2025-02-07 | 2025-02-14
COLO 2 | Cell 3 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER | #FFFDA5 | EE29 | 2024-12-19 | 2025-01-10
COLO 2 | Cell 3 | Electrical Room |  | Finishes and Signage - COLO2 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-01-10 | 2025-01-16
COLO 2 | Cell 3 | Data Hall |  | Termination at PDU & Busway - COLO2 Cell 3 - DH | #FFFDA5 | EE18 | 2025-01-29 | 2025-02-18
COLO 2 | Cell 3 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH | #EF9E5B | ET7 | 2025-02-05 | 2025-02-18
COLO 2 | Cell 3 | Data Hall |  | Finishes and Signage - COLO2 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-02-28 | 2025-03-06
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 TCP/MSB - COLO2 Cell 3 | #FFFDA5 | EE57 | 2025-02-19 | 2025-02-25
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 UPS - COLO2 Cell 3 | #FFFDA5 | EE62 | 2025-02-26 | 2025-03-04
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 PDUs - COLO2 Cell 3 | #FFFDA5 | EE63 | 2025-02-26 | 2025-03-04
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 ADP - COLO2 Cell 3 | #FFFDA5 | EE58 | 2025-02-19 | 2025-02-25
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 ATSs - COLO2 Cell 3 | #FFFDA5 | EE60 | 2025-02-26 | 2025-03-04
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 AHUs - COLO2 Cell 3 | #FFFDA5 | EE59 | 2025-03-05 | 2025-03-11
COLO 2 | Cell 3 | CX - L2 |  | Interior - L2 Busway - COLO2 Cell 3 | #FFFDA5 | EE61 | 2025-03-05 | 2025-03-11
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 TCP/MSB - COLO2 Cell 3 | #FFFDA5 | EE57 | 2025-03-19 | 2025-03-25
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 UPS - COLO2 Cell 3 | #FFFDA5 | EE62 | 2025-03-26 | 2025-04-01
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 PDUs - COLO2 Cell 3 | #FFFDA5 | EE63 | 2025-03-26 | 2025-04-01
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 ADP - COLO2 Cell 3 | #FFFDA5 | EE58 | 2025-03-26 | 2025-04-01
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 ATSs - COLO2 Cell 3 | #FFFDA5 | EE60 | 2025-04-02 | 2025-04-08
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 AHUs - COLO2 Cell 3 | #FFFDA5 | EE59 | 2025-04-09 | 2025-04-22
COLO 2 | Cell 3 | CX - L3 |  | Interior - L3 Busway - COLO2 Cell 3 | #FFFDA5 | EE61 | 2025-04-23 | 2025-04-29
COLO 2 | Cell 4 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO2 Cell 4 - MG | #EF9E5B | ET22 | 2025-01-24 | 2025-02-07
COLO 2 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO2 Cell 4 - MG | #C00000 | I-R | 2025-02-07 | 2025-02-11
COLO 2 | Cell 4 | Mech Gallery |  | Install ceiling and Light Fittings - COLO2 Cell 4 - MG | #FFFDA5 | EE35 | 2025-02-11 | 2025-02-21
COLO 2 | Cell 4 | Mech Gallery |  | Trim out MEP - COLO2 Cell 4 - MG | #FFFDA5 | EE36 | 2025-02-21 | 2025-02-28
COLO 2 | Cell 4 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO2 Cell 4 - ER | #FFFDA5 | EE28 | 2024-12-27 | 2025-01-03
COLO 2 | Cell 4 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER | #FFFDA5 | EE29 | 2025-01-13 | 2025-01-31
COLO 2 | Cell 4 | Electrical Room |  | Finishes and Signage - COLO2 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-02-03 | 2025-02-07
COLO 2 | Cell 4 | Data Hall |  | Termination at PDU & Busway - COLO2 Cell 4 - DH | #FFFDA5 | EE18 | 2025-02-12 | 2025-03-04
COLO 2 | Cell 4 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH | #EF9E5B | ET7 | 2025-02-19 | 2025-03-04
COLO 2 | Cell 4 | Data Hall |  | Finishes and Signage - COLO2 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-03-07 | 2025-03-13
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 TCP/MSB - COLO2 Cell 4 | #FFFDA5 | EE57 | 2025-03-05 | 2025-03-11
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 UPS - COLO2 Cell 4 | #FFFDA5 | EE62 | 2025-03-12 | 2025-03-18
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 PDUs - COLO2 Cell 4 | #FFFDA5 | EE63 | 2025-03-12 | 2025-03-18
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 ADP - COLO2 Cell 4 | #FFFDA5 | EE58 | 2025-03-12 | 2025-03-18
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 ATSs - COLO2 Cell 4 | #FFFDA5 | EE60 | 2025-03-19 | 2025-03-25
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 AHUs - COLO2 Cell 4 | #FFFDA5 | EE59 | 2025-03-19 | 2025-03-25
COLO 2 | Cell 4 | CX - L2 |  | Interior - L2 Busway - COLO2 Cell 4 | #FFFDA5 | EE61 | 2025-03-19 | 2025-03-25
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 TCP/MSB - COLO2 Cell 4 | #FFFDA5 | EE57 | 2025-03-19 | 2025-03-25
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 PDUs - COLO2 Cell 4 | #FFFDA5 | EE62 | 2025-03-26 | 2025-04-01
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 ADP - COLO2 Cell 4 | #FFFDA5 | EE63 | 2025-03-26 | 2025-04-01
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 ATSs - COLO2 Cell 4 | #FFFDA5 | EE58 | 2025-04-02 | 2025-04-08
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 UPS - COLO2 Cell 4 | #FFFDA5 | EE60 | 2025-04-09 | 2025-04-15
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 AHUs - COLO2 Cell 4 | #FFFDA5 | EE59 | 2025-04-09 | 2025-04-22
COLO 2 | Cell 4 | CX - L3 |  | Interior - L3 Busway - COLO2 Cell 4 | #FFFDA5 | EE61 | 2025-04-23 | 2025-04-29
COLO 2 | All | CX - Microsoft |  | Level 4 Cx - Colo 2 | #000000 | MS1 | 2025-04-30 | 2025-06-03
COLO 2 | All | CX - Microsoft |  | Level 5 Cx / IST - Colo 2 | #000000 | MS2 | 2025-06-04 | 2025-06-05
COLO 5 | Cell 1 | Mech Gallery |  | Trim out MEP - COLO5 Cell 1 - MG | #FFFDA5 | EE36 | 2025-02-05 | 2025-02-11
COLO 5 | Cell 1 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER | #FFFDA5 | EE29 | 2024-12-24 | 2025-01-15
COLO 5 | Cell 1 | Electrical Room |  | Finishes and Signage - COLO5 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-01-13 | 2025-01-17
COLO 5 | Cell 1 | Data Hall |  | Termination at PDU & Busway- COLO5 Cell 1 - DH | #FFFDA5 | EE18 | 2025-01-27 | 2025-02-14
COLO 5 | Cell 1 | Data Hall |  | Finishes and Signage - COLO5 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-02-17 | 2025-02-21
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 TCP/MSB - COLO5 Cell 1 | #FFFDA5 | EE57 | 2025-03-04 | 2025-03-10
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 UPS - COLO5 Cell 1 | #FFFDA5 | EE62 | 2025-03-11 | 2025-03-17
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 ADP - COLO5 Cell 1 | #FFFDA5 | EE58 | 2025-03-11 | 2025-03-17
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 PDUs - COLO5 Cell 1 | #FFFDA5 | EE63 | 2025-03-18 | 2025-03-24
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 AHUs - COLO5 Cell 1 | #FFFDA5 | EE59 | 2025-03-18 | 2025-03-24
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 ATSs - COLO5 Cell 1 | #FFFDA5 | EE60 | 2025-03-18 | 2025-03-24
COLO 5 | Cell 1 | CX - L2 |  | Interior - L2 Busway - COLO5 Cell 1 | #FFFDA5 | EE61 | 2025-03-18 | 2025-03-24
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 TCP/MSB - COLO5 Cell 1 | #FFFDA5 | EE57 | 2025-03-25 | 2025-03-31
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 PDUs - COLO5 Cell 1 | #FFFDA5 | EE63 | 2025-03-25 | 2025-03-31
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 UPS - COLO5 Cell 1 | #FFFDA5 | EE62 | 2025-04-01 | 2025-04-07
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 ADP - COLO5 Cell 1 | #FFFDA5 | EE58 | 2025-03-25 | 2025-03-31
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 ATSs - COLO5 Cell 1 | #FFFDA5 | EE60 | 2025-04-01 | 2025-04-07
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 AHUs - COLO5 Cell 1 | #FFFDA5 | EE59 | 2025-03-27 | 2025-04-09
COLO 5 | Cell 1 | CX - L3 |  | Interior - L3 Busway - COLO5 Cell 1 | #FFFDA5 | EE61 | 2025-04-08 | 2025-04-14
COLO 5 | Cell 2 | Mech Gallery |  | Install ceiling and Light Fittings - COLO5 Cell 2 - MG | #FFFDA5 | EE35 | 2025-01-31 | 2025-02-11
COLO 5 | Cell 2 | Mech Gallery |  | Trim out MEP - COLO5 Cell 2 - MG | #FFFDA5 | EE36 | 2025-02-12 | 2025-02-18
COLO 5 | Cell 2 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER | #FFFDA5 | EE29 | 2025-01-16 | 2025-02-05
COLO 5 | Cell 2 | Electrical Room |  | Finishes and Signage - COLO5 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-02-24 | 2025-02-28
COLO 5 | Cell 2 | Data Hall |  | Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH | #FFFDA5 | EE18 | 2025-02-03 | 2025-02-21
COLO 5 | Cell 2 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH | #EF9E5B | ET7 | 2025-02-10 | 2025-02-21
COLO 5 | Cell 2 | Data Hall |  | Termination at PDU & Busway- COLO5 Cell 2 - DH | #FFFDA5 | EE19 | 2025-02-24 | 2025-03-14
COLO 5 | Cell 2 | Data Hall |  | Finishes and Signage - COLO5 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-03-17 | 2025-03-21
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 TCP/MSB - COLO5 Cell 2 | #FFFDA5 | EE57 | 2025-03-04 | 2025-03-10
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 UPS - COLO5 Cell 2 | #FFFDA5 | EE62 | 2025-03-11 | 2025-03-17
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 PDUs - COLO5 Cell 2 | #FFFDA5 | EE63 | 2025-03-11 | 2025-03-17
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 ADP - COLO5 Cell 2 | #FFFDA5 | EE58 | 2025-03-11 | 2025-03-17
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 AHUs - COLO5 Cell 2 | #FFFDA5 | EE59 | 2025-03-18 | 2025-03-24
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 ATSs - COLO5 Cell 2 | #FFFDA5 | EE60 | 2025-03-18 | 2025-03-24
COLO 5 | Cell 2 | CX - L2 |  | Interior - L2 Busway - COLO5 Cell 2 | #FFFDA5 | EE61 | 2025-03-18 | 2025-03-24
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 TCP/MSB - COLO5 Cell 2 | #FFFDA5 | EE57 | 2025-03-28 | 2025-04-03
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 PDUs - COLO5 Cell 2 | #FFFDA5 | EE63 | 2025-03-28 | 2025-04-03
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 ADP - COLO5 Cell 2 | #FFFDA5 | EE58 | 2025-03-28 | 2025-04-03
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 UPS - COLO5 Cell 2 | #FFFDA5 | EE62 | 2025-04-04 | 2025-04-10
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 ATSs - COLO5 Cell 2 | #FFFDA5 | EE60 | 2025-04-04 | 2025-04-10
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 AHUs - COLO5 Cell 2 | #FFFDA5 | EE59 | 2025-04-11 | 2025-04-24
COLO 5 | Cell 2 | CX - L3 |  | Interior - L3 Busway - COLO5 Cell 2 | #FFFDA5 | EE61 | 2025-04-23 | 2025-04-29
COLO 5 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO5 Cell 3 - MG | #C00000 | I-R | 2025-02-12 | 2025-02-13
COLO 5 | Cell 3 | Mech Gallery |  | Install ceiling and Light Fittings - COLO5 Cell 3 - MG | #FFFDA5 | EE35 | 2025-02-14 | 2025-02-25
COLO 5 | Cell 3 | Mech Gallery |  | Trim out MEP - COLO5 Cell 3 - MG | #FFFDA5 | EE36 | 2025-02-26 | 2025-03-04
COLO 5 | Cell 3 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO5 Cell 3 - ER | #FFFDA5 | EE28 | 2025-01-02 | 2025-01-08
COLO 5 | Cell 3 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER | #FFFDA5 | EE18 | 2025-02-06 | 2025-02-26
COLO 5 | Cell 3 | Electrical Room |  | Finishes and Signage - COLO5 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-03-24 | 2025-03-28
COLO 5 | Cell 3 | Data Hall |  | Cable Pulling at PDU & Busway- COLO5 Cell 3 - DH | #FFFDA5 | EE17 | 2025-02-17 | 2025-02-28
COLO 5 | Cell 3 | Data Hall |  | Termination at PDU & Busway - COLO5 Cell 3 - DH | #FFFDA5 | EE18 | 2025-02-24 | 2025-03-14
COLO 5 | Cell 3 | Data Hall |  | Finishes and Signage - COLO5 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 TCP/MSB - COLO5 Cell 3 | #FFFDA5 | EE57 | 2025-03-10 | 2025-03-14
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 UPS - COLO5 Cell 3 | #FFFDA5 | EE62 | 2025-03-17 | 2025-03-21
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 PDUs - COLO5 Cell 3 | #FFFDA5 | EE63 | 2025-03-17 | 2025-03-21
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 ADP - COLO5 Cell 3 | #FFFDA5 | EE58 | 2025-03-17 | 2025-03-21
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 AHUs - COLO5 Cell 3 | #FFFDA5 | EE59 | 2025-03-24 | 2025-03-28
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 ATSs - COLO5 Cell 3 | #FFFDA5 | EE60 | 2025-03-24 | 2025-03-28
COLO 5 | Cell 3 | CX - L2 |  | Interior - L2 Busway - COLO5 Cell 3 | #FFFDA5 | EE61 | 2025-03-24 | 2025-03-28
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 TCP/MSB - COLO5 Cell 3 | #FFFDA5 | EE57 | 2025-03-28 | 2025-04-03
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 PDUs - COLO5 Cell 3 | #FFFDA5 | EE63 | 2025-03-28 | 2025-04-03
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 ADP - COLO5 Cell 3 | #FFFDA5 | EE58 | 2025-03-28 | 2025-04-03
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 UPS - COLO5 Cell 3 | #FFFDA5 | EE62 | 2025-04-04 | 2025-04-10
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 ATSs - COLO5 Cell 3 | #FFFDA5 | EE60 | 2025-04-04 | 2025-04-10
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 AHUs - COLO5 Cell 3 | #FFFDA5 | EE59 | 2025-04-04 | 2025-04-17
COLO 5 | Cell 3 | CX - L3 |  | Interior - L3 Busway - COLO5 Cell 3 | #FFFDA5 | EE61 | 2025-04-16 | 2025-04-22
COLO 5 | Cell 4 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO5 Cell 4 - MG | #EF9E5B | ET22 | 2025-02-12 | 2025-02-25
COLO 5 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO5 Cell 4 - MG | #C00000 | I-R | 2025-02-26 | 2025-02-27
COLO 5 | Cell 4 | Mech Gallery |  | Install ceiling and Light Fittings - COLO5 Cell 4 - MG | #FFFDA5 | EE35 | 2025-02-28 | 2025-03-11
COLO 5 | Cell 4 | Mech Gallery |  | Trim out MEP - COLO5 Cell 4 - MG | #FFFDA5 | EE36 | 2025-03-12 | 2025-03-18
COLO 5 | Cell 4 | Electrical Room |  | Installation of ADP & ATS - COLO5 Cell 4 - ER | #FFFDA5 | EE27 | 2025-01-07 | 2025-01-13
COLO 5 | Cell 4 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO5 Cell 4 - ER | #FFFDA5 | EE28 | 2025-01-09 | 2025-01-15
COLO 5 | Cell 4 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER | #FFFDA5 | EE17 | 2025-02-27 | 2025-03-19
COLO 5 | Cell 4 | Electrical Room |  | Finishes and Signage - COLO5 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 4 | Data Hall |  | Closing Construction Access Door - COLO5 Cell 4 - DH | #04A261 | W4 | 2025-03-03 | 2025-03-21
COLO 5 | Cell 4 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH | #EF9E5B | ET7 | 2025-03-10 | 2025-03-21
COLO 5 | Cell 4 | Data Hall |  | Termination at PDU & Busway - COLO5 Cell 4 - DH | #FFFDA5 | EE18 | 2025-03-17 | 2025-04-04
COLO 5 | Cell 4 | Data Hall |  | Finishes and Signage - COLO5 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-04-14 | 2025-04-18
COLO 5 | Cell 4 | CX - L1 |  | Interior - L1 PDUs - COLO5 Cell 4 | #FFFDA5 | EE63 | 2025-03-03 | 2025-03-03
COLO 5 | Cell 4 | CX - L1 |  | Interior - L1 ATSs - COLO5 Cell 4 | #FFFDA5 | EE59 | 2025-01-14 | 2025-01-14
COLO 5 | Cell 4 | CX - L1 |  | Interior - L1 Busway - COLO5 Cell 4 | #FFFDA5 | EE61 | 2025-01-14 | 2025-01-14
COLO 5 | Cell 4 | CX - L1 |  | Interior - L1 ADP - COLO5 Cell 4 | #FFFDA5 | EE58 | 2025-01-14 | 2025-01-14
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 TCP/MSB - COLO5 Cell 4 | #FFFDA5 | EE57 | 2025-03-20 | 2025-03-26
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 UPS - COLO5 Cell 4 | #FFFDA5 | EE62 | 2025-03-27 | 2025-04-02
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 PDUs - COLO5 Cell 4 | #FFFDA5 | EE63 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 ADP - COLO5 Cell 4 | #FFFDA5 | EE58 | 2025-03-24 | 2025-03-28
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 AHUs - COLO5 Cell 4 | #FFFDA5 | EE59 | 2025-03-24 | 2025-03-28
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 ATSs - COLO5 Cell 4 | #FFFDA5 | EE60 | 2025-03-24 | 2025-03-28
COLO 5 | Cell 4 | CX - L2 |  | Interior - L2 Busway - COLO5 Cell 4 | #FFFDA5 | EE61 | 2025-04-03 | 2025-04-09
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 TCP/MSB - COLO5 Cell 4 | #FFFDA5 | EE57 | 2025-03-28 | 2025-04-03
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 PDUs - COLO5 Cell 4 | #FFFDA5 | EE63 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 ADP - COLO5 Cell 4 | #FFFDA5 | EE58 | 2025-04-04 | 2025-04-10
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 ATSs - COLO5 Cell 4 | #FFFDA5 | EE60 | 2025-04-11 | 2025-04-17
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 UPS - COLO5 Cell 4 | #FFFDA5 | EE62 | 2025-04-11 | 2025-04-17
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 AHUs - COLO5 Cell 4 | #FFFDA5 | EE59 | 2025-04-04 | 2025-04-17
COLO 5 | Cell 4 | CX - L3 |  | Interior - L3 Busway - COLO5 Cell 4 | #FFFDA5 | EE61 | 2025-04-18 | 2025-04-24
COLO 5 | All | CX - Microsoft |  | Level 4 Cx - Colo 5 | #000000 | MS1 | 2025-04-30 | 2025-06-03
COLO 5 | All | CX - Microsoft |  | Level 5 Cx / IST - Colo 5 | #000000 | MS2 | 2025-06-04 | 2025-06-05
COLO 3 | Cell 1 | Mech Gallery |  | Install ceiling and Light Fittings - COLO3 Cell 1 - MG | #FFFDA5 | EE35 | 2025-01-28 | 2025-02-07
COLO 3 | Cell 1 | Mech Gallery |  | Trim out MEP - COLO3 Cell 1 - MG | #FFFDA5 | EE36 | 2025-02-07 | 2025-02-14
COLO 3 | Cell 1 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO3 Cell 1 - ER | #FFFDA5 | EE28 | 2025-01-06 | 2025-01-10
COLO 3 | Cell 1 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER | #FFFDA5 | EE29 | 2025-01-13 | 2025-01-31
COLO 3 | Cell 1 | Electrical Room |  | Installation of UPS Equipment - COLO3 Cell 1 - ER | #FFFDA5 | EE23 | 2025-02-03 | 2025-02-07
COLO 3 | Cell 1 | Electrical Room |  | Door Frame Installation - COLO3 Cell 1 - ER | #3399FF | J36 | 2025-02-10 | 2025-02-14
COLO 3 | Cell 1 | Electrical Room |  | Finishes and Signage - COLO3 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-02-17 | 2025-02-21
COLO 3 | Cell 1 | Data Hall |  | Install PDU's - COLO3 Cell 1 - DH | #FFFDA5 | EE7 | 2025-01-27 | 2025-01-31
COLO 3 | Cell 1 | Data Hall |  | Begin HAC Assembly - COLO3 Cell 1 - DH | #FED7E8 | S1 | 2025-01-27 | 2025-01-31
COLO 3 | Cell 1 | Data Hall |  | HAC install and Rise - COLO3 Cell 1 - DH | #FED7E8 | S2 | 2025-02-03 | 2025-02-07
COLO 3 | Cell 1 | Data Hall |  | Install Busway - COLO3 Cell 1 - DH | #FFFDA5 | EE10 | 2025-01-29 | 2025-02-04
COLO 3 | Cell 1 | Data Hall |  | Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH | #FFFDA5 | EE17 | 2025-02-03 | 2025-02-21
COLO 3 | Cell 1 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH | #EF9E5B | ET7 | 2025-02-10 | 2025-02-21
COLO 3 | Cell 1 | Data Hall |  | Termination at PDU & Busway- COLO3 Cell 1 - DH | #FFFDA5 | EE18 | 2025-02-10 | 2025-02-28
COLO 3 | Cell 1 | Data Hall |  | Finishes and Signage - COLO3 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-03-03 | 2025-03-07
COLO 3 | Cell 1 | CX - L1 |  | Interior - L1 PDUs - COLO3 Cell 1 | #FFFDA5 | EE63 | 2025-02-03 | 2025-02-03
COLO 3 | Cell 1 | CX - L1 |  | Interior - L1 UPS - COLO3 Cell 1 | #FFFDA5 | EE62 | 2025-02-10 | 2025-02-10
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 TCP/MSB - COLO3 Cell 1 | #FFFDA5 | EE57 | 2025-03-18 | 2025-03-24
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 UPS - COLO3 Cell 1 | #FFFDA5 | EE62 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 PDUs - COLO3 Cell 1 | #FFFDA5 | EE63 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 ADP - COLO3 Cell 1 | #FFFDA5 | EE58 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 ATSs - COLO3 Cell 1 | #FFFDA5 | EE60 | 2025-04-01 | 2025-04-07
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 Busway - COLO3 Cell 1 | #FFFDA5 | EE61 | 2025-04-01 | 2025-04-07
COLO 3 | Cell 1 | CX - L2 |  | Interior - L2 AHUs - COLO3 Cell 1 | #FFFDA5 | EE59 | 2025-04-08 | 2025-04-14
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 TCP/MSB - COLO3 Cell 1 | #FFFDA5 | EE57 | 2025-05-02 | 2025-05-08
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 UPS - COLO3 Cell 1 | #FFFDA5 | EE62 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 PDUs - COLO3 Cell 1 | #FFFDA5 | EE63 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 ADP - COLO3 Cell 1 | #FFFDA5 | EE58 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 ATSs - COLO3 Cell 1 | #FFFDA5 | EE60 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 AHUs - COLO3 Cell 1 | #FFFDA5 | EE59 | 2025-05-05 | 2025-05-16
COLO 3 | Cell 1 | CX - L3 |  | Interior - L3 Busway - COLO3 Cell 1 | #FFFDA5 | EE61 | 2025-05-16 | 2025-05-22
COLO 3 | Cell 2 | Mech Gallery |  | Placing the AHU - COLO3 Cell 2 - MG | #CFE741 | GA6 | 2025-01-22 | 2025-01-24
COLO 3 | Cell 2 | Mech Gallery |  | Post Wall Overhead MEP - COLO3 Cell 2 - MG | #FFFDA5 | EE70 | 2025-01-15 | 2025-02-04
COLO 3 | Cell 2 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO3 Cell 2 - MG | #EF9E5B | ET22 | 2025-01-24 | 2025-02-07
COLO 3 | Cell 2 | Mech Gallery | Inspections | Pipe Testing - COLO3 Cell 2 - MG | #C00000 | I-R | 2025-02-07 | 2025-02-11
COLO 3 | Cell 2 | Mech Gallery |  | Install ceiling and Light Fittings - COLO3 Cell 2 - MG | #FFFDA5 | EE35 | 2025-02-11 | 2025-02-21
COLO 3 | Cell 2 | Mech Gallery |  | Trim out MEP - COLO3 Cell 2 - MG | #FFFDA5 | EE36 | 2025-02-21 | 2025-02-28
COLO 3 | Cell 2 | Electrical Room |  | Install DX Split Units - COLO3 Cell 2 - ER | #987655 | GH3 | 2025-01-10 | 2025-01-16
COLO 3 | Cell 2 | Electrical Room |  | Installation of ADP & ATS - COLO3 Cell 2 - ER | #FFFDA5 | EE27 | 2025-01-13 | 2025-01-17
COLO 3 | Cell 2 | Electrical Room |  | Installation of UPS Equipment - COLO3 Cell 2 - ER | #FFFDA5 | EE23 | 2025-01-13 | 2025-01-17
COLO 3 | Cell 2 | Electrical Room |  | Installation of TCP/MSB - COLO3 Cell 2 - ER | #FFFDA5 | EE71 | 2025-01-13 | 2025-01-17
COLO 3 | Cell 2 | Electrical Room |  | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | #FFFDA5 | EE72 | 2025-01-09 | 2025-01-22
COLO 3 | Cell 2 | Electrical Room |  | Door Frame Installation - COLO3 Cell 2 - ER | #3399FF | J36 | 2025-01-20 | 2025-01-24
COLO 3 | Cell 2 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO3 Cell 2 - ER | #FFFDA5 | EE28 | 2025-01-15 | 2025-01-21
COLO 3 | Cell 2 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER | #FFFDA5 | EE29 | 2025-02-03 | 2025-02-21
COLO 3 | Cell 2 | Electrical Room |  | Finishes and Signage - COLO3 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-02-24 | 2025-02-28
COLO 3 | Cell 2 | Data Hall |  | Ceiling Grid and Tile - COLO3 Cell 2 - DH | #3399FF | J7 | 2025-01-20 | 2025-01-24
COLO 3 | Cell 2 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH | #FFFDA5 | EE73 | 2025-01-27 | 2025-02-07
COLO 3 | Cell 2 | Data Hall |  | Install PDU's - COLO3 Cell 2 - DH | #FFFDA5 | EE7 | 2025-02-10 | 2025-02-14
COLO 3 | Cell 2 | Data Hall |  | Begin HAC Assembly - COLO3 Cell 2 - DH | #FED7E8 | S1 | 2025-02-10 | 2025-02-14
COLO 3 | Cell 2 | Data Hall |  | Install Busway - COLO3 Cell 2 - DH | #FFFDA5 | EE10 | 2025-02-12 | 2025-02-18
COLO 3 | Cell 2 | Data Hall |  | HAC install and Rise - COLO3 Cell 2 - DH | #FED7E8 | S2 | 2025-02-17 | 2025-02-21
COLO 3 | Cell 2 | Data Hall |  | Cable Pulling at PDU & Busway- COLO3 Cell 2 - DH | #FFFDA5 | EE17 | 2025-02-17 | 2025-02-28
COLO 3 | Cell 2 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 2 - DH | #EF9E5B | ET7 | 2025-02-24 | 2025-03-07
COLO 3 | Cell 2 | Data Hall |  | Termination at PDU & Busway - COLO3 Cell 2 - DH | #FFFDA5 | EE18 | 2025-02-24 | 2025-03-14
COLO 3 | Cell 2 | Data Hall |  | Finishes and Signage - COLO3 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-03-10 | 2025-03-14
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 AHUs - COLO3 Cell 2 | #FFFDA5 | EE59 | 2025-01-22 | 2025-01-22
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 TCP/MSB - COLO3 Cell 2 | #FFFDA5 | EE57 | 2025-01-20 | 2025-01-20
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 ATSs - COLO3 Cell 2 | #FFFDA5 | EE60 | 2025-01-20 | 2025-01-20
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 Busway - COLO3 Cell 2 | #FFFDA5 | EE61 | 2025-01-20 | 2025-01-20
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 ADP - COLO3 Cell 2 | #FFFDA5 | EE58 | 2025-01-20 | 2025-01-20
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 PDUs - COLO3 Cell 2 | #FFFDA5 | EE63 | 2025-02-17 | 2025-02-17
COLO 3 | Cell 2 | CX - L1 |  | Interior - L1 UPS - COLO3 Cell 2 | #FFFDA5 | EE62 | 2025-02-11 | 2025-02-11
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 TCP/MSB - COLO3 Cell 2 | #FFFDA5 | EE57 | 2025-03-18 | 2025-03-24
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 UPS - COLO3 Cell 2 | #FFFDA5 | EE62 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 PDUs - COLO3 Cell 2 | #FFFDA5 | EE63 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 ADP - COLO3 Cell 2 | #FFFDA5 | EE58 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 ATSs - COLO3 Cell 2 | #FFFDA5 | EE60 | 2025-04-01 | 2025-04-07
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 Busway - COLO3 Cell 2 | #FFFDA5 | EE61 | 2025-04-01 | 2025-04-07
COLO 3 | Cell 2 | CX - L2 |  | Interior - L2 AHUs - COLO3 Cell 2 | #FFFDA5 | EE59 | 2025-04-08 | 2025-04-14
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 TCP/MSB - COLO3 Cell 2 | #FFFDA5 | EE57 | 2025-05-02 | 2025-05-08
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 UPS - COLO3 Cell 2 | #FFFDA5 | EE62 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 ADP - COLO3 Cell 2 | #FFFDA5 | EE58 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 PDUs - COLO3 Cell 2 | #FFFDA5 | EE63 | 2025-05-16 | 2025-05-22
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 ATSs - COLO3 Cell 2 | #FFFDA5 | EE60 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 AHUs - COLO3 Cell 2 | #FFFDA5 | EE59 | 2025-05-05 | 2025-05-16
COLO 3 | Cell 2 | CX - L3 |  | Interior - L3 Busway - COLO3 Cell 2 | #FFFDA5 | EE61 | 2025-05-16 | 2025-05-22
COLO 3 | Cell 3 | Mech Gallery |  | Post Wall Overhead MEP - COLO3 Cell 3 - MG | #FFFDA5 | EE70 | 2025-01-29 | 2025-02-18
COLO 3 | Cell 3 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO3 Cell 3 - MG | #EF9E5B | ET22 | 2025-02-07 | 2025-02-21
COLO 3 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO3 Cell 3 - MG | #C00000 | I-R | 2025-02-21 | 2025-02-25
COLO 3 | Cell 3 | Mech Gallery |  | Install ceiling and Light Fittings - COLO3 Cell 3 - MG | #FFFDA5 | EE35 | 2025-02-25 | 2025-03-07
COLO 3 | Cell 3 | Mech Gallery |  | Trim out MEP - COLO3 Cell 3 - MG | #FFFDA5 | EE36 | 2025-03-07 | 2025-03-14
COLO 3 | Cell 3 | Electrical Room |  | Install DX Split Units - COLO3 Cell 3 - ER | #987655 | GH3 | 2025-01-24 | 2025-01-30
COLO 3 | Cell 3 | Electrical Room |  | Installation of ADP & ATS - COLO3 Cell 3 - ER | #FFFDA5 | EE27 | 2025-01-27 | 2025-01-31
COLO 3 | Cell 3 | Electrical Room |  | Installation of UPS Equipment - COLO3 Cell 3 - ER | #FFFDA5 | EE23 | 2025-01-27 | 2025-01-31
COLO 3 | Cell 3 | Electrical Room |  | Installation of TCP/MSB - COLO3 Cell 3 - ER | #FFFDA5 | EE71 | 2025-01-27 | 2025-01-31
COLO 3 | Cell 3 | Electrical Room |  | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | #FFFDA5 | EE72 | 2025-01-23 | 2025-02-05
COLO 3 | Cell 3 | Electrical Room |  | Door Frame Installation - COLO3 Cell 3 - ER | #3399FF | J36 | 2025-02-03 | 2025-02-07
COLO 3 | Cell 3 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO3 Cell 3 - ER | #FFFDA5 | EE28 | 2025-01-29 | 2025-02-04
COLO 3 | Cell 3 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER | #FFFDA5 | EE29 | 2025-02-24 | 2025-03-14
COLO 3 | Cell 3 | Electrical Room |  | Finishes and Signage - COLO3 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-03-12 | 2025-03-18
COLO 3 | Cell 3 | Data Hall |  | Ceiling Grid and Tile - COLO3 Cell 3 - DH | #3399FF | J7 | 2025-02-03 | 2025-02-07
COLO 3 | Cell 3 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH | #FFFDA5 | EE73 | 2025-02-10 | 2025-02-21
COLO 3 | Cell 3 | Data Hall |  | Install PDU's - COLO3 Cell 3 - DH | #FFFDA5 | EE7 | 2025-02-24 | 2025-02-28
COLO 3 | Cell 3 | Data Hall |  | Begin HAC Assembly - COLO3 Cell 3 - DH | #FED7E8 | S1 | 2025-02-24 | 2025-02-28
COLO 3 | Cell 3 | Data Hall |  | Install Busway - COLO3 Cell 3 - DH | #FFFDA5 | EE10 | 2025-02-26 | 2025-03-04
COLO 3 | Cell 3 | Data Hall |  | HAC install and Rise - COLO3 Cell 3 - DH | #FED7E8 | S2 | 2025-03-03 | 2025-03-07
COLO 3 | Cell 3 | Data Hall |  | Cable Pulling at PDU & Busway- COLO3 Cell 3 - DH | #FFFDA5 | EE17 | 2025-03-03 | 2025-03-14
COLO 3 | Cell 3 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 3 - DH | #EF9E5B | ET7 | 2025-03-10 | 2025-03-21
COLO 3 | Cell 3 | Data Hall |  | Termination at PDU & Busway - COLO3 Cell 3 - DH | #FFFDA5 | EE18 | 2025-03-17 | 2025-04-04
COLO 3 | Cell 3 | Data Hall |  | Finishes and Signage - COLO3 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 AHUs - COLO3 Cell 3 | #FFFDA5 | EE59 | 2025-02-05 | 2025-02-05
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 TCP/MSB - COLO3 Cell 3 | #FFFDA5 | EE57 | 2025-02-03 | 2025-02-03
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 ATSs - COLO3 Cell 3 | #FFFDA5 | EE60 | 2025-02-03 | 2025-02-03
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 Busway - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-02-03 | 2025-02-03
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 ADP - COLO3 Cell 3 | #FFFDA5 | EE58 | 2025-02-03 | 2025-02-03
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 PDUs - COLO3 Cell 3 | #FFFDA5 | EE63 | 2025-03-03 | 2025-03-03
COLO 3 | Cell 3 | CX - L1 |  | Interior - L1 UPS - COLO3 Cell 3 | #FFFDA5 | EE62 | 2025-02-12 | 2025-02-12
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 TCP/MSB - COLO3 Cell 3 | #FFFDA5 | EE57 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 ATSs - COLO3 Cell 3 | #FFFDA5 | EE60 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 ADP - COLO3 Cell 3 | #FFFDA5 | EE58 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 UPS - COLO3 Cell 3 | #FFFDA5 | EE62 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 PDUs - COLO3 Cell 3 | #FFFDA5 | EE63 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 Busway - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-04-07 | 2025-04-11
COLO 3 | Cell 3 | CX - L2 |  | Interior - L2 AHUs - COLO3 Cell 3 | #FFFDA5 | EE59 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 TCP/MSB - COLO3 Cell 3 | #FFFDA5 | EE57 | 2025-05-02 | 2025-05-08
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 UPS - COLO3 Cell 3 | #FFFDA5 | EE62 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 PDUs - COLO3 Cell 3 | #FFFDA5 | EE63 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 ADP - COLO3 Cell 3 | #FFFDA5 | EE58 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 ATSs - COLO3 Cell 3 | #FFFDA5 | EE60 | 2025-05-12 | 2025-05-16
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 Busway - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-05-12 | 2025-05-16
COLO 3 | Cell 3 | CX - L3 |  | Interior - L3 AHUs - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-05-05 | 2025-05-16
COLO 3 | Cell 4 | Mech Gallery |  | Deliver AHU into Mech. Gallery - COLO3 Cell 4 - MG | #CFE741 | GA12 | 2025-01-27 | 2025-01-28
COLO 3 | Cell 4 | Mech Gallery |  | Install Walls and Primer Paint - COLO3 Cell 4 - MG | #D6F2FF | T3 | 2025-01-29 | 2025-02-11
COLO 3 | Cell 4 | Mech Gallery |  | Layout Ceiling and install Pencile Rod - COLO3 Cell 4 - MG | #3399FF | J9 | 2025-02-12 | 2025-02-12
COLO 3 | Cell 4 | Mech Gallery |  | Placing the AHU - COLO3 Cell 4 - MG | #CFE741 | GA6 | 2025-02-19 | 2025-02-21
COLO 3 | Cell 4 | Mech Gallery |  | Post Wall Overhead MEP - COLO3 Cell 4 - MG | #FFFDA5 | EE70 | 2025-02-12 | 2025-03-04
COLO 3 | Cell 4 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO3 Cell 4 - MG | #EF9E5B | ET22 | 2025-02-21 | 2025-03-07
COLO 3 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO3 Cell 4 - MG | #C00000 | I-R | 2025-03-07 | 2025-03-11
COLO 3 | Cell 4 | Mech Gallery |  | Install ceiling and Light Fittings - COLO3 Cell 4 - MG | #FFFDA5 | EE35 | 2025-03-11 | 2025-03-21
COLO 3 | Cell 4 | Mech Gallery |  | Trim out MEP - COLO3 Cell 4 - MG | #FFFDA5 | EE36 | 2025-03-21 | 2025-03-28
COLO 3 | Cell 4 | Electrical Room |  | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 4 - ER | #FFFDA5 | EE1 | 2025-01-21 | 2025-02-03
COLO 3 | Cell 4 | Electrical Room |  | Install Ceiling - COLO3 Cell 4 - ER | #3399FF | J17 | 2025-02-04 | 2025-02-06
COLO 3 | Cell 4 | Electrical Room |  | Install DX Split Units - COLO3 Cell 4 - ER | #987655 | GH3 | 2025-02-07 | 2025-02-13
COLO 3 | Cell 4 | Electrical Room |  | Installation of ADP & ATS - COLO3 Cell 4 - ER | #FFFDA5 | EE27 | 2025-02-10 | 2025-02-14
COLO 3 | Cell 4 | Electrical Room |  | Installation of UPS Equipment - COLO3 Cell 4 - ER | #FFFDA5 | EE23 | 2025-02-10 | 2025-02-14
COLO 3 | Cell 4 | Electrical Room |  | Installation of TCP/MSB - COLO3 Cell 4 - ER | #FFFDA5 | EE71 | 2025-02-10 | 2025-02-14
COLO 3 | Cell 4 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO3 Cell 4 - ER | #FFFDA5 | EE28 | 2025-02-12 | 2025-02-18
COLO 3 | Cell 4 | Electrical Room |  | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | #FFFDA5 | EE72 | 2025-02-06 | 2025-02-19
COLO 3 | Cell 4 | Electrical Room |  | Door Frame Installation - COLO3 Cell 4 - ER | #3399FF | J36 | 2025-02-17 | 2025-02-21
COLO 3 | Cell 4 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER | #FFFDA5 | EE29 | 2025-03-17 | 2025-04-04
COLO 3 | Cell 4 | Electrical Room |  | Finishes and Signage - COLO3 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-04-02 | 2025-04-08
COLO 3 | Cell 4 | Data Hall |  | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 4 - DH | #FFFDA5 | EE74 | 2025-01-13 | 2025-01-28
COLO 3 | Cell 4 | Data Hall |  | Security Screen Installation - COLO3 Cell 4 - DH | #3399FF | J6 | 2025-02-12 | 2025-02-14
COLO 3 | Cell 4 | Data Hall |  | Ceiling Grid and Tile - COLO3 Cell 4 - DH | #3399FF | J7 | 2025-02-17 | 2025-02-21
COLO 3 | Cell 4 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 4 - DH | #FFFDA5 | EE73 | 2025-02-24 | 2025-03-07
COLO 3 | Cell 4 | Data Hall |  | Install PDU's - COLO3 Cell 4 - DH | #FFFDA5 | EE7 | 2025-03-10 | 2025-03-14
COLO 3 | Cell 4 | Data Hall |  | Begin HAC Assembly - COLO3 Cell 4 - DH | #FED7E8 | S1 | 2025-03-10 | 2025-03-14
COLO 3 | Cell 4 | Data Hall |  | Install Busway - COLO3 Cell 4 - DH | #FFFDA5 | EE10 | 2025-03-12 | 2025-03-18
COLO 3 | Cell 4 | Data Hall |  | HAC install and Rise - COLO3 Cell 4 - DH | #FED7E8 | S2 | 2025-03-17 | 2025-03-21
COLO 3 | Cell 4 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH | #EF9E5B | ET7 | 2025-03-24 | 2025-04-04
COLO 3 | Cell 4 | Data Hall |  | Cable Pulling at PDU & Busway- COLO3 Cell 4 - DH | #FFFDA5 | EE17 | 2025-03-17 | 2025-03-28
COLO 3 | Cell 4 | Data Hall |  | Termination at PDU & Busway - COLO3 Cell 4 - DH | #FFFDA5 | EE18 | 2025-04-07 | 2025-04-25
COLO 3 | Cell 4 | Data Hall |  | Finishes and Signage - COLO3 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-04-21 | 2025-04-25
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 AHUs - COLO3 Cell 4 | #FFFDA5 | EE61 | 2025-02-19 | 2025-02-19
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 TCP/MSB - COLO3 Cell 4 | #FFFDA5 | EE57 | 2025-02-17 | 2025-02-17
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 ATSs - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-02-17 | 2025-02-17
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 Busway - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-02-17 | 2025-02-17
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 ADP - COLO3 Cell 4 | #FFFDA5 | EE58 | 2025-02-17 | 2025-02-17
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 UPS - COLO3 Cell 4 | #FFFDA5 | EE62 | 2025-02-12 | 2025-02-12
COLO 3 | Cell 4 | CX - L1 |  | Interior - L1 PDUs - COLO3 Cell 4 | #FFFDA5 | EE63 | 2025-03-17 | 2025-03-17
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 TCP/MSB - COLO3 Cell 4 | #FFFDA5 | EE57 | 2025-04-07 | 2025-04-11
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 UPS - COLO3 Cell 4 | #FFFDA5 | EE62 | 2025-04-14 | 2025-04-18
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 ATSs - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-04-14 | 2025-04-18
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 Busway - COLO3 Cell 4 | #FFFDA5 | EE61 | 2025-04-21 | 2025-04-25
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 ADP - COLO3 Cell 4 | #FFFDA5 | EE58 | 2025-04-21 | 2025-04-25
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 PDUs - COLO3 Cell 4 | #FFFDA5 | EE63 | 2025-04-28 | 2025-05-02
COLO 3 | Cell 4 | CX - L2 |  | Interior - L2 AHUs - COLO3 Cell 4 | #FFFDA5 | EE59 | 2025-04-28 | 2025-05-02
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 TCP/MSB - COLO3 Cell 4 | #FFFDA5 | EE57 | 2025-05-02 | 2025-05-08
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 PDUs - COLO3 Cell 4 | #FFFDA5 | EE63 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 ADP - COLO3 Cell 4 | #FFFDA5 | EE58 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 AHUs - COLO3 Cell 4 | #FFFDA5 | EE59 | 2025-05-05 | 2025-05-16
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 ATSs - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-05-12 | 2025-05-16
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 UPS - COLO3 Cell 4 | #FFFDA5 | EE62 | 2025-05-09 | 2025-05-15
COLO 3 | Cell 4 | CX - L3 |  | Interior - L3 Busway - COLO3 Cell 4 | #FFFDA5 | EE61 | 2025-05-19 | 2025-05-23
COLO 3 | All | CX - Microsoft |  | Level 4 Cx - Colo 3 | #000000 | MS1 | 2025-05-27 | 2025-06-30
COLO 3 | All | CX - Microsoft |  | Level 5 Cx / IST - Colo 3 | #000000 | MS2 | 2025-07-01 | 2025-07-02
COLO 4 | Cell 1 | Mech Gallery |  | Placing the AHU - COLO4 Cell 1 - MG | #CFE741 | GA6 | 2025-01-22 | 2025-01-24
COLO 4 | Cell 1 | Mech Gallery |  | Post Wall Overhead MEP - COLO4 Cell 1 - MG | #FFFDA5 | EE70 | 2025-01-15 | 2025-02-04
COLO 4 | Cell 1 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO4 Cell 1 - MG | #FFFDA5 | EE1 | 2025-01-24 | 2025-02-07
COLO 4 | Cell 1 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 1 - MG | #C00000 | I-R | 2025-02-07 | 2025-02-11
COLO 4 | Cell 1 | Mech Gallery |  | Install ceiling and Light Fittings - COLO4 Cell 1 - MG | #FFFDA5 | EE35 | 2025-02-11 | 2025-02-21
COLO 4 | Cell 1 | Mech Gallery |  | Trim out MEP - COLO4 Cell 1 - MG | #FFFDA5 | EE36 | 2025-02-21 | 2025-02-28
COLO 4 | Cell 1 | Electrical Room |  | Installation of ADP & ATS - COLO4 Cell 1 - ER | #FFFDA5 | EE27 | 2025-01-07 | 2025-01-13
COLO 4 | Cell 1 | Electrical Room |  | Installation of UPS Equipment - COLO4 Cell 1 - ER | #FFFDA5 | EE23 | 2024-12-24 | 2024-12-31
COLO 4 | Cell 1 | Electrical Room |  | Installation of TCP/MSB - COLO4 Cell 1 - ER | #FFFDA5 | EE71 | 2025-01-07 | 2025-01-13
COLO 4 | Cell 1 | Electrical Room |  | Install DX Split Units - COLO4 Cell 1 - ER | #987655 | GH3 | 2024-12-23 | 2024-12-30
COLO 4 | Cell 1 | Electrical Room |  | Below Ceiling MEP Rough In - COLO4 Cell 1 - ER | #FFFDA5 | EE72 | 2024-12-20 | 2025-01-06
COLO 4 | Cell 1 | Electrical Room |  | Door Frame Installation - COLO4 Cell 1 - ER | #3399FF | J36 | 2025-01-03 | 2025-01-09
COLO 4 | Cell 1 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO4 Cell 1 - ER | #FFFDA5 | EE28 | 2025-01-09 | 2025-01-15
COLO 4 | Cell 1 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER | #FFFDA5 | EE29 | 2025-01-16 | 2025-02-05
COLO 4 | Cell 1 | Electrical Room |  | Finishes and Signage - COLO4 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-02-03 | 2025-02-07
COLO 4 | Cell 1 | Data Hall |  | Ceiling Grid and Tile - COLO4 Cell 1 - DH | #3399FF | J7 | 2025-01-20 | 2025-01-24
COLO 4 | Cell 1 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 1 - DH | #FFFDA5 | EE73 | 2025-01-27 | 2025-02-07
COLO 4 | Cell 1 | Data Hall |  | Install PDU's - COLO4 Cell 1 - DH | #FFFDA5 | EE7 | 2025-02-10 | 2025-02-14
COLO 4 | Cell 1 | Data Hall |  | Begin HAC Assembly - COLO4 Cell 1 - DH | #FED7E8 | S1 | 2025-02-10 | 2025-02-14
COLO 4 | Cell 1 | Data Hall |  | Install Busway - COLO4 Cell 1 - DH | #FFFDA5 | EE10 | 2025-02-12 | 2025-02-18
COLO 4 | Cell 1 | Data Hall |  | HAC install and Rise - COLO4 Cell 1 - DH | #FED7E8 | S2 | 2025-02-17 | 2025-02-21
COLO 4 | Cell 1 | Data Hall |  | Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH | #FFFDA5 | EE17 | 2025-02-17 | 2025-03-07
COLO 4 | Cell 1 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH | #EF9E5B | ET22 | 2025-02-24 | 2025-03-07
COLO 4 | Cell 1 | Data Hall |  | Termination at PDU & Busway- COLO4 Cell 1 - DH | #FFFDA5 | EE18 | 2025-02-24 | 2025-03-14
COLO 4 | Cell 1 | Data Hall |  | Finishes and Signage - COLO4 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-03-17 | 2025-03-21
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 AHUs - COLO4 Cell 1 | #FFFDA5 | EE59 | 2025-01-22 | 2025-01-22
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 UPS - COLO4 Cell 1 | #FFFDA5 | EE62 | 2025-01-02 | 2025-01-02
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 TCP/MSB - COLO4 Cell 1 | #FFFDA5 | EE57 | 2025-01-14 | 2025-01-14
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 ATSs - COLO4 Cell 1 | #FFFDA5 | EE60 | 2025-01-14 | 2025-01-14
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 ADP - COLO4 Cell 1 | #FFFDA5 | EE58 | 2025-01-14 | 2025-01-14
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 PDUs - COLO4 Cell 1 | #FFFDA5 | EE63 | 2025-02-17 | 2025-02-17
COLO 4 | Cell 1 | CX - L1 |  | Interior - L1 Busway - COLO4 Cell 1 | #FFFDA5 | EE61 | 2025-01-14 | 2025-01-14
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 TCP/MSB - COLO4 Cell 1 | #FFFDA5 | EE57 | 2025-03-18 | 2025-03-24
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 UPS - COLO4 Cell 1 | #FFFDA5 | EE62 | 2025-03-25 | 2025-03-31
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 PDUs - COLO4 Cell 1 | #FFFDA5 | EE63 | 2025-03-25 | 2025-03-31
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 ADP - COLO4 Cell 1 | #FFFDA5 | EE58 | 2025-03-25 | 2025-03-31
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 ATSs - COLO4 Cell 1 | #FFFDA5 | EE60 | 2025-04-01 | 2025-04-07
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 Busway - COLO4 Cell 1 | #FFFDA5 | EE61 | 2025-04-01 | 2025-04-07
COLO 4 | Cell 1 | CX - L2 |  | Interior - L2 AHUs - COLO4 Cell 1 | #FFFDA5 | EE59 | 2025-04-08 | 2025-04-14
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 TCP/MSB - COLO4 Cell 1 | #FFFDA5 | EE57 | 2025-04-25 | 2025-05-01
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 UPS - COLO4 Cell 1 | #FFFDA5 | EE62 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 PDUs - COLO4 Cell 1 | #FFFDA5 | EE63 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 ADP - COLO4 Cell 1 | #FFFDA5 | EE58 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 ATSs - COLO4 Cell 1 | #FFFDA5 | EE60 | 2025-05-09 | 2025-05-15
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 AHUs - COLO4 Cell 1 | #FFFDA5 | EE59 | 2025-05-16 | 2025-05-30
COLO 4 | Cell 1 | CX - L3 |  | Interior - L3 Busway - COLO4 Cell 1 | #FFFDA5 | EE61 | 2025-06-02 | 2025-06-06
COLO 4 | Cell 2 | Mech Gallery |  | Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG | #CFE741 | GA12 | 2025-01-13 | 2025-01-14
COLO 4 | Cell 2 | Mech Gallery |  | Install Walls and Primer Paint - COLO4 Cell 2 - MG | #D6F2FF | T3 | 2025-01-15 | 2025-01-28
COLO 4 | Cell 2 | Mech Gallery |  | Layout Ceiling and install Pencile Rod - COLO4 Cell 2 - MG | #3399FF | J9 | 2025-01-29 | 2025-01-29
COLO 4 | Cell 2 | Mech Gallery |  | Placing the AHU - COLO4 Cell 2 - MG | #CFE741 | GA6 | 2025-02-05 | 2025-02-07
COLO 4 | Cell 2 | Mech Gallery |  | Post Wall Overhead MEP - COLO4 Cell 2 - MG | #FFFDA5 | EE70 | 2025-01-29 | 2025-02-18
COLO 4 | Cell 2 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO4 Cell 2 - MG | #EF9E5B | ET22 | 2025-02-07 | 2025-02-21
COLO 4 | Cell 2 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 2 - MG | #C00000 | I-R | 2025-02-21 | 2025-02-25
COLO 4 | Cell 2 | Mech Gallery |  | Install ceiling and Light Fittings - COLO4 Cell 2 - MG | #FFFDA5 | EE35 | 2025-02-25 | 2025-03-07
COLO 4 | Cell 2 | Mech Gallery |  | Trim out MEP - COLO4 Cell 2 - MG | #FFFDA5 | EE36 | 2025-03-07 | 2025-03-14
COLO 4 | Cell 2 | Electrical Room |  | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 2 - ER | #FFFDA5 | EE1 | 2024-12-20 | 2025-01-06
COLO 4 | Cell 2 | Electrical Room |  | Install Ceiling - COLO4 Cell 2 - ER | #3399FF | J17 | 2025-01-07 | 2025-01-09
COLO 4 | Cell 2 | Electrical Room |  | Install DX Split Units - COLO4 Cell 2 - ER | #987655 | GH3 | 2025-01-10 | 2025-01-16
COLO 4 | Cell 2 | Electrical Room |  | Installation of ADP & ATS - COLO4 Cell 2 - ER | #FFFDA5 | EE27 | 2025-01-14 | 2025-01-20
COLO 4 | Cell 2 | Electrical Room |  | Installation of UPS Equipment - COLO4 Cell 2 - ER | #FFFDA5 | EE23 | 2025-01-13 | 2025-01-17
COLO 4 | Cell 2 | Electrical Room |  | Installation of TCP/MSB - COLO4 Cell 2 - ER | #FFFDA5 | EE71 | 2025-01-14 | 2025-01-20
COLO 4 | Cell 2 | Electrical Room |  | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | #FFFDA5 | EE72 | 2025-01-09 | 2025-01-22
COLO 4 | Cell 2 | Electrical Room |  | Door Frame Installation - COLO4 Cell 2 - ER | #3399FF | J36 | 2025-01-20 | 2025-01-24
COLO 4 | Cell 2 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO4 Cell 2 - ER | #FFFDA5 | EE28 | 2025-01-16 | 2025-01-22
COLO 4 | Cell 2 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER | #FFFDA5 | EE29 | 2025-02-06 | 2025-02-26
COLO 4 | Cell 2 | Electrical Room |  | Finishes and Signage - COLO4 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-02-24 | 2025-02-28
COLO 4 | Cell 2 | Data Hall |  | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH | #FFFDA5 | EE74 | 2024-12-06 | 2024-12-23
COLO 4 | Cell 2 | Data Hall |  | Security Screen Installation - COLO4 Cell 2 - DH | #3399FF | J6 | 2025-01-29 | 2025-01-31
COLO 4 | Cell 2 | Data Hall |  | Ceiling Grid and Tile - COLO4 Cell 2 - DH | #3399FF | J7 | 2025-02-03 | 2025-02-07
COLO 4 | Cell 2 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH | #FFFDA5 | EE73 | 2025-02-10 | 2025-02-21
COLO 4 | Cell 2 | Data Hall |  | Install PDU's - COLO4 Cell 2 - DH | #FFFDA5 | EE7 | 2025-02-24 | 2025-02-28
COLO 4 | Cell 2 | Data Hall |  | Begin HAC Assembly - COLO4 Cell 2 - DH | #FED7E8 | S1 | 2025-02-24 | 2025-02-28
COLO 4 | Cell 2 | Data Hall |  | Install Busway - COLO4 Cell 2 - DH | #FFFDA5 | EE10 | 2025-02-26 | 2025-03-04
COLO 4 | Cell 2 | Data Hall |  | HAC install and Rise - COLO4 Cell 2 - DH | #FED7E8 | S2 | 2025-03-03 | 2025-03-07
COLO 4 | Cell 2 | Data Hall |  | Cable Pulling at PDU & Busway- COLO4 Cell 2 - DH | #FFFDA5 | EE17 | 2025-03-03 | 2025-03-14
COLO 4 | Cell 2 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 2 - DH | #EF9E5B | ET7 | 2025-03-10 | 2025-03-21
COLO 4 | Cell 2 | Data Hall |  | Termination at PDU & Busway - COLO4 Cell 2 - DH | #FFFDA5 | EE18 | 2025-03-10 | 2025-03-28
COLO 4 | Cell 2 | Data Hall |  | Finishes and Signage - COLO4 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-03-24 | 2025-03-28
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 UPS - COLO4 Cell 2 | #FFFDA5 | EE62 | 2025-01-20 | 2025-01-20
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 TCP/MSB - COLO4 Cell 2 | #FFFDA5 | EE57 | 2025-01-21 | 2025-01-21
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 ATSs - COLO4 Cell 2 | #FFFDA5 | EE60 | 2025-01-21 | 2025-01-21
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 ADP - COLO4 Cell 2 | #FFFDA5 | EE58 | 2025-01-21 | 2025-01-21
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 AHUs - COLO4 Cell 2 | #FFFDA5 | EE59 | 2025-02-05 | 2025-02-05
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 PDUs - COLO4 Cell 2 | #FFFDA5 | EE63 | 2025-03-03 | 2025-03-03
COLO 4 | Cell 2 | CX - L1 |  | Interior - L1 Busway - COLO4 Cell 2 | #FFFDA5 | EE61 | 2025-01-21 | 2025-01-21
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 TCP/MSB - COLO4 Cell 2 | #FFFDA5 | EE57 | 2025-04-01 | 2025-04-07
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 UPS - COLO4 Cell 2 | #FFFDA5 | EE62 | 2025-04-08 | 2025-04-14
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 PDUs - COLO4 Cell 2 | #FFFDA5 | EE63 | 2025-04-08 | 2025-04-14
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 ADP - COLO4 Cell 2 | #FFFDA5 | EE58 | 2025-04-08 | 2025-04-14
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 ATSs - COLO4 Cell 2 | #FFFDA5 | EE60 | 2025-04-15 | 2025-04-21
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 Busway - COLO4 Cell 2 | #FFFDA5 | EE61 | 2025-04-15 | 2025-04-21
COLO 4 | Cell 2 | CX - L2 |  | Interior - L2 AHUs - COLO4 Cell 2 | #FFFDA5 | EE59 | 2025-04-22 | 2025-04-28
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 TCP/MSB - COLO4 Cell 2 | #FFFDA5 | EE57 | 2025-04-25 | 2025-05-01
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 UPS - COLO4 Cell 2 | #FFFDA5 | EE62 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 PDUs - COLO4 Cell 2 | #FFFDA5 | EE63 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 ADP - COLO4 Cell 2 | #FFFDA5 | EE58 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 ATSs - COLO4 Cell 2 | #FFFDA5 | EE60 | 2025-05-09 | 2025-05-15
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 AHUs - COLO4 Cell 2 | #FFFDA5 | EE59 | 2025-05-16 | 2025-05-30
COLO 4 | Cell 2 | CX - L3 |  | Interior - L3 Busway - COLO4 Cell 2 | #FFFDA5 | EE61 | 2025-06-02 | 2025-06-06
COLO 4 | Cell 3 | Mech Gallery |  | Overhead MEP Installation - COLO4 Cell 3 - MG | #FFFDA5 | EE73 | 2025-01-13 | 2025-01-24
COLO 4 | Cell 3 | Mech Gallery |  | Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG | #CFE741 | GA12 | 2025-01-27 | 2025-01-28
COLO 4 | Cell 3 | Mech Gallery |  | Install Walls and Primer Paint - COLO4 Cell 3 - MG | #D6F2FF | T3 | 2025-01-29 | 2025-02-11
COLO 4 | Cell 3 | Mech Gallery |  | Layout Ceiling and install Pencile Rod - COLO4 Cell 3 - MG | #3399FF | J9 | 2025-02-12 | 2025-02-12
COLO 4 | Cell 3 | Mech Gallery |  | Placing the AHU - COLO4 Cell 3 - MG | #CFE741 | GA6 | 2025-02-19 | 2025-02-21
COLO 4 | Cell 3 | Mech Gallery |  | Post Wall Overhead MEP - COLO4 Cell 3 - MG | #FFFDA5 | EE70 | 2025-02-12 | 2025-03-04
COLO 4 | Cell 3 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO4 Cell 3 - MG | #EF9E5B | ET22 | 2025-02-21 | 2025-03-07
COLO 4 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 3 - MG | #C00000 | I-R | 2025-03-07 | 2025-03-11
COLO 4 | Cell 3 | Mech Gallery |  | Install ceiling and Light Fittings - COLO4 Cell 3 - MG | #FFFDA5 | EE35 | 2025-03-11 | 2025-03-21
COLO 4 | Cell 3 | Mech Gallery |  | Trim out MEP - COLO4 Cell 3 - MG | #FFFDA5 | EE36 | 2025-03-21 | 2025-03-28
COLO 4 | Cell 3 | Electrical Room |  | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 3 - ER | #FFFDA5 | EE1 | 2025-01-07 | 2025-01-20
COLO 4 | Cell 3 | Electrical Room |  | Install Ceiling - COLO4 Cell 3 - ER | #3399FF | J17 | 2025-01-21 | 2025-01-23
COLO 4 | Cell 3 | Electrical Room |  | Install DX Split Units - COLO4 Cell 3 - ER | #987655 | GH3 | 2025-01-24 | 2025-01-30
COLO 4 | Cell 3 | Electrical Room |  | Installation of ADP & ATS - COLO4 Cell 3 - ER | #FFFDA5 | EE27 | 2025-01-27 | 2025-01-31
COLO 4 | Cell 3 | Electrical Room |  | Installation of UPS Equipment - COLO4 Cell 3 - ER | #FFFDA5 | EE23 | 2025-01-27 | 2025-01-31
COLO 4 | Cell 3 | Electrical Room |  | Installation of TCP/MSB - COLO4 Cell 3 - ER | #FFFDA5 | EE71 | 2025-01-27 | 2025-01-31
COLO 4 | Cell 3 | Electrical Room |  | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | #FFFDA5 | EE72 | 2025-01-23 | 2025-02-05
COLO 4 | Cell 3 | Electrical Room |  | Door Frame Installation - COLO4 Cell 3 - ER | #3399FF | J36 | 2025-02-03 | 2025-02-07
COLO 4 | Cell 3 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO4 Cell 3 - ER | #FFFDA5 | EE28 | 2025-01-29 | 2025-02-04
COLO 4 | Cell 3 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER | #FFFDA5 | EE29 | 2025-02-27 | 2025-03-19
COLO 4 | Cell 3 | Electrical Room |  | Finishes and Signage - COLO4 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-03-17 | 2025-03-21
COLO 4 | Cell 3 | Data Hall |  | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH | #FFFDA5 | EE74 | 2024-12-24 | 2025-01-10
COLO 4 | Cell 3 | Data Hall |  | Security Screen Installation - COLO4 Cell 3 - DH | #3399FF | J6 | 2025-02-12 | 2025-02-14
COLO 4 | Cell 3 | Data Hall |  | Ceiling Grid and Tile - COLO4 Cell 3 - DH | #3399FF | J7 | 2025-02-17 | 2025-02-21
COLO 4 | Cell 3 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH | #FFFDA5 | EE73 | 2025-02-24 | 2025-03-07
COLO 4 | Cell 3 | Data Hall |  | Install PDU's - COLO4 Cell 3 - DH | #FFFDA5 | EE7 | 2025-03-10 | 2025-03-14
COLO 4 | Cell 3 | Data Hall |  | Begin HAC Assembly - COLO4 Cell 3 - DH | #FED7E8 | S1 | 2025-03-10 | 2025-03-14
COLO 4 | Cell 3 | Data Hall |  | Install Busway - COLO4 Cell 3 - DH | #FFFDA5 | EE10 | 2025-03-12 | 2025-03-18
COLO 4 | Cell 3 | Data Hall |  | HAC install and Rise - COLO4 Cell 3 - DH | #FED7E8 | S2 | 2025-03-17 | 2025-03-21
COLO 4 | Cell 3 | Data Hall |  | Cable Pulling at PDU & Busway- COLO4 Cell 3 - DH | #FFFDA5 | EE17 | 2025-03-17 | 2025-03-28
COLO 4 | Cell 3 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 3 - DH | #EF9E5B | ET7 | 2025-03-24 | 2025-04-04
COLO 4 | Cell 3 | Data Hall |  | Termination at PDU & Busway - COLO4 Cell 3 - DH | #FFFDA5 | EE18 | 2025-03-31 | 2025-04-18
COLO 4 | Cell 3 | Data Hall |  | Finishes and Signage - COLO4 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-04-14 | 2025-04-18
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 UPS - COLO4 Cell 3 | #FFFDA5 | EE62 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 TCP/MSB - COLO4 Cell 3 | #FFFDA5 | EE57 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 ATSs - COLO4 Cell 3 | #FFFDA5 | EE60 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 ADP - COLO4 Cell 3 | #FFFDA5 | EE58 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 AHUs - COLO4 Cell 3 | #FFFDA5 | EE59 | 2025-02-19 | 2025-02-19
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 PDUs - COLO4 Cell 3 | #FFFDA5 | EE63 | 2025-03-17 | 2025-03-17
COLO 4 | Cell 3 | CX - L1 |  | Interior - L1 Busway - COLO4 Cell 3 | #FFFDA5 | EE61 | 2025-02-03 | 2025-02-03
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 TCP/MSB - COLO4 Cell 3 | #FFFDA5 | EE57 | 2025-04-07 | 2025-04-11
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 UPS - COLO4 Cell 3 | #FFFDA5 | EE62 | 2025-04-14 | 2025-04-18
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 PDUs - COLO4 Cell 3 | #FFFDA5 | EE63 | 2025-04-14 | 2025-04-18
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 ADP - COLO4 Cell 3 | #FFFDA5 | EE58 | 2025-04-14 | 2025-04-18
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 ATSs - COLO4 Cell 3 | #FFFDA5 | EE60 | 2025-04-21 | 2025-04-25
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 Busway - COLO4 Cell 3 | #FFFDA5 | EE61 | 2025-04-21 | 2025-04-25
COLO 4 | Cell 3 | CX - L2 |  | Interior - L2 AHUs - COLO4 Cell 3 | #FFFDA5 | EE59 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 TCP/MSB - COLO4 Cell 3 | #FFFDA5 | EE57 | 2025-04-25 | 2025-05-01
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 UPS - COLO4 Cell 3 | #FFFDA5 | EE62 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 PDUs - COLO4 Cell 3 | #FFFDA5 | EE63 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 ADP - COLO4 Cell 3 | #FFFDA5 | EE58 | 2025-05-02 | 2025-05-08
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 ATSs - COLO4 Cell 3 | #FFFDA5 | EE60 | 2025-05-09 | 2025-05-15
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 AHUs - COLO4 Cell 3 | #FFFDA5 | EE59 | 2025-05-16 | 2025-05-30
COLO 4 | Cell 3 | CX - L3 |  | Interior - L3 Busway - COLO4 Cell 3 | #FFFDA5 | EE61 | 2025-06-02 | 2025-06-06
COLO 4 | Cell 4 | Mech Gallery |  | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG | #CFE741 | GA3 | 2025-01-06 | 2025-01-10
COLO 4 | Cell 4 | Mech Gallery |  | Overhead MEP Installation - COLO4 Cell 4 - MG | #FFFDA5 | EE73 | 2025-01-27 | 2025-02-07
COLO 4 | Cell 4 | Mech Gallery |  | Deliver AHU into Mech. Gallery - COLO4 Cell 4 - MG | #CFE741 | GA12 | 2025-02-10 | 2025-02-11
COLO 4 | Cell 4 | Mech Gallery |  | Install Walls and Primer Paint - COLO4 Cell 4 - MG | #D6F2FF | T3 | 2025-02-12 | 2025-02-25
COLO 4 | Cell 4 | Mech Gallery |  | Layout Ceiling and install Pencile Rod - COLO4 Cell 4 - MG | #3399FF | J9 | 2025-02-26 | 2025-02-26
COLO 4 | Cell 4 | Mech Gallery |  | Placing the AHU - COLO4 Cell 4 - MG | #CFE741 | GA6 | 2025-03-05 | 2025-03-07
COLO 4 | Cell 4 | Mech Gallery |  | Post Wall Overhead MEP - COLO4 Cell 4 - MG | #FFFDA5 | EE70 | 2025-02-26 | 2025-03-18
COLO 4 | Cell 4 | Mech Gallery |  | Piping and Electrical Termination to AHUs - COLO4 Cell 4 - MG | #EF9E5B | ET22 | 2025-03-07 | 2025-03-21
COLO 4 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 4 - MG | #C00000 | I-R | 2025-03-21 | 2025-03-25
COLO 4 | Cell 4 | Mech Gallery |  | Install ceiling and Light Fittings - COLO4 Cell 4 - MG | #FFFDA5 | EE35 | 2025-03-25 | 2025-04-04
COLO 4 | Cell 4 | Mech Gallery |  | Trim out MEP - COLO4 Cell 4 - MG | #FFFDA5 | EE36 | 2025-04-04 | 2025-04-11
COLO 4 | Cell 4 | Electrical Room |  | Install Walls and Primer Paint - COLO4 Cell 4 - ER | #D6F2FF | T3 | 2025-01-03 | 2025-01-16
COLO 4 | Cell 4 | Electrical Room |  | Install Upper Screens - COLO4 Cell 4 - ER | #3399FF | J37 | 2025-01-14 | 2025-01-20
COLO 4 | Cell 4 | Electrical Room |  | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 4 - ER | #FFFDA5 | EE1 | 2025-01-21 | 2025-02-03
COLO 4 | Cell 4 | Electrical Room |  | Install Ceiling - COLO4 Cell 4 - ER | #3399FF | J17 | 2025-02-04 | 2025-02-06
COLO 4 | Cell 4 | Electrical Room |  | Installation of ADP & ATS - COLO4 Cell 4 - ER | #FFFDA5 | EE27 | 2025-02-06 | 2025-02-12
COLO 4 | Cell 4 | Electrical Room |  | Installation of TCP/MSB - COLO4 Cell 4 - ER | #FFFDA5 | EE71 | 2025-02-06 | 2025-02-12
COLO 4 | Cell 4 | Electrical Room |  | Install DX Split Units - COLO4 Cell 4 - ER | #987655 | GH3 | 2025-02-07 | 2025-02-13
COLO 4 | Cell 4 | Electrical Room |  | Installation of UPS Equipment - COLO4 Cell 4 - ER | #FFFDA5 | EE23 | 2025-02-10 | 2025-02-14
COLO 4 | Cell 4 | Electrical Room |  | Connect to Cable tray and conduit equipment - COLO4 Cell 4 - ER | #FFFDA5 | EE28 | 2025-02-06 | 2025-02-12
COLO 4 | Cell 4 | Electrical Room |  | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | #FFFDA5 | EE72 | 2025-02-06 | 2025-02-19
COLO 4 | Cell 4 | Electrical Room |  | Door Frame Installation - COLO4 Cell 4 - ER | #3399FF | J36 | 2025-02-17 | 2025-02-21
COLO 4 | Cell 4 | Electrical Room |  | Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER | #FFFDA5 | EE29 | 2025-03-20 | 2025-04-09
COLO 4 | Cell 4 | Electrical Room |  | Finishes and Signage - COLO4 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-04-03 | 2025-04-09
COLO 4 | Cell 4 | Data Hall |  | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 4 - DH | #FFFDA5 | EE74 | 2025-01-13 | 2025-01-28
COLO 4 | Cell 4 | Data Hall |  | Security Screen Installation - COLO4 Cell 4 - DH | #3399FF | J6 | 2025-02-26 | 2025-02-28
COLO 4 | Cell 4 | Data Hall |  | Ceiling Grid and Tile - COLO4 Cell 4 - DH | #3399FF | J7 | 2025-03-03 | 2025-03-07
COLO 4 | Cell 4 | Data Hall |  | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 4 - DH | #FFFDA5 | EE73 | 2025-03-10 | 2025-03-21
COLO 4 | Cell 4 | Data Hall |  | Install PDU's - COLO4 Cell 4 - DH | #FFFDA5 | EE7 | 2025-03-24 | 2025-03-28
COLO 4 | Cell 4 | Data Hall |  | Begin HAC Assembly - COLO4 Cell 4 - DH | #FED7E8 | S1 | 2025-03-24 | 2025-03-28
COLO 4 | Cell 4 | Data Hall |  | Install Busway - COLO4 Cell 4 - DH | #FFFDA5 | EE10 | 2025-03-26 | 2025-04-01
COLO 4 | Cell 4 | Data Hall |  | HAC install and Rise - COLO4 Cell 4 - DH | #FED7E8 | S2 | 2025-03-31 | 2025-04-04
COLO 4 | Cell 4 | Data Hall |  | Cable Pulling at PDU & Busway- COLO4 Cell 4 - DH | #FFFDA5 | EE17 | 2025-03-31 | 2025-04-11
COLO 4 | Cell 4 | Data Hall |  | Closing Construction Access Door - COLO4 Cell 4 - DH | #04A261 | W4 | 2025-03-31 | 2025-04-18
COLO 4 | Cell 4 | Data Hall |  | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH | #EF9E5B | ET7 | 2025-04-07 | 2025-04-18
COLO 4 | Cell 4 | Data Hall |  | Termination at PDU & Busway - COLO4 Cell 4 - DH | #FFFDA5 | EE18 | 2025-04-21 | 2025-05-09
COLO 4 | Cell 4 | Data Hall |  | Finishes and Signage - COLO4 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 TCP/MSB - COLO4 Cell 4 | #FFFDA5 | EE57 | 2025-02-13 | 2025-02-13
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 ATSs - COLO4 Cell 4 | #FFFDA5 | EE60 | 2025-02-13 | 2025-02-13
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 ADP - COLO4 Cell 4 | #FFFDA5 | EE58 | 2025-02-13 | 2025-02-13
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 UPS - COLO4 Cell 4 | #FFFDA5 | EE62 | 2025-02-17 | 2025-02-17
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 AHUs - COLO4 Cell 4 | #FFFDA5 | EE59 | 2025-03-05 | 2025-03-05
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 PDUs - COLO4 Cell 4 | #FFFDA5 | EE63 | 2025-03-31 | 2025-03-31
COLO 4 | Cell 4 | CX - L1 |  | Interior - L1 Busway - COLO4 Cell 4 | #FFFDA5 | EE61 | 2025-02-13 | 2025-02-13
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 TCP/MSB - COLO4 Cell 4 | #FFFDA5 | EE57 | 2025-04-21 | 2025-04-25
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 UPS - COLO4 Cell 4 | #FFFDA5 | EE62 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 PDUs - COLO4 Cell 4 | #FFFDA5 | EE63 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 ADP - COLO4 Cell 4 | #FFFDA5 | EE58 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 ATSs - COLO4 Cell 4 | #FFFDA5 | EE60 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 Busway - COLO4 Cell 4 | #FFFDA5 | EE61 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 4 | CX - L2 |  | Interior - L2 AHUs - COLO4 Cell 4 | #FFFDA5 | EE59 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 TCP/MSB - COLO4 Cell 4 | #FFFDA5 | EE57 | 2025-05-09 | 2025-05-15
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 UPS - COLO4 Cell 4 | #FFFDA5 | EE62 | 2025-06-03 | 2025-06-09
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 PDUs - COLO4 Cell 4 | #FFFDA5 | EE63 | 2025-05-16 | 2025-05-22
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 ADP - COLO4 Cell 4 | #FFFDA5 | EE58 | 2025-05-16 | 2025-05-22
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 ATSs - COLO4 Cell 4 | #FFFDA5 | EE60 | 2025-05-23 | 2025-05-30
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 AHUs - COLO4 Cell 4 | #FFFDA5 | EE59 | 2025-06-03 | 2025-06-16
COLO 4 | Cell 4 | CX - L3 |  | Interior - L3 Busway - COLO4 Cell 4 | #FFFDA5 | EE61 | 2025-06-17 | 2025-06-23
COLO 4 | All | CX - Microsoft |  | Level 4 Cx - Colo 4 | #000000 | MS1 | 2025-06-25 | 2025-07-30
COLO 4 | All | CX - Microsoft |  | Level 5 Cx / IST - Colo 4 | #000000 | MS2 | 2025-08-01 | 2025-08-04

## CFA - Schedule
|  |  | 2024 | [62 empty] | 2025
|  |  | Oct |  | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug
|  |  | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04
phase | location | area | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
COLO 4 | All | CX - Microsoft | Jun 25 Wed: MS1; Jun 26 Thu: MS1; Jun 27 Fri: MS1; Jun 28 Sat: MS1; Jun 29 Sun: MS1; Jun 30 Mon: MS1; Jul 01 Tue: MS1; Jul 02 Wed: MS1; Jul 03 Thu: MS1; Jul 04 Fri: MS1; Jul 05 Sat: MS1; Jul 06 Sun: MS1; Jul 07 Mon: MS1; Jul 08 Tue: MS1; Jul 09 Wed: MS1; Jul 10 Thu: MS1; Jul 11 Fri: MS1; Jul 12 Sat: MS1; Jul 13 Sun: MS1; Jul 14 Mon: MS1; Jul 15 Tue: MS1; Jul 16 Wed: MS1; Jul 17 Thu: MS1; Jul 18 Fri: MS1; Jul 19 Sat: MS1; Jul 20 Sun: MS1; Jul 21 Mon: MS1; Jul 22 Tue: MS1; Jul 23 Wed: MS1; Jul 24 Thu: MS1; Jul 25 Fri: MS1; Jul 26 Sat: MS1; Jul 27 Sun: MS1; Jul 28 Mon: MS1; Jul 29 Tue: MS1; Jul 30 Wed: MS1; Aug 01 Fri: MS2; Aug 02 Sat: MS2; Aug 03 Sun: MS2; Aug 04 Mon: MS2
| Cell 1 | CX - L1 | Jan 02 Thu: EE62; Jan 14 Tue: EE57; Jan 22 Wed: EE59; Feb 17 Mon: EE63
EE60
EE58
EE61
|  | CX - L2 | Mar 18 Tue: EE57; Mar 19 Wed: EE57; Mar 20 Thu: EE57; Mar 21 Fri: EE57; Mar 22 Sat: EE57; Mar 23 Sun: EE57; Mar 24 Mon: EE57; Mar 25 Tue: EE62; Mar 26 Wed: EE62; Mar 27 Thu: EE62; Mar 28 Fri: EE62; Mar 29 Sat: EE62; Mar 30 Sun: EE62; Mar 31 Mon: EE62; Apr 01 Tue: EE60; Apr 02 Wed: EE60; Apr 03 Thu: EE60; Apr 04 Fri: EE60; Apr 05 Sat: EE60; Apr 06 Sun: EE60; Apr 07 Mon: EE60; Apr 08 Tue: EE59; Apr 09 Wed: EE59; Apr 10 Thu: EE59; Apr 11 Fri: EE59; Apr 12 Sat: EE59; Apr 13 Sun: EE59; Apr 14 Mon: EE59
[149 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[149 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | Apr 25 Fri: EE57; Apr 26 Sat: EE57; Apr 27 Sun: EE57; Apr 28 Mon: EE57; Apr 29 Tue: EE57; Apr 30 Wed: EE57; May 01 Thu: EE57; May 02 Fri: EE62; May 03 Sat: EE62; May 04 Sun: EE62; May 05 Mon: EE62; May 06 Tue: EE62; May 07 Wed: EE62; May 08 Thu: EE62; May 09 Fri: EE60; May 10 Sat: EE60; May 11 Sun: EE60; May 12 Mon: EE60; May 13 Tue: EE60; May 14 Wed: EE60; May 15 Thu: EE60; May 16 Fri: EE59; May 17 Sat: EE59; May 18 Sun: EE59; May 19 Mon: EE59; May 20 Tue: EE59; May 21 Wed: EE59; May 22 Thu: EE59; May 23 Fri: EE59; May 24 Sat: EE59; May 25 Sun: EE59; May 26 Mon: EE59; May 27 Tue: EE59; May 28 Wed: EE59; May 29 Thu: EE59; May 30 Fri: EE59; Jun 02 Mon: EE61; Jun 03 Tue: EE61; Jun 04 Wed: EE61; Jun 05 Thu: EE61; Jun 06 Fri: EE61
[187 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[187 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | Jan 20 Mon: J7; Jan 21 Tue: J7; Jan 22 Wed: J7; Jan 23 Thu: J7; Jan 24 Fri: J7; Jan 27 Mon: EE73; Jan 28 Tue: EE73; Jan 29 Wed: EE73; Jan 30 Thu: EE73; Jan 31 Fri: EE73; Feb 01 Sat: EE73; Feb 02 Sun: EE73; Feb 03 Mon: EE73; Feb 04 Tue: EE73; Feb 05 Wed: EE73; Feb 06 Thu: EE73; Feb 07 Fri: EE73; Feb 10 Mon: EE7; Feb 11 Tue: EE7; Feb 12 Wed: EE7; Feb 13 Thu: EE7; Feb 14 Fri: EE7; Feb 17 Mon: S2; Feb 18 Tue: S2; Feb 19 Wed: S2; Feb 20 Thu: S2; Feb 21 Fri: S2; Feb 24 Mon: ET22; Feb 25 Tue: ET22; Feb 26 Wed: ET22; Feb 27 Thu: ET22; Feb 28 Fri: ET22; Mar 01 Sat: ET22; Mar 02 Sun: ET22; Mar 03 Mon: ET22; Mar 04 Tue: ET22; Mar 05 Wed: ET22; Mar 06 Thu: ET22; Mar 07 Fri: ET22; Mar 17 Mon: ALL3; Mar 18 Tue: ALL3; Mar 19 Wed: ALL3; Mar 20 Thu: ALL3; Mar 21 Fri: ALL3
[106 empty] | S1 | S1 | S1 | S1 | S1 |  |  | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17
[108 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [5 empty] | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | Dec 20 Fri: EE72; Dec 21 Sat: EE72; Dec 22 Sun: EE72; Dec 23 Mon: EE72; Dec 24 Tue: EE72; Dec 25 Wed: EE72; Dec 26 Thu: EE72; Dec 27 Fri: EE72; Dec 28 Sat: EE72; Dec 29 Sun: EE72; Dec 30 Mon: EE72; Dec 31 Tue: EE72; Jan 01 Wed: EE72; Jan 02 Thu: EE72; Jan 03 Fri: EE72; Jan 04 Sat: EE72; Jan 05 Sun: EE72; Jan 06 Mon: EE72; Jan 07 Tue: EE27; Jan 08 Wed: EE27; Jan 09 Thu: EE27; Jan 10 Fri: EE27; Jan 11 Sat: EE27; Jan 12 Sun: EE27; Jan 13 Mon: EE27; Jan 16 Thu: EE29; Jan 17 Fri: EE29; Jan 18 Sat: EE29; Jan 19 Sun: EE29; Jan 20 Mon: EE29; Jan 21 Tue: EE29; Jan 22 Wed: EE29; Jan 23 Thu: EE29; Jan 24 Fri: EE29; Jan 25 Sat: EE29; Jan 26 Sun: EE29; Jan 27 Mon: EE29; Jan 28 Tue: EE29; Jan 29 Wed: EE29; Jan 30 Thu: EE29; Jan 31 Fri: EE29; Feb 01 Sat: EE29; Feb 02 Sun: EE29; Feb 03 Mon: EE29; Feb 04 Tue: EE29; Feb 05 Wed: EE29
[57 empty] | GH3 | GH3 | GH3 | GH3 | GH3 | GH3 | GH3 | GH3 |  |  |  | J36 | J36 | J36 | J36 | J36 | J36 | J36 | [24 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[58 empty] | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | EE23 | [6 empty] | EE71 | EE71 | EE71 | EE71 | EE71 | EE71 | EE71
[74 empty] | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28
|  | Mech Gallery | Jan 15 Wed: EE70; Jan 16 Thu: EE70; Jan 17 Fri: EE70; Jan 18 Sat: EE70; Jan 19 Sun: EE70; Jan 20 Mon: EE70; Jan 21 Tue: EE70; Jan 22 Wed: EE70; Jan 23 Thu: EE70; Jan 24 Fri: EE70; Jan 25 Sat: EE70; Jan 26 Sun: EE70; Jan 27 Mon: EE70; Jan 28 Tue: EE70; Jan 29 Wed: EE70; Jan 30 Thu: EE70; Jan 31 Fri: EE70; Feb 01 Sat: EE70; Feb 02 Sun: EE70; Feb 03 Mon: EE70; Feb 04 Tue: EE70; Feb 07 Fri: I-R; Feb 08 Sat: I-R; Feb 09 Sun: I-R; Feb 10 Mon: I-R; Feb 11 Tue: I-R; Feb 21 Fri: EE36; Feb 22 Sat: EE36; Feb 23 Sun: EE36; Feb 24 Mon: EE36; Feb 25 Tue: EE36; Feb 26 Wed: EE36; Feb 27 Thu: EE36; Feb 28 Fri: EE36
[87 empty] | GA6 | GA6 | GA6 | [17 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
[89 empty] | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | EE1
| Cell 2 | CX - L1 | Jan 20 Mon: EE62; Jan 21 Tue: EE57; Feb 05 Wed: EE59; Mar 03 Mon: EE63
EE60
EE58
EE61
|  | CX - L2 | Apr 01 Tue: EE57; Apr 02 Wed: EE57; Apr 03 Thu: EE57; Apr 04 Fri: EE57; Apr 05 Sat: EE57; Apr 06 Sun: EE57; Apr 07 Mon: EE57; Apr 08 Tue: EE62; Apr 09 Wed: EE62; Apr 10 Thu: EE62; Apr 11 Fri: EE62; Apr 12 Sat: EE62; Apr 13 Sun: EE62; Apr 14 Mon: EE62; Apr 15 Tue: EE60; Apr 16 Wed: EE60; Apr 17 Thu: EE60; Apr 18 Fri: EE60; Apr 19 Sat: EE60; Apr 20 Sun: EE60; Apr 21 Mon: EE60; Apr 22 Tue: EE59; Apr 23 Wed: EE59; Apr 24 Thu: EE59; Apr 25 Fri: EE59; Apr 26 Sat: EE59; Apr 27 Sun: EE59; Apr 28 Mon: EE59
[163 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[163 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | Apr 25 Fri: EE57; Apr 26 Sat: EE57; Apr 27 Sun: EE57; Apr 28 Mon: EE57; Apr 29 Tue: EE57; Apr 30 Wed: EE57; May 01 Thu: EE57; May 02 Fri: EE62; May 03 Sat: EE62; May 04 Sun: EE62; May 05 Mon: EE62; May 06 Tue: EE62; May 07 Wed: EE62; May 08 Thu: EE62; May 09 Fri: EE60; May 10 Sat: EE60; May 11 Sun: EE60; May 12 Mon: EE60; May 13 Tue: EE60; May 14 Wed: EE60; May 15 Thu: EE60; May 16 Fri: EE59; May 17 Sat: EE59; May 18 Sun: EE59; May 19 Mon: EE59; May 20 Tue: EE59; May 21 Wed: EE59; May 22 Thu: EE59; May 23 Fri: EE59; May 24 Sat: EE59; May 25 Sun: EE59; May 26 Mon: EE59; May 27 Tue: EE59; May 28 Wed: EE59; May 29 Thu: EE59; May 30 Fri: EE59; Jun 02 Mon: EE61; Jun 03 Tue: EE61; Jun 04 Wed: EE61; Jun 05 Thu: EE61; Jun 06 Fri: EE61
[187 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[187 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | Dec 06 Fri: EE74; Dec 07 Sat: EE74; Dec 08 Sun: EE74; Dec 09 Mon: EE74; Dec 10 Tue: EE74; Dec 11 Wed: EE74; Dec 12 Thu: EE74; Dec 13 Fri: EE74; Dec 14 Sat: EE74; Dec 15 Sun: EE74; Dec 16 Mon: EE74; Dec 17 Tue: EE74; Dec 18 Wed: EE74; Dec 19 Thu: EE74; Dec 20 Fri: EE74; Dec 21 Sat: EE74; Dec 22 Sun: EE74; Dec 23 Mon: EE74; Jan 29 Wed: J6; Jan 30 Thu: J6; Jan 31 Fri: J6; Feb 03 Mon: J7; Feb 04 Tue: J7; Feb 05 Wed: J7; Feb 06 Thu: J7; Feb 07 Fri: J7; Feb 10 Mon: EE73; Feb 11 Tue: EE73; Feb 12 Wed: EE73; Feb 13 Thu: EE73; Feb 14 Fri: EE73; Feb 15 Sat: EE73; Feb 16 Sun: EE73; Feb 17 Mon: EE73; Feb 18 Tue: EE73; Feb 19 Wed: EE73; Feb 20 Thu: EE73; Feb 21 Fri: EE73; Feb 24 Mon: EE7; Feb 25 Tue: EE7; Feb 26 Wed: EE7; Feb 27 Thu: EE7; Feb 28 Fri: EE7; Mar 03 Mon: S2; Mar 04 Tue: S2; Mar 05 Wed: S2; Mar 06 Thu: S2; Mar 07 Fri: S2; Mar 10 Mon: ET7; Mar 11 Tue: ET7; Mar 12 Wed: ET7; Mar 13 Thu: ET7; Mar 14 Fri: ET7; Mar 15 Sat: ET7; Mar 16 Sun: ET7; Mar 17 Mon: ET7; Mar 18 Tue: ET7; Mar 19 Wed: ET7; Mar 20 Thu: ET7; Mar 21 Fri: ET7; Mar 24 Mon: ALL3; Mar 25 Tue: ALL3; Mar 26 Wed: ALL3; Mar 27 Thu: ALL3; Mar 28 Fri: ALL3
[120 empty] | S1 | S1 | S1 | S1 | S1 |  |  | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17
[122 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [5 empty] | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | Dec 20 Fri: EE1; Dec 21 Sat: EE1; Dec 22 Sun: EE1; Dec 23 Mon: EE1; Dec 24 Tue: EE1; Dec 25 Wed: EE1; Dec 26 Thu: EE1; Dec 27 Fri: EE1; Dec 28 Sat: EE1; Dec 29 Sun: EE1; Dec 30 Mon: EE1; Dec 31 Tue: EE1; Jan 01 Wed: EE1; Jan 02 Thu: EE1; Jan 03 Fri: EE1; Jan 04 Sat: EE1; Jan 05 Sun: EE1; Jan 06 Mon: EE1; Jan 07 Tue: J17; Jan 08 Wed: J17; Jan 09 Thu: J17; Jan 10 Fri: GH3; Jan 11 Sat: GH3; Jan 12 Sun: GH3; Jan 13 Mon: GH3; Jan 14 Tue: GH3; Jan 15 Wed: GH3; Jan 16 Thu: GH3; Jan 20 Mon: J36; Jan 21 Tue: J36; Jan 22 Wed: J36; Jan 23 Thu: J36; Jan 24 Fri: J36; Feb 06 Thu: EE29; Feb 07 Fri: EE29; Feb 08 Sat: EE29; Feb 09 Sun: EE29; Feb 10 Mon: EE29; Feb 11 Tue: EE29; Feb 12 Wed: EE29; Feb 13 Thu: EE29; Feb 14 Fri: EE29; Feb 15 Sat: EE29; Feb 16 Sun: EE29; Feb 17 Mon: EE29; Feb 18 Tue: EE29; Feb 19 Wed: EE29; Feb 20 Thu: EE29; Feb 21 Fri: EE29; Feb 22 Sat: EE29; Feb 23 Sun: EE29; Feb 24 Mon: EE29; Feb 25 Tue: EE29; Feb 26 Wed: EE29
[74 empty] | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | [32 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[78 empty] | EE23 | EE23 | EE23 | EE23 | EE23
[79 empty] | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27
[79 empty] | EE71 | EE71 | EE71 | EE71 | EE71 | EE71 | EE71
[81 empty] | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28
|  | Mech Gallery | Jan 13 Mon: GA12; Jan 14 Tue: GA12; Jan 15 Wed: T3; Jan 16 Thu: T3; Jan 17 Fri: T3; Jan 18 Sat: T3; Jan 19 Sun: T3; Jan 20 Mon: T3; Jan 21 Tue: T3; Jan 22 Wed: T3; Jan 23 Thu: T3; Jan 24 Fri: T3; Jan 25 Sat: T3; Jan 26 Sun: T3; Jan 27 Mon: T3; Jan 28 Tue: T3; Jan 29 Wed: J9; Feb 05 Wed: GA6; Feb 06 Thu: GA6; Feb 07 Fri: GA6; Feb 21 Fri: I-R; Feb 22 Sat: I-R; Feb 23 Sun: I-R; Feb 24 Mon: I-R; Feb 25 Tue: I-R; Mar 07 Fri: EE36; Mar 08 Sat: EE36; Mar 09 Sun: EE36; Mar 10 Mon: EE36; Mar 11 Tue: EE36; Mar 12 Wed: EE36; Mar 13 Thu: EE36; Mar 14 Fri: EE36
[94 empty] | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | [6 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
[103 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22
| Cell 3 | CX - L1 | Feb 03 Mon: EE62; Feb 19 Wed: EE59; Mar 17 Mon: EE63
EE57
EE60
EE58
|  | CX - L2 | Apr 07 Mon: EE57; Apr 08 Tue: EE57; Apr 09 Wed: EE57; Apr 10 Thu: EE57; Apr 11 Fri: EE57; Apr 14 Mon: EE62; Apr 15 Tue: EE62; Apr 16 Wed: EE62; Apr 17 Thu: EE62; Apr 18 Fri: EE62; Apr 21 Mon: EE60; Apr 22 Tue: EE60; Apr 23 Wed: EE60; Apr 24 Thu: EE60; Apr 25 Fri: EE60; Apr 28 Mon: EE59; Apr 29 Tue: EE59; Apr 30 Wed: EE59; May 01 Thu: EE59; May 02 Fri: EE59
[169 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE61 | EE61 | EE61 | EE61 | EE61
[169 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | Apr 25 Fri: EE57; Apr 26 Sat: EE57; Apr 27 Sun: EE57; Apr 28 Mon: EE57; Apr 29 Tue: EE57; Apr 30 Wed: EE57; May 01 Thu: EE57; May 02 Fri: EE62; May 03 Sat: EE62; May 04 Sun: EE62; May 05 Mon: EE62; May 06 Tue: EE62; May 07 Wed: EE62; May 08 Thu: EE62; May 09 Fri: EE60; May 10 Sat: EE60; May 11 Sun: EE60; May 12 Mon: EE60; May 13 Tue: EE60; May 14 Wed: EE60; May 15 Thu: EE60; May 16 Fri: EE59; May 17 Sat: EE59; May 18 Sun: EE59; May 19 Mon: EE59; May 20 Tue: EE59; May 21 Wed: EE59; May 22 Thu: EE59; May 23 Fri: EE59; May 24 Sat: EE59; May 25 Sun: EE59; May 26 Mon: EE59; May 27 Tue: EE59; May 28 Wed: EE59; May 29 Thu: EE59; May 30 Fri: EE59; Jun 02 Mon: EE61; Jun 03 Tue: EE61; Jun 04 Wed: EE61; Jun 05 Thu: EE61; Jun 06 Fri: EE61
[187 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[187 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | Dec 24 Tue: EE74; Dec 25 Wed: EE74; Dec 26 Thu: EE74; Dec 27 Fri: EE74; Dec 28 Sat: EE74; Dec 29 Sun: EE74; Dec 30 Mon: EE74; Dec 31 Tue: EE74; Jan 01 Wed: EE74; Jan 02 Thu: EE74; Jan 03 Fri: EE74; Jan 04 Sat: EE74; Jan 05 Sun: EE74; Jan 06 Mon: EE74; Jan 07 Tue: EE74; Jan 08 Wed: EE74; Jan 09 Thu: EE74; Jan 10 Fri: EE74; Feb 12 Wed: J6; Feb 13 Thu: J6; Feb 14 Fri: J6; Feb 17 Mon: J7; Feb 18 Tue: J7; Feb 19 Wed: J7; Feb 20 Thu: J7; Feb 21 Fri: J7; Feb 24 Mon: EE73; Feb 25 Tue: EE73; Feb 26 Wed: EE73; Feb 27 Thu: EE73; Feb 28 Fri: EE73; Mar 01 Sat: EE73; Mar 02 Sun: EE73; Mar 03 Mon: EE73; Mar 04 Tue: EE73; Mar 05 Wed: EE73; Mar 06 Thu: EE73; Mar 07 Fri: EE73; Mar 10 Mon: EE7; Mar 11 Tue: EE7; Mar 12 Wed: EE7; Mar 13 Thu: EE7; Mar 14 Fri: EE7; Mar 17 Mon: S2; Mar 18 Tue: S2; Mar 19 Wed: S2; Mar 20 Thu: S2; Mar 21 Fri: S2; Mar 24 Mon: ET7; Mar 25 Tue: ET7; Mar 26 Wed: ET7; Mar 27 Thu: ET7; Mar 28 Fri: ET7; Mar 29 Sat: ET7; Mar 30 Sun: ET7; Mar 31 Mon: ET7; Apr 01 Tue: ET7; Apr 02 Wed: ET7; Apr 03 Thu: ET7; Apr 04 Fri: ET7; Apr 14 Mon: ALL3; Apr 15 Tue: ALL3; Apr 16 Wed: ALL3; Apr 17 Thu: ALL3; Apr 18 Fri: ALL3
[134 empty] | S1 | S1 | S1 | S1 | S1 |  |  | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 |  |  | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
[136 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10
|  | Electrical Room | Jan 07 Tue: EE1; Jan 08 Wed: EE1; Jan 09 Thu: EE1; Jan 10 Fri: EE1; Jan 11 Sat: EE1; Jan 12 Sun: EE1; Jan 13 Mon: EE1; Jan 14 Tue: EE1; Jan 15 Wed: EE1; Jan 16 Thu: EE1; Jan 17 Fri: EE1; Jan 18 Sat: EE1; Jan 19 Sun: EE1; Jan 20 Mon: EE1; Jan 21 Tue: J17; Jan 22 Wed: J17; Jan 23 Thu: J17; Jan 24 Fri: GH3; Jan 25 Sat: GH3; Jan 26 Sun: GH3; Jan 27 Mon: GH3; Jan 28 Tue: GH3; Jan 29 Wed: GH3; Jan 30 Thu: GH3; Feb 03 Mon: J36; Feb 04 Tue: J36; Feb 05 Wed: J36; Feb 06 Thu: J36; Feb 07 Fri: J36; Feb 27 Thu: EE29; Feb 28 Fri: EE29; Mar 01 Sat: EE29; Mar 02 Sun: EE29; Mar 03 Mon: EE29; Mar 04 Tue: EE29; Mar 05 Wed: EE29; Mar 06 Thu: EE29; Mar 07 Fri: EE29; Mar 08 Sat: EE29; Mar 09 Sun: EE29; Mar 10 Mon: EE29; Mar 11 Tue: EE29; Mar 12 Wed: EE29; Mar 13 Thu: EE29; Mar 14 Fri: EE29; Mar 15 Sat: EE29; Mar 16 Sun: EE29; Mar 17 Mon: EE29; Mar 18 Tue: EE29; Mar 19 Wed: EE29
[88 empty] | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | [39 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[92 empty] | EE27 | EE27 | EE27 | EE27 | EE27
[92 empty] | EE23 | EE23 | EE23 | EE23 | EE23
|  | Mech Gallery | Jan 13 Mon: EE73; Jan 14 Tue: EE73; Jan 15 Wed: EE73; Jan 16 Thu: EE73; Jan 17 Fri: EE73; Jan 18 Sat: EE73; Jan 19 Sun: EE73; Jan 20 Mon: EE73; Jan 21 Tue: EE73; Jan 22 Wed: EE73; Jan 23 Thu: EE73; Jan 24 Fri: EE73; Jan 27 Mon: GA12; Jan 28 Tue: GA12; Jan 29 Wed: T3; Jan 30 Thu: T3; Jan 31 Fri: T3; Feb 01 Sat: T3; Feb 02 Sun: T3; Feb 03 Mon: T3; Feb 04 Tue: T3; Feb 05 Wed: T3; Feb 06 Thu: T3; Feb 07 Fri: T3; Feb 08 Sat: T3; Feb 09 Sun: T3; Feb 10 Mon: T3; Feb 11 Tue: T3; Feb 12 Wed: J9; Feb 19 Wed: GA6; Feb 20 Thu: GA6; Feb 21 Fri: GA6; Mar 07 Fri: I-R; Mar 08 Sat: I-R; Mar 09 Sun: I-R; Mar 10 Mon: I-R; Mar 11 Tue: I-R; Mar 21 Fri: EE36; Mar 22 Sat: EE36; Mar 23 Sun: EE36; Mar 24 Mon: EE36; Mar 25 Tue: EE36; Mar 26 Wed: EE36; Mar 27 Thu: EE36; Mar 28 Fri: EE36
[108 empty] | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | [6 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
[117 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22
| Cell 4 | CX - L1 | Feb 13 Thu: EE57; Feb 17 Mon: EE62; Mar 05 Wed: EE59; Mar 31 Mon: EE63
EE60
EE58
EE61
|  | CX - L2 | Apr 21 Mon: EE57; Apr 22 Tue: EE57; Apr 23 Wed: EE57; Apr 24 Thu: EE57; Apr 25 Fri: EE57; Apr 28 Mon: EE62; Apr 29 Tue: EE62; Apr 30 Wed: EE62; May 01 Thu: EE62; May 02 Fri: EE62; May 05 Mon: EE60; May 06 Tue: EE60; May 07 Wed: EE60; May 08 Thu: EE60; May 09 Fri: EE60; May 12 Mon: EE59; May 13 Tue: EE59; May 14 Wed: EE59; May 15 Thu: EE59; May 16 Fri: EE59
[183 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE61 | EE61 | EE61 | EE61 | EE61
[183 empty] | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | May 09 Fri: EE57; May 10 Sat: EE57; May 11 Sun: EE57; May 12 Mon: EE57; May 13 Tue: EE57; May 14 Wed: EE57; May 15 Thu: EE57; May 16 Fri: EE63; May 17 Sat: EE63; May 18 Sun: EE63; May 19 Mon: EE63; May 20 Tue: EE63; May 21 Wed: EE63; May 22 Thu: EE63; May 23 Fri: EE60; May 24 Sat: EE60; May 25 Sun: EE60; May 26 Mon: EE60; May 27 Tue: EE60; May 28 Wed: EE60; May 29 Thu: EE60; May 30 Fri: EE60; Jun 03 Tue: EE62; Jun 04 Wed: EE62; Jun 05 Thu: EE62; Jun 06 Fri: EE62; Jun 07 Sat: EE62; Jun 08 Sun: EE62; Jun 09 Mon: EE62; Jun 17 Tue: EE61; Jun 18 Wed: EE61; Jun 19 Thu: EE61; Jun 20 Fri: EE61; Jun 21 Sat: EE61; Jun 22 Sun: EE61; Jun 23 Mon: EE61
[201 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | [11 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | Data Hall | Jan 13 Mon: EE74; Jan 14 Tue: EE74; Jan 15 Wed: EE74; Jan 16 Thu: EE74; Jan 17 Fri: EE74; Jan 18 Sat: EE74; Jan 19 Sun: EE74; Jan 20 Mon: EE74; Jan 21 Tue: EE74; Jan 22 Wed: EE74; Jan 23 Thu: EE74; Jan 24 Fri: EE74; Jan 25 Sat: EE74; Jan 26 Sun: EE74; Jan 27 Mon: EE74; Jan 28 Tue: EE74; Feb 26 Wed: J6; Feb 27 Thu: J6; Feb 28 Fri: J6; Mar 03 Mon: J7; Mar 04 Tue: J7; Mar 05 Wed: J7; Mar 06 Thu: J7; Mar 07 Fri: J7; Mar 10 Mon: EE73; Mar 11 Tue: EE73; Mar 12 Wed: EE73; Mar 13 Thu: EE73; Mar 14 Fri: EE73; Mar 15 Sat: EE73; Mar 16 Sun: EE73; Mar 17 Mon: EE73; Mar 18 Tue: EE73; Mar 19 Wed: EE73; Mar 20 Thu: EE73; Mar 21 Fri: EE73; Mar 24 Mon: EE7; Mar 25 Tue: EE7; Mar 26 Wed: EE7; Mar 27 Thu: EE7; Mar 28 Fri: EE7; Mar 31 Mon: S2; Apr 01 Tue: S2; Apr 02 Wed: S2; Apr 03 Thu: S2; Apr 04 Fri: S2; Apr 07 Mon: ET7; Apr 08 Tue: ET7; Apr 09 Wed: ET7; Apr 10 Thu: ET7; Apr 11 Fri: ET7; Apr 12 Sat: ET7; Apr 13 Sun: ET7; Apr 14 Mon: ET7; Apr 15 Tue: ET7; Apr 16 Wed: ET7; Apr 17 Thu: ET7; Apr 18 Fri: ET7; Apr 21 Mon: EE18; Apr 22 Tue: EE18; Apr 23 Wed: EE18; Apr 24 Thu: EE18; Apr 25 Fri: EE18; Apr 26 Sat: EE18; Apr 27 Sun: EE18; Apr 28 Mon: EE18; Apr 29 Tue: EE18; Apr 30 Wed: EE18; May 01 Thu: EE18; May 02 Fri: EE18; May 03 Sat: EE18; May 04 Sun: EE18; May 05 Mon: EE18; May 06 Tue: EE18; May 07 Wed: EE18; May 08 Thu: EE18; May 09 Fri: EE18
[148 empty] | S1 | S1 | S1 | S1 | S1 |  |  | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | [23 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[150 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10
[155 empty] | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4 | W4
|  | Electrical Room | Jan 03 Fri: T3; Jan 04 Sat: T3; Jan 05 Sun: T3; Jan 06 Mon: T3; Jan 07 Tue: T3; Jan 08 Wed: T3; Jan 09 Thu: T3; Jan 10 Fri: T3; Jan 11 Sat: T3; Jan 12 Sun: T3; Jan 13 Mon: T3; Jan 14 Tue: T3; Jan 15 Wed: T3; Jan 16 Thu: T3; Jan 21 Tue: EE1; Jan 22 Wed: EE1; Jan 23 Thu: EE1; Jan 24 Fri: EE1; Jan 25 Sat: EE1; Jan 26 Sun: EE1; Jan 27 Mon: EE1; Jan 28 Tue: EE1; Jan 29 Wed: EE1; Jan 30 Thu: EE1; Jan 31 Fri: EE1; Feb 01 Sat: EE1; Feb 02 Sun: EE1; Feb 03 Mon: EE1; Feb 04 Tue: J17; Feb 05 Wed: J17; Feb 06 Thu: J17; Feb 07 Fri: GH3; Feb 08 Sat: GH3; Feb 09 Sun: GH3; Feb 10 Mon: GH3; Feb 11 Tue: GH3; Feb 12 Wed: GH3; Feb 13 Thu: GH3; Feb 17 Mon: J36; Feb 18 Tue: J36; Feb 19 Wed: J36; Feb 20 Thu: J36; Feb 21 Fri: J36; Mar 20 Thu: EE29; Mar 21 Fri: EE29; Mar 22 Sat: EE29; Mar 23 Sun: EE29; Mar 24 Mon: EE29; Mar 25 Tue: EE29; Mar 26 Wed: EE29; Mar 27 Thu: EE29; Mar 28 Fri: EE29; Mar 29 Sat: EE29; Mar 30 Sun: EE29; Mar 31 Mon: EE29; Apr 01 Tue: EE29; Apr 02 Wed: EE29; Apr 03 Thu: EE29; Apr 04 Fri: EE29; Apr 05 Sat: EE29; Apr 06 Sun: EE29; Apr 07 Mon: EE29; Apr 08 Tue: EE29; Apr 09 Wed: EE29
[79 empty] | J37 | J37 | J37 | J37 | J37 | J37 | J37 | [16 empty] | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | EE27 | [49 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[102 empty] | EE71 | EE71 | EE71 | EE71 | EE71 | EE71 | EE71
[102 empty] | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28
|  | Mech Gallery | Jan 06 Mon: GA3; Jan 07 Tue: GA3; Jan 08 Wed: GA3; Jan 09 Thu: GA3; Jan 10 Fri: GA3; Jan 27 Mon: EE73; Jan 28 Tue: EE73; Jan 29 Wed: EE73; Jan 30 Thu: EE73; Jan 31 Fri: EE73; Feb 01 Sat: EE73; Feb 02 Sun: EE73; Feb 03 Mon: EE73; Feb 04 Tue: EE73; Feb 05 Wed: EE73; Feb 06 Thu: EE73; Feb 07 Fri: EE73; Feb 10 Mon: GA12; Feb 11 Tue: GA12; Feb 12 Wed: T3; Feb 13 Thu: T3; Feb 14 Fri: T3; Feb 15 Sat: T3; Feb 16 Sun: T3; Feb 17 Mon: T3; Feb 18 Tue: T3; Feb 19 Wed: T3; Feb 20 Thu: T3; Feb 21 Fri: T3; Feb 22 Sat: T3; Feb 23 Sun: T3; Feb 24 Mon: T3; Feb 25 Tue: T3; Feb 26 Wed: J9; Mar 05 Wed: GA6; Mar 06 Thu: GA6; Mar 07 Fri: GA6; Mar 21 Fri: I-R; Mar 22 Sat: I-R; Mar 23 Sun: I-R; Mar 24 Mon: I-R; Mar 25 Tue: I-R; Apr 04 Fri: EE36; Apr 05 Sat: EE36; Apr 06 Sun: EE36; Apr 07 Mon: EE36; Apr 08 Tue: EE36; Apr 09 Wed: EE36; Apr 10 Thu: EE36; Apr 11 Fri: EE36
[122 empty] | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | [6 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
[131 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22
Yardwork | COLO 2 | North | Nov 27 Wed: RC1; Nov 28 Thu: RC1; Nov 29 Fri: RC1; Nov 30 Sat: RC1; Dec 01 Sun: RC1; Dec 02 Mon: RC1; Dec 03 Tue: RC1; Dec 04 Wed: RC1; Dec 05 Thu: RC1; Dec 06 Fri: RC1; Dec 07 Sat: RC1; Dec 08 Sun: RC1; Dec 09 Mon: RC1; Dec 10 Tue: RC1; Dec 11 Wed: RC1; Dec 12 Thu: RC1; Dec 13 Fri: RC1; Dec 14 Sat: RC1; Dec 15 Sun: RC1; Dec 16 Mon: RC1; Dec 17 Tue: RC1; Dec 18 Wed: RC1; Dec 19 Thu: RC1; Dec 20 Fri: RC1; Dec 21 Sat: RC1; Dec 22 Sun: RC1; Dec 23 Mon: RC1; Dec 24 Tue: RC1; Dec 25 Wed: RC1; Dec 26 Thu: RC1
|  | South | Oct 30 Wed: RC1; Oct 31 Thu: RC1; Nov 01 Fri: RC1; Nov 02 Sat: RC1; Nov 03 Sun: RC1; Nov 04 Mon: RC1; Nov 05 Tue: RC1; Nov 06 Wed: RC1; Nov 07 Thu: RC1; Nov 08 Fri: RC1; Nov 09 Sat: RC1; Nov 10 Sun: RC1; Nov 11 Mon: RC1; Nov 12 Tue: RC1; Nov 13 Wed: RC1; Nov 14 Thu: RC1; Nov 15 Fri: RC1; Nov 16 Sat: RC1; Nov 17 Sun: RC1; Nov 18 Mon: RC1; Nov 19 Tue: RC1; Nov 20 Wed: RC1; Nov 21 Thu: RC1; Nov 22 Fri: RC1; Nov 23 Sat: RC1; Nov 24 Sun: RC1; Nov 25 Mon: RC1; Nov 26 Tue: RC1; Jan 31 Fri: EE35; Feb 01 Sat: EE35; Feb 02 Sun: EE35; Feb 03 Mon: EE35; Feb 04 Tue: EE35; Feb 05 Wed: EE35; Feb 06 Thu: EE35; Feb 07 Fri: EE35; Feb 08 Sat: EE35; Feb 09 Sun: EE35; Feb 10 Mon: EE35; Feb 11 Tue: EE35; Feb 12 Wed: EE35; Feb 13 Thu: EE35; Feb 14 Fri: EE35; Feb 15 Sat: EE35; Feb 16 Sun: EE35; Feb 17 Mon: EE35; Feb 18 Tue: EE35; Feb 19 Wed: EE35; Feb 20 Thu: EE35
| COLO 3 | North | Nov 27 Wed: RC1; Nov 28 Thu: RC1; Nov 29 Fri: RC1; Nov 30 Sat: RC1; Dec 01 Sun: RC1; Dec 02 Mon: RC1; Dec 03 Tue: RC1; Dec 04 Wed: RC1; Dec 05 Thu: RC1; Dec 06 Fri: RC1; Dec 07 Sat: RC1; Dec 08 Sun: RC1; Dec 09 Mon: RC1; Dec 10 Tue: RC1; Dec 11 Wed: RC1; Dec 12 Thu: RC1; Dec 13 Fri: RC1; Dec 14 Sat: RC1; Dec 15 Sun: RC1; Dec 16 Mon: RC1; Dec 17 Tue: RC1; Dec 18 Wed: RC1; Dec 19 Thu: RC1; Dec 20 Fri: RC1; Dec 21 Sat: RC1; Dec 22 Sun: RC1; Dec 23 Mon: RC1; Dec 24 Tue: RC1; Dec 25 Wed: RC1; Dec 26 Thu: RC1; Dec 27 Fri: EE35; Dec 28 Sat: EE35; Dec 29 Sun: EE35; Dec 30 Mon: EE35; Dec 31 Tue: EE35; Jan 01 Wed: EE35; Jan 02 Thu: EE35; Jan 03 Fri: EE35; Jan 04 Sat: EE35; Jan 05 Sun: EE35; Jan 06 Mon: EE35; Jan 07 Tue: EE35; Jan 08 Wed: EE35; Jan 09 Thu: EE35; Jan 10 Fri: EE35; Jan 11 Sat: EE35; Jan 12 Sun: EE35; Jan 13 Mon: EE35; Jan 14 Tue: EE35; Jan 15 Wed: EE35; Jan 16 Thu: EE35; Jan 17 Fri: EE35
|  | South | Nov 20 Wed: RC1; Nov 21 Thu: RC1; Nov 22 Fri: RC1; Nov 23 Sat: RC1; Nov 24 Sun: RC1; Nov 25 Mon: RC1; Nov 26 Tue: RC1; Nov 27 Wed: RC1; Nov 28 Thu: RC1; Nov 29 Fri: RC1; Nov 30 Sat: RC1; Dec 01 Sun: RC1; Dec 02 Mon: RC1; Dec 03 Tue: RC1; Dec 04 Wed: RC1; Dec 05 Thu: RC1; Dec 06 Fri: RC1; Dec 07 Sat: RC1; Dec 08 Sun: RC1; Dec 09 Mon: RC1; Dec 10 Tue: RC1; Dec 11 Wed: RC1; Dec 12 Thu: RC1; Dec 13 Fri: RC1; Dec 14 Sat: RC1; Dec 15 Sun: RC1; Dec 16 Mon: RC1; Dec 17 Tue: RC1; Dec 18 Wed: RC1
| COLO 4 | North | Dec 12 Thu: RC1; Dec 13 Fri: RC1; Dec 14 Sat: RC1; Dec 15 Sun: RC1; Dec 16 Mon: RC1; Dec 17 Tue: RC1; Dec 18 Wed: RC1; Dec 19 Thu: RC1; Dec 20 Fri: RC1; Dec 21 Sat: RC1; Dec 22 Sun: RC1; Dec 23 Mon: RC1; Dec 24 Tue: RC1; Dec 25 Wed: RC1; Dec 26 Thu: RC1; Dec 27 Fri: RC1; Dec 28 Sat: RC1; Dec 29 Sun: RC1; Dec 30 Mon: RC1; Dec 31 Tue: RC1; Jan 01 Wed: RC1; Jan 02 Thu: RC1; Jan 03 Fri: RC1; Jan 04 Sat: RC1; Jan 05 Sun: RC1; Jan 06 Mon: RC1; Jan 07 Tue: RC1; Jan 08 Wed: RC1; Jan 09 Thu: RC1; Jan 10 Fri: RC1; Jan 13 Mon: EE35; Jan 14 Tue: EE35; Jan 15 Wed: EE35; Jan 16 Thu: EE35; Jan 17 Fri: EE35; Jan 18 Sat: EE35; Jan 19 Sun: EE35; Jan 20 Mon: EE35; Jan 21 Tue: EE35; Jan 22 Wed: EE35; Jan 23 Thu: EE35; Jan 24 Fri: EE35; Jan 25 Sat: EE35; Jan 26 Sun: EE35; Jan 27 Mon: EE35; Jan 28 Tue: EE35; Jan 29 Wed: EE35; Jan 30 Thu: EE35; Jan 31 Fri: EE35
|  | South | Dec 05 Thu: RC1; Dec 06 Fri: RC1; Dec 07 Sat: RC1; Dec 08 Sun: RC1; Dec 09 Mon: RC1; Dec 10 Tue: RC1; Dec 11 Wed: RC1; Dec 12 Thu: RC1; Dec 13 Fri: RC1; Dec 14 Sat: RC1; Dec 15 Sun: RC1; Dec 16 Mon: RC1; Dec 17 Tue: RC1; Dec 18 Wed: RC1; Dec 19 Thu: RC1; Dec 20 Fri: RC1; Dec 21 Sat: RC1; Dec 22 Sun: RC1; Dec 23 Mon: RC1; Dec 24 Tue: RC1; Dec 25 Wed: RC1; Dec 26 Thu: RC1; Dec 27 Fri: RC1; Dec 28 Sat: RC1; Dec 29 Sun: RC1; Dec 30 Mon: RC1; Dec 31 Tue: RC1; Jan 01 Wed: RC1; Jan 02 Thu: RC1; Jan 03 Fri: RC1; Jan 06 Mon: EE46; Jan 07 Tue: EE46; Jan 08 Wed: EE46; Jan 09 Thu: EE46; Jan 10 Fri: EE46; Jan 11 Sat: EE46; Jan 12 Sun: EE46; Jan 13 Mon: EE46; Jan 14 Tue: EE46; Jan 15 Wed: EE46; Jan 16 Thu: EE46; Jan 17 Fri: EE46; Jan 18 Sat: EE46; Jan 19 Sun: EE46; Jan 20 Mon: EE46; Jan 21 Tue: EE46; Jan 22 Wed: EE46; Jan 23 Thu: EE46; Jan 24 Fri: EE46
| COLO 5 | East | Nov 06 Wed: RC1; Nov 07 Thu: RC1; Nov 08 Fri: RC1; Nov 09 Sat: RC1; Nov 10 Sun: RC1; Nov 11 Mon: RC1; Nov 12 Tue: RC1; Nov 13 Wed: RC1; Nov 14 Thu: RC1; Nov 15 Fri: RC1; Nov 16 Sat: RC1; Nov 17 Sun: RC1; Nov 18 Mon: RC1; Nov 19 Tue: RC1; Nov 20 Wed: RC1; Nov 21 Thu: RC1; Nov 22 Fri: RC1; Nov 23 Sat: RC1; Nov 24 Sun: RC1; Nov 25 Mon: RC1; Nov 26 Tue: RC1; Nov 27 Wed: RC1; Nov 28 Thu: RC1; Nov 29 Fri: RC1; Nov 30 Sat: RC1; Dec 01 Sun: RC1; Dec 02 Mon: RC1; Dec 03 Tue: RC1; Dec 04 Wed: RC1
|  | West | Dec 05 Thu: RC1; Dec 06 Fri: RC1; Dec 07 Sat: RC1; Dec 08 Sun: RC1; Dec 09 Mon: RC1; Dec 10 Tue: RC1; Dec 11 Wed: RC1; Dec 12 Thu: RC1; Dec 13 Fri: RC1; Dec 14 Sat: RC1; Dec 15 Sun: RC1; Dec 16 Mon: RC1; Dec 17 Tue: RC1; Dec 18 Wed: RC1; Dec 19 Thu: RC1; Dec 20 Fri: RC1; Dec 21 Sat: RC1; Dec 22 Sun: RC1; Dec 23 Mon: RC1; Dec 24 Tue: RC1; Dec 25 Wed: RC1; Dec 26 Thu: RC1; Dec 27 Fri: RC1; Dec 28 Sat: RC1; Dec 29 Sun: RC1; Dec 30 Mon: RC1; Dec 31 Tue: RC1; Jan 01 Wed: RC1; Jan 02 Thu: RC1; Jan 03 Fri: RC1
[45 empty] | EE34 | EE34 | EE34 | EE34 | EE34 | EE34 | EE34
COLO 2 | All | CX - Microsoft | Apr 30 Wed: MS1; May 01 Thu: MS1; May 02 Fri: MS1; May 03 Sat: MS1; May 04 Sun: MS1; May 05 Mon: MS1; May 06 Tue: MS1; May 07 Wed: MS1; May 08 Thu: MS1; May 09 Fri: MS1; May 10 Sat: MS1; May 11 Sun: MS1; May 12 Mon: MS1; May 13 Tue: MS1; May 14 Wed: MS1; May 15 Thu: MS1; May 16 Fri: MS1; May 17 Sat: MS1; May 18 Sun: MS1; May 19 Mon: MS1; May 20 Tue: MS1; May 21 Wed: MS1; May 22 Thu: MS1; May 23 Fri: MS1; May 24 Sat: MS1; May 25 Sun: MS1; May 26 Mon: MS1; May 27 Tue: MS1; May 28 Wed: MS1; May 29 Thu: MS1; May 30 Fri: MS1; May 31 Sat: MS1; Jun 01 Sun: MS1; Jun 02 Mon: MS1; Jun 03 Tue: MS1; Jun 04 Wed: MS2; Jun 05 Thu: MS2
| Cell 1 | CX - L2 | Jan 22 Wed: EE58; Jan 23 Thu: EE58; Jan 24 Fri: EE58; Jan 25 Sat: EE58; Jan 26 Sun: EE58; Jan 27 Mon: EE58; Jan 28 Tue: EE58; Jan 31 Fri: EE61; Feb 01 Sat: EE61; Feb 02 Sun: EE61; Feb 03 Mon: EE61; Feb 04 Tue: EE61; Feb 05 Wed: EE61; Feb 06 Thu: EE61; Feb 13 Thu: EE57; Feb 14 Fri: EE57; Feb 15 Sat: EE57; Feb 16 Sun: EE57; Feb 17 Mon: EE57; Feb 18 Tue: EE57; Feb 19 Wed: EE57
[87 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 |  |  | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62
[87 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 |  |  | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
|  | CX - L3 | Mar 19 Wed: EE57; Mar 20 Thu: EE57; Mar 21 Fri: EE57; Mar 22 Sat: EE57; Mar 23 Sun: EE57; Mar 24 Mon: EE57; Mar 25 Tue: EE57; Mar 26 Wed: EE62; Mar 27 Thu: EE62; Mar 28 Fri: EE62; Mar 29 Sat: EE62; Mar 30 Sun: EE62; Mar 31 Mon: EE62; Apr 01 Tue: EE62; Apr 02 Wed: EE60; Apr 03 Thu: EE60; Apr 04 Fri: EE60; Apr 05 Sat: EE60; Apr 06 Sun: EE60; Apr 07 Mon: EE60; Apr 08 Tue: EE60; Apr 09 Wed: EE59; Apr 10 Thu: EE59; Apr 11 Fri: EE59; Apr 12 Sat: EE59; Apr 13 Sun: EE59; Apr 14 Mon: EE59; Apr 15 Tue: EE59; Apr 16 Wed: EE59; Apr 17 Thu: EE59; Apr 18 Fri: EE59; Apr 19 Sat: EE59; Apr 20 Sun: EE59; Apr 21 Mon: EE59; Apr 22 Tue: EE59; Apr 23 Wed: EE61; Apr 24 Thu: EE61; Apr 25 Fri: EE61; Apr 26 Sat: EE61; Apr 27 Sun: EE61; Apr 28 Mon: EE61; Apr 29 Tue: EE61
[150 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[150 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | Jan 10 Fri: EE17; Jan 11 Sat: EE17; Jan 12 Sun: EE17; Jan 13 Mon: EE17; Jan 14 Tue: EE17; Jan 15 Wed: EE17; Jan 16 Thu: EE17; Jan 17 Fri: EE17; Jan 18 Sat: EE17; Jan 19 Sun: EE17; Jan 20 Mon: EE17; Jan 21 Tue: EE17; Jan 22 Wed: EE17; Jan 23 Thu: EE17; Jan 24 Fri: EE17; Jan 25 Sat: EE17; Jan 26 Sun: EE17; Jan 27 Mon: EE17; Jan 28 Tue: EE17; Jan 29 Wed: EE17; Jan 30 Thu: EE17; Feb 07 Fri: ALL3; Feb 08 Sat: ALL3; Feb 09 Sun: ALL3; Feb 10 Mon: ALL3; Feb 11 Tue: ALL3; Feb 12 Wed: ALL3; Feb 13 Thu: ALL3
[82 empty] | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | Dec 17 Tue: EE29; Dec 18 Wed: EE29; Dec 19 Thu: EE29; Dec 20 Fri: EE29; Dec 21 Sat: EE29; Dec 22 Sun: EE29; Dec 23 Mon: EE29; Dec 24 Tue: EE29; Dec 25 Wed: EE29; Dec 26 Thu: EE29; Dec 27 Fri: EE29; Dec 28 Sat: EE29; Dec 29 Sun: EE29; Dec 30 Mon: EE29; Dec 31 Tue: EE29; Jan 01 Wed: EE29; Jan 02 Thu: EE29; Jan 03 Fri: EE29; Jan 04 Sat: EE29; Jan 05 Sun: EE29; Jan 06 Mon: EE29; Jan 07 Tue: EE29; Jan 08 Wed: EE29; Jan 10 Fri: ALL3; Jan 11 Sat: ALL3; Jan 12 Sun: ALL3; Jan 13 Mon: ALL3; Jan 14 Tue: ALL3; Jan 15 Wed: ALL3; Jan 16 Thu: ALL3
| Cell 2 | CX - L2 | Feb 13 Thu: EE57; Feb 14 Fri: EE57; Feb 15 Sat: EE57; Feb 16 Sun: EE57; Feb 17 Mon: EE57; Feb 18 Tue: EE57; Feb 19 Wed: EE57; Feb 20 Thu: EE62; Feb 21 Fri: EE62; Feb 22 Sat: EE62; Feb 23 Sun: EE62; Feb 24 Mon: EE62; Feb 25 Tue: EE62; Feb 26 Wed: EE62; Feb 27 Thu: EE60; Feb 28 Fri: EE60; Mar 01 Sat: EE60; Mar 02 Sun: EE60; Mar 03 Mon: EE60; Mar 04 Tue: EE60; Mar 05 Wed: EE60; Mar 06 Thu: EE59; Mar 07 Fri: EE59; Mar 08 Sat: EE59; Mar 09 Sun: EE59; Mar 10 Mon: EE59; Mar 11 Tue: EE59; Mar 12 Wed: EE59
[116 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[116 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | Mar 19 Wed: EE57; Mar 20 Thu: EE57; Mar 21 Fri: EE57; Mar 22 Sat: EE57; Mar 23 Sun: EE57; Mar 24 Mon: EE57; Mar 25 Tue: EE57; Mar 26 Wed: EE62; Mar 27 Thu: EE62; Mar 28 Fri: EE62; Mar 29 Sat: EE62; Mar 30 Sun: EE62; Mar 31 Mon: EE62; Apr 01 Tue: EE62; Apr 02 Wed: EE60; Apr 03 Thu: EE60; Apr 04 Fri: EE60; Apr 05 Sat: EE60; Apr 06 Sun: EE60; Apr 07 Mon: EE60; Apr 08 Tue: EE60; Apr 09 Wed: EE59; Apr 10 Thu: EE59; Apr 11 Fri: EE59; Apr 12 Sat: EE59; Apr 13 Sun: EE59; Apr 14 Mon: EE59; Apr 15 Tue: EE59; Apr 16 Wed: EE59; Apr 17 Thu: EE59; Apr 18 Fri: EE59; Apr 19 Sat: EE59; Apr 20 Sun: EE59; Apr 21 Mon: EE59; Apr 22 Tue: EE59; Apr 23 Wed: EE61; Apr 24 Thu: EE61; Apr 25 Fri: EE61; Apr 26 Sat: EE61; Apr 27 Sun: EE61; Apr 28 Mon: EE61; Apr 29 Tue: EE61
[150 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[150 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | Jan 17 Fri: EE17; Jan 18 Sat: EE17; Jan 19 Sun: EE17; Jan 20 Mon: EE17; Jan 21 Tue: EE17; Jan 22 Wed: EE17; Jan 23 Thu: EE17; Jan 24 Fri: EE17; Jan 25 Sat: EE17; Jan 26 Sun: EE17; Jan 27 Mon: EE17; Jan 28 Tue: EE17; Jan 29 Wed: EE17; Jan 30 Thu: EE17; Jan 31 Fri: EE18; Feb 01 Sat: EE18; Feb 02 Sun: EE18; Feb 03 Mon: EE18; Feb 04 Tue: EE18; Feb 05 Wed: EE18; Feb 06 Thu: EE18; Feb 07 Fri: EE18; Feb 08 Sat: EE18; Feb 09 Sun: EE18; Feb 10 Mon: EE18; Feb 11 Tue: EE18; Feb 12 Wed: EE18; Feb 13 Thu: EE18; Feb 14 Fri: EE18; Feb 15 Sat: EE18; Feb 16 Sun: EE18; Feb 17 Mon: EE18; Feb 18 Tue: EE18; Feb 19 Wed: EE18; Feb 20 Thu: EE18; Feb 21 Fri: ALL3; Feb 22 Sat: ALL3; Feb 23 Sun: ALL3; Feb 24 Mon: ALL3; Feb 25 Tue: ALL3; Feb 26 Wed: ALL3; Feb 27 Thu: ALL3
|  | Electrical Room | Jan 09 Thu: EE29; Jan 10 Fri: EE29; Jan 11 Sat: EE29; Jan 12 Sun: EE29; Jan 13 Mon: EE29; Jan 14 Tue: EE29; Jan 15 Wed: EE29; Jan 16 Thu: EE29; Jan 17 Fri: EE29; Jan 18 Sat: EE29; Jan 19 Sun: EE29; Jan 20 Mon: EE29; Jan 21 Tue: EE29; Jan 22 Wed: EE29; Jan 23 Thu: EE29; Jan 24 Fri: EE29; Jan 25 Sat: EE29; Jan 26 Sun: EE29; Jan 27 Mon: EE29; Jan 28 Tue: EE29; Jan 29 Wed: EE29; Jan 30 Thu: ALL3; Jan 31 Fri: ALL3; Feb 01 Sat: ALL3; Feb 02 Sun: ALL3; Feb 03 Mon: ALL3; Feb 04 Tue: ALL3; Feb 05 Wed: ALL3
|  | Mech Gallery | Jan 14 Tue: EE35; Jan 15 Wed: EE35; Jan 16 Thu: EE35; Jan 17 Fri: EE35; Jan 18 Sat: EE35; Jan 19 Sun: EE35; Jan 20 Mon: EE35; Jan 21 Tue: EE35; Jan 22 Wed: EE35; Jan 23 Thu: EE35; Jan 24 Fri: EE35
[89 empty] | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36
| Cell 3 | CX - L2 | Feb 19 Wed: EE57; Feb 20 Thu: EE57; Feb 21 Fri: EE57; Feb 22 Sat: EE57; Feb 23 Sun: EE57; Feb 24 Mon: EE57; Feb 25 Tue: EE57; Feb 26 Wed: EE62; Feb 27 Thu: EE62; Feb 28 Fri: EE62; Mar 01 Sat: EE62; Mar 02 Sun: EE62; Mar 03 Mon: EE62; Mar 04 Tue: EE62; Mar 05 Wed: EE59; Mar 06 Thu: EE59; Mar 07 Fri: EE59; Mar 08 Sat: EE59; Mar 09 Sun: EE59; Mar 10 Mon: EE59; Mar 11 Tue: EE59
[115 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[122 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
|  | CX - L3 | Mar 19 Wed: EE57; Mar 20 Thu: EE57; Mar 21 Fri: EE57; Mar 22 Sat: EE57; Mar 23 Sun: EE57; Mar 24 Mon: EE57; Mar 25 Tue: EE57; Mar 26 Wed: EE62; Mar 27 Thu: EE62; Mar 28 Fri: EE62; Mar 29 Sat: EE62; Mar 30 Sun: EE62; Mar 31 Mon: EE62; Apr 01 Tue: EE62; Apr 02 Wed: EE60; Apr 03 Thu: EE60; Apr 04 Fri: EE60; Apr 05 Sat: EE60; Apr 06 Sun: EE60; Apr 07 Mon: EE60; Apr 08 Tue: EE60; Apr 09 Wed: EE59; Apr 10 Thu: EE59; Apr 11 Fri: EE59; Apr 12 Sat: EE59; Apr 13 Sun: EE59; Apr 14 Mon: EE59; Apr 15 Tue: EE59; Apr 16 Wed: EE59; Apr 17 Thu: EE59; Apr 18 Fri: EE59; Apr 19 Sat: EE59; Apr 20 Sun: EE59; Apr 21 Mon: EE59; Apr 22 Tue: EE59; Apr 23 Wed: EE61; Apr 24 Thu: EE61; Apr 25 Fri: EE61; Apr 26 Sat: EE61; Apr 27 Sun: EE61; Apr 28 Mon: EE61; Apr 29 Tue: EE61
[150 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[150 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | Jan 29 Wed: EE18; Jan 30 Thu: EE18; Jan 31 Fri: EE18; Feb 01 Sat: EE18; Feb 02 Sun: EE18; Feb 03 Mon: EE18; Feb 04 Tue: EE18; Feb 05 Wed: EE18; Feb 06 Thu: EE18; Feb 07 Fri: EE18; Feb 08 Sat: EE18; Feb 09 Sun: EE18; Feb 10 Mon: EE18; Feb 11 Tue: EE18; Feb 12 Wed: EE18; Feb 13 Thu: EE18; Feb 14 Fri: EE18; Feb 15 Sat: EE18; Feb 16 Sun: EE18; Feb 17 Mon: EE18; Feb 18 Tue: EE18; Feb 28 Fri: ALL3; Mar 01 Sat: ALL3; Mar 02 Sun: ALL3; Mar 03 Mon: ALL3; Mar 04 Tue: ALL3; Mar 05 Wed: ALL3; Mar 06 Thu: ALL3
[101 empty] | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7
|  | Electrical Room | Dec 19 Thu: EE29; Dec 20 Fri: EE29; Dec 21 Sat: EE29; Dec 22 Sun: EE29; Dec 23 Mon: EE29; Dec 24 Tue: EE29; Dec 25 Wed: EE29; Dec 26 Thu: EE29; Dec 27 Fri: EE29; Dec 28 Sat: EE29; Dec 29 Sun: EE29; Dec 30 Mon: EE29; Dec 31 Tue: EE29; Jan 01 Wed: EE29; Jan 02 Thu: EE29; Jan 03 Fri: EE29; Jan 04 Sat: EE29; Jan 05 Sun: EE29; Jan 06 Mon: EE29; Jan 07 Tue: EE29; Jan 08 Wed: EE29; Jan 09 Thu: EE29; Jan 10 Fri: EE29
[75 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
|  | Mech Gallery | Jan 24 Fri: I-R; Jan 25 Sat: I-R; Jan 26 Sun: I-R; Jan 27 Mon: I-R; Jan 28 Tue: I-R; Feb 07 Fri: EE36; Feb 08 Sat: EE36; Feb 09 Sun: EE36; Feb 10 Mon: EE36; Feb 11 Tue: EE36; Feb 12 Wed: EE36; Feb 13 Thu: EE36; Feb 14 Fri: EE36
[93 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
| Cell 4 | CX - L2 | Mar 05 Wed: EE57; Mar 06 Thu: EE57; Mar 07 Fri: EE57; Mar 08 Sat: EE57; Mar 09 Sun: EE57; Mar 10 Mon: EE57; Mar 11 Tue: EE57; Mar 12 Wed: EE62; Mar 13 Thu: EE62; Mar 14 Fri: EE62; Mar 15 Sat: EE62; Mar 16 Sun: EE62; Mar 17 Mon: EE62; Mar 18 Tue: EE62; Mar 19 Wed: EE60; Mar 20 Thu: EE60; Mar 21 Fri: EE60; Mar 22 Sat: EE60; Mar 23 Sun: EE60; Mar 24 Mon: EE60; Mar 25 Tue: EE60
[136 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
[136 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
|  | CX - L3 | Mar 19 Wed: EE57; Mar 20 Thu: EE57; Mar 21 Fri: EE57; Mar 22 Sat: EE57; Mar 23 Sun: EE57; Mar 24 Mon: EE57; Mar 25 Tue: EE57; Mar 26 Wed: EE62; Mar 27 Thu: EE62; Mar 28 Fri: EE62; Mar 29 Sat: EE62; Mar 30 Sun: EE62; Mar 31 Mon: EE62; Apr 01 Tue: EE62; Apr 02 Wed: EE58; Apr 03 Thu: EE58; Apr 04 Fri: EE58; Apr 05 Sat: EE58; Apr 06 Sun: EE58; Apr 07 Mon: EE58; Apr 08 Tue: EE58; Apr 09 Wed: EE60; Apr 10 Thu: EE60; Apr 11 Fri: EE60; Apr 12 Sat: EE60; Apr 13 Sun: EE60; Apr 14 Mon: EE60; Apr 15 Tue: EE60; Apr 23 Wed: EE61; Apr 24 Thu: EE61; Apr 25 Fri: EE61; Apr 26 Sat: EE61; Apr 27 Sun: EE61; Apr 28 Mon: EE61; Apr 29 Tue: EE61
[150 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | [7 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | Data Hall | Feb 12 Wed: EE18; Feb 13 Thu: EE18; Feb 14 Fri: EE18; Feb 15 Sat: EE18; Feb 16 Sun: EE18; Feb 17 Mon: EE18; Feb 18 Tue: EE18; Feb 19 Wed: EE18; Feb 20 Thu: EE18; Feb 21 Fri: EE18; Feb 22 Sat: EE18; Feb 23 Sun: EE18; Feb 24 Mon: EE18; Feb 25 Tue: EE18; Feb 26 Wed: EE18; Feb 27 Thu: EE18; Feb 28 Fri: EE18; Mar 01 Sat: EE18; Mar 02 Sun: EE18; Mar 03 Mon: EE18; Mar 04 Tue: EE18; Mar 07 Fri: ALL3; Mar 08 Sat: ALL3; Mar 09 Sun: ALL3; Mar 10 Mon: ALL3; Mar 11 Tue: ALL3; Mar 12 Wed: ALL3; Mar 13 Thu: ALL3
[115 empty] | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7
|  | Electrical Room | Dec 27 Fri: EE28; Dec 28 Sat: EE28; Dec 29 Sun: EE28; Dec 30 Mon: EE28; Dec 31 Tue: EE28; Jan 01 Wed: EE28; Jan 02 Thu: EE28; Jan 03 Fri: EE28; Jan 13 Mon: EE29; Jan 14 Tue: EE29; Jan 15 Wed: EE29; Jan 16 Thu: EE29; Jan 17 Fri: EE29; Jan 18 Sat: EE29; Jan 19 Sun: EE29; Jan 20 Mon: EE29; Jan 21 Tue: EE29; Jan 22 Wed: EE29; Jan 23 Thu: EE29; Jan 24 Fri: EE29; Jan 25 Sat: EE29; Jan 26 Sun: EE29; Jan 27 Mon: EE29; Jan 28 Tue: EE29; Jan 29 Wed: EE29; Jan 30 Thu: EE29; Jan 31 Fri: EE29; Feb 03 Mon: ALL3; Feb 04 Tue: ALL3; Feb 05 Wed: ALL3; Feb 06 Thu: ALL3; Feb 07 Fri: ALL3
|  | Mech Gallery | Jan 24 Fri: ET22; Jan 25 Sat: ET22; Jan 26 Sun: ET22; Jan 27 Mon: ET22; Jan 28 Tue: ET22; Jan 29 Wed: ET22; Jan 30 Thu: ET22; Jan 31 Fri: ET22; Feb 01 Sat: ET22; Feb 02 Sun: ET22; Feb 03 Mon: ET22; Feb 04 Tue: ET22; Feb 05 Wed: ET22; Feb 06 Thu: ET22; Feb 07 Fri: ET22; Feb 11 Tue: EE35; Feb 12 Wed: EE35; Feb 13 Thu: EE35; Feb 14 Fri: EE35; Feb 15 Sat: EE35; Feb 16 Sun: EE35; Feb 17 Mon: EE35; Feb 18 Tue: EE35; Feb 19 Wed: EE35; Feb 20 Thu: EE35; Feb 21 Fri: EE35
[103 empty] | I-R | I-R | I-R | I-R | I-R | [9 empty] | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36
COLO 3 | All | CX - Microsoft | May 27 Tue: MS1; May 28 Wed: MS1; May 29 Thu: MS1; May 30 Fri: MS1; May 31 Sat: MS1; Jun 01 Sun: MS1; Jun 02 Mon: MS1; Jun 03 Tue: MS1; Jun 04 Wed: MS1; Jun 05 Thu: MS1; Jun 06 Fri: MS1; Jun 07 Sat: MS1; Jun 08 Sun: MS1; Jun 09 Mon: MS1; Jun 10 Tue: MS1; Jun 11 Wed: MS1; Jun 12 Thu: MS1; Jun 13 Fri: MS1; Jun 14 Sat: MS1; Jun 15 Sun: MS1; Jun 16 Mon: MS1; Jun 17 Tue: MS1; Jun 18 Wed: MS1; Jun 19 Thu: MS1; Jun 20 Fri: MS1; Jun 21 Sat: MS1; Jun 22 Sun: MS1; Jun 23 Mon: MS1; Jun 24 Tue: MS1; Jun 25 Wed: MS1; Jun 26 Thu: MS1; Jun 27 Fri: MS1; Jun 28 Sat: MS1; Jun 29 Sun: MS1; Jun 30 Mon: MS1; Jul 01 Tue: MS2; Jul 02 Wed: MS2
| Cell 1 | CX - L1 | Feb 03 Mon: EE63; Feb 10 Mon: EE62
|  | CX - L2 | Mar 18 Tue: EE57; Mar 19 Wed: EE57; Mar 20 Thu: EE57; Mar 21 Fri: EE57; Mar 22 Sat: EE57; Mar 23 Sun: EE57; Mar 24 Mon: EE57; Mar 25 Tue: EE62; Mar 26 Wed: EE62; Mar 27 Thu: EE62; Mar 28 Fri: EE62; Mar 29 Sat: EE62; Mar 30 Sun: EE62; Mar 31 Mon: EE62; Apr 01 Tue: EE60; Apr 02 Wed: EE60; Apr 03 Thu: EE60; Apr 04 Fri: EE60; Apr 05 Sat: EE60; Apr 06 Sun: EE60; Apr 07 Mon: EE60; Apr 08 Tue: EE59; Apr 09 Wed: EE59; Apr 10 Thu: EE59; Apr 11 Fri: EE59; Apr 12 Sat: EE59; Apr 13 Sun: EE59; Apr 14 Mon: EE59
[149 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[149 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | May 02 Fri: EE57; May 03 Sat: EE57; May 04 Sun: EE57; May 05 Mon: EE57; May 06 Tue: EE57; May 07 Wed: EE57; May 08 Thu: EE57; May 09 Fri: EE62; May 10 Sat: EE62; May 11 Sun: EE62; May 12 Mon: EE62; May 13 Tue: EE62; May 14 Wed: EE62; May 15 Thu: EE62; May 16 Fri: EE61; May 17 Sat: EE61; May 18 Sun: EE61; May 19 Mon: EE61; May 20 Tue: EE61; May 21 Wed: EE61; May 22 Thu: EE61
[190 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
[194 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[194 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
[194 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
|  | Data Hall | Jan 27 Mon: EE7; Jan 28 Tue: EE7; Jan 29 Wed: EE7; Jan 30 Thu: EE7; Jan 31 Fri: EE7; Feb 03 Mon: S2; Feb 04 Tue: S2; Feb 05 Wed: S2; Feb 06 Thu: S2; Feb 07 Fri: S2; Feb 10 Mon: ET7; Feb 11 Tue: ET7; Feb 12 Wed: ET7; Feb 13 Thu: ET7; Feb 14 Fri: ET7; Feb 15 Sat: ET7; Feb 16 Sun: ET7; Feb 17 Mon: ET7; Feb 18 Tue: ET7; Feb 19 Wed: ET7; Feb 20 Thu: ET7; Feb 21 Fri: ET7; Mar 03 Mon: ALL3; Mar 04 Tue: ALL3; Mar 05 Wed: ALL3; Mar 06 Thu: ALL3; Mar 07 Fri: ALL3
[92 empty] | S1 | S1 | S1 | S1 | S1 |  |  | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17
[94 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [5 empty] | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | Jan 06 Mon: EE28; Jan 07 Tue: EE28; Jan 08 Wed: EE28; Jan 09 Thu: EE28; Jan 10 Fri: EE28; Jan 13 Mon: EE29; Jan 14 Tue: EE29; Jan 15 Wed: EE29; Jan 16 Thu: EE29; Jan 17 Fri: EE29; Jan 18 Sat: EE29; Jan 19 Sun: EE29; Jan 20 Mon: EE29; Jan 21 Tue: EE29; Jan 22 Wed: EE29; Jan 23 Thu: EE29; Jan 24 Fri: EE29; Jan 25 Sat: EE29; Jan 26 Sun: EE29; Jan 27 Mon: EE29; Jan 28 Tue: EE29; Jan 29 Wed: EE29; Jan 30 Thu: EE29; Jan 31 Fri: EE29; Feb 03 Mon: EE23; Feb 04 Tue: EE23; Feb 05 Wed: EE23; Feb 06 Thu: EE23; Feb 07 Fri: EE23; Feb 10 Mon: J36; Feb 11 Tue: J36; Feb 12 Wed: J36; Feb 13 Thu: J36; Feb 14 Fri: J36; Feb 17 Mon: ALL3; Feb 18 Tue: ALL3; Feb 19 Wed: ALL3; Feb 20 Thu: ALL3; Feb 21 Fri: ALL3
|  | Mech Gallery | Jan 28 Tue: EE35; Jan 29 Wed: EE35; Jan 30 Thu: EE35; Jan 31 Fri: EE35; Feb 01 Sat: EE35; Feb 02 Sun: EE35; Feb 03 Mon: EE35; Feb 04 Tue: EE35; Feb 05 Wed: EE35; Feb 06 Thu: EE35; Feb 07 Fri: EE35
[103 empty] | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36 | EE36
| Cell 2 | CX - L1 | Jan 20 Mon: EE57; Jan 22 Wed: EE59; Feb 11 Tue: EE62; Feb 17 Mon: EE63
EE60
EE61
EE58
|  | CX - L2 | Mar 18 Tue: EE57; Mar 19 Wed: EE57; Mar 20 Thu: EE57; Mar 21 Fri: EE57; Mar 22 Sat: EE57; Mar 23 Sun: EE57; Mar 24 Mon: EE57; Mar 25 Tue: EE62; Mar 26 Wed: EE62; Mar 27 Thu: EE62; Mar 28 Fri: EE62; Mar 29 Sat: EE62; Mar 30 Sun: EE62; Mar 31 Mon: EE62; Apr 01 Tue: EE60; Apr 02 Wed: EE60; Apr 03 Thu: EE60; Apr 04 Fri: EE60; Apr 05 Sat: EE60; Apr 06 Sun: EE60; Apr 07 Mon: EE60; Apr 08 Tue: EE59; Apr 09 Wed: EE59; Apr 10 Thu: EE59; Apr 11 Fri: EE59; Apr 12 Sat: EE59; Apr 13 Sun: EE59; Apr 14 Mon: EE59
[149 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[149 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | CX - L3 | May 02 Fri: EE57; May 03 Sat: EE57; May 04 Sun: EE57; May 05 Mon: EE57; May 06 Tue: EE57; May 07 Wed: EE57; May 08 Thu: EE57; May 09 Fri: EE62; May 10 Sat: EE62; May 11 Sun: EE62; May 12 Mon: EE62; May 13 Tue: EE62; May 14 Wed: EE62; May 15 Thu: EE62; May 16 Fri: EE63; May 17 Sat: EE63; May 18 Sun: EE63; May 19 Mon: EE63; May 20 Tue: EE63; May 21 Wed: EE63; May 22 Thu: EE63
[190 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
[194 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[194 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
|  | Data Hall | Jan 20 Mon: J7; Jan 21 Tue: J7; Jan 22 Wed: J7; Jan 23 Thu: J7; Jan 24 Fri: J7; Jan 27 Mon: EE73; Jan 28 Tue: EE73; Jan 29 Wed: EE73; Jan 30 Thu: EE73; Jan 31 Fri: EE73; Feb 01 Sat: EE73; Feb 02 Sun: EE73; Feb 03 Mon: EE73; Feb 04 Tue: EE73; Feb 05 Wed: EE73; Feb 06 Thu: EE73; Feb 07 Fri: EE73; Feb 10 Mon: EE7; Feb 11 Tue: EE7; Feb 12 Wed: EE7; Feb 13 Thu: EE7; Feb 14 Fri: EE7; Feb 17 Mon: S2; Feb 18 Tue: S2; Feb 19 Wed: S2; Feb 20 Thu: S2; Feb 21 Fri: S2; Feb 24 Mon: ET7; Feb 25 Tue: ET7; Feb 26 Wed: ET7; Feb 27 Thu: ET7; Feb 28 Fri: ET7; Mar 01 Sat: ET7; Mar 02 Sun: ET7; Mar 03 Mon: ET7; Mar 04 Tue: ET7; Mar 05 Wed: ET7; Mar 06 Thu: ET7; Mar 07 Fri: ET7; Mar 10 Mon: ALL3; Mar 11 Tue: ALL3; Mar 12 Wed: ALL3; Mar 13 Thu: ALL3; Mar 14 Fri: ALL3
[106 empty] | S1 | S1 | S1 | S1 | S1 |  |  | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17
[108 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [5 empty] | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | Jan 09 Thu: EE72; Jan 10 Fri: EE72; Jan 11 Sat: EE72; Jan 12 Sun: EE72; Jan 13 Mon: EE72; Jan 14 Tue: EE72; Jan 15 Wed: EE72; Jan 16 Thu: EE72; Jan 17 Fri: EE72; Jan 18 Sat: EE72; Jan 19 Sun: EE72; Jan 20 Mon: EE72; Jan 21 Tue: EE72; Jan 22 Wed: EE72; Feb 03 Mon: EE29; Feb 04 Tue: EE29; Feb 05 Wed: EE29; Feb 06 Thu: EE29; Feb 07 Fri: EE29; Feb 08 Sat: EE29; Feb 09 Sun: EE29; Feb 10 Mon: EE29; Feb 11 Tue: EE29; Feb 12 Wed: EE29; Feb 13 Thu: EE29; Feb 14 Fri: EE29; Feb 15 Sat: EE29; Feb 16 Sun: EE29; Feb 17 Mon: EE29; Feb 18 Tue: EE29; Feb 19 Wed: EE29; Feb 20 Thu: EE29; Feb 21 Fri: EE29; Feb 24 Mon: ALL3; Feb 25 Tue: ALL3; Feb 26 Wed: ALL3; Feb 27 Thu: ALL3; Feb 28 Fri: ALL3
[75 empty] | GH3 | GH3 | GH3 | GH3 | GH3 | GH3 | GH3 |  |  |  | J36 | J36 | J36 | J36 | J36
[78 empty] | EE27 | EE27 | EE27 | EE27 | EE27
[78 empty] | EE23 | EE23 | EE23 | EE23 | EE23
|  | Mech Gallery | Jan 15 Wed: EE70; Jan 16 Thu: EE70; Jan 17 Fri: EE70; Jan 18 Sat: EE70; Jan 19 Sun: EE70; Jan 20 Mon: EE70; Jan 21 Tue: EE70; Jan 22 Wed: EE70; Jan 23 Thu: EE70; Jan 24 Fri: EE70; Jan 25 Sat: EE70; Jan 26 Sun: EE70; Jan 27 Mon: EE70; Jan 28 Tue: EE70; Jan 29 Wed: EE70; Jan 30 Thu: EE70; Jan 31 Fri: EE70; Feb 01 Sat: EE70; Feb 02 Sun: EE70; Feb 03 Mon: EE70; Feb 04 Tue: EE70; Feb 07 Fri: I-R; Feb 08 Sat: I-R; Feb 09 Sun: I-R; Feb 10 Mon: I-R; Feb 11 Tue: I-R; Feb 21 Fri: EE36; Feb 22 Sat: EE36; Feb 23 Sun: EE36; Feb 24 Mon: EE36; Feb 25 Tue: EE36; Feb 26 Wed: EE36; Feb 27 Thu: EE36; Feb 28 Fri: EE36
[87 empty] | GA6 | GA6 | GA6 | [17 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
[89 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22
| Cell 3 | CX - L1 | Feb 03 Mon: EE57; Feb 05 Wed: EE59; Feb 12 Wed: EE62; Mar 03 Mon: EE63
EE60
EE61
EE58
|  | CX - L2 | Mar 24 Mon: EE57; Mar 25 Tue: EE57; Mar 26 Wed: EE57; Mar 27 Thu: EE57; Mar 28 Fri: EE57; Mar 31 Mon: EE62; Apr 01 Tue: EE62; Apr 02 Wed: EE62; Apr 03 Thu: EE62; Apr 04 Fri: EE62; Apr 07 Mon: EE61; Apr 08 Tue: EE61; Apr 09 Wed: EE61; Apr 10 Thu: EE61; Apr 11 Fri: EE61
[148 empty] | EE60 | EE60 | EE60 | EE60 | EE60 |  |  | EE63 | EE63 | EE63 | EE63 | EE63
[148 empty] | EE58 | EE58 | EE58 | EE58 | EE58 |  |  | EE59 | EE59 | EE59 | EE59 | EE59
|  | CX - L3 | May 02 Fri: EE57; May 03 Sat: EE57; May 04 Sun: EE57; May 05 Mon: EE57; May 06 Tue: EE57; May 07 Wed: EE57; May 08 Thu: EE57; May 09 Fri: EE62; May 10 Sat: EE62; May 11 Sun: EE62; May 12 Mon: EE62; May 13 Tue: EE62; May 14 Wed: EE62; May 15 Thu: EE62
[190 empty] | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[194 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63
[194 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
[197 empty] | EE60 | EE60 | EE60 | EE60 | EE60
[197 empty] | EE61 | EE61 | EE61 | EE61 | EE61
|  | Data Hall | Feb 03 Mon: J7; Feb 04 Tue: J7; Feb 05 Wed: J7; Feb 06 Thu: J7; Feb 07 Fri: J7; Feb 10 Mon: EE73; Feb 11 Tue: EE73; Feb 12 Wed: EE73; Feb 13 Thu: EE73; Feb 14 Fri: EE73; Feb 15 Sat: EE73; Feb 16 Sun: EE73; Feb 17 Mon: EE73; Feb 18 Tue: EE73; Feb 19 Wed: EE73; Feb 20 Thu: EE73; Feb 21 Fri: EE73; Feb 24 Mon: EE7; Feb 25 Tue: EE7; Feb 26 Wed: EE7; Feb 27 Thu: EE7; Feb 28 Fri: EE7; Mar 03 Mon: S2; Mar 04 Tue: S2; Mar 05 Wed: S2; Mar 06 Thu: S2; Mar 07 Fri: S2; Mar 10 Mon: ET7; Mar 11 Tue: ET7; Mar 12 Wed: ET7; Mar 13 Thu: ET7; Mar 14 Fri: ET7; Mar 15 Sat: ET7; Mar 16 Sun: ET7; Mar 17 Mon: ET7; Mar 18 Tue: ET7; Mar 19 Wed: ET7; Mar 20 Thu: ET7; Mar 21 Fri: ET7; Mar 31 Mon: ALL3; Apr 01 Tue: ALL3; Apr 02 Wed: ALL3; Apr 03 Thu: ALL3; Apr 04 Fri: ALL3
[120 empty] | S1 | S1 | S1 | S1 | S1 |  |  | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 |  |  | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
[122 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10
|  | Electrical Room | Jan 23 Thu: EE72; Jan 24 Fri: EE72; Jan 25 Sat: EE72; Jan 26 Sun: EE72; Jan 27 Mon: EE72; Jan 28 Tue: EE72; Jan 29 Wed: EE72; Jan 30 Thu: EE72; Jan 31 Fri: EE72; Feb 01 Sat: EE72; Feb 02 Sun: EE72; Feb 03 Mon: EE72; Feb 04 Tue: EE72; Feb 05 Wed: EE72; Feb 24 Mon: EE29; Feb 25 Tue: EE29; Feb 26 Wed: EE29; Feb 27 Thu: EE29; Feb 28 Fri: EE29; Mar 01 Sat: EE29; Mar 02 Sun: EE29; Mar 03 Mon: EE29; Mar 04 Tue: EE29; Mar 05 Wed: EE29; Mar 06 Thu: EE29; Mar 07 Fri: EE29; Mar 08 Sat: EE29; Mar 09 Sun: EE29; Mar 10 Mon: EE29; Mar 11 Tue: EE29; Mar 12 Wed: EE29; Mar 13 Thu: EE29; Mar 14 Fri: EE29
[89 empty] | GH3 | GH3 | GH3 | GH3 | GH3 | GH3 | GH3 |  |  |  | J36 | J36 | J36 | J36 | J36 | [32 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[92 empty] | EE27 | EE27 | EE27 | EE27 | EE27
[92 empty] | EE23 | EE23 | EE23 | EE23 | EE23
|  | Mech Gallery | Jan 29 Wed: EE70; Jan 30 Thu: EE70; Jan 31 Fri: EE70; Feb 01 Sat: EE70; Feb 02 Sun: EE70; Feb 03 Mon: EE70; Feb 04 Tue: EE70; Feb 05 Wed: EE70; Feb 06 Thu: EE70; Feb 07 Fri: EE70; Feb 08 Sat: EE70; Feb 09 Sun: EE70; Feb 10 Mon: EE70; Feb 11 Tue: EE70; Feb 12 Wed: EE70; Feb 13 Thu: EE70; Feb 14 Fri: EE70; Feb 15 Sat: EE70; Feb 16 Sun: EE70; Feb 17 Mon: EE70; Feb 18 Tue: EE70; Feb 21 Fri: I-R; Feb 22 Sat: I-R; Feb 23 Sun: I-R; Feb 24 Mon: I-R; Feb 25 Tue: I-R; Mar 07 Fri: EE36; Mar 08 Sat: EE36; Mar 09 Sun: EE36; Mar 10 Mon: EE36; Mar 11 Tue: EE36; Mar 12 Wed: EE36; Mar 13 Thu: EE36; Mar 14 Fri: EE36
[103 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 |  |  |  | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
| Cell 4 | CX - L1 | Feb 12 Wed: EE62; Feb 17 Mon: EE57; Feb 19 Wed: EE61; Mar 17 Mon: EE63
EE60
EE60
EE58
|  | CX - L2 | Apr 07 Mon: EE57; Apr 08 Tue: EE57; Apr 09 Wed: EE57; Apr 10 Thu: EE57; Apr 11 Fri: EE57; Apr 14 Mon: EE62; Apr 15 Tue: EE62; Apr 16 Wed: EE62; Apr 17 Thu: EE62; Apr 18 Fri: EE62; Apr 21 Mon: EE61; Apr 22 Tue: EE61; Apr 23 Wed: EE61; Apr 24 Thu: EE61; Apr 25 Fri: EE61; Apr 28 Mon: EE63; Apr 29 Tue: EE63; Apr 30 Wed: EE63; May 01 Thu: EE63; May 02 Fri: EE63
[169 empty] | EE60 | EE60 | EE60 | EE60 | EE60 |  |  | EE58 | EE58 | EE58 | EE58 | EE58 |  |  | EE59 | EE59 | EE59 | EE59 | EE59
|  | CX - L3 | May 02 Fri: EE57; May 03 Sat: EE57; May 04 Sun: EE57; May 05 Mon: EE57; May 06 Tue: EE57; May 07 Wed: EE57; May 08 Thu: EE57; May 09 Fri: EE63; May 10 Sat: EE63; May 11 Sun: EE63; May 12 Mon: EE63; May 13 Tue: EE63; May 14 Wed: EE63; May 15 Thu: EE63; May 19 Mon: EE61; May 20 Tue: EE61; May 21 Wed: EE61; May 22 Thu: EE61; May 23 Fri: EE61
[190 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
[194 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
[194 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62
[197 empty] | EE60 | EE60 | EE60 | EE60 | EE60
|  | Data Hall | Jan 13 Mon: EE74; Jan 14 Tue: EE74; Jan 15 Wed: EE74; Jan 16 Thu: EE74; Jan 17 Fri: EE74; Jan 18 Sat: EE74; Jan 19 Sun: EE74; Jan 20 Mon: EE74; Jan 21 Tue: EE74; Jan 22 Wed: EE74; Jan 23 Thu: EE74; Jan 24 Fri: EE74; Jan 25 Sat: EE74; Jan 26 Sun: EE74; Jan 27 Mon: EE74; Jan 28 Tue: EE74; Feb 12 Wed: J6; Feb 13 Thu: J6; Feb 14 Fri: J6; Feb 17 Mon: J7; Feb 18 Tue: J7; Feb 19 Wed: J7; Feb 20 Thu: J7; Feb 21 Fri: J7; Feb 24 Mon: EE73; Feb 25 Tue: EE73; Feb 26 Wed: EE73; Feb 27 Thu: EE73; Feb 28 Fri: EE73; Mar 01 Sat: EE73; Mar 02 Sun: EE73; Mar 03 Mon: EE73; Mar 04 Tue: EE73; Mar 05 Wed: EE73; Mar 06 Thu: EE73; Mar 07 Fri: EE73; Mar 10 Mon: EE7; Mar 11 Tue: EE7; Mar 12 Wed: EE7; Mar 13 Thu: EE7; Mar 14 Fri: EE7; Mar 17 Mon: S2; Mar 18 Tue: S2; Mar 19 Wed: S2; Mar 20 Thu: S2; Mar 21 Fri: S2; Mar 24 Mon: ET7; Mar 25 Tue: ET7; Mar 26 Wed: ET7; Mar 27 Thu: ET7; Mar 28 Fri: ET7; Mar 29 Sat: ET7; Mar 30 Sun: ET7; Mar 31 Mon: ET7; Apr 01 Tue: ET7; Apr 02 Wed: ET7; Apr 03 Thu: ET7; Apr 04 Fri: ET7; Apr 07 Mon: EE18; Apr 08 Tue: EE18; Apr 09 Wed: EE18; Apr 10 Thu: EE18; Apr 11 Fri: EE18; Apr 12 Sat: EE18; Apr 13 Sun: EE18; Apr 14 Mon: EE18; Apr 15 Tue: EE18; Apr 16 Wed: EE18; Apr 17 Thu: EE18; Apr 18 Fri: EE18; Apr 19 Sat: EE18; Apr 20 Sun: EE18; Apr 21 Mon: EE18; Apr 22 Tue: EE18; Apr 23 Wed: EE18; Apr 24 Thu: EE18; Apr 25 Fri: EE18
[134 empty] | S1 | S1 | S1 | S1 | S1 |  |  | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | [23 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[136 empty] | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10
|  | Electrical Room | Jan 21 Tue: EE1; Jan 22 Wed: EE1; Jan 23 Thu: EE1; Jan 24 Fri: EE1; Jan 25 Sat: EE1; Jan 26 Sun: EE1; Jan 27 Mon: EE1; Jan 28 Tue: EE1; Jan 29 Wed: EE1; Jan 30 Thu: EE1; Jan 31 Fri: EE1; Feb 01 Sat: EE1; Feb 02 Sun: EE1; Feb 03 Mon: EE1; Feb 04 Tue: J17; Feb 05 Wed: J17; Feb 06 Thu: J17; Feb 07 Fri: GH3; Feb 08 Sat: GH3; Feb 09 Sun: GH3; Feb 10 Mon: GH3; Feb 11 Tue: GH3; Feb 12 Wed: GH3; Feb 13 Thu: GH3; Feb 17 Mon: J36; Feb 18 Tue: J36; Feb 19 Wed: J36; Feb 20 Thu: J36; Feb 21 Fri: J36; Mar 17 Mon: EE29; Mar 18 Tue: EE29; Mar 19 Wed: EE29; Mar 20 Thu: EE29; Mar 21 Fri: EE29; Mar 22 Sat: EE29; Mar 23 Sun: EE29; Mar 24 Mon: EE29; Mar 25 Tue: EE29; Mar 26 Wed: EE29; Mar 27 Thu: EE29; Mar 28 Fri: EE29; Mar 29 Sat: EE29; Mar 30 Sun: EE29; Mar 31 Mon: EE29; Apr 01 Tue: EE29; Apr 02 Wed: EE29; Apr 03 Thu: EE29; Apr 04 Fri: EE29
[102 empty] | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | EE72 | [41 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
[106 empty] | EE27 | EE27 | EE27 | EE27 | EE27
[106 empty] | EE23 | EE23 | EE23 | EE23 | EE23
[106 empty] | EE71 | EE71 | EE71 | EE71 | EE71
|  | Mech Gallery | Jan 27 Mon: GA12; Jan 28 Tue: GA12; Jan 29 Wed: T3; Jan 30 Thu: T3; Jan 31 Fri: T3; Feb 01 Sat: T3; Feb 02 Sun: T3; Feb 03 Mon: T3; Feb 04 Tue: T3; Feb 05 Wed: T3; Feb 06 Thu: T3; Feb 07 Fri: T3; Feb 08 Sat: T3; Feb 09 Sun: T3; Feb 10 Mon: T3; Feb 11 Tue: T3; Feb 12 Wed: J9; Feb 19 Wed: GA6; Feb 20 Thu: GA6; Feb 21 Fri: GA6; Mar 07 Fri: I-R; Mar 08 Sat: I-R; Mar 09 Sun: I-R; Mar 10 Mon: I-R; Mar 11 Tue: I-R; Mar 21 Fri: EE36; Mar 22 Sat: EE36; Mar 23 Sun: EE36; Mar 24 Mon: EE36; Mar 25 Tue: EE36; Mar 26 Wed: EE36; Mar 27 Thu: EE36; Mar 28 Fri: EE36
[108 empty] | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | EE70 | [6 empty] | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35 | EE35
[117 empty] | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22 | ET22
CX Level 2 | COLO 2 | COLO 2 | Feb 04 Tue: EE48; Feb 05 Wed: EE48; Feb 06 Thu: EE48; Feb 07 Fri: EE48; Feb 08 Sat: EE48; Feb 09 Sun: EE48; Feb 10 Mon: EE48; Feb 11 Tue: EE48; Feb 12 Wed: EE48; Feb 13 Thu: EE48; Feb 14 Fri: EE48; Feb 15 Sat: EE48; Feb 16 Sun: EE48; Feb 17 Mon: EE48; Feb 18 Tue: EE48; Feb 19 Wed: EE48; Feb 20 Thu: EE48; Feb 21 Fri: EE48; Feb 22 Sat: EE48; Feb 23 Sun: EE48; Feb 24 Mon: EE48; Feb 25 Tue: EE48; Feb 26 Wed: EE48; Feb 27 Thu: EE48; Feb 28 Fri: EE48
[100 empty] | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49
[100 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
| COLO 3 | COLO 3 | Mar 07 Fri: EE54; Mar 08 Sat: EE54; Mar 09 Sun: EE54; Mar 10 Mon: EE54; Mar 11 Tue: EE54; Mar 12 Wed: EE54; Mar 13 Thu: EE54
[131 empty] | EE55 | EE55 | EE55 | EE55 | EE55 | EE55 | EE55
[131 empty] | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48
[131 empty] | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49
[131 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
| COLO 4 | COLO 4 | Mar 07 Fri: EE48; Mar 08 Sat: EE48; Mar 09 Sun: EE48; Mar 10 Mon: EE48; Mar 11 Tue: EE48; Mar 12 Wed: EE48; Mar 13 Thu: EE48; Mar 14 Fri: EE48; Mar 15 Sat: EE48; Mar 16 Sun: EE48; Mar 17 Mon: EE48; Mar 18 Tue: EE48; Mar 19 Wed: EE48; Mar 20 Thu: EE48; Mar 21 Fri: EE48; Mar 22 Sat: EE48; Mar 23 Sun: EE48; Mar 24 Mon: EE48; Mar 25 Tue: EE48; Mar 26 Wed: EE48; Mar 27 Thu: EE48; Mar 28 Fri: EE48; Mar 29 Sat: EE48; Mar 30 Sun: EE48; Mar 31 Mon: EE48; Apr 01 Tue: EE48; Apr 02 Wed: EE48; Apr 03 Thu: EE48
[131 empty] | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49
[131 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
| COLO 5 | COLO 5 | Jan 15 Wed: EE48; Jan 16 Thu: EE48; Jan 17 Fri: EE48; Jan 18 Sat: EE48; Jan 19 Sun: EE48; Jan 20 Mon: EE48; Jan 21 Tue: EE48; Jan 22 Wed: EE48; Jan 23 Thu: EE48; Jan 24 Fri: EE48; Jan 25 Sat: EE48; Jan 26 Sun: EE48; Jan 27 Mon: EE48; Jan 28 Tue: EE48; Jan 29 Wed: EE48; Jan 30 Thu: EE48; Jan 31 Fri: EE48; Feb 01 Sat: EE48; Feb 02 Sun: EE48; Feb 03 Mon: EE48; Feb 04 Tue: EE48; Feb 05 Wed: EE48; Feb 06 Thu: EE48; Feb 07 Fri: EE48; Feb 08 Sat: EE48; Feb 09 Sun: EE48; Feb 10 Mon: EE48; Feb 11 Tue: EE48
[80 empty] | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49 | EE49
[80 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[95 empty] | EE51 | EE51 | EE51 | EE51 | EE51 | EE51 | EE51
[95 empty] | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53
| Site | Site | Mar 07 Fri: EE47; Mar 08 Sat: EE47; Mar 09 Sun: EE47; Mar 10 Mon: EE47; Mar 11 Tue: EE47; Mar 12 Wed: EE47; Mar 13 Thu: EE47
COLO 5 | All | CX - Microsoft | Apr 30 Wed: MS1; May 01 Thu: MS1; May 02 Fri: MS1; May 03 Sat: MS1; May 04 Sun: MS1; May 05 Mon: MS1; May 06 Tue: MS1; May 07 Wed: MS1; May 08 Thu: MS1; May 09 Fri: MS1; May 10 Sat: MS1; May 11 Sun: MS1; May 12 Mon: MS1; May 13 Tue: MS1; May 14 Wed: MS1; May 15 Thu: MS1; May 16 Fri: MS1; May 17 Sat: MS1; May 18 Sun: MS1; May 19 Mon: MS1; May 20 Tue: MS1; May 21 Wed: MS1; May 22 Thu: MS1; May 23 Fri: MS1; May 24 Sat: MS1; May 25 Sun: MS1; May 26 Mon: MS1; May 27 Tue: MS1; May 28 Wed: MS1; May 29 Thu: MS1; May 30 Fri: MS1; May 31 Sat: MS1; Jun 01 Sun: MS1; Jun 02 Mon: MS1; Jun 03 Tue: MS1; Jun 04 Wed: MS2; Jun 05 Thu: MS2
| Cell 1 | CX - L2 | Mar 04 Tue: EE57; Mar 05 Wed: EE57; Mar 06 Thu: EE57; Mar 07 Fri: EE57; Mar 08 Sat: EE57; Mar 09 Sun: EE57; Mar 10 Mon: EE57; Mar 11 Tue: EE62; Mar 12 Wed: EE62; Mar 13 Thu: EE62; Mar 14 Fri: EE62; Mar 15 Sat: EE62; Mar 16 Sun: EE62; Mar 17 Mon: EE62; Mar 18 Tue: EE63; Mar 19 Wed: EE63; Mar 20 Thu: EE63; Mar 21 Fri: EE63; Mar 22 Sat: EE63; Mar 23 Sun: EE63; Mar 24 Mon: EE63
[135 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
[142 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
[142 empty] | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
|  | CX - L3 | Mar 25 Tue: EE57; Mar 26 Wed: EE57; Mar 27 Thu: EE57; Mar 28 Fri: EE57; Mar 29 Sat: EE57; Mar 30 Sun: EE57; Mar 31 Mon: EE57; Apr 01 Tue: EE62; Apr 02 Wed: EE62; Apr 03 Thu: EE62; Apr 04 Fri: EE62; Apr 05 Sat: EE62; Apr 06 Sun: EE62; Apr 07 Mon: EE62; Apr 08 Tue: EE61; Apr 09 Wed: EE61; Apr 10 Thu: EE61; Apr 11 Fri: EE61; Apr 12 Sat: EE61; Apr 13 Sun: EE61; Apr 14 Mon: EE61
[149 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
[149 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
[151 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | Data Hall | Jan 27 Mon: EE18; Jan 28 Tue: EE18; Jan 29 Wed: EE18; Jan 30 Thu: EE18; Jan 31 Fri: EE18; Feb 01 Sat: EE18; Feb 02 Sun: EE18; Feb 03 Mon: EE18; Feb 04 Tue: EE18; Feb 05 Wed: EE18; Feb 06 Thu: EE18; Feb 07 Fri: EE18; Feb 08 Sat: EE18; Feb 09 Sun: EE18; Feb 10 Mon: EE18; Feb 11 Tue: EE18; Feb 12 Wed: EE18; Feb 13 Thu: EE18; Feb 14 Fri: EE18; Feb 17 Mon: ALL3; Feb 18 Tue: ALL3; Feb 19 Wed: ALL3; Feb 20 Thu: ALL3; Feb 21 Fri: ALL3
|  | Electrical Room | Dec 24 Tue: EE29; Dec 25 Wed: EE29; Dec 26 Thu: EE29; Dec 27 Fri: EE29; Dec 28 Sat: EE29; Dec 29 Sun: EE29; Dec 30 Mon: EE29; Dec 31 Tue: EE29; Jan 01 Wed: EE29; Jan 02 Thu: EE29; Jan 03 Fri: EE29; Jan 04 Sat: EE29; Jan 05 Sun: EE29; Jan 06 Mon: EE29; Jan 07 Tue: EE29; Jan 08 Wed: EE29; Jan 09 Thu: EE29; Jan 10 Fri: EE29; Jan 11 Sat: EE29; Jan 12 Sun: EE29; Jan 13 Mon: EE29; Jan 14 Tue: EE29; Jan 15 Wed: EE29
[78 empty] | ALL3 | ALL3 | ALL3 | ALL3 | ALL3
|  | Mech Gallery | Feb 05 Wed: EE36; Feb 06 Thu: EE36; Feb 07 Fri: EE36; Feb 08 Sat: EE36; Feb 09 Sun: EE36; Feb 10 Mon: EE36; Feb 11 Tue: EE36
| Cell 2 | CX - L2 | Mar 04 Tue: EE57; Mar 05 Wed: EE57; Mar 06 Thu: EE57; Mar 07 Fri: EE57; Mar 08 Sat: EE57; Mar 09 Sun: EE57; Mar 10 Mon: EE57; Mar 11 Tue: EE62; Mar 12 Wed: EE62; Mar 13 Thu: EE62; Mar 14 Fri: EE62; Mar 15 Sat: EE62; Mar 16 Sun: EE62; Mar 17 Mon: EE62; Mar 18 Tue: EE59; Mar 19 Wed: EE59; Mar 20 Thu: EE59; Mar 21 Fri: EE59; Mar 22 Sat: EE59; Mar 23 Sun: EE59; Mar 24 Mon: EE59
[135 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
[135 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
|  | CX - L3 | Mar 28 Fri: EE57; Mar 29 Sat: EE57; Mar 30 Sun: EE57; Mar 31 Mon: EE57; Apr 01 Tue: EE57; Apr 02 Wed: EE57; Apr 03 Thu: EE57; Apr 04 Fri: EE62; Apr 05 Sat: EE62; Apr 06 Sun: EE62; Apr 07 Mon: EE62; Apr 08 Tue: EE62; Apr 09 Wed: EE62; Apr 10 Thu: EE62; Apr 11 Fri: EE59; Apr 12 Sat: EE59; Apr 13 Sun: EE59; Apr 14 Mon: EE59; Apr 15 Tue: EE59; Apr 16 Wed: EE59; Apr 17 Thu: EE59; Apr 18 Fri: EE59; Apr 19 Sat: EE59; Apr 20 Sun: EE59; Apr 21 Mon: EE59; Apr 22 Tue: EE59; Apr 23 Wed: EE59; Apr 24 Thu: EE59
[152 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | [12 empty] | EE61 | EE61 | EE61 | EE61 | EE61 | EE61 | EE61
[152 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58
|  | Data Hall | Feb 03 Mon: EE18; Feb 04 Tue: EE18; Feb 05 Wed: EE18; Feb 06 Thu: EE18; Feb 07 Fri: EE18; Feb 08 Sat: EE18; Feb 09 Sun: EE18; Feb 10 Mon: EE18; Feb 11 Tue: EE18; Feb 12 Wed: EE18; Feb 13 Thu: EE18; Feb 14 Fri: EE18; Feb 15 Sat: EE18; Feb 16 Sun: EE18; Feb 17 Mon: EE18; Feb 18 Tue: EE18; Feb 19 Wed: EE18; Feb 20 Thu: EE18; Feb 21 Fri: EE18; Feb 24 Mon: EE19; Feb 25 Tue: EE19; Feb 26 Wed: EE19; Feb 27 Thu: EE19; Feb 28 Fri: EE19; Mar 01 Sat: EE19; Mar 02 Sun: EE19; Mar 03 Mon: EE19; Mar 04 Tue: EE19; Mar 05 Wed: EE19; Mar 06 Thu: EE19; Mar 07 Fri: EE19; Mar 08 Sat: EE19; Mar 09 Sun: EE19; Mar 10 Mon: EE19; Mar 11 Tue: EE19; Mar 12 Wed: EE19; Mar 13 Thu: EE19; Mar 14 Fri: EE19; Mar 17 Mon: ALL3; Mar 18 Tue: ALL3; Mar 19 Wed: ALL3; Mar 20 Thu: ALL3; Mar 21 Fri: ALL3
[106 empty] | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7
|  | Electrical Room | Jan 16 Thu: EE29; Jan 17 Fri: EE29; Jan 18 Sat: EE29; Jan 19 Sun: EE29; Jan 20 Mon: EE29; Jan 21 Tue: EE29; Jan 22 Wed: EE29; Jan 23 Thu: EE29; Jan 24 Fri: EE29; Jan 25 Sat: EE29; Jan 26 Sun: EE29; Jan 27 Mon: EE29; Jan 28 Tue: EE29; Jan 29 Wed: EE29; Jan 30 Thu: EE29; Jan 31 Fri: EE29; Feb 01 Sat: EE29; Feb 02 Sun: EE29; Feb 03 Mon: EE29; Feb 04 Tue: EE29; Feb 05 Wed: EE29; Feb 24 Mon: ALL3; Feb 25 Tue: ALL3; Feb 26 Wed: ALL3; Feb 27 Thu: ALL3; Feb 28 Fri: ALL3
|  | Mech Gallery | Jan 31 Fri: EE35; Feb 01 Sat: EE35; Feb 02 Sun: EE35; Feb 03 Mon: EE35; Feb 04 Tue: EE35; Feb 05 Wed: EE35; Feb 06 Thu: EE35; Feb 07 Fri: EE35; Feb 08 Sat: EE35; Feb 09 Sun: EE35; Feb 10 Mon: EE35; Feb 11 Tue: EE35; Feb 12 Wed: EE36; Feb 13 Thu: EE36; Feb 14 Fri: EE36; Feb 15 Sat: EE36; Feb 16 Sun: EE36; Feb 17 Mon: EE36; Feb 18 Tue: EE36
| Cell 3 | CX - L2 | Mar 10 Mon: EE57; Mar 11 Tue: EE57; Mar 12 Wed: EE57; Mar 13 Thu: EE57; Mar 14 Fri: EE57; Mar 17 Mon: EE62; Mar 18 Tue: EE62; Mar 19 Wed: EE62; Mar 20 Thu: EE62; Mar 21 Fri: EE62; Mar 24 Mon: EE59; Mar 25 Tue: EE59; Mar 26 Wed: EE59; Mar 27 Thu: EE59; Mar 28 Fri: EE59
[141 empty] | EE63 | EE63 | EE63 | EE63 | EE63 |  |  | EE60 | EE60 | EE60 | EE60 | EE60
[141 empty] | EE58 | EE58 | EE58 | EE58 | EE58 |  |  | EE61 | EE61 | EE61 | EE61 | EE61
|  | CX - L3 | Mar 28 Fri: EE57; Mar 29 Sat: EE57; Mar 30 Sun: EE57; Mar 31 Mon: EE57; Apr 01 Tue: EE57; Apr 02 Wed: EE57; Apr 03 Thu: EE57; Apr 04 Fri: EE62; Apr 05 Sat: EE62; Apr 06 Sun: EE62; Apr 07 Mon: EE62; Apr 08 Tue: EE62; Apr 09 Wed: EE62; Apr 10 Thu: EE62; Apr 16 Wed: EE61; Apr 17 Thu: EE61; Apr 18 Fri: EE61; Apr 19 Sat: EE61; Apr 20 Sun: EE61; Apr 21 Mon: EE61; Apr 22 Tue: EE61
[152 empty] | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE63 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 | EE60
[152 empty] | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE58 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
|  | Data Hall | Feb 17 Mon: EE17; Feb 18 Tue: EE17; Feb 19 Wed: EE17; Feb 20 Thu: EE17; Feb 21 Fri: EE17; Feb 22 Sat: EE17; Feb 23 Sun: EE17; Feb 24 Mon: EE17; Feb 25 Tue: EE17; Feb 26 Wed: EE17; Feb 27 Thu: EE17; Feb 28 Fri: EE17; Mar 31 Mon: ALL3; Apr 01 Tue: ALL3; Apr 02 Wed: ALL3; Apr 03 Thu: ALL3; Apr 04 Fri: ALL3
[120 empty] | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | Jan 02 Thu: EE28; Jan 03 Fri: EE28; Jan 04 Sat: EE28; Jan 05 Sun: EE28; Jan 06 Mon: EE28; Jan 07 Tue: EE28; Jan 08 Wed: EE28; Feb 06 Thu: EE18; Feb 07 Fri: EE18; Feb 08 Sat: EE18; Feb 09 Sun: EE18; Feb 10 Mon: EE18; Feb 11 Tue: EE18; Feb 12 Wed: EE18; Feb 13 Thu: EE18; Feb 14 Fri: EE18; Feb 15 Sat: EE18; Feb 16 Sun: EE18; Feb 17 Mon: EE18; Feb 18 Tue: EE18; Feb 19 Wed: EE18; Feb 20 Thu: EE18; Feb 21 Fri: EE18; Feb 22 Sat: EE18; Feb 23 Sun: EE18; Feb 24 Mon: EE18; Feb 25 Tue: EE18; Feb 26 Wed: EE18; Mar 24 Mon: ALL3; Mar 25 Tue: ALL3; Mar 26 Wed: ALL3; Mar 27 Thu: ALL3; Mar 28 Fri: ALL3
|  | Mech Gallery | Feb 12 Wed: I-R; Feb 13 Thu: I-R; Feb 14 Fri: EE35; Feb 15 Sat: EE35; Feb 16 Sun: EE35; Feb 17 Mon: EE35; Feb 18 Tue: EE35; Feb 19 Wed: EE35; Feb 20 Thu: EE35; Feb 21 Fri: EE35; Feb 22 Sat: EE35; Feb 23 Sun: EE35; Feb 24 Mon: EE35; Feb 25 Tue: EE35; Feb 26 Wed: EE36; Feb 27 Thu: EE36; Feb 28 Fri: EE36; Mar 01 Sat: EE36; Mar 02 Sun: EE36; Mar 03 Mon: EE36; Mar 04 Tue: EE36
| Cell 4 | CX - L1 | Jan 14 Tue: EE59; Mar 03 Mon: EE63
EE61
EE58
|  | CX - L2 | Mar 20 Thu: EE57; Mar 21 Fri: EE57; Mar 22 Sat: EE57; Mar 23 Sun: EE57; Mar 24 Mon: EE57; Mar 25 Tue: EE57; Mar 26 Wed: EE57; Mar 27 Thu: EE62; Mar 28 Fri: EE62; Mar 29 Sat: EE62; Mar 30 Sun: EE62; Mar 31 Mon: EE62; Apr 01 Tue: EE62; Apr 02 Wed: EE62; Apr 03 Thu: EE61; Apr 04 Fri: EE61; Apr 05 Sat: EE61; Apr 06 Sun: EE61; Apr 07 Mon: EE61; Apr 08 Tue: EE61; Apr 09 Wed: EE61
[148 empty] | EE58 | EE58 | EE58 | EE58 | EE58 |  |  | EE63 | EE63 | EE63 | EE63 | EE63
[148 empty] | EE59 | EE59 | EE59 | EE59 | EE59
[148 empty] | EE60 | EE60 | EE60 | EE60 | EE60
|  | CX - L3 | Mar 28 Fri: EE57; Mar 29 Sat: EE57; Mar 30 Sun: EE57; Mar 31 Mon: EE57; Apr 01 Tue: EE57; Apr 02 Wed: EE57; Apr 03 Thu: EE57; Apr 04 Fri: EE58; Apr 05 Sat: EE58; Apr 06 Sun: EE58; Apr 07 Mon: EE58; Apr 08 Tue: EE58; Apr 09 Wed: EE58; Apr 10 Thu: EE58; Apr 11 Fri: EE60; Apr 12 Sat: EE60; Apr 13 Sun: EE60; Apr 14 Mon: EE60; Apr 15 Tue: EE60; Apr 16 Wed: EE60; Apr 17 Thu: EE60; Apr 18 Fri: EE61; Apr 19 Sat: EE61; Apr 20 Sun: EE61; Apr 21 Mon: EE61; Apr 22 Tue: EE61; Apr 23 Wed: EE61; Apr 24 Thu: EE61
[159 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
[162 empty] | EE63 | EE63 | EE63 | EE63 | EE63
[166 empty] | EE62 | EE62 | EE62 | EE62 | EE62 | EE62 | EE62
|  | Data Hall | Mar 03 Mon: W4; Mar 04 Tue: W4; Mar 05 Wed: W4; Mar 06 Thu: W4; Mar 07 Fri: W4; Mar 08 Sat: W4; Mar 09 Sun: W4; Mar 10 Mon: W4; Mar 11 Tue: W4; Mar 12 Wed: W4; Mar 13 Thu: W4; Mar 14 Fri: W4; Mar 15 Sat: W4; Mar 16 Sun: W4; Mar 17 Mon: W4; Mar 18 Tue: W4; Mar 19 Wed: W4; Mar 20 Thu: W4; Mar 21 Fri: W4; Apr 14 Mon: ALL3; Apr 15 Tue: ALL3; Apr 16 Wed: ALL3; Apr 17 Thu: ALL3; Apr 18 Fri: ALL3
[134 empty] | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7 | ET7
[141 empty] | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18 | EE18
|  | Electrical Room | Jan 07 Tue: EE27; Jan 08 Wed: EE27; Jan 09 Thu: EE27; Jan 10 Fri: EE27; Jan 11 Sat: EE27; Jan 12 Sun: EE27; Jan 13 Mon: EE27; Feb 27 Thu: EE17; Feb 28 Fri: EE17; Mar 01 Sat: EE17; Mar 02 Sun: EE17; Mar 03 Mon: EE17; Mar 04 Tue: EE17; Mar 05 Wed: EE17; Mar 06 Thu: EE17; Mar 07 Fri: EE17; Mar 08 Sat: EE17; Mar 09 Sun: EE17; Mar 10 Mon: EE17; Mar 11 Tue: EE17; Mar 12 Wed: EE17; Mar 13 Thu: EE17; Mar 14 Fri: EE17; Mar 15 Sat: EE17; Mar 16 Sun: EE17; Mar 17 Mon: EE17; Mar 18 Tue: EE17; Mar 19 Wed: EE17; Apr 07 Mon: ALL3; Apr 08 Tue: ALL3; Apr 09 Wed: ALL3; Apr 10 Thu: ALL3; Apr 11 Fri: ALL3
[74 empty] | EE28 | EE28 | EE28 | EE28 | EE28 | EE28 | EE28
|  | Mech Gallery | Feb 12 Wed: ET22; Feb 13 Thu: ET22; Feb 14 Fri: ET22; Feb 15 Sat: ET22; Feb 16 Sun: ET22; Feb 17 Mon: ET22; Feb 18 Tue: ET22; Feb 19 Wed: ET22; Feb 20 Thu: ET22; Feb 21 Fri: ET22; Feb 22 Sat: ET22; Feb 23 Sun: ET22; Feb 24 Mon: ET22; Feb 25 Tue: ET22; Feb 26 Wed: I-R; Feb 27 Thu: I-R; Feb 28 Fri: EE35; Mar 01 Sat: EE35; Mar 02 Sun: EE35; Mar 03 Mon: EE35; Mar 04 Tue: EE35; Mar 05 Wed: EE35; Mar 06 Thu: EE35; Mar 07 Fri: EE35; Mar 08 Sat: EE35; Mar 09 Sun: EE35; Mar 10 Mon: EE35; Mar 11 Tue: EE35; Mar 12 Wed: EE36; Mar 13 Thu: EE36; Mar 14 Fri: EE36; Mar 15 Sat: EE36; Mar 16 Sun: EE36; Mar 17 Mon: EE36; Mar 18 Tue: EE36
CX Level 3 | COLO 2 | Cell 1 | Mar 03 Mon: EE49; Mar 04 Tue: EE49; Mar 05 Wed: EE49; Mar 06 Thu: EE49; Mar 07 Fri: EE49; Mar 08 Sat: EE49; Mar 09 Sun: EE49; Mar 10 Mon: EE49; Mar 11 Tue: EE49; Mar 12 Wed: EE49; Mar 13 Thu: EE49; Mar 14 Fri: EE49; Mar 15 Sat: EE49; Mar 16 Sun: EE49; Mar 17 Mon: EE49; Mar 18 Tue: EE49; Mar 19 Wed: EE49; Mar 20 Thu: EE49; Mar 21 Fri: EE49
[127 empty] | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48
[127 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
| COLO 3 | All | Mar 21 Fri: EE55; Mar 22 Sat: EE55; Mar 23 Sun: EE55; Mar 24 Mon: EE55; Mar 25 Tue: EE55; Mar 26 Wed: EE55; Mar 27 Thu: EE55; Mar 28 Fri: EE54; Mar 29 Sat: EE54; Mar 30 Sun: EE54; Mar 31 Mon: EE54; Apr 01 Tue: EE54; Apr 02 Wed: EE54; Apr 03 Thu: EE54
|  | Cell 1 | Apr 04 Fri: EE49; Apr 05 Sat: EE49; Apr 06 Sun: EE49; Apr 07 Mon: EE49; Apr 08 Tue: EE49; Apr 09 Wed: EE49; Apr 10 Thu: EE49; Apr 11 Fri: EE49; Apr 12 Sat: EE49; Apr 13 Sun: EE49; Apr 14 Mon: EE49; Apr 15 Tue: EE49; Apr 16 Wed: EE49; Apr 17 Thu: EE49; Apr 18 Fri: EE49; Apr 19 Sat: EE49; Apr 20 Sun: EE49; Apr 21 Mon: EE49; Apr 22 Tue: EE49; Apr 23 Wed: EE49; Apr 24 Thu: EE49
[159 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[166 empty] | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48
| COLO 4 | Cell 1 | Apr 04 Fri: EE49; Apr 05 Sat: EE49; Apr 06 Sun: EE49; Apr 07 Mon: EE49; Apr 08 Tue: EE49; Apr 09 Wed: EE49; Apr 10 Thu: EE49; Apr 11 Fri: EE49; Apr 12 Sat: EE49; Apr 13 Sun: EE49; Apr 14 Mon: EE49; Apr 15 Tue: EE49; Apr 16 Wed: EE49; Apr 17 Thu: EE49; Apr 18 Fri: EE49; Apr 19 Sat: EE49; Apr 20 Sun: EE49; Apr 21 Mon: EE49; Apr 22 Tue: EE49; Apr 23 Wed: EE49; Apr 24 Thu: EE49
[159 empty] | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48
[159 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
| COLO 5 | All | Mar 21 Fri: EE53; Mar 22 Sat: EE53; Mar 23 Sun: EE53; Mar 24 Mon: EE53; Mar 25 Tue: EE53; Mar 26 Wed: EE53; Mar 27 Thu: EE53
[145 empty] | EE51 | EE51 | EE51 | EE51 | EE51 | EE51 | EE51
|  | Cell 1 | Feb 28 Fri: EE49; Mar 01 Sat: EE49; Mar 02 Sun: EE49; Mar 03 Mon: EE49; Mar 04 Tue: EE49; Mar 05 Wed: EE49; Mar 06 Thu: EE49; Mar 07 Fri: EE49; Mar 08 Sat: EE49; Mar 09 Sun: EE49; Mar 10 Mon: EE49; Mar 11 Tue: EE49; Mar 12 Wed: EE49; Mar 13 Thu: EE49; Mar 14 Fri: EE49; Mar 15 Sat: EE49; Mar 16 Sun: EE49; Mar 17 Mon: EE49; Mar 18 Tue: EE49; Mar 19 Wed: EE49; Mar 20 Thu: EE49
[124 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[131 empty] | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48
| Site | Site | Mar 14 Fri: EE47; Mar 15 Sat: EE47; Mar 16 Sun: EE47; Mar 17 Mon: EE47; Mar 18 Tue: EE47; Mar 19 Wed: EE47; Mar 20 Thu: EE47
Note on IH5: Activity Name: Level 4 Cx - Colo 4 Phase: COLO 4 Location: All Trade: None Start Date: 25-Jun-2025 End Date: 30-Jul-2025
Note on JS5: Activity Name: Level 5 Cx / IST - Colo 4 Phase: COLO 4 Location: All Trade: None Start Date: 01-Aug-2025 End Date: 04-Aug-2025
Note on BP7: Activity Name: Interior - L1 UPS - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 02-Jan-2025 End Date: 02-Jan-2025
Note on CB7: Activity Name: Interior - L1 TCP/MSB - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on CJ7: Activity Name: Interior - L1 AHUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 22-Jan-2025 End Date: 22-Jan-2025
Note on DJ7: Activity Name: Interior - L1 PDUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on CB8: Activity Name: Interior - L1 ATSs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on CB9: Activity Name: Interior - L1 ADP - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on CB10: Activity Name: Interior - L1 Busway - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on EM11: Activity Name: Interior - L2 TCP/MSB - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on ET11: Activity Name: Interior - L2 UPS - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on FA11: Activity Name: Interior - L2 ATSs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on FH11: Activity Name: Interior - L2 AHUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on ET12: Activity Name: Interior - L2 PDUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on FA12: Activity Name: Interior - L2 Busway - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on ET13: Activity Name: Interior - L2 ADP - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on FY17: Activity Name: Interior - L3 TCP/MSB - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 25-Apr-2025 End Date: 01-May-2025
Note on GF17: Activity Name: Interior - L3 UPS - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on GM17: Activity Name: Interior - L3 ATSs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GT17: Activity Name: Interior - L3 AHUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 16-May-2025 End Date: 30-May-2025
Note on HK17: Activity Name: Interior - L3 Busway - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 02-Jun-2025 End Date: 06-Jun-2025
Note on GF18: Activity Name: Interior - L3 PDUs - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on GF19: Activity Name: Interior - L3 ADP - COLO4 Cell 1 Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on CH23: Activity Name: Ceiling Grid and Tile - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 20-Jan-2025 End Date: 24-Jan-2025
Note on CO23: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 27-Jan-2025 End Date: 07-Feb-2025
Note on DC23: Activity Name: Install PDU's - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on DJ23: Activity Name: HAC install and Rise - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on DQ23: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 24-Feb-2025 End Date: 07-Mar-2025
Note on EL23: Activity Name: Finishes and Signage - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on DC24: Activity Name: Begin HAC Assembly - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on DJ24: Activity Name: Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 17-Feb-2025 End Date: 07-Mar-2025
Note on DE25: Activity Name: Install Busway - COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 12-Feb-2025 End Date: 18-Feb-2025
Note on DQ25: Activity Name: Termination at PDU & Busway- COLO4 Cell 1 - DH Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 24-Feb-2025 End Date: 14-Mar-2025
Note on BC27: Activity Name: Below Ceiling MEP Rough In - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 20-Dec-2024 End Date: 06-Jan-2025
Note on BU27: Activity Name: Installation of ADP & ATS - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 07-Jan-2025 End Date: 13-Jan-2025
Note on CD27: Activity Name: Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 16-Jan-2025 End Date: 05-Feb-2025
Note on BF28: Activity Name: Install DX Split Units - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 23-Dec-2024 End Date: 30-Dec-2024
Note on BQ28: Activity Name: Door Frame Installation - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 03-Jan-2025 End Date: 09-Jan-2025
Note on CV28: Activity Name: Finishes and Signage - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on BG29: Activity Name: Installation of UPS Equipment - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 24-Dec-2024 End Date: 31-Dec-2024
Note on BU29: Activity Name: Installation of TCP/MSB - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 07-Jan-2025 End Date: 13-Jan-2025
Note on BW30: Activity Name: Connect to Cable tray and conduit equipment - COLO4 Cell 1 - ER Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 09-Jan-2025 End Date: 15-Jan-2025
Note on CC33: Activity Name: Post Wall Overhead MEP - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 15-Jan-2025 End Date: 04-Feb-2025
Note on CZ33: Activity Name: Pipe Testing - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: Inspections Start Date: 07-Feb-2025 End Date: 11-Feb-2025
Note on DN33: Activity Name: Trim out MEP - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 21-Feb-2025 End Date: 28-Feb-2025
Note on CJ34: Activity Name: Placing the AHU - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 22-Jan-2025 End Date: 24-Jan-2025
Note on DD34: Activity Name: Install ceiling and Light Fittings - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 11-Feb-2025 End Date: 21-Feb-2025
Note on CL35: Activity Name: Piping and Electrical Termination to AHUs - COLO4 Cell 1 - MG Phase: COLO 4 Location: Cell 1 Trade: None Start Date: 24-Jan-2025 End Date: 07-Feb-2025
Note on CH37: Activity Name: Interior - L1 UPS - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 20-Jan-2025 End Date: 20-Jan-2025
Note on CI37: Activity Name: Interior - L1 TCP/MSB - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 21-Jan-2025 End Date: 21-Jan-2025
Note on CX37: Activity Name: Interior - L1 AHUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 05-Feb-2025 End Date: 05-Feb-2025
Note on DX37: Activity Name: Interior - L1 PDUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on CI38: Activity Name: Interior - L1 ATSs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 21-Jan-2025 End Date: 21-Jan-2025
Note on CI39: Activity Name: Interior - L1 ADP - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 21-Jan-2025 End Date: 21-Jan-2025
Note on CI40: Activity Name: Interior - L1 Busway - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 21-Jan-2025 End Date: 21-Jan-2025
Note on FA44: Activity Name: Interior - L2 TCP/MSB - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on FH44: Activity Name: Interior - L2 UPS - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on FO44: Activity Name: Interior - L2 ATSs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 15-Apr-2025 End Date: 21-Apr-2025
Note on FV44: Activity Name: Interior - L2 AHUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 22-Apr-2025 End Date: 28-Apr-2025
Note on FH45: Activity Name: Interior - L2 PDUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on FO45: Activity Name: Interior - L2 Busway - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 15-Apr-2025 End Date: 21-Apr-2025
Note on FH46: Activity Name: Interior - L2 ADP - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on FY50: Activity Name: Interior - L3 TCP/MSB - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 25-Apr-2025 End Date: 01-May-2025
Note on GF50: Activity Name: Interior - L3 UPS - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on GM50: Activity Name: Interior - L3 ATSs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GT50: Activity Name: Interior - L3 AHUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 16-May-2025 End Date: 30-May-2025
Note on HK50: Activity Name: Interior - L3 Busway - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 02-Jun-2025 End Date: 06-Jun-2025
Note on GF51: Activity Name: Interior - L3 PDUs - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on GF52: Activity Name: Interior - L3 ADP - COLO4 Cell 2 Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on AO56: Activity Name: Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 06-Dec-2024 End Date: 23-Dec-2024
Note on CQ56: Activity Name: Security Screen Installation - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 29-Jan-2025 End Date: 31-Jan-2025
Note on CV56: Activity Name: Ceiling Grid and Tile - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on DC56: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 10-Feb-2025 End Date: 21-Feb-2025
Note on DQ56: Activity Name: Install PDU's - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on DX56: Activity Name: HAC install and Rise - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 03-Mar-2025 End Date: 07-Mar-2025
Note on EE56: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 10-Mar-2025 End Date: 21-Mar-2025
Note on ES56: Activity Name: Finishes and Signage - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DQ57: Activity Name: Begin HAC Assembly - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on DX57: Activity Name: Cable Pulling at PDU & Busway- COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 03-Mar-2025 End Date: 14-Mar-2025
Note on DS58: Activity Name: Install Busway - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on EE58: Activity Name: Termination at PDU & Busway - COLO4 Cell 2 - DH Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 10-Mar-2025 End Date: 28-Mar-2025
Note on BC60: Activity Name: Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 20-Dec-2024 End Date: 06-Jan-2025
Note on BU60: Activity Name: Install Ceiling - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 07-Jan-2025 End Date: 09-Jan-2025
Note on BX60: Activity Name: Install DX Split Units - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 10-Jan-2025 End Date: 16-Jan-2025
Note on CH60: Activity Name: Door Frame Installation - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 20-Jan-2025 End Date: 24-Jan-2025
Note on CY60: Activity Name: Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 06-Feb-2025 End Date: 26-Feb-2025
Note on BW61: Activity Name: Below Ceiling MEP Rough In - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 09-Jan-2025 End Date: 22-Jan-2025
Note on DQ61: Activity Name: Finishes and Signage - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on CA62: Activity Name: Installation of UPS Equipment - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 13-Jan-2025 End Date: 17-Jan-2025
Note on CB63: Activity Name: Installation of ADP & ATS - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 14-Jan-2025 End Date: 20-Jan-2025
Note on CB64: Activity Name: Installation of TCP/MSB - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 14-Jan-2025 End Date: 20-Jan-2025
Note on CD65: Activity Name: Connect to Cable tray and conduit equipment - COLO4 Cell 2 - ER Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 16-Jan-2025 End Date: 22-Jan-2025
Note on CA67: Activity Name: Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 13-Jan-2025 End Date: 14-Jan-2025
Note on CC67: Activity Name: Install Walls and Primer Paint - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 15-Jan-2025 End Date: 28-Jan-2025
Note on CQ67: Activity Name: Layout Ceiling and install Pencile Rod - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 29-Jan-2025 End Date: 29-Jan-2025
Note on CX67: Activity Name: Placing the AHU - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 05-Feb-2025 End Date: 07-Feb-2025
Note on DN67: Activity Name: Pipe Testing - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: Inspections Start Date: 21-Feb-2025 End Date: 25-Feb-2025
Note on EB67: Activity Name: Trim out MEP - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 07-Mar-2025 End Date: 14-Mar-2025
Note on CQ68: Activity Name: Post Wall Overhead MEP - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 29-Jan-2025 End Date: 18-Feb-2025
Note on DR68: Activity Name: Install ceiling and Light Fittings - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 25-Feb-2025 End Date: 07-Mar-2025
Note on CZ69: Activity Name: Piping and Electrical Termination to AHUs - COLO4 Cell 2 - MG Phase: COLO 4 Location: Cell 2 Trade: None Start Date: 07-Feb-2025 End Date: 21-Feb-2025
Note on CV72: Activity Name: Interior - L1 UPS - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on DL72: Activity Name: Interior - L1 AHUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 19-Feb-2025 End Date: 19-Feb-2025
Note on EL72: Activity Name: Interior - L1 PDUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 17-Mar-2025
Note on CV73: Activity Name: Interior - L1 TCP/MSB - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on CV74: Activity Name: Interior - L1 ATSs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on CV75: Activity Name: Interior - L1 ADP - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on FG76: Activity Name: Interior - L2 TCP/MSB - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on FN76: Activity Name: Interior - L2 UPS - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on FU76: Activity Name: Interior - L2 ATSs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on GB76: Activity Name: Interior - L2 AHUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on FN77: Activity Name: Interior - L2 PDUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on FU77: Activity Name: Interior - L2 Busway - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on FN78: Activity Name: Interior - L2 ADP - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on FY80: Activity Name: Interior - L3 TCP/MSB - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 25-Apr-2025 End Date: 01-May-2025
Note on GF80: Activity Name: Interior - L3 UPS - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on GM80: Activity Name: Interior - L3 ATSs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GT80: Activity Name: Interior - L3 AHUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 16-May-2025 End Date: 30-May-2025
Note on HK80: Activity Name: Interior - L3 Busway - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 02-Jun-2025 End Date: 06-Jun-2025
Note on GF81: Activity Name: Interior - L3 PDUs - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on GF82: Activity Name: Interior - L3 ADP - COLO4 Cell 3 Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on BG84: Activity Name: Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 24-Dec-2024 End Date: 10-Jan-2025
Note on DE84: Activity Name: Security Screen Installation - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 12-Feb-2025 End Date: 14-Feb-2025
Note on DJ84: Activity Name: Ceiling Grid and Tile - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on DQ84: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 24-Feb-2025 End Date: 07-Mar-2025
Note on EE84: Activity Name: Install PDU's - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on EL84: Activity Name: HAC install and Rise - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on ES84: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 24-Mar-2025 End Date: 04-Apr-2025
Note on FN84: Activity Name: Finishes and Signage - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on EE85: Activity Name: Begin HAC Assembly - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on EL85: Activity Name: Cable Pulling at PDU & Busway- COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 28-Mar-2025
Note on EZ85: Activity Name: Termination at PDU & Busway - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 31-Mar-2025 End Date: 18-Apr-2025
Note on EG86: Activity Name: Install Busway - COLO4 Cell 3 - DH Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on BU89: Activity Name: Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 07-Jan-2025 End Date: 20-Jan-2025
Note on CI89: Activity Name: Install Ceiling - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 21-Jan-2025 End Date: 23-Jan-2025
Note on CL89: Activity Name: Install DX Split Units - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 24-Jan-2025 End Date: 30-Jan-2025
Note on CV89: Activity Name: Door Frame Installation - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on DT89: Activity Name: Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 27-Feb-2025 End Date: 19-Mar-2025
Note on CK90: Activity Name: Below Ceiling MEP Rough In - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 23-Jan-2025 End Date: 05-Feb-2025
Note on EL90: Activity Name: Finishes and Signage - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on CO91: Activity Name: Installation of ADP & ATS - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on CO92: Activity Name: Installation of UPS Equipment - COLO4 Cell 3 - ER Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on CA93: Activity Name: Overhead MEP Installation - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 13-Jan-2025 End Date: 24-Jan-2025
Note on CO93: Activity Name: Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 27-Jan-2025 End Date: 28-Jan-2025
Note on CQ93: Activity Name: Install Walls and Primer Paint - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 29-Jan-2025 End Date: 11-Feb-2025
Note on DE93: Activity Name: Layout Ceiling and install Pencile Rod - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 12-Feb-2025 End Date: 12-Feb-2025
Note on DL93: Activity Name: Placing the AHU - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 19-Feb-2025 End Date: 21-Feb-2025
Note on EB93: Activity Name: Pipe Testing - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: Inspections Start Date: 07-Mar-2025 End Date: 11-Mar-2025
Note on EP93: Activity Name: Trim out MEP - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 21-Mar-2025 End Date: 28-Mar-2025
Note on DE94: Activity Name: Post Wall Overhead MEP - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 12-Feb-2025 End Date: 04-Mar-2025
Note on EF94: Activity Name: Install ceiling and Light Fittings - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 11-Mar-2025 End Date: 21-Mar-2025
Note on DN95: Activity Name: Piping and Electrical Termination to AHUs - COLO4 Cell 3 - MG Phase: COLO 4 Location: Cell 3 Trade: None Start Date: 21-Feb-2025 End Date: 07-Mar-2025
Note on DF97: Activity Name: Interior - L1 TCP/MSB - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 13-Feb-2025 End Date: 13-Feb-2025
Note on DJ97: Activity Name: Interior - L1 UPS - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on DZ97: Activity Name: Interior - L1 AHUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 05-Mar-2025 End Date: 05-Mar-2025
Note on EZ97: Activity Name: Interior - L1 PDUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 31-Mar-2025 End Date: 31-Mar-2025
Note on DF98: Activity Name: Interior - L1 ATSs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 13-Feb-2025 End Date: 13-Feb-2025
Note on DF99: Activity Name: Interior - L1 ADP - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 13-Feb-2025 End Date: 13-Feb-2025
Note on DF100: Activity Name: Interior - L1 Busway - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 13-Feb-2025 End Date: 13-Feb-2025
Note on FU101: Activity Name: Interior - L2 TCP/MSB - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on GB101: Activity Name: Interior - L2 UPS - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on GI101: Activity Name: Interior - L2 ATSs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 05-May-2025 End Date: 09-May-2025
Note on GP101: Activity Name: Interior - L2 AHUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 12-May-2025 End Date: 16-May-2025
Note on GB102: Activity Name: Interior - L2 PDUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on GI102: Activity Name: Interior - L2 Busway - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 05-May-2025 End Date: 09-May-2025
Note on GB103: Activity Name: Interior - L2 ADP - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on GM107: Activity Name: Interior - L3 TCP/MSB - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GT107: Activity Name: Interior - L3 PDUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 16-May-2025 End Date: 22-May-2025
Note on HA107: Activity Name: Interior - L3 ATSs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 23-May-2025 End Date: 30-May-2025
Note on HL107: Activity Name: Interior - L3 UPS - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 03-Jun-2025 End Date: 09-Jun-2025
Note on HZ107: Activity Name: Interior - L3 Busway - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 17-Jun-2025 End Date: 23-Jun-2025
Note on GT108: Activity Name: Interior - L3 ADP - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 16-May-2025 End Date: 22-May-2025
Note on HL108: Activity Name: Interior - L3 AHUs - COLO4 Cell 4 Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 03-Jun-2025 End Date: 16-Jun-2025
Note on CA113: Activity Name: Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 13-Jan-2025 End Date: 28-Jan-2025
Note on DS113: Activity Name: Security Screen Installation - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 26-Feb-2025 End Date: 28-Feb-2025
Note on DX113: Activity Name: Ceiling Grid and Tile - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 03-Mar-2025 End Date: 07-Mar-2025
Note on EE113: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 10-Mar-2025 End Date: 21-Mar-2025
Note on ES113: Activity Name: Install PDU's - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EZ113: Activity Name: HAC install and Rise - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on FG113: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 07-Apr-2025 End Date: 18-Apr-2025
Note on FU113: Activity Name: Termination at PDU & Busway - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 21-Apr-2025 End Date: 09-May-2025
Note on ES114: Activity Name: Begin HAC Assembly - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EZ114: Activity Name: Cable Pulling at PDU & Busway- COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 31-Mar-2025 End Date: 11-Apr-2025
Note on GI114: Activity Name: Finishes and Signage - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 05-May-2025 End Date: 09-May-2025
Note on EU115: Activity Name: Install Busway - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on EZ116: Activity Name: Closing Construction Access Door - COLO4 Cell 4 - DH Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 31-Mar-2025 End Date: 18-Apr-2025
Note on BQ117: Activity Name: Install Walls and Primer Paint - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 03-Jan-2025 End Date: 16-Jan-2025
Note on CI117: Activity Name: Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 21-Jan-2025 End Date: 03-Feb-2025
Note on CW117: Activity Name: Install Ceiling - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 04-Feb-2025 End Date: 06-Feb-2025
Note on CZ117: Activity Name: Install DX Split Units - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on DJ117: Activity Name: Door Frame Installation - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on EO117: Activity Name: Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 20-Mar-2025 End Date: 09-Apr-2025
Note on CB118: Activity Name: Install Upper Screens - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 14-Jan-2025 End Date: 20-Jan-2025
Note on CY118: Activity Name: Installation of ADP & ATS - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 06-Feb-2025 End Date: 12-Feb-2025
Note on FC118: Activity Name: Finishes and Signage - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 03-Apr-2025 End Date: 09-Apr-2025
Note on CY119: Activity Name: Installation of TCP/MSB - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 06-Feb-2025 End Date: 12-Feb-2025
Note on CY120: Activity Name: Connect to Cable tray and conduit equipment - COLO4 Cell 4 - ER Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 06-Feb-2025 End Date: 12-Feb-2025
Note on BT121: Activity Name: Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 06-Jan-2025 End Date: 10-Jan-2025
Note on CO121: Activity Name: Overhead MEP Installation - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 27-Jan-2025 End Date: 07-Feb-2025
Note on DC121: Activity Name: Deliver AHU into Mech. Gallery - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 10-Feb-2025 End Date: 11-Feb-2025
Note on DE121: Activity Name: Install Walls and Primer Paint - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 12-Feb-2025 End Date: 25-Feb-2025
Note on DS121: Activity Name: Layout Ceiling and install Pencile Rod - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 26-Feb-2025 End Date: 26-Feb-2025
Note on DZ121: Activity Name: Placing the AHU - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 05-Mar-2025 End Date: 07-Mar-2025
Note on EP121: Activity Name: Pipe Testing - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: Inspections Start Date: 21-Mar-2025 End Date: 25-Mar-2025
Note on FD121: Activity Name: Trim out MEP - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 04-Apr-2025 End Date: 11-Apr-2025
Note on DS122: Activity Name: Post Wall Overhead MEP - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 26-Feb-2025 End Date: 18-Mar-2025
Note on ET122: Activity Name: Install ceiling and Light Fittings - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 25-Mar-2025 End Date: 04-Apr-2025
Note on EB123: Activity Name: Piping and Electrical Termination to AHUs - COLO4 Cell 4 - MG Phase: COLO 4 Location: Cell 4 Trade: None Start Date: 07-Mar-2025 End Date: 21-Mar-2025
Note on AF125: Activity Name: Install screen wall - Colo 2 - North Phase: Yardwork Location: COLO 2 Trade: None Start Date: 27-Nov-2024 End Date: 26-Dec-2024
Note on D126: Activity Name: Install screen wall - Colo 2 - South Phase: Yardwork Location: COLO 2 Trade: None Start Date: 30-Oct-2024 End Date: 26-Nov-2024
Note on CS126: Activity Name: Wire pulling and termination for TCP/MSB - Colo 2 - South Phase: Yardwork Location: COLO 2 Trade: None Start Date: 31-Jan-2025 End Date: 20-Feb-2025
Note on AF128: Activity Name: Install screen wall - Colo 3 - North Phase: Yardwork Location: COLO 3 Trade: None Start Date: 27-Nov-2024 End Date: 26-Dec-2024
Note on BJ128: Activity Name: Wire pulling and termination for TCP/MSB - Colo 3 - North Phase: Yardwork Location: COLO 3 Trade: None Start Date: 27-Dec-2024 End Date: 17-Jan-2025
Note on Y130: Activity Name: Install screen wall - Colo 3 - South Phase: Yardwork Location: COLO 3 Trade: None Start Date: 20-Nov-2024 End Date: 18-Dec-2024
Note on AU131: Activity Name: Install screen wall - Colo 4 - North Phase: Yardwork Location: COLO 4 Trade: None Start Date: 12-Dec-2024 End Date: 10-Jan-2025
Note on CA131: Activity Name: Wire pulling and termination for TCP/MSB - Colo 4 - North Phase: Yardwork Location: COLO 4 Trade: None Start Date: 13-Jan-2025 End Date: 31-Jan-2025
Note on AN133: Activity Name: Install screen wall - Colo 4 - South Phase: Yardwork Location: COLO 4 Trade: None Start Date: 05-Dec-2024 End Date: 03-Jan-2025
Note on BT133: Activity Name: Wire pulling and termination for TCP/MSB - Colo 4 - South Phase: Yardwork Location: COLO 4 Trade: None Start Date: 06-Jan-2025 End Date: 24-Jan-2025
Note on K135: Activity Name: Install screen wall - Colo 5 - East Phase: Yardwork Location: COLO 5 Trade: None Start Date: 06-Nov-2024 End Date: 04-Dec-2024
Note on AN136: Activity Name: Install screen wall - Colo 5 - West Phase: Yardwork Location: COLO 5 Trade: None Start Date: 05-Dec-2024 End Date: 03-Jan-2025
Note on AT137: Activity Name: Install Generator Muffler - Colo 5 - West Phase: Yardwork Location: COLO 5 Trade: None Start Date: 11-Dec-2024 End Date: 17-Dec-2024
Note on GD138: Activity Name: Level 4 Cx - Colo 2 Phase: COLO 2 Location: All Trade: None Start Date: 30-Apr-2025 End Date: 03-Jun-2025
Note on HM138: Activity Name: Level 5 Cx / IST - Colo 2 Phase: COLO 2 Location: All Trade: None Start Date: 04-Jun-2025 End Date: 05-Jun-2025
Note on CJ140: Activity Name: Interior - L2 ADP - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 22-Jan-2025 End Date: 28-Jan-2025
Note on CS140: Activity Name: Interior - L2 Busway - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 31-Jan-2025 End Date: 06-Feb-2025
Note on DF140: Activity Name: Interior - L2 TCP/MSB - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 13-Feb-2025 End Date: 19-Feb-2025
Note on CJ141: Activity Name: Interior - L2 AHUs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 22-Jan-2025 End Date: 28-Jan-2025
Note on CS141: Activity Name: Interior - L2 UPS - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 31-Jan-2025 End Date: 06-Feb-2025
Note on CJ142: Activity Name: Interior - L2 ATSs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 22-Jan-2025 End Date: 28-Jan-2025
Note on CS142: Activity Name: Interior - L2 PDUs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 31-Jan-2025 End Date: 06-Feb-2025
Note on EN144: Activity Name: Interior - L3 TCP/MSB - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on EU144: Activity Name: Interior - L3 UPS - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on FB144: Activity Name: Interior - L3 ATSs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 02-Apr-2025 End Date: 08-Apr-2025
Note on FI144: Activity Name: Interior - L3 AHUs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 09-Apr-2025 End Date: 22-Apr-2025
Note on FW144: Activity Name: Interior - L3 Busway - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 23-Apr-2025 End Date: 29-Apr-2025
Note on EU145: Activity Name: Interior - L3 PDUs - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on EU146: Activity Name: Interior - L3 ADP - COLO2 Cell 1 Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on BX148: Activity Name: Cable Pulling at PDU to Busway & MSB - COLO2 Cell 1 - DH Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 10-Jan-2025 End Date: 30-Jan-2025
Note on CZ148: Activity Name: Finishes and Signage - COLO2 Cell 1 - DH Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on CE149: Activity Name: Termination at PDU to Busway & MSB- COLO2 Cell 1 - DH Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 17-Jan-2025 End Date: 06-Feb-2025
Note on AZ151: Activity Name: Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 17-Dec-2024 End Date: 08-Jan-2025
Note on BX151: Activity Name: Finishes and Signage - COLO2 Cell 1 - ER Phase: COLO 2 Location: Cell 1 Trade: None Start Date: 10-Jan-2025 End Date: 16-Jan-2025
Note on DF153: Activity Name: Interior - L2 TCP/MSB - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 13-Feb-2025 End Date: 19-Feb-2025
Note on DM153: Activity Name: Interior - L2 UPS - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 20-Feb-2025 End Date: 26-Feb-2025
Note on DT153: Activity Name: Interior - L2 ATSs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 27-Feb-2025 End Date: 05-Mar-2025
Note on EA153: Activity Name: Interior - L2 AHUs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 06-Mar-2025 End Date: 12-Mar-2025
Note on DM154: Activity Name: Interior - L2 PDUs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 20-Feb-2025 End Date: 26-Feb-2025
Note on DT154: Activity Name: Interior - L2 Busway - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 27-Feb-2025 End Date: 05-Mar-2025
Note on DM155: Activity Name: Interior - L2 ADP - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 20-Feb-2025 End Date: 26-Feb-2025
Note on EN157: Activity Name: Interior - L3 TCP/MSB - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on EU157: Activity Name: Interior - L3 UPS - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on FB157: Activity Name: Interior - L3 ATSs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 02-Apr-2025 End Date: 08-Apr-2025
Note on FI157: Activity Name: Interior - L3 AHUs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 09-Apr-2025 End Date: 22-Apr-2025
Note on FW157: Activity Name: Interior - L3 Busway - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 23-Apr-2025 End Date: 29-Apr-2025
Note on EU158: Activity Name: Interior - L3 PDUs - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on EU159: Activity Name: Interior - L3 ADP - COLO2 Cell 2 Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on CE162: Activity Name: Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 17-Jan-2025 End Date: 30-Jan-2025
Note on CS162: Activity Name: Termination at PDU & Busway - COLO2 Cell 2 - DH Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 31-Jan-2025 End Date: 20-Feb-2025
Note on DN162: Activity Name: Finishes and Signage - COLO2 Cell 2 - DH Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 21-Feb-2025 End Date: 27-Feb-2025
Note on BW165: Activity Name: Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 09-Jan-2025 End Date: 29-Jan-2025
Note on CR165: Activity Name: Finishes and Signage - COLO2 Cell 2 - ER Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 30-Jan-2025 End Date: 05-Feb-2025
Note on CB167: Activity Name: Install ceiling and Light Fittings - COLO2 Cell 2 - MG Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 14-Jan-2025 End Date: 24-Jan-2025
Note on CL168: Activity Name: Trim out MEP - COLO2 Cell 2 - MG Phase: COLO 2 Location: Cell 2 Trade: None Start Date: 24-Jan-2025 End Date: 31-Jan-2025
Note on DL169: Activity Name: Interior - L2 TCP/MSB - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 19-Feb-2025 End Date: 25-Feb-2025
Note on DS169: Activity Name: Interior - L2 UPS - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on DZ169: Activity Name: Interior - L2 AHUs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on DL170: Activity Name: Interior - L2 ADP - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 19-Feb-2025 End Date: 25-Feb-2025
Note on DS170: Activity Name: Interior - L2 PDUs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on DZ170: Activity Name: Interior - L2 Busway - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on DS171: Activity Name: Interior - L2 ATSs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on EN175: Activity Name: Interior - L3 TCP/MSB - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on EU175: Activity Name: Interior - L3 UPS - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on FB175: Activity Name: Interior - L3 ATSs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 02-Apr-2025 End Date: 08-Apr-2025
Note on FI175: Activity Name: Interior - L3 AHUs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 09-Apr-2025 End Date: 22-Apr-2025
Note on FW175: Activity Name: Interior - L3 Busway - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 23-Apr-2025 End Date: 29-Apr-2025
Note on EU176: Activity Name: Interior - L3 PDUs - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on EU177: Activity Name: Interior - L3 ADP - COLO2 Cell 3 Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on CQ181: Activity Name: Termination at PDU & Busway - COLO2 Cell 3 - DH Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 29-Jan-2025 End Date: 18-Feb-2025
Note on DU181: Activity Name: Finishes and Signage - COLO2 Cell 3 - DH Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 28-Feb-2025 End Date: 06-Mar-2025
Note on CX182: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 05-Feb-2025 End Date: 18-Feb-2025
Note on BB184: Activity Name: Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 19-Dec-2024 End Date: 10-Jan-2025
Note on BX185: Activity Name: Finishes and Signage - COLO2 Cell 3 - ER Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 10-Jan-2025 End Date: 16-Jan-2025
Note on CL186: Activity Name: Pipe Testing - COLO2 Cell 3 - MG Phase: COLO 2 Location: Cell 3 Trade: Inspections Start Date: 24-Jan-2025 End Date: 28-Jan-2025
Note on CZ186: Activity Name: Trim out MEP - COLO2 Cell 3 - MG Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 07-Feb-2025 End Date: 14-Feb-2025
Note on CP187: Activity Name: Install ceiling and Light Fittings - COLO2 Cell 3 - MG Phase: COLO 2 Location: Cell 3 Trade: None Start Date: 28-Jan-2025 End Date: 07-Feb-2025
Note on DZ189: Activity Name: Interior - L2 TCP/MSB - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on EG189: Activity Name: Interior - L2 UPS - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on EN189: Activity Name: Interior - L2 ATSs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on EG190: Activity Name: Interior - L2 PDUs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on EN190: Activity Name: Interior - L2 AHUs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on EG191: Activity Name: Interior - L2 ADP - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on EN191: Activity Name: Interior - L2 Busway - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on EN194: Activity Name: Interior - L3 TCP/MSB - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on EU194: Activity Name: Interior - L3 PDUs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on FB194: Activity Name: Interior - L3 ATSs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 02-Apr-2025 End Date: 08-Apr-2025
Note on FI194: Activity Name: Interior - L3 UPS - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 09-Apr-2025 End Date: 15-Apr-2025
Note on FW194: Activity Name: Interior - L3 Busway - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 23-Apr-2025 End Date: 29-Apr-2025
Note on EU195: Activity Name: Interior - L3 ADP - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on FI195: Activity Name: Interior - L3 AHUs - COLO2 Cell 4 Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 09-Apr-2025 End Date: 22-Apr-2025
Note on DE200: Activity Name: Termination at PDU & Busway - COLO2 Cell 4 - DH Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 12-Feb-2025 End Date: 04-Mar-2025
Note on EB200: Activity Name: Finishes and Signage - COLO2 Cell 4 - DH Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 07-Mar-2025 End Date: 13-Mar-2025
Note on DL201: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 19-Feb-2025 End Date: 04-Mar-2025
Note on BJ203: Activity Name: Connect to Cable tray and conduit equipment - COLO2 Cell 4 - ER Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 27-Dec-2024 End Date: 03-Jan-2025
Note on CA203: Activity Name: Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 13-Jan-2025 End Date: 31-Jan-2025
Note on CV203: Activity Name: Finishes and Signage - COLO2 Cell 4 - ER Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on CL206: Activity Name: Piping and Electrical Termination to AHUs - COLO2 Cell 4 - MG Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 24-Jan-2025 End Date: 07-Feb-2025
Note on DD206: Activity Name: Install ceiling and Light Fittings - COLO2 Cell 4 - MG Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 11-Feb-2025 End Date: 21-Feb-2025
Note on CZ207: Activity Name: Pipe Testing - COLO2 Cell 4 - MG Phase: COLO 2 Location: Cell 4 Trade: Inspections Start Date: 07-Feb-2025 End Date: 11-Feb-2025
Note on DN207: Activity Name: Trim out MEP - COLO2 Cell 4 - MG Phase: COLO 2 Location: Cell 4 Trade: None Start Date: 21-Feb-2025 End Date: 28-Feb-2025
Note on HE210: Activity Name: Level 4 Cx - Colo 3 Phase: COLO 3 Location: All Trade: None Start Date: 27-May-2025 End Date: 30-Jun-2025
Note on IN210: Activity Name: Level 5 Cx / IST - Colo 3 Phase: COLO 3 Location: All Trade: None Start Date: 01-Jul-2025 End Date: 02-Jul-2025
Note on CV212: Activity Name: Interior - L1 PDUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on DC212: Activity Name: Interior - L1 UPS - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on EM214: Activity Name: Interior - L2 TCP/MSB - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on ET214: Activity Name: Interior - L2 UPS - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on FA214: Activity Name: Interior - L2 ATSs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on FH214: Activity Name: Interior - L2 AHUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on ET215: Activity Name: Interior - L2 PDUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on FA215: Activity Name: Interior - L2 Busway - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on ET216: Activity Name: Interior - L2 ADP - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on GF218: Activity Name: Interior - L3 TCP/MSB - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on GM218: Activity Name: Interior - L3 UPS - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GT218: Activity Name: Interior - L3 Busway - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 16-May-2025 End Date: 22-May-2025
Note on GI219: Activity Name: Interior - L3 AHUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 05-May-2025 End Date: 16-May-2025
Note on GM220: Activity Name: Interior - L3 PDUs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GM221: Activity Name: Interior - L3 ADP - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GM222: Activity Name: Interior - L3 ATSs - COLO3 Cell 1 Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on CO224: Activity Name: Install PDU's - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on CV224: Activity Name: HAC install and Rise - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on DC224: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 10-Feb-2025 End Date: 21-Feb-2025
Note on DX224: Activity Name: Finishes and Signage - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 03-Mar-2025 End Date: 07-Mar-2025
Note on CO225: Activity Name: Begin HAC Assembly - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on CV225: Activity Name: Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 21-Feb-2025
Note on CQ226: Activity Name: Install Busway - COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on DC226: Activity Name: Termination at PDU & Busway- COLO3 Cell 1 - DH Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 10-Feb-2025 End Date: 28-Feb-2025
Note on BT228: Activity Name: Connect to Cable tray and conduit equipment - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 06-Jan-2025 End Date: 10-Jan-2025
Note on CA228: Activity Name: Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 13-Jan-2025 End Date: 31-Jan-2025
Note on CV228: Activity Name: Installation of UPS Equipment - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on DC228: Activity Name: Door Frame Installation - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on DJ228: Activity Name: Finishes and Signage - COLO3 Cell 1 - ER Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on CP232: Activity Name: Install ceiling and Light Fittings - COLO3 Cell 1 - MG Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 28-Jan-2025 End Date: 07-Feb-2025
Note on CZ233: Activity Name: Trim out MEP - COLO3 Cell 1 - MG Phase: COLO 3 Location: Cell 1 Trade: None Start Date: 07-Feb-2025 End Date: 14-Feb-2025
Note on CH234: Activity Name: Interior - L1 TCP/MSB - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 20-Jan-2025 End Date: 20-Jan-2025
Note on CJ234: Activity Name: Interior - L1 AHUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 22-Jan-2025 End Date: 22-Jan-2025
Note on DD234: Activity Name: Interior - L1 UPS - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 11-Feb-2025 End Date: 11-Feb-2025
Note on DJ234: Activity Name: Interior - L1 PDUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on CH235: Activity Name: Interior - L1 ATSs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 20-Jan-2025 End Date: 20-Jan-2025
Note on CH236: Activity Name: Interior - L1 Busway - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 20-Jan-2025 End Date: 20-Jan-2025
Note on CH237: Activity Name: Interior - L1 ADP - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 20-Jan-2025 End Date: 20-Jan-2025
Note on EM241: Activity Name: Interior - L2 TCP/MSB - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on ET241: Activity Name: Interior - L2 UPS - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on FA241: Activity Name: Interior - L2 ATSs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on FH241: Activity Name: Interior - L2 AHUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on ET242: Activity Name: Interior - L2 PDUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on FA242: Activity Name: Interior - L2 Busway - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on ET243: Activity Name: Interior - L2 ADP - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on GF247: Activity Name: Interior - L3 TCP/MSB - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on GM247: Activity Name: Interior - L3 UPS - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GT247: Activity Name: Interior - L3 PDUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 16-May-2025 End Date: 22-May-2025
Note on GI248: Activity Name: Interior - L3 AHUs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 05-May-2025 End Date: 16-May-2025
Note on GM249: Activity Name: Interior - L3 ADP - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GT249: Activity Name: Interior - L3 Busway - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 16-May-2025 End Date: 22-May-2025
Note on GM250: Activity Name: Interior - L3 ATSs - COLO3 Cell 2 Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on CH252: Activity Name: Ceiling Grid and Tile - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 20-Jan-2025 End Date: 24-Jan-2025
Note on CO252: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 27-Jan-2025 End Date: 07-Feb-2025
Note on DC252: Activity Name: Install PDU's - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on DJ252: Activity Name: HAC install and Rise - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on DQ252: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 24-Feb-2025 End Date: 07-Mar-2025
Note on EE252: Activity Name: Finishes and Signage - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on DC253: Activity Name: Begin HAC Assembly - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on DJ253: Activity Name: Cable Pulling at PDU & Busway- COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 17-Feb-2025 End Date: 28-Feb-2025
Note on DE254: Activity Name: Install Busway - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 12-Feb-2025 End Date: 18-Feb-2025
Note on DQ254: Activity Name: Termination at PDU & Busway - COLO3 Cell 2 - DH Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 24-Feb-2025 End Date: 14-Mar-2025
Note on BW256: Activity Name: Below Ceiling MEP Rough In - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 09-Jan-2025 End Date: 22-Jan-2025
Note on CV256: Activity Name: Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 03-Feb-2025 End Date: 21-Feb-2025
Note on DQ256: Activity Name: Finishes and Signage - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on BX257: Activity Name: Install DX Split Units - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 10-Jan-2025 End Date: 16-Jan-2025
Note on CH257: Activity Name: Door Frame Installation - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 20-Jan-2025 End Date: 24-Jan-2025
Note on CA258: Activity Name: Installation of ADP & ATS - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 13-Jan-2025 End Date: 17-Jan-2025
Note on CA259: Activity Name: Installation of UPS Equipment - COLO3 Cell 2 - ER Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 13-Jan-2025 End Date: 17-Jan-2025
Note on CC260: Activity Name: Post Wall Overhead MEP - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 15-Jan-2025 End Date: 04-Feb-2025
Note on CZ260: Activity Name: Pipe Testing - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: Inspections Start Date: 07-Feb-2025 End Date: 11-Feb-2025
Note on DN260: Activity Name: Trim out MEP - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 21-Feb-2025 End Date: 28-Feb-2025
Note on CJ261: Activity Name: Placing the AHU - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 22-Jan-2025 End Date: 24-Jan-2025
Note on DD261: Activity Name: Install ceiling and Light Fittings - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 11-Feb-2025 End Date: 21-Feb-2025
Note on CL262: Activity Name: Piping and Electrical Termination to AHUs - COLO3 Cell 2 - MG Phase: COLO 3 Location: Cell 2 Trade: None Start Date: 24-Jan-2025 End Date: 07-Feb-2025
Note on CV264: Activity Name: Interior - L1 TCP/MSB - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on CX264: Activity Name: Interior - L1 AHUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 05-Feb-2025 End Date: 05-Feb-2025
Note on DE264: Activity Name: Interior - L1 UPS - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 12-Feb-2025 End Date: 12-Feb-2025
Note on DX264: Activity Name: Interior - L1 PDUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on CV265: Activity Name: Interior - L1 ATSs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on CV266: Activity Name: Interior - L1 Busway - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on CV267: Activity Name: Interior - L1 ADP - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on ES268: Activity Name: Interior - L2 TCP/MSB - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EZ268: Activity Name: Interior - L2 UPS - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on FG268: Activity Name: Interior - L2 Busway - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on ES269: Activity Name: Interior - L2 ATSs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EZ269: Activity Name: Interior - L2 PDUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on ES270: Activity Name: Interior - L2 ADP - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EZ270: Activity Name: Interior - L2 AHUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on GF272: Activity Name: Interior - L3 TCP/MSB - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on GM272: Activity Name: Interior - L3 UPS - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GI273: Activity Name: Interior - L3 AHUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 05-May-2025 End Date: 16-May-2025
Note on GM274: Activity Name: Interior - L3 PDUs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GM275: Activity Name: Interior - L3 ADP - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GP276: Activity Name: Interior - L3 ATSs - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 12-May-2025 End Date: 16-May-2025
Note on GP277: Activity Name: Interior - L3 Busway - COLO3 Cell 3 Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 12-May-2025 End Date: 16-May-2025
Note on CV279: Activity Name: Ceiling Grid and Tile - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on DC279: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 10-Feb-2025 End Date: 21-Feb-2025
Note on DQ279: Activity Name: Install PDU's - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on DX279: Activity Name: HAC install and Rise - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 03-Mar-2025 End Date: 07-Mar-2025
Note on EE279: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 10-Mar-2025 End Date: 21-Mar-2025
Note on EZ279: Activity Name: Finishes and Signage - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on DQ280: Activity Name: Begin HAC Assembly - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on DX280: Activity Name: Cable Pulling at PDU & Busway- COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 03-Mar-2025 End Date: 14-Mar-2025
Note on EL280: Activity Name: Termination at PDU & Busway - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 04-Apr-2025
Note on DS281: Activity Name: Install Busway - COLO3 Cell 3 - DH Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on CK284: Activity Name: Below Ceiling MEP Rough In - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 23-Jan-2025 End Date: 05-Feb-2025
Note on DQ284: Activity Name: Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 24-Feb-2025 End Date: 14-Mar-2025
Note on CL285: Activity Name: Install DX Split Units - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 24-Jan-2025 End Date: 30-Jan-2025
Note on CV285: Activity Name: Door Frame Installation - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on EG285: Activity Name: Finishes and Signage - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on CO286: Activity Name: Installation of ADP & ATS - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on CO287: Activity Name: Installation of UPS Equipment - COLO3 Cell 3 - ER Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 27-Jan-2025 End Date: 31-Jan-2025
Note on CQ288: Activity Name: Post Wall Overhead MEP - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 29-Jan-2025 End Date: 18-Feb-2025
Note on DN288: Activity Name: Pipe Testing - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: Inspections Start Date: 21-Feb-2025 End Date: 25-Feb-2025
Note on EB288: Activity Name: Trim out MEP - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 07-Mar-2025 End Date: 14-Mar-2025
Note on CZ289: Activity Name: Piping and Electrical Termination to AHUs - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 07-Feb-2025 End Date: 21-Feb-2025
Note on DR289: Activity Name: Install ceiling and Light Fittings - COLO3 Cell 3 - MG Phase: COLO 3 Location: Cell 3 Trade: None Start Date: 25-Feb-2025 End Date: 07-Mar-2025
Note on DE292: Activity Name: Interior - L1 UPS - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 12-Feb-2025 End Date: 12-Feb-2025
Note on DJ292: Activity Name: Interior - L1 TCP/MSB - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on DL292: Activity Name: Interior - L1 AHUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 19-Feb-2025 End Date: 19-Feb-2025
Note on EL292: Activity Name: Interior - L1 PDUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 17-Mar-2025 End Date: 17-Mar-2025
Note on DJ293: Activity Name: Interior - L1 ATSs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on DJ294: Activity Name: Interior - L1 Busway - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on DJ295: Activity Name: Interior - L1 ADP - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on FG296: Activity Name: Interior - L2 TCP/MSB - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on FN296: Activity Name: Interior - L2 UPS - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on FU296: Activity Name: Interior - L2 Busway - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on GB296: Activity Name: Interior - L2 PDUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on FN297: Activity Name: Interior - L2 ATSs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on FU297: Activity Name: Interior - L2 ADP - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on GB297: Activity Name: Interior - L2 AHUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 28-Apr-2025 End Date: 02-May-2025
Note on GF302: Activity Name: Interior - L3 TCP/MSB - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 02-May-2025 End Date: 08-May-2025
Note on GM302: Activity Name: Interior - L3 PDUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GW302: Activity Name: Interior - L3 Busway - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 19-May-2025 End Date: 23-May-2025
Note on GI303: Activity Name: Interior - L3 AHUs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 05-May-2025 End Date: 16-May-2025
Note on GM304: Activity Name: Interior - L3 ADP - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GM305: Activity Name: Interior - L3 UPS - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 09-May-2025 End Date: 15-May-2025
Note on GP306: Activity Name: Interior - L3 ATSs - COLO3 Cell 4 Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 12-May-2025 End Date: 16-May-2025
Note on CA309: Activity Name: Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 13-Jan-2025 End Date: 28-Jan-2025
Note on DE309: Activity Name: Security Screen Installation - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 12-Feb-2025 End Date: 14-Feb-2025
Note on DJ309: Activity Name: Ceiling Grid and Tile - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on DQ309: Activity Name: Overhead MEP Installation (Below Ceiling) - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 24-Feb-2025 End Date: 07-Mar-2025
Note on EE309: Activity Name: Install PDU's - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on EL309: Activity Name: HAC install and Rise - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on ES309: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 24-Mar-2025 End Date: 04-Apr-2025
Note on FG309: Activity Name: Termination at PDU & Busway - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 07-Apr-2025 End Date: 25-Apr-2025
Note on EE310: Activity Name: Begin HAC Assembly - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on EL310: Activity Name: Cable Pulling at PDU & Busway- COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 17-Mar-2025 End Date: 28-Mar-2025
Note on FU310: Activity Name: Finishes and Signage - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on EG311: Activity Name: Install Busway - COLO3 Cell 4 - DH Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on CI313: Activity Name: Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 21-Jan-2025 End Date: 03-Feb-2025
Note on CW313: Activity Name: Install Ceiling - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 04-Feb-2025 End Date: 06-Feb-2025
Note on CZ313: Activity Name: Install DX Split Units - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on DJ313: Activity Name: Door Frame Installation - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on EL313: Activity Name: Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 17-Mar-2025 End Date: 04-Apr-2025
Note on CY314: Activity Name: Below Ceiling MEP Rough In - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 06-Feb-2025 End Date: 19-Feb-2025
Note on FB314: Activity Name: Finishes and Signage - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 02-Apr-2025 End Date: 08-Apr-2025
Note on DC315: Activity Name: Installation of ADP & ATS - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on DC316: Activity Name: Installation of UPS Equipment - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on DC317: Activity Name: Installation of TCP/MSB - COLO3 Cell 4 - ER Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 10-Feb-2025 End Date: 14-Feb-2025
Note on CO318: Activity Name: Deliver AHU into Mech. Gallery - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 27-Jan-2025 End Date: 28-Jan-2025
Note on CQ318: Activity Name: Install Walls and Primer Paint - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 29-Jan-2025 End Date: 11-Feb-2025
Note on DE318: Activity Name: Layout Ceiling and install Pencile Rod - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 12-Feb-2025 End Date: 12-Feb-2025
Note on DL318: Activity Name: Placing the AHU - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 19-Feb-2025 End Date: 21-Feb-2025
Note on EB318: Activity Name: Pipe Testing - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: Inspections Start Date: 07-Mar-2025 End Date: 11-Mar-2025
Note on EP318: Activity Name: Trim out MEP - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 21-Mar-2025 End Date: 28-Mar-2025
Note on DE319: Activity Name: Post Wall Overhead MEP - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 12-Feb-2025 End Date: 04-Mar-2025
Note on EF319: Activity Name: Install ceiling and Light Fittings - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 11-Mar-2025 End Date: 21-Mar-2025
Note on DN320: Activity Name: Piping and Electrical Termination to AHUs - COLO3 Cell 4 - MG Phase: COLO 3 Location: Cell 4 Trade: None Start Date: 21-Feb-2025 End Date: 07-Mar-2025
Note on CW322: Activity Name: L2 XFMR - COLO2 Phase: CX Level 2 Location: COLO 2 Trade: None Start Date: 04-Feb-2025 End Date: 28-Feb-2025
Note on CW323: Activity Name: L2 GEN - COLO2 Phase: CX Level 2 Location: COLO 2 Trade: None Start Date: 04-Feb-2025 End Date: 28-Feb-2025
Note on CW324: Activity Name: L2 UPM - COLO2 Phase: CX Level 2 Location: COLO 2 Trade: None Start Date: 04-Feb-2025 End Date: 28-Feb-2025
Note on EB325: Activity Name: L2 UMS 03 - COLO 3 Phase: CX Level 2 Location: COLO 3 Trade: None Start Date: 07-Mar-2025 End Date: 13-Mar-2025
Note on EB326: Activity Name: L2 UMS 04 - COLO 3 Phase: CX Level 2 Location: COLO 3 Trade: None Start Date: 07-Mar-2025 End Date: 13-Mar-2025
Note on EB327: Activity Name: L2 XFMR - COLO3 Phase: CX Level 2 Location: COLO 3 Trade: None Start Date: 07-Mar-2025 End Date: 03-Apr-2025
Note on EB328: Activity Name: L2 GEN - COLO3 Phase: CX Level 2 Location: COLO 3 Trade: None Start Date: 07-Mar-2025 End Date: 03-Apr-2025
Note on EB329: Activity Name: L2 UPM - COLO3 (UPM ROJ Driving) Phase: CX Level 2 Location: COLO 3 Trade: None Start Date: 07-Mar-2025 End Date: 03-Apr-2025
Note on EB330: Activity Name: L2 XFMR - COLO4 Phase: CX Level 2 Location: COLO 4 Trade: None Start Date: 07-Mar-2025 End Date: 03-Apr-2025
Note on EB331: Activity Name: L2 GEN - COLO4 Phase: CX Level 2 Location: COLO 4 Trade: None Start Date: 07-Mar-2025 End Date: 03-Apr-2025
Note on EB332: Activity Name: L2 UPM - COLO4 (UPM ROJ Driving) Phase: CX Level 2 Location: COLO 4 Trade: None Start Date: 07-Mar-2025 End Date: 03-Apr-2025
Note on CC333: Activity Name: L2 XFMR - COLO5 Phase: CX Level 2 Location: COLO 5 Trade: None Start Date: 15-Jan-2025 End Date: 11-Feb-2025
Note on CC334: Activity Name: L2 GEN - COLO5 Phase: CX Level 2 Location: COLO 5 Trade: None Start Date: 15-Jan-2025 End Date: 11-Feb-2025
Note on CC335: Activity Name: L2 UPM - COLO5 (UPM ROJ Driving) Phase: CX Level 2 Location: COLO 5 Trade: None Start Date: 15-Jan-2025 End Date: 11-Feb-2025
Note on CR336: Activity Name: L2 UMS 01 - COLO 5 Phase: CX Level 2 Location: COLO 5 Trade: None Start Date: 30-Jan-2025 End Date: 05-Feb-2025
Note on CR337: Activity Name: L2 URS 01 - COLO 5 Phase: CX Level 2 Location: COLO 5 Trade: None Start Date: 30-Jan-2025 End Date: 05-Feb-2025
Note on EB338: Activity Name: L2 UTS / UTSR - Site Phase: CX Level 2 Location: Site Trade: None Start Date: 07-Mar-2025 End Date: 13-Mar-2025
Note on GD339: Activity Name: Level 4 Cx - Colo 5 Phase: COLO 5 Location: All Trade: None Start Date: 30-Apr-2025 End Date: 03-Jun-2025
Note on HM339: Activity Name: Level 5 Cx / IST - Colo 5 Phase: COLO 5 Location: All Trade: None Start Date: 04-Jun-2025 End Date: 05-Jun-2025
Note on DY341: Activity Name: Interior - L2 TCP/MSB - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on EF341: Activity Name: Interior - L2 UPS - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on EM341: Activity Name: Interior - L2 PDUs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on EF342: Activity Name: Interior - L2 ADP - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on EM342: Activity Name: Interior - L2 AHUs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on EM343: Activity Name: Interior - L2 ATSs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on EM344: Activity Name: Interior - L2 Busway - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on ET346: Activity Name: Interior - L3 TCP/MSB - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on FA346: Activity Name: Interior - L3 UPS - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on FH346: Activity Name: Interior - L3 Busway - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 08-Apr-2025 End Date: 14-Apr-2025
Note on ET347: Activity Name: Interior - L3 PDUs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on FA347: Activity Name: Interior - L3 ATSs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 01-Apr-2025 End Date: 07-Apr-2025
Note on ET348: Activity Name: Interior - L3 ADP - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 25-Mar-2025 End Date: 31-Mar-2025
Note on EV349: Activity Name: Interior - L3 AHUs - COLO5 Cell 1 Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 27-Mar-2025 End Date: 09-Apr-2025
Note on CO353: Activity Name: Termination at PDU & Busway- COLO5 Cell 1 - DH Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 27-Jan-2025 End Date: 14-Feb-2025
Note on DJ353: Activity Name: Finishes and Signage - COLO5 Cell 1 - DH Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 17-Feb-2025 End Date: 21-Feb-2025
Note on BG355: Activity Name: Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 24-Dec-2024 End Date: 15-Jan-2025
Note on CA356: Activity Name: Finishes and Signage - COLO5 Cell 1 - ER Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 13-Jan-2025 End Date: 17-Jan-2025
Note on CX357: Activity Name: Trim out MEP - COLO5 Cell 1 - MG Phase: COLO 5 Location: Cell 1 Trade: None Start Date: 05-Feb-2025 End Date: 11-Feb-2025
Note on DY358: Activity Name: Interior - L2 TCP/MSB - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on EF358: Activity Name: Interior - L2 UPS - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on EM358: Activity Name: Interior - L2 AHUs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on EF359: Activity Name: Interior - L2 PDUs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on EM359: Activity Name: Interior - L2 ATSs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on EF360: Activity Name: Interior - L2 ADP - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on EM360: Activity Name: Interior - L2 Busway - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on EW364: Activity Name: Interior - L3 TCP/MSB - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on FD364: Activity Name: Interior - L3 UPS - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on FK364: Activity Name: Interior - L3 AHUs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 11-Apr-2025 End Date: 24-Apr-2025
Note on EW365: Activity Name: Interior - L3 PDUs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on FD365: Activity Name: Interior - L3 ATSs - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on FW365: Activity Name: Interior - L3 Busway - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 23-Apr-2025 End Date: 29-Apr-2025
Note on EW366: Activity Name: Interior - L3 ADP - COLO5 Cell 2 Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on CV371: Activity Name: Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 03-Feb-2025 End Date: 21-Feb-2025
Note on DQ371: Activity Name: Termination at PDU & Busway- COLO5 Cell 2 - DH Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 24-Feb-2025 End Date: 14-Mar-2025
Note on EL371: Activity Name: Finishes and Signage - COLO5 Cell 2 - DH Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on DC372: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 10-Feb-2025 End Date: 21-Feb-2025
Note on CD375: Activity Name: Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 16-Jan-2025 End Date: 05-Feb-2025
Note on DQ375: Activity Name: Finishes and Signage - COLO5 Cell 2 - ER Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on CS377: Activity Name: Install ceiling and Light Fittings - COLO5 Cell 2 - MG Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 31-Jan-2025 End Date: 11-Feb-2025
Note on DE377: Activity Name: Trim out MEP - COLO5 Cell 2 - MG Phase: COLO 5 Location: Cell 2 Trade: None Start Date: 12-Feb-2025 End Date: 18-Feb-2025
Note on EE379: Activity Name: Interior - L2 TCP/MSB - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 10-Mar-2025 End Date: 14-Mar-2025
Note on EL379: Activity Name: Interior - L2 UPS - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on ES379: Activity Name: Interior - L2 AHUs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EL380: Activity Name: Interior - L2 PDUs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on ES380: Activity Name: Interior - L2 ATSs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EL381: Activity Name: Interior - L2 ADP - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on ES381: Activity Name: Interior - L2 Busway - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EW384: Activity Name: Interior - L3 TCP/MSB - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on FD384: Activity Name: Interior - L3 UPS - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on FP384: Activity Name: Interior - L3 Busway - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 16-Apr-2025 End Date: 22-Apr-2025
Note on EW385: Activity Name: Interior - L3 PDUs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on FD385: Activity Name: Interior - L3 ATSs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on EW386: Activity Name: Interior - L3 ADP - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on FD386: Activity Name: Interior - L3 AHUs - COLO5 Cell 3 Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 04-Apr-2025 End Date: 17-Apr-2025
Note on DJ391: Activity Name: Cable Pulling at PDU & Busway- COLO5 Cell 3 - DH Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 17-Feb-2025 End Date: 28-Feb-2025
Note on EZ391: Activity Name: Finishes and Signage - COLO5 Cell 3 - DH Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on DQ392: Activity Name: Termination at PDU & Busway - COLO5 Cell 3 - DH Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 24-Feb-2025 End Date: 14-Mar-2025
Note on BP394: Activity Name: Connect to Cable tray and conduit equipment - COLO5 Cell 3 - ER Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 02-Jan-2025 End Date: 08-Jan-2025
Note on CY394: Activity Name: Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 06-Feb-2025 End Date: 26-Feb-2025
Note on ES394: Activity Name: Finishes and Signage - COLO5 Cell 3 - ER Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on DE397: Activity Name: Pipe Testing - COLO5 Cell 3 - MG Phase: COLO 5 Location: Cell 3 Trade: Inspections Start Date: 12-Feb-2025 End Date: 13-Feb-2025
Note on DG397: Activity Name: Install ceiling and Light Fittings - COLO5 Cell 3 - MG Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 14-Feb-2025 End Date: 25-Feb-2025
Note on DS397: Activity Name: Trim out MEP - COLO5 Cell 3 - MG Phase: COLO 5 Location: Cell 3 Trade: None Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on CB400: Activity Name: Interior - L1 ATSs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on DX400: Activity Name: Interior - L1 PDUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on CB401: Activity Name: Interior - L1 Busway - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on CB402: Activity Name: Interior - L1 ADP - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 14-Jan-2025 End Date: 14-Jan-2025
Note on EO404: Activity Name: Interior - L2 TCP/MSB - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 20-Mar-2025 End Date: 26-Mar-2025
Note on EV404: Activity Name: Interior - L2 UPS - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 27-Mar-2025 End Date: 02-Apr-2025
Note on FC404: Activity Name: Interior - L2 Busway - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 03-Apr-2025 End Date: 09-Apr-2025
Note on ES405: Activity Name: Interior - L2 ADP - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EZ405: Activity Name: Interior - L2 PDUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 31-Mar-2025 End Date: 04-Apr-2025
Note on ES406: Activity Name: Interior - L2 AHUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on ES407: Activity Name: Interior - L2 ATSs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 24-Mar-2025 End Date: 28-Mar-2025
Note on EW408: Activity Name: Interior - L3 TCP/MSB - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on FD408: Activity Name: Interior - L3 ADP - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on FK408: Activity Name: Interior - L3 ATSs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 11-Apr-2025 End Date: 17-Apr-2025
Note on FR408: Activity Name: Interior - L3 Busway - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 18-Apr-2025 End Date: 24-Apr-2025
Note on FD409: Activity Name: Interior - L3 AHUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 04-Apr-2025 End Date: 17-Apr-2025
Note on FG410: Activity Name: Interior - L3 PDUs - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on FK411: Activity Name: Interior - L3 UPS - COLO5 Cell 4 Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 11-Apr-2025 End Date: 17-Apr-2025
Note on DX415: Activity Name: Closing Construction Access Door - COLO5 Cell 4 - DH Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 03-Mar-2025 End Date: 21-Mar-2025
Note on FN415: Activity Name: Finishes and Signage - COLO5 Cell 4 - DH Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 14-Apr-2025 End Date: 18-Apr-2025
Note on EE416: Activity Name: Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 10-Mar-2025 End Date: 21-Mar-2025
Note on EL417: Activity Name: Termination at PDU & Busway - COLO5 Cell 4 - DH Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 17-Mar-2025 End Date: 04-Apr-2025
Note on BU419: Activity Name: Installation of ADP & ATS - COLO5 Cell 4 - ER Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 07-Jan-2025 End Date: 13-Jan-2025
Note on DT419: Activity Name: Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 27-Feb-2025 End Date: 19-Mar-2025
Note on FG419: Activity Name: Finishes and Signage - COLO5 Cell 4 - ER Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on BW420: Activity Name: Connect to Cable tray and conduit equipment - COLO5 Cell 4 - ER Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 09-Jan-2025 End Date: 15-Jan-2025
Note on DE423: Activity Name: Piping and Electrical Termination to AHUs - COLO5 Cell 4 - MG Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 12-Feb-2025 End Date: 25-Feb-2025
Note on DS423: Activity Name: Pipe Testing - COLO5 Cell 4 - MG Phase: COLO 5 Location: Cell 4 Trade: Inspections Start Date: 26-Feb-2025 End Date: 27-Feb-2025
Note on DU423: Activity Name: Install ceiling and Light Fittings - COLO5 Cell 4 - MG Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 28-Feb-2025 End Date: 11-Mar-2025
Note on EG423: Activity Name: Trim out MEP - COLO5 Cell 4 - MG Phase: COLO 5 Location: Cell 4 Trade: None Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on DX427: Activity Name: L3 GEN - Colo 2 Cell 1 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 03-Mar-2025 End Date: 21-Mar-2025
Note on DX428: Activity Name: L3 XFMR - Colo 2 Cell 1 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 03-Mar-2025 End Date: 21-Mar-2025
Note on DX429: Activity Name: L3 UPM - Colo 2 Cell 1 Phase: CX Level 3 Location: COLO 2 Trade: None Start Date: 03-Mar-2025 End Date: 28-Mar-2025
Note on EP430: Activity Name: L3 UMS 04 - COLO 3 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 21-Mar-2025 End Date: 27-Mar-2025
Note on EW430: Activity Name: L3 UMS 03 - COLO 3 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 28-Mar-2025 End Date: 03-Apr-2025
Note on FD432: Activity Name: L3 GEN - Cell 1 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 04-Apr-2025 End Date: 24-Apr-2025
Note on FD433: Activity Name: L3 UPM - Cell 1 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 04-Apr-2025 End Date: 01-May-2025
Note on FK434: Activity Name: L3 XFMR - Cell 1 Phase: CX Level 3 Location: COLO 3 Trade: None Start Date: 11-Apr-2025 End Date: 01-May-2025
Note on FD435: Activity Name: L3 GEN - Cell 1 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 04-Apr-2025 End Date: 24-Apr-2025
Note on FD436: Activity Name: L3 XFMR - Cell 1 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 04-Apr-2025 End Date: 24-Apr-2025
Note on FD437: Activity Name: L3 UPM - Cell 1 Phase: CX Level 3 Location: COLO 4 Trade: None Start Date: 04-Apr-2025 End Date: 01-May-2025
Note on EP438: Activity Name: L3 URS 01 - COLO 5 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 21-Mar-2025 End Date: 27-Mar-2025
Note on EP439: Activity Name: L3 UMS 01 - COLO 5 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 21-Mar-2025 End Date: 27-Mar-2025
Note on DU440: Activity Name: L3 GEN - Cell 1 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 28-Feb-2025 End Date: 20-Mar-2025
Note on DU441: Activity Name: L3 UPM - Cell 1 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 28-Feb-2025 End Date: 27-Mar-2025
Note on EB442: Activity Name: L3 XFMR - Cell 1 Phase: CX Level 3 Location: COLO 5 Trade: None Start Date: 07-Mar-2025 End Date: 27-Mar-2025
Note on EI443: Activity Name: L3 UTS / UTSR - Site Phase: CX Level 3 Location: Site Trade: None Start Date: 14-Mar-2025 End Date: 20-Mar-2025

## CFA - Legends
COLO 4 |  | Yardwork |  | COLO 2 |  | COLO 3 |  | CX Level 2 |  | COLO 5 |  | CX Level 3
|  | RC1 | Install screen wall - Colo 2 - North |  |  |  |  | EE48 | L2 XFMR - COLO2 |  |  | EE49 | L3 GEN - Colo 2 Cell 1
Inspections |  | EE35 | Wire pulling and termination for TCP/MSB - Colo 2 - South | Inspections |  | Inspections |  |  |  | Inspections
I-R | Pipe Testing - COLO4 Cell 1 - MG |  |  | I-R | Pipe Testing - COLO2 Cell 3 - MG | I-R | Pipe Testing - COLO3 Cell 2 - MG |  |  | I-R | Pipe Testing - COLO5 Cell 3 - MG
N/A |  |  |  | N/A |  | N/A |  |  |  | N/A
MS1 | Level 4 Cx - Colo 4 |  |  | MS1 | Level 4 Cx - Colo 2 | MS1 | Level 4 Cx - Colo 3 |  |  | MS1 | Level 4 Cx - Colo 5
W4 | Closing Construction Access Door - COLO4 Cell 4 - DH |  |  | ET7 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH | J36 | Door Frame Installation - COLO3 Cell 1 - ER |  |  | W4 | Closing Construction Access Door - COLO5 Cell 4 - DH
J7 | Ceiling Grid and Tile - COLO4 Cell 1 - DH |  |  | ALL3 | Finishes and Signage - COLO2 Cell 1 - DH | GH3 | Install DX Split Units - COLO3 Cell 2 - ER |  |  | ET7 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH
GH3 | Install DX Split Units - COLO4 Cell 1 - ER |  |  | EE58 | Interior - L2 ADP - COLO2 Cell 1 | GA6 | Placing the AHU - COLO3 Cell 2 - MG |  |  | ALL3 | Finishes and Signage - COLO5 Cell 1 - DH
GA6 | Placing the AHU - COLO4 Cell 1 - MG |  |  |  |  | T3 | Install Walls and Primer Paint - COLO3 Cell 4 - MG |  |  | EE57 | Interior - L2 TCP/MSB - COLO5 Cell 1
T3 | Install Walls and Primer Paint - COLO4 Cell 2 - MG |  |  |  |  | ET7 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH
ET22 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH |  |  |  |  | ALL3 | Finishes and Signage - COLO3 Cell 1 - DH
ALL3 | Finishes and Signage - COLO4 Cell 1 - DH |  |  |  |  | S1 | Begin HAC Assembly - COLO3 Cell 1 - DH
S1 | Begin HAC Assembly - COLO4 Cell 1 - DH |  |  |  |  | EE63 | Interior - L1 PDUs - COLO3 Cell 1
EE62 | Interior - L1 UPS - COLO4 Cell 1