## Sheet1
Phase | Area | Trade | Color | Act Code | Task Name | Start Date | End Date
Exteriors | Exterior & Site | Boldt | #156082 | B01 | Install Monument Signs | 2026-04-16 | 2026-04-24
Exteriors | Exterior & Site | Boldt | #156082 | B02 | Install Building Signage | 2026-04-09 | 2026-04-15
Exteriors | Exterior & Site | Boldt | #156082 | B03 | Install Exterior Building Lights | 2026-04-16 | 2026-04-29
Exteriors | Exterior & Site | Boldt | #156082 | B04 | Install Fencing | 2026-11-23 | 2026-12-18
Exteriors | Exterior & Site | Electrical | #83E28E | E05 | Install Site Lighting | 2025-09-05 | 2025-10-02
Exteriors | Exterior & Site | Exteriors | #92D050 | EX4 | Form & Pour Sidewalks | 2026-10-19 | 2026-11-20
Exteriors | Exterior & Site | Exteriors | #92D050 | EX5 | Landscaping | 2026-11-23 | 2027-01-01
Exteriors | Exterior & Site | Exteriors | #92D050 | EX6 | Final Parking Lot Paving | 2026-12-21 | 2027-01-08
Exteriors | Exterior & Site | Exteriors | #92D050 | EX7 | Sealing & Striping Parking Lot | 2027-01-11 | 2027-01-22
Exteriors | Exterior Envelope & Roof | Electrical | #83E28E | E04 | Electrical Hook Ups for Mechanical Units | 2026-03-26 | 2026-04-08
Exteriors | Exterior Envelope & Roof | Exteriors | #F8F200 | GL-03 | Install Prefabricated Exterior Wall System | 2026-02-03 | 2026-03-30
Exteriors | Exterior Envelope & Roof | Exteriors | #F8F200 | GL-04 | Prefabrication of Exterior Wall System | 2025-07-07 | 2025-12-19
Exteriors | Exterior Envelope & Roof | Exteriors | #92D050 | EX1 | Delivery of Exterior Prefab System | 2026-01-30 | 2026-02-12
Exteriors | Exterior Envelope & Roof | Exteriors | #92D050 | EX2 | Exterior Complete / Building Dry In |  | 2026-04-08
Exteriors | Exterior Envelope & Roof | Exteriors | #92D050 | EX3 | Weather Days | 2026-04-09 | 2026-05-06
Exteriors | Exterior Envelope & Roof | Glazing | #94DCF8 | GL-02 | Install Windows | 2026-03-05 | 2026-04-08
Exteriors | Exterior Envelope & Roof | Mechanical | #FFFF66 | ME-02 | Install Supports for Mechanical Units & Roof Curbs | 2026-01-06 | 2026-01-26
Exteriors | Exterior Envelope & Roof | Mechanical | #FFFF66 | ME-03 | Install Mechanical Units on Roof | 2026-03-12 | 2026-03-25
Exteriors | Exterior Envelope & Roof | MEP | #CC0066 | MEP6 | Install MEP Deck Inserts | 2026-01-06 | 2026-01-26
Exteriors | Exterior Envelope & Roof | Roofing | #F1A983 | RF-01 | Install Roofing | 2026-02-12 | 2026-03-11
Exteriors | Exterior Envelope & Roof | Structural | #BFBFBF | ST-02 | Install Structural Steel & Stairs | 2025-11-17 | 2025-12-05
Exteriors | Exterior Envelope & Roof | Structural | #BFBFBF | ST-03 | Install Metal Decking | 2025-12-08 | 2026-01-05
Exteriors | Exterior Envelope & Roof | Structural | #BFBFBF | ST-04 | Install Reinforcement at Metal Decks | 2025-12-23 | 2026-01-26
Exteriors | Exterior Envelope & Roof | Structural | #BFBFBF | ST-05 | Place Concrete at Metal Decks | 2026-01-27 | 2026-02-09
Foundations | Foundations | Foundations | #FF7C80 | F1 | Layout Building Footings | 2025-09-04 | 2025-09-08
Foundations | Foundations | Foundations | #FF7C80 | F2 | Excavate Footings | 2025-09-22 | 2025-09-30
Foundations | Foundations | Foundations | #FF7C80 | F3 | Install Rebar for Footings | 2025-09-25 | 2025-10-10
Foundations | Foundations | Foundations | #FF7C80 | F4 | Inspection for Footing Pour | 2025-10-13 | 2025-10-13
Foundations | Foundations | Foundations | #FF7C80 | F5 | Place Concrete for Footings | 2025-10-14 | 2025-10-15
Foundations | Foundations | Foundations | #FF7C80 | F6 | Install UG Building Utilities | 2025-09-08 | 2025-09-26
Foundations | Foundations | Foundations | #FF7C80 | F7 | Install Forms for Building Slab | 2025-10-21 | 2025-10-29
Foundations | Foundations | Foundations | #FF7C80 | F8 | Install Rebar for Building Slab | 2025-10-23 | 2025-11-05
Foundations | Foundations | Foundations | #FF7C80 | F9 | Inspection for Building Slab Pour | 2025-11-16 | 2025-11-06
Foundations | Foundations | Foundations | #FF7C80 | F10 | Place & Finish Concrete for Building Slab | 2025-11-17 | 2025-11-10
Foundations | Foundations | Foundations | #FF7C80 | F11 | Layout for Building Slab | 2025-10-16 | 2025-10-20
Foundations | LINAC | LINAC | #747474 | LIN1 | Foundations / SOG | 2025-09-29 | 2025-10-31
Foundations | LINAC | LINAC | #747474 | LIN2 | Form / Pour Walls | 2025-11-03 | 2025-12-19
Foundations | LINAC | LINAC | #747474 | LIN3 | Cure Time & Strip Forms | 2025-12-22 | 2026-01-14
Foundations | LINAC | LINAC | #747474 | LIN4 | Roof | 2026-01-15 | 2026-02-11
Foundations | LINAC | LINAC | #747474 | LIN3 | Cure Time & Strip Forms | 2026-02-12 | 2026-03-12
Foundations | LINAC | LINAC | #747474 | LIN5 | Clean / Sack & Patch | 2026-03-13 | 2026-03-19
Interiors | 1st Floor | ACT | #404040 | AC1 | Install ACT | 2026-08-17 | 2026-09-11
Interiors | 1st Floor | Boldt | #156082 | FC01 | Final Clean | 2026-11-26 | 2026-12-04
Interiors | 1st Floor | Boldt | #156082 | FC02 | Punchlist | 2026-11-30 | 2026-12-11
Interiors | 1st Floor | Carpentry | #CC6600 | C1 | Install Casework & Accessories | 2026-09-28 | 2026-10-23
Interiors | 1st Floor | DFH | #CCCCFF | DFH1 | Install Doors & Hardware | 2026-11-02 | 2026-11-20
Interiors | 1st Floor | Drywall | #FF7A5B | D1 | Install Drywall | 2026-07-16 | 2026-08-19
Interiors | 1st Floor | Drywall | #FF7A5B | D2 | Tape & Finish | 2026-07-23 | 2026-08-26
Interiors | 1st Floor | Fireproof | #FFC000 | FP | Fireproofing | 2026-04-23 | 2026-05-13
Interiors | 1st Floor | Flooring | #FF66CC | FL1 | Install Flooring | 2026-10-05 | 2026-10-30
Interiors | 1st Floor | Interiors | #109C85 | IN1 | Install Ceiling Tile | 2026-09-07 | 2026-09-25
Interiors | 1st Floor | Interiors | #109C85 | IN2 | Install Signage | 2026-11-16 | 2026-11-20
Interiors | 1st Floor | Interiors | #109C85 | IN3 | Install PODS | 2026-06-02 | 2026-06-15
Interiors | 1st Floor | Interiors | #109C85 | IN4 | Install OFCI Equipment | 2026-10-19 | 2026-11-06
Interiors | 1st Floor | MEP | #CC0066 | MEP7 | MEP Rough In | 2026-07-09 | 2026-08-12
Interiors | 1st Floor | MEP | #CC0066 | MEP8 | MEP Rough In at ACT | 2026-08-24 | 2026-09-18
Interiors | 1st Floor | MEP | #CC0066 | MEP9 | OH MEP Rough In | 2026-05-14 | 2026-06-10
Interiors | 1st Floor | Paint | #7030A0 | P1 | Prime & Paint | 2026-08-10 | 2026-09-04
Interiors | 1st Floor | Paint | #7030A0 | P2 | Final Paint | 2026-11-23 | 2026-11-27
Interiors | 1st Floor | Walls | #00CC00 | W1 | Prefabrication of Interior Walls | 2025-12-11 | 2026-05-27
Interiors | 1st Floor | Walls | #00CC00 | W2 | Delivery of Prefabricated Walls | 2026-05-21 | 2026-06-03
Interiors | 1st Floor | Walls | #00CC00 | W3 | Layout for Prefab Walls | 2026-04-13 | 2026-04-21
Interiors | 1st Floor | Walls | #00CC00 | W4 | Install of Prefab Walls | 2026-07-02 | 2026-08-05
Interiors | 2nd Floor | ACT | #404040 | AC1 | Install ACT | 2026-07-20 | 2026-08-14
Interiors | 2nd Floor | Boldt | #156082 | FC01 | Final Clean | 2026-10-14 | 2026-10-22
Interiors | 2nd Floor | Boldt | #156082 | FC02 | Punchlist | 2026-10-14 | 2026-10-27
Interiors | 2nd Floor | Carpentry | #CC6600 | C1 | Install Casework & Accessories | 2026-08-12 | 2026-09-08
Interiors | 2nd Floor | DFH | #CCCCFF | DFH1 | Install Doors & Hardware | 2026-09-16 | 2026-10-06
Interiors | 2nd Floor | Drywall | #FF7A5B | D1 | Install Drywall | 2026-06-18 | 2026-07-22
Interiors | 2nd Floor | Drywall | #FF7A5B | D2 | Tape & Finish | 2026-06-25 | 2026-07-29
Interiors | 2nd Floor | Fireproof | #FFC000 | FP | Fireproofing | 2026-04-02 | 2027-04-22
Interiors | 2nd Floor | Flooring | #FF66CC | FL1 | Install Flooring | 2026-08-19 | 2026-09-15
Interiors | 2nd Floor | Interiors | #109C85 | IN1 | Install Ceiling Tile | 2026-08-10 | 2026-08-28
Interiors | 2nd Floor | Interiors | #109C85 | IN2 | Intsall Signage | 2026-09-30 | 2026-10-06
Interiors | 2nd Floor | Interiors | #109C85 | IN3 | Install PODS | 2026-05-14 | 2026-05-20
Interiors | 2nd Floor | Interiors | #109C85 | IN4 | Install OFCI Equipment | 2026-09-02 | 2026-09-22
Interiors | 2nd Floor | MEP | #CC0066 | MEP7 | MEP Rough In | 2026-06-11 | 2026-07-15
Interiors | 2nd Floor | MEP | #CC0066 | MEP8 | MEP Rough In at ACT | 2026-07-27 | 2026-08-21
Interiors | 2nd Floor | MEP | #CC0066 | MEP9 | OH MEP Rough In | 2026-04-23 | 2026-05-20
Interiors | 2nd Floor | Paint | #7030A0 | P1 | Prime & Paint | 2026-07-13 | 2026-08-07
Interiors | 2nd Floor | Paint | #7030A0 | P2 | Final Paint | 2026-10-07 | 2026-10-13
Interiors | 2nd Floor | Walls | #00CC00 | W1 | Prefabrication of Interior Walls | 2025-12-01 | 2026-05-15
Interiors | 2nd Floor | Walls | #00CC00 | W2 | Delivery of Prefabricated Walls | 2026-05-11 | 2026-05-22
Interiors | 2nd Floor | Walls | #00CC00 | W3 | Layout for Prefab Walls | 2026-04-06 | 2026-04-10
Interiors | 2nd Floor | Walls | #00CC00 | W4 | Install of Prefab Walls | 2026-06-04 | 2026-07-08
Interiors | 3rd Floor | ACT | #404040 | AC1 | Install ACT | 2026-06-22 | 2026-07-17
Interiors | 3rd Floor | Boldt | #156082 | FC01 | Final Clean | 2026-09-11 | 2026-09-21
Interiors | 3rd Floor | Boldt | #156082 | FC02 | Punchlist | 2026-09-11 | 2026-09-24
Interiors | 3rd Floor | Carpentry | #CC6600 | C1 | Install Casework & Accessories | 2026-07-15 | 2026-08-11
Interiors | 3rd Floor | DFH | #CCCCFF | DFH1 | Install Doors & Hardware | 2026-08-14 | 2026-09-03
Interiors | 3rd Floor | Drywall | #FF7A5B | D1 | Install Drywall | 2026-05-21 | 2026-06-24
Interiors | 3rd Floor | Drywall | #FF7A5B | D2 | Tape & Finish | 2026-05-28 | 2026-07-01
Interiors | 3rd Floor | Fireproof | #FFC000 | FP | Fireproofing | 2026-03-12 | 2026-04-01
Interiors | 3rd Floor | Flooring | #FF66CC | FL1 | Install Flooring | 2026-07-22 | 2026-08-18
Interiors | 3rd Floor | Interiors | #109C85 | IN1 | Install Ceiling Tile | 2026-07-13 | 2026-07-31
Interiors | 3rd Floor | Interiors | #109C85 | IN2 | Intsall Signage | 2026-08-28 | 2026-09-03
Interiors | 3rd Floor | Interiors | #109C85 | IN3 | Install PODS | 2026-04-30 | 2026-05-13
Interiors | 3rd Floor | Interiors | #109C85 | IN4 | Install OFCI Equipment | 2026-08-05 | 2026-08-25
Interiors | 3rd Floor | MEP | #CC0066 | MEP7 | MEP Rough In | 2026-05-14 | 2026-06-17
Interiors | 3rd Floor | MEP | #CC0066 | MEP8 | MEP Rough In at ACT | 2026-06-29 | 2026-07-24
Interiors | 3rd Floor | MEP | #CC0066 | MEP9 | OH MEP Rough In | 2026-04-02 | 2026-04-29
Interiors | 3rd Floor | Paint | #7030A0 | P1 | Prime & Paint | 2026-06-15 | 2026-07-10
Interiors | 3rd Floor | Paint | #7030A0 | P2 | Final Paint | 2026-09-04 | 2026-09-10
Interiors | 3rd Floor | Walls | #00CC00 | W1 | Prefabrication of Interior Walls | 2025-10-16 | 2026-04-01
Interiors | 3rd Floor | Walls | #00CC00 | W2 | Delivery of Prefabricated Walls | 2026-04-16 | 2026-04-29
Interiors | 3rd Floor | Walls | #00CC00 | W3 | Layout for Prefab Walls | 2026-03-30 | 2026-04-03
Interiors | 3rd Floor | Walls | #00CC00 | W4 | Install of Prefab Walls | 2026-05-07 | 2026-06-10
Interiors | Close Out | Close Out | #A6C9EC | CO-01 | Final Agency Sign Off | 2027-06-03 | 2027-06-09
Interiors | Close Out | Close Out | #A6C9EC | CO-02 | Recieve C of O |  | 2027-06-09
Interiors | Close Out | Close Out | #A6C9EC | CO-03 | First Patient - ASC |  | 2027-10-15
Interiors | Close Out | Close Out | #A6C9EC | CO-04 | CDPH Licensing | 2027-06-11 | 2027-10-14
Interiors | Close Out | Close Out | #A6C9EC | CO-05 | Receive TCO | 2027-03-04 | 2027-03-17
Interiors | Close Out | Close Out | #A6C9EC | CO-06 | Owner Fit Up/Staff & Stock | 2027-03-18 | 2027-06-09
Interiors | Close Out | Close Out | #A6C9EC | CO-07 | First Patient - Clinic |  | 2027-06-10
Interiors | Shafts/Elevators | Elevator | #0070C0 | EL-02 | Install Elevators | 2026-03-09 | 2026-10-02
Interiors | Shafts/Elevators | Fireproof | #FFC000 | FP | Fireproofing | 2026-02-09 | 2026-02-20
Interiors | Shafts/Elevators | MEP | #CC0066 | MEP7 | MEP Rough in Walls - All Floors | 2026-02-23 | 2026-03-06
Interiors | Shafts/Elevators | Walls | #00CC00 | W3 | Layout Wall Framing - All Floors | 2026-02-04 | 2026-02-10
Interiors | Shafts/Elevators | Walls | #00CC00 | W5 | Frame Walls - All Floors | 2026-02-16 | 2026-03-06
Interiors | Start Up & Commissionning | Boldt | #156082 | COM01 | Air Balance | 2026-12-21 | 2027-01-18
Interiors | Start Up & Commissionning | Boldt | #156082 | COM02 | Fire Alarm Testing | 2027-02-02 | 2027-02-17
Interiors | Start Up & Commissionning | Boldt | #156082 | COM03 | Power on to Building | 2026-06-15 | 2026-07-10
Interiors | Start Up & Commissionning | Boldt | #156082 | COM04 | Provide Air Balance Report | 2027-01-19 | 2027-02-01
Interiors | Start Up & Commissionning | Boldt | #156082 | COM05 | Start Up & Test Generator | 2027-02-18 | 2027-03-03
Interiors | Start Up & Commissionning | Boldt | #156082 | COM06 | State Elevator Inspection | 2027-02-18 | 2027-03-03
Interiors | Start Up & Commissionning | Boldt | #156082 | COM07 | Fire Alarm Pretesting | 2027-01-12 | 2027-02-01
Interiors | Start Up & Commissionning | Boldt | #156082 | COM08 | Install SMUD Gear | 2026-06-01 | 2026-06-12
Interiors | Start Up & Commissionning | Boldt | #156082 | COM09 | Air Quality Control Board Sign Off | 2027-02-18 | 2027-03-03
Interiors | Start Up & Commissionning | HVAC | #66FF66 | HVAC1 | Start Up HVAC Units | 2026-12-27 | 2026-12-18
Site | Site Work | Site | #C00000 | SI-01 | Site Demo & Clearing / SS & SD Tie In's | 2025-05-06 | 2025-06-02
Site | Site Work | Site | #C00000 | SI-02 | Grading for Building Pad & Parking Lots | 2025-08-22 | 2025-09-11
Site | Site Work | Site | #C00000 | SI-03 | Install UG Utilities | 2025-05-27 | 2025-07-29
Site | Site Work | Site | #C00000 | SI-04 | Install Retaining Walls | 2025-05-27 | 2025-09-29
Site | Site Work | Site | #C00000 | SI-05 | Phase 1 Site - Mobilization | 2025-05-05 | 2025-05-09
Site | Site Work | Site | #C00000 | SI-06 | Building Pad Certified |  | 2025-09-04
Site | Site Work | Site | #C00000 | SI-07 | Install SWPPP BMPs | 2025-05-05 | 2025-05-23
Site | Site Work | Site | #C00000 | SI-08 | Weather Days | 2025-09-05 | 2025-10-02
Site | Site Work | Site | #C00000 | SI-09 | Site Survey | 2025-05-05 | 2025-05-07
Site | Site Work | Site | #C00000 | SI-10 | Install Temp Site Fencing | 2025-05-05 | 2025-05-13
Site | Site Work | Site | #C00000 | SI-11 | Survey for Building Layout | 2025-09-02 | 2025-09-04
Site | Site Work | Site | #C00000 | SI-12 | Install UG Site Utilities | 2025-09-02 | 2025-09-22
Site | Site Work | Site | #C00000 | SI-13 | Form & Pour Curbs/Gutters at Parking Lot | 2025-09-05 | 2025-09-25
Site | Site Work | Site | #C00000 | SI-14 | Pave 1st Lift | 2025-09-26 | 2025-10-01
Site | Site Work | Site | #C00000 | SI-15 | Install Project Trailers | 2025-10-02 | 2025-10-06
Site | Site Work | Site | #C00000 | SI-16 | FOUNDATIONS PERMIT | 2025-09-05 | 2025-09-11