## Sheet1
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E22 | Control Power Checks | 2025-06-04 | 2025-06-12
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E22 | Control Power Checks | 2025-06-09 | 2025-06-18
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E22 | Control Power Checks | 2025-06-13 | 2025-06-23
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E22 | Control Power Checks | 2025-06-24 | 2025-07-07
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E21 | EPMS Point to Point Checks | 2025-06-13 | 2025-06-23
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E21 | EPMS Point to Point Checks | 2025-06-19 | 2025-06-27
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E21 | EPMS Point to Point Checks | 2025-06-24 | 2025-07-02
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E21 | EPMS Point to Point Checks | 2025-07-08 | 2025-07-18
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E20 | FTE Energizations [480v] | 2025-06-25 | 2025-06-28
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E20 | FTE Energizations [480v] | 2025-06-28 | 2025-07-02
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E20 | FTE Energizations [480v] | 2025-07-03 | 2025-07-09
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E20 | FTE Energizations [480v] | 2025-07-19 | 2025-07-24
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) | Electrical | #F3F0A8 | E19 | Install Metering Cabinet [Prior to Energization] | 2025-06-19 | 2025-06-24
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E16 | Loadbanking | 2025-07-16 | 2025-07-19
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E16 | Loadbanking | 2025-07-21 | 2025-07-24
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E16 | Loadbanking | 2025-07-25 | 2025-07-30
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E16 | Loadbanking | 2025-08-09 | 2025-08-14
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E15 | Startups | 2025-06-30 | 2025-07-15
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E15 | Startups | 2025-07-03 | 2025-07-18
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E15 | Startups | 2025-07-10 | 2025-07-23
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E15 | Startups | 2025-07-25 | 2025-08-08
Commissioning (L2 - L5) COLO3 | C3 Functional Testing (Level 4) | MSFT | #E2EFDA | W2 | Testing L4 <MSFT Duration> | 2025-08-15 | 2025-09-15
Commissioning (L2 - L5) COLO3 | C3 Functional Testing (Level 5) | MSFT | #E2EFDA | W3 | Testing L5 <MSFT Duration> | 2025-09-16 | 2025-09-18
Commissioning (L2 - L5) COLO3 | C3 Yellow Tags (Level 2) CELL 1 | Electrical | #F3F0A8 | EE24 | Yellow Tags | 2025-05-05 | 2025-05-28
Commissioning (L2 - L5) COLO3 | C3 Yellow Tags (Level 2) CELL 2 | Electrical | #F3F0A8 | EE24 | Yellow Tags | 2025-05-15 | 2025-06-07
Commissioning (L2 - L5) COLO3 | C3 Yellow Tags (Level 2) CELL 4 | Electrical | #F3F0A8 | EE24 | Yellow Tags | 2025-05-27 | 2025-06-18
Commissioning (L2 - L5) COLO3 | C3 Yellow Tags (Level 2) CELL 3 | Electrical | #F3F0A8 | EE24 | Yellow Tags | 2025-06-09 | 2025-07-02
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E22 | Control Power Checks | 2025-06-20 | 2025-06-28
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E22 | Control Power Checks | 2025-06-25 | 2025-07-03
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E22 | Control Power Checks | 2025-07-18 | 2025-07-28
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E22 | Control Power Checks | 2025-08-06 | 2025-08-14
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E21 | EPMS Point to Point Checks | 2025-06-30 | 2025-07-10
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E21 | EPMS Point to Point Checks | 2025-07-07 | 2025-07-15
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E21 | EPMS Point to Point Checks | 2025-07-29 | 2025-08-06
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E21 | EPMS Point to Point Checks | 2025-08-15 | 2025-08-25
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E20 | FTE Energizations [480v] | 2025-07-11 | 2025-07-15
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E20 | FTE Energizations [480v] | 2025-07-16 | 2025-07-19
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E20 | FTE Energizations [480v] | 2025-08-07 | 2025-08-11
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E20 | FTE Energizations [480v] | 2025-08-26 | 2025-08-29
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E16 | Loadbanking | 2025-07-31 | 2025-08-04
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E16 | Loadbanking | 2025-08-05 | 2025-08-08
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E16 | Loadbanking | 2025-08-27 | 2025-08-30
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E16 | Loadbanking | 2025-09-16 | 2025-09-19
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E15 | Startups | 2025-07-21 | 2025-08-04
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E15 | Startups | 2025-07-16 | 2025-07-30
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E15 | Startups | 2025-08-12 | 2025-08-26
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E15 | Startups | 2025-08-30 | 2025-09-15
Commissioning (L2 - L5) COLO4 | C4 Functional Testing (Level 4) | MSFT | #E2EFDA | W1 | Testing <MSFT Duration> | 2025-09-20 | 2025-10-16
Commissioning (L2 - L5) COLO4 | C4 Functional Testing (Level 5) | MSFT | #E2EFDA | W1 | Testing <MSFT Duration> | 2025-10-17 | 2025-10-20
Commissioning (L2 - L5) COLO4 | C4 Yellow Tags (Level 2) CELL 1 | Electrical | #F3F0A8 | EE24 | Yellow Tags | 2025-05-06 | 2025-05-29
Commissioning (L2 - L5) COLO4 | C4 Yellow Tags (Level 2) CELL 2 | Electrical | #F3F0A8 | EE24 | Yellow Tags | 2025-05-31 | 2025-06-24
Commissioning (L2 - L5) COLO4 | C4 Yellow Tags (Level 2) CELL 4 | Electrical | #F3F0A8 | EE24 | Yellow Tags | 2025-06-27 | 2025-07-22
Commissioning (L2 - L5) COLO4 | C4 Yellow Tags (Level 2) CELL 3 | Electrical | #F3F0A8 | EE24 | Yellow Tags | 2025-07-22 | 2025-08-14
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E22 | Control Power Checks | 2025-07-19 | 2025-07-29
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E22 | Control Power Checks | 2025-07-24 | 2025-08-02
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E22 | Control Power Checks | 2025-08-04 | 2025-08-12
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E22 | Control Power Checks | 2025-08-25 | 2025-09-03
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E21 | EPMS Point to Point Checks | 2025-07-30 | 2025-08-07
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E21 | EPMS Point to Point Checks | 2025-08-04 | 2025-08-12
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E21 | EPMS Point to Point Checks | 2025-08-13 | 2025-08-22
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E21 | EPMS Point to Point Checks | 2025-09-04 | 2025-09-13
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E20 | FTE Energizations [480v] | 2025-08-08 | 2025-08-12
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E20 | FTE Energizations [480v] | 2025-08-13 | 2025-08-18
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E20 | FTE Energizations [480v] | 2025-08-23 | 2025-08-27
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E20 | FTE Energizations [480v] | 2025-09-15 | 2025-09-19
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E16 | Loadbanking | 2025-08-28 | 2025-09-02
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E16 | Loadbanking | 2025-09-03 | 2025-09-08
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E16 | Loadbanking | 2025-09-13 | 2025-09-17
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E16 | Loadbanking | 2025-10-06 | 2025-10-11
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 1 | Electrical | #F3F0A8 | E15 | Startups | 2025-08-13 | 2025-08-27
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 2 | Electrical | #F3F0A8 | E15 | Startups | 2025-08-19 | 2025-09-02
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 4 | Electrical | #F3F0A8 | E15 | Startups | 2025-08-28 | 2025-09-12
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 3 | Electrical | #F3F0A8 | E15 | Startups | 2025-09-20 | 2025-10-04
Commissioning (L2 - L5) COLO5 | C5 Functional Testing (Level 4) | MSFT | #E2EFDA | W1 | Testing <MSFT Duration> | 2025-10-17 | 2025-11-15
Commissioning (L2 - L5) COLO5 | C5 Functional Testing (Level 5) | MSFT | #E2EFDA | W1 | Testing <MSFT Duration> | 2025-11-17 | 2025-11-19
Commissioning (L2 - L5) COLO5 | C5 Yellow Tags (Level 2) CELL 1 | Electrical | #F3F0A8 | EE24 | Yellow Tags | 2025-06-05 | 2025-06-28
Commissioning (L2 - L5) COLO5 | C5 Yellow Tags (Level 2) CELL 2 | Electrical | #F3F0A8 | EE24 | Yellow Tags | 2025-06-28 | 2025-07-23
Commissioning (L2 - L5) COLO5 | C5 Yellow Tags (Level 2) CELL 4 | Electrical | #F3F0A8 | EE24 | Yellow Tags | 2025-07-15 | 2025-08-07
Commissioning (L2 - L5) COLO5 | C5 Yellow Tags (Level 2) CELL 3 | Electrical | #F3F0A8 | EE24 | Yellow Tags | 2025-08-09 | 2025-09-03
Core & Shell | Admin/ COLO 3 | Drywall | #CFACFF | D3 | Install Exterior Wall Panels | 2024-11-18 | 2024-11-29
Core & Shell | COLO 4 | Drywall | #CFACFF | D3 | Install Exterior Wall Panels | 2024-11-21 | 2024-12-14
Core & Shell | COLO 5 | Drywall | #CFACFF | D3 | Install Exterior Wall Panels | 2024-12-04 | 2024-12-31
Core & Shell | Admin/ COLO 3 | Mech | #F8D9E7 | S4 | Install Louvers & Dampers | 2024-12-16 | 2025-01-06
Core & Shell | COLO 4 | Mech | #D3E660 | M4 | Install Louvers & Dampers | 2025-01-07 | 2025-01-25
Core & Shell | COLO 5 | Mech | #D3E660 | M4 | Install Louvers & Dampers | 2025-01-27 | 2025-02-14
Core & Shell | Admin/ COLO 3 | Framing | #5297F8 | X36 | Install Misc. Metals (Trims, Gutters, Catwalks) | 2024-12-30 | 2025-01-17
Core & Shell | COLO 4 | Framing | #5297F8 | X36 | Install Misc. Metals (Trims, Gutters, Catwalks) | 2025-01-11 | 2025-01-30
Core & Shell | COLO 5 | Framing | #5297F8 | X36 | Install Misc. Metals (Trims, Gutters, Catwalks) | 2025-01-27 | 2025-02-14
Core & Shell | Admin/ COLO 3 | Framing | #5297F8 | X37 | Install Primary Steel | 2024-10-14 | 2024-11-07
Core & Shell | COLO 4 | Framing | #5297F8 | X37 | Install Primary Steel | 2024-11-01 | 2024-11-20
Core & Shell | COLO 5 | Framing | #5297F8 | X37 | Install Primary Steel | 2024-11-12 | 2024-12-03
Core & Shell | Admin/ COLO 3 | Framing | #5297F8 | X8 | Install Roof Panels | 2024-11-30 | 2024-12-14
Core & Shell | COLO 4 | Framing | #5297F8 | X8 | Install Roof Panels | 2024-12-16 | 2024-12-31
Core & Shell | COLO 5 | Framing | #5297F8 | X8 | Install Roof Panels | 2025-01-02 | 2025-01-15
Core & Shell | Admin/ COLO 3 | SOG | #C65911 | F2 | Prep / Place SOG | 2024-12-16 | 2024-12-27
Core & Shell | COLO 4 | SOG | #C65911 | F2 | Prep / Place SOG | 2024-12-30 | 2025-01-10
Core & Shell | COLO 5 | SOG | #C65911 | F2 | Prep / Place SOG | 2025-01-14 | 2025-01-25
Core & Shell | Admin/ COLO 3 | Electrical | #F3F0A8 | E14 | UG MEP Work AMS | 2024-11-13 | 2024-12-14
Core & Shell | COLO 4 | Electrical | #F3F0A8 | E14 | UG MEP Work AMS | 2024-12-04 | 2024-12-27
Core & Shell | COLO 5 | Electrical | #F3F0A8 | E14 | UG MEP Work AMS | 2024-12-17 | 2025-01-13
Core & Shell | Admin/ COLO 3 | Buffer | #E7E6E6 | BW | Weather Days | 2024-12-30 | 2025-01-16
Electrical Yard | Admin/ COLO 3 | Electrical | #F3F0A8 | E26 | Build Equipment Pads for Generators | 2025-02-20 | 2025-03-03
Electrical Yard | COLO 4 | Electrical | #F3F0A8 | E26 | Build Equipment Pads for Generators | 2025-03-27 | 2025-04-05
Electrical Yard | COLO 5 | Electrical | #F3F0A8 | E26 | Build Equipment Pads for Generators | 2025-04-30 | 2025-05-10
Electrical Yard | Admin/ COLO 3 | Electrical | #F3F0A8 | E25 | Build Equipment Pads for UMSs | 2025-02-10 | 2025-02-19
Electrical Yard | COLO 4 | Electrical | #F3F0A8 | E25 | Build Equipment Pads for UMSs | 2025-03-15 | 2025-03-26
Electrical Yard | COLO 5 | Electrical | #F3F0A8 | E25 | Build Equipment Pads for UMSs | 2025-04-19 | 2025-04-29
Electrical Yard | Admin/ COLO 3 | Electrical | #F3F0A8 | E24 | Build Equipment Pads for UPMs | 2025-01-29 | 2025-02-07
Electrical Yard | COLO 4 | Electrical | #F3F0A8 | E24 | Build Equipment Pads for UPMs | 2025-03-05 | 2025-03-14
Electrical Yard | COLO 5 | Electrical | #F3F0A8 | E24 | Build Equipment Pads for UPMs | 2025-04-08 | 2025-04-18
Electrical Yard | Admin/ COLO 3 | Electrical | #F3F0A8 | E23 | Build Equipment Pads for XFMs | 2025-01-17 | 2025-01-28
Electrical Yard | COLO 4 | Electrical | #F3F0A8 | E23 | Build Equipment Pads for XFMs | 2025-02-21 | 2025-03-04
Electrical Yard | COLO 5 | Electrical | #F3F0A8 | E23 | Build Equipment Pads for XFMs | 2025-03-28 | 2025-04-07
Electrical Yard | Admin/ COLO 3 | Electrical | #F3F0A8 | E28 | Install Generators | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F3F0A8 | E28 | Install Generators | 2025-04-11 | 2025-04-24
Electrical Yard | COLO 5 | Electrical | #F3F0A8 | E28 | Install Generators | 2025-05-19 | 2025-05-31
Electrical Yard | Admin/ COLO 3 | Electrical | #F3F0A8 | E29 | Install UMSs | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F3F0A8 | E29 | Install UMSs | 2025-04-02 | 2025-04-15
Electrical Yard | COLO 5 | Electrical | #F3F0A8 | E29 | Install UMSs | 2025-05-16 | 2025-05-29
Electrical Yard | Admin/ COLO 3 | Electrical | #F3F0A8 | E30 | Install UPMs | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F3F0A8 | E30 | Install UPMs | 2025-04-02 | 2025-04-15
Electrical Yard | COLO 5 | Electrical | #F3F0A8 | E30 | Install UPMs | 2025-05-14 | 2025-05-27
Electrical Yard | Admin/ COLO 3 | Electrical | #F3F0A8 | E27 | Install XFMs | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F3F0A8 | E27 | Install XFMs | 2025-04-02 | 2025-04-15
Electrical Yard | COLO 5 | Electrical | #F3F0A8 | E27 | Install XFMs | 2025-05-12 | 2025-05-23
Electrical Yard | Admin/ COLO 3 CELL 1 | Electrical | #F3F0A8 | E35 | MV Cable Pulling & Terminating | 2025-04-25 | 2025-05-05
Electrical Yard | Admin/ COLO 3 CELL 2 | Electrical | #F3F0A8 | E35 | MV Cable Pulling & Terminating | 2025-05-06 | 2025-05-14
Electrical Yard | Admin/ COLO 3 CELL 4 | Electrical | #F3F0A8 | E35 | MV Cable Pulling & Terminating | 2025-05-15 | 2025-05-23
Electrical Yard | Admin/ COLO 3 CELL 3 | Electrical | #F3F0A8 | E35 | MV Cable Pulling & Terminating | 2025-05-27 | 2025-06-03
Electrical Yard | COLO 4 CELL1 | Electrical | #F3F0A8 | E35 | MV Cable Pulling & Terminating | 2025-04-25 | 2025-05-05
Electrical Yard | COLO 4 CELL2 | Electrical | #F3F0A8 | E35 | MV Cable Pulling & Terminating | 2025-05-06 | 2025-05-14
Electrical Yard | COLO 4 CELL 4 | Electrical | #F3F0A8 | E35 | MV Cable Pulling & Terminating | 2025-05-15 | 2025-05-23
Electrical Yard | COLO 4 CELL 3 | Electrical | #F3F0A8 | E35 | MV Cable Pulling & Terminating | 2025-05-27 | 2025-06-04
Electrical Yard | COLO 5 CELL1 | Electrical | #F3F0A8 | E40 | MV Cable Pulling & Terminating(To Junction Box) | 2025-05-02 | 2025-05-12
Electrical Yard | COLO 5 CELL 2 | Electrical | #F3F0A8 | E40 | MV Cable Pulling & Terminating(To Junction Box) | 2025-05-13 | 2025-05-21
Electrical Yard | COLO 5 CELL 4 | Electrical | #F3F0A8 | E40 | MV Cable Pulling & Terminating(To Junction Box) | 2025-05-22 | 2025-05-31
Electrical Yard | COLO 5 CELL 3 | Electrical | #F3F0A8 | E40 | MV Cable Pulling & Terminating(To Junction Box) | 2025-06-02 | 2025-06-10
Electrical Yard | COLO 5 CELL 1 | Electrical | #F3F0A8 | E41 | Terminate MV Gear | 2025-05-30 | 2025-06-03
Electrical Yard | COLO 5 CELL 2 | Electrical | #F3F0A8 | E41 | Terminate MV Gear | 2025-06-04 | 2025-06-07
Electrical Yard | COLO 5 CELL 4 | Electrical | #F3F0A8 | E41 | Terminate MV Gear | 2025-06-09 | 2025-06-12
Electrical Yard | COLO 5 CELL 3 | Electrical | #F3F0A8 | E41 | Terminate MV Gear | 2025-06-13 | 2025-06-18
Fitout Admin Area | Beneficial Use Rooms Electrical Rooms | Electrical | #F3F0A8 | EE28 | Cable Tray / Ceiling Steel Height | 2025-02-04 | 2025-02-04
Fitout Admin Area | Remaining Rooms Fire Riser Room | Framing | #5297F8 | X17 | Ceiling Grid & Tile | 2025-02-18 | 2025-02-21
Fitout Admin Area | Remaining Rooms Restrooms & Janitor Room | Framing | #5297F8 | X17 | Ceiling Grid & Tile | 2025-02-18 | 2025-02-21
Fitout Admin Area | Remaining Rooms Fire Riser Room | Fire Protection | #C96C74 | R11 | Complete Pipe/ Valves | 2025-02-22 | 2025-02-24
Fitout Admin Area | Beneficial Use Rooms SER (Security Equip Room) | Drywall | #CFACFF | D5 | Finish Drywall | 2025-02-06 | 2025-02-07
Fitout Admin Area | Beneficial Use Rooms Storage (High Value & Secure) Rooms | Drywall | #CFACFF | D5 | Finish Drywall | 2025-02-26 | 2025-03-03
Fitout Admin Area | Remaining Rooms Fire Riser Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-02-12 | 2025-02-13
Fitout Admin Area | Remaining Rooms Restrooms & Janitor Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-02-13 | 2025-02-14
Fitout Admin Area | Remaining Rooms Loading Dock | Drywall | #CFACFF | D5 | Finish Drywall | 2025-02-15 | 2025-02-17
Fitout Admin Area | Beneficial Use Rooms Electrical Rooms | Drywall | #CFACFF | D6 | Finish Drywall and Wall Protection | 2025-01-28 | 2025-01-31
Fitout Admin Area | Beneficial Use Rooms Entry Room1 | Drywall | #CFACFF | D6 | Finish Drywall and Wall Protection | 2025-01-30 | 2025-02-03
Fitout Admin Area | Beneficial Use Rooms Entry Room2 | Drywall | #CFACFF | D6 | Finish Drywall and Wall Protection | 2025-02-01 | 2025-02-05
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Drywall | #CFACFF | D6 | Finish Drywall and Wall Protection | 2025-02-04 | 2025-02-07
Fitout Admin Area | Beneficial Use Rooms Electrical Rooms | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-01-20 | 2025-01-20
Fitout Admin Area | Beneficial Use Rooms Entry Room1 | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-01-21 | 2025-01-21
Fitout Admin Area | Beneficial Use Rooms Entry Room2 | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-01-22 | 2025-01-22
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-01-23 | 2025-01-23
Fitout Admin Area | Beneficial Use Rooms SER (Security Equip Room) | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-01-24 | 2025-01-24
Fitout Admin Area | Beneficial Use Rooms Storage (High Value & Secure) Rooms | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-01-25 | 2025-01-25
Fitout Admin Area | Remaining Rooms Fire Riser Room | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-01-27 | 2025-01-27
Fitout Admin Area | Remaining Rooms Restrooms & Janitor Room | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-01-28 | 2025-01-28
Fitout Admin Area | Remaining Rooms Loading Dock | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-01-29 | 2025-01-29
Fitout Admin Area | Beneficial Use Rooms Storage (High Value & Secure) Rooms | CLAYCO | #C00000 | C1 | Fit-out | 2025-03-06 | 2025-03-17
Fitout Admin Area | Beneficial Use Rooms Electrical Rooms | Framing | #5297F8 | X21 | Framing | 2025-01-21 | 2025-01-21
Fitout Admin Area | Beneficial Use Rooms Entry Room1 | Framing | #5297F8 | X21 | Framing | 2025-01-22 | 2025-01-22
Fitout Admin Area | Beneficial Use Rooms Entry Room2 | Framing | #5297F8 | X21 | Framing | 2025-01-23 | 2025-01-23
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Framing | #5297F8 | X21 | Framing | 2025-01-24 | 2025-01-24
Fitout Admin Area | Beneficial Use Rooms SER (Security Equip Room) | Framing | #5297F8 | X21 | Framing | 2025-01-25 | 2025-01-25
Fitout Admin Area | Beneficial Use Rooms Storage (High Value & Secure) Rooms | Framing | #5297F8 | X21 | Framing | 2025-01-27 | 2025-01-27
Fitout Admin Area | Remaining Rooms Fire Riser Room | Framing | #5297F8 | X21 | Framing | 2025-01-28 | 2025-01-28
Fitout Admin Area | Remaining Rooms Restrooms & Janitor Room | Framing | #5297F8 | X21 | Framing | 2025-01-29 | 2025-01-29
Fitout Admin Area | Remaining Rooms Loading Dock | Framing | #5297F8 | X21 | Framing | 2025-01-30 | 2025-01-30
Fitout Admin Area | Remaining Rooms Admin Gen Finishes & Punch | Framing | #5297F8 | X34 | Install Doors | 2025-02-22 | 2025-02-26
Fitout Admin Area | Remaining Rooms Fire Riser Room | Framing | #5297F8 | X35 | Install downcomers | 2025-01-31 | 2025-01-31
Fitout Admin Area | Remaining Rooms Fire Riser Room | Mech | #D3E660 | M1 | Install Duct Work | 2025-01-29 | 2025-01-30
Fitout Admin Area | Remaining Rooms Loading Dock | Mech | #D3E660 | M1 | Install Ductwork | 2025-01-29 | 2025-02-15
Fitout Admin Area | Remaining Rooms Loading Dock | Mech | #D3E660 | M2 | Install Ductwork (Remaining Rooms, Corridor) | 2025-01-30 | 2025-02-17
Fitout Admin Area | Beneficial Use Rooms Storage (High Value & Secure) Rooms | Mech | #D3E660 | M3 | Install Ductwork and Cracs | 2025-02-07 | 2025-02-25
Fitout Admin Area | Beneficial Use Rooms Entry Room1 | Electrical | #F3F0A8 | EE45 | Install Raceway | 2025-02-06 | 2025-02-10
Fitout Admin Area | Beneficial Use Rooms Entry Room2 | Electrical | #F3F0A8 | EE45 | Install Raceway | 2025-02-10 | 2025-02-12
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Electrical | #F3F0A8 | EE45 | Install Raceway | 2025-02-12 | 2025-02-14
Fitout Admin Area | Beneficial Use Rooms SER (Security Equip Room) | Electrical | #F3F0A8 | EE45 | Install Raceway | 2025-02-12 | 2025-02-14
Fitout Admin Area | Remaining Rooms Admin Gen Finishes & Punch | Electrical | #F3F0A8 | EEA | Light Fixtures Installation | 2025-02-27 | 2025-03-11
Fitout Admin Area | Beneficial Use Rooms Electrical Rooms | MEP | #FF7BFF | MEP1 | MEP Rough-In & OH | 2025-01-22 | 2025-01-23
Fitout Admin Area | Beneficial Use Rooms Entry Room1 | MEP | #FF7BFF | MEP1 | MEP Rough-In & OH | 2025-01-24 | 2025-01-25
Fitout Admin Area | Beneficial Use Rooms Entry Room2 | MEP | #FF7BFF | MEP1 | MEP Rough-In & OH | 2025-01-27 | 2025-01-28
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | MEP | #FF7BFF | MEP1 | MEP Rough-In & OH | 2025-01-29 | 2025-01-30
Fitout Admin Area | Beneficial Use Rooms SER (Security Equip Room) | MEP | #FF7BFF | MEP1 | MEP Rough-In & OH | 2025-01-31 | 2025-02-01
Fitout Admin Area | Beneficial Use Rooms Storage (High Value & Secure) Rooms | MEP | #FF7BFF | MEP1 | MEP Rough-In & OH | 2025-02-03 | 2025-02-04
Fitout Admin Area | Remaining Rooms Fire Riser Room | MEP | #FF7BFF | MEP1 | MEP Rough-In & OH | 2025-02-05 | 2025-02-06
Fitout Admin Area | Remaining Rooms Restrooms & Janitor Room | MEP | #FF7BFF | MEP1 | MEP Rough-In & OH | 2025-02-07 | 2025-02-10
Fitout Admin Area | Remaining Rooms Loading Dock | MEP | #FF7BFF | MEP1 | MEP Rough-In & OH | 2025-02-11 | 2025-02-12
Fitout Admin Area | Beneficial Use Rooms Electrical Rooms | Painting | #DBF1FE | Y1 | Paint | 2025-02-01 | 2025-02-03
Fitout Admin Area | Beneficial Use Rooms Entry Room1 | Painting | #DBF1FE | Y1 | Paint | 2025-02-04 | 2025-02-05
Fitout Admin Area | Beneficial Use Rooms Entry Room2 | Painting | #DBF1FE | Y1 | Paint | 2025-02-06 | 2025-02-07
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Painting | #DBF1FE | Y1 | Paint | 2025-02-10 | 2025-02-11
Fitout Admin Area | Beneficial Use Rooms SER (Security Equip Room) | Painting | #DBF1FE | Y1 | Paint | 2025-02-10 | 2025-02-11
Fitout Admin Area | Beneficial Use Rooms Storage (High Value & Secure) Rooms | Painting | #DBF1FE | Y1 | Paint | 2025-03-04 | 2025-03-05
Fitout Admin Area | Remaining Rooms Fire Riser Room | Painting | #DBF1FE | Y1 | Paint | 2025-02-14 | 2025-02-15
Fitout Admin Area | Remaining Rooms Restrooms & Janitor Room | Painting | #DBF1FE | Y1 | Paint | 2025-02-15 | 2025-02-17
Fitout Admin Area | Remaining Rooms Loading Dock | Painting | #DBF1FE | Y1 | Paint | 2025-02-18 | 2025-02-19
Fitout Admin Area | Remaining Rooms Loading Dock | Plumbing | #30585A | P5 | Plumbing | 2025-02-20 | 2025-03-10
Fitout Admin Area | Beneficial Use Rooms Electrical Rooms | Electrical | #F3F0A8 | EE46 | Pull Branches | 2025-03-29 | 2025-04-11
Fitout Admin Area | Remaining Rooms Loading Dock | Electrical | #F3F0A8 | EE29 | Pull Cables | 2025-03-11 | 2025-03-13
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Telecom | #E3A267 | T3 | Pull Copper for BAS VLAN | 2025-03-21 | 2025-04-04
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Telecom | #E3A267 | T4 | Pull Copper for EPMS VLAN | 2025-02-20 | 2025-03-06
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Telecom | #E3A267 | T5 | Pull Copper for Tahuya VLAN | 2025-03-07 | 2025-03-20
Fitout Admin Area | Beneficial Use Rooms Electrical Rooms | Electrical | #F3F0A8 | EE49 | Pull Feeders | 2025-03-12 | 2025-03-28
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Telecom | #E3A267 | T6 | Pull Fiber For BAS VLAN | 2025-03-21 | 2025-04-04
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Telecom | #E3A267 | T7 | Pull Fiber For CEI Network | 2025-04-21 | 2025-05-05
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Telecom | #E3A267 | T8 | Pull Fiber For EPMS VLAN | 2025-02-20 | 2025-03-06
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Telecom | #E3A267 | T9 | Pull Fiber For Tahuya VLAN | 2025-03-07 | 2025-03-20
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Telecom | #E3A267 | T10 | Pull Fiber/Copper For CORPNET Network | 2025-04-05 | 2025-04-19
Fitout Admin Area | Beneficial Use Rooms Punchlist | CLAYCO | #C00000 | CP | PunchList | 2025-05-06 | 2025-05-09
Fitout Admin Area | Remaining Rooms Admin Gen Finishes & Punch | CLAYCO | #C00000 | CPP | Remaining Area Punchlist | 2025-03-12 | 2025-03-17
Fitout Admin Area | Remaining Rooms Loading Dock | MEP | #FF7BFF | MEP2 | Rough-in | 2025-01-31 | 2025-01-31
Fitout Admin Area | Beneficial Use Rooms Electrical Rooms | Framing | #5297F8 | X16 | Secondary / Ceiling Steel | 2025-01-27 | 2025-01-27
Fitout Admin Area | Beneficial Use Rooms Entry Room1 | Framing | #5297F8 | X16 | Secondary / Ceiling Steel | 2025-01-29 | 2025-01-29
Fitout Admin Area | Beneficial Use Rooms Entry Room2 | Framing | #5297F8 | X16 | Secondary / Ceiling Steel | 2025-01-31 | 2025-01-31
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Framing | #5297F8 | X16 | Secondary / Ceiling Steel | 2025-02-03 | 2025-02-03
Fitout Admin Area | Beneficial Use Rooms SER (Security Equip Room) | Framing | #5297F8 | X16 | Secondary / Ceiling Steel | 2025-02-05 | 2025-02-05
Fitout Admin Area | Remaining Rooms Fire Riser Room | Framing | #5297F8 | X16 | Secondary / Ceiling Steel | 2025-02-11 | 2025-02-11
Fitout Admin Area | Beneficial Use Rooms Electrical Rooms | Electrical | #F3F0A8 | EE51 | Set Electrical Equipment | 2025-03-03 | 2025-03-11
Fitout Admin Area | Beneficial Use Rooms Entry Room1 | Electrical | #F3F0A8 | EE52 | Set ER-1 Equipment | 2025-02-11 | 2025-02-14
Fitout Admin Area | Beneficial Use Rooms Entry Room2 | Electrical | #F3F0A8 | EE53 | Set ER-2 Equipment | 2025-02-13 | 2025-02-17
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Electrical | #F3F0A8 | EE54 | Set FCR Equipment | 2025-02-15 | 2025-02-19
Fitout Admin Area | Beneficial Use Rooms SER (Security Equip Room) | Electrical | #F3F0A8 | EE55 | Set SER Room Equipment | 2025-02-15 | 2025-02-19
Fitout Admin Area | Beneficial Use Rooms Electrical Rooms | Electrical | #F3F0A8 | EE56 | Terminate Electrical / Mechanical Equipment | 2025-04-14 | 2025-04-17
Fitout Admin Area | Beneficial Use Rooms Electrical Rooms | Drywall | #CFACFF | D4 | Top Out Drywall - Ceiling Steel Height | 2025-01-24 | 2025-01-25
Fitout Admin Area | Beneficial Use Rooms Entry Room1 | Drywall | #CFACFF | D4 | Top Out Drywall - Ceiling Steel Height | 2025-01-27 | 2025-01-28
Fitout Admin Area | Beneficial Use Rooms Entry Room2 | Drywall | #CFACFF | D4 | Top Out Drywall - Ceiling Steel Height | 2025-01-29 | 2025-01-30
Fitout Admin Area | Beneficial Use Rooms FCR (Facilities Control Room) | Drywall | #CFACFF | D4 | Top Out Drywall - Ceiling Steel Height | 2025-01-31 | 2025-02-01
Fitout Admin Area | Beneficial Use Rooms SER (Security Equip Room) | Drywall | #CFACFF | D4 | Top Out Drywall - Ceiling Steel Height | 2025-02-03 | 2025-02-04
Fitout Admin Area | Beneficial Use Rooms Storage (High Value & Secure) Rooms | Drywall | #CFACFF | D4 | Top Out Drywall - Ceiling Steel Height | 2025-02-05 | 2025-02-06
Fitout Admin Area | Remaining Rooms Fire Riser Room | Drywall | #CFACFF | D4 | Top Out Drywall - Ceiling Steel Height | 2025-02-07 | 2025-02-10
Fitout Admin Area | Remaining Rooms Restrooms & Janitor Room | Drywall | #CFACFF | D4 | Top Out Drywall - Ceiling Steel Height | 2025-02-11 | 2025-02-12
Fitout Admin Area | Remaining Rooms Loading Dock | Drywall | #CFACFF | D4 | Top Out Drywall - Ceiling Steel Height | 2025-02-13 | 2025-02-14
Fitout COLO3 | C3 CELL 1 Data Hall | HACs | #F8D9E7 | S1 | Assemble HACs [Qty - 5] | 2025-02-22 | 2025-02-27
Fitout COLO3 | C3 CELL 2 Data Hall | HACs | #F8D9E7 | S1 | Assemble HACs [Qty - 5] | 2025-03-04 | 2025-03-08
Fitout COLO3 | C3 CELL 3 Data Hall | HACs | #F8D9E7 | S1 | Assemble HACs [Qty - 5] | 2025-03-27 | 2025-04-01
Fitout COLO3 | C3 CELL 4 Data Hall | HACs | #F8D9E7 | S1 | Assemble HACs [Qty - 5] | 2025-03-14 | 2025-03-19
Fitout COLO3 | C3 CELL 1 Data Hall | Electrical | #F3F0A8 | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-03-11 | 2025-03-13
Fitout COLO3 | C3 CELL 2 Data Hall | Electrical | #F3F0A8 | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-03-19 | 2025-03-21
Fitout COLO3 | C3 CELL 3 Data Hall | Electrical | #F3F0A8 | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-04-11 | 2025-04-15
Fitout COLO3 | C3 CELL 4 Data Hall | Electrical | #F3F0A8 | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-03-31 | 2025-04-02
Fitout COLO3 | C3 CELL 1 Data Hall | HACs | #F8D9E7 | S4 | Detail HACs | 2025-03-11 | 2025-03-14
Fitout COLO3 | C3 CELL 2 Data Hall | HACs | #F8D9E7 | S4 | Detail HACs | 2025-03-19 | 2025-03-24
Fitout COLO3 | C3 CELL 3 Data Hall | HACs | #F8D9E7 | S4 | Detail HACs | 2025-04-11 | 2025-04-16
Fitout COLO3 | C3 CELL 4 Data Hall | HACs | #F8D9E7 | S4 | Detail HACs | 2025-03-31 | 2025-04-03
Fitout COLO3 | C3 CELL 4 Data Hall | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-02-24 | 2025-02-25
Fitout COLO3 | C3 CELL 1 Data Hall | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-02-06 | 2025-02-07
Fitout COLO3 | C3 CELL 1 Electrical Room | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-02-15 | 2025-02-15
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-03-06 | 2025-03-06
Fitout COLO3 | C3 CELL 2 Data Hall | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-02-13 | 2025-02-14
Fitout COLO3 | C3 CELL 2 Electrical Room | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-02-13 | 2025-02-13
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-03-04 | 2025-03-04
Fitout COLO3 | C3 CELL 3 Data Hall | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-03-08 | 2025-03-10
Fitout COLO3 | C3 CELL 3 Electrical Room | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-03-08 | 2025-03-08
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-03-27 | 2025-03-27
Fitout COLO3 | C3 CELL 4 Electrical Room | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-02-24 | 2025-02-24
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-03-14 | 2025-03-14
Fitout COLO3 | C3 CELL 1 Data Hall | Drywall | #CFACFF | D5 | Finish Drywall | 2025-02-01 | 2025-02-04
Fitout COLO3 | C3 CELL 1 Electrical Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-02-22 | 2025-03-04
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Drywall | #CFACFF | D5 | Finish Drywall | 2025-03-06 | 2025-03-07
Fitout COLO3 | C3 CELL 2 Data Hall | Drywall | #CFACFF | D5 | Finish Drywall | 2025-02-11 | 2025-02-13
Fitout COLO3 | C3 CELL 2 Electrical Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-02-13 | 2025-02-14
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Drywall | #CFACFF | D5 | Finish Drywall | 2025-03-04 | 2025-03-05
Fitout COLO3 | C3 CELL 3 Data Hall | Drywall | #CFACFF | D5 | Finish Drywall | 2025-03-06 | 2025-03-08
Fitout COLO3 | C3 CELL 3 Electrical Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-03-08 | 2025-03-10
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Drywall | #CFACFF | D5 | Finish Drywall | 2025-03-27 | 2025-03-28
Fitout COLO3 | C3 CELL 4 Data Hall | Drywall | #CFACFF | D5 | Finish Drywall | 2025-02-21 | 2025-02-24
Fitout COLO3 | C3 CELL 4 Electrical Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-02-24 | 2025-02-25
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Drywall | #CFACFF | D5 | Finish Drywall | 2025-03-14 | 2025-03-15
Fitout COLO3 | C3 CELL 1 Data Hall | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-01-29 | 2025-01-31
Fitout COLO3 | C3 CELL 1 Electrical Room | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-02-11 | 2025-02-12
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-02-13 | 2025-02-14
Fitout COLO3 | C3 CELL 2 Data Hall | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-02-06 | 2025-02-10
Fitout COLO3 | C3 CELL 2 Electrical Room | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-02-07 | 2025-02-10
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-02-11 | 2025-02-12
Fitout COLO3 | C3 CELL 3 Data Hall | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-03-03 | 2025-03-05
Fitout COLO3 | C3 CELL 3 Electrical Room | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-03-04 | 2025-03-05
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-03-06 | 2025-03-07
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | CLAYCO | #C00000 | CC | General Cleaning | 2025-03-08 | 2025-03-11
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | CLAYCO | #C00000 | CC | General Cleaning | 2025-04-01 | 2025-04-03
Fitout COLO3 | C3 CELL 1 Data Hall | CLAYCO | #C00000 | CC | General Cleaning | 2025-02-18 | 2025-02-18
Fitout COLO3 | C3 CELL 1 Electrical Room | CLAYCO | #C00000 | CC | General Cleaning | 2025-03-07 | 2025-03-07
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | CLAYCO | #C00000 | CC | General Cleaning | 2025-03-11 | 2025-03-13
Fitout COLO3 | C3 CELL 2 Data Hall | CLAYCO | #C00000 | CC | General Cleaning | 2025-02-26 | 2025-02-26
Fitout COLO3 | C3 CELL 2 Electrical Room | CLAYCO | #C00000 | CC | General Cleaning | 2025-02-18 | 2025-02-18
Fitout COLO3 | C3 CELL 3 Data Hall | CLAYCO | #C00000 | CC | General Cleaning | 2025-03-21 | 2025-03-21
Fitout COLO3 | C3 CELL 3 Electrical Room | CLAYCO | #C00000 | CC | General Cleaning | 2025-03-13 | 2025-03-13
Fitout COLO3 | C3 CELL 4 Data Hall | CLAYCO | #C00000 | CC | General Cleaning | 2025-03-10 | 2025-03-10
Fitout COLO3 | C3 CELL 4 Electrical Room | CLAYCO | #C00000 | CC | General Cleaning | 2025-02-28 | 2025-02-28
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | CLAYCO | #C00000 | CC | General Cleaning | 2025-03-19 | 2025-03-21
Fitout COLO3 | C3 CELL 1 Data Hall | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-01-25 | 2025-01-28
Fitout COLO3 | C3 CELL 1 Electrical Room | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-01-31 | 2025-02-10
Fitout COLO3 | C3 CELL 2 Data Hall | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-02-03 | 2025-02-05
Fitout COLO3 | C3 CELL 2 Electrical Room | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-02-05 | 2025-02-06
Fitout COLO3 | C3 CELL 3 Data Hall | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-02-26 | 2025-02-28
Fitout COLO3 | C3 CELL 3 Electrical Room | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-02-28 | 2025-03-03
Fitout COLO3 | C3 CELL 4 Data Hall | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-02-14 | 2025-02-17
Fitout COLO3 | C3 CELL 4 Electrical Room | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-02-17 | 2025-02-18
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | BAS | #303450 | BA | Install BAS Equipments | 2025-03-12 | 2025-03-24
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | BAS | #303450 | BA | Install BAS Equipments | 2025-03-10 | 2025-03-20
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | BAS | #303450 | BA | Install BAS Equipments | 2025-04-02 | 2025-04-14
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | BAS | #303450 | BA | Install BAS Equipments | 2025-03-20 | 2025-04-01
Fitout COLO3 | C3 CELL 1 Data Hall | Electrical | #F3F0A8 | EE39 | Install Busways on HAC Arms | 2025-02-25 | 2025-03-03
Fitout COLO3 | C3 CELL 2 Data Hall | Electrical | #F3F0A8 | EE39 | Install Busways on HAC Arms | 2025-03-06 | 2025-03-11
Fitout COLO3 | C3 CELL 3 Data Hall | Electrical | #F3F0A8 | EE39 | Install Busways on HAC Arms | 2025-03-29 | 2025-04-03
Fitout COLO3 | C3 CELL 4 Data Hall | Electrical | #F3F0A8 | EE39 | Install Busways on HAC Arms | 2025-03-17 | 2025-03-21
Fitout COLO3 | C3 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-02-17 | 2025-02-18
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-03-12 | 2025-03-13
Fitout COLO3 | C3 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-02-14 | 2025-02-15
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-03-10 | 2025-03-11
Fitout COLO3 | C3 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-03-10 | 2025-03-11
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-04-02 | 2025-04-03
Fitout COLO3 | C3 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-02-25 | 2025-02-26
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-03-20 | 2025-03-21
Fitout COLO3 | C3 CELL 1 Data Hall | Framing | #5297F8 | X26 | Install Ceiling Grid | 2025-02-18 | 2025-02-21
Fitout COLO3 | C3 CELL 2 Data Hall | Framing | #5297F8 | X26 | Install Ceiling Grid | 2025-02-26 | 2025-03-03
Fitout COLO3 | C3 CELL 3 Data Hall | Framing | #5297F8 | X26 | Install Ceiling Grid | 2025-03-21 | 2025-03-26
Fitout COLO3 | C3 CELL 4 Data Hall | Framing | #5297F8 | X26 | Install Ceiling Grid | 2025-03-10 | 2025-03-13
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Framing | #5297F8 | X27 | Install Ceiling Grid + Device Tiles | 2025-03-07 | 2025-03-11
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Framing | #5297F8 | X27 | Install Ceiling Grid + Device Tiles | 2025-03-05 | 2025-03-08
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Framing | #5297F8 | X27 | Install Ceiling Grid + Device Tiles | 2025-03-28 | 2025-04-01
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Framing | #5297F8 | X27 | Install Ceiling Grid + Device Tiles | 2025-03-15 | 2025-03-19
Fitout COLO3 | C3 CELL 1 Data Hall | Electrical | #F3F0A8 | EE43 | Install Conduits PDU to Cable Trays | 2025-03-14 | 2025-03-17
Fitout COLO3 | C3 CELL 2 Data Hall | Electrical | #F3F0A8 | EE43 | Install Conduits PDU to Cable Trays | 2025-03-24 | 2025-03-26
Fitout COLO3 | C3 CELL 3 Data Hall | Electrical | #F3F0A8 | EE43 | Install Conduits PDU to Cable Trays | 2025-04-16 | 2025-04-18
Fitout COLO3 | C3 CELL 4 Data Hall | Electrical | #F3F0A8 | EE43 | Install Conduits PDU to Cable Trays | 2025-04-03 | 2025-04-05
Fitout COLO3 | C3 CELL 1 Data Hall | Framing | #5297F8 | X35 | Install Device Tiles | 2025-02-27 | 2025-02-28
Fitout COLO3 | C3 CELL 2 Data Hall | Framing | #5297F8 | X35 | Install Device Tiles | 2025-03-08 | 2025-03-10
Fitout COLO3 | C3 CELL 3 Data Hall | Framing | #5297F8 | X35 | Install Device Tiles | 2025-04-01 | 2025-04-02
Fitout COLO3 | C3 CELL 4 Data Hall | Framing | #5297F8 | X35 | Install Device Tiles | 2025-03-19 | 2025-03-20
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Drywall | #CFACFF | D2 | Install Drywall | 2025-03-04 | 2025-03-05
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Drywall | #CFACFF | D2 | Install Drywall | 2025-02-28 | 2025-03-03
Fitout COLO3 | C3 CELL 1 Data Hall | Drywall | #CFACFF | D2 | Install Drywall | 2025-01-29 | 2025-01-31
Fitout COLO3 | C3 CELL 2 Data Hall | Drywall | #CFACFF | D2 | Install Drywall | 2025-02-06 | 2025-02-10
Fitout COLO3 | C3 CELL 3 Data Hall | Drywall | #CFACFF | D2 | Install Drywall | 2025-03-03 | 2025-03-05
Fitout COLO3 | C3 CELL 4 Data Hall | Drywall | #CFACFF | D2 | Install Drywall | 2025-02-18 | 2025-02-20
Fitout COLO3 | C3 CELL 1 Electrical Room | Drywall | #CFACFF | D2 | Install Drywall | 2025-02-11 | 2025-02-21
Fitout COLO3 | C3 CELL 2 Electrical Room | Drywall | #CFACFF | D2 | Install Drywall | 2025-02-07 | 2025-02-12
Fitout COLO3 | C3 CELL 3 Electrical Room | Drywall | #CFACFF | D2 | Install Drywall | 2025-03-04 | 2025-03-07
Fitout COLO3 | C3 CELL 4 Electrical Room | Drywall | #CFACFF | D2 | Install Drywall | 2025-02-19 | 2025-02-22
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Drywall | #CFACFF | D2 | Install Drywall | 2025-03-25 | 2025-03-26
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Drywall | #CFACFF | D2 | Install Drywall | 2025-03-12 | 2025-03-13
Fitout COLO3 | C3 CELL 1 Data Hall | Electrical | #F3F0A8 | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-02-27 | 2025-03-05
Fitout COLO3 | C3 CELL 2 Data Hall | Electrical | #F3F0A8 | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-03-08 | 2025-03-13
Fitout COLO3 | C3 CELL 3 Data Hall | Electrical | #F3F0A8 | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-01 | 2025-04-05
Fitout COLO3 | C3 CELL 4 Data Hall | Electrical | #F3F0A8 | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-03-19 | 2025-03-25
Fitout COLO3 | C3 CELL 1 Data Hall | Framing | #5297F8 | X21 | Framing | 2025-01-20 | 2025-01-24
Fitout COLO3 | C3 CELL 1 Electrical Room | Framing | #5297F8 | X21 | Framing | 2025-01-25 | 2025-01-30
Fitout COLO3 | C3 CELL 2 Data Hall | Framing | #5297F8 | X21 | Framing | 2025-01-30 | 2025-02-01
Fitout COLO3 | C3 CELL 2 Electrical Room | Framing | #5297F8 | X21 | Framing | 2025-02-03 | 2025-02-04
Fitout COLO3 | C3 CELL 3 Data Hall | Framing | #5297F8 | X21 | Framing | 2025-02-22 | 2025-02-25
Fitout COLO3 | C3 CELL 3 Electrical Room | Framing | #5297F8 | X21 | Framing | 2025-02-26 | 2025-02-27
Fitout COLO3 | C3 CELL 4 Data Hall | Framing | #5297F8 | X21 | Framing | 2025-02-11 | 2025-02-13
Fitout COLO3 | C3 CELL 4 Electrical Room | Framing | #5297F8 | X21 | Framing | 2025-02-14 | 2025-02-15
Fitout COLO3 | C3 CELL 1 Data Hall | Electrical | #F3F0A8 | EE44 | Install Perimeter Cable Trays | 2025-02-22 | 2025-02-26
Fitout COLO3 | C3 CELL 2 Data Hall | Electrical | #F3F0A8 | EE44 | Install Perimeter Cable Trays | 2025-03-04 | 2025-03-07
Fitout COLO3 | C3 CELL 3 Data Hall | Electrical | #F3F0A8 | EE44 | Install Perimeter Cable Trays | 2025-03-27 | 2025-03-31
Fitout COLO3 | C3 CELL 4 Data Hall | Electrical | #F3F0A8 | EE44 | Install Perimeter Cable Trays | 2025-03-14 | 2025-03-18
Fitout COLO3 | C3 CELL 1 Data Hall | Framing | #5297F8 | X19 | Install Screen Mesh + Caulking | 2025-02-10 | 2025-02-12
Fitout COLO3 | C3 CELL 2 Data Hall | Framing | #5297F8 | X19 | Install Screen Mesh + Caulking | 2025-02-18 | 2025-02-20
Fitout COLO3 | C3 CELL 3 Data Hall | Framing | #5297F8 | X19 | Install Screen Mesh + Caulking | 2025-03-13 | 2025-03-15
Fitout COLO3 | C3 CELL 4 Data Hall | Framing | #5297F8 | X19 | Install Screen Mesh + Caulking | 2025-02-28 | 2025-03-04
Fitout COLO3 | C3 CELL 1 Data Hall | Framing | #5297F8 | X38 | Install Secondary Steel | 2025-02-13 | 2025-02-14
Fitout COLO3 | C3 CELL 2 Data Hall | Framing | #5297F8 | X38 | Install Secondary Steel | 2025-02-21 | 2025-02-22
Fitout COLO3 | C3 CELL 3 Data Hall | Framing | #5297F8 | X38 | Install Secondary Steel | 2025-03-17 | 2025-03-18
Fitout COLO3 | C3 CELL 4 Data Hall | Framing | #5297F8 | X38 | Install Secondary Steel | 2025-03-05 | 2025-03-06
Fitout COLO3 | C3 CELL 1 Data Hall | Framing | #5297F8 | X9 | Layout Framing | 2025-01-17 | 2025-01-17
Fitout COLO3 | C3 CELL 2 Data Hall | Framing | #5297F8 | X9 | Layout Framing | 2025-01-29 | 2025-01-29
Fitout COLO3 | C3 CELL 3 Data Hall | Framing | #5297F8 | X9 | Layout Framing | 2025-02-21 | 2025-02-21
Fitout COLO3 | C3 CELL 4 Data Hall | Framing | #5297F8 | X9 | Layout Framing | 2025-02-10 | 2025-02-10
Fitout COLO3 | C3 CELL 4 Data Hall | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-02-21 | 2025-02-25
Fitout COLO3 | C3 CELL 1 Data Hall | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-02-01 | 2025-02-05
Fitout COLO3 | C3 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-02-13 | 2025-02-15
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-02-15 | 2025-02-18
Fitout COLO3 | C3 CELL 2 Data Hall | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-02-11 | 2025-02-14
Fitout COLO3 | C3 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-02-11 | 2025-02-13
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-02-13 | 2025-02-15
Fitout COLO3 | C3 CELL 3 Data Hall | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-03-06 | 2025-03-10
Fitout COLO3 | C3 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-03-06 | 2025-03-08
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-03-08 | 2025-03-11
Fitout COLO3 | C3 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-02-21 | 2025-02-24
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-02-24 | 2025-02-26
Fitout COLO3 | C3 CELL 1 Data Hall | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-02-01 | 2025-02-04
Fitout COLO3 | C3 CELL 1 Electrical Room | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-02-13 | 2025-02-14
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-02-15 | 2025-02-17
Fitout COLO3 | C3 CELL 2 Data Hall | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-02-11 | 2025-02-13
Fitout COLO3 | C3 CELL 2 Electrical Room | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-02-11 | 2025-02-12
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-02-13 | 2025-02-14
Fitout COLO3 | C3 CELL 3 Data Hall | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-03-06 | 2025-03-08
Fitout COLO3 | C3 CELL 3 Electrical Room | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-03-06 | 2025-03-07
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-03-08 | 2025-03-10
Fitout COLO3 | C3 CELL 4 Data Hall | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-02-21 | 2025-02-24
Fitout COLO3 | C3 CELL 4 Electrical Room | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-02-21 | 2025-02-22
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-02-24 | 2025-02-25
Fitout COLO3 | C3 CELL 4 Data Hall | Fire Protection | #C96C74 | R4 | Fire Protection OH R/I | 2025-02-18 | 2025-02-20
Fitout COLO3 | C3 CELL 4 Electrical Room | Fire Protection | #C96C74 | R5 | Fire Protection OH R/I | 2025-02-19 | 2025-02-20
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Fire Protection | #C96C74 | R6 | Fire Protection OH R/I | 2025-02-21 | 2025-02-22
Fitout COLO3 | C3 CELL 2 Data Hall | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-02-13 | 2025-02-14
Fitout COLO3 | C3 CELL 1 Data Hall | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-02-04 | 2025-02-05
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-02-19 | 2025-02-25
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-02-17 | 2025-02-22
Fitout COLO3 | C3 CELL 3 Data Hall | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-03-08 | 2025-03-10
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-03-12 | 2025-03-18
Fitout COLO3 | C3 CELL 4 Data Hall | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-02-24 | 2025-02-25
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-02-27 | 2025-03-06
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Plumbing | #30585A | P4 | Overhead R/I - Plumbing | 2025-02-26 | 2025-03-05
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Plumbing | #30585A | P4 | Overhead R/I - Plumbing | 2025-02-24 | 2025-03-03
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Plumbing | #30585A | P4 | Overhead R/I - Plumbing | 2025-03-19 | 2025-03-26
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Plumbing | #30585A | P4 | Overhead R/I - Plumbing | 2025-03-07 | 2025-03-13
Fitout COLO3 | C3 CELL 1 Data Hall | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-02-05 | 2025-02-07
Fitout COLO3 | C3 CELL 1 Electrical Room | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-03-05 | 2025-03-06
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-03-08 | 2025-03-10
Fitout COLO3 | C3 CELL 2 Data Hall | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-02-14 | 2025-02-17
Fitout COLO3 | C3 CELL 2 Electrical Room | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-02-15 | 2025-02-17
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-03-06 | 2025-03-07
Fitout COLO3 | C3 CELL 3 Data Hall | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-03-10 | 2025-03-12
Fitout COLO3 | C3 CELL 3 Electrical Room | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-03-11 | 2025-03-12
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-03-29 | 2025-03-31
Fitout COLO3 | C3 CELL 4 Data Hall | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-02-25 | 2025-02-27
Fitout COLO3 | C3 CELL 4 Electrical Room | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-02-26 | 2025-02-27
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-03-17 | 2025-03-18
Fitout COLO3 | C3 CELL 1 Data Hall | Painting | #DBF1FE | Y7 | Paint Secondary Steel | 2025-02-15 | 2025-02-17
Fitout COLO3 | C3 CELL 2 Data Hall | Painting | #DBF1FE | Y7 | Paint Secondary Steel | 2025-02-24 | 2025-02-25
Fitout COLO3 | C3 CELL 3 Data Hall | Painting | #DBF1FE | Y7 | Paint Secondary Steel | 2025-03-19 | 2025-03-20
Fitout COLO3 | C3 CELL 4 Data Hall | Painting | #DBF1FE | Y7 | Paint Secondary Steel | 2025-03-07 | 2025-03-08
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | BAS | #303450 | BA1 | Pull & Terminate BAS Equipments | 2025-03-25 | 2025-04-02
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | BAS | #303450 | BA1 | Pull & Terminate BAS Equipments | 2025-03-21 | 2025-03-31
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | BAS | #303450 | BA1 | Pull & Terminate BAS Equipments | 2025-04-15 | 2025-04-23
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | BAS | #303450 | BA1 | Pull & Terminate BAS Equipments | 2025-04-02 | 2025-04-10
Fitout COLO3 | C3 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE47 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-03-17 | 2025-03-29
Fitout COLO3 | C3 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE47 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-04-14 | 2025-04-25
Fitout COLO3 | C3 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE47.1 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-05-10 | 2025-05-22
Fitout COLO3 | C3 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE47.1 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-03-07 | 2025-03-19
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Electrical | #F3F0A8 | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-03-19 | 2025-04-02
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Electrical | #F3F0A8 | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-03-17 | 2025-03-31
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Electrical | #F3F0A8 | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-04-09 | 2025-04-23
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Electrical | #F3F0A8 | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-03-28 | 2025-04-10
Fitout COLO3 | C3 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-03-31 | 2025-04-11
Fitout COLO3 | C3 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-04-26 | 2025-05-08
Fitout COLO3 | C3 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-05-23 | 2025-06-04
Fitout COLO3 | C3 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-04-26 | 2025-05-09
Fitout COLO3 | C3 CELL 1 Data Hall | Electrical | #F3F0A8 | EE17 | Pull Feeders from PDUs to Busways | 2025-03-18 | 2025-03-24
Fitout COLO3 | C3 CELL 2 Data Hall | Electrical | #F3F0A8 | EE17 | Pull Feeders from PDUs to Busways | 2025-03-27 | 2025-04-01
Fitout COLO3 | C3 CELL 3 Data Hall | Electrical | #F3F0A8 | EE17 | Pull Feeders from PDUs to Busways | 2025-04-19 | 2025-04-24
Fitout COLO3 | C3 CELL 4 Data Hall | Electrical | #F3F0A8 | EE17 | Pull Feeders from PDUs to Busways | 2025-04-07 | 2025-04-11
Fitout COLO3 | C3 CELL 1 Punchlist | CLAYCO | #C00000 | CP | Punchlist | 2025-04-17 | 2025-04-28
Fitout COLO3 | C3 CELL 2 Punchlist | CLAYCO | #C00000 | CP | Punchlist | 2025-05-13 | 2025-05-23
Fitout COLO3 | C3 CELL 3 Punchlist | CLAYCO | #C00000 | CP | Punchlist | 2025-06-09 | 2025-06-20
Fitout COLO3 | C3 CELL 4 Punchlist | CLAYCO | #C00000 | CP | Punchlist | 2025-05-10 | 2025-05-21
Fitout COLO3 | C3 CELL 1 Data Hall | HACs | #F8D9E7 | S2 | Raise HACs | 2025-03-06 | 2025-03-10
Fitout COLO3 | C3 CELL 2 Data Hall | HACs | #F8D9E7 | S2 | Raise HACs | 2025-03-14 | 2025-03-18
Fitout COLO3 | C3 CELL 3 Data Hall | HACs | #F8D9E7 | S2 | Raise HACs | 2025-04-07 | 2025-04-10
Fitout COLO3 | C3 CELL 4 Data Hall | HACs | #F8D9E7 | S2 | Raise HACs | 2025-03-26 | 2025-03-29
Fitout COLO3 | C3 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE51 | Set Electrical Equipments | 2025-03-10 | 2025-03-15
Fitout COLO3 | C3 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE51 | Set Electrical Equipments | 2025-03-17 | 2025-03-20
Fitout COLO3 | C3 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE51 | Set Electrical Equipments | 2025-03-14 | 2025-03-18
Fitout COLO3 | C3 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE51 | Set Electrical Equipments | 2025-03-03 | 2025-03-06
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Mech | #D3E660 | M6 | Set Mechanical Equipments | 2025-03-14 | 2025-03-18
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Mech | #D3E660 | M6 | Set Mechanical Equipments | 2025-03-12 | 2025-03-15
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Mech | #D3E660 | M6 | Set Mechanical Equipments | 2025-04-04 | 2025-04-08
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Mech | #D3E660 | M6 | Set Mechanical Equipments | 2025-03-24 | 2025-03-27
Fitout COLO3 | C3 CELL 1 Data Hall | Electrical | #F3F0A8 | EE7 | Set PDUs | 2025-02-27 | 2025-03-04
Fitout COLO3 | C3 CELL 2 Data Hall | Electrical | #F3F0A8 | EE7 | Set PDUs | 2025-03-08 | 2025-03-12
Fitout COLO3 | C3 CELL 3 Data Hall | Electrical | #F3F0A8 | EE7 | Set PDUs | 2025-04-01 | 2025-04-04
Fitout COLO3 | C3 CELL 4 Data Hall | Electrical | #F3F0A8 | EE7 | Set PDUs | 2025-03-19 | 2025-03-24
Fitout COLO3 | C3 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-03-31 | 2025-04-03
Fitout COLO3 | C3 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-04-26 | 2025-04-30
Fitout COLO3 | C3 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-05-23 | 2025-05-28
Fitout COLO3 | C3 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-03-20 | 2025-03-25
Fitout COLO3 | C3 CELL 1 Mechanical Gallery | Mech | #D3E660 | M7 | Terminate Mechanical Equipments | 2025-04-03 | 2025-04-07
Fitout COLO3 | C3 CELL 2 Mechanical Gallery | Mech | #D3E660 | M7 | Terminate Mechanical Equipments | 2025-04-01 | 2025-04-04
Fitout COLO3 | C3 CELL 3 Mechanical Gallery | Mech | #D3E660 | M7 | Terminate Mechanical Equipments | 2025-04-24 | 2025-04-28
Fitout COLO3 | C3 CELL 4 Mechanical Gallery | Mech | #D3E660 | M7 | Terminate Mechanical Equipments | 2025-04-11 | 2025-04-16
Fitout COLO3 | C3 CELL 1 Data Hall | Electrical | #F3F0A8 | EE58 | Terminate PDUs | 2025-04-14 | 2025-04-16
Fitout COLO3 | C3 CELL 2 Data Hall | Electrical | #F3F0A8 | EE58 | Terminate PDUs | 2025-05-09 | 2025-05-12
Fitout COLO3 | C3 CELL 3 Data Hall | Electrical | #F3F0A8 | EE58 | Terminate PDUs | 2025-06-05 | 2025-06-07
Fitout COLO3 | C3 CELL 4 Data Hall | Electrical | #F3F0A8 | EE58 | Terminate PDUs | 2025-05-10 | 2025-05-13
Fitout COLO4 | C4 CELL 1 Data Hall | HACs | #F8D9E7 | S1 | Assemble HACs [Qty - 5] | 2025-03-29 | 2025-04-03
Fitout COLO4 | C4 CELL 2 Data Hall | HACs | #F8D9E7 | S1 | Assemble HACs [Qty - 5] | 2025-04-07 | 2025-04-11
Fitout COLO4 | C4 CELL 3 Data Hall | HACs | #F8D9E7 | S1 | Assemble HACs [Qty - 5] | 2025-04-30 | 2025-05-06
Fitout COLO4 | C4 CELL 4 Data Hall | HACs | #F8D9E7 | S1 | Assemble HACs [Qty - 5] | 2025-04-18 | 2025-04-23
Fitout COLO4 | C4 CELL 1 Data Hall | Electrical | #F3F0A8 | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-04-15 | 2025-04-17
Fitout COLO4 | C4 CELL 2 Data Hall | Electrical | #F3F0A8 | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-04-23 | 2025-04-25
Fitout COLO4 | C4 CELL 3 Data Hall | Electrical | #F3F0A8 | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-16 | 2025-05-19
Fitout COLO4 | C4 CELL 4 Data Hall | Electrical | #F3F0A8 | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-05 | 2025-05-07
Fitout COLO4 | C4 CELL 1 Data Hall | HACs | #F8D9E7 | S4 | Detail HACs | 2025-04-15 | 2025-04-18
Fitout COLO4 | C4 CELL 2 Data Hall | HACs | #F8D9E7 | S4 | Detail HACs | 2025-04-23 | 2025-04-26
Fitout COLO4 | C4 CELL 3 Data Hall | HACs | #F8D9E7 | S4 | Detail HACs | 2025-05-16 | 2025-05-20
Fitout COLO4 | C4 CELL 4 Data Hall | HACs | #F8D9E7 | S4 | Detail HACs | 2025-05-05 | 2025-05-08
Fitout COLO4 | C4 CELL 1 Data Hall | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-03-11 | 2025-03-12
Fitout COLO4 | C4 CELL 1 Electrical Room | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-03-11 | 2025-03-11
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-03-29 | 2025-03-29
Fitout COLO4 | C4 CELL 2 Data Hall | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-03-19 | 2025-03-20
Fitout COLO4 | C4 CELL 2 Electrical Room | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-03-19 | 2025-03-19
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-04-07 | 2025-04-07
Fitout COLO4 | C4 CELL 3 Data Hall | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-04-11 | 2025-04-14
Fitout COLO4 | C4 CELL 3 Electrical Room | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-04-11 | 2025-04-11
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-04-30 | 2025-04-30
Fitout COLO4 | C4 CELL 4 Data Hall | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-03-31 | 2025-04-01
Fitout COLO4 | C4 CELL 4 Electrical Room | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-03-31 | 2025-03-31
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-04-18 | 2025-04-18
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Drywall | #CFACFF | D5 | Finish Drywall | 2025-03-29 | 2025-03-31
Fitout COLO4 | C4 CELL 1 Data Hall | Drywall | #CFACFF | D5 | Finish Drywall | 2025-03-08 | 2025-03-11
Fitout COLO4 | C4 CELL 1 Electrical Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-03-11 | 2025-03-12
Fitout COLO4 | C4 CELL 2 Data Hall | Drywall | #CFACFF | D5 | Finish Drywall | 2025-03-17 | 2025-03-19
Fitout COLO4 | C4 CELL 2 Electrical Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-03-19 | 2025-03-20
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Drywall | #CFACFF | D5 | Finish Drywall | 2025-04-07 | 2025-04-08
Fitout COLO4 | C4 CELL 3 Data Hall | Drywall | #CFACFF | D5 | Finish Drywall | 2025-04-09 | 2025-04-11
Fitout COLO4 | C4 CELL 3 Electrical Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-04-11 | 2025-04-14
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Drywall | #CFACFF | D5 | Finish Drywall | 2025-04-30 | 2025-05-01
Fitout COLO4 | C4 CELL 4 Data Hall | Drywall | #CFACFF | D5 | Finish Drywall | 2025-03-28 | 2025-03-31
Fitout COLO4 | C4 CELL 4 Electrical Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-03-31 | 2025-04-01
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Drywall | #CFACFF | D5 | Finish Drywall | 2025-04-18 | 2025-04-19
Fitout COLO4 | C4 CELL 1 Data Hall | CLAYCO | #C00000 | CC | General Cleaning | 2025-03-25 | 2025-03-25
Fitout COLO4 | C4 CELL 1 Electrical Room | CLAYCO | #C00000 | CC | General Cleaning | 2025-03-15 | 2025-03-15
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | CLAYCO | #C00000 | CC | General Cleaning | 2025-04-03 | 2025-04-05
Fitout COLO4 | C4 CELL 2 Data Hall | CLAYCO | #C00000 | CC | General Cleaning | 2025-04-02 | 2025-04-02
Fitout COLO4 | C4 CELL 2 Electrical Room | CLAYCO | #C00000 | CC | General Cleaning | 2025-03-25 | 2025-03-25
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | CLAYCO | #C00000 | CC | General Cleaning | 2025-04-11 | 2025-04-15
Fitout COLO4 | C4 CELL 3 Data Hall | CLAYCO | #C00000 | CC | General Cleaning | 2025-04-25 | 2025-04-25
Fitout COLO4 | C4 CELL 3 Electrical Room | CLAYCO | #C00000 | CC | General Cleaning | 2025-04-17 | 2025-04-17
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | CLAYCO | #C00000 | CC | General Cleaning | 2025-05-06 | 2025-05-08
Fitout COLO4 | C4 CELL 4 Data Hall | CLAYCO | #C00000 | CC | General Cleaning | 2025-04-14 | 2025-04-14
Fitout COLO4 | C4 CELL 4 Electrical Room | CLAYCO | #C00000 | CC | General Cleaning | 2025-04-04 | 2025-04-04
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | CLAYCO | #C00000 | CC | General Cleaning | 2025-04-23 | 2025-04-25
Fitout COLO4 | C4 CELL 1 Data Hall | Framing | #5297F8 | X21 | Framing | 2025-02-25 | 2025-02-27
Fitout COLO4 | C4 CELL 1 Data Hall | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-02-28 | 2025-03-04
Fitout COLO4 | C4 CELL 1 Electrical Room | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-03-04 | 2025-03-05
Fitout COLO4 | C4 CELL 2 Data Hall | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-03-10 | 2025-03-12
Fitout COLO4 | C4 CELL 2 Electrical Room | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-03-12 | 2025-03-13
Fitout COLO4 | C4 CELL 3 Data Hall | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-04-02 | 2025-04-04
Fitout COLO4 | C4 CELL 3 Electrical Room | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-04-04 | 2025-04-05
Fitout COLO4 | C4 CELL 4 Data Hall | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-03-20 | 2025-03-24
Fitout COLO4 | C4 CELL 4 Electrical Room | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-03-24 | 2025-03-25
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | BAS | #303450 | BA | Install BAS Equipments | 2025-04-04 | 2025-04-16
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | BAS | #303450 | BA | Install BAS Equipments | 2025-04-14 | 2025-04-24
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | BAS | #303450 | BA | Install BAS Equipments | 2025-05-07 | 2025-05-17
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | BAS | #303450 | BA | Install BAS Equipments | 2025-04-24 | 2025-05-06
Fitout COLO4 | C4 CELL 1 Data Hall | Electrical | #F3F0A8 | EE39 | Install Busways on HAC Arms | 2025-04-01 | 2025-04-05
Fitout COLO4 | C4 CELL 2 Data Hall | Electrical | #F3F0A8 | EE39 | Install Busways on HAC Arms | 2025-04-09 | 2025-04-15
Fitout COLO4 | C4 CELL 3 Data Hall | Electrical | #F3F0A8 | EE39 | Install Busways on HAC Arms | 2025-05-02 | 2025-05-08
Fitout COLO4 | C4 CELL 4 Data Hall | Electrical | #F3F0A8 | EE39 | Install Busways on HAC Arms | 2025-04-21 | 2025-04-25
Fitout COLO4 | C4 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-03-12 | 2025-03-13
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-04-04 | 2025-04-05
Fitout COLO4 | C4 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-03-20 | 2025-03-21
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-04-14 | 2025-04-15
Fitout COLO4 | C4 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-04-14 | 2025-04-15
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-05-07 | 2025-05-08
Fitout COLO4 | C4 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-04-01 | 2025-04-02
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-04-24 | 2025-04-25
Fitout COLO4 | C4 CELL 1 Data Hall | Framing | #5297F8 | X26 | Install Ceiling Grid | 2025-03-25 | 2025-03-28
Fitout COLO4 | C4 CELL 2 Data Hall | Framing | #5297F8 | X26 | Install Ceiling Grid | 2025-04-02 | 2025-04-05
Fitout COLO4 | C4 CELL 3 Data Hall | Framing | #5297F8 | X26 | Install Ceiling Grid | 2025-04-25 | 2025-04-29
Fitout COLO4 | C4 CELL 4 Data Hall | Framing | #5297F8 | X26 | Install Ceiling Grid | 2025-04-14 | 2025-04-17
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Framing | #5297F8 | X27 | Install Ceiling Grid + Device Tiles | 2025-03-31 | 2025-04-03
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Framing | #5297F8 | X27 | Install Ceiling Grid + Device Tiles | 2025-04-08 | 2025-04-11
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Framing | #5297F8 | X27 | Install Ceiling Grid + Device Tiles | 2025-05-01 | 2025-05-06
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Framing | #5297F8 | X27 | Install Ceiling Grid + Device Tiles | 2025-04-19 | 2025-04-23
Fitout COLO4 | C4 CELL 1 Data Hall | Electrical | #F3F0A8 | EE43 | Install Conduits PDU to Cable Trays | 2025-04-18 | 2025-04-21
Fitout COLO4 | C4 CELL 2 Data Hall | Electrical | #F3F0A8 | EE43 | Install Conduits PDU to Cable Trays | 2025-04-26 | 2025-04-29
Fitout COLO4 | C4 CELL 3 Data Hall | Electrical | #F3F0A8 | EE43 | Install Conduits PDU to Cable Trays | 2025-05-20 | 2025-05-22
Fitout COLO4 | C4 CELL 4 Data Hall | Electrical | #F3F0A8 | EE43 | Install Conduits PDU to Cable Trays | 2025-05-08 | 2025-05-10
Fitout COLO4 | C4 CELL 1 Data Hall | Framing | #5297F8 | X35 | Install Device Tiles | 2025-04-03 | 2025-04-04
Fitout COLO4 | C4 CELL 2 Data Hall | Framing | #5297F8 | X35 | Install Device Tiles | 2025-04-11 | 2025-04-14
Fitout COLO4 | C4 CELL 3 Data Hall | Framing | #5297F8 | X35 | Install Device Tiles | 2025-05-06 | 2025-05-07
Fitout COLO4 | C4 CELL 4 Data Hall | Framing | #5297F8 | X35 | Install Device Tiles | 2025-04-23 | 2025-04-24
Fitout COLO4 | C4 CELL 1 Data Hall | Drywall | #CFACFF | D2 | Install Drywall | 2025-03-05 | 2025-03-07
Fitout COLO4 | C4 CELL 2 Data Hall | Drywall | #CFACFF | D2 | Install Drywall | 2025-03-13 | 2025-03-15
Fitout COLO4 | C4 CELL 3 Data Hall | Drywall | #CFACFF | D2 | Install Drywall | 2025-04-05 | 2025-04-08
Fitout COLO4 | C4 CELL 4 Data Hall | Drywall | #CFACFF | D2 | Install Drywall | 2025-03-25 | 2025-03-27
Fitout COLO4 | C4 CELL 1 Electrical Room | Drywall | #CFACFF | D2 | Install Drywall | 2025-03-06 | 2025-03-10
Fitout COLO4 | C4 CELL 2 Electrical Room | Drywall | #CFACFF | D2 | Install Drywall | 2025-03-14 | 2025-03-18
Fitout COLO4 | C4 CELL 3 Electrical Room | Drywall | #CFACFF | D2 | Install Drywall | 2025-04-07 | 2025-04-10
Fitout COLO4 | C4 CELL 4 Electrical Room | Drywall | #CFACFF | D2 | Install Drywall | 2025-03-26 | 2025-03-29
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Drywall | #CFACFF | D2 | Install Drywall | 2025-03-27 | 2025-03-28
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Drywall | #CFACFF | D2 | Install Drywall | 2025-04-04 | 2025-04-05
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Drywall | #CFACFF | D2 | Install Drywall | 2025-04-28 | 2025-04-29
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Drywall | #CFACFF | D2 | Install Drywall | 2025-04-16 | 2025-04-17
Fitout COLO4 | C4 CELL 1 Data Hall | Electrical | #F3F0A8 | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-03 | 2025-04-08
Fitout COLO4 | C4 CELL 2 Data Hall | Electrical | #F3F0A8 | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-11 | 2025-04-17
Fitout COLO4 | C4 CELL 3 Data Hall | Electrical | #F3F0A8 | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-06 | 2025-05-10
Fitout COLO4 | C4 CELL 4 Data Hall | Electrical | #F3F0A8 | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-23 | 2025-04-28
Fitout COLO4 | C4 CELL 4 Electrical Room | Framing | #5297F8 | X21 | Framing | 2025-03-20 | 2025-03-21
Fitout COLO4 | C4 CELL 1 Electrical Room | Framing | #5297F8 | X21 | Framing | 2025-02-28 | 2025-03-03
Fitout COLO4 | C4 CELL 2 Data Hall | Framing | #5297F8 | X21 | Framing | 2025-03-06 | 2025-03-08
Fitout COLO4 | C4 CELL 2 Electrical Room | Framing | #5297F8 | X21 | Framing | 2025-03-10 | 2025-03-11
Fitout COLO4 | C4 CELL 3 Data Hall | Framing | #5297F8 | X21 | Framing | 2025-03-29 | 2025-04-01
Fitout COLO4 | C4 CELL 3 Electrical Room | Framing | #5297F8 | X21 | Framing | 2025-04-02 | 2025-04-03
Fitout COLO4 | C4 CELL 4 Data Hall | Framing | #5297F8 | X21 | Framing | 2025-03-17 | 2025-03-19
Fitout COLO4 | C4 CELL 1 Data Hall | Electrical | #F3F0A8 | EE44 | Install Perimeter Cable Trays | 2025-03-29 | 2025-04-02
Fitout COLO4 | C4 CELL 2 Data Hall | Electrical | #F3F0A8 | EE44 | Install Perimeter Cable Trays | 2025-04-07 | 2025-04-10
Fitout COLO4 | C4 CELL 3 Data Hall | Electrical | #F3F0A8 | EE44 | Install Perimeter Cable Trays | 2025-04-30 | 2025-05-05
Fitout COLO4 | C4 CELL 4 Data Hall | Electrical | #F3F0A8 | EE44 | Install Perimeter Cable Trays | 2025-04-18 | 2025-04-22
Fitout COLO4 | C4 CELL 1 Data Hall | Framing | #5297F8 | X19 | Install Screen Mesh + Caulking | 2025-03-15 | 2025-03-18
Fitout COLO4 | C4 CELL 2 Data Hall | Framing | #5297F8 | X19 | Install Screen Mesh + Caulking | 2025-03-25 | 2025-03-27
Fitout COLO4 | C4 CELL 3 Data Hall | Framing | #5297F8 | X19 | Install Screen Mesh + Caulking | 2025-04-17 | 2025-04-19
Fitout COLO4 | C4 CELL 4 Data Hall | Framing | #5297F8 | X19 | Install Screen Mesh + Caulking | 2025-04-04 | 2025-04-07
Fitout COLO4 | C4 CELL 1 Data Hall | Framing | #5297F8 | X38 | Install Secondary Steel | 2025-03-19 | 2025-03-20
Fitout COLO4 | C4 CELL 2 Data Hall | Framing | #5297F8 | X38 | Install Secondary Steel | 2025-03-28 | 2025-03-29
Fitout COLO4 | C4 CELL 3 Data Hall | Framing | #5297F8 | X38 | Install Secondary Steel | 2025-04-21 | 2025-04-22
Fitout COLO4 | C4 CELL 4 Data Hall | Framing | #5297F8 | X38 | Install Secondary Steel | 2025-04-08 | 2025-04-09
Fitout COLO4 | C4 CELL 1 Data Hall | Framing | #5297F8 | X9 | Layout Framing | 2025-02-24 | 2025-02-24
Fitout COLO4 | C4 CELL 2 Data Hall | Framing | #5297F8 | X9 | Layout Framing | 2025-03-05 | 2025-03-05
Fitout COLO4 | C4 CELL 3 Data Hall | Framing | #5297F8 | X9 | Layout Framing | 2025-03-28 | 2025-03-28
Fitout COLO4 | C4 CELL 4 Data Hall | Framing | #5297F8 | X9 | Layout Framing | 2025-03-15 | 2025-03-15
Fitout COLO4 | C4 CELL 1 Data Hall | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-03-08 | 2025-03-12
Fitout COLO4 | C4 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-03-08 | 2025-03-11
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-03-11 | 2025-03-13
Fitout COLO4 | C4 CELL 2 Data Hall | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-03-17 | 2025-03-20
Fitout COLO4 | C4 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-03-17 | 2025-03-19
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-03-19 | 2025-03-21
Fitout COLO4 | C4 CELL 3 Data Hall | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-04-09 | 2025-04-14
Fitout COLO4 | C4 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-04-09 | 2025-04-11
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-04-11 | 2025-04-15
Fitout COLO4 | C4 CELL 4 Data Hall | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-03-28 | 2025-04-01
Fitout COLO4 | C4 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-03-28 | 2025-03-31
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-03-31 | 2025-04-02
Fitout COLO4 | C4 CELL 1 Data Hall | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-03-08 | 2025-03-11
Fitout COLO4 | C4 CELL 1 Electrical Room | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-03-08 | 2025-03-10
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-03-11 | 2025-03-12
Fitout COLO4 | C4 CELL 2 Data Hall | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-03-17 | 2025-03-19
Fitout COLO4 | C4 CELL 2 Electrical Room | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-03-17 | 2025-03-18
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-03-19 | 2025-03-20
Fitout COLO4 | C4 CELL 3 Data Hall | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-04-09 | 2025-04-11
Fitout COLO4 | C4 CELL 3 Electrical Room | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-04-09 | 2025-04-10
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-04-11 | 2025-04-14
Fitout COLO4 | C4 CELL 4 Data Hall | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-03-28 | 2025-03-31
Fitout COLO4 | C4 CELL 4 Electrical Room | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-03-28 | 2025-03-29
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-03-31 | 2025-04-01
Fitout COLO4 | C4 CELL 1 Data Hall | Fire Protection | #C96C77 | R7 | Fire Protection OH R/I | 2025-03-05 | 2025-03-07
Fitout COLO4 | C4 CELL 1 Electrical Room | Fire Protection | #C96C78 | R8 | Fire Protection OH R/I | 2025-03-06 | 2025-03-07
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Fire Protection | #C96C79 | R9 | Fire Protection OH R/I | 2025-03-08 | 2025-03-10
Fitout COLO4 | C4 CELL 2 Data Hall | Fire Protection | #C96C80 | R10 | Fire Protection OH R/I | 2025-03-13 | 2025-03-15
Fitout COLO4 | C4 CELL 2 Electrical Room | Fire Protection | #C96C81 | R11 | Fire Protection OH R/I | 2025-03-14 | 2025-03-15
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Fire Protection | #C96C82 | R12 | Fire Protection OH R/I | 2025-03-17 | 2025-03-18
Fitout COLO4 | C4 CELL 3 Data Hall | Fire Protection | #C96C83 | R13 | Fire Protection OH R/I | 2025-04-05 | 2025-04-08
Fitout COLO4 | C4 CELL 3 Electrical Room | Fire Protection | #C96C84 | R14 | Fire Protection OH R/I | 2025-04-07 | 2025-04-08
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Fire Protection | #C96C85 | R15 | Fire Protection OH R/I | 2025-04-09 | 2025-04-10
Fitout COLO4 | C4 CELL 4 Data Hall | Fire Protection | #C96C86 | R16 | Fire Protection OH R/I | 2025-03-25 | 2025-03-27
Fitout COLO4 | C4 CELL 4 Electrical Room | Fire Protection | #C96C87 | R17 | Fire Protection OH R/I | 2025-03-26 | 2025-03-27
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Fire Protection | #C96C88 | R18 | Fire Protection OH R/I | 2025-03-28 | 2025-03-29
Fitout COLO4 | C4 CELL 1 Data Hall | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-03-11 | 2025-03-12
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-03-14 | 2025-03-20
Fitout COLO4 | C4 CELL 2 Data Hall | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-03-19 | 2025-03-20
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-03-24 | 2025-03-29
Fitout COLO4 | C4 CELL 3 Data Hall | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-04-11 | 2025-04-14
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-04-16 | 2025-04-22
Fitout COLO4 | C4 CELL 4 Data Hall | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-03-31 | 2025-04-01
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-04-03 | 2025-04-09
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Plumbing | #30585A | P4 | Overhead R/I - Plumbing | 2025-03-21 | 2025-03-28
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Plumbing | #30585A | P4 | Overhead R/I - Plumbing | 2025-03-31 | 2025-04-05
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Plumbing | #30585A | P4 | Overhead R/I - Plumbing | 2025-04-23 | 2025-04-29
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Plumbing | #30585A | P4 | Overhead R/I - Plumbing | 2025-04-10 | 2025-04-17
Fitout COLO4 | C4 CELL 1 Data Hall | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-03-12 | 2025-03-14
Fitout COLO4 | C4 CELL 1 Electrical Room | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-03-13 | 2025-03-14
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-04-01 | 2025-04-02
Fitout COLO4 | C4 CELL 2 Data Hall | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-03-20 | 2025-03-24
Fitout COLO4 | C4 CELL 2 Electrical Room | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-03-21 | 2025-03-24
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-04-09 | 2025-04-10
Fitout COLO4 | C4 CELL 3 Data Hall | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-04-14 | 2025-04-16
Fitout COLO4 | C4 CELL 3 Electrical Room | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-04-15 | 2025-04-16
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-05-02 | 2025-05-05
Fitout COLO4 | C4 CELL 4 Data Hall | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-04-01 | 2025-04-03
Fitout COLO4 | C4 CELL 4 Electrical Room | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-04-02 | 2025-04-03
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-04-21 | 2025-04-22
Fitout COLO4 | C4 CELL 1 Data Hall | Painting | #DBF1FE | Y7 | Paint Secondary Steel | 2025-03-21 | 2025-03-24
Fitout COLO4 | C4 CELL 2 Data Hall | Painting | #DBF1FE | Y7 | Paint Secondary Steel | 2025-03-31 | 2025-04-01
Fitout COLO4 | C4 CELL 3 Data Hall | Painting | #DBF1FE | Y7 | Paint Secondary Steel | 2025-04-23 | 2025-04-24
Fitout COLO4 | C4 CELL 4 Data Hall | Painting | #DBF1FE | Y7 | Paint Secondary Steel | 2025-04-10 | 2025-04-11
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | BAS | #303450 | BA1 | Pull & Terminate BAS Equipments | 2025-04-17 | 2025-04-25
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | BAS | #303450 | BA1 | Pull & Terminate BAS Equipments | 2025-04-25 | 2025-05-05
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | BAS | #303450 | BA1 | Pull & Terminate BAS Equipments | 2025-05-19 | 2025-05-28
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | BAS | #303450 | BA1 | Pull & Terminate BAS Equipments | 2025-05-07 | 2025-05-15
Fitout COLO4 | C4 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE47 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-04-04 | 2025-04-17
Fitout COLO4 | C4 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE47 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-05-01 | 2025-05-14
Fitout COLO4 | C4 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE47.1 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-06-24 | 2025-07-08
Fitout COLO4 | C4 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE47.1 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-05-28 | 2025-06-09
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Electrical | #F3F0A8 | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-04-11 | 2025-04-25
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Electrical | #F3F0A8 | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-04-21 | 2025-05-05
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Electrical | #F3F0A8 | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-14 | 2025-05-28
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Electrical | #F3F0A8 | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-01 | 2025-05-15
Fitout COLO4 | C4 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-04-18 | 2025-04-30
Fitout COLO4 | C4 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-05-15 | 2025-05-27
Fitout COLO4 | C4 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-07-09 | 2025-07-19
Fitout COLO4 | C4 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-06-10 | 2025-06-23
Fitout COLO4 | C4 CELL 1 Data Hall | Electrical | #F3F0A8 | EE17 | Pull Feeders from PDUs to Busways | 2025-04-22 | 2025-04-26
Fitout COLO4 | C4 CELL 2 Data Hall | Electrical | #F3F0A8 | EE17 | Pull Feeders from PDUs to Busways | 2025-04-30 | 2025-05-06
Fitout COLO4 | C4 CELL 3 Data Hall | Electrical | #F3F0A8 | EE17 | Pull Feeders from PDUs to Busways | 2025-05-23 | 2025-05-29
Fitout COLO4 | C4 CELL 4 Data Hall | Electrical | #F3F0A8 | EE17 | Pull Feeders from PDUs to Busways | 2025-05-12 | 2025-05-16
Fitout COLO4 | C4 CELL 1 Punchlist | CLAYCO | #C00000 | CP | Punchlist | 2025-05-06 | 2025-05-16
Fitout COLO4 | C4 CELL 2 Punchlist | CLAYCO | #C00000 | CP | Punchlist | 2025-05-31 | 2025-06-11
Fitout COLO4 | C4 CELL 3 Punchlist | CLAYCO | #C00000 | CP | Punchlist | 2025-07-22 | 2025-08-02
Fitout COLO4 | C4 CELL 4 Punchlist | CLAYCO | #C00000 | CP | Punchlist | 2025-06-27 | 2025-07-10
Fitout COLO4 | C4 CELL 1 Data Hall | HACs | #F8D9E7 | S2 | Raise HACs | 2025-04-09 | 2025-04-14
Fitout COLO4 | C4 CELL 2 Data Hall | HACs | #F8D9E7 | S2 | Raise HACs | 2025-04-18 | 2025-04-22
Fitout COLO4 | C4 CELL 3 Data Hall | HACs | #F8D9E7 | S2 | Raise HACs | 2025-05-12 | 2025-05-15
Fitout COLO4 | C4 CELL 4 Data Hall | HACs | #F8D9E7 | S2 | Raise HACs | 2025-04-29 | 2025-05-02
Fitout COLO4 | C4 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE51 | Set Electrical Equipments | 2025-03-31 | 2025-04-03
Fitout COLO4 | C4 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE51 | Set Electrical Equipments | 2025-03-26 | 2025-03-29
Fitout COLO4 | C4 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE51 | Set Electrical Equipments | 2025-04-18 | 2025-04-22
Fitout COLO4 | C4 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE51 | Set Electrical Equipments | 2025-04-05 | 2025-04-09
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Mech | #D3E660 | M6 | Set Mechanical Equipments | 2025-04-07 | 2025-04-10
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Mech | #D3E660 | M6 | Set Mechanical Equipments | 2025-04-16 | 2025-04-19
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Mech | #D3E660 | M6 | Set Mechanical Equipments | 2025-05-09 | 2025-05-13
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Mech | #D3E660 | M6 | Set Mechanical Equipments | 2025-04-26 | 2025-04-30
Fitout COLO4 | C4 CELL 1 Data Hall | Electrical | #F3F0A8 | EE7 | Set PDUs | 2025-04-03 | 2025-04-07
Fitout COLO4 | C4 CELL 2 Data Hall | Electrical | #F3F0A8 | EE7 | Set PDUs | 2025-04-11 | 2025-04-16
Fitout COLO4 | C4 CELL 3 Data Hall | Electrical | #F3F0A8 | EE7 | Set PDUs | 2025-05-06 | 2025-05-09
Fitout COLO4 | C4 CELL 4 Data Hall | Electrical | #F3F0A8 | EE7 | Set PDUs | 2025-04-23 | 2025-04-26
Fitout COLO4 | C4 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-04-18 | 2025-04-22
Fitout COLO4 | C4 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-05-15 | 2025-05-19
Fitout COLO4 | C4 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-07-09 | 2025-07-12
Fitout COLO4 | C4 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-06-10 | 2025-06-13
Fitout COLO4 | C4 CELL 1 Mechanical Gallery | Mech | #D3E660 | M7 | Terminate Mechanical Equipments | 2025-04-26 | 2025-04-30
Fitout COLO4 | C4 CELL 2 Mechanical Gallery | Mech | #D3E660 | M7 | Terminate Mechanical Equipments | 2025-05-06 | 2025-05-09
Fitout COLO4 | C4 CELL 3 Mechanical Gallery | Mech | #D3E660 | M7 | Terminate Mechanical Equipments | 2025-05-29 | 2025-06-02
Fitout COLO4 | C4 CELL 4 Mechanical Gallery | Mech | #D3E660 | M7 | Terminate Mechanical Equipments | 2025-05-16 | 2025-05-20
Fitout COLO4 | C4 CELL 1 Data Hall | Electrical | #F3F0A8 | EE58 | Terminate PDUs | 2025-05-01 | 2025-05-05
Fitout COLO4 | C4 CELL 2 Data Hall | Electrical | #F3F0A8 | EE58 | Terminate PDUs | 2025-05-28 | 2025-05-30
Fitout COLO4 | C4 CELL 3 Data Hall | Electrical | #F3F0A8 | EE58 | Terminate PDUs | 2025-07-18 | 2025-07-21
Fitout COLO4 | C4 CELL 4 Data Hall | Electrical | #F3F0A8 | EE58 | Terminate PDUs | 2025-06-24 | 2025-06-26
Fitout COLO5 | C5 CELL 1 Data Hall | HACs | #F8D9E7 | S1 | Assemble HACs [Qty - 5] | 2025-05-02 | 2025-05-08
Fitout COLO5 | C5 CELL 2 Data Hall | HACs | #F8D9E7 | S1 | Assemble HACs [Qty - 5] | 2025-05-12 | 2025-05-16
Fitout COLO5 | C5 CELL 3 Data Hall | HACs | #F8D9E7 | S1 | Assemble HACs [Qty - 5] | 2025-06-04 | 2025-06-09
Fitout COLO5 | C5 CELL 4 Data Hall | HACs | #F8D9E7 | S1 | Assemble HACs [Qty - 5] | 2025-05-22 | 2025-05-28
Fitout COLO5 | C5 CELL 1 Data Hall | Electrical | #F3F0A8 | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-19 | 2025-05-21
Fitout COLO5 | C5 CELL 2 Data Hall | Electrical | #F3F0A8 | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-28 | 2025-05-30
Fitout COLO5 | C5 CELL 3 Data Hall | Electrical | #F3F0A8 | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-06-20 | 2025-06-23
Fitout COLO5 | C5 CELL 4 Data Hall | Electrical | #F3F0A8 | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-06-07 | 2025-06-10
Fitout COLO5 | C5 CELL 1 Data Hall | HACs | #F8D9E7 | S4 | Detail HACs | 2025-05-19 | 2025-05-22
Fitout COLO5 | C5 CELL 2 Data Hall | HACs | #F8D9E7 | S4 | Detail HACs | 2025-05-28 | 2025-05-31
Fitout COLO5 | C5 CELL 3 Data Hall | HACs | #F8D9E7 | S4 | Detail HACs | 2025-06-20 | 2025-06-24
Fitout COLO5 | C5 CELL 4 Data Hall | HACs | #F8D9E7 | S4 | Detail HACs | 2025-06-07 | 2025-06-11
Fitout COLO5 | C5 CELL 1 Data Hall | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-04-15 | 2025-04-16
Fitout COLO5 | C5 CELL 1 Electrical Room | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-04-15 | 2025-04-15
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-05-02 | 2025-05-02
Fitout COLO5 | C5 CELL 2 Data Hall | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-04-23 | 2025-04-24
Fitout COLO5 | C5 CELL 2 Electrical Room | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-04-23 | 2025-04-23
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-05-12 | 2025-05-12
Fitout COLO5 | C5 CELL 3 Data Hall | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-05-16 | 2025-05-17
Fitout COLO5 | C5 CELL 3 Electrical Room | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-05-16 | 2025-05-16
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-06-04 | 2025-06-04
Fitout COLO5 | C5 CELL 4 Data Hall | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-05-05 | 2025-05-06
Fitout COLO5 | C5 CELL 4 Electrical Room | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-05-05 | 2025-05-05
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Framing | #5297F8 | X30 | Drop Cable Tray [Hanging Rods] | 2025-05-22 | 2025-05-22
Fitout COLO5 | C5 CELL 1 Data Hall | Drywall | #CFACFF | D5 | Finish Drywall | 2025-04-11 | 2025-04-15
Fitout COLO5 | C5 CELL 1 Electrical Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-04-15 | 2025-04-16
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Drywall | #CFACFF | D5 | Finish Drywall | 2025-05-02 | 2025-05-05
Fitout COLO5 | C5 CELL 2 Data Hall | Drywall | #CFACFF | D5 | Finish Drywall | 2025-04-21 | 2025-04-23
Fitout COLO5 | C5 CELL 2 Electrical Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-04-23 | 2025-04-24
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Drywall | #CFACFF | D5 | Finish Drywall | 2025-05-12 | 2025-05-13
Fitout COLO5 | C5 CELL 3 Data Hall | Drywall | #CFACFF | D5 | Finish Drywall | 2025-05-14 | 2025-05-16
Fitout COLO5 | C5 CELL 3 Electrical Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-05-16 | 2025-05-17
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Drywall | #CFACFF | D5 | Finish Drywall | 2025-06-04 | 2025-06-05
Fitout COLO5 | C5 CELL 4 Data Hall | Drywall | #CFACFF | D5 | Finish Drywall | 2025-05-01 | 2025-05-05
Fitout COLO5 | C5 CELL 4 Electrical Room | Drywall | #CFACFF | D5 | Finish Drywall | 2025-05-05 | 2025-05-06
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Drywall | #CFACFF | D5 | Finish Drywall | 2025-05-22 | 2025-05-23
Fitout COLO5 | C5 CELL 1 Data Hall | CLAYCO | #C00000 | CC | General Cleaning | 2025-04-28 | 2025-04-28
Fitout COLO5 | C5 CELL 1 Electrical Room | CLAYCO | #C00000 | CC | General Cleaning | 2025-04-19 | 2025-04-19
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | CLAYCO | #C00000 | CC | General Cleaning | 2025-05-08 | 2025-05-10
Fitout COLO5 | C5 CELL 2 Data Hall | CLAYCO | #C00000 | CC | General Cleaning | 2025-05-07 | 2025-05-07
Fitout COLO5 | C5 CELL 2 Electrical Room | CLAYCO | #C00000 | CC | General Cleaning | 2025-04-28 | 2025-04-28
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | CLAYCO | #C00000 | CC | General Cleaning | 2025-05-16 | 2025-05-19
Fitout COLO5 | C5 CELL 3 Data Hall | CLAYCO | #C00000 | CC | General Cleaning | 2025-05-30 | 2025-05-30
Fitout COLO5 | C5 CELL 3 Electrical Room | CLAYCO | #C00000 | CC | General Cleaning | 2025-05-21 | 2025-05-21
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | CLAYCO | #C00000 | CC | General Cleaning | 2025-06-09 | 2025-06-11
Fitout COLO5 | C5 CELL 4 Data Hall | CLAYCO | #C00000 | CC | General Cleaning | 2025-05-17 | 2025-05-17
Fitout COLO5 | C5 CELL 4 Electrical Room | CLAYCO | #C00000 | CC | General Cleaning | 2025-05-09 | 2025-05-09
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | CLAYCO | #C00000 | CC | General Cleaning | 2025-05-28 | 2025-05-30
Fitout COLO5 | C5 CELL 1 Data Hall | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-04-04 | 2025-04-07
Fitout COLO5 | C5 CELL 1 Electrical Room | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-04-07 | 2025-04-08
Fitout COLO5 | C5 CELL 2 Data Hall | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-04-14 | 2025-04-16
Fitout COLO5 | C5 CELL 2 Electrical Room | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-04-16 | 2025-04-17
Fitout COLO5 | C5 CELL 3 Data Hall | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-05-07 | 2025-05-09
Fitout COLO5 | C5 CELL 3 Electrical Room | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-05-09 | 2025-05-10
Fitout COLO5 | C5 CELL 4 Data Hall | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-04-24 | 2025-04-26
Fitout COLO5 | C5 CELL 4 Electrical Room | Drywall | #CFACFF | D1 | In-Wall R/I | 2025-04-26 | 2025-04-28
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | BAS | #303450 | BA | Install BAS Equipments | 2025-05-09 | 2025-05-20
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | BAS | #303450 | BA | Install BAS Equipments | 2025-05-17 | 2025-05-29
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | BAS | #303450 | BA | Install BAS Equipments | 2025-06-10 | 2025-06-21
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | BAS | #303450 | BA | Install BAS Equipments | 2025-05-29 | 2025-06-09
Fitout COLO5 | C5 CELL 1 Data Hall | Electrical | #F3F0A8 | EE39 | Install Busways on HAC Arms | 2025-05-06 | 2025-05-10
Fitout COLO5 | C5 CELL 2 Data Hall | Electrical | #F3F0A8 | EE39 | Install Busways on HAC Arms | 2025-05-14 | 2025-05-19
Fitout COLO5 | C5 CELL 3 Data Hall | Electrical | #F3F0A8 | EE39 | Install Busways on HAC Arms | 2025-06-06 | 2025-06-11
Fitout COLO5 | C5 CELL 4 Data Hall | Electrical | #F3F0A8 | EE39 | Install Busways on HAC Arms | 2025-05-27 | 2025-05-30
Fitout COLO5 | C5 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-04-16 | 2025-04-17
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-05-09 | 2025-05-10
Fitout COLO5 | C5 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-04-24 | 2025-04-25
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-05-17 | 2025-05-19
Fitout COLO5 | C5 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-05-17 | 2025-05-19
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-06-10 | 2025-06-11
Fitout COLO5 | C5 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-05-06 | 2025-05-07
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Electrical | #F3F0A8 | EE35 | Install Cable Trays / Pathways | 2025-05-29 | 2025-05-30
Fitout COLO5 | C5 CELL 1 Data Hall | Framing | #5297F8 | X26 | Install Ceiling Grid | 2025-04-28 | 2025-05-01
Fitout COLO5 | C5 CELL 2 Data Hall | Framing | #5297F8 | X26 | Install Ceiling Grid | 2025-05-07 | 2025-05-10
Fitout COLO5 | C5 CELL 3 Data Hall | Framing | #5297F8 | X26 | Install Ceiling Grid | 2025-05-30 | 2025-06-03
Fitout COLO5 | C5 CELL 4 Data Hall | Framing | #5297F8 | X26 | Install Ceiling Grid | 2025-05-17 | 2025-05-21
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Framing | #5297F8 | X27 | Install Ceiling Grid + Device Tiles | 2025-05-05 | 2025-05-08
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Framing | #5297F8 | X27 | Install Ceiling Grid + Device Tiles | 2025-05-13 | 2025-05-16
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Framing | #5297F8 | X27 | Install Ceiling Grid + Device Tiles | 2025-06-05 | 2025-06-09
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Framing | #5297F8 | X27 | Install Ceiling Grid + Device Tiles | 2025-05-23 | 2025-05-28
Fitout COLO5 | C5 CELL 1 Data Hall | Electrical | #F3F0A8 | EE43 | Install Conduits PDU to Cable Trays | 2025-05-22 | 2025-05-23
Fitout COLO5 | C5 CELL 2 Data Hall | Electrical | #F3F0A8 | EE43 | Install Conduits PDU to Cable Trays | 2025-05-31 | 2025-06-03
Fitout COLO5 | C5 CELL 3 Data Hall | Electrical | #F3F0A8 | EE43 | Install Conduits PDU to Cable Trays | 2025-06-24 | 2025-06-26
Fitout COLO5 | C5 CELL 4 Data Hall | Electrical | #F3F0A8 | EE43 | Install Conduits PDU to Cable Trays | 2025-06-11 | 2025-06-13
Fitout COLO5 | C5 CELL 1 Data Hall | Framing | #5297F8 | X35 | Install Device Tiles | 2025-05-08 | 2025-05-09
Fitout COLO5 | C5 CELL 2 Data Hall | Framing | #5297F8 | X35 | Install Device Tiles | 2025-05-16 | 2025-05-17
Fitout COLO5 | C5 CELL 3 Data Hall | Framing | #5297F8 | X35 | Install Device Tiles | 2025-06-09 | 2025-06-10
Fitout COLO5 | C5 CELL 4 Data Hall | Framing | #5297F8 | X35 | Install Device Tiles | 2025-05-28 | 2025-05-29
Fitout COLO5 | C5 CELL 1 Data Hall | Drywall | #CFACFF | D2 | Install Drywall | 2025-04-08 | 2025-04-10
Fitout COLO5 | C5 CELL 2 Data Hall | Drywall | #CFACFF | D2 | Install Drywall | 2025-04-17 | 2025-04-19
Fitout COLO5 | C5 CELL 3 Data Hall | Drywall | #CFACFF | D2 | Install Drywall | 2025-05-10 | 2025-05-13
Fitout COLO5 | C5 CELL 4 Data Hall | Drywall | #CFACFF | D2 | Install Drywall | 2025-04-28 | 2025-04-30
Fitout COLO5 | C5 CELL 2 Electrical Room | Drywall | #CFACFF | D2 | Install Drywall | 2025-04-18 | 2025-04-22
Fitout COLO5 | C5 CELL 1 Electrical Room | Drywall | #CFACFF | D2 | Install Drywall | 2025-04-09 | 2025-04-14
Fitout COLO5 | C5 CELL 3 Electrical Room | Drywall | #CFACFF | D2 | Install Drywall | 2025-05-12 | 2025-05-15
Fitout COLO5 | C5 CELL 4 Electrical Room | Drywall | #CFACFF | D2 | Install Drywall | 2025-04-29 | 2025-05-02
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Drywall | #CFACFF | D2 | Install Drywall | 2025-04-30 | 2025-05-01
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Drywall | #CFACFF | D2 | Install Drywall | 2025-05-09 | 2025-05-10
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Drywall | #CFACFF | D2 | Install Drywall | 2025-06-02 | 2025-06-03
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Drywall | #CFACFF | D2 | Install Drywall | 2025-05-20 | 2025-05-21
Fitout COLO5 | C5 CELL 1 Data Hall | Electrical | #F3F0A8 | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-08 | 2025-05-13
Fitout COLO5 | C5 CELL 2 Data Hall | Electrical | #F3F0A8 | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-16 | 2025-05-21
Fitout COLO5 | C5 CELL 3 Data Hall | Electrical | #F3F0A8 | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-06-09 | 2025-06-13
Fitout COLO5 | C5 CELL 4 Data Hall | Electrical | #F3F0A8 | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-28 | 2025-06-02
Fitout COLO5 | C5 CELL 1 Data Hall | Framing | #5297F8 | X21 | Framing | 2025-04-01 | 2025-04-03
Fitout COLO5 | C5 CELL 1 Electrical Room | Framing | #5297F8 | X21 | Framing | 2025-04-04 | 2025-04-05
Fitout COLO5 | C5 CELL 2 Data Hall | Framing | #5297F8 | X21 | Framing | 2025-04-09 | 2025-04-11
Fitout COLO5 | C5 CELL 2 Electrical Room | Framing | #5297F8 | X21 | Framing | 2025-04-14 | 2025-04-15
Fitout COLO5 | C5 CELL 3 Data Hall | Framing | #5297F8 | X21 | Framing | 2025-05-02 | 2025-05-06
Fitout COLO5 | C5 CELL 3 Electrical Room | Framing | #5297F8 | X21 | Framing | 2025-05-07 | 2025-05-08
Fitout COLO5 | C5 CELL 4 Data Hall | Framing | #5297F8 | X21 | Framing | 2025-04-21 | 2025-04-23
Fitout COLO5 | C5 CELL 4 Electrical Room | Framing | #5297F8 | X21 | Framing | 2025-04-24 | 2025-04-25
Fitout COLO5 | C5 CELL 1 Data Hall | Electrical | #F3F0A8 | EE44 | Install Perimeter Cable Trays | 2025-05-02 | 2025-05-07
Fitout COLO5 | C5 CELL 2 Data Hall | Electrical | #F3F0A8 | EE44 | Install Perimeter Cable Trays | 2025-05-12 | 2025-05-15
Fitout COLO5 | C5 CELL 3 Data Hall | Electrical | #F3F0A8 | EE44 | Install Perimeter Cable Trays | 2025-06-04 | 2025-06-07
Fitout COLO5 | C5 CELL 4 Data Hall | Electrical | #F3F0A8 | EE44 | Install Perimeter Cable Trays | 2025-05-22 | 2025-05-27
Fitout COLO5 | C5 CELL 1 Data Hall | Framing | #5297F8 | X19 | Install Screen Mesh + Caulking | 2025-04-19 | 2025-04-22
Fitout COLO5 | C5 CELL 2 Data Hall | Framing | #5297F8 | X19 | Install Screen Mesh + Caulking | 2025-04-28 | 2025-04-30
Fitout COLO5 | C5 CELL 3 Data Hall | Framing | #5297F8 | X19 | Install Screen Mesh + Caulking | 2025-05-21 | 2025-05-23
Fitout COLO5 | C5 CELL 4 Data Hall | Framing | #5297F8 | X19 | Install Screen Mesh + Caulking | 2025-05-09 | 2025-05-12
Fitout COLO5 | C5 CELL 1 Data Hall | Framing | #5297F8 | X38 | Install Secondary Steel | 2025-04-23 | 2025-04-24
Fitout COLO5 | C5 CELL 2 Data Hall | Framing | #5297F8 | X38 | Install Secondary Steel | 2025-05-01 | 2025-05-02
Fitout COLO5 | C5 CELL 3 Data Hall | Framing | #5297F8 | X38 | Install Secondary Steel | 2025-05-27 | 2025-05-27
Fitout COLO5 | C5 CELL 4 Data Hall | Framing | #5297F8 | X38 | Install Secondary Steel | 2025-05-13 | 2025-05-14
Fitout COLO5 | C5 CELL 1 Data Hall | Framing | #5297F8 | X9 | Layout Framing | 2025-03-31 | 2025-03-31
Fitout COLO5 | C5 CELL 2 Data Hall | Framing | #5297F8 | X9 | Layout Framing | 2025-04-08 | 2025-04-08
Fitout COLO5 | C5 CELL 3 Data Hall | Framing | #5297F8 | X9 | Layout Framing | 2025-05-01 | 2025-05-01
Fitout COLO5 | C5 CELL 4 Data Hall | Framing | #5297F8 | X9 | Layout Framing | 2025-04-19 | 2025-04-19
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-05-05 | 2025-05-07
Fitout COLO5 | C5 CELL 1 Data Hall | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-04-11 | 2025-04-16
Fitout COLO5 | C5 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-04-11 | 2025-04-15
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-04-15 | 2025-04-17
Fitout COLO5 | C5 CELL 2 Data Hall | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-04-21 | 2025-04-24
Fitout COLO5 | C5 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-04-21 | 2025-04-23
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-04-23 | 2025-04-25
Fitout COLO5 | C5 CELL 3 Data Hall | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-05-14 | 2025-05-17
Fitout COLO5 | C5 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-05-14 | 2025-05-16
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-05-16 | 2025-05-19
Fitout COLO5 | C5 CELL 4 Data Hall | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-05-01 | 2025-05-06
Fitout COLO5 | C5 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE1 | Overhead R/I - Electrical | 2025-05-01 | 2025-05-05
Fitout COLO5 | C5 CELL 1 Data Hall | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-04-11 | 2025-04-15
Fitout COLO5 | C5 CELL 1 Electrical Room | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-04-11 | 2025-04-14
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-04-15 | 2025-04-16
Fitout COLO5 | C5 CELL 2 Data Hall | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-04-21 | 2025-04-23
Fitout COLO5 | C5 CELL 2 Electrical Room | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-04-21 | 2025-04-22
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-04-23 | 2025-04-24
Fitout COLO5 | C5 CELL 3 Data Hall | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-05-14 | 2025-05-16
Fitout COLO5 | C5 CELL 3 Electrical Room | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-05-14 | 2025-05-15
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-05-16 | 2025-05-17
Fitout COLO5 | C5 CELL 4 Data Hall | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-05-01 | 2025-05-05
Fitout COLO5 | C5 CELL 4 Electrical Room | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-05-01 | 2025-05-02
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Fire Protection | #C96C74 | R1 | Overhead R/I - Fire Alarm | 2025-05-05 | 2025-05-06
Fitout COLO5 | C5 CELL 1 Data Hall | Fire Protection | #C96C74 | R19 | Fire Protection OH R/I | 2025-04-08 | 2025-04-10
Fitout COLO5 | C5 CELL 1 Electrical Room | Fire Protection | #C96C74 | R20 | Fire Protection OH R/I | 2025-04-09 | 2025-04-10
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Fire Protection | #C96C74 | R21 | Fire Protection OH R/I | 2025-04-11 | 2025-04-14
Fitout COLO5 | C5 CELL 2 Data Hall | Fire Protection | #C96C74 | R22 | Fire Protection OH R/I | 2025-04-17 | 2025-04-19
Fitout COLO5 | C5 CELL 2 Electrical Room | Fire Protection | #C96C74 | R23 | Fire Protection OH R/I | 2025-04-18 | 2025-04-19
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Fire Protection | #C96C74 | R24 | Fire Protection OH R/I | 2025-04-21 | 2025-04-22
Fitout COLO5 | C5 CELL 3 Data Hall | Fire Protection | #C96C74 | R25 | Fire Protection OH R/I | 2025-05-10 | 2025-05-13
Fitout COLO5 | C5 CELL 3 Electrical Room | Fire Protection | #C96C74 | R26 | Fire Protection OH R/I | 2025-05-12 | 2025-05-13
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Fire Protection | #C96C74 | R27 | Fire Protection OH R/I | 2025-05-14 | 2025-05-15
Fitout COLO5 | C5 CELL 4 Data Hall | Fire Protection | #C96C74 | R28 | Fire Protection OH R/I | 2025-04-28 | 2025-04-30
Fitout COLO5 | C5 CELL 4 Electrical Room | Fire Protection | #C96C74 | R29 | Fire Protection OH R/I | 2025-04-29 | 2025-04-30
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Fire Protection | #C96C74 | R30 | Fire Protection OH R/I | 2025-05-01 | 2025-05-02
Fitout COLO5 | C5 CELL 1 Data Hall | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-04-15 | 2025-04-16
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-04-18 | 2025-04-24
Fitout COLO5 | C5 CELL 2 Data Hall | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-04-23 | 2025-04-24
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-04-26 | 2025-05-02
Fitout COLO5 | C5 CELL 3 Data Hall | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-05-16 | 2025-05-17
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-05-20 | 2025-05-27
Fitout COLO5 | C5 CELL 4 Data Hall | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-05-05 | 2025-05-06
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Mech | #D3E660 | M5 | Overhead R/I - Mechanical | 2025-05-08 | 2025-05-14
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Plumbing | #30585A | P4 | Overhead R/I - Plumbing | 2025-04-25 | 2025-05-01
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Plumbing | #30585A | P4 | Overhead R/I - Plumbing | 2025-05-05 | 2025-05-10
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Plumbing | #30585A | P4 | Overhead R/I - Plumbing | 2025-05-28 | 2025-06-03
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Plumbing | #30585A | P4 | Overhead R/I - Plumbing | 2025-05-15 | 2025-05-21
Fitout COLO5 | C5 CELL 1 Data Hall | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-04-16 | 2025-04-18
Fitout COLO5 | C5 CELL 1 Electrical Room | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-04-17 | 2025-04-18
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-05-06 | 2025-05-07
Fitout COLO5 | C5 CELL 2 Data Hall | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-04-24 | 2025-04-26
Fitout COLO5 | C5 CELL 2 Electrical Room | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-04-25 | 2025-04-26
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-05-14 | 2025-05-15
Fitout COLO5 | C5 CELL 3 Data Hall | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-05-17 | 2025-05-20
Fitout COLO5 | C5 CELL 3 Electrical Room | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-05-19 | 2025-05-20
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-06-06 | 2025-06-07
Fitout COLO5 | C5 CELL 4 Data Hall | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-05-06 | 2025-05-08
Fitout COLO5 | C5 CELL 4 Electrical Room | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-05-07 | 2025-05-08
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Painting | #DBF1FE | Y2 | Paint Dry-Wall | 2025-05-27 | 2025-05-27
Fitout COLO5 | C5 CELL 1 Data Hall | Painting | #DBF1FE | Y7 | Paint Secondary Steel | 2025-04-25 | 2025-04-26
Fitout COLO5 | C5 CELL 2 Data Hall | Painting | #DBF1FE | Y7 | Paint Secondary Steel | 2025-05-05 | 2025-05-06
Fitout COLO5 | C5 CELL 3 Data Hall | Painting | #DBF1FE | Y7 | Paint Secondary Steel | 2025-05-28 | 2025-05-29
Fitout COLO5 | C5 CELL 4 Data Hall | Painting | #DBF1FE | Y7 | Paint Secondary Steel | 2025-05-15 | 2025-05-16
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | BAS | #303450 | BA1 | Pull & Terminate BAS Equipments | 2025-05-21 | 2025-05-30
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | BAS | #303450 | BA1 | Pull & Terminate BAS Equipments | 2025-05-30 | 2025-06-07
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | BAS | #303450 | BA1 | Pull & Terminate BAS Equipments | 2025-06-23 | 2025-07-01
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | BAS | #303450 | BA1 | Pull & Terminate BAS Equipments | 2025-06-10 | 2025-06-19
Fitout COLO5 | C5 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE47 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-05-02 | 2025-05-15
Fitout COLO5 | C5 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE47 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-05-30 | 2025-06-11
Fitout COLO5 | C5 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE47.1 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-07-11 | 2025-07-23
Fitout COLO5 | C5 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE47.1 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-06-12 | 2025-06-25
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Electrical | #F3F0A8 | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-16 | 2025-05-30
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Electrical | #F3F0A8 | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-27 | 2025-06-07
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Electrical | #F3F0A8 | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-06-18 | 2025-07-01
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Electrical | #F3F0A8 | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-06-05 | 2025-06-19
Fitout COLO5 | C5 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-05-16 | 2025-05-29
Fitout COLO5 | C5 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-06-12 | 2025-06-24
Fitout COLO5 | C5 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-07-24 | 2025-08-05
Fitout COLO5 | C5 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-06-26 | 2025-07-10
Fitout COLO5 | C5 CELL 1 Data Hall | Electrical | #F3F0A8 | EE17 | Pull Feeders from PDUs to Busways | 2025-05-27 | 2025-05-31
Fitout COLO5 | C5 CELL 2 Data Hall | Electrical | #F3F0A8 | EE17 | Pull Feeders from PDUs to Busways | 2025-06-04 | 2025-06-09
Fitout COLO5 | C5 CELL 3 Data Hall | Electrical | #F3F0A8 | EE17 | Pull Feeders from PDUs to Busways | 2025-06-27 | 2025-07-02
Fitout COLO5 | C5 CELL 4 Data Hall | Electrical | #F3F0A8 | EE17 | Pull Feeders from PDUs to Busways | 2025-06-16 | 2025-06-20
Fitout COLO5 | C5 CELL 1 Punchlist | CLAYCO | #C00000 | CP | Punchlist | 2025-06-05 | 2025-06-17
Fitout COLO5 | C5 CELL 2 Punchlist | CLAYCO | #C00000 | CP | Punchlist | 2025-06-28 | 2025-07-11
Fitout COLO5 | C5 CELL 3 Punchlist | CLAYCO | #C00000 | CP | Punchlist | 2025-08-09 | 2025-08-21
Fitout COLO5 | C5 CELL 4 Punchlist | CLAYCO | #C00000 | CP | Punchlist | 2025-07-15 | 2025-07-25
Fitout COLO5 | C5 CELL 1 Data Hall | HACs | #F8D9E7 | S2 | Raise HACs | 2025-05-14 | 2025-05-17
Fitout COLO5 | C5 CELL 2 Data Hall | HACs | #F8D9E7 | S2 | Raise HACs | 2025-05-22 | 2025-05-27
Fitout COLO5 | C5 CELL 3 Data Hall | HACs | #F8D9E7 | S2 | Raise HACs | 2025-06-16 | 2025-06-19
Fitout COLO5 | C5 CELL 4 Data Hall | HACs | #F8D9E7 | S2 | Raise HACs | 2025-06-03 | 2025-06-06
Fitout COLO5 | C5 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE51 | Set Electrical Equipments | 2025-04-21 | 2025-05-01
Fitout COLO5 | C5 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE51 | Set Electrical Equipments | 2025-04-29 | 2025-05-02
Fitout COLO5 | C5 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE51 | Set Electrical Equipments | 2025-05-22 | 2025-05-27
Fitout COLO5 | C5 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE51 | Set Electrical Equipments | 2025-05-10 | 2025-05-14
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Mech | #D3E660 | M6 | Set Mechanical Equipments | 2025-05-12 | 2025-05-15
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Mech | #D3E660 | M6 | Set Mechanical Equipments | 2025-05-20 | 2025-05-23
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Mech | #D3E660 | M6 | Set Mechanical Equipments | 2025-06-12 | 2025-06-17
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Mech | #D3E660 | M6 | Set Mechanical Equipments | 2025-05-31 | 2025-06-04
Fitout COLO5 | C5 CELL 1 Data Hall | Electrical | #F3F0A8 | EE7 | Set PDUs | 2025-05-08 | 2025-05-12
Fitout COLO5 | C5 CELL 2 Data Hall | Electrical | #F3F0A8 | EE7 | Set PDUs | 2025-05-16 | 2025-05-20
Fitout COLO5 | C5 CELL 3 Data Hall | Electrical | #F3F0A8 | EE7 | Set PDUs | 2025-06-09 | 2025-06-12
Fitout COLO5 | C5 CELL 4 Data Hall | Electrical | #F3F0A8 | EE7 | Set PDUs | 2025-05-28 | 2025-05-31
Fitout COLO5 | C5 CELL 1 Electrical Room | Electrical | #F3F0A8 | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-05-16 | 2025-05-20
Fitout COLO5 | C5 CELL 2 Electrical Room | Electrical | #F3F0A8 | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-06-12 | 2025-06-17
Fitout COLO5 | C5 CELL 3 Electrical Room | Electrical | #F3F0A8 | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-07-24 | 2025-07-29
Fitout COLO5 | C5 CELL 4 Electrical Room | Electrical | #F3F0A8 | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-06-26 | 2025-06-30
Fitout COLO5 | C5 CELL 3 Mechanical Gallery | Mech | #D3E660 | M7 | Terminate Mechanical Equipments | 2025-07-02 | 2025-07-08
Fitout COLO5 | C5 CELL 1 Mechanical Gallery | Mech | #D3E660 | M7 | Terminate Mechanical Equipments | 2025-05-31 | 2025-06-04
Fitout COLO5 | C5 CELL 2 Mechanical Gallery | Mech | #D3E660 | M7 | Terminate Mechanical Equipments | 2025-06-09 | 2025-06-12
Fitout COLO5 | C5 CELL 4 Mechanical Gallery | Mech | #D3E660 | M7 | Terminate Mechanical Equipments | 2025-06-20 | 2025-06-24
Fitout COLO5 | C5 CELL 1 Data Hall | Electrical | #F3F0A8 | EE58 | Terminate PDUs | 2025-06-02 | 2025-06-04
Fitout COLO5 | C5 CELL 2 Data Hall | Electrical | #F3F0A8 | EE58 | Terminate PDUs | 2025-06-25 | 2025-06-27
Fitout COLO5 | C5 CELL 3 Data Hall | Electrical | #F3F0A8 | EE58 | Terminate PDUs | 2025-08-06 | 2025-08-08
Fitout COLO5 | C5 CELL 4 Data Hall | Electrical | #F3F0A8 | EE58 | Terminate PDUs | 2025-07-11 | 2025-07-14
Foundations | Foundations | Foundations | #C65911 | F1 | Foundations / Stem Walls | 2024-09-19 | 2024-10-09
Foundations | Foundations | Foundations | #C65911 | F1 | Foundations / Stem Walls | 2024-10-10 | 2024-11-12
Preconstruction | BIM | BIM | #808080 | 0.1 | Above ground BIM Co-ordination | 2024-09-27 | 2024-12-23
Preconstruction | BIM | BIM | #808080 | 0 | BIM Kickoff | 2024-07-18
Preconstruction | RFP / PSR | Precon | #D0CECE | PC1 | PSR Executed (Early Works) | 2024-06-06 | 2024-06-06
Preconstruction | RFP / PSR | Precon | #D0CECE | PC2 | PSR Executed (Full GMP) | 2024-09-30 | 2024-09-30
Preconstruction | RFP / PSR | Precon | #D0CECE | PC3 | RFP Issued (Revised 3.21.24) and Proposal Due to MSFT | 2024-03-25 | 2024-04-12
Preconstruction | BIM | BIM | #808080 | 0 | UG BIM Co-ordination | 19-Jul-24 A | 2024-09-26
Procurement | Early Awards | Procure | #A6A6A7 | 19 | ARL & Subcontractor Awards | 2024-06-07 | 2024-09-07
Procurement | Early Awards | Procure | #A6A6A6 | 14 | Buyouts & Early Procurement | 2024-06-07 | 2024-09-30
Procurement MSFT OFCI ROJ CFCI (Critical Only) | CFCI (Critical Only) | Procure | #A6A6A7 | 20 | Cable Bus Fabrication/ Lead Time | 2024-11-15 | 2025-03-03
Procurement MSFT OFCI ROJ CFCI (Critical Only) | CFCI (Critical Only) | Procure | #A6A6A7 | 21 | CFCI- MV Cables Fabrication/ Lead Time | 2024-08-17 | 2025-04-24
Procurement MSFT OFCI ROJ CFCI (Critical Only) | CFCI (Critical Only) | Procure | #A6A6A7 | 31 | HACs Fabrication/ Lead Time | 2024-11-15 | 2024-12-05
Procurement MSFT OFCI ROJ CFCI (Critical Only) | CFCI (Critical Only) | Procure | #A6A6A7 | 116 | MV Metering Cabinet - *Not Used* [65 Weeks] - Not Tied | 2024-08-07 | 2025-11-21
Procurement MSFT OFCI ROJ CFCI (Critical Only) | CFCI (Critical Only) | Procure | #A6A6A7 | 117 | MV Metering Cabinet - Substitute [43 Weeks] | 2024-08-07 | 2025-06-18
Procurement MSFT OFCI ROJ COLO3 | C3 Building Automation System | Procure | #A6A6A7 | 15 | Admin/C03- OFCI- Building Automation System (BAS) (ALC) Shipping/ ROJ | 2025-02-19 | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 UPS System W / Battery | Procure | #A6A6A7 | 16 | Admin/C03- OFCI- Received SUB Warehouse 9/28/2023 UPS System w/ Battery (UPS) (Eaton) (SOW Del Date- 8/13/23) | 2024-09-02
Procurement MSFT OFCI ROJ COLO3 | C3 Air Handling Units | Procure | #A6A6A7 | 17 | Air Handling Units (AHU) (Stulz) Delivered |  | 2025-03-13
Procurement MSFT OFCI ROJ COLO3 | C3 Air Handling Units | Procure | #A6A6A7 | 18 | Air Handling Units (AHU) (Stulz) Shipped/ROJ | 2025-03-09 | 2025-03-13
Procurement MSFT OFCI ROJ COLO3 | C3 Auto Transfer Control Panel | Procure | #A6A6A6 | 1 | Auto Transfer Control Panel (TCP) Delivered |  | 2025-03-08
Procurement MSFT OFCI ROJ COLO3 | C3 Auto Transfer Control Panel | Procure | #A6A6A6 | 2 | Auto Transfer Control Panel (TCP) Shipping/ ROJ | 2025-03-08 | 2025-03-08
Procurement MSFT OFCI ROJ COLO3 | C3 Automatic Transfer Switches | Procure | #A6A6A6 | 3 | Automatic Transfer Switches (ATS) (Schneider) Delivered |  | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 Automatic Transfer Switches | Procure | #A6A6A6 | 4 | Automatic Transfer Switches (ATS) (Schneider) Shipping/ ROJ | 2025-02-19 | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 Auxillary Power Distribution | Procure | #A6A6A6 | 5 | Auxillary (Mech) Power Distribution Panels (ADP) Delivered |  | 2025-03-08
Procurement MSFT OFCI ROJ COLO3 | C3 Auxillary Power Distribution | Procure | #A6A6A6 | 6 | Auxillary (Mech) Power Distribution Panels (ADP) Shipping/ ROJ | 2025-03-08 | 2025-03-08
Procurement MSFT OFCI ROJ COLO3 | C3 Building Automation System | Procure | #A6A6A6 | 9 | Building Automation System (BAS) (ALC) Delivered |  | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 Busway / Busplugs | Procure | #A6A6A6 | 12 | Busway / Busplugs (Starline Holding) Delivered |  | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 Busway / Busplugs | Procure | #A6A6A6 | 13 | Busway / Busplugs (Starline Holding) Shipping/ ROJ | 2025-02-19 | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 Elec Performance Monitoring System | Procure | #A6A6A7 | 27 | Elec. Performance Monitoring System (EPMS) (Schneider) Delivered |  | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 Elec Performance Monitoring System | Procure | #A6A6A7 | 28 | Elec. Performance Monitoring System (EPMS) (Schneider) Shipping/ ROJ | 2025-02-19 | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 HAC/Racking | Procure | #A6A6A7 | 29 | HAC/Racking (Tate Access) Delivered |  | 2025-02-21
Procurement MSFT OFCI ROJ COLO3 | C3 HAC/Racking | Procure | #A6A6A7 | 30 | HAC/Racking (Tate Access) Shipping/ ROJ | 2025-02-19 | 2025-02-21
Procurement MSFT OFCI ROJ COLO3 | C3 LV Switchgear | Procure | #A6A6A7 | 34 | LV Switchgear (LVS) (Eaton) Delivered |  | 2025-03-04
Procurement MSFT OFCI ROJ COLO3 | C3 LV Switchgear | Procure | #A6A6A7 | 35 | LV Switchgear (LVS) (Eaton) Shipping/ ROJ | 2025-02-28 | 2025-03-04
Procurement MSFT OFCI ROJ COLO3 | C3 Main LV Switch Board | Procure | #A6A6A7 | 36 | Main LV Switch Board (MSB) Delivered |  | 2025-03-08
Procurement MSFT OFCI ROJ COLO3 | C3 Main LV Switch Board | Procure | #A6A6A7 | 37 | Main LV Switch Board (MSB) Shipping/ ROJ | 2025-03-08 | 2025-03-08
Procurement MSFT OFCI ROJ COLO3 | C3 Medium Voltage Switchgear | Procure | #A6A6A7 | 42 | Medium Voltage Switchgear (MVS) (JD Power Sys) Delivered |  | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 Medium Voltage Switchgear | Procure | #A6A6A7 | 43 | Medium Voltage Switchgear (MVS) (JD Power Sys) Shipping/ ROJ | 2025-02-19 | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 Packaged Diesel Generator Set | Procure | #A6A6A7 | 46 | Packaged Diesel Generator Set (CAT Holt) Delivered |  | 2025-02-24
Procurement MSFT OFCI ROJ COLO3 | C3 Packaged Diesel Generator Set | Procure | #A6A6A7 | 47 | Packaged Diesel Generator Set (CAT Holt) Shipping/ ROJ | 2025-02-20 | 2025-02-24
Procurement MSFT OFCI ROJ COLO3 | C3 Pad Mounted Transformers | Procure | #A6A6A7 | 52 | Pad Mounted Transformers (XFM-TX) Delivered |  | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 Pad Mounted Transformers | Procure | #A6A6A7 | 53 | Pad Mounted Transformers (XFM-TX) Shipping/ ROJ | 2025-02-19 | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 PEMB Procurement (1st Del) | Procure | #A6A6A7 | 56 | PEMB Procurement (1st Del) (Nucor) Delivered |  | 2024-10-14
Procurement MSFT OFCI ROJ COLO3 | C3 PEMB Procurement (1st Del) | Procure | #A6A6A7 | 57 | PEMB Procurement (1st Del) (Nucor) Shipping/ ROJ | 2024-10-14 | 2024-10-14
Procurement MSFT OFCI ROJ COLO3 | C3 Power Distribution Units | Procure | #A6A6A7 | 60 | Power Distribution Units (PDU) Delivered |  | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 Power Distribution Units | Procure | #A6A6A7 | 61 | Power Distribution Units (PDU) Shipping/ ROJ | 2025-02-19 | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 Elec Performance Monitoring System | Procure | #A6A6A7 | 62 | Receive Elec. Performance Monitoring System (EPMS) (Schneider) (SOW Del Date- 4/30/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO3 | C3 Air Handling Units | Procure | #A6A6A7 | 63 | Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/04/24) | 2024-10-09
Procurement MSFT OFCI ROJ COLO3 | C3 Auto Transfer Control Panel | Procure | #A6A6A7 | 67 | Receive Auto Transfer Control Panel (TCP) (Del Date- 3/8/2025) | 2025-03-08
Procurement MSFT OFCI ROJ COLO3 | C3 Automatic Transfer Switches | Procure | #A6A6A7 | 69 | Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 4/30/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO3 | C3 Auxillary Power Distribution | Procure | #A6A6A7 | 72 | Receive Auxillary (Mech) Power Distribution Panels (ADP) (Del Date- 3/8/2025) | 2025-03-08
Procurement MSFT OFCI ROJ COLO3 | C3 Building Automation System | Procure | #A6A6A7 | 75 | Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 11/28/24) | 2024-11-30
Procurement MSFT OFCI ROJ COLO3 | C3 Busway / Busplugs | Procure | #A6A6A7 | 78 | Receive Busway / Busplugs (Starline Holding) (Del Date- 1/25/24) | 2024-04-09
Procurement MSFT OFCI ROJ COLO3 | C3 HAC/Racking | Procure | #A6A6A7 | 81 | Receive HAC/Racking (Tate Access) (SOW Del Date- 5/17/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO3 | C3 LV Switchgear | Procure | #A6A6A7 | 86 | Receive LV Switchgear (LVS) (Eaton) (SOW Del Date- 2/28/25) | 2025-02-28
Procurement MSFT OFCI ROJ COLO3 | C3 Main LV Switch Board | Procure | #A6A6A7 | 89 | Receive Main LV Switch Board (MSB) (SOW Del Date- 3/8/2025) | 2025-03-08
Procurement MSFT OFCI ROJ COLO3 | C3 Medium Voltage Switchgear | Procure | #A6A6A7 | 92 | Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 7/30/24) | 2024-10-15
Procurement MSFT OFCI ROJ COLO3 | C3 Packaged Diesel Generator Set | Procure | #A6A6A7 | 95 | Receive Packaged Diesel Generator Set (CAT Holt) (SOW Del Date- 5/14/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO3 | C3 Pad Mounted Transformers | Procure | #A6A6A7 | 98 | Receive Pad Mounted Transformers (XFM-TX) (Del Date- 7/30/2024) | 2024-11-15
Procurement MSFT OFCI ROJ COLO3 | C3 PEMB Procurement (1st Del) | Procure | #A6A6A7 | 100 | Receive PEMB Procurement (1st Del) (Nucor) (SOW Del Date-10/3/24) | 2024-10-14
Procurement MSFT OFCI ROJ COLO3 | C3 Power Distribution Units | Procure | #A6A6A7 | 101 | Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 4/30/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO3 | C3 Utility Pad Mount Switchgear | Procure | #A6A6A7 | 103 | Receive Utility Pad Mount Switchgear (Del Date- 7/30/2024) | 2024-10-23
Procurement MSFT OFCI ROJ COLO3 | C3 UPS System W / Battery | Procure | #A6A6A7 | 112 | UPS System w/ Battery (UPS) (Eaton) Delivered |  | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 UPS System W / Battery | Procure | #A6A6A7 | 113 | UPS System w/ Battery (UPS) (Eaton) Shipping/ ROJ | 2025-02-19 | 2025-02-23
Procurement MSFT OFCI ROJ COLO3 | C3 Utility Pad Mount Switchgear | Procure | #A6A6A7 | 114 | Utility Pad Mount Switchgear (UPM) Delivered | 2025-02-24 | 2025-02-28
Procurement MSFT OFCI ROJ COLO3 | C3 Utility Pad Mount Switchgear | Procure | #A6A6A7 | 115 | Utility Pad Mount Switchgear (UPM) Shipping/ ROJ | 2025-02-19 | 2025-02-23
Procurement MSFT OFCI ROJ COLO4 | C4 Air Handling Units | Procure | #A6A6A7 | 17 | Air Handling Units (AHU) (Stulz) Delivered |  | 2025-04-05
Procurement MSFT OFCI ROJ COLO4 | C4 Air Handling Units | Procure | #A6A6A7 | 18 | Air Handling Units (AHU) (Stulz) Shipping/ ROJ | 2025-04-01 | 2025-04-05
Procurement MSFT OFCI ROJ COLO4 | C4 Auto Transfer Control Panel | Procure | #A6A6A6 | 1 | Auto Transfer Control Panel (TCP) Delivered |  | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Auto Transfer Control Panel | Procure | #A6A6A6 | 2 | Auto Transfer Control Panel (TCP) Shipping/ROJ | 2025-03-30 | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Automatic Transfer Switches | Procure | #A6A6A6 | 3 | Automatic Transfer Switches (ATS) (Schneider) Delivered |  | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Automatic Transfer Switches | Procure | #A6A6A6 | 4 | Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ | 2025-03-26 | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Building Automation System | Procure | #A6A6A6 | 7 | Building Automation System (BAS) (Automated Logic Corp) Delivered |  | 2025-01-04
Procurement MSFT OFCI ROJ COLO4 | C4 Building Automation System | Procure | #A6A6A6 | 8 | Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ | 2024-12-29 | 2025-01-04
Procurement MSFT OFCI ROJ COLO4 | C4 Busway / Busplugs | Procure | #A6A6A6 | 10 | Busway / Busplugs (BSW) (Starline Holding) Delivered |  | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Busway / Busplugs | Procure | #A6A6A6 | 11 | Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ | 2025-03-26 | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Elec Performance Monitoring System | Procure | #A6A6A7 | 23 | Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Delivered |  | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Elec Performance Monitoring System | Procure | #A6A6A7 | 24 | Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Shipping/ROJ | 2025-03-26 | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 HAC/Racking | Procure | #A6A6A7 | 29 | HAC/Racking (Tate Access) Delivered |  | 2025-03-28
Procurement MSFT OFCI ROJ COLO4 | C4 HAC/Racking | Procure | #A6A6A7 | 30 | HAC/Racking (Tate Access) Shipping/ROJ | 2025-03-26 | 2025-03-28
Procurement MSFT OFCI ROJ COLO4 | C4 LV Switchgear | Procure | #A6A6A7 | 32 | LV Switchgear (Eaton) Delivered |  | 2025-03-02
Procurement MSFT OFCI ROJ COLO4 | C4 LV Switchgear | Procure | #A6A6A7 | 33 | LV Switchgear (Eaton) Shipping/ROJ | 2025-02-28 | 2025-03-02
Procurement MSFT OFCI ROJ COLO4 | C4 Main LV Switch Board | Procure | #A6A6A7 | 36 | Main LV Switch Board (MSB) Delivered |  | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Main LV Switch Board | Procure | #A6A6A7 | 37 | Main LV Switch Board (MSB) Shipping/ROJ | 2025-03-30 | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Auxillary Power Distribution | Procure | #A6A6A7 | 38 | Mech Power Distribution Panels (ADP) Delivered |  | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Auxillary Power Distribution | Procure | #A6A6A7 | 39 | Mech Power Distribution Panels (ADP) Shipping/ROJ | 2025-03-30 | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Medium Voltage Switchgear | Procure | #A6A6A7 | 40 | Medium Voltage Switchgear (JDC Power Sys) Delivered |  | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Medium Voltage Switchgear | Procure | #A6A6A7 | 41 | Medium Voltage Switchgear (JDC Power Sys) Shipping/ROJ | 2025-03-26 | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Packaged Diesel Generator Set | Procure | #A6A6A7 | 48 | Packaged Diesel Generator Set (GEN) (CAT Holt) Delivered |  | 2025-04-10
Procurement MSFT OFCI ROJ COLO4 | C4 Packaged Diesel Generator Set | Procure | #A6A6A7 | 49 | Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ | 2025-04-06 | 2025-04-10
Procurement MSFT OFCI ROJ COLO4 | C4 Pad Mounted Transformers | Procure | #A6A6A7 | 54 | Pad Mounted Transformers (XMF) Delivered |  | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Pad Mounted Transformers | Procure | #A6A6A7 | 55 | Pad Mounted Transformers (XMF) Shipping/ROJ | 2025-03-26 | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Power Distribution Units | Procure | #A6A6A7 | 58 | Power Distribution Units (PDU) (ABB) Delivered |  | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Power Distribution Units | Procure | #A6A6A7 | 59 | Power Distribution Units (PDU) (ABB) Shipping/ROJ | 2025-03-26 | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Air Handling Units | Procure | #A6A6A7 | 65 | Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/9/24) | 2024-09-30
Procurement MSFT OFCI ROJ COLO4 | C4 Auto Transfer Control Panel | Procure | #A6A6A7 | 68 | Receive Auto Transfer Control Panel (TCP) (Del Date-3/30/2025) | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Automatic Transfer Switches | Procure | #A6A6A7 | 70 | Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 6/30/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO4 | C4 Building Automation System | Procure | #A6A6A7 | 74 | Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 12/29/24) | 2024-12-29
Procurement MSFT OFCI ROJ COLO4 | C4 Busway / Busplugs | Procure | #A6A6A7 | 76 | Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 2/23/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO4 | C4 Elec Performance Monitoring System | Procure | #A6A6A7 | 79 | Receive Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) (SOW Del Date- 6/30/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO4 | C4 HAC/Racking | Procure | #A6A6A7 | 82 | Receive HAC/Racking (Tate Access) (SOW Del Date- 6/18/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO4 | C4 LV Switchgear | Procure | #A6A6A7 | 84 | Receive LV Switchgear (Eaton) (SOW Del Date- 2/28/25) | 2025-02-28
Procurement MSFT OFCI ROJ COLO4 | C4 Main LV Switch Board | Procure | #A6A6A7 | 87 | Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Auxillary Power Distribution | Procure | #A6A6A7 | 90 | Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Medium Voltage Switchgear | Procure | #A6A6A7 | 93 | Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 8/30/24) | 2024-10-23
Procurement MSFT OFCI ROJ COLO4 | C4 Packaged Diesel Generator Set | Procure | #A6A6A7 | 96 | Receive Packaged Diesel Generator Set (GEN) (CAT Holt) (SOW Del Date- 6/4/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO4 | C4 Utility Pad Mount Switchgear | Procure | #A6A6A7 | 105 | Receive Utility Pad Mount Switchgear (UPM) (Del Date 8/30/2024) | 2024-10-23
Procurement MSFT OFCI ROJ COLO4 | C4 UPS System W / Battery | Procure | #A6A6A7 | 106 | Received SUB Warehouse 11/23/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 11/11/23) | 2024-09-02
Procurement MSFT OFCI ROJ COLO4 | C4 Pad Mounted Transformers | Procure | #A6A6A7 | 108 | Reveive Pad Mounted Transformers (XMF) (Del Date 8/30/2024) | 2024-11-15
Procurement MSFT OFCI ROJ COLO4 | C4 Power Distribution Units | Procure | #A6A6A7 | 109 | Reveive Power Distribution Units (PDU) (ABB) (SOW Del Date- 7/12/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO4 | C4 UPS System W / Battery | Procure | #A6A6A7 | 110 | Static UPS System W/Batt (UPS) (Eaton) Delivered |  | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 UPS System W / Battery | Procure | #A6A6A7 | 111 | Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ | 2025-03-26 | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Utility Pad Mount Switchgear | Procure | #A6A6A7 | 114 | Utility Pad Mount Switchgear (UPM) Delivered |  | 2025-03-30
Procurement MSFT OFCI ROJ COLO4 | C4 Utility Pad Mount Switchgear | Procure | #A6A6A7 | 115 | Utility Pad Mount Switchgear (UPM) Shipping/ROJ | 2025-03-26 | 2025-03-30
Procurement MSFT OFCI ROJ COLO5 | C5 Air Handling Units | Procure | #A6A6A7 | 17 | Air Handling Units (AHU) (Stulz) Delivered |  | 2025-05-11
Procurement MSFT OFCI ROJ COLO5 | C5 Air Handling Units | Procure | #A6A6A7 | 18 | Air Handling Units (AHU) (Stulz) Shipping/ROJ | 2025-05-11 | 2025-05-11
Procurement MSFT OFCI ROJ COLO5 | C5 Auto Transfer Control Panel | Procure | #A6A6A6 | 1 | Auto Transfer Control Panel (TCP) Delivered |  | 2025-04-04
Procurement MSFT OFCI ROJ COLO5 | C5 Auto Transfer Control Panel | Procure | #A6A6A6 | 2 | Auto Transfer Control Panel (TCP) Shipping/ROJ | 2025-03-30 | 2025-04-04
Procurement MSFT OFCI ROJ COLO5 | C5 Automatic Transfer Switches | Procure | #A6A6A6 | 3 | Automatic Transfer Switches (ATS) (Schneider) Delivered |  | 2025-04-20
Procurement MSFT OFCI ROJ COLO5 | C5 Automatic Transfer Switches | Procure | #A6A6A6 | 4 | Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ | 2025-04-20 | 2025-04-20
Procurement MSFT OFCI ROJ COLO5 | C5 Building Automation System | Procure | #A6A6A6 | 7 | Building Automation System (BAS) (Automated Logic Corp) Delivered |  | 2025-02-02
Procurement MSFT OFCI ROJ COLO5 | C5 Building Automation System | Procure | #A6A6A6 | 8 | Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ | 2025-01-28 | 2025-02-02
Procurement MSFT OFCI ROJ COLO5 | C5 Busway / Busplugs | Procure | #A6A6A6 | 10 | Busway / Busplugs (BSW) (Starline Holding) Delivered |  | 2025-05-03
Procurement MSFT OFCI ROJ COLO5 | C5 Busway / Busplugs | Procure | #A6A6A6 | 11 | Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ | 2025-04-29 | 2025-05-03
Procurement MSFT OFCI ROJ COLO5 | C5 Elec Performance Monitoring System | Procure | #A6A6A7 | 25 | Elec. Performance Monitoring Syst. (EPMS) (Schneider) Delivered |  | 2025-04-20
Procurement MSFT OFCI ROJ COLO5 | C5 Elec Performance Monitoring System | Procure | #A6A6A7 | 26 | Elec. Performance Monitoring Syst. (EPMS) (Schneider) Shipping/ROJ | 2025-04-20 | 2025-04-20
Procurement MSFT OFCI ROJ COLO5 | C5 HAC/Racking | Procure | #A6A6A7 | 29 | HAC/Racking (Tate Access) Delivered |  | 2025-04-28
Procurement MSFT OFCI ROJ COLO5 | C5 HAC/Racking | Procure | #A6A6A7 | 30 | HAC/Racking (Tate Access) Shipping/ROJ | 2025-04-25 | 2025-04-28
Procurement MSFT OFCI ROJ COLO5 | C5 LV Switchgear | Procure | #A6A6A7 | 32 | LV Switchgear (Eaton) Delivered |  | 2025-04-03
Procurement MSFT OFCI ROJ COLO5 | C5 LV Switchgear | Procure | #A6A6A7 | 33 | LV Switchgear (Eaton) Shipping/ROJ | 2025-03-30 | 2025-04-03
Procurement MSFT OFCI ROJ COLO5 | C5 Main LV Switch Board | Procure | #A6A6A7 | 36 | Main LV Switch Board (MSB) Delivered |  | 2025-04-04
Procurement MSFT OFCI ROJ COLO5 | C5 Main LV Switch Board | Procure | #A6A6A7 | 37 | Main LV Switch Board (MSB) Shipping/ROJ | 2025-03-30 | 2025-04-04
Procurement MSFT OFCI ROJ COLO5 | C5 Auxillary Power Distribution | Procure | #A6A6A7 | 38 | Mech Power Distribution Panels (ADP) Delivered |  | 2025-04-04
Procurement MSFT OFCI ROJ COLO5 | C5 Auxillary Power Distribution | Procure | #A6A6A7 | 39 | Mech Power Distribution Panels (ADP) Shipping/ROJ | 2025-03-30 | 2025-04-04
Procurement MSFT OFCI ROJ COLO5 | C5 Medium Voltage Switchgear | Procure | #A6A6A7 | 44 | Medium Voltage Switchgear (MVS) (JDC Power Sys) Delivered |  | 2025-05-03
Procurement MSFT OFCI ROJ COLO5 | C5 Medium Voltage Switchgear | Procure | #A6A6A7 | 45 | Medium Voltage Switchgear (MVS) (JDC Power Sys) Shipping/ROJ | 2025-04-29 | 2025-05-03
Procurement MSFT OFCI ROJ COLO5 | C5 Packaged Diesel Generator Set | Procure | #A6A6A7 | 50 | Packaged Diesel Generator Set (GPC) (CAT Holt) Delivered |  | 2025-05-15
Procurement MSFT OFCI ROJ COLO5 | C5 Packaged Diesel Generator Set | Procure | #A6A6A7 | 51 | Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ | 2025-05-11 | 2025-05-15
Procurement MSFT OFCI ROJ COLO5 | C5 Pad Mounted Transformers | Procure | #A6A6A7 | 54 | Pad Mounted Transformers (XMF) Delivered |  | 2025-05-03
Procurement MSFT OFCI ROJ COLO5 | C5 Pad Mounted Transformers | Procure | #A6A6A7 | 55 | Pad Mounted Transformers (XMF) Shipping/ROJ | 2025-04-29 | 2025-05-03
Procurement MSFT OFCI ROJ COLO5 | C5Power Distribution Units | Procure | #A6A6A7 | 58 | Power Distribution Units (PDU) (ABB) Delivered |  | 2025-05-07
Procurement MSFT OFCI ROJ COLO5 | C5Power Distribution Units | Procure | #A6A6A7 | 59 | Power Distribution Units (PDU) (ABB) Shipping/ROJ | 2025-05-03 | 2025-05-07
Procurement MSFT OFCI ROJ COLO5 | C5 Air Handling Units | Procure | #A6A6A7 | 64 | Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/16/24) | 2024-09-12
Procurement MSFT OFCI ROJ COLO5 | C5 Auto Transfer Control Panel | Procure | #A6A6A7 | 66 | Receive Auto Transfer Control Panel (TCP) (Del Date 3/30/2025) | 2025-03-30
Procurement MSFT OFCI ROJ COLO5 | C5 Automatic Transfer Switches | Procure | #A6A6A7 | 71 | Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 8/31/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO5 | C5 Building Automation System | Procure | #A6A6A7 | 73 | Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 1/28/25) | 2025-01-28
Procurement MSFT OFCI ROJ COLO5 | C5 Busway / Busplugs | Procure | #A6A6A7 | 77 | Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 4/23/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO5 | C5 Elec Performance Monitoring System | Procure | #A6A6A7 | 80 | Receive Elec. Performance Monitoring Syst. (EPMS) (Schneider) (SOW Del Date- 8/31/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO5 | C5 HAC/Racking | Procure | #A6A6A7 | 83 | Receive HAC/Racking (Tate Access) (SOW Del Date- 7/3/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO5 | C5 LV Switchgear | Procure | #A6A6A7 | 85 | Receive LV Switchgear (Eaton) (SOW Del Date- 3/30/25) | 2025-03-30
Procurement MSFT OFCI ROJ COLO5 | C5 Main LV Switch Board | Procure | #A6A6A7 | 88 | Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) | 2025-03-30
Procurement MSFT OFCI ROJ COLO5 | C5 Auxillary Power Distribution | Procure | #A6A6A7 | 91 | Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) | 2025-03-30
Procurement MSFT OFCI ROJ COLO5 | C5 Medium Voltage Switchgear | Procure | #A6A6A7 | 94 | Receive Medium Voltage Switchgear (MVS) (JDC Power Sys) (SOW Del Date- 10/30/24) | 2024-10-30
Procurement MSFT OFCI ROJ COLO5 | C5 Packaged Diesel Generator Set | Procure | #A6A6A7 | 97 | Receive Packaged Diesel Generator Set (GPC) (CAT Holt) (SOW Del Date- 6/26/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO5 | C5 Pad Mounted Transformers | Procure | #A6A6A7 | 99 | Receive Pad Mounted Transformers (XMF) (Del Date 10/30/2024) | 2024-11-15
Procurement MSFT OFCI ROJ COLO5 | C5Power Distribution Units | Procure | #A6A6A7 | 102 | Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 9/30/24) | 2024-11-15
Procurement MSFT OFCI ROJ COLO5 | C5 Utility Pad Mount Switchgear | Procure | #A6A6A7 | 104 | Receive Utility Pad Mount Switchgear (UPM) (Del Date 10/30/2024) | 2024-10-23
Procurement MSFT OFCI ROJ COLO5 | C5 UPS System W / Battery | Procure | #A6A6A7 | 107 | Received SUB Warehouse 12/28/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 12/11/23) | 2024-09-02
Procurement MSFT OFCI ROJ COLO5 | C5 UPS System W / Battery | Procure | #A6A6A7 | 110 | Static UPS System W/Batt (UPS) (Eaton) Delivered |  | 2025-03-30
Procurement MSFT OFCI ROJ COLO5 | C5 UPS System W / Battery | Procure | #A6A6A7 | 111 | Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ | 2025-03-26 | 2025-03-30
Procurement MSFT OFCI ROJ COLO5 | C5 Utility Pad Mount Switchgear | Procure | #A6A6A7 | 114 | Utility Pad Mount Switchgear (UPM) Delivered |  | 2025-05-03
Procurement MSFT OFCI ROJ COLO5 | C5 Utility Pad Mount Switchgear | Procure | #A6A6A7 | 115 | Utility Pad Mount Switchgear (UPM) Shipping/ROJ | 2025-04-29 | 2025-05-03
Site Prep/ Mobilization | Site Prep/ Mobilization | Earthwork | #A1490E | U2 | Fine Grading Building Pad | 2024-08-19 | 2024-09-04
Site Prep/ Mobilization | Site Prep/ Mobilization | CLAYCO | #C00000 | CT | Set-Up Trailers & Install Temp Utilities | 2024-07-25 | 2024-09-16
Site Prep/ Mobilization | Site Prep/ Mobilization | CLAYCO | #C00000 | CM | Site Mobilization | 2024-07-24
Site Utilities | Under Building Pad | Earthwork | #A1490E | U1 | Backfill after UG work (MV / Telecom) | 2024-11-05 | 2024-11-15
Site Utilities | Overall | Telecom | #E3A267 | T1 | Install Deep Telecom | 2024-10-08 | 2024-11-14
Site Utilities | Overall | Electrical | #F3F0A8 | E18 | Install MV Ductbanks | 2024-10-25 | 2024-11-22
Site Utilities | Overall | Plumbing | #30585A | P1 | Install Sanitary Lines | 2024-11-04 | 2024-12-09
Site Utilities | Overall | Plumbing | #30585A | P2 | Install Storm Lines | 2024-10-09 | 2024-12-06
Site Utilities | Under Building Pad | Electrical | #F3F0A8 | E17 | Install UG Electrical / UPM Crossing (under Building Pad) | 2024-10-25 | 2024-11-13
Site Utilities | Under Building Pad | Telecom | #E3A267 | T1 | Install UG Telecom (under Building Pad) | 2024-10-08 | 2024-10-10
Site Utilities | Overall | Plumbing | #30585A | P3 | Install Water Line | 2024-11-04 | 2024-12-26
Site Utilities | Overall | Electrical | #F3F0A8 | E16 | Permanent Power | 2025-05-05

## CFA - Schedule
|  | 2024 | [281 empty] | 2025
|  | Mar | [6 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov
|  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
phase | location | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Procurement | Early Awards | Jun 07: 19; Jun 08: 19; Jun 09: 19; Jun 10: 19; Jun 11: 19; Jun 12: 19; Jun 13: 19; Jun 14: 19; Jun 15: 19; Jun 16: 19; Jun 17: 19; Jun 18: 19; Jun 19: 19; Jun 20: 19; Jun 21: 19; Jun 22: 19; Jun 23: 19; Jun 24: 19; Jun 25: 19; Jun 26: 19; Jun 27: 19; Jun 28: 19; Jun 29: 19; Jun 30: 19; Jul 01: 19; Jul 02: 19; Jul 03: 19; Jul 04: 19; Jul 05: 19; Jul 06: 19; Jul 07: 19; Jul 08: 19; Jul 09: 19; Jul 10: 19; Jul 11: 19; Jul 12: 19; Jul 13: 19; Jul 14: 19; Jul 15: 19; Jul 16: 19; Jul 17: 19; Jul 18: 19; Jul 19: 19; Jul 20: 19; Jul 21: 19; Jul 22: 19; Jul 23: 19; Jul 24: 19; Jul 25: 19; Jul 26: 19; Jul 27: 19; Jul 28: 19; Jul 29: 19; Jul 30: 19; Jul 31: 19; Aug 01: 19; Aug 02: 19; Aug 03: 19; Aug 04: 19; Aug 05: 19; Aug 06: 19; Aug 07: 19; Aug 08: 19; Aug 09: 19; Aug 10: 19; Aug 11: 19; Aug 12: 19; Aug 13: 19; Aug 14: 19; Aug 15: 19; Aug 16: 19; Aug 17: 19; Aug 18: 19; Aug 19: 19; Aug 20: 19; Aug 21: 19; Aug 22: 19; Aug 23: 19; Aug 24: 19; Aug 25: 19; Aug 26: 19; Aug 27: 19; Aug 28: 19; Aug 29: 19; Aug 30: 19; Aug 31: 19; Sep 01: 19; Sep 02: 19; Sep 03: 19; Sep 04: 19; Sep 05: 19; Sep 06: 19; Sep 07: 19
[76 empty] | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
Procurement MSFT OFCI ROJ CFCI (Critical Only) | CFCI (Critical Only) | Aug 07: 117; Aug 08: 117; Aug 09: 117; Aug 10: 117; Aug 11: 117; Aug 12: 117; Aug 13: 117; Aug 14: 117; Aug 15: 117; Aug 16: 117; Aug 17: 117; Aug 18: 117; Aug 19: 117; Aug 20: 117; Aug 21: 117; Aug 22: 117; Aug 23: 117; Aug 24: 117; Aug 25: 117; Aug 26: 117; Aug 27: 117; Aug 28: 117; Aug 29: 117; Aug 30: 117; Aug 31: 117; Sep 01: 117; Sep 02: 117; Sep 03: 117; Sep 04: 117; Sep 05: 117; Sep 06: 117; Sep 07: 117; Sep 08: 117; Sep 09: 117; Sep 10: 117; Sep 11: 117; Sep 12: 117; Sep 13: 117; Sep 14: 117; Sep 15: 117; Sep 16: 117; Sep 17: 117; Sep 18: 117; Sep 19: 117; Sep 20: 117; Sep 21: 117; Sep 22: 117; Sep 23: 117; Sep 24: 117; Sep 25: 117; Sep 26: 117; Sep 27: 117; Sep 28: 117; Sep 29: 117; Sep 30: 117; Oct 01: 117; Oct 02: 117; Oct 03: 117; Oct 04: 117; Oct 05: 117; Oct 06: 117; Oct 07: 117; Oct 08: 117; Oct 09: 117; Oct 10: 117; Oct 11: 117; Oct 12: 117; Oct 13: 117; Oct 14: 117; Oct 15: 117; Oct 16: 117; Oct 17: 117; Oct 18: 117; Oct 19: 117; Oct 20: 117; Oct 21: 117; Oct 22: 117; Oct 23: 117; Oct 24: 117; Oct 25: 117; Oct 26: 117; Oct 27: 117; Oct 28: 117; Oct 29: 117; Oct 30: 117; Oct 31: 117; Nov 01: 117; Nov 02: 117; Nov 03: 117; Nov 04: 117; Nov 05: 117; Nov 06: 117; Nov 07: 117; Nov 08: 117; Nov 09: 117; Nov 10: 117; Nov 11: 117; Nov 12: 117; Nov 13: 117; Nov 14: 117; Nov 15: 117; Nov 16: 117; Nov 17: 117; Nov 18: 117; Nov 19: 117; Nov 20: 117; Nov 21: 117; Nov 22: 117; Nov 23: 117; Nov 24: 117; Nov 25: 117; Nov 26: 117; Nov 27: 117; Nov 28: 117; Nov 29: 117; Nov 30: 117; Dec 01: 117; Dec 02: 117; Dec 03: 117; Dec 04: 117; Dec 05: 117; Dec 06: 117; Dec 07: 117; Dec 08: 117; Dec 09: 117; Dec 10: 117; Dec 11: 117; Dec 12: 117; Dec 13: 117; Dec 14: 117; Dec 15: 117; Dec 16: 117; Dec 17: 117; Dec 18: 117; Dec 19: 117; Dec 20: 117; Dec 21: 117; Dec 22: 117; Dec 23: 117; Dec 24: 117; Dec 25: 117; Dec 26: 117; Dec 27: 117; Dec 28: 117; Dec 29: 117; Dec 30: 117; Dec 31: 117; Jan 01: 117; Jan 02: 117; Jan 03: 117; Jan 04: 117; Jan 05: 117; Jan 06: 117; Jan 07: 117; Jan 08: 117; Jan 09: 117; Jan 10: 117; Jan 11: 117; Jan 12: 117; Jan 13: 117; Jan 14: 117; Jan 15: 117; Jan 16: 117; Jan 17: 117; Jan 18: 117; Jan 19: 117; Jan 20: 117; Jan 21: 117; Jan 22: 117; Jan 23: 117; Jan 24: 117; Jan 25: 117; Jan 26: 117; Jan 27: 117; Jan 28: 117; Jan 29: 117; Jan 30: 117; Jan 31: 117; Feb 01: 117; Feb 02: 117; Feb 03: 117; Feb 04: 117; Feb 05: 117; Feb 06: 117; Feb 07: 117; Feb 08: 117; Feb 09: 117; Feb 10: 117; Feb 11: 117; Feb 12: 117; Feb 13: 117; Feb 14: 117; Feb 15: 117; Feb 16: 117; Feb 17: 117; Feb 18: 117; Feb 19: 117; Feb 20: 117; Feb 21: 117; Feb 22: 117; Feb 23: 117; Feb 24: 117; Feb 25: 117; Feb 26: 117; Feb 27: 117; Feb 28: 117; Mar 01: 117; Mar 02: 117; Mar 03: 117; Mar 04: 117; Mar 05: 117; Mar 06: 117; Mar 07: 117; Mar 08: 117; Mar 09: 117; Mar 10: 117; Mar 11: 117; Mar 12: 117; Mar 13: 117; Mar 14: 117; Mar 15: 117; Mar 16: 117; Mar 17: 117; Mar 18: 117; Mar 19: 117; Mar 20: 117; Mar 21: 117; Mar 22: 117; Mar 23: 117; Mar 24: 117; Mar 25: 117; Mar 26: 117; Mar 27: 117; Mar 28: 117; Mar 29: 117; Mar 30: 117; Mar 31: 117; Apr 01: 117; Apr 02: 117; Apr 03: 117; Apr 04: 117; Apr 05: 117; Apr 06: 117; Apr 07: 117; Apr 08: 117; Apr 09: 117; Apr 10: 117; Apr 11: 117; Apr 12: 117; Apr 13: 117; Apr 14: 117; Apr 15: 117; Apr 16: 117; Apr 17: 117; Apr 18: 117; Apr 19: 117; Apr 20: 117; Apr 21: 117; Apr 22: 117; Apr 23: 117; Apr 24: 117; Apr 25: 117; Apr 26: 117; Apr 27: 117; Apr 28: 117; Apr 29: 117; Apr 30: 117; May 01: 117; May 02: 117; May 03: 117; May 04: 117; May 05: 117; May 06: 117; May 07: 117; May 08: 117; May 09: 117; May 10: 117; May 11: 117; May 12: 117; May 13: 117; May 14: 117; May 15: 117; May 16: 117; May 17: 117; May 18: 117; May 19: 117; May 20: 117; May 21: 117; May 22: 117; May 23: 117; May 24: 117; May 25: 117; May 26: 117; May 27: 117; May 28: 117; May 29: 117; May 30: 117; May 31: 117; Jun 01: 117; Jun 02: 117; Jun 03: 117; Jun 04: 117; Jun 05: 117; Jun 06: 117; Jun 07: 117; Jun 08: 117; Jun 09: 117; Jun 10: 117; Jun 11: 117; Jun 12: 117; Jun 13: 117; Jun 14: 117; Jun 15: 117; Jun 16: 117; Jun 17: 117; Jun 18: 117
[137 empty] | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116 | 116
[147 empty] | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
[237 empty] | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
[237 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Procurement MSFT OFCI ROJ COLO3 | C3 Air Handling Units | Oct 09: 63; Mar 09: 18; Mar 10: 18; Mar 11: 18; Mar 12: 18; Mar 13: 18
17
C3 Auto Transfer Control Panel | bar: Mar 08
67
| C3 Automatic Transfer Switches | Nov 15: 69; Feb 19: 4; Feb 20: 4; Feb 21: 4; Feb 22: 4; Feb 23: 4
3
| C3 Auxillary Power Distribution | Mar 08: 5
72
| C3 Building Automation System | Nov 30: 75; Feb 19: 15; Feb 20: 15; Feb 21: 15; Feb 22: 15; Feb 23: 15
9
| C3 Busway / Busplugs | Apr 09: 78; Feb 19: 13; Feb 20: 13; Feb 21: 13; Feb 22: 13; Feb 23: 13
12
| C3 Elec Performance Monitoring System | Nov 15: 62; Feb 19: 28; Feb 20: 28; Feb 21: 28; Feb 22: 28; Feb 23: 28
27
| C3 HAC/Racking | Nov 15: 81; Feb 19: 30; Feb 20: 30; Feb 21: 30
29
| C3 LV Switchgear | Feb 28: 86; Mar 04: 34
[342 empty] | 35 | 35 | 35 | 35 | 35
| C3 Main LV Switch Board | Mar 08: 36
89
| C3 Medium Voltage Switchgear | Oct 15: 92; Feb 19: 43; Feb 20: 43; Feb 21: 43; Feb 22: 43; Feb 23: 43
42
| C3 PEMB Procurement (1st Del) | Oct 14: 56
100
| C3 Packaged Diesel Generator Set | Nov 15: 95; Feb 20: 47; Feb 21: 47; Feb 22: 47; Feb 23: 47; Feb 24: 47
46
| C3 Pad Mounted Transformers | Nov 15: 98; Feb 19: 53; Feb 20: 53; Feb 21: 53; Feb 22: 53; Feb 23: 53
52
| C3 Power Distribution Units | Nov 15: 101; Feb 19: 61; Feb 20: 61; Feb 21: 61; Feb 22: 61; Feb 23: 61
60
| C3 UPS System W / Battery | Sep 02: 16; Feb 19: 113; Feb 20: 113; Feb 21: 113; Feb 22: 113; Feb 23: 113
112
| C3 Utility Pad Mount Switchgear | Oct 23: 103; Feb 19: 115; Feb 20: 115; Feb 21: 115; Feb 22: 115; Feb 23: 115; Feb 24: 114; Feb 25: 114; Feb 26: 114; Feb 27: 114; Feb 28: 114
Procurement MSFT OFCI ROJ COLO4 | C4 Air Handling Units | Sep 30: 65; Apr 01: 18; Apr 02: 18; Apr 03: 18; Apr 04: 18; Apr 05: 18
17
C4 Auto Transfer Control Panel | bar: Mar 30
68
| C4 Automatic Transfer Switches | Nov 15: 70; Mar 26: 4; Mar 27: 4; Mar 28: 4; Mar 29: 4; Mar 30: 4
3
| C4 Auxillary Power Distribution | Mar 30: 38
90
| C4 Building Automation System | Dec 29: 74; Jan 04: 7
[281 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8
| C4 Busway / Busplugs | Nov 15: 76; Mar 26: 11; Mar 27: 11; Mar 28: 11; Mar 29: 11; Mar 30: 11
10
| C4 Elec Performance Monitoring System | Nov 15: 79; Mar 26: 24; Mar 27: 24; Mar 28: 24; Mar 29: 24; Mar 30: 24
23
| C4 HAC/Racking | Nov 15: 82; Mar 26: 30; Mar 27: 30; Mar 28: 30
29
| C4 LV Switchgear | Feb 28: 84; Mar 02: 32
[342 empty] | 33 | 33 | 33
| C4 Main LV Switch Board | Mar 30: 36
87
| C4 Medium Voltage Switchgear | Oct 23: 93; Mar 26: 41; Mar 27: 41; Mar 28: 41; Mar 29: 41; Mar 30: 41
40
| C4 Packaged Diesel Generator Set | Nov 15: 96; Apr 06: 49; Apr 07: 49; Apr 08: 49; Apr 09: 49; Apr 10: 49
48
| C4 Pad Mounted Transformers | Nov 15: 108; Mar 26: 55; Mar 27: 55; Mar 28: 55; Mar 29: 55; Mar 30: 55
54
| C4 Power Distribution Units | Nov 15: 109; Mar 26: 59; Mar 27: 59; Mar 28: 59; Mar 29: 59; Mar 30: 59
58
| C4 UPS System W / Battery | Sep 02: 106; Mar 26: 111; Mar 27: 111; Mar 28: 111; Mar 29: 111; Mar 30: 111
110
| C4 Utility Pad Mount Switchgear | Oct 23: 105; Mar 26: 115; Mar 27: 115; Mar 28: 115; Mar 29: 115; Mar 30: 115
114
Procurement MSFT OFCI ROJ COLO5 | C5 Air Handling Units | Sep 12: 64; May 11: 17
18
| C5 Auto Transfer Control Panel | Mar 30: 66; Apr 04: 1
[372 empty] | 2 | 2 | 2 | 2 | 2 | 2
| C5 Automatic Transfer Switches | Nov 15: 71; Apr 20: 3
4
| C5 Auxillary Power Distribution | Mar 30: 91; Apr 04: 38
[372 empty] | 39 | 39 | 39 | 39 | 39 | 39
| C5 Building Automation System | Jan 28: 73; Feb 02: 7
[311 empty] | 8 | 8 | 8 | 8 | 8 | 8
| C5 Busway / Busplugs | Nov 15: 77; Apr 29: 11; Apr 30: 11; May 01: 11; May 02: 11; May 03: 11
10
| C5 Elec Performance Monitoring System | Nov 15: 80; Apr 20: 25
26
| C5 HAC/Racking | Nov 15: 83; Apr 25: 30; Apr 26: 30; Apr 27: 30; Apr 28: 30
29
| C5 LV Switchgear | Mar 30: 85; Apr 03: 32
[372 empty] | 33 | 33 | 33 | 33 | 33
| C5 Main LV Switch Board | Mar 30: 88; Apr 04: 36
[372 empty] | 37 | 37 | 37 | 37 | 37 | 37
| C5 Medium Voltage Switchgear | Oct 30: 94; Apr 29: 45; Apr 30: 45; May 01: 45; May 02: 45; May 03: 45
44
| C5 Packaged Diesel Generator Set | Nov 15: 97; May 11: 51; May 12: 51; May 13: 51; May 14: 51; May 15: 51
50
| C5 Pad Mounted Transformers | Nov 15: 99; Apr 29: 55; Apr 30: 55; May 01: 55; May 02: 55; May 03: 55
54
| C5 UPS System W / Battery | Sep 02: 107; Mar 26: 111; Mar 27: 111; Mar 28: 111; Mar 29: 111; Mar 30: 111
110
| C5 Utility Pad Mount Switchgear | Oct 23: 104; Apr 29: 115; Apr 30: 115; May 01: 115; May 02: 115; May 03: 115
114
| C5Power Distribution Units | Nov 15: 102; May 03: 59; May 04: 59; May 05: 59; May 06: 59; May 07: 59
58
Preconstruction | BIM | Jul 18: NaN; Jul 19: NaN; Jul 20: NaN; Jul 21: NaN; Jul 22: NaN; Jul 23: NaN; Jul 24: NaN; Jul 25: NaN; Jul 26: NaN; Jul 27: NaN; Jul 28: NaN; Jul 29: NaN; Jul 30: NaN; Jul 31: NaN; Aug 01: NaN; Aug 02: NaN; Aug 03: NaN; Aug 04: NaN; Aug 05: NaN; Aug 06: NaN; Aug 07: NaN; Aug 08: NaN; Aug 09: NaN; Aug 10: NaN; Aug 11: NaN; Aug 12: NaN; Aug 13: NaN; Aug 14: NaN; Aug 15: NaN; Aug 16: NaN; Aug 17: NaN; Aug 18: NaN; Aug 19: NaN; Aug 20: NaN; Aug 21: NaN; Aug 22: NaN; Aug 23: NaN; Aug 24: NaN; Aug 25: NaN; Aug 26: NaN; Aug 27: NaN; Aug 28: NaN; Aug 29: NaN; Aug 30: NaN; Aug 31: NaN; Sep 01: NaN; Sep 02: NaN; Sep 03: NaN; Sep 04: NaN; Sep 05: NaN; Sep 06: NaN; Sep 07: NaN; Sep 08: NaN; Sep 09: NaN; Sep 10: NaN; Sep 11: NaN; Sep 12: NaN; Sep 13: NaN; Sep 14: NaN; Sep 15: NaN; Sep 16: NaN; Sep 17: NaN; Sep 18: NaN; Sep 19: NaN; Sep 20: NaN; Sep 21: NaN; Sep 22: NaN; Sep 23: NaN; Sep 24: NaN; Sep 25: NaN; Sep 26: NaN; Sep 27: 0.1; Sep 28: 0.1; Sep 29: 0.1; Sep 30: 0.1; Oct 01: 0.1; Oct 02: 0.1; Oct 03: 0.1; Oct 04: 0.1; Oct 05: 0.1; Oct 06: 0.1; Oct 07: 0.1; Oct 08: 0.1; Oct 09: 0.1; Oct 10: 0.1; Oct 11: 0.1; Oct 12: 0.1; Oct 13: 0.1; Oct 14: 0.1; Oct 15: 0.1; Oct 16: 0.1; Oct 17: 0.1; Oct 18: 0.1; Oct 19: 0.1; Oct 20: 0.1; Oct 21: 0.1; Oct 22: 0.1; Oct 23: 0.1; Oct 24: 0.1; Oct 25: 0.1; Oct 26: 0.1; Oct 27: 0.1; Oct 28: 0.1; Oct 29: 0.1; Oct 30: 0.1; Oct 31: 0.1; Nov 01: 0.1; Nov 02: 0.1; Nov 03: 0.1; Nov 04: 0.1; Nov 05: 0.1; Nov 06: 0.1; Nov 07: 0.1; Nov 08: 0.1; Nov 09: 0.1; Nov 10: 0.1; Nov 11: 0.1; Nov 12: 0.1; Nov 13: 0.1; Nov 14: 0.1; Nov 15: 0.1; Nov 16: 0.1; Nov 17: 0.1; Nov 18: 0.1; Nov 19: 0.1; Nov 20: 0.1; Nov 21: 0.1; Nov 22: 0.1; Nov 23: 0.1; Nov 24: 0.1; Nov 25: 0.1; Nov 26: 0.1; Nov 27: 0.1; Nov 28: 0.1; Nov 29: 0.1; Nov 30: 0.1; Dec 01: 0.1; Dec 02: 0.1; Dec 03: 0.1; Dec 04: 0.1; Dec 05: 0.1; Dec 06: 0.1; Dec 07: 0.1; Dec 08: 0.1; Dec 09: 0.1; Dec 10: 0.1; Dec 11: 0.1; Dec 12: 0.1; Dec 13: 0.1; Dec 14: 0.1; Dec 15: 0.1; Dec 16: 0.1; Dec 17: 0.1; Dec 18: 0.1; Dec 19: 0.1; Dec 20: 0.1; Dec 21: 0.1; Dec 22: 0.1; Dec 23: 0.1
| RFP / PSR | Mar 25: PC3; Mar 26: PC3; Mar 27: PC3; Mar 28: PC3; Mar 29: PC3; Mar 30: PC3; Mar 31: PC3; Apr 01: PC3; Apr 02: PC3; Apr 03: PC3; Apr 04: PC3; Apr 05: PC3; Apr 06: PC3; Apr 07: PC3; Apr 08: PC3; Apr 09: PC3; Apr 10: PC3; Apr 11: PC3; Apr 12: PC3; Jun 06: PC1; Sep 30: PC2
Site Prep/ Mobilization | Site Prep/ Mobilization | bar: Jul 24 to Sep 16
[149 empty] | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2 | U2
Foundations | Foundations | bar: Sep 19 to Nov 12
Site Utilities | Overall | Oct 08: T1; Oct 09: T1; Oct 10: T1; Oct 11: T1; Oct 12: T1; Oct 13: T1; Oct 14: T1; Oct 15: T1; Oct 16: T1; Oct 17: T1; Oct 18: T1; Oct 19: T1; Oct 20: T1; Oct 21: T1; Oct 22: T1; Oct 23: T1; Oct 24: T1; Oct 25: T1; Oct 26: T1; Oct 27: T1; Oct 28: T1; Oct 29: T1; Oct 30: T1; Oct 31: T1; Nov 01: T1; Nov 02: T1; Nov 03: T1; Nov 04: T1; Nov 05: T1; Nov 06: T1; Nov 07: T1; Nov 08: T1; Nov 09: T1; Nov 10: T1; Nov 11: T1; Nov 12: T1; Nov 13: T1; Nov 14: T1; May 05: E16
[200 empty] | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2 | P2
[216 empty] | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18 | E18
[226 empty] | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1 | P1
[226 empty] | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3 | P3
| Under Building Pad | Oct 08: T1; Oct 09: T1; Oct 10: T1; Oct 25: E17; Oct 26: E17; Oct 27: E17; Oct 28: E17; Oct 29: E17; Oct 30: E17; Oct 31: E17; Nov 01: E17; Nov 02: E17; Nov 03: E17; Nov 04: E17; Nov 05: E17; Nov 06: E17; Nov 07: E17; Nov 08: E17; Nov 09: E17; Nov 10: E17; Nov 11: E17; Nov 12: E17; Nov 13: E17
[227 empty] | U1 | U1 | U1 | U1 | U1 | U1 | U1 | U1 | U1 | U1 | U1
Core & Shell | Admin/ COLO 3 | Oct 14: X37; Oct 15: X37; Oct 16: X37; Oct 17: X37; Oct 18: X37; Oct 19: X37; Oct 20: X37; Oct 21: X37; Oct 22: X37; Oct 23: X37; Oct 24: X37; Oct 25: X37; Oct 26: X37; Oct 27: X37; Oct 28: X37; Oct 29: X37; Oct 30: X37; Oct 31: X37; Nov 01: X37; Nov 02: X37; Nov 03: X37; Nov 04: X37; Nov 05: X37; Nov 06: X37; Nov 07: X37; Nov 13: E14; Nov 14: E14; Nov 15: E14; Nov 16: E14; Nov 17: E14; Nov 18: E14; Nov 19: E14; Nov 20: E14; Nov 21: E14; Nov 22: E14; Nov 23: E14; Nov 24: E14; Nov 25: E14; Nov 26: E14; Nov 27: E14; Nov 28: E14; Nov 29: E14; Nov 30: E14; Dec 01: E14; Dec 02: E14; Dec 03: E14; Dec 04: E14; Dec 05: E14; Dec 06: E14; Dec 07: E14; Dec 08: E14; Dec 09: E14; Dec 10: E14; Dec 11: E14; Dec 12: E14; Dec 13: E14; Dec 14: E14; Dec 16: F2; Dec 17: F2; Dec 18: F2; Dec 19: F2; Dec 20: F2; Dec 21: F2; Dec 22: F2; Dec 23: F2; Dec 24: F2; Dec 25: F2; Dec 26: F2; Dec 27: F2; Dec 30: BW; Dec 31: BW; Jan 01: BW; Jan 02: BW; Jan 03: BW; Jan 04: BW; Jan 05: BW; Jan 06: BW; Jan 07: BW; Jan 08: BW; Jan 09: BW; Jan 10: BW; Jan 11: BW; Jan 12: BW; Jan 13: BW; Jan 14: BW; Jan 15: BW; Jan 16: BW
[240 empty] | D3 | D3 | D3 | D3 | D3 | D3 | D3 | D3 | D3 | D3 | D3 | D3 | X8 | X8 | X8 | X8 | X8 | X8 | X8 | X8 | X8 | X8 | X8 | X8 | X8 | X8 | X8 |  | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4
[282 empty] | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36
| COLO 4 | Nov 01: X37; Nov 02: X37; Nov 03: X37; Nov 04: X37; Nov 05: X37; Nov 06: X37; Nov 07: X37; Nov 08: X37; Nov 09: X37; Nov 10: X37; Nov 11: X37; Nov 12: X37; Nov 13: X37; Nov 14: X37; Nov 15: X37; Nov 16: X37; Nov 17: X37; Nov 18: X37; Nov 19: X37; Nov 20: X37; Nov 21: D3; Nov 22: D3; Nov 23: D3; Nov 24: D3; Nov 25: D3; Nov 26: D3; Nov 27: D3; Nov 28: D3; Nov 29: D3; Nov 30: D3; Dec 01: D3; Dec 02: D3; Dec 03: D3; Dec 04: D3; Dec 05: D3; Dec 06: D3; Dec 07: D3; Dec 08: D3; Dec 09: D3; Dec 10: D3; Dec 11: D3; Dec 12: D3; Dec 13: D3; Dec 14: D3; Dec 16: X8; Dec 17: X8; Dec 18: X8; Dec 19: X8; Dec 20: X8; Dec 21: X8; Dec 22: X8; Dec 23: X8; Dec 24: X8; Dec 25: X8; Dec 26: X8; Dec 27: X8; Dec 28: X8; Dec 29: X8; Dec 30: X8; Dec 31: X8; Jan 07: M4; Jan 08: M4; Jan 09: M4; Jan 10: M4; Jan 11: M4; Jan 12: M4; Jan 13: M4; Jan 14: M4; Jan 15: M4; Jan 16: M4; Jan 17: M4; Jan 18: M4; Jan 19: M4; Jan 20: M4; Jan 21: M4; Jan 22: M4; Jan 23: M4; Jan 24: M4; Jan 25: M4
[256 empty] | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 |  |  | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36
| COLO 5 | Nov 12: X37; Nov 13: X37; Nov 14: X37; Nov 15: X37; Nov 16: X37; Nov 17: X37; Nov 18: X37; Nov 19: X37; Nov 20: X37; Nov 21: X37; Nov 22: X37; Nov 23: X37; Nov 24: X37; Nov 25: X37; Nov 26: X37; Nov 27: X37; Nov 28: X37; Nov 29: X37; Nov 30: X37; Dec 01: X37; Dec 02: X37; Dec 03: X37; Dec 04: D3; Dec 05: D3; Dec 06: D3; Dec 07: D3; Dec 08: D3; Dec 09: D3; Dec 10: D3; Dec 11: D3; Dec 12: D3; Dec 13: D3; Dec 14: D3; Dec 15: D3; Dec 16: D3; Dec 17: D3; Dec 18: D3; Dec 19: D3; Dec 20: D3; Dec 21: D3; Dec 22: D3; Dec 23: D3; Dec 24: D3; Dec 25: D3; Dec 26: D3; Dec 27: D3; Dec 28: D3; Dec 29: D3; Dec 30: D3; Dec 31: D3; Jan 02: X8; Jan 03: X8; Jan 04: X8; Jan 05: X8; Jan 06: X8; Jan 07: X8; Jan 08: X8; Jan 09: X8; Jan 10: X8; Jan 11: X8; Jan 12: X8; Jan 13: X8; Jan 14: X8; Jan 15: X8; Jan 27: M4; Jan 28: M4; Jan 29: M4; Jan 30: M4; Jan 31: M4; Feb 01: M4; Feb 02: M4; Feb 03: M4; Feb 04: M4; Feb 05: M4; Feb 06: M4; Feb 07: M4; Feb 08: M4; Feb 09: M4; Feb 10: M4; Feb 11: M4; Feb 12: M4; Feb 13: M4; Feb 14: M4
[269 empty] | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 |  | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36 | X36
Fitout COLO3 | C3 CELL 1 Data Hall | Jan 17: X9; Jan 20: X21; Jan 21: X21; Jan 22: X21; Jan 23: X21; Jan 24: X21; Jan 25: D1; Jan 26: D1; Jan 27: D1; Jan 28: D1; Jan 29: D2; Jan 30: D2; Jan 31: D2; Feb 01: D5; Feb 02: D5; Feb 03: D5; Feb 04: D5; Feb 05: Y2; Feb 06: Y2; Feb 07: Y2; Feb 10: X19; Feb 11: X19; Feb 12: X19; Feb 13: X38; Feb 14: X38; Feb 15: Y7; Feb 16: Y7; Feb 17: Y7; Feb 18: CC; Feb 22: EE44; Feb 23: EE44; Feb 24: EE44; Feb 25: EE44; Feb 26: EE44; Feb 27: X35; Feb 28: X35; Mar 06: S2; Mar 07: S2; Mar 08: S2; Mar 09: S2; Mar 10: S2; Mar 11: EE43; Mar 12: EE43; Mar 13: EE43; Mar 14: EE43; Mar 15: EE43; Mar 16: EE43; Mar 17: EE43; Mar 18: EE17; Mar 19: EE17; Mar 20: EE17; Mar 21: EE17; Mar 22: EE17; Mar 23: EE17; Mar 24: EE17; Apr 14: EE58; Apr 15: EE58; Apr 16: EE58
[312 empty] | R4 | R4 | R4 | R1 | R1 | R1 | M5 | M5 | X30 | X30 | [10 empty] | X26 | X26 | X26 | X26 | S1 | S1 | S1 | S1 | S1 | EE7 | EE7 | EE7 | EE7 | EE7 | EE7 | [6 empty] | S4 | S4 | S4 | S4
[315 empty] | EE1 | EE1 | EE1 | EE1 | EE1 | [19 empty] | EE39 | EE39 | EE39 | EE39 | EE39 | EE39 | EE39
[341 empty] | EE11 | EE11 | EE11 | EE11 | EE11 | EE11 | EE11
| C3 CELL 1 Electrical Room | Jan 25: X21; Jan 26: X21; Jan 27: X21; Jan 28: X21; Jan 29: X21; Jan 30: X21; Jan 31: D1; Feb 01: D1; Feb 02: D1; Feb 03: D1; Feb 04: D1; Feb 05: D1; Feb 06: D1; Feb 07: D1; Feb 08: D1; Feb 09: D1; Feb 10: D1; Feb 11: R4; Feb 12: R4; Feb 13: R1; Feb 14: R1; Feb 15: X30; Feb 17: EE35; Feb 18: EE35; Feb 22: D5; Feb 23: D5; Feb 24: D5; Feb 25: D5; Feb 26: D5; Feb 27: D5; Feb 28: D5; Mar 01: D5; Mar 02: D5; Mar 03: D5; Mar 04: D5; Mar 05: Y2; Mar 06: Y2; Mar 07: CC; Mar 10: EE51; Mar 11: EE51; Mar 12: EE51; Mar 13: EE51; Mar 14: EE51; Mar 15: EE51; Mar 17: EE47; Mar 18: EE47; Mar 19: EE47; Mar 20: EE47; Mar 21: EE47; Mar 22: EE47; Mar 23: EE47; Mar 24: EE47; Mar 25: EE47; Mar 26: EE47; Mar 27: EE47; Mar 28: EE47; Mar 29: EE47; Mar 31: EE57; Apr 01: EE57; Apr 02: EE57; Apr 03: EE57
[325 empty] | D2 | D2 | D2 | D2 | D2 | D2 | D2 | D2 | D2 | D2 | D2 | [37 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[327 empty] | EE1 | EE1 | EE1
| C3 CELL 1 Mechanical Gallery | Feb 13: R4; Feb 14: R4; Feb 15: R1; Feb 16: R1; Feb 17: R1; Feb 19: M5; Feb 20: M5; Feb 21: M5; Feb 22: M5; Feb 23: M5; Feb 24: M5; Feb 25: M5; Feb 26: P4; Feb 27: P4; Feb 28: P4; Mar 01: P4; Mar 02: P4; Mar 03: P4; Mar 04: P4; Mar 05: P4; Mar 06: X30; Mar 07: X27; Mar 08: X27; Mar 09: X27; Mar 10: X27; Mar 11: X27; Mar 12: EE35; Mar 13: EE35; Mar 14: M6; Mar 15: M6; Mar 16: M6; Mar 17: M6; Mar 18: M6; Mar 19: EE48; Mar 20: EE48; Mar 21: EE48; Mar 22: EE48; Mar 23: EE48; Mar 24: EE48; Mar 25: EE48; Mar 26: EE48; Mar 27: EE48; Mar 28: EE48; Mar 29: EE48; Mar 30: EE48; Mar 31: EE48; Apr 01: EE48; Apr 02: EE48; Apr 03: M7; Apr 04: M7; Apr 05: M7; Apr 06: M7; Apr 07: M7
[329 empty] | EE1 | EE1 | EE1 | EE1 | [13 empty] | D2 | D2 | D5 | D5 | Y2 | Y2 | Y2 | CC | CC | CC | [11 empty] | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1
[354 empty] | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA
C3 CELL 1 Punchlist | bar: Apr 17 to Apr 28
| C3 CELL 2 Data Hall | Jan 29: X9; Jan 30: X21; Jan 31: X21; Feb 01: X21; Feb 03: D1; Feb 04: D1; Feb 05: D1; Feb 06: D2; Feb 07: D2; Feb 08: D2; Feb 09: D2; Feb 10: D2; Feb 11: D5; Feb 12: D5; Feb 13: D5; Feb 14: Y2; Feb 15: Y2; Feb 16: Y2; Feb 17: Y2; Feb 18: X19; Feb 19: X19; Feb 20: X19; Feb 21: X38; Feb 22: X38; Feb 24: Y7; Feb 25: Y7; Feb 26: CC; Mar 04: EE44; Mar 05: EE44; Mar 06: EE44; Mar 07: EE44; Mar 08: X35; Mar 09: X35; Mar 10: X35; Mar 14: S2; Mar 15: S2; Mar 16: S2; Mar 17: S2; Mar 18: S2; Mar 19: EE43; Mar 20: EE43; Mar 21: EE43; Mar 24: EE43; Mar 25: EE43; Mar 26: EE43; Mar 27: EE17; Mar 28: EE17; Mar 29: EE17; Mar 30: EE17; Mar 31: EE17; Apr 01: EE17; May 09: EE58; May 10: EE58; May 11: EE58; May 12: EE58
[320 empty] | R4 | R4 | R4 | R4 | R4 | R1 | R1 | X30 | X30 | [11 empty] | X26 | X26 | X26 | X26 | X26 | X26 | S1 | S1 | S1 | S1 | EE7 | EE7 | EE7 | EE7 | EE7 | [6 empty] | S4 | S4 | S4 | S4 | S4 | S4
[325 empty] | EE1 | EE1 | M5 | M5 | [19 empty] | EE39 | EE39 | EE39 | EE39 | EE39 | EE39
[350 empty] | EE11 | EE11 | EE11 | EE11 | EE11 | EE11
| C3 CELL 2 Electrical Room | Feb 03: X21; Feb 04: X21; Feb 05: D1; Feb 06: D1; Feb 07: R4; Feb 08: R4; Feb 09: R4; Feb 10: R4; Feb 11: R1; Feb 12: R1; Feb 13: X30; Feb 14: EE35; Feb 15: EE35; Feb 18: CC; Mar 17: EE51; Mar 18: EE51; Mar 19: EE51; Mar 20: EE51; Apr 14: EE47; Apr 15: EE47; Apr 16: EE47; Apr 17: EE47; Apr 18: EE47; Apr 19: EE47; Apr 20: EE47; Apr 21: EE47; Apr 22: EE47; Apr 23: EE47; Apr 24: EE47; Apr 25: EE47; Apr 26: EE57; Apr 27: EE57; Apr 28: EE57; Apr 29: EE57; Apr 30: EE57
[321 empty] | D2 | D2 | D2 | D2 | D2 | D2 | D5 | D5 | Y2 | Y2 | Y2 | [67 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[325 empty] | EE1 | EE1 | EE1
| C3 CELL 2 Mechanical Gallery | Feb 11: R4; Feb 12: R4; Feb 13: R1; Feb 14: R1; Feb 17: M5; Feb 18: M5; Feb 19: M5; Feb 20: M5; Feb 21: M5; Feb 22: M5; Feb 24: P4; Feb 25: P4; Feb 26: P4; Feb 27: P4; Feb 28: P4; Mar 01: P4; Mar 02: P4; Mar 03: P4; Mar 04: X30; Mar 05: X27; Mar 06: X27; Mar 07: X27; Mar 08: X27; Mar 10: EE35; Mar 11: EE35; Mar 12: M6; Mar 13: M6; Mar 14: M6; Mar 15: M6; Mar 17: EE48; Mar 18: EE48; Mar 19: EE48; Mar 20: EE48; Mar 21: EE48; Mar 22: EE48; Mar 23: EE48; Mar 24: EE48; Mar 25: EE48; Mar 26: EE48; Mar 27: EE48; Mar 28: EE48; Mar 29: EE48; Mar 30: EE48; Mar 31: EE48; Apr 01: M7; Apr 02: M7; Apr 03: M7; Apr 04: M7
[327 empty] | EE1 | EE1 | EE1 | [12 empty] | D2 | D2 | D2 | D2 | D5 | D5 | Y2 | Y2 | CC | CC | CC | CC | [9 empty] | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1
[352 empty] | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA
C3 CELL 2 Punchlist | bar: May 13 to May 23
| C3 CELL 3 Data Hall | Feb 21: X9; Feb 22: X21; Feb 23: X21; Feb 24: X21; Feb 25: X21; Feb 26: D1; Feb 27: D1; Feb 28: D1; Mar 03: D2; Mar 04: D2; Mar 05: D2; Mar 06: D5; Mar 07: D5; Mar 08: D5; Mar 10: Y2; Mar 11: Y2; Mar 12: Y2; Mar 13: X19; Mar 14: X19; Mar 15: X19; Mar 17: X38; Mar 18: X38; Mar 19: Y7; Mar 20: Y7; Mar 21: CC; Mar 27: EE44; Mar 28: EE44; Mar 29: EE44; Mar 30: EE44; Mar 31: EE44; Apr 01: X35; Apr 02: X35; Apr 07: S2; Apr 08: S2; Apr 09: S2; Apr 10: S2; Apr 11: EE43; Apr 12: EE43; Apr 13: EE43; Apr 14: EE43; Apr 15: EE43; Apr 16: EE43; Apr 17: EE43; Apr 18: EE43; Apr 19: EE17; Apr 20: EE17; Apr 21: EE17; Apr 22: EE17; Apr 23: EE17; Apr 24: EE17; Jun 05: EE58; Jun 06: EE58; Jun 07: EE58
[345 empty] | R4 | R4 | R4 | R1 | R1 | X30 | X30 | X30 | [10 empty] | X26 | X26 | X26 | X26 | X26 | X26 | S1 | S1 | S1 | S1 | S1 | EE7 | EE7 | EE7 | EE7 | [6 empty] | S4 | S4 | S4 | S4 | S4 | S4
[348 empty] | EE1 | EE1 | EE1 | EE1 | EE1 | [18 empty] | EE39 | EE39 | EE39 | EE39 | EE39 | EE39
[350 empty] | M5 | M5 | M5 | [21 empty] | EE11 | EE11 | EE11 | EE11 | EE11
| C3 CELL 3 Electrical Room | Feb 26: X21; Feb 27: X21; Feb 28: D1; Mar 01: D1; Mar 02: D1; Mar 03: D1; Mar 04: R4; Mar 05: R4; Mar 06: R1; Mar 07: R1; Mar 08: X30; Mar 10: EE35; Mar 11: EE35; Mar 13: CC; Mar 14: EE51; Mar 15: EE51; Mar 16: EE51; Mar 17: EE51; Mar 18: EE51; May 10: EE47.1; May 11: EE47.1; May 12: EE47.1; May 13: EE47.1; May 14: EE47.1; May 15: EE47.1; May 16: EE47.1; May 17: EE47.1; May 18: EE47.1; May 19: EE47.1; May 20: EE47.1; May 21: EE47.1; May 22: EE47.1; May 23: EE57; May 24: EE57; May 25: EE57; May 26: EE57; May 27: EE57; May 28: EE57
[346 empty] | D2 | D2 | D2 | D2 | D5 | D5 | D5 | Y2 | Y2 | [71 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[348 empty] | EE1 | EE1 | EE1
| C3 CELL 3 Mechanical Gallery | Mar 06: R4; Mar 07: R4; Mar 08: R1; Mar 09: R1; Mar 10: R1; Mar 12: M5; Mar 13: M5; Mar 14: M5; Mar 15: M5; Mar 16: M5; Mar 17: M5; Mar 18: M5; Mar 19: P4; Mar 20: P4; Mar 21: P4; Mar 22: P4; Mar 23: P4; Mar 24: P4; Mar 25: P4; Mar 26: P4; Mar 27: X30; Mar 28: X27; Mar 29: X27; Mar 30: X27; Mar 31: X27; Apr 01: X27; Apr 02: EE35; Apr 03: EE35; Apr 04: M6; Apr 05: M6; Apr 06: M6; Apr 07: M6; Apr 08: M6; Apr 09: EE48; Apr 10: EE48; Apr 11: EE48; Apr 12: EE48; Apr 13: EE48; Apr 14: EE48; Apr 15: EE48; Apr 16: EE48; Apr 17: EE48; Apr 18: EE48; Apr 19: EE48; Apr 20: EE48; Apr 21: EE48; Apr 22: EE48; Apr 23: EE48; Apr 24: M7; Apr 25: M7; Apr 26: M7; Apr 27: M7; Apr 28: M7
[350 empty] | EE1 | EE1 | EE1 | EE1 | [13 empty] | D2 | D2 | D5 | D5 | Y2 | Y2 | Y2 | CC | CC | CC | [11 empty] | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1
[375 empty] | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA
C3 CELL 3 Punchlist | bar: Jun 09 to Jun 20
| C3 CELL 4 Data Hall | Feb 10: X9; Feb 11: X21; Feb 12: X21; Feb 13: X21; Feb 14: D1; Feb 15: D1; Feb 16: D1; Feb 17: D1; Feb 18: D2; Feb 19: D2; Feb 20: D2; Feb 21: D5; Feb 22: D5; Feb 23: D5; Feb 24: D5; Feb 25: Y2; Feb 26: Y2; Feb 27: Y2; Feb 28: X19; Mar 01: X19; Mar 02: X19; Mar 03: X19; Mar 04: X19; Mar 05: X38; Mar 06: X38; Mar 07: Y7; Mar 08: Y7; Mar 10: CC; Mar 14: EE44; Mar 15: EE44; Mar 16: EE44; Mar 17: EE44; Mar 18: EE44; Mar 19: X35; Mar 20: X35; Mar 26: S2; Mar 27: S2; Mar 28: S2; Mar 29: S2; Mar 31: EE43; Apr 01: EE43; Apr 02: EE43; Apr 03: EE43; Apr 04: EE43; Apr 05: EE43; Apr 07: EE17; Apr 08: EE17; Apr 09: EE17; Apr 10: EE17; Apr 11: EE17; May 10: EE58; May 11: EE58; May 12: EE58; May 13: EE58
[332 empty] | R4 | R4 | R4 | R1 | R1 | R1 | X30 | X30 | [12 empty] | X26 | X26 | X26 | X26 | S1 | S1 | S1 | S1 | S1 | EE7 | EE7 | EE7 | EE7 | EE7 | EE7 | [6 empty] | S4 | S4 | S4 | S4
[335 empty] | EE1 | EE1 | EE1 | M5 | M5 | [19 empty] | EE39 | EE39 | EE39 | EE39 | EE39
[361 empty] | EE11 | EE11 | EE11 | EE11 | EE11 | EE11 | EE11
| C3 CELL 4 Electrical Room | Feb 14: X21; Feb 15: X21; Feb 17: D1; Feb 18: D1; Feb 19: R5; Feb 20: R5; Feb 21: R1; Feb 22: R1; Feb 24: X30; Feb 25: EE35; Feb 26: EE35; Feb 28: CC; Mar 03: EE51; Mar 04: EE51; Mar 05: EE51; Mar 06: EE51; Mar 07: EE47.1; Mar 08: EE47.1; Mar 09: EE47.1; Mar 10: EE47.1; Mar 11: EE47.1; Mar 12: EE47.1; Mar 13: EE47.1; Mar 14: EE47.1; Mar 15: EE47.1; Mar 16: EE47.1; Mar 17: EE47.1; Mar 18: EE47.1; Mar 19: EE47.1; Mar 20: EE57; Mar 21: EE57; Mar 22: EE57; Mar 23: EE57; Mar 24: EE57; Mar 25: EE57; Apr 26: EE50; Apr 27: EE50; Apr 28: EE50; Apr 29: EE50; Apr 30: EE50; May 01: EE50; May 02: EE50; May 03: EE50; May 04: EE50; May 05: EE50; May 06: EE50; May 07: EE50; May 08: EE50; May 09: EE50
[333 empty] | D2 | D2 | D2 | D2 |  | D5 | D5 | Y2 | Y2
[335 empty] | EE1 | EE1 | EE1 | EE1
| C3 CELL 4 Mechanical Gallery | Feb 21: R6; Feb 22: R6; Feb 24: R1; Feb 25: R1; Feb 27: M5; Feb 28: M5; Mar 01: M5; Mar 02: M5; Mar 03: M5; Mar 04: M5; Mar 05: M5; Mar 06: M5; Mar 07: P4; Mar 08: P4; Mar 09: P4; Mar 10: P4; Mar 11: P4; Mar 12: P4; Mar 13: P4; Mar 14: X30; Mar 15: X27; Mar 16: X27; Mar 17: X27; Mar 18: X27; Mar 19: X27; Mar 20: EE35; Mar 21: EE35; Mar 24: M6; Mar 25: M6; Mar 26: M6; Mar 27: M6; Mar 28: EE48; Mar 29: EE48; Mar 30: EE48; Mar 31: EE48; Apr 01: EE48; Apr 02: EE48; Apr 03: EE48; Apr 04: EE48; Apr 05: EE48; Apr 06: EE48; Apr 07: EE48; Apr 08: EE48; Apr 09: EE48; Apr 10: EE48; Apr 11: M7; Apr 12: M7; Apr 13: M7; Apr 14: M7; Apr 15: M7; Apr 16: M7
[338 empty] | EE1 | EE1 | EE1 | [13 empty] | D2 | D2 | D5 | D5 |  | Y2 | Y2 | CC | CC | CC | [11 empty] | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1
[362 empty] | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA
C3 CELL 4 Punchlist | bar: May 10 to May 21
Fitout Admin Area | Beneficial Use Rooms Electrical Rooms | Jan 20: R4; Jan 21: X21; Jan 22: MEP1; Jan 23: MEP1; Jan 24: D4; Jan 25: D4; Jan 27: X16; Jan 28: D6; Jan 29: D6; Jan 30: D6; Jan 31: D6; Feb 01: Y1; Feb 02: Y1; Feb 03: Y1; Feb 04: EE28; Mar 03: EE51; Mar 04: EE51; Mar 05: EE51; Mar 06: EE51; Mar 07: EE51; Mar 08: EE51; Mar 09: EE51; Mar 10: EE51; Mar 11: EE51; Mar 12: EE49; Mar 13: EE49; Mar 14: EE49; Mar 15: EE49; Mar 16: EE49; Mar 17: EE49; Mar 18: EE49; Mar 19: EE49; Mar 20: EE49; Mar 21: EE49; Mar 22: EE49; Mar 23: EE49; Mar 24: EE49; Mar 25: EE49; Mar 26: EE49; Mar 27: EE49; Mar 28: EE49; Mar 29: EE46; Mar 30: EE46; Mar 31: EE46; Apr 01: EE46; Apr 02: EE46; Apr 03: EE46; Apr 04: EE46; Apr 05: EE46; Apr 06: EE46; Apr 07: EE46; Apr 08: EE46; Apr 09: EE46; Apr 10: EE46; Apr 11: EE46; Apr 14: EE56; Apr 15: EE56; Apr 16: EE56; Apr 17: EE56
| Beneficial Use Rooms Entry Room1 | Jan 21: R4; Jan 22: X21; Jan 24: MEP1; Jan 25: MEP1; Jan 27: D4; Jan 28: D4; Jan 29: X16; Jan 30: D6; Jan 31: D6; Feb 01: D6; Feb 02: D6; Feb 03: D6; Feb 04: Y1; Feb 05: Y1; Feb 06: EE45; Feb 07: EE45; Feb 08: EE45; Feb 09: EE45; Feb 10: EE45; Feb 11: EE52; Feb 12: EE52; Feb 13: EE52; Feb 14: EE52
| Beneficial Use Rooms Entry Room2 | Jan 22: R4; Jan 23: X21; Jan 27: MEP1; Jan 28: MEP1; Jan 29: D4; Jan 30: D4; Jan 31: X16; Feb 01: D6; Feb 02: D6; Feb 03: D6; Feb 04: D6; Feb 05: D6; Feb 06: Y1; Feb 07: Y1; Feb 10: EE45; Feb 11: EE45; Feb 12: EE45; Feb 13: EE53; Feb 14: EE53; Feb 15: EE53; Feb 16: EE53; Feb 17: EE53
| Beneficial Use Rooms FCR (Facilities Control Room) | Jan 23: R4; Jan 24: X21; Jan 29: MEP1; Jan 30: MEP1; Jan 31: D4; Feb 01: D4; Feb 03: X16; Feb 04: D6; Feb 05: D6; Feb 06: D6; Feb 07: D6; Feb 10: Y1; Feb 11: Y1; Feb 12: EE45; Feb 13: EE45; Feb 14: EE45; Feb 15: EE54; Feb 16: EE54; Feb 17: EE54; Feb 18: EE54; Feb 19: EE54; Feb 20: T4; Feb 21: T4; Feb 22: T4; Feb 23: T4; Feb 24: T4; Feb 25: T4; Feb 26: T4; Feb 27: T4; Feb 28: T4; Mar 01: T4; Mar 02: T4; Mar 03: T4; Mar 04: T4; Mar 05: T4; Mar 06: T4; Mar 07: T5; Mar 08: T5; Mar 09: T5; Mar 10: T5; Mar 11: T5; Mar 12: T5; Mar 13: T5; Mar 14: T5; Mar 15: T5; Mar 16: T5; Mar 17: T5; Mar 18: T5; Mar 19: T5; Mar 20: T5; Mar 21: T3; Mar 22: T3; Mar 23: T3; Mar 24: T3; Mar 25: T3; Mar 26: T3; Mar 27: T3; Mar 28: T3; Mar 29: T3; Mar 30: T3; Mar 31: T3; Apr 01: T3; Apr 02: T3; Apr 03: T3; Apr 04: T3; Apr 05: T10; Apr 06: T10; Apr 07: T10; Apr 08: T10; Apr 09: T10; Apr 10: T10; Apr 11: T10; Apr 12: T10; Apr 13: T10; Apr 14: T10; Apr 15: T10; Apr 16: T10; Apr 17: T10; Apr 18: T10; Apr 19: T10; Apr 21: T7; Apr 22: T7; Apr 23: T7; Apr 24: T7; Apr 25: T7; Apr 26: T7; Apr 27: T7; Apr 28: T7; Apr 29: T7; Apr 30: T7; May 01: T7; May 02: T7; May 03: T7; May 04: T7; May 05: T7
[334 empty] | T8 | T8 | T8 | T8 | T8 | T8 | T8 | T8 | T8 | T8 | T8 | T8 | T8 | T8 | T8 | T9 | T9 | T9 | T9 | T9 | T9 | T9 | T9 | T9 | T9 | T9 | T9 | T9 | T9 | T6 | T6 | T6 | T6 | T6 | T6 | T6 | T6 | T6 | T6 | T6 | T6 | T6 | T6 | T6
Beneficial Use Rooms Punchlist | bar: May 06 to May 09
| Beneficial Use Rooms SER (Security Equip Room) | Jan 24: R4; Jan 25: X21; Jan 31: MEP1; Feb 01: MEP1; Feb 03: D4; Feb 04: D4; Feb 05: X16; Feb 06: D5; Feb 07: D5; Feb 10: Y1; Feb 11: Y1; Feb 12: EE45; Feb 13: EE45; Feb 14: EE45; Feb 15: EE55; Feb 16: EE55; Feb 17: EE55; Feb 18: EE55; Feb 19: EE55
| Beneficial Use Rooms Storage (High Value & Secure) Rooms | Jan 25: R4; Jan 27: X21; Feb 03: MEP1; Feb 04: MEP1; Feb 05: D4; Feb 06: D4; Feb 07: M3; Feb 08: M3; Feb 09: M3; Feb 10: M3; Feb 11: M3; Feb 12: M3; Feb 13: M3; Feb 14: M3; Feb 15: M3; Feb 16: M3; Feb 17: M3; Feb 18: M3; Feb 19: M3; Feb 20: M3; Feb 21: M3; Feb 22: M3; Feb 23: M3; Feb 24: M3; Feb 25: M3; Feb 26: D5; Feb 27: D5; Feb 28: D5; Mar 01: D5; Mar 02: D5; Mar 03: D5; Mar 04: Y1; Mar 05: Y1; Mar 06: C1; Mar 07: C1; Mar 08: C1; Mar 09: C1; Mar 10: C1; Mar 11: C1; Mar 12: C1; Mar 13: C1; Mar 14: C1; Mar 15: C1; Mar 16: C1; Mar 17: C1
| Remaining Rooms Admin Gen Finishes & Punch | Feb 22: X34; Feb 23: X34; Feb 24: X34; Feb 25: X34; Feb 26: X34; Feb 27: EEA; Feb 28: EEA; Mar 01: EEA; Mar 02: EEA; Mar 03: EEA; Mar 04: EEA; Mar 05: EEA; Mar 06: EEA; Mar 07: EEA; Mar 08: EEA; Mar 09: EEA; Mar 10: EEA; Mar 11: EEA; Mar 12: CPP; Mar 13: CPP; Mar 14: CPP; Mar 15: CPP; Mar 16: CPP; Mar 17: CPP
| Remaining Rooms Fire Riser Room | Jan 27: R4; Jan 28: X21; Jan 29: M1; Jan 30: M1; Jan 31: X35; Feb 05: MEP1; Feb 06: MEP1; Feb 07: D4; Feb 08: D4; Feb 09: D4; Feb 10: D4; Feb 11: X16; Feb 12: D5; Feb 13: D5; Feb 14: Y1; Feb 15: Y1; Feb 18: X17; Feb 19: X17; Feb 20: X17; Feb 21: X17; Feb 22: R11; Feb 23: R11; Feb 24: R11
| Remaining Rooms Loading Dock | Jan 29: R4; Jan 30: X21; Jan 31: MEP2; Feb 11: MEP1; Feb 12: MEP1; Feb 13: D4; Feb 14: D4; Feb 15: D5; Feb 16: D5; Feb 17: D5; Feb 18: Y1; Feb 19: Y1; Feb 20: P5; Feb 21: P5; Feb 22: P5; Feb 23: P5; Feb 24: P5; Feb 25: P5; Feb 26: P5; Feb 27: P5; Feb 28: P5; Mar 01: P5; Mar 02: P5; Mar 03: P5; Mar 04: P5; Mar 05: P5; Mar 06: P5; Mar 07: P5; Mar 08: P5; Mar 09: P5; Mar 10: P5; Mar 11: EE29; Mar 12: EE29; Mar 13: EE29
[312 empty] | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1
[313 empty] | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2
| Remaining Rooms Restrooms & Janitor Room | Jan 28: R4; Jan 29: X21; Feb 07: MEP1; Feb 08: MEP1; Feb 09: MEP1; Feb 10: MEP1; Feb 11: D4; Feb 12: D4; Feb 13: D5; Feb 14: D5; Feb 15: Y1; Feb 16: Y1; Feb 17: Y1; Feb 18: X17; Feb 19: X17; Feb 20: X17; Feb 21: X17
Fitout COLO4 | C4 CELL 1 Data Hall | Feb 24: X9; Feb 25: X21; Feb 26: X21; Feb 27: X21; Feb 28: D1; Mar 01: D1; Mar 02: D1; Mar 03: D1; Mar 04: D1; Mar 05: D2; Mar 06: D2; Mar 07: D2; Mar 08: D5; Mar 09: D5; Mar 10: D5; Mar 11: D5; Mar 12: Y2; Mar 13: Y2; Mar 14: Y2; Mar 15: X19; Mar 16: X19; Mar 17: X19; Mar 18: X19; Mar 19: X38; Mar 20: X38; Mar 21: Y7; Mar 22: Y7; Mar 23: Y7; Mar 24: Y7; Mar 25: CC; Mar 29: EE44; Mar 30: EE44; Mar 31: EE44; Apr 01: EE44; Apr 02: EE44; Apr 03: X35; Apr 04: X35; Apr 09: S2; Apr 10: S2; Apr 11: S2; Apr 12: S2; Apr 13: S2; Apr 14: S2; Apr 15: EE43; Apr 16: EE43; Apr 17: EE43; Apr 18: EE43; Apr 19: EE43; Apr 20: EE43; Apr 21: EE43; Apr 22: EE17; Apr 23: EE17; Apr 24: EE17; Apr 25: EE17; Apr 26: EE17; May 01: EE58; May 02: EE58; May 03: EE58; May 04: EE58; May 05: EE58
[347 empty] | R7 | R7 | R7 | R1 | R1 | R1 | X30 | X30 | [12 empty] | X26 | X26 | X26 | X26 | S1 | S1 | S1 | S1 | S1 | EE7 | EE7 | EE7 | EE7 | EE7 | [7 empty] | S4 | S4 | S4 | S4
[350 empty] | EE1 | EE1 | EE1 | M5 | M5 | [19 empty] | EE39 | EE39 | EE39 | EE39 | EE39
[376 empty] | EE11 | EE11 | EE11 | EE11 | EE11 | EE11
| C4 CELL 1 Electrical Room | Feb 28: X21; Mar 01: X21; Mar 02: X21; Mar 03: X21; Mar 04: D1; Mar 05: D1; Mar 06: R8; Mar 07: R8; Mar 08: R1; Mar 09: R1; Mar 10: R1; Mar 11: X30; Mar 12: EE35; Mar 13: EE35; Mar 15: CC; Mar 31: EE51; Apr 01: EE51; Apr 02: EE51; Apr 03: EE51; Apr 04: EE47; Apr 05: EE47; Apr 06: EE47; Apr 07: EE47; Apr 08: EE47; Apr 09: EE47; Apr 10: EE47; Apr 11: EE47; Apr 12: EE47; Apr 13: EE47; Apr 14: EE47; Apr 15: EE47; Apr 16: EE47; Apr 17: EE47; Apr 18: EE57; Apr 19: EE57; Apr 20: EE57; Apr 21: EE57; Apr 22: EE57
[348 empty] | D2 | D2 | D2 | D2 | D2 | D5 | D5 | Y2 | Y2 | [34 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[350 empty] | EE1 | EE1 | EE1 | EE1
| C4 CELL 1 Mechanical Gallery | Mar 08: R9; Mar 09: R9; Mar 10: R9; Mar 11: R1; Mar 12: R1; Mar 14: M5; Mar 15: M5; Mar 16: M5; Mar 17: M5; Mar 18: M5; Mar 19: M5; Mar 20: M5; Mar 21: P4; Mar 22: P4; Mar 23: P4; Mar 24: P4; Mar 25: P4; Mar 26: P4; Mar 27: P4; Mar 28: P4; Mar 29: X30; Mar 31: X27; Apr 01: X27; Apr 02: X27; Apr 03: X27; Apr 04: EE35; Apr 05: EE35; Apr 07: M6; Apr 08: M6; Apr 09: M6; Apr 10: M6; Apr 11: EE48; Apr 12: EE48; Apr 13: EE48; Apr 14: EE48; Apr 15: EE48; Apr 16: EE48; Apr 17: EE48; Apr 18: EE48; Apr 19: EE48; Apr 20: EE48; Apr 21: EE48; Apr 22: EE48; Apr 23: EE48; Apr 24: EE48; Apr 25: EE48; Apr 26: M7; Apr 27: M7; Apr 28: M7; Apr 29: M7; Apr 30: M7
[353 empty] | EE1 | EE1 | EE1 | [13 empty] | D2 | D2 | D5 | D5 | D5 | Y2 | Y2 | CC | CC | CC | [11 empty] | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1
[377 empty] | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA
C4 CELL 1 Punchlist | bar: May 06 to May 16
| C4 CELL 2 Data Hall | Mar 05: X9; Mar 06: X21; Mar 07: X21; Mar 08: X21; Mar 10: D1; Mar 11: D1; Mar 12: D1; Mar 13: D2; Mar 14: D2; Mar 15: D2; Mar 17: D5; Mar 18: D5; Mar 19: D5; Mar 20: Y2; Mar 21: Y2; Mar 22: Y2; Mar 23: Y2; Mar 24: Y2; Mar 25: X19; Mar 26: X19; Mar 27: X19; Mar 28: X38; Mar 29: X38; Mar 31: Y7; Apr 01: Y7; Apr 02: CC; Apr 07: EE44; Apr 08: EE44; Apr 09: EE44; Apr 10: EE44; Apr 11: X35; Apr 12: X35; Apr 13: X35; Apr 14: X35; Apr 18: S2; Apr 19: S2; Apr 20: S2; Apr 21: S2; Apr 22: S2; Apr 23: EE43; Apr 24: EE43; Apr 25: EE43; Apr 26: EE43; Apr 27: EE43; Apr 28: EE43; Apr 29: EE43; Apr 30: EE17; May 01: EE17; May 02: EE17; May 03: EE17; May 04: EE17; May 05: EE17; May 06: EE17; May 28: EE58; May 29: EE58; May 30: EE58
[355 empty] | R10 | R10 | R10 |  | R1 | R1 | X30 | X30 | [12 empty] | X26 | X26 | X26 | X26 |  | S1 | S1 | S1 | S1 | EE7 | EE7 | EE7 | EE7 | EE7 | EE7 | [6 empty] | S4 | S4 | S4 | S4
[359 empty] | EE1 | EE1 | M5 | M5 | [19 empty] | EE39 | EE39 | EE39 | EE39 | EE39 | EE39 | EE39
[384 empty] | EE11 | EE11 | EE11 | EE11 | EE11 | EE11 | EE11
| C4 CELL 2 Electrical Room | Mar 10: X21; Mar 11: X21; Mar 12: D1; Mar 13: D1; Mar 14: R11; Mar 15: R11; Mar 17: R1; Mar 18: R1; Mar 19: X30; Mar 20: EE35; Mar 21: EE35; Mar 25: CC; Mar 26: EE51; Mar 27: EE51; Mar 28: EE51; Mar 29: EE51; May 01: EE47; May 02: EE47; May 03: EE47; May 04: EE47; May 05: EE47; May 06: EE47; May 07: EE47; May 08: EE47; May 09: EE47; May 10: EE47; May 11: EE47; May 12: EE47; May 13: EE47; May 14: EE47; May 15: EE57; May 16: EE57; May 17: EE57; May 18: EE57; May 19: EE57
[356 empty] | D2 | D2 | D2 | D2 | D2 | D5 | D5 | Y2 | Y2 | Y2 | Y2 | [51 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[359 empty] | EE1 | EE1 | EE1
| C4 CELL 2 Mechanical Gallery | Mar 17: R12; Mar 18: R12; Mar 19: R1; Mar 20: R1; Mar 24: M5; Mar 25: M5; Mar 26: M5; Mar 27: M5; Mar 28: M5; Mar 29: M5; Mar 31: P4; Apr 01: P4; Apr 02: P4; Apr 03: P4; Apr 04: P4; Apr 05: P4; Apr 07: X30; Apr 08: X27; Apr 09: X27; Apr 10: X27; Apr 11: X27; Apr 14: EE35; Apr 15: EE35; Apr 16: M6; Apr 17: M6; Apr 18: M6; Apr 19: M6; Apr 21: EE48; Apr 22: EE48; Apr 23: EE48; Apr 24: EE48; Apr 25: EE48; Apr 26: EE48; Apr 27: EE48; Apr 28: EE48; Apr 29: EE48; Apr 30: EE48; May 01: EE48; May 02: EE48; May 03: EE48; May 04: EE48; May 05: EE48; May 06: M7; May 07: M7; May 08: M7; May 09: M7
[361 empty] | EE1 | EE1 | EE1 | [13 empty] | D2 | D2 |  | D5 | D5 | Y2 | Y2 | CC | CC | CC | CC | CC | [9 empty] | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1
[387 empty] | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA
C4 CELL 2 Punchlist | bar: May 31 to Jun 11
| C4 CELL 3 Data Hall | Mar 28: X9; Mar 29: X21; Mar 30: X21; Mar 31: X21; Apr 01: X21; Apr 02: D1; Apr 03: D1; Apr 04: D1; Apr 05: D2; Apr 06: D2; Apr 07: D2; Apr 08: D2; Apr 09: D5; Apr 10: D5; Apr 11: D5; Apr 14: Y2; Apr 15: Y2; Apr 16: Y2; Apr 17: X19; Apr 18: X19; Apr 19: X19; Apr 21: X38; Apr 22: X38; Apr 23: Y7; Apr 24: Y7; Apr 25: CC; Apr 30: EE44; May 01: EE44; May 02: EE44; May 03: EE44; May 04: EE44; May 05: EE44; May 06: X35; May 07: X35; May 12: S2; May 13: S2; May 14: S2; May 15: S2; May 16: EE43; May 17: EE43; May 18: EE43; May 19: EE43; May 20: EE43; May 21: EE43; May 22: EE43; May 23: EE17; May 24: EE17; May 25: EE17; May 26: EE17; May 27: EE17; May 28: EE17; May 29: EE17; Jul 18: EE58; Jul 19: EE58; Jul 20: EE58; Jul 21: EE58
[378 empty] | R13 | R13 | R13 | R13 | R1 | R1 | X30 | X30 | X30 | X30 | [10 empty] | X26 | X26 | X26 | X26 | X26 | S1 | S1 | S1 | S1 | S1 | S1 | EE7 | EE7 | EE7 | EE7 | [6 empty] | S4 | S4 | S4 | S4 | S4
[382 empty] | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | [17 empty] | EE39 | EE39 | EE39 | EE39 | EE39 | EE39 | EE39
[384 empty] | M5 | M5 | M5 | M5 | [21 empty] | EE11 | EE11 | EE11 | EE11 | EE11
| C4 CELL 3 Electrical Room | Apr 02: X21; Apr 03: X21; Apr 04: D1; Apr 05: D1; Apr 07: R14; Apr 08: R14; Apr 09: R1; Apr 10: R1; Apr 11: X30; Apr 14: EE35; Apr 15: EE35; Apr 17: CC; Apr 18: EE51; Apr 19: EE51; Apr 20: EE51; Apr 21: EE51; Apr 22: EE51; Jun 24: EE47.1; Jun 25: EE47.1; Jun 26: EE47.1; Jun 27: EE47.1; Jun 28: EE47.1; Jun 29: EE47.1; Jun 30: EE47.1; Jul 01: EE47.1; Jul 02: EE47.1; Jul 03: EE47.1; Jul 04: EE47.1; Jul 05: EE47.1; Jul 06: EE47.1; Jul 07: EE47.1; Jul 08: EE47.1; Jul 09: EE57; Jul 10: EE57; Jul 11: EE57; Jul 12: EE57
[380 empty] | D2 | D2 | D2 | D2 | D5 | D5 | D5 | D5 | Y2 | Y2 | [83 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[382 empty] | EE1 | EE1 | EE1
| C4 CELL 3 Mechanical Gallery | Apr 09: R15; Apr 10: R15; Apr 11: R1; Apr 12: R1; Apr 13: R1; Apr 14: R1; Apr 16: M5; Apr 17: M5; Apr 18: M5; Apr 19: M5; Apr 20: M5; Apr 21: M5; Apr 22: M5; Apr 23: P4; Apr 24: P4; Apr 25: P4; Apr 26: P4; Apr 27: P4; Apr 28: P4; Apr 29: P4; Apr 30: X30; May 01: X27; May 02: X27; May 03: X27; May 04: X27; May 05: X27; May 06: X27; May 07: EE35; May 08: EE35; May 09: M6; May 10: M6; May 11: M6; May 12: M6; May 13: M6; May 14: EE48; May 15: EE48; May 16: EE48; May 17: EE48; May 18: EE48; May 19: EE48; May 20: EE48; May 21: EE48; May 22: EE48; May 23: EE48; May 24: EE48; May 25: EE48; May 26: EE48; May 27: EE48; May 28: EE48; May 29: M7; May 30: M7; May 31: M7; Jun 01: M7; Jun 02: M7
[384 empty] | EE1 | EE1 | EE1 | EE1 | EE1 | [12 empty] | D2 | D2 | D5 | D5 | Y2 | Y2 | Y2 | Y2 | CC | CC | CC | [10 empty] | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1
[410 empty] | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA
C4 CELL 3 Punchlist | bar: Jul 22 to Aug 02
| C4 CELL 4 Data Hall | Mar 15: X9; Mar 17: X21; Mar 18: X21; Mar 19: X21; Mar 20: D1; Mar 21: D1; Mar 22: D1; Mar 23: D1; Mar 24: D1; Mar 25: D2; Mar 26: D2; Mar 27: D2; Mar 28: D5; Mar 29: D5; Mar 30: D5; Mar 31: D5; Apr 01: Y2; Apr 02: Y2; Apr 03: Y2; Apr 04: X19; Apr 05: X19; Apr 06: X19; Apr 07: X19; Apr 08: X38; Apr 09: X38; Apr 10: Y7; Apr 11: Y7; Apr 14: CC; Apr 18: EE44; Apr 19: EE44; Apr 20: EE44; Apr 21: EE44; Apr 22: EE44; Apr 23: X35; Apr 24: X35; Apr 29: S2; Apr 30: S2; May 01: S2; May 02: S2; May 05: EE43; May 06: EE43; May 07: EE43; May 08: EE43; May 09: EE43; May 10: EE43; May 12: EE17; May 13: EE17; May 14: EE17; May 15: EE17; May 16: EE17; Jun 24: EE58; Jun 25: EE58; Jun 26: EE58
[367 empty] | R16 | R16 | R16 | R1 | R1 | R1 | X30 | X30 | [12 empty] | X26 | X26 | X26 | X26 | S1 | S1 | S1 | S1 | S1 | EE7 | EE7 | EE7 | EE7 | [8 empty] | S4 | S4 | S4 | S4
[370 empty] | EE1 | EE1 | EE1 | M5 | M5 | [19 empty] | EE39 | EE39 | EE39 | EE39 | EE39
[396 empty] | EE11 | EE11 | EE11 | EE11 | EE11 | EE11
| C4 CELL 4 Electrical Room | Mar 20: X21; Mar 21: X21; Mar 24: D1; Mar 25: D1; Mar 26: R17; Mar 27: R17; Mar 28: R1; Mar 29: R1; Mar 31: X30; Apr 01: EE35; Apr 02: EE35; Apr 04: CC; Apr 05: EE51; Apr 06: EE51; Apr 07: EE51; Apr 08: EE51; Apr 09: EE51; May 28: EE47.1; May 29: EE47.1; May 30: EE47.1; May 31: EE47.1; Jun 01: EE47.1; Jun 02: EE47.1; Jun 03: EE47.1; Jun 04: EE47.1; Jun 05: EE47.1; Jun 06: EE47.1; Jun 07: EE47.1; Jun 08: EE47.1; Jun 09: EE47.1; Jun 10: EE57; Jun 11: EE57; Jun 12: EE57; Jun 13: EE57
[368 empty] | D2 | D2 | D2 | D2 |  | D5 | D5 | Y2 | Y2 | [67 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[370 empty] | EE1 | EE1 | EE1 | EE1
| C4 CELL 4 Mechanical Gallery | Mar 28: R18; Mar 29: R18; Mar 31: R1; Apr 01: R1; Apr 03: M5; Apr 04: M5; Apr 05: M5; Apr 06: M5; Apr 07: M5; Apr 08: M5; Apr 09: M5; Apr 10: P4; Apr 11: P4; Apr 12: P4; Apr 13: P4; Apr 14: P4; Apr 15: P4; Apr 16: P4; Apr 17: P4; Apr 18: X30; Apr 19: X27; Apr 20: X27; Apr 21: X27; Apr 22: X27; Apr 23: X27; Apr 24: EE35; Apr 25: EE35; Apr 26: M6; Apr 27: M6; Apr 28: M6; Apr 29: M6; Apr 30: M6; May 01: EE48; May 02: EE48; May 03: EE48; May 04: EE48; May 05: EE48; May 06: EE48; May 07: EE48; May 08: EE48; May 09: EE48; May 10: EE48; May 11: EE48; May 12: EE48; May 13: EE48; May 14: EE48; May 15: EE48; May 16: M7; May 17: M7; May 18: M7; May 19: M7; May 20: M7
[373 empty] | EE1 | EE1 | EE1 | [13 empty] | D2 | D2 | D5 | D5 |  | Y2 | Y2 | CC | CC | CC | [11 empty] | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1
[397 empty] | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA
C4 CELL 4 Punchlist | bar: Jun 27 to Jul 10
Fitout COLO5 | C5 CELL 1 Data Hall | Mar 31: X9; Apr 01: X21; Apr 02: X21; Apr 03: X21; Apr 04: D1; Apr 05: D1; Apr 06: D1; Apr 07: D1; Apr 08: D2; Apr 09: D2; Apr 10: D2; Apr 11: D5; Apr 12: D5; Apr 13: D5; Apr 14: D5; Apr 15: D5; Apr 16: Y2; Apr 17: Y2; Apr 18: Y2; Apr 19: X19; Apr 20: X19; Apr 21: X19; Apr 22: X19; Apr 23: X38; Apr 24: X38; Apr 25: Y7; Apr 26: Y7; Apr 28: CC; May 02: EE44; May 03: EE44; May 04: EE44; May 05: EE44; May 06: EE44; May 07: EE44; May 08: X35; May 09: X35; May 14: S2; May 15: S2; May 16: S2; May 17: S2; May 19: EE43; May 20: EE43; May 21: EE43; May 22: EE43; May 23: EE43; May 27: EE17; May 28: EE17; May 29: EE17; May 30: EE17; May 31: EE17; Jun 02: EE58; Jun 03: EE58; Jun 04: EE58
[381 empty] | R19 | R19 | R19 | R1 | R1 | R1 | R1 | X30 | X30 | [11 empty] | X26 | X26 | X26 | X26 | S1 | S1 | S1 | S1 | S1 | S1 | EE7 | EE7 | EE7 | EE7 | EE7 | [6 empty] | S4 | S4 | S4 | S4
[384 empty] | EE1 | EE1 | EE1 | EE1 | M5 | M5 | [19 empty] | EE39 | EE39 | EE39 | EE39 | EE39
[411 empty] | EE11 | EE11 | EE11 | EE11 | EE11 | EE11
| C5 CELL 1 Electrical Room | Apr 04: X21; Apr 05: X21; Apr 07: D1; Apr 08: D1; Apr 09: R20; Apr 10: R20; Apr 11: R1; Apr 12: R1; Apr 13: R1; Apr 14: R1; Apr 15: X30; Apr 16: EE35; Apr 17: EE35; Apr 19: CC; Apr 21: EE51; Apr 22: EE51; Apr 23: EE51; Apr 24: EE51; Apr 25: EE51; Apr 26: EE51; Apr 27: EE51; Apr 28: EE51; Apr 29: EE51; Apr 30: EE51; May 01: EE51; May 02: EE47; May 03: EE47; May 04: EE47; May 05: EE47; May 06: EE47; May 07: EE47; May 08: EE47; May 09: EE47; May 10: EE47; May 11: EE47; May 12: EE47; May 13: EE47; May 14: EE47; May 15: EE47; May 16: EE57; May 17: EE57; May 18: EE57; May 19: EE57; May 20: EE57
[382 empty] | D2 | D2 | D2 | D2 | D2 | D2 | D5 | D5 | Y2 | Y2 | [27 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[384 empty] | EE1 | EE1 | EE1 | EE1 | EE1
| C5 CELL 1 Mechanical Gallery | Apr 11: R21; Apr 12: R21; Apr 13: R21; Apr 14: R21; Apr 15: R1; Apr 16: R1; Apr 18: M5; Apr 19: M5; Apr 20: M5; Apr 21: M5; Apr 22: M5; Apr 23: M5; Apr 24: M5; Apr 25: P4; Apr 26: P4; Apr 27: P4; Apr 28: P4; Apr 29: P4; Apr 30: P4; May 01: P4; May 02: X30; May 05: X27; May 06: X27; May 07: X27; May 08: X27; May 09: EE35; May 10: EE35; May 12: M6; May 13: M6; May 14: M6; May 15: M6; May 16: EE48; May 17: EE48; May 18: EE48; May 19: EE48; May 20: EE48; May 21: EE48; May 22: EE48; May 23: EE48; May 24: EE48; May 25: EE48; May 26: EE48; May 27: EE48; May 28: EE48; May 29: EE48; May 30: EE48; May 31: M7; Jun 01: M7; Jun 02: M7; Jun 03: M7; Jun 04: M7
[388 empty] | EE1 | EE1 | EE1 | [12 empty] | D2 | D2 | D5 | D5 | D5 | D5 | Y2 | Y2 | CC | CC | CC | [10 empty] | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1
[412 empty] | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA
C5 CELL 1 Punchlist | bar: Jun 05 to Jun 17
| C5 CELL 2 Data Hall | Apr 08: X9; Apr 09: X21; Apr 10: X21; Apr 11: X21; Apr 14: D1; Apr 15: D1; Apr 16: D1; Apr 17: D2; Apr 18: D2; Apr 19: D2; Apr 21: D5; Apr 22: D5; Apr 23: D5; Apr 24: Y2; Apr 25: Y2; Apr 26: Y2; Apr 28: X19; Apr 29: X19; Apr 30: X19; May 01: X38; May 02: X38; May 05: Y7; May 06: Y7; May 07: CC; May 12: EE44; May 13: EE44; May 14: EE44; May 15: EE44; May 16: X35; May 17: X35; May 22: S2; May 23: S2; May 24: S2; May 25: S2; May 26: S2; May 27: S2; May 28: EE43; May 29: EE43; May 30: EE43; May 31: EE43; Jun 01: EE43; Jun 02: EE43; Jun 03: EE43; Jun 04: EE17; Jun 05: EE17; Jun 06: EE17; Jun 07: EE17; Jun 08: EE17; Jun 09: EE17; Jun 25: EE58; Jun 26: EE58; Jun 27: EE58
[390 empty] | R22 | R22 | R22 |  | R1 | R1 | X30 | X30 | [12 empty] | X26 | X26 | X26 | X26 |  | S1 | S1 | S1 | S1 | EE7 | EE7 | EE7 | EE7 | EE7 | [7 empty] | S4 | S4 | S4 | S4
[394 empty] | EE1 | EE1 | M5 | M5 | [19 empty] | EE39 | EE39 | EE39 | EE39 | EE39 | EE39
[419 empty] | EE11 | EE11 | EE11 | EE11 | EE11 | EE11
| C5 CELL 2 Electrical Room | Apr 14: X21; Apr 15: X21; Apr 16: D1; Apr 17: D1; Apr 18: R23; Apr 19: R23; Apr 21: R1; Apr 22: R1; Apr 23: X30; Apr 24: EE35; Apr 25: EE35; Apr 28: CC; Apr 29: EE51; Apr 30: EE51; May 01: EE51; May 02: EE51; May 30: EE47; May 31: EE47; Jun 01: EE47; Jun 02: EE47; Jun 03: EE47; Jun 04: EE47; Jun 05: EE47; Jun 06: EE47; Jun 07: EE47; Jun 08: EE47; Jun 09: EE47; Jun 10: EE47; Jun 11: EE47; Jun 12: EE57; Jun 13: EE57; Jun 14: EE57; Jun 15: EE57; Jun 16: EE57; Jun 17: EE57
[391 empty] | D2 | D2 | D2 | D2 | D2 | D5 | D5 | Y2 | Y2 | [46 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[394 empty] | EE1 | EE1 | EE1
| C5 CELL 2 Mechanical Gallery | Apr 21: R24; Apr 22: R24; Apr 23: R1; Apr 24: R1; Apr 26: M5; Apr 27: M5; Apr 28: M5; Apr 29: M5; Apr 30: M5; May 01: M5; May 02: M5; May 05: P4; May 06: P4; May 07: P4; May 08: P4; May 09: P4; May 10: P4; May 12: X30; May 13: X27; May 14: X27; May 15: X27; May 16: X27; May 17: EE35; May 18: EE35; May 19: EE35; May 20: M6; May 21: M6; May 22: M6; May 23: M6; May 27: EE48; May 28: EE48; May 29: EE48; May 30: EE48; May 31: EE48; Jun 01: EE48; Jun 02: EE48; Jun 03: EE48; Jun 04: EE48; Jun 05: EE48; Jun 06: EE48; Jun 07: EE48; Jun 09: M7; Jun 10: M7; Jun 11: M7; Jun 12: M7
[396 empty] | EE1 | EE1 | EE1 | [13 empty] | D2 | D2 |  | D5 | D5 | Y2 | Y2 | CC | CC | CC | CC | [10 empty] | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1
[420 empty] | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA
C5 CELL 2 Punchlist | bar: Jun 28 to Jul 11
| C5 CELL 3 Data Hall | May 01: X9; May 02: X21; May 03: X21; May 04: X21; May 05: X21; May 06: X21; May 07: D1; May 08: D1; May 09: D1; May 10: D2; May 11: D2; May 12: D2; May 13: D2; May 14: D5; May 15: D5; May 16: D5; May 17: Y2; May 18: Y2; May 19: Y2; May 20: Y2; May 21: X19; May 22: X19; May 23: X19; May 27: X38; May 28: Y7; May 29: Y7; May 30: CC; Jun 04: EE44; Jun 05: EE44; Jun 06: EE44; Jun 07: EE44; Jun 09: X35; Jun 10: X35; Jun 16: S2; Jun 17: S2; Jun 18: S2; Jun 19: S2; Jun 20: EE43; Jun 21: EE43; Jun 22: EE43; Jun 23: EE43; Jun 24: EE43; Jun 25: EE43; Jun 26: EE43; Jun 27: EE17; Jun 28: EE17; Jun 29: EE17; Jun 30: EE17; Jul 01: EE17; Jul 02: EE17; Aug 06: EE58; Aug 07: EE58; Aug 08: EE58
[413 empty] | R25 | R25 | R25 | R25 | R1 | R1 | X30 | X30 | [12 empty] | X26 | X26 | X26 | X26 | X26 | S1 | S1 | S1 | S1 | S1 | EE7 | EE7 | EE7 | EE7 | [7 empty] | S4 | S4 | S4 | S4 | S4
[417 empty] | EE1 | EE1 | M5 | M5 | [19 empty] | EE39 | EE39 | EE39 | EE39 | EE39 | EE39
[443 empty] | EE11 | EE11 | EE11 | EE11 | EE11
| C5 CELL 3 Electrical Room | May 07: X21; May 08: X21; May 09: D1; May 10: D1; May 12: R26; May 13: R26; May 14: R1; May 15: R1; May 16: X30; May 17: EE35; May 18: EE35; May 19: EE35; May 21: CC; May 22: EE51; May 23: EE51; May 24: EE51; May 25: EE51; May 26: EE51; May 27: EE51; Jul 11: EE47.1; Jul 12: EE47.1; Jul 13: EE47.1; Jul 14: EE47.1; Jul 15: EE47.1; Jul 16: EE47.1; Jul 17: EE47.1; Jul 18: EE47.1; Jul 19: EE47.1; Jul 20: EE47.1; Jul 21: EE47.1; Jul 22: EE47.1; Jul 23: EE47.1; Jul 24: EE57; Jul 25: EE57; Jul 26: EE57; Jul 27: EE57; Jul 28: EE57; Jul 29: EE57
[415 empty] | D2 | D2 | D2 | D2 | D5 | D5 |  | Y2 | Y2 | [64 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[417 empty] | EE1 | EE1 | EE1
| C5 CELL 3 Mechanical Gallery | May 14: R27; May 15: R27; May 16: R1; May 17: R1; May 20: M5; May 21: M5; May 22: M5; May 23: M5; May 24: M5; May 25: M5; May 26: M5; May 27: M5; May 28: P4; May 29: P4; May 30: P4; May 31: P4; Jun 01: P4; Jun 02: P4; Jun 03: P4; Jun 04: X30; Jun 05: X27; Jun 06: X27; Jun 07: X27; Jun 08: X27; Jun 09: X27; Jun 10: EE35; Jun 11: EE35; Jun 12: M6; Jun 13: M6; Jun 14: M6; Jun 15: M6; Jun 16: M6; Jun 17: M6; Jun 18: EE48; Jun 19: EE48; Jun 20: EE48; Jun 21: EE48; Jun 22: EE48; Jun 23: EE48; Jun 24: EE48; Jun 25: EE48; Jun 26: EE48; Jun 27: EE48; Jun 28: EE48; Jun 29: EE48; Jun 30: EE48; Jul 01: EE48; Jul 02: M7; Jul 03: M7; Jul 04: M7; Jul 05: M7; Jul 06: M7; Jul 07: M7; Jul 08: M7
[419 empty] | EE1 | EE1 | EE1 | EE1 | [13 empty] | D2 | D2 | D5 | D5 | Y2 | Y2 |  | CC | CC | CC | [11 empty] | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1
[444 empty] | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA
C5 CELL 3 Punchlist | bar: Aug 09 to Aug 21
| C5 CELL 4 Data Hall | Apr 19: X9; Apr 21: X21; Apr 22: X21; Apr 23: X21; Apr 24: D1; Apr 25: D1; Apr 26: D1; Apr 28: D2; Apr 29: D2; Apr 30: D2; May 01: D5; May 02: D5; May 03: D5; May 04: D5; May 05: D5; May 06: Y2; May 07: Y2; May 08: Y2; May 09: X19; May 10: X19; May 11: X19; May 12: X19; May 13: X38; May 14: X38; May 15: Y7; May 16: Y7; May 17: CC; May 22: EE44; May 23: EE44; May 24: EE44; May 25: EE44; May 26: EE44; May 27: EE44; May 28: X35; May 29: X35; Jun 03: S2; Jun 04: S2; Jun 05: S2; Jun 06: S2; Jun 07: EE43; Jun 08: EE43; Jun 09: EE43; Jun 10: EE43; Jun 11: EE43; Jun 12: EE43; Jun 13: EE43; Jun 16: EE17; Jun 17: EE17; Jun 18: EE17; Jun 19: EE17; Jun 20: EE17; Jul 11: EE58; Jul 12: EE58; Jul 13: EE58; Jul 14: EE58
[401 empty] | R28 | R28 | R28 | R1 | R1 | R1 | R1 | X30 | X30 | [10 empty] | X26 | X26 | X26 | X26 | X26 | S1 | S1 | S1 | S1 | S1 | S1 | EE7 | EE7 | EE7 | EE7 | [6 empty] | S4 | S4 | S4 | S4 | S4
[404 empty] | EE1 | EE1 | EE1 | EE1 | M5 | M5 | [20 empty] | EE39 | EE39 | EE39 | EE39
[431 empty] | EE11 | EE11 | EE11 | EE11 | EE11 | EE11
| C5 CELL 4 Electrical Room | Apr 24: X21; Apr 25: X21; Apr 26: D1; Apr 27: D1; Apr 28: D1; Apr 29: R29; Apr 30: R29; May 01: R1; May 02: R1; May 05: X30; May 06: EE35; May 07: EE35; May 09: CC; May 10: EE51; May 11: EE51; May 12: EE51; May 13: EE51; May 14: EE51; Jun 12: EE47.1; Jun 13: EE47.1; Jun 14: EE47.1; Jun 15: EE47.1; Jun 16: EE47.1; Jun 17: EE47.1; Jun 18: EE47.1; Jun 19: EE47.1; Jun 20: EE47.1; Jun 21: EE47.1; Jun 22: EE47.1; Jun 23: EE47.1; Jun 24: EE47.1; Jun 25: EE47.1; Jun 26: EE57; Jun 27: EE57; Jun 28: EE57; Jun 29: EE57; Jun 30: EE57
[402 empty] | D2 | D2 | D2 | D2 |  |  | D5 | D5 | Y2 | Y2 | [48 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50
[404 empty] | EE1 | EE1 | EE1 | EE1 | EE1
| C5 CELL 4 Mechanical Gallery | May 01: R30; May 02: R30; May 05: R1; May 06: R1; May 08: M5; May 09: M5; May 10: M5; May 11: M5; May 12: M5; May 13: M5; May 14: M5; May 15: P4; May 16: P4; May 17: P4; May 18: P4; May 19: P4; May 20: P4; May 21: P4; May 22: X30; May 23: X27; May 24: X27; May 25: X27; May 26: X27; May 27: X27; May 28: X27; May 29: EE35; May 30: EE35; May 31: M6; Jun 01: M6; Jun 02: M6; Jun 03: M6; Jun 04: M6; Jun 05: EE48; Jun 06: EE48; Jun 07: EE48; Jun 08: EE48; Jun 09: EE48; Jun 10: EE48; Jun 11: EE48; Jun 12: EE48; Jun 13: EE48; Jun 14: EE48; Jun 15: EE48; Jun 16: EE48; Jun 17: EE48; Jun 18: EE48; Jun 19: EE48; Jun 20: M7; Jun 21: M7; Jun 22: M7; Jun 23: M7; Jun 24: M7
[408 empty] | EE1 | EE1 | EE1 | [12 empty] | D2 | D2 | D5 | D5 |  |  |  | Y2 | CC | CC | CC | [10 empty] | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1 | BA1
[432 empty] | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA | BA
C5 CELL 4 Punchlist | bar: Jul 15 to Jul 25
Electrical Yard | Admin/ COLO 3 | Jan 17: E23; Jan 18: E23; Jan 19: E23; Jan 20: E23; Jan 21: E23; Jan 22: E23; Jan 23: E23; Jan 24: E23; Jan 25: E23; Jan 26: E23; Jan 27: E23; Jan 28: E23; Jan 29: E24; Jan 30: E24; Jan 31: E24; Feb 01: E24; Feb 02: E24; Feb 03: E24; Feb 04: E24; Feb 05: E24; Feb 06: E24; Feb 07: E24; Feb 10: E25; Feb 11: E25; Feb 12: E25; Feb 13: E25; Feb 14: E25; Feb 15: E25; Feb 16: E25; Feb 17: E25; Feb 18: E25; Feb 19: E25; Feb 20: E26; Feb 21: E26; Feb 22: E26; Feb 23: E26; Feb 24: E26; Feb 25: E26; Feb 26: E26; Feb 27: E26; Feb 28: E26; Mar 01: E26; Mar 02: E26; Mar 03: E26; Mar 04: E28; Mar 05: E28; Mar 06: E28; Mar 07: E28; Mar 08: E28; Mar 09: E28; Mar 10: E28; Mar 11: E28; Mar 12: E28; Mar 13: E28; Mar 14: E28; Mar 15: E28
[346 empty] | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29
[346 empty] | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30
[346 empty] | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27
| Admin/ COLO 3 CELL 1 | Apr 25: E35; Apr 26: E35; Apr 27: E35; Apr 28: E35; Apr 29: E35; Apr 30: E35; May 01: E35; May 02: E35; May 03: E35; May 04: E35; May 05: E35
| Admin/ COLO 3 CELL 2 | May 06: E35; May 07: E35; May 08: E35; May 09: E35; May 10: E35; May 11: E35; May 12: E35; May 13: E35; May 14: E35
| Admin/ COLO 3 CELL 3 | May 27: E35; May 28: E35; May 29: E35; May 30: E35; May 31: E35; Jun 01: E35; Jun 02: E35; Jun 03: E35
| Admin/ COLO 3 CELL 4 | May 15: E35; May 16: E35; May 17: E35; May 18: E35; May 19: E35; May 20: E35; May 21: E35; May 22: E35; May 23: E35
| COLO 4 | Feb 21: E23; Feb 22: E23; Feb 23: E23; Feb 24: E23; Feb 25: E23; Feb 26: E23; Feb 27: E23; Feb 28: E23; Mar 01: E23; Mar 02: E23; Mar 03: E23; Mar 04: E23; Mar 05: E24; Mar 06: E24; Mar 07: E24; Mar 08: E24; Mar 09: E24; Mar 10: E24; Mar 11: E24; Mar 12: E24; Mar 13: E24; Mar 14: E24; Mar 15: E25; Mar 16: E25; Mar 17: E25; Mar 18: E25; Mar 19: E25; Mar 20: E25; Mar 21: E25; Mar 22: E25; Mar 23: E25; Mar 24: E25; Mar 25: E25; Mar 26: E25; Mar 27: E26; Mar 28: E26; Mar 29: E26; Mar 30: E26; Mar 31: E26; Apr 01: E26; Apr 02: E26; Apr 03: E26; Apr 04: E26; Apr 05: E26; Apr 11: E28; Apr 12: E28; Apr 13: E28; Apr 14: E28; Apr 15: E28; Apr 16: E28; Apr 17: E28; Apr 18: E28; Apr 19: E28; Apr 20: E28; Apr 21: E28; Apr 22: E28; Apr 23: E28; Apr 24: E28
[375 empty] | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29
[375 empty] | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30
[375 empty] | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27
| COLO 4 CELL 3 | May 27: E35; May 28: E35; May 29: E35; May 30: E35; May 31: E35; Jun 01: E35; Jun 02: E35; Jun 03: E35; Jun 04: E35
| COLO 4 CELL 4 | May 15: E35; May 16: E35; May 17: E35; May 18: E35; May 19: E35; May 20: E35; May 21: E35; May 22: E35; May 23: E35
| COLO 4 CELL1 | Apr 25: E35; Apr 26: E35; Apr 27: E35; Apr 28: E35; Apr 29: E35; Apr 30: E35; May 01: E35; May 02: E35; May 03: E35; May 04: E35; May 05: E35
| COLO 4 CELL2 | May 06: E35; May 07: E35; May 08: E35; May 09: E35; May 10: E35; May 11: E35; May 12: E35; May 13: E35; May 14: E35
| COLO 5 | Mar 28: E23; Mar 29: E23; Mar 30: E23; Mar 31: E23; Apr 01: E23; Apr 02: E23; Apr 03: E23; Apr 04: E23; Apr 05: E23; Apr 06: E23; Apr 07: E23; Apr 08: E24; Apr 09: E24; Apr 10: E24; Apr 11: E24; Apr 12: E24; Apr 13: E24; Apr 14: E24; Apr 15: E24; Apr 16: E24; Apr 17: E24; Apr 18: E24; Apr 19: E25; Apr 20: E25; Apr 21: E25; Apr 22: E25; Apr 23: E25; Apr 24: E25; Apr 25: E25; Apr 26: E25; Apr 27: E25; Apr 28: E25; Apr 29: E25; Apr 30: E26; May 01: E26; May 02: E26; May 03: E26; May 04: E26; May 05: E26; May 06: E26; May 07: E26; May 08: E26; May 09: E26; May 10: E26; May 12: E27; May 13: E27; May 14: E27; May 15: E27; May 16: E27; May 17: E27; May 18: E27; May 19: E27; May 20: E27; May 21: E27; May 22: E27; May 23: E27
[417 empty] | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30
[419 empty] | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E29
[422 empty] | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28
| COLO 5 CELL 1 | May 30: E41; May 31: E41; Jun 01: E41; Jun 02: E41; Jun 03: E41
| COLO 5 CELL 2 | May 13: E40; May 14: E40; May 15: E40; May 16: E40; May 17: E40; May 18: E40; May 19: E40; May 20: E40; May 21: E40; Jun 04: E41; Jun 05: E41; Jun 06: E41; Jun 07: E41
| COLO 5 CELL 3 | Jun 02: E40; Jun 03: E40; Jun 04: E40; Jun 05: E40; Jun 06: E40; Jun 07: E40; Jun 08: E40; Jun 09: E40; Jun 10: E40; Jun 13: E41; Jun 14: E41; Jun 15: E41; Jun 16: E41; Jun 17: E41; Jun 18: E41
| COLO 5 CELL 4 | May 22: E40; May 23: E40; May 24: E40; May 25: E40; May 26: E40; May 27: E40; May 28: E40; May 29: E40; May 30: E40; May 31: E40; Jun 09: E41; Jun 10: E41; Jun 11: E41; Jun 12: E41
| COLO 5 CELL1 | May 02: E40; May 03: E40; May 04: E40; May 05: E40; May 06: E40; May 07: E40; May 08: E40; May 09: E40; May 10: E40; May 11: E40; May 12: E40
Commissioning (L2 - L5) COLO3 | C3 Energizations & Startups (Level 3) | Jun 19: E19; Jun 20: E19; Jun 21: E19; Jun 22: E19; Jun 23: E19; Jun 24: E19
| C3 Energizations & Startups (Level 3) CELL 1 | Jun 04: E22; Jun 05: E22; Jun 06: E22; Jun 07: E22; Jun 08: E22; Jun 09: E22; Jun 10: E22; Jun 11: E22; Jun 12: E22; Jun 13: E21; Jun 14: E21; Jun 15: E21; Jun 16: E21; Jun 17: E21; Jun 18: E21; Jun 19: E21; Jun 20: E21; Jun 21: E21; Jun 22: E21; Jun 23: E21; Jun 25: E20; Jun 26: E20; Jun 27: E20; Jun 28: E20; Jun 30: E15; Jul 01: E15; Jul 02: E15; Jul 03: E15; Jul 04: E15; Jul 05: E15; Jul 06: E15; Jul 07: E15; Jul 08: E15; Jul 09: E15; Jul 10: E15; Jul 11: E15; Jul 12: E15; Jul 13: E15; Jul 14: E15; Jul 15: E15; Jul 16: E16; Jul 17: E16; Jul 18: E16; Jul 19: E16
| C3 Energizations & Startups (Level 3) CELL 2 | Jun 09: E22; Jun 10: E22; Jun 11: E22; Jun 12: E22; Jun 13: E22; Jun 14: E22; Jun 15: E22; Jun 16: E22; Jun 17: E22; Jun 18: E22; Jun 19: E21; Jun 20: E21; Jun 21: E21; Jun 22: E21; Jun 23: E21; Jun 24: E21; Jun 25: E21; Jun 26: E21; Jun 27: E21; Jun 28: E20; Jun 29: E20; Jun 30: E20; Jul 01: E20; Jul 02: E20; Jul 03: E15; Jul 04: E15; Jul 05: E15; Jul 06: E15; Jul 07: E15; Jul 08: E15; Jul 09: E15; Jul 10: E15; Jul 11: E15; Jul 12: E15; Jul 13: E15; Jul 14: E15; Jul 15: E15; Jul 16: E15; Jul 17: E15; Jul 18: E15; Jul 21: E16; Jul 22: E16; Jul 23: E16; Jul 24: E16
| C3 Energizations & Startups (Level 3) CELL 3 | Jun 24: E22; Jun 25: E22; Jun 26: E22; Jun 27: E22; Jun 28: E22; Jun 29: E22; Jun 30: E22; Jul 01: E22; Jul 02: E22; Jul 03: E22; Jul 04: E22; Jul 05: E22; Jul 06: E22; Jul 07: E22; Jul 08: E21; Jul 09: E21; Jul 10: E21; Jul 11: E21; Jul 12: E21; Jul 13: E21; Jul 14: E21; Jul 15: E21; Jul 16: E21; Jul 17: E21; Jul 18: E21; Jul 19: E20; Jul 20: E20; Jul 21: E20; Jul 22: E20; Jul 23: E20; Jul 24: E20; Jul 25: E15; Jul 26: E15; Jul 27: E15; Jul 28: E15; Jul 29: E15; Jul 30: E15; Jul 31: E15; Aug 01: E15; Aug 02: E15; Aug 03: E15; Aug 04: E15; Aug 05: E15; Aug 06: E15; Aug 07: E15; Aug 08: E15; Aug 09: E16; Aug 10: E16; Aug 11: E16; Aug 12: E16; Aug 13: E16; Aug 14: E16
| C3 Energizations & Startups (Level 3) CELL 4 | Jun 13: E22; Jun 14: E22; Jun 15: E22; Jun 16: E22; Jun 17: E22; Jun 18: E22; Jun 19: E22; Jun 20: E22; Jun 21: E22; Jun 22: E22; Jun 23: E22; Jun 24: E21; Jun 25: E21; Jun 26: E21; Jun 27: E21; Jun 28: E21; Jun 29: E21; Jun 30: E21; Jul 01: E21; Jul 02: E21; Jul 03: E20; Jul 04: E20; Jul 05: E20; Jul 06: E20; Jul 07: E20; Jul 08: E20; Jul 09: E20; Jul 10: E15; Jul 11: E15; Jul 12: E15; Jul 13: E15; Jul 14: E15; Jul 15: E15; Jul 16: E15; Jul 17: E15; Jul 18: E15; Jul 19: E15; Jul 20: E15; Jul 21: E15; Jul 22: E15; Jul 23: E15; Jul 25: E16; Jul 26: E16; Jul 27: E16; Jul 28: E16; Jul 29: E16; Jul 30: E16
C3 Functional Testing (Level 4) | bar: Aug 15 to Sep 15
C3 Functional Testing (Level 5) | bar: Sep 16 to Sep 18
| C3 Yellow Tags (Level 2) CELL 1 | May 05: EE24; May 06: EE24; May 07: EE24; May 08: EE24; May 09: EE24; May 10: EE24; May 11: EE24; May 12: EE24; May 13: EE24; May 14: EE24; May 15: EE24; May 16: EE24; May 17: EE24; May 18: EE24; May 19: EE24; May 20: EE24; May 21: EE24; May 22: EE24; May 23: EE24; May 24: EE24; May 25: EE24; May 26: EE24; May 27: EE24; May 28: EE24
| C3 Yellow Tags (Level 2) CELL 2 | May 15: EE24; May 16: EE24; May 17: EE24; May 18: EE24; May 19: EE24; May 20: EE24; May 21: EE24; May 22: EE24; May 23: EE24; May 24: EE24; May 25: EE24; May 26: EE24; May 27: EE24; May 28: EE24; May 29: EE24; May 30: EE24; May 31: EE24; Jun 01: EE24; Jun 02: EE24; Jun 03: EE24; Jun 04: EE24; Jun 05: EE24; Jun 06: EE24; Jun 07: EE24
| C3 Yellow Tags (Level 2) CELL 3 | Jun 09: EE24; Jun 10: EE24; Jun 11: EE24; Jun 12: EE24; Jun 13: EE24; Jun 14: EE24; Jun 15: EE24; Jun 16: EE24; Jun 17: EE24; Jun 18: EE24; Jun 19: EE24; Jun 20: EE24; Jun 21: EE24; Jun 22: EE24; Jun 23: EE24; Jun 24: EE24; Jun 25: EE24; Jun 26: EE24; Jun 27: EE24; Jun 28: EE24; Jun 29: EE24; Jun 30: EE24; Jul 01: EE24; Jul 02: EE24
| C3 Yellow Tags (Level 2) CELL 4 | May 27: EE24; May 28: EE24; May 29: EE24; May 30: EE24; May 31: EE24; Jun 01: EE24; Jun 02: EE24; Jun 03: EE24; Jun 04: EE24; Jun 05: EE24; Jun 06: EE24; Jun 07: EE24; Jun 08: EE24; Jun 09: EE24; Jun 10: EE24; Jun 11: EE24; Jun 12: EE24; Jun 13: EE24; Jun 14: EE24; Jun 15: EE24; Jun 16: EE24; Jun 17: EE24; Jun 18: EE24
Commissioning (L2 - L5) COLO4 | C4 Energizations & Startups (Level 3) CELL 1 | Jun 20: E22; Jun 21: E22; Jun 22: E22; Jun 23: E22; Jun 24: E22; Jun 25: E22; Jun 26: E22; Jun 27: E22; Jun 28: E22; Jun 30: E21; Jul 01: E21; Jul 02: E21; Jul 03: E21; Jul 04: E21; Jul 05: E21; Jul 06: E21; Jul 07: E21; Jul 08: E21; Jul 09: E21; Jul 10: E21; Jul 11: E20; Jul 12: E20; Jul 13: E20; Jul 14: E20; Jul 15: E20; Jul 16: E15; Jul 17: E15; Jul 18: E15; Jul 19: E15; Jul 20: E15; Jul 21: E15; Jul 22: E15; Jul 23: E15; Jul 24: E15; Jul 25: E15; Jul 26: E15; Jul 27: E15; Jul 28: E15; Jul 29: E15; Jul 30: E15; Jul 31: E16; Aug 01: E16; Aug 02: E16; Aug 03: E16; Aug 04: E16
| C4 Energizations & Startups (Level 3) CELL 2 | Jun 25: E22; Jun 26: E22; Jun 27: E22; Jun 28: E22; Jun 29: E22; Jun 30: E22; Jul 01: E22; Jul 02: E22; Jul 03: E22; Jul 07: E21; Jul 08: E21; Jul 09: E21; Jul 10: E21; Jul 11: E21; Jul 12: E21; Jul 13: E21; Jul 14: E21; Jul 15: E21; Jul 16: E20; Jul 17: E20; Jul 18: E20; Jul 19: E20; Jul 21: E15; Jul 22: E15; Jul 23: E15; Jul 24: E15; Jul 25: E15; Jul 26: E15; Jul 27: E15; Jul 28: E15; Jul 29: E15; Jul 30: E15; Jul 31: E15; Aug 01: E15; Aug 02: E15; Aug 03: E15; Aug 04: E15; Aug 05: E16; Aug 06: E16; Aug 07: E16; Aug 08: E16
| C4 Energizations & Startups (Level 3) CELL 3 | Aug 06: E22; Aug 07: E22; Aug 08: E22; Aug 09: E22; Aug 10: E22; Aug 11: E22; Aug 12: E22; Aug 13: E22; Aug 14: E22; Aug 15: E21; Aug 16: E21; Aug 17: E21; Aug 18: E21; Aug 19: E21; Aug 20: E21; Aug 21: E21; Aug 22: E21; Aug 23: E21; Aug 24: E21; Aug 25: E21; Aug 26: E20; Aug 27: E20; Aug 28: E20; Aug 29: E20; Aug 30: E15; Aug 31: E15; Sep 01: E15; Sep 02: E15; Sep 03: E15; Sep 04: E15; Sep 05: E15; Sep 06: E15; Sep 07: E15; Sep 08: E15; Sep 09: E15; Sep 10: E15; Sep 11: E15; Sep 12: E15; Sep 13: E15; Sep 14: E15; Sep 15: E15; Sep 16: E16; Sep 17: E16; Sep 18: E16; Sep 19: E16
| C4 Energizations & Startups (Level 3) CELL 4 | Jul 18: E22; Jul 19: E22; Jul 20: E22; Jul 21: E22; Jul 22: E22; Jul 23: E22; Jul 24: E22; Jul 25: E22; Jul 26: E22; Jul 27: E22; Jul 28: E22; Jul 29: E21; Jul 30: E21; Jul 31: E21; Aug 01: E21; Aug 02: E21; Aug 03: E21; Aug 04: E21; Aug 05: E21; Aug 06: E21; Aug 07: E20; Aug 08: E20; Aug 09: E20; Aug 10: E20; Aug 11: E20; Aug 12: E15; Aug 13: E15; Aug 14: E15; Aug 15: E15; Aug 16: E15; Aug 17: E15; Aug 18: E15; Aug 19: E15; Aug 20: E15; Aug 21: E15; Aug 22: E15; Aug 23: E15; Aug 24: E15; Aug 25: E15; Aug 26: E15; Aug 27: E16; Aug 28: E16; Aug 29: E16; Aug 30: E16
C4 Functional Testing (Level 4) | bar: Sep 20 to Oct 16
C4 Functional Testing (Level 5) | bar: Oct 17 to Oct 20
| C4 Yellow Tags (Level 2) CELL 1 | May 06: EE24; May 07: EE24; May 08: EE24; May 09: EE24; May 10: EE24; May 11: EE24; May 12: EE24; May 13: EE24; May 14: EE24; May 15: EE24; May 16: EE24; May 17: EE24; May 18: EE24; May 19: EE24; May 20: EE24; May 21: EE24; May 22: EE24; May 23: EE24; May 24: EE24; May 25: EE24; May 26: EE24; May 27: EE24; May 28: EE24; May 29: EE24
| C4 Yellow Tags (Level 2) CELL 2 | May 31: EE24; Jun 01: EE24; Jun 02: EE24; Jun 03: EE24; Jun 04: EE24; Jun 05: EE24; Jun 06: EE24; Jun 07: EE24; Jun 08: EE24; Jun 09: EE24; Jun 10: EE24; Jun 11: EE24; Jun 12: EE24; Jun 13: EE24; Jun 14: EE24; Jun 15: EE24; Jun 16: EE24; Jun 17: EE24; Jun 18: EE24; Jun 19: EE24; Jun 20: EE24; Jun 21: EE24; Jun 22: EE24; Jun 23: EE24; Jun 24: EE24
| C4 Yellow Tags (Level 2) CELL 3 | Jul 22: EE24; Jul 23: EE24; Jul 24: EE24; Jul 25: EE24; Jul 26: EE24; Jul 27: EE24; Jul 28: EE24; Jul 29: EE24; Jul 30: EE24; Jul 31: EE24; Aug 01: EE24; Aug 02: EE24; Aug 03: EE24; Aug 04: EE24; Aug 05: EE24; Aug 06: EE24; Aug 07: EE24; Aug 08: EE24; Aug 09: EE24; Aug 10: EE24; Aug 11: EE24; Aug 12: EE24; Aug 13: EE24; Aug 14: EE24
| C4 Yellow Tags (Level 2) CELL 4 | Jun 27: EE24; Jun 28: EE24; Jun 29: EE24; Jun 30: EE24; Jul 01: EE24; Jul 02: EE24; Jul 03: EE24; Jul 04: EE24; Jul 05: EE24; Jul 06: EE24; Jul 07: EE24; Jul 08: EE24; Jul 09: EE24; Jul 10: EE24; Jul 11: EE24; Jul 12: EE24; Jul 13: EE24; Jul 14: EE24; Jul 15: EE24; Jul 16: EE24; Jul 17: EE24; Jul 18: EE24; Jul 19: EE24; Jul 20: EE24; Jul 21: EE24; Jul 22: EE24
Commissioning (L2 - L5) COLO5 | C5 Energizations & Startups (Level 3) CELL 1 | Jul 19: E22; Jul 20: E22; Jul 21: E22; Jul 22: E22; Jul 23: E22; Jul 24: E22; Jul 25: E22; Jul 26: E22; Jul 27: E22; Jul 28: E22; Jul 29: E22; Jul 30: E21; Jul 31: E21; Aug 01: E21; Aug 02: E21; Aug 03: E21; Aug 04: E21; Aug 05: E21; Aug 06: E21; Aug 07: E21; Aug 08: E20; Aug 09: E20; Aug 10: E20; Aug 11: E20; Aug 12: E20; Aug 13: E15; Aug 14: E15; Aug 15: E15; Aug 16: E15; Aug 17: E15; Aug 18: E15; Aug 19: E15; Aug 20: E15; Aug 21: E15; Aug 22: E15; Aug 23: E15; Aug 24: E15; Aug 25: E15; Aug 26: E15; Aug 27: E15; Aug 28: E16; Aug 29: E16; Aug 30: E16; Aug 31: E16; Sep 01: E16; Sep 02: E16
| C5 Energizations & Startups (Level 3) CELL 2 | Jul 24: E22; Jul 25: E22; Jul 26: E22; Jul 27: E22; Jul 28: E22; Jul 29: E22; Jul 30: E22; Jul 31: E22; Aug 01: E22; Aug 02: E22; Aug 04: E21; Aug 05: E21; Aug 06: E21; Aug 07: E21; Aug 08: E21; Aug 09: E21; Aug 10: E21; Aug 11: E21; Aug 12: E21; Aug 13: E20; Aug 14: E20; Aug 15: E20; Aug 16: E20; Aug 17: E20; Aug 18: E20; Aug 19: E15; Aug 20: E15; Aug 21: E15; Aug 22: E15; Aug 23: E15; Aug 24: E15; Aug 25: E15; Aug 26: E15; Aug 27: E15; Aug 28: E15; Aug 29: E15; Aug 30: E15; Aug 31: E15; Sep 01: E15; Sep 02: E15; Sep 03: E16; Sep 04: E16; Sep 05: E16; Sep 06: E16; Sep 07: E16; Sep 08: E16
| C5 Energizations & Startups (Level 3) CELL 3 | Aug 25: E22; Aug 26: E22; Aug 27: E22; Aug 28: E22; Aug 29: E22; Aug 30: E22; Aug 31: E22; Sep 01: E22; Sep 02: E22; Sep 03: E22; Sep 04: E21; Sep 05: E21; Sep 06: E21; Sep 07: E21; Sep 08: E21; Sep 09: E21; Sep 10: E21; Sep 11: E21; Sep 12: E21; Sep 13: E21; Sep 15: E20; Sep 16: E20; Sep 17: E20; Sep 18: E20; Sep 19: E20; Sep 20: E15; Sep 21: E15; Sep 22: E15; Sep 23: E15; Sep 24: E15; Sep 25: E15; Sep 26: E15; Sep 27: E15; Sep 28: E15; Sep 29: E15; Sep 30: E15; Oct 01: E15; Oct 02: E15; Oct 03: E15; Oct 04: E15; Oct 06: E16; Oct 07: E16; Oct 08: E16; Oct 09: E16; Oct 10: E16; Oct 11: E16
| C5 Energizations & Startups (Level 3) CELL 4 | Aug 04: E22; Aug 05: E22; Aug 06: E22; Aug 07: E22; Aug 08: E22; Aug 09: E22; Aug 10: E22; Aug 11: E22; Aug 12: E22; Aug 13: E21; Aug 14: E21; Aug 15: E21; Aug 16: E21; Aug 17: E21; Aug 18: E21; Aug 19: E21; Aug 20: E21; Aug 21: E21; Aug 22: E21; Aug 23: E20; Aug 24: E20; Aug 25: E20; Aug 26: E20; Aug 27: E20; Aug 28: E15; Aug 29: E15; Aug 30: E15; Aug 31: E15; Sep 01: E15; Sep 02: E15; Sep 03: E15; Sep 04: E15; Sep 05: E15; Sep 06: E15; Sep 07: E15; Sep 08: E15; Sep 09: E15; Sep 10: E15; Sep 11: E15; Sep 12: E15; Sep 13: E16; Sep 14: E16; Sep 15: E16; Sep 16: E16; Sep 17: E16
C5 Functional Testing (Level 4) | bar: Oct 17 to Nov 15
C5 Functional Testing (Level 5) | bar: Nov 17 to Nov 19
| C5 Yellow Tags (Level 2) CELL 1 | Jun 05: EE24; Jun 06: EE24; Jun 07: EE24; Jun 08: EE24; Jun 09: EE24; Jun 10: EE24; Jun 11: EE24; Jun 12: EE24; Jun 13: EE24; Jun 14: EE24; Jun 15: EE24; Jun 16: EE24; Jun 17: EE24; Jun 18: EE24; Jun 19: EE24; Jun 20: EE24; Jun 21: EE24; Jun 22: EE24; Jun 23: EE24; Jun 24: EE24; Jun 25: EE24; Jun 26: EE24; Jun 27: EE24; Jun 28: EE24
| C5 Yellow Tags (Level 2) CELL 2 | Jun 28: EE24; Jun 29: EE24; Jun 30: EE24; Jul 01: EE24; Jul 02: EE24; Jul 03: EE24; Jul 04: EE24; Jul 05: EE24; Jul 06: EE24; Jul 07: EE24; Jul 08: EE24; Jul 09: EE24; Jul 10: EE24; Jul 11: EE24; Jul 12: EE24; Jul 13: EE24; Jul 14: EE24; Jul 15: EE24; Jul 16: EE24; Jul 17: EE24; Jul 18: EE24; Jul 19: EE24; Jul 20: EE24; Jul 21: EE24; Jul 22: EE24; Jul 23: EE24
| C5 Yellow Tags (Level 2) CELL 3 | Aug 09: EE24; Aug 10: EE24; Aug 11: EE24; Aug 12: EE24; Aug 13: EE24; Aug 14: EE24; Aug 15: EE24; Aug 16: EE24; Aug 17: EE24; Aug 18: EE24; Aug 19: EE24; Aug 20: EE24; Aug 21: EE24; Aug 22: EE24; Aug 23: EE24; Aug 24: EE24; Aug 25: EE24; Aug 26: EE24; Aug 27: EE24; Aug 28: EE24; Aug 29: EE24; Aug 30: EE24; Aug 31: EE24; Sep 01: EE24; Sep 02: EE24; Sep 03: EE24
| C5 Yellow Tags (Level 2) CELL 4 | Jul 15: EE24; Jul 16: EE24; Jul 17: EE24; Jul 18: EE24; Jul 19: EE24; Jul 20: EE24; Jul 21: EE24; Jul 22: EE24; Jul 23: EE24; Jul 24: EE24; Jul 25: EE24; Jul 26: EE24; Jul 27: EE24; Jul 28: EE24; Jul 29: EE24; Jul 30: EE24; Jul 31: EE24; Aug 01: EE24; Aug 02: EE24; Aug 03: EE24; Aug 04: EE24; Aug 05: EE24; Aug 06: EE24; Aug 07: EE24
Note on BY5: Activity Name: ARL & Subcontractor Awards Phase: Procurement Location: Early Awards Trade: Procure Start Date: 07-Jun-2024 End Date: 07-Sep-2024
Note on BY6: Activity Name: Buyouts & Early Procurement Phase: Procurement Location: Early Awards Trade: Procure Start Date: 07-Jun-2024 End Date: 30-Sep-2024
Note on EH7: Activity Name: MV Metering Cabinet - Substitute [43 Weeks] Phase: Procurement MSFT OFCI ROJ CFCI (Critical Only) Location: CFCI (Critical Only) Trade: Procure Start Date: 07-Aug-2024 End Date: 18-Jun-2025
Note on EH8: Activity Name: MV Metering Cabinet - *Not Used* [65 Weeks] - Not Tied Phase: Procurement MSFT OFCI ROJ CFCI (Critical Only) Location: CFCI (Critical Only) Trade: Procure Start Date: 07-Aug-2024 End Date: 21-Nov-2025
Note on ER9: Activity Name: CFCI- MV Cables Fabrication/ Lead Time Phase: Procurement MSFT OFCI ROJ CFCI (Critical Only) Location: CFCI (Critical Only) Trade: Procure Start Date: 17-Aug-2024 End Date: 24-Apr-2025
Note on ID10: Activity Name: HACs Fabrication/ Lead Time Phase: Procurement MSFT OFCI ROJ CFCI (Critical Only) Location: CFCI (Critical Only) Trade: Procure Start Date: 15-Nov-2024 End Date: 05-Dec-2024
Note on ID11: Activity Name: Cable Bus Fabrication/ Lead Time Phase: Procurement MSFT OFCI ROJ CFCI (Critical Only) Location: CFCI (Critical Only) Trade: Procure Start Date: 15-Nov-2024 End Date: 03-Mar-2025
Note on GS12: Activity Name: Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/04/24) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Air Handling Units Trade: Procure Start Date: 09-Oct-2024 End Date: 09-Oct-2024
Note on MN12: Activity Name: Air Handling Units (AHU) (Stulz) Shipped/ROJ Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Air Handling Units Trade: Procure Start Date: 09-Mar-2025 End Date: 13-Mar-2025
Note on MR13: Activity Name: Air Handling Units (AHU) (Stulz) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Air Handling Units Trade: Procure Start Date: 13-Mar-2025 End Date: 13-Mar-2025
Note on MM15: Activity Name: Auto Transfer Control Panel (TCP) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Auto Transfer Control Panel Trade: Procure Start Date: 08-Mar-2025 End Date: 08-Mar-2025
Note on MM16: Activity Name: Receive Auto Transfer Control Panel (TCP) (Del Date- 3/8/2025) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Auto Transfer Control Panel Trade: Procure Start Date: 08-Mar-2025 End Date: 08-Mar-2025
Note on ID18: Activity Name: Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 4/30/24) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Automatic Transfer Switches Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on LV18: Activity Name: Automatic Transfer Switches (ATS) (Schneider) Shipping/ ROJ Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Automatic Transfer Switches Trade: Procure Start Date: 19-Feb-2025 End Date: 23-Feb-2025
Note on LZ19: Activity Name: Automatic Transfer Switches (ATS) (Schneider) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Automatic Transfer Switches Trade: Procure Start Date: 23-Feb-2025 End Date: 23-Feb-2025
Note on MM21: Activity Name: Auxillary (Mech) Power Distribution Panels (ADP) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Auxillary Power Distribution Trade: Procure Start Date: 08-Mar-2025 End Date: 08-Mar-2025
Note on MM22: Activity Name: Receive Auxillary (Mech) Power Distribution Panels (ADP) (Del Date- 3/8/2025) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Auxillary Power Distribution Trade: Procure Start Date: 08-Mar-2025 End Date: 08-Mar-2025
Note on IS24: Activity Name: Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 11/28/24) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Building Automation System Trade: Procure Start Date: 30-Nov-2024 End Date: 30-Nov-2024
Note on LV24: Activity Name: Admin/C03- OFCI- Building Automation System (BAS) (ALC) Shipping/ ROJ Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Building Automation System Trade: Procure Start Date: 19-Feb-2025 End Date: 23-Feb-2025
Note on LZ25: Activity Name: Building Automation System (BAS) (ALC) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Building Automation System Trade: Procure Start Date: 23-Feb-2025 End Date: 23-Feb-2025
Note on R27: Activity Name: Receive Busway / Busplugs (Starline Holding) (Del Date- 1/25/24) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Busway / Busplugs Trade: Procure Start Date: 09-Apr-2024 End Date: 09-Apr-2024
Note on LV27: Activity Name: Busway / Busplugs (Starline Holding) Shipping/ ROJ Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Busway / Busplugs Trade: Procure Start Date: 19-Feb-2025 End Date: 23-Feb-2025
Note on LZ28: Activity Name: Busway / Busplugs (Starline Holding) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Busway / Busplugs Trade: Procure Start Date: 23-Feb-2025 End Date: 23-Feb-2025
Note on ID30: Activity Name: Receive Elec. Performance Monitoring System (EPMS) (Schneider) (SOW Del Date- 4/30/24) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Elec Performance Monitoring System Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on LV30: Activity Name: Elec. Performance Monitoring System (EPMS) (Schneider) Shipping/ ROJ Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Elec Performance Monitoring System Trade: Procure Start Date: 19-Feb-2025 End Date: 23-Feb-2025
Note on LZ31: Activity Name: Elec. Performance Monitoring System (EPMS) (Schneider) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Elec Performance Monitoring System Trade: Procure Start Date: 23-Feb-2025 End Date: 23-Feb-2025
Note on ID33: Activity Name: Receive HAC/Racking (Tate Access) (SOW Del Date- 5/17/24) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 HAC/Racking Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on LV33: Activity Name: HAC/Racking (Tate Access) Shipping/ ROJ Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 HAC/Racking Trade: Procure Start Date: 19-Feb-2025 End Date: 21-Feb-2025
Note on LX34: Activity Name: HAC/Racking (Tate Access) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 HAC/Racking Trade: Procure Start Date: 21-Feb-2025 End Date: 21-Feb-2025
Note on ME36: Activity Name: Receive LV Switchgear (LVS) (Eaton) (SOW Del Date- 2/28/25) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 LV Switchgear Trade: Procure Start Date: 28-Feb-2025 End Date: 28-Feb-2025
Note on MI36: Activity Name: LV Switchgear (LVS) (Eaton) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 LV Switchgear Trade: Procure Start Date: 04-Mar-2025 End Date: 04-Mar-2025
Note on ME37: Activity Name: LV Switchgear (LVS) (Eaton) Shipping/ ROJ Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 LV Switchgear Trade: Procure Start Date: 28-Feb-2025 End Date: 04-Mar-2025
Note on MM39: Activity Name: Main LV Switch Board (MSB) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Main LV Switch Board Trade: Procure Start Date: 08-Mar-2025 End Date: 08-Mar-2025
Note on MM40: Activity Name: Receive Main LV Switch Board (MSB) (SOW Del Date- 3/8/2025) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Main LV Switch Board Trade: Procure Start Date: 08-Mar-2025 End Date: 08-Mar-2025
Note on GY42: Activity Name: Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 7/30/24) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Medium Voltage Switchgear Trade: Procure Start Date: 15-Oct-2024 End Date: 15-Oct-2024
Note on LV42: Activity Name: Medium Voltage Switchgear (MVS) (JD Power Sys) Shipping/ ROJ Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Medium Voltage Switchgear Trade: Procure Start Date: 19-Feb-2025 End Date: 23-Feb-2025
Note on LZ43: Activity Name: Medium Voltage Switchgear (MVS) (JD Power Sys) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Medium Voltage Switchgear Trade: Procure Start Date: 23-Feb-2025 End Date: 23-Feb-2025
Note on GX45: Activity Name: PEMB Procurement (1st Del) (Nucor) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 PEMB Procurement (1st Del) Trade: Procure Start Date: 14-Oct-2024 End Date: 14-Oct-2024
Note on GX46: Activity Name: Receive PEMB Procurement (1st Del) (Nucor) (SOW Del Date-10/3/24) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 PEMB Procurement (1st Del) Trade: Procure Start Date: 14-Oct-2024 End Date: 14-Oct-2024
Note on ID48: Activity Name: Receive Packaged Diesel Generator Set (CAT Holt) (SOW Del Date- 5/14/24) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Packaged Diesel Generator Set Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on LW48: Activity Name: Packaged Diesel Generator Set (CAT Holt) Shipping/ ROJ Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Packaged Diesel Generator Set Trade: Procure Start Date: 20-Feb-2025 End Date: 24-Feb-2025
Note on MA49: Activity Name: Packaged Diesel Generator Set (CAT Holt) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Packaged Diesel Generator Set Trade: Procure Start Date: 24-Feb-2025 End Date: 24-Feb-2025
Note on ID51: Activity Name: Receive Pad Mounted Transformers (XFM-TX) (Del Date- 7/30/2024) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Pad Mounted Transformers Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on LV51: Activity Name: Pad Mounted Transformers (XFM-TX) Shipping/ ROJ Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Pad Mounted Transformers Trade: Procure Start Date: 19-Feb-2025 End Date: 23-Feb-2025
Note on LZ52: Activity Name: Pad Mounted Transformers (XFM-TX) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Pad Mounted Transformers Trade: Procure Start Date: 23-Feb-2025 End Date: 23-Feb-2025
Note on ID54: Activity Name: Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 4/30/24) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Power Distribution Units Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on LV54: Activity Name: Power Distribution Units (PDU) Shipping/ ROJ Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Power Distribution Units Trade: Procure Start Date: 19-Feb-2025 End Date: 23-Feb-2025
Note on LZ55: Activity Name: Power Distribution Units (PDU) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Power Distribution Units Trade: Procure Start Date: 23-Feb-2025 End Date: 23-Feb-2025
Note on FH57: Activity Name: Admin/C03- OFCI- Received SUB Warehouse 9/28/2023 UPS System w/ Battery (UPS) (Eaton) (SOW Del Date- 8/13/23) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 UPS System W / Battery Trade: Procure Start Date: 02-Sep-2024 End Date: 02-Sep-2024
Note on LV57: Activity Name: UPS System w/ Battery (UPS) (Eaton) Shipping/ ROJ Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 UPS System W / Battery Trade: Procure Start Date: 19-Feb-2025 End Date: 23-Feb-2025
Note on LZ58: Activity Name: UPS System w/ Battery (UPS) (Eaton) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 UPS System W / Battery Trade: Procure Start Date: 23-Feb-2025 End Date: 23-Feb-2025
Note on HG60: Activity Name: Receive Utility Pad Mount Switchgear (Del Date- 7/30/2024) Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Utility Pad Mount Switchgear Trade: Procure Start Date: 23-Oct-2024 End Date: 23-Oct-2024
Note on LV60: Activity Name: Utility Pad Mount Switchgear (UPM) Shipping/ ROJ Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Utility Pad Mount Switchgear Trade: Procure Start Date: 19-Feb-2025 End Date: 23-Feb-2025
Note on MA60: Activity Name: Utility Pad Mount Switchgear (UPM) Delivered Phase: Procurement MSFT OFCI ROJ COLO3 Location: C3 Utility Pad Mount Switchgear Trade: Procure Start Date: 24-Feb-2025 End Date: 28-Feb-2025
Note on GJ63: Activity Name: Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/9/24) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Air Handling Units Trade: Procure Start Date: 30-Sep-2024 End Date: 30-Sep-2024
Note on NK63: Activity Name: Air Handling Units (AHU) (Stulz) Shipping/ ROJ Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Air Handling Units Trade: Procure Start Date: 01-Apr-2025 End Date: 05-Apr-2025
Note on NO64: Activity Name: Air Handling Units (AHU) (Stulz) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Air Handling Units Trade: Procure Start Date: 05-Apr-2025 End Date: 05-Apr-2025
Note on NI66: Activity Name: Auto Transfer Control Panel (TCP) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Auto Transfer Control Panel Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on NI67: Activity Name: Receive Auto Transfer Control Panel (TCP) (Del Date-3/30/2025) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Auto Transfer Control Panel Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on ID69: Activity Name: Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 6/30/24) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Automatic Transfer Switches Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on NE69: Activity Name: Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Automatic Transfer Switches Trade: Procure Start Date: 26-Mar-2025 End Date: 30-Mar-2025
Note on NI70: Activity Name: Automatic Transfer Switches (ATS) (Schneider) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Automatic Transfer Switches Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on NI72: Activity Name: Mech Power Distribution Panels (ADP) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Auxillary Power Distribution Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on NI73: Activity Name: Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Auxillary Power Distribution Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on JV75: Activity Name: Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 12/29/24) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Building Automation System Trade: Procure Start Date: 29-Dec-2024 End Date: 29-Dec-2024
Note on KB75: Activity Name: Building Automation System (BAS) (Automated Logic Corp) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Building Automation System Trade: Procure Start Date: 04-Jan-2025 End Date: 04-Jan-2025
Note on JV76: Activity Name: Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Building Automation System Trade: Procure Start Date: 29-Dec-2024 End Date: 04-Jan-2025
Note on ID78: Activity Name: Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 2/23/24) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Busway / Busplugs Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on NE78: Activity Name: Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Busway / Busplugs Trade: Procure Start Date: 26-Mar-2025 End Date: 30-Mar-2025
Note on NI79: Activity Name: Busway / Busplugs (BSW) (Starline Holding) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Busway / Busplugs Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on ID81: Activity Name: Receive Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) (SOW Del Date- 6/30/24) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Elec Performance Monitoring System Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on NE81: Activity Name: Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Elec Performance Monitoring System Trade: Procure Start Date: 26-Mar-2025 End Date: 30-Mar-2025
Note on NI82: Activity Name: Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Elec Performance Monitoring System Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on ID84: Activity Name: Receive HAC/Racking (Tate Access) (SOW Del Date- 6/18/24) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 HAC/Racking Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on NE84: Activity Name: HAC/Racking (Tate Access) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 HAC/Racking Trade: Procure Start Date: 26-Mar-2025 End Date: 28-Mar-2025
Note on NG85: Activity Name: HAC/Racking (Tate Access) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 HAC/Racking Trade: Procure Start Date: 28-Mar-2025 End Date: 28-Mar-2025
Note on ME87: Activity Name: Receive LV Switchgear (Eaton) (SOW Del Date- 2/28/25) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 LV Switchgear Trade: Procure Start Date: 28-Feb-2025 End Date: 28-Feb-2025
Note on MG87: Activity Name: LV Switchgear (Eaton) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 LV Switchgear Trade: Procure Start Date: 02-Mar-2025 End Date: 02-Mar-2025
Note on ME88: Activity Name: LV Switchgear (Eaton) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 LV Switchgear Trade: Procure Start Date: 28-Feb-2025 End Date: 02-Mar-2025
Note on NI90: Activity Name: Main LV Switch Board (MSB) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Main LV Switch Board Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on NI91: Activity Name: Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Main LV Switch Board Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on HG93: Activity Name: Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 8/30/24) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Medium Voltage Switchgear Trade: Procure Start Date: 23-Oct-2024 End Date: 23-Oct-2024
Note on NE93: Activity Name: Medium Voltage Switchgear (JDC Power Sys) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Medium Voltage Switchgear Trade: Procure Start Date: 26-Mar-2025 End Date: 30-Mar-2025
Note on NI94: Activity Name: Medium Voltage Switchgear (JDC Power Sys) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Medium Voltage Switchgear Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on ID96: Activity Name: Receive Packaged Diesel Generator Set (GEN) (CAT Holt) (SOW Del Date- 6/4/24) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Packaged Diesel Generator Set Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on NP96: Activity Name: Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Packaged Diesel Generator Set Trade: Procure Start Date: 06-Apr-2025 End Date: 10-Apr-2025
Note on NT97: Activity Name: Packaged Diesel Generator Set (GEN) (CAT Holt) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Packaged Diesel Generator Set Trade: Procure Start Date: 10-Apr-2025 End Date: 10-Apr-2025
Note on ID99: Activity Name: Reveive Pad Mounted Transformers (XMF) (Del Date 8/30/2024) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Pad Mounted Transformers Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on NE99: Activity Name: Pad Mounted Transformers (XMF) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Pad Mounted Transformers Trade: Procure Start Date: 26-Mar-2025 End Date: 30-Mar-2025
Note on NI100: Activity Name: Pad Mounted Transformers (XMF) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Pad Mounted Transformers Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on ID102: Activity Name: Reveive Power Distribution Units (PDU) (ABB) (SOW Del Date- 7/12/24) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Power Distribution Units Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on NE102: Activity Name: Power Distribution Units (PDU) (ABB) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Power Distribution Units Trade: Procure Start Date: 26-Mar-2025 End Date: 30-Mar-2025
Note on NI103: Activity Name: Power Distribution Units (PDU) (ABB) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Power Distribution Units Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on FH105: Activity Name: Received SUB Warehouse 11/23/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 11/11/23) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 UPS System W / Battery Trade: Procure Start Date: 02-Sep-2024 End Date: 02-Sep-2024
Note on NE105: Activity Name: Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 UPS System W / Battery Trade: Procure Start Date: 26-Mar-2025 End Date: 30-Mar-2025
Note on NI106: Activity Name: Static UPS System W/Batt (UPS) (Eaton) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 UPS System W / Battery Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on HG108: Activity Name: Receive Utility Pad Mount Switchgear (UPM) (Del Date 8/30/2024) Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Utility Pad Mount Switchgear Trade: Procure Start Date: 23-Oct-2024 End Date: 23-Oct-2024
Note on NE108: Activity Name: Utility Pad Mount Switchgear (UPM) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Utility Pad Mount Switchgear Trade: Procure Start Date: 26-Mar-2025 End Date: 30-Mar-2025
Note on NI109: Activity Name: Utility Pad Mount Switchgear (UPM) Delivered Phase: Procurement MSFT OFCI ROJ COLO4 Location: C4 Utility Pad Mount Switchgear Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on FR111: Activity Name: Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/16/24) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Air Handling Units Trade: Procure Start Date: 12-Sep-2024 End Date: 12-Sep-2024
Note on OY111: Activity Name: Air Handling Units (AHU) (Stulz) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Air Handling Units Trade: Procure Start Date: 11-May-2025 End Date: 11-May-2025
Note on OY112: Activity Name: Air Handling Units (AHU) (Stulz) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Air Handling Units Trade: Procure Start Date: 11-May-2025 End Date: 11-May-2025
Note on NI114: Activity Name: Receive Auto Transfer Control Panel (TCP) (Del Date 3/30/2025) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Auto Transfer Control Panel Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on NN114: Activity Name: Auto Transfer Control Panel (TCP) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Auto Transfer Control Panel Trade: Procure Start Date: 04-Apr-2025 End Date: 04-Apr-2025
Note on NI115: Activity Name: Auto Transfer Control Panel (TCP) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Auto Transfer Control Panel Trade: Procure Start Date: 30-Mar-2025 End Date: 04-Apr-2025
Note on ID117: Activity Name: Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 8/31/24) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Automatic Transfer Switches Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on OD117: Activity Name: Automatic Transfer Switches (ATS) (Schneider) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Automatic Transfer Switches Trade: Procure Start Date: 20-Apr-2025 End Date: 20-Apr-2025
Note on OD118: Activity Name: Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Automatic Transfer Switches Trade: Procure Start Date: 20-Apr-2025 End Date: 20-Apr-2025
Note on NI120: Activity Name: Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Auxillary Power Distribution Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on NN120: Activity Name: Mech Power Distribution Panels (ADP) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Auxillary Power Distribution Trade: Procure Start Date: 04-Apr-2025 End Date: 04-Apr-2025
Note on NI121: Activity Name: Mech Power Distribution Panels (ADP) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Auxillary Power Distribution Trade: Procure Start Date: 30-Mar-2025 End Date: 04-Apr-2025
Note on KZ123: Activity Name: Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 1/28/25) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Building Automation System Trade: Procure Start Date: 28-Jan-2025 End Date: 28-Jan-2025
Note on LE123: Activity Name: Building Automation System (BAS) (Automated Logic Corp) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Building Automation System Trade: Procure Start Date: 02-Feb-2025 End Date: 02-Feb-2025
Note on KZ124: Activity Name: Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Building Automation System Trade: Procure Start Date: 28-Jan-2025 End Date: 02-Feb-2025
Note on ID126: Activity Name: Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 4/23/24) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Busway / Busplugs Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on OM126: Activity Name: Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Busway / Busplugs Trade: Procure Start Date: 29-Apr-2025 End Date: 03-May-2025
Note on OQ127: Activity Name: Busway / Busplugs (BSW) (Starline Holding) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Busway / Busplugs Trade: Procure Start Date: 03-May-2025 End Date: 03-May-2025
Note on ID129: Activity Name: Receive Elec. Performance Monitoring Syst. (EPMS) (Schneider) (SOW Del Date- 8/31/24) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Elec Performance Monitoring System Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on OD129: Activity Name: Elec. Performance Monitoring Syst. (EPMS) (Schneider) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Elec Performance Monitoring System Trade: Procure Start Date: 20-Apr-2025 End Date: 20-Apr-2025
Note on OD130: Activity Name: Elec. Performance Monitoring Syst. (EPMS) (Schneider) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Elec Performance Monitoring System Trade: Procure Start Date: 20-Apr-2025 End Date: 20-Apr-2025
Note on ID132: Activity Name: Receive HAC/Racking (Tate Access) (SOW Del Date- 7/3/24) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 HAC/Racking Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on OI132: Activity Name: HAC/Racking (Tate Access) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 HAC/Racking Trade: Procure Start Date: 25-Apr-2025 End Date: 28-Apr-2025
Note on OL133: Activity Name: HAC/Racking (Tate Access) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 HAC/Racking Trade: Procure Start Date: 28-Apr-2025 End Date: 28-Apr-2025
Note on NI135: Activity Name: Receive LV Switchgear (Eaton) (SOW Del Date- 3/30/25) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 LV Switchgear Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on NM135: Activity Name: LV Switchgear (Eaton) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 LV Switchgear Trade: Procure Start Date: 03-Apr-2025 End Date: 03-Apr-2025
Note on NI136: Activity Name: LV Switchgear (Eaton) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 LV Switchgear Trade: Procure Start Date: 30-Mar-2025 End Date: 03-Apr-2025
Note on NI138: Activity Name: Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Main LV Switch Board Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on NN138: Activity Name: Main LV Switch Board (MSB) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Main LV Switch Board Trade: Procure Start Date: 04-Apr-2025 End Date: 04-Apr-2025
Note on NI139: Activity Name: Main LV Switch Board (MSB) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Main LV Switch Board Trade: Procure Start Date: 30-Mar-2025 End Date: 04-Apr-2025
Note on HN141: Activity Name: Receive Medium Voltage Switchgear (MVS) (JDC Power Sys) (SOW Del Date- 10/30/24) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Medium Voltage Switchgear Trade: Procure Start Date: 30-Oct-2024 End Date: 30-Oct-2024
Note on OM141: Activity Name: Medium Voltage Switchgear (MVS) (JDC Power Sys) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Medium Voltage Switchgear Trade: Procure Start Date: 29-Apr-2025 End Date: 03-May-2025
Note on OQ142: Activity Name: Medium Voltage Switchgear (MVS) (JDC Power Sys) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Medium Voltage Switchgear Trade: Procure Start Date: 03-May-2025 End Date: 03-May-2025
Note on ID144: Activity Name: Receive Packaged Diesel Generator Set (GPC) (CAT Holt) (SOW Del Date- 6/26/24) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Packaged Diesel Generator Set Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on OY144: Activity Name: Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Packaged Diesel Generator Set Trade: Procure Start Date: 11-May-2025 End Date: 15-May-2025
Note on PC145: Activity Name: Packaged Diesel Generator Set (GPC) (CAT Holt) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Packaged Diesel Generator Set Trade: Procure Start Date: 15-May-2025 End Date: 15-May-2025
Note on ID147: Activity Name: Receive Pad Mounted Transformers (XMF) (Del Date 10/30/2024) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Pad Mounted Transformers Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on OM147: Activity Name: Pad Mounted Transformers (XMF) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Pad Mounted Transformers Trade: Procure Start Date: 29-Apr-2025 End Date: 03-May-2025
Note on OQ148: Activity Name: Pad Mounted Transformers (XMF) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Pad Mounted Transformers Trade: Procure Start Date: 03-May-2025 End Date: 03-May-2025
Note on FH150: Activity Name: Received SUB Warehouse 12/28/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 12/11/23) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 UPS System W / Battery Trade: Procure Start Date: 02-Sep-2024 End Date: 02-Sep-2024
Note on NE150: Activity Name: Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 UPS System W / Battery Trade: Procure Start Date: 26-Mar-2025 End Date: 30-Mar-2025
Note on NI151: Activity Name: Static UPS System W/Batt (UPS) (Eaton) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 UPS System W / Battery Trade: Procure Start Date: 30-Mar-2025 End Date: 30-Mar-2025
Note on HG153: Activity Name: Receive Utility Pad Mount Switchgear (UPM) (Del Date 10/30/2024) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Utility Pad Mount Switchgear Trade: Procure Start Date: 23-Oct-2024 End Date: 23-Oct-2024
Note on OM153: Activity Name: Utility Pad Mount Switchgear (UPM) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Utility Pad Mount Switchgear Trade: Procure Start Date: 29-Apr-2025 End Date: 03-May-2025
Note on OQ154: Activity Name: Utility Pad Mount Switchgear (UPM) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5 Utility Pad Mount Switchgear Trade: Procure Start Date: 03-May-2025 End Date: 03-May-2025
Note on ID156: Activity Name: Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 9/30/24) Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5Power Distribution Units Trade: Procure Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on OQ156: Activity Name: Power Distribution Units (PDU) (ABB) Shipping/ROJ Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5Power Distribution Units Trade: Procure Start Date: 03-May-2025 End Date: 07-May-2025
Note on OU157: Activity Name: Power Distribution Units (PDU) (ABB) Delivered Phase: Procurement MSFT OFCI ROJ COLO5 Location: C5Power Distribution Units Trade: Procure Start Date: 07-May-2025 End Date: 07-May-2025
Note on DN159: Activity Name: BIM Kickoff Phase: Preconstruction Location: BIM Trade: BIM Start Date: 18-Jul-2024 End Date: 18-Jul-2024
Note on DO159: Activity Name: UG BIM Co-ordination Phase: Preconstruction Location: BIM Trade: BIM Start Date: 19-Jul-2024 End Date: 26-Sep-2024
Note on GG159: Activity Name: Above ground BIM Co-ordination Phase: Preconstruction Location: BIM Trade: BIM Start Date: 27-Sep-2024 End Date: 23-Dec-2024
Note on C162: Activity Name: RFP Issued (Revised 3.21.24) and Proposal Due to MSFT Phase: Preconstruction Location: RFP / PSR Trade: Precon Start Date: 25-Mar-2024 End Date: 12-Apr-2024
Note on BX162: Activity Name: PSR Executed (Early Works) Phase: Preconstruction Location: RFP / PSR Trade: Precon Start Date: 06-Jun-2024 End Date: 06-Jun-2024
Note on GJ162: Activity Name: PSR Executed (Full GMP) Phase: Preconstruction Location: RFP / PSR Trade: Precon Start Date: 30-Sep-2024 End Date: 30-Sep-2024
Note on DT165: Activity Name: Site Mobilization Phase: Site Prep/ Mobilization Location: Site Prep/ Mobilization Trade: CLAYCO Start Date: 24-Jul-2024 End Date: 24-Jul-2024
Note on DU165: Activity Name: Set-Up Trailers & Install Temp Utilities Phase: Site Prep/ Mobilization Location: Site Prep/ Mobilization Trade: CLAYCO Start Date: 25-Jul-2024 End Date: 16-Sep-2024
Note on ET166: Activity Name: Fine Grading Building Pad Phase: Site Prep/ Mobilization Location: Site Prep/ Mobilization Trade: Earthwork Start Date: 19-Aug-2024 End Date: 04-Sep-2024
Note on FY168: Activity Name: Foundations / Stem Walls Phase: Foundations Location: Foundations Trade: Foundations Start Date: 19-Sep-2024 End Date: 09-Oct-2024
Note on GT168: Activity Name: Foundations / Stem Walls Phase: Foundations Location: Foundations Trade: Foundations Start Date: 10-Oct-2024 End Date: 12-Nov-2024
Note on GR170: Activity Name: Install Deep Telecom Phase: Site Utilities Location: Overall Trade: Telecom Start Date: 08-Oct-2024 End Date: 14-Nov-2024
Note on OS170: Activity Name: Permanent Power Phase: Site Utilities Location: Overall Trade: Electrical Start Date: 05-May-2025 End Date: 05-May-2025
Note on GS171: Activity Name: Install Storm Lines Phase: Site Utilities Location: Overall Trade: Plumbing Start Date: 09-Oct-2024 End Date: 06-Dec-2024
Note on HI172: Activity Name: Install MV Ductbanks Phase: Site Utilities Location: Overall Trade: Electrical Start Date: 25-Oct-2024 End Date: 22-Nov-2024
Note on HS173: Activity Name: Install Sanitary Lines Phase: Site Utilities Location: Overall Trade: Plumbing Start Date: 04-Nov-2024 End Date: 09-Dec-2024
Note on HS174: Activity Name: Install Water Line Phase: Site Utilities Location: Overall Trade: Plumbing Start Date: 04-Nov-2024 End Date: 26-Dec-2024
Note on GR176: Activity Name: Install UG Telecom (under Building Pad) Phase: Site Utilities Location: Under Building Pad Trade: Telecom Start Date: 08-Oct-2024 End Date: 10-Oct-2024
Note on HI176: Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Phase: Site Utilities Location: Under Building Pad Trade: Electrical Start Date: 25-Oct-2024 End Date: 13-Nov-2024
Note on HT177: Activity Name: Backfill after UG work (MV / Telecom) Phase: Site Utilities Location: Under Building Pad Trade: Earthwork Start Date: 05-Nov-2024 End Date: 15-Nov-2024
Note on GX179: Activity Name: Install Primary Steel Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Start Date: 14-Oct-2024 End Date: 07-Nov-2024
Note on IB179: Activity Name: UG MEP Work AMS Phase: Core & Shell Location: Admin/ COLO 3 Trade: Electrical Start Date: 13-Nov-2024 End Date: 14-Dec-2024
Note on JI179: Activity Name: Prep / Place SOG Phase: Core & Shell Location: Admin/ COLO 3 Trade: SOG Start Date: 16-Dec-2024 End Date: 27-Dec-2024
Note on JW179: Activity Name: Weather Days Phase: Core & Shell Location: Admin/ COLO 3 Trade: Buffer Start Date: 30-Dec-2024 End Date: 16-Jan-2025
Note on IG180: Activity Name: Install Exterior Wall Panels Phase: Core & Shell Location: Admin/ COLO 3 Trade: Drywall Start Date: 18-Nov-2024 End Date: 29-Nov-2024
Note on IS180: Activity Name: Install Roof Panels Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Start Date: 30-Nov-2024 End Date: 14-Dec-2024
Note on JI180: Activity Name: Install Louvers & Dampers Phase: Core & Shell Location: Admin/ COLO 3 Trade: Mech Start Date: 16-Dec-2024 End Date: 06-Jan-2025
Note on JW181: Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Start Date: 30-Dec-2024 End Date: 17-Jan-2025
Note on HP185: Activity Name: Install Primary Steel Phase: Core & Shell Location: COLO 4 Trade: Framing Start Date: 01-Nov-2024 End Date: 20-Nov-2024
Note on IJ185: Activity Name: Install Exterior Wall Panels Phase: Core & Shell Location: COLO 4 Trade: Drywall Start Date: 21-Nov-2024 End Date: 14-Dec-2024
Note on JI185: Activity Name: Install Roof Panels Phase: Core & Shell Location: COLO 4 Trade: Framing Start Date: 16-Dec-2024 End Date: 31-Dec-2024
Note on KE185: Activity Name: Install Louvers & Dampers Phase: Core & Shell Location: COLO 4 Trade: Mech Start Date: 07-Jan-2025 End Date: 25-Jan-2025
Note on IW186: Activity Name: UG MEP Work AMS Phase: Core & Shell Location: COLO 4 Trade: Electrical Start Date: 04-Dec-2024 End Date: 27-Dec-2024
Note on JW186: Activity Name: Prep / Place SOG Phase: Core & Shell Location: COLO 4 Trade: SOG Start Date: 30-Dec-2024 End Date: 10-Jan-2025
Note on KI186: Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Phase: Core & Shell Location: COLO 4 Trade: Framing Start Date: 11-Jan-2025 End Date: 30-Jan-2025
Note on IA190: Activity Name: Install Primary Steel Phase: Core & Shell Location: COLO 5 Trade: Framing Start Date: 12-Nov-2024 End Date: 03-Dec-2024
Note on IW190: Activity Name: Install Exterior Wall Panels Phase: Core & Shell Location: COLO 5 Trade: Drywall Start Date: 04-Dec-2024 End Date: 31-Dec-2024
Note on JZ190: Activity Name: Install Roof Panels Phase: Core & Shell Location: COLO 5 Trade: Framing Start Date: 02-Jan-2025 End Date: 15-Jan-2025
Note on KY190: Activity Name: Install Louvers & Dampers Phase: Core & Shell Location: COLO 5 Trade: Mech Start Date: 27-Jan-2025 End Date: 14-Feb-2025
Note on JJ191: Activity Name: UG MEP Work AMS Phase: Core & Shell Location: COLO 5 Trade: Electrical Start Date: 17-Dec-2024 End Date: 13-Jan-2025
Note on KL191: Activity Name: Prep / Place SOG Phase: Core & Shell Location: COLO 5 Trade: SOG Start Date: 14-Jan-2025 End Date: 25-Jan-2025
Note on KY191: Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Phase: Core & Shell Location: COLO 5 Trade: Framing Start Date: 27-Jan-2025 End Date: 14-Feb-2025
Note on KO195: Activity Name: Layout Framing Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Framing Start Date: 17-Jan-2025 End Date: 17-Jan-2025
Note on KR195: Activity Name: Framing Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Framing Start Date: 20-Jan-2025 End Date: 24-Jan-2025
Note on KW195: Activity Name: In-Wall R/I Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Drywall Start Date: 25-Jan-2025 End Date: 28-Jan-2025
Note on LA195: Activity Name: Install Drywall Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Drywall Start Date: 29-Jan-2025 End Date: 31-Jan-2025
Note on LD195: Activity Name: Finish Drywall Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Drywall Start Date: 01-Feb-2025 End Date: 04-Feb-2025
Note on LH195: Activity Name: Paint Dry-Wall Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Painting Start Date: 05-Feb-2025 End Date: 07-Feb-2025
Note on LM195: Activity Name: Install Screen Mesh + Caulking Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Framing Start Date: 10-Feb-2025 End Date: 12-Feb-2025
Note on LP195: Activity Name: Install Secondary Steel Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Framing Start Date: 13-Feb-2025 End Date: 14-Feb-2025
Note on LR195: Activity Name: Paint Secondary Steel Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Painting Start Date: 15-Feb-2025 End Date: 17-Feb-2025
Note on LU195: Activity Name: General Cleaning Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: CLAYCO Start Date: 18-Feb-2025 End Date: 18-Feb-2025
Note on LY195: Activity Name: Install Perimeter Cable Trays Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Electrical Start Date: 22-Feb-2025 End Date: 26-Feb-2025
Note on MD195: Activity Name: Install Device Tiles Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Framing Start Date: 27-Feb-2025 End Date: 28-Feb-2025
Note on MK195: Activity Name: Raise HACs Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: HACs Start Date: 06-Mar-2025 End Date: 10-Mar-2025
Note on MP195: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Electrical Start Date: 11-Mar-2025 End Date: 13-Mar-2025
Note on MS195: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Electrical Start Date: 14-Mar-2025 End Date: 17-Mar-2025
Note on MW195: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Electrical Start Date: 18-Mar-2025 End Date: 24-Mar-2025
Note on NX195: Activity Name: Terminate PDUs Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Electrical Start Date: 14-Apr-2025 End Date: 16-Apr-2025
Note on LA196: Activity Name: Fire Protection OH R/I Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Fire Protection Start Date: 29-Jan-2025 End Date: 31-Jan-2025
Note on LD196: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Fire Protection Start Date: 01-Feb-2025 End Date: 04-Feb-2025
Note on LG196: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Mech Start Date: 04-Feb-2025 End Date: 05-Feb-2025
Note on LI196: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Framing Start Date: 06-Feb-2025 End Date: 07-Feb-2025
Note on LU196: Activity Name: Install Ceiling Grid Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Framing Start Date: 18-Feb-2025 End Date: 21-Feb-2025
Note on LY196: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: HACs Start Date: 22-Feb-2025 End Date: 27-Feb-2025
Note on MD196: Activity Name: Set PDUs Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Electrical Start Date: 27-Feb-2025 End Date: 04-Mar-2025
Note on MP196: Activity Name: Detail HACs Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: HACs Start Date: 11-Mar-2025 End Date: 14-Mar-2025
Note on LD197: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Electrical Start Date: 01-Feb-2025 End Date: 05-Feb-2025
Note on MB197: Activity Name: Install Busways on HAC Arms Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Electrical Start Date: 25-Feb-2025 End Date: 03-Mar-2025
Note on MD198: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout COLO3 Location: C3 CELL 1 Data Hall Trade: Electrical Start Date: 27-Feb-2025 End Date: 05-Mar-2025
Note on KW203: Activity Name: Framing Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Framing Start Date: 25-Jan-2025 End Date: 30-Jan-2025
Note on LC203: Activity Name: In-Wall R/I Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Drywall Start Date: 31-Jan-2025 End Date: 10-Feb-2025
Note on LN203: Activity Name: Fire Protection OH R/I Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Fire Protection Start Date: 11-Feb-2025 End Date: 12-Feb-2025
Note on LP203: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Fire Protection Start Date: 13-Feb-2025 End Date: 14-Feb-2025
Note on LR203: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Framing Start Date: 15-Feb-2025 End Date: 15-Feb-2025
Note on LT203: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Electrical Start Date: 17-Feb-2025 End Date: 18-Feb-2025
Note on LY203: Activity Name: Finish Drywall Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Drywall Start Date: 22-Feb-2025 End Date: 04-Mar-2025
Note on MJ203: Activity Name: Paint Dry-Wall Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Painting Start Date: 05-Mar-2025 End Date: 06-Mar-2025
Note on ML203: Activity Name: General Cleaning Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: CLAYCO Start Date: 07-Mar-2025 End Date: 07-Mar-2025
Note on MO203: Activity Name: Set Electrical Equipments Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Electrical Start Date: 10-Mar-2025 End Date: 15-Mar-2025
Note on MV203: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Electrical Start Date: 17-Mar-2025 End Date: 29-Mar-2025
Note on NJ203: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Electrical Start Date: 31-Mar-2025 End Date: 03-Apr-2025
Note on LN204: Activity Name: Install Drywall Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Drywall Start Date: 11-Feb-2025 End Date: 21-Feb-2025
Note on NJ204: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Electrical Start Date: 31-Mar-2025 End Date: 11-Apr-2025
Note on LP205: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO3 Location: C3 CELL 1 Electrical Room Trade: Electrical Start Date: 13-Feb-2025 End Date: 15-Feb-2025
Note on LP209: Activity Name: Fire Protection OH R/I Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Fire Protection Start Date: 13-Feb-2025 End Date: 14-Feb-2025
Note on LR209: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Fire Protection Start Date: 15-Feb-2025 End Date: 17-Feb-2025
Note on LV209: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Mech Start Date: 19-Feb-2025 End Date: 25-Feb-2025
Note on MC209: Activity Name: Overhead R/I - Plumbing Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Plumbing Start Date: 26-Feb-2025 End Date: 05-Mar-2025
Note on MK209: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Framing Start Date: 06-Mar-2025 End Date: 06-Mar-2025
Note on ML209: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Framing Start Date: 07-Mar-2025 End Date: 11-Mar-2025
Note on MQ209: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Electrical Start Date: 12-Mar-2025 End Date: 13-Mar-2025
Note on MS209: Activity Name: Set Mechanical Equipments Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Mech Start Date: 14-Mar-2025 End Date: 18-Mar-2025
Note on MX209: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Electrical Start Date: 19-Mar-2025 End Date: 02-Apr-2025
Note on NM209: Activity Name: Terminate Mechanical Equipments Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Mech Start Date: 03-Apr-2025 End Date: 07-Apr-2025
Note on LR210: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Electrical Start Date: 15-Feb-2025 End Date: 18-Feb-2025
Note on MI210: Activity Name: Install Drywall Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Drywall Start Date: 04-Mar-2025 End Date: 05-Mar-2025
Note on MK210: Activity Name: Finish Drywall Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Drywall Start Date: 06-Mar-2025 End Date: 07-Mar-2025
Note on MM210: Activity Name: Paint Dry-Wall Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: Painting Start Date: 08-Mar-2025 End Date: 10-Mar-2025
Note on MP210: Activity Name: General Cleaning Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: CLAYCO Start Date: 11-Mar-2025 End Date: 13-Mar-2025
Note on ND210: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: BAS Start Date: 25-Mar-2025 End Date: 02-Apr-2025
Note on MQ211: Activity Name: Install BAS Equipments Phase: Fitout COLO3 Location: C3 CELL 1 Mechanical Gallery Trade: BAS Start Date: 12-Mar-2025 End Date: 24-Mar-2025
Note on OA215: Activity Name: Punchlist Phase: Fitout COLO3 Location: C3 CELL 1 Punchlist Trade: CLAYCO Start Date: 17-Apr-2025 End Date: 28-Apr-2025
Note on LA216: Activity Name: Layout Framing Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Framing Start Date: 29-Jan-2025 End Date: 29-Jan-2025
Note on LB216: Activity Name: Framing Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Framing Start Date: 30-Jan-2025 End Date: 01-Feb-2025
Note on LF216: Activity Name: In-Wall R/I Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Drywall Start Date: 03-Feb-2025 End Date: 05-Feb-2025
Note on LI216: Activity Name: Install Drywall Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Drywall Start Date: 06-Feb-2025 End Date: 10-Feb-2025
Note on LN216: Activity Name: Finish Drywall Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Drywall Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on LQ216: Activity Name: Paint Dry-Wall Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Painting Start Date: 14-Feb-2025 End Date: 17-Feb-2025
Note on LU216: Activity Name: Install Screen Mesh + Caulking Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Framing Start Date: 18-Feb-2025 End Date: 20-Feb-2025
Note on LX216: Activity Name: Install Secondary Steel Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Framing Start Date: 21-Feb-2025 End Date: 22-Feb-2025
Note on MA216: Activity Name: Paint Secondary Steel Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Painting Start Date: 24-Feb-2025 End Date: 25-Feb-2025
Note on MC216: Activity Name: General Cleaning Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: CLAYCO Start Date: 26-Feb-2025 End Date: 26-Feb-2025
Note on MI216: Activity Name: Install Perimeter Cable Trays Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Electrical Start Date: 04-Mar-2025 End Date: 07-Mar-2025
Note on MM216: Activity Name: Install Device Tiles Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Framing Start Date: 08-Mar-2025 End Date: 10-Mar-2025
Note on MS216: Activity Name: Raise HACs Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: HACs Start Date: 14-Mar-2025 End Date: 18-Mar-2025
Note on MX216: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Electrical Start Date: 19-Mar-2025 End Date: 21-Mar-2025
Note on NC216: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Electrical Start Date: 24-Mar-2025 End Date: 26-Mar-2025
Note on NF216: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Electrical Start Date: 27-Mar-2025 End Date: 01-Apr-2025
Note on OW216: Activity Name: Terminate PDUs Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Electrical Start Date: 09-May-2025 End Date: 12-May-2025
Note on LI217: Activity Name: Fire Protection OH R/I Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Fire Protection Start Date: 06-Feb-2025 End Date: 10-Feb-2025
Note on LN217: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Fire Protection Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on LP217: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Framing Start Date: 13-Feb-2025 End Date: 14-Feb-2025
Note on MC217: Activity Name: Install Ceiling Grid Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Framing Start Date: 26-Feb-2025 End Date: 03-Mar-2025
Note on MI217: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: HACs Start Date: 04-Mar-2025 End Date: 08-Mar-2025
Note on MM217: Activity Name: Set PDUs Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Electrical Start Date: 08-Mar-2025 End Date: 12-Mar-2025
Note on MX217: Activity Name: Detail HACs Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: HACs Start Date: 19-Mar-2025 End Date: 24-Mar-2025
Note on LN218: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Electrical Start Date: 11-Feb-2025 End Date: 14-Feb-2025
Note on LP218: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Mech Start Date: 13-Feb-2025 End Date: 14-Feb-2025
Note on MK218: Activity Name: Install Busways on HAC Arms Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Electrical Start Date: 06-Mar-2025 End Date: 11-Mar-2025
Note on MM219: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout COLO3 Location: C3 CELL 2 Data Hall Trade: Electrical Start Date: 08-Mar-2025 End Date: 13-Mar-2025
Note on LF224: Activity Name: Framing Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Framing Start Date: 03-Feb-2025 End Date: 04-Feb-2025
Note on LH224: Activity Name: In-Wall R/I Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Drywall Start Date: 05-Feb-2025 End Date: 06-Feb-2025
Note on LJ224: Activity Name: Fire Protection OH R/I Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Fire Protection Start Date: 07-Feb-2025 End Date: 10-Feb-2025
Note on LN224: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Fire Protection Start Date: 11-Feb-2025 End Date: 12-Feb-2025
Note on LP224: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Framing Start Date: 13-Feb-2025 End Date: 13-Feb-2025
Note on LQ224: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Electrical Start Date: 14-Feb-2025 End Date: 15-Feb-2025
Note on LU224: Activity Name: General Cleaning Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: CLAYCO Start Date: 18-Feb-2025 End Date: 18-Feb-2025
Note on MV224: Activity Name: Set Electrical Equipments Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Electrical Start Date: 17-Mar-2025 End Date: 20-Mar-2025
Note on NX224: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Electrical Start Date: 14-Apr-2025 End Date: 25-Apr-2025
Note on OJ224: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Electrical Start Date: 26-Apr-2025 End Date: 30-Apr-2025
Note on LJ225: Activity Name: Install Drywall Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Drywall Start Date: 07-Feb-2025 End Date: 12-Feb-2025
Note on LP225: Activity Name: Finish Drywall Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Drywall Start Date: 13-Feb-2025 End Date: 14-Feb-2025
Note on LR225: Activity Name: Paint Dry-Wall Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Painting Start Date: 15-Feb-2025 End Date: 17-Feb-2025
Note on OJ225: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Electrical Start Date: 26-Apr-2025 End Date: 08-May-2025
Note on LN226: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO3 Location: C3 CELL 2 Electrical Room Trade: Electrical Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on LN230: Activity Name: Fire Protection OH R/I Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Fire Protection Start Date: 11-Feb-2025 End Date: 12-Feb-2025
Note on LP230: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Fire Protection Start Date: 13-Feb-2025 End Date: 14-Feb-2025
Note on LT230: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Mech Start Date: 17-Feb-2025 End Date: 22-Feb-2025
Note on MA230: Activity Name: Overhead R/I - Plumbing Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Plumbing Start Date: 24-Feb-2025 End Date: 03-Mar-2025
Note on MI230: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Framing Start Date: 04-Mar-2025 End Date: 04-Mar-2025
Note on MJ230: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Framing Start Date: 05-Mar-2025 End Date: 08-Mar-2025
Note on MO230: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Electrical Start Date: 10-Mar-2025 End Date: 11-Mar-2025
Note on MQ230: Activity Name: Set Mechanical Equipments Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Mech Start Date: 12-Mar-2025 End Date: 15-Mar-2025
Note on MV230: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Electrical Start Date: 17-Mar-2025 End Date: 31-Mar-2025
Note on NK230: Activity Name: Terminate Mechanical Equipments Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Mech Start Date: 01-Apr-2025 End Date: 04-Apr-2025
Note on LP231: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Electrical Start Date: 13-Feb-2025 End Date: 15-Feb-2025
Note on ME231: Activity Name: Install Drywall Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Drywall Start Date: 28-Feb-2025 End Date: 03-Mar-2025
Note on MI231: Activity Name: Finish Drywall Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Drywall Start Date: 04-Mar-2025 End Date: 05-Mar-2025
Note on MK231: Activity Name: Paint Dry-Wall Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: Painting Start Date: 06-Mar-2025 End Date: 07-Mar-2025
Note on MM231: Activity Name: General Cleaning Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: CLAYCO Start Date: 08-Mar-2025 End Date: 11-Mar-2025
Note on MZ231: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: BAS Start Date: 21-Mar-2025 End Date: 31-Mar-2025
Note on MO232: Activity Name: Install BAS Equipments Phase: Fitout COLO3 Location: C3 CELL 2 Mechanical Gallery Trade: BAS Start Date: 10-Mar-2025 End Date: 20-Mar-2025
Note on PA236: Activity Name: Punchlist Phase: Fitout COLO3 Location: C3 CELL 2 Punchlist Trade: CLAYCO Start Date: 13-May-2025 End Date: 23-May-2025
Note on LX237: Activity Name: Layout Framing Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Framing Start Date: 21-Feb-2025 End Date: 21-Feb-2025
Note on LY237: Activity Name: Framing Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Framing Start Date: 22-Feb-2025 End Date: 25-Feb-2025
Note on MC237: Activity Name: In-Wall R/I Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Drywall Start Date: 26-Feb-2025 End Date: 28-Feb-2025
Note on MH237: Activity Name: Install Drywall Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Drywall Start Date: 03-Mar-2025 End Date: 05-Mar-2025
Note on MK237: Activity Name: Finish Drywall Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Drywall Start Date: 06-Mar-2025 End Date: 08-Mar-2025
Note on MO237: Activity Name: Paint Dry-Wall Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Painting Start Date: 10-Mar-2025 End Date: 12-Mar-2025
Note on MR237: Activity Name: Install Screen Mesh + Caulking Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Framing Start Date: 13-Mar-2025 End Date: 15-Mar-2025
Note on MV237: Activity Name: Install Secondary Steel Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Framing Start Date: 17-Mar-2025 End Date: 18-Mar-2025
Note on MX237: Activity Name: Paint Secondary Steel Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Painting Start Date: 19-Mar-2025 End Date: 20-Mar-2025
Note on MZ237: Activity Name: General Cleaning Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: CLAYCO Start Date: 21-Mar-2025 End Date: 21-Mar-2025
Note on NF237: Activity Name: Install Perimeter Cable Trays Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Electrical Start Date: 27-Mar-2025 End Date: 31-Mar-2025
Note on NK237: Activity Name: Install Device Tiles Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Framing Start Date: 01-Apr-2025 End Date: 02-Apr-2025
Note on NQ237: Activity Name: Raise HACs Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: HACs Start Date: 07-Apr-2025 End Date: 10-Apr-2025
Note on NU237: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Electrical Start Date: 11-Apr-2025 End Date: 15-Apr-2025
Note on NZ237: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Electrical Start Date: 16-Apr-2025 End Date: 18-Apr-2025
Note on OC237: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Electrical Start Date: 19-Apr-2025 End Date: 24-Apr-2025
Note on PX237: Activity Name: Terminate PDUs Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Electrical Start Date: 05-Jun-2025 End Date: 07-Jun-2025
Note on MH238: Activity Name: Fire Protection OH R/I Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Fire Protection Start Date: 03-Mar-2025 End Date: 05-Mar-2025
Note on MK238: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Fire Protection Start Date: 06-Mar-2025 End Date: 08-Mar-2025
Note on MM238: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Framing Start Date: 08-Mar-2025 End Date: 10-Mar-2025
Note on MZ238: Activity Name: Install Ceiling Grid Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Framing Start Date: 21-Mar-2025 End Date: 26-Mar-2025
Note on NF238: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: HACs Start Date: 27-Mar-2025 End Date: 01-Apr-2025
Note on NK238: Activity Name: Set PDUs Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Electrical Start Date: 01-Apr-2025 End Date: 04-Apr-2025
Note on NU238: Activity Name: Detail HACs Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: HACs Start Date: 11-Apr-2025 End Date: 16-Apr-2025
Note on MK239: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Electrical Start Date: 06-Mar-2025 End Date: 10-Mar-2025
Note on NH239: Activity Name: Install Busways on HAC Arms Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Electrical Start Date: 29-Mar-2025 End Date: 03-Apr-2025
Note on MM240: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Mech Start Date: 08-Mar-2025 End Date: 10-Mar-2025
Note on NK240: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout COLO3 Location: C3 CELL 3 Data Hall Trade: Electrical Start Date: 01-Apr-2025 End Date: 05-Apr-2025
Note on MC245: Activity Name: Framing Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Framing Start Date: 26-Feb-2025 End Date: 27-Feb-2025
Note on ME245: Activity Name: In-Wall R/I Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Drywall Start Date: 28-Feb-2025 End Date: 03-Mar-2025
Note on MI245: Activity Name: Fire Protection OH R/I Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Fire Protection Start Date: 04-Mar-2025 End Date: 05-Mar-2025
Note on MK245: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Fire Protection Start Date: 06-Mar-2025 End Date: 07-Mar-2025
Note on MM245: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Framing Start Date: 08-Mar-2025 End Date: 08-Mar-2025
Note on MO245: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Electrical Start Date: 10-Mar-2025 End Date: 11-Mar-2025
Note on MR245: Activity Name: General Cleaning Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: CLAYCO Start Date: 13-Mar-2025 End Date: 13-Mar-2025
Note on MS245: Activity Name: Set Electrical Equipments Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Electrical Start Date: 14-Mar-2025 End Date: 18-Mar-2025
Note on OX245: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Electrical Start Date: 10-May-2025 End Date: 22-May-2025
Note on PK245: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Electrical Start Date: 23-May-2025 End Date: 28-May-2025
Note on MI246: Activity Name: Install Drywall Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Drywall Start Date: 04-Mar-2025 End Date: 07-Mar-2025
Note on MM246: Activity Name: Finish Drywall Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Drywall Start Date: 08-Mar-2025 End Date: 10-Mar-2025
Note on MP246: Activity Name: Paint Dry-Wall Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Painting Start Date: 11-Mar-2025 End Date: 12-Mar-2025
Note on PK246: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Electrical Start Date: 23-May-2025 End Date: 04-Jun-2025
Note on MK247: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO3 Location: C3 CELL 3 Electrical Room Trade: Electrical Start Date: 06-Mar-2025 End Date: 08-Mar-2025
Note on MK251: Activity Name: Fire Protection OH R/I Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Fire Protection Start Date: 06-Mar-2025 End Date: 07-Mar-2025
Note on MM251: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Fire Protection Start Date: 08-Mar-2025 End Date: 10-Mar-2025
Note on MQ251: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Mech Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on MX251: Activity Name: Overhead R/I - Plumbing Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Plumbing Start Date: 19-Mar-2025 End Date: 26-Mar-2025
Note on NF251: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Framing Start Date: 27-Mar-2025 End Date: 27-Mar-2025
Note on NG251: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Framing Start Date: 28-Mar-2025 End Date: 01-Apr-2025
Note on NL251: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Electrical Start Date: 02-Apr-2025 End Date: 03-Apr-2025
Note on NN251: Activity Name: Set Mechanical Equipments Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Mech Start Date: 04-Apr-2025 End Date: 08-Apr-2025
Note on NS251: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Electrical Start Date: 09-Apr-2025 End Date: 23-Apr-2025
Note on OH251: Activity Name: Terminate Mechanical Equipments Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Mech Start Date: 24-Apr-2025 End Date: 28-Apr-2025
Note on MM252: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Electrical Start Date: 08-Mar-2025 End Date: 11-Mar-2025
Note on ND252: Activity Name: Install Drywall Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Drywall Start Date: 25-Mar-2025 End Date: 26-Mar-2025
Note on NF252: Activity Name: Finish Drywall Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Drywall Start Date: 27-Mar-2025 End Date: 28-Mar-2025
Note on NH252: Activity Name: Paint Dry-Wall Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: Painting Start Date: 29-Mar-2025 End Date: 31-Mar-2025
Note on NK252: Activity Name: General Cleaning Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: CLAYCO Start Date: 01-Apr-2025 End Date: 03-Apr-2025
Note on NY252: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: BAS Start Date: 15-Apr-2025 End Date: 23-Apr-2025
Note on NL253: Activity Name: Install BAS Equipments Phase: Fitout COLO3 Location: C3 CELL 3 Mechanical Gallery Trade: BAS Start Date: 02-Apr-2025 End Date: 14-Apr-2025
Note on QB257: Activity Name: Punchlist Phase: Fitout COLO3 Location: C3 CELL 3 Punchlist Trade: CLAYCO Start Date: 09-Jun-2025 End Date: 20-Jun-2025
Note on LM258: Activity Name: Layout Framing Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Framing Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on LN258: Activity Name: Framing Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Framing Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on LQ258: Activity Name: In-Wall R/I Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Drywall Start Date: 14-Feb-2025 End Date: 17-Feb-2025
Note on LU258: Activity Name: Install Drywall Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Drywall Start Date: 18-Feb-2025 End Date: 20-Feb-2025
Note on LX258: Activity Name: Finish Drywall Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Drywall Start Date: 21-Feb-2025 End Date: 24-Feb-2025
Note on MB258: Activity Name: Paint Dry-Wall Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Painting Start Date: 25-Feb-2025 End Date: 27-Feb-2025
Note on ME258: Activity Name: Install Screen Mesh + Caulking Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Framing Start Date: 28-Feb-2025 End Date: 04-Mar-2025
Note on MJ258: Activity Name: Install Secondary Steel Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Framing Start Date: 05-Mar-2025 End Date: 06-Mar-2025
Note on ML258: Activity Name: Paint Secondary Steel Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Painting Start Date: 07-Mar-2025 End Date: 08-Mar-2025
Note on MO258: Activity Name: General Cleaning Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: CLAYCO Start Date: 10-Mar-2025 End Date: 10-Mar-2025
Note on MS258: Activity Name: Install Perimeter Cable Trays Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Electrical Start Date: 14-Mar-2025 End Date: 18-Mar-2025
Note on MX258: Activity Name: Install Device Tiles Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Framing Start Date: 19-Mar-2025 End Date: 20-Mar-2025
Note on NE258: Activity Name: Raise HACs Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: HACs Start Date: 26-Mar-2025 End Date: 29-Mar-2025
Note on NJ258: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Electrical Start Date: 31-Mar-2025 End Date: 02-Apr-2025
Note on NM258: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Electrical Start Date: 03-Apr-2025 End Date: 05-Apr-2025
Note on NQ258: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Electrical Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on OX258: Activity Name: Terminate PDUs Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Electrical Start Date: 10-May-2025 End Date: 13-May-2025
Note on LU259: Activity Name: Fire Protection OH R/I Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Fire Protection Start Date: 18-Feb-2025 End Date: 20-Feb-2025
Note on LX259: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Fire Protection Start Date: 21-Feb-2025 End Date: 24-Feb-2025
Note on MA259: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Framing Start Date: 24-Feb-2025 End Date: 25-Feb-2025
Note on MO259: Activity Name: Install Ceiling Grid Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Framing Start Date: 10-Mar-2025 End Date: 13-Mar-2025
Note on MS259: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: HACs Start Date: 14-Mar-2025 End Date: 19-Mar-2025
Note on MX259: Activity Name: Set PDUs Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Electrical Start Date: 19-Mar-2025 End Date: 24-Mar-2025
Note on NJ259: Activity Name: Detail HACs Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: HACs Start Date: 31-Mar-2025 End Date: 03-Apr-2025
Note on LX260: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Electrical Start Date: 21-Feb-2025 End Date: 25-Feb-2025
Note on MA260: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Mech Start Date: 24-Feb-2025 End Date: 25-Feb-2025
Note on MV260: Activity Name: Install Busways on HAC Arms Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Electrical Start Date: 17-Mar-2025 End Date: 21-Mar-2025
Note on MX261: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout COLO3 Location: C3 CELL 4 Data Hall Trade: Electrical Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on LQ266: Activity Name: Framing Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Framing Start Date: 14-Feb-2025 End Date: 15-Feb-2025
Note on LT266: Activity Name: In-Wall R/I Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Drywall Start Date: 17-Feb-2025 End Date: 18-Feb-2025
Note on LV266: Activity Name: Fire Protection OH R/I Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Fire Protection Start Date: 19-Feb-2025 End Date: 20-Feb-2025
Note on LX266: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Fire Protection Start Date: 21-Feb-2025 End Date: 22-Feb-2025
Note on MA266: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Framing Start Date: 24-Feb-2025 End Date: 24-Feb-2025
Note on MB266: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Electrical Start Date: 25-Feb-2025 End Date: 26-Feb-2025
Note on ME266: Activity Name: General Cleaning Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: CLAYCO Start Date: 28-Feb-2025 End Date: 28-Feb-2025
Note on MH266: Activity Name: Set Electrical Equipments Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Electrical Start Date: 03-Mar-2025 End Date: 06-Mar-2025
Note on ML266: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Electrical Start Date: 07-Mar-2025 End Date: 19-Mar-2025
Note on MY266: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Electrical Start Date: 20-Mar-2025 End Date: 25-Mar-2025
Note on OJ266: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Electrical Start Date: 26-Apr-2025 End Date: 09-May-2025
Note on LV267: Activity Name: Install Drywall Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Drywall Start Date: 19-Feb-2025 End Date: 22-Feb-2025
Note on MA267: Activity Name: Finish Drywall Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Drywall Start Date: 24-Feb-2025 End Date: 25-Feb-2025
Note on MC267: Activity Name: Paint Dry-Wall Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Painting Start Date: 26-Feb-2025 End Date: 27-Feb-2025
Note on LX268: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO3 Location: C3 CELL 4 Electrical Room Trade: Electrical Start Date: 21-Feb-2025 End Date: 24-Feb-2025
Note on LX272: Activity Name: Fire Protection OH R/I Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Fire Protection Start Date: 21-Feb-2025 End Date: 22-Feb-2025
Note on MA272: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Fire Protection Start Date: 24-Feb-2025 End Date: 25-Feb-2025
Note on MD272: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Mech Start Date: 27-Feb-2025 End Date: 06-Mar-2025
Note on ML272: Activity Name: Overhead R/I - Plumbing Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Plumbing Start Date: 07-Mar-2025 End Date: 13-Mar-2025
Note on MS272: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Framing Start Date: 14-Mar-2025 End Date: 14-Mar-2025
Note on MT272: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Framing Start Date: 15-Mar-2025 End Date: 19-Mar-2025
Note on MY272: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Electrical Start Date: 20-Mar-2025 End Date: 21-Mar-2025
Note on NC272: Activity Name: Set Mechanical Equipments Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Mech Start Date: 24-Mar-2025 End Date: 27-Mar-2025
Note on NG272: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Electrical Start Date: 28-Mar-2025 End Date: 10-Apr-2025
Note on NU272: Activity Name: Terminate Mechanical Equipments Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Mech Start Date: 11-Apr-2025 End Date: 16-Apr-2025
Note on MA273: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Electrical Start Date: 24-Feb-2025 End Date: 26-Feb-2025
Note on MQ273: Activity Name: Install Drywall Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Drywall Start Date: 12-Mar-2025 End Date: 13-Mar-2025
Note on MS273: Activity Name: Finish Drywall Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Drywall Start Date: 14-Mar-2025 End Date: 15-Mar-2025
Note on MV273: Activity Name: Paint Dry-Wall Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: Painting Start Date: 17-Mar-2025 End Date: 18-Mar-2025
Note on MX273: Activity Name: General Cleaning Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: CLAYCO Start Date: 19-Mar-2025 End Date: 21-Mar-2025
Note on NL273: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: BAS Start Date: 02-Apr-2025 End Date: 10-Apr-2025
Note on MY274: Activity Name: Install BAS Equipments Phase: Fitout COLO3 Location: C3 CELL 4 Mechanical Gallery Trade: BAS Start Date: 20-Mar-2025 End Date: 01-Apr-2025
Note on OX278: Activity Name: Punchlist Phase: Fitout COLO3 Location: C3 CELL 4 Punchlist Trade: CLAYCO Start Date: 10-May-2025 End Date: 21-May-2025
Note on KR279: Activity Name: Fire Protection OH R/I Phase: Fitout Admin Area Location: Beneficial Use Rooms Electrical Rooms Trade: Fire Protection Start Date: 20-Jan-2025 End Date: 20-Jan-2025
Note on KS279: Activity Name: Framing Phase: Fitout Admin Area Location: Beneficial Use Rooms Electrical Rooms Trade: Framing Start Date: 21-Jan-2025 End Date: 21-Jan-2025
Note on KT279: Activity Name: MEP Rough-In & OH Phase: Fitout Admin Area Location: Beneficial Use Rooms Electrical Rooms Trade: MEP Start Date: 22-Jan-2025 End Date: 23-Jan-2025
Note on KV279: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Admin Area Location: Beneficial Use Rooms Electrical Rooms Trade: Drywall Start Date: 24-Jan-2025 End Date: 25-Jan-2025
Note on KY279: Activity Name: Secondary / Ceiling Steel Phase: Fitout Admin Area Location: Beneficial Use Rooms Electrical Rooms Trade: Framing Start Date: 27-Jan-2025 End Date: 27-Jan-2025
Note on KZ279: Activity Name: Finish Drywall and Wall Protection Phase: Fitout Admin Area Location: Beneficial Use Rooms Electrical Rooms Trade: Drywall Start Date: 28-Jan-2025 End Date: 31-Jan-2025
Note on LD279: Activity Name: Paint Phase: Fitout Admin Area Location: Beneficial Use Rooms Electrical Rooms Trade: Painting Start Date: 01-Feb-2025 End Date: 03-Feb-2025
Note on LG279: Activity Name: Cable Tray / Ceiling Steel Height Phase: Fitout Admin Area Location: Beneficial Use Rooms Electrical Rooms Trade: Electrical Start Date: 04-Feb-2025 End Date: 04-Feb-2025
Note on MH279: Activity Name: Set Electrical Equipment Phase: Fitout Admin Area Location: Beneficial Use Rooms Electrical Rooms Trade: Electrical Start Date: 03-Mar-2025 End Date: 11-Mar-2025
Note on MQ279: Activity Name: Pull Feeders Phase: Fitout Admin Area Location: Beneficial Use Rooms Electrical Rooms Trade: Electrical Start Date: 12-Mar-2025 End Date: 28-Mar-2025
Note on NH279: Activity Name: Pull Branches Phase: Fitout Admin Area Location: Beneficial Use Rooms Electrical Rooms Trade: Electrical Start Date: 29-Mar-2025 End Date: 11-Apr-2025
Note on NX279: Activity Name: Terminate Electrical / Mechanical Equipment Phase: Fitout Admin Area Location: Beneficial Use Rooms Electrical Rooms Trade: Electrical Start Date: 14-Apr-2025 End Date: 17-Apr-2025
Note on KS283: Activity Name: Fire Protection OH R/I Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room1 Trade: Fire Protection Start Date: 21-Jan-2025 End Date: 21-Jan-2025
Note on KT283: Activity Name: Framing Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room1 Trade: Framing Start Date: 22-Jan-2025 End Date: 22-Jan-2025
Note on KV283: Activity Name: MEP Rough-In & OH Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room1 Trade: MEP Start Date: 24-Jan-2025 End Date: 25-Jan-2025
Note on KY283: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room1 Trade: Drywall Start Date: 27-Jan-2025 End Date: 28-Jan-2025
Note on LA283: Activity Name: Secondary / Ceiling Steel Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room1 Trade: Framing Start Date: 29-Jan-2025 End Date: 29-Jan-2025
Note on LB283: Activity Name: Finish Drywall and Wall Protection Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room1 Trade: Drywall Start Date: 30-Jan-2025 End Date: 03-Feb-2025
Note on LG283: Activity Name: Paint Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room1 Trade: Painting Start Date: 04-Feb-2025 End Date: 05-Feb-2025
Note on LI283: Activity Name: Install Raceway Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room1 Trade: Electrical Start Date: 06-Feb-2025 End Date: 10-Feb-2025
Note on LN283: Activity Name: Set ER-1 Equipment Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room1 Trade: Electrical Start Date: 11-Feb-2025 End Date: 14-Feb-2025
Note on KT287: Activity Name: Fire Protection OH R/I Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room2 Trade: Fire Protection Start Date: 22-Jan-2025 End Date: 22-Jan-2025
Note on KU287: Activity Name: Framing Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room2 Trade: Framing Start Date: 23-Jan-2025 End Date: 23-Jan-2025
Note on KY287: Activity Name: MEP Rough-In & OH Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room2 Trade: MEP Start Date: 27-Jan-2025 End Date: 28-Jan-2025
Note on LA287: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room2 Trade: Drywall Start Date: 29-Jan-2025 End Date: 30-Jan-2025
Note on LC287: Activity Name: Secondary / Ceiling Steel Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room2 Trade: Framing Start Date: 31-Jan-2025 End Date: 31-Jan-2025
Note on LD287: Activity Name: Finish Drywall and Wall Protection Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room2 Trade: Drywall Start Date: 01-Feb-2025 End Date: 05-Feb-2025
Note on LI287: Activity Name: Paint Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room2 Trade: Painting Start Date: 06-Feb-2025 End Date: 07-Feb-2025
Note on LM287: Activity Name: Install Raceway Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room2 Trade: Electrical Start Date: 10-Feb-2025 End Date: 12-Feb-2025
Note on LP287: Activity Name: Set ER-2 Equipment Phase: Fitout Admin Area Location: Beneficial Use Rooms Entry Room2 Trade: Electrical Start Date: 13-Feb-2025 End Date: 17-Feb-2025
Note on KU291: Activity Name: Fire Protection OH R/I Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Fire Protection Start Date: 23-Jan-2025 End Date: 23-Jan-2025
Note on KV291: Activity Name: Framing Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Framing Start Date: 24-Jan-2025 End Date: 24-Jan-2025
Note on LA291: Activity Name: MEP Rough-In & OH Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: MEP Start Date: 29-Jan-2025 End Date: 30-Jan-2025
Note on LC291: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Drywall Start Date: 31-Jan-2025 End Date: 01-Feb-2025
Note on LF291: Activity Name: Secondary / Ceiling Steel Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Framing Start Date: 03-Feb-2025 End Date: 03-Feb-2025
Note on LG291: Activity Name: Finish Drywall and Wall Protection Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Drywall Start Date: 04-Feb-2025 End Date: 07-Feb-2025
Note on LM291: Activity Name: Paint Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Painting Start Date: 10-Feb-2025 End Date: 11-Feb-2025
Note on LO291: Activity Name: Install Raceway Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Electrical Start Date: 12-Feb-2025 End Date: 14-Feb-2025
Note on LR291: Activity Name: Set FCR Equipment Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Electrical Start Date: 15-Feb-2025 End Date: 19-Feb-2025
Note on LW291: Activity Name: Pull Copper for EPMS VLAN Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Telecom Start Date: 20-Feb-2025 End Date: 06-Mar-2025
Note on ML291: Activity Name: Pull Copper for Tahuya VLAN Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Telecom Start Date: 07-Mar-2025 End Date: 20-Mar-2025
Note on MZ291: Activity Name: Pull Copper for BAS VLAN Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Telecom Start Date: 21-Mar-2025 End Date: 04-Apr-2025
Note on NO291: Activity Name: Pull Fiber/Copper For CORPNET Network Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Telecom Start Date: 05-Apr-2025 End Date: 19-Apr-2025
Note on OE291: Activity Name: Pull Fiber For CEI Network Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Telecom Start Date: 21-Apr-2025 End Date: 05-May-2025
Note on LW292: Activity Name: Pull Fiber For EPMS VLAN Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Telecom Start Date: 20-Feb-2025 End Date: 06-Mar-2025
Note on ML292: Activity Name: Pull Fiber For Tahuya VLAN Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Telecom Start Date: 07-Mar-2025 End Date: 20-Mar-2025
Note on MZ292: Activity Name: Pull Fiber For BAS VLAN Phase: Fitout Admin Area Location: Beneficial Use Rooms FCR (Facilities Control Room) Trade: Telecom Start Date: 21-Mar-2025 End Date: 04-Apr-2025
Note on OT296: Activity Name: PunchList Phase: Fitout Admin Area Location: Beneficial Use Rooms Punchlist Trade: CLAYCO Start Date: 06-May-2025 End Date: 09-May-2025
Note on KV297: Activity Name: Fire Protection OH R/I Phase: Fitout Admin Area Location: Beneficial Use Rooms SER (Security Equip Room) Trade: Fire Protection Start Date: 24-Jan-2025 End Date: 24-Jan-2025
Note on KW297: Activity Name: Framing Phase: Fitout Admin Area Location: Beneficial Use Rooms SER (Security Equip Room) Trade: Framing Start Date: 25-Jan-2025 End Date: 25-Jan-2025
Note on LC297: Activity Name: MEP Rough-In & OH Phase: Fitout Admin Area Location: Beneficial Use Rooms SER (Security Equip Room) Trade: MEP Start Date: 31-Jan-2025 End Date: 01-Feb-2025
Note on LF297: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Admin Area Location: Beneficial Use Rooms SER (Security Equip Room) Trade: Drywall Start Date: 03-Feb-2025 End Date: 04-Feb-2025
Note on LH297: Activity Name: Secondary / Ceiling Steel Phase: Fitout Admin Area Location: Beneficial Use Rooms SER (Security Equip Room) Trade: Framing Start Date: 05-Feb-2025 End Date: 05-Feb-2025
Note on LI297: Activity Name: Finish Drywall Phase: Fitout Admin Area Location: Beneficial Use Rooms SER (Security Equip Room) Trade: Drywall Start Date: 06-Feb-2025 End Date: 07-Feb-2025
Note on LM297: Activity Name: Paint Phase: Fitout Admin Area Location: Beneficial Use Rooms SER (Security Equip Room) Trade: Painting Start Date: 10-Feb-2025 End Date: 11-Feb-2025
Note on LO297: Activity Name: Install Raceway Phase: Fitout Admin Area Location: Beneficial Use Rooms SER (Security Equip Room) Trade: Electrical Start Date: 12-Feb-2025 End Date: 14-Feb-2025
Note on LR297: Activity Name: Set SER Room Equipment Phase: Fitout Admin Area Location: Beneficial Use Rooms SER (Security Equip Room) Trade: Electrical Start Date: 15-Feb-2025 End Date: 19-Feb-2025
Note on KW301: Activity Name: Fire Protection OH R/I Phase: Fitout Admin Area Location: Beneficial Use Rooms Storage (High Value & Secure) Rooms Trade: Fire Protection Start Date: 25-Jan-2025 End Date: 25-Jan-2025
Note on KY301: Activity Name: Framing Phase: Fitout Admin Area Location: Beneficial Use Rooms Storage (High Value & Secure) Rooms Trade: Framing Start Date: 27-Jan-2025 End Date: 27-Jan-2025
Note on LF301: Activity Name: MEP Rough-In & OH Phase: Fitout Admin Area Location: Beneficial Use Rooms Storage (High Value & Secure) Rooms Trade: MEP Start Date: 03-Feb-2025 End Date: 04-Feb-2025
Note on LH301: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Admin Area Location: Beneficial Use Rooms Storage (High Value & Secure) Rooms Trade: Drywall Start Date: 05-Feb-2025 End Date: 06-Feb-2025
Note on LJ301: Activity Name: Install Ductwork and Cracs Phase: Fitout Admin Area Location: Beneficial Use Rooms Storage (High Value & Secure) Rooms Trade: Mech Start Date: 07-Feb-2025 End Date: 25-Feb-2025
Note on MC301: Activity Name: Finish Drywall Phase: Fitout Admin Area Location: Beneficial Use Rooms Storage (High Value & Secure) Rooms Trade: Drywall Start Date: 26-Feb-2025 End Date: 03-Mar-2025
Note on MI301: Activity Name: Paint Phase: Fitout Admin Area Location: Beneficial Use Rooms Storage (High Value & Secure) Rooms Trade: Painting Start Date: 04-Mar-2025 End Date: 05-Mar-2025
Note on MK301: Activity Name: Fit-out Phase: Fitout Admin Area Location: Beneficial Use Rooms Storage (High Value & Secure) Rooms Trade: CLAYCO Start Date: 06-Mar-2025 End Date: 17-Mar-2025
Note on LY305: Activity Name: Install Doors Phase: Fitout Admin Area Location: Remaining Rooms Admin Gen Finishes & Punch Trade: Framing Start Date: 22-Feb-2025 End Date: 26-Feb-2025
Note on MD305: Activity Name: Light Fixtures Installation Phase: Fitout Admin Area Location: Remaining Rooms Admin Gen Finishes & Punch Trade: Electrical Start Date: 27-Feb-2025 End Date: 11-Mar-2025
Note on MQ305: Activity Name: Remaining Area Punchlist Phase: Fitout Admin Area Location: Remaining Rooms Admin Gen Finishes & Punch Trade: CLAYCO Start Date: 12-Mar-2025 End Date: 17-Mar-2025
Note on KY308: Activity Name: Fire Protection OH R/I Phase: Fitout Admin Area Location: Remaining Rooms Fire Riser Room Trade: Fire Protection Start Date: 27-Jan-2025 End Date: 27-Jan-2025
Note on KZ308: Activity Name: Framing Phase: Fitout Admin Area Location: Remaining Rooms Fire Riser Room Trade: Framing Start Date: 28-Jan-2025 End Date: 28-Jan-2025
Note on LA308: Activity Name: Install Duct Work Phase: Fitout Admin Area Location: Remaining Rooms Fire Riser Room Trade: Mech Start Date: 29-Jan-2025 End Date: 30-Jan-2025
Note on LC308: Activity Name: Install downcomers Phase: Fitout Admin Area Location: Remaining Rooms Fire Riser Room Trade: Framing Start Date: 31-Jan-2025 End Date: 31-Jan-2025
Note on LH308: Activity Name: MEP Rough-In & OH Phase: Fitout Admin Area Location: Remaining Rooms Fire Riser Room Trade: MEP Start Date: 05-Feb-2025 End Date: 06-Feb-2025
Note on LJ308: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Admin Area Location: Remaining Rooms Fire Riser Room Trade: Drywall Start Date: 07-Feb-2025 End Date: 10-Feb-2025
Note on LN308: Activity Name: Secondary / Ceiling Steel Phase: Fitout Admin Area Location: Remaining Rooms Fire Riser Room Trade: Framing Start Date: 11-Feb-2025 End Date: 11-Feb-2025
Note on LO308: Activity Name: Finish Drywall Phase: Fitout Admin Area Location: Remaining Rooms Fire Riser Room Trade: Drywall Start Date: 12-Feb-2025 End Date: 13-Feb-2025
Note on LQ308: Activity Name: Paint Phase: Fitout Admin Area Location: Remaining Rooms Fire Riser Room Trade: Painting Start Date: 14-Feb-2025 End Date: 15-Feb-2025
Note on LU308: Activity Name: Ceiling Grid & Tile Phase: Fitout Admin Area Location: Remaining Rooms Fire Riser Room Trade: Framing Start Date: 18-Feb-2025 End Date: 21-Feb-2025
Note on LY308: Activity Name: Complete Pipe/ Valves Phase: Fitout Admin Area Location: Remaining Rooms Fire Riser Room Trade: Fire Protection Start Date: 22-Feb-2025 End Date: 24-Feb-2025
Note on LA312: Activity Name: Fire Protection OH R/I Phase: Fitout Admin Area Location: Remaining Rooms Loading Dock Trade: Fire Protection Start Date: 29-Jan-2025 End Date: 29-Jan-2025
Note on LB312: Activity Name: Framing Phase: Fitout Admin Area Location: Remaining Rooms Loading Dock Trade: Framing Start Date: 30-Jan-2025 End Date: 30-Jan-2025
Note on LC312: Activity Name: Rough-in Phase: Fitout Admin Area Location: Remaining Rooms Loading Dock Trade: MEP Start Date: 31-Jan-2025 End Date: 31-Jan-2025
Note on LN312: Activity Name: MEP Rough-In & OH Phase: Fitout Admin Area Location: Remaining Rooms Loading Dock Trade: MEP Start Date: 11-Feb-2025 End Date: 12-Feb-2025
Note on LP312: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Admin Area Location: Remaining Rooms Loading Dock Trade: Drywall Start Date: 13-Feb-2025 End Date: 14-Feb-2025
Note on LR312: Activity Name: Finish Drywall Phase: Fitout Admin Area Location: Remaining Rooms Loading Dock Trade: Drywall Start Date: 15-Feb-2025 End Date: 17-Feb-2025
Note on LU312: Activity Name: Paint Phase: Fitout Admin Area Location: Remaining Rooms Loading Dock Trade: Painting Start Date: 18-Feb-2025 End Date: 19-Feb-2025
Note on LW312: Activity Name: Plumbing Phase: Fitout Admin Area Location: Remaining Rooms Loading Dock Trade: Plumbing Start Date: 20-Feb-2025 End Date: 10-Mar-2025
Note on MP312: Activity Name: Pull Cables Phase: Fitout Admin Area Location: Remaining Rooms Loading Dock Trade: Electrical Start Date: 11-Mar-2025 End Date: 13-Mar-2025
Note on LA313: Activity Name: Install Ductwork Phase: Fitout Admin Area Location: Remaining Rooms Loading Dock Trade: Mech Start Date: 29-Jan-2025 End Date: 15-Feb-2025
Note on LB314: Activity Name: Install Ductwork (Remaining Rooms, Corridor) Phase: Fitout Admin Area Location: Remaining Rooms Loading Dock Trade: Mech Start Date: 30-Jan-2025 End Date: 17-Feb-2025
Note on KZ318: Activity Name: Fire Protection OH R/I Phase: Fitout Admin Area Location: Remaining Rooms Restrooms & Janitor Room Trade: Fire Protection Start Date: 28-Jan-2025 End Date: 28-Jan-2025
Note on LA318: Activity Name: Framing Phase: Fitout Admin Area Location: Remaining Rooms Restrooms & Janitor Room Trade: Framing Start Date: 29-Jan-2025 End Date: 29-Jan-2025
Note on LJ318: Activity Name: MEP Rough-In & OH Phase: Fitout Admin Area Location: Remaining Rooms Restrooms & Janitor Room Trade: MEP Start Date: 07-Feb-2025 End Date: 10-Feb-2025
Note on LN318: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Admin Area Location: Remaining Rooms Restrooms & Janitor Room Trade: Drywall Start Date: 11-Feb-2025 End Date: 12-Feb-2025
Note on LP318: Activity Name: Finish Drywall Phase: Fitout Admin Area Location: Remaining Rooms Restrooms & Janitor Room Trade: Drywall Start Date: 13-Feb-2025 End Date: 14-Feb-2025
Note on LR318: Activity Name: Paint Phase: Fitout Admin Area Location: Remaining Rooms Restrooms & Janitor Room Trade: Painting Start Date: 15-Feb-2025 End Date: 17-Feb-2025
Note on LU318: Activity Name: Ceiling Grid & Tile Phase: Fitout Admin Area Location: Remaining Rooms Restrooms & Janitor Room Trade: Framing Start Date: 18-Feb-2025 End Date: 21-Feb-2025
Note on MA322: Activity Name: Layout Framing Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Framing Start Date: 24-Feb-2025 End Date: 24-Feb-2025
Note on MB322: Activity Name: Framing Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Framing Start Date: 25-Feb-2025 End Date: 27-Feb-2025
Note on ME322: Activity Name: In-Wall R/I Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Drywall Start Date: 28-Feb-2025 End Date: 04-Mar-2025
Note on MJ322: Activity Name: Install Drywall Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Drywall Start Date: 05-Mar-2025 End Date: 07-Mar-2025
Note on MM322: Activity Name: Finish Drywall Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Drywall Start Date: 08-Mar-2025 End Date: 11-Mar-2025
Note on MQ322: Activity Name: Paint Dry-Wall Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Painting Start Date: 12-Mar-2025 End Date: 14-Mar-2025
Note on MT322: Activity Name: Install Screen Mesh + Caulking Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Framing Start Date: 15-Mar-2025 End Date: 18-Mar-2025
Note on MX322: Activity Name: Install Secondary Steel Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Framing Start Date: 19-Mar-2025 End Date: 20-Mar-2025
Note on MZ322: Activity Name: Paint Secondary Steel Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Painting Start Date: 21-Mar-2025 End Date: 24-Mar-2025
Note on ND322: Activity Name: General Cleaning Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: CLAYCO Start Date: 25-Mar-2025 End Date: 25-Mar-2025
Note on NH322: Activity Name: Install Perimeter Cable Trays Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Electrical Start Date: 29-Mar-2025 End Date: 02-Apr-2025
Note on NM322: Activity Name: Install Device Tiles Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Framing Start Date: 03-Apr-2025 End Date: 04-Apr-2025
Note on NS322: Activity Name: Raise HACs Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: HACs Start Date: 09-Apr-2025 End Date: 14-Apr-2025
Note on NY322: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Electrical Start Date: 15-Apr-2025 End Date: 17-Apr-2025
Note on OB322: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Electrical Start Date: 18-Apr-2025 End Date: 21-Apr-2025
Note on OF322: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Electrical Start Date: 22-Apr-2025 End Date: 26-Apr-2025
Note on OO322: Activity Name: Terminate PDUs Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Electrical Start Date: 01-May-2025 End Date: 05-May-2025
Note on MJ323: Activity Name: Fire Protection OH R/I Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Fire Protection Start Date: 05-Mar-2025 End Date: 07-Mar-2025
Note on MM323: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Fire Protection Start Date: 08-Mar-2025 End Date: 11-Mar-2025
Note on MP323: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Framing Start Date: 11-Mar-2025 End Date: 12-Mar-2025
Note on ND323: Activity Name: Install Ceiling Grid Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Framing Start Date: 25-Mar-2025 End Date: 28-Mar-2025
Note on NH323: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: HACs Start Date: 29-Mar-2025 End Date: 03-Apr-2025
Note on NM323: Activity Name: Set PDUs Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Electrical Start Date: 03-Apr-2025 End Date: 07-Apr-2025
Note on NY323: Activity Name: Detail HACs Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: HACs Start Date: 15-Apr-2025 End Date: 18-Apr-2025
Note on MM324: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Electrical Start Date: 08-Mar-2025 End Date: 12-Mar-2025
Note on MP324: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Mech Start Date: 11-Mar-2025 End Date: 12-Mar-2025
Note on NK324: Activity Name: Install Busways on HAC Arms Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Electrical Start Date: 01-Apr-2025 End Date: 05-Apr-2025
Note on NM325: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout COLO4 Location: C4 CELL 1 Data Hall Trade: Electrical Start Date: 03-Apr-2025 End Date: 08-Apr-2025
Note on ME330: Activity Name: Framing Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Framing Start Date: 28-Feb-2025 End Date: 03-Mar-2025
Note on MI330: Activity Name: In-Wall R/I Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Drywall Start Date: 04-Mar-2025 End Date: 05-Mar-2025
Note on MK330: Activity Name: Fire Protection OH R/I Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Fire Protection Start Date: 06-Mar-2025 End Date: 07-Mar-2025
Note on MM330: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Fire Protection Start Date: 08-Mar-2025 End Date: 10-Mar-2025
Note on MP330: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Framing Start Date: 11-Mar-2025 End Date: 11-Mar-2025
Note on MQ330: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Electrical Start Date: 12-Mar-2025 End Date: 13-Mar-2025
Note on MT330: Activity Name: General Cleaning Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: CLAYCO Start Date: 15-Mar-2025 End Date: 15-Mar-2025
Note on NJ330: Activity Name: Set Electrical Equipments Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Electrical Start Date: 31-Mar-2025 End Date: 03-Apr-2025
Note on NN330: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Electrical Start Date: 04-Apr-2025 End Date: 17-Apr-2025
Note on OB330: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Electrical Start Date: 18-Apr-2025 End Date: 22-Apr-2025
Note on MK331: Activity Name: Install Drywall Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Drywall Start Date: 06-Mar-2025 End Date: 10-Mar-2025
Note on MP331: Activity Name: Finish Drywall Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Drywall Start Date: 11-Mar-2025 End Date: 12-Mar-2025
Note on MR331: Activity Name: Paint Dry-Wall Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Painting Start Date: 13-Mar-2025 End Date: 14-Mar-2025
Note on OB331: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Electrical Start Date: 18-Apr-2025 End Date: 30-Apr-2025
Note on MM332: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO4 Location: C4 CELL 1 Electrical Room Trade: Electrical Start Date: 08-Mar-2025 End Date: 11-Mar-2025
Note on MM336: Activity Name: Fire Protection OH R/I Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Fire Protection Start Date: 08-Mar-2025 End Date: 10-Mar-2025
Note on MP336: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Fire Protection Start Date: 11-Mar-2025 End Date: 12-Mar-2025
Note on MS336: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Mech Start Date: 14-Mar-2025 End Date: 20-Mar-2025
Note on MZ336: Activity Name: Overhead R/I - Plumbing Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Plumbing Start Date: 21-Mar-2025 End Date: 28-Mar-2025
Note on NH336: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Framing Start Date: 29-Mar-2025 End Date: 29-Mar-2025
Note on NJ336: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Framing Start Date: 31-Mar-2025 End Date: 03-Apr-2025
Note on NN336: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Electrical Start Date: 04-Apr-2025 End Date: 05-Apr-2025
Note on NQ336: Activity Name: Set Mechanical Equipments Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Mech Start Date: 07-Apr-2025 End Date: 10-Apr-2025
Note on NU336: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Electrical Start Date: 11-Apr-2025 End Date: 25-Apr-2025
Note on OJ336: Activity Name: Terminate Mechanical Equipments Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Mech Start Date: 26-Apr-2025 End Date: 30-Apr-2025
Note on MP337: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Electrical Start Date: 11-Mar-2025 End Date: 13-Mar-2025
Note on NF337: Activity Name: Install Drywall Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Drywall Start Date: 27-Mar-2025 End Date: 28-Mar-2025
Note on NH337: Activity Name: Finish Drywall Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Drywall Start Date: 29-Mar-2025 End Date: 31-Mar-2025
Note on NK337: Activity Name: Paint Dry-Wall Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: Painting Start Date: 01-Apr-2025 End Date: 02-Apr-2025
Note on NM337: Activity Name: General Cleaning Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: CLAYCO Start Date: 03-Apr-2025 End Date: 05-Apr-2025
Note on OA337: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: BAS Start Date: 17-Apr-2025 End Date: 25-Apr-2025
Note on NN338: Activity Name: Install BAS Equipments Phase: Fitout COLO4 Location: C4 CELL 1 Mechanical Gallery Trade: BAS Start Date: 04-Apr-2025 End Date: 16-Apr-2025
Note on OT342: Activity Name: Punchlist Phase: Fitout COLO4 Location: C4 CELL 1 Punchlist Trade: CLAYCO Start Date: 06-May-2025 End Date: 16-May-2025
Note on MJ343: Activity Name: Layout Framing Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Framing Start Date: 05-Mar-2025 End Date: 05-Mar-2025
Note on MK343: Activity Name: Framing Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Framing Start Date: 06-Mar-2025 End Date: 08-Mar-2025
Note on MO343: Activity Name: In-Wall R/I Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Drywall Start Date: 10-Mar-2025 End Date: 12-Mar-2025
Note on MR343: Activity Name: Install Drywall Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Drywall Start Date: 13-Mar-2025 End Date: 15-Mar-2025
Note on MV343: Activity Name: Finish Drywall Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Drywall Start Date: 17-Mar-2025 End Date: 19-Mar-2025
Note on MY343: Activity Name: Paint Dry-Wall Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Painting Start Date: 20-Mar-2025 End Date: 24-Mar-2025
Note on ND343: Activity Name: Install Screen Mesh + Caulking Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Framing Start Date: 25-Mar-2025 End Date: 27-Mar-2025
Note on NG343: Activity Name: Install Secondary Steel Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Framing Start Date: 28-Mar-2025 End Date: 29-Mar-2025
Note on NJ343: Activity Name: Paint Secondary Steel Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Painting Start Date: 31-Mar-2025 End Date: 01-Apr-2025
Note on NL343: Activity Name: General Cleaning Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: CLAYCO Start Date: 02-Apr-2025 End Date: 02-Apr-2025
Note on NQ343: Activity Name: Install Perimeter Cable Trays Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Electrical Start Date: 07-Apr-2025 End Date: 10-Apr-2025
Note on NU343: Activity Name: Install Device Tiles Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Framing Start Date: 11-Apr-2025 End Date: 14-Apr-2025
Note on OB343: Activity Name: Raise HACs Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: HACs Start Date: 18-Apr-2025 End Date: 22-Apr-2025
Note on OG343: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Electrical Start Date: 23-Apr-2025 End Date: 25-Apr-2025
Note on OJ343: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Electrical Start Date: 26-Apr-2025 End Date: 29-Apr-2025
Note on ON343: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Electrical Start Date: 30-Apr-2025 End Date: 06-May-2025
Note on PP343: Activity Name: Terminate PDUs Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Electrical Start Date: 28-May-2025 End Date: 30-May-2025
Note on MR344: Activity Name: Fire Protection OH R/I Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Fire Protection Start Date: 13-Mar-2025 End Date: 15-Mar-2025
Note on MV344: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Fire Protection Start Date: 17-Mar-2025 End Date: 19-Mar-2025
Note on MX344: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Framing Start Date: 19-Mar-2025 End Date: 20-Mar-2025
Note on NL344: Activity Name: Install Ceiling Grid Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Framing Start Date: 02-Apr-2025 End Date: 05-Apr-2025
Note on NQ344: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: HACs Start Date: 07-Apr-2025 End Date: 11-Apr-2025
Note on NU344: Activity Name: Set PDUs Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Electrical Start Date: 11-Apr-2025 End Date: 16-Apr-2025
Note on OG344: Activity Name: Detail HACs Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: HACs Start Date: 23-Apr-2025 End Date: 26-Apr-2025
Note on MV345: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Electrical Start Date: 17-Mar-2025 End Date: 20-Mar-2025
Note on MX345: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Mech Start Date: 19-Mar-2025 End Date: 20-Mar-2025
Note on NS345: Activity Name: Install Busways on HAC Arms Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Electrical Start Date: 09-Apr-2025 End Date: 15-Apr-2025
Note on NU346: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout COLO4 Location: C4 CELL 2 Data Hall Trade: Electrical Start Date: 11-Apr-2025 End Date: 17-Apr-2025
Note on MO351: Activity Name: Framing Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Framing Start Date: 10-Mar-2025 End Date: 11-Mar-2025
Note on MQ351: Activity Name: In-Wall R/I Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Drywall Start Date: 12-Mar-2025 End Date: 13-Mar-2025
Note on MS351: Activity Name: Fire Protection OH R/I Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Fire Protection Start Date: 14-Mar-2025 End Date: 15-Mar-2025
Note on MV351: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Fire Protection Start Date: 17-Mar-2025 End Date: 18-Mar-2025
Note on MX351: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Framing Start Date: 19-Mar-2025 End Date: 19-Mar-2025
Note on MY351: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Electrical Start Date: 20-Mar-2025 End Date: 21-Mar-2025
Note on ND351: Activity Name: General Cleaning Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: CLAYCO Start Date: 25-Mar-2025 End Date: 25-Mar-2025
Note on NE351: Activity Name: Set Electrical Equipments Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Electrical Start Date: 26-Mar-2025 End Date: 29-Mar-2025
Note on OO351: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Electrical Start Date: 01-May-2025 End Date: 14-May-2025
Note on PC351: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Electrical Start Date: 15-May-2025 End Date: 19-May-2025
Note on MS352: Activity Name: Install Drywall Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Drywall Start Date: 14-Mar-2025 End Date: 18-Mar-2025
Note on MX352: Activity Name: Finish Drywall Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Drywall Start Date: 19-Mar-2025 End Date: 20-Mar-2025
Note on MZ352: Activity Name: Paint Dry-Wall Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Painting Start Date: 21-Mar-2025 End Date: 24-Mar-2025
Note on PC352: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Electrical Start Date: 15-May-2025 End Date: 27-May-2025
Note on MV353: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO4 Location: C4 CELL 2 Electrical Room Trade: Electrical Start Date: 17-Mar-2025 End Date: 19-Mar-2025
Note on MV357: Activity Name: Fire Protection OH R/I Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Fire Protection Start Date: 17-Mar-2025 End Date: 18-Mar-2025
Note on MX357: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Fire Protection Start Date: 19-Mar-2025 End Date: 20-Mar-2025
Note on NC357: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Mech Start Date: 24-Mar-2025 End Date: 29-Mar-2025
Note on NJ357: Activity Name: Overhead R/I - Plumbing Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Plumbing Start Date: 31-Mar-2025 End Date: 05-Apr-2025
Note on NQ357: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Framing Start Date: 07-Apr-2025 End Date: 07-Apr-2025
Note on NR357: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Framing Start Date: 08-Apr-2025 End Date: 11-Apr-2025
Note on NX357: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Electrical Start Date: 14-Apr-2025 End Date: 15-Apr-2025
Note on NZ357: Activity Name: Set Mechanical Equipments Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Mech Start Date: 16-Apr-2025 End Date: 19-Apr-2025
Note on OE357: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Electrical Start Date: 21-Apr-2025 End Date: 05-May-2025
Note on OT357: Activity Name: Terminate Mechanical Equipments Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Mech Start Date: 06-May-2025 End Date: 09-May-2025
Note on MX358: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Electrical Start Date: 19-Mar-2025 End Date: 21-Mar-2025
Note on NN358: Activity Name: Install Drywall Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Drywall Start Date: 04-Apr-2025 End Date: 05-Apr-2025
Note on NQ358: Activity Name: Finish Drywall Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Drywall Start Date: 07-Apr-2025 End Date: 08-Apr-2025
Note on NS358: Activity Name: Paint Dry-Wall Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: Painting Start Date: 09-Apr-2025 End Date: 10-Apr-2025
Note on NU358: Activity Name: General Cleaning Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: CLAYCO Start Date: 11-Apr-2025 End Date: 15-Apr-2025
Note on OI358: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: BAS Start Date: 25-Apr-2025 End Date: 05-May-2025
Note on NX359: Activity Name: Install BAS Equipments Phase: Fitout COLO4 Location: C4 CELL 2 Mechanical Gallery Trade: BAS Start Date: 14-Apr-2025 End Date: 24-Apr-2025
Note on PS363: Activity Name: Punchlist Phase: Fitout COLO4 Location: C4 CELL 2 Punchlist Trade: CLAYCO Start Date: 31-May-2025 End Date: 11-Jun-2025
Note on NG364: Activity Name: Layout Framing Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Framing Start Date: 28-Mar-2025 End Date: 28-Mar-2025
Note on NH364: Activity Name: Framing Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Framing Start Date: 29-Mar-2025 End Date: 01-Apr-2025
Note on NL364: Activity Name: In-Wall R/I Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Drywall Start Date: 02-Apr-2025 End Date: 04-Apr-2025
Note on NO364: Activity Name: Install Drywall Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Drywall Start Date: 05-Apr-2025 End Date: 08-Apr-2025
Note on NS364: Activity Name: Finish Drywall Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Drywall Start Date: 09-Apr-2025 End Date: 11-Apr-2025
Note on NX364: Activity Name: Paint Dry-Wall Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Painting Start Date: 14-Apr-2025 End Date: 16-Apr-2025
Note on OA364: Activity Name: Install Screen Mesh + Caulking Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Framing Start Date: 17-Apr-2025 End Date: 19-Apr-2025
Note on OE364: Activity Name: Install Secondary Steel Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Framing Start Date: 21-Apr-2025 End Date: 22-Apr-2025
Note on OG364: Activity Name: Paint Secondary Steel Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Painting Start Date: 23-Apr-2025 End Date: 24-Apr-2025
Note on OI364: Activity Name: General Cleaning Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: CLAYCO Start Date: 25-Apr-2025 End Date: 25-Apr-2025
Note on ON364: Activity Name: Install Perimeter Cable Trays Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Electrical Start Date: 30-Apr-2025 End Date: 05-May-2025
Note on OT364: Activity Name: Install Device Tiles Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Framing Start Date: 06-May-2025 End Date: 07-May-2025
Note on OZ364: Activity Name: Raise HACs Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: HACs Start Date: 12-May-2025 End Date: 15-May-2025
Note on PD364: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Electrical Start Date: 16-May-2025 End Date: 19-May-2025
Note on PH364: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Electrical Start Date: 20-May-2025 End Date: 22-May-2025
Note on PK364: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Electrical Start Date: 23-May-2025 End Date: 29-May-2025
Note on RO364: Activity Name: Terminate PDUs Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Electrical Start Date: 18-Jul-2025 End Date: 21-Jul-2025
Note on NO365: Activity Name: Fire Protection OH R/I Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Fire Protection Start Date: 05-Apr-2025 End Date: 08-Apr-2025
Note on NS365: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Fire Protection Start Date: 09-Apr-2025 End Date: 11-Apr-2025
Note on NU365: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Framing Start Date: 11-Apr-2025 End Date: 14-Apr-2025
Note on OI365: Activity Name: Install Ceiling Grid Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Framing Start Date: 25-Apr-2025 End Date: 29-Apr-2025
Note on ON365: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: HACs Start Date: 30-Apr-2025 End Date: 06-May-2025
Note on OT365: Activity Name: Set PDUs Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Electrical Start Date: 06-May-2025 End Date: 09-May-2025
Note on PD365: Activity Name: Detail HACs Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: HACs Start Date: 16-May-2025 End Date: 20-May-2025
Note on NS366: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Electrical Start Date: 09-Apr-2025 End Date: 14-Apr-2025
Note on OP366: Activity Name: Install Busways on HAC Arms Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Electrical Start Date: 02-May-2025 End Date: 08-May-2025
Note on NU367: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Mech Start Date: 11-Apr-2025 End Date: 14-Apr-2025
Note on OT367: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout COLO4 Location: C4 CELL 3 Data Hall Trade: Electrical Start Date: 06-May-2025 End Date: 10-May-2025
Note on NL372: Activity Name: Framing Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Framing Start Date: 02-Apr-2025 End Date: 03-Apr-2025
Note on NN372: Activity Name: In-Wall R/I Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Drywall Start Date: 04-Apr-2025 End Date: 05-Apr-2025
Note on NQ372: Activity Name: Fire Protection OH R/I Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Fire Protection Start Date: 07-Apr-2025 End Date: 08-Apr-2025
Note on NS372: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Fire Protection Start Date: 09-Apr-2025 End Date: 10-Apr-2025
Note on NU372: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Framing Start Date: 11-Apr-2025 End Date: 11-Apr-2025
Note on NX372: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Electrical Start Date: 14-Apr-2025 End Date: 15-Apr-2025
Note on OA372: Activity Name: General Cleaning Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: CLAYCO Start Date: 17-Apr-2025 End Date: 17-Apr-2025
Note on OB372: Activity Name: Set Electrical Equipments Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Electrical Start Date: 18-Apr-2025 End Date: 22-Apr-2025
Note on QQ372: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Electrical Start Date: 24-Jun-2025 End Date: 08-Jul-2025
Note on RF372: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Electrical Start Date: 09-Jul-2025 End Date: 12-Jul-2025
Note on NQ373: Activity Name: Install Drywall Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Drywall Start Date: 07-Apr-2025 End Date: 10-Apr-2025
Note on NU373: Activity Name: Finish Drywall Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Drywall Start Date: 11-Apr-2025 End Date: 14-Apr-2025
Note on NY373: Activity Name: Paint Dry-Wall Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Painting Start Date: 15-Apr-2025 End Date: 16-Apr-2025
Note on RF373: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Electrical Start Date: 09-Jul-2025 End Date: 19-Jul-2025
Note on NS374: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO4 Location: C4 CELL 3 Electrical Room Trade: Electrical Start Date: 09-Apr-2025 End Date: 11-Apr-2025
Note on NS378: Activity Name: Fire Protection OH R/I Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Fire Protection Start Date: 09-Apr-2025 End Date: 10-Apr-2025
Note on NU378: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Fire Protection Start Date: 11-Apr-2025 End Date: 14-Apr-2025
Note on NZ378: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Mech Start Date: 16-Apr-2025 End Date: 22-Apr-2025
Note on OG378: Activity Name: Overhead R/I - Plumbing Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Plumbing Start Date: 23-Apr-2025 End Date: 29-Apr-2025
Note on ON378: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Framing Start Date: 30-Apr-2025 End Date: 30-Apr-2025
Note on OO378: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Framing Start Date: 01-May-2025 End Date: 06-May-2025
Note on OU378: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Electrical Start Date: 07-May-2025 End Date: 08-May-2025
Note on OW378: Activity Name: Set Mechanical Equipments Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Mech Start Date: 09-May-2025 End Date: 13-May-2025
Note on PB378: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Electrical Start Date: 14-May-2025 End Date: 28-May-2025
Note on PQ378: Activity Name: Terminate Mechanical Equipments Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Mech Start Date: 29-May-2025 End Date: 02-Jun-2025
Note on NU379: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Electrical Start Date: 11-Apr-2025 End Date: 15-Apr-2025
Note on OL379: Activity Name: Install Drywall Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Drywall Start Date: 28-Apr-2025 End Date: 29-Apr-2025
Note on ON379: Activity Name: Finish Drywall Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Drywall Start Date: 30-Apr-2025 End Date: 01-May-2025
Note on OP379: Activity Name: Paint Dry-Wall Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: Painting Start Date: 02-May-2025 End Date: 05-May-2025
Note on OT379: Activity Name: General Cleaning Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: CLAYCO Start Date: 06-May-2025 End Date: 08-May-2025
Note on PG379: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: BAS Start Date: 19-May-2025 End Date: 28-May-2025
Note on OU380: Activity Name: Install BAS Equipments Phase: Fitout COLO4 Location: C4 CELL 3 Mechanical Gallery Trade: BAS Start Date: 07-May-2025 End Date: 17-May-2025
Note on RS384: Activity Name: Punchlist Phase: Fitout COLO4 Location: C4 CELL 3 Punchlist Trade: CLAYCO Start Date: 22-Jul-2025 End Date: 02-Aug-2025
Note on MT385: Activity Name: Layout Framing Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Framing Start Date: 15-Mar-2025 End Date: 15-Mar-2025
Note on MV385: Activity Name: Framing Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Framing Start Date: 17-Mar-2025 End Date: 19-Mar-2025
Note on MY385: Activity Name: In-Wall R/I Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Drywall Start Date: 20-Mar-2025 End Date: 24-Mar-2025
Note on ND385: Activity Name: Install Drywall Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Drywall Start Date: 25-Mar-2025 End Date: 27-Mar-2025
Note on NG385: Activity Name: Finish Drywall Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Drywall Start Date: 28-Mar-2025 End Date: 31-Mar-2025
Note on NK385: Activity Name: Paint Dry-Wall Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Painting Start Date: 01-Apr-2025 End Date: 03-Apr-2025
Note on NN385: Activity Name: Install Screen Mesh + Caulking Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Framing Start Date: 04-Apr-2025 End Date: 07-Apr-2025
Note on NR385: Activity Name: Install Secondary Steel Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Framing Start Date: 08-Apr-2025 End Date: 09-Apr-2025
Note on NT385: Activity Name: Paint Secondary Steel Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Painting Start Date: 10-Apr-2025 End Date: 11-Apr-2025
Note on NX385: Activity Name: General Cleaning Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: CLAYCO Start Date: 14-Apr-2025 End Date: 14-Apr-2025
Note on OB385: Activity Name: Install Perimeter Cable Trays Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Electrical Start Date: 18-Apr-2025 End Date: 22-Apr-2025
Note on OG385: Activity Name: Install Device Tiles Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Framing Start Date: 23-Apr-2025 End Date: 24-Apr-2025
Note on OM385: Activity Name: Raise HACs Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: HACs Start Date: 29-Apr-2025 End Date: 02-May-2025
Note on OS385: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Electrical Start Date: 05-May-2025 End Date: 07-May-2025
Note on OV385: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Electrical Start Date: 08-May-2025 End Date: 10-May-2025
Note on OZ385: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Electrical Start Date: 12-May-2025 End Date: 16-May-2025
Note on QQ385: Activity Name: Terminate PDUs Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Electrical Start Date: 24-Jun-2025 End Date: 26-Jun-2025
Note on ND386: Activity Name: Fire Protection OH R/I Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Fire Protection Start Date: 25-Mar-2025 End Date: 27-Mar-2025
Note on NG386: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Fire Protection Start Date: 28-Mar-2025 End Date: 31-Mar-2025
Note on NJ386: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Framing Start Date: 31-Mar-2025 End Date: 01-Apr-2025
Note on NX386: Activity Name: Install Ceiling Grid Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Framing Start Date: 14-Apr-2025 End Date: 17-Apr-2025
Note on OB386: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: HACs Start Date: 18-Apr-2025 End Date: 23-Apr-2025
Note on OG386: Activity Name: Set PDUs Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Electrical Start Date: 23-Apr-2025 End Date: 26-Apr-2025
Note on OS386: Activity Name: Detail HACs Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: HACs Start Date: 05-May-2025 End Date: 08-May-2025
Note on NG387: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Electrical Start Date: 28-Mar-2025 End Date: 01-Apr-2025
Note on NJ387: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Mech Start Date: 31-Mar-2025 End Date: 01-Apr-2025
Note on OE387: Activity Name: Install Busways on HAC Arms Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Electrical Start Date: 21-Apr-2025 End Date: 25-Apr-2025
Note on OG388: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout COLO4 Location: C4 CELL 4 Data Hall Trade: Electrical Start Date: 23-Apr-2025 End Date: 28-Apr-2025
Note on MY393: Activity Name: Framing Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Framing Start Date: 20-Mar-2025 End Date: 21-Mar-2025
Note on NC393: Activity Name: In-Wall R/I Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Drywall Start Date: 24-Mar-2025 End Date: 25-Mar-2025
Note on NE393: Activity Name: Fire Protection OH R/I Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Fire Protection Start Date: 26-Mar-2025 End Date: 27-Mar-2025
Note on NG393: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Fire Protection Start Date: 28-Mar-2025 End Date: 29-Mar-2025
Note on NJ393: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Framing Start Date: 31-Mar-2025 End Date: 31-Mar-2025
Note on NK393: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Electrical Start Date: 01-Apr-2025 End Date: 02-Apr-2025
Note on NN393: Activity Name: General Cleaning Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: CLAYCO Start Date: 04-Apr-2025 End Date: 04-Apr-2025
Note on NO393: Activity Name: Set Electrical Equipments Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Electrical Start Date: 05-Apr-2025 End Date: 09-Apr-2025
Note on PP393: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Electrical Start Date: 28-May-2025 End Date: 09-Jun-2025
Note on QC393: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Electrical Start Date: 10-Jun-2025 End Date: 13-Jun-2025
Note on NE394: Activity Name: Install Drywall Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Drywall Start Date: 26-Mar-2025 End Date: 29-Mar-2025
Note on NJ394: Activity Name: Finish Drywall Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Drywall Start Date: 31-Mar-2025 End Date: 01-Apr-2025
Note on NL394: Activity Name: Paint Dry-Wall Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Painting Start Date: 02-Apr-2025 End Date: 03-Apr-2025
Note on QC394: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Electrical Start Date: 10-Jun-2025 End Date: 23-Jun-2025
Note on NG395: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO4 Location: C4 CELL 4 Electrical Room Trade: Electrical Start Date: 28-Mar-2025 End Date: 31-Mar-2025
Note on NG399: Activity Name: Fire Protection OH R/I Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Fire Protection Start Date: 28-Mar-2025 End Date: 29-Mar-2025
Note on NJ399: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Fire Protection Start Date: 31-Mar-2025 End Date: 01-Apr-2025
Note on NM399: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Mech Start Date: 03-Apr-2025 End Date: 09-Apr-2025
Note on NT399: Activity Name: Overhead R/I - Plumbing Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Plumbing Start Date: 10-Apr-2025 End Date: 17-Apr-2025
Note on OB399: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Framing Start Date: 18-Apr-2025 End Date: 18-Apr-2025
Note on OC399: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Framing Start Date: 19-Apr-2025 End Date: 23-Apr-2025
Note on OH399: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Electrical Start Date: 24-Apr-2025 End Date: 25-Apr-2025
Note on OJ399: Activity Name: Set Mechanical Equipments Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Mech Start Date: 26-Apr-2025 End Date: 30-Apr-2025
Note on OO399: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Electrical Start Date: 01-May-2025 End Date: 15-May-2025
Note on PD399: Activity Name: Terminate Mechanical Equipments Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Mech Start Date: 16-May-2025 End Date: 20-May-2025
Note on NJ400: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Electrical Start Date: 31-Mar-2025 End Date: 02-Apr-2025
Note on NZ400: Activity Name: Install Drywall Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Drywall Start Date: 16-Apr-2025 End Date: 17-Apr-2025
Note on OB400: Activity Name: Finish Drywall Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Drywall Start Date: 18-Apr-2025 End Date: 19-Apr-2025
Note on OE400: Activity Name: Paint Dry-Wall Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: Painting Start Date: 21-Apr-2025 End Date: 22-Apr-2025
Note on OG400: Activity Name: General Cleaning Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: CLAYCO Start Date: 23-Apr-2025 End Date: 25-Apr-2025
Note on OU400: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: BAS Start Date: 07-May-2025 End Date: 15-May-2025
Note on OH401: Activity Name: Install BAS Equipments Phase: Fitout COLO4 Location: C4 CELL 4 Mechanical Gallery Trade: BAS Start Date: 24-Apr-2025 End Date: 06-May-2025
Note on QT405: Activity Name: Punchlist Phase: Fitout COLO4 Location: C4 CELL 4 Punchlist Trade: CLAYCO Start Date: 27-Jun-2025 End Date: 10-Jul-2025
Note on NJ406: Activity Name: Layout Framing Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Framing Start Date: 31-Mar-2025 End Date: 31-Mar-2025
Note on NK406: Activity Name: Framing Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Framing Start Date: 01-Apr-2025 End Date: 03-Apr-2025
Note on NN406: Activity Name: In-Wall R/I Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Drywall Start Date: 04-Apr-2025 End Date: 07-Apr-2025
Note on NR406: Activity Name: Install Drywall Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Drywall Start Date: 08-Apr-2025 End Date: 10-Apr-2025
Note on NU406: Activity Name: Finish Drywall Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Drywall Start Date: 11-Apr-2025 End Date: 15-Apr-2025
Note on NZ406: Activity Name: Paint Dry-Wall Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Painting Start Date: 16-Apr-2025 End Date: 18-Apr-2025
Note on OC406: Activity Name: Install Screen Mesh + Caulking Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Framing Start Date: 19-Apr-2025 End Date: 22-Apr-2025
Note on OG406: Activity Name: Install Secondary Steel Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Framing Start Date: 23-Apr-2025 End Date: 24-Apr-2025
Note on OI406: Activity Name: Paint Secondary Steel Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Painting Start Date: 25-Apr-2025 End Date: 26-Apr-2025
Note on OL406: Activity Name: General Cleaning Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: CLAYCO Start Date: 28-Apr-2025 End Date: 28-Apr-2025
Note on OP406: Activity Name: Install Perimeter Cable Trays Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Electrical Start Date: 02-May-2025 End Date: 07-May-2025
Note on OV406: Activity Name: Install Device Tiles Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Framing Start Date: 08-May-2025 End Date: 09-May-2025
Note on PB406: Activity Name: Raise HACs Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: HACs Start Date: 14-May-2025 End Date: 17-May-2025
Note on PG406: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Electrical Start Date: 19-May-2025 End Date: 21-May-2025
Note on PJ406: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Electrical Start Date: 22-May-2025 End Date: 23-May-2025
Note on PO406: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Electrical Start Date: 27-May-2025 End Date: 31-May-2025
Note on PU406: Activity Name: Terminate PDUs Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Electrical Start Date: 02-Jun-2025 End Date: 04-Jun-2025
Note on NR407: Activity Name: Fire Protection OH R/I Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Fire Protection Start Date: 08-Apr-2025 End Date: 10-Apr-2025
Note on NU407: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Fire Protection Start Date: 11-Apr-2025 End Date: 15-Apr-2025
Note on NY407: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Framing Start Date: 15-Apr-2025 End Date: 16-Apr-2025
Note on OL407: Activity Name: Install Ceiling Grid Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Framing Start Date: 28-Apr-2025 End Date: 01-May-2025
Note on OP407: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: HACs Start Date: 02-May-2025 End Date: 08-May-2025
Note on OV407: Activity Name: Set PDUs Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Electrical Start Date: 08-May-2025 End Date: 12-May-2025
Note on PG407: Activity Name: Detail HACs Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: HACs Start Date: 19-May-2025 End Date: 22-May-2025
Note on NU408: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Electrical Start Date: 11-Apr-2025 End Date: 16-Apr-2025
Note on NY408: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Mech Start Date: 15-Apr-2025 End Date: 16-Apr-2025
Note on OT408: Activity Name: Install Busways on HAC Arms Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Electrical Start Date: 06-May-2025 End Date: 10-May-2025
Note on OV409: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout COLO5 Location: C5 CELL 1 Data Hall Trade: Electrical Start Date: 08-May-2025 End Date: 13-May-2025
Note on NN414: Activity Name: Framing Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Framing Start Date: 04-Apr-2025 End Date: 05-Apr-2025
Note on NQ414: Activity Name: In-Wall R/I Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Drywall Start Date: 07-Apr-2025 End Date: 08-Apr-2025
Note on NS414: Activity Name: Fire Protection OH R/I Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Fire Protection Start Date: 09-Apr-2025 End Date: 10-Apr-2025
Note on NU414: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Fire Protection Start Date: 11-Apr-2025 End Date: 14-Apr-2025
Note on NY414: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Framing Start Date: 15-Apr-2025 End Date: 15-Apr-2025
Note on NZ414: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Electrical Start Date: 16-Apr-2025 End Date: 17-Apr-2025
Note on OC414: Activity Name: General Cleaning Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: CLAYCO Start Date: 19-Apr-2025 End Date: 19-Apr-2025
Note on OE414: Activity Name: Set Electrical Equipments Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Electrical Start Date: 21-Apr-2025 End Date: 01-May-2025
Note on OP414: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Electrical Start Date: 02-May-2025 End Date: 15-May-2025
Note on PD414: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Electrical Start Date: 16-May-2025 End Date: 20-May-2025
Note on NS415: Activity Name: Install Drywall Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Drywall Start Date: 09-Apr-2025 End Date: 14-Apr-2025
Note on NY415: Activity Name: Finish Drywall Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Drywall Start Date: 15-Apr-2025 End Date: 16-Apr-2025
Note on OA415: Activity Name: Paint Dry-Wall Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Painting Start Date: 17-Apr-2025 End Date: 18-Apr-2025
Note on PD415: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Electrical Start Date: 16-May-2025 End Date: 29-May-2025
Note on NU416: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO5 Location: C5 CELL 1 Electrical Room Trade: Electrical Start Date: 11-Apr-2025 End Date: 15-Apr-2025
Note on NU420: Activity Name: Fire Protection OH R/I Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Fire Protection Start Date: 11-Apr-2025 End Date: 14-Apr-2025
Note on NY420: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Fire Protection Start Date: 15-Apr-2025 End Date: 16-Apr-2025
Note on OB420: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Mech Start Date: 18-Apr-2025 End Date: 24-Apr-2025
Note on OI420: Activity Name: Overhead R/I - Plumbing Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Plumbing Start Date: 25-Apr-2025 End Date: 01-May-2025
Note on OP420: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Framing Start Date: 02-May-2025 End Date: 02-May-2025
Note on OS420: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Framing Start Date: 05-May-2025 End Date: 08-May-2025
Note on OW420: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Electrical Start Date: 09-May-2025 End Date: 10-May-2025
Note on OZ420: Activity Name: Set Mechanical Equipments Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Mech Start Date: 12-May-2025 End Date: 15-May-2025
Note on PD420: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Electrical Start Date: 16-May-2025 End Date: 30-May-2025
Note on PS420: Activity Name: Terminate Mechanical Equipments Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Mech Start Date: 31-May-2025 End Date: 04-Jun-2025
Note on NY421: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Electrical Start Date: 15-Apr-2025 End Date: 17-Apr-2025
Note on ON421: Activity Name: Install Drywall Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Drywall Start Date: 30-Apr-2025 End Date: 01-May-2025
Note on OP421: Activity Name: Finish Drywall Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Drywall Start Date: 02-May-2025 End Date: 05-May-2025
Note on OT421: Activity Name: Paint Dry-Wall Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: Painting Start Date: 06-May-2025 End Date: 07-May-2025
Note on OV421: Activity Name: General Cleaning Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: CLAYCO Start Date: 08-May-2025 End Date: 10-May-2025
Note on PI421: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: BAS Start Date: 21-May-2025 End Date: 30-May-2025
Note on OW422: Activity Name: Install BAS Equipments Phase: Fitout COLO5 Location: C5 CELL 1 Mechanical Gallery Trade: BAS Start Date: 09-May-2025 End Date: 20-May-2025
Note on PX426: Activity Name: Punchlist Phase: Fitout COLO5 Location: C5 CELL 1 Punchlist Trade: CLAYCO Start Date: 05-Jun-2025 End Date: 17-Jun-2025
Note on NR427: Activity Name: Layout Framing Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Framing Start Date: 08-Apr-2025 End Date: 08-Apr-2025
Note on NS427: Activity Name: Framing Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Framing Start Date: 09-Apr-2025 End Date: 11-Apr-2025
Note on NX427: Activity Name: In-Wall R/I Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Drywall Start Date: 14-Apr-2025 End Date: 16-Apr-2025
Note on OA427: Activity Name: Install Drywall Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Drywall Start Date: 17-Apr-2025 End Date: 19-Apr-2025
Note on OE427: Activity Name: Finish Drywall Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Drywall Start Date: 21-Apr-2025 End Date: 23-Apr-2025
Note on OH427: Activity Name: Paint Dry-Wall Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Painting Start Date: 24-Apr-2025 End Date: 26-Apr-2025
Note on OL427: Activity Name: Install Screen Mesh + Caulking Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Framing Start Date: 28-Apr-2025 End Date: 30-Apr-2025
Note on OO427: Activity Name: Install Secondary Steel Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Framing Start Date: 01-May-2025 End Date: 02-May-2025
Note on OS427: Activity Name: Paint Secondary Steel Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Painting Start Date: 05-May-2025 End Date: 06-May-2025
Note on OU427: Activity Name: General Cleaning Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: CLAYCO Start Date: 07-May-2025 End Date: 07-May-2025
Note on OZ427: Activity Name: Install Perimeter Cable Trays Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Electrical Start Date: 12-May-2025 End Date: 15-May-2025
Note on PD427: Activity Name: Install Device Tiles Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Framing Start Date: 16-May-2025 End Date: 17-May-2025
Note on PJ427: Activity Name: Raise HACs Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: HACs Start Date: 22-May-2025 End Date: 27-May-2025
Note on PP427: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Electrical Start Date: 28-May-2025 End Date: 30-May-2025
Note on PS427: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Electrical Start Date: 31-May-2025 End Date: 03-Jun-2025
Note on PW427: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Electrical Start Date: 04-Jun-2025 End Date: 09-Jun-2025
Note on QR427: Activity Name: Terminate PDUs Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Electrical Start Date: 25-Jun-2025 End Date: 27-Jun-2025
Note on OA428: Activity Name: Fire Protection OH R/I Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Fire Protection Start Date: 17-Apr-2025 End Date: 19-Apr-2025
Note on OE428: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Fire Protection Start Date: 21-Apr-2025 End Date: 23-Apr-2025
Note on OG428: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Framing Start Date: 23-Apr-2025 End Date: 24-Apr-2025
Note on OU428: Activity Name: Install Ceiling Grid Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Framing Start Date: 07-May-2025 End Date: 10-May-2025
Note on OZ428: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: HACs Start Date: 12-May-2025 End Date: 16-May-2025
Note on PD428: Activity Name: Set PDUs Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Electrical Start Date: 16-May-2025 End Date: 20-May-2025
Note on PP428: Activity Name: Detail HACs Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: HACs Start Date: 28-May-2025 End Date: 31-May-2025
Note on OE429: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Electrical Start Date: 21-Apr-2025 End Date: 24-Apr-2025
Note on OG429: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Mech Start Date: 23-Apr-2025 End Date: 24-Apr-2025
Note on PB429: Activity Name: Install Busways on HAC Arms Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Electrical Start Date: 14-May-2025 End Date: 19-May-2025
Note on PD430: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout COLO5 Location: C5 CELL 2 Data Hall Trade: Electrical Start Date: 16-May-2025 End Date: 21-May-2025
Note on NX435: Activity Name: Framing Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Framing Start Date: 14-Apr-2025 End Date: 15-Apr-2025
Note on NZ435: Activity Name: In-Wall R/I Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Drywall Start Date: 16-Apr-2025 End Date: 17-Apr-2025
Note on OB435: Activity Name: Fire Protection OH R/I Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Fire Protection Start Date: 18-Apr-2025 End Date: 19-Apr-2025
Note on OE435: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Fire Protection Start Date: 21-Apr-2025 End Date: 22-Apr-2025
Note on OG435: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Framing Start Date: 23-Apr-2025 End Date: 23-Apr-2025
Note on OH435: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Electrical Start Date: 24-Apr-2025 End Date: 25-Apr-2025
Note on OL435: Activity Name: General Cleaning Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: CLAYCO Start Date: 28-Apr-2025 End Date: 28-Apr-2025
Note on OM435: Activity Name: Set Electrical Equipments Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Electrical Start Date: 29-Apr-2025 End Date: 02-May-2025
Note on PR435: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Electrical Start Date: 30-May-2025 End Date: 11-Jun-2025
Note on QE435: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Electrical Start Date: 12-Jun-2025 End Date: 17-Jun-2025
Note on OB436: Activity Name: Install Drywall Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Drywall Start Date: 18-Apr-2025 End Date: 22-Apr-2025
Note on OG436: Activity Name: Finish Drywall Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Drywall Start Date: 23-Apr-2025 End Date: 24-Apr-2025
Note on OI436: Activity Name: Paint Dry-Wall Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Painting Start Date: 25-Apr-2025 End Date: 26-Apr-2025
Note on QE436: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Electrical Start Date: 12-Jun-2025 End Date: 24-Jun-2025
Note on OE437: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO5 Location: C5 CELL 2 Electrical Room Trade: Electrical Start Date: 21-Apr-2025 End Date: 23-Apr-2025
Note on OE441: Activity Name: Fire Protection OH R/I Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Fire Protection Start Date: 21-Apr-2025 End Date: 22-Apr-2025
Note on OG441: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Fire Protection Start Date: 23-Apr-2025 End Date: 24-Apr-2025
Note on OJ441: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Mech Start Date: 26-Apr-2025 End Date: 02-May-2025
Note on OS441: Activity Name: Overhead R/I - Plumbing Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Plumbing Start Date: 05-May-2025 End Date: 10-May-2025
Note on OZ441: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Framing Start Date: 12-May-2025 End Date: 12-May-2025
Note on PA441: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Framing Start Date: 13-May-2025 End Date: 16-May-2025
Note on PE441: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Electrical Start Date: 17-May-2025 End Date: 19-May-2025
Note on PH441: Activity Name: Set Mechanical Equipments Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Mech Start Date: 20-May-2025 End Date: 23-May-2025
Note on PO441: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Electrical Start Date: 27-May-2025 End Date: 07-Jun-2025
Note on QB441: Activity Name: Terminate Mechanical Equipments Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Mech Start Date: 09-Jun-2025 End Date: 12-Jun-2025
Note on OG442: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Electrical Start Date: 23-Apr-2025 End Date: 25-Apr-2025
Note on OW442: Activity Name: Install Drywall Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Drywall Start Date: 09-May-2025 End Date: 10-May-2025
Note on OZ442: Activity Name: Finish Drywall Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Drywall Start Date: 12-May-2025 End Date: 13-May-2025
Note on PB442: Activity Name: Paint Dry-Wall Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: Painting Start Date: 14-May-2025 End Date: 15-May-2025
Note on PD442: Activity Name: General Cleaning Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: CLAYCO Start Date: 16-May-2025 End Date: 19-May-2025
Note on PR442: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: BAS Start Date: 30-May-2025 End Date: 07-Jun-2025
Note on PE443: Activity Name: Install BAS Equipments Phase: Fitout COLO5 Location: C5 CELL 2 Mechanical Gallery Trade: BAS Start Date: 17-May-2025 End Date: 29-May-2025
Note on QU447: Activity Name: Punchlist Phase: Fitout COLO5 Location: C5 CELL 2 Punchlist Trade: CLAYCO Start Date: 28-Jun-2025 End Date: 11-Jul-2025
Note on OO448: Activity Name: Layout Framing Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Framing Start Date: 01-May-2025 End Date: 01-May-2025
Note on OP448: Activity Name: Framing Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Framing Start Date: 02-May-2025 End Date: 06-May-2025
Note on OU448: Activity Name: In-Wall R/I Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Drywall Start Date: 07-May-2025 End Date: 09-May-2025
Note on OX448: Activity Name: Install Drywall Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Drywall Start Date: 10-May-2025 End Date: 13-May-2025
Note on PB448: Activity Name: Finish Drywall Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Drywall Start Date: 14-May-2025 End Date: 16-May-2025
Note on PE448: Activity Name: Paint Dry-Wall Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Painting Start Date: 17-May-2025 End Date: 20-May-2025
Note on PI448: Activity Name: Install Screen Mesh + Caulking Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Framing Start Date: 21-May-2025 End Date: 23-May-2025
Note on PO448: Activity Name: Install Secondary Steel Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Framing Start Date: 27-May-2025 End Date: 27-May-2025
Note on PP448: Activity Name: Paint Secondary Steel Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Painting Start Date: 28-May-2025 End Date: 29-May-2025
Note on PR448: Activity Name: General Cleaning Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: CLAYCO Start Date: 30-May-2025 End Date: 30-May-2025
Note on PW448: Activity Name: Install Perimeter Cable Trays Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Electrical Start Date: 04-Jun-2025 End Date: 07-Jun-2025
Note on QB448: Activity Name: Install Device Tiles Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Framing Start Date: 09-Jun-2025 End Date: 10-Jun-2025
Note on QI448: Activity Name: Raise HACs Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: HACs Start Date: 16-Jun-2025 End Date: 19-Jun-2025
Note on QM448: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Electrical Start Date: 20-Jun-2025 End Date: 23-Jun-2025
Note on QQ448: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Electrical Start Date: 24-Jun-2025 End Date: 26-Jun-2025
Note on QT448: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Electrical Start Date: 27-Jun-2025 End Date: 02-Jul-2025
Note on SH448: Activity Name: Terminate PDUs Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Electrical Start Date: 06-Aug-2025 End Date: 08-Aug-2025
Note on OX449: Activity Name: Fire Protection OH R/I Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Fire Protection Start Date: 10-May-2025 End Date: 13-May-2025
Note on PB449: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Fire Protection Start Date: 14-May-2025 End Date: 16-May-2025
Note on PD449: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Framing Start Date: 16-May-2025 End Date: 17-May-2025
Note on PR449: Activity Name: Install Ceiling Grid Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Framing Start Date: 30-May-2025 End Date: 03-Jun-2025
Note on PW449: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: HACs Start Date: 04-Jun-2025 End Date: 09-Jun-2025
Note on QB449: Activity Name: Set PDUs Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Electrical Start Date: 09-Jun-2025 End Date: 12-Jun-2025
Note on QM449: Activity Name: Detail HACs Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: HACs Start Date: 20-Jun-2025 End Date: 24-Jun-2025
Note on PB450: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Electrical Start Date: 14-May-2025 End Date: 17-May-2025
Note on PD450: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Mech Start Date: 16-May-2025 End Date: 17-May-2025
Note on PY450: Activity Name: Install Busways on HAC Arms Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Electrical Start Date: 06-Jun-2025 End Date: 11-Jun-2025
Note on QB451: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout COLO5 Location: C5 CELL 3 Data Hall Trade: Electrical Start Date: 09-Jun-2025 End Date: 13-Jun-2025
Note on OU456: Activity Name: Framing Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Framing Start Date: 07-May-2025 End Date: 08-May-2025
Note on OW456: Activity Name: In-Wall R/I Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Drywall Start Date: 09-May-2025 End Date: 10-May-2025
Note on OZ456: Activity Name: Fire Protection OH R/I Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Fire Protection Start Date: 12-May-2025 End Date: 13-May-2025
Note on PB456: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Fire Protection Start Date: 14-May-2025 End Date: 15-May-2025
Note on PD456: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Framing Start Date: 16-May-2025 End Date: 16-May-2025
Note on PE456: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Electrical Start Date: 17-May-2025 End Date: 19-May-2025
Note on PI456: Activity Name: General Cleaning Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: CLAYCO Start Date: 21-May-2025 End Date: 21-May-2025
Note on PJ456: Activity Name: Set Electrical Equipments Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Electrical Start Date: 22-May-2025 End Date: 27-May-2025
Note on RH456: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Electrical Start Date: 11-Jul-2025 End Date: 23-Jul-2025
Note on RU456: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Electrical Start Date: 24-Jul-2025 End Date: 29-Jul-2025
Note on OZ457: Activity Name: Install Drywall Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Drywall Start Date: 12-May-2025 End Date: 15-May-2025
Note on PD457: Activity Name: Finish Drywall Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Drywall Start Date: 16-May-2025 End Date: 17-May-2025
Note on PG457: Activity Name: Paint Dry-Wall Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Painting Start Date: 19-May-2025 End Date: 20-May-2025
Note on RU457: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Electrical Start Date: 24-Jul-2025 End Date: 05-Aug-2025
Note on PB458: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO5 Location: C5 CELL 3 Electrical Room Trade: Electrical Start Date: 14-May-2025 End Date: 16-May-2025
Note on PB462: Activity Name: Fire Protection OH R/I Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Fire Protection Start Date: 14-May-2025 End Date: 15-May-2025
Note on PD462: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Fire Protection Start Date: 16-May-2025 End Date: 17-May-2025
Note on PH462: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Mech Start Date: 20-May-2025 End Date: 27-May-2025
Note on PP462: Activity Name: Overhead R/I - Plumbing Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Plumbing Start Date: 28-May-2025 End Date: 03-Jun-2025
Note on PW462: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Framing Start Date: 04-Jun-2025 End Date: 04-Jun-2025
Note on PX462: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Framing Start Date: 05-Jun-2025 End Date: 09-Jun-2025
Note on QC462: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Electrical Start Date: 10-Jun-2025 End Date: 11-Jun-2025
Note on QE462: Activity Name: Set Mechanical Equipments Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Mech Start Date: 12-Jun-2025 End Date: 17-Jun-2025
Note on QK462: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Electrical Start Date: 18-Jun-2025 End Date: 01-Jul-2025
Note on QY462: Activity Name: Terminate Mechanical Equipments Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Mech Start Date: 02-Jul-2025 End Date: 08-Jul-2025
Note on PD463: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Electrical Start Date: 16-May-2025 End Date: 19-May-2025
Note on PU463: Activity Name: Install Drywall Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Drywall Start Date: 02-Jun-2025 End Date: 03-Jun-2025
Note on PW463: Activity Name: Finish Drywall Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Drywall Start Date: 04-Jun-2025 End Date: 05-Jun-2025
Note on PY463: Activity Name: Paint Dry-Wall Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: Painting Start Date: 06-Jun-2025 End Date: 07-Jun-2025
Note on QB463: Activity Name: General Cleaning Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: CLAYCO Start Date: 09-Jun-2025 End Date: 11-Jun-2025
Note on QP463: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: BAS Start Date: 23-Jun-2025 End Date: 01-Jul-2025
Note on QC464: Activity Name: Install BAS Equipments Phase: Fitout COLO5 Location: C5 CELL 3 Mechanical Gallery Trade: BAS Start Date: 10-Jun-2025 End Date: 21-Jun-2025
Note on SK468: Activity Name: Punchlist Phase: Fitout COLO5 Location: C5 CELL 3 Punchlist Trade: CLAYCO Start Date: 09-Aug-2025 End Date: 21-Aug-2025
Note on OC469: Activity Name: Layout Framing Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Framing Start Date: 19-Apr-2025 End Date: 19-Apr-2025
Note on OE469: Activity Name: Framing Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Framing Start Date: 21-Apr-2025 End Date: 23-Apr-2025
Note on OH469: Activity Name: In-Wall R/I Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Drywall Start Date: 24-Apr-2025 End Date: 26-Apr-2025
Note on OL469: Activity Name: Install Drywall Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Drywall Start Date: 28-Apr-2025 End Date: 30-Apr-2025
Note on OO469: Activity Name: Finish Drywall Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Drywall Start Date: 01-May-2025 End Date: 05-May-2025
Note on OT469: Activity Name: Paint Dry-Wall Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Painting Start Date: 06-May-2025 End Date: 08-May-2025
Note on OW469: Activity Name: Install Screen Mesh + Caulking Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Framing Start Date: 09-May-2025 End Date: 12-May-2025
Note on PA469: Activity Name: Install Secondary Steel Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Framing Start Date: 13-May-2025 End Date: 14-May-2025
Note on PC469: Activity Name: Paint Secondary Steel Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Painting Start Date: 15-May-2025 End Date: 16-May-2025
Note on PE469: Activity Name: General Cleaning Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: CLAYCO Start Date: 17-May-2025 End Date: 17-May-2025
Note on PJ469: Activity Name: Install Perimeter Cable Trays Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Electrical Start Date: 22-May-2025 End Date: 27-May-2025
Note on PP469: Activity Name: Install Device Tiles Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Framing Start Date: 28-May-2025 End Date: 29-May-2025
Note on PV469: Activity Name: Raise HACs Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: HACs Start Date: 03-Jun-2025 End Date: 06-Jun-2025
Note on PZ469: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Electrical Start Date: 07-Jun-2025 End Date: 10-Jun-2025
Note on QD469: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Electrical Start Date: 11-Jun-2025 End Date: 13-Jun-2025
Note on QI469: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Electrical Start Date: 16-Jun-2025 End Date: 20-Jun-2025
Note on RH469: Activity Name: Terminate PDUs Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Electrical Start Date: 11-Jul-2025 End Date: 14-Jul-2025
Note on OL470: Activity Name: Fire Protection OH R/I Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Fire Protection Start Date: 28-Apr-2025 End Date: 30-Apr-2025
Note on OO470: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Fire Protection Start Date: 01-May-2025 End Date: 05-May-2025
Note on OS470: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Framing Start Date: 05-May-2025 End Date: 06-May-2025
Note on PE470: Activity Name: Install Ceiling Grid Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Framing Start Date: 17-May-2025 End Date: 21-May-2025
Note on PJ470: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: HACs Start Date: 22-May-2025 End Date: 28-May-2025
Note on PP470: Activity Name: Set PDUs Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Electrical Start Date: 28-May-2025 End Date: 31-May-2025
Note on PZ470: Activity Name: Detail HACs Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: HACs Start Date: 07-Jun-2025 End Date: 11-Jun-2025
Note on OO471: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Electrical Start Date: 01-May-2025 End Date: 06-May-2025
Note on OS471: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Mech Start Date: 05-May-2025 End Date: 06-May-2025
Note on PO471: Activity Name: Install Busways on HAC Arms Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Electrical Start Date: 27-May-2025 End Date: 30-May-2025
Note on PP472: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout COLO5 Location: C5 CELL 4 Data Hall Trade: Electrical Start Date: 28-May-2025 End Date: 02-Jun-2025
Note on OH477: Activity Name: Framing Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Framing Start Date: 24-Apr-2025 End Date: 25-Apr-2025
Note on OJ477: Activity Name: In-Wall R/I Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Drywall Start Date: 26-Apr-2025 End Date: 28-Apr-2025
Note on OM477: Activity Name: Fire Protection OH R/I Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Fire Protection Start Date: 29-Apr-2025 End Date: 30-Apr-2025
Note on OO477: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Fire Protection Start Date: 01-May-2025 End Date: 02-May-2025
Note on OS477: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Framing Start Date: 05-May-2025 End Date: 05-May-2025
Note on OT477: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Electrical Start Date: 06-May-2025 End Date: 07-May-2025
Note on OW477: Activity Name: General Cleaning Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: CLAYCO Start Date: 09-May-2025 End Date: 09-May-2025
Note on OX477: Activity Name: Set Electrical Equipments Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Electrical Start Date: 10-May-2025 End Date: 14-May-2025
Note on QE477: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Electrical Start Date: 12-Jun-2025 End Date: 25-Jun-2025
Note on QS477: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Electrical Start Date: 26-Jun-2025 End Date: 30-Jun-2025
Note on OM478: Activity Name: Install Drywall Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Drywall Start Date: 29-Apr-2025 End Date: 02-May-2025
Note on OS478: Activity Name: Finish Drywall Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Drywall Start Date: 05-May-2025 End Date: 06-May-2025
Note on OU478: Activity Name: Paint Dry-Wall Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Painting Start Date: 07-May-2025 End Date: 08-May-2025
Note on QS478: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Electrical Start Date: 26-Jun-2025 End Date: 10-Jul-2025
Note on OO479: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO5 Location: C5 CELL 4 Electrical Room Trade: Electrical Start Date: 01-May-2025 End Date: 05-May-2025
Note on OO483: Activity Name: Fire Protection OH R/I Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Fire Protection Start Date: 01-May-2025 End Date: 02-May-2025
Note on OS483: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Fire Protection Start Date: 05-May-2025 End Date: 06-May-2025
Note on OV483: Activity Name: Overhead R/I - Mechanical Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Mech Start Date: 08-May-2025 End Date: 14-May-2025
Note on PC483: Activity Name: Overhead R/I - Plumbing Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Plumbing Start Date: 15-May-2025 End Date: 21-May-2025
Note on PJ483: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Framing Start Date: 22-May-2025 End Date: 22-May-2025
Note on PK483: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Framing Start Date: 23-May-2025 End Date: 28-May-2025
Note on PQ483: Activity Name: Install Cable Trays / Pathways Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Electrical Start Date: 29-May-2025 End Date: 30-May-2025
Note on PS483: Activity Name: Set Mechanical Equipments Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Mech Start Date: 31-May-2025 End Date: 04-Jun-2025
Note on PX483: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Electrical Start Date: 05-Jun-2025 End Date: 19-Jun-2025
Note on QM483: Activity Name: Terminate Mechanical Equipments Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Mech Start Date: 20-Jun-2025 End Date: 24-Jun-2025
Note on OS484: Activity Name: Overhead R/I - Electrical Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Electrical Start Date: 05-May-2025 End Date: 07-May-2025
Note on PH484: Activity Name: Install Drywall Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Drywall Start Date: 20-May-2025 End Date: 21-May-2025
Note on PJ484: Activity Name: Finish Drywall Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Drywall Start Date: 22-May-2025 End Date: 23-May-2025
Note on PO484: Activity Name: Paint Dry-Wall Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: Painting Start Date: 27-May-2025 End Date: 27-May-2025
Note on PP484: Activity Name: General Cleaning Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: CLAYCO Start Date: 28-May-2025 End Date: 30-May-2025
Note on QC484: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: BAS Start Date: 10-Jun-2025 End Date: 19-Jun-2025
Note on PQ485: Activity Name: Install BAS Equipments Phase: Fitout COLO5 Location: C5 CELL 4 Mechanical Gallery Trade: BAS Start Date: 29-May-2025 End Date: 09-Jun-2025
Note on RL489: Activity Name: Punchlist Phase: Fitout COLO5 Location: C5 CELL 4 Punchlist Trade: CLAYCO Start Date: 15-Jul-2025 End Date: 25-Jul-2025
Note on KO490: Activity Name: Build Equipment Pads for XFMs Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 17-Jan-2025 End Date: 28-Jan-2025
Note on LA490: Activity Name: Build Equipment Pads for UPMs Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 29-Jan-2025 End Date: 07-Feb-2025
Note on LM490: Activity Name: Build Equipment Pads for UMSs Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 10-Feb-2025 End Date: 19-Feb-2025
Note on LW490: Activity Name: Build Equipment Pads for Generators Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 20-Feb-2025 End Date: 03-Mar-2025
Note on MI490: Activity Name: Install Generators Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 04-Mar-2025 End Date: 15-Mar-2025
Note on MI491: Activity Name: Install UMSs Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 04-Mar-2025 End Date: 15-Mar-2025
Note on MI492: Activity Name: Install UPMs Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 04-Mar-2025 End Date: 15-Mar-2025
Note on MI493: Activity Name: Install XFMs Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 04-Mar-2025 End Date: 15-Mar-2025
Note on OI497: Activity Name: MV Cable Pulling & Terminating Phase: Electrical Yard Location: Admin/ COLO 3 CELL 1 Trade: Electrical Start Date: 25-Apr-2025 End Date: 05-May-2025
Note on OT498: Activity Name: MV Cable Pulling & Terminating Phase: Electrical Yard Location: Admin/ COLO 3 CELL 2 Trade: Electrical Start Date: 06-May-2025 End Date: 14-May-2025
Note on PO499: Activity Name: MV Cable Pulling & Terminating Phase: Electrical Yard Location: Admin/ COLO 3 CELL 3 Trade: Electrical Start Date: 27-May-2025 End Date: 03-Jun-2025
Note on PC500: Activity Name: MV Cable Pulling & Terminating Phase: Electrical Yard Location: Admin/ COLO 3 CELL 4 Trade: Electrical Start Date: 15-May-2025 End Date: 23-May-2025
Note on LX501: Activity Name: Build Equipment Pads for XFMs Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 21-Feb-2025 End Date: 04-Mar-2025
Note on MJ501: Activity Name: Build Equipment Pads for UPMs Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 05-Mar-2025 End Date: 14-Mar-2025
Note on MT501: Activity Name: Build Equipment Pads for UMSs Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 15-Mar-2025 End Date: 26-Mar-2025
Note on NF501: Activity Name: Build Equipment Pads for Generators Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 27-Mar-2025 End Date: 05-Apr-2025
Note on NU501: Activity Name: Install Generators Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 11-Apr-2025 End Date: 24-Apr-2025
Note on NL502: Activity Name: Install UMSs Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 02-Apr-2025 End Date: 15-Apr-2025
Note on NL503: Activity Name: Install UPMs Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 02-Apr-2025 End Date: 15-Apr-2025
Note on NL504: Activity Name: Install XFMs Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 02-Apr-2025 End Date: 15-Apr-2025
Note on PO508: Activity Name: MV Cable Pulling & Terminating Phase: Electrical Yard Location: COLO 4 CELL 3 Trade: Electrical Start Date: 27-May-2025 End Date: 04-Jun-2025
Note on PC509: Activity Name: MV Cable Pulling & Terminating Phase: Electrical Yard Location: COLO 4 CELL 4 Trade: Electrical Start Date: 15-May-2025 End Date: 23-May-2025
Note on OI510: Activity Name: MV Cable Pulling & Terminating Phase: Electrical Yard Location: COLO 4 CELL1 Trade: Electrical Start Date: 25-Apr-2025 End Date: 05-May-2025
Note on OT511: Activity Name: MV Cable Pulling & Terminating Phase: Electrical Yard Location: COLO 4 CELL2 Trade: Electrical Start Date: 06-May-2025 End Date: 14-May-2025
Note on NG512: Activity Name: Build Equipment Pads for XFMs Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 28-Mar-2025 End Date: 07-Apr-2025
Note on NR512: Activity Name: Build Equipment Pads for UPMs Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 08-Apr-2025 End Date: 18-Apr-2025
Note on OC512: Activity Name: Build Equipment Pads for UMSs Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 19-Apr-2025 End Date: 29-Apr-2025
Note on ON512: Activity Name: Build Equipment Pads for Generators Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 30-Apr-2025 End Date: 10-May-2025
Note on OZ512: Activity Name: Install XFMs Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 12-May-2025 End Date: 23-May-2025
Note on PB513: Activity Name: Install UPMs Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 14-May-2025 End Date: 27-May-2025
Note on PD514: Activity Name: Install UMSs Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 16-May-2025 End Date: 29-May-2025
Note on PG515: Activity Name: Install Generators Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 19-May-2025 End Date: 31-May-2025
Note on PR519: Activity Name: Terminate MV Gear Phase: Electrical Yard Location: COLO 5 CELL 1 Trade: Electrical Start Date: 30-May-2025 End Date: 03-Jun-2025
Note on PA520: Activity Name: MV Cable Pulling & Terminating(To Junction Box) Phase: Electrical Yard Location: COLO 5 CELL 2 Trade: Electrical Start Date: 13-May-2025 End Date: 21-May-2025
Note on PW520: Activity Name: Terminate MV Gear Phase: Electrical Yard Location: COLO 5 CELL 2 Trade: Electrical Start Date: 04-Jun-2025 End Date: 07-Jun-2025
Note on PU522: Activity Name: MV Cable Pulling & Terminating(To Junction Box) Phase: Electrical Yard Location: COLO 5 CELL 3 Trade: Electrical Start Date: 02-Jun-2025 End Date: 10-Jun-2025
Note on QF522: Activity Name: Terminate MV Gear Phase: Electrical Yard Location: COLO 5 CELL 3 Trade: Electrical Start Date: 13-Jun-2025 End Date: 18-Jun-2025
Note on PJ524: Activity Name: MV Cable Pulling & Terminating(To Junction Box) Phase: Electrical Yard Location: COLO 5 CELL 4 Trade: Electrical Start Date: 22-May-2025 End Date: 31-May-2025
Note on QB524: Activity Name: Terminate MV Gear Phase: Electrical Yard Location: COLO 5 CELL 4 Trade: Electrical Start Date: 09-Jun-2025 End Date: 12-Jun-2025
Note on OP526: Activity Name: MV Cable Pulling & Terminating(To Junction Box) Phase: Electrical Yard Location: COLO 5 CELL1 Trade: Electrical Start Date: 02-May-2025 End Date: 12-May-2025
Note on QL527: Activity Name: Install Metering Cabinet [Prior to Energization] Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) Trade: Electrical Start Date: 19-Jun-2025 End Date: 24-Jun-2025
Note on PW528: Activity Name: Control Power Checks Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 04-Jun-2025 End Date: 12-Jun-2025
Note on QF528: Activity Name: EPMS Point to Point Checks Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 13-Jun-2025 End Date: 23-Jun-2025
Note on QR528: Activity Name: FTE Energizations [480v] Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 25-Jun-2025 End Date: 28-Jun-2025
Note on QW528: Activity Name: Startups Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 30-Jun-2025 End Date: 15-Jul-2025
Note on RM528: Activity Name: Loadbanking Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 16-Jul-2025 End Date: 19-Jul-2025
Note on QB532: Activity Name: Control Power Checks Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 09-Jun-2025 End Date: 18-Jun-2025
Note on QL532: Activity Name: EPMS Point to Point Checks Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 19-Jun-2025 End Date: 27-Jun-2025
Note on QU532: Activity Name: FTE Energizations [480v] Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 28-Jun-2025 End Date: 02-Jul-2025
Note on QZ532: Activity Name: Startups Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 03-Jul-2025 End Date: 18-Jul-2025
Note on RR532: Activity Name: Loadbanking Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 21-Jul-2025 End Date: 24-Jul-2025
Note on QQ536: Activity Name: Control Power Checks Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 24-Jun-2025 End Date: 07-Jul-2025
Note on RE536: Activity Name: EPMS Point to Point Checks Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 08-Jul-2025 End Date: 18-Jul-2025
Note on RP536: Activity Name: FTE Energizations [480v] Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 19-Jul-2025 End Date: 24-Jul-2025
Note on RV536: Activity Name: Startups Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 25-Jul-2025 End Date: 08-Aug-2025
Note on SK536: Activity Name: Loadbanking Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 09-Aug-2025 End Date: 14-Aug-2025
Note on QF540: Activity Name: Control Power Checks Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 13-Jun-2025 End Date: 23-Jun-2025
Note on QQ540: Activity Name: EPMS Point to Point Checks Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 24-Jun-2025 End Date: 02-Jul-2025
Note on QZ540: Activity Name: FTE Energizations [480v] Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 03-Jul-2025 End Date: 09-Jul-2025
Note on RG540: Activity Name: Startups Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 10-Jul-2025 End Date: 23-Jul-2025
Note on RV540: Activity Name: Loadbanking Phase: Commissioning (L2 - L5) COLO3 Location: C3 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 25-Jul-2025 End Date: 30-Jul-2025
Note on SQ544: Activity Name: Testing L4 <MSFT Duration> Phase: Commissioning (L2 - L5) COLO3 Location: C3 Functional Testing (Level 4) Trade: MSFT Start Date: 15-Aug-2025 End Date: 15-Sep-2025
Note on TW545: Activity Name: Testing L5 <MSFT Duration> Phase: Commissioning (L2 - L5) COLO3 Location: C3 Functional Testing (Level 5) Trade: MSFT Start Date: 16-Sep-2025 End Date: 18-Sep-2025
Note on OS546: Activity Name: Yellow Tags Phase: Commissioning (L2 - L5) COLO3 Location: C3 Yellow Tags (Level 2) CELL 1 Trade: Electrical Start Date: 05-May-2025 End Date: 28-May-2025
Note on PC547: Activity Name: Yellow Tags Phase: Commissioning (L2 - L5) COLO3 Location: C3 Yellow Tags (Level 2) CELL 2 Trade: Electrical Start Date: 15-May-2025 End Date: 07-Jun-2025
Note on QB548: Activity Name: Yellow Tags Phase: Commissioning (L2 - L5) COLO3 Location: C3 Yellow Tags (Level 2) CELL 3 Trade: Electrical Start Date: 09-Jun-2025 End Date: 02-Jul-2025
Note on PO549: Activity Name: Yellow Tags Phase: Commissioning (L2 - L5) COLO3 Location: C3 Yellow Tags (Level 2) CELL 4 Trade: Electrical Start Date: 27-May-2025 End Date: 18-Jun-2025
Note on QM550: Activity Name: Control Power Checks Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 20-Jun-2025 End Date: 28-Jun-2025
Note on QW550: Activity Name: EPMS Point to Point Checks Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 30-Jun-2025 End Date: 10-Jul-2025
Note on RH550: Activity Name: FTE Energizations [480v] Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 11-Jul-2025 End Date: 15-Jul-2025
Note on RM550: Activity Name: Startups Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 16-Jul-2025 End Date: 30-Jul-2025
Note on SB550: Activity Name: Loadbanking Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 31-Jul-2025 End Date: 04-Aug-2025
Note on QR554: Activity Name: Control Power Checks Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 25-Jun-2025 End Date: 03-Jul-2025
Note on RD554: Activity Name: EPMS Point to Point Checks Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 07-Jul-2025 End Date: 15-Jul-2025
Note on RM554: Activity Name: FTE Energizations [480v] Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 16-Jul-2025 End Date: 19-Jul-2025
Note on RR554: Activity Name: Startups Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 21-Jul-2025 End Date: 04-Aug-2025
Note on SG554: Activity Name: Loadbanking Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 05-Aug-2025 End Date: 08-Aug-2025
Note on SH558: Activity Name: Control Power Checks Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 06-Aug-2025 End Date: 14-Aug-2025
Note on SQ558: Activity Name: EPMS Point to Point Checks Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 15-Aug-2025 End Date: 25-Aug-2025
Note on TB558: Activity Name: FTE Energizations [480v] Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 26-Aug-2025 End Date: 29-Aug-2025
Note on TF558: Activity Name: Startups Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 30-Aug-2025 End Date: 15-Sep-2025
Note on TW558: Activity Name: Loadbanking Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 16-Sep-2025 End Date: 19-Sep-2025
Note on RO562: Activity Name: Control Power Checks Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 18-Jul-2025 End Date: 28-Jul-2025
Note on RZ562: Activity Name: EPMS Point to Point Checks Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 29-Jul-2025 End Date: 06-Aug-2025
Note on SI562: Activity Name: FTE Energizations [480v] Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 07-Aug-2025 End Date: 11-Aug-2025
Note on SN562: Activity Name: Startups Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 12-Aug-2025 End Date: 26-Aug-2025
Note on TC562: Activity Name: Loadbanking Phase: Commissioning (L2 - L5) COLO4 Location: C4 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 27-Aug-2025 End Date: 30-Aug-2025
Note on UA566: Activity Name: Testing <MSFT Duration> Phase: Commissioning (L2 - L5) COLO4 Location: C4 Functional Testing (Level 4) Trade: MSFT Start Date: 20-Sep-2025 End Date: 16-Oct-2025
Note on VB567: Activity Name: Testing <MSFT Duration> Phase: Commissioning (L2 - L5) COLO4 Location: C4 Functional Testing (Level 5) Trade: MSFT Start Date: 17-Oct-2025 End Date: 20-Oct-2025
Note on OT568: Activity Name: Yellow Tags Phase: Commissioning (L2 - L5) COLO4 Location: C4 Yellow Tags (Level 2) CELL 1 Trade: Electrical Start Date: 06-May-2025 End Date: 29-May-2025
Note on PS569: Activity Name: Yellow Tags Phase: Commissioning (L2 - L5) COLO4 Location: C4 Yellow Tags (Level 2) CELL 2 Trade: Electrical Start Date: 31-May-2025 End Date: 24-Jun-2025
Note on RS570: Activity Name: Yellow Tags Phase: Commissioning (L2 - L5) COLO4 Location: C4 Yellow Tags (Level 2) CELL 3 Trade: Electrical Start Date: 22-Jul-2025 End Date: 14-Aug-2025
Note on QT571: Activity Name: Yellow Tags Phase: Commissioning (L2 - L5) COLO4 Location: C4 Yellow Tags (Level 2) CELL 4 Trade: Electrical Start Date: 27-Jun-2025 End Date: 22-Jul-2025
Note on RP572: Activity Name: Control Power Checks Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 19-Jul-2025 End Date: 29-Jul-2025
Note on SA572: Activity Name: EPMS Point to Point Checks Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 30-Jul-2025 End Date: 07-Aug-2025
Note on SJ572: Activity Name: FTE Energizations [480v] Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 08-Aug-2025 End Date: 12-Aug-2025
Note on SO572: Activity Name: Startups Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 13-Aug-2025 End Date: 27-Aug-2025
Note on TD572: Activity Name: Loadbanking Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 1 Trade: Electrical Start Date: 28-Aug-2025 End Date: 02-Sep-2025
Note on RU576: Activity Name: Control Power Checks Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 24-Jul-2025 End Date: 02-Aug-2025
Note on SF576: Activity Name: EPMS Point to Point Checks Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 04-Aug-2025 End Date: 12-Aug-2025
Note on SO576: Activity Name: FTE Energizations [480v] Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 13-Aug-2025 End Date: 18-Aug-2025
Note on SU576: Activity Name: Startups Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 19-Aug-2025 End Date: 02-Sep-2025
Note on TJ576: Activity Name: Loadbanking Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 2 Trade: Electrical Start Date: 03-Sep-2025 End Date: 08-Sep-2025
Note on TA580: Activity Name: Control Power Checks Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 25-Aug-2025 End Date: 03-Sep-2025
Note on TK580: Activity Name: EPMS Point to Point Checks Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 04-Sep-2025 End Date: 13-Sep-2025
Note on TV580: Activity Name: FTE Energizations [480v] Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 15-Sep-2025 End Date: 19-Sep-2025
Note on UA580: Activity Name: Startups Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 20-Sep-2025 End Date: 04-Oct-2025
Note on UQ580: Activity Name: Loadbanking Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 3 Trade: Electrical Start Date: 06-Oct-2025 End Date: 11-Oct-2025
Note on SF584: Activity Name: Control Power Checks Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 04-Aug-2025 End Date: 12-Aug-2025
Note on SO584: Activity Name: EPMS Point to Point Checks Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 13-Aug-2025 End Date: 22-Aug-2025
Note on SY584: Activity Name: FTE Energizations [480v] Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 23-Aug-2025 End Date: 27-Aug-2025
Note on TD584: Activity Name: Startups Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 28-Aug-2025 End Date: 12-Sep-2025
Note on TT584: Activity Name: Loadbanking Phase: Commissioning (L2 - L5) COLO5 Location: C5 Energizations & Startups (Level 3) CELL 4 Trade: Electrical Start Date: 13-Sep-2025 End Date: 17-Sep-2025
Note on VB588: Activity Name: Testing <MSFT Duration> Phase: Commissioning (L2 - L5) COLO5 Location: C5 Functional Testing (Level 4) Trade: MSFT Start Date: 17-Oct-2025 End Date: 15-Nov-2025
Note on WG589: Activity Name: Testing <MSFT Duration> Phase: Commissioning (L2 - L5) COLO5 Location: C5 Functional Testing (Level 5) Trade: MSFT Start Date: 17-Nov-2025 End Date: 19-Nov-2025
Note on PX590: Activity Name: Yellow Tags Phase: Commissioning (L2 - L5) COLO5 Location: C5 Yellow Tags (Level 2) CELL 1 Trade: Electrical Start Date: 05-Jun-2025 End Date: 28-Jun-2025
Note on QU591: Activity Name: Yellow Tags Phase: Commissioning (L2 - L5) COLO5 Location: C5 Yellow Tags (Level 2) CELL 2 Trade: Electrical Start Date: 28-Jun-2025 End Date: 23-Jul-2025
Note on SK592: Activity Name: Yellow Tags Phase: Commissioning (L2 - L5) COLO5 Location: C5 Yellow Tags (Level 2) CELL 3 Trade: Electrical Start Date: 09-Aug-2025 End Date: 03-Sep-2025
Note on RL593: Activity Name: Yellow Tags Phase: Commissioning (L2 - L5) COLO5 Location: C5 Yellow Tags (Level 2) CELL 4 Trade: Electrical Start Date: 15-Jul-2025 End Date: 07-Aug-2025

## CFA - Legends
Commissioning (L2 - L5) COLO3 |  | Commissioning (L2 - L5) COLO4 |  | Commissioning (L2 - L5) COLO5 |  | Core & Shell |  | Electrical Yard |  | Fitout Admin Area |  | Fitout COLO3 |  | Fitout COLO4 |  | Fitout COLO5 |  | Foundations |  | Preconstruction |  | Procurement |  | Procurement MSFT OFCI ROJ CFCI (Critical Only) |  | Procurement MSFT OFCI ROJ COLO3 |  | Procurement MSFT OFCI ROJ COLO4 |  | Procurement MSFT OFCI ROJ COLO5 |  | Site Prep/ Mobilization |  | Site Utilities
[24 empty] | 116 | MV Metering Cabinet - *Not Used* [65 Weeks] - Not Tied | 1 | Auto Transfer Control Panel (TCP) Delivered | 1 | Auto Transfer Control Panel (TCP) Delivered | 1 | Auto Transfer Control Panel (TCP) Delivered |  |  | U1 | Backfill after UG work (MV / Telecom)
Electrical |  | Electrical |  | Electrical |  | Buffer |  | Electrical |  | CLAYCO |  | BAS |  | BAS |  | BAS |  | Foundations |  | BIM |  | Procure |  | 117 | MV Metering Cabinet - Substitute [43 Weeks] | 100 | Receive PEMB Procurement (1st Del) (Nucor) (SOW Del Date-10/3/24) | 10 | Busway / Busplugs (BSW) (Starline Holding) Delivered | 10 | Busway / Busplugs (BSW) (Starline Holding) Delivered | CLAYCO
E15 | Startups | E15 | Startups | E15 | Startups | BW | Weather Days | E23 | Build Equipment Pads for XFMs | C1 | Fit-out | BA | Install BAS Equipments | BA | Install BAS Equipments | BA | Install BAS Equipments | F1 | Foundations / Stem Walls |  | BIM Kickoff | 14 | Buyouts & Early Procurement | 20 | Cable Bus Fabrication/ Lead Time | 101 | Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 4/30/24) | 105 | Receive Utility Pad Mount Switchgear (UPM) (Del Date 8/30/2024) | 102 | Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 9/30/24) | CM | Site Mobilization | Electrical
E16 | Loadbanking | E16 | Loadbanking | E16 | Loadbanking |  |  | E24 | Build Equipment Pads for UPMs | CP | PunchList | BA1 | Pull & Terminate BAS Equipments | BA1 | Pull & Terminate BAS Equipments | BA1 | Pull & Terminate BAS Equipments |  |  | 0.1 | Above ground BIM Co-ordination | 19 | ARL & Subcontractor Awards | 21 | CFCI- MV Cables Fabrication/ Lead Time | 103 | Receive Utility Pad Mount Switchgear (Del Date- 7/30/2024) | 106 | Received SUB Warehouse 11/23/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 11/11/23) | 104 | Receive Utility Pad Mount Switchgear (UPM) (Del Date 10/30/2024) | CT | Set-Up Trailers & Install Temp Utilities | E16 | Permanent Power
E19 | Install Metering Cabinet [Prior to Energization] | E20 | FTE Energizations [480v] | E20 | FTE Energizations [480v] | Drywall |  | E25 | Build Equipment Pads for UMSs | CPP | Remaining Area Punchlist | [12 empty] | 31 | HACs Fabrication/ Lead Time | 112 | UPS System w/ Battery (UPS) (Eaton) Delivered | 108 | Reveive Pad Mounted Transformers (XMF) (Del Date 8/30/2024) | 107 | Received SUB Warehouse 12/28/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 12/11/23) |  |  | E17 | Install UG Electrical / UPM Crossing (under Building Pad)
E20 | FTE Energizations [480v] | E21 | EPMS Point to Point Checks | E21 | EPMS Point to Point Checks | D3 | Install Exterior Wall Panels | E26 | Build Equipment Pads for Generators |  |  | CLAYCO |  | CLAYCO |  | CLAYCO |  |  |  | Precon | [5 empty] | 113 | UPS System w/ Battery (UPS) (Eaton) Shipping/ ROJ | 109 | Reveive Power Distribution Units (PDU) (ABB) (SOW Del Date- 7/12/24) | 11 | Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ | Earthwork |  | E18 | Install MV Ductbanks
E21 | EPMS Point to Point Checks | E22 | Control Power Checks | E22 | Control Power Checks |  |  | E27 | Install XFMs | Drywall |  | CC | General Cleaning | CC | General Cleaning | CC | General Cleaning |  |  | PC1 | PSR Executed (Early Works) |  |  |  |  | 114 | Utility Pad Mount Switchgear (UPM) Delivered | 11 | Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ | 110 | Static UPS System W/Batt (UPS) (Eaton) Delivered | U2 | Fine Grading Building Pad
E22 | Control Power Checks | EE24 | Yellow Tags | EE24 | Yellow Tags | Electrical |  | E28 | Install Generators | D4 | Top Out Drywall - Ceiling Steel Height | CP | Punchlist | CP | Punchlist | CP | Punchlist |  |  | PC2 | PSR Executed (Full GMP) |  |  |  |  | 115 | Utility Pad Mount Switchgear (UPM) Shipping/ ROJ | 110 | Static UPS System W/Batt (UPS) (Eaton) Delivered | 111 | Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ |  |  | Plumbing
EE24 | Yellow Tags |  |  |  |  | E14 | UG MEP Work AMS | E29 | Install UMSs | D5 | Finish Drywall | [8 empty] | PC3 | RFP Issued (Revised 3.21.24) and Proposal Due to MSFT |  |  |  |  | 12 | Busway / Busplugs (Starline Holding) Delivered | 111 | Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ | 114 | Utility Pad Mount Switchgear (UPM) Delivered |  |  | P1 | Install Sanitary Lines
|  | MSFT |  | MSFT |  |  |  | E30 | Install UPMs | D6 | Finish Drywall and Wall Protection | Drywall |  | Drywall |  | Drywall | [9 empty] | 13 | Busway / Busplugs (Starline Holding) Shipping/ ROJ | 114 | Utility Pad Mount Switchgear (UPM) Delivered | 115 | Utility Pad Mount Switchgear (UPM) Shipping/ROJ |  |  | P2 | Install Storm Lines
MSFT |  | W1 | Testing <MSFT Duration> | W1 | Testing <MSFT Duration> | Framing |  | E35 | MV Cable Pulling & Terminating |  |  | D1 | In-Wall R/I | D1 | In-Wall R/I | D1 | In-Wall R/I | [8 empty] | 15 | Admin/C03- OFCI- Building Automation System (BAS) (ALC) Shipping/ ROJ | 115 | Utility Pad Mount Switchgear (UPM) Shipping/ROJ | 17 | Air Handling Units (AHU) (Stulz) Delivered |  |  | P3 | Install Water Line
W2 | Testing L4 <MSFT Duration> |  |  |  |  | X36 | Install Misc. Metals (Trims, Gutters, Catwalks) | E40 | MV Cable Pulling & Terminating(To Junction Box) | Electrical |  | D2 | Install Drywall | D2 | Install Drywall | D2 | Install Drywall | [8 empty] | 16 | Admin/C03- OFCI- Received SUB Warehouse 9/28/2023 UPS System w/ Battery (UPS) (Eaton) (SOW Del Date- 8/13/23) | 17 | Air Handling Units (AHU) (Stulz) Delivered | 18 | Air Handling Units (AHU) (Stulz) Shipping/ROJ
W3 | Testing L5 <MSFT Duration> |  |  |  |  | X37 | Install Primary Steel | E41 | Terminate MV Gear | EE28 | Cable Tray / Ceiling Steel Height | D5 | Finish Drywall | D5 | Finish Drywall | D5 | Finish Drywall | [8 empty] | 17 | Air Handling Units (AHU) (Stulz) Delivered | 18 | Air Handling Units (AHU) (Stulz) Shipping/ ROJ | 2 | Auto Transfer Control Panel (TCP) Shipping/ROJ |  |  | Telecom
[6 empty] | X8 | Install Roof Panels |  |  | EE29 | Pull Cables | [14 empty] | 18 | Air Handling Units (AHU) (Stulz) Shipped/ROJ | 2 | Auto Transfer Control Panel (TCP) Shipping/ROJ | 25 | Elec. Performance Monitoring Syst. (EPMS) (Schneider) Delivered |  |  | T1 | Install UG Telecom (under Building Pad)
[10 empty] | EE45 | Install Raceway | Electrical |  | Electrical |  | Electrical | [9 empty] | 2 | Auto Transfer Control Panel (TCP) Shipping/ ROJ | 23 | Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Delivered | 26 | Elec. Performance Monitoring Syst. (EPMS) (Schneider) Shipping/ROJ
[6 empty] | Mech |  |  |  | EE46 | Pull Branches | EE1 | Overhead R/I - Electrical | EE1 | Overhead R/I - Electrical | EE1 | Overhead R/I - Electrical | [8 empty] | 27 | Elec. Performance Monitoring System (EPMS) (Schneider) Delivered | 24 | Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Shipping/ROJ | 29 | HAC/Racking (Tate Access) Delivered
[6 empty] | M4 | Install Louvers & Dampers |  |  | EE49 | Pull Feeders | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | EE11 | Install Fiber Runner [ Cable Trays on HAC Arms] | [8 empty] | 28 | Elec. Performance Monitoring System (EPMS) (Schneider) Shipping/ ROJ | 29 | HAC/Racking (Tate Access) Delivered | 3 | Automatic Transfer Switches (ATS) (Schneider) Delivered
[6 empty] | S4 | Install Louvers & Dampers |  |  | EE51 | Set Electrical Equipment | EE17 | Pull Feeders from PDUs to Busways | EE17 | Pull Feeders from PDUs to Busways | EE17 | Pull Feeders from PDUs to Busways | [8 empty] | 29 | HAC/Racking (Tate Access) Delivered | 3 | Automatic Transfer Switches (ATS) (Schneider) Delivered | 30 | HAC/Racking (Tate Access) Shipping/ROJ
[10 empty] | EE52 | Set ER-1 Equipment | EE35 | Install Cable Trays / Pathways | EE35 | Install Cable Trays / Pathways | EE35 | Install Cable Trays / Pathways | [8 empty] | 3 | Automatic Transfer Switches (ATS) (Schneider) Delivered | 30 | HAC/Racking (Tate Access) Shipping/ROJ | 32 | LV Switchgear (Eaton) Delivered
[6 empty] | SOG |  |  |  | EE53 | Set ER-2 Equipment | EE39 | Install Busways on HAC Arms | EE39 | Install Busways on HAC Arms | EE39 | Install Busways on HAC Arms | [8 empty] | 30 | HAC/Racking (Tate Access) Shipping/ ROJ | 32 | LV Switchgear (Eaton) Delivered | 33 | LV Switchgear (Eaton) Shipping/ROJ
[6 empty] | F2 | Prep / Place SOG |  |  | EE54 | Set FCR Equipment | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | EE43 | Connect Perimeter Cable Trays to HAC Cable Trays | [8 empty] | 34 | LV Switchgear (LVS) (Eaton) Delivered | 33 | LV Switchgear (Eaton) Shipping/ROJ | 36 | Main LV Switch Board (MSB) Delivered
[10 empty] | EE55 | Set SER Room Equipment | EE44 | Install Perimeter Cable Trays | EE44 | Install Perimeter Cable Trays | EE44 | Install Perimeter Cable Trays | [8 empty] | 35 | LV Switchgear (LVS) (Eaton) Shipping/ ROJ | 36 | Main LV Switch Board (MSB) Delivered | 37 | Main LV Switch Board (MSB) Shipping/ROJ
[10 empty] | EE56 | Terminate Electrical / Mechanical Equipment | EE47 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | EE47 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | EE47 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | [8 empty] | 36 | Main LV Switch Board (MSB) Delivered | 37 | Main LV Switch Board (MSB) Shipping/ROJ | 38 | Mech Power Distribution Panels (ADP) Delivered
[10 empty] | EEA | Light Fixtures Installation | EE47.1 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | EE47.1 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | EE47.1 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | [8 empty] | 37 | Main LV Switch Board (MSB) Shipping/ ROJ | 38 | Mech Power Distribution Panels (ADP) Delivered | 39 | Mech Power Distribution Panels (ADP) Shipping/ROJ
[12 empty] | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | EE48 | Pull Cable to Mechanical Equipments [From Electrical Room] | [8 empty] | 4 | Automatic Transfer Switches (ATS) (Schneider) Shipping/ ROJ | 39 | Mech Power Distribution Panels (ADP) Shipping/ROJ | 4 | Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ
[10 empty] | Fire Protection |  | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | EE50 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | [8 empty] | 42 | Medium Voltage Switchgear (MVS) (JD Power Sys) Delivered | 4 | Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ | 44 | Medium Voltage Switchgear (MVS) (JDC Power Sys) Delivered
[10 empty] | R11 | Complete Pipe/ Valves | EE51 | Set Electrical Equipments | EE51 | Set Electrical Equipments | EE51 | Set Electrical Equipments | [8 empty] | 43 | Medium Voltage Switchgear (MVS) (JD Power Sys) Shipping/ ROJ | 40 | Medium Voltage Switchgear (JDC Power Sys) Delivered | 45 | Medium Voltage Switchgear (MVS) (JDC Power Sys) Shipping/ROJ
[10 empty] | R4 | Fire Protection OH R/I | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | EE57 | Terminate Electrical Equipments [Inside Electrical Room] | [8 empty] | 46 | Packaged Diesel Generator Set (CAT Holt) Delivered | 41 | Medium Voltage Switchgear (JDC Power Sys) Shipping/ROJ | 50 | Packaged Diesel Generator Set (GPC) (CAT Holt) Delivered
[12 empty] | EE58 | Terminate PDUs | EE58 | Terminate PDUs | EE58 | Terminate PDUs | [8 empty] | 47 | Packaged Diesel Generator Set (CAT Holt) Shipping/ ROJ | 48 | Packaged Diesel Generator Set (GEN) (CAT Holt) Delivered | 51 | Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ
[10 empty] | Framing |  | EE7 | Set PDUs | EE7 | Set PDUs | EE7 | Set PDUs | [8 empty] | 5 | Auxillary (Mech) Power Distribution Panels (ADP) Delivered | 49 | Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ | 54 | Pad Mounted Transformers (XMF) Delivered
[10 empty] | X16 | Secondary / Ceiling Steel | [14 empty] | 52 | Pad Mounted Transformers (XFM-TX) Delivered | 54 | Pad Mounted Transformers (XMF) Delivered | 55 | Pad Mounted Transformers (XMF) Shipping/ROJ
[10 empty] | X17 | Ceiling Grid & Tile | Fire Protection |  | Fire Protection |  | Fire Protection | [9 empty] | 53 | Pad Mounted Transformers (XFM-TX) Shipping/ ROJ | 55 | Pad Mounted Transformers (XMF) Shipping/ROJ | 58 | Power Distribution Units (PDU) (ABB) Delivered
[10 empty] | X21 | Framing | R1 | Overhead R/I - Fire Alarm | R1 | Overhead R/I - Fire Alarm | R1 | Overhead R/I - Fire Alarm | [8 empty] | 56 | PEMB Procurement (1st Del) (Nucor) Delivered | 58 | Power Distribution Units (PDU) (ABB) Delivered | 59 | Power Distribution Units (PDU) (ABB) Shipping/ROJ
[10 empty] | X34 | Install Doors | R4 | Fire Protection OH R/I | R10 | Fire Protection OH R/I | R19 | Fire Protection OH R/I | [8 empty] | 57 | PEMB Procurement (1st Del) (Nucor) Shipping/ ROJ | 59 | Power Distribution Units (PDU) (ABB) Shipping/ROJ | 64 | Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/16/24)
[10 empty] | X35 | Install downcomers | R5 | Fire Protection OH R/I | R11 | Fire Protection OH R/I | R20 | Fire Protection OH R/I | [8 empty] | 6 | Auxillary (Mech) Power Distribution Panels (ADP) Shipping/ ROJ | 65 | Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/9/24) | 66 | Receive Auto Transfer Control Panel (TCP) (Del Date 3/30/2025)
[12 empty] | R6 | Fire Protection OH R/I | R12 | Fire Protection OH R/I | R21 | Fire Protection OH R/I | [8 empty] | 60 | Power Distribution Units (PDU) Delivered | 68 | Receive Auto Transfer Control Panel (TCP) (Del Date-3/30/2025) | 7 | Building Automation System (BAS) (Automated Logic Corp) Delivered
[10 empty] | MEP |  |  |  | R13 | Fire Protection OH R/I | R22 | Fire Protection OH R/I | [8 empty] | 61 | Power Distribution Units (PDU) Shipping/ ROJ | 7 | Building Automation System (BAS) (Automated Logic Corp) Delivered | 71 | Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 8/31/24)
[10 empty] | MEP1 | MEP Rough-In & OH | Framing |  | R14 | Fire Protection OH R/I | R23 | Fire Protection OH R/I | [8 empty] | 62 | Receive Elec. Performance Monitoring System (EPMS) (Schneider) (SOW Del Date- 4/30/24) | 70 | Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 6/30/24) | 73 | Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 1/28/25)
[10 empty] | MEP2 | Rough-in | X19 | Install Screen Mesh + Caulking | R15 | Fire Protection OH R/I | R24 | Fire Protection OH R/I | [8 empty] | 63 | Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/04/24) | 74 | Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 12/29/24) | 77 | Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 4/23/24)
[12 empty] | X21 | Framing | R16 | Fire Protection OH R/I | R25 | Fire Protection OH R/I | [8 empty] | 67 | Receive Auto Transfer Control Panel (TCP) (Del Date- 3/8/2025) | 76 | Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 2/23/24) | 8 | Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ
[10 empty] | Mech |  | X26 | Install Ceiling Grid | R17 | Fire Protection OH R/I | R26 | Fire Protection OH R/I | [8 empty] | 69 | Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 4/30/24) | 79 | Receive Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) (SOW Del Date- 6/30/24) | 80 | Receive Elec. Performance Monitoring Syst. (EPMS) (Schneider) (SOW Del Date- 8/31/24)
[10 empty] | M1 | Install Duct Work | X27 | Install Ceiling Grid + Device Tiles | R18 | Fire Protection OH R/I | R27 | Fire Protection OH R/I | [8 empty] | 72 | Receive Auxillary (Mech) Power Distribution Panels (ADP) (Del Date- 3/8/2025) | 8 | Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ | 83 | Receive HAC/Racking (Tate Access) (SOW Del Date- 7/3/24)
[10 empty] | M2 | Install Ductwork (Remaining Rooms, Corridor) | X30 | Drop Cable Tray [Hanging Rods] | R7 | Fire Protection OH R/I | R28 | Fire Protection OH R/I | [8 empty] | 75 | Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 11/28/24) | 82 | Receive HAC/Racking (Tate Access) (SOW Del Date- 6/18/24) | 85 | Receive LV Switchgear (Eaton) (SOW Del Date- 3/30/25)
[10 empty] | M3 | Install Ductwork and Cracs | X35 | Install Device Tiles | R8 | Fire Protection OH R/I | R29 | Fire Protection OH R/I | [8 empty] | 78 | Receive Busway / Busplugs (Starline Holding) (Del Date- 1/25/24) | 84 | Receive LV Switchgear (Eaton) (SOW Del Date- 2/28/25) | 88 | Receive Main LV Switch Board (MSB) (Del Date 3/30/2025)
[12 empty] | X38 | Install Secondary Steel | R9 | Fire Protection OH R/I | R30 | Fire Protection OH R/I | [8 empty] | 81 | Receive HAC/Racking (Tate Access) (SOW Del Date- 5/17/24) | 87 | Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) | 91 | Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025)
[10 empty] | Painting |  | X9 | Layout Framing | [12 empty] | 86 | Receive LV Switchgear (LVS) (Eaton) (SOW Del Date- 2/28/25) | 90 | Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) | 94 | Receive Medium Voltage Switchgear (MVS) (JDC Power Sys) (SOW Del Date- 10/30/24)
[10 empty] | Y1 | Paint |  |  | Framing |  | Framing | [9 empty] | 89 | Receive Main LV Switch Board (MSB) (SOW Del Date- 3/8/2025) | 93 | Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 8/30/24) | 97 | Receive Packaged Diesel Generator Set (GPC) (CAT Holt) (SOW Del Date- 6/26/24)
[12 empty] | HACs |  | X19 | Install Screen Mesh + Caulking | X19 | Install Screen Mesh + Caulking | [8 empty] | 9 | Building Automation System (BAS) (ALC) Delivered | 96 | Receive Packaged Diesel Generator Set (GEN) (CAT Holt) (SOW Del Date- 6/4/24) | 99 | Receive Pad Mounted Transformers (XMF) (Del Date 10/30/2024)
[10 empty] | Plumbing |  | S1 | Assemble HACs [Qty - 5] | X21 | Framing | X21 | Framing | [8 empty] | 92 | Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 7/30/24)
[10 empty] | P5 | Plumbing | S2 | Raise HACs | X26 | Install Ceiling Grid | X26 | Install Ceiling Grid | [8 empty] | 95 | Receive Packaged Diesel Generator Set (CAT Holt) (SOW Del Date- 5/14/24)
[12 empty] | S4 | Detail HACs | X27 | Install Ceiling Grid + Device Tiles | X27 | Install Ceiling Grid + Device Tiles | [8 empty] | 98 | Receive Pad Mounted Transformers (XFM-TX) (Del Date- 7/30/2024)
[10 empty] | Telecom |  |  |  | X30 | Drop Cable Tray [Hanging Rods] | X30 | Drop Cable Tray [Hanging Rods]
[10 empty] | T10 | Pull Fiber/Copper For CORPNET Network | Mech |  | X35 | Install Device Tiles | X35 | Install Device Tiles
[10 empty] | T3 | Pull Copper for BAS VLAN | M5 | Overhead R/I - Mechanical | X38 | Install Secondary Steel | X38 | Install Secondary Steel
[10 empty] | T4 | Pull Copper for EPMS VLAN | M6 | Set Mechanical Equipments | X9 | Layout Framing | X9 | Layout Framing
[10 empty] | T5 | Pull Copper for Tahuya VLAN | M7 | Terminate Mechanical Equipments
[10 empty] | T6 | Pull Fiber For BAS VLAN |  |  | HACs |  | HACs
[10 empty] | T7 | Pull Fiber For CEI Network | Painting |  | S1 | Assemble HACs [Qty - 5] | S1 | Assemble HACs [Qty - 5]
[10 empty] | T8 | Pull Fiber For EPMS VLAN | Y2 | Paint Dry-Wall | S2 | Raise HACs | S2 | Raise HACs
[10 empty] | T9 | Pull Fiber For Tahuya VLAN | Y7 | Paint Secondary Steel | S4 | Detail HACs | S4 | Detail HACs
[12 empty] | Plumbing |  | Mech |  | Mech
[12 empty] | P4 | Overhead R/I - Plumbing | M5 | Overhead R/I - Mechanical | M5 | Overhead R/I - Mechanical
[14 empty] | M6 | Set Mechanical Equipments | M6 | Set Mechanical Equipments
[14 empty] | M7 | Terminate Mechanical Equipments | M7 | Terminate Mechanical Equipments
[14 empty] | Painting |  | Painting
[14 empty] | Y2 | Paint Dry-Wall | Y2 | Paint Dry-Wall
[14 empty] | Y7 | Paint Secondary Steel | Y7 | Paint Secondary Steel
[14 empty] | Plumbing |  | Plumbing
[14 empty] | P4 | Overhead R/I - Plumbing | P4 | Overhead R/I - Plumbing