## Sheet1
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML0 | Cx L5 IST Complete (White Tag) | 2025-09-18 | 2025-09-18
Commissioning | COLO 3 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-05 | 2025-05-28
Commissioning | COLO 3 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-15 | 2025-06-07
Commissioning | COLO 3 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-06-09 | 2025-07-02
Commissioning | COLO 3 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-27 | 2025-06-18
Commissioning | COLO 4 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-06 | 2025-05-29
Commissioning | COLO 4 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-31 | 2025-06-24
Commissioning | COLO 4 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-07-22 | 2025-08-14
Commissioning | COLO 4 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-06-27 | 2025-07-22
Commissioning | COLO 5 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-06-05 | 2025-06-28
Commissioning | COLO 5 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-06-28 | 2025-07-23
Commissioning | COLO 5 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-08-09 | 2025-09-03
Commissioning | COLO 5 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-07-15 | 2025-08-07
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- EPMS Point to Point Checks | 2025-06-13 | 2025-06-23
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- FTE Energizations [480v] | 2025-06-24 | 2025-06-27
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- Install Metering Cabinet [Prior to Energization] | 2025-06-12 | 2025-06-18
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- Loadbanking | 2025-07-15 | 2025-07-18
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- Startups | 2025-06-28 | 2025-07-14
Commissioning | COLO 3 | Microsoft | #196B24 | 4&5 | 4Cx- Testing <MSFT Duration> | 2025-08-15 | 2025-09-15
Commissioning | COLO 4 | Microsoft | #196B24 | 4&5 | 4Cx- Testing <MSFT Duration> | 2025-09-20 | 2025-10-16
Commissioning | COLO 5 | Microsoft | #196B24 | 4&5 | 4Cx- Testing <MSFT Duration> | 2025-10-17 | 2025-11-15
Commissioning | COLO 3 | Microsoft | #196B24 | 4&5 | 5Cx- Testing <MSFT Duration> | 2025-09-16 | 2025-09-18
Commissioning | COLO 4 | Microsoft | #196B24 | 4&5 | 5Cx- Testing <MSFT Duration> | 2025-10-17 | 2025-10-20
Commissioning | COLO 5 | Microsoft | #196B24 | 4&5 | 5Cx- Testing <MSFT Duration> | 2025-11-17 | 2025-11-19
Milestones | Milestone | Milestone | #808080 | ML1 | Admin & COLO3-5 Fitout Complete | 2025-10-01 | 2025-10-01
Fitout | COLO 3 - CELL 1 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-02-22 | 2025-02-27
Fitout | COLO 3 - CELL 2 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-03-04 | 2025-03-08
Fitout | COLO 3 - CELL 3 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-03-27 | 2025-04-01
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-03-14 | 2025-03-19
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-03-29 | 2025-04-03
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-04-07 | 2025-04-11
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-04-30 | 2025-05-06
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-04-18 | 2025-04-23
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-05-02 | 2025-05-08
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-05-12 | 2025-05-16
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-06-04 | 2025-06-09
Fitout | CELL 4 Data Hall Fitout Activities | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-05-22 | 2025-05-28
Site Utilities | Under Building Pad | Earthwork | #7E350E | EW1 | Backfill after UG work (MV / Telecom) | 2024-11-07 | 2024-11-08
Fitout | Punchlist | Punchlist | #A02B93 | PU1 | Beneficial Rooms PunchList | 2025-05-06 | 2025-05-09
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML1 | Beneficial Use | 2025-08-14 | 2025-08-14
Milestones | COLO 4 | Milestone | #000000 | ML2 | Beneficial Use | 2025-09-19 | 2025-09-19
Milestones | COLO 5 | Milestone | #000000 | ML3 | Beneficial Use | 2025-10-11 | 2025-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML4 | Beneficial Use - All Facility & Network Telecom Access/ Devices etc. | 2025-10-01 | 2025-10-01
Milestones | COLO 4 | Milestone | #000000 | ML5 | Beneficial Use - Distrbuted Antenna System (DAS) | 2025-09-19 | 2025-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML6 | Beneficial Use - Distributed Antenna System (DAS) | 2025-08-14 | 2025-08-14
Milestones | COLO 5 | Milestone | #000000 | ML7 | Beneficial Use - Distributed Antenna System (DAS) | 2025-10-11 | 2025-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML8 | Beneficial Use - Facility Cable Room (FCR) | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML9 | Beneficial Use - Meet Me Room or Entry Rooms (MMR/ER) | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML10 | Beneficial Use - Middle of Row (MOR) Cabinets | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML11 | Beneficial Use - Radio Over Internet Protocol (RoIP) | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML12 | Beneficial Use - Secure & High Value Storage Rooms | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML13 | Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets | 2025-08-14 | 2025-08-14
Milestones | COLO 4 | Milestone | #000000 | ML14 | Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets | 2025-09-19 | 2025-09-19
Milestones | COLO 5 | Milestone | #000000 | ML15 | Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets | 2025-10-11 | 2025-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML16 | Beneficial Use - Security Equipment Room (SER) | 2025-08-14 | 2025-08-14
Milestones | COLO 5 | Milestone | #000000 | ML17 | Beneficial Use - Security Low Voltage (SLV) System | 2025-10-11 | 2025-10-11
Milestones | COLO 4 | Milestone | #000000 | ML18 | Beneficial Use - Security Low Voltage (SLV) Systems | 2025-09-19 | 2025-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML19 | Beneficial Use (IDF#1,#2,#3 & #4) | 2025-08-14 | 2025-08-14
Milestones | COLO 5 | Milestone | #000000 | ML20 | Beneficial Use (IDF#1,#2,#3 & #4) | 2025-10-11 | 2025-10-11
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use Facility Cable Room (FCR) | 2025-10-11 | 2025-10-11
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use Meet Me Room or Entry Rooms (MMR/ER) | 2025-10-11 | 2025-10-11
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE29 | Beneficial Use Rooms | 2025-01-20 | 2025-05-09
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use Secure & High Value Storage Rooms | 2025-10-11 | 2025-10-11
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- (IDF#1,#2,#3 & #4) | 2025-09-19 | 2025-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Beneficial Use- Facilities Operations Center (FOC) | 2025-08-14 | 2025-08-14
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Facilities Operations Center (FOC) | 2025-09-19 | 2025-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Facility Cable Room (FCR) | 2025-09-19 | 2025-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Meet Me Room or Entry Rooms (MMR/ER) | 2025-09-19 | 2025-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Middle of Row (MOR) Cabinets | 2025-09-19 | 2025-09-19
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use- Middle of Row (MOR) Cabinets | 2025-10-11 | 2025-10-11
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Radio OVer Internet Protocol (RoIP) | 2025-09-19 | 2025-09-19
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use- Radio Over Internet Protocol (RoIP) | 2025-10-11 | 2025-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Beneficial Use- Regional Network Gateway (RNG) | 2025-08-14 | 2025-08-14
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Secure & High Value Storage Rooms | 2025-09-19 | 2025-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Beneficial Use- Security Low Voltage (SLV) System | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Beneficial Use- Security Operations Center (SOC) | 2025-08-14 | 2025-08-14
BIM | BIM | BIM | #DAE9F8 | BIM | BIM- Above ground BIM Co-ordination | 2024-09-06 | 2024-10-12
BIM | BIM | BIM | #DAE9F8 | BIM | BIM- BIM Kickoff | 2024-07-18 | 2024-07-18
BIM | BIM | BIM | #DAE9F8 | BIM | BIM- UG BIM Co-ordination | 2024-07-19 | 2024-08-17
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | EE30 | Build Equipment Pads for Generators | 2025-02-20 | 2025-03-03
Electrical Yard | COLO 4 | Electrical | #F2F09E | EE30 | Build Equipment Pads for Generators | 2025-03-27 | 2025-04-05
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE30 | Build Equipment Pads for Generators | 2025-04-30 | 2025-05-10
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UMSs | 2025-02-10 | 2025-02-19
Electrical Yard | COLO 4 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UMSs | 2025-03-15 | 2025-03-26
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UMSs | 2025-04-19 | 2025-04-29
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UPMs | 2025-01-29 | 2025-02-07
Electrical Yard | COLO 4 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UPMs | 2025-03-05 | 2025-03-14
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UPMs | 2025-04-08 | 2025-04-18
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | EE31 | Build Equipment Pads for XFMs | 2025-01-17 | 2025-01-28
Electrical Yard | COLO 4 | Electrical | #F2F09E | EE31 | Build Equipment Pads for XFMs | 2025-02-21 | 2025-03-04
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE31 | Build Equipment Pads for XFMs | 2025-03-28 | 2025-04-07
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Building Footprint Pad Ready | 2024-09-30 | 2024-09-30
Fitout | Electrical Room | Electrical | #F2F09E | EE28 | Cable Tray / Ceiling Steel Height | 2025-02-04 | 2025-02-04
Fitout | Fire Riser Room | Framing | #3598FE | J17 | Ceiling Grid & Tile | 2025-02-18 | 2025-02-21
Fitout | Restrooms & Janitor Room | Framing | #3598FE | J17 | Ceiling Grid & Tile | 2025-02-18 | 2025-02-21
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- Cable Bus Fabrication/ Lead Time | 2024-10-31 | 2025-03-03
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- HACs Fabrication/ Lead Time | 2024-10-31 | 2024-12-05
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- MV Cables Fabrication/ Lead Time | 2024-08-22 | 2025-04-29
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- MV Metering Cabinet - *Not Used* [65 Weeks] - Not Tied | 2024-08-21 | 2025-11-30
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- MV Metering Cabinet - Substitute [43 Weeks] | 2024-08-21 | 2025-06-25
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Building Pad Ready | 2024-09-05 | 2024-09-05
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Closeout Complete | 2026-01-22 | 2026-01-22
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Commissioning Complete | 2025-11-19 | 2025-11-19
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Construction Start | 2024-08-21 | 2024-08-21
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Electrical Service Available | 2025-05-05 | 2025-05-05
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Enclosure Complete | 2025-01-15 | 2025-01-15
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Final Completion (SC+40d) | 2026-01-22 | 2026-01-22
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Foundations Complete | 2024-11-12 | 2024-11-12
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Roofing Complete | 2024-12-31 | 2024-12-31
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Structure Complete | 2024-12-03 | 2024-12-03
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Structure Start | 2024-09-10 | 2024-09-10
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Substantial Completion | 2025-12-02 | 2025-12-02
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Utilities Available to Owner (Gas Service N/A) | 2024-12-26 | 2024-12-26
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Clayco Proposal Due date | 2024-10-11 | 2024-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete BAS Testing | 2025-08-30 | 2025-08-30
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete CX L3 (Green Tag) | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete EPMS Testing | 2025-08-30 | 2025-08-30
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Fire Alarm | 2025-08-30 | 2025-08-30
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete L1 Cx (All Red Tags/ ROJ) | 2025-06-04 | 2025-06-04
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete L2 Cx (Yellow Tag) | 2025-07-02 | 2025-07-02
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete L4 Cx (Blue Tag) | 2025-09-15 | 2025-09-15
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Last ROJ | 2025-03-08 | 2025-03-08
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete SOG | 2024-12-27 | 2024-12-27
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Superstructure | 2024-12-14 | 2024-12-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete U/G Utilities (No Elec) | 2024-12-14 | 2024-12-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete U/G Utilities/ MV UG Electrical | 2024-12-14 | 2024-12-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Utility Power- On | 2025-05-05 | 2025-05-05
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Weather Tight | 2025-01-16 | 2025-01-16
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete BAS Testing | 2025-09-30 | 2025-09-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete BAS Testing | 2025-10-31 | 2025-10-31
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Earthwork & U/G Site Utilities | 2024-12-26 | 2024-12-26
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete EPMS Testing | 2025-09-30 | 2025-09-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete EPMS Testing | 2025-10-31 | 2025-10-31
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Fire Alarm | 2025-09-30 | 2025-09-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Fire Alarm | 2025-10-31 | 2025-10-31
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Foundation | 2024-09-19 | 2024-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Foundation | 2024-10-31 | 2024-10-31
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Foundation | 2024-11-12 | 2024-11-12
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete L1 Cx (All Red Tags/ ROJ) | 2025-07-19 | 2025-07-19
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete L1 Cx (All Red Tags/ ROJ) | 2025-08-05 | 2025-08-05
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete L2 Cx (Yellow Tag) | 2025-08-14 | 2025-08-14
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete L2 Cx (Yellow Tag) | 2025-09-03 | 2025-09-03
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete L4 Cx (Blue Tag) | 2025-10-16 | 2025-10-16
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete L4 Cx (Blue Tag) | 2025-11-15 | 2025-11-15
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Landscaping/ Hardscaping | 2025-11-19 | 2025-11-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Last ROJ | 2025-03-30 | 2025-03-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Last ROJ | 2025-03-31 | 2025-03-31
Fitout | Fire Riser Room | Fire Protection | #D85234 | GSA | Complete Pipe/ Valves | 2025-02-22 | 2025-02-24
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete SOG | 2025-01-10 | 2025-01-10
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete SOG | 2025-01-25 | 2025-01-25
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Superstructure | 2024-12-31 | 2024-12-31
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Superstructure | 2025-01-15 | 2025-01-15
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete U/G Utilities/ MV UG Electric | 2024-12-27 | 2024-12-27
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete U/G Utilities/ MV UG Electric | 2025-01-13 | 2025-01-13
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Utility Power- On | 2025-05-05 | 2025-05-05
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Utility Power- On | 2025-05-05 | 2025-05-05
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-03-11 | 2025-03-13
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-03-19 | 2025-03-21
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-04-11 | 2025-04-15
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-03-31 | 2025-04-02
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-04-15 | 2025-04-17
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-04-23 | 2025-04-25
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-16 | 2025-05-19
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-05 | 2025-05-07
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-19 | 2025-05-21
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-28 | 2025-05-30
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-06-20 | 2025-06-23
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-06-07 | 2025-06-10
Commissioning | COLO 3 - CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-04 | 2025-06-12
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-09 | 2025-06-18
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-24 | 2025-07-07
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-13 | 2025-06-23
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-20 | 2025-06-28
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-25 | 2025-07-03
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-08-06 | 2025-08-14
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-07-18 | 2025-07-28
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-07-19 | 2025-07-29
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-07-24 | 2025-08-02
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-08-25 | 2025-09-03
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-08-04 | 2025-08-12
Milestones | COLO 4 | Milestone | #000000 | ML21 | CX L3 Complete | 2025-09-19 | 2025-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Cx L5 IST Complete | 2025-10-20 | 2025-10-20
Milestones | COLO 5 | Milestone | #000000 | ML21 | CX Level 3 Complete | 2025-10-11 | 2025-10-11
Milestones | COLO 5 | Milestone | #000000 | ML21 | Cx Level 5 IST Complete | 2025-11-19 | 2025-11-19
Fitout | COLO 3 - CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-03-11 | 2025-03-14
Fitout | COLO 3 - CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-03-19 | 2025-03-24
Fitout | COLO 3 - CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-04-11 | 2025-04-16
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-03-31 | 2025-04-03
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-04-15 | 2025-04-18
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-04-23 | 2025-04-26
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-05-16 | 2025-05-20
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-05-05 | 2025-05-08
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-05-19 | 2025-05-22
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-05-28 | 2025-05-31
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-06-20 | 2025-06-24
Fitout | CELL 4 Data Hall Fitout Activities | HAC's | #FED8E8 | S2 | Detail HACs | 2025-06-07 | 2025-06-11
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-06 | 2025-02-07
Fitout | COLO 3 - CELL 1 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-15 | 2025-02-15
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-06 | 2025-03-06
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-13 | 2025-02-13
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-04 | 2025-03-04
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-08 | 2025-03-10
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-08 | 2025-03-08
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-27 | 2025-03-27
Fitout | CELL 4 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-24 | 2025-02-25
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-24 | 2025-02-24
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-14 | 2025-03-14
Fitout | CELL 1 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-11 | 2025-03-12
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-11 | 2025-03-11
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-29 | 2025-03-29
Fitout | CELL 2 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-19 | 2025-03-20
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-19 | 2025-03-19
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-07 | 2025-04-07
Fitout | CELL 3 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-11 | 2025-04-14
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-11 | 2025-04-11
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-30 | 2025-04-30
Fitout | CELL 4 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-31 | 2025-04-01
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-31 | 2025-03-31
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-18 | 2025-04-18
Fitout | CELL 1 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-15 | 2025-04-16
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-15 | 2025-04-15
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-02 | 2025-05-02
Fitout | CELL 2 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-23 | 2025-04-24
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-23 | 2025-04-23
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-12 | 2025-05-12
Fitout | CELL 3 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-16 | 2025-05-17
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-16 | 2025-05-16
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-06-04 | 2025-06-04
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-05 | 2025-05-06
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-05 | 2025-05-05
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-22 | 2025-05-22
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Earthworks & U/G Utilities Start | 2025-03-05 | 2025-03-05
Milestones | COLO 5 | Milestone | #000000 | ML21 | Entire Building | 2025-02-14 | 2025-02-14
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-06-19 | 2025-06-27
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-07-08 | 2025-07-18
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-06-24 | 2025-07-02
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-06-30 | 2025-07-10
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-07-07 | 2025-07-15
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-08-15 | 2025-08-25
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-07-29 | 2025-08-06
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-07-30 | 2025-08-07
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-08-04 | 2025-08-12
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-09-04 | 2025-09-13
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-08-13 | 2025-08-22
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Final Completion/ Turnover to Operations | 2025-10-02 | 2025-10-02
Milestones | COLO 4 | Milestone | #000000 | ML21 | Final Completion/ Turnover to Operations | 2025-11-06 | 2025-11-06
Milestones | COLO 5 | Milestone | #000000 | ML21 | Final Completion/Turnover to Operations | 2025-12-04 | 2025-12-04
Site Prep/ Mobilization | Milestone | Milestone | #000000 | ML21 | Fine Grading Building Pad | 2024-08-19 | 2024-09-04
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-01 | 2025-02-04
Fitout | COLO 3 - CELL 1 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-22 | 2025-03-04
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-06 | 2025-03-07
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-11 | 2025-02-13
Fitout | COLO 3 - CELL 2 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-04 | 2025-03-05
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-06 | 2025-03-08
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-08 | 2025-03-10
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-27 | 2025-03-28
Fitout | CELL 4 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-21 | 2025-02-24
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-24 | 2025-02-25
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-14 | 2025-03-15
Fitout | CELL 1 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-08 | 2025-03-11
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-11 | 2025-03-12
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-29 | 2025-03-31
Fitout | CELL 2 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-17 | 2025-03-19
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-19 | 2025-03-20
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-07 | 2025-04-08
Fitout | CELL 3 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-09 | 2025-04-11
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-11 | 2025-04-14
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-30 | 2025-05-01
Fitout | CELL 4 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-28 | 2025-03-31
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-31 | 2025-04-01
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-18 | 2025-04-19
Fitout | CELL 1 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-11 | 2025-04-15
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-15 | 2025-04-16
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-02 | 2025-05-05
Fitout | CELL 2 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-21 | 2025-04-23
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-23 | 2025-04-24
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-12 | 2025-05-13
Fitout | CELL 3 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-14 | 2025-05-16
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-16 | 2025-05-17
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-06-04 | 2025-06-05
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-01 | 2025-05-05
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-05 | 2025-05-06
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-22 | 2025-05-23
Fitout | Fire Riser Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-12 | 2025-02-13
Fitout | Loading Dock | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-15 | 2025-02-17
Fitout | Restrooms & Janitor Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-13 | 2025-02-14
Fitout | SER (Security Equipment Room) | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-06 | 2025-02-07
Fitout | STORAGE (High Value & Secure) Rooms | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-26 | 2025-03-03
Fitout | Electrical Room | Framing | #3598FE | J13 | Finsh Drywall and Wall Protection | 2025-01-28 | 2025-01-31
Fitout | Entry Room 1 | Framing | #3598FE | J13 | Finsh Drywall and Wall Protection | 2025-01-30 | 2025-02-03
Fitout | Entry Room 2 | Framing | #3598FE | J13 | Finsh Drywall and Wall Protection | 2025-02-01 | 2025-02-05
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | J13 | Finsh Drywall and Wall Protection | 2025-02-04 | 2025-02-07
Fitout | Electrical Room | Framing | #3598FE | J13 | Fire Protection OH R/I | 2025-01-20 | 2025-01-20
Fitout | Entry Room 1 | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-21 | 2025-01-21
Fitout | Entry Room 2 | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-22 | 2025-01-22
Fitout | FCR (Facilities Control Room) | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-23 | 2025-01-23
Fitout | Fire Riser Room | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-27 | 2025-01-27
Fitout | Loading Dock | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-29 | 2025-01-29
Fitout | Restrooms & Janitor Room | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-28 | 2025-01-28
Fitout | SER (Security Equipment Room) | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-24 | 2025-01-24
Fitout | STORAGE (High Value & Secure) Rooms | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-25 | 2025-01-25
Fitout | STORAGE (High Value & Secure) Rooms | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-03-06 | 2025-03-17
Milestones | COLO 4 | Milestone | #000000 | ML21 | Foundation Start | 2024-09-16 | 2024-09-16
Milestones | COLO 5 | Milestone | #000000 | ML21 | Foundation Start | 2024-09-09 | 2024-09-09
Milestones | Milestone | Milestone | #000000 | ML21 | Foundations / Stem Walls (100% Complete) | 2024-10-10 | 2024-11-02
Milestones | Milestone | Milestone | #000000 | ML21 | Foundations / Stem Walls (50% Complete) | 2024-09-09 | 2024-10-09
Fitout | Electrical Room | Framing | #3598FE | J11 | Framing | 2025-01-21 | 2025-01-21
Fitout | Entry Room 1 | Framing | #3598FE | J11 | Framing | 2025-01-22 | 2025-01-22
Fitout | Entry Room 2 | Framing | #3598FE | J11 | Framing | 2025-01-23 | 2025-01-23
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | J11 | Framing | 2025-01-24 | 2025-01-24
Fitout | Fire Riser Room | Framing | #3598FE | J11 | Framing | 2025-01-28 | 2025-01-28
Fitout | Loading Dock | Framing | #3598FE | J11 | Framing | 2025-01-30 | 2025-01-30
Fitout | Restrooms & Janitor Room | Framing | #3598FE | J11 | Framing | 2025-01-29 | 2025-01-29
Fitout | SER (Security Equipment Room) | Framing | #3598FE | J11 | Framing | 2025-01-25 | 2025-01-25
Fitout | STORAGE (High Value & Secure) Rooms | Framing | #3598FE | J11 | Framing | 2025-01-27 | 2025-01-27
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-06-28 | 2025-07-02
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-07-19 | 2025-07-24
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-07-03 | 2025-07-09
Commissioning | CELL 1 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-07-11 | 2025-07-15
Commissioning | CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-07-16 | 2025-07-19
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-26 | 2025-08-29
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-07 | 2025-08-11
Commissioning | CELL 1 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-08 | 2025-08-12
Commissioning | CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-13 | 2025-08-18
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-09-15 | 2025-09-19
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-23 | 2025-08-27
Milestones | General | Milestone | #000000 | ML21 | GC Mobilization Finish/ Site Secured | 2024-09-16 | 2024-09-16
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | GC Mobilization Start | 2025-02-25 | 2025-02-25
Fitout | COLO 3 - CELL 1 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-02-18 | 2025-02-18
Fitout | COLO 3 - CELL 1 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-07 | 2025-03-07
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-11 | 2025-03-13
Fitout | COLO 3 - CELL 2 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-02-26 | 2025-02-26
Fitout | COLO 3 - CELL 2 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-02-18 | 2025-02-18
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-08 | 2025-03-11
Fitout | COLO 3 - CELL 3 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-21 | 2025-03-21
Fitout | CELL 3 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-13 | 2025-03-13
Fitout | CELL 3 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-01 | 2025-04-03
Fitout | CELL 4 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-10 | 2025-03-10
Fitout | CELL 4 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-02-28 | 2025-02-28
Fitout | CELL 4 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-19 | 2025-03-21
Fitout | CELL 1 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-25 | 2025-03-25
Fitout | CELL 1 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-15 | 2025-03-15
Fitout | CELL 1 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-03 | 2025-04-05
Fitout | CELL 2 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-02 | 2025-04-02
Fitout | CELL 2 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-25 | 2025-03-25
Fitout | CELL 2 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-11 | 2025-04-15
Fitout | CELL 3 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-25 | 2025-04-25
Fitout | CELL 3 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-17 | 2025-04-17
Fitout | CELL 3 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-06 | 2025-05-08
Fitout | CELL 4 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-14 | 2025-04-14
Fitout | CELL 4 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-04 | 2025-04-04
Fitout | CELL 4 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-23 | 2025-04-25
Fitout | CELL 1 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-28 | 2025-04-28
Fitout | CELL 1 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-19 | 2025-04-19
Fitout | CELL 1 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-08 | 2025-05-10
Fitout | CELL 2 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-07 | 2025-05-07
Fitout | CELL 2 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-28 | 2025-04-28
Fitout | CELL 2 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-16 | 2025-05-19
Fitout | CELL 3 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-30 | 2025-05-30
Fitout | CELL 3 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-21 | 2025-05-21
Fitout | CELL 3 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-06-09 | 2025-06-11
Fitout | CELL 4 Data Hall Fitout Activities | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-17 | 2025-05-17
Fitout | CELL 4 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-09 | 2025-05-09
Fitout | CELL 4 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-28 | 2025-05-30
Milestones | COLO 4 | Milestone | #000000 | ML21 | Generator Ready for Fuel | 2025-04-24 | 2025-04-24
Milestones | COLO 5 | Milestone | #000000 | ML21 | Generator Ready for Fuel | 2025-05-31 | 2025-05-31
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Generator Ready for Fuel (Exterior Yard) | 2025-03-15 | 2025-03-15
Fitout | CELL 1 Data Hall | Framing | #3598FE | J3 | IInstall Framing | 2025-02-25 | 2025-02-27
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-01-25 | 2025-01-28
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-01-31 | 2025-02-10
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-03 | 2025-02-05
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-05 | 2025-02-06
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-26 | 2025-02-28
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-28 | 2025-03-03
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-14 | 2025-02-17
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-17 | 2025-02-18
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-28 | 2025-03-04
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-04 | 2025-03-05
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-10 | 2025-03-12
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-12 | 2025-03-13
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-02 | 2025-04-04
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-04 | 2025-04-05
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-20 | 2025-03-24
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-24 | 2025-03-25
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-04 | 2025-04-07
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-07 | 2025-04-08
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-14 | 2025-04-16
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-16 | 2025-04-17
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-05-07 | 2025-05-09
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-05-09 | 2025-05-10
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-24 | 2025-04-26
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-26 | 2025-04-28
Fitout | COLO 3 - CELL 1 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-03-12 | 2025-03-24
Fitout | COLO 3 - CELL 2 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-03-10 | 2025-03-20
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-04-02 | 2025-04-14
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-03-20 | 2025-04-01
Fitout | CELL 1 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-04-04 | 2025-04-16
Fitout | CELL 2 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-04-14 | 2025-04-24
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-05-07 | 2025-05-17
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-04-24 | 2025-05-06
Fitout | CELL 1 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-05-09 | 2025-05-20
Fitout | CELL 2 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-05-17 | 2025-05-29
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-06-10 | 2025-06-21
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-05-29 | 2025-06-09
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-02-25 | 2025-03-03
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-03-06 | 2025-03-11
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-03-29 | 2025-04-03
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-03-17 | 2025-03-21
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-04-01 | 2025-04-05
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-04-09 | 2025-04-15
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-05-02 | 2025-05-08
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-04-21 | 2025-04-25
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-05-06 | 2025-05-10
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-05-14 | 2025-05-19
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-06-06 | 2025-06-11
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-05-27 | 2025-05-30
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-02-17 | 2025-02-18
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-12 | 2025-03-13
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-02-14 | 2025-02-15
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-10 | 2025-03-11
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-10 | 2025-03-11
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-02 | 2025-04-03
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-02-25 | 2025-02-26
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-20 | 2025-03-21
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-12 | 2025-03-13
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-04 | 2025-04-05
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-20 | 2025-03-21
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-14 | 2025-04-15
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-14 | 2025-04-15
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-07 | 2025-05-08
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-01 | 2025-04-02
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-24 | 2025-04-25
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-16 | 2025-04-17
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-09 | 2025-05-10
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-24 | 2025-04-25
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-17 | 2025-05-19
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-17 | 2025-05-19
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-06-10 | 2025-06-11
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-06 | 2025-05-07
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-29 | 2025-05-30
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-02-18 | 2025-02-21
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-02-26 | 2025-03-03
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-03-21 | 2025-03-26
Fitout | CELL 4 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-03-10 | 2025-03-13
Fitout | CELL 1 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-03-25 | 2025-03-28
Fitout | CELL 2 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-04-02 | 2025-04-05
Fitout | CELL 3 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-04-25 | 2025-04-29
Fitout | CELL 4 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-04-14 | 2025-04-17
Fitout | CELL 1 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-04-28 | 2025-05-01
Fitout | CELL 2 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-05-07 | 2025-05-10
Fitout | CELL 3 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-05-30 | 2025-06-03
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-05-17 | 2025-05-21
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-07 | 2025-03-11
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-05 | 2025-03-08
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-28 | 2025-04-01
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-15 | 2025-03-19
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-31 | 2025-04-03
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-04-08 | 2025-04-11
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-05-01 | 2025-05-06
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-04-19 | 2025-04-23
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-05-05 | 2025-05-08
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-05-13 | 2025-05-16
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-06-05 | 2025-06-09
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-05-23 | 2025-05-28
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-03-14 | 2025-03-17
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-03-24 | 2025-03-26
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-04-16 | 2025-04-18
Fitout | CELL 4 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-04-03 | 2025-04-05
Fitout | CELL 1 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-04-18 | 2025-04-21
Fitout | CELL 2 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-04-26 | 2025-04-29
Fitout | CELL 3 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-05-20 | 2025-05-22
Fitout | CELL 4 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-05-08 | 2025-05-10
Fitout | CELL 1 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-05-22 | 2025-05-23
Fitout | CELL 2 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-05-31 | 2025-06-03
Fitout | CELL 3 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-06-24 | 2025-06-26
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-06-11 | 2025-06-13
Site Utilities | Overall | Framing | #3598FE | J22 | Install Deep Telecom | 2024-09-23 | 2024-10-21
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-02-27 | 2025-02-28
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-03-08 | 2025-03-10
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-04-01 | 2025-04-02
Fitout | CELL 4 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-03-19 | 2025-03-20
Fitout | CELL 1 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-04-03 | 2025-04-04
Fitout | CELL 2 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-04-11 | 2025-04-14
Fitout | CELL 3 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-05-06 | 2025-05-07
Fitout | CELL 4 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-04-23 | 2025-04-24
Fitout | CELL 1 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-05-08 | 2025-05-09
Fitout | CELL 2 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-05-16 | 2025-05-17
Fitout | CELL 3 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-06-09 | 2025-06-10
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J23 | Install Device Tiles | 2025-05-28 | 2025-05-29
Fitout | Admin | Framing | #3598FE | J24 | Install Doors | 2025-02-22 | 2025-02-26
Fitout | Fire Riser Room | Framing | #3598FE | J30 | Install downcomers | 2025-01-31 | 2025-01-31
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-01-29 | 2025-01-31
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-02-06 | 2025-02-10
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-03-03 | 2025-03-05
Fitout | CELL 4 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-02-18 | 2025-02-20
Fitout | CELL 1 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-03-05 | 2025-03-07
Fitout | CELL 2 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-03-13 | 2025-03-15
Fitout | CELL 3 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-04-05 | 2025-04-08
Fitout | CELL 4 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-03-25 | 2025-03-27
Fitout | CELL 1 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-04-08 | 2025-04-10
Fitout | CELL 2 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-04-17 | 2025-04-19
Fitout | CELL 3 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-05-10 | 2025-05-13
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-04-28 | 2025-04-30
Fitout | COLO 3 - CELL 1 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-02-11 | 2025-02-21
Fitout | COLO 3 - CELL 2 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-02-07 | 2025-02-12
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-03-04 | 2025-03-07
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-02-19 | 2025-02-22
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-03-06 | 2025-03-10
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-03-14 | 2025-03-18
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-04-07 | 2025-04-10
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-03-26 | 2025-03-29
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-04-09 | 2025-04-14
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-04-18 | 2025-04-22
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-05-12 | 2025-05-15
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-04-29 | 2025-05-02
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-03-04 | 2025-03-05
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-02-28 | 2025-03-03
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-03-25 | 2025-03-26
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-03-12 | 2025-03-13
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-03-27 | 2025-03-28
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-04-04 | 2025-04-05
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-04-28 | 2025-04-29
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-04-16 | 2025-04-17
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-04-30 | 2025-05-01
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-05-09 | 2025-05-10
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-06-02 | 2025-06-03
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-05-20 | 2025-05-21
Fitout | Fire Riser Room | Framing | #3598FE | J31 | Install Duct Work | 2025-01-29 | 2025-01-30
Fitout | Loading Dock | Framing | #3598FE | J31 | Install Ductwork | 2025-01-29 | 2025-02-15
Fitout | Loading Dock | Framing | #3598FE | J31 | Install Ductwork (Remaining Rooms, Corridor) | 2025-01-30 | 2025-02-17
Fitout | STORAGE (High Value & Secure) Rooms | Framing | #3598FE | J31 | Install Ductwork and Cracs | 2025-02-07 | 2025-02-25
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J32 | Install Exterior Wall Panels | 2024-11-30 | 2024-12-14
Core & Shell | COLO 4 | Framing | #3598FE | J32 | Install Exterior Wall Panels | 2024-12-16 | 2024-12-31
Core & Shell | COLO 5 | Framing | #3598FE | J32 | Install Exterior Wall Panels | 2025-01-02 | 2025-01-15
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-02-27 | 2025-03-05
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-03-08 | 2025-03-13
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-01 | 2025-04-05
Fitout | CELL 4 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-03-19 | 2025-03-25
Fitout | CELL 1 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-03 | 2025-04-08
Fitout | CELL 2 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-11 | 2025-04-17
Fitout | CELL 3 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-06 | 2025-05-10
Fitout | CELL 4 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-23 | 2025-04-28
Fitout | CELL 1 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-08 | 2025-05-13
Fitout | CELL 2 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-16 | 2025-05-21
Fitout | CELL 3 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-06-09 | 2025-06-13
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-28 | 2025-06-02
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-01-20 | 2025-01-24
Fitout | COLO 3 - CELL 1 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-01-25 | 2025-01-30
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-01-30 | 2025-02-01
Fitout | COLO 3 - CELL 2 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-02-03 | 2025-02-04
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-02-22 | 2025-02-25
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-02-26 | 2025-02-27
Fitout | CELL 4 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-02-11 | 2025-02-13
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-02-14 | 2025-02-15
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-02-28 | 2025-03-03
Fitout | CELL 2 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-03-06 | 2025-03-08
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-03-10 | 2025-03-11
Fitout | CELL 3 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-03-29 | 2025-04-01
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-04-02 | 2025-04-03
Fitout | CELL 4 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-03-17 | 2025-03-19
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-03-20 | 2025-03-21
Fitout | CELL 1 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-04-01 | 2025-04-03
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-04-04 | 2025-04-05
Fitout | CELL 2 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-04-09 | 2025-04-11
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-04-14 | 2025-04-15
Fitout | CELL 3 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-05-02 | 2025-05-06
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-05-07 | 2025-05-08
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J3 | Install Framing | 2025-04-21 | 2025-04-23
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-04-24 | 2025-04-25
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E34 | Install Generators | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F2F09E | E34 | Install Generators | 2025-04-11 | 2025-04-24
Electrical Yard | COLO 5 | Electrical | #F2F09E | E34 | Install Generators | 2025-05-19 | 2025-05-31
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J34 | Install Louvers & Dampers | 2024-12-16 | 2025-01-06
Core & Shell | COLO 4 | Framing | #3598FE | J34 | Install Louvers & Dampers | 2025-01-07 | 2025-01-25
Core & Shell | COLO 5 | Framing | #3598FE | J34 | Install Louvers & Dampers | 2025-01-27 | 2025-02-14
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J35 | Install Misc. Metals (Trims, Gutters, Catwalks) | 2024-12-30 | 2025-01-17
Core & Shell | COLO 4 | Framing | #3598FE | J35 | Install Misc. Metals (Trims, Gutters, Catwalks) | 2025-01-11 | 2025-01-30
Core & Shell | COLO 5 | Framing | #3598FE | J35 | Install Misc. Metals (Trims, Gutters, Catwalks) | 2025-01-27 | 2025-02-14
Site Utilities | Overall | Framing | #3598FE | J36 | Install MV Ductbanks | 2024-10-04 | 2024-11-18
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-02-22 | 2025-02-26
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-03-04 | 2025-03-07
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-03-27 | 2025-03-31
Fitout | CELL 4 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-03-14 | 2025-03-18
Fitout | CELL 1 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-03-29 | 2025-04-02
Fitout | CELL 2 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-04-07 | 2025-04-10
Fitout | CELL 3 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-04-30 | 2025-05-05
Fitout | CELL 4 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-04-18 | 2025-04-22
Fitout | CELL 1 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-05-02 | 2025-05-07
Fitout | CELL 2 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-05-12 | 2025-05-15
Fitout | CELL 3 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-06-04 | 2025-06-07
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-05-22 | 2025-05-27
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J38 | Install Primary Steel | 2024-10-21 | 2024-11-07
Core & Shell | COLO 4 | Framing | #3598FE | J38 | Install Primary Steel | 2024-11-02 | 2024-11-20
Core & Shell | COLO 5 | Framing | #3598FE | J38 | Install Primary Steel | 2024-11-14 | 2024-12-03
Fitout | Entry Room 1 | Framing | #3598FE | J39 | Install Raceway | 2025-02-06 | 2025-02-10
Fitout | Entry Room 2 | Framing | #3598FE | J39 | Install Raceway | 2025-02-10 | 2025-02-12
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | J39 | Install Raceway | 2025-02-12 | 2025-02-14
Fitout | SER (Security Equipment Room) | Framing | #3598FE | J39 | Install Raceway | 2025-02-12 | 2025-02-14
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J40 | Install Roof Panels | 2024-11-08 | 2024-11-29
Core & Shell | COLO 4 | Framing | #3598FE | J40 | Install Roof Panels | 2024-11-21 | 2024-12-14
Core & Shell | COLO 5 | Framing | #3598FE | J40 | Install Roof Panels | 2024-12-04 | 2024-12-31
Site Utilities | Overall | Framing | #3598FE | J41 | Install Sanitary Lines | 2024-11-04 | 2024-12-03
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-02-10 | 2025-02-12
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-02-18 | 2025-02-20
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-03-13 | 2025-03-15
Fitout | CELL 4 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-02-28 | 2025-03-04
Fitout | CELL 1 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-03-15 | 2025-03-18
Fitout | CELL 2 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-03-25 | 2025-03-27
Fitout | CELL 3 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-04-17 | 2025-04-19
Fitout | CELL 4 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-04-04 | 2025-04-07
Fitout | CELL 1 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-04-19 | 2025-04-22
Fitout | CELL 2 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-04-28 | 2025-04-30
Fitout | CELL 3 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-05-21 | 2025-05-23
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-05-09 | 2025-05-12
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-02-21 | 2025-02-22
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-03-17 | 2025-03-18
Fitout | CELL 4 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-03-05 | 2025-03-06
Fitout | CELL 1 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-03-19 | 2025-03-20
Fitout | CELL 2 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-03-28 | 2025-03-29
Fitout | CELL 3 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-04-21 | 2025-04-22
Fitout | CELL 4 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-04-08 | 2025-04-09
Fitout | CELL 1 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-04-23 | 2025-04-24
Fitout | CELL 2 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-05-01 | 2025-05-02
Fitout | CELL 3 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-05-27 | 2025-05-27
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J42 | Install Secondary Steel | 2025-05-13 | 2025-05-14
Site Utilities | Overall | Framing | #3598FE | J43 | Install Storm Lines | 2024-11-09 | 2024-12-17
Site Utilities | Under Building Pad | Electrical | #F2F09E | EE36 | Install UG Electrical / UPM Crossing (under Building Pad) | 2024-09-30 | 2024-10-30
Site Utilities | Under Building Pad | Electrical | #F2F09E | EE37 | Install UG Telecom (under Building Pad) | 2024-09-18 | 2024-10-04
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E28 | Install UMSs | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F2F09E | E28 | Install UMSs | 2025-04-02 | 2025-04-15
Electrical Yard | COLO 5 | Electrical | #F2F09E | E28 | Install UMSs | 2025-05-16 | 2025-05-29
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E30 | Install UPMs | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F2F09E | E30 | Install UPMs | 2025-04-02 | 2025-04-15
Electrical Yard | COLO 5 | Electrical | #F2F09E | E30 | Install UPMs | 2025-05-14 | 2025-05-27
Site Utilities | Overall | Electrical | #F2F09E | E38 | Install Water Line | 2024-11-15 | 2024-12-26
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E39 | Install XFMs | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F2F09E | E39 | Install XFMs | 2025-04-02 | 2025-04-15
Electrical Yard | COLO 5 | Electrical | #F2F09E | E39 | Install XFMs | 2025-05-12 | 2025-05-23
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-01-17 | 2025-01-17
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-01-29 | 2025-01-29
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-02-21 | 2025-02-21
Fitout | CELL 4 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-02-10 | 2025-02-10
Fitout | CELL 1 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-02-24 | 2025-02-24
Fitout | CELL 2 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-03-05 | 2025-03-05
Fitout | CELL 3 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-03-28 | 2025-03-28
Fitout | CELL 4 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-03-15 | 2025-03-15
Fitout | CELL 1 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-03-31 | 2025-03-31
Fitout | CELL 2 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-04-08 | 2025-04-08
Fitout | CELL 3 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-05-01 | 2025-05-01
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J1 | Layout Framing | 2025-04-19 | 2025-04-19
Fitout | Admin | Electrical | #F2F09E | EEA | Light Fixtures Installation | 2025-02-27 | 2025-03-11
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-07-19 | 2025-07-23
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-08-09 | 2025-08-14
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-07-24 | 2025-07-29
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-07-31 | 2025-08-04
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-08-05 | 2025-08-08
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-09-16 | 2025-09-19
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-08-27 | 2025-08-30
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-08-28 | 2025-09-02
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-09-03 | 2025-09-08
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-10-06 | 2025-10-11
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-09-13 | 2025-09-17
Fitout | Electrical Room | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-22 | 2025-01-23
Fitout | Entry Room 1 | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-24 | 2025-01-25
Fitout | Entry Room 2 | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-27 | 2025-01-28
Fitout | FCR (Facilities Control Room) | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-29 | 2025-01-30
Fitout | Fire Riser Room | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-02-05 | 2025-02-06
Fitout | Loading Dock | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-02-11 | 2025-02-12
Fitout | Restrooms & Janitor Room | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-02-07 | 2025-02-10
Fitout | SER (Security Equipment Room) | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-31 | 2025-02-01
Fitout | STORAGE (High Value & Secure) Rooms | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-02-03 | 2025-02-04
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 1 | 2025-04-25 | 2025-05-05
Electrical Yard | COLO 4 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 1 | 2025-04-25 | 2025-05-05
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 2 | 2025-05-06 | 2025-05-14
Electrical Yard | COLO 4 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 2 | 2025-05-06 | 2025-05-14
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 3 | 2025-05-27 | 2025-06-03
Electrical Yard | COLO 4 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 3 | 2025-05-27 | 2025-06-04
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 4 | 2025-05-15 | 2025-05-23
Electrical Yard | COLO 4 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 4 | 2025-05-15 | 2025-05-23
Electrical Yard | COLO 5 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating(To Junction Box) to Cell 1 | 2025-05-02 | 2025-05-12
Electrical Yard | COLO 5 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating(To Junction Box) to Cell 2 | 2025-05-13 | 2025-05-21
Electrical Yard | COLO 5 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating(To Junction Box) to Cell 3 | 2025-06-02 | 2025-06-10
Electrical Yard | COLO 5 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating(To Junction Box) to Cell 4 | 2025-05-22 | 2025-05-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ1 | OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/04/24) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ2 | OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/9/24) | 2024-09-09 | 2024-09-09
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ3 | OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date- 3/8/2025) | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ4 | OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 4/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ5 | OFCI- Receive Auxillary (Mech) Power Distribution Panels (ADP) (Del Date- 3/8/2025) | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ6 | OFCI- Air Handling Units (AHU) (Stulz) Delivered | 2025-03-13 | 2025-03-13
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ7 | OFCI- Air Handling Units (AHU) (Stulz) Delivered | 2025-04-05 | 2025-04-05
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ8 | OFCI- Air Handling Units (AHU) (Stulz) Delivered | 2025-05-11 | 2025-05-11
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ9 | OFCI- Air Handling Units (AHU) (Stulz) Shipped/ROJ | 2025-03-09 | 2025-03-13
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ10 | OFCI- Air Handling Units (AHU) (Stulz) Shipping/ ROJ | 2025-04-01 | 2025-04-05
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ11 | OFCI- Air Handling Units (AHU) (Stulz) Shipping/ROJ | 2025-05-11 | 2025-05-11
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ12 | OFCI- Auto Transfer Control Panel (TCP) Delivered | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ13 | OFCI- Auto Transfer Control Panel (TCP) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ14 | OFCI- Auto Transfer Control Panel (TCP) Delivered | 2025-04-04 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ15 | OFCI- Auto Transfer Control Panel (TCP) Shipping/ ROJ | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ16 | OFCI- Auto Transfer Control Panel (TCP) Shipping/ROJ | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ17 | OFCI- Auto Transfer Control Panel (TCP) Shipping/ROJ | 2025-03-30 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ18 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ19 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ20 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered | 2025-04-20 | 2025-04-20
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ21 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ22 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ23 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ | 2025-04-20 | 2025-04-20
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ24 | OFCI- Auxillary (Mech) Power Distribution Panels (ADP) Delivered | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ25 | OFCI- Auxillary (Mech) Power Distribution Panels (ADP) Shipping/ ROJ | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ26 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Delivered | 2025-01-04 | 2025-01-04
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ27 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Delivered | 2025-02-02 | 2025-02-02
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ28 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ | 2024-12-29 | 2025-01-04
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ29 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ | 2025-01-28 | 2025-02-02
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ30 | OFCI- Building Automation System (BAS) (ALC) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ31 | OFCI- Building Automation System (BAS) (ALC) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ32 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ33 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Delivered | 2025-05-03 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ34 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ35 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ | 2025-04-29 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ36 | OFCI- Busway / Busplugs (Starline Holding) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ37 | OFCI- Busway / Busplugs (Starline Holding) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ38 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ39 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ40 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (Schneider) Delivered | 2025-04-20 | 2025-04-20
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ41 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (Schneider) Shipping/ROJ | 2025-04-20 | 2025-04-20
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ42 | OFCI- Elec. Performance Monitoring System (EPMS) (Schneider) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ43 | OFCI- Elec. Performance Monitoring System (EPMS) (Schneider) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ44 | OFCI- HAC/Racking (Tate Access) Delivered | 2025-02-21 | 2025-02-21
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ45 | OFCI- HAC/Racking (Tate Access) Delivered | 2025-03-28 | 2025-03-28
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ46 | OFCI- HAC/Racking (Tate Access) Delivered | 2025-04-28 | 2025-04-28
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ47 | OFCI- HAC/Racking (Tate Access) Shipping/ ROJ | 2025-02-19 | 2025-02-21
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ48 | OFCI- HAC/Racking (Tate Access) Shipping/ROJ | 2025-03-26 | 2025-03-28
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ49 | OFCI- HAC/Racking (Tate Access) Shipping/ROJ | 2025-04-25 | 2025-04-28
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ50 | OFCI- LV Switchgear (Eaton) Delivered | 2025-03-02 | 2025-03-02
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ51 | OFCI- LV Switchgear (Eaton) Delivered | 2025-04-03 | 2025-04-03
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ52 | OFCI- LV Switchgear (Eaton) Shipping/ROJ | 2025-02-28 | 2025-03-02
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ53 | OFCI- LV Switchgear (Eaton) Shipping/ROJ | 2025-03-30 | 2025-04-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ54 | OFCI- LV Switchgear (LVS) (Eaton) Delivered | 2025-03-04 | 2025-03-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ55 | OFCI- LV Switchgear (LVS) (Eaton) Shipping/ ROJ | 2025-02-28 | 2025-03-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ56 | OFCI- Main LV Switch Board (MSB) Delivered | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ57 | OFCI- Main LV Switch Board (MSB) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ58 | OFCI- Main LV Switch Board (MSB) Delivered | 2025-04-04 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ59 | OFCI- Main LV Switch Board (MSB) Shipping/ ROJ | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ60 | OFCI- Main LV Switch Board (MSB) Shipping/ROJ | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ61 | OFCI- Main LV Switch Board (MSB) Shipping/ROJ | 2025-03-30 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ62 | OFCI- Mech Power Distribution Panels (ADP) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ63 | OFCI- Mech Power Distribution Panels (ADP) Delivered | 2025-04-04 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ64 | OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ65 | OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ | 2025-03-30 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ66 | OFCI- Medium Voltage Switchgear (JDC Power Sys) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ67 | OFCI- Medium Voltage Switchgear (JDC Power Sys) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ68 | OFCI- Medium Voltage Switchgear (MVS) (JD Power Sys) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ69 | OFCI- Medium Voltage Switchgear (MVS) (JD Power Sys) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ70 | OFCI- Medium Voltage Switchgear (MVS) (JDC Power Sys) Delivered | 2025-05-03 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ71 | OFCI- Medium Voltage Switchgear (MVS) (JDC Power Sys) Shipping/ROJ | 2025-04-29 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ72 | OFCI- Packaged Diesel Generator Set (CAT Holt) Delivered | 2025-02-24 | 2025-02-24
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ73 | OFCI- Packaged Diesel Generator Set (CAT Holt) Shipping/ ROJ | 2025-02-20 | 2025-02-24
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ74 | OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Delivered | 2025-04-10 | 2025-04-10
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ75 | OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ | 2025-04-06 | 2025-04-10
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ76 | OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Delivered | 2025-05-15 | 2025-05-15
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ77 | OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ | 2025-05-11 | 2025-05-15
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ78 | OFCI- Pad Mounted Transformers (XFM-TX) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ79 | OFCI- Pad Mounted Transformers (XFM-TX) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ80 | OFCI- Pad Mounted Transformers (XMF) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ81 | OFCI- Pad Mounted Transformers (XMF) Delivered | 2025-05-03 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ82 | OFCI- Pad Mounted Transformers (XMF) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ83 | OFCI- Pad Mounted Transformers (XMF) Shipping/ROJ | 2025-04-29 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 3-5 | ROJ | #747474 | ROJ84 | OFCI- PEMB Procurement (1st Del) (Nucor) Delivered | 2024-10-25 | 2024-10-25
MSFT OFCI ROJ Dates | COLO 3-5 | ROJ | #747474 | ROJ85 | OFCI- PEMB Procurement (1st Del) (Nucor) Shipping/ ROJ | 2024-10-21 | 2024-10-25
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ86 | OFCI- Power Distribution Units (PDU) (ABB) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ87 | OFCI- Power Distribution Units (PDU) (ABB) Delivered | 2025-05-07 | 2025-05-07
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ88 | OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ89 | OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ | 2025-05-03 | 2025-05-07
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ90 | OFCI- Power Distribution Units (PDU) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ91 | OFCI- Power Distribution Units (PDU) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ92 | OFCI- Receive Elec. Performance Monitoring System (EPMS) (Schneider) (SOW Del Date- 4/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ93 | OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/16/24) | 2024-09-16 | 2024-09-16
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ94 | OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ95 | OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date-3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ96 | OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 6/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ97 | OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 8/31/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ98 | OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 1/28/25) | 2025-01-28 | 2025-01-28
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ99 | OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 12/29/24) | 2024-12-29 | 2024-12-29
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ100 | OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 11/28/24) | 2024-11-30 | 2024-11-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ101 | OFCI- Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 2/23/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ102 | OFCI- Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 4/23/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ103 | OFCI- Receive Busway / Busplugs (Starline Holding) (Del Date- 1/25/24) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ104 | OFCI- Receive Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) (SOW Del Date- 6/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ105 | OFCI- Receive Elec. Performance Monitoring Syst. (EPMS) (Schneider) (SOW Del Date- 8/31/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ106 | OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 5/17/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ107 | OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 6/18/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ108 | OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 7/3/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ109 | OFCI- Receive LV Switchgear (Eaton) (SOW Del Date- 2/28/25) | 2025-02-28 | 2025-02-28
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ110 | OFCI- Receive LV Switchgear (Eaton) (SOW Del Date- 3/30/25) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ111 | OFCI- Receive LV Switchgear (LVS) (Eaton) (SOW Del Date- 2/28/25) | 2025-02-28 | 2025-02-28
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ112 | OFCI- Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ113 | OFCI- Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ114 | OFCI- Receive Main LV Switch Board (MSB) (SOW Del Date- 3/8/2025) | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ115 | OFCI- Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ116 | OFCI- Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ117 | OFCI- Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 7/30/24) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ118 | OFCI- Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 8/30/24) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ119 | OFCI- Receive Medium Voltage Switchgear (MVS) (JDC Power Sys) (SOW Del Date- 10/30/24) | 2024-10-30 | 2024-10-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ120 | OFCI- Receive Packaged Diesel Generator Set (CAT Holt) (SOW Del Date- 5/14/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ121 | OFCI- Receive Packaged Diesel Generator Set (GEN) (CAT Holt) (SOW Del Date- 6/4/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ122 | OFCI- Receive Packaged Diesel Generator Set (GPC) (CAT Holt) (SOW Del Date- 6/26/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ123 | OFCI- Receive Pad Mounted Transformers (XFM-TX) (Del Date- 7/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ124 | OFCI- Receive Pad Mounted Transformers (XMF) (Del Date 10/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3-5 | ROJ | #747474 | ROJ125 | OFCI- Receive PEMB Procurement (1st Del) (Nucor) (SOW Del Date-10/3/24) | 2024-10-03 | 2024-10-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ126 | OFCI- Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 4/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ127 | OFCI- Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 9/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ128 | OFCI- Receive Utility Pad Mount Switchgear (Del Date- 7/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ129 | OFCI- Receive Utility Pad Mount Switchgear (UPM) (Del Date 10/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ130 | OFCI- Receive Utility Pad Mount Switchgear (UPM) (Del Date 8/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ131 | OFCI- Received SUB Warehouse 11/23/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 11/11/23) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ132 | OFCI- Received SUB Warehouse 12/28/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 12/11/23) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ133 | OFCI- Received SUB Warehouse 9/28/2023 UPS System w/ Battery (UPS) (Eaton) (SOW Del Date- 8/13/23) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ134 | OFCI- Reveive Pad Mounted Transformers (XMF) (Del Date 8/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ135 | OFCI- Reveive Power Distribution Units (PDU) (ABB) (SOW Del Date- 7/12/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ136 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ137 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ138 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ139 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ140 | OFCI- UPS System w/ Battery (UPS) (Eaton) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ141 | OFCI- UPS System w/ Battery (UPS) (Eaton) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ142 | OFCI- Utility Pad Mount Switchgear (UPM) Delivered | 2025-02-24 | 2025-02-28
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ143 | OFCI- Utility Pad Mount Switchgear (UPM) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ144 | OFCI- Utility Pad Mount Switchgear (UPM) Delivered | 2025-05-03 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ145 | OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ146 | OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ147 | OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ | 2025-04-29 | 2025-05-03
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-01 | 2025-02-05
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-13 | 2025-02-15
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-15 | 2025-02-18
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-11 | 2025-02-14
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-11 | 2025-02-13
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-13 | 2025-02-15
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-06 | 2025-03-10
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-06 | 2025-03-08
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-08 | 2025-03-11
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-21 | 2025-02-25
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-21 | 2025-02-24
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-24 | 2025-02-26
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-08 | 2025-03-12
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-08 | 2025-03-11
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-11 | 2025-03-13
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-17 | 2025-03-20
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-17 | 2025-03-19
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-19 | 2025-03-21
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-09 | 2025-04-14
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-09 | 2025-04-11
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-11 | 2025-04-15
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-28 | 2025-04-01
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-28 | 2025-03-31
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-31 | 2025-04-02
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-11 | 2025-04-16
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-11 | 2025-04-15
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-15 | 2025-04-17
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-21 | 2025-04-24
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-21 | 2025-04-23
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-23 | 2025-04-25
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-14 | 2025-05-17
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-14 | 2025-05-16
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-16 | 2025-05-19
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-01 | 2025-05-06
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-01 | 2025-05-05
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-05 | 2025-05-07
Fitout | COLO 3 - CELL 1 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-01 | 2025-02-04
Fitout | COLO 3 - CELL 1 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-15 | 2025-02-17
Fitout | COLO 3 - CELL 2 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-11 | 2025-02-13
Fitout | COLO 3 - CELL 2 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-11 | 2025-02-12
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 3 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-06 | 2025-03-08
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-06 | 2025-03-07
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-08 | 2025-03-10
Fitout | CELL 4 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-21 | 2025-02-24
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-21 | 2025-02-22
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-24 | 2025-02-25
Fitout | CELL 1 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-08 | 2025-03-11
Fitout | CELL 1 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-08 | 2025-03-10
Fitout | CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-11 | 2025-03-12
Fitout | CELL 2 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-17 | 2025-03-19
Fitout | CELL 2 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-17 | 2025-03-18
Fitout | CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-19 | 2025-03-20
Fitout | CELL 3 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-09 | 2025-04-11
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-09 | 2025-04-10
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-11 | 2025-04-14
Fitout | CELL 4 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-28 | 2025-03-31
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-28 | 2025-03-29
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-31 | 2025-04-01
Fitout | CELL 1 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-11 | 2025-04-15
Fitout | CELL 1 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-11 | 2025-04-14
Fitout | CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-15 | 2025-04-16
Fitout | CELL 2 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-21 | 2025-04-23
Fitout | CELL 2 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-21 | 2025-04-22
Fitout | CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-23 | 2025-04-24
Fitout | CELL 3 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-14 | 2025-05-16
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-14 | 2025-05-15
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-16 | 2025-05-17
Fitout | CELL 4 Data Hall Fitout Activities | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-01 | 2025-05-05
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-01 | 2025-05-02
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-05 | 2025-05-06
Fitout | COLO 3 - CELL 1 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-01-29 | 2025-01-31
Fitout | COLO 3 - CELL 1 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-11 | 2025-02-12
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-06 | 2025-02-10
Fitout | COLO 3 - CELL 2 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-07 | 2025-02-10
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-11 | 2025-02-12
Fitout | COLO 3 - CELL 3 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-03 | 2025-03-05
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-04 | 2025-03-05
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-06 | 2025-03-07
Fitout | CELL 4 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-18 | 2025-02-20
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-19 | 2025-02-20
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-21 | 2025-02-22
Fitout | CELL 1 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-05 | 2025-03-07
Fitout | CELL 1 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-06 | 2025-03-07
Fitout | CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-08 | 2025-03-10
Fitout | CELL 2 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-13 | 2025-03-15
Fitout | CELL 2 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-14 | 2025-03-15
Fitout | CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-17 | 2025-03-18
Fitout | CELL 3 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-05 | 2025-04-08
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-07 | 2025-04-08
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-09 | 2025-04-10
Fitout | CELL 4 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-25 | 2025-03-27
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-26 | 2025-03-27
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-28 | 2025-03-29
Fitout | CELL 1 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-08 | 2025-04-10
Fitout | CELL 1 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-09 | 2025-04-10
Fitout | CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-11 | 2025-04-14
Fitout | CELL 2 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-17 | 2025-04-19
Fitout | CELL 2 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-18 | 2025-04-19
Fitout | CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-21 | 2025-04-22
Fitout | CELL 3 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-05-10 | 2025-05-13
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-05-12 | 2025-05-13
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-05-14 | 2025-05-15
Fitout | CELL 4 Data Hall Fitout Activities | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-28 | 2025-04-30
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-29 | 2025-04-30
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-05-01 | 2025-05-02
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-04 | 2025-02-05
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-19 | 2025-02-25
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-17 | 2025-02-22
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-08 | 2025-03-10
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-12 | 2025-03-18
Fitout | CELL 4 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-24 | 2025-02-25
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-27 | 2025-03-06
Fitout | CELL 1 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-11 | 2025-03-12
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-14 | 2025-03-20
Fitout | CELL 2 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-19 | 2025-03-20
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-24 | 2025-03-29
Fitout | CELL 3 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-11 | 2025-04-14
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-16 | 2025-04-22
Fitout | CELL 4 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-31 | 2025-04-01
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-03 | 2025-04-09
Fitout | CELL 1 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-15 | 2025-04-16
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-18 | 2025-04-24
Fitout | CELL 2 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-23 | 2025-04-24
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-26 | 2025-05-02
Fitout | CELL 3 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-05-16 | 2025-05-17
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-05-20 | 2025-05-27
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-05-05 | 2025-05-06
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-05-08 | 2025-05-14
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-02-26 | 2025-03-05
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-02-24 | 2025-03-03
Fitout | CELL 3 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-03-19 | 2025-03-26
Fitout | CELL 4 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-03-07 | 2025-03-13
Fitout | CELL 1 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-03-21 | 2025-03-28
Fitout | CELL 2 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-03-31 | 2025-04-05
Fitout | CELL 3 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-04-23 | 2025-04-29
Fitout | CELL 4 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-04-10 | 2025-04-17
Fitout | CELL 1 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-04-25 | 2025-05-01
Fitout | CELL 2 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-05-05 | 2025-05-10
Fitout | CELL 3 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-05-28 | 2025-06-03
Fitout | CELL 4 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-05-15 | 2025-05-21
Fitout | Electrical Room | Paiting | #D6F2FF | T2 | Paint | 2025-02-01 | 2025-02-03
Fitout | Entry Room 1 | Paiting | #D6F2FF | T2 | Paint | 2025-02-04 | 2025-02-05
Fitout | Entry Room 2 | Paiting | #D6F2FF | T2 | Paint | 2025-02-06 | 2025-02-07
Fitout | FCR (Facilities Control Room) | Paiting | #D6F2FF | T2 | Paint | 2025-02-10 | 2025-02-11
Fitout | Fire Riser Room | Paiting | #D6F2FF | T2 | Paint | 2025-02-14 | 2025-02-15
Fitout | Loading Dock | Paiting | #D6F2FF | T2 | Paint | 2025-02-18 | 2025-02-19
Fitout | Restrooms & Janitor Room | Paiting | #D6F2FF | T2 | Paint | 2025-02-15 | 2025-02-17
Fitout | SER (Security Equipment Room) | Paiting | #D6F2FF | T2 | Paint | 2025-02-10 | 2025-02-11
Fitout | STORAGE (High Value & Secure) Rooms | Paiting | #D6F2FF | T2 | Paint | 2025-03-04 | 2025-03-05
Fitout | COLO 3 - CELL 1 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-05 | 2025-02-07
Fitout | COLO 3 - CELL 1 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-05 | 2025-03-06
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-08 | 2025-03-10
Fitout | COLO 3 - CELL 2 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-14 | 2025-02-17
Fitout | COLO 3 - CELL 2 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-15 | 2025-02-17
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-06 | 2025-03-07
Fitout | COLO 3 - CELL 3 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-10 | 2025-03-12
Fitout | CELL 3 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-11 | 2025-03-12
Fitout | CELL 3 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-29 | 2025-03-31
Fitout | CELL 4 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-25 | 2025-02-27
Fitout | CELL 4 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-26 | 2025-02-27
Fitout | CELL 4 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-17 | 2025-03-18
Fitout | CELL 1 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-12 | 2025-03-14
Fitout | CELL 1 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-13 | 2025-03-14
Fitout | CELL 1 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-01 | 2025-04-02
Fitout | CELL 2 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-20 | 2025-03-24
Fitout | CELL 2 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-21 | 2025-03-24
Fitout | CELL 2 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-09 | 2025-04-10
Fitout | CELL 3 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-14 | 2025-04-16
Fitout | CELL 3 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-15 | 2025-04-16
Fitout | CELL 3 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-02 | 2025-05-05
Fitout | CELL 4 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-01 | 2025-04-03
Fitout | CELL 4 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-02 | 2025-04-03
Fitout | CELL 4 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-21 | 2025-04-22
Fitout | CELL 1 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-16 | 2025-04-18
Fitout | CELL 1 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-17 | 2025-04-18
Fitout | CELL 1 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-06 | 2025-05-07
Fitout | CELL 2 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-24 | 2025-04-26
Fitout | CELL 2 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-25 | 2025-04-26
Fitout | CELL 2 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-14 | 2025-05-15
Fitout | CELL 3 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-17 | 2025-05-20
Fitout | CELL 3 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-19 | 2025-05-20
Fitout | CELL 3 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-06-06 | 2025-06-07
Fitout | CELL 4 Data Hall Fitout Activities | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-06 | 2025-05-08
Fitout | CELL 4 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-07 | 2025-05-08
Fitout | CELL 4 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-27 | 2025-05-27
Fitout | COLO 3 - CELL 1 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-02-15 | 2025-02-17
Fitout | COLO 3 - CELL 2 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-02-24 | 2025-02-25
Fitout | COLO 3 - CELL 3 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-03-19 | 2025-03-20
Fitout | CELL 4 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-03-07 | 2025-03-08
Fitout | CELL 1 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-03-21 | 2025-03-24
Fitout | CELL 2 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-03-31 | 2025-04-01
Fitout | CELL 3 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-04-23 | 2025-04-24
Fitout | CELL 4 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-04-10 | 2025-04-11
Fitout | CELL 1 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-04-25 | 2025-04-26
Fitout | CELL 2 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-05-05 | 2025-05-06
Fitout | CELL 3 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-05-28 | 2025-05-29
Fitout | CELL 4 Data Hall Fitout Activities | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-05-15 | 2025-05-16
Site Utilities | Overall | Milestone | #000000 | MLPP | Permanent Power (Need by Date) | 2025-05-05 | 2025-05-05
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Phase 1 Security Pre-Testing Complete | 2025-08-30 | 2025-08-30
Milestones | COLO 4 | Milestone | #000000 | ML21 | Phase 1 Security Pre-Testing Complete | 2025-09-30 | 2025-09-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Phase 1 Security Pre-Testing Complete | 2025-10-31 | 2025-10-31
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Phase 2 Security Pre-Testing Complete | 2025-09-04 | 2025-09-04
Milestones | COLO 4 | Milestone | #000000 | ML21 | Phase 2 Security Pre-Testing Complete | 2025-10-04 | 2025-10-04
Milestones | COLO 5 | Milestone | #000000 | ML21 | Phase 2 Security Pre-Testing Complete | 2025-11-03 | 2025-11-03
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Phase 3 Security Pre-Testing Complete | 2025-09-25 | 2025-09-25
Milestones | COLO 4 | Milestone | #000000 | ML21 | Phase 3 Security Pre-Testing Complete | 2025-10-23 | 2025-10-23
Milestones | COLO 5 | Milestone | #000000 | ML21 | Phase 3 Security Pre-Testing Complete | 2025-11-26 | 2025-11-26
Fitout | Loading Dock | Plumbing | #2A4D4F | GPB | Plumbing | 2025-02-20 | 2025-03-10
Core & Shell | Admin/ COLO 3 | Concrete | #80804A | SOG | Prep / Place SOG | 2024-12-16 | 2024-12-27
Core & Shell | COLO 4 | Concrete | #80804A | SOG | Prep / Place SOG | 2024-12-30 | 2025-01-10
Core & Shell | COLO 5 | Concrete | #80804A | SOG | Prep / Place SOG | 2025-01-14 | 2025-01-25
Early Awards | Milestone | Milestone | #000000 | ML21 | PROCUREMENT- ARL & Subcontractor Awards | 2024-07-16 | 2024-09-27
Early Awards | Milestone | Milestone | #000000 | ML21 | PROCUREMENT- Buyouts & Early Procurement | 2024-07-16 | 2024-09-27
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | PSR (Contract) Executed | 2024-09-30 | 2024-09-30
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | E39 | Pull & Terminate BAS Equipments | 2025-03-25 | 2025-04-02
Fitout | COLO 3 - CELL 2 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-03-21 | 2025-03-31
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-04-15 | 2025-04-23
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-04-02 | 2025-04-10
Fitout | CELL 1 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-04-17 | 2025-04-25
Fitout | CELL 2 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-04-25 | 2025-05-05
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-05-19 | 2025-05-28
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-05-07 | 2025-05-15
Fitout | CELL 1 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-05-21 | 2025-05-30
Fitout | CELL 2 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-05-30 | 2025-06-07
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-06-23 | 2025-07-01
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-06-10 | 2025-06-19
Fitout | Electrical Room | Electrical | #F2F09E | EE24 | Pull Branches From Admin | 2025-03-29 | 2025-04-11
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-03-17 | 2025-03-29
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-04-14 | 2025-04-25
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-04-04 | 2025-04-17
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-05-01 | 2025-05-14
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-05-02 | 2025-05-15
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-05-30 | 2025-06-11
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-05-10 | 2025-05-22
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-03-07 | 2025-03-19
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-06-24 | 2025-07-08
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-05-28 | 2025-06-09
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-07-11 | 2025-07-23
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-06-12 | 2025-06-25
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-03-19 | 2025-04-02
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-03-17 | 2025-03-31
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-04-09 | 2025-04-23
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-03-28 | 2025-04-10
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-04-11 | 2025-04-25
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-04-21 | 2025-05-05
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-14 | 2025-05-28
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-01 | 2025-05-15
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-16 | 2025-05-30
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-27 | 2025-06-07
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-06-18 | 2025-07-01
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-06-05 | 2025-06-19
Fitout | Loading Dock | Electrical | #F2F09E | EE43 | Pull Cables | 2025-03-11 | 2025-03-13
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE44 | Pull Copper for BAS VLAN | 2025-03-21 | 2025-04-04
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE45 | Pull Copper for EPMS VLAN | 2025-02-20 | 2025-03-06
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE46 | Pull Copper for Tahuya VLAN | 2025-03-07 | 2025-03-20
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-03-31 | 2025-04-11
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-04-26 | 2025-05-08
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-04-18 | 2025-04-30
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-05-15 | 2025-05-27
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-05-16 | 2025-05-29
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-06-12 | 2025-06-24
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-05-23 | 2025-06-04
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-04-26 | 2025-05-09
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-07-09 | 2025-07-19
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-06-10 | 2025-06-23
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-07-24 | 2025-08-05
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-06-26 | 2025-07-10
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-03-18 | 2025-03-24
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-03-27 | 2025-04-01
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-04-19 | 2025-04-24
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-04-07 | 2025-04-11
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-04-22 | 2025-04-26
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-04-30 | 2025-05-06
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-05-23 | 2025-05-29
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-05-12 | 2025-05-16
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-05-27 | 2025-05-31
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-06-04 | 2025-06-09
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-06-27 | 2025-07-02
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-06-16 | 2025-06-20
Fitout | Electrical Room | Electrical | #F2F09E | EE29 | Pull Feeders to Admin | 2025-03-12 | 2025-03-28
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE48 | Pull Fiber For BAS VLAN | 2025-03-21 | 2025-04-04
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE49 | Pull Fiber For CEI Network | 2025-04-21 | 2025-05-05
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE50 | Pull Fiber For EPMS VLAN | 2025-02-20 | 2025-03-06
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE51 | Pull Fiber For Tahuya VLAN | 2025-03-07 | 2025-03-20
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE52 | Pull Fiber/Copper For CORPNET Network | 2025-04-05 | 2025-04-19
Fitout | COLO 3 - CELL 2 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-05-13 | 2025-05-23
Fitout | CELL 3 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-06-09 | 2025-06-20
Fitout | CELL 4 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-05-10 | 2025-05-21
Fitout | CELL 1 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-04-17 | 2025-04-28
Fitout | CELL 1 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-05-06 | 2025-05-16
Fitout | CELL 2 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-05-31 | 2025-06-11
Fitout | CELL 3 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-07-22 | 2025-08-02
Fitout | CELL 4 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-06-27 | 2025-07-10
Fitout | CELL 1 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-06-05 | 2025-06-17
Fitout | CELL 2 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-06-28 | 2025-07-11
Fitout | CELL 3 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-08-09 | 2025-08-21
Fitout | CELL 4 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-07-15 | 2025-07-25
Fitout | COLO 3 - CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-03-06 | 2025-03-10
Fitout | COLO 3 - CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-03-14 | 2025-03-18
Fitout | COLO 3 - CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-04-07 | 2025-04-10
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-03-26 | 2025-03-29
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-04-09 | 2025-04-14
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-04-18 | 2025-04-22
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-05-12 | 2025-05-15
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-04-29 | 2025-05-02
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-05-14 | 2025-05-17
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-05-22 | 2025-05-27
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-06-16 | 2025-06-19
Fitout | CELL 4 Data Hall Fitout Activities | HAC's | #FED8E8 | S2 | Raise HACs | 2025-06-03 | 2025-06-06
Milestones | COLO 4 | Milestone | #000000 | ML21 | Ready for Network Install | 2025-09-24 | 2025-09-24
Milestones | COLO 5 | Milestone | #000000 | ML21 | Ready for Network Install | 2025-10-17 | 2025-10-17
Fitout | Admin | Clayco | #C9392A | CL | Remaining Area Punchlist | 2025-03-12 | 2025-03-17
Fitout | Punchlist | Punchlist | #A02B93 | PU1 | Remaining Rooms | 2025-01-27 | 2025-03-17
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- Microsoft Awards CHI11 | 2024-05-06 | 2024-05-10
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- Microsoft Reviews Proposals | 2024-04-15 | 2024-05-02
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- PSR Executed (Early Works) | 2024-06-06 | 2024-06-06
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- PSR Executed (Full GMP) | 2024-09-30 | 2024-09-30
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- RFP Issued (Revised 3.21.24) and Proposal Due to MSFT | 2024-03-25 | 2024-04-12
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | RNI | 2025-08-20 | 2025-08-20
Fitout | Loading Dock | Milestone | #000000 | ML21 | Rough-in | 2025-01-31 | 2025-01-31
Fitout | Electrical Room | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-01-27 | 2025-01-27
Fitout | Entry Room 1 | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-01-29 | 2025-01-29
Fitout | Entry Room 2 | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-01-31 | 2025-01-31
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-02-03 | 2025-02-03
Fitout | Fire Riser Room | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-02-11 | 2025-02-11
Fitout | SER (Security Equipment Room) | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-02-05 | 2025-02-05
Milestones | COLO 5 | Milestone | #000000 | ML21 | Secuirty Lockdown | 2025-12-04 | 2025-12-04
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Security Lockdown | 2025-10-02 | 2025-10-02
Milestones | COLO 4 | Milestone | #000000 | ML21 | Security Lockdown | 2025-11-06 | 2025-11-06
Fitout | Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipment in Admin | 2025-03-03 | 2025-03-11
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-10 | 2025-03-15
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-17 | 2025-03-20
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-14 | 2025-03-18
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-03 | 2025-03-06
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-31 | 2025-04-03
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-26 | 2025-03-29
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-04-18 | 2025-04-22
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-04-05 | 2025-04-09
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-04-21 | 2025-05-01
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-04-29 | 2025-05-02
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-05-22 | 2025-05-27
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-05-10 | 2025-05-14
Fitout | Entry Room 1 | Electrical | #F2F09E | EE54 | Set ER-1 Equipment | 2025-02-11 | 2025-02-14
Fitout | Entry Room 2 | Electrical | #F2F09E | EE55 | Set ER-2 Equipment | 2025-02-13 | 2025-02-17
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE56 | Set FCR Equipment | 2025-02-15 | 2025-02-19
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-03-14 | 2025-03-18
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-03-12 | 2025-03-15
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-04-04 | 2025-04-08
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-03-24 | 2025-03-27
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-04-07 | 2025-04-10
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-04-16 | 2025-04-19
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-05-09 | 2025-05-13
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-04-26 | 2025-04-30
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-05-12 | 2025-05-15
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-05-20 | 2025-05-23
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-06-12 | 2025-06-17
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-05-31 | 2025-06-04
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-02-27 | 2025-03-04
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-03-08 | 2025-03-12
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-04-01 | 2025-04-04
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-03-19 | 2025-03-24
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-04-03 | 2025-04-07
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-04-11 | 2025-04-16
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-05-06 | 2025-05-09
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-04-23 | 2025-04-26
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-05-08 | 2025-05-12
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-05-16 | 2025-05-20
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-06-09 | 2025-06-12
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE7 | Set PDUs | 2025-05-28 | 2025-05-31
Fitout | SER (Security Equipment Room) | HAC's | #FED8E8 | S3 | Set SER Room Equipment | 2025-02-15 | 2025-02-19
Site Prep/ Mobilization | Milestone | Milestone | #000000 | ML21 | Set-Up Trailers & Install Temp Utilities | 2024-07-25 | 2024-08-08
Site Prep/ Mobilization | Milestone | Milestone | #000000 | ML21 | Site Mobilization | 2024-07-24 | 2024-07-24
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start First ROJ - CLAYCO Took over Storage 9/2/2024 | 2024-09-05 | 2024-09-05
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start First ROJ CLAYCO Took over Storage 9/2/2024 | 2024-09-05 | 2024-09-05
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start First ROJ CLAYCO Took over Storage 9/2/2024 | 2024-09-05 | 2024-09-05
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start Foundation | 2024-09-19 | 2024-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L1 CX | 2025-04-09 | 2025-04-09
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L1 CX | 2025-04-23 | 2025-04-23
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L1 CX | 2025-04-21 | 2025-04-21
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L2 CX (Yellow Tag) | 2025-05-05 | 2025-05-05
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L2 CX (Yellow Tag) | 2025-05-06 | 2025-05-06
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L2 CX (Yellow Tag) | 2025-06-05 | 2025-06-05
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L3 CX | 2025-06-20 | 2025-06-20
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L3 CX | 2025-07-19 | 2025-07-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L3 CX (Green Tag) | 2025-06-04 | 2025-06-04
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L4 Cx (Blue Tag) | 2025-08-15 | 2025-08-15
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L4 Cx (Blue Tag) | 2025-09-20 | 2025-09-20
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L4 Cx (Blue Tag) | 2025-10-17 | 2025-10-17
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L5 Cx (White Tag) | 2025-09-16 | 2025-09-16
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L5 Cx (White Tag) | 2025-10-17 | 2025-10-17
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L5 Cx (White Tag) | 2025-11-17 | 2025-11-17
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start Superstructure | 2024-09-19 | 2024-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start Superstructure | 2024-11-02 | 2024-11-02
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start Superstructure | 2024-11-14 | 2024-11-14
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-03 | 2025-07-18
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-25 | 2025-08-08
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-10 | 2025-07-23
Commissioning | CELL 1 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-16 | 2025-07-30
Commissioning | CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-21 | 2025-08-04
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-30 | 2025-09-15
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-12 | 2025-08-26
Commissioning | CELL 1 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-13 | 2025-08-27
Commissioning | CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-19 | 2025-09-02
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-09-20 | 2025-10-04
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-28 | 2025-09-12
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Substantial Completion | 2025-10-01 | 2025-10-01
Milestones | COLO 4 | Milestone | #000000 | ML21 | Substantial Completion | 2025-10-29 | 2025-10-29
Milestones | COLO 5 | Milestone | #000000 | ML21 | Substantial Completion | 2025-12-02 | 2025-12-02
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | TCO / C of O | 2025-09-30 | 2025-09-30
Milestones | COLO 4 | Milestone | #000000 | ML21 | TCO / C of O | 2025-10-29 | 2025-10-29
Milestones | COLO 5 | Milestone | #000000 | ML21 | TCO / C of O | 2025-12-02 | 2025-12-02
Fitout | Electrical Room | Electrical | #F2F09E | EE58 | Terminate Electrical / Mechanical Equipment | 2025-04-14 | 2025-04-17
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-03-31 | 2025-04-03
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-04-26 | 2025-04-30
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-05-23 | 2025-05-28
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-03-20 | 2025-03-25
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-04-18 | 2025-04-22
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-05-15 | 2025-05-19
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-07-09 | 2025-07-12
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-06-10 | 2025-06-13
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-05-16 | 2025-05-20
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-06-12 | 2025-06-17
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-07-24 | 2025-07-29
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-06-26 | 2025-06-30
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-03 | 2025-04-07
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-01 | 2025-04-04
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-24 | 2025-04-28
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-11 | 2025-04-16
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-26 | 2025-04-30
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-05-06 | 2025-05-09
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-05-29 | 2025-06-02
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-05-16 | 2025-05-20
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-05-31 | 2025-06-04
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-06-09 | 2025-06-12
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-07-02 | 2025-07-08
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-06-20 | 2025-06-24
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE61 | Terminate MV Gear - Cell 1 | 2025-05-30 | 2025-06-03
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE61 | Terminate MV Gear - Cell 2 | 2025-06-04 | 2025-06-07
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE61 | Terminate MV Gear - Cell 3 | 2025-06-13 | 2025-06-18
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE61 | Terminate MV Gear - Cell 4 | 2025-06-09 | 2025-06-12
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-04-14 | 2025-04-16
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-05-09 | 2025-05-12
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-06-05 | 2025-06-07
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-05-10 | 2025-05-13
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-05-01 | 2025-05-05
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-05-28 | 2025-05-30
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-07-18 | 2025-07-21
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-06-24 | 2025-06-26
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-06-02 | 2025-06-04
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-06-25 | 2025-06-27
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-08-06 | 2025-08-08
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-07-11 | 2025-07-14
Fitout | Electrical Room | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-01-24 | 2025-01-25
Fitout | Entry Room 1 | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-01-27 | 2025-01-28
Fitout | Entry Room 2 | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-01-29 | 2025-01-30
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-01-31 | 2025-02-01
Fitout | Fire Riser Room | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-07 | 2025-02-10
Fitout | Loading Dock | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-13 | 2025-02-14
Fitout | Restrooms & Janitor Room | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-11 | 2025-02-12
Fitout | SER (Security Equipment Room) | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-03 | 2025-02-04
Fitout | STORAGE (High Value & Secure) Rooms | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-05 | 2025-02-06
Core & Shell | Admin/ COLO 3 | Plumbing | #2A4D4F | GPC | UG MEP Work (Plumbing) | 2024-11-14 | 2024-12-14
Core & Shell | COLO 4 | Plumbing | #2A4D4F | GPC | UG MEP Work (Plumbing) | 2024-12-04 | 2024-12-27
Core & Shell | COLO 5 | Plumbing | #2A4D4F | GPC | UG MEP Work (Plumbing) | 2024-12-17 | 2025-01-13
Core & Shell | Admin/ COLO 3 | Plumbing | #2A4D4F | GPD | Weather Days | 2024-12-30 | 2025-01-16
Milestones | COLO 4 | Milestone | #000000 | ML21 | Weather Tight | 2025-01-30 | 2025-01-30
Milestones | Key Milestone | Milestone | #000000 | ML21 | TBD | 2024-03-25 | 2024-09-30

## CFA - Schedule
|  | 2024 | [239 empty] | 2025
|  | May | [25 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov
|  | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15
phase | location | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Milestones | Admin/ COLO 3 | Sep 05: ML21; Sep 19: ML21; Sep 30: ML21; Oct 11: ML21; Dec 14: ML21; Dec 26: ML21; Dec 27: ML21; Jan 16: ML21; Feb 25: ML21; Mar 05: ML21; Mar 08: ML21; Mar 15: ML21; Apr 09: ML21; May 05: ML21; Jun 04: ML21; Jul 02: ML21; Aug 14: ML1; Aug 15: ML21; Aug 20: ML21; Aug 30: ML21; Sep 04: ML21; Sep 15: ML21; Sep 16: ML21; Sep 18: ML0; Sep 25: ML21; Sep 30: ML21; Oct 01: ML4; Oct 02: ML21
[138 empty] | ML21 | [10 empty] | ML21 | [74 empty] | ML21 | [141 empty] | ML21 | [29 empty] | ML21 | [70 empty] | ML6 | [15 empty] | ML21 | [31 empty] | ML21 | ML21
[138 empty] | ML21 | [85 empty] | ML21 | [242 empty] | ML8 | [15 empty] | ML21
[467 empty] | ML9 | [15 empty] | ML21
ML10
ML11
ML12
ML13
ML16
ML19
ML21
ML21
ML21
ML21
ML21
| COLO 4 | Sep 05: ML21; Sep 16: ML21; Oct 31: ML21; Nov 02: ML21; Dec 27: ML21; Dec 31: ML21; Jan 10: ML21; Jan 30: ML21; Mar 30: ML21; Apr 23: ML21; Apr 24: ML21; May 05: ML21; May 06: ML21; Jun 20: ML21; Jul 19: ML21; Aug 14: ML21; Sep 19: ML2; Sep 20: ML21; Sep 24: ML21; Sep 30: ML21; Oct 04: ML21; Oct 16: ML21; Oct 17: ML21; Oct 20: ML21; Oct 23: ML21; Oct 29: ML21; Nov 06: ML21
[503 empty] | ML5 | [10 empty] | ML21 | [28 empty] | ML21 | [7 empty] | ML21
[503 empty] | ML14 | [10 empty] | ML21
[503 empty] | ML18 | [10 empty] | ML21
ML21
ML21
ML21
ML21
ML21
ML21
ML21
ML21
| COLO 5 | Sep 05: ML21; Sep 09: ML21; Nov 12: ML21; Nov 14: ML21; Jan 13: ML21; Jan 15: ML21; Jan 25: ML21; Feb 14: ML21; Mar 31: ML21; Apr 21: ML21; May 05: ML21; May 31: ML21; Jun 05: ML21; Jul 19: ML21; Aug 05: ML21; Sep 03: ML21; Oct 11: ML3; Oct 17: ML21; Oct 31: ML21; Nov 03: ML21; Nov 15: ML21
[525 empty] | ML7 | [5 empty] | ML21 | [13 empty] | ML21
[525 empty] | ML15 | [19 empty] | ML21
[525 empty] | ML17 | [19 empty] | ML21
ML20
ML21
ML21
ML21
ML21
ML21
ML21
| General | Sep 16: ML21
| Key Milestone | Aug 21: ML21; Sep 05: ML21; Sep 10: ML21; Nov 12: ML21; Dec 03: ML21; Dec 26: ML21; Dec 31: ML21; Jan 15: ML21; May 05: ML21
| Milestone | Sep 09: ML21; Sep 10: ML21; Sep 11: ML21; Sep 12: ML21; Sep 13: ML21; Sep 14: ML21; Sep 15: ML21; Sep 16: ML21; Sep 17: ML21; Sep 18: ML21; Sep 19: ML21; Sep 20: ML21; Sep 21: ML21; Sep 22: ML21; Sep 23: ML21; Sep 24: ML21; Sep 25: ML21; Sep 26: ML21; Sep 27: ML21; Sep 28: ML21; Sep 29: ML21; Sep 30: ML21; Oct 01: ML21; Oct 02: ML21; Oct 03: ML21; Oct 04: ML21; Oct 05: ML21; Oct 06: ML21; Oct 07: ML21; Oct 08: ML21; Oct 09: ML21; Oct 10: ML21; Oct 11: ML21; Oct 12: ML21; Oct 13: ML21; Oct 14: ML21; Oct 15: ML21; Oct 16: ML21; Oct 17: ML21; Oct 18: ML21; Oct 19: ML21; Oct 20: ML21; Oct 21: ML21; Oct 22: ML21; Oct 23: ML21; Oct 24: ML21; Oct 25: ML21; Oct 26: ML21; Oct 27: ML21; Oct 28: ML21; Oct 29: ML21; Oct 30: ML21; Oct 31: ML21; Nov 01: ML21; Nov 02: ML21; Oct 01: ML1
BIM | BIM | Jul 18: BIM; Jul 19: BIM; Jul 20: BIM; Jul 21: BIM; Jul 22: BIM; Jul 23: BIM; Jul 24: BIM; Jul 25: BIM; Jul 26: BIM; Jul 27: BIM; Jul 28: BIM; Jul 29: BIM; Jul 30: BIM; Jul 31: BIM; Aug 01: BIM; Aug 02: BIM; Aug 03: BIM; Aug 04: BIM; Aug 05: BIM; Aug 06: BIM; Aug 07: BIM; Aug 08: BIM; Aug 09: BIM; Aug 10: BIM; Aug 11: BIM; Aug 12: BIM; Aug 13: BIM; Aug 14: BIM; Aug 15: BIM; Aug 16: BIM; Aug 17: BIM; Sep 06: BIM; Sep 07: BIM; Sep 08: BIM; Sep 09: BIM; Sep 10: BIM; Sep 11: BIM; Sep 12: BIM; Sep 13: BIM; Sep 14: BIM; Sep 15: BIM; Sep 16: BIM; Sep 17: BIM; Sep 18: BIM; Sep 19: BIM; Sep 20: BIM; Sep 21: BIM; Sep 22: BIM; Sep 23: BIM; Sep 24: BIM; Sep 25: BIM; Sep 26: BIM; Sep 27: BIM; Sep 28: BIM; Sep 29: BIM; Sep 30: BIM; Oct 01: BIM; Oct 02: BIM; Oct 03: BIM; Oct 04: BIM; Oct 05: BIM; Oct 06: BIM; Oct 07: BIM; Oct 08: BIM; Oct 09: BIM; Oct 10: BIM; Oct 11: BIM; Oct 12: BIM
CFCI Procurement | CFCI | Oct 31: CFCI; Nov 01: CFCI; Nov 02: CFCI; Nov 03: CFCI; Nov 04: CFCI; Nov 05: CFCI; Nov 06: CFCI; Nov 07: CFCI; Nov 08: CFCI; Nov 09: CFCI; Nov 10: CFCI; Nov 11: CFCI; Nov 12: CFCI; Nov 13: CFCI; Nov 14: CFCI; Nov 15: CFCI; Nov 16: CFCI; Nov 17: CFCI; Nov 18: CFCI; Nov 19: CFCI; Nov 20: CFCI; Nov 21: CFCI; Nov 22: CFCI; Nov 23: CFCI; Nov 24: CFCI; Nov 25: CFCI; Nov 26: CFCI; Nov 27: CFCI; Nov 28: CFCI; Nov 29: CFCI; Nov 30: CFCI; Dec 01: CFCI; Dec 02: CFCI; Dec 03: CFCI; Dec 04: CFCI; Dec 05: CFCI; Dec 06: CFCI; Dec 07: CFCI; Dec 08: CFCI; Dec 09: CFCI; Dec 10: CFCI; Dec 11: CFCI; Dec 12: CFCI; Dec 13: CFCI; Dec 14: CFCI; Dec 15: CFCI; Dec 16: CFCI; Dec 17: CFCI; Dec 18: CFCI; Dec 19: CFCI; Dec 20: CFCI; Dec 21: CFCI; Dec 22: CFCI; Dec 23: CFCI; Dec 24: CFCI; Dec 25: CFCI; Dec 26: CFCI; Dec 27: CFCI; Dec 28: CFCI; Dec 29: CFCI; Dec 30: CFCI; Dec 31: CFCI; Jan 01: CFCI; Jan 02: CFCI; Jan 03: CFCI; Jan 04: CFCI; Jan 05: CFCI; Jan 06: CFCI; Jan 07: CFCI; Jan 08: CFCI; Jan 09: CFCI; Jan 10: CFCI; Jan 11: CFCI; Jan 12: CFCI; Jan 13: CFCI; Jan 14: CFCI; Jan 15: CFCI; Jan 16: CFCI; Jan 17: CFCI; Jan 18: CFCI; Jan 19: CFCI; Jan 20: CFCI; Jan 21: CFCI; Jan 22: CFCI; Jan 23: CFCI; Jan 24: CFCI; Jan 25: CFCI; Jan 26: CFCI; Jan 27: CFCI; Jan 28: CFCI; Jan 29: CFCI; Jan 30: CFCI; Jan 31: CFCI; Feb 01: CFCI; Feb 02: CFCI; Feb 03: CFCI; Feb 04: CFCI; Feb 05: CFCI; Feb 06: CFCI; Feb 07: CFCI; Feb 08: CFCI; Feb 09: CFCI; Feb 10: CFCI; Feb 11: CFCI; Feb 12: CFCI; Feb 13: CFCI; Feb 14: CFCI; Feb 15: CFCI; Feb 16: CFCI; Feb 17: CFCI; Feb 18: CFCI; Feb 19: CFCI; Feb 20: CFCI; Feb 21: CFCI; Feb 22: CFCI; Feb 23: CFCI; Feb 24: CFCI; Feb 25: CFCI; Feb 26: CFCI; Feb 27: CFCI; Feb 28: CFCI; Mar 01: CFCI; Mar 02: CFCI; Mar 03: CFCI
[180 empty] | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI
[110 empty] | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI
[109 empty] | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI | CFCI
Commissioning | CELL 1 Energizations & Startups (Level 3) | Jun 20: EE33; Jun 21: EE33; Jun 22: EE33; Jun 23: EE33; Jun 24: EE33; Jun 25: EE33; Jun 26: EE33; Jun 27: EE33; Jun 28: EE33; Jun 30: EE34; Jul 01: EE34; Jul 02: EE34; Jul 03: EE34; Jul 04: EE34; Jul 05: EE34; Jul 06: EE34; Jul 07: EE34; Jul 08: EE34; Jul 09: EE34; Jul 10: EE34; Jul 11: Cx1; Jul 12: Cx1; Jul 13: Cx1; Jul 14: Cx1; Jul 15: Cx1; Jul 19: EE33; Jul 20: EE33; Jul 21: EE33; Jul 22: EE33; Jul 23: EE33; Jul 24: EE33; Jul 25: EE33; Jul 26: EE33; Jul 27: EE33; Jul 28: EE33; Jul 29: EE33; Jul 30: EE34; Jul 31: EE34; Aug 01: EE34; Aug 02: EE34; Aug 03: EE34; Aug 04: EE34; Aug 05: EE34; Aug 06: EE34; Aug 07: EE34; Aug 08: Cx1; Aug 09: Cx1; Aug 10: Cx1; Aug 11: Cx1; Aug 12: Cx1; Aug 13: Cx3; Aug 14: Cx3; Aug 15: Cx3; Aug 16: Cx3; Aug 17: Cx3; Aug 18: Cx3; Aug 19: Cx3; Aug 20: Cx3; Aug 21: Cx3; Aug 22: Cx3; Aug 23: Cx3; Aug 24: Cx3; Aug 25: Cx3; Aug 26: Cx3; Aug 27: Cx3; Aug 28: E39; Aug 29: E39; Aug 30: E39; Aug 31: E39; Sep 01: E39; Sep 02: E39
[438 empty] | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | E39 | E39 | E39 | E39 | E39
| CELL 2 Energizations & Startups (Level 3) | Jun 25: EE33; Jun 26: EE33; Jun 27: EE33; Jun 28: EE33; Jun 29: EE33; Jun 30: EE33; Jul 01: EE33; Jul 02: EE33; Jul 03: EE33; Jul 07: EE34; Jul 08: EE34; Jul 09: EE34; Jul 10: EE34; Jul 11: EE34; Jul 12: EE34; Jul 13: EE34; Jul 14: EE34; Jul 15: EE34; Jul 16: Cx1; Jul 17: Cx1; Jul 18: Cx1; Jul 19: Cx1; Jul 24: EE33; Jul 25: EE33; Jul 26: EE33; Jul 27: EE33; Jul 28: EE33; Jul 29: EE33; Jul 30: EE33; Jul 31: EE33; Aug 01: EE33; Aug 02: EE33; Aug 04: EE34; Aug 05: EE34; Aug 06: EE34; Aug 07: EE34; Aug 08: EE34; Aug 09: EE34; Aug 10: EE34; Aug 11: EE34; Aug 12: EE34; Aug 13: Cx1; Aug 14: Cx1; Aug 15: Cx1; Aug 16: Cx1; Aug 17: Cx1; Aug 18: Cx1; Aug 19: Cx3; Aug 20: Cx3; Aug 21: Cx3; Aug 22: Cx3; Aug 23: Cx3; Aug 24: Cx3; Aug 25: Cx3; Aug 26: Cx3; Aug 27: Cx3; Aug 28: Cx3; Aug 29: Cx3; Aug 30: Cx3; Aug 31: Cx3; Sep 01: Cx3; Sep 02: Cx3; Sep 03: E39; Sep 04: E39; Sep 05: E39; Sep 06: E39; Sep 07: E39; Sep 08: E39
[443 empty] | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | E39 | E39 | E39 | E39
| CELL 3 Energizations & Startups (Level 3) | Jun 24: EE33; Jun 25: EE33; Jun 26: EE33; Jun 27: EE33; Jun 28: EE33; Jun 29: EE33; Jun 30: EE33; Jul 01: EE33; Jul 02: EE33; Jul 03: EE33; Jul 04: EE33; Jul 05: EE33; Jul 06: EE33; Jul 07: EE33; Jul 08: EE34; Jul 09: EE34; Jul 10: EE34; Jul 11: EE34; Jul 12: EE34; Jul 13: EE34; Jul 14: EE34; Jul 15: EE34; Jul 16: EE34; Jul 17: EE34; Jul 18: EE34; Jul 19: Cx1; Jul 20: Cx1; Jul 21: Cx1; Jul 22: Cx1; Jul 23: Cx1; Jul 24: Cx1; Aug 06: EE33; Aug 07: EE33; Aug 08: EE33; Aug 09: EE33; Aug 10: EE33; Aug 11: EE33; Aug 12: EE33; Aug 13: EE33; Aug 14: EE33; Aug 25: EE33; Aug 26: EE33; Aug 27: EE33; Aug 28: EE33; Aug 29: EE33; Aug 30: EE33; Aug 31: EE33; Sep 01: EE33; Sep 02: EE33; Sep 03: EE33; Sep 04: EE34; Sep 05: EE34; Sep 06: EE34; Sep 07: EE34; Sep 08: EE34; Sep 09: EE34; Sep 10: EE34; Sep 11: EE34; Sep 12: EE34; Sep 13: EE34; Sep 15: Cx1; Sep 16: Cx1; Sep 17: Cx1; Sep 18: Cx1; Sep 19: Cx1; Sep 20: Cx3; Sep 21: Cx3; Sep 22: Cx3; Sep 23: Cx3; Sep 24: Cx3; Sep 25: Cx3; Sep 26: Cx3; Sep 27: Cx3; Sep 28: Cx3; Sep 29: Cx3; Sep 30: Cx3; Oct 01: Cx3; Oct 02: Cx3; Oct 03: Cx3; Oct 04: Cx3; Oct 06: E39; Oct 07: E39; Oct 08: E39; Oct 09: E39; Oct 10: E39; Oct 11: E39
[447 empty] | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | E39 | E39 | E39 | E39 | E39 | E39 | EE34 | EE34 | EE34 | EE34 | EE34 | EE34 | EE34 | EE34 | EE34 | EE34 | EE34 | Cx1 | Cx1 | Cx1 | Cx1 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | E39 | E39 | E39 | E39
| CELL 4 Energizations & Startups (Level 3) | Jun 13: EE33; Jun 14: EE33; Jun 15: EE33; Jun 16: EE33; Jun 17: EE33; Jun 18: EE33; Jun 19: EE33; Jun 20: EE33; Jun 21: EE33; Jun 22: EE33; Jun 23: EE33; Jun 24: EE34; Jun 25: EE34; Jun 26: EE34; Jun 27: EE34; Jun 28: EE34; Jun 29: EE34; Jun 30: EE34; Jul 01: EE34; Jul 02: EE34; Jul 03: Cx1; Jul 04: Cx1; Jul 05: Cx1; Jul 06: Cx1; Jul 07: Cx1; Jul 08: Cx1; Jul 09: Cx1; Jul 18: EE33; Jul 19: EE33; Jul 20: EE33; Jul 21: EE33; Jul 22: EE33; Jul 23: EE33; Jul 24: EE33; Jul 25: EE33; Jul 26: EE33; Jul 27: EE33; Jul 28: EE33; Aug 04: EE33; Aug 05: EE33; Aug 06: EE33; Aug 07: EE33; Aug 08: EE33; Aug 09: EE33; Aug 10: EE33; Aug 11: EE33; Aug 12: EE33; Aug 13: EE34; Aug 14: EE34; Aug 15: EE34; Aug 16: EE34; Aug 17: EE34; Aug 18: EE34; Aug 19: EE34; Aug 20: EE34; Aug 21: EE34; Aug 22: EE34; Aug 23: Cx1; Aug 24: Cx1; Aug 25: Cx1; Aug 26: Cx1; Aug 27: Cx1; Sep 13: E39; Sep 14: E39; Sep 15: E39; Sep 16: E39; Sep 17: E39
[432 empty] | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | E39 | E39 | E39 | E39 | E39 | E39 | EE34 | EE34 | EE34 | EE34 | EE34 | EE34 | EE34 | EE34 | Cx1 | Cx1 | Cx1 | Cx1 | Cx1 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | E39 | E39 | E39 | E39
[481 empty] | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3 | Cx3
| COLO 3 | May 05: L2; May 06: L2; May 07: L2; May 08: L2; May 09: L2; May 10: L2; May 11: L2; May 12: L2; May 13: L2; May 14: L2; May 15: L2; May 16: L2; May 17: L2; May 18: L2; May 19: L2; May 20: L2; May 21: L2; May 22: L2; May 23: L2; May 24: L2; May 25: L2; May 26: L2; May 27: L2; May 28: L2; Jun 09: L2; Jun 10: L2; Jun 11: L2; Jun 12: L2; Jun 13: L2; Jun 14: L2; Jun 15: L2; Jun 16: L2; Jun 17: L2; Jun 18: L2; Jun 19: L2; Jun 20: L2; Jun 21: L2; Jun 22: L2; Jun 23: L2; Jun 24: L2; Jun 25: L2; Jun 26: L2; Jun 27: L2; Jun 28: L2; Jun 29: L2; Jun 30: L2; Jul 01: L2; Jul 02: L2; Jul 15: L3; Jul 16: L3; Jul 17: L3; Jul 18: L3; Aug 15: 4&5; Aug 16: 4&5; Aug 17: 4&5; Aug 18: 4&5; Aug 19: 4&5; Aug 20: 4&5; Aug 21: 4&5; Aug 22: 4&5; Aug 23: 4&5; Aug 24: 4&5; Aug 25: 4&5; Aug 26: 4&5; Aug 27: 4&5; Aug 28: 4&5; Aug 29: 4&5; Aug 30: 4&5; Aug 31: 4&5; Sep 01: 4&5; Sep 02: 4&5; Sep 03: 4&5; Sep 04: 4&5; Sep 05: 4&5; Sep 06: 4&5; Sep 07: 4&5; Sep 08: 4&5; Sep 09: 4&5; Sep 10: 4&5; Sep 11: 4&5; Sep 12: 4&5; Sep 13: 4&5; Sep 14: 4&5; Sep 15: 4&5; Sep 16: 4&5; Sep 17: 4&5; Sep 18: 4&5
[376 empty] | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | [16 empty] | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3
[388 empty] | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2
[405 empty] | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3 | L3
[404 empty] | L3 | L3 | L3 | L3 | L3 | L3 | L3
| COLO 3 - CELL 1 Energizations & Startups (Level 3) | Jun 04: EE33; Jun 05: EE33; Jun 06: EE33; Jun 07: EE33; Jun 08: EE33; Jun 09: EE33; Jun 10: EE33; Jun 11: EE33; Jun 12: EE33
| COLO 3 - CELL 2 Energizations & Startups (Level 3) | Jun 09: EE33; Jun 10: EE33; Jun 11: EE33; Jun 12: EE33; Jun 13: EE33; Jun 14: EE33; Jun 15: EE33; Jun 16: EE33; Jun 17: EE33; Jun 18: EE33; Jun 19: EE34; Jun 20: EE34; Jun 21: EE34; Jun 22: EE34; Jun 23: EE34; Jun 24: EE34; Jun 25: EE34; Jun 26: EE34; Jun 27: EE34; Jun 28: Cx1; Jun 29: Cx1; Jun 30: Cx1; Jul 01: Cx1; Jul 02: Cx1; Jul 03: Cx3; Jul 04: Cx3; Jul 05: Cx3; Jul 06: Cx3; Jul 07: Cx3; Jul 08: Cx3; Jul 09: Cx3; Jul 10: Cx3; Jul 11: Cx3; Jul 12: Cx3; Jul 13: Cx3; Jul 14: Cx3; Jul 15: Cx3; Jul 16: Cx3; Jul 17: Cx3; Jul 18: Cx3; Jul 19: E39; Jul 20: E39; Jul 21: E39; Jul 22: E39; Jul 23: E39
| COLO 4 | May 06: L2; May 07: L2; May 08: L2; May 09: L2; May 10: L2; May 11: L2; May 12: L2; May 13: L2; May 14: L2; May 15: L2; May 16: L2; May 17: L2; May 18: L2; May 19: L2; May 20: L2; May 21: L2; May 22: L2; May 23: L2; May 24: L2; May 25: L2; May 26: L2; May 27: L2; May 28: L2; May 29: L2; May 31: L2; Jun 01: L2; Jun 02: L2; Jun 03: L2; Jun 04: L2; Jun 05: L2; Jun 06: L2; Jun 07: L2; Jun 08: L2; Jun 09: L2; Jun 10: L2; Jun 11: L2; Jun 12: L2; Jun 13: L2; Jun 14: L2; Jun 15: L2; Jun 16: L2; Jun 17: L2; Jun 18: L2; Jun 19: L2; Jun 20: L2; Jun 21: L2; Jun 22: L2; Jun 23: L2; Jun 24: L2; Jul 22: L2; Jul 23: L2; Jul 24: L2; Jul 25: L2; Jul 26: L2; Jul 27: L2; Jul 28: L2; Jul 29: L2; Jul 30: L2; Jul 31: L2; Aug 01: L2; Aug 02: L2; Aug 03: L2; Aug 04: L2; Aug 05: L2; Aug 06: L2; Aug 07: L2; Aug 08: L2; Aug 09: L2; Aug 10: L2; Aug 11: L2; Aug 12: L2; Aug 13: L2; Aug 14: L2; Sep 20: 4&5; Sep 21: 4&5; Sep 22: 4&5; Sep 23: 4&5; Sep 24: 4&5; Sep 25: 4&5; Sep 26: 4&5; Sep 27: 4&5; Sep 28: 4&5; Sep 29: 4&5; Sep 30: 4&5; Oct 01: 4&5; Oct 02: 4&5; Oct 03: 4&5; Oct 04: 4&5; Oct 05: 4&5; Oct 06: 4&5; Oct 07: 4&5; Oct 08: 4&5; Oct 09: 4&5; Oct 10: 4&5; Oct 11: 4&5; Oct 12: 4&5; Oct 13: 4&5; Oct 14: 4&5; Oct 15: 4&5; Oct 16: 4&5; Oct 17: 4&5; Oct 18: 4&5; Oct 19: 4&5; Oct 20: 4&5
[419 empty] | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2
| COLO 5 | Jun 05: L2; Jun 06: L2; Jun 07: L2; Jun 08: L2; Jun 09: L2; Jun 10: L2; Jun 11: L2; Jun 12: L2; Jun 13: L2; Jun 14: L2; Jun 15: L2; Jun 16: L2; Jun 17: L2; Jun 18: L2; Jun 19: L2; Jun 20: L2; Jun 21: L2; Jun 22: L2; Jun 23: L2; Jun 24: L2; Jun 25: L2; Jun 26: L2; Jun 27: L2; Jun 28: L2; Aug 09: L2; Aug 10: L2; Aug 11: L2; Aug 12: L2; Aug 13: L2; Aug 14: L2; Aug 15: L2; Aug 16: L2; Aug 17: L2; Aug 18: L2; Aug 19: L2; Aug 20: L2; Aug 21: L2; Aug 22: L2; Aug 23: L2; Aug 24: L2; Aug 25: L2; Aug 26: L2; Aug 27: L2; Aug 28: L2; Aug 29: L2; Aug 30: L2; Aug 31: L2; Sep 01: L2; Sep 02: L2; Sep 03: L2; Oct 17: 4&5; Oct 18: 4&5; Oct 19: 4&5; Oct 20: 4&5; Oct 21: 4&5; Oct 22: 4&5; Oct 23: 4&5; Oct 24: 4&5; Oct 25: 4&5; Oct 26: 4&5; Oct 27: 4&5; Oct 28: 4&5; Oct 29: 4&5; Oct 30: 4&5; Oct 31: 4&5; Nov 01: 4&5; Nov 02: 4&5; Nov 03: 4&5; Nov 04: 4&5; Nov 05: 4&5; Nov 06: 4&5; Nov 07: 4&5; Nov 08: 4&5; Nov 09: 4&5; Nov 10: 4&5; Nov 11: 4&5; Nov 12: 4&5; Nov 13: 4&5; Nov 14: 4&5; Nov 15: 4&5
[420 empty] | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2
[437 empty] | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2 | L2
Core & Shell | Admin/ COLO 3 | Oct 21: J38; Oct 22: J38; Oct 23: J38; Oct 24: J38; Oct 25: J38; Oct 26: J38; Oct 27: J38; Oct 28: J38; Oct 29: J38; Oct 30: J38; Oct 31: J38; Nov 01: J38; Nov 02: J38; Nov 03: J38; Nov 04: J38; Nov 05: J38; Nov 06: J38; Nov 07: J38; Nov 08: J40; Nov 09: J40; Nov 10: J40; Nov 11: J40; Nov 12: J40; Nov 13: J40; Nov 14: J40; Nov 15: J40; Nov 16: J40; Nov 17: J40; Nov 18: J40; Nov 19: J40; Nov 20: J40; Nov 21: J40; Nov 22: J40; Nov 23: J40; Nov 24: J40; Nov 25: J40; Nov 26: J40; Nov 27: J40; Nov 28: J40; Nov 29: J40; Nov 30: J32; Dec 01: J32; Dec 02: J32; Dec 03: J32; Dec 04: J32; Dec 05: J32; Dec 06: J32; Dec 07: J32; Dec 08: J32; Dec 09: J32; Dec 10: J32; Dec 11: J32; Dec 12: J32; Dec 13: J32; Dec 14: J32; Dec 16: J34; Dec 17: J34; Dec 18: J34; Dec 19: J34; Dec 20: J34; Dec 21: J34; Dec 22: J34; Dec 23: J34; Dec 24: J34; Dec 25: J34; Dec 26: J34; Dec 27: J34; Dec 28: J34; Dec 29: J34; Dec 30: J34; Dec 31: J34; Jan 01: J34; Jan 02: J34; Jan 03: J34; Jan 04: J34; Jan 05: J34; Jan 06: J34
[194 empty] | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC |  | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG |  |  | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35
[240 empty] | GPD | GPD | GPD | GPD | GPD | GPD | GPD | GPD | GPD | GPD | GPD | GPD | GPD | GPD | GPD | GPD | GPD | GPD
| COLO 4 | Nov 02: J38; Nov 03: J38; Nov 04: J38; Nov 05: J38; Nov 06: J38; Nov 07: J38; Nov 08: J38; Nov 09: J38; Nov 10: J38; Nov 11: J38; Nov 12: J38; Nov 13: J38; Nov 14: J38; Nov 15: J38; Nov 16: J38; Nov 17: J38; Nov 18: J38; Nov 19: J38; Nov 20: J38; Nov 21: J40; Nov 22: J40; Nov 23: J40; Nov 24: J40; Nov 25: J40; Nov 26: J40; Nov 27: J40; Nov 28: J40; Nov 29: J40; Nov 30: J40; Dec 01: J40; Dec 02: J40; Dec 03: J40; Dec 04: J40; Dec 05: J40; Dec 06: J40; Dec 07: J40; Dec 08: J40; Dec 09: J40; Dec 10: J40; Dec 11: J40; Dec 12: J40; Dec 13: J40; Dec 14: J40; Dec 16: J32; Dec 17: J32; Dec 18: J32; Dec 19: J32; Dec 20: J32; Dec 21: J32; Dec 22: J32; Dec 23: J32; Dec 24: J32; Dec 25: J32; Dec 26: J32; Dec 27: J32; Dec 28: J32; Dec 29: J32; Dec 30: J32; Dec 31: J32; Jan 07: J34; Jan 08: J34; Jan 09: J34; Jan 10: J34; Jan 11: J34; Jan 12: J34; Jan 13: J34; Jan 14: J34; Jan 15: J34; Jan 16: J34; Jan 17: J34; Jan 18: J34; Jan 19: J34; Jan 20: J34; Jan 21: J34; Jan 22: J34; Jan 23: J34; Jan 24: J34; Jan 25: J34
[214 empty] | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC |  |  | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35
| COLO 5 | Nov 14: J38; Nov 15: J38; Nov 16: J38; Nov 17: J38; Nov 18: J38; Nov 19: J38; Nov 20: J38; Nov 21: J38; Nov 22: J38; Nov 23: J38; Nov 24: J38; Nov 25: J38; Nov 26: J38; Nov 27: J38; Nov 28: J38; Nov 29: J38; Nov 30: J38; Dec 01: J38; Dec 02: J38; Dec 03: J38; Dec 04: J40; Dec 05: J40; Dec 06: J40; Dec 07: J40; Dec 08: J40; Dec 09: J40; Dec 10: J40; Dec 11: J40; Dec 12: J40; Dec 13: J40; Dec 14: J40; Dec 15: J40; Dec 16: J40; Dec 17: J40; Dec 18: J40; Dec 19: J40; Dec 20: J40; Dec 21: J40; Dec 22: J40; Dec 23: J40; Dec 24: J40; Dec 25: J40; Dec 26: J40; Dec 27: J40; Dec 28: J40; Dec 29: J40; Dec 30: J40; Dec 31: J40; Jan 02: J32; Jan 03: J32; Jan 04: J32; Jan 05: J32; Jan 06: J32; Jan 07: J32; Jan 08: J32; Jan 09: J32; Jan 10: J32; Jan 11: J32; Jan 12: J32; Jan 13: J32; Jan 14: J32; Jan 15: J32; Jan 27: J34; Jan 28: J34; Jan 29: J34; Jan 30: J34; Jan 31: J34; Feb 01: J34; Feb 02: J34; Feb 03: J34; Feb 04: J34; Feb 05: J34; Feb 06: J34; Feb 07: J34; Feb 08: J34; Feb 09: J34; Feb 10: J34; Feb 11: J34; Feb 12: J34; Feb 13: J34; Feb 14: J34
[227 empty] | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | GPC | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG | SOG |  | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35 | J35
Early Awards | Milestone | Jul 16: ML21; Jul 17: ML21; Jul 18: ML21; Jul 19: ML21; Jul 20: ML21; Jul 21: ML21; Jul 22: ML21; Jul 23: ML21; Jul 24: ML21; Jul 25: ML21; Jul 26: ML21; Jul 27: ML21; Jul 28: ML21; Jul 29: ML21; Jul 30: ML21; Jul 31: ML21; Aug 01: ML21; Aug 02: ML21; Aug 03: ML21; Aug 04: ML21; Aug 05: ML21; Aug 06: ML21; Aug 07: ML21; Aug 08: ML21; Aug 09: ML21; Aug 10: ML21; Aug 11: ML21; Aug 12: ML21; Aug 13: ML21; Aug 14: ML21; Aug 15: ML21; Aug 16: ML21; Aug 17: ML21; Aug 18: ML21; Aug 19: ML21; Aug 20: ML21; Aug 21: ML21; Aug 22: ML21; Aug 23: ML21; Aug 24: ML21; Aug 25: ML21; Aug 26: ML21; Aug 27: ML21; Aug 28: ML21; Aug 29: ML21; Aug 30: ML21; Aug 31: ML21; Sep 01: ML21; Sep 02: ML21; Sep 03: ML21; Sep 04: ML21; Sep 05: ML21; Sep 06: ML21; Sep 07: ML21; Sep 08: ML21; Sep 09: ML21; Sep 10: ML21; Sep 11: ML21; Sep 12: ML21; Sep 13: ML21; Sep 14: ML21; Sep 15: ML21; Sep 16: ML21; Sep 17: ML21; Sep 18: ML21; Sep 19: ML21; Sep 20: ML21; Sep 21: ML21; Sep 22: ML21; Sep 23: ML21; Sep 24: ML21; Sep 25: ML21; Sep 26: ML21; Sep 27: ML21
[73 empty] | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21 | ML21
Electrical Yard | Admin/ COLO 3 | Jan 17: EE31; Jan 18: EE31; Jan 19: EE31; Jan 20: EE31; Jan 21: EE31; Jan 22: EE31; Jan 23: EE31; Jan 24: EE31; Jan 25: EE31; Jan 26: EE31; Jan 27: EE31; Jan 28: EE31; Jan 29: EE31; Jan 30: EE31; Jan 31: EE31; Feb 01: EE31; Feb 02: EE31; Feb 03: EE31; Feb 04: EE31; Feb 05: EE31; Feb 06: EE31; Feb 07: EE31; Feb 10: EE31; Feb 11: EE31; Feb 12: EE31; Feb 13: EE31; Feb 14: EE31; Feb 15: EE31; Feb 16: EE31; Feb 17: EE31; Feb 18: EE31; Feb 19: EE31; Feb 20: EE30; Feb 21: EE30; Feb 22: EE30; Feb 23: EE30; Feb 24: EE30; Feb 25: EE30; Feb 26: EE30; Feb 27: EE30; Feb 28: EE30; Mar 01: EE30; Mar 02: EE30; Mar 03: EE30; Mar 04: E34; Mar 05: E34; Mar 06: E34; Mar 07: E34; Mar 08: E34; Mar 09: E34; Mar 10: E34; Mar 11: E34; Mar 12: E34; Mar 13: E34; Mar 14: E34; Mar 15: E34; Apr 25: E35; Apr 26: E35; Apr 27: E35; Apr 28: E35; Apr 29: E35; Apr 30: E35; May 01: E35; May 02: E35; May 03: E35; May 04: E35; May 05: E35; May 06: E35; May 07: E35; May 08: E35; May 09: E35; May 10: E35; May 11: E35; May 12: E35; May 13: E35; May 14: E35; May 15: E35; May 16: E35; May 17: E35; May 18: E35; May 19: E35; May 20: E35; May 21: E35; May 22: E35; May 23: E35; May 27: E35; May 28: E35; May 29: E35; May 30: E35; May 31: E35; Jun 01: E35; Jun 02: E35; Jun 03: E35
[304 empty] | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28
[304 empty] | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30
[304 empty] | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39
| COLO 4 | Feb 21: EE31; Feb 22: EE31; Feb 23: EE31; Feb 24: EE31; Feb 25: EE31; Feb 26: EE31; Feb 27: EE31; Feb 28: EE31; Mar 01: EE31; Mar 02: EE31; Mar 03: EE31; Mar 04: EE31; Mar 05: EE31; Mar 06: EE31; Mar 07: EE31; Mar 08: EE31; Mar 09: EE31; Mar 10: EE31; Mar 11: EE31; Mar 12: EE31; Mar 13: EE31; Mar 14: EE31; Mar 15: EE31; Mar 16: EE31; Mar 17: EE31; Mar 18: EE31; Mar 19: EE31; Mar 20: EE31; Mar 21: EE31; Mar 22: EE31; Mar 23: EE31; Mar 24: EE31; Mar 25: EE31; Mar 26: EE31; Mar 27: EE30; Mar 28: EE30; Mar 29: EE30; Mar 30: EE30; Mar 31: EE30; Apr 01: EE30; Apr 02: EE30; Apr 03: EE30; Apr 04: EE30; Apr 05: EE30; Apr 11: E34; Apr 12: E34; Apr 13: E34; Apr 14: E34; Apr 15: E34; Apr 16: E34; Apr 17: E34; Apr 18: E34; Apr 19: E34; Apr 20: E34; Apr 21: E34; Apr 22: E34; Apr 23: E34; Apr 24: E34; Apr 25: E35; Apr 26: E35; Apr 27: E35; Apr 28: E35; Apr 29: E35; Apr 30: E35; May 01: E35; May 02: E35; May 03: E35; May 04: E35; May 05: E35; May 06: E35; May 07: E35; May 08: E35; May 09: E35; May 10: E35; May 11: E35; May 12: E35; May 13: E35; May 14: E35; May 15: E35; May 16: E35; May 17: E35; May 18: E35; May 19: E35; May 20: E35; May 21: E35; May 22: E35; May 23: E35; May 27: E35; May 28: E35; May 29: E35; May 30: E35; May 31: E35; Jun 01: E35; Jun 02: E35; Jun 03: E35; Jun 04: E35
[333 empty] | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28
[333 empty] | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30
[333 empty] | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39
| COLO 5 | Jan 20: EE29; Jan 21: EE29; Jan 22: EE29; Jan 23: EE29; Jan 24: EE29; Jan 25: EE29; Jan 26: EE29; Jan 27: EE29; Jan 28: EE29; Jan 29: EE29; Jan 30: EE29; Jan 31: EE29; Feb 01: EE29; Feb 02: EE29; Feb 03: EE29; Feb 04: EE29; Feb 05: EE29; Feb 06: EE29; Feb 07: EE29; Feb 08: EE29; Feb 09: EE29; Feb 10: EE29; Feb 11: EE29; Feb 12: EE29; Feb 13: EE29; Feb 14: EE29; Feb 15: EE29; Feb 16: EE29; Feb 17: EE29; Feb 18: EE29; Feb 19: EE29; Feb 20: EE29; Feb 21: EE29; Feb 22: EE29; Feb 23: EE29; Feb 24: EE29; Feb 25: EE29; Feb 26: EE29; Feb 27: EE29; Feb 28: EE29; Mar 01: EE29; Mar 02: EE29; Mar 03: EE29; Mar 04: EE29; Mar 05: EE29; Mar 06: EE29; Mar 07: EE29; Mar 08: EE29; Mar 09: EE29; Mar 10: EE29; Mar 11: EE29; Mar 12: EE29; Mar 13: EE29; Mar 14: EE29; Mar 15: EE29; Mar 16: EE29; Mar 17: EE29; Mar 18: EE29; Mar 19: EE29; Mar 20: EE29; Mar 21: EE29; Mar 22: EE29; Mar 23: EE29; Mar 24: EE29; Mar 25: EE29; Mar 26: EE29; Mar 27: EE29; Mar 28: EE29; Mar 29: EE29; Mar 30: EE29; Mar 31: EE29; Apr 01: EE29; Apr 02: EE29; Apr 03: EE29; Apr 04: EE29; Apr 05: EE29; Apr 06: EE29; Apr 07: EE29; Apr 08: EE29; Apr 09: EE29; Apr 10: EE29; Apr 11: EE29; Apr 12: EE29; Apr 13: EE29; Apr 14: EE29; Apr 15: EE29; Apr 16: EE29; Apr 17: EE29; Apr 18: EE29; Apr 19: EE29; Apr 20: EE29; Apr 21: EE29; Apr 22: EE29; Apr 23: EE29; Apr 24: EE29; Apr 25: EE29; Apr 26: EE29; Apr 27: EE29; Apr 28: EE29; Apr 29: EE29; Apr 30: EE29; May 01: EE29; May 02: EE29; May 03: EE29; May 04: EE29; May 05: EE29; May 06: EE29; May 07: EE29; May 08: EE29; May 09: EE29; May 19: E34; May 20: E34; May 21: E34; May 22: E34; May 23: E34; May 24: E34; May 25: E34; May 26: E34; May 27: E34; May 28: E34; May 29: E34; May 30: E34; May 31: E34; Jun 02: E35; Jun 03: E35; Jun 04: E35; Jun 05: E35; Jun 06: E35; Jun 07: E35; Jun 08: E35; Jun 09: E35; Jun 10: E35; Jun 13: EE61; Jun 14: EE61; Jun 15: EE61; Jun 16: EE61; Jun 17: EE61; Jun 18: EE61
[328 empty] | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE31 | EE30 | EE30 | EE30 | EE30 | EE30 | EE30 | EE30 | EE30 | EE30 | EE30 | EE30 | [5 empty] | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | E28 | [5 empty] | EE61 | EE61 | EE61 | EE61 |  | EE61 | EE61 | EE61 | EE61
[363 empty] | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 |  | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30
[373 empty] | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39 | E39
[374 empty] | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35 | E35
[391 empty] | EE61 | EE61 | EE61 | EE61 | EE61
Fitout | Admin | Feb 22: J24; Feb 23: J24; Feb 24: J24; Feb 25: J24; Feb 26: J24; Feb 27: EEA; Feb 28: EEA; Mar 01: EEA; Mar 02: EEA; Mar 03: EEA; Mar 04: EEA; Mar 05: EEA; Mar 06: EEA; Mar 07: EEA; Mar 08: EEA; Mar 09: EEA; Mar 10: EEA; Mar 11: EEA; Mar 12: CL; Mar 13: CL; Mar 14: CL; Mar 15: CL; Mar 16: CL; Mar 17: CL
| CELL 1 Data Hall | Feb 24: J1; Feb 25: J3; Feb 26: J3; Feb 27: J3; Feb 28: EE2; Mar 01: EE2; Mar 02: EE2; Mar 03: EE2; Mar 04: EE2; Mar 05: J4; Mar 06: J4; Mar 07: J4; Mar 11: J5; Mar 12: J5; Mar 15: J6; Mar 16: J6; Mar 17: J6; Mar 18: J6; Mar 19: J42; Mar 20: J42; Mar 21: T3; Mar 22: T3; Mar 23: T3; Mar 24: T3; Mar 25: Cx2; Mar 29: S1; Mar 30: S1; Mar 31: S1; Apr 01: S1; Apr 02: S1; Apr 03: S1; Apr 04: EE2; Apr 05: EE2; Apr 06: EE2; Apr 07: EE2; Apr 08: J4; Apr 09: J4; Apr 10: J4; Apr 15: EE32; Apr 16: EE32; Apr 17: EE32; Apr 23: J42; Apr 24: J42; Apr 25: T3; Apr 26: T3; Apr 28: Cx2; May 02: S1; May 03: S1; May 04: S1; May 05: S1; May 06: S1; May 07: S1; May 08: S1; May 14: S2; May 15: S2; May 16: S2; May 17: S2; May 19: EE32; May 20: EE32; May 21: EE32; May 27: EE17; May 28: EE17; May 29: EE17; May 30: EE17; May 31: EE17; Jun 02: EE19; Jun 03: EE19; Jun 04: EE19
[305 empty] | GSD | GSD | GSD | J5 | J5 | J5 | J5 | [13 empty] | J16 | J16 | J16 | J16 |  |  |  | EE10 | EE10 | EE10 | EE10 | EE10 | [9 empty] | S2 | S2 | S2 | S2 | [9 empty] | J16 | J16 | J16 | J16 |  |  |  |  | EE10 | EE10 | EE10 | EE10 | EE10 | [8 empty] | S2 | S2 | S2 | S2
[308 empty] | EE1 | EE1 | EE1 | EE1 | EE1 | [18 empty] | J1 |  |  | J23 | J23 | [10 empty] | J5 | J5 |  | J21 | J21 | J21 | J21 | [9 empty] | EE19 | EE19 | EE19 | EE19 | EE19 | J37 | J37 | J23 | J23 | [12 empty] | J21 | J21
[308 empty] | GSC | GSC | GSC | GSC | [17 empty] | J37 | J37 | J37 | J37 | J37 | J33 | J33 | J33 | J33 | J33 | J33 |  |  | J5 | J5 | J5 | J5 | J5 |  |  |  | J6 | J6 | J6 | J6 | [15 empty] | J33 | J33 | J33 | J33 | J33 | J33
[311 empty] | J44 | J44 | [19 empty] | J3 | J3 | J3 |  |  |  |  | GSD | GSD | GSD | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | [5 empty] | EE17 | EE17 | EE17 | EE17 | EE17 | [11 empty] | EE7 | EE7 | EE7 | EE7 | EE7
[312 empty] | T1 | T1 | T1 | [19 empty] | EE7 | EE7 | EE7 | EE7 | EE7 |  | S2 | S2 | S2 | S2 | S2 | S2 | GSC
[346 empty] | J44 | J44
[347 empty] | T1 | T1 | T1
| CELL 1 Electrical Room | Feb 28: J3; Mar 01: J3; Mar 02: J3; Mar 03: J3; Mar 04: EE2; Mar 05: EE2; Mar 06: J4; Mar 07: J4; Mar 08: J4; Mar 09: J4; Mar 10: J4; Mar 11: J5; Mar 15: Cx2; Mar 31: EE53; Apr 01: EE53; Apr 02: EE53; Apr 03: EE53; Apr 04: J3; Apr 05: J3; Apr 07: EE2; Apr 08: EE2; Apr 09: J4; Apr 10: J4; Apr 11: J4; Apr 12: J4; Apr 13: J4; Apr 14: J4; Apr 15: J5; Apr 19: Cx2; May 02: EE29; May 03: EE29; May 04: EE29; May 05: EE29; May 06: EE29; May 07: EE29; May 08: EE29; May 09: EE29; May 10: EE29; May 11: EE29; May 12: EE29; May 13: EE29; May 14: EE29; May 15: EE29; May 16: EE47; May 17: EE47; May 18: EE47; May 19: EE47; May 20: EE47; May 21: EE47; May 22: EE47; May 23: EE47; May 24: EE47; May 25: EE47; May 26: EE47; May 27: EE47; May 28: EE47; May 29: EE47
[306 empty] | GSD | GSD |  |  |  | J5 | J5 | [27 empty] | GSD | GSD |  |  |  |  | J5 | J5 | [29 empty] | EE59 | EE59 | EE59 | EE59 | EE59
[308 empty] | GSC | GSC | GSC | EE1 | EE35 | EE35 | [28 empty] | GSC | GSC | GSC | GSC | EE1 | EE35 | EE35
[313 empty] | T1 | T1 | [33 empty] | T1 | T1
[335 empty] | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47
[352 empty] | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53 | EE53
[349 empty] | EE59 | EE59 | EE59 | EE59 | EE59
| CELL 1 Mechanical Gallery | Mar 08: GSD; Mar 09: GSD; Mar 10: GSD; Mar 11: EE1; Mar 12: EE1; Mar 13: EE1; Mar 14: J44; Mar 15: J44; Mar 16: J44; Mar 17: J44; Mar 18: J44; Mar 19: J44; Mar 20: J44; Mar 27: J4; Mar 28: J4; Mar 29: J5; Apr 03: Cx2; Apr 04: Cx2; Apr 05: Cx2; Apr 18: J44; Apr 19: J44; Apr 20: J44; Apr 21: J44; Apr 22: J44; Apr 23: J44; Apr 24: J44; Apr 30: J4; May 01: J4; May 02: J5; May 08: Cx2; May 09: Cx2; May 10: Cx2; May 21: GBB; May 22: GBB; May 23: GBB; May 24: GBB; May 25: GBB; May 26: GBB; May 27: GBB; May 28: GBB; May 29: GBB; May 30: GBB; May 31: EE60; Jun 01: EE60; Jun 02: EE60; Jun 03: EE60; Jun 04: EE60
[311 empty] | GSC | GSC | [8 empty] | GPA | GPA | GPA | GPA | GPA | GPA | GPA | GPA | J5 | J5 | J5 |  |  |  | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | [8 empty] | GPA | GPA | GPA | GPA | GPA | GPA | GPA | J5 | J5 | J5 | J5 |  |  |  | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA
[331 empty] | J20 | J20 | J20 | J20 | EE35 | EE35 |  | EE57 | EE57 | EE57 | EE57 | GSD | GSD | GSD | GSD | EE1 | EE1 | EE1 | [8 empty] | EE60 | EE60 | EE60 | EE60 | EE60 |  |  |  |  | J20 | J20 | J20 | J20 | EE35 | EE35 |  | EE57 | EE57 | EE57 | EE57 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42
[332 empty] | T1 | T1 | [12 empty] | GSC | GSC | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | [10 empty] | T1 | T1
[342 empty] | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42
| CELL 1 Punchlist | Apr 17: PU1; Apr 18: PU1; Apr 19: PU1; Apr 20: PU1; Apr 21: PU1; Apr 22: PU1; Apr 23: PU1; Apr 24: PU1; Apr 25: PU1; Apr 26: PU1; Apr 27: PU1; Apr 28: PU1; May 06: PU1; May 07: PU1; May 08: PU1; May 09: PU1; May 10: PU1; May 11: PU1; May 12: PU1; May 13: PU1; May 14: PU1; May 15: PU1; May 16: PU1; Jun 05: PU1; Jun 06: PU1; Jun 07: PU1; Jun 08: PU1; Jun 09: PU1; Jun 10: PU1; Jun 11: PU1; Jun 12: PU1; Jun 13: PU1; Jun 14: PU1; Jun 15: PU1; Jun 16: PU1; Jun 17: PU1
| CELL 2 Data Hall | Mar 05: J1; Mar 06: J3; Mar 07: J3; Mar 08: J3; Mar 10: EE2; Mar 11: EE2; Mar 12: EE2; Mar 13: J4; Mar 14: J4; Mar 15: J4; Mar 19: J5; Mar 20: J5; Mar 25: J6; Mar 26: J6; Mar 27: J6; Mar 28: J42; Mar 29: J42; Mar 31: T3; Apr 01: T3; Apr 02: Cx2; Apr 07: S1; Apr 08: S1; Apr 09: S1; Apr 10: S1; Apr 11: S1; Apr 14: EE2; Apr 15: EE2; Apr 16: EE2; Apr 17: J4; Apr 18: J4; Apr 19: J4; Apr 23: EE32; Apr 24: EE32; Apr 25: EE32; May 01: J42; May 02: J42; May 05: T3; May 06: T3; May 07: Cx2; May 12: S1; May 13: S1; May 14: S1; May 15: S1; May 16: S1; May 22: S2; May 23: S2; May 24: S2; May 25: S2; May 26: S2; May 27: S2; May 28: EE32; May 29: EE32; May 30: EE32; Jun 04: EE17; Jun 05: EE17; Jun 06: EE17; Jun 07: EE17; Jun 08: EE17; Jun 09: EE17; Jun 25: EE19; Jun 26: EE19; Jun 27: EE19
[313 empty] | GSD | GSD | GSD |  | J5 | J5 | J5 | [13 empty] | J16 | J16 | J16 | J16 |  |  |  | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [7 empty] | S2 | S2 | S2 | S2 | [10 empty] | J16 | J16 | J16 | J16 |  |  |  | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [8 empty] | S2 | S2 | S2 | S2
[317 empty] | EE1 | EE1 | EE1 | EE1 | [18 empty] | J1 |  |  | J23 | J23 | J23 | J23 | [8 empty] | J5 | J5 |  | J21 | J21 | J21 | J21 | [12 empty] | J37 | J37 | J37 | J37 | J23 | J23 | [10 empty] | EE19 | EE19 | EE19 | J21 | J21 | J21 | J21
[317 empty] | GSC | GSC | GSC | [18 empty] | J37 | J37 | J37 | J37 | J33 | J33 | J33 | J33 | J33 | J33 | J33 |  |  |  | J5 | J5 | J5 |  |  |  |  | J6 | J6 | J6 | [15 empty] | J33 | J33 | J33 | J33 | J33 | J33
[319 empty] | J44 | J44 | [19 empty] | J3 | J3 | J3 | [5 empty] | GSD | GSD | GSD |  | EE1 | EE1 | EE1 | EE1 | [5 empty] | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | [9 empty] | EE7 | EE7 | EE7 | EE7 | EE7
[320 empty] | T1 | T1 | T1 | T1 | T1 | [17 empty] | EE7 | EE7 | EE7 | EE7 | EE7 | EE7 |  | S2 | S2 | S2 | S2 | S2 | GSC
[354 empty] | J44 | J44
[355 empty] | T1 | T1 | T1
| CELL 2 Electrical Room | Mar 10: J3; Mar 11: J3; Mar 12: EE2; Mar 13: EE2; Mar 14: J4; Mar 15: J4; Mar 16: J4; Mar 17: J4; Mar 18: J4; Mar 19: J5; Mar 25: Cx2; Mar 26: EE53; Mar 27: EE53; Mar 28: EE53; Mar 29: EE53; Apr 14: J3; Apr 15: J3; Apr 16: EE2; Apr 17: EE2; Apr 18: J4; Apr 19: J4; Apr 20: J4; Apr 21: J4; Apr 22: J4; Apr 23: J5; Apr 28: Cx2; May 01: EE29; May 02: EE29; May 03: EE29; May 04: EE29; May 05: EE29; May 06: EE29; May 07: EE29; May 08: EE29; May 09: EE29; May 10: EE29; May 11: EE29; May 12: EE29; May 13: EE29; May 14: EE29; May 15: EE47; May 16: EE47; May 17: EE47; May 18: EE47; May 19: EE47; May 20: EE47; May 21: EE47; May 22: EE47; May 23: EE47; May 24: EE47; May 25: EE47; May 26: EE47; May 27: EE47; May 30: EE29; May 31: EE29; Jun 01: EE29; Jun 02: EE29; Jun 03: EE29; Jun 04: EE29; Jun 05: EE29; Jun 06: EE29; Jun 07: EE29; Jun 08: EE29; Jun 09: EE29; Jun 10: EE29; Jun 11: EE29; Jun 12: EE47; Jun 13: EE47; Jun 14: EE47; Jun 15: EE47; Jun 16: EE47; Jun 17: EE47; Jun 18: EE47; Jun 19: EE47; Jun 20: EE47; Jun 21: EE47; Jun 22: EE47; Jun 23: EE47; Jun 24: EE47
[314 empty] | GSD | GSD |  |  |  | J5 | J5 | [28 empty] | GSD | GSD |  |  |  | J5 | J5 |  |  |  |  | EE53 | EE53 | EE53 | EE53 | [12 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | [23 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
[317 empty] | GSC | GSC | EE1 | EE35 | EE35 | [30 empty] | GSC | GSC | EE1 | EE35 | EE35
[321 empty] | T1 | T1 | T1 | T1 | [31 empty] | T1 | T1
| CELL 2 Mechanical Gallery | Mar 17: GSD; Mar 18: GSD; Mar 19: EE1; Mar 20: EE1; Mar 21: EE1; Mar 24: J44; Mar 25: J44; Mar 26: J44; Mar 27: J44; Mar 28: J44; Mar 29: J44; Apr 04: J4; Apr 05: J4; Apr 07: J5; Apr 11: Cx2; Apr 12: Cx2; Apr 13: Cx2; Apr 14: Cx2; Apr 15: Cx2; Apr 26: J44; Apr 27: J44; Apr 28: J44; Apr 29: J44; Apr 30: J44; May 01: J44; May 02: J44; May 09: J4; May 10: J4; May 12: J5; May 16: Cx2; May 17: Cx2; May 18: Cx2; May 19: Cx2; May 30: GBB; May 31: GBB; Jun 01: GBB; Jun 02: GBB; Jun 03: GBB; Jun 04: GBB; Jun 05: GBB; Jun 06: GBB; Jun 07: GBB; Jun 09: EE60; Jun 10: EE60; Jun 11: EE60; Jun 12: EE60
[319 empty] | GSC | GSC | [10 empty] | GPA | GPA | GPA | GPA | GPA | GPA |  | J5 | J5 | [5 empty] | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | [10 empty] | GPA | GPA | GPA | GPA | GPA | GPA |  | J5 | J5 |  |  |  | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA
[339 empty] | J20 | J20 | J20 | J20 |  |  | EE35 | EE35 | EE57 | EE57 | EE57 | EE57 |  | GSD | GSD | EE1 | EE1 | EE1 | [10 empty] | EE60 | EE60 | EE60 | EE60 |  |  |  | J20 | J20 | J20 | J20 | EE35 | EE35 | EE35 | EE57 | EE57 | EE57 | EE57 |  |  |  | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42
[340 empty] | T1 | T1 | [12 empty] | GSC | GSC | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | [8 empty] | T1 | T1
[352 empty] | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42
| CELL 2 Punchlist | May 31: PU1; Jun 01: PU1; Jun 02: PU1; Jun 03: PU1; Jun 04: PU1; Jun 05: PU1; Jun 06: PU1; Jun 07: PU1; Jun 08: PU1; Jun 09: PU1; Jun 10: PU1; Jun 11: PU1; Jun 28: PU1; Jun 29: PU1; Jun 30: PU1; Jul 01: PU1; Jul 02: PU1; Jul 03: PU1; Jul 04: PU1; Jul 05: PU1; Jul 06: PU1; Jul 07: PU1; Jul 08: PU1; Jul 09: PU1; Jul 10: PU1; Jul 11: PU1
| CELL 3 Data Hall | Mar 28: J1; Mar 29: J3; Mar 30: J3; Mar 31: J3; Apr 01: J3; Apr 02: EE2; Apr 03: EE2; Apr 04: EE2; Apr 05: J4; Apr 06: J4; Apr 07: J4; Apr 08: J4; Apr 11: J5; Apr 12: J5; Apr 13: J5; Apr 14: J5; Apr 17: J6; Apr 18: J6; Apr 19: J6; Apr 21: J42; Apr 22: J42; Apr 23: T3; Apr 24: T3; Apr 25: Cx2; Apr 30: S1; May 01: S1; May 02: S1; May 03: S1; May 04: S1; May 05: S1; May 06: S1; May 07: EE2; May 08: EE2; May 09: EE2; May 10: J4; May 11: J4; May 12: J4; May 13: J4; May 16: EE32; May 17: EE32; May 18: EE32; May 19: EE32; May 27: J42; May 28: T3; May 29: T3; May 30: Cx2; Jun 04: S1; Jun 05: S1; Jun 06: S1; Jun 07: S1; Jun 08: S1; Jun 09: S1; Jun 16: S2; Jun 17: S2; Jun 18: S2; Jun 19: S2; Jun 20: EE32; Jun 21: EE32; Jun 22: EE32; Jun 23: EE32; Jun 27: EE17; Jun 28: EE17; Jun 29: EE17; Jun 30: EE17; Jul 01: EE17; Jul 02: EE17; Jul 18: EE19; Jul 19: EE19; Jul 20: EE19; Jul 21: EE19; Aug 06: EE19; Aug 07: EE19; Aug 08: EE19
[336 empty] | GSD | GSD | GSD | GSD | J5 | J5 | J5 | [13 empty] | J16 | J16 | J16 | J16 | J16 |  |  | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [7 empty] | S2 | S2 | S2 | S2 | S2 | [9 empty] | J16 | J16 | J16 | J16 | J16 |  |  | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [8 empty] | S2 | S2 | S2 | S2 | S2
[340 empty] | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | [16 empty] | J1 |  |  |  |  | J23 | J23 | [8 empty] | J5 | J5 |  |  | J21 | J21 | J21 | [12 empty] | J37 | J37 | J37 | J37 |  | J23 | J23 | [13 empty] | J21 | J21 | J21
[340 empty] | GSC | GSC | GSC | [18 empty] | J37 | J37 | J37 | J37 | J37 | J37 | J33 | J33 | J33 | J33 | J33 |  |  |  | J5 | J5 | J5 |  |  |  |  | J6 | J6 | J6 | [16 empty] | J33 | J33 | J33 | J33 | J33
[342 empty] | J44 | J44 | J44 | J44 | [17 empty] | J3 | J3 | J3 | J3 | J3 |  |  |  | GSD | GSD | GSD | GSD | EE1 | EE1 | EE1 | EE1 | [5 empty] | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | EE17 | [10 empty] | EE7 | EE7 | EE7 | EE7
[345 empty] | T1 | T1 | T1 | [19 empty] | EE7 | EE7 | EE7 | EE7 |  |  | S2 | S2 | S2 | S2 | GSC
[377 empty] | J44 | J44
[378 empty] | T1 | T1 | T1 | T1
| CELL 3 Electrical Room | Feb 26: J3; Feb 27: J3; Feb 28: EE2; Mar 01: EE2; Mar 02: EE2; Mar 03: EE2; Mar 04: J4; Mar 05: J4; Mar 06: J4; Mar 07: J4; Mar 08: J5; Mar 13: Cx2; Mar 14: EE53; Mar 15: EE53; Mar 16: EE53; Mar 17: EE53; Mar 18: EE53; Apr 02: J3; Apr 03: J3; Apr 04: EE2; Apr 05: EE2; Apr 07: J4; Apr 08: J4; Apr 09: J4; Apr 10: J4; Apr 11: J5; Apr 17: Cx2; Apr 18: EE53; Apr 19: EE53; Apr 20: EE53; Apr 21: EE53; Apr 22: EE53; May 07: J3; May 08: J3; May 09: EE2; May 10: EE2; May 12: J4; May 13: J4; May 14: J4; May 15: J4; May 16: J5; May 21: Cx2; May 23: EE47; May 24: EE47; May 25: EE47; May 26: EE47; May 27: EE47; May 28: EE47; May 29: EE47; May 30: EE47; May 31: EE47; Jun 01: EE47; Jun 02: EE47; Jun 03: EE47; Jun 04: EE47; Jun 24: EE29; Jun 25: EE29; Jun 26: EE29; Jun 27: EE29; Jun 28: EE29; Jun 29: EE29; Jun 30: EE29; Jul 01: EE29; Jul 02: EE29; Jul 03: EE29; Jul 04: EE29; Jul 05: EE29; Jul 06: EE29; Jul 07: EE29; Jul 08: EE29; Jul 11: EE29; Jul 12: EE29; Jul 13: EE29; Jul 14: EE29; Jul 15: EE29; Jul 16: EE29; Jul 17: EE29; Jul 18: EE29; Jul 19: EE29; Jul 20: EE29; Jul 21: EE29; Jul 22: EE29; Jul 23: EE29; Jul 24: EE47; Jul 25: EE47; Jul 26: EE47; Jul 27: EE47; Jul 28: EE47; Jul 29: EE47; Jul 30: EE47; Jul 31: EE47; Aug 01: EE47; Aug 02: EE47; Aug 03: EE47; Aug 04: EE47; Aug 05: EE47
[304 empty] | GSD | GSD |  |  | J5 | J5 | J5 | [27 empty] | GSD | GSD |  |  | J5 | J5 | J5 | J5 | [27 empty] | GSD | GSD |  |  | J5 | J5 | [52 empty] | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 |  |  |  |  | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
[306 empty] | GSC | GSC | EE1 |  | EE35 | EE35 | [28 empty] | GSC | GSC | EE1 |  |  | EE35 | EE35 | [28 empty] | GSC | GSC | EE1 | EE35 | EE35 | EE35 | [50 empty] | EE59 | EE59 | EE59 | EE59
[311 empty] | T1 | T1 | [33 empty] | T1 | T1 | [32 empty] | T1 | T1
[371 empty] | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29 | EE29
[383 empty] | EE53 | EE53 | EE53 | EE53 | EE53 | EE53
[384 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59
| CELL 3 Mechanical Gallery | Mar 06: GSD; Mar 07: GSD; Mar 08: EE1; Mar 09: EE1; Mar 10: EE1; Mar 11: EE1; Mar 12: J44; Mar 13: J44; Mar 14: J44; Mar 15: J44; Mar 16: J44; Mar 17: J44; Mar 18: J44; Mar 25: J4; Mar 26: J4; Mar 27: J5; Apr 01: Cx2; Apr 02: Cx2; Apr 03: Cx2; Apr 16: J44; Apr 17: J44; Apr 18: J44; Apr 19: J44; Apr 20: J44; Apr 21: J44; Apr 22: J44; Apr 28: J4; Apr 29: J4; Apr 30: J5; May 06: Cx2; May 07: Cx2; May 08: Cx2; May 20: J44; May 21: J44; May 22: J44; May 23: J44; May 24: J44; May 25: J44; May 26: J44; May 27: J44; Jun 02: J4; Jun 03: J4; Jun 04: J5; Jun 09: Cx2; Jun 10: Cx2; Jun 11: Cx2; Jun 23: GBB; Jun 24: GBB; Jun 25: GBB; Jun 26: GBB; Jun 27: GBB; Jun 28: GBB; Jun 29: GBB; Jun 30: GBB; Jul 01: GBB; Jul 02: EE60; Jul 03: EE60; Jul 04: EE60; Jul 05: EE60; Jul 06: EE60; Jul 07: EE60; Jul 08: EE60
[308 empty] | GSC | GSC | GSC | [8 empty] | GPA | GPA | GPA | GPA | GPA | GPA | GPA | GPA | J5 | J5 |  |  |  |  | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | [8 empty] | GPA | GPA | GPA | GPA | GPA | GPA | GPA | J5 | J5 | [5 empty] | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | [10 empty] | GPA | GPA | GPA | GPA | GPA | GPA | GPA | J5 | J5 |  |  |  |  | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA
[328 empty] | J20 | J20 | J20 | J20 | J20 | EE35 | EE35 | EE57 | EE57 | EE57 | EE57 | EE57 | GSD | GSD | EE1 | EE1 | EE1 | EE1 | EE1 | [8 empty] | EE60 | EE60 | EE60 | EE60 | EE60 |  |  | J20 | J20 | J20 | J20 | J20 | J20 | EE35 | EE35 | EE57 | EE57 | EE57 | EE57 | EE57 | GSD | GSD | EE1 | EE1 | EE1 | EE1 | [9 empty] | EE60 | EE60 | EE60 | EE60 | EE60 |  |  | J20 | J20 | J20 | J20 | J20 | EE35 | EE35 | EE57 | EE57 | EE57 | EE57 | EE57 | EE57 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42
[329 empty] | T1 | T1 | T1 | [10 empty] | GSC | GSC | GSC | GSC | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | [8 empty] | T1 | T1 | T1 | T1 | [10 empty] | GSC | GSC |  | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | [8 empty] | T1 | T1
[340 empty] | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | [20 empty] | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42
| CELL 3 Punchlist | Jun 09: PU1; Jun 10: PU1; Jun 11: PU1; Jun 12: PU1; Jun 13: PU1; Jun 14: PU1; Jun 15: PU1; Jun 16: PU1; Jun 17: PU1; Jun 18: PU1; Jun 19: PU1; Jun 20: PU1; Jul 22: PU1; Jul 23: PU1; Jul 24: PU1; Jul 25: PU1; Jul 26: PU1; Jul 27: PU1; Jul 28: PU1; Jul 29: PU1; Jul 30: PU1; Jul 31: PU1; Aug 01: PU1; Aug 02: PU1; Aug 09: PU1; Aug 10: PU1; Aug 11: PU1; Aug 12: PU1; Aug 13: PU1; Aug 14: PU1; Aug 15: PU1; Aug 16: PU1; Aug 17: PU1; Aug 18: PU1; Aug 19: PU1; Aug 20: PU1; Aug 21: PU1
| CELL 4 Data Hall | Feb 10: J1; Feb 11: J3; Feb 12: J3; Feb 13: J3; Feb 14: EE2; Feb 15: EE2; Feb 16: EE2; Feb 17: EE2; Feb 18: J4; Feb 19: J4; Feb 20: J4; Feb 24: J5; Feb 25: J5; Feb 28: J6; Mar 01: J6; Mar 02: J6; Mar 03: J6; Mar 04: J6; Mar 05: J42; Mar 06: J42; Mar 07: T3; Mar 08: T3; Mar 10: Cx2; Mar 14: S1; Mar 15: S1; Mar 16: S1; Mar 17: S1; Mar 18: S1; Mar 19: S1; Mar 20: EE2; Mar 21: EE2; Mar 22: EE2; Mar 23: EE2; Mar 24: EE2; Mar 25: J4; Mar 26: J4; Mar 27: J4; Mar 31: EE32; Apr 01: EE32; Apr 02: EE32; Apr 08: J42; Apr 09: J42; Apr 10: T3; Apr 11: T3; Apr 14: Cx2; Apr 18: S1; Apr 19: S1; Apr 20: S1; Apr 21: S1; Apr 22: S1; Apr 23: S1; Apr 29: S2; Apr 30: S2; May 01: S2; May 02: S2; May 05: EE32; May 06: EE32; May 07: EE32; May 12: EE17; May 13: EE17; May 14: EE17; May 15: EE17; May 16: EE17; Jun 24: EE19; Jun 25: EE19; Jun 26: EE19
[290 empty] | GSD | GSD | GSD | J5 | J5 | J5 | J5 | [13 empty] | J16 | J16 | J16 | J16 |  |  |  | EE10 | EE10 | EE10 | EE10 | EE10 | [9 empty] | S2 | S2 | S2 | S2 | [10 empty] | J16 | J16 | J16 | J16 |  |  |  | EE10 | EE10 | EE10 | EE10 | EE10 | [9 empty] | S2 | S2 | S2 | S2
[293 empty] | EE1 | EE1 | EE1 | EE1 | EE1 | [17 empty] | J1 |  |  |  | J23 | J23 | [10 empty] | J5 | J5 |  | J21 | J21 | J21 | [12 empty] | J37 | J37 | J37 | J37 | J37 | J23 | J23 | [13 empty] | J21 | J21 | J21
[293 empty] | GSC | GSC | GSC | GSC | [17 empty] | J37 | J37 | J37 | J37 | J37 | J33 | J33 | J33 | J33 | J33 | J33 | J33 |  |  | J5 | J5 | J5 | J5 |  |  |  | J6 | J6 | J6 | J6 | [15 empty] | J33 | J33 | J33 | J33 | J33 | J33 | [11 empty] | EE19 | EE19 | EE19 | EE19
[296 empty] | J44 | J44 | [19 empty] | J3 | J3 | J3 | [5 empty] | GSD | GSD | GSD | EE1 | EE1 | EE1 | EE1 | EE1 | [5 empty] | EE17 | EE17 | EE17 | EE17 | EE17 | [11 empty] | EE7 | EE7 | EE7 | EE7
[297 empty] | T1 | T1 | T1 | [19 empty] | EE7 | EE7 | EE7 | EE7 | EE7 | EE7 |  | S2 | S2 | S2 | S2 | GSC | GSC
[331 empty] | J44 | J44
[332 empty] | T1 | T1 | T1
| CELL 4 Data Hall Fitout Activities | Apr 19: J1; Apr 21: J3; Apr 22: J3; Apr 23: J3; Apr 24: EE2; Apr 25: EE2; Apr 26: EE2; Apr 28: J4; Apr 29: J4; Apr 30: J4; May 05: J5; May 06: J5; May 09: J6; May 10: J6; May 11: J6; May 12: J6; May 13: J42; May 14: J42; May 15: T3; May 16: T3; May 17: Cx2; May 22: S1; May 23: S1; May 24: S1; May 25: S1; May 26: S1; May 27: S1; May 28: S1; Jun 03: S2; Jun 04: S2; Jun 05: S2; Jun 06: S2; Jun 07: EE32; Jun 08: EE32; Jun 09: EE32; Jun 10: EE32; Jun 16: EE17; Jun 17: EE17; Jun 18: EE17; Jun 19: EE17; Jun 20: EE17; Jul 11: EE19; Jul 12: EE19; Jul 13: EE19; Jul 14: EE19
[359 empty] | GSD | GSD | GSD | J5 | J5 | J5 | J5 | J5 | [11 empty] | J16 | J16 | J16 | J16 | J16 | [5 empty] | EE10 | EE10 | EE10 | EE10 | [7 empty] | S2 | S2 | S2 | S2 | S2
[362 empty] | EE1 | EE1 | EE1 | EE1 | EE1 | EE1 | [15 empty] | J37 | J37 | J37 | J37 | J37 | J37 | J23 | J23 | [12 empty] | J21 | J21 | J21
[362 empty] | GSC | GSC | GSC | GSC | GSC | [22 empty] | J33 | J33 | J33 | J33 | J33 | J33
[366 empty] | J44 | J44 | [21 empty] | EE7 | EE7 | EE7 | EE7
[367 empty] | T1 | T1 | T1
| CELL 4 Electrical Room | Feb 14: J3; Feb 15: J3; Feb 17: EE2; Feb 18: EE2; Feb 19: J4; Feb 20: J4; Feb 21: J4; Feb 22: J4; Feb 24: J5; Feb 28: Cx2; Mar 03: EE53; Mar 04: EE53; Mar 05: EE53; Mar 06: EE53; Mar 07: EE29; Mar 08: EE29; Mar 09: EE29; Mar 10: EE29; Mar 11: EE29; Mar 12: EE29; Mar 13: EE29; Mar 14: EE29; Mar 15: EE29; Mar 16: EE29; Mar 17: EE29; Mar 18: EE29; Mar 19: EE29; Mar 20: J3; Mar 21: J3; Mar 24: EE2; Mar 25: EE2; Mar 26: J4; Mar 27: J4; Mar 28: J4; Mar 29: J4; Mar 31: J5; Apr 04: Cx2; Apr 05: EE53; Apr 06: EE53; Apr 07: EE53; Apr 08: EE53; Apr 09: EE53; Apr 24: J3; Apr 25: J3; Apr 26: EE2; Apr 27: EE2; Apr 28: EE2; Apr 29: J4; Apr 30: J4; May 01: J4; May 02: J4; May 05: J5; May 09: Cx2; May 10: EE53; May 11: EE53; May 12: EE53; May 13: EE53; May 14: EE53; May 28: EE29; May 29: EE29; May 30: EE29; May 31: EE29; Jun 01: EE29; Jun 02: EE29; Jun 03: EE29; Jun 04: EE29; Jun 05: EE29; Jun 06: EE29; Jun 07: EE29; Jun 08: EE29; Jun 09: EE29; Jun 12: EE29; Jun 13: EE29; Jun 14: EE29; Jun 15: EE29; Jun 16: EE29; Jun 17: EE29; Jun 18: EE29; Jun 19: EE29; Jun 20: EE29; Jun 21: EE29; Jun 22: EE29; Jun 23: EE29; Jun 24: EE29; Jun 25: EE29; Jun 26: EE47; Jun 27: EE47; Jun 28: EE47; Jun 29: EE47; Jun 30: EE47; Jul 01: EE47; Jul 02: EE47; Jul 03: EE47; Jul 04: EE47; Jul 05: EE47; Jul 06: EE47; Jul 07: EE47; Jul 08: EE47; Jul 09: EE47; Jul 10: EE47
[291 empty] | GSD | GSD |  |  |  | J5 | J5 | [22 empty] | EE59 | EE59 | EE59 | EE59 | EE59 | EE59 | GSD | GSD |  |  |  | J5 | J5 | [27 empty] | GSD | GSD |  |  |  |  | J5 | J5 | [34 empty] | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 |  |  | EE59 | EE59 | EE59 | EE59 | EE59
[293 empty] | GSC | GSC | EE1 | EE1 | EE35 | EE35 | [29 empty] | GSC | GSC | EE1 | EE1 | EE35 | EE35 | [28 empty] | GSC | GSC | EE1 | EE1 | EE1 | EE35 | EE35 | [33 empty] | EE59 | EE59 | EE59 | EE59
[298 empty] | T1 | T1 | [33 empty] | T1 | T1 | [33 empty] | T1 | T1
[357 empty] | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47 | EE47
| CELL 4 Mechanical Gallery | Feb 21: GSD; Feb 22: GSD; Feb 24: EE1; Feb 25: EE1; Feb 26: EE1; Feb 27: J44; Feb 28: J44; Mar 01: J44; Mar 02: J44; Mar 03: J44; Mar 04: J44; Mar 05: J44; Mar 06: J44; Mar 12: J4; Mar 13: J4; Mar 14: J5; Mar 19: Cx2; Mar 20: Cx2; Mar 21: Cx2; Apr 03: J44; Apr 04: J44; Apr 05: J44; Apr 06: J44; Apr 07: J44; Apr 08: J44; Apr 09: J44; Apr 16: J4; Apr 17: J4; Apr 18: J5; Apr 23: Cx2; Apr 24: Cx2; Apr 25: Cx2; May 08: J44; May 09: J44; May 10: J44; May 11: J44; May 12: J44; May 13: J44; May 14: J44; May 20: J4; May 21: J4; May 22: J5; May 28: Cx2; May 29: Cx2; May 30: Cx2; Jun 10: GBB; Jun 11: GBB; Jun 12: GBB; Jun 13: GBB; Jun 14: GBB; Jun 15: GBB; Jun 16: GBB; Jun 17: GBB; Jun 18: GBB; Jun 19: GBB; Jun 20: EE60; Jun 21: EE60; Jun 22: EE60; Jun 23: EE60; Jun 24: EE60
[296 empty] | GSC | GSC | [9 empty] | GPA | GPA | GPA | GPA | GPA | GPA | GPA | J5 | J5 |  |  |  |  | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | [8 empty] | GPA | GPA | GPA | GPA | GPA | GPA | GPA | GPA | J5 | J5 |  |  |  |  | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | [8 empty] | GPA | GPA | GPA | GPA | GPA | GPA | GPA | J5 | J5 | [5 empty] | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA
[315 empty] | J20 | J20 | J20 | J20 | J20 | EE35 | EE35 |  |  | EE57 | EE57 | EE57 | EE57 | GSD | GSD |  | EE1 | EE1 | EE1 | [8 empty] | EE60 | EE60 | EE60 | EE60 | EE60 | EE60 |  |  | J20 | J20 | J20 | J20 | J20 | EE35 | EE35 | EE57 | EE57 | EE57 | EE57 | EE57 | GSD | GSD |  |  | EE1 | EE1 | EE1 | [8 empty] | EE60 | EE60 | EE60 | EE60 | EE60 |  |  | J20 | J20 | J20 | J20 | J20 | J20 | EE35 | EE35 | EE57 | EE57 | EE57 | EE57 | EE57 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42
[317 empty] | T1 | T1 | [12 empty] | GSC | GSC | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | [10 empty] | T1 | T1 | [12 empty] | GSC | GSC | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | GBB | [11 empty] | T1
[328 empty] | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | [20 empty] | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42
| CELL 4 Punchlist | May 10: PU1; May 11: PU1; May 12: PU1; May 13: PU1; May 14: PU1; May 15: PU1; May 16: PU1; May 17: PU1; May 18: PU1; May 19: PU1; May 20: PU1; May 21: PU1; Jun 27: PU1; Jun 28: PU1; Jun 29: PU1; Jun 30: PU1; Jul 01: PU1; Jul 02: PU1; Jul 03: PU1; Jul 04: PU1; Jul 05: PU1; Jul 06: PU1; Jul 07: PU1; Jul 08: PU1; Jul 09: PU1; Jul 10: PU1; Jul 15: PU1; Jul 16: PU1; Jul 17: PU1; Jul 18: PU1; Jul 19: PU1; Jul 20: PU1; Jul 21: PU1; Jul 22: PU1; Jul 23: PU1; Jul 24: PU1; Jul 25: PU1
| COLO 3 - CELL 1 Data Hall | Jan 17: J1; Jan 20: J3; Jan 21: J3; Jan 22: J3; Jan 23: J3; Jan 24: J3; Jan 25: EE2; Jan 26: EE2; Jan 27: EE2; Jan 28: EE2; Jan 29: J4; Jan 30: J4; Jan 31: J4; Feb 01: J5; Feb 02: J5; Feb 03: J5; Feb 04: J5; Feb 06: J5; Feb 07: J5; Feb 10: J6; Feb 11: J6; Feb 12: J6; Feb 13: J42; Feb 14: J42; Feb 15: T3; Feb 16: T3; Feb 17: T3; Feb 18: Cx2; Feb 22: S1; Feb 23: S1; Feb 24: S1; Feb 25: S1; Feb 26: S1; Feb 27: S1; Mar 06: S2; Mar 07: S2; Mar 08: S2; Mar 09: S2; Mar 10: S2; Mar 11: EE32; Mar 12: EE32; Mar 13: EE32; Mar 18: EE17; Mar 19: EE17; Mar 20: EE17; Mar 21: EE17; Mar 22: EE17; Mar 23: EE17; Mar 24: EE17; Apr 14: EE19; Apr 15: EE19; Apr 16: EE19
[270 empty] | GSD | GSD | GSD | EE1 | EE1 | EE1 | EE1 | EE1 | [12 empty] | J16 | J16 | J16 | J16 |  |  |  | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [7 empty] | S2 | S2 | S2 | S2
[273 empty] | GSC | GSC | GSC | GSC | [17 empty] | J37 | J37 | J37 | J37 | J37 | J23 | J23 | [13 empty] | J21 | J21 | J21 | J21
[276 empty] | J44 | J44 | [21 empty] | J33 | J33 | J33 | J33 | J33 | J33 | J33
[277 empty] | T1 | T1 | T1 | [19 empty] | EE7 | EE7 | EE7 | EE7 | EE7 | EE7
| COLO 3 - CELL 1 Electrical Room | Jan 25: J3; Jan 26: J3; Jan 27: J3; Jan 28: J3; Jan 29: J3; Jan 30: J3; Jan 31: EE2; Feb 01: EE2; Feb 02: EE2; Feb 03: EE2; Feb 04: EE2; Feb 05: EE2; Feb 06: EE2; Feb 07: EE2; Feb 08: EE2; Feb 09: EE2; Feb 10: EE2; Feb 15: J5; Feb 17: EE35; Feb 18: EE35; Feb 22: J5; Feb 23: J5; Feb 24: J5; Feb 25: J5; Feb 26: J5; Feb 27: J5; Feb 28: J5; Mar 01: J5; Mar 02: J5; Mar 03: J5; Mar 04: J5; Mar 05: T1; Mar 06: T1; Mar 07: Cx2; Mar 10: EE53; Mar 11: EE53; Mar 12: EE53; Mar 13: EE53; Mar 14: EE53; Mar 15: EE53; Mar 17: EE29; Mar 18: EE29; Mar 19: EE29; Mar 20: EE29; Mar 21: EE29; Mar 22: EE29; Mar 23: EE29; Mar 24: EE29; Mar 25: EE29; Mar 26: EE29; Mar 27: EE29; Mar 28: EE29; Mar 29: EE29; Mar 31: EE47; Apr 01: EE47; Apr 02: EE47; Apr 03: EE47; Apr 04: EE47; Apr 05: EE47; Apr 06: EE47; Apr 07: EE47; Apr 08: EE47; Apr 09: EE47; Apr 10: EE47; Apr 11: EE47
[283 empty] | GSD | GSD | J4 | J4 | J4 | J4 | J4 | J4 | J4 | J4 | J4 | [37 empty] | EE59 | EE59 | EE59 | EE59
[285 empty] | GSC | GSC | EE1
| COLO 3 - CELL 1 Mechanical Gallery | Feb 13: GSD; Feb 14: GSD; Feb 15: EE1; Feb 16: EE1; Feb 17: EE1; Feb 18: EE1; Feb 19: J44; Feb 20: J44; Feb 21: J44; Feb 22: J44; Feb 23: J44; Feb 24: J44; Feb 25: J44; Mar 04: J4; Mar 05: J4; Mar 06: J5; Mar 11: Cx2; Mar 12: Cx2; Mar 13: Cx2; Mar 25: E39; Mar 26: E39; Mar 27: E39; Mar 28: E39; Mar 29: E39; Mar 30: E39; Mar 31: E39; Apr 01: E39; Apr 02: E39; Apr 03: EE60; Apr 04: EE60; Apr 05: EE60; Apr 06: EE60; Apr 07: EE60
[287 empty] | GSC | GSC | GSC | [8 empty] | GPA | GPA | GPA | GPA | GPA | GPA | GPA | GPA | J5 | J5 |  |  |  |  | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA
[307 empty] | J20 | J20 | J20 | J20 | J20 | EE35 | EE35 | EE57 | EE57 | EE57 | EE57 | EE57 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42
[308 empty] | T1 | T1 | T1
| COLO 3 - CELL 2 Data Hall | Jan 29: J1; Jan 30: J3; Jan 31: J3; Feb 01: J3; Feb 03: EE2; Feb 04: EE2; Feb 05: EE2; Feb 06: J4; Feb 07: J4; Feb 08: J4; Feb 09: J4; Feb 10: J4; Feb 13: J5; Feb 14: J5; Feb 18: J6; Feb 19: J6; Feb 20: J6; Feb 21: J42; Feb 22: J42; Feb 24: T3; Feb 25: T3; Feb 26: Cx2; Mar 04: S1; Mar 05: S1; Mar 06: S1; Mar 07: S1; Mar 08: S1; Mar 14: S2; Mar 15: S2; Mar 16: S2; Mar 17: S2; Mar 18: S2; Mar 19: EE32; Mar 20: EE32; Mar 21: EE32; Mar 27: EE17; Mar 28: EE17; Mar 29: EE17; Mar 30: EE17; Mar 31: EE17; Apr 01: EE17; May 09: EE19; May 10: EE19; May 11: EE19; May 12: EE19
[278 empty] | GSD | GSD | GSD | GSD | GSD | J5 | J5 | J5 | [12 empty] | J16 | J16 | J16 | J16 | J16 | J16 |  |  | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [7 empty] | S2 | S2 | S2 | S2 | S2 | S2
[283 empty] | EE1 | EE1 | EE1 | EE1 | [17 empty] | J37 | J37 | J37 | J37 | J23 | J23 | J23 | [13 empty] | J21 | J21 | J21
[283 empty] | GSC | GSC | GSC | [22 empty] | J33 | J33 | J33 | J33 | J33 | J33
[285 empty] | J44 | J44 | [21 empty] | EE7 | EE7 | EE7 | EE7 | EE7
[286 empty] | T1 | T1 | T1 | T1
| COLO 3 - CELL 2 Electrical Room | Feb 03: J3; Feb 04: J3; Feb 05: EE2; Feb 06: EE2; Feb 07: J4; Feb 08: J4; Feb 09: J4; Feb 10: J4; Feb 11: J4; Feb 12: J4; Feb 13: J5; Feb 18: Cx2; Mar 17: EE53; Mar 18: EE53; Mar 19: EE53; Mar 20: EE53; Apr 14: EE29; Apr 15: EE29; Apr 16: EE29; Apr 17: EE29; Apr 18: EE29; Apr 19: EE29; Apr 20: EE29; Apr 21: EE29; Apr 22: EE29; Apr 23: EE29; Apr 24: EE29; Apr 25: EE29; Apr 26: EE47; Apr 27: EE47; Apr 28: EE47; Apr 29: EE47; Apr 30: EE47; May 01: EE47; May 02: EE47; May 03: EE47; May 04: EE47; May 05: EE47; May 06: EE47; May 07: EE47; May 08: EE47
[279 empty] | GSD | GSD | GSD | GSD |  |  | J5 | J5 | [70 empty] | EE59 | EE59 | EE59 | EE59 | EE59
[283 empty] | GSC | GSC | EE1 | EE35 | EE35
[287 empty] | T1 | T1 | T1
| COLO 3 - CELL 2 Mechanical Gallery | Feb 11: GSD; Feb 12: GSD; Feb 13: EE1; Feb 14: EE1; Feb 15: EE1; Feb 17: J44; Feb 18: J44; Feb 19: J44; Feb 20: J44; Feb 21: J44; Feb 22: J44; Feb 28: J4; Mar 01: J4; Mar 02: J4; Mar 03: J4; Mar 04: J5; Mar 08: Cx2; Mar 09: Cx2; Mar 10: Cx2; Mar 11: Cx2; Mar 21: GBB; Mar 22: GBB; Mar 23: GBB; Mar 24: GBB; Mar 25: GBB; Mar 26: GBB; Mar 27: GBB; Mar 28: GBB; Mar 29: GBB; Mar 30: GBB; Mar 31: GBB; Apr 01: EE60; Apr 02: EE60; Apr 03: EE60; Apr 04: EE60
[285 empty] | GSC | GSC | [9 empty] | GPA | GPA | GPA | GPA | GPA | GPA | GPA | GPA | J5 | J5 |  |  |  |  | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA | GBA
[305 empty] | J20 | J20 | J20 | J20 |  | EE35 | EE35 | EE57 | EE57 | EE57 | EE57 |  | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42 | EE42
[306 empty] | T1 | T1
| COLO 3 - CELL 2 Punchlist | May 13: PU1; May 14: PU1; May 15: PU1; May 16: PU1; May 17: PU1; May 18: PU1; May 19: PU1; May 20: PU1; May 21: PU1; May 22: PU1; May 23: PU1
| COLO 3 - CELL 3 Data Hall | Feb 21: J1; Feb 22: J3; Feb 23: J3; Feb 24: J3; Feb 25: J3; Feb 26: EE2; Feb 27: EE2; Feb 28: EE2; Mar 03: J4; Mar 04: J4; Mar 05: J4; Mar 08: J5; Mar 09: J5; Mar 10: J5; Mar 13: J6; Mar 14: J6; Mar 15: J6; Mar 17: J42; Mar 18: J42; Mar 19: T3; Mar 20: T3; Mar 21: Cx2; Mar 27: S1; Mar 28: S1; Mar 29: S1; Mar 30: S1; Mar 31: S1; Apr 01: S1; Apr 07: S2; Apr 08: S2; Apr 09: S2; Apr 10: S2; Apr 11: EE32; Apr 12: EE32; Apr 13: EE32; Apr 14: EE32; Apr 15: EE32; Apr 19: EE17; Apr 20: EE17; Apr 21: EE17; Apr 22: EE17; Apr 23: EE17; Apr 24: EE17; Jun 05: EE19; Jun 06: EE19; Jun 07: EE19
[303 empty] | GSD | GSD | GSD | J5 | J5 | J5 | [12 empty] | J16 | J16 | J16 | J16 | J16 | J16 |  |  | EE10 | EE10 | EE10 | EE10 | EE10 | EE10 | [7 empty] | S2 | S2 | S2 | S2 | S2 | S2
[306 empty] | EE1 | EE1 | EE1 | EE1 | EE1 | [16 empty] | J37 | J37 | J37 | J37 | J37 | J23 | J23 | [13 empty] | J21 | J21 | J21
[306 empty] | GSC | GSC | GSC | [23 empty] | J33 | J33 | J33 | J33 | J33
[308 empty] | J44 | J44 | J44 | [21 empty] | EE7 | EE7 | EE7 | EE7
[310 empty] | T1 | T1 | T1
| Electrical Room | Jan 20: J13; Jan 21: J11; Jan 22: MEP1; Jan 23: MEP1; Jan 24: JC; Jan 25: JC; Jan 27: JA; Jan 28: J13; Jan 29: J13; Jan 30: J13; Jan 31: J13; Feb 01: T2; Feb 02: T2; Feb 03: T2; Feb 04: EE28; Mar 03: EE53; Mar 04: EE53; Mar 05: EE53; Mar 06: EE53; Mar 07: EE53; Mar 08: EE53; Mar 09: EE53; Mar 10: EE53; Mar 11: EE53; Mar 12: EE29; Mar 13: EE29; Mar 14: EE29; Mar 15: EE29; Mar 16: EE29; Mar 17: EE29; Mar 18: EE29; Mar 19: EE29; Mar 20: EE29; Mar 21: EE29; Mar 22: EE29; Mar 23: EE29; Mar 24: EE29; Mar 25: EE29; Mar 26: EE29; Mar 27: EE29; Mar 28: EE29; Mar 29: EE24; Mar 30: EE24; Mar 31: EE24; Apr 01: EE24; Apr 02: EE24; Apr 03: EE24; Apr 04: EE24; Apr 05: EE24; Apr 06: EE24; Apr 07: EE24; Apr 08: EE24; Apr 09: EE24; Apr 10: EE24; Apr 11: EE24; Apr 14: EE58; Apr 15: EE58; Apr 16: EE58; Apr 17: EE58
| Entry Room 1 | Jan 21: GSB; Jan 22: J11; Jan 24: MEP1; Jan 25: MEP1; Jan 27: JC; Jan 28: JC; Jan 29: JA; Jan 30: J13; Jan 31: J13; Feb 01: J13; Feb 02: J13; Feb 03: J13; Feb 04: T2; Feb 05: T2; Feb 06: J39; Feb 07: J39; Feb 08: J39; Feb 09: J39; Feb 10: J39; Feb 11: EE54; Feb 12: EE54; Feb 13: EE54; Feb 14: EE54
| Entry Room 2 | Jan 22: GSB; Jan 23: J11; Jan 27: MEP1; Jan 28: MEP1; Jan 29: JC; Jan 30: JC; Jan 31: JA; Feb 01: J13; Feb 02: J13; Feb 03: J13; Feb 04: J13; Feb 05: J13; Feb 06: T2; Feb 07: T2; Feb 10: J39; Feb 11: J39; Feb 12: J39; Feb 13: EE55; Feb 14: EE55; Feb 15: EE55; Feb 16: EE55; Feb 17: EE55
| FCR (Facilities Control Room) | Jan 23: GSB; Jan 24: J11; Jan 29: MEP1; Jan 30: MEP1; Jan 31: JC; Feb 01: JC; Feb 03: JA; Feb 04: J13; Feb 05: J13; Feb 06: J13; Feb 07: J13; Feb 10: T2; Feb 11: T2; Feb 12: J39; Feb 13: J39; Feb 14: J39; Feb 15: EE56; Feb 16: EE56; Feb 17: EE56; Feb 18: EE56; Feb 19: EE56; Feb 20: EE45; Feb 21: EE45; Feb 22: EE45; Feb 23: EE45; Feb 24: EE45; Feb 25: EE45; Feb 26: EE45; Feb 27: EE45; Feb 28: EE45; Mar 01: EE45; Mar 02: EE45; Mar 03: EE45; Mar 04: EE45; Mar 05: EE45; Mar 06: EE45; Mar 07: EE46; Mar 08: EE46; Mar 09: EE46; Mar 10: EE46; Mar 11: EE46; Mar 12: EE46; Mar 13: EE46; Mar 14: EE46; Mar 15: EE46; Mar 16: EE46; Mar 17: EE46; Mar 18: EE46; Mar 19: EE46; Mar 20: EE46; Mar 21: EE44; Mar 22: EE44; Mar 23: EE44; Mar 24: EE44; Mar 25: EE44; Mar 26: EE44; Mar 27: EE44; Mar 28: EE44; Mar 29: EE44; Mar 30: EE44; Mar 31: EE44; Apr 01: EE44; Apr 02: EE44; Apr 03: EE44; Apr 04: EE44; Apr 05: EE52; Apr 06: EE52; Apr 07: EE52; Apr 08: EE52; Apr 09: EE52; Apr 10: EE52; Apr 11: EE52; Apr 12: EE52; Apr 13: EE52; Apr 14: EE52; Apr 15: EE52; Apr 16: EE52; Apr 17: EE52; Apr 18: EE52; Apr 19: EE52; Apr 21: EE49; Apr 22: EE49; Apr 23: EE49; Apr 24: EE49; Apr 25: EE49; Apr 26: EE49; Apr 27: EE49; Apr 28: EE49; Apr 29: EE49; Apr 30: EE49; May 01: EE49; May 02: EE49; May 03: EE49; May 04: EE49; May 05: EE49
[292 empty] | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE50 | EE51 | EE51 | EE51 | EE51 | EE51 | EE51 | EE51 | EE51 | EE51 | EE51 | EE51 | EE51 | EE51 | EE51 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48 | EE48
| Fire Riser Room | Jan 27: GSB; Jan 28: J11; Jan 29: J31; Jan 30: J31; Jan 31: J30; Feb 05: MEP1; Feb 06: MEP1; Feb 07: JC; Feb 08: JC; Feb 09: JC; Feb 10: JC; Feb 11: JA; Feb 12: J5; Feb 13: J5; Feb 14: T2; Feb 15: T2; Feb 18: J17; Feb 19: J17; Feb 20: J17; Feb 21: J17; Feb 22: GSA; Feb 23: GSA; Feb 24: GSA
| Loading Dock | Jan 29: GSB; Jan 30: J11; Feb 15: J5; Feb 16: J5; Feb 17: J5; Feb 18: T2; Feb 19: T2; Feb 20: GPB; Feb 21: GPB; Feb 22: GPB; Feb 23: GPB; Feb 24: GPB; Feb 25: GPB; Feb 26: GPB; Feb 27: GPB; Feb 28: GPB; Mar 01: GPB; Mar 02: GPB; Mar 03: GPB; Mar 04: GPB; Mar 05: GPB; Mar 06: GPB; Mar 07: GPB; Mar 08: GPB; Mar 09: GPB; Mar 10: GPB; Mar 11: EE43; Mar 12: EE43; Mar 13: EE43
[270 empty] | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31
[271 empty] | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31 | J31
[272 empty] | ML21 | [10 empty] | MEP1 | MEP1 | JC | JC
| Punchlist | Jan 27: PU1; Jan 28: PU1; Jan 29: PU1; Jan 30: PU1; Jan 31: PU1; Feb 01: PU1; Feb 02: PU1; Feb 03: PU1; Feb 04: PU1; Feb 05: PU1; Feb 06: PU1; Feb 07: PU1; Feb 08: PU1; Feb 09: PU1; Feb 10: PU1; Feb 11: PU1; Feb 12: PU1; Feb 13: PU1; Feb 14: PU1; Feb 15: PU1; Feb 16: PU1; Feb 17: PU1; Feb 18: PU1; Feb 19: PU1; Feb 20: PU1; Feb 21: PU1; Feb 22: PU1; Feb 23: PU1; Feb 24: PU1; Feb 25: PU1; Feb 26: PU1; Feb 27: PU1; Feb 28: PU1; Mar 01: PU1; Mar 02: PU1; Mar 03: PU1; Mar 04: PU1; Mar 05: PU1; Mar 06: PU1; Mar 07: PU1; Mar 08: PU1; Mar 09: PU1; Mar 10: PU1; Mar 11: PU1; Mar 12: PU1; Mar 13: PU1; Mar 14: PU1; Mar 15: PU1; Mar 16: PU1; Mar 17: PU1; May 06: PU1; May 07: PU1; May 08: PU1; May 09: PU1
| Restrooms & Janitor Room | Jan 28: GSB; Jan 29: J11; Feb 07: MEP1; Feb 08: MEP1; Feb 09: MEP1; Feb 10: MEP1; Feb 11: JC; Feb 12: JC; Feb 13: J5; Feb 14: J5; Feb 15: T2; Feb 16: T2; Feb 17: T2; Feb 18: J17; Feb 19: J17; Feb 20: J17; Feb 21: J17
| SER (Security Equipment Room) | Jan 24: GSB; Jan 25: J11; Jan 31: MEP1; Feb 01: MEP1; Feb 03: JC; Feb 04: JC; Feb 05: JA; Feb 06: J5; Feb 07: J5; Feb 10: T2; Feb 11: T2; Feb 12: J39; Feb 13: J39; Feb 14: J39; Feb 15: S3; Feb 16: S3; Feb 17: S3; Feb 18: S3; Feb 19: S3
| STORAGE (High Value & Secure) Rooms | Jan 25: GSB; Jan 27: J11; Feb 03: MEP1; Feb 04: MEP1; Feb 05: JC; Feb 06: JC; Feb 07: J31; Feb 08: J31; Feb 09: J31; Feb 10: J31; Feb 11: J31; Feb 12: J31; Feb 13: J31; Feb 14: J31; Feb 15: J31; Feb 16: J31; Feb 17: J31; Feb 18: J31; Feb 19: J31; Feb 20: J31; Feb 21: J31; Feb 22: J31; Feb 23: J31; Feb 24: J31; Feb 25: J31; Feb 26: J5; Feb 27: J5; Feb 28: J5; Mar 01: J5; Mar 02: J5; Mar 03: J5; Mar 04: T2; Mar 05: T2; Mar 06: GSB; Mar 07: GSB; Mar 08: GSB; Mar 09: GSB; Mar 10: GSB; Mar 11: GSB; Mar 12: GSB; Mar 13: GSB; Mar 14: GSB; Mar 15: GSB; Mar 16: GSB; Mar 17: GSB
MSFT OFCI ROJ Dates | COLO 3 | Sep 05: ROJ1; Oct 31: ROJ4; Nov 30: ROJ100; Feb 23: ROJ18; Feb 24: ROJ72; Mar 04: ROJ54; Mar 08: ROJ3; Mar 13: ROJ6
[124 empty] | ROJ103 | [55 empty] | ROJ92 | [110 empty] | ROJ21 | ROJ21 | ROJ21 | ROJ21 | ROJ21 |  |  |  |  | ROJ111 | ROJ55 | ROJ55 | ROJ55 | ROJ55 |  |  |  | ROJ5 | ROJ9 | ROJ9 | ROJ9 | ROJ9 | ROJ9
[124 empty] | ROJ117 | [55 empty] | ROJ106 | [114 empty] | ROJ30 | [12 empty] | ROJ12
[124 empty] | ROJ133 | [55 empty] | ROJ120 | [110 empty] | ROJ31 | ROJ31 | ROJ31 | ROJ31 | ROJ31 | [12 empty] | ROJ15
[180 empty] | ROJ123 | [112 empty] | ROJ44 |  | ROJ36 | [12 empty] | ROJ24
[180 empty] | ROJ126 | [110 empty] | ROJ47 | ROJ47 | ROJ47 | ROJ37 | ROJ37 | [12 empty] | ROJ25
[180 empty] | ROJ128 | [114 empty] | ROJ42 | [12 empty] | ROJ56
[291 empty] | ROJ43 | ROJ43 | ROJ43 | ROJ43 | ROJ43 | [12 empty] | ROJ59
[295 empty] | ROJ68 | [12 empty] | ROJ114
[291 empty] | ROJ69 | ROJ69 | ROJ69 | ROJ69 | ROJ69
[292 empty] | ROJ73 | ROJ73 | ROJ73 | ROJ73 | ROJ73
[295 empty] | ROJ78 | ROJ142 | ROJ142 | ROJ142 | ROJ142 | ROJ142
[291 empty] | ROJ79 | ROJ79 | ROJ79 | ROJ79 | ROJ79
ROJ90
[291 empty] | ROJ91 | ROJ91 | ROJ91 | ROJ91 | ROJ91
ROJ140
[291 empty] | ROJ141 | ROJ141 | ROJ141 | ROJ141 | ROJ141
[291 empty] | ROJ145 | ROJ145 | ROJ145 | ROJ145 | ROJ145
| COLO 3-5 | Oct 03: ROJ125; Oct 25: ROJ84
[170 empty] | ROJ85 | ROJ85 | ROJ85 | ROJ85 | ROJ85
| COLO 4 | Sep 05: ROJ118; Sep 09: ROJ2; Oct 31: ROJ96; Jan 04: ROJ26; Mar 02: ROJ50; Mar 30: ROJ13; Apr 05: ROJ7; Apr 10: ROJ74
[124 empty] | ROJ131 | [55 empty] | ROJ101 | [58 empty] | ROJ99 | ROJ28 | ROJ28 | ROJ28 | ROJ28 | ROJ28 | ROJ28 | [54 empty] | ROJ109 | ROJ52 | ROJ52 | [27 empty] | ROJ16 |  | ROJ10 | ROJ10 | ROJ10 | ROJ10 | ROJ10 | ROJ75 | ROJ75 | ROJ75 | ROJ75 | ROJ75
[180 empty] | ROJ104 | [149 empty] | ROJ19
[180 empty] | ROJ107 | [145 empty] | ROJ22 | ROJ22 | ROJ45 | ROJ22 | ROJ22
[180 empty] | ROJ121 | [145 empty] | ROJ48 | ROJ48 | ROJ48 |  | ROJ32
[180 empty] | ROJ130 | [145 empty] | ROJ34 | ROJ34 | ROJ34 | ROJ34 | ROJ34
[180 empty] | ROJ134 | [149 empty] | ROJ38
[180 empty] | ROJ135 | [145 empty] | ROJ39 | ROJ39 | ROJ39 | ROJ39 | ROJ39
ROJ57
ROJ60
ROJ62
ROJ64
ROJ66
[326 empty] | ROJ67 | ROJ67 | ROJ67 | ROJ67 | ROJ67
ROJ80
[326 empty] | ROJ82 | ROJ82 | ROJ82 | ROJ82 | ROJ82
ROJ86
[326 empty] | ROJ88 | ROJ88 | ROJ88 | ROJ88 | ROJ88
ROJ95
ROJ112
ROJ115
ROJ136
[326 empty] | ROJ138 | ROJ138 | ROJ138 | ROJ138 | ROJ138
ROJ143
[326 empty] | ROJ146 | ROJ146 | ROJ146 | ROJ146 | ROJ146
| COLO 5 | Sep 05: ROJ132; Sep 16: ROJ93; Oct 30: ROJ119; Oct 31: ROJ97; Feb 02: ROJ27; Apr 04: ROJ14; Apr 20: ROJ20; Apr 28: ROJ46; May 03: ROJ33; May 07: ROJ87; May 11: ROJ8; May 15: ROJ76
[180 empty] | ROJ102 | [88 empty] | ROJ98 | ROJ29 | ROJ29 | ROJ29 | ROJ29 | ROJ29 | [55 empty] | ROJ17 | ROJ17 | ROJ17 | ROJ17 | ROJ51 | ROJ17 | [15 empty] | ROJ23 |  |  |  |  | ROJ49 | ROJ49 | ROJ49 | ROJ49 | ROJ35 | ROJ35 | ROJ35 | ROJ35 | ROJ35 | [7 empty] | ROJ11
[180 empty] | ROJ105 | [149 empty] | ROJ53 | ROJ53 | ROJ53 | ROJ53 | ROJ53 | ROJ58 | [15 empty] | ROJ40 | [12 empty] | ROJ70 | [7 empty] | ROJ77 | ROJ77 | ROJ77 | ROJ77 | ROJ77
[180 empty] | ROJ108 | [149 empty] | ROJ61 | ROJ61 | ROJ61 | ROJ61 | ROJ61 | ROJ61 | [15 empty] | ROJ41 | [8 empty] | ROJ71 | ROJ71 | ROJ71 | ROJ71 | ROJ71
[180 empty] | ROJ122 | [149 empty] | ROJ94 |  |  |  |  | ROJ63 | [28 empty] | ROJ81
[180 empty] | ROJ124 | [149 empty] | ROJ110 | ROJ65 | ROJ65 | ROJ65 | ROJ65 | ROJ65 | [24 empty] | ROJ83 | ROJ83 | ROJ83 | ROJ83 | ROJ83
[180 empty] | ROJ127 | [149 empty] | ROJ113 | [33 empty] | ROJ89 | ROJ89 | ROJ89 | ROJ89 | ROJ89
[180 empty] | ROJ129 | [149 empty] | ROJ116 | [33 empty] | ROJ144
[330 empty] | ROJ137 | [29 empty] | ROJ147 | ROJ147 | ROJ147 | ROJ147 | ROJ147
[326 empty] | ROJ139 | ROJ139 | ROJ139 | ROJ139 | ROJ139
RFP / PSR | Milestone | May 06: ML21; May 07: ML21; May 08: ML21; May 09: ML21; May 10: ML21; Jun 06: ML21; Jul 24: ML21; Jul 25: ML21; Jul 26: ML21; Jul 27: ML21; Jul 28: ML21; Jul 29: ML21; Jul 30: ML21; Jul 31: ML21; Aug 01: ML21; Aug 02: ML21; Aug 03: ML21; Aug 04: ML21; Aug 05: ML21; Aug 06: ML21; Aug 07: ML21; Aug 08: ML21; Aug 19: ML21; Aug 20: ML21; Aug 21: ML21; Aug 22: ML21; Aug 23: ML21; Aug 24: ML21; Aug 25: ML21; Aug 26: ML21; Aug 27: ML21; Aug 28: ML21; Aug 29: ML21; Aug 30: ML21; Aug 31: ML21; Sep 01: ML21; Sep 02: ML21; Sep 03: ML21; Sep 04: ML21; Sep 30: ML21
Site Prep/ Mobilization | Milestone
Site Utilities | Overall | Sep 23: J22; Sep 24: J22; Sep 25: J22; Sep 26: J22; Sep 27: J22; Sep 28: J22; Sep 29: J22; Sep 30: J22; Oct 01: J22; Oct 02: J22; Oct 03: J22; Oct 04: J22; Oct 05: J22; Oct 06: J22; Oct 07: J22; Oct 08: J22; Oct 09: J22; Oct 10: J22; Oct 11: J22; Oct 12: J22; Oct 13: J22; Oct 14: J22; Oct 15: J22; Oct 16: J22; Oct 17: J22; Oct 18: J22; Oct 19: J22; Oct 20: J22; Oct 21: J22; May 05: MLPP
[153 empty] | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36 | J36
[184 empty] | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41 | J41
[189 empty] | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43 | J43
[195 empty] | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38 | E38
| Under Building Pad | Sep 30: EE36; Oct 01: EE36; Oct 02: EE36; Oct 03: EE36; Oct 04: EE36; Oct 05: EE36; Oct 06: EE36; Oct 07: EE36; Oct 08: EE36; Oct 09: EE36; Oct 10: EE36; Oct 11: EE36; Oct 12: EE36; Oct 13: EE36; Oct 14: EE36; Oct 15: EE36; Oct 16: EE36; Oct 17: EE36; Oct 18: EE36; Oct 19: EE36; Oct 20: EE36; Oct 21: EE36; Oct 22: EE36; Oct 23: EE36; Oct 24: EE36; Oct 25: EE36; Oct 26: EE36; Oct 27: EE36; Oct 28: EE36; Oct 29: EE36; Oct 30: EE36; Nov 07: EW1; Nov 08: EW1
[137 empty] | EE37 | EE37 | EE37 | EE37 | EE37 | EE37 | EE37 | EE37 | EE37 | EE37 | EE37 | EE37 | EE37 | EE37 | EE37 | EE37 | EE37
Note on DU5: Activity Name: Start First ROJ CLAYCO Took over Storage 9/2/2024 Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on EI5: Activity Name: Complete Foundation Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 19-Sep-24 End Date: 19-Sep-24
Note on ET5: Activity Name: Building Footprint Pad Ready Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 30-Sep-24 End Date: 30-Sep-24
Note on FE5: Activity Name: Clayco Proposal Due date Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 11-Oct-24 End Date: 11-Oct-24
Note on HQ5: Activity Name: Complete Superstructure Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Dec-24 End Date: 14-Dec-24
Note on IC5: Activity Name: Complete Earthwork & U/G Site Utilities Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 26-Dec-24 End Date: 26-Dec-24
Note on ID5: Activity Name: Complete SOG Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 27-Dec-24 End Date: 27-Dec-24
Note on IX5: Activity Name: Complete Weather Tight Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 16-Jan-25 End Date: 16-Jan-25
Note on KL5: Activity Name: GC Mobilization Start Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 25-Feb-25 End Date: 25-Feb-25
Note on KT5: Activity Name: Earthworks & U/G Utilities Start Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 05-Mar-25 End Date: 05-Mar-25
Note on KW5: Activity Name: Complete Last ROJ Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 08-Mar-25 End Date: 08-Mar-25
Note on LD5: Activity Name: Generator Ready for Fuel (Exterior Yard) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 15-Mar-25 End Date: 15-Mar-25
Note on MC5: Activity Name: Start L1 CX Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 09-Apr-25 End Date: 09-Apr-25
Note on NC5: Activity Name: Complete Utility Power- On Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 05-May-25 End Date: 05-May-25
Note on OG5: Activity Name: Complete L1 Cx (All Red Tags/ ROJ) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 04-Jun-25 End Date: 04-Jun-25
Note on PI5: Activity Name: Complete L2 Cx (Yellow Tag) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 02-Jul-25 End Date: 02-Jul-25
Note on QZ5: Activity Name: Beneficial Use Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on RA5: Activity Name: Start L4 Cx (Blue Tag) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 15-Aug-25 End Date: 15-Aug-25
Note on RF5: Activity Name: RNI Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 20-Aug-25 End Date: 20-Aug-25
Note on RP5: Activity Name: Complete BAS Testing Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 30-Aug-25 End Date: 30-Aug-25
Note on RU5: Activity Name: Phase 2 Security Pre-Testing Complete Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 04-Sep-25 End Date: 04-Sep-25
Note on SF5: Activity Name: Complete L4 Cx (Blue Tag) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 15-Sep-25 End Date: 15-Sep-25
Note on SG5: Activity Name: Start L5 Cx (White Tag) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 16-Sep-25 End Date: 16-Sep-25
Note on SI5: Activity Name: Cx L5 IST Complete (White Tag) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 18-Sep-25 End Date: 18-Sep-25
Note on SP5: Activity Name: Phase 3 Security Pre-Testing Complete Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 25-Sep-25 End Date: 25-Sep-25
Note on SU5: Activity Name: TCO / C of O Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 30-Sep-25 End Date: 30-Sep-25
Note on SV5: Activity Name: Beneficial Use - All Facility & Network Telecom Access/ Devices etc. Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 01-Oct-25 End Date: 01-Oct-25
Note on SW5: Activity Name: Final Completion/ Turnover to Operations Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 02-Oct-25 End Date: 02-Oct-25
Note on EI6: Activity Name: Start Foundation Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 19-Sep-24 End Date: 19-Sep-24
Note on ET6: Activity Name: PSR (Contract) Executed Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 30-Sep-24 End Date: 30-Sep-24
Note on HQ6: Activity Name: Complete U/G Utilities (No Elec) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Dec-24 End Date: 14-Dec-24
Note on NC6: Activity Name: Start L2 CX (Yellow Tag) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 05-May-25 End Date: 05-May-25
Note on OG6: Activity Name: Start L3 CX (Green Tag) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 04-Jun-25 End Date: 04-Jun-25
Note on QZ6: Activity Name: Beneficial Use - Distributed Antenna System (DAS) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on RP6: Activity Name: Complete EPMS Testing Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 30-Aug-25 End Date: 30-Aug-25
Note on SV6: Activity Name: Substantial Completion Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 01-Oct-25 End Date: 01-Oct-25
Note on SW6: Activity Name: Security Lockdown Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 02-Oct-25 End Date: 02-Oct-25
Note on EI7: Activity Name: Start Superstructure Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 19-Sep-24 End Date: 19-Sep-24
Note on HQ7: Activity Name: Complete U/G Utilities/ MV UG Electrical Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Dec-24 End Date: 14-Dec-24
Note on QZ7: Activity Name: Beneficial Use - Facility Cable Room (FCR) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on RP7: Activity Name: Complete Fire Alarm Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 30-Aug-25 End Date: 30-Aug-25
Note on QZ8: Activity Name: Beneficial Use - Meet Me Room or Entry Rooms (MMR/ER) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on RP8: Activity Name: Phase 1 Security Pre-Testing Complete Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 30-Aug-25 End Date: 30-Aug-25
Note on QZ9: Activity Name: Beneficial Use - Middle of Row (MOR) Cabinets Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on QZ10: Activity Name: Beneficial Use - Radio Over Internet Protocol (RoIP) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on QZ11: Activity Name: Beneficial Use - Secure & High Value Storage Rooms Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on QZ12: Activity Name: Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on QZ13: Activity Name: Beneficial Use - Security Equipment Room (SER) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on QZ14: Activity Name: Beneficial Use (IDF#1,#2,#3 & #4) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on QZ15: Activity Name: Beneficial Use- Facilities Operations Center (FOC) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on QZ16: Activity Name: Beneficial Use- Regional Network Gateway (RNG) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on QZ17: Activity Name: Beneficial Use- Security Low Voltage (SLV) System Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on QZ18: Activity Name: Beneficial Use- Security Operations Center (SOC) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on QZ19: Activity Name: Complete CX L3 (Green Tag) Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on DU23: Activity Name: Start First ROJ CLAYCO Took over Storage 9/2/2024 Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on EF23: Activity Name: Foundation Start Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 16-Sep-24 End Date: 16-Sep-24
Note on FY23: Activity Name: Complete Foundation Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on GA23: Activity Name: Start Superstructure Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 02-Nov-24 End Date: 02-Nov-24
Note on ID23: Activity Name: Complete U/G Utilities/ MV UG Electric Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 27-Dec-24 End Date: 27-Dec-24
Note on IH23: Activity Name: Complete Superstructure Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 31-Dec-24 End Date: 31-Dec-24
Note on IR23: Activity Name: Complete SOG Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 10-Jan-25 End Date: 10-Jan-25
Note on JL23: Activity Name: Weather Tight Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 30-Jan-25 End Date: 30-Jan-25
Note on LS23: Activity Name: Complete Last ROJ Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on MQ23: Activity Name: Start L1 CX Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 23-Apr-25 End Date: 23-Apr-25
Note on MR23: Activity Name: Generator Ready for Fuel Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 24-Apr-25 End Date: 24-Apr-25
Note on NC23: Activity Name: Complete Utility Power- On Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 05-May-25 End Date: 05-May-25
Note on ND23: Activity Name: Start L2 CX (Yellow Tag) Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 06-May-25 End Date: 06-May-25
Note on OW23: Activity Name: Start L3 CX Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 20-Jun-25 End Date: 20-Jun-25
Note on PZ23: Activity Name: Complete L1 Cx (All Red Tags/ ROJ) Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 19-Jul-25 End Date: 19-Jul-25
Note on QZ23: Activity Name: Complete L2 Cx (Yellow Tag) Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on SJ23: Activity Name: Beneficial Use Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 19-Sep-25 End Date: 19-Sep-25
Note on SK23: Activity Name: Start L4 Cx (Blue Tag) Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 20-Sep-25 End Date: 20-Sep-25
Note on SO23: Activity Name: Ready for Network Install Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 24-Sep-25 End Date: 24-Sep-25
Note on SU23: Activity Name: Complete BAS Testing Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 30-Sep-25 End Date: 30-Sep-25
Note on SY23: Activity Name: Phase 2 Security Pre-Testing Complete Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 04-Oct-25 End Date: 04-Oct-25
Note on TK23: Activity Name: Complete L4 Cx (Blue Tag) Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 16-Oct-25 End Date: 16-Oct-25
Note on TL23: Activity Name: Start L5 Cx (White Tag) Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 17-Oct-25 End Date: 17-Oct-25
Note on TO23: Activity Name: Cx L5 IST Complete Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 20-Oct-25 End Date: 20-Oct-25
Note on TR23: Activity Name: Phase 3 Security Pre-Testing Complete Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 23-Oct-25 End Date: 23-Oct-25
Note on TX23: Activity Name: Substantial Completion Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 29-Oct-25 End Date: 29-Oct-25
Note on UF23: Activity Name: Final Completion/ Turnover to Operations Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 06-Nov-25 End Date: 06-Nov-25
Note on SJ24: Activity Name: Beneficial Use - Distrbuted Antenna System (DAS) Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 19-Sep-25 End Date: 19-Sep-25
Note on SU24: Activity Name: Complete EPMS Testing Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 30-Sep-25 End Date: 30-Sep-25
Note on TX24: Activity Name: TCO / C of O Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 29-Oct-25 End Date: 29-Oct-25
Note on UF24: Activity Name: Security Lockdown Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 06-Nov-25 End Date: 06-Nov-25
Note on SJ25: Activity Name: Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 19-Sep-25 End Date: 19-Sep-25
Note on SU25: Activity Name: Complete Fire Alarm Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 30-Sep-25 End Date: 30-Sep-25
Note on SJ26: Activity Name: Beneficial Use - Security Low Voltage (SLV) Systems Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 19-Sep-25 End Date: 19-Sep-25
Note on SU26: Activity Name: Phase 1 Security Pre-Testing Complete Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 30-Sep-25 End Date: 30-Sep-25
Note on SJ27: Activity Name: Beneficial Use- (IDF#1,#2,#3 & #4) Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 19-Sep-25 End Date: 19-Sep-25
Note on SJ28: Activity Name: Beneficial Use- Facilities Operations Center (FOC) Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 19-Sep-25 End Date: 19-Sep-25
Note on SJ29: Activity Name: Beneficial Use- Facility Cable Room (FCR) Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 19-Sep-25 End Date: 19-Sep-25
Note on SJ30: Activity Name: Beneficial Use- Meet Me Room or Entry Rooms (MMR/ER) Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 19-Sep-25 End Date: 19-Sep-25
Note on SJ31: Activity Name: Beneficial Use- Middle of Row (MOR) Cabinets Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 19-Sep-25 End Date: 19-Sep-25
Note on SJ32: Activity Name: Beneficial Use- Radio OVer Internet Protocol (RoIP) Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 19-Sep-25 End Date: 19-Sep-25
Note on SJ33: Activity Name: Beneficial Use- Secure & High Value Storage Rooms Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 19-Sep-25 End Date: 19-Sep-25
Note on SJ34: Activity Name: CX L3 Complete Phase: Milestones Location: COLO 4 Trade: Milestone Start Date: 19-Sep-25 End Date: 19-Sep-25
Note on DU38: Activity Name: Start First ROJ - CLAYCO Took over Storage 9/2/2024 Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on DY38: Activity Name: Foundation Start Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 09-Sep-24 End Date: 09-Sep-24
Note on GK38: Activity Name: Complete Foundation Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 12-Nov-24 End Date: 12-Nov-24
Note on GM38: Activity Name: Start Superstructure Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 14-Nov-24 End Date: 14-Nov-24
Note on IU38: Activity Name: Complete U/G Utilities/ MV UG Electric Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 13-Jan-25 End Date: 13-Jan-25
Note on IW38: Activity Name: Complete Superstructure Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 15-Jan-25 End Date: 15-Jan-25
Note on JG38: Activity Name: Complete SOG Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 25-Jan-25 End Date: 25-Jan-25
Note on KA38: Activity Name: Entire Building Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 14-Feb-25 End Date: 14-Feb-25
Note on LT38: Activity Name: Complete Last ROJ Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 31-Mar-25 End Date: 31-Mar-25
Note on MO38: Activity Name: Start L1 CX Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 21-Apr-25 End Date: 21-Apr-25
Note on NC38: Activity Name: Complete Utility Power- On Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 05-May-25 End Date: 05-May-25
Note on OC38: Activity Name: Generator Ready for Fuel Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 31-May-25 End Date: 31-May-25
Note on OH38: Activity Name: Start L2 CX (Yellow Tag) Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 05-Jun-25 End Date: 05-Jun-25
Note on PZ38: Activity Name: Start L3 CX Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 19-Jul-25 End Date: 19-Jul-25
Note on QQ38: Activity Name: Complete L1 Cx (All Red Tags/ ROJ) Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 05-Aug-25 End Date: 05-Aug-25
Note on RT38: Activity Name: Complete L2 Cx (Yellow Tag) Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 03-Sep-25 End Date: 03-Sep-25
Note on TF38: Activity Name: Beneficial Use Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 11-Oct-25 End Date: 11-Oct-25
Note on TL38: Activity Name: Ready for Network Install Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 17-Oct-25 End Date: 17-Oct-25
Note on TZ38: Activity Name: Complete BAS Testing Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 31-Oct-25 End Date: 31-Oct-25
Note on UC38: Activity Name: Phase 2 Security Pre-Testing Complete Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 03-Nov-25 End Date: 03-Nov-25
Note on UO38: Activity Name: Complete L4 Cx (Blue Tag) Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 15-Nov-25 End Date: 15-Nov-25
Note on TF39: Activity Name: Beneficial Use - Distributed Antenna System (DAS) Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 11-Oct-25 End Date: 11-Oct-25
Note on TL39: Activity Name: Start L4 Cx (Blue Tag) Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 17-Oct-25 End Date: 17-Oct-25
Note on TZ39: Activity Name: Complete EPMS Testing Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 31-Oct-25 End Date: 31-Oct-25
Note on TF40: Activity Name: Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 11-Oct-25 End Date: 11-Oct-25
Note on TZ40: Activity Name: Complete Fire Alarm Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 31-Oct-25 End Date: 31-Oct-25
Note on TF41: Activity Name: Beneficial Use - Security Low Voltage (SLV) System Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 11-Oct-25 End Date: 11-Oct-25
Note on TZ41: Activity Name: Phase 1 Security Pre-Testing Complete Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 31-Oct-25 End Date: 31-Oct-25
Note on TF42: Activity Name: Beneficial Use (IDF#1,#2,#3 & #4) Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 11-Oct-25 End Date: 11-Oct-25
Note on TF43: Activity Name: Beneficial Use Facility Cable Room (FCR) Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 11-Oct-25 End Date: 11-Oct-25
Note on TF44: Activity Name: Beneficial Use Meet Me Room or Entry Rooms (MMR/ER) Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 11-Oct-25 End Date: 11-Oct-25
Note on TF45: Activity Name: Beneficial Use Secure & High Value Storage Rooms Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 11-Oct-25 End Date: 11-Oct-25
Note on TF46: Activity Name: Beneficial Use- Middle of Row (MOR) Cabinets Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 11-Oct-25 End Date: 11-Oct-25
Note on TF47: Activity Name: Beneficial Use- Radio Over Internet Protocol (RoIP) Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 11-Oct-25 End Date: 11-Oct-25
Note on TF48: Activity Name: CX Level 3 Complete Phase: Milestones Location: COLO 5 Trade: Milestone Start Date: 11-Oct-25 End Date: 11-Oct-25
Note on EF52: Activity Name: GC Mobilization Finish/ Site Secured Phase: Milestones Location: General Trade: Milestone Start Date: 16-Sep-24 End Date: 16-Sep-24
Note on DF53: Activity Name: CHI11: Construction Start Phase: Milestones Location: Key Milestone Trade: Milestone Start Date: 21-Aug-24 End Date: 21-Aug-24
Note on DU53: Activity Name: CHI11: Building Pad Ready Phase: Milestones Location: Key Milestone Trade: Milestone Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on DZ53: Activity Name: CHI11: Structure Start Phase: Milestones Location: Key Milestone Trade: Milestone Start Date: 10-Sep-24 End Date: 10-Sep-24
Note on GK53: Activity Name: CHI11: Foundations Complete Phase: Milestones Location: Key Milestone Trade: Milestone Start Date: 12-Nov-24 End Date: 12-Nov-24
Note on HF53: Activity Name: CHI11: Structure Complete Phase: Milestones Location: Key Milestone Trade: Milestone Start Date: 03-Dec-24 End Date: 03-Dec-24
Note on IC53: Activity Name: CHI11: Utilities Available to Owner (Gas Service N/A) Phase: Milestones Location: Key Milestone Trade: Milestone Start Date: 26-Dec-24 End Date: 26-Dec-24
Note on IH53: Activity Name: CHI11: Roofing Complete Phase: Milestones Location: Key Milestone Trade: Milestone Start Date: 31-Dec-24 End Date: 31-Dec-24
Note on IW53: Activity Name: CHI11: Enclosure Complete Phase: Milestones Location: Key Milestone Trade: Milestone Start Date: 15-Jan-25 End Date: 15-Jan-25
Note on NC53: Activity Name: CHI11: Electrical Service Available Phase: Milestones Location: Key Milestone Trade: Milestone Start Date: 05-May-25 End Date: 05-May-25
Note on DY58: Activity Name: Foundations / Stem Walls (50% Complete) Phase: Milestones Location: Milestone Trade: Milestone Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on FD58: Activity Name: Foundations / Stem Walls (100% Complete) Phase: Milestones Location: Milestone Trade: Milestone Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on SV58: Activity Name: Admin & COLO3-5 Fitout Complete Phase: Milestones Location: Milestone Trade: Milestone Start Date: 01-Oct-25 End Date: 01-Oct-25
Note on BX61: Activity Name: BIM- BIM Kickoff Phase: BIM Location: BIM Trade: BIM Start Date: 18-Jul-24 End Date: 18-Jul-24
Note on BY61: Activity Name: BIM- UG BIM Co-ordination Phase: BIM Location: BIM Trade: BIM Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on DV61: Activity Name: BIM- Above ground BIM Co-ordination Phase: BIM Location: BIM Trade: BIM Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on FY64: Activity Name: CFCI- Cable Bus Fabrication/ Lead Time Phase: CFCI Procurement Location: CFCI Trade: CFCI Start Date: 31-Oct-24 End Date: 03-Mar-25
Note on FY65: Activity Name: CFCI- HACs Fabrication/ Lead Time Phase: CFCI Procurement Location: CFCI Trade: CFCI Start Date: 31-Oct-24 End Date: 05-Dec-24
Note on DG66: Activity Name: CFCI- MV Cables Fabrication/ Lead Time Phase: CFCI Procurement Location: CFCI Trade: CFCI Start Date: 22-Aug-24 End Date: 29-Apr-25
Note on DF67: Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Phase: CFCI Procurement Location: CFCI Trade: CFCI Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OW69: Activity Name: Control Power Checks Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Start Date: 20-Jun-25 End Date: 28-Jun-25
Note on PG69: Activity Name: EPMS Point to Point Checks Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Start Date: 30-Jun-25 End Date: 10-Jul-25
Note on PR69: Activity Name: FTE Energizations [480v] Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Start Date: 11-Jul-25 End Date: 15-Jul-25
Note on PZ69: Activity Name: Control Power Checks Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Start Date: 19-Jul-25 End Date: 29-Jul-25
Note on QK69: Activity Name: EPMS Point to Point Checks Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Start Date: 30-Jul-25 End Date: 07-Aug-25
Note on QT69: Activity Name: FTE Energizations [480v] Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Start Date: 08-Aug-25 End Date: 12-Aug-25
Note on QY69: Activity Name: Startups Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RN69: Activity Name: Loadbanking Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Start Date: 28-Aug-25 End Date: 02-Sep-25
Note on PW70: Activity Name: Startups Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QL70: Activity Name: Loadbanking Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Start Date: 31-Jul-25 End Date: 04-Aug-25
Note on PB74: Activity Name: Control Power Checks Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Start Date: 25-Jun-25 End Date: 03-Jul-25
Note on PN74: Activity Name: EPMS Point to Point Checks Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Start Date: 07-Jul-25 End Date: 15-Jul-25
Note on PW74: Activity Name: FTE Energizations [480v] Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Start Date: 16-Jul-25 End Date: 19-Jul-25
Note on QE74: Activity Name: Control Power Checks Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Start Date: 24-Jul-25 End Date: 02-Aug-25
Note on QP74: Activity Name: EPMS Point to Point Checks Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Start Date: 04-Aug-25 End Date: 12-Aug-25
Note on QY74: Activity Name: FTE Energizations [480v] Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Start Date: 13-Aug-25 End Date: 18-Aug-25
Note on RE74: Activity Name: Startups Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RT74: Activity Name: Loadbanking Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Start Date: 03-Sep-25 End Date: 08-Sep-25
Note on QB75: Activity Name: Startups Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QQ75: Activity Name: Loadbanking Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Start Date: 05-Aug-25 End Date: 08-Aug-25
Note on PA79: Activity Name: Control Power Checks Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PO79: Activity Name: EPMS Point to Point Checks Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Start Date: 08-Jul-25 End Date: 18-Jul-25
Note on PZ79: Activity Name: FTE Energizations [480v] Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Start Date: 19-Jul-25 End Date: 24-Jul-25
Note on QR79: Activity Name: Control Power Checks Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Start Date: 06-Aug-25 End Date: 14-Aug-25
Note on RK79: Activity Name: Control Power Checks Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Start Date: 25-Aug-25 End Date: 03-Sep-25
Note on RU79: Activity Name: EPMS Point to Point Checks Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Start Date: 04-Sep-25 End Date: 13-Sep-25
Note on SF79: Activity Name: FTE Energizations [480v] Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Start Date: 15-Sep-25 End Date: 19-Sep-25
Note on SK79: Activity Name: Startups Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on TA79: Activity Name: Loadbanking Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Start Date: 06-Oct-25 End Date: 11-Oct-25
Note on QF80: Activity Name: Startups Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QU80: Activity Name: Loadbanking Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Start Date: 09-Aug-25 End Date: 14-Aug-25
Note on RA80: Activity Name: EPMS Point to Point Checks Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Start Date: 15-Aug-25 End Date: 25-Aug-25
Note on RL80: Activity Name: FTE Energizations [480v] Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Start Date: 26-Aug-25 End Date: 29-Aug-25
Note on RP80: Activity Name: Startups Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on SG80: Activity Name: Loadbanking Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Start Date: 16-Sep-25 End Date: 19-Sep-25
Note on OP84: Activity Name: Control Power Checks Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on PA84: Activity Name: EPMS Point to Point Checks Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Start Date: 24-Jun-25 End Date: 02-Jul-25
Note on PJ84: Activity Name: FTE Energizations [480v] Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Start Date: 03-Jul-25 End Date: 09-Jul-25
Note on PY84: Activity Name: Control Power Checks Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Start Date: 18-Jul-25 End Date: 28-Jul-25
Note on QP84: Activity Name: Control Power Checks Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Start Date: 04-Aug-25 End Date: 12-Aug-25
Note on QY84: Activity Name: EPMS Point to Point Checks Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Start Date: 13-Aug-25 End Date: 22-Aug-25
Note on RI84: Activity Name: FTE Energizations [480v] Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Start Date: 23-Aug-25 End Date: 27-Aug-25
Note on SD84: Activity Name: Loadbanking Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Start Date: 13-Sep-25 End Date: 17-Sep-25
Note on PQ85: Activity Name: Startups Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on QE85: Activity Name: Loadbanking Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on QJ85: Activity Name: EPMS Point to Point Checks Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Start Date: 29-Jul-25 End Date: 06-Aug-25
Note on QS85: Activity Name: FTE Energizations [480v] Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Start Date: 07-Aug-25 End Date: 11-Aug-25
Note on QX85: Activity Name: Startups Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RM85: Activity Name: Loadbanking Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Start Date: 27-Aug-25 End Date: 30-Aug-25
Note on RN86: Activity Name: Startups Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on NC89: Activity Name: 2Cx- Yellow Tags Phase: Commissioning Location: COLO 3 Trade: TBD Start Date: 05-May-25 End Date: 28-May-25
Note on OL89: Activity Name: 2Cx- Yellow Tags Phase: Commissioning Location: COLO 3 Trade: TBD Start Date: 09-Jun-25 End Date: 02-Jul-25
Note on PV89: Activity Name: 3Cx- Loadbanking Phase: Commissioning Location: COLO 3 Trade: TBD Start Date: 15-Jul-25 End Date: 18-Jul-25
Note on RA89: Activity Name: 4Cx- Testing <MSFT Duration> Phase: Commissioning Location: COLO 3 Trade: Microsoft Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on SG89: Activity Name: 5Cx- Testing <MSFT Duration> Phase: Commissioning Location: COLO 3 Trade: Microsoft Start Date: 16-Sep-25 End Date: 18-Sep-25
Note on NM90: Activity Name: 2Cx- Yellow Tags Phase: Commissioning Location: COLO 3 Trade: TBD Start Date: 15-May-25 End Date: 07-Jun-25
Note on PA90: Activity Name: 3Cx- FTE Energizations [480v] Phase: Commissioning Location: COLO 3 Trade: TBD Start Date: 24-Jun-25 End Date: 27-Jun-25
Note on PE90: Activity Name: 3Cx- Startups Phase: Commissioning Location: COLO 3 Trade: TBD Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on NY91: Activity Name: 2Cx- Yellow Tags Phase: Commissioning Location: COLO 3 Trade: TBD Start Date: 27-May-25 End Date: 18-Jun-25
Note on OP92: Activity Name: 3Cx- EPMS Point to Point Checks Phase: Commissioning Location: COLO 3 Trade: TBD Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on OO93: Activity Name: 3Cx- Install Metering Cabinet [Prior to Energization] Phase: Commissioning Location: COLO 3 Trade: TBD Start Date: 12-Jun-25 End Date: 18-Jun-25
Note on OG96: Activity Name: Control Power Checks Phase: Commissioning Location: COLO 3 - CELL 1 Energizations & Startups (Level 3) Trade: Electrical Start Date: 04-Jun-25 End Date: 12-Jun-25
Note on OL97: Activity Name: Control Power Checks Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Start Date: 09-Jun-25 End Date: 18-Jun-25
Note on OV97: Activity Name: EPMS Point to Point Checks Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Start Date: 19-Jun-25 End Date: 27-Jun-25
Note on PE97: Activity Name: FTE Energizations [480v] Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Start Date: 28-Jun-25 End Date: 02-Jul-25
Note on PJ97: Activity Name: Startups Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on PZ97: Activity Name: Loadbanking Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Start Date: 19-Jul-25 End Date: 23-Jul-25
Note on ND101: Activity Name: 2Cx- Yellow Tags Phase: Commissioning Location: COLO 4 Trade: TBD Start Date: 06-May-25 End Date: 29-May-25
Note on OC101: Activity Name: 2Cx- Yellow Tags Phase: Commissioning Location: COLO 4 Trade: TBD Start Date: 31-May-25 End Date: 24-Jun-25
Note on QC101: Activity Name: 2Cx- Yellow Tags Phase: Commissioning Location: COLO 4 Trade: TBD Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on SK101: Activity Name: 4Cx- Testing <MSFT Duration> Phase: Commissioning Location: COLO 4 Trade: Microsoft Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TL101: Activity Name: 5Cx- Testing <MSFT Duration> Phase: Commissioning Location: COLO 4 Trade: Microsoft Start Date: 17-Oct-25 End Date: 20-Oct-25
Note on PD102: Activity Name: 2Cx- Yellow Tags Phase: Commissioning Location: COLO 4 Trade: TBD Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on OH106: Activity Name: 2Cx- Yellow Tags Phase: Commissioning Location: COLO 5 Trade: TBD Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on QU106: Activity Name: 2Cx- Yellow Tags Phase: Commissioning Location: COLO 5 Trade: TBD Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on TL106: Activity Name: 4Cx- Testing <MSFT Duration> Phase: Commissioning Location: COLO 5 Trade: Microsoft Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on PE107: Activity Name: 2Cx- Yellow Tags Phase: Commissioning Location: COLO 5 Trade: TBD Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PV108: Activity Name: 2Cx- Yellow Tags Phase: Commissioning Location: COLO 5 Trade: TBD Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on FO111: Activity Name: Install Primary Steel Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on GG111: Activity Name: Install Roof Panels Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Start Date: 08-Nov-24 End Date: 29-Nov-24
Note on HC111: Activity Name: Install Exterior Wall Panels Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Start Date: 30-Nov-24 End Date: 14-Dec-24
Note on HS111: Activity Name: Install Louvers & Dampers Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Start Date: 16-Dec-24 End Date: 06-Jan-25
Note on GM112: Activity Name: UG MEP Work (Plumbing) Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HS112: Activity Name: Prep / Place SOG Phase: Core & Shell Location: Admin/ COLO 3 Trade: Concrete Start Date: 16-Dec-24 End Date: 27-Dec-24
Note on IG112: Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Start Date: 30-Dec-24 End Date: 17-Jan-25
Note on IG113: Activity Name: Weather Days Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on GA117: Activity Name: Install Primary Steel Phase: Core & Shell Location: COLO 4 Trade: Framing Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GT117: Activity Name: Install Roof Panels Phase: Core & Shell Location: COLO 4 Trade: Framing Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on HS117: Activity Name: Install Exterior Wall Panels Phase: Core & Shell Location: COLO 4 Trade: Framing Start Date: 16-Dec-24 End Date: 31-Dec-24
Note on IO117: Activity Name: Install Louvers & Dampers Phase: Core & Shell Location: COLO 4 Trade: Framing Start Date: 07-Jan-25 End Date: 25-Jan-25
Note on HG118: Activity Name: UG MEP Work (Plumbing) Phase: Core & Shell Location: COLO 4 Trade: Plumbing Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on IG118: Activity Name: Prep / Place SOG Phase: Core & Shell Location: COLO 4 Trade: Concrete Start Date: 30-Dec-24 End Date: 10-Jan-25
Note on IS118: Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Phase: Core & Shell Location: COLO 4 Trade: Framing Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on GM122: Activity Name: Install Primary Steel Phase: Core & Shell Location: COLO 5 Trade: Framing Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on HG122: Activity Name: Install Roof Panels Phase: Core & Shell Location: COLO 5 Trade: Framing Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on IJ122: Activity Name: Install Exterior Wall Panels Phase: Core & Shell Location: COLO 5 Trade: Framing Start Date: 02-Jan-25 End Date: 15-Jan-25
Note on JI122: Activity Name: Install Louvers & Dampers Phase: Core & Shell Location: COLO 5 Trade: Framing Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on HT123: Activity Name: UG MEP Work (Plumbing) Phase: Core & Shell Location: COLO 5 Trade: Plumbing Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IV123: Activity Name: Prep / Place SOG Phase: Core & Shell Location: COLO 5 Trade: Concrete Start Date: 14-Jan-25 End Date: 25-Jan-25
Note on JI123: Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Phase: Core & Shell Location: COLO 5 Trade: Framing Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on BV127: Activity Name: PROCUREMENT- ARL & Subcontractor Awards Phase: Early Awards Location: Milestone Trade: Milestone Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on BV128: Activity Name: PROCUREMENT- Buyouts & Early Procurement Phase: Early Awards Location: Milestone Trade: Milestone Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on IY129: Activity Name: Build Equipment Pads for XFMs Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 17-Jan-25 End Date: 28-Jan-25
Note on JK129: Activity Name: Build Equipment Pads for UPMs Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 29-Jan-25 End Date: 07-Feb-25
Note on JW129: Activity Name: Build Equipment Pads for UMSs Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 10-Feb-25 End Date: 19-Feb-25
Note on KG129: Activity Name: Build Equipment Pads for Generators Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 20-Feb-25 End Date: 03-Mar-25
Note on KS129: Activity Name: Install Generators Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on MS129: Activity Name: MV Cable Pulling & Terminating to Cell 1 Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 25-Apr-25 End Date: 05-May-25
Note on ND129: Activity Name: MV Cable Pulling & Terminating to Cell 2 Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 06-May-25 End Date: 14-May-25
Note on NM129: Activity Name: MV Cable Pulling & Terminating to Cell 4 Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 15-May-25 End Date: 23-May-25
Note on NY129: Activity Name: MV Cable Pulling & Terminating to Cell 3 Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 27-May-25 End Date: 03-Jun-25
Note on KS130: Activity Name: Install UMSs Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on KS131: Activity Name: Install UPMs Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on KS132: Activity Name: Install XFMs Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on KH136: Activity Name: Build Equipment Pads for XFMs Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 21-Feb-25 End Date: 04-Mar-25
Note on KT136: Activity Name: Build Equipment Pads for UPMs Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 05-Mar-25 End Date: 14-Mar-25
Note on LD136: Activity Name: Build Equipment Pads for UMSs Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 15-Mar-25 End Date: 26-Mar-25
Note on LP136: Activity Name: Build Equipment Pads for Generators Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 27-Mar-25 End Date: 05-Apr-25
Note on ME136: Activity Name: Install Generators Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 11-Apr-25 End Date: 24-Apr-25
Note on MS136: Activity Name: MV Cable Pulling & Terminating to Cell 1 Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 25-Apr-25 End Date: 05-May-25
Note on ND136: Activity Name: MV Cable Pulling & Terminating to Cell 2 Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 06-May-25 End Date: 14-May-25
Note on NM136: Activity Name: MV Cable Pulling & Terminating to Cell 4 Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 15-May-25 End Date: 23-May-25
Note on NY136: Activity Name: MV Cable Pulling & Terminating to Cell 3 Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 27-May-25 End Date: 04-Jun-25
Note on LV137: Activity Name: Install UMSs Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on LV138: Activity Name: Install UPMs Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on LV139: Activity Name: Install XFMs Phase: Electrical Yard Location: COLO 4 Trade: Electrical Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on JB143: Activity Name: Beneficial Use Rooms Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 20-Jan-25 End Date: 09-May-25
Note on NQ143: Activity Name: Install Generators Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 19-May-25 End Date: 31-May-25
Note on OE143: Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 3 Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 02-Jun-25 End Date: 10-Jun-25
Note on OP143: Activity Name: Terminate MV Gear - Cell 3 Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 13-Jun-25 End Date: 18-Jun-25
Note on LQ144: Activity Name: Build Equipment Pads for XFMs Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 28-Mar-25 End Date: 07-Apr-25
Note on MB144: Activity Name: Build Equipment Pads for UPMs Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 08-Apr-25 End Date: 18-Apr-25
Note on MM144: Activity Name: Build Equipment Pads for UMSs Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 19-Apr-25 End Date: 29-Apr-25
Note on MX144: Activity Name: Build Equipment Pads for Generators Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 30-Apr-25 End Date: 10-May-25
Note on NN144: Activity Name: Install UMSs Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 16-May-25 End Date: 29-May-25
Note on OG144: Activity Name: Terminate MV Gear - Cell 2 Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 04-Jun-25 End Date: 07-Jun-25
Note on OL144: Activity Name: Terminate MV Gear - Cell 4 Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on MZ145: Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 1 Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 02-May-25 End Date: 12-May-25
Note on NL145: Activity Name: Install UPMs Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 14-May-25 End Date: 27-May-25
Note on NJ146: Activity Name: Install XFMs Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 12-May-25 End Date: 23-May-25
Note on NK147: Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 2 Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 13-May-25 End Date: 21-May-25
Note on NT147: Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 4 Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 22-May-25 End Date: 31-May-25
Note on OB148: Activity Name: Terminate MV Gear - Cell 1 Phase: Electrical Yard Location: COLO 5 Trade: Electrical Start Date: 30-May-25 End Date: 03-Jun-25
Note on KI151: Activity Name: Install Doors Phase: Fitout Location: Admin Trade: Framing Start Date: 22-Feb-25 End Date: 26-Feb-25
Note on KN151: Activity Name: Light Fixtures Installation Phase: Fitout Location: Admin Trade: Electrical Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on LA151: Activity Name: Remaining Area Punchlist Phase: Fitout Location: Admin Trade: Clayco Start Date: 12-Mar-25 End Date: 17-Mar-25
Note on KK154: Activity Name: Layout Framing Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 24-Feb-25 End Date: 24-Feb-25
Note on KL154: Activity Name: IInstall Framing Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 25-Feb-25 End Date: 27-Feb-25
Note on KO154: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KT154: Activity Name: Install Drywall (One Side - Facing DH) Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 05-Mar-25 End Date: 07-Mar-25
Note on KZ154: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 11-Mar-25 End Date: 12-Mar-25
Note on LD154: Activity Name: Install Screen Mesh + Caulking Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 15-Mar-25 End Date: 18-Mar-25
Note on LH154: Activity Name: Install Secondary Steel Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on LJ154: Activity Name: Paint Secondary Steel Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Start Date: 21-Mar-25 End Date: 24-Mar-25
Note on LN154: Activity Name: General Cleaning Phase: Fitout Location: CELL 1 Data Hall Trade: Cx Start Date: 25-Mar-25 End Date: 25-Mar-25
Note on LR154: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Start Date: 29-Mar-25 End Date: 03-Apr-25
Note on LX154: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 04-Apr-25 End Date: 07-Apr-25
Note on MB154: Activity Name: Install Drywall (One Side - Facing DH) Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 08-Apr-25 End Date: 10-Apr-25
Note on MI154: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 15-Apr-25 End Date: 17-Apr-25
Note on MQ154: Activity Name: Install Secondary Steel Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 23-Apr-25 End Date: 24-Apr-25
Note on MS154: Activity Name: Paint Secondary Steel Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Start Date: 25-Apr-25 End Date: 26-Apr-25
Note on MV154: Activity Name: General Cleaning Phase: Fitout Location: CELL 1 Data Hall Trade: Cx Start Date: 28-Apr-25 End Date: 28-Apr-25
Note on MZ154: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Start Date: 02-May-25 End Date: 08-May-25
Note on NL154: Activity Name: Raise HACs Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Start Date: 14-May-25 End Date: 17-May-25
Note on NQ154: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 19-May-25 End Date: 21-May-25
Note on NY154: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 27-May-25 End Date: 31-May-25
Note on OE154: Activity Name: Terminate PDUs Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 02-Jun-25 End Date: 04-Jun-25
Note on KT155: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 1 Data Hall Trade: Fire Protection Start Date: 05-Mar-25 End Date: 07-Mar-25
Note on KW155: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 08-Mar-25 End Date: 11-Mar-25
Note on LN155: Activity Name: Install Ceiling Grid Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 25-Mar-25 End Date: 28-Mar-25
Note on LU155: Activity Name: Install Busways on HAC Arms Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 01-Apr-25 End Date: 05-Apr-25
Note on MI155: Activity Name: Detail HACs Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Start Date: 15-Apr-25 End Date: 18-Apr-25
Note on MV155: Activity Name: Install Ceiling Grid Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 28-Apr-25 End Date: 01-May-25
Note on ND155: Activity Name: Install Busways on HAC Arms Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 06-May-25 End Date: 10-May-25
Note on NQ155: Activity Name: Detail HACs Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Start Date: 19-May-25 End Date: 22-May-25
Note on KW156: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 08-Mar-25 End Date: 12-Mar-25
Note on LT156: Activity Name: Layout Framing Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 31-Mar-25 End Date: 31-Mar-25
Note on LW156: Activity Name: Install Device Tiles Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 03-Apr-25 End Date: 04-Apr-25
Note on MI156: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 15-Apr-25 End Date: 16-Apr-25
Note on ML156: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 18-Apr-25 End Date: 21-Apr-25
Note on MY156: Activity Name: Terminate PDUs Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 01-May-25 End Date: 05-May-25
Note on MZ156: Activity Name: Install Perimeter Cable Trays Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 02-May-25 End Date: 07-May-25
Note on NF156: Activity Name: Install Device Tiles Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 08-May-25 End Date: 09-May-25
Note on NT156: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 22-May-25 End Date: 23-May-25
Note on KW157: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 1 Data Hall Trade: Fire Protection Start Date: 08-Mar-25 End Date: 11-Mar-25
Note on LR157: Activity Name: Install Perimeter Cable Trays Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 29-Mar-25 End Date: 02-Apr-25
Note on LW157: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 03-Apr-25 End Date: 08-Apr-25
Note on ME157: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 11-Apr-25 End Date: 15-Apr-25
Note on MM157: Activity Name: Install Screen Mesh + Caulking Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 19-Apr-25 End Date: 22-Apr-25
Note on NF157: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 08-May-25 End Date: 13-May-25
Note on KZ158: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 11-Mar-25 End Date: 12-Mar-25
Note on LU158: Activity Name: Install Framing Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 01-Apr-25 End Date: 03-Apr-25
Note on MB158: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 1 Data Hall Trade: Fire Protection Start Date: 08-Apr-25 End Date: 10-Apr-25
Note on ME158: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MP158: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 22-Apr-25 End Date: 26-Apr-25
Note on NF158: Activity Name: Set PDUs Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 08-May-25 End Date: 12-May-25
Note on LA159: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Start Date: 12-Mar-25 End Date: 14-Mar-25
Note on LW159: Activity Name: Set PDUs Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Start Date: 03-Apr-25 End Date: 07-Apr-25
Note on MC159: Activity Name: Raise HACs Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Start Date: 09-Apr-25 End Date: 14-Apr-25
Note on ME159: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 1 Data Hall Trade: Fire Protection Start Date: 11-Apr-25 End Date: 15-Apr-25
Note on MI160: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Start Date: 15-Apr-25 End Date: 16-Apr-25
Note on MJ161: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Start Date: 16-Apr-25 End Date: 18-Apr-25
Note on KO164: Activity Name: Install Framing Phase: Fitout Location: CELL 1 Electrical Room Trade: Framing Start Date: 28-Feb-25 End Date: 03-Mar-25
Note on KS164: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Start Date: 04-Mar-25 End Date: 05-Mar-25
Note on KU164: Activity Name: Install Drywall [Elec + Battery Rooms] Phase: Fitout Location: CELL 1 Electrical Room Trade: Framing Start Date: 06-Mar-25 End Date: 10-Mar-25
Note on KZ164: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 1 Electrical Room Trade: Framing Start Date: 11-Mar-25 End Date: 11-Mar-25
Note on LD164: Activity Name: General Cleaning Phase: Fitout Location: CELL 1 Electrical Room Trade: Cx Start Date: 15-Mar-25 End Date: 15-Mar-25
Note on LT164: Activity Name: Set Electrical Equipments Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on LX164: Activity Name: Install Framing Phase: Fitout Location: CELL 1 Electrical Room Trade: Framing Start Date: 04-Apr-25 End Date: 05-Apr-25
Note on MA164: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Start Date: 07-Apr-25 End Date: 08-Apr-25
Note on MC164: Activity Name: Install Drywall [Elec + Battery Rooms] Phase: Fitout Location: CELL 1 Electrical Room Trade: Framing Start Date: 09-Apr-25 End Date: 14-Apr-25
Note on MI164: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 1 Electrical Room Trade: Framing Start Date: 15-Apr-25 End Date: 15-Apr-25
Note on MM164: Activity Name: General Cleaning Phase: Fitout Location: CELL 1 Electrical Room Trade: Cx Start Date: 19-Apr-25 End Date: 19-Apr-25
Note on MZ164: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Start Date: 02-May-25 End Date: 15-May-25
Note on NN164: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Start Date: 16-May-25 End Date: 29-May-25
Note on KU165: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 1 Electrical Room Trade: Fire Protection Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on KZ165: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 1 Electrical Room Trade: Framing Start Date: 11-Mar-25 End Date: 12-Mar-25
Note on MC165: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 1 Electrical Room Trade: Fire Protection Start Date: 09-Apr-25 End Date: 10-Apr-25
Note on MI165: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 1 Electrical Room Trade: Framing Start Date: 15-Apr-25 End Date: 16-Apr-25
Note on NN165: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Start Date: 16-May-25 End Date: 20-May-25
Note on KW166: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 1 Electrical Room Trade: Fire Protection Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LA166: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Start Date: 12-Mar-25 End Date: 13-Mar-25
Note on ME166: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 1 Electrical Room Trade: Fire Protection Start Date: 11-Apr-25 End Date: 14-Apr-25
Note on MJ166: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Start Date: 16-Apr-25 End Date: 17-Apr-25
Note on LB167: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 1 Electrical Room Trade: Paiting Start Date: 13-Mar-25 End Date: 14-Mar-25
Note on MK167: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 1 Electrical Room Trade: Paiting Start Date: 17-Apr-25 End Date: 18-Apr-25
Note on LX168: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on ML168: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Start Date: 18-Apr-25 End Date: 30-Apr-25
Note on MO169: Activity Name: Set Electrical Equipments Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Start Date: 21-Apr-25 End Date: 01-May-25
Note on ML170: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on KW171: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Fire Protection Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on KZ171: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Start Date: 11-Mar-25 End Date: 13-Mar-25
Note on LC171: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Start Date: 14-Mar-25 End Date: 20-Mar-25
Note on LP171: Activity Name: Install Drywall [Mech Gallery] Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Start Date: 27-Mar-25 End Date: 28-Mar-25
Note on LR171: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Start Date: 29-Mar-25 End Date: 29-Mar-25
Note on LW171: Activity Name: General Cleaning Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Cx Start Date: 03-Apr-25 End Date: 05-Apr-25
Note on ML171: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Start Date: 18-Apr-25 End Date: 24-Apr-25
Note on MX171: Activity Name: Install Drywall [Mech Gallery] Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Start Date: 30-Apr-25 End Date: 01-May-25
Note on MZ171: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Start Date: 02-May-25 End Date: 02-May-25
Note on NF171: Activity Name: General Cleaning Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Cx Start Date: 08-May-25 End Date: 10-May-25
Note on NS171: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: BAS Start Date: 21-May-25 End Date: 30-May-25
Note on OC171: Activity Name: Terminate Mechanical Equipments Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Start Date: 31-May-25 End Date: 04-Jun-25
Note on KZ172: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Fire Protection Start Date: 11-Mar-25 End Date: 12-Mar-25
Note on LJ172: Activity Name: Overhead R/I - Plumbing Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Plumbing Start Date: 21-Mar-25 End Date: 28-Mar-25
Note on LR172: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Start Date: 29-Mar-25 End Date: 31-Mar-25
Note on LX172: Activity Name: Install BAS Equipments Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: BAS Start Date: 04-Apr-25 End Date: 16-Apr-25
Note on MS172: Activity Name: Overhead R/I - Plumbing Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Plumbing Start Date: 25-Apr-25 End Date: 01-May-25
Note on MZ172: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Start Date: 02-May-25 End Date: 05-May-25
Note on NG172: Activity Name: Install BAS Equipments Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: BAS Start Date: 09-May-25 End Date: 20-May-25
Note on LT173: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on LX173: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Start Date: 04-Apr-25 End Date: 05-Apr-25
Note on MA173: Activity Name: Set Mechanical Equipments Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on ME173: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Fire Protection Start Date: 11-Apr-25 End Date: 14-Apr-25
Note on MI173: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Start Date: 15-Apr-25 End Date: 17-Apr-25
Note on MT173: Activity Name: Terminate Mechanical Equipments Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on NC173: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Start Date: 05-May-25 End Date: 08-May-25
Note on NG173: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Start Date: 09-May-25 End Date: 10-May-25
Note on NJ173: Activity Name: Set Mechanical Equipments Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Start Date: 12-May-25 End Date: 15-May-25
Note on NN173: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Start Date: 16-May-25 End Date: 30-May-25
Note on LU174: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Paiting Start Date: 01-Apr-25 End Date: 02-Apr-25
Note on MI174: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Fire Protection Start Date: 15-Apr-25 End Date: 16-Apr-25
Note on MK174: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: BAS Start Date: 17-Apr-25 End Date: 25-Apr-25
Note on ND174: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Paiting Start Date: 06-May-25 End Date: 07-May-25
Note on ME175: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MK178: Activity Name: Punchlist Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Start Date: 17-Apr-25 End Date: 28-Apr-25
Note on ND178: Activity Name: Punchlist Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Start Date: 06-May-25 End Date: 16-May-25
Note on OH178: Activity Name: Punchlist Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on KT181: Activity Name: Layout Framing Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 05-Mar-25 End Date: 05-Mar-25
Note on KU181: Activity Name: Install Framing Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 06-Mar-25 End Date: 08-Mar-25
Note on KY181: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 10-Mar-25 End Date: 12-Mar-25
Note on LB181: Activity Name: Install Drywall (One Side - Facing DH) Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 13-Mar-25 End Date: 15-Mar-25
Note on LH181: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on LN181: Activity Name: Install Screen Mesh + Caulking Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 25-Mar-25 End Date: 27-Mar-25
Note on LQ181: Activity Name: Install Secondary Steel Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 28-Mar-25 End Date: 29-Mar-25
Note on LT181: Activity Name: Paint Secondary Steel Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Start Date: 31-Mar-25 End Date: 01-Apr-25
Note on LV181: Activity Name: General Cleaning Phase: Fitout Location: CELL 2 Data Hall Trade: Cx Start Date: 02-Apr-25 End Date: 02-Apr-25
Note on MA181: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Start Date: 07-Apr-25 End Date: 11-Apr-25
Note on MH181: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 14-Apr-25 End Date: 16-Apr-25
Note on MK181: Activity Name: Install Drywall (One Side - Facing DH) Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 17-Apr-25 End Date: 19-Apr-25
Note on MQ181: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 23-Apr-25 End Date: 25-Apr-25
Note on MY181: Activity Name: Install Secondary Steel Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 01-May-25 End Date: 02-May-25
Note on NC181: Activity Name: Paint Secondary Steel Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Start Date: 05-May-25 End Date: 06-May-25
Note on NE181: Activity Name: General Cleaning Phase: Fitout Location: CELL 2 Data Hall Trade: Cx Start Date: 07-May-25 End Date: 07-May-25
Note on NJ181: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Start Date: 12-May-25 End Date: 16-May-25
Note on NT181: Activity Name: Raise HACs Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Start Date: 22-May-25 End Date: 27-May-25
Note on NZ181: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 28-May-25 End Date: 30-May-25
Note on OG181: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 04-Jun-25 End Date: 09-Jun-25
Note on PB181: Activity Name: Terminate PDUs Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 25-Jun-25 End Date: 27-Jun-25
Note on LB182: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 2 Data Hall Trade: Fire Protection Start Date: 13-Mar-25 End Date: 15-Mar-25
Note on LF182: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 17-Mar-25 End Date: 19-Mar-25
Note on LV182: Activity Name: Install Ceiling Grid Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 02-Apr-25 End Date: 05-Apr-25
Note on MC182: Activity Name: Install Busways on HAC Arms Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 09-Apr-25 End Date: 15-Apr-25
Note on MQ182: Activity Name: Detail HACs Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Start Date: 23-Apr-25 End Date: 26-Apr-25
Note on NE182: Activity Name: Install Ceiling Grid Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 07-May-25 End Date: 10-May-25
Note on NL182: Activity Name: Install Busways on HAC Arms Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 14-May-25 End Date: 19-May-25
Note on NZ182: Activity Name: Detail HACs Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Start Date: 28-May-25 End Date: 31-May-25
Note on LF183: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 17-Mar-25 End Date: 20-Mar-25
Note on MB183: Activity Name: Layout Framing Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 08-Apr-25 End Date: 08-Apr-25
Note on ME183: Activity Name: Install Device Tiles Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 11-Apr-25 End Date: 14-Apr-25
Note on MQ183: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 23-Apr-25 End Date: 24-Apr-25
Note on MT183: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 26-Apr-25 End Date: 29-Apr-25
Note on NJ183: Activity Name: Install Perimeter Cable Trays Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 12-May-25 End Date: 15-May-25
Note on NN183: Activity Name: Install Device Tiles Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 16-May-25 End Date: 17-May-25
Note on NZ183: Activity Name: Terminate PDUs Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 28-May-25 End Date: 30-May-25
Note on OC183: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 31-May-25 End Date: 03-Jun-25
Note on LF184: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 2 Data Hall Trade: Fire Protection Start Date: 17-Mar-25 End Date: 19-Mar-25
Note on MA184: Activity Name: Install Perimeter Cable Trays Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on ME184: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 11-Apr-25 End Date: 17-Apr-25
Note on MO184: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 21-Apr-25 End Date: 23-Apr-25
Note on MV184: Activity Name: Install Screen Mesh + Caulking Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 28-Apr-25 End Date: 30-Apr-25
Note on NN184: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 16-May-25 End Date: 21-May-25
Note on LH185: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on MC185: Activity Name: Install Framing Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 09-Apr-25 End Date: 11-Apr-25
Note on MK185: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 2 Data Hall Trade: Fire Protection Start Date: 17-Apr-25 End Date: 19-Apr-25
Note on MO185: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 21-Apr-25 End Date: 24-Apr-25
Note on MX185: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 30-Apr-25 End Date: 06-May-25
Note on NN185: Activity Name: Set PDUs Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 16-May-25 End Date: 20-May-25
Note on LI186: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Start Date: 20-Mar-25 End Date: 24-Mar-25
Note on ME186: Activity Name: Set PDUs Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on ML186: Activity Name: Raise HACs Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MO186: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 2 Data Hall Trade: Fire Protection Start Date: 21-Apr-25 End Date: 23-Apr-25
Note on MQ187: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Start Date: 23-Apr-25 End Date: 24-Apr-25
Note on MR188: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Start Date: 24-Apr-25 End Date: 26-Apr-25
Note on KY191: Activity Name: Install Framing Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Start Date: 10-Mar-25 End Date: 11-Mar-25
Note on LA191: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Start Date: 12-Mar-25 End Date: 13-Mar-25
Note on LC191: Activity Name: Install Drywall [Elec + Battery Rooms] Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LH191: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Start Date: 19-Mar-25 End Date: 19-Mar-25
Note on LN191: Activity Name: General Cleaning Phase: Fitout Location: CELL 2 Electrical Room Trade: Cx Start Date: 25-Mar-25 End Date: 25-Mar-25
Note on LO191: Activity Name: Set Electrical Equipments Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Start Date: 26-Mar-25 End Date: 29-Mar-25
Note on MH191: Activity Name: Install Framing Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Start Date: 14-Apr-25 End Date: 15-Apr-25
Note on MJ191: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Start Date: 16-Apr-25 End Date: 17-Apr-25
Note on ML191: Activity Name: Install Drywall [Elec + Battery Rooms] Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MQ191: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Start Date: 23-Apr-25 End Date: 23-Apr-25
Note on MV191: Activity Name: General Cleaning Phase: Fitout Location: CELL 2 Electrical Room Trade: Cx Start Date: 28-Apr-25 End Date: 28-Apr-25
Note on MY191: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Start Date: 01-May-25 End Date: 14-May-25
Note on NM191: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Start Date: 15-May-25 End Date: 27-May-25
Note on OB191: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Start Date: 30-May-25 End Date: 11-Jun-25
Note on OO191: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Start Date: 12-Jun-25 End Date: 24-Jun-25
Note on LC192: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 2 Electrical Room Trade: Fire Protection Start Date: 14-Mar-25 End Date: 15-Mar-25
Note on LH192: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on ML192: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 2 Electrical Room Trade: Fire Protection Start Date: 18-Apr-25 End Date: 19-Apr-25
Note on MQ192: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Start Date: 23-Apr-25 End Date: 24-Apr-25
Note on MW192: Activity Name: Set Electrical Equipments Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Start Date: 29-Apr-25 End Date: 02-May-25
Note on NM192: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Start Date: 15-May-25 End Date: 19-May-25
Note on OO192: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on LF193: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 2 Electrical Room Trade: Fire Protection Start Date: 17-Mar-25 End Date: 18-Mar-25
Note on LI193: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Start Date: 20-Mar-25 End Date: 21-Mar-25
Note on MO193: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 2 Electrical Room Trade: Fire Protection Start Date: 21-Apr-25 End Date: 22-Apr-25
Note on MR193: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Start Date: 24-Apr-25 End Date: 25-Apr-25
Note on LJ194: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 2 Electrical Room Trade: Paiting Start Date: 21-Mar-25 End Date: 24-Mar-25
Note on MS194: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 2 Electrical Room Trade: Paiting Start Date: 25-Apr-25 End Date: 26-Apr-25
Note on LF197: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Fire Protection Start Date: 17-Mar-25 End Date: 18-Mar-25
Note on LH197: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Start Date: 19-Mar-25 End Date: 21-Mar-25
Note on LM197: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Start Date: 24-Mar-25 End Date: 29-Mar-25
Note on LX197: Activity Name: Install Drywall [Mech Gallery] Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Start Date: 04-Apr-25 End Date: 05-Apr-25
Note on MA197: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Start Date: 07-Apr-25 End Date: 07-Apr-25
Note on ME197: Activity Name: General Cleaning Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Cx Start Date: 11-Apr-25 End Date: 15-Apr-25
Note on MT197: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Start Date: 26-Apr-25 End Date: 02-May-25
Note on NG197: Activity Name: Install Drywall [Mech Gallery] Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Start Date: 09-May-25 End Date: 10-May-25
Note on NJ197: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Start Date: 12-May-25 End Date: 12-May-25
Note on NN197: Activity Name: General Cleaning Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Cx Start Date: 16-May-25 End Date: 19-May-25
Note on OB197: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: BAS Start Date: 30-May-25 End Date: 07-Jun-25
Note on OL197: Activity Name: Terminate Mechanical Equipments Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on LH198: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Fire Protection Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on LT198: Activity Name: Overhead R/I - Plumbing Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Plumbing Start Date: 31-Mar-25 End Date: 05-Apr-25
Note on MA198: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Start Date: 07-Apr-25 End Date: 08-Apr-25
Note on MH198: Activity Name: Install BAS Equipments Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: BAS Start Date: 14-Apr-25 End Date: 24-Apr-25
Note on NC198: Activity Name: Overhead R/I - Plumbing Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Plumbing Start Date: 05-May-25 End Date: 10-May-25
Note on NJ198: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Start Date: 12-May-25 End Date: 13-May-25
Note on NO198: Activity Name: Install BAS Equipments Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: BAS Start Date: 17-May-25 End Date: 29-May-25
Note on MB199: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Start Date: 08-Apr-25 End Date: 11-Apr-25
Note on MH199: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Start Date: 14-Apr-25 End Date: 15-Apr-25
Note on MJ199: Activity Name: Set Mechanical Equipments Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Start Date: 16-Apr-25 End Date: 19-Apr-25
Note on MO199: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Fire Protection Start Date: 21-Apr-25 End Date: 22-Apr-25
Note on MQ199: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Start Date: 23-Apr-25 End Date: 25-Apr-25
Note on ND199: Activity Name: Terminate Mechanical Equipments Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Start Date: 06-May-25 End Date: 09-May-25
Note on NK199: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Start Date: 13-May-25 End Date: 16-May-25
Note on NO199: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Start Date: 17-May-25 End Date: 19-May-25
Note on NR199: Activity Name: Set Mechanical Equipments Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Start Date: 20-May-25 End Date: 23-May-25
Note on NY199: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Start Date: 27-May-25 End Date: 07-Jun-25
Note on MC200: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Paiting Start Date: 09-Apr-25 End Date: 10-Apr-25
Note on MQ200: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Fire Protection Start Date: 23-Apr-25 End Date: 24-Apr-25
Note on MS200: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: BAS Start Date: 25-Apr-25 End Date: 05-May-25
Note on NL200: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Paiting Start Date: 14-May-25 End Date: 15-May-25
Note on MO201: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Start Date: 21-Apr-25 End Date: 05-May-25
Note on OC204: Activity Name: Punchlist Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Start Date: 31-May-25 End Date: 11-Jun-25
Note on PE204: Activity Name: Punchlist Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on LQ206: Activity Name: Layout Framing Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 28-Mar-25 End Date: 28-Mar-25
Note on LR206: Activity Name: Install Framing Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 29-Mar-25 End Date: 01-Apr-25
Note on LV206: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 02-Apr-25 End Date: 04-Apr-25
Note on LY206: Activity Name: Install Drywall (One Side - Facing DH) Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 05-Apr-25 End Date: 08-Apr-25
Note on ME206: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 11-Apr-25 End Date: 14-Apr-25
Note on MK206: Activity Name: Install Screen Mesh + Caulking Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 17-Apr-25 End Date: 19-Apr-25
Note on MO206: Activity Name: Install Secondary Steel Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 21-Apr-25 End Date: 22-Apr-25
Note on MQ206: Activity Name: Paint Secondary Steel Phase: Fitout Location: CELL 3 Data Hall Trade: Paiting Start Date: 23-Apr-25 End Date: 24-Apr-25
Note on MS206: Activity Name: General Cleaning Phase: Fitout Location: CELL 3 Data Hall Trade: Cx Start Date: 25-Apr-25 End Date: 25-Apr-25
Note on MX206: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Start Date: 30-Apr-25 End Date: 06-May-25
Note on NE206: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 07-May-25 End Date: 09-May-25
Note on NH206: Activity Name: Install Drywall (One Side - Facing DH) Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 10-May-25 End Date: 13-May-25
Note on NN206: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 16-May-25 End Date: 19-May-25
Note on NY206: Activity Name: Install Secondary Steel Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 27-May-25 End Date: 27-May-25
Note on NZ206: Activity Name: Paint Secondary Steel Phase: Fitout Location: CELL 3 Data Hall Trade: Paiting Start Date: 28-May-25 End Date: 29-May-25
Note on OB206: Activity Name: General Cleaning Phase: Fitout Location: CELL 3 Data Hall Trade: Cx Start Date: 30-May-25 End Date: 30-May-25
Note on OG206: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Start Date: 04-Jun-25 End Date: 09-Jun-25
Note on OS206: Activity Name: Raise HACs Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Start Date: 16-Jun-25 End Date: 19-Jun-25
Note on OW206: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 20-Jun-25 End Date: 23-Jun-25
Note on PD206: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 27-Jun-25 End Date: 02-Jul-25
Note on PY206: Activity Name: Terminate PDUs Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 18-Jul-25 End Date: 21-Jul-25
Note on QR206: Activity Name: Terminate PDUs Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 06-Aug-25 End Date: 08-Aug-25
Note on LY207: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 3 Data Hall Trade: Fire Protection Start Date: 05-Apr-25 End Date: 08-Apr-25
Note on MC207: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 09-Apr-25 End Date: 11-Apr-25
Note on MS207: Activity Name: Install Ceiling Grid Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 25-Apr-25 End Date: 29-Apr-25
Note on MZ207: Activity Name: Install Busways on HAC Arms Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 02-May-25 End Date: 08-May-25
Note on NN207: Activity Name: Detail HACs Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Start Date: 16-May-25 End Date: 20-May-25
Note on OB207: Activity Name: Install Ceiling Grid Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 30-May-25 End Date: 03-Jun-25
Note on OI207: Activity Name: Install Busways on HAC Arms Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 06-Jun-25 End Date: 11-Jun-25
Note on OW207: Activity Name: Detail HACs Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Start Date: 20-Jun-25 End Date: 24-Jun-25
Note on MC208: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 09-Apr-25 End Date: 14-Apr-25
Note on MY208: Activity Name: Layout Framing Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 01-May-25 End Date: 01-May-25
Note on ND208: Activity Name: Install Device Tiles Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 06-May-25 End Date: 07-May-25
Note on NN208: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 16-May-25 End Date: 17-May-25
Note on NR208: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 20-May-25 End Date: 22-May-25
Note on OG208: Activity Name: Install Perimeter Cable Trays Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 04-Jun-25 End Date: 07-Jun-25
Note on OL208: Activity Name: Install Device Tiles Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 09-Jun-25 End Date: 10-Jun-25
Note on PA208: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 24-Jun-25 End Date: 26-Jun-25
Note on MC209: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 3 Data Hall Trade: Fire Protection Start Date: 09-Apr-25 End Date: 11-Apr-25
Note on MX209: Activity Name: Install Perimeter Cable Trays Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 30-Apr-25 End Date: 05-May-25
Note on ND209: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 06-May-25 End Date: 10-May-25
Note on NL209: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 14-May-25 End Date: 16-May-25
Note on NS209: Activity Name: Install Screen Mesh + Caulking Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 21-May-25 End Date: 23-May-25
Note on OL209: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 09-Jun-25 End Date: 13-Jun-25
Note on ME210: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 11-Apr-25 End Date: 14-Apr-25
Note on MZ210: Activity Name: Install Framing Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 02-May-25 End Date: 06-May-25
Note on NH210: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 3 Data Hall Trade: Fire Protection Start Date: 10-May-25 End Date: 13-May-25
Note on NL210: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 14-May-25 End Date: 17-May-25
Note on NU210: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 23-May-25 End Date: 29-May-25
Note on OL210: Activity Name: Set PDUs Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on MH211: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 3 Data Hall Trade: Paiting Start Date: 14-Apr-25 End Date: 16-Apr-25
Note on ND211: Activity Name: Set PDUs Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Start Date: 06-May-25 End Date: 09-May-25
Note on NJ211: Activity Name: Raise HACs Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Start Date: 12-May-25 End Date: 15-May-25
Note on NL211: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 3 Data Hall Trade: Fire Protection Start Date: 14-May-25 End Date: 16-May-25
Note on NN212: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Start Date: 16-May-25 End Date: 17-May-25
Note on NO213: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 3 Data Hall Trade: Paiting Start Date: 17-May-25 End Date: 20-May-25
Note on KM216: Activity Name: Install Framing Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Start Date: 26-Feb-25 End Date: 27-Feb-25
Note on KO216: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 28-Feb-25 End Date: 03-Mar-25
Note on KS216: Activity Name: Install Drywall [Elec + Battery Rooms] Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Start Date: 04-Mar-25 End Date: 07-Mar-25
Note on KW216: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Start Date: 08-Mar-25 End Date: 08-Mar-25
Note on LB216: Activity Name: General Cleaning Phase: Fitout Location: CELL 3 Electrical Room Trade: Cx Start Date: 13-Mar-25 End Date: 13-Mar-25
Note on LC216: Activity Name: Set Electrical Equipments Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LV216: Activity Name: Install Framing Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Start Date: 02-Apr-25 End Date: 03-Apr-25
Note on LX216: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 04-Apr-25 End Date: 05-Apr-25
Note on MA216: Activity Name: Install Drywall [Elec + Battery Rooms] Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on ME216: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Start Date: 11-Apr-25 End Date: 11-Apr-25
Note on MK216: Activity Name: General Cleaning Phase: Fitout Location: CELL 3 Electrical Room Trade: Cx Start Date: 17-Apr-25 End Date: 17-Apr-25
Note on ML216: Activity Name: Set Electrical Equipments Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on NE216: Activity Name: Install Framing Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Start Date: 07-May-25 End Date: 08-May-25
Note on NG216: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 09-May-25 End Date: 10-May-25
Note on NJ216: Activity Name: Install Drywall [Elec + Battery Rooms] Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Start Date: 12-May-25 End Date: 15-May-25
Note on NN216: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Start Date: 16-May-25 End Date: 16-May-25
Note on NS216: Activity Name: General Cleaning Phase: Fitout Location: CELL 3 Electrical Room Trade: Cx Start Date: 21-May-25 End Date: 21-May-25
Note on NU216: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 23-May-25 End Date: 04-Jun-25
Note on PA216: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PR216: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 11-Jul-25 End Date: 23-Jul-25
Note on QE216: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 24-Jul-25 End Date: 05-Aug-25
Note on KS217: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Start Date: 04-Mar-25 End Date: 05-Mar-25
Note on KW217: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on MA217: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Start Date: 07-Apr-25 End Date: 08-Apr-25
Note on ME217: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Start Date: 11-Apr-25 End Date: 14-Apr-25
Note on NJ217: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Start Date: 12-May-25 End Date: 13-May-25
Note on NN217: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Start Date: 16-May-25 End Date: 17-May-25
Note on PP217: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 09-Jul-25 End Date: 19-Jul-25
Note on QE217: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on KU218: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on KY218: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 10-Mar-25 End Date: 11-Mar-25
Note on MC218: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Start Date: 09-Apr-25 End Date: 10-Apr-25
Note on MH218: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 14-Apr-25 End Date: 15-Apr-25
Note on NL218: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Start Date: 14-May-25 End Date: 15-May-25
Note on NO218: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 17-May-25 End Date: 19-May-25
Note on PP218: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 09-Jul-25 End Date: 12-Jul-25
Note on KZ219: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 3 Electrical Room Trade: Paiting Start Date: 11-Mar-25 End Date: 12-Mar-25
Note on MI219: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 3 Electrical Room Trade: Paiting Start Date: 15-Apr-25 End Date: 16-Apr-25
Note on NQ219: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 3 Electrical Room Trade: Paiting Start Date: 19-May-25 End Date: 20-May-25
Note on NH220: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 10-May-25 End Date: 22-May-25
Note on NT221: Activity Name: Set Electrical Equipments Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 22-May-25 End Date: 27-May-25
Note on NU222: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Start Date: 23-May-25 End Date: 28-May-25
Note on KU223: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Fire Protection Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on KW223: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 08-Mar-25 End Date: 11-Mar-25
Note on LA223: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 12-Mar-25 End Date: 18-Mar-25
Note on LN223: Activity Name: Install Drywall [Mech Gallery] Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 25-Mar-25 End Date: 26-Mar-25
Note on LP223: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 27-Mar-25 End Date: 27-Mar-25
Note on LU223: Activity Name: General Cleaning Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Cx Start Date: 01-Apr-25 End Date: 03-Apr-25
Note on MJ223: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 16-Apr-25 End Date: 22-Apr-25
Note on MV223: Activity Name: Install Drywall [Mech Gallery] Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 28-Apr-25 End Date: 29-Apr-25
Note on MX223: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 30-Apr-25 End Date: 30-Apr-25
Note on ND223: Activity Name: General Cleaning Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Cx Start Date: 06-May-25 End Date: 08-May-25
Note on NR223: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 20-May-25 End Date: 27-May-25
Note on OE223: Activity Name: Install Drywall [Mech Gallery] Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 02-Jun-25 End Date: 03-Jun-25
Note on OG223: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 04-Jun-25 End Date: 04-Jun-25
Note on OL223: Activity Name: General Cleaning Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Cx Start Date: 09-Jun-25 End Date: 11-Jun-25
Note on OZ223: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: BAS Start Date: 23-Jun-25 End Date: 01-Jul-25
Note on PI223: Activity Name: Terminate Mechanical Equipments Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 02-Jul-25 End Date: 08-Jul-25
Note on KW224: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Fire Protection Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LH224: Activity Name: Overhead R/I - Plumbing Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Plumbing Start Date: 19-Mar-25 End Date: 26-Mar-25
Note on LP224: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 27-Mar-25 End Date: 28-Mar-25
Note on LV224: Activity Name: Install BAS Equipments Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: BAS Start Date: 02-Apr-25 End Date: 14-Apr-25
Note on MQ224: Activity Name: Overhead R/I - Plumbing Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Plumbing Start Date: 23-Apr-25 End Date: 29-Apr-25
Note on MX224: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 30-Apr-25 End Date: 01-May-25
Note on NE224: Activity Name: Install BAS Equipments Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: BAS Start Date: 07-May-25 End Date: 17-May-25
Note on NZ224: Activity Name: Overhead R/I - Plumbing Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Plumbing Start Date: 28-May-25 End Date: 03-Jun-25
Note on OG224: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 04-Jun-25 End Date: 05-Jun-25
Note on OM224: Activity Name: Install BAS Equipments Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: BAS Start Date: 10-Jun-25 End Date: 21-Jun-25
Note on LQ225: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 28-Mar-25 End Date: 01-Apr-25
Note on LV225: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 02-Apr-25 End Date: 03-Apr-25
Note on LX225: Activity Name: Set Mechanical Equipments Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 04-Apr-25 End Date: 08-Apr-25
Note on MC225: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Fire Protection Start Date: 09-Apr-25 End Date: 10-Apr-25
Note on ME225: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 11-Apr-25 End Date: 15-Apr-25
Note on MR225: Activity Name: Terminate Mechanical Equipments Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 24-Apr-25 End Date: 28-Apr-25
Note on MY225: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 01-May-25 End Date: 06-May-25
Note on NE225: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 07-May-25 End Date: 08-May-25
Note on NG225: Activity Name: Set Mechanical Equipments Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 09-May-25 End Date: 13-May-25
Note on NL225: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Fire Protection Start Date: 14-May-25 End Date: 15-May-25
Note on NN225: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 16-May-25 End Date: 19-May-25
Note on OA225: Activity Name: Terminate Mechanical Equipments Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 29-May-25 End Date: 02-Jun-25
Note on OH225: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Start Date: 05-Jun-25 End Date: 09-Jun-25
Note on OM225: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 10-Jun-25 End Date: 11-Jun-25
Note on OO225: Activity Name: Set Mechanical Equipments Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on OU225: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on LR226: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Paiting Start Date: 29-Mar-25 End Date: 31-Mar-25
Note on ME226: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Fire Protection Start Date: 11-Apr-25 End Date: 14-Apr-25
Note on MI226: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: BAS Start Date: 15-Apr-25 End Date: 23-Apr-25
Note on MZ226: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Paiting Start Date: 02-May-25 End Date: 05-May-25
Note on NN226: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Fire Protection Start Date: 16-May-25 End Date: 17-May-25
Note on NQ226: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: BAS Start Date: 19-May-25 End Date: 28-May-25
Note on OI226: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Paiting Start Date: 06-Jun-25 End Date: 07-Jun-25
Note on MC227: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on NL227: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Start Date: 14-May-25 End Date: 28-May-25
Note on OL230: Activity Name: Punchlist Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Start Date: 09-Jun-25 End Date: 20-Jun-25
Note on QC230: Activity Name: Punchlist Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Start Date: 22-Jul-25 End Date: 02-Aug-25
Note on QU230: Activity Name: Punchlist Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on JW233: Activity Name: Layout Framing Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 10-Feb-25 End Date: 10-Feb-25
Note on JX233: Activity Name: Install Framing Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 11-Feb-25 End Date: 13-Feb-25
Note on KA233: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 14-Feb-25 End Date: 17-Feb-25
Note on KE233: Activity Name: Install Drywall (One Side - Facing DH) Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 18-Feb-25 End Date: 20-Feb-25
Note on KK233: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 24-Feb-25 End Date: 25-Feb-25
Note on KO233: Activity Name: Install Screen Mesh + Caulking Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KT233: Activity Name: Install Secondary Steel Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 05-Mar-25 End Date: 06-Mar-25
Note on KV233: Activity Name: Paint Secondary Steel Phase: Fitout Location: CELL 4 Data Hall Trade: Paiting Start Date: 07-Mar-25 End Date: 08-Mar-25
Note on KY233: Activity Name: General Cleaning Phase: Fitout Location: CELL 4 Data Hall Trade: Cx Start Date: 10-Mar-25 End Date: 10-Mar-25
Note on LC233: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Start Date: 14-Mar-25 End Date: 19-Mar-25
Note on LI233: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 20-Mar-25 End Date: 24-Mar-25
Note on LN233: Activity Name: Install Drywall (One Side - Facing DH) Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 25-Mar-25 End Date: 27-Mar-25
Note on LT233: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 31-Mar-25 End Date: 02-Apr-25
Note on MB233: Activity Name: Install Secondary Steel Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 08-Apr-25 End Date: 09-Apr-25
Note on MD233: Activity Name: Paint Secondary Steel Phase: Fitout Location: CELL 4 Data Hall Trade: Paiting Start Date: 10-Apr-25 End Date: 11-Apr-25
Note on MH233: Activity Name: General Cleaning Phase: Fitout Location: CELL 4 Data Hall Trade: Cx Start Date: 14-Apr-25 End Date: 14-Apr-25
Note on ML233: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Start Date: 18-Apr-25 End Date: 23-Apr-25
Note on MW233: Activity Name: Raise HACs Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Start Date: 29-Apr-25 End Date: 02-May-25
Note on NC233: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 05-May-25 End Date: 07-May-25
Note on NJ233: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 12-May-25 End Date: 16-May-25
Note on PA233: Activity Name: Terminate PDUs Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 24-Jun-25 End Date: 26-Jun-25
Note on KE234: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 4 Data Hall Trade: Fire Protection Start Date: 18-Feb-25 End Date: 20-Feb-25
Note on KH234: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 21-Feb-25 End Date: 24-Feb-25
Note on KY234: Activity Name: Install Ceiling Grid Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 10-Mar-25 End Date: 13-Mar-25
Note on LF234: Activity Name: Install Busways on HAC Arms Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 17-Mar-25 End Date: 21-Mar-25
Note on LT234: Activity Name: Detail HACs Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on MH234: Activity Name: Install Ceiling Grid Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 14-Apr-25 End Date: 17-Apr-25
Note on MO234: Activity Name: Install Busways on HAC Arms Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 21-Apr-25 End Date: 25-Apr-25
Note on NC234: Activity Name: Detail HACs Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Start Date: 05-May-25 End Date: 08-May-25
Note on KH235: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 21-Feb-25 End Date: 25-Feb-25
Note on LD235: Activity Name: Layout Framing Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 15-Mar-25 End Date: 15-Mar-25
Note on LH235: Activity Name: Install Device Tiles Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on LT235: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 31-Mar-25 End Date: 01-Apr-25
Note on LW235: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 03-Apr-25 End Date: 05-Apr-25
Note on ML235: Activity Name: Install Perimeter Cable Trays Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MQ235: Activity Name: Install Device Tiles Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 23-Apr-25 End Date: 24-Apr-25
Note on NF235: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 08-May-25 End Date: 10-May-25
Note on KH236: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 4 Data Hall Trade: Fire Protection Start Date: 21-Feb-25 End Date: 24-Feb-25
Note on LC236: Activity Name: Install Perimeter Cable Trays Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LH236: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 19-Mar-25 End Date: 25-Mar-25
Note on LQ236: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 28-Mar-25 End Date: 31-Mar-25
Note on LX236: Activity Name: Install Screen Mesh + Caulking Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 04-Apr-25 End Date: 07-Apr-25
Note on MQ236: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 23-Apr-25 End Date: 28-Apr-25
Note on NH236: Activity Name: Terminate PDUs Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 10-May-25 End Date: 13-May-25
Note on KK237: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 24-Feb-25 End Date: 25-Feb-25
Note on LF237: Activity Name: Install Framing Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 17-Mar-25 End Date: 19-Mar-25
Note on LN237: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 4 Data Hall Trade: Fire Protection Start Date: 25-Mar-25 End Date: 27-Mar-25
Note on LQ237: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 28-Mar-25 End Date: 01-Apr-25
Note on MA237: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 07-Apr-25 End Date: 11-Apr-25
Note on MQ237: Activity Name: Set PDUs Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 23-Apr-25 End Date: 26-Apr-25
Note on KL238: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 4 Data Hall Trade: Paiting Start Date: 25-Feb-25 End Date: 27-Feb-25
Note on LH238: Activity Name: Set PDUs Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Start Date: 19-Mar-25 End Date: 24-Mar-25
Note on LO238: Activity Name: Raise HACs Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Start Date: 26-Mar-25 End Date: 29-Mar-25
Note on LQ238: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 4 Data Hall Trade: Fire Protection Start Date: 28-Mar-25 End Date: 31-Mar-25
Note on LT239: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Start Date: 31-Mar-25 End Date: 01-Apr-25
Note on LU240: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 4 Data Hall Trade: Paiting Start Date: 01-Apr-25 End Date: 03-Apr-25
Note on MM243: Activity Name: Layout Framing Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Start Date: 19-Apr-25 End Date: 19-Apr-25
Note on MO243: Activity Name: Install Framing Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Start Date: 21-Apr-25 End Date: 23-Apr-25
Note on MR243: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Start Date: 24-Apr-25 End Date: 26-Apr-25
Note on MV243: Activity Name: Install Drywall (One Side - Facing DH) Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Start Date: 28-Apr-25 End Date: 30-Apr-25
Note on NC243: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Start Date: 05-May-25 End Date: 06-May-25
Note on NG243: Activity Name: Install Screen Mesh + Caulking Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Start Date: 09-May-25 End Date: 12-May-25
Note on NK243: Activity Name: Install Secondary Steel Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Start Date: 13-May-25 End Date: 14-May-25
Note on NM243: Activity Name: Paint Secondary Steel Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Paiting Start Date: 15-May-25 End Date: 16-May-25
Note on NO243: Activity Name: General Cleaning Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Cx Start Date: 17-May-25 End Date: 17-May-25
Note on NT243: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: HAC's Start Date: 22-May-25 End Date: 28-May-25
Note on OF243: Activity Name: Raise HACs Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: HAC's Start Date: 03-Jun-25 End Date: 06-Jun-25
Note on OJ243: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Start Date: 07-Jun-25 End Date: 10-Jun-25
Note on OS243: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Start Date: 16-Jun-25 End Date: 20-Jun-25
Note on PR243: Activity Name: Terminate PDUs Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Start Date: 11-Jul-25 End Date: 14-Jul-25
Note on MV244: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Fire Protection Start Date: 28-Apr-25 End Date: 30-Apr-25
Note on MY244: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Start Date: 01-May-25 End Date: 05-May-25
Note on NO244: Activity Name: Install Ceiling Grid Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Start Date: 17-May-25 End Date: 21-May-25
Note on NY244: Activity Name: Install Busways on HAC Arms Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Start Date: 27-May-25 End Date: 30-May-25
Note on OJ244: Activity Name: Detail HACs Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: HAC's Start Date: 07-Jun-25 End Date: 11-Jun-25
Note on MY245: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Start Date: 01-May-25 End Date: 06-May-25
Note on NT245: Activity Name: Install Perimeter Cable Trays Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Start Date: 22-May-25 End Date: 27-May-25
Note on NZ245: Activity Name: Install Device Tiles Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Start Date: 28-May-25 End Date: 29-May-25
Note on ON245: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Start Date: 11-Jun-25 End Date: 13-Jun-25
Note on MY246: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Fire Protection Start Date: 01-May-25 End Date: 05-May-25
Note on NZ246: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Start Date: 28-May-25 End Date: 02-Jun-25
Note on NC247: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Start Date: 05-May-25 End Date: 06-May-25
Note on NZ247: Activity Name: Set PDUs Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Start Date: 28-May-25 End Date: 31-May-25
Note on ND248: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Paiting Start Date: 06-May-25 End Date: 08-May-25
Note on KA251: Activity Name: Install Framing Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Start Date: 14-Feb-25 End Date: 15-Feb-25
Note on KD251: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 17-Feb-25 End Date: 18-Feb-25
Note on KF251: Activity Name: Install Drywall [Elec + Battery Rooms] Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Start Date: 19-Feb-25 End Date: 22-Feb-25
Note on KK251: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Start Date: 24-Feb-25 End Date: 24-Feb-25
Note on KO251: Activity Name: General Cleaning Phase: Fitout Location: CELL 4 Electrical Room Trade: Cx Start Date: 28-Feb-25 End Date: 28-Feb-25
Note on KR251: Activity Name: Set Electrical Equipments Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 03-Mar-25 End Date: 06-Mar-25
Note on KV251: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LI251: Activity Name: Install Framing Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Start Date: 20-Mar-25 End Date: 21-Mar-25
Note on LM251: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 24-Mar-25 End Date: 25-Mar-25
Note on LO251: Activity Name: Install Drywall [Elec + Battery Rooms] Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Start Date: 26-Mar-25 End Date: 29-Mar-25
Note on LT251: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Start Date: 31-Mar-25 End Date: 31-Mar-25
Note on LX251: Activity Name: General Cleaning Phase: Fitout Location: CELL 4 Electrical Room Trade: Cx Start Date: 04-Apr-25 End Date: 04-Apr-25
Note on LY251: Activity Name: Set Electrical Equipments Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 05-Apr-25 End Date: 09-Apr-25
Note on MR251: Activity Name: Install Framing Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Start Date: 24-Apr-25 End Date: 25-Apr-25
Note on MT251: Activity Name: In-Wall R/I Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 26-Apr-25 End Date: 28-Apr-25
Note on MW251: Activity Name: Install Drywall [Elec + Battery Rooms] Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Start Date: 29-Apr-25 End Date: 02-May-25
Note on NC251: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Start Date: 05-May-25 End Date: 05-May-25
Note on NG251: Activity Name: General Cleaning Phase: Fitout Location: CELL 4 Electrical Room Trade: Cx Start Date: 09-May-25 End Date: 09-May-25
Note on NH251: Activity Name: Set Electrical Equipments Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 10-May-25 End Date: 14-May-25
Note on NZ251: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 28-May-25 End Date: 09-Jun-25
Note on OO251: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 12-Jun-25 End Date: 25-Jun-25
Note on PC251: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 26-Jun-25 End Date: 10-Jul-25
Note on KF252: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Start Date: 19-Feb-25 End Date: 20-Feb-25
Note on KK252: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Start Date: 24-Feb-25 End Date: 25-Feb-25
Note on LI252: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 20-Mar-25 End Date: 25-Mar-25
Note on LO252: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Start Date: 26-Mar-25 End Date: 27-Mar-25
Note on LT252: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Start Date: 31-Mar-25 End Date: 01-Apr-25
Note on MW252: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Start Date: 29-Apr-25 End Date: 30-Apr-25
Note on NC252: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Start Date: 05-May-25 End Date: 06-May-25
Note on OM252: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 10-Jun-25 End Date: 23-Jun-25
Note on PC252: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 26-Jun-25 End Date: 30-Jun-25
Note on KH253: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Start Date: 21-Feb-25 End Date: 22-Feb-25
Note on KL253: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 25-Feb-25 End Date: 26-Feb-25
Note on LQ253: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Start Date: 28-Mar-25 End Date: 29-Mar-25
Note on LU253: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 01-Apr-25 End Date: 02-Apr-25
Note on MY253: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Start Date: 01-May-25 End Date: 02-May-25
Note on ND253: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 06-May-25 End Date: 07-May-25
Note on OM253: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 10-Jun-25 End Date: 13-Jun-25
Note on KM254: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 4 Electrical Room Trade: Paiting Start Date: 26-Feb-25 End Date: 27-Feb-25
Note on LV254: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 4 Electrical Room Trade: Paiting Start Date: 02-Apr-25 End Date: 03-Apr-25
Note on NE254: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 4 Electrical Room Trade: Paiting Start Date: 07-May-25 End Date: 08-May-25
Note on MT255: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Start Date: 26-Apr-25 End Date: 09-May-25
Note on KH258: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Fire Protection Start Date: 21-Feb-25 End Date: 22-Feb-25
Note on KK258: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 24-Feb-25 End Date: 26-Feb-25
Note on KN258: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 27-Feb-25 End Date: 06-Mar-25
Note on LA258: Activity Name: Install Drywall [Mech Gallery] Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 12-Mar-25 End Date: 13-Mar-25
Note on LC258: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 14-Mar-25 End Date: 14-Mar-25
Note on LH258: Activity Name: General Cleaning Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Cx Start Date: 19-Mar-25 End Date: 21-Mar-25
Note on LW258: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 03-Apr-25 End Date: 09-Apr-25
Note on MJ258: Activity Name: Install Drywall [Mech Gallery] Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 16-Apr-25 End Date: 17-Apr-25
Note on ML258: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 18-Apr-25 End Date: 18-Apr-25
Note on MQ258: Activity Name: General Cleaning Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Cx Start Date: 23-Apr-25 End Date: 25-Apr-25
Note on NF258: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 08-May-25 End Date: 14-May-25
Note on NR258: Activity Name: Install Drywall [Mech Gallery] Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 20-May-25 End Date: 21-May-25
Note on NT258: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 22-May-25 End Date: 22-May-25
Note on NZ258: Activity Name: General Cleaning Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Cx Start Date: 28-May-25 End Date: 30-May-25
Note on OM258: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: BAS Start Date: 10-Jun-25 End Date: 19-Jun-25
Note on OW258: Activity Name: Terminate Mechanical Equipments Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 20-Jun-25 End Date: 24-Jun-25
Note on KK259: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Fire Protection Start Date: 24-Feb-25 End Date: 25-Feb-25
Note on KV259: Activity Name: Overhead R/I - Plumbing Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Plumbing Start Date: 07-Mar-25 End Date: 13-Mar-25
Note on LC259: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 14-Mar-25 End Date: 15-Mar-25
Note on LI259: Activity Name: Install BAS Equipments Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: BAS Start Date: 20-Mar-25 End Date: 01-Apr-25
Note on MD259: Activity Name: Overhead R/I - Plumbing Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Plumbing Start Date: 10-Apr-25 End Date: 17-Apr-25
Note on ML259: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 18-Apr-25 End Date: 19-Apr-25
Note on MR259: Activity Name: Install BAS Equipments Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: BAS Start Date: 24-Apr-25 End Date: 06-May-25
Note on NM259: Activity Name: Overhead R/I - Plumbing Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Plumbing Start Date: 15-May-25 End Date: 21-May-25
Note on NT259: Activity Name: Finish Dry-Wall Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 22-May-25 End Date: 23-May-25
Note on OA259: Activity Name: Install BAS Equipments Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: BAS Start Date: 29-May-25 End Date: 09-Jun-25
Note on LD260: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 15-Mar-25 End Date: 19-Mar-25
Note on LI260: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 20-Mar-25 End Date: 21-Mar-25
Note on LM260: Activity Name: Set Mechanical Equipments Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 24-Mar-25 End Date: 27-Mar-25
Note on LQ260: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Fire Protection Start Date: 28-Mar-25 End Date: 29-Mar-25
Note on LT260: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 31-Mar-25 End Date: 02-Apr-25
Note on ME260: Activity Name: Terminate Mechanical Equipments Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MM260: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 19-Apr-25 End Date: 23-Apr-25
Note on MR260: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 24-Apr-25 End Date: 25-Apr-25
Note on MT260: Activity Name: Set Mechanical Equipments Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on MY260: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Fire Protection Start Date: 01-May-25 End Date: 02-May-25
Note on NC260: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 05-May-25 End Date: 07-May-25
Note on NN260: Activity Name: Terminate Mechanical Equipments Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 16-May-25 End Date: 20-May-25
Note on NU260: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Start Date: 23-May-25 End Date: 28-May-25
Note on OA260: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 29-May-25 End Date: 30-May-25
Note on OC260: Activity Name: Set Mechanical Equipments Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 31-May-25 End Date: 04-Jun-25
Note on OH260: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on LF261: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Paiting Start Date: 17-Mar-25 End Date: 18-Mar-25
Note on LT261: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Fire Protection Start Date: 31-Mar-25 End Date: 01-Apr-25
Note on LV261: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: BAS Start Date: 02-Apr-25 End Date: 10-Apr-25
Note on MO261: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Paiting Start Date: 21-Apr-25 End Date: 22-Apr-25
Note on NC261: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Fire Protection Start Date: 05-May-25 End Date: 06-May-25
Note on NE261: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: BAS Start Date: 07-May-25 End Date: 15-May-25
Note on NY261: Activity Name: Paint Dry-Wall Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Paiting Start Date: 27-May-25 End Date: 27-May-25
Note on LQ262: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on MY262: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Start Date: 01-May-25 End Date: 15-May-25
Note on NH265: Activity Name: Punchlist Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Start Date: 10-May-25 End Date: 21-May-25
Note on PD265: Activity Name: Punchlist Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PV265: Activity Name: Punchlist Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Start Date: 15-Jul-25 End Date: 25-Jul-25
Note on IY268: Activity Name: Layout Framing Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Start Date: 17-Jan-25 End Date: 17-Jan-25
Note on JB268: Activity Name: Install Framing Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Start Date: 20-Jan-25 End Date: 24-Jan-25
Note on JG268: Activity Name: In-Wall R/I Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Start Date: 25-Jan-25 End Date: 28-Jan-25
Note on JK268: Activity Name: Install Drywall (One Side - Facing DH) Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Start Date: 29-Jan-25 End Date: 31-Jan-25
Note on JN268: Activity Name: Finish Dry-Wall Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Start Date: 01-Feb-25 End Date: 04-Feb-25
Note on JS268: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Start Date: 06-Feb-25 End Date: 07-Feb-25
Note on JW268: Activity Name: Install Screen Mesh + Caulking Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Start Date: 10-Feb-25 End Date: 12-Feb-25
Note on JZ268: Activity Name: Install Secondary Steel Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KB268: Activity Name: Paint Secondary Steel Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Paiting Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KE268: Activity Name: General Cleaning Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Cx Start Date: 18-Feb-25 End Date: 18-Feb-25
Note on KI268: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: HAC's Start Date: 22-Feb-25 End Date: 27-Feb-25
Note on KU268: Activity Name: Raise HACs Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: HAC's Start Date: 06-Mar-25 End Date: 10-Mar-25
Note on KZ268: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Start Date: 11-Mar-25 End Date: 13-Mar-25
Note on LG268: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Start Date: 18-Mar-25 End Date: 24-Mar-25
Note on MH268: Activity Name: Terminate PDUs Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Start Date: 14-Apr-25 End Date: 16-Apr-25
Note on JK269: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Fire Protection Start Date: 29-Jan-25 End Date: 31-Jan-25
Note on JN269: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Start Date: 01-Feb-25 End Date: 05-Feb-25
Note on KE269: Activity Name: Install Ceiling Grid Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on KL269: Activity Name: Install Busways on HAC Arms Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Start Date: 25-Feb-25 End Date: 03-Mar-25
Note on KZ269: Activity Name: Detail HACs Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: HAC's Start Date: 11-Mar-25 End Date: 14-Mar-25
Note on JN270: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Fire Protection Start Date: 01-Feb-25 End Date: 04-Feb-25
Note on KI270: Activity Name: Install Perimeter Cable Trays Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Start Date: 22-Feb-25 End Date: 26-Feb-25
Note on KN270: Activity Name: Install Device Tiles Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Start Date: 27-Feb-25 End Date: 28-Feb-25
Note on LC270: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Start Date: 14-Mar-25 End Date: 17-Mar-25
Note on JQ271: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Start Date: 04-Feb-25 End Date: 05-Feb-25
Note on KN271: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Start Date: 27-Feb-25 End Date: 05-Mar-25
Note on JR272: Activity Name: Paint Dry-Wall Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Paiting Start Date: 05-Feb-25 End Date: 07-Feb-25
Note on KN272: Activity Name: Set PDUs Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Start Date: 27-Feb-25 End Date: 04-Mar-25
Note on JG276: Activity Name: Install Framing Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Start Date: 25-Jan-25 End Date: 30-Jan-25
Note on JM276: Activity Name: In-Wall R/I Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Start Date: 31-Jan-25 End Date: 10-Feb-25
Note on KB276: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Start Date: 15-Feb-25 End Date: 15-Feb-25
Note on KD276: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Start Date: 17-Feb-25 End Date: 18-Feb-25
Note on KI276: Activity Name: Finish Dry-Wall Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Start Date: 22-Feb-25 End Date: 04-Mar-25
Note on KT276: Activity Name: Paint Dry-Wall Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Paiting Start Date: 05-Mar-25 End Date: 06-Mar-25
Note on KV276: Activity Name: General Cleaning Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Cx Start Date: 07-Mar-25 End Date: 07-Mar-25
Note on KY276: Activity Name: Set Electrical Equipments Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Start Date: 10-Mar-25 End Date: 15-Mar-25
Note on LF276: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LT276: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Start Date: 31-Mar-25 End Date: 11-Apr-25
Note on JX277: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Fire Protection Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on LT277: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on JZ278: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Fire Protection Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on JZ282: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Fire Protection Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KB282: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Start Date: 15-Feb-25 End Date: 18-Feb-25
Note on KF282: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Start Date: 19-Feb-25 End Date: 25-Feb-25
Note on KS282: Activity Name: Install Drywall [Mech Gallery] Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Start Date: 04-Mar-25 End Date: 05-Mar-25
Note on KU282: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Start Date: 06-Mar-25 End Date: 06-Mar-25
Note on KZ282: Activity Name: General Cleaning Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Cx Start Date: 11-Mar-25 End Date: 13-Mar-25
Note on LN282: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Start Date: 25-Mar-25 End Date: 02-Apr-25
Note on LW282: Activity Name: Terminate Mechanical Equipments Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Start Date: 03-Apr-25 End Date: 07-Apr-25
Note on KB283: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Fire Protection Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KM283: Activity Name: Overhead R/I - Plumbing Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Plumbing Start Date: 26-Feb-25 End Date: 05-Mar-25
Note on KU283: Activity Name: Finish Dry-Wall Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on LA283: Activity Name: Install BAS Equipments Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: BAS Start Date: 12-Mar-25 End Date: 24-Mar-25
Note on KV284: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Start Date: 07-Mar-25 End Date: 11-Mar-25
Note on LA284: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Start Date: 12-Mar-25 End Date: 13-Mar-25
Note on LC284: Activity Name: Set Mechanical Equipments Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LH284: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on KW285: Activity Name: Paint Dry-Wall Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Paiting Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on JK288: Activity Name: Layout Framing Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Start Date: 29-Jan-25 End Date: 29-Jan-25
Note on JL288: Activity Name: Install Framing Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Start Date: 30-Jan-25 End Date: 01-Feb-25
Note on JP288: Activity Name: In-Wall R/I Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Start Date: 03-Feb-25 End Date: 05-Feb-25
Note on JS288: Activity Name: Install Drywall (One Side - Facing DH) Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Start Date: 06-Feb-25 End Date: 10-Feb-25
Note on JZ288: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KE288: Activity Name: Install Screen Mesh + Caulking Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Start Date: 18-Feb-25 End Date: 20-Feb-25
Note on KH288: Activity Name: Install Secondary Steel Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Start Date: 21-Feb-25 End Date: 22-Feb-25
Note on KK288: Activity Name: Paint Secondary Steel Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Paiting Start Date: 24-Feb-25 End Date: 25-Feb-25
Note on KM288: Activity Name: General Cleaning Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Cx Start Date: 26-Feb-25 End Date: 26-Feb-25
Note on KS288: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: HAC's Start Date: 04-Mar-25 End Date: 08-Mar-25
Note on LC288: Activity Name: Raise HACs Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: HAC's Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LH288: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Start Date: 19-Mar-25 End Date: 21-Mar-25
Note on LP288: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Start Date: 27-Mar-25 End Date: 01-Apr-25
Note on NG288: Activity Name: Terminate PDUs Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Start Date: 09-May-25 End Date: 12-May-25
Note on JS289: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Fire Protection Start Date: 06-Feb-25 End Date: 10-Feb-25
Note on JX289: Activity Name: Finish Dry-Wall Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Start Date: 11-Feb-25 End Date: 13-Feb-25
Note on KM289: Activity Name: Install Ceiling Grid Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KU289: Activity Name: Install Busways on HAC Arms Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Start Date: 06-Mar-25 End Date: 11-Mar-25
Note on LH289: Activity Name: Detail HACs Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: HAC's Start Date: 19-Mar-25 End Date: 24-Mar-25
Note on JX290: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Start Date: 11-Feb-25 End Date: 14-Feb-25
Note on KS290: Activity Name: Install Perimeter Cable Trays Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Start Date: 04-Mar-25 End Date: 07-Mar-25
Note on KW290: Activity Name: Install Device Tiles Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LM290: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Start Date: 24-Mar-25 End Date: 26-Mar-25
Note on JX291: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Fire Protection Start Date: 11-Feb-25 End Date: 13-Feb-25
Note on KW291: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Start Date: 08-Mar-25 End Date: 13-Mar-25
Note on JZ292: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KW292: Activity Name: Set PDUs Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Start Date: 08-Mar-25 End Date: 12-Mar-25
Note on KA293: Activity Name: Paint Dry-Wall Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Paiting Start Date: 14-Feb-25 End Date: 17-Feb-25
Note on JP296: Activity Name: Install Framing Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Framing Start Date: 03-Feb-25 End Date: 04-Feb-25
Note on JR296: Activity Name: In-Wall R/I Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Start Date: 05-Feb-25 End Date: 06-Feb-25
Note on JT296: Activity Name: Install Drywall [Elec + Battery Rooms] Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Framing Start Date: 07-Feb-25 End Date: 12-Feb-25
Note on JZ296: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Framing Start Date: 13-Feb-25 End Date: 13-Feb-25
Note on KE296: Activity Name: General Cleaning Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Cx Start Date: 18-Feb-25 End Date: 18-Feb-25
Note on LF296: Activity Name: Set Electrical Equipments Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Start Date: 17-Mar-25 End Date: 20-Mar-25
Note on MH296: Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Start Date: 14-Apr-25 End Date: 25-Apr-25
Note on MT296: Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Start Date: 26-Apr-25 End Date: 08-May-25
Note on JT297: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Fire Protection Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on JZ297: Activity Name: Finish Dry-Wall Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Framing Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on MT297: Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on JX298: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Fire Protection Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on KA298: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Start Date: 14-Feb-25 End Date: 15-Feb-25
Note on KB299: Activity Name: Paint Dry-Wall Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Paiting Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on JX302: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Fire Protection Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on JZ302: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Start Date: 13-Feb-25 End Date: 15-Feb-25
Note on KD302: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Start Date: 17-Feb-25 End Date: 22-Feb-25
Note on KO302: Activity Name: Install Drywall [Mech Gallery] Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Start Date: 28-Feb-25 End Date: 03-Mar-25
Note on KS302: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Start Date: 04-Mar-25 End Date: 04-Mar-25
Note on KW302: Activity Name: General Cleaning Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Cx Start Date: 08-Mar-25 End Date: 11-Mar-25
Note on LJ302: Activity Name: Pull & Terminate BAS Equipments Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: BAS Start Date: 21-Mar-25 End Date: 31-Mar-25
Note on LU302: Activity Name: Terminate Mechanical Equipments Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Start Date: 01-Apr-25 End Date: 04-Apr-25
Note on JZ303: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Fire Protection Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KK303: Activity Name: Overhead R/I - Plumbing Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Plumbing Start Date: 24-Feb-25 End Date: 03-Mar-25
Note on KS303: Activity Name: Finish Dry-Wall Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Start Date: 04-Mar-25 End Date: 05-Mar-25
Note on KY303: Activity Name: Install BAS Equipments Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: BAS Start Date: 10-Mar-25 End Date: 20-Mar-25
Note on KT304: Activity Name: Install Ceiling Grid + Device Tiles Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Start Date: 05-Mar-25 End Date: 08-Mar-25
Note on KY304: Activity Name: Install Cable Trays / Pathways Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Start Date: 10-Mar-25 End Date: 11-Mar-25
Note on LA304: Activity Name: Set Mechanical Equipments Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Start Date: 12-Mar-25 End Date: 15-Mar-25
Note on LF304: Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on KU305: Activity Name: Paint Dry-Wall Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Paiting Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on NK308: Activity Name: Punchlist Phase: Fitout Location: COLO 3 - CELL 2 Punchlist Trade: Punchlist Start Date: 13-May-25 End Date: 23-May-25
Note on KH309: Activity Name: Layout Framing Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Start Date: 21-Feb-25 End Date: 21-Feb-25
Note on KI309: Activity Name: Install Framing Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Start Date: 22-Feb-25 End Date: 25-Feb-25
Note on KM309: Activity Name: In-Wall R/I Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Start Date: 26-Feb-25 End Date: 28-Feb-25
Note on KR309: Activity Name: Install Drywall (One Side - Facing DH) Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Start Date: 03-Mar-25 End Date: 05-Mar-25
Note on KW309: Activity Name: Drop Cable Tray [Hanging Rods] Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LB309: Activity Name: Install Screen Mesh + Caulking Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Start Date: 13-Mar-25 End Date: 15-Mar-25
Note on LF309: Activity Name: Install Secondary Steel Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Start Date: 17-Mar-25 End Date: 18-Mar-25
Note on LH309: Activity Name: Paint Secondary Steel Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Paiting Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on LJ309: Activity Name: General Cleaning Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Cx Start Date: 21-Mar-25 End Date: 21-Mar-25
Note on LP309: Activity Name: Assemble HACs [Qty - 5] Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: HAC's Start Date: 27-Mar-25 End Date: 01-Apr-25
Note on MA309: Activity Name: Raise HACs Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: HAC's Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on ME309: Activity Name: Connect Perimeter Cable Trays to HAC Cable Trays Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Start Date: 11-Apr-25 End Date: 15-Apr-25
Note on MM309: Activity Name: Pull Feeders from PDUs to Busways Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Start Date: 19-Apr-25 End Date: 24-Apr-25
Note on OH309: Activity Name: Terminate PDUs Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Start Date: 05-Jun-25 End Date: 07-Jun-25
Note on KR310: Activity Name: Overhead R/I - Fire Protection Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Fire Protection Start Date: 03-Mar-25 End Date: 05-Mar-25
Note on KU310: Activity Name: Finish Dry-Wall Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Start Date: 06-Mar-25 End Date: 08-Mar-25
Note on LJ310: Activity Name: Install Ceiling Grid Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Start Date: 21-Mar-25 End Date: 26-Mar-25
Note on LR310: Activity Name: Install Busways on HAC Arms Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Start Date: 29-Mar-25 End Date: 03-Apr-25
Note on ME310: Activity Name: Detail HACs Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: HAC's Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on KU311: Activity Name: Overhead R/I - Electrical Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Start Date: 06-Mar-25 End Date: 10-Mar-25
Note on LP311: Activity Name: Install Perimeter Cable Trays Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Start Date: 27-Mar-25 End Date: 31-Mar-25
Note on LU311: Activity Name: Install Device Tiles Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Start Date: 01-Apr-25 End Date: 02-Apr-25
Note on MJ311: Activity Name: Install Conduits PDU to Cable Trays Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Start Date: 16-Apr-25 End Date: 18-Apr-25
Note on KU312: Activity Name: Overhead R/I - Fire Alarm Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Fire Protection Start Date: 06-Mar-25 End Date: 08-Mar-25
Note on LU312: Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Start Date: 01-Apr-25 End Date: 05-Apr-25
Note on KW313: Activity Name: Overhead R/I - Mechanical Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LU313: Activity Name: Set PDUs Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Start Date: 01-Apr-25 End Date: 04-Apr-25
Note on KY314: Activity Name: Paint Dry-Wall Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Paiting Start Date: 10-Mar-25 End Date: 12-Mar-25
Note on JB317: Activity Name: Fire Protection OH R/I Phase: Fitout Location: Electrical Room Trade: Framing Start Date: 20-Jan-25 End Date: 20-Jan-25
Note on JC317: Activity Name: Framing Phase: Fitout Location: Electrical Room Trade: Framing Start Date: 21-Jan-25 End Date: 21-Jan-25
Note on JD317: Activity Name: MEP Rough-In & OH Phase: Fitout Location: Electrical Room Trade: MEP Start Date: 22-Jan-25 End Date: 23-Jan-25
Note on JF317: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Location: Electrical Room Trade: Framing Start Date: 24-Jan-25 End Date: 25-Jan-25
Note on JI317: Activity Name: Secondary / Ceiling Steel Phase: Fitout Location: Electrical Room Trade: Framing Start Date: 27-Jan-25 End Date: 27-Jan-25
Note on JJ317: Activity Name: Finsh Drywall and Wall Protection Phase: Fitout Location: Electrical Room Trade: Framing Start Date: 28-Jan-25 End Date: 31-Jan-25
Note on JN317: Activity Name: Paint Phase: Fitout Location: Electrical Room Trade: Paiting Start Date: 01-Feb-25 End Date: 03-Feb-25
Note on JQ317: Activity Name: Cable Tray / Ceiling Steel Height Phase: Fitout Location: Electrical Room Trade: Electrical Start Date: 04-Feb-25 End Date: 04-Feb-25
Note on KR317: Activity Name: Set Electrical Equipment in Admin Phase: Fitout Location: Electrical Room Trade: Electrical Start Date: 03-Mar-25 End Date: 11-Mar-25
Note on LA317: Activity Name: Pull Feeders to Admin Phase: Fitout Location: Electrical Room Trade: Electrical Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LR317: Activity Name: Pull Branches From Admin Phase: Fitout Location: Electrical Room Trade: Electrical Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on MH317: Activity Name: Terminate Electrical / Mechanical Equipment Phase: Fitout Location: Electrical Room Trade: Electrical Start Date: 14-Apr-25 End Date: 17-Apr-25
Note on JC321: Activity Name: Fire Protection OH R/I Phase: Fitout Location: Entry Room 1 Trade: Fire Protection Start Date: 21-Jan-25 End Date: 21-Jan-25
Note on JD321: Activity Name: Framing Phase: Fitout Location: Entry Room 1 Trade: Framing Start Date: 22-Jan-25 End Date: 22-Jan-25
Note on JF321: Activity Name: MEP Rough-In & OH Phase: Fitout Location: Entry Room 1 Trade: MEP Start Date: 24-Jan-25 End Date: 25-Jan-25
Note on JI321: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Location: Entry Room 1 Trade: Framing Start Date: 27-Jan-25 End Date: 28-Jan-25
Note on JK321: Activity Name: Secondary / Ceiling Steel Phase: Fitout Location: Entry Room 1 Trade: Framing Start Date: 29-Jan-25 End Date: 29-Jan-25
Note on JL321: Activity Name: Finsh Drywall and Wall Protection Phase: Fitout Location: Entry Room 1 Trade: Framing Start Date: 30-Jan-25 End Date: 03-Feb-25
Note on JQ321: Activity Name: Paint Phase: Fitout Location: Entry Room 1 Trade: Paiting Start Date: 04-Feb-25 End Date: 05-Feb-25
Note on JS321: Activity Name: Install Raceway Phase: Fitout Location: Entry Room 1 Trade: Framing Start Date: 06-Feb-25 End Date: 10-Feb-25
Note on JX321: Activity Name: Set ER-1 Equipment Phase: Fitout Location: Entry Room 1 Trade: Electrical Start Date: 11-Feb-25 End Date: 14-Feb-25
Note on JD325: Activity Name: Fire Protection OH R/I Phase: Fitout Location: Entry Room 2 Trade: Fire Protection Start Date: 22-Jan-25 End Date: 22-Jan-25
Note on JE325: Activity Name: Framing Phase: Fitout Location: Entry Room 2 Trade: Framing Start Date: 23-Jan-25 End Date: 23-Jan-25
Note on JI325: Activity Name: MEP Rough-In & OH Phase: Fitout Location: Entry Room 2 Trade: MEP Start Date: 27-Jan-25 End Date: 28-Jan-25
Note on JK325: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Location: Entry Room 2 Trade: Framing Start Date: 29-Jan-25 End Date: 30-Jan-25
Note on JM325: Activity Name: Secondary / Ceiling Steel Phase: Fitout Location: Entry Room 2 Trade: Framing Start Date: 31-Jan-25 End Date: 31-Jan-25
Note on JN325: Activity Name: Finsh Drywall and Wall Protection Phase: Fitout Location: Entry Room 2 Trade: Framing Start Date: 01-Feb-25 End Date: 05-Feb-25
Note on JS325: Activity Name: Paint Phase: Fitout Location: Entry Room 2 Trade: Paiting Start Date: 06-Feb-25 End Date: 07-Feb-25
Note on JW325: Activity Name: Install Raceway Phase: Fitout Location: Entry Room 2 Trade: Framing Start Date: 10-Feb-25 End Date: 12-Feb-25
Note on JZ325: Activity Name: Set ER-2 Equipment Phase: Fitout Location: Entry Room 2 Trade: Electrical Start Date: 13-Feb-25 End Date: 17-Feb-25
Note on JE329: Activity Name: Fire Protection OH R/I Phase: Fitout Location: FCR (Facilities Control Room) Trade: Fire Protection Start Date: 23-Jan-25 End Date: 23-Jan-25
Note on JF329: Activity Name: Framing Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Start Date: 24-Jan-25 End Date: 24-Jan-25
Note on JK329: Activity Name: MEP Rough-In & OH Phase: Fitout Location: FCR (Facilities Control Room) Trade: MEP Start Date: 29-Jan-25 End Date: 30-Jan-25
Note on JM329: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Start Date: 31-Jan-25 End Date: 01-Feb-25
Note on JP329: Activity Name: Secondary / Ceiling Steel Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Start Date: 03-Feb-25 End Date: 03-Feb-25
Note on JQ329: Activity Name: Finsh Drywall and Wall Protection Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Start Date: 04-Feb-25 End Date: 07-Feb-25
Note on JW329: Activity Name: Paint Phase: Fitout Location: FCR (Facilities Control Room) Trade: Paiting Start Date: 10-Feb-25 End Date: 11-Feb-25
Note on JY329: Activity Name: Install Raceway Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Start Date: 12-Feb-25 End Date: 14-Feb-25
Note on KB329: Activity Name: Set FCR Equipment Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Start Date: 15-Feb-25 End Date: 19-Feb-25
Note on KG329: Activity Name: Pull Copper for EPMS VLAN Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KV329: Activity Name: Pull Copper for Tahuya VLAN Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LJ329: Activity Name: Pull Copper for BAS VLAN Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on LY329: Activity Name: Pull Fiber/Copper For CORPNET Network Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MO329: Activity Name: Pull Fiber For CEI Network Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Start Date: 21-Apr-25 End Date: 05-May-25
Note on KG330: Activity Name: Pull Fiber For EPMS VLAN Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KV330: Activity Name: Pull Fiber For Tahuya VLAN Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LJ330: Activity Name: Pull Fiber For BAS VLAN Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on JI334: Activity Name: Fire Protection OH R/I Phase: Fitout Location: Fire Riser Room Trade: Fire Protection Start Date: 27-Jan-25 End Date: 27-Jan-25
Note on JJ334: Activity Name: Framing Phase: Fitout Location: Fire Riser Room Trade: Framing Start Date: 28-Jan-25 End Date: 28-Jan-25
Note on JK334: Activity Name: Install Duct Work Phase: Fitout Location: Fire Riser Room Trade: Framing Start Date: 29-Jan-25 End Date: 30-Jan-25
Note on JM334: Activity Name: Install downcomers Phase: Fitout Location: Fire Riser Room Trade: Framing Start Date: 31-Jan-25 End Date: 31-Jan-25
Note on JR334: Activity Name: MEP Rough-In & OH Phase: Fitout Location: Fire Riser Room Trade: MEP Start Date: 05-Feb-25 End Date: 06-Feb-25
Note on JT334: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Location: Fire Riser Room Trade: Framing Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on JX334: Activity Name: Secondary / Ceiling Steel Phase: Fitout Location: Fire Riser Room Trade: Framing Start Date: 11-Feb-25 End Date: 11-Feb-25
Note on JY334: Activity Name: Finish Dry-Wall Phase: Fitout Location: Fire Riser Room Trade: Framing Start Date: 12-Feb-25 End Date: 13-Feb-25
Note on KA334: Activity Name: Paint Phase: Fitout Location: Fire Riser Room Trade: Paiting Start Date: 14-Feb-25 End Date: 15-Feb-25
Note on KE334: Activity Name: Ceiling Grid & Tile Phase: Fitout Location: Fire Riser Room Trade: Framing Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on KI334: Activity Name: Complete Pipe/ Valves Phase: Fitout Location: Fire Riser Room Trade: Fire Protection Start Date: 22-Feb-25 End Date: 24-Feb-25
Note on JK338: Activity Name: Fire Protection OH R/I Phase: Fitout Location: Loading Dock Trade: Fire Protection Start Date: 29-Jan-25 End Date: 29-Jan-25
Note on JL338: Activity Name: Framing Phase: Fitout Location: Loading Dock Trade: Framing Start Date: 30-Jan-25 End Date: 30-Jan-25
Note on KB338: Activity Name: Finish Dry-Wall Phase: Fitout Location: Loading Dock Trade: Framing Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KE338: Activity Name: Paint Phase: Fitout Location: Loading Dock Trade: Paiting Start Date: 18-Feb-25 End Date: 19-Feb-25
Note on KG338: Activity Name: Plumbing Phase: Fitout Location: Loading Dock Trade: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KZ338: Activity Name: Pull Cables Phase: Fitout Location: Loading Dock Trade: Electrical Start Date: 11-Mar-25 End Date: 13-Mar-25
Note on JK339: Activity Name: Install Ductwork Phase: Fitout Location: Loading Dock Trade: Framing Start Date: 29-Jan-25 End Date: 15-Feb-25
Note on JL340: Activity Name: Install Ductwork (Remaining Rooms, Corridor) Phase: Fitout Location: Loading Dock Trade: Framing Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on JM341: Activity Name: Rough-in Phase: Fitout Location: Loading Dock Trade: Milestone Start Date: 31-Jan-25 End Date: 31-Jan-25
Note on JX341: Activity Name: MEP Rough-In & OH Phase: Fitout Location: Loading Dock Trade: MEP Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on JZ341: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Location: Loading Dock Trade: Framing Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on JI344: Activity Name: Remaining Rooms Phase: Fitout Location: Punchlist Trade: Punchlist Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on ND344: Activity Name: Beneficial Rooms PunchList Phase: Fitout Location: Punchlist Trade: Punchlist Start Date: 06-May-25 End Date: 09-May-25
Note on JJ346: Activity Name: Fire Protection OH R/I Phase: Fitout Location: Restrooms & Janitor Room Trade: Fire Protection Start Date: 28-Jan-25 End Date: 28-Jan-25
Note on JK346: Activity Name: Framing Phase: Fitout Location: Restrooms & Janitor Room Trade: Framing Start Date: 29-Jan-25 End Date: 29-Jan-25
Note on JT346: Activity Name: MEP Rough-In & OH Phase: Fitout Location: Restrooms & Janitor Room Trade: MEP Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on JX346: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Location: Restrooms & Janitor Room Trade: Framing Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on JZ346: Activity Name: Finish Dry-Wall Phase: Fitout Location: Restrooms & Janitor Room Trade: Framing Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KB346: Activity Name: Paint Phase: Fitout Location: Restrooms & Janitor Room Trade: Paiting Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KE346: Activity Name: Ceiling Grid & Tile Phase: Fitout Location: Restrooms & Janitor Room Trade: Framing Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on JF350: Activity Name: Fire Protection OH R/I Phase: Fitout Location: SER (Security Equipment Room) Trade: Fire Protection Start Date: 24-Jan-25 End Date: 24-Jan-25
Note on JG350: Activity Name: Framing Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Start Date: 25-Jan-25 End Date: 25-Jan-25
Note on JM350: Activity Name: MEP Rough-In & OH Phase: Fitout Location: SER (Security Equipment Room) Trade: MEP Start Date: 31-Jan-25 End Date: 01-Feb-25
Note on JP350: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Start Date: 03-Feb-25 End Date: 04-Feb-25
Note on JR350: Activity Name: Secondary / Ceiling Steel Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Start Date: 05-Feb-25 End Date: 05-Feb-25
Note on JS350: Activity Name: Finish Dry-Wall Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Start Date: 06-Feb-25 End Date: 07-Feb-25
Note on JW350: Activity Name: Paint Phase: Fitout Location: SER (Security Equipment Room) Trade: Paiting Start Date: 10-Feb-25 End Date: 11-Feb-25
Note on JY350: Activity Name: Install Raceway Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Start Date: 12-Feb-25 End Date: 14-Feb-25
Note on KB350: Activity Name: Set SER Room Equipment Phase: Fitout Location: SER (Security Equipment Room) Trade: HAC's Start Date: 15-Feb-25 End Date: 19-Feb-25
Note on JG354: Activity Name: Fire Protection OH R/I Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Start Date: 25-Jan-25 End Date: 25-Jan-25
Note on JI354: Activity Name: Framing Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Start Date: 27-Jan-25 End Date: 27-Jan-25
Note on JP354: Activity Name: MEP Rough-In & OH Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: MEP Start Date: 03-Feb-25 End Date: 04-Feb-25
Note on JR354: Activity Name: Top Out Drywall - Ceiling Steel Height Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Start Date: 05-Feb-25 End Date: 06-Feb-25
Note on JT354: Activity Name: Install Ductwork and Cracs Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KM354: Activity Name: Finish Dry-Wall Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KS354: Activity Name: Paint Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Paiting Start Date: 04-Mar-25 End Date: 05-Mar-25
Note on KU354: Activity Name: Fire Protection OH R/I Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Start Date: 06-Mar-25 End Date: 17-Mar-25
Note on DU358: Activity Name: OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/04/24) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on FY358: Activity Name: OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 4/30/24) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on HC358: Activity Name: OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 11/28/24) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 30-Nov-24 End Date: 30-Nov-24
Note on KJ358: Activity Name: OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 23-Feb-25 End Date: 23-Feb-25
Note on KK358: Activity Name: OFCI- Packaged Diesel Generator Set (CAT Holt) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 24-Feb-25 End Date: 24-Feb-25
Note on KS358: Activity Name: OFCI- LV Switchgear (LVS) (Eaton) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 04-Mar-25 End Date: 04-Mar-25
Note on KW358: Activity Name: OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date- 3/8/2025) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 08-Mar-25 End Date: 08-Mar-25
Note on LB358: Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 13-Mar-25 End Date: 13-Mar-25
Note on DU359: Activity Name: OFCI- Receive Busway / Busplugs (Starline Holding) (Del Date- 1/25/24) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on FY359: Activity Name: OFCI- Receive Elec. Performance Monitoring System (EPMS) (Schneider) (SOW Del Date- 4/30/24) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on KF359: Activity Name: OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 19-Feb-25 End Date: 23-Feb-25
Note on KO359: Activity Name: OFCI- Receive LV Switchgear (LVS) (Eaton) (SOW Del Date- 2/28/25) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 28-Feb-25 End Date: 28-Feb-25
Note on KW359: Activity Name: OFCI- Receive Auxillary (Mech) Power Distribution Panels (ADP) (Del Date- 3/8/2025) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 08-Mar-25 End Date: 08-Mar-25
Note on KX359: Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Shipped/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 09-Mar-25 End Date: 13-Mar-25
Note on DU360: Activity Name: OFCI- Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 7/30/24) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on FY360: Activity Name: OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 5/17/24) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on KJ360: Activity Name: OFCI- Building Automation System (BAS) (ALC) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 23-Feb-25 End Date: 23-Feb-25
Note on KW360: Activity Name: OFCI- Auto Transfer Control Panel (TCP) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 08-Mar-25 End Date: 08-Mar-25
Note on DU361: Activity Name: OFCI- Received SUB Warehouse 9/28/2023 UPS System w/ Battery (UPS) (Eaton) (SOW Del Date- 8/13/23) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on FY361: Activity Name: OFCI- Receive Packaged Diesel Generator Set (CAT Holt) (SOW Del Date- 5/14/24) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on KF361: Activity Name: OFCI- Building Automation System (BAS) (ALC) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 19-Feb-25 End Date: 23-Feb-25
Note on KW361: Activity Name: OFCI- Auto Transfer Control Panel (TCP) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 08-Mar-25 End Date: 08-Mar-25
Note on FY362: Activity Name: OFCI- Receive Pad Mounted Transformers (XFM-TX) (Del Date- 7/30/2024) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on KH362: Activity Name: OFCI- HAC/Racking (Tate Access) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 21-Feb-25 End Date: 21-Feb-25
Note on KJ362: Activity Name: OFCI- Busway / Busplugs (Starline Holding) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 23-Feb-25 End Date: 23-Feb-25
Note on KW362: Activity Name: OFCI- Auxillary (Mech) Power Distribution Panels (ADP) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 08-Mar-25 End Date: 08-Mar-25
Note on FY363: Activity Name: OFCI- Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 4/30/24) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on KF363: Activity Name: OFCI- HAC/Racking (Tate Access) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 19-Feb-25 End Date: 21-Feb-25
Note on KW363: Activity Name: OFCI- Auxillary (Mech) Power Distribution Panels (ADP) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 08-Mar-25 End Date: 08-Mar-25
Note on FY364: Activity Name: OFCI- Receive Utility Pad Mount Switchgear (Del Date- 7/30/2024) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on KJ364: Activity Name: OFCI- Elec. Performance Monitoring System (EPMS) (Schneider) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 23-Feb-25 End Date: 23-Feb-25
Note on KW364: Activity Name: OFCI- Main LV Switch Board (MSB) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 08-Mar-25 End Date: 08-Mar-25
Note on KF365: Activity Name: OFCI- Elec. Performance Monitoring System (EPMS) (Schneider) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 19-Feb-25 End Date: 23-Feb-25
Note on KW365: Activity Name: OFCI- Main LV Switch Board (MSB) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 08-Mar-25 End Date: 08-Mar-25
Note on KJ366: Activity Name: OFCI- Medium Voltage Switchgear (MVS) (JD Power Sys) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 23-Feb-25 End Date: 23-Feb-25
Note on KW366: Activity Name: OFCI- Receive Main LV Switch Board (MSB) (SOW Del Date- 3/8/2025) Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 08-Mar-25 End Date: 08-Mar-25
Note on KF367: Activity Name: OFCI- Medium Voltage Switchgear (MVS) (JD Power Sys) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 19-Feb-25 End Date: 23-Feb-25
Note on KG368: Activity Name: OFCI- Packaged Diesel Generator Set (CAT Holt) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 20-Feb-25 End Date: 24-Feb-25
Note on KJ369: Activity Name: OFCI- Pad Mounted Transformers (XFM-TX) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 23-Feb-25 End Date: 23-Feb-25
Note on KK369: Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 24-Feb-25 End Date: 28-Feb-25
Note on KF370: Activity Name: OFCI- Pad Mounted Transformers (XFM-TX) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 19-Feb-25 End Date: 23-Feb-25
Note on KJ371: Activity Name: OFCI- Power Distribution Units (PDU) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 23-Feb-25 End Date: 23-Feb-25
Note on KF372: Activity Name: OFCI- Power Distribution Units (PDU) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 19-Feb-25 End Date: 23-Feb-25
Note on KJ373: Activity Name: OFCI- UPS System w/ Battery (UPS) (Eaton) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 23-Feb-25 End Date: 23-Feb-25
Note on KF374: Activity Name: OFCI- UPS System w/ Battery (UPS) (Eaton) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 19-Feb-25 End Date: 23-Feb-25
Note on KF375: Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Start Date: 19-Feb-25 End Date: 23-Feb-25
Note on EW379: Activity Name: OFCI- Receive PEMB Procurement (1st Del) (Nucor) (SOW Del Date-10/3/24) Phase: MSFT OFCI ROJ Dates Location: COLO 3-5 Trade: ROJ Start Date: 03-Oct-24 End Date: 03-Oct-24
Note on FS379: Activity Name: OFCI- PEMB Procurement (1st Del) (Nucor) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 3-5 Trade: ROJ Start Date: 25-Oct-24 End Date: 25-Oct-24
Note on FO380: Activity Name: OFCI- PEMB Procurement (1st Del) (Nucor) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 3-5 Trade: ROJ Start Date: 21-Oct-24 End Date: 25-Oct-24
Note on DU382: Activity Name: OFCI- Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 8/30/24) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on DY382: Activity Name: OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/9/24) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 09-Sep-24 End Date: 09-Sep-24
Note on FY382: Activity Name: OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 6/30/24) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on IL382: Activity Name: OFCI- Building Automation System (BAS) (Automated Logic Corp) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 04-Jan-25 End Date: 04-Jan-25
Note on KQ382: Activity Name: OFCI- LV Switchgear (Eaton) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 02-Mar-25 End Date: 02-Mar-25
Note on LS382: Activity Name: OFCI- Auto Transfer Control Panel (TCP) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LY382: Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 05-Apr-25 End Date: 05-Apr-25
Note on MD382: Activity Name: OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 10-Apr-25 End Date: 10-Apr-25
Note on DU383: Activity Name: OFCI- Received SUB Warehouse 11/23/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 11/11/23) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on FY383: Activity Name: OFCI- Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 2/23/24) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on IF383: Activity Name: OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 12/29/24) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 29-Dec-24 End Date: 29-Dec-24
Note on KO383: Activity Name: OFCI- Receive LV Switchgear (Eaton) (SOW Del Date- 2/28/25) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 28-Feb-25 End Date: 28-Feb-25
Note on LS383: Activity Name: OFCI- Auto Transfer Control Panel (TCP) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LU383: Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Shipping/ ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 01-Apr-25 End Date: 05-Apr-25
Note on LZ383: Activity Name: OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 06-Apr-25 End Date: 10-Apr-25
Note on FY384: Activity Name: OFCI- Receive Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) (SOW Del Date- 6/30/24) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on LS384: Activity Name: OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on FY385: Activity Name: OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 6/18/24) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on LO385: Activity Name: OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LQ385: Activity Name: OFCI- HAC/Racking (Tate Access) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 28-Mar-25 End Date: 28-Mar-25
Note on FY386: Activity Name: OFCI- Receive Packaged Diesel Generator Set (GEN) (CAT Holt) (SOW Del Date- 6/4/24) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on LO386: Activity Name: OFCI- HAC/Racking (Tate Access) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 26-Mar-25 End Date: 28-Mar-25
Note on LS386: Activity Name: OFCI- Busway / Busplugs (BSW) (Starline Holding) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on FY387: Activity Name: OFCI- Receive Utility Pad Mount Switchgear (UPM) (Del Date 8/30/2024) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on LO387: Activity Name: OFCI- Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on FY388: Activity Name: OFCI- Reveive Pad Mounted Transformers (XMF) (Del Date 8/30/2024) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on LS388: Activity Name: OFCI- Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on FY389: Activity Name: OFCI- Reveive Power Distribution Units (PDU) (ABB) (SOW Del Date- 7/12/24) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on LO389: Activity Name: OFCI- Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LS390: Activity Name: OFCI- Main LV Switch Board (MSB) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LS391: Activity Name: OFCI- Main LV Switch Board (MSB) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LS392: Activity Name: OFCI- Mech Power Distribution Panels (ADP) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LS393: Activity Name: OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LS394: Activity Name: OFCI- Medium Voltage Switchgear (JDC Power Sys) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LO395: Activity Name: OFCI- Medium Voltage Switchgear (JDC Power Sys) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LS396: Activity Name: OFCI- Pad Mounted Transformers (XMF) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LO397: Activity Name: OFCI- Pad Mounted Transformers (XMF) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LS398: Activity Name: OFCI- Power Distribution Units (PDU) (ABB) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LO399: Activity Name: OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LS400: Activity Name: OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date-3/30/2025) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LS401: Activity Name: OFCI- Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LS402: Activity Name: OFCI- Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LS403: Activity Name: OFCI- Static UPS System W/Batt (UPS) (Eaton) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LO404: Activity Name: OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LS405: Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LO406: Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on DU410: Activity Name: OFCI- Received SUB Warehouse 12/28/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 12/11/23) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on EF410: Activity Name: OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/16/24) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 16-Sep-24 End Date: 16-Sep-24
Note on FX410: Activity Name: OFCI- Receive Medium Voltage Switchgear (MVS) (JDC Power Sys) (SOW Del Date- 10/30/24) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 30-Oct-24 End Date: 30-Oct-24
Note on FY410: Activity Name: OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 8/31/24) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on JO410: Activity Name: OFCI- Building Automation System (BAS) (Automated Logic Corp) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 02-Feb-25 End Date: 02-Feb-25
Note on LX410: Activity Name: OFCI- Auto Transfer Control Panel (TCP) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 04-Apr-25 End Date: 04-Apr-25
Note on MN410: Activity Name: OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 20-Apr-25 End Date: 20-Apr-25
Note on MV410: Activity Name: OFCI- HAC/Racking (Tate Access) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 28-Apr-25 End Date: 28-Apr-25
Note on NA410: Activity Name: OFCI- Busway / Busplugs (BSW) (Starline Holding) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 03-May-25 End Date: 03-May-25
Note on NE410: Activity Name: OFCI- Power Distribution Units (PDU) (ABB) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 07-May-25 End Date: 07-May-25
Note on NI410: Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 11-May-25 End Date: 11-May-25
Note on NM410: Activity Name: OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 15-May-25 End Date: 15-May-25
Note on FY411: Activity Name: OFCI- Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 4/23/24) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on JJ411: Activity Name: OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 1/28/25) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 28-Jan-25 End Date: 28-Jan-25
Note on LS411: Activity Name: OFCI- Auto Transfer Control Panel (TCP) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 30-Mar-25 End Date: 04-Apr-25
Note on LW411: Activity Name: OFCI- LV Switchgear (Eaton) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 03-Apr-25 End Date: 03-Apr-25
Note on MN411: Activity Name: OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 20-Apr-25 End Date: 20-Apr-25
Note on MS411: Activity Name: OFCI- HAC/Racking (Tate Access) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 25-Apr-25 End Date: 28-Apr-25
Note on MW411: Activity Name: OFCI- Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 29-Apr-25 End Date: 03-May-25
Note on NI411: Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 11-May-25 End Date: 11-May-25
Note on FY412: Activity Name: OFCI- Receive Elec. Performance Monitoring Syst. (EPMS) (Schneider) (SOW Del Date- 8/31/24) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on LS412: Activity Name: OFCI- LV Switchgear (Eaton) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 30-Mar-25 End Date: 03-Apr-25
Note on LX412: Activity Name: OFCI- Main LV Switch Board (MSB) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 04-Apr-25 End Date: 04-Apr-25
Note on MN412: Activity Name: OFCI- Elec. Performance Monitoring Syst. (EPMS) (Schneider) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 20-Apr-25 End Date: 20-Apr-25
Note on NA412: Activity Name: OFCI- Medium Voltage Switchgear (MVS) (JDC Power Sys) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 03-May-25 End Date: 03-May-25
Note on NI412: Activity Name: OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 11-May-25 End Date: 15-May-25
Note on FY413: Activity Name: OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 7/3/24) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on LS413: Activity Name: OFCI- Main LV Switch Board (MSB) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 30-Mar-25 End Date: 04-Apr-25
Note on MN413: Activity Name: OFCI- Elec. Performance Monitoring Syst. (EPMS) (Schneider) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 20-Apr-25 End Date: 20-Apr-25
Note on MW413: Activity Name: OFCI- Medium Voltage Switchgear (MVS) (JDC Power Sys) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 29-Apr-25 End Date: 03-May-25
Note on FY414: Activity Name: OFCI- Receive Packaged Diesel Generator Set (GPC) (CAT Holt) (SOW Del Date- 6/26/24) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on LS414: Activity Name: OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date 3/30/2025) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on LX414: Activity Name: OFCI- Mech Power Distribution Panels (ADP) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 04-Apr-25 End Date: 04-Apr-25
Note on NA414: Activity Name: OFCI- Pad Mounted Transformers (XMF) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 03-May-25 End Date: 03-May-25
Note on FY415: Activity Name: OFCI- Receive Pad Mounted Transformers (XMF) (Del Date 10/30/2024) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on LS415: Activity Name: OFCI- Receive LV Switchgear (Eaton) (SOW Del Date- 3/30/25) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on MW415: Activity Name: OFCI- Pad Mounted Transformers (XMF) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 29-Apr-25 End Date: 03-May-25
Note on FY416: Activity Name: OFCI- Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 9/30/24) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on LS416: Activity Name: OFCI- Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on NA416: Activity Name: OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 03-May-25 End Date: 07-May-25
Note on FY417: Activity Name: OFCI- Receive Utility Pad Mount Switchgear (UPM) (Del Date 10/30/2024) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on LS417: Activity Name: OFCI- Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on NA417: Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 03-May-25 End Date: 03-May-25
Note on LS418: Activity Name: OFCI- Static UPS System W/Batt (UPS) (Eaton) Delivered Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on MW418: Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 29-Apr-25 End Date: 03-May-25
Note on LO419: Activity Name: OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on C423: Activity Name: RFP- Microsoft Awards CHI11 Phase: RFP / PSR Location: Milestone Trade: Milestone Start Date: 06-May-24 End Date: 10-May-24
Note on AH423: Activity Name: RFP- PSR Executed (Early Works) Phase: RFP / PSR Location: Milestone Trade: Milestone Start Date: 06-Jun-24 End Date: 06-Jun-24
Note on CD423: Activity Name: Site Mobilization Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Start Date: 24-Jul-24 End Date: 24-Jul-24
Note on CE423: Activity Name: Set-Up Trailers & Install Temp Utilities Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on DD423: Activity Name: Fine Grading Building Pad Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on ET423: Activity Name: RFP- PSR Executed (Full GMP) Phase: RFP / PSR Location: Milestone Trade: Milestone Start Date: 30-Sep-24 End Date: 30-Sep-24
Note on EM430: Activity Name: Install Deep Telecom Phase: Site Utilities Location: Overall Trade: Framing Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on NC430: Activity Name: Permanent Power (Need by Date) Phase: Site Utilities Location: Overall Trade: Milestone Start Date: 05-May-25 End Date: 05-May-25
Note on EX431: Activity Name: Install MV Ductbanks Phase: Site Utilities Location: Overall Trade: Framing Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on GC432: Activity Name: Install Sanitary Lines Phase: Site Utilities Location: Overall Trade: Framing Start Date: 04-Nov-24 End Date: 03-Dec-24
Note on GH433: Activity Name: Install Storm Lines Phase: Site Utilities Location: Overall Trade: Framing Start Date: 09-Nov-24 End Date: 17-Dec-24
Note on GN434: Activity Name: Install Water Line Phase: Site Utilities Location: Overall Trade: Electrical Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on ET436: Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Phase: Site Utilities Location: Under Building Pad Trade: Electrical Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on GF436: Activity Name: Backfill after UG work (MV / Telecom) Phase: Site Utilities Location: Under Building Pad Trade: Earthwork Start Date: 07-Nov-24 End Date: 08-Nov-24
Note on EH437: Activity Name: Install UG Telecom (under Building Pad) Phase: Site Utilities Location: Under Building Pad Trade: Electrical Start Date: 18-Sep-24 End Date: 04-Oct-24

## CFA - Legends
BIM |  | CFCI Procurement |  | Commissioning |  | Core & Shell |  | Early Awards |  | Electrical Yard |  | Fitout |  | MSFT OFCI ROJ Dates |  | Milestones |  | RFP / PSR |  | Site Prep/ Mobilization |  | Site Utilities
[18 empty] | ML21 | RFP- Microsoft Awards CHI11 | ML21 | Fine Grading Building Pad
BIM |  | CFCI |  | Cx |  | Concrete |  | Milestone |  | Electrical |  | BAS |  | ROJ |  | Milestone | [5 empty] | Earthwork
BIM | BIM- Above ground BIM Co-ordination | CFCI | CFCI- Cable Bus Fabrication/ Lead Time | Cx1 | FTE Energizations [480v] | SOG | Prep / Place SOG | ML21 | PROCUREMENT- ARL & Subcontractor Awards | E28 | Install UMSs | GBA | Install BAS Equipments | ROJ1 | OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/04/24) | ML0 | Cx L5 IST Complete (White Tag) |  |  |  |  | EW1 | Backfill after UG work (MV / Telecom)
|  |  |  | Cx3 | Startups |  |  |  |  | E30 | Install UPMs | GBB | Pull & Terminate BAS Equipments | ROJ10 | OFCI- Air Handling Units (AHU) (Stulz) Shipping/ ROJ | ML1 | Beneficial Use
[6 empty] | Framing |  |  |  | E34 | Install Generators |  |  | ROJ100 | OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 11/28/24) | ML1 | Admin & COLO3-5 Fitout Complete |  |  |  |  | Electrical
|  |  |  | Electrical |  | J32 | Install Exterior Wall Panels |  |  | E35 | MV Cable Pulling & Terminating(To Junction Box) to Cell 1 | Clayco |  | ROJ101 | OFCI- Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 2/23/24) | ML10 | Beneficial Use - Middle of Row (MOR) Cabinets |  |  |  |  | E38 | Install Water Line
|  |  |  | E39 | Loadbanking | J34 | Install Louvers & Dampers |  |  | E39 | Install XFMs | CL | Remaining Area Punchlist | ROJ102 | OFCI- Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 4/23/24) | ML11 | Beneficial Use - Radio Over Internet Protocol (RoIP) |  |  |  |  | EE36 | Install UG Electrical / UPM Crossing (under Building Pad)
|  |  |  | EE33 | Control Power Checks | J35 | Install Misc. Metals (Trims, Gutters, Catwalks) |  |  | EE29 | Beneficial Use Rooms |  |  | ROJ103 | OFCI- Receive Busway / Busplugs (Starline Holding) (Del Date- 1/25/24) | ML12 | Beneficial Use - Secure & High Value Storage Rooms |  |  |  |  | EE37 | Install UG Telecom (under Building Pad)
|  |  |  | EE34 | EPMS Point to Point Checks | J38 | Install Primary Steel |  |  | EE30 | Build Equipment Pads for Generators | Cx |  | ROJ104 | OFCI- Receive Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) (SOW Del Date- 6/30/24) | ML13 | Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets
[6 empty] | J40 | Install Roof Panels |  |  | EE31 | Build Equipment Pads for UMSs | Cx2 | General Cleaning | ROJ105 | OFCI- Receive Elec. Performance Monitoring Syst. (EPMS) (Schneider) (SOW Del Date- 8/31/24) | ML14 | Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets |  |  |  |  | Framing
|  |  |  | Microsoft | [5 empty] | EE61 | Terminate MV Gear - Cell 1 |  |  | ROJ106 | OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 5/17/24) | ML15 | Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets |  |  |  |  | J22 | Install Deep Telecom
|  |  |  | 4&5 | 4Cx- Testing <MSFT Duration> | Plumbing | [5 empty] | Electrical |  | ROJ107 | OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 6/18/24) | ML16 | Beneficial Use - Security Equipment Room (SER) |  |  |  |  | J36 | Install MV Ductbanks
[6 empty] | GPC | UG MEP Work (Plumbing) |  |  |  |  | E39 | Pull & Terminate BAS Equipments | ROJ108 | OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 7/3/24) | ML17 | Beneficial Use - Security Low Voltage (SLV) System |  |  |  |  | J41 | Install Sanitary Lines
|  |  |  | TBD |  | GPD | Weather Days |  |  |  |  | EE1 | Overhead R/I - Electrical | ROJ109 | OFCI- Receive LV Switchgear (Eaton) (SOW Del Date- 2/28/25) | ML18 | Beneficial Use - Security Low Voltage (SLV) Systems |  |  |  |  | J43 | Install Storm Lines
|  |  |  | L2 | 2Cx- Yellow Tags | [6 empty] | EE10 | Install Busways on HAC Arms | ROJ11 | OFCI- Air Handling Units (AHU) (Stulz) Shipping/ROJ | ML19 | Beneficial Use (IDF#1,#2,#3 & #4)
|  |  |  | L3 | 3Cx- EPMS Point to Point Checks | [6 empty] | EE17 | Pull Feeders from PDUs to Busways | ROJ110 | OFCI- Receive LV Switchgear (Eaton) (SOW Del Date- 3/30/25) | ML2 | Beneficial Use |  |  |  |  | Milestone
[12 empty] | EE19 | Terminate PDUs | ROJ111 | OFCI- Receive LV Switchgear (LVS) (Eaton) (SOW Del Date- 2/28/25) | ML20 | Beneficial Use (IDF#1,#2,#3 & #4) |  |  |  |  | MLPP | Permanent Power (Need by Date)
[12 empty] | EE2 | In-Wall R/I | ROJ112 | OFCI- Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) | ML21 | Beneficial Use- Facilities Operations Center (FOC)
[12 empty] | EE24 | Pull Branches From Admin | ROJ113 | OFCI- Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) | ML3 | Beneficial Use
[12 empty] | EE28 | Cable Tray / Ceiling Steel Height | ROJ114 | OFCI- Receive Main LV Switch Board (MSB) (SOW Del Date- 3/8/2025) | ML4 | Beneficial Use - All Facility & Network Telecom Access/ Devices etc.
[12 empty] | EE29 | Pull Feeders to Admin | ROJ115 | OFCI- Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) | ML5 | Beneficial Use - Distrbuted Antenna System (DAS)
[12 empty] | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | ROJ116 | OFCI- Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) | ML6 | Beneficial Use - Distributed Antenna System (DAS)
[12 empty] | EE35 | Install Cable Trays / Pathways | ROJ117 | OFCI- Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 7/30/24) | ML7 | Beneficial Use - Distributed Antenna System (DAS)
[12 empty] | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | ROJ118 | OFCI- Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 8/30/24) | ML8 | Beneficial Use - Facility Cable Room (FCR)
[12 empty] | EE43 | Pull Cables | ROJ119 | OFCI- Receive Medium Voltage Switchgear (MVS) (JDC Power Sys) (SOW Del Date- 10/30/24) | ML9 | Beneficial Use - Meet Me Room or Entry Rooms (MMR/ER)
[12 empty] | EE44 | Pull Copper for BAS VLAN | ROJ12 | OFCI- Auto Transfer Control Panel (TCP) Delivered
[12 empty] | EE45 | Pull Copper for EPMS VLAN | ROJ120 | OFCI- Receive Packaged Diesel Generator Set (CAT Holt) (SOW Del Date- 5/14/24)
[12 empty] | EE46 | Pull Copper for Tahuya VLAN | ROJ121 | OFCI- Receive Packaged Diesel Generator Set (GEN) (CAT Holt) (SOW Del Date- 6/4/24)
[12 empty] | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | ROJ122 | OFCI- Receive Packaged Diesel Generator Set (GPC) (CAT Holt) (SOW Del Date- 6/26/24)
[12 empty] | EE48 | Pull Fiber For BAS VLAN | ROJ123 | OFCI- Receive Pad Mounted Transformers (XFM-TX) (Del Date- 7/30/2024)
[12 empty] | EE49 | Pull Fiber For CEI Network | ROJ124 | OFCI- Receive Pad Mounted Transformers (XMF) (Del Date 10/30/2024)
[12 empty] | EE50 | Pull Fiber For EPMS VLAN | ROJ125 | OFCI- Receive PEMB Procurement (1st Del) (Nucor) (SOW Del Date-10/3/24)
[12 empty] | EE51 | Pull Fiber For Tahuya VLAN | ROJ126 | OFCI- Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 4/30/24)
[12 empty] | EE52 | Pull Fiber/Copper For CORPNET Network | ROJ127 | OFCI- Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 9/30/24)
[12 empty] | EE53 | Set Electrical Equipment in Admin | ROJ128 | OFCI- Receive Utility Pad Mount Switchgear (Del Date- 7/30/2024)
[12 empty] | EE54 | Set ER-1 Equipment | ROJ129 | OFCI- Receive Utility Pad Mount Switchgear (UPM) (Del Date 10/30/2024)
[12 empty] | EE55 | Set ER-2 Equipment | ROJ13 | OFCI- Auto Transfer Control Panel (TCP) Delivered
[12 empty] | EE56 | Set FCR Equipment | ROJ130 | OFCI- Receive Utility Pad Mount Switchgear (UPM) (Del Date 8/30/2024)
[12 empty] | EE57 | Set Mechanical Equipments | ROJ131 | OFCI- Received SUB Warehouse 11/23/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 11/11/23)
[12 empty] | EE58 | Terminate Electrical / Mechanical Equipment | ROJ132 | OFCI- Received SUB Warehouse 12/28/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 12/11/23)
[12 empty] | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | ROJ133 | OFCI- Received SUB Warehouse 9/28/2023 UPS System w/ Battery (UPS) (Eaton) (SOW Del Date- 8/13/23)
[12 empty] | EE60 | Terminate Mechanical Equipments | ROJ134 | OFCI- Reveive Pad Mounted Transformers (XMF) (Del Date 8/30/2024)
[12 empty] | EE7 | Set PDUs | ROJ135 | OFCI- Reveive Power Distribution Units (PDU) (ABB) (SOW Del Date- 7/12/24)
[12 empty] | EEA | Light Fixtures Installation | ROJ136 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Delivered
[14 empty] | ROJ137 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Delivered
[12 empty] | Fire Protection |  | ROJ138 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ
[12 empty] | GSA | Complete Pipe/ Valves | ROJ139 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ
[12 empty] | GSB | Fire Protection OH R/I | ROJ14 | OFCI- Auto Transfer Control Panel (TCP) Delivered
[12 empty] | GSC | Overhead R/I - Fire Alarm | ROJ140 | OFCI- UPS System w/ Battery (UPS) (Eaton) Delivered
[12 empty] | GSD | Overhead R/I - Fire Protection | ROJ141 | OFCI- UPS System w/ Battery (UPS) (Eaton) Shipping/ ROJ
[14 empty] | ROJ142 | OFCI- Utility Pad Mount Switchgear (UPM) Delivered
[12 empty] | Framing |  | ROJ143 | OFCI- Utility Pad Mount Switchgear (UPM) Delivered
[12 empty] | J1 | Layout Framing | ROJ144 | OFCI- Utility Pad Mount Switchgear (UPM) Delivered
[12 empty] | J11 | Framing | ROJ145 | OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ ROJ
[12 empty] | J13 | Finsh Drywall and Wall Protection | ROJ146 | OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ
[12 empty] | J16 | Install Ceiling Grid | ROJ147 | OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ
[12 empty] | J17 | Ceiling Grid & Tile | ROJ15 | OFCI- Auto Transfer Control Panel (TCP) Shipping/ ROJ
[12 empty] | J20 | Install Ceiling Grid + Device Tiles | ROJ16 | OFCI- Auto Transfer Control Panel (TCP) Shipping/ROJ
[12 empty] | J21 | Install Conduits PDU to Cable Trays | ROJ17 | OFCI- Auto Transfer Control Panel (TCP) Shipping/ROJ
[12 empty] | J23 | Install Device Tiles | ROJ18 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered
[12 empty] | J24 | Install Doors | ROJ19 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered
[12 empty] | J3 | Install Framing | ROJ2 | OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/9/24)
[12 empty] | J30 | Install downcomers | ROJ20 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered
[12 empty] | J31 | Install Duct Work | ROJ21 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ ROJ
[12 empty] | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | ROJ22 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ
[12 empty] | J37 | Install Perimeter Cable Trays | ROJ23 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ
[12 empty] | J39 | Install Raceway | ROJ24 | OFCI- Auxillary (Mech) Power Distribution Panels (ADP) Delivered
[12 empty] | J4 | Install Drywall (One Side - Facing DH) | ROJ25 | OFCI- Auxillary (Mech) Power Distribution Panels (ADP) Shipping/ ROJ
[12 empty] | J42 | Install Secondary Steel | ROJ26 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Delivered
[12 empty] | J44 | Overhead R/I - Mechanical | ROJ27 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Delivered
[12 empty] | J5 | Drop Cable Tray [Hanging Rods] | ROJ28 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ
[12 empty] | J6 | Install Screen Mesh + Caulking | ROJ29 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ
[12 empty] | JA | Secondary / Ceiling Steel | ROJ3 | OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date- 3/8/2025)
[12 empty] | JC | Top Out Drywall - Ceiling Steel Height | ROJ30 | OFCI- Building Automation System (BAS) (ALC) Delivered
[14 empty] | ROJ31 | OFCI- Building Automation System (BAS) (ALC) Shipping/ ROJ
[12 empty] | HAC's |  | ROJ32 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Delivered
[12 empty] | S1 | Assemble HACs [Qty - 5] | ROJ33 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Delivered
[12 empty] | S2 | Detail HACs | ROJ34 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ
[12 empty] | S3 | Set SER Room Equipment | ROJ35 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ
[14 empty] | ROJ36 | OFCI- Busway / Busplugs (Starline Holding) Delivered
[12 empty] | MEP |  | ROJ37 | OFCI- Busway / Busplugs (Starline Holding) Shipping/ ROJ
[12 empty] | MEP1 | MEP Rough-In & OH | ROJ38 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Delivered
[14 empty] | ROJ39 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Shipping/ROJ
[12 empty] | Milestone |  | ROJ4 | OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 4/30/24)
[12 empty] | ML21 | Rough-in | ROJ40 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (Schneider) Delivered
[14 empty] | ROJ41 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (Schneider) Shipping/ROJ
[12 empty] | Paiting |  | ROJ42 | OFCI- Elec. Performance Monitoring System (EPMS) (Schneider) Delivered
[12 empty] | T1 | Paint Dry-Wall | ROJ43 | OFCI- Elec. Performance Monitoring System (EPMS) (Schneider) Shipping/ ROJ
[12 empty] | T2 | Paint | ROJ44 | OFCI- HAC/Racking (Tate Access) Delivered
[12 empty] | T3 | Paint Secondary Steel | ROJ45 | OFCI- HAC/Racking (Tate Access) Delivered
[14 empty] | ROJ46 | OFCI- HAC/Racking (Tate Access) Delivered
[12 empty] | Plumbing |  | ROJ47 | OFCI- HAC/Racking (Tate Access) Shipping/ ROJ
[12 empty] | GPA | Overhead R/I - Plumbing | ROJ48 | OFCI- HAC/Racking (Tate Access) Shipping/ROJ
[12 empty] | GPB | Plumbing | ROJ49 | OFCI- HAC/Racking (Tate Access) Shipping/ROJ
[14 empty] | ROJ5 | OFCI- Receive Auxillary (Mech) Power Distribution Panels (ADP) (Del Date- 3/8/2025)
[12 empty] | Punchlist |  | ROJ50 | OFCI- LV Switchgear (Eaton) Delivered
[12 empty] | PU1 | Beneficial Rooms PunchList | ROJ51 | OFCI- LV Switchgear (Eaton) Delivered
[14 empty] | ROJ52 | OFCI- LV Switchgear (Eaton) Shipping/ROJ
[14 empty] | ROJ53 | OFCI- LV Switchgear (Eaton) Shipping/ROJ
[14 empty] | ROJ54 | OFCI- LV Switchgear (LVS) (Eaton) Delivered
[14 empty] | ROJ55 | OFCI- LV Switchgear (LVS) (Eaton) Shipping/ ROJ
[14 empty] | ROJ56 | OFCI- Main LV Switch Board (MSB) Delivered
[14 empty] | ROJ57 | OFCI- Main LV Switch Board (MSB) Delivered
[14 empty] | ROJ58 | OFCI- Main LV Switch Board (MSB) Delivered
[14 empty] | ROJ59 | OFCI- Main LV Switch Board (MSB) Shipping/ ROJ
[14 empty] | ROJ6 | OFCI- Air Handling Units (AHU) (Stulz) Delivered
[14 empty] | ROJ60 | OFCI- Main LV Switch Board (MSB) Shipping/ROJ
[14 empty] | ROJ61 | OFCI- Main LV Switch Board (MSB) Shipping/ROJ
[14 empty] | ROJ62 | OFCI- Mech Power Distribution Panels (ADP) Delivered
[14 empty] | ROJ63 | OFCI- Mech Power Distribution Panels (ADP) Delivered
[14 empty] | ROJ64 | OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ
[14 empty] | ROJ65 | OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ
[14 empty] | ROJ66 | OFCI- Medium Voltage Switchgear (JDC Power Sys) Delivered
[14 empty] | ROJ67 | OFCI- Medium Voltage Switchgear (JDC Power Sys) Shipping/ROJ
[14 empty] | ROJ68 | OFCI- Medium Voltage Switchgear (MVS) (JD Power Sys) Delivered
[14 empty] | ROJ69 | OFCI- Medium Voltage Switchgear (MVS) (JD Power Sys) Shipping/ ROJ
[14 empty] | ROJ7 | OFCI- Air Handling Units (AHU) (Stulz) Delivered
[14 empty] | ROJ70 | OFCI- Medium Voltage Switchgear (MVS) (JDC Power Sys) Delivered
[14 empty] | ROJ71 | OFCI- Medium Voltage Switchgear (MVS) (JDC Power Sys) Shipping/ROJ
[14 empty] | ROJ72 | OFCI- Packaged Diesel Generator Set (CAT Holt) Delivered
[14 empty] | ROJ73 | OFCI- Packaged Diesel Generator Set (CAT Holt) Shipping/ ROJ
[14 empty] | ROJ74 | OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Delivered
[14 empty] | ROJ75 | OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ
[14 empty] | ROJ76 | OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Delivered
[14 empty] | ROJ77 | OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ
[14 empty] | ROJ78 | OFCI- Pad Mounted Transformers (XFM-TX) Delivered
[14 empty] | ROJ79 | OFCI- Pad Mounted Transformers (XFM-TX) Shipping/ ROJ
[14 empty] | ROJ8 | OFCI- Air Handling Units (AHU) (Stulz) Delivered
[14 empty] | ROJ80 | OFCI- Pad Mounted Transformers (XMF) Delivered
[14 empty] | ROJ81 | OFCI- Pad Mounted Transformers (XMF) Delivered
[14 empty] | ROJ82 | OFCI- Pad Mounted Transformers (XMF) Shipping/ROJ
[14 empty] | ROJ83 | OFCI- Pad Mounted Transformers (XMF) Shipping/ROJ
[14 empty] | ROJ84 | OFCI- PEMB Procurement (1st Del) (Nucor) Delivered
[14 empty] | ROJ85 | OFCI- PEMB Procurement (1st Del) (Nucor) Shipping/ ROJ
[14 empty] | ROJ86 | OFCI- Power Distribution Units (PDU) (ABB) Delivered
[14 empty] | ROJ87 | OFCI- Power Distribution Units (PDU) (ABB) Delivered
[14 empty] | ROJ88 | OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ
[14 empty] | ROJ89 | OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ
[14 empty] | ROJ9 | OFCI- Air Handling Units (AHU) (Stulz) Shipped/ROJ
[14 empty] | ROJ90 | OFCI- Power Distribution Units (PDU) Delivered
[14 empty] | ROJ91 | OFCI- Power Distribution Units (PDU) Shipping/ ROJ
[14 empty] | ROJ92 | OFCI- Receive Elec. Performance Monitoring System (EPMS) (Schneider) (SOW Del Date- 4/30/24)
[14 empty] | ROJ93 | OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/16/24)
[14 empty] | ROJ94 | OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date 3/30/2025)
[14 empty] | ROJ95 | OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date-3/30/2025)
[14 empty] | ROJ96 | OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 6/30/24)
[14 empty] | ROJ97 | OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 8/31/24)
[14 empty] | ROJ98 | OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 1/28/25)
[14 empty] | ROJ99 | OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 12/29/24)