## Sheet1
Phase | Location | Trade | Color | Act Code | Act Name | Start | Finish
Framing | 1st Floor | American Contractors | #CBF9F0 | AF | Frame | 2024-12-30 09:00 | 2025-01-10 17:00
Framing | 2nd Floor | American Contractors | #CBF9F0 | AT | Trusses | 2025-01-13 09:00 | 2025-01-22 17:00
Framing | 2nd Floor | American Contractors | #CBF9F0 | AD | Deck | 2025-01-22 09:00 | 2025-01-28 17:00
Framing | 2nd Floor | American Contractors | #CBF9F0 | AF | Frame | 2025-01-29 09:00 | 2025-02-11 17:00
Framing | 3rd Floor | American Contractors | #CBF9F0 | AT | Trusses | 2025-02-05 09:00 | 2025-02-14 17:00
Framing | 3rd Floor | American Contractors | #CBF9F0 | AD | Deck | 2025-02-14 09:00 | 2025-02-20 17:00
Framing | Attic | American Contractors | #CBF9F0 | AT | Trusses | 2024-12-04 09:00 | 2024-12-06 17:00
Framing | Attic | American Contractors | #CBF9F0 | AD | Deck | 2024-12-09 09:00 | 2024-12-10 17:00
Framing | Attic | American Contractors | #CBF9F0 | AC | Frame Corridor | 2024-12-11 09:00 | 2024-12-17 17:00
Framing | Roof | American Contractors | #CBF9F0 | AT | Trusses | 2024-12-18 09:00 | 2025-01-02 17:00
Framing | Roof | American Contractors | #CBF9F0 | AS | Sheath | 2025-01-01 09:00 | 2025-01-07 17:00
Framing | Framing | American Contractors | #CBF9F0 | AC | Frame Elevator, Trash Chute and Stair Tower Roofs | 2025-01-08 09:00 | 2025-01-21 17:00
Framing | Roof | American Contractors | #CBF9F0 | AR | Dry-In | 2025-01-08 09:00 | 2025-01-28 17:00
Fenstrations and Skin | 1st Floor | 84 Lumber | #9BC2E7 | 8S | Sheathing & Windows | 2025-02-21 09:00 | 2025-04-10 17:00
Fenstrations and Skin | 2nd Floor | 84 Lumber | #9BC2E7 | 8S | Sheathing & Windows | 2025-02-21 09:00 | 2025-04-10 17:00
Fenstrations and Skin | 3rd Floor | 84 Lumber | #9BC2E7 | 8S | Sheathing & Windows | 2025-02-21 09:00 | 2025-04-10 17:00
Fenstrations and Skin | 1st Floor | Solid Construction | #FFC8AD | DS | Siding - All Elevations | 2025-05-08 09:00 | 2025-06-18 17:00
Fenstrations and Skin | 2nd Floor | Solid Construction | #FFC8AD | DS | Siding - All Elevations | 2025-05-08 09:00 | 2025-06-18 17:00
Fenstrations and Skin | 3rd Floor | Solid Construction | #FFC8AD | DS | Siding - All Elevations | 2025-06-19 09:00 | 2025-07-09 17:00
Fenstrations and Skin | Atic? | Green Air Mechanical | #9F9D19 | GG | Gutter & Vents | 2025-07-10 09:00 | 2025-07-23 17:00
Fenstrations and Skin | 1st Floor | Solid Construction | #FFC8AD | DG | Soffit Siding | 2025-07-10 09:00 | 2025-07-16 17:00
Fenstrations and Skin | 1st Floor | Morris Steel | #C6C8D1 | MF | Storefront | 2025-07-17 09:00 | 2025-07-23 17:00
Fenstrations and Skin | 1st Floor? | Morris Steel | #C6C8D1 | MC | Canopy | 2025-07-24 09:00 | 2025-07-30 17:00
Masonry Facades | North | Brick Solutions | #019EFF | ME | Masonry Elevation | 2025-03-07 09:00 | 2025-03-20 17:00
Masonry Facades | East | Brick Solutions | #019EFF | ME | Masonry Elevation | 2025-03-21 09:00 | 2025-04-03 17:00
Masonry Facades | South A | Brick Solutions | #019EFF | ME | Masonry Elevation | 2025-03-21 09:00 | 2025-03-25 17:00
Masonry Facades | West Courtyard | Brick Solutions | #019EFF | ME | Masonry Elevation | 2025-04-04 09:00 | 2025-04-15 17:00
Masonry Facades | North Courtyard | Brick Solutions | #019EFF | ME | Masonry Elevation | 2025-04-16 09:00 | 2025-04-25 17:00
Masonry Facades | East Courtyard | Brick Solutions | #019EFF | ME | Masonry Elevation | 2025-04-28 09:00 | 2025-05-07 17:00
Masonry Facades | South B | Brick Solutions | #019EFF | ME | Masonry Elevation | 2025-05-08 09:00 | 2025-05-12 17:00
Masonry Facades | West | Brick Solutions | #019EFF | ME | Masonry Elevation | 2025-05-13 09:00 | 2025-05-26 17:00
Vertical | MEP R/Is | Davishar | #C6E0B4 | PW | Set Water Service & Equipment | 2025-01-29 09:00 | 2025-02-04 17:00
Vertical | MEP R/Is | Otis | #B78593 | OM | Set Elevator Machines 1 & 2 (Protect) | 2024-07-04 09:00 | 2024-07-05 17:00
Vertical | MEP R/Is | Current Electric | #FFF3B2 | EG | Set Electrical Gear | 2025-02-05 09:00 | 2025-02-18 17:00
Vertical | MEP R/Is | Current Electric | #FFF3B2 | EF | Electrical Feeders | 2025-02-19 09:00 | 2025-03-04 17:00
Vertical | MEP R/Is | Green Air Mechanical | #9F9D19 | GD | HVAC Duct Risers | 2025-01-29 09:00 | 2025-02-18 17:00
Vertical | MEP R/Is | Morris Steel | #C6C8D1 | MS | Set Trash Chute | 2025-01-29 09:00 | 2025-02-04 17:00
Vertical | MEP R/Is | Ranger | #CD0000 | SR | Sprinkler Risers | 2025-02-05 09:00 | 2025-02-25 17:00
Vertical | MEP R/Is | Davishar | #C6E0B4 | PS | Plumbing Stacks & Roof Vents | 2025-02-19 09:00 | 2025-03-11 17:00
Vertical | MEP R/Is | Breeden | #346093 | WI | Shaft Wall Inspections | 2025-02-19 09:00 | 2025-03-04 17:00
Vertical | MEP R/Is | Solid Construction | #FFC8AD | DR | Set Roof Top Equipment | 2025-03-12 09:00 | 2025-03-18 17:00
Vertical | Transportation | Otis | #B78593 | O2 | Elevator 1 | 2025-03-05 09:00 | 2025-04-08 17:00
Vertical | Transportation | Otis | #B78593 | O1 | Elevator 2 | 2025-04-09 09:00 | 2025-05-13 17:00
Interiors | 1st Floor | Quality Building Products | #CD8105 | QP | Pre-insul & Gyp for Plumbing & Ins | 2025-02-19 09:00 | 2025-02-25 17:00
Interiors | 1st Floor | Green Air Mechanical | #9F9D19 | GC | Above Ceiling HVAC R/I | 2025-02-26 09:00 | 2025-03-04 17:00
Interiors | 1st Floor | Davishar | #C6E0B4 | PU | Plumbing Unit R/I Domestic, Sanitary, Set Tubs | 2025-03-05 09:00 | 2025-03-11 17:00
Interiors | 1st Floor | Ranger | #CD0000 | SS | OH Sprinkler R/I and Hydro Ins | 2025-03-12 09:00 | 2025-03-18 17:00
Interiors | 1st Floor | Current Electric | #FFF3B2 | EW | Electrical Wall R/I | 2025-03-19 09:00 | 2025-03-25 17:00
Interiors | 1st Floor | Current Electric | #FFF3B2 | EL | Electrical Lighting OH R/I | 2025-03-19 09:00 | 2025-03-25 17:00
Interiors | 1st Floor | Current Electric | #FFF3B2 | ER | Low Voltage Wall R/I (Tele/Cable/IT) | 2025-03-19 09:00 | 2025-03-25 17:00
Interiors | 1st Floor | Breeden | #346093 | CI | R/I Trade Close-in Inspections | 2025-03-26 09:00 | 2025-03-27 17:00
Exteriors | 1st Floor | Quality Building Products | #CD8105 | QE | Insulate Exterior Walls | 2025-03-28 09:00 | 2025-03-31 17:00
Interiors | 1st Floor | Quality Building Products | #CD8105 | QC | Insulate Ceilings | 2025-03-31 09:00 | 2025-04-02 17:00
Interiors | 1st Floor | Breeden | #346093 | II | Insulation Inspection | 2025-04-03 09:00 | 2025-04-03 17:00
Interiors | 1st Floor | American Contractors | #CBF9F0 | AP | Framing & R/I Punchlist - Set Unit Entry FMs | 2025-04-04 09:00 | 2025-04-09 17:00
Interiors | 1st Floor | Blue Sky | #8EA9DB | BS | Stock Drywall | 2025-04-04 09:00 | 2025-04-08 17:00
Interiors | 1st Floor | Blue Sky | #8EA9DB | BH | Hang Drywall | 2025-04-09 09:00 | 2025-04-15 17:00
Interiors | 1st Floor | ECPF | #F659A9 | GY | Gypcrete | 2025-04-16 09:00 | 2025-04-17 17:00
Interiors | 1st Floor | Blue Sky | #8EA9DB | BP | Prime Paint | 2025-04-18 09:00 | 2025-04-23 17:00
Interiors | 1st Floor | Blue Sky | #8EA9DB | BU | Point Up Drywall | 2025-04-22 09:00 | 2025-04-24 17:00
Interiors | 1st Floor | Green Air Mechanical | #9F9D19 | GA | Set AHU | 2025-04-25 09:00 | 2025-04-25 17:00
Interiors | 1st Floor | Davishar | #C6E0B4 | PH | Set HWH and Plumb (Set Submeter) | 2025-04-28 09:00 | 2025-04-28 17:00
Interiors | 1st Floor | Current Electric | #FFF3B2 | EB | Electrical Panel Brkrs and Equipment Terminations | 2025-04-25 09:00 | 2025-04-29 17:00
Interiors | 1st Floor | Current Electric | #FFF3B2 | EP | Low Voltage Panel | 2025-04-25 09:00 | 2025-04-28 17:00
Interiors | 1st Floor | Ranger | #CD0000 | SH | Sprinkler Head Escutheons | 2025-04-25 09:00 | 2025-04-29 17:00
Interiors | 1st Floor | Current Electric | #FFF3B2 | ES | Switch and Plug | 2025-04-30 09:00 | 2025-05-02 17:00
Interiors | 1st Floor | Current Electric | #FFF3B2 | EWT | Wire Thermostats | 2025-04-30 09:00 | 2025-05-02 17:00
Interiors | 1st Floor | Green Air Mechanical | #9F9D19 | GS | Start-up HVAC | 2025-05-05 09:00 | 2025-05-06 17:00
Interiors | 1st Floor | Heritage Woodworks | #941651 | HV | Set Cabinets & Vanities | 2025-05-07 09:00 | 2025-05-13 17:00
Interiors | 1st Floor | American Contractors | #CBF9F0 | AH | Install Pre-hung Doors | 2025-05-14 09:00 | 2025-05-15 17:00
Interiors | 1st Floor | American Contractors | #CBF9F0 | AR | Running Trim and Stools | 2025-05-16 09:00 | 2025-05-20 17:00
Interiors | 1st Floor | Heritage Woodworks | #941651 | HC | Set Countertops | 2025-05-21 09:00 | 2025-05-27 17:00
Interiors | 1st Floor | Walkers | #6870DE | WC | Ceramic Tile (Floors & Walls) | 2025-05-21 09:00 | 2025-05-27 17:00
Interiors | 1st Floor | Walkers | #6870DE | WB | Ceramic Backsplash | 2025-05-28 09:00 | 2025-06-02 17:00
Interiors | 1st Floor | Walkers | #6870DE | WL | LVT Flooring | 2025-06-03 09:00 | 2025-06-06 17:00
Interiors | 1st Floor | Current Electric | #FFF3B2 | ET | Electrical Trim (Plates & Lights) | 2025-06-09 09:00 | 2025-06-13 17:00
Interiors | 1st Floor | Current Electric | #FFF3B2 | EV | Trim Low Voltage | 2025-06-09 09:00 | 2025-06-11 17:00
Interiors | 1st Floor | Green Air Mechanical | #9F9D19 | GT | G/R/Ds HVAC Trim | 2025-06-16 09:00 | 2025-06-18 17:00
Interiors | 1st Floor | Davishar | #C6E0B4 | PT | Trim Plumbing (Disposals/DWs) | 2025-06-16 09:00 | 2025-06-18 17:00
Interiors | 1st Floor | TBD | #404040 | TA | Install Appliances | 2025-06-19 09:00 | 2025-06-23 17:00
Interiors | 1st Floor | American Contractors | #CBF9F0 | AH | Door Hardware | 2025-06-19 09:00 | 2025-06-23 17:00
Interiors | 1st Floor | Blue Sky | #8EA9DB | BF | Final Paint | 2025-06-24 09:00 | 2025-06-30 17:00
Interiors | 1st Floor | Blue Sky | #8EA9DB | BD | Drywall Point Up | 2025-07-01 09:00 | 2025-07-02 17:00
Interiors | 1st Floor | Morris Steel | #C6C8D1 | MM | Mirrors and Toilet Accessories | 2025-07-03 09:00 | 2025-07-04 17:00
Interiors | 1st Floor | American Contractors | #CBF9F0 | AV | Closet Shelving | 2025-07-07 | 2025-10-07
Interiors | 1st Floor | Clean | #B8A6E3 | RC | Rough-Clean | 2025-07-11 09:00 | 2025-07-16 17:00
Interiors | 1st Floor | Walkers | #6870DE | WP | Pad and Carpet (Protect) | 2025-07-17 09:00 | 2025-07-23 17:00
Interiors | 1st Floor | Breeden | #346093 | SI | Trade Final Ins (Sprinkler, Plumbing, HVAC, Electric, LV) | 2025-07-24 09:00 | 2025-07-30 17:00
Interiors | 1st Floor | Blue Sky | #8EA9DB | BT | Paint Touch-up & Caulk | 2025-07-24 09:00 | 2025-07-25 17:00
Interiors | 1st Floor | Breeden | #346093 | CP | Contractor Punchlist | 2025-07-31 09:00 | 2025-08-06 17:00
Interiors | 2nd Floor | Quality Building Products | #CD8105 | QP | Pre-insul & Gyp for Plumbing & Ins | 2025-02-26 09:00 | 2025-03-04 17:00
Interiors | 2nd Floor | Green Air Mechanical | #9F9D19 | GC | Above Ceiling HVAC R/I | 2025-03-05 09:00 | 2025-03-11 17:00
Interiors | 2nd Floor | Davishar | #C6E0B4 | PU | Plumbing Unit R/I Domestic, Sanitary, Set Tubs | 2025-03-12 09:00 | 2025-03-18 17:00
Interiors | 2nd Floor | Ranger | #CD0000 | SS | OH Sprinkler R/I and Hydro Ins | 2025-03-19 09:00 | 2025-03-25 17:00
Interiors | 2nd Floor | Current Electric | #FFF3B2 | EW | Electrical Wall R/I | 2025-03-26 09:00 | 2025-04-01 17:00
Interiors | 2nd Floor | Current Electric | #FFF3B2 | EL | Electrical Lighting OH R/I | 2025-03-26 09:00 | 2025-04-01 17:00
Interiors | 2nd Floor | Current Electric | #FFF3B2 | ER | Low Voltage Wall R/I (Tele/Cable/IT) | 2025-03-26 09:00 | 2025-04-01 17:00
Interiors | 2nd Floor | Breeden | #346093 | CI | R/I Trade Close-in Inspections | 2025-04-02 09:00 | 2025-04-03 17:00
Exteriors | 2nd Floor | Quality Building Products | #CD8105 | QE | Insulate Exterior Walls | 2025-04-04 09:00 | 2025-04-07 17:00
Interiors | 2nd Floor | Quality Building Products | #CD8105 | QC | Insulate Ceilings | 2025-04-07 09:00 | 2025-04-09 17:00
Interiors | 2nd Floor | Breeden | #346093 | II | Insulation Inspection | 2025-04-10 09:00 | 2025-04-10 17:00
Interiors | 2nd Floor | American Contractors | #CBF9F0 | AP | Framing & R/I Punchlist - Set Unit Entry FMs | 2025-04-11 09:00 | 2025-04-16 17:00
Interiors | 2nd Floor | Blue Sky | #8EA9DB | BS | Stock Drywall | 2025-04-11 09:00 | 2025-04-15 17:00
Interiors | 2nd Floor | Blue Sky | #8EA9DB | BH | Hang Drywall | 2025-04-16 09:00 | 2025-04-22 17:00
Interiors | 2nd Floor | ECPF | #F659A9 | GY | Gypcrete | 4/23/2025 | 4/24/2025
Interiors | 2nd Floor | Blue Sky | #8EA9DB | BP | Prime Paint | 2025-04-25 09:00 | 2025-04-30 17:00
Interiors | 2nd Floor | Blue Sky | #8EA9DB | BU | Point Up Drywall | 2025-04-29 09:00 | 2025-05-01 17:00
Interiors | 2nd Floor | Green Air Mechanical | #9F9D19 | GA | Set AHU | 2025-05-02 09:00 | 2025-05-02 17:00
Interiors | 2nd Floor | Davishar | #C6E0B4 | PH | Set HWH and Plumb (Set Submeter) | 2025-05-05 09:00 | 2025-05-05 17:00
Interiors | 2nd Floor | Current Electric | #FFF3B2 | EB | Electrical Panel Brkrs and Equipment Terminations | 2025-05-02 09:00 | 2025-05-06 17:00
Interiors | 2nd Floor | Current Electric | #FFF3B2 | EP | Low Voltage Panel | 2025-05-02 09:00 | 2025-05-05 17:00
Interiors | 2nd Floor | Ranger | #CD0000 | SH | Sprinkler Head Escutheons | 2025-05-02 09:00 | 2025-05-06 17:00
Interiors | 2nd Floor | Current Electric | #FFF3B2 | ES | Switch and Plug | 2025-05-07 09:00 | 2025-05-09 17:00
Interiors | 2nd Floor | Current Electric | #FFF3B2 | EWT | Wire Thermostats | 2025-05-07 09:00 | 2025-05-09 17:00
Interiors | 2nd Floor | Green Air Mechanical | #9F9D19 | GS | Start-up HVAC | 2025-05-12 09:00 | 2025-05-13 17:00
Interiors | 2nd Floor | Heritage Woodworks | #941651 | HV | Set Cabinets & Vanities | 2025-05-14 09:00 | 2025-05-20 17:00
Interiors | 2nd Floor | American Contractors | #CBF9F0 | AH | Install Pre-hung Doors | 2025-05-21 09:00 | 2025-05-22 17:00
Interiors | 2nd Floor | American Contractors | #CBF9F0 | AR | Running Trim and Stools | 2025-05-23 09:00 | 2025-05-27 17:00
Interiors | 2nd Floor | Heritage Woodworks | #941651 | HC | Set Countertops | 2025-05-28 09:00 | 2025-06-03 17:00
Interiors | 2nd Floor | Walkers | #6870DE | WC | Ceramic Tile (Floors & Walls) | 2025-05-28 09:00 | 2025-06-03 17:00
Interiors | 2nd Floor | Walkers | #6870DE | WB | Ceramic Backsplash | 2025-06-04 09:00 | 2025-06-09 17:00
Interiors | 2nd Floor | Walkers | #6870DE | WL | LVT Flooring | 2025-06-10 09:00 | 2025-06-13 17:00
Interiors | 2nd Floor | Current Electric | #FFF3B2 | ET | Electrical Trim (Plates & Lights) | 2025-06-16 09:00 | 2025-06-20 17:00
Interiors | 2nd Floor | Current Electric | #FFF3B2 | EV | Trim Low Voltage | 2025-06-16 09:00 | 2025-06-18 17:00
Interiors | 2nd Floor | Green Air Mechanical | #9F9D19 | GT | G/R/Ds HVAC Trim | 2025-06-23 09:00 | 2025-06-25 17:00
Interiors | 2nd Floor | Davishar | #C6E0B4 | PT | Trim Plumbing (Disposals/DWs) | 2025-06-23 09:00 | 2025-06-25 17:00
Interiors | 2nd Floor | TBD | #404040 | TA | Install Appliances | 2025-06-26 09:00 | 2025-06-30 17:00
Interiors | 2nd Floor | American Contractors | #CBF9F0 | AH | Door Hardware | 2025-06-26 09:00 | 2025-06-30 17:00
Interiors | 2nd Floor | Blue Sky | #8EA9DB | BF | Final Paint | 2025-07-01 09:00 | 2025-07-07 17:00
Interiors | 2nd Floor | Blue Sky | #8EA9DB | BD | Drywall Point Up | 2025-07-08 09:00 | 2025-07-09 17:00
Interiors | 2nd Floor | Morris Steel | #C6C8D1 | MM | Mirrors and Toilet Accessories | 2025-07-10 09:00 | 2025-07-11 17:00
Interiors | 2nd Floor | American Contractors | #CBF9F0 | AV | Closet Shelving | 2025-07-14 09:00 | 2025-07-17 17:00
Interiors | 2nd Floor | Clean | #B8A6E3 | RC | Rough-Clean | 2025-07-18 09:00 | 2025-07-23 17:00
Interiors | 2nd Floor | Walkers | #6870DE | WP | Pad and Carpet (Protect) | 2025-07-24 09:00 | 2025-07-30 17:00
Interiors | 2nd Floor | Breeden | #346093 | SI | Trade Final Ins (Sprinkler, Plumbing, HVAC, Electric, LV) | 2025-07-31 09:00 | 2025-08-06 17:00
Interiors | 2nd Floor | Blue Sky | #8EA9DB | BT | Paint Touch-up & Caulk | 2025-07-31 09:00 | 2025-08-01 17:00
Interiors | 2nd Floor | Breeden | #346093 | CP | Contractor Punchlist | 2025-08-07 09:00 | 2025-08-13 17:00
Interiors | 3rd Floor | Quality Building Products | #CD8105 | QP | Pre-insul & Gyp for Plumbing & Ins | 2025-03-05 09:00 | 2025-03-11 17:00
Interiors | 3rd Floor | Green Air Mechanical | #9F9D19 | GC | Above Ceiling HVAC R/I | 2025-03-12 09:00 | 2025-03-18 17:00
Interiors | 3rd Floor | Davishar | #C6E0B4 | PU | Plumbing Unit R/I Domestic, Sanitary, Set Tubs | 2025-03-19 09:00 | 2025-03-25 17:00
Interiors | 3rd Floor | Ranger | #CD0000 | SS | OH Sprinkler R/I and Hydro Ins | 2025-03-26 09:00 | 2025-04-01 17:00
Interiors | 3rd Floor | Current Electric | #FFF3B2 | EW | Electrical Wall R/I | 2025-04-02 09:00 | 2025-04-08 17:00
Interiors | 3rd Floor | Current Electric | #FFF3B2 | EL | Electrical Lighting OH R/I | 2025-04-02 09:00 | 2025-04-08 17:00
Interiors | 3rd Floor | Current Electric | #FFF3B2 | ER | Low Voltage Wall R/I (Tele/Cable/IT) | 2025-04-02 09:00 | 2025-04-08 17:00
Interiors | 3rd Floor | Breeden | #346093 | CI | R/I Trade Close-in Inspections | 2025-04-09 09:00 | 2025-04-10 17:00
Exteriors | 3rd Floor | Quality Building Products | #CD8105 | QE | Insulate Exterior Walls | 2025-04-11 09:00 | 2025-04-14 17:00
Interiors | 3rd Floor | Quality Building Products | #CD8105 | QC | Insulate Ceilings | 2025-04-14 09:00 | 2025-04-16 17:00
Interiors | 3rd Floor | Breeden | #346093 | II | Insulation Inspection | 2025-04-17 09:00 | 2025-04-17 17:00
Interiors | 3rd Floor | American Contractors | #CBF9F0 | AP | Framing & R/I Punchlist - Set Unit Entry FMs | 2025-04-18 09:00 | 2025-04-23 17:00
Interiors | 3rd Floor | Blue Sky | #8EA9DB | BS | Stock Drywall | 2025-04-18 09:00 | 2025-04-22 17:00
Interiors | 3rd Floor | Blue Sky | #8EA9DB | BH | Hang Drywall | 2025-04-23 09:00 | 2025-04-29 17:00
Interiors | 3rd Floor | ECPF | #F659A9 | GY | Gypcrete | 2025-04-30 09:00 | 2025-05-01 17:00
Interiors | 3rd Floor | Blue Sky | #8EA9DB | BP | Prime Paint | 2025-05-02 09:00 | 2025-05-07 17:00
Interiors | 3rd Floor | Blue Sky | #8EA9DB | BU | Point Up Drywall | 2025-05-06 09:00 | 2025-05-08 17:00
Interiors | 3rd Floor | Green Air Mechanical | #9F9D19 | GA | Set AHU | 2025-05-09 09:00 | 2025-05-09 17:00
Interiors | 3rd Floor | Davishar | #C6E0B4 | PH | Set HWH and Plumb (Set Submeter) | 2025-05-12 09:00 | 2025-05-12 17:00
Interiors | 3rd Floor | Current Electric | #FFF3B2 | EB | Electrical Panel Brkrs and Equipment Terminations | 2025-05-09 09:00 | 2025-05-13 17:00
Interiors | 3rd Floor | Current Electric | #FFF3B2 | EP | Low Voltage Panel | 2025-05-09 09:00 | 2025-05-12 17:00
Interiors | 3rd Floor | Ranger | #CD0000 | SH | Sprinkler Head Escutheons | 2025-05-09 09:00 | 2025-05-13 17:00
Interiors | 3rd Floor | Current Electric | #FFF3B2 | ES | Switch and Plug | 2025-05-14 09:00 | 2025-05-16 17:00
Interiors | 3rd Floor | Current Electric | #FFF3B2 | EWT | Wire Thermostats | 2025-05-14 09:00 | 2025-05-16 17:00
Interiors | 3rd Floor | Green Air Mechanical | #9F9D19 | GS | Start-up HVAC | 2025-05-19 09:00 | 2025-05-20 17:00
Interiors | 3rd Floor | Heritage Woodworks | #941651 | HV | Set Cabinets & Vanities | 2025-05-21 09:00 | 2025-05-27 17:00
Interiors | 3rd Floor | American Contractors | #CBF9F0 | AH | Install Pre-hung Doors | 2025-05-28 09:00 | 2025-05-29 17:00
Interiors | 3rd Floor | American Contractors | #CBF9F0 | AR | Running Trim and Stools | 2025-05-30 09:00 | 2025-06-03 17:00
Interiors | 3rd Floor | Heritage Woodworks | #941651 | HC | Set Countertops | 2025-06-04 09:00 | 2025-06-10 17:00
Interiors | 3rd Floor | Walkers | #6870DE | WC | Ceramic Tile (Floors & Walls) | 2025-06-04 09:00 | 2025-06-10 17:00
Interiors | 3rd Floor | Walkers | #6870DE | WB | Ceramic Backsplash | 2025-06-11 09:00 | 2025-06-16 17:00
Interiors | 3rd Floor | Walkers | #6870DE | WL | LVT Flooring | 2025-06-17 09:00 | 2025-06-20 17:00
Interiors | 3rd Floor | Current Electric | #FFF3B2 | ET | Electrical Trim (Plates & Lights) | 2025-06-23 09:00 | 2025-06-27 17:00
Interiors | 3rd Floor | Current Electric | #FFF3B2 | EV | Trim Low Voltage | 2025-06-23 09:00 | 2025-06-25 17:00
Interiors | 3rd Floor | Green Air Mechanical | #9F9D19 | GT | G/R/Ds HVAC Trim | 2025-06-30 09:00 | 2025-07-02 17:00
Interiors | 3rd Floor | Davishar | #C6E0B4 | PT | Trim Plumbing (Disposals/DWs) | 2025-06-30 09:00 | 2025-07-02 17:00
Interiors | 3rd Floor | TBD | #404040 | TA | Install Appliances | 2025-07-03 09:00 | 2025-07-07 17:00
Interiors | 3rd Floor | American Contractors | #CBF9F0 | AH | Door Hardware | 2025-07-03 09:00 | 2025-07-07 17:00
Interiors | 3rd Floor | Blue Sky | #8EA9DB | BF | Final Paint | 2025-07-08 09:00 | 2025-07-14 17:00
Interiors | 3rd Floor | Blue Sky | #8EA9DB | BD | Drywall Point Up | 2025-07-15 09:00 | 2025-07-16 17:00
Interiors | 3rd Floor | Morris Steel | #C6C8D1 | MM | Mirrors and Toilet Accessories | 2025-07-17 09:00 | 2025-07-18 17:00
Interiors | 3rd Floor | American Contractors | #CBF9F0 | AV | Closet Shelving | 2025-07-21 09:00 | 2025-07-24 17:00
Interiors | 3rd Floor | Clean | #B8A6E3 | RC | Rough-Clean | 2025-07-25 09:00 | 2025-07-30 17:00
Interiors | 3rd Floor | Walkers | #6870DE | WP | Pad and Carpet (Protect) | 2025-07-31 09:00 | 2025-08-06 17:00
Interiors | 3rd Floor | Breeden | #346093 | SI | Trade Final Ins (Sprinkler, Plumbing, HVAC, Electric, LV) | 2025-08-07 09:00 | 2025-08-13 17:00
Interiors | 3rd Floor | Blue Sky | #8EA9DB | BT | Paint Touch-up & Caulk | 2025-08-07 09:00 | 2025-08-08 17:00
Interiors | 3rd Floor | Breeden | #346093 | CP | Contractor Punchlist | 2025-08-14 09:00 | 2025-08-20 17:00
Vertical | 1st Floor | Otis | #B78593 | OF | Finishes Corridor & Elevator Lobby | 2025-05-07 09:00 | 2025-07-15 17:00
Vertical | 2nd Floor | Otis | #B78593 | OF | Finishes Corridor & Elevator Lobby | 2025-05-14 09:00 | 2025-07-22 17:00
Vertical | 3rd Floor | Otis | #B78593 | OF | Finishes Corridor & Elevator Lobby | 2025-05-21 09:00 | 2025-07-29 17:00
Vertical | Stairs | TBD | #404040 | TS | Stair 1 | 2025-07-30 09:00 | 2025-08-12 17:00
Vertical | Stairs | TBD | #404040 | TS | Stair 2 | 2025-07-30 09:00 | 2025-08-12 17:00
Vertical | 1st Floor | Heritage Woodworks | #941651 | HA | Amenity Finishes | 2025-05-14 09:00 | 2025-07-22 17:00

## CFA - Schedule
|  | 2024 | [180 empty] | 2025
|  | Jul | [27 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct
|  | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07
phase | location | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue
Framing | 1st Floor | bar: Dec 30 to Jan 10
2nd Floor | bar: Jan 13 to Jan 22; Jan 29 to Feb 11
[204 empty] | AD | AD | AD | AD | AD | AD | AD
3rd Floor | bar: Feb 05 to Feb 14
[227 empty] | AD | AD | AD | AD | AD | AD | AD
| Attic | Dec 04: AT; Dec 05: AT; Dec 06: AT; Dec 09: AD; Dec 10: AD; Dec 11: AC; Dec 12: AC; Dec 13: AC; Dec 14: AC; Dec 15: AC; Dec 16: AC; Dec 17: AC
Framing | bar: Jan 08 to Jan 21
Roof | bar: Dec 18 to Jan 02; Jan 08 to Jan 28
[183 empty] | AS | AS | AS | AS | AS | AS | AS
Interiors | 1st Floor | Feb 19: QP; Feb 20: QP; Feb 21: QP; Feb 22: QP; Feb 23: QP; Feb 24: QP; Feb 25: QP; Feb 26: GC; Feb 27: GC; Feb 28: GC; Mar 01: GC; Mar 02: GC; Mar 03: GC; Mar 04: GC; Mar 05: PU; Mar 06: PU; Mar 07: PU; Mar 08: PU; Mar 09: PU; Mar 10: PU; Mar 11: PU; Mar 12: SS; Mar 13: SS; Mar 14: SS; Mar 15: SS; Mar 16: SS; Mar 17: SS; Mar 18: SS; Mar 19: EW; Mar 20: EW; Mar 21: EW; Mar 22: EW; Mar 23: EW; Mar 24: EW; Mar 25: EW; Mar 26: CI; Mar 27: CI; Mar 31: QC; Apr 01: QC; Apr 02: QC; Apr 03: II; Apr 04: BS; Apr 05: BS; Apr 06: BS; Apr 07: BS; Apr 08: BS; Apr 09: BH; Apr 10: BH; Apr 11: BH; Apr 12: BH; Apr 13: BH; Apr 14: BH; Apr 15: BH; Apr 16: GY; Apr 17: GY; Apr 18: BP; Apr 19: BP; Apr 20: BP; Apr 21: BP; Apr 22: BP; Apr 23: BP; Apr 25: GA; Apr 28: PH; Apr 30: ES; May 01: ES; May 02: ES; May 05: GS; May 06: GS; May 07: HV; May 08: HV; May 09: HV; May 10: HV; May 11: HV; May 12: HV; May 13: HV; May 14: AH; May 15: AH; May 16: AR; May 17: AR; May 18: AR; May 19: AR; May 20: AR; May 21: HC; May 22: HC; May 23: HC; May 24: HC; May 25: HC; May 26: HC; May 27: HC; May 28: WB; May 29: WB; May 30: WB; May 31: WB; Jun 01: WB; Jun 02: WB; Jun 03: WL; Jun 04: WL; Jun 05: WL; Jun 06: WL; Jun 09: EV; Jun 10: EV; Jun 11: EV; Jun 16: GT; Jun 17: GT; Jun 18: GT; Jun 19: AH; Jun 20: AH; Jun 21: AH; Jun 22: AH; Jun 23: AH; Jun 24: BF; Jun 25: BF; Jun 26: BF; Jun 27: BF; Jun 28: BF; Jun 29: BF; Jun 30: BF; Jul 01: BD; Jul 02: BD; Jul 03: MM; Jul 04: MM; Jul 07: AV; Jul 08: AV; Jul 09: AV; Jul 10: AV; Jul 11: AV; Jul 12: AV; Jul 13: AV; Jul 14: AV; Jul 15: AV; Jul 16: AV; Jul 17: AV; Jul 18: AV; Jul 19: AV; Jul 20: AV; Jul 21: AV; Jul 22: AV; Jul 23: AV; Jul 24: AV; Jul 25: AV; Jul 26: AV; Jul 27: AV; Jul 28: AV; Jul 29: AV; Jul 30: AV; Jul 31: AV; Aug 01: AV; Aug 02: AV; Aug 03: AV; Aug 04: AV; Aug 05: AV; Aug 06: AV; Aug 07: AV; Aug 08: AV; Aug 09: AV; Aug 10: AV; Aug 11: AV; Aug 12: AV; Aug 13: AV; Aug 14: AV; Aug 15: AV; Aug 16: AV; Aug 17: AV; Aug 18: AV; Aug 19: AV; Aug 20: AV; Aug 21: AV; Aug 22: AV; Aug 23: AV; Aug 24: AV; Aug 25: AV; Aug 26: AV; Aug 27: AV; Aug 28: AV; Aug 29: AV; Aug 30: AV; Aug 31: AV; Sep 01: AV; Sep 02: AV; Sep 03: AV; Sep 04: AV; Sep 05: AV; Sep 06: AV; Sep 07: AV; Sep 08: AV; Sep 09: AV; Sep 10: AV; Sep 11: AV; Sep 12: AV; Sep 13: AV; Sep 14: AV; Sep 15: AV; Sep 16: AV; Sep 17: AV; Sep 18: AV; Sep 19: AV; Sep 20: AV; Sep 21: AV; Sep 22: AV; Sep 23: AV; Sep 24: AV; Sep 25: AV; Sep 26: AV; Sep 27: AV; Sep 28: AV; Sep 29: AV; Sep 30: AV; Oct 01: AV; Oct 02: AV; Oct 03: AV; Oct 04: AV; Oct 05: AV; Oct 06: AV; Oct 07: AV
[260 empty] | EL | EL | EL | EL | EL | EL | EL | [9 empty] | AP | AP | AP | AP | AP | AP | [12 empty] | BU | BU | BU | EP | EP | EP | EP |  | EWT | EWT | EWT | [18 empty] | WC | WC | WC | WC | WC | WC | WC | [12 empty] | ET | ET | ET | ET | ET |  |  | PT | PT | PT | TA | TA | TA | TA | TA | [17 empty] | RC | RC | RC | RC | RC | RC | WP | WP | WP | WP | WP | WP | WP | BT | BT | [5 empty] | CP | CP | CP | CP | CP | CP | CP
[260 empty] | ER | ER | ER | ER | ER | ER | ER | [30 empty] | SH | SH | SH | SH | SH | [85 empty] | SI | SI | SI | SI | SI | SI | SI
[297 empty] | EB | EB | EB | EB | EB
| 2nd Floor | [237 empty] | QP | QP | QP | QP | QP | QP | QP | GC | GC | GC | GC | GC | GC | GC | PU | PU | PU | PU | PU | PU | PU | SS | SS | SS | SS | SS | SS | SS | EW | EW | EW | EW | EW | EW | EW | CI | CI |  |  |  | QC | QC | QC | II | BS | BS | BS | BS | BS | BH | BH | BH | BH | BH | BH | BH | GY | GY | BP | BP | BP | BP | BP | BP |  | GA |  |  | PH |  | ES | ES | ES |  |  | GS | GS | HV | HV | HV | HV | HV | HV | HV | AH | AH | AR | AR | AR | AR | AR | HC | HC | HC | HC | HC | HC | HC | WB | WB | WB | WB | WB | WB | WL | WL | WL | WL |  |  | EV | EV | EV |  |  |  |  | GT | GT | GT | AH | AH | AH | AH | AH | BF | BF | BF | BF | BF | BF | BF | BD | BD | MM | MM |  |  | AV | AV | AV | AV | RC | RC | RC | RC | RC | RC | WP | WP | WP | WP | WP | WP | WP | BT | BT | [5 empty] | CP | CP | CP | CP | CP | CP | CP
[283 empty] | AP | AP | AP | AP | AP | AP | [12 empty] | BU | BU | BU | EP | EP | EP | EP |  | EWT | EWT | EWT | [18 empty] | WC | WC | WC | WC | WC | WC | WC | [12 empty] | ET | ET | ET | ET | ET |  |  | PT | PT | PT | TA | TA | TA | TA | TA | [30 empty] | SI | SI | SI | SI | SI | SI | SI | bar: EW to EW
[304 empty] | SH | SH | SH | SH | SH | bar: EW to EW
[304 empty] | EB | EB | EB | EB | EB
| 3rd Floor | [244 empty] | QP | QP | QP | QP | QP | QP | QP | GC | GC | GC | GC | GC | GC | GC | PU | PU | PU | PU | PU | PU | PU | SS | SS | SS | SS | SS | SS | SS | EW | EW | EW | EW | EW | EW | EW | CI | CI |  |  |  | QC | QC | QC | II | BS | BS | BS | BS | BS | BH | BH | BH | BH | BH | BH | BH | GY | GY | BP | BP | BP | BP | BP | BP |  | GA |  |  | PH |  | ES | ES | ES |  |  | GS | GS | HV | HV | HV | HV | HV | HV | HV | AH | AH | AR | AR | AR | AR | AR | HC | HC | HC | HC | HC | HC | HC | WB | WB | WB | WB | WB | WB | WL | WL | WL | WL |  |  | EV | EV | EV |  |  |  |  | GT | GT | GT | AH | AH | AH | AH | AH | BF | BF | BF | BF | BF | BF | BF | BD | BD | MM | MM |  |  | AV | AV | AV | AV | RC | RC | RC | RC | RC | RC | WP | WP | WP | WP | WP | WP | WP | BT | BT | [5 empty] | CP | CP | CP | CP | CP | CP | CP
[290 empty] | AP | AP | AP | AP | AP | AP | [12 empty] | BU | BU | BU | EP | EP | EP | EP |  | EWT | EWT | EWT | [18 empty] | WC | WC | WC | WC | WC | WC | WC | [12 empty] | ET | ET | ET | ET | ET |  |  | PT | PT | PT | TA | TA | TA | TA | TA | [30 empty] | SI | SI | SI | SI | SI | SI | SI | bar: EW to EW
[311 empty] | SH | SH | SH | SH | SH | bar: EW to EW
[311 empty] | EB | EB | EB | EB | EB
Exteriors | 1st Floor | bar: SS to SS
2nd Floor | bar: EW to EW
| 3rd Floor | [281 empty] | QE | QE | QE | QE
Masonry Facades | East | bar: PU to EW
| East Courtyard | [298 empty] | ME | ME | ME | ME | ME | ME | ME | ME | ME | ME
North | bar: QP to PU
| North Courtyard | [286 empty] | ME | ME | ME | ME | ME | ME | ME | ME | ME | ME
South A | bar: PU to PU
| South B | [308 empty] | ME | ME | ME | ME | ME
| West | [313 empty] | ME | ME | ME | ME | ME | ME | ME | ME | ME | ME | ME | ME | ME | ME
| West Courtyard | [281 empty] | ME | ME | ME | ME | ME | bar: EW to CI
Vertical | 1st Floor | [307 empty] | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF
[316 empty] | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA | HA
| 2nd Floor | [314 empty] | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF
| 3rd Floor | [321 empty] | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF | OF
| MEP R/Is | OM | OM | [207 empty] | PW | PW | PW | PW | PW | PW | PW | EG | EG | EG | EG | EG | EG | EG | EG | EG | EG | EG | EG | EG | EG | EF | EF | EF | EF | EF | EF | EF | EF | EF | EF | EF | EF | EF | EF | bar: GC to GC
[211 empty] | MS | MS | MS | MS | MS | MS | MS | SR | SR | SR | SR | SR | SR | SR | SR | SR | SR | SR | SR | SR | SR | SR | SR | SR | SR | SR | SR | SR
[211 empty] | GD | GD | GD | GD | GD | GD | GD | GD | GD | GD | GD | GD | GD | GD | GD | GD | GD | GD | GD | GD | GD | WI | WI | WI | WI | WI | WI | WI | WI | WI | WI | WI | WI | WI | WI
[232 empty] | PS | PS | PS | PS | PS | PS | PS | PS | PS | PS | PS | PS | PS | PS | bar: QP to QP
| Stairs | [391 empty] | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS
[393 empty] | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS | TS
| Transportation | [281 empty] | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | bar: QP to CI
Fenstrations and Skin | 1st Floor | [232 empty] | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | [64 empty] | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | [21 empty] | DG | DG | DG | DG | DG | DG | DG | MF | MF | MF | MF | MF | MF | MF | bar: QP to CI
| 1st Floor? | [385 empty] | MC | MC | MC | MC | MC | MC | MC
| 2nd Floor | [232 empty] | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | [64 empty] | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | bar: QP to CI
| 3rd Floor | [232 empty] | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | 8S | [106 empty] | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | bar: QP to CI
| Atic? | [371 empty] | GG | GG | GG | GG | GG | GG | GG | GG | GG | GG | GG | GG | GG | GG
Note on FZ5: Activity Name: Frame Phase: Framing Location: 1st Floor Trade: American Contractors Start Date: 30-Dec-2024 End Date: 10-Jan-2025
Note on GN6: Activity Name: Trusses Phase: Framing Location: 2nd Floor Trade: American Contractors Start Date: 13-Jan-2025 End Date: 22-Jan-2025
Note on HD6: Activity Name: Frame Phase: Framing Location: 2nd Floor Trade: American Contractors Start Date: 29-Jan-2025 End Date: 11-Feb-2025
Note on GW7: Activity Name: Deck Phase: Framing Location: 2nd Floor Trade: American Contractors Start Date: 22-Jan-2025 End Date: 28-Jan-2025
Note on HK9: Activity Name: Trusses Phase: Framing Location: 3rd Floor Trade: American Contractors Start Date: 05-Feb-2025 End Date: 14-Feb-2025
Note on HT10: Activity Name: Deck Phase: Framing Location: 3rd Floor Trade: American Contractors Start Date: 14-Feb-2025 End Date: 20-Feb-2025
Note on EZ11: Activity Name: Trusses Phase: Framing Location: Attic Trade: American Contractors Start Date: 04-Dec-2024 End Date: 06-Dec-2024
Note on FE11: Activity Name: Deck Phase: Framing Location: Attic Trade: American Contractors Start Date: 09-Dec-2024 End Date: 10-Dec-2024
Note on FG11: Activity Name: Frame Corridor Phase: Framing Location: Attic Trade: American Contractors Start Date: 11-Dec-2024 End Date: 17-Dec-2024
Note on GI14: Activity Name: Frame Elevator, Trash Chute and Stair Tower Roofs Phase: Framing Location: Framing Trade: American Contractors Start Date: 08-Jan-2025 End Date: 21-Jan-2025
Note on FN15: Activity Name: Trusses Phase: Framing Location: Roof Trade: American Contractors Start Date: 18-Dec-2024 End Date: 02-Jan-2025
Note on GI15: Activity Name: Dry-In Phase: Framing Location: Roof Trade: American Contractors Start Date: 08-Jan-2025 End Date: 28-Jan-2025
Note on GB16: Activity Name: Sheath Phase: Framing Location: Roof Trade: American Contractors Start Date: 01-Jan-2025 End Date: 07-Jan-2025
Note on HY18: Activity Name: Pre-insul & Gyp for Plumbing & Ins Phase: Interiors Location: 1st Floor Trade: Quality Building Products Start Date: 19-Feb-2025 End Date: 25-Feb-2025
Note on IF18: Activity Name: Above Ceiling HVAC R/I Phase: Interiors Location: 1st Floor Trade: Green Air Mechanical Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on IM18: Activity Name: Plumbing Unit R/I Domestic, Sanitary, Set Tubs Phase: Interiors Location: 1st Floor Trade: Davishar Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on IT18: Activity Name: OH Sprinkler R/I and Hydro Ins Phase: Interiors Location: 1st Floor Trade: Ranger Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on JA18: Activity Name: Electrical Wall R/I Phase: Interiors Location: 1st Floor Trade: Current Electric Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on JH18: Activity Name: R/I Trade Close-in Inspections Phase: Interiors Location: 1st Floor Trade: Breeden Start Date: 26-Mar-2025 End Date: 27-Mar-2025
Note on JM18: Activity Name: Insulate Ceilings Phase: Interiors Location: 1st Floor Trade: Quality Building Products Start Date: 31-Mar-2025 End Date: 02-Apr-2025
Note on JP18: Activity Name: Insulation Inspection Phase: Interiors Location: 1st Floor Trade: Breeden Start Date: 03-Apr-2025 End Date: 03-Apr-2025
Note on JQ18: Activity Name: Stock Drywall Phase: Interiors Location: 1st Floor Trade: Blue Sky Start Date: 04-Apr-2025 End Date: 08-Apr-2025
Note on JV18: Activity Name: Hang Drywall Phase: Interiors Location: 1st Floor Trade: Blue Sky Start Date: 09-Apr-2025 End Date: 15-Apr-2025
Note on KC18: Activity Name: Gypcrete Phase: Interiors Location: 1st Floor Trade: ECPF Start Date: 16-Apr-2025 End Date: 17-Apr-2025
Note on KE18: Activity Name: Prime Paint Phase: Interiors Location: 1st Floor Trade: Blue Sky Start Date: 18-Apr-2025 End Date: 23-Apr-2025
Note on KL18: Activity Name: Set AHU Phase: Interiors Location: 1st Floor Trade: Green Air Mechanical Start Date: 25-Apr-2025 End Date: 25-Apr-2025
Note on KO18: Activity Name: Set HWH and Plumb (Set Submeter) Phase: Interiors Location: 1st Floor Trade: Davishar Start Date: 28-Apr-2025 End Date: 28-Apr-2025
Note on KQ18: Activity Name: Switch and Plug Phase: Interiors Location: 1st Floor Trade: Current Electric Start Date: 30-Apr-2025 End Date: 02-May-2025
Note on KV18: Activity Name: Start-up HVAC Phase: Interiors Location: 1st Floor Trade: Green Air Mechanical Start Date: 05-May-2025 End Date: 06-May-2025
Note on KX18: Activity Name: Set Cabinets & Vanities Phase: Interiors Location: 1st Floor Trade: Heritage Woodworks Start Date: 07-May-2025 End Date: 13-May-2025
Note on LE18: Activity Name: Install Pre-hung Doors Phase: Interiors Location: 1st Floor Trade: American Contractors Start Date: 14-May-2025 End Date: 15-May-2025
Note on LG18: Activity Name: Running Trim and Stools Phase: Interiors Location: 1st Floor Trade: American Contractors Start Date: 16-May-2025 End Date: 20-May-2025
Note on LL18: Activity Name: Set Countertops Phase: Interiors Location: 1st Floor Trade: Heritage Woodworks Start Date: 21-May-2025 End Date: 27-May-2025
Note on LS18: Activity Name: Ceramic Backsplash Phase: Interiors Location: 1st Floor Trade: Walkers Start Date: 28-May-2025 End Date: 02-Jun-2025
Note on LY18: Activity Name: LVT Flooring Phase: Interiors Location: 1st Floor Trade: Walkers Start Date: 03-Jun-2025 End Date: 06-Jun-2025
Note on ME18: Activity Name: Trim Low Voltage Phase: Interiors Location: 1st Floor Trade: Current Electric Start Date: 09-Jun-2025 End Date: 11-Jun-2025
Note on ML18: Activity Name: G/R/Ds HVAC Trim Phase: Interiors Location: 1st Floor Trade: Green Air Mechanical Start Date: 16-Jun-2025 End Date: 18-Jun-2025
Note on MO18: Activity Name: Door Hardware Phase: Interiors Location: 1st Floor Trade: American Contractors Start Date: 19-Jun-2025 End Date: 23-Jun-2025
Note on MT18: Activity Name: Final Paint Phase: Interiors Location: 1st Floor Trade: Blue Sky Start Date: 24-Jun-2025 End Date: 30-Jun-2025
Note on NA18: Activity Name: Drywall Point Up Phase: Interiors Location: 1st Floor Trade: Blue Sky Start Date: 01-Jul-2025 End Date: 02-Jul-2025
Note on NC18: Activity Name: Mirrors and Toilet Accessories Phase: Interiors Location: 1st Floor Trade: Morris Steel Start Date: 03-Jul-2025 End Date: 04-Jul-2025
Note on NG18: Activity Name: Closet Shelving Phase: Interiors Location: 1st Floor Trade: American Contractors Start Date: 07-Jul-2025 End Date: 07-Oct-2025
Note on JA19: Activity Name: Electrical Lighting OH R/I Phase: Interiors Location: 1st Floor Trade: Current Electric Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on JQ19: Activity Name: Framing & R/I Punchlist - Set Unit Entry FMs Phase: Interiors Location: 1st Floor Trade: American Contractors Start Date: 04-Apr-2025 End Date: 09-Apr-2025
Note on KI19: Activity Name: Point Up Drywall Phase: Interiors Location: 1st Floor Trade: Blue Sky Start Date: 22-Apr-2025 End Date: 24-Apr-2025
Note on KL19: Activity Name: Low Voltage Panel Phase: Interiors Location: 1st Floor Trade: Current Electric Start Date: 25-Apr-2025 End Date: 28-Apr-2025
Note on KQ19: Activity Name: Wire Thermostats Phase: Interiors Location: 1st Floor Trade: Current Electric Start Date: 30-Apr-2025 End Date: 02-May-2025
Note on LL19: Activity Name: Ceramic Tile (Floors & Walls) Phase: Interiors Location: 1st Floor Trade: Walkers Start Date: 21-May-2025 End Date: 27-May-2025
Note on ME19: Activity Name: Electrical Trim (Plates & Lights) Phase: Interiors Location: 1st Floor Trade: Current Electric Start Date: 09-Jun-2025 End Date: 13-Jun-2025
Note on ML19: Activity Name: Trim Plumbing (Disposals/DWs) Phase: Interiors Location: 1st Floor Trade: Davishar Start Date: 16-Jun-2025 End Date: 18-Jun-2025
Note on MO19: Activity Name: Install Appliances Phase: Interiors Location: 1st Floor Trade: TBD Start Date: 19-Jun-2025 End Date: 23-Jun-2025
Note on NK19: Activity Name: Rough-Clean Phase: Interiors Location: 1st Floor Trade: Clean Start Date: 11-Jul-2025 End Date: 16-Jul-2025
Note on NQ19: Activity Name: Pad and Carpet (Protect) Phase: Interiors Location: 1st Floor Trade: Walkers Start Date: 17-Jul-2025 End Date: 23-Jul-2025
Note on NX19: Activity Name: Paint Touch-up & Caulk Phase: Interiors Location: 1st Floor Trade: Blue Sky Start Date: 24-Jul-2025 End Date: 25-Jul-2025
Note on OE19: Activity Name: Contractor Punchlist Phase: Interiors Location: 1st Floor Trade: Breeden Start Date: 31-Jul-2025 End Date: 06-Aug-2025
Note on JA20: Activity Name: Low Voltage Wall R/I (Tele/Cable/IT) Phase: Interiors Location: 1st Floor Trade: Current Electric Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on KL20: Activity Name: Sprinkler Head Escutheons Phase: Interiors Location: 1st Floor Trade: Ranger Start Date: 25-Apr-2025 End Date: 29-Apr-2025
Note on NX20: Activity Name: Trade Final Ins (Sprinkler, Plumbing, HVAC, Electric, LV) Phase: Interiors Location: 1st Floor Trade: Breeden Start Date: 24-Jul-2025 End Date: 30-Jul-2025
Note on KL21: Activity Name: Electrical Panel Brkrs and Equipment Terminations Phase: Interiors Location: 1st Floor Trade: Current Electric Start Date: 25-Apr-2025 End Date: 29-Apr-2025
Note on IF22: Activity Name: Pre-insul & Gyp for Plumbing & Ins Phase: Interiors Location: 2nd Floor Trade: Quality Building Products Start Date: 26-Feb-2025 End Date: 04-Mar-2025
Note on IM22: Activity Name: Above Ceiling HVAC R/I Phase: Interiors Location: 2nd Floor Trade: Green Air Mechanical Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on IT22: Activity Name: Plumbing Unit R/I Domestic, Sanitary, Set Tubs Phase: Interiors Location: 2nd Floor Trade: Davishar Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on JA22: Activity Name: OH Sprinkler R/I and Hydro Ins Phase: Interiors Location: 2nd Floor Trade: Ranger Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on JH22: Activity Name: Electrical Wall R/I Phase: Interiors Location: 2nd Floor Trade: Current Electric Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on JO22: Activity Name: R/I Trade Close-in Inspections Phase: Interiors Location: 2nd Floor Trade: Breeden Start Date: 02-Apr-2025 End Date: 03-Apr-2025
Note on JT22: Activity Name: Insulate Ceilings Phase: Interiors Location: 2nd Floor Trade: Quality Building Products Start Date: 07-Apr-2025 End Date: 09-Apr-2025
Note on JW22: Activity Name: Insulation Inspection Phase: Interiors Location: 2nd Floor Trade: Breeden Start Date: 10-Apr-2025 End Date: 10-Apr-2025
Note on JX22: Activity Name: Stock Drywall Phase: Interiors Location: 2nd Floor Trade: Blue Sky Start Date: 11-Apr-2025 End Date: 15-Apr-2025
Note on KC22: Activity Name: Hang Drywall Phase: Interiors Location: 2nd Floor Trade: Blue Sky Start Date: 16-Apr-2025 End Date: 22-Apr-2025
Note on KJ22: Activity Name: Gypcrete Phase: Interiors Location: 2nd Floor Trade: ECPF Start Date: 23-Apr-2025 End Date: 24-Apr-2025
Note on KL22: Activity Name: Prime Paint Phase: Interiors Location: 2nd Floor Trade: Blue Sky Start Date: 25-Apr-2025 End Date: 30-Apr-2025
Note on KS22: Activity Name: Set AHU Phase: Interiors Location: 2nd Floor Trade: Green Air Mechanical Start Date: 02-May-2025 End Date: 02-May-2025
Note on KV22: Activity Name: Set HWH and Plumb (Set Submeter) Phase: Interiors Location: 2nd Floor Trade: Davishar Start Date: 05-May-2025 End Date: 05-May-2025
Note on KX22: Activity Name: Switch and Plug Phase: Interiors Location: 2nd Floor Trade: Current Electric Start Date: 07-May-2025 End Date: 09-May-2025
Note on LC22: Activity Name: Start-up HVAC Phase: Interiors Location: 2nd Floor Trade: Green Air Mechanical Start Date: 12-May-2025 End Date: 13-May-2025
Note on LE22: Activity Name: Set Cabinets & Vanities Phase: Interiors Location: 2nd Floor Trade: Heritage Woodworks Start Date: 14-May-2025 End Date: 20-May-2025
Note on LL22: Activity Name: Install Pre-hung Doors Phase: Interiors Location: 2nd Floor Trade: American Contractors Start Date: 21-May-2025 End Date: 22-May-2025
Note on LN22: Activity Name: Running Trim and Stools Phase: Interiors Location: 2nd Floor Trade: American Contractors Start Date: 23-May-2025 End Date: 27-May-2025
Note on LS22: Activity Name: Set Countertops Phase: Interiors Location: 2nd Floor Trade: Heritage Woodworks Start Date: 28-May-2025 End Date: 03-Jun-2025
Note on LZ22: Activity Name: Ceramic Backsplash Phase: Interiors Location: 2nd Floor Trade: Walkers Start Date: 04-Jun-2025 End Date: 09-Jun-2025
Note on MF22: Activity Name: LVT Flooring Phase: Interiors Location: 2nd Floor Trade: Walkers Start Date: 10-Jun-2025 End Date: 13-Jun-2025
Note on ML22: Activity Name: Trim Low Voltage Phase: Interiors Location: 2nd Floor Trade: Current Electric Start Date: 16-Jun-2025 End Date: 18-Jun-2025
Note on MS22: Activity Name: G/R/Ds HVAC Trim Phase: Interiors Location: 2nd Floor Trade: Green Air Mechanical Start Date: 23-Jun-2025 End Date: 25-Jun-2025
Note on MV22: Activity Name: Door Hardware Phase: Interiors Location: 2nd Floor Trade: American Contractors Start Date: 26-Jun-2025 End Date: 30-Jun-2025
Note on NA22: Activity Name: Final Paint Phase: Interiors Location: 2nd Floor Trade: Blue Sky Start Date: 01-Jul-2025 End Date: 07-Jul-2025
Note on NH22: Activity Name: Drywall Point Up Phase: Interiors Location: 2nd Floor Trade: Blue Sky Start Date: 08-Jul-2025 End Date: 09-Jul-2025
Note on NJ22: Activity Name: Mirrors and Toilet Accessories Phase: Interiors Location: 2nd Floor Trade: Morris Steel Start Date: 10-Jul-2025 End Date: 11-Jul-2025
Note on NN22: Activity Name: Closet Shelving Phase: Interiors Location: 2nd Floor Trade: American Contractors Start Date: 14-Jul-2025 End Date: 17-Jul-2025
Note on NR22: Activity Name: Rough-Clean Phase: Interiors Location: 2nd Floor Trade: Clean Start Date: 18-Jul-2025 End Date: 23-Jul-2025
Note on NX22: Activity Name: Pad and Carpet (Protect) Phase: Interiors Location: 2nd Floor Trade: Walkers Start Date: 24-Jul-2025 End Date: 30-Jul-2025
Note on OE22: Activity Name: Paint Touch-up & Caulk Phase: Interiors Location: 2nd Floor Trade: Blue Sky Start Date: 31-Jul-2025 End Date: 01-Aug-2025
Note on OL22: Activity Name: Contractor Punchlist Phase: Interiors Location: 2nd Floor Trade: Breeden Start Date: 07-Aug-2025 End Date: 13-Aug-2025
Note on JH23: Activity Name: Electrical Lighting OH R/I Phase: Interiors Location: 2nd Floor Trade: Current Electric Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on JX23: Activity Name: Framing & R/I Punchlist - Set Unit Entry FMs Phase: Interiors Location: 2nd Floor Trade: American Contractors Start Date: 11-Apr-2025 End Date: 16-Apr-2025
Note on KP23: Activity Name: Point Up Drywall Phase: Interiors Location: 2nd Floor Trade: Blue Sky Start Date: 29-Apr-2025 End Date: 01-May-2025
Note on KS23: Activity Name: Low Voltage Panel Phase: Interiors Location: 2nd Floor Trade: Current Electric Start Date: 02-May-2025 End Date: 05-May-2025
Note on KX23: Activity Name: Wire Thermostats Phase: Interiors Location: 2nd Floor Trade: Current Electric Start Date: 07-May-2025 End Date: 09-May-2025
Note on LS23: Activity Name: Ceramic Tile (Floors & Walls) Phase: Interiors Location: 2nd Floor Trade: Walkers Start Date: 28-May-2025 End Date: 03-Jun-2025
Note on ML23: Activity Name: Electrical Trim (Plates & Lights) Phase: Interiors Location: 2nd Floor Trade: Current Electric Start Date: 16-Jun-2025 End Date: 20-Jun-2025
Note on MS23: Activity Name: Trim Plumbing (Disposals/DWs) Phase: Interiors Location: 2nd Floor Trade: Davishar Start Date: 23-Jun-2025 End Date: 25-Jun-2025
Note on MV23: Activity Name: Install Appliances Phase: Interiors Location: 2nd Floor Trade: TBD Start Date: 26-Jun-2025 End Date: 30-Jun-2025
Note on OE23: Activity Name: Trade Final Ins (Sprinkler, Plumbing, HVAC, Electric, LV) Phase: Interiors Location: 2nd Floor Trade: Breeden Start Date: 31-Jul-2025 End Date: 06-Aug-2025
Note on JH24: Activity Name: Low Voltage Wall R/I (Tele/Cable/IT) Phase: Interiors Location: 2nd Floor Trade: Current Electric Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on KS24: Activity Name: Sprinkler Head Escutheons Phase: Interiors Location: 2nd Floor Trade: Ranger Start Date: 02-May-2025 End Date: 06-May-2025
Note on KS25: Activity Name: Electrical Panel Brkrs and Equipment Terminations Phase: Interiors Location: 2nd Floor Trade: Current Electric Start Date: 02-May-2025 End Date: 06-May-2025
Note on IM27: Activity Name: Pre-insul & Gyp for Plumbing & Ins Phase: Interiors Location: 3rd Floor Trade: Quality Building Products Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on IT27: Activity Name: Above Ceiling HVAC R/I Phase: Interiors Location: 3rd Floor Trade: Green Air Mechanical Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on JA27: Activity Name: Plumbing Unit R/I Domestic, Sanitary, Set Tubs Phase: Interiors Location: 3rd Floor Trade: Davishar Start Date: 19-Mar-2025 End Date: 25-Mar-2025
Note on JH27: Activity Name: OH Sprinkler R/I and Hydro Ins Phase: Interiors Location: 3rd Floor Trade: Ranger Start Date: 26-Mar-2025 End Date: 01-Apr-2025
Note on JO27: Activity Name: Electrical Wall R/I Phase: Interiors Location: 3rd Floor Trade: Current Electric Start Date: 02-Apr-2025 End Date: 08-Apr-2025
Note on JV27: Activity Name: R/I Trade Close-in Inspections Phase: Interiors Location: 3rd Floor Trade: Breeden Start Date: 09-Apr-2025 End Date: 10-Apr-2025
Note on KA27: Activity Name: Insulate Ceilings Phase: Interiors Location: 3rd Floor Trade: Quality Building Products Start Date: 14-Apr-2025 End Date: 16-Apr-2025
Note on KD27: Activity Name: Insulation Inspection Phase: Interiors Location: 3rd Floor Trade: Breeden Start Date: 17-Apr-2025 End Date: 17-Apr-2025
Note on KE27: Activity Name: Stock Drywall Phase: Interiors Location: 3rd Floor Trade: Blue Sky Start Date: 18-Apr-2025 End Date: 22-Apr-2025
Note on KJ27: Activity Name: Hang Drywall Phase: Interiors Location: 3rd Floor Trade: Blue Sky Start Date: 23-Apr-2025 End Date: 29-Apr-2025
Note on KQ27: Activity Name: Gypcrete Phase: Interiors Location: 3rd Floor Trade: ECPF Start Date: 30-Apr-2025 End Date: 01-May-2025
Note on KS27: Activity Name: Prime Paint Phase: Interiors Location: 3rd Floor Trade: Blue Sky Start Date: 02-May-2025 End Date: 07-May-2025
Note on KZ27: Activity Name: Set AHU Phase: Interiors Location: 3rd Floor Trade: Green Air Mechanical Start Date: 09-May-2025 End Date: 09-May-2025
Note on LC27: Activity Name: Set HWH and Plumb (Set Submeter) Phase: Interiors Location: 3rd Floor Trade: Davishar Start Date: 12-May-2025 End Date: 12-May-2025
Note on LE27: Activity Name: Switch and Plug Phase: Interiors Location: 3rd Floor Trade: Current Electric Start Date: 14-May-2025 End Date: 16-May-2025
Note on LJ27: Activity Name: Start-up HVAC Phase: Interiors Location: 3rd Floor Trade: Green Air Mechanical Start Date: 19-May-2025 End Date: 20-May-2025
Note on LL27: Activity Name: Set Cabinets & Vanities Phase: Interiors Location: 3rd Floor Trade: Heritage Woodworks Start Date: 21-May-2025 End Date: 27-May-2025
Note on LS27: Activity Name: Install Pre-hung Doors Phase: Interiors Location: 3rd Floor Trade: American Contractors Start Date: 28-May-2025 End Date: 29-May-2025
Note on LU27: Activity Name: Running Trim and Stools Phase: Interiors Location: 3rd Floor Trade: American Contractors Start Date: 30-May-2025 End Date: 03-Jun-2025
Note on LZ27: Activity Name: Set Countertops Phase: Interiors Location: 3rd Floor Trade: Heritage Woodworks Start Date: 04-Jun-2025 End Date: 10-Jun-2025
Note on MG27: Activity Name: Ceramic Backsplash Phase: Interiors Location: 3rd Floor Trade: Walkers Start Date: 11-Jun-2025 End Date: 16-Jun-2025
Note on MM27: Activity Name: LVT Flooring Phase: Interiors Location: 3rd Floor Trade: Walkers Start Date: 17-Jun-2025 End Date: 20-Jun-2025
Note on MS27: Activity Name: Trim Low Voltage Phase: Interiors Location: 3rd Floor Trade: Current Electric Start Date: 23-Jun-2025 End Date: 25-Jun-2025
Note on MZ27: Activity Name: G/R/Ds HVAC Trim Phase: Interiors Location: 3rd Floor Trade: Green Air Mechanical Start Date: 30-Jun-2025 End Date: 02-Jul-2025
Note on NC27: Activity Name: Door Hardware Phase: Interiors Location: 3rd Floor Trade: American Contractors Start Date: 03-Jul-2025 End Date: 07-Jul-2025
Note on NH27: Activity Name: Final Paint Phase: Interiors Location: 3rd Floor Trade: Blue Sky Start Date: 08-Jul-2025 End Date: 14-Jul-2025
Note on NO27: Activity Name: Drywall Point Up Phase: Interiors Location: 3rd Floor Trade: Blue Sky Start Date: 15-Jul-2025 End Date: 16-Jul-2025
Note on NQ27: Activity Name: Mirrors and Toilet Accessories Phase: Interiors Location: 3rd Floor Trade: Morris Steel Start Date: 17-Jul-2025 End Date: 18-Jul-2025
Note on NU27: Activity Name: Closet Shelving Phase: Interiors Location: 3rd Floor Trade: American Contractors Start Date: 21-Jul-2025 End Date: 24-Jul-2025
Note on NY27: Activity Name: Rough-Clean Phase: Interiors Location: 3rd Floor Trade: Clean Start Date: 25-Jul-2025 End Date: 30-Jul-2025
Note on OE27: Activity Name: Pad and Carpet (Protect) Phase: Interiors Location: 3rd Floor Trade: Walkers Start Date: 31-Jul-2025 End Date: 06-Aug-2025
Note on OL27: Activity Name: Paint Touch-up & Caulk Phase: Interiors Location: 3rd Floor Trade: Blue Sky Start Date: 07-Aug-2025 End Date: 08-Aug-2025
Note on OS27: Activity Name: Contractor Punchlist Phase: Interiors Location: 3rd Floor Trade: Breeden Start Date: 14-Aug-2025 End Date: 20-Aug-2025
Note on JO28: Activity Name: Electrical Lighting OH R/I Phase: Interiors Location: 3rd Floor Trade: Current Electric Start Date: 02-Apr-2025 End Date: 08-Apr-2025
Note on KE28: Activity Name: Framing & R/I Punchlist - Set Unit Entry FMs Phase: Interiors Location: 3rd Floor Trade: American Contractors Start Date: 18-Apr-2025 End Date: 23-Apr-2025
Note on KW28: Activity Name: Point Up Drywall Phase: Interiors Location: 3rd Floor Trade: Blue Sky Start Date: 06-May-2025 End Date: 08-May-2025
Note on KZ28: Activity Name: Low Voltage Panel Phase: Interiors Location: 3rd Floor Trade: Current Electric Start Date: 09-May-2025 End Date: 12-May-2025
Note on LE28: Activity Name: Wire Thermostats Phase: Interiors Location: 3rd Floor Trade: Current Electric Start Date: 14-May-2025 End Date: 16-May-2025
Note on LZ28: Activity Name: Ceramic Tile (Floors & Walls) Phase: Interiors Location: 3rd Floor Trade: Walkers Start Date: 04-Jun-2025 End Date: 10-Jun-2025
Note on MS28: Activity Name: Electrical Trim (Plates & Lights) Phase: Interiors Location: 3rd Floor Trade: Current Electric Start Date: 23-Jun-2025 End Date: 27-Jun-2025
Note on MZ28: Activity Name: Trim Plumbing (Disposals/DWs) Phase: Interiors Location: 3rd Floor Trade: Davishar Start Date: 30-Jun-2025 End Date: 02-Jul-2025
Note on NC28: Activity Name: Install Appliances Phase: Interiors Location: 3rd Floor Trade: TBD Start Date: 03-Jul-2025 End Date: 07-Jul-2025
Note on OL28: Activity Name: Trade Final Ins (Sprinkler, Plumbing, HVAC, Electric, LV) Phase: Interiors Location: 3rd Floor Trade: Breeden Start Date: 07-Aug-2025 End Date: 13-Aug-2025
Note on JO29: Activity Name: Low Voltage Wall R/I (Tele/Cable/IT) Phase: Interiors Location: 3rd Floor Trade: Current Electric Start Date: 02-Apr-2025 End Date: 08-Apr-2025
Note on KZ29: Activity Name: Sprinkler Head Escutheons Phase: Interiors Location: 3rd Floor Trade: Ranger Start Date: 09-May-2025 End Date: 13-May-2025
Note on KZ30: Activity Name: Electrical Panel Brkrs and Equipment Terminations Phase: Interiors Location: 3rd Floor Trade: Current Electric Start Date: 09-May-2025 End Date: 13-May-2025
Note on JJ32: Activity Name: Insulate Exterior Walls Phase: Exteriors Location: 1st Floor Trade: Quality Building Products Start Date: 28-Mar-2025 End Date: 31-Mar-2025
Note on JQ33: Activity Name: Insulate Exterior Walls Phase: Exteriors Location: 2nd Floor Trade: Quality Building Products Start Date: 04-Apr-2025 End Date: 07-Apr-2025
Note on JX34: Activity Name: Insulate Exterior Walls Phase: Exteriors Location: 3rd Floor Trade: Quality Building Products Start Date: 11-Apr-2025 End Date: 14-Apr-2025
Note on JC35: Activity Name: Masonry Elevation Phase: Masonry Facades Location: East Trade: Brick Solutions Start Date: 21-Mar-2025 End Date: 03-Apr-2025
Note on KO36: Activity Name: Masonry Elevation Phase: Masonry Facades Location: East Courtyard Trade: Brick Solutions Start Date: 28-Apr-2025 End Date: 07-May-2025
Note on IO37: Activity Name: Masonry Elevation Phase: Masonry Facades Location: North Trade: Brick Solutions Start Date: 07-Mar-2025 End Date: 20-Mar-2025
Note on KC38: Activity Name: Masonry Elevation Phase: Masonry Facades Location: North Courtyard Trade: Brick Solutions Start Date: 16-Apr-2025 End Date: 25-Apr-2025
Note on JC39: Activity Name: Masonry Elevation Phase: Masonry Facades Location: South A Trade: Brick Solutions Start Date: 21-Mar-2025 End Date: 25-Mar-2025
Note on KY40: Activity Name: Masonry Elevation Phase: Masonry Facades Location: South B Trade: Brick Solutions Start Date: 08-May-2025 End Date: 12-May-2025
Note on LD41: Activity Name: Masonry Elevation Phase: Masonry Facades Location: West Trade: Brick Solutions Start Date: 13-May-2025 End Date: 26-May-2025
Note on JQ42: Activity Name: Masonry Elevation Phase: Masonry Facades Location: West Courtyard Trade: Brick Solutions Start Date: 04-Apr-2025 End Date: 15-Apr-2025
Note on KX43: Activity Name: Finishes Corridor & Elevator Lobby Phase: Vertical Location: 1st Floor Trade: Otis Start Date: 07-May-2025 End Date: 15-Jul-2025
Note on LE44: Activity Name: Amenity Finishes Phase: Vertical Location: 1st Floor Trade: Heritage Woodworks Start Date: 14-May-2025 End Date: 22-Jul-2025
Note on LE45: Activity Name: Finishes Corridor & Elevator Lobby Phase: Vertical Location: 2nd Floor Trade: Otis Start Date: 14-May-2025 End Date: 22-Jul-2025
Note on LL46: Activity Name: Finishes Corridor & Elevator Lobby Phase: Vertical Location: 3rd Floor Trade: Otis Start Date: 21-May-2025 End Date: 29-Jul-2025
Note on C47: Activity Name: Set Elevator Machines 1 & 2 (Protect) Phase: Vertical Location: MEP R/Is Trade: Otis Start Date: 04-Jul-2024 End Date: 05-Jul-2024
Note on HD47: Activity Name: Set Water Service & Equipment Phase: Vertical Location: MEP R/Is Trade: Davishar Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on HK47: Activity Name: Set Electrical Gear Phase: Vertical Location: MEP R/Is Trade: Current Electric Start Date: 05-Feb-2025 End Date: 18-Feb-2025
Note on HY47: Activity Name: Electrical Feeders Phase: Vertical Location: MEP R/Is Trade: Current Electric Start Date: 19-Feb-2025 End Date: 04-Mar-2025
Note on IT47: Activity Name: Set Roof Top Equipment Phase: Vertical Location: MEP R/Is Trade: Solid Construction Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on HD48: Activity Name: Set Trash Chute Phase: Vertical Location: MEP R/Is Trade: Morris Steel Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on HK48: Activity Name: Sprinkler Risers Phase: Vertical Location: MEP R/Is Trade: Ranger Start Date: 05-Feb-2025 End Date: 25-Feb-2025
Note on HD49: Activity Name: HVAC Duct Risers Phase: Vertical Location: MEP R/Is Trade: Green Air Mechanical Start Date: 29-Jan-2025 End Date: 18-Feb-2025
Note on HY49: Activity Name: Shaft Wall Inspections Phase: Vertical Location: MEP R/Is Trade: Breeden Start Date: 19-Feb-2025 End Date: 04-Mar-2025
Note on HY50: Activity Name: Plumbing Stacks & Roof Vents Phase: Vertical Location: MEP R/Is Trade: Davishar Start Date: 19-Feb-2025 End Date: 11-Mar-2025
Note on OD54: Activity Name: Stair 1 Phase: Vertical Location: Stairs Trade: TBD Start Date: 30-Jul-2025 End Date: 12-Aug-2025
Note on OD55: Activity Name: Stair 2 Phase: Vertical Location: Stairs Trade: TBD Start Date: 30-Jul-2025 End Date: 12-Aug-2025
Note on IM56: Activity Name: Elevator 1 Phase: Vertical Location: Transportation Trade: Otis Start Date: 05-Mar-2025 End Date: 08-Apr-2025
Note on JV56: Activity Name: Elevator 2 Phase: Vertical Location: Transportation Trade: Otis Start Date: 09-Apr-2025 End Date: 13-May-2025
Note on IA58: Activity Name: Sheathing & Windows Phase: Fenstrations and Skin Location: 1st Floor Trade: 84 Lumber Start Date: 21-Feb-2025 End Date: 10-Apr-2025
Note on KY58: Activity Name: Siding - All Elevations Phase: Fenstrations and Skin Location: 1st Floor Trade: Solid Construction Start Date: 08-May-2025 End Date: 18-Jun-2025
Note on NJ58: Activity Name: Soffit Siding Phase: Fenstrations and Skin Location: 1st Floor Trade: Solid Construction Start Date: 10-Jul-2025 End Date: 16-Jul-2025
Note on NQ58: Activity Name: Storefront Phase: Fenstrations and Skin Location: 1st Floor Trade: Morris Steel Start Date: 17-Jul-2025 End Date: 23-Jul-2025
Note on NX62: Activity Name: Canopy Phase: Fenstrations and Skin Location: 1st Floor? Trade: Morris Steel Start Date: 24-Jul-2025 End Date: 30-Jul-2025
Note on IA63: Activity Name: Sheathing & Windows Phase: Fenstrations and Skin Location: 2nd Floor Trade: 84 Lumber Start Date: 21-Feb-2025 End Date: 10-Apr-2025
Note on KY63: Activity Name: Siding - All Elevations Phase: Fenstrations and Skin Location: 2nd Floor Trade: Solid Construction Start Date: 08-May-2025 End Date: 18-Jun-2025
Note on IA65: Activity Name: Sheathing & Windows Phase: Fenstrations and Skin Location: 3rd Floor Trade: 84 Lumber Start Date: 21-Feb-2025 End Date: 10-Apr-2025
Note on MO65: Activity Name: Siding - All Elevations Phase: Fenstrations and Skin Location: 3rd Floor Trade: Solid Construction Start Date: 19-Jun-2025 End Date: 09-Jul-2025
Note on NJ67: Activity Name: Gutter & Vents Phase: Fenstrations and Skin Location: Atic? Trade: Green Air Mechanical Start Date: 10-Jul-2025 End Date: 23-Jul-2025

## CFA - Legends
Exteriors |  | Fenstrations and Skin |  | Framing |  | Interiors |  | Masonry Facades |  | Vertical
[6 empty] | AH | Install Pre-hung Doors
Quality Building Products |  | 84 Lumber |  | American Contractors |  | AP | Framing & R/I Punchlist - Set Unit Entry FMs | Brick Solutions |  | Breeden
QE | Insulate Exterior Walls | 8S | Sheathing & Windows | AC | Frame Corridor | AR | Running Trim and Stools | ME | Masonry Elevation | WI | Shaft Wall Inspections
|  |  |  | AD | Deck | AV | Closet Shelving
|  | Green Air Mechanical |  | AF | Frame |  |  |  |  | Current Electric
|  | GG | Gutter & Vents | AR | Dry-In | Blue Sky |  |  |  | EF | Electrical Feeders
|  |  |  | AS | Sheath | BD | Drywall Point Up |  |  | EG | Set Electrical Gear
|  | Morris Steel |  | AT | Trusses | BF | Final Paint
|  | MC | Canopy |  |  | BH | Hang Drywall |  |  | Davishar
|  | MF | Storefront |  |  | BP | Prime Paint |  |  | PS | Plumbing Stacks & Roof Vents
[6 empty] | BS | Stock Drywall |  |  | PW | Set Water Service & Equipment
|  | Solid Construction |  |  |  | BT | Paint Touch-up & Caulk
|  | DG | Soffit Siding |  |  | BU | Point Up Drywall |  |  | Green Air Mechanical
|  | DS | Siding - All Elevations | [6 empty] | GD | HVAC Duct Risers
Breeden
[6 empty] | CI | R/I Trade Close-in Inspections |  |  | Heritage Woodworks
[6 empty] | CP | Contractor Punchlist |  |  | HA | Amenity Finishes
[6 empty] | II | Insulation Inspection
[6 empty] | SI | Trade Final Ins (Sprinkler, Plumbing, HVAC, Electric, LV) |  |  | Morris Steel
[10 empty] | MS | Set Trash Chute
Clean
[6 empty] | RC | Rough-Clean |  |  | Otis
[10 empty] | O1 | Elevator 2
[6 empty] | Current Electric |  |  |  | O2 | Elevator 1
[6 empty] | EB | Electrical Panel Brkrs and Equipment Terminations |  |  | OF | Finishes Corridor & Elevator Lobby
[6 empty] | EL | Electrical Lighting OH R/I |  |  | OM | Set Elevator Machines 1 & 2 (Protect)
[6 empty] | EP | Low Voltage Panel
[6 empty] | ER | Low Voltage Wall R/I (Tele/Cable/IT) |  |  | Ranger
[6 empty] | ES | Switch and Plug |  |  | SR | Sprinkler Risers
[6 empty] | ET | Electrical Trim (Plates & Lights)
[6 empty] | EV | Trim Low Voltage |  |  | Solid Construction
[6 empty] | EW | Electrical Wall R/I |  |  | DR | Set Roof Top Equipment
[6 empty] | EWT | Wire Thermostats
TBD
[6 empty] | Davishar |  |  |  | TS | Stair 1
[6 empty] | PH | Set HWH and Plumb (Set Submeter)
[6 empty] | PT | Trim Plumbing (Disposals/DWs)
[6 empty] | PU | Plumbing Unit R/I Domestic, Sanitary, Set Tubs
ECPF
[6 empty] | GY | Gypcrete
Green Air Mechanical
[6 empty] | GA | Set AHU
[6 empty] | GC | Above Ceiling HVAC R/I
[6 empty] | GS | Start-up HVAC
[6 empty] | GT | G/R/Ds HVAC Trim
Heritage Woodworks
[6 empty] | HC | Set Countertops
[6 empty] | HV | Set Cabinets & Vanities
Morris Steel
[6 empty] | MM | Mirrors and Toilet Accessories
Quality Building Products
[6 empty] | QC | Insulate Ceilings
[6 empty] | QP | Pre-insul & Gyp for Plumbing & Ins
Ranger
[6 empty] | SH | Sprinkler Head Escutheons
[6 empty] | SS | OH Sprinkler R/I and Hydro Ins
TBD
[6 empty] | TA | Install Appliances
Walkers
[6 empty] | WB | Ceramic Backsplash
[6 empty] | WC | Ceramic Tile (Floors & Walls)
[6 empty] | WL | LVT Flooring
[6 empty] | WP | Pad and Carpet (Protect)