## Sheet1
Phase | Location | Area | Trade | Activity Name | Color | Activity Code | Start | Finish
Pre-Construction | Precon |  | Precon Team | 28. Assign Pre excavation checklist | #632523 | PREC-1 | 2024-01-08 | 2024-01-08
Pre-Construction | Precon |  | Precon Team | 3.0 Pre construction and mobilization | #632523 | PREC-2 | 2023-09-28 | 2023-12-20
Pre-Construction | Precon |  | Precon Team | 3.0, 4.0. 5.0 pre, during and post construction total job | #632523 | PREC-3 | 2023-09-28 | 2025-05-05
Pre-Construction | Precon |  | Precon Team | Assign conrete pour checklist | #632523 | PREC-4 | 2024-09-09 | 2024-09-09
Mobilization | Mobilization |  | Mobilization Team | Assign Mobilization check list | #637B23 | MOB-1 | 2023-09-28 | 2023-12-20
Pre-Construction | Precon |  | Precon Team | Assign Equipment & Tools check list | #632523 | PREC-5 | 2023-09-28 | 2023-12-20
Pre-Construction | Precon |  | Precon Team | Assign exterior wall pre board inspection check list | #632523 | PREC-6 | 2024-11-08 | 2024-11-08
Pre-Construction | Precon |  | Precon Team | Assign Final Building Checklist | #632523 | PREC-7 | 2025-03-03 | 2025-03-03
Mobilization | Mobilization |  | Mobilization Team | Assign Site Services Planning check list | #637B23 | MOB-2 | 2023-09-28 | 2023-12-20
Mobilization | Mobilization |  | Mobilization Team | Assign Sub Contractor planning checklist | #637B23 | MOB-3 | 2023-09-28 | 2023-12-20
Pre-Construction | Precon |  | Precon Team | Assign framing check list | #632523 | PREC-8 | 2024-05-14 | 2024-05-14
Pre-Construction | Precon |  | Precon Team | Assign framing checklist | #632523 | PREC-8 | 2024-04-16 | 2024-04-16
Pre-Construction | Precon |  | Precon Team | Assign framing checklist | #632523 | PREC-8 | 2024-06-10 | 2024-06-10
Pre-Construction | Precon |  | Precon Team | Assign framing checklist | #632523 | PREC-8 | 2024-07-08 | 2024-07-08
Pre-Construction | Precon |  | Precon Team | Assign gypcrete pour checklist | #632523 | PREC-8 | 2024-11-25 | 2024-11-25
Sitework | Site |  | Site Sub | 4.1 Site Services & Foundation Work | #8064A2 | SIT- | 2023-12-21 | 2024-03-25
Sitework | Site |  | Site Sub | Site Preparation | #8064A2 | SIT- | 2023-12-21 | 2024-01-05
Sitework | Site |  | Site Sub | 18. Assign site prep check list (First) | #8064A2 | SIT- | 2023-12-28 | 2023-12-28
Foundation | Interior Bldg |  | Concrete | Assign hollow core erection checklist | #974706 | CON-1 | 2024-05-27 | 2024-05-27
Foundation | Interior Bldg |  | Concrete | Assign pre back fill check list | #974706 | CON-1 | 2024-03-01 | 2024-03-01
Pre-Construction | Precon |  | Precon Team | Assign Health and Safety checklist | #632523 | PREC-8 | 2023-09-28 | 2023-12-20
Foundation | Interior Bldg |  | Concrete | Assign pre concrete pour checklist | #974706 | CON-1 | 2024-02-27 | 2024-02-27
Pre-Construction | Precon |  | Precon Team | Assign hollow core checklist | #632523 | PREC-8 | 2024-06-13 | 2024-06-13
Foundation | Interior Bldg |  | Concrete | Assign pre concrete pour checklist | #974706 | CON-1 | 2024-07-08 | 2024-07-08
Sitework | Site |  | Site Sub | Strip site | #8064A2 | SIT- | 2023-12-29 | 2024-01-04
Foundation | Interior Bldg |  | Concrete | Assign pre concrete pour checklist | #974706 | CON-1 | 2024-12-12 | 2024-12-16
Foundation | Parkade |  | Concrete | Back fill and level parkade | #974706 | CON-2 | 2024-06-20 | 2024-06-26
Pre-Construction | Precon |  | Precon Team | Assign hollow core erection checklist | #632523 | PREC-8 | 2024-04-19 | 2024-04-19
Foundation | Interior Bldg |  | Concrete | Back fill exterior grade beam | #974706 | CON-2 | 2024-03-06 | 2024-03-07
Foundation | Interior Bldg |  | Concrete | Back fill foundation | #974706 | CON-2 | 2024-03-01 | 2024-03-14
Interior | Interior Bldg |  | Inspection | Architectural walk throughs | #C00000 | INS-2 | 2025-02-19 | 2025-02-20
Foundation | Parkade |  | Concrete | Back fill interior parkade | #974706 | CON-2 | 2024-03-08 | 2024-03-14
Foundation | Interior Bldg |  | Concrete | Build templates for Anchor bolts | #974706 | CON-3 | 2024-02-15 | 2024-02-15
Foundation | Interior Bldg |  | Concrete | Deliver pakade slab rebar | #974706 | CON-4 | 2024-06-19 | 2024-06-19
Interior | Interior Bldg |  | Inspection | Building inspector walk throughs | #C00000 | INS-3 | 2025-02-21 | 2025-02-24
Pre-Construction | Precon |  | Precon Team | Assign hollow core ordering checklist | #632523 | PREC-8 | 2023-09-28 | 2023-09-28
Foundation | Interior Bldg |  | Concrete | deliver rebar (footings and gradebeam only) | #974706 | CON-5 | 2023-12-21 | 2023-12-21
Foundation | Parkade |  | Concrete | Dig footing and parkade foot print | #974706 | CON-6 | 2024-01-08 | 2024-01-16
Foundation | Interior Bldg |  | Concrete | Ensure Sleeves for electrical are run in the grade beam prior to pouring | #974706 | CON-7 | 2024-02-06 | 2024-02-06
Foundation | Interior Bldg |  | Concrete | Excavate areas | #974706 | CON-8 | 2024-08-26 | 2024-08-27
Foundation | Interior Bldg |  | Concrete | Excavation | #974706 | CON-8 | 2024-01-08 | 2024-01-18
Foundation | Interior Bldg |  | Concrete | Exterior concrete works | #974706 | CON-9 | 2024-08-26 | 2024-12-19
Interior | Interior Bldg |  | CX | Assign water and sewer commissioning checklist | #000000 | CX- | 2024-03-25 | 2024-03-25
Foundation | Interior Bldg |  | Concrete | Form footings | #974706 | CON-10 | 2024-01-19 | 2024-01-24
Foundation | Interior Bldg |  | Concrete | Form grade beam | #974706 | CON-11 | 2024-02-06 | 2024-02-14
Foundation | Interior Bldg |  | Concrete | Foundation | #974706 | CON-12 | 2024-01-19 | 2024-02-29
Foundation | Level 2 |  | Concrete | Hollowcore 2nd floor | #974706 | CON-13 | 2024-04-16 | 2024-06-17
Foundation | Level 3 |  | Concrete | Hollowcore 3rd floor | #974706 | CON-13 | 2024-05-23 | 2024-05-28
Foundation | Level 4 |  | Concrete | Hollowcore 4th floor | #974706 | CON-13 | 2024-06-11 | 2024-06-13
Sitework | Site |  | Site Sub | Site services W/S/S install | #8064A2 | SIT- | 2024-03-15 | 2024-03-25
Pre-Construction | Precon |  | Precon Team | Assign parkade slab rough in checklist | #632523 | PREC-8 | 2024-06-27 | 2024-06-27
Sitework | Site |  | Site Sub | Install water and sewer | #8064A2 | SIT- | 2024-03-18 | 2024-03-22
Interior | Interior Bldg |  | CX | Commision Water/sewer/storm | #000000 | CX- | 2024-03-25 | 2024-03-25
Interior | Interior Bldg |  | Steel | Strucutral Steel | #A02B93 | STL-1 | 2024-03-15 | 2024-03-21
Interior | Interior Bldg |  | Steel | Structural steel erection | #A02B93 | STL-2 | 2024-03-20 | 2024-03-21
Pre-Construction | Precon |  | Precon Team | Assign Permits check list | #632523 | PREC-8 | 2023-09-28 | 2023-12-20
Sitework | Site |  | Site Sub | Structural steel delivered and sorted onsite | #8064A2 | SIT- | 2024-03-18 | 2024-03-18
Interior | Interior Bldg |  | Framing | 4.2 Framing | #F79646 | FRA- | 2024-04-11 | 2025-01-03
Interior | Interior Bldg |  | Mechanical | Mechanical rough in in slab | #4D93D9 | MCH-1 | 2024-06-12 | 2024-06-18
Interior | Interior Bldg |  | Electrical | Electrical rough in in slab | #ECD76A | ELE-1 | 2024-06-12 | 2024-06-18
Interior | Interior Bldg |  | Drywall | 4.3 Rough In, Steel Stud Drywall | #F2F3B1 | DRY-1 | 2024-08-05 | 2025-01-23
Interior | Interior Bldg |  | Inspection | Call for Electrical and Mechanical Inspection | #C00000 | INS-4 | 2025-01-23 | 2025-01-23
Foundation | Interior Bldg |  | Concrete | Install balcony piles | #974706 | CON-14 | 2023-12-25 | 2023-12-27
Foundation | Level 3 |  | Concrete | Install hollow core 3rd floor, Install backer rod & grout | #974706 | CON-15 | 2024-05-23 | 2024-05-28
Foundation | Level 4 |  | Concrete | Install hollow core 4th floor and grout | #974706 | CON-15 | 2024-06-11 | 2024-06-12
Pre-Construction | Precon |  | Precon Team | Assign post decking install check list | #632523 | PREC-8 | 2024-09-17 | 2024-09-17
Sitework | Site |  | Site Sub | Radon rock install | #8064A2 | SIT-1 | 2024-06-28 | 2024-07-01
Sitework | Site |  | Site Sub | Install poly | #8064A2 | SIT-2 | 2024-07-02 | 2024-07-02
Foundation | Level 2 |  | Concrete | Install hollowcore 2nd floor , Install backer rod & Grout 2nd floor | #974706 | CON-15 | 2024-04-16 | 2024-04-18
Foundation | Interior Bldg |  | Concrete | Install underground insulation | #E9F132 | INSU-1 | 2024-03-04 | 2024-03-05
Foundation | Interior Bldg |  | Concrete | Measure corner offsets for excavation | #974706 | CON-16 | 2024-01-05 | 2024-01-05
Interior | Interior Bldg |  | Plumbing | Deliver tubs & showers to suites / checklist | #F7C7AC | PLU-1 | 2024-07-17 | 2024-07-18
Interior | Interior Bldg |  | Vertical Flow | Install stairs | #FFF2FF | VF-1 | 2024-07-30 | 2024-07-30
Pre-Construction | Precon |  | Precon Team | Assign post landscaping checklist | #632523 | PREC-8 | 2025-05-02 | 2025-05-02
Foundation | Interior Bldg |  | Concrete | Order all Anchor bolts | #974706 | CON-17 | 2023-12-21 | 2023-12-21
Foundation | Interior Bldg |  | Concrete | Pour exterior pads | #974706 | CON-18 | 2024-09-10 | 2024-09-10
Pre-Construction | Precon |  | Precon Team | Assign pre-pour checklist | #632523 | PREC-8 | 2024-02-02 | 2024-02-02
Interior | Interior Bldg |  | Inspection | Call for Electrical and Mechanical inspection | #C00000 | INS-4 | 2024-10-31 | 2024-10-31
Interior | Interior Bldg |  | Vertical Flow | Delivery of Elevator & Install | #FFF2FF | VF-2 | 2024-10-14 | 2025-01-03
Interior | Interior Bldg |  | Cleaning | Final suite clean | #4F81BD | CL-2 | 2025-02-27 | 2025-02-28
Pre-Construction | Precon |  | Precon Team | Assign Procurement Plan check list | #632523 | PREC-8 | 2023-09-28 | 2023-12-20
Foundation | Interior Bldg |  | Concrete | Pour exterior sidewalks | #974706 | CON-19 | 2024-12-17 | 2024-12-19
Foundation | Interior Bldg |  | Concrete | Pour footings | #974706 | CON-20 | 2024-02-05 | 2024-02-05
Foundation | Interior Bldg |  | Concrete | Pour grade beam | #974706 | CON-21 | 2024-02-29 | 2024-02-29
Interior | Interior Bldg |  | Inspection | Call for envelope reviewer inspection | #C00000 | INS-5 | 2024-11-26 | 2024-11-26
Interior | Interior Bldg |  | Drywall | Assign Corridor & Stairwell pre board inspection checklist | #F2F3B1 | DRY-2 | 2024-11-28 | 2024-11-28
Pre-Construction | Precon |  | Precon Team | Assign Project Team | #632523 | PREC-8 | 2023-09-28 | 2023-12-20
Interior | Interior Bldg |  | Drywall | Assign corridor & stairwell pre board inspection checklist | #F2F3B1 | DRY-2 | 2024-11-12 | 2024-11-12
Interior | Interior Bldg |  | Drywall | Assign Corridor & Stairwell pre board inspection checklist | #F2F3B1 | DRY-2 | 2024-11-08 | 2024-11-08
Foundation | Interior Bldg |  | Concrete | Pour Gypcrete | #A6A6A6 | GYP-1 | 2024-11-25 | 2024-11-26
Foundation | Parkade |  | Concrete | Pour parakde slab | #974706 | CON-22 | 2024-06-27 | 2024-07-10
Pre-Construction | Precon |  | Precon Team | Assign roofing and water proofing checklist | #632523 | PREC-8 | 2024-08-07 | 2024-08-07
Interior | Interior Bldg |  | Drywall | Assign pre board inspection check list | #F2F3B1 | DRY-3 | 2024-11-28 | 2024-11-28
Interior | Interior Bldg |  | Drywall | Assign pre board inspection check list | #F2F3B1 | DRY-3 | 2024-11-15 | 2024-11-15
Pre-Construction | Precon |  | Precon Team | Assign Safety Equipment and Materials checklist | #632523 | PREC-8 | 2023-09-28 | 2023-12-20
Interior | Interior Bldg |  | Drywall | Assign pre board inspection checklist | #F2F3B1 | DRY-3 | 2025-01-22 | 2025-01-22
Interior | Interior Bldg |  | Drywall | Assign pre board inspection checklist | #F2F3B1 | DRY-3 | 2025-01-22 | 2025-01-22
Interior | Interior Bldg |  | Drywall | Assign pre board interior walls checklist | #F2F3B1 | DRY-3 | 2024-11-28 | 2024-11-28
Interior | Interior Bldg |  | Drywall | Assign pre board interior walls checklist | #F2F3B1 | DRY-3 | 2024-11-15 | 2024-11-15
Interior | Interior Bldg |  | Drywall | Assign pre board interior walls checklist | #F2F3B1 | DRY-3 | 2024-11-08 | 2024-11-08
Interior | Interior Bldg |  | Drywall | Board and prepare electrical/mechanical room | #F2F3B1 | DRY-4 | 2024-12-06 | 2024-12-10
Interior | Interior Bldg |  | Gypcrete | Gypcrete | #A6A6A6 | GYP-1 | 2024-11-25 | 2024-11-26
Interior | Interior Bldg |  | Finishing | 4.4 Finishing | #4EB8A4 | FIN-1 | 2024-08-09 | 2025-05-05
Exteriors | Outside Bldg |  | Windows | install windows and doors | #DAE9F8 | WIN-1 | 2024-07-08 | 2024-11-26
Interior | Interior Bldg |  | Inspection | Call for Mechanical & Electrical inspection of attic | #C00000 | INS-6 | 2024-09-04 | 2024-09-04
Pre-Construction | Precon |  | Precon Team | Assign structural steel checklist | #632523 | PREC-8 | 2024-03-15 | 2024-03-15
Interior | Interior Bldg |  | Inspection | Call for Mechanical and Electrical inspection | #C00000 | INS-6 | 2024-11-25 | 2024-11-25
Interior | Interior Bldg |  | Inspection | Call for Mechanical and Electrical Inspection | #C00000 | INS-6 | 2024-11-12 | 2024-11-12
Interior | Interior Bldg |  | Inspection | Call for structural inspection | #C00000 | INS-7 | 2024-08-20 | 2024-08-20
Exteriors | Outside Bldg |  | Exteriors | Roofing and water proofing | #4BACC6 | EXT-1 | 2024-08-07 | 2024-08-23
Pre-Construction | Precon |  | Precon Team | Assign taping inspection checklist | #632523 | PREC-8 | 2024-12-23 | 2024-12-23
Exteriors | Outside Bldg |  | Exteriors | Install roofing and water proofing | #4BACC6 | EXT-2 | 2024-08-12 | 2024-08-23
Exteriors | Outside Bldg |  | Siding | Soffit & Tower Siding | #747474 | SID-1 | 2024-09-03 | 2025-01-03
Exteriors | Outside Bldg |  | Exteriors | Building paper the whole building | #4BACC6 | EXT-3 | 2024-09-03 | 2024-11-25
Interior | Interior Bldg |  | Inspection | Contact Canada Post to get the address's created | #C00000 | INS-8 | 2025-02-14 | 2025-02-14
Pre-Construction | Precon |  | Precon Team | Assign taping inspection checklist | #632523 | PREC-8 | 2024-10-07 | 2024-10-07
Exteriors | Outside Bldg |  | Siding | Siding towers | #747474 | SID-2 | 2024-11-27 | 2024-12-16
Interior | Interior Bldg |  | Electrical | Electrical rough in in ceiling | #ECD76A | ELE-3 | 2024-08-26 | 2024-09-03
Foundation | Parkade |  | Concrete | Pour parkade floor | #974706 | CON-22 | 2024-07-09 | 2024-07-10
Foundation | Interior Bldg |  | Concrete | Rebar exterior sidewalks | #974706 | CON-23 | 2024-12-09 | 2024-12-11
Sitework | Site |  | Site Sub | Form exterior pads | #8064A2 | SIT-3 | 2024-08-28 | 2024-09-03
Foundation | Interior Bldg |  | Concrete | Survey for balcony piles | #974706 | CON-24 | 2023-12-21 | 2023-12-22
Pre-Construction | Precon |  | Precon Team | Assign taping inspection checklist | #632523 | PREC-8 | 2024-12-19 | 2024-12-19
Foundation | Interior Bldg |  | Concrete | Survey offsets, and footings | #974706 | CON-25 | 2024-01-17 | 2024-01-17
Sitework | Site |  | Site Sub | Excatae exterior sidewalks | #8064A2 | SIT-4 | 2024-09-11 | 2024-12-03
Sitework | Site |  | Site Sub | Form exterior sidewalks | #8064A2 | SIT-5 | 2024-12-04 | 2024-12-06
Foundation | Interior Bldg |  | Concrete | Tie footing rebar | #974706 | CON-26 | 2024-01-25 | 2024-01-31
Foundation | Interior Bldg |  | Concrete | Tie Grade beam rebar | #974706 | CON-27 | 2024-02-16 | 2024-02-26
Foundation | Parkade |  | Concrete | Tie parkade rebar | #974706 | CON-28 | 2024-07-03 | 2024-07-05
Interior | Interior Bldg |  | Paint | Final coat of paint | #59F3FF | PAI-2 | 2025-02-13 | 2025-02-25
Interior | Interior Bldg |  | Paint | Final coat of paint | #59F3FF | PAI-2 | 2025-02-03 | 2025-02-13
Interior | Interior Bldg |  | Paint | Final coat of paint | #59F3FF | PAI-2 | 2025-01-24 | 2025-02-05
Interior | Interior Bldg |  | Flooring | Install railings on all floors | #F9503A | FLO-8 | 2025-01-20 | 2025-02-06
Interior | Interior Bldg |  | Framing | Install metal doors and frames | #F79646 | FRA-5 | 2024-12-24 | 2025-01-06
Interior | Interior Bldg |  | Framing | Install pocket door frames | #F79646 | FRA-6 | 2024-09-06 | 2024-09-12
Interior | Interior Bldg |  | Framing | Install pocket door frames | #F79646 | FRA-6 | 2024-09-20 | 2024-09-26
Interior | Interior Bldg |  | Framing | Install pocket foor frame | #F79646 | FRA-6 | 2024-08-28 | 2024-09-03
Interior | Interior Bldg |  | Flooring | Install windows & doors all floors | #F9503A | FLO-10 | 2024-08-01 | 2024-08-13
Interior | Interior Bldg |  | Plumbing | Install tubs and showers | #F7C7AC | PLU-2 | 2024-08-30 | 2024-09-04
Interior | Interior Bldg |  | Plumbing | Install tubs and showers | #F7C7AC | PLU-2 | 2024-09-06 | 2024-09-11
Interior | Interior Bldg |  | Plumbing | Install tubs and showers | #F7C7AC | PLU-2 | 2024-09-26 | 2024-09-27
Interior | Interior Bldg |  | Electrical | Main service electrical room install | #ECD76A | ELE-4 | 2024-11-28 | 2024-12-26
Interior | Interior Bldg |  | Mechanical | Main service mechanical room install | #4D93D9 | MCH-2 | 2024-11-28 | 2025-01-22
Interior | Interior Bldg |  | Mechanical | Mechanical rough in in ceiling | #4D93D9 | MCH-4 | 2024-08-05 | 2024-08-14
Interior | Interior Bldg |  | Rough-In (General) | Rough in interior walls | #948A54 | RI-3 | 2024-11-21 | 2024-12-04
Interior | Interior Bldg |  | Sprinkler | Sprinkler install in attic | #B5E6A2 | SPR-2 | 2024-08-07 | 2024-08-21
Interior | Interior Bldg |  | Exteriors | Install exterior decking all floors | #4BACC6 | EXT-11 | 2024-09-03 | 2024-09-16
Interior | Interior Bldg |  | Sprinkler | Install underground sprinklers | #B5E6A2 | SPR-4 | 2025-04-11 | 2025-04-17
Interior | Interior Bldg |  | CX | Commision landscaping | #000000 | CX- | 2025-05-02 | 2025-05-05
Interior | Interior Bldg |  | CX | Final commissioning and deficiency | #000000 | CX- | 2025-02-14 | 2025-03-03
Interior | Interior Bldg |  | Inspection | Enginering walk throughs | #C00000 | INS-9 | 2025-02-19 | 2025-02-20
Interior | Interior Bldg |  | Inspection | Fire alarm verification | #C00000 | INS-10 | 2025-02-14 | 2025-02-17
Interior | Interior Bldg |  | Inspection | Sprinkler testing | #C00000 | INS-13 | 2025-02-14 | 2025-02-17
Interior | Interior Bldg |  | CX | Elevator commissioning | #000000 | CX- | 2025-02-14 | 2025-02-17
Exteriors | Outside Bldg |  | Siding | Assign siding checklist | #747474 | SID-3 | 2024-12-24 | 2024-12-24
Exteriors | Outside Bldg |  | Siding | Assign siding checklist | #747474 | SID-3 | 2024-12-10 | 2024-12-10
Exteriors | Outside Bldg |  | Siding | Assign siding checklist | #747474 | SID-3 | 2024-11-22 | 2024-11-22
Exteriors | Outside Bldg |  | Siding | Assign siding checklist | #747474 | SID-3 | 2024-11-06 | 2024-11-06
Pre-Construction | Precon |  | Precon Team | Assign taping inspection checklist | #632523 | PREC-8 | 2024-12-05 | 2024-12-05
Pre-Construction | Precon |  | Precon Team | Assign taping inspection checklist | #632523 | PREC-8 | 2024-11-15 | 2024-11-15
Pre-Construction | Precon |  | Precon Team | Assign taping inspection checklist | #632523 | PREC-8 | 2024-11-28 | 2024-11-28
Pre-Construction | Precon |  | Precon Team | Assign taping inspection checklist for suites | #632523 | PREC-8 | 2024-12-19 | 2024-12-19
Pre-Construction | Precon |  | Precon Team | Assign taping inspection checklist for suites | #632523 | PREC-8 | 2024-12-05 | 2024-12-05
Pre-Construction | Precon |  | Precon Team | Assign tower siding checklist | #632523 | PREC-8 | 2024-11-26 | 2024-11-26
Pre-Construction | Precon |  | Precon Team | Assign water and sewer and storm checklist | #632523 | PREC-8 | 2024-03-15 | 2024-03-15
Pre-Construction | Precon |  | Precon Team | Assign window & door installation checklist | #632523 | PREC-8 | 2024-07-08 | 2024-07-08
Interior | Interior Bldg |  | COO | Prepare occupancy paperwork | #D9D9D9 | COO-1 | 2025-02-25 | 2025-02-26
Interior | Interior Bldg |  | COO | Receive occupancy | #D9D9D9 | COO-2 | 2025-02-27 | 2025-02-28
Interior | Interior Bldg |  | COO | Move in dates confirmed | #D9D9D9 | COO-3 | 2025-03-03 | 2025-03-03
Interior | Interior Bldg |  | COO | 5.0 Sales, Occupancy, Closings | #D9D9D9 | COO-4 | 2025-03-03 | 2025-05-01
Interior | Interior Bldg |  | COO | Pre sale move in dates confirmed | #D9D9D9 | COO-5 | 2025-03-03 | 2025-03-03
Interior | Interior Bldg |  | CX | Finalize home owner extras | #000000 | CX-1 | 2025-03-04 | 2025-03-10
Exteriors | Level 2 |  | Exteriors | Board exterior walls on 2nd and sheds | #4BACC6 | EXT-4 | 2024-11-28 | 2024-12-04
Exteriors | Parkade |  | Exteriors | Board parkade exterior walls and sheds | #4BACC6 | EXT-5 | 2024-12-09 | 2024-12-09
Exteriors | Parkade |  | Exteriors | Board Parkade interior walls | #4BACC6 | EXT-6 | 2024-12-10 | 2024-12-13
Interior | Interior Bldg |  | CX | Load home owners into copper | #000000 | CX-2 | 2025-03-04 | 2025-03-04
Interior | Interior Bldg |  | CX | Move in binders created | #000000 | CX-3 | 2025-03-04 | 2025-03-10
Interior | Interior Bldg |  | CX | Update home owner permissions in Construction online | #000000 | CX-4 | 2025-03-04 | 2025-03-04
Interior | Interior Bldg |  | CX | Unit Commissioning Inspection list | #000000 | CX-5 | 2025-03-04 | 2025-03-10
Interior | Interior Bldg |  | Cleaning | Unit Commissioning deficiency clean up confirmed | #4F81BD | CL-3 | 2025-03-11 | 2025-03-17
Interior | Interior Bldg |  | Cleaning | Building close out cleanup deficiencies confirmed | #4F81BD | CL-4 | 2025-03-05 | 2025-03-11
Interior | Interior Bldg |  | CX | Keys and gift cards and welcome package created | #000000 | CX-6 | 2025-03-04 | 2025-03-10
Interior | Interior Bldg |  | CX | Home owner walk through and punch list | #000000 | CX-7 | 2025-03-11 | 2025-03-11
Interior | Interior Bldg |  | Cleaning | Home owner walk through punch list clean up | #4F81BD | CL-5 | 2025-03-12 | 2025-03-18
Interior | Interior Bldg |  | CX | New move ins and warranty through service manager | #000000 | CX-8 | 2025-03-04 | 2025-05-01
Interior | Interior Bldg |  | CX | Send out contractor surveys | #000000 | CX-9 | 2025-03-05 | 2025-03-05
Interior | Interior Bldg |  | CX | Schedule 1 on 1 contractor review meetings | #000000 | CX-10 | 2025-03-06 | 2025-03-12
Pre-Construction | Precon |  | Precon Team | Building close out check list | #632523 | PREC-9 | 2025-03-04 | 2025-03-04
Interior | Interior Bldg |  | CX | Schedule contractor group meeting to review survey results | #000000 | CX-11 | 2025-03-06 | 2025-03-12
Foundation | Interior Bldg |  | Concrete | Tie rebar exterior pads | #974706 | CON-29 | 2024-09-04 | 2024-09-06
Interior | Interior Bldg |  | CX | Project post mordem internal | #000000 | CX-12 | 2025-03-13 | 2025-03-13
Interior | Interior Bldg |  | CX | Move info to Dev co work flow 1.0, 2.0, 6.0 | #000000 | CX-13 | 2025-03-18 | 2025-03-18
Interior | Level 1 | Common Areas | Cleaning | Construction clean on 1 | #4F81BD | CL-1 | 2025-02-14 | 2025-02-18
Interior | Level 1 | Common Areas | Cleaning | Final suite clean on 1 | #4F81BD | CL-2 | 2025-02-20 | 2025-02-24
Interior | Level 1 | Common Areas | CX | Assign Unit Commissioning Inspection list on 1 | #000000 | CX- | 2025-02-19 | 2025-02-19
Interior | Level 1 | Ceilings | Finishing | Ceiling texture on 1 | #4EB8A4 | FIN-2 | 2025-01-02 | 2025-01-03
Interior | Level 1 | Electrical Systems | Electrical | Electrical finishing on 1 | #ECD76A | ELE-2 | 2025-02-11 | 2025-02-13
Pre-Construction | Precon | Cabinets | Precon Team | Building handover (PM to SM) checklist | #632523 | PREC-10 | 2025-03-04 | 2025-03-10
Exteriors | Outside Bldg | Attic | Exteriors | Blow in attic insulation | #4BACC6 | EXT-7 | 2024-09-18 | 2024-09-20
Interior | Level 1 | Cabinets | Finishing | finishing parkade level 1 | #4EB8A4 | FIN-3 | 2025-01-02 | 2025-02-24
Interior | Level 1 | Flooring | Flooring | Install flooring on 1 | #F9503A | FLO-7 | 2025-01-15 | 2025-01-16
Interior | Level 1 | Cabinets | Carpentry | Install cabinets on 1 | #964100 | CAR-2 | 2025-01-17 | 2025-01-20
Interior | Level 1 | Countertops | Carpentry | Install countertops on 1 | #964100 | CAR-3 | 2025-02-10 | 2025-02-10
Interior | Level 1 | Doors and Frames | Carpentry | Install interior doors and case on 1 | #964100 | CAR-4 | 2025-01-08 | 2025-01-09
Sitework | Site | Survey | Site Sub | Call the surveyor to measure for condo plan | #8064A2 | SIT-6 | 2024-10-29 | 2024-10-31
Interior | Level 1 | Doors and Frames | Framing | Install suite entry doors and frames and Interior doors, trims and jambs | #F79646 | FRA-7 | 2024-12-23 | 2025-01-03
Interior | Level 1 | Doors and Frames | Framing | Install suite entry doors and frames and Interior doors, trims and jambs | #F79646 | FRA-7 | 2024-12-09 | 2024-12-13
Interior | Level 1 | Doors and Frames | Framing | Install suite entry doors and frames and Interior doors, trims and jambs | #F79646 | FRA-7 | 2024-12-02 | 2024-12-06
Interior | Level 1 | Mechanical Systems | Mechanical | Mechanical finishing on 1 | #4D93D9 | MCH-3 | 2025-02-11 | 2025-02-13
Interior | Level 1 | Fire Systems | Paint | Paint 1rst coat of color on 1 | #59F3FF | PAI-3 | 2025-01-10 | 2025-01-16
Interior | Level 1 | Structural | Paint | Prime paint on 1 | #59F3FF | PAI-4 | 2025-01-03 | 2025-01-07
Interior | Level 1 | Closets | Carpentry | Spray out closet interiors and trim on 1 | #964100 | CAR-6 | 2025-01-10 | 2025-01-10
Interior | Level 1 | Hallways and Stairwells | Sprinkler | Sprinkler finishing on 1 | #B5E6A2 | SPR-1 | 2025-02-11 | 2025-02-13
Interior | Level 2 | Flooring | Framing | Framing 2nd floor | #F79646 | FRA- | 2024-04-19 | 2024-05-14
Interior | Level 2 | Flooring | Framing | Frame 2nd floor | #F79646 | FRA- | 2024-04-19 | 2024-05-13
Interior | Level 2 | Hallways and Stairwells | Flooring | 2nd floor - Taper do the rectification of deficiences | #F9503A | FLO-2 | 2024-12-23 | 2024-12-23
Interior | Level 2 | Countertops | Flooring | 2nd floor counter top measurement for template | #F9503A | FLO-3 | 2025-01-16 | 2025-01-20
Interior | Level 2 | Flooring | Flooring | 2nd floor finishing | #F9503A | FLO-4 | 2024-12-16 | 2025-02-28
Interior | Level 2 | Hallways and Stairwells | Cleaning | Construction clean 2nd floor | #4F81BD | CL-1 | 2025-02-24 | 2025-02-27
Interior | Level 2 | Common Areas | CX | Assign Unit Commissioning Inspection list 2nd floor | #000000 | CX- | 2025-02-27 | 2025-02-27
Interior | Level 2 | Common Areas | Framing | Back framing on 2nd | #F79646 | FRA-1 | 2024-08-21 | 2024-08-27
Interior | Level 2 | Hallways and Stairwells | Drywall | Board 2nd floor hallways and stairwells | #F2F3B1 | DRY-4 | 2024-11-28 | 2024-12-04
Interior | Level 2 | Walls | Drywall | Board 2nd floor walls | #F2F3B1 | DRY-4 | 2024-11-28 | 2024-12-04
Interior | Level 2 | Walls / Ceilings | Drywall | Board upper 16" strips in common area and all suites on 2nd | #F2F3B1 | DRY-4 | 2024-08-30 | 2024-09-04
Interior | Level 2 | Walls / Ceilings | Drywall | Fire tape / Fire caulk upper strips on 2nd | #F2F3B1 | DRY-5 | 2024-11-25 | 2024-11-25
Interior | Level 2 | Ceilings | Framing | Frame drops on 2nd | #F79646 | FRA-3 | 2024-11-26 | 2024-12-02
Interior | Level 2 | Flooring | Flooring | Core floors begin at 2nd | #F9503A | FLO-5 | 2024-07-24 | 2024-07-26
Interior | Level 2 | Cabinets | Carpentry | Install cabinets 2nd floor | #964100 | CAR-6 | 2025-01-13 | 2025-01-17
Interior | Level 2 | Suites | Drywall | Layout suites on 2nd floor | #F2F3B1 | DRY-7 | 2024-07-18 | 2024-07-22
Interior | Level 2 | Flooring | Flooring | Install flooring 2nd floor | #F9503A | FLO-7 | 2025-01-08 | 2025-01-16
Interior | Level 2 | Ceilings | Finishing | Ceiling texture on 2nd | #4EB8A4 | FIN-2 | 2024-12-16 | 2024-12-17
Interior | Level 2 | Electrical Systems | Electrical | Electrical finishing 2nd floor | #ECD76A | ELE-2 | 2025-02-07 | 2025-02-13
Interior | Level 2 | Hallways and Stairwells | Electrical | Electrical rough in hallways & stairwells on 2nd | #ECD76A | ELE-3 | 2024-11-08 | 2024-11-22
Interior | Level 2 | Suites | Electrical | Electrical rough in on 2nd | #ECD76A | ELE-3 | 2024-11-08 | 2024-11-22
Interior | Level 2 | Base and Hardware | Carpentry | Install base and hardware 2nd floor | #964100 | CAR-1 | 2025-01-17 | 2025-01-24
Interior | Level 2 | Doors and Frames | Carpentry | Install interior doors and case on 2nd | #964100 | CAR-4 | 2024-12-23 | 2025-01-03
Interior | Level 2 | Countertops | Carpentry | Manufacturing and Install countertops 2nd floor | #964100 | CAR-5 | 2025-01-21 | 2025-02-07
Interior | Level 2 | Mechanical Systems | Mechanical | Mechanical finishing 2nd floor | #4D93D9 | MCH-3 | 2025-02-07 | 2025-02-13
Interior | Level 2 | Hallways and Stairwells | Mechanical | Mechanical rough in hallways & stairwells on 2nd | #4D93D9 | MCH-4 | 2024-11-01 | 2024-11-15
Interior | Level 2 | Suites | Mechanical | Mechanical rough in on 2nd | #4D93D9 | MCH-4 | 2024-11-01 | 2024-11-15
Interior | Level 2 | Fire Systems | Paint | Paint 1st coat of color 2nd floor | #59F3FF | PAI-3 | 2024-12-27 | 2025-01-03
Interior | Level 2 | Fire Systems | Paint | Prime paint on 2nd | #59F3FF | PAI-4 | 2024-12-18 | 2024-12-23
Interior | Level 2 | Suites | Rough-In (General) | Rough in 2nd floor | #948A54 | RI-1 | 2024-08-12 | 2025-01-03
Interior | Level 2 | Fire Systems | Sprinkler | Sprinkler finishing 2nd floor | #B5E6A2 | SPR-1 | 2025-02-07 | 2025-02-13
Interior | Level 2 | Hallways and Stairwells | Sprinkler | Sprinkler rough in corridor & stairwells on 2nd | #B5E6A2 | SPR-3 | 2024-08-26 | 2024-09-06
Interior | Level 2 | Suites | Sprinkler | Sprinkler rough in on 2nd | #B5E6A2 | SPR-3 | 2024-08-26 | 2024-09-06
Interior | Level 2 | Walls / Ceilings | Drywall | Steel stud install on 2nd & drywall behind the tubs including fire wall taping if it is a fire wall | #F2F3B1 | DRY-9 | 2024-08-12 | 2024-08-29
Interior | Level 2 | Hallways and Stairwells | Drywall | Tape 2nd floor hallways and stair wells | #F2F3B1 | DRY-11 | 2024-12-05 | 2024-12-19
Interior | Level 2 | Suites | Drywall | Tape suites on 2nd | #F2F3B1 | DRY-10 | 2024-12-05 | 2024-12-19
Interior | Level 2 | Bathrooms | Plumbing | Water dams 2nd floor | #F7C7AC | PLU-3 | 2024-08-19 | 2024-08-23
Interior | Level 3 | Flooring | Framing | Framing 3rd floor | #F79646 | FRA- | 2024-05-28 | 2024-07-26
Interior | Level 3 | Flooring | Framing | Frame 3rd floor | #F79646 | FRA- | 2024-05-28 | 2024-06-07
Interior | Level 3 | Suites | Framing | Layout suites on 3rd floor | #F79646 | FRA- | 2024-07-23 | 2024-07-26
Interior | Level 3 | Walls / Ceilings | Flooring | 3rd floor - Taper do the rectification of deficiencies | #F9503A | FLO-2 | 2024-12-10 | 2024-12-10
Interior | Level 3 | Countertops | Flooring | 3rd floor counter top measurement for template | #F9503A | FLO- | 2025-01-08 | 2025-01-10
Interior | Level 3 | Flooring | Flooring | 3rd floor finishing | #F9503A | FLO-3 | 2024-12-02 | 2025-02-18
Interior | Level 3 | Common Areas | Cleaning | Construction clean on 3rd | #4F81BD | CL-1 | 2025-02-11 | 2025-02-17
Interior | Level 3 | Common Areas | Cleaning | Final suite clean on 3rd | #4F81BD | CL-2 | 2025-02-17 | 2025-02-18
Interior | Level 3 | Common Areas | CX | Assign Unit Commissioning Inspection list on 3rd | #000000 | CX- | 2025-02-17 | 2025-02-17
Interior | Level 3 | Flooring | Flooring | Core floor beings at 3rd floor | #F9503A | FLO-5 | 2024-07-29 | 2024-07-31
Interior | Level 3 | Hallways and Stairwells | Framing | Back framing on 3rd | #F79646 | FRA-1 | 2024-09-10 | 2024-09-16
Interior | Level 3 | Walls / Ceilings | Drywall | Board upper 16" strips in common area & all suites on 3rd | #F2F3B1 | DRY-4 | 2024-09-11 | 2024-09-16
Interior | Level 3 | Walls / Ceilings | Drywall | Fire tape / Fire caulk upper strips on 3rd | #F2F3B1 | DRY-5 | 2024-11-11 | 2024-11-11
Interior | Level 3 | Ceilings | Framing | Frame drops on 3rd | #F79646 | FRA-3 | 2024-11-12 | 2024-11-18
Interior | Level 3 | Ceilings | Finishing | Ceiling texture on 3rd | #4EB8A4 | FIN-2 | 2024-12-02 | 2024-12-03
Interior | Level 3 | Electrical Systems | Electrical | Electrical finishing on 3rd | #ECD76A | ELE-2 | 2025-01-29 | 2025-02-04
Interior | Level 3 | Hallways and Stairwells | Electrical | Electrical rough in hallways & stairwells on 3rd | #ECD76A | ELE-3 | 2024-10-28 | 2024-11-08
Interior | Level 3 | Suites | Electrical | Electrical rough in on 3rd | #ECD76A | ELE-3 | 2024-10-28 | 2024-11-08
Interior | Level 3 | Base and Hardware | Carpentry | Install base and hardware on 3rd | #964100 | CAR-1 | 2025-01-08 | 2025-01-13
Interior | Level 3 | Cabinets | Carpentry | Install cabinets on 3rd | #964100 | CAR-2 | 2024-12-18 | 2025-01-10
Interior | Level 3 | Flooring | Flooring | Install flooring on 3rd | #F9503A | FLO-7 | 2024-12-17 | 2025-01-07
Interior | Level 3 | Doors and Frames | Carpentry | Install interior doors and case on 3rd | #964100 | CAR-4 | 2024-12-09 | 2024-12-13
Interior | Level 3 | Walls / Ceilings | Drywall | Load boards on floor and Board 3rd floor walls | #F2F3B1 | DRY-8 | 2024-11-15 | 2024-11-22
Interior | Level 3 | Walls / Ceilings | Drywall | Load boards on floor and Board exterior walls on 3rd and sheds | #F2F3B1 | DRY-8 | 2024-11-15 | 2024-11-22
Interior | Level 3 | Hallways and Stairwells | Drywall | Load the board on floor and Board 3rd floor hallways and stairwells | #F2F3B1 | DRY-8 | 2024-11-15 | 2024-11-22
Interior | Level 3 | Countertops | Carpentry | Manufacturing and Install countertops on 3rd | #964100 | CAR-5 | 2025-01-10 | 2025-01-29
Interior | Level 3 | Mechanical Systems | Mechanical | Mechanical finishing on 3rd | #4D93D9 | MCH-3 | 2025-01-29 | 2025-02-04
Interior | Level 3 | Hallways and Stairwells | Mechanical | Mechanical rough in hallways & stairwells on 3rd | #4D93D9 | MCH-4 | 2024-10-28 | 2024-11-07
Sitework | Parkade | Mechanical Systems | Site Sub | Parkade - Measurement for template | #8064A2 | SIT-7 | 2025-01-21 | 2025-01-21
Sitework | Parkade | Paint | Site Sub | Parkade - Taper to rectify deficiencies | #8064A2 | SIT-8 | 2025-01-07 | 2025-01-07
Interior | Level 3 | Suites | Mechanical | Mechanical rough in on 3rd | #4D93D9 | MCH-4 | 2024-10-28 | 2024-11-07
Exteriors | Level 2 | Walls / Ceilings | Insulation | Poly and insulate on 2nd exterior walls | #E9F132 | INSU-1 | 2024-11-25 | 2024-11-28
Exteriors | Level 3 | Walls / Ceilings | Insulation | Poly and insulate on 3rd exterior walls | #E9F132 | INSU-1 | 2024-11-12 | 2024-11-15
Exteriors | Level 4 | Walls / Ceilings | Insulation | Poly and insulate on 4th exterior walls | #E9F132 | INSU-1 | 2024-11-05 | 2024-11-07
Exteriors | Parkade | Walls / Ceilings | Insulation | Poly and insulate parkade exterior walls | #E9F132 | INSU-2 | 2024-08-22 | 2024-08-23
Interior | Level 3 | Fire Systems | Paint | Paint 1st coat of color on 3rd | #59F3FF | PAI-3 | 2024-12-12 | 2024-12-17
Interior | Level 3 | Walls / Ceilings | Paint | Prime paint on 3rd | #59F3FF | PAI-4 | 2024-12-05 | 2024-12-10
Interior | Level 3 | Suites | Rough-In (General) | Rough in 3rd floor | #948A54 | RI-1 | 2024-08-19 | 2024-12-13
Interior | Level 3 | Closets | Carpentry | Spray out closet interiors and trim on 3rd | #964100 | CAR-6 | 2024-12-12 | 2024-12-17
Interior | Level 3 | Fire Systems | Sprinkler | Sprinkler finishing on 3rd | #B5E6A2 | SPR-1 | 2025-01-29 | 2025-02-04
Interior | Level 3 | Hallways and Stairwells | Sprinkler | Sprinkler rough in hallways & stairwells on 3rd | #B5E6A2 | SPR-3 | 2024-09-09 | 2024-09-20
Interior | Level 3 | Suites | Sprinkler | Sprinkler rough in on 3rd | #B5E6A2 | SPR-3 | 2024-09-09 | 2024-09-20
Interior | Level 3 | Walls / Ceilings | Drywall | Steel stud install on 3rd & drywall behind the tubs including fire wall taping if it is a fire wall | #F2F3B1 | DRY-9 | 2024-08-30 | 2024-09-05
Exteriors | Parkade | Walls / Ceilings | Rough-In (General) | Rough in exterior walls - parkade and sheds | #948A54 | RI-2 | 2024-11-18 | 2024-12-06
Exteriors | Level 2 | Walls / Ceilings | Rough-In (General) | Rough in exterior walls on 2nd and sheds | #948A54 | RI-2 | 2024-11-08 | 2024-11-21
Exteriors | Level 3 | Walls / Ceilings | Rough-In (General) | Rough in exterior walls on 3rd and sheds | #948A54 | RI-2 | 2024-10-28 | 2024-11-08
Interior | Level 3 | Hallways and Stairwells | Drywall | Tape 3rd floor hallways and stair wells | #F2F3B1 | DRY-11 | 2024-11-22 | 2024-12-05
Interior | Level 3 | Suites | Drywall | Tape suites on 3rd | #F2F3B1 | DRY-10 | 2024-11-22 | 2024-12-05
Exteriors | Parkade | Parkade | Rough-In (General) | Rough in Parkade | #948A54 | RI-4 | 2024-08-19 | 2025-01-23
Exteriors | Level 2 | Walls / Ceilings | Siding | Siding 2nd floor | #747474 | SID-4 | 2024-11-22 | 2024-12-09
Exteriors | Level 3 | Walls / Ceilings | Siding | Siding 3rd floor | #747474 | SID-4 | 2024-11-06 | 2024-11-21
Exteriors | Level 4 | Walls / Ceilings | Siding | Siding 4th floor | #747474 | SID-4 | 2024-10-21 | 2024-11-05
Exteriors | Parkade | Walls / Ceilings | Siding | Siding parkade level | #747474 | SID-4 | 2024-12-10 | 2024-12-23
Interior | Level 3 | Bathrooms | Plumbing | Water dams 3rd floor | #F7C7AC | PLU-3 | 2024-08-19 | 2024-08-23
Interior | Level 4 | Framing | Inspection | 4th floor framing inspection | #C00000 | INS-1 | 2024-11-04 | 2024-11-04
Interior | Level 4 | Walls / Ceilings | Framing | Framing 4th floor | #F79646 | FRA- | 2024-06-19 | 2024-07-31
Interior | Level 4 | Walls / Ceilings | Framing | Frame 4th floor | #F79646 | FRA- | 2024-06-19 | 2024-07-05
Interior | Level 4 | Common Areas | Cleaning | Construction clean on 4th | #4F81BD | CL-1 | 2025-02-03 | 2025-02-07
Interior | Level 4 | Suites | Cleaning | Final suite clean on 4th | #4F81BD | CL-2 | 2025-02-07 | 2025-02-10
Interior | Level 4 | Walls / Ceilings | Flooring | 4th floor - Taper do the rectification of deficiencies | #F9503A | FLO-2 | 2024-12-02 | 2024-12-03
Interior | Level 4 | Countertops | Flooring | 4th floor counter top measurements for template | #F9503A | FLO-4 | 2024-12-17 | 2024-12-19
Interior | Level 4 | Common Areas | Framing | Back framing on 4th | #F79646 | FRA-1 | 2024-09-23 | 2024-09-27
Interior | Level 4 | Walls / Ceilings | Drywall | Board upper 16" strips in common area and all suites on 4th | #F2F3B1 | DRY-4 | 2024-09-27 | 2024-10-02
Interior | Level 4 | Fire Systems | Drywall | Fire tape / Fire caulk upper strips on 4th | #F2F3B1 | DRY-5 | 2024-11-01 | 2024-11-01
Interior | Level 4 | Ceilings | Framing | Frame drops on 4th | #F79646 | FRA-3 | 2024-11-29 | 2024-12-05
Interior | Level 4 | Ceilings | Drywall | Install drywall on 4th floor ceiling | #F2F3B1 | DRY-6 | 2024-09-11 | 2024-09-17
Interior | Level 4 | Flooring | Flooring | Core floor beings at 4th floor | #F9503A | FLO-5 | 2024-08-01 | 2024-08-02
Interior | Level 4 | Exterior Walls | Flooring | Install fascia and soffit 4th floor | #F9503A | FLO-6 | 2024-11-15 | 2024-11-25
Interior | Level 4 | Ceilings | Finishing | Ceiling texture on 4th | #4EB8A4 | FIN-2 | 2024-11-26 | 2024-11-27
Interior | Level 4 | Electrical Systems | Electrical | Electrical finishing on 4th | #ECD76A | ELE-2 | 2025-01-21 | 2025-01-27
Interior | Level 4 | Hallways and Stairwells | Electrical | Electrical rough in hallways stairwells on 4th | #ECD76A | ELE-3 | 2024-10-21 | 2024-10-31
Interior | Level 4 | Suites | Electrical | Electrical rough in on 4th | #ECD76A | ELE-3 | 2024-10-21 | 2024-10-31
Interior | Level 4 | Suites | Finishing | finishing on 4th | #4EB8A4 | FIN-3 | 2024-11-26 | 2025-02-10
Interior | Level 4 | Base and Hardware | Carpentry | Install base and hardware on 4th | #964100 | CAR-1 | 2024-12-20 | 2025-01-03
Interior | Level 4 | Cabinets | Carpentry | Install cabinets on 4th | #964100 | CAR-2 | 2024-12-11 | 2024-12-18
Interior | Level 4 | Flooring | Flooring | Install flooring on 4th | #F9503A | FLO-7 | 2024-12-09 | 2024-12-16
Interior | Level 4 | Ceilings | Flooring | Install sound bar 4th floor | #F9503A | FLO-9 | 2024-09-09 | 2024-09-10
Interior | Level 4 | Doors and Frames | Carpentry | Install interior doors and case on 4th | #964100 | CAR-4 | 2024-12-02 | 2024-12-06
Interior | Level 4 | Hallways and Stairwells | Drywall | Load the board on floor and Board 4th floor hallways and stairwells | #F2F3B1 | DRY-8 | 2024-11-08 | 2024-11-15
Interior | Level 4 | Walls / Ceilings | Drywall | Load the board on floor and Board 4th floor walls | #F2F3B1 | DRY-8 | 2024-11-08 | 2024-11-15
Interior | Level 4 | Exterior Walls | Drywall | Load the board on floor and Board exterior walls on 4th and sheds | #F2F3B1 | DRY-8 | 2024-11-08 | 2024-11-15
Interior | Level 4 | Countertops | Carpentry | manufacturing and Install countertops on 4th | #964100 | CAR-5 | 2025-01-02 | 2025-01-21
Exteriors | Outside Bldg | Mechanical Systems | Exteriors | Exterior | #4BACC6 | EXT-8 | 2024-08-09 | 2025-05-05
Exteriors | Outside Bldg | Balconies | Exteriors | Grind all balconys smooth | #4BACC6 | EXT-9 | 2024-08-09 | 2024-08-22
Interior | Level 4 | Suites | Mechanical | Mechanical finishing on 4th | #4D93D9 | MCH-3 | 2025-01-21 | 2025-01-27
Pre-Construction | Precon | Mobilization | Precon Team | De mobilization (checklist) | #632523 | PREC-11 | 2025-03-05 | 2025-03-11
Interior | Level 4 | Hallways and Stairwells | Mechanical | Mechanical rough in hallways stairwells on 4th | #4D93D9 | MCH-4 | 2024-10-21 | 2024-10-25
Sitework | Landscaping | Landscaping | Site Sub | Rough grade landscaping | #8064A2 | SIT-9 | 2025-04-04 | 2025-04-10
Interior | Level 4 | Suites | Mechanical | Mechanical rough in on 4th | #4D93D9 | MCH-4 | 2024-10-21 | 2024-10-25
Sitework | Landscaping | Landscaping | Site Sub | Install landscaping | #8064A2 | SIT-10 | 2025-04-18 | 2025-05-01
Interior | Level 4 | Closets | Paint | Paint 1st coat of color on 4th | #59F3FF | PAI-3 | 2024-12-05 | 2024-12-10
Sitework | Landscaping | Signage | Site Sub | Install building signage | #8064A2 | SIT-11 | 2025-02-28 | 2025-02-28
Pre-Construction | Precon | Commissioning | Precon Team | Hold Pre Kick-Off meeting with Engineers and Trades people | #632523 | PREC-12 | 2023-09-28 | 2023-10-02
Interior | Level 4 | Suites | Flooring | Layout suites 4th floor | #F9503A | FLO-11 | 2024-07-29 | 2024-08-01
Interior | Level 4 | Fire Systems | Paint | Prime paint on 4th | #59F3FF | PAI-4 | 2024-11-28 | 2024-12-03
Interior | Level 4 | Suites | Rough-In (General) | Rough in 4th floor | #948A54 | RI-1 | 2024-08-19 | 2024-12-06
Foundation | Interior Bldg | Ceilings | Inspection | Geo Tech Engineer inspection | #C00000 | INS-11 | 2024-01-18 | 2024-01-18
Exteriors | Level 3 | Exterior Walls | Exteriors | Organize 3rd party building exterior review, including roof, siding and flashings | #4BACC6 | EXT-10 | 2025-02-19 | 2025-02-19
Foundation | Interior Bldg | Walls / Ceilings | Inspection | Rebar Inspection Structural Engineer | #C00000 | INS-12 | 2024-02-01 | 2024-02-01
Foundation | Interior Bldg | Bathrooms | Inspection | Rebar inspection Structural Engineer | #C00000 | INS-12 | 2024-02-28 | 2024-02-28
Interior | Level 4 | Ceilings | Rough-In (General) | Rough in 4th floor ceiling | #948A54 | RI-1 | 2024-08-05 | 2024-10-07
Interior | Level 4 | Exterior Walls | Rough-In (General) | Rough in exterior walls on 4th and sheds | #948A54 | RI-2 | 2024-10-21 | 2024-10-31
Interior | Level 4 | Closets | Carpentry | Spray out closet interiors and trim on 4th | #964100 | CAR-6 | 2024-12-05 | 2024-12-10
Interior | Level 4 | Fire Systems | Sprinkler | Sprinkler finishing on 4th | #B5E6A2 | SPR-1 | 2025-01-21 | 2025-01-27
Interior | Level 4 | Common Areas | CX | Assign Unit Commissioning Inspection list on 4th | #000000 | CX- | 2025-02-07 | 2025-02-07
Pre-Construction | Precon | Structural | Precon Team | Order Rebar (30 days before site delivery date required) | #632523 | PREC-13 | 2023-12-08 | 2023-12-08
Interior | Level 4 | Hallways and Stairwells | Sprinkler | Sprinkler rough in hallways stairwells on 4th | #B5E6A2 | SPR-3 | 2024-09-23 | 2024-09-30
Interior | Level 4 | Suites | Sprinkler | Sprinkler rough in on 4th | #B5E6A2 | SPR-3 | 2024-09-23 | 2024-09-30
Interior | Level 4 | Walls / Ceilings | Drywall | Steel stud install on 4th & drywall behind the tubs including fire wall taping if it is a fire wall | #F2F3B1 | DRY-9 | 2024-09-18 | 2024-09-26
Interior | Level 4 | Ceilings | Drywall | Tape 4th floor ceiling | #F2F3B1 | DRY-11 | 2024-09-23 | 2024-10-04
Interior | Level 4 | Hallways and Stairwells | Drywall | Tape 4th floor hallways and stair wells | #F2F3B1 | DRY-11 | 2024-11-15 | 2024-11-28
Interior | Level 4 | Suites | Drywall | Tape suites on 4th | #F2F3B1 | DRY-10 | 2024-11-15 | 2024-11-28
Interior | Level 4 | Bathrooms | Plumbing | Water dams 4th floor | #F7C7AC | PLU-3 | 2024-08-19 | 2024-08-23
Interior | Level 4 | Ceilings | Flooring | Poly 4th floor ceiling | #F9503A | FLO-12 | 2024-09-05 | 2024-09-06
Pre-Construction | Precon | Training | Precon Team | Organize site team to have training and certificates | #632523 | PREC-14 | 2023-09-28 | 2023-09-28
Interior | Parkade | Parkade | Rough-In (General) | Rough in parkade slab | #948A54 | RI-1 | 2024-06-12 | 2024-06-26
Pre-Construction | Precon | Locates | Precon Team | Schedule locates to be done | #632523 | PREC-15 | 2023-12-21 | 2023-12-27
Pre-Construction | Precon | Pile Contractor | Precon Team | Schedule Pile contractor | #632523 | PREC-16 | 2023-12-21 | 2023-12-21
Interior | Parkade | Parkade | Framing | Framing parkade | #F79646 | FRA- | 2024-04-11 | 2024-04-16
Interior | Parkade | Parkade | Framing | Frame parkade level | #F79646 | FRA- | 2024-04-11 | 2024-04-15
Interior | Parkade | Ceilings | Paint | Paint underside of ceiling in parkade | #59F3FF | PAI-1 | 2024-06-17 | 2024-06-17
Interior | Parkade | Parkade | Framing | Frame and board Parkade beams | #F79646 | FRA-2 | 2024-12-16 | 2024-12-20
Interior | Parkade | Parkade | Framing | Frame interior parkade walls | #F79646 | FRA-4 | 2024-08-19 | 2024-08-23
Interior | Parkade | Parkade | Drywall | Tape parkade interior and exterior walls | #F2F3B1 | DRY-10 | 2024-12-13 | 2024-12-23
Interior | Roof | Roof | Framing | Roof trusses install | #F79646 | FRA- | 2024-07-09 | 2024-08-20
Interior | Roof | Roof | Framing | Install roof trusses and sheeting and towers | #F79646 | FRA- | 2024-07-09 | 2024-08-06
Interior | Roof | Roof | Framing | Assign roof trusses framing checklist | #F79646 | FRA- | 2024-08-07 | 2024-08-07

## CFA - Schedule
|  |  | 2023 | [94 empty] | 2024 | [365 empty] | 2025
|  |  | Sep |  |  | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [28 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May
|  |  | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05
phase | location | area | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
Mobilization | Mobilization | N/A | Sep 28: MOB-1; Sep 29: MOB-1; Sep 30: MOB-1; Oct 01: MOB-1; Oct 02: MOB-1; Oct 03: MOB-1; Oct 04: MOB-1; Oct 05: MOB-1; Oct 06: MOB-1; Oct 07: MOB-1; Oct 08: MOB-1; Oct 09: MOB-1; Oct 10: MOB-1; Oct 11: MOB-1; Oct 12: MOB-1; Oct 13: MOB-1; Oct 14: MOB-1; Oct 15: MOB-1; Oct 16: MOB-1; Oct 17: MOB-1; Oct 18: MOB-1; Oct 19: MOB-1; Oct 20: MOB-1; Oct 21: MOB-1; Oct 22: MOB-1; Oct 23: MOB-1; Oct 24: MOB-1; Oct 25: MOB-1; Oct 26: MOB-1; Oct 27: MOB-1; Oct 28: MOB-1; Oct 29: MOB-1; Oct 30: MOB-1; Oct 31: MOB-1; Nov 01: MOB-1; Nov 02: MOB-1; Nov 03: MOB-1; Nov 04: MOB-1; Nov 05: MOB-1; Nov 06: MOB-1; Nov 07: MOB-1; Nov 08: MOB-1; Nov 09: MOB-1; Nov 10: MOB-1; Nov 11: MOB-1; Nov 12: MOB-1; Nov 13: MOB-1; Nov 14: MOB-1; Nov 15: MOB-1; Nov 16: MOB-1; Nov 17: MOB-1; Nov 18: MOB-1; Nov 19: MOB-1; Nov 20: MOB-1; Nov 21: MOB-1; Nov 22: MOB-1; Nov 23: MOB-1; Nov 24: MOB-1; Nov 25: MOB-1; Nov 26: MOB-1; Nov 27: MOB-1; Nov 28: MOB-1; Nov 29: MOB-1; Nov 30: MOB-1; Dec 01: MOB-1; Dec 02: MOB-1; Dec 03: MOB-1; Dec 04: MOB-1; Dec 05: MOB-1; Dec 06: MOB-1; Dec 07: MOB-1; Dec 08: MOB-1; Dec 09: MOB-1; Dec 10: MOB-1; Dec 11: MOB-1; Dec 12: MOB-1; Dec 13: MOB-1; Dec 14: MOB-1; Dec 15: MOB-1; Dec 16: MOB-1; Dec 17: MOB-1; Dec 18: MOB-1; Dec 19: MOB-1; Dec 20: MOB-1
|  |  | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2 | MOB-2
|  |  | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3 | MOB-3
Foundation | Interior Bldg | Bathrooms | Feb 28: INS-12
|  | Ceilings | Jan 18: INS-11
|  | N/A | Dec 21: CON-5; Dec 25: CON-14; Dec 26: CON-14; Dec 27: CON-14; Jan 05: CON-16; Jan 08: CON-8; Jan 09: CON-8; Jan 10: CON-8; Jan 11: CON-8; Jan 12: CON-8; Jan 13: CON-8; Jan 14: CON-8; Jan 15: CON-8; Jan 16: CON-8; Jan 17: CON-8; Jan 18: CON-8; Jan 19: CON-10; Jan 20: CON-10; Jan 21: CON-10; Jan 22: CON-10; Jan 23: CON-10; Jan 24: CON-10; Jan 25: CON-26; Jan 26: CON-26; Jan 27: CON-26; Jan 28: CON-26; Jan 29: CON-26; Jan 30: CON-26; Jan 31: CON-26; Feb 05: CON-20; Feb 06: CON-7; Feb 15: CON-3; Feb 16: CON-27; Feb 17: CON-27; Feb 18: CON-27; Feb 19: CON-27; Feb 20: CON-27; Feb 21: CON-27; Feb 22: CON-27; Feb 23: CON-27; Feb 24: CON-27; Feb 25: CON-27; Feb 26: CON-27; Feb 27: CON-1; Feb 29: CON-21; Mar 01: CON-1; Mar 04: INSU-1; Mar 05: INSU-1; Mar 06: CON-2; Mar 07: CON-2; May 27: CON-1; Jun 19: CON-4; Jul 08: CON-1; Aug 26: CON-8; Aug 27: CON-8; Sep 04: CON-29; Sep 05: CON-29; Sep 06: CON-29; Sep 10: CON-18; Nov 25: GYP-1; Nov 26: GYP-1; Dec 09: CON-23; Dec 10: CON-23; Dec 11: CON-23; Dec 12: CON-1; Dec 13: CON-1; Dec 14: CON-1; Dec 15: CON-1; Dec 16: CON-1; Dec 17: CON-19; Dec 18: CON-19; Dec 19: CON-19
[87 empty] | CON-17 | [26 empty] | CON-25 |  | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-12 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | CON-2 | [164 empty] | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9 | CON-9
[87 empty] | CON-24 | CON-24 | [45 empty] | CON-11 | CON-11 | CON-11 | CON-11 | CON-11 | CON-11 | CON-11 | CON-11 | CON-11
|  | Walls / Ceilings | Feb 01: INS-12
| Level 2 | N/A | Apr 16: CON-15; Apr 17: CON-15; Apr 18: CON-15
[204 empty] | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13 | CON-13
| Level 3 | N/A | May 23: CON-13; May 24: CON-13; May 25: CON-13; May 26: CON-13; May 27: CON-13; May 28: CON-13
[241 empty] | CON-15 | CON-15 | CON-15 | CON-15 | CON-15 | CON-15
| Level 4 | N/A | Jun 11: CON-15; Jun 12: CON-15
[260 empty] | CON-13 | CON-13 | CON-13
| Parkade | N/A | Jan 08: CON-6; Jan 09: CON-6; Jan 10: CON-6; Jan 11: CON-6; Jan 12: CON-6; Jan 13: CON-6; Jan 14: CON-6; Jan 15: CON-6; Jan 16: CON-6; Mar 08: CON-2; Mar 09: CON-2; Mar 10: CON-2; Mar 11: CON-2; Mar 12: CON-2; Mar 13: CON-2; Mar 14: CON-2; Jun 20: CON-2; Jun 21: CON-2; Jun 22: CON-2; Jun 23: CON-2; Jun 24: CON-2; Jun 25: CON-2; Jun 26: CON-2; Jun 27: CON-22; Jun 28: CON-22; Jun 29: CON-22; Jun 30: CON-22; Jul 01: CON-22; Jul 02: CON-22; Jul 03: CON-22; Jul 04: CON-22; Jul 05: CON-22; Jul 06: CON-22; Jul 07: CON-22; Jul 08: CON-22; Jul 09: CON-22; Jul 10: CON-22
[282 empty] | CON-28 | CON-28 | CON-28 |  |  |  | CON-22 | CON-22
Pre-Construction | Precon | Cabinets | Mar 04: PREC-10; Mar 05: PREC-10; Mar 06: PREC-10; Mar 07: PREC-10; Mar 08: PREC-10; Mar 09: PREC-10; Mar 10: PREC-10
|  | Commissioning | Sep 28: PREC-12; Sep 29: PREC-12; Sep 30: PREC-12; Oct 01: PREC-12; Oct 02: PREC-12
|  | Locates | Dec 21: PREC-15; Dec 22: PREC-15; Dec 23: PREC-15; Dec 24: PREC-15; Dec 25: PREC-15; Dec 26: PREC-15; Dec 27: PREC-15
|  | Mobilization | Mar 05: PREC-11; Mar 06: PREC-11; Mar 07: PREC-11; Mar 08: PREC-11; Mar 09: PREC-11; Mar 10: PREC-11; Mar 11: PREC-11
|  | N/A | Sep 28: PREC-8; Jan 08: PREC-1; Feb 02: PREC-8; Mar 15: PREC-8; Apr 16: PREC-8; Apr 19: PREC-8; May 14: PREC-8; Jun 10: PREC-8; Jun 13: PREC-8; Jun 27: PREC-8; Jul 08: PREC-8; Aug 07: PREC-8; Sep 09: PREC-4; Sep 17: PREC-8; Oct 07: PREC-8; Nov 08: PREC-6; Nov 15: PREC-8; Nov 25: PREC-8; Nov 26: PREC-8; Nov 28: PREC-8; Dec 05: PREC-8; Dec 19: PREC-8; Dec 23: PREC-8; Mar 03: PREC-7; Mar 04: PREC-9; May 02: PREC-8
|  |  | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | PREC-2 | [85 empty] | PREC-8 | [114 empty] | PREC-8 | [149 empty] | PREC-8 | [13 empty] | PREC-8
|  |  | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5 | PREC-5
|  |  | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8
|  |  | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8 | PREC-8
|  | Pile Contractor | Dec 21: PREC-16
|  | Structural | Dec 08: PREC-13
|  | Training | Sep 28: PREC-14
Sitework | Landscaping | Landscaping | Apr 04: SIT-9; Apr 05: SIT-9; Apr 06: SIT-9; Apr 07: SIT-9; Apr 08: SIT-9; Apr 09: SIT-9; Apr 10: SIT-9; Apr 18: SIT-10; Apr 19: SIT-10; Apr 20: SIT-10; Apr 21: SIT-10; Apr 22: SIT-10; Apr 23: SIT-10; Apr 24: SIT-10; Apr 25: SIT-10; Apr 26: SIT-10; Apr 27: SIT-10; Apr 28: SIT-10; Apr 29: SIT-10; Apr 30: SIT-10; May 01: SIT-10
|  | Signage | Feb 28: SIT-11
| Parkade | Mechanical Systems | Jan 21: SIT-7
|  | Paint | Jan 07: SIT-8
| Site | N/A | Dec 21: SIT-; Dec 22: SIT-; Dec 23: SIT-; Dec 24: SIT-; Dec 25: SIT-; Dec 26: SIT-; Dec 27: SIT-; Dec 28: SIT-; Dec 29: SIT-; Dec 30: SIT-; Dec 31: SIT-; Jan 01: SIT-; Jan 02: SIT-; Jan 03: SIT-; Jan 04: SIT-; Jan 05: SIT-; Mar 15: SIT-; Mar 16: SIT-; Mar 17: SIT-; Mar 18: SIT-; Mar 19: SIT-; Mar 20: SIT-; Mar 21: SIT-; Mar 22: SIT-; Mar 23: SIT-; Mar 24: SIT-; Mar 25: SIT-; Jun 28: SIT-1; Jun 29: SIT-1; Jun 30: SIT-1; Jul 01: SIT-1; Jul 02: SIT-2; Aug 28: SIT-3; Aug 29: SIT-3; Aug 30: SIT-3; Aug 31: SIT-3; Sep 01: SIT-3; Sep 02: SIT-3; Sep 03: SIT-3; Sep 11: SIT-4; Sep 12: SIT-4; Sep 13: SIT-4; Sep 14: SIT-4; Sep 15: SIT-4; Sep 16: SIT-4; Sep 17: SIT-4; Sep 18: SIT-4; Sep 19: SIT-4; Sep 20: SIT-4; Sep 21: SIT-4; Sep 22: SIT-4; Sep 23: SIT-4; Sep 24: SIT-4; Sep 25: SIT-4; Sep 26: SIT-4; Sep 27: SIT-4; Sep 28: SIT-4; Sep 29: SIT-4; Sep 30: SIT-4; Oct 01: SIT-4; Oct 02: SIT-4; Oct 03: SIT-4; Oct 04: SIT-4; Oct 05: SIT-4; Oct 06: SIT-4; Oct 07: SIT-4; Oct 08: SIT-4; Oct 09: SIT-4; Oct 10: SIT-4; Oct 11: SIT-4; Oct 12: SIT-4; Oct 13: SIT-4; Oct 14: SIT-4; Oct 15: SIT-4; Oct 16: SIT-4; Oct 17: SIT-4; Oct 18: SIT-4; Oct 19: SIT-4; Oct 20: SIT-4; Oct 21: SIT-4; Oct 22: SIT-4; Oct 23: SIT-4; Oct 24: SIT-4; Oct 25: SIT-4; Oct 26: SIT-4; Oct 27: SIT-4; Oct 28: SIT-4; Oct 29: SIT-4; Oct 30: SIT-4; Oct 31: SIT-4; Nov 01: SIT-4; Nov 02: SIT-4; Nov 03: SIT-4; Nov 04: SIT-4; Nov 05: SIT-4; Nov 06: SIT-4; Nov 07: SIT-4; Nov 08: SIT-4; Nov 09: SIT-4; Nov 10: SIT-4; Nov 11: SIT-4; Nov 12: SIT-4; Nov 13: SIT-4; Nov 14: SIT-4; Nov 15: SIT-4; Nov 16: SIT-4; Nov 17: SIT-4; Nov 18: SIT-4; Nov 19: SIT-4; Nov 20: SIT-4; Nov 21: SIT-4; Nov 22: SIT-4; Nov 23: SIT-4; Nov 24: SIT-4; Nov 25: SIT-4; Nov 26: SIT-4; Nov 27: SIT-4; Nov 28: SIT-4; Nov 29: SIT-4; Nov 30: SIT-4; Dec 01: SIT-4; Dec 02: SIT-4; Dec 03: SIT-4; Dec 04: SIT-5; Dec 05: SIT-5; Dec 06: SIT-5
[87 empty] | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT-
[94 empty] | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | SIT- | [73 empty] | SIT-
[175 empty] | SIT- | SIT- | SIT- | SIT- | SIT-
|  | Survey | Oct 29: SIT-6; Oct 30: SIT-6; Oct 31: SIT-6
Exteriors | Level 2 | N/A | Nov 28: EXT-4; Nov 29: EXT-4; Nov 30: EXT-4; Dec 01: EXT-4; Dec 02: EXT-4; Dec 03: EXT-4; Dec 04: EXT-4
|  | Walls / Ceilings | Nov 08: RI-2; Nov 09: RI-2; Nov 10: RI-2; Nov 11: RI-2; Nov 12: RI-2; Nov 13: RI-2; Nov 14: RI-2; Nov 15: RI-2; Nov 16: RI-2; Nov 17: RI-2; Nov 18: RI-2; Nov 19: RI-2; Nov 20: RI-2; Nov 21: RI-2; Nov 22: SID-4; Nov 23: SID-4; Nov 24: SID-4; Nov 25: SID-4; Nov 26: SID-4; Nov 27: SID-4; Nov 28: SID-4; Nov 29: SID-4; Nov 30: SID-4; Dec 01: SID-4; Dec 02: SID-4; Dec 03: SID-4; Dec 04: SID-4; Dec 05: SID-4; Dec 06: SID-4; Dec 07: SID-4; Dec 08: SID-4; Dec 09: SID-4
[427 empty] | INSU-1 | INSU-1 | INSU-1 | INSU-1
| Level 3 | Exterior Walls | Feb 19: EXT-10
|  | Walls / Ceilings | Oct 28: RI-2; Oct 29: RI-2; Oct 30: RI-2; Oct 31: RI-2; Nov 01: RI-2; Nov 02: RI-2; Nov 03: RI-2; Nov 04: RI-2; Nov 05: RI-2; Nov 06: RI-2; Nov 07: RI-2; Nov 08: RI-2; Nov 12: INSU-1; Nov 13: INSU-1; Nov 14: INSU-1; Nov 15: INSU-1
[408 empty] | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4 | SID-4
| Level 4 | Walls / Ceilings | Oct 21: SID-4; Oct 22: SID-4; Oct 23: SID-4; Oct 24: SID-4; Oct 25: SID-4; Oct 26: SID-4; Oct 27: SID-4; Oct 28: SID-4; Oct 29: SID-4; Oct 30: SID-4; Oct 31: SID-4; Nov 01: SID-4; Nov 02: SID-4; Nov 03: SID-4; Nov 04: SID-4; Nov 05: SID-4
[407 empty] | INSU-1 | INSU-1 | INSU-1
| Outside Bldg | Attic | Sep 18: EXT-7; Sep 19: EXT-7; Sep 20: EXT-7
|  | Balconies | Aug 09: EXT-9; Aug 10: EXT-9; Aug 11: EXT-9; Aug 12: EXT-9; Aug 13: EXT-9; Aug 14: EXT-9; Aug 15: EXT-9; Aug 16: EXT-9; Aug 17: EXT-9; Aug 18: EXT-9; Aug 19: EXT-9; Aug 20: EXT-9; Aug 21: EXT-9; Aug 22: EXT-9
|  | Mechanical Systems | Aug 09: EXT-8; Aug 10: EXT-8; Aug 11: EXT-8; Aug 12: EXT-8; Aug 13: EXT-8; Aug 14: EXT-8; Aug 15: EXT-8; Aug 16: EXT-8; Aug 17: EXT-8; Aug 18: EXT-8; Aug 19: EXT-8; Aug 20: EXT-8; Aug 21: EXT-8; Aug 22: EXT-8; Aug 23: EXT-8; Aug 24: EXT-8; Aug 25: EXT-8; Aug 26: EXT-8; Aug 27: EXT-8; Aug 28: EXT-8; Aug 29: EXT-8; Aug 30: EXT-8; Aug 31: EXT-8; Sep 01: EXT-8; Sep 02: EXT-8; Sep 03: EXT-8; Sep 04: EXT-8; Sep 05: EXT-8; Sep 06: EXT-8; Sep 07: EXT-8; Sep 08: EXT-8; Sep 09: EXT-8; Sep 10: EXT-8; Sep 11: EXT-8; Sep 12: EXT-8; Sep 13: EXT-8; Sep 14: EXT-8; Sep 15: EXT-8; Sep 16: EXT-8; Sep 17: EXT-8; Sep 18: EXT-8; Sep 19: EXT-8; Sep 20: EXT-8; Sep 21: EXT-8; Sep 22: EXT-8; Sep 23: EXT-8; Sep 24: EXT-8; Sep 25: EXT-8; Sep 26: EXT-8; Sep 27: EXT-8; Sep 28: EXT-8; Sep 29: EXT-8; Sep 30: EXT-8; Oct 01: EXT-8; Oct 02: EXT-8; Oct 03: EXT-8; Oct 04: EXT-8; Oct 05: EXT-8; Oct 06: EXT-8; Oct 07: EXT-8; Oct 08: EXT-8; Oct 09: EXT-8; Oct 10: EXT-8; Oct 11: EXT-8; Oct 12: EXT-8; Oct 13: EXT-8; Oct 14: EXT-8; Oct 15: EXT-8; Oct 16: EXT-8; Oct 17: EXT-8; Oct 18: EXT-8; Oct 19: EXT-8; Oct 20: EXT-8; Oct 21: EXT-8; Oct 22: EXT-8; Oct 23: EXT-8; Oct 24: EXT-8; Oct 25: EXT-8; Oct 26: EXT-8; Oct 27: EXT-8; Oct 28: EXT-8; Oct 29: EXT-8; Oct 30: EXT-8; Oct 31: EXT-8; Nov 01: EXT-8; Nov 02: EXT-8; Nov 03: EXT-8; Nov 04: EXT-8; Nov 05: EXT-8; Nov 06: EXT-8; Nov 07: EXT-8; Nov 08: EXT-8; Nov 09: EXT-8; Nov 10: EXT-8; Nov 11: EXT-8; Nov 12: EXT-8; Nov 13: EXT-8; Nov 14: EXT-8; Nov 15: EXT-8; Nov 16: EXT-8; Nov 17: EXT-8; Nov 18: EXT-8; Nov 19: EXT-8; Nov 20: EXT-8; Nov 21: EXT-8; Nov 22: EXT-8; Nov 23: EXT-8; Nov 24: EXT-8; Nov 25: EXT-8; Nov 26: EXT-8; Nov 27: EXT-8; Nov 28: EXT-8; Nov 29: EXT-8; Nov 30: EXT-8; Dec 01: EXT-8; Dec 02: EXT-8; Dec 03: EXT-8; Dec 04: EXT-8; Dec 05: EXT-8; Dec 06: EXT-8; Dec 07: EXT-8; Dec 08: EXT-8; Dec 09: EXT-8; Dec 10: EXT-8; Dec 11: EXT-8; Dec 12: EXT-8; Dec 13: EXT-8; Dec 14: EXT-8; Dec 15: EXT-8; Dec 16: EXT-8; Dec 17: EXT-8; Dec 18: EXT-8; Dec 19: EXT-8; Dec 20: EXT-8; Dec 21: EXT-8; Dec 22: EXT-8; Dec 23: EXT-8; Dec 24: EXT-8; Dec 25: EXT-8; Dec 26: EXT-8; Dec 27: EXT-8; Dec 28: EXT-8; Dec 29: EXT-8; Dec 30: EXT-8; Dec 31: EXT-8; Jan 01: EXT-8; Jan 02: EXT-8; Jan 03: EXT-8; Jan 04: EXT-8; Jan 05: EXT-8; Jan 06: EXT-8; Jan 07: EXT-8; Jan 08: EXT-8; Jan 09: EXT-8; Jan 10: EXT-8; Jan 11: EXT-8; Jan 12: EXT-8; Jan 13: EXT-8; Jan 14: EXT-8; Jan 15: EXT-8; Jan 16: EXT-8; Jan 17: EXT-8; Jan 18: EXT-8; Jan 19: EXT-8; Jan 20: EXT-8; Jan 21: EXT-8; Jan 22: EXT-8; Jan 23: EXT-8; Jan 24: EXT-8; Jan 25: EXT-8; Jan 26: EXT-8; Jan 27: EXT-8; Jan 28: EXT-8; Jan 29: EXT-8; Jan 30: EXT-8; Jan 31: EXT-8; Feb 01: EXT-8; Feb 02: EXT-8; Feb 03: EXT-8; Feb 04: EXT-8; Feb 05: EXT-8; Feb 06: EXT-8; Feb 07: EXT-8; Feb 08: EXT-8; Feb 09: EXT-8; Feb 10: EXT-8; Feb 11: EXT-8; Feb 12: EXT-8; Feb 13: EXT-8; Feb 14: EXT-8; Feb 15: EXT-8; Feb 16: EXT-8; Feb 17: EXT-8; Feb 18: EXT-8; Feb 19: EXT-8; Feb 20: EXT-8; Feb 21: EXT-8; Feb 22: EXT-8; Feb 23: EXT-8; Feb 24: EXT-8; Feb 25: EXT-8; Feb 26: EXT-8; Feb 27: EXT-8; Feb 28: EXT-8; Mar 01: EXT-8; Mar 02: EXT-8; Mar 03: EXT-8; Mar 04: EXT-8; Mar 05: EXT-8; Mar 06: EXT-8; Mar 07: EXT-8; Mar 08: EXT-8; Mar 09: EXT-8; Mar 10: EXT-8; Mar 11: EXT-8; Mar 12: EXT-8; Mar 13: EXT-8; Mar 14: EXT-8; Mar 15: EXT-8; Mar 16: EXT-8; Mar 17: EXT-8; Mar 18: EXT-8; Mar 19: EXT-8; Mar 20: EXT-8; Mar 21: EXT-8; Mar 22: EXT-8; Mar 23: EXT-8; Mar 24: EXT-8; Mar 25: EXT-8; Mar 26: EXT-8; Mar 27: EXT-8; Mar 28: EXT-8; Mar 29: EXT-8; Mar 30: EXT-8; Mar 31: EXT-8; Apr 01: EXT-8; Apr 02: EXT-8; Apr 03: EXT-8; Apr 04: EXT-8; Apr 05: EXT-8; Apr 06: EXT-8; Apr 07: EXT-8; Apr 08: EXT-8; Apr 09: EXT-8; Apr 10: EXT-8; Apr 11: EXT-8; Apr 12: EXT-8; Apr 13: EXT-8; Apr 14: EXT-8; Apr 15: EXT-8; Apr 16: EXT-8; Apr 17: EXT-8; Apr 18: EXT-8; Apr 19: EXT-8; Apr 20: EXT-8; Apr 21: EXT-8; Apr 22: EXT-8; Apr 23: EXT-8; Apr 24: EXT-8; Apr 25: EXT-8; Apr 26: EXT-8; Apr 27: EXT-8; Apr 28: EXT-8; Apr 29: EXT-8; Apr 30: EXT-8; May 01: EXT-8; May 02: EXT-8; May 03: EXT-8; May 04: EXT-8; May 05: EXT-8
|  | N/A | Jul 08: WIN-1; Jul 09: WIN-1; Jul 10: WIN-1; Jul 11: WIN-1; Jul 12: WIN-1; Jul 13: WIN-1; Jul 14: WIN-1; Jul 15: WIN-1; Jul 16: WIN-1; Jul 17: WIN-1; Jul 18: WIN-1; Jul 19: WIN-1; Jul 20: WIN-1; Jul 21: WIN-1; Jul 22: WIN-1; Jul 23: WIN-1; Jul 24: WIN-1; Jul 25: WIN-1; Jul 26: WIN-1; Jul 27: WIN-1; Jul 28: WIN-1; Jul 29: WIN-1; Jul 30: WIN-1; Jul 31: WIN-1; Aug 01: WIN-1; Aug 02: WIN-1; Aug 03: WIN-1; Aug 04: WIN-1; Aug 05: WIN-1; Aug 06: WIN-1; Aug 07: WIN-1; Aug 08: WIN-1; Aug 09: WIN-1; Aug 10: WIN-1; Aug 11: WIN-1; Aug 12: WIN-1; Aug 13: WIN-1; Aug 14: WIN-1; Aug 15: WIN-1; Aug 16: WIN-1; Aug 17: WIN-1; Aug 18: WIN-1; Aug 19: WIN-1; Aug 20: WIN-1; Aug 21: WIN-1; Aug 22: WIN-1; Aug 23: WIN-1; Aug 24: WIN-1; Aug 25: WIN-1; Aug 26: WIN-1; Aug 27: WIN-1; Aug 28: WIN-1; Aug 29: WIN-1; Aug 30: WIN-1; Aug 31: WIN-1; Sep 01: WIN-1; Sep 02: WIN-1; Sep 03: WIN-1; Sep 04: WIN-1; Sep 05: WIN-1; Sep 06: WIN-1; Sep 07: WIN-1; Sep 08: WIN-1; Sep 09: WIN-1; Sep 10: WIN-1; Sep 11: WIN-1; Sep 12: WIN-1; Sep 13: WIN-1; Sep 14: WIN-1; Sep 15: WIN-1; Sep 16: WIN-1; Sep 17: WIN-1; Sep 18: WIN-1; Sep 19: WIN-1; Sep 20: WIN-1; Sep 21: WIN-1; Sep 22: WIN-1; Sep 23: WIN-1; Sep 24: WIN-1; Sep 25: WIN-1; Sep 26: WIN-1; Sep 27: WIN-1; Sep 28: WIN-1; Sep 29: WIN-1; Sep 30: WIN-1; Oct 01: WIN-1; Oct 02: WIN-1; Oct 03: WIN-1; Oct 04: WIN-1; Oct 05: WIN-1; Oct 06: WIN-1; Oct 07: WIN-1; Oct 08: WIN-1; Oct 09: WIN-1; Oct 10: WIN-1; Oct 11: WIN-1; Oct 12: WIN-1; Oct 13: WIN-1; Oct 14: WIN-1; Oct 15: WIN-1; Oct 16: WIN-1; Oct 17: WIN-1; Oct 18: WIN-1; Oct 19: WIN-1; Oct 20: WIN-1; Oct 21: WIN-1; Oct 22: WIN-1; Oct 23: WIN-1; Oct 24: WIN-1; Oct 25: WIN-1; Oct 26: WIN-1; Oct 27: WIN-1; Oct 28: WIN-1; Oct 29: WIN-1; Oct 30: WIN-1; Oct 31: WIN-1; Nov 01: WIN-1; Nov 02: WIN-1; Nov 03: WIN-1; Nov 04: WIN-1; Nov 05: WIN-1; Nov 06: WIN-1; Nov 07: WIN-1; Nov 08: WIN-1; Nov 09: WIN-1; Nov 10: WIN-1; Nov 11: WIN-1; Nov 12: WIN-1; Nov 13: WIN-1; Nov 14: WIN-1; Nov 15: WIN-1; Nov 16: WIN-1; Nov 17: WIN-1; Nov 18: WIN-1; Nov 19: WIN-1; Nov 20: WIN-1; Nov 21: WIN-1; Nov 22: WIN-1; Nov 23: WIN-1; Nov 24: WIN-1; Nov 25: WIN-1; Nov 26: WIN-1; Nov 27: SID-2; Nov 28: SID-2; Nov 29: SID-2; Nov 30: SID-2; Dec 01: SID-2; Dec 02: SID-2; Dec 03: SID-2; Dec 04: SID-2; Dec 05: SID-2; Dec 06: SID-2; Dec 07: SID-2; Dec 08: SID-2; Dec 09: SID-2; Dec 10: SID-2; Dec 11: SID-2; Dec 12: SID-2; Dec 13: SID-2; Dec 14: SID-2; Dec 15: SID-2; Dec 16: SID-2; Dec 24: SID-3
[317 empty] | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | [10 empty] | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | EXT-3 | [14 empty] | SID-3
[322 empty] | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | EXT-2 | [10 empty] | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1 | SID-1
[408 empty] | SID-3 | [15 empty] | SID-3
| Parkade | N/A | Dec 09: EXT-5; Dec 10: EXT-6; Dec 11: EXT-6; Dec 12: EXT-6; Dec 13: EXT-6
|  | Parkade | Aug 19: RI-4; Aug 20: RI-4; Aug 21: RI-4; Aug 22: RI-4; Aug 23: RI-4; Aug 24: RI-4; Aug 25: RI-4; Aug 26: RI-4; Aug 27: RI-4; Aug 28: RI-4; Aug 29: RI-4; Aug 30: RI-4; Aug 31: RI-4; Sep 01: RI-4; Sep 02: RI-4; Sep 03: RI-4; Sep 04: RI-4; Sep 05: RI-4; Sep 06: RI-4; Sep 07: RI-4; Sep 08: RI-4; Sep 09: RI-4; Sep 10: RI-4; Sep 11: RI-4; Sep 12: RI-4; Sep 13: RI-4; Sep 14: RI-4; Sep 15: RI-4; Sep 16: RI-4; Sep 17: RI-4; Sep 18: RI-4; Sep 19: RI-4; Sep 20: RI-4; Sep 21: RI-4; Sep 22: RI-4; Sep 23: RI-4; Sep 24: RI-4; Sep 25: RI-4; Sep 26: RI-4; Sep 27: RI-4; Sep 28: RI-4; Sep 29: RI-4; Sep 30: RI-4; Oct 01: RI-4; Oct 02: RI-4; Oct 03: RI-4; Oct 04: RI-4; Oct 05: RI-4; Oct 06: RI-4; Oct 07: RI-4; Oct 08: RI-4; Oct 09: RI-4; Oct 10: RI-4; Oct 11: RI-4; Oct 12: RI-4; Oct 13: RI-4; Oct 14: RI-4; Oct 15: RI-4; Oct 16: RI-4; Oct 17: RI-4; Oct 18: RI-4; Oct 19: RI-4; Oct 20: RI-4; Oct 21: RI-4; Oct 22: RI-4; Oct 23: RI-4; Oct 24: RI-4; Oct 25: RI-4; Oct 26: RI-4; Oct 27: RI-4; Oct 28: RI-4; Oct 29: RI-4; Oct 30: RI-4; Oct 31: RI-4; Nov 01: RI-4; Nov 02: RI-4; Nov 03: RI-4; Nov 04: RI-4; Nov 05: RI-4; Nov 06: RI-4; Nov 07: RI-4; Nov 08: RI-4; Nov 09: RI-4; Nov 10: RI-4; Nov 11: RI-4; Nov 12: RI-4; Nov 13: RI-4; Nov 14: RI-4; Nov 15: RI-4; Nov 16: RI-4; Nov 17: RI-4; Nov 18: RI-4; Nov 19: RI-4; Nov 20: RI-4; Nov 21: RI-4; Nov 22: RI-4; Nov 23: RI-4; Nov 24: RI-4; Nov 25: RI-4; Nov 26: RI-4; Nov 27: RI-4; Nov 28: RI-4; Nov 29: RI-4; Nov 30: RI-4; Dec 01: RI-4; Dec 02: RI-4; Dec 03: RI-4; Dec 04: RI-4; Dec 05: RI-4; Dec 06: RI-4; Dec 07: RI-4; Dec 08: RI-4; Dec 09: RI-4; Dec 10: RI-4; Dec 11: RI-4; Dec 12: RI-4; Dec 13: RI-4; Dec 14: RI-4; Dec 15: RI-4; Dec 16: RI-4; Dec 17: RI-4; Dec 18: RI-4; Dec 19: RI-4; Dec 20: RI-4; Dec 21: RI-4; Dec 22: RI-4; Dec 23: RI-4; Dec 24: RI-4; Dec 25: RI-4; Dec 26: RI-4; Dec 27: RI-4; Dec 28: RI-4; Dec 29: RI-4; Dec 30: RI-4; Dec 31: RI-4; Jan 01: RI-4; Jan 02: RI-4; Jan 03: RI-4; Jan 04: RI-4; Jan 05: RI-4; Jan 06: RI-4; Jan 07: RI-4; Jan 08: RI-4; Jan 09: RI-4; Jan 10: RI-4; Jan 11: RI-4; Jan 12: RI-4; Jan 13: RI-4; Jan 14: RI-4; Jan 15: RI-4; Jan 16: RI-4; Jan 17: RI-4; Jan 18: RI-4; Jan 19: RI-4; Jan 20: RI-4; Jan 21: RI-4; Jan 22: RI-4; Jan 23: RI-4
|  | Walls / Ceilings | Aug 22: INSU-2; Aug 23: INSU-2; Nov 18: RI-2; Nov 19: RI-2; Nov 20: RI-2; Nov 21: RI-2; Nov 22: RI-2; Nov 23: RI-2; Nov 24: RI-2; Nov 25: RI-2; Nov 26: RI-2; Nov 27: RI-2; Nov 28: RI-2; Nov 29: RI-2; Nov 30: RI-2; Dec 01: RI-2; Dec 02: RI-2; Dec 03: RI-2; Dec 04: RI-2; Dec 05: RI-2; Dec 06: RI-2; Dec 10: SID-4; Dec 11: SID-4; Dec 12: SID-4; Dec 13: SID-4; Dec 14: SID-4; Dec 15: SID-4; Dec 16: SID-4; Dec 17: SID-4; Dec 18: SID-4; Dec 19: SID-4; Dec 20: SID-4; Dec 21: SID-4; Dec 22: SID-4; Dec 23: SID-4
Interior | Interior Bldg | N/A | Mar 15: STL-1; Mar 16: STL-1; Mar 17: STL-1; Mar 18: STL-1; Mar 19: STL-1; Mar 20: STL-1; Mar 21: STL-1; Mar 25: CX-; Apr 11: FRA-; Apr 12: FRA-; Apr 13: FRA-; Apr 14: FRA-; Apr 15: FRA-; Apr 16: FRA-; Apr 17: FRA-; Apr 18: FRA-; Apr 19: FRA-; Apr 20: FRA-; Apr 21: FRA-; Apr 22: FRA-; Apr 23: FRA-; Apr 24: FRA-; Apr 25: FRA-; Apr 26: FRA-; Apr 27: FRA-; Apr 28: FRA-; Apr 29: FRA-; Apr 30: FRA-; May 01: FRA-; May 02: FRA-; May 03: FRA-; May 04: FRA-; May 05: FRA-; May 06: FRA-; May 07: FRA-; May 08: FRA-; May 09: FRA-; May 10: FRA-; May 11: FRA-; May 12: FRA-; May 13: FRA-; May 14: FRA-; May 15: FRA-; May 16: FRA-; May 17: FRA-; May 18: FRA-; May 19: FRA-; May 20: FRA-; May 21: FRA-; May 22: FRA-; May 23: FRA-; May 24: FRA-; May 25: FRA-; May 26: FRA-; May 27: FRA-; May 28: FRA-; May 29: FRA-; May 30: FRA-; May 31: FRA-; Jun 01: FRA-; Jun 02: FRA-; Jun 03: FRA-; Jun 04: FRA-; Jun 05: FRA-; Jun 06: FRA-; Jun 07: FRA-; Jun 08: FRA-; Jun 09: FRA-; Jun 10: FRA-; Jun 11: FRA-; Jun 12: FRA-; Jun 13: FRA-; Jun 14: FRA-; Jun 15: FRA-; Jun 16: FRA-; Jun 17: FRA-; Jun 18: FRA-; Jun 19: FRA-; Jun 20: FRA-; Jun 21: FRA-; Jun 22: FRA-; Jun 23: FRA-; Jun 24: FRA-; Jun 25: FRA-; Jun 26: FRA-; Jun 27: FRA-; Jun 28: FRA-; Jun 29: FRA-; Jun 30: FRA-; Jul 01: FRA-; Jul 02: FRA-; Jul 03: FRA-; Jul 04: FRA-; Jul 05: FRA-; Jul 06: FRA-; Jul 07: FRA-; Jul 08: FRA-; Jul 09: FRA-; Jul 10: FRA-; Jul 11: FRA-; Jul 12: FRA-; Jul 13: FRA-; Jul 14: FRA-; Jul 15: FRA-; Jul 16: FRA-; Jul 17: FRA-; Jul 18: FRA-; Jul 19: FRA-; Jul 20: FRA-; Jul 21: FRA-; Jul 22: FRA-; Jul 23: FRA-; Jul 24: FRA-; Jul 25: FRA-; Jul 26: FRA-; Jul 27: FRA-; Jul 28: FRA-; Jul 29: FRA-; Jul 30: FRA-; Jul 31: FRA-; Aug 01: FRA-; Aug 02: FRA-; Aug 03: FRA-; Aug 04: FRA-; Aug 05: FRA-; Aug 06: FRA-; Aug 07: FRA-; Aug 08: FRA-; Aug 09: FRA-; Aug 10: FRA-; Aug 11: FRA-; Aug 12: FRA-; Aug 13: FRA-; Aug 14: FRA-; Aug 15: FRA-; Aug 16: FRA-; Aug 17: FRA-; Aug 18: FRA-; Aug 19: FRA-; Aug 20: FRA-; Aug 21: FRA-; Aug 22: FRA-; Aug 23: FRA-; Aug 24: FRA-; Aug 25: FRA-; Aug 26: FRA-; Aug 27: FRA-; Aug 28: FRA-; Aug 29: FRA-; Aug 30: FRA-; Aug 31: FRA-; Sep 01: FRA-; Sep 02: FRA-; Sep 03: FRA-; Sep 04: FRA-; Sep 05: FRA-; Sep 06: FRA-; Sep 07: FRA-; Sep 08: FRA-; Sep 09: FRA-; Sep 10: FRA-; Sep 11: FRA-; Sep 12: FRA-; Sep 13: FRA-; Sep 14: FRA-; Sep 15: FRA-; Sep 16: FRA-; Sep 17: FRA-; Sep 18: FRA-; Sep 19: FRA-; Sep 20: FRA-; Sep 21: FRA-; Sep 22: FRA-; Sep 23: FRA-; Sep 24: FRA-; Sep 25: FRA-; Sep 26: FRA-; Sep 27: FRA-; Sep 28: FRA-; Sep 29: FRA-; Sep 30: FRA-; Oct 01: FRA-; Oct 02: FRA-; Oct 03: FRA-; Oct 04: FRA-; Oct 05: FRA-; Oct 06: FRA-; Oct 07: FRA-; Oct 08: FRA-; Oct 09: FRA-; Oct 10: FRA-; Oct 11: FRA-; Oct 12: FRA-; Oct 13: FRA-; Oct 14: FRA-; Oct 15: FRA-; Oct 16: FRA-; Oct 17: FRA-; Oct 18: FRA-; Oct 19: FRA-; Oct 20: FRA-; Oct 21: FRA-; Oct 22: FRA-; Oct 23: FRA-; Oct 24: FRA-; Oct 25: FRA-; Oct 26: FRA-; Oct 27: FRA-; Oct 28: FRA-; Oct 29: FRA-; Oct 30: FRA-; Oct 31: FRA-; Nov 01: FRA-; Nov 02: FRA-; Nov 03: FRA-; Nov 04: FRA-; Nov 05: FRA-; Nov 06: FRA-; Nov 07: FRA-; Nov 08: FRA-; Nov 09: FRA-; Nov 10: FRA-; Nov 11: FRA-; Nov 12: FRA-; Nov 13: FRA-; Nov 14: FRA-; Nov 15: FRA-; Nov 16: FRA-; Nov 17: FRA-; Nov 18: FRA-; Nov 19: FRA-; Nov 20: FRA-; Nov 21: FRA-; Nov 22: FRA-; Nov 23: FRA-; Nov 24: FRA-; Nov 25: FRA-; Nov 26: FRA-; Nov 27: FRA-; Nov 28: FRA-; Nov 29: FRA-; Nov 30: FRA-; Dec 01: FRA-; Dec 02: FRA-; Dec 03: FRA-; Dec 04: FRA-; Dec 05: FRA-; Dec 06: FRA-; Dec 07: FRA-; Dec 08: FRA-; Dec 09: FRA-; Dec 10: FRA-; Dec 11: FRA-; Dec 12: FRA-; Dec 13: FRA-; Dec 14: FRA-; Dec 15: FRA-; Dec 16: FRA-; Dec 17: FRA-; Dec 18: FRA-; Dec 19: FRA-; Dec 20: FRA-; Dec 21: FRA-; Dec 22: FRA-; Dec 23: FRA-; Dec 24: FRA-; Dec 25: FRA-; Dec 26: FRA-; Dec 27: FRA-; Dec 28: FRA-; Dec 29: FRA-; Dec 30: FRA-; Dec 31: FRA-; Jan 01: FRA-; Jan 02: FRA-; Jan 03: FRA-; Jan 20: FLO-8; Jan 21: FLO-8; Jan 22: FLO-8; Jan 23: FLO-8; Jan 24: FLO-8; Jan 25: FLO-8; Jan 26: FLO-8; Jan 27: FLO-8; Jan 28: FLO-8; Jan 29: FLO-8; Jan 30: FLO-8; Jan 31: FLO-8; Feb 01: FLO-8; Feb 02: FLO-8; Feb 03: FLO-8; Feb 04: FLO-8; Feb 05: FLO-8; Feb 06: FLO-8; Feb 13: PAI-2; Feb 14: PAI-2; Feb 15: PAI-2; Feb 16: PAI-2; Feb 17: PAI-2; Feb 18: PAI-2; Feb 19: PAI-2; Feb 20: PAI-2; Feb 21: PAI-2; Feb 22: PAI-2; Feb 23: PAI-2; Feb 24: PAI-2; Feb 25: PAI-2; Feb 27: CL-2; Feb 28: CL-2; Mar 03: COO-3; Mar 04: CX-2; Mar 05: CX-9; Mar 06: CX-10; Mar 07: CX-10; Mar 08: CX-10; Mar 09: CX-10; Mar 10: CX-10; Mar 11: CX-10; Mar 12: CX-10; Mar 13: CX-12; Mar 18: CX-13; Apr 11: SPR-4; Apr 12: SPR-4; Apr 13: SPR-4; Apr 14: SPR-4; Apr 15: SPR-4; Apr 16: SPR-4; Apr 17: SPR-4; May 02: CX-; May 03: CX-; May 04: CX-; May 05: CX-
[177 empty] | STL-2 | STL-2 |  |  |  | CX- | [78 empty] | MCH-1 | MCH-1 | MCH-1 | MCH-1 | MCH-1 | MCH-1 | MCH-1 | [28 empty] | PLU-1 | PLU-1 | [11 empty] | VF-1 |  | FLO-10 | FLO-10 | FLO-10 | FLO-10 | FLO-10 | FLO-10 | FLO-10 | FLO-10 | FLO-10 | FLO-10 | FLO-10 | FLO-10 | FLO-10 | [6 empty] | INS-7 | [5 empty] | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | INS-6 |  | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | [8 empty] | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | [17 empty] | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | VF-2 | [18 empty] | DRY-3 | INS-4 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | [8 empty] | INS-8 |  |  |  |  | INS-2 | INS-2 | INS-3 | INS-3 | INS-3 | INS-3 | COO-1 | COO-1 | COO-2 | COO-2 |  |  | COO-5 | CX-4 | CL-4 | CL-4 | CL-4 | CL-4 | CL-4 | CL-4 | CL-4 | CL-5 | CL-5 | CL-5 | CL-5 | CL-5 | CL-5 | CL-5
[261 empty] | ELE-1 | ELE-1 | ELE-1 | ELE-1 | ELE-1 | ELE-1 | ELE-1 | [47 empty] | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | [13 empty] | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 |  |  | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | FRA-6 | [13 empty] | PLU-2 | PLU-2 | [33 empty] | INS-4 | [7 empty] | DRY-2 |  |  |  | INS-6 |  |  | DRY-3 | [5 empty] | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 | RI-3 |  | DRY-4 | DRY-4 | DRY-4 | DRY-4 | DRY-4 | [13 empty] | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | FRA-5 | [15 empty] | DRY-3 | [11 empty] | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | PAI-2 | INS-10 | INS-10 | INS-10 | INS-10 |  | INS-9 | INS-9 | [10 empty] | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4 | COO-4
[315 empty] | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | DRY-1 | [21 empty] | INS-13 | INS-13 | INS-13 | INS-13 | [14 empty] | CX-1 | CX-1 | CX-1 | CX-1 | CX-1 | CX-1 | CX-1 | CX-7
[317 empty] | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | SPR-2 | [8 empty] | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | [64 empty] | DRY-3 |  |  |  | DRY-2 |  |  | DRY-3 | [9 empty] | INS-6 | INS-5 |  | DRY-2 | [77 empty] | CX- | CX- | CX- | CX- | [14 empty] | CX-3 | CX-3 | CX-3 | CX-3 | CX-3 | CX-3 | CX-3 | CL-3 | CL-3 | CL-3 | CL-3 | CL-3 | CL-3 | CL-3
[319 empty] | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1 | FIN-1
[344 empty] | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | [69 empty] | GYP-1 | GYP-1 |  | DRY-3 | [77 empty] | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX- | CX-5 | CX-5 | CX-5 | CX-5 | CX-5 | CX-5 | CX-5
[430 empty] | DRY-3 | [95 empty] | CX-6 | CX-6 | CX-6 | CX-6 | CX-6 | CX-6 | CX-6
[430 empty] | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | ELE-4 | [67 empty] | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8 | CX-8
[430 empty] | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | MCH-2 | [42 empty] | CX-11 | CX-11 | CX-11 | CX-11 | CX-11 | CX-11 | CX-11
| Level 1 | Cabinets | Jan 02: FIN-3; Jan 03: FIN-3; Jan 04: FIN-3; Jan 05: FIN-3; Jan 06: FIN-3; Jan 07: FIN-3; Jan 08: FIN-3; Jan 09: FIN-3; Jan 10: FIN-3; Jan 11: FIN-3; Jan 12: FIN-3; Jan 13: FIN-3; Jan 14: FIN-3; Jan 15: FIN-3; Jan 16: FIN-3; Jan 17: FIN-3; Jan 18: FIN-3; Jan 19: FIN-3; Jan 20: FIN-3; Jan 21: FIN-3; Jan 22: FIN-3; Jan 23: FIN-3; Jan 24: FIN-3; Jan 25: FIN-3; Jan 26: FIN-3; Jan 27: FIN-3; Jan 28: FIN-3; Jan 29: FIN-3; Jan 30: FIN-3; Jan 31: FIN-3; Feb 01: FIN-3; Feb 02: FIN-3; Feb 03: FIN-3; Feb 04: FIN-3; Feb 05: FIN-3; Feb 06: FIN-3; Feb 07: FIN-3; Feb 08: FIN-3; Feb 09: FIN-3; Feb 10: FIN-3; Feb 11: FIN-3; Feb 12: FIN-3; Feb 13: FIN-3; Feb 14: FIN-3; Feb 15: FIN-3; Feb 16: FIN-3; Feb 17: FIN-3; Feb 18: FIN-3; Feb 19: FIN-3; Feb 20: FIN-3; Feb 21: FIN-3; Feb 22: FIN-3; Feb 23: FIN-3; Feb 24: FIN-3
[480 empty] | CAR-2 | CAR-2 | CAR-2 | CAR-2
|  | Ceilings | Jan 02: FIN-2; Jan 03: FIN-2
|  | Closets | Jan 10: CAR-6
|  | Common Areas | Feb 14: CL-1; Feb 15: CL-1; Feb 16: CL-1; Feb 17: CL-1; Feb 18: CL-1; Feb 19: CX-; Feb 20: CL-2; Feb 21: CL-2; Feb 22: CL-2; Feb 23: CL-2; Feb 24: CL-2
|  | Countertops | Feb 10: CAR-3
|  | Doors and Frames | Dec 02: FRA-7; Dec 03: FRA-7; Dec 04: FRA-7; Dec 05: FRA-7; Dec 06: FRA-7; Dec 09: FRA-7; Dec 10: FRA-7; Dec 11: FRA-7; Dec 12: FRA-7; Dec 13: FRA-7; Dec 23: FRA-7; Dec 24: FRA-7; Dec 25: FRA-7; Dec 26: FRA-7; Dec 27: FRA-7; Dec 28: FRA-7; Dec 29: FRA-7; Dec 30: FRA-7; Dec 31: FRA-7; Jan 01: FRA-7; Jan 02: FRA-7; Jan 03: FRA-7; Jan 08: CAR-4; Jan 09: CAR-4
|  | Electrical Systems | Feb 11: ELE-2; Feb 12: ELE-2; Feb 13: ELE-2
|  | Fire Systems | Jan 10: PAI-3; Jan 11: PAI-3; Jan 12: PAI-3; Jan 13: PAI-3; Jan 14: PAI-3; Jan 15: PAI-3; Jan 16: PAI-3
|  | Flooring | Jan 15: FLO-7; Jan 16: FLO-7
|  | Hallways and Stairwells | Feb 11: SPR-1; Feb 12: SPR-1; Feb 13: SPR-1
|  | Mechanical Systems | Feb 11: MCH-3; Feb 12: MCH-3; Feb 13: MCH-3
|  | Structural | Jan 03: PAI-4; Jan 04: PAI-4; Jan 05: PAI-4; Jan 06: PAI-4; Jan 07: PAI-4
| Level 2 | Base and Hardware | Jan 17: CAR-1; Jan 18: CAR-1; Jan 19: CAR-1; Jan 20: CAR-1; Jan 21: CAR-1; Jan 22: CAR-1; Jan 23: CAR-1; Jan 24: CAR-1
|  | Bathrooms | Aug 19: PLU-3; Aug 20: PLU-3; Aug 21: PLU-3; Aug 22: PLU-3; Aug 23: PLU-3
|  | Cabinets | Jan 13: CAR-6; Jan 14: CAR-6; Jan 15: CAR-6; Jan 16: CAR-6; Jan 17: CAR-6
|  | Ceilings | Nov 26: FRA-3; Nov 27: FRA-3; Nov 28: FRA-3; Nov 29: FRA-3; Nov 30: FRA-3; Dec 01: FRA-3; Dec 02: FRA-3; Dec 16: FIN-2; Dec 17: FIN-2
|  | Common Areas | Aug 21: FRA-1; Aug 22: FRA-1; Aug 23: FRA-1; Aug 24: FRA-1; Aug 25: FRA-1; Aug 26: FRA-1; Aug 27: FRA-1; Feb 27: CX-
|  | Countertops | Jan 16: FLO-3; Jan 17: FLO-3; Jan 18: FLO-3; Jan 19: FLO-3; Jan 20: FLO-3; Jan 21: CAR-5; Jan 22: CAR-5; Jan 23: CAR-5; Jan 24: CAR-5; Jan 25: CAR-5; Jan 26: CAR-5; Jan 27: CAR-5; Jan 28: CAR-5; Jan 29: CAR-5; Jan 30: CAR-5; Jan 31: CAR-5; Feb 01: CAR-5; Feb 02: CAR-5; Feb 03: CAR-5; Feb 04: CAR-5; Feb 05: CAR-5; Feb 06: CAR-5; Feb 07: CAR-5
|  | Doors and Frames | Dec 23: CAR-4; Dec 24: CAR-4; Dec 25: CAR-4; Dec 26: CAR-4; Dec 27: CAR-4; Dec 28: CAR-4; Dec 29: CAR-4; Dec 30: CAR-4; Dec 31: CAR-4; Jan 01: CAR-4; Jan 02: CAR-4; Jan 03: CAR-4
|  | Electrical Systems | Feb 07: ELE-2; Feb 08: ELE-2; Feb 09: ELE-2; Feb 10: ELE-2; Feb 11: ELE-2; Feb 12: ELE-2; Feb 13: ELE-2
|  | Fire Systems | Dec 18: PAI-4; Dec 19: PAI-4; Dec 20: PAI-4; Dec 21: PAI-4; Dec 22: PAI-4; Dec 23: PAI-4; Dec 27: PAI-3; Dec 28: PAI-3; Dec 29: PAI-3; Dec 30: PAI-3; Dec 31: PAI-3; Jan 01: PAI-3; Jan 02: PAI-3; Jan 03: PAI-3; Feb 07: SPR-1; Feb 08: SPR-1; Feb 09: SPR-1; Feb 10: SPR-1; Feb 11: SPR-1; Feb 12: SPR-1; Feb 13: SPR-1
|  | Flooring | Apr 19: FRA-; Apr 20: FRA-; Apr 21: FRA-; Apr 22: FRA-; Apr 23: FRA-; Apr 24: FRA-; Apr 25: FRA-; Apr 26: FRA-; Apr 27: FRA-; Apr 28: FRA-; Apr 29: FRA-; Apr 30: FRA-; May 01: FRA-; May 02: FRA-; May 03: FRA-; May 04: FRA-; May 05: FRA-; May 06: FRA-; May 07: FRA-; May 08: FRA-; May 09: FRA-; May 10: FRA-; May 11: FRA-; May 12: FRA-; May 13: FRA-; Jul 24: FLO-5; Jul 25: FLO-5; Jul 26: FLO-5; Dec 16: FLO-4; Dec 17: FLO-4; Dec 18: FLO-4; Dec 19: FLO-4; Dec 20: FLO-4; Dec 21: FLO-4; Dec 22: FLO-4; Dec 23: FLO-4; Dec 24: FLO-4; Dec 25: FLO-4; Dec 26: FLO-4; Dec 27: FLO-4; Dec 28: FLO-4; Dec 29: FLO-4; Dec 30: FLO-4; Dec 31: FLO-4; Jan 01: FLO-4; Jan 02: FLO-4; Jan 03: FLO-4; Jan 04: FLO-4; Jan 05: FLO-4; Jan 06: FLO-4; Jan 07: FLO-4; Jan 08: FLO-4; Jan 09: FLO-4; Jan 10: FLO-4; Jan 11: FLO-4; Jan 12: FLO-4; Jan 13: FLO-4; Jan 14: FLO-4; Jan 15: FLO-4; Jan 16: FLO-4; Jan 17: FLO-4; Jan 18: FLO-4; Jan 19: FLO-4; Jan 20: FLO-4; Jan 21: FLO-4; Jan 22: FLO-4; Jan 23: FLO-4; Jan 24: FLO-4; Jan 25: FLO-4; Jan 26: FLO-4; Jan 27: FLO-4; Jan 28: FLO-4; Jan 29: FLO-4; Jan 30: FLO-4; Jan 31: FLO-4; Feb 01: FLO-4; Feb 02: FLO-4; Feb 03: FLO-4; Feb 04: FLO-4; Feb 05: FLO-4; Feb 06: FLO-4; Feb 07: FLO-4; Feb 08: FLO-4; Feb 09: FLO-4; Feb 10: FLO-4; Feb 11: FLO-4; Feb 12: FLO-4; Feb 13: FLO-4; Feb 14: FLO-4; Feb 15: FLO-4; Feb 16: FLO-4; Feb 17: FLO-4; Feb 18: FLO-4; Feb 19: FLO-4; Feb 20: FLO-4; Feb 21: FLO-4; Feb 22: FLO-4; Feb 23: FLO-4; Feb 24: FLO-4; Feb 25: FLO-4; Feb 26: FLO-4; Feb 27: FLO-4; Feb 28: FLO-4
[207 empty] | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | [238 empty] | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7
|  | Hallways and Stairwells | Aug 26: SPR-3; Aug 27: SPR-3; Aug 28: SPR-3; Aug 29: SPR-3; Aug 30: SPR-3; Aug 31: SPR-3; Sep 01: SPR-3; Sep 02: SPR-3; Sep 03: SPR-3; Sep 04: SPR-3; Sep 05: SPR-3; Sep 06: SPR-3; Nov 01: MCH-4; Nov 02: MCH-4; Nov 03: MCH-4; Nov 04: MCH-4; Nov 05: MCH-4; Nov 06: MCH-4; Nov 07: MCH-4; Nov 08: MCH-4; Nov 09: MCH-4; Nov 10: MCH-4; Nov 11: MCH-4; Nov 12: MCH-4; Nov 13: MCH-4; Nov 14: MCH-4; Nov 15: MCH-4; Nov 28: DRY-4; Nov 29: DRY-4; Nov 30: DRY-4; Dec 01: DRY-4; Dec 02: DRY-4; Dec 03: DRY-4; Dec 04: DRY-4; Dec 05: DRY-11; Dec 06: DRY-11; Dec 07: DRY-11; Dec 08: DRY-11; Dec 09: DRY-11; Dec 10: DRY-11; Dec 11: DRY-11; Dec 12: DRY-11; Dec 13: DRY-11; Dec 14: DRY-11; Dec 15: DRY-11; Dec 16: DRY-11; Dec 17: DRY-11; Dec 18: DRY-11; Dec 19: DRY-11; Dec 23: FLO-2; Feb 24: CL-1; Feb 25: CL-1; Feb 26: CL-1; Feb 27: CL-1
[410 empty] | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3
|  | Mechanical Systems | Feb 07: MCH-3; Feb 08: MCH-3; Feb 09: MCH-3; Feb 10: MCH-3; Feb 11: MCH-3; Feb 12: MCH-3; Feb 13: MCH-3
|  | Suites | Jul 18: DRY-7; Jul 19: DRY-7; Jul 20: DRY-7; Jul 21: DRY-7; Jul 22: DRY-7; Aug 12: RI-1; Aug 13: RI-1; Aug 14: RI-1; Aug 15: RI-1; Aug 16: RI-1; Aug 17: RI-1; Aug 18: RI-1; Aug 19: RI-1; Aug 20: RI-1; Aug 21: RI-1; Aug 22: RI-1; Aug 23: RI-1; Aug 24: RI-1; Aug 25: RI-1; Aug 26: RI-1; Aug 27: RI-1; Aug 28: RI-1; Aug 29: RI-1; Aug 30: RI-1; Aug 31: RI-1; Sep 01: RI-1; Sep 02: RI-1; Sep 03: RI-1; Sep 04: RI-1; Sep 05: RI-1; Sep 06: RI-1; Sep 07: RI-1; Sep 08: RI-1; Sep 09: RI-1; Sep 10: RI-1; Sep 11: RI-1; Sep 12: RI-1; Sep 13: RI-1; Sep 14: RI-1; Sep 15: RI-1; Sep 16: RI-1; Sep 17: RI-1; Sep 18: RI-1; Sep 19: RI-1; Sep 20: RI-1; Sep 21: RI-1; Sep 22: RI-1; Sep 23: RI-1; Sep 24: RI-1; Sep 25: RI-1; Sep 26: RI-1; Sep 27: RI-1; Sep 28: RI-1; Sep 29: RI-1; Sep 30: RI-1; Oct 01: RI-1; Oct 02: RI-1; Oct 03: RI-1; Oct 04: RI-1; Oct 05: RI-1; Oct 06: RI-1; Oct 07: RI-1; Oct 08: RI-1; Oct 09: RI-1; Oct 10: RI-1; Oct 11: RI-1; Oct 12: RI-1; Oct 13: RI-1; Oct 14: RI-1; Oct 15: RI-1; Oct 16: RI-1; Oct 17: RI-1; Oct 18: RI-1; Oct 19: RI-1; Oct 20: RI-1; Oct 21: RI-1; Oct 22: RI-1; Oct 23: RI-1; Oct 24: RI-1; Oct 25: RI-1; Oct 26: RI-1; Oct 27: RI-1; Oct 28: RI-1; Oct 29: RI-1; Oct 30: RI-1; Oct 31: RI-1; Nov 01: RI-1; Nov 02: RI-1; Nov 03: RI-1; Nov 04: RI-1; Nov 05: RI-1; Nov 06: RI-1; Nov 07: RI-1; Nov 08: RI-1; Nov 09: RI-1; Nov 10: RI-1; Nov 11: RI-1; Nov 12: RI-1; Nov 13: RI-1; Nov 14: RI-1; Nov 15: RI-1; Nov 16: RI-1; Nov 17: RI-1; Nov 18: RI-1; Nov 19: RI-1; Nov 20: RI-1; Nov 21: RI-1; Nov 22: RI-1; Nov 23: RI-1; Nov 24: RI-1; Nov 25: RI-1; Nov 26: RI-1; Nov 27: RI-1; Nov 28: RI-1; Nov 29: RI-1; Nov 30: RI-1; Dec 01: RI-1; Dec 02: RI-1; Dec 03: RI-1; Dec 04: RI-1; Dec 05: RI-1; Dec 06: RI-1; Dec 07: RI-1; Dec 08: RI-1; Dec 09: RI-1; Dec 10: RI-1; Dec 11: RI-1; Dec 12: RI-1; Dec 13: RI-1; Dec 14: RI-1; Dec 15: RI-1; Dec 16: RI-1; Dec 17: RI-1; Dec 18: RI-1; Dec 19: RI-1; Dec 20: RI-1; Dec 21: RI-1; Dec 22: RI-1; Dec 23: RI-1; Dec 24: RI-1; Dec 25: RI-1; Dec 26: RI-1; Dec 27: RI-1; Dec 28: RI-1; Dec 29: RI-1; Dec 30: RI-1; Dec 31: RI-1; Jan 01: RI-1; Jan 02: RI-1; Jan 03: RI-1
[336 empty] | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | [55 empty] | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | [19 empty] | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10
[410 empty] | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3
|  | Walls | Nov 28: DRY-4; Nov 29: DRY-4; Nov 30: DRY-4; Dec 01: DRY-4; Dec 02: DRY-4; Dec 03: DRY-4; Dec 04: DRY-4
|  | Walls / Ceilings | Aug 12: DRY-9; Aug 13: DRY-9; Aug 14: DRY-9; Aug 15: DRY-9; Aug 16: DRY-9; Aug 17: DRY-9; Aug 18: DRY-9; Aug 19: DRY-9; Aug 20: DRY-9; Aug 21: DRY-9; Aug 22: DRY-9; Aug 23: DRY-9; Aug 24: DRY-9; Aug 25: DRY-9; Aug 26: DRY-9; Aug 27: DRY-9; Aug 28: DRY-9; Aug 29: DRY-9; Aug 30: DRY-4; Aug 31: DRY-4; Sep 01: DRY-4; Sep 02: DRY-4; Sep 03: DRY-4; Sep 04: DRY-4; Nov 25: DRY-5
| Level 3 | Base and Hardware | Jan 08: CAR-1; Jan 09: CAR-1; Jan 10: CAR-1; Jan 11: CAR-1; Jan 12: CAR-1; Jan 13: CAR-1
|  | Bathrooms | Aug 19: PLU-3; Aug 20: PLU-3; Aug 21: PLU-3; Aug 22: PLU-3; Aug 23: PLU-3
|  | Cabinets | Dec 18: CAR-2; Dec 19: CAR-2; Dec 20: CAR-2; Dec 21: CAR-2; Dec 22: CAR-2; Dec 23: CAR-2; Dec 24: CAR-2; Dec 25: CAR-2; Dec 26: CAR-2; Dec 27: CAR-2; Dec 28: CAR-2; Dec 29: CAR-2; Dec 30: CAR-2; Dec 31: CAR-2; Jan 01: CAR-2; Jan 02: CAR-2; Jan 03: CAR-2; Jan 04: CAR-2; Jan 05: CAR-2; Jan 06: CAR-2; Jan 07: CAR-2; Jan 08: CAR-2; Jan 09: CAR-2; Jan 10: CAR-2
|  | Ceilings | Nov 12: FRA-3; Nov 13: FRA-3; Nov 14: FRA-3; Nov 15: FRA-3; Nov 16: FRA-3; Nov 17: FRA-3; Nov 18: FRA-3; Dec 02: FIN-2; Dec 03: FIN-2
|  | Closets | Dec 12: CAR-6; Dec 13: CAR-6; Dec 14: CAR-6; Dec 15: CAR-6; Dec 16: CAR-6; Dec 17: CAR-6
|  | Common Areas | Feb 11: CL-1; Feb 12: CL-1; Feb 13: CL-1; Feb 14: CL-1; Feb 15: CL-1; Feb 16: CL-1; Feb 17: CL-1
CX-
[511 empty] | CL-2 | CL-2
|  | Countertops | Jan 08: FLO-; Jan 09: FLO-; Jan 10: FLO-
[473 empty] | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5 | CAR-5
|  | Doors and Frames | Dec 09: CAR-4; Dec 10: CAR-4; Dec 11: CAR-4; Dec 12: CAR-4; Dec 13: CAR-4
|  | Electrical Systems | Jan 29: ELE-2; Jan 30: ELE-2; Jan 31: ELE-2; Feb 01: ELE-2; Feb 02: ELE-2; Feb 03: ELE-2; Feb 04: ELE-2
|  | Fire Systems | Dec 12: PAI-3; Dec 13: PAI-3; Dec 14: PAI-3; Dec 15: PAI-3; Dec 16: PAI-3; Dec 17: PAI-3; Jan 29: SPR-1; Jan 30: SPR-1; Jan 31: SPR-1; Feb 01: SPR-1; Feb 02: SPR-1; Feb 03: SPR-1; Feb 04: SPR-1
|  | Flooring | May 28: FRA-; May 29: FRA-; May 30: FRA-; May 31: FRA-; Jun 01: FRA-; Jun 02: FRA-; Jun 03: FRA-; Jun 04: FRA-; Jun 05: FRA-; Jun 06: FRA-; Jun 07: FRA-; Jul 29: FLO-5; Jul 30: FLO-5; Jul 31: FLO-5; Dec 02: FLO-3; Dec 03: FLO-3; Dec 04: FLO-3; Dec 05: FLO-3; Dec 06: FLO-3; Dec 07: FLO-3; Dec 08: FLO-3; Dec 09: FLO-3; Dec 10: FLO-3; Dec 11: FLO-3; Dec 12: FLO-3; Dec 13: FLO-3; Dec 14: FLO-3; Dec 15: FLO-3; Dec 16: FLO-3; Dec 17: FLO-3; Dec 18: FLO-3; Dec 19: FLO-3; Dec 20: FLO-3; Dec 21: FLO-3; Dec 22: FLO-3; Dec 23: FLO-3; Dec 24: FLO-3; Dec 25: FLO-3; Dec 26: FLO-3; Dec 27: FLO-3; Dec 28: FLO-3; Dec 29: FLO-3; Dec 30: FLO-3; Dec 31: FLO-3; Jan 01: FLO-3; Jan 02: FLO-3; Jan 03: FLO-3; Jan 04: FLO-3; Jan 05: FLO-3; Jan 06: FLO-3; Jan 07: FLO-3; Jan 08: FLO-3; Jan 09: FLO-3; Jan 10: FLO-3; Jan 11: FLO-3; Jan 12: FLO-3; Jan 13: FLO-3; Jan 14: FLO-3; Jan 15: FLO-3; Jan 16: FLO-3; Jan 17: FLO-3; Jan 18: FLO-3; Jan 19: FLO-3; Jan 20: FLO-3; Jan 21: FLO-3; Jan 22: FLO-3; Jan 23: FLO-3; Jan 24: FLO-3; Jan 25: FLO-3; Jan 26: FLO-3; Jan 27: FLO-3; Jan 28: FLO-3; Jan 29: FLO-3; Jan 30: FLO-3; Jan 31: FLO-3; Feb 01: FLO-3; Feb 02: FLO-3; Feb 03: FLO-3; Feb 04: FLO-3; Feb 05: FLO-3; Feb 06: FLO-3; Feb 07: FLO-3; Feb 08: FLO-3; Feb 09: FLO-3; Feb 10: FLO-3; Feb 11: FLO-3; Feb 12: FLO-3; Feb 13: FLO-3; Feb 14: FLO-3; Feb 15: FLO-3; Feb 16: FLO-3; Feb 17: FLO-3; Feb 18: FLO-3
[246 empty] | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | [143 empty] | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7 | FLO-7
|  | Hallways and Stairwells | Sep 09: SPR-3; Sep 10: SPR-3; Sep 11: SPR-3; Sep 12: SPR-3; Sep 13: SPR-3; Sep 14: SPR-3; Sep 15: SPR-3; Sep 16: SPR-3; Sep 17: SPR-3; Sep 18: SPR-3; Sep 19: SPR-3; Sep 20: SPR-3; Oct 28: MCH-4; Oct 29: MCH-4; Oct 30: MCH-4; Oct 31: MCH-4; Nov 01: MCH-4; Nov 02: MCH-4; Nov 03: MCH-4; Nov 04: MCH-4; Nov 05: MCH-4; Nov 06: MCH-4; Nov 07: MCH-4; Nov 15: DRY-8; Nov 16: DRY-8; Nov 17: DRY-8; Nov 18: DRY-8; Nov 19: DRY-8; Nov 20: DRY-8; Nov 21: DRY-8; Nov 22: DRY-8
[351 empty] | FRA-1 | FRA-1 | FRA-1 | FRA-1 | FRA-1 | FRA-1 | FRA-1 | [41 empty] | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | [13 empty] | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11
|  | Mechanical Systems | Jan 29: MCH-3; Jan 30: MCH-3; Jan 31: MCH-3; Feb 01: MCH-3; Feb 02: MCH-3; Feb 03: MCH-3; Feb 04: MCH-3
|  | Suites | Jul 23: FRA-; Jul 24: FRA-; Jul 25: FRA-; Jul 26: FRA-; Aug 19: RI-1; Aug 20: RI-1; Aug 21: RI-1; Aug 22: RI-1; Aug 23: RI-1; Aug 24: RI-1; Aug 25: RI-1; Aug 26: RI-1; Aug 27: RI-1; Aug 28: RI-1; Aug 29: RI-1; Aug 30: RI-1; Aug 31: RI-1; Sep 01: RI-1; Sep 02: RI-1; Sep 03: RI-1; Sep 04: RI-1; Sep 05: RI-1; Sep 06: RI-1; Sep 07: RI-1; Sep 08: RI-1; Sep 09: RI-1; Sep 10: RI-1; Sep 11: RI-1; Sep 12: RI-1; Sep 13: RI-1; Sep 14: RI-1; Sep 15: RI-1; Sep 16: RI-1; Sep 17: RI-1; Sep 18: RI-1; Sep 19: RI-1; Sep 20: RI-1; Sep 21: RI-1; Sep 22: RI-1; Sep 23: RI-1; Sep 24: RI-1; Sep 25: RI-1; Sep 26: RI-1; Sep 27: RI-1; Sep 28: RI-1; Sep 29: RI-1; Sep 30: RI-1; Oct 01: RI-1; Oct 02: RI-1; Oct 03: RI-1; Oct 04: RI-1; Oct 05: RI-1; Oct 06: RI-1; Oct 07: RI-1; Oct 08: RI-1; Oct 09: RI-1; Oct 10: RI-1; Oct 11: RI-1; Oct 12: RI-1; Oct 13: RI-1; Oct 14: RI-1; Oct 15: RI-1; Oct 16: RI-1; Oct 17: RI-1; Oct 18: RI-1; Oct 19: RI-1; Oct 20: RI-1; Oct 21: RI-1; Oct 22: RI-1; Oct 23: RI-1; Oct 24: RI-1; Oct 25: RI-1; Oct 26: RI-1; Oct 27: RI-1; Oct 28: RI-1; Oct 29: RI-1; Oct 30: RI-1; Oct 31: RI-1; Nov 01: RI-1; Nov 02: RI-1; Nov 03: RI-1; Nov 04: RI-1; Nov 05: RI-1; Nov 06: RI-1; Nov 07: RI-1; Nov 08: RI-1; Nov 09: RI-1; Nov 10: RI-1; Nov 11: RI-1; Nov 12: RI-1; Nov 13: RI-1; Nov 14: RI-1; Nov 15: RI-1; Nov 16: RI-1; Nov 17: RI-1; Nov 18: RI-1; Nov 19: RI-1; Nov 20: RI-1; Nov 21: RI-1; Nov 22: RI-1; Nov 23: RI-1; Nov 24: RI-1; Nov 25: RI-1; Nov 26: RI-1; Nov 27: RI-1; Nov 28: RI-1; Nov 29: RI-1; Nov 30: RI-1; Dec 01: RI-1; Dec 02: RI-1; Dec 03: RI-1; Dec 04: RI-1; Dec 05: RI-1; Dec 06: RI-1; Dec 07: RI-1; Dec 08: RI-1; Dec 09: RI-1; Dec 10: RI-1; Dec 11: RI-1; Dec 12: RI-1; Dec 13: RI-1
[350 empty] | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | [37 empty] | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | [14 empty] | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10
[399 empty] | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3
|  | Walls / Ceilings | Aug 30: DRY-9; Aug 31: DRY-9; Sep 01: DRY-9; Sep 02: DRY-9; Sep 03: DRY-9; Sep 04: DRY-9; Sep 05: DRY-9; Sep 11: DRY-4; Sep 12: DRY-4; Sep 13: DRY-4; Sep 14: DRY-4; Sep 15: DRY-4; Sep 16: DRY-4; Nov 11: DRY-5; Nov 15: DRY-8; Nov 16: DRY-8; Nov 17: DRY-8; Nov 18: DRY-8; Nov 19: DRY-8; Nov 20: DRY-8; Nov 21: DRY-8; Nov 22: DRY-8; Dec 05: PAI-4; Dec 06: PAI-4; Dec 07: PAI-4; Dec 08: PAI-4; Dec 09: PAI-4; Dec 10: PAI-4
[417 empty] | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | DRY-8 | [17 empty] | FLO-2
| Level 4 | Base and Hardware | Dec 20: CAR-1; Dec 21: CAR-1; Dec 22: CAR-1; Dec 23: CAR-1; Dec 24: CAR-1; Dec 25: CAR-1; Dec 26: CAR-1; Dec 27: CAR-1; Dec 28: CAR-1; Dec 29: CAR-1; Dec 30: CAR-1; Dec 31: CAR-1; Jan 01: CAR-1; Jan 02: CAR-1; Jan 03: CAR-1
|  | Bathrooms | Aug 19: PLU-3; Aug 20: PLU-3; Aug 21: PLU-3; Aug 22: PLU-3; Aug 23: PLU-3
|  | Cabinets | Dec 11: CAR-2; Dec 12: CAR-2; Dec 13: CAR-2; Dec 14: CAR-2; Dec 15: CAR-2; Dec 16: CAR-2; Dec 17: CAR-2; Dec 18: CAR-2
|  | Ceilings | Aug 05: RI-1; Aug 06: RI-1; Aug 07: RI-1; Aug 08: RI-1; Aug 09: RI-1; Aug 10: RI-1; Aug 11: RI-1; Aug 12: RI-1; Aug 13: RI-1; Aug 14: RI-1; Aug 15: RI-1; Aug 16: RI-1; Aug 17: RI-1; Aug 18: RI-1; Aug 19: RI-1; Aug 20: RI-1; Aug 21: RI-1; Aug 22: RI-1; Aug 23: RI-1; Aug 24: RI-1; Aug 25: RI-1; Aug 26: RI-1; Aug 27: RI-1; Aug 28: RI-1; Aug 29: RI-1; Aug 30: RI-1; Aug 31: RI-1; Sep 01: RI-1; Sep 02: RI-1; Sep 03: RI-1; Sep 04: RI-1; Sep 05: RI-1; Sep 06: RI-1; Sep 07: RI-1; Sep 08: RI-1; Sep 09: RI-1; Sep 10: RI-1; Sep 11: RI-1; Sep 12: RI-1; Sep 13: RI-1; Sep 14: RI-1; Sep 15: RI-1; Sep 16: RI-1; Sep 17: RI-1; Sep 18: RI-1; Sep 19: RI-1; Sep 20: RI-1; Sep 21: RI-1; Sep 22: RI-1; Sep 23: RI-1; Sep 24: RI-1; Sep 25: RI-1; Sep 26: RI-1; Sep 27: RI-1; Sep 28: RI-1; Sep 29: RI-1; Sep 30: RI-1; Oct 01: RI-1; Oct 02: RI-1; Oct 03: RI-1; Oct 04: RI-1; Oct 05: RI-1; Oct 06: RI-1; Oct 07: RI-1; Nov 26: FIN-2; Nov 27: FIN-2; Nov 29: FRA-3; Nov 30: FRA-3; Dec 01: FRA-3; Dec 02: FRA-3; Dec 03: FRA-3; Dec 04: FRA-3; Dec 05: FRA-3
[346 empty] | FLO-12 | FLO-12 |  |  | FLO-9 | FLO-9 | DRY-6 | DRY-6 | DRY-6 | DRY-6 | DRY-6 | DRY-6 | DRY-6 | [5 empty] | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11
|  | Closets | Dec 05: PAI-3; Dec 06: PAI-3; Dec 07: PAI-3; Dec 08: PAI-3; Dec 09: PAI-3; Dec 10: PAI-3
[437 empty] | CAR-6 | CAR-6 | CAR-6 | CAR-6 | CAR-6 | CAR-6
|  | Common Areas | Sep 23: FRA-1; Sep 24: FRA-1; Sep 25: FRA-1; Sep 26: FRA-1; Sep 27: FRA-1; Feb 03: CL-1; Feb 04: CL-1; Feb 05: CL-1; Feb 06: CL-1; Feb 07: CL-1
CX-
|  | Countertops | Dec 17: FLO-4; Dec 18: FLO-4; Dec 19: FLO-4; Jan 02: CAR-5; Jan 03: CAR-5; Jan 04: CAR-5; Jan 05: CAR-5; Jan 06: CAR-5; Jan 07: CAR-5; Jan 08: CAR-5; Jan 09: CAR-5; Jan 10: CAR-5; Jan 11: CAR-5; Jan 12: CAR-5; Jan 13: CAR-5; Jan 14: CAR-5; Jan 15: CAR-5; Jan 16: CAR-5; Jan 17: CAR-5; Jan 18: CAR-5; Jan 19: CAR-5; Jan 20: CAR-5; Jan 21: CAR-5
|  | Doors and Frames | Dec 02: CAR-4; Dec 03: CAR-4; Dec 04: CAR-4; Dec 05: CAR-4; Dec 06: CAR-4
|  | Electrical Systems | Jan 21: ELE-2; Jan 22: ELE-2; Jan 23: ELE-2; Jan 24: ELE-2; Jan 25: ELE-2; Jan 26: ELE-2; Jan 27: ELE-2
|  | Exterior Walls | Oct 21: RI-2; Oct 22: RI-2; Oct 23: RI-2; Oct 24: RI-2; Oct 25: RI-2; Oct 26: RI-2; Oct 27: RI-2; Oct 28: RI-2; Oct 29: RI-2; Oct 30: RI-2; Oct 31: RI-2; Nov 08: DRY-8; Nov 09: DRY-8; Nov 10: DRY-8; Nov 11: DRY-8; Nov 12: DRY-8; Nov 13: DRY-8; Nov 14: DRY-8; Nov 15: DRY-8
[417 empty] | FLO-6 | FLO-6 | FLO-6 | FLO-6 | FLO-6 | FLO-6 | FLO-6 | FLO-6 | FLO-6 | FLO-6 | FLO-6
|  | Fire Systems | Nov 01: DRY-5; Nov 28: PAI-4; Nov 29: PAI-4; Nov 30: PAI-4; Dec 01: PAI-4; Dec 02: PAI-4; Dec 03: PAI-4; Jan 21: SPR-1; Jan 22: SPR-1; Jan 23: SPR-1; Jan 24: SPR-1; Jan 25: SPR-1; Jan 26: SPR-1; Jan 27: SPR-1
|  | Flooring | Aug 01: FLO-5; Aug 02: FLO-5; Dec 09: FLO-7; Dec 10: FLO-7; Dec 11: FLO-7; Dec 12: FLO-7; Dec 13: FLO-7; Dec 14: FLO-7; Dec 15: FLO-7; Dec 16: FLO-7
|  | Framing | Nov 04: INS-1
|  | Hallways and Stairwells | Sep 23: SPR-3; Sep 24: SPR-3; Sep 25: SPR-3; Sep 26: SPR-3; Sep 27: SPR-3; Sep 28: SPR-3; Sep 29: SPR-3; Sep 30: SPR-3; Oct 21: MCH-4; Oct 22: MCH-4; Oct 23: MCH-4; Oct 24: MCH-4; Oct 25: MCH-4; Nov 08: DRY-8; Nov 09: DRY-8; Nov 10: DRY-8; Nov 11: DRY-8; Nov 12: DRY-8; Nov 13: DRY-8; Nov 14: DRY-8; Nov 15: DRY-8
[392 empty] | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | [14 empty] | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11 | DRY-11
|  | Suites | Jul 29: FLO-11; Jul 30: FLO-11; Jul 31: FLO-11; Aug 01: FLO-11; Aug 19: RI-1; Aug 20: RI-1; Aug 21: RI-1; Aug 22: RI-1; Aug 23: RI-1; Aug 24: RI-1; Aug 25: RI-1; Aug 26: RI-1; Aug 27: RI-1; Aug 28: RI-1; Aug 29: RI-1; Aug 30: RI-1; Aug 31: RI-1; Sep 01: RI-1; Sep 02: RI-1; Sep 03: RI-1; Sep 04: RI-1; Sep 05: RI-1; Sep 06: RI-1; Sep 07: RI-1; Sep 08: RI-1; Sep 09: RI-1; Sep 10: RI-1; Sep 11: RI-1; Sep 12: RI-1; Sep 13: RI-1; Sep 14: RI-1; Sep 15: RI-1; Sep 16: RI-1; Sep 17: RI-1; Sep 18: RI-1; Sep 19: RI-1; Sep 20: RI-1; Sep 21: RI-1; Sep 22: RI-1; Sep 23: RI-1; Sep 24: RI-1; Sep 25: RI-1; Sep 26: RI-1; Sep 27: RI-1; Sep 28: RI-1; Sep 29: RI-1; Sep 30: RI-1; Oct 01: RI-1; Oct 02: RI-1; Oct 03: RI-1; Oct 04: RI-1; Oct 05: RI-1; Oct 06: RI-1; Oct 07: RI-1; Oct 08: RI-1; Oct 09: RI-1; Oct 10: RI-1; Oct 11: RI-1; Oct 12: RI-1; Oct 13: RI-1; Oct 14: RI-1; Oct 15: RI-1; Oct 16: RI-1; Oct 17: RI-1; Oct 18: RI-1; Oct 19: RI-1; Oct 20: RI-1; Oct 21: RI-1; Oct 22: RI-1; Oct 23: RI-1; Oct 24: RI-1; Oct 25: RI-1; Oct 26: RI-1; Oct 27: RI-1; Oct 28: RI-1; Oct 29: RI-1; Oct 30: RI-1; Oct 31: RI-1; Nov 01: RI-1; Nov 02: RI-1; Nov 03: RI-1; Nov 04: RI-1; Nov 05: RI-1; Nov 06: RI-1; Nov 07: RI-1; Nov 08: RI-1; Nov 09: RI-1; Nov 10: RI-1; Nov 11: RI-1; Nov 12: RI-1; Nov 13: RI-1; Nov 14: RI-1; Nov 15: RI-1; Nov 16: RI-1; Nov 17: RI-1; Nov 18: RI-1; Nov 19: RI-1; Nov 20: RI-1; Nov 21: RI-1; Nov 22: RI-1; Nov 23: RI-1; Nov 24: RI-1; Nov 25: RI-1; Nov 26: RI-1; Nov 27: RI-1; Nov 28: RI-1; Nov 29: RI-1; Nov 30: RI-1; Dec 01: RI-1; Dec 02: RI-1; Dec 03: RI-1; Dec 04: RI-1; Dec 05: RI-1; Dec 06: RI-1; Jan 21: MCH-3; Jan 22: MCH-3; Jan 23: MCH-3; Jan 24: MCH-3; Jan 25: MCH-3; Jan 26: MCH-3; Jan 27: MCH-3; Feb 07: CL-2; Feb 08: CL-2; Feb 09: CL-2; Feb 10: CL-2
[364 empty] | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | SPR-3 | [20 empty] | MCH-4 | MCH-4 | MCH-4 | MCH-4 | MCH-4 | [20 empty] | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10 | DRY-10
[392 empty] | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | ELE-3 | [25 empty] | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3 | FIN-3
|  | Walls / Ceilings | Jun 19: FRA-; Jun 20: FRA-; Jun 21: FRA-; Jun 22: FRA-; Jun 23: FRA-; Jun 24: FRA-; Jun 25: FRA-; Jun 26: FRA-; Jun 27: FRA-; Jun 28: FRA-; Jun 29: FRA-; Jun 30: FRA-; Jul 01: FRA-; Jul 02: FRA-; Jul 03: FRA-; Jul 04: FRA-; Jul 05: FRA-; Sep 18: DRY-9; Sep 19: DRY-9; Sep 20: DRY-9; Sep 21: DRY-9; Sep 22: DRY-9; Sep 23: DRY-9; Sep 24: DRY-9; Sep 25: DRY-9; Sep 26: DRY-9; Sep 27: DRY-4; Sep 28: DRY-4; Sep 29: DRY-4; Sep 30: DRY-4; Oct 01: DRY-4; Oct 02: DRY-4; Nov 08: DRY-8; Nov 09: DRY-8; Nov 10: DRY-8; Nov 11: DRY-8; Nov 12: DRY-8; Nov 13: DRY-8; Nov 14: DRY-8; Nov 15: DRY-8; Dec 02: FLO-2; Dec 03: FLO-2
[268 empty] | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA-
| Parkade | Ceilings | Jun 17: PAI-1
|  | Parkade | Apr 11: FRA-; Apr 12: FRA-; Apr 13: FRA-; Apr 14: FRA-; Apr 15: FRA-; Jun 12: RI-1; Jun 13: RI-1; Jun 14: RI-1; Jun 15: RI-1; Jun 16: RI-1; Jun 17: RI-1; Jun 18: RI-1; Jun 19: RI-1; Jun 20: RI-1; Jun 21: RI-1; Jun 22: RI-1; Jun 23: RI-1; Jun 24: RI-1; Jun 25: RI-1; Jun 26: RI-1; Aug 19: FRA-4; Aug 20: FRA-4; Aug 21: FRA-4; Aug 22: FRA-4; Aug 23: FRA-4; Dec 13: DRY-10; Dec 14: DRY-10; Dec 15: DRY-10; Dec 16: DRY-10; Dec 17: DRY-10; Dec 18: DRY-10; Dec 19: DRY-10; Dec 20: DRY-10; Dec 21: DRY-10; Dec 22: DRY-10; Dec 23: DRY-10
[199 empty] | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | [243 empty] | FRA-2 | FRA-2 | FRA-2 | FRA-2 | FRA-2
| Roof | Roof | Jul 09: FRA-; Jul 10: FRA-; Jul 11: FRA-; Jul 12: FRA-; Jul 13: FRA-; Jul 14: FRA-; Jul 15: FRA-; Jul 16: FRA-; Jul 17: FRA-; Jul 18: FRA-; Jul 19: FRA-; Jul 20: FRA-; Jul 21: FRA-; Jul 22: FRA-; Jul 23: FRA-; Jul 24: FRA-; Jul 25: FRA-; Jul 26: FRA-; Jul 27: FRA-; Jul 28: FRA-; Jul 29: FRA-; Jul 30: FRA-; Jul 31: FRA-; Aug 01: FRA-; Aug 02: FRA-; Aug 03: FRA-; Aug 04: FRA-; Aug 05: FRA-; Aug 06: FRA-; Aug 07: FRA-
[288 empty] | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA- | FRA-
Note on D5: Activity Name: Assign Mobilization check list Phase: Mobilization Location: Mobilization Trade: Mobilization Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on D6: Activity Name: Assign Site Services Planning check list Phase: Mobilization Location: Mobilization Trade: Mobilization Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on D7: Activity Name: Assign Sub Contractor planning checklist Phase: Mobilization Location: Mobilization Trade: Mobilization Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on FA8: Activity Name: Rebar inspection Structural Engineer Phase: Foundation Location: Interior Bldg Trade: Inspection Start Date: 28-Feb-2024 End Date: 28-Feb-2024
Note on DL9: Activity Name: Geo Tech Engineer inspection Phase: Foundation Location: Interior Bldg Trade: Inspection Start Date: 18-Jan-2024 End Date: 18-Jan-2024
Note on CJ10: Activity Name: deliver rebar (footings and gradebeam only) Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 21-Dec-2023 End Date: 21-Dec-2023
Note on CN10: Activity Name: Install balcony piles Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 25-Dec-2023 End Date: 27-Dec-2023
Note on CY10: Activity Name: Measure corner offsets for excavation Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 05-Jan-2024 End Date: 05-Jan-2024
Note on DB10: Activity Name: Excavation Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 08-Jan-2024 End Date: 18-Jan-2024
Note on DM10: Activity Name: Form footings Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 19-Jan-2024 End Date: 24-Jan-2024
Note on DS10: Activity Name: Tie footing rebar Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 25-Jan-2024 End Date: 31-Jan-2024
Note on ED10: Activity Name: Pour footings Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 05-Feb-2024 End Date: 05-Feb-2024
Note on EE10: Activity Name: Ensure Sleeves for electrical are run in the grade beam prior to pouring Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 06-Feb-2024 End Date: 06-Feb-2024
Note on EN10: Activity Name: Build templates for Anchor bolts Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 15-Feb-2024 End Date: 15-Feb-2024
Note on EO10: Activity Name: Tie Grade beam rebar Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 16-Feb-2024 End Date: 26-Feb-2024
Note on EZ10: Activity Name: Assign pre concrete pour checklist Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 27-Feb-2024 End Date: 27-Feb-2024
Note on FB10: Activity Name: Pour grade beam Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 29-Feb-2024 End Date: 29-Feb-2024
Note on FC10: Activity Name: Assign pre back fill check list Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 01-Mar-2024 End Date: 01-Mar-2024
Note on FF10: Activity Name: Install underground insulation Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 04-Mar-2024 End Date: 05-Mar-2024
Note on FH10: Activity Name: Back fill exterior grade beam Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 06-Mar-2024 End Date: 07-Mar-2024
Note on IL10: Activity Name: Assign hollow core erection checklist Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 27-May-2024 End Date: 27-May-2024
Note on JI10: Activity Name: Deliver pakade slab rebar Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 19-Jun-2024 End Date: 19-Jun-2024
Note on KB10: Activity Name: Assign pre concrete pour checklist Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 08-Jul-2024 End Date: 08-Jul-2024
Note on LY10: Activity Name: Excavate areas Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 26-Aug-2024 End Date: 27-Aug-2024
Note on MH10: Activity Name: Tie rebar exterior pads Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 04-Sep-2024 End Date: 06-Sep-2024
Note on MN10: Activity Name: Pour exterior pads Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 10-Sep-2024 End Date: 10-Sep-2024
Note on PL10: Activity Name: Pour Gypcrete Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 25-Nov-2024 End Date: 26-Nov-2024
Note on PZ10: Activity Name: Rebar exterior sidewalks Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 09-Dec-2024 End Date: 11-Dec-2024
Note on QC10: Activity Name: Assign pre concrete pour checklist Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 12-Dec-2024 End Date: 16-Dec-2024
Note on QH10: Activity Name: Pour exterior sidewalks Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 17-Dec-2024 End Date: 19-Dec-2024
Note on CJ11: Activity Name: Order all Anchor bolts Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 21-Dec-2023 End Date: 21-Dec-2023
Note on DK11: Activity Name: Survey offsets, and footings Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 17-Jan-2024 End Date: 17-Jan-2024
Note on DM11: Activity Name: Foundation Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 19-Jan-2024 End Date: 29-Feb-2024
Note on FC11: Activity Name: Back fill foundation Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 01-Mar-2024 End Date: 14-Mar-2024
Note on LY11: Activity Name: Exterior concrete works Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 26-Aug-2024 End Date: 19-Dec-2024
Note on CJ12: Activity Name: Survey for balcony piles Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 21-Dec-2023 End Date: 22-Dec-2023
Note on EE12: Activity Name: Form grade beam Phase: Foundation Location: Interior Bldg Trade: Concrete Start Date: 06-Feb-2024 End Date: 14-Feb-2024
Note on DZ16: Activity Name: Rebar Inspection Structural Engineer Phase: Foundation Location: Interior Bldg Trade: Inspection Start Date: 01-Feb-2024 End Date: 01-Feb-2024
Note on GW17: Activity Name: Install hollowcore 2nd floor , Install backer rod & Grout 2nd floor Phase: Foundation Location: Level 2 Trade: Concrete Start Date: 16-Apr-2024 End Date: 18-Apr-2024
Note on GW18: Activity Name: Hollowcore 2nd floor Phase: Foundation Location: Level 2 Trade: Concrete Start Date: 16-Apr-2024 End Date: 17-Jun-2024
Note on IH19: Activity Name: Hollowcore 3rd floor Phase: Foundation Location: Level 3 Trade: Concrete Start Date: 23-May-2024 End Date: 28-May-2024
Note on IH20: Activity Name: Install hollow core 3rd floor, Install backer rod & grout Phase: Foundation Location: Level 3 Trade: Concrete Start Date: 23-May-2024 End Date: 28-May-2024
Note on JA21: Activity Name: Install hollow core 4th floor and grout Phase: Foundation Location: Level 4 Trade: Concrete Start Date: 11-Jun-2024 End Date: 12-Jun-2024
Note on JA22: Activity Name: Hollowcore 4th floor Phase: Foundation Location: Level 4 Trade: Concrete Start Date: 11-Jun-2024 End Date: 13-Jun-2024
Note on DB23: Activity Name: Dig footing and parkade foot print Phase: Foundation Location: Parkade Trade: Concrete Start Date: 08-Jan-2024 End Date: 16-Jan-2024
Note on FJ23: Activity Name: Back fill interior parkade Phase: Foundation Location: Parkade Trade: Concrete Start Date: 08-Mar-2024 End Date: 14-Mar-2024
Note on JJ23: Activity Name: Back fill and level parkade Phase: Foundation Location: Parkade Trade: Concrete Start Date: 20-Jun-2024 End Date: 26-Jun-2024
Note on JQ23: Activity Name: Pour parakde slab Phase: Foundation Location: Parkade Trade: Concrete Start Date: 27-Jun-2024 End Date: 10-Jul-2024
Note on JW24: Activity Name: Tie parkade rebar Phase: Foundation Location: Parkade Trade: Concrete Start Date: 03-Jul-2024 End Date: 05-Jul-2024
Note on KC24: Activity Name: Pour parkade floor Phase: Foundation Location: Parkade Trade: Concrete Start Date: 09-Jul-2024 End Date: 10-Jul-2024
Note on TG28: Activity Name: Building handover (PM to SM) checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on D29: Activity Name: Hold Pre Kick-Off meeting with Engineers and Trades people Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 02-Oct-2023
Note on CJ30: Activity Name: Schedule locates to be done Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 21-Dec-2023 End Date: 27-Dec-2023
Note on TH31: Activity Name: De mobilization (checklist) Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on D32: Activity Name: Assign hollow core ordering checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 28-Sep-2023
Note on DB32: Activity Name: 28. Assign Pre excavation checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 08-Jan-2024 End Date: 08-Jan-2024
Note on EA32: Activity Name: Assign pre-pour checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 02-Feb-2024 End Date: 02-Feb-2024
Note on FQ32: Activity Name: Assign structural steel checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 15-Mar-2024 End Date: 15-Mar-2024
Note on GW32: Activity Name: Assign framing checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 16-Apr-2024 End Date: 16-Apr-2024
Note on GZ32: Activity Name: Assign hollow core erection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 19-Apr-2024 End Date: 19-Apr-2024
Note on HY32: Activity Name: Assign framing check list Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 14-May-2024 End Date: 14-May-2024
Note on IZ32: Activity Name: Assign framing checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 10-Jun-2024 End Date: 10-Jun-2024
Note on JC32: Activity Name: Assign hollow core checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 13-Jun-2024 End Date: 13-Jun-2024
Note on JQ32: Activity Name: Assign parkade slab rough in checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 27-Jun-2024 End Date: 27-Jun-2024
Note on KB32: Activity Name: Assign framing checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 08-Jul-2024 End Date: 08-Jul-2024
Note on LF32: Activity Name: Assign roofing and water proofing checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 07-Aug-2024 End Date: 07-Aug-2024
Note on MM32: Activity Name: Assign conrete pour checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 09-Sep-2024 End Date: 09-Sep-2024
Note on MU32: Activity Name: Assign post decking install check list Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 17-Sep-2024 End Date: 17-Sep-2024
Note on NO32: Activity Name: Assign taping inspection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 07-Oct-2024 End Date: 07-Oct-2024
Note on OU32: Activity Name: Assign exterior wall pre board inspection check list Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 08-Nov-2024 End Date: 08-Nov-2024
Note on PB32: Activity Name: Assign taping inspection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on PL32: Activity Name: Assign gypcrete pour checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 25-Nov-2024 End Date: 25-Nov-2024
Note on PM32: Activity Name: Assign tower siding checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 26-Nov-2024 End Date: 26-Nov-2024
Note on PO32: Activity Name: Assign taping inspection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Nov-2024 End Date: 28-Nov-2024
Note on PV32: Activity Name: Assign taping inspection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 05-Dec-2024 End Date: 05-Dec-2024
Note on QJ32: Activity Name: Assign taping inspection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 19-Dec-2024 End Date: 19-Dec-2024
Note on QN32: Activity Name: Assign taping inspection checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 23-Dec-2024 End Date: 23-Dec-2024
Note on TF32: Activity Name: Assign Final Building Checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on TG32: Activity Name: Building close out check list Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 04-Mar-2025 End Date: 04-Mar-2025
Note on VN32: Activity Name: Assign post landscaping checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 02-May-2025 End Date: 02-May-2025
Note on D33: Activity Name: 3.0 Pre construction and mobilization Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on FQ33: Activity Name: Assign water and sewer and storm checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 15-Mar-2024 End Date: 15-Mar-2024
Note on KB33: Activity Name: Assign window & door installation checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 08-Jul-2024 End Date: 08-Jul-2024
Note on PV33: Activity Name: Assign taping inspection checklist for suites Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 05-Dec-2024 End Date: 05-Dec-2024
Note on QJ33: Activity Name: Assign taping inspection checklist for suites Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 19-Dec-2024 End Date: 19-Dec-2024
Note on D34: Activity Name: Assign Equipment & Tools check list Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on D35: Activity Name: Assign Health and Safety checklist Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on D36: Activity Name: Assign Permits check list Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on CJ37: Activity Name: Schedule Pile contractor Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 21-Dec-2023 End Date: 21-Dec-2023
Note on BW38: Activity Name: Order Rebar (30 days before site delivery date required) Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 08-Dec-2023 End Date: 08-Dec-2023
Note on D39: Activity Name: Organize site team to have training and certificates Phase: Pre-Construction Location: Precon Trade: Precon Team Start Date: 28-Sep-2023 End Date: 28-Sep-2023
Note on UL40: Activity Name: Rough grade landscaping Phase: Sitework Location: Landscaping Trade: Site Sub Start Date: 04-Apr-2025 End Date: 10-Apr-2025
Note on UZ40: Activity Name: Install landscaping Phase: Sitework Location: Landscaping Trade: Site Sub Start Date: 18-Apr-2025 End Date: 01-May-2025
Note on TC42: Activity Name: Install building signage Phase: Sitework Location: Landscaping Trade: Site Sub Start Date: 28-Feb-2025 End Date: 28-Feb-2025
Note on RQ43: Activity Name: Parkade - Measurement for template Phase: Sitework Location: Parkade Trade: Site Sub Start Date: 21-Jan-2025 End Date: 21-Jan-2025
Note on RC44: Activity Name: Parkade - Taper to rectify deficiencies Phase: Sitework Location: Parkade Trade: Site Sub Start Date: 07-Jan-2025 End Date: 07-Jan-2025
Note on CJ45: Activity Name: Site Preparation Phase: Sitework Location: Site Trade: Site Sub Start Date: 21-Dec-2023 End Date: 05-Jan-2024
Note on FQ45: Activity Name: Site services W/S/S install Phase: Sitework Location: Site Trade: Site Sub Start Date: 15-Mar-2024 End Date: 25-Mar-2024
Note on JR45: Activity Name: Radon rock install Phase: Sitework Location: Site Trade: Site Sub Start Date: 28-Jun-2024 End Date: 01-Jul-2024
Note on JV45: Activity Name: Install poly Phase: Sitework Location: Site Trade: Site Sub Start Date: 02-Jul-2024 End Date: 02-Jul-2024
Note on MA45: Activity Name: Form exterior pads Phase: Sitework Location: Site Trade: Site Sub Start Date: 28-Aug-2024 End Date: 03-Sep-2024
Note on MO45: Activity Name: Excatae exterior sidewalks Phase: Sitework Location: Site Trade: Site Sub Start Date: 11-Sep-2024 End Date: 03-Dec-2024
Note on PU45: Activity Name: Form exterior sidewalks Phase: Sitework Location: Site Trade: Site Sub Start Date: 04-Dec-2024 End Date: 06-Dec-2024
Note on CJ46: Activity Name: 4.1 Site Services & Foundation Work Phase: Sitework Location: Site Trade: Site Sub Start Date: 21-Dec-2023 End Date: 25-Mar-2024
Note on CQ47: Activity Name: 18. Assign site prep check list (First) Phase: Sitework Location: Site Trade: Site Sub Start Date: 28-Dec-2023 End Date: 28-Dec-2023
Note on CR47: Activity Name: Strip site Phase: Sitework Location: Site Trade: Site Sub Start Date: 29-Dec-2023 End Date: 04-Jan-2024
Note on FT47: Activity Name: Structural steel delivered and sorted onsite Phase: Sitework Location: Site Trade: Site Sub Start Date: 18-Mar-2024 End Date: 18-Mar-2024
Note on FT48: Activity Name: Install water and sewer Phase: Sitework Location: Site Trade: Site Sub Start Date: 18-Mar-2024 End Date: 22-Mar-2024
Note on OK50: Activity Name: Call the surveyor to measure for condo plan Phase: Sitework Location: Site Trade: Site Sub Start Date: 29-Oct-2024 End Date: 31-Oct-2024
Note on PO51: Activity Name: Board exterior walls on 2nd and sheds Phase: Exteriors Location: Level 2 Trade: Exteriors Start Date: 28-Nov-2024 End Date: 04-Dec-2024
Note on OU52: Activity Name: Rough in exterior walls on 2nd and sheds Phase: Exteriors Location: Level 2 Trade: Rough-In (General) Start Date: 08-Nov-2024 End Date: 21-Nov-2024
Note on PI52: Activity Name: Siding 2nd floor Phase: Exteriors Location: Level 2 Trade: Siding Start Date: 22-Nov-2024 End Date: 09-Dec-2024
Note on PL53: Activity Name: Poly and insulate on 2nd exterior walls Phase: Exteriors Location: Level 2 Trade: Insulation Start Date: 25-Nov-2024 End Date: 28-Nov-2024
Note on ST55: Activity Name: Organize 3rd party building exterior review, including roof, siding and flashings Phase: Exteriors Location: Level 3 Trade: Exteriors Start Date: 19-Feb-2025 End Date: 19-Feb-2025
Note on OJ56: Activity Name: Rough in exterior walls on 3rd and sheds Phase: Exteriors Location: Level 3 Trade: Rough-In (General) Start Date: 28-Oct-2024 End Date: 08-Nov-2024
Note on OY56: Activity Name: Poly and insulate on 3rd exterior walls Phase: Exteriors Location: Level 3 Trade: Insulation Start Date: 12-Nov-2024 End Date: 15-Nov-2024
Note on OS57: Activity Name: Siding 3rd floor Phase: Exteriors Location: Level 3 Trade: Siding Start Date: 06-Nov-2024 End Date: 21-Nov-2024
Note on OC59: Activity Name: Siding 4th floor Phase: Exteriors Location: Level 4 Trade: Siding Start Date: 21-Oct-2024 End Date: 05-Nov-2024
Note on OR60: Activity Name: Poly and insulate on 4th exterior walls Phase: Exteriors Location: Level 4 Trade: Insulation Start Date: 05-Nov-2024 End Date: 07-Nov-2024
Note on MV61: Activity Name: Blow in attic insulation Phase: Exteriors Location: Outside Bldg Trade: Exteriors Start Date: 18-Sep-2024 End Date: 20-Sep-2024
Note on LH62: Activity Name: Grind all balconys smooth Phase: Exteriors Location: Outside Bldg Trade: Exteriors Start Date: 09-Aug-2024 End Date: 22-Aug-2024
Note on LH63: Activity Name: Exterior Phase: Exteriors Location: Outside Bldg Trade: Exteriors Start Date: 09-Aug-2024 End Date: 05-May-2025
Note on KB64: Activity Name: install windows and doors Phase: Exteriors Location: Outside Bldg Trade: Windows Start Date: 08-Jul-2024 End Date: 26-Nov-2024
Note on PN64: Activity Name: Siding towers Phase: Exteriors Location: Outside Bldg Trade: Siding Start Date: 27-Nov-2024 End Date: 16-Dec-2024
Note on QO64: Activity Name: Assign siding checklist Phase: Exteriors Location: Outside Bldg Trade: Siding Start Date: 24-Dec-2024 End Date: 24-Dec-2024
Note on LF65: Activity Name: Roofing and water proofing Phase: Exteriors Location: Outside Bldg Trade: Exteriors Start Date: 07-Aug-2024 End Date: 23-Aug-2024
Note on MG65: Activity Name: Building paper the whole building Phase: Exteriors Location: Outside Bldg Trade: Exteriors Start Date: 03-Sep-2024 End Date: 25-Nov-2024
Note on QA65: Activity Name: Assign siding checklist Phase: Exteriors Location: Outside Bldg Trade: Siding Start Date: 10-Dec-2024 End Date: 10-Dec-2024
Note on LK66: Activity Name: Install roofing and water proofing Phase: Exteriors Location: Outside Bldg Trade: Exteriors Start Date: 12-Aug-2024 End Date: 23-Aug-2024
Note on MG66: Activity Name: Soffit & Tower Siding Phase: Exteriors Location: Outside Bldg Trade: Siding Start Date: 03-Sep-2024 End Date: 03-Jan-2025
Note on OS67: Activity Name: Assign siding checklist Phase: Exteriors Location: Outside Bldg Trade: Siding Start Date: 06-Nov-2024 End Date: 06-Nov-2024
Note on PI67: Activity Name: Assign siding checklist Phase: Exteriors Location: Outside Bldg Trade: Siding Start Date: 22-Nov-2024 End Date: 22-Nov-2024
Note on PZ69: Activity Name: Board parkade exterior walls and sheds Phase: Exteriors Location: Parkade Trade: Exteriors Start Date: 09-Dec-2024 End Date: 09-Dec-2024
Note on QA69: Activity Name: Board Parkade interior walls Phase: Exteriors Location: Parkade Trade: Exteriors Start Date: 10-Dec-2024 End Date: 13-Dec-2024
Note on LR71: Activity Name: Rough in Parkade Phase: Exteriors Location: Parkade Trade: Rough-In (General) Start Date: 19-Aug-2024 End Date: 23-Jan-2025
Note on LU72: Activity Name: Poly and insulate parkade exterior walls Phase: Exteriors Location: Parkade Trade: Insulation Start Date: 22-Aug-2024 End Date: 23-Aug-2024
Note on PE72: Activity Name: Rough in exterior walls - parkade and sheds Phase: Exteriors Location: Parkade Trade: Rough-In (General) Start Date: 18-Nov-2024 End Date: 06-Dec-2024
Note on QA72: Activity Name: Siding parkade level Phase: Exteriors Location: Parkade Trade: Siding Start Date: 10-Dec-2024 End Date: 23-Dec-2024
Note on FQ75: Activity Name: Strucutral Steel Phase: Interior Location: Interior Bldg Trade: Steel Start Date: 15-Mar-2024 End Date: 21-Mar-2024
Note on GA75: Activity Name: Assign water and sewer commissioning checklist Phase: Interior Location: Interior Bldg Trade: CX Start Date: 25-Mar-2024 End Date: 25-Mar-2024
Note on GR75: Activity Name: 4.2 Framing Phase: Interior Location: Interior Bldg Trade: Framing Start Date: 11-Apr-2024 End Date: 03-Jan-2025
Note on RP75: Activity Name: Install railings on all floors Phase: Interior Location: Interior Bldg Trade: Flooring Start Date: 20-Jan-2025 End Date: 06-Feb-2025
Note on SN75: Activity Name: Final coat of paint Phase: Interior Location: Interior Bldg Trade: Paint Start Date: 13-Feb-2025 End Date: 25-Feb-2025
Note on TB75: Activity Name: Final suite clean Phase: Interior Location: Interior Bldg Trade: Cleaning Start Date: 27-Feb-2025 End Date: 28-Feb-2025
Note on TF75: Activity Name: Move in dates confirmed Phase: Interior Location: Interior Bldg Trade: COO Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on TG75: Activity Name: Load home owners into copper Phase: Interior Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 04-Mar-2025
Note on TH75: Activity Name: Send out contractor surveys Phase: Interior Location: Interior Bldg Trade: CX Start Date: 05-Mar-2025 End Date: 05-Mar-2025
Note on TI75: Activity Name: Schedule 1 on 1 contractor review meetings Phase: Interior Location: Interior Bldg Trade: CX Start Date: 06-Mar-2025 End Date: 12-Mar-2025
Note on TP75: Activity Name: Project post mordem internal Phase: Interior Location: Interior Bldg Trade: CX Start Date: 13-Mar-2025 End Date: 13-Mar-2025
Note on TU75: Activity Name: Move info to Dev co work flow 1.0, 2.0, 6.0 Phase: Interior Location: Interior Bldg Trade: CX Start Date: 18-Mar-2025 End Date: 18-Mar-2025
Note on US75: Activity Name: Install underground sprinklers Phase: Interior Location: Interior Bldg Trade: Sprinkler Start Date: 11-Apr-2025 End Date: 17-Apr-2025
Note on VN75: Activity Name: Commision landscaping Phase: Interior Location: Interior Bldg Trade: CX Start Date: 02-May-2025 End Date: 05-May-2025
Note on FV76: Activity Name: Structural steel erection Phase: Interior Location: Interior Bldg Trade: Steel Start Date: 20-Mar-2024 End Date: 21-Mar-2024
Note on GA76: Activity Name: Commision Water/sewer/storm Phase: Interior Location: Interior Bldg Trade: CX Start Date: 25-Mar-2024 End Date: 25-Mar-2024
Note on JB76: Activity Name: Mechanical rough in in slab Phase: Interior Location: Interior Bldg Trade: Mechanical Start Date: 12-Jun-2024 End Date: 18-Jun-2024
Note on KK76: Activity Name: Deliver tubs & showers to suites / checklist Phase: Interior Location: Interior Bldg Trade: Plumbing Start Date: 17-Jul-2024 End Date: 18-Jul-2024
Note on KX76: Activity Name: Install stairs Phase: Interior Location: Interior Bldg Trade: Vertical Flow Start Date: 30-Jul-2024 End Date: 30-Jul-2024
Note on KZ76: Activity Name: Install windows & doors all floors Phase: Interior Location: Interior Bldg Trade: Flooring Start Date: 01-Aug-2024 End Date: 13-Aug-2024
Note on LS76: Activity Name: Call for structural inspection Phase: Interior Location: Interior Bldg Trade: Inspection Start Date: 20-Aug-2024 End Date: 20-Aug-2024
Note on LY76: Activity Name: Electrical rough in in ceiling Phase: Interior Location: Interior Bldg Trade: Electrical Start Date: 26-Aug-2024 End Date: 03-Sep-2024
Note on MH76: Activity Name: Call for Mechanical & Electrical inspection of attic Phase: Interior Location: Interior Bldg Trade: Inspection Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on MJ76: Activity Name: Install tubs and showers Phase: Interior Location: Interior Bldg Trade: Plumbing Start Date: 06-Sep-2024 End Date: 11-Sep-2024
Note on MX76: Activity Name: Install pocket door frames Phase: Interior Location: Interior Bldg Trade: Framing Start Date: 20-Sep-2024 End Date: 26-Sep-2024
Note on NV76: Activity Name: Delivery of Elevator & Install Phase: Interior Location: Interior Bldg Trade: Vertical Flow Start Date: 14-Oct-2024 End Date: 03-Jan-2025
Note on RR76: Activity Name: Assign pre board inspection checklist Phase: Interior Location: Interior Bldg Trade: Drywall Start Date: 22-Jan-2025 End Date: 22-Jan-2025
Note on RS76: Activity Name: Call for Electrical and Mechanical Inspection Phase: Interior Location: Interior Bldg Trade: Inspection Start Date: 23-Jan-2025 End Date: 23-Jan-2025
Note on RT76: Activity Name: Final coat of paint Phase: Interior Location: Interior Bldg Trade: Paint Start Date: 24-Jan-2025 End Date: 05-Feb-2025
Note on SO76: Activity Name: Contact Canada Post to get the address's created Phase: Interior Location: Interior Bldg Trade: Inspection Start Date: 14-Feb-2025 End Date: 14-Feb-2025
Note on ST76: Activity Name: Architectural walk throughs Phase: Interior Location: Interior Bldg Trade: Inspection Start Date: 19-Feb-2025 End Date: 20-Feb-2025
Note on SV76: Activity Name: Building inspector walk throughs Phase: Interior Location: Interior Bldg Trade: Inspection Start Date: 21-Feb-2025 End Date: 24-Feb-2025
Note on SZ76: Activity Name: Prepare occupancy paperwork Phase: Interior Location: Interior Bldg Trade: COO Start Date: 25-Feb-2025 End Date: 26-Feb-2025
Note on TB76: Activity Name: Receive occupancy Phase: Interior Location: Interior Bldg Trade: COO Start Date: 27-Feb-2025 End Date: 28-Feb-2025
Note on TF76: Activity Name: Pre sale move in dates confirmed Phase: Interior Location: Interior Bldg Trade: COO Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on TG76: Activity Name: Update home owner permissions in Construction online Phase: Interior Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 04-Mar-2025
Note on TH76: Activity Name: Building close out cleanup deficiencies confirmed Phase: Interior Location: Interior Bldg Trade: Cleaning Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on TO76: Activity Name: Home owner walk through punch list clean up Phase: Interior Location: Interior Bldg Trade: Cleaning Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on JB77: Activity Name: Electrical rough in in slab Phase: Interior Location: Interior Bldg Trade: Electrical Start Date: 12-Jun-2024 End Date: 18-Jun-2024
Note on LD77: Activity Name: Mechanical rough in in ceiling Phase: Interior Location: Interior Bldg Trade: Mechanical Start Date: 05-Aug-2024 End Date: 14-Aug-2024
Note on MA77: Activity Name: Install pocket foor frame Phase: Interior Location: Interior Bldg Trade: Framing Start Date: 28-Aug-2024 End Date: 03-Sep-2024
Note on MJ77: Activity Name: Install pocket door frames Phase: Interior Location: Interior Bldg Trade: Framing Start Date: 06-Sep-2024 End Date: 12-Sep-2024
Note on ND77: Activity Name: Install tubs and showers Phase: Interior Location: Interior Bldg Trade: Plumbing Start Date: 26-Sep-2024 End Date: 27-Sep-2024
Note on OM77: Activity Name: Call for Electrical and Mechanical inspection Phase: Interior Location: Interior Bldg Trade: Inspection Start Date: 31-Oct-2024 End Date: 31-Oct-2024
Note on OU77: Activity Name: Assign Corridor & Stairwell pre board inspection checklist Phase: Interior Location: Interior Bldg Trade: Drywall Start Date: 08-Nov-2024 End Date: 08-Nov-2024
Note on OY77: Activity Name: Call for Mechanical and Electrical Inspection Phase: Interior Location: Interior Bldg Trade: Inspection Start Date: 12-Nov-2024 End Date: 12-Nov-2024
Note on PB77: Activity Name: Assign pre board inspection check list Phase: Interior Location: Interior Bldg Trade: Drywall Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on PH77: Activity Name: Rough in interior walls Phase: Interior Location: Interior Bldg Trade: Rough-In (General) Start Date: 21-Nov-2024 End Date: 04-Dec-2024
Note on PW77: Activity Name: Board and prepare electrical/mechanical room Phase: Interior Location: Interior Bldg Trade: Drywall Start Date: 06-Dec-2024 End Date: 10-Dec-2024
Note on QO77: Activity Name: Install metal doors and frames Phase: Interior Location: Interior Bldg Trade: Framing Start Date: 24-Dec-2024 End Date: 06-Jan-2025
Note on RR77: Activity Name: Assign pre board inspection checklist Phase: Interior Location: Interior Bldg Trade: Drywall Start Date: 22-Jan-2025 End Date: 22-Jan-2025
Note on SD77: Activity Name: Final coat of paint Phase: Interior Location: Interior Bldg Trade: Paint Start Date: 03-Feb-2025 End Date: 13-Feb-2025
Note on SO77: Activity Name: Fire alarm verification Phase: Interior Location: Interior Bldg Trade: Inspection Start Date: 14-Feb-2025 End Date: 17-Feb-2025
Note on ST77: Activity Name: Enginering walk throughs Phase: Interior Location: Interior Bldg Trade: Inspection Start Date: 19-Feb-2025 End Date: 20-Feb-2025
Note on TF77: Activity Name: 5.0 Sales, Occupancy, Closings Phase: Interior Location: Interior Bldg Trade: COO Start Date: 03-Mar-2025 End Date: 01-May-2025
Note on LD78: Activity Name: 4.3 Rough In, Steel Stud Drywall Phase: Interior Location: Interior Bldg Trade: Drywall Start Date: 05-Aug-2024 End Date: 23-Jan-2025
Note on SO78: Activity Name: Sprinkler testing Phase: Interior Location: Interior Bldg Trade: Inspection Start Date: 14-Feb-2025 End Date: 17-Feb-2025
Note on TG78: Activity Name: Finalize home owner extras Phase: Interior Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on TN78: Activity Name: Home owner walk through and punch list Phase: Interior Location: Interior Bldg Trade: CX Start Date: 11-Mar-2025 End Date: 11-Mar-2025
Note on LF79: Activity Name: Sprinkler install in attic Phase: Interior Location: Interior Bldg Trade: Sprinkler Start Date: 07-Aug-2024 End Date: 21-Aug-2024
Note on MC79: Activity Name: Install tubs and showers Phase: Interior Location: Interior Bldg Trade: Plumbing Start Date: 30-Aug-2024 End Date: 04-Sep-2024
Note on OU79: Activity Name: Assign pre board interior walls checklist Phase: Interior Location: Interior Bldg Trade: Drywall Start Date: 08-Nov-2024 End Date: 08-Nov-2024
Note on OY79: Activity Name: Assign corridor & stairwell pre board inspection checklist Phase: Interior Location: Interior Bldg Trade: Drywall Start Date: 12-Nov-2024 End Date: 12-Nov-2024
Note on PB79: Activity Name: Assign pre board interior walls checklist Phase: Interior Location: Interior Bldg Trade: Drywall Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on PL79: Activity Name: Call for Mechanical and Electrical inspection Phase: Interior Location: Interior Bldg Trade: Inspection Start Date: 25-Nov-2024 End Date: 25-Nov-2024
Note on PM79: Activity Name: Call for envelope reviewer inspection Phase: Interior Location: Interior Bldg Trade: Inspection Start Date: 26-Nov-2024 End Date: 26-Nov-2024
Note on PO79: Activity Name: Assign Corridor & Stairwell pre board inspection checklist Phase: Interior Location: Interior Bldg Trade: Drywall Start Date: 28-Nov-2024 End Date: 28-Nov-2024
Note on SO79: Activity Name: Elevator commissioning Phase: Interior Location: Interior Bldg Trade: CX Start Date: 14-Feb-2025 End Date: 17-Feb-2025
Note on TG79: Activity Name: Move in binders created Phase: Interior Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on TN79: Activity Name: Unit Commissioning deficiency clean up confirmed Phase: Interior Location: Interior Bldg Trade: Cleaning Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on LH80: Activity Name: 4.4 Finishing Phase: Interior Location: Interior Bldg Trade: Finishing Start Date: 09-Aug-2024 End Date: 05-May-2025
Note on MG81: Activity Name: Install exterior decking all floors Phase: Interior Location: Interior Bldg Trade: Exteriors Start Date: 03-Sep-2024 End Date: 16-Sep-2024
Note on PL81: Activity Name: Gypcrete Phase: Interior Location: Interior Bldg Trade: Gypcrete Start Date: 25-Nov-2024 End Date: 26-Nov-2024
Note on PO81: Activity Name: Assign pre board inspection check list Phase: Interior Location: Interior Bldg Trade: Drywall Start Date: 28-Nov-2024 End Date: 28-Nov-2024
Note on SO81: Activity Name: Final commissioning and deficiency Phase: Interior Location: Interior Bldg Trade: CX Start Date: 14-Feb-2025 End Date: 03-Mar-2025
Note on TG81: Activity Name: Unit Commissioning Inspection list Phase: Interior Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on PO82: Activity Name: Assign pre board interior walls checklist Phase: Interior Location: Interior Bldg Trade: Drywall Start Date: 28-Nov-2024 End Date: 28-Nov-2024
Note on TG82: Activity Name: Keys and gift cards and welcome package created Phase: Interior Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on PO83: Activity Name: Main service electrical room install Phase: Interior Location: Interior Bldg Trade: Electrical Start Date: 28-Nov-2024 End Date: 26-Dec-2024
Note on TG83: Activity Name: New move ins and warranty through service manager Phase: Interior Location: Interior Bldg Trade: CX Start Date: 04-Mar-2025 End Date: 01-May-2025
Note on PO84: Activity Name: Main service mechanical room install Phase: Interior Location: Interior Bldg Trade: Mechanical Start Date: 28-Nov-2024 End Date: 22-Jan-2025
Note on TI84: Activity Name: Schedule contractor group meeting to review survey results Phase: Interior Location: Interior Bldg Trade: CX Start Date: 06-Mar-2025 End Date: 12-Mar-2025
Note on QX86: Activity Name: finishing parkade level 1 Phase: Interior Location: Level 1 Trade: Finishing Start Date: 02-Jan-2025 End Date: 24-Feb-2025
Note on RM87: Activity Name: Install cabinets on 1 Phase: Interior Location: Level 1 Trade: Carpentry Start Date: 17-Jan-2025 End Date: 20-Jan-2025
Note on QX88: Activity Name: Ceiling texture on 1 Phase: Interior Location: Level 1 Trade: Finishing Start Date: 02-Jan-2025 End Date: 03-Jan-2025
Note on RF89: Activity Name: Spray out closet interiors and trim on 1 Phase: Interior Location: Level 1 Trade: Carpentry Start Date: 10-Jan-2025 End Date: 10-Jan-2025
Note on SO90: Activity Name: Construction clean on 1 Phase: Interior Location: Level 1 Trade: Cleaning Start Date: 14-Feb-2025 End Date: 18-Feb-2025
Note on ST90: Activity Name: Assign Unit Commissioning Inspection list on 1 Phase: Interior Location: Level 1 Trade: CX Start Date: 19-Feb-2025 End Date: 19-Feb-2025
Note on SU90: Activity Name: Final suite clean on 1 Phase: Interior Location: Level 1 Trade: Cleaning Start Date: 20-Feb-2025 End Date: 24-Feb-2025
Note on SK93: Activity Name: Install countertops on 1 Phase: Interior Location: Level 1 Trade: Carpentry Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on PS94: Activity Name: Install suite entry doors and frames and Interior doors, trims and jambs Phase: Interior Location: Level 1 Trade: Framing Start Date: 02-Dec-2024 End Date: 06-Dec-2024
Note on PZ94: Activity Name: Install suite entry doors and frames and Interior doors, trims and jambs Phase: Interior Location: Level 1 Trade: Framing Start Date: 09-Dec-2024 End Date: 13-Dec-2024
Note on QN94: Activity Name: Install suite entry doors and frames and Interior doors, trims and jambs Phase: Interior Location: Level 1 Trade: Framing Start Date: 23-Dec-2024 End Date: 03-Jan-2025
Note on RD94: Activity Name: Install interior doors and case on 1 Phase: Interior Location: Level 1 Trade: Carpentry Start Date: 08-Jan-2025 End Date: 09-Jan-2025
Note on SL98: Activity Name: Electrical finishing on 1 Phase: Interior Location: Level 1 Trade: Electrical Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on RF99: Activity Name: Paint 1rst coat of color on 1 Phase: Interior Location: Level 1 Trade: Paint Start Date: 10-Jan-2025 End Date: 16-Jan-2025
Note on RK100: Activity Name: Install flooring on 1 Phase: Interior Location: Level 1 Trade: Flooring Start Date: 15-Jan-2025 End Date: 16-Jan-2025
Note on SL101: Activity Name: Sprinkler finishing on 1 Phase: Interior Location: Level 1 Trade: Sprinkler Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on SL102: Activity Name: Mechanical finishing on 1 Phase: Interior Location: Level 1 Trade: Mechanical Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on QY103: Activity Name: Prime paint on 1 Phase: Interior Location: Level 1 Trade: Paint Start Date: 03-Jan-2025 End Date: 07-Jan-2025
Note on RM104: Activity Name: Install base and hardware 2nd floor Phase: Interior Location: Level 2 Trade: Carpentry Start Date: 17-Jan-2025 End Date: 24-Jan-2025
Note on LR105: Activity Name: Water dams 2nd floor Phase: Interior Location: Level 2 Trade: Plumbing Start Date: 19-Aug-2024 End Date: 23-Aug-2024
Note on RI106: Activity Name: Install cabinets 2nd floor Phase: Interior Location: Level 2 Trade: Carpentry Start Date: 13-Jan-2025 End Date: 17-Jan-2025
Note on PM107: Activity Name: Frame drops on 2nd Phase: Interior Location: Level 2 Trade: Framing Start Date: 26-Nov-2024 End Date: 02-Dec-2024
Note on QG107: Activity Name: Ceiling texture on 2nd Phase: Interior Location: Level 2 Trade: Finishing Start Date: 16-Dec-2024 End Date: 17-Dec-2024
Note on LT109: Activity Name: Back framing on 2nd Phase: Interior Location: Level 2 Trade: Framing Start Date: 21-Aug-2024 End Date: 27-Aug-2024
Note on TB109: Activity Name: Assign Unit Commissioning Inspection list 2nd floor Phase: Interior Location: Level 2 Trade: CX Start Date: 27-Feb-2025 End Date: 27-Feb-2025
Note on RL111: Activity Name: 2nd floor counter top measurement for template Phase: Interior Location: Level 2 Trade: Flooring Start Date: 16-Jan-2025 End Date: 20-Jan-2025
Note on RQ111: Activity Name: Manufacturing and Install countertops 2nd floor Phase: Interior Location: Level 2 Trade: Carpentry Start Date: 21-Jan-2025 End Date: 07-Feb-2025
Note on QN113: Activity Name: Install interior doors and case on 2nd Phase: Interior Location: Level 2 Trade: Carpentry Start Date: 23-Dec-2024 End Date: 03-Jan-2025
Note on SH114: Activity Name: Electrical finishing 2nd floor Phase: Interior Location: Level 2 Trade: Electrical Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on QI115: Activity Name: Prime paint on 2nd Phase: Interior Location: Level 2 Trade: Paint Start Date: 18-Dec-2024 End Date: 23-Dec-2024
Note on QR115: Activity Name: Paint 1st coat of color 2nd floor Phase: Interior Location: Level 2 Trade: Paint Start Date: 27-Dec-2024 End Date: 03-Jan-2025
Note on SH115: Activity Name: Sprinkler finishing 2nd floor Phase: Interior Location: Level 2 Trade: Sprinkler Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on GZ118: Activity Name: Frame 2nd floor Phase: Interior Location: Level 2 Trade: Framing Start Date: 19-Apr-2024 End Date: 13-May-2024
Note on KR118: Activity Name: Core floors begin at 2nd Phase: Interior Location: Level 2 Trade: Flooring Start Date: 24-Jul-2024 End Date: 26-Jul-2024
Note on QG118: Activity Name: 2nd floor finishing Phase: Interior Location: Level 2 Trade: Flooring Start Date: 16-Dec-2024 End Date: 28-Feb-2025
Note on GZ119: Activity Name: Framing 2nd floor Phase: Interior Location: Level 2 Trade: Framing Start Date: 19-Apr-2024 End Date: 14-May-2024
Note on RD119: Activity Name: Install flooring 2nd floor Phase: Interior Location: Level 2 Trade: Flooring Start Date: 08-Jan-2025 End Date: 16-Jan-2025
Note on LY122: Activity Name: Sprinkler rough in corridor & stairwells on 2nd Phase: Interior Location: Level 2 Trade: Sprinkler Start Date: 26-Aug-2024 End Date: 06-Sep-2024
Note on ON122: Activity Name: Mechanical rough in hallways & stairwells on 2nd Phase: Interior Location: Level 2 Trade: Mechanical Start Date: 01-Nov-2024 End Date: 15-Nov-2024
Note on PO122: Activity Name: Board 2nd floor hallways and stairwells Phase: Interior Location: Level 2 Trade: Drywall Start Date: 28-Nov-2024 End Date: 04-Dec-2024
Note on PV122: Activity Name: Tape 2nd floor hallways and stair wells Phase: Interior Location: Level 2 Trade: Drywall Start Date: 05-Dec-2024 End Date: 19-Dec-2024
Note on QN122: Activity Name: 2nd floor - Taper do the rectification of deficiences Phase: Interior Location: Level 2 Trade: Flooring Start Date: 23-Dec-2024 End Date: 23-Dec-2024
Note on SY122: Activity Name: Construction clean 2nd floor Phase: Interior Location: Level 2 Trade: Cleaning Start Date: 24-Feb-2025 End Date: 27-Feb-2025
Note on OU123: Activity Name: Electrical rough in hallways & stairwells on 2nd Phase: Interior Location: Level 2 Trade: Electrical Start Date: 08-Nov-2024 End Date: 22-Nov-2024
Note on SH126: Activity Name: Mechanical finishing 2nd floor Phase: Interior Location: Level 2 Trade: Mechanical Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on KL127: Activity Name: Layout suites on 2nd floor Phase: Interior Location: Level 2 Trade: Drywall Start Date: 18-Jul-2024 End Date: 22-Jul-2024
Note on LK127: Activity Name: Rough in 2nd floor Phase: Interior Location: Level 2 Trade: Rough-In (General) Start Date: 12-Aug-2024 End Date: 03-Jan-2025
Note on LY128: Activity Name: Sprinkler rough in on 2nd Phase: Interior Location: Level 2 Trade: Sprinkler Start Date: 26-Aug-2024 End Date: 06-Sep-2024
Note on ON128: Activity Name: Mechanical rough in on 2nd Phase: Interior Location: Level 2 Trade: Mechanical Start Date: 01-Nov-2024 End Date: 15-Nov-2024
Note on PV128: Activity Name: Tape suites on 2nd Phase: Interior Location: Level 2 Trade: Drywall Start Date: 05-Dec-2024 End Date: 19-Dec-2024
Note on OU129: Activity Name: Electrical rough in on 2nd Phase: Interior Location: Level 2 Trade: Electrical Start Date: 08-Nov-2024 End Date: 22-Nov-2024
Note on PO131: Activity Name: Board 2nd floor walls Phase: Interior Location: Level 2 Trade: Drywall Start Date: 28-Nov-2024 End Date: 04-Dec-2024
Note on LK132: Activity Name: Steel stud install on 2nd & drywall behind the tubs including fire wall taping if it is a fire wall Phase: Interior Location: Level 2 Trade: Drywall Start Date: 12-Aug-2024 End Date: 29-Aug-2024
Note on MC132: Activity Name: Board upper 16" strips in common area and all suites on 2nd Phase: Interior Location: Level 2 Trade: Drywall Start Date: 30-Aug-2024 End Date: 04-Sep-2024
Note on PL132: Activity Name: Fire tape / Fire caulk upper strips on 2nd Phase: Interior Location: Level 2 Trade: Drywall Start Date: 25-Nov-2024 End Date: 25-Nov-2024
Note on RD135: Activity Name: Install base and hardware on 3rd Phase: Interior Location: Level 3 Trade: Carpentry Start Date: 08-Jan-2025 End Date: 13-Jan-2025
Note on LR136: Activity Name: Water dams 3rd floor Phase: Interior Location: Level 3 Trade: Plumbing Start Date: 19-Aug-2024 End Date: 23-Aug-2024
Note on QI137: Activity Name: Install cabinets on 3rd Phase: Interior Location: Level 3 Trade: Carpentry Start Date: 18-Dec-2024 End Date: 10-Jan-2025
Note on OY138: Activity Name: Frame drops on 3rd Phase: Interior Location: Level 3 Trade: Framing Start Date: 12-Nov-2024 End Date: 18-Nov-2024
Note on PS138: Activity Name: Ceiling texture on 3rd Phase: Interior Location: Level 3 Trade: Finishing Start Date: 02-Dec-2024 End Date: 03-Dec-2024
Note on QC140: Activity Name: Spray out closet interiors and trim on 3rd Phase: Interior Location: Level 3 Trade: Carpentry Start Date: 12-Dec-2024 End Date: 17-Dec-2024
Note on SL141: Activity Name: Construction clean on 3rd Phase: Interior Location: Level 3 Trade: Cleaning Start Date: 11-Feb-2025 End Date: 17-Feb-2025
Note on SR142: Activity Name: Assign Unit Commissioning Inspection list on 3rd Phase: Interior Location: Level 3 Trade: CX Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on SR143: Activity Name: Final suite clean on 3rd Phase: Interior Location: Level 3 Trade: Cleaning Start Date: 17-Feb-2025 End Date: 18-Feb-2025
Note on RD144: Activity Name: 3rd floor counter top measurement for template Phase: Interior Location: Level 3 Trade: Flooring Start Date: 08-Jan-2025 End Date: 10-Jan-2025
Note on RF145: Activity Name: Manufacturing and Install countertops on 3rd Phase: Interior Location: Level 3 Trade: Carpentry Start Date: 10-Jan-2025 End Date: 29-Jan-2025
Note on PZ146: Activity Name: Install interior doors and case on 3rd Phase: Interior Location: Level 3 Trade: Carpentry Start Date: 09-Dec-2024 End Date: 13-Dec-2024
Note on RY147: Activity Name: Electrical finishing on 3rd Phase: Interior Location: Level 3 Trade: Electrical Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on QC148: Activity Name: Paint 1st coat of color on 3rd Phase: Interior Location: Level 3 Trade: Paint Start Date: 12-Dec-2024 End Date: 17-Dec-2024
Note on RY148: Activity Name: Sprinkler finishing on 3rd Phase: Interior Location: Level 3 Trade: Sprinkler Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on IM150: Activity Name: Frame 3rd floor Phase: Interior Location: Level 3 Trade: Framing Start Date: 28-May-2024 End Date: 07-Jun-2024
Note on KW150: Activity Name: Core floor beings at 3rd floor Phase: Interior Location: Level 3 Trade: Flooring Start Date: 29-Jul-2024 End Date: 31-Jul-2024
Note on PS150: Activity Name: 3rd floor finishing Phase: Interior Location: Level 3 Trade: Flooring Start Date: 02-Dec-2024 End Date: 18-Feb-2025
Note on IM151: Activity Name: Framing 3rd floor Phase: Interior Location: Level 3 Trade: Framing Start Date: 28-May-2024 End Date: 26-Jul-2024
Note on QH151: Activity Name: Install flooring on 3rd Phase: Interior Location: Level 3 Trade: Flooring Start Date: 17-Dec-2024 End Date: 07-Jan-2025
Note on MM155: Activity Name: Sprinkler rough in hallways & stairwells on 3rd Phase: Interior Location: Level 3 Trade: Sprinkler Start Date: 09-Sep-2024 End Date: 20-Sep-2024
Note on OJ155: Activity Name: Mechanical rough in hallways & stairwells on 3rd Phase: Interior Location: Level 3 Trade: Mechanical Start Date: 28-Oct-2024 End Date: 07-Nov-2024
Note on PB155: Activity Name: Load the board on floor and Board 3rd floor hallways and stairwells Phase: Interior Location: Level 3 Trade: Drywall Start Date: 15-Nov-2024 End Date: 22-Nov-2024
Note on MN156: Activity Name: Back framing on 3rd Phase: Interior Location: Level 3 Trade: Framing Start Date: 10-Sep-2024 End Date: 16-Sep-2024
Note on OJ156: Activity Name: Electrical rough in hallways & stairwells on 3rd Phase: Interior Location: Level 3 Trade: Electrical Start Date: 28-Oct-2024 End Date: 08-Nov-2024
Note on PI156: Activity Name: Tape 3rd floor hallways and stair wells Phase: Interior Location: Level 3 Trade: Drywall Start Date: 22-Nov-2024 End Date: 05-Dec-2024
Note on RY159: Activity Name: Mechanical finishing on 3rd Phase: Interior Location: Level 3 Trade: Mechanical Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on KQ160: Activity Name: Layout suites on 3rd floor Phase: Interior Location: Level 3 Trade: Framing Start Date: 23-Jul-2024 End Date: 26-Jul-2024
Note on LR160: Activity Name: Rough in 3rd floor Phase: Interior Location: Level 3 Trade: Rough-In (General) Start Date: 19-Aug-2024 End Date: 13-Dec-2024
Note on MM161: Activity Name: Sprinkler rough in on 3rd Phase: Interior Location: Level 3 Trade: Sprinkler Start Date: 09-Sep-2024 End Date: 20-Sep-2024
Note on OJ161: Activity Name: Mechanical rough in on 3rd Phase: Interior Location: Level 3 Trade: Mechanical Start Date: 28-Oct-2024 End Date: 07-Nov-2024
Note on PI161: Activity Name: Tape suites on 3rd Phase: Interior Location: Level 3 Trade: Drywall Start Date: 22-Nov-2024 End Date: 05-Dec-2024
Note on OJ162: Activity Name: Electrical rough in on 3rd Phase: Interior Location: Level 3 Trade: Electrical Start Date: 28-Oct-2024 End Date: 08-Nov-2024
Note on MC164: Activity Name: Steel stud install on 3rd & drywall behind the tubs including fire wall taping if it is a fire wall Phase: Interior Location: Level 3 Trade: Drywall Start Date: 30-Aug-2024 End Date: 05-Sep-2024
Note on MO164: Activity Name: Board upper 16" strips in common area & all suites on 3rd Phase: Interior Location: Level 3 Trade: Drywall Start Date: 11-Sep-2024 End Date: 16-Sep-2024
Note on OX164: Activity Name: Fire tape / Fire caulk upper strips on 3rd Phase: Interior Location: Level 3 Trade: Drywall Start Date: 11-Nov-2024 End Date: 11-Nov-2024
Note on PB164: Activity Name: Load boards on floor and Board 3rd floor walls Phase: Interior Location: Level 3 Trade: Drywall Start Date: 15-Nov-2024 End Date: 22-Nov-2024
Note on PV164: Activity Name: Prime paint on 3rd Phase: Interior Location: Level 3 Trade: Paint Start Date: 05-Dec-2024 End Date: 10-Dec-2024
Note on PB165: Activity Name: Load boards on floor and Board exterior walls on 3rd and sheds Phase: Interior Location: Level 3 Trade: Drywall Start Date: 15-Nov-2024 End Date: 22-Nov-2024
Note on QA165: Activity Name: 3rd floor - Taper do the rectification of deficiencies Phase: Interior Location: Level 3 Trade: Flooring Start Date: 10-Dec-2024 End Date: 10-Dec-2024
Note on QK169: Activity Name: Install base and hardware on 4th Phase: Interior Location: Level 4 Trade: Carpentry Start Date: 20-Dec-2024 End Date: 03-Jan-2025
Note on LR170: Activity Name: Water dams 4th floor Phase: Interior Location: Level 4 Trade: Plumbing Start Date: 19-Aug-2024 End Date: 23-Aug-2024
Note on QB171: Activity Name: Install cabinets on 4th Phase: Interior Location: Level 4 Trade: Carpentry Start Date: 11-Dec-2024 End Date: 18-Dec-2024
Note on LD172: Activity Name: Rough in 4th floor ceiling Phase: Interior Location: Level 4 Trade: Rough-In (General) Start Date: 05-Aug-2024 End Date: 07-Oct-2024
Note on PM172: Activity Name: Ceiling texture on 4th Phase: Interior Location: Level 4 Trade: Finishing Start Date: 26-Nov-2024 End Date: 27-Nov-2024
Note on PP172: Activity Name: Frame drops on 4th Phase: Interior Location: Level 4 Trade: Framing Start Date: 29-Nov-2024 End Date: 05-Dec-2024
Note on MI173: Activity Name: Poly 4th floor ceiling Phase: Interior Location: Level 4 Trade: Flooring Start Date: 05-Sep-2024 End Date: 06-Sep-2024
Note on MM173: Activity Name: Install sound bar 4th floor Phase: Interior Location: Level 4 Trade: Flooring Start Date: 09-Sep-2024 End Date: 10-Sep-2024
Note on MO173: Activity Name: Install drywall on 4th floor ceiling Phase: Interior Location: Level 4 Trade: Drywall Start Date: 11-Sep-2024 End Date: 17-Sep-2024
Note on NA173: Activity Name: Tape 4th floor ceiling Phase: Interior Location: Level 4 Trade: Drywall Start Date: 23-Sep-2024 End Date: 04-Oct-2024
Note on PV176: Activity Name: Paint 1st coat of color on 4th Phase: Interior Location: Level 4 Trade: Paint Start Date: 05-Dec-2024 End Date: 10-Dec-2024
Note on PV177: Activity Name: Spray out closet interiors and trim on 4th Phase: Interior Location: Level 4 Trade: Carpentry Start Date: 05-Dec-2024 End Date: 10-Dec-2024
Note on NA178: Activity Name: Back framing on 4th Phase: Interior Location: Level 4 Trade: Framing Start Date: 23-Sep-2024 End Date: 27-Sep-2024
Note on SD178: Activity Name: Construction clean on 4th Phase: Interior Location: Level 4 Trade: Cleaning Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on SH179: Activity Name: Assign Unit Commissioning Inspection list on 4th Phase: Interior Location: Level 4 Trade: CX Start Date: 07-Feb-2025 End Date: 07-Feb-2025
Note on QH181: Activity Name: 4th floor counter top measurements for template Phase: Interior Location: Level 4 Trade: Flooring Start Date: 17-Dec-2024 End Date: 19-Dec-2024
Note on QX181: Activity Name: manufacturing and Install countertops on 4th Phase: Interior Location: Level 4 Trade: Carpentry Start Date: 02-Jan-2025 End Date: 21-Jan-2025
Note on PS183: Activity Name: Install interior doors and case on 4th Phase: Interior Location: Level 4 Trade: Carpentry Start Date: 02-Dec-2024 End Date: 06-Dec-2024
Note on RQ184: Activity Name: Electrical finishing on 4th Phase: Interior Location: Level 4 Trade: Electrical Start Date: 21-Jan-2025 End Date: 27-Jan-2025
Note on OC185: Activity Name: Rough in exterior walls on 4th and sheds Phase: Interior Location: Level 4 Trade: Rough-In (General) Start Date: 21-Oct-2024 End Date: 31-Oct-2024
Note on OU185: Activity Name: Load the board on floor and Board exterior walls on 4th and sheds Phase: Interior Location: Level 4 Trade: Drywall Start Date: 08-Nov-2024 End Date: 15-Nov-2024
Note on PB186: Activity Name: Install fascia and soffit 4th floor Phase: Interior Location: Level 4 Trade: Flooring Start Date: 15-Nov-2024 End Date: 25-Nov-2024
Note on ON188: Activity Name: Fire tape / Fire caulk upper strips on 4th Phase: Interior Location: Level 4 Trade: Drywall Start Date: 01-Nov-2024 End Date: 01-Nov-2024
Note on PO188: Activity Name: Prime paint on 4th Phase: Interior Location: Level 4 Trade: Paint Start Date: 28-Nov-2024 End Date: 03-Dec-2024
Note on RQ188: Activity Name: Sprinkler finishing on 4th Phase: Interior Location: Level 4 Trade: Sprinkler Start Date: 21-Jan-2025 End Date: 27-Jan-2025
Note on KZ191: Activity Name: Core floor beings at 4th floor Phase: Interior Location: Level 4 Trade: Flooring Start Date: 01-Aug-2024 End Date: 02-Aug-2024
Note on PZ191: Activity Name: Install flooring on 4th Phase: Interior Location: Level 4 Trade: Flooring Start Date: 09-Dec-2024 End Date: 16-Dec-2024
Note on OQ193: Activity Name: 4th floor framing inspection Phase: Interior Location: Level 4 Trade: Inspection Start Date: 04-Nov-2024 End Date: 04-Nov-2024
Note on NA194: Activity Name: Sprinkler rough in hallways stairwells on 4th Phase: Interior Location: Level 4 Trade: Sprinkler Start Date: 23-Sep-2024 End Date: 30-Sep-2024
Note on OC194: Activity Name: Mechanical rough in hallways stairwells on 4th Phase: Interior Location: Level 4 Trade: Mechanical Start Date: 21-Oct-2024 End Date: 25-Oct-2024
Note on OU194: Activity Name: Load the board on floor and Board 4th floor hallways and stairwells Phase: Interior Location: Level 4 Trade: Drywall Start Date: 08-Nov-2024 End Date: 15-Nov-2024
Note on OC195: Activity Name: Electrical rough in hallways stairwells on 4th Phase: Interior Location: Level 4 Trade: Electrical Start Date: 21-Oct-2024 End Date: 31-Oct-2024
Note on PB195: Activity Name: Tape 4th floor hallways and stair wells Phase: Interior Location: Level 4 Trade: Drywall Start Date: 15-Nov-2024 End Date: 28-Nov-2024
Note on KW198: Activity Name: Layout suites 4th floor Phase: Interior Location: Level 4 Trade: Flooring Start Date: 29-Jul-2024 End Date: 01-Aug-2024
Note on LR198: Activity Name: Rough in 4th floor Phase: Interior Location: Level 4 Trade: Rough-In (General) Start Date: 19-Aug-2024 End Date: 06-Dec-2024
Note on RQ198: Activity Name: Mechanical finishing on 4th Phase: Interior Location: Level 4 Trade: Mechanical Start Date: 21-Jan-2025 End Date: 27-Jan-2025
Note on SH198: Activity Name: Final suite clean on 4th Phase: Interior Location: Level 4 Trade: Cleaning Start Date: 07-Feb-2025 End Date: 10-Feb-2025
Note on NA199: Activity Name: Sprinkler rough in on 4th Phase: Interior Location: Level 4 Trade: Sprinkler Start Date: 23-Sep-2024 End Date: 30-Sep-2024
Note on OC199: Activity Name: Mechanical rough in on 4th Phase: Interior Location: Level 4 Trade: Mechanical Start Date: 21-Oct-2024 End Date: 25-Oct-2024
Note on PB199: Activity Name: Tape suites on 4th Phase: Interior Location: Level 4 Trade: Drywall Start Date: 15-Nov-2024 End Date: 28-Nov-2024
Note on OC200: Activity Name: Electrical rough in on 4th Phase: Interior Location: Level 4 Trade: Electrical Start Date: 21-Oct-2024 End Date: 31-Oct-2024
Note on PM200: Activity Name: finishing on 4th Phase: Interior Location: Level 4 Trade: Finishing Start Date: 26-Nov-2024 End Date: 10-Feb-2025
Note on JI202: Activity Name: Frame 4th floor Phase: Interior Location: Level 4 Trade: Framing Start Date: 19-Jun-2024 End Date: 05-Jul-2024
Note on MV202: Activity Name: Steel stud install on 4th & drywall behind the tubs including fire wall taping if it is a fire wall Phase: Interior Location: Level 4 Trade: Drywall Start Date: 18-Sep-2024 End Date: 26-Sep-2024
Note on NE202: Activity Name: Board upper 16" strips in common area and all suites on 4th Phase: Interior Location: Level 4 Trade: Drywall Start Date: 27-Sep-2024 End Date: 02-Oct-2024
Note on OU202: Activity Name: Load the board on floor and Board 4th floor walls Phase: Interior Location: Level 4 Trade: Drywall Start Date: 08-Nov-2024 End Date: 15-Nov-2024
Note on PS202: Activity Name: 4th floor - Taper do the rectification of deficiencies Phase: Interior Location: Level 4 Trade: Flooring Start Date: 02-Dec-2024 End Date: 03-Dec-2024
Note on JI203: Activity Name: Framing 4th floor Phase: Interior Location: Level 4 Trade: Framing Start Date: 19-Jun-2024 End Date: 31-Jul-2024
Note on JG207: Activity Name: Paint underside of ceiling in parkade Phase: Interior Location: Parkade Trade: Paint Start Date: 17-Jun-2024 End Date: 17-Jun-2024
Note on GR208: Activity Name: Frame parkade level Phase: Interior Location: Parkade Trade: Framing Start Date: 11-Apr-2024 End Date: 15-Apr-2024
Note on JB208: Activity Name: Rough in parkade slab Phase: Interior Location: Parkade Trade: Rough-In (General) Start Date: 12-Jun-2024 End Date: 26-Jun-2024
Note on LR208: Activity Name: Frame interior parkade walls Phase: Interior Location: Parkade Trade: Framing Start Date: 19-Aug-2024 End Date: 23-Aug-2024
Note on QD208: Activity Name: Tape parkade interior and exterior walls Phase: Interior Location: Parkade Trade: Drywall Start Date: 13-Dec-2024 End Date: 23-Dec-2024
Note on GR209: Activity Name: Framing parkade Phase: Interior Location: Parkade Trade: Framing Start Date: 11-Apr-2024 End Date: 16-Apr-2024
Note on QG209: Activity Name: Frame and board Parkade beams Phase: Interior Location: Parkade Trade: Framing Start Date: 16-Dec-2024 End Date: 20-Dec-2024
Note on KC212: Activity Name: Install roof trusses and sheeting and towers Phase: Interior Location: Roof Trade: Framing Start Date: 09-Jul-2024 End Date: 06-Aug-2024
Note on LF212: Activity Name: Assign roof trusses framing checklist Phase: Interior Location: Roof Trade: Framing Start Date: 07-Aug-2024 End Date: 07-Aug-2024
Note on KC213: Activity Name: Roof trusses install Phase: Interior Location: Roof Trade: Framing Start Date: 09-Jul-2024 End Date: 20-Aug-2024

## CFA - Legends
Exteriors |  | Foundation |  | Interior |  | Mobilization |  | Pre-Construction |  | Sitework
Attic |  | Bathrooms |  | Base and Hardware |  | N/A |  | Cabinets |  | Landscaping
EXT-7 | Blow in attic insulation | INS-12 | Rebar inspection Structural Engineer | CAR-1 | Install base and hardware 2nd floor | MOB-1 | Assign Mobilization check list | PREC-10 | Building handover (PM to SM) checklist | SIT-10 | Install landscaping
[6 empty] | MOB-2 | Assign Site Services Planning check list |  |  | SIT-9 | Rough grade landscaping
Balconies |  | Ceilings |  | Bathrooms |  | MOB-3 | Assign Sub Contractor planning checklist | Commissioning
EXT-9 | Grind all balconys smooth | INS-11 | Geo Tech Engineer inspection | PLU-3 | Water dams 2nd floor |  |  | PREC-12 | Hold Pre Kick-Off meeting with Engineers and Trades people | Mechanical Systems
[10 empty] | SIT-7 | Parkade - Measurement for template
Exterior Walls |  | N/A |  | Cabinets |  |  |  | Locates
EXT-10 | Organize 3rd party building exterior review, including roof, siding and flashings | CON-1 | Assign hollow core erection checklist | CAR-2 | Install cabinets on 1 |  |  | PREC-15 | Schedule locates to be done | N/A
|  | CON-10 | Form footings | CAR-6 | Install cabinets 2nd floor |  |  |  |  | SIT- | 4.1 Site Services & Foundation Work
Mechanical Systems |  | CON-11 | Form grade beam | FIN-3 | finishing parkade level 1 |  |  | Mobilization |  | SIT-1 | Radon rock install
EXT-8 | Exterior | CON-12 | Foundation |  |  |  |  | PREC-11 | De mobilization (checklist) | SIT-2 | Install poly
|  | CON-13 | Hollowcore 2nd floor | Ceilings | [5 empty] | SIT-3 | Form exterior pads
N/A |  | CON-14 | Install balcony piles | DRY-11 | Tape 4th floor ceiling |  |  | N/A |  | SIT-4 | Excatae exterior sidewalks
EXT-1 | Roofing and water proofing | CON-15 | Install hollowcore 2nd floor , Install backer rod & Grout 2nd floor | DRY-6 | Install drywall on 4th floor ceiling |  |  | PREC-1 | 28. Assign Pre excavation checklist | SIT-5 | Form exterior sidewalks
EXT-2 | Install roofing and water proofing | CON-16 | Measure corner offsets for excavation | FIN-2 | Ceiling texture on 1 |  |  | PREC-2 | 3.0 Pre construction and mobilization
EXT-3 | Building paper the whole building | CON-17 | Order all Anchor bolts | FLO-12 | Poly 4th floor ceiling |  |  | PREC-3 | 3.0, 4.0. 5.0 pre, during and post construction total job | Paint
EXT-4 | Board exterior walls on 2nd and sheds | CON-18 | Pour exterior pads | FLO-9 | Install sound bar 4th floor |  |  | PREC-4 | Assign conrete pour checklist | SIT-8 | Parkade - Taper to rectify deficiencies
EXT-5 | Board parkade exterior walls and sheds | CON-19 | Pour exterior sidewalks | FRA-3 | Frame drops on 2nd |  |  | PREC-5 | Assign Equipment & Tools check list
EXT-6 | Board Parkade interior walls | CON-2 | Back fill exterior grade beam | PAI-1 | Paint underside of ceiling in parkade |  |  | PREC-6 | Assign exterior wall pre board inspection check list | Signage
SID-1 | Soffit & Tower Siding | CON-20 | Pour footings | RI-1 | Rough in 4th floor ceiling |  |  | PREC-7 | Assign Final Building Checklist | SIT-11 | Install building signage
SID-2 | Siding towers | CON-21 | Pour grade beam |  |  |  |  | PREC-8 | Assign framing check list
SID-3 | Assign siding checklist | CON-22 | Pour parakde slab | Closets |  |  |  | PREC-9 | Building close out check list | Survey
WIN-1 | install windows and doors | CON-23 | Rebar exterior sidewalks | CAR-6 | Spray out closet interiors and trim on 1 |  |  |  |  | SIT-6 | Call the surveyor to measure for condo plan
|  | CON-24 | Survey for balcony piles | PAI-3 | Paint 1st coat of color on 4th |  |  | Pile Contractor
Parkade |  | CON-25 | Survey offsets, and footings |  |  |  |  | PREC-16 | Schedule Pile contractor
RI-4 | Rough in Parkade | CON-26 | Tie footing rebar | Common Areas
|  | CON-27 | Tie Grade beam rebar | CL-1 | Construction clean on 1 |  |  | Structural
Walls / Ceilings |  | CON-28 | Tie parkade rebar | CL-2 | Final suite clean on 1 |  |  | PREC-13 | Order Rebar (30 days before site delivery date required)
INSU-1 | Poly and insulate on 2nd exterior walls | CON-29 | Tie rebar exterior pads | CX- | Assign Unit Commissioning Inspection list on 1
INSU-2 | Poly and insulate parkade exterior walls | CON-3 | Build templates for Anchor bolts | FRA-1 | Back framing on 2nd |  |  | Training
RI-2 | Rough in exterior walls on 2nd and sheds | CON-4 | Deliver pakade slab rebar |  |  |  |  | PREC-14 | Organize site team to have training and certificates
SID-4 | Siding 2nd floor | CON-5 | deliver rebar (footings and gradebeam only) | Countertops
|  | CON-6 | Dig footing and parkade foot print | CAR-3 | Install countertops on 1
|  | CON-7 | Ensure Sleeves for electrical are run in the grade beam prior to pouring | CAR-5 | Manufacturing and Install countertops 2nd floor
|  | CON-8 | Excavate areas | FLO- | 3rd floor counter top measurement for template
|  | CON-9 | Exterior concrete works | FLO-3 | 2nd floor counter top measurement for template
|  | GYP-1 | Pour Gypcrete | FLO-4 | 4th floor counter top measurements for template
|  | INSU-1 | Install underground insulation
Doors and Frames
|  | Walls / Ceilings |  | CAR-4 | Install interior doors and case on 1
|  | INS-12 | Rebar Inspection Structural Engineer | FRA-7 | Install suite entry doors and frames and Interior doors, trims and jambs
Electrical Systems
|  |  |  | ELE-2 | Electrical finishing on 1
Exterior Walls
|  |  |  | DRY-8 | Load the board on floor and Board exterior walls on 4th and sheds
|  |  |  | FLO-6 | Install fascia and soffit 4th floor
|  |  |  | RI-2 | Rough in exterior walls on 4th and sheds
Fire Systems
|  |  |  | DRY-5 | Fire tape / Fire caulk upper strips on 4th
|  |  |  | PAI-3 | Paint 1rst coat of color on 1
|  |  |  | PAI-4 | Prime paint on 2nd
|  |  |  | SPR-1 | Sprinkler finishing 2nd floor
Flooring
|  |  |  | FLO-3 | 3rd floor finishing
|  |  |  | FLO-4 | 2nd floor finishing
|  |  |  | FLO-5 | Core floors begin at 2nd
|  |  |  | FLO-7 | Install flooring on 1
|  |  |  | FRA- | Framing 2nd floor
Framing
|  |  |  | INS-1 | 4th floor framing inspection
Hallways and Stairwells
|  |  |  | CL-1 | Construction clean 2nd floor
|  |  |  | DRY-11 | Tape 2nd floor hallways and stair wells
|  |  |  | DRY-4 | Board 2nd floor hallways and stairwells
|  |  |  | DRY-8 | Load the board on floor and Board 3rd floor hallways and stairwells
|  |  |  | ELE-3 | Electrical rough in hallways & stairwells on 2nd
|  |  |  | FLO-2 | 2nd floor - Taper do the rectification of deficiences
|  |  |  | FRA-1 | Back framing on 3rd
|  |  |  | MCH-4 | Mechanical rough in hallways & stairwells on 2nd
|  |  |  | SPR-1 | Sprinkler finishing on 1
|  |  |  | SPR-3 | Sprinkler rough in corridor & stairwells on 2nd
Mechanical Systems
|  |  |  | MCH-3 | Mechanical finishing on 1
N/A
|  |  |  | CL-2 | Final suite clean
|  |  |  | CL-3 | Unit Commissioning deficiency clean up confirmed
|  |  |  | CL-4 | Building close out cleanup deficiencies confirmed
|  |  |  | CL-5 | Home owner walk through punch list clean up
|  |  |  | COO-1 | Prepare occupancy paperwork
|  |  |  | COO-2 | Receive occupancy
|  |  |  | COO-3 | Move in dates confirmed
|  |  |  | COO-4 | 5.0 Sales, Occupancy, Closings
|  |  |  | COO-5 | Pre sale move in dates confirmed
|  |  |  | CX- | Assign water and sewer commissioning checklist
|  |  |  | CX-1 | Finalize home owner extras
|  |  |  | CX-10 | Schedule 1 on 1 contractor review meetings
|  |  |  | CX-11 | Schedule contractor group meeting to review survey results
|  |  |  | CX-12 | Project post mordem internal
|  |  |  | CX-13 | Move info to Dev co work flow 1.0, 2.0, 6.0
|  |  |  | CX-2 | Load home owners into copper
|  |  |  | CX-3 | Move in binders created
|  |  |  | CX-4 | Update home owner permissions in Construction online
|  |  |  | CX-5 | Unit Commissioning Inspection list
|  |  |  | CX-6 | Keys and gift cards and welcome package created
|  |  |  | CX-7 | Home owner walk through and punch list
|  |  |  | CX-8 | New move ins and warranty through service manager
|  |  |  | CX-9 | Send out contractor surveys
|  |  |  | DRY-1 | 4.3 Rough In, Steel Stud Drywall
|  |  |  | DRY-2 | Assign Corridor & Stairwell pre board inspection checklist
|  |  |  | DRY-3 | Assign pre board inspection check list
|  |  |  | DRY-4 | Board and prepare electrical/mechanical room
|  |  |  | ELE-1 | Electrical rough in in slab
|  |  |  | ELE-3 | Electrical rough in in ceiling
|  |  |  | ELE-4 | Main service electrical room install
|  |  |  | EXT-11 | Install exterior decking all floors
|  |  |  | FIN-1 | 4.4 Finishing
|  |  |  | FLO-10 | Install windows & doors all floors
|  |  |  | FLO-8 | Install railings on all floors
|  |  |  | FRA- | 4.2 Framing
|  |  |  | FRA-5 | Install metal doors and frames
|  |  |  | FRA-6 | Install pocket door frames
|  |  |  | GYP-1 | Gypcrete
|  |  |  | INS-10 | Fire alarm verification
|  |  |  | INS-13 | Sprinkler testing
|  |  |  | INS-2 | Architectural walk throughs
|  |  |  | INS-3 | Building inspector walk throughs
|  |  |  | INS-4 | Call for Electrical and Mechanical Inspection
|  |  |  | INS-5 | Call for envelope reviewer inspection
|  |  |  | INS-6 | Call for Mechanical & Electrical inspection of attic
|  |  |  | INS-7 | Call for structural inspection
|  |  |  | INS-8 | Contact Canada Post to get the address's created
|  |  |  | INS-9 | Enginering walk throughs
|  |  |  | MCH-1 | Mechanical rough in in slab
|  |  |  | MCH-2 | Main service mechanical room install
|  |  |  | MCH-4 | Mechanical rough in in ceiling
|  |  |  | PAI-2 | Final coat of paint
|  |  |  | PLU-1 | Deliver tubs & showers to suites / checklist
|  |  |  | PLU-2 | Install tubs and showers
|  |  |  | RI-3 | Rough in interior walls
|  |  |  | SPR-2 | Sprinkler install in attic
|  |  |  | SPR-4 | Install underground sprinklers
|  |  |  | STL-1 | Strucutral Steel
|  |  |  | STL-2 | Structural steel erection
|  |  |  | VF-1 | Install stairs
|  |  |  | VF-2 | Delivery of Elevator & Install
Parkade
|  |  |  | DRY-10 | Tape parkade interior and exterior walls
|  |  |  | FRA- | Framing parkade
|  |  |  | FRA-2 | Frame and board Parkade beams
|  |  |  | FRA-4 | Frame interior parkade walls
|  |  |  | RI-1 | Rough in parkade slab
Roof
|  |  |  | FRA- | Roof trusses install
Structural
|  |  |  | PAI-4 | Prime paint on 1
Suites
|  |  |  | CL-2 | Final suite clean on 4th
|  |  |  | DRY-10 | Tape suites on 2nd
|  |  |  | DRY-7 | Layout suites on 2nd floor
|  |  |  | ELE-3 | Electrical rough in on 2nd
|  |  |  | FIN-3 | finishing on 4th
|  |  |  | FLO-11 | Layout suites 4th floor
|  |  |  | FRA- | Layout suites on 3rd floor
|  |  |  | MCH-3 | Mechanical finishing on 4th
|  |  |  | MCH-4 | Mechanical rough in on 2nd
|  |  |  | RI-1 | Rough in 2nd floor
|  |  |  | SPR-3 | Sprinkler rough in on 2nd
Walls
|  |  |  | DRY-4 | Board 2nd floor walls
Walls / Ceilings
|  |  |  | DRY-4 | Board upper 16" strips in common area and all suites on 2nd
|  |  |  | DRY-5 | Fire tape / Fire caulk upper strips on 2nd
|  |  |  | DRY-8 | Load boards on floor and Board 3rd floor walls
|  |  |  | DRY-9 | Steel stud install on 2nd & drywall behind the tubs including fire wall taping if it is a fire wall
|  |  |  | FLO-2 | 3rd floor - Taper do the rectification of deficiencies
|  |  |  | FRA- | Framing 4th floor
|  |  |  | PAI-4 | Prime paint on 3rd