## Sheet1
Phase | Location | Area | Trade | Activity Name | Color | Activity Code | Start | Finish
Weather Days | Weather | Weather | McGough | Weather Days (3 days per month) | #000000 | WD | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | All | Building | McGough | SWPPP | #C40E4D | M-10 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | All | Building | McGough | Substantial Completion | #C40E4D | M-11 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | McGough | Submit Store Front Shop Drawings | #C40E4D | SUB-27 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | Architect | DD 1 Safety & Risk Assessment | #E4DFEC | M-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | Architect | DD 2 | #E4DFEC | M-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | Architect | DD 3 | #E4DFEC | M-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | Architect | Architect - DD 4 | #E4DFEC | M-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | Architect | DD Package Submission Owner & Cost Estimator | #E4DFEC | M-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | Architect | Early Site Utility, Grading, Foundation Package & Underfloor MEP | #E4DFEC | M-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | Architect | Start CD Package | #E4DFEC | M-7 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | McGough | Submit Store Front Product Data | #C40E4D | SUB-28 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | McGough | Submit Steel Structure Shop Drawings | #C40E4D | SUB-29 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | Owner | Owner Comments Due | #76933C | OW-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | Owner | Owner DD & GMP Signoff | #76933C | OW-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | Owner | DD Final Page Turn & Owner Sign-off | #76933C | OW-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | Owner | Issue Complete CD Package | #76933C | OW-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | Architect | Review of Early Site Utility, Grading, Foundation Package & Underfloor MEP for Contracts | #E4DFEC | M-8 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | Architect | Review of CD to Issue Contracts | #E4DFEC | M-9 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | McGough | Submit Steel Structure Product Data | #C40E4D | SUB-30 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | McGough | Submit Security Glazing Shop Drawings | #C40E4D | SUB-31 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | McGough | Submit Security Glazing Product Data | #C40E4D | SUB-32 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | McGough | Submit Overhead Door Shop Drawings | #C40E4D | SUB-33 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | McGough | Submit Overhead Door Product Data | #C40E4D | SUB-34 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | McGough | Submit Kitchen Equipment Shop Drawings | #C40E4D | SUB-35 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | McGough | Submit Kitchen Equipment Product Data | #C40E4D | SUB-36 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | McGough | Submit Generator Shop Drawings | #C40E4D | SUB-37 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | McGough | Submit Generator Product Data | #C40E4D | SUB-38 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | McGough | Submit Electrical Switchgear Shop Drawings | #C40E4D | SUB-39 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | McGough | Submit Electrical Switchgear Product Data | #C40E4D | SUB-40 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | McGough | Submit Curtainwall Shop Drawings | #C40E4D | SUB-41 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | McGough | Submit Curtainwall Product Data | #C40E4D | SUB-42 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | McGough | Submit Chiller Shop Drawings | #C40E4D | SUB-43 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | McGough | Submit Chiller Product Data | #C40E4D | SUB-44 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | McGough | Submit Boilers Shop Drawings | #C40E4D | SUB-45 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | McGough | Submit Boilers Product Data | #C40E4D | SUB-46 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | McGough | Submit ATS Shop Drawings | #C40E4D | SUB-47 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | McGough | Submit ATS Product Data | #C40E4D | SUB-48 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | Owner | Procure Transformer (by others) | #76933C | OW-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | Electrical | Procure & Fabricate Generator | #FFFFE8 | EL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | Electrical | Procure & Fabricate Electrical Switchgear | #FFFFE8 | EL-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | Electrical | Procure & Fabricate ATS | #FFFFE8 | EL-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Mechanical | Hook-up/Final Connections Chillers - Mechanical Yard | #0F243E | MEC-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Mechanical | Install AHU 1 (Roof) - Zone 5 | #0F243E | MEC-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Mechanical | Install AHU 2 (Roof) - Zone 6 | #0F243E | MEC-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | Steel | Procure & Fabricate Structural Steel | #1F5499 | SL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | Glass/Glazing | Procure & Fabricate Security Glazing | #DAEEF3 | PRO-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | OH Door | Procure & Fabricate Overhead Door (4) | #F79646 | PRO-26 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | Glass/Glazing | Procure & Fabricate Curtainwall | #DAEEF3 | PRO-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | Glass/Glazing | Procure & Fabricate Store Fronts | #DAEEF3 | PRO-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | Doors & Hardware | Procure & Fabricate Antiligature Door Hardware/Kingsway Kits | #6D5B23 | DOOR-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | Kitchen Equip | Procure & Fabricate Kitchen Equipment | #948A54 | PRO-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | McGough | Submit Antiligature Door Hardware/Kingsway Kits Shop Drawings | #C40E4D | SUB-49 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | McGough | Submit Antiligature Door Hardware/Kingsway Kits Product Data | #C40E4D | SUB-50 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | McGough | Submit AHU Shop Drawings | #C40E4D | SUB-51 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | McGough | Submit AHU Product Data | #C40E4D | SUB-52 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | McGough | QA/QC Complete List - Zone 6 | #C40E4D | MG-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | McGough | QA/QC Complete List - Zone 5 | #C40E4D | MG-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | Architect | Owner Approve Chiller Shop Drawings | #E4DFEC | SUB-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | Architect | Owner Approve AHU Shop Drawings | #E4DFEC | SUB-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | Architect | Owner Approve Generator Shop Drawings | #E4DFEC | SUB-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | Architect | Owner Approve Electrical Switchgear Shop Drawings | #E4DFEC | SUB-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | Architect | Owner Approve ATS Shop Drawings | #E4DFEC | SUB-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | Architect | Owner Approve Boilers Shop Drawings | #E4DFEC | SUB-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | McGough | QA/QC Complete List - Zone 4 | #C40E4D | MG-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | McGough | QA/QC Complete List - Zone 3 | #C40E4D | MG-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | McGough | QA/QC Complete List - Zone 2 | #C40E4D | MG-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | McGough | QA/QC Complete List - Zone 1 | #C40E4D | MG-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | All | Pre-Qual | McGough | Pre-Qual Structural Steel Sub | #C40E4D | PRO-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | All | Pre-Qual | McGough | Pre-Qual Store Fronts Sub | #C40E4D | PRO-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | All | Pre-Qual | McGough | Pre-Qual Security Glazing Sub | #C40E4D | PRO-7 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | Architect | Owner Approve Curtainwall Shop Drawings | #E4DFEC | SUB-7 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | Architect | Owner Approve Store Front Shop Drawings | #E4DFEC | SUB-8 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | Architect | Owner Approve Security Glazing Shop Drawings | #E4DFEC | SUB-9 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | Architect | Owner Approve Steel Structure Shop Drawings | #E4DFEC | SUB-10 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | Architect | Owner Approve Overhead Door Shop Drawings | #E4DFEC | SUB-11 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | Architect | Owner Approve Kitchen Equipment Shop Drawings | #E4DFEC | SUB-12 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Shop Drawings | Architect | Owner Approve Antiligature Door Hardware/Kingsway Kits Shop Drawings | #E4DFEC | SUB-13 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | All | Pre-Qual | McGough | Pre-Qual Overhead Door Sub | #C40E4D | PRO-8 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | All | Pre-Qual | McGough | Pre-Qual Mechanical Sub | #C40E4D | PRO-9 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | All | Pre-Qual | McGough | Pre-Qual Kitchen Equipment Sub | #C40E4D | PRO-10 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | All | Pre-Qual | McGough | Pre-Qual Electrical Sub | #C40E4D | PRO-11 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | All | Pre-Qual | McGough | Pre-Qual Antiligature Door Hardware/Kingsway Kits Sub | #C40E4D | PRO-12 | 1969-12-31 18:01 | 1969-12-31 18:01
Permits | Permits | Permits | McGough | Permitting - TXDot | #C40E4D | PER-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | McGough | OH MEPF Inspections - Zone 6 | #C40E4D | MG-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | McGough | OH MEPF Inspections - Zone 5 | #C40E4D | MG-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | McGough | OH MEPF Inspections - Zone 4 | #C40E4D | MG-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | McGough | OH MEPF Inspections - Zone 3 | #C40E4D | MG-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | McGough | OH MEPF Inspections - Zone 2 | #C40E4D | MG-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | McGough | OH MEPF Inspections - Zone 1 | #C40E4D | MG-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | All | Building | McGough | Mobilization | #C40E4D | MG-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | Architect | Owner Approve Curtainwall Product Data | #E4DFEC | SUB-14 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | Architect | Owner Approve Store Front Product Data | #E4DFEC | SUB-15 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | Architect | Owner Approve Security Glazing Product Data | #E4DFEC | SUB-16 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | Architect | Owner Approve Steel Structure Product Data | #E4DFEC | SUB-17 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | Architect | Owner Approve Overhead Door Product Data | #E4DFEC | SUB-18 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | Architect | Owner Approve Chiller Product Data | #E4DFEC | SUB-19 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | Architect | Owner Approve AHU Product Data | #E4DFEC | SUB-20 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | Architect | Owner Approve Generator Product Data | #E4DFEC | SUB-21 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | Architect | Owner Approve Kitchen Equipment Product Data | #E4DFEC | SUB-22 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | Architect | Owner Approve Electrical Switchgear Product Data | #E4DFEC | SUB-23 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | Architect | Owner Approve ATS Product Data | #E4DFEC | SUB-24 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | Architect | Owner Approve Boilers Product Data | #E4DFEC | SUB-25 | 1969-12-31 18:01 | 1969-12-31 18:01
Submittals | All | Product Data | Architect | Owner Approve Antiligature Door Hardware/Kingsway Kits Product Data | #E4DFEC | SUB-26 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | All | Pre-Qual | McGough | McGough - Pre-Qual Curtainwall Sub | #C40E4D | MG-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | Excavation | All | Site | Backfill Select Fill - Building Pad | #808080 | SITE-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | Outsite | Clear & Grub | Site | Clear & Grub - Building Foot Print | #808080 | SITE-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | Excavation | All | Site | Excavate - Building Pad | #808080 | SITE-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | West | Playa Lake | Site | Excavate - Playa Lake West | #808080 | SITE-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | East | Playa Lake East | Site | Expand (Excavate) Existing Slopes - Playa Lake East | #808080 | SITE-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | West | Playa Lake | Site | Grade Slopes - Playa Lake West | #808080 | SITE-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | East | Playa Lake East | Site | Install 12" HDPE Pipe - Playa Lake East | #808080 | SITE-7 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | East | Playa Lake East | Site | Install 15" HDPE Pipe - Playa Lake East | #808080 | SITE-7 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | East | Playa Lake East | Site | Install 18" HDPE Pipe - Playa Lake East | #808080 | SITE-7 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | East | Playa Lake East | Site | Install 24" HDPE Pipe - Playa Lake East | #808080 | SITE-7 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | East | Playa Lake East | Site | Install 30" HDPE Pipe - Playa Lake East | #808080 | SITE-7 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | East | Playa Lake East | Site | Install Concrete Pilot Channel - Playa Lake East | #808080 | SITE-8 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | East | Playa Lake East | Site | Install Inlets (5) - Playa Lake East | #808080 | SITE-9 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | East | Playa Lake | Site | Install Manholes (3) - Playa Lake East | #808080 | SITE-10 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | East | Playa Lake East | Site | Install Precast Discharge w/Rip Rap - Playa Lake East | #808080 | SITE-11 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | East | Playa Lake East | Site | Regrade Slopes - Playa Lake East | #808080 | SITE-12 | 1969-12-31 18:01 | 1969-12-31 18:01
Utilities | All | All | Utilities | Excavate, Install & Backfill 8" Water Line From Peach Ave | #8DB4E2 | UT-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Utilities | All | All | Utilities | Excavate, Install & Backfill 4" Gas Service From Peach Ave | #8DB4E2 | UT-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Utilities | All | All | Utilities | Install 8" Waste Water From Peach Ave | #8DB4E2 | UT-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Utilities | All | All | Utilities | Install Electric Utility Trench (Proposed) (Includes Excavate, Backfill, & Flowable Fill) | #8DB4E2 | UT-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Utilities | All | All | Utilities | Install Fiber Line (Includes Trenching) | #8DB4E2 | UT-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Sitework | Site | All | Concrete | Site Paving | #215967 | CON-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Landscape | Hardscape | All | Landscape | Hardscape/Landscaping | #0F243E | LAN-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Deep Structural | Deep Structural | Piler | Install Piers (24') - Zone 1 | #60497A | PI-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Deep Structural | Deep Structural | Piler | Install Piers (24') - Zone 2 | #60497A | PI-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Deep Structural | Deep Structural | Piler | Install Piers (24') - Zone 3 | #60497A | PI-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Deep Structural | Deep Structural | Piler | Install Piers (24') - Zone 4 | #60497A | PI-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Deep Structural | Deep Structural | Piler | Install Piers (24') - Zone 5 | #60497A | PI-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Deep Structural | Deep Structural | Piler | Install Pile Caps (30) - All Zones | #60497A | PI-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Deep Structural | Deep Structural | Piler | Install Piers (24') - Zone 6 | #60497A | PI-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Grade Beams | Grade Beams | Concrete | F/R/P Grade Beams - East (Zones 1 & 3) | #215967 | CON-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Grade Beams | Grade Beams | Concrete | F/R/P Grade Beams - South (Zones 1, 2 & 6) | #215967 | CON-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Grade Beams | Grade Beams | Concrete | F/R/P Grade Beams - West (Zones 5 & 6) | #215967 | CON-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Grade Beams | Grade Beams | Concrete | F/R/P Grade Beams - North (Zones 3, 4 & 5) | #215967 | CON-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Grade Beams | Grade Beams | Concrete | F/R/P Internal Grade Beams | #215967 | CON-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Slabs | Zone 1 | Concrete | F/R/P Slab on Grade - Zone 1 | #215967 | CON-7 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Slabs | Zone 2 | Concrete | F/R/P Slab on Grade - Zone 2 | #215967 | CON-8 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Slabs | Zone 3 | Concrete | F/R/P Slab on Grade - Zone 3 | #215967 | CON-9 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Slabs | Zone 4 | Concrete | F/R/P Slab on Grade - Zone 4 | #215967 | CON-10 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Slabs | Zone 5 | Concrete | F/R/P Slab on Grade - Zone 5 | #215967 | CON-11 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Slabs | Zone 6 | Concrete | F/R/P Slab on Grade - Zone 6 | #215967 | CON-12 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Underground Strucuture | Zone 1 | Elect & Plumb | Under Slab MEP - Zone 1 | #FFFFC9 | ELPL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Underground Strucuture | Mechanical Yard | Elect & Plumb | Underground MEP - Mechanical Yard | #FFFFC9 | ELPL-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Underground Strucuture | Zone 2 | Elect & Plumb | Under Slab MEP - Zone 2 | #FFFFC9 | ELPL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Underground Strucuture | Zone 3 | Elect & Plumb | Under Slab MEP - Zone 3 | #FFFFC9 | ELPL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Underground Strucuture | Zone 4 | Elect & Plumb | Under Slab MEP - Zone 4 | #FFFFC9 | ELPL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Underground Strucuture | Zone 5 | Elect & Plumb | Under Slab MEP - Zone 5 | #FFFFC9 | ELPL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Underground Strucuture | Zone 6 | Elect & Plumb | Under Slab MEP - Zone 6 | #FFFFC9 | ELPL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Underground Strucuture | Zone 7A | Elect & Plumb | Underground MEP - Zone 7A | #FFFFC9 | ELPL-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Foundations | Underground Strucuture | Zone 7B | Elect & Plumb | Underground MEP - Zone 7B | #FFFFC9 | ELPL-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | Above Grade Structures | Zone 1 | Steel | Steel Framing & Decking - Zone 1 | #1F5499 | SL-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | Above Grade Structures | Zone 2 | Steel | Steel Framing & Decking - Zone 2 | #1F5499 | SL-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | Above Grade Structures | Zone 3 | Steel | Steel Framing & Decking - Zone 3 | #1F5499 | SL-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | Above Grade Structures | Zone 4 | Steel | Steel Framing & Decking - Zone 4 | #1F5499 | SL-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | Above Grade Structures | Zone 5 | Steel | Steel Framing & Decking - Zone 5 | #1F5499 | SL-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | Above Grade Structures | Zone 6 | Steel | Steel Framing & Decking - Zone 6 | #1F5499 | SL-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Framer | Ceiling Trim Out - Zone 1 | #FF80B1 | FR-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Framer | Ceiling Trim Out - Zone 3 | #FF80B1 | FR-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Weatherproofer | Exterior Weatherproof - North Elevation | #1F497D | WP-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Glass/Glazing | Curatinwall - North Elevation | #DAEEF3 | GLA-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Masonry | Masonry - North Elevation | #3CD646 | MAS-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Glass/Glazing | Store Front/Glass/Glazing - North Elevation | #DAEEF3 | GLA-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Framer | Close Ceiling - Zone 1 | #FF80B1 | FR-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Framer | Close Ceilings - Zone 3 | #FF80B1 | FR-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Weatherproofer | Exterior Weatherproof - West Elevation | #1F497D | WP-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Cladding | Exterior Metal Panels - West Elevation | #92CDDC | CLA-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Masonry | Exterior Masonry - West Elevation | #3CD646 | MAS-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Glass/Glazing | Store Front/Glass/Glazing - West Elevation | #DAEEF3 | GLA-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Framer | Exterior Framing - East Elevation | #FF80B1 | FR-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Framer | Exterior Framing - North Elevation | #FF80B1 | FR-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Weatherproofer | Exterior Weatherproof - South Elevation | #1F497D | WP-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Cladding | Exterior Metal Panels - South Elevation | #92CDDC | CLA-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Masonry | Exterior Masonry - South Elevation | #3CD646 | MAS-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Glass/Glazing | Store Front/Glass/Glazing - South Elevation | #DAEEF3 | GLA-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Framer | Exterior Framing - South Elevation | #FF80B1 | FR-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Framer | Exterior Framing - West Elevation | #FF80B1 | FR-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Weatherproofer | Exterior Weatherproof - East Elevation | #1F497D | WP-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Cladding | Exterior Metal Panels - East Elevation | #92CDDC | CLA-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Masonry | Exterior Masonry - East Elevation | #3CD646 | MAS-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Glass/Glazing | Store Front/Glass/Glazing - East Elevation | #DAEEF3 | GLA-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Roofer | Install Roofing - All Zones | #C0504D | ROOF-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Misc Metals | Install Screenwall - Zone 2 | #808080 | MIS-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Misc Metals | Install Screenwall - Zone 5 | #808080 | MIS-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Misc Metals | Install Screenwall - Zone 6 | #808080 | MIS-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | MEP | OH MEPF Rough-in - Zone 6 | #948A54 | MEP-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | MEP | OH MEPF Rough-in - Zone 5 | #948A54 | MEP-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Contracts | McGough | Issue Contract to Structural Steel Sub | #C40E4D | PRO-13 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Contracts | McGough | Issue Contract to Store Fronts Sub | #C40E4D | PRO-14 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Mechanical | Install AHU 3 & 4 (Roof) - Zone 4 | #0F243E | MEC-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Mechanical Room | Concrete | Install Housekeeping Pads - Zone 1 Mechanical Room | #215967 | CON-13 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Mechanical | Install AHU 5 (Roof) - Zone 3 | #0F243E | MEC-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Mechanical Room | Plumbing | Set/Install HWP (3) - Zone 1 Mechanical Room | #3017FF | PLU-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Mechanical Room | Plumbing | Set/Install CHWP (3) - Zone 1 Mechanical Room | #3017FF | PLU-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Mechanical | Install AHU 6 (Roof) - Zone 2 | #0F243E | MEC-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Mechanical Room | Electrical | Install Electrical Switchgear - Zone 1 Mechanical Room | #FFFFE8 | EL-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Mechanical Room | Electrical | Install ATS - Zone 1 Mechanical Room | #FFFFE8 | EL-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | MEP | OH MEPF Rough-in - Zone 4 | #948A54 | MEP-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | MEP | OH MEPF Rough-in - Zone 3 | #948A54 | MEP-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Contracts | McGough | Issue Contract to Security Glazing Sub | #C40E4D | PRO-15 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Contracts | McGough | Issue Contract to Overhead Door Sub | #C40E4D | PRO-16 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Mechanical | Install AHU 7 (Roof) - Zone 1 | #0F243E | MEC-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | MEP | OH MEPF Rough-in - Zone 2 | #948A54 | MEP-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | MEP | OH MEPF Rough-in - Zone 1 | #948A54 | MEP-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Contracts | McGough | Issue Contract to Mechanical Sub | #C40E4D | PRO-17 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Contracts | McGough | Issue Contract to Kitchen Equipment Sub | #C40E4D | PRO-18 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Mechanical Room | Mechanical | Install Boilers - Zone 1 Mechanical Room | #0F243E | MEC-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | MEP | In-wall MEP Rough-in - Zone 6 | #948A54 | MEP-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | MEP | In-wall MEP Rough-in - Zone 5 | #948A54 | MEP-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Contracts | McGough | Issue Contract to Electrical Sub | #C40E4D | PRO-19 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Contracts | McGough | Issue Contract to Curtainwall Sub | #C40E4D | PRO-20 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | Mechanical | Procure & Fabricate AHU's | #0F243E | PRO-23 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | MEP | In-wall MEP Rough-in - Zone 4 | #948A54 | MEP-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | MEP | In-wall MEP Rough-in - Zone 3 | #948A54 | MEP-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Contracts | McGough | Issue Contract to Civil Sub | #C40E4D | PRO-21 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Contracts | McGough | Issue Contract to Antiligature Door Hardware/Kingsway Kits Sub | #C40E4D | PRO-22 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | Mechanical | Procure & Fabricate Boilers | #0F243E | PRO-25 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | MEP | In-wall MEP Rough-in - Zone 2 | #948A54 | MEP-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | MEP | In-wall MEP Rough-in - Zone 1 | #948A54 | MEP-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | McGough | In-wall MEP Inspections - Zone 6 | #C40E4D | MG-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | McGough | In-wall MEP Inspections - Zone 5 | #C40E4D | MG-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Procurement | Procurement | Material | Mechanical | Procure & Fabricate Chillers | #0F243E | PRO-24 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Flooring | Sealed Concrete Flooring - Zone 6 | #8064A2 | FL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Framer | Exterior Sheathing - East Elevation | #FF80B1 | FR-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Framer | Exterior Sheathing - North Elevation | #FF80B1 | FR-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Framer | Exterior Sheathing - South Elevation | #FF80B1 | FR-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Drywall | Two Side Walls - Zone 1 | #FFD662 | DRY-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Drywall | Tape & Float - Zone 1 | #FFD662 | DRY-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Tile | Install Wet Work (Restroom, Locker Room & Shower Area) - Zone 1 | #67FF85 | T-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Exteriors | Building Envelope | North Elevation | Framer | Exterior Sheathing - West Elevation | #FF80B1 | FR-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Paint | Install Hard Ceiling - Zone 2 | #D8E4BC | PA-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Framer | Frame Walls & Ceilings - Zone 1 | #FF80B1 | FR-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Paint | Paint 1st Coat - Zone 1 | #D8E4BC | PA-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Millwork | Install Millwork - Zone 1 | #FFE29A | MILL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Paint | Paint 1st Coat - Zone 2 | #D8E4BC | PA-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Inspection | Ceiling Inspection - Zone 1 | #C00000 | INS-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Framer | Frame Walls & Ceilings - Zone 2 | #FF80B1 | FR-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Plumbing | Plumbing Fixtures & Trim Out - Zone 1 | #3017FF | PLU-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | OH Doors | Install OH Doors (2) - Zone 1 Mechanical Room | #FABF8F | OH-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Flooring | Sealed Concrete Flooring - Zone 5 | #8064A2 | FL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Electrical | Electrical Fixtures & Trim Out - Zone 1 | #FFFFE8 | EL-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Doors | Install Doors & Hardware - Zone 1 | #6D5B23 | DOOR-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | McGough | In-wall MEP Inspections - Zone 4 | #C40E4D | MG-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Concrete | F/R/P Concrete Pads - Mechanical Yard | #215967 | CON-14 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Concrete | Cure Concrete Pads - Mechanical Yard | #215967 | CON-15 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Concrete | F/R/P Concrete Pad Sally Port - Mechanical Yard | #215967 | CON-16 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Masonry | Install CMU Walls - Mechanical Yard | #3CD646 | MAS-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Concrete | Cure Concrete Pad Sally Port - Mechanical Yard | #215967 | CON-17 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Mechanical | Set Chillers (3) - Mechanical Yard | #0F243E | MEC-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Mechanical | Set Fuel Tank - Mechanical Yard | #0F243E | MEC-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Electrical | Set Generator - Mechanical Yard | #FFFFE8 | EL-7 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Electrical | Hook-up/Final Connections Generator - Mechanical Yard | #FFFFE8 | EL-8 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Mechanical Room | Mechanical | Set/Install VFD's - Zone 1 Mechanical Room | #0F243E | MEC-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Kitchen | Specialties | Install Kitchen Equipment | #FFD6B5 | SPE-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Framer | Frame Walls & Ceilings - Zone 3 | #FF80B1 | FR-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Doors | Install Door Frames - Zone 2 | #6D5B23 | DOOR-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Framer | Frame Walls & Ceilings - Zone 4 | #FF80B1 | FR-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Drywall | Two Side Walls - Zone 2 | #FFD662 | DRY-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Drywall | Tape & Float - Zone 2 | #FFD662 | DRY-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Tile | Install Wet Work (Restrooms) - Zone 2 | #67FF85 | T-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Paint | Paint 1st Coat - Zone 3 | #D8E4BC | PA-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | OH Doors | Install OH Doors (2) - Zone 2 | #FABF8F | OH-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Framer | Frame Walls & Ceilings - Zone 5 | #FF80B1 | FR-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Paint | Paint 1st Coat - Zone 4 | #D8E4BC | PA-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Paint | Paint 1st Coat - Zone 5 | #D8E4BC | PA-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Paint | Paint 1st Coat - Zone 6 | #D8E4BC | PA-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Plumbing | Plumbing Fixtures & Trim Out - Zone 2 | #3017FF | PLU-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Millwork | Install Millwork - Zone 2 | #FFE29A | MILL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Flooring | Sealed Concrete Flooring - Zone 1 | #8064A2 | FL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Flooring | Install Tile Flooring - Zone 4 | #8064A2 | FL-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Electrical | Electrical Fixtures & Trim Out - Zone 2 | #FFFFE8 | EL-9 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Doors | Install Doors & Hardware - Zone 2 | #6D5B23 | DOOR-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | McGough | In-wall MEP Inspections - Zone 3 | #C40E4D | MG-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Framer | Frame Walls & Ceilings - Zone 6 | #FF80B1 | FR-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Doors | Install Door Frames - Zone 3 | #6D5B23 | DOOR-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Framer | In-wall Blocking - Zone 1 | #FF80B1 | FR-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Drywall | Two Side Walls - Zone 3 | #FFD662 | DRY-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Paint | Paint 2nd Coat - Zone 1 | #D8E4BC | PA-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Drywall | Tape & Float - Zone 3 | #FFD662 | DRY-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Paint | Paint 2nd Coat - Zone 2 | #D8E4BC | PA-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Framer | In-wall Blocking - Zone 2 | #FF80B1 | FR-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Framer | In-wall Blocking - Zone 3 | #FF80B1 | FR-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Tile | Install Wet Work (Restrooms) - Zone 3 | #67FF85 | T-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Framer | In-wall Blocking - Zone 4 | #FF80B1 | FR-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Inspection | Ceiling Inspection - Zone 3 | #C00000 | INS-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Framer | In-wall Blocking - Zone 5 | #FF80B1 | FR-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Plumbing | Plumbing Fixtures & Trim Out - Zone 3 | #3017FF | PLU-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Millwork | Install Millwork - Zone 3 | #FFE29A | MILL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Flooring | Install Tile Flooring - Zone 3 | #8064A2 | FL-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Flooring | Install Terazzo Flooring - Zone 4 | #8064A2 | FL-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Electrical | Electrical Fixtures & Trim Out- Zone 3 | #FFFFE8 | EL-9 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Flooring | Install Sheet Rubber Flooring - Zone 6 | #8064A2 | FL-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Doors | Install Doors & Hardware - Zone 3 | #6D5B23 | DOOR-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | McGough | In-wall MEP Inspections - Zone 2 | #C40E4D | MG-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Framer | In-wall Blocking - Zone 6 | #FF80B1 | FR-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Doors | Install Door Frames - Zone 4 | #6D5B23 | DOOR-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Framer | Install ACT Ceilings - Zone 2 | #FF80B1 | FR-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Drywall | Two Side Walls - Zone 4 | #FFD662 | DRY-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Paint | Paint 2nd Coat - Zone 3 | #D8E4BC | PA-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Drywall | Tape & Float - Zone 4 | #FFD662 | DRY-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Paint | Paint 2nd Coat - Zone 4 | #D8E4BC | PA-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Framer | Install ACT Ceilings - Zone 4 | #FF80B1 | FR-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Paint | Paint 2nd Coat - Zone 5 | #D8E4BC | PA-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Tile | Install Wet Work - Zone 4 | #67FF85 | T-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Drywall | Install Hard Ceilings - Zone 4 | #FFD662 | DRY-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Millwork | Install Millwork - Zone 4 | #FFE29A | MILL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Plumbing | Plumbing Fixtures & Trim Out - Zone 4 | #3017FF | PLU-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Flooring | Install Sheet Rubber Flooring - Zone 5 | #8064A2 | FL-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Flooring | Install Sheet Rubber Flooring - Zone 3 | #8064A2 | FL-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Electrical | Electrical Fixtures & Trim Out - Zone 4 | #FFFFE8 | EL-9 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Flooring | Install Sheet Rubber Flooring - Zone 2 | #8064A2 | FL-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Flooring | Install Resinous Flooring - Zone 6 | #8064A2 | FL-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Flooring | Install Resinous Flooring - Zone 5 | #8064A2 | FL-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Doors | Install Doors & Hardware - Zone 4 | #6D5B23 | DOOR-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | McGough | In-wall MEP Inspections - Zone 1 | #C40E4D | MG-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Framer | Install ACT Ceilings - Zone 5 | #FF80B1 | FR-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Doors | Install Door Frames - Zone 5 | #6D5B23 | DOOR-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Framer | Install ACT Grid - Zone 1 | #FF80B1 | FR-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Framer | Install ACT Grid - Zone 3 | #FF80B1 | FR-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Drywall | Tape & Float - Zone 5 | #FFD662 | DRY-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Paint | Paint 2nd Coat - Zone 6 | #D8E4BC | PA-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Paint | Paint Final Coat - Zone 1 | #D8E4BC | PA-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Framer | Install Ceilings - Zone 6 | #FF80B1 | FR-7 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Paint | Paint Final Coat - Zone 2 | #D8E4BC | PA-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Tile | Install Wet Work (Patient & Staff Restrooms) - Zone 5 | #67FF85 | T-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Drywall | Install Hard Lid Ceilings - Zone 5 | #FFD662 | DRY-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Millwork | Install Millwork - Zone 5 | #FFE29A | MILL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Flooring | Install Resinous Flooring - Zone 4 | #8064A2 | FL-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 2 | Flooring | Install Resinous Flooring - Zone 2 | #8064A2 | FL-5 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Electrical | Electrical Fixtures & Trim Out - Zone 5 | #FFFFE8 | EL-9 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Flooring | Install LVT Flooring - Zone 6 | #8064A2 | FL-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Flooring | Install LVT Flooring - Zone 5 | #8064A2 | FL-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Plumbing | Plumbing Fixtures & Trim Out - Zone 5 | #3017FF | PLU-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Specialties | Care Team Station Finishes - Zone 5 | #FFD6B5 | SPE-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Doors | Install Doors & Hardware - Zone 5 | #6D5B23 | DOOR-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Low Voltage | Safety/Security & Troubleshooting - Zone 5 | #FF7225 | LV-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | All | Building | McGough | GMP Issued | #C40E4D | MG-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Framer | Install Door Frames - Zone 1 | #FF80B1 | FR-8 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Doors | Install Door Frames - Zone 6 | #6D5B23 | DOOR-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Framer | Paint Final Coat - Zone 3 | #FF80B1 | FR-9 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Drywall | Two Side Walls - Zone 6 | #FFD662 | DRY-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Drywall | Tape & Float - Zone 6 | #FFD662 | DRY-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Paint | Paint Final Coat - Zone 4 | #D8E4BC | PA-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Paint | Paint Final Coat - Zone 5 | #D8E4BC | PA-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Framer | Paint Final Coat - Zone 6 | #FF80B1 | FR-9 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 5 | Framer | Two Side Walls - Zone 5 | #FF80B1 | FR-10 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Drywall | Install Hard Lid Ceilings - Zone 6 | #FFD662 | DRY-4 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Flooring | Install LVT Flooring - Zone 4 | #8064A2 | FL-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 3 | Flooring | Install LVT Flooring - Zone 3 | #8064A2 | FL-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Tile | Install Wet Work (Patient & Staff Restrooms) - Zone 6 | #67FF85 | T-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Electrical | Electrical Fixtures & Trim Out - Zone 6 | #FFFFE8 | EL-9 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 1 | Flooring | Install LVT Flooring - Zone 1 | #8064A2 | FL-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Millwork | Install Millwork - Zone 6 | #FFE29A | MILL-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 4 | Flooring | Install Athletic Gym Vinyl Flooring - Zone 4 | #8064A2 | FL-7 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Plumbing | Plumbing Fixtures & Trim Out - Zone 6 | #3017FF | PLU-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Doors | Install Doors & Hardware - Zone 6 | #6D5B23 | DOOR-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Low Voltage | Safety/Security & Troubleshooting - Zone 6 | #FF7225 | LV-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 6 | Specialties | Care Team Station Finishes - Zone 6 | #FFD6B5 | SPE-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Punchlist | FF&E | FF&E | McGough | FF&E | #C40E4D | MG-7 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 7A | Specialties | Finishes In Courtyard - Zone 7A | #FFD6B5 | SPE-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Interiors | RI & Finishes | Zone 7B | Specialties | Finishes In Courtyard - Zone 7B | #FFD6B5 | SPE-3 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | McGough | DD GMP Pricing Completion | #C40E4D | MG-8 | 1969-12-31 18:01 | 1969-12-31 18:01
Commissioning | Testing | Testing | Fire Alarm | Fire Alarm Testing | #963634 | FA-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Commissioning | Testing | Testing | Mechanical | Test & Balance | #0F243E | MEC-6 | 1969-12-31 18:01 | 1969-12-31 18:01
Commissioning | Testing | Testing | Commissioner | Testing All Systems | #FABF8F | CX-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Commissioning | Testing | Testing | Low Voltage | Security/Access Controls Testing (Cameras, Badge Readers, Panic Buttons, etc.) | #FF7225 | LV-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Commissioning | Testing | Testing | Owner | Owner Test & Balance | #76933C | OW-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Commissioning | Commissioning | Commissioning | Commissioner | Commissioning All Systems | #FABF8F | CX-2 | 1969-12-31 18:01 | 1969-12-31 18:01
Punchlist | Punchlist | Punchlist | Architect | Project Punchlist | #4F81BD | PUN-1 | 1969-12-31 18:01 | 1969-12-31 18:01
Milestone | Design | Building | McGough | Cost Reconciliation | #C40E4D | MG-9 | 1969-12-31 18:01 | 1969-12-31 18:01

## CFA - Schedule
|  |  | 2024 | [118 empty] | 2025 | [364 empty] | 2026 | [364 empty] | 2027
|  |  | Sep | [26 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct
|  |  | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
phase | location | area | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue
Milestone | All | Building | Mar 04: MG-6; Mar 05: MG-6; Mar 06: MG-6; Mar 07: MG-6; Mar 27: M-10; Mar 28: M-10; Mar 29: M-10; Mar 30: M-10; Mar 31: M-10; Apr 01: M-10; Apr 02: M-10; Apr 03: M-10; Apr 04: M-10; Apr 05: M-10; Apr 06: M-10; Apr 07: M-10; Apr 08: M-10; Apr 09: M-10; May 05: M-11
[207 empty] | MG-3 | MG-3 | MG-3 | MG-3 | MG-3 | MG-3 | MG-3 | MG-3 | MG-3 | MG-3 | MG-3 | MG-3 | MG-3 | MG-3
| Design | Building | Sep 04: M-1; Sep 05: M-1; Sep 19: M-2; Oct 17: M-3; Nov 14: M-4; Dec 11: M-5; Dec 12: M-5; Dec 13: M-5; Dec 14: M-5; Dec 15: M-5; Dec 16: M-5; Dec 17: M-5; Dec 18: M-5; Dec 19: M-7; Dec 20: MG-8; Dec 21: MG-8; Dec 22: MG-8; Dec 23: MG-8; Dec 24: MG-8; Dec 25: MG-8; Dec 26: MG-8; Dec 27: MG-8; Dec 28: MG-8; Dec 29: MG-8; Dec 30: MG-8; Dec 31: MG-8; Jan 01: MG-8; Jan 02: MG-8; Jan 03: MG-8; Jan 04: MG-8; Jan 05: MG-8; Jan 06: MG-8; Jan 07: MG-8; Jan 08: MG-8; Jan 09: MG-8; Jan 10: MG-8; Jan 11: MG-8; Jan 12: MG-8; Jan 13: MG-8; Jan 14: MG-8; Jan 15: MG-8; Jan 16: MG-8; Jan 17: MG-8; Jan 18: MG-8; Jan 19: MG-8; Jan 20: MG-8; Jan 21: MG-8; Jan 22: MG-8; Jan 23: MG-8; Jan 24: MG-8; Jan 25: MG-8; Jan 26: MG-8; Jan 27: MG-8; Jan 28: MG-8; Jan 29: MG-8; Jan 30: OW-6; Jan 31: OW-6; Feb 01: OW-6; Feb 02: OW-6; Feb 03: OW-6; Feb 04: OW-6; Feb 05: OW-6; Feb 06: OW-6; Feb 07: OW-6; Feb 08: OW-6; Feb 09: OW-6; Feb 10: OW-6; Feb 11: OW-6; Feb 12: OW-6; Feb 13: OW-5; Feb 14: OW-5; Feb 15: OW-5; Feb 16: OW-5; Feb 17: OW-5; Feb 18: OW-5; Feb 19: OW-5; Feb 20: OW-5; Feb 21: OW-5; Feb 22: OW-5; Feb 23: OW-5; Feb 24: OW-5; Feb 25: OW-5; Feb 26: OW-5; Feb 27: OW-5; Feb 28: OW-5; Mar 01: OW-5; Mar 02: OW-5; Mar 03: OW-5; Mar 27: M-8; Mar 28: M-8; Mar 29: M-8; Mar 30: M-8; Mar 31: M-8; Apr 01: M-8; Apr 02: M-8; Apr 03: M-8; Apr 04: M-8; Apr 05: M-8; Apr 06: M-8; Apr 07: M-8; Apr 08: M-8; Apr 09: M-8; Apr 10: M-8; Apr 11: M-8; Apr 12: M-8; Apr 13: M-8; Apr 14: M-8; Apr 15: M-8; Apr 16: M-8; Apr 17: M-8; Apr 18: M-8; Apr 19: M-8; Apr 20: M-8; Apr 21: M-8; Apr 22: M-8; Apr 23: M-8; Apr 24: M-8; Apr 25: M-8; Apr 26: M-8; Apr 27: M-8; Apr 28: M-8; Apr 29: M-8; Apr 30: M-8; May 01: M-8; May 02: M-8; May 03: M-8; May 04: M-8; May 05: M-8; May 06: M-8; May 07: M-8; May 08: M-8; May 09: M-8; May 10: M-8; May 11: M-8; May 12: M-8; May 13: M-8; May 14: M-8; May 15: M-8; May 16: M-8; May 17: M-8; May 18: M-8; May 19: M-8; May 20: M-8; May 21: M-8; May 22: M-8; Jul 10: M-9; Jul 11: M-9; Jul 12: M-9; Jul 13: M-9; Jul 14: M-9; Jul 15: M-9; Jul 16: M-9; Jul 17: M-9; Jul 18: M-9; Jul 19: M-9; Jul 20: M-9; Jul 21: M-9; Jul 22: M-9; Jul 23: M-9; Jul 24: M-9; Jul 25: M-9; Jul 26: M-9; Jul 27: M-9; Jul 28: M-9; Jul 29: M-9; Jul 30: M-9; Jul 31: M-9; Aug 01: M-9; Aug 02: M-9; Aug 03: M-9; Aug 04: M-9; Aug 05: M-9; Aug 06: M-9; Aug 07: M-9; Aug 08: M-9; Aug 09: M-9; Aug 10: M-9; Aug 11: M-9; Aug 12: M-9; Aug 13: M-9; Aug 14: M-9; Aug 15: M-9; Aug 16: M-9; Aug 17: M-9; Aug 18: M-9; Aug 19: M-9; Aug 20: M-9; Aug 21: M-9; Aug 22: M-9; Aug 23: M-9; Aug 24: M-9; Aug 25: M-9; Aug 26: M-9; Aug 27: M-9; Aug 28: M-9; Aug 29: M-9; Aug 30: M-9; Aug 31: M-9; Sep 01: M-9; Sep 02: M-9; Sep 03: M-9; Sep 04: M-9
[109 empty] | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | M-6 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3 | OW-3
[151 empty] | MG-9 | MG-9 | MG-9 | MG-9 | MG-9 | MG-9 | MG-9 | MG-9 | MG-9 | MG-9 | MG-9 | MG-9 | MG-9 | MG-9 | [13 empty] | OW-4
Procurement | All | Pre-Qual | Dec 18: PRO-5; Dec 19: PRO-5; Dec 20: PRO-5; Dec 21: PRO-5; Dec 22: PRO-5; Dec 23: PRO-5; Dec 24: PRO-5; Dec 25: PRO-5; Dec 26: PRO-5; Dec 27: PRO-5; Mar 27: PRO-9; Mar 28: PRO-9; Mar 29: PRO-9; Mar 30: PRO-9; Mar 31: PRO-9; Apr 01: PRO-9; Apr 02: PRO-9
[108 empty] | PRO-6 | PRO-6 | PRO-6 | PRO-6 | PRO-6 | PRO-6 | PRO-6 | PRO-6 | PRO-6 | PRO-6 | [89 empty] | PRO-11 | PRO-11 | PRO-11 | PRO-11 | PRO-11 | PRO-11 | PRO-11
[108 empty] | PRO-7 | PRO-7 | PRO-7 | PRO-7 | PRO-7 | PRO-7 | PRO-7 | PRO-7 | PRO-7 | PRO-7
[108 empty] | PRO-8 | PRO-8 | PRO-8 | PRO-8 | PRO-8 | PRO-8 | PRO-8 | PRO-8 | PRO-8 | PRO-8
[108 empty] | PRO-10 | PRO-10 | PRO-10 | PRO-10 | PRO-10 | PRO-10 | PRO-10 | PRO-10 | PRO-10 | PRO-10
[108 empty] | PRO-12 | PRO-12 | PRO-12 | PRO-12 | PRO-12 | PRO-12 | PRO-12 | PRO-12 | PRO-12 | PRO-12
[108 empty] | MG-4 | MG-4 | MG-4 | MG-4 | MG-4 | MG-4 | MG-4 | MG-4 | MG-4 | MG-4
| Procurement | Contracts | May 23: PRO-17; May 24: PRO-17; May 25: PRO-17; May 26: PRO-17; May 27: PRO-17; May 28: PRO-17; May 29: PRO-17; May 30: PRO-17; May 31: PRO-17; Jun 01: PRO-17; Jun 02: PRO-17; Jun 03: PRO-17; Jun 04: PRO-17; Jun 05: PRO-17; Jun 06: PRO-17; Jun 07: PRO-17; Jun 08: PRO-17; Jun 09: PRO-17; Jun 10: PRO-17; Jun 11: PRO-17; Jun 12: PRO-17; Jun 13: PRO-17; Jun 14: PRO-17; Jun 15: PRO-17; Jun 16: PRO-17; Jun 17: PRO-17; Jun 18: PRO-17; Jun 19: PRO-17; Jun 20: PRO-17; Sep 05: PRO-13; Sep 06: PRO-13; Sep 07: PRO-13; Sep 08: PRO-13; Sep 09: PRO-13; Sep 10: PRO-13; Sep 11: PRO-13; Sep 12: PRO-13; Sep 13: PRO-13; Sep 14: PRO-13; Sep 15: PRO-13; Sep 16: PRO-13; Sep 17: PRO-13; Sep 18: PRO-13; Sep 19: PRO-13; Sep 20: PRO-13; Sep 21: PRO-13; Sep 22: PRO-13; Sep 23: PRO-13; Sep 24: PRO-13; Sep 25: PRO-13; Sep 26: PRO-13; Sep 27: PRO-13; Sep 28: PRO-13; Sep 29: PRO-13; Sep 30: PRO-13; Oct 01: PRO-13; Oct 02: PRO-13
[264 empty] | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | PRO-19 | [76 empty] | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14 | PRO-14
[264 empty] | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | PRO-21 | [76 empty] | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15 | PRO-15
[369 empty] | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16 | PRO-16
[369 empty] | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18 | PRO-18
[369 empty] | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20 | PRO-20
|  | Material | Dec 18: OW-2; Dec 19: OW-2; Dec 20: OW-2; Dec 21: OW-2; Dec 22: OW-2; Dec 23: OW-2; Dec 24: OW-2; Dec 25: OW-2; Dec 26: OW-2; Dec 27: OW-2; Dec 28: OW-2; Dec 29: OW-2; Dec 30: OW-2; Dec 31: OW-2; Jan 01: OW-2; Jan 02: OW-2; Jan 03: OW-2; Jan 04: OW-2; Jan 05: OW-2; Jan 06: OW-2; Jan 07: OW-2; Jan 08: OW-2; Jan 09: OW-2; Jan 10: OW-2; Jan 11: OW-2; Jan 12: OW-2; Jan 13: OW-2; Jan 14: OW-2; Jan 15: OW-2; Jan 16: OW-2; Jan 17: OW-2; Jan 18: OW-2; Jan 19: OW-2; Jan 20: OW-2; Jan 21: OW-2; Jan 22: OW-2; Jan 23: OW-2; Jan 24: OW-2; Jan 25: OW-2; Jan 26: OW-2; Jan 27: OW-2; Jan 28: OW-2; Jan 29: OW-2; Jan 30: OW-2; Jan 31: OW-2; Feb 01: OW-2; Feb 02: OW-2; Feb 03: OW-2; Feb 04: OW-2; Feb 05: OW-2; Feb 06: OW-2; Feb 07: OW-2; Feb 08: OW-2; Feb 09: OW-2; Feb 10: OW-2; Feb 11: OW-2; Feb 12: OW-2; Feb 13: OW-2; Feb 14: OW-2; Feb 15: OW-2; Feb 16: OW-2; Feb 17: OW-2; Feb 18: OW-2; Feb 19: OW-2; Feb 20: OW-2; Feb 21: OW-2; Feb 22: OW-2; Feb 23: OW-2; Feb 24: OW-2; Feb 25: OW-2; Feb 26: OW-2; Feb 27: OW-2; Feb 28: OW-2; Mar 01: OW-2; Mar 02: OW-2; Mar 03: OW-2; Mar 04: OW-2; Mar 05: OW-2; Mar 06: OW-2; Mar 07: OW-2; Mar 08: OW-2; Mar 09: OW-2; Mar 10: OW-2; Mar 11: OW-2; Mar 12: OW-2; Mar 13: OW-2; Mar 14: OW-2; Mar 15: OW-2; Mar 16: OW-2; Mar 17: OW-2; Mar 18: OW-2; Mar 19: OW-2; Mar 20: OW-2; Mar 21: OW-2; Mar 22: OW-2; Mar 23: OW-2; Mar 24: OW-2; Mar 25: OW-2; Mar 26: OW-2; Mar 27: OW-2; Mar 28: OW-2; Mar 29: OW-2; Mar 30: OW-2; Mar 31: OW-2; Apr 01: OW-2; Apr 02: OW-2; Apr 03: OW-2; Apr 04: OW-2; Apr 05: OW-2; Apr 06: OW-2; Apr 07: OW-2; Apr 08: OW-2; Apr 09: OW-2; Apr 10: OW-2; Apr 11: OW-2; Apr 12: OW-2; Apr 13: OW-2; Apr 14: OW-2; Apr 15: OW-2; Apr 16: OW-2; Apr 17: OW-2; Apr 18: OW-2; Apr 19: OW-2; Apr 20: OW-2; Apr 21: OW-2; Apr 22: OW-2; Apr 23: OW-2; Apr 24: OW-2; Apr 25: OW-2; Apr 26: OW-2; Apr 27: OW-2; Apr 28: OW-2; Apr 29: OW-2; Apr 30: OW-2; May 01: OW-2; May 02: OW-2; May 03: OW-2; May 04: OW-2; May 05: OW-2; May 06: OW-2; May 07: OW-2; May 08: OW-2; May 09: OW-2; May 10: OW-2; May 11: OW-2; May 12: OW-2; May 13: OW-2; May 14: OW-2; May 15: OW-2; May 16: OW-2; May 17: OW-2; May 18: OW-2; May 19: OW-2; May 20: OW-2; May 21: OW-2; May 22: OW-2; May 23: OW-2; May 24: OW-2; May 25: OW-2; May 26: OW-2; May 27: OW-2; May 28: OW-2; May 29: OW-2; May 30: OW-2; May 31: OW-2; Jun 01: OW-2; Jun 02: OW-2; Jun 03: OW-2; Jun 04: OW-2; Jun 05: OW-2; Jun 06: OW-2; Jun 07: OW-2; Jun 08: OW-2; Jun 09: OW-2; Jun 10: OW-2; Jun 11: OW-2; Jun 12: OW-2; Jun 13: OW-2; Jun 14: OW-2; Jun 15: OW-2; Jun 16: OW-2; Jun 17: OW-2; Jun 18: OW-2; Jun 19: OW-2; Jun 20: OW-2; Jun 21: OW-2; Jun 22: OW-2; Jun 23: OW-2; Jun 24: OW-2; Jun 25: OW-2; Jun 26: OW-2; Jun 27: OW-2; Jun 28: OW-2; Jun 29: OW-2; Jun 30: OW-2; Jul 01: OW-2; Jul 02: OW-2; Jul 03: OW-2; Jul 04: OW-2; Jul 05: OW-2; Jul 06: OW-2; Jul 07: OW-2; Jul 08: OW-2; Jul 09: OW-2; Jul 10: OW-2; Jul 11: OW-2; Jul 12: OW-2; Jul 13: OW-2; Jul 14: OW-2; Jul 15: OW-2; Jul 16: OW-2; Jul 17: OW-2; Jul 18: OW-2; Jul 19: OW-2; Jul 20: OW-2; Jul 21: OW-2; Jul 22: OW-2; Jul 23: OW-2; Jul 24: OW-2; Jul 25: OW-2; Jul 26: OW-2; Jul 27: OW-2; Jul 28: OW-2; Jul 29: OW-2; Jul 30: OW-2; Jul 31: OW-2; Aug 01: OW-2; Aug 02: OW-2; Aug 03: OW-2; Aug 04: OW-2; Aug 05: OW-2; Aug 06: OW-2; Aug 07: OW-2; Aug 08: OW-2; Oct 24: SL-1; Oct 25: SL-1; Oct 26: SL-1; Oct 27: SL-1; Oct 28: SL-1; Oct 29: SL-1; Oct 30: SL-1; Oct 31: SL-1; Nov 01: SL-1; Nov 02: SL-1; Nov 03: SL-1; Nov 04: SL-1; Nov 05: SL-1; Nov 06: SL-1; Nov 07: SL-1; Nov 08: SL-1; Nov 09: SL-1; Nov 10: SL-1; Nov 11: SL-1; Nov 12: SL-1; Nov 13: SL-1; Nov 14: SL-1; Nov 15: SL-1; Nov 16: SL-1; Nov 17: SL-1; Nov 18: SL-1; Nov 19: SL-1; Nov 20: SL-1; Nov 21: SL-1; Nov 22: SL-1; Nov 23: SL-1; Nov 24: SL-1; Nov 25: SL-1; Nov 26: SL-1; Nov 27: SL-1; Nov 28: SL-1; Nov 29: SL-1; Nov 30: SL-1; Dec 01: SL-1; Dec 02: SL-1; Dec 03: SL-1; Dec 04: SL-1; Dec 05: SL-1; Dec 06: SL-1; Dec 07: SL-1; Dec 08: SL-1; Dec 09: SL-1; Dec 10: SL-1; Dec 11: SL-1; Dec 12: SL-1; Dec 13: SL-1; Dec 14: SL-1; Dec 15: SL-1; Dec 16: SL-1; Dec 17: SL-1; Dec 18: SL-1; Dec 19: SL-1; Dec 20: SL-1; Dec 21: SL-1; Dec 22: SL-1; Dec 23: SL-1; Dec 24: SL-1; Dec 25: SL-1; Dec 26: SL-1; Dec 27: SL-1; Dec 28: SL-1; Dec 29: SL-1; Dec 30: SL-1; Dec 31: SL-1; Jan 01: SL-1; Jan 02: SL-1; Jan 03: SL-1; Jan 04: SL-1; Jan 05: SL-1; Jan 06: SL-1; Jan 07: SL-1; Jan 08: SL-1; Jan 09: SL-1; Jan 10: SL-1; Jan 11: SL-1; Jan 12: SL-1; Jan 13: SL-1; Jan 28: DOOR-3; Jan 29: DOOR-3; Jan 30: DOOR-3; Jan 31: DOOR-3; Feb 01: DOOR-3; Feb 02: DOOR-3; Feb 03: DOOR-3; Feb 04: DOOR-3; Feb 05: DOOR-3; Feb 06: DOOR-3; Feb 07: DOOR-3; Feb 08: DOOR-3; Feb 09: DOOR-3; Feb 10: DOOR-3; Feb 11: DOOR-3; Feb 12: DOOR-3; Feb 13: DOOR-3; Feb 14: DOOR-3; Feb 15: DOOR-3; Feb 16: DOOR-3; Feb 17: DOOR-3; Feb 18: DOOR-3; Feb 19: DOOR-3; Feb 20: DOOR-3; Feb 21: DOOR-3; Feb 22: DOOR-3; Feb 23: DOOR-3; Feb 24: DOOR-3; Feb 25: DOOR-3; Feb 26: DOOR-3; Feb 27: DOOR-3; Feb 28: DOOR-3; Mar 01: DOOR-3; Mar 02: DOOR-3; Mar 03: DOOR-3; Mar 04: DOOR-3; Mar 05: DOOR-3; Mar 06: DOOR-3; Mar 07: DOOR-3; Mar 08: DOOR-3; Mar 09: DOOR-3; Mar 10: DOOR-3; Mar 11: DOOR-3; Mar 12: DOOR-3; Mar 13: DOOR-3; Mar 14: DOOR-3; Mar 15: DOOR-3; Mar 16: DOOR-3; Mar 17: DOOR-3; Mar 18: DOOR-3; Mar 19: DOOR-3; Mar 20: DOOR-3; Mar 21: DOOR-3; Mar 22: DOOR-3; Mar 23: DOOR-3; Mar 24: DOOR-3; Mar 25: DOOR-3; Mar 26: DOOR-3; Mar 27: DOOR-3; Mar 28: DOOR-3; Mar 29: DOOR-3; Mar 30: DOOR-3; Mar 31: DOOR-3; Apr 01: DOOR-3; Apr 02: DOOR-3; Apr 03: DOOR-3; Apr 04: DOOR-3; Apr 05: DOOR-3; Apr 06: DOOR-3; Apr 07: DOOR-3; Apr 08: DOOR-3; Apr 09: DOOR-3; Apr 10: DOOR-3; Apr 11: DOOR-3; Apr 12: DOOR-3; Apr 13: DOOR-3; Apr 14: DOOR-3; Apr 15: DOOR-3; Apr 16: DOOR-3; Apr 17: DOOR-3; Apr 18: DOOR-3; Apr 19: DOOR-3; Apr 20: DOOR-3; Apr 21: DOOR-3; Apr 22: DOOR-3; Apr 23: DOOR-3; Apr 24: DOOR-3; Apr 25: DOOR-3; Apr 26: DOOR-3; Apr 27: DOOR-3; Apr 28: DOOR-3; Apr 29: DOOR-3; Apr 30: DOOR-3; May 01: DOOR-3; May 02: DOOR-3; May 03: DOOR-3; May 04: DOOR-3; May 05: DOOR-3; May 06: DOOR-3; May 07: DOOR-3; May 08: DOOR-3; May 09: DOOR-3; May 10: DOOR-3; May 11: DOOR-3; May 12: DOOR-3; May 13: DOOR-3; May 14: DOOR-3; May 15: DOOR-3; May 16: DOOR-3; May 17: DOOR-3; May 18: DOOR-3; May 19: DOOR-3; May 20: DOOR-3; May 21: DOOR-3; May 22: DOOR-3; May 23: DOOR-3; May 24: DOOR-3; May 25: DOOR-3; May 26: DOOR-3; May 27: DOOR-3; May 28: DOOR-3; May 29: DOOR-3; May 30: DOOR-3; May 31: DOOR-3; Jun 01: DOOR-3; Jun 02: DOOR-3; Jun 03: DOOR-3; Jun 04: DOOR-3; Jun 05: DOOR-3; Jun 06: DOOR-3; Jun 07: DOOR-3; Jun 08: DOOR-3; Jun 09: DOOR-3; Jun 10: DOOR-3; Jun 11: DOOR-3; Jun 12: DOOR-3; Jun 13: DOOR-3; Jun 14: DOOR-3; Jun 15: DOOR-3; Jun 16: DOOR-3; Jun 17: DOOR-3; Jun 18: DOOR-3
[317 empty] | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23 | PRO-23
[317 empty] | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24 | PRO-24
[317 empty] | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1 | EL-1
Submittals | All | Product Data | Mar 10: SUB-28; Mar 11: SUB-28; Mar 12: SUB-28; Mar 13: SUB-28; Mar 14: SUB-28; Mar 15: SUB-28; Mar 16: SUB-28; Mar 17: SUB-28; Mar 18: SUB-28; Mar 19: SUB-28; Mar 20: SUB-28; Mar 21: SUB-28; Mar 24: SUB-14; Mar 25: SUB-14; Mar 26: SUB-14; Mar 27: SUB-14; Mar 28: SUB-14
[190 empty] | SUB-30 | SUB-30 | SUB-30 | SUB-30 | SUB-30 | SUB-30 | SUB-30 | SUB-30 | SUB-30 | SUB-30 | SUB-30 | SUB-30 |  |  | SUB-15 | SUB-15 | SUB-15 | SUB-15 | SUB-15
[190 empty] | SUB-32 | SUB-32 | SUB-32 | SUB-32 | SUB-32 | SUB-32 | SUB-32 | SUB-32 | SUB-32 | SUB-32 | SUB-32 | SUB-32 |  |  | SUB-16 | SUB-16 | SUB-16 | SUB-16 | SUB-16
[190 empty] | SUB-34 | SUB-34 | SUB-34 | SUB-34 | SUB-34 | SUB-34 | SUB-34 | SUB-34 | SUB-34 | SUB-34 | SUB-34 | SUB-34 |  |  | SUB-17 | SUB-17 | SUB-17 | SUB-17 | SUB-17
[190 empty] | SUB-36 | SUB-36 | SUB-36 | SUB-36 | SUB-36 | SUB-36 | SUB-36 | SUB-36 | SUB-36 | SUB-36 | SUB-36 | SUB-36 |  |  | SUB-18 | SUB-18 | SUB-18 | SUB-18 | SUB-18
[190 empty] | SUB-38 | SUB-38 | SUB-38 | SUB-38 | SUB-38 | SUB-38 | SUB-38 | SUB-38 | SUB-38 | SUB-38 | SUB-38 | SUB-38 |  |  | SUB-19 | SUB-19 | SUB-19 | SUB-19 | SUB-19
[190 empty] | SUB-40 | SUB-40 | SUB-40 | SUB-40 | SUB-40 | SUB-40 | SUB-40 | SUB-40 | SUB-40 | SUB-40 | SUB-40 | SUB-40 |  |  | SUB-20 | SUB-20 | SUB-20 | SUB-20 | SUB-20
[190 empty] | SUB-42 | SUB-42 | SUB-42 | SUB-42 | SUB-42 | SUB-42 | SUB-42 | SUB-42 | SUB-42 | SUB-42 | SUB-42 | SUB-42 |  |  | SUB-21 | SUB-21 | SUB-21 | SUB-21 | SUB-21
[190 empty] | SUB-44 | SUB-44 | SUB-44 | SUB-44 | SUB-44 | SUB-44 | SUB-44 | SUB-44 | SUB-44 | SUB-44 | SUB-44 | SUB-44 |  |  | SUB-22 | SUB-22 | SUB-22 | SUB-22 | SUB-22
[190 empty] | SUB-46 | SUB-46 | SUB-46 | SUB-46 | SUB-46 | SUB-46 | SUB-46 | SUB-46 | SUB-46 | SUB-46 | SUB-46 | SUB-46 |  |  | SUB-23 | SUB-23 | SUB-23 | SUB-23 | SUB-23
[190 empty] | SUB-48 | SUB-48 | SUB-48 | SUB-48 | SUB-48 | SUB-48 | SUB-48 | SUB-48 | SUB-48 | SUB-48 | SUB-48 | SUB-48 |  |  | SUB-24 | SUB-24 | SUB-24 | SUB-24 | SUB-24
[190 empty] | SUB-50 | SUB-50 | SUB-50 | SUB-50 | SUB-50 | SUB-50 | SUB-50 | SUB-50 | SUB-50 | SUB-50 | SUB-50 | SUB-50 |  |  | SUB-25 | SUB-25 | SUB-25 | SUB-25 | SUB-25
[190 empty] | SUB-52 | SUB-52 | SUB-52 | SUB-52 | SUB-52 | SUB-52 | SUB-52 | SUB-52 | SUB-52 | SUB-52 | SUB-52 | SUB-52 |  |  | SUB-26 | SUB-26 | SUB-26 | SUB-26 | SUB-26
|  | Shop Drawings | Jun 23: SUB-37; Jun 24: SUB-37; Jun 25: SUB-37; Jun 26: SUB-37; Jun 27: SUB-37; Jun 28: SUB-37; Jun 29: SUB-37; Jun 30: SUB-37; Jul 01: SUB-37; Jul 02: SUB-37; Jul 03: SUB-37; Jul 04: SUB-37; Jul 05: SUB-37; Jul 06: SUB-37; Jul 07: SUB-37; Jul 08: SUB-1; Jul 09: SUB-1; Jul 10: SUB-1; Jul 11: SUB-1; Jul 12: SUB-1; Jul 13: SUB-1; Jul 14: SUB-1; Oct 03: SUB-27; Oct 04: SUB-27; Oct 05: SUB-27; Oct 06: SUB-27; Oct 07: SUB-27; Oct 08: SUB-27; Oct 09: SUB-27; Oct 10: SUB-27; Oct 11: SUB-27; Oct 12: SUB-27; Oct 13: SUB-27; Oct 14: SUB-27; Oct 15: SUB-27; Oct 16: SUB-27; Oct 17: SUB-7; Oct 18: SUB-7; Oct 19: SUB-7; Oct 20: SUB-7; Oct 21: SUB-7; Oct 22: SUB-7; Oct 23: SUB-7
[295 empty] | SUB-39 | SUB-39 | SUB-39 | SUB-39 | SUB-39 | SUB-39 | SUB-39 | SUB-39 | SUB-39 | SUB-39 | SUB-39 | SUB-39 | SUB-39 | SUB-39 | SUB-39 | SUB-2 | SUB-2 | SUB-2 | SUB-2 | SUB-2 | SUB-2 | SUB-2 | [80 empty] | SUB-29 | SUB-29 | SUB-29 | SUB-29 | SUB-29 | SUB-29 | SUB-29 | SUB-29 | SUB-29 | SUB-29 | SUB-29 | SUB-29 | SUB-29 | SUB-29 | SUB-8 | SUB-8 | SUB-8 | SUB-8 | SUB-8 | SUB-8 | SUB-8
[295 empty] | SUB-43 | SUB-43 | SUB-43 | SUB-43 | SUB-43 | SUB-43 | SUB-43 | SUB-43 | SUB-43 | SUB-43 | SUB-43 | SUB-43 | SUB-43 | SUB-43 | SUB-43 | SUB-3 | SUB-3 | SUB-3 | SUB-3 | SUB-3 | SUB-3 | SUB-3 | [80 empty] | SUB-31 | SUB-31 | SUB-31 | SUB-31 | SUB-31 | SUB-31 | SUB-31 | SUB-31 | SUB-31 | SUB-31 | SUB-31 | SUB-31 | SUB-31 | SUB-31 | SUB-9 | SUB-9 | SUB-9 | SUB-9 | SUB-9 | SUB-9 | SUB-9
[295 empty] | SUB-45 | SUB-45 | SUB-45 | SUB-45 | SUB-45 | SUB-45 | SUB-45 | SUB-45 | SUB-45 | SUB-45 | SUB-45 | SUB-45 | SUB-45 | SUB-45 | SUB-45 | SUB-4 | SUB-4 | SUB-4 | SUB-4 | SUB-4 | SUB-4 | SUB-4 | [80 empty] | SUB-33 | SUB-33 | SUB-33 | SUB-33 | SUB-33 | SUB-33 | SUB-33 | SUB-33 | SUB-33 | SUB-33 | SUB-33 | SUB-33 | SUB-33 | SUB-33 | SUB-10 | SUB-10 | SUB-10 | SUB-10 | SUB-10 | SUB-10 | SUB-10
[295 empty] | SUB-47 | SUB-47 | SUB-47 | SUB-47 | SUB-47 | SUB-47 | SUB-47 | SUB-47 | SUB-47 | SUB-47 | SUB-47 | SUB-47 | SUB-47 | SUB-47 | SUB-47 | SUB-5 | SUB-5 | SUB-5 | SUB-5 | SUB-5 | SUB-5 | SUB-5 | [80 empty] | SUB-35 | SUB-35 | SUB-35 | SUB-35 | SUB-35 | SUB-35 | SUB-35 | SUB-35 | SUB-35 | SUB-35 | SUB-35 | SUB-35 | SUB-35 | SUB-35 | SUB-11 | SUB-11 | SUB-11 | SUB-11 | SUB-11 | SUB-11 | SUB-11
[295 empty] | SUB-51 | SUB-51 | SUB-51 | SUB-51 | SUB-51 | SUB-51 | SUB-51 | SUB-51 | SUB-51 | SUB-51 | SUB-51 | SUB-51 | SUB-51 | SUB-51 | SUB-51 | SUB-6 | SUB-6 | SUB-6 | SUB-6 | SUB-6 | SUB-6 | SUB-6 | [80 empty] | SUB-41 | SUB-41 | SUB-41 | SUB-41 | SUB-41 | SUB-41 | SUB-41 | SUB-41 | SUB-41 | SUB-41 | SUB-41 | SUB-41 | SUB-41 | SUB-41 | SUB-12 | SUB-12 | SUB-12 | SUB-12 | SUB-12 | SUB-12 | SUB-12
[397 empty] | SUB-49 | SUB-49 | SUB-49 | SUB-49 | SUB-49 | SUB-49 | SUB-49 | SUB-49 | SUB-49 | SUB-49 | SUB-49 | SUB-49 | SUB-49 | SUB-49 | SUB-13 | SUB-13 | SUB-13 | SUB-13 | SUB-13 | SUB-13 | SUB-13
Permits | Permits | Permits | Jan 15: PER-1; Jan 16: PER-1; Jan 17: PER-1; Jan 18: PER-1; Jan 19: PER-1; Jan 20: PER-1; Jan 21: PER-1; Jan 22: PER-1; Jan 23: PER-1; Jan 24: PER-1; Jan 25: PER-1; Jan 26: PER-1; Jan 27: PER-1; Jan 28: PER-1; Jan 29: PER-1; Jan 30: PER-1; Jan 31: PER-1; Feb 01: PER-1; Feb 02: PER-1; Feb 03: PER-1; Feb 04: PER-1; Feb 05: PER-1; Feb 06: PER-1; Feb 07: PER-1; Feb 08: PER-1; Feb 09: PER-1; Feb 10: PER-1; Feb 11: PER-1; Feb 12: PER-1; Feb 13: PER-1; Feb 14: PER-1; Feb 15: PER-1; Feb 16: PER-1; Feb 17: PER-1; Feb 18: PER-1; Feb 19: PER-1; Feb 20: PER-1; Feb 21: PER-1; Feb 22: PER-1; Feb 23: PER-1; Feb 24: PER-1; Feb 25: PER-1; Feb 26: PER-1; Feb 27: PER-1; Feb 28: PER-1; Mar 01: PER-1; Mar 02: PER-1; Mar 03: PER-1; Mar 04: PER-1; Mar 05: PER-1; Mar 06: PER-1; Mar 07: PER-1; Mar 08: PER-1; Mar 09: PER-1; Mar 10: PER-1; Mar 11: PER-1; Mar 12: PER-1; Mar 13: PER-1; Mar 14: PER-1; Mar 15: PER-1; Mar 16: PER-1; Mar 17: PER-1; Mar 18: PER-1; Mar 19: PER-1; Mar 20: PER-1; Mar 21: PER-1; Mar 22: PER-1; Mar 23: PER-1; Mar 24: PER-1; Mar 25: PER-1; Mar 26: PER-1; Mar 27: PER-1; Mar 28: PER-1; Mar 29: PER-1; Mar 30: PER-1; Mar 31: PER-1; Apr 01: PER-1; Apr 02: PER-1; Apr 03: PER-1; Apr 04: PER-1; Apr 05: PER-1; Apr 06: PER-1; Apr 07: PER-1; Apr 08: PER-1; Apr 09: PER-1; Apr 10: PER-1; Apr 11: PER-1; Apr 12: PER-1; Apr 13: PER-1; Apr 14: PER-1; Apr 15: PER-1; Apr 16: PER-1; Apr 17: PER-1; Apr 18: PER-1; Apr 19: PER-1; Apr 20: PER-1; Apr 21: PER-1; Apr 22: PER-1; Apr 23: PER-1; Apr 24: PER-1; Apr 25: PER-1; Apr 26: PER-1; Apr 27: PER-1; Apr 28: PER-1; Apr 29: PER-1; Apr 30: PER-1; May 01: PER-1; May 02: PER-1; May 03: PER-1; May 04: PER-1; May 05: PER-1; May 06: PER-1; May 07: PER-1; May 08: PER-1; May 09: PER-1; May 10: PER-1; May 11: PER-1; May 12: PER-1; May 13: PER-1; May 14: PER-1; May 15: PER-1; May 16: PER-1; May 17: PER-1; May 18: PER-1; May 19: PER-1; May 20: PER-1; May 21: PER-1
Utilities | All | All | Apr 10: UT-1; Apr 11: UT-1; Apr 12: UT-1; Apr 13: UT-1; Apr 14: UT-1; Apr 15: UT-1; Apr 16: UT-1; Apr 17: UT-1; Apr 18: UT-1; Apr 19: UT-1; Apr 20: UT-1; Apr 21: UT-1; Apr 22: UT-1; Apr 23: UT-1; Apr 24: UT-1; Apr 25: UT-1; Apr 26: UT-1; Apr 27: UT-1; Apr 28: UT-1; Apr 29: UT-1; Apr 30: UT-1; May 01: UT-1; May 02: UT-1; May 03: UT-1; May 04: UT-1; May 05: UT-1; May 06: UT-1; May 07: UT-1; May 08: UT-1; May 09: UT-4; May 10: UT-4; May 11: UT-4; May 12: UT-4; May 13: UT-4; May 14: UT-4; May 15: UT-4; May 16: UT-4; May 17: UT-4; May 18: UT-4; May 19: UT-4; May 20: UT-4; May 21: UT-4; May 22: UT-4
[221 empty] | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1 | UT-1
[221 empty] | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2 | UT-2
[221 empty] | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3 | UT-3
Sitework | East | Playa Lake | Oct 24: SITE-10; Oct 25: SITE-10; Oct 26: SITE-10; Oct 27: SITE-10; Oct 28: SITE-10; Oct 29: SITE-10; Oct 30: SITE-10; Oct 31: SITE-10; Nov 01: SITE-10; Nov 02: SITE-10; Nov 03: SITE-10; Nov 04: SITE-10; Nov 05: SITE-10; Nov 06: SITE-10; Nov 07: SITE-10; Nov 08: SITE-10; Nov 09: SITE-10; Nov 10: SITE-10; Nov 11: SITE-10; Nov 12: SITE-10; Nov 13: SITE-10
|  | Playa Lake East | Jul 29: SITE-5; Jul 30: SITE-5; Jul 31: SITE-5; Aug 01: SITE-5; Aug 02: SITE-5; Aug 03: SITE-5; Aug 04: SITE-5; Aug 05: SITE-5; Aug 06: SITE-5; Aug 07: SITE-5; Aug 08: SITE-5; Aug 09: SITE-5; Aug 10: SITE-5; Aug 11: SITE-5; Aug 12: SITE-12; Aug 13: SITE-12; Aug 14: SITE-12; Aug 15: SITE-12; Aug 16: SITE-12; Aug 17: SITE-12; Aug 18: SITE-12; Sep 03: SITE-11; Sep 04: SITE-11; Sep 08: SITE-7; Sep 09: SITE-7; Sep 10: SITE-7; Sep 11: SITE-7; Sep 12: SITE-7; Sep 15: SITE-7; Sep 16: SITE-7; Sep 17: SITE-7; Sep 18: SITE-7; Sep 19: SITE-7; Sep 20: SITE-7; Sep 21: SITE-7; Sep 22: SITE-7; Sep 23: SITE-7; Sep 24: SITE-7; Sep 25: SITE-7; Sep 26: SITE-7; Sep 29: SITE-7; Sep 30: SITE-7; Oct 01: SITE-7; Oct 02: SITE-7; Oct 03: SITE-7; Oct 04: SITE-7; Oct 05: SITE-7; Oct 06: SITE-7; Oct 07: SITE-7; Oct 08: SITE-7; Oct 09: SITE-7; Oct 10: SITE-7; Oct 11: SITE-7; Oct 12: SITE-7; Oct 13: SITE-7; Oct 14: SITE-7; Oct 15: SITE-7; Oct 16: SITE-7
[345 empty] | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-8 | SITE-7 | SITE-7 | SITE-7 | [27 empty] | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9 | SITE-9
| Excavation | All | Jul 29: SITE-3; Jul 30: SITE-3; Jul 31: SITE-3; Aug 01: SITE-3; Aug 02: SITE-3; Aug 03: SITE-3; Aug 04: SITE-3; Aug 05: SITE-3; Aug 06: SITE-3; Aug 07: SITE-3; Aug 08: SITE-3; Aug 09: SITE-3; Aug 10: SITE-3; Aug 11: SITE-3; Aug 12: SITE-1; Aug 13: SITE-1; Aug 14: SITE-1; Aug 15: SITE-1; Aug 16: SITE-1; Aug 17: SITE-1; Aug 18: SITE-1; Aug 19: SITE-1; Aug 20: SITE-1; Aug 21: SITE-1; Aug 22: SITE-1; Aug 23: SITE-1; Aug 24: SITE-1; Aug 25: SITE-1; Aug 26: SITE-1; Aug 27: SITE-1; Aug 28: SITE-1; Aug 29: SITE-1; Aug 30: SITE-1; Aug 31: SITE-1; Sep 01: SITE-1; Sep 02: SITE-1
| Outsite | Clear & Grub | Jun 23: SITE-2; Jun 24: SITE-2; Jun 25: SITE-2; Jun 26: SITE-2; Jun 27: SITE-2; Jun 28: SITE-2; Jun 29: SITE-2; Jun 30: SITE-2; Jul 01: SITE-2; Jul 02: SITE-2; Jul 03: SITE-2; Jul 04: SITE-2; Jul 05: SITE-2; Jul 06: SITE-2; Jul 07: SITE-2; Jul 08: SITE-2; Jul 09: SITE-2; Jul 10: SITE-2; Jul 11: SITE-2; Jul 12: SITE-2; Jul 13: SITE-2; Jul 14: SITE-2; Jul 15: SITE-2; Jul 16: SITE-2; Jul 17: SITE-2; Jul 18: SITE-2; Jul 19: SITE-2; Jul 20: SITE-2; Jul 21: SITE-2; Jul 22: SITE-2; Jul 23: SITE-2; Jul 24: SITE-2; Jul 25: SITE-2; Jul 26: SITE-2; Jul 27: SITE-2; Jul 28: SITE-2
| Site | All | Jul 29: CON-1; Jul 30: CON-1; Jul 31: CON-1; Aug 01: CON-1; Aug 02: CON-1; Aug 03: CON-1; Aug 04: CON-1; Aug 05: CON-1; Aug 06: CON-1; Aug 07: CON-1; Aug 08: CON-1; Aug 09: CON-1; Aug 10: CON-1; Aug 11: CON-1; Aug 12: CON-1; Aug 13: CON-1; Aug 14: CON-1; Aug 15: CON-1; Aug 16: CON-1; Aug 17: CON-1; Aug 18: CON-1; Aug 19: CON-1; Aug 20: CON-1; Aug 21: CON-1; Aug 22: CON-1; Aug 23: CON-1; Aug 24: CON-1; Aug 25: CON-1; Aug 26: CON-1; Aug 27: CON-1; Aug 28: CON-1; Aug 29: CON-1; Aug 30: CON-1; Aug 31: CON-1; Sep 01: CON-1; Sep 02: CON-1; Sep 03: CON-1; Sep 04: CON-1; Sep 05: CON-1; Sep 06: CON-1; Sep 07: CON-1; Sep 08: CON-1; Sep 09: CON-1; Sep 10: CON-1; Sep 11: CON-1; Sep 12: CON-1; Sep 13: CON-1; Sep 14: CON-1; Sep 15: CON-1; Sep 16: CON-1; Sep 17: CON-1; Sep 18: CON-1; Sep 19: CON-1; Sep 20: CON-1; Sep 21: CON-1; Sep 22: CON-1; Sep 23: CON-1; Sep 24: CON-1; Sep 25: CON-1; Sep 26: CON-1; Sep 27: CON-1; Sep 28: CON-1; Sep 29: CON-1; Sep 30: CON-1; Oct 01: CON-1; Oct 02: CON-1; Oct 03: CON-1; Oct 04: CON-1; Oct 05: CON-1; Oct 06: CON-1; Oct 07: CON-1; Oct 08: CON-1; Oct 09: CON-1; Oct 10: CON-1; Oct 11: CON-1; Oct 12: CON-1; Oct 13: CON-1; Oct 14: CON-1; Oct 15: CON-1; Oct 16: CON-1; Oct 17: CON-1; Oct 18: CON-1; Oct 19: CON-1; Oct 20: CON-1; Oct 21: CON-1; Oct 22: CON-1; Oct 23: CON-1; Oct 24: CON-1; Oct 25: CON-1; Oct 26: CON-1; Oct 27: CON-1; Oct 28: CON-1; Oct 29: CON-1; Oct 30: CON-1; Oct 31: CON-1; Nov 01: CON-1; Nov 02: CON-1; Nov 03: CON-1; Nov 04: CON-1; Nov 05: CON-1; Nov 06: CON-1; Nov 07: CON-1; Nov 08: CON-1; Nov 09: CON-1; Nov 10: CON-1; Nov 11: CON-1; Nov 12: CON-1; Nov 13: CON-1; Nov 14: CON-1; Nov 15: CON-1; Nov 16: CON-1; Nov 17: CON-1; Nov 18: CON-1; Nov 19: CON-1; Nov 20: CON-1; Nov 21: CON-1; Nov 22: CON-1; Nov 23: CON-1; Nov 24: CON-1; Nov 25: CON-1; Nov 26: CON-1; Nov 27: CON-1; Nov 28: CON-1; Nov 29: CON-1; Nov 30: CON-1; Dec 01: CON-1; Dec 02: CON-1; Dec 03: CON-1; Dec 04: CON-1; Dec 05: CON-1; Dec 06: CON-1; Dec 07: CON-1; Dec 08: CON-1; Dec 09: CON-1; Dec 10: CON-1; Dec 11: CON-1; Dec 12: CON-1; Dec 13: CON-1; Dec 14: CON-1; Dec 15: CON-1; Dec 16: CON-1; Dec 17: CON-1; Dec 18: CON-1; Dec 19: CON-1; Dec 20: CON-1; Dec 21: CON-1; Dec 22: CON-1; Dec 23: CON-1; Dec 24: CON-1; Dec 25: CON-1; Dec 26: CON-1; Dec 27: CON-1; Dec 28: CON-1; Dec 29: CON-1; Dec 30: CON-1; Dec 31: CON-1; Jan 01: CON-1; Jan 02: CON-1; Jan 03: CON-1; Jan 04: CON-1; Jan 05: CON-1; Jan 06: CON-1; Jan 07: CON-1; Jan 08: CON-1; Jan 09: CON-1; Jan 10: CON-1; Jan 11: CON-1; Jan 12: CON-1; Jan 13: CON-1; Jan 14: CON-1; Jan 15: CON-1; Jan 16: CON-1; Jan 17: CON-1; Jan 18: CON-1; Jan 19: CON-1; Jan 20: CON-1; Jan 21: CON-1; Jan 22: CON-1; Jan 23: CON-1; Jan 24: CON-1; Jan 25: CON-1; Jan 26: CON-1; Jan 27: CON-1; Jan 28: CON-1; Jan 29: CON-1; Jan 30: CON-1; Jan 31: CON-1; Feb 01: CON-1; Feb 02: CON-1; Feb 03: CON-1; Feb 04: CON-1; Feb 05: CON-1; Feb 06: CON-1; Feb 07: CON-1; Feb 08: CON-1; Feb 09: CON-1; Feb 10: CON-1; Feb 11: CON-1; Feb 12: CON-1; Feb 13: CON-1; Feb 14: CON-1; Feb 15: CON-1; Feb 16: CON-1; Feb 17: CON-1; Feb 18: CON-1; Feb 19: CON-1; Feb 20: CON-1; Feb 21: CON-1; Feb 22: CON-1; Feb 23: CON-1; Feb 24: CON-1; Feb 25: CON-1; Feb 26: CON-1; Feb 27: CON-1; Feb 28: CON-1; Mar 01: CON-1; Mar 02: CON-1; Mar 03: CON-1; Mar 04: CON-1; Mar 05: CON-1; Mar 06: CON-1
| West | Playa Lake | Aug 19: SITE-4; Aug 20: SITE-4; Aug 21: SITE-4; Aug 22: SITE-4; Aug 23: SITE-4; Aug 24: SITE-4; Aug 25: SITE-4; Aug 26: SITE-4; Aug 27: SITE-4; Aug 28: SITE-4; Aug 29: SITE-4; Aug 30: SITE-4; Aug 31: SITE-4; Sep 01: SITE-4; Sep 02: SITE-4; Sep 03: SITE-6; Sep 04: SITE-6; Sep 05: SITE-6; Sep 06: SITE-6; Sep 07: SITE-6; Sep 08: SITE-6; Sep 09: SITE-6
Foundations | Deep Structural | Deep Structural | Sep 03: PI-1; Sep 04: PI-1; Sep 05: PI-1; Sep 06: PI-1; Sep 07: PI-1; Sep 08: PI-1; Sep 09: PI-1; Sep 10: PI-1; Sep 11: PI-1; Sep 12: PI-1; Sep 13: PI-1; Sep 14: PI-1; Sep 15: PI-1; Sep 16: PI-1; Sep 17: PI-1; Sep 18: PI-1; Sep 19: PI-1; Sep 20: PI-1; Sep 21: PI-1; Sep 22: PI-1; Sep 23: PI-1; Sep 24: PI-1; Sep 25: PI-1; Sep 26: PI-1; Sep 27: PI-1; Sep 28: PI-1; Sep 29: PI-1; Sep 30: PI-1; Oct 01: PI-1; Oct 02: PI-1; Oct 03: PI-1; Oct 04: PI-1; Oct 05: PI-1; Oct 06: PI-1; Oct 07: PI-1; Oct 08: PI-1; Oct 09: PI-1; Oct 10: PI-1; Oct 11: PI-1; Oct 12: PI-1; Oct 13: PI-1; Oct 14: PI-1
[395 empty] | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2 | PI-2
| Grade Beams | Grade Beams | Sep 24: CON-2; Sep 25: CON-2; Sep 26: CON-2; Sep 27: CON-2; Sep 28: CON-2; Sep 29: CON-2; Sep 30: CON-2; Oct 01: CON-2; Oct 02: CON-2; Oct 03: CON-2; Oct 04: CON-2; Oct 05: CON-2; Oct 06: CON-2; Oct 07: CON-2; Oct 08: CON-2; Oct 09: CON-2; Oct 10: CON-2; Oct 11: CON-2; Oct 12: CON-2; Oct 13: CON-2; Oct 14: CON-2; Oct 15: CON-3; Oct 16: CON-3; Oct 17: CON-3; Oct 18: CON-3; Oct 19: CON-3; Oct 20: CON-3; Oct 21: CON-3; Oct 22: CON-3; Oct 23: CON-3; Oct 24: CON-3; Oct 25: CON-3; Oct 26: CON-3; Oct 27: CON-3; Oct 28: CON-3; Oct 29: CON-3; Oct 30: CON-3; Oct 31: CON-3; Nov 01: CON-3; Nov 02: CON-3; Nov 03: CON-3; Nov 04: CON-3; Nov 05: CON-4; Nov 06: CON-4; Nov 07: CON-4; Nov 08: CON-4; Nov 09: CON-4; Nov 10: CON-4; Nov 11: CON-4; Nov 12: CON-4; Nov 13: CON-4; Nov 14: CON-4; Nov 15: CON-4; Nov 16: CON-4; Nov 17: CON-4; Nov 18: CON-4; Nov 19: CON-4; Nov 20: CON-4; Nov 21: CON-4; Nov 22: CON-4; Nov 23: CON-4; Nov 24: CON-4; Nov 25: CON-4; Nov 26: CON-5; Nov 27: CON-5; Nov 28: CON-5; Nov 29: CON-5; Nov 30: CON-5; Dec 01: CON-5; Dec 02: CON-5; Dec 03: CON-5; Dec 04: CON-5; Dec 05: CON-5; Dec 06: CON-5; Dec 07: CON-5; Dec 08: CON-5; Dec 09: CON-5; Dec 10: CON-5; Dec 11: CON-5; Dec 12: CON-5; Dec 13: CON-5; Dec 14: CON-5; Dec 15: CON-5; Dec 16: CON-5; Dec 17: CON-5; Dec 18: CON-5; Dec 19: CON-6; Dec 20: CON-6; Dec 21: CON-6; Dec 22: CON-6; Dec 23: CON-6; Dec 24: CON-6; Dec 25: CON-6; Dec 26: CON-6; Dec 27: CON-6; Dec 28: CON-6; Dec 29: CON-6; Dec 30: CON-6; Dec 31: CON-6; Jan 01: CON-6; Jan 02: CON-6; Jan 03: CON-6; Jan 04: CON-6; Jan 05: CON-6; Jan 06: CON-6; Jan 07: CON-6; Jan 08: CON-6; Jan 09: CON-6; Jan 10: CON-6; Jan 11: CON-6; Jan 12: CON-6; Jan 13: CON-6; Jan 14: CON-6; Jan 15: CON-6; Jan 16: CON-6
| Slabs | Zone 1 | Nov 26: CON-7; Nov 27: CON-7; Nov 28: CON-7; Nov 29: CON-7; Nov 30: CON-7; Dec 01: CON-7; Dec 02: CON-7; Dec 03: CON-7; Dec 04: CON-7; Dec 05: CON-7; Dec 06: CON-7; Dec 07: CON-7; Dec 08: CON-7; Dec 09: CON-7; Dec 10: CON-7; Dec 11: CON-7; Dec 12: CON-7; Dec 13: CON-7; Dec 14: CON-7; Dec 15: CON-7; Dec 16: CON-7; Dec 17: CON-7; Dec 18: CON-7
|  | Zone 2 | Jan 19: CON-8; Jan 20: CON-8; Jan 21: CON-8; Jan 22: CON-8; Jan 23: CON-8; Jan 24: CON-8; Jan 25: CON-8; Jan 26: CON-8; Jan 27: CON-8; Jan 28: CON-8; Jan 29: CON-8; Jan 30: CON-8; Jan 31: CON-8; Feb 01: CON-8; Feb 02: CON-8; Feb 03: CON-8; Feb 04: CON-8; Feb 05: CON-8; Feb 06: CON-8
|  | Zone 3 | Feb 16: CON-9; Feb 17: CON-9; Feb 18: CON-9; Feb 19: CON-9; Feb 20: CON-9; Feb 21: CON-9; Feb 22: CON-9; Feb 23: CON-9; Feb 24: CON-9; Feb 25: CON-9; Feb 26: CON-9; Feb 27: CON-9
|  | Zone 4 | Mar 16: CON-10; Mar 17: CON-10; Mar 18: CON-10; Mar 19: CON-10; Mar 20: CON-10; Mar 21: CON-10; Mar 22: CON-10; Mar 23: CON-10; Mar 24: CON-10; Mar 25: CON-10; Mar 26: CON-10; Mar 27: CON-10
|  | Zone 5 | Apr 28: CON-11; Apr 29: CON-11; Apr 30: CON-11; May 01: CON-11; May 02: CON-11; May 03: CON-11; May 04: CON-11; May 05: CON-11; May 06: CON-11; May 07: CON-11; May 08: CON-11; May 09: CON-11; May 10: CON-11; May 11: CON-11; May 12: CON-11; May 13: CON-11; May 14: CON-11; May 15: CON-11; May 16: CON-11; May 17: CON-11; May 18: CON-11
|  | Zone 6 | Jun 10: CON-12; Jun 11: CON-12; Jun 12: CON-12; Jun 13: CON-12; Jun 14: CON-12; Jun 15: CON-12; Jun 16: CON-12; Jun 17: CON-12; Jun 18: CON-12; Jun 19: CON-12; Jun 20: CON-12; Jun 21: CON-12; Jun 22: CON-12; Jun 23: CON-12; Jun 24: CON-12; Jun 25: CON-12; Jun 26: CON-12; Jun 27: CON-12; Jun 28: CON-12; Jun 29: CON-12; Jun 30: CON-12
| Underground Strucuture | Mechanical Yard | Oct 15: ELPL-2; Oct 16: ELPL-2; Oct 17: ELPL-2; Oct 18: ELPL-2; Oct 19: ELPL-2; Oct 20: ELPL-2; Oct 21: ELPL-2; Oct 22: ELPL-2; Oct 23: ELPL-2; Oct 24: ELPL-2; Oct 25: ELPL-2; Oct 26: ELPL-2; Oct 27: ELPL-2; Oct 28: ELPL-2; Oct 29: ELPL-2; Oct 30: ELPL-2; Oct 31: ELPL-2; Nov 01: ELPL-2; Nov 02: ELPL-2; Nov 03: ELPL-2; Nov 04: ELPL-2; Nov 05: ELPL-2; Nov 06: ELPL-2; Nov 07: ELPL-2; Nov 08: ELPL-2; Nov 09: ELPL-2; Nov 10: ELPL-2; Nov 11: ELPL-2; Nov 12: ELPL-2; Nov 13: ELPL-2; Nov 14: ELPL-2; Nov 15: ELPL-2; Nov 16: ELPL-2; Nov 17: ELPL-2; Nov 18: ELPL-2; Nov 19: ELPL-2; Nov 20: ELPL-2; Nov 21: ELPL-2; Nov 22: ELPL-2; Nov 23: ELPL-2; Nov 24: ELPL-2; Nov 25: ELPL-2; Nov 26: ELPL-2; Nov 27: ELPL-2; Nov 28: ELPL-2; Nov 29: ELPL-2; Nov 30: ELPL-2; Dec 01: ELPL-2; Dec 02: ELPL-2; Dec 03: ELPL-2; Dec 04: ELPL-2; Dec 05: ELPL-2; Dec 06: ELPL-2; Dec 07: ELPL-2; Dec 08: ELPL-2; Dec 09: ELPL-2; Dec 10: ELPL-2; Dec 11: ELPL-2; Dec 12: ELPL-2; Dec 13: ELPL-2; Dec 14: ELPL-2; Dec 15: ELPL-2; Dec 16: ELPL-2; Dec 17: ELPL-2; Dec 18: ELPL-2; Dec 19: ELPL-2; Dec 20: ELPL-2; Dec 21: ELPL-2; Dec 22: ELPL-2; Dec 23: ELPL-2; Dec 24: ELPL-2; Dec 25: ELPL-2; Dec 26: ELPL-2; Dec 27: ELPL-2; Dec 28: ELPL-2; Dec 29: ELPL-2; Dec 30: ELPL-2; Dec 31: ELPL-2; Jan 01: ELPL-2; Jan 02: ELPL-2; Jan 03: ELPL-2; Jan 04: ELPL-2; Jan 05: ELPL-2; Jan 06: ELPL-2; Jan 07: ELPL-2; Jan 08: ELPL-2; Jan 09: ELPL-2; Jan 10: ELPL-2; Jan 11: ELPL-2; Jan 12: ELPL-2; Jan 13: ELPL-2; Jan 14: ELPL-2; Jan 15: ELPL-2; Jan 16: ELPL-2
|  | Zone 1 | Oct 15: ELPL-1; Oct 16: ELPL-1; Oct 17: ELPL-1; Oct 18: ELPL-1; Oct 19: ELPL-1; Oct 20: ELPL-1; Oct 21: ELPL-1; Oct 22: ELPL-1; Oct 23: ELPL-1; Oct 24: ELPL-1; Oct 25: ELPL-1; Oct 26: ELPL-1; Oct 27: ELPL-1; Oct 28: ELPL-1; Oct 29: ELPL-1; Oct 30: ELPL-1; Oct 31: ELPL-1; Nov 01: ELPL-1; Nov 02: ELPL-1; Nov 03: ELPL-1; Nov 04: ELPL-1; Nov 05: ELPL-1; Nov 06: ELPL-1; Nov 07: ELPL-1; Nov 08: ELPL-1; Nov 09: ELPL-1; Nov 10: ELPL-1; Nov 11: ELPL-1; Nov 12: ELPL-1; Nov 13: ELPL-1; Nov 14: ELPL-1; Nov 15: ELPL-1; Nov 16: ELPL-1; Nov 17: ELPL-1; Nov 18: ELPL-1; Nov 19: ELPL-1; Nov 20: ELPL-1; Nov 21: ELPL-1; Nov 22: ELPL-1; Nov 23: ELPL-1; Nov 24: ELPL-1; Nov 25: ELPL-1
|  | Zone 2 | Nov 26: ELPL-1; Nov 27: ELPL-1; Nov 28: ELPL-1; Nov 29: ELPL-1; Nov 30: ELPL-1; Dec 01: ELPL-1; Dec 02: ELPL-1; Dec 03: ELPL-1; Dec 04: ELPL-1; Dec 05: ELPL-1; Dec 06: ELPL-1; Dec 07: ELPL-1; Dec 08: ELPL-1; Dec 09: ELPL-1; Dec 10: ELPL-1; Dec 11: ELPL-1; Dec 12: ELPL-1; Dec 13: ELPL-1; Dec 14: ELPL-1; Dec 15: ELPL-1; Dec 16: ELPL-1; Dec 17: ELPL-1; Dec 18: ELPL-1; Dec 19: ELPL-1; Dec 20: ELPL-1; Dec 21: ELPL-1; Dec 22: ELPL-1; Dec 23: ELPL-1; Dec 24: ELPL-1; Dec 25: ELPL-1; Dec 26: ELPL-1; Dec 27: ELPL-1; Dec 28: ELPL-1; Dec 29: ELPL-1; Dec 30: ELPL-1; Dec 31: ELPL-1; Jan 01: ELPL-1; Jan 02: ELPL-1; Jan 03: ELPL-1; Jan 04: ELPL-1; Jan 05: ELPL-1; Jan 06: ELPL-1; Jan 07: ELPL-1; Jan 08: ELPL-1; Jan 09: ELPL-1; Jan 10: ELPL-1; Jan 11: ELPL-1; Jan 12: ELPL-1; Jan 13: ELPL-1; Jan 14: ELPL-1; Jan 15: ELPL-1; Jan 16: ELPL-1
|  | Zone 3 | Jan 19: ELPL-1; Jan 20: ELPL-1; Jan 21: ELPL-1; Jan 22: ELPL-1; Jan 23: ELPL-1; Jan 24: ELPL-1; Jan 25: ELPL-1; Jan 26: ELPL-1; Jan 27: ELPL-1; Jan 28: ELPL-1; Jan 29: ELPL-1; Jan 30: ELPL-1; Jan 31: ELPL-1; Feb 01: ELPL-1; Feb 02: ELPL-1; Feb 03: ELPL-1; Feb 04: ELPL-1; Feb 05: ELPL-1; Feb 06: ELPL-1; Feb 07: ELPL-1; Feb 08: ELPL-1; Feb 09: ELPL-1; Feb 10: ELPL-1; Feb 11: ELPL-1; Feb 12: ELPL-1; Feb 13: ELPL-1
|  | Zone 4 | Feb 16: ELPL-1; Feb 17: ELPL-1; Feb 18: ELPL-1; Feb 19: ELPL-1; Feb 20: ELPL-1; Feb 21: ELPL-1; Feb 22: ELPL-1; Feb 23: ELPL-1; Feb 24: ELPL-1; Feb 25: ELPL-1; Feb 26: ELPL-1; Feb 27: ELPL-1; Feb 28: ELPL-1; Mar 01: ELPL-1; Mar 02: ELPL-1; Mar 03: ELPL-1; Mar 04: ELPL-1; Mar 05: ELPL-1; Mar 06: ELPL-1; Mar 07: ELPL-1; Mar 08: ELPL-1; Mar 09: ELPL-1; Mar 10: ELPL-1; Mar 11: ELPL-1; Mar 12: ELPL-1; Mar 13: ELPL-1
|  | Zone 5 | Mar 16: ELPL-1; Mar 17: ELPL-1; Mar 18: ELPL-1; Mar 19: ELPL-1; Mar 20: ELPL-1; Mar 21: ELPL-1; Mar 22: ELPL-1; Mar 23: ELPL-1; Mar 24: ELPL-1; Mar 25: ELPL-1; Mar 26: ELPL-1; Mar 27: ELPL-1; Mar 28: ELPL-1; Mar 29: ELPL-1; Mar 30: ELPL-1; Mar 31: ELPL-1; Apr 01: ELPL-1; Apr 02: ELPL-1; Apr 03: ELPL-1; Apr 04: ELPL-1; Apr 05: ELPL-1; Apr 06: ELPL-1; Apr 07: ELPL-1; Apr 08: ELPL-1; Apr 09: ELPL-1; Apr 10: ELPL-1; Apr 11: ELPL-1; Apr 12: ELPL-1; Apr 13: ELPL-1; Apr 14: ELPL-1; Apr 15: ELPL-1; Apr 16: ELPL-1; Apr 17: ELPL-1; Apr 18: ELPL-1; Apr 19: ELPL-1; Apr 20: ELPL-1; Apr 21: ELPL-1; Apr 22: ELPL-1; Apr 23: ELPL-1; Apr 24: ELPL-1; Apr 25: ELPL-1; Apr 26: ELPL-1; Apr 27: ELPL-1
|  | Zone 6 | Apr 28: ELPL-1; Apr 29: ELPL-1; Apr 30: ELPL-1; May 01: ELPL-1; May 02: ELPL-1; May 03: ELPL-1; May 04: ELPL-1; May 05: ELPL-1; May 06: ELPL-1; May 07: ELPL-1; May 08: ELPL-1; May 09: ELPL-1; May 10: ELPL-1; May 11: ELPL-1; May 12: ELPL-1; May 13: ELPL-1; May 14: ELPL-1; May 15: ELPL-1; May 16: ELPL-1; May 17: ELPL-1; May 18: ELPL-1; May 19: ELPL-1; May 20: ELPL-1; May 21: ELPL-1; May 22: ELPL-1; May 23: ELPL-1; May 24: ELPL-1; May 25: ELPL-1; May 26: ELPL-1; May 27: ELPL-1; May 28: ELPL-1; May 29: ELPL-1; May 30: ELPL-1; May 31: ELPL-1; Jun 01: ELPL-1; Jun 02: ELPL-1; Jun 03: ELPL-1; Jun 04: ELPL-1; Jun 05: ELPL-1; Jun 06: ELPL-1; Jun 07: ELPL-1; Jun 08: ELPL-1; Jun 09: ELPL-1
|  | Zone 7A | Jun 10: ELPL-3; Jun 11: ELPL-3; Jun 12: ELPL-3; Jun 13: ELPL-3; Jun 14: ELPL-3; Jun 15: ELPL-3; Jun 16: ELPL-3; Jun 17: ELPL-3; Jun 18: ELPL-3; Jun 19: ELPL-3; Jun 20: ELPL-3; Jun 21: ELPL-3; Jun 22: ELPL-3; Jun 23: ELPL-3; Jun 24: ELPL-3; Jun 25: ELPL-3; Jun 26: ELPL-3; Jun 27: ELPL-3; Jun 28: ELPL-3; Jun 29: ELPL-3; Jun 30: ELPL-3
|  | Zone 7B | Jul 01: ELPL-3; Jul 02: ELPL-3; Jul 03: ELPL-3; Jul 04: ELPL-3; Jul 05: ELPL-3; Jul 06: ELPL-3; Jul 07: ELPL-3; Jul 08: ELPL-3; Jul 09: ELPL-3; Jul 10: ELPL-3; Jul 11: ELPL-3; Jul 12: ELPL-3; Jul 13: ELPL-3; Jul 14: ELPL-3; Jul 15: ELPL-3; Jul 16: ELPL-3; Jul 17: ELPL-3; Jul 18: ELPL-3; Jul 19: ELPL-3; Jul 20: ELPL-3; Jul 21: ELPL-3; Jul 22: ELPL-3
Interiors | Above Grade Structures | Zone 1 | Jan 14: SL-2; Jan 15: SL-2; Jan 16: SL-2; Jan 17: SL-2; Jan 18: SL-2; Jan 19: SL-2; Jan 20: SL-2; Jan 21: SL-2; Jan 22: SL-2; Jan 23: SL-2; Jan 24: SL-2; Jan 25: SL-2; Jan 26: SL-2; Jan 27: SL-2
|  | Zone 2 | Jan 28: SL-2; Jan 29: SL-2; Jan 30: SL-2; Jan 31: SL-2; Feb 01: SL-2; Feb 02: SL-2; Feb 03: SL-2; Feb 04: SL-2; Feb 05: SL-2; Feb 06: SL-2; Feb 07: SL-2; Feb 08: SL-2; Feb 09: SL-2; Feb 10: SL-2
|  | Zone 3 | Feb 11: SL-2; Feb 12: SL-2; Feb 13: SL-2; Feb 14: SL-2; Feb 15: SL-2; Feb 16: SL-2; Feb 17: SL-2; Feb 18: SL-2; Feb 19: SL-2; Feb 20: SL-2; Feb 21: SL-2; Feb 22: SL-2; Feb 23: SL-2; Feb 24: SL-2
|  | Zone 4 | Feb 25: SL-2; Feb 26: SL-2; Feb 27: SL-2; Feb 28: SL-2; Mar 01: SL-2; Mar 02: SL-2; Mar 03: SL-2; Mar 04: SL-2; Mar 05: SL-2; Mar 06: SL-2; Mar 07: SL-2; Mar 08: SL-2; Mar 09: SL-2; Mar 10: SL-2
|  | Zone 5 | Mar 11: SL-2; Mar 12: SL-2; Mar 13: SL-2; Mar 14: SL-2; Mar 15: SL-2; Mar 16: SL-2; Mar 17: SL-2; Mar 18: SL-2; Mar 19: SL-2; Mar 20: SL-2; Mar 21: SL-2; Mar 22: SL-2; Mar 23: SL-2; Mar 24: SL-2
|  | Zone 6 | Mar 25: SL-2; Mar 26: SL-2; Mar 27: SL-2; Mar 28: SL-2; Mar 29: SL-2; Mar 30: SL-2; Mar 31: SL-2; Apr 01: SL-2; Apr 02: SL-2; Apr 03: SL-2; Apr 04: SL-2; Apr 05: SL-2; Apr 06: SL-2; Apr 07: SL-2; Apr 08: SL-2
| RI & Finishes | Kitchen | Apr 28: SPE-1; Apr 29: SPE-1; Apr 30: SPE-1; May 01: SPE-1; May 02: SPE-1; May 03: SPE-1; May 04: SPE-1; May 05: SPE-1; May 06: SPE-1; May 07: SPE-1; May 08: SPE-1; May 09: SPE-1; May 10: SPE-1; May 11: SPE-1; May 12: SPE-1; May 13: SPE-1; May 14: SPE-1; May 15: SPE-1; May 16: SPE-1; May 17: SPE-1; May 18: SPE-1; May 19: SPE-1; May 20: SPE-1; May 21: SPE-1; May 22: SPE-1; May 23: SPE-1; May 24: SPE-1; May 25: SPE-1; May 26: SPE-1; May 27: SPE-1; May 28: SPE-1; May 29: SPE-1; May 30: SPE-1; May 31: SPE-1; Jun 01: SPE-1; Jun 02: SPE-1; Jun 03: SPE-1; Jun 04: SPE-1; Jun 05: SPE-1; Jun 06: SPE-1; Jun 07: SPE-1; Jun 08: SPE-1; Jun 09: SPE-1; Jun 10: SPE-1; Jun 11: SPE-1; Jun 12: SPE-1; Jun 13: SPE-1; Jun 14: SPE-1; Jun 15: SPE-1; Jun 16: SPE-1; Jun 17: SPE-1; Jun 18: SPE-1; Jun 19: SPE-1; Jun 20: SPE-1; Jun 21: SPE-1; Jun 22: SPE-1; Jun 23: SPE-1; Jun 24: SPE-1; Jun 25: SPE-1; Jun 26: SPE-1; Jun 27: SPE-1; Jun 28: SPE-1; Jun 29: SPE-1; Jun 30: SPE-1; Jul 01: SPE-1; Jul 02: SPE-1; Jul 03: SPE-1; Jul 04: SPE-1; Jul 05: SPE-1; Jul 06: SPE-1; Jul 07: SPE-1; Jul 08: SPE-1; Jul 09: SPE-1; Jul 10: SPE-1; Jul 11: SPE-1; Jul 12: SPE-1; Jul 13: SPE-1; Jul 14: SPE-1; Jul 15: SPE-1; Jul 16: SPE-1; Jul 17: SPE-1; Jul 18: SPE-1; Jul 19: SPE-1; Jul 20: SPE-1; Jul 21: SPE-1; Jul 22: SPE-1
|  | Mechanical Room | Dec 12: CON-13; Dec 13: CON-13; Dec 14: CON-13; Dec 15: CON-13; Dec 16: CON-13; Dec 17: CON-13; Dec 18: CON-13; May 18: MEC-1; May 19: MEC-1; May 20: MEC-1; May 21: MEC-1; May 22: MEC-1; May 23: MEC-1; May 24: MEC-1; May 25: MEC-1; May 26: MEC-1; May 27: MEC-1; May 28: MEC-1; May 29: MEC-1; May 30: MEC-1; May 31: MEC-1; Jun 01: MEC-1; Jun 02: PLU-1; Jun 03: PLU-1; Jun 04: PLU-1; Jun 05: PLU-1; Jun 06: PLU-1; Jun 07: PLU-1; Jun 08: PLU-1; Jun 09: PLU-1; Jun 10: PLU-1; Jun 11: PLU-1; Jun 12: PLU-1; Jun 13: PLU-1; Jun 14: PLU-1; Jun 15: PLU-1; Jun 16: PLU-1; Jun 17: PLU-1; Jun 18: PLU-1; Jun 19: PLU-1; Jun 20: PLU-1; Jun 21: PLU-1; Jun 22: PLU-1; Jun 23: MEC-5; Jun 24: MEC-5; Jun 25: MEC-5; Jun 26: MEC-5; Jun 27: MEC-5; Jun 28: MEC-5; Jun 29: MEC-5; Jun 30: MEC-5; Jul 01: MEC-5; Jul 02: MEC-5; Jul 03: MEC-5; Jul 04: MEC-5; Jul 05: MEC-5; Jul 06: MEC-5; Jul 07: MEC-5; Jul 08: MEC-5; Jul 09: MEC-5; Jul 10: MEC-5; Jul 11: MEC-5; Jul 12: MEC-5; Jul 13: MEC-5; Jul 14: MEC-5; Jul 15: MEC-5; Jul 16: MEC-5; Jul 17: MEC-5; Jul 18: MEC-5; Jul 19: MEC-5; Jul 20: MEC-5; Jul 21: MEC-5; Jul 30: EL-5; Jul 31: EL-5; Aug 01: EL-5; Aug 02: EL-5; Aug 03: EL-5; Aug 04: EL-5; Aug 05: EL-5; Aug 06: EL-5; Aug 07: EL-5; Aug 08: EL-5; Aug 09: EL-5; Aug 10: EL-5; Aug 11: EL-5; Aug 12: EL-5
[639 empty] | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | PLU-1 | [37 empty] | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4 | EL-4
|  | Zone 1 | Jan 28: FL-1; Jan 29: FL-1; Jan 30: FL-1; Jan 31: FL-1; Feb 01: FL-1; Feb 02: FL-1; Feb 03: FL-1; Feb 04: FL-1; Feb 05: FL-1; Feb 06: FL-1; Feb 07: FL-1; Feb 08: FL-1; Feb 09: FL-1; Feb 10: FL-1; Feb 11: FR-4; Feb 12: FR-4; Feb 13: FR-4; Feb 14: FR-4; Feb 15: FR-4; Feb 16: FR-4; Feb 17: FR-4; Feb 18: FR-4; Feb 19: FR-4; Feb 20: FR-4; Feb 21: FR-4; Feb 22: FR-4; Feb 23: FR-4; Feb 24: FR-4; Feb 25: MEP-1; Feb 26: MEP-1; Feb 27: MEP-1; Feb 28: MEP-1; Mar 01: MEP-1; Mar 02: MEP-1; Mar 03: MEP-1; Mar 04: MEP-1; Mar 05: MEP-1; Mar 06: MEP-1; Mar 07: MEP-1; Mar 08: MEP-1; Mar 09: MEP-1; Mar 10: MEP-1; Mar 11: MEP-1; Mar 12: MEP-1; Mar 13: MEP-1; Mar 14: MEP-1; Mar 15: MEP-1; Mar 16: MEP-1; Mar 17: MEP-1; Mar 18: MEP-1; Mar 19: MEP-1; Mar 20: MEP-1; Mar 21: MEP-1; Mar 22: MEP-1; Mar 23: MEP-1; Mar 24: MEP-1; Mar 25: MG-2; Mar 26: FR-5; Mar 27: FR-5; Mar 30: DRY-1; Mar 31: DRY-1; Apr 01: DRY-1; Apr 02: DRY-1; Apr 03: DRY-1; Apr 04: DRY-1; Apr 05: DRY-1; Apr 06: DRY-1; Apr 07: DRY-1; Apr 08: DRY-1; Apr 09: T-1; Apr 10: T-1; Apr 11: T-1; Apr 12: T-1; Apr 13: T-1; Apr 14: T-1; Apr 15: T-1; Apr 23: FR-6; Apr 24: FR-6; Apr 25: FR-6; Apr 26: FR-6; Apr 27: FR-6; Apr 28: FR-6; Apr 29: FR-6; Apr 30: PA-2; May 01: PA-2; May 02: PA-2; May 03: PA-2; May 04: PA-2; May 05: PA-2; May 06: PA-2; May 07: PA-3; May 08: PA-3; May 09: PA-3; May 10: PA-3; May 11: PA-3; May 12: PA-3; May 13: PA-3; May 14: PLU-2; May 15: PLU-2; May 16: PLU-2; May 17: PLU-2; May 18: PLU-2; May 19: PLU-2; May 20: PLU-2; Jun 22: DOOR-1; Jun 23: DOOR-1; Jun 24: DOOR-1; Jun 25: DOOR-1; Jun 26: DOOR-1; Jun 27: DOOR-1; Jun 28: DOOR-1; Jun 29: DOOR-1; Jun 30: DOOR-1; Jul 01: DOOR-1; Jul 02: DOOR-1; Jul 03: DOOR-1; Jul 04: DOOR-1; Jul 05: DOOR-1; Jul 06: DOOR-1; Jul 22: MG-1; Jul 23: MG-1; Jul 24: MG-1; Jul 25: MG-1; Jul 26: MG-1; Jul 27: MG-1; Jul 28: MG-1; Jul 29: MG-1; Jul 30: MG-1; Jul 31: MG-1; Aug 01: MG-1; Aug 02: MG-1; Aug 03: MG-1; Aug 04: MG-1; Aug 05: MG-1; Aug 06: MG-1; Aug 07: MG-1; Aug 08: MG-1; Aug 09: MG-1; Aug 10: MG-1; Aug 11: MG-1; Aug 12: MG-1; Aug 13: MG-1; Aug 14: MG-1; Aug 15: MG-1; Aug 16: MG-1; Aug 17: MG-1; Aug 18: MG-1; Sep 08: MEC-1; Sep 09: MEC-1; Sep 10: MEC-1; Sep 11: MEC-1; Sep 12: MEC-1; Sep 13: MEC-1; Sep 14: MEC-1
[526 empty] | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 | CON-14 |  |  | CON-15 | CON-15 | CON-15 | CON-15 | CON-15 | [12 empty] | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | PA-1 | PA-1 | PA-1 | PA-1 | PA-1 | PA-1 | PA-1 | FR-1 | FR-1 | FR-1 | FR-1 | FR-1 | FR-1 | FR-1 | FR-1 | FR-1 |  |  | INS-1 | FR-2 | FR-2 | FR-2 | EL-6 | EL-6 | EL-6 | EL-6 | EL-6 | EL-6 | EL-6 | [69 empty] | EL-7 | EL-7 |  |  | MEC-4 | MEC-4 | MEC-4 | MEC-4 | MEC-4
[528 empty] | FR-8 | FR-8 | FR-8 | FR-8 | FR-8 | FR-8 | FR-8 | FR-8 | FR-8 | FR-8 | FR-8 | FR-8 | FR-8 | FR-8 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MG-5 | [14 empty] | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | MAS-3 | [74 empty] | EL-8 | EL-8 | EL-8 | EL-8 | EL-8
[568 empty] | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-16 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17 | CON-17
|  | Zone 2 | Feb 25: FR-4; Feb 26: FR-4; Feb 27: FR-4; Feb 28: FR-4; Mar 01: FR-4; Mar 02: FR-4; Mar 03: FR-4; Mar 04: FR-4; Mar 05: FR-4; Mar 06: FR-4; Mar 07: FR-4; Mar 08: FR-4; Mar 09: FR-4; Mar 10: FR-4; Mar 11: DOOR-2; Mar 12: DOOR-2; Mar 13: DOOR-2; Mar 14: DOOR-2; Mar 15: DOOR-2; Mar 16: DOOR-2; Mar 17: DOOR-2; Apr 09: MG-2; Apr 10: FR-5; Apr 11: FR-5; Apr 12: FR-5; Apr 13: FR-5; Apr 14: DRY-1; Apr 15: DRY-1; Apr 16: DRY-1; Apr 17: DRY-1; Apr 18: DRY-1; Apr 19: DRY-1; Apr 20: DRY-1; Apr 21: DRY-1; Apr 22: DRY-1; Apr 23: DRY-2; Apr 24: DRY-2; Apr 25: DRY-2; Apr 26: DRY-2; Apr 27: DRY-2; Apr 28: DRY-2; Apr 29: DRY-2; Apr 30: DRY-2; May 01: DRY-2; May 02: DRY-2; May 03: DRY-2; May 04: DRY-2; May 05: DRY-2; May 06: DRY-2; May 07: FR-6; May 08: FR-6; May 09: FR-6; May 10: FR-6; May 11: FR-6; May 12: PA-4; May 13: PA-4; May 14: PA-4; May 15: PA-4; May 16: PA-4; May 17: PA-4; May 18: PA-4; May 19: PA-4; May 20: PA-4; May 21: PA-4; May 22: PA-4; May 23: PA-4; May 24: PA-4; May 25: PA-4; May 26: PA-4; May 27: PA-4; May 28: PA-4; May 29: PA-4; May 30: PA-4; May 31: PA-4; Jun 01: PA-4; Jun 02: PA-4; Jun 03: PA-4; Jun 04: PA-4; Jun 05: PA-4; Jun 08: EL-9; Jun 09: EL-9; Jun 10: EL-9; Jun 11: EL-9; Jun 12: EL-9; Jun 13: EL-9; Jun 14: EL-9; Jun 15: EL-9; Jun 16: EL-9; Jun 17: EL-9; Jun 18: EL-9; Jun 19: EL-9; Jun 20: EL-9; Jun 21: EL-9; Jun 22: EL-9; Jun 23: EL-9; Jun 24: EL-9; Jun 25: EL-9; Jun 26: EL-9; Jul 07: DOOR-1; Jul 08: DOOR-1; Jul 09: DOOR-1; Jul 10: DOOR-1; Jul 11: DOOR-1; Jul 12: DOOR-1; Jul 13: DOOR-1; Jul 14: MG-1; Jul 15: MG-1; Jul 16: MG-1; Jul 17: MG-1; Jul 18: MG-1; Jul 19: MG-1; Jul 20: MG-1; Sep 15: MEC-1; Sep 16: MEC-1; Sep 17: MEC-1; Sep 18: MEC-1; Sep 19: MEC-1; Sep 20: MEC-1; Sep 21: MEC-1
[556 empty] | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MG-5 | [13 empty] | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 |  |  |  | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4
[556 empty] | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | [21 empty] | PA-1 | PA-1 | PA-1 | PA-1 | PA-1 | PA-1 | PA-1 | PA-2 | PA-2 | PA-2 | PA-2 | PA-2 | PA-2 | PA-2 | PA-3 | PA-3 | PA-3 | PA-3 | PA-3 | PA-3 | PA-3 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2
[606 empty] | OH-1 | OH-1 | OH-1 | OH-1 | OH-1 | OH-1 | OH-1 | [32 empty] | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5
|  | Zone 3 | Mar 11: FR-4; Mar 12: FR-4; Mar 13: FR-4; Mar 14: FR-4; Mar 15: FR-4; Mar 16: FR-4; Mar 17: FR-4; Mar 18: FR-4; Mar 19: FR-4; Mar 20: FR-4; Mar 21: FR-4; Mar 22: FR-4; Mar 23: FR-4; Mar 24: FR-4; Mar 25: DOOR-2; Mar 26: DOOR-2; Mar 27: DOOR-2; Apr 09: MG-2; Apr 23: MG-5; Apr 24: FR-5; Apr 25: FR-5; Apr 26: FR-5; Apr 27: FR-5; Apr 28: DRY-1; Apr 29: DRY-1; Apr 30: DRY-1; May 01: DRY-1; May 02: DRY-1; May 03: DRY-1; May 04: DRY-1; May 05: DRY-1; May 06: DRY-1; May 07: PA-1; May 08: PA-1; May 09: PA-1; May 10: PA-1; May 11: PA-1; May 12: PA-1; May 13: PA-1; May 14: PA-2; May 15: PA-2; May 16: PA-2; May 17: PA-2; May 18: PA-2; May 19: PA-2; May 20: PA-2; May 21: FR-6; May 22: FR-6; May 23: FR-6; May 24: FR-6; May 25: FR-6; May 26: FR-6; May 27: FR-6; May 28: FR-6; May 29: FR-1; May 30: FR-1; May 31: FR-1; Jun 01: FR-1; Jun 02: FR-1; Jun 03: FR-1; Jun 04: FR-1; Jun 05: FR-1; Jun 06: FR-1; Jun 07: FR-1; Jun 08: FR-1; Jun 09: INS-1; Jun 10: FR-2; Jun 11: FR-2; Jun 12: FR-2; Jun 15: MILL-1; Jun 16: MILL-1; Jun 17: MILL-1; Jun 18: MILL-1; Jun 19: MILL-1; Jun 22: FL-6; Jun 23: FL-6; Jun 24: FL-6; Jun 25: FL-6; Jun 26: FL-6; Jun 29: FL-4; Jun 30: FL-4; Jul 01: FL-4; Jul 02: FL-4; Jul 03: FL-4; Jul 04: FL-4; Jul 05: FL-4; Jul 06: FL-4; Jul 07: FL-4; Jul 08: FL-4; Jul 09: FL-4; Jul 10: FL-4; Jul 11: FL-4; Jul 12: FL-4; Jul 13: FL-4; Jul 14: DOOR-1; Jul 15: DOOR-1; Jul 16: DOOR-1; Jul 17: MG-1; Jul 18: MG-1; Jul 19: MG-1; Jul 20: MG-1; Jul 21: MG-1; Jul 22: MG-1; Jul 23: MG-1; Sep 22: MEC-1; Sep 23: MEC-1; Sep 24: MEC-1; Sep 25: MEC-1; Sep 26: MEC-1; Sep 27: MEC-1; Sep 28: MEC-1
[570 empty] | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | [28 empty] | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | FR-9 | FR-9 | FR-9 | FR-9 | FR-9 | FR-9 | FR-9 | FR-9 | [14 empty] | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 |  |  |  | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9
[570 empty] | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | [28 empty] | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | [10 empty] | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2
|  | Zone 4 | Mar 25: FR-4; Mar 26: FR-4; Mar 27: FR-4; Mar 28: FR-4; Mar 29: FR-4; Mar 30: FR-4; Mar 31: FR-4; Apr 01: FR-4; Apr 02: FR-4; Apr 03: FR-4; Apr 04: FR-4; Apr 05: FR-4; Apr 06: FR-4; Apr 07: FR-4; Apr 08: FR-4; Apr 09: DOOR-2; Apr 10: DOOR-2; Apr 11: DOOR-2; Apr 12: DOOR-2; Apr 13: DOOR-2; May 07: MG-2; May 08: FR-5; May 09: FR-5; May 10: FR-5; May 11: FR-5; May 12: DRY-1; May 13: DRY-1; May 14: DRY-1; May 15: DRY-1; May 16: DRY-1; May 17: DRY-1; May 18: DRY-1; May 19: DRY-1; May 20: DRY-1; May 21: PA-1; May 22: PA-1; May 23: PA-1; May 24: PA-1; May 25: PA-1; May 26: PA-1; May 27: PA-1; May 28: PA-1; May 29: PA-2; May 30: PA-2; May 31: PA-2; Jun 01: PA-2; Jun 02: PA-2; Jun 03: PA-2; Jun 04: PA-2; Jun 05: FR-6; Jun 06: FR-6; Jun 07: FR-6; Jun 08: FR-6; Jun 09: FR-6; Jun 10: DRY-3; Jun 11: DRY-3; Jun 12: DRY-3; Jun 13: DRY-3; Jun 14: DRY-3; Jun 15: DRY-3; Jun 16: DRY-3; Jun 17: DRY-3; Jun 18: DRY-3; Jun 19: DRY-3; Jun 20: DRY-3; Jun 21: DRY-3; Jun 22: DRY-3; Jun 23: DRY-3; Jun 24: DRY-3; Jun 25: DRY-3; Jun 26: DRY-3; Jun 27: DRY-3; Jun 28: DRY-3; Jun 29: DRY-3; Jun 30: DRY-3; Jul 01: DRY-3; Jul 02: DRY-3; Jul 03: DRY-3; Jul 04: DRY-3; Jul 05: DRY-3; Jul 06: DRY-3; Jul 07: FL-6; Jul 08: FL-6; Jul 09: FL-6; Jul 10: FL-6; Jul 11: FL-6; Jul 12: FL-6; Jul 13: FL-6; Jul 14: EL-9; Jul 15: EL-9; Jul 16: EL-9; Jul 17: EL-9; Jul 18: EL-9; Jul 19: EL-9; Jul 20: EL-9; Jul 21: EL-9; Jul 22: EL-9; Jul 23: EL-9; Jul 24: EL-9; Jul 25: EL-9; Jul 26: EL-9; Jul 27: EL-9; Aug 11: FL-5; Aug 12: FL-5; Aug 13: FL-5; Aug 14: FL-5; Aug 15: FL-5; Aug 16: FL-5; Aug 17: FL-5; Aug 18: FL-5; Aug 19: FL-5; Aug 20: FL-5; Aug 21: FL-5; Aug 22: FL-5; Aug 23: FL-5; Aug 24: FL-5; Aug 25: DOOR-1; Aug 26: DOOR-1; Aug 27: DOOR-1; Aug 28: MG-1; Aug 29: MG-1; Aug 30: MG-1; Aug 31: MG-1; Sep 01: MG-1; Sep 02: MG-1; Sep 03: MG-1; Sep 29: MEC-1; Sep 30: MEC-1; Oct 01: MEC-1; Oct 02: MEC-1; Oct 03: MEC-1; Oct 04: MEC-1; Oct 05: MEC-1; Oct 06: MEC-1
[585 empty] | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MG-5 | [13 empty] | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | PA-3 | PA-3 | PA-3 | PA-3 | PA-3 | PA-3 | PA-3 | [10 empty] | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | [10 empty] | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | FL-2 | [21 empty] | FL-7 | FL-7 | FL-7 | FL-7 | FL-7 | FL-7 | FL-7 | FL-7 | FL-7 | FL-7 | FL-7 | FL-7 | FL-7 | FL-7
[585 empty] | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | [29 empty] | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | [7 empty] | PLU-2 | [17 empty] | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3 | FL-3
|  | Zone 5 | Apr 09: FR-4; Apr 10: FR-4; Apr 11: FR-4; Apr 12: FR-4; Apr 13: FR-4; Apr 14: FR-4; Apr 15: FR-4; Apr 16: FR-4; Apr 17: FR-4; Apr 18: FR-4; Apr 19: FR-4; Apr 20: FR-4; Apr 21: FR-4; Apr 22: FR-4; Apr 23: DOOR-2; Apr 24: DOOR-2; Apr 25: DOOR-2; Apr 26: DOOR-2; Apr 27: DOOR-2; Apr 28: DOOR-2; Apr 29: DOOR-2; Apr 30: DOOR-2; May 01: DOOR-2; May 02: DOOR-2; May 03: DOOR-2; May 04: DOOR-2; May 05: DOOR-2; May 06: DOOR-2; May 21: MG-2; May 22: FR-5; May 23: FR-5; May 24: FR-5; May 25: FR-5; May 26: FR-5; May 27: FR-10; May 28: FR-10; May 29: FR-10; May 30: FR-10; May 31: FR-10; Jun 01: FR-10; Jun 02: FR-10; Jun 03: FR-10; Jun 04: FR-10; Jun 05: PA-1; Jun 06: PA-1; Jun 07: PA-1; Jun 08: PA-1; Jun 09: PA-1; Jun 10: PA-1; Jun 11: PA-1; Jun 12: PA-2; Jun 13: PA-2; Jun 14: PA-2; Jun 15: PA-2; Jun 16: PA-2; Jun 17: PA-2; Jun 18: PA-2; Jun 19: FR-6; Jun 20: FR-6; Jun 21: FR-6; Jun 22: FR-6; Jun 23: FR-6; Jun 24: DRY-3; Jun 25: DRY-3; Jun 26: DRY-3; Jun 27: DRY-3; Jun 28: DRY-3; Jun 29: DRY-3; Jun 30: DRY-3; Jul 01: DRY-3; Jul 02: DRY-3; Jul 03: DRY-3; Jul 04: DRY-3; Jul 05: DRY-3; Jul 06: DRY-3; Jul 07: DRY-3; Jul 08: DRY-3; Jul 09: DRY-3; Jul 10: DRY-3; Jul 11: DRY-3; Jul 12: DRY-3; Jul 13: DRY-3; Jul 14: DRY-3; Jul 15: DRY-3; Jul 16: DRY-3; Jul 17: DRY-3; Jul 18: DRY-3; Jul 19: DRY-3; Jul 20: DRY-3; Jul 21: FL-6; Jul 22: FL-6; Jul 23: FL-6; Jul 24: FL-6; Jul 25: FL-6; Jul 26: FL-6; Jul 27: FL-6; Jul 28: FL-6; Jul 29: FL-6; Jul 30: FL-6; Aug 18: FL-1; Aug 19: FL-1; Aug 20: FL-1; Aug 21: FL-1; Aug 22: FL-1; Aug 23: FL-1; Aug 24: FL-1; Aug 25: FL-5; Aug 26: FL-5; Aug 27: FL-5; Aug 28: FL-5; Aug 29: FL-5; Aug 30: FL-5; Aug 31: FL-5; Sep 01: FL-5; Sep 02: FL-5; Sep 03: FL-5; Sep 04: FL-5; Sep 05: FL-5; Sep 06: FL-5; Sep 07: FL-5; Sep 08: FL-5; Sep 09: FL-5; Sep 10: FL-5; Sep 11: FL-5; Sep 12: FL-5; Sep 13: FL-5; Sep 14: FL-5; Sep 15: FL-5; Sep 16: FL-5; Sep 17: FL-5; Sep 18: FL-5; Sep 19: FL-5; Sep 20: FL-5; Sep 21: FL-5; Sep 22: FL-5; Sep 23: FL-5; Sep 24: FL-5; Sep 25: FL-5; Sep 26: FL-5; Sep 27: FL-5; Sep 28: FL-5; Sep 29: FL-5; Sep 30: FL-5; Oct 01: FL-5; Oct 02: FL-5; Oct 03: FL-5; Oct 04: FL-5; Oct 05: FL-5; Oct 06: FL-5; Oct 07: FL-5; Oct 08: FL-5; Oct 09: FL-5; Oct 10: FL-5; Oct 11: FL-5; Oct 12: FL-5; Oct 13: FL-5; Oct 14: FL-5; Oct 15: FL-5; Oct 16: FL-5; Oct 17: FL-5; Oct 18: FL-5; Oct 19: FL-5; Oct 20: FL-5; Oct 21: FL-5; Oct 22: FL-5; Oct 23: FL-5; Oct 24: FL-5; Oct 25: FL-5; Oct 26: FL-5; Oct 27: FL-5; Oct 28: FL-5; Oct 29: FL-5; Oct 30: FL-5; Oct 31: FL-5; Nov 01: FL-5; Nov 02: FL-5; Nov 03: FL-5; Nov 04: FL-5; Nov 05: FL-5; Nov 06: FL-5; Nov 07: FL-5; Nov 08: FL-5; Nov 09: FL-5; Nov 10: FL-5; Nov 11: DOOR-1; Nov 12: DOOR-1; Nov 13: DOOR-1; Nov 14: DOOR-1; Nov 15: DOOR-1; Nov 16: DOOR-1; Nov 17: DOOR-1; Nov 18: DOOR-1; Nov 19: DOOR-1; Nov 20: DOOR-1; Nov 21: DOOR-1; Nov 22: DOOR-1; Nov 23: DOOR-1; Nov 24: DOOR-1; Nov 25: DOOR-1; Nov 26: DOOR-1; Nov 27: DOOR-1; Nov 28: DOOR-1; Nov 29: DOOR-1; Nov 30: DOOR-1; Dec 01: DOOR-1; Dec 02: DOOR-1; Dec 03: DOOR-1; Dec 04: DOOR-1; Dec 05: DOOR-1; Dec 06: DOOR-1; Dec 07: DOOR-1; Dec 08: DOOR-1; Dec 09: DOOR-1; Dec 10: DOOR-1; Dec 11: DOOR-1; Dec 12: DOOR-1; Dec 13: DOOR-1; Dec 14: DOOR-1; Dec 15: DOOR-1; Dec 16: DOOR-1; Dec 17: DOOR-1; Dec 18: DOOR-1; Dec 19: DOOR-1; Dec 20: DOOR-1; Dec 21: DOOR-1; Dec 22: DOOR-1; Dec 23: DOOR-1; Dec 24: DOOR-1; Dec 25: DOOR-1; Dec 26: DOOR-1; Dec 27: DOOR-1; Dec 28: DOOR-1; Dec 29: DOOR-1; Dec 30: DOOR-1; Dec 31: DOOR-1; Jan 01: DOOR-1; Jan 02: DOOR-1; Jan 03: DOOR-1; Jan 04: DOOR-1; Jan 05: DOOR-1; Jan 06: DOOR-1; Jan 07: DOOR-1; Jan 08: DOOR-1; Jan 09: DOOR-1; Jan 10: DOOR-1; Jan 11: DOOR-1; Jan 12: LV-1; Jan 13: LV-1; Jan 14: LV-1; Jan 15: LV-1; Jan 16: LV-1; Jan 17: LV-1; Jan 18: LV-1; Jan 19: LV-1; Jan 20: LV-1; Jan 21: LV-1; Jan 22: LV-1; Jan 23: LV-1; Jan 24: LV-1; Jan 25: LV-1; Jan 26: LV-1; Jan 27: LV-1; Jan 28: LV-1; Jan 29: LV-1; Jan 30: LV-1; Jan 31: LV-1; Feb 01: LV-1; Feb 02: LV-1; Feb 03: LV-1; Feb 04: LV-1; Feb 05: LV-1; Feb 06: LV-1; Feb 07: LV-1; Feb 08: LV-1; Feb 09: LV-1; Feb 10: LV-1; Feb 11: LV-1; Feb 12: LV-1; Feb 13: LV-1; Feb 14: LV-1; Feb 15: LV-1; Feb 16: LV-1; Feb 17: LV-1; Feb 18: LV-1; Feb 19: LV-1; Feb 20: LV-1; Feb 21: LV-1; Feb 22: LV-1; Feb 23: MG-1; Feb 24: MG-1; Feb 25: MG-1; Feb 26: MG-1; Feb 27: MG-1; Feb 28: MG-1; Mar 01: MG-1
[599 empty] | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MG-5 | [14 empty] | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | PA-3 | PA-3 | PA-3 | PA-3 | PA-3 | PA-3 | PA-3 |  |  |  | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | MILL-1 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2 | SPE-2
[599 empty] | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | [29 empty] | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 |  |  |  | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2
[688 empty] | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | FL-4 | [50 empty] | MEC-1 | MEC-1 | MEC-1 | MEC-1 | MEC-1 | MEC-1 | MEC-1
|  | Zone 6 | Apr 23: FR-4; Apr 24: FR-4; Apr 25: FR-4; Apr 26: FR-4; Apr 27: FR-4; Apr 28: FR-4; Apr 29: FR-4; Apr 30: FR-4; May 01: FR-4; May 02: FR-4; May 03: FR-4; May 04: FR-4; May 05: FR-4; May 06: FR-4; May 07: DOOR-2; Jun 05: MG-2; Jun 08: FR-5; Jun 09: FR-5; Jun 10: DRY-1; Jun 11: DRY-1; Jun 12: DRY-1; Jun 13: DRY-1; Jun 14: DRY-1; Jun 15: DRY-1; Jun 16: DRY-1; Jun 17: DRY-1; Jun 18: DRY-1; Jun 19: PA-1; Jun 20: PA-1; Jun 21: PA-1; Jun 22: PA-1; Jun 23: PA-1; Jun 24: PA-1; Jun 25: PA-1; Jun 26: PA-2; Jun 27: PA-2; Jun 28: PA-2; Jun 29: PA-2; Jun 30: PA-2; Jul 01: PA-2; Jul 02: PA-2; Jul 06: FR-7; Jul 07: FR-7; Jul 08: FR-7; Jul 09: DRY-4; Jul 10: DRY-4; Jul 11: DRY-4; Jul 12: DRY-4; Jul 13: DRY-4; Jul 14: DRY-4; Jul 15: DRY-4; Jul 16: DRY-4; Jul 17: DRY-4; Jul 18: DRY-4; Jul 19: DRY-4; Jul 20: DRY-4; Jul 21: DRY-4; Jul 22: DRY-4; Jul 23: DRY-4; Jul 24: DRY-4; Jul 25: DRY-4; Jul 26: DRY-4; Jul 27: DRY-4; Jul 28: DRY-4; Jul 29: DRY-4; Jul 30: DRY-4; Jul 31: DRY-4; Aug 01: DRY-4; Aug 02: DRY-4; Aug 03: DRY-4; Aug 04: FL-6; Aug 05: FL-6; Aug 06: FL-6; Aug 07: FL-6; Aug 08: FL-6; Aug 09: FL-6; Aug 10: FL-6; Aug 11: FL-6; Aug 12: FL-6; Aug 13: FL-6; Aug 18: FL-4; Aug 19: FL-4; Aug 20: FL-4; Aug 21: FL-4; Aug 22: FL-4; Aug 23: FL-4; Aug 24: FL-4; Aug 25: FL-4; Aug 26: FL-4; Aug 27: FL-4; Aug 28: FL-4; Aug 29: FL-4; Aug 30: FL-4; Aug 31: FL-4; Sep 01: FL-4; Sep 02: FL-4; Sep 03: FL-4; Sep 04: FL-4; Sep 05: FL-4; Sep 06: FL-4; Sep 07: FL-4; Sep 08: FL-4; Sep 09: FL-4; Sep 10: FL-4; Sep 11: FL-4; Sep 12: FL-4; Sep 13: FL-4; Sep 14: FL-4; Sep 15: FL-4; Sep 16: FL-1; Sep 17: FL-1; Sep 18: FL-1; Sep 19: FL-1; Sep 20: FL-1; Sep 21: FL-1; Sep 22: FL-1; Oct 14: MEC-1; Oct 15: MEC-1; Oct 16: MEC-1; Oct 17: MEC-1; Oct 18: MEC-1; Oct 19: MEC-1; Oct 20: MEC-1; Nov 04: MILL-1; Nov 05: MILL-1; Nov 06: MILL-1; Nov 07: MILL-1; Nov 08: MILL-1; Nov 09: MILL-1; Nov 10: MILL-1; Nov 11: MILL-1; Nov 12: MILL-1; Nov 13: MILL-1; Nov 14: MILL-1; Nov 15: MILL-1; Nov 16: MILL-1; Nov 17: MILL-1; Nov 18: MILL-1; Nov 19: MILL-1; Nov 20: MILL-1; Nov 21: MILL-1; Nov 22: MILL-1; Nov 23: MILL-1; Nov 24: MILL-1; Nov 25: MILL-1; Nov 26: MILL-1; Nov 27: MILL-1; Nov 28: MILL-1; Nov 29: MILL-1; Nov 30: MILL-1; Dec 01: MILL-1; Dec 02: MILL-1; Dec 03: MILL-1; Dec 04: MILL-1; Dec 05: MILL-1; Dec 06: MILL-1; Dec 07: MILL-1; Dec 08: MILL-1; Dec 09: MILL-1; Dec 10: MILL-1; Dec 11: MILL-1; Dec 12: MILL-1; Dec 13: MILL-1; Dec 14: MILL-1; Dec 15: MILL-1; Dec 16: MILL-1; Dec 17: MILL-1; Dec 18: MILL-1; Dec 19: MILL-1; Dec 20: MILL-1; Dec 21: MILL-1; Dec 22: MILL-1; Dec 23: MILL-1; Dec 24: MILL-1; Dec 25: MILL-1; Dec 26: MILL-1; Dec 27: MILL-1; Dec 28: MILL-1; Dec 29: MILL-1; Dec 30: MILL-1; Dec 31: MILL-1; Jan 01: MILL-1; Jan 02: MILL-1; Jan 03: MILL-1; Jan 04: MILL-1; Jan 05: MILL-1; Jan 06: MILL-1; Jan 07: MILL-1; Jan 08: MILL-1; Jan 09: MILL-1; Jan 10: MILL-1; Jan 11: MILL-1; Jan 12: MILL-1; Jan 13: MILL-1; Jan 14: MILL-1; Jan 15: MILL-1; Jan 16: MILL-1; Jan 17: MILL-1; Jan 18: MILL-1; Jan 19: MILL-1; Jan 20: MILL-1; Jan 21: MILL-1; Jan 22: MILL-1; Jan 23: MILL-1; Jan 24: MILL-1; Jan 25: MILL-1; Jan 26: MILL-1; Jan 27: MILL-1; Jan 28: MILL-1; Jan 29: MILL-1; Jan 30: MILL-1; Jan 31: MILL-1; Feb 01: MILL-1; Feb 02: MILL-1; Feb 03: MILL-1; Feb 04: MILL-1; Feb 05: MILL-1; Feb 06: MILL-1; Feb 07: MILL-1; Feb 08: MILL-1; Feb 09: MILL-1; Feb 10: MILL-1; Feb 11: MILL-1; Feb 12: MILL-1; Feb 13: MILL-1; Feb 14: MILL-1; Feb 15: MILL-1; Feb 16: MILL-1; Feb 17: MILL-1; Feb 18: MILL-1; Feb 19: MILL-1; Feb 20: MILL-1; Feb 21: MILL-1; Feb 22: MILL-1; Feb 23: MILL-1; Feb 24: MILL-1; Feb 25: MILL-1; Feb 26: MILL-1; Feb 27: MILL-1; Feb 28: MILL-1; Mar 01: MILL-1; Mar 02: MILL-1; Mar 03: MILL-1; Mar 04: MILL-1; Mar 05: MILL-1; Mar 06: MILL-1; Mar 07: MILL-1; Mar 08: MILL-1; Mar 09: MILL-1; Mar 10: MILL-1; Mar 11: MILL-1; Mar 12: MILL-1; Mar 13: MILL-1; Mar 14: MILL-1; Mar 15: MILL-1; Mar 16: MILL-1; Mar 17: MILL-1; Mar 18: SPE-2; Mar 19: SPE-2; Mar 20: SPE-2; Mar 21: SPE-2; Mar 22: SPE-2; Mar 23: SPE-2; Mar 24: SPE-2; Mar 25: SPE-2; Mar 26: SPE-2; Mar 27: SPE-2; Mar 28: SPE-2; Mar 29: SPE-2; Mar 30: SPE-2; Mar 31: SPE-2; Apr 01: SPE-2; Apr 02: SPE-2; Apr 03: SPE-2; Apr 04: SPE-2; Apr 05: SPE-2; Apr 06: SPE-2; Apr 07: SPE-2; Apr 08: SPE-2; Apr 09: SPE-2; Apr 10: SPE-2; Apr 11: SPE-2; Apr 12: SPE-2; Apr 13: SPE-2; Apr 14: SPE-2; Apr 15: SPE-2; Apr 16: SPE-2; Apr 17: SPE-2; Apr 18: SPE-2; Apr 19: SPE-2; Apr 20: SPE-2; Apr 21: SPE-2; Apr 22: SPE-2; Apr 23: SPE-2; Apr 24: SPE-2; Apr 25: SPE-2; Apr 26: SPE-2; Apr 27: SPE-2; Apr 28: SPE-2; Apr 29: MG-1; Apr 30: MG-1; May 01: MG-1; May 02: MG-1; May 03: MG-1; May 04: MG-1; May 05: MG-1
[613 empty] | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MEP-1 | MG-5 | [13 empty] | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 | DRY-2 |  |  |  | FR-9 | FR-9 | FR-9 | FR-9 | FR-9 | [59 empty] | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | T-1 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | PLU-2 | [51 empty] | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1 | LV-1
[613 empty] | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | MEP-2 | [96 empty] | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | EL-9 | [21 empty] | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5 | FL-5
[863 empty] | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1 | DOOR-1
|  | Zone 7A | Sep 15: SPE-3; Sep 16: SPE-3; Sep 17: SPE-3; Sep 18: SPE-3; Sep 19: SPE-3; Sep 20: SPE-3; Sep 21: SPE-3; Sep 22: SPE-3; Sep 23: SPE-3; Sep 24: SPE-3; Sep 25: SPE-3; Sep 26: SPE-3; Sep 27: SPE-3; Sep 28: SPE-3; Sep 29: SPE-3; Sep 30: SPE-3; Oct 01: SPE-3; Oct 02: SPE-3; Oct 03: SPE-3; Oct 04: SPE-3; Oct 05: SPE-3; Oct 06: SPE-3; Oct 07: SPE-3; Oct 08: SPE-3; Oct 09: SPE-3; Oct 10: SPE-3; Oct 11: SPE-3; Oct 12: SPE-3; Oct 13: SPE-3; Oct 14: SPE-3; Oct 15: SPE-3; Oct 16: SPE-3; Oct 17: SPE-3; Oct 18: SPE-3; Oct 19: SPE-3; Oct 20: SPE-3; Oct 21: SPE-3; Oct 22: SPE-3; Oct 23: SPE-3; Oct 24: SPE-3; Oct 25: SPE-3; Oct 26: SPE-3; Oct 27: SPE-3; Oct 28: SPE-3; Oct 29: SPE-3; Oct 30: SPE-3; Oct 31: SPE-3; Nov 01: SPE-3; Nov 02: SPE-3; Nov 03: SPE-3; Nov 04: SPE-3; Nov 05: SPE-3; Nov 06: SPE-3; Nov 07: SPE-3; Nov 08: SPE-3; Nov 09: SPE-3; Nov 10: SPE-3; Nov 11: SPE-3; Nov 12: SPE-3; Nov 13: SPE-3; Nov 14: SPE-3; Nov 15: SPE-3; Nov 16: SPE-3; Nov 17: SPE-3; Nov 18: SPE-3; Nov 19: SPE-3; Nov 20: SPE-3; Nov 21: SPE-3; Nov 22: SPE-3; Nov 23: SPE-3; Nov 24: SPE-3; Nov 25: SPE-3; Nov 26: SPE-3; Nov 27: SPE-3; Nov 28: SPE-3; Nov 29: SPE-3; Nov 30: SPE-3; Dec 01: SPE-3; Dec 02: SPE-3; Dec 03: SPE-3; Dec 04: SPE-3; Dec 05: SPE-3; Dec 06: SPE-3; Dec 07: SPE-3; Dec 08: SPE-3; Dec 09: SPE-3; Dec 10: SPE-3; Dec 11: SPE-3; Dec 12: SPE-3; Dec 13: SPE-3; Dec 14: SPE-3; Dec 15: SPE-3; Dec 16: SPE-3; Dec 17: SPE-3; Dec 18: SPE-3; Dec 19: SPE-3; Dec 20: SPE-3; Dec 21: SPE-3; Dec 22: SPE-3; Dec 23: SPE-3; Dec 24: SPE-3; Dec 25: SPE-3; Dec 26: SPE-3; Dec 27: SPE-3; Dec 28: SPE-3; Dec 29: SPE-3; Dec 30: SPE-3; Dec 31: SPE-3; Jan 01: SPE-3; Jan 02: SPE-3; Jan 03: SPE-3; Jan 04: SPE-3; Jan 05: SPE-3; Jan 06: SPE-3; Jan 07: SPE-3; Jan 08: SPE-3; Jan 09: SPE-3; Jan 10: SPE-3; Jan 11: SPE-3; Jan 12: SPE-3; Jan 13: SPE-3; Jan 14: SPE-3; Jan 15: SPE-3; Jan 16: SPE-3; Jan 17: SPE-3; Jan 18: SPE-3; Jan 19: SPE-3; Jan 20: SPE-3; Jan 21: SPE-3; Jan 22: SPE-3; Jan 23: SPE-3; Jan 24: SPE-3; Jan 25: SPE-3; Jan 26: SPE-3
|  | Zone 7B | May 07: SPE-3; May 08: SPE-3; May 09: SPE-3; May 10: SPE-3; May 11: SPE-3; May 12: SPE-3; May 13: SPE-3; May 14: SPE-3; May 15: SPE-3; May 16: SPE-3; May 17: SPE-3; May 18: SPE-3; May 19: SPE-3; May 20: SPE-3; May 21: SPE-3; May 22: SPE-3; May 23: SPE-3; May 24: SPE-3; May 25: SPE-3; May 26: SPE-3; May 27: SPE-3; May 28: SPE-3; May 29: SPE-3; May 30: SPE-3; May 31: SPE-3; Jun 01: SPE-3; Jun 02: SPE-3; Jun 03: SPE-3; Jun 04: SPE-3; Jun 05: SPE-3; Jun 06: SPE-3; Jun 07: SPE-3; Jun 08: SPE-3; Jun 09: SPE-3; Jun 10: SPE-3; Jun 11: SPE-3; Jun 12: SPE-3; Jun 13: SPE-3; Jun 14: SPE-3; Jun 15: SPE-3; Jun 16: SPE-3; Jun 17: SPE-3; Jun 18: SPE-3; Jun 19: SPE-3; Jun 20: SPE-3; Jun 21: SPE-3; Jun 22: SPE-3; Jun 23: SPE-3; Jun 24: SPE-3; Jun 25: SPE-3; Jun 26: SPE-3; Jun 27: SPE-3; Jun 28: SPE-3; Jun 29: SPE-3; Jun 30: SPE-3; Jul 01: SPE-3; Jul 02: SPE-3; Jul 03: SPE-3; Jul 04: SPE-3; Jul 05: SPE-3; Jul 06: SPE-3; Jul 07: SPE-3; Jul 08: SPE-3; Jul 09: SPE-3; Jul 10: SPE-3; Jul 11: SPE-3; Jul 12: SPE-3; Jul 13: SPE-3; Jul 14: SPE-3; Jul 15: SPE-3; Jul 16: SPE-3; Jul 17: SPE-3; Jul 18: SPE-3; Jul 19: SPE-3; Jul 20: SPE-3; Jul 21: SPE-3; Jul 22: SPE-3; Jul 23: SPE-3; Jul 24: SPE-3; Jul 25: SPE-3; Jul 26: SPE-3; Jul 27: SPE-3; Jul 28: SPE-3; Jul 29: SPE-3; Jul 30: SPE-3; Jul 31: SPE-3; Aug 01: SPE-3; Aug 02: SPE-3; Aug 03: SPE-3; Aug 04: SPE-3; Aug 05: SPE-3; Aug 06: SPE-3; Aug 07: SPE-3; Aug 08: SPE-3; Aug 09: SPE-3; Aug 10: SPE-3; Aug 11: SPE-3; Aug 12: SPE-3; Aug 13: SPE-3; Aug 14: SPE-3; Aug 15: SPE-3; Aug 16: SPE-3; Aug 17: SPE-3; Aug 18: SPE-3; Aug 19: SPE-3; Aug 20: SPE-3; Aug 21: SPE-3; Aug 22: SPE-3; Aug 23: SPE-3; Aug 24: SPE-3; Aug 25: SPE-3; Aug 26: SPE-3; Aug 27: SPE-3; Aug 28: SPE-3; Aug 29: SPE-3; Aug 30: SPE-3; Aug 31: SPE-3; Sep 01: SPE-3; Sep 02: SPE-3; Sep 03: SPE-3; Sep 04: SPE-3; Sep 05: SPE-3; Sep 06: SPE-3; Sep 07: SPE-3; Sep 08: SPE-3; Sep 09: SPE-3; Sep 10: SPE-3; Sep 11: SPE-3; Sep 12: SPE-3; Sep 13: SPE-3; Sep 14: SPE-3
Exteriors | Building Envelope | North Elevation | Mar 25: FR-3; Mar 26: FR-3; Mar 27: FR-3; Mar 28: FR-3; Mar 29: FR-3; Mar 30: FR-3; Mar 31: FR-3; Apr 01: FR-3; Apr 02: FR-3; Apr 03: FR-3; Apr 04: FR-3; Apr 05: FR-3; Apr 06: FR-3; Apr 07: FR-3; Apr 08: FR-3; Apr 09: FR-3; Apr 10: FR-3; Apr 11: FR-3; Apr 12: FR-3; Apr 13: FR-3; Apr 14: FR-3; Apr 15: FR-3; Apr 16: FR-3; Apr 17: FR-3; Apr 18: FR-3; Apr 19: FR-3; Apr 20: FR-3; Apr 21: FR-3; Apr 22: FR-3; Apr 23: WP-1; Apr 24: WP-1; Apr 25: WP-1; Apr 26: WP-1; Apr 27: WP-1; Apr 28: WP-1; Apr 29: WP-1; Apr 30: CLA-2; May 01: CLA-2; May 02: CLA-2; May 03: CLA-2; May 04: CLA-2; May 05: CLA-2; May 06: CLA-2; May 07: CLA-2; May 08: CLA-2; May 09: CLA-2; May 10: CLA-2; May 11: CLA-2; May 12: CLA-2; May 13: CLA-2; May 14: CLA-2; May 15: CLA-2; May 16: CLA-2; May 17: CLA-2; May 18: CLA-2; May 19: CLA-2; May 20: CLA-2; May 21: WP-1; May 22: WP-1; May 23: WP-1; May 24: WP-1; May 25: WP-1; May 26: WP-1; May 27: WP-1; May 28: WP-1; May 29: GLA-1; May 30: GLA-1; May 31: GLA-1; Jun 01: GLA-1; Jun 02: GLA-1; Jun 03: GLA-1; Jun 04: GLA-1; Jun 05: GLA-1; Jun 06: GLA-1; Jun 07: GLA-1; Jun 08: GLA-1; Jun 09: GLA-1; Jun 10: GLA-1; Jun 11: GLA-1; Jun 12: CLA-1; Jun 13: CLA-1; Jun 14: CLA-1; Jun 15: CLA-1; Jun 16: CLA-1; Jun 17: CLA-1; Jun 18: CLA-1; Jun 19: CLA-1; Jun 20: CLA-1; Jun 21: CLA-1; Jun 22: CLA-1; Jun 23: CLA-1; Jun 24: CLA-1; Jun 25: CLA-1; Jun 26: CLA-1; Jun 27: CLA-1; Jun 28: CLA-1; Jun 29: CLA-1; Jun 30: CLA-1; Jul 01: CLA-1; Jul 02: CLA-1; Jul 06: GLA-2; Jul 07: GLA-2; Jul 08: GLA-2; Jul 09: GLA-2; Jul 10: GLA-2; Jul 11: GLA-2; Jul 12: GLA-2; Jul 13: GLA-2; Jul 14: GLA-2; Jul 15: GLA-2; Jul 16: GLA-2; Jul 17: GLA-2; Jul 18: GLA-2; Jul 19: GLA-2; Jul 20: GLA-2; Jul 21: GLA-2; Jul 22: GLA-2; Jul 23: GLA-2; Jul 24: GLA-2; Jul 25: GLA-2; Jul 26: GLA-2; Jul 27: GLA-2; Jul 28: GLA-2; Jul 29: GLA-2; Jul 30: GLA-2; Jul 31: GLA-2; Aug 03: GLA-2; Aug 04: GLA-2; Aug 05: GLA-2; Aug 06: GLA-2; Aug 07: GLA-2; Aug 08: GLA-2; Aug 09: GLA-2; Aug 10: GLA-2; Aug 11: GLA-2; Aug 12: GLA-2; Aug 13: GLA-2; Aug 14: GLA-2; Aug 15: GLA-2; Aug 16: GLA-2; Aug 17: GLA-2; Aug 18: GLA-2; Aug 19: GLA-2; Aug 20: GLA-2; Aug 21: GLA-2; Aug 22: GLA-2; Aug 23: GLA-2; Aug 24: GLA-2; Aug 25: GLA-2; Aug 26: GLA-2; Aug 27: GLA-2; Aug 28: GLA-2; Sep 22: MIS-1; Sep 23: MIS-1; Sep 24: MIS-1; Sep 25: MIS-1; Sep 26: MIS-1; Sep 27: MIS-1; Sep 28: MIS-1; Sep 29: MIS-1; Sep 30: MIS-1; Oct 01: MIS-1; Oct 02: MIS-1; Oct 03: MIS-1; Oct 04: MIS-1; Oct 05: MIS-1; Oct 06: MIS-1; Oct 07: MIS-1; Oct 08: MIS-1; Oct 09: MIS-1; Oct 10: MIS-1; Oct 11: MIS-1; Oct 12: MIS-1; Oct 13: MIS-1; Oct 14: MIS-1; Oct 15: MIS-1; Oct 16: MIS-1; Oct 17: MIS-1; Oct 18: MIS-1; Oct 19: MIS-1; Oct 20: MIS-1; Oct 21: MIS-1; Oct 22: MIS-1; Oct 23: MIS-1; Oct 24: MIS-1; Oct 25: MIS-1; Oct 26: MIS-1
[585 empty] | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | WP-1 | WP-1 | WP-1 | WP-1 | WP-1 | WP-1 | WP-1 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | CLA-3 | WP-1 | WP-1 | WP-1 | WP-1 | WP-1 | WP-1 | WP-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1 | ROOF-1
[599 empty] | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 |  |  |  | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | [16 empty] | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1
[613 empty] | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | FR-3 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | MAS-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2
[635 empty] | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | MAS-1 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2 | GLA-2
[680 empty] | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1 | MIS-1
Commissioning | Commissioning | Commissioning | May 28: CX-2; May 29: CX-2; May 30: CX-2; May 31: CX-2; Jun 01: CX-2; Jun 02: CX-2; Jun 03: CX-2; Jun 04: CX-2; Jun 05: CX-2; Jun 06: CX-2; Jun 07: CX-2; Jun 08: CX-2; Jun 09: CX-2; Jun 10: CX-2; Jun 11: CX-2; Jun 12: CX-2; Jun 13: CX-2; Jun 14: CX-2; Jun 15: CX-2; Jun 16: CX-2; Jun 17: CX-2; Jun 18: CX-2; Jun 19: CX-2; Jun 20: CX-2; Jun 21: CX-2; Jun 22: CX-2; Jun 23: CX-2; Jun 24: CX-2; Jun 25: CX-2; Jun 26: CX-2; Jun 27: CX-2; Jun 28: CX-2; Jun 29: CX-2; Jun 30: CX-2; Jul 01: CX-2; Jul 02: CX-2; Jul 03: CX-2; Jul 04: CX-2; Jul 05: CX-2; Jul 06: CX-2; Jul 07: CX-2; Jul 08: CX-2; Jul 09: CX-2; Jul 10: CX-2; Jul 11: CX-2; Jul 12: CX-2; Jul 13: CX-2; Jul 14: CX-2; Jul 15: CX-2; Jul 16: CX-2; Jul 17: CX-2; Jul 18: CX-2; Jul 19: CX-2; Jul 20: CX-2; Jul 21: CX-2; Jul 22: CX-2; Jul 23: CX-2; Jul 24: CX-2; Jul 25: CX-2; Jul 26: CX-2; Jul 27: CX-2; Jul 28: CX-2; Jul 29: CX-2; Jul 30: CX-2; Jul 31: CX-2; Aug 01: CX-2; Aug 02: CX-2; Aug 03: CX-2; Aug 04: CX-2; Aug 05: CX-2; Aug 06: CX-2; Aug 07: CX-2; Aug 08: CX-2; Aug 09: CX-2; Aug 10: CX-2; Aug 11: CX-2; Aug 12: CX-2; Aug 13: CX-2; Aug 14: CX-2; Aug 15: CX-2; Aug 16: CX-2; Aug 17: CX-2; Aug 18: CX-2; Aug 19: CX-2; Aug 20: CX-2; Aug 21: CX-2; Aug 22: CX-2; Aug 23: CX-2; Aug 24: CX-2; Aug 25: CX-2; Aug 26: CX-2; Aug 27: CX-2; Aug 28: CX-2; Aug 29: CX-2; Aug 30: CX-2; Aug 31: CX-2; Sep 01: CX-2; Sep 02: CX-2; Sep 03: CX-2; Sep 04: CX-2; Sep 05: CX-2; Sep 06: CX-2; Sep 07: CX-2; Sep 08: CX-2; Sep 09: CX-2; Sep 10: CX-2; Sep 11: CX-2; Sep 12: CX-2; Sep 13: CX-2; Sep 14: CX-2; Sep 15: CX-2; Sep 16: CX-2; Sep 17: CX-2; Sep 18: CX-2; Sep 19: CX-2; Sep 20: CX-2; Sep 21: CX-2; Sep 22: CX-2; Sep 23: CX-2; Sep 24: CX-2; Sep 25: CX-2; Sep 26: CX-2; Sep 27: CX-2; Sep 28: CX-2; Sep 29: CX-2; Sep 30: CX-2; Oct 01: CX-2; Oct 02: CX-2; Oct 03: CX-2; Oct 04: CX-2; Oct 05: CX-2; Oct 06: CX-2; Oct 07: CX-2; Oct 08: CX-2; Oct 09: CX-2; Oct 10: CX-2; Oct 11: CX-2; Oct 12: CX-2; Oct 13: CX-2; Oct 14: CX-2; Oct 15: CX-2; Oct 16: CX-2; Oct 17: CX-2; Oct 18: CX-2; Oct 19: CX-2
| Testing | Testing | Dec 18: FA-1; Dec 19: FA-1; Dec 20: FA-1; Dec 21: FA-1; Dec 22: FA-1; Dec 23: FA-1; Dec 24: FA-1; Dec 25: FA-1; Dec 26: FA-1; Dec 27: FA-1; Dec 28: FA-1; Dec 29: FA-1; Dec 30: FA-1; Dec 31: FA-1; Jan 01: FA-1; Jan 02: FA-1; Jan 03: FA-1; Jan 04: FA-1; Jan 05: FA-1; Jan 06: FA-1; Jan 07: FA-1; Jan 08: FA-1; Jan 09: FA-1; Jan 10: FA-1; Jan 11: FA-1; Jan 12: FA-1; Jan 13: FA-1; Jan 14: FA-1; Jan 15: FA-1; Jan 16: FA-1; Jan 17: FA-1; Jan 18: FA-1; Jan 19: FA-1; Jan 20: FA-1; Jan 21: FA-1; Jan 22: FA-1; Jan 23: FA-1; Jan 24: FA-1; Jan 25: FA-1; Jan 26: FA-1; Jan 27: FA-1; Jan 28: FA-1; Jan 29: FA-1; Jan 30: FA-1; Jan 31: FA-1; Feb 01: FA-1; Feb 02: FA-1; Feb 03: FA-1; Feb 04: FA-1; Feb 05: FA-1; Feb 06: FA-1; Feb 07: FA-1; Feb 08: FA-1; Feb 09: FA-1; Feb 10: FA-1; Feb 11: FA-1; Feb 12: FA-1; Feb 13: FA-1; Feb 14: FA-1; Feb 15: FA-1; Feb 16: FA-1; Feb 17: FA-1; Feb 18: FA-1; Feb 19: FA-1; Feb 20: FA-1; Feb 21: FA-1; Feb 22: FA-1; Feb 23: FA-1; Feb 24: FA-1; Feb 25: FA-1; Feb 26: FA-1; Feb 27: FA-1; Feb 28: FA-1; Mar 01: FA-1; Mar 02: FA-1; Mar 03: FA-1; Mar 04: FA-1; Mar 05: FA-1; Mar 06: FA-1; Mar 07: FA-1; Mar 08: FA-1; Mar 09: FA-1; Mar 10: FA-1; Mar 11: FA-1; Mar 12: FA-1; Mar 13: FA-1; Mar 14: FA-1; Mar 15: FA-1; Mar 16: FA-1; Mar 17: FA-1; Mar 18: FA-1; Sep 15: MEC-6; Sep 16: MEC-6; Sep 17: MEC-6; Sep 18: MEC-6; Sep 19: MEC-6; Sep 20: MEC-6; Sep 21: MEC-6; Sep 22: MEC-6; Sep 23: MEC-6; Sep 24: MEC-6; Sep 25: MEC-6; Sep 26: MEC-6; Sep 27: MEC-6; Sep 28: MEC-6; Sep 29: MEC-6; Sep 30: MEC-6; Oct 01: MEC-6; Oct 02: MEC-6; Oct 03: MEC-6; Oct 04: MEC-6; Oct 05: MEC-6; Oct 06: MEC-6; Oct 07: MEC-6; Oct 08: MEC-6; Oct 09: MEC-6; Oct 10: MEC-6; Oct 11: MEC-6; Oct 12: MEC-6; Oct 13: MEC-6; Oct 14: MEC-6; Oct 15: MEC-6; Oct 16: MEC-6; Oct 17: MEC-6; Oct 18: MEC-6; Oct 19: MEC-6; Oct 20: MEC-6; Oct 21: MEC-6; Oct 22: MEC-6; Oct 23: MEC-6; Oct 24: MEC-6; Oct 25: MEC-6; Oct 26: MEC-6; Oct 27: MEC-6; Oct 28: MEC-6; Oct 29: MEC-6; Oct 30: MEC-6; Oct 31: MEC-6; Nov 01: MEC-6; Nov 02: MEC-6; Nov 03: MEC-6; Nov 04: MEC-6; Nov 05: MEC-6; Nov 06: MEC-6; Nov 07: MEC-6; Nov 08: MEC-6; Nov 09: MEC-6; Nov 10: MEC-6; Nov 11: MEC-6; Nov 12: MEC-6; Nov 13: MEC-6; Nov 14: MEC-6; Nov 15: MEC-6; Nov 16: MEC-6; Nov 17: MEC-6; Nov 18: MEC-6; Nov 19: MEC-6; Nov 20: MEC-6; Nov 21: MEC-6; Nov 22: MEC-6; Nov 23: MEC-6; Nov 24: MEC-6; Nov 25: MEC-6; Nov 26: MEC-6; Nov 27: MEC-6; Nov 28: MEC-6; Nov 29: MEC-6; Nov 30: MEC-6; Dec 01: MEC-6; Dec 02: MEC-6; Dec 03: MEC-6; Dec 04: MEC-6; Dec 05: MEC-6; Dec 06: MEC-6; Dec 07: MEC-6; Dec 08: MEC-6; Dec 09: MEC-6; Dec 10: MEC-6; Dec 11: MEC-6; Dec 12: MEC-6; Dec 13: MEC-6; Dec 14: MEC-6; Dec 15: MEC-6; Dec 16: MEC-6; Dec 17: MEC-6; Dec 18: MEC-6; Dec 19: MEC-6; Dec 20: MEC-6; Dec 21: MEC-6; Dec 22: MEC-6; Dec 23: MEC-6; Dec 24: MEC-6; Dec 25: MEC-6; Dec 26: MEC-6; Dec 27: MEC-6; Dec 28: MEC-6; Dec 29: MEC-6; Dec 30: MEC-6; Dec 31: MEC-6; Jan 01: MEC-6; Jan 02: MEC-6; Jan 03: MEC-6; Jan 04: MEC-6; Jan 05: MEC-6; Jan 06: MEC-6; Jan 07: MEC-6; Jan 08: MEC-6; Jan 09: MEC-6; Jan 10: MEC-6; Jan 11: MEC-6; Jan 12: MEC-6; Jan 13: MEC-6; Jan 14: MEC-6; Jan 15: MEC-6; Jan 16: MEC-6; Jan 17: MEC-6; Jan 18: MEC-6; Jan 19: MEC-6; Jan 20: MEC-6; Jan 21: MEC-6; Jan 22: MEC-6; Jan 23: MEC-6; Jan 24: MEC-6; Jan 25: MEC-6; Jan 26: MEC-6; Jan 27: MEC-6; Jan 28: MEC-6; Jan 29: MEC-6; Jan 30: MEC-6; Jan 31: MEC-6; Feb 01: MEC-6; Feb 02: MEC-6; Feb 03: MEC-6; Feb 04: MEC-6; Feb 05: MEC-6; Feb 06: MEC-6; Feb 07: MEC-6; Feb 08: MEC-6; Feb 09: MEC-6; Feb 10: MEC-6; Feb 11: MEC-6; Feb 12: MEC-6; Feb 13: MEC-6; Feb 14: MEC-6; Feb 15: MEC-6; Feb 16: MEC-6; Feb 17: MEC-6; Feb 18: MEC-6; Feb 19: MEC-6; Feb 20: MEC-6; Feb 21: MEC-6; Feb 22: MEC-6; Feb 23: MEC-6; Feb 24: MEC-6; Feb 25: MEC-6; Feb 26: MEC-6; Feb 27: MEC-6; Feb 28: MEC-6; Mar 01: MEC-6; Mar 02: MEC-6; Mar 03: MEC-6; Mar 04: MEC-6; Mar 05: MEC-6; Mar 06: MEC-6; Mar 07: MEC-6; Mar 08: MEC-6; Mar 09: MEC-6; Apr 16: CX-1; Apr 17: CX-1; Apr 18: CX-1; Apr 19: CX-1; Apr 20: CX-1; Apr 21: CX-1; Apr 22: CX-1; Apr 23: CX-1; Apr 24: CX-1; Apr 25: CX-1; Apr 26: CX-1; Apr 27: CX-1; Apr 28: CX-1; Apr 29: CX-1; Apr 30: CX-1; May 01: CX-1; May 02: CX-1; May 03: CX-1; May 04: CX-1; May 05: CX-1; May 06: CX-1; May 07: CX-1; May 08: CX-1; May 09: CX-1; May 10: CX-1; May 11: CX-1; May 12: CX-1; May 13: CX-1; May 14: CX-1; May 15: CX-1; May 16: CX-1; May 17: CX-1; May 18: CX-1; May 19: CX-1; May 20: CX-1; May 21: CX-1; May 22: CX-1; May 23: CX-1; May 24: CX-1; May 25: CX-1; May 26: CX-1; May 27: CX-1; May 28: CX-1; May 29: CX-1; May 30: CX-1; May 31: CX-1; Jun 01: CX-1; Jun 02: CX-1; Jun 03: CX-1; Jun 04: CX-1; Jun 05: CX-1; Jun 06: CX-1; Jun 07: CX-1; Jun 08: CX-1; Jun 09: CX-1; Jun 10: CX-1; Jun 11: CX-1; Jun 12: CX-1; Jun 13: CX-1; Jun 14: CX-1; Jun 15: CX-1; Jun 16: CX-1; Jun 17: CX-1; Jun 18: CX-1; Jun 19: CX-1; Jun 20: CX-1; Jun 21: CX-1; Jun 22: CX-1; Jun 23: CX-1; Jun 24: CX-1; Jun 25: CX-1; Jun 26: CX-1; Jun 27: CX-1; Jun 28: CX-1; Jun 29: CX-1; Jun 30: CX-1; Jul 01: CX-1; Jul 02: CX-1; Jul 03: CX-1; Jul 04: CX-1; Jul 05: CX-1; Jul 06: CX-1; Jul 07: CX-1; Jul 08: CX-1; Jul 09: CX-1; Jul 10: CX-1; Jul 11: CX-1; Jul 12: CX-1
[957 empty] | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2 | LV-2
[977 empty] | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1 | OW-1
Landscape | Hardscape | All | Jul 06: LAN-1; Jul 07: LAN-1; Jul 08: LAN-1; Jul 09: LAN-1; Jul 10: LAN-1; Jul 11: LAN-1; Jul 12: LAN-1; Jul 13: LAN-1; Jul 14: LAN-1; Jul 15: LAN-1; Jul 16: LAN-1; Jul 17: LAN-1; Jul 18: LAN-1; Jul 19: LAN-1; Jul 20: LAN-1; Jul 21: LAN-1; Jul 22: LAN-1; Jul 23: LAN-1; Jul 24: LAN-1; Jul 25: LAN-1; Jul 26: LAN-1; Jul 27: LAN-1; Jul 28: LAN-1; Jul 29: LAN-1; Jul 30: LAN-1; Jul 31: LAN-1; Aug 01: LAN-1; Aug 02: LAN-1; Aug 03: LAN-1; Aug 04: LAN-1; Aug 05: LAN-1; Aug 06: LAN-1; Aug 07: LAN-1; Aug 08: LAN-1; Aug 09: LAN-1; Aug 10: LAN-1; Aug 11: LAN-1; Aug 12: LAN-1; Aug 13: LAN-1; Aug 14: LAN-1; Aug 15: LAN-1; Aug 16: LAN-1; Aug 17: LAN-1; Aug 18: LAN-1; Aug 19: LAN-1; Aug 20: LAN-1; Aug 21: LAN-1; Aug 22: LAN-1; Aug 23: LAN-1; Aug 24: LAN-1; Aug 25: LAN-1; Aug 26: LAN-1; Aug 27: LAN-1; Aug 28: LAN-1; Aug 29: LAN-1; Aug 30: LAN-1; Aug 31: LAN-1; Sep 01: LAN-1; Sep 02: LAN-1; Sep 03: LAN-1; Sep 04: LAN-1; Sep 05: LAN-1; Sep 06: LAN-1; Sep 07: LAN-1; Sep 08: LAN-1; Sep 09: LAN-1; Sep 10: LAN-1; Sep 11: LAN-1; Sep 12: LAN-1; Sep 13: LAN-1; Sep 14: LAN-1; Sep 15: LAN-1; Sep 16: LAN-1; Sep 17: LAN-1; Sep 18: LAN-1; Sep 19: LAN-1; Sep 20: LAN-1; Sep 21: LAN-1; Sep 22: LAN-1; Sep 23: LAN-1; Sep 24: LAN-1; Sep 25: LAN-1; Sep 26: LAN-1; Sep 27: LAN-1; Sep 28: LAN-1; Sep 29: LAN-1; Sep 30: LAN-1; Oct 01: LAN-1; Oct 02: LAN-1; Oct 03: LAN-1; Oct 04: LAN-1; Oct 05: LAN-1; Oct 06: LAN-1; Oct 07: LAN-1; Oct 08: LAN-1; Oct 09: LAN-1; Oct 10: LAN-1; Oct 11: LAN-1; Oct 12: LAN-1; Oct 13: LAN-1; Oct 14: LAN-1; Oct 15: LAN-1; Oct 16: LAN-1; Oct 17: LAN-1; Oct 18: LAN-1; Oct 19: LAN-1; Oct 20: LAN-1; Oct 21: LAN-1; Oct 22: LAN-1; Oct 23: LAN-1; Oct 24: LAN-1; Oct 25: LAN-1; Oct 26: LAN-1; Oct 27: LAN-1; Oct 28: LAN-1; Oct 29: LAN-1; Oct 30: LAN-1; Oct 31: LAN-1; Nov 01: LAN-1; Nov 02: LAN-1; Nov 03: LAN-1; Nov 04: LAN-1; Nov 05: LAN-1; Nov 06: LAN-1; Nov 07: LAN-1; Nov 08: LAN-1; Nov 09: LAN-1; Nov 10: LAN-1; Nov 11: LAN-1; Nov 12: LAN-1; Nov 13: LAN-1; Nov 14: LAN-1; Nov 15: LAN-1; Nov 16: LAN-1; Nov 17: LAN-1; Nov 18: LAN-1; Nov 19: LAN-1; Nov 20: LAN-1; Nov 21: LAN-1; Nov 22: LAN-1; Nov 23: LAN-1; Nov 24: LAN-1; Nov 25: LAN-1; Nov 26: LAN-1; Nov 27: LAN-1; Nov 28: LAN-1; Nov 29: LAN-1; Nov 30: LAN-1; Dec 01: LAN-1; Dec 02: LAN-1; Dec 03: LAN-1; Dec 04: LAN-1; Dec 05: LAN-1; Dec 06: LAN-1; Dec 07: LAN-1; Dec 08: LAN-1; Dec 09: LAN-1; Dec 10: LAN-1; Dec 11: LAN-1; Dec 12: LAN-1; Dec 13: LAN-1; Dec 14: LAN-1; Dec 15: LAN-1; Dec 16: LAN-1; Dec 17: LAN-1; Dec 18: LAN-1; Dec 19: LAN-1; Dec 20: LAN-1; Dec 21: LAN-1; Dec 22: LAN-1; Dec 23: LAN-1
Weather Days | Weather | Weather | bar: Sep 25 to Jan 04
Punchlist | FF&E | FF&E | Jan 27: MG-7; Jan 28: MG-7; Jan 29: MG-7; Jan 30: MG-7; Jan 31: MG-7; Feb 01: MG-7; Feb 02: MG-7; Feb 03: MG-7; Feb 04: MG-7; Feb 05: MG-7; Feb 06: MG-7; Feb 07: MG-7; Feb 08: MG-7; Feb 09: MG-7; Feb 10: MG-7; Feb 11: MG-7; Feb 12: MG-7; Feb 13: MG-7; Feb 14: MG-7; Feb 15: MG-7; Feb 16: MG-7; Feb 17: MG-7; Feb 18: MG-7; Feb 19: MG-7; Feb 20: MG-7; Feb 21: MG-7; Feb 22: MG-7; Feb 23: MG-7; Feb 24: MG-7; Feb 25: MG-7; Feb 26: MG-7; Feb 27: MG-7; Feb 28: MG-7; Mar 01: MG-7; Mar 02: MG-7; Mar 03: MG-7; Mar 04: MG-7; Mar 05: MG-7; Mar 06: MG-7; Mar 07: MG-7; Mar 08: MG-7; Mar 09: MG-7; Mar 10: MG-7; Mar 11: MG-7; Mar 12: MG-7; Mar 13: MG-7; Mar 14: MG-7; Mar 15: MG-7; Mar 16: MG-7; Mar 17: MG-7; Mar 18: MG-7; Mar 19: MG-7; Mar 20: MG-7; Mar 21: MG-7; Mar 22: MG-7; Mar 23: MG-7; Mar 24: MG-7; Mar 25: MG-7; Mar 26: MG-7; Mar 27: MG-7; Mar 28: MG-7; Mar 29: MG-7; Mar 30: MG-7
| Punchlist | Punchlist | Mar 25: PUN-1; Mar 26: PUN-1; Mar 27: PUN-1; Mar 28: PUN-1; Mar 29: PUN-1; Mar 30: PUN-1; Mar 31: PUN-1; Apr 01: PUN-1; Apr 02: PUN-1; Apr 03: PUN-1; Apr 04: PUN-1; Apr 05: PUN-1; Apr 06: PUN-1; Apr 07: PUN-1; Apr 08: PUN-1; Apr 09: PUN-1; Apr 10: PUN-1; Apr 11: PUN-1; Apr 12: PUN-1; Apr 13: PUN-1; Apr 14: PUN-1; Apr 15: PUN-1; Apr 16: PUN-1; Apr 17: PUN-1; Apr 18: PUN-1; Apr 19: PUN-1; Apr 20: PUN-1; Apr 21: PUN-1; Apr 22: PUN-1; Apr 23: PUN-1; Apr 24: PUN-1; Apr 25: PUN-1; Apr 26: PUN-1; Apr 27: PUN-1; Apr 28: PUN-1; Apr 29: PUN-1; Apr 30: PUN-1; May 01: PUN-1; May 02: PUN-1; May 03: PUN-1; May 04: PUN-1; May 05: PUN-1

## CFA - Legends
Commissioning |  | Exteriors |  | Foundations |  | Interiors |  | Landscape |  | Milestone |  | Permits |  | Procurement |  | Punchlist |  | Sitework |  | Submittals |  | Utilities |  | Weather Days
Commissioning |  | North Elevation |  | Deep Structural |  | Kitchen |  | All |  | Building |  | Permits |  | Contracts |  | FF&E |  | All |  | Product Data |  | All |  | Weather
CX-2 | Commissioning All Systems | CLA-1 | Exterior Metal Panels - West Elevation | PI-1 | Install Piers (24') - Zone 1 | SPE-1 | Install Kitchen Equipment | LAN-1 | Hardscape/Landscaping | M-1 | DD 1 Safety & Risk Assessment | PER-1 | Permitting - TXDot | PRO-13 | Issue Contract to Structural Steel Sub | MG-7 | FF&E | CON-1 | Site Paving | SUB-14 | Owner Approve Curtainwall Product Data | UT-1 | Excavate, Install & Backfill 8" Water Line From Peach Ave | WD | Weather Days (3 days per month)
|  | CLA-2 | Exterior Metal Panels - South Elevation | PI-2 | Install Pile Caps (30) - All Zones |  |  |  |  | M-10 | SWPPP |  |  | PRO-14 | Issue Contract to Store Fronts Sub |  |  | SITE-1 | Backfill Select Fill - Building Pad | SUB-15 | Owner Approve Store Front Product Data | UT-2 | Install 8" Waste Water From Peach Ave
Testing |  | CLA-3 | Exterior Metal Panels - East Elevation |  |  | Mechanical Room |  |  |  | M-11 | Substantial Completion |  |  | PRO-15 | Issue Contract to Security Glazing Sub | Punchlist |  | SITE-3 | Excavate - Building Pad | SUB-16 | Owner Approve Security Glazing Product Data | UT-3 | Install Electric Utility Trench (Proposed) (Includes Excavate, Backfill, & Flowable Fill)
CX-1 | Testing All Systems | FR-3 | Exterior Framing - East Elevation | Grade Beams |  | CON-13 | Install Housekeeping Pads - Zone 1 Mechanical Room |  |  | M-2 | DD 2 |  |  | PRO-16 | Issue Contract to Overhead Door Sub | PUN-1 | Project Punchlist |  |  | SUB-17 | Owner Approve Steel Structure Product Data | UT-4 | Install Fiber Line (Includes Trenching)
FA-1 | Fire Alarm Testing | GLA-1 | Curatinwall - North Elevation | CON-2 | F/R/P Grade Beams - East (Zones 1 & 3) | EL-4 | Install Electrical Switchgear - Zone 1 Mechanical Room |  |  | M-3 | DD 3 |  |  | PRO-17 | Issue Contract to Mechanical Sub |  |  | Clear & Grub |  | SUB-18 | Owner Approve Overhead Door Product Data
LV-2 | Security/Access Controls Testing (Cameras, Badge Readers, Panic Buttons, etc.) | GLA-2 | Store Front/Glass/Glazing - North Elevation | CON-3 | F/R/P Grade Beams - South (Zones 1, 2 & 6) | EL-5 | Install ATS - Zone 1 Mechanical Room |  |  | M-4 | Architect - DD 4 |  |  | PRO-18 | Issue Contract to Kitchen Equipment Sub |  |  | SITE-2 | Clear & Grub - Building Foot Print | SUB-19 | Owner Approve Chiller Product Data
MEC-6 | Test & Balance | MAS-1 | Masonry - North Elevation | CON-4 | F/R/P Grade Beams - West (Zones 5 & 6) | MEC-1 | Install Boilers - Zone 1 Mechanical Room |  |  | M-5 | DD Package Submission Owner & Cost Estimator |  |  | PRO-19 | Issue Contract to Electrical Sub |  |  |  |  | SUB-20 | Owner Approve AHU Product Data
OW-1 | Owner Test & Balance | MAS-2 | Exterior Masonry - West Elevation | CON-5 | F/R/P Grade Beams - North (Zones 3, 4 & 5) | MEC-5 | Set/Install VFD's - Zone 1 Mechanical Room |  |  | M-6 | Early Site Utility, Grading, Foundation Package & Underfloor MEP |  |  | PRO-20 | Issue Contract to Curtainwall Sub |  |  | Playa Lake |  | SUB-21 | Owner Approve Generator Product Data
|  | MIS-1 | Install Screenwall - Zone 2 | CON-6 | F/R/P Internal Grade Beams | PLU-1 | Set/Install HWP (3) - Zone 1 Mechanical Room |  |  | M-7 | Start CD Package |  |  | PRO-21 | Issue Contract to Civil Sub |  |  | SITE-10 | Install Manholes (3) - Playa Lake East | SUB-22 | Owner Approve Kitchen Equipment Product Data
|  | ROOF-1 | Install Roofing - All Zones | [6 empty] | M-8 | Review of Early Site Utility, Grading, Foundation Package & Underfloor MEP for Contracts |  |  | PRO-22 | Issue Contract to Antiligature Door Hardware/Kingsway Kits Sub |  |  | SITE-4 | Excavate - Playa Lake West | SUB-23 | Owner Approve Electrical Switchgear Product Data
|  | WP-1 | Exterior Weatherproof - North Elevation | Mechanical Yard |  | Zone 1 |  |  |  | M-9 | Review of CD to Issue Contracts | [6 empty] | SITE-6 | Grade Slopes - Playa Lake West | SUB-24 | Owner Approve ATS Product Data
|  |  |  | ELPL-2 | Underground MEP - Mechanical Yard | CON-14 | F/R/P Concrete Pads - Mechanical Yard |  |  | MG-3 | Mobilization |  |  | Material | [5 empty] | SUB-25 | Owner Approve Boilers Product Data
[6 empty] | CON-15 | Cure Concrete Pads - Mechanical Yard |  |  | MG-6 | GMP Issued |  |  | DOOR-3 | Procure & Fabricate Antiligature Door Hardware/Kingsway Kits |  |  | Playa Lake East |  | SUB-26 | Owner Approve Antiligature Door Hardware/Kingsway Kits Product Data
|  |  |  | Zone 1 |  | CON-16 | F/R/P Concrete Pad Sally Port - Mechanical Yard |  |  | MG-8 | DD GMP Pricing Completion |  |  | EL-1 | Procure & Fabricate Generator |  |  | SITE-11 | Install Precast Discharge w/Rip Rap - Playa Lake East | SUB-28 | Submit Store Front Product Data
|  |  |  | CON-7 | F/R/P Slab on Grade - Zone 1 | CON-17 | Cure Concrete Pad Sally Port - Mechanical Yard |  |  | MG-9 | Cost Reconciliation |  |  | EL-2 | Procure & Fabricate Electrical Switchgear |  |  | SITE-12 | Regrade Slopes - Playa Lake East | SUB-30 | Submit Steel Structure Product Data
|  |  |  | ELPL-1 | Under Slab MEP - Zone 1 | DOOR-1 | Install Doors & Hardware - Zone 1 |  |  | OW-3 | Issue Complete CD Package |  |  | EL-3 | Procure & Fabricate ATS |  |  | SITE-5 | Expand (Excavate) Existing Slopes - Playa Lake East | SUB-32 | Submit Security Glazing Product Data
[6 empty] | DRY-1 | Two Side Walls - Zone 1 |  |  | OW-4 | DD Final Page Turn & Owner Sign-off |  |  | OW-2 | Procure Transformer (by others) |  |  | SITE-7 | Install 12" HDPE Pipe - Playa Lake East | SUB-34 | Submit Overhead Door Product Data
|  |  |  | Zone 2 |  | DRY-2 | Tape & Float - Zone 1 |  |  | OW-5 | Owner DD & GMP Signoff |  |  | PRO-1 | Procure & Fabricate Security Glazing |  |  | SITE-8 | Install Concrete Pilot Channel - Playa Lake East | SUB-36 | Submit Kitchen Equipment Product Data
|  |  |  | CON-8 | F/R/P Slab on Grade - Zone 2 | EL-6 | Electrical Fixtures & Trim Out - Zone 1 |  |  | OW-6 | Owner Comments Due |  |  | PRO-2 | Procure & Fabricate Curtainwall |  |  | SITE-9 | Install Inlets (5) - Playa Lake East | SUB-38 | Submit Generator Product Data
|  |  |  | ELPL-1 | Under Slab MEP - Zone 2 | EL-7 | Set Generator - Mechanical Yard | [6 empty] | PRO-23 | Procure & Fabricate AHU's |  |  |  |  | SUB-40 | Submit Electrical Switchgear Product Data
[6 empty] | EL-8 | Hook-up/Final Connections Generator - Mechanical Yard | [6 empty] | PRO-24 | Procure & Fabricate Chillers |  |  |  |  | SUB-42 | Submit Curtainwall Product Data
|  |  |  | Zone 3 |  | FL-1 | Sealed Concrete Flooring - Zone 1 | [6 empty] | PRO-25 | Procure & Fabricate Boilers |  |  |  |  | SUB-44 | Submit Chiller Product Data
|  |  |  | CON-9 | F/R/P Slab on Grade - Zone 3 | FL-6 | Install LVT Flooring - Zone 1 | [6 empty] | PRO-26 | Procure & Fabricate Overhead Door (4) |  |  |  |  | SUB-46 | Submit Boilers Product Data
|  |  |  | ELPL-1 | Under Slab MEP - Zone 3 | FR-1 | Ceiling Trim Out - Zone 1 | [6 empty] | PRO-3 | Procure & Fabricate Store Fronts |  |  |  |  | SUB-48 | Submit ATS Product Data
[6 empty] | FR-2 | Close Ceiling - Zone 1 | [6 empty] | PRO-4 | Procure & Fabricate Kitchen Equipment |  |  |  |  | SUB-50 | Submit Antiligature Door Hardware/Kingsway Kits Product Data
|  |  |  | Zone 4 |  | FR-4 | Frame Walls & Ceilings - Zone 1 | [6 empty] | SL-1 | Procure & Fabricate Structural Steel |  |  |  |  | SUB-52 | Submit AHU Product Data
|  |  |  | CON-10 | F/R/P Slab on Grade - Zone 4 | FR-5 | In-wall Blocking - Zone 1
|  |  |  | ELPL-1 | Under Slab MEP - Zone 4 | FR-6 | Install ACT Grid - Zone 1 | [6 empty] | Pre-Qual | [5 empty] | Shop Drawings
[6 empty] | FR-8 | Install Door Frames - Zone 1 | [6 empty] | MG-4 | McGough - Pre-Qual Curtainwall Sub |  |  |  |  | SUB-1 | Owner Approve Chiller Shop Drawings
|  |  |  | Zone 5 |  | INS-1 | Ceiling Inspection - Zone 1 | [6 empty] | PRO-10 | Pre-Qual Kitchen Equipment Sub |  |  |  |  | SUB-10 | Owner Approve Steel Structure Shop Drawings
|  |  |  | CON-11 | F/R/P Slab on Grade - Zone 5 | MAS-3 | Install CMU Walls - Mechanical Yard | [6 empty] | PRO-11 | Pre-Qual Electrical Sub |  |  |  |  | SUB-11 | Owner Approve Overhead Door Shop Drawings
|  |  |  | ELPL-1 | Under Slab MEP - Zone 5 | MEC-1 | Install AHU 7 (Roof) - Zone 1 | [6 empty] | PRO-12 | Pre-Qual Antiligature Door Hardware/Kingsway Kits Sub |  |  |  |  | SUB-12 | Owner Approve Kitchen Equipment Shop Drawings
[6 empty] | MEC-2 | Hook-up/Final Connections Chillers - Mechanical Yard | [6 empty] | PRO-5 | Pre-Qual Structural Steel Sub |  |  |  |  | SUB-13 | Owner Approve Antiligature Door Hardware/Kingsway Kits Shop Drawings
|  |  |  | Zone 6 |  | MEC-3 | Set Chillers (3) - Mechanical Yard | [6 empty] | PRO-6 | Pre-Qual Store Fronts Sub |  |  |  |  | SUB-2 | Owner Approve AHU Shop Drawings
|  |  |  | CON-12 | F/R/P Slab on Grade - Zone 6 | MEC-4 | Set Fuel Tank - Mechanical Yard | [6 empty] | PRO-7 | Pre-Qual Security Glazing Sub |  |  |  |  | SUB-27 | Submit Store Front Shop Drawings
|  |  |  | ELPL-1 | Under Slab MEP - Zone 6 | MEP-1 | OH MEPF Rough-in - Zone 1 | [6 empty] | PRO-8 | Pre-Qual Overhead Door Sub |  |  |  |  | SUB-29 | Submit Steel Structure Shop Drawings
[6 empty] | MEP-2 | In-wall MEP Rough-in - Zone 1 | [6 empty] | PRO-9 | Pre-Qual Mechanical Sub |  |  |  |  | SUB-3 | Owner Approve Generator Shop Drawings
|  |  |  | Zone 7A |  | MG-1 | QA/QC Complete List - Zone 1 | [12 empty] | SUB-31 | Submit Security Glazing Shop Drawings
|  |  |  | ELPL-3 | Underground MEP - Zone 7A | MG-2 | OH MEPF Inspections - Zone 1 | [12 empty] | SUB-33 | Submit Overhead Door Shop Drawings
[6 empty] | MG-5 | In-wall MEP Inspections - Zone 1 | [12 empty] | SUB-35 | Submit Kitchen Equipment Shop Drawings
|  |  |  | Zone 7B |  | MILL-1 | Install Millwork - Zone 1 | [12 empty] | SUB-37 | Submit Generator Shop Drawings
|  |  |  | ELPL-3 | Underground MEP - Zone 7B | OH-1 | Install OH Doors (2) - Zone 1 Mechanical Room | [12 empty] | SUB-39 | Submit Electrical Switchgear Shop Drawings
[6 empty] | PA-1 | Paint 1st Coat - Zone 1 | [12 empty] | SUB-4 | Owner Approve Electrical Switchgear Shop Drawings
[6 empty] | PA-2 | Paint 2nd Coat - Zone 1 | [12 empty] | SUB-41 | Submit Curtainwall Shop Drawings
[6 empty] | PA-3 | Paint Final Coat - Zone 1 | [12 empty] | SUB-43 | Submit Chiller Shop Drawings
[6 empty] | PLU-2 | Plumbing Fixtures & Trim Out - Zone 1 | [12 empty] | SUB-45 | Submit Boilers Shop Drawings
[6 empty] | SL-2 | Steel Framing & Decking - Zone 1 | [12 empty] | SUB-47 | Submit ATS Shop Drawings
[6 empty] | T-1 | Install Wet Work (Restroom, Locker Room & Shower Area) - Zone 1 | [12 empty] | SUB-49 | Submit Antiligature Door Hardware/Kingsway Kits Shop Drawings
[20 empty] | SUB-5 | Owner Approve ATS Shop Drawings
[6 empty] | Zone 2 | [13 empty] | SUB-51 | Submit AHU Shop Drawings
[6 empty] | DOOR-1 | Install Doors & Hardware - Zone 2 | [12 empty] | SUB-6 | Owner Approve Boilers Shop Drawings
[6 empty] | DOOR-2 | Install Door Frames - Zone 2 | [12 empty] | SUB-7 | Owner Approve Curtainwall Shop Drawings
[6 empty] | DRY-1 | Two Side Walls - Zone 2 | [12 empty] | SUB-8 | Owner Approve Store Front Shop Drawings
[6 empty] | DRY-2 | Tape & Float - Zone 2 | [12 empty] | SUB-9 | Owner Approve Security Glazing Shop Drawings
[6 empty] | EL-9 | Electrical Fixtures & Trim Out - Zone 2
[6 empty] | FL-4 | Install Sheet Rubber Flooring - Zone 2
[6 empty] | FL-5 | Install Resinous Flooring - Zone 2
[6 empty] | FR-4 | Frame Walls & Ceilings - Zone 2
[6 empty] | FR-5 | In-wall Blocking - Zone 2
[6 empty] | FR-6 | Install ACT Ceilings - Zone 2
[6 empty] | MEC-1 | Install AHU 6 (Roof) - Zone 2
[6 empty] | MEP-1 | OH MEPF Rough-in - Zone 2
[6 empty] | MEP-2 | In-wall MEP Rough-in - Zone 2
[6 empty] | MG-1 | QA/QC Complete List - Zone 2
[6 empty] | MG-2 | OH MEPF Inspections - Zone 2
[6 empty] | MG-5 | In-wall MEP Inspections - Zone 2
[6 empty] | MILL-1 | Install Millwork - Zone 2
[6 empty] | OH-1 | Install OH Doors (2) - Zone 2
[6 empty] | PA-1 | Paint 1st Coat - Zone 2
[6 empty] | PA-2 | Paint 2nd Coat - Zone 2
[6 empty] | PA-3 | Paint Final Coat - Zone 2
[6 empty] | PA-4 | Install Hard Ceiling - Zone 2
[6 empty] | PLU-2 | Plumbing Fixtures & Trim Out - Zone 2
[6 empty] | SL-2 | Steel Framing & Decking - Zone 2
[6 empty] | T-1 | Install Wet Work (Restrooms) - Zone 2
Zone 3
[6 empty] | DOOR-1 | Install Doors & Hardware - Zone 3
[6 empty] | DOOR-2 | Install Door Frames - Zone 3
[6 empty] | DRY-1 | Two Side Walls - Zone 3
[6 empty] | DRY-2 | Tape & Float - Zone 3
[6 empty] | EL-9 | Electrical Fixtures & Trim Out- Zone 3
[6 empty] | FL-2 | Install Tile Flooring - Zone 3
[6 empty] | FL-4 | Install Sheet Rubber Flooring - Zone 3
[6 empty] | FL-6 | Install LVT Flooring - Zone 3
[6 empty] | FR-1 | Ceiling Trim Out - Zone 3
[6 empty] | FR-2 | Close Ceilings - Zone 3
[6 empty] | FR-4 | Frame Walls & Ceilings - Zone 3
[6 empty] | FR-5 | In-wall Blocking - Zone 3
[6 empty] | FR-6 | Install ACT Grid - Zone 3
[6 empty] | FR-9 | Paint Final Coat - Zone 3
[6 empty] | INS-1 | Ceiling Inspection - Zone 3
[6 empty] | MEC-1 | Install AHU 5 (Roof) - Zone 3
[6 empty] | MEP-1 | OH MEPF Rough-in - Zone 3
[6 empty] | MEP-2 | In-wall MEP Rough-in - Zone 3
[6 empty] | MG-1 | QA/QC Complete List - Zone 3
[6 empty] | MG-2 | OH MEPF Inspections - Zone 3
[6 empty] | MG-5 | In-wall MEP Inspections - Zone 3
[6 empty] | MILL-1 | Install Millwork - Zone 3
[6 empty] | PA-1 | Paint 1st Coat - Zone 3
[6 empty] | PA-2 | Paint 2nd Coat - Zone 3
[6 empty] | PLU-2 | Plumbing Fixtures & Trim Out - Zone 3
[6 empty] | SL-2 | Steel Framing & Decking - Zone 3
[6 empty] | T-1 | Install Wet Work (Restrooms) - Zone 3
Zone 4
[6 empty] | DOOR-1 | Install Doors & Hardware - Zone 4
[6 empty] | DOOR-2 | Install Door Frames - Zone 4
[6 empty] | DRY-1 | Two Side Walls - Zone 4
[6 empty] | DRY-2 | Tape & Float - Zone 4
[6 empty] | DRY-3 | Install Hard Ceilings - Zone 4
[6 empty] | EL-9 | Electrical Fixtures & Trim Out - Zone 4
[6 empty] | FL-2 | Install Tile Flooring - Zone 4
[6 empty] | FL-3 | Install Terazzo Flooring - Zone 4
[6 empty] | FL-5 | Install Resinous Flooring - Zone 4
[6 empty] | FL-6 | Install LVT Flooring - Zone 4
[6 empty] | FL-7 | Install Athletic Gym Vinyl Flooring - Zone 4
[6 empty] | FR-4 | Frame Walls & Ceilings - Zone 4
[6 empty] | FR-5 | In-wall Blocking - Zone 4
[6 empty] | FR-6 | Install ACT Ceilings - Zone 4
[6 empty] | MEC-1 | Install AHU 3 & 4 (Roof) - Zone 4
[6 empty] | MEP-1 | OH MEPF Rough-in - Zone 4
[6 empty] | MEP-2 | In-wall MEP Rough-in - Zone 4
[6 empty] | MG-1 | QA/QC Complete List - Zone 4
[6 empty] | MG-2 | OH MEPF Inspections - Zone 4
[6 empty] | MG-5 | In-wall MEP Inspections - Zone 4
[6 empty] | MILL-1 | Install Millwork - Zone 4
[6 empty] | PA-1 | Paint 1st Coat - Zone 4
[6 empty] | PA-2 | Paint 2nd Coat - Zone 4
[6 empty] | PA-3 | Paint Final Coat - Zone 4
[6 empty] | PLU-2 | Plumbing Fixtures & Trim Out - Zone 4
[6 empty] | SL-2 | Steel Framing & Decking - Zone 4
[6 empty] | T-1 | Install Wet Work - Zone 4
Zone 5
[6 empty] | DOOR-1 | Install Doors & Hardware - Zone 5
[6 empty] | DOOR-2 | Install Door Frames - Zone 5
[6 empty] | DRY-2 | Tape & Float - Zone 5
[6 empty] | DRY-3 | Install Hard Lid Ceilings - Zone 5
[6 empty] | EL-9 | Electrical Fixtures & Trim Out - Zone 5
[6 empty] | FL-1 | Sealed Concrete Flooring - Zone 5
[6 empty] | FL-4 | Install Sheet Rubber Flooring - Zone 5
[6 empty] | FL-5 | Install Resinous Flooring - Zone 5
[6 empty] | FL-6 | Install LVT Flooring - Zone 5
[6 empty] | FR-10 | Two Side Walls - Zone 5
[6 empty] | FR-4 | Frame Walls & Ceilings - Zone 5
[6 empty] | FR-5 | In-wall Blocking - Zone 5
[6 empty] | FR-6 | Install ACT Ceilings - Zone 5
[6 empty] | LV-1 | Safety/Security & Troubleshooting - Zone 5
[6 empty] | MEC-1 | Install AHU 1 (Roof) - Zone 5
[6 empty] | MEP-1 | OH MEPF Rough-in - Zone 5
[6 empty] | MEP-2 | In-wall MEP Rough-in - Zone 5
[6 empty] | MG-1 | QA/QC Complete List - Zone 5
[6 empty] | MG-2 | OH MEPF Inspections - Zone 5
[6 empty] | MG-5 | In-wall MEP Inspections - Zone 5
[6 empty] | MILL-1 | Install Millwork - Zone 5
[6 empty] | PA-1 | Paint 1st Coat - Zone 5
[6 empty] | PA-2 | Paint 2nd Coat - Zone 5
[6 empty] | PA-3 | Paint Final Coat - Zone 5
[6 empty] | PLU-2 | Plumbing Fixtures & Trim Out - Zone 5
[6 empty] | SL-2 | Steel Framing & Decking - Zone 5
[6 empty] | SPE-2 | Care Team Station Finishes - Zone 5
[6 empty] | T-1 | Install Wet Work (Patient & Staff Restrooms) - Zone 5
Zone 6
[6 empty] | DOOR-1 | Install Doors & Hardware - Zone 6
[6 empty] | DOOR-2 | Install Door Frames - Zone 6
[6 empty] | DRY-1 | Two Side Walls - Zone 6
[6 empty] | DRY-2 | Tape & Float - Zone 6
[6 empty] | DRY-4 | Install Hard Lid Ceilings - Zone 6
[6 empty] | EL-9 | Electrical Fixtures & Trim Out - Zone 6
[6 empty] | FL-1 | Sealed Concrete Flooring - Zone 6
[6 empty] | FL-4 | Install Sheet Rubber Flooring - Zone 6
[6 empty] | FL-5 | Install Resinous Flooring - Zone 6
[6 empty] | FL-6 | Install LVT Flooring - Zone 6
[6 empty] | FR-4 | Frame Walls & Ceilings - Zone 6
[6 empty] | FR-5 | In-wall Blocking - Zone 6
[6 empty] | FR-7 | Install Ceilings - Zone 6
[6 empty] | FR-9 | Paint Final Coat - Zone 6
[6 empty] | LV-1 | Safety/Security & Troubleshooting - Zone 6
[6 empty] | MEC-1 | Install AHU 2 (Roof) - Zone 6
[6 empty] | MEP-1 | OH MEPF Rough-in - Zone 6
[6 empty] | MEP-2 | In-wall MEP Rough-in - Zone 6
[6 empty] | MG-1 | QA/QC Complete List - Zone 6
[6 empty] | MG-2 | OH MEPF Inspections - Zone 6
[6 empty] | MG-5 | In-wall MEP Inspections - Zone 6
[6 empty] | MILL-1 | Install Millwork - Zone 6
[6 empty] | PA-1 | Paint 1st Coat - Zone 6
[6 empty] | PA-2 | Paint 2nd Coat - Zone 6
[6 empty] | PLU-2 | Plumbing Fixtures & Trim Out - Zone 6
[6 empty] | SL-2 | Steel Framing & Decking - Zone 6
[6 empty] | SPE-2 | Care Team Station Finishes - Zone 6
[6 empty] | T-1 | Install Wet Work (Patient & Staff Restrooms) - Zone 6
Zone 7A
[6 empty] | SPE-3 | Finishes In Courtyard - Zone 7A
Zone 7B
[6 empty] | SPE-3 | Finishes In Courtyard - Zone 7B