## Sheet1
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish
Precon | Prep | Construction Company | #632523 | PRE-1 | 3.0, 4.0. 5.0 pre, during and post construction total job | 2023-09-28 | 2025-05-05
Precon | Prep | Construction Company | #632523 | PRE-2 | 3.0 Pre construction and mobilization | 2023-09-28 | 2023-12-20
Precon | Prep | Construction Company | #632523 | PRE-3 | Assign Permits check list | 2023-09-28 | 2023-12-20
Precon | Prep | Construction Company | #632523 | PRE-4 | Assign Health and Safety checklist | 2023-09-28 | 2023-12-20
Precon | Prep | Construction Company | #632523 | PRE-5 | Assign Mobilization check list | 2023-09-28 | 2023-12-20
Precon | Prep | Construction Company | #632523 | PRE-6 | Assign Equipment & Tools check list | 2023-09-28 | 2023-12-20
Precon | Prep | Construction Company | #632523 | PRE-7 | Assign Safety Equipment and Materials checklist | 2023-09-28 | 2023-12-20
Precon | Prep | Construction Company | #632523 | PRE-8 | Assign Procurement Plan check list | 2023-09-28 | 2023-12-20
Precon | Prep | Construction Company | #632523 | PRE-9 | Assign Site Services Planning check list | 2023-09-28 | 2023-12-20
Precon | Prep | Construction Company | #632523 | PRE-10 | Assign Sub Contractor planning checklist | 2023-09-28 | 2023-12-20
Precon | Prep | Construction Company | #632523 | PRE-11 | Assign Project Team | 2023-09-28 | 2023-12-20
Precon | Prep | Construction Company | #632523 | PRE-12 | Hold Pre Kick-Off meeting with Engineers and Trades people | 2023-09-28 | 2023-10-02
Precon | Prep | Construction Company | #632523 | PRE-13 | Assign hollow core ordering checklist | 2023-09-28 | 2023-09-28
Precon | Prep | Construction Company | #632523 | PRE-14 | Organize site team to have training and certificates | 2023-09-28 | 2023-09-28
Precon | Prep | Construction Company | #632523 | PRE-15 | Order Rebar (30 days before site delivery date required) | 2023-12-08 | 2023-12-08
Sitework & Foundations | Site | Site Sub | #8064A2 | SITE-1 | 4.1 Site Services & Foundation Work | 2023-12-21 | 2024-03-25
Sitework | Site | Site Sub | #8064A2 | SITE-2 | Site Preparation | 2023-12-21 | 2024-01-05
Sitework | Site | Site Sub | #8064A2 | SITE-3 | 18. Assign site prep check list (First) | 2023-12-28 | 2023-12-28
Sitework | Site | Site Sub | #8064A2 | SITE-4 | deliver rebar (footings and gradebeam only) | 2023-12-21 | 2023-12-21
Sitework | Site | Site Sub | #8064A2 | SITE-5 | Order all Anchor bolts | 2023-12-21 | 2023-12-21
Sitework | Site | Site Sub | #8064A2 | SITE-6 | Schedule locates to be done | 2023-12-21 | 2023-12-27
Sitework | Site | Site Sub | #8064A2 | SITE-7 | Survey for balcony piles | 2023-12-21 | 2023-12-22
Sitework | Site | Site Sub | #8064A2 | SITE-8 | Schedule Pile contractor | 2023-12-21 | 2023-12-21
Sitework | Site | Site Sub | #8064A2 | SITE-9 | Install balcony piles | 2023-12-25 | 2023-12-27
Sitework | Site | Site Sub | #8064A2 | SITE-10 | Strip site | 2023-12-29 | 2024-01-04
Sitework | Site | Site Sub | #8064A2 | SITE-11 | Measure corner offsets for excavation | 2024-01-05 | 2024-01-05
Sitework | Site | Site Sub | #8064A2 | SITE-12 | Excavation | 2024-01-08 | 2024-01-18
Sitework | Site | Site Sub | #8064A2 | SITE-13 | 28. Assign Pre excavation checklist | 2024-01-08 | 2024-01-08
Sitework | Site | Site Sub | #8064A2 | SITE-14 | Dig footing and parkade foot print | 2024-01-08 | 2024-01-16
Sitework | Site | Site Sub | #8064A2 | SITE-15 | Survey offsets, and footings | 2024-01-17 | 2024-01-17
Sitework | Site | Site Sub | #8064A2 | SITE-16 | Geo Tech Engineer inspection | 2024-01-18 | 2024-01-18
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-1 | Foundation | 2024-01-19 | 2024-02-29
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-2 | Form footings | 2024-01-19 | 2024-01-24
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-3 | Tie footing rebar | 2024-01-25 | 2024-01-31
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-4 | Rebar Inspection Structural Engineer | 2024-02-01 | 2024-02-01
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-5 | Assign pre-pour checklist | 2024-02-02 | 2024-02-02
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-6 | Pour footings | 2024-02-05 | 2024-02-05
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-7 | Form grade beam | 2024-02-06 | 2024-02-14
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-8 | Build templates for Anchor bolts | 2024-02-15 | 2024-02-15
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-9 | Tie Grade beam rebar | 2024-02-16 | 2024-02-26
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-10 | Ensure Sleeves for electrical are run in the grade beam prior to pouring | 2024-02-06 | 2024-02-06
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-11 | Assign pre concrete pour checklist | 2024-02-27 | 2024-02-27
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-12 | Rebar inspection Structural Engineer | 2024-02-28 | 2024-02-28
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-13 | Pour grade beam | 2024-02-29 | 2024-02-29
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-14 | Back fill foundation | 2024-03-01 | 2024-03-14
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-15 | Assign pre back fill check list | 2024-03-01 | 2024-03-01
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-16 | Install underground insulation | 2024-03-04 | 2024-03-05
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-17 | Back fill exterior grade beam | 2024-03-06 | 2024-03-07
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-18 | Back fill interior parkade | 2024-03-08 | 2024-03-14
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-19 | Site services W/S/S install | 2024-03-15 | 2024-03-25
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-20 | Assign water and sewer and storm checklist | 2024-03-15 | 2024-03-15
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-21 | Install water and sewer | 2024-03-18 | 2024-03-22
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-22 | Assign water and sewer commissioning checklist | 2024-03-25 | 2024-03-25
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-23 | Commision Water/sewer/storm | 2024-03-25 | 2024-03-25
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-24 | Strucutral Steel | 2024-03-15 | 2024-03-21
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-25 | Assign structural steel checklist | 2024-03-15 | 2024-03-15
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-26 | Structural steel delivered and sorted onsite | 2024-03-18 | 2024-03-18
Foundations | Bellow the Ground | Concrete | #974706 | FOUND-27 | Structural steel erection | 2024-03-20 | 2024-03-21
Framing & RI | Structure | Framer & MEP | #F79646 | STR-1 | 4.2 Framing | 2024-04-11 | 2025-01-03
Framing & RI | Structure | Framer & MEP | #F79646 | STR-2 | Rough in parkade slab | 2024-06-12 | 2024-06-26
Framing & RI | Structure | Framer & MEP | #F79646 | STR-3 | Mechanical rough in in slab | 2024-06-12 | 2024-06-18
Framing & RI | Structure | Framer & MEP | #F79646 | STR-4 | Electrical rough in in slab | 2024-06-12 | 2024-06-18
Framing & RI | Structure | Framer & MEP | #F79646 | STR-5 | Deliver pakade slab rebar | 2024-06-19 | 2024-06-19
Framing & RI | Structure | Framer & MEP | #F79646 | STR-6 | Back fill and level parkade | 2024-06-20 | 2024-06-26
Framing & RI | Structure | Framer & MEP | #F79646 | STR-7 | Pour parakde slab | 2024-06-27 | 2024-07-10
Framing & RI | Structure | Framer & MEP | #F79646 | STR-8 | Assign parkade slab rough in checklist | 2024-06-27 | 2024-06-27
Framing & RI | Structure | Framer & MEP | #F79646 | STR-9 | Radon rock install | 2024-06-28 | 2024-07-01
Framing & RI | Structure | Framer & MEP | #F79646 | STR-10 | Install poly | 2024-07-02 | 2024-07-02
Framing & RI | Structure | Framer & MEP | #F79646 | STR-11 | Tie parkade rebar | 2024-07-03 | 2024-07-05
Framing & RI | Structure | Framer & MEP | #F79646 | STR-12 | Assign pre concrete pour checklist | 2024-07-08 | 2024-07-08
Framing & RI | Structure | Framer & MEP | #F79646 | STR-13 | Pour parkade floor | 2024-07-09 | 2024-07-10
Framing & RI | Structure | Framer & MEP | #F79646 | STR-14 | Framing parkade | 2024-04-11 | 2024-04-16
Framing & RI | Structure | Framer & MEP | #F79646 | STR-15 | Frame parkade level | 2024-04-11 | 2024-04-15
Framing & RI | Structure | Framer & MEP | #F79646 | STR-16 | Assign framing checklist | 2024-04-16 | 2024-04-16
Framing & RI | Structure | Framer & MEP | #F79646 | STR-17 | Hollowcore 2nd floor | 2024-04-16 | 2024-06-17
Framing & RI | Structure | Framer & MEP | #F79646 | STR-18 | Install hollowcore 2nd floor , Install backer rod & Grout 2nd floor | 2024-04-16 | 2024-04-18
Framing & RI | Structure | Framer & MEP | #F79646 | STR-19 | Assign hollow core erection checklist | 2024-04-19 | 2024-04-19
Framing & RI | Structure | Framer & MEP | #F79646 | STR-20 | Paint underside of ceiling in parkade | 2024-06-17 | 2024-06-17
Framing & RI | Structure | Framer & MEP | #F79646 | STR-21 | Framing 2nd floor | 2024-04-19 | 2024-05-14
Framing & RI | Structure | Framer & MEP | #F79646 | STR-22 | Frame 2nd floor | 2024-04-19 | 2024-05-13
Framing & RI | Structure | Framer & MEP | #F79646 | STR-23 | Assign framing check list | 2024-05-14 | 2024-05-14
Framing & RI | Structure | Framer & MEP | #F79646 | STR-24 | Hollowcore 3rd floor | 2024-05-23 | 2024-05-28
Framing & RI | Structure | Framer & MEP | #F79646 | STR-25 | Install hollow core 3rd floor, Install backer rod & grout | 2024-05-23 | 2024-05-28
Framing & RI | Structure | Framer & MEP | #F79646 | STR-26 | Assign hollow core erection checklist | 2024-05-27 | 2024-05-27
Framing & RI | Structure | Framer & MEP | #F79646 | STR-27 | Framing 3rd floor | 2024-05-28 | 2024-07-26
Framing & RI | Structure | Framer & MEP | #F79646 | STR-28 | Frame 3rd floor | 2024-05-28 | 2024-06-07
Framing & RI | Structure | Framer & MEP | #F79646 | STR-29 | Assign framing checklist | 2024-06-10 | 2024-06-10
Framing & RI | Structure | Framer & MEP | #F79646 | STR-30 | Layout suites on 2nd floor | 2024-07-18 | 2024-07-22
Framing & RI | Structure | Framer & MEP | #F79646 | STR-31 | Core floors begin at 2nd | 2024-07-24 | 2024-07-26
Framing & RI | Structure | Framer & MEP | #F79646 | STR-32 | Hollowcore 4th floor | 2024-06-11 | 2024-06-13
Framing & RI | Structure | Framer & MEP | #F79646 | STR-33 | Install hollow core 4th floor and grout | 2024-06-11 | 2024-06-12
Framing & RI | Structure | Framer & MEP | #F79646 | STR-34 | Assign hollow core checklist | 2024-06-13 | 2024-06-13
Framing & RI | Structure | Framer & MEP | #F79646 | STR-35 | Framing 4th floor | 2024-06-19 | 2024-07-31
Framing & RI | Structure | Framer & MEP | #F79646 | STR-36 | Frame 4th floor | 2024-06-19 | 2024-07-05
Framing & RI | Structure | Framer & MEP | #F79646 | STR-37 | Assign framing checklist | 2024-07-08 | 2024-07-08
Framing & RI | Structure | Framer & MEP | #F79646 | STR-38 | Layout suites on 3rd floor | 2024-07-23 | 2024-07-26
Framing & RI | Structure | Framer & MEP | #F79646 | STR-39 | Core floor beings at 3rd floor | 2024-07-29 | 2024-07-31
Framing & RI | Structure | Framer & MEP | #F79646 | STR-40 | Roof trusses install | 2024-07-09 | 2024-08-20
Framing & RI | Structure | Framer & MEP | #F79646 | STR-41 | Install roof trusses and sheeting and towers | 2024-07-09 | 2024-08-06
Framing & RI | Structure | Framer & MEP | #F79646 | STR-42 | Assign roof trusses framing checklist | 2024-08-07 | 2024-08-07
Framing & RI | Structure | Framer & MEP | #F79646 | STR-43 | Call for structural inspection | 2024-08-20 | 2024-08-20
Framing & RI | Structure | Framer & MEP | #F79646 | STR-44 | Layout suites 4th floor | 2024-07-29 | 2024-08-01
Framing & RI | Structure | Framer & MEP | #F79646 | STR-45 | Core floor beings at 4th floor | 2024-08-01 | 2024-08-02
Exterior | Building | Exterior Subs | #4BACC6 | EXT-1 | install windows and doors | 2024-07-08 | 2024-11-26
Exterior | Building | Exterior Subs | #4BACC6 | EXT-2 | Deliver tubs & showers to suites / checklist | 2024-07-17 | 2024-07-18
Exterior | Building | Exterior Subs | #4BACC6 | EXT-3 | Assign window & door installation checklist | 2024-07-08 | 2024-07-08
Exterior | Building | Exterior Subs | #4BACC6 | EXT-4 | Install windows & doors all floors | 2024-08-01 | 2024-08-13
Exterior | Building | Exterior Subs | #4BACC6 | EXT-5 | Install stairs | 2024-07-30 | 2024-07-30
Exterior | Building | Exterior Subs | #4BACC6 | EXT-6 | Call for envelope reviewer inspection | 2024-11-26 | 2024-11-26
Exterior | Building | Exterior Subs | #4BACC6 | EXT-7 | Roofing and water proofing | 2024-08-07 | 2024-08-23
Exterior | Building | Exterior Subs | #4BACC6 | EXT-8 | Assign roofing and water proofing checklist | 2024-08-07 | 2024-08-07
Exterior | Building | Exterior Subs | #4BACC6 | EXT-9 | Install roofing and water proofing | 2024-08-12 | 2024-08-23
Exterior | Building | Exterior Subs | #4BACC6 | EXT-10 | Soffit & Tower Siding | 2024-09-03 | 2025-01-03
Exterior | Building | Exterior Subs | #4BACC6 | EXT-11 | Building paper the whole building | 2024-09-03 | 2024-11-25
Exterior | Building | Exterior Subs | #4BACC6 | EXT-12 | Install fascia and soffit 4th floor | 2024-11-15 | 2024-11-25
Exterior | Building | Exterior Subs | #4BACC6 | EXT-13 | Assign tower siding checklist | 2024-11-26 | 2024-11-26
Exterior | Building | Exterior Subs | #4BACC6 | EXT-14 | Siding towers | 2024-11-27 | 2024-12-16
Exterior | Building | Exterior Subs | #4BACC6 | EXT-15 | Delivery of Elevator & Install | 2024-10-14 | 2025-01-03
Exterior | Building | Exterior Subs | #4BACC6 | EXT-16 | Exterior concrete works | 2024-08-26 | 2024-12-19
Exterior | Building | Exterior Subs | #4BACC6 | EXT-17 | Excavate areas | 2024-08-26 | 2024-08-27
Exterior | Building | Exterior Subs | #4BACC6 | EXT-18 | Form exterior pads | 2024-08-28 | 2024-09-03
Exterior | Building | Exterior Subs | #4BACC6 | EXT-19 | Tie rebar exterior pads | 2024-09-04 | 2024-09-06
Exterior | Building | Exterior Subs | #4BACC6 | EXT-20 | Assign conrete pour checklist | 2024-09-09 | 2024-09-09
Exterior | Building | Exterior Subs | #4BACC6 | EXT-21 | Pour exterior pads | 2024-09-10 | 2024-09-10
Exterior | Building | Exterior Subs | #4BACC6 | EXT-22 | Excatae exterior sidewalks | 2024-09-11 | 2024-12-03
Exterior | Building | Exterior Subs | #4BACC6 | EXT-23 | Form exterior sidewalks | 2024-12-04 | 2024-12-06
Exterior | Building | Exterior Subs | #4BACC6 | EXT-24 | Rebar exterior sidewalks | 2024-12-09 | 2024-12-11
Exterior | Building | Exterior Subs | #4BACC6 | EXT-25 | Assign pre concrete pour checklist | 2024-12-12 | 2024-12-16
Exterior | Building | Exterior Subs | #4BACC6 | EXT-26 | Pour exterior sidewalks | 2024-12-17 | 2024-12-19
Interiors | Finishes | Clean | #4F81BD | Cl-1 | Construction clean 2nd floor | 2025-02-24 | 2025-02-27
Interiors | Finishes | Clean | #4F81BD | Cl-1 | Construction clean on 1 | 2025-02-14 | 2025-02-18
Interiors | Finishes | Clean | #4F81BD | Cl-1 | Construction clean on 3rd | 2025-02-11 | 2025-02-17
Interiors | Finishes | Clean | #4F81BD | Cl-1 | Construction clean on 4th | 2025-02-03 | 2025-02-07
Interiors | Finishes | Clean | #4F81BD | Cl-2 | Final suite clean | 2025-02-27 | 2025-02-28
Interiors | Finishes | Clean | #4F81BD | Cl-2 | Final suite clean on 1 | 2025-02-20 | 2025-02-24
Interiors | Finishes | Clean | #4F81BD | Cl-2 | Final suite clean on 3rd | 2025-02-17 | 2025-02-18
Interiors | Finishes | Clean | #4F81BD | Cl-2 | Final suite clean on 4th | 2025-02-07 | 2025-02-10
Interiors | Finishes | Construction Company | #632523 | CC-1 | Assign Unit Commissioning Inspection list 2nd floor | 2025-02-27 | 2025-02-27
Interiors | Finishes | Construction Company | #632523 | CC-1 | Assign Unit Commissioning Inspection list on 1 | 2025-02-19 | 2025-02-19
Interiors | Finishes | Construction Company | #632523 | CC-1 | Assign Unit Commissioning Inspection list on 3rd | 2025-02-17 | 2025-02-17
Interiors | Finishes | Drywall | #F2F3B1 | D-1 | 2nd floor - Taper do the rectification of deficiences | 2024-12-23 | 2024-12-23
Interiors | Finishes | Drywall | #F2F3B1 | D-1 | 3rd floor - Taper do the rectification of deficiencies | 2024-12-10 | 2024-12-10
Interiors | Finishes | Drywall | #F2F3B1 | D-1 | 4th floor - Taper do the rectification of deficiencies | 2024-12-02 | 2024-12-03
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-2 | 4th floor framing inspection | 2024-11-04 | 2024-11-04
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-3 | Assign Corridor & Stairwell pre board inspection checklist | 2024-11-28 | 2024-11-28
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-3 | Assign corridor & stairwell pre board inspection checklist | 2024-11-12 | 2024-11-12
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-3 | Assign Corridor & Stairwell pre board inspection checklist | 2024-11-08 | 2024-11-08
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-4 | Assign pre board inspection check list | 2024-11-28 | 2024-11-28
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-4 | Assign pre board inspection check list | 2024-11-15 | 2024-11-15
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-4 | Assign pre board inspection checklist | 2025-01-22 | 2025-01-22
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-4 | Assign pre board inspection checklist | 2025-01-22 | 2025-01-22
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-4 | Assign pre board interior walls checklist | 2024-11-28 | 2024-11-28
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-4 | Assign pre board interior walls checklist | 2024-11-15 | 2024-11-15
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-4 | Assign pre board interior walls checklist | 2024-11-08 | 2024-11-08
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-5 | Assign siding checklist | 2024-12-24 | 2024-12-24
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-5 | Assign siding checklist | 2024-12-10 | 2024-12-10
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-5 | Assign siding checklist | 2024-11-22 | 2024-11-22
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-5 | Assign siding checklist | 2024-11-06 | 2024-11-06
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-6 | Assign taping inspection checklist | 2024-12-23 | 2024-12-23
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-6 | Assign taping inspection checklist | 2024-10-07 | 2024-10-07
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-6 | Assign taping inspection checklist | 2024-12-19 | 2024-12-19
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-6 | Assign taping inspection checklist | 2024-12-05 | 2024-12-05
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-6 | Assign taping inspection checklist | 2024-11-15 | 2024-11-15
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-6 | Assign taping inspection checklist | 2024-11-28 | 2024-11-28
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-6 | Assign taping inspection checklist for suites | 2024-12-19 | 2024-12-19
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-6 | Assign taping inspection checklist for suites | 2024-12-05 | 2024-12-05
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-7 | Back framing on 2nd | 2024-08-21 | 2024-08-27
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-7 | Back framing on 3rd | 2024-09-10 | 2024-09-16
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-7 | Back framing on 4th | 2024-09-23 | 2024-09-27
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-8 | Board 2nd floor hallways and stairwells | 2024-11-28 | 2024-12-04
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-8 | Board 2nd floor walls | 2024-11-28 | 2024-12-04
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-9 | Board and prepare electrical/mechanical room | 2024-12-06 | 2024-12-10
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-10 | Board exterior walls on 2nd and sheds | 2024-11-28 | 2024-12-04
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-11 | Board parkade exterior walls and sheds | 2024-12-09 | 2024-12-09
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-12 | Board Parkade interior walls | 2024-12-10 | 2024-12-13
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-13 | Board upper 16" strips in common area & all suites on 3rd | 2024-09-11 | 2024-09-16
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-13 | Board upper 16" strips in common area and all suites on 2nd | 2024-08-30 | 2024-09-04
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-13 | Board upper 16" strips in common area and all suites on 4th | 2024-09-27 | 2024-10-02
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-14 | Fire tape / Fire caulk upper strips on 2nd | 2024-11-25 | 2024-11-25
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-14 | Fire tape / Fire caulk upper strips on 3rd | 2024-11-11 | 2024-11-11
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-14 | Fire tape / Fire caulk upper strips on 4th | 2024-11-01 | 2024-11-01
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-15 | Frame and board Parkade beams | 2024-12-16 | 2024-12-20
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-16 | Frame drops on 2nd | 2024-11-26 | 2024-12-02
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-16 | Frame drops on 3rd | 2024-11-12 | 2024-11-18
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-16 | Frame drops on 4th | 2024-11-29 | 2024-12-05
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-17 | Frame interior parkade walls | 2024-08-19 | 2024-08-23
Interiors | Rough-Ins | Drywall | #F2F3B1 | D-18 | Install drywall on 4th floor ceiling | 2024-09-11 | 2024-09-17
Interiors | Rough-Ins | Gypcrete | #A6A6A6 | GP-1 | Assign gypcrete pour checklist | 2024-11-25 | 2024-11-25
Interiors | Rough-Ins | Gypcrete | #A6A6A6 | GP-1 | Gypcrete | 2024-11-25 | 2024-11-26
Interiors | Rough-Ins | Gypcrete | #A6A6A6 | GP-1 | Pour Gypcrete | 2024-11-25 | 2024-11-26
Interiors | Finishes | MEPF | #948A54 | MEPF-1 | 2nd floor counter top measurement for template | 2025-01-16 | 2025-01-20
Interiors | Finishes | MEPF | #948A54 | MEPF-2 | 2nd floor finishing | 2024-12-16 | 2025-02-28
Interiors | Finishes | MEPF | #948A54 | MEPF-1 | 3rd floor counter top measurement for template | 2025-01-08 | 2025-01-10
Interiors | Finishes | MEPF | #948A54 | MEPF-2 | 3rd floor finishing | 2024-12-02 | 2025-02-18
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-3 | 4.3 Rough In, Steel Stud Drywall | 2024-08-05 | 2025-01-23
Interiors | Finishes | MEPF | #948A54 | MEPF-4 | 4.4 Finishing | 2024-08-09 | 2025-05-05
Interiors | Finishes | MEPF | #948A54 | MEPF-5 | 4th floor counter top measurements for template | 2024-12-17 | 2024-12-19
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-6 | Assign exterior wall pre board inspection check list | 2024-11-08 | 2024-11-08
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-7 | Blow in attic insulation | 2024-09-18 | 2024-09-20
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-8 | Call for Electrical and Mechanical Inspection | 2025-01-23 | 2025-01-23
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-8 | Call for Electrical and Mechanical inspection | 2024-10-31 | 2024-10-31
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-9 | Call for Mechanical & Electrical inspection of attic | 2024-09-04 | 2024-09-04
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-9 | Call for Mechanical and Electrical inspection | 2024-11-25 | 2024-11-25
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-9 | Call for Mechanical and Electrical Inspection | 2024-11-12 | 2024-11-12
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-10 | Call the surveyor to measure for condo plan | 2024-10-29 | 2024-10-31
Interiors | Finishes | MEPF | #948A54 | MEPF-11 | Ceiling texture on 1 | 2025-01-02 | 2025-01-03
Interiors | Finishes | MEPF | #948A54 | MEPF-11 | Ceiling texture on 2nd | 2024-12-16 | 2024-12-17
Interiors | Finishes | MEPF | #948A54 | MEPF-11 | Ceiling texture on 3rd | 2024-12-02 | 2024-12-03
Interiors | Finishes | MEPF | #948A54 | MEPF-11 | Ceiling texture on 4th | 2024-11-26 | 2024-11-27
Interiors | Finishes | MEPF | #948A54 | MEPF-12 | Electrical finishing 2nd floor | 2025-02-07 | 2025-02-13
Interiors | Finishes | MEPF | #948A54 | MEPF-12 | Electrical finishing on 1 | 2025-02-11 | 2025-02-13
Interiors | Finishes | MEPF | #948A54 | MEPF-12 | Electrical finishing on 3rd | 2025-01-29 | 2025-02-04
Interiors | Finishes | MEPF | #948A54 | MEPF-12 | Electrical finishing on 4th | 2025-01-21 | 2025-01-27
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-13 | Electrical rough in hallways & stairwells on 2nd | 2024-11-08 | 2024-11-22
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-13 | Electrical rough in hallways & stairwells on 3rd | 2024-10-28 | 2024-11-08
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-13 | Electrical rough in hallways stairwells on 4th | 2024-10-21 | 2024-10-31
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-14 | Electrical rough in in ceiling | 2024-08-26 | 2024-09-03
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-15 | Electrical rough in on 2nd | 2024-11-08 | 2024-11-22
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-15 | Electrical rough in on 3rd | 2024-10-28 | 2024-11-08
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-15 | Electrical rough in on 4th | 2024-10-21 | 2024-10-31
Interiors | Finishes | MEPF | #948A54 | MEPF-16 | Final coat of paint | 2025-02-13 | 2025-02-25
Interiors | Finishes | MEPF | #948A54 | MEPF-16 | Final coat of paint | 2025-02-03 | 2025-02-13
Interiors | Finishes | MEPF | #948A54 | MEPF-16 | Final coat of paint | 2025-01-24 | 2025-02-05
Interiors | Finishes | MEPF | #948A54 | MEPF-17 | finishing on 4th | 2024-11-26 | 2025-02-10
Interiors | Finishes | MEPF | #948A54 | MEPF-18 | finishing parkade level 1 | 2025-01-02 | 2025-02-24
Interiors | Finishes | MEPF | #948A54 | MEPF-19 | Install base and hardware 2nd floor | 2025-01-17 | 2025-01-24
Interiors | Finishes | MEPF | #948A54 | MEPF-19 | Install base and hardware on 3rd | 2025-01-08 | 2025-01-13
Interiors | Finishes | MEPF | #948A54 | MEPF-19 | Install base and hardware on 4th | 2024-12-20 | 2025-01-03
Interiors | Finishes | MEPF | #948A54 | MEPF-20 | Install cabinets 2nd floor | 2025-01-13 | 2025-01-17
Interiors | Finishes | MEPF | #948A54 | MEPF-20 | Install cabinets on 1 | 2025-01-17 | 2025-01-20
Interiors | Finishes | MEPF | #948A54 | MEPF-20 | Install cabinets on 3rd | 2024-12-18 | 2025-01-10
Interiors | Finishes | MEPF | #948A54 | MEPF-20 | Install cabinets on 4th | 2024-12-11 | 2024-12-18
Interiors | Finishes | MEPF | #948A54 | MEPF-21 | Install countertops on 1 | 2025-02-10 | 2025-02-10
Interiors | Finishes | MEPF | #948A54 | MEPF-22 | Install flooring 2nd floor | 2025-01-08 | 2025-01-16
Interiors | Finishes | MEPF | #948A54 | MEPF-22 | Install flooring on 1 | 2025-01-15 | 2025-01-16
Interiors | Finishes | MEPF | #948A54 | MEPF-22 | Install flooring on 3rd | 2024-12-17 | 2025-01-07
Interiors | Finishes | MEPF | #948A54 | MEPF-22 | Install flooring on 4th | 2024-12-09 | 2024-12-16
Interiors | Finishes | MEPF | #948A54 | MEPF-23 | Install interior doors and case on 1 | 2025-01-08 | 2025-01-09
Interiors | Finishes | MEPF | #948A54 | MEPF-23 | Install interior doors and case on 2nd | 2024-12-23 | 2025-01-03
Interiors | Finishes | MEPF | #948A54 | MEPF-23 | Install interior doors and case on 3rd | 2024-12-09 | 2024-12-13
Interiors | Finishes | MEPF | #948A54 | MEPF-23 | Install interior doors and case on 4th | 2024-12-02 | 2024-12-06
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-24 | Install metal doors and frames | 2024-12-24 | 2025-01-06
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-25 | Install pocket door frames | 2024-09-06 | 2024-09-12
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-25 | Install pocket door frames | 2024-09-20 | 2024-09-26
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-25 | Install pocket foor frame | 2024-08-28 | 2024-09-03
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-26 | Install sound bar 4th floor | 2024-09-09 | 2024-09-10
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-27 | Install suite entry doors and frames and Interior doors, trims and jambs | 2024-12-23 | 2025-01-03
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-27 | Install suite entry doors and frames and Interior doors, trims and jambs | 2024-12-09 | 2024-12-13
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-27 | Install suite entry doors and frames and Interior doors, trims and jambs | 2024-12-02 | 2024-12-06
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-28 | Install tubs and showers | 2024-08-30 | 2024-09-04
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-28 | Install tubs and showers | 2024-09-06 | 2024-09-11
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-28 | Install tubs and showers | 2024-09-26 | 2024-09-27
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-29 | Load boards on floor and Board 3rd floor walls | 2024-11-15 | 2024-11-22
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-29 | Load boards on floor and Board exterior walls on 3rd and sheds | 2024-11-15 | 2024-11-22
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-29 | Load the board on floor and Board 3rd floor hallways and stairwells | 2024-11-15 | 2024-11-22
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-29 | Load the board on floor and Board 4th floor hallways and stairwells | 2024-11-08 | 2024-11-15
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-29 | Load the board on floor and Board 4th floor walls | 2024-11-08 | 2024-11-15
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-29 | Load the board on floor and Board exterior walls on 4th and sheds | 2024-11-08 | 2024-11-15
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-30 | Main service electrical room install | 2024-11-28 | 2024-12-26
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-32 | Main service mechanical room install | 2024-11-28 | 2025-01-22
Interiors | Finishes | MEPF | #948A54 | MEPF-33 | Manufacturing and Install countertops 2nd floor | 2025-01-21 | 2025-02-07
Interiors | Finishes | MEPF | #948A54 | MEPF-33 | Manufacturing and Install countertops on 3rd | 2025-01-10 | 2025-01-29
Interiors | Finishes | MEPF | #948A54 | MEPF-33 | manufacturing and Install countertops on 4th | 2025-01-02 | 2025-01-21
Interiors | Finishes | MEPF | #948A54 | MEPF-34 | Mechanical finishing 2nd floor | 2025-02-07 | 2025-02-13
Interiors | Finishes | MEPF | #948A54 | MEPF-34 | Mechanical finishing on 1 | 2025-02-11 | 2025-02-13
Interiors | Finishes | MEPF | #948A54 | MEPF-34 | Mechanical finishing on 3rd | 2025-01-29 | 2025-02-04
Interiors | Finishes | MEPF | #948A54 | MEPF-34 | Mechanical finishing on 4th | 2025-01-21 | 2025-01-27
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-35 | Mechanical rough in hallways & stairwells on 2nd | 2024-11-01 | 2024-11-15
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-35 | Mechanical rough in hallways & stairwells on 3rd | 2024-10-28 | 2024-11-07
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-35 | Mechanical rough in hallways stairwells on 4th | 2024-10-21 | 2024-10-25
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-35 | Mechanical rough in in ceiling | 2024-08-05 | 2024-08-14
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-35 | Mechanical rough in on 2nd | 2024-11-01 | 2024-11-15
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-35 | Mechanical rough in on 3rd | 2024-10-28 | 2024-11-07
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-35 | Mechanical rough in on 4th | 2024-10-21 | 2024-10-25
Interiors | Finishes | MEPF | #948A54 | MEPF-36 | Paint 1rst coat of color on 1 | 2025-01-10 | 2025-01-16
Interiors | Finishes | MEPF | #948A54 | MEPF-36 | Paint 1st coat of color 2nd floor | 2024-12-27 | 2025-01-03
Interiors | Finishes | MEPF | #948A54 | MEPF-36 | Paint 1st coat of color on 3rd | 2024-12-12 | 2024-12-17
Interiors | Finishes | MEPF | #948A54 | MEPF-36 | Paint 1st coat of color on 4th | 2024-12-05 | 2024-12-10
Interiors | Finishes | MEPF | #948A54 | MEPF-37 | Parkade - Measurement for template | 2025-01-21 | 2025-01-21
Interiors | Finishes | MEPF | #948A54 | MEPF-37 | Parkade - Taper to rectify deficiencies | 2025-01-07 | 2025-01-07
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-38 | Poly 4th floor ceiling | 2024-09-05 | 2024-09-06
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-39 | Poly and insulate on 2nd exterior walls | 2024-11-25 | 2024-11-28
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-39 | Poly and insulate on 3rd exterior walls | 2024-11-12 | 2024-11-15
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-39 | Poly and insulate on 4th exterior walls | 2024-11-05 | 2024-11-07
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-39 | Poly and insulate parkade exterior walls | 2024-08-22 | 2024-08-23
Interiors | Finishes | MEPF | #948A54 | MEPF-40 | Prime paint on 1 | 2025-01-03 | 2025-01-07
Interiors | Finishes | MEPF | #948A54 | MEPF-40 | Prime paint on 2nd | 2024-12-18 | 2024-12-23
Interiors | Finishes | MEPF | #948A54 | MEPF-40 | Prime paint on 3rd | 2024-12-05 | 2024-12-10
Interiors | Finishes | MEPF | #948A54 | MEPF-40 | Prime paint on 4th | 2024-11-28 | 2024-12-03
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-41 | Rough in 2nd floor | 2024-08-12 | 2025-01-03
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-41 | Rough in 3rd floor | 2024-08-19 | 2024-12-13
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-41 | Rough in 4th floor | 2024-08-19 | 2024-12-06
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-41 | Rough in 4th floor ceiling | 2024-08-05 | 2024-10-07
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-41 | Rough in exterior walls - parkade and sheds | 2024-11-18 | 2024-12-06
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-41 | Rough in exterior walls on 2nd and sheds | 2024-11-08 | 2024-11-21
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-41 | Rough in exterior walls on 3rd and sheds | 2024-10-28 | 2024-11-08
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-41 | Rough in exterior walls on 4th and sheds | 2024-10-21 | 2024-10-31
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-41 | Rough in interior walls | 2024-11-21 | 2024-12-04
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-41 | Rough in Parkade | 2024-08-19 | 2025-01-23
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-42 | Siding 2nd floor | 2024-11-22 | 2024-12-09
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-42 | Siding 3rd floor | 2024-11-06 | 2024-11-21
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-42 | Siding 4th floor | 2024-10-21 | 2024-11-05
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-42 | Siding parkade level | 2024-12-10 | 2024-12-23
Interiors | Finishes | MEPF | #948A54 | MEPF-43 | Spray out closet interiors and trim on 1 | 2025-01-10 | 2025-01-10
Interiors | Finishes | MEPF | #948A54 | MEPF-43 | Spray out closet interiors and trim on 3rd | 2024-12-12 | 2024-12-17
Interiors | Finishes | MEPF | #948A54 | MEPF-43 | Spray out closet interiors and trim on 4th | 2024-12-05 | 2024-12-10
Interiors | Finishes | MEPF | #948A54 | MEPF-44 | Sprinkler finishing 2nd floor | 2025-02-07 | 2025-02-13
Interiors | Finishes | MEPF | #948A54 | MEPF-44 | Sprinkler finishing on 1 | 2025-02-11 | 2025-02-13
Interiors | Finishes | MEPF | #948A54 | MEPF-44 | Sprinkler finishing on 3rd | 2025-01-29 | 2025-02-04
Interiors | Finishes | MEPF | #948A54 | MEPF-44 | Sprinkler finishing on 4th | 2025-01-21 | 2025-01-27
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-45 | Sprinkler install in attic | 2024-08-07 | 2024-08-21
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-46 | Sprinkler rough in corridor & stairwells on 2nd | 2024-08-26 | 2024-09-06
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-46 | Sprinkler rough in hallways & stairwells on 3rd | 2024-09-09 | 2024-09-20
Commissioning | Commissioning | CX | #000000 | CX-1 | Assign Unit Commissioning Inspection list on 4th | 2025-02-07 | 2025-02-07
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-46 | Sprinkler rough in hallways stairwells on 4th | 2024-09-23 | 2024-09-30
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-46 | Sprinkler rough in on 2nd | 2024-08-26 | 2024-09-06
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-46 | Sprinkler rough in on 3rd | 2024-09-09 | 2024-09-20
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-46 | Sprinkler rough in on 4th | 2024-09-23 | 2024-09-30
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-47 | Steel stud install on 2nd & drywall behind the tubs including fire wall taping if it is a fire wall | 2024-08-12 | 2024-08-29
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-47 | Steel stud install on 3rd & drywall behind the tubs including fire wall taping if it is a fire wall | 2024-08-30 | 2024-09-05
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-47 | Steel stud install on 4th & drywall behind the tubs including fire wall taping if it is a fire wall | 2024-09-18 | 2024-09-26
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-48 | Tape 2nd floor hallways and stair wells | 2024-12-05 | 2024-12-19
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-48 | Tape 3rd floor hallways and stair wells | 2024-11-22 | 2024-12-05
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-48 | Tape 4th floor ceiling | 2024-09-23 | 2024-10-04
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-48 | Tape 4th floor hallways and stair wells | 2024-11-15 | 2024-11-28
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-48 | Tape parkade interior and exterior walls | 2024-12-13 | 2024-12-23
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-48 | Tape suites on 2nd | 2024-12-05 | 2024-12-19
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-48 | Tape suites on 3rd | 2024-11-22 | 2024-12-05
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-48 | Tape suites on 4th | 2024-11-15 | 2024-11-28
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-49 | Water dams 2nd floor | 2024-08-19 | 2024-08-23
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-49 | Water dams 3rd floor | 2024-08-19 | 2024-08-23
Interiors | Rough-Ins | MEPF | #948A54 | MEPF-49 | Water dams 4th floor | 2024-08-19 | 2024-08-23
Exteriors & Landscaping |  | Exterior Subs | #DA9694 | LAND-1 | Exterior | 2024-08-09 | 2025-05-05
Exteriors & Landscaping |  | Exterior Subs | #DA9694 | LAND-2 | Grind all balconys smooth | 2024-08-09 | 2024-08-22
Exteriors & Landscaping |  | Exterior Subs | #DA9694 | LAND-3 | Install exterior decking all floors | 2024-09-03 | 2024-09-16
Exteriors & Landscaping |  | Exterior Subs | #DA9694 | LAND-4 | Assign post decking install check list | 2024-09-17 | 2024-09-17
Exteriors & Landscaping |  | Exterior Subs | #DA9694 | LAND-5 | Install railings on all floors | 2025-01-20 | 2025-02-06
Exteriors & Landscaping |  | Exterior Subs | #DA9694 | LAND-6 | Rough grade landscaping | 2025-04-04 | 2025-04-10
Exteriors & Landscaping |  | Exterior Subs | #DA9694 | LAND-7 | Install underground sprinklers | 2025-04-11 | 2025-04-17
Exteriors & Landscaping |  | Exterior Subs | #DA9694 | LAND-8 | Install landscaping | 2025-04-18 | 2025-05-01
Exteriors & Landscaping |  | Exterior Subs | #DA9694 | LAND-9 | Commision landscaping | 2025-05-02 | 2025-05-05
Exteriors & Landscaping |  | Exterior Subs | #DA9694 | LAND-10 | Install building signage | 2025-02-28 | 2025-02-28
Exteriors & Landscaping |  | Exterior Subs | #DA9694 | LAND-11 | Assign post landscaping checklist | 2025-05-02 | 2025-05-02
Commissioning | Commissioning | Construction Company | #632523 | CX-2 | Final commissioning and deficiency | 2025-02-14 | 2025-03-03
Commissioning | Commissioning | Construction Company | #632523 | CX-3 | Fire alarm verification | 2025-02-14 | 2025-02-17
Commissioning | Commissioning | Construction Company | #632523 | CX-4 | Contact Canada Post to get the address's created | 2025-02-14 | 2025-02-14
Commissioning | Commissioning | Construction Company | #632523 | CX-5 | Enginering walk throughs | 2025-02-19 | 2025-02-20
Commissioning | Commissioning | Construction Company | #632523 | CX-6 | Organize 3rd party building exterior review, including roof, siding and flashings | 2025-02-19 | 2025-02-19
Commissioning | Commissioning | Construction Company | #632523 | CX-7 | Sprinkler testing | 2025-02-14 | 2025-02-17
Commissioning | Commissioning | Construction Company | #632523 | CX-8 | Archetectural walk throughs | 2025-02-19 | 2025-02-20
Commissioning | Commissioning | Construction Company | #632523 | CX-9 | Building inspector walk throughs | 2025-02-21 | 2025-02-24
Commissioning | Commissioning | Construction Company | #632523 | CX-10 | Elevator commissioning | 2025-02-14 | 2025-02-17
Commissioning | Commissioning | Construction Company | #632523 | CX-11 | Prepare occupancy paperwork | 2025-02-25 | 2025-02-26
Commissioning | Commissioning | Construction Company | #632523 | CX-12 | Receive occupancy | 2025-02-27 | 2025-02-28
Commissioning | Commissioning | Construction Company | #632523 | CX-13 | Move in dates confirmed | 2025-03-03 | 2025-03-03
Commissioning | Commissioning | Construction Company | #632523 | CX-14 | Assign Final Building Checklist | 2025-03-03 | 2025-03-03
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-15 | 5.0 Sales, Occupancy, Closings | 2025-03-03 | 2025-05-01
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-16 | Pre sale move in dates confirmed | 2025-03-03 | 2025-03-03
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-17 | Finalize home owner extras | 2025-03-04 | 2025-03-10
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-18 | Load home owners into copper | 2025-03-04 | 2025-03-04
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-19 | Move in binders created | 2025-03-04 | 2025-03-10
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-20 | Update home owner permissions in Construction online | 2025-03-04 | 2025-03-04
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-21 | Unit Commissioning Inspection list | 2025-03-04 | 2025-03-10
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-22 | Unit Commissioning deficiency clean up confirmed | 2025-03-11 | 2025-03-17
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-23 | Building close out check list | 2025-03-04 | 2025-03-04
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-24 | Building close out cleanup deficiencies confirmed | 2025-03-05 | 2025-03-11
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-25 | Building handover (PM to SM) checklist | 2025-03-04 | 2025-03-10
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-26 | De mobilization (checklist) | 2025-03-05 | 2025-03-11
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-27 | Keys and gift cards and welcome package created | 2025-03-04 | 2025-03-10
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-28 | Home owner walk through and punch list | 2025-03-11 | 2025-03-11
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-29 | Home owner walk through punch list clean up | 2025-03-12 | 2025-03-18
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-30 | New move ins and warranty through service manager | 2025-03-04 | 2025-05-01
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-31 | Send out contractor surveys | 2025-03-05 | 2025-03-05
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-32 | Schedule 1 on 1 contractor review meetings | 2025-03-06 | 2025-03-12
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-33 | Schedule contractor group meeting to review survey results | 2025-03-06 | 2025-03-12
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-34 | Project post mordem internal | 2025-03-13 | 2025-03-13
Occupancy & Closing | Occupancy & Closing | Construction Company | #632523 | CX-35 | Move info to Dev co work flow 1.0, 2.0, 6.0 | 2025-03-18 | 2025-03-18

## CFA - Schedule
|  | 2023 | [94 empty] | 2024 | [365 empty] | 2025
|  | Sep |  |  | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [28 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May
|  | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05
phase | location | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
Precon | Prep | Sep 28: PRE-13; Dec 08: PRE-15
PRE-14
|  | PRE-12 | PRE-12 | PRE-12 | PRE-12 | PRE-12
|  | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2 | PRE-2
|  | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3 | PRE-3
|  | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4 | PRE-4
|  | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5 | PRE-5
|  | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6 | PRE-6
|  | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7 | PRE-7
|  | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8 | PRE-8
|  | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9 | PRE-9
|  | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10 | PRE-10
|  | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11 | PRE-11
|  | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1 | PRE-1
Sitework | Site | Dec 21: SITE-4; Dec 25: SITE-9; Dec 26: SITE-9; Dec 27: SITE-9; Dec 28: SITE-3; Dec 29: SITE-10; Dec 30: SITE-10; Dec 31: SITE-10; Jan 01: SITE-10; Jan 02: SITE-10; Jan 03: SITE-10; Jan 04: SITE-10; Jan 05: SITE-11; Jan 08: SITE-13; Jan 17: SITE-15; Jan 18: SITE-16
[86 empty] | SITE-5 | [17 empty] | SITE-14 | SITE-14 | SITE-14 | SITE-14 | SITE-14 | SITE-14 | SITE-14 | SITE-14 | SITE-14
[86 empty] | SITE-8 | [17 empty] | SITE-12 | SITE-12 | SITE-12 | SITE-12 | SITE-12 | SITE-12 | SITE-12 | SITE-12 | SITE-12 | SITE-12 | SITE-12
[86 empty] | SITE-7 | SITE-7
[86 empty] | SITE-6 | SITE-6 | SITE-6 | SITE-6 | SITE-6 | SITE-6 | SITE-6
[86 empty] | SITE-2 | SITE-2 | SITE-2 | SITE-2 | SITE-2 | SITE-2 | SITE-2 | SITE-2 | SITE-2 | SITE-2 | SITE-2 | SITE-2 | SITE-2 | SITE-2 | SITE-2 | SITE-2
Sitework & Foundations | Site | Dec 21: SITE-1; Dec 22: SITE-1; Dec 23: SITE-1; Dec 24: SITE-1; Dec 25: SITE-1; Dec 26: SITE-1; Dec 27: SITE-1; Dec 28: SITE-1; Dec 29: SITE-1; Dec 30: SITE-1; Dec 31: SITE-1; Jan 01: SITE-1; Jan 02: SITE-1; Jan 03: SITE-1; Jan 04: SITE-1; Jan 05: SITE-1; Jan 06: SITE-1; Jan 07: SITE-1; Jan 08: SITE-1; Jan 09: SITE-1; Jan 10: SITE-1; Jan 11: SITE-1; Jan 12: SITE-1; Jan 13: SITE-1; Jan 14: SITE-1; Jan 15: SITE-1; Jan 16: SITE-1; Jan 17: SITE-1; Jan 18: SITE-1; Jan 19: SITE-1; Jan 20: SITE-1; Jan 21: SITE-1; Jan 22: SITE-1; Jan 23: SITE-1; Jan 24: SITE-1; Jan 25: SITE-1; Jan 26: SITE-1; Jan 27: SITE-1; Jan 28: SITE-1; Jan 29: SITE-1; Jan 30: SITE-1; Jan 31: SITE-1; Feb 01: SITE-1; Feb 02: SITE-1; Feb 03: SITE-1; Feb 04: SITE-1; Feb 05: SITE-1; Feb 06: SITE-1; Feb 07: SITE-1; Feb 08: SITE-1; Feb 09: SITE-1; Feb 10: SITE-1; Feb 11: SITE-1; Feb 12: SITE-1; Feb 13: SITE-1; Feb 14: SITE-1; Feb 15: SITE-1; Feb 16: SITE-1; Feb 17: SITE-1; Feb 18: SITE-1; Feb 19: SITE-1; Feb 20: SITE-1; Feb 21: SITE-1; Feb 22: SITE-1; Feb 23: SITE-1; Feb 24: SITE-1; Feb 25: SITE-1; Feb 26: SITE-1; Feb 27: SITE-1; Feb 28: SITE-1; Feb 29: SITE-1; Mar 01: SITE-1; Mar 02: SITE-1; Mar 03: SITE-1; Mar 04: SITE-1; Mar 05: SITE-1; Mar 06: SITE-1; Mar 07: SITE-1; Mar 08: SITE-1; Mar 09: SITE-1; Mar 10: SITE-1; Mar 11: SITE-1; Mar 12: SITE-1; Mar 13: SITE-1; Mar 14: SITE-1; Mar 15: SITE-1; Mar 16: SITE-1; Mar 17: SITE-1; Mar 18: SITE-1; Mar 19: SITE-1; Mar 20: SITE-1; Mar 21: SITE-1; Mar 22: SITE-1; Mar 23: SITE-1; Mar 24: SITE-1; Mar 25: SITE-1
Foundations | Bellow the Ground | Jan 19: FOUND-2; Jan 20: FOUND-2; Jan 21: FOUND-2; Jan 22: FOUND-2; Jan 23: FOUND-2; Jan 24: FOUND-2; Jan 25: FOUND-3; Jan 26: FOUND-3; Jan 27: FOUND-3; Jan 28: FOUND-3; Jan 29: FOUND-3; Jan 30: FOUND-3; Jan 31: FOUND-3; Feb 01: FOUND-4; Feb 02: FOUND-5; Feb 05: FOUND-6; Feb 06: FOUND-10; Feb 15: FOUND-8; Feb 16: FOUND-9; Feb 17: FOUND-9; Feb 18: FOUND-9; Feb 19: FOUND-9; Feb 20: FOUND-9; Feb 21: FOUND-9; Feb 22: FOUND-9; Feb 23: FOUND-9; Feb 24: FOUND-9; Feb 25: FOUND-9; Feb 26: FOUND-9; Feb 27: FOUND-11; Feb 28: FOUND-12; Feb 29: FOUND-13; Mar 01: FOUND-15; Mar 04: FOUND-16; Mar 05: FOUND-16; Mar 06: FOUND-17; Mar 07: FOUND-17; Mar 08: FOUND-18; Mar 09: FOUND-18; Mar 10: FOUND-18; Mar 11: FOUND-18; Mar 12: FOUND-18; Mar 13: FOUND-18; Mar 14: FOUND-18; Mar 15: FOUND-20; Mar 18: FOUND-26; Mar 20: FOUND-27; Mar 21: FOUND-27; Mar 25: FOUND-22
[115 empty] | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-1 | FOUND-14 | FOUND-14 | FOUND-14 | FOUND-14 | FOUND-14 | FOUND-14 | FOUND-14 | FOUND-14 | FOUND-14 | FOUND-14 | FOUND-14 | FOUND-14 | FOUND-14 | FOUND-14 | FOUND-25 |  |  | FOUND-21 | FOUND-21 | FOUND-21 | FOUND-21 | FOUND-21 |  |  | FOUND-23
[133 empty] | FOUND-7 | FOUND-7 | FOUND-7 | FOUND-7 | FOUND-7 | FOUND-7 | FOUND-7 | FOUND-7 | FOUND-7 | [29 empty] | FOUND-24 | FOUND-24 | FOUND-24 | FOUND-24 | FOUND-24 | FOUND-24 | FOUND-24
[171 empty] | FOUND-19 | FOUND-19 | FOUND-19 | FOUND-19 | FOUND-19 | FOUND-19 | FOUND-19 | FOUND-19 | FOUND-19 | FOUND-19 | FOUND-19
Framing & RI | Structure | Apr 11: STR-15; Apr 12: STR-15; Apr 13: STR-15; Apr 14: STR-15; Apr 15: STR-15; Apr 16: STR-16; Apr 19: STR-19; May 14: STR-23; May 23: STR-24; May 24: STR-24; May 25: STR-24; May 26: STR-24; May 27: STR-24; May 28: STR-24; Jun 10: STR-29; Jun 11: STR-33; Jun 12: STR-33; Jun 13: STR-34; Jun 17: STR-20; Jun 19: STR-5; Jun 20: STR-6; Jun 21: STR-6; Jun 22: STR-6; Jun 23: STR-6; Jun 24: STR-6; Jun 25: STR-6; Jun 26: STR-6; Jun 27: STR-8; Jun 28: STR-9; Jun 29: STR-9; Jun 30: STR-9; Jul 01: STR-9; Jul 02: STR-10; Jul 03: STR-11; Jul 04: STR-11; Jul 05: STR-11; Jul 08: STR-12; Jul 09: STR-13; Jul 10: STR-13; Jul 18: STR-30; Jul 19: STR-30; Jul 20: STR-30; Jul 21: STR-30; Jul 22: STR-30; Jul 23: STR-38; Jul 24: STR-38; Jul 25: STR-38; Jul 26: STR-38; Jul 29: STR-39; Jul 30: STR-39; Jul 31: STR-39; Aug 01: STR-45; Aug 02: STR-45; Aug 07: STR-42; Aug 20: STR-43
[198 empty] | STR-14 | STR-14 | STR-14 | STR-14 | STR-14 | STR-14 |  |  | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | STR-22 | [9 empty] | STR-25 | STR-25 | STR-25 | STR-25 | STR-25 | STR-25 | [13 empty] | STR-32 | STR-32 | STR-32 | [5 empty] | STR-36 | STR-36 | STR-36 | STR-36 | STR-36 | STR-36 | STR-36 | STR-36 | STR-36 | STR-36 | STR-36 | STR-36 | STR-36 | STR-36 | STR-36 | STR-36 | STR-36 |  |  | STR-37 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41 | STR-41
[198 empty] | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1 | STR-1
[203 empty] | STR-18 | STR-18 | STR-18 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | STR-21 | [12 empty] | STR-26 | STR-28 | STR-28 | STR-28 | STR-28 | STR-28 | STR-28 | STR-28 | STR-28 | STR-28 | STR-28 | STR-28 |  |  |  |  | STR-3 | STR-3 | STR-3 | STR-3 | STR-3 | STR-3 | STR-3 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35 | STR-35
[203 empty] | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | STR-17 | [9 empty] | STR-7 | STR-7 | STR-7 | STR-7 | STR-7 | STR-7 | STR-7 | STR-7 | STR-7 | STR-7 | STR-7 | STR-7 | STR-7 | STR-7 | [13 empty] | STR-31 | STR-31 | STR-31 |  |  | STR-44 | STR-44 | STR-44 | STR-44
[245 empty] | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27 | STR-27
[260 empty] | STR-4 | STR-4 | STR-4 | STR-4 | STR-4 | STR-4 | STR-4 | [20 empty] | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40 | STR-40
[260 empty] | STR-2 | STR-2 | STR-2 | STR-2 | STR-2 | STR-2 | STR-2 | STR-2 | STR-2 | STR-2 | STR-2 | STR-2 | STR-2 | STR-2 | STR-2
Interiors | Finishes | Aug 09: MEPF-4; Aug 10: MEPF-4; Aug 11: MEPF-4; Aug 12: MEPF-4; Aug 13: MEPF-4; Aug 14: MEPF-4; Aug 15: MEPF-4; Aug 16: MEPF-4; Aug 17: MEPF-4; Aug 18: MEPF-4; Aug 19: MEPF-4; Aug 20: MEPF-4; Aug 21: MEPF-4; Aug 22: MEPF-4; Aug 23: MEPF-4; Aug 24: MEPF-4; Aug 25: MEPF-4; Aug 26: MEPF-4; Aug 27: MEPF-4; Aug 28: MEPF-4; Aug 29: MEPF-4; Aug 30: MEPF-4; Aug 31: MEPF-4; Sep 01: MEPF-4; Sep 02: MEPF-4; Sep 03: MEPF-4; Sep 04: MEPF-4; Sep 05: MEPF-4; Sep 06: MEPF-4; Sep 07: MEPF-4; Sep 08: MEPF-4; Sep 09: MEPF-4; Sep 10: MEPF-4; Sep 11: MEPF-4; Sep 12: MEPF-4; Sep 13: MEPF-4; Sep 14: MEPF-4; Sep 15: MEPF-4; Sep 16: MEPF-4; Sep 17: MEPF-4; Sep 18: MEPF-4; Sep 19: MEPF-4; Sep 20: MEPF-4; Sep 21: MEPF-4; Sep 22: MEPF-4; Sep 23: MEPF-4; Sep 24: MEPF-4; Sep 25: MEPF-4; Sep 26: MEPF-4; Sep 27: MEPF-4; Sep 28: MEPF-4; Sep 29: MEPF-4; Sep 30: MEPF-4; Oct 01: MEPF-4; Oct 02: MEPF-4; Oct 03: MEPF-4; Oct 04: MEPF-4; Oct 05: MEPF-4; Oct 06: MEPF-4; Oct 07: MEPF-4; Oct 08: MEPF-4; Oct 09: MEPF-4; Oct 10: MEPF-4; Oct 11: MEPF-4; Oct 12: MEPF-4; Oct 13: MEPF-4; Oct 14: MEPF-4; Oct 15: MEPF-4; Oct 16: MEPF-4; Oct 17: MEPF-4; Oct 18: MEPF-4; Oct 19: MEPF-4; Oct 20: MEPF-4; Oct 21: MEPF-4; Oct 22: MEPF-4; Oct 23: MEPF-4; Oct 24: MEPF-4; Oct 25: MEPF-4; Oct 26: MEPF-4; Oct 27: MEPF-4; Oct 28: MEPF-4; Oct 29: MEPF-4; Oct 30: MEPF-4; Oct 31: MEPF-4; Nov 01: MEPF-4; Nov 02: MEPF-4; Nov 03: MEPF-4; Nov 04: MEPF-4; Nov 05: MEPF-4; Nov 06: MEPF-4; Nov 07: MEPF-4; Nov 08: MEPF-4; Nov 09: MEPF-4; Nov 10: MEPF-4; Nov 11: MEPF-4; Nov 12: MEPF-4; Nov 13: MEPF-4; Nov 14: MEPF-4; Nov 15: MEPF-4; Nov 16: MEPF-4; Nov 17: MEPF-4; Nov 18: MEPF-4; Nov 19: MEPF-4; Nov 20: MEPF-4; Nov 21: MEPF-4; Nov 22: MEPF-4; Nov 23: MEPF-4; Nov 24: MEPF-4; Nov 25: MEPF-4; Nov 26: MEPF-4; Nov 27: MEPF-4; Nov 28: MEPF-4; Nov 29: MEPF-4; Nov 30: MEPF-4; Dec 01: MEPF-4; Dec 02: MEPF-4; Dec 03: MEPF-4; Dec 04: MEPF-4; Dec 05: MEPF-4; Dec 06: MEPF-4; Dec 07: MEPF-4; Dec 08: MEPF-4; Dec 09: MEPF-4; Dec 10: MEPF-4; Dec 11: MEPF-4; Dec 12: MEPF-4; Dec 13: MEPF-4; Dec 14: MEPF-4; Dec 15: MEPF-4; Dec 16: MEPF-4; Dec 17: MEPF-4; Dec 18: MEPF-4; Dec 19: MEPF-4; Dec 20: MEPF-4; Dec 21: MEPF-4; Dec 22: MEPF-4; Dec 23: MEPF-4; Dec 24: MEPF-4; Dec 25: MEPF-4; Dec 26: MEPF-4; Dec 27: MEPF-4; Dec 28: MEPF-4; Dec 29: MEPF-4; Dec 30: MEPF-4; Dec 31: MEPF-4; Jan 01: MEPF-4; Jan 02: MEPF-4; Jan 03: MEPF-4; Jan 04: MEPF-4; Jan 05: MEPF-4; Jan 06: MEPF-4; Jan 07: MEPF-4; Jan 08: MEPF-4; Jan 09: MEPF-4; Jan 10: MEPF-4; Jan 11: MEPF-4; Jan 12: MEPF-4; Jan 13: MEPF-4; Jan 14: MEPF-4; Jan 15: MEPF-4; Jan 16: MEPF-4; Jan 17: MEPF-4; Jan 18: MEPF-4; Jan 19: MEPF-4; Jan 20: MEPF-4; Jan 21: MEPF-4; Jan 22: MEPF-4; Jan 23: MEPF-4; Jan 24: MEPF-4; Jan 25: MEPF-4; Jan 26: MEPF-4; Jan 27: MEPF-4; Jan 28: MEPF-4; Jan 29: MEPF-4; Jan 30: MEPF-4; Jan 31: MEPF-4; Feb 01: MEPF-4; Feb 02: MEPF-4; Feb 03: MEPF-4; Feb 04: MEPF-4; Feb 05: MEPF-4; Feb 06: MEPF-4; Feb 07: MEPF-4; Feb 08: MEPF-4; Feb 09: MEPF-4; Feb 10: MEPF-4; Feb 11: MEPF-4; Feb 12: MEPF-4; Feb 13: MEPF-4; Feb 14: MEPF-4; Feb 15: MEPF-4; Feb 16: MEPF-4; Feb 17: MEPF-4; Feb 18: MEPF-4; Feb 19: MEPF-4; Feb 20: MEPF-4; Feb 21: MEPF-4; Feb 22: MEPF-4; Feb 23: MEPF-4; Feb 24: MEPF-4; Feb 25: MEPF-4; Feb 26: MEPF-4; Feb 27: MEPF-4; Feb 28: MEPF-4; Mar 01: MEPF-4; Mar 02: MEPF-4; Mar 03: MEPF-4; Mar 04: MEPF-4; Mar 05: MEPF-4; Mar 06: MEPF-4; Mar 07: MEPF-4; Mar 08: MEPF-4; Mar 09: MEPF-4; Mar 10: MEPF-4; Mar 11: MEPF-4; Mar 12: MEPF-4; Mar 13: MEPF-4; Mar 14: MEPF-4; Mar 15: MEPF-4; Mar 16: MEPF-4; Mar 17: MEPF-4; Mar 18: MEPF-4; Mar 19: MEPF-4; Mar 20: MEPF-4; Mar 21: MEPF-4; Mar 22: MEPF-4; Mar 23: MEPF-4; Mar 24: MEPF-4; Mar 25: MEPF-4; Mar 26: MEPF-4; Mar 27: MEPF-4; Mar 28: MEPF-4; Mar 29: MEPF-4; Mar 30: MEPF-4; Mar 31: MEPF-4; Apr 01: MEPF-4; Apr 02: MEPF-4; Apr 03: MEPF-4; Apr 04: MEPF-4; Apr 05: MEPF-4; Apr 06: MEPF-4; Apr 07: MEPF-4; Apr 08: MEPF-4; Apr 09: MEPF-4; Apr 10: MEPF-4; Apr 11: MEPF-4; Apr 12: MEPF-4; Apr 13: MEPF-4; Apr 14: MEPF-4; Apr 15: MEPF-4; Apr 16: MEPF-4; Apr 17: MEPF-4; Apr 18: MEPF-4; Apr 19: MEPF-4; Apr 20: MEPF-4; Apr 21: MEPF-4; Apr 22: MEPF-4; Apr 23: MEPF-4; Apr 24: MEPF-4; Apr 25: MEPF-4; Apr 26: MEPF-4; Apr 27: MEPF-4; Apr 28: MEPF-4; Apr 29: MEPF-4; Apr 30: MEPF-4; May 01: MEPF-4; May 02: MEPF-4; May 03: MEPF-4; May 04: MEPF-4; May 05: MEPF-4
[427 empty] | MEPF-11 | MEPF-11 | MEPF-40 | MEPF-40 | MEPF-40 | MEPF-40 | MEPF-40 | MEPF-40 |  | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 |  | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 |  |  |  | MEPF-37 | MEPF-23 | MEPF-23 | MEPF-43 |  |  | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 |  |  |  | MEPF-37 |  |  | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 |  | Cl-2 | Cl-2 | Cl-2 | Cl-2 | MEPF-12 | MEPF-12 | MEPF-12 | Cl-1 | Cl-1 | Cl-1 | Cl-1 | Cl-1 | CC-1 | Cl-2 | Cl-2 | Cl-2 | Cl-2 | Cl-2 |  |  | CC-1
[427 empty] | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-17 | MEPF-34 | MEPF-34 | MEPF-34 |  |  |  | CC-1 | [6 empty] | Cl-1 | Cl-1 | Cl-1 | Cl-1
[433 empty] | D-1 | D-1 |  | MEPF-40 | MEPF-40 | MEPF-40 | MEPF-40 | MEPF-40 | MEPF-40 |  | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-40 | MEPF-40 | MEPF-40 | MEPF-40 | MEPF-40 | MEPF-40 |  |  |  | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 |  |  |  |  | MEPF-1 | MEPF-1 | MEPF-1 |  |  |  |  | MEPF-22 | MEPF-22 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-12 | MEPF-12 | MEPF-12 | MEPF-12 | MEPF-12 | MEPF-12 | MEPF-12 |  | MEPF-12 | MEPF-12 | MEPF-12 | MEPF-12 | MEPF-12 | MEPF-12 | MEPF-12 |  |  | MEPF-12 | MEPF-12 | MEPF-12 | MEPF-12 | MEPF-12 | MEPF-12 | MEPF-12 |  |  |  | Cl-2 | Cl-2 | [8 empty] | Cl-2 | Cl-2
[433 empty] | MEPF-11 | MEPF-11 |  | MEPF-43 | MEPF-43 | MEPF-43 | MEPF-43 | MEPF-43 | MEPF-43 |  | MEPF-43 | MEPF-43 | MEPF-43 | MEPF-43 | MEPF-43 | MEPF-43 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | MEPF-20 | [5 empty] | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-1 | MEPF-34 | MEPF-34 | MEPF-34 | MEPF-34 | MEPF-34 | MEPF-34 | MEPF-34 |  | MEPF-34 | MEPF-34 | MEPF-34 | MEPF-34 | MEPF-34 | MEPF-34 | MEPF-34 |  |  | MEPF-34 | MEPF-34 | MEPF-34 | MEPF-34 | MEPF-34 | MEPF-34 | MEPF-34
[433 empty] | MEPF-23 | MEPF-23 | MEPF-23 | MEPF-23 | MEPF-23 |  |  | MEPF-23 | MEPF-23 | MEPF-23 | MEPF-23 | MEPF-23 |  |  | MEPF-11 | MEPF-11 | [5 empty] | D-1 | [9 empty] | MEPF-11 | MEPF-11 |  |  |  |  | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 |  |  |  | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 | MEPF-19 |  |  |  |  | MEPF-44 | MEPF-44 | MEPF-44 | MEPF-44 | MEPF-44 | MEPF-44 | MEPF-44 |  |  | MEPF-44 | MEPF-44 | MEPF-44 | MEPF-44 | MEPF-44 | MEPF-44 | MEPF-44
[433 empty] | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2
[440 empty] | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-5 | MEPF-5 | MEPF-5 |  |  |  | MEPF-23 | MEPF-23 | MEPF-23 | MEPF-23 | MEPF-23 | MEPF-23 | MEPF-23 | MEPF-23 | MEPF-23 | MEPF-23 | MEPF-23 | MEPF-23 |  |  |  |  | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 |  |  |  |  | MEPF-44 | MEPF-44 | MEPF-44 | MEPF-44 | MEPF-44 | MEPF-44 | MEPF-44 | [6 empty] | Cl-1 | Cl-1 | Cl-1 | Cl-1 | Cl-1 |  |  | MEPF-21 | MEPF-44 | MEPF-44 | MEPF-44
[441 empty] | D-1 | [5 empty] | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2 | MEPF-2
[448 empty] | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 | MEPF-22 |  |  | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 | MEPF-36 |  |  |  |  | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 |  |  |  | Cl-1 | Cl-1 | Cl-1 | Cl-1 | Cl-1 | Cl-1 | Cl-1
[464 empty] | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | [12 empty] | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16
[464 empty] | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18 | MEPF-18
[465 empty] | MEPF-40 | MEPF-40 | MEPF-40 | MEPF-40 | MEPF-40 |  |  | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | MEPF-33 | [14 empty] | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16 | MEPF-16
| Rough-Ins | Aug 05: MEPF-35; Aug 06: MEPF-35; Aug 07: MEPF-35; Aug 08: MEPF-35; Aug 09: MEPF-35; Aug 10: MEPF-35; Aug 11: MEPF-35; Aug 12: MEPF-35; Aug 13: MEPF-35; Aug 14: MEPF-35; Aug 19: D-17; Aug 20: D-17; Aug 21: D-17; Aug 22: D-17; Aug 23: D-17; Aug 26: MEPF-14; Aug 27: MEPF-14; Aug 28: MEPF-14; Aug 29: MEPF-14; Aug 30: MEPF-14; Aug 31: MEPF-14; Sep 01: MEPF-14; Sep 02: MEPF-14; Sep 03: MEPF-14; Sep 04: MEPF-9; Sep 05: MEPF-38; Sep 06: MEPF-38; Sep 09: MEPF-26; Sep 10: MEPF-26; Sep 11: D-13; Sep 12: D-13; Sep 13: D-13; Sep 14: D-13; Sep 15: D-13; Sep 16: D-13; Sep 18: MEPF-7; Sep 19: MEPF-7; Sep 20: MEPF-7; Sep 23: D-7; Sep 24: D-7; Sep 25: D-7; Sep 26: D-7; Sep 27: D-7; Oct 07: D-6; Oct 21: MEPF-35; Oct 22: MEPF-35; Oct 23: MEPF-35; Oct 24: MEPF-35; Oct 25: MEPF-35; Oct 28: MEPF-35; Oct 29: MEPF-35; Oct 30: MEPF-35; Oct 31: MEPF-35; Nov 01: MEPF-35; Nov 02: MEPF-35; Nov 03: MEPF-35; Nov 04: MEPF-35; Nov 05: MEPF-35; Nov 06: MEPF-35; Nov 07: MEPF-35; Nov 08: D-3; Nov 11: D-14; Nov 12: D-3; Nov 15: D-4; Nov 18: MEPF-41; Nov 19: MEPF-41; Nov 20: MEPF-41; Nov 21: MEPF-41; Nov 22: MEPF-41; Nov 23: MEPF-41; Nov 24: MEPF-41; Nov 25: MEPF-41; Nov 26: MEPF-41; Nov 27: MEPF-41; Nov 28: MEPF-41; Nov 29: MEPF-41; Nov 30: MEPF-41; Dec 01: MEPF-41; Dec 02: MEPF-41; Dec 03: MEPF-41; Dec 04: MEPF-41; Dec 05: MEPF-41; Dec 06: MEPF-41; Dec 09: D-11; Dec 10: D-5; Dec 13: MEPF-48; Dec 14: MEPF-48; Dec 15: MEPF-48; Dec 16: MEPF-48; Dec 17: MEPF-48; Dec 18: MEPF-48; Dec 19: MEPF-48; Dec 20: MEPF-48; Dec 21: MEPF-48; Dec 22: MEPF-48; Dec 23: MEPF-48; Dec 24: D-5; Jan 22: D-4; Jan 23: MEPF-8
[314 empty] | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | [13 empty] | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 |  |  | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | D-4 |  |  |  | MEPF-9 |  |  | D-4 | [5 empty] | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | D-6 | D-9 | D-9 | D-9 | D-9 | D-9 | [5 empty] | D-15 | D-15 | D-15 | D-15 | D-15 |  |  | D-6 | MEPF-24 | MEPF-24 | MEPF-24 | MEPF-24 | MEPF-24 | MEPF-24 | MEPF-24 | MEPF-24 | MEPF-24 | MEPF-24 | MEPF-24 | MEPF-24 | MEPF-24 | MEPF-24 | [15 empty] | D-4
[314 empty] | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3 | MEPF-3
[316 empty] | MEPF-45 | MEPF-45 | MEPF-45 | MEPF-45 | MEPF-45 | MEPF-45 | MEPF-45 | MEPF-45 | MEPF-45 | MEPF-45 | MEPF-45 | MEPF-45 | MEPF-45 | MEPF-45 | MEPF-45 | MEPF-39 | MEPF-39 |  |  | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 |  |  | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 |  |  | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | [20 empty] | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | D-14 |  |  | D-2 | MEPF-39 | MEPF-39 | MEPF-39 | MEPF-6 |  |  |  | MEPF-39 | MEPF-39 | MEPF-39 | MEPF-39 | [6 empty] | D-5 |  |  | D-14 | D-16 | D-16 | D-16 | D-16 | D-16 | D-16 | D-16 |  |  | D-6 |  |  |  | MEPF-27 | MEPF-27 | MEPF-27 | MEPF-27 | MEPF-27 | [5 empty] | D-6 |  |  |  | MEPF-27 | MEPF-27 | MEPF-27 | MEPF-27 | MEPF-27 | MEPF-27 | MEPF-27 | MEPF-27 | MEPF-27 | MEPF-27 | MEPF-27 | MEPF-27
[321 empty] | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | D-13 | D-13 | D-13 | D-13 | D-13 | D-13 |  | MEPF-28 | MEPF-28 | MEPF-28 | MEPF-28 | MEPF-28 | MEPF-28 | [6 empty] | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | D-13 | D-13 | D-13 | D-13 | D-13 | D-13 | [18 empty] | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | [6 empty] | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 |  |  |  |  | D-12 | D-12 | D-12 | D-12 | [5 empty] | D-6
[321 empty] | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41
[328 empty] | MEPF-49 | MEPF-49 | MEPF-49 | MEPF-49 | MEPF-49 |  |  | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 |  |  | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 |  |  | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | MEPF-46 | [20 empty] | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | MEPF-35 | [6 empty] | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 |  |  |  |  | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42
[328 empty] | MEPF-49 | MEPF-49 | MEPF-49 | MEPF-49 | MEPF-49 |  |  |  |  | MEPF-25 | MEPF-25 | MEPF-25 | MEPF-25 | MEPF-25 | MEPF-25 | MEPF-25 |  |  | MEPF-25 | MEPF-25 | MEPF-25 | MEPF-25 | MEPF-25 | MEPF-25 | MEPF-25 | [7 empty] | MEPF-25 | MEPF-25 | MEPF-25 | MEPF-25 | MEPF-25 | MEPF-25 | MEPF-25 | [24 empty] | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | D-5 |  | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | [6 empty] | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42
[328 empty] | MEPF-49 | MEPF-49 | MEPF-49 | MEPF-49 | MEPF-49 | [6 empty] | MEPF-28 | MEPF-28 | MEPF-28 | MEPF-28 | MEPF-28 | MEPF-28 | [5 empty] | D-7 | D-7 | D-7 | D-7 | D-7 | D-7 | D-7 | [6 empty] | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | [23 empty] | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 |  |  |  | D-16 | D-16 | D-16 | D-16 | D-16 | D-16 | D-16 | [6 empty] | GP-1 |  |  | D-3 | D-16 | D-16 | D-16 | D-16 | D-16 | D-16 | D-16
[328 empty] | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41
[328 empty] | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41
[328 empty] | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41
[330 empty] | D-7 | D-7 | D-7 | D-7 | D-7 | D-7 | D-7 |  |  | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | MEPF-47 | [5 empty] | D-18 | D-18 | D-18 | D-18 | D-18 | D-18 | D-18 | [8 empty] | MEPF-28 | MEPF-28 | [30 empty] | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | [6 empty] | D-6 | [9 empty] | MEPF-9 |  |  | D-4 |  |  |  | MEPF-27 | MEPF-27 | MEPF-27 | MEPF-27 | MEPF-27
[398 empty] | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | [6 empty] | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 |  |  | GP-1 | GP-1 |  | D-4 | [6 empty] | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48
[399 empty] | MEPF-10 | MEPF-10 | MEPF-10 | [5 empty] | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 | MEPF-42 |  |  |  | GP-1 | GP-1 |  | D-6 | [6 empty] | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48
[401 empty] | MEPF-8 | [7 empty] | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | [9 empty] | MEPF-39 | MEPF-39 | MEPF-39 | MEPF-39
[409 empty] | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | [12 empty] | D-8 | D-8 | D-8 | D-8 | D-8 | D-8 | D-8
[409 empty] | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | MEPF-41 | [6 empty] | D-8 | D-8 | D-8 | D-8 | D-8 | D-8 | D-8
[409 empty] | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | MEPF-13 | [5 empty] | D-10 | D-10 | D-10 | D-10 | D-10 | D-10 | D-10
[409 empty] | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | MEPF-15 | [5 empty] | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30 | MEPF-30
[416 empty] | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | [5 empty] | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32 | MEPF-32
[416 empty] | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29 | MEPF-29
[416 empty] | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48
[416 empty] | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48 | MEPF-48
Exterior | Building | Jul 08: EXT-3; Jul 17: EXT-2; Jul 18: EXT-2; Jul 30: EXT-5; Aug 01: EXT-4; Aug 02: EXT-4; Aug 03: EXT-4; Aug 04: EXT-4; Aug 05: EXT-4; Aug 06: EXT-4; Aug 07: EXT-4; Aug 08: EXT-4; Aug 09: EXT-4; Aug 10: EXT-4; Aug 11: EXT-4; Aug 12: EXT-4; Aug 13: EXT-4; Aug 26: EXT-17; Aug 27: EXT-17; Aug 28: EXT-18; Aug 29: EXT-18; Aug 30: EXT-18; Aug 31: EXT-18; Sep 01: EXT-18; Sep 02: EXT-18; Sep 03: EXT-18; Sep 04: EXT-19; Sep 05: EXT-19; Sep 06: EXT-19; Sep 09: EXT-20; Sep 10: EXT-21; Sep 11: EXT-22; Sep 12: EXT-22; Sep 13: EXT-22; Sep 14: EXT-22; Sep 15: EXT-22; Sep 16: EXT-22; Sep 17: EXT-22; Sep 18: EXT-22; Sep 19: EXT-22; Sep 20: EXT-22; Sep 21: EXT-22; Sep 22: EXT-22; Sep 23: EXT-22; Sep 24: EXT-22; Sep 25: EXT-22; Sep 26: EXT-22; Sep 27: EXT-22; Sep 28: EXT-22; Sep 29: EXT-22; Sep 30: EXT-22; Oct 01: EXT-22; Oct 02: EXT-22; Oct 03: EXT-22; Oct 04: EXT-22; Oct 05: EXT-22; Oct 06: EXT-22; Oct 07: EXT-22; Oct 08: EXT-22; Oct 09: EXT-22; Oct 10: EXT-22; Oct 11: EXT-22; Oct 12: EXT-22; Oct 13: EXT-22; Oct 14: EXT-22; Oct 15: EXT-22; Oct 16: EXT-22; Oct 17: EXT-22; Oct 18: EXT-22; Oct 19: EXT-22; Oct 20: EXT-22; Oct 21: EXT-22; Oct 22: EXT-22; Oct 23: EXT-22; Oct 24: EXT-22; Oct 25: EXT-22; Oct 26: EXT-22; Oct 27: EXT-22; Oct 28: EXT-22; Oct 29: EXT-22; Oct 30: EXT-22; Oct 31: EXT-22; Nov 01: EXT-22; Nov 02: EXT-22; Nov 03: EXT-22; Nov 04: EXT-22; Nov 05: EXT-22; Nov 06: EXT-22; Nov 07: EXT-22; Nov 08: EXT-22; Nov 09: EXT-22; Nov 10: EXT-22; Nov 11: EXT-22; Nov 12: EXT-22; Nov 13: EXT-22; Nov 14: EXT-22; Nov 15: EXT-22; Nov 16: EXT-22; Nov 17: EXT-22; Nov 18: EXT-22; Nov 19: EXT-22; Nov 20: EXT-22; Nov 21: EXT-22; Nov 22: EXT-22; Nov 23: EXT-22; Nov 24: EXT-22; Nov 25: EXT-22; Nov 26: EXT-22; Nov 27: EXT-22; Nov 28: EXT-22; Nov 29: EXT-22; Nov 30: EXT-22; Dec 01: EXT-22; Dec 02: EXT-22; Dec 03: EXT-22; Dec 04: EXT-23; Dec 05: EXT-23; Dec 06: EXT-23; Dec 09: EXT-24; Dec 10: EXT-24; Dec 11: EXT-24; Dec 12: EXT-25; Dec 13: EXT-25; Dec 14: EXT-25; Dec 15: EXT-25; Dec 16: EXT-25; Dec 17: EXT-26; Dec 18: EXT-26; Dec 19: EXT-26
[286 empty] | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-1 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14 | EXT-14
[316 empty] | EXT-8 |  |  |  |  | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 | EXT-9 |  |  | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16 | EXT-16
[316 empty] | EXT-7 | EXT-7 | EXT-7 | EXT-7 | EXT-7 | EXT-7 | EXT-7 | EXT-7 | EXT-7 | EXT-7 | EXT-7 | EXT-7 | EXT-7 | EXT-7 | EXT-7 | EXT-7 | EXT-7 | [10 empty] | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-11 | EXT-6
[343 empty] | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10 | EXT-10
[384 empty] | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15 | EXT-15
[416 empty] | EXT-12 | EXT-12 | EXT-12 | EXT-12 | EXT-12 | EXT-12 | EXT-12 | EXT-12 | EXT-12 | EXT-12 | EXT-12 | EXT-13
Commissioning | Commissioning | Feb 07: CX-1; Feb 14: CX-4; Feb 19: CX-6; Feb 21: CX-9; Feb 22: CX-9; Feb 23: CX-9; Feb 24: CX-9; Feb 25: CX-11; Feb 26: CX-11; Feb 27: CX-12; Feb 28: CX-12; Mar 03: CX-13
[507 empty] | CX-3 | CX-3 | CX-3 | CX-3 |  | CX-5 | CX-5 | [10 empty] | CX-14
[507 empty] | CX-7 | CX-7 | CX-7 | CX-7 |  | CX-8 | CX-8
[507 empty] | CX-10 | CX-10 | CX-10 | CX-10
[507 empty] | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2 | CX-2
Occupancy & Closing | Occupancy & Closing | Mar 03: CX-16; Mar 04: CX-18; Mar 05: CX-31; Mar 06: CX-32; Mar 07: CX-32; Mar 08: CX-32; Mar 09: CX-32; Mar 10: CX-32; Mar 11: CX-32; Mar 12: CX-32; Mar 13: CX-34; Mar 18: CX-35
[524 empty] | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15 | CX-15
[525 empty] | CX-20 | CX-24 | CX-24 | CX-24 | CX-24 | CX-24 | CX-24 | CX-24 | CX-29 | CX-29 | CX-29 | CX-29 | CX-29 | CX-29 | CX-29
[525 empty] | CX-23 | CX-26 | CX-26 | CX-26 | CX-26 | CX-26 | CX-26 | CX-26
[525 empty] | CX-17 | CX-17 | CX-17 | CX-17 | CX-17 | CX-17 | CX-17 | CX-28
[525 empty] | CX-19 | CX-19 | CX-19 | CX-19 | CX-19 | CX-19 | CX-19 | CX-22 | CX-22 | CX-22 | CX-22 | CX-22 | CX-22 | CX-22
[525 empty] | CX-21 | CX-21 | CX-21 | CX-21 | CX-21 | CX-21 | CX-21
[525 empty] | CX-25 | CX-25 | CX-25 | CX-25 | CX-25 | CX-25 | CX-25
[525 empty] | CX-27 | CX-27 | CX-27 | CX-27 | CX-27 | CX-27 | CX-27
[525 empty] | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30 | CX-30
[527 empty] | CX-33 | CX-33 | CX-33 | CX-33 | CX-33 | CX-33 | CX-33
Note on C5: Activity Name: Assign hollow core ordering checklist Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 28-Sep-2023
Note on BV5: Activity Name: Order Rebar (30 days before site delivery date required) Phase: Precon Location: Prep Trade: Construction Company Start Date: 08-Dec-2023 End Date: 08-Dec-2023
Note on C6: Activity Name: Organize site team to have training and certificates Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 28-Sep-2023
Note on C7: Activity Name: Hold Pre Kick-Off meeting with Engineers and Trades people Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 02-Oct-2023
Note on C8: Activity Name: 3.0 Pre construction and mobilization Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C9: Activity Name: Assign Permits check list Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C10: Activity Name: Assign Health and Safety checklist Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C11: Activity Name: Assign Mobilization check list Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C12: Activity Name: Assign Equipment & Tools check list Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C13: Activity Name: Assign Safety Equipment and Materials checklist Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C14: Activity Name: Assign Procurement Plan check list Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C15: Activity Name: Assign Site Services Planning check list Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C16: Activity Name: Assign Sub Contractor planning checklist Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C17: Activity Name: Assign Project Team Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 20-Dec-2023
Note on C18: Activity Name: 3.0, 4.0. 5.0 pre, during and post construction total job Phase: Precon Location: Prep Trade: Construction Company Start Date: 28-Sep-2023 End Date: 05-May-2025
Note on CI20: Activity Name: deliver rebar (footings and gradebeam only) Phase: Sitework Location: Site Trade: Site Sub Start Date: 21-Dec-2023 End Date: 21-Dec-2023
Note on CM20: Activity Name: Install balcony piles Phase: Sitework Location: Site Trade: Site Sub Start Date: 25-Dec-2023 End Date: 27-Dec-2023
Note on CP20: Activity Name: 18. Assign site prep check list (First) Phase: Sitework Location: Site Trade: Site Sub Start Date: 28-Dec-2023 End Date: 28-Dec-2023
Note on CQ20: Activity Name: Strip site Phase: Sitework Location: Site Trade: Site Sub Start Date: 29-Dec-2023 End Date: 04-Jan-2024
Note on CX20: Activity Name: Measure corner offsets for excavation Phase: Sitework Location: Site Trade: Site Sub Start Date: 05-Jan-2024 End Date: 05-Jan-2024
Note on DA20: Activity Name: 28. Assign Pre excavation checklist Phase: Sitework Location: Site Trade: Site Sub Start Date: 08-Jan-2024 End Date: 08-Jan-2024
Note on DJ20: Activity Name: Survey offsets, and footings Phase: Sitework Location: Site Trade: Site Sub Start Date: 17-Jan-2024 End Date: 17-Jan-2024
Note on DK20: Activity Name: Geo Tech Engineer inspection Phase: Sitework Location: Site Trade: Site Sub Start Date: 18-Jan-2024 End Date: 18-Jan-2024
Note on CI21: Activity Name: Order all Anchor bolts Phase: Sitework Location: Site Trade: Site Sub Start Date: 21-Dec-2023 End Date: 21-Dec-2023
Note on DA21: Activity Name: Dig footing and parkade foot print Phase: Sitework Location: Site Trade: Site Sub Start Date: 08-Jan-2024 End Date: 16-Jan-2024
Note on CI22: Activity Name: Schedule Pile contractor Phase: Sitework Location: Site Trade: Site Sub Start Date: 21-Dec-2023 End Date: 21-Dec-2023
Note on DA22: Activity Name: Excavation Phase: Sitework Location: Site Trade: Site Sub Start Date: 08-Jan-2024 End Date: 18-Jan-2024
Note on CI23: Activity Name: Survey for balcony piles Phase: Sitework Location: Site Trade: Site Sub Start Date: 21-Dec-2023 End Date: 22-Dec-2023
Note on CI24: Activity Name: Schedule locates to be done Phase: Sitework Location: Site Trade: Site Sub Start Date: 21-Dec-2023 End Date: 27-Dec-2023
Note on CI25: Activity Name: Site Preparation Phase: Sitework Location: Site Trade: Site Sub Start Date: 21-Dec-2023 End Date: 05-Jan-2024
Note on CI29: Activity Name: 4.1 Site Services & Foundation Work Phase: Sitework & Foundations Location: Site Trade: Site Sub Start Date: 21-Dec-2023 End Date: 25-Mar-2024
Note on DL30: Activity Name: Form footings Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 19-Jan-2024 End Date: 24-Jan-2024
Note on DR30: Activity Name: Tie footing rebar Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 25-Jan-2024 End Date: 31-Jan-2024
Note on DY30: Activity Name: Rebar Inspection Structural Engineer Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 01-Feb-2024 End Date: 01-Feb-2024
Note on DZ30: Activity Name: Assign pre-pour checklist Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 02-Feb-2024 End Date: 02-Feb-2024
Note on EC30: Activity Name: Pour footings Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 05-Feb-2024 End Date: 05-Feb-2024
Note on ED30: Activity Name: Ensure Sleeves for electrical are run in the grade beam prior to pouring Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 06-Feb-2024 End Date: 06-Feb-2024
Note on EM30: Activity Name: Build templates for Anchor bolts Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 15-Feb-2024 End Date: 15-Feb-2024
Note on EN30: Activity Name: Tie Grade beam rebar Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 16-Feb-2024 End Date: 26-Feb-2024
Note on EY30: Activity Name: Assign pre concrete pour checklist Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 27-Feb-2024 End Date: 27-Feb-2024
Note on EZ30: Activity Name: Rebar inspection Structural Engineer Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 28-Feb-2024 End Date: 28-Feb-2024
Note on FA30: Activity Name: Pour grade beam Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 29-Feb-2024 End Date: 29-Feb-2024
Note on FB30: Activity Name: Assign pre back fill check list Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 01-Mar-2024 End Date: 01-Mar-2024
Note on FE30: Activity Name: Install underground insulation Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 04-Mar-2024 End Date: 05-Mar-2024
Note on FG30: Activity Name: Back fill exterior grade beam Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 06-Mar-2024 End Date: 07-Mar-2024
Note on FI30: Activity Name: Back fill interior parkade Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 08-Mar-2024 End Date: 14-Mar-2024
Note on FP30: Activity Name: Assign water and sewer and storm checklist Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 15-Mar-2024 End Date: 15-Mar-2024
Note on FS30: Activity Name: Structural steel delivered and sorted onsite Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 18-Mar-2024 End Date: 18-Mar-2024
Note on FU30: Activity Name: Structural steel erection Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 20-Mar-2024 End Date: 21-Mar-2024
Note on FZ30: Activity Name: Assign water and sewer commissioning checklist Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 25-Mar-2024 End Date: 25-Mar-2024
Note on DL31: Activity Name: Foundation Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 19-Jan-2024 End Date: 29-Feb-2024
Note on FB31: Activity Name: Back fill foundation Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 01-Mar-2024 End Date: 14-Mar-2024
Note on FP31: Activity Name: Assign structural steel checklist Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 15-Mar-2024 End Date: 15-Mar-2024
Note on FS31: Activity Name: Install water and sewer Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 18-Mar-2024 End Date: 22-Mar-2024
Note on FZ31: Activity Name: Commision Water/sewer/storm Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 25-Mar-2024 End Date: 25-Mar-2024
Note on ED32: Activity Name: Form grade beam Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 06-Feb-2024 End Date: 14-Feb-2024
Note on FP32: Activity Name: Strucutral Steel Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 15-Mar-2024 End Date: 21-Mar-2024
Note on FP33: Activity Name: Site services W/S/S install Phase: Foundations Location: Bellow the Ground Trade: Concrete Start Date: 15-Mar-2024 End Date: 25-Mar-2024
Note on GQ37: Activity Name: Frame parkade level Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 11-Apr-2024 End Date: 15-Apr-2024
Note on GV37: Activity Name: Assign framing checklist Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 16-Apr-2024 End Date: 16-Apr-2024
Note on GY37: Activity Name: Assign hollow core erection checklist Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 19-Apr-2024 End Date: 19-Apr-2024
Note on HX37: Activity Name: Assign framing check list Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 14-May-2024 End Date: 14-May-2024
Note on IG37: Activity Name: Hollowcore 3rd floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 23-May-2024 End Date: 28-May-2024
Note on IY37: Activity Name: Assign framing checklist Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 10-Jun-2024 End Date: 10-Jun-2024
Note on IZ37: Activity Name: Install hollow core 4th floor and grout Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 11-Jun-2024 End Date: 12-Jun-2024
Note on JB37: Activity Name: Assign hollow core checklist Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 13-Jun-2024 End Date: 13-Jun-2024
Note on JF37: Activity Name: Paint underside of ceiling in parkade Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 17-Jun-2024 End Date: 17-Jun-2024
Note on JH37: Activity Name: Deliver pakade slab rebar Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 19-Jun-2024 End Date: 19-Jun-2024
Note on JI37: Activity Name: Back fill and level parkade Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 20-Jun-2024 End Date: 26-Jun-2024
Note on JP37: Activity Name: Assign parkade slab rough in checklist Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 27-Jun-2024 End Date: 27-Jun-2024
Note on JQ37: Activity Name: Radon rock install Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 28-Jun-2024 End Date: 01-Jul-2024
Note on JU37: Activity Name: Install poly Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 02-Jul-2024 End Date: 02-Jul-2024
Note on JV37: Activity Name: Tie parkade rebar Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 03-Jul-2024 End Date: 05-Jul-2024
Note on KA37: Activity Name: Assign pre concrete pour checklist Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 08-Jul-2024 End Date: 08-Jul-2024
Note on KB37: Activity Name: Pour parkade floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 09-Jul-2024 End Date: 10-Jul-2024
Note on KK37: Activity Name: Layout suites on 2nd floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 18-Jul-2024 End Date: 22-Jul-2024
Note on KP37: Activity Name: Layout suites on 3rd floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 23-Jul-2024 End Date: 26-Jul-2024
Note on KV37: Activity Name: Core floor beings at 3rd floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 29-Jul-2024 End Date: 31-Jul-2024
Note on KY37: Activity Name: Core floor beings at 4th floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 01-Aug-2024 End Date: 02-Aug-2024
Note on LE37: Activity Name: Assign roof trusses framing checklist Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 07-Aug-2024 End Date: 07-Aug-2024
Note on LR37: Activity Name: Call for structural inspection Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 20-Aug-2024 End Date: 20-Aug-2024
Note on GQ38: Activity Name: Framing parkade Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 11-Apr-2024 End Date: 16-Apr-2024
Note on GY38: Activity Name: Frame 2nd floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 19-Apr-2024 End Date: 13-May-2024
Note on IG38: Activity Name: Install hollow core 3rd floor, Install backer rod & grout Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 23-May-2024 End Date: 28-May-2024
Note on IZ38: Activity Name: Hollowcore 4th floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 11-Jun-2024 End Date: 13-Jun-2024
Note on JH38: Activity Name: Frame 4th floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 19-Jun-2024 End Date: 05-Jul-2024
Note on KA38: Activity Name: Assign framing checklist Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 08-Jul-2024 End Date: 08-Jul-2024
Note on KB38: Activity Name: Install roof trusses and sheeting and towers Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 09-Jul-2024 End Date: 06-Aug-2024
Note on GQ39: Activity Name: 4.2 Framing Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 11-Apr-2024 End Date: 03-Jan-2025
Note on GV40: Activity Name: Install hollowcore 2nd floor , Install backer rod & Grout 2nd floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 16-Apr-2024 End Date: 18-Apr-2024
Note on GY40: Activity Name: Framing 2nd floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 19-Apr-2024 End Date: 14-May-2024
Note on IK40: Activity Name: Assign hollow core erection checklist Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 27-May-2024 End Date: 27-May-2024
Note on IL40: Activity Name: Frame 3rd floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 28-May-2024 End Date: 07-Jun-2024
Note on JA40: Activity Name: Mechanical rough in in slab Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 12-Jun-2024 End Date: 18-Jun-2024
Note on JH40: Activity Name: Framing 4th floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 19-Jun-2024 End Date: 31-Jul-2024
Note on GV41: Activity Name: Hollowcore 2nd floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 16-Apr-2024 End Date: 17-Jun-2024
Note on JP41: Activity Name: Pour parakde slab Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 27-Jun-2024 End Date: 10-Jul-2024
Note on KQ41: Activity Name: Core floors begin at 2nd Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 24-Jul-2024 End Date: 26-Jul-2024
Note on KV41: Activity Name: Layout suites 4th floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 29-Jul-2024 End Date: 01-Aug-2024
Note on IL42: Activity Name: Framing 3rd floor Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 28-May-2024 End Date: 26-Jul-2024
Note on JA43: Activity Name: Electrical rough in in slab Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 12-Jun-2024 End Date: 18-Jun-2024
Note on KB43: Activity Name: Roof trusses install Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 09-Jul-2024 End Date: 20-Aug-2024
Note on JA44: Activity Name: Rough in parkade slab Phase: Framing & RI Location: Structure Trade: Framer & MEP Start Date: 12-Jun-2024 End Date: 26-Jun-2024
Note on LG48: Activity Name: 4.4 Finishing Phase: Interiors Location: Finishes Trade: MEPF Start Date: 09-Aug-2024 End Date: 05-May-2025
Note on PL49: Activity Name: Ceiling texture on 4th Phase: Interiors Location: Finishes Trade: MEPF Start Date: 26-Nov-2024 End Date: 27-Nov-2024
Note on PN49: Activity Name: Prime paint on 4th Phase: Interiors Location: Finishes Trade: MEPF Start Date: 28-Nov-2024 End Date: 03-Dec-2024
Note on PU49: Activity Name: Paint 1st coat of color on 4th Phase: Interiors Location: Finishes Trade: MEPF Start Date: 05-Dec-2024 End Date: 10-Dec-2024
Note on QA49: Activity Name: Install cabinets on 4th Phase: Interiors Location: Finishes Trade: MEPF Start Date: 11-Dec-2024 End Date: 18-Dec-2024
Note on QJ49: Activity Name: Install base and hardware on 4th Phase: Interiors Location: Finishes Trade: MEPF Start Date: 20-Dec-2024 End Date: 03-Jan-2025
Note on RB49: Activity Name: Parkade - Taper to rectify deficiencies Phase: Interiors Location: Finishes Trade: MEPF Start Date: 07-Jan-2025 End Date: 07-Jan-2025
Note on RC49: Activity Name: Install interior doors and case on 1 Phase: Interiors Location: Finishes Trade: MEPF Start Date: 08-Jan-2025 End Date: 09-Jan-2025
Note on RE49: Activity Name: Spray out closet interiors and trim on 1 Phase: Interiors Location: Finishes Trade: MEPF Start Date: 10-Jan-2025 End Date: 10-Jan-2025
Note on RH49: Activity Name: Install cabinets 2nd floor Phase: Interiors Location: Finishes Trade: MEPF Start Date: 13-Jan-2025 End Date: 17-Jan-2025
Note on RP49: Activity Name: Parkade - Measurement for template Phase: Interiors Location: Finishes Trade: MEPF Start Date: 21-Jan-2025 End Date: 21-Jan-2025
Note on RS49: Activity Name: Final coat of paint Phase: Interiors Location: Finishes Trade: MEPF Start Date: 24-Jan-2025 End Date: 05-Feb-2025
Note on SG49: Activity Name: Final suite clean on 4th Phase: Interiors Location: Finishes Trade: Clean Start Date: 07-Feb-2025 End Date: 10-Feb-2025
Note on SK49: Activity Name: Electrical finishing on 1 Phase: Interiors Location: Finishes Trade: MEPF Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on SN49: Activity Name: Construction clean on 1 Phase: Interiors Location: Finishes Trade: Clean Start Date: 14-Feb-2025 End Date: 18-Feb-2025
Note on SS49: Activity Name: Assign Unit Commissioning Inspection list on 1 Phase: Interiors Location: Finishes Trade: Construction Company Start Date: 19-Feb-2025 End Date: 19-Feb-2025
Note on ST49: Activity Name: Final suite clean on 1 Phase: Interiors Location: Finishes Trade: Clean Start Date: 20-Feb-2025 End Date: 24-Feb-2025
Note on TA49: Activity Name: Assign Unit Commissioning Inspection list 2nd floor Phase: Interiors Location: Finishes Trade: Construction Company Start Date: 27-Feb-2025 End Date: 27-Feb-2025
Note on PL50: Activity Name: finishing on 4th Phase: Interiors Location: Finishes Trade: MEPF Start Date: 26-Nov-2024 End Date: 10-Feb-2025
Note on SK50: Activity Name: Mechanical finishing on 1 Phase: Interiors Location: Finishes Trade: MEPF Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on SQ50: Activity Name: Assign Unit Commissioning Inspection list on 3rd Phase: Interiors Location: Finishes Trade: Construction Company Start Date: 17-Feb-2025 End Date: 17-Feb-2025
Note on SX50: Activity Name: Construction clean 2nd floor Phase: Interiors Location: Finishes Trade: Clean Start Date: 24-Feb-2025 End Date: 27-Feb-2025
Note on PR51: Activity Name: 4th floor - Taper do the rectification of deficiencies Phase: Interiors Location: Finishes Trade: Drywall Start Date: 02-Dec-2024 End Date: 03-Dec-2024
Note on PU51: Activity Name: Prime paint on 3rd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 05-Dec-2024 End Date: 10-Dec-2024
Note on QB51: Activity Name: Paint 1st coat of color on 3rd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 12-Dec-2024 End Date: 17-Dec-2024
Note on QH51: Activity Name: Prime paint on 2nd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 18-Dec-2024 End Date: 23-Dec-2024
Note on QQ51: Activity Name: Paint 1st coat of color 2nd floor Phase: Interiors Location: Finishes Trade: MEPF Start Date: 27-Dec-2024 End Date: 03-Jan-2025
Note on RC51: Activity Name: 3rd floor counter top measurement for template Phase: Interiors Location: Finishes Trade: MEPF Start Date: 08-Jan-2025 End Date: 10-Jan-2025
Note on RJ51: Activity Name: Install flooring on 1 Phase: Interiors Location: Finishes Trade: MEPF Start Date: 15-Jan-2025 End Date: 16-Jan-2025
Note on RL51: Activity Name: Install cabinets on 1 Phase: Interiors Location: Finishes Trade: MEPF Start Date: 17-Jan-2025 End Date: 20-Jan-2025
Note on RP51: Activity Name: Electrical finishing on 4th Phase: Interiors Location: Finishes Trade: MEPF Start Date: 21-Jan-2025 End Date: 27-Jan-2025
Note on RX51: Activity Name: Electrical finishing on 3rd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on SG51: Activity Name: Electrical finishing 2nd floor Phase: Interiors Location: Finishes Trade: MEPF Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on SQ51: Activity Name: Final suite clean on 3rd Phase: Interiors Location: Finishes Trade: Clean Start Date: 17-Feb-2025 End Date: 18-Feb-2025
Note on TA51: Activity Name: Final suite clean Phase: Interiors Location: Finishes Trade: Clean Start Date: 27-Feb-2025 End Date: 28-Feb-2025
Note on PR52: Activity Name: Ceiling texture on 3rd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 02-Dec-2024 End Date: 03-Dec-2024
Note on PU52: Activity Name: Spray out closet interiors and trim on 4th Phase: Interiors Location: Finishes Trade: MEPF Start Date: 05-Dec-2024 End Date: 10-Dec-2024
Note on QB52: Activity Name: Spray out closet interiors and trim on 3rd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 12-Dec-2024 End Date: 17-Dec-2024
Note on QH52: Activity Name: Install cabinets on 3rd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 18-Dec-2024 End Date: 10-Jan-2025
Note on RK52: Activity Name: 2nd floor counter top measurement for template Phase: Interiors Location: Finishes Trade: MEPF Start Date: 16-Jan-2025 End Date: 20-Jan-2025
Note on RP52: Activity Name: Mechanical finishing on 4th Phase: Interiors Location: Finishes Trade: MEPF Start Date: 21-Jan-2025 End Date: 27-Jan-2025
Note on RX52: Activity Name: Mechanical finishing on 3rd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on SG52: Activity Name: Mechanical finishing 2nd floor Phase: Interiors Location: Finishes Trade: MEPF Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on PR53: Activity Name: Install interior doors and case on 4th Phase: Interiors Location: Finishes Trade: MEPF Start Date: 02-Dec-2024 End Date: 06-Dec-2024
Note on PY53: Activity Name: Install interior doors and case on 3rd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 09-Dec-2024 End Date: 13-Dec-2024
Note on QF53: Activity Name: Ceiling texture on 2nd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 16-Dec-2024 End Date: 17-Dec-2024
Note on QM53: Activity Name: 2nd floor - Taper do the rectification of deficiences Phase: Interiors Location: Finishes Trade: Drywall Start Date: 23-Dec-2024 End Date: 23-Dec-2024
Note on QW53: Activity Name: Ceiling texture on 1 Phase: Interiors Location: Finishes Trade: MEPF Start Date: 02-Jan-2025 End Date: 03-Jan-2025
Note on RC53: Activity Name: Install base and hardware on 3rd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 08-Jan-2025 End Date: 13-Jan-2025
Note on RL53: Activity Name: Install base and hardware 2nd floor Phase: Interiors Location: Finishes Trade: MEPF Start Date: 17-Jan-2025 End Date: 24-Jan-2025
Note on RX53: Activity Name: Sprinkler finishing on 3rd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 29-Jan-2025 End Date: 04-Feb-2025
Note on SG53: Activity Name: Sprinkler finishing 2nd floor Phase: Interiors Location: Finishes Trade: MEPF Start Date: 07-Feb-2025 End Date: 13-Feb-2025
Note on PR54: Activity Name: 3rd floor finishing Phase: Interiors Location: Finishes Trade: MEPF Start Date: 02-Dec-2024 End Date: 18-Feb-2025
Note on PY55: Activity Name: Install flooring on 4th Phase: Interiors Location: Finishes Trade: MEPF Start Date: 09-Dec-2024 End Date: 16-Dec-2024
Note on QG55: Activity Name: 4th floor counter top measurements for template Phase: Interiors Location: Finishes Trade: MEPF Start Date: 17-Dec-2024 End Date: 19-Dec-2024
Note on QM55: Activity Name: Install interior doors and case on 2nd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 23-Dec-2024 End Date: 03-Jan-2025
Note on RC55: Activity Name: Install flooring 2nd floor Phase: Interiors Location: Finishes Trade: MEPF Start Date: 08-Jan-2025 End Date: 16-Jan-2025
Note on RP55: Activity Name: Sprinkler finishing on 4th Phase: Interiors Location: Finishes Trade: MEPF Start Date: 21-Jan-2025 End Date: 27-Jan-2025
Note on SC55: Activity Name: Construction clean on 4th Phase: Interiors Location: Finishes Trade: Clean Start Date: 03-Feb-2025 End Date: 07-Feb-2025
Note on SJ55: Activity Name: Install countertops on 1 Phase: Interiors Location: Finishes Trade: MEPF Start Date: 10-Feb-2025 End Date: 10-Feb-2025
Note on SK55: Activity Name: Sprinkler finishing on 1 Phase: Interiors Location: Finishes Trade: MEPF Start Date: 11-Feb-2025 End Date: 13-Feb-2025
Note on PZ56: Activity Name: 3rd floor - Taper do the rectification of deficiencies Phase: Interiors Location: Finishes Trade: Drywall Start Date: 10-Dec-2024 End Date: 10-Dec-2024
Note on QF56: Activity Name: 2nd floor finishing Phase: Interiors Location: Finishes Trade: MEPF Start Date: 16-Dec-2024 End Date: 28-Feb-2025
Note on QG57: Activity Name: Install flooring on 3rd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 17-Dec-2024 End Date: 07-Jan-2025
Note on RE57: Activity Name: Paint 1rst coat of color on 1 Phase: Interiors Location: Finishes Trade: MEPF Start Date: 10-Jan-2025 End Date: 16-Jan-2025
Note on RP57: Activity Name: Manufacturing and Install countertops 2nd floor Phase: Interiors Location: Finishes Trade: MEPF Start Date: 21-Jan-2025 End Date: 07-Feb-2025
Note on SK57: Activity Name: Construction clean on 3rd Phase: Interiors Location: Finishes Trade: Clean Start Date: 11-Feb-2025 End Date: 17-Feb-2025
Note on QW58: Activity Name: manufacturing and Install countertops on 4th Phase: Interiors Location: Finishes Trade: MEPF Start Date: 02-Jan-2025 End Date: 21-Jan-2025
Note on SC58: Activity Name: Final coat of paint Phase: Interiors Location: Finishes Trade: MEPF Start Date: 03-Feb-2025 End Date: 13-Feb-2025
Note on QW59: Activity Name: finishing parkade level 1 Phase: Interiors Location: Finishes Trade: MEPF Start Date: 02-Jan-2025 End Date: 24-Feb-2025
Note on QX60: Activity Name: Prime paint on 1 Phase: Interiors Location: Finishes Trade: MEPF Start Date: 03-Jan-2025 End Date: 07-Jan-2025
Note on RE60: Activity Name: Manufacturing and Install countertops on 3rd Phase: Interiors Location: Finishes Trade: MEPF Start Date: 10-Jan-2025 End Date: 29-Jan-2025
Note on SM60: Activity Name: Final coat of paint Phase: Interiors Location: Finishes Trade: MEPF Start Date: 13-Feb-2025 End Date: 25-Feb-2025
Note on LC64: Activity Name: Mechanical rough in in ceiling Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 05-Aug-2024 End Date: 14-Aug-2024
Note on LQ64: Activity Name: Frame interior parkade walls Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 19-Aug-2024 End Date: 23-Aug-2024
Note on LX64: Activity Name: Electrical rough in in ceiling Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 26-Aug-2024 End Date: 03-Sep-2024
Note on MG64: Activity Name: Call for Mechanical & Electrical inspection of attic Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 04-Sep-2024 End Date: 04-Sep-2024
Note on MH64: Activity Name: Poly 4th floor ceiling Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 05-Sep-2024 End Date: 06-Sep-2024
Note on ML64: Activity Name: Install sound bar 4th floor Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 09-Sep-2024 End Date: 10-Sep-2024
Note on MN64: Activity Name: Board upper 16" strips in common area & all suites on 3rd Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 11-Sep-2024 End Date: 16-Sep-2024
Note on MU64: Activity Name: Blow in attic insulation Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 18-Sep-2024 End Date: 20-Sep-2024
Note on MZ64: Activity Name: Back framing on 4th Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 23-Sep-2024 End Date: 27-Sep-2024
Note on NN64: Activity Name: Assign taping inspection checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 07-Oct-2024 End Date: 07-Oct-2024
Note on OB64: Activity Name: Mechanical rough in hallways stairwells on 4th Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 21-Oct-2024 End Date: 25-Oct-2024
Note on OI64: Activity Name: Mechanical rough in hallways & stairwells on 3rd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 28-Oct-2024 End Date: 07-Nov-2024
Note on OT64: Activity Name: Assign Corridor & Stairwell pre board inspection checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 08-Nov-2024 End Date: 08-Nov-2024
Note on OW64: Activity Name: Fire tape / Fire caulk upper strips on 3rd Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 11-Nov-2024 End Date: 11-Nov-2024
Note on OX64: Activity Name: Assign corridor & stairwell pre board inspection checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 12-Nov-2024 End Date: 12-Nov-2024
Note on PA64: Activity Name: Assign pre board inspection check list Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on PD64: Activity Name: Rough in exterior walls - parkade and sheds Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 18-Nov-2024 End Date: 06-Dec-2024
Note on PY64: Activity Name: Board parkade exterior walls and sheds Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 09-Dec-2024 End Date: 09-Dec-2024
Note on PZ64: Activity Name: Assign siding checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 10-Dec-2024 End Date: 10-Dec-2024
Note on QC64: Activity Name: Tape parkade interior and exterior walls Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 13-Dec-2024 End Date: 23-Dec-2024
Note on QN64: Activity Name: Assign siding checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 24-Dec-2024 End Date: 24-Dec-2024
Note on RQ64: Activity Name: Assign pre board inspection checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 22-Jan-2025 End Date: 22-Jan-2025
Note on RR64: Activity Name: Call for Electrical and Mechanical Inspection Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 23-Jan-2025 End Date: 23-Jan-2025
Note on LC65: Activity Name: Rough in 4th floor ceiling Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 05-Aug-2024 End Date: 07-Oct-2024
Note on OB65: Activity Name: Mechanical rough in on 4th Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 21-Oct-2024 End Date: 25-Oct-2024
Note on OI65: Activity Name: Mechanical rough in on 3rd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 28-Oct-2024 End Date: 07-Nov-2024
Note on OT65: Activity Name: Assign pre board interior walls checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 08-Nov-2024 End Date: 08-Nov-2024
Note on OX65: Activity Name: Call for Mechanical and Electrical Inspection Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 12-Nov-2024 End Date: 12-Nov-2024
Note on PA65: Activity Name: Assign pre board interior walls checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on PG65: Activity Name: Rough in interior walls Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 21-Nov-2024 End Date: 04-Dec-2024
Note on PU65: Activity Name: Assign taping inspection checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 05-Dec-2024 End Date: 05-Dec-2024
Note on PV65: Activity Name: Board and prepare electrical/mechanical room Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 06-Dec-2024 End Date: 10-Dec-2024
Note on QF65: Activity Name: Frame and board Parkade beams Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 16-Dec-2024 End Date: 20-Dec-2024
Note on QM65: Activity Name: Assign taping inspection checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 23-Dec-2024 End Date: 23-Dec-2024
Note on QN65: Activity Name: Install metal doors and frames Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 24-Dec-2024 End Date: 06-Jan-2025
Note on RQ65: Activity Name: Assign pre board inspection checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 22-Jan-2025 End Date: 22-Jan-2025
Note on LC66: Activity Name: 4.3 Rough In, Steel Stud Drywall Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 05-Aug-2024 End Date: 23-Jan-2025
Note on LE67: Activity Name: Sprinkler install in attic Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 07-Aug-2024 End Date: 21-Aug-2024
Note on LT67: Activity Name: Poly and insulate parkade exterior walls Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 22-Aug-2024 End Date: 23-Aug-2024
Note on LX67: Activity Name: Sprinkler rough in corridor & stairwells on 2nd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 26-Aug-2024 End Date: 06-Sep-2024
Note on ML67: Activity Name: Sprinkler rough in hallways & stairwells on 3rd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 09-Sep-2024 End Date: 20-Sep-2024
Note on MZ67: Activity Name: Sprinkler rough in hallways stairwells on 4th Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 23-Sep-2024 End Date: 30-Sep-2024
Note on OB67: Activity Name: Electrical rough in hallways stairwells on 4th Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 21-Oct-2024 End Date: 31-Oct-2024
Note on OM67: Activity Name: Fire tape / Fire caulk upper strips on 4th Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 01-Nov-2024 End Date: 01-Nov-2024
Note on OP67: Activity Name: 4th floor framing inspection Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 04-Nov-2024 End Date: 04-Nov-2024
Note on OQ67: Activity Name: Poly and insulate on 4th exterior walls Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 05-Nov-2024 End Date: 07-Nov-2024
Note on OT67: Activity Name: Assign exterior wall pre board inspection check list Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 08-Nov-2024 End Date: 08-Nov-2024
Note on OX67: Activity Name: Poly and insulate on 3rd exterior walls Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 12-Nov-2024 End Date: 15-Nov-2024
Note on PH67: Activity Name: Assign siding checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 22-Nov-2024 End Date: 22-Nov-2024
Note on PK67: Activity Name: Fire tape / Fire caulk upper strips on 2nd Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 25-Nov-2024 End Date: 25-Nov-2024
Note on PL67: Activity Name: Frame drops on 2nd Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 26-Nov-2024 End Date: 02-Dec-2024
Note on PU67: Activity Name: Assign taping inspection checklist for suites Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 05-Dec-2024 End Date: 05-Dec-2024
Note on PY67: Activity Name: Install suite entry doors and frames and Interior doors, trims and jambs Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 09-Dec-2024 End Date: 13-Dec-2024
Note on QI67: Activity Name: Assign taping inspection checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 19-Dec-2024 End Date: 19-Dec-2024
Note on QM67: Activity Name: Install suite entry doors and frames and Interior doors, trims and jambs Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 23-Dec-2024 End Date: 03-Jan-2025
Note on LJ68: Activity Name: Steel stud install on 2nd & drywall behind the tubs including fire wall taping if it is a fire wall Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 12-Aug-2024 End Date: 29-Aug-2024
Note on MB68: Activity Name: Board upper 16" strips in common area and all suites on 2nd Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 30-Aug-2024 End Date: 04-Sep-2024
Note on MI68: Activity Name: Install tubs and showers Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 06-Sep-2024 End Date: 11-Sep-2024
Note on MU68: Activity Name: Steel stud install on 4th & drywall behind the tubs including fire wall taping if it is a fire wall Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 18-Sep-2024 End Date: 26-Sep-2024
Note on ND68: Activity Name: Board upper 16" strips in common area and all suites on 4th Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 27-Sep-2024 End Date: 02-Oct-2024
Note on OB68: Activity Name: Electrical rough in on 4th Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 21-Oct-2024 End Date: 31-Oct-2024
Note on OM68: Activity Name: Mechanical rough in hallways & stairwells on 2nd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 01-Nov-2024 End Date: 15-Nov-2024
Note on PH68: Activity Name: Tape 3rd floor hallways and stair wells Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 22-Nov-2024 End Date: 05-Dec-2024
Note on PZ68: Activity Name: Board Parkade interior walls Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 10-Dec-2024 End Date: 13-Dec-2024
Note on QI68: Activity Name: Assign taping inspection checklist for suites Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 19-Dec-2024 End Date: 19-Dec-2024
Note on LJ69: Activity Name: Rough in 2nd floor Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 12-Aug-2024 End Date: 03-Jan-2025
Note on LQ70: Activity Name: Water dams 2nd floor Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 19-Aug-2024 End Date: 23-Aug-2024
Note on LX70: Activity Name: Sprinkler rough in on 2nd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 26-Aug-2024 End Date: 06-Sep-2024
Note on ML70: Activity Name: Sprinkler rough in on 3rd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 09-Sep-2024 End Date: 20-Sep-2024
Note on MZ70: Activity Name: Sprinkler rough in on 4th Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 23-Sep-2024 End Date: 30-Sep-2024
Note on OB70: Activity Name: Rough in exterior walls on 4th and sheds Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 21-Oct-2024 End Date: 31-Oct-2024
Note on OM70: Activity Name: Mechanical rough in on 2nd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 01-Nov-2024 End Date: 15-Nov-2024
Note on PH70: Activity Name: Tape suites on 3rd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 22-Nov-2024 End Date: 05-Dec-2024
Note on PZ70: Activity Name: Siding parkade level Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 10-Dec-2024 End Date: 23-Dec-2024
Note on LQ71: Activity Name: Water dams 3rd floor Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 19-Aug-2024 End Date: 23-Aug-2024
Note on LZ71: Activity Name: Install pocket foor frame Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 28-Aug-2024 End Date: 03-Sep-2024
Note on MI71: Activity Name: Install pocket door frames Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 06-Sep-2024 End Date: 12-Sep-2024
Note on MW71: Activity Name: Install pocket door frames Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 20-Sep-2024 End Date: 26-Sep-2024
Note on OB71: Activity Name: Siding 4th floor Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 21-Oct-2024 End Date: 05-Nov-2024
Note on OR71: Activity Name: Assign siding checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 06-Nov-2024 End Date: 06-Nov-2024
Note on OT71: Activity Name: Load the board on floor and Board 4th floor hallways and stairwells Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 08-Nov-2024 End Date: 15-Nov-2024
Note on PH71: Activity Name: Siding 2nd floor Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 22-Nov-2024 End Date: 09-Dec-2024
Note on LQ72: Activity Name: Water dams 4th floor Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 19-Aug-2024 End Date: 23-Aug-2024
Note on MB72: Activity Name: Install tubs and showers Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 30-Aug-2024 End Date: 04-Sep-2024
Note on MM72: Activity Name: Back framing on 3rd Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 10-Sep-2024 End Date: 16-Sep-2024
Note on MZ72: Activity Name: Tape 4th floor ceiling Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 23-Sep-2024 End Date: 04-Oct-2024
Note on OI72: Activity Name: Electrical rough in hallways & stairwells on 3rd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 28-Oct-2024 End Date: 08-Nov-2024
Note on OX72: Activity Name: Frame drops on 3rd Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 12-Nov-2024 End Date: 18-Nov-2024
Note on PK72: Activity Name: Assign gypcrete pour checklist Phase: Interiors Location: Rough-Ins Trade: Gypcrete Start Date: 25-Nov-2024 End Date: 25-Nov-2024
Note on PN72: Activity Name: Assign Corridor & Stairwell pre board inspection checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 28-Nov-2024 End Date: 28-Nov-2024
Note on PO72: Activity Name: Frame drops on 4th Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 29-Nov-2024 End Date: 05-Dec-2024
Note on LQ73: Activity Name: Rough in 4th floor Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 19-Aug-2024 End Date: 06-Dec-2024
Note on LQ74: Activity Name: Rough in 3rd floor Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 19-Aug-2024 End Date: 13-Dec-2024
Note on LQ75: Activity Name: Rough in Parkade Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 19-Aug-2024 End Date: 23-Jan-2025
Note on LS76: Activity Name: Back framing on 2nd Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 21-Aug-2024 End Date: 27-Aug-2024
Note on MB76: Activity Name: Steel stud install on 3rd & drywall behind the tubs including fire wall taping if it is a fire wall Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 30-Aug-2024 End Date: 05-Sep-2024
Note on MN76: Activity Name: Install drywall on 4th floor ceiling Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 11-Sep-2024 End Date: 17-Sep-2024
Note on NC76: Activity Name: Install tubs and showers Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 26-Sep-2024 End Date: 27-Sep-2024
Note on OI76: Activity Name: Electrical rough in on 3rd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 28-Oct-2024 End Date: 08-Nov-2024
Note on PA76: Activity Name: Assign taping inspection checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 15-Nov-2024 End Date: 15-Nov-2024
Note on PK76: Activity Name: Call for Mechanical and Electrical inspection Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 25-Nov-2024 End Date: 25-Nov-2024
Note on PN76: Activity Name: Assign pre board inspection check list Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 28-Nov-2024 End Date: 28-Nov-2024
Note on PR76: Activity Name: Install suite entry doors and frames and Interior doors, trims and jambs Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 02-Dec-2024 End Date: 06-Dec-2024
Note on OI77: Activity Name: Rough in exterior walls on 3rd and sheds Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 28-Oct-2024 End Date: 08-Nov-2024
Note on PA77: Activity Name: Load boards on floor and Board 3rd floor walls Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 15-Nov-2024 End Date: 22-Nov-2024
Note on PK77: Activity Name: Gypcrete Phase: Interiors Location: Rough-Ins Trade: Gypcrete Start Date: 25-Nov-2024 End Date: 26-Nov-2024
Note on PN77: Activity Name: Assign pre board interior walls checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 28-Nov-2024 End Date: 28-Nov-2024
Note on PU77: Activity Name: Tape 2nd floor hallways and stair wells Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 05-Dec-2024 End Date: 19-Dec-2024
Note on OJ78: Activity Name: Call the surveyor to measure for condo plan Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 29-Oct-2024 End Date: 31-Oct-2024
Note on OR78: Activity Name: Siding 3rd floor Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 06-Nov-2024 End Date: 21-Nov-2024
Note on PK78: Activity Name: Pour Gypcrete Phase: Interiors Location: Rough-Ins Trade: Gypcrete Start Date: 25-Nov-2024 End Date: 26-Nov-2024
Note on PN78: Activity Name: Assign taping inspection checklist Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 28-Nov-2024 End Date: 28-Nov-2024
Note on PU78: Activity Name: Tape suites on 2nd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 05-Dec-2024 End Date: 19-Dec-2024
Note on OL79: Activity Name: Call for Electrical and Mechanical inspection Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 31-Oct-2024 End Date: 31-Oct-2024
Note on OT79: Activity Name: Load the board on floor and Board 4th floor walls Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 08-Nov-2024 End Date: 15-Nov-2024
Note on PK79: Activity Name: Poly and insulate on 2nd exterior walls Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 25-Nov-2024 End Date: 28-Nov-2024
Note on OT80: Activity Name: Load the board on floor and Board exterior walls on 4th and sheds Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 08-Nov-2024 End Date: 15-Nov-2024
Note on PN80: Activity Name: Board 2nd floor hallways and stairwells Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 28-Nov-2024 End Date: 04-Dec-2024
Note on OT81: Activity Name: Rough in exterior walls on 2nd and sheds Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 08-Nov-2024 End Date: 21-Nov-2024
Note on PN81: Activity Name: Board 2nd floor walls Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 28-Nov-2024 End Date: 04-Dec-2024
Note on OT82: Activity Name: Electrical rough in hallways & stairwells on 2nd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 08-Nov-2024 End Date: 22-Nov-2024
Note on PN82: Activity Name: Board exterior walls on 2nd and sheds Phase: Interiors Location: Rough-Ins Trade: Drywall Start Date: 28-Nov-2024 End Date: 04-Dec-2024
Note on OT83: Activity Name: Electrical rough in on 2nd Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 08-Nov-2024 End Date: 22-Nov-2024
Note on PN83: Activity Name: Main service electrical room install Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 28-Nov-2024 End Date: 26-Dec-2024
Note on PA84: Activity Name: Load boards on floor and Board exterior walls on 3rd and sheds Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 15-Nov-2024 End Date: 22-Nov-2024
Note on PN84: Activity Name: Main service mechanical room install Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 28-Nov-2024 End Date: 22-Jan-2025
Note on PA85: Activity Name: Load the board on floor and Board 3rd floor hallways and stairwells Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 15-Nov-2024 End Date: 22-Nov-2024
Note on PA86: Activity Name: Tape 4th floor hallways and stair wells Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 15-Nov-2024 End Date: 28-Nov-2024
Note on PA87: Activity Name: Tape suites on 4th Phase: Interiors Location: Rough-Ins Trade: MEPF Start Date: 15-Nov-2024 End Date: 28-Nov-2024
Note on KA91: Activity Name: Assign window & door installation checklist Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 08-Jul-2024 End Date: 08-Jul-2024
Note on KJ91: Activity Name: Deliver tubs & showers to suites / checklist Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 17-Jul-2024 End Date: 18-Jul-2024
Note on KW91: Activity Name: Install stairs Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 30-Jul-2024 End Date: 30-Jul-2024
Note on KY91: Activity Name: Install windows & doors all floors Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 01-Aug-2024 End Date: 13-Aug-2024
Note on LX91: Activity Name: Excavate areas Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 26-Aug-2024 End Date: 27-Aug-2024
Note on LZ91: Activity Name: Form exterior pads Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 28-Aug-2024 End Date: 03-Sep-2024
Note on MG91: Activity Name: Tie rebar exterior pads Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 04-Sep-2024 End Date: 06-Sep-2024
Note on ML91: Activity Name: Assign conrete pour checklist Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 09-Sep-2024 End Date: 09-Sep-2024
Note on MM91: Activity Name: Pour exterior pads Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 10-Sep-2024 End Date: 10-Sep-2024
Note on MN91: Activity Name: Excatae exterior sidewalks Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 11-Sep-2024 End Date: 03-Dec-2024
Note on PT91: Activity Name: Form exterior sidewalks Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 04-Dec-2024 End Date: 06-Dec-2024
Note on PY91: Activity Name: Rebar exterior sidewalks Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 09-Dec-2024 End Date: 11-Dec-2024
Note on QB91: Activity Name: Assign pre concrete pour checklist Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 12-Dec-2024 End Date: 16-Dec-2024
Note on QG91: Activity Name: Pour exterior sidewalks Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 17-Dec-2024 End Date: 19-Dec-2024
Note on KA92: Activity Name: install windows and doors Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 08-Jul-2024 End Date: 26-Nov-2024
Note on PM92: Activity Name: Siding towers Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 27-Nov-2024 End Date: 16-Dec-2024
Note on LE93: Activity Name: Assign roofing and water proofing checklist Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 07-Aug-2024 End Date: 07-Aug-2024
Note on LJ93: Activity Name: Install roofing and water proofing Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 12-Aug-2024 End Date: 23-Aug-2024
Note on LX93: Activity Name: Exterior concrete works Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 26-Aug-2024 End Date: 19-Dec-2024
Note on LE94: Activity Name: Roofing and water proofing Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 07-Aug-2024 End Date: 23-Aug-2024
Note on MF94: Activity Name: Building paper the whole building Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 03-Sep-2024 End Date: 25-Nov-2024
Note on PL94: Activity Name: Call for envelope reviewer inspection Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 26-Nov-2024 End Date: 26-Nov-2024
Note on MF95: Activity Name: Soffit & Tower Siding Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 03-Sep-2024 End Date: 03-Jan-2025
Note on NU96: Activity Name: Delivery of Elevator & Install Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 14-Oct-2024 End Date: 03-Jan-2025
Note on PA97: Activity Name: Install fascia and soffit 4th floor Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 15-Nov-2024 End Date: 25-Nov-2024
Note on PL97: Activity Name: Assign tower siding checklist Phase: Exterior Location: Building Trade: Exterior Subs Start Date: 26-Nov-2024 End Date: 26-Nov-2024
Note on SG101: Activity Name: Assign Unit Commissioning Inspection list on 4th Phase: Commissioning Location: Commissioning Trade: CX Start Date: 07-Feb-2025 End Date: 07-Feb-2025
Note on SN101: Activity Name: Contact Canada Post to get the address's created Phase: Commissioning Location: Commissioning Trade: Construction Company Start Date: 14-Feb-2025 End Date: 14-Feb-2025
Note on SS101: Activity Name: Organize 3rd party building exterior review, including roof, siding and flashings Phase: Commissioning Location: Commissioning Trade: Construction Company Start Date: 19-Feb-2025 End Date: 19-Feb-2025
Note on SU101: Activity Name: Building inspector walk throughs Phase: Commissioning Location: Commissioning Trade: Construction Company Start Date: 21-Feb-2025 End Date: 24-Feb-2025
Note on SY101: Activity Name: Prepare occupancy paperwork Phase: Commissioning Location: Commissioning Trade: Construction Company Start Date: 25-Feb-2025 End Date: 26-Feb-2025
Note on TA101: Activity Name: Receive occupancy Phase: Commissioning Location: Commissioning Trade: Construction Company Start Date: 27-Feb-2025 End Date: 28-Feb-2025
Note on TE101: Activity Name: Move in dates confirmed Phase: Commissioning Location: Commissioning Trade: Construction Company Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on SN102: Activity Name: Fire alarm verification Phase: Commissioning Location: Commissioning Trade: Construction Company Start Date: 14-Feb-2025 End Date: 17-Feb-2025
Note on SS102: Activity Name: Enginering walk throughs Phase: Commissioning Location: Commissioning Trade: Construction Company Start Date: 19-Feb-2025 End Date: 20-Feb-2025
Note on TE102: Activity Name: Assign Final Building Checklist Phase: Commissioning Location: Commissioning Trade: Construction Company Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on SN103: Activity Name: Sprinkler testing Phase: Commissioning Location: Commissioning Trade: Construction Company Start Date: 14-Feb-2025 End Date: 17-Feb-2025
Note on SS103: Activity Name: Archetectural walk throughs Phase: Commissioning Location: Commissioning Trade: Construction Company Start Date: 19-Feb-2025 End Date: 20-Feb-2025
Note on SN104: Activity Name: Elevator commissioning Phase: Commissioning Location: Commissioning Trade: Construction Company Start Date: 14-Feb-2025 End Date: 17-Feb-2025
Note on SN105: Activity Name: Final commissioning and deficiency Phase: Commissioning Location: Commissioning Trade: Construction Company Start Date: 14-Feb-2025 End Date: 03-Mar-2025
Note on TE109: Activity Name: Pre sale move in dates confirmed Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 03-Mar-2025 End Date: 03-Mar-2025
Note on TF109: Activity Name: Load home owners into copper Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 04-Mar-2025 End Date: 04-Mar-2025
Note on TG109: Activity Name: Send out contractor surveys Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 05-Mar-2025 End Date: 05-Mar-2025
Note on TH109: Activity Name: Schedule 1 on 1 contractor review meetings Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 06-Mar-2025 End Date: 12-Mar-2025
Note on TO109: Activity Name: Project post mordem internal Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 13-Mar-2025 End Date: 13-Mar-2025
Note on TT109: Activity Name: Move info to Dev co work flow 1.0, 2.0, 6.0 Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 18-Mar-2025 End Date: 18-Mar-2025
Note on TE110: Activity Name: 5.0 Sales, Occupancy, Closings Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 03-Mar-2025 End Date: 01-May-2025
Note on TF111: Activity Name: Update home owner permissions in Construction online Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 04-Mar-2025 End Date: 04-Mar-2025
Note on TG111: Activity Name: Building close out cleanup deficiencies confirmed Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on TN111: Activity Name: Home owner walk through punch list clean up Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 12-Mar-2025 End Date: 18-Mar-2025
Note on TF112: Activity Name: Building close out check list Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 04-Mar-2025 End Date: 04-Mar-2025
Note on TG112: Activity Name: De mobilization (checklist) Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 05-Mar-2025 End Date: 11-Mar-2025
Note on TF113: Activity Name: Finalize home owner extras Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on TM113: Activity Name: Home owner walk through and punch list Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 11-Mar-2025 End Date: 11-Mar-2025
Note on TF114: Activity Name: Move in binders created Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on TM114: Activity Name: Unit Commissioning deficiency clean up confirmed Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 11-Mar-2025 End Date: 17-Mar-2025
Note on TF115: Activity Name: Unit Commissioning Inspection list Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on TF116: Activity Name: Building handover (PM to SM) checklist Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on TF117: Activity Name: Keys and gift cards and welcome package created Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 04-Mar-2025 End Date: 10-Mar-2025
Note on TF118: Activity Name: New move ins and warranty through service manager Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 04-Mar-2025 End Date: 01-May-2025
Note on TH119: Activity Name: Schedule contractor group meeting to review survey results Phase: Occupancy & Closing Location: Occupancy & Closing Trade: Construction Company Start Date: 06-Mar-2025 End Date: 12-Mar-2025

## CFA - Legends
Precon |  | Sitework |  | Sitework & Foundations |  | Foundations |  | Framing & RI |  | Interiors |  | Exterior |  | Exteriors & Landscaping |  | Commissioning |  | Occupancy & Closing
|  |  |  | SITE-1 | 4.1 Site Services & Foundation Work | [8 empty] | LAND-2 | Grind all balconys smooth |  |  | CX-16 | Pre sale move in dates confirmed
Construction Company |  | Site Sub |  |  |  | Concrete |  | Framer & MEP |  | Clean |  | Exterior Subs |  |  |  | CX
PRE-13 | Assign hollow core ordering checklist | SITE-4 | deliver rebar (footings and gradebeam only) |  |  | FOUND-2 | Form footings | STR-15 | Frame parkade level | Cl-1 | Construction clean on 4th | EXT-3 | Assign window & door installation checklist |  |  | CX-1 | Assign Unit Commissioning Inspection list on 4th
[10 empty] | Construction Company | [5 empty] | Construction Company
[10 empty] | CC-1 | Assign Unit Commissioning Inspection list on 3rd |  |  |  |  | CX-4 | Contact Canada Post to get the address's created
Drywall
[10 empty] | D-1 | 4th floor - Taper do the rectification of deficiencies
Gypcrete
[10 empty] | GP-1 | Assign gypcrete pour checklist
MEPF
[10 empty] | MEPF-4 | 4.4 Finishing