## Sheet1
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML0 | Cx L5 IST Complete (White Tag) | 2025-09-18 | 2025-09-18
Commissioning | COLO 3 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-05 | 2025-05-28
Commissioning | COLO 3 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-15 | 2025-06-07
Commissioning | COLO 3 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-06-09 | 2025-07-02
Commissioning | COLO 3 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-27 | 2025-06-18
Commissioning | COLO 4 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-06 | 2025-05-29
Commissioning | COLO 4 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-05-31 | 2025-06-24
Commissioning | COLO 4 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-07-22 | 2025-08-14
Commissioning | COLO 4 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-06-27 | 2025-07-22
Commissioning | COLO 5 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-06-05 | 2025-06-28
Commissioning | COLO 5 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-06-28 | 2025-07-23
Commissioning | COLO 5 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-08-09 | 2025-09-03
Commissioning | COLO 5 | TBD | #196B24 | L2 | 2Cx- Yellow Tags | 2025-07-15 | 2025-08-07
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- EPMS Point to Point Checks | 2025-06-13 | 2025-06-23
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- FTE Energizations [480v] | 2025-06-24 | 2025-06-27
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- Install Metering Cabinet [Prior to Energization] | 2025-06-12 | 2025-06-18
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- Loadbanking | 2025-07-15 | 2025-07-18
Commissioning | COLO 3 | TBD | #196B24 | L3 | 3Cx- Startups | 2025-06-28 | 2025-07-14
Commissioning | COLO 3 | Microsoft | #196B24 | 4&5 | 4Cx- Testing <MSFT Duration> | 2025-08-15 | 2025-09-15
Commissioning | COLO 4 | Microsoft | #196B24 | 4&5 | 4Cx- Testing <MSFT Duration> | 2025-09-20 | 2025-10-16
Commissioning | COLO 5 | Microsoft | #196B24 | 4&5 | 4Cx- Testing <MSFT Duration> | 2025-10-17 | 2025-11-15
Commissioning | COLO 3 | Microsoft | #196B24 | 4&5 | 5Cx- Testing <MSFT Duration> | 2025-09-16 | 2025-09-18
Commissioning | COLO 4 | Microsoft | #196B24 | 4&5 | 5Cx- Testing <MSFT Duration> | 2025-10-17 | 2025-10-20
Commissioning | COLO 5 | Microsoft | #196B24 | 4&5 | 5Cx- Testing <MSFT Duration> | 2025-11-17 | 2025-11-19
Milestones | Milestone | Milestone | #808080 | ML1 | Admin & COLO3-5 Fitout Complete | 2025-10-01 | 2025-10-01
Fitout | COLO 3 - CELL 1 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-02-22 | 2025-02-27
Fitout | COLO 3 - CELL 2 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-03-04 | 2025-03-08
Fitout | COLO 3 - CELL 3 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-03-27 | 2025-04-01
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-03-14 | 2025-03-19
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-03-29 | 2025-04-03
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-04-07 | 2025-04-11
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-04-30 | 2025-05-06
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-04-18 | 2025-04-23
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-05-02 | 2025-05-08
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-05-12 | 2025-05-16
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-06-04 | 2025-06-09
Fitout | CELL 4 Data Hall Fitout Activities | HAC's | #FED8E8 | S1 | Assemble HACs [Qty - 5] | 2025-05-22 | 2025-05-28
Site Utilities | Under Building Pad | Earthwork | #7E350E | EW1 | Backfill after UG work (MV / Telecom) | 2024-11-07 | 2024-11-08
Fitout | Punchlist | Punchlist | #A02B93 | PU1 | Beneficial Rooms PunchList | 2025-05-06 | 2025-05-09
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML1 | Beneficial Use | 2025-08-14 | 2025-08-14
Milestones | COLO 4 | Milestone | #000000 | ML2 | Beneficial Use | 2025-09-19 | 2025-09-19
Milestones | COLO 5 | Milestone | #000000 | ML3 | Beneficial Use | 2025-10-11 | 2025-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML4 | Beneficial Use - All Facility & Network Telecom Access/ Devices etc. | 2025-10-01 | 2025-10-01
Milestones | COLO 4 | Milestone | #000000 | ML5 | Beneficial Use - Distrbuted Antenna System (DAS) | 2025-09-19 | 2025-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML6 | Beneficial Use - Distributed Antenna System (DAS) | 2025-08-14 | 2025-08-14
Milestones | COLO 5 | Milestone | #000000 | ML7 | Beneficial Use - Distributed Antenna System (DAS) | 2025-10-11 | 2025-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML8 | Beneficial Use - Facility Cable Room (FCR) | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML9 | Beneficial Use - Meet Me Room or Entry Rooms (MMR/ER) | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML10 | Beneficial Use - Middle of Row (MOR) Cabinets | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML11 | Beneficial Use - Radio Over Internet Protocol (RoIP) | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML12 | Beneficial Use - Secure & High Value Storage Rooms | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML13 | Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets | 2025-08-14 | 2025-08-14
Milestones | COLO 4 | Milestone | #000000 | ML14 | Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets | 2025-09-19 | 2025-09-19
Milestones | COLO 5 | Milestone | #000000 | ML15 | Beneficial Use - Security Corp Cable Rack (SCCR) Cabinets | 2025-10-11 | 2025-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML16 | Beneficial Use - Security Equipment Room (SER) | 2025-08-14 | 2025-08-14
Milestones | COLO 5 | Milestone | #000000 | ML17 | Beneficial Use - Security Low Voltage (SLV) System | 2025-10-11 | 2025-10-11
Milestones | COLO 4 | Milestone | #000000 | ML18 | Beneficial Use - Security Low Voltage (SLV) Systems | 2025-09-19 | 2025-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML19 | Beneficial Use (IDF#1,#2,#3 & #4) | 2025-08-14 | 2025-08-14
Milestones | COLO 5 | Milestone | #000000 | ML20 | Beneficial Use (IDF#1,#2,#3 & #4) | 2025-10-11 | 2025-10-11
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use Facility Cable Room (FCR) | 2025-10-11 | 2025-10-11
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use Meet Me Room or Entry Rooms (MMR/ER) | 2025-10-11 | 2025-10-11
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE29 | Beneficial Use Rooms | 2025-01-20 | 2025-05-09
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use Secure & High Value Storage Rooms | 2025-10-11 | 2025-10-11
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- (IDF#1,#2,#3 & #4) | 2025-09-19 | 2025-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Beneficial Use- Facilities Operations Center (FOC) | 2025-08-14 | 2025-08-14
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Facilities Operations Center (FOC) | 2025-09-19 | 2025-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Facility Cable Room (FCR) | 2025-09-19 | 2025-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Meet Me Room or Entry Rooms (MMR/ER) | 2025-09-19 | 2025-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Middle of Row (MOR) Cabinets | 2025-09-19 | 2025-09-19
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use- Middle of Row (MOR) Cabinets | 2025-10-11 | 2025-10-11
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Radio OVer Internet Protocol (RoIP) | 2025-09-19 | 2025-09-19
Milestones | COLO 5 | Milestone | #000000 | ML21 | Beneficial Use- Radio Over Internet Protocol (RoIP) | 2025-10-11 | 2025-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Beneficial Use- Regional Network Gateway (RNG) | 2025-08-14 | 2025-08-14
Milestones | COLO 4 | Milestone | #000000 | ML21 | Beneficial Use- Secure & High Value Storage Rooms | 2025-09-19 | 2025-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Beneficial Use- Security Low Voltage (SLV) System | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Beneficial Use- Security Operations Center (SOC) | 2025-08-14 | 2025-08-14
BIM | BIM | BIM | #DAE9F8 | BIM | BIM- Above ground BIM Co-ordination | 2024-09-06 | 2024-10-12
BIM | BIM | BIM | #DAE9F8 | BIM | BIM- BIM Kickoff | 2024-07-18 | 2024-07-18
BIM | BIM | BIM | #DAE9F8 | BIM | BIM- UG BIM Co-ordination | 2024-07-19 | 2024-08-17
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | EE30 | Build Equipment Pads for Generators | 2025-02-20 | 2025-03-03
Electrical Yard | COLO 4 | Electrical | #F2F09E | EE30 | Build Equipment Pads for Generators | 2025-03-27 | 2025-04-05
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE30 | Build Equipment Pads for Generators | 2025-04-30 | 2025-05-10
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UMSs | 2025-02-10 | 2025-02-19
Electrical Yard | COLO 4 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UMSs | 2025-03-15 | 2025-03-26
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UMSs | 2025-04-19 | 2025-04-29
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UPMs | 2025-01-29 | 2025-02-07
Electrical Yard | COLO 4 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UPMs | 2025-03-05 | 2025-03-14
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE31 | Build Equipment Pads for UPMs | 2025-04-08 | 2025-04-18
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | EE31 | Build Equipment Pads for XFMs | 2025-01-17 | 2025-01-28
Electrical Yard | COLO 4 | Electrical | #F2F09E | EE31 | Build Equipment Pads for XFMs | 2025-02-21 | 2025-03-04
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE31 | Build Equipment Pads for XFMs | 2025-03-28 | 2025-04-07
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Building Footprint Pad Ready | 2024-09-30 | 2024-09-30
Fitout | Electrical Room | Electrical | #F2F09E | EE28 | Cable Tray / Ceiling Steel Height | 2025-02-04 | 2025-02-04
Fitout | Fire Riser Room | Framing | #3598FE | J17 | Ceiling Grid & Tile | 2025-02-18 | 2025-02-21
Fitout | Restrooms & Janitor Room | Framing | #3598FE | J17 | Ceiling Grid & Tile | 2025-02-18 | 2025-02-21
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- Cable Bus Fabrication/ Lead Time | 2024-10-31 | 2025-03-03
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- HACs Fabrication/ Lead Time | 2024-10-31 | 2024-12-05
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- MV Cables Fabrication/ Lead Time | 2024-08-22 | 2025-04-29
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- MV Metering Cabinet - *Not Used* [65 Weeks] - Not Tied | 2024-08-21 | 2025-11-30
CFCI Procurement | CFCI | CFCI | #F7C7AC | CFCI | CFCI- MV Metering Cabinet - Substitute [43 Weeks] | 2024-08-21 | 2025-06-25
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Building Pad Ready | 2024-09-05 | 2024-09-05
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Closeout Complete | 2026-01-22 | 2026-01-22
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Commissioning Complete | 2025-11-19 | 2025-11-19
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Construction Start | 2024-08-21 | 2024-08-21
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Electrical Service Available | 2025-05-05 | 2025-05-05
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Enclosure Complete | 2025-01-15 | 2025-01-15
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Final Completion (SC+40d) | 2026-01-22 | 2026-01-22
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Foundations Complete | 2024-11-12 | 2024-11-12
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Roofing Complete | 2024-12-31 | 2024-12-31
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Structure Complete | 2024-12-03 | 2024-12-03
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Structure Start | 2024-09-10 | 2024-09-10
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Substantial Completion | 2025-12-02 | 2025-12-02
Milestones | Key Milestone | Milestone | #000000 | ML21 | CHI11: Utilities Available to Owner (Gas Service N/A) | 2024-12-26 | 2024-12-26
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Clayco Proposal Due date | 2024-10-11 | 2024-10-11
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete BAS Testing | 2025-08-30 | 2025-08-30
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete CX L3 (Green Tag) | 2025-08-14 | 2025-08-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete EPMS Testing | 2025-08-30 | 2025-08-30
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Fire Alarm | 2025-08-30 | 2025-08-30
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete L1 Cx (All Red Tags/ ROJ) | 2025-06-04 | 2025-06-04
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete L2 Cx (Yellow Tag) | 2025-07-02 | 2025-07-02
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete L4 Cx (Blue Tag) | 2025-09-15 | 2025-09-15
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Last ROJ | 2025-03-08 | 2025-03-08
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete SOG | 2024-12-27 | 2024-12-27
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Superstructure | 2024-12-14 | 2024-12-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete U/G Utilities (No Elec) | 2024-12-14 | 2024-12-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete U/G Utilities/ MV UG Electrical | 2024-12-14 | 2024-12-14
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Utility Power- On | 2025-05-05 | 2025-05-05
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Weather Tight | 2025-01-16 | 2025-01-16
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete BAS Testing | 2025-09-30 | 2025-09-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete BAS Testing | 2025-10-31 | 2025-10-31
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Earthwork & U/G Site Utilities | 2024-12-26 | 2024-12-26
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete EPMS Testing | 2025-09-30 | 2025-09-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete EPMS Testing | 2025-10-31 | 2025-10-31
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Fire Alarm | 2025-09-30 | 2025-09-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Fire Alarm | 2025-10-31 | 2025-10-31
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Foundation | 2024-09-19 | 2024-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Foundation | 2024-10-31 | 2024-10-31
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Foundation | 2024-11-12 | 2024-11-12
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete L1 Cx (All Red Tags/ ROJ) | 2025-07-19 | 2025-07-19
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete L1 Cx (All Red Tags/ ROJ) | 2025-08-05 | 2025-08-05
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete L2 Cx (Yellow Tag) | 2025-08-14 | 2025-08-14
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete L2 Cx (Yellow Tag) | 2025-09-03 | 2025-09-03
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete L4 Cx (Blue Tag) | 2025-10-16 | 2025-10-16
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete L4 Cx (Blue Tag) | 2025-11-15 | 2025-11-15
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Complete Landscaping/ Hardscaping | 2025-11-19 | 2025-11-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Last ROJ | 2025-03-30 | 2025-03-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Last ROJ | 2025-03-31 | 2025-03-31
Fitout | Fire Riser Room | Fire Protection | #D85234 | GSA | Complete Pipe/ Valves | 2025-02-22 | 2025-02-24
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete SOG | 2025-01-10 | 2025-01-10
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete SOG | 2025-01-25 | 2025-01-25
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Superstructure | 2024-12-31 | 2024-12-31
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Superstructure | 2025-01-15 | 2025-01-15
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete U/G Utilities/ MV UG Electric | 2024-12-27 | 2024-12-27
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete U/G Utilities/ MV UG Electric | 2025-01-13 | 2025-01-13
Milestones | COLO 4 | Milestone | #000000 | ML21 | Complete Utility Power- On | 2025-05-05 | 2025-05-05
Milestones | COLO 5 | Milestone | #000000 | ML21 | Complete Utility Power- On | 2025-05-05 | 2025-05-05
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-03-11 | 2025-03-13
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-03-19 | 2025-03-21
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-04-11 | 2025-04-15
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-03-31 | 2025-04-02
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-04-15 | 2025-04-17
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-04-23 | 2025-04-25
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-16 | 2025-05-19
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-05 | 2025-05-07
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-19 | 2025-05-21
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-05-28 | 2025-05-30
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-06-20 | 2025-06-23
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE32 | Connect Perimeter Cable Trays to HAC Cable Trays | 2025-06-07 | 2025-06-10
Commissioning | COLO 3 - CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-04 | 2025-06-12
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-09 | 2025-06-18
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-24 | 2025-07-07
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-13 | 2025-06-23
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-20 | 2025-06-28
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-06-25 | 2025-07-03
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-08-06 | 2025-08-14
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-07-18 | 2025-07-28
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-07-19 | 2025-07-29
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-07-24 | 2025-08-02
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-08-25 | 2025-09-03
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE33 | Control Power Checks | 2025-08-04 | 2025-08-12
Milestones | COLO 4 | Milestone | #000000 | ML21 | CX L3 Complete | 2025-09-19 | 2025-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Cx L5 IST Complete | 2025-10-20 | 2025-10-20
Milestones | COLO 5 | Milestone | #000000 | ML21 | CX Level 3 Complete | 2025-10-11 | 2025-10-11
Milestones | COLO 5 | Milestone | #000000 | ML21 | Cx Level 5 IST Complete | 2025-11-19 | 2025-11-19
Fitout | COLO 3 - CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-03-11 | 2025-03-14
Fitout | COLO 3 - CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-03-19 | 2025-03-24
Fitout | COLO 3 - CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-04-11 | 2025-04-16
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-03-31 | 2025-04-03
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-04-15 | 2025-04-18
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-04-23 | 2025-04-26
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-05-16 | 2025-05-20
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-05-05 | 2025-05-08
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-05-19 | 2025-05-22
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-05-28 | 2025-05-31
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Detail HACs | 2025-06-20 | 2025-06-24
Fitout | CELL 4 Data Hall Fitout Activities | HAC's | #FED8E8 | S2 | Detail HACs | 2025-06-07 | 2025-06-11
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-06 | 2025-02-07
Fitout | COLO 3 - CELL 1 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-15 | 2025-02-15
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-06 | 2025-03-06
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-13 | 2025-02-13
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-04 | 2025-03-04
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-08 | 2025-03-10
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-08 | 2025-03-08
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-27 | 2025-03-27
Fitout | CELL 4 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-24 | 2025-02-25
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-02-24 | 2025-02-24
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-14 | 2025-03-14
Fitout | CELL 1 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-11 | 2025-03-12
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-11 | 2025-03-11
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-29 | 2025-03-29
Fitout | CELL 2 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-19 | 2025-03-20
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-19 | 2025-03-19
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-07 | 2025-04-07
Fitout | CELL 3 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-11 | 2025-04-14
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-11 | 2025-04-11
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-30 | 2025-04-30
Fitout | CELL 4 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-31 | 2025-04-01
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-03-31 | 2025-03-31
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-18 | 2025-04-18
Fitout | CELL 1 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-15 | 2025-04-16
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-15 | 2025-04-15
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-02 | 2025-05-02
Fitout | CELL 2 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-23 | 2025-04-24
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-04-23 | 2025-04-23
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-12 | 2025-05-12
Fitout | CELL 3 Data Hall | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-16 | 2025-05-17
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-16 | 2025-05-16
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-06-04 | 2025-06-04
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-05 | 2025-05-06
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-05 | 2025-05-05
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Drop Cable Tray [Hanging Rods] | 2025-05-22 | 2025-05-22
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Earthworks & U/G Utilities Start | 2025-03-05 | 2025-03-05
Milestones | COLO 5 | Milestone | #000000 | ML21 | Entire Building | 2025-02-14 | 2025-02-14
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-06-19 | 2025-06-27
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-07-08 | 2025-07-18
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-06-24 | 2025-07-02
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-06-30 | 2025-07-10
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-07-07 | 2025-07-15
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-08-15 | 2025-08-25
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-07-29 | 2025-08-06
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-07-30 | 2025-08-07
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-08-04 | 2025-08-12
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-09-04 | 2025-09-13
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | EE34 | EPMS Point to Point Checks | 2025-08-13 | 2025-08-22
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Final Completion/ Turnover to Operations | 2025-10-02 | 2025-10-02
Milestones | COLO 4 | Milestone | #000000 | ML21 | Final Completion/ Turnover to Operations | 2025-11-06 | 2025-11-06
Milestones | COLO 5 | Milestone | #000000 | ML21 | Final Completion/Turnover to Operations | 2025-12-04 | 2025-12-04
Site Prep/ Mobilization | Milestone | Milestone | #000000 | ML21 | Fine Grading Building Pad | 2024-08-19 | 2024-09-04
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-01 | 2025-02-04
Fitout | COLO 3 - CELL 1 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-22 | 2025-03-04
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-06 | 2025-03-07
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-11 | 2025-02-13
Fitout | COLO 3 - CELL 2 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-04 | 2025-03-05
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-06 | 2025-03-08
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-08 | 2025-03-10
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-27 | 2025-03-28
Fitout | CELL 4 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-21 | 2025-02-24
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-24 | 2025-02-25
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-14 | 2025-03-15
Fitout | CELL 1 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-08 | 2025-03-11
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-11 | 2025-03-12
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-29 | 2025-03-31
Fitout | CELL 2 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-17 | 2025-03-19
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-19 | 2025-03-20
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-07 | 2025-04-08
Fitout | CELL 3 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-09 | 2025-04-11
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-11 | 2025-04-14
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-30 | 2025-05-01
Fitout | CELL 4 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-28 | 2025-03-31
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-03-31 | 2025-04-01
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-18 | 2025-04-19
Fitout | CELL 1 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-11 | 2025-04-15
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-15 | 2025-04-16
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-02 | 2025-05-05
Fitout | CELL 2 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-21 | 2025-04-23
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-04-23 | 2025-04-24
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-12 | 2025-05-13
Fitout | CELL 3 Data Hall | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-14 | 2025-05-16
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-16 | 2025-05-17
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-06-04 | 2025-06-05
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-01 | 2025-05-05
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-05 | 2025-05-06
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-05-22 | 2025-05-23
Fitout | Fire Riser Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-12 | 2025-02-13
Fitout | Loading Dock | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-15 | 2025-02-17
Fitout | Restrooms & Janitor Room | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-13 | 2025-02-14
Fitout | SER (Security Equipment Room) | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-06 | 2025-02-07
Fitout | STORAGE (High Value & Secure) Rooms | Framing | #3598FE | J5 | Finish Dry-Wall | 2025-02-26 | 2025-03-03
Fitout | Electrical Room | Framing | #3598FE | J13 | Finsh Drywall and Wall Protection | 2025-01-28 | 2025-01-31
Fitout | Entry Room 1 | Framing | #3598FE | J13 | Finsh Drywall and Wall Protection | 2025-01-30 | 2025-02-03
Fitout | Entry Room 2 | Framing | #3598FE | J13 | Finsh Drywall and Wall Protection | 2025-02-01 | 2025-02-05
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | J13 | Finsh Drywall and Wall Protection | 2025-02-04 | 2025-02-07
Fitout | Electrical Room | Framing | #3598FE | J13 | Fire Protection OH R/I | 2025-01-20 | 2025-01-20
Fitout | Entry Room 1 | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-21 | 2025-01-21
Fitout | Entry Room 2 | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-22 | 2025-01-22
Fitout | FCR (Facilities Control Room) | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-23 | 2025-01-23
Fitout | Fire Riser Room | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-27 | 2025-01-27
Fitout | Loading Dock | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-29 | 2025-01-29
Fitout | Restrooms & Janitor Room | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-28 | 2025-01-28
Fitout | SER (Security Equipment Room) | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-24 | 2025-01-24
Fitout | STORAGE (High Value & Secure) Rooms | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-01-25 | 2025-01-25
Fitout | STORAGE (High Value & Secure) Rooms | Fire Protection | #D85234 | GSB | Fire Protection OH R/I | 2025-03-06 | 2025-03-17
Milestones | COLO 4 | Milestone | #000000 | ML21 | Foundation Start | 2024-09-16 | 2024-09-16
Milestones | COLO 5 | Milestone | #000000 | ML21 | Foundation Start | 2024-09-09 | 2024-09-09
Milestones | Milestone | Milestone | #000000 | ML21 | Foundations / Stem Walls (100% Complete) | 2024-10-10 | 2024-11-02
Milestones | Milestone | Milestone | #000000 | ML21 | Foundations / Stem Walls (50% Complete) | 2024-09-09 | 2024-10-09
Fitout | Electrical Room | Framing | #3598FE | J11 | Framing | 2025-01-21 | 2025-01-21
Fitout | Entry Room 1 | Framing | #3598FE | J11 | Framing | 2025-01-22 | 2025-01-22
Fitout | Entry Room 2 | Framing | #3598FE | J11 | Framing | 2025-01-23 | 2025-01-23
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | J11 | Framing | 2025-01-24 | 2025-01-24
Fitout | Fire Riser Room | Framing | #3598FE | J11 | Framing | 2025-01-28 | 2025-01-28
Fitout | Loading Dock | Framing | #3598FE | J11 | Framing | 2025-01-30 | 2025-01-30
Fitout | Restrooms & Janitor Room | Framing | #3598FE | J11 | Framing | 2025-01-29 | 2025-01-29
Fitout | SER (Security Equipment Room) | Framing | #3598FE | J11 | Framing | 2025-01-25 | 2025-01-25
Fitout | STORAGE (High Value & Secure) Rooms | Framing | #3598FE | J11 | Framing | 2025-01-27 | 2025-01-27
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-06-28 | 2025-07-02
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-07-19 | 2025-07-24
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-07-03 | 2025-07-09
Commissioning | CELL 1 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-07-11 | 2025-07-15
Commissioning | CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-07-16 | 2025-07-19
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-26 | 2025-08-29
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-07 | 2025-08-11
Commissioning | CELL 1 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-08 | 2025-08-12
Commissioning | CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-13 | 2025-08-18
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-09-15 | 2025-09-19
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx1 | FTE Energizations [480v] | 2025-08-23 | 2025-08-27
Milestones | General | Milestone | #000000 | ML21 | GC Mobilization Finish/ Site Secured | 2024-09-16 | 2024-09-16
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | GC Mobilization Start | 2025-02-25 | 2025-02-25
Fitout | COLO 3 - CELL 1 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-02-18 | 2025-02-18
Fitout | COLO 3 - CELL 1 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-07 | 2025-03-07
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-11 | 2025-03-13
Fitout | COLO 3 - CELL 2 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-02-26 | 2025-02-26
Fitout | COLO 3 - CELL 2 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-02-18 | 2025-02-18
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-08 | 2025-03-11
Fitout | COLO 3 - CELL 3 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-21 | 2025-03-21
Fitout | CELL 3 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-13 | 2025-03-13
Fitout | CELL 3 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-01 | 2025-04-03
Fitout | CELL 4 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-10 | 2025-03-10
Fitout | CELL 4 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-02-28 | 2025-02-28
Fitout | CELL 4 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-19 | 2025-03-21
Fitout | CELL 1 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-25 | 2025-03-25
Fitout | CELL 1 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-15 | 2025-03-15
Fitout | CELL 1 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-03 | 2025-04-05
Fitout | CELL 2 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-02 | 2025-04-02
Fitout | CELL 2 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-03-25 | 2025-03-25
Fitout | CELL 2 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-11 | 2025-04-15
Fitout | CELL 3 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-25 | 2025-04-25
Fitout | CELL 3 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-17 | 2025-04-17
Fitout | CELL 3 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-06 | 2025-05-08
Fitout | CELL 4 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-14 | 2025-04-14
Fitout | CELL 4 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-04 | 2025-04-04
Fitout | CELL 4 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-23 | 2025-04-25
Fitout | CELL 1 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-28 | 2025-04-28
Fitout | CELL 1 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-19 | 2025-04-19
Fitout | CELL 1 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-08 | 2025-05-10
Fitout | CELL 2 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-07 | 2025-05-07
Fitout | CELL 2 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-04-28 | 2025-04-28
Fitout | CELL 2 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-16 | 2025-05-19
Fitout | CELL 3 Data Hall | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-30 | 2025-05-30
Fitout | CELL 3 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-21 | 2025-05-21
Fitout | CELL 3 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-06-09 | 2025-06-11
Fitout | CELL 4 Data Hall Fitout Activities | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-17 | 2025-05-17
Fitout | CELL 4 Electrical Room | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-09 | 2025-05-09
Fitout | CELL 4 Mechanical Gallery | Cx | #8ED973 | Cx2 | General Cleaning | 2025-05-28 | 2025-05-30
Milestones | COLO 4 | Milestone | #000000 | ML21 | Generator Ready for Fuel | 2025-04-24 | 2025-04-24
Milestones | COLO 5 | Milestone | #000000 | ML21 | Generator Ready for Fuel | 2025-05-31 | 2025-05-31
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Generator Ready for Fuel (Exterior Yard) | 2025-03-15 | 2025-03-15
Fitout | CELL 1 Data Hall | Framing | #3598FE | J3 | IInstall Framing | 2025-02-25 | 2025-02-27
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-01-25 | 2025-01-28
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-01-31 | 2025-02-10
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-03 | 2025-02-05
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-05 | 2025-02-06
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-26 | 2025-02-28
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-28 | 2025-03-03
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-14 | 2025-02-17
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-17 | 2025-02-18
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-02-28 | 2025-03-04
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-04 | 2025-03-05
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-10 | 2025-03-12
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-12 | 2025-03-13
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-02 | 2025-04-04
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-04 | 2025-04-05
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-20 | 2025-03-24
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-03-24 | 2025-03-25
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-04 | 2025-04-07
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-07 | 2025-04-08
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-14 | 2025-04-16
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-16 | 2025-04-17
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-05-07 | 2025-05-09
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-05-09 | 2025-05-10
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-24 | 2025-04-26
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE2 | In-Wall R/I | 2025-04-26 | 2025-04-28
Fitout | COLO 3 - CELL 1 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-03-12 | 2025-03-24
Fitout | COLO 3 - CELL 2 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-03-10 | 2025-03-20
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-04-02 | 2025-04-14
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-03-20 | 2025-04-01
Fitout | CELL 1 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-04-04 | 2025-04-16
Fitout | CELL 2 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-04-14 | 2025-04-24
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-05-07 | 2025-05-17
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-04-24 | 2025-05-06
Fitout | CELL 1 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-05-09 | 2025-05-20
Fitout | CELL 2 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-05-17 | 2025-05-29
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-06-10 | 2025-06-21
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBA | Install BAS Equipments | 2025-05-29 | 2025-06-09
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-02-25 | 2025-03-03
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-03-06 | 2025-03-11
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-03-29 | 2025-04-03
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-03-17 | 2025-03-21
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-04-01 | 2025-04-05
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-04-09 | 2025-04-15
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-05-02 | 2025-05-08
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-04-21 | 2025-04-25
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-05-06 | 2025-05-10
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-05-14 | 2025-05-19
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-06-06 | 2025-06-11
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE10 | Install Busways on HAC Arms | 2025-05-27 | 2025-05-30
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-02-17 | 2025-02-18
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-12 | 2025-03-13
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-02-14 | 2025-02-15
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-10 | 2025-03-11
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-10 | 2025-03-11
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-02 | 2025-04-03
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-02-25 | 2025-02-26
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-20 | 2025-03-21
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-12 | 2025-03-13
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-04 | 2025-04-05
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-03-20 | 2025-03-21
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-14 | 2025-04-15
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-14 | 2025-04-15
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-07 | 2025-05-08
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-01 | 2025-04-02
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-24 | 2025-04-25
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-16 | 2025-04-17
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-09 | 2025-05-10
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-04-24 | 2025-04-25
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-17 | 2025-05-19
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-17 | 2025-05-19
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-06-10 | 2025-06-11
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-06 | 2025-05-07
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE35 | Install Cable Trays / Pathways | 2025-05-29 | 2025-05-30
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-02-18 | 2025-02-21
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-02-26 | 2025-03-03
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-03-21 | 2025-03-26
Fitout | CELL 4 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-03-10 | 2025-03-13
Fitout | CELL 1 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-03-25 | 2025-03-28
Fitout | CELL 2 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-04-02 | 2025-04-05
Fitout | CELL 3 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-04-25 | 2025-04-29
Fitout | CELL 4 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-04-14 | 2025-04-17
Fitout | CELL 1 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-04-28 | 2025-05-01
Fitout | CELL 2 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-05-07 | 2025-05-10
Fitout | CELL 3 Data Hall | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-05-30 | 2025-06-03
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J16 | Install Ceiling Grid | 2025-05-17 | 2025-05-21
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-07 | 2025-03-11
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-05 | 2025-03-08
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-28 | 2025-04-01
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-15 | 2025-03-19
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-03-31 | 2025-04-03
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-04-08 | 2025-04-11
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-05-01 | 2025-05-06
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-04-19 | 2025-04-23
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-05-05 | 2025-05-08
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-05-13 | 2025-05-16
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-06-05 | 2025-06-09
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J20 | Install Ceiling Grid + Device Tiles | 2025-05-23 | 2025-05-28
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-03-14 | 2025-03-17
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-03-24 | 2025-03-26
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-04-16 | 2025-04-18
Fitout | CELL 4 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-04-03 | 2025-04-05
Fitout | CELL 1 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-04-18 | 2025-04-21
Fitout | CELL 2 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-04-26 | 2025-04-29
Fitout | CELL 3 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-05-20 | 2025-05-22
Fitout | CELL 4 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-05-08 | 2025-05-10
Fitout | CELL 1 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-05-22 | 2025-05-23
Fitout | CELL 2 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-05-31 | 2025-06-03
Fitout | CELL 3 Data Hall | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-06-24 | 2025-06-26
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J21 | Install Conduits PDU to Cable Trays | 2025-06-11 | 2025-06-13
Site Utilities | Overall | Framing | #3598FE | J22 | Install Deep Telecom | 2024-09-23 | 2024-10-21
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-02-27 | 2025-02-28
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-03-08 | 2025-03-10
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-04-01 | 2025-04-02
Fitout | CELL 4 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-03-19 | 2025-03-20
Fitout | CELL 1 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-04-03 | 2025-04-04
Fitout | CELL 2 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-04-11 | 2025-04-14
Fitout | CELL 3 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-05-06 | 2025-05-07
Fitout | CELL 4 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-04-23 | 2025-04-24
Fitout | CELL 1 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-05-08 | 2025-05-09
Fitout | CELL 2 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-05-16 | 2025-05-17
Fitout | CELL 3 Data Hall | Framing | #3598FE | J23 | Install Device Tiles | 2025-06-09 | 2025-06-10
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J23 | Install Device Tiles | 2025-05-28 | 2025-05-29
Fitout | Admin | Framing | #3598FE | J24 | Install Doors | 2025-02-22 | 2025-02-26
Fitout | Fire Riser Room | Framing | #3598FE | J30 | Install downcomers | 2025-01-31 | 2025-01-31
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-01-29 | 2025-01-31
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-02-06 | 2025-02-10
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-03-03 | 2025-03-05
Fitout | CELL 4 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-02-18 | 2025-02-20
Fitout | CELL 1 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-03-05 | 2025-03-07
Fitout | CELL 2 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-03-13 | 2025-03-15
Fitout | CELL 3 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-04-05 | 2025-04-08
Fitout | CELL 4 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-03-25 | 2025-03-27
Fitout | CELL 1 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-04-08 | 2025-04-10
Fitout | CELL 2 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-04-17 | 2025-04-19
Fitout | CELL 3 Data Hall | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-05-10 | 2025-05-13
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J4 | Install Drywall (One Side - Facing DH) | 2025-04-28 | 2025-04-30
Fitout | COLO 3 - CELL 1 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-02-11 | 2025-02-21
Fitout | COLO 3 - CELL 2 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-02-07 | 2025-02-12
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-03-04 | 2025-03-07
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-02-19 | 2025-02-22
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-03-06 | 2025-03-10
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-03-14 | 2025-03-18
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-04-07 | 2025-04-10
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-03-26 | 2025-03-29
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-04-09 | 2025-04-14
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-04-18 | 2025-04-22
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-05-12 | 2025-05-15
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J4 | Install Drywall [Elec + Battery Rooms] | 2025-04-29 | 2025-05-02
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-03-04 | 2025-03-05
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-02-28 | 2025-03-03
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-03-25 | 2025-03-26
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-03-12 | 2025-03-13
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-03-27 | 2025-03-28
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-04-04 | 2025-04-05
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-04-28 | 2025-04-29
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-04-16 | 2025-04-17
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-04-30 | 2025-05-01
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-05-09 | 2025-05-10
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-06-02 | 2025-06-03
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J4 | Install Drywall [Mech Gallery] | 2025-05-20 | 2025-05-21
Fitout | Fire Riser Room | Framing | #3598FE | J31 | Install Duct Work | 2025-01-29 | 2025-01-30
Fitout | Loading Dock | Framing | #3598FE | J31 | Install Ductwork | 2025-01-29 | 2025-02-15
Fitout | Loading Dock | Framing | #3598FE | J31 | Install Ductwork (Remaining Rooms, Corridor) | 2025-01-30 | 2025-02-17
Fitout | STORAGE (High Value & Secure) Rooms | Framing | #3598FE | J31 | Install Ductwork and Cracs | 2025-02-07 | 2025-02-25
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J32 | Install Exterior Wall Panels | 2024-11-30 | 2024-12-14
Core & Shell | COLO 4 | Framing | #3598FE | J32 | Install Exterior Wall Panels | 2024-12-16 | 2024-12-31
Core & Shell | COLO 5 | Framing | #3598FE | J32 | Install Exterior Wall Panels | 2025-01-02 | 2025-01-15
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-02-27 | 2025-03-05
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-03-08 | 2025-03-13
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-01 | 2025-04-05
Fitout | CELL 4 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-03-19 | 2025-03-25
Fitout | CELL 1 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-03 | 2025-04-08
Fitout | CELL 2 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-11 | 2025-04-17
Fitout | CELL 3 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-06 | 2025-05-10
Fitout | CELL 4 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-04-23 | 2025-04-28
Fitout | CELL 1 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-08 | 2025-05-13
Fitout | CELL 2 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-16 | 2025-05-21
Fitout | CELL 3 Data Hall | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-06-09 | 2025-06-13
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J33 | Install Fiber Runner [ Cable Trays on HAC Arms] | 2025-05-28 | 2025-06-02
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-01-20 | 2025-01-24
Fitout | COLO 3 - CELL 1 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-01-25 | 2025-01-30
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-01-30 | 2025-02-01
Fitout | COLO 3 - CELL 2 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-02-03 | 2025-02-04
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-02-22 | 2025-02-25
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-02-26 | 2025-02-27
Fitout | CELL 4 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-02-11 | 2025-02-13
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-02-14 | 2025-02-15
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-02-28 | 2025-03-03
Fitout | CELL 2 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-03-06 | 2025-03-08
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-03-10 | 2025-03-11
Fitout | CELL 3 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-03-29 | 2025-04-01
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-04-02 | 2025-04-03
Fitout | CELL 4 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-03-17 | 2025-03-19
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-03-20 | 2025-03-21
Fitout | CELL 1 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-04-01 | 2025-04-03
Fitout | CELL 1 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-04-04 | 2025-04-05
Fitout | CELL 2 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-04-09 | 2025-04-11
Fitout | CELL 2 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-04-14 | 2025-04-15
Fitout | CELL 3 Data Hall | Framing | #3598FE | J3 | Install Framing | 2025-05-02 | 2025-05-06
Fitout | CELL 3 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-05-07 | 2025-05-08
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J3 | Install Framing | 2025-04-21 | 2025-04-23
Fitout | CELL 4 Electrical Room | Framing | #3598FE | J3 | Install Framing | 2025-04-24 | 2025-04-25
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E34 | Install Generators | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F2F09E | E34 | Install Generators | 2025-04-11 | 2025-04-24
Electrical Yard | COLO 5 | Electrical | #F2F09E | E34 | Install Generators | 2025-05-19 | 2025-05-31
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J34 | Install Louvers & Dampers | 2024-12-16 | 2025-01-06
Core & Shell | COLO 4 | Framing | #3598FE | J34 | Install Louvers & Dampers | 2025-01-07 | 2025-01-25
Core & Shell | COLO 5 | Framing | #3598FE | J34 | Install Louvers & Dampers | 2025-01-27 | 2025-02-14
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J35 | Install Misc. Metals (Trims, Gutters, Catwalks) | 2024-12-30 | 2025-01-17
Core & Shell | COLO 4 | Framing | #3598FE | J35 | Install Misc. Metals (Trims, Gutters, Catwalks) | 2025-01-11 | 2025-01-30
Core & Shell | COLO 5 | Framing | #3598FE | J35 | Install Misc. Metals (Trims, Gutters, Catwalks) | 2025-01-27 | 2025-02-14
Site Utilities | Overall | Framing | #3598FE | J36 | Install MV Ductbanks | 2024-10-04 | 2024-11-18
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-02-22 | 2025-02-26
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-03-04 | 2025-03-07
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-03-27 | 2025-03-31
Fitout | CELL 4 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-03-14 | 2025-03-18
Fitout | CELL 1 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-03-29 | 2025-04-02
Fitout | CELL 2 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-04-07 | 2025-04-10
Fitout | CELL 3 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-04-30 | 2025-05-05
Fitout | CELL 4 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-04-18 | 2025-04-22
Fitout | CELL 1 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-05-02 | 2025-05-07
Fitout | CELL 2 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-05-12 | 2025-05-15
Fitout | CELL 3 Data Hall | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-06-04 | 2025-06-07
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J37 | Install Perimeter Cable Trays | 2025-05-22 | 2025-05-27
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J38 | Install Primary Steel | 2024-10-21 | 2024-11-07
Core & Shell | COLO 4 | Framing | #3598FE | J38 | Install Primary Steel | 2024-11-02 | 2024-11-20
Core & Shell | COLO 5 | Framing | #3598FE | J38 | Install Primary Steel | 2024-11-14 | 2024-12-03
Fitout | Entry Room 1 | Framing | #3598FE | J39 | Install Raceway | 2025-02-06 | 2025-02-10
Fitout | Entry Room 2 | Framing | #3598FE | J39 | Install Raceway | 2025-02-10 | 2025-02-12
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | J39 | Install Raceway | 2025-02-12 | 2025-02-14
Fitout | SER (Security Equipment Room) | Framing | #3598FE | J39 | Install Raceway | 2025-02-12 | 2025-02-14
Core & Shell | Admin/ COLO 3 | Framing | #3598FE | J40 | Install Roof Panels | 2024-11-08 | 2024-11-29
Core & Shell | COLO 4 | Framing | #3598FE | J40 | Install Roof Panels | 2024-11-21 | 2024-12-14
Core & Shell | COLO 5 | Framing | #3598FE | J40 | Install Roof Panels | 2024-12-04 | 2024-12-31
Site Utilities | Overall | Framing | #3598FE | J41 | Install Sanitary Lines | 2024-11-04 | 2024-12-03
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-02-10 | 2025-02-12
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-02-18 | 2025-02-20
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-03-13 | 2025-03-15
Fitout | CELL 4 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-02-28 | 2025-03-04
Fitout | CELL 1 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-03-15 | 2025-03-18
Fitout | CELL 2 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-03-25 | 2025-03-27
Fitout | CELL 3 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-04-17 | 2025-04-19
Fitout | CELL 4 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-04-04 | 2025-04-07
Fitout | CELL 1 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-04-19 | 2025-04-22
Fitout | CELL 2 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-04-28 | 2025-04-30
Fitout | CELL 3 Data Hall | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-05-21 | 2025-05-23
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J6 | Install Screen Mesh + Caulking | 2025-05-09 | 2025-05-12
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-02-21 | 2025-02-22
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-03-17 | 2025-03-18
Fitout | CELL 4 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-03-05 | 2025-03-06
Fitout | CELL 1 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-03-19 | 2025-03-20
Fitout | CELL 2 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-03-28 | 2025-03-29
Fitout | CELL 3 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-04-21 | 2025-04-22
Fitout | CELL 4 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-04-08 | 2025-04-09
Fitout | CELL 1 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-04-23 | 2025-04-24
Fitout | CELL 2 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-05-01 | 2025-05-02
Fitout | CELL 3 Data Hall | Framing | #3598FE | J42 | Install Secondary Steel | 2025-05-27 | 2025-05-27
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J42 | Install Secondary Steel | 2025-05-13 | 2025-05-14
Site Utilities | Overall | Framing | #3598FE | J43 | Install Storm Lines | 2024-11-09 | 2024-12-17
Site Utilities | Under Building Pad | Electrical | #F2F09E | EE36 | Install UG Electrical / UPM Crossing (under Building Pad) | 2024-09-30 | 2024-10-30
Site Utilities | Under Building Pad | Electrical | #F2F09E | EE37 | Install UG Telecom (under Building Pad) | 2024-09-18 | 2024-10-04
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E28 | Install UMSs | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F2F09E | E28 | Install UMSs | 2025-04-02 | 2025-04-15
Electrical Yard | COLO 5 | Electrical | #F2F09E | E28 | Install UMSs | 2025-05-16 | 2025-05-29
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E30 | Install UPMs | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F2F09E | E30 | Install UPMs | 2025-04-02 | 2025-04-15
Electrical Yard | COLO 5 | Electrical | #F2F09E | E30 | Install UPMs | 2025-05-14 | 2025-05-27
Site Utilities | Overall | Electrical | #F2F09E | E38 | Install Water Line | 2024-11-15 | 2024-12-26
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E39 | Install XFMs | 2025-03-04 | 2025-03-15
Electrical Yard | COLO 4 | Electrical | #F2F09E | E39 | Install XFMs | 2025-04-02 | 2025-04-15
Electrical Yard | COLO 5 | Electrical | #F2F09E | E39 | Install XFMs | 2025-05-12 | 2025-05-23
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-01-17 | 2025-01-17
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-01-29 | 2025-01-29
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-02-21 | 2025-02-21
Fitout | CELL 4 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-02-10 | 2025-02-10
Fitout | CELL 1 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-02-24 | 2025-02-24
Fitout | CELL 2 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-03-05 | 2025-03-05
Fitout | CELL 3 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-03-28 | 2025-03-28
Fitout | CELL 4 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-03-15 | 2025-03-15
Fitout | CELL 1 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-03-31 | 2025-03-31
Fitout | CELL 2 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-04-08 | 2025-04-08
Fitout | CELL 3 Data Hall | Framing | #3598FE | J1 | Layout Framing | 2025-05-01 | 2025-05-01
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J1 | Layout Framing | 2025-04-19 | 2025-04-19
Fitout | Admin | Electrical | #F2F09E | EEA | Light Fixtures Installation | 2025-02-27 | 2025-03-11
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-07-19 | 2025-07-23
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-08-09 | 2025-08-14
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-07-24 | 2025-07-29
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-07-31 | 2025-08-04
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-08-05 | 2025-08-08
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-09-16 | 2025-09-19
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-08-27 | 2025-08-30
Commissioning | CELL 1 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-08-28 | 2025-09-02
Commissioning | CELL 2 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-09-03 | 2025-09-08
Commissioning | CELL 3 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-10-06 | 2025-10-11
Commissioning | CELL 4 Energizations & Startups (Level 3) | Electrical | #F2F09E | E39 | Loadbanking | 2025-09-13 | 2025-09-17
Fitout | Electrical Room | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-22 | 2025-01-23
Fitout | Entry Room 1 | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-24 | 2025-01-25
Fitout | Entry Room 2 | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-27 | 2025-01-28
Fitout | FCR (Facilities Control Room) | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-29 | 2025-01-30
Fitout | Fire Riser Room | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-02-05 | 2025-02-06
Fitout | Loading Dock | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-02-11 | 2025-02-12
Fitout | Restrooms & Janitor Room | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-02-07 | 2025-02-10
Fitout | SER (Security Equipment Room) | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-01-31 | 2025-02-01
Fitout | STORAGE (High Value & Secure) Rooms | MEP | #D86DCD | MEP1 | MEP Rough-In & OH | 2025-02-03 | 2025-02-04
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 1 | 2025-04-25 | 2025-05-05
Electrical Yard | COLO 4 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 1 | 2025-04-25 | 2025-05-05
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 2 | 2025-05-06 | 2025-05-14
Electrical Yard | COLO 4 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 2 | 2025-05-06 | 2025-05-14
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 3 | 2025-05-27 | 2025-06-03
Electrical Yard | COLO 4 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 3 | 2025-05-27 | 2025-06-04
Electrical Yard | Admin/ COLO 3 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 4 | 2025-05-15 | 2025-05-23
Electrical Yard | COLO 4 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating to Cell 4 | 2025-05-15 | 2025-05-23
Electrical Yard | COLO 5 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating(To Junction Box) to Cell 1 | 2025-05-02 | 2025-05-12
Electrical Yard | COLO 5 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating(To Junction Box) to Cell 2 | 2025-05-13 | 2025-05-21
Electrical Yard | COLO 5 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating(To Junction Box) to Cell 3 | 2025-06-02 | 2025-06-10
Electrical Yard | COLO 5 | Electrical | #F2F09E | E35 | MV Cable Pulling & Terminating(To Junction Box) to Cell 4 | 2025-05-22 | 2025-05-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ1 | OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/04/24) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ2 | OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/9/24) | 2024-09-09 | 2024-09-09
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ3 | OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date- 3/8/2025) | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ4 | OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 4/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ5 | OFCI- Receive Auxillary (Mech) Power Distribution Panels (ADP) (Del Date- 3/8/2025) | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ6 | OFCI- Air Handling Units (AHU) (Stulz) Delivered | 2025-03-13 | 2025-03-13
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ7 | OFCI- Air Handling Units (AHU) (Stulz) Delivered | 2025-04-05 | 2025-04-05
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ8 | OFCI- Air Handling Units (AHU) (Stulz) Delivered | 2025-05-11 | 2025-05-11
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ9 | OFCI- Air Handling Units (AHU) (Stulz) Shipped/ROJ | 2025-03-09 | 2025-03-13
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ10 | OFCI- Air Handling Units (AHU) (Stulz) Shipping/ ROJ | 2025-04-01 | 2025-04-05
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ11 | OFCI- Air Handling Units (AHU) (Stulz) Shipping/ROJ | 2025-05-11 | 2025-05-11
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ12 | OFCI- Auto Transfer Control Panel (TCP) Delivered | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ13 | OFCI- Auto Transfer Control Panel (TCP) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ14 | OFCI- Auto Transfer Control Panel (TCP) Delivered | 2025-04-04 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ15 | OFCI- Auto Transfer Control Panel (TCP) Shipping/ ROJ | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ16 | OFCI- Auto Transfer Control Panel (TCP) Shipping/ROJ | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ17 | OFCI- Auto Transfer Control Panel (TCP) Shipping/ROJ | 2025-03-30 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ18 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ19 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ20 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Delivered | 2025-04-20 | 2025-04-20
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ21 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ22 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ23 | OFCI- Automatic Transfer Switches (ATS) (Schneider) Shipping/ROJ | 2025-04-20 | 2025-04-20
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ24 | OFCI- Auxillary (Mech) Power Distribution Panels (ADP) Delivered | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ25 | OFCI- Auxillary (Mech) Power Distribution Panels (ADP) Shipping/ ROJ | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ26 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Delivered | 2025-01-04 | 2025-01-04
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ27 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Delivered | 2025-02-02 | 2025-02-02
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ28 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ | 2024-12-29 | 2025-01-04
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ29 | OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ | 2025-01-28 | 2025-02-02
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ30 | OFCI- Building Automation System (BAS) (ALC) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ31 | OFCI- Building Automation System (BAS) (ALC) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ32 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ33 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Delivered | 2025-05-03 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ34 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ35 | OFCI- Busway / Busplugs (BSW) (Starline Holding) Shipping/ROJ | 2025-04-29 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ36 | OFCI- Busway / Busplugs (Starline Holding) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ37 | OFCI- Busway / Busplugs (Starline Holding) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ38 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ39 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ40 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (Schneider) Delivered | 2025-04-20 | 2025-04-20
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ41 | OFCI- Elec. Performance Monitoring Syst. (EPMS) (Schneider) Shipping/ROJ | 2025-04-20 | 2025-04-20
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ42 | OFCI- Elec. Performance Monitoring System (EPMS) (Schneider) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ43 | OFCI- Elec. Performance Monitoring System (EPMS) (Schneider) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ44 | OFCI- HAC/Racking (Tate Access) Delivered | 2025-02-21 | 2025-02-21
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ45 | OFCI- HAC/Racking (Tate Access) Delivered | 2025-03-28 | 2025-03-28
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ46 | OFCI- HAC/Racking (Tate Access) Delivered | 2025-04-28 | 2025-04-28
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ47 | OFCI- HAC/Racking (Tate Access) Shipping/ ROJ | 2025-02-19 | 2025-02-21
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ48 | OFCI- HAC/Racking (Tate Access) Shipping/ROJ | 2025-03-26 | 2025-03-28
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ49 | OFCI- HAC/Racking (Tate Access) Shipping/ROJ | 2025-04-25 | 2025-04-28
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ50 | OFCI- LV Switchgear (Eaton) Delivered | 2025-03-02 | 2025-03-02
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ51 | OFCI- LV Switchgear (Eaton) Delivered | 2025-04-03 | 2025-04-03
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ52 | OFCI- LV Switchgear (Eaton) Shipping/ROJ | 2025-02-28 | 2025-03-02
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ53 | OFCI- LV Switchgear (Eaton) Shipping/ROJ | 2025-03-30 | 2025-04-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ54 | OFCI- LV Switchgear (LVS) (Eaton) Delivered | 2025-03-04 | 2025-03-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ55 | OFCI- LV Switchgear (LVS) (Eaton) Shipping/ ROJ | 2025-02-28 | 2025-03-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ56 | OFCI- Main LV Switch Board (MSB) Delivered | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ57 | OFCI- Main LV Switch Board (MSB) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ58 | OFCI- Main LV Switch Board (MSB) Delivered | 2025-04-04 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ59 | OFCI- Main LV Switch Board (MSB) Shipping/ ROJ | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ60 | OFCI- Main LV Switch Board (MSB) Shipping/ROJ | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ61 | OFCI- Main LV Switch Board (MSB) Shipping/ROJ | 2025-03-30 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ62 | OFCI- Mech Power Distribution Panels (ADP) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ63 | OFCI- Mech Power Distribution Panels (ADP) Delivered | 2025-04-04 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ64 | OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ65 | OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ | 2025-03-30 | 2025-04-04
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ66 | OFCI- Medium Voltage Switchgear (JDC Power Sys) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ67 | OFCI- Medium Voltage Switchgear (JDC Power Sys) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ68 | OFCI- Medium Voltage Switchgear (MVS) (JD Power Sys) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ69 | OFCI- Medium Voltage Switchgear (MVS) (JD Power Sys) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ70 | OFCI- Medium Voltage Switchgear (MVS) (JDC Power Sys) Delivered | 2025-05-03 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ71 | OFCI- Medium Voltage Switchgear (MVS) (JDC Power Sys) Shipping/ROJ | 2025-04-29 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ72 | OFCI- Packaged Diesel Generator Set (CAT Holt) Delivered | 2025-02-24 | 2025-02-24
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ73 | OFCI- Packaged Diesel Generator Set (CAT Holt) Shipping/ ROJ | 2025-02-20 | 2025-02-24
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ74 | OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Delivered | 2025-04-10 | 2025-04-10
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ75 | OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ | 2025-04-06 | 2025-04-10
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ76 | OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Delivered | 2025-05-15 | 2025-05-15
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ77 | OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ | 2025-05-11 | 2025-05-15
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ78 | OFCI- Pad Mounted Transformers (XFM-TX) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ79 | OFCI- Pad Mounted Transformers (XFM-TX) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ80 | OFCI- Pad Mounted Transformers (XMF) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ81 | OFCI- Pad Mounted Transformers (XMF) Delivered | 2025-05-03 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ82 | OFCI- Pad Mounted Transformers (XMF) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ83 | OFCI- Pad Mounted Transformers (XMF) Shipping/ROJ | 2025-04-29 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 3-5 | ROJ | #747474 | ROJ84 | OFCI- PEMB Procurement (1st Del) (Nucor) Delivered | 2024-10-25 | 2024-10-25
MSFT OFCI ROJ Dates | COLO 3-5 | ROJ | #747474 | ROJ85 | OFCI- PEMB Procurement (1st Del) (Nucor) Shipping/ ROJ | 2024-10-21 | 2024-10-25
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ86 | OFCI- Power Distribution Units (PDU) (ABB) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ87 | OFCI- Power Distribution Units (PDU) (ABB) Delivered | 2025-05-07 | 2025-05-07
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ88 | OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ89 | OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ | 2025-05-03 | 2025-05-07
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ90 | OFCI- Power Distribution Units (PDU) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ91 | OFCI- Power Distribution Units (PDU) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ92 | OFCI- Receive Elec. Performance Monitoring System (EPMS) (Schneider) (SOW Del Date- 4/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ93 | OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/16/24) | 2024-09-16 | 2024-09-16
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ94 | OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ95 | OFCI- Receive Auto Transfer Control Panel (TCP) (Del Date-3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ96 | OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 6/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ97 | OFCI- Receive Automatic Transfer Switches (ATS) (Schneider) (SOW Del Date- 8/31/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ98 | OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 1/28/25) | 2025-01-28 | 2025-01-28
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ99 | OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 12/29/24) | 2024-12-29 | 2024-12-29
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ100 | OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 11/28/24) | 2024-11-30 | 2024-11-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ101 | OFCI- Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 2/23/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ102 | OFCI- Receive Busway / Busplugs (BSW) (Starline Holding) (SOW Del Date- 4/23/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ103 | OFCI- Receive Busway / Busplugs (Starline Holding) (Del Date- 1/25/24) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ104 | OFCI- Receive Elec. Performance Monitoring Syst. (EPMS) (EPMS) (Schneider) (SOW Del Date- 6/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ105 | OFCI- Receive Elec. Performance Monitoring Syst. (EPMS) (Schneider) (SOW Del Date- 8/31/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ106 | OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 5/17/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ107 | OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 6/18/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ108 | OFCI- Receive HAC/Racking (Tate Access) (SOW Del Date- 7/3/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ109 | OFCI- Receive LV Switchgear (Eaton) (SOW Del Date- 2/28/25) | 2025-02-28 | 2025-02-28
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ110 | OFCI- Receive LV Switchgear (Eaton) (SOW Del Date- 3/30/25) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ111 | OFCI- Receive LV Switchgear (LVS) (Eaton) (SOW Del Date- 2/28/25) | 2025-02-28 | 2025-02-28
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ112 | OFCI- Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ113 | OFCI- Receive Main LV Switch Board (MSB) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ114 | OFCI- Receive Main LV Switch Board (MSB) (SOW Del Date- 3/8/2025) | 2025-03-08 | 2025-03-08
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ115 | OFCI- Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ116 | OFCI- Receive Mech Power Distribution Panels (ADP) (Del Date 3/30/2025) | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ117 | OFCI- Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 7/30/24) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ118 | OFCI- Receive Medium Voltage Switchgear (JDC Power Sys) (SOW Del Date- 8/30/24) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ119 | OFCI- Receive Medium Voltage Switchgear (MVS) (JDC Power Sys) (SOW Del Date- 10/30/24) | 2024-10-30 | 2024-10-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ120 | OFCI- Receive Packaged Diesel Generator Set (CAT Holt) (SOW Del Date- 5/14/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ121 | OFCI- Receive Packaged Diesel Generator Set (GEN) (CAT Holt) (SOW Del Date- 6/4/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ122 | OFCI- Receive Packaged Diesel Generator Set (GPC) (CAT Holt) (SOW Del Date- 6/26/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ123 | OFCI- Receive Pad Mounted Transformers (XFM-TX) (Del Date- 7/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ124 | OFCI- Receive Pad Mounted Transformers (XMF) (Del Date 10/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3-5 | ROJ | #747474 | ROJ125 | OFCI- Receive PEMB Procurement (1st Del) (Nucor) (SOW Del Date-10/3/24) | 2024-10-03 | 2024-10-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ126 | OFCI- Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 4/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ127 | OFCI- Receive Power Distribution Units (PDU) (ABB) (SOW Del Date- 9/30/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ128 | OFCI- Receive Utility Pad Mount Switchgear (Del Date- 7/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ129 | OFCI- Receive Utility Pad Mount Switchgear (UPM) (Del Date 10/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ130 | OFCI- Receive Utility Pad Mount Switchgear (UPM) (Del Date 8/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ131 | OFCI- Received SUB Warehouse 11/23/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 11/11/23) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ132 | OFCI- Received SUB Warehouse 12/28/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 12/11/23) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ133 | OFCI- Received SUB Warehouse 9/28/2023 UPS System w/ Battery (UPS) (Eaton) (SOW Del Date- 8/13/23) | 2024-09-05 | 2024-09-05
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ134 | OFCI- Reveive Pad Mounted Transformers (XMF) (Del Date 8/30/2024) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ135 | OFCI- Reveive Power Distribution Units (PDU) (ABB) (SOW Del Date- 7/12/24) | 2024-10-31 | 2024-10-31
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ136 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ137 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ138 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ139 | OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ140 | OFCI- UPS System w/ Battery (UPS) (Eaton) Delivered | 2025-02-23 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ141 | OFCI- UPS System w/ Battery (UPS) (Eaton) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ142 | OFCI- Utility Pad Mount Switchgear (UPM) Delivered | 2025-02-24 | 2025-02-28
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ143 | OFCI- Utility Pad Mount Switchgear (UPM) Delivered | 2025-03-30 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ144 | OFCI- Utility Pad Mount Switchgear (UPM) Delivered | 2025-05-03 | 2025-05-03
MSFT OFCI ROJ Dates | COLO 3 | ROJ | #747474 | ROJ145 | OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ ROJ | 2025-02-19 | 2025-02-23
MSFT OFCI ROJ Dates | COLO 4 | ROJ | #747474 | ROJ146 | OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ | 2025-03-26 | 2025-03-30
MSFT OFCI ROJ Dates | COLO 5 | ROJ | #747474 | ROJ147 | OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ | 2025-04-29 | 2025-05-03
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-01 | 2025-02-05
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-13 | 2025-02-15
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-15 | 2025-02-18
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-11 | 2025-02-14
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-11 | 2025-02-13
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-13 | 2025-02-15
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-06 | 2025-03-10
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-06 | 2025-03-08
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-08 | 2025-03-11
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-21 | 2025-02-25
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-21 | 2025-02-24
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-02-24 | 2025-02-26
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-08 | 2025-03-12
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-08 | 2025-03-11
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-11 | 2025-03-13
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-17 | 2025-03-20
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-17 | 2025-03-19
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-19 | 2025-03-21
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-09 | 2025-04-14
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-09 | 2025-04-11
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-11 | 2025-04-15
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-28 | 2025-04-01
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-28 | 2025-03-31
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-03-31 | 2025-04-02
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-11 | 2025-04-16
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-11 | 2025-04-15
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-15 | 2025-04-17
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-21 | 2025-04-24
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-21 | 2025-04-23
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-04-23 | 2025-04-25
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-14 | 2025-05-17
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-14 | 2025-05-16
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-16 | 2025-05-19
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-01 | 2025-05-06
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-01 | 2025-05-05
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE1 | Overhead R/I - Electrical | 2025-05-05 | 2025-05-07
Fitout | COLO 3 - CELL 1 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-01 | 2025-02-04
Fitout | COLO 3 - CELL 1 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-15 | 2025-02-17
Fitout | COLO 3 - CELL 2 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-11 | 2025-02-13
Fitout | COLO 3 - CELL 2 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-11 | 2025-02-12
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 3 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-06 | 2025-03-08
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-06 | 2025-03-07
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-08 | 2025-03-10
Fitout | CELL 4 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-21 | 2025-02-24
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-21 | 2025-02-22
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-02-24 | 2025-02-25
Fitout | CELL 1 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-08 | 2025-03-11
Fitout | CELL 1 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-08 | 2025-03-10
Fitout | CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-11 | 2025-03-12
Fitout | CELL 2 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-17 | 2025-03-19
Fitout | CELL 2 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-17 | 2025-03-18
Fitout | CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-19 | 2025-03-20
Fitout | CELL 3 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-09 | 2025-04-11
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-09 | 2025-04-10
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-11 | 2025-04-14
Fitout | CELL 4 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-28 | 2025-03-31
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-28 | 2025-03-29
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-03-31 | 2025-04-01
Fitout | CELL 1 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-11 | 2025-04-15
Fitout | CELL 1 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-11 | 2025-04-14
Fitout | CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-15 | 2025-04-16
Fitout | CELL 2 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-21 | 2025-04-23
Fitout | CELL 2 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-21 | 2025-04-22
Fitout | CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-04-23 | 2025-04-24
Fitout | CELL 3 Data Hall | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-14 | 2025-05-16
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-14 | 2025-05-15
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-16 | 2025-05-17
Fitout | CELL 4 Data Hall Fitout Activities | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-01 | 2025-05-05
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-01 | 2025-05-02
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSC | Overhead R/I - Fire Alarm | 2025-05-05 | 2025-05-06
Fitout | COLO 3 - CELL 1 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-01-29 | 2025-01-31
Fitout | COLO 3 - CELL 1 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-11 | 2025-02-12
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-06 | 2025-02-10
Fitout | COLO 3 - CELL 2 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-07 | 2025-02-10
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-11 | 2025-02-12
Fitout | COLO 3 - CELL 3 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-03 | 2025-03-05
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-04 | 2025-03-05
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-06 | 2025-03-07
Fitout | CELL 4 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-18 | 2025-02-20
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-19 | 2025-02-20
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-02-21 | 2025-02-22
Fitout | CELL 1 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-05 | 2025-03-07
Fitout | CELL 1 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-06 | 2025-03-07
Fitout | CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-08 | 2025-03-10
Fitout | CELL 2 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-13 | 2025-03-15
Fitout | CELL 2 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-14 | 2025-03-15
Fitout | CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-17 | 2025-03-18
Fitout | CELL 3 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-05 | 2025-04-08
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-07 | 2025-04-08
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-09 | 2025-04-10
Fitout | CELL 4 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-25 | 2025-03-27
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-26 | 2025-03-27
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-03-28 | 2025-03-29
Fitout | CELL 1 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-08 | 2025-04-10
Fitout | CELL 1 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-09 | 2025-04-10
Fitout | CELL 1 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-11 | 2025-04-14
Fitout | CELL 2 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-17 | 2025-04-19
Fitout | CELL 2 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-18 | 2025-04-19
Fitout | CELL 2 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-21 | 2025-04-22
Fitout | CELL 3 Data Hall | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-05-10 | 2025-05-13
Fitout | CELL 3 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-05-12 | 2025-05-13
Fitout | CELL 3 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-05-14 | 2025-05-15
Fitout | CELL 4 Data Hall Fitout Activities | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-28 | 2025-04-30
Fitout | CELL 4 Electrical Room | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-04-29 | 2025-04-30
Fitout | CELL 4 Mechanical Gallery | Fire Protection | #D85234 | GSD | Overhead R/I - Fire Protection | 2025-05-01 | 2025-05-02
Fitout | COLO 3 - CELL 1 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-04 | 2025-02-05
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-19 | 2025-02-25
Fitout | COLO 3 - CELL 2 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-13 | 2025-02-14
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-17 | 2025-02-22
Fitout | COLO 3 - CELL 3 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-08 | 2025-03-10
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-12 | 2025-03-18
Fitout | CELL 4 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-24 | 2025-02-25
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-02-27 | 2025-03-06
Fitout | CELL 1 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-11 | 2025-03-12
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-14 | 2025-03-20
Fitout | CELL 2 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-19 | 2025-03-20
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-24 | 2025-03-29
Fitout | CELL 3 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-11 | 2025-04-14
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-16 | 2025-04-22
Fitout | CELL 4 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-03-31 | 2025-04-01
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-03 | 2025-04-09
Fitout | CELL 1 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-15 | 2025-04-16
Fitout | CELL 1 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-18 | 2025-04-24
Fitout | CELL 2 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-23 | 2025-04-24
Fitout | CELL 2 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-04-26 | 2025-05-02
Fitout | CELL 3 Data Hall | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-05-16 | 2025-05-17
Fitout | CELL 3 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-05-20 | 2025-05-27
Fitout | CELL 4 Data Hall Fitout Activities | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-05-05 | 2025-05-06
Fitout | CELL 4 Mechanical Gallery | Framing | #3598FE | J44 | Overhead R/I - Mechanical | 2025-05-08 | 2025-05-14
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-02-26 | 2025-03-05
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-02-24 | 2025-03-03
Fitout | CELL 3 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-03-19 | 2025-03-26
Fitout | CELL 4 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-03-07 | 2025-03-13
Fitout | CELL 1 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-03-21 | 2025-03-28
Fitout | CELL 2 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-03-31 | 2025-04-05
Fitout | CELL 3 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-04-23 | 2025-04-29
Fitout | CELL 4 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-04-10 | 2025-04-17
Fitout | CELL 1 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-04-25 | 2025-05-01
Fitout | CELL 2 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-05-05 | 2025-05-10
Fitout | CELL 3 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-05-28 | 2025-06-03
Fitout | CELL 4 Mechanical Gallery | Plumbing | #2A4D4F | GPA | Overhead R/I - Plumbing | 2025-05-15 | 2025-05-21
Fitout | Electrical Room | Paiting | #D6F2FF | T2 | Paint | 2025-02-01 | 2025-02-03
Fitout | Entry Room 1 | Paiting | #D6F2FF | T2 | Paint | 2025-02-04 | 2025-02-05
Fitout | Entry Room 2 | Paiting | #D6F2FF | T2 | Paint | 2025-02-06 | 2025-02-07
Fitout | FCR (Facilities Control Room) | Paiting | #D6F2FF | T2 | Paint | 2025-02-10 | 2025-02-11
Fitout | Fire Riser Room | Paiting | #D6F2FF | T2 | Paint | 2025-02-14 | 2025-02-15
Fitout | Loading Dock | Paiting | #D6F2FF | T2 | Paint | 2025-02-18 | 2025-02-19
Fitout | Restrooms & Janitor Room | Paiting | #D6F2FF | T2 | Paint | 2025-02-15 | 2025-02-17
Fitout | SER (Security Equipment Room) | Paiting | #D6F2FF | T2 | Paint | 2025-02-10 | 2025-02-11
Fitout | STORAGE (High Value & Secure) Rooms | Paiting | #D6F2FF | T2 | Paint | 2025-03-04 | 2025-03-05
Fitout | COLO 3 - CELL 1 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-05 | 2025-02-07
Fitout | COLO 3 - CELL 1 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-05 | 2025-03-06
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-08 | 2025-03-10
Fitout | COLO 3 - CELL 2 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-14 | 2025-02-17
Fitout | COLO 3 - CELL 2 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-15 | 2025-02-17
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-06 | 2025-03-07
Fitout | COLO 3 - CELL 3 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-10 | 2025-03-12
Fitout | CELL 3 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-11 | 2025-03-12
Fitout | CELL 3 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-29 | 2025-03-31
Fitout | CELL 4 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-25 | 2025-02-27
Fitout | CELL 4 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-02-26 | 2025-02-27
Fitout | CELL 4 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-17 | 2025-03-18
Fitout | CELL 1 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-12 | 2025-03-14
Fitout | CELL 1 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-13 | 2025-03-14
Fitout | CELL 1 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-01 | 2025-04-02
Fitout | CELL 2 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-20 | 2025-03-24
Fitout | CELL 2 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-03-21 | 2025-03-24
Fitout | CELL 2 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-09 | 2025-04-10
Fitout | CELL 3 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-14 | 2025-04-16
Fitout | CELL 3 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-15 | 2025-04-16
Fitout | CELL 3 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-02 | 2025-05-05
Fitout | CELL 4 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-01 | 2025-04-03
Fitout | CELL 4 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-02 | 2025-04-03
Fitout | CELL 4 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-21 | 2025-04-22
Fitout | CELL 1 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-16 | 2025-04-18
Fitout | CELL 1 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-17 | 2025-04-18
Fitout | CELL 1 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-06 | 2025-05-07
Fitout | CELL 2 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-24 | 2025-04-26
Fitout | CELL 2 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-04-25 | 2025-04-26
Fitout | CELL 2 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-14 | 2025-05-15
Fitout | CELL 3 Data Hall | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-17 | 2025-05-20
Fitout | CELL 3 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-19 | 2025-05-20
Fitout | CELL 3 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-06-06 | 2025-06-07
Fitout | CELL 4 Data Hall Fitout Activities | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-06 | 2025-05-08
Fitout | CELL 4 Electrical Room | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-07 | 2025-05-08
Fitout | CELL 4 Mechanical Gallery | Paiting | #D6F2FF | T1 | Paint Dry-Wall | 2025-05-27 | 2025-05-27
Fitout | COLO 3 - CELL 1 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-02-15 | 2025-02-17
Fitout | COLO 3 - CELL 2 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-02-24 | 2025-02-25
Fitout | COLO 3 - CELL 3 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-03-19 | 2025-03-20
Fitout | CELL 4 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-03-07 | 2025-03-08
Fitout | CELL 1 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-03-21 | 2025-03-24
Fitout | CELL 2 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-03-31 | 2025-04-01
Fitout | CELL 3 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-04-23 | 2025-04-24
Fitout | CELL 4 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-04-10 | 2025-04-11
Fitout | CELL 1 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-04-25 | 2025-04-26
Fitout | CELL 2 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-05-05 | 2025-05-06
Fitout | CELL 3 Data Hall | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-05-28 | 2025-05-29
Fitout | CELL 4 Data Hall Fitout Activities | Paiting | #D6F2FF | T3 | Paint Secondary Steel | 2025-05-15 | 2025-05-16
Site Utilities | Overall | Milestone | #000000 | MLPP | Permanent Power (Need by Date) | 2025-05-05 | 2025-05-05
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Phase 1 Security Pre-Testing Complete | 2025-08-30 | 2025-08-30
Milestones | COLO 4 | Milestone | #000000 | ML21 | Phase 1 Security Pre-Testing Complete | 2025-09-30 | 2025-09-30
Milestones | COLO 5 | Milestone | #000000 | ML21 | Phase 1 Security Pre-Testing Complete | 2025-10-31 | 2025-10-31
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Phase 2 Security Pre-Testing Complete | 2025-09-04 | 2025-09-04
Milestones | COLO 4 | Milestone | #000000 | ML21 | Phase 2 Security Pre-Testing Complete | 2025-10-04 | 2025-10-04
Milestones | COLO 5 | Milestone | #000000 | ML21 | Phase 2 Security Pre-Testing Complete | 2025-11-03 | 2025-11-03
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Phase 3 Security Pre-Testing Complete | 2025-09-25 | 2025-09-25
Milestones | COLO 4 | Milestone | #000000 | ML21 | Phase 3 Security Pre-Testing Complete | 2025-10-23 | 2025-10-23
Milestones | COLO 5 | Milestone | #000000 | ML21 | Phase 3 Security Pre-Testing Complete | 2025-11-26 | 2025-11-26
Fitout | Loading Dock | Plumbing | #2A4D4F | GPB | Plumbing | 2025-02-20 | 2025-03-10
Core & Shell | Admin/ COLO 3 | Concrete | #80804A | SOG | Prep / Place SOG | 2024-12-16 | 2024-12-27
Core & Shell | COLO 4 | Concrete | #80804A | SOG | Prep / Place SOG | 2024-12-30 | 2025-01-10
Core & Shell | COLO 5 | Concrete | #80804A | SOG | Prep / Place SOG | 2025-01-14 | 2025-01-25
Early Awards | Milestone | Milestone | #000000 | ML21 | PROCUREMENT- ARL & Subcontractor Awards | 2024-07-16 | 2024-09-27
Early Awards | Milestone | Milestone | #000000 | ML21 | PROCUREMENT- Buyouts & Early Procurement | 2024-07-16 | 2024-09-27
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | PSR (Contract) Executed | 2024-09-30 | 2024-09-30
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | E39 | Pull & Terminate BAS Equipments | 2025-03-25 | 2025-04-02
Fitout | COLO 3 - CELL 2 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-03-21 | 2025-03-31
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-04-15 | 2025-04-23
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-04-02 | 2025-04-10
Fitout | CELL 1 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-04-17 | 2025-04-25
Fitout | CELL 2 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-04-25 | 2025-05-05
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-05-19 | 2025-05-28
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-05-07 | 2025-05-15
Fitout | CELL 1 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-05-21 | 2025-05-30
Fitout | CELL 2 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-05-30 | 2025-06-07
Fitout | CELL 3 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-06-23 | 2025-07-01
Fitout | CELL 4 Mechanical Gallery | BAS | #2F3452 | GBB | Pull & Terminate BAS Equipments | 2025-06-10 | 2025-06-19
Fitout | Electrical Room | Electrical | #F2F09E | EE24 | Pull Branches From Admin | 2025-03-29 | 2025-04-11
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-03-17 | 2025-03-29
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-04-14 | 2025-04-25
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-04-04 | 2025-04-17
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-05-01 | 2025-05-14
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-05-02 | 2025-05-15
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 | 2025-05-30 | 2025-06-11
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-05-10 | 2025-05-22
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-03-07 | 2025-03-19
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-06-24 | 2025-07-08
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-05-28 | 2025-06-09
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-07-11 | 2025-07-23
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE29 | Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 | 2025-06-12 | 2025-06-25
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-03-19 | 2025-04-02
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-03-17 | 2025-03-31
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-04-09 | 2025-04-23
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-03-28 | 2025-04-10
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-04-11 | 2025-04-25
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-04-21 | 2025-05-05
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-14 | 2025-05-28
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-01 | 2025-05-15
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-16 | 2025-05-30
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-05-27 | 2025-06-07
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-06-18 | 2025-07-01
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE42 | Pull Cable to Mechanical Equipments [From Electrical Room] | 2025-06-05 | 2025-06-19
Fitout | Loading Dock | Electrical | #F2F09E | EE43 | Pull Cables | 2025-03-11 | 2025-03-13
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE44 | Pull Copper for BAS VLAN | 2025-03-21 | 2025-04-04
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE45 | Pull Copper for EPMS VLAN | 2025-02-20 | 2025-03-06
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE46 | Pull Copper for Tahuya VLAN | 2025-03-07 | 2025-03-20
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-03-31 | 2025-04-11
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-04-26 | 2025-05-08
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-04-18 | 2025-04-30
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-05-15 | 2025-05-27
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-05-16 | 2025-05-29
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 1 | 2025-06-12 | 2025-06-24
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-05-23 | 2025-06-04
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-04-26 | 2025-05-09
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-07-09 | 2025-07-19
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-06-10 | 2025-06-23
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-07-24 | 2025-08-05
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE47 | Pull Feeders from Electrical Room to PDUs Pull Crew 2 | 2025-06-26 | 2025-07-10
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-03-18 | 2025-03-24
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-03-27 | 2025-04-01
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-04-19 | 2025-04-24
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-04-07 | 2025-04-11
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-04-22 | 2025-04-26
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-04-30 | 2025-05-06
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-05-23 | 2025-05-29
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-05-12 | 2025-05-16
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-05-27 | 2025-05-31
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-06-04 | 2025-06-09
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-06-27 | 2025-07-02
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE17 | Pull Feeders from PDUs to Busways | 2025-06-16 | 2025-06-20
Fitout | Electrical Room | Electrical | #F2F09E | EE29 | Pull Feeders to Admin | 2025-03-12 | 2025-03-28
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE48 | Pull Fiber For BAS VLAN | 2025-03-21 | 2025-04-04
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE49 | Pull Fiber For CEI Network | 2025-04-21 | 2025-05-05
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE50 | Pull Fiber For EPMS VLAN | 2025-02-20 | 2025-03-06
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE51 | Pull Fiber For Tahuya VLAN | 2025-03-07 | 2025-03-20
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE52 | Pull Fiber/Copper For CORPNET Network | 2025-04-05 | 2025-04-19
Fitout | COLO 3 - CELL 2 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-05-13 | 2025-05-23
Fitout | CELL 3 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-06-09 | 2025-06-20
Fitout | CELL 4 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-05-10 | 2025-05-21
Fitout | CELL 1 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-04-17 | 2025-04-28
Fitout | CELL 1 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-05-06 | 2025-05-16
Fitout | CELL 2 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-05-31 | 2025-06-11
Fitout | CELL 3 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-07-22 | 2025-08-02
Fitout | CELL 4 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-06-27 | 2025-07-10
Fitout | CELL 1 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-06-05 | 2025-06-17
Fitout | CELL 2 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-06-28 | 2025-07-11
Fitout | CELL 3 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-08-09 | 2025-08-21
Fitout | CELL 4 Punchlist | Punchlist | #A02B93 | PU1 | Punchlist | 2025-07-15 | 2025-07-25
Fitout | COLO 3 - CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-03-06 | 2025-03-10
Fitout | COLO 3 - CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-03-14 | 2025-03-18
Fitout | COLO 3 - CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-04-07 | 2025-04-10
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-03-26 | 2025-03-29
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-04-09 | 2025-04-14
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-04-18 | 2025-04-22
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-05-12 | 2025-05-15
Fitout | CELL 4 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-04-29 | 2025-05-02
Fitout | CELL 1 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-05-14 | 2025-05-17
Fitout | CELL 2 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-05-22 | 2025-05-27
Fitout | CELL 3 Data Hall | HAC's | #FED8E8 | S2 | Raise HACs | 2025-06-16 | 2025-06-19
Fitout | CELL 4 Data Hall Fitout Activities | HAC's | #FED8E8 | S2 | Raise HACs | 2025-06-03 | 2025-06-06
Milestones | COLO 4 | Milestone | #000000 | ML21 | Ready for Network Install | 2025-09-24 | 2025-09-24
Milestones | COLO 5 | Milestone | #000000 | ML21 | Ready for Network Install | 2025-10-17 | 2025-10-17
Fitout | Admin | Clayco | #C9392A | CL | Remaining Area Punchlist | 2025-03-12 | 2025-03-17
Fitout | Punchlist | Punchlist | #A02B93 | PU1 | Remaining Rooms | 2025-01-27 | 2025-03-17
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- Microsoft Awards CHI11 | 2024-05-06 | 2024-05-10
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- Microsoft Reviews Proposals | 2024-04-15 | 2024-05-02
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- PSR Executed (Early Works) | 2024-06-06 | 2024-06-06
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- PSR Executed (Full GMP) | 2024-09-30 | 2024-09-30
RFP / PSR | Milestone | Milestone | #000000 | ML21 | RFP- RFP Issued (Revised 3.21.24) and Proposal Due to MSFT | 2024-03-25 | 2024-04-12
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | RNI | 2025-08-20 | 2025-08-20
Fitout | Loading Dock | Milestone | #000000 | ML21 | Rough-in | 2025-01-31 | 2025-01-31
Fitout | Electrical Room | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-01-27 | 2025-01-27
Fitout | Entry Room 1 | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-01-29 | 2025-01-29
Fitout | Entry Room 2 | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-01-31 | 2025-01-31
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-02-03 | 2025-02-03
Fitout | Fire Riser Room | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-02-11 | 2025-02-11
Fitout | SER (Security Equipment Room) | Framing | #3598FE | JA | Secondary / Ceiling Steel | 2025-02-05 | 2025-02-05
Milestones | COLO 5 | Milestone | #000000 | ML21 | Secuirty Lockdown | 2025-12-04 | 2025-12-04
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Security Lockdown | 2025-10-02 | 2025-10-02
Milestones | COLO 4 | Milestone | #000000 | ML21 | Security Lockdown | 2025-11-06 | 2025-11-06
Fitout | Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipment in Admin | 2025-03-03 | 2025-03-11
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-10 | 2025-03-15
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-17 | 2025-03-20
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-14 | 2025-03-18
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-03 | 2025-03-06
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-31 | 2025-04-03
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-03-26 | 2025-03-29
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-04-18 | 2025-04-22
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-04-05 | 2025-04-09
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-04-21 | 2025-05-01
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-04-29 | 2025-05-02
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-05-22 | 2025-05-27
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE53 | Set Electrical Equipments | 2025-05-10 | 2025-05-14
Fitout | Entry Room 1 | Electrical | #F2F09E | EE54 | Set ER-1 Equipment | 2025-02-11 | 2025-02-14
Fitout | Entry Room 2 | Electrical | #F2F09E | EE55 | Set ER-2 Equipment | 2025-02-13 | 2025-02-17
Fitout | FCR (Facilities Control Room) | Electrical | #F2F09E | EE56 | Set FCR Equipment | 2025-02-15 | 2025-02-19
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-03-14 | 2025-03-18
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-03-12 | 2025-03-15
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-04-04 | 2025-04-08
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-03-24 | 2025-03-27
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-04-07 | 2025-04-10
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-04-16 | 2025-04-19
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-05-09 | 2025-05-13
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-04-26 | 2025-04-30
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-05-12 | 2025-05-15
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-05-20 | 2025-05-23
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-06-12 | 2025-06-17
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE57 | Set Mechanical Equipments | 2025-05-31 | 2025-06-04
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-02-27 | 2025-03-04
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-03-08 | 2025-03-12
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-04-01 | 2025-04-04
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-03-19 | 2025-03-24
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-04-03 | 2025-04-07
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-04-11 | 2025-04-16
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-05-06 | 2025-05-09
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-04-23 | 2025-04-26
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-05-08 | 2025-05-12
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-05-16 | 2025-05-20
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE7 | Set PDUs | 2025-06-09 | 2025-06-12
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE7 | Set PDUs | 2025-05-28 | 2025-05-31
Fitout | SER (Security Equipment Room) | HAC's | #FED8E8 | S3 | Set SER Room Equipment | 2025-02-15 | 2025-02-19
Site Prep/ Mobilization | Milestone | Milestone | #000000 | ML21 | Set-Up Trailers & Install Temp Utilities | 2024-07-25 | 2024-08-08
Site Prep/ Mobilization | Milestone | Milestone | #000000 | ML21 | Site Mobilization | 2024-07-24 | 2024-07-24
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start First ROJ - CLAYCO Took over Storage 9/2/2024 | 2024-09-05 | 2024-09-05
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start First ROJ CLAYCO Took over Storage 9/2/2024 | 2024-09-05 | 2024-09-05
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start First ROJ CLAYCO Took over Storage 9/2/2024 | 2024-09-05 | 2024-09-05
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start Foundation | 2024-09-19 | 2024-09-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L1 CX | 2025-04-09 | 2025-04-09
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L1 CX | 2025-04-23 | 2025-04-23
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L1 CX | 2025-04-21 | 2025-04-21
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L2 CX (Yellow Tag) | 2025-05-05 | 2025-05-05
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L2 CX (Yellow Tag) | 2025-05-06 | 2025-05-06
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L2 CX (Yellow Tag) | 2025-06-05 | 2025-06-05
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L3 CX | 2025-06-20 | 2025-06-20
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L3 CX | 2025-07-19 | 2025-07-19
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L3 CX (Green Tag) | 2025-06-04 | 2025-06-04
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L4 Cx (Blue Tag) | 2025-08-15 | 2025-08-15
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L4 Cx (Blue Tag) | 2025-09-20 | 2025-09-20
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L4 Cx (Blue Tag) | 2025-10-17 | 2025-10-17
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start L5 Cx (White Tag) | 2025-09-16 | 2025-09-16
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start L5 Cx (White Tag) | 2025-10-17 | 2025-10-17
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start L5 Cx (White Tag) | 2025-11-17 | 2025-11-17
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Start Superstructure | 2024-09-19 | 2024-09-19
Milestones | COLO 4 | Milestone | #000000 | ML21 | Start Superstructure | 2024-11-02 | 2024-11-02
Milestones | COLO 5 | Milestone | #000000 | ML21 | Start Superstructure | 2024-11-14 | 2024-11-14
Commissioning | COLO 3 - CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-03 | 2025-07-18
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-25 | 2025-08-08
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-10 | 2025-07-23
Commissioning | CELL 1 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-16 | 2025-07-30
Commissioning | CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-07-21 | 2025-08-04
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-30 | 2025-09-15
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-12 | 2025-08-26
Commissioning | CELL 1 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-13 | 2025-08-27
Commissioning | CELL 2 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-19 | 2025-09-02
Commissioning | CELL 3 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-09-20 | 2025-10-04
Commissioning | CELL 4 Energizations & Startups (Level 3) | Cx | #8ED973 | Cx3 | Startups | 2025-08-28 | 2025-09-12
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | Substantial Completion | 2025-10-01 | 2025-10-01
Milestones | COLO 4 | Milestone | #000000 | ML21 | Substantial Completion | 2025-10-29 | 2025-10-29
Milestones | COLO 5 | Milestone | #000000 | ML21 | Substantial Completion | 2025-12-02 | 2025-12-02
Milestones | Admin/ COLO 3 | Milestone | #000000 | ML21 | TCO / C of O | 2025-09-30 | 2025-09-30
Milestones | COLO 4 | Milestone | #000000 | ML21 | TCO / C of O | 2025-10-29 | 2025-10-29
Milestones | COLO 5 | Milestone | #000000 | ML21 | TCO / C of O | 2025-12-02 | 2025-12-02
Fitout | Electrical Room | Electrical | #F2F09E | EE58 | Terminate Electrical / Mechanical Equipment | 2025-04-14 | 2025-04-17
Fitout | COLO 3 - CELL 1 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-03-31 | 2025-04-03
Fitout | COLO 3 - CELL 2 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-04-26 | 2025-04-30
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-05-23 | 2025-05-28
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-03-20 | 2025-03-25
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-04-18 | 2025-04-22
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-05-15 | 2025-05-19
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-07-09 | 2025-07-12
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-06-10 | 2025-06-13
Fitout | CELL 1 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-05-16 | 2025-05-20
Fitout | CELL 2 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-06-12 | 2025-06-17
Fitout | CELL 3 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-07-24 | 2025-07-29
Fitout | CELL 4 Electrical Room | Electrical | #F2F09E | EE59 | Terminate Electrical Equipments [Inside Electrical Room] | 2025-06-26 | 2025-06-30
Fitout | COLO 3 - CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-03 | 2025-04-07
Fitout | COLO 3 - CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-01 | 2025-04-04
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-24 | 2025-04-28
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-11 | 2025-04-16
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-04-26 | 2025-04-30
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-05-06 | 2025-05-09
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-05-29 | 2025-06-02
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-05-16 | 2025-05-20
Fitout | CELL 1 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-05-31 | 2025-06-04
Fitout | CELL 2 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-06-09 | 2025-06-12
Fitout | CELL 3 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-07-02 | 2025-07-08
Fitout | CELL 4 Mechanical Gallery | Electrical | #F2F09E | EE60 | Terminate Mechanical Equipments | 2025-06-20 | 2025-06-24
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE61 | Terminate MV Gear - Cell 1 | 2025-05-30 | 2025-06-03
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE61 | Terminate MV Gear - Cell 2 | 2025-06-04 | 2025-06-07
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE61 | Terminate MV Gear - Cell 3 | 2025-06-13 | 2025-06-18
Electrical Yard | COLO 5 | Electrical | #F2F09E | EE61 | Terminate MV Gear - Cell 4 | 2025-06-09 | 2025-06-12
Fitout | COLO 3 - CELL 1 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-04-14 | 2025-04-16
Fitout | COLO 3 - CELL 2 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-05-09 | 2025-05-12
Fitout | COLO 3 - CELL 3 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-06-05 | 2025-06-07
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-05-10 | 2025-05-13
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-05-01 | 2025-05-05
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-05-28 | 2025-05-30
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-07-18 | 2025-07-21
Fitout | CELL 4 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-06-24 | 2025-06-26
Fitout | CELL 1 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-06-02 | 2025-06-04
Fitout | CELL 2 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-06-25 | 2025-06-27
Fitout | CELL 3 Data Hall | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-08-06 | 2025-08-08
Fitout | CELL 4 Data Hall Fitout Activities | Electrical | #F2F09E | EE19 | Terminate PDUs | 2025-07-11 | 2025-07-14
Fitout | Electrical Room | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-01-24 | 2025-01-25
Fitout | Entry Room 1 | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-01-27 | 2025-01-28
Fitout | Entry Room 2 | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-01-29 | 2025-01-30
Fitout | FCR (Facilities Control Room) | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-01-31 | 2025-02-01
Fitout | Fire Riser Room | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-07 | 2025-02-10
Fitout | Loading Dock | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-13 | 2025-02-14
Fitout | Restrooms & Janitor Room | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-11 | 2025-02-12
Fitout | SER (Security Equipment Room) | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-03 | 2025-02-04
Fitout | STORAGE (High Value & Secure) Rooms | Framing | #3598FE | JC | Top Out Drywall - Ceiling Steel Height | 2025-02-05 | 2025-02-06
Core & Shell | Admin/ COLO 3 | Plumbing | #2A4D4F | GPC | UG MEP Work (Plumbing) | 2024-11-14 | 2024-12-14
Core & Shell | COLO 4 | Plumbing | #2A4D4F | GPC | UG MEP Work (Plumbing) | 2024-12-04 | 2024-12-27
Core & Shell | COLO 5 | Plumbing | #2A4D4F | GPC | UG MEP Work (Plumbing) | 2024-12-17 | 2025-01-13
Core & Shell | Admin/ COLO 3 | Plumbing | #2A4D4F | GPD | Weather Days | 2024-12-30 | 2025-01-16
Milestones | COLO 4 | Milestone | #000000 | ML21 | Weather Tight | 2025-01-30 | 2025-01-30
Milestones | Key Milestone | Milestone | #000000 | ML21 | TBD | 2024-03-25 | 2024-09-30

## Sheet2
[7 empty] | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025
[7 empty] | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov
[7 empty] | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15
phase | location | entry | activity_code | color | start | finish | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Milestones | Admin/ COLO 3 | 1 | ML0 | #000000 | 18-Sep-25 | 18-Sep-25 | Sep 05: ML21; Sep 19: ML21; Sep 30: ML21; Oct 11: ML21; Dec 14: ML21; Dec 26: ML21; Dec 27: ML21; Jan 16: ML21; Feb 25: ML21; Mar 05: ML21; Mar 08: ML21; Mar 15: ML21; Apr 09: ML21; May 05: ML21; Jun 04: ML21; Jul 02: ML21; Aug 14: ML21; Aug 15: ML21; Aug 20: ML21; Aug 30: ML21; Sep 04: ML21; Sep 15: ML21; Sep 16: ML21; Sep 18: ML0; Sep 25: ML21; Sep 30: ML21; Oct 01: ML21; Oct 02: ML21
|  | 40 | ML1 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 43 | ML4 | #000000 | 01-Oct-25 | 01-Oct-25
|  | 45 | ML6 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 47 | ML8 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 48 | ML9 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 49 | ML10 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 50 | ML11 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 51 | ML12 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 52 | ML13 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 55 | ML16 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 58 | ML19 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 65 | ML21 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 73 | ML21 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 75 | ML21 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 76 | ML21 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 92 | ML21 | #000000 | 30-Sep-24 | 30-Sep-24
|  | 114 | ML21 | #000000 | 11-Oct-24 | 11-Oct-24
|  | 115 | ML21 | #000000 | 30-Aug-25 | 30-Aug-25
|  | 116 | ML21 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 117 | ML21 | #000000 | 30-Aug-25 | 30-Aug-25
|  | 118 | ML21 | #000000 | 30-Aug-25 | 30-Aug-25
|  | 119 | ML21 | #000000 | 04-Jun-25 | 04-Jun-25
|  | 120 | ML21 | #000000 | 02-Jul-25 | 02-Jul-25
|  | 121 | ML21 | #000000 | 15-Sep-25 | 15-Sep-25
|  | 122 | ML21 | #000000 | 08-Mar-25 | 08-Mar-25
|  | 123 | ML21 | #000000 | 27-Dec-24 | 27-Dec-24
|  | 124 | ML21 | #000000 | 14-Dec-24 | 14-Dec-24
|  | 125 | ML21 | #000000 | 14-Dec-24 | 14-Dec-24
|  | 126 | ML21 | #000000 | 14-Dec-24 | 14-Dec-24
|  | 127 | ML21 | #000000 | 05-May-25 | 05-May-25
|  | 128 | ML21 | #000000 | 16-Jan-25 | 16-Jan-25
|  | 131 | ML21 | #000000 | 26-Dec-24 | 26-Dec-24
|  | 136 | ML21 | #000000 | 19-Sep-24 | 19-Sep-24
|  | 145 | ML21 | #000000 | 19-Nov-25 | 19-Nov-25
|  | 233 | ML21 | #000000 | 05-Mar-25 | 05-Mar-25
|  | 246 | ML21 | #000000 | 02-Oct-25 | 02-Oct-25
|  | 330 | ML21 | #000000 | 25-Feb-25 | 25-Feb-25
|  | 369 | ML21 | #000000 | 15-Mar-25 | 15-Mar-25
|  | 1036 | ML21 | #000000 | 30-Aug-25 | 30-Aug-25
|  | 1039 | ML21 | #000000 | 04-Sep-25 | 04-Sep-25
|  | 1042 | ML21 | #000000 | 25-Sep-25 | 25-Sep-25
|  | 1051 | ML21 | #000000 | 30-Sep-24 | 30-Sep-24
|  | 1156 | ML21 | #000000 | 20-Aug-25 | 20-Aug-25
|  | 1165 | ML21 | #000000 | 02-Oct-25 | 02-Oct-25
|  | 1211 | ML21 | #000000 | 05-Sep-24 | 05-Sep-24
|  | 1213 | ML21 | #000000 | 19-Sep-24 | 19-Sep-24
|  | 1214 | ML21 | #000000 | 09-Apr-25 | 09-Apr-25
|  | 1217 | ML21 | #000000 | 05-May-25 | 05-May-25
|  | 1222 | ML21 | #000000 | 04-Jun-25 | 04-Jun-25
|  | 1223 | ML21 | #000000 | 15-Aug-25 | 15-Aug-25
|  | 1226 | ML21 | #000000 | 16-Sep-25 | 16-Sep-25
|  | 1229 | ML21 | #000000 | 19-Sep-24 | 19-Sep-24
|  | 1243 | ML21 | #000000 | 01-Oct-25 | 01-Oct-25
|  | 1246 | ML21 | #000000 | 30-Sep-25 | 30-Sep-25
| COLO 4 | 41 | ML2 | #000000 | 19-Sep-25 | 19-Sep-25 | Sep 05: ML21; Sep 16: ML21; Oct 31: ML21; Nov 02: ML21; Dec 27: ML21; Dec 31: ML21; Jan 10: ML21; Jan 30: ML21; Mar 30: ML21; Apr 23: ML21; Apr 24: ML21; May 05: ML21; May 06: ML21; Jun 20: ML21; Jul 19: ML21; Aug 14: ML21; Sep 19: ML21; Sep 20: ML21; Sep 24: ML21; Sep 30: ML21; Oct 04: ML21; Oct 16: ML21; Oct 17: ML21; Oct 20: ML21; Oct 23: ML21; Oct 29: ML21; Nov 06: ML21
|  | 44 | ML5 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 53 | ML14 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 57 | ML18 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 64 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 66 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 67 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 68 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 69 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 71 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 74 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 129 | ML21 | #000000 | 30-Sep-25 | 30-Sep-25
|  | 132 | ML21 | #000000 | 30-Sep-25 | 30-Sep-25
|  | 134 | ML21 | #000000 | 30-Sep-25 | 30-Sep-25
|  | 137 | ML21 | #000000 | 31-Oct-24 | 31-Oct-24
|  | 139 | ML21 | #000000 | 19-Jul-25 | 19-Jul-25
|  | 141 | ML21 | #000000 | 14-Aug-25 | 14-Aug-25
|  | 143 | ML21 | #000000 | 16-Oct-25 | 16-Oct-25
|  | 146 | ML21 | #000000 | 30-Mar-25 | 30-Mar-25
|  | 149 | ML21 | #000000 | 10-Jan-25 | 10-Jan-25
|  | 151 | ML21 | #000000 | 31-Dec-24 | 31-Dec-24
|  | 153 | ML21 | #000000 | 27-Dec-24 | 27-Dec-24
|  | 155 | ML21 | #000000 | 05-May-25 | 05-May-25
|  | 181 | ML21 | #000000 | 19-Sep-25 | 19-Sep-25
|  | 182 | ML21 | #000000 | 20-Oct-25 | 20-Oct-25
|  | 247 | ML21 | #000000 | 06-Nov-25 | 06-Nov-25
|  | 305 | ML21 | #000000 | 16-Sep-24 | 16-Sep-24
|  | 367 | ML21 | #000000 | 24-Apr-25 | 24-Apr-25
|  | 1037 | ML21 | #000000 | 30-Sep-25 | 30-Sep-25
|  | 1040 | ML21 | #000000 | 04-Oct-25 | 04-Oct-25
|  | 1043 | ML21 | #000000 | 23-Oct-25 | 23-Oct-25
|  | 1147 | ML21 | #000000 | 24-Sep-25 | 24-Sep-25
|  | 1166 | ML21 | #000000 | 06-Nov-25 | 06-Nov-25
|  | 1212 | ML21 | #000000 | 05-Sep-24 | 05-Sep-24
|  | 1215 | ML21 | #000000 | 23-Apr-25 | 23-Apr-25
|  | 1218 | ML21 | #000000 | 06-May-25 | 06-May-25
|  | 1220 | ML21 | #000000 | 20-Jun-25 | 20-Jun-25
|  | 1224 | ML21 | #000000 | 20-Sep-25 | 20-Sep-25
|  | 1227 | ML21 | #000000 | 17-Oct-25 | 17-Oct-25
|  | 1230 | ML21 | #000000 | 02-Nov-24 | 02-Nov-24
|  | 1244 | ML21 | #000000 | 29-Oct-25 | 29-Oct-25
|  | 1247 | ML21 | #000000 | 29-Oct-25 | 29-Oct-25
|  | 1303 | ML21 | #000000 | 30-Jan-25 | 30-Jan-25
| COLO 5 | 42 | ML3 | #000000 | 11-Oct-25 | 11-Oct-25 | Sep 05: ML21; Sep 09: ML21; Nov 12: ML21; Nov 14: ML21; Jan 13: ML21; Jan 15: ML21; Jan 25: ML21; Feb 14: ML21; Mar 31: ML21; Apr 21: ML21; May 05: ML21; May 31: ML21; Jun 05: ML21; Jul 19: ML21; Aug 05: ML21; Sep 03: ML21; Oct 11: ML21; Oct 17: ML21; Oct 31: ML21; Nov 03: ML21; Nov 15: ML21
|  | 46 | ML7 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 54 | ML15 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 56 | ML17 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 59 | ML20 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 60 | ML21 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 61 | ML21 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 63 | ML21 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 70 | ML21 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 72 | ML21 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 130 | ML21 | #000000 | 31-Oct-25 | 31-Oct-25
|  | 133 | ML21 | #000000 | 31-Oct-25 | 31-Oct-25
|  | 135 | ML21 | #000000 | 31-Oct-25 | 31-Oct-25
|  | 138 | ML21 | #000000 | 12-Nov-24 | 12-Nov-24
|  | 140 | ML21 | #000000 | 05-Aug-25 | 05-Aug-25
|  | 142 | ML21 | #000000 | 03-Sep-25 | 03-Sep-25
|  | 144 | ML21 | #000000 | 15-Nov-25 | 15-Nov-25
|  | 147 | ML21 | #000000 | 31-Mar-25 | 31-Mar-25
|  | 150 | ML21 | #000000 | 25-Jan-25 | 25-Jan-25
|  | 152 | ML21 | #000000 | 15-Jan-25 | 15-Jan-25
|  | 154 | ML21 | #000000 | 13-Jan-25 | 13-Jan-25
|  | 156 | ML21 | #000000 | 05-May-25 | 05-May-25
|  | 183 | ML21 | #000000 | 11-Oct-25 | 11-Oct-25
|  | 184 | ML21 | #000000 | 19-Nov-25 | 19-Nov-25
|  | 234 | ML21 | #000000 | 14-Feb-25 | 14-Feb-25
|  | 248 | ML21 | #000000 | 04-Dec-25 | 04-Dec-25
|  | 306 | ML21 | #000000 | 09-Sep-24 | 09-Sep-24
|  | 368 | ML21 | #000000 | 31-May-25 | 31-May-25
|  | 1038 | ML21 | #000000 | 31-Oct-25 | 31-Oct-25
|  | 1041 | ML21 | #000000 | 03-Nov-25 | 03-Nov-25
|  | 1044 | ML21 | #000000 | 26-Nov-25 | 26-Nov-25
|  | 1148 | ML21 | #000000 | 17-Oct-25 | 17-Oct-25
|  | 1164 | ML21 | #000000 | 04-Dec-25 | 04-Dec-25
|  | 1210 | ML21 | #000000 | 05-Sep-24 | 05-Sep-24
|  | 1216 | ML21 | #000000 | 21-Apr-25 | 21-Apr-25
|  | 1219 | ML21 | #000000 | 05-Jun-25 | 05-Jun-25
|  | 1221 | ML21 | #000000 | 19-Jul-25 | 19-Jul-25
|  | 1225 | ML21 | #000000 | 17-Oct-25 | 17-Oct-25
|  | 1228 | ML21 | #000000 | 17-Nov-25 | 17-Nov-25
|  | 1231 | ML21 | #000000 | 14-Nov-24 | 14-Nov-24
|  | 1245 | ML21 | #000000 | 02-Dec-25 | 02-Dec-25
|  | 1248 | ML21 | #000000 | 02-Dec-25 | 02-Dec-25
| General | 329 | ML21 | #000000 | 16-Sep-24 | 16-Sep-24 | Sep 16: ML21
| Key Milestone | 101 | ML21 | #000000 | 05-Sep-24 | 05-Sep-24 | Aug 21: ML21; Sep 05: ML21; Sep 10: ML21; Nov 12: ML21; Dec 03: ML21; Dec 26: ML21; Dec 31: ML21; Jan 15: ML21; May 05: ML21
|  | 102 | ML21 | #000000 | 22-Jan-26 | 22-Jan-26
|  | 103 | ML21 | #000000 | 19-Nov-25 | 19-Nov-25
|  | 104 | ML21 | #000000 | 21-Aug-24 | 21-Aug-24
|  | 105 | ML21 | #000000 | 05-May-25 | 05-May-25
|  | 106 | ML21 | #000000 | 15-Jan-25 | 15-Jan-25
|  | 107 | ML21 | #000000 | 22-Jan-26 | 22-Jan-26
|  | 108 | ML21 | #000000 | 12-Nov-24 | 12-Nov-24
|  | 109 | ML21 | #000000 | 31-Dec-24 | 31-Dec-24
|  | 110 | ML21 | #000000 | 03-Dec-24 | 03-Dec-24
|  | 111 | ML21 | #000000 | 10-Sep-24 | 10-Sep-24
|  | 112 | ML21 | #000000 | 02-Dec-25 | 02-Dec-25
|  | 113 | ML21 | #000000 | 26-Dec-24 | 26-Dec-24
|  | 1304 | ML21 | #000000 | 25-Mar-24 | 30-Sep-24
| Milestone | 25 | ML1 | #808080 | 01-Oct-25 | 01-Oct-25 | Sep 09: ML21; Sep 10: ML21; Sep 11: ML21; Sep 12: ML21; Sep 13: ML21; Sep 14: ML21; Sep 15: ML21; Sep 16: ML21; Sep 17: ML21; Sep 18: ML21; Sep 19: ML21; Sep 20: ML21; Sep 21: ML21; Sep 22: ML21; Sep 23: ML21; Sep 24: ML21; Sep 25: ML21; Sep 26: ML21; Sep 27: ML21; Sep 28: ML21; Sep 29: ML21; Sep 30: ML21; Oct 01: ML21; Oct 02: ML21; Oct 03: ML21; Oct 04: ML21; Oct 05: ML21; Oct 06: ML21; Oct 07: ML21; Oct 08: ML21; Oct 09: ML21; Oct 10: ML21; Oct 11: ML21; Oct 12: ML21; Oct 13: ML21; Oct 14: ML21; Oct 15: ML21; Oct 16: ML21; Oct 17: ML21; Oct 18: ML21; Oct 19: ML21; Oct 20: ML21; Oct 21: ML21; Oct 22: ML21; Oct 23: ML21; Oct 24: ML21; Oct 25: ML21; Oct 26: ML21; Oct 27: ML21; Oct 28: ML21; Oct 29: ML21; Oct 30: ML21; Oct 31: ML21; Nov 01: ML21; Nov 02: ML21; Oct 01: ML1
|  | 307 | ML21 | #000000 | 10-Oct-24 | 02-Nov-24
|  | 308 | ML21 | #000000 | 09-Sep-24 | 09-Oct-24
BIM | BIM | 77 | BIM | #DAE9F8 | 06-Sep-24 | 12-Oct-24 | Jul 18: BIM; Jul 19: BIM; Jul 20: BIM; Jul 21: BIM; Jul 22: BIM; Jul 23: BIM; Jul 24: BIM; Jul 25: BIM; Jul 26: BIM; Jul 27: BIM; Jul 28: BIM; Jul 29: BIM; Jul 30: BIM; Jul 31: BIM; Aug 01: BIM; Aug 02: BIM; Aug 03: BIM; Aug 04: BIM; Aug 05: BIM; Aug 06: BIM; Aug 07: BIM; Aug 08: BIM; Aug 09: BIM; Aug 10: BIM; Aug 11: BIM; Aug 12: BIM; Aug 13: BIM; Aug 14: BIM; Aug 15: BIM; Aug 16: BIM; Aug 17: BIM; Sep 06: BIM; Sep 07: BIM; Sep 08: BIM; Sep 09: BIM; Sep 10: BIM; Sep 11: BIM; Sep 12: BIM; Sep 13: BIM; Sep 14: BIM; Sep 15: BIM; Sep 16: BIM; Sep 17: BIM; Sep 18: BIM; Sep 19: BIM; Sep 20: BIM; Sep 21: BIM; Sep 22: BIM; Sep 23: BIM; Sep 24: BIM; Sep 25: BIM; Sep 26: BIM; Sep 27: BIM; Sep 28: BIM; Sep 29: BIM; Sep 30: BIM; Oct 01: BIM; Oct 02: BIM; Oct 03: BIM; Oct 04: BIM; Oct 05: BIM; Oct 06: BIM; Oct 07: BIM; Oct 08: BIM; Oct 09: BIM; Oct 10: BIM; Oct 11: BIM; Oct 12: BIM
|  | 78 | BIM | #DAE9F8 | 18-Jul-24 | 18-Jul-24
|  | 79 | BIM | #DAE9F8 | 19-Jul-24 | 17-Aug-24
CFCI Procurement | CFCI | 96 | CFCI | #F7C7AC | 31-Oct-24 | 03-Mar-25 | Aug 21: CFCI; Aug 22: CFCI; Aug 23: CFCI; Aug 24: CFCI; Aug 25: CFCI; Aug 26: CFCI; Aug 27: CFCI; Aug 28: CFCI; Aug 29: CFCI; Aug 30: CFCI; Aug 31: CFCI; Sep 01: CFCI; Sep 02: CFCI; Sep 03: CFCI; Sep 04: CFCI; Sep 05: CFCI; Sep 06: CFCI; Sep 07: CFCI; Sep 08: CFCI; Sep 09: CFCI; Sep 10: CFCI; Sep 11: CFCI; Sep 12: CFCI; Sep 13: CFCI; Sep 14: CFCI; Sep 15: CFCI; Sep 16: CFCI; Sep 17: CFCI; Sep 18: CFCI; Sep 19: CFCI; Sep 20: CFCI; Sep 21: CFCI; Sep 22: CFCI; Sep 23: CFCI; Sep 24: CFCI; Sep 25: CFCI; Sep 26: CFCI; Sep 27: CFCI; Sep 28: CFCI; Sep 29: CFCI; Sep 30: CFCI; Oct 01: CFCI; Oct 02: CFCI; Oct 03: CFCI; Oct 04: CFCI; Oct 05: CFCI; Oct 06: CFCI; Oct 07: CFCI; Oct 08: CFCI; Oct 09: CFCI; Oct 10: CFCI; Oct 11: CFCI; Oct 12: CFCI; Oct 13: CFCI; Oct 14: CFCI; Oct 15: CFCI; Oct 16: CFCI; Oct 17: CFCI; Oct 18: CFCI; Oct 19: CFCI; Oct 20: CFCI; Oct 21: CFCI; Oct 22: CFCI; Oct 23: CFCI; Oct 24: CFCI; Oct 25: CFCI; Oct 26: CFCI; Oct 27: CFCI; Oct 28: CFCI; Oct 29: CFCI; Oct 30: CFCI; Oct 31: CFCI; Nov 01: CFCI; Nov 02: CFCI; Nov 03: CFCI; Nov 04: CFCI; Nov 05: CFCI; Nov 06: CFCI; Nov 07: CFCI; Nov 08: CFCI; Nov 09: CFCI; Nov 10: CFCI; Nov 11: CFCI; Nov 12: CFCI; Nov 13: CFCI; Nov 14: CFCI; Nov 15: CFCI; Nov 16: CFCI; Nov 17: CFCI; Nov 18: CFCI; Nov 19: CFCI; Nov 20: CFCI; Nov 21: CFCI; Nov 22: CFCI; Nov 23: CFCI; Nov 24: CFCI; Nov 25: CFCI; Nov 26: CFCI; Nov 27: CFCI; Nov 28: CFCI; Nov 29: CFCI; Nov 30: CFCI; Dec 01: CFCI; Dec 02: CFCI; Dec 03: CFCI; Dec 04: CFCI; Dec 05: CFCI; Dec 06: CFCI; Dec 07: CFCI; Dec 08: CFCI; Dec 09: CFCI; Dec 10: CFCI; Dec 11: CFCI; Dec 12: CFCI; Dec 13: CFCI; Dec 14: CFCI; Dec 15: CFCI; Dec 16: CFCI; Dec 17: CFCI; Dec 18: CFCI; Dec 19: CFCI; Dec 20: CFCI; Dec 21: CFCI; Dec 22: CFCI; Dec 23: CFCI; Dec 24: CFCI; Dec 25: CFCI; Dec 26: CFCI; Dec 27: CFCI; Dec 28: CFCI; Dec 29: CFCI; Dec 30: CFCI; Dec 31: CFCI; Jan 01: CFCI; Jan 02: CFCI; Jan 03: CFCI; Jan 04: CFCI; Jan 05: CFCI; Jan 06: CFCI; Jan 07: CFCI; Jan 08: CFCI; Jan 09: CFCI; Jan 10: CFCI; Jan 11: CFCI; Jan 12: CFCI; Jan 13: CFCI; Jan 14: CFCI; Jan 15: CFCI; Jan 16: CFCI; Jan 17: CFCI; Jan 18: CFCI; Jan 19: CFCI; Jan 20: CFCI; Jan 21: CFCI; Jan 22: CFCI; Jan 23: CFCI; Jan 24: CFCI; Jan 25: CFCI; Jan 26: CFCI; Jan 27: CFCI; Jan 28: CFCI; Jan 29: CFCI; Jan 30: CFCI; Jan 31: CFCI; Feb 01: CFCI; Feb 02: CFCI; Feb 03: CFCI; Feb 04: CFCI; Feb 05: CFCI; Feb 06: CFCI; Feb 07: CFCI; Feb 08: CFCI; Feb 09: CFCI; Feb 10: CFCI; Feb 11: CFCI; Feb 12: CFCI; Feb 13: CFCI; Feb 14: CFCI; Feb 15: CFCI; Feb 16: CFCI; Feb 17: CFCI; Feb 18: CFCI; Feb 19: CFCI; Feb 20: CFCI; Feb 21: CFCI; Feb 22: CFCI; Feb 23: CFCI; Feb 24: CFCI; Feb 25: CFCI; Feb 26: CFCI; Feb 27: CFCI; Feb 28: CFCI; Mar 01: CFCI; Mar 02: CFCI; Mar 03: CFCI; Mar 04: CFCI; Mar 05: CFCI; Mar 06: CFCI; Mar 07: CFCI; Mar 08: CFCI; Mar 09: CFCI; Mar 10: CFCI; Mar 11: CFCI; Mar 12: CFCI; Mar 13: CFCI; Mar 14: CFCI; Mar 15: CFCI; Mar 16: CFCI; Mar 17: CFCI; Mar 18: CFCI; Mar 19: CFCI; Mar 20: CFCI; Mar 21: CFCI; Mar 22: CFCI; Mar 23: CFCI; Mar 24: CFCI; Mar 25: CFCI; Mar 26: CFCI; Mar 27: CFCI; Mar 28: CFCI; Mar 29: CFCI; Mar 30: CFCI; Mar 31: CFCI; Apr 01: CFCI; Apr 02: CFCI; Apr 03: CFCI; Apr 04: CFCI; Apr 05: CFCI; Apr 06: CFCI; Apr 07: CFCI; Apr 08: CFCI; Apr 09: CFCI; Apr 10: CFCI; Apr 11: CFCI; Apr 12: CFCI; Apr 13: CFCI; Apr 14: CFCI; Apr 15: CFCI; Apr 16: CFCI; Apr 17: CFCI; Apr 18: CFCI; Apr 19: CFCI; Apr 20: CFCI; Apr 21: CFCI; Apr 22: CFCI; Apr 23: CFCI; Apr 24: CFCI; Apr 25: CFCI; Apr 26: CFCI; Apr 27: CFCI; Apr 28: CFCI; Apr 29: CFCI; Apr 30: CFCI; May 01: CFCI; May 02: CFCI; May 03: CFCI; May 04: CFCI; May 05: CFCI; May 06: CFCI; May 07: CFCI; May 08: CFCI; May 09: CFCI; May 10: CFCI; May 11: CFCI; May 12: CFCI; May 13: CFCI; May 14: CFCI; May 15: CFCI; May 16: CFCI; May 17: CFCI; May 18: CFCI; May 19: CFCI; May 20: CFCI; May 21: CFCI; May 22: CFCI; May 23: CFCI; May 24: CFCI; May 25: CFCI; May 26: CFCI; May 27: CFCI; May 28: CFCI; May 29: CFCI; May 30: CFCI; May 31: CFCI; Jun 01: CFCI; Jun 02: CFCI; Jun 03: CFCI; Jun 04: CFCI; Jun 05: CFCI; Jun 06: CFCI; Jun 07: CFCI; Jun 08: CFCI; Jun 09: CFCI; Jun 10: CFCI; Jun 11: CFCI; Jun 12: CFCI; Jun 13: CFCI; Jun 14: CFCI; Jun 15: CFCI; Jun 16: CFCI; Jun 17: CFCI; Jun 18: CFCI; Jun 19: CFCI; Jun 20: CFCI; Jun 21: CFCI; Jun 22: CFCI; Jun 23: CFCI; Jun 24: CFCI; Jun 25: CFCI
|  | 97 | CFCI | #F7C7AC | 31-Oct-24 | 05-Dec-24
|  | 98 | CFCI | #F7C7AC | 22-Aug-24 | 29-Apr-25
|  | 99 | CFCI | #F7C7AC | 21-Aug-24 | 30-Nov-25
|  | 100 | CFCI | #F7C7AC | 21-Aug-24 | 25-Jun-25
Commissioning | CELL 1 Energizations & Startups (Level 3) | 173 | EE33 | #F2F09E | 20-Jun-25 | 28-Jun-25 | Jun 20: EE33; Jun 21: EE33; Jun 22: EE33; Jun 23: EE33; Jun 24: EE33; Jun 25: EE33; Jun 26: EE33; Jun 27: EE33; Jun 28: EE33; Jun 30: EE34; Jul 01: EE34; Jul 02: EE34; Jul 03: EE34; Jul 04: EE34; Jul 05: EE34; Jul 06: EE34; Jul 07: EE34; Jul 08: EE34; Jul 09: EE34; Jul 10: EE34; Jul 11: Cx1; Jul 12: Cx1; Jul 13: Cx1; Jul 14: Cx1; Jul 15: Cx1; Jul 16: Cx3; Jul 17: Cx3; Jul 18: Cx3; Jul 19: Cx3; Jul 20: Cx3; Jul 21: Cx3; Jul 22: Cx3; Jul 23: Cx3; Jul 24: Cx3; Jul 25: Cx3; Jul 26: Cx3; Jul 27: Cx3; Jul 28: Cx3; Jul 29: Cx3; Jul 30: Cx3; Jul 31: E39; Aug 01: E39; Aug 02: E39; Aug 03: E39; Aug 04: E39; Aug 05: EE34; Aug 06: EE34; Aug 07: EE34; Aug 08: Cx1; Aug 09: Cx1; Aug 10: Cx1; Aug 11: Cx1; Aug 12: Cx1; Aug 13: Cx3; Aug 14: Cx3; Aug 15: Cx3; Aug 16: Cx3; Aug 17: Cx3; Aug 18: Cx3; Aug 19: Cx3; Aug 20: Cx3; Aug 21: Cx3; Aug 22: Cx3; Aug 23: Cx3; Aug 24: Cx3; Aug 25: Cx3; Aug 26: Cx3; Aug 27: Cx3; Aug 28: E39; Aug 29: E39; Aug 30: E39; Aug 31: E39; Sep 01: E39; Sep 02: E39
|  | 177 | EE33 | #F2F09E | 19-Jul-25 | 29-Jul-25
|  | 238 | EE34 | #F2F09E | 30-Jun-25 | 10-Jul-25
|  | 242 | EE34 | #F2F09E | 30-Jul-25 | 07-Aug-25
|  | 321 | Cx1 | #8ED973 | 11-Jul-25 | 15-Jul-25
|  | 325 | Cx1 | #8ED973 | 08-Aug-25 | 12-Aug-25
|  | 658 | E39 | #F2F09E | 31-Jul-25 | 04-Aug-25
|  | 662 | E39 | #F2F09E | 28-Aug-25 | 02-Sep-25
|  | 1235 | Cx3 | #8ED973 | 16-Jul-25 | 30-Jul-25
|  | 1239 | Cx3 | #8ED973 | 13-Aug-25 | 27-Aug-25
| CELL 2 Energizations & Startups (Level 3) | 174 | EE33 | #F2F09E | 25-Jun-25 | 03-Jul-25 | Jun 25: EE33; Jun 26: EE33; Jun 27: EE33; Jun 28: EE33; Jun 29: EE33; Jun 30: EE33; Jul 01: EE33; Jul 02: EE33; Jul 03: EE33; Jul 07: EE34; Jul 08: EE34; Jul 09: EE34; Jul 10: EE34; Jul 11: EE34; Jul 12: EE34; Jul 13: EE34; Jul 14: EE34; Jul 15: EE34; Jul 16: Cx1; Jul 17: Cx1; Jul 18: Cx1; Jul 19: Cx1; Jul 21: Cx3; Jul 22: Cx3; Jul 23: Cx3; Jul 24: Cx3; Jul 25: Cx3; Jul 26: Cx3; Jul 27: Cx3; Jul 28: Cx3; Jul 29: Cx3; Jul 30: Cx3; Jul 31: Cx3; Aug 01: Cx3; Aug 02: Cx3; Aug 03: Cx3; Aug 04: Cx3; Aug 05: E39; Aug 06: E39; Aug 07: E39; Aug 08: E39; Aug 09: EE34; Aug 10: EE34; Aug 11: EE34; Aug 12: EE34; Aug 13: Cx1; Aug 14: Cx1; Aug 15: Cx1; Aug 16: Cx1; Aug 17: Cx1; Aug 18: Cx1; Aug 19: Cx3; Aug 20: Cx3; Aug 21: Cx3; Aug 22: Cx3; Aug 23: Cx3; Aug 24: Cx3; Aug 25: Cx3; Aug 26: Cx3; Aug 27: Cx3; Aug 28: Cx3; Aug 29: Cx3; Aug 30: Cx3; Aug 31: Cx3; Sep 01: Cx3; Sep 02: Cx3; Sep 03: E39; Sep 04: E39; Sep 05: E39; Sep 06: E39; Sep 07: E39; Sep 08: E39
|  | 178 | EE33 | #F2F09E | 24-Jul-25 | 02-Aug-25
|  | 239 | EE34 | #F2F09E | 07-Jul-25 | 15-Jul-25
|  | 243 | EE34 | #F2F09E | 04-Aug-25 | 12-Aug-25
|  | 322 | Cx1 | #8ED973 | 16-Jul-25 | 19-Jul-25
|  | 326 | Cx1 | #8ED973 | 13-Aug-25 | 18-Aug-25
|  | 659 | E39 | #F2F09E | 05-Aug-25 | 08-Aug-25
|  | 663 | E39 | #F2F09E | 03-Sep-25 | 08-Sep-25
|  | 1236 | Cx3 | #8ED973 | 21-Jul-25 | 04-Aug-25
|  | 1240 | Cx3 | #8ED973 | 19-Aug-25 | 02-Sep-25
| CELL 3 Energizations & Startups (Level 3) | 171 | EE33 | #F2F09E | 24-Jun-25 | 07-Jul-25 | Jun 24: EE33; Jun 25: EE33; Jun 26: EE33; Jun 27: EE33; Jun 28: EE33; Jun 29: EE33; Jun 30: EE33; Jul 01: EE33; Jul 02: EE33; Jul 03: EE33; Jul 04: EE33; Jul 05: EE33; Jul 06: EE33; Jul 07: EE33; Jul 08: EE34; Jul 09: EE34; Jul 10: EE34; Jul 11: EE34; Jul 12: EE34; Jul 13: EE34; Jul 14: EE34; Jul 15: EE34; Jul 16: EE34; Jul 17: EE34; Jul 18: EE34; Jul 19: Cx1; Jul 20: Cx1; Jul 21: Cx1; Jul 22: Cx1; Jul 23: Cx1; Jul 24: Cx1; Jul 25: Cx3; Jul 26: Cx3; Jul 27: Cx3; Jul 28: Cx3; Jul 29: Cx3; Jul 30: Cx3; Jul 31: Cx3; Aug 01: Cx3; Aug 02: Cx3; Aug 03: Cx3; Aug 04: Cx3; Aug 05: Cx3; Aug 06: Cx3; Aug 07: Cx3; Aug 08: Cx3; Aug 09: E39; Aug 10: E39; Aug 11: E39; Aug 12: E39; Aug 13: E39; Aug 14: E39; Aug 15: EE34; Aug 16: EE34; Aug 17: EE34; Aug 18: EE34; Aug 19: EE34; Aug 20: EE34; Aug 21: EE34; Aug 22: EE34; Aug 23: EE34; Aug 24: EE34; Aug 25: EE34; Aug 26: Cx1; Aug 27: Cx1; Aug 28: Cx1; Aug 29: Cx1; Aug 30: Cx3; Aug 31: Cx3; Sep 01: Cx3; Sep 02: Cx3; Sep 03: Cx3; Sep 04: Cx3; Sep 05: Cx3; Sep 06: Cx3; Sep 07: Cx3; Sep 08: Cx3; Sep 09: Cx3; Sep 10: Cx3; Sep 11: Cx3; Sep 12: Cx3; Sep 13: Cx3; Sep 14: Cx3; Sep 15: Cx3; Sep 16: E39; Sep 17: E39; Sep 18: E39; Sep 19: E39; Sep 20: Cx3; Sep 21: Cx3; Sep 22: Cx3; Sep 23: Cx3; Sep 24: Cx3; Sep 25: Cx3; Sep 26: Cx3; Sep 27: Cx3; Sep 28: Cx3; Sep 29: Cx3; Sep 30: Cx3; Oct 01: Cx3; Oct 02: Cx3; Oct 03: Cx3; Oct 04: Cx3; Oct 06: E39; Oct 07: E39; Oct 08: E39; Oct 09: E39; Oct 10: E39; Oct 11: E39
|  | 175 | EE33 | #F2F09E | 06-Aug-25 | 14-Aug-25
|  | 179 | EE33 | #F2F09E | 25-Aug-25 | 03-Sep-25
|  | 236 | EE34 | #F2F09E | 08-Jul-25 | 18-Jul-25
|  | 240 | EE34 | #F2F09E | 15-Aug-25 | 25-Aug-25
|  | 244 | EE34 | #F2F09E | 04-Sep-25 | 13-Sep-25
|  | 319 | Cx1 | #8ED973 | 19-Jul-25 | 24-Jul-25
|  | 323 | Cx1 | #8ED973 | 26-Aug-25 | 29-Aug-25
|  | 327 | Cx1 | #8ED973 | 15-Sep-25 | 19-Sep-25
|  | 656 | E39 | #F2F09E | 09-Aug-25 | 14-Aug-25
|  | 660 | E39 | #F2F09E | 16-Sep-25 | 19-Sep-25
|  | 664 | E39 | #F2F09E | 06-Oct-25 | 11-Oct-25
|  | 1233 | Cx3 | #8ED973 | 25-Jul-25 | 08-Aug-25
|  | 1237 | Cx3 | #8ED973 | 30-Aug-25 | 15-Sep-25
|  | 1241 | Cx3 | #8ED973 | 20-Sep-25 | 04-Oct-25
| CELL 4 Energizations & Startups (Level 3) | 172 | EE33 | #F2F09E | 13-Jun-25 | 23-Jun-25 | Jun 13: EE33; Jun 14: EE33; Jun 15: EE33; Jun 16: EE33; Jun 17: EE33; Jun 18: EE33; Jun 19: EE33; Jun 20: EE33; Jun 21: EE33; Jun 22: EE33; Jun 23: EE33; Jun 24: EE34; Jun 25: EE34; Jun 26: EE34; Jun 27: EE34; Jun 28: EE34; Jun 29: EE34; Jun 30: EE34; Jul 01: EE34; Jul 02: EE34; Jul 03: Cx1; Jul 04: Cx1; Jul 05: Cx1; Jul 06: Cx1; Jul 07: Cx1; Jul 08: Cx1; Jul 09: Cx1; Jul 10: Cx3; Jul 11: Cx3; Jul 12: Cx3; Jul 13: Cx3; Jul 14: Cx3; Jul 15: Cx3; Jul 16: Cx3; Jul 17: Cx3; Jul 18: Cx3; Jul 19: Cx3; Jul 20: Cx3; Jul 21: Cx3; Jul 22: Cx3; Jul 23: Cx3; Jul 24: E39; Jul 25: E39; Jul 26: E39; Jul 27: E39; Jul 28: E39; Jul 29: E39; Jul 30: EE34; Jul 31: EE34; Aug 01: EE34; Aug 02: EE34; Aug 03: EE34; Aug 04: EE34; Aug 05: EE34; Aug 06: EE34; Aug 07: Cx1; Aug 08: Cx1; Aug 09: Cx1; Aug 10: Cx1; Aug 11: Cx1; Aug 12: Cx3; Aug 13: Cx3; Aug 14: Cx3; Aug 15: Cx3; Aug 16: Cx3; Aug 17: Cx3; Aug 18: Cx3; Aug 19: Cx3; Aug 20: Cx3; Aug 21: Cx3; Aug 22: Cx3; Aug 23: Cx3; Aug 24: Cx3; Aug 25: Cx3; Aug 26: Cx3; Aug 27: E39; Aug 28: Cx3; Aug 29: Cx3; Aug 30: Cx3; Aug 31: Cx3; Sep 01: Cx3; Sep 02: Cx3; Sep 03: Cx3; Sep 04: Cx3; Sep 05: Cx3; Sep 06: Cx3; Sep 07: Cx3; Sep 08: Cx3; Sep 09: Cx3; Sep 10: Cx3; Sep 11: Cx3; Sep 12: Cx3; Sep 13: E39; Sep 14: E39; Sep 15: E39; Sep 16: E39; Sep 17: E39
|  | 176 | EE33 | #F2F09E | 18-Jul-25 | 28-Jul-25
|  | 180 | EE33 | #F2F09E | 04-Aug-25 | 12-Aug-25
|  | 237 | EE34 | #F2F09E | 24-Jun-25 | 02-Jul-25
|  | 241 | EE34 | #F2F09E | 29-Jul-25 | 06-Aug-25
|  | 245 | EE34 | #F2F09E | 13-Aug-25 | 22-Aug-25
|  | 320 | Cx1 | #8ED973 | 03-Jul-25 | 09-Jul-25
|  | 324 | Cx1 | #8ED973 | 07-Aug-25 | 11-Aug-25
|  | 328 | Cx1 | #8ED973 | 23-Aug-25 | 27-Aug-25
|  | 657 | E39 | #F2F09E | 24-Jul-25 | 29-Jul-25
|  | 661 | E39 | #F2F09E | 27-Aug-25 | 30-Aug-25
|  | 665 | E39 | #F2F09E | 13-Sep-25 | 17-Sep-25
|  | 1234 | Cx3 | #8ED973 | 10-Jul-25 | 23-Jul-25
|  | 1238 | Cx3 | #8ED973 | 12-Aug-25 | 26-Aug-25
|  | 1242 | Cx3 | #8ED973 | 28-Aug-25 | 12-Sep-25
| COLO 3 | 2 | L2 | #196B24 | 05-May-25 | 28-May-25 | May 05: L2; May 06: L2; May 07: L2; May 08: L2; May 09: L2; May 10: L2; May 11: L2; May 12: L2; May 13: L2; May 14: L2; May 15: L2; May 16: L2; May 17: L2; May 18: L2; May 19: L2; May 20: L2; May 21: L2; May 22: L2; May 23: L2; May 24: L2; May 25: L2; May 26: L2; May 27: L2; May 28: L2; May 29: L2; May 30: L2; May 31: L2; Jun 01: L2; Jun 02: L2; Jun 03: L2; Jun 04: L2; Jun 05: L2; Jun 06: L2; Jun 07: L2; Jun 08: L2; Jun 09: L2; Jun 10: L2; Jun 11: L2; Jun 12: L3; Jun 13: L3; Jun 14: L3; Jun 15: L3; Jun 16: L3; Jun 17: L3; Jun 18: L3; Jun 19: L3; Jun 20: L3; Jun 21: L3; Jun 22: L3; Jun 23: L3; Jun 24: L3; Jun 25: L3; Jun 26: L3; Jun 27: L3; Jun 28: L3; Jun 29: L3; Jun 30: L3; Jul 01: L3; Jul 02: L3; Jul 03: L3; Jul 04: L3; Jul 05: L3; Jul 06: L3; Jul 07: L3; Jul 08: L3; Jul 09: L3; Jul 10: L3; Jul 11: L3; Jul 12: L3; Jul 13: L3; Jul 14: L3; Jul 15: L3; Jul 16: L3; Jul 17: L3; Jul 18: L3; Aug 15: 4&5; Aug 16: 4&5; Aug 17: 4&5; Aug 18: 4&5; Aug 19: 4&5; Aug 20: 4&5; Aug 21: 4&5; Aug 22: 4&5; Aug 23: 4&5; Aug 24: 4&5; Aug 25: 4&5; Aug 26: 4&5; Aug 27: 4&5; Aug 28: 4&5; Aug 29: 4&5; Aug 30: 4&5; Aug 31: 4&5; Sep 01: 4&5; Sep 02: 4&5; Sep 03: 4&5; Sep 04: 4&5; Sep 05: 4&5; Sep 06: 4&5; Sep 07: 4&5; Sep 08: 4&5; Sep 09: 4&5; Sep 10: 4&5; Sep 11: 4&5; Sep 12: 4&5; Sep 13: 4&5; Sep 14: 4&5; Sep 15: 4&5; Sep 16: 4&5; Sep 17: 4&5; Sep 18: 4&5
|  | 3 | L2 | #196B24 | 15-May-25 | 07-Jun-25
|  | 4 | L2 | #196B24 | 09-Jun-25 | 02-Jul-25
|  | 5 | L2 | #196B24 | 27-May-25 | 18-Jun-25
|  | 14 | L3 | #196B24 | 13-Jun-25 | 23-Jun-25
|  | 15 | L3 | #196B24 | 24-Jun-25 | 27-Jun-25
|  | 16 | L3 | #196B24 | 12-Jun-25 | 18-Jun-25
|  | 17 | L3 | #196B24 | 15-Jul-25 | 18-Jul-25
|  | 18 | L3 | #196B24 | 28-Jun-25 | 14-Jul-25
|  | 19 | 4&5 | #196B24 | 15-Aug-25 | 15-Sep-25
|  | 22 | 4&5 | #196B24 | 16-Sep-25 | 18-Sep-25
| COLO 3 - CELL 1 Energizations & Startups (Level 3) | 169 | EE33 | #F2F09E | 04-Jun-25 | 12-Jun-25 | Jun 04: EE33; Jun 05: EE33; Jun 06: EE33; Jun 07: EE33; Jun 08: EE33; Jun 09: EE33; Jun 10: EE33; Jun 11: EE33; Jun 12: EE33
| COLO 3 - CELL 2 Energizations & Startups (Level 3) | 170 | EE33 | #F2F09E | 09-Jun-25 | 18-Jun-25 | Jun 09: EE33; Jun 10: EE33; Jun 11: EE33; Jun 12: EE33; Jun 13: EE33; Jun 14: EE33; Jun 15: EE33; Jun 16: EE33; Jun 17: EE33; Jun 18: EE33; Jun 19: EE34; Jun 20: EE34; Jun 21: EE34; Jun 22: EE34; Jun 23: EE34; Jun 24: EE34; Jun 25: EE34; Jun 26: EE34; Jun 27: EE34; Jun 28: Cx1; Jun 29: Cx1; Jun 30: Cx1; Jul 01: Cx1; Jul 02: Cx1; Jul 03: Cx3; Jul 04: Cx3; Jul 05: Cx3; Jul 06: Cx3; Jul 07: Cx3; Jul 08: Cx3; Jul 09: Cx3; Jul 10: Cx3; Jul 11: Cx3; Jul 12: Cx3; Jul 13: Cx3; Jul 14: Cx3; Jul 15: Cx3; Jul 16: Cx3; Jul 17: Cx3; Jul 18: Cx3; Jul 19: E39; Jul 20: E39; Jul 21: E39; Jul 22: E39; Jul 23: E39
|  | 235 | EE34 | #F2F09E | 19-Jun-25 | 27-Jun-25
|  | 318 | Cx1 | #8ED973 | 28-Jun-25 | 02-Jul-25
|  | 655 | E39 | #F2F09E | 19-Jul-25 | 23-Jul-25
|  | 1232 | Cx3 | #8ED973 | 03-Jul-25 | 18-Jul-25
| COLO 4 | 6 | L2 | #196B24 | 06-May-25 | 29-May-25 | May 06: L2; May 07: L2; May 08: L2; May 09: L2; May 10: L2; May 11: L2; May 12: L2; May 13: L2; May 14: L2; May 15: L2; May 16: L2; May 17: L2; May 18: L2; May 19: L2; May 20: L2; May 21: L2; May 22: L2; May 23: L2; May 24: L2; May 25: L2; May 26: L2; May 27: L2; May 28: L2; May 29: L2; May 31: L2; Jun 01: L2; Jun 02: L2; Jun 03: L2; Jun 04: L2; Jun 05: L2; Jun 06: L2; Jun 07: L2; Jun 08: L2; Jun 09: L2; Jun 10: L2; Jun 11: L2; Jun 12: L2; Jun 13: L2; Jun 14: L2; Jun 15: L2; Jun 16: L2; Jun 17: L2; Jun 18: L2; Jun 19: L2; Jun 20: L2; Jun 21: L2; Jun 22: L2; Jun 23: L2; Jun 24: L2; Jun 27: L2; Jun 28: L2; Jun 29: L2; Jun 30: L2; Jul 01: L2; Jul 02: L2; Jul 03: L2; Jul 04: L2; Jul 05: L2; Jul 06: L2; Jul 07: L2; Jul 08: L2; Jul 09: L2; Jul 10: L2; Jul 11: L2; Jul 12: L2; Jul 13: L2; Jul 14: L2; Jul 15: L2; Jul 16: L2; Jul 17: L2; Jul 18: L2; Jul 19: L2; Jul 20: L2; Jul 21: L2; Jul 22: L2; Jul 23: L2; Jul 24: L2; Jul 25: L2; Jul 26: L2; Jul 27: L2; Jul 28: L2; Jul 29: L2; Jul 30: L2; Jul 31: L2; Aug 01: L2; Aug 02: L2; Aug 03: L2; Aug 04: L2; Aug 05: L2; Aug 06: L2; Aug 07: L2; Aug 08: L2; Aug 09: L2; Aug 10: L2; Aug 11: L2; Aug 12: L2; Aug 13: L2; Aug 14: L2; Sep 20: 4&5; Sep 21: 4&5; Sep 22: 4&5; Sep 23: 4&5; Sep 24: 4&5; Sep 25: 4&5; Sep 26: 4&5; Sep 27: 4&5; Sep 28: 4&5; Sep 29: 4&5; Sep 30: 4&5; Oct 01: 4&5; Oct 02: 4&5; Oct 03: 4&5; Oct 04: 4&5; Oct 05: 4&5; Oct 06: 4&5; Oct 07: 4&5; Oct 08: 4&5; Oct 09: 4&5; Oct 10: 4&5; Oct 11: 4&5; Oct 12: 4&5; Oct 13: 4&5; Oct 14: 4&5; Oct 15: 4&5; Oct 16: 4&5; Oct 17: 4&5; Oct 18: 4&5; Oct 19: 4&5; Oct 20: 4&5
|  | 7 | L2 | #196B24 | 31-May-25 | 24-Jun-25
|  | 8 | L2 | #196B24 | 22-Jul-25 | 14-Aug-25
|  | 9 | L2 | #196B24 | 27-Jun-25 | 22-Jul-25
|  | 20 | 4&5 | #196B24 | 20-Sep-25 | 16-Oct-25
|  | 23 | 4&5 | #196B24 | 17-Oct-25 | 20-Oct-25
| COLO 5 | 10 | L2 | #196B24 | 05-Jun-25 | 28-Jun-25 | Jun 05: L2; Jun 06: L2; Jun 07: L2; Jun 08: L2; Jun 09: L2; Jun 10: L2; Jun 11: L2; Jun 12: L2; Jun 13: L2; Jun 14: L2; Jun 15: L2; Jun 16: L2; Jun 17: L2; Jun 18: L2; Jun 19: L2; Jun 20: L2; Jun 21: L2; Jun 22: L2; Jun 23: L2; Jun 24: L2; Jun 25: L2; Jun 26: L2; Jun 27: L2; Jun 28: L2; Jun 29: L2; Jun 30: L2; Jul 01: L2; Jul 02: L2; Jul 03: L2; Jul 04: L2; Jul 05: L2; Jul 06: L2; Jul 07: L2; Jul 08: L2; Jul 09: L2; Jul 10: L2; Jul 11: L2; Jul 12: L2; Jul 13: L2; Jul 14: L2; Jul 15: L2; Jul 16: L2; Jul 17: L2; Jul 18: L2; Jul 19: L2; Jul 20: L2; Jul 21: L2; Jul 22: L2; Jul 23: L2; Jul 24: L2; Jul 25: L2; Jul 26: L2; Jul 27: L2; Jul 28: L2; Jul 29: L2; Jul 30: L2; Jul 31: L2; Aug 01: L2; Aug 02: L2; Aug 03: L2; Aug 04: L2; Aug 05: L2; Aug 06: L2; Aug 07: L2; Aug 09: L2; Aug 10: L2; Aug 11: L2; Aug 12: L2; Aug 13: L2; Aug 14: L2; Aug 15: L2; Aug 16: L2; Aug 17: L2; Aug 18: L2; Aug 19: L2; Aug 20: L2; Aug 21: L2; Aug 22: L2; Aug 23: L2; Aug 24: L2; Aug 25: L2; Aug 26: L2; Aug 27: L2; Aug 28: L2; Aug 29: L2; Aug 30: L2; Aug 31: L2; Sep 01: L2; Sep 02: L2; Sep 03: L2; Oct 17: 4&5; Oct 18: 4&5; Oct 19: 4&5; Oct 20: 4&5; Oct 21: 4&5; Oct 22: 4&5; Oct 23: 4&5; Oct 24: 4&5; Oct 25: 4&5; Oct 26: 4&5; Oct 27: 4&5; Oct 28: 4&5; Oct 29: 4&5; Oct 30: 4&5; Oct 31: 4&5; Nov 01: 4&5; Nov 02: 4&5; Nov 03: 4&5; Nov 04: 4&5; Nov 05: 4&5; Nov 06: 4&5; Nov 07: 4&5; Nov 08: 4&5; Nov 09: 4&5; Nov 10: 4&5; Nov 11: 4&5; Nov 12: 4&5; Nov 13: 4&5; Nov 14: 4&5; Nov 15: 4&5
|  | 11 | L2 | #196B24 | 28-Jun-25 | 23-Jul-25
|  | 12 | L2 | #196B24 | 09-Aug-25 | 03-Sep-25
|  | 13 | L2 | #196B24 | 15-Jul-25 | 07-Aug-25
|  | 21 | 4&5 | #196B24 | 17-Oct-25 | 15-Nov-25
|  | 24 | 4&5 | #196B24 | 17-Nov-25 | 19-Nov-25
Core & Shell | Admin/ COLO 3 | 534 | J32 | #3598FE | 30-Nov-24 | 14-Dec-24 | Oct 21: J38; Oct 22: J38; Oct 23: J38; Oct 24: J38; Oct 25: J38; Oct 26: J38; Oct 27: J38; Oct 28: J38; Oct 29: J38; Oct 30: J38; Oct 31: J38; Nov 01: J38; Nov 02: J38; Nov 03: J38; Nov 04: J38; Nov 05: J38; Nov 06: J38; Nov 07: J38; Nov 08: J40; Nov 09: J40; Nov 10: J40; Nov 11: J40; Nov 12: J40; Nov 13: J40; Nov 14: GPC; Nov 15: GPC; Nov 16: GPC; Nov 17: GPC; Nov 18: GPC; Nov 19: GPC; Nov 20: GPC; Nov 21: GPC; Nov 22: GPC; Nov 23: GPC; Nov 24: GPC; Nov 25: GPC; Nov 26: GPC; Nov 27: GPC; Nov 28: GPC; Nov 29: GPC; Nov 30: GPC; Dec 01: GPC; Dec 02: GPC; Dec 03: GPC; Dec 04: GPC; Dec 05: GPC; Dec 06: GPC; Dec 07: GPC; Dec 08: GPC; Dec 09: GPC; Dec 10: GPC; Dec 11: GPC; Dec 12: GPC; Dec 13: GPC; Dec 14: GPC; Dec 16: SOG; Dec 17: SOG; Dec 18: SOG; Dec 19: SOG; Dec 20: SOG; Dec 21: SOG; Dec 22: SOG; Dec 23: SOG; Dec 24: SOG; Dec 25: SOG; Dec 26: SOG; Dec 27: SOG; Dec 28: J34; Dec 29: J34; Dec 30: GPD; Dec 31: GPD; Jan 01: GPD; Jan 02: GPD; Jan 03: GPD; Jan 04: GPD; Jan 05: GPD; Jan 06: GPD; Jan 07: GPD; Jan 08: GPD; Jan 09: GPD; Jan 10: GPD; Jan 11: GPD; Jan 12: GPD; Jan 13: GPD; Jan 14: GPD; Jan 15: GPD; Jan 16: GPD; Jan 17: J35
|  | 575 | J34 | #3598FE | 16-Dec-24 | 06-Jan-25
|  | 578 | J35 | #3598FE | 30-Dec-24 | 17-Jan-25
|  | 594 | J38 | #3598FE | 21-Oct-24 | 07-Nov-24
|  | 601 | J40 | #3598FE | 08-Nov-24 | 29-Nov-24
|  | 1046 | SOG | #80804A | 16-Dec-24 | 27-Dec-24
|  | 1299 | GPC | #2A4D4F | 14-Nov-24 | 14-Dec-24
|  | 1302 | GPD | #2A4D4F | 30-Dec-24 | 16-Jan-25
| COLO 4 | 535 | J32 | #3598FE | 16-Dec-24 | 31-Dec-24 | Nov 02: J38; Nov 03: J38; Nov 04: J38; Nov 05: J38; Nov 06: J38; Nov 07: J38; Nov 08: J38; Nov 09: J38; Nov 10: J38; Nov 11: J38; Nov 12: J38; Nov 13: J38; Nov 14: J38; Nov 15: J38; Nov 16: J38; Nov 17: J38; Nov 18: J38; Nov 19: J38; Nov 20: J38; Nov 21: J40; Nov 22: J40; Nov 23: J40; Nov 24: J40; Nov 25: J40; Nov 26: J40; Nov 27: J40; Nov 28: J40; Nov 29: J40; Nov 30: J40; Dec 01: J40; Dec 02: J40; Dec 03: J40; Dec 04: GPC; Dec 05: GPC; Dec 06: GPC; Dec 07: GPC; Dec 08: GPC; Dec 09: GPC; Dec 10: GPC; Dec 11: GPC; Dec 12: GPC; Dec 13: GPC; Dec 14: GPC; Dec 15: GPC; Dec 16: GPC; Dec 17: GPC; Dec 18: GPC; Dec 19: GPC; Dec 20: GPC; Dec 21: GPC; Dec 22: GPC; Dec 23: GPC; Dec 24: GPC; Dec 25: GPC; Dec 26: GPC; Dec 27: GPC; Dec 28: J32; Dec 29: J32; Dec 30: SOG; Dec 31: SOG; Jan 01: SOG; Jan 02: SOG; Jan 03: SOG; Jan 04: SOG; Jan 05: SOG; Jan 06: SOG; Jan 07: SOG; Jan 08: SOG; Jan 09: SOG; Jan 10: SOG; Jan 11: J35; Jan 12: J35; Jan 13: J35; Jan 14: J35; Jan 15: J35; Jan 16: J35; Jan 17: J35; Jan 18: J35; Jan 19: J35; Jan 20: J35; Jan 21: J35; Jan 22: J35; Jan 23: J35; Jan 24: J35; Jan 25: J35; Jan 26: J35; Jan 27: J35; Jan 28: J35; Jan 29: J35; Jan 30: J35
|  | 576 | J34 | #3598FE | 07-Jan-25 | 25-Jan-25
|  | 579 | J35 | #3598FE | 11-Jan-25 | 30-Jan-25
|  | 595 | J38 | #3598FE | 02-Nov-24 | 20-Nov-24
|  | 602 | J40 | #3598FE | 21-Nov-24 | 14-Dec-24
|  | 1047 | SOG | #80804A | 30-Dec-24 | 10-Jan-25
|  | 1300 | GPC | #2A4D4F | 04-Dec-24 | 27-Dec-24
| COLO 5 | 536 | J32 | #3598FE | 02-Jan-25 | 15-Jan-25 | Nov 14: J38; Nov 15: J38; Nov 16: J38; Nov 17: J38; Nov 18: J38; Nov 19: J38; Nov 20: J38; Nov 21: J38; Nov 22: J38; Nov 23: J38; Nov 24: J38; Nov 25: J38; Nov 26: J38; Nov 27: J38; Nov 28: J38; Nov 29: J38; Nov 30: J38; Dec 01: J38; Dec 02: J38; Dec 03: J38; Dec 04: J40; Dec 05: J40; Dec 06: J40; Dec 07: J40; Dec 08: J40; Dec 09: J40; Dec 10: J40; Dec 11: J40; Dec 12: J40; Dec 13: J40; Dec 14: J40; Dec 15: J40; Dec 16: J40; Dec 17: GPC; Dec 18: GPC; Dec 19: GPC; Dec 20: GPC; Dec 21: GPC; Dec 22: GPC; Dec 23: GPC; Dec 24: GPC; Dec 25: GPC; Dec 26: GPC; Dec 27: GPC; Dec 28: GPC; Dec 29: GPC; Dec 30: GPC; Dec 31: GPC; Jan 01: GPC; Jan 02: GPC; Jan 03: GPC; Jan 04: GPC; Jan 05: GPC; Jan 06: GPC; Jan 07: GPC; Jan 08: GPC; Jan 09: GPC; Jan 10: GPC; Jan 11: GPC; Jan 12: GPC; Jan 13: GPC; Jan 14: SOG; Jan 15: SOG; Jan 16: SOG; Jan 17: SOG; Jan 18: SOG; Jan 19: SOG; Jan 20: SOG; Jan 21: SOG; Jan 22: SOG; Jan 23: SOG; Jan 24: SOG; Jan 25: SOG; Jan 27: J35; Jan 28: J35; Jan 29: J35; Jan 30: J35; Jan 31: J35; Feb 01: J35; Feb 02: J35; Feb 03: J35; Feb 04: J35; Feb 05: J35; Feb 06: J35; Feb 07: J35; Feb 08: J35; Feb 09: J35; Feb 10: J35; Feb 11: J35; Feb 12: J35; Feb 13: J35; Feb 14: J35
|  | 577 | J34 | #3598FE | 27-Jan-25 | 14-Feb-25
|  | 580 | J35 | #3598FE | 27-Jan-25 | 14-Feb-25
|  | 596 | J38 | #3598FE | 14-Nov-24 | 03-Dec-24
|  | 603 | J40 | #3598FE | 04-Dec-24 | 31-Dec-24
|  | 1048 | SOG | #80804A | 14-Jan-25 | 25-Jan-25
|  | 1301 | GPC | #2A4D4F | 17-Dec-24 | 13-Jan-25
Early Awards | Milestone | 1049 | ML21 | #000000 | 16-Jul-24 | 27-Sep-24 | Jul 16: ML21; Jul 17: ML21; Jul 18: ML21; Jul 19: ML21; Jul 20: ML21; Jul 21: ML21; Jul 22: ML21; Jul 23: ML21; Jul 24: ML21; Jul 25: ML21; Jul 26: ML21; Jul 27: ML21; Jul 28: ML21; Jul 29: ML21; Jul 30: ML21; Jul 31: ML21; Aug 01: ML21; Aug 02: ML21; Aug 03: ML21; Aug 04: ML21; Aug 05: ML21; Aug 06: ML21; Aug 07: ML21; Aug 08: ML21; Aug 09: ML21; Aug 10: ML21; Aug 11: ML21; Aug 12: ML21; Aug 13: ML21; Aug 14: ML21; Aug 15: ML21; Aug 16: ML21; Aug 17: ML21; Aug 18: ML21; Aug 19: ML21; Aug 20: ML21; Aug 21: ML21; Aug 22: ML21; Aug 23: ML21; Aug 24: ML21; Aug 25: ML21; Aug 26: ML21; Aug 27: ML21; Aug 28: ML21; Aug 29: ML21; Aug 30: ML21; Aug 31: ML21; Sep 01: ML21; Sep 02: ML21; Sep 03: ML21; Sep 04: ML21; Sep 05: ML21; Sep 06: ML21; Sep 07: ML21; Sep 08: ML21; Sep 09: ML21; Sep 10: ML21; Sep 11: ML21; Sep 12: ML21; Sep 13: ML21; Sep 14: ML21; Sep 15: ML21; Sep 16: ML21; Sep 17: ML21; Sep 18: ML21; Sep 19: ML21; Sep 20: ML21; Sep 21: ML21; Sep 22: ML21; Sep 23: ML21; Sep 24: ML21; Sep 25: ML21; Sep 26: ML21; Sep 27: ML21
|  | 1050 | ML21 | #000000 | 16-Jul-24 | 27-Sep-24
Electrical Yard | Admin/ COLO 3 | 80 | EE30 | #F2F09E | 20-Feb-25 | 03-Mar-25 | Jan 17: EE31; Jan 18: EE31; Jan 19: EE31; Jan 20: EE31; Jan 21: EE31; Jan 22: EE31; Jan 23: EE31; Jan 24: EE31; Jan 25: EE31; Jan 26: EE31; Jan 27: EE31; Jan 28: EE31; Jan 29: EE31; Jan 30: EE31; Jan 31: EE31; Feb 01: EE31; Feb 02: EE31; Feb 03: EE31; Feb 04: EE31; Feb 05: EE31; Feb 06: EE31; Feb 07: EE31; Feb 10: EE31; Feb 11: EE31; Feb 12: EE31; Feb 13: EE31; Feb 14: EE31; Feb 15: EE31; Feb 16: EE31; Feb 17: EE31; Feb 18: EE31; Feb 19: EE31; Feb 20: EE30; Feb 21: EE30; Feb 22: EE30; Feb 23: EE30; Feb 24: EE30; Feb 25: EE30; Feb 26: EE30; Feb 27: EE30; Feb 28: EE30; Mar 01: EE30; Mar 02: EE30; Mar 03: EE30; Mar 04: E39; Mar 05: E39; Mar 06: E39; Mar 07: E39; Mar 08: E39; Mar 09: E39; Mar 10: E39; Mar 11: E39; Mar 12: E39; Mar 13: E39; Mar 14: E39; Mar 15: E39; Apr 25: E35; Apr 26: E35; Apr 27: E35; Apr 28: E35; Apr 29: E35; Apr 30: E35; May 01: E35; May 02: E35; May 03: E35; May 04: E35; May 05: E35; May 06: E35; May 07: E35; May 08: E35; May 09: E35; May 10: E35; May 11: E35; May 12: E35; May 13: E35; May 14: E35; May 15: E35; May 16: E35; May 17: E35; May 18: E35; May 19: E35; May 20: E35; May 21: E35; May 22: E35; May 23: E35; May 27: E35; May 28: E35; May 29: E35; May 30: E35; May 31: E35; Jun 01: E35; Jun 02: E35; Jun 03: E35
|  | 83 | EE31 | #F2F09E | 10-Feb-25 | 19-Feb-25
|  | 86 | EE31 | #F2F09E | 29-Jan-25 | 07-Feb-25
|  | 89 | EE31 | #F2F09E | 17-Jan-25 | 28-Jan-25
|  | 572 | E34 | #F2F09E | 04-Mar-25 | 15-Mar-25
|  | 632 | E28 | #F2F09E | 04-Mar-25 | 15-Mar-25
|  | 635 | E30 | #F2F09E | 04-Mar-25 | 15-Mar-25
|  | 639 | E39 | #F2F09E | 04-Mar-25 | 15-Mar-25
|  | 675 | E35 | #F2F09E | 25-Apr-25 | 05-May-25
|  | 677 | E35 | #F2F09E | 06-May-25 | 14-May-25
|  | 679 | E35 | #F2F09E | 27-May-25 | 03-Jun-25
|  | 681 | E35 | #F2F09E | 15-May-25 | 23-May-25
| COLO 4 | 81 | EE30 | #F2F09E | 27-Mar-25 | 05-Apr-25 | Feb 21: EE31; Feb 22: EE31; Feb 23: EE31; Feb 24: EE31; Feb 25: EE31; Feb 26: EE31; Feb 27: EE31; Feb 28: EE31; Mar 01: EE31; Mar 02: EE31; Mar 03: EE31; Mar 04: EE31; Mar 05: EE31; Mar 06: EE31; Mar 07: EE31; Mar 08: EE31; Mar 09: EE31; Mar 10: EE31; Mar 11: EE31; Mar 12: EE31; Mar 13: EE31; Mar 14: EE31; Mar 15: EE31; Mar 16: EE31; Mar 17: EE31; Mar 18: EE31; Mar 19: EE31; Mar 20: EE31; Mar 21: EE31; Mar 22: EE31; Mar 23: EE31; Mar 24: EE31; Mar 25: EE31; Mar 26: EE31; Mar 27: EE30; Mar 28: EE30; Mar 29: EE30; Mar 30: EE30; Mar 31: EE30; Apr 01: EE30; Apr 02: E39; Apr 03: E39; Apr 04: E39; Apr 05: E39; Apr 06: E39; Apr 07: E39; Apr 08: E39; Apr 09: E39; Apr 10: E39; Apr 11: E39; Apr 12: E39; Apr 13: E39; Apr 14: E39; Apr 15: E39; Apr 16: E34; Apr 17: E34; Apr 18: E34; Apr 19: E34; Apr 20: E34; Apr 21: E34; Apr 22: E34; Apr 23: E34; Apr 24: E34; Apr 25: E35; Apr 26: E35; Apr 27: E35; Apr 28: E35; Apr 29: E35; Apr 30: E35; May 01: E35; May 02: E35; May 03: E35; May 04: E35; May 05: E35; May 06: E35; May 07: E35; May 08: E35; May 09: E35; May 10: E35; May 11: E35; May 12: E35; May 13: E35; May 14: E35; May 15: E35; May 16: E35; May 17: E35; May 18: E35; May 19: E35; May 20: E35; May 21: E35; May 22: E35; May 23: E35; May 27: E35; May 28: E35; May 29: E35; May 30: E35; May 31: E35; Jun 01: E35; Jun 02: E35; Jun 03: E35; Jun 04: E35
|  | 84 | EE31 | #F2F09E | 15-Mar-25 | 26-Mar-25
|  | 87 | EE31 | #F2F09E | 05-Mar-25 | 14-Mar-25
|  | 90 | EE31 | #F2F09E | 21-Feb-25 | 04-Mar-25
|  | 573 | E34 | #F2F09E | 11-Apr-25 | 24-Apr-25
|  | 633 | E28 | #F2F09E | 02-Apr-25 | 15-Apr-25
|  | 636 | E30 | #F2F09E | 02-Apr-25 | 15-Apr-25
|  | 640 | E39 | #F2F09E | 02-Apr-25 | 15-Apr-25
|  | 676 | E35 | #F2F09E | 25-Apr-25 | 05-May-25
|  | 678 | E35 | #F2F09E | 06-May-25 | 14-May-25
|  | 680 | E35 | #F2F09E | 27-May-25 | 04-Jun-25
|  | 682 | E35 | #F2F09E | 15-May-25 | 23-May-25
| COLO 5 | 62 | EE29 | #F2F09E | 20-Jan-25 | 09-May-25 | Jan 20: EE29; Jan 21: EE29; Jan 22: EE29; Jan 23: EE29; Jan 24: EE29; Jan 25: EE29; Jan 26: EE29; Jan 27: EE29; Jan 28: EE29; Jan 29: EE29; Jan 30: EE29; Jan 31: EE29; Feb 01: EE29; Feb 02: EE29; Feb 03: EE29; Feb 04: EE29; Feb 05: EE29; Feb 06: EE29; Feb 07: EE29; Feb 08: EE29; Feb 09: EE29; Feb 10: EE29; Feb 11: EE29; Feb 12: EE29; Feb 13: EE29; Feb 14: EE29; Feb 15: EE29; Feb 16: EE29; Feb 17: EE29; Feb 18: EE29; Feb 19: EE29; Feb 20: EE29; Feb 21: EE29; Feb 22: EE29; Feb 23: EE29; Feb 24: EE29; Feb 25: EE29; Feb 26: EE29; Feb 27: EE29; Feb 28: EE29; Mar 01: EE29; Mar 02: EE29; Mar 03: EE29; Mar 04: EE29; Mar 05: EE29; Mar 06: EE29; Mar 07: EE29; Mar 08: EE29; Mar 09: EE29; Mar 10: EE29; Mar 11: EE29; Mar 12: EE29; Mar 13: EE29; Mar 14: EE29; Mar 15: EE29; Mar 16: EE29; Mar 17: EE29; Mar 18: EE29; Mar 19: EE29; Mar 20: EE29; Mar 21: EE29; Mar 22: EE29; Mar 23: EE29; Mar 24: EE29; Mar 25: EE29; Mar 26: EE29; Mar 27: EE29; Mar 28: EE31; Mar 29: EE31; Mar 30: EE31; Mar 31: EE31; Apr 01: EE31; Apr 02: EE31; Apr 03: EE31; Apr 04: EE31; Apr 05: EE31; Apr 06: EE31; Apr 07: EE31; Apr 08: EE31; Apr 09: EE31; Apr 10: EE31; Apr 11: EE31; Apr 12: EE31; Apr 13: EE31; Apr 14: EE31; Apr 15: EE31; Apr 16: EE31; Apr 17: EE31; Apr 18: EE31; Apr 19: EE31; Apr 20: EE31; Apr 21: EE31; Apr 22: EE31; Apr 23: EE31; Apr 24: EE31; Apr 25: EE31; Apr 26: EE31; Apr 27: EE31; Apr 28: EE31; Apr 29: EE31; Apr 30: EE30; May 01: EE30; May 02: E35; May 03: E35; May 04: E35; May 05: E35; May 06: E35; May 07: E35; May 08: E35; May 09: E35; May 10: E35; May 11: E35; May 12: E35; May 13: E35; May 14: E35; May 15: E35; May 16: E35; May 17: E35; May 18: E35; May 19: E35; May 20: E35; May 21: E35; May 22: E35; May 23: E35; May 24: E35; May 25: E35; May 26: E35; May 27: E35; May 28: E35; May 29: E35; May 30: EE61; May 31: EE61; Jun 01: EE61; Jun 02: EE61; Jun 03: EE61; Jun 04: EE61; Jun 05: EE61; Jun 06: EE61; Jun 07: EE61; Jun 08: E35; Jun 09: EE61; Jun 10: EE61; Jun 11: EE61; Jun 12: EE61; Jun 13: EE61; Jun 14: EE61; Jun 15: EE61; Jun 16: EE61; Jun 17: EE61; Jun 18: EE61
|  | 82 | EE30 | #F2F09E | 30-Apr-25 | 10-May-25
|  | 85 | EE31 | #F2F09E | 19-Apr-25 | 29-Apr-25
|  | 88 | EE31 | #F2F09E | 08-Apr-25 | 18-Apr-25
|  | 91 | EE31 | #F2F09E | 28-Mar-25 | 07-Apr-25
|  | 574 | E34 | #F2F09E | 19-May-25 | 31-May-25
|  | 634 | E28 | #F2F09E | 16-May-25 | 29-May-25
|  | 637 | E30 | #F2F09E | 14-May-25 | 27-May-25
|  | 641 | E39 | #F2F09E | 12-May-25 | 23-May-25
|  | 683 | E35 | #F2F09E | 02-May-25 | 12-May-25
|  | 684 | E35 | #F2F09E | 13-May-25 | 21-May-25
|  | 685 | E35 | #F2F09E | 02-Jun-25 | 10-Jun-25
|  | 686 | E35 | #F2F09E | 22-May-25 | 31-May-25
|  | 1274 | EE61 | #F2F09E | 30-May-25 | 03-Jun-25
|  | 1275 | EE61 | #F2F09E | 04-Jun-25 | 07-Jun-25
|  | 1276 | EE61 | #F2F09E | 13-Jun-25 | 18-Jun-25
|  | 1277 | EE61 | #F2F09E | 09-Jun-25 | 12-Jun-25
Fitout | Admin | 492 | J24 | #3598FE | 22-Feb-25 | 26-Feb-25 | Feb 22: J24; Feb 23: J24; Feb 24: J24; Feb 25: J24; Feb 26: J24; Feb 27: EEA; Feb 28: EEA; Mar 01: EEA; Mar 02: EEA; Mar 03: EEA; Mar 04: EEA; Mar 05: EEA; Mar 06: EEA; Mar 07: EEA; Mar 08: EEA; Mar 09: EEA; Mar 10: EEA; Mar 11: EEA; Mar 12: CL; Mar 13: CL; Mar 14: CL; Mar 15: CL; Mar 16: CL; Mar 17: CL
|  | 654 | EEA | #F2F09E | 27-Feb-25 | 11-Mar-25
|  | 1149 | CL | #C9392A | 12-Mar-25 | 17-Mar-25
| CELL 1 Data Hall | 30 | S1 | #FED8E8 | 29-Mar-25 | 03-Apr-25 | Feb 24: J1; Feb 25: J3; Feb 26: J3; Feb 27: J3; Feb 28: EE2; Mar 01: EE2; Mar 02: EE2; Mar 03: EE2; Mar 04: EE2; Mar 05: GSD; Mar 06: GSD; Mar 07: GSD; Mar 08: GSC; Mar 09: GSC; Mar 10: GSC; Mar 11: J44; Mar 12: T1; Mar 13: T1; Mar 14: T1; Mar 15: J6; Mar 16: J6; Mar 17: J6; Mar 18: J6; Mar 19: J42; Mar 20: J42; Mar 21: T3; Mar 22: T3; Mar 23: T3; Mar 24: T3; Mar 25: J16; Mar 26: J16; Mar 27: J16; Mar 28: J16; Mar 29: J37; Mar 30: J37; Mar 31: J1; Apr 01: J37; Apr 02: J37; Apr 03: EE7; Apr 04: EE7; Apr 05: EE7; Apr 06: EE7; Apr 07: EE7; Apr 08: GSD; Apr 09: S2; Apr 10: S2; Apr 11: S2; Apr 12: S2; Apr 13: S2; Apr 14: S2; Apr 15: J44; Apr 16: T1; Apr 17: T1; Apr 18: T1; Apr 19: J6; Apr 20: J6; Apr 21: J6; Apr 22: EE17; Apr 23: EE17; Apr 24: EE17; Apr 25: EE17; Apr 26: EE17; Apr 28: J16; Apr 29: J16; Apr 30: J16; May 01: EE19; May 02: EE19; May 03: EE19; May 04: EE19; May 05: EE19; May 06: J37; May 07: J37; May 08: EE7; May 09: EE7; May 10: EE7; May 11: EE7; May 12: EE7; May 13: J33; May 14: S2; May 15: S2; May 16: S2; May 17: S2; May 19: S2; May 20: S2; May 21: S2; May 22: J21; May 23: J21; May 27: EE17; May 28: EE17; May 29: EE17; May 30: EE17; May 31: EE17; Jun 02: EE19; Jun 03: EE19; Jun 04: EE19
|  | 34 | S1 | #FED8E8 | 02-May-25 | 08-May-25
|  | 161 | EE32 | #F2F09E | 15-Apr-25 | 17-Apr-25
|  | 165 | EE32 | #F2F09E | 19-May-25 | 21-May-25
|  | 189 | S2 | #FED8E8 | 15-Apr-25 | 18-Apr-25
|  | 193 | S2 | #FED8E8 | 19-May-25 | 22-May-25
|  | 209 | J5 | #3598FE | 11-Mar-25 | 12-Mar-25
|  | 221 | J5 | #3598FE | 15-Apr-25 | 16-Apr-25
|  | 262 | J5 | #3598FE | 08-Mar-25 | 11-Mar-25
|  | 274 | J5 | #3598FE | 11-Apr-25 | 15-Apr-25
|  | 343 | Cx2 | #8ED973 | 25-Mar-25 | 25-Mar-25
|  | 355 | Cx2 | #8ED973 | 28-Apr-25 | 28-Apr-25
|  | 370 | J3 | #3598FE | 25-Feb-25 | 27-Feb-25
|  | 379 | EE2 | #F2F09E | 28-Feb-25 | 04-Mar-25
|  | 387 | EE2 | #F2F09E | 04-Apr-25 | 07-Apr-25
|  | 411 | EE10 | #F2F09E | 01-Apr-25 | 05-Apr-25
|  | 415 | EE10 | #F2F09E | 06-May-25 | 10-May-25
|  | 447 | J16 | #3598FE | 25-Mar-25 | 28-Mar-25
|  | 451 | J16 | #3598FE | 28-Apr-25 | 01-May-25
|  | 471 | J21 | #3598FE | 18-Apr-25 | 21-Apr-25
|  | 475 | J21 | #3598FE | 22-May-25 | 23-May-25
|  | 484 | J23 | #3598FE | 03-Apr-25 | 04-Apr-25
|  | 488 | J23 | #3598FE | 08-May-25 | 09-May-25
|  | 498 | J4 | #3598FE | 05-Mar-25 | 07-Mar-25
|  | 502 | J4 | #3598FE | 08-Apr-25 | 10-Apr-25
|  | 541 | J33 | #3598FE | 03-Apr-25 | 08-Apr-25
|  | 545 | J33 | #3598FE | 08-May-25 | 13-May-25
|  | 564 | J3 | #3598FE | 01-Apr-25 | 03-Apr-25
|  | 586 | J37 | #3598FE | 29-Mar-25 | 02-Apr-25
|  | 590 | J37 | #3598FE | 02-May-25 | 07-May-25
|  | 609 | J6 | #3598FE | 15-Mar-25 | 18-Mar-25
|  | 613 | J6 | #3598FE | 19-Apr-25 | 22-Apr-25
|  | 621 | J42 | #3598FE | 19-Mar-25 | 20-Mar-25
|  | 625 | J42 | #3598FE | 23-Apr-25 | 24-Apr-25
|  | 646 | J1 | #3598FE | 24-Feb-25 | 24-Feb-25
|  | 650 | J1 | #3598FE | 31-Mar-25 | 31-Mar-25
|  | 846 | EE1 | #F2F09E | 08-Mar-25 | 12-Mar-25
|  | 858 | EE1 | #F2F09E | 11-Apr-25 | 16-Apr-25
|  | 882 | GSC | #D85234 | 08-Mar-25 | 11-Mar-25
|  | 894 | GSC | #D85234 | 11-Apr-25 | 15-Apr-25
|  | 918 | GSD | #D85234 | 05-Mar-25 | 07-Mar-25
|  | 930 | GSD | #D85234 | 08-Apr-25 | 10-Apr-25
|  | 950 | J44 | #3598FE | 11-Mar-25 | 12-Mar-25
|  | 958 | J44 | #3598FE | 15-Apr-25 | 16-Apr-25
|  | 999 | T1 | #D6F2FF | 12-Mar-25 | 14-Mar-25
|  | 1011 | T1 | #D6F2FF | 16-Apr-25 | 18-Apr-25
|  | 1027 | T3 | #D6F2FF | 21-Mar-25 | 24-Mar-25
|  | 1031 | T3 | #D6F2FF | 25-Apr-25 | 26-Apr-25
|  | 1109 | EE17 | #F2F09E | 22-Apr-25 | 26-Apr-25
|  | 1113 | EE17 | #F2F09E | 27-May-25 | 31-May-25
|  | 1139 | S2 | #FED8E8 | 09-Apr-25 | 14-Apr-25
|  | 1143 | S2 | #FED8E8 | 14-May-25 | 17-May-25
|  | 1199 | EE7 | #F2F09E | 03-Apr-25 | 07-Apr-25
|  | 1203 | EE7 | #F2F09E | 08-May-25 | 12-May-25
|  | 1282 | EE19 | #F2F09E | 01-May-25 | 05-May-25
|  | 1286 | EE19 | #F2F09E | 02-Jun-25 | 04-Jun-25
| CELL 1 Electrical Room | 210 | J5 | #3598FE | 11-Mar-25 | 11-Mar-25 | Feb 28: J3; Mar 01: J3; Mar 02: J3; Mar 03: J3; Mar 04: EE2; Mar 05: EE2; Mar 06: GSD; Mar 07: GSD; Mar 08: GSC; Mar 09: GSC; Mar 10: GSC; Mar 11: EE1; Mar 12: EE35; Mar 13: T1; Mar 14: T1; Mar 15: Cx2; Mar 31: EE53; Apr 01: EE53; Apr 02: EE53; Apr 03: EE53; Apr 04: EE29; Apr 05: EE29; Apr 06: EE29; Apr 07: EE29; Apr 08: EE29; Apr 09: EE29; Apr 10: EE29; Apr 11: EE29; Apr 12: EE29; Apr 13: EE29; Apr 14: EE29; Apr 15: EE29; Apr 16: EE29; Apr 17: EE29; Apr 18: EE59; Apr 19: EE59; Apr 20: EE59; Apr 21: EE59; Apr 22: EE59; Apr 23: EE53; Apr 24: EE53; Apr 25: EE53; Apr 26: EE53; Apr 27: EE53; Apr 28: EE53; Apr 29: EE53; Apr 30: EE53; May 01: EE53; May 02: EE29; May 03: EE29; May 04: EE29; May 05: EE29; May 06: EE29; May 07: EE29; May 08: EE29; May 09: EE29; May 10: EE29; May 11: EE29; May 12: EE29; May 13: EE29; May 14: EE29; May 15: EE29; May 16: EE59; May 17: EE59; May 18: EE59; May 19: EE59; May 20: EE59; May 21: EE47; May 22: EE47; May 23: EE47; May 24: EE47; May 25: EE47; May 26: EE47; May 27: EE47; May 28: EE47; May 29: EE47
|  | 222 | J5 | #3598FE | 15-Apr-25 | 15-Apr-25
|  | 263 | J5 | #3598FE | 11-Mar-25 | 12-Mar-25
|  | 275 | J5 | #3598FE | 15-Apr-25 | 16-Apr-25
|  | 344 | Cx2 | #8ED973 | 15-Mar-25 | 15-Mar-25
|  | 356 | Cx2 | #8ED973 | 19-Apr-25 | 19-Apr-25
|  | 380 | EE2 | #F2F09E | 04-Mar-25 | 05-Mar-25
|  | 388 | EE2 | #F2F09E | 07-Apr-25 | 08-Apr-25
|  | 427 | EE35 | #F2F09E | 12-Mar-25 | 13-Mar-25
|  | 435 | EE35 | #F2F09E | 16-Apr-25 | 17-Apr-25
|  | 510 | J4 | #3598FE | 06-Mar-25 | 10-Mar-25
|  | 514 | J4 | #3598FE | 09-Apr-25 | 14-Apr-25
|  | 557 | J3 | #3598FE | 28-Feb-25 | 03-Mar-25
|  | 565 | J3 | #3598FE | 04-Apr-25 | 05-Apr-25
|  | 847 | EE1 | #F2F09E | 08-Mar-25 | 11-Mar-25
|  | 859 | EE1 | #F2F09E | 11-Apr-25 | 15-Apr-25
|  | 883 | GSC | #D85234 | 08-Mar-25 | 10-Mar-25
|  | 895 | GSC | #D85234 | 11-Apr-25 | 14-Apr-25
|  | 919 | GSD | #D85234 | 06-Mar-25 | 07-Mar-25
|  | 931 | GSD | #D85234 | 09-Apr-25 | 10-Apr-25
|  | 1000 | T1 | #D6F2FF | 13-Mar-25 | 14-Mar-25
|  | 1012 | T1 | #D6F2FF | 17-Apr-25 | 18-Apr-25
|  | 1067 | EE29 | #F2F09E | 04-Apr-25 | 17-Apr-25
|  | 1069 | EE29 | #F2F09E | 02-May-25 | 15-May-25
|  | 1095 | EE47 | #F2F09E | 18-Apr-25 | 30-Apr-25
|  | 1097 | EE47 | #F2F09E | 16-May-25 | 29-May-25
|  | 1172 | EE53 | #F2F09E | 31-Mar-25 | 03-Apr-25
|  | 1176 | EE53 | #F2F09E | 21-Apr-25 | 01-May-25
|  | 1254 | EE59 | #F2F09E | 18-Apr-25 | 22-Apr-25
|  | 1258 | EE59 | #F2F09E | 16-May-25 | 20-May-25
| CELL 1 Mechanical Gallery | 211 | J5 | #3598FE | 29-Mar-25 | 29-Mar-25 | Mar 08: GSD; Mar 09: GSD; Mar 10: GSD; Mar 11: GSC; Mar 12: GSC; Mar 13: EE1; Mar 14: J44; Mar 15: J44; Mar 16: J44; Mar 17: J44; Mar 18: J44; Mar 19: J44; Mar 20: J44; Mar 21: GPA; Mar 22: GPA; Mar 23: GPA; Mar 24: GPA; Mar 25: GPA; Mar 26: GPA; Mar 27: GPA; Mar 28: GPA; Mar 29: J5; Mar 30: J5; Mar 31: J20; Apr 01: T1; Apr 02: T1; Apr 03: J20; Apr 04: EE35; Apr 05: EE35; Apr 06: GBA; Apr 07: EE57; Apr 08: EE57; Apr 09: EE57; Apr 10: EE57; Apr 11: EE42; Apr 12: EE42; Apr 13: EE42; Apr 14: EE42; Apr 15: EE42; Apr 16: EE42; Apr 17: EE42; Apr 18: EE42; Apr 19: EE42; Apr 20: EE42; Apr 21: EE42; Apr 22: EE42; Apr 23: EE42; Apr 24: EE42; Apr 25: EE42; Apr 26: EE60; Apr 27: EE60; Apr 28: EE60; Apr 29: EE60; Apr 30: EE60; May 01: GPA; May 02: J5; May 03: J5; May 04: J5; May 05: J20; May 06: T1; May 07: T1; May 08: J20; May 09: EE35; May 10: EE35; May 11: GBA; May 12: EE57; May 13: EE57; May 14: EE57; May 15: EE57; May 16: EE42; May 17: EE42; May 18: EE42; May 19: EE42; May 20: EE42; May 21: EE42; May 22: EE42; May 23: EE42; May 24: EE42; May 25: EE42; May 26: EE42; May 27: EE42; May 28: EE42; May 29: EE42; May 30: EE42; May 31: EE60; Jun 01: EE60; Jun 02: EE60; Jun 03: EE60; Jun 04: EE60
|  | 223 | J5 | #3598FE | 02-May-25 | 02-May-25
|  | 264 | J5 | #3598FE | 29-Mar-25 | 31-Mar-25
|  | 276 | J5 | #3598FE | 02-May-25 | 05-May-25
|  | 345 | Cx2 | #8ED973 | 03-Apr-25 | 05-Apr-25
|  | 357 | Cx2 | #8ED973 | 08-May-25 | 10-May-25
|  | 399 | GBA | #2F3452 | 04-Apr-25 | 16-Apr-25
|  | 403 | GBA | #2F3452 | 09-May-25 | 20-May-25
|  | 428 | EE35 | #F2F09E | 04-Apr-25 | 05-Apr-25
|  | 436 | EE35 | #F2F09E | 09-May-25 | 10-May-25
|  | 459 | J20 | #3598FE | 31-Mar-25 | 03-Apr-25
|  | 463 | J20 | #3598FE | 05-May-25 | 08-May-25
|  | 522 | J4 | #3598FE | 27-Mar-25 | 28-Mar-25
|  | 526 | J4 | #3598FE | 30-Apr-25 | 01-May-25
|  | 848 | EE1 | #F2F09E | 11-Mar-25 | 13-Mar-25
|  | 860 | EE1 | #F2F09E | 15-Apr-25 | 17-Apr-25
|  | 884 | GSC | #D85234 | 11-Mar-25 | 12-Mar-25
|  | 896 | GSC | #D85234 | 15-Apr-25 | 16-Apr-25
|  | 920 | GSD | #D85234 | 08-Mar-25 | 10-Mar-25
|  | 932 | GSD | #D85234 | 11-Apr-25 | 14-Apr-25
|  | 951 | J44 | #3598FE | 14-Mar-25 | 20-Mar-25
|  | 959 | J44 | #3598FE | 18-Apr-25 | 24-Apr-25
|  | 970 | GPA | #2A4D4F | 21-Mar-25 | 28-Mar-25
|  | 974 | GPA | #2A4D4F | 25-Apr-25 | 01-May-25
|  | 1001 | T1 | #D6F2FF | 01-Apr-25 | 02-Apr-25
|  | 1013 | T1 | #D6F2FF | 06-May-25 | 07-May-25
|  | 1056 | GBB | #2F3452 | 17-Apr-25 | 25-Apr-25
|  | 1060 | GBB | #2F3452 | 21-May-25 | 30-May-25
|  | 1081 | EE42 | #F2F09E | 11-Apr-25 | 25-Apr-25
|  | 1085 | EE42 | #F2F09E | 16-May-25 | 30-May-25
|  | 1187 | EE57 | #F2F09E | 07-Apr-25 | 10-Apr-25
|  | 1191 | EE57 | #F2F09E | 12-May-25 | 15-May-25
|  | 1266 | EE60 | #F2F09E | 26-Apr-25 | 30-Apr-25
|  | 1270 | EE60 | #F2F09E | 31-May-25 | 04-Jun-25
| CELL 1 Punchlist | 1126 | PU1 | #A02B93 | 17-Apr-25 | 28-Apr-25 | Apr 17: PU1; Apr 18: PU1; Apr 19: PU1; Apr 20: PU1; Apr 21: PU1; Apr 22: PU1; Apr 23: PU1; Apr 24: PU1; Apr 25: PU1; Apr 26: PU1; Apr 27: PU1; Apr 28: PU1; May 06: PU1; May 07: PU1; May 08: PU1; May 09: PU1; May 10: PU1; May 11: PU1; May 12: PU1; May 13: PU1; May 14: PU1; May 15: PU1; May 16: PU1; Jun 05: PU1; Jun 06: PU1; Jun 07: PU1; Jun 08: PU1; Jun 09: PU1; Jun 10: PU1; Jun 11: PU1; Jun 12: PU1; Jun 13: PU1; Jun 14: PU1; Jun 15: PU1; Jun 16: PU1; Jun 17: PU1
|  | 1127 | PU1 | #A02B93 | 06-May-25 | 16-May-25
|  | 1131 | PU1 | #A02B93 | 05-Jun-25 | 17-Jun-25
| CELL 2 Data Hall | 31 | S1 | #FED8E8 | 07-Apr-25 | 11-Apr-25 | Mar 05: J1; Mar 06: J3; Mar 07: J3; Mar 08: J3; Mar 10: EE2; Mar 11: EE2; Mar 12: EE2; Mar 13: GSD; Mar 14: GSD; Mar 15: GSD; Mar 17: GSC; Mar 18: GSC; Mar 19: J44; Mar 20: T1; Mar 21: T1; Mar 22: T1; Mar 23: T1; Mar 24: T1; Mar 25: J6; Mar 26: J6; Mar 27: J6; Mar 28: J42; Mar 29: J42; Mar 31: T3; Apr 01: T3; Apr 02: J16; Apr 03: J16; Apr 04: J16; Apr 05: J16; Apr 07: J37; Apr 08: J1; Apr 09: J37; Apr 10: J37; Apr 11: EE7; Apr 12: EE7; Apr 13: EE7; Apr 14: EE7; Apr 15: EE7; Apr 16: EE7; Apr 17: GSD; Apr 18: S2; Apr 19: S2; Apr 20: S2; Apr 21: S2; Apr 22: S2; Apr 23: J44; Apr 24: T1; Apr 25: T1; Apr 26: T1; Apr 27: J21; Apr 28: J6; Apr 29: J6; Apr 30: EE17; May 01: EE17; May 02: EE17; May 03: EE17; May 04: EE17; May 05: EE17; May 06: EE17; May 07: J16; May 08: J16; May 09: J16; May 10: J16; May 12: J37; May 13: J37; May 14: J37; May 15: J37; May 16: EE7; May 17: EE7; May 18: EE7; May 19: EE7; May 20: EE7; May 21: J33; May 22: S2; May 23: S2; May 24: S2; May 25: S2; May 26: S2; May 27: S2; May 28: EE19; May 29: EE19; May 30: EE19; May 31: J21; Jun 01: J21; Jun 02: J21; Jun 03: J21; Jun 04: EE17; Jun 05: EE17; Jun 06: EE17; Jun 07: EE17; Jun 08: EE17; Jun 09: EE17; Jun 25: EE19; Jun 26: EE19; Jun 27: EE19
|  | 35 | S1 | #FED8E8 | 12-May-25 | 16-May-25
|  | 162 | EE32 | #F2F09E | 23-Apr-25 | 25-Apr-25
|  | 166 | EE32 | #F2F09E | 28-May-25 | 30-May-25
|  | 190 | S2 | #FED8E8 | 23-Apr-25 | 26-Apr-25
|  | 194 | S2 | #FED8E8 | 28-May-25 | 31-May-25
|  | 212 | J5 | #3598FE | 19-Mar-25 | 20-Mar-25
|  | 224 | J5 | #3598FE | 23-Apr-25 | 24-Apr-25
|  | 265 | J5 | #3598FE | 17-Mar-25 | 19-Mar-25
|  | 277 | J5 | #3598FE | 21-Apr-25 | 23-Apr-25
|  | 346 | Cx2 | #8ED973 | 02-Apr-25 | 02-Apr-25
|  | 358 | Cx2 | #8ED973 | 07-May-25 | 07-May-25
|  | 381 | EE2 | #F2F09E | 10-Mar-25 | 12-Mar-25
|  | 389 | EE2 | #F2F09E | 14-Apr-25 | 16-Apr-25
|  | 412 | EE10 | #F2F09E | 09-Apr-25 | 15-Apr-25
|  | 416 | EE10 | #F2F09E | 14-May-25 | 19-May-25
|  | 448 | J16 | #3598FE | 02-Apr-25 | 05-Apr-25
|  | 452 | J16 | #3598FE | 07-May-25 | 10-May-25
|  | 472 | J21 | #3598FE | 26-Apr-25 | 29-Apr-25
|  | 476 | J21 | #3598FE | 31-May-25 | 03-Jun-25
|  | 485 | J23 | #3598FE | 11-Apr-25 | 14-Apr-25
|  | 489 | J23 | #3598FE | 16-May-25 | 17-May-25
|  | 499 | J4 | #3598FE | 13-Mar-25 | 15-Mar-25
|  | 503 | J4 | #3598FE | 17-Apr-25 | 19-Apr-25
|  | 542 | J33 | #3598FE | 11-Apr-25 | 17-Apr-25
|  | 546 | J33 | #3598FE | 16-May-25 | 21-May-25
|  | 558 | J3 | #3598FE | 06-Mar-25 | 08-Mar-25
|  | 566 | J3 | #3598FE | 09-Apr-25 | 11-Apr-25
|  | 587 | J37 | #3598FE | 07-Apr-25 | 10-Apr-25
|  | 591 | J37 | #3598FE | 12-May-25 | 15-May-25
|  | 610 | J6 | #3598FE | 25-Mar-25 | 27-Mar-25
|  | 614 | J6 | #3598FE | 28-Apr-25 | 30-Apr-25
|  | 622 | J42 | #3598FE | 28-Mar-25 | 29-Mar-25
|  | 626 | J42 | #3598FE | 01-May-25 | 02-May-25
|  | 647 | J1 | #3598FE | 05-Mar-25 | 05-Mar-25
|  | 651 | J1 | #3598FE | 08-Apr-25 | 08-Apr-25
|  | 849 | EE1 | #F2F09E | 17-Mar-25 | 20-Mar-25
|  | 861 | EE1 | #F2F09E | 21-Apr-25 | 24-Apr-25
|  | 885 | GSC | #D85234 | 17-Mar-25 | 19-Mar-25
|  | 897 | GSC | #D85234 | 21-Apr-25 | 23-Apr-25
|  | 921 | GSD | #D85234 | 13-Mar-25 | 15-Mar-25
|  | 933 | GSD | #D85234 | 17-Apr-25 | 19-Apr-25
|  | 952 | J44 | #3598FE | 19-Mar-25 | 20-Mar-25
|  | 960 | J44 | #3598FE | 23-Apr-25 | 24-Apr-25
|  | 1002 | T1 | #D6F2FF | 20-Mar-25 | 24-Mar-25
|  | 1014 | T1 | #D6F2FF | 24-Apr-25 | 26-Apr-25
|  | 1028 | T3 | #D6F2FF | 31-Mar-25 | 01-Apr-25
|  | 1032 | T3 | #D6F2FF | 05-May-25 | 06-May-25
|  | 1110 | EE17 | #F2F09E | 30-Apr-25 | 06-May-25
|  | 1114 | EE17 | #F2F09E | 04-Jun-25 | 09-Jun-25
|  | 1140 | S2 | #FED8E8 | 18-Apr-25 | 22-Apr-25
|  | 1144 | S2 | #FED8E8 | 22-May-25 | 27-May-25
|  | 1200 | EE7 | #F2F09E | 11-Apr-25 | 16-Apr-25
|  | 1204 | EE7 | #F2F09E | 16-May-25 | 20-May-25
|  | 1283 | EE19 | #F2F09E | 28-May-25 | 30-May-25
|  | 1287 | EE19 | #F2F09E | 25-Jun-25 | 27-Jun-25
| CELL 2 Electrical Room | 213 | J5 | #3598FE | 19-Mar-25 | 19-Mar-25 | Mar 10: J3; Mar 11: J3; Mar 12: EE2; Mar 13: EE2; Mar 14: GSD; Mar 15: GSD; Mar 16: J4; Mar 17: GSC; Mar 18: GSC; Mar 19: EE1; Mar 20: EE35; Mar 21: T1; Mar 22: T1; Mar 23: T1; Mar 24: T1; Mar 25: Cx2; Mar 26: EE53; Mar 27: EE53; Mar 28: EE53; Mar 29: EE53; Apr 14: J3; Apr 15: J3; Apr 16: EE2; Apr 17: EE2; Apr 18: GSD; Apr 19: GSD; Apr 20: J4; Apr 21: GSC; Apr 22: GSC; Apr 23: EE1; Apr 24: EE35; Apr 25: T1; Apr 26: T1; Apr 28: Cx2; Apr 29: EE53; Apr 30: EE53; May 01: EE53; May 02: EE53; May 03: EE29; May 04: EE29; May 05: EE29; May 06: EE29; May 07: EE29; May 08: EE29; May 09: EE29; May 10: EE29; May 11: EE29; May 12: EE29; May 13: EE29; May 14: EE29; May 15: EE59; May 16: EE59; May 17: EE59; May 18: EE59; May 19: EE59; May 20: EE47; May 21: EE47; May 22: EE47; May 23: EE47; May 24: EE47; May 25: EE47; May 26: EE47; May 27: EE47; May 30: EE29; May 31: EE29; Jun 01: EE29; Jun 02: EE29; Jun 03: EE29; Jun 04: EE29; Jun 05: EE29; Jun 06: EE29; Jun 07: EE29; Jun 08: EE29; Jun 09: EE29; Jun 10: EE29; Jun 11: EE29; Jun 12: EE59; Jun 13: EE59; Jun 14: EE59; Jun 15: EE59; Jun 16: EE59; Jun 17: EE59; Jun 18: EE47; Jun 19: EE47; Jun 20: EE47; Jun 21: EE47; Jun 22: EE47; Jun 23: EE47; Jun 24: EE47
|  | 225 | J5 | #3598FE | 23-Apr-25 | 23-Apr-25
|  | 266 | J5 | #3598FE | 19-Mar-25 | 20-Mar-25
|  | 278 | J5 | #3598FE | 23-Apr-25 | 24-Apr-25
|  | 347 | Cx2 | #8ED973 | 25-Mar-25 | 25-Mar-25
|  | 359 | Cx2 | #8ED973 | 28-Apr-25 | 28-Apr-25
|  | 382 | EE2 | #F2F09E | 12-Mar-25 | 13-Mar-25
|  | 390 | EE2 | #F2F09E | 16-Apr-25 | 17-Apr-25
|  | 429 | EE35 | #F2F09E | 20-Mar-25 | 21-Mar-25
|  | 437 | EE35 | #F2F09E | 24-Apr-25 | 25-Apr-25
|  | 511 | J4 | #3598FE | 14-Mar-25 | 18-Mar-25
|  | 515 | J4 | #3598FE | 18-Apr-25 | 22-Apr-25
|  | 559 | J3 | #3598FE | 10-Mar-25 | 11-Mar-25
|  | 567 | J3 | #3598FE | 14-Apr-25 | 15-Apr-25
|  | 850 | EE1 | #F2F09E | 17-Mar-25 | 19-Mar-25
|  | 862 | EE1 | #F2F09E | 21-Apr-25 | 23-Apr-25
|  | 886 | GSC | #D85234 | 17-Mar-25 | 18-Mar-25
|  | 898 | GSC | #D85234 | 21-Apr-25 | 22-Apr-25
|  | 922 | GSD | #D85234 | 14-Mar-25 | 15-Mar-25
|  | 934 | GSD | #D85234 | 18-Apr-25 | 19-Apr-25
|  | 1003 | T1 | #D6F2FF | 21-Mar-25 | 24-Mar-25
|  | 1015 | T1 | #D6F2FF | 25-Apr-25 | 26-Apr-25
|  | 1068 | EE29 | #F2F09E | 01-May-25 | 14-May-25
|  | 1070 | EE29 | #F2F09E | 30-May-25 | 11-Jun-25
|  | 1096 | EE47 | #F2F09E | 15-May-25 | 27-May-25
|  | 1098 | EE47 | #F2F09E | 12-Jun-25 | 24-Jun-25
|  | 1173 | EE53 | #F2F09E | 26-Mar-25 | 29-Mar-25
|  | 1177 | EE53 | #F2F09E | 29-Apr-25 | 02-May-25
|  | 1255 | EE59 | #F2F09E | 15-May-25 | 19-May-25
|  | 1259 | EE59 | #F2F09E | 12-Jun-25 | 17-Jun-25
| CELL 2 Mechanical Gallery | 214 | J5 | #3598FE | 07-Apr-25 | 07-Apr-25 | Mar 17: GSD; Mar 18: GSD; Mar 19: GSC; Mar 20: GSC; Mar 21: EE1; Mar 24: J44; Mar 25: J44; Mar 26: J44; Mar 27: J44; Mar 28: J44; Mar 29: J44; Mar 31: GPA; Apr 01: GPA; Apr 02: GPA; Apr 03: GPA; Apr 04: GPA; Apr 05: GPA; Apr 07: J5; Apr 08: J20; Apr 09: T1; Apr 10: T1; Apr 11: J20; Apr 12: Cx2; Apr 13: Cx2; Apr 14: EE35; Apr 15: EE35; Apr 16: EE57; Apr 17: EE57; Apr 18: EE57; Apr 19: EE57; Apr 20: GBA; Apr 21: EE42; Apr 22: EE42; Apr 23: EE42; Apr 24: EE42; Apr 25: EE42; Apr 26: EE42; Apr 27: EE42; Apr 28: EE42; Apr 29: EE42; Apr 30: EE42; May 01: EE42; May 02: EE42; May 03: EE42; May 04: EE42; May 05: EE42; May 06: EE60; May 07: EE60; May 08: EE60; May 09: EE60; May 10: GPA; May 12: J5; May 13: J20; May 14: T1; May 15: T1; May 16: J20; May 17: EE35; May 18: EE35; May 19: EE35; May 20: EE57; May 21: EE57; May 22: EE57; May 23: EE57; May 24: GBA; May 25: GBA; May 26: GBA; May 27: EE42; May 28: EE42; May 29: EE42; May 30: EE42; May 31: EE42; Jun 01: EE42; Jun 02: EE42; Jun 03: EE42; Jun 04: EE42; Jun 05: EE42; Jun 06: EE42; Jun 07: EE42; Jun 09: EE60; Jun 10: EE60; Jun 11: EE60; Jun 12: EE60
|  | 226 | J5 | #3598FE | 12-May-25 | 12-May-25
|  | 267 | J5 | #3598FE | 07-Apr-25 | 08-Apr-25
|  | 279 | J5 | #3598FE | 12-May-25 | 13-May-25
|  | 348 | Cx2 | #8ED973 | 11-Apr-25 | 15-Apr-25
|  | 360 | Cx2 | #8ED973 | 16-May-25 | 19-May-25
|  | 400 | GBA | #2F3452 | 14-Apr-25 | 24-Apr-25
|  | 404 | GBA | #2F3452 | 17-May-25 | 29-May-25
|  | 430 | EE35 | #F2F09E | 14-Apr-25 | 15-Apr-25
|  | 438 | EE35 | #F2F09E | 17-May-25 | 19-May-25
|  | 460 | J20 | #3598FE | 08-Apr-25 | 11-Apr-25
|  | 464 | J20 | #3598FE | 13-May-25 | 16-May-25
|  | 523 | J4 | #3598FE | 04-Apr-25 | 05-Apr-25
|  | 527 | J4 | #3598FE | 09-May-25 | 10-May-25
|  | 851 | EE1 | #F2F09E | 19-Mar-25 | 21-Mar-25
|  | 863 | EE1 | #F2F09E | 23-Apr-25 | 25-Apr-25
|  | 887 | GSC | #D85234 | 19-Mar-25 | 20-Mar-25
|  | 899 | GSC | #D85234 | 23-Apr-25 | 24-Apr-25
|  | 923 | GSD | #D85234 | 17-Mar-25 | 18-Mar-25
|  | 935 | GSD | #D85234 | 21-Apr-25 | 22-Apr-25
|  | 953 | J44 | #3598FE | 24-Mar-25 | 29-Mar-25
|  | 961 | J44 | #3598FE | 26-Apr-25 | 02-May-25
|  | 971 | GPA | #2A4D4F | 31-Mar-25 | 05-Apr-25
|  | 975 | GPA | #2A4D4F | 05-May-25 | 10-May-25
|  | 1004 | T1 | #D6F2FF | 09-Apr-25 | 10-Apr-25
|  | 1016 | T1 | #D6F2FF | 14-May-25 | 15-May-25
|  | 1057 | GBB | #2F3452 | 25-Apr-25 | 05-May-25
|  | 1061 | GBB | #2F3452 | 30-May-25 | 07-Jun-25
|  | 1082 | EE42 | #F2F09E | 21-Apr-25 | 05-May-25
|  | 1086 | EE42 | #F2F09E | 27-May-25 | 07-Jun-25
|  | 1188 | EE57 | #F2F09E | 16-Apr-25 | 19-Apr-25
|  | 1192 | EE57 | #F2F09E | 20-May-25 | 23-May-25
|  | 1267 | EE60 | #F2F09E | 06-May-25 | 09-May-25
|  | 1271 | EE60 | #F2F09E | 09-Jun-25 | 12-Jun-25
| CELL 2 Punchlist | 1128 | PU1 | #A02B93 | 31-May-25 | 11-Jun-25 | May 31: PU1; Jun 01: PU1; Jun 02: PU1; Jun 03: PU1; Jun 04: PU1; Jun 05: PU1; Jun 06: PU1; Jun 07: PU1; Jun 08: PU1; Jun 09: PU1; Jun 10: PU1; Jun 11: PU1; Jun 28: PU1; Jun 29: PU1; Jun 30: PU1; Jul 01: PU1; Jul 02: PU1; Jul 03: PU1; Jul 04: PU1; Jul 05: PU1; Jul 06: PU1; Jul 07: PU1; Jul 08: PU1; Jul 09: PU1; Jul 10: PU1; Jul 11: PU1
|  | 1132 | PU1 | #A02B93 | 28-Jun-25 | 11-Jul-25
| CELL 3 Data Hall | 32 | S1 | #FED8E8 | 30-Apr-25 | 06-May-25 | Mar 28: J1; Mar 29: J3; Mar 30: J3; Mar 31: J3; Apr 01: J3; Apr 02: EE2; Apr 03: EE2; Apr 04: EE2; Apr 05: GSD; Apr 06: GSD; Apr 07: GSD; Apr 08: GSD; Apr 09: GSC; Apr 10: GSC; Apr 11: J44; Apr 12: J44; Apr 13: J44; Apr 14: T1; Apr 15: T1; Apr 16: T1; Apr 17: J6; Apr 18: J6; Apr 19: J6; Apr 21: J42; Apr 22: J42; Apr 23: T3; Apr 24: T3; Apr 25: J16; Apr 26: J16; Apr 27: J16; Apr 28: J16; Apr 29: J16; Apr 30: J37; May 01: J1; May 02: J37; May 03: J37; May 04: J37; May 05: J37; May 06: EE7; May 07: EE7; May 08: EE7; May 09: EE7; May 10: GSD; May 11: GSD; May 12: S2; May 13: S2; May 14: S2; May 15: S2; May 16: J44; May 17: T1; May 18: T1; May 19: T1; May 20: T1; May 21: J6; May 22: J6; May 23: EE17; May 24: EE17; May 25: EE17; May 26: EE17; May 27: EE17; May 28: EE17; May 29: EE17; May 30: J16; May 31: J16; Jun 01: J16; Jun 02: J16; Jun 03: J16; Jun 04: J37; Jun 05: J37; Jun 06: J37; Jun 07: J37; Jun 08: EE10; Jun 09: EE7; Jun 10: EE7; Jun 11: EE7; Jun 12: EE7; Jun 13: J33; Jun 16: S2; Jun 17: S2; Jun 18: S2; Jun 19: S2; Jun 20: S2; Jun 21: S2; Jun 22: S2; Jun 23: S2; Jun 24: J21; Jun 25: J21; Jun 26: J21; Jun 27: EE17; Jun 28: EE17; Jun 29: EE17; Jun 30: EE17; Jul 01: EE17; Jul 02: EE17; Jul 18: EE19; Jul 19: EE19; Jul 20: EE19; Jul 21: EE19; Aug 06: EE19; Aug 07: EE19; Aug 08: EE19
|  | 36 | S1 | #FED8E8 | 04-Jun-25 | 09-Jun-25
|  | 163 | EE32 | #F2F09E | 16-May-25 | 19-May-25
|  | 167 | EE32 | #F2F09E | 20-Jun-25 | 23-Jun-25
|  | 191 | S2 | #FED8E8 | 16-May-25 | 20-May-25
|  | 195 | S2 | #FED8E8 | 20-Jun-25 | 24-Jun-25
|  | 215 | J5 | #3598FE | 11-Apr-25 | 14-Apr-25
|  | 227 | J5 | #3598FE | 16-May-25 | 17-May-25
|  | 268 | J5 | #3598FE | 09-Apr-25 | 11-Apr-25
|  | 280 | J5 | #3598FE | 14-May-25 | 16-May-25
|  | 349 | Cx2 | #8ED973 | 25-Apr-25 | 25-Apr-25
|  | 361 | Cx2 | #8ED973 | 30-May-25 | 30-May-25
|  | 383 | EE2 | #F2F09E | 02-Apr-25 | 04-Apr-25
|  | 391 | EE2 | #F2F09E | 07-May-25 | 09-May-25
|  | 413 | EE10 | #F2F09E | 02-May-25 | 08-May-25
|  | 417 | EE10 | #F2F09E | 06-Jun-25 | 11-Jun-25
|  | 449 | J16 | #3598FE | 25-Apr-25 | 29-Apr-25
|  | 453 | J16 | #3598FE | 30-May-25 | 03-Jun-25
|  | 473 | J21 | #3598FE | 20-May-25 | 22-May-25
|  | 477 | J21 | #3598FE | 24-Jun-25 | 26-Jun-25
|  | 486 | J23 | #3598FE | 06-May-25 | 07-May-25
|  | 490 | J23 | #3598FE | 09-Jun-25 | 10-Jun-25
|  | 500 | J4 | #3598FE | 05-Apr-25 | 08-Apr-25
|  | 504 | J4 | #3598FE | 10-May-25 | 13-May-25
|  | 543 | J33 | #3598FE | 06-May-25 | 10-May-25
|  | 547 | J33 | #3598FE | 09-Jun-25 | 13-Jun-25
|  | 560 | J3 | #3598FE | 29-Mar-25 | 01-Apr-25
|  | 568 | J3 | #3598FE | 02-May-25 | 06-May-25
|  | 588 | J37 | #3598FE | 30-Apr-25 | 05-May-25
|  | 592 | J37 | #3598FE | 04-Jun-25 | 07-Jun-25
|  | 611 | J6 | #3598FE | 17-Apr-25 | 19-Apr-25
|  | 615 | J6 | #3598FE | 21-May-25 | 23-May-25
|  | 623 | J42 | #3598FE | 21-Apr-25 | 22-Apr-25
|  | 627 | J42 | #3598FE | 27-May-25 | 27-May-25
|  | 648 | J1 | #3598FE | 28-Mar-25 | 28-Mar-25
|  | 652 | J1 | #3598FE | 01-May-25 | 01-May-25
|  | 852 | EE1 | #F2F09E | 09-Apr-25 | 14-Apr-25
|  | 864 | EE1 | #F2F09E | 14-May-25 | 17-May-25
|  | 888 | GSC | #D85234 | 09-Apr-25 | 11-Apr-25
|  | 900 | GSC | #D85234 | 14-May-25 | 16-May-25
|  | 924 | GSD | #D85234 | 05-Apr-25 | 08-Apr-25
|  | 936 | GSD | #D85234 | 10-May-25 | 13-May-25
|  | 954 | J44 | #3598FE | 11-Apr-25 | 14-Apr-25
|  | 962 | J44 | #3598FE | 16-May-25 | 17-May-25
|  | 1005 | T1 | #D6F2FF | 14-Apr-25 | 16-Apr-25
|  | 1017 | T1 | #D6F2FF | 17-May-25 | 20-May-25
|  | 1029 | T3 | #D6F2FF | 23-Apr-25 | 24-Apr-25
|  | 1033 | T3 | #D6F2FF | 28-May-25 | 29-May-25
|  | 1111 | EE17 | #F2F09E | 23-May-25 | 29-May-25
|  | 1115 | EE17 | #F2F09E | 27-Jun-25 | 02-Jul-25
|  | 1141 | S2 | #FED8E8 | 12-May-25 | 15-May-25
|  | 1145 | S2 | #FED8E8 | 16-Jun-25 | 19-Jun-25
|  | 1201 | EE7 | #F2F09E | 06-May-25 | 09-May-25
|  | 1205 | EE7 | #F2F09E | 09-Jun-25 | 12-Jun-25
|  | 1284 | EE19 | #F2F09E | 18-Jul-25 | 21-Jul-25
|  | 1288 | EE19 | #F2F09E | 06-Aug-25 | 08-Aug-25
| CELL 3 Electrical Room | 204 | J5 | #3598FE | 08-Mar-25 | 08-Mar-25 | Feb 26: J3; Feb 27: J3; Feb 28: EE2; Mar 01: EE2; Mar 02: EE2; Mar 03: EE2; Mar 04: GSD; Mar 05: GSD; Mar 06: GSC; Mar 07: GSC; Mar 08: EE1; Mar 09: J5; Mar 10: EE35; Mar 11: T1; Mar 12: T1; Mar 13: Cx2; Mar 14: EE53; Mar 15: EE53; Mar 16: EE53; Mar 17: EE53; Mar 18: EE53; Apr 02: J3; Apr 03: J3; Apr 04: EE2; Apr 05: EE2; Apr 07: GSD; Apr 08: GSD; Apr 09: GSC; Apr 10: GSC; Apr 11: EE1; Apr 12: J5; Apr 13: J5; Apr 14: EE35; Apr 15: T1; Apr 16: T1; Apr 17: Cx2; Apr 18: EE53; Apr 19: EE53; Apr 20: EE53; Apr 21: EE53; Apr 22: EE53; May 07: J3; May 08: J3; May 09: EE2; May 10: EE29; May 11: EE29; May 12: EE29; May 13: EE29; May 14: EE29; May 15: EE29; May 16: EE29; May 17: EE29; May 18: EE29; May 19: EE29; May 20: EE29; May 21: EE29; May 22: EE53; May 23: EE59; May 24: EE59; May 25: EE59; May 26: EE59; May 27: EE59; May 28: EE59; May 29: EE47; May 30: EE47; May 31: EE47; Jun 01: EE47; Jun 02: EE47; Jun 03: EE47; Jun 04: EE47; Jun 24: EE29; Jun 25: EE29; Jun 26: EE29; Jun 27: EE29; Jun 28: EE29; Jun 29: EE29; Jun 30: EE29; Jul 01: EE29; Jul 02: EE29; Jul 03: EE29; Jul 04: EE29; Jul 05: EE29; Jul 06: EE29; Jul 07: EE29; Jul 08: EE29; Jul 09: EE59; Jul 10: EE59; Jul 11: EE59; Jul 12: EE59; Jul 13: EE47; Jul 14: EE47; Jul 15: EE47; Jul 16: EE47; Jul 17: EE47; Jul 18: EE47; Jul 19: EE47; Jul 20: EE29; Jul 21: EE29; Jul 22: EE29; Jul 23: EE29; Jul 24: EE59; Jul 25: EE59; Jul 26: EE59; Jul 27: EE59; Jul 28: EE59; Jul 29: EE59; Jul 30: EE47; Jul 31: EE47; Aug 01: EE47; Aug 02: EE47; Aug 03: EE47; Aug 04: EE47; Aug 05: EE47
|  | 216 | J5 | #3598FE | 11-Apr-25 | 11-Apr-25
|  | 228 | J5 | #3598FE | 16-May-25 | 16-May-25
|  | 257 | J5 | #3598FE | 08-Mar-25 | 10-Mar-25
|  | 269 | J5 | #3598FE | 11-Apr-25 | 14-Apr-25
|  | 281 | J5 | #3598FE | 16-May-25 | 17-May-25
|  | 338 | Cx2 | #8ED973 | 13-Mar-25 | 13-Mar-25
|  | 350 | Cx2 | #8ED973 | 17-Apr-25 | 17-Apr-25
|  | 362 | Cx2 | #8ED973 | 21-May-25 | 21-May-25
|  | 376 | EE2 | #F2F09E | 28-Feb-25 | 03-Mar-25
|  | 384 | EE2 | #F2F09E | 04-Apr-25 | 05-Apr-25
|  | 392 | EE2 | #F2F09E | 09-May-25 | 10-May-25
|  | 423 | EE35 | #F2F09E | 10-Mar-25 | 11-Mar-25
|  | 431 | EE35 | #F2F09E | 14-Apr-25 | 15-Apr-25
|  | 439 | EE35 | #F2F09E | 17-May-25 | 19-May-25
|  | 508 | J4 | #3598FE | 04-Mar-25 | 07-Mar-25
|  | 512 | J4 | #3598FE | 07-Apr-25 | 10-Apr-25
|  | 516 | J4 | #3598FE | 12-May-25 | 15-May-25
|  | 554 | J3 | #3598FE | 26-Feb-25 | 27-Feb-25
|  | 561 | J3 | #3598FE | 02-Apr-25 | 03-Apr-25
|  | 569 | J3 | #3598FE | 07-May-25 | 08-May-25
|  | 841 | EE1 | #F2F09E | 06-Mar-25 | 08-Mar-25
|  | 853 | EE1 | #F2F09E | 09-Apr-25 | 11-Apr-25
|  | 865 | EE1 | #F2F09E | 14-May-25 | 16-May-25
|  | 877 | GSC | #D85234 | 06-Mar-25 | 07-Mar-25
|  | 889 | GSC | #D85234 | 09-Apr-25 | 10-Apr-25
|  | 901 | GSC | #D85234 | 14-May-25 | 15-May-25
|  | 913 | GSD | #D85234 | 04-Mar-25 | 05-Mar-25
|  | 925 | GSD | #D85234 | 07-Apr-25 | 08-Apr-25
|  | 937 | GSD | #D85234 | 12-May-25 | 13-May-25
|  | 994 | T1 | #D6F2FF | 11-Mar-25 | 12-Mar-25
|  | 1006 | T1 | #D6F2FF | 15-Apr-25 | 16-Apr-25
|  | 1018 | T1 | #D6F2FF | 19-May-25 | 20-May-25
|  | 1071 | EE29 | #F2F09E | 10-May-25 | 22-May-25
|  | 1073 | EE29 | #F2F09E | 24-Jun-25 | 08-Jul-25
|  | 1075 | EE29 | #F2F09E | 11-Jul-25 | 23-Jul-25
|  | 1099 | EE47 | #F2F09E | 23-May-25 | 04-Jun-25
|  | 1101 | EE47 | #F2F09E | 09-Jul-25 | 19-Jul-25
|  | 1103 | EE47 | #F2F09E | 24-Jul-25 | 05-Aug-25
|  | 1170 | EE53 | #F2F09E | 14-Mar-25 | 18-Mar-25
|  | 1174 | EE53 | #F2F09E | 18-Apr-25 | 22-Apr-25
|  | 1178 | EE53 | #F2F09E | 22-May-25 | 27-May-25
|  | 1252 | EE59 | #F2F09E | 23-May-25 | 28-May-25
|  | 1256 | EE59 | #F2F09E | 09-Jul-25 | 12-Jul-25
|  | 1260 | EE59 | #F2F09E | 24-Jul-25 | 29-Jul-25
| CELL 3 Mechanical Gallery | 205 | J5 | #3598FE | 27-Mar-25 | 27-Mar-25 | Mar 06: GSD; Mar 07: GSD; Mar 08: GSC; Mar 09: GSC; Mar 10: GSC; Mar 11: EE1; Mar 12: J44; Mar 13: J44; Mar 14: J44; Mar 15: J44; Mar 16: J44; Mar 17: J44; Mar 18: J44; Mar 19: GPA; Mar 20: GPA; Mar 21: GPA; Mar 22: GPA; Mar 23: GPA; Mar 24: GPA; Mar 25: GPA; Mar 26: GPA; Mar 27: J5; Mar 28: J20; Mar 29: T1; Mar 30: T1; Mar 31: T1; Apr 01: J20; Apr 02: EE35; Apr 03: EE35; Apr 04: EE57; Apr 05: EE57; Apr 06: EE57; Apr 07: EE57; Apr 08: EE57; Apr 09: EE42; Apr 10: EE42; Apr 11: EE42; Apr 12: EE42; Apr 13: EE42; Apr 14: EE42; Apr 15: EE42; Apr 16: EE42; Apr 17: EE42; Apr 18: EE42; Apr 19: EE42; Apr 20: EE42; Apr 21: EE42; Apr 22: EE42; Apr 23: EE42; Apr 24: EE60; Apr 25: EE60; Apr 26: EE60; Apr 27: EE60; Apr 28: EE60; Apr 29: GPA; Apr 30: J5; May 01: J20; May 02: T1; May 03: T1; May 04: T1; May 05: T1; May 06: J20; May 07: EE35; May 08: EE35; May 09: EE57; May 10: EE57; May 11: EE57; May 12: EE57; May 13: EE57; May 14: EE42; May 15: EE42; May 16: EE42; May 17: EE42; May 18: EE42; May 19: EE42; May 20: EE42; May 21: EE42; May 22: EE42; May 23: EE42; May 24: EE42; May 25: EE42; May 26: EE42; May 27: EE42; May 28: EE42; May 29: EE60; May 30: EE60; May 31: EE60; Jun 01: EE60; Jun 02: EE60; Jun 03: GPA; Jun 04: J5; Jun 05: J20; Jun 06: T1; Jun 07: T1; Jun 08: J20; Jun 09: J20; Jun 10: EE35; Jun 11: EE35; Jun 12: EE57; Jun 13: EE57; Jun 14: EE57; Jun 15: EE57; Jun 16: EE57; Jun 17: EE57; Jun 18: EE42; Jun 19: EE42; Jun 20: EE42; Jun 21: EE42; Jun 22: EE42; Jun 23: EE42; Jun 24: EE42; Jun 25: EE42; Jun 26: EE42; Jun 27: EE42; Jun 28: EE42; Jun 29: EE42; Jun 30: EE42; Jul 01: EE42; Jul 02: EE60; Jul 03: EE60; Jul 04: EE60; Jul 05: EE60; Jul 06: EE60; Jul 07: EE60; Jul 08: EE60
|  | 217 | J5 | #3598FE | 30-Apr-25 | 30-Apr-25
|  | 229 | J5 | #3598FE | 04-Jun-25 | 04-Jun-25
|  | 258 | J5 | #3598FE | 27-Mar-25 | 28-Mar-25
|  | 270 | J5 | #3598FE | 30-Apr-25 | 01-May-25
|  | 282 | J5 | #3598FE | 04-Jun-25 | 05-Jun-25
|  | 339 | Cx2 | #8ED973 | 01-Apr-25 | 03-Apr-25
|  | 351 | Cx2 | #8ED973 | 06-May-25 | 08-May-25
|  | 363 | Cx2 | #8ED973 | 09-Jun-25 | 11-Jun-25
|  | 397 | GBA | #2F3452 | 02-Apr-25 | 14-Apr-25
|  | 401 | GBA | #2F3452 | 07-May-25 | 17-May-25
|  | 405 | GBA | #2F3452 | 10-Jun-25 | 21-Jun-25
|  | 424 | EE35 | #F2F09E | 02-Apr-25 | 03-Apr-25
|  | 432 | EE35 | #F2F09E | 07-May-25 | 08-May-25
|  | 440 | EE35 | #F2F09E | 10-Jun-25 | 11-Jun-25
|  | 457 | J20 | #3598FE | 28-Mar-25 | 01-Apr-25
|  | 461 | J20 | #3598FE | 01-May-25 | 06-May-25
|  | 465 | J20 | #3598FE | 05-Jun-25 | 09-Jun-25
|  | 520 | J4 | #3598FE | 25-Mar-25 | 26-Mar-25
|  | 524 | J4 | #3598FE | 28-Apr-25 | 29-Apr-25
|  | 528 | J4 | #3598FE | 02-Jun-25 | 03-Jun-25
|  | 842 | EE1 | #F2F09E | 08-Mar-25 | 11-Mar-25
|  | 854 | EE1 | #F2F09E | 11-Apr-25 | 15-Apr-25
|  | 866 | EE1 | #F2F09E | 16-May-25 | 19-May-25
|  | 878 | GSC | #D85234 | 08-Mar-25 | 10-Mar-25
|  | 890 | GSC | #D85234 | 11-Apr-25 | 14-Apr-25
|  | 902 | GSC | #D85234 | 16-May-25 | 17-May-25
|  | 914 | GSD | #D85234 | 06-Mar-25 | 07-Mar-25
|  | 926 | GSD | #D85234 | 09-Apr-25 | 10-Apr-25
|  | 938 | GSD | #D85234 | 14-May-25 | 15-May-25
|  | 947 | J44 | #3598FE | 12-Mar-25 | 18-Mar-25
|  | 955 | J44 | #3598FE | 16-Apr-25 | 22-Apr-25
|  | 963 | J44 | #3598FE | 20-May-25 | 27-May-25
|  | 968 | GPA | #2A4D4F | 19-Mar-25 | 26-Mar-25
|  | 972 | GPA | #2A4D4F | 23-Apr-25 | 29-Apr-25
|  | 976 | GPA | #2A4D4F | 28-May-25 | 03-Jun-25
|  | 995 | T1 | #D6F2FF | 29-Mar-25 | 31-Mar-25
|  | 1007 | T1 | #D6F2FF | 02-May-25 | 05-May-25
|  | 1019 | T1 | #D6F2FF | 06-Jun-25 | 07-Jun-25
|  | 1054 | GBB | #2F3452 | 15-Apr-25 | 23-Apr-25
|  | 1058 | GBB | #2F3452 | 19-May-25 | 28-May-25
|  | 1062 | GBB | #2F3452 | 23-Jun-25 | 01-Jul-25
|  | 1079 | EE42 | #F2F09E | 09-Apr-25 | 23-Apr-25
|  | 1083 | EE42 | #F2F09E | 14-May-25 | 28-May-25
|  | 1087 | EE42 | #F2F09E | 18-Jun-25 | 01-Jul-25
|  | 1185 | EE57 | #F2F09E | 04-Apr-25 | 08-Apr-25
|  | 1189 | EE57 | #F2F09E | 09-May-25 | 13-May-25
|  | 1193 | EE57 | #F2F09E | 12-Jun-25 | 17-Jun-25
|  | 1264 | EE60 | #F2F09E | 24-Apr-25 | 28-Apr-25
|  | 1268 | EE60 | #F2F09E | 29-May-25 | 02-Jun-25
|  | 1272 | EE60 | #F2F09E | 02-Jul-25 | 08-Jul-25
| CELL 3 Punchlist | 1124 | PU1 | #A02B93 | 09-Jun-25 | 20-Jun-25 | Jun 09: PU1; Jun 10: PU1; Jun 11: PU1; Jun 12: PU1; Jun 13: PU1; Jun 14: PU1; Jun 15: PU1; Jun 16: PU1; Jun 17: PU1; Jun 18: PU1; Jun 19: PU1; Jun 20: PU1; Jul 22: PU1; Jul 23: PU1; Jul 24: PU1; Jul 25: PU1; Jul 26: PU1; Jul 27: PU1; Jul 28: PU1; Jul 29: PU1; Jul 30: PU1; Jul 31: PU1; Aug 01: PU1; Aug 02: PU1; Aug 09: PU1; Aug 10: PU1; Aug 11: PU1; Aug 12: PU1; Aug 13: PU1; Aug 14: PU1; Aug 15: PU1; Aug 16: PU1; Aug 17: PU1; Aug 18: PU1; Aug 19: PU1; Aug 20: PU1; Aug 21: PU1
|  | 1129 | PU1 | #A02B93 | 22-Jul-25 | 02-Aug-25
|  | 1133 | PU1 | #A02B93 | 09-Aug-25 | 21-Aug-25
| CELL 4 Data Hall | 29 | S1 | #FED8E8 | 14-Mar-25 | 19-Mar-25 | Feb 10: J1; Feb 11: J3; Feb 12: J3; Feb 13: J3; Feb 14: EE2; Feb 15: EE2; Feb 16: EE2; Feb 17: EE2; Feb 18: GSD; Feb 19: GSD; Feb 20: GSD; Feb 21: GSC; Feb 22: GSC; Feb 23: GSC; Feb 24: J44; Feb 25: T1; Feb 26: T1; Feb 27: T1; Feb 28: J6; Mar 01: J6; Mar 02: J6; Mar 03: J6; Mar 04: J6; Mar 05: J42; Mar 06: J42; Mar 07: T3; Mar 08: T3; Mar 10: J16; Mar 11: J16; Mar 12: J16; Mar 13: J16; Mar 14: J37; Mar 15: J1; Mar 16: J37; Mar 17: J37; Mar 18: J37; Mar 19: EE7; Mar 20: EE7; Mar 21: EE7; Mar 22: EE7; Mar 23: EE7; Mar 24: EE7; Mar 25: GSD; Mar 26: S2; Mar 27: S2; Mar 28: S2; Mar 29: S2; Mar 30: GSC; Mar 31: J44; Apr 01: T1; Apr 02: T1; Apr 03: T1; Apr 04: J6; Apr 05: J6; Apr 06: J6; Apr 07: EE17; Apr 08: EE17; Apr 09: EE17; Apr 10: EE17; Apr 11: EE17; Apr 14: J16; Apr 15: J16; Apr 16: J16; Apr 17: J16; Apr 18: J37; Apr 19: J37; Apr 20: J37; Apr 21: J37; Apr 22: J37; Apr 23: EE7; Apr 24: EE7; Apr 25: EE7; Apr 26: EE7; Apr 27: J33; Apr 28: J33; Apr 29: S2; Apr 30: S2; May 01: S2; May 02: S2; May 05: S2; May 06: S2; May 07: S2; May 08: J21; May 09: J21; May 10: EE19; May 11: EE19; May 12: EE19; May 13: EE19; May 14: EE17; May 15: EE17; May 16: EE17; Jun 24: EE19; Jun 25: EE19; Jun 26: EE19
|  | 33 | S1 | #FED8E8 | 18-Apr-25 | 23-Apr-25
|  | 160 | EE32 | #F2F09E | 31-Mar-25 | 02-Apr-25
|  | 164 | EE32 | #F2F09E | 05-May-25 | 07-May-25
|  | 188 | S2 | #FED8E8 | 31-Mar-25 | 03-Apr-25
|  | 192 | S2 | #FED8E8 | 05-May-25 | 08-May-25
|  | 206 | J5 | #3598FE | 24-Feb-25 | 25-Feb-25
|  | 218 | J5 | #3598FE | 31-Mar-25 | 01-Apr-25
|  | 259 | J5 | #3598FE | 21-Feb-25 | 24-Feb-25
|  | 271 | J5 | #3598FE | 28-Mar-25 | 31-Mar-25
|  | 340 | Cx2 | #8ED973 | 10-Mar-25 | 10-Mar-25
|  | 352 | Cx2 | #8ED973 | 14-Apr-25 | 14-Apr-25
|  | 377 | EE2 | #F2F09E | 14-Feb-25 | 17-Feb-25
|  | 385 | EE2 | #F2F09E | 20-Mar-25 | 24-Mar-25
|  | 410 | EE10 | #F2F09E | 17-Mar-25 | 21-Mar-25
|  | 414 | EE10 | #F2F09E | 21-Apr-25 | 25-Apr-25
|  | 446 | J16 | #3598FE | 10-Mar-25 | 13-Mar-25
|  | 450 | J16 | #3598FE | 14-Apr-25 | 17-Apr-25
|  | 470 | J21 | #3598FE | 03-Apr-25 | 05-Apr-25
|  | 474 | J21 | #3598FE | 08-May-25 | 10-May-25
|  | 483 | J23 | #3598FE | 19-Mar-25 | 20-Mar-25
|  | 487 | J23 | #3598FE | 23-Apr-25 | 24-Apr-25
|  | 497 | J4 | #3598FE | 18-Feb-25 | 20-Feb-25
|  | 501 | J4 | #3598FE | 25-Mar-25 | 27-Mar-25
|  | 540 | J33 | #3598FE | 19-Mar-25 | 25-Mar-25
|  | 544 | J33 | #3598FE | 23-Apr-25 | 28-Apr-25
|  | 555 | J3 | #3598FE | 11-Feb-25 | 13-Feb-25
|  | 562 | J3 | #3598FE | 17-Mar-25 | 19-Mar-25
|  | 585 | J37 | #3598FE | 14-Mar-25 | 18-Mar-25
|  | 589 | J37 | #3598FE | 18-Apr-25 | 22-Apr-25
|  | 608 | J6 | #3598FE | 28-Feb-25 | 04-Mar-25
|  | 612 | J6 | #3598FE | 04-Apr-25 | 07-Apr-25
|  | 620 | J42 | #3598FE | 05-Mar-25 | 06-Mar-25
|  | 624 | J42 | #3598FE | 08-Apr-25 | 09-Apr-25
|  | 645 | J1 | #3598FE | 10-Feb-25 | 10-Feb-25
|  | 649 | J1 | #3598FE | 15-Mar-25 | 15-Mar-25
|  | 843 | EE1 | #F2F09E | 21-Feb-25 | 25-Feb-25
|  | 855 | EE1 | #F2F09E | 28-Mar-25 | 01-Apr-25
|  | 879 | GSC | #D85234 | 21-Feb-25 | 24-Feb-25
|  | 891 | GSC | #D85234 | 28-Mar-25 | 31-Mar-25
|  | 915 | GSD | #D85234 | 18-Feb-25 | 20-Feb-25
|  | 927 | GSD | #D85234 | 25-Mar-25 | 27-Mar-25
|  | 948 | J44 | #3598FE | 24-Feb-25 | 25-Feb-25
|  | 956 | J44 | #3598FE | 31-Mar-25 | 01-Apr-25
|  | 996 | T1 | #D6F2FF | 25-Feb-25 | 27-Feb-25
|  | 1008 | T1 | #D6F2FF | 01-Apr-25 | 03-Apr-25
|  | 1026 | T3 | #D6F2FF | 07-Mar-25 | 08-Mar-25
|  | 1030 | T3 | #D6F2FF | 10-Apr-25 | 11-Apr-25
|  | 1108 | EE17 | #F2F09E | 07-Apr-25 | 11-Apr-25
|  | 1112 | EE17 | #F2F09E | 12-May-25 | 16-May-25
|  | 1138 | S2 | #FED8E8 | 26-Mar-25 | 29-Mar-25
|  | 1142 | S2 | #FED8E8 | 29-Apr-25 | 02-May-25
|  | 1198 | EE7 | #F2F09E | 19-Mar-25 | 24-Mar-25
|  | 1202 | EE7 | #F2F09E | 23-Apr-25 | 26-Apr-25
|  | 1281 | EE19 | #F2F09E | 10-May-25 | 13-May-25
|  | 1285 | EE19 | #F2F09E | 24-Jun-25 | 26-Jun-25
| CELL 4 Data Hall Fitout Activities | 37 | S1 | #FED8E8 | 22-May-25 | 28-May-25 | Apr 19: J1; Apr 21: J3; Apr 22: J3; Apr 23: J3; Apr 24: EE2; Apr 25: EE2; Apr 26: EE2; Apr 28: GSD; Apr 29: GSD; Apr 30: GSD; May 01: GSC; May 02: GSC; May 03: GSC; May 04: GSC; May 05: J44; May 06: T1; May 07: T1; May 08: T1; May 09: J6; May 10: J6; May 11: J6; May 12: J6; May 13: J42; May 14: J42; May 15: T3; May 16: T3; May 17: J16; May 18: J16; May 19: J16; May 20: J16; May 21: J16; May 22: J37; May 23: J37; May 24: J37; May 25: J37; May 26: J37; May 27: J37; May 28: EE7; May 29: EE7; May 30: EE7; May 31: EE7; Jun 01: J33; Jun 02: J33; Jun 03: S2; Jun 04: S2; Jun 05: S2; Jun 06: S2; Jun 07: S2; Jun 08: S2; Jun 09: S2; Jun 10: S2; Jun 11: J21; Jun 12: J21; Jun 13: J21; Jun 16: EE17; Jun 17: EE17; Jun 18: EE17; Jun 19: EE17; Jun 20: EE17; Jul 11: EE19; Jul 12: EE19; Jul 13: EE19; Jul 14: EE19
|  | 168 | EE32 | #F2F09E | 07-Jun-25 | 10-Jun-25
|  | 196 | S2 | #FED8E8 | 07-Jun-25 | 11-Jun-25
|  | 230 | J5 | #3598FE | 05-May-25 | 06-May-25
|  | 283 | J5 | #3598FE | 01-May-25 | 05-May-25
|  | 364 | Cx2 | #8ED973 | 17-May-25 | 17-May-25
|  | 393 | EE2 | #F2F09E | 24-Apr-25 | 26-Apr-25
|  | 418 | EE10 | #F2F09E | 27-May-25 | 30-May-25
|  | 454 | J16 | #3598FE | 17-May-25 | 21-May-25
|  | 478 | J21 | #3598FE | 11-Jun-25 | 13-Jun-25
|  | 491 | J23 | #3598FE | 28-May-25 | 29-May-25
|  | 505 | J4 | #3598FE | 28-Apr-25 | 30-Apr-25
|  | 548 | J33 | #3598FE | 28-May-25 | 02-Jun-25
|  | 570 | J3 | #3598FE | 21-Apr-25 | 23-Apr-25
|  | 593 | J37 | #3598FE | 22-May-25 | 27-May-25
|  | 616 | J6 | #3598FE | 09-May-25 | 12-May-25
|  | 628 | J42 | #3598FE | 13-May-25 | 14-May-25
|  | 653 | J1 | #3598FE | 19-Apr-25 | 19-Apr-25
|  | 867 | EE1 | #F2F09E | 01-May-25 | 06-May-25
|  | 903 | GSC | #D85234 | 01-May-25 | 05-May-25
|  | 939 | GSD | #D85234 | 28-Apr-25 | 30-Apr-25
|  | 964 | J44 | #3598FE | 05-May-25 | 06-May-25
|  | 1020 | T1 | #D6F2FF | 06-May-25 | 08-May-25
|  | 1034 | T3 | #D6F2FF | 15-May-25 | 16-May-25
|  | 1116 | EE17 | #F2F09E | 16-Jun-25 | 20-Jun-25
|  | 1146 | S2 | #FED8E8 | 03-Jun-25 | 06-Jun-25
|  | 1206 | EE7 | #F2F09E | 28-May-25 | 31-May-25
|  | 1289 | EE19 | #F2F09E | 11-Jul-25 | 14-Jul-25
| CELL 4 Electrical Room | 207 | J5 | #3598FE | 24-Feb-25 | 24-Feb-25 | Feb 14: J3; Feb 15: J3; Feb 17: EE2; Feb 18: EE2; Feb 19: GSD; Feb 20: GSD; Feb 21: GSC; Feb 22: GSC; Feb 23: EE1; Feb 24: EE1; Feb 25: EE35; Feb 26: T1; Feb 27: T1; Feb 28: Cx2; Mar 03: EE53; Mar 04: EE53; Mar 05: EE53; Mar 06: EE53; Mar 07: EE29; Mar 08: EE29; Mar 09: EE29; Mar 10: EE29; Mar 11: EE29; Mar 12: EE29; Mar 13: EE29; Mar 14: EE29; Mar 15: EE29; Mar 16: EE29; Mar 17: EE29; Mar 18: EE29; Mar 19: EE29; Mar 20: EE59; Mar 21: EE59; Mar 22: EE59; Mar 23: EE59; Mar 24: EE59; Mar 25: EE59; Mar 26: GSD; Mar 27: GSD; Mar 28: GSC; Mar 29: GSC; Mar 30: EE1; Mar 31: EE1; Apr 01: EE35; Apr 02: T1; Apr 03: T1; Apr 04: Cx2; Apr 05: EE53; Apr 06: EE53; Apr 07: EE53; Apr 08: EE53; Apr 09: EE53; Apr 24: J3; Apr 25: J3; Apr 26: EE47; Apr 27: EE47; Apr 28: EE47; Apr 29: EE47; Apr 30: EE47; May 01: EE47; May 02: EE47; May 03: EE47; May 04: EE47; May 05: EE47; May 06: EE47; May 07: EE47; May 08: EE47; May 09: EE47; May 10: EE53; May 11: EE53; May 12: EE53; May 13: EE53; May 14: EE53; May 28: EE29; May 29: EE29; May 30: EE29; May 31: EE29; Jun 01: EE29; Jun 02: EE29; Jun 03: EE29; Jun 04: EE29; Jun 05: EE29; Jun 06: EE29; Jun 07: EE29; Jun 08: EE29; Jun 09: EE29; Jun 10: EE59; Jun 11: EE59; Jun 12: EE59; Jun 13: EE59; Jun 14: EE47; Jun 15: EE47; Jun 16: EE47; Jun 17: EE47; Jun 18: EE47; Jun 19: EE47; Jun 20: EE47; Jun 21: EE47; Jun 22: EE47; Jun 23: EE47; Jun 24: EE29; Jun 25: EE29; Jun 26: EE59; Jun 27: EE59; Jun 28: EE59; Jun 29: EE59; Jun 30: EE59; Jul 01: EE47; Jul 02: EE47; Jul 03: EE47; Jul 04: EE47; Jul 05: EE47; Jul 06: EE47; Jul 07: EE47; Jul 08: EE47; Jul 09: EE47; Jul 10: EE47
|  | 219 | J5 | #3598FE | 31-Mar-25 | 31-Mar-25
|  | 231 | J5 | #3598FE | 05-May-25 | 05-May-25
|  | 260 | J5 | #3598FE | 24-Feb-25 | 25-Feb-25
|  | 272 | J5 | #3598FE | 31-Mar-25 | 01-Apr-25
|  | 284 | J5 | #3598FE | 05-May-25 | 06-May-25
|  | 341 | Cx2 | #8ED973 | 28-Feb-25 | 28-Feb-25
|  | 353 | Cx2 | #8ED973 | 04-Apr-25 | 04-Apr-25
|  | 365 | Cx2 | #8ED973 | 09-May-25 | 09-May-25
|  | 378 | EE2 | #F2F09E | 17-Feb-25 | 18-Feb-25
|  | 386 | EE2 | #F2F09E | 24-Mar-25 | 25-Mar-25
|  | 394 | EE2 | #F2F09E | 26-Apr-25 | 28-Apr-25
|  | 425 | EE35 | #F2F09E | 25-Feb-25 | 26-Feb-25
|  | 433 | EE35 | #F2F09E | 01-Apr-25 | 02-Apr-25
|  | 441 | EE35 | #F2F09E | 06-May-25 | 07-May-25
|  | 509 | J4 | #3598FE | 19-Feb-25 | 22-Feb-25
|  | 513 | J4 | #3598FE | 26-Mar-25 | 29-Mar-25
|  | 517 | J4 | #3598FE | 29-Apr-25 | 02-May-25
|  | 556 | J3 | #3598FE | 14-Feb-25 | 15-Feb-25
|  | 563 | J3 | #3598FE | 20-Mar-25 | 21-Mar-25
|  | 571 | J3 | #3598FE | 24-Apr-25 | 25-Apr-25
|  | 844 | EE1 | #F2F09E | 21-Feb-25 | 24-Feb-25
|  | 856 | EE1 | #F2F09E | 28-Mar-25 | 31-Mar-25
|  | 868 | EE1 | #F2F09E | 01-May-25 | 05-May-25
|  | 880 | GSC | #D85234 | 21-Feb-25 | 22-Feb-25
|  | 892 | GSC | #D85234 | 28-Mar-25 | 29-Mar-25
|  | 904 | GSC | #D85234 | 01-May-25 | 02-May-25
|  | 916 | GSD | #D85234 | 19-Feb-25 | 20-Feb-25
|  | 928 | GSD | #D85234 | 26-Mar-25 | 27-Mar-25
|  | 940 | GSD | #D85234 | 29-Apr-25 | 30-Apr-25
|  | 997 | T1 | #D6F2FF | 26-Feb-25 | 27-Feb-25
|  | 1009 | T1 | #D6F2FF | 02-Apr-25 | 03-Apr-25
|  | 1021 | T1 | #D6F2FF | 07-May-25 | 08-May-25
|  | 1072 | EE29 | #F2F09E | 07-Mar-25 | 19-Mar-25
|  | 1074 | EE29 | #F2F09E | 28-May-25 | 09-Jun-25
|  | 1076 | EE29 | #F2F09E | 12-Jun-25 | 25-Jun-25
|  | 1100 | EE47 | #F2F09E | 26-Apr-25 | 09-May-25
|  | 1102 | EE47 | #F2F09E | 10-Jun-25 | 23-Jun-25
|  | 1104 | EE47 | #F2F09E | 26-Jun-25 | 10-Jul-25
|  | 1171 | EE53 | #F2F09E | 03-Mar-25 | 06-Mar-25
|  | 1175 | EE53 | #F2F09E | 05-Apr-25 | 09-Apr-25
|  | 1179 | EE53 | #F2F09E | 10-May-25 | 14-May-25
|  | 1253 | EE59 | #F2F09E | 20-Mar-25 | 25-Mar-25
|  | 1257 | EE59 | #F2F09E | 10-Jun-25 | 13-Jun-25
|  | 1261 | EE59 | #F2F09E | 26-Jun-25 | 30-Jun-25
| CELL 4 Mechanical Gallery | 208 | J5 | #3598FE | 14-Mar-25 | 14-Mar-25 | Feb 21: GSD; Feb 22: GSD; Feb 24: GSC; Feb 25: GSC; Feb 26: EE1; Feb 27: J44; Feb 28: J44; Mar 01: J44; Mar 02: J44; Mar 03: J44; Mar 04: J44; Mar 05: J44; Mar 06: J44; Mar 07: GPA; Mar 08: GPA; Mar 09: GPA; Mar 10: GPA; Mar 11: GPA; Mar 12: GPA; Mar 13: GPA; Mar 14: J5; Mar 15: J20; Mar 16: J20; Mar 17: T1; Mar 18: T1; Mar 19: J20; Mar 20: EE35; Mar 21: EE35; Mar 22: GBA; Mar 23: GBA; Mar 24: EE57; Mar 25: EE57; Mar 26: EE57; Mar 27: EE57; Mar 28: EE42; Mar 29: EE42; Mar 30: EE42; Mar 31: EE42; Apr 01: EE42; Apr 02: EE42; Apr 03: EE42; Apr 04: EE42; Apr 05: EE42; Apr 06: EE42; Apr 07: EE42; Apr 08: EE42; Apr 09: EE42; Apr 10: EE42; Apr 11: EE60; Apr 12: EE60; Apr 13: EE60; Apr 14: EE60; Apr 15: EE60; Apr 16: EE60; Apr 17: GPA; Apr 18: J5; Apr 19: J20; Apr 20: J20; Apr 21: T1; Apr 22: T1; Apr 23: J20; Apr 24: EE35; Apr 25: EE35; Apr 26: EE57; Apr 27: EE57; Apr 28: EE57; Apr 29: EE57; Apr 30: EE57; May 01: EE42; May 02: EE42; May 03: EE42; May 04: EE42; May 05: EE42; May 06: EE42; May 07: EE42; May 08: EE42; May 09: EE42; May 10: EE42; May 11: EE42; May 12: EE42; May 13: EE42; May 14: EE42; May 15: EE42; May 16: EE60; May 17: EE60; May 18: EE60; May 19: EE60; May 20: EE60; May 21: GPA; May 22: J5; May 23: J20; May 24: J20; May 25: J20; May 26: J20; May 27: T1; May 28: J20; May 29: EE35; May 30: EE35; May 31: EE57; Jun 01: EE57; Jun 02: EE57; Jun 03: EE57; Jun 04: EE57; Jun 05: EE42; Jun 06: EE42; Jun 07: EE42; Jun 08: EE42; Jun 09: EE42; Jun 10: EE42; Jun 11: EE42; Jun 12: EE42; Jun 13: EE42; Jun 14: EE42; Jun 15: EE42; Jun 16: EE42; Jun 17: EE42; Jun 18: EE42; Jun 19: EE42; Jun 20: EE60; Jun 21: EE60; Jun 22: EE60; Jun 23: EE60; Jun 24: EE60
|  | 220 | J5 | #3598FE | 18-Apr-25 | 18-Apr-25
|  | 232 | J5 | #3598FE | 22-May-25 | 22-May-25
|  | 261 | J5 | #3598FE | 14-Mar-25 | 15-Mar-25
|  | 273 | J5 | #3598FE | 18-Apr-25 | 19-Apr-25
|  | 285 | J5 | #3598FE | 22-May-25 | 23-May-25
|  | 342 | Cx2 | #8ED973 | 19-Mar-25 | 21-Mar-25
|  | 354 | Cx2 | #8ED973 | 23-Apr-25 | 25-Apr-25
|  | 366 | Cx2 | #8ED973 | 28-May-25 | 30-May-25
|  | 398 | GBA | #2F3452 | 20-Mar-25 | 01-Apr-25
|  | 402 | GBA | #2F3452 | 24-Apr-25 | 06-May-25
|  | 406 | GBA | #2F3452 | 29-May-25 | 09-Jun-25
|  | 426 | EE35 | #F2F09E | 20-Mar-25 | 21-Mar-25
|  | 434 | EE35 | #F2F09E | 24-Apr-25 | 25-Apr-25
|  | 442 | EE35 | #F2F09E | 29-May-25 | 30-May-25
|  | 458 | J20 | #3598FE | 15-Mar-25 | 19-Mar-25
|  | 462 | J20 | #3598FE | 19-Apr-25 | 23-Apr-25
|  | 466 | J20 | #3598FE | 23-May-25 | 28-May-25
|  | 521 | J4 | #3598FE | 12-Mar-25 | 13-Mar-25
|  | 525 | J4 | #3598FE | 16-Apr-25 | 17-Apr-25
|  | 529 | J4 | #3598FE | 20-May-25 | 21-May-25
|  | 845 | EE1 | #F2F09E | 24-Feb-25 | 26-Feb-25
|  | 857 | EE1 | #F2F09E | 31-Mar-25 | 02-Apr-25
|  | 869 | EE1 | #F2F09E | 05-May-25 | 07-May-25
|  | 881 | GSC | #D85234 | 24-Feb-25 | 25-Feb-25
|  | 893 | GSC | #D85234 | 31-Mar-25 | 01-Apr-25
|  | 905 | GSC | #D85234 | 05-May-25 | 06-May-25
|  | 917 | GSD | #D85234 | 21-Feb-25 | 22-Feb-25
|  | 929 | GSD | #D85234 | 28-Mar-25 | 29-Mar-25
|  | 941 | GSD | #D85234 | 01-May-25 | 02-May-25
|  | 949 | J44 | #3598FE | 27-Feb-25 | 06-Mar-25
|  | 957 | J44 | #3598FE | 03-Apr-25 | 09-Apr-25
|  | 965 | J44 | #3598FE | 08-May-25 | 14-May-25
|  | 969 | GPA | #2A4D4F | 07-Mar-25 | 13-Mar-25
|  | 973 | GPA | #2A4D4F | 10-Apr-25 | 17-Apr-25
|  | 977 | GPA | #2A4D4F | 15-May-25 | 21-May-25
|  | 998 | T1 | #D6F2FF | 17-Mar-25 | 18-Mar-25
|  | 1010 | T1 | #D6F2FF | 21-Apr-25 | 22-Apr-25
|  | 1022 | T1 | #D6F2FF | 27-May-25 | 27-May-25
|  | 1055 | GBB | #2F3452 | 02-Apr-25 | 10-Apr-25
|  | 1059 | GBB | #2F3452 | 07-May-25 | 15-May-25
|  | 1063 | GBB | #2F3452 | 10-Jun-25 | 19-Jun-25
|  | 1080 | EE42 | #F2F09E | 28-Mar-25 | 10-Apr-25
|  | 1084 | EE42 | #F2F09E | 01-May-25 | 15-May-25
|  | 1088 | EE42 | #F2F09E | 05-Jun-25 | 19-Jun-25
|  | 1186 | EE57 | #F2F09E | 24-Mar-25 | 27-Mar-25
|  | 1190 | EE57 | #F2F09E | 26-Apr-25 | 30-Apr-25
|  | 1194 | EE57 | #F2F09E | 31-May-25 | 04-Jun-25
|  | 1265 | EE60 | #F2F09E | 11-Apr-25 | 16-Apr-25
|  | 1269 | EE60 | #F2F09E | 16-May-25 | 20-May-25
|  | 1273 | EE60 | #F2F09E | 20-Jun-25 | 24-Jun-25
| CELL 4 Punchlist | 1125 | PU1 | #A02B93 | 10-May-25 | 21-May-25 | May 10: PU1; May 11: PU1; May 12: PU1; May 13: PU1; May 14: PU1; May 15: PU1; May 16: PU1; May 17: PU1; May 18: PU1; May 19: PU1; May 20: PU1; May 21: PU1; Jun 27: PU1; Jun 28: PU1; Jun 29: PU1; Jun 30: PU1; Jul 01: PU1; Jul 02: PU1; Jul 03: PU1; Jul 04: PU1; Jul 05: PU1; Jul 06: PU1; Jul 07: PU1; Jul 08: PU1; Jul 09: PU1; Jul 10: PU1; Jul 15: PU1; Jul 16: PU1; Jul 17: PU1; Jul 18: PU1; Jul 19: PU1; Jul 20: PU1; Jul 21: PU1; Jul 22: PU1; Jul 23: PU1; Jul 24: PU1; Jul 25: PU1
|  | 1130 | PU1 | #A02B93 | 27-Jun-25 | 10-Jul-25
|  | 1134 | PU1 | #A02B93 | 15-Jul-25 | 25-Jul-25
| COLO 3 - CELL 1 Data Hall | 26 | S1 | #FED8E8 | 22-Feb-25 | 27-Feb-25 | Jan 17: J1; Jan 20: J3; Jan 21: J3; Jan 22: J3; Jan 23: J3; Jan 24: J3; Jan 25: EE2; Jan 26: EE2; Jan 27: EE2; Jan 28: EE2; Jan 29: GSD; Jan 30: GSD; Jan 31: GSD; Feb 01: GSC; Feb 02: GSC; Feb 03: GSC; Feb 04: J44; Feb 05: T1; Feb 06: T1; Feb 07: T1; Feb 10: J6; Feb 11: J6; Feb 12: J6; Feb 13: J42; Feb 14: J42; Feb 15: T3; Feb 16: T3; Feb 17: T3; Feb 18: J16; Feb 19: J16; Feb 20: J16; Feb 21: J16; Feb 22: J37; Feb 23: J37; Feb 24: J37; Feb 25: J37; Feb 26: J37; Feb 27: EE7; Feb 28: EE7; Mar 01: EE7; Mar 02: EE7; Mar 03: EE7; Mar 04: EE7; Mar 05: J33; Mar 06: S2; Mar 07: S2; Mar 08: S2; Mar 09: S2; Mar 10: S2; Mar 11: S2; Mar 12: S2; Mar 13: S2; Mar 14: J21; Mar 15: J21; Mar 16: J21; Mar 17: J21; Mar 18: EE17; Mar 19: EE17; Mar 20: EE17; Mar 21: EE17; Mar 22: EE17; Mar 23: EE17; Mar 24: EE17; Apr 14: EE19; Apr 15: EE19; Apr 16: EE19
|  | 157 | EE32 | #F2F09E | 11-Mar-25 | 13-Mar-25
|  | 185 | S2 | #FED8E8 | 11-Mar-25 | 14-Mar-25
|  | 197 | J5 | #3598FE | 06-Feb-25 | 07-Feb-25
|  | 250 | J5 | #3598FE | 01-Feb-25 | 04-Feb-25
|  | 331 | Cx2 | #8ED973 | 18-Feb-25 | 18-Feb-25
|  | 371 | EE2 | #F2F09E | 25-Jan-25 | 28-Jan-25
|  | 407 | EE10 | #F2F09E | 25-Feb-25 | 03-Mar-25
|  | 443 | J16 | #3598FE | 18-Feb-25 | 21-Feb-25
|  | 467 | J21 | #3598FE | 14-Mar-25 | 17-Mar-25
|  | 480 | J23 | #3598FE | 27-Feb-25 | 28-Feb-25
|  | 494 | J4 | #3598FE | 29-Jan-25 | 31-Jan-25
|  | 537 | J33 | #3598FE | 27-Feb-25 | 05-Mar-25
|  | 549 | J3 | #3598FE | 20-Jan-25 | 24-Jan-25
|  | 582 | J37 | #3598FE | 22-Feb-25 | 26-Feb-25
|  | 605 | J6 | #3598FE | 10-Feb-25 | 12-Feb-25
|  | 617 | J42 | #3598FE | 13-Feb-25 | 14-Feb-25
|  | 642 | J1 | #3598FE | 17-Jan-25 | 17-Jan-25
|  | 834 | EE1 | #F2F09E | 01-Feb-25 | 05-Feb-25
|  | 870 | GSC | #D85234 | 01-Feb-25 | 04-Feb-25
|  | 906 | GSD | #D85234 | 29-Jan-25 | 31-Jan-25
|  | 942 | J44 | #3598FE | 04-Feb-25 | 05-Feb-25
|  | 987 | T1 | #D6F2FF | 05-Feb-25 | 07-Feb-25
|  | 1023 | T3 | #D6F2FF | 15-Feb-25 | 17-Feb-25
|  | 1105 | EE17 | #F2F09E | 18-Mar-25 | 24-Mar-25
|  | 1135 | S2 | #FED8E8 | 06-Mar-25 | 10-Mar-25
|  | 1195 | EE7 | #F2F09E | 27-Feb-25 | 04-Mar-25
|  | 1278 | EE19 | #F2F09E | 14-Apr-25 | 16-Apr-25
| COLO 3 - CELL 1 Electrical Room | 198 | J5 | #3598FE | 15-Feb-25 | 15-Feb-25 | Jan 25: J3; Jan 26: J3; Jan 27: J3; Jan 28: J3; Jan 29: J3; Jan 30: J3; Jan 31: EE2; Feb 01: EE2; Feb 02: EE2; Feb 03: EE2; Feb 04: EE2; Feb 05: EE2; Feb 06: EE2; Feb 07: EE2; Feb 08: EE2; Feb 09: EE2; Feb 10: EE2; Feb 11: GSD; Feb 12: GSD; Feb 13: GSC; Feb 14: GSC; Feb 15: EE1; Feb 16: J4; Feb 17: J4; Feb 18: J4; Feb 19: J4; Feb 20: J4; Feb 21: J4; Feb 22: J5; Feb 23: J5; Feb 24: J5; Feb 25: J5; Feb 26: J5; Feb 27: J5; Feb 28: J5; Mar 01: J5; Mar 02: J5; Mar 03: J5; Mar 04: J5; Mar 05: T1; Mar 06: T1; Mar 07: Cx2; Mar 10: EE53; Mar 11: EE53; Mar 12: EE53; Mar 13: EE53; Mar 14: EE53; Mar 15: EE53; Mar 17: EE29; Mar 18: EE29; Mar 19: EE29; Mar 20: EE29; Mar 21: EE29; Mar 22: EE29; Mar 23: EE29; Mar 24: EE29; Mar 25: EE29; Mar 26: EE29; Mar 27: EE29; Mar 28: EE29; Mar 29: EE29; Mar 31: EE59; Apr 01: EE59; Apr 02: EE59; Apr 03: EE59; Apr 04: EE47; Apr 05: EE47; Apr 06: EE47; Apr 07: EE47; Apr 08: EE47; Apr 09: EE47; Apr 10: EE47; Apr 11: EE47
|  | 251 | J5 | #3598FE | 22-Feb-25 | 04-Mar-25
|  | 332 | Cx2 | #8ED973 | 07-Mar-25 | 07-Mar-25
|  | 372 | EE2 | #F2F09E | 31-Jan-25 | 10-Feb-25
|  | 419 | EE35 | #F2F09E | 17-Feb-25 | 18-Feb-25
|  | 506 | J4 | #3598FE | 11-Feb-25 | 21-Feb-25
|  | 550 | J3 | #3598FE | 25-Jan-25 | 30-Jan-25
|  | 835 | EE1 | #F2F09E | 13-Feb-25 | 15-Feb-25
|  | 871 | GSC | #D85234 | 13-Feb-25 | 14-Feb-25
|  | 907 | GSD | #D85234 | 11-Feb-25 | 12-Feb-25
|  | 988 | T1 | #D6F2FF | 05-Mar-25 | 06-Mar-25
|  | 1065 | EE29 | #F2F09E | 17-Mar-25 | 29-Mar-25
|  | 1093 | EE47 | #F2F09E | 31-Mar-25 | 11-Apr-25
|  | 1168 | EE53 | #F2F09E | 10-Mar-25 | 15-Mar-25
|  | 1250 | EE59 | #F2F09E | 31-Mar-25 | 03-Apr-25
| COLO 3 - CELL 1 Mechanical Gallery | 199 | J5 | #3598FE | 06-Mar-25 | 06-Mar-25 | Feb 13: GSD; Feb 14: GSD; Feb 15: GSC; Feb 16: GSC; Feb 17: GSC; Feb 18: EE1; Feb 19: J44; Feb 20: J44; Feb 21: J44; Feb 22: J44; Feb 23: J44; Feb 24: J44; Feb 25: J44; Feb 26: GPA; Feb 27: GPA; Feb 28: GPA; Mar 01: GPA; Mar 02: GPA; Mar 03: GPA; Mar 04: GPA; Mar 05: GPA; Mar 06: J5; Mar 07: J20; Mar 08: T1; Mar 09: T1; Mar 10: T1; Mar 11: J20; Mar 12: EE35; Mar 13: EE35; Mar 14: EE57; Mar 15: EE57; Mar 16: EE57; Mar 17: EE57; Mar 18: EE57; Mar 19: EE42; Mar 20: EE42; Mar 21: EE42; Mar 22: EE42; Mar 23: EE42; Mar 24: EE42; Mar 25: EE42; Mar 26: EE42; Mar 27: EE42; Mar 28: EE42; Mar 29: EE42; Mar 30: EE42; Mar 31: EE42; Apr 01: EE42; Apr 02: EE42; Apr 03: EE60; Apr 04: EE60; Apr 05: EE60; Apr 06: EE60; Apr 07: EE60
|  | 252 | J5 | #3598FE | 06-Mar-25 | 07-Mar-25
|  | 333 | Cx2 | #8ED973 | 11-Mar-25 | 13-Mar-25
|  | 395 | GBA | #2F3452 | 12-Mar-25 | 24-Mar-25
|  | 420 | EE35 | #F2F09E | 12-Mar-25 | 13-Mar-25
|  | 455 | J20 | #3598FE | 07-Mar-25 | 11-Mar-25
|  | 518 | J4 | #3598FE | 04-Mar-25 | 05-Mar-25
|  | 836 | EE1 | #F2F09E | 15-Feb-25 | 18-Feb-25
|  | 872 | GSC | #D85234 | 15-Feb-25 | 17-Feb-25
|  | 908 | GSD | #D85234 | 13-Feb-25 | 14-Feb-25
|  | 943 | J44 | #3598FE | 19-Feb-25 | 25-Feb-25
|  | 966 | GPA | #2A4D4F | 26-Feb-25 | 05-Mar-25
|  | 989 | T1 | #D6F2FF | 08-Mar-25 | 10-Mar-25
|  | 1052 | E39 | #F2F09E | 25-Mar-25 | 02-Apr-25
|  | 1077 | EE42 | #F2F09E | 19-Mar-25 | 02-Apr-25
|  | 1183 | EE57 | #F2F09E | 14-Mar-25 | 18-Mar-25
|  | 1262 | EE60 | #F2F09E | 03-Apr-25 | 07-Apr-25
| COLO 3 - CELL 2 Data Hall | 27 | S1 | #FED8E8 | 04-Mar-25 | 08-Mar-25 | Jan 29: J1; Jan 30: J3; Jan 31: J3; Feb 01: J3; Feb 03: EE2; Feb 04: EE2; Feb 05: EE2; Feb 06: GSD; Feb 07: GSD; Feb 08: GSD; Feb 09: GSD; Feb 10: GSD; Feb 11: GSC; Feb 12: GSC; Feb 13: J44; Feb 14: T1; Feb 15: T1; Feb 16: T1; Feb 17: T1; Feb 18: J6; Feb 19: J6; Feb 20: J6; Feb 21: J42; Feb 22: J42; Feb 24: T3; Feb 25: T3; Feb 26: J16; Feb 27: J16; Feb 28: J16; Mar 01: J16; Mar 02: J16; Mar 03: J16; Mar 04: J37; Mar 05: J37; Mar 06: J37; Mar 07: J37; Mar 08: EE7; Mar 09: EE7; Mar 10: EE7; Mar 11: EE7; Mar 12: EE7; Mar 13: J33; Mar 14: S2; Mar 15: S2; Mar 16: S2; Mar 17: S2; Mar 18: S2; Mar 19: S2; Mar 20: S2; Mar 21: S2; Mar 22: S2; Mar 23: S2; Mar 24: J21; Mar 25: J21; Mar 26: J21; Mar 27: EE17; Mar 28: EE17; Mar 29: EE17; Mar 30: EE17; Mar 31: EE17; Apr 01: EE17; May 09: EE19; May 10: EE19; May 11: EE19; May 12: EE19
|  | 158 | EE32 | #F2F09E | 19-Mar-25 | 21-Mar-25
|  | 186 | S2 | #FED8E8 | 19-Mar-25 | 24-Mar-25
|  | 200 | J5 | #3598FE | 13-Feb-25 | 14-Feb-25
|  | 253 | J5 | #3598FE | 11-Feb-25 | 13-Feb-25
|  | 334 | Cx2 | #8ED973 | 26-Feb-25 | 26-Feb-25
|  | 373 | EE2 | #F2F09E | 03-Feb-25 | 05-Feb-25
|  | 408 | EE10 | #F2F09E | 06-Mar-25 | 11-Mar-25
|  | 444 | J16 | #3598FE | 26-Feb-25 | 03-Mar-25
|  | 468 | J21 | #3598FE | 24-Mar-25 | 26-Mar-25
|  | 481 | J23 | #3598FE | 08-Mar-25 | 10-Mar-25
|  | 495 | J4 | #3598FE | 06-Feb-25 | 10-Feb-25
|  | 538 | J33 | #3598FE | 08-Mar-25 | 13-Mar-25
|  | 551 | J3 | #3598FE | 30-Jan-25 | 01-Feb-25
|  | 583 | J37 | #3598FE | 04-Mar-25 | 07-Mar-25
|  | 606 | J6 | #3598FE | 18-Feb-25 | 20-Feb-25
|  | 618 | J42 | #3598FE | 21-Feb-25 | 22-Feb-25
|  | 643 | J1 | #3598FE | 29-Jan-25 | 29-Jan-25
|  | 837 | EE1 | #F2F09E | 11-Feb-25 | 14-Feb-25
|  | 873 | GSC | #D85234 | 11-Feb-25 | 13-Feb-25
|  | 909 | GSD | #D85234 | 06-Feb-25 | 10-Feb-25
|  | 944 | J44 | #3598FE | 13-Feb-25 | 14-Feb-25
|  | 990 | T1 | #D6F2FF | 14-Feb-25 | 17-Feb-25
|  | 1024 | T3 | #D6F2FF | 24-Feb-25 | 25-Feb-25
|  | 1106 | EE17 | #F2F09E | 27-Mar-25 | 01-Apr-25
|  | 1136 | S2 | #FED8E8 | 14-Mar-25 | 18-Mar-25
|  | 1196 | EE7 | #F2F09E | 08-Mar-25 | 12-Mar-25
|  | 1279 | EE19 | #F2F09E | 09-May-25 | 12-May-25
| COLO 3 - CELL 2 Electrical Room | 201 | J5 | #3598FE | 13-Feb-25 | 13-Feb-25 | Feb 03: J3; Feb 04: J3; Feb 05: EE2; Feb 06: EE2; Feb 07: GSD; Feb 08: GSD; Feb 09: GSD; Feb 10: GSD; Feb 11: GSC; Feb 12: GSC; Feb 13: EE1; Feb 14: EE35; Feb 15: T1; Feb 16: T1; Feb 17: T1; Feb 18: Cx2; Mar 17: EE53; Mar 18: EE53; Mar 19: EE53; Mar 20: EE53; Apr 14: EE29; Apr 15: EE29; Apr 16: EE29; Apr 17: EE29; Apr 18: EE29; Apr 19: EE29; Apr 20: EE29; Apr 21: EE29; Apr 22: EE29; Apr 23: EE29; Apr 24: EE29; Apr 25: EE29; Apr 26: EE59; Apr 27: EE59; Apr 28: EE59; Apr 29: EE59; Apr 30: EE59; May 01: EE47; May 02: EE47; May 03: EE47; May 04: EE47; May 05: EE47; May 06: EE47; May 07: EE47; May 08: EE47
|  | 254 | J5 | #3598FE | 13-Feb-25 | 14-Feb-25
|  | 335 | Cx2 | #8ED973 | 18-Feb-25 | 18-Feb-25
|  | 374 | EE2 | #F2F09E | 05-Feb-25 | 06-Feb-25
|  | 421 | EE35 | #F2F09E | 14-Feb-25 | 15-Feb-25
|  | 507 | J4 | #3598FE | 07-Feb-25 | 12-Feb-25
|  | 552 | J3 | #3598FE | 03-Feb-25 | 04-Feb-25
|  | 838 | EE1 | #F2F09E | 11-Feb-25 | 13-Feb-25
|  | 874 | GSC | #D85234 | 11-Feb-25 | 12-Feb-25
|  | 910 | GSD | #D85234 | 07-Feb-25 | 10-Feb-25
|  | 991 | T1 | #D6F2FF | 15-Feb-25 | 17-Feb-25
|  | 1066 | EE29 | #F2F09E | 14-Apr-25 | 25-Apr-25
|  | 1094 | EE47 | #F2F09E | 26-Apr-25 | 08-May-25
|  | 1169 | EE53 | #F2F09E | 17-Mar-25 | 20-Mar-25
|  | 1251 | EE59 | #F2F09E | 26-Apr-25 | 30-Apr-25
| COLO 3 - CELL 2 Mechanical Gallery | 202 | J5 | #3598FE | 04-Mar-25 | 04-Mar-25 | Feb 11: GSD; Feb 12: GSD; Feb 13: GSC; Feb 14: GSC; Feb 15: EE1; Feb 17: J44; Feb 18: J44; Feb 19: J44; Feb 20: J44; Feb 21: J44; Feb 22: J44; Feb 24: GPA; Feb 25: GPA; Feb 26: GPA; Feb 27: GPA; Feb 28: GPA; Mar 01: GPA; Mar 02: GPA; Mar 03: GPA; Mar 04: J5; Mar 05: J20; Mar 06: T1; Mar 07: T1; Mar 08: J20; Mar 09: Cx2; Mar 10: EE35; Mar 11: EE35; Mar 12: EE57; Mar 13: EE57; Mar 14: EE57; Mar 15: EE57; Mar 16: GBA; Mar 17: EE42; Mar 18: EE42; Mar 19: EE42; Mar 20: EE42; Mar 21: EE42; Mar 22: EE42; Mar 23: EE42; Mar 24: EE42; Mar 25: EE42; Mar 26: EE42; Mar 27: EE42; Mar 28: EE42; Mar 29: EE42; Mar 30: EE42; Mar 31: EE42; Apr 01: EE60; Apr 02: EE60; Apr 03: EE60; Apr 04: EE60
|  | 255 | J5 | #3598FE | 04-Mar-25 | 05-Mar-25
|  | 336 | Cx2 | #8ED973 | 08-Mar-25 | 11-Mar-25
|  | 396 | GBA | #2F3452 | 10-Mar-25 | 20-Mar-25
|  | 422 | EE35 | #F2F09E | 10-Mar-25 | 11-Mar-25
|  | 456 | J20 | #3598FE | 05-Mar-25 | 08-Mar-25
|  | 519 | J4 | #3598FE | 28-Feb-25 | 03-Mar-25
|  | 839 | EE1 | #F2F09E | 13-Feb-25 | 15-Feb-25
|  | 875 | GSC | #D85234 | 13-Feb-25 | 14-Feb-25
|  | 911 | GSD | #D85234 | 11-Feb-25 | 12-Feb-25
|  | 945 | J44 | #3598FE | 17-Feb-25 | 22-Feb-25
|  | 967 | GPA | #2A4D4F | 24-Feb-25 | 03-Mar-25
|  | 992 | T1 | #D6F2FF | 06-Mar-25 | 07-Mar-25
|  | 1053 | GBB | #2F3452 | 21-Mar-25 | 31-Mar-25
|  | 1078 | EE42 | #F2F09E | 17-Mar-25 | 31-Mar-25
|  | 1184 | EE57 | #F2F09E | 12-Mar-25 | 15-Mar-25
|  | 1263 | EE60 | #F2F09E | 01-Apr-25 | 04-Apr-25
| COLO 3 - CELL 2 Punchlist | 1123 | PU1 | #A02B93 | 13-May-25 | 23-May-25 | May 13: PU1; May 14: PU1; May 15: PU1; May 16: PU1; May 17: PU1; May 18: PU1; May 19: PU1; May 20: PU1; May 21: PU1; May 22: PU1; May 23: PU1
| COLO 3 - CELL 3 Data Hall | 28 | S1 | #FED8E8 | 27-Mar-25 | 01-Apr-25 | Feb 21: J1; Feb 22: J3; Feb 23: J3; Feb 24: J3; Feb 25: J3; Feb 26: EE2; Feb 27: EE2; Feb 28: EE2; Mar 03: GSD; Mar 04: GSD; Mar 05: GSD; Mar 06: GSC; Mar 07: GSC; Mar 08: J44; Mar 09: J44; Mar 10: T1; Mar 11: T1; Mar 12: T1; Mar 13: J6; Mar 14: J6; Mar 15: J6; Mar 17: J42; Mar 18: J42; Mar 19: T3; Mar 20: T3; Mar 21: J16; Mar 22: J16; Mar 23: J16; Mar 24: J16; Mar 25: J16; Mar 26: J16; Mar 27: J37; Mar 28: J37; Mar 29: J37; Mar 30: J37; Mar 31: J37; Apr 01: EE7; Apr 02: EE7; Apr 03: EE7; Apr 04: EE7; Apr 05: J33; Apr 07: S2; Apr 08: S2; Apr 09: S2; Apr 10: S2; Apr 11: S2; Apr 12: S2; Apr 13: S2; Apr 14: S2; Apr 15: S2; Apr 16: J21; Apr 17: J21; Apr 18: J21; Apr 19: EE17; Apr 20: EE17; Apr 21: EE17; Apr 22: EE17; Apr 23: EE17; Apr 24: EE17; Jun 05: EE19; Jun 06: EE19; Jun 07: EE19
|  | 159 | EE32 | #F2F09E | 11-Apr-25 | 15-Apr-25
|  | 187 | S2 | #FED8E8 | 11-Apr-25 | 16-Apr-25
|  | 203 | J5 | #3598FE | 08-Mar-25 | 10-Mar-25
|  | 256 | J5 | #3598FE | 06-Mar-25 | 08-Mar-25
|  | 337 | Cx2 | #8ED973 | 21-Mar-25 | 21-Mar-25
|  | 375 | EE2 | #F2F09E | 26-Feb-25 | 28-Feb-25
|  | 409 | EE10 | #F2F09E | 29-Mar-25 | 03-Apr-25
|  | 445 | J16 | #3598FE | 21-Mar-25 | 26-Mar-25
|  | 469 | J21 | #3598FE | 16-Apr-25 | 18-Apr-25
|  | 482 | J23 | #3598FE | 01-Apr-25 | 02-Apr-25
|  | 496 | J4 | #3598FE | 03-Mar-25 | 05-Mar-25
|  | 539 | J33 | #3598FE | 01-Apr-25 | 05-Apr-25
|  | 553 | J3 | #3598FE | 22-Feb-25 | 25-Feb-25
|  | 584 | J37 | #3598FE | 27-Mar-25 | 31-Mar-25
|  | 607 | J6 | #3598FE | 13-Mar-25 | 15-Mar-25
|  | 619 | J42 | #3598FE | 17-Mar-25 | 18-Mar-25
|  | 644 | J1 | #3598FE | 21-Feb-25 | 21-Feb-25
|  | 840 | EE1 | #F2F09E | 06-Mar-25 | 10-Mar-25
|  | 876 | GSC | #D85234 | 06-Mar-25 | 08-Mar-25
|  | 912 | GSD | #D85234 | 03-Mar-25 | 05-Mar-25
|  | 946 | J44 | #3598FE | 08-Mar-25 | 10-Mar-25
|  | 993 | T1 | #D6F2FF | 10-Mar-25 | 12-Mar-25
|  | 1025 | T3 | #D6F2FF | 19-Mar-25 | 20-Mar-25
|  | 1107 | EE17 | #F2F09E | 19-Apr-25 | 24-Apr-25
|  | 1137 | S2 | #FED8E8 | 07-Apr-25 | 10-Apr-25
|  | 1197 | EE7 | #F2F09E | 01-Apr-25 | 04-Apr-25
|  | 1280 | EE19 | #F2F09E | 05-Jun-25 | 07-Jun-25
| Electrical Room | 93 | EE28 | #F2F09E | 04-Feb-25 | 04-Feb-25 | Jan 20: J13; Jan 21: J11; Jan 22: MEP1; Jan 23: MEP1; Jan 24: JC; Jan 25: JC; Jan 27: JA; Jan 28: J13; Jan 29: J13; Jan 30: J13; Jan 31: J13; Feb 01: T2; Feb 02: T2; Feb 03: T2; Feb 04: EE28; Mar 03: EE53; Mar 04: EE53; Mar 05: EE53; Mar 06: EE53; Mar 07: EE53; Mar 08: EE53; Mar 09: EE53; Mar 10: EE53; Mar 11: EE53; Mar 12: EE29; Mar 13: EE29; Mar 14: EE29; Mar 15: EE29; Mar 16: EE29; Mar 17: EE29; Mar 18: EE29; Mar 19: EE29; Mar 20: EE29; Mar 21: EE29; Mar 22: EE29; Mar 23: EE29; Mar 24: EE29; Mar 25: EE29; Mar 26: EE29; Mar 27: EE29; Mar 28: EE29; Mar 29: EE24; Mar 30: EE24; Mar 31: EE24; Apr 01: EE24; Apr 02: EE24; Apr 03: EE24; Apr 04: EE24; Apr 05: EE24; Apr 06: EE24; Apr 07: EE24; Apr 08: EE24; Apr 09: EE24; Apr 10: EE24; Apr 11: EE24; Apr 14: EE58; Apr 15: EE58; Apr 16: EE58; Apr 17: EE58
|  | 291 | J13 | #3598FE | 28-Jan-25 | 31-Jan-25
|  | 295 | J13 | #3598FE | 20-Jan-25 | 20-Jan-25
|  | 309 | J11 | #3598FE | 21-Jan-25 | 21-Jan-25
|  | 666 | MEP1 | #D86DCD | 22-Jan-25 | 23-Jan-25
|  | 978 | T2 | #D6F2FF | 01-Feb-25 | 03-Feb-25
|  | 1064 | EE24 | #F2F09E | 29-Mar-25 | 11-Apr-25
|  | 1117 | EE29 | #F2F09E | 12-Mar-25 | 28-Mar-25
|  | 1158 | JA | #3598FE | 27-Jan-25 | 27-Jan-25
|  | 1167 | EE53 | #F2F09E | 03-Mar-25 | 11-Mar-25
|  | 1249 | EE58 | #F2F09E | 14-Apr-25 | 17-Apr-25
|  | 1290 | JC | #3598FE | 24-Jan-25 | 25-Jan-25
| Entry Room 1 | 292 | J13 | #3598FE | 30-Jan-25 | 03-Feb-25 | Jan 21: GSB; Jan 22: J11; Jan 24: MEP1; Jan 25: MEP1; Jan 27: JC; Jan 28: JC; Jan 29: JA; Jan 30: J13; Jan 31: J13; Feb 01: J13; Feb 02: J13; Feb 03: J13; Feb 04: T2; Feb 05: T2; Feb 06: J39; Feb 07: J39; Feb 08: J39; Feb 09: J39; Feb 10: J39; Feb 11: EE54; Feb 12: EE54; Feb 13: EE54; Feb 14: EE54
|  | 296 | GSB | #D85234 | 21-Jan-25 | 21-Jan-25
|  | 310 | J11 | #3598FE | 22-Jan-25 | 22-Jan-25
|  | 597 | J39 | #3598FE | 06-Feb-25 | 10-Feb-25
|  | 667 | MEP1 | #D86DCD | 24-Jan-25 | 25-Jan-25
|  | 979 | T2 | #D6F2FF | 04-Feb-25 | 05-Feb-25
|  | 1159 | JA | #3598FE | 29-Jan-25 | 29-Jan-25
|  | 1180 | EE54 | #F2F09E | 11-Feb-25 | 14-Feb-25
|  | 1291 | JC | #3598FE | 27-Jan-25 | 28-Jan-25
| Entry Room 2 | 293 | J13 | #3598FE | 01-Feb-25 | 05-Feb-25 | Jan 22: GSB; Jan 23: J11; Jan 27: MEP1; Jan 28: MEP1; Jan 29: JC; Jan 30: JC; Jan 31: JA; Feb 01: J13; Feb 02: J13; Feb 03: J13; Feb 04: J13; Feb 05: J13; Feb 06: T2; Feb 07: T2; Feb 10: J39; Feb 11: J39; Feb 12: J39; Feb 13: EE55; Feb 14: EE55; Feb 15: EE55; Feb 16: EE55; Feb 17: EE55
|  | 297 | GSB | #D85234 | 22-Jan-25 | 22-Jan-25
|  | 311 | J11 | #3598FE | 23-Jan-25 | 23-Jan-25
|  | 598 | J39 | #3598FE | 10-Feb-25 | 12-Feb-25
|  | 668 | MEP1 | #D86DCD | 27-Jan-25 | 28-Jan-25
|  | 980 | T2 | #D6F2FF | 06-Feb-25 | 07-Feb-25
|  | 1160 | JA | #3598FE | 31-Jan-25 | 31-Jan-25
|  | 1181 | EE55 | #F2F09E | 13-Feb-25 | 17-Feb-25
|  | 1292 | JC | #3598FE | 29-Jan-25 | 30-Jan-25
| FCR (Facilities Control Room) | 294 | J13 | #3598FE | 04-Feb-25 | 07-Feb-25 | Jan 23: GSB; Jan 24: J11; Jan 29: MEP1; Jan 30: MEP1; Jan 31: JC; Feb 01: JC; Feb 03: JA; Feb 04: J13; Feb 05: J13; Feb 06: J13; Feb 07: J13; Feb 10: T2; Feb 11: T2; Feb 12: J39; Feb 13: J39; Feb 14: J39; Feb 15: EE56; Feb 16: EE56; Feb 17: EE56; Feb 18: EE56; Feb 19: EE56; Feb 20: EE50; Feb 21: EE50; Feb 22: EE50; Feb 23: EE50; Feb 24: EE50; Feb 25: EE50; Feb 26: EE50; Feb 27: EE50; Feb 28: EE50; Mar 01: EE50; Mar 02: EE50; Mar 03: EE50; Mar 04: EE50; Mar 05: EE50; Mar 06: EE50; Mar 07: EE51; Mar 08: EE51; Mar 09: EE51; Mar 10: EE51; Mar 11: EE51; Mar 12: EE51; Mar 13: EE51; Mar 14: EE51; Mar 15: EE51; Mar 16: EE51; Mar 17: EE51; Mar 18: EE51; Mar 19: EE51; Mar 20: EE51; Mar 21: EE48; Mar 22: EE48; Mar 23: EE48; Mar 24: EE48; Mar 25: EE48; Mar 26: EE48; Mar 27: EE48; Mar 28: EE48; Mar 29: EE48; Mar 30: EE48; Mar 31: EE48; Apr 01: EE48; Apr 02: EE48; Apr 03: EE48; Apr 04: EE48; Apr 05: EE52; Apr 06: EE52; Apr 07: EE52; Apr 08: EE52; Apr 09: EE52; Apr 10: EE52; Apr 11: EE52; Apr 12: EE52; Apr 13: EE52; Apr 14: EE52; Apr 15: EE52; Apr 16: EE52; Apr 17: EE52; Apr 18: EE52; Apr 19: EE52; Apr 21: EE49; Apr 22: EE49; Apr 23: EE49; Apr 24: EE49; Apr 25: EE49; Apr 26: EE49; Apr 27: EE49; Apr 28: EE49; Apr 29: EE49; Apr 30: EE49; May 01: EE49; May 02: EE49; May 03: EE49; May 04: EE49; May 05: EE49
|  | 298 | GSB | #D85234 | 23-Jan-25 | 23-Jan-25
|  | 312 | J11 | #3598FE | 24-Jan-25 | 24-Jan-25
|  | 599 | J39 | #3598FE | 12-Feb-25 | 14-Feb-25
|  | 669 | MEP1 | #D86DCD | 29-Jan-25 | 30-Jan-25
|  | 981 | T2 | #D6F2FF | 10-Feb-25 | 11-Feb-25
|  | 1090 | EE44 | #F2F09E | 21-Mar-25 | 04-Apr-25
|  | 1091 | EE45 | #F2F09E | 20-Feb-25 | 06-Mar-25
|  | 1092 | EE46 | #F2F09E | 07-Mar-25 | 20-Mar-25
|  | 1118 | EE48 | #F2F09E | 21-Mar-25 | 04-Apr-25
|  | 1119 | EE49 | #F2F09E | 21-Apr-25 | 05-May-25
|  | 1120 | EE50 | #F2F09E | 20-Feb-25 | 06-Mar-25
|  | 1121 | EE51 | #F2F09E | 07-Mar-25 | 20-Mar-25
|  | 1122 | EE52 | #F2F09E | 05-Apr-25 | 19-Apr-25
|  | 1161 | JA | #3598FE | 03-Feb-25 | 03-Feb-25
|  | 1182 | EE56 | #F2F09E | 15-Feb-25 | 19-Feb-25
|  | 1293 | JC | #3598FE | 31-Jan-25 | 01-Feb-25
| Fire Riser Room | 94 | J17 | #3598FE | 18-Feb-25 | 21-Feb-25 | Jan 27: GSB; Jan 28: J11; Jan 29: J31; Jan 30: J31; Jan 31: J30; Feb 05: MEP1; Feb 06: MEP1; Feb 07: JC; Feb 08: JC; Feb 09: JC; Feb 10: JC; Feb 11: JA; Feb 12: J5; Feb 13: J5; Feb 14: T2; Feb 15: T2; Feb 18: J17; Feb 19: J17; Feb 20: J17; Feb 21: J17; Feb 22: GSA; Feb 23: GSA; Feb 24: GSA
|  | 148 | GSA | #D85234 | 22-Feb-25 | 24-Feb-25
|  | 286 | J5 | #3598FE | 12-Feb-25 | 13-Feb-25
|  | 299 | GSB | #D85234 | 27-Jan-25 | 27-Jan-25
|  | 313 | J11 | #3598FE | 28-Jan-25 | 28-Jan-25
|  | 493 | J30 | #3598FE | 31-Jan-25 | 31-Jan-25
|  | 530 | J31 | #3598FE | 29-Jan-25 | 30-Jan-25
|  | 670 | MEP1 | #D86DCD | 05-Feb-25 | 06-Feb-25
|  | 982 | T2 | #D6F2FF | 14-Feb-25 | 15-Feb-25
|  | 1162 | JA | #3598FE | 11-Feb-25 | 11-Feb-25
|  | 1294 | JC | #3598FE | 07-Feb-25 | 10-Feb-25
| Loading Dock | 287 | J5 | #3598FE | 15-Feb-25 | 17-Feb-25 | Jan 29: J31; Jan 30: J31; Jan 31: ML21; Feb 01: J31; Feb 02: J31; Feb 03: J31; Feb 04: J31; Feb 05: J31; Feb 06: J31; Feb 07: J31; Feb 08: J31; Feb 09: J31; Feb 10: J31; Feb 11: MEP1; Feb 12: MEP1; Feb 13: JC; Feb 14: JC; Feb 15: J31; Feb 16: J31; Feb 17: J31; Feb 18: T2; Feb 19: T2; Feb 20: GPB; Feb 21: GPB; Feb 22: GPB; Feb 23: GPB; Feb 24: GPB; Feb 25: GPB; Feb 26: GPB; Feb 27: GPB; Feb 28: GPB; Mar 01: GPB; Mar 02: GPB; Mar 03: GPB; Mar 04: GPB; Mar 05: GPB; Mar 06: GPB; Mar 07: GPB; Mar 08: GPB; Mar 09: GPB; Mar 10: GPB; Mar 11: EE43; Mar 12: EE43; Mar 13: EE43
|  | 300 | GSB | #D85234 | 29-Jan-25 | 29-Jan-25
|  | 314 | J11 | #3598FE | 30-Jan-25 | 30-Jan-25
|  | 531 | J31 | #3598FE | 29-Jan-25 | 15-Feb-25
|  | 532 | J31 | #3598FE | 30-Jan-25 | 17-Feb-25
|  | 671 | MEP1 | #D86DCD | 11-Feb-25 | 12-Feb-25
|  | 983 | T2 | #D6F2FF | 18-Feb-25 | 19-Feb-25
|  | 1045 | GPB | #2A4D4F | 20-Feb-25 | 10-Mar-25
|  | 1089 | EE43 | #F2F09E | 11-Mar-25 | 13-Mar-25
|  | 1157 | ML21 | #000000 | 31-Jan-25 | 31-Jan-25
|  | 1295 | JC | #3598FE | 13-Feb-25 | 14-Feb-25
| Punchlist | 39 | PU1 | #A02B93 | 06-May-25 | 09-May-25 | Jan 27: PU1; Jan 28: PU1; Jan 29: PU1; Jan 30: PU1; Jan 31: PU1; Feb 01: PU1; Feb 02: PU1; Feb 03: PU1; Feb 04: PU1; Feb 05: PU1; Feb 06: PU1; Feb 07: PU1; Feb 08: PU1; Feb 09: PU1; Feb 10: PU1; Feb 11: PU1; Feb 12: PU1; Feb 13: PU1; Feb 14: PU1; Feb 15: PU1; Feb 16: PU1; Feb 17: PU1; Feb 18: PU1; Feb 19: PU1; Feb 20: PU1; Feb 21: PU1; Feb 22: PU1; Feb 23: PU1; Feb 24: PU1; Feb 25: PU1; Feb 26: PU1; Feb 27: PU1; Feb 28: PU1; Mar 01: PU1; Mar 02: PU1; Mar 03: PU1; Mar 04: PU1; Mar 05: PU1; Mar 06: PU1; Mar 07: PU1; Mar 08: PU1; Mar 09: PU1; Mar 10: PU1; Mar 11: PU1; Mar 12: PU1; Mar 13: PU1; Mar 14: PU1; Mar 15: PU1; Mar 16: PU1; Mar 17: PU1; May 06: PU1; May 07: PU1; May 08: PU1; May 09: PU1
|  | 1150 | PU1 | #A02B93 | 27-Jan-25 | 17-Mar-25
| Restrooms & Janitor Room | 95 | J17 | #3598FE | 18-Feb-25 | 21-Feb-25 | Jan 28: GSB; Jan 29: J11; Feb 07: MEP1; Feb 08: MEP1; Feb 09: MEP1; Feb 10: MEP1; Feb 11: JC; Feb 12: JC; Feb 13: J5; Feb 14: J5; Feb 15: T2; Feb 16: T2; Feb 17: T2; Feb 18: J17; Feb 19: J17; Feb 20: J17; Feb 21: J17
|  | 288 | J5 | #3598FE | 13-Feb-25 | 14-Feb-25
|  | 301 | GSB | #D85234 | 28-Jan-25 | 28-Jan-25
|  | 315 | J11 | #3598FE | 29-Jan-25 | 29-Jan-25
|  | 672 | MEP1 | #D86DCD | 07-Feb-25 | 10-Feb-25
|  | 984 | T2 | #D6F2FF | 15-Feb-25 | 17-Feb-25
|  | 1296 | JC | #3598FE | 11-Feb-25 | 12-Feb-25
| SER (Security Equipment Room) | 289 | J5 | #3598FE | 06-Feb-25 | 07-Feb-25 | Jan 24: GSB; Jan 25: J11; Jan 31: MEP1; Feb 01: MEP1; Feb 03: JC; Feb 04: JC; Feb 05: JA; Feb 06: J5; Feb 07: J5; Feb 10: T2; Feb 11: T2; Feb 12: J39; Feb 13: J39; Feb 14: J39; Feb 15: S3; Feb 16: S3; Feb 17: S3; Feb 18: S3; Feb 19: S3
|  | 302 | GSB | #D85234 | 24-Jan-25 | 24-Jan-25
|  | 316 | J11 | #3598FE | 25-Jan-25 | 25-Jan-25
|  | 600 | J39 | #3598FE | 12-Feb-25 | 14-Feb-25
|  | 673 | MEP1 | #D86DCD | 31-Jan-25 | 01-Feb-25
|  | 985 | T2 | #D6F2FF | 10-Feb-25 | 11-Feb-25
|  | 1163 | JA | #3598FE | 05-Feb-25 | 05-Feb-25
|  | 1207 | S3 | #FED8E8 | 15-Feb-25 | 19-Feb-25
|  | 1297 | JC | #3598FE | 03-Feb-25 | 04-Feb-25
| STORAGE (High Value & Secure) Rooms | 290 | J5 | #3598FE | 26-Feb-25 | 03-Mar-25 | Jan 25: GSB; Jan 27: J11; Feb 03: MEP1; Feb 04: MEP1; Feb 05: JC; Feb 06: JC; Feb 07: J31; Feb 08: J31; Feb 09: J31; Feb 10: J31; Feb 11: J31; Feb 12: J31; Feb 13: J31; Feb 14: J31; Feb 15: J31; Feb 16: J31; Feb 17: J31; Feb 18: J31; Feb 19: J31; Feb 20: J31; Feb 21: J31; Feb 22: J31; Feb 23: J31; Feb 24: J31; Feb 25: J31; Feb 26: J5; Feb 27: J5; Feb 28: J5; Mar 01: J5; Mar 02: J5; Mar 03: J5; Mar 04: T2; Mar 05: T2; Mar 06: GSB; Mar 07: GSB; Mar 08: GSB; Mar 09: GSB; Mar 10: GSB; Mar 11: GSB; Mar 12: GSB; Mar 13: GSB; Mar 14: GSB; Mar 15: GSB; Mar 16: GSB; Mar 17: GSB
|  | 303 | GSB | #D85234 | 25-Jan-25 | 25-Jan-25
|  | 304 | GSB | #D85234 | 06-Mar-25 | 17-Mar-25
|  | 317 | J11 | #3598FE | 27-Jan-25 | 27-Jan-25
|  | 533 | J31 | #3598FE | 07-Feb-25 | 25-Feb-25
|  | 674 | MEP1 | #D86DCD | 03-Feb-25 | 04-Feb-25
|  | 986 | T2 | #D6F2FF | 04-Mar-25 | 05-Mar-25
|  | 1298 | JC | #3598FE | 05-Feb-25 | 06-Feb-25
MSFT OFCI ROJ Dates | COLO 3 | 687 | ROJ1 | #747474 | 05-Sep-24 | 05-Sep-24 | Sep 05: ROJ133; Oct 31: ROJ128; Nov 30: ROJ100; Feb 19: ROJ145; Feb 20: ROJ145; Feb 21: ROJ145; Feb 22: ROJ145; Feb 23: ROJ145; Feb 24: ROJ142; Feb 25: ROJ142; Feb 26: ROJ142; Feb 27: ROJ142; Feb 28: ROJ142; Mar 01: ROJ55; Mar 02: ROJ55; Mar 03: ROJ55; Mar 04: ROJ55; Mar 08: ROJ114; Mar 09: ROJ9; Mar 10: ROJ9; Mar 11: ROJ9; Mar 12: ROJ9; Mar 13: ROJ9
|  | 689 | ROJ3 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 690 | ROJ4 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 691 | ROJ5 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 692 | ROJ6 | #747474 | 13-Mar-25 | 13-Mar-25
|  | 695 | ROJ9 | #747474 | 09-Mar-25 | 13-Mar-25
|  | 698 | ROJ12 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 701 | ROJ15 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 704 | ROJ18 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 707 | ROJ21 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 710 | ROJ24 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 711 | ROJ25 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 716 | ROJ30 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 717 | ROJ31 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 722 | ROJ36 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 723 | ROJ37 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 728 | ROJ42 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 729 | ROJ43 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 730 | ROJ44 | #747474 | 21-Feb-25 | 21-Feb-25
|  | 733 | ROJ47 | #747474 | 19-Feb-25 | 21-Feb-25
|  | 740 | ROJ54 | #747474 | 04-Mar-25 | 04-Mar-25
|  | 741 | ROJ55 | #747474 | 28-Feb-25 | 04-Mar-25
|  | 742 | ROJ56 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 745 | ROJ59 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 754 | ROJ68 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 755 | ROJ69 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 758 | ROJ72 | #747474 | 24-Feb-25 | 24-Feb-25
|  | 759 | ROJ73 | #747474 | 20-Feb-25 | 24-Feb-25
|  | 764 | ROJ78 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 765 | ROJ79 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 776 | ROJ90 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 777 | ROJ91 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 778 | ROJ92 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 786 | ROJ100 | #747474 | 30-Nov-24 | 30-Nov-24
|  | 789 | ROJ103 | #747474 | 05-Sep-24 | 05-Sep-24
|  | 792 | ROJ106 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 797 | ROJ111 | #747474 | 28-Feb-25 | 28-Feb-25
|  | 800 | ROJ114 | #747474 | 08-Mar-25 | 08-Mar-25
|  | 803 | ROJ117 | #747474 | 05-Sep-24 | 05-Sep-24
|  | 806 | ROJ120 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 809 | ROJ123 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 812 | ROJ126 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 814 | ROJ128 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 819 | ROJ133 | #747474 | 05-Sep-24 | 05-Sep-24
|  | 826 | ROJ140 | #747474 | 23-Feb-25 | 23-Feb-25
|  | 827 | ROJ141 | #747474 | 19-Feb-25 | 23-Feb-25
|  | 828 | ROJ142 | #747474 | 24-Feb-25 | 28-Feb-25
|  | 831 | ROJ145 | #747474 | 19-Feb-25 | 23-Feb-25
| COLO 3-5 | 770 | ROJ84 | #747474 | 25-Oct-24 | 25-Oct-24 | Oct 03: ROJ125; Oct 21: ROJ85; Oct 22: ROJ85; Oct 23: ROJ85; Oct 24: ROJ85; Oct 25: ROJ85
|  | 771 | ROJ85 | #747474 | 21-Oct-24 | 25-Oct-24
|  | 811 | ROJ125 | #747474 | 03-Oct-24 | 03-Oct-24
| COLO 4 | 688 | ROJ2 | #747474 | 09-Sep-24 | 09-Sep-24 | Sep 05: ROJ131; Sep 09: ROJ2; Oct 31: ROJ135; Dec 29: ROJ99; Dec 30: ROJ28; Dec 31: ROJ28; Jan 01: ROJ28; Jan 02: ROJ28; Jan 03: ROJ28; Jan 04: ROJ28; Feb 28: ROJ109; Mar 01: ROJ52; Mar 02: ROJ52; Mar 26: ROJ146; Mar 27: ROJ146; Mar 28: ROJ146; Mar 29: ROJ146; Mar 30: ROJ146; Apr 01: ROJ10; Apr 02: ROJ10; Apr 03: ROJ10; Apr 04: ROJ10; Apr 05: ROJ10; Apr 06: ROJ75; Apr 07: ROJ75; Apr 08: ROJ75; Apr 09: ROJ75; Apr 10: ROJ75
|  | 693 | ROJ7 | #747474 | 05-Apr-25 | 05-Apr-25
|  | 696 | ROJ10 | #747474 | 01-Apr-25 | 05-Apr-25
|  | 699 | ROJ13 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 702 | ROJ16 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 705 | ROJ19 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 708 | ROJ22 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 712 | ROJ26 | #747474 | 04-Jan-25 | 04-Jan-25
|  | 714 | ROJ28 | #747474 | 29-Dec-24 | 04-Jan-25
|  | 718 | ROJ32 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 720 | ROJ34 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 724 | ROJ38 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 725 | ROJ39 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 731 | ROJ45 | #747474 | 28-Mar-25 | 28-Mar-25
|  | 734 | ROJ48 | #747474 | 26-Mar-25 | 28-Mar-25
|  | 736 | ROJ50 | #747474 | 02-Mar-25 | 02-Mar-25
|  | 738 | ROJ52 | #747474 | 28-Feb-25 | 02-Mar-25
|  | 743 | ROJ57 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 746 | ROJ60 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 748 | ROJ62 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 750 | ROJ64 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 752 | ROJ66 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 753 | ROJ67 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 760 | ROJ74 | #747474 | 10-Apr-25 | 10-Apr-25
|  | 761 | ROJ75 | #747474 | 06-Apr-25 | 10-Apr-25
|  | 766 | ROJ80 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 768 | ROJ82 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 772 | ROJ86 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 774 | ROJ88 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 781 | ROJ95 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 782 | ROJ96 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 785 | ROJ99 | #747474 | 29-Dec-24 | 29-Dec-24
|  | 787 | ROJ101 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 790 | ROJ104 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 793 | ROJ107 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 795 | ROJ109 | #747474 | 28-Feb-25 | 28-Feb-25
|  | 798 | ROJ112 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 801 | ROJ115 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 804 | ROJ118 | #747474 | 05-Sep-24 | 05-Sep-24
|  | 807 | ROJ121 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 816 | ROJ130 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 817 | ROJ131 | #747474 | 05-Sep-24 | 05-Sep-24
|  | 820 | ROJ134 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 821 | ROJ135 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 822 | ROJ136 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 824 | ROJ138 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 829 | ROJ143 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 832 | ROJ146 | #747474 | 26-Mar-25 | 30-Mar-25
| COLO 5 | 694 | ROJ8 | #747474 | 11-May-25 | 11-May-25 | Sep 05: ROJ132; Sep 16: ROJ93; Oct 30: ROJ119; Oct 31: ROJ129; Jan 28: ROJ98; Jan 29: ROJ29; Jan 30: ROJ29; Jan 31: ROJ29; Feb 01: ROJ29; Feb 02: ROJ29; Mar 26: ROJ139; Mar 27: ROJ139; Mar 28: ROJ139; Mar 29: ROJ139; Mar 30: ROJ139; Mar 31: ROJ65; Apr 01: ROJ65; Apr 02: ROJ65; Apr 03: ROJ65; Apr 04: ROJ65; Apr 20: ROJ41; Apr 25: ROJ49; Apr 26: ROJ49; Apr 27: ROJ49; Apr 28: ROJ49; Apr 29: ROJ147; Apr 30: ROJ147; May 01: ROJ147; May 02: ROJ147; May 03: ROJ147; May 04: ROJ89; May 05: ROJ89; May 06: ROJ89; May 07: ROJ89; May 11: ROJ77; May 12: ROJ77; May 13: ROJ77; May 14: ROJ77; May 15: ROJ77
|  | 697 | ROJ11 | #747474 | 11-May-25 | 11-May-25
|  | 700 | ROJ14 | #747474 | 04-Apr-25 | 04-Apr-25
|  | 703 | ROJ17 | #747474 | 30-Mar-25 | 04-Apr-25
|  | 706 | ROJ20 | #747474 | 20-Apr-25 | 20-Apr-25
|  | 709 | ROJ23 | #747474 | 20-Apr-25 | 20-Apr-25
|  | 713 | ROJ27 | #747474 | 02-Feb-25 | 02-Feb-25
|  | 715 | ROJ29 | #747474 | 28-Jan-25 | 02-Feb-25
|  | 719 | ROJ33 | #747474 | 03-May-25 | 03-May-25
|  | 721 | ROJ35 | #747474 | 29-Apr-25 | 03-May-25
|  | 726 | ROJ40 | #747474 | 20-Apr-25 | 20-Apr-25
|  | 727 | ROJ41 | #747474 | 20-Apr-25 | 20-Apr-25
|  | 732 | ROJ46 | #747474 | 28-Apr-25 | 28-Apr-25
|  | 735 | ROJ49 | #747474 | 25-Apr-25 | 28-Apr-25
|  | 737 | ROJ51 | #747474 | 03-Apr-25 | 03-Apr-25
|  | 739 | ROJ53 | #747474 | 30-Mar-25 | 03-Apr-25
|  | 744 | ROJ58 | #747474 | 04-Apr-25 | 04-Apr-25
|  | 747 | ROJ61 | #747474 | 30-Mar-25 | 04-Apr-25
|  | 749 | ROJ63 | #747474 | 04-Apr-25 | 04-Apr-25
|  | 751 | ROJ65 | #747474 | 30-Mar-25 | 04-Apr-25
|  | 756 | ROJ70 | #747474 | 03-May-25 | 03-May-25
|  | 757 | ROJ71 | #747474 | 29-Apr-25 | 03-May-25
|  | 762 | ROJ76 | #747474 | 15-May-25 | 15-May-25
|  | 763 | ROJ77 | #747474 | 11-May-25 | 15-May-25
|  | 767 | ROJ81 | #747474 | 03-May-25 | 03-May-25
|  | 769 | ROJ83 | #747474 | 29-Apr-25 | 03-May-25
|  | 773 | ROJ87 | #747474 | 07-May-25 | 07-May-25
|  | 775 | ROJ89 | #747474 | 03-May-25 | 07-May-25
|  | 779 | ROJ93 | #747474 | 16-Sep-24 | 16-Sep-24
|  | 780 | ROJ94 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 783 | ROJ97 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 784 | ROJ98 | #747474 | 28-Jan-25 | 28-Jan-25
|  | 788 | ROJ102 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 791 | ROJ105 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 794 | ROJ108 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 796 | ROJ110 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 799 | ROJ113 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 802 | ROJ116 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 805 | ROJ119 | #747474 | 30-Oct-24 | 30-Oct-24
|  | 808 | ROJ122 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 810 | ROJ124 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 813 | ROJ127 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 815 | ROJ129 | #747474 | 31-Oct-24 | 31-Oct-24
|  | 818 | ROJ132 | #747474 | 05-Sep-24 | 05-Sep-24
|  | 823 | ROJ137 | #747474 | 30-Mar-25 | 30-Mar-25
|  | 825 | ROJ139 | #747474 | 26-Mar-25 | 30-Mar-25
|  | 830 | ROJ144 | #747474 | 03-May-25 | 03-May-25
|  | 833 | ROJ147 | #747474 | 29-Apr-25 | 03-May-25
RFP / PSR | Milestone | 1151 | ML21 | #000000 | 06-May-24 | 10-May-24 | May 06: ML21; May 07: ML21; May 08: ML21; May 09: ML21; May 10: ML21; Jun 06: ML21; Jul 24: ML21; Jul 25: ML21; Jul 26: ML21; Jul 27: ML21; Jul 28: ML21; Jul 29: ML21; Jul 30: ML21; Jul 31: ML21; Aug 01: ML21; Aug 02: ML21; Aug 03: ML21; Aug 04: ML21; Aug 05: ML21; Aug 06: ML21; Aug 07: ML21; Aug 08: ML21; Aug 19: ML21; Aug 20: ML21; Aug 21: ML21; Aug 22: ML21; Aug 23: ML21; Aug 24: ML21; Aug 25: ML21; Aug 26: ML21; Aug 27: ML21; Aug 28: ML21; Aug 29: ML21; Aug 30: ML21; Aug 31: ML21; Sep 01: ML21; Sep 02: ML21; Sep 03: ML21; Sep 04: ML21; Sep 30: ML21
|  | 1152 | ML21 | #000000 | 15-Apr-24 | 02-May-24
|  | 1153 | ML21 | #000000 | 06-Jun-24 | 06-Jun-24
|  | 1154 | ML21 | #000000 | 30-Sep-24 | 30-Sep-24
|  | 1155 | ML21 | #000000 | 25-Mar-24 | 12-Apr-24
Site Prep/ Mobilization | Milestone | 249 | ML21 | #000000 | 19-Aug-24 | 04-Sep-24
|  | 1208 | ML21 | #000000 | 25-Jul-24 | 08-Aug-24
|  | 1209 | ML21 | #000000 | 24-Jul-24 | 24-Jul-24
Site Utilities | Overall | 479 | J22 | #3598FE | 23-Sep-24 | 21-Oct-24 | Sep 23: J22; Sep 24: J22; Sep 25: J22; Sep 26: J22; Sep 27: J22; Sep 28: J22; Sep 29: J22; Sep 30: J22; Oct 01: J22; Oct 02: J22; Oct 03: J22; Oct 04: J22; Oct 05: J22; Oct 06: J22; Oct 07: J22; Oct 08: J22; Oct 09: J22; Oct 10: J22; Oct 11: J22; Oct 12: J22; Oct 13: J22; Oct 14: J22; Oct 15: J22; Oct 16: J22; Oct 17: J22; Oct 18: J22; Oct 19: J22; Oct 20: J22; Oct 21: J22
|  | 581 | J36 | #3598FE | 04-Oct-24 | 18-Nov-24 | Oct 04: J36; Oct 05: J36; Oct 06: J36; Oct 07: J36; Oct 08: J36; Oct 09: J36; Oct 10: J36; Oct 11: J36; Oct 12: J36; Oct 13: J36; Oct 14: J36; Oct 15: J36; Oct 16: J36; Oct 17: J36; Oct 18: J36; Oct 19: J36; Oct 20: J36; Oct 21: J36; Oct 22: J36; Oct 23: J36; Oct 24: J36; Oct 25: J36; Oct 26: J36; Oct 27: J36; Oct 28: J36; Oct 29: J36; Oct 30: J36; Oct 31: J36; Nov 01: J36; Nov 02: J36; Nov 03: J36; Nov 04: J41; Nov 05: J41; Nov 06: J41; Nov 07: J41; Nov 08: J41; Nov 09: J43; Nov 10: J43; Nov 11: J43; Nov 12: J43; Nov 13: J43; Nov 14: J43; Nov 15: E38; Nov 16: E38; Nov 17: E38; Nov 18: E38; Nov 19: E38; Nov 20: E38; Nov 21: E38; Nov 22: E38; Nov 23: E38; Nov 24: E38; Nov 25: E38; Nov 26: E38; Nov 27: E38; Nov 28: E38; Nov 29: E38; Nov 30: E38; Dec 01: E38; Dec 02: E38; Dec 03: E38; Dec 04: E38; Dec 05: E38; Dec 06: E38; Dec 07: E38; Dec 08: E38; Dec 09: E38; Dec 10: E38; Dec 11: E38; Dec 12: E38; Dec 13: E38; Dec 14: E38; Dec 15: E38; Dec 16: E38; Dec 17: E38; Dec 18: E38; Dec 19: E38; Dec 20: E38; Dec 21: E38; Dec 22: E38; Dec 23: E38; Dec 24: E38; Dec 25: E38; Dec 26: E38; May 05: MLPP
|  | 604 | J41 | #3598FE | 04-Nov-24 | 03-Dec-24
|  | 629 | J43 | #3598FE | 09-Nov-24 | 17-Dec-24
|  | 638 | E38 | #F2F09E | 15-Nov-24 | 26-Dec-24
|  | 1035 | MLPP | #000000 | 05-May-25 | 05-May-25
| Under Building Pad | 38 | EW1 | #7E350E | 07-Nov-24 | 08-Nov-24 | Sep 18: EE37; Sep 19: EE37; Sep 20: EE37; Sep 21: EE37; Sep 22: EE37; Sep 23: EE37; Sep 24: EE37; Sep 25: EE37; Sep 26: EE37; Sep 27: EE37; Sep 28: EE37; Sep 29: EE37; Sep 30: EE37; Oct 01: EE37; Oct 02: EE37; Oct 03: EE37; Oct 04: EE37; Oct 05: EE36; Oct 06: EE36; Oct 07: EE36; Oct 08: EE36; Oct 09: EE36; Oct 10: EE36; Oct 11: EE36; Oct 12: EE36; Oct 13: EE36; Oct 14: EE36; Oct 15: EE36; Oct 16: EE36; Oct 17: EE36; Oct 18: EE36; Oct 19: EE36; Oct 20: EE36; Oct 21: EE36; Oct 22: EE36; Oct 23: EE36; Oct 24: EE36; Oct 25: EE36; Oct 26: EE36; Oct 27: EE36; Oct 28: EE36; Oct 29: EE36; Oct 30: EE36; Nov 07: EW1; Nov 08: EW1
|  | 630 | EE36 | #F2F09E | 30-Sep-24 | 30-Oct-24
|  | 631 | EE37 | #F2F09E | 18-Sep-24 | 04-Oct-24
Note on DZ5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Start First ROJ CLAYCO Took over Storage 9/2/2024 Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on EN5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Start Superstructure Start Date: 19-Sep-24 End Date: 19-Sep-24
Note on EY5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: PSR (Contract) Executed Start Date: 30-Sep-24 End Date: 30-Sep-24
Note on FJ5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Clayco Proposal Due date Start Date: 11-Oct-24 End Date: 11-Oct-24
Note on HV5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Complete U/G Utilities/ MV UG Electrical Start Date: 14-Dec-24 End Date: 14-Dec-24
Note on IH5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Complete Earthwork & U/G Site Utilities Start Date: 26-Dec-24 End Date: 26-Dec-24
Note on II5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Complete SOG Start Date: 27-Dec-24 End Date: 27-Dec-24
Note on JC5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Complete Weather Tight Start Date: 16-Jan-25 End Date: 16-Jan-25
Note on KQ5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: GC Mobilization Start Start Date: 25-Feb-25 End Date: 25-Feb-25
Note on KY5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Earthworks & U/G Utilities Start Start Date: 05-Mar-25 End Date: 05-Mar-25
Note on LB5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Complete Last ROJ Start Date: 08-Mar-25 End Date: 08-Mar-25
Note on LI5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Generator Ready for Fuel (Exterior Yard) Start Date: 15-Mar-25 End Date: 15-Mar-25
Note on MH5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Start L1 CX Start Date: 09-Apr-25 End Date: 09-Apr-25
Note on NH5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Start L2 CX (Yellow Tag) Start Date: 05-May-25 End Date: 05-May-25
Note on OL5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Start L3 CX (Green Tag) Start Date: 04-Jun-25 End Date: 04-Jun-25
Note on PN5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Complete L2 Cx (Yellow Tag) Start Date: 02-Jul-25 End Date: 02-Jul-25
Note on RE5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Complete CX L3 (Green Tag) Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on RF5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Start L4 Cx (Blue Tag) Start Date: 15-Aug-25 End Date: 15-Aug-25
Note on RK5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: RNI Start Date: 20-Aug-25 End Date: 20-Aug-25
Note on RU5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Phase 1 Security Pre-Testing Complete Start Date: 30-Aug-25 End Date: 30-Aug-25
Note on RZ5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Phase 2 Security Pre-Testing Complete Start Date: 04-Sep-25 End Date: 04-Sep-25
Note on SK5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Complete L4 Cx (Blue Tag) Start Date: 15-Sep-25 End Date: 15-Sep-25
Note on SL5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Start L5 Cx (White Tag) Start Date: 16-Sep-25 End Date: 16-Sep-25
Note on SN5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Cx L5 IST Complete (White Tag) Start Date: 18-Sep-25 End Date: 18-Sep-25
Note on SU5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Phase 3 Security Pre-Testing Complete Start Date: 25-Sep-25 End Date: 25-Sep-25
Note on SZ5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: TCO / C of O Start Date: 30-Sep-25 End Date: 30-Sep-25
Note on TA5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Substantial Completion Start Date: 01-Oct-25 End Date: 01-Oct-25
Note on TB5: Phase: Milestones Location: Admin/ COLO 3 Trade: Milestone Activity Name: Security Lockdown Start Date: 02-Oct-25 End Date: 02-Oct-25
Note on DZ60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Start First ROJ CLAYCO Took over Storage 9/2/2024 Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on EK60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Foundation Start Start Date: 16-Sep-24 End Date: 16-Sep-24
Note on GD60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Complete Foundation Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on GF60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Start Superstructure Start Date: 02-Nov-24 End Date: 02-Nov-24
Note on II60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Complete U/G Utilities/ MV UG Electric Start Date: 27-Dec-24 End Date: 27-Dec-24
Note on IM60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Complete Superstructure Start Date: 31-Dec-24 End Date: 31-Dec-24
Note on IW60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Complete SOG Start Date: 10-Jan-25 End Date: 10-Jan-25
Note on JQ60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Weather Tight Start Date: 30-Jan-25 End Date: 30-Jan-25
Note on LX60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Complete Last ROJ Start Date: 30-Mar-25 End Date: 30-Mar-25
Note on MV60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Start L1 CX Start Date: 23-Apr-25 End Date: 23-Apr-25
Note on MW60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Generator Ready for Fuel Start Date: 24-Apr-25 End Date: 24-Apr-25
Note on NH60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Complete Utility Power- On Start Date: 05-May-25 End Date: 05-May-25
Note on NI60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Start L2 CX (Yellow Tag) Start Date: 06-May-25 End Date: 06-May-25
Note on PB60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Start L3 CX Start Date: 20-Jun-25 End Date: 20-Jun-25
Note on QE60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Complete L1 Cx (All Red Tags/ ROJ) Start Date: 19-Jul-25 End Date: 19-Jul-25
Note on RE60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Complete L2 Cx (Yellow Tag) Start Date: 14-Aug-25 End Date: 14-Aug-25
Note on SO60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: CX L3 Complete Start Date: 19-Sep-25 End Date: 19-Sep-25
Note on SP60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Start L4 Cx (Blue Tag) Start Date: 20-Sep-25 End Date: 20-Sep-25
Note on ST60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Ready for Network Install Start Date: 24-Sep-25 End Date: 24-Sep-25
Note on SZ60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Phase 1 Security Pre-Testing Complete Start Date: 30-Sep-25 End Date: 30-Sep-25
Note on TD60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Phase 2 Security Pre-Testing Complete Start Date: 04-Oct-25 End Date: 04-Oct-25
Note on TP60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Complete L4 Cx (Blue Tag) Start Date: 16-Oct-25 End Date: 16-Oct-25
Note on TQ60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Start L5 Cx (White Tag) Start Date: 17-Oct-25 End Date: 17-Oct-25
Note on TT60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Cx L5 IST Complete Start Date: 20-Oct-25 End Date: 20-Oct-25
Note on TW60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Phase 3 Security Pre-Testing Complete Start Date: 23-Oct-25 End Date: 23-Oct-25
Note on UC60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: TCO / C of O Start Date: 29-Oct-25 End Date: 29-Oct-25
Note on UK60: Phase: Milestones Location: COLO 4 Trade: Milestone Activity Name: Security Lockdown Start Date: 06-Nov-25 End Date: 06-Nov-25
Note on DZ103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Start First ROJ - CLAYCO Took over Storage 9/2/2024 Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on ED103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Foundation Start Start Date: 09-Sep-24 End Date: 09-Sep-24
Note on GP103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Complete Foundation Start Date: 12-Nov-24 End Date: 12-Nov-24
Note on GR103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Start Superstructure Start Date: 14-Nov-24 End Date: 14-Nov-24
Note on IZ103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Complete U/G Utilities/ MV UG Electric Start Date: 13-Jan-25 End Date: 13-Jan-25
Note on JB103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Complete Superstructure Start Date: 15-Jan-25 End Date: 15-Jan-25
Note on JL103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Complete SOG Start Date: 25-Jan-25 End Date: 25-Jan-25
Note on KF103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Entire Building Start Date: 14-Feb-25 End Date: 14-Feb-25
Note on LY103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Complete Last ROJ Start Date: 31-Mar-25 End Date: 31-Mar-25
Note on MT103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Start L1 CX Start Date: 21-Apr-25 End Date: 21-Apr-25
Note on NH103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Complete Utility Power- On Start Date: 05-May-25 End Date: 05-May-25
Note on OH103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Generator Ready for Fuel Start Date: 31-May-25 End Date: 31-May-25
Note on OM103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Start L2 CX (Yellow Tag) Start Date: 05-Jun-25 End Date: 05-Jun-25
Note on QE103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Start L3 CX Start Date: 19-Jul-25 End Date: 19-Jul-25
Note on QV103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Complete L1 Cx (All Red Tags/ ROJ) Start Date: 05-Aug-25 End Date: 05-Aug-25
Note on RY103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Complete L2 Cx (Yellow Tag) Start Date: 03-Sep-25 End Date: 03-Sep-25
Note on TK103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: CX Level 3 Complete Start Date: 11-Oct-25 End Date: 11-Oct-25
Note on TQ103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Start L4 Cx (Blue Tag) Start Date: 17-Oct-25 End Date: 17-Oct-25
Note on UE103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Phase 1 Security Pre-Testing Complete Start Date: 31-Oct-25 End Date: 31-Oct-25
Note on UH103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Phase 2 Security Pre-Testing Complete Start Date: 03-Nov-25 End Date: 03-Nov-25
Note on UT103: Phase: Milestones Location: COLO 5 Trade: Milestone Activity Name: Complete L4 Cx (Blue Tag) Start Date: 15-Nov-25 End Date: 15-Nov-25
Note on EK145: Phase: Milestones Location: General Trade: Milestone Activity Name: GC Mobilization Finish/ Site Secured Start Date: 16-Sep-24 End Date: 16-Sep-24
Note on DK146: Phase: Milestones Location: Key Milestone Trade: Milestone Activity Name: CHI11: Construction Start Start Date: 21-Aug-24 End Date: 21-Aug-24
Note on DZ146: Phase: Milestones Location: Key Milestone Trade: Milestone Activity Name: CHI11: Building Pad Ready Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on EE146: Phase: Milestones Location: Key Milestone Trade: Milestone Activity Name: CHI11: Structure Start Start Date: 10-Sep-24 End Date: 10-Sep-24
Note on GP146: Phase: Milestones Location: Key Milestone Trade: Milestone Activity Name: CHI11: Foundations Complete Start Date: 12-Nov-24 End Date: 12-Nov-24
Note on HK146: Phase: Milestones Location: Key Milestone Trade: Milestone Activity Name: CHI11: Structure Complete Start Date: 03-Dec-24 End Date: 03-Dec-24
Note on IH146: Phase: Milestones Location: Key Milestone Trade: Milestone Activity Name: CHI11: Utilities Available to Owner (Gas Service N/A) Start Date: 26-Dec-24 End Date: 26-Dec-24
Note on IM146: Phase: Milestones Location: Key Milestone Trade: Milestone Activity Name: CHI11: Roofing Complete Start Date: 31-Dec-24 End Date: 31-Dec-24
Note on JB146: Phase: Milestones Location: Key Milestone Trade: Milestone Activity Name: CHI11: Enclosure Complete Start Date: 15-Jan-25 End Date: 15-Jan-25
Note on NH146: Phase: Milestones Location: Key Milestone Trade: Milestone Activity Name: CHI11: Electrical Service Available Start Date: 05-May-25 End Date: 05-May-25
Note on ED160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EE160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EF160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EG160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EH160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EI160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EJ160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EK160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EL160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EM160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EN160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EO160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EP160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EQ160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on ER160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on ES160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on ET160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EU160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EV160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EW160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EX160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EY160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on EZ160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on FA160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on FB160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on FC160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on FD160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on FE160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on FF160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on FG160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on FH160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (50% Complete) Start Date: 09-Sep-24 End Date: 09-Oct-24
Note on FI160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FJ160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FK160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FL160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FM160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FN160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FO160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FP160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FQ160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FR160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FS160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FT160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FU160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FV160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FW160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FX160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FY160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on FZ160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on GA160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on GB160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on GC160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on GD160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on GE160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on GF160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Foundations / Stem Walls (100% Complete) Start Date: 10-Oct-24 End Date: 02-Nov-24
Note on TA160: Phase: Milestones Location: Milestone Trade: Milestone Activity Name: Admin & COLO3-5 Fitout Complete Start Date: 01-Oct-25 End Date: 01-Oct-25
Note on CC163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- BIM Kickoff Start Date: 18-Jul-24 End Date: 18-Jul-24
Note on CD163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CE163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CF163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CG163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CH163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CI163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CJ163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CK163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CL163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CM163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CN163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CO163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CP163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CQ163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CR163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CS163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CT163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CU163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CV163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CW163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CX163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CY163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on CZ163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on DA163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on DB163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on DC163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on DD163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on DE163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on DF163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on DG163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- UG BIM Co-ordination Start Date: 19-Jul-24 End Date: 17-Aug-24
Note on EA163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EB163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EC163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on ED163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EE163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EF163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EG163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EH163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EI163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EJ163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EK163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EL163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EM163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EN163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EO163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EP163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EQ163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on ER163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on ES163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on ET163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EU163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EV163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EW163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EX163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EY163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on EZ163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on FA163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on FB163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on FC163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on FD163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on FE163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on FF163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on FG163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on FH163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on FI163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on FJ163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on FK163: Phase: BIM Location: BIM Trade: BIM Activity Name: BIM- Above ground BIM Co-ordination Start Date: 06-Sep-24 End Date: 12-Oct-24
Note on DK166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DL166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DM166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DN166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DO166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DP166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DQ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DR166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DS166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DT166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DU166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DV166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DW166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DX166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DY166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on DZ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EA166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EB166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EC166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on ED166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EE166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EF166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EG166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EH166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EI166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EJ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EK166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EL166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EM166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EN166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EO166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EP166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EQ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on ER166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on ES166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on ET166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EU166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EV166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EW166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EX166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EY166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on EZ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FA166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FB166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FC166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FD166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FE166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FF166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FG166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FH166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FI166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FJ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FK166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FL166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FM166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FN166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FO166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FP166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FQ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FR166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FS166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FT166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FU166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FV166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FW166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FX166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FY166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on FZ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GA166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GB166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GC166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GD166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GE166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GF166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GG166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GH166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GI166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GJ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GK166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GL166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GM166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GN166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GO166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GP166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GQ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GR166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GS166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GT166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GU166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GV166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GW166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GX166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GY166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on GZ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HA166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HB166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HC166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HD166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HE166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HF166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HG166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HH166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HI166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HJ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HK166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HL166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HM166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HN166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HO166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HP166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HQ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HR166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HS166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HT166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HU166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HV166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HW166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HX166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HY166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on HZ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IA166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IB166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IC166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on ID166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IE166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IF166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IG166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IH166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on II166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IJ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IK166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IL166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IM166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IN166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IO166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IP166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IQ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IR166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IS166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IT166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IU166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IV166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IW166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IX166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IY166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on IZ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JA166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JB166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JC166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JD166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JE166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JF166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JG166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JH166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JI166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JJ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JK166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JL166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JM166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JN166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JO166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JP166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JQ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JR166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JS166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JT166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JU166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JV166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JW166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JX166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JY166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on JZ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KA166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KB166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KC166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KD166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KE166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KF166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KG166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KH166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KI166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KJ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KK166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KL166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KM166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KN166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KO166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KP166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KQ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KR166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KS166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KT166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KU166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KV166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KW166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KX166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KY166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on KZ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LA166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LB166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LC166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LD166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LE166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LF166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LG166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LH166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LI166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LJ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LK166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LL166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LM166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LN166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LO166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LP166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LQ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LR166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LS166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LT166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LU166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LV166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LW166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LX166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LY166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on LZ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MA166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MB166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MC166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MD166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on ME166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MF166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MG166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MH166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MI166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MJ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MK166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on ML166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MM166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MN166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MO166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MP166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MQ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MR166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MS166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MT166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MU166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MV166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MW166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MX166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MY166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on MZ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NA166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NB166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NC166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on ND166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NE166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NF166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NG166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NH166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NI166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NJ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NK166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NL166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NM166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NN166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NO166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NP166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NQ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NR166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NS166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NT166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NU166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NV166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NW166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NX166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NY166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on NZ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OA166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OB166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OC166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OD166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OE166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OF166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OG166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OH166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OI166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OJ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OK166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OL166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OM166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on ON166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OO166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OP166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OQ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OR166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OS166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OT166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OU166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OV166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OW166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OX166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OY166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on OZ166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on PA166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on PB166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on PC166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on PD166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on PE166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on PF166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on PG166: Phase: CFCI Procurement Location: CFCI Trade: CFCI Activity Name: CFCI- MV Metering Cabinet - Substitute [43 Weeks] Start Date: 21-Aug-24 End Date: 25-Jun-25
Note on PB171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 20-Jun-25 End Date: 28-Jun-25
Note on PC171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 20-Jun-25 End Date: 28-Jun-25
Note on PD171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 20-Jun-25 End Date: 28-Jun-25
Note on PE171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 20-Jun-25 End Date: 28-Jun-25
Note on PF171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 20-Jun-25 End Date: 28-Jun-25
Note on PG171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 20-Jun-25 End Date: 28-Jun-25
Note on PH171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 20-Jun-25 End Date: 28-Jun-25
Note on PI171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 20-Jun-25 End Date: 28-Jun-25
Note on PJ171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 20-Jun-25 End Date: 28-Jun-25
Note on PL171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jun-25 End Date: 10-Jul-25
Note on PM171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jun-25 End Date: 10-Jul-25
Note on PN171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jun-25 End Date: 10-Jul-25
Note on PO171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jun-25 End Date: 10-Jul-25
Note on PP171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jun-25 End Date: 10-Jul-25
Note on PQ171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jun-25 End Date: 10-Jul-25
Note on PR171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jun-25 End Date: 10-Jul-25
Note on PS171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jun-25 End Date: 10-Jul-25
Note on PT171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jun-25 End Date: 10-Jul-25
Note on PU171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jun-25 End Date: 10-Jul-25
Note on PV171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jun-25 End Date: 10-Jul-25
Note on PW171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 11-Jul-25 End Date: 15-Jul-25
Note on PX171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 11-Jul-25 End Date: 15-Jul-25
Note on PY171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 11-Jul-25 End Date: 15-Jul-25
Note on PZ171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 11-Jul-25 End Date: 15-Jul-25
Note on QA171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 11-Jul-25 End Date: 15-Jul-25
Note on QB171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QC171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QD171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QE171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QF171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QG171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QH171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QI171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QJ171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QK171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QL171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QM171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QN171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QO171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QP171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 16-Jul-25 End Date: 30-Jul-25
Note on QQ171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 31-Jul-25 End Date: 04-Aug-25
Note on QR171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 31-Jul-25 End Date: 04-Aug-25
Note on QS171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 31-Jul-25 End Date: 04-Aug-25
Note on QT171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 31-Jul-25 End Date: 04-Aug-25
Note on QU171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 31-Jul-25 End Date: 04-Aug-25
Note on QV171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jul-25 End Date: 07-Aug-25
Note on QW171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jul-25 End Date: 07-Aug-25
Note on QX171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 30-Jul-25 End Date: 07-Aug-25
Note on QY171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 08-Aug-25 End Date: 12-Aug-25
Note on QZ171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 08-Aug-25 End Date: 12-Aug-25
Note on RA171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 08-Aug-25 End Date: 12-Aug-25
Note on RB171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 08-Aug-25 End Date: 12-Aug-25
Note on RC171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 08-Aug-25 End Date: 12-Aug-25
Note on RD171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RE171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RF171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RG171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RH171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RI171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RJ171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RK171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RL171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RM171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RN171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RO171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RP171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RQ171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RR171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 13-Aug-25 End Date: 27-Aug-25
Note on RS171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 28-Aug-25 End Date: 02-Sep-25
Note on RT171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 28-Aug-25 End Date: 02-Sep-25
Note on RU171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 28-Aug-25 End Date: 02-Sep-25
Note on RV171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 28-Aug-25 End Date: 02-Sep-25
Note on RW171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 28-Aug-25 End Date: 02-Sep-25
Note on RX171: Phase: Commissioning Location: CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 28-Aug-25 End Date: 02-Sep-25
Note on PG181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 25-Jun-25 End Date: 03-Jul-25
Note on PH181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 25-Jun-25 End Date: 03-Jul-25
Note on PI181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 25-Jun-25 End Date: 03-Jul-25
Note on PJ181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 25-Jun-25 End Date: 03-Jul-25
Note on PK181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 25-Jun-25 End Date: 03-Jul-25
Note on PL181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 25-Jun-25 End Date: 03-Jul-25
Note on PM181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 25-Jun-25 End Date: 03-Jul-25
Note on PN181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 25-Jun-25 End Date: 03-Jul-25
Note on PO181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 25-Jun-25 End Date: 03-Jul-25
Note on PS181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 07-Jul-25 End Date: 15-Jul-25
Note on PT181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 07-Jul-25 End Date: 15-Jul-25
Note on PU181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 07-Jul-25 End Date: 15-Jul-25
Note on PV181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 07-Jul-25 End Date: 15-Jul-25
Note on PW181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 07-Jul-25 End Date: 15-Jul-25
Note on PX181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 07-Jul-25 End Date: 15-Jul-25
Note on PY181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 07-Jul-25 End Date: 15-Jul-25
Note on PZ181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 07-Jul-25 End Date: 15-Jul-25
Note on QA181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 07-Jul-25 End Date: 15-Jul-25
Note on QB181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 16-Jul-25 End Date: 19-Jul-25
Note on QC181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 16-Jul-25 End Date: 19-Jul-25
Note on QD181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 16-Jul-25 End Date: 19-Jul-25
Note on QE181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 16-Jul-25 End Date: 19-Jul-25
Note on QG181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QH181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QI181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QJ181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QK181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QL181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QM181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QN181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QO181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QP181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QQ181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QR181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QS181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QT181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QU181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 21-Jul-25 End Date: 04-Aug-25
Note on QV181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 05-Aug-25 End Date: 08-Aug-25
Note on QW181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 05-Aug-25 End Date: 08-Aug-25
Note on QX181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 05-Aug-25 End Date: 08-Aug-25
Note on QY181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 05-Aug-25 End Date: 08-Aug-25
Note on QZ181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 04-Aug-25 End Date: 12-Aug-25
Note on RA181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 04-Aug-25 End Date: 12-Aug-25
Note on RB181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 04-Aug-25 End Date: 12-Aug-25
Note on RC181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 04-Aug-25 End Date: 12-Aug-25
Note on RD181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 13-Aug-25 End Date: 18-Aug-25
Note on RE181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 13-Aug-25 End Date: 18-Aug-25
Note on RF181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 13-Aug-25 End Date: 18-Aug-25
Note on RG181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 13-Aug-25 End Date: 18-Aug-25
Note on RH181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 13-Aug-25 End Date: 18-Aug-25
Note on RI181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 13-Aug-25 End Date: 18-Aug-25
Note on RJ181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RK181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RL181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RM181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RN181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RO181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RP181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RQ181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RR181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RS181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RT181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RU181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RV181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RW181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RX181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 19-Aug-25 End Date: 02-Sep-25
Note on RY181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 03-Sep-25 End Date: 08-Sep-25
Note on RZ181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 03-Sep-25 End Date: 08-Sep-25
Note on SA181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 03-Sep-25 End Date: 08-Sep-25
Note on SB181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 03-Sep-25 End Date: 08-Sep-25
Note on SC181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 03-Sep-25 End Date: 08-Sep-25
Note on SD181: Phase: Commissioning Location: CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 03-Sep-25 End Date: 08-Sep-25
Note on PF191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PG191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PH191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PI191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PJ191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PK191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PL191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PM191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PN191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PO191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PP191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PQ191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PR191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PS191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 24-Jun-25 End Date: 07-Jul-25
Note on PT191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 08-Jul-25 End Date: 18-Jul-25
Note on PU191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 08-Jul-25 End Date: 18-Jul-25
Note on PV191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 08-Jul-25 End Date: 18-Jul-25
Note on PW191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 08-Jul-25 End Date: 18-Jul-25
Note on PX191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 08-Jul-25 End Date: 18-Jul-25
Note on PY191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 08-Jul-25 End Date: 18-Jul-25
Note on PZ191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 08-Jul-25 End Date: 18-Jul-25
Note on QA191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 08-Jul-25 End Date: 18-Jul-25
Note on QB191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 08-Jul-25 End Date: 18-Jul-25
Note on QC191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 08-Jul-25 End Date: 18-Jul-25
Note on QD191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 08-Jul-25 End Date: 18-Jul-25
Note on QE191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 19-Jul-25 End Date: 24-Jul-25
Note on QF191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 19-Jul-25 End Date: 24-Jul-25
Note on QG191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 19-Jul-25 End Date: 24-Jul-25
Note on QH191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 19-Jul-25 End Date: 24-Jul-25
Note on QI191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 19-Jul-25 End Date: 24-Jul-25
Note on QJ191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 19-Jul-25 End Date: 24-Jul-25
Note on QK191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QL191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QM191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QN191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QO191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QP191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QQ191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QR191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QS191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QT191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QU191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QV191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QW191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QX191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QY191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 25-Jul-25 End Date: 08-Aug-25
Note on QZ191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 09-Aug-25 End Date: 14-Aug-25
Note on RA191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 09-Aug-25 End Date: 14-Aug-25
Note on RB191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 09-Aug-25 End Date: 14-Aug-25
Note on RC191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 09-Aug-25 End Date: 14-Aug-25
Note on RD191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 09-Aug-25 End Date: 14-Aug-25
Note on RE191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 09-Aug-25 End Date: 14-Aug-25
Note on RF191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 15-Aug-25 End Date: 25-Aug-25
Note on RG191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 15-Aug-25 End Date: 25-Aug-25
Note on RH191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 15-Aug-25 End Date: 25-Aug-25
Note on RI191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 15-Aug-25 End Date: 25-Aug-25
Note on RJ191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 15-Aug-25 End Date: 25-Aug-25
Note on RK191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 15-Aug-25 End Date: 25-Aug-25
Note on RL191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 15-Aug-25 End Date: 25-Aug-25
Note on RM191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 15-Aug-25 End Date: 25-Aug-25
Note on RN191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 15-Aug-25 End Date: 25-Aug-25
Note on RO191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 15-Aug-25 End Date: 25-Aug-25
Note on RP191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 15-Aug-25 End Date: 25-Aug-25
Note on RQ191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 26-Aug-25 End Date: 29-Aug-25
Note on RR191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 26-Aug-25 End Date: 29-Aug-25
Note on RS191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 26-Aug-25 End Date: 29-Aug-25
Note on RT191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 26-Aug-25 End Date: 29-Aug-25
Note on RU191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on RV191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on RW191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on RX191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on RY191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on RZ191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on SA191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on SB191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on SC191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on SD191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on SE191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on SF191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on SG191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on SH191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on SI191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on SJ191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on SK191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 30-Aug-25 End Date: 15-Sep-25
Note on SL191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 16-Sep-25 End Date: 19-Sep-25
Note on SM191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 16-Sep-25 End Date: 19-Sep-25
Note on SN191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 16-Sep-25 End Date: 19-Sep-25
Note on SO191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 16-Sep-25 End Date: 19-Sep-25
Note on SP191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on SQ191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on SR191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on SS191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on ST191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on SU191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on SV191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on SW191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on SX191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on SY191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on SZ191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on TA191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on TB191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on TC191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on TD191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 20-Sep-25 End Date: 04-Oct-25
Note on TF191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 06-Oct-25 End Date: 11-Oct-25
Note on TG191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 06-Oct-25 End Date: 11-Oct-25
Note on TH191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 06-Oct-25 End Date: 11-Oct-25
Note on TI191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 06-Oct-25 End Date: 11-Oct-25
Note on TJ191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 06-Oct-25 End Date: 11-Oct-25
Note on TK191: Phase: Commissioning Location: CELL 3 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 06-Oct-25 End Date: 11-Oct-25
Note on OU206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on OV206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on OW206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on OX206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on OY206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on OZ206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on PA206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on PB206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on PC206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on PD206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on PE206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on PF206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 24-Jun-25 End Date: 02-Jul-25
Note on PG206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 24-Jun-25 End Date: 02-Jul-25
Note on PH206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 24-Jun-25 End Date: 02-Jul-25
Note on PI206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 24-Jun-25 End Date: 02-Jul-25
Note on PJ206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 24-Jun-25 End Date: 02-Jul-25
Note on PK206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 24-Jun-25 End Date: 02-Jul-25
Note on PL206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 24-Jun-25 End Date: 02-Jul-25
Note on PM206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 24-Jun-25 End Date: 02-Jul-25
Note on PN206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 24-Jun-25 End Date: 02-Jul-25
Note on PO206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 03-Jul-25 End Date: 09-Jul-25
Note on PP206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 03-Jul-25 End Date: 09-Jul-25
Note on PQ206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 03-Jul-25 End Date: 09-Jul-25
Note on PR206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 03-Jul-25 End Date: 09-Jul-25
Note on PS206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 03-Jul-25 End Date: 09-Jul-25
Note on PT206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 03-Jul-25 End Date: 09-Jul-25
Note on PU206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 03-Jul-25 End Date: 09-Jul-25
Note on PV206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on PW206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on PX206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on PY206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on PZ206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on QA206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on QB206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on QC206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on QD206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on QE206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on QF206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on QG206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on QH206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on QI206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 10-Jul-25 End Date: 23-Jul-25
Note on QJ206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on QK206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on QL206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on QM206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on QN206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on QO206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on QP206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 29-Jul-25 End Date: 06-Aug-25
Note on QQ206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 29-Jul-25 End Date: 06-Aug-25
Note on QR206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 29-Jul-25 End Date: 06-Aug-25
Note on QS206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 29-Jul-25 End Date: 06-Aug-25
Note on QT206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 29-Jul-25 End Date: 06-Aug-25
Note on QU206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 29-Jul-25 End Date: 06-Aug-25
Note on QV206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 29-Jul-25 End Date: 06-Aug-25
Note on QW206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 29-Jul-25 End Date: 06-Aug-25
Note on QX206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 07-Aug-25 End Date: 11-Aug-25
Note on QY206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 07-Aug-25 End Date: 11-Aug-25
Note on QZ206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 07-Aug-25 End Date: 11-Aug-25
Note on RA206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 07-Aug-25 End Date: 11-Aug-25
Note on RB206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 07-Aug-25 End Date: 11-Aug-25
Note on RC206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RD206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RE206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RF206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RG206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RH206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RI206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RJ206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RK206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RL206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RM206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RN206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RO206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RP206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RQ206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 12-Aug-25 End Date: 26-Aug-25
Note on RR206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 27-Aug-25 End Date: 30-Aug-25
Note on RS206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on RT206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on RU206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on RV206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on RW206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on RX206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on RY206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on RZ206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on SA206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on SB206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on SC206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on SD206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on SE206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on SF206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on SG206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on SH206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 28-Aug-25 End Date: 12-Sep-25
Note on SI206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 13-Sep-25 End Date: 17-Sep-25
Note on SJ206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 13-Sep-25 End Date: 17-Sep-25
Note on SK206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 13-Sep-25 End Date: 17-Sep-25
Note on SL206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 13-Sep-25 End Date: 17-Sep-25
Note on SM206: Phase: Commissioning Location: CELL 4 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 13-Sep-25 End Date: 17-Sep-25
Note on NH221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-May-25 End Date: 28-May-25
Note on NI221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-May-25 End Date: 28-May-25
Note on NJ221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-May-25 End Date: 28-May-25
Note on NK221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-May-25 End Date: 28-May-25
Note on NL221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-May-25 End Date: 28-May-25
Note on NM221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-May-25 End Date: 28-May-25
Note on NN221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-May-25 End Date: 28-May-25
Note on NO221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-May-25 End Date: 28-May-25
Note on NP221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-May-25 End Date: 28-May-25
Note on NQ221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-May-25 End Date: 28-May-25
Note on NR221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-May-25 End Date: 07-Jun-25
Note on NS221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-May-25 End Date: 07-Jun-25
Note on NT221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-May-25 End Date: 07-Jun-25
Note on NU221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-May-25 End Date: 07-Jun-25
Note on NV221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-May-25 End Date: 07-Jun-25
Note on NW221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-May-25 End Date: 07-Jun-25
Note on NX221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-May-25 End Date: 07-Jun-25
Note on NY221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-May-25 End Date: 07-Jun-25
Note on NZ221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-May-25 End Date: 07-Jun-25
Note on OA221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-May-25 End Date: 07-Jun-25
Note on OB221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-May-25 End Date: 07-Jun-25
Note on OC221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-May-25 End Date: 07-Jun-25
Note on OD221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OE221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OF221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OG221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OH221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OI221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OJ221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OK221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OL221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OM221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on ON221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OO221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OP221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OQ221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OR221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OS221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-May-25 End Date: 18-Jun-25
Note on OT221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Install Metering Cabinet [Prior to Energization] Start Date: 12-Jun-25 End Date: 18-Jun-25
Note on OU221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Install Metering Cabinet [Prior to Energization] Start Date: 12-Jun-25 End Date: 18-Jun-25
Note on OV221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Install Metering Cabinet [Prior to Energization] Start Date: 12-Jun-25 End Date: 18-Jun-25
Note on OW221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Install Metering Cabinet [Prior to Energization] Start Date: 12-Jun-25 End Date: 18-Jun-25
Note on OX221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Install Metering Cabinet [Prior to Energization] Start Date: 12-Jun-25 End Date: 18-Jun-25
Note on OY221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Install Metering Cabinet [Prior to Energization] Start Date: 12-Jun-25 End Date: 18-Jun-25
Note on OZ221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Install Metering Cabinet [Prior to Energization] Start Date: 12-Jun-25 End Date: 18-Jun-25
Note on PA221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- EPMS Point to Point Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on PB221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- EPMS Point to Point Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on PC221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- EPMS Point to Point Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on PD221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- EPMS Point to Point Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on PE221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- EPMS Point to Point Checks Start Date: 13-Jun-25 End Date: 23-Jun-25
Note on PF221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- FTE Energizations [480v] Start Date: 24-Jun-25 End Date: 27-Jun-25
Note on PG221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- FTE Energizations [480v] Start Date: 24-Jun-25 End Date: 27-Jun-25
Note on PH221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- FTE Energizations [480v] Start Date: 24-Jun-25 End Date: 27-Jun-25
Note on PI221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- FTE Energizations [480v] Start Date: 24-Jun-25 End Date: 27-Jun-25
Note on PJ221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PK221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PL221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PM221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PN221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PO221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PP221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PQ221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PR221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PS221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PT221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PU221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PV221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PW221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PX221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PY221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on PZ221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Startups Start Date: 28-Jun-25 End Date: 14-Jul-25
Note on QA221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Loadbanking Start Date: 15-Jul-25 End Date: 18-Jul-25
Note on QB221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Loadbanking Start Date: 15-Jul-25 End Date: 18-Jul-25
Note on QC221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Loadbanking Start Date: 15-Jul-25 End Date: 18-Jul-25
Note on QD221: Phase: Commissioning Location: COLO 3 Trade: TBD Activity Name: 3Cx- Loadbanking Start Date: 15-Jul-25 End Date: 18-Jul-25
Note on RF221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RG221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RH221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RI221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RJ221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RK221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RL221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RM221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RN221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RO221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RP221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RQ221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RR221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RS221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RT221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RU221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RV221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RW221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RX221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RY221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on RZ221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on SA221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on SB221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on SC221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on SD221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on SE221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on SF221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on SG221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on SH221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on SI221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on SJ221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on SK221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 15-Aug-25 End Date: 15-Sep-25
Note on SL221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 5Cx- Testing <MSFT Duration> Start Date: 16-Sep-25 End Date: 18-Sep-25
Note on SM221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 5Cx- Testing <MSFT Duration> Start Date: 16-Sep-25 End Date: 18-Sep-25
Note on SN221: Phase: Commissioning Location: COLO 3 Trade: Microsoft Activity Name: 5Cx- Testing <MSFT Duration> Start Date: 16-Sep-25 End Date: 18-Sep-25
Note on OL232: Phase: Commissioning Location: COLO 3 - CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 04-Jun-25 End Date: 12-Jun-25
Note on OM232: Phase: Commissioning Location: COLO 3 - CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 04-Jun-25 End Date: 12-Jun-25
Note on ON232: Phase: Commissioning Location: COLO 3 - CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 04-Jun-25 End Date: 12-Jun-25
Note on OO232: Phase: Commissioning Location: COLO 3 - CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 04-Jun-25 End Date: 12-Jun-25
Note on OP232: Phase: Commissioning Location: COLO 3 - CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 04-Jun-25 End Date: 12-Jun-25
Note on OQ232: Phase: Commissioning Location: COLO 3 - CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 04-Jun-25 End Date: 12-Jun-25
Note on OR232: Phase: Commissioning Location: COLO 3 - CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 04-Jun-25 End Date: 12-Jun-25
Note on OS232: Phase: Commissioning Location: COLO 3 - CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 04-Jun-25 End Date: 12-Jun-25
Note on OT232: Phase: Commissioning Location: COLO 3 - CELL 1 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 04-Jun-25 End Date: 12-Jun-25
Note on OQ233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 09-Jun-25 End Date: 18-Jun-25
Note on OR233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 09-Jun-25 End Date: 18-Jun-25
Note on OS233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 09-Jun-25 End Date: 18-Jun-25
Note on OT233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 09-Jun-25 End Date: 18-Jun-25
Note on OU233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 09-Jun-25 End Date: 18-Jun-25
Note on OV233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 09-Jun-25 End Date: 18-Jun-25
Note on OW233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 09-Jun-25 End Date: 18-Jun-25
Note on OX233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 09-Jun-25 End Date: 18-Jun-25
Note on OY233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 09-Jun-25 End Date: 18-Jun-25
Note on OZ233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Control Power Checks Start Date: 09-Jun-25 End Date: 18-Jun-25
Note on PA233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 19-Jun-25 End Date: 27-Jun-25
Note on PB233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 19-Jun-25 End Date: 27-Jun-25
Note on PC233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 19-Jun-25 End Date: 27-Jun-25
Note on PD233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 19-Jun-25 End Date: 27-Jun-25
Note on PE233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 19-Jun-25 End Date: 27-Jun-25
Note on PF233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 19-Jun-25 End Date: 27-Jun-25
Note on PG233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 19-Jun-25 End Date: 27-Jun-25
Note on PH233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 19-Jun-25 End Date: 27-Jun-25
Note on PI233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: EPMS Point to Point Checks Start Date: 19-Jun-25 End Date: 27-Jun-25
Note on PJ233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 28-Jun-25 End Date: 02-Jul-25
Note on PK233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 28-Jun-25 End Date: 02-Jul-25
Note on PL233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 28-Jun-25 End Date: 02-Jul-25
Note on PM233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 28-Jun-25 End Date: 02-Jul-25
Note on PN233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: FTE Energizations [480v] Start Date: 28-Jun-25 End Date: 02-Jul-25
Note on PO233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on PP233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on PQ233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on PR233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on PS233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on PT233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on PU233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on PV233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on PW233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on PX233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on PY233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on PZ233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on QA233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on QB233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on QC233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on QD233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Cx Activity Name: Startups Start Date: 03-Jul-25 End Date: 18-Jul-25
Note on QE233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 19-Jul-25 End Date: 23-Jul-25
Note on QF233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 19-Jul-25 End Date: 23-Jul-25
Note on QG233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 19-Jul-25 End Date: 23-Jul-25
Note on QH233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 19-Jul-25 End Date: 23-Jul-25
Note on QI233: Phase: Commissioning Location: COLO 3 - CELL 2 Energizations & Startups (Level 3) Trade: Electrical Activity Name: Loadbanking Start Date: 19-Jul-25 End Date: 23-Jul-25
Note on NI238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NJ238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NK238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NL238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NM238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NN238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NO238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NP238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NQ238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NR238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NS238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NT238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NU238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NV238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NW238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NX238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NY238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on NZ238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on OA238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on OB238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on OC238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on OD238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on OE238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on OF238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 06-May-25 End Date: 29-May-25
Note on OH238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OI238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OJ238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OK238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OL238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OM238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on ON238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OO238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OP238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OQ238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OR238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OS238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OT238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OU238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OV238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OW238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OX238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OY238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on OZ238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on PA238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on PB238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on PC238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on PD238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on PE238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on PF238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 31-May-25 End Date: 24-Jun-25
Note on PI238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PJ238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PK238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PL238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PM238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PN238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PO238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PP238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PQ238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PR238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PS238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PT238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PU238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PV238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PW238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PX238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PY238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on PZ238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on QA238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on QB238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on QC238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on QD238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on QE238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on QF238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on QG238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on QH238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 27-Jun-25 End Date: 22-Jul-25
Note on QI238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QJ238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QK238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QL238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QM238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QN238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QO238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QP238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QQ238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QR238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QS238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QT238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QU238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QV238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QW238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QX238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QY238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on QZ238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on RA238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on RB238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on RC238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on RD238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on RE238: Phase: Commissioning Location: COLO 4 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 22-Jul-25 End Date: 14-Aug-25
Note on SP238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on SQ238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on SR238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on SS238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on ST238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on SU238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on SV238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on SW238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on SX238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on SY238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on SZ238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TA238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TB238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TC238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TD238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TE238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TF238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TG238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TH238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TI238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TJ238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TK238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TL238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TM238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TN238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TO238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TP238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 20-Sep-25 End Date: 16-Oct-25
Note on TQ238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 5Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 20-Oct-25
Note on TR238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 5Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 20-Oct-25
Note on TS238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 5Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 20-Oct-25
Note on TT238: Phase: Commissioning Location: COLO 4 Trade: Microsoft Activity Name: 5Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 20-Oct-25
Note on OM244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on ON244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on OO244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on OP244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on OQ244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on OR244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on OS244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on OT244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on OU244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on OV244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on OW244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on OX244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on OY244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on OZ244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on PA244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on PB244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on PC244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on PD244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on PE244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on PF244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on PG244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on PH244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on PI244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 05-Jun-25 End Date: 28-Jun-25
Note on PJ244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PK244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PL244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PM244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PN244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PO244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PP244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PQ244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PR244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PS244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PT244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PU244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PV244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PW244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PX244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PY244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on PZ244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 28-Jun-25 End Date: 23-Jul-25
Note on QA244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QB244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QC244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QD244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QE244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QF244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QG244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QH244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QI244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QJ244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QK244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QL244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QM244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QN244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QO244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QP244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QQ244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QR244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QS244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QT244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QU244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QV244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QW244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QX244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 15-Jul-25 End Date: 07-Aug-25
Note on QZ244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RA244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RB244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RC244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RD244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RE244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RF244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RG244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RH244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RI244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RJ244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RK244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RL244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RM244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RN244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RO244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RP244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RQ244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RR244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RS244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RT244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RU244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RV244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RW244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RX244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on RY244: Phase: Commissioning Location: COLO 5 Trade: TBD Activity Name: 2Cx- Yellow Tags Start Date: 09-Aug-25 End Date: 03-Sep-25
Note on TQ244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on TR244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on TS244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on TT244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on TU244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on TV244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on TW244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on TX244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on TY244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on TZ244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UA244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UB244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UC244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UD244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UE244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UF244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UG244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UH244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UI244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UJ244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UK244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UL244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UM244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UN244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UO244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UP244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UQ244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UR244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on US244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on UT244: Phase: Commissioning Location: COLO 5 Trade: Microsoft Activity Name: 4Cx- Testing <MSFT Duration> Start Date: 17-Oct-25 End Date: 15-Nov-25
Note on FT250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on FU250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on FV250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on FW250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on FX250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on FY250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on FZ250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on GA250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on GB250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on GC250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on GD250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on GE250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on GF250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on GG250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on GH250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on GI250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on GJ250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on GK250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Primary Steel Start Date: 21-Oct-24 End Date: 07-Nov-24
Note on GL250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Roof Panels Start Date: 08-Nov-24 End Date: 29-Nov-24
Note on GM250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Roof Panels Start Date: 08-Nov-24 End Date: 29-Nov-24
Note on GN250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Roof Panels Start Date: 08-Nov-24 End Date: 29-Nov-24
Note on GO250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Roof Panels Start Date: 08-Nov-24 End Date: 29-Nov-24
Note on GP250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Roof Panels Start Date: 08-Nov-24 End Date: 29-Nov-24
Note on GQ250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Roof Panels Start Date: 08-Nov-24 End Date: 29-Nov-24
Note on GR250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on GS250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on GT250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on GU250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on GV250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on GW250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on GX250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on GY250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on GZ250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HA250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HB250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HC250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HD250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HE250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HF250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HG250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HH250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HI250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HJ250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HK250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HL250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HM250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HN250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HO250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HP250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HQ250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HR250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HS250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HT250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HU250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HV250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 14-Nov-24 End Date: 14-Dec-24
Note on HX250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 16-Dec-24 End Date: 27-Dec-24
Note on HY250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 16-Dec-24 End Date: 27-Dec-24
Note on HZ250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 16-Dec-24 End Date: 27-Dec-24
Note on IA250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 16-Dec-24 End Date: 27-Dec-24
Note on IB250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 16-Dec-24 End Date: 27-Dec-24
Note on IC250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 16-Dec-24 End Date: 27-Dec-24
Note on ID250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 16-Dec-24 End Date: 27-Dec-24
Note on IE250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 16-Dec-24 End Date: 27-Dec-24
Note on IF250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 16-Dec-24 End Date: 27-Dec-24
Note on IG250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 16-Dec-24 End Date: 27-Dec-24
Note on IH250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 16-Dec-24 End Date: 27-Dec-24
Note on II250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 16-Dec-24 End Date: 27-Dec-24
Note on IJ250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Louvers & Dampers Start Date: 16-Dec-24 End Date: 06-Jan-25
Note on IK250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Louvers & Dampers Start Date: 16-Dec-24 End Date: 06-Jan-25
Note on IL250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IM250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IN250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IO250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IP250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IQ250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IR250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IS250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IT250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IU250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IV250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IW250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IX250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IY250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on IZ250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on JA250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on JB250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on JC250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Plumbing Activity Name: Weather Days Start Date: 30-Dec-24 End Date: 16-Jan-25
Note on JD250: Phase: Core & Shell Location: Admin/ COLO 3 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 30-Dec-24 End Date: 17-Jan-25
Note on GF258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GG258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GH258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GI258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GJ258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GK258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GL258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GM258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GN258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GO258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GP258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GQ258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GR258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GS258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GT258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GU258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GV258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GW258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GX258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Primary Steel Start Date: 02-Nov-24 End Date: 20-Nov-24
Note on GY258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Roof Panels Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on GZ258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Roof Panels Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on HA258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Roof Panels Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on HB258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Roof Panels Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on HC258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Roof Panels Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on HD258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Roof Panels Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on HE258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Roof Panels Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on HF258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Roof Panels Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on HG258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Roof Panels Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on HH258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Roof Panels Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on HI258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Roof Panels Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on HJ258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Roof Panels Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on HK258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Roof Panels Start Date: 21-Nov-24 End Date: 14-Dec-24
Note on HL258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HM258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HN258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HO258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HP258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HQ258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HR258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HS258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HT258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HU258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HV258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HW258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HX258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HY258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on HZ258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on IA258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on IB258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on IC258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on ID258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on IE258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on IF258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on IG258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on IH258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on II258: Phase: Core & Shell Location: COLO 4 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 04-Dec-24 End Date: 27-Dec-24
Note on IJ258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Exterior Wall Panels Start Date: 16-Dec-24 End Date: 31-Dec-24
Note on IK258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Exterior Wall Panels Start Date: 16-Dec-24 End Date: 31-Dec-24
Note on IL258: Phase: Core & Shell Location: COLO 4 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 30-Dec-24 End Date: 10-Jan-25
Note on IM258: Phase: Core & Shell Location: COLO 4 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 30-Dec-24 End Date: 10-Jan-25
Note on IN258: Phase: Core & Shell Location: COLO 4 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 30-Dec-24 End Date: 10-Jan-25
Note on IO258: Phase: Core & Shell Location: COLO 4 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 30-Dec-24 End Date: 10-Jan-25
Note on IP258: Phase: Core & Shell Location: COLO 4 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 30-Dec-24 End Date: 10-Jan-25
Note on IQ258: Phase: Core & Shell Location: COLO 4 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 30-Dec-24 End Date: 10-Jan-25
Note on IR258: Phase: Core & Shell Location: COLO 4 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 30-Dec-24 End Date: 10-Jan-25
Note on IS258: Phase: Core & Shell Location: COLO 4 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 30-Dec-24 End Date: 10-Jan-25
Note on IT258: Phase: Core & Shell Location: COLO 4 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 30-Dec-24 End Date: 10-Jan-25
Note on IU258: Phase: Core & Shell Location: COLO 4 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 30-Dec-24 End Date: 10-Jan-25
Note on IV258: Phase: Core & Shell Location: COLO 4 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 30-Dec-24 End Date: 10-Jan-25
Note on IW258: Phase: Core & Shell Location: COLO 4 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 30-Dec-24 End Date: 10-Jan-25
Note on IX258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on IY258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on IZ258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JA258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JB258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JC258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JD258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JE258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JF258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JG258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JH258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JI258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JJ258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JK258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JL258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JM258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JN258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JO258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JP258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on JQ258: Phase: Core & Shell Location: COLO 4 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 11-Jan-25 End Date: 30-Jan-25
Note on GR265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on GS265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on GT265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on GU265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on GV265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on GW265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on GX265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on GY265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on GZ265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on HA265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on HB265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on HC265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on HD265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on HE265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on HF265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on HG265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on HH265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on HI265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on HJ265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on HK265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Primary Steel Start Date: 14-Nov-24 End Date: 03-Dec-24
Note on HL265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Roof Panels Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on HM265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Roof Panels Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on HN265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Roof Panels Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on HO265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Roof Panels Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on HP265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Roof Panels Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on HQ265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Roof Panels Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on HR265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Roof Panels Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on HS265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Roof Panels Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on HT265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Roof Panels Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on HU265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Roof Panels Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on HV265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Roof Panels Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on HW265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Roof Panels Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on HX265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Roof Panels Start Date: 04-Dec-24 End Date: 31-Dec-24
Note on HY265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on HZ265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IA265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IB265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IC265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on ID265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IE265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IF265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IG265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IH265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on II265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IJ265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IK265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IL265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IM265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IN265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IO265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IP265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IQ265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IR265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IS265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IT265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IU265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IV265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IW265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IX265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IY265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on IZ265: Phase: Core & Shell Location: COLO 5 Trade: Plumbing Activity Name: UG MEP Work (Plumbing) Start Date: 17-Dec-24 End Date: 13-Jan-25
Note on JA265: Phase: Core & Shell Location: COLO 5 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 14-Jan-25 End Date: 25-Jan-25
Note on JB265: Phase: Core & Shell Location: COLO 5 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 14-Jan-25 End Date: 25-Jan-25
Note on JC265: Phase: Core & Shell Location: COLO 5 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 14-Jan-25 End Date: 25-Jan-25
Note on JD265: Phase: Core & Shell Location: COLO 5 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 14-Jan-25 End Date: 25-Jan-25
Note on JE265: Phase: Core & Shell Location: COLO 5 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 14-Jan-25 End Date: 25-Jan-25
Note on JF265: Phase: Core & Shell Location: COLO 5 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 14-Jan-25 End Date: 25-Jan-25
Note on JG265: Phase: Core & Shell Location: COLO 5 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 14-Jan-25 End Date: 25-Jan-25
Note on JH265: Phase: Core & Shell Location: COLO 5 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 14-Jan-25 End Date: 25-Jan-25
Note on JI265: Phase: Core & Shell Location: COLO 5 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 14-Jan-25 End Date: 25-Jan-25
Note on JJ265: Phase: Core & Shell Location: COLO 5 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 14-Jan-25 End Date: 25-Jan-25
Note on JK265: Phase: Core & Shell Location: COLO 5 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 14-Jan-25 End Date: 25-Jan-25
Note on JL265: Phase: Core & Shell Location: COLO 5 Trade: Concrete Activity Name: Prep / Place SOG Start Date: 14-Jan-25 End Date: 25-Jan-25
Note on JN265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on JO265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on JP265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on JQ265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on JR265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on JS265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on JT265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on JU265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on JV265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on JW265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on JX265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on JY265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on JZ265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on KA265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on KB265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on KC265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on KD265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on KE265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on KF265: Phase: Core & Shell Location: COLO 5 Trade: Framing Activity Name: Install Misc. Metals (Trims, Gutters, Catwalks) Start Date: 27-Jan-25 End Date: 14-Feb-25
Note on CA272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CB272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CC272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CD272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CE272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CF272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CG272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CH272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CI272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CJ272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CK272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CL272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CM272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CN272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CO272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CP272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CQ272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CR272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CS272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CT272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CU272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CV272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CW272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CX272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CY272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on CZ272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DA272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DB272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DC272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DD272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DE272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DF272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DG272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DH272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DI272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DJ272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DK272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DL272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DM272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DN272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DO272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DP272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DQ272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DR272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DS272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DT272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DU272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DV272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DW272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DX272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DY272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on DZ272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EA272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EB272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EC272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on ED272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EE272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EF272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EG272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EH272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EI272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EJ272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EK272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EL272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EM272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EN272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EO272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EP272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EQ272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on ER272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on ES272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on ET272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EU272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on EV272: Phase: Early Awards Location: Milestone Trade: Milestone Activity Name: PROCUREMENT- Buyouts & Early Procurement Start Date: 16-Jul-24 End Date: 27-Sep-24
Note on JD274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 17-Jan-25 End Date: 28-Jan-25
Note on JE274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 17-Jan-25 End Date: 28-Jan-25
Note on JF274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 17-Jan-25 End Date: 28-Jan-25
Note on JG274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 17-Jan-25 End Date: 28-Jan-25
Note on JH274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 17-Jan-25 End Date: 28-Jan-25
Note on JI274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 17-Jan-25 End Date: 28-Jan-25
Note on JJ274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 17-Jan-25 End Date: 28-Jan-25
Note on JK274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 17-Jan-25 End Date: 28-Jan-25
Note on JL274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 17-Jan-25 End Date: 28-Jan-25
Note on JM274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 17-Jan-25 End Date: 28-Jan-25
Note on JN274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 17-Jan-25 End Date: 28-Jan-25
Note on JO274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 17-Jan-25 End Date: 28-Jan-25
Note on JP274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 29-Jan-25 End Date: 07-Feb-25
Note on JQ274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 29-Jan-25 End Date: 07-Feb-25
Note on JR274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 29-Jan-25 End Date: 07-Feb-25
Note on JS274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 29-Jan-25 End Date: 07-Feb-25
Note on JT274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 29-Jan-25 End Date: 07-Feb-25
Note on JU274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 29-Jan-25 End Date: 07-Feb-25
Note on JV274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 29-Jan-25 End Date: 07-Feb-25
Note on JW274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 29-Jan-25 End Date: 07-Feb-25
Note on JX274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 29-Jan-25 End Date: 07-Feb-25
Note on JY274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 29-Jan-25 End Date: 07-Feb-25
Note on KB274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 10-Feb-25 End Date: 19-Feb-25
Note on KC274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 10-Feb-25 End Date: 19-Feb-25
Note on KD274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 10-Feb-25 End Date: 19-Feb-25
Note on KE274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 10-Feb-25 End Date: 19-Feb-25
Note on KF274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 10-Feb-25 End Date: 19-Feb-25
Note on KG274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 10-Feb-25 End Date: 19-Feb-25
Note on KH274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 10-Feb-25 End Date: 19-Feb-25
Note on KI274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 10-Feb-25 End Date: 19-Feb-25
Note on KJ274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 10-Feb-25 End Date: 19-Feb-25
Note on KK274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 10-Feb-25 End Date: 19-Feb-25
Note on KL274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 20-Feb-25 End Date: 03-Mar-25
Note on KM274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 20-Feb-25 End Date: 03-Mar-25
Note on KN274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 20-Feb-25 End Date: 03-Mar-25
Note on KO274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 20-Feb-25 End Date: 03-Mar-25
Note on KP274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 20-Feb-25 End Date: 03-Mar-25
Note on KQ274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 20-Feb-25 End Date: 03-Mar-25
Note on KR274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 20-Feb-25 End Date: 03-Mar-25
Note on KS274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 20-Feb-25 End Date: 03-Mar-25
Note on KT274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 20-Feb-25 End Date: 03-Mar-25
Note on KU274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 20-Feb-25 End Date: 03-Mar-25
Note on KV274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 20-Feb-25 End Date: 03-Mar-25
Note on KW274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 20-Feb-25 End Date: 03-Mar-25
Note on KX274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Install XFMs Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on KY274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Install XFMs Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on KZ274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Install XFMs Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on LA274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Install XFMs Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on LB274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Install XFMs Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on LC274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Install XFMs Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on LD274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Install XFMs Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on LE274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Install XFMs Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on LF274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Install XFMs Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on LG274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Install XFMs Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on LH274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Install XFMs Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on LI274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: Install XFMs Start Date: 04-Mar-25 End Date: 15-Mar-25
Note on MX274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on MY274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on MZ274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NA274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NB274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NC274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on ND274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NE274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NF274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NG274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NH274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NI274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NJ274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NK274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NL274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NM274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NN274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NO274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NP274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NQ274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NR274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NS274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NT274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NU274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NV274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NW274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NX274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NY274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NZ274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on OD274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 03-Jun-25
Note on OE274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 03-Jun-25
Note on OF274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 03-Jun-25
Note on OG274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 03-Jun-25
Note on OH274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 03-Jun-25
Note on OI274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 03-Jun-25
Note on OJ274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 03-Jun-25
Note on OK274: Phase: Electrical Yard Location: Admin/ COLO 3 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 03-Jun-25
Note on KM286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 21-Feb-25 End Date: 04-Mar-25
Note on KN286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 21-Feb-25 End Date: 04-Mar-25
Note on KO286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 21-Feb-25 End Date: 04-Mar-25
Note on KP286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 21-Feb-25 End Date: 04-Mar-25
Note on KQ286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 21-Feb-25 End Date: 04-Mar-25
Note on KR286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 21-Feb-25 End Date: 04-Mar-25
Note on KS286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 21-Feb-25 End Date: 04-Mar-25
Note on KT286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 21-Feb-25 End Date: 04-Mar-25
Note on KU286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 21-Feb-25 End Date: 04-Mar-25
Note on KV286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 21-Feb-25 End Date: 04-Mar-25
Note on KW286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 21-Feb-25 End Date: 04-Mar-25
Note on KX286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 21-Feb-25 End Date: 04-Mar-25
Note on KY286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 05-Mar-25 End Date: 14-Mar-25
Note on KZ286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 05-Mar-25 End Date: 14-Mar-25
Note on LA286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 05-Mar-25 End Date: 14-Mar-25
Note on LB286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 05-Mar-25 End Date: 14-Mar-25
Note on LC286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 05-Mar-25 End Date: 14-Mar-25
Note on LD286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 05-Mar-25 End Date: 14-Mar-25
Note on LE286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 05-Mar-25 End Date: 14-Mar-25
Note on LF286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 05-Mar-25 End Date: 14-Mar-25
Note on LG286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 05-Mar-25 End Date: 14-Mar-25
Note on LH286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 05-Mar-25 End Date: 14-Mar-25
Note on LI286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 15-Mar-25 End Date: 26-Mar-25
Note on LJ286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 15-Mar-25 End Date: 26-Mar-25
Note on LK286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 15-Mar-25 End Date: 26-Mar-25
Note on LL286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 15-Mar-25 End Date: 26-Mar-25
Note on LM286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 15-Mar-25 End Date: 26-Mar-25
Note on LN286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 15-Mar-25 End Date: 26-Mar-25
Note on LO286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 15-Mar-25 End Date: 26-Mar-25
Note on LP286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 15-Mar-25 End Date: 26-Mar-25
Note on LQ286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 15-Mar-25 End Date: 26-Mar-25
Note on LR286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 15-Mar-25 End Date: 26-Mar-25
Note on LS286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 15-Mar-25 End Date: 26-Mar-25
Note on LT286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 15-Mar-25 End Date: 26-Mar-25
Note on LU286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 27-Mar-25 End Date: 05-Apr-25
Note on LV286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 27-Mar-25 End Date: 05-Apr-25
Note on LW286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 27-Mar-25 End Date: 05-Apr-25
Note on LX286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 27-Mar-25 End Date: 05-Apr-25
Note on LY286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 27-Mar-25 End Date: 05-Apr-25
Note on LZ286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 27-Mar-25 End Date: 05-Apr-25
Note on MA286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on MB286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on MC286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on MD286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on ME286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on MF286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on MG286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on MH286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on MI286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on MJ286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on MK286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on ML286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on MM286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on MN286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install XFMs Start Date: 02-Apr-25 End Date: 15-Apr-25
Note on MO286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install Generators Start Date: 11-Apr-25 End Date: 24-Apr-25
Note on MP286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install Generators Start Date: 11-Apr-25 End Date: 24-Apr-25
Note on MQ286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install Generators Start Date: 11-Apr-25 End Date: 24-Apr-25
Note on MR286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install Generators Start Date: 11-Apr-25 End Date: 24-Apr-25
Note on MS286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install Generators Start Date: 11-Apr-25 End Date: 24-Apr-25
Note on MT286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install Generators Start Date: 11-Apr-25 End Date: 24-Apr-25
Note on MU286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install Generators Start Date: 11-Apr-25 End Date: 24-Apr-25
Note on MV286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install Generators Start Date: 11-Apr-25 End Date: 24-Apr-25
Note on MW286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: Install Generators Start Date: 11-Apr-25 End Date: 24-Apr-25
Note on MX286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on MY286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on MZ286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NA286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NB286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NC286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on ND286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NE286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NF286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NG286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NH286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 1 Start Date: 25-Apr-25 End Date: 05-May-25
Note on NI286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NJ286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NK286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NL286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NM286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NN286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NO286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NP286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NQ286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 2 Start Date: 06-May-25 End Date: 14-May-25
Note on NR286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NS286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NT286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NU286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NV286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NW286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NX286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NY286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on NZ286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 4 Start Date: 15-May-25 End Date: 23-May-25
Note on OD286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 04-Jun-25
Note on OE286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 04-Jun-25
Note on OF286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 04-Jun-25
Note on OG286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 04-Jun-25
Note on OH286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 04-Jun-25
Note on OI286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 04-Jun-25
Note on OJ286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 04-Jun-25
Note on OK286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 04-Jun-25
Note on OL286: Phase: Electrical Yard Location: COLO 4 Trade: Electrical Activity Name: MV Cable Pulling & Terminating to Cell 3 Start Date: 27-May-25 End Date: 04-Jun-25
Note on JG298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JH298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JI298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JJ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JK298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JL298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JM298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JN298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JO298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JP298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JQ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JR298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JS298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JT298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JU298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JV298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JW298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JX298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JY298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on JZ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KA298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KB298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KC298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KD298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KE298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KF298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KG298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KH298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KI298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KJ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KK298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KL298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KM298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KN298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KO298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KP298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KQ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KR298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KS298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KT298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KU298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KV298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KW298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KX298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KY298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on KZ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LA298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LB298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LC298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LD298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LE298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LF298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LG298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LH298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LI298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LJ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LK298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LL298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LM298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LN298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LO298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LP298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LQ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LR298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LS298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LT298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LU298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Beneficial Use Rooms Start Date: 20-Jan-25 End Date: 09-May-25
Note on LV298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 28-Mar-25 End Date: 07-Apr-25
Note on LW298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 28-Mar-25 End Date: 07-Apr-25
Note on LX298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 28-Mar-25 End Date: 07-Apr-25
Note on LY298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 28-Mar-25 End Date: 07-Apr-25
Note on LZ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 28-Mar-25 End Date: 07-Apr-25
Note on MA298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 28-Mar-25 End Date: 07-Apr-25
Note on MB298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 28-Mar-25 End Date: 07-Apr-25
Note on MC298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 28-Mar-25 End Date: 07-Apr-25
Note on MD298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 28-Mar-25 End Date: 07-Apr-25
Note on ME298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 28-Mar-25 End Date: 07-Apr-25
Note on MF298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for XFMs Start Date: 28-Mar-25 End Date: 07-Apr-25
Note on MG298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 08-Apr-25 End Date: 18-Apr-25
Note on MH298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 08-Apr-25 End Date: 18-Apr-25
Note on MI298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 08-Apr-25 End Date: 18-Apr-25
Note on MJ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 08-Apr-25 End Date: 18-Apr-25
Note on MK298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 08-Apr-25 End Date: 18-Apr-25
Note on ML298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 08-Apr-25 End Date: 18-Apr-25
Note on MM298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 08-Apr-25 End Date: 18-Apr-25
Note on MN298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 08-Apr-25 End Date: 18-Apr-25
Note on MO298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 08-Apr-25 End Date: 18-Apr-25
Note on MP298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 08-Apr-25 End Date: 18-Apr-25
Note on MQ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UPMs Start Date: 08-Apr-25 End Date: 18-Apr-25
Note on MR298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 19-Apr-25 End Date: 29-Apr-25
Note on MS298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 19-Apr-25 End Date: 29-Apr-25
Note on MT298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 19-Apr-25 End Date: 29-Apr-25
Note on MU298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 19-Apr-25 End Date: 29-Apr-25
Note on MV298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 19-Apr-25 End Date: 29-Apr-25
Note on MW298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 19-Apr-25 End Date: 29-Apr-25
Note on MX298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 19-Apr-25 End Date: 29-Apr-25
Note on MY298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 19-Apr-25 End Date: 29-Apr-25
Note on MZ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 19-Apr-25 End Date: 29-Apr-25
Note on NA298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 19-Apr-25 End Date: 29-Apr-25
Note on NB298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for UMSs Start Date: 19-Apr-25 End Date: 29-Apr-25
Note on NC298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 30-Apr-25 End Date: 10-May-25
Note on ND298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Build Equipment Pads for Generators Start Date: 30-Apr-25 End Date: 10-May-25
Note on NE298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 1 Start Date: 02-May-25 End Date: 12-May-25
Note on NF298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 1 Start Date: 02-May-25 End Date: 12-May-25
Note on NG298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 1 Start Date: 02-May-25 End Date: 12-May-25
Note on NH298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 1 Start Date: 02-May-25 End Date: 12-May-25
Note on NI298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 1 Start Date: 02-May-25 End Date: 12-May-25
Note on NJ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 1 Start Date: 02-May-25 End Date: 12-May-25
Note on NK298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 1 Start Date: 02-May-25 End Date: 12-May-25
Note on NL298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 1 Start Date: 02-May-25 End Date: 12-May-25
Note on NM298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 1 Start Date: 02-May-25 End Date: 12-May-25
Note on NN298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 1 Start Date: 02-May-25 End Date: 12-May-25
Note on NO298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 1 Start Date: 02-May-25 End Date: 12-May-25
Note on NP298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 2 Start Date: 13-May-25 End Date: 21-May-25
Note on NQ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 2 Start Date: 13-May-25 End Date: 21-May-25
Note on NR298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 2 Start Date: 13-May-25 End Date: 21-May-25
Note on NS298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 2 Start Date: 13-May-25 End Date: 21-May-25
Note on NT298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 2 Start Date: 13-May-25 End Date: 21-May-25
Note on NU298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 2 Start Date: 13-May-25 End Date: 21-May-25
Note on NV298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 2 Start Date: 13-May-25 End Date: 21-May-25
Note on NW298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 2 Start Date: 13-May-25 End Date: 21-May-25
Note on NX298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 2 Start Date: 13-May-25 End Date: 21-May-25
Note on NY298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 4 Start Date: 22-May-25 End Date: 31-May-25
Note on NZ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 4 Start Date: 22-May-25 End Date: 31-May-25
Note on OA298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 4 Start Date: 22-May-25 End Date: 31-May-25
Note on OB298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 4 Start Date: 22-May-25 End Date: 31-May-25
Note on OC298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 4 Start Date: 22-May-25 End Date: 31-May-25
Note on OD298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 4 Start Date: 22-May-25 End Date: 31-May-25
Note on OE298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 4 Start Date: 22-May-25 End Date: 31-May-25
Note on OF298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 4 Start Date: 22-May-25 End Date: 31-May-25
Note on OG298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 1 Start Date: 30-May-25 End Date: 03-Jun-25
Note on OH298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 1 Start Date: 30-May-25 End Date: 03-Jun-25
Note on OI298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 1 Start Date: 30-May-25 End Date: 03-Jun-25
Note on OJ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 1 Start Date: 30-May-25 End Date: 03-Jun-25
Note on OK298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 1 Start Date: 30-May-25 End Date: 03-Jun-25
Note on OL298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 2 Start Date: 04-Jun-25 End Date: 07-Jun-25
Note on OM298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 2 Start Date: 04-Jun-25 End Date: 07-Jun-25
Note on ON298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 2 Start Date: 04-Jun-25 End Date: 07-Jun-25
Note on OO298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 2 Start Date: 04-Jun-25 End Date: 07-Jun-25
Note on OP298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: MV Cable Pulling & Terminating(To Junction Box) to Cell 3 Start Date: 02-Jun-25 End Date: 10-Jun-25
Note on OQ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 4 Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on OR298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 4 Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on OS298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 4 Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on OT298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 4 Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on OU298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 3 Start Date: 13-Jun-25 End Date: 18-Jun-25
Note on OV298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 3 Start Date: 13-Jun-25 End Date: 18-Jun-25
Note on OW298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 3 Start Date: 13-Jun-25 End Date: 18-Jun-25
Note on OX298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 3 Start Date: 13-Jun-25 End Date: 18-Jun-25
Note on OY298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 3 Start Date: 13-Jun-25 End Date: 18-Jun-25
Note on OZ298: Phase: Electrical Yard Location: COLO 5 Trade: Electrical Activity Name: Terminate MV Gear - Cell 3 Start Date: 13-Jun-25 End Date: 18-Jun-25
Note on KN315: Phase: Fitout Location: Admin Trade: Framing Activity Name: Install Doors Start Date: 22-Feb-25 End Date: 26-Feb-25
Note on KO315: Phase: Fitout Location: Admin Trade: Framing Activity Name: Install Doors Start Date: 22-Feb-25 End Date: 26-Feb-25
Note on KP315: Phase: Fitout Location: Admin Trade: Framing Activity Name: Install Doors Start Date: 22-Feb-25 End Date: 26-Feb-25
Note on KQ315: Phase: Fitout Location: Admin Trade: Framing Activity Name: Install Doors Start Date: 22-Feb-25 End Date: 26-Feb-25
Note on KR315: Phase: Fitout Location: Admin Trade: Framing Activity Name: Install Doors Start Date: 22-Feb-25 End Date: 26-Feb-25
Note on KS315: Phase: Fitout Location: Admin Trade: Electrical Activity Name: Light Fixtures Installation Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on KT315: Phase: Fitout Location: Admin Trade: Electrical Activity Name: Light Fixtures Installation Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on KU315: Phase: Fitout Location: Admin Trade: Electrical Activity Name: Light Fixtures Installation Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on KV315: Phase: Fitout Location: Admin Trade: Electrical Activity Name: Light Fixtures Installation Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on KW315: Phase: Fitout Location: Admin Trade: Electrical Activity Name: Light Fixtures Installation Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on KX315: Phase: Fitout Location: Admin Trade: Electrical Activity Name: Light Fixtures Installation Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on KY315: Phase: Fitout Location: Admin Trade: Electrical Activity Name: Light Fixtures Installation Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on KZ315: Phase: Fitout Location: Admin Trade: Electrical Activity Name: Light Fixtures Installation Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on LA315: Phase: Fitout Location: Admin Trade: Electrical Activity Name: Light Fixtures Installation Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on LB315: Phase: Fitout Location: Admin Trade: Electrical Activity Name: Light Fixtures Installation Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on LC315: Phase: Fitout Location: Admin Trade: Electrical Activity Name: Light Fixtures Installation Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on LD315: Phase: Fitout Location: Admin Trade: Electrical Activity Name: Light Fixtures Installation Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on LE315: Phase: Fitout Location: Admin Trade: Electrical Activity Name: Light Fixtures Installation Start Date: 27-Feb-25 End Date: 11-Mar-25
Note on LF315: Phase: Fitout Location: Admin Trade: Clayco Activity Name: Remaining Area Punchlist Start Date: 12-Mar-25 End Date: 17-Mar-25
Note on LG315: Phase: Fitout Location: Admin Trade: Clayco Activity Name: Remaining Area Punchlist Start Date: 12-Mar-25 End Date: 17-Mar-25
Note on LH315: Phase: Fitout Location: Admin Trade: Clayco Activity Name: Remaining Area Punchlist Start Date: 12-Mar-25 End Date: 17-Mar-25
Note on LI315: Phase: Fitout Location: Admin Trade: Clayco Activity Name: Remaining Area Punchlist Start Date: 12-Mar-25 End Date: 17-Mar-25
Note on LJ315: Phase: Fitout Location: Admin Trade: Clayco Activity Name: Remaining Area Punchlist Start Date: 12-Mar-25 End Date: 17-Mar-25
Note on LK315: Phase: Fitout Location: Admin Trade: Clayco Activity Name: Remaining Area Punchlist Start Date: 12-Mar-25 End Date: 17-Mar-25
Note on KP318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Layout Framing Start Date: 24-Feb-25 End Date: 24-Feb-25
Note on KQ318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: IInstall Framing Start Date: 25-Feb-25 End Date: 27-Feb-25
Note on KR318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: IInstall Framing Start Date: 25-Feb-25 End Date: 27-Feb-25
Note on KS318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: IInstall Framing Start Date: 25-Feb-25 End Date: 27-Feb-25
Note on KT318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KU318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KV318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KW318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KX318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KY318: Phase: Fitout Location: CELL 1 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 05-Mar-25 End Date: 07-Mar-25
Note on KZ318: Phase: Fitout Location: CELL 1 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 05-Mar-25 End Date: 07-Mar-25
Note on LA318: Phase: Fitout Location: CELL 1 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 05-Mar-25 End Date: 07-Mar-25
Note on LB318: Phase: Fitout Location: CELL 1 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 08-Mar-25 End Date: 11-Mar-25
Note on LC318: Phase: Fitout Location: CELL 1 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 08-Mar-25 End Date: 11-Mar-25
Note on LD318: Phase: Fitout Location: CELL 1 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 08-Mar-25 End Date: 11-Mar-25
Note on LE318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 11-Mar-25 End Date: 12-Mar-25
Note on LF318: Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 12-Mar-25 End Date: 14-Mar-25
Note on LG318: Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 12-Mar-25 End Date: 14-Mar-25
Note on LH318: Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 12-Mar-25 End Date: 14-Mar-25
Note on LI318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 15-Mar-25 End Date: 18-Mar-25
Note on LJ318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 15-Mar-25 End Date: 18-Mar-25
Note on LK318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 15-Mar-25 End Date: 18-Mar-25
Note on LL318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 15-Mar-25 End Date: 18-Mar-25
Note on LM318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on LN318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on LO318: Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 21-Mar-25 End Date: 24-Mar-25
Note on LP318: Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 21-Mar-25 End Date: 24-Mar-25
Note on LQ318: Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 21-Mar-25 End Date: 24-Mar-25
Note on LR318: Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 21-Mar-25 End Date: 24-Mar-25
Note on LS318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 25-Mar-25 End Date: 28-Mar-25
Note on LT318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 25-Mar-25 End Date: 28-Mar-25
Note on LU318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 25-Mar-25 End Date: 28-Mar-25
Note on LV318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 25-Mar-25 End Date: 28-Mar-25
Note on LW318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 29-Mar-25 End Date: 02-Apr-25
Note on LX318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 29-Mar-25 End Date: 02-Apr-25
Note on LY318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Layout Framing Start Date: 31-Mar-25 End Date: 31-Mar-25
Note on LZ318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 29-Mar-25 End Date: 02-Apr-25
Note on MA318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 29-Mar-25 End Date: 02-Apr-25
Note on MB318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 03-Apr-25 End Date: 07-Apr-25
Note on MC318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 03-Apr-25 End Date: 07-Apr-25
Note on MD318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 03-Apr-25 End Date: 07-Apr-25
Note on ME318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 03-Apr-25 End Date: 07-Apr-25
Note on MF318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 03-Apr-25 End Date: 07-Apr-25
Note on MG318: Phase: Fitout Location: CELL 1 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 08-Apr-25 End Date: 10-Apr-25
Note on MH318: Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 09-Apr-25 End Date: 14-Apr-25
Note on MI318: Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 09-Apr-25 End Date: 14-Apr-25
Note on MJ318: Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 09-Apr-25 End Date: 14-Apr-25
Note on MK318: Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 09-Apr-25 End Date: 14-Apr-25
Note on ML318: Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 09-Apr-25 End Date: 14-Apr-25
Note on MM318: Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 09-Apr-25 End Date: 14-Apr-25
Note on MN318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 15-Apr-25 End Date: 16-Apr-25
Note on MO318: Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 16-Apr-25 End Date: 18-Apr-25
Note on MP318: Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 16-Apr-25 End Date: 18-Apr-25
Note on MQ318: Phase: Fitout Location: CELL 1 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 16-Apr-25 End Date: 18-Apr-25
Note on MR318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 19-Apr-25 End Date: 22-Apr-25
Note on MS318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 19-Apr-25 End Date: 22-Apr-25
Note on MT318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 19-Apr-25 End Date: 22-Apr-25
Note on MU318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 22-Apr-25 End Date: 26-Apr-25
Note on MV318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 22-Apr-25 End Date: 26-Apr-25
Note on MW318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 22-Apr-25 End Date: 26-Apr-25
Note on MX318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 22-Apr-25 End Date: 26-Apr-25
Note on MY318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 22-Apr-25 End Date: 26-Apr-25
Note on NA318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 28-Apr-25 End Date: 01-May-25
Note on NB318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 28-Apr-25 End Date: 01-May-25
Note on NC318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 28-Apr-25 End Date: 01-May-25
Note on ND318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 01-May-25 End Date: 05-May-25
Note on NE318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 01-May-25 End Date: 05-May-25
Note on NF318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 01-May-25 End Date: 05-May-25
Note on NG318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 01-May-25 End Date: 05-May-25
Note on NH318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 01-May-25 End Date: 05-May-25
Note on NI318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 02-May-25 End Date: 07-May-25
Note on NJ318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 02-May-25 End Date: 07-May-25
Note on NK318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 08-May-25 End Date: 12-May-25
Note on NL318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 08-May-25 End Date: 12-May-25
Note on NM318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 08-May-25 End Date: 12-May-25
Note on NN318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 08-May-25 End Date: 12-May-25
Note on NO318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 08-May-25 End Date: 12-May-25
Note on NP318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Start Date: 08-May-25 End Date: 13-May-25
Note on NQ318: Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 14-May-25 End Date: 17-May-25
Note on NR318: Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 14-May-25 End Date: 17-May-25
Note on NS318: Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 14-May-25 End Date: 17-May-25
Note on NT318: Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 14-May-25 End Date: 17-May-25
Note on NV318: Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 19-May-25 End Date: 22-May-25
Note on NW318: Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 19-May-25 End Date: 22-May-25
Note on NX318: Phase: Fitout Location: CELL 1 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 19-May-25 End Date: 22-May-25
Note on NY318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 22-May-25 End Date: 23-May-25
Note on NZ318: Phase: Fitout Location: CELL 1 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 22-May-25 End Date: 23-May-25
Note on OD318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-May-25 End Date: 31-May-25
Note on OE318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-May-25 End Date: 31-May-25
Note on OF318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-May-25 End Date: 31-May-25
Note on OG318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-May-25 End Date: 31-May-25
Note on OH318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-May-25 End Date: 31-May-25
Note on OJ318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 02-Jun-25 End Date: 04-Jun-25
Note on OK318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 02-Jun-25 End Date: 04-Jun-25
Note on OL318: Phase: Fitout Location: CELL 1 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 02-Jun-25 End Date: 04-Jun-25
Note on KT374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 28-Feb-25 End Date: 03-Mar-25
Note on KU374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 28-Feb-25 End Date: 03-Mar-25
Note on KV374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 28-Feb-25 End Date: 03-Mar-25
Note on KW374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 28-Feb-25 End Date: 03-Mar-25
Note on KX374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 04-Mar-25 End Date: 05-Mar-25
Note on KY374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 04-Mar-25 End Date: 05-Mar-25
Note on KZ374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on LA374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on LB374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LC374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LD374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LE374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 08-Mar-25 End Date: 11-Mar-25
Note on LF374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 12-Mar-25 End Date: 13-Mar-25
Note on LG374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 13-Mar-25 End Date: 14-Mar-25
Note on LH374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 13-Mar-25 End Date: 14-Mar-25
Note on LI374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Cx Activity Name: General Cleaning Start Date: 15-Mar-25 End Date: 15-Mar-25
Note on LY374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on LZ374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on MA374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on MB374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on MC374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on MD374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on ME374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on MF374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on MG374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on MH374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on MI374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on MJ374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on MK374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on ML374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on MM374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on MN374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on MO374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on MP374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 04-Apr-25 End Date: 17-Apr-25
Note on MQ374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MR374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MS374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MT374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MU374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MV374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 21-Apr-25 End Date: 01-May-25
Note on MW374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 21-Apr-25 End Date: 01-May-25
Note on MX374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 21-Apr-25 End Date: 01-May-25
Note on MY374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 21-Apr-25 End Date: 01-May-25
Note on MZ374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 21-Apr-25 End Date: 01-May-25
Note on NA374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 21-Apr-25 End Date: 01-May-25
Note on NB374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 21-Apr-25 End Date: 01-May-25
Note on NC374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 21-Apr-25 End Date: 01-May-25
Note on ND374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 21-Apr-25 End Date: 01-May-25
Note on NE374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NF374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NG374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NH374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NI374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NJ374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NK374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NL374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NM374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NN374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NO374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NP374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NQ374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NR374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 02-May-25 End Date: 15-May-25
Note on NS374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 16-May-25 End Date: 20-May-25
Note on NT374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 16-May-25 End Date: 20-May-25
Note on NU374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 16-May-25 End Date: 20-May-25
Note on NV374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 16-May-25 End Date: 20-May-25
Note on NW374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 16-May-25 End Date: 20-May-25
Note on NX374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 16-May-25 End Date: 29-May-25
Note on NY374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 16-May-25 End Date: 29-May-25
Note on NZ374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 16-May-25 End Date: 29-May-25
Note on OA374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 16-May-25 End Date: 29-May-25
Note on OB374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 16-May-25 End Date: 29-May-25
Note on OC374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 16-May-25 End Date: 29-May-25
Note on OD374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 16-May-25 End Date: 29-May-25
Note on OE374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 16-May-25 End Date: 29-May-25
Note on OF374: Phase: Fitout Location: CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 16-May-25 End Date: 29-May-25
Note on LB404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LC404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LD404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LE404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 11-Mar-25 End Date: 12-Mar-25
Note on LF404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 11-Mar-25 End Date: 12-Mar-25
Note on LG404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 11-Mar-25 End Date: 13-Mar-25
Note on LH404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 14-Mar-25 End Date: 20-Mar-25
Note on LI404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 14-Mar-25 End Date: 20-Mar-25
Note on LJ404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 14-Mar-25 End Date: 20-Mar-25
Note on LK404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 14-Mar-25 End Date: 20-Mar-25
Note on LL404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 14-Mar-25 End Date: 20-Mar-25
Note on LM404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 14-Mar-25 End Date: 20-Mar-25
Note on LN404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 14-Mar-25 End Date: 20-Mar-25
Note on LO404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 21-Mar-25 End Date: 28-Mar-25
Note on LP404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 21-Mar-25 End Date: 28-Mar-25
Note on LQ404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 21-Mar-25 End Date: 28-Mar-25
Note on LR404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 21-Mar-25 End Date: 28-Mar-25
Note on LS404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 21-Mar-25 End Date: 28-Mar-25
Note on LT404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 21-Mar-25 End Date: 28-Mar-25
Note on LU404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 21-Mar-25 End Date: 28-Mar-25
Note on LV404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 21-Mar-25 End Date: 28-Mar-25
Note on LW404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 29-Mar-25 End Date: 31-Mar-25
Note on LX404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 29-Mar-25 End Date: 31-Mar-25
Note on LY404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on LZ404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 01-Apr-25 End Date: 02-Apr-25
Note on MA404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 01-Apr-25 End Date: 02-Apr-25
Note on MB404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on MC404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 04-Apr-25 End Date: 05-Apr-25
Note on MD404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 04-Apr-25 End Date: 05-Apr-25
Note on ME404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: BAS Activity Name: Install BAS Equipments Start Date: 04-Apr-25 End Date: 16-Apr-25
Note on MF404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on MG404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on MH404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on MI404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on MJ404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MK404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on ML404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MM404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MN404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MO404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MP404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MQ404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MR404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MS404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MT404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MU404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MV404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MW404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MX404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 11-Apr-25 End Date: 25-Apr-25
Note on MY404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on MZ404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on NA404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on NB404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on NC404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on ND404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 25-Apr-25 End Date: 01-May-25
Note on NE404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 02-May-25 End Date: 05-May-25
Note on NF404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 02-May-25 End Date: 05-May-25
Note on NG404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 02-May-25 End Date: 05-May-25
Note on NH404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 05-May-25 End Date: 08-May-25
Note on NI404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 06-May-25 End Date: 07-May-25
Note on NJ404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 06-May-25 End Date: 07-May-25
Note on NK404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 05-May-25 End Date: 08-May-25
Note on NL404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 09-May-25 End Date: 10-May-25
Note on NM404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 09-May-25 End Date: 10-May-25
Note on NN404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: BAS Activity Name: Install BAS Equipments Start Date: 09-May-25 End Date: 20-May-25
Note on NO404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-May-25 End Date: 15-May-25
Note on NP404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-May-25 End Date: 15-May-25
Note on NQ404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-May-25 End Date: 15-May-25
Note on NR404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-May-25 End Date: 15-May-25
Note on NS404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on NT404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on NU404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on NV404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on NW404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on NX404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on NY404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on NZ404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on OA404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on OB404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on OC404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on OD404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on OE404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on OF404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on OG404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 16-May-25 End Date: 30-May-25
Note on OH404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 31-May-25 End Date: 04-Jun-25
Note on OI404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 31-May-25 End Date: 04-Jun-25
Note on OJ404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 31-May-25 End Date: 04-Jun-25
Note on OK404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 31-May-25 End Date: 04-Jun-25
Note on OL404: Phase: Fitout Location: CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 31-May-25 End Date: 04-Jun-25
Note on MP438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 17-Apr-25 End Date: 28-Apr-25
Note on MQ438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 17-Apr-25 End Date: 28-Apr-25
Note on MR438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 17-Apr-25 End Date: 28-Apr-25
Note on MS438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 17-Apr-25 End Date: 28-Apr-25
Note on MT438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 17-Apr-25 End Date: 28-Apr-25
Note on MU438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 17-Apr-25 End Date: 28-Apr-25
Note on MV438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 17-Apr-25 End Date: 28-Apr-25
Note on MW438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 17-Apr-25 End Date: 28-Apr-25
Note on MX438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 17-Apr-25 End Date: 28-Apr-25
Note on MY438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 17-Apr-25 End Date: 28-Apr-25
Note on MZ438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 17-Apr-25 End Date: 28-Apr-25
Note on NA438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 17-Apr-25 End Date: 28-Apr-25
Note on NI438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 06-May-25 End Date: 16-May-25
Note on NJ438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 06-May-25 End Date: 16-May-25
Note on NK438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 06-May-25 End Date: 16-May-25
Note on NL438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 06-May-25 End Date: 16-May-25
Note on NM438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 06-May-25 End Date: 16-May-25
Note on NN438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 06-May-25 End Date: 16-May-25
Note on NO438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 06-May-25 End Date: 16-May-25
Note on NP438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 06-May-25 End Date: 16-May-25
Note on NQ438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 06-May-25 End Date: 16-May-25
Note on NR438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 06-May-25 End Date: 16-May-25
Note on NS438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 06-May-25 End Date: 16-May-25
Note on OM438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on ON438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on OO438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on OP438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on OQ438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on OR438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on OS438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on OT438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on OU438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on OV438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on OW438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on OX438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on OY438: Phase: Fitout Location: CELL 1 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 05-Jun-25 End Date: 17-Jun-25
Note on KY441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Layout Framing Start Date: 05-Mar-25 End Date: 05-Mar-25
Note on KZ441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 06-Mar-25 End Date: 08-Mar-25
Note on LA441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 06-Mar-25 End Date: 08-Mar-25
Note on LB441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 06-Mar-25 End Date: 08-Mar-25
Note on LD441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 10-Mar-25 End Date: 12-Mar-25
Note on LE441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 10-Mar-25 End Date: 12-Mar-25
Note on LF441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 10-Mar-25 End Date: 12-Mar-25
Note on LG441: Phase: Fitout Location: CELL 2 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 13-Mar-25 End Date: 15-Mar-25
Note on LH441: Phase: Fitout Location: CELL 2 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 13-Mar-25 End Date: 15-Mar-25
Note on LI441: Phase: Fitout Location: CELL 2 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 13-Mar-25 End Date: 15-Mar-25
Note on LK441: Phase: Fitout Location: CELL 2 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 17-Mar-25 End Date: 19-Mar-25
Note on LL441: Phase: Fitout Location: CELL 2 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 17-Mar-25 End Date: 19-Mar-25
Note on LM441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on LN441: Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 20-Mar-25 End Date: 24-Mar-25
Note on LO441: Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 20-Mar-25 End Date: 24-Mar-25
Note on LP441: Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 20-Mar-25 End Date: 24-Mar-25
Note on LQ441: Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 20-Mar-25 End Date: 24-Mar-25
Note on LR441: Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 20-Mar-25 End Date: 24-Mar-25
Note on LS441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 25-Mar-25 End Date: 27-Mar-25
Note on LT441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 25-Mar-25 End Date: 27-Mar-25
Note on LU441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 25-Mar-25 End Date: 27-Mar-25
Note on LV441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 28-Mar-25 End Date: 29-Mar-25
Note on LW441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 28-Mar-25 End Date: 29-Mar-25
Note on LY441: Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 31-Mar-25 End Date: 01-Apr-25
Note on LZ441: Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 31-Mar-25 End Date: 01-Apr-25
Note on MA441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 02-Apr-25 End Date: 05-Apr-25
Note on MB441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 02-Apr-25 End Date: 05-Apr-25
Note on MC441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 02-Apr-25 End Date: 05-Apr-25
Note on MD441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 02-Apr-25 End Date: 05-Apr-25
Note on MF441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on MG441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Layout Framing Start Date: 08-Apr-25 End Date: 08-Apr-25
Note on MH441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on MI441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on MJ441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MK441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on ML441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MM441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MN441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MO441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MP441: Phase: Fitout Location: CELL 2 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 17-Apr-25 End Date: 19-Apr-25
Note on MQ441: Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MR441: Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MS441: Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MT441: Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MU441: Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MV441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 23-Apr-25 End Date: 24-Apr-25
Note on MW441: Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 24-Apr-25 End Date: 26-Apr-25
Note on MX441: Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 24-Apr-25 End Date: 26-Apr-25
Note on MY441: Phase: Fitout Location: CELL 2 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 24-Apr-25 End Date: 26-Apr-25
Note on MZ441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 26-Apr-25 End Date: 29-Apr-25
Note on NA441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 28-Apr-25 End Date: 30-Apr-25
Note on NB441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 28-Apr-25 End Date: 30-Apr-25
Note on NC441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 30-Apr-25 End Date: 06-May-25
Note on ND441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 30-Apr-25 End Date: 06-May-25
Note on NE441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 30-Apr-25 End Date: 06-May-25
Note on NF441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 30-Apr-25 End Date: 06-May-25
Note on NG441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 30-Apr-25 End Date: 06-May-25
Note on NH441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 30-Apr-25 End Date: 06-May-25
Note on NI441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 30-Apr-25 End Date: 06-May-25
Note on NJ441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 07-May-25 End Date: 10-May-25
Note on NK441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 07-May-25 End Date: 10-May-25
Note on NL441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 07-May-25 End Date: 10-May-25
Note on NM441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 07-May-25 End Date: 10-May-25
Note on NO441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 12-May-25 End Date: 15-May-25
Note on NP441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 12-May-25 End Date: 15-May-25
Note on NQ441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 12-May-25 End Date: 15-May-25
Note on NR441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 12-May-25 End Date: 15-May-25
Note on NS441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 16-May-25 End Date: 20-May-25
Note on NT441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 16-May-25 End Date: 20-May-25
Note on NU441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 16-May-25 End Date: 20-May-25
Note on NV441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 16-May-25 End Date: 20-May-25
Note on NW441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 16-May-25 End Date: 20-May-25
Note on NX441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Start Date: 16-May-25 End Date: 21-May-25
Note on NY441: Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 22-May-25 End Date: 27-May-25
Note on NZ441: Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 22-May-25 End Date: 27-May-25
Note on OA441: Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 22-May-25 End Date: 27-May-25
Note on OB441: Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 22-May-25 End Date: 27-May-25
Note on OC441: Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 22-May-25 End Date: 27-May-25
Note on OD441: Phase: Fitout Location: CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 22-May-25 End Date: 27-May-25
Note on OE441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 28-May-25 End Date: 30-May-25
Note on OF441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 28-May-25 End Date: 30-May-25
Note on OG441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 28-May-25 End Date: 30-May-25
Note on OH441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 31-May-25 End Date: 03-Jun-25
Note on OI441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 31-May-25 End Date: 03-Jun-25
Note on OJ441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 31-May-25 End Date: 03-Jun-25
Note on OK441: Phase: Fitout Location: CELL 2 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 31-May-25 End Date: 03-Jun-25
Note on OL441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 04-Jun-25 End Date: 09-Jun-25
Note on OM441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 04-Jun-25 End Date: 09-Jun-25
Note on ON441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 04-Jun-25 End Date: 09-Jun-25
Note on OO441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 04-Jun-25 End Date: 09-Jun-25
Note on OP441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 04-Jun-25 End Date: 09-Jun-25
Note on OQ441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 04-Jun-25 End Date: 09-Jun-25
Note on PG441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 25-Jun-25 End Date: 27-Jun-25
Note on PH441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 25-Jun-25 End Date: 27-Jun-25
Note on PI441: Phase: Fitout Location: CELL 2 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 25-Jun-25 End Date: 27-Jun-25
Note on LD497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 10-Mar-25 End Date: 11-Mar-25
Note on LE497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 10-Mar-25 End Date: 11-Mar-25
Note on LF497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 12-Mar-25 End Date: 13-Mar-25
Note on LG497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 12-Mar-25 End Date: 13-Mar-25
Note on LH497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 14-Mar-25 End Date: 15-Mar-25
Note on LI497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 14-Mar-25 End Date: 15-Mar-25
Note on LJ497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Activity Name: Install Drywall [Elec + Battery Rooms] Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LK497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 17-Mar-25 End Date: 18-Mar-25
Note on LL497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 17-Mar-25 End Date: 18-Mar-25
Note on LM497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 17-Mar-25 End Date: 19-Mar-25
Note on LN497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 20-Mar-25 End Date: 21-Mar-25
Note on LO497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 21-Mar-25 End Date: 24-Mar-25
Note on LP497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 21-Mar-25 End Date: 24-Mar-25
Note on LQ497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 21-Mar-25 End Date: 24-Mar-25
Note on LR497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 21-Mar-25 End Date: 24-Mar-25
Note on LS497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Cx Activity Name: General Cleaning Start Date: 25-Mar-25 End Date: 25-Mar-25
Note on LT497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 26-Mar-25 End Date: 29-Mar-25
Note on LU497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 26-Mar-25 End Date: 29-Mar-25
Note on LV497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 26-Mar-25 End Date: 29-Mar-25
Note on LW497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 26-Mar-25 End Date: 29-Mar-25
Note on MM497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 14-Apr-25 End Date: 15-Apr-25
Note on MN497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 14-Apr-25 End Date: 15-Apr-25
Note on MO497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 16-Apr-25 End Date: 17-Apr-25
Note on MP497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 16-Apr-25 End Date: 17-Apr-25
Note on MQ497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 18-Apr-25 End Date: 19-Apr-25
Note on MR497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 18-Apr-25 End Date: 19-Apr-25
Note on MS497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Framing Activity Name: Install Drywall [Elec + Battery Rooms] Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MT497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 21-Apr-25 End Date: 22-Apr-25
Note on MU497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 21-Apr-25 End Date: 22-Apr-25
Note on MV497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 21-Apr-25 End Date: 23-Apr-25
Note on MW497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 24-Apr-25 End Date: 25-Apr-25
Note on MX497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 25-Apr-25 End Date: 26-Apr-25
Note on MY497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 25-Apr-25 End Date: 26-Apr-25
Note on NA497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Cx Activity Name: General Cleaning Start Date: 28-Apr-25 End Date: 28-Apr-25
Note on NB497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 29-Apr-25 End Date: 02-May-25
Note on NC497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 29-Apr-25 End Date: 02-May-25
Note on ND497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 29-Apr-25 End Date: 02-May-25
Note on NE497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 29-Apr-25 End Date: 02-May-25
Note on NF497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 01-May-25 End Date: 14-May-25
Note on NG497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 01-May-25 End Date: 14-May-25
Note on NH497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 01-May-25 End Date: 14-May-25
Note on NI497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 01-May-25 End Date: 14-May-25
Note on NJ497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 01-May-25 End Date: 14-May-25
Note on NK497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 01-May-25 End Date: 14-May-25
Note on NL497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 01-May-25 End Date: 14-May-25
Note on NM497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 01-May-25 End Date: 14-May-25
Note on NN497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 01-May-25 End Date: 14-May-25
Note on NO497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 01-May-25 End Date: 14-May-25
Note on NP497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 01-May-25 End Date: 14-May-25
Note on NQ497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 01-May-25 End Date: 14-May-25
Note on NR497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 15-May-25 End Date: 19-May-25
Note on NS497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 15-May-25 End Date: 19-May-25
Note on NT497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 15-May-25 End Date: 19-May-25
Note on NU497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 15-May-25 End Date: 19-May-25
Note on NV497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 15-May-25 End Date: 19-May-25
Note on NW497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 15-May-25 End Date: 27-May-25
Note on NX497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 15-May-25 End Date: 27-May-25
Note on NY497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 15-May-25 End Date: 27-May-25
Note on NZ497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 15-May-25 End Date: 27-May-25
Note on OA497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 15-May-25 End Date: 27-May-25
Note on OB497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 15-May-25 End Date: 27-May-25
Note on OC497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 15-May-25 End Date: 27-May-25
Note on OD497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 15-May-25 End Date: 27-May-25
Note on OG497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 30-May-25 End Date: 11-Jun-25
Note on OH497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 30-May-25 End Date: 11-Jun-25
Note on OI497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 30-May-25 End Date: 11-Jun-25
Note on OJ497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 30-May-25 End Date: 11-Jun-25
Note on OK497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 30-May-25 End Date: 11-Jun-25
Note on OL497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 30-May-25 End Date: 11-Jun-25
Note on OM497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 30-May-25 End Date: 11-Jun-25
Note on ON497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 30-May-25 End Date: 11-Jun-25
Note on OO497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 30-May-25 End Date: 11-Jun-25
Note on OP497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 30-May-25 End Date: 11-Jun-25
Note on OQ497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 30-May-25 End Date: 11-Jun-25
Note on OR497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 30-May-25 End Date: 11-Jun-25
Note on OS497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 30-May-25 End Date: 11-Jun-25
Note on OT497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on OU497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on OV497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on OW497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on OX497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on OY497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on OZ497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 12-Jun-25 End Date: 24-Jun-25
Note on PA497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 12-Jun-25 End Date: 24-Jun-25
Note on PB497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 12-Jun-25 End Date: 24-Jun-25
Note on PC497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 12-Jun-25 End Date: 24-Jun-25
Note on PD497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 12-Jun-25 End Date: 24-Jun-25
Note on PE497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 12-Jun-25 End Date: 24-Jun-25
Note on PF497: Phase: Fitout Location: CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 12-Jun-25 End Date: 24-Jun-25
Note on LK527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 17-Mar-25 End Date: 18-Mar-25
Note on LL527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 17-Mar-25 End Date: 18-Mar-25
Note on LM527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on LN527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on LO527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 19-Mar-25 End Date: 21-Mar-25
Note on LR527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 24-Mar-25 End Date: 29-Mar-25
Note on LS527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 24-Mar-25 End Date: 29-Mar-25
Note on LT527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 24-Mar-25 End Date: 29-Mar-25
Note on LU527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 24-Mar-25 End Date: 29-Mar-25
Note on LV527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 24-Mar-25 End Date: 29-Mar-25
Note on LW527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 24-Mar-25 End Date: 29-Mar-25
Note on LY527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 31-Mar-25 End Date: 05-Apr-25
Note on LZ527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 31-Mar-25 End Date: 05-Apr-25
Note on MA527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 31-Mar-25 End Date: 05-Apr-25
Note on MB527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 31-Mar-25 End Date: 05-Apr-25
Note on MC527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 31-Mar-25 End Date: 05-Apr-25
Note on MD527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 31-Mar-25 End Date: 05-Apr-25
Note on MF527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 07-Apr-25 End Date: 08-Apr-25
Note on MG527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 08-Apr-25 End Date: 11-Apr-25
Note on MH527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 09-Apr-25 End Date: 10-Apr-25
Note on MI527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 09-Apr-25 End Date: 10-Apr-25
Note on MJ527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 08-Apr-25 End Date: 11-Apr-25
Note on MK527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Cx Activity Name: General Cleaning Start Date: 11-Apr-25 End Date: 15-Apr-25
Note on ML527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Cx Activity Name: General Cleaning Start Date: 11-Apr-25 End Date: 15-Apr-25
Note on MM527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 14-Apr-25 End Date: 15-Apr-25
Note on MN527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 14-Apr-25 End Date: 15-Apr-25
Note on MO527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 16-Apr-25 End Date: 19-Apr-25
Note on MP527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 16-Apr-25 End Date: 19-Apr-25
Note on MQ527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 16-Apr-25 End Date: 19-Apr-25
Note on MR527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 16-Apr-25 End Date: 19-Apr-25
Note on MS527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: BAS Activity Name: Install BAS Equipments Start Date: 14-Apr-25 End Date: 24-Apr-25
Note on MT527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on MU527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on MV527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on MW527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on MX527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on MY527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on MZ527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on NA527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on NB527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on NC527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on ND527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on NE527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on NF527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on NG527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on NH527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 21-Apr-25 End Date: 05-May-25
Note on NI527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 06-May-25 End Date: 09-May-25
Note on NJ527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 06-May-25 End Date: 09-May-25
Note on NK527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 06-May-25 End Date: 09-May-25
Note on NL527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 06-May-25 End Date: 09-May-25
Note on NM527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 05-May-25 End Date: 10-May-25
Note on NO527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 12-May-25 End Date: 13-May-25
Note on NP527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 13-May-25 End Date: 16-May-25
Note on NQ527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 14-May-25 End Date: 15-May-25
Note on NR527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 14-May-25 End Date: 15-May-25
Note on NS527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 13-May-25 End Date: 16-May-25
Note on NT527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 17-May-25 End Date: 19-May-25
Note on NU527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 17-May-25 End Date: 19-May-25
Note on NV527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 17-May-25 End Date: 19-May-25
Note on NW527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 20-May-25 End Date: 23-May-25
Note on NX527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 20-May-25 End Date: 23-May-25
Note on NY527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 20-May-25 End Date: 23-May-25
Note on NZ527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 20-May-25 End Date: 23-May-25
Note on OA527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: BAS Activity Name: Install BAS Equipments Start Date: 17-May-25 End Date: 29-May-25
Note on OB527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: BAS Activity Name: Install BAS Equipments Start Date: 17-May-25 End Date: 29-May-25
Note on OC527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: BAS Activity Name: Install BAS Equipments Start Date: 17-May-25 End Date: 29-May-25
Note on OD527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 27-May-25 End Date: 07-Jun-25
Note on OE527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 27-May-25 End Date: 07-Jun-25
Note on OF527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 27-May-25 End Date: 07-Jun-25
Note on OG527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 27-May-25 End Date: 07-Jun-25
Note on OH527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 27-May-25 End Date: 07-Jun-25
Note on OI527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 27-May-25 End Date: 07-Jun-25
Note on OJ527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 27-May-25 End Date: 07-Jun-25
Note on OK527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 27-May-25 End Date: 07-Jun-25
Note on OL527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 27-May-25 End Date: 07-Jun-25
Note on OM527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 27-May-25 End Date: 07-Jun-25
Note on ON527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 27-May-25 End Date: 07-Jun-25
Note on OO527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 27-May-25 End Date: 07-Jun-25
Note on OQ527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on OR527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on OS527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on OT527: Phase: Fitout Location: CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on OH561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 31-May-25 End Date: 11-Jun-25
Note on OI561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 31-May-25 End Date: 11-Jun-25
Note on OJ561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 31-May-25 End Date: 11-Jun-25
Note on OK561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 31-May-25 End Date: 11-Jun-25
Note on OL561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 31-May-25 End Date: 11-Jun-25
Note on OM561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 31-May-25 End Date: 11-Jun-25
Note on ON561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 31-May-25 End Date: 11-Jun-25
Note on OO561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 31-May-25 End Date: 11-Jun-25
Note on OP561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 31-May-25 End Date: 11-Jun-25
Note on OQ561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 31-May-25 End Date: 11-Jun-25
Note on OR561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 31-May-25 End Date: 11-Jun-25
Note on OS561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 31-May-25 End Date: 11-Jun-25
Note on PJ561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on PK561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on PL561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on PM561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on PN561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on PO561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on PP561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on PQ561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on PR561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on PS561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on PT561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on PU561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on PV561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on PW561: Phase: Fitout Location: CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 28-Jun-25 End Date: 11-Jul-25
Note on LV563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Layout Framing Start Date: 28-Mar-25 End Date: 28-Mar-25
Note on LW563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 29-Mar-25 End Date: 01-Apr-25
Note on LX563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 29-Mar-25 End Date: 01-Apr-25
Note on LY563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 29-Mar-25 End Date: 01-Apr-25
Note on LZ563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 29-Mar-25 End Date: 01-Apr-25
Note on MA563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 02-Apr-25 End Date: 04-Apr-25
Note on MB563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 02-Apr-25 End Date: 04-Apr-25
Note on MC563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 02-Apr-25 End Date: 04-Apr-25
Note on MD563: Phase: Fitout Location: CELL 3 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 05-Apr-25 End Date: 08-Apr-25
Note on ME563: Phase: Fitout Location: CELL 3 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 05-Apr-25 End Date: 08-Apr-25
Note on MF563: Phase: Fitout Location: CELL 3 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 05-Apr-25 End Date: 08-Apr-25
Note on MG563: Phase: Fitout Location: CELL 3 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 05-Apr-25 End Date: 08-Apr-25
Note on MH563: Phase: Fitout Location: CELL 3 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 09-Apr-25 End Date: 11-Apr-25
Note on MI563: Phase: Fitout Location: CELL 3 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 09-Apr-25 End Date: 11-Apr-25
Note on MJ563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 11-Apr-25 End Date: 14-Apr-25
Note on MK563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 11-Apr-25 End Date: 14-Apr-25
Note on ML563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 11-Apr-25 End Date: 14-Apr-25
Note on MM563: Phase: Fitout Location: CELL 3 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 14-Apr-25 End Date: 16-Apr-25
Note on MN563: Phase: Fitout Location: CELL 3 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 14-Apr-25 End Date: 16-Apr-25
Note on MO563: Phase: Fitout Location: CELL 3 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 14-Apr-25 End Date: 16-Apr-25
Note on MP563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 17-Apr-25 End Date: 19-Apr-25
Note on MQ563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 17-Apr-25 End Date: 19-Apr-25
Note on MR563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 17-Apr-25 End Date: 19-Apr-25
Note on MT563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 21-Apr-25 End Date: 22-Apr-25
Note on MU563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 21-Apr-25 End Date: 22-Apr-25
Note on MV563: Phase: Fitout Location: CELL 3 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 23-Apr-25 End Date: 24-Apr-25
Note on MW563: Phase: Fitout Location: CELL 3 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 23-Apr-25 End Date: 24-Apr-25
Note on MX563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 25-Apr-25 End Date: 29-Apr-25
Note on MY563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 25-Apr-25 End Date: 29-Apr-25
Note on MZ563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 25-Apr-25 End Date: 29-Apr-25
Note on NA563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 25-Apr-25 End Date: 29-Apr-25
Note on NB563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 25-Apr-25 End Date: 29-Apr-25
Note on NC563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 30-Apr-25 End Date: 05-May-25
Note on ND563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Layout Framing Start Date: 01-May-25 End Date: 01-May-25
Note on NE563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 30-Apr-25 End Date: 05-May-25
Note on NF563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 30-Apr-25 End Date: 05-May-25
Note on NG563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 30-Apr-25 End Date: 05-May-25
Note on NH563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 30-Apr-25 End Date: 05-May-25
Note on NI563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 06-May-25 End Date: 09-May-25
Note on NJ563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 06-May-25 End Date: 09-May-25
Note on NK563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 06-May-25 End Date: 09-May-25
Note on NL563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 06-May-25 End Date: 09-May-25
Note on NM563: Phase: Fitout Location: CELL 3 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 10-May-25 End Date: 13-May-25
Note on NN563: Phase: Fitout Location: CELL 3 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 10-May-25 End Date: 13-May-25
Note on NO563: Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 12-May-25 End Date: 15-May-25
Note on NP563: Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 12-May-25 End Date: 15-May-25
Note on NQ563: Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 12-May-25 End Date: 15-May-25
Note on NR563: Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 12-May-25 End Date: 15-May-25
Note on NS563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 16-May-25 End Date: 17-May-25
Note on NT563: Phase: Fitout Location: CELL 3 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 17-May-25 End Date: 20-May-25
Note on NU563: Phase: Fitout Location: CELL 3 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 17-May-25 End Date: 20-May-25
Note on NV563: Phase: Fitout Location: CELL 3 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 17-May-25 End Date: 20-May-25
Note on NW563: Phase: Fitout Location: CELL 3 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 17-May-25 End Date: 20-May-25
Note on NX563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 21-May-25 End Date: 23-May-25
Note on NY563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 21-May-25 End Date: 23-May-25
Note on NZ563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 23-May-25 End Date: 29-May-25
Note on OA563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 23-May-25 End Date: 29-May-25
Note on OB563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 23-May-25 End Date: 29-May-25
Note on OC563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 23-May-25 End Date: 29-May-25
Note on OD563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 23-May-25 End Date: 29-May-25
Note on OE563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 23-May-25 End Date: 29-May-25
Note on OF563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 23-May-25 End Date: 29-May-25
Note on OG563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 30-May-25 End Date: 03-Jun-25
Note on OH563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 30-May-25 End Date: 03-Jun-25
Note on OI563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 30-May-25 End Date: 03-Jun-25
Note on OJ563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 30-May-25 End Date: 03-Jun-25
Note on OK563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 30-May-25 End Date: 03-Jun-25
Note on OL563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 04-Jun-25 End Date: 07-Jun-25
Note on OM563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 04-Jun-25 End Date: 07-Jun-25
Note on ON563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 04-Jun-25 End Date: 07-Jun-25
Note on OO563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 04-Jun-25 End Date: 07-Jun-25
Note on OP563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Install Busways on HAC Arms Start Date: 06-Jun-25 End Date: 11-Jun-25
Note on OQ563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on OR563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on OS563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on OT563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 09-Jun-25 End Date: 12-Jun-25
Note on OU563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Start Date: 09-Jun-25 End Date: 13-Jun-25
Note on OX563: Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 16-Jun-25 End Date: 19-Jun-25
Note on OY563: Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 16-Jun-25 End Date: 19-Jun-25
Note on OZ563: Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 16-Jun-25 End Date: 19-Jun-25
Note on PA563: Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 16-Jun-25 End Date: 19-Jun-25
Note on PB563: Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 20-Jun-25 End Date: 24-Jun-25
Note on PC563: Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 20-Jun-25 End Date: 24-Jun-25
Note on PD563: Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 20-Jun-25 End Date: 24-Jun-25
Note on PE563: Phase: Fitout Location: CELL 3 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 20-Jun-25 End Date: 24-Jun-25
Note on PF563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 24-Jun-25 End Date: 26-Jun-25
Note on PG563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 24-Jun-25 End Date: 26-Jun-25
Note on PH563: Phase: Fitout Location: CELL 3 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 24-Jun-25 End Date: 26-Jun-25
Note on PI563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-Jun-25 End Date: 02-Jul-25
Note on PJ563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-Jun-25 End Date: 02-Jul-25
Note on PK563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-Jun-25 End Date: 02-Jul-25
Note on PL563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-Jun-25 End Date: 02-Jul-25
Note on PM563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-Jun-25 End Date: 02-Jul-25
Note on PN563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-Jun-25 End Date: 02-Jul-25
Note on QD563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 18-Jul-25 End Date: 21-Jul-25
Note on QE563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 18-Jul-25 End Date: 21-Jul-25
Note on QF563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 18-Jul-25 End Date: 21-Jul-25
Note on QG563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 18-Jul-25 End Date: 21-Jul-25
Note on QW563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 06-Aug-25 End Date: 08-Aug-25
Note on QX563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 06-Aug-25 End Date: 08-Aug-25
Note on QY563: Phase: Fitout Location: CELL 3 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 06-Aug-25 End Date: 08-Aug-25
Note on KR619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 26-Feb-25 End Date: 27-Feb-25
Note on KS619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 26-Feb-25 End Date: 27-Feb-25
Note on KT619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 28-Feb-25 End Date: 03-Mar-25
Note on KU619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 28-Feb-25 End Date: 03-Mar-25
Note on KV619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 28-Feb-25 End Date: 03-Mar-25
Note on KW619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 28-Feb-25 End Date: 03-Mar-25
Note on KX619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 04-Mar-25 End Date: 05-Mar-25
Note on KY619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 04-Mar-25 End Date: 05-Mar-25
Note on KZ619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on LA619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on LB619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 06-Mar-25 End Date: 08-Mar-25
Note on LC619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LD619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 10-Mar-25 End Date: 11-Mar-25
Note on LE619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 11-Mar-25 End Date: 12-Mar-25
Note on LF619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 11-Mar-25 End Date: 12-Mar-25
Note on LG619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Cx Activity Name: General Cleaning Start Date: 13-Mar-25 End Date: 13-Mar-25
Note on LH619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LI619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LJ619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LK619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LL619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on MA619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 02-Apr-25 End Date: 03-Apr-25
Note on MB619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 02-Apr-25 End Date: 03-Apr-25
Note on MC619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 04-Apr-25 End Date: 05-Apr-25
Note on MD619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 04-Apr-25 End Date: 05-Apr-25
Note on MF619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 07-Apr-25 End Date: 08-Apr-25
Note on MG619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 07-Apr-25 End Date: 08-Apr-25
Note on MH619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 09-Apr-25 End Date: 10-Apr-25
Note on MI619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 09-Apr-25 End Date: 10-Apr-25
Note on MJ619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 09-Apr-25 End Date: 11-Apr-25
Note on MK619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 11-Apr-25 End Date: 14-Apr-25
Note on ML619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 11-Apr-25 End Date: 14-Apr-25
Note on MM619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 14-Apr-25 End Date: 15-Apr-25
Note on MN619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 15-Apr-25 End Date: 16-Apr-25
Note on MO619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 15-Apr-25 End Date: 16-Apr-25
Note on MP619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Cx Activity Name: General Cleaning Start Date: 17-Apr-25 End Date: 17-Apr-25
Note on MQ619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MR619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MS619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MT619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MU619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on NJ619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 07-May-25 End Date: 08-May-25
Note on NK619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 07-May-25 End Date: 08-May-25
Note on NL619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 09-May-25 End Date: 10-May-25
Note on NM619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 10-May-25 End Date: 22-May-25
Note on NN619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 10-May-25 End Date: 22-May-25
Note on NO619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 10-May-25 End Date: 22-May-25
Note on NP619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 10-May-25 End Date: 22-May-25
Note on NQ619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 10-May-25 End Date: 22-May-25
Note on NR619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 10-May-25 End Date: 22-May-25
Note on NS619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 10-May-25 End Date: 22-May-25
Note on NT619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 10-May-25 End Date: 22-May-25
Note on NU619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 10-May-25 End Date: 22-May-25
Note on NV619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 10-May-25 End Date: 22-May-25
Note on NW619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 10-May-25 End Date: 22-May-25
Note on NX619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 10-May-25 End Date: 22-May-25
Note on NY619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 22-May-25 End Date: 27-May-25
Note on NZ619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 23-May-25 End Date: 28-May-25
Note on OA619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 23-May-25 End Date: 28-May-25
Note on OB619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 23-May-25 End Date: 28-May-25
Note on OC619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 23-May-25 End Date: 28-May-25
Note on OD619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 23-May-25 End Date: 28-May-25
Note on OE619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 23-May-25 End Date: 28-May-25
Note on OF619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 23-May-25 End Date: 04-Jun-25
Note on OG619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 23-May-25 End Date: 04-Jun-25
Note on OH619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 23-May-25 End Date: 04-Jun-25
Note on OI619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 23-May-25 End Date: 04-Jun-25
Note on OJ619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 23-May-25 End Date: 04-Jun-25
Note on OK619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 23-May-25 End Date: 04-Jun-25
Note on OL619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 23-May-25 End Date: 04-Jun-25
Note on PF619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PG619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PH619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PI619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PJ619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PK619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PL619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PM619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PN619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PO619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PP619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PQ619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PR619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PS619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PT619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 24-Jun-25 End Date: 08-Jul-25
Note on PU619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 09-Jul-25 End Date: 12-Jul-25
Note on PV619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 09-Jul-25 End Date: 12-Jul-25
Note on PW619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 09-Jul-25 End Date: 12-Jul-25
Note on PX619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 09-Jul-25 End Date: 12-Jul-25
Note on PY619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 09-Jul-25 End Date: 19-Jul-25
Note on PZ619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 09-Jul-25 End Date: 19-Jul-25
Note on QA619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 09-Jul-25 End Date: 19-Jul-25
Note on QB619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 09-Jul-25 End Date: 19-Jul-25
Note on QC619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 09-Jul-25 End Date: 19-Jul-25
Note on QD619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 09-Jul-25 End Date: 19-Jul-25
Note on QE619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 09-Jul-25 End Date: 19-Jul-25
Note on QF619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 11-Jul-25 End Date: 23-Jul-25
Note on QG619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 11-Jul-25 End Date: 23-Jul-25
Note on QH619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 11-Jul-25 End Date: 23-Jul-25
Note on QI619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 11-Jul-25 End Date: 23-Jul-25
Note on QJ619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on QK619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on QL619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on QM619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on QN619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on QO619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 24-Jul-25 End Date: 29-Jul-25
Note on QP619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 24-Jul-25 End Date: 05-Aug-25
Note on QQ619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 24-Jul-25 End Date: 05-Aug-25
Note on QR619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 24-Jul-25 End Date: 05-Aug-25
Note on QS619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 24-Jul-25 End Date: 05-Aug-25
Note on QT619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 24-Jul-25 End Date: 05-Aug-25
Note on QU619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 24-Jul-25 End Date: 05-Aug-25
Note on QV619: Phase: Fitout Location: CELL 3 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 24-Jul-25 End Date: 05-Aug-25
Note on KZ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on LA664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on LB664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LC664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LD664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LE664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 08-Mar-25 End Date: 11-Mar-25
Note on LF664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 12-Mar-25 End Date: 18-Mar-25
Note on LG664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 12-Mar-25 End Date: 18-Mar-25
Note on LH664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 12-Mar-25 End Date: 18-Mar-25
Note on LI664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 12-Mar-25 End Date: 18-Mar-25
Note on LJ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 12-Mar-25 End Date: 18-Mar-25
Note on LK664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 12-Mar-25 End Date: 18-Mar-25
Note on LL664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 12-Mar-25 End Date: 18-Mar-25
Note on LM664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 19-Mar-25 End Date: 26-Mar-25
Note on LN664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 19-Mar-25 End Date: 26-Mar-25
Note on LO664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 19-Mar-25 End Date: 26-Mar-25
Note on LP664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 19-Mar-25 End Date: 26-Mar-25
Note on LQ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 19-Mar-25 End Date: 26-Mar-25
Note on LR664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 19-Mar-25 End Date: 26-Mar-25
Note on LS664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 19-Mar-25 End Date: 26-Mar-25
Note on LT664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 19-Mar-25 End Date: 26-Mar-25
Note on LU664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 27-Mar-25 End Date: 28-Mar-25
Note on LV664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 28-Mar-25 End Date: 01-Apr-25
Note on LW664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 29-Mar-25 End Date: 31-Mar-25
Note on LX664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 29-Mar-25 End Date: 31-Mar-25
Note on LY664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 29-Mar-25 End Date: 31-Mar-25
Note on LZ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 28-Mar-25 End Date: 01-Apr-25
Note on MA664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 02-Apr-25 End Date: 03-Apr-25
Note on MB664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 02-Apr-25 End Date: 03-Apr-25
Note on MC664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 04-Apr-25 End Date: 08-Apr-25
Note on MD664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 04-Apr-25 End Date: 08-Apr-25
Note on ME664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 04-Apr-25 End Date: 08-Apr-25
Note on MF664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 04-Apr-25 End Date: 08-Apr-25
Note on MG664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 04-Apr-25 End Date: 08-Apr-25
Note on MH664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MI664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MJ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MK664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on ML664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MM664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MN664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MO664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MP664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MQ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MR664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MS664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MT664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MU664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MV664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 09-Apr-25 End Date: 23-Apr-25
Note on MW664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 24-Apr-25 End Date: 28-Apr-25
Note on MX664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 24-Apr-25 End Date: 28-Apr-25
Note on MY664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 24-Apr-25 End Date: 28-Apr-25
Note on MZ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 24-Apr-25 End Date: 28-Apr-25
Note on NA664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 24-Apr-25 End Date: 28-Apr-25
Note on NB664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 23-Apr-25 End Date: 29-Apr-25
Note on NC664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 30-Apr-25 End Date: 01-May-25
Note on ND664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 01-May-25 End Date: 06-May-25
Note on NE664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 02-May-25 End Date: 05-May-25
Note on NF664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 02-May-25 End Date: 05-May-25
Note on NG664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 02-May-25 End Date: 05-May-25
Note on NH664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 02-May-25 End Date: 05-May-25
Note on NI664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 01-May-25 End Date: 06-May-25
Note on NJ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 07-May-25 End Date: 08-May-25
Note on NK664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 07-May-25 End Date: 08-May-25
Note on NL664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 09-May-25 End Date: 13-May-25
Note on NM664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 09-May-25 End Date: 13-May-25
Note on NN664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 09-May-25 End Date: 13-May-25
Note on NO664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 09-May-25 End Date: 13-May-25
Note on NP664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 09-May-25 End Date: 13-May-25
Note on NQ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on NR664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on NS664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on NT664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on NU664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on NV664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on NW664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on NX664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on NY664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on NZ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on OA664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on OB664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on OC664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on OD664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on OE664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 14-May-25 End Date: 28-May-25
Note on OF664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 29-May-25 End Date: 02-Jun-25
Note on OG664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 29-May-25 End Date: 02-Jun-25
Note on OH664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 29-May-25 End Date: 02-Jun-25
Note on OI664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 29-May-25 End Date: 02-Jun-25
Note on OJ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 29-May-25 End Date: 02-Jun-25
Note on OK664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 28-May-25 End Date: 03-Jun-25
Note on OL664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 04-Jun-25 End Date: 05-Jun-25
Note on OM664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 05-Jun-25 End Date: 09-Jun-25
Note on ON664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 06-Jun-25 End Date: 07-Jun-25
Note on OO664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 06-Jun-25 End Date: 07-Jun-25
Note on OP664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 05-Jun-25 End Date: 09-Jun-25
Note on OQ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 05-Jun-25 End Date: 09-Jun-25
Note on OR664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 10-Jun-25 End Date: 11-Jun-25
Note on OS664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 10-Jun-25 End Date: 11-Jun-25
Note on OT664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on OU664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on OV664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on OW664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on OX664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on OY664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-Jun-25 End Date: 17-Jun-25
Note on OZ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PA664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PB664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PC664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PD664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PE664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PF664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PG664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PH664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PI664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PJ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PK664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PL664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PM664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 18-Jun-25 End Date: 01-Jul-25
Note on PN664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 02-Jul-25 End Date: 08-Jul-25
Note on PO664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 02-Jul-25 End Date: 08-Jul-25
Note on PP664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 02-Jul-25 End Date: 08-Jul-25
Note on PQ664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 02-Jul-25 End Date: 08-Jul-25
Note on PR664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 02-Jul-25 End Date: 08-Jul-25
Note on PS664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 02-Jul-25 End Date: 08-Jul-25
Note on PT664: Phase: Fitout Location: CELL 3 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 02-Jul-25 End Date: 08-Jul-25
Note on OQ715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Jun-25 End Date: 20-Jun-25
Note on OR715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Jun-25 End Date: 20-Jun-25
Note on OS715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Jun-25 End Date: 20-Jun-25
Note on OT715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Jun-25 End Date: 20-Jun-25
Note on OU715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Jun-25 End Date: 20-Jun-25
Note on OV715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Jun-25 End Date: 20-Jun-25
Note on OW715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Jun-25 End Date: 20-Jun-25
Note on OX715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Jun-25 End Date: 20-Jun-25
Note on OY715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Jun-25 End Date: 20-Jun-25
Note on OZ715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Jun-25 End Date: 20-Jun-25
Note on PA715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Jun-25 End Date: 20-Jun-25
Note on PB715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Jun-25 End Date: 20-Jun-25
Note on QH715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 22-Jul-25 End Date: 02-Aug-25
Note on QI715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 22-Jul-25 End Date: 02-Aug-25
Note on QJ715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 22-Jul-25 End Date: 02-Aug-25
Note on QK715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 22-Jul-25 End Date: 02-Aug-25
Note on QL715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 22-Jul-25 End Date: 02-Aug-25
Note on QM715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 22-Jul-25 End Date: 02-Aug-25
Note on QN715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 22-Jul-25 End Date: 02-Aug-25
Note on QO715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 22-Jul-25 End Date: 02-Aug-25
Note on QP715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 22-Jul-25 End Date: 02-Aug-25
Note on QQ715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 22-Jul-25 End Date: 02-Aug-25
Note on QR715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 22-Jul-25 End Date: 02-Aug-25
Note on QS715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 22-Jul-25 End Date: 02-Aug-25
Note on QZ715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on RA715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on RB715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on RC715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on RD715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on RE715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on RF715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on RG715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on RH715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on RI715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on RJ715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on RK715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on RL715: Phase: Fitout Location: CELL 3 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 09-Aug-25 End Date: 21-Aug-25
Note on KB718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Layout Framing Start Date: 10-Feb-25 End Date: 10-Feb-25
Note on KC718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 11-Feb-25 End Date: 13-Feb-25
Note on KD718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 11-Feb-25 End Date: 13-Feb-25
Note on KE718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 11-Feb-25 End Date: 13-Feb-25
Note on KF718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 14-Feb-25 End Date: 17-Feb-25
Note on KG718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 14-Feb-25 End Date: 17-Feb-25
Note on KH718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 14-Feb-25 End Date: 17-Feb-25
Note on KI718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 14-Feb-25 End Date: 17-Feb-25
Note on KJ718: Phase: Fitout Location: CELL 4 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 18-Feb-25 End Date: 20-Feb-25
Note on KK718: Phase: Fitout Location: CELL 4 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 18-Feb-25 End Date: 20-Feb-25
Note on KL718: Phase: Fitout Location: CELL 4 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 18-Feb-25 End Date: 20-Feb-25
Note on KM718: Phase: Fitout Location: CELL 4 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 21-Feb-25 End Date: 24-Feb-25
Note on KN718: Phase: Fitout Location: CELL 4 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 21-Feb-25 End Date: 24-Feb-25
Note on KO718: Phase: Fitout Location: CELL 4 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 21-Feb-25 End Date: 24-Feb-25
Note on KP718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 24-Feb-25 End Date: 25-Feb-25
Note on KQ718: Phase: Fitout Location: CELL 4 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 25-Feb-25 End Date: 27-Feb-25
Note on KR718: Phase: Fitout Location: CELL 4 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 25-Feb-25 End Date: 27-Feb-25
Note on KS718: Phase: Fitout Location: CELL 4 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 25-Feb-25 End Date: 27-Feb-25
Note on KT718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KU718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KV718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KW718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KX718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KY718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 05-Mar-25 End Date: 06-Mar-25
Note on KZ718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 05-Mar-25 End Date: 06-Mar-25
Note on LA718: Phase: Fitout Location: CELL 4 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 07-Mar-25 End Date: 08-Mar-25
Note on LB718: Phase: Fitout Location: CELL 4 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 07-Mar-25 End Date: 08-Mar-25
Note on LD718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 10-Mar-25 End Date: 13-Mar-25
Note on LE718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 10-Mar-25 End Date: 13-Mar-25
Note on LF718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 10-Mar-25 End Date: 13-Mar-25
Note on LG718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 10-Mar-25 End Date: 13-Mar-25
Note on LH718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LI718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Layout Framing Start Date: 15-Mar-25 End Date: 15-Mar-25
Note on LJ718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LK718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LL718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LM718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 19-Mar-25 End Date: 24-Mar-25
Note on LN718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 19-Mar-25 End Date: 24-Mar-25
Note on LO718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 19-Mar-25 End Date: 24-Mar-25
Note on LP718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 19-Mar-25 End Date: 24-Mar-25
Note on LQ718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 19-Mar-25 End Date: 24-Mar-25
Note on LR718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 19-Mar-25 End Date: 24-Mar-25
Note on LS718: Phase: Fitout Location: CELL 4 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 25-Mar-25 End Date: 27-Mar-25
Note on LT718: Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 26-Mar-25 End Date: 29-Mar-25
Note on LU718: Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 26-Mar-25 End Date: 29-Mar-25
Note on LV718: Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 26-Mar-25 End Date: 29-Mar-25
Note on LW718: Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 26-Mar-25 End Date: 29-Mar-25
Note on LX718: Phase: Fitout Location: CELL 4 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 28-Mar-25 End Date: 31-Mar-25
Note on LY718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 31-Mar-25 End Date: 01-Apr-25
Note on LZ718: Phase: Fitout Location: CELL 4 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 01-Apr-25 End Date: 03-Apr-25
Note on MA718: Phase: Fitout Location: CELL 4 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 01-Apr-25 End Date: 03-Apr-25
Note on MB718: Phase: Fitout Location: CELL 4 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 01-Apr-25 End Date: 03-Apr-25
Note on MC718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 04-Apr-25 End Date: 07-Apr-25
Note on MD718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 04-Apr-25 End Date: 07-Apr-25
Note on ME718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 04-Apr-25 End Date: 07-Apr-25
Note on MF718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 07-Apr-25 End Date: 11-Apr-25
Note on MG718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 07-Apr-25 End Date: 11-Apr-25
Note on MH718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 07-Apr-25 End Date: 11-Apr-25
Note on MI718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 07-Apr-25 End Date: 11-Apr-25
Note on MJ718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 07-Apr-25 End Date: 11-Apr-25
Note on MM718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 14-Apr-25 End Date: 17-Apr-25
Note on MN718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 14-Apr-25 End Date: 17-Apr-25
Note on MO718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 14-Apr-25 End Date: 17-Apr-25
Note on MP718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 14-Apr-25 End Date: 17-Apr-25
Note on MQ718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MR718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MS718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MT718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MU718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 18-Apr-25 End Date: 22-Apr-25
Note on MV718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 23-Apr-25 End Date: 26-Apr-25
Note on MW718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 23-Apr-25 End Date: 26-Apr-25
Note on MX718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 23-Apr-25 End Date: 26-Apr-25
Note on MY718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 23-Apr-25 End Date: 26-Apr-25
Note on MZ718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Start Date: 23-Apr-25 End Date: 28-Apr-25
Note on NA718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Start Date: 23-Apr-25 End Date: 28-Apr-25
Note on NB718: Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 29-Apr-25 End Date: 02-May-25
Note on NC718: Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 29-Apr-25 End Date: 02-May-25
Note on ND718: Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 29-Apr-25 End Date: 02-May-25
Note on NE718: Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 29-Apr-25 End Date: 02-May-25
Note on NH718: Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 05-May-25 End Date: 08-May-25
Note on NI718: Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 05-May-25 End Date: 08-May-25
Note on NJ718: Phase: Fitout Location: CELL 4 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 05-May-25 End Date: 08-May-25
Note on NK718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 08-May-25 End Date: 10-May-25
Note on NL718: Phase: Fitout Location: CELL 4 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 08-May-25 End Date: 10-May-25
Note on NM718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 10-May-25 End Date: 13-May-25
Note on NN718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 10-May-25 End Date: 13-May-25
Note on NO718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 10-May-25 End Date: 13-May-25
Note on NP718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 10-May-25 End Date: 13-May-25
Note on NQ718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 12-May-25 End Date: 16-May-25
Note on NR718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 12-May-25 End Date: 16-May-25
Note on NS718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 12-May-25 End Date: 16-May-25
Note on PF718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 24-Jun-25 End Date: 26-Jun-25
Note on PG718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 24-Jun-25 End Date: 26-Jun-25
Note on PH718: Phase: Fitout Location: CELL 4 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 24-Jun-25 End Date: 26-Jun-25
Note on MR774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Layout Framing Start Date: 19-Apr-25 End Date: 19-Apr-25
Note on MT774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Framing Start Date: 21-Apr-25 End Date: 23-Apr-25
Note on MU774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Framing Start Date: 21-Apr-25 End Date: 23-Apr-25
Note on MV774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Framing Start Date: 21-Apr-25 End Date: 23-Apr-25
Note on MW774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: In-Wall R/I Start Date: 24-Apr-25 End Date: 26-Apr-25
Note on MX774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: In-Wall R/I Start Date: 24-Apr-25 End Date: 26-Apr-25
Note on MY774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: In-Wall R/I Start Date: 24-Apr-25 End Date: 26-Apr-25
Note on NA774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 28-Apr-25 End Date: 30-Apr-25
Note on NB774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 28-Apr-25 End Date: 30-Apr-25
Note on NC774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 28-Apr-25 End Date: 30-Apr-25
Note on ND774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 01-May-25 End Date: 05-May-25
Note on NE774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 01-May-25 End Date: 05-May-25
Note on NF774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 01-May-25 End Date: 05-May-25
Note on NG774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 01-May-25 End Date: 05-May-25
Note on NH774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 05-May-25 End Date: 06-May-25
Note on NI774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 06-May-25 End Date: 08-May-25
Note on NJ774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 06-May-25 End Date: 08-May-25
Note on NK774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 06-May-25 End Date: 08-May-25
Note on NL774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 09-May-25 End Date: 12-May-25
Note on NM774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 09-May-25 End Date: 12-May-25
Note on NN774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 09-May-25 End Date: 12-May-25
Note on NO774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 09-May-25 End Date: 12-May-25
Note on NP774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Secondary Steel Start Date: 13-May-25 End Date: 14-May-25
Note on NQ774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Secondary Steel Start Date: 13-May-25 End Date: 14-May-25
Note on NR774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 15-May-25 End Date: 16-May-25
Note on NS774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 15-May-25 End Date: 16-May-25
Note on NT774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Ceiling Grid Start Date: 17-May-25 End Date: 21-May-25
Note on NU774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Ceiling Grid Start Date: 17-May-25 End Date: 21-May-25
Note on NV774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Ceiling Grid Start Date: 17-May-25 End Date: 21-May-25
Note on NW774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Ceiling Grid Start Date: 17-May-25 End Date: 21-May-25
Note on NX774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Ceiling Grid Start Date: 17-May-25 End Date: 21-May-25
Note on NY774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 22-May-25 End Date: 27-May-25
Note on NZ774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 22-May-25 End Date: 27-May-25
Note on OA774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 22-May-25 End Date: 27-May-25
Note on OB774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 22-May-25 End Date: 27-May-25
Note on OC774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 22-May-25 End Date: 27-May-25
Note on OD774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 22-May-25 End Date: 27-May-25
Note on OE774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: Set PDUs Start Date: 28-May-25 End Date: 31-May-25
Note on OF774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: Set PDUs Start Date: 28-May-25 End Date: 31-May-25
Note on OG774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: Set PDUs Start Date: 28-May-25 End Date: 31-May-25
Note on OH774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: Set PDUs Start Date: 28-May-25 End Date: 31-May-25
Note on OI774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Start Date: 28-May-25 End Date: 02-Jun-25
Note on OJ774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Start Date: 28-May-25 End Date: 02-Jun-25
Note on OK774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: HAC's Activity Name: Raise HACs Start Date: 03-Jun-25 End Date: 06-Jun-25
Note on OL774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: HAC's Activity Name: Raise HACs Start Date: 03-Jun-25 End Date: 06-Jun-25
Note on OM774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: HAC's Activity Name: Raise HACs Start Date: 03-Jun-25 End Date: 06-Jun-25
Note on ON774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: HAC's Activity Name: Raise HACs Start Date: 03-Jun-25 End Date: 06-Jun-25
Note on OO774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: HAC's Activity Name: Detail HACs Start Date: 07-Jun-25 End Date: 11-Jun-25
Note on OP774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: HAC's Activity Name: Detail HACs Start Date: 07-Jun-25 End Date: 11-Jun-25
Note on OQ774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: HAC's Activity Name: Detail HACs Start Date: 07-Jun-25 End Date: 11-Jun-25
Note on OR774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: HAC's Activity Name: Detail HACs Start Date: 07-Jun-25 End Date: 11-Jun-25
Note on OS774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 11-Jun-25 End Date: 13-Jun-25
Note on OT774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 11-Jun-25 End Date: 13-Jun-25
Note on OU774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 11-Jun-25 End Date: 13-Jun-25
Note on OX774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 16-Jun-25 End Date: 20-Jun-25
Note on OY774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 16-Jun-25 End Date: 20-Jun-25
Note on OZ774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 16-Jun-25 End Date: 20-Jun-25
Note on PA774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 16-Jun-25 End Date: 20-Jun-25
Note on PB774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 16-Jun-25 End Date: 20-Jun-25
Note on PW774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: Terminate PDUs Start Date: 11-Jul-25 End Date: 14-Jul-25
Note on PX774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: Terminate PDUs Start Date: 11-Jul-25 End Date: 14-Jul-25
Note on PY774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: Terminate PDUs Start Date: 11-Jul-25 End Date: 14-Jul-25
Note on PZ774: Phase: Fitout Location: CELL 4 Data Hall Fitout Activities Trade: Electrical Activity Name: Terminate PDUs Start Date: 11-Jul-25 End Date: 14-Jul-25
Note on KF802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 14-Feb-25 End Date: 15-Feb-25
Note on KG802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 14-Feb-25 End Date: 15-Feb-25
Note on KI802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 17-Feb-25 End Date: 18-Feb-25
Note on KJ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 17-Feb-25 End Date: 18-Feb-25
Note on KK802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 19-Feb-25 End Date: 20-Feb-25
Note on KL802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 19-Feb-25 End Date: 20-Feb-25
Note on KM802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 21-Feb-25 End Date: 22-Feb-25
Note on KN802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 21-Feb-25 End Date: 22-Feb-25
Note on KO802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 21-Feb-25 End Date: 24-Feb-25
Note on KP802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 21-Feb-25 End Date: 24-Feb-25
Note on KQ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 25-Feb-25 End Date: 26-Feb-25
Note on KR802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 26-Feb-25 End Date: 27-Feb-25
Note on KS802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 26-Feb-25 End Date: 27-Feb-25
Note on KT802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Cx Activity Name: General Cleaning Start Date: 28-Feb-25 End Date: 28-Feb-25
Note on KW802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 03-Mar-25 End Date: 06-Mar-25
Note on KX802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 03-Mar-25 End Date: 06-Mar-25
Note on KY802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 03-Mar-25 End Date: 06-Mar-25
Note on KZ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 03-Mar-25 End Date: 06-Mar-25
Note on LA802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LB802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LC802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LD802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LE802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LF802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LG802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LH802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LI802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LJ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LK802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LL802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LM802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 07-Mar-25 End Date: 19-Mar-25
Note on LN802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 20-Mar-25 End Date: 25-Mar-25
Note on LO802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 20-Mar-25 End Date: 25-Mar-25
Note on LP802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 20-Mar-25 End Date: 25-Mar-25
Note on LQ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 20-Mar-25 End Date: 25-Mar-25
Note on LR802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 20-Mar-25 End Date: 25-Mar-25
Note on LS802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 20-Mar-25 End Date: 25-Mar-25
Note on LT802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 26-Mar-25 End Date: 27-Mar-25
Note on LU802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 26-Mar-25 End Date: 27-Mar-25
Note on LV802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 28-Mar-25 End Date: 29-Mar-25
Note on LW802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 28-Mar-25 End Date: 29-Mar-25
Note on LX802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 28-Mar-25 End Date: 31-Mar-25
Note on LY802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 28-Mar-25 End Date: 31-Mar-25
Note on LZ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 01-Apr-25 End Date: 02-Apr-25
Note on MA802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 02-Apr-25 End Date: 03-Apr-25
Note on MB802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 02-Apr-25 End Date: 03-Apr-25
Note on MC802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Cx Activity Name: General Cleaning Start Date: 04-Apr-25 End Date: 04-Apr-25
Note on MD802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 05-Apr-25 End Date: 09-Apr-25
Note on ME802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 05-Apr-25 End Date: 09-Apr-25
Note on MF802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 05-Apr-25 End Date: 09-Apr-25
Note on MG802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 05-Apr-25 End Date: 09-Apr-25
Note on MH802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 05-Apr-25 End Date: 09-Apr-25
Note on MW802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 24-Apr-25 End Date: 25-Apr-25
Note on MX802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 24-Apr-25 End Date: 25-Apr-25
Note on MY802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on MZ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on NA802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on NB802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on NC802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on ND802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on NE802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on NF802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on NG802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on NH802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on NI802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on NJ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on NK802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on NL802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Apr-25 End Date: 09-May-25
Note on NM802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 10-May-25 End Date: 14-May-25
Note on NN802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 10-May-25 End Date: 14-May-25
Note on NO802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 10-May-25 End Date: 14-May-25
Note on NP802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 10-May-25 End Date: 14-May-25
Note on NQ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 10-May-25 End Date: 14-May-25
Note on OE802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 28-May-25 End Date: 09-Jun-25
Note on OF802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 28-May-25 End Date: 09-Jun-25
Note on OG802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 28-May-25 End Date: 09-Jun-25
Note on OH802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 28-May-25 End Date: 09-Jun-25
Note on OI802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 28-May-25 End Date: 09-Jun-25
Note on OJ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 28-May-25 End Date: 09-Jun-25
Note on OK802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 28-May-25 End Date: 09-Jun-25
Note on OL802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 28-May-25 End Date: 09-Jun-25
Note on OM802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 28-May-25 End Date: 09-Jun-25
Note on ON802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 28-May-25 End Date: 09-Jun-25
Note on OO802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 28-May-25 End Date: 09-Jun-25
Note on OP802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 28-May-25 End Date: 09-Jun-25
Note on OQ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 28-May-25 End Date: 09-Jun-25
Note on OR802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 10-Jun-25 End Date: 13-Jun-25
Note on OS802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 10-Jun-25 End Date: 13-Jun-25
Note on OT802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 10-Jun-25 End Date: 13-Jun-25
Note on OU802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 10-Jun-25 End Date: 13-Jun-25
Note on OV802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 10-Jun-25 End Date: 23-Jun-25
Note on OW802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 10-Jun-25 End Date: 23-Jun-25
Note on OX802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 10-Jun-25 End Date: 23-Jun-25
Note on OY802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 10-Jun-25 End Date: 23-Jun-25
Note on OZ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 10-Jun-25 End Date: 23-Jun-25
Note on PA802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 10-Jun-25 End Date: 23-Jun-25
Note on PB802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 10-Jun-25 End Date: 23-Jun-25
Note on PC802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 10-Jun-25 End Date: 23-Jun-25
Note on PD802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 10-Jun-25 End Date: 23-Jun-25
Note on PE802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 10-Jun-25 End Date: 23-Jun-25
Note on PF802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 12-Jun-25 End Date: 25-Jun-25
Note on PG802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 2 Start Date: 12-Jun-25 End Date: 25-Jun-25
Note on PH802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 26-Jun-25 End Date: 30-Jun-25
Note on PI802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 26-Jun-25 End Date: 30-Jun-25
Note on PJ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 26-Jun-25 End Date: 30-Jun-25
Note on PK802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 26-Jun-25 End Date: 30-Jun-25
Note on PL802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 26-Jun-25 End Date: 30-Jun-25
Note on PM802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Jun-25 End Date: 10-Jul-25
Note on PN802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Jun-25 End Date: 10-Jul-25
Note on PO802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Jun-25 End Date: 10-Jul-25
Note on PP802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Jun-25 End Date: 10-Jul-25
Note on PQ802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Jun-25 End Date: 10-Jul-25
Note on PR802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Jun-25 End Date: 10-Jul-25
Note on PS802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Jun-25 End Date: 10-Jul-25
Note on PT802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Jun-25 End Date: 10-Jul-25
Note on PU802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Jun-25 End Date: 10-Jul-25
Note on PV802: Phase: Fitout Location: CELL 4 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 2 Start Date: 26-Jun-25 End Date: 10-Jul-25
Note on KM847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 21-Feb-25 End Date: 22-Feb-25
Note on KN847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 21-Feb-25 End Date: 22-Feb-25
Note on KP847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 24-Feb-25 End Date: 25-Feb-25
Note on KQ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 24-Feb-25 End Date: 25-Feb-25
Note on KR847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 24-Feb-25 End Date: 26-Feb-25
Note on KS847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 27-Feb-25 End Date: 06-Mar-25
Note on KT847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 27-Feb-25 End Date: 06-Mar-25
Note on KU847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 27-Feb-25 End Date: 06-Mar-25
Note on KV847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 27-Feb-25 End Date: 06-Mar-25
Note on KW847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 27-Feb-25 End Date: 06-Mar-25
Note on KX847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 27-Feb-25 End Date: 06-Mar-25
Note on KY847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 27-Feb-25 End Date: 06-Mar-25
Note on KZ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 27-Feb-25 End Date: 06-Mar-25
Note on LA847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 07-Mar-25 End Date: 13-Mar-25
Note on LB847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 07-Mar-25 End Date: 13-Mar-25
Note on LC847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 07-Mar-25 End Date: 13-Mar-25
Note on LD847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 07-Mar-25 End Date: 13-Mar-25
Note on LE847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 07-Mar-25 End Date: 13-Mar-25
Note on LF847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 07-Mar-25 End Date: 13-Mar-25
Note on LG847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 07-Mar-25 End Date: 13-Mar-25
Note on LH847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 14-Mar-25 End Date: 15-Mar-25
Note on LI847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 15-Mar-25 End Date: 19-Mar-25
Note on LJ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 15-Mar-25 End Date: 19-Mar-25
Note on LK847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 17-Mar-25 End Date: 18-Mar-25
Note on LL847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 17-Mar-25 End Date: 18-Mar-25
Note on LM847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 15-Mar-25 End Date: 19-Mar-25
Note on LN847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 20-Mar-25 End Date: 21-Mar-25
Note on LO847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 20-Mar-25 End Date: 21-Mar-25
Note on LP847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: BAS Activity Name: Install BAS Equipments Start Date: 20-Mar-25 End Date: 01-Apr-25
Note on LQ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: BAS Activity Name: Install BAS Equipments Start Date: 20-Mar-25 End Date: 01-Apr-25
Note on LR847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 24-Mar-25 End Date: 27-Mar-25
Note on LS847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 24-Mar-25 End Date: 27-Mar-25
Note on LT847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 24-Mar-25 End Date: 27-Mar-25
Note on LU847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 24-Mar-25 End Date: 27-Mar-25
Note on LV847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on LW847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on LX847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on LY847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on LZ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on MA847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on MB847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on MC847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on MD847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on ME847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on MF847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on MG847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on MH847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on MI847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 28-Mar-25 End Date: 10-Apr-25
Note on MJ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MK847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on ML847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MM847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MN847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MO847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MP847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 10-Apr-25 End Date: 17-Apr-25
Note on MQ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 18-Apr-25 End Date: 19-Apr-25
Note on MR847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 19-Apr-25 End Date: 23-Apr-25
Note on MS847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 19-Apr-25 End Date: 23-Apr-25
Note on MT847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 21-Apr-25 End Date: 22-Apr-25
Note on MU847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 21-Apr-25 End Date: 22-Apr-25
Note on MV847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 19-Apr-25 End Date: 23-Apr-25
Note on MW847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 24-Apr-25 End Date: 25-Apr-25
Note on MX847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 24-Apr-25 End Date: 25-Apr-25
Note on MY847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on MZ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on NA847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on NB847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on NC847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on ND847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NE847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NF847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NG847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NH847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NI847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NJ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NK847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NL847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NM847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NN847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NO847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NP847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NQ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NR847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 01-May-25 End Date: 15-May-25
Note on NS847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 16-May-25 End Date: 20-May-25
Note on NT847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 16-May-25 End Date: 20-May-25
Note on NU847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 16-May-25 End Date: 20-May-25
Note on NV847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 16-May-25 End Date: 20-May-25
Note on NW847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 16-May-25 End Date: 20-May-25
Note on NX847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 15-May-25 End Date: 21-May-25
Note on NY847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 22-May-25 End Date: 23-May-25
Note on NZ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 23-May-25 End Date: 28-May-25
Note on OA847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 23-May-25 End Date: 28-May-25
Note on OB847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 23-May-25 End Date: 28-May-25
Note on OC847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 23-May-25 End Date: 28-May-25
Note on OD847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 27-May-25 End Date: 27-May-25
Note on OE847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 23-May-25 End Date: 28-May-25
Note on OF847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 29-May-25 End Date: 30-May-25
Note on OG847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 29-May-25 End Date: 30-May-25
Note on OH847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 31-May-25 End Date: 04-Jun-25
Note on OI847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 31-May-25 End Date: 04-Jun-25
Note on OJ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 31-May-25 End Date: 04-Jun-25
Note on OK847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 31-May-25 End Date: 04-Jun-25
Note on OL847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 31-May-25 End Date: 04-Jun-25
Note on OM847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on ON847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on OO847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on OP847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on OQ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on OR847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on OS847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on OT847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on OU847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on OV847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on OW847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on OX847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on OY847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on OZ847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on PA847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 05-Jun-25 End Date: 19-Jun-25
Note on PB847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 20-Jun-25 End Date: 24-Jun-25
Note on PC847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 20-Jun-25 End Date: 24-Jun-25
Note on PD847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 20-Jun-25 End Date: 24-Jun-25
Note on PE847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 20-Jun-25 End Date: 24-Jun-25
Note on PF847: Phase: Fitout Location: CELL 4 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 20-Jun-25 End Date: 24-Jun-25
Note on NM898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 10-May-25 End Date: 21-May-25
Note on NN898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 10-May-25 End Date: 21-May-25
Note on NO898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 10-May-25 End Date: 21-May-25
Note on NP898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 10-May-25 End Date: 21-May-25
Note on NQ898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 10-May-25 End Date: 21-May-25
Note on NR898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 10-May-25 End Date: 21-May-25
Note on NS898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 10-May-25 End Date: 21-May-25
Note on NT898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 10-May-25 End Date: 21-May-25
Note on NU898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 10-May-25 End Date: 21-May-25
Note on NV898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 10-May-25 End Date: 21-May-25
Note on NW898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 10-May-25 End Date: 21-May-25
Note on NX898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 10-May-25 End Date: 21-May-25
Note on PI898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PJ898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PK898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PL898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PM898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PN898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PO898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PP898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PQ898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PR898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PS898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PT898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PU898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on PV898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 27-Jun-25 End Date: 10-Jul-25
Note on QA898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 15-Jul-25 End Date: 25-Jul-25
Note on QB898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 15-Jul-25 End Date: 25-Jul-25
Note on QC898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 15-Jul-25 End Date: 25-Jul-25
Note on QD898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 15-Jul-25 End Date: 25-Jul-25
Note on QE898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 15-Jul-25 End Date: 25-Jul-25
Note on QF898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 15-Jul-25 End Date: 25-Jul-25
Note on QG898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 15-Jul-25 End Date: 25-Jul-25
Note on QH898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 15-Jul-25 End Date: 25-Jul-25
Note on QI898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 15-Jul-25 End Date: 25-Jul-25
Note on QJ898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 15-Jul-25 End Date: 25-Jul-25
Note on QK898: Phase: Fitout Location: CELL 4 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 15-Jul-25 End Date: 25-Jul-25
Note on JD901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Layout Framing Start Date: 17-Jan-25 End Date: 17-Jan-25
Note on JG901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 20-Jan-25 End Date: 24-Jan-25
Note on JH901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 20-Jan-25 End Date: 24-Jan-25
Note on JI901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 20-Jan-25 End Date: 24-Jan-25
Note on JJ901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 20-Jan-25 End Date: 24-Jan-25
Note on JK901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 20-Jan-25 End Date: 24-Jan-25
Note on JL901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 25-Jan-25 End Date: 28-Jan-25
Note on JM901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 25-Jan-25 End Date: 28-Jan-25
Note on JN901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 25-Jan-25 End Date: 28-Jan-25
Note on JO901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 25-Jan-25 End Date: 28-Jan-25
Note on JP901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 29-Jan-25 End Date: 31-Jan-25
Note on JQ901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 29-Jan-25 End Date: 31-Jan-25
Note on JR901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 29-Jan-25 End Date: 31-Jan-25
Note on JS901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 01-Feb-25 End Date: 04-Feb-25
Note on JT901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 01-Feb-25 End Date: 04-Feb-25
Note on JU901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 01-Feb-25 End Date: 04-Feb-25
Note on JV901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 04-Feb-25 End Date: 05-Feb-25
Note on JW901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 05-Feb-25 End Date: 07-Feb-25
Note on JX901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 05-Feb-25 End Date: 07-Feb-25
Note on JY901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 05-Feb-25 End Date: 07-Feb-25
Note on KB901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 10-Feb-25 End Date: 12-Feb-25
Note on KC901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 10-Feb-25 End Date: 12-Feb-25
Note on KD901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 10-Feb-25 End Date: 12-Feb-25
Note on KE901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KF901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KG901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KH901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KI901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KJ901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on KK901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on KL901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on KM901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on KN901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 22-Feb-25 End Date: 26-Feb-25
Note on KO901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 22-Feb-25 End Date: 26-Feb-25
Note on KP901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 22-Feb-25 End Date: 26-Feb-25
Note on KQ901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 22-Feb-25 End Date: 26-Feb-25
Note on KR901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 22-Feb-25 End Date: 26-Feb-25
Note on KS901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 27-Feb-25 End Date: 04-Mar-25
Note on KT901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 27-Feb-25 End Date: 04-Mar-25
Note on KU901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 27-Feb-25 End Date: 04-Mar-25
Note on KV901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 27-Feb-25 End Date: 04-Mar-25
Note on KW901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 27-Feb-25 End Date: 04-Mar-25
Note on KX901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 27-Feb-25 End Date: 04-Mar-25
Note on KY901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Start Date: 27-Feb-25 End Date: 05-Mar-25
Note on KZ901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 06-Mar-25 End Date: 10-Mar-25
Note on LA901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 06-Mar-25 End Date: 10-Mar-25
Note on LB901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 06-Mar-25 End Date: 10-Mar-25
Note on LC901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 06-Mar-25 End Date: 10-Mar-25
Note on LD901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 06-Mar-25 End Date: 10-Mar-25
Note on LE901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 11-Mar-25 End Date: 14-Mar-25
Note on LF901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 11-Mar-25 End Date: 14-Mar-25
Note on LG901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 11-Mar-25 End Date: 14-Mar-25
Note on LH901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 14-Mar-25 End Date: 17-Mar-25
Note on LI901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 14-Mar-25 End Date: 17-Mar-25
Note on LJ901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 14-Mar-25 End Date: 17-Mar-25
Note on LK901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 14-Mar-25 End Date: 17-Mar-25
Note on LL901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 18-Mar-25 End Date: 24-Mar-25
Note on LM901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 18-Mar-25 End Date: 24-Mar-25
Note on LN901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 18-Mar-25 End Date: 24-Mar-25
Note on LO901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 18-Mar-25 End Date: 24-Mar-25
Note on LP901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 18-Mar-25 End Date: 24-Mar-25
Note on LQ901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 18-Mar-25 End Date: 24-Mar-25
Note on LR901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 18-Mar-25 End Date: 24-Mar-25
Note on MM901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 14-Apr-25 End Date: 16-Apr-25
Note on MN901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 14-Apr-25 End Date: 16-Apr-25
Note on MO901: Phase: Fitout Location: COLO 3 - CELL 1 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 14-Apr-25 End Date: 16-Apr-25
Note on JL929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 25-Jan-25 End Date: 30-Jan-25
Note on JM929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 25-Jan-25 End Date: 30-Jan-25
Note on JN929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 25-Jan-25 End Date: 30-Jan-25
Note on JO929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 25-Jan-25 End Date: 30-Jan-25
Note on JP929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 25-Jan-25 End Date: 30-Jan-25
Note on JQ929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 25-Jan-25 End Date: 30-Jan-25
Note on JR929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 31-Jan-25 End Date: 10-Feb-25
Note on JS929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 31-Jan-25 End Date: 10-Feb-25
Note on JT929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 31-Jan-25 End Date: 10-Feb-25
Note on JU929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 31-Jan-25 End Date: 10-Feb-25
Note on JV929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 31-Jan-25 End Date: 10-Feb-25
Note on JW929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 31-Jan-25 End Date: 10-Feb-25
Note on JX929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 31-Jan-25 End Date: 10-Feb-25
Note on JY929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 31-Jan-25 End Date: 10-Feb-25
Note on JZ929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 31-Jan-25 End Date: 10-Feb-25
Note on KA929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 31-Jan-25 End Date: 10-Feb-25
Note on KB929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 31-Jan-25 End Date: 10-Feb-25
Note on KC929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on KD929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on KE929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KF929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KG929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 13-Feb-25 End Date: 15-Feb-25
Note on KH929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Install Drywall [Elec + Battery Rooms] Start Date: 11-Feb-25 End Date: 21-Feb-25
Note on KI929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Install Drywall [Elec + Battery Rooms] Start Date: 11-Feb-25 End Date: 21-Feb-25
Note on KJ929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Install Drywall [Elec + Battery Rooms] Start Date: 11-Feb-25 End Date: 21-Feb-25
Note on KK929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Install Drywall [Elec + Battery Rooms] Start Date: 11-Feb-25 End Date: 21-Feb-25
Note on KL929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Install Drywall [Elec + Battery Rooms] Start Date: 11-Feb-25 End Date: 21-Feb-25
Note on KM929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Install Drywall [Elec + Battery Rooms] Start Date: 11-Feb-25 End Date: 21-Feb-25
Note on KN929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 22-Feb-25 End Date: 04-Mar-25
Note on KO929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 22-Feb-25 End Date: 04-Mar-25
Note on KP929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 22-Feb-25 End Date: 04-Mar-25
Note on KQ929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 22-Feb-25 End Date: 04-Mar-25
Note on KR929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 22-Feb-25 End Date: 04-Mar-25
Note on KS929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 22-Feb-25 End Date: 04-Mar-25
Note on KT929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 22-Feb-25 End Date: 04-Mar-25
Note on KU929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 22-Feb-25 End Date: 04-Mar-25
Note on KV929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 22-Feb-25 End Date: 04-Mar-25
Note on KW929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 22-Feb-25 End Date: 04-Mar-25
Note on KX929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 22-Feb-25 End Date: 04-Mar-25
Note on KY929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 05-Mar-25 End Date: 06-Mar-25
Note on KZ929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 05-Mar-25 End Date: 06-Mar-25
Note on LA929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Cx Activity Name: General Cleaning Start Date: 07-Mar-25 End Date: 07-Mar-25
Note on LD929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 10-Mar-25 End Date: 15-Mar-25
Note on LE929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 10-Mar-25 End Date: 15-Mar-25
Note on LF929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 10-Mar-25 End Date: 15-Mar-25
Note on LG929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 10-Mar-25 End Date: 15-Mar-25
Note on LH929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 10-Mar-25 End Date: 15-Mar-25
Note on LI929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 10-Mar-25 End Date: 15-Mar-25
Note on LK929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LL929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LM929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LN929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LO929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LP929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LQ929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LR929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LS929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LT929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LU929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LV929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LW929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 17-Mar-25 End Date: 29-Mar-25
Note on LY929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on LZ929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on MA929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on MB929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 31-Mar-25 End Date: 03-Apr-25
Note on MC929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 31-Mar-25 End Date: 11-Apr-25
Note on MD929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 31-Mar-25 End Date: 11-Apr-25
Note on ME929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 31-Mar-25 End Date: 11-Apr-25
Note on MF929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 31-Mar-25 End Date: 11-Apr-25
Note on MG929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 31-Mar-25 End Date: 11-Apr-25
Note on MH929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 31-Mar-25 End Date: 11-Apr-25
Note on MI929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 31-Mar-25 End Date: 11-Apr-25
Note on MJ929: Phase: Fitout Location: COLO 3 - CELL 1 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 31-Mar-25 End Date: 11-Apr-25
Note on KE944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KF944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KG944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KH944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KI944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KJ944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 15-Feb-25 End Date: 18-Feb-25
Note on KK944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 19-Feb-25 End Date: 25-Feb-25
Note on KL944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 19-Feb-25 End Date: 25-Feb-25
Note on KM944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 19-Feb-25 End Date: 25-Feb-25
Note on KN944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 19-Feb-25 End Date: 25-Feb-25
Note on KO944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 19-Feb-25 End Date: 25-Feb-25
Note on KP944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 19-Feb-25 End Date: 25-Feb-25
Note on KQ944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 19-Feb-25 End Date: 25-Feb-25
Note on KR944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 26-Feb-25 End Date: 05-Mar-25
Note on KS944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 26-Feb-25 End Date: 05-Mar-25
Note on KT944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 26-Feb-25 End Date: 05-Mar-25
Note on KU944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 26-Feb-25 End Date: 05-Mar-25
Note on KV944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 26-Feb-25 End Date: 05-Mar-25
Note on KW944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 26-Feb-25 End Date: 05-Mar-25
Note on KX944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 26-Feb-25 End Date: 05-Mar-25
Note on KY944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 26-Feb-25 End Date: 05-Mar-25
Note on KZ944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on LA944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 07-Mar-25 End Date: 11-Mar-25
Note on LB944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LC944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LD944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LE944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 07-Mar-25 End Date: 11-Mar-25
Note on LF944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 12-Mar-25 End Date: 13-Mar-25
Note on LG944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 12-Mar-25 End Date: 13-Mar-25
Note on LH944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LI944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LJ944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LK944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LL944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LM944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on LN944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on LO944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on LP944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on LQ944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on LR944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on LS944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on LT944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on LU944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on LV944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on LW944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on LX944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on LY944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on LZ944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on MA944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 19-Mar-25 End Date: 02-Apr-25
Note on MB944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 03-Apr-25 End Date: 07-Apr-25
Note on MC944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 03-Apr-25 End Date: 07-Apr-25
Note on MD944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 03-Apr-25 End Date: 07-Apr-25
Note on ME944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 03-Apr-25 End Date: 07-Apr-25
Note on MF944: Phase: Fitout Location: COLO 3 - CELL 1 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 03-Apr-25 End Date: 07-Apr-25
Note on JP961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Layout Framing Start Date: 29-Jan-25 End Date: 29-Jan-25
Note on JQ961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 30-Jan-25 End Date: 01-Feb-25
Note on JR961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 30-Jan-25 End Date: 01-Feb-25
Note on JS961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 30-Jan-25 End Date: 01-Feb-25
Note on JU961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 03-Feb-25 End Date: 05-Feb-25
Note on JV961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 03-Feb-25 End Date: 05-Feb-25
Note on JW961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 03-Feb-25 End Date: 05-Feb-25
Note on JX961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 06-Feb-25 End Date: 10-Feb-25
Note on JY961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 06-Feb-25 End Date: 10-Feb-25
Note on JZ961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 06-Feb-25 End Date: 10-Feb-25
Note on KA961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 06-Feb-25 End Date: 10-Feb-25
Note on KB961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 06-Feb-25 End Date: 10-Feb-25
Note on KC961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 11-Feb-25 End Date: 13-Feb-25
Note on KD961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 11-Feb-25 End Date: 13-Feb-25
Note on KE961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KF961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 14-Feb-25 End Date: 17-Feb-25
Note on KG961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 14-Feb-25 End Date: 17-Feb-25
Note on KH961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 14-Feb-25 End Date: 17-Feb-25
Note on KI961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 14-Feb-25 End Date: 17-Feb-25
Note on KJ961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 18-Feb-25 End Date: 20-Feb-25
Note on KK961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 18-Feb-25 End Date: 20-Feb-25
Note on KL961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 18-Feb-25 End Date: 20-Feb-25
Note on KM961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 21-Feb-25 End Date: 22-Feb-25
Note on KN961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 21-Feb-25 End Date: 22-Feb-25
Note on KP961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 24-Feb-25 End Date: 25-Feb-25
Note on KQ961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 24-Feb-25 End Date: 25-Feb-25
Note on KR961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KS961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KT961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KU961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KV961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KW961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KX961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 04-Mar-25 End Date: 07-Mar-25
Note on KY961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 04-Mar-25 End Date: 07-Mar-25
Note on KZ961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 04-Mar-25 End Date: 07-Mar-25
Note on LA961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 04-Mar-25 End Date: 07-Mar-25
Note on LB961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 08-Mar-25 End Date: 12-Mar-25
Note on LC961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 08-Mar-25 End Date: 12-Mar-25
Note on LD961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 08-Mar-25 End Date: 12-Mar-25
Note on LE961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 08-Mar-25 End Date: 12-Mar-25
Note on LF961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 08-Mar-25 End Date: 12-Mar-25
Note on LG961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Start Date: 08-Mar-25 End Date: 13-Mar-25
Note on LH961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LI961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LJ961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LK961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LL961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 14-Mar-25 End Date: 18-Mar-25
Note on LM961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 19-Mar-25 End Date: 24-Mar-25
Note on LN961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 19-Mar-25 End Date: 24-Mar-25
Note on LO961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 19-Mar-25 End Date: 24-Mar-25
Note on LP961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 19-Mar-25 End Date: 24-Mar-25
Note on LQ961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 19-Mar-25 End Date: 24-Mar-25
Note on LR961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 24-Mar-25 End Date: 26-Mar-25
Note on LS961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 24-Mar-25 End Date: 26-Mar-25
Note on LT961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 24-Mar-25 End Date: 26-Mar-25
Note on LU961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-Mar-25 End Date: 01-Apr-25
Note on LV961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-Mar-25 End Date: 01-Apr-25
Note on LW961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-Mar-25 End Date: 01-Apr-25
Note on LX961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-Mar-25 End Date: 01-Apr-25
Note on LY961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-Mar-25 End Date: 01-Apr-25
Note on LZ961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 27-Mar-25 End Date: 01-Apr-25
Note on NL961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 09-May-25 End Date: 12-May-25
Note on NM961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 09-May-25 End Date: 12-May-25
Note on NN961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 09-May-25 End Date: 12-May-25
Note on NO961: Phase: Fitout Location: COLO 3 - CELL 2 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 09-May-25 End Date: 12-May-25
Note on JU989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 03-Feb-25 End Date: 04-Feb-25
Note on JV989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Framing Activity Name: Install Framing Start Date: 03-Feb-25 End Date: 04-Feb-25
Note on JW989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 05-Feb-25 End Date: 06-Feb-25
Note on JX989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: In-Wall R/I Start Date: 05-Feb-25 End Date: 06-Feb-25
Note on JY989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on JZ989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on KA989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on KB989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on KC989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on KD989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on KE989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 11-Feb-25 End Date: 13-Feb-25
Note on KF989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 14-Feb-25 End Date: 15-Feb-25
Note on KG989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KH989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KI989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KJ989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Cx Activity Name: General Cleaning Start Date: 18-Feb-25 End Date: 18-Feb-25
Note on LK989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 17-Mar-25 End Date: 20-Mar-25
Note on LL989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 17-Mar-25 End Date: 20-Mar-25
Note on LM989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 17-Mar-25 End Date: 20-Mar-25
Note on LN989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Set Electrical Equipments Start Date: 17-Mar-25 End Date: 20-Mar-25
Note on MM989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 14-Apr-25 End Date: 25-Apr-25
Note on MN989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 14-Apr-25 End Date: 25-Apr-25
Note on MO989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 14-Apr-25 End Date: 25-Apr-25
Note on MP989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 14-Apr-25 End Date: 25-Apr-25
Note on MQ989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 14-Apr-25 End Date: 25-Apr-25
Note on MR989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 14-Apr-25 End Date: 25-Apr-25
Note on MS989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 14-Apr-25 End Date: 25-Apr-25
Note on MT989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 14-Apr-25 End Date: 25-Apr-25
Note on MU989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 14-Apr-25 End Date: 25-Apr-25
Note on MV989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 14-Apr-25 End Date: 25-Apr-25
Note on MW989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 14-Apr-25 End Date: 25-Apr-25
Note on MX989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Cable between Elec Equipments [Inside Electrical Room] Pull Crew 1 Start Date: 14-Apr-25 End Date: 25-Apr-25
Note on MY989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on MZ989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on NA989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on NB989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on NC989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Terminate Electrical Equipments [Inside Electrical Room] Start Date: 26-Apr-25 End Date: 30-Apr-25
Note on ND989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 26-Apr-25 End Date: 08-May-25
Note on NE989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 26-Apr-25 End Date: 08-May-25
Note on NF989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 26-Apr-25 End Date: 08-May-25
Note on NG989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 26-Apr-25 End Date: 08-May-25
Note on NH989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 26-Apr-25 End Date: 08-May-25
Note on NI989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 26-Apr-25 End Date: 08-May-25
Note on NJ989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 26-Apr-25 End Date: 08-May-25
Note on NK989: Phase: Fitout Location: COLO 3 - CELL 2 Electrical Room Trade: Electrical Activity Name: Pull Feeders from Electrical Room to PDUs Pull Crew 1 Start Date: 26-Apr-25 End Date: 08-May-25
Note on KC1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on KD1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on KE1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KF1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KG1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Overhead R/I - Electrical Start Date: 13-Feb-25 End Date: 15-Feb-25
Note on KI1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 17-Feb-25 End Date: 22-Feb-25
Note on KJ1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 17-Feb-25 End Date: 22-Feb-25
Note on KK1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 17-Feb-25 End Date: 22-Feb-25
Note on KL1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 17-Feb-25 End Date: 22-Feb-25
Note on KM1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 17-Feb-25 End Date: 22-Feb-25
Note on KN1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 17-Feb-25 End Date: 22-Feb-25
Note on KP1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 24-Feb-25 End Date: 03-Mar-25
Note on KQ1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 24-Feb-25 End Date: 03-Mar-25
Note on KR1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 24-Feb-25 End Date: 03-Mar-25
Note on KS1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 24-Feb-25 End Date: 03-Mar-25
Note on KT1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 24-Feb-25 End Date: 03-Mar-25
Note on KU1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 24-Feb-25 End Date: 03-Mar-25
Note on KV1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 24-Feb-25 End Date: 03-Mar-25
Note on KW1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Plumbing Activity Name: Overhead R/I - Plumbing Start Date: 24-Feb-25 End Date: 03-Mar-25
Note on KX1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Activity Name: Finish Dry-Wall Start Date: 04-Mar-25 End Date: 05-Mar-25
Note on KY1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 05-Mar-25 End Date: 08-Mar-25
Note on KZ1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on LA1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 06-Mar-25 End Date: 07-Mar-25
Note on LB1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Framing Activity Name: Install Ceiling Grid + Device Tiles Start Date: 05-Mar-25 End Date: 08-Mar-25
Note on LC1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Cx Activity Name: General Cleaning Start Date: 08-Mar-25 End Date: 11-Mar-25
Note on LD1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 10-Mar-25 End Date: 11-Mar-25
Note on LE1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Install Cable Trays / Pathways Start Date: 10-Mar-25 End Date: 11-Mar-25
Note on LF1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-Mar-25 End Date: 15-Mar-25
Note on LG1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-Mar-25 End Date: 15-Mar-25
Note on LH1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-Mar-25 End Date: 15-Mar-25
Note on LI1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Set Mechanical Equipments Start Date: 12-Mar-25 End Date: 15-Mar-25
Note on LJ1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: BAS Activity Name: Install BAS Equipments Start Date: 10-Mar-25 End Date: 20-Mar-25
Note on LK1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LL1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LM1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LN1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LO1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LP1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LQ1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LR1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LS1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LT1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LU1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LV1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LW1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LX1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LY1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Pull Cable to Mechanical Equipments [From Electrical Room] Start Date: 17-Mar-25 End Date: 31-Mar-25
Note on LZ1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 01-Apr-25 End Date: 04-Apr-25
Note on MA1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 01-Apr-25 End Date: 04-Apr-25
Note on MB1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 01-Apr-25 End Date: 04-Apr-25
Note on MC1004: Phase: Fitout Location: COLO 3 - CELL 2 Mechanical Gallery Trade: Electrical Activity Name: Terminate Mechanical Equipments Start Date: 01-Apr-25 End Date: 04-Apr-25
Note on NP1021: Phase: Fitout Location: COLO 3 - CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 13-May-25 End Date: 23-May-25
Note on NQ1021: Phase: Fitout Location: COLO 3 - CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 13-May-25 End Date: 23-May-25
Note on NR1021: Phase: Fitout Location: COLO 3 - CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 13-May-25 End Date: 23-May-25
Note on NS1021: Phase: Fitout Location: COLO 3 - CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 13-May-25 End Date: 23-May-25
Note on NT1021: Phase: Fitout Location: COLO 3 - CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 13-May-25 End Date: 23-May-25
Note on NU1021: Phase: Fitout Location: COLO 3 - CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 13-May-25 End Date: 23-May-25
Note on NV1021: Phase: Fitout Location: COLO 3 - CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 13-May-25 End Date: 23-May-25
Note on NW1021: Phase: Fitout Location: COLO 3 - CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 13-May-25 End Date: 23-May-25
Note on NX1021: Phase: Fitout Location: COLO 3 - CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 13-May-25 End Date: 23-May-25
Note on NY1021: Phase: Fitout Location: COLO 3 - CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 13-May-25 End Date: 23-May-25
Note on NZ1021: Phase: Fitout Location: COLO 3 - CELL 2 Punchlist Trade: Punchlist Activity Name: Punchlist Start Date: 13-May-25 End Date: 23-May-25
Note on KM1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Layout Framing Start Date: 21-Feb-25 End Date: 21-Feb-25
Note on KN1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 22-Feb-25 End Date: 25-Feb-25
Note on KO1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 22-Feb-25 End Date: 25-Feb-25
Note on KP1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 22-Feb-25 End Date: 25-Feb-25
Note on KQ1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Framing Start Date: 22-Feb-25 End Date: 25-Feb-25
Note on KR1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 26-Feb-25 End Date: 28-Feb-25
Note on KS1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 26-Feb-25 End Date: 28-Feb-25
Note on KT1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: In-Wall R/I Start Date: 26-Feb-25 End Date: 28-Feb-25
Note on KW1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 03-Mar-25 End Date: 05-Mar-25
Note on KX1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 03-Mar-25 End Date: 05-Mar-25
Note on KY1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Protection Start Date: 03-Mar-25 End Date: 05-Mar-25
Note on KZ1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 06-Mar-25 End Date: 08-Mar-25
Note on LA1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Fire Protection Activity Name: Overhead R/I - Fire Alarm Start Date: 06-Mar-25 End Date: 08-Mar-25
Note on LB1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LC1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Overhead R/I - Mechanical Start Date: 08-Mar-25 End Date: 10-Mar-25
Note on LD1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 10-Mar-25 End Date: 12-Mar-25
Note on LE1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 10-Mar-25 End Date: 12-Mar-25
Note on LF1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Paiting Activity Name: Paint Dry-Wall Start Date: 10-Mar-25 End Date: 12-Mar-25
Note on LG1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 13-Mar-25 End Date: 15-Mar-25
Note on LH1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 13-Mar-25 End Date: 15-Mar-25
Note on LI1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Screen Mesh + Caulking Start Date: 13-Mar-25 End Date: 15-Mar-25
Note on LK1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 17-Mar-25 End Date: 18-Mar-25
Note on LL1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Secondary Steel Start Date: 17-Mar-25 End Date: 18-Mar-25
Note on LM1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on LN1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Paiting Activity Name: Paint Secondary Steel Start Date: 19-Mar-25 End Date: 20-Mar-25
Note on LO1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 21-Mar-25 End Date: 26-Mar-25
Note on LP1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 21-Mar-25 End Date: 26-Mar-25
Note on LQ1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 21-Mar-25 End Date: 26-Mar-25
Note on LR1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 21-Mar-25 End Date: 26-Mar-25
Note on LS1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 21-Mar-25 End Date: 26-Mar-25
Note on LT1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Ceiling Grid Start Date: 21-Mar-25 End Date: 26-Mar-25
Note on LU1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 27-Mar-25 End Date: 31-Mar-25
Note on LV1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 27-Mar-25 End Date: 31-Mar-25
Note on LW1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 27-Mar-25 End Date: 31-Mar-25
Note on LX1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 27-Mar-25 End Date: 31-Mar-25
Note on LY1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Perimeter Cable Trays Start Date: 27-Mar-25 End Date: 31-Mar-25
Note on LZ1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 01-Apr-25 End Date: 04-Apr-25
Note on MA1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 01-Apr-25 End Date: 04-Apr-25
Note on MB1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 01-Apr-25 End Date: 04-Apr-25
Note on MC1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: Set PDUs Start Date: 01-Apr-25 End Date: 04-Apr-25
Note on MD1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Fiber Runner [ Cable Trays on HAC Arms] Start Date: 01-Apr-25 End Date: 05-Apr-25
Note on MF1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on MG1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on MH1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on MI1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: HAC's Activity Name: Raise HACs Start Date: 07-Apr-25 End Date: 10-Apr-25
Note on MJ1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MK1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on ML1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MM1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MN1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: HAC's Activity Name: Detail HACs Start Date: 11-Apr-25 End Date: 16-Apr-25
Note on MO1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 16-Apr-25 End Date: 18-Apr-25
Note on MP1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 16-Apr-25 End Date: 18-Apr-25
Note on MQ1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Framing Activity Name: Install Conduits PDU to Cable Trays Start Date: 16-Apr-25 End Date: 18-Apr-25
Note on MR1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 19-Apr-25 End Date: 24-Apr-25
Note on MS1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 19-Apr-25 End Date: 24-Apr-25
Note on MT1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 19-Apr-25 End Date: 24-Apr-25
Note on MU1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 19-Apr-25 End Date: 24-Apr-25
Note on MV1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 19-Apr-25 End Date: 24-Apr-25
Note on MW1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: Pull Feeders from PDUs to Busways Start Date: 19-Apr-25 End Date: 24-Apr-25
Note on OM1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 05-Jun-25 End Date: 07-Jun-25
Note on ON1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 05-Jun-25 End Date: 07-Jun-25
Note on OO1022: Phase: Fitout Location: COLO 3 - CELL 3 Data Hall Trade: Electrical Activity Name: Terminate PDUs Start Date: 05-Jun-25 End Date: 07-Jun-25
Note on JG1050: Phase: Fitout Location: Electrical Room Trade: Framing Activity Name: Fire Protection OH R/I Start Date: 20-Jan-25 End Date: 20-Jan-25
Note on JH1050: Phase: Fitout Location: Electrical Room Trade: Framing Activity Name: Framing Start Date: 21-Jan-25 End Date: 21-Jan-25
Note on JI1050: Phase: Fitout Location: Electrical Room Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 22-Jan-25 End Date: 23-Jan-25
Note on JJ1050: Phase: Fitout Location: Electrical Room Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 22-Jan-25 End Date: 23-Jan-25
Note on JK1050: Phase: Fitout Location: Electrical Room Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 24-Jan-25 End Date: 25-Jan-25
Note on JL1050: Phase: Fitout Location: Electrical Room Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 24-Jan-25 End Date: 25-Jan-25
Note on JN1050: Phase: Fitout Location: Electrical Room Trade: Framing Activity Name: Secondary / Ceiling Steel Start Date: 27-Jan-25 End Date: 27-Jan-25
Note on JO1050: Phase: Fitout Location: Electrical Room Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 28-Jan-25 End Date: 31-Jan-25
Note on JP1050: Phase: Fitout Location: Electrical Room Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 28-Jan-25 End Date: 31-Jan-25
Note on JQ1050: Phase: Fitout Location: Electrical Room Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 28-Jan-25 End Date: 31-Jan-25
Note on JR1050: Phase: Fitout Location: Electrical Room Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 28-Jan-25 End Date: 31-Jan-25
Note on JS1050: Phase: Fitout Location: Electrical Room Trade: Paiting Activity Name: Paint Start Date: 01-Feb-25 End Date: 03-Feb-25
Note on JT1050: Phase: Fitout Location: Electrical Room Trade: Paiting Activity Name: Paint Start Date: 01-Feb-25 End Date: 03-Feb-25
Note on JU1050: Phase: Fitout Location: Electrical Room Trade: Paiting Activity Name: Paint Start Date: 01-Feb-25 End Date: 03-Feb-25
Note on JV1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Cable Tray / Ceiling Steel Height Start Date: 04-Feb-25 End Date: 04-Feb-25
Note on KW1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Set Electrical Equipment in Admin Start Date: 03-Mar-25 End Date: 11-Mar-25
Note on KX1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Set Electrical Equipment in Admin Start Date: 03-Mar-25 End Date: 11-Mar-25
Note on KY1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Set Electrical Equipment in Admin Start Date: 03-Mar-25 End Date: 11-Mar-25
Note on KZ1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Set Electrical Equipment in Admin Start Date: 03-Mar-25 End Date: 11-Mar-25
Note on LA1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Set Electrical Equipment in Admin Start Date: 03-Mar-25 End Date: 11-Mar-25
Note on LB1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Set Electrical Equipment in Admin Start Date: 03-Mar-25 End Date: 11-Mar-25
Note on LC1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Set Electrical Equipment in Admin Start Date: 03-Mar-25 End Date: 11-Mar-25
Note on LD1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Set Electrical Equipment in Admin Start Date: 03-Mar-25 End Date: 11-Mar-25
Note on LE1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Set Electrical Equipment in Admin Start Date: 03-Mar-25 End Date: 11-Mar-25
Note on LF1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LG1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LH1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LI1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LJ1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LK1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LL1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LM1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LN1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LO1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LP1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LQ1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LR1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LS1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LT1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LU1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LV1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Feeders to Admin Start Date: 12-Mar-25 End Date: 28-Mar-25
Note on LW1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on LX1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on LY1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on LZ1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on MA1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on MB1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on MC1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on MD1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on ME1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on MF1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on MG1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on MH1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on MI1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on MJ1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Pull Branches From Admin Start Date: 29-Mar-25 End Date: 11-Apr-25
Note on MM1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Terminate Electrical / Mechanical Equipment Start Date: 14-Apr-25 End Date: 17-Apr-25
Note on MN1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Terminate Electrical / Mechanical Equipment Start Date: 14-Apr-25 End Date: 17-Apr-25
Note on MO1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Terminate Electrical / Mechanical Equipment Start Date: 14-Apr-25 End Date: 17-Apr-25
Note on MP1050: Phase: Fitout Location: Electrical Room Trade: Electrical Activity Name: Terminate Electrical / Mechanical Equipment Start Date: 14-Apr-25 End Date: 17-Apr-25
Note on JH1062: Phase: Fitout Location: Entry Room 1 Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 21-Jan-25 End Date: 21-Jan-25
Note on JI1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Framing Start Date: 22-Jan-25 End Date: 22-Jan-25
Note on JK1062: Phase: Fitout Location: Entry Room 1 Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 24-Jan-25 End Date: 25-Jan-25
Note on JL1062: Phase: Fitout Location: Entry Room 1 Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 24-Jan-25 End Date: 25-Jan-25
Note on JN1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 27-Jan-25 End Date: 28-Jan-25
Note on JO1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 27-Jan-25 End Date: 28-Jan-25
Note on JP1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Secondary / Ceiling Steel Start Date: 29-Jan-25 End Date: 29-Jan-25
Note on JQ1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 30-Jan-25 End Date: 03-Feb-25
Note on JR1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 30-Jan-25 End Date: 03-Feb-25
Note on JS1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 30-Jan-25 End Date: 03-Feb-25
Note on JT1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 30-Jan-25 End Date: 03-Feb-25
Note on JU1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 30-Jan-25 End Date: 03-Feb-25
Note on JV1062: Phase: Fitout Location: Entry Room 1 Trade: Paiting Activity Name: Paint Start Date: 04-Feb-25 End Date: 05-Feb-25
Note on JW1062: Phase: Fitout Location: Entry Room 1 Trade: Paiting Activity Name: Paint Start Date: 04-Feb-25 End Date: 05-Feb-25
Note on JX1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Install Raceway Start Date: 06-Feb-25 End Date: 10-Feb-25
Note on JY1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Install Raceway Start Date: 06-Feb-25 End Date: 10-Feb-25
Note on JZ1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Install Raceway Start Date: 06-Feb-25 End Date: 10-Feb-25
Note on KA1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Install Raceway Start Date: 06-Feb-25 End Date: 10-Feb-25
Note on KB1062: Phase: Fitout Location: Entry Room 1 Trade: Framing Activity Name: Install Raceway Start Date: 06-Feb-25 End Date: 10-Feb-25
Note on KC1062: Phase: Fitout Location: Entry Room 1 Trade: Electrical Activity Name: Set ER-1 Equipment Start Date: 11-Feb-25 End Date: 14-Feb-25
Note on KD1062: Phase: Fitout Location: Entry Room 1 Trade: Electrical Activity Name: Set ER-1 Equipment Start Date: 11-Feb-25 End Date: 14-Feb-25
Note on KE1062: Phase: Fitout Location: Entry Room 1 Trade: Electrical Activity Name: Set ER-1 Equipment Start Date: 11-Feb-25 End Date: 14-Feb-25
Note on KF1062: Phase: Fitout Location: Entry Room 1 Trade: Electrical Activity Name: Set ER-1 Equipment Start Date: 11-Feb-25 End Date: 14-Feb-25
Note on JI1071: Phase: Fitout Location: Entry Room 2 Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 22-Jan-25 End Date: 22-Jan-25
Note on JJ1071: Phase: Fitout Location: Entry Room 2 Trade: Framing Activity Name: Framing Start Date: 23-Jan-25 End Date: 23-Jan-25
Note on JN1071: Phase: Fitout Location: Entry Room 2 Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 27-Jan-25 End Date: 28-Jan-25
Note on JO1071: Phase: Fitout Location: Entry Room 2 Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 27-Jan-25 End Date: 28-Jan-25
Note on JP1071: Phase: Fitout Location: Entry Room 2 Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 29-Jan-25 End Date: 30-Jan-25
Note on JQ1071: Phase: Fitout Location: Entry Room 2 Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 29-Jan-25 End Date: 30-Jan-25
Note on JR1071: Phase: Fitout Location: Entry Room 2 Trade: Framing Activity Name: Secondary / Ceiling Steel Start Date: 31-Jan-25 End Date: 31-Jan-25
Note on JS1071: Phase: Fitout Location: Entry Room 2 Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 01-Feb-25 End Date: 05-Feb-25
Note on JT1071: Phase: Fitout Location: Entry Room 2 Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 01-Feb-25 End Date: 05-Feb-25
Note on JU1071: Phase: Fitout Location: Entry Room 2 Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 01-Feb-25 End Date: 05-Feb-25
Note on JV1071: Phase: Fitout Location: Entry Room 2 Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 01-Feb-25 End Date: 05-Feb-25
Note on JW1071: Phase: Fitout Location: Entry Room 2 Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 01-Feb-25 End Date: 05-Feb-25
Note on JX1071: Phase: Fitout Location: Entry Room 2 Trade: Paiting Activity Name: Paint Start Date: 06-Feb-25 End Date: 07-Feb-25
Note on JY1071: Phase: Fitout Location: Entry Room 2 Trade: Paiting Activity Name: Paint Start Date: 06-Feb-25 End Date: 07-Feb-25
Note on KB1071: Phase: Fitout Location: Entry Room 2 Trade: Framing Activity Name: Install Raceway Start Date: 10-Feb-25 End Date: 12-Feb-25
Note on KC1071: Phase: Fitout Location: Entry Room 2 Trade: Framing Activity Name: Install Raceway Start Date: 10-Feb-25 End Date: 12-Feb-25
Note on KD1071: Phase: Fitout Location: Entry Room 2 Trade: Framing Activity Name: Install Raceway Start Date: 10-Feb-25 End Date: 12-Feb-25
Note on KE1071: Phase: Fitout Location: Entry Room 2 Trade: Electrical Activity Name: Set ER-2 Equipment Start Date: 13-Feb-25 End Date: 17-Feb-25
Note on KF1071: Phase: Fitout Location: Entry Room 2 Trade: Electrical Activity Name: Set ER-2 Equipment Start Date: 13-Feb-25 End Date: 17-Feb-25
Note on KG1071: Phase: Fitout Location: Entry Room 2 Trade: Electrical Activity Name: Set ER-2 Equipment Start Date: 13-Feb-25 End Date: 17-Feb-25
Note on KH1071: Phase: Fitout Location: Entry Room 2 Trade: Electrical Activity Name: Set ER-2 Equipment Start Date: 13-Feb-25 End Date: 17-Feb-25
Note on KI1071: Phase: Fitout Location: Entry Room 2 Trade: Electrical Activity Name: Set ER-2 Equipment Start Date: 13-Feb-25 End Date: 17-Feb-25
Note on JJ1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 23-Jan-25 End Date: 23-Jan-25
Note on JK1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Activity Name: Framing Start Date: 24-Jan-25 End Date: 24-Jan-25
Note on JP1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 29-Jan-25 End Date: 30-Jan-25
Note on JQ1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 29-Jan-25 End Date: 30-Jan-25
Note on JR1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 31-Jan-25 End Date: 01-Feb-25
Note on JS1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 31-Jan-25 End Date: 01-Feb-25
Note on JU1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Activity Name: Secondary / Ceiling Steel Start Date: 03-Feb-25 End Date: 03-Feb-25
Note on JV1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 04-Feb-25 End Date: 07-Feb-25
Note on JW1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 04-Feb-25 End Date: 07-Feb-25
Note on JX1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 04-Feb-25 End Date: 07-Feb-25
Note on JY1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Activity Name: Finsh Drywall and Wall Protection Start Date: 04-Feb-25 End Date: 07-Feb-25
Note on KB1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Paiting Activity Name: Paint Start Date: 10-Feb-25 End Date: 11-Feb-25
Note on KC1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Paiting Activity Name: Paint Start Date: 10-Feb-25 End Date: 11-Feb-25
Note on KD1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Activity Name: Install Raceway Start Date: 12-Feb-25 End Date: 14-Feb-25
Note on KE1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Activity Name: Install Raceway Start Date: 12-Feb-25 End Date: 14-Feb-25
Note on KF1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Framing Activity Name: Install Raceway Start Date: 12-Feb-25 End Date: 14-Feb-25
Note on KG1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Set FCR Equipment Start Date: 15-Feb-25 End Date: 19-Feb-25
Note on KH1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Set FCR Equipment Start Date: 15-Feb-25 End Date: 19-Feb-25
Note on KI1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Set FCR Equipment Start Date: 15-Feb-25 End Date: 19-Feb-25
Note on KJ1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Set FCR Equipment Start Date: 15-Feb-25 End Date: 19-Feb-25
Note on KK1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Set FCR Equipment Start Date: 15-Feb-25 End Date: 19-Feb-25
Note on KL1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KM1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KN1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KO1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KP1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KQ1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KR1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KS1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KT1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KU1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KV1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KW1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KX1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KY1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on KZ1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For EPMS VLAN Start Date: 20-Feb-25 End Date: 06-Mar-25
Note on LA1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LB1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LC1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LD1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LE1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LF1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LG1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LH1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LI1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LJ1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LK1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LL1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LM1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LN1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For Tahuya VLAN Start Date: 07-Mar-25 End Date: 20-Mar-25
Note on LO1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on LP1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on LQ1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on LR1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on LS1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on LT1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on LU1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on LV1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on LW1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on LX1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on LY1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on LZ1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on MA1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on MB1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on MC1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For BAS VLAN Start Date: 21-Mar-25 End Date: 04-Apr-25
Note on MD1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on ME1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MF1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MG1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MH1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MI1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MJ1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MK1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on ML1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MM1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MN1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MO1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MP1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MQ1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MR1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber/Copper For CORPNET Network Start Date: 05-Apr-25 End Date: 19-Apr-25
Note on MT1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on MU1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on MV1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on MW1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on MX1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on MY1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on MZ1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on NA1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on NB1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on NC1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on ND1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on NE1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on NF1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on NG1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on NH1080: Phase: Fitout Location: FCR (Facilities Control Room) Trade: Electrical Activity Name: Pull Fiber For CEI Network Start Date: 21-Apr-25 End Date: 05-May-25
Note on JN1097: Phase: Fitout Location: Fire Riser Room Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 27-Jan-25 End Date: 27-Jan-25
Note on JO1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Framing Start Date: 28-Jan-25 End Date: 28-Jan-25
Note on JP1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Install Duct Work Start Date: 29-Jan-25 End Date: 30-Jan-25
Note on JQ1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Install Duct Work Start Date: 29-Jan-25 End Date: 30-Jan-25
Note on JR1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Install downcomers Start Date: 31-Jan-25 End Date: 31-Jan-25
Note on JW1097: Phase: Fitout Location: Fire Riser Room Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 05-Feb-25 End Date: 06-Feb-25
Note on JX1097: Phase: Fitout Location: Fire Riser Room Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 05-Feb-25 End Date: 06-Feb-25
Note on JY1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on JZ1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on KA1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on KB1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on KC1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Secondary / Ceiling Steel Start Date: 11-Feb-25 End Date: 11-Feb-25
Note on KD1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 12-Feb-25 End Date: 13-Feb-25
Note on KE1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 12-Feb-25 End Date: 13-Feb-25
Note on KF1097: Phase: Fitout Location: Fire Riser Room Trade: Paiting Activity Name: Paint Start Date: 14-Feb-25 End Date: 15-Feb-25
Note on KG1097: Phase: Fitout Location: Fire Riser Room Trade: Paiting Activity Name: Paint Start Date: 14-Feb-25 End Date: 15-Feb-25
Note on KJ1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Ceiling Grid & Tile Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on KK1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Ceiling Grid & Tile Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on KL1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Ceiling Grid & Tile Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on KM1097: Phase: Fitout Location: Fire Riser Room Trade: Framing Activity Name: Ceiling Grid & Tile Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on KN1097: Phase: Fitout Location: Fire Riser Room Trade: Fire Protection Activity Name: Complete Pipe/ Valves Start Date: 22-Feb-25 End Date: 24-Feb-25
Note on KO1097: Phase: Fitout Location: Fire Riser Room Trade: Fire Protection Activity Name: Complete Pipe/ Valves Start Date: 22-Feb-25 End Date: 24-Feb-25
Note on KP1097: Phase: Fitout Location: Fire Riser Room Trade: Fire Protection Activity Name: Complete Pipe/ Valves Start Date: 22-Feb-25 End Date: 24-Feb-25
Note on JP1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork Start Date: 29-Jan-25 End Date: 15-Feb-25
Note on JQ1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on JR1108: Phase: Fitout Location: Loading Dock Trade: Milestone Activity Name: Rough-in Start Date: 31-Jan-25 End Date: 31-Jan-25
Note on JS1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on JT1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on JU1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on JV1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on JW1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on JX1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on JY1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on JZ1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on KA1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on KB1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on KC1108: Phase: Fitout Location: Loading Dock Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on KD1108: Phase: Fitout Location: Loading Dock Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on KE1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KF1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KG1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on KH1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on KI1108: Phase: Fitout Location: Loading Dock Trade: Framing Activity Name: Install Ductwork (Remaining Rooms, Corridor) Start Date: 30-Jan-25 End Date: 17-Feb-25
Note on KJ1108: Phase: Fitout Location: Loading Dock Trade: Paiting Activity Name: Paint Start Date: 18-Feb-25 End Date: 19-Feb-25
Note on KK1108: Phase: Fitout Location: Loading Dock Trade: Paiting Activity Name: Paint Start Date: 18-Feb-25 End Date: 19-Feb-25
Note on KL1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KM1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KN1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KO1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KP1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KQ1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KR1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KS1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KT1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KU1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KV1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KW1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KX1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KY1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on KZ1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on LA1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on LB1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on LC1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on LD1108: Phase: Fitout Location: Loading Dock Trade: Plumbing Activity Name: Plumbing Start Date: 20-Feb-25 End Date: 10-Mar-25
Note on LE1108: Phase: Fitout Location: Loading Dock Trade: Electrical Activity Name: Pull Cables Start Date: 11-Mar-25 End Date: 13-Mar-25
Note on LF1108: Phase: Fitout Location: Loading Dock Trade: Electrical Activity Name: Pull Cables Start Date: 11-Mar-25 End Date: 13-Mar-25
Note on LG1108: Phase: Fitout Location: Loading Dock Trade: Electrical Activity Name: Pull Cables Start Date: 11-Mar-25 End Date: 13-Mar-25
Note on JN1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on JO1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on JP1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on JQ1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on JR1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on JS1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on JT1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on JU1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on JV1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on JW1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on JX1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on JY1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on JZ1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KA1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KB1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KC1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KD1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KE1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KF1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KG1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KH1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KI1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KJ1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KK1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KL1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KM1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KN1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KO1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KP1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KQ1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KR1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KS1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KT1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KU1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KV1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KW1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KX1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KY1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on KZ1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on LA1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on LB1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on LC1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on LD1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on LE1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on LF1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on LG1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on LH1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on LI1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on LJ1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on LK1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Remaining Rooms Start Date: 27-Jan-25 End Date: 17-Mar-25
Note on NI1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Beneficial Rooms PunchList Start Date: 06-May-25 End Date: 09-May-25
Note on NJ1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Beneficial Rooms PunchList Start Date: 06-May-25 End Date: 09-May-25
Note on NK1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Beneficial Rooms PunchList Start Date: 06-May-25 End Date: 09-May-25
Note on NL1119: Phase: Fitout Location: Punchlist Trade: Punchlist Activity Name: Beneficial Rooms PunchList Start Date: 06-May-25 End Date: 09-May-25
Note on JO1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 28-Jan-25 End Date: 28-Jan-25
Note on JP1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: Framing Activity Name: Framing Start Date: 29-Jan-25 End Date: 29-Jan-25
Note on JY1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on JZ1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on KA1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on KB1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 07-Feb-25 End Date: 10-Feb-25
Note on KC1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on KD1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 11-Feb-25 End Date: 12-Feb-25
Note on KE1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KF1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: Framing Activity Name: Finish Dry-Wall Start Date: 13-Feb-25 End Date: 14-Feb-25
Note on KG1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: Paiting Activity Name: Paint Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KH1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: Paiting Activity Name: Paint Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KI1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: Paiting Activity Name: Paint Start Date: 15-Feb-25 End Date: 17-Feb-25
Note on KJ1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: Framing Activity Name: Ceiling Grid & Tile Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on KK1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: Framing Activity Name: Ceiling Grid & Tile Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on KL1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: Framing Activity Name: Ceiling Grid & Tile Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on KM1121: Phase: Fitout Location: Restrooms & Janitor Room Trade: Framing Activity Name: Ceiling Grid & Tile Start Date: 18-Feb-25 End Date: 21-Feb-25
Note on JK1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 24-Jan-25 End Date: 24-Jan-25
Note on JL1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Activity Name: Framing Start Date: 25-Jan-25 End Date: 25-Jan-25
Note on JR1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 31-Jan-25 End Date: 01-Feb-25
Note on JS1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 31-Jan-25 End Date: 01-Feb-25
Note on JU1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 03-Feb-25 End Date: 04-Feb-25
Note on JV1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 03-Feb-25 End Date: 04-Feb-25
Note on JW1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Activity Name: Secondary / Ceiling Steel Start Date: 05-Feb-25 End Date: 05-Feb-25
Note on JX1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Activity Name: Finish Dry-Wall Start Date: 06-Feb-25 End Date: 07-Feb-25
Note on JY1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Activity Name: Finish Dry-Wall Start Date: 06-Feb-25 End Date: 07-Feb-25
Note on KB1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: Paiting Activity Name: Paint Start Date: 10-Feb-25 End Date: 11-Feb-25
Note on KC1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: Paiting Activity Name: Paint Start Date: 10-Feb-25 End Date: 11-Feb-25
Note on KD1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Activity Name: Install Raceway Start Date: 12-Feb-25 End Date: 14-Feb-25
Note on KE1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Activity Name: Install Raceway Start Date: 12-Feb-25 End Date: 14-Feb-25
Note on KF1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: Framing Activity Name: Install Raceway Start Date: 12-Feb-25 End Date: 14-Feb-25
Note on KG1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: HAC's Activity Name: Set SER Room Equipment Start Date: 15-Feb-25 End Date: 19-Feb-25
Note on KH1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: HAC's Activity Name: Set SER Room Equipment Start Date: 15-Feb-25 End Date: 19-Feb-25
Note on KI1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: HAC's Activity Name: Set SER Room Equipment Start Date: 15-Feb-25 End Date: 19-Feb-25
Note on KJ1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: HAC's Activity Name: Set SER Room Equipment Start Date: 15-Feb-25 End Date: 19-Feb-25
Note on KK1128: Phase: Fitout Location: SER (Security Equipment Room) Trade: HAC's Activity Name: Set SER Room Equipment Start Date: 15-Feb-25 End Date: 19-Feb-25
Note on JL1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 25-Jan-25 End Date: 25-Jan-25
Note on JN1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Framing Start Date: 27-Jan-25 End Date: 27-Jan-25
Note on JU1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 03-Feb-25 End Date: 04-Feb-25
Note on JV1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: MEP Activity Name: MEP Rough-In & OH Start Date: 03-Feb-25 End Date: 04-Feb-25
Note on JW1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 05-Feb-25 End Date: 06-Feb-25
Note on JX1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Top Out Drywall - Ceiling Steel Height Start Date: 05-Feb-25 End Date: 06-Feb-25
Note on JY1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on JZ1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KA1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KB1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KC1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KD1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KE1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KF1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KG1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KH1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KI1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KJ1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KK1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KL1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KM1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KN1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KO1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KP1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KQ1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Install Ductwork and Cracs Start Date: 07-Feb-25 End Date: 25-Feb-25
Note on KR1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Finish Dry-Wall Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KS1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Finish Dry-Wall Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KT1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Finish Dry-Wall Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KU1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Finish Dry-Wall Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KV1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Finish Dry-Wall Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KW1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Framing Activity Name: Finish Dry-Wall Start Date: 26-Feb-25 End Date: 03-Mar-25
Note on KX1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Paiting Activity Name: Paint Start Date: 04-Mar-25 End Date: 05-Mar-25
Note on KY1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Paiting Activity Name: Paint Start Date: 04-Mar-25 End Date: 05-Mar-25
Note on KZ1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 06-Mar-25 End Date: 17-Mar-25
Note on LA1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 06-Mar-25 End Date: 17-Mar-25
Note on LB1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 06-Mar-25 End Date: 17-Mar-25
Note on LC1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 06-Mar-25 End Date: 17-Mar-25
Note on LD1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 06-Mar-25 End Date: 17-Mar-25
Note on LE1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 06-Mar-25 End Date: 17-Mar-25
Note on LF1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 06-Mar-25 End Date: 17-Mar-25
Note on LG1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 06-Mar-25 End Date: 17-Mar-25
Note on LH1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 06-Mar-25 End Date: 17-Mar-25
Note on LI1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 06-Mar-25 End Date: 17-Mar-25
Note on LJ1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 06-Mar-25 End Date: 17-Mar-25
Note on LK1137: Phase: Fitout Location: STORAGE (High Value & Secure) Rooms Trade: Fire Protection Activity Name: Fire Protection OH R/I Start Date: 06-Mar-25 End Date: 17-Mar-25
Note on DZ1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Received SUB Warehouse 9/28/2023 UPS System w/ Battery (UPS) (Eaton) (SOW Del Date- 8/13/23) Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on GD1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Receive Utility Pad Mount Switchgear (Del Date- 7/30/2024) Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on HH1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 11/28/24) Start Date: 30-Nov-24 End Date: 30-Nov-24
Note on KK1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ ROJ Start Date: 19-Feb-25 End Date: 23-Feb-25
Note on KL1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ ROJ Start Date: 19-Feb-25 End Date: 23-Feb-25
Note on KM1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ ROJ Start Date: 19-Feb-25 End Date: 23-Feb-25
Note on KN1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ ROJ Start Date: 19-Feb-25 End Date: 23-Feb-25
Note on KO1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ ROJ Start Date: 19-Feb-25 End Date: 23-Feb-25
Note on KP1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Delivered Start Date: 24-Feb-25 End Date: 28-Feb-25
Note on KQ1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Delivered Start Date: 24-Feb-25 End Date: 28-Feb-25
Note on KR1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Delivered Start Date: 24-Feb-25 End Date: 28-Feb-25
Note on KS1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Delivered Start Date: 24-Feb-25 End Date: 28-Feb-25
Note on KT1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Delivered Start Date: 24-Feb-25 End Date: 28-Feb-25
Note on KU1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- LV Switchgear (LVS) (Eaton) Shipping/ ROJ Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KV1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- LV Switchgear (LVS) (Eaton) Shipping/ ROJ Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KW1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- LV Switchgear (LVS) (Eaton) Shipping/ ROJ Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on KX1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- LV Switchgear (LVS) (Eaton) Shipping/ ROJ Start Date: 28-Feb-25 End Date: 04-Mar-25
Note on LB1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Receive Main LV Switch Board (MSB) (SOW Del Date- 3/8/2025) Start Date: 08-Mar-25 End Date: 08-Mar-25
Note on LC1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Shipped/ROJ Start Date: 09-Mar-25 End Date: 13-Mar-25
Note on LD1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Shipped/ROJ Start Date: 09-Mar-25 End Date: 13-Mar-25
Note on LE1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Shipped/ROJ Start Date: 09-Mar-25 End Date: 13-Mar-25
Note on LF1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Shipped/ROJ Start Date: 09-Mar-25 End Date: 13-Mar-25
Note on LG1145: Phase: MSFT OFCI ROJ Dates Location: COLO 3 Trade: ROJ Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Shipped/ROJ Start Date: 09-Mar-25 End Date: 13-Mar-25
Note on FB1193: Phase: MSFT OFCI ROJ Dates Location: COLO 3-5 Trade: ROJ Activity Name: OFCI- Receive PEMB Procurement (1st Del) (Nucor) (SOW Del Date-10/3/24) Start Date: 03-Oct-24 End Date: 03-Oct-24
Note on FT1193: Phase: MSFT OFCI ROJ Dates Location: COLO 3-5 Trade: ROJ Activity Name: OFCI- PEMB Procurement (1st Del) (Nucor) Shipping/ ROJ Start Date: 21-Oct-24 End Date: 25-Oct-24
Note on FU1193: Phase: MSFT OFCI ROJ Dates Location: COLO 3-5 Trade: ROJ Activity Name: OFCI- PEMB Procurement (1st Del) (Nucor) Shipping/ ROJ Start Date: 21-Oct-24 End Date: 25-Oct-24
Note on FV1193: Phase: MSFT OFCI ROJ Dates Location: COLO 3-5 Trade: ROJ Activity Name: OFCI- PEMB Procurement (1st Del) (Nucor) Shipping/ ROJ Start Date: 21-Oct-24 End Date: 25-Oct-24
Note on FW1193: Phase: MSFT OFCI ROJ Dates Location: COLO 3-5 Trade: ROJ Activity Name: OFCI- PEMB Procurement (1st Del) (Nucor) Shipping/ ROJ Start Date: 21-Oct-24 End Date: 25-Oct-24
Note on FX1193: Phase: MSFT OFCI ROJ Dates Location: COLO 3-5 Trade: ROJ Activity Name: OFCI- PEMB Procurement (1st Del) (Nucor) Shipping/ ROJ Start Date: 21-Oct-24 End Date: 25-Oct-24
Note on DZ1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Received SUB Warehouse 11/23/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 11/11/23) Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on ED1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/9/24) Start Date: 09-Sep-24 End Date: 09-Sep-24
Note on GD1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Reveive Power Distribution Units (PDU) (ABB) (SOW Del Date- 7/12/24) Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on IK1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 12/29/24) Start Date: 29-Dec-24 End Date: 29-Dec-24
Note on IL1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ Start Date: 29-Dec-24 End Date: 04-Jan-25
Note on IM1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ Start Date: 29-Dec-24 End Date: 04-Jan-25
Note on IN1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ Start Date: 29-Dec-24 End Date: 04-Jan-25
Note on IO1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ Start Date: 29-Dec-24 End Date: 04-Jan-25
Note on IP1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ Start Date: 29-Dec-24 End Date: 04-Jan-25
Note on IQ1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ Start Date: 29-Dec-24 End Date: 04-Jan-25
Note on KT1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Receive LV Switchgear (Eaton) (SOW Del Date- 2/28/25) Start Date: 28-Feb-25 End Date: 28-Feb-25
Note on KU1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- LV Switchgear (Eaton) Shipping/ROJ Start Date: 28-Feb-25 End Date: 02-Mar-25
Note on KV1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- LV Switchgear (Eaton) Shipping/ROJ Start Date: 28-Feb-25 End Date: 02-Mar-25
Note on LT1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LU1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LV1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LW1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LX1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LZ1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Shipping/ ROJ Start Date: 01-Apr-25 End Date: 05-Apr-25
Note on MA1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Shipping/ ROJ Start Date: 01-Apr-25 End Date: 05-Apr-25
Note on MB1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Shipping/ ROJ Start Date: 01-Apr-25 End Date: 05-Apr-25
Note on MC1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Shipping/ ROJ Start Date: 01-Apr-25 End Date: 05-Apr-25
Note on MD1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Air Handling Units (AHU) (Stulz) Shipping/ ROJ Start Date: 01-Apr-25 End Date: 05-Apr-25
Note on ME1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ Start Date: 06-Apr-25 End Date: 10-Apr-25
Note on MF1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ Start Date: 06-Apr-25 End Date: 10-Apr-25
Note on MG1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ Start Date: 06-Apr-25 End Date: 10-Apr-25
Note on MH1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ Start Date: 06-Apr-25 End Date: 10-Apr-25
Note on MI1196: Phase: MSFT OFCI ROJ Dates Location: COLO 4 Trade: ROJ Activity Name: OFCI- Packaged Diesel Generator Set (GEN) (CAT Holt) Shipping/ROJ Start Date: 06-Apr-25 End Date: 10-Apr-25
Note on DZ1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Received SUB Warehouse 12/28/2023 Static UPS System W/Batt (UPS) (Eaton) (SOW Del Date- 12/11/23) Start Date: 05-Sep-24 End Date: 05-Sep-24
Note on EK1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Receive Air Handling Units (AHU) (Stulz) (SOW Del Date- 9/16/24) Start Date: 16-Sep-24 End Date: 16-Sep-24
Note on GC1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Receive Medium Voltage Switchgear (MVS) (JDC Power Sys) (SOW Del Date- 10/30/24) Start Date: 30-Oct-24 End Date: 30-Oct-24
Note on GD1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Receive Utility Pad Mount Switchgear (UPM) (Del Date 10/30/2024) Start Date: 31-Oct-24 End Date: 31-Oct-24
Note on JO1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Receive Building Automation System (BAS) (Automated Logic Corp) (SOW Del Date- 1/28/25) Start Date: 28-Jan-25 End Date: 28-Jan-25
Note on JP1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ Start Date: 28-Jan-25 End Date: 02-Feb-25
Note on JQ1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ Start Date: 28-Jan-25 End Date: 02-Feb-25
Note on JR1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ Start Date: 28-Jan-25 End Date: 02-Feb-25
Note on JS1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ Start Date: 28-Jan-25 End Date: 02-Feb-25
Note on JT1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Building Automation System (BAS) (Automated Logic Corp) Shipping/ROJ Start Date: 28-Jan-25 End Date: 02-Feb-25
Note on LT1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LU1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LV1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LW1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LX1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Static UPS System W/Batt (UPS) (Eaton) Shipping/ROJ Start Date: 26-Mar-25 End Date: 30-Mar-25
Note on LY1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ Start Date: 30-Mar-25 End Date: 04-Apr-25
Note on LZ1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ Start Date: 30-Mar-25 End Date: 04-Apr-25
Note on MA1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ Start Date: 30-Mar-25 End Date: 04-Apr-25
Note on MB1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ Start Date: 30-Mar-25 End Date: 04-Apr-25
Note on MC1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Mech Power Distribution Panels (ADP) Shipping/ROJ Start Date: 30-Mar-25 End Date: 04-Apr-25
Note on MS1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Elec. Performance Monitoring Syst. (EPMS) (Schneider) Shipping/ROJ Start Date: 20-Apr-25 End Date: 20-Apr-25
Note on MX1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- HAC/Racking (Tate Access) Shipping/ROJ Start Date: 25-Apr-25 End Date: 28-Apr-25
Note on MY1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- HAC/Racking (Tate Access) Shipping/ROJ Start Date: 25-Apr-25 End Date: 28-Apr-25
Note on MZ1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- HAC/Racking (Tate Access) Shipping/ROJ Start Date: 25-Apr-25 End Date: 28-Apr-25
Note on NA1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- HAC/Racking (Tate Access) Shipping/ROJ Start Date: 25-Apr-25 End Date: 28-Apr-25
Note on NB1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ Start Date: 29-Apr-25 End Date: 03-May-25
Note on NC1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ Start Date: 29-Apr-25 End Date: 03-May-25
Note on ND1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ Start Date: 29-Apr-25 End Date: 03-May-25
Note on NE1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ Start Date: 29-Apr-25 End Date: 03-May-25
Note on NF1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Utility Pad Mount Switchgear (UPM) Shipping/ROJ Start Date: 29-Apr-25 End Date: 03-May-25
Note on NG1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ Start Date: 03-May-25 End Date: 07-May-25
Note on NH1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ Start Date: 03-May-25 End Date: 07-May-25
Note on NI1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ Start Date: 03-May-25 End Date: 07-May-25
Note on NJ1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Power Distribution Units (PDU) (ABB) Shipping/ROJ Start Date: 03-May-25 End Date: 07-May-25
Note on NN1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ Start Date: 11-May-25 End Date: 15-May-25
Note on NO1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ Start Date: 11-May-25 End Date: 15-May-25
Note on NP1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ Start Date: 11-May-25 End Date: 15-May-25
Note on NQ1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ Start Date: 11-May-25 End Date: 15-May-25
Note on NR1244: Phase: MSFT OFCI ROJ Dates Location: COLO 5 Trade: ROJ Activity Name: OFCI- Packaged Diesel Generator Set (GPC) (CAT Holt) Shipping/ROJ Start Date: 11-May-25 End Date: 15-May-25
Note on H1292: Phase: RFP / PSR Location: Milestone Trade: Milestone Activity Name: RFP- Microsoft Awards CHI11 Start Date: 06-May-24 End Date: 10-May-24
Note on I1292: Phase: RFP / PSR Location: Milestone Trade: Milestone Activity Name: RFP- Microsoft Awards CHI11 Start Date: 06-May-24 End Date: 10-May-24
Note on J1292: Phase: RFP / PSR Location: Milestone Trade: Milestone Activity Name: RFP- Microsoft Awards CHI11 Start Date: 06-May-24 End Date: 10-May-24
Note on K1292: Phase: RFP / PSR Location: Milestone Trade: Milestone Activity Name: RFP- Microsoft Awards CHI11 Start Date: 06-May-24 End Date: 10-May-24
Note on L1292: Phase: RFP / PSR Location: Milestone Trade: Milestone Activity Name: RFP- Microsoft Awards CHI11 Start Date: 06-May-24 End Date: 10-May-24
Note on AM1292: Phase: RFP / PSR Location: Milestone Trade: Milestone Activity Name: RFP- PSR Executed (Early Works) Start Date: 06-Jun-24 End Date: 06-Jun-24
Note on CI1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Site Mobilization Start Date: 24-Jul-24 End Date: 24-Jul-24
Note on CJ1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CK1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CL1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CM1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CN1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CO1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CP1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CQ1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CR1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CS1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CT1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CU1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CV1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CW1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on CX1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Set-Up Trailers & Install Temp Utilities Start Date: 25-Jul-24 End Date: 08-Aug-24
Note on DI1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DJ1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DK1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DL1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DM1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DN1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DO1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DP1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DQ1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DR1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DS1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DT1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DU1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DV1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DW1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DX1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on DY1292: Phase: Site Prep/ Mobilization Location: Milestone Trade: Milestone Activity Name: Fine Grading Building Pad Start Date: 19-Aug-24 End Date: 04-Sep-24
Note on EY1292: Phase: RFP / PSR Location: Milestone Trade: Milestone Activity Name: RFP- PSR Executed (Full GMP) Start Date: 30-Sep-24 End Date: 30-Sep-24
Note on ER1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on ES1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on ET1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on EU1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on EV1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on EW1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on EX1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on EY1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on EZ1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FA1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FB1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FC1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FD1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FE1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FF1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FG1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FH1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FI1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FJ1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FK1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FL1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FM1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FN1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FO1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FP1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FQ1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FR1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FS1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FT1300: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Deep Telecom Start Date: 23-Sep-24 End Date: 21-Oct-24
Note on FC1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FD1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FE1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FF1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FG1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FH1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FI1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FJ1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FK1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FL1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FM1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FN1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FO1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FP1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FQ1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FR1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FS1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FT1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FU1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FV1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FW1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FX1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FY1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on FZ1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on GA1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on GB1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on GC1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on GD1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on GE1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on GF1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on GG1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install MV Ductbanks Start Date: 04-Oct-24 End Date: 18-Nov-24
Note on GH1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Sanitary Lines Start Date: 04-Nov-24 End Date: 03-Dec-24
Note on GI1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Sanitary Lines Start Date: 04-Nov-24 End Date: 03-Dec-24
Note on GJ1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Sanitary Lines Start Date: 04-Nov-24 End Date: 03-Dec-24
Note on GK1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Sanitary Lines Start Date: 04-Nov-24 End Date: 03-Dec-24
Note on GL1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Sanitary Lines Start Date: 04-Nov-24 End Date: 03-Dec-24
Note on GM1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Storm Lines Start Date: 09-Nov-24 End Date: 17-Dec-24
Note on GN1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Storm Lines Start Date: 09-Nov-24 End Date: 17-Dec-24
Note on GO1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Storm Lines Start Date: 09-Nov-24 End Date: 17-Dec-24
Note on GP1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Storm Lines Start Date: 09-Nov-24 End Date: 17-Dec-24
Note on GQ1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Storm Lines Start Date: 09-Nov-24 End Date: 17-Dec-24
Note on GR1301: Phase: Site Utilities Location: Overall Trade: Framing Activity Name: Install Storm Lines Start Date: 09-Nov-24 End Date: 17-Dec-24
Note on GS1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on GT1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on GU1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on GV1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on GW1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on GX1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on GY1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on GZ1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HA1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HB1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HC1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HD1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HE1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HF1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HG1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HH1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HI1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HJ1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HK1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HL1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HM1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HN1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HO1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HP1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HQ1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HR1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HS1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HT1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HU1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HV1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HW1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HX1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HY1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on HZ1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on IA1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on IB1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on IC1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on ID1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on IE1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on IF1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on IG1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on IH1301: Phase: Site Utilities Location: Overall Trade: Electrical Activity Name: Install Water Line Start Date: 15-Nov-24 End Date: 26-Dec-24
Note on NH1301: Phase: Site Utilities Location: Overall Trade: Milestone Activity Name: Permanent Power (Need by Date) Start Date: 05-May-25 End Date: 05-May-25
Note on EM1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on EN1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on EO1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on EP1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on EQ1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on ER1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on ES1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on ET1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on EU1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on EV1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on EW1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on EX1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on EY1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on EZ1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on FA1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on FB1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on FC1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Telecom (under Building Pad) Start Date: 18-Sep-24 End Date: 04-Oct-24
Note on FD1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FE1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FF1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FG1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FH1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FI1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FJ1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FK1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FL1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FM1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FN1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FO1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FP1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FQ1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FR1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FS1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FT1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FU1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FV1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FW1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FX1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FY1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on FZ1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on GA1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on GB1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on GC1306: Phase: Site Utilities Location: Under Building Pad Trade: Electrical Activity Name: Install UG Electrical / UPM Crossing (under Building Pad) Start Date: 30-Sep-24 End Date: 30-Oct-24
Note on GK1306: Phase: Site Utilities Location: Under Building Pad Trade: Earthwork Activity Name: Backfill after UG work (MV / Telecom) Start Date: 07-Nov-24 End Date: 08-Nov-24
Note on GL1306: Phase: Site Utilities Location: Under Building Pad Trade: Earthwork Activity Name: Backfill after UG work (MV / Telecom) Start Date: 07-Nov-24 End Date: 08-Nov-24