## Sheet1
CPM | [6 empty] | 2024 | 2024
[7 empty] | Sep | Sep | [23 empty] | Oct
PM | LT | PM | LT | PM | PM | PM | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
Phase | Location | Trade | Activity Code | Activity Name | Start | Finish | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Phase 1 | Zone 1 | Trade 1 | 1A | Activity 1 | 6-Sep-24 | 20-Sep-24 | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | [9 empty] | 1B | 1B | 1B | 1B | 1B | 1B |  | 1E | 1E | 1E | 1E | 1E | 1E
Phase 1 | Zone 1 | Trade 2 | 2A | Activity 1 | 9-Sep-24 | 15-Sep-24 |  |  |  | 2A | 2A | 2A | 2A | 2A | 2A | 2A | 2B | 2B | 2B | 2B | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C |  |  |  |  | 2C | 2C | 2C | 2C | 2C | 2E | 2E | 2E
Phase 1 | Zone 1 | Trade 1 | 1B | Activity 2 | 30-Sep-24 | 5-Oct-24 | [22 empty] | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D
Phase 1 | Zone 1 | Trade 2 | 2B | Activity 2 | 16-Sep-24 | 19-Sep-24 | [29 empty] | 2D | 2D | 2D
Phase 1 | Zone 1 | Trade 1 | 1C | Activity 3 | 20-Sep-24 | 30-Sep-24
Phase 1 | Zone 1 | Trade 2 | 2C | Activity 3 | 5-Oct-24 | 9-Oct-24
Phase 1 | Zone 1 | Trade 1 | 1D | Activity 4 | 28-Sep-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | 2D | Activity 4 | 5-Oct-24 | 7-Oct-24
Phase 1 | Zone 1 | Trade 1 | 1E | Activity 5 | 7-Oct-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | 2E | Activity 5 | 10-Oct-24 | 12-Oct-24
phase | trade | activity_code | activity_name
Phase 1 | Trade 1 | 1A | Activity 1
|  | 1B | Activity 2
|  | 1C | Activity 3
|  | 1D | Activity 4
|  | 1E | Activity 5
| Trade 2 | 2A | Activity 1
|  | 2B | Activity 2
|  | 2C | Activity 3
|  | 2D | Activity 4
|  | 2E | Activity 5

## Sheet2
CPM | [7 empty] | 2024 | 2024
[8 empty] | Sep | Sep | [23 empty] | Oct
PM | LT | PM |  | LT | PM | PM | PM | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1A | Activity 1 | 6-Sep-24 | 20-Sep-24 | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | 1A | [9 empty] | 1B | 1B | 1B | 1B | 1B | 1B |  | 1E | 1E | 1E | 1E | 1E | 1E
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2A | Activity 1 | 9-Sep-24 | 15-Sep-24 |  |  |  | 2A | 2A | 2A | 2A | 2A | 2A | 2A | 2B | 2B | 2B | 2B | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C |  |  |  |  | 2C | 2C | 2C | 2C | 2C | 2E | 2E | 2E
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1B | Activity 2 | 30-Sep-24 | 5-Oct-24 | [22 empty] | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D | 1D
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2B | Activity 2 | 16-Sep-24 | 19-Sep-24 | [29 empty] | 2D | 2D | 2D
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1C | Activity 3 | 20-Sep-24 | 30-Sep-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2C | Activity 3 | 5-Oct-24 | 9-Oct-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1D | Activity 4 | 28-Sep-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2D | Activity 4 | 5-Oct-24 | 7-Oct-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1E | Activity 5 | 7-Oct-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2E | Activity 5 | 10-Oct-24 | 12-Oct-24
phase | trade | activity_code | activity_name
Phase 1 | Trade 1 | 1A | Activity 1
|  | 1B | Activity 2
|  | 1C | Activity 3
|  | 1D | Activity 4
|  | 1E | Activity 5
| Trade 2 | 2A | Activity 1
|  | 2B | Activity 2
|  | 2C | Activity 3
|  | 2D | Activity 4
|  | 2E | Activity 5

## Test Dani
CPM | [7 empty] | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024
[8 empty] | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct
PM | LT | PM |  | LT | PM | PM | PM | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1A | Activity 1 | 6-Sep-24 | 20-Sep-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2A | Activity 1 | 9-Sep-24 | 15-Sep-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1B | Activity 2 | 30-Sep-24 | 5-Oct-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2B | Activity 2 | 16-Sep-24 | 19-Sep-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1C | Activity 3 | 20-Sep-24 | 30-Sep-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2C | Activity 3 | 5-Oct-24 | 9-Oct-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1D | Activity 4 | 28-Sep-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2D | Activity 4 | 5-Oct-24 | 7-Oct-24
Phase 1 | Zone 1 | Trade 1 | #8ED973 | 1E | Activity 5 | 7-Oct-24 | 12-Oct-24
Phase 1 | Zone 1 | Trade 2 | #4D93D9 | 2E | Activity 5 | 10-Oct-24 | 12-Oct-24
phase | trade | activity_code | activity_name
Phase 1 | Trade 1 | 1A | Activity 1
|  | 1B | Activity 2
|  | 1C | Activity 3
|  | 1D | Activity 4
|  | 1E | Activity 5
| Trade 2 | 2A | Activity 1
|  | 2B | Activity 2
|  | 2C | Activity 3
|  | 2D | Activity 4
|  | 2E | Activity 5

## Framework
CPM | [7 empty] | Gantt
PM | LT | PM | LT | PM | PM | PM
Phase | Location | Trade | Activity Code | Activity Name | Start | Finish |  | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12
Phase 1 | Zone 1 | Trade 1 | 1A | Activity 1 | 2024-09-06 | 2024-09-20 | bar: 2024-09-06 to 2024-09-20
Phase 1 | Zone 1 | Trade 2 | 2A | Activity 1 | 2024-09-09 | 2024-09-15 | bar: 2024-09-09 to 2024-09-15
Phase 1 | Zone 1 | Trade 1 | 1B | Activity 2 | 2024-09-30 | 2024-10-05 | bar: 2024-09-30 to 2024-10-05
Phase 1 | Zone 1 | Trade 2 | 2B | Activity 2 | 2024-09-16 | 2024-09-19 | bar: 2024-09-16 to 2024-09-19
Phase 1 | Zone 1 | Trade 1 | 1C | Activity 3 | 2024-09-20 | 2024-09-30 | bar: 2024-09-20 to 2024-09-30
Phase 1 | Zone 1 | Trade 2 | 2C | Activity 3 | 2024-10-05 | 2024-10-09 | bar: 2024-10-05 to 2024-10-09
Phase 1 | Zone 1 | Trade 1 | 1D | Activity 4 | 2024-09-28 | 2024-10-12 | bar: 2024-09-28 to 2024-10-12
Phase 1 | Zone 1 | Trade 2 | 2D | Activity 4 | 2024-10-05 | 2024-10-07 | bar: 2024-10-05 to 2024-10-07
Phase 1 | Zone 1 | Trade 1 | 1E | Activity 5 | 2024-10-07 | 2024-10-12 | bar: 2024-10-07 to 2024-10-12
Phase 1 | Zone 1 | Trade 2 | 2E | Activity 5 | 2024-10-10 | 2024-10-12 | bar: 2024-10-10 to 2024-10-12
Will be there | Might be there | Not there | Not there | Will be there | Will be there | Will be there
looking for unique and looking same activities done by same trade
Flow Analysis
Legend
[6 empty] | Trade 1 |  | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12
[6 empty] | 1A | Activity 1 | bar: 2024-09-06 to 2024-09-20; 2024-09-28 to 2024-10-12
[6 empty] | 1B | Activity 2 |  |  |  | 2A | 2A | 2A | 2A | 2A | 2A | 2A | 2B | 2B | 2B | 2B | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C | 1C |  |  |  |  | 2C | 2C | 2C | 2C | 2C | 2E | 2E | 2E
[6 empty] | 1C | Activity 3 | bar: 2024-09-30 to 2024-10-05; 2024-10-07 to 2024-10-12
[6 empty] | 1D | Activity 4 | bar: 2024-10-05 to 2024-10-07
[6 empty] | 1E | Activity 5
Trade 2
[6 empty] | 2A | Activity 1
[6 empty] | 2B | Activity 2
[6 empty] | 2C | Activity 3
[6 empty] | 2D | Activity 4
[6 empty] | 2E | Activity 5