## CFA - Fill Table
| UID | ID | Name | Type | IsNull | WBS | OutlineNumber | OutlineLevel | Priority | Start | Finish | Duration | DurationFormat | ResumeValid | EffortDriven | Recurring | OverAllocated | Estimated | Milestone | Summary | Critical | IsSubproject | IsSubprojectReadOnly | ExternalTask | EarlyStart | EarlyFinish | LateStart | LateFinish | StartVariance | FinishVariance | FixedCostAccrual | RemainingDuration | ConstraintType | CalendarUID | LevelAssignments | LevelingCanSplit | IgnoreResourceCalendar | HideBar | Rollup | EarnedValueMethod | Baseline | Active | Manual | ManualStart | ManualFinish | ManualDuration | Work | Stop | PercentComplete | ActualStart | ActualDuration | ActualWork | Notes | PhysicalPercentComplete | PredecessorLink | WorkVariance
0 | 1 | 1 | 3.0, 4.0. 5.0 pre, during and post construction total job | 0 | 0 | 1 | 1 | 1 | 500 | 2023-09-28T08:00:00 | 2025-05-05T17:00:00 | PT3272H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2025-05-05T17:00:00 | 2023-09-28T08:00:00 | 2025-05-05T17:00:00 | -480000 | -1920000 | 3 | PT3272H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2025-05-05T17:00:00 | PT3272H0M0S
1 | 2 | 2 | 3.0 Pre construction and mobilization | 0 | 0 | 2 | 2 | 2 | 500 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | -480000 |  | 3 | PT480H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S
2 | 3 | 3 | Assign Permits check list | 0 | 0 | 2.1 | 2.1 | 3 | 500 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | PT480H0M0S | 2023-12-20T17:00:00 | 100 | 2023-09-28T08:00:00 | PT480H0M0S | PT480H0M0S | ---- Task Notes ---- 3. Assign Permits check list ---- Field Notes ---- 3. Assign Permits check list ---- Sub Notes ---- 3. Assign Permits check list | 100
3 | 4 | 4 | Assign Health and Safety checklist | 0 | 0 | 2.2 | 2.2 | 3 | 500 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | PT480H0M0S | 2023-12-20T17:00:00 | 100 | 2023-09-28T08:00:00 | PT480H0M0S | PT480H0M0S |  | 100
4 | 5 | 5 | Assign Mobilization check list | 0 | 0 | 2.3 | 2.3 | 3 | 500 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | PT480H0M0S | 2023-12-20T17:00:00 | 100 | 2023-09-28T08:00:00 | PT480H0M0S | PT480H0M0S |  | 100
5 | 6 | 6 | Assign Equipment & Tools check list | 0 | 0 | 2.4 | 2.4 | 3 | 500 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | PT480H0M0S | 2023-12-20T17:00:00 | 100 | 2023-09-28T08:00:00 | PT480H0M0S | PT480H0M0S |  | 100
6 | 7 | 7 | Assign Safety Equipment and Materials checklist | 0 | 0 | 2.5 | 2.5 | 3 | 500 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | PT480H0M0S | 2023-12-20T17:00:00 | 100 | 2023-09-28T08:00:00 | PT480H0M0S | PT480H0M0S |  | 100
7 | 8 | 8 | Assign Procurement Plan check list | 0 | 0 | 2.6 | 2.6 | 3 | 500 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | PT480H0M0S | 2023-12-20T17:00:00 | 100 | 2023-09-28T08:00:00 | PT480H0M0S | PT480H0M0S |  | 100
8 | 9 | 9 | Assign Site Services Planning check list | 0 | 0 | 2.7 | 2.7 | 3 | 500 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | PT480H0M0S | 2023-12-20T17:00:00 | 100 | 2023-09-28T08:00:00 | PT480H0M0S | PT480H0M0S |  | 100
9 | 10 | 10 | Assign Sub Contractor planning checklist | 0 | 0 | 2.8 | 2.8 | 3 | 500 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | PT480H0M0S | 2023-12-20T17:00:00 | 100 | 2023-09-28T08:00:00 | PT480H0M0S | PT480H0M0S |  | 100
10 | 11 | 11 | Assign Project Team | 0 | 0 | 2.9 | 2.9 | 3 | 500 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2023-12-20T17:00:00 | PT480H0M0S | PT480H0M0S | 2023-12-20T17:00:00 | 100 | 2023-09-28T08:00:00 | PT480H0M0S | PT480H0M0S |  | 100
11 | 12 | 12 | Hold Pre Kick-Off meeting with Engineers and Trades people | 0 | 0 | 2.10 | 2.10 | 3 | 500 | 2023-09-28T08:00:00 | 2023-10-02T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2023-10-02T17:00:00 | 2023-09-28T08:00:00 | 2023-10-02T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2023-10-02T17:00:00 | PT24H0M0S | PT24H0M0S | 2023-10-02T17:00:00 | 100 | 2023-09-28T08:00:00 | PT24H0M0S | PT24H0M0S |  | 100
12 | 13 | 13 | Assign hollow core ordering checklist | 0 | 0 | 2.11 | 2.11 | 3 | 500 | 2023-09-28T08:00:00 | 2023-09-28T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2023-09-28T17:00:00 | 2023-09-28T08:00:00 | 2023-09-28T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2023-09-28T17:00:00 | PT8H0M0S | PT8H0M0S | 2023-09-28T17:00:00 | 100 | 2023-09-28T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
13 | 14 | 14 | Organize site team to have training and certificates | 0 | 0 | 2.12 | 2.12 | 3 | 500 | 2023-09-28T08:00:00 | 2023-09-28T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-28T08:00:00 | 2023-09-28T17:00:00 | 2023-09-28T08:00:00 | 2023-09-28T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-09-28T08:00:00 | 2023-09-28T17:00:00 | PT8H0M0S | PT8H0M0S | 2023-09-28T17:00:00 | 100 | 2023-09-28T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
14 | 15 | 15 | Order Rebar (30 days before site delivery date required) | 0 | 0 | 2.13 | 2.13 | 3 | 500 | 2023-12-08T08:00:00 | 2023-12-08T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-08T08:00:00 | 2023-12-08T17:00:00 | 2023-12-08T08:00:00 | 2023-12-08T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-12-08T08:00:00 | 2023-12-08T17:00:00 | PT8H0M0S | PT8H0M0S | 2023-12-08T17:00:00 | 100 | 2023-12-08T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
15 | 16 | 16 | 4.1 Site Services & Foundation Work | 0 | 0 | 3 | 3 | 2 | 500 | 2023-12-21T08:00:00 | 2024-03-25T17:00:00 | PT520H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2023-12-21T08:00:00 | 2024-03-25T17:00:00 | 2023-12-21T08:00:00 | 2024-03-25T17:00:00 | -480000 |  | 3 | PT520H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-12-21T08:00:00 | 2024-03-25T17:00:00 | PT520H0M0S
16 | 17 | 17 | Site Preparation | 0 | 0 | 4 | 4 | 3 | 500 | 2023-12-21T08:00:00 | 2024-01-05T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2023-12-21T08:00:00 | 2024-01-05T17:00:00 | 2023-12-21T08:00:00 | 2024-01-05T17:00:00 | -480000 |  | 3 | PT72H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-12-21T08:00:00 | 2024-01-05T17:00:00 | PT72H0M0S
17 | 18 | 18 | 18. Assign site prep check list (First) | 0 | 0 | 4.1 | 4.1 | 4 | 500 | 2023-12-28T08:00:00 | 2023-12-28T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-28T08:00:00 | 2023-12-28T17:00:00 | 2023-12-28T08:00:00 | 2023-12-28T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-12-28T08:00:00 | 2023-12-28T17:00:00 | PT8H0M0S | PT8H0M0S | 2023-12-28T17:00:00 | 100 | 2023-12-28T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
18 | 19 | 19 | deliver rebar (footings and gradebeam only) | 0 | 0 | 4.2 | 4.2 | 4 | 500 | 2023-12-21T08:00:00 | 2023-12-21T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-21T08:00:00 | 2023-12-21T17:00:00 | 2023-12-21T08:00:00 | 2023-12-21T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-12-21T08:00:00 | 2023-12-21T17:00:00 | PT8H0M0S | PT8H0M0S | 2023-12-21T17:00:00 | 100 | 2023-12-21T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
19 | 20 | 20 | Order all Anchor bolts | 0 | 0 | 4.3 | 4.3 | 4 | 500 | 2023-12-21T08:00:00 | 2023-12-21T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-21T08:00:00 | 2023-12-21T17:00:00 | 2023-12-21T08:00:00 | 2023-12-21T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-12-21T08:00:00 | 2023-12-21T17:00:00 | PT8H0M0S | PT8H0M0S | 2023-12-21T17:00:00 | 100 | 2023-12-21T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
20 | 21 | 21 | Schedule locates to be done | 0 | 0 | 4.4 | 4.4 | 4 | 500 | 2023-12-21T08:00:00 | 2023-12-27T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-21T08:00:00 | 2023-12-27T17:00:00 | 2023-12-21T08:00:00 | 2023-12-27T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-12-21T08:00:00 | 2023-12-27T17:00:00 | PT24H0M0S | PT24H0M0S | 2023-12-27T17:00:00 | 100 | 2023-12-21T08:00:00 | PT24H0M0S | PT24H0M0S |  | 100
21 | 22 | 22 | Survey for balcony piles | 0 | 0 | 4.5 | 4.5 | 4 | 500 | 2023-12-21T08:00:00 | 2023-12-22T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-21T08:00:00 | 2023-12-22T17:00:00 | 2023-12-21T08:00:00 | 2023-12-22T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-12-21T08:00:00 | 2023-12-22T17:00:00 | PT16H0M0S | PT16H0M0S | 2023-12-22T17:00:00 | 100 | 2023-12-21T08:00:00 | PT16H0M0S | PT16H0M0S |  | 100
22 | 23 | 23 | Schedule Pile contractor | 0 | 0 | 4.6 | 4.6 | 4 | 500 | 2023-12-21T08:00:00 | 2023-12-21T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-21T08:00:00 | 2023-12-21T17:00:00 | 2023-12-21T08:00:00 | 2023-12-21T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-12-21T08:00:00 | 2023-12-21T17:00:00 | PT8H0M0S | PT8H0M0S | 2023-12-21T17:00:00 | 100 | 2023-12-21T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
23 | 24 | 24 | Install balcony piles | 0 | 0 | 4.7 | 4.7 | 4 | 500 | 2023-12-25T08:00:00 | 2023-12-27T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-25T08:00:00 | 2023-12-27T17:00:00 | 2023-12-25T08:00:00 | 2023-12-27T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-12-25T08:00:00 | 2023-12-27T17:00:00 | PT8H0M0S | PT8H0M0S | 2023-12-27T17:00:00 | 100 | 2023-12-25T08:00:00 | PT8H0M0S | PT8H0M0S | Are these screw piles? Why are we installing these before the foundation? | 100
24 | 25 | 25 | Strip site | 0 | 0 | 4.8 | 4.8 | 4 | 500 | 2023-12-29T08:00:00 | 2024-01-04T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-29T08:00:00 | 2024-01-04T17:00:00 | 2023-12-29T08:00:00 | 2024-01-04T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2023-12-29T08:00:00 | 2024-01-04T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-01-04T17:00:00 | 100 | 2023-12-29T08:00:00 | PT32H0M0S | PT32H0M0S |  | 100
25 | 26 | 26 | Measure corner offsets for excavation | 0 | 0 | 4.9 | 4.9 | 4 | 500 | 2024-01-05T08:00:00 | 2024-01-05T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-01-05T08:00:00 | 2024-01-05T17:00:00 | 2024-01-05T08:00:00 | 2024-01-05T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-01-05T08:00:00 | 2024-01-05T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-01-05T17:00:00 | 100 | 2024-01-05T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
26 | 27 | 27 | Excavation | 0 | 0 | 5 | 5 | 3 | 500 | 2024-01-08T08:00:00 | 2024-01-18T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-01-08T08:00:00 | 2024-01-18T17:00:00 | 2024-01-08T08:00:00 | 2024-01-18T17:00:00 | -480000 |  | 3 | PT72H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-01-08T08:00:00 | 2024-01-18T17:00:00 | PT72H0M0S
27 | 28 | 28 | 28. Assign Pre excavation checklist | 0 | 0 | 5.1 | 5.1 | 4 | 500 | 2024-01-08T08:00:00 | 2024-01-08T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-01-08T08:00:00 | 2024-01-08T17:00:00 | 2024-01-08T08:00:00 | 2024-01-08T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-01-08T08:00:00 | 2024-01-08T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-01-08T17:00:00 | 100 | 2024-01-08T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
28 | 29 | 29 | Dig footing and parkade foot print | 0 | 0 | 5.2 | 5.2 | 4 | 500 | 2024-01-08T08:00:00 | 2024-01-16T17:00:00 | PT56H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-01-08T08:00:00 | 2024-01-16T17:00:00 | 2024-01-08T08:00:00 | 2024-01-16T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-01-08T08:00:00 | 2024-01-16T17:00:00 | PT56H0M0S | PT56H0M0S | 2024-01-16T17:00:00 | 100 | 2024-01-08T08:00:00 | PT56H0M0S | PT56H0M0S |  | 100
29 | 30 | 30 | Survey offsets, and footings | 0 | 0 | 5.3 | 5.3 | 4 | 500 | 2024-01-17T08:00:00 | 2024-01-17T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-01-17T08:00:00 | 2024-01-17T17:00:00 | 2024-01-17T08:00:00 | 2024-01-17T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-01-17T08:00:00 | 2024-01-17T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-01-17T17:00:00 | 100 | 2024-01-17T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
30 | 31 | 31 | Geo Tech Engineer inspection | 0 | 0 | 5.4 | 5.4 | 4 | 500 | 2024-01-18T08:00:00 | 2024-01-18T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-01-18T08:00:00 | 2024-01-18T17:00:00 | 2024-01-18T08:00:00 | 2024-01-18T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-01-18T08:00:00 | 2024-01-18T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-01-18T17:00:00 | 100 | 2024-01-18T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
31 | 32 | 32 | Foundation | 0 | 0 | 6 | 6 | 3 | 500 | 2024-01-19T08:00:00 | 2024-02-29T17:00:00 | PT240H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-01-19T08:00:00 | 2024-02-29T17:00:00 | 2024-01-19T08:00:00 | 2024-02-29T17:00:00 | -480000 |  | 3 | PT240H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-01-19T08:00:00 | 2024-02-29T17:00:00 | PT240H0M0S
32 | 33 | 33 | Form footings | 0 | 0 | 6.1 | 6.1 | 4 | 500 | 2024-01-19T08:00:00 | 2024-01-24T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-01-19T08:00:00 | 2024-01-24T17:00:00 | 2024-01-19T08:00:00 | 2024-01-24T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-01-19T08:00:00 | 2024-01-24T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-01-24T17:00:00 | 100 | 2024-01-19T08:00:00 | PT32H0M0S | PT32H0M0S |  | 100
33 | 34 | 34 | Tie footing rebar | 0 | 0 | 6.2 | 6.2 | 4 | 500 | 2024-01-25T08:00:00 | 2024-01-31T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-01-25T08:00:00 | 2024-01-31T17:00:00 | 2024-01-25T08:00:00 | 2024-01-31T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-01-25T08:00:00 | 2024-01-31T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-01-31T17:00:00 | 100 | 2024-01-25T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
34 | 35 | 35 | Rebar Inspection Structural Engineer | 0 | 0 | 6.3 | 6.3 | 4 | 500 | 2024-02-01T08:00:00 | 2024-02-01T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-02-01T08:00:00 | 2024-02-01T17:00:00 | 2024-02-01T08:00:00 | 2024-02-01T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-02-01T08:00:00 | 2024-02-01T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-02-01T17:00:00 | 100 | 2024-02-01T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
35 | 36 | 36 | Assign pre-pour checklist | 0 | 0 | 6.4 | 6.4 | 4 | 500 | 2024-02-02T08:00:00 | 2024-02-02T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-02-02T08:00:00 | 2024-02-02T17:00:00 | 2024-02-02T08:00:00 | 2024-02-02T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-02-02T08:00:00 | 2024-02-02T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-02-02T17:00:00 | 100 | 2024-02-02T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
36 | 37 | 37 | Pour footings | 0 | 0 | 6.5 | 6.5 | 4 | 500 | 2024-02-05T08:00:00 | 2024-02-05T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-02-05T08:00:00 | 2024-02-05T17:00:00 | 2024-02-05T08:00:00 | 2024-02-05T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-02-05T08:00:00 | 2024-02-05T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-02-05T17:00:00 | 100 | 2024-02-05T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
37 | 38 | 38 | Form grade beam | 0 | 0 | 6.6 | 6.6 | 4 | 500 | 2024-02-06T08:00:00 | 2024-02-14T17:00:00 | PT56H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-02-06T08:00:00 | 2024-02-14T17:00:00 | 2024-02-06T08:00:00 | 2024-02-14T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-02-06T08:00:00 | 2024-02-14T17:00:00 | PT56H0M0S | PT56H0M0S | 2024-02-14T17:00:00 | 100 | 2024-02-06T08:00:00 | PT56H0M0S | PT56H0M0S |  | 100
38 | 39 | 39 | Build templates for Anchor bolts | 0 | 0 | 6.7 | 6.7 | 4 | 500 | 2024-02-15T08:00:00 | 2024-02-15T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-02-15T08:00:00 | 2024-02-15T17:00:00 | 2024-02-15T08:00:00 | 2024-02-15T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-02-15T08:00:00 | 2024-02-15T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-02-15T17:00:00 | 100 | 2024-02-15T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
39 | 40 | 40 | Tie Grade beam rebar | 0 | 0 | 6.8 | 6.8 | 4 | 500 | 2024-02-16T08:00:00 | 2024-02-26T17:00:00 | PT56H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-02-16T08:00:00 | 2024-02-26T17:00:00 | 2024-02-16T08:00:00 | 2024-02-26T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-02-16T08:00:00 | 2024-02-26T17:00:00 | PT56H0M0S | PT56H0M0S | 2024-02-26T17:00:00 | 100 | 2024-02-16T08:00:00 | PT56H0M0S | PT56H0M0S |  | 100
40 | 41 | 41 | Ensure Sleeves for electrical are run in the grade beam prior to pouring | 0 | 0 | 6.9 | 6.9 | 4 | 500 | 2024-02-06T08:00:00 | 2024-02-06T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-02-06T08:00:00 | 2024-02-06T17:00:00 | 2024-02-06T08:00:00 | 2024-02-06T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-02-06T08:00:00 | 2024-02-06T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-02-06T17:00:00 | 100 | 2024-02-06T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
41 | 42 | 42 | Assign pre concrete pour checklist | 0 | 0 | 6.10 | 6.10 | 4 | 500 | 2024-02-27T08:00:00 | 2024-02-27T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-02-27T08:00:00 | 2024-02-27T17:00:00 | 2024-02-27T08:00:00 | 2024-02-27T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-02-27T08:00:00 | 2024-02-27T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-02-27T17:00:00 | 100 | 2024-02-27T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
42 | 43 | 43 | Rebar inspection Structural Engineer | 0 | 0 | 6.11 | 6.11 | 4 | 500 | 2024-02-28T08:00:00 | 2024-02-28T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-02-28T08:00:00 | 2024-02-28T17:00:00 | 2024-02-28T08:00:00 | 2024-02-28T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-02-28T08:00:00 | 2024-02-28T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-02-28T17:00:00 | 100 | 2024-02-28T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
43 | 44 | 44 | Pour grade beam | 0 | 0 | 6.12 | 6.12 | 4 | 500 | 2024-02-29T08:00:00 | 2024-02-29T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-02-29T08:00:00 | 2024-02-29T17:00:00 | 2024-02-29T08:00:00 | 2024-02-29T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-02-29T08:00:00 | 2024-02-29T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-02-29T17:00:00 | 100 | 2024-02-29T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
44 | 45 | 45 | Back fill foundation | 0 | 0 | 7 | 7 | 3 | 500 | 2024-03-01T08:00:00 | 2024-03-14T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-03-01T08:00:00 | 2024-03-14T17:00:00 | 2024-03-01T08:00:00 | 2024-03-14T17:00:00 | -480000 |  | 3 | PT80H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-01T08:00:00 | 2024-03-14T17:00:00 | PT80H0M0S
45 | 46 | 46 | Assign pre back fill check list | 0 | 0 | 7.1 | 7.1 | 4 | 500 | 2024-03-01T08:00:00 | 2024-03-01T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-01T08:00:00 | 2024-03-01T17:00:00 | 2024-03-01T08:00:00 | 2024-03-01T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-01T08:00:00 | 2024-03-01T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-03-01T17:00:00 | 100 | 2024-03-01T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
46 | 47 | 47 | Install underground insulation | 0 | 0 | 7.2 | 7.2 | 4 | 500 | 2024-03-04T08:00:00 | 2024-03-05T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-04T08:00:00 | 2024-03-05T17:00:00 | 2024-03-04T08:00:00 | 2024-03-05T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-04T08:00:00 | 2024-03-05T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-03-05T17:00:00 | 100 | 2024-03-04T08:00:00 | PT16H0M0S | PT16H0M0S |  | 100
47 | 48 | 48 | Back fill exterior grade beam | 0 | 0 | 7.3 | 7.3 | 4 | 500 | 2024-03-06T08:00:00 | 2024-03-07T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-06T08:00:00 | 2024-03-07T17:00:00 | 2024-03-06T08:00:00 | 2024-03-07T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-06T08:00:00 | 2024-03-07T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-03-07T17:00:00 | 100 | 2024-03-06T08:00:00 | PT16H0M0S | PT16H0M0S |  | 100
48 | 49 | 49 | Back fill interior parkade | 0 | 0 | 7.4 | 7.4 | 4 | 500 | 2024-03-08T08:00:00 | 2024-03-14T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-08T08:00:00 | 2024-03-14T17:00:00 | 2024-03-08T08:00:00 | 2024-03-14T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-08T08:00:00 | 2024-03-14T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-03-14T17:00:00 | 100 | 2024-03-08T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
49 | 50 | 50 | Site services W/S/S install | 0 | 0 | 8 | 8 | 3 | 500 | 2024-03-15T08:00:00 | 2024-03-25T17:00:00 | PT56H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-03-15T08:00:00 | 2024-03-25T17:00:00 | 2024-03-15T08:00:00 | 2024-03-25T17:00:00 | -480000 |  | 3 | PT56H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-15T08:00:00 | 2024-03-25T17:00:00 | PT56H0M0S
50 | 51 | 51 | Assign water and sewer and storm checklist | 0 | 0 | 8.1 | 8.1 | 4 | 500 | 2024-03-15T08:00:00 | 2024-03-15T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-15T08:00:00 | 2024-03-15T17:00:00 | 2024-03-15T08:00:00 | 2024-03-15T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-15T08:00:00 | 2024-03-15T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-03-15T17:00:00 | 100 | 2024-03-15T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
51 | 52 | 52 | Install water and sewer | 0 | 0 | 8.2 | 8.2 | 4 | 500 | 2024-03-18T08:00:00 | 2024-03-22T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-18T08:00:00 | 2024-03-22T17:00:00 | 2024-03-18T08:00:00 | 2024-03-22T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-18T08:00:00 | 2024-03-22T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-03-22T17:00:00 | 100 | 2024-03-18T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
52 | 53 | 53 | Assign water and sewer commissioning checklist | 0 | 0 | 8.3 | 8.3 | 4 | 500 | 2024-03-25T08:00:00 | 2024-03-25T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-25T08:00:00 | 2024-03-25T17:00:00 | 2024-03-25T08:00:00 | 2024-03-25T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-25T08:00:00 | 2024-03-25T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-03-25T17:00:00 | 100 | 2024-03-25T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
53 | 54 | 54 | Commision Water/sewer/storm | 0 | 0 | 8.4 | 8.4 | 4 | 500 | 2024-03-25T08:00:00 | 2024-03-25T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-25T08:00:00 | 2024-03-25T17:00:00 | 2024-03-25T08:00:00 | 2024-03-25T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-25T08:00:00 | 2024-03-25T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-03-25T17:00:00 | 100 | 2024-03-25T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
54 | 55 | 55 | Strucutral Steel | 0 | 0 | 9 | 9 | 3 | 500 | 2024-03-15T08:00:00 | 2024-03-21T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-03-15T08:00:00 | 2024-03-21T17:00:00 | 2024-03-15T08:00:00 | 2024-03-21T17:00:00 | -480000 | 480000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-15T08:00:00 | 2024-03-21T17:00:00 | PT40H0M0S
55 | 56 | 56 | Assign structural steel checklist | 0 | 0 | 9.1 | 9.1 | 4 | 500 | 2024-03-15T08:00:00 | 2024-03-15T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-15T08:00:00 | 2024-03-15T17:00:00 | 2024-03-15T08:00:00 | 2024-03-15T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-15T08:00:00 | 2024-03-15T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-03-15T17:00:00 | 100 | 2024-03-15T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
56 | 57 | 57 | Structural steel delivered and sorted onsite | 0 | 0 | 9.2 | 9.2 | 4 | 500 | 2024-03-18T08:00:00 | 2024-03-18T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-18T08:00:00 | 2024-03-18T17:00:00 | 2024-03-18T08:00:00 | 2024-03-18T17:00:00 | -480000 |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-18T08:00:00 | 2024-03-18T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-03-18T17:00:00 | 100 | 2024-03-18T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
57 | 58 | 58 | Structural steel erection | 0 | 0 | 9.3 | 9.3 | 4 | 500 | 2024-03-20T08:00:00 | 2024-03-21T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-20T08:00:00 | 2024-03-21T17:00:00 | 2024-03-20T08:00:00 | 2024-03-21T17:00:00 |  | 480000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-03-20T08:00:00 | 2024-03-21T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-03-21T17:00:00 | 100 | 2024-03-20T08:00:00 | PT16H0M0S | PT16H0M0S | ---- Field Notes ---- Started on schedule but missed the west beam; had to return on March 28 to finish. Snowstorm delayed the framer so this mishap did not affect other trades. - 10/04/2024 20:07:37 by David Neufeld | 100
58 | 59 | 59 | 4.2 Framing | 0 | 0 | 10 | 10 | 2 | 500 | 2024-04-11T08:00:00 | 2025-01-03T17:00:00 | PT1488H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-04-11T08:00:00 | 2025-01-03T17:00:00 | 2024-04-11T08:00:00 | 2025-01-03T17:00:00 | 6720000 | 59040000 | 3 | PT1488H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-04-11T08:00:00 | 2025-01-03T17:00:00 | PT1488H0M0S
59 | 60 | 60 | Rough in parkade slab | 0 | 0 | 11 | 11 | 3 | 500 | 2024-06-12T08:00:00 | 2024-06-26T17:00:00 | PT88H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-06-12T08:00:00 | 2024-06-26T17:00:00 | 2024-06-12T08:00:00 | 2024-06-26T17:00:00 | 27840000 | 28800000 | 3 | PT88H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-12T08:00:00 | 2024-06-26T17:00:00 | PT88H0M0S
60 | 61 | 61 | Mechanical rough in in slab | 0 | 0 | 11.1 | 11.1 | 4 | 500 | 2024-06-12T08:00:00 | 2024-06-18T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-06-12T08:00:00 | 2024-06-18T17:00:00 | 2024-06-12T08:00:00 | 2024-06-18T17:00:00 | 27840000 | 28320000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-12T08:00:00 | 2024-06-18T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-06-18T17:00:00 | 100 | 2024-06-12T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
61 | 62 | 62 | Electrical rough in in slab | 0 | 0 | 11.2 | 11.2 | 4 | 500 | 2024-06-12T08:00:00 | 2024-06-18T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-06-12T08:00:00 | 2024-06-18T17:00:00 | 2024-06-12T08:00:00 | 2024-06-18T17:00:00 | 27840000 | 28320000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-12T08:00:00 | 2024-06-18T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-06-18T17:00:00 | 100 | 2024-06-12T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
62 | 63 | 63 | Deliver pakade slab rebar | 0 | 0 | 11.3 | 11.3 | 4 | 500 | 2024-06-19T08:00:00 | 2024-06-19T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-06-19T08:00:00 | 2024-06-19T17:00:00 | 2024-06-19T08:00:00 | 2024-06-19T17:00:00 | 30240000 | 30720000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-19T08:00:00 | 2024-06-19T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-06-19T17:00:00 | 100 | 2024-06-19T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
63 | 64 | 64 | Back fill and level parkade | 0 | 0 | 11.4 | 11.4 | 4 | 500 | 2024-06-20T08:00:00 | 2024-06-26T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-06-20T08:00:00 | 2024-06-26T17:00:00 | 2024-06-20T08:00:00 | 2024-06-26T17:00:00 | 28320000 | 28800000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-20T08:00:00 | 2024-06-26T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-06-26T17:00:00 | 100 | 2024-06-20T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
64 | 65 | 65 | Pour parakde slab | 0 | 0 | 12 | 12 | 3 | 500 | 2024-06-27T08:00:00 | 2024-07-10T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-06-27T08:00:00 | 2024-07-10T17:00:00 | 2024-06-27T08:00:00 | 2024-07-10T17:00:00 | 28320000 | 28800000 | 3 | PT72H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-27T08:00:00 | 2024-07-10T17:00:00 | PT72H0M0S
65 | 66 | 66 | Assign parkade slab rough in checklist | 0 | 0 | 12.1 | 12.1 | 4 | 500 | 2024-06-27T08:00:00 | 2024-06-27T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-06-27T08:00:00 | 2024-06-27T17:00:00 | 2024-06-27T08:00:00 | 2024-06-27T17:00:00 | 28320000 | 28800000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-27T08:00:00 | 2024-06-27T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-06-27T17:00:00 | 100 | 2024-06-27T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
66 | 67 | 67 | Radon rock install | 0 | 0 | 12.2 | 12.2 | 4 | 500 | 2024-06-28T08:00:00 | 2024-07-01T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-06-28T08:00:00 | 2024-07-01T17:00:00 | 2024-06-28T08:00:00 | 2024-07-01T17:00:00 | 28320000 | 28800000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-28T08:00:00 | 2024-07-01T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-07-01T17:00:00 | 100 | 2024-06-28T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100 |  | -480000.0
67 | 68 | 68 | Install poly | 0 | 0 | 12.3 | 12.3 | 4 | 500 | 2024-07-02T08:00:00 | 2024-07-02T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-02T08:00:00 | 2024-07-02T17:00:00 | 2024-07-02T08:00:00 | 2024-07-02T17:00:00 | 28320000 | 28800000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-02T08:00:00 | 2024-07-02T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-07-02T17:00:00 | 100 | 2024-07-02T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
68 | 69 | 69 | Tie parkade rebar | 0 | 0 | 12.4 | 12.4 | 4 | 500 | 2024-07-03T08:00:00 | 2024-07-05T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-03T08:00:00 | 2024-07-05T17:00:00 | 2024-07-03T08:00:00 | 2024-07-05T17:00:00 | 28320000 | 28800000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-03T08:00:00 | 2024-07-05T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-07-05T17:00:00 | 100 | 2024-07-03T08:00:00 | PT24H0M0S | PT24H0M0S |  | 100
69 | 70 | 70 | Assign pre concrete pour checklist | 0 | 0 | 12.5 | 12.5 | 4 | 500 | 2024-07-08T08:00:00 | 2024-07-08T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-08T08:00:00 | 2024-07-08T17:00:00 | 2024-07-08T08:00:00 | 2024-07-08T17:00:00 | 28320000 | 28800000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-08T08:00:00 | 2024-07-08T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-07-08T17:00:00 | 100 | 2024-07-08T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
70 | 71 | 71 | Pour parkade floor | 0 | 0 | 12.6 | 12.6 | 4 | 500 | 2024-07-09T08:00:00 | 2024-07-10T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-09T08:00:00 | 2024-07-10T17:00:00 | 2024-07-09T08:00:00 | 2024-07-10T17:00:00 | 28320000 | 28800000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-09T08:00:00 | 2024-07-10T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-07-10T17:00:00 | 100 | 2024-07-09T08:00:00 | PT16H0M0S | PT16H0M0S |  | 100
71 | 72 | 72 | Framing parkade | 0 | 0 | 13 | 13 | 3 | 500 | 2024-04-11T08:00:00 | 2024-04-16T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-04-11T08:00:00 | 2024-04-16T17:00:00 | 2024-04-11T08:00:00 | 2024-04-16T17:00:00 | 6720000 | 6240000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-04-11T08:00:00 | 2024-04-16T17:00:00 | PT32H0M0S
72 | 73 | 73 | Frame parkade level | 0 | 0 | 13.1 | 13.1 | 4 | 500 | 2024-04-11T08:00:00 | 2024-04-15T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-11T08:00:00 | 2024-04-15T17:00:00 | 2024-04-11T08:00:00 | 2024-04-15T17:00:00 | 6720000 | 6240000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-04-11T08:00:00 | 2024-04-15T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-04-15T17:00:00 | 100 | 2024-04-11T08:00:00 | PT24H0M0S | PT24H0M0S | ---- Field Notes ---- Framed walls were delivered on April 9 with installation beginning on April 10th. Josh altered the 4th floor from 7 to 8 units and the Framed walls were already pre-built leaving framer to build additional walls on site. - 10/04/2024 20:14:41 by David Neufeld | 100 |  | -960000.0
73 | 74 | 74 | Assign framing checklist | 0 | 0 | 13.2 | 13.2 | 4 | 500 | 2024-04-16T08:00:00 | 2024-04-16T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-16T08:00:00 | 2024-04-16T17:00:00 | 2024-04-16T08:00:00 | 2024-04-16T17:00:00 | 5760000 | 6240000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-04-16T08:00:00 | 2024-04-16T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-04-16T17:00:00 | 100 | 2024-04-16T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
74 | 75 | 75 | Hollowcore 2nd floor | 0 | 0 | 14 | 14 | 3 | 500 | 2024-04-16T08:00:00 | 2024-06-17T17:00:00 | PT360H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-04-16T08:00:00 | 2024-06-17T17:00:00 | 2024-04-16T08:00:00 | 2024-06-17T17:00:00 | 5760000 | 25920000 | 3 | PT360H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-04-16T08:00:00 | 2024-06-17T17:00:00 | PT360H0M0S
75 | 76 | 76 | Install hollowcore 2nd floor , Install backer rod & Grout 2nd floor | 0 | 0 | 14.1 | 14.1 | 4 | 500 | 2024-04-16T08:00:00 | 2024-04-18T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-16T08:00:00 | 2024-04-18T17:00:00 | 2024-04-16T08:00:00 | 2024-04-18T17:00:00 | 5760000 | 6240000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-04-16T08:00:00 | 2024-04-18T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-04-18T17:00:00 | 100 | 2024-04-16T08:00:00 | PT24H0M0S | PT24H0M0S |  | 100
76 | 77 | 77 | Assign hollow core erection checklist | 0 | 0 | 14.2 | 14.2 | 4 | 500 | 2024-04-19T08:00:00 | 2024-04-19T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-19T08:00:00 | 2024-04-19T17:00:00 | 2024-04-19T08:00:00 | 2024-04-19T17:00:00 | 7200000 | 7680000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-04-19T08:00:00 | 2024-04-19T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-04-19T17:00:00 | 100 | 2024-04-19T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
77 | 78 | 78 | Paint underside of ceiling in parkade | 0 | 0 | 14.3 | 14.3 | 4 | 500 | 2024-06-17T08:00:00 | 2024-06-17T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-06-17T08:00:00 | 2024-06-17T17:00:00 | 2024-06-17T08:00:00 | 2024-06-17T17:00:00 | 25440000 | 25920000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-17T08:00:00 | 2024-06-17T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-06-17T17:00:00 | 100 | 2024-06-17T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
78 | 79 | 79 | Framing 2nd floor | 0 | 0 | 15 | 15 | 3 | 500 | 2024-04-19T08:00:00 | 2024-05-14T17:00:00 | PT144H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-04-19T08:00:00 | 2024-05-14T17:00:00 | 2024-04-19T08:00:00 | 2024-05-14T17:00:00 | 5760000 | 11520000 | 3 | PT144H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-04-19T08:00:00 | 2024-05-14T17:00:00 | PT144H0M0S
79 | 80 | 80 | Frame 2nd floor | 0 | 0 | 15.1 | 15.1 | 4 | 500 | 2024-04-19T08:00:00 | 2024-05-13T17:00:00 | PT136H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-19T08:00:00 | 2024-05-13T17:00:00 | 2024-04-19T08:00:00 | 2024-05-13T17:00:00 | 5760000 | 11040000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-04-19T08:00:00 | 2024-05-13T17:00:00 | PT136H0M0S | PT136H0M0S | 2024-05-13T17:00:00 | 100 | 2024-04-19T08:00:00 | PT136H0M0S | PT136H0M0S |  | 100 |  | 4800000.0
80 | 81 | 81 | Assign framing check list | 0 | 0 | 15.2 | 15.2 | 4 | 500 | 2024-05-14T08:00:00 | 2024-05-14T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-14T08:00:00 | 2024-05-14T17:00:00 | 2024-05-14T08:00:00 | 2024-05-14T17:00:00 | 13920000 | 14400000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-05-14T08:00:00 | 2024-05-14T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-05-14T17:00:00 | 100 | 2024-05-14T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
81 | 82 | 82 | Hollowcore 3rd floor | 0 | 0 | 16 | 16 | 3 | 500 | 2024-05-23T08:00:00 | 2024-05-28T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-05-23T08:00:00 | 2024-05-28T17:00:00 | 2024-05-23T08:00:00 | 2024-05-28T17:00:00 | 13920000 | 14880000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-05-23T08:00:00 | 2024-05-28T17:00:00 | PT32H0M0S
82 | 83 | 83 | Install hollow core 3rd floor, Install backer rod & grout | 0 | 0 | 16.1 | 16.1 | 4 | 500 | 2024-05-23T08:00:00 | 2024-05-28T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-23T08:00:00 | 2024-05-28T17:00:00 | 2024-05-23T08:00:00 | 2024-05-28T17:00:00 | 13920000 | 14880000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-05-23T08:00:00 | 2024-05-28T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-05-28T17:00:00 | 100 | 2024-05-23T08:00:00 | PT32H0M0S | PT32H0M0S |  | 100 |  | 480000.0
83 | 84 | 84 | Assign hollow core erection checklist | 0 | 0 | 16.2 | 16.2 | 4 | 500 | 2024-05-27T08:00:00 | 2024-05-27T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-27T08:00:00 | 2024-05-27T17:00:00 | 2024-05-27T08:00:00 | 2024-05-27T17:00:00 | 14880000 | 15360000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-05-27T08:00:00 | 2024-05-27T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-05-27T17:00:00 | 100 | 2024-05-27T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
84 | 85 | 85 | Framing 3rd floor | 0 | 0 | 17 | 17 | 3 | 500 | 2024-05-28T08:00:00 | 2024-07-26T17:00:00 | PT344H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-05-28T08:00:00 | 2024-07-26T17:00:00 | 2024-05-28T08:00:00 | 2024-07-26T17:00:00 | 13920000 | 15360000 | 3 | PT344H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-05-28T08:00:00 | 2024-07-26T17:00:00 | PT344H0M0S
85 | 86 | 86 | Frame 3rd floor | 0 | 0 | 17.1 | 17.1 | 4 | 500 | 2024-05-28T08:00:00 | 2024-06-07T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-28T08:00:00 | 2024-06-07T17:00:00 | 2024-05-28T08:00:00 | 2024-06-07T17:00:00 | 13920000 | 15360000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-05-28T08:00:00 | 2024-06-07T17:00:00 | PT72H0M0S | PT72H0M0S | 2024-06-07T17:00:00 | 100 | 2024-05-28T08:00:00 | PT72H0M0S | PT72H0M0S |  | 100 |  | 960000.0
86 | 87 | 87 | Assign framing checklist | 0 | 0 | 17.2 | 17.2 | 4 | 500 | 2024-06-10T08:00:00 | 2024-06-10T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-06-10T08:00:00 | 2024-06-10T17:00:00 | 2024-06-10T08:00:00 | 2024-06-10T17:00:00 | 14880000 | 15360000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-10T08:00:00 | 2024-06-10T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-06-10T17:00:00 | 100 | 2024-06-10T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
87 | 88 | 88 | Layout suites on 2nd floor | 0 | 0 | 17.3 | 17.3 | 4 | 500 | 2024-07-18T08:00:00 | 2024-07-22T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-18T08:00:00 | 2024-07-22T17:00:00 | 2024-07-18T08:00:00 | 2024-07-22T17:00:00 | 31680000 | 31200000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-18T08:00:00 | 2024-07-22T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-07-22T17:00:00 | 100 | 2024-07-18T08:00:00 | PT24H0M0S | PT24H0M0S |  | 100 |  | -960000.0
88 | 89 | 89 | Core floors begin at 2nd | 0 | 0 | 17.4 | 17.4 | 4 | 500 | 2024-07-24T08:00:00 | 2024-07-26T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-24T08:00:00 | 2024-07-26T17:00:00 | 2024-07-24T08:00:00 | 2024-07-26T17:00:00 | 18240000 | 15360000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-24T08:00:00 | 2024-07-26T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-07-26T17:00:00 | 100 | 2024-07-24T08:00:00 | PT24H0M0S | PT24H0M0S |  | 100 |  | -3360000.0
89 | 90 | 90 | Hollowcore 4th floor | 0 | 0 | 18 | 18 | 3 | 500 | 2024-06-11T08:00:00 | 2024-06-13T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-06-11T08:00:00 | 2024-06-13T17:00:00 | 2024-06-11T08:00:00 | 2024-06-13T17:00:00 | 15360000 | 15840000 | 3 | PT24H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-11T08:00:00 | 2024-06-13T17:00:00 | PT24H0M0S
90 | 91 | 91 | Install hollow core 4th floor and grout | 0 | 0 | 18.1 | 18.1 | 4 | 500 | 2024-06-11T08:00:00 | 2024-06-12T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-06-11T08:00:00 | 2024-06-12T17:00:00 | 2024-06-11T08:00:00 | 2024-06-12T17:00:00 | 15360000 | 15360000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-11T08:00:00 | 2024-06-12T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-06-12T17:00:00 | 100 | 2024-06-11T08:00:00 | PT16H0M0S | PT16H0M0S |  | 100 |  | -480000.0
91 | 92 | 92 | Assign hollow core checklist | 0 | 0 | 18.2 | 18.2 | 4 | 500 | 2024-06-13T08:00:00 | 2024-06-13T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-06-13T08:00:00 | 2024-06-13T17:00:00 | 2024-06-13T08:00:00 | 2024-06-13T17:00:00 | 16320000 | 16800000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-13T08:00:00 | 2024-06-13T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-06-13T17:00:00 | 100 | 2024-06-13T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
92 | 93 | 93 | Framing 4th floor | 0 | 0 | 19 | 19 | 3 | 500 | 2024-06-19T08:00:00 | 2024-07-31T17:00:00 | PT240H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-06-19T08:00:00 | 2024-07-31T17:00:00 | 2024-06-19T08:00:00 | 2024-07-31T17:00:00 | 16800000 | 28320000 | 3 | PT240H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-19T08:00:00 | 2024-07-31T17:00:00 | PT240H0M0S
93 | 94 | 94 | Frame 4th floor | 0 | 0 | 19.1 | 19.1 | 4 | 500 | 2024-06-19T08:00:00 | 2024-07-05T17:00:00 | PT96H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-06-19T08:00:00 | 2024-07-05T17:00:00 | 2024-06-19T08:00:00 | 2024-07-05T17:00:00 | 16800000 | 20160000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-06-19T08:00:00 | 2024-07-05T17:00:00 | PT96H0M0S | PT96H0M0S | 2024-07-05T17:00:00 | 100 | 2024-06-19T08:00:00 | PT96H0M0S | PT96H0M0S |  | 100 |  | 2400000.0
94 | 95 | 95 | Assign framing checklist | 0 | 0 | 19.2 | 19.2 | 4 | 500 | 2024-07-08T08:00:00 | 2024-07-08T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-08T08:00:00 | 2024-07-08T17:00:00 | 2024-07-08T08:00:00 | 2024-07-08T17:00:00 | 19680000 | 20160000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-08T08:00:00 | 2024-07-08T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-07-08T17:00:00 | 100 | 2024-07-08T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
95 | 96 | 96 | Layout suites on 3rd floor | 0 | 0 | 19.3 | 19.3 | 4 | 500 | 2024-07-23T08:00:00 | 2024-07-26T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-23T08:00:00 | 2024-07-26T17:00:00 | 2024-07-23T08:00:00 | 2024-07-26T17:00:00 | 28320000 | 28320000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-23T08:00:00 | 2024-07-26T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-07-26T17:00:00 | 100 | 2024-07-23T08:00:00 | PT32H0M0S | PT32H0M0S |  | 100 |  | -480000.0
96 | 97 | 97 | Core floor beings at 3rd floor | 0 | 0 | 19.4 | 19.4 | 4 | 500 | 2024-07-29T08:00:00 | 2024-07-31T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-29T08:00:00 | 2024-07-31T17:00:00 | 2024-07-29T08:00:00 | 2024-07-31T17:00:00 |  |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-29T08:00:00 | 2024-07-31T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-07-31T17:00:00 | 100 | 2024-07-29T08:00:00 | PT24H0M0S | PT24H0M0S |  | 100
97 | 98 | 98 | Roof trusses install | 0 | 0 | 20 | 20 | 3 | 500 | 2024-07-09T08:00:00 | 2024-08-20T17:00:00 | PT248H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-07-09T08:00:00 | 2024-08-20T17:00:00 | 2024-07-09T08:00:00 | 2024-08-20T17:00:00 | 20160000 | 28320000 | 3 | PT248H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-09T08:00:00 | 2024-08-20T17:00:00 | PT248H0M0S
98 | 99 | 99 | Install roof trusses and sheeting and towers | 0 | 0 | 20.1 | 20.1 | 4 | 500 | 2024-07-09T08:00:00 | 2024-08-06T17:00:00 | PT168H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-09T08:00:00 | 2024-08-06T17:00:00 | 2024-07-09T08:00:00 | 2024-08-06T17:00:00 | 20160000 | 25920000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-09T08:00:00 | 2024-08-06T17:00:00 | PT168H0M0S | PT168H0M0S | 2024-08-06T17:00:00 | 100 | 2024-07-09T08:00:00 | PT168H0M0S | PT168H0M0S |  | 100 |  | 5280000.0
99 | 100 | 100 | Assign roof trusses framing checklist | 0 | 0 | 20.2 | 20.2 | 4 | 500 | 2024-08-07T08:00:00 | 2024-08-07T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-07T08:00:00 | 2024-08-07T17:00:00 | 2024-08-07T08:00:00 | 2024-08-07T17:00:00 | 25440000 | 25920000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-07T08:00:00 | 2024-08-07T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-08-07T17:00:00 | 100 | 2024-08-07T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
100 | 101 | 101 | Call for structural inspection | 0 | 0 | 20.3 | 20.3 | 4 | 500 | 2024-08-20T08:00:00 | 2024-08-20T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-20T08:00:00 | 2024-08-20T17:00:00 | 2024-08-20T08:00:00 | 2024-08-20T17:00:00 | 29760000 | 30240000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-20T08:00:00 | 2024-08-20T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-08-20T17:00:00 | 100 | 2024-08-20T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
101 | 102 | 102 | Layout suites 4th floor | 0 | 0 | 20.4 | 20.4 | 4 | 500 | 2024-07-29T08:00:00 | 2024-08-01T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-29T08:00:00 | 2024-08-01T17:00:00 | 2024-07-29T08:00:00 | 2024-08-01T17:00:00 | 22080000 | 22080000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-29T08:00:00 | 2024-08-01T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-08-01T17:00:00 | 100 | 2024-07-29T08:00:00 | PT32H0M0S | PT32H0M0S |  | 100 |  | -480000.0
102 | 103 | 103 | Core floor beings at 4th floor | 0 | 0 | 20.5 | 20.5 | 4 | 500 | 2024-08-01T08:00:00 | 2024-08-02T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-01T08:00:00 | 2024-08-02T17:00:00 | 2024-08-01T08:00:00 | 2024-08-02T17:00:00 |  |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-01T08:00:00 | 2024-08-02T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-08-02T17:00:00 | 100 | 2024-08-01T08:00:00 | PT16H0M0S | PT16H0M0S |  | 100
103 | 104 | 104 | install windows and doors | 0 | 0 | 21 | 21 | 3 | 500 | 2024-07-08T08:00:00 | 2024-11-26T17:00:00 | PT808H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-07-08T08:00:00 | 2024-11-26T17:00:00 | 2024-07-08T08:00:00 | 2024-11-26T17:00:00 | 7680000 | 48960000 | 3 | PT808H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-08T08:00:00 | 2024-11-26T17:00:00 | PT808H0M0S
104 | 105 | 105 | Deliver tubs & showers to suites / checklist | 0 | 0 | 21.1 | 21.1 | 4 | 500 | 2024-07-17T08:00:00 | 2024-07-18T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-17T08:00:00 | 2024-07-18T17:00:00 | 2024-07-17T08:00:00 | 2024-07-18T17:00:00 | 11040000 | 11520000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-17T08:00:00 | 2024-07-18T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-07-18T17:00:00 | 100 | 2024-07-17T08:00:00 | PT16H0M0S | PT16H0M0S |  | 100
105 | 106 | 106 | Assign window & door installation checklist | 0 | 0 | 21.2 | 21.2 | 4 | 500 | 2024-07-08T08:00:00 | 2024-07-08T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-08T08:00:00 | 2024-07-08T17:00:00 | 2024-07-08T08:00:00 | 2024-07-08T17:00:00 |  | 480000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-08T08:00:00 | 2024-07-08T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-07-08T17:00:00 | 100 | 2024-07-08T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
106 | 107 | 107 | Install windows & doors all floors | 0 | 0 | 21.3 | 21.3 | 4 | 500 | 2024-08-01T08:00:00 | 2024-08-13T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-01T08:00:00 | 2024-08-13T17:00:00 | 2024-08-01T08:00:00 | 2024-08-13T17:00:00 | 15360000 | 13440000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-01T08:00:00 | 2024-08-13T17:00:00 | PT72H0M0S | PT72H0M0S | 2024-08-13T17:00:00 | 100 | 2024-08-01T08:00:00 | PT72H0M0S | PT72H0M0S |  | 100 |  | -1920000.0
107 | 108 | 108 | Install stairs | 0 | 0 | 21.4 | 21.4 | 4 | 500 | 2024-07-30T08:00:00 | 2024-07-30T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-30T08:00:00 | 2024-07-30T17:00:00 | 2024-07-30T08:00:00 | 2024-07-30T17:00:00 | 7680000 | 8160000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-07-30T08:00:00 | 2024-07-30T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-07-30T17:00:00 | 100 | 2024-07-30T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
108 | 109 | 109 | Call for envelope reviewer inspection | 0 | 0 | 21.5 | 21.5 | 4 | 500 | 2024-11-26T08:00:00 | 2024-11-26T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-26T08:00:00 | 2024-11-26T17:00:00 | 2024-11-26T08:00:00 | 2024-11-26T17:00:00 | 48480000 | 48960000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-26T08:00:00 | 2024-11-26T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-26T17:00:00 | 0 | 2024-11-26T08:00:00 |  |  |  | 0
109 | 110 | 110 | Roofing and water proofing | 0 | 0 | 22 | 22 | 3 | 500 | 2024-08-07T08:00:00 | 2024-08-23T17:00:00 | PT104H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-08-07T08:00:00 | 2024-08-23T17:00:00 | 2024-08-07T08:00:00 | 2024-08-23T17:00:00 | 25440000 | 24960000 | 3 | PT104H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-07T08:00:00 | 2024-08-23T17:00:00 | PT104H0M0S
110 | 111 | 111 | Assign roofing and water proofing checklist | 0 | 0 | 22.1 | 22.1 | 4 | 500 | 2024-08-07T08:00:00 | 2024-08-07T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-07T08:00:00 | 2024-08-07T17:00:00 | 2024-08-07T08:00:00 | 2024-08-07T17:00:00 | 18720000 | 19200000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-07T08:00:00 | 2024-08-07T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-08-07T17:00:00 | 100 | 2024-08-07T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
111 | 112 | 112 | Install roofing and water proofing | 0 | 0 | 22.2 | 22.2 | 4 | 500 | 2024-08-12T08:00:00 | 2024-08-23T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-12T08:00:00 | 2024-08-23T17:00:00 | 2024-08-12T08:00:00 | 2024-08-23T17:00:00 | 26880000 | 25440000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-12T08:00:00 | 2024-08-23T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-08-23T17:00:00 | 100 | 2024-08-12T08:00:00 | PT80H0M0S | PT80H0M0S |  | 100 |  | -1920000.0
112 | 113 | 113 | Soffit & Tower Siding | 0 | 0 | 23 | 23 | 3 | 500 | 2024-09-03T08:00:00 | 2025-01-03T17:00:00 | PT672H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-09-03T08:00:00 | 2025-01-03T17:00:00 | 2024-09-03T08:00:00 | 2025-01-03T17:00:00 | 27840000 | 63840000 | 3 | PT672H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-03T08:00:00 | 2025-01-03T17:00:00 | PT672H0M0S
113 | 114 | 114 | Building paper the whole building | 0 | 0 | 23.1 | 23.1 | 4 | 500 | 2024-09-03T08:00:00 | 2024-11-25T17:00:00 | PT472H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-09-03T08:00:00 | 2024-11-25T17:00:00 | 2024-09-03T08:00:00 | 2024-11-25T17:00:00 | 27840000 | 54720000 | 3 | PT118H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-03T08:00:00 | 2024-11-25T17:00:00 | PT472H0M0S | PT472H0M0S | 2024-11-25T17:00:00 | 75 | 2024-09-03T08:00:00 | PT354H0M0S | PT354H0M0S |  | 75 |  | 25920000
114 | 115 | 115 | Install fascia and soffit 4th floor | 0 | 0 | 23.2 | 23.2 | 4 | 500 | 2024-11-15T08:00:00 | 2024-11-25T17:00:00 | PT56H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-15T08:00:00 | 2024-11-25T17:00:00 | 2024-11-15T08:00:00 | 2024-11-25T17:00:00 | 53280000 | 55680000 | 3 | PT5H36M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-15T08:00:00 | 2024-11-25T17:00:00 | PT56H0M0S | PT56H0M0S | 2024-11-25T17:00:00 | 90 | 2024-11-15T08:00:00 | PT50H24M0S | PT50H24M0S |  | 90 |  | 1920000.0
115 | 116 | 116 | Assign tower siding checklist | 0 | 0 | 23.3 | 23.3 | 4 | 500 | 2024-11-26T08:00:00 | 2024-11-26T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-26T08:00:00 | 2024-11-26T17:00:00 | 2024-11-26T08:00:00 | 2024-11-26T17:00:00 | 49920000 | 50400000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-26T08:00:00 | 2024-11-26T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-26T17:00:00 | 0 | 2024-11-26T08:00:00 |  |  |  | 0
116 | 117 | 117 | Siding towers | 0 | 0 | 23.4 | 23.4 | 4 | 500 | 2024-11-27T08:00:00 | 2024-12-16T17:00:00 | PT112H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-27T08:00:00 | 2024-12-16T17:00:00 | 2024-11-27T08:00:00 | 2024-12-16T17:00:00 | 57120000 | 57600000 | 3 | PT112H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-27T08:00:00 | 2024-12-16T17:00:00 | PT112H0M0S | PT112H0M0S | 2024-12-16T17:00:00 | 0 | 2024-11-27T08:00:00 |  |  |  | 0 |  | 480000.0
117 | 118 | 118 | Delivery of Elevator & Install | 0 | 0 | 23.5 | 23.5 | 4 | 500 | 2024-10-14T08:00:00 | 2025-01-03T17:00:00 | PT440H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-10-14T08:00:00 | 2025-01-03T17:00:00 | 2024-10-14T08:00:00 | 2025-01-03T17:00:00 | 35520000 | 64320000 | 3 | PT330H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-14T08:00:00 | 2025-01-03T17:00:00 | PT440H0M0S | PT440H0M0S | 2025-01-03T17:00:00 | 25 | 2024-10-14T08:00:00 | PT110H0M0S | PT110H0M0S |  | 25 |  | 26400000
118 | 119 | 119 | Exterior concrete works | 0 | 0 | 24 | 24 | 3 | 500 | 2024-08-26T08:00:00 | 2024-12-19T17:00:00 | PT664H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-08-26T08:00:00 | 2024-12-19T17:00:00 | 2024-08-26T08:00:00 | 2024-12-19T17:00:00 | 24960000 | 53760000 | 3 | PT664H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-26T08:00:00 | 2024-12-19T17:00:00 | PT664H0M0S
119 | 120 | 120 | Excavate areas | 0 | 0 | 24.1 | 24.1 | 4 | 500 | 2024-08-26T08:00:00 | 2024-08-27T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-26T08:00:00 | 2024-08-27T17:00:00 | 2024-08-26T08:00:00 | 2024-08-27T17:00:00 | 24960000 | 25440000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-26T08:00:00 | 2024-08-27T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-08-27T17:00:00 | 100 | 2024-08-26T08:00:00 | PT16H0M0S | PT16H0M0S |  | 100
120 | 121 | 121 | Form exterior pads | 0 | 0 | 24.2 | 24.2 | 4 | 500 | 2024-08-28T08:00:00 | 2024-09-03T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-28T08:00:00 | 2024-09-03T17:00:00 | 2024-08-28T08:00:00 | 2024-09-03T17:00:00 | 24960000 | 25440000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-28T08:00:00 | 2024-09-03T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-09-03T17:00:00 | 100 | 2024-08-28T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
121 | 122 | 122 | Tie rebar exterior pads | 0 | 0 | 24.3 | 24.3 | 4 | 500 | 2024-09-04T08:00:00 | 2024-09-06T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-04T08:00:00 | 2024-09-06T17:00:00 | 2024-09-04T08:00:00 | 2024-09-06T17:00:00 | 24960000 | 25440000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-04T08:00:00 | 2024-09-06T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-09-06T17:00:00 | 100 | 2024-09-04T08:00:00 | PT24H0M0S | PT24H0M0S |  | 100
122 | 123 | 123 | Assign conrete pour checklist | 0 | 0 | 24.4 | 24.4 | 4 | 500 | 2024-09-09T08:00:00 | 2024-09-09T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-09T08:00:00 | 2024-09-09T17:00:00 | 2024-09-09T08:00:00 | 2024-09-09T17:00:00 | 24960000 | 25440000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-09T08:00:00 | 2024-09-09T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-09-09T17:00:00 | 100 | 2024-09-09T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
123 | 124 | 124 | Pour exterior pads | 0 | 0 | 24.5 | 24.5 | 4 | 500 | 2024-09-10T08:00:00 | 2024-09-10T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-10T08:00:00 | 2024-09-10T17:00:00 | 2024-09-10T08:00:00 | 2024-09-10T17:00:00 | 24960000 | 25440000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-10T08:00:00 | 2024-09-10T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-09-10T17:00:00 | 100 | 2024-09-10T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
124 | 125 | 125 | Excatae exterior sidewalks | 0 | 0 | 24.6 | 24.6 | 4 | 500 | 2024-09-11T08:00:00 | 2024-12-03T17:00:00 | PT472H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-09-11T08:00:00 | 2024-12-03T17:00:00 | 2024-09-11T08:00:00 | 2024-12-03T17:00:00 | 24960000 | 51840000 | 3 | PT141H36M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-11T08:00:00 | 2024-12-03T17:00:00 | PT472H0M0S | PT472H0M0S | 2024-12-03T17:00:00 | 70 | 2024-09-11T08:00:00 | PT330H24M0S | PT330H24M0S |  | 70 |  | 26400000
125 | 126 | 126 | Form exterior sidewalks | 0 | 0 | 24.7 | 24.7 | 4 | 500 | 2024-12-04T08:00:00 | 2024-12-06T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-04T08:00:00 | 2024-12-06T17:00:00 | 2024-12-04T08:00:00 | 2024-12-06T17:00:00 | 51360000 | 51840000 | 3 | PT7H11M60S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-04T08:00:00 | 2024-12-06T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-12-06T17:00:00 | 70 | 2024-12-04T08:00:00 | PT16H47M60S | PT16H47M60S |  | 70
126 | 127 | 127 | Rebar exterior sidewalks | 0 | 0 | 24.8 | 24.8 | 4 | 500 | 2024-12-09T08:00:00 | 2024-12-11T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-09T08:00:00 | 2024-12-11T17:00:00 | 2024-12-09T08:00:00 | 2024-12-11T17:00:00 | 51360000 | 51840000 | 3 | PT7H11M60S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-09T08:00:00 | 2024-12-11T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-12-11T17:00:00 | 70 | 2024-12-09T08:00:00 | PT16H47M60S | PT16H47M60S |  | 70
127 | 128 | 128 | Assign pre concrete pour checklist | 0 | 0 | 24.9 | 24.9 | 4 | 500 | 2024-12-12T08:00:00 | 2024-12-16T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-12T08:00:00 | 2024-12-16T17:00:00 | 2024-12-12T08:00:00 | 2024-12-16T17:00:00 | 51360000 | 52800000 | 3 | PT7H11M60S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-12T08:00:00 | 2024-12-16T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-12-16T17:00:00 | 70 | 2024-12-12T08:00:00 | PT16H47M60S | PT16H47M60S |  | 70 |  | 960000.0
128 | 129 | 129 | Pour exterior sidewalks | 0 | 0 | 24.10 | 24.10 | 4 | 500 | 2024-12-17T08:00:00 | 2024-12-19T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-17T08:00:00 | 2024-12-19T17:00:00 | 2024-12-17T08:00:00 | 2024-12-19T17:00:00 | 52320000 | 53760000 | 3 | PT7H11M60S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-17T08:00:00 | 2024-12-19T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-12-19T17:00:00 | 70 | 2024-12-17T08:00:00 | PT16H47M60S | PT16H47M60S |  | 70 |  | 960000.0
129 | 130 | 130 | 4.3 Rough In, Steel Stud Drywall | 0 | 0 | 25 | 25 | 2 | 500 | 2024-08-05T08:00:00 | 2025-01-23T17:00:00 | PT952H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-08-05T08:00:00 | 2025-01-23T17:00:00 | 2024-08-05T08:00:00 | 2025-01-23T17:00:00 | 43680000 | -18720000 | 3 | PT952H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-05T08:00:00 | 2025-01-23T17:00:00 | PT952H0M0S
130 | 131 | 131 | Rough in Parkade | 0 | 0 | 26 | 26 | 3 | 500 | 2024-08-19T08:00:00 | 2025-01-23T17:00:00 | PT872H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-08-19T08:00:00 | 2025-01-23T17:00:00 | 2024-08-19T08:00:00 | 2025-01-23T17:00:00 | 48480000 | 81120000 | 3 | PT872H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-19T08:00:00 | 2025-01-23T17:00:00 | PT872H0M0S
131 | 132 | 132 | Frame interior parkade walls | 0 | 0 | 26.1 | 26.1 | 4 | 500 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | 40320000 | 40800000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-08-23T17:00:00 | 100 | 2024-08-19T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
132 | 133 | 133 | Rough in interior walls | 0 | 0 | 26.2 | 26.2 | 4 | 500 | 2024-11-21T08:00:00 | 2024-12-04T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-21T08:00:00 | 2024-12-04T17:00:00 | 2024-11-21T08:00:00 | 2024-12-04T17:00:00 | 70560000 | 73440000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-21T08:00:00 | 2024-12-04T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-12-04T17:00:00 | 50 | 2024-11-21T08:00:00 | PT40H0M0S | PT40H0M0S |  | 50 |  | 2400000.0
133 | 134 | 134 | Rough in exterior walls - parkade and sheds | 0 | 0 | 26.3 | 26.3 | 4 | 500 | 2024-11-18T08:00:00 | 2024-12-06T17:00:00 | PT120H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-18T08:00:00 | 2024-12-06T17:00:00 | 2024-11-18T08:00:00 | 2024-12-06T17:00:00 | 79680000 | 84960000 | 3 | PT60H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-18T08:00:00 | 2024-12-06T17:00:00 | PT120H0M0S | PT120H0M0S | 2024-12-06T17:00:00 | 50 | 2024-11-18T08:00:00 | PT60H0M0S | PT60H0M0S |  | 50 |  | 4800000.0
134 | 135 | 135 | Board and prepare electrical/mechanical room | 0 | 0 | 26.4 | 26.4 | 4 | 500 | 2024-12-06T08:00:00 | 2024-12-10T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-06T08:00:00 | 2024-12-10T17:00:00 | 2024-12-06T08:00:00 | 2024-12-10T17:00:00 | 73440000 | 73920000 | 3 | PT24H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-06T08:00:00 | 2024-12-10T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-12-10T17:00:00 | 0 | 2024-12-06T08:00:00 |  |  |  | 0
135 | 136 | 136 | Main service electrical room install | 0 | 0 | 26.5 | 26.5 | 4 | 500 | 2024-11-28T08:00:00 | 2024-12-26T17:00:00 | PT144H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-28T08:00:00 | 2024-12-26T17:00:00 | 2024-11-28T08:00:00 | 2024-12-26T17:00:00 | 69120000 | 72480000 | 3 | PT144H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-28T08:00:00 | 2024-12-26T17:00:00 | PT144H0M0S | PT144H0M0S | 2024-12-26T17:00:00 | 0 | 2024-11-28T08:00:00 |  |  |  | 0 |  | 1440000.0
136 | 137 | 137 | Main service mechanical room install | 0 | 0 | 26.6 | 26.6 | 4 | 500 | 2024-11-28T08:00:00 | 2025-01-22T17:00:00 | PT288H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-28T08:00:00 | 2025-01-22T17:00:00 | 2024-11-28T08:00:00 | 2025-01-22T17:00:00 | 69120000 | 81600000 | 3 | PT288H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-28T08:00:00 | 2025-01-22T17:00:00 | PT288H0M0S | PT288H0M0S | 2025-01-22T17:00:00 | 0 | 2024-11-28T08:00:00 |  |  |  | 0 |  | 10080000
137 | 138 | 138 | Call for Electrical and Mechanical Inspection | 0 | 0 | 26.7 | 26.7 | 4 | 500 | 2025-01-23T08:00:00 | 2025-01-23T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-23T08:00:00 | 2025-01-23T17:00:00 | 2025-01-23T08:00:00 | 2025-01-23T17:00:00 |  |  | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-23T08:00:00 | 2025-01-23T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-01-23T17:00:00 | 0 | 2025-01-23T08:00:00 |  |  |  | 0
138 | 139 | 139 | Siding parkade level | 0 | 0 | 26.8 | 26.8 | 4 | 500 | 2024-12-10T08:00:00 | 2024-12-23T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-10T08:00:00 | 2024-12-23T17:00:00 | 2024-12-10T08:00:00 | 2024-12-23T17:00:00 | 84480000 | 84960000 | 3 | PT80H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-10T08:00:00 | 2024-12-23T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-12-23T17:00:00 | 0 | 2024-12-10T08:00:00 |  |  |  | 0
139 | 140 | 140 | Assign siding checklist | 0 | 0 | 26.9 | 26.9 | 4 | 500 | 2024-12-24T08:00:00 | 2024-12-24T17:00:00 | PT0H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-24T08:00:00 | 2024-12-24T17:00:00 | 2024-12-24T08:00:00 | 2024-12-24T17:00:00 | 84480000 | 84960000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-24T08:00:00 | 2024-12-24T17:00:00 |  |  | 2024-12-24T17:00:00 | 0 | 2024-12-24T08:00:00 |  |  |  | 0 |  | -480000.0
140 | 141 | 141 | Poly and insulate parkade exterior walls | 0 | 0 | 26.10 | 26.10 | 4 | 500 | 2024-08-22T08:00:00 | 2024-08-23T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-22T08:00:00 | 2024-08-23T17:00:00 | 2024-08-22T08:00:00 | 2024-08-23T17:00:00 | 47520000 | 48000000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-22T08:00:00 | 2024-08-23T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-08-23T17:00:00 | 100 | 2024-08-22T08:00:00 | PT16H0M0S | PT16H0M0S |  | 100
141 | 142 | 142 | Assign pre board inspection checklist | 0 | 0 | 26.11 | 26.11 | 4 | 500 | 2025-01-22T08:00:00 | 2025-01-22T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-01-22T08:00:00 | 2025-01-22T17:00:00 | 2025-01-22T08:00:00 | 2025-01-22T17:00:00 | 99840000 | 100320000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-22T08:00:00 | 2025-01-22T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-01-22T17:00:00 | 100 | 2025-01-22T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
142 | 143 | 143 | Board parkade exterior walls and sheds | 0 | 0 | 26.12 | 26.12 | 4 | 500 | 2024-12-09T08:00:00 | 2024-12-09T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-09T08:00:00 | 2024-12-09T17:00:00 | 2024-12-09T08:00:00 | 2024-12-09T17:00:00 | 83520000 | 82080000 | 3 | PT1H35M60S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-09T08:00:00 | 2024-12-09T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-12-09T17:00:00 | 80 | 2024-12-09T08:00:00 | PT6H24M0S | PT6H24M0S |  | 80 |  | -1920000.0
143 | 144 | 144 | Assign pre board inspection checklist | 0 | 0 | 26.13 | 26.13 | 4 | 500 | 2025-01-22T08:00:00 | 2025-01-22T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-01-22T08:00:00 | 2025-01-22T17:00:00 | 2025-01-22T08:00:00 | 2025-01-22T17:00:00 | 87840000 | 88320000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-22T08:00:00 | 2025-01-22T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-01-22T17:00:00 | 100 | 2025-01-22T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
144 | 145 | 145 | Board Parkade interior walls | 0 | 0 | 26.14 | 26.14 | 4 | 500 | 2024-12-10T08:00:00 | 2024-12-13T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-10T08:00:00 | 2024-12-13T17:00:00 | 2024-12-10T08:00:00 | 2024-12-13T17:00:00 | 72480000 | 72480000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-10T08:00:00 | 2024-12-13T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-12-13T17:00:00 | 0 | 2024-12-10T08:00:00 |  |  |  | 0 |  | -480000.0
145 | 146 | 146 | Frame and board Parkade beams | 0 | 0 | 26.15 | 26.15 | 4 | 500 | 2024-12-16T08:00:00 | 2024-12-20T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-12-16T08:00:00 | 2024-12-20T17:00:00 | 2024-12-16T08:00:00 | 2024-12-20T17:00:00 | 83520000 | 84000000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-16T08:00:00 | 2024-12-20T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-12-20T17:00:00 | 100 | 2024-12-16T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
146 | 147 | 147 | Tape parkade interior and exterior walls | 0 | 0 | 26.16 | 26.16 | 4 | 500 | 2024-12-13T08:00:00 | 2024-12-23T17:00:00 | PT56H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-13T08:00:00 | 2024-12-23T17:00:00 | 2024-12-13T08:00:00 | 2024-12-23T17:00:00 | 71520000 | 72960000 | 3 | PT56H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-13T08:00:00 | 2024-12-23T17:00:00 | PT56H0M0S | PT56H0M0S | 2024-12-23T17:00:00 | 0 | 2024-12-13T08:00:00 |  |  |  | 0 |  | 960000.0
147 | 148 | 148 | Assign taping inspection checklist | 0 | 0 | 26.17 | 26.17 | 4 | 500 | 2024-12-23T08:00:00 | 2024-12-23T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-23T08:00:00 | 2024-12-23T17:00:00 | 2024-12-23T08:00:00 | 2024-12-23T17:00:00 | 72000000 | 72480000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-23T08:00:00 | 2024-12-23T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-12-23T17:00:00 | 0 | 2024-12-23T08:00:00 |  |  |  | 0
148 | 149 | 149 | Install metal doors and frames | 0 | 0 | 26.18 | 26.18 | 4 | 500 | 2024-12-24T08:00:00 | 2025-01-06T17:00:00 | PT48H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-24T08:00:00 | 2025-01-06T17:00:00 | 2024-12-24T08:00:00 | 2025-01-06T17:00:00 | 72000000 | 74880000 | 3 | PT48H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-24T08:00:00 | 2025-01-06T17:00:00 | PT48H0M0S | PT48H0M0S | 2025-01-06T17:00:00 | 0 | 2024-12-24T08:00:00 |  |  |  | 0 |  | 480000.0
149 | 150 | 150 | Rough in 4th floor ceiling | 0 | 0 | 27 | 27 | 3 | 500 | 2024-08-05T08:00:00 | 2024-10-07T17:00:00 | PT368H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-08-05T08:00:00 | 2024-10-07T17:00:00 | 2024-08-05T08:00:00 | 2024-10-07T17:00:00 | 17280000 | 24000000 | 3 | PT368H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-05T08:00:00 | 2024-10-07T17:00:00 | PT368H0M0S
150 | 151 | 151 | Electrical rough in in ceiling | 0 | 0 | 27.1 | 27.1 | 4 | 500 | 2024-08-26T08:00:00 | 2024-09-03T17:00:00 | PT56H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-26T08:00:00 | 2024-09-03T17:00:00 | 2024-08-26T08:00:00 | 2024-09-03T17:00:00 | 24480000 | 23520000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-26T08:00:00 | 2024-09-03T17:00:00 | PT56H0M0S | PT56H0M0S | 2024-09-03T17:00:00 | 100 | 2024-08-26T08:00:00 | PT56H0M0S | PT56H0M0S |  | 100 |  | -1440000.0
151 | 152 | 152 | Mechanical rough in in ceiling | 0 | 0 | 27.2 | 27.2 | 4 | 500 | 2024-08-05T08:00:00 | 2024-08-14T17:00:00 | PT64H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-05T08:00:00 | 2024-08-14T17:00:00 | 2024-08-05T08:00:00 | 2024-08-14T17:00:00 | 17280000 | 19200000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-05T08:00:00 | 2024-08-14T17:00:00 | PT64H0M0S | PT64H0M0S | 2024-08-14T17:00:00 | 100 | 2024-08-05T08:00:00 | PT64H0M0S | PT64H0M0S |  | 100 |  | 1440000.0
152 | 153 | 153 | Sprinkler install in attic | 0 | 0 | 27.3 | 27.3 | 4 | 500 | 2024-08-07T08:00:00 | 2024-08-21T17:00:00 | PT88H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-07T08:00:00 | 2024-08-21T17:00:00 | 2024-08-07T08:00:00 | 2024-08-21T17:00:00 | 18240000 | 19200000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-07T08:00:00 | 2024-08-21T17:00:00 | PT88H0M0S | PT88H0M0S | 2024-08-21T17:00:00 | 100 | 2024-08-07T08:00:00 | PT88H0M0S | PT88H0M0S |  | 100 |  | 480000.0
153 | 154 | 154 | Call for Mechanical & Electrical inspection of attic | 0 | 0 | 27.4 | 27.4 | 4 | 500 | 2024-09-04T08:00:00 | 2024-09-04T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-04T08:00:00 | 2024-09-04T17:00:00 | 2024-09-04T08:00:00 | 2024-09-04T17:00:00 |  |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-04T08:00:00 | 2024-09-04T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-09-04T17:00:00 | 100 | 2024-09-04T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
154 | 155 | 155 | Poly 4th floor ceiling | 0 | 0 | 27.5 | 27.5 | 4 | 500 | 2024-09-05T08:00:00 | 2024-09-06T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-05T08:00:00 | 2024-09-06T17:00:00 | 2024-09-05T08:00:00 | 2024-09-06T17:00:00 | 23520000 | 24000000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-05T08:00:00 | 2024-09-06T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-09-06T17:00:00 | 100 | 2024-09-05T08:00:00 | PT16H0M0S | PT16H0M0S |  | 100
155 | 156 | 156 | Install sound bar 4th floor | 0 | 0 | 27.6 | 27.6 | 4 | 500 | 2024-09-09T08:00:00 | 2024-09-10T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-09T08:00:00 | 2024-09-10T17:00:00 | 2024-09-09T08:00:00 | 2024-09-10T17:00:00 | 23520000 | 23520000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-09T08:00:00 | 2024-09-10T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-09-10T17:00:00 | 100 | 2024-09-09T08:00:00 | PT16H0M0S | PT16H0M0S |  | 100
156 | 157 | 157 | Install drywall on 4th floor ceiling | 0 | 0 | 27.7 | 27.7 | 4 | 500 | 2024-09-11T08:00:00 | 2024-09-17T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-11T08:00:00 | 2024-09-17T17:00:00 | 2024-09-11T08:00:00 | 2024-09-17T17:00:00 | 23040000 | 23520000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-11T08:00:00 | 2024-09-17T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-09-17T17:00:00 | 100 | 2024-09-11T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
157 | 158 | 158 | Blow in attic insulation | 0 | 0 | 27.8 | 27.8 | 4 | 500 | 2024-09-18T08:00:00 | 2024-09-20T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-18T08:00:00 | 2024-09-20T17:00:00 | 2024-09-18T08:00:00 | 2024-09-20T17:00:00 | 23040000 | 24000000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-18T08:00:00 | 2024-09-20T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-09-20T17:00:00 | 100 | 2024-09-18T08:00:00 | PT24H0M0S | PT24H0M0S |  | 100 |  | 480000.0
158 | 159 | 159 | Tape 4th floor ceiling | 0 | 0 | 27.9 | 27.9 | 4 | 500 | 2024-09-23T08:00:00 | 2024-10-04T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-09-23T08:00:00 | 2024-10-04T17:00:00 | 2024-09-23T08:00:00 | 2024-10-04T17:00:00 | 23520000 | 24000000 | 3 | PT80H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-23T08:00:00 | 2024-10-04T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-10-04T17:00:00 | 0 | 2024-09-23T08:00:00 |  |  |  | 0
159 | 160 | 160 | Assign taping inspection checklist | 0 | 0 | 27.10 | 27.10 | 4 | 500 | 2024-10-07T08:00:00 | 2024-10-07T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-10-07T08:00:00 | 2024-10-07T17:00:00 | 2024-10-07T08:00:00 | 2024-10-07T17:00:00 | 23520000 | 24000000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-07T08:00:00 | 2024-10-07T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-10-07T17:00:00 | 0 | 2024-10-07T08:00:00 |  |  |  | 0
160 | 161 | 161 | Rough in 2nd floor | 0 | 0 | 28 | 28 | 3 | 500 | 2024-08-12T08:00:00 | 2025-01-03T17:00:00 | PT800H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-08-12T08:00:00 | 2025-01-03T17:00:00 | 2024-08-12T08:00:00 | 2025-01-03T17:00:00 | 19680000 | 18240000 | 3 | PT800H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-12T08:00:00 | 2025-01-03T17:00:00 | PT800H0M0S
161 | 162 | 162 | Steel stud install on 2nd & drywall behind the tubs including fire wall taping if it is a fire wall | 0 | 0 | 28.1 | 28.1 | 4 | 500 | 2024-08-12T08:00:00 | 2024-08-29T17:00:00 | PT112H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-12T08:00:00 | 2024-08-29T17:00:00 | 2024-08-12T08:00:00 | 2024-08-29T17:00:00 | 12480000 | 17280000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-12T08:00:00 | 2024-08-29T17:00:00 | PT112H0M0S | PT112H0M0S | 2024-08-29T17:00:00 | 100 | 2024-08-12T08:00:00 | PT112H0M0S | PT112H0M0S |  | 100 |  | 4320000.0
162 | 163 | 163 | Install pocket foor frame | 0 | 0 | 28.2 | 28.2 | 4 | 500 | 2024-08-28T08:00:00 | 2024-09-03T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-28T08:00:00 | 2024-09-03T17:00:00 | 2024-08-28T08:00:00 | 2024-09-03T17:00:00 |  |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-28T08:00:00 | 2024-09-03T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-09-03T17:00:00 | 100 | 2024-08-28T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
163 | 164 | 164 | Install tubs and showers | 0 | 0 | 28.3 | 28.3 | 4 | 500 | 2024-08-30T08:00:00 | 2024-09-04T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-30T08:00:00 | 2024-09-04T17:00:00 | 2024-08-30T08:00:00 | 2024-09-04T17:00:00 | 16800000 | 18240000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-30T08:00:00 | 2024-09-04T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-09-04T17:00:00 | 100 | 2024-08-30T08:00:00 | PT32H0M0S | PT32H0M0S |  | 100 |  | 960000.0
164 | 165 | 165 | Water dams 2nd floor | 0 | 0 | 28.4 | 28.4 | 4 | 500 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | 17280000 | 17760000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-08-23T17:00:00 | 100 | 2024-08-19T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100 |  | 480000.0
165 | 166 | 166 | Rough in exterior walls on 2nd and sheds | 0 | 0 | 28.5 | 28.5 | 4 | 500 | 2024-11-08T08:00:00 | 2024-11-21T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-08T08:00:00 | 2024-11-21T17:00:00 | 2024-11-08T08:00:00 | 2024-11-21T17:00:00 | 50400000 | 50880000 | 3 | PT14H23M60S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-08T08:00:00 | 2024-11-21T17:00:00 | PT72H0M0S | PT72H0M0S | 2024-11-21T17:00:00 | 80 | 2024-11-08T08:00:00 | PT57H36M0S | PT57H36M0S |  | 80 |  | -480000.0
166 | 167 | 167 | Electrical rough in on 2nd | 0 | 0 | 28.6 | 28.6 | 4 | 500 | 2024-11-08T08:00:00 | 2024-11-22T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-08T08:00:00 | 2024-11-22T17:00:00 | 2024-11-08T08:00:00 | 2024-11-22T17:00:00 | 40800000 | 41760000 | 3 | PT80H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-08T08:00:00 | 2024-11-22T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-11-22T17:00:00 | 0 | 2024-11-08T08:00:00 |  |  |  | 0
167 | 168 | 168 | Electrical rough in hallways & stairwells on 2nd | 0 | 0 | 28.7 | 28.7 | 4 | 500 | 2024-11-08T08:00:00 | 2024-11-22T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-08T08:00:00 | 2024-11-22T17:00:00 | 2024-11-08T08:00:00 | 2024-11-22T17:00:00 | 15840000 | 18240000 | 3 | PT80H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-08T08:00:00 | 2024-11-22T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-11-22T17:00:00 | 0 | 2024-11-08T08:00:00 |  |  |  | 0 |  | 1440000.0
168 | 169 | 169 | Sprinkler rough in on 2nd | 0 | 0 | 28.8 | 28.8 | 4 | 500 | 2024-08-26T08:00:00 | 2024-09-06T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-26T08:00:00 | 2024-09-06T17:00:00 | 2024-08-26T08:00:00 | 2024-09-06T17:00:00 | 14880000 | 15360000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-26T08:00:00 | 2024-09-06T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-09-06T17:00:00 | 100 | 2024-08-26T08:00:00 | PT80H0M0S | PT80H0M0S |  | 100
169 | 170 | 170 | Sprinkler rough in corridor & stairwells on 2nd | 0 | 0 | 28.9 | 28.9 | 4 | 500 | 2024-08-26T08:00:00 | 2024-09-06T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-26T08:00:00 | 2024-09-06T17:00:00 | 2024-08-26T08:00:00 | 2024-09-06T17:00:00 | -16800000 | -14880000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-26T08:00:00 | 2024-09-06T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-09-06T17:00:00 | 100 | 2024-08-26T08:00:00 | PT80H0M0S | PT80H0M0S |  | 100 |  | 1440000.0
170 | 171 | 171 | Mechanical rough in on 2nd | 0 | 0 | 28.10 | 28.10 | 4 | 500 | 2024-11-01T08:00:00 | 2024-11-15T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-01T08:00:00 | 2024-11-15T17:00:00 | 2024-11-01T08:00:00 | 2024-11-15T17:00:00 | 38400000 | 39360000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-01T08:00:00 | 2024-11-15T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-11-15T17:00:00 | 80 | 2024-11-01T08:00:00 | PT64H0M0S | PT64H0M0S |  | 80
171 | 172 | 172 | Mechanical rough in hallways & stairwells on 2nd | 0 | 0 | 28.11 | 28.11 | 4 | 500 | 2024-11-01T08:00:00 | 2024-11-15T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-01T08:00:00 | 2024-11-15T17:00:00 | 2024-11-01T08:00:00 | 2024-11-15T17:00:00 | 10080000 | 12480000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-01T08:00:00 | 2024-11-15T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-11-15T17:00:00 | 80 | 2024-11-01T08:00:00 | PT64H0M0S | PT64H0M0S |  | 80 |  | 1440000.0
172 | 173 | 173 | Call for Mechanical and Electrical inspection | 0 | 0 | 28.12 | 28.12 | 4 | 500 | 2024-11-25T08:00:00 | 2024-11-25T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-25T08:00:00 | 2024-11-25T17:00:00 | 2024-11-25T08:00:00 | 2024-11-25T17:00:00 |  |  | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-25T08:00:00 | 2024-11-25T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-25T17:00:00 | 0 | 2024-11-25T08:00:00 |  |  |  | 0
173 | 174 | 174 | Siding 2nd floor | 0 | 0 | 28.13 | 28.13 | 4 | 500 | 2024-11-22T08:00:00 | 2024-12-09T17:00:00 | PT96H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-22T08:00:00 | 2024-12-09T17:00:00 | 2024-11-22T08:00:00 | 2024-12-09T17:00:00 | 48000000 | 47040000 | 3 | PT96H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-22T08:00:00 | 2024-12-09T17:00:00 | PT96H0M0S | PT96H0M0S | 2024-12-09T17:00:00 | 0 | 2024-11-22T08:00:00 |  |  |  | 0 |  | -1440000.0
174 | 175 | 175 | Assign siding checklist | 0 | 0 | 28.14 | 28.14 | 4 | 500 | 2024-12-10T08:00:00 | 2024-12-10T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-10T08:00:00 | 2024-12-10T17:00:00 | 2024-12-10T08:00:00 | 2024-12-10T17:00:00 | 46560000 | 47040000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-10T08:00:00 | 2024-12-10T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-12-10T17:00:00 | 0 | 2024-12-10T08:00:00 |  |  |  | 0
175 | 176 | 176 | Poly and insulate on 2nd exterior walls | 0 | 0 | 28.15 | 28.15 | 4 | 500 | 2024-11-25T08:00:00 | 2024-11-28T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-25T08:00:00 | 2024-11-28T17:00:00 | 2024-11-25T08:00:00 | 2024-11-28T17:00:00 | 50880000 | 51840000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-25T08:00:00 | 2024-11-28T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-11-28T17:00:00 | 0 | 2024-11-25T08:00:00 |  |  |  | 0 |  | 960000.0
176 | 177 | 177 | Board upper 16" strips in common area and all suites on 2nd | 0 | 0 | 28.16 | 28.16 | 4 | 500 | 2024-08-30T08:00:00 | 2024-09-04T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-30T08:00:00 | 2024-09-04T17:00:00 | 2024-08-30T08:00:00 | 2024-09-04T17:00:00 | 16800000 | 17280000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-30T08:00:00 | 2024-09-04T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-09-04T17:00:00 | 100 | 2024-08-30T08:00:00 | PT32H0M0S | PT32H0M0S |  | 100
177 | 178 | 178 | Fire tape / Fire caulk upper strips on 2nd | 0 | 0 | 28.17 | 28.17 | 4 | 500 | 2024-11-25T08:00:00 | 2024-11-25T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-25T08:00:00 | 2024-11-25T17:00:00 | 2024-11-25T08:00:00 | 2024-11-25T17:00:00 | 44160000 | 44640000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-25T08:00:00 | 2024-11-25T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-25T17:00:00 | 100 | 2024-11-25T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
178 | 179 | 179 | Frame drops on 2nd | 0 | 0 | 28.18 | 28.18 | 4 | 500 | 2024-11-26T08:00:00 | 2024-12-02T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-26T08:00:00 | 2024-12-02T17:00:00 | 2024-11-26T08:00:00 | 2024-12-02T17:00:00 | 44160000 | 44640000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-26T08:00:00 | 2024-12-02T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-12-02T17:00:00 | 100 | 2024-11-26T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
179 | 180 | 180 | Back framing on 2nd | 0 | 0 | 28.19 | 28.19 | 4 | 500 | 2024-08-21T08:00:00 | 2024-08-27T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-21T08:00:00 | 2024-08-27T17:00:00 | 2024-08-21T08:00:00 | 2024-08-27T17:00:00 | 13440000 | 13920000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-21T08:00:00 | 2024-08-27T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-08-27T17:00:00 | 100 | 2024-08-21T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
180 | 181 | 181 | Assign pre board interior walls checklist | 0 | 0 | 28.20 | 28.20 | 4 | 500 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | 42720000 | 43200000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-28T17:00:00 | 0 | 2024-11-28T08:00:00 |  |  |  | 0
181 | 182 | 182 | Board 2nd floor walls | 0 | 0 | 28.21 | 28.21 | 4 | 500 | 2024-11-28T08:00:00 | 2024-12-04T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-28T08:00:00 | 2024-12-04T17:00:00 | 2024-11-28T08:00:00 | 2024-12-04T17:00:00 | 42240000 | 42720000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-28T08:00:00 | 2024-12-04T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-12-04T17:00:00 | 0 | 2024-11-28T08:00:00 |  |  |  | 0
182 | 183 | 183 | Assign pre board inspection check list | 0 | 0 | 28.22 | 28.22 | 4 | 500 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | 52320000 | 52800000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-28T17:00:00 | 0 | 2024-11-28T08:00:00 |  |  |  | 0
183 | 184 | 184 | Board exterior walls on 2nd and sheds | 0 | 0 | 28.23 | 28.23 | 4 | 500 | 2024-11-28T08:00:00 | 2024-12-04T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-28T08:00:00 | 2024-12-04T17:00:00 | 2024-11-28T08:00:00 | 2024-12-04T17:00:00 | 52320000 | 52800000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-28T08:00:00 | 2024-12-04T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-12-04T17:00:00 | 0 | 2024-11-28T08:00:00 |  |  |  | 0 |  | 480000.0
184 | 185 | 185 | Tape suites on 2nd | 0 | 0 | 28.24 | 28.24 | 4 | 500 | 2024-12-05T08:00:00 | 2024-12-19T17:00:00 | PT88H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-05T08:00:00 | 2024-12-19T17:00:00 | 2024-12-05T08:00:00 | 2024-12-19T17:00:00 | 30720000 | 31680000 | 3 | PT88H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-05T08:00:00 | 2024-12-19T17:00:00 | PT88H0M0S | PT88H0M0S | 2024-12-19T17:00:00 | 0 | 2024-12-05T08:00:00 |  |  |  | 0 |  | 480000.0
185 | 186 | 186 | Assign taping inspection checklist for suites | 0 | 0 | 28.25 | 28.25 | 4 | 500 | 2024-12-19T08:00:00 | 2024-12-19T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-19T08:00:00 | 2024-12-19T17:00:00 | 2024-12-19T08:00:00 | 2024-12-19T17:00:00 | 30720000 | 31200000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-19T08:00:00 | 2024-12-19T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-12-19T17:00:00 | 0 | 2024-12-19T08:00:00 |  |  |  | 0
186 | 187 | 187 | Assign Corridor & Stairwell pre board inspection checklist | 0 | 0 | 28.26 | 28.26 | 4 | 500 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | 12480000 | 12960000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-28T17:00:00 | 0 | 2024-11-28T08:00:00 |  |  |  | 0
187 | 188 | 188 | Board 2nd floor hallways and stairwells | 0 | 0 | 28.27 | 28.27 | 4 | 500 | 2024-11-28T08:00:00 | 2024-12-04T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-28T08:00:00 | 2024-12-04T17:00:00 | 2024-11-28T08:00:00 | 2024-12-04T17:00:00 | 12000000 | 12960000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-28T08:00:00 | 2024-12-04T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-12-04T17:00:00 | 0 | 2024-11-28T08:00:00 |  |  |  | 0 |  | 480000.0
188 | 189 | 189 | Tape 2nd floor hallways and stair wells | 0 | 0 | 28.28 | 28.28 | 4 | 500 | 2024-12-05T08:00:00 | 2024-12-19T17:00:00 | PT88H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-05T08:00:00 | 2024-12-19T17:00:00 | 2024-12-05T08:00:00 | 2024-12-19T17:00:00 | 12480000 | 15840000 | 3 | PT88H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-05T08:00:00 | 2024-12-19T17:00:00 | PT88H0M0S | PT88H0M0S | 2024-12-19T17:00:00 | 0 | 2024-12-05T08:00:00 |  |  |  | 0 |  | 2880000.0
189 | 190 | 190 | Assign taping inspection checklist | 0 | 0 | 28.29 | 28.29 | 4 | 500 | 2024-12-19T08:00:00 | 2024-12-19T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-19T08:00:00 | 2024-12-19T17:00:00 | 2024-12-19T08:00:00 | 2024-12-19T17:00:00 | 14880000 | 15360000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-19T08:00:00 | 2024-12-19T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-12-19T17:00:00 | 0 | 2024-12-19T08:00:00 |  |  |  | 0
190 | 191 | 191 | Install suite entry doors and frames and Interior doors, trims and jambs | 0 | 0 | 28.30 | 28.30 | 4 | 500 | 2024-12-23T08:00:00 | 2025-01-03T17:00:00 | PT48H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-23T08:00:00 | 2025-01-03T17:00:00 | 2024-12-23T08:00:00 | 2025-01-03T17:00:00 | 15360000 | 18240000 | 3 | PT48H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-23T08:00:00 | 2025-01-03T17:00:00 | PT48H0M0S | PT48H0M0S | 2025-01-03T17:00:00 | 0 | 2024-12-23T08:00:00 |  |  |  | 0 |  | 960000.0
191 | 192 | 192 | Rough in 3rd floor | 0 | 0 | 29 | 29 | 3 | 500 | 2024-08-19T08:00:00 | 2024-12-13T17:00:00 | PT672H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-08-19T08:00:00 | 2024-12-13T17:00:00 | 2024-08-19T08:00:00 | 2024-12-13T17:00:00 | 5760000 | 10560000 | 3 | PT672H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-19T08:00:00 | 2024-12-13T17:00:00 | PT672H0M0S
192 | 193 | 193 | Steel stud install on 3rd & drywall behind the tubs including fire wall taping if it is a fire wall | 0 | 0 | 29.1 | 29.1 | 4 | 500 | 2024-08-30T08:00:00 | 2024-09-05T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-30T08:00:00 | 2024-09-05T17:00:00 | 2024-08-30T08:00:00 | 2024-09-05T17:00:00 | 10080000 | 10560000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-30T08:00:00 | 2024-09-05T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-09-05T17:00:00 | 100 | 2024-08-30T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
193 | 194 | 194 | Install pocket door frames | 0 | 0 | 29.2 | 29.2 | 4 | 500 | 2024-09-06T08:00:00 | 2024-09-12T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-06T08:00:00 | 2024-09-12T17:00:00 | 2024-09-06T08:00:00 | 2024-09-12T17:00:00 |  |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-06T08:00:00 | 2024-09-12T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-09-12T17:00:00 | 100 | 2024-09-06T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
194 | 195 | 195 | Install tubs and showers | 0 | 0 | 29.3 | 29.3 | 4 | 500 | 2024-09-06T08:00:00 | 2024-09-11T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-06T08:00:00 | 2024-09-11T17:00:00 | 2024-09-06T08:00:00 | 2024-09-11T17:00:00 | 10080000 | 11040000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-06T08:00:00 | 2024-09-11T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-09-11T17:00:00 | 100 | 2024-09-06T08:00:00 | PT32H0M0S | PT32H0M0S |  | 100 |  | 480000.0
195 | 196 | 196 | Water dams 3rd floor | 0 | 0 | 29.4 | 29.4 | 4 | 500 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | -20640000 | -20160000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-08-23T17:00:00 | 100 | 2024-08-19T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
196 | 197 | 197 | Rough in exterior walls on 3rd and sheds | 0 | 0 | 29.5 | 29.5 | 4 | 500 | 2024-10-28T08:00:00 | 2024-11-08T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-28T08:00:00 | 2024-11-08T17:00:00 | 2024-10-28T08:00:00 | 2024-11-08T17:00:00 | 8160000 | 8640000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-28T08:00:00 | 2024-11-08T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-11-08T17:00:00 | 100 | 2024-10-28T08:00:00 | PT80H0M0S | PT80H0M0S |  | 100
197 | 198 | 198 | Electrical rough in on 3rd | 0 | 0 | 29.6 | 29.6 | 4 | 500 | 2024-10-28T08:00:00 | 2024-11-08T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-10-28T08:00:00 | 2024-11-08T17:00:00 | 2024-10-28T08:00:00 | 2024-11-08T17:00:00 | 27360000 | 27840000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-28T08:00:00 | 2024-11-08T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-11-08T17:00:00 | 80 | 2024-10-28T08:00:00 | PT64H0M0S | PT64H0M0S |  | 80
198 | 199 | 199 | Electrical rough in hallways & stairwells on 3rd | 0 | 0 | 29.7 | 29.7 | 4 | 500 | 2024-10-28T08:00:00 | 2024-11-08T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-10-28T08:00:00 | 2024-11-08T17:00:00 | 2024-10-28T08:00:00 | 2024-11-08T17:00:00 | 5760000 | 8640000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-28T08:00:00 | 2024-11-08T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-11-08T17:00:00 | 80 | 2024-10-28T08:00:00 | PT64H0M0S | PT64H0M0S |  | 80 |  | 2400000.0
199 | 200 | 200 | Sprinkler rough in on 3rd | 0 | 0 | 29.8 | 29.8 | 4 | 500 | 2024-09-09T08:00:00 | 2024-09-20T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-09T08:00:00 | 2024-09-20T17:00:00 | 2024-09-09T08:00:00 | 2024-09-20T17:00:00 | 10560000 | 11040000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-09T08:00:00 | 2024-09-20T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-09-20T17:00:00 | 100 | 2024-09-09T08:00:00 | PT80H0M0S | PT80H0M0S |  | 100
200 | 201 | 201 | Sprinkler rough in hallways & stairwells on 3rd | 0 | 0 | 29.9 | 29.9 | 4 | 500 | 2024-09-09T08:00:00 | 2024-09-20T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-09T08:00:00 | 2024-09-20T17:00:00 | 2024-09-09T08:00:00 | 2024-09-20T17:00:00 | -11040000 | -8160000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-09T08:00:00 | 2024-09-20T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-09-20T17:00:00 | 100 | 2024-09-09T08:00:00 | PT80H0M0S | PT80H0M0S |  | 100 |  | 2400000.0
201 | 202 | 202 | Mechanical rough in on 3rd | 0 | 0 | 29.10 | 29.10 | 4 | 500 | 2024-10-28T08:00:00 | 2024-11-07T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-10-28T08:00:00 | 2024-11-07T17:00:00 | 2024-10-28T08:00:00 | 2024-11-07T17:00:00 | 27360000 | 27360000 | 3 | PT0H43M12S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-28T08:00:00 | 2024-11-07T17:00:00 | PT72H0M0S | PT72H0M0S | 2024-11-07T17:00:00 | 99 | 2024-10-28T08:00:00 | PT71H16M48S | PT71H16M48S |  | 99 |  | -480000.0
202 | 203 | 203 | Mechanical rough in hallways & stairwells on 3rd | 0 | 0 | 29.11 | 29.11 | 4 | 500 | 2024-10-28T08:00:00 | 2024-11-07T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-10-28T08:00:00 | 2024-11-07T17:00:00 | 2024-10-28T08:00:00 | 2024-11-07T17:00:00 | 5760000 | 8160000 | 3 | PT0H43M12S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-28T08:00:00 | 2024-11-07T17:00:00 | PT72H0M0S | PT72H0M0S | 2024-11-07T17:00:00 | 99 | 2024-10-28T08:00:00 | PT71H16M48S | PT71H16M48S |  | 99 |  | 1920000.0
203 | 204 | 204 | Call for Mechanical and Electrical Inspection | 0 | 0 | 29.12 | 29.12 | 4 | 500 | 2024-11-12T08:00:00 | 2024-11-12T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-12T08:00:00 | 2024-11-12T17:00:00 | 2024-11-12T08:00:00 | 2024-11-12T17:00:00 |  |  | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-12T08:00:00 | 2024-11-12T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-12T17:00:00 | 0 | 2024-11-12T08:00:00 |  |  |  | 0
204 | 205 | 205 | Siding 3rd floor | 0 | 0 | 29.13 | 29.13 | 4 | 500 | 2024-11-06T08:00:00 | 2024-11-21T17:00:00 | PT88H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-06T08:00:00 | 2024-11-21T17:00:00 | 2024-11-06T08:00:00 | 2024-11-21T17:00:00 | 4320000 | 3360000 | 3 | PT88H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-06T08:00:00 | 2024-11-21T17:00:00 | PT88H0M0S | PT88H0M0S | 2024-11-21T17:00:00 | 0 | 2024-11-06T08:00:00 |  |  |  | 0 |  | -1440000.0
205 | 206 | 206 | Assign siding checklist | 0 | 0 | 29.14 | 29.14 | 4 | 500 | 2024-11-22T08:00:00 | 2024-11-22T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-22T08:00:00 | 2024-11-22T17:00:00 | 2024-11-22T08:00:00 | 2024-11-22T17:00:00 | 2880000 | 3360000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-22T08:00:00 | 2024-11-22T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-22T17:00:00 | 0 | 2024-11-22T08:00:00 |  |  |  | 0
206 | 207 | 207 | Poly and insulate on 3rd exterior walls | 0 | 0 | 29.15 | 29.15 | 4 | 500 | 2024-11-12T08:00:00 | 2024-11-15T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-12T08:00:00 | 2024-11-15T17:00:00 | 2024-11-12T08:00:00 | 2024-11-15T17:00:00 | 8640000 | 10080000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-12T08:00:00 | 2024-11-15T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-11-15T17:00:00 | 0 | 2024-11-12T08:00:00 |  |  |  | 0 |  | 960000.0
207 | 208 | 208 | Board upper 16" strips in common area & all suites on 3rd | 0 | 0 | 29.16 | 29.16 | 4 | 500 | 2024-09-11T08:00:00 | 2024-09-16T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-11T08:00:00 | 2024-09-16T17:00:00 | 2024-09-11T08:00:00 | 2024-09-16T17:00:00 | 11520000 | 13440000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-11T08:00:00 | 2024-09-16T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-09-16T17:00:00 | 100 | 2024-09-11T08:00:00 | PT32H0M0S | PT32H0M0S |  | 100 |  | 1440000.0
208 | 209 | 209 | Fire tape / Fire caulk upper strips on 3rd | 0 | 0 | 29.17 | 29.17 | 4 | 500 | 2024-11-11T08:00:00 | 2024-11-11T17:00:00 | PT0H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-11T08:00:00 | 2024-11-11T17:00:00 | 2024-11-11T08:00:00 | 2024-11-11T17:00:00 | 31680000 | 32160000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-11T08:00:00 | 2024-11-11T17:00:00 |  |  | 2024-11-11T17:00:00 | 100 | 2024-11-11T08:00:00 |  |  |  | 100 |  | -480000.0
209 | 210 | 210 | Frame drops on 3rd | 0 | 0 | 29.18 | 29.18 | 4 | 500 | 2024-11-12T08:00:00 | 2024-11-18T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-12T08:00:00 | 2024-11-18T17:00:00 | 2024-11-12T08:00:00 | 2024-11-18T17:00:00 | 31680000 | 34080000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-12T08:00:00 | 2024-11-18T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-11-18T17:00:00 | 100 | 2024-11-12T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100 |  | 1920000.0
210 | 211 | 211 | Back framing on 3rd | 0 | 0 | 29.19 | 29.19 | 4 | 500 | 2024-09-10T08:00:00 | 2024-09-16T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-10T08:00:00 | 2024-09-16T17:00:00 | 2024-09-10T08:00:00 | 2024-09-16T17:00:00 | 11040000 | 11520000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-10T08:00:00 | 2024-09-16T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-09-16T17:00:00 | 100 | 2024-09-10T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
211 | 212 | 212 | Assign pre board interior walls checklist | 0 | 0 | 29.20 | 29.20 | 4 | 500 | 2024-11-15T08:00:00 | 2024-11-15T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-15T08:00:00 | 2024-11-15T17:00:00 | 2024-11-15T08:00:00 | 2024-11-15T17:00:00 | 29280000 | 29760000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-15T08:00:00 | 2024-11-15T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-15T17:00:00 | 0 | 2024-11-15T08:00:00 |  |  |  | 0
212 | 213 | 213 | Load boards on floor and Board 3rd floor walls | 0 | 0 | 29.21 | 29.21 | 4 | 500 | 2024-11-15T08:00:00 | 2024-11-22T17:00:00 | PT48H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-15T08:00:00 | 2024-11-22T17:00:00 | 2024-11-15T08:00:00 | 2024-11-22T17:00:00 | 28800000 | 29760000 | 3 | PT48H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-15T08:00:00 | 2024-11-22T17:00:00 | PT48H0M0S | PT48H0M0S | 2024-11-22T17:00:00 | 0 | 2024-11-15T08:00:00 |  |  |  | 0 |  | 480000.0
213 | 214 | 214 | Assign pre board inspection check list | 0 | 0 | 29.22 | 29.22 | 4 | 500 | 2024-11-15T08:00:00 | 2024-11-15T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-15T08:00:00 | 2024-11-15T17:00:00 | 2024-11-15T08:00:00 | 2024-11-15T17:00:00 | 10080000 | 10560000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-15T08:00:00 | 2024-11-15T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-15T17:00:00 | 0 | 2024-11-15T08:00:00 |  |  |  | 0
214 | 215 | 215 | Load boards on floor and Board exterior walls on 3rd and sheds | 0 | 0 | 29.23 | 29.23 | 4 | 500 | 2024-11-15T08:00:00 | 2024-11-22T17:00:00 | PT48H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-15T08:00:00 | 2024-11-22T17:00:00 | 2024-11-15T08:00:00 | 2024-11-22T17:00:00 | 9120000 | 10080000 | 3 | PT48H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-15T08:00:00 | 2024-11-22T17:00:00 | PT48H0M0S | PT48H0M0S | 2024-11-22T17:00:00 | 0 | 2024-11-15T08:00:00 |  |  |  | 0 |  | 480000.0
215 | 216 | 216 | Tape suites on 3rd | 0 | 0 | 29.24 | 29.24 | 4 | 500 | 2024-11-22T08:00:00 | 2024-12-05T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-22T08:00:00 | 2024-12-05T17:00:00 | 2024-11-22T08:00:00 | 2024-12-05T17:00:00 | 21120000 | 21600000 | 3 | PT80H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-22T08:00:00 | 2024-12-05T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-12-05T17:00:00 | 0 | 2024-11-22T08:00:00 |  |  |  | 0
216 | 217 | 217 | Assign taping inspection checklist for suites | 0 | 0 | 29.25 | 29.25 | 4 | 500 | 2024-12-05T08:00:00 | 2024-12-05T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-05T08:00:00 | 2024-12-05T17:00:00 | 2024-12-05T08:00:00 | 2024-12-05T17:00:00 | 20640000 | 21120000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-05T08:00:00 | 2024-12-05T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-12-05T17:00:00 | 0 | 2024-12-05T08:00:00 |  |  |  | 0
217 | 218 | 218 | Assign corridor & stairwell pre board inspection checklist | 0 | 0 | 29.26 | 29.26 | 4 | 500 | 2024-11-12T08:00:00 | 2024-11-12T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-12T08:00:00 | 2024-11-12T17:00:00 | 2024-11-12T08:00:00 | 2024-11-12T17:00:00 | 8640000 | 9120000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-12T08:00:00 | 2024-11-12T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-12T17:00:00 | 0 | 2024-11-12T08:00:00 |  |  |  | 0
218 | 219 | 219 | Load the board on floor and Board 3rd floor hallways and stairwells | 0 | 0 | 29.27 | 29.27 | 4 | 500 | 2024-11-15T08:00:00 | 2024-11-22T17:00:00 | PT48H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-15T08:00:00 | 2024-11-22T17:00:00 | 2024-11-15T08:00:00 | 2024-11-22T17:00:00 | 9600000 | 10560000 | 3 | PT48H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-15T08:00:00 | 2024-11-22T17:00:00 | PT48H0M0S | PT48H0M0S | 2024-11-22T17:00:00 | 0 | 2024-11-15T08:00:00 |  |  |  | 0 |  | 480000.0
219 | 220 | 220 | Tape 3rd floor hallways and stair wells | 0 | 0 | 29.28 | 29.28 | 4 | 500 | 2024-11-22T08:00:00 | 2024-12-05T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-22T08:00:00 | 2024-12-05T17:00:00 | 2024-11-22T08:00:00 | 2024-12-05T17:00:00 | 9600000 | 12480000 | 3 | PT80H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-22T08:00:00 | 2024-12-05T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-12-05T17:00:00 | 0 | 2024-11-22T08:00:00 |  |  |  | 0 |  | 2400000.0
220 | 221 | 221 | Assign taping inspection checklist | 0 | 0 | 29.29 | 29.29 | 4 | 500 | 2024-12-05T08:00:00 | 2024-12-05T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-05T08:00:00 | 2024-12-05T17:00:00 | 2024-12-05T08:00:00 | 2024-12-05T17:00:00 | 11520000 | 12000000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-05T08:00:00 | 2024-12-05T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-12-05T17:00:00 | 0 | 2024-12-05T08:00:00 |  |  |  | 0
221 | 222 | 222 | Install suite entry doors and frames and Interior doors, trims and jambs | 0 | 0 | 29.30 | 29.30 | 4 | 500 | 2024-12-09T08:00:00 | 2024-12-13T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-09T08:00:00 | 2024-12-13T17:00:00 | 2024-12-09T08:00:00 | 2024-12-13T17:00:00 | 12000000 | 12480000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-09T08:00:00 | 2024-12-13T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-12-13T17:00:00 | 0 | 2024-12-09T08:00:00 |  |  |  | 0
222 | 223 | 223 | Rough in 4th floor | 0 | 0 | 30 | 30 | 3 | 500 | 2024-08-19T08:00:00 | 2024-12-06T17:00:00 | PT632H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-08-19T08:00:00 | 2024-12-06T17:00:00 | 2024-08-19T08:00:00 | 2024-12-06T17:00:00 | -20640000 | -35040000 | 3 | PT632H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-19T08:00:00 | 2024-12-06T17:00:00 | PT632H0M0S
223 | 224 | 224 | Steel stud install on 4th & drywall behind the tubs including fire wall taping if it is a fire wall | 0 | 0 | 30.1 | 30.1 | 4 | 500 | 2024-09-18T08:00:00 | 2024-09-26T17:00:00 | PT56H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-18T08:00:00 | 2024-09-26T17:00:00 | 2024-09-18T08:00:00 | 2024-09-26T17:00:00 | -26880000 | -25440000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-18T08:00:00 | 2024-09-26T17:00:00 | PT56H0M0S | PT56H0M0S | 2024-09-26T17:00:00 | 100 | 2024-09-18T08:00:00 | PT56H0M0S | PT56H0M0S |  | 100 |  | 960000.0
224 | 225 | 225 | Install pocket door frames | 0 | 0 | 30.2 | 30.2 | 4 | 500 | 2024-09-20T08:00:00 | 2024-09-26T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-20T08:00:00 | 2024-09-26T17:00:00 | 2024-09-20T08:00:00 | 2024-09-26T17:00:00 |  |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-20T08:00:00 | 2024-09-26T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-09-26T17:00:00 | 100 | 2024-09-20T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
225 | 226 | 226 | Call the surveyor to measure for condo plan | 0 | 0 | 30.3 | 30.3 | 4 | 500 | 2024-10-29T08:00:00 | 2024-10-31T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-10-29T08:00:00 | 2024-10-31T17:00:00 | 2024-10-29T08:00:00 | 2024-10-31T17:00:00 |  |  | 3 | PT24H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-29T08:00:00 | 2024-10-31T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-10-31T17:00:00 | 0 | 2024-10-29T08:00:00 |  |  |  | 0
226 | 227 | 227 | Install tubs and showers | 0 | 0 | 30.4 | 30.4 | 4 | 500 | 2024-09-26T08:00:00 | 2024-09-27T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-26T08:00:00 | 2024-09-27T17:00:00 | 2024-09-26T08:00:00 | 2024-09-27T17:00:00 | -26400000 | -26400000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-26T08:00:00 | 2024-09-27T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-09-27T17:00:00 | 100 | 2024-09-26T08:00:00 | PT16H0M0S | PT16H0M0S |  | 100 |  | -480000.0
227 | 228 | 228 | Water dams 4th floor | 0 | 0 | 30.5 | 30.5 | 4 | 500 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | -23040000 | -22560000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-19T08:00:00 | 2024-08-23T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-08-23T17:00:00 | 100 | 2024-08-19T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
228 | 229 | 229 | Rough in exterior walls on 4th and sheds | 0 | 0 | 30.6 | 30.6 | 4 | 500 | 2024-10-21T08:00:00 | 2024-10-31T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-21T08:00:00 | 2024-10-31T17:00:00 | 2024-10-21T08:00:00 | 2024-10-31T17:00:00 | 960000 | 3360000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-21T08:00:00 | 2024-10-31T17:00:00 | PT72H0M0S | PT72H0M0S | 2024-10-31T17:00:00 | 100 | 2024-10-21T08:00:00 | PT72H0M0S | PT72H0M0S |  | 100 |  | 1920000.0
229 | 230 | 230 | Electrical rough in on 4th | 0 | 0 | 30.7 | 30.7 | 4 | 500 | 2024-10-21T08:00:00 | 2024-10-31T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-21T08:00:00 | 2024-10-31T17:00:00 | 2024-10-21T08:00:00 | 2024-10-31T17:00:00 | -18240000 | -18240000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-21T08:00:00 | 2024-10-31T17:00:00 | PT72H0M0S | PT72H0M0S | 2024-10-31T17:00:00 | 100 | 2024-10-21T08:00:00 | PT72H0M0S | PT72H0M0S |  | 100
230 | 231 | 231 | Electrical rough in hallways stairwells on 4th | 0 | 0 | 30.8 | 30.8 | 4 | 500 | 2024-10-21T08:00:00 | 2024-10-31T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-21T08:00:00 | 2024-10-31T17:00:00 | 2024-10-21T08:00:00 | 2024-10-31T17:00:00 | -42720000 | -40320000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-21T08:00:00 | 2024-10-31T17:00:00 | PT72H0M0S | PT72H0M0S | 2024-10-31T17:00:00 | 100 | 2024-10-21T08:00:00 | PT72H0M0S | PT72H0M0S |  | 100 |  | 1920000.0
231 | 232 | 232 | Sprinkler rough in on 4th | 0 | 0 | 30.9 | 30.9 | 4 | 500 | 2024-09-23T08:00:00 | 2024-09-30T17:00:00 | PT48H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-23T08:00:00 | 2024-09-30T17:00:00 | 2024-09-23T08:00:00 | 2024-09-30T17:00:00 | -27840000 | -29280000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-23T08:00:00 | 2024-09-30T17:00:00 | PT48H0M0S | PT48H0M0S | 2024-09-30T17:00:00 | 100 | 2024-09-23T08:00:00 | PT48H0M0S | PT48H0M0S |  | 100 |  | -1440000.0
232 | 233 | 233 | Sprinkler rough in hallways stairwells on 4th | 0 | 0 | 30.10 | 30.10 | 4 | 500 | 2024-09-23T08:00:00 | 2024-09-30T17:00:00 | PT48H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-23T08:00:00 | 2024-09-30T17:00:00 | 2024-09-23T08:00:00 | 2024-09-30T17:00:00 | -52320000 | -51360000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-23T08:00:00 | 2024-09-30T17:00:00 | PT48H0M0S | PT48H0M0S | 2024-09-30T17:00:00 | 100 | 2024-09-23T08:00:00 | PT48H0M0S | PT48H0M0S |  | 100 |  | 480000.0
233 | 234 | 234 | Mechanical rough in on 4th | 0 | 0 | 30.11 | 30.11 | 4 | 500 | 2024-10-21T08:00:00 | 2024-10-25T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-21T08:00:00 | 2024-10-25T17:00:00 | 2024-10-21T08:00:00 | 2024-10-25T17:00:00 | -18240000 | -20160000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-21T08:00:00 | 2024-10-25T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-10-25T17:00:00 | 100 | 2024-10-21T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100 |  | -1920000.0
234 | 235 | 235 | Mechanical rough in hallways stairwells on 4th | 0 | 0 | 30.12 | 30.12 | 4 | 500 | 2024-10-21T08:00:00 | 2024-10-25T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-21T08:00:00 | 2024-10-25T17:00:00 | 2024-10-21T08:00:00 | 2024-10-25T17:00:00 | -42720000 | -42240000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-21T08:00:00 | 2024-10-25T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-10-25T17:00:00 | 100 | 2024-10-21T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
235 | 236 | 236 | Call for Electrical and Mechanical inspection | 0 | 0 | 30.13 | 30.13 | 4 | 500 | 2024-10-31T08:00:00 | 2024-10-31T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-31T08:00:00 | 2024-10-31T17:00:00 | 2024-10-31T08:00:00 | 2024-10-31T17:00:00 |  |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-31T08:00:00 | 2024-10-31T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-10-31T17:00:00 | 100 | 2024-10-31T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
236 | 237 | 237 | Siding 4th floor | 0 | 0 | 30.14 | 30.14 | 4 | 500 | 2024-10-21T08:00:00 | 2024-11-05T17:00:00 | PT96H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-10-21T08:00:00 | 2024-11-05T17:00:00 | 2024-10-21T08:00:00 | 2024-11-05T17:00:00 | -3840000 | -4800000 | 3 | PT96H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-10-21T08:00:00 | 2024-11-05T17:00:00 | PT96H0M0S | PT96H0M0S | 2024-11-05T17:00:00 | 0 | 2024-10-21T08:00:00 |  |  |  | 0 |  | -960000.0
237 | 238 | 238 | Assign siding checklist | 0 | 0 | 30.15 | 30.15 | 4 | 500 | 2024-11-06T08:00:00 | 2024-11-06T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-06T08:00:00 | 2024-11-06T17:00:00 | 2024-11-06T08:00:00 | 2024-11-06T17:00:00 | -5280000 | -4800000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-06T08:00:00 | 2024-11-06T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-06T17:00:00 | 0 | 2024-11-06T08:00:00 |  |  |  | 0
238 | 239 | 239 | 4th floor framing inspection | 0 | 0 | 30.16 | 30.16 | 4 | 500 | 2024-11-04T08:00:00 | 2024-11-04T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-04T08:00:00 | 2024-11-04T17:00:00 | 2024-11-04T08:00:00 | 2024-11-04T17:00:00 |  |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-04T08:00:00 | 2024-11-04T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-04T17:00:00 | 100 | 2024-11-04T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
239 | 240 | 240 | Poly and insulate on 4th exterior walls | 0 | 0 | 30.17 | 30.17 | 4 | 500 | 2024-11-05T08:00:00 | 2024-11-07T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-05T08:00:00 | 2024-11-07T17:00:00 | 2024-11-05T08:00:00 | 2024-11-07T17:00:00 | 3840000 | 4800000 | 3 | PT24H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-05T08:00:00 | 2024-11-07T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-11-07T17:00:00 | 0 | 2024-11-05T08:00:00 |  |  |  | 0 |  | 480000.0
240 | 241 | 241 | Board upper 16" strips in common area and all suites on 4th | 0 | 0 | 30.18 | 30.18 | 4 | 500 | 2024-09-27T08:00:00 | 2024-10-02T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-27T08:00:00 | 2024-10-02T17:00:00 | 2024-09-27T08:00:00 | 2024-10-02T17:00:00 | -26400000 | -24480000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-27T08:00:00 | 2024-10-02T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-10-02T17:00:00 | 100 | 2024-09-27T08:00:00 | PT32H0M0S | PT32H0M0S |  | 100 |  | 1440000.0
241 | 242 | 242 | Fire tape / Fire caulk upper strips on 4th | 0 | 0 | 30.19 | 30.19 | 4 | 500 | 2024-11-01T08:00:00 | 2024-11-01T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-01T08:00:00 | 2024-11-01T17:00:00 | 2024-11-01T08:00:00 | 2024-11-01T17:00:00 | -14400000 | -13920000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-01T08:00:00 | 2024-11-01T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-01T17:00:00 | 100 | 2024-11-01T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
242 | 243 | 243 | Frame drops on 4th | 0 | 0 | 30.20 | 30.20 | 4 | 500 | 2024-11-29T08:00:00 | 2024-12-05T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-29T08:00:00 | 2024-12-05T17:00:00 | 2024-11-29T08:00:00 | 2024-12-05T17:00:00 | -4800000 | -2400000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-29T08:00:00 | 2024-12-05T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-12-05T17:00:00 | 100 | 2024-11-29T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100 |  | 1920000.0
243 | 244 | 244 | Back framing on 4th | 0 | 0 | 30.21 | 30.21 | 4 | 500 | 2024-09-23T08:00:00 | 2024-09-27T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-23T08:00:00 | 2024-09-27T17:00:00 | 2024-09-23T08:00:00 | 2024-09-27T17:00:00 | -27840000 | -27360000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-23T08:00:00 | 2024-09-27T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-09-27T17:00:00 | 100 | 2024-09-23T08:00:00 | PT40H0M0S | PT40H0M0S |  | 100
244 | 245 | 245 | Assign pre board interior walls checklist | 0 | 0 | 30.22 | 30.22 | 4 | 500 | 2024-11-08T08:00:00 | 2024-11-08T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-08T08:00:00 | 2024-11-08T17:00:00 | 2024-11-08T08:00:00 | 2024-11-08T17:00:00 | -16320000 | -15840000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-08T08:00:00 | 2024-11-08T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-08T17:00:00 | 0 | 2024-11-08T08:00:00 |  |  |  | 0 |  | 480000.0
245 | 246 | 246 | Load the board on floor and Board 4th floor walls | 0 | 0 | 30.23 | 30.23 | 4 | 500 | 2024-11-08T08:00:00 | 2024-11-15T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-08T08:00:00 | 2024-11-15T17:00:00 | 2024-11-08T08:00:00 | 2024-11-15T17:00:00 | -16800000 | -18240000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-08T08:00:00 | 2024-11-15T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-11-15T17:00:00 | 0 | 2024-11-08T08:00:00 |  |  |  | 0 |  | -1440000.0
246 | 247 | 247 | Assign exterior wall pre board inspection check list | 0 | 0 | 30.24 | 30.24 | 4 | 500 | 2024-11-08T08:00:00 | 2024-11-08T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-08T08:00:00 | 2024-11-08T17:00:00 | 2024-11-08T08:00:00 | 2024-11-08T17:00:00 | 5280000 | 5760000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-08T08:00:00 | 2024-11-08T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-08T17:00:00 | 0 | 2024-11-08T08:00:00 |  |  |  | 0
247 | 248 | 248 | Load the board on floor and Board exterior walls on 4th and sheds | 0 | 0 | 30.25 | 30.25 | 4 | 500 | 2024-11-08T08:00:00 | 2024-11-15T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-08T08:00:00 | 2024-11-15T17:00:00 | 2024-11-08T08:00:00 | 2024-11-15T17:00:00 | 4320000 | 5280000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-08T08:00:00 | 2024-11-15T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-11-15T17:00:00 | 0 | 2024-11-08T08:00:00 |  |  |  | 0
248 | 249 | 249 | Tape suites on 4th | 0 | 0 | 30.26 | 30.26 | 4 | 500 | 2024-11-15T08:00:00 | 2024-11-28T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-15T08:00:00 | 2024-11-28T17:00:00 | 2024-11-15T08:00:00 | 2024-11-28T17:00:00 | -27360000 | -26880000 | 3 | PT80H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-15T08:00:00 | 2024-11-28T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-11-28T17:00:00 | 0 | 2024-11-15T08:00:00 |  |  |  | 0
249 | 250 | 250 | Assign taping inspection checklist | 0 | 0 | 30.27 | 30.27 | 4 | 500 | 2024-11-15T08:00:00 | 2024-11-15T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-15T08:00:00 | 2024-11-15T17:00:00 | 2024-11-15T08:00:00 | 2024-11-15T17:00:00 | -32160000 | -31680000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-15T08:00:00 | 2024-11-15T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-15T17:00:00 | 0 | 2024-11-15T08:00:00 |  |  |  | 0
250 | 251 | 251 | Assign Corridor & Stairwell pre board inspection checklist | 0 | 0 | 30.28 | 30.28 | 4 | 500 | 2024-11-08T08:00:00 | 2024-11-08T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-08T08:00:00 | 2024-11-08T17:00:00 | 2024-11-08T08:00:00 | 2024-11-08T17:00:00 | -38400000 | -37920000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-08T08:00:00 | 2024-11-08T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-08T17:00:00 | 0 | 2024-11-08T08:00:00 |  |  |  | 0
251 | 252 | 252 | Load the board on floor and Board 4th floor hallways and stairwells | 0 | 0 | 30.29 | 30.29 | 4 | 500 | 2024-11-08T08:00:00 | 2024-11-15T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-08T08:00:00 | 2024-11-15T17:00:00 | 2024-11-08T08:00:00 | 2024-11-15T17:00:00 | -38880000 | -37920000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-08T08:00:00 | 2024-11-15T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-11-15T17:00:00 | 0 | 2024-11-08T08:00:00 |  |  |  | 0
252 | 253 | 253 | Tape 4th floor hallways and stair wells | 0 | 0 | 30.30 | 30.30 | 4 | 500 | 2024-11-15T08:00:00 | 2024-11-28T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-15T08:00:00 | 2024-11-28T17:00:00 | 2024-11-15T08:00:00 | 2024-11-28T17:00:00 | -38880000 | -36000000 | 3 | PT80H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-15T08:00:00 | 2024-11-28T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-11-28T17:00:00 | 0 | 2024-11-15T08:00:00 |  |  |  | 0 |  | 2400000.0
253 | 254 | 254 | Assign taping inspection checklist | 0 | 0 | 30.31 | 30.31 | 4 | 500 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | -36960000 | -36480000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-28T08:00:00 | 2024-11-28T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-28T17:00:00 | 0 | 2024-11-28T08:00:00 |  |  |  | 0
254 | 255 | 255 | Install suite entry doors and frames and Interior doors, trims and jambs | 0 | 0 | 30.32 | 30.32 | 4 | 500 | 2024-12-02T08:00:00 | 2024-12-06T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-02T08:00:00 | 2024-12-06T17:00:00 | 2024-12-02T08:00:00 | 2024-12-06T17:00:00 | -36480000 | -35040000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-02T08:00:00 | 2024-12-06T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-12-06T17:00:00 | 0 | 2024-12-02T08:00:00 |  |  |  | 0 |  | 960000.0
255 | 256 | 256 | Gypcrete | 0 | 0 | 31 | 31 | 2 | 500 | 2024-11-25T08:00:00 | 2024-11-26T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-11-25T08:00:00 | 2024-11-26T17:00:00 | 2024-11-25T08:00:00 | 2024-11-26T17:00:00 |  |  | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-25T08:00:00 | 2024-11-26T17:00:00 | PT16H0M0S
256 | 257 | 257 | Assign gypcrete pour checklist | 0 | 0 | 31.1 | 31.1 | 3 | 500 | 2024-11-25T08:00:00 | 2024-11-25T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-25T08:00:00 | 2024-11-25T17:00:00 | 2024-11-25T08:00:00 | 2024-11-25T17:00:00 |  |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-25T08:00:00 | 2024-11-25T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-11-25T17:00:00 | 100 | 2024-11-25T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
257 | 258 | 258 | Pour Gypcrete | 0 | 0 | 31.2 | 31.2 | 3 | 500 | 2024-11-25T08:00:00 | 2024-11-26T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-25T08:00:00 | 2024-11-26T17:00:00 | 2024-11-25T08:00:00 | 2024-11-26T17:00:00 |  |  | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-25T08:00:00 | 2024-11-26T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-11-26T17:00:00 | 100 | 2024-11-25T08:00:00 | PT16H0M0S | PT16H0M0S |  | 100
258 | 259 | 259 | 4.4 Finishing | 0 | 0 | 32 | 32 | 2 | 500 | 2024-08-09T08:00:00 | 2025-05-05T17:00:00 | PT1496H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-08-09T08:00:00 | 2025-05-05T17:00:00 | 2024-08-09T08:00:00 | 2025-05-05T17:00:00 | -14400000 | -1920000 | 3 | PT1496H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-09T08:00:00 | 2025-05-05T17:00:00 | PT1496H0M0S
259 | 260 | 260 | 2nd floor finishing | 0 | 0 | 33 | 33 | 3 | 500 | 2024-12-16T08:00:00 | 2025-02-28T17:00:00 | PT408H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-12-16T08:00:00 | 2025-02-28T17:00:00 | 2024-12-16T08:00:00 | 2025-02-28T17:00:00 | 29280000 | 19200000 | 3 | PT408H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-16T08:00:00 | 2025-02-28T17:00:00 | PT408H0M0S
260 | 261 | 261 | Ceiling texture on 2nd | 0 | 0 | 33.1 | 33.1 | 4 | 500 | 2024-12-16T08:00:00 | 2024-12-17T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-16T08:00:00 | 2024-12-17T17:00:00 | 2024-12-16T08:00:00 | 2024-12-17T17:00:00 | 26880000 | 25920000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-16T08:00:00 | 2024-12-17T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-12-17T17:00:00 | 0 | 2024-12-16T08:00:00 |  |  |  | 0 |  | -1440000.0
261 | 262 | 262 | Prime paint on 2nd | 0 | 0 | 33.2 | 33.2 | 4 | 500 | 2024-12-18T08:00:00 | 2024-12-23T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-18T08:00:00 | 2024-12-23T17:00:00 | 2024-12-18T08:00:00 | 2024-12-23T17:00:00 | 30240000 | 30240000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-18T08:00:00 | 2024-12-23T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-12-23T17:00:00 | 0 | 2024-12-18T08:00:00 |  |  |  | 0 |  | -480000.0
262 | 263 | 263 | 2nd floor - Taper do the rectification of deficiences | 0 | 0 | 33.3 | 33.3 | 4 | 500 | 2024-12-23T08:00:00 | 2024-12-23T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-23T08:00:00 | 2024-12-23T17:00:00 | 2024-12-23T08:00:00 | 2024-12-23T17:00:00 |  |  | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-23T08:00:00 | 2024-12-23T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-12-23T17:00:00 | 0 | 2024-12-23T08:00:00 |  |  |  | 0
263 | 264 | 264 | Install interior doors and case on 2nd | 0 | 0 | 33.4 | 33.4 | 4 | 500 | 2024-12-23T08:00:00 | 2025-01-03T17:00:00 | PT48H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-23T08:00:00 | 2025-01-03T17:00:00 | 2024-12-23T08:00:00 | 2025-01-03T17:00:00 | 26880000 | 27360000 | 3 | PT48H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-23T08:00:00 | 2025-01-03T17:00:00 | PT48H0M0S | PT48H0M0S | 2025-01-03T17:00:00 | 0 | 2024-12-23T08:00:00 |  |  |  | 0 |  | -1920000.0
264 | 265 | 265 | Paint 1st coat of color 2nd floor | 0 | 0 | 33.5 | 33.5 | 4 | 500 | 2024-12-27T08:00:00 | 2025-01-03T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-27T08:00:00 | 2025-01-03T17:00:00 | 2024-12-27T08:00:00 | 2025-01-03T17:00:00 | 22560000 | 21120000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-27T08:00:00 | 2025-01-03T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-01-03T17:00:00 | 0 | 2024-12-27T08:00:00 |  |  |  | 0 |  | -2400000.0
265 | 266 | 266 | Install flooring 2nd floor | 0 | 0 | 33.6 | 33.6 | 4 | 500 | 2025-01-08T08:00:00 | 2025-01-16T17:00:00 | PT56H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-08T08:00:00 | 2025-01-16T17:00:00 | 2025-01-08T08:00:00 | 2025-01-16T17:00:00 | 21600000 | 23040000 | 3 | PT56H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-08T08:00:00 | 2025-01-16T17:00:00 | PT56H0M0S | PT56H0M0S | 2025-01-16T17:00:00 | 0 | 2025-01-08T08:00:00 |  |  |  | 0 |  | 1440000.0
266 | 267 | 267 | Install cabinets 2nd floor | 0 | 0 | 33.7 | 33.7 | 4 | 500 | 2025-01-13T08:00:00 | 2025-01-17T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-13T08:00:00 | 2025-01-17T17:00:00 | 2025-01-13T08:00:00 | 2025-01-17T17:00:00 | 20640000 | 21120000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-13T08:00:00 | 2025-01-17T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-01-17T17:00:00 | 0 | 2025-01-13T08:00:00 |  |  |  | 0
267 | 268 | 268 | 2nd floor counter top measurement for template | 0 | 0 | 33.8 | 33.8 | 4 | 500 | 2025-01-16T08:00:00 | 2025-01-20T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-16T08:00:00 | 2025-01-20T17:00:00 | 2025-01-16T08:00:00 | 2025-01-20T17:00:00 |  |  | 3 | PT24H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-16T08:00:00 | 2025-01-20T17:00:00 | PT24H0M0S | PT24H0M0S | 2025-01-20T17:00:00 | 0 | 2025-01-16T08:00:00 |  |  |  | 0
268 | 269 | 269 | Manufacturing and Install countertops 2nd floor | 0 | 0 | 33.9 | 33.9 | 4 | 500 | 2025-01-21T08:00:00 | 2025-02-07T17:00:00 | PT112H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-21T08:00:00 | 2025-02-07T17:00:00 | 2025-01-21T08:00:00 | 2025-02-07T17:00:00 | 21120000 | 25920000 | 3 | PT112H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-21T08:00:00 | 2025-02-07T17:00:00 | PT112H0M0S | PT112H0M0S | 2025-02-07T17:00:00 | 0 | 2025-01-21T08:00:00 |  |  |  | 0 |  | 4320000.0
269 | 270 | 270 | Install base and hardware 2nd floor | 0 | 0 | 33.10 | 33.10 | 4 | 500 | 2025-01-17T08:00:00 | 2025-01-24T17:00:00 | PT48H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-17T08:00:00 | 2025-01-24T17:00:00 | 2025-01-17T08:00:00 | 2025-01-24T17:00:00 | 17760000 | 16320000 | 3 | PT48H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-17T08:00:00 | 2025-01-24T17:00:00 | PT48H0M0S | PT48H0M0S | 2025-01-24T17:00:00 | 0 | 2025-01-17T08:00:00 |  |  |  | 0 |  | -1920000.0
270 | 271 | 271 | Mechanical finishing 2nd floor | 0 | 0 | 33.11 | 33.11 | 4 | 500 | 2025-02-07T08:00:00 | 2025-02-13T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-07T08:00:00 | 2025-02-13T17:00:00 | 2025-02-07T08:00:00 | 2025-02-13T17:00:00 | 20160000 | 18240000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-07T08:00:00 | 2025-02-13T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-02-13T17:00:00 | 0 | 2025-02-07T08:00:00 |  |  |  | 0 |  | -2400000.0
271 | 272 | 272 | Electrical finishing 2nd floor | 0 | 0 | 33.12 | 33.12 | 4 | 500 | 2025-02-07T08:00:00 | 2025-02-13T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-07T08:00:00 | 2025-02-13T17:00:00 | 2025-02-07T08:00:00 | 2025-02-13T17:00:00 | 20160000 | 18240000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-07T08:00:00 | 2025-02-13T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-02-13T17:00:00 | 0 | 2025-02-07T08:00:00 |  |  |  | 0 |  | -2400000.0
272 | 273 | 273 | Sprinkler finishing 2nd floor | 0 | 0 | 33.13 | 33.13 | 4 | 500 | 2025-02-07T08:00:00 | 2025-02-13T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-07T08:00:00 | 2025-02-13T17:00:00 | 2025-02-07T08:00:00 | 2025-02-13T17:00:00 | 20160000 | 18240000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-07T08:00:00 | 2025-02-13T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-02-13T17:00:00 | 0 | 2025-02-07T08:00:00 |  |  |  | 0 |  | -2400000.0
273 | 274 | 274 | Final coat of paint | 0 | 0 | 33.14 | 33.14 | 4 | 500 | 2025-02-13T08:00:00 | 2025-02-25T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-13T08:00:00 | 2025-02-25T17:00:00 | 2025-02-13T08:00:00 | 2025-02-25T17:00:00 |  |  | 3 | PT72H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-13T08:00:00 | 2025-02-25T17:00:00 | PT72H0M0S | PT72H0M0S | 2025-02-25T17:00:00 | 0 | 2025-02-13T08:00:00 |  |  |  | 0
274 | 275 | 275 | Construction clean 2nd floor | 0 | 0 | 33.15 | 33.15 | 4 | 500 | 2025-02-24T08:00:00 | 2025-02-27T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-24T08:00:00 | 2025-02-27T17:00:00 | 2025-02-24T08:00:00 | 2025-02-27T17:00:00 | 20640000 | 20640000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-24T08:00:00 | 2025-02-27T17:00:00 | PT32H0M0S | PT32H0M0S | 2025-02-27T17:00:00 | 0 | 2025-02-24T08:00:00 |  |  |  | 0 |  | 960000.0
275 | 276 | 276 | Assign Unit Commissioning Inspection list 2nd floor | 0 | 0 | 33.16 | 33.16 | 4 | 500 | 2025-02-27T08:00:00 | 2025-02-27T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-27T08:00:00 | 2025-02-27T17:00:00 | 2025-02-27T08:00:00 | 2025-02-27T17:00:00 | 19680000 | 20160000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-27T08:00:00 | 2025-02-27T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-02-27T17:00:00 | 0 | 2025-02-27T08:00:00 |  |  | Go to | 0
276 | 277 | 277 | Final suite clean | 0 | 0 | 33.17 | 33.17 | 4 | 500 | 2025-02-27T08:00:00 | 2025-02-28T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-27T08:00:00 | 2025-02-28T17:00:00 | 2025-02-27T08:00:00 | 2025-02-28T17:00:00 | 19200000 | 19200000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-27T08:00:00 | 2025-02-28T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-02-28T17:00:00 | 0 | 2025-02-27T08:00:00 |  |  |  | 0
277 | 278 | 278 | 3rd floor finishing | 0 | 0 | 34 | 34 | 3 | 500 | 2024-12-02T08:00:00 | 2025-02-18T17:00:00 | PT424H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-12-02T08:00:00 | 2025-02-18T17:00:00 | 2024-12-02T08:00:00 | 2025-02-18T17:00:00 | 19200000 | 15840000 | 3 | PT424H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-02T08:00:00 | 2025-02-18T17:00:00 | PT424H0M0S
278 | 279 | 279 | Ceiling texture on 3rd | 0 | 0 | 34.1 | 34.1 | 4 | 500 | 2024-12-02T08:00:00 | 2024-12-03T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-02T08:00:00 | 2024-12-03T17:00:00 | 2024-12-02T08:00:00 | 2024-12-03T17:00:00 | 16800000 | 16800000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-02T08:00:00 | 2024-12-03T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-12-03T17:00:00 | 0 | 2024-12-02T08:00:00 |  |  |  | 0 |  | -480000.0
279 | 280 | 280 | Prime paint on 3rd | 0 | 0 | 34.2 | 34.2 | 4 | 500 | 2024-12-05T08:00:00 | 2024-12-10T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-05T08:00:00 | 2024-12-10T17:00:00 | 2024-12-05T08:00:00 | 2024-12-10T17:00:00 | 20640000 | 20640000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-05T08:00:00 | 2024-12-10T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-12-10T17:00:00 | 0 | 2024-12-05T08:00:00 |  |  |  | 0 |  | -480000.0
280 | 281 | 281 | 3rd floor - Taper do the rectification of deficiencies | 0 | 0 | 34.3 | 34.3 | 4 | 500 | 2024-12-10T08:00:00 | 2024-12-10T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-10T08:00:00 | 2024-12-10T17:00:00 | 2024-12-10T08:00:00 | 2024-12-10T17:00:00 |  |  | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-10T08:00:00 | 2024-12-10T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-12-10T17:00:00 | 0 | 2024-12-10T08:00:00 |  |  |  | 0
281 | 282 | 282 | Install interior doors and case on 3rd | 0 | 0 | 34.4 | 34.4 | 4 | 500 | 2024-12-09T08:00:00 | 2024-12-13T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-09T08:00:00 | 2024-12-13T17:00:00 | 2024-12-09T08:00:00 | 2024-12-13T17:00:00 | 17760000 | 15840000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-09T08:00:00 | 2024-12-13T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-12-13T17:00:00 | 0 | 2024-12-09T08:00:00 |  |  |  | 0 |  | -2400000.0
282 | 283 | 283 | Paint 1st coat of color on 3rd | 0 | 0 | 34.5 | 34.5 | 4 | 500 | 2024-12-12T08:00:00 | 2024-12-17T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-12T08:00:00 | 2024-12-17T17:00:00 | 2024-12-12T08:00:00 | 2024-12-17T17:00:00 | 12000000 | 9600000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-12T08:00:00 | 2024-12-17T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-12-17T17:00:00 | 0 | 2024-12-12T08:00:00 |  |  |  | 0 |  | -2400000.0
283 | 284 | 284 | Spray out closet interiors and trim on 3rd | 0 | 0 | 34.6 | 34.6 | 4 | 500 | 2024-12-12T08:00:00 | 2024-12-17T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-12T08:00:00 | 2024-12-17T17:00:00 | 2024-12-12T08:00:00 | 2024-12-17T17:00:00 | 14400000 | 14400000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-12T08:00:00 | 2024-12-17T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-12-17T17:00:00 | 0 | 2024-12-12T08:00:00 |  |  |  | 0 |  | -480000.0
284 | 285 | 285 | Install flooring on 3rd | 0 | 0 | 34.7 | 34.7 | 4 | 500 | 2024-12-17T08:00:00 | 2025-01-07T17:00:00 | PT96H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-17T08:00:00 | 2025-01-07T17:00:00 | 2024-12-17T08:00:00 | 2025-01-07T17:00:00 | 8640000 | 14400000 | 3 | PT96H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-17T08:00:00 | 2025-01-07T17:00:00 | PT96H0M0S | PT96H0M0S | 2025-01-07T17:00:00 | 0 | 2024-12-17T08:00:00 |  |  |  | 0 |  | 3360000.0
285 | 286 | 286 | Install cabinets on 3rd | 0 | 0 | 34.8 | 34.8 | 4 | 500 | 2024-12-18T08:00:00 | 2025-01-10T17:00:00 | PT112H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-18T08:00:00 | 2025-01-10T17:00:00 | 2024-12-18T08:00:00 | 2025-01-10T17:00:00 | 6720000 | 13440000 | 3 | PT112H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-18T08:00:00 | 2025-01-10T17:00:00 | PT112H0M0S | PT112H0M0S | 2025-01-10T17:00:00 | 0 | 2024-12-18T08:00:00 |  |  |  | 0 |  | 4320000.0
286 | 287 | 287 | 3rd floor counter top measurement for template | 0 | 0 | 34.9 | 34.9 | 4 | 500 | 2025-01-08T08:00:00 | 2025-01-10T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-08T08:00:00 | 2025-01-10T17:00:00 | 2025-01-08T08:00:00 | 2025-01-10T17:00:00 |  |  | 3 | PT24H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-08T08:00:00 | 2025-01-10T17:00:00 | PT24H0M0S | PT24H0M0S | 2025-01-10T17:00:00 | 0 | 2025-01-08T08:00:00 |  |  |  | 0
287 | 288 | 288 | Manufacturing and Install countertops on 3rd | 0 | 0 | 34.10 | 34.10 | 4 | 500 | 2025-01-10T08:00:00 | 2025-01-29T17:00:00 | PT112H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-10T08:00:00 | 2025-01-29T17:00:00 | 2025-01-10T08:00:00 | 2025-01-29T17:00:00 | 12480000 | 18240000 | 3 | PT112H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-10T08:00:00 | 2025-01-29T17:00:00 | PT112H0M0S | PT112H0M0S | 2025-01-29T17:00:00 | 0 | 2025-01-10T08:00:00 |  |  |  | 0 |  | 5280000.0
288 | 289 | 289 | Install base and hardware on 3rd | 0 | 0 | 34.11 | 34.11 | 4 | 500 | 2025-01-08T08:00:00 | 2025-01-13T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-08T08:00:00 | 2025-01-13T17:00:00 | 2025-01-08T08:00:00 | 2025-01-13T17:00:00 | 10080000 | 7680000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-08T08:00:00 | 2025-01-13T17:00:00 | PT32H0M0S | PT32H0M0S | 2025-01-13T17:00:00 | 0 | 2025-01-08T08:00:00 |  |  |  | 0 |  | -2880000.0
289 | 290 | 290 | Mechanical finishing on 3rd | 0 | 0 | 34.12 | 34.12 | 4 | 500 | 2025-01-29T08:00:00 | 2025-02-04T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-29T08:00:00 | 2025-02-04T17:00:00 | 2025-01-29T08:00:00 | 2025-02-04T17:00:00 | 17280000 | 15360000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-29T08:00:00 | 2025-02-04T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-02-04T17:00:00 | 0 | 2025-01-29T08:00:00 |  |  |  | 0 |  | -2400000.0
290 | 291 | 291 | Electrical finishing on 3rd | 0 | 0 | 34.13 | 34.13 | 4 | 500 | 2025-01-29T08:00:00 | 2025-02-04T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-29T08:00:00 | 2025-02-04T17:00:00 | 2025-01-29T08:00:00 | 2025-02-04T17:00:00 | 17280000 | 15360000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-29T08:00:00 | 2025-02-04T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-02-04T17:00:00 | 0 | 2025-01-29T08:00:00 |  |  |  | 0 |  | -2400000.0
291 | 292 | 292 | Sprinkler finishing on 3rd | 0 | 0 | 34.14 | 34.14 | 4 | 500 | 2025-01-29T08:00:00 | 2025-02-04T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-29T08:00:00 | 2025-02-04T17:00:00 | 2025-01-29T08:00:00 | 2025-02-04T17:00:00 | 17280000 | 15360000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-29T08:00:00 | 2025-02-04T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-02-04T17:00:00 | 0 | 2025-01-29T08:00:00 |  |  |  | 0 |  | -2400000.0
292 | 293 | 293 | Final coat of paint | 0 | 0 | 34.15 | 34.15 | 4 | 500 | 2025-02-03T08:00:00 | 2025-02-13T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-03T08:00:00 | 2025-02-13T17:00:00 | 2025-02-03T08:00:00 | 2025-02-13T17:00:00 |  |  | 3 | PT72H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-03T08:00:00 | 2025-02-13T17:00:00 | PT72H0M0S | PT72H0M0S | 2025-02-13T17:00:00 | 0 | 2025-02-03T08:00:00 |  |  |  | 0
293 | 294 | 294 | Construction clean on 3rd | 0 | 0 | 34.16 | 34.16 | 4 | 500 | 2025-02-11T08:00:00 | 2025-02-17T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-11T08:00:00 | 2025-02-17T17:00:00 | 2025-02-11T08:00:00 | 2025-02-17T17:00:00 | 16800000 | 17280000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-11T08:00:00 | 2025-02-17T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-02-17T17:00:00 | 0 | 2025-02-11T08:00:00 |  |  |  | 0 |  | 1440000.0
294 | 295 | 295 | Assign Unit Commissioning Inspection list on 3rd | 0 | 0 | 34.17 | 34.17 | 4 | 500 | 2025-02-17T08:00:00 | 2025-02-17T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-17T08:00:00 | 2025-02-17T17:00:00 | 2025-02-17T08:00:00 | 2025-02-17T17:00:00 | 16320000 | 16800000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-17T08:00:00 | 2025-02-17T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-02-17T17:00:00 | 0 | 2025-02-17T08:00:00 |  |  |  | 0
295 | 296 | 296 | Final suite clean on 3rd | 0 | 0 | 34.18 | 34.18 | 4 | 500 | 2025-02-17T08:00:00 | 2025-02-18T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-17T08:00:00 | 2025-02-18T17:00:00 | 2025-02-17T08:00:00 | 2025-02-18T17:00:00 | 15840000 | 15840000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-17T08:00:00 | 2025-02-18T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-02-18T17:00:00 | 0 | 2025-02-17T08:00:00 |  |  |  | 0
296 | 297 | 297 | finishing on 4th | 0 | 0 | 35 | 35 | 3 | 500 | 2024-11-26T08:00:00 | 2025-02-10T17:00:00 | PT408H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-11-26T08:00:00 | 2025-02-10T17:00:00 | 2024-11-26T08:00:00 | 2025-02-10T17:00:00 | -28800000 | -30720000 | 3 | PT408H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-26T08:00:00 | 2025-02-10T17:00:00 | PT408H0M0S
297 | 298 | 298 | Ceiling texture on 4th | 0 | 0 | 35.1 | 35.1 | 4 | 500 | 2024-11-26T08:00:00 | 2024-11-27T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-26T08:00:00 | 2024-11-27T17:00:00 | 2024-11-26T08:00:00 | 2024-11-27T17:00:00 | -31200000 | -32160000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-26T08:00:00 | 2024-11-27T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-11-27T17:00:00 | 0 | 2024-11-26T08:00:00 |  |  |  | 0 |  | -1440000.0
298 | 299 | 299 | Prime paint on 4th | 0 | 0 | 35.2 | 35.2 | 4 | 500 | 2024-11-28T08:00:00 | 2024-12-03T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-11-28T08:00:00 | 2024-12-03T17:00:00 | 2024-11-28T08:00:00 | 2024-12-03T17:00:00 | -27840000 | -27840000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-11-28T08:00:00 | 2024-12-03T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-12-03T17:00:00 | 0 | 2024-11-28T08:00:00 |  |  |  | 0 |  | -480000.0
299 | 300 | 300 | 4th floor - Taper do the rectification of deficiencies | 0 | 0 | 35.3 | 35.3 | 4 | 500 | 2024-12-02T08:00:00 | 2024-12-03T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-02T08:00:00 | 2024-12-03T17:00:00 | 2024-12-02T08:00:00 | 2024-12-03T17:00:00 |  |  | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-02T08:00:00 | 2024-12-03T17:00:00 | PT16H0M0S | PT16H0M0S | 2024-12-03T17:00:00 | 0 | 2024-12-02T08:00:00 |  |  |  | 0
300 | 301 | 301 | Install interior doors and case on 4th | 0 | 0 | 35.4 | 35.4 | 4 | 500 | 2024-12-02T08:00:00 | 2024-12-06T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-02T08:00:00 | 2024-12-06T17:00:00 | 2024-12-02T08:00:00 | 2024-12-06T17:00:00 | -31680000 | -33600000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-02T08:00:00 | 2024-12-06T17:00:00 | PT40H0M0S | PT40H0M0S | 2024-12-06T17:00:00 | 0 | 2024-12-02T08:00:00 |  |  |  | 0 |  | -2400000.0
301 | 302 | 302 | Paint 1st coat of color on 4th | 0 | 0 | 35.5 | 35.5 | 4 | 500 | 2024-12-05T08:00:00 | 2024-12-10T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-05T08:00:00 | 2024-12-10T17:00:00 | 2024-12-05T08:00:00 | 2024-12-10T17:00:00 | -36480000 | -36480000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-05T08:00:00 | 2024-12-10T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-12-10T17:00:00 | 0 | 2024-12-05T08:00:00 |  |  |  | 0 |  | -480000.0
302 | 303 | 303 | Spray out closet interiors and trim on 4th | 0 | 0 | 35.6 | 35.6 | 4 | 500 | 2024-12-05T08:00:00 | 2024-12-10T17:00:00 | PT32H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-05T08:00:00 | 2024-12-10T17:00:00 | 2024-12-05T08:00:00 | 2024-12-10T17:00:00 | -35040000 | -34080000 | 3 | PT32H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-05T08:00:00 | 2024-12-10T17:00:00 | PT32H0M0S | PT32H0M0S | 2024-12-10T17:00:00 | 0 | 2024-12-05T08:00:00 |  |  |  | 0 |  | 480000.0
303 | 304 | 304 | Install flooring on 4th | 0 | 0 | 35.7 | 35.7 | 4 | 500 | 2024-12-09T08:00:00 | 2024-12-16T17:00:00 | PT48H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-09T08:00:00 | 2024-12-16T17:00:00 | 2024-12-09T08:00:00 | 2024-12-16T17:00:00 | -37920000 | -36960000 | 3 | PT48H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-09T08:00:00 | 2024-12-16T17:00:00 | PT48H0M0S | PT48H0M0S | 2024-12-16T17:00:00 | 0 | 2024-12-09T08:00:00 |  |  |  | 0 |  | 480000.0
304 | 305 | 305 | Install cabinets on 4th | 0 | 0 | 35.8 | 35.8 | 4 | 500 | 2024-12-11T08:00:00 | 2024-12-18T17:00:00 | PT48H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-11T08:00:00 | 2024-12-18T17:00:00 | 2024-12-11T08:00:00 | 2024-12-18T17:00:00 | -39360000 | -38400000 | 3 | PT48H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-11T08:00:00 | 2024-12-18T17:00:00 | PT48H0M0S | PT48H0M0S | 2024-12-18T17:00:00 | 0 | 2024-12-11T08:00:00 |  |  |  | 0 |  | 480000.0
305 | 306 | 306 | 4th floor counter top measurements for template | 0 | 0 | 35.9 | 35.9 | 4 | 500 | 2024-12-17T08:00:00 | 2024-12-19T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-17T08:00:00 | 2024-12-19T17:00:00 | 2024-12-17T08:00:00 | 2024-12-19T17:00:00 |  |  | 3 | PT24H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-17T08:00:00 | 2024-12-19T17:00:00 | PT24H0M0S | PT24H0M0S | 2024-12-19T17:00:00 | 0 | 2024-12-17T08:00:00 |  |  |  | 0
306 | 307 | 307 | Install base and hardware on 4th | 0 | 0 | 35.10 | 35.10 | 4 | 500 | 2024-12-20T08:00:00 | 2025-01-03T17:00:00 | PT56H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2024-12-20T08:00:00 | 2025-01-03T17:00:00 | 2024-12-20T08:00:00 | 2025-01-03T17:00:00 | -39840000 | -38880000 | 3 | PT56H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-12-20T08:00:00 | 2025-01-03T17:00:00 | PT56H0M0S | PT56H0M0S | 2025-01-03T17:00:00 | 0 | 2024-12-20T08:00:00 |  |  |  | 0 |  | -1440000.0
307 | 308 | 308 | manufacturing and Install countertops on 4th | 0 | 0 | 35.11 | 35.11 | 4 | 500 | 2025-01-02T08:00:00 | 2025-01-21T17:00:00 | PT112H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-02T08:00:00 | 2025-01-21T17:00:00 | 2025-01-02T08:00:00 | 2025-01-21T17:00:00 | -34080000 | -28320000 | 3 | PT112H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-02T08:00:00 | 2025-01-21T17:00:00 | PT112H0M0S | PT112H0M0S | 2025-01-21T17:00:00 | 0 | 2025-01-02T08:00:00 |  |  |  | 0 |  | 5280000.0
308 | 309 | 309 | Mechanical finishing on 4th | 0 | 0 | 35.12 | 35.12 | 4 | 500 | 2025-01-21T08:00:00 | 2025-01-27T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-21T08:00:00 | 2025-01-27T17:00:00 | 2025-01-21T08:00:00 | 2025-01-27T17:00:00 | -29280000 | -31200000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-21T08:00:00 | 2025-01-27T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-01-27T17:00:00 | 0 | 2025-01-21T08:00:00 |  |  |  | 0 |  | -2400000.0
309 | 310 | 310 | Electrical finishing on 4th | 0 | 0 | 35.13 | 35.13 | 4 | 500 | 2025-01-21T08:00:00 | 2025-01-27T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-21T08:00:00 | 2025-01-27T17:00:00 | 2025-01-21T08:00:00 | 2025-01-27T17:00:00 | -29280000 | -31200000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-21T08:00:00 | 2025-01-27T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-01-27T17:00:00 | 0 | 2025-01-21T08:00:00 |  |  |  | 0 |  | -2400000.0
310 | 311 | 311 | Sprinkler finishing on 4th | 0 | 0 | 35.14 | 35.14 | 4 | 500 | 2025-01-21T08:00:00 | 2025-01-27T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-21T08:00:00 | 2025-01-27T17:00:00 | 2025-01-21T08:00:00 | 2025-01-27T17:00:00 | -29280000 | -31200000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-21T08:00:00 | 2025-01-27T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-01-27T17:00:00 | 0 | 2025-01-21T08:00:00 |  |  |  | 0 |  | -2400000.0
311 | 312 | 312 | Final coat of paint | 0 | 0 | 35.15 | 35.15 | 4 | 500 | 2025-01-24T08:00:00 | 2025-02-05T17:00:00 | PT72H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-24T08:00:00 | 2025-02-05T17:00:00 | 2025-01-24T08:00:00 | 2025-02-05T17:00:00 |  |  | 3 | PT72H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-24T08:00:00 | 2025-02-05T17:00:00 | PT72H0M0S | PT72H0M0S | 2025-02-05T17:00:00 | 0 | 2025-01-24T08:00:00 |  |  |  | 0
312 | 313 | 313 | Construction clean on 4th | 0 | 0 | 35.16 | 35.16 | 4 | 500 | 2025-02-03T08:00:00 | 2025-02-07T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-03T08:00:00 | 2025-02-07T17:00:00 | 2025-02-03T08:00:00 | 2025-02-07T17:00:00 | -29760000 | -29280000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-03T08:00:00 | 2025-02-07T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-02-07T17:00:00 | 0 | 2025-02-03T08:00:00 |  |  |  | 0
313 | 314 | 314 | Assign Unit Commissioning Inspection list on 4th | 0 | 0 | 35.17 | 35.17 | 4 | 500 | 2025-02-07T08:00:00 | 2025-02-07T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-07T08:00:00 | 2025-02-07T17:00:00 | 2025-02-07T08:00:00 | 2025-02-07T17:00:00 | -30240000 | -29760000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-07T08:00:00 | 2025-02-07T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-02-07T17:00:00 | 0 | 2025-02-07T08:00:00 |  |  |  | 0
314 | 315 | 315 | Final suite clean on 4th | 0 | 0 | 35.18 | 35.18 | 4 | 500 | 2025-02-07T08:00:00 | 2025-02-10T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-07T08:00:00 | 2025-02-10T17:00:00 | 2025-02-07T08:00:00 | 2025-02-10T17:00:00 | -30720000 | -30720000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-07T08:00:00 | 2025-02-10T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-02-10T17:00:00 | 0 | 2025-02-07T08:00:00 |  |  |  | 0 |  | -480000.0
315 | 316 | 316 | finishing parkade level 1 | 0 | 0 | 36 | 36 | 3 | 500 | 2025-01-02T08:00:00 | 2025-02-24T17:00:00 | PT304H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2025-01-02T08:00:00 | 2025-02-24T17:00:00 | 2025-01-02T08:00:00 | 2025-02-24T17:00:00 | -18240000 | -12000000 | 3 | PT304H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-02T08:00:00 | 2025-02-24T17:00:00 | PT304H0M0S
316 | 317 | 317 | Ceiling texture on 1 | 0 | 0 | 36.1 | 36.1 | 4 | 500 | 2025-01-02T08:00:00 | 2025-01-03T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-02T08:00:00 | 2025-01-03T17:00:00 | 2025-01-02T08:00:00 | 2025-01-03T17:00:00 | -19680000 | -19680000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-02T08:00:00 | 2025-01-03T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-01-03T17:00:00 | 0 | 2025-01-02T08:00:00 |  |  |  | 0 |  | -480000.0
317 | 318 | 318 | Prime paint on 1 | 0 | 0 | 36.2 | 36.2 | 4 | 500 | 2025-01-03T08:00:00 | 2025-01-07T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-03T08:00:00 | 2025-01-07T17:00:00 | 2025-01-03T08:00:00 | 2025-01-07T17:00:00 | -17760000 | -17280000 | 3 | PT24H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-03T08:00:00 | 2025-01-07T17:00:00 | PT24H0M0S | PT24H0M0S | 2025-01-07T17:00:00 | 0 | 2025-01-03T08:00:00 |  |  |  | 0
318 | 319 | 319 | Parkade - Taper to rectify deficiencies | 0 | 0 | 36.3 | 36.3 | 4 | 500 | 2025-01-07T08:00:00 | 2025-01-07T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-07T08:00:00 | 2025-01-07T17:00:00 | 2025-01-07T08:00:00 | 2025-01-07T17:00:00 |  |  | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-07T08:00:00 | 2025-01-07T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-01-07T17:00:00 | 0 | 2025-01-07T08:00:00 |  |  |  | 0
319 | 320 | 320 | Install interior doors and case on 1 | 0 | 0 | 36.4 | 36.4 | 4 | 500 | 2025-01-08T08:00:00 | 2025-01-09T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-08T08:00:00 | 2025-01-09T17:00:00 | 2025-01-08T08:00:00 | 2025-01-09T17:00:00 | -19200000 | -18720000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-08T08:00:00 | 2025-01-09T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-01-09T17:00:00 | 0 | 2025-01-08T08:00:00 |  |  |  | 0
320 | 321 | 321 | Paint 1rst coat of color on 1 | 0 | 0 | 36.5 | 36.5 | 4 | 500 | 2025-01-10T08:00:00 | 2025-01-16T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-10T08:00:00 | 2025-01-16T17:00:00 | 2025-01-10T08:00:00 | 2025-01-16T17:00:00 | -19680000 | -18240000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-10T08:00:00 | 2025-01-16T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-01-16T17:00:00 | 0 | 2025-01-10T08:00:00 |  |  |  | 0 |  | 960000.0
321 | 322 | 322 | Spray out closet interiors and trim on 1 | 0 | 0 | 36.6 | 36.6 | 4 | 500 | 2025-01-10T08:00:00 | 2025-01-10T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-10T08:00:00 | 2025-01-10T17:00:00 | 2025-01-10T08:00:00 | 2025-01-10T17:00:00 | -19200000 | -18720000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-10T08:00:00 | 2025-01-10T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-01-10T17:00:00 | 0 | 2025-01-10T08:00:00 |  |  |  | 0
322 | 323 | 323 | Install flooring on 1 | 0 | 0 | 36.7 | 36.7 | 4 | 500 | 2025-01-15T08:00:00 | 2025-01-16T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-15T08:00:00 | 2025-01-16T17:00:00 | 2025-01-15T08:00:00 | 2025-01-16T17:00:00 | -19680000 | -19200000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-15T08:00:00 | 2025-01-16T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-01-16T17:00:00 | 0 | 2025-01-15T08:00:00 |  |  |  | 0
323 | 324 | 324 | Install cabinets on 1 | 0 | 0 | 36.8 | 36.8 | 4 | 500 | 2025-01-17T08:00:00 | 2025-01-20T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-17T08:00:00 | 2025-01-20T17:00:00 | 2025-01-17T08:00:00 | 2025-01-20T17:00:00 | -19680000 | -18720000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-17T08:00:00 | 2025-01-20T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-01-20T17:00:00 | 0 | 2025-01-17T08:00:00 |  |  |  | 0 |  | 480000.0
324 | 325 | 325 | Parkade - Measurement for template | 0 | 0 | 36.9 | 36.9 | 4 | 500 | 2025-01-21T08:00:00 | 2025-01-21T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-21T08:00:00 | 2025-01-21T17:00:00 | 2025-01-21T08:00:00 | 2025-01-21T17:00:00 |  |  | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-21T08:00:00 | 2025-01-21T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-01-21T17:00:00 | 0 | 2025-01-21T08:00:00 |  |  |  | 0
325 | 326 | 326 | Install countertops on 1 | 0 | 0 | 36.10 | 36.10 | 4 | 500 | 2025-02-10T08:00:00 | 2025-02-10T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-10T08:00:00 | 2025-02-10T17:00:00 | 2025-02-10T08:00:00 | 2025-02-10T17:00:00 | -12480000 | -12000000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-10T08:00:00 | 2025-02-10T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-02-10T17:00:00 | 0 | 2025-02-10T08:00:00 |  |  |  | 0
326 | 327 | 327 | Mechanical finishing on 1 | 0 | 0 | 36.11 | 36.11 | 4 | 500 | 2025-02-11T08:00:00 | 2025-02-13T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-11T08:00:00 | 2025-02-13T17:00:00 | 2025-02-11T08:00:00 | 2025-02-13T17:00:00 | -12480000 | -12000000 | 3 | PT24H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-11T08:00:00 | 2025-02-13T17:00:00 | PT24H0M0S | PT24H0M0S | 2025-02-13T17:00:00 | 0 | 2025-02-11T08:00:00 |  |  |  | 0
327 | 328 | 328 | Electrical finishing on 1 | 0 | 0 | 36.12 | 36.12 | 4 | 500 | 2025-02-11T08:00:00 | 2025-02-13T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-11T08:00:00 | 2025-02-13T17:00:00 | 2025-02-11T08:00:00 | 2025-02-13T17:00:00 | -12480000 | -12000000 | 3 | PT24H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-11T08:00:00 | 2025-02-13T17:00:00 | PT24H0M0S | PT24H0M0S | 2025-02-13T17:00:00 | 0 | 2025-02-11T08:00:00 |  |  |  | 0
328 | 329 | 329 | Sprinkler finishing on 1 | 0 | 0 | 36.13 | 36.13 | 4 | 500 | 2025-02-11T08:00:00 | 2025-02-13T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-11T08:00:00 | 2025-02-13T17:00:00 | 2025-02-11T08:00:00 | 2025-02-13T17:00:00 | -12480000 | -12000000 | 3 | PT24H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-11T08:00:00 | 2025-02-13T17:00:00 | PT24H0M0S | PT24H0M0S | 2025-02-13T17:00:00 | 0 | 2025-02-11T08:00:00 |  |  |  | 0
329 | 330 | 330 | Construction clean on 1 | 0 | 0 | 36.14 | 36.14 | 4 | 500 | 2025-02-14T08:00:00 | 2025-02-18T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-14T08:00:00 | 2025-02-18T17:00:00 | 2025-02-14T08:00:00 | 2025-02-18T17:00:00 | -12480000 | -12000000 | 3 | PT24H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-14T08:00:00 | 2025-02-18T17:00:00 | PT24H0M0S | PT24H0M0S | 2025-02-18T17:00:00 | 0 | 2025-02-14T08:00:00 |  |  |  | 0
330 | 331 | 331 | Assign Unit Commissioning Inspection list on 1 | 0 | 0 | 36.15 | 36.15 | 4 | 500 | 2025-02-19T08:00:00 | 2025-02-19T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-19T08:00:00 | 2025-02-19T17:00:00 | 2025-02-19T08:00:00 | 2025-02-19T17:00:00 | -12480000 | -12000000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-19T08:00:00 | 2025-02-19T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-02-19T17:00:00 | 0 | 2025-02-19T08:00:00 |  |  |  | 0
331 | 332 | 332 | Final suite clean on 1 | 0 | 0 | 36.16 | 36.16 | 4 | 500 | 2025-02-20T08:00:00 | 2025-02-24T17:00:00 | PT24H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-20T08:00:00 | 2025-02-24T17:00:00 | 2025-02-20T08:00:00 | 2025-02-24T17:00:00 | -12480000 | -12000000 | 3 | PT24H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-20T08:00:00 | 2025-02-24T17:00:00 | PT24H0M0S | PT24H0M0S | 2025-02-24T17:00:00 | 0 | 2025-02-20T08:00:00 |  |  |  | 0
332 | 333 | 333 | Exterior | 0 | 0 | 37 | 37 | 3 | 500 | 2024-08-09T08:00:00 | 2025-05-05T17:00:00 | PT1496H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2024-08-09T08:00:00 | 2025-05-05T17:00:00 | 2024-08-09T08:00:00 | 2025-05-05T17:00:00 | -19200000 | 50400000 | 3 | PT1496H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-09T08:00:00 | 2025-05-05T17:00:00 | PT1496H0M0S
333 | 334 | 334 | Grind all balconys smooth | 0 | 0 | 37.1 | 37.1 | 4 | 500 | 2024-08-09T08:00:00 | 2024-08-22T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-09T08:00:00 | 2024-08-22T17:00:00 | 2024-08-09T08:00:00 | 2024-08-22T17:00:00 | -19200000 | -16320000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-08-09T08:00:00 | 2024-08-22T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-08-22T17:00:00 | 100 | 2024-08-09T08:00:00 | PT80H0M0S | PT80H0M0S |  | 100 |  | 2400000.0
334 | 335 | 335 | Install exterior decking all floors | 0 | 0 | 37.2 | 37.2 | 4 | 500 | 2024-09-03T08:00:00 | 2024-09-16T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-03T08:00:00 | 2024-09-16T17:00:00 | 2024-09-03T08:00:00 | 2024-09-16T17:00:00 | -13440000 | -12960000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-03T08:00:00 | 2024-09-16T17:00:00 | PT80H0M0S | PT80H0M0S | 2024-09-16T17:00:00 | 100 | 2024-09-03T08:00:00 | PT80H0M0S | PT80H0M0S |  | 100
335 | 336 | 336 | Assign post decking install check list | 0 | 0 | 37.3 | 37.3 | 4 | 500 | 2024-09-17T08:00:00 | 2024-09-17T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-17T08:00:00 | 2024-09-17T17:00:00 | 2024-09-17T08:00:00 | 2024-09-17T17:00:00 | -13440000 | -12960000 | 3 |  | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2024-09-17T08:00:00 | 2024-09-17T17:00:00 | PT8H0M0S | PT8H0M0S | 2024-09-17T17:00:00 | 100 | 2024-09-17T08:00:00 | PT8H0M0S | PT8H0M0S |  | 100
336 | 337 | 337 | Install railings on all floors | 0 | 0 | 37.4 | 37.4 | 4 | 500 | 2025-01-20T08:00:00 | 2025-02-06T17:00:00 | PT112H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-01-20T08:00:00 | 2025-02-06T17:00:00 | 2025-01-20T08:00:00 | 2025-02-06T17:00:00 | 29280000 | 31680000 | 3 | PT112H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-01-20T08:00:00 | 2025-02-06T17:00:00 | PT112H0M0S | PT112H0M0S | 2025-02-06T17:00:00 | 0 | 2025-01-20T08:00:00 |  |  |  | 0 |  | 1920000.0
337 | 338 | 338 | Rough grade landscaping | 0 | 0 | 37.5 | 37.5 | 4 | 500 | 2025-04-04T08:00:00 | 2025-04-10T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-04-04T08:00:00 | 2025-04-10T17:00:00 | 2025-04-04T08:00:00 | 2025-04-10T17:00:00 | 50400000 | 50880000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-04-04T08:00:00 | 2025-04-10T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-04-10T17:00:00 | 0 | 2025-04-04T08:00:00 |  |  |  | 0 |  | 480000.0
338 | 339 | 339 | Install underground sprinklers | 0 | 0 | 37.6 | 37.6 | 4 | 500 | 2025-04-11T08:00:00 | 2025-04-17T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-04-11T08:00:00 | 2025-04-17T17:00:00 | 2025-04-11T08:00:00 | 2025-04-17T17:00:00 | 50400000 | 50880000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-04-11T08:00:00 | 2025-04-17T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-04-17T17:00:00 | 0 | 2025-04-11T08:00:00 |  |  |  | 0
339 | 340 | 340 | Install landscaping | 0 | 0 | 37.7 | 37.7 | 4 | 500 | 2025-04-18T08:00:00 | 2025-05-01T17:00:00 | PT80H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-04-18T08:00:00 | 2025-05-01T17:00:00 | 2025-04-18T08:00:00 | 2025-05-01T17:00:00 | 50400000 | 50880000 | 3 | PT80H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-04-18T08:00:00 | 2025-05-01T17:00:00 | PT80H0M0S | PT80H0M0S | 2025-05-01T17:00:00 | 0 | 2025-04-18T08:00:00 |  |  |  | 0
340 | 341 | 341 | Commision landscaping | 0 | 0 | 37.8 | 37.8 | 4 | 500 | 2025-05-02T08:00:00 | 2025-05-05T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-05-02T08:00:00 | 2025-05-05T17:00:00 | 2025-05-02T08:00:00 | 2025-05-05T17:00:00 | 50400000 | 50880000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-05-02T08:00:00 | 2025-05-05T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-05-05T17:00:00 | 0 | 2025-05-02T08:00:00 |  |  |  | 0
341 | 342 | 342 | Install building signage | 0 | 0 | 37.9 | 37.9 | 4 | 500 | 2025-02-28T08:00:00 | 2025-02-28T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-28T08:00:00 | 2025-02-28T17:00:00 | 2025-02-28T08:00:00 | 2025-02-28T17:00:00 | 27840000 | 28320000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-28T08:00:00 | 2025-02-28T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-02-28T17:00:00 | 0 | 2025-02-28T08:00:00 |  |  |  | 0
342 | 343 | 343 | Assign post landscaping checklist | 0 | 0 | 37.10 | 37.10 | 4 | 500 | 2025-05-02T08:00:00 | 2025-05-02T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-05-02T08:00:00 | 2025-05-02T17:00:00 | 2025-05-02T08:00:00 | 2025-05-02T17:00:00 |  |  | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-05-02T08:00:00 | 2025-05-02T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-05-02T17:00:00 | 0 | 2025-05-02T08:00:00 |  |  |  | 0
343 | 344 | 344 | Final commissioning and deficiency | 0 | 0 | 38 | 38 | 3 | 500 | 2025-02-14T08:00:00 | 2025-03-03T17:00:00 | PT96H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2025-02-14T08:00:00 | 2025-03-03T17:00:00 | 2025-02-14T08:00:00 | 2025-03-03T17:00:00 | -12480000 | -13440000 | 3 | PT96H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-14T08:00:00 | 2025-03-03T17:00:00 | PT96H0M0S
344 | 345 | 345 | Fire alarm verification | 0 | 0 | 38.1 | 38.1 | 4 | 500 | 2025-02-14T08:00:00 | 2025-02-17T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-14T08:00:00 | 2025-02-17T17:00:00 | 2025-02-14T08:00:00 | 2025-02-17T17:00:00 | -12480000 | -12000000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-14T08:00:00 | 2025-02-17T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-02-17T17:00:00 | 0 | 2025-02-14T08:00:00 |  |  |  | 0
345 | 346 | 346 | Contact Canada Post to get the address's created | 0 | 0 | 38.2 | 38.2 | 4 | 500 | 2025-02-14T08:00:00 | 2025-02-14T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-14T08:00:00 | 2025-02-14T17:00:00 | 2025-02-14T08:00:00 | 2025-02-14T17:00:00 | -12480000 | -12000000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-14T08:00:00 | 2025-02-14T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-02-14T17:00:00 | 0 | 2025-02-14T08:00:00 |  |  |  | 0
346 | 347 | 347 | Enginering walk throughs | 0 | 0 | 38.3 | 38.3 | 4 | 500 | 2025-02-19T08:00:00 | 2025-02-20T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-19T08:00:00 | 2025-02-20T17:00:00 | 2025-02-19T08:00:00 | 2025-02-20T17:00:00 | -11040000 | -11520000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-19T08:00:00 | 2025-02-20T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-02-20T17:00:00 | 0 | 2025-02-19T08:00:00 |  |  |  | 0 |  | -960000.0
347 | 348 | 348 | Organize 3rd party building exterior review, including roof, siding and flashings | 0 | 0 | 38.4 | 38.4 | 4 | 500 | 2025-02-19T08:00:00 | 2025-02-19T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-19T08:00:00 | 2025-02-19T17:00:00 | 2025-02-19T08:00:00 | 2025-02-19T17:00:00 | -11040000 | -10560000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-19T08:00:00 | 2025-02-19T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-02-19T17:00:00 | 0 | 2025-02-19T08:00:00 |  |  |  | 0
348 | 349 | 349 | Sprinkler testing | 0 | 0 | 38.5 | 38.5 | 4 | 500 | 2025-02-14T08:00:00 | 2025-02-17T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-14T08:00:00 | 2025-02-17T17:00:00 | 2025-02-14T08:00:00 | 2025-02-17T17:00:00 | -12480000 | -12000000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-14T08:00:00 | 2025-02-17T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-02-17T17:00:00 | 0 | 2025-02-14T08:00:00 |  |  |  | 0
349 | 350 | 350 | Archetectural walk throughs | 0 | 0 | 38.6 | 38.6 | 4 | 500 | 2025-02-19T08:00:00 | 2025-02-20T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-19T08:00:00 | 2025-02-20T17:00:00 | 2025-02-19T08:00:00 | 2025-02-20T17:00:00 | -11040000 | -10560000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-19T08:00:00 | 2025-02-20T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-02-20T17:00:00 | 0 | 2025-02-19T08:00:00 |  |  |  | 0
350 | 351 | 351 | Building inspector walk throughs | 0 | 0 | 38.7 | 38.7 | 4 | 500 | 2025-02-21T08:00:00 | 2025-02-24T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-21T08:00:00 | 2025-02-24T17:00:00 | 2025-02-21T08:00:00 | 2025-02-24T17:00:00 | -10080000 | -9600000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-21T08:00:00 | 2025-02-24T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-02-24T17:00:00 | 0 | 2025-02-21T08:00:00 |  |  |  | 0
351 | 352 | 352 | Elevator commissioning | 0 | 0 | 38.8 | 38.8 | 4 | 500 | 2025-02-14T08:00:00 | 2025-02-17T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-14T08:00:00 | 2025-02-17T17:00:00 | 2025-02-14T08:00:00 | 2025-02-17T17:00:00 | -12480000 | -12000000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-14T08:00:00 | 2025-02-17T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-02-17T17:00:00 | 0 | 2025-02-14T08:00:00 |  |  |  | 0
352 | 353 | 353 | Prepare occupancy paperwork | 0 | 0 | 38.9 | 38.9 | 4 | 500 | 2025-02-25T08:00:00 | 2025-02-26T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-25T08:00:00 | 2025-02-26T17:00:00 | 2025-02-25T08:00:00 | 2025-02-26T17:00:00 | -9120000 | -11040000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-25T08:00:00 | 2025-02-26T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-02-26T17:00:00 | 0 | 2025-02-25T08:00:00 |  |  |  | 0 |  | -2400000.0
353 | 354 | 354 | Receive occupancy | 0 | 0 | 38.10 | 38.10 | 4 | 500 | 2025-02-27T08:00:00 | 2025-02-28T17:00:00 | PT16H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-02-27T08:00:00 | 2025-02-28T17:00:00 | 2025-02-27T08:00:00 | 2025-02-28T17:00:00 | -11520000 | -13440000 | 3 | PT16H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-02-27T08:00:00 | 2025-02-28T17:00:00 | PT16H0M0S | PT16H0M0S | 2025-02-28T17:00:00 | 0 | 2025-02-27T08:00:00 |  |  |  | 0 |  | -2400000.0
354 | 355 | 355 | Move in dates confirmed | 0 | 0 | 38.11 | 38.11 | 4 | 500 | 2025-03-03T08:00:00 | 2025-03-03T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-03T08:00:00 | 2025-03-03T17:00:00 | 2025-03-03T08:00:00 | 2025-03-03T17:00:00 | -13920000 | -13440000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-03T08:00:00 | 2025-03-03T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-03-03T17:00:00 | 0 | 2025-03-03T08:00:00 |  |  |  | 0
355 | 356 | 356 | Assign Final Building Checklist | 0 | 0 | 38.12 | 38.12 | 4 | 500 | 2025-03-03T08:00:00 | 2025-03-03T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-03T08:00:00 | 2025-03-03T17:00:00 | 2025-03-03T08:00:00 | 2025-03-03T17:00:00 | -13920000 | -13440000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-03T08:00:00 | 2025-03-03T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-03-03T17:00:00 | 0 | 2025-03-03T08:00:00 |  |  |  | 0
356 | 357 | 357 | 5.0 Sales, Occupancy, Closings | 0 | 0 | 39 | 39 | 2 | 500 | 2025-03-03T08:00:00 | 2025-05-01T17:00:00 | PT352H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2025-03-03T08:00:00 | 2025-05-01T17:00:00 | 2025-03-03T08:00:00 | 2025-05-01T17:00:00 | 57600000 | -960000 | 3 | PT352H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-03T08:00:00 | 2025-05-01T17:00:00 | PT352H0M0S
357 | 358 | 358 | Pre sale move in dates confirmed | 0 | 0 | 39.1 | 39.1 | 3 | 500 | 2025-03-03T08:00:00 | 2025-03-03T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-03T08:00:00 | 2025-03-03T17:00:00 | 2025-03-03T08:00:00 | 2025-03-03T17:00:00 | 57600000 | 58080000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-03T08:00:00 | 2025-03-03T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-03-03T17:00:00 | 0 | 2025-03-03T08:00:00 |  |  |  | 0
358 | 359 | 359 | Finalize home owner extras | 0 | 0 | 39.2 | 39.2 | 3 | 500 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | 57600000 | 58080000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-03-10T17:00:00 | 0 | 2025-03-04T08:00:00 |  |  |  | 0
359 | 360 | 360 | Load home owners into copper | 0 | 0 | 39.3 | 39.3 | 3 | 500 | 2025-03-04T08:00:00 | 2025-03-04T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-04T08:00:00 | 2025-03-04T17:00:00 | 2025-03-04T08:00:00 | 2025-03-04T17:00:00 | 57600000 | 58080000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-04T08:00:00 | 2025-03-04T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-03-04T17:00:00 | 0 | 2025-03-04T08:00:00 |  |  |  | 0
360 | 361 | 361 | Move in binders created | 0 | 0 | 39.4 | 39.4 | 3 | 500 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | 57600000 | 58080000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-03-10T17:00:00 | 0 | 2025-03-04T08:00:00 |  |  |  | 0
361 | 362 | 362 | Update home owner permissions in Construction online | 0 | 0 | 39.5 | 39.5 | 3 | 500 | 2025-03-04T08:00:00 | 2025-03-04T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-04T08:00:00 | 2025-03-04T17:00:00 | 2025-03-04T08:00:00 | 2025-03-04T17:00:00 | 57600000 | 58080000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-04T08:00:00 | 2025-03-04T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-03-04T17:00:00 | 0 | 2025-03-04T08:00:00 |  |  |  | 0
362 | 363 | 363 | Unit Commissioning Inspection list | 0 | 0 | 39.6 | 39.6 | 3 | 500 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | 57600000 | 58080000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-03-10T17:00:00 | 0 | 2025-03-04T08:00:00 |  |  |  | 0
363 | 364 | 364 | Unit Commissioning deficiency clean up confirmed | 0 | 0 | 39.7 | 39.7 | 3 | 500 | 2025-03-11T08:00:00 | 2025-03-17T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-11T08:00:00 | 2025-03-17T17:00:00 | 2025-03-11T08:00:00 | 2025-03-17T17:00:00 | 57600000 | 58080000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-11T08:00:00 | 2025-03-17T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-03-17T17:00:00 | 0 | 2025-03-11T08:00:00 |  |  |  | 0
364 | 365 | 365 | Building close out check list | 0 | 0 | 39.8 | 39.8 | 3 | 500 | 2025-03-04T08:00:00 | 2025-03-04T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-04T08:00:00 | 2025-03-04T17:00:00 | 2025-03-04T08:00:00 | 2025-03-04T17:00:00 | 57600000 | 58080000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-04T08:00:00 | 2025-03-04T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-03-04T17:00:00 | 0 | 2025-03-04T08:00:00 |  |  |  | 0
365 | 366 | 366 | Building close out cleanup deficiencies confirmed | 0 | 0 | 39.9 | 39.9 | 3 | 500 | 2025-03-05T08:00:00 | 2025-03-11T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-05T08:00:00 | 2025-03-11T17:00:00 | 2025-03-05T08:00:00 | 2025-03-11T17:00:00 | 57600000 | 58080000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-05T08:00:00 | 2025-03-11T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-03-11T17:00:00 | 0 | 2025-03-05T08:00:00 |  |  |  | 0
366 | 367 | 367 | Building handover (PM to SM) checklist | 0 | 0 | 39.10 | 39.10 | 3 | 500 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | 57600000 | 58080000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-03-10T17:00:00 | 0 | 2025-03-04T08:00:00 |  |  |  | 0
367 | 368 | 368 | De mobilization (checklist) | 0 | 0 | 39.11 | 39.11 | 3 | 500 | 2025-03-05T08:00:00 | 2025-03-11T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-05T08:00:00 | 2025-03-11T17:00:00 | 2025-03-05T08:00:00 | 2025-03-11T17:00:00 | 57600000 | 58080000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-05T08:00:00 | 2025-03-11T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-03-11T17:00:00 | 0 | 2025-03-05T08:00:00 |  |  |  | 0
368 | 369 | 369 | Keys and gift cards and welcome package created | 0 | 0 | 39.12 | 39.12 | 3 | 500 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | 57600000 | 58080000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-04T08:00:00 | 2025-03-10T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-03-10T17:00:00 | 0 | 2025-03-04T08:00:00 |  |  |  | 0
369 | 370 | 370 | Home owner walk through and punch list | 0 | 0 | 39.13 | 39.13 | 3 | 500 | 2025-03-11T08:00:00 | 2025-03-11T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-11T08:00:00 | 2025-03-11T17:00:00 | 2025-03-11T08:00:00 | 2025-03-11T17:00:00 | 57600000 | 58080000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-11T08:00:00 | 2025-03-11T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-03-11T17:00:00 | 0 | 2025-03-11T08:00:00 |  |  |  | 0
370 | 371 | 371 | Home owner walk through punch list clean up | 0 | 0 | 39.14 | 39.14 | 3 | 500 | 2025-03-12T08:00:00 | 2025-03-18T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-12T08:00:00 | 2025-03-18T17:00:00 | 2025-03-12T08:00:00 | 2025-03-18T17:00:00 | 57600000 | 58080000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-12T08:00:00 | 2025-03-18T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-03-18T17:00:00 | 0 | 2025-03-12T08:00:00 |  |  |  | 0
371 | 372 | 372 | New move ins and warranty through service manager | 0 | 0 | 39.15 | 39.15 | 3 | 500 | 2025-03-04T08:00:00 | 2025-05-01T17:00:00 | PT344H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-04T08:00:00 | 2025-05-01T17:00:00 | 2025-03-04T08:00:00 | 2025-05-01T17:00:00 | 57600000 | 49920000 | 3 | PT344H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-04T08:00:00 | 2025-05-01T17:00:00 | PT344H0M0S | PT344H0M0S | 2025-05-01T17:00:00 | 0 | 2025-03-04T08:00:00 |  |  |  | 0 |  | -7680000.0
372 | 373 | 373 | Send out contractor surveys | 0 | 0 | 39.16 | 39.16 | 3 | 500 | 2025-03-05T08:00:00 | 2025-03-05T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-05T08:00:00 | 2025-03-05T17:00:00 | 2025-03-05T08:00:00 | 2025-03-05T17:00:00 | -18240000 | -17760000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-05T08:00:00 | 2025-03-05T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-03-05T17:00:00 | 0 | 2025-03-05T08:00:00 |  |  |  | 0
373 | 374 | 374 | Schedule 1 on 1 contractor review meetings | 0 | 0 | 39.17 | 39.17 | 3 | 500 | 2025-03-06T08:00:00 | 2025-03-12T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-06T08:00:00 | 2025-03-12T17:00:00 | 2025-03-06T08:00:00 | 2025-03-12T17:00:00 | -18240000 | -17760000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-06T08:00:00 | 2025-03-12T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-03-12T17:00:00 | 0 | 2025-03-06T08:00:00 |  |  |  | 0
374 | 375 | 375 | Schedule contractor group meeting to review survey results | 0 | 0 | 39.18 | 39.18 | 3 | 500 | 2025-03-06T08:00:00 | 2025-03-12T17:00:00 | PT40H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-06T08:00:00 | 2025-03-12T17:00:00 | 2025-03-06T08:00:00 | 2025-03-12T17:00:00 | -18240000 | -17760000 | 3 | PT40H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-06T08:00:00 | 2025-03-12T17:00:00 | PT40H0M0S | PT40H0M0S | 2025-03-12T17:00:00 | 0 | 2025-03-06T08:00:00 |  |  |  | 0
375 | 376 | 376 | Project post mordem internal | 0 | 0 | 39.19 | 39.19 | 3 | 500 | 2025-03-13T08:00:00 | 2025-03-13T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-13T08:00:00 | 2025-03-13T17:00:00 | 2025-03-13T08:00:00 | 2025-03-13T17:00:00 | -18240000 | -17760000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-13T08:00:00 | 2025-03-13T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-03-13T17:00:00 | 0 | 2025-03-13T08:00:00 |  |  |  | 0
376 | 377 | 377 | Move info to Dev co work flow 1.0, 2.0, 6.0 | 0 | 0 | 39.20 | 39.20 | 3 | 500 | 2025-03-18T08:00:00 | 2025-03-18T17:00:00 | PT8H0M0S | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2025-03-18T08:00:00 | 2025-03-18T17:00:00 | 2025-03-18T08:00:00 | 2025-03-18T17:00:00 | 33600000 | 34080000 | 3 | PT8H0M0S | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2025-03-18T08:00:00 | 2025-03-18T17:00:00 | PT8H0M0S | PT8H0M0S | 2025-03-18T17:00:00 | 0 | 2025-03-18T08:00:00 |  |  |  | 0