## Sheet1
Phase | Area | Zone | Trade | Activity Name | Color | Activity Code | Start | Finish
Yardwork | COLO 2 | South | Gurtz Electric | Wire pulling and termination for TCP/MSB - Colo 2 - South | #FFFDA5 | EE35 | 2024-12-27 | 2025-01-31
Yardwork | COLO 2 | South | Ralph Simpson & Crown Core | Install screen wall - Colo 2 - South | #D9D9D9 | RC1 | 2024-11-11 | 2025-03-07
Yardwork | COLO 2 | North | Ralph Simpson & Crown Core | Install screen wall - Colo 2 - North | #D9D9D9 | RC1 | 2025-02-10 | 2025-03-07
Yardwork | COLO 5 | East | Ralph Simpson & Crown Core | Install screen wall - Colo 5 - East | #D9D9D9 | RC1 | 2024-11-11 | 2025-01-31
Yardwork | COLO 5 | West | Gurtz Electric | Install Generator Muffler - Colo 5 - West | #FFFDA5 | EE34 | 2025-01-17 | 2025-01-21
Yardwork | COLO 5 | West | Ralph Simpson & Crown Core | Install screen wall - Colo 5 - West | #D9D9D9 | RC1 | 2025-02-03 | 2025-02-28
Yardwork | COLO 3 | South | Gurtz Electric | Pull & Terminate Underground Cables (UMS to UPM to XMFR) | #FFFDA5 | EE46 | 2025-01-17 | 2025-02-06
Yardwork | COLO 3 | South | Ralph Simpson & Crown Core | Install screen wall - Colo 3 - South | #D9D9D9 | RC1 | 2024-12-30 | 2025-02-28
Yardwork | COLO 3 | North | Gurtz Electric | Wire pulling and termination for TCP/MSB - Colo 3 - North | #FFFDA5 | EE35 | 2024-12-27 | 2025-01-31
Yardwork | COLO 3 | North | Gurtz Electric | Pull & Terminate Underground Cables (UMS to UPM to XMFR) | #FFFDA5 | EE46 | 2025-01-17 | 2025-02-13
Yardwork | COLO 3 | North | Ralph Simpson & Crown Core | Install screen wall - Colo 3 - North | #D9D9D9 | RC1 | 2024-12-30 | 2025-02-28
Yardwork | COLO 4 | South | Gurtz Electric | Wire pulling and termination for TCP/MSB - Colo 4 - South | #FFFDA5 | EE46 | 2024-12-27 | 2025-01-31
Yardwork | COLO 4 | South | Gurtz Electric | Pull & Terminate Underground Cables (UMS to UPM to XMFR) | #FFFDA5 | EE46 | 2025-02-14 | 2025-03-13
Yardwork | COLO 4 | South | Ralph Simpson & Crown Core | Install screen wall - Colo 4 - South | #D9D9D9 | RC1 | 2025-03-03 | 2025-03-28
Yardwork | COLO 4 | North | Gurtz Electric | Wire pulling and termination for TCP/MSB - Colo 4 - North | #FFFDA5 | EE35 | 2024-12-27 | 2025-01-31
Yardwork | COLO 4 | North | Gurtz Electric | Pull & Terminate Underground Cables (UMS to UPM to XMFR) | #FFFDA5 | EE46 | 2025-02-14 | 2025-03-13
Yardwork | COLO 4 | North | Ralph Simpson & Crown Core | Install screen wall - Colo 4 - North | #D9D9D9 | RC1 | 2025-03-03 | 2025-03-28
CX Level 2 | Site | Site | Gurtz Electric | L2 UTS / UTSR - Site | #FFFDA5 | EE47 | 2025-02-03 | 2025-02-10
CX Level 2 | COLO 2 | COLO 2 | Gurtz Electric | L2 XFMR - COLO2 | #FFFDA5 | EE48 | 2025-02-11 | 2025-03-10
CX Level 2 | COLO 2 | COLO 2 | Gurtz Electric | L2 GEN - COLO2 | #FFFDA5 | EE49 | 2025-02-11 | 2025-03-10
CX Level 2 | COLO 2 | COLO 2 | Gurtz Electric | L2 UPM - COLO2 | #FFFDA5 | EE50 | 2025-02-12 | 2025-03-11
CX Level 2 | COLO 5 | COLO 5 | Gurtz Electric | L2 UMS 01 - COLO 5 | #FFFDA5 | EE51 | 2025-02-11 | 2025-02-17
CX Level 2 | COLO 5 | COLO 5 | Gurtz Electric | L2 UMS 02 - COLO 5 | #FFFDA5 | EE52 | 2025-02-18 | 2025-02-24
CX Level 2 | COLO 5 | COLO 5 | Gurtz Electric | L2 URS 01 - COLO 5 | #FFFDA5 | EE53 | 2025-03-11 | 2025-03-17
CX Level 2 | COLO 5 | COLO 5 | Gurtz Electric | L2 XFMR - COLO5 | #FFFDA5 | EE48 | 2025-03-11 | 2025-04-07
CX Level 2 | COLO 5 | COLO 5 | Gurtz Electric | L2 GEN - COLO5 | #FFFDA5 | EE49 | 2025-03-11 | 2025-04-07
CX Level 2 | COLO 5 | COLO 5 | Gurtz Electric | L2 UPM - COLO5 (UPM ROJ Driving) | #FFFDA5 | EE50 | 2025-06-25 | 2025-07-23
CX Level 2 | COLO 3 | COLO 3 | Gurtz Electric | L2 UMS 03 - COLO 3 | #FFFDA5 | EE54 | 2025-02-25 | 2025-03-03
CX Level 2 | COLO 3 | COLO 3 | Gurtz Electric | L2 UMS 04 - COLO 3 | #FFFDA5 | EE55 | 2025-03-04 | 2025-03-10
CX Level 2 | COLO 3 | COLO 3 | Gurtz Electric | L2 XFMR - COLO3 | #FFFDA5 | EE48 | 2025-04-08 | 2025-05-05
CX Level 2 | COLO 3 | COLO 3 | Gurtz Electric | L2 GEN - COLO3 | #FFFDA5 | EE49 | 2025-04-08 | 2025-05-05
CX Level 2 | COLO 3 | COLO 3 | Gurtz Electric | L2 UPM - COLO3 (UPM ROJ Driving) | #FFFDA5 | EE50 | 2025-07-07 | 2025-08-01
CX Level 2 | COLO 4 | COLO 4 | Gurtz Electric | L2 XFMR - COLO4 | #FFFDA5 | EE48 | 2025-05-06 | 2025-06-03
CX Level 2 | COLO 4 | COLO 4 | Gurtz Electric | L2 GEN - COLO4 | #FFFDA5 | EE49 | 2025-05-06 | 2025-06-03
CX Level 2 | COLO 4 | COLO 4 | Gurtz Electric | L2 UPM - COLO4 (UPM ROJ Driving) | #FFFDA5 | EE50 | 2025-07-16 | 2025-08-12
CX Level 3 | Site | Site | Gurtz Electric | L3 UTS / UTSR - Site | #FFFDA5 | EE47 | 2025-03-14 | 2025-03-20
CX Level 3 | COLO 2 | Cell 1 | Gurtz Electric | L3 GEN - Colo 2 Cell 1 | #FFFDA5 | EE49 | 2025-03-14 | 2025-03-20
CX Level 3 | COLO 2 | Cell 2 | Gurtz Electric | L3 GEN - Colo 2 Cell 2 | #FFFDA5 | EE49 | 2025-03-14 | 2025-03-20
CX Level 3 | COLO 2 | Cell 3 | Gurtz Electric | L3 GEN - Colo 2 Cell 3 | #FFFDA5 | EE49 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 2 | All | Gurtz Electric | EPMS/BAS Turn-Up | #FFFDA5 | EE56 | 2025-03-28 | 2025-03-28
CX Level 3 | COLO 2 | Cell 1 | Gurtz Electric | L3 UPM - Colo 2 Cell 1 | #FFFDA5 | EE50 | 2025-03-28 | 2025-04-03
CX Level 3 | COLO 2 | Cell 4 | Gurtz Electric | L3 GEN - Colo 2 Cell 4 | #FFFDA5 | EE49 | 2025-03-28 | 2025-04-03
CX Level 3 | COLO 2 | Cell 2 | Gurtz Electric | L3 UPM - Colo 2 Cell 2 | #FFFDA5 | EE50 | 2025-03-28 | 2025-04-03
CX Level 3 | COLO 2 | Cell 3 | Gurtz Electric | L3 UPM - Colo 2 Cell 3 | #FFFDA5 | EE50 | 2025-03-28 | 2025-04-03
CX Level 3 | COLO 2 | Cell 4 | Gurtz Electric | L3 UPM - Colo 2 Cell 4 | #FFFDA5 | EE50 | 2025-03-28 | 2025-04-03
CX Level 3 | COLO 2 | Cell 1 | Gurtz Electric | L3 XFMR - Colo 2 Cell 1 | #FFFDA5 | EE48 | 2025-04-04 | 2025-04-10
CX Level 3 | COLO 2 | Cell 2 | Gurtz Electric | L3 XFMR - Colo 2 Cell 2 | #FFFDA5 | EE48 | 2025-04-04 | 2025-04-10
CX Level 3 | COLO 2 | Cell 3 | Gurtz Electric | L3 XFMR - Colo 2 Cell 3 | #FFFDA5 | EE48 | 2025-04-04 | 2025-04-10
CX Level 3 | COLO 2 | Cell 4 | Gurtz Electric | L3 XFMR - Colo 2 Cell 4 | #FFFDA5 | EE48 | 2025-04-04 | 2025-04-10
CX Level 3 | COLO 5 | All | Gurtz Electric | L3 URS 01 - COLO 5 | #FFFDA5 | EE53 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 5 | All | Gurtz Electric | L3 UMS 01 - COLO 5 | #FFFDA5 | EE51 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 5 | All | Gurtz Electric | L3 UMS 02 - COLO 5 | #FFFDA5 | EE52 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 5 | All | Gurtz Electric | EPMS/BAS Turn-Up | #FFFDA5 | EE56 | 2025-04-11 | 2025-04-11
CX Level 3 | COLO 5 | Cell 1 | Gurtz Electric | L3 GEN - Cell 1 | #FFFDA5 | EE49 | 2025-04-08 | 2025-04-14
CX Level 3 | COLO 5 | Cell 2 | Gurtz Electric | L3 GEN - Cell 2 | #FFFDA5 | EE49 | 2025-04-15 | 2025-04-21
CX Level 3 | COLO 5 | Cell 3 | Gurtz Electric | L3 GEN - Cell 3 | #FFFDA5 | EE49 | 2025-04-22 | 2025-04-28
CX Level 3 | COLO 5 | Cell 4 | Gurtz Electric | L3 GEN - Cell 4 | #FFFDA5 | EE49 | 2025-04-29 | 2025-05-05
CX Level 3 | COLO 5 | Cell 1 | Gurtz Electric | L3 UPM - Cell 1 | #FFFDA5 | EE50 | 2025-07-24 | 2025-07-30
CX Level 3 | COLO 5 | Cell 2 | Gurtz Electric | L3 UPM - Cell 2 | #FFFDA5 | EE50 | 2025-07-24 | 2025-07-30
CX Level 3 | COLO 5 | Cell 1 | Gurtz Electric | L3 XFMR - Cell 1 | #FFFDA5 | EE48 | 2025-07-31 | 2025-08-06
CX Level 3 | COLO 5 | Cell 3 | Gurtz Electric | L3 UPM - Cell 3 | #FFFDA5 | EE50 | 2025-07-31 | 2025-08-06
CX Level 3 | COLO 5 | Cell 4 | Gurtz Electric | L3 UPM - Cell 4 | #FFFDA5 | EE50 | 2025-07-31 | 2025-08-06
CX Level 3 | COLO 5 | Cell 2 | Gurtz Electric | L3 XFMR - Cell 2 | #FFFDA5 | EE48 | 2025-07-31 | 2025-08-06
CX Level 3 | COLO 5 | Cell 3 | Gurtz Electric | L3 XFMR - Cell 3 | #FFFDA5 | EE48 | 2025-08-07 | 2025-08-13
CX Level 3 | COLO 5 | Cell 4 | Gurtz Electric | L3 XFMR - Cell 4 | #FFFDA5 | EE48 | 2025-08-07 | 2025-08-13
CX Level 3 | COLO 3 | All | Gurtz Electric | L3 UMS 04 - COLO 3 | #FFFDA5 | EE55 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 3 | All | Gurtz Electric | L3 UMS 03 - COLO 3 | #FFFDA5 | EE54 | 2025-03-21 | 2025-03-27
CX Level 3 | COLO 3 | All | Gurtz Electric | EPMS/BAS Turn-Up | #FFFDA5 | EE56 | 2025-04-11 | 2025-04-11
CX Level 3 | COLO 3 | Cell 2 | Gurtz Electric | L3 GEN - Cell 2 | #FFFDA5 | EE49 | 2025-05-06 | 2025-05-12
CX Level 3 | COLO 3 | Cell 3 | Gurtz Electric | L3 GEN - Cell 3 | #FFFDA5 | EE49 | 2025-05-06 | 2025-05-12
CX Level 3 | COLO 3 | Cell 4 | Gurtz Electric | L3 GEN - Cell 4 | #FFFDA5 | EE49 | 2025-05-06 | 2025-05-12
CX Level 3 | COLO 3 | Cell 1 | Gurtz Electric | L3 GEN - Cell 1 | #FFFDA5 | EE49 | 2025-05-07 | 2025-05-13
CX Level 3 | COLO 3 | Cell 1 | Gurtz Electric | L3 UPM - Cell 1 | #FFFDA5 | EE50 | 2025-08-04 | 2025-08-08
CX Level 3 | COLO 3 | Cell 2 | Gurtz Electric | L3 UPM - Cell 2 | #FFFDA5 | EE50 | 2025-08-04 | 2025-08-08
CX Level 3 | COLO 3 | Cell 1 | Gurtz Electric | L3 XFMR - Cell 1 | #FFFDA5 | EE48 | 2025-08-11 | 2025-08-15
CX Level 3 | COLO 3 | Cell 3 | Gurtz Electric | L3 UPM - Cell 3 | #FFFDA5 | EE50 | 2025-08-11 | 2025-08-15
CX Level 3 | COLO 3 | Cell 4 | Gurtz Electric | L3 UPM - Cell 4 | #FFFDA5 | EE50 | 2025-08-11 | 2025-08-15
CX Level 3 | COLO 3 | Cell 2 | Gurtz Electric | L3 XFMR - Cell 2 | #FFFDA5 | EE48 | 2025-08-11 | 2025-08-15
CX Level 3 | COLO 3 | Cell 3 | Gurtz Electric | L3 XFMR - Cell 3 | #FFFDA5 | EE48 | 2025-08-18 | 2025-08-22
CX Level 3 | COLO 3 | Cell 4 | Gurtz Electric | L3 XFMR - Cell 4 | #FFFDA5 | EE48 | 2025-08-18 | 2025-08-22
CX Level 3 | COLO 4 | All | Gurtz Electric | EPMS/BAS Turn-Up | #FFFDA5 | EE56 | 2025-04-25 | 2025-04-25
CX Level 3 | COLO 4 | Cell 1 | Gurtz Electric | L3 GEN - Cell 1 | #FFFDA5 | EE49 | 2025-06-04 | 2025-06-10
CX Level 3 | COLO 4 | Cell 2 | Gurtz Electric | L3 GEN - Cell 2 | #FFFDA5 | EE49 | 2025-06-11 | 2025-06-17
CX Level 3 | COLO 4 | Cell 3 | Gurtz Electric | L3 GEN - Cell 3 | #FFFDA5 | EE49 | 2025-06-18 | 2025-06-24
CX Level 3 | COLO 4 | Cell 4 | Gurtz Electric | L3 GEN - Cell 4 | #FFFDA5 | EE49 | 2025-06-25 | 2025-07-01
CX Level 3 | COLO 4 | Cell 1 | Gurtz Electric | L3 UPM - Cell 1 | #FFFDA5 | EE50 | 2025-08-25 | 2025-08-29
CX Level 3 | COLO 4 | Cell 2 | Gurtz Electric | L3 UPM - Cell 2 | #FFFDA5 | EE50 | 2025-08-25 | 2025-08-29
CX Level 3 | COLO 4 | Cell 1 | Gurtz Electric | L3 XFMR - Cell 1 | #FFFDA5 | EE48 | 2025-09-02 | 2025-09-08
CX Level 3 | COLO 4 | Cell 3 | Gurtz Electric | L3 UPM - Cell 3 | #FFFDA5 | EE50 | 2025-09-02 | 2025-09-08
CX Level 3 | COLO 4 | Cell 4 | Gurtz Electric | L3 UPM - Cell 4 | #FFFDA5 | EE50 | 2025-09-02 | 2025-09-08
CX Level 3 | COLO 4 | Cell 2 | Gurtz Electric | L3 XFMR - Cell 2 | #FFFDA5 | EE48 | 2025-09-02 | 2025-09-08
CX Level 3 | COLO 4 | Cell 3 | Gurtz Electric | L3 XFMR - Cell 3 | #FFFDA5 | EE48 | 2025-09-09 | 2025-09-15
CX Level 3 | COLO 4 | Cell 4 | Gurtz Electric | L3 XFMR - Cell 4 | #FFFDA5 | EE48 | 2025-09-09 | 2025-09-15
COLO 2 | Cell 1 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | #FFFDA5 | EE29 | 2025-01-03 | 2025-01-31
COLO 2 | Cell 1 | Electrical Room | All Trades | Finishes and Signage - COLO2 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-02-03 | 2025-02-07
COLO 2 | Cell 1 | Data Hall | Gurtz Electric | Cable Pulling at PDU to Busway & MSB - COLO2 Cell 1 - DH | #FFFDA5 | EE17 | 2025-01-03 | 2025-01-31
COLO 2 | Cell 1 | Data Hall | Gurtz Electric | Termination at PDU to Busway & MSB- COLO2 Cell 1 - DH | #FFFDA5 | EE18 | 2025-01-10 | 2025-02-07
COLO 2 | Cell 1 | Data Hall | All Trades | Finishes and Signage - COLO2 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO2 Cell 1 | #FFFDA5 | EE57 | 2025-02-03 | 2025-02-07
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO2 Cell 1 | #FFFDA5 | EE58 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO2 Cell 1 | #FFFDA5 | EE59 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO2 Cell 1 | #FFFDA5 | EE60 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO2 Cell 1 | #FFFDA5 | EE61 | 2025-02-24 | 2025-02-28
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO2 Cell 1 | #FFFDA5 | EE62 | 2025-03-12 | 2025-03-18
COLO 2 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO2 Cell 1 | #FFFDA5 | EE63 | 2025-03-12 | 2025-03-18
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO2 Cell 1 | #FFFDA5 | EE57 | 2025-04-08 | 2025-04-14
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO2 Cell 1 | #FFFDA5 | EE62 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO2 Cell 1 | #FFFDA5 | EE63 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO2 Cell 1 | #FFFDA5 | EE58 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO2 Cell 1 | #FFFDA5 | EE60 | 2025-04-22 | 2025-04-28
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO2 Cell 1 | #FFFDA5 | EE59 | 2025-04-29 | 2025-05-12
COLO 2 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO2 Cell 1 | #FFFDA5 | EE61 | 2025-05-13 | 2025-05-19
COLO 2 | Cell 2 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | #FFFDA5 | EE35 | 2025-01-10 | 2025-01-21
COLO 2 | Cell 2 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO2 Cell 2 - MG | #FFFDA5 | EE36 | 2025-01-22 | 2025-01-28
COLO 2 | Cell 2 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | #FFFDA5 | EE29 | 2025-01-03 | 2025-01-31
COLO 2 | Cell 2 | Electrical Room | All Trades | Finishes and Signage - COLO2 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 2 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH | #FFFDA5 | EE17 | 2025-01-03 | 2025-01-23
COLO 2 | Cell 2 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO2 Cell 2 - DH | #FFFDA5 | EE18 | 2025-01-24 | 2025-02-13
COLO 2 | Cell 2 | Data Hall | All Trades | Finishes and Signage - COLO2 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO2 Cell 2 | #FFFDA5 | EE57 | 2025-02-03 | 2025-02-07
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO2 Cell 2 | #FFFDA5 | EE62 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO2 Cell 2 | #FFFDA5 | EE63 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO2 Cell 2 | #FFFDA5 | EE58 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO2 Cell 2 | #FFFDA5 | EE60 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO2 Cell 2 | #FFFDA5 | EE59 | 2025-02-24 | 2025-02-28
COLO 2 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO2 Cell 2 | #FFFDA5 | EE61 | 2025-03-03 | 2025-03-07
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO2 Cell 2 | #FFFDA5 | EE57 | 2025-04-08 | 2025-04-14
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO2 Cell 2 | #FFFDA5 | EE62 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO2 Cell 2 | #FFFDA5 | EE63 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO2 Cell 2 | #FFFDA5 | EE58 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO2 Cell 2 | #FFFDA5 | EE60 | 2025-04-22 | 2025-04-28
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO2 Cell 2 | #FFFDA5 | EE59 | 2025-04-29 | 2025-05-12
COLO 2 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO2 Cell 2 | #FFFDA5 | EE61 | 2025-05-13 | 2025-05-19
COLO 2 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO2 Cell 3 - MG | #C00000 | I-R | 2025-01-17 | 2025-01-20
COLO 2 | Cell 3 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO2 Cell 3 - MG | #FFFDA5 | EE35 | 2025-01-22 | 2025-01-31
COLO 2 | Cell 3 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO2 Cell 3 - MG | #FFFDA5 | EE36 | 2025-02-03 | 2025-02-07
COLO 2 | Cell 3 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER | #FFFDA5 | EE29 | 2025-01-10 | 2025-01-30
COLO 2 | Cell 3 | Electrical Room | All Trades | Finishes and Signage - COLO2 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-01-28 | 2025-02-03
COLO 2 | Cell 3 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO2 Cell 3 - DH | #FFFDA5 | EE18 | 2025-01-10 | 2025-01-30
COLO 2 | Cell 3 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH | #EF9E5B | ET7 | 2025-01-17 | 2025-01-30
COLO 2 | Cell 3 | Data Hall | All Trades | Finishes and Signage - COLO2 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-02-24 | 2025-02-28
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO2 Cell 3 | #FFFDA5 | EE57 | 2025-02-10 | 2025-02-14
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO2 Cell 3 | #FFFDA5 | EE62 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO2 Cell 3 | #FFFDA5 | EE63 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO2 Cell 3 | #FFFDA5 | EE58 | 2025-02-17 | 2025-02-21
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO2 Cell 3 | #FFFDA5 | EE60 | 2025-02-24 | 2025-02-28
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO2 Cell 3 | #FFFDA5 | EE59 | 2025-03-03 | 2025-03-07
COLO 2 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO2 Cell 3 | #FFFDA5 | EE61 | 2025-03-03 | 2025-03-07
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO2 Cell 3 | #FFFDA5 | EE57 | 2025-04-15 | 2025-04-21
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO2 Cell 3 | #FFFDA5 | EE62 | 2025-04-22 | 2025-04-28
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO2 Cell 3 | #FFFDA5 | EE63 | 2025-04-22 | 2025-04-28
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO2 Cell 3 | #FFFDA5 | EE58 | 2025-04-22 | 2025-04-28
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO2 Cell 3 | #FFFDA5 | EE60 | 2025-04-29 | 2025-05-05
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO2 Cell 3 | #FFFDA5 | EE59 | 2025-05-06 | 2025-05-19
COLO 2 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO2 Cell 3 | #FFFDA5 | EE61 | 2025-05-20 | 2025-05-27
COLO 2 | Cell 4 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO2 Cell 4 - MG | #EF9E5B | ET22 | 2025-01-17 | 2025-01-30
COLO 2 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO2 Cell 4 - MG | #C00000 | I-R | 2025-01-31 | 2025-02-03
COLO 2 | Cell 4 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO2 Cell 4 - MG | #FFFDA5 | EE35 | 2025-02-04 | 2025-02-13
COLO 2 | Cell 4 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO2 Cell 4 - MG | #FFFDA5 | EE36 | 2025-02-14 | 2025-02-20
COLO 2 | Cell 4 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO2 Cell 4 - ER | #FFFDA5 | EE28 | 2025-01-14 | 2025-01-20
COLO 2 | Cell 4 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER | #FFFDA5 | EE29 | 2025-01-31 | 2025-02-20
COLO 2 | Cell 4 | Electrical Room | All Trades | Finishes and Signage - COLO2 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-02-21 | 2025-02-27
COLO 2 | Cell 4 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO2 Cell 4 - DH | #FFFDA5 | EE18 | 2025-01-10 | 2025-01-30
COLO 2 | Cell 4 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH | #EF9E5B | ET7 | 2025-01-31 | 2025-02-13
COLO 2 | Cell 4 | Data Hall | All Trades | Finishes and Signage - COLO2 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-03-03 | 2025-03-07
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO2 Cell 4 | #FFFDA5 | EE57 | 2025-02-21 | 2025-02-27
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO2 Cell 4 | #FFFDA5 | EE62 | 2025-02-28 | 2025-03-06
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO2 Cell 4 | #FFFDA5 | EE63 | 2025-02-28 | 2025-03-06
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO2 Cell 4 | #FFFDA5 | EE58 | 2025-02-28 | 2025-03-06
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO2 Cell 4 | #FFFDA5 | EE60 | 2025-03-07 | 2025-03-13
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO2 Cell 4 | #FFFDA5 | EE59 | 2025-03-10 | 2025-03-14
COLO 2 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO2 Cell 4 | #FFFDA5 | EE61 | 2025-03-10 | 2025-03-14
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO2 Cell 4 | #FFFDA5 | EE57 | 2025-04-22 | 2025-04-28
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO2 Cell 4 | #FFFDA5 | EE62 | 2025-04-29 | 2025-05-05
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO2 Cell 4 | #FFFDA5 | EE63 | 2025-04-29 | 2025-05-05
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO2 Cell 4 | #FFFDA5 | EE58 | 2025-05-06 | 2025-05-12
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO2 Cell 4 | #FFFDA5 | EE60 | 2025-05-13 | 2025-05-19
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO2 Cell 4 | #FFFDA5 | EE59 | 2025-05-13 | 2025-05-27
COLO 2 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO2 Cell 4 | #FFFDA5 | EE61 | 2025-05-28 | 2025-06-03
COLO 2 | All | CX - Microsoft | Microsoft | Level 4 Cx - Colo 2 | #000000 | MS1 | 2025-06-04 | 2025-07-01
COLO 2 | All | CX - Microsoft | Microsoft | Level 5 Cx / IST - Colo 2 | #000000 | MS2 | 2025-07-02 | 2025-07-03
COLO 5 | Cell 1 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO5 Cell 1 - MG | #FFFDA5 | EE36 | 2025-01-17 | 2025-01-23
COLO 5 | Cell 1 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER | #FFFDA5 | EE29 | 2024-12-31 | 2025-01-31
COLO 5 | Cell 1 | Electrical Room | All Trades | Finishes and Signage - COLO5 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-01-29 | 2025-02-04
COLO 5 | Cell 1 | Data Hall | Gurtz Electric | Termination at PDU & Busway- COLO5 Cell 1 - DH | #FFFDA5 | EE18 | 2025-01-17 | 2025-02-06
COLO 5 | Cell 1 | Data Hall | All Trades | Finishes and Signage - COLO5 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-02-07 | 2025-02-13
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO5 Cell 1 | #FFFDA5 | EE57 | 2025-03-17 | 2025-03-21
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO5 Cell 1 | #FFFDA5 | EE62 | 2025-03-24 | 2025-03-28
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO5 Cell 1 | #FFFDA5 | EE58 | 2025-03-24 | 2025-03-28
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO5 Cell 1 | #FFFDA5 | EE63 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO5 Cell 1 | #FFFDA5 | EE59 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO5 Cell 1 | #FFFDA5 | EE60 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO5 Cell 1 | #FFFDA5 | EE61 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO5 Cell 1 | #FFFDA5 | EE57 | 2025-08-04 | 2025-08-08
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO5 Cell 1 | #FFFDA5 | EE63 | 2025-08-04 | 2025-08-08
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO5 Cell 1 | #FFFDA5 | EE62 | 2025-08-11 | 2025-08-15
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO5 Cell 1 | #FFFDA5 | EE58 | 2025-08-11 | 2025-08-15
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO5 Cell 1 | #FFFDA5 | EE60 | 2025-08-18 | 2025-08-22
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO5 Cell 1 | #FFFDA5 | EE59 | 2025-08-13 | 2025-08-26
COLO 5 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO5 Cell 1 | #FFFDA5 | EE61 | 2025-08-25 | 2025-08-29
COLO 5 | Cell 2 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO5 Cell 2 - MG | #FFFDA5 | EE35 | 2025-01-10 | 2025-01-21
COLO 5 | Cell 2 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO5 Cell 2 - MG | #FFFDA5 | EE36 | 2025-01-24 | 2025-01-30
COLO 5 | Cell 2 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER | #FFFDA5 | EE29 | 2025-01-21 | 2025-02-03
COLO 5 | Cell 2 | Electrical Room | All Trades | Finishes and Signage - COLO5 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-02-14 | 2025-02-20
COLO 5 | Cell 2 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH | #FFFDA5 | EE18 | 2025-01-17 | 2025-01-30
COLO 5 | Cell 2 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH | #EF9E5B | ET7 | 2025-01-17 | 2025-01-30
COLO 5 | Cell 2 | Data Hall | Gurtz Electric | Termination at PDU & Busway- COLO5 Cell 2 - DH | #FFFDA5 | EE19 | 2025-01-31 | 2025-02-20
COLO 5 | Cell 2 | Data Hall | All Trades | Finishes and Signage - COLO5 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-02-21 | 2025-02-27
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO5 Cell 2 | #FFFDA5 | EE57 | 2025-03-24 | 2025-03-28
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO5 Cell 2 | #FFFDA5 | EE62 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO5 Cell 2 | #FFFDA5 | EE63 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO5 Cell 2 | #FFFDA5 | EE58 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO5 Cell 2 | #FFFDA5 | EE59 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO5 Cell 2 | #FFFDA5 | EE60 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO5 Cell 2 | #FFFDA5 | EE61 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO5 Cell 2 | #FFFDA5 | EE57 | 2025-08-07 | 2025-08-13
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO5 Cell 2 | #FFFDA5 | EE63 | 2025-08-07 | 2025-08-13
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO5 Cell 2 | #FFFDA5 | EE58 | 2025-08-07 | 2025-08-13
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO5 Cell 2 | #FFFDA5 | EE62 | 2025-08-14 | 2025-08-20
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO5 Cell 2 | #FFFDA5 | EE60 | 2025-08-14 | 2025-08-20
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO5 Cell 2 | #FFFDA5 | EE59 | 2025-08-21 | 2025-09-04
COLO 5 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO5 Cell 2 | #FFFDA5 | EE61 | 2025-09-03 | 2025-09-09
COLO 5 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO5 Cell 3 - MG | #C00000 | I-R | 2025-01-17 | 2025-01-20
COLO 5 | Cell 3 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO5 Cell 3 - MG | #FFFDA5 | EE35 | 2025-01-22 | 2025-01-31
COLO 5 | Cell 3 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO5 Cell 3 - MG | #FFFDA5 | EE36 | 2025-02-03 | 2025-02-07
COLO 5 | Cell 3 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO5 Cell 3 - ER | #FFFDA5 | EE28 | 2025-01-14 | 2025-01-20
COLO 5 | Cell 3 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER | #FFFDA5 | EE18 | 2025-01-21 | 2025-02-03
COLO 5 | Cell 3 | Electrical Room | All Trades | Finishes and Signage - COLO5 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-02-28 | 2025-03-06
COLO 5 | Cell 3 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO5 Cell 3 - DH | #FFFDA5 | EE17 | 2025-01-10 | 2025-01-23
COLO 5 | Cell 3 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO5 Cell 3 - DH | #FFFDA5 | EE18 | 2025-01-31 | 2025-02-20
COLO 5 | Cell 3 | Data Hall | All Trades | Finishes and Signage - COLO5 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-03-07 | 2025-03-13
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO5 Cell 3 | #FFFDA5 | EE57 | 2025-03-31 | 2025-04-04
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO5 Cell 3 | #FFFDA5 | EE62 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO5 Cell 3 | #FFFDA5 | EE63 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO5 Cell 3 | #FFFDA5 | EE58 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO5 Cell 3 | #FFFDA5 | EE59 | 2025-04-14 | 2025-04-18
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO5 Cell 3 | #FFFDA5 | EE60 | 2025-04-14 | 2025-04-18
COLO 5 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO5 Cell 3 | #FFFDA5 | EE61 | 2025-04-14 | 2025-04-18
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO5 Cell 3 | #FFFDA5 | EE57 | 2025-08-14 | 2025-08-20
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO5 Cell 3 | #FFFDA5 | EE63 | 2025-08-14 | 2025-08-20
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO5 Cell 3 | #FFFDA5 | EE58 | 2025-08-14 | 2025-08-20
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO5 Cell 3 | #FFFDA5 | EE62 | 2025-08-21 | 2025-08-27
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO5 Cell 3 | #FFFDA5 | EE60 | 2025-08-21 | 2025-08-27
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO5 Cell 3 | #FFFDA5 | EE59 | 2025-08-21 | 2025-09-04
COLO 5 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO5 Cell 3 | #FFFDA5 | EE61 | 2025-09-03 | 2025-09-09
COLO 5 | Cell 4 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO5 Cell 4 - MG | #EF9E5B | ET22 | 2025-01-17 | 2025-01-30
COLO 5 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO5 Cell 4 - MG | #C00000 | I-R | 2025-01-31 | 2025-02-03
COLO 5 | Cell 4 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO5 Cell 4 - MG | #FFFDA5 | EE35 | 2025-02-04 | 2025-02-13
COLO 5 | Cell 4 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO5 Cell 4 - MG | #FFFDA5 | EE36 | 2025-02-14 | 2025-02-20
COLO 5 | Cell 4 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO5 Cell 4 - ER | #FFFDA5 | EE27 | 2025-01-17 | 2025-01-23
COLO 5 | Cell 4 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO5 Cell 4 - ER | #FFFDA5 | EE28 | 2025-01-21 | 2025-01-27
COLO 5 | Cell 4 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER | #FFFDA5 | EE17 | 2025-01-28 | 2025-02-10
COLO 5 | Cell 4 | Electrical Room | All Trades | Finishes and Signage - COLO5 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-03-14 | 2025-03-20
COLO 5 | Cell 4 | Data Hall | WALSH | Closing Construction Access Door - COLO5 Cell 4 - DH | #04A261 | W4 | 2025-01-03 | 2025-01-23
COLO 5 | Cell 4 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH | #EF9E5B | ET7 | 2025-01-31 | 2025-02-13
COLO 5 | Cell 4 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO5 Cell 4 - DH | #FFFDA5 | EE18 | 2025-02-21 | 2025-03-13
COLO 5 | Cell 4 | Data Hall | All Trades | Finishes and Signage - COLO5 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-03-21 | 2025-03-27
COLO 5 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO5 Cell 4 | #FFFDA5 | EE63 | 2025-01-24 | 2025-01-24
COLO 5 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO5 Cell 4 | #FFFDA5 | EE59 | 2025-01-24 | 2025-01-24
COLO 5 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO5 Cell 4 | #FFFDA5 | EE61 | 2025-01-24 | 2025-01-24
COLO 5 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO5 Cell 4 | #FFFDA5 | EE58 | 2025-01-24 | 2025-01-24
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO5 Cell 4 | #FFFDA5 | EE57 | 2025-04-07 | 2025-04-11
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO5 Cell 4 | #FFFDA5 | EE62 | 2025-04-14 | 2025-04-18
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO5 Cell 4 | #FFFDA5 | EE63 | 2025-04-14 | 2025-04-18
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO5 Cell 4 | #FFFDA5 | EE58 | 2025-04-14 | 2025-04-18
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO5 Cell 4 | #FFFDA5 | EE59 | 2025-04-21 | 2025-04-25
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO5 Cell 4 | #FFFDA5 | EE60 | 2025-04-21 | 2025-04-25
COLO 5 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO5 Cell 4 | #FFFDA5 | EE61 | 2025-04-21 | 2025-04-25
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO5 Cell 4 | #FFFDA5 | EE57 | 2025-08-21 | 2025-08-27
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO5 Cell 4 | #FFFDA5 | EE63 | 2025-08-21 | 2025-08-27
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO5 Cell 4 | #FFFDA5 | EE58 | 2025-08-28 | 2025-09-04
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO5 Cell 4 | #FFFDA5 | EE60 | 2025-09-05 | 2025-09-11
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO5 Cell 4 | #FFFDA5 | EE62 | 2025-09-10 | 2025-09-16
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO5 Cell 4 | #FFFDA5 | EE59 | 2025-09-10 | 2025-09-23
COLO 5 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO5 Cell 4 | #FFFDA5 | EE61 | 2025-09-22 | 2025-09-26
COLO 5 | All | CX - Microsoft | Microsoft | Level 4 Cx - Colo 5 | #000000 | MS1 | 2025-09-29 | 2025-10-24
COLO 5 | All | CX - Microsoft | Microsoft | Level 5 Cx / IST - Colo 5 | #000000 | MS2 | 2025-10-27 | 2025-10-28
COLO 3 | Cell 1 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO3 Cell 1 - MG | #FFFDA5 | EE35 | 2025-01-14 | 2025-01-23
COLO 3 | Cell 1 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO3 Cell 1 - MG | #FFFDA5 | EE36 | 2025-01-24 | 2025-01-30
COLO 3 | Cell 1 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO3 Cell 1 - ER | #FFFDA5 | EE28 | 2025-01-27 | 2025-01-31
COLO 3 | Cell 1 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER | #FFFDA5 | EE29 | 2025-02-03 | 2025-02-18
COLO 3 | Cell 1 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO3 Cell 1 - ER | #FFFDA5 | EE23 | 2025-02-19 | 2025-02-25
COLO 3 | Cell 1 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO3 Cell 1 - ER | #3399FF | J36 | 2025-02-26 | 2025-03-04
COLO 3 | Cell 1 | Electrical Room | All Trades | Finishes and Signage - COLO3 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-03-05 | 2025-03-11
COLO 3 | Cell 1 | Data Hall | Gurtz Electric | Install PDU's - COLO3 Cell 1 - DH | #FFFDA5 | EE7 | 2025-01-17 | 2025-01-23
COLO 3 | Cell 1 | Data Hall | Interior System | Begin HAC Assembly - COLO3 Cell 1 - DH | #FED7E8 | S1 | 2025-01-17 | 2025-01-23
COLO 3 | Cell 1 | Data Hall | Interior System | HAC install and Rise - COLO3 Cell 1 - DH | #FED7E8 | S2 | 2025-01-24 | 2025-01-30
COLO 3 | Cell 1 | Data Hall | Gurtz Electric | Install Busway - COLO3 Cell 1 - DH | #FFFDA5 | EE10 | 2025-01-27 | 2025-01-31
COLO 3 | Cell 1 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH | #FFFDA5 | EE17 | 2025-01-24 | 2025-02-13
COLO 3 | Cell 1 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH | #EF9E5B | ET7 | 2025-01-31 | 2025-02-13
COLO 3 | Cell 1 | Data Hall | Gurtz Electric | Termination at PDU & Busway- COLO3 Cell 1 - DH | #FFFDA5 | EE18 | 2025-02-03 | 2025-02-21
COLO 3 | Cell 1 | Data Hall | All Trades | Finishes and Signage - COLO3 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-02-24 | 2025-02-28
COLO 3 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO3 Cell 1 | #FFFDA5 | EE63 | 2025-01-24 | 2025-01-24
COLO 3 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO3 Cell 1 | #FFFDA5 | EE62 | 2025-02-26 | 2025-02-26
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO3 Cell 1 | #FFFDA5 | EE57 | 2025-03-17 | 2025-03-21
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO3 Cell 1 | #FFFDA5 | EE62 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO3 Cell 1 | #FFFDA5 | EE63 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO3 Cell 1 | #FFFDA5 | EE58 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO3 Cell 1 | #FFFDA5 | EE60 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO3 Cell 1 | #FFFDA5 | EE61 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO3 Cell 1 | #FFFDA5 | EE59 | 2025-04-07 | 2025-04-11
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO3 Cell 1 | #FFFDA5 | EE57 | 2025-08-18 | 2025-08-22
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO3 Cell 1 | #FFFDA5 | EE62 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO3 Cell 1 | #FFFDA5 | EE63 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO3 Cell 1 | #FFFDA5 | EE58 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO3 Cell 1 | #FFFDA5 | EE60 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO3 Cell 1 | #FFFDA5 | EE59 | 2025-09-10 | 2025-09-23
COLO 3 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO3 Cell 1 | #FFFDA5 | EE61 | 2025-09-24 | 2025-09-30
COLO 3 | Cell 2 | Mech Gallery | Great Lakes Air Design | Placing the AHU - COLO3 Cell 2 - MG | #CFE741 | GA6 | 2025-01-17 | 2025-01-21
COLO 3 | Cell 2 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO3 Cell 2 - MG | #FFFDA5 | EE70 | 2025-01-10 | 2025-01-30
COLO 3 | Cell 2 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO3 Cell 2 - MG | #EF9E5B | ET22 | 2025-01-21 | 2025-02-04
COLO 3 | Cell 2 | Mech Gallery | Inspections | Pipe Testing - COLO3 Cell 2 - MG | #C00000 | I-R | 2025-02-04 | 2025-02-06
COLO 3 | Cell 2 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO3 Cell 2 - MG | #FFFDA5 | EE35 | 2025-02-06 | 2025-02-18
COLO 3 | Cell 2 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO3 Cell 2 - MG | #FFFDA5 | EE36 | 2025-02-18 | 2025-02-25
COLO 3 | Cell 2 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO3 Cell 2 - ER | #987655 | GH3 | 2025-01-15 | 2025-01-21
COLO 3 | Cell 2 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO3 Cell 2 - ER | #FFFDA5 | EE27 | 2025-01-16 | 2025-01-22
COLO 3 | Cell 2 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO3 Cell 2 - ER | #FFFDA5 | EE23 | 2025-01-16 | 2025-01-22
COLO 3 | Cell 2 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO3 Cell 2 - ER | #FFFDA5 | EE71 | 2025-01-16 | 2025-01-22
COLO 3 | Cell 2 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | #FFFDA5 | EE72 | 2025-01-14 | 2025-01-27
COLO 3 | Cell 2 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO3 Cell 2 - ER | #3399FF | J36 | 2025-01-23 | 2025-01-29
COLO 3 | Cell 2 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO3 Cell 2 - ER | #FFFDA5 | EE28 | 2025-02-03 | 2025-02-07
COLO 3 | Cell 2 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER | #FFFDA5 | EE29 | 2025-02-19 | 2025-03-06
COLO 3 | Cell 2 | Electrical Room | All Trades | Finishes and Signage - COLO3 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-03-12 | 2025-03-18
COLO 3 | Cell 2 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO3 Cell 2 - DH | #3399FF | J7 | 2025-01-15 | 2025-01-21
COLO 3 | Cell 2 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH | #FFFDA5 | EE73 | 2025-01-22 | 2025-02-04
COLO 3 | Cell 2 | Data Hall | Gurtz Electric | Install PDU's - COLO3 Cell 2 - DH | #FFFDA5 | EE7 | 2025-02-05 | 2025-02-11
COLO 3 | Cell 2 | Data Hall | Interior System | Begin HAC Assembly - COLO3 Cell 2 - DH | #FED7E8 | S1 | 2025-02-05 | 2025-02-11
COLO 3 | Cell 2 | Data Hall | Gurtz Electric | Install Busway - COLO3 Cell 2 - DH | #FFFDA5 | EE10 | 2025-02-07 | 2025-02-13
COLO 3 | Cell 2 | Data Hall | Interior System | HAC install and Rise - COLO3 Cell 2 - DH | #FED7E8 | S2 | 2025-02-12 | 2025-02-18
COLO 3 | Cell 2 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO3 Cell 2 - DH | #FFFDA5 | EE17 | 2025-02-12 | 2025-02-25
COLO 3 | Cell 2 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 2 - DH | #EF9E5B | ET7 | 2025-02-19 | 2025-03-04
COLO 3 | Cell 2 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO3 Cell 2 - DH | #FFFDA5 | EE18 | 2025-02-14 | 2025-03-06
COLO 3 | Cell 2 | Data Hall | All Trades | Finishes and Signage - COLO3 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-03-05 | 2025-03-11
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO3 Cell 2 | #FFFDA5 | EE59 | 2025-01-17 | 2025-01-17
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO3 Cell 2 | #FFFDA5 | EE57 | 2025-01-23 | 2025-01-23
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO3 Cell 2 | #FFFDA5 | EE60 | 2025-01-23 | 2025-01-23
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO3 Cell 2 | #FFFDA5 | EE61 | 2025-01-23 | 2025-01-23
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO3 Cell 2 | #FFFDA5 | EE58 | 2025-01-23 | 2025-01-23
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO3 Cell 2 | #FFFDA5 | EE63 | 2025-02-12 | 2025-02-12
COLO 3 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO3 Cell 2 | #FFFDA5 | EE62 | 2025-02-27 | 2025-02-27
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO3 Cell 2 | #FFFDA5 | EE57 | 2025-03-17 | 2025-03-21
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO3 Cell 2 | #FFFDA5 | EE62 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO3 Cell 2 | #FFFDA5 | EE63 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO3 Cell 2 | #FFFDA5 | EE58 | 2025-03-24 | 2025-03-28
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO3 Cell 2 | #FFFDA5 | EE60 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO3 Cell 2 | #FFFDA5 | EE61 | 2025-03-31 | 2025-04-04
COLO 3 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO3 Cell 2 | #FFFDA5 | EE59 | 2025-04-14 | 2025-04-18
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO3 Cell 2 | #FFFDA5 | EE57 | 2025-08-18 | 2025-08-22
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO3 Cell 2 | #FFFDA5 | EE62 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO3 Cell 2 | #FFFDA5 | EE58 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO3 Cell 2 | #FFFDA5 | EE63 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO3 Cell 2 | #FFFDA5 | EE60 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO3 Cell 2 | #FFFDA5 | EE59 | 2025-09-10 | 2025-09-23
COLO 3 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO3 Cell 2 | #FFFDA5 | EE61 | 2025-09-24 | 2025-09-30
COLO 3 | Cell 3 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO3 Cell 3 - MG | #FFFDA5 | EE70 | 2025-01-10 | 2025-01-30
COLO 3 | Cell 3 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO3 Cell 3 - MG | #EF9E5B | ET22 | 2025-02-04 | 2025-02-18
COLO 3 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO3 Cell 3 - MG | #C00000 | I-R | 2025-02-18 | 2025-02-20
COLO 3 | Cell 3 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO3 Cell 3 - MG | #FFFDA5 | EE35 | 2025-02-20 | 2025-03-04
COLO 3 | Cell 3 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO3 Cell 3 - MG | #FFFDA5 | EE36 | 2025-03-04 | 2025-03-11
COLO 3 | Cell 3 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO3 Cell 3 - ER | #987655 | GH3 | 2025-01-17 | 2025-01-23
COLO 3 | Cell 3 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO3 Cell 3 - ER | #FFFDA5 | EE27 | 2025-01-30 | 2025-02-05
COLO 3 | Cell 3 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO3 Cell 3 - ER | #FFFDA5 | EE23 | 2025-01-30 | 2025-02-05
COLO 3 | Cell 3 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO3 Cell 3 - ER | #FFFDA5 | EE71 | 2025-01-30 | 2025-02-05
COLO 3 | Cell 3 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | #FFFDA5 | EE72 | 2025-01-28 | 2025-02-10
COLO 3 | Cell 3 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO3 Cell 3 - ER | #3399FF | J36 | 2025-02-06 | 2025-02-12
COLO 3 | Cell 3 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO3 Cell 3 - ER | #FFFDA5 | EE28 | 2025-02-10 | 2025-02-14
COLO 3 | Cell 3 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER | #FFFDA5 | EE29 | 2025-03-07 | 2025-03-24
COLO 3 | Cell 3 | Electrical Room | All Trades | Finishes and Signage - COLO3 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-03-20 | 2025-03-26
COLO 3 | Cell 3 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO3 Cell 3 - DH | #3399FF | J7 | 2025-01-22 | 2025-01-28
COLO 3 | Cell 3 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH | #FFFDA5 | EE73 | 2025-02-05 | 2025-02-18
COLO 3 | Cell 3 | Data Hall | Gurtz Electric | Install PDU's - COLO3 Cell 3 - DH | #FFFDA5 | EE7 | 2025-02-19 | 2025-02-25
COLO 3 | Cell 3 | Data Hall | Interior System | Begin HAC Assembly - COLO3 Cell 3 - DH | #FED7E8 | S1 | 2025-02-19 | 2025-02-25
COLO 3 | Cell 3 | Data Hall | Gurtz Electric | Install Busway - COLO3 Cell 3 - DH | #FFFDA5 | EE10 | 2025-02-21 | 2025-02-27
COLO 3 | Cell 3 | Data Hall | Interior System | HAC install and Rise - COLO3 Cell 3 - DH | #FED7E8 | S2 | 2025-02-26 | 2025-03-04
COLO 3 | Cell 3 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO3 Cell 3 - DH | #FFFDA5 | EE17 | 2025-02-26 | 2025-03-11
COLO 3 | Cell 3 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 3 - DH | #EF9E5B | ET7 | 2025-03-05 | 2025-03-18
COLO 3 | Cell 3 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO3 Cell 3 - DH | #FFFDA5 | EE18 | 2025-03-12 | 2025-04-01
COLO 3 | Cell 3 | Data Hall | All Trades | Finishes and Signage - COLO3 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-03-26 | 2025-04-01
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO3 Cell 3 | #FFFDA5 | EE59 | 2025-01-21 | 2025-01-22
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO3 Cell 3 | #FFFDA5 | EE57 | 2025-02-06 | 2025-02-06
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO3 Cell 3 | #FFFDA5 | EE60 | 2025-02-06 | 2025-02-06
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-02-06 | 2025-02-06
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO3 Cell 3 | #FFFDA5 | EE58 | 2025-02-06 | 2025-02-06
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO3 Cell 3 | #FFFDA5 | EE63 | 2025-02-26 | 2025-02-26
COLO 3 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO3 Cell 3 | #FFFDA5 | EE62 | 2025-02-28 | 2025-02-28
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO3 Cell 3 | #FFFDA5 | EE57 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO3 Cell 3 | #FFFDA5 | EE60 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO3 Cell 3 | #FFFDA5 | EE58 | 2025-03-25 | 2025-03-31
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO3 Cell 3 | #FFFDA5 | EE62 | 2025-04-01 | 2025-04-07
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO3 Cell 3 | #FFFDA5 | EE63 | 2025-04-01 | 2025-04-07
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-04-08 | 2025-04-14
COLO 3 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO3 Cell 3 | #FFFDA5 | EE59 | 2025-04-21 | 2025-04-25
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO3 Cell 3 | #FFFDA5 | EE57 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO3 Cell 3 | #FFFDA5 | EE62 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO3 Cell 3 | #FFFDA5 | EE63 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO3 Cell 3 | #FFFDA5 | EE58 | 2025-09-09 | 2025-09-15
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO3 Cell 3 | #FFFDA5 | EE60 | 2025-09-17 | 2025-09-23
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-09-24 | 2025-09-30
COLO 3 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO3 Cell 3 | #FFFDA5 | EE61 | 2025-09-24 | 2025-10-07
COLO 3 | Cell 4 | Mech Gallery | Great Lakes Air Design | Deliver AHU into Mech. Gallery - COLO3 Cell 4 - MG | #CFE741 | GA12 | 2025-01-17 | 2025-01-20
COLO 3 | Cell 4 | Mech Gallery | All - Tech | Install Walls and Primer Paint - COLO3 Cell 4 - MG | #D6F2FF | T3 | 2025-01-21 | 2025-02-03
COLO 3 | Cell 4 | Mech Gallery | Anning - Johnson | Layout Ceiling and install Pencile Rod - COLO3 Cell 4 - MG | #3399FF | J9 | 2025-02-04 | 2025-02-04
COLO 3 | Cell 4 | Mech Gallery | Great Lakes Air Design | Placing the AHU - COLO3 Cell 4 - MG | #CFE741 | GA6 | 2025-02-11 | 2025-02-13
COLO 3 | Cell 4 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO3 Cell 4 - MG | #FFFDA5 | EE70 | 2025-02-04 | 2025-02-24
COLO 3 | Cell 4 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO3 Cell 4 - MG | #EF9E5B | ET22 | 2025-02-18 | 2025-03-04
COLO 3 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO3 Cell 4 - MG | #C00000 | I-R | 2025-03-04 | 2025-03-06
COLO 3 | Cell 4 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO3 Cell 4 - MG | #FFFDA5 | EE35 | 2025-03-06 | 2025-03-18
COLO 3 | Cell 4 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO3 Cell 4 - MG | #FFFDA5 | EE36 | 2025-03-18 | 2025-03-25
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 4 - ER | #FFFDA5 | EE1 | 2025-01-13 | 2025-01-24
COLO 3 | Cell 4 | Electrical Room | Anning - Johnson | Install Ceiling - COLO3 Cell 4 - ER | #3399FF | J17 | 2025-01-27 | 2025-01-29
COLO 3 | Cell 4 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO3 Cell 4 - ER | #987655 | GH3 | 2025-01-30 | 2025-02-05
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO3 Cell 4 - ER | #FFFDA5 | EE27 | 2025-02-13 | 2025-02-19
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO3 Cell 4 - ER | #FFFDA5 | EE23 | 2025-02-13 | 2025-02-19
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO3 Cell 4 - ER | #FFFDA5 | EE71 | 2025-02-13 | 2025-02-19
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO3 Cell 4 - ER | #FFFDA5 | EE28 | 2025-02-17 | 2025-02-21
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | #FFFDA5 | EE72 | 2025-02-11 | 2025-02-24
COLO 3 | Cell 4 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO3 Cell 4 - ER | #3399FF | J36 | 2025-02-20 | 2025-02-26
COLO 3 | Cell 4 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER | #FFFDA5 | EE29 | 2025-03-04 | 2025-03-24
COLO 3 | Cell 4 | Electrical Room | All Trades | Finishes and Signage - COLO3 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-03-27 | 2025-04-02
COLO 3 | Cell 4 | Data Hall | Gurtz Electric | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 4 - DH | #FFFDA5 | EE74 | 2025-01-10 | 2025-01-27
COLO 3 | Cell 4 | Data Hall | Anning - Johnson | Security Screen Installation - COLO3 Cell 4 - DH | #3399FF | J6 | 2025-02-04 | 2025-02-06
COLO 3 | Cell 4 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO3 Cell 4 - DH | #3399FF | J7 | 2025-02-07 | 2025-02-13
COLO 3 | Cell 4 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 4 - DH | #FFFDA5 | EE73 | 2025-02-19 | 2025-03-04
COLO 3 | Cell 4 | Data Hall | Gurtz Electric | Install PDU's - COLO3 Cell 4 - DH | #FFFDA5 | EE7 | 2025-03-05 | 2025-03-11
COLO 3 | Cell 4 | Data Hall | Interior System | Begin HAC Assembly - COLO3 Cell 4 - DH | #FED7E8 | S1 | 2025-03-05 | 2025-03-11
COLO 3 | Cell 4 | Data Hall | Gurtz Electric | Install Busway - COLO3 Cell 4 - DH | #FFFDA5 | EE10 | 2025-03-07 | 2025-03-13
COLO 3 | Cell 4 | Data Hall | Interior System | HAC install and Rise - COLO3 Cell 4 - DH | #FED7E8 | S2 | 2025-03-12 | 2025-03-18
COLO 3 | Cell 4 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH | #EF9E5B | ET7 | 2025-03-05 | 2025-03-18
COLO 3 | Cell 4 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO3 Cell 4 - DH | #FFFDA5 | EE17 | 2025-03-12 | 2025-03-25
COLO 3 | Cell 4 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO3 Cell 4 - DH | #FFFDA5 | EE18 | 2025-04-02 | 2025-04-15
COLO 3 | Cell 4 | Data Hall | All Trades | Finishes and Signage - COLO3 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-04-09 | 2025-04-15
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO3 Cell 4 | #FFFDA5 | EE61 | 2025-02-11 | 2025-02-11
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO3 Cell 4 | #FFFDA5 | EE57 | 2025-02-20 | 2025-02-20
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-02-20 | 2025-02-20
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-02-20 | 2025-02-20
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO3 Cell 4 | #FFFDA5 | EE58 | 2025-02-20 | 2025-02-20
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO3 Cell 4 | #FFFDA5 | EE62 | 2025-02-28 | 2025-02-28
COLO 3 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO3 Cell 4 | #FFFDA5 | EE63 | 2025-03-12 | 2025-03-12
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO3 Cell 4 | #FFFDA5 | EE57 | 2025-03-25 | 2025-04-01
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO3 Cell 4 | #FFFDA5 | EE62 | 2025-04-01 | 2025-04-08
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-04-01 | 2025-04-08
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO3 Cell 4 | #FFFDA5 | EE61 | 2025-04-08 | 2025-04-15
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO3 Cell 4 | #FFFDA5 | EE58 | 2025-04-08 | 2025-04-15
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO3 Cell 4 | #FFFDA5 | EE63 | 2025-04-16 | 2025-04-22
COLO 3 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO3 Cell 4 | #FFFDA5 | EE59 | 2025-04-21 | 2025-04-25
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO3 Cell 4 | #FFFDA5 | EE57 | 2025-08-25 | 2025-08-29
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO3 Cell 4 | #FFFDA5 | EE63 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO3 Cell 4 | #FFFDA5 | EE58 | 2025-09-02 | 2025-09-08
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO3 Cell 4 | #FFFDA5 | EE59 | 2025-09-03 | 2025-09-16
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO3 Cell 4 | #FFFDA5 | EE60 | 2025-09-10 | 2025-09-16
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO3 Cell 4 | #FFFDA5 | EE62 | 2025-09-24 | 2025-09-30
COLO 3 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO3 Cell 4 | #FFFDA5 | EE61 | 2025-10-01 | 2025-10-07
COLO 3 | All | CX - Microsoft | Microsoft | Level 4 Cx - Colo 3 | #000000 | MS1 | 2025-10-08 | 2025-11-06
COLO 3 | All | CX - Microsoft | Microsoft | Level 5 Cx / IST - Colo 3 | #000000 | MS2 | 2025-10-08 | 2025-11-04
COLO 4 | Cell 1 | Mech Gallery | Great Lakes Air Design | Placing the AHU - COLO4 Cell 1 - MG | #CFE741 | GA6 | 2025-01-17 | 2025-01-21
COLO 4 | Cell 1 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO4 Cell 1 - MG | #FFFDA5 | EE70 | 2025-01-10 | 2025-01-30
COLO 4 | Cell 1 | Mech Gallery | Gurtz Electric | Piping and Electrical Termination to AHUs - COLO4 Cell 1 - MG | #FFFDA5 | EE1 | 2025-01-21 | 2025-02-04
COLO 4 | Cell 1 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 1 - MG | #C00000 | I-R | 2025-02-04 | 2025-02-06
COLO 4 | Cell 1 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO4 Cell 1 - MG | #FFFDA5 | EE35 | 2025-02-06 | 2025-02-18
COLO 4 | Cell 1 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO4 Cell 1 - MG | #FFFDA5 | EE36 | 2025-02-18 | 2025-02-25
COLO 4 | Cell 1 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO4 Cell 1 - ER | #FFFDA5 | EE27 | 2025-01-17 | 2025-01-23
COLO 4 | Cell 1 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO4 Cell 1 - ER | #FFFDA5 | EE23 | 2025-01-17 | 2025-01-23
COLO 4 | Cell 1 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO4 Cell 1 - ER | #FFFDA5 | EE71 | 2025-01-17 | 2025-01-23
COLO 4 | Cell 1 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO4 Cell 1 - ER | #987655 | GH3 | 2025-01-17 | 2025-01-23
COLO 4 | Cell 1 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO4 Cell 1 - ER | #FFFDA5 | EE72 | 2025-01-14 | 2025-01-27
COLO 4 | Cell 1 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO4 Cell 1 - ER | #3399FF | J36 | 2025-01-24 | 2025-01-30
COLO 4 | Cell 1 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO4 Cell 1 - ER | #FFFDA5 | EE28 | 2025-02-11 | 2025-02-17
COLO 4 | Cell 1 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER | #FFFDA5 | EE29 | 2025-02-18 | 2025-03-10
COLO 4 | Cell 1 | Electrical Room | All Trades | Finishes and Signage - COLO4 Cell 1 - ER | #F2F2F2 | ALL3 | 2025-03-06 | 2025-03-12
COLO 4 | Cell 1 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO4 Cell 1 - DH | #3399FF | J7 | 2025-01-17 | 2025-01-23
COLO 4 | Cell 1 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 1 - DH | #FFFDA5 | EE73 | 2025-01-24 | 2025-02-06
COLO 4 | Cell 1 | Data Hall | Gurtz Electric | Install PDU's - COLO4 Cell 1 - DH | #FFFDA5 | EE7 | 2025-02-07 | 2025-02-13
COLO 4 | Cell 1 | Data Hall | Interior System | Begin HAC Assembly - COLO4 Cell 1 - DH | #FED7E8 | S1 | 2025-02-07 | 2025-02-13
COLO 4 | Cell 1 | Data Hall | Gurtz Electric | Install Busway - COLO4 Cell 1 - DH | #FFFDA5 | EE10 | 2025-02-11 | 2025-02-17
COLO 4 | Cell 1 | Data Hall | Interior System | HAC install and Rise - COLO4 Cell 1 - DH | #FED7E8 | S2 | 2025-02-14 | 2025-02-20
COLO 4 | Cell 1 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH | #FFFDA5 | EE17 | 2025-02-14 | 2025-03-06
COLO 4 | Cell 1 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH | #EF9E5B | ET22 | 2025-02-21 | 2025-03-06
COLO 4 | Cell 1 | Data Hall | Gurtz Electric | Termination at PDU & Busway- COLO4 Cell 1 - DH | #FFFDA5 | EE18 | 2025-02-21 | 2025-03-13
COLO 4 | Cell 1 | Data Hall | All Trades | Finishes and Signage - COLO4 Cell 1 - DH | #F2F2F2 | ALL3 | 2025-03-14 | 2025-03-20
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO4 Cell 1 | #FFFDA5 | EE59 | 2025-01-17 | 2025-01-17
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO4 Cell 1 | #FFFDA5 | EE62 | 2025-01-24 | 2025-01-24
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO4 Cell 1 | #FFFDA5 | EE57 | 2025-01-24 | 2025-01-24
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO4 Cell 1 | #FFFDA5 | EE60 | 2025-01-24 | 2025-01-24
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO4 Cell 1 | #FFFDA5 | EE58 | 2025-01-24 | 2025-01-24
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO4 Cell 1 | #FFFDA5 | EE63 | 2025-02-14 | 2025-02-14
COLO 4 | Cell 1 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO4 Cell 1 | #FFFDA5 | EE61 | 2025-02-18 | 2025-02-18
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO4 Cell 1 | #FFFDA5 | EE57 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO4 Cell 1 | #FFFDA5 | EE62 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO4 Cell 1 | #FFFDA5 | EE63 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO4 Cell 1 | #FFFDA5 | EE58 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO4 Cell 1 | #FFFDA5 | EE60 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO4 Cell 1 | #FFFDA5 | EE61 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 1 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO4 Cell 1 | #FFFDA5 | EE59 | 2025-05-19 | 2025-05-23
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO4 Cell 1 | #FFFDA5 | EE57 | 2025-09-29 | 2025-10-03
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO4 Cell 1 | #FFFDA5 | EE62 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO4 Cell 1 | #FFFDA5 | EE63 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO4 Cell 1 | #FFFDA5 | EE58 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO4 Cell 1 | #FFFDA5 | EE60 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO4 Cell 1 | #FFFDA5 | EE59 | 2025-10-20 | 2025-10-31
COLO 4 | Cell 1 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO4 Cell 1 | #FFFDA5 | EE61 | 2025-11-03 | 2025-11-07
COLO 4 | Cell 2 | Mech Gallery | Great Lakes Air Design | Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG | #CFE741 | GA12 | 2025-01-17 | 2025-01-20
COLO 4 | Cell 2 | Mech Gallery | All - Tech | Install Walls and Primer Paint - COLO4 Cell 2 - MG | #D6F2FF | T3 | 2025-01-21 | 2025-02-03
COLO 4 | Cell 2 | Mech Gallery | Anning - Johnson | Layout Ceiling and install Pencile Rod - COLO4 Cell 2 - MG | #3399FF | J9 | 2025-02-04 | 2025-02-04
COLO 4 | Cell 2 | Mech Gallery | Great Lakes Air Design | Placing the AHU - COLO4 Cell 2 - MG | #CFE741 | GA6 | 2025-02-11 | 2025-02-13
COLO 4 | Cell 2 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO4 Cell 2 - MG | #FFFDA5 | EE70 | 2025-02-04 | 2025-02-24
COLO 4 | Cell 2 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO4 Cell 2 - MG | #EF9E5B | ET22 | 2025-02-13 | 2025-02-27
COLO 4 | Cell 2 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 2 - MG | #C00000 | I-R | 2025-02-27 | 2025-03-03
COLO 4 | Cell 2 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO4 Cell 2 - MG | #FFFDA5 | EE35 | 2025-03-03 | 2025-03-13
COLO 4 | Cell 2 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO4 Cell 2 - MG | #FFFDA5 | EE36 | 2025-03-13 | 2025-03-20
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 2 - ER | #FFFDA5 | EE1 | 2025-01-21 | 2025-01-27
COLO 4 | Cell 2 | Electrical Room | Anning - Johnson | Install Ceiling - COLO4 Cell 2 - ER | #3399FF | J17 | 2025-01-28 | 2025-01-30
COLO 4 | Cell 2 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO4 Cell 2 - ER | #987655 | GH3 | 2025-01-31 | 2025-02-06
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO4 Cell 2 - ER | #FFFDA5 | EE27 | 2025-02-03 | 2025-02-07
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO4 Cell 2 - ER | #FFFDA5 | EE23 | 2025-02-03 | 2025-02-07
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO4 Cell 2 - ER | #FFFDA5 | EE71 | 2025-02-03 | 2025-02-07
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | #FFFDA5 | EE72 | 2025-01-30 | 2025-02-12
COLO 4 | Cell 2 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO4 Cell 2 - ER | #3399FF | J36 | 2025-02-10 | 2025-02-14
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO4 Cell 2 - ER | #FFFDA5 | EE28 | 2025-02-18 | 2025-02-24
COLO 4 | Cell 2 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER | #FFFDA5 | EE29 | 2025-03-11 | 2025-03-31
COLO 4 | Cell 2 | Electrical Room | All Trades | Finishes and Signage - COLO4 Cell 2 - ER | #F2F2F2 | ALL3 | 2025-03-27 | 2025-04-02
COLO 4 | Cell 2 | Data Hall | Gurtz Electric | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH | #FFFDA5 | EE74 | 2025-01-10 | 2025-01-27
COLO 4 | Cell 2 | Data Hall | Anning - Johnson | Security Screen Installation - COLO4 Cell 2 - DH | #3399FF | J6 | 2025-02-04 | 2025-02-06
COLO 4 | Cell 2 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO4 Cell 2 - DH | #3399FF | J7 | 2025-02-07 | 2025-02-13
COLO 4 | Cell 2 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH | #FFFDA5 | EE73 | 2025-02-14 | 2025-02-27
COLO 4 | Cell 2 | Data Hall | Gurtz Electric | Install PDU's - COLO4 Cell 2 - DH | #FFFDA5 | EE7 | 2025-02-28 | 2025-03-06
COLO 4 | Cell 2 | Data Hall | Interior System | Begin HAC Assembly - COLO4 Cell 2 - DH | #FED7E8 | S1 | 2025-02-28 | 2025-03-06
COLO 4 | Cell 2 | Data Hall | Gurtz Electric | Install Busway - COLO4 Cell 2 - DH | #FFFDA5 | EE10 | 2025-03-04 | 2025-03-10
COLO 4 | Cell 2 | Data Hall | Interior System | HAC install and Rise - COLO4 Cell 2 - DH | #FED7E8 | S2 | 2025-03-07 | 2025-03-13
COLO 4 | Cell 2 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO4 Cell 2 - DH | #FFFDA5 | EE17 | 2025-03-07 | 2025-03-20
COLO 4 | Cell 2 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 2 - DH | #EF9E5B | ET7 | 2025-03-14 | 2025-03-27
COLO 4 | Cell 2 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO4 Cell 2 - DH | #FFFDA5 | EE18 | 2025-03-11 | 2025-03-31
COLO 4 | Cell 2 | Data Hall | All Trades | Finishes and Signage - COLO4 Cell 2 - DH | #F2F2F2 | ALL3 | 2025-03-28 | 2025-04-03
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO4 Cell 2 | #FFFDA5 | EE62 | 2025-02-10 | 2025-02-10
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO4 Cell 2 | #FFFDA5 | EE57 | 2025-02-10 | 2025-02-10
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO4 Cell 2 | #FFFDA5 | EE60 | 2025-02-10 | 2025-02-10
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO4 Cell 2 | #FFFDA5 | EE58 | 2025-02-10 | 2025-02-10
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO4 Cell 2 | #FFFDA5 | EE59 | 2025-02-11 | 2025-02-11
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO4 Cell 2 | #FFFDA5 | EE63 | 2025-03-07 | 2025-03-07
COLO 4 | Cell 2 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO4 Cell 2 | #FFFDA5 | EE61 | 2025-03-11 | 2025-03-11
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO4 Cell 2 | #FFFDA5 | EE57 | 2025-04-28 | 2025-05-02
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO4 Cell 2 | #FFFDA5 | EE62 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO4 Cell 2 | #FFFDA5 | EE63 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO4 Cell 2 | #FFFDA5 | EE58 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO4 Cell 2 | #FFFDA5 | EE60 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO4 Cell 2 | #FFFDA5 | EE61 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 2 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO4 Cell 2 | #FFFDA5 | EE59 | 2025-05-19 | 2025-05-23
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO4 Cell 2 | #FFFDA5 | EE57 | 2025-09-29 | 2025-10-03
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO4 Cell 2 | #FFFDA5 | EE62 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO4 Cell 2 | #FFFDA5 | EE63 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO4 Cell 2 | #FFFDA5 | EE58 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO4 Cell 2 | #FFFDA5 | EE60 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO4 Cell 2 | #FFFDA5 | EE59 | 2025-10-20 | 2025-10-31
COLO 4 | Cell 2 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO4 Cell 2 | #FFFDA5 | EE61 | 2025-11-03 | 2025-11-07
COLO 4 | Cell 3 | Mech Gallery | Gurtz Electric | Overhead MEP Installation - COLO4 Cell 3 - MG | #FFFDA5 | EE73 | 2025-01-10 | 2025-01-23
COLO 4 | Cell 3 | Mech Gallery | Great Lakes Air Design | Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG | #CFE741 | GA12 | 2025-01-24 | 2025-01-27
COLO 4 | Cell 3 | Mech Gallery | All - Tech | Install Walls and Primer Paint - COLO4 Cell 3 - MG | #D6F2FF | T3 | 2025-02-04 | 2025-02-17
COLO 4 | Cell 3 | Mech Gallery | Anning - Johnson | Layout Ceiling and install Pencile Rod - COLO4 Cell 3 - MG | #3399FF | J9 | 2025-02-18 | 2025-02-18
COLO 4 | Cell 3 | Mech Gallery | Great Lakes Air Design | Placing the AHU - COLO4 Cell 3 - MG | #CFE741 | GA6 | 2025-02-25 | 2025-02-27
COLO 4 | Cell 3 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO4 Cell 3 - MG | #FFFDA5 | EE70 | 2025-02-18 | 2025-03-10
COLO 4 | Cell 3 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO4 Cell 3 - MG | #EF9E5B | ET22 | 2025-02-27 | 2025-03-13
COLO 4 | Cell 3 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 3 - MG | #C00000 | I-R | 2025-03-13 | 2025-03-17
COLO 4 | Cell 3 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO4 Cell 3 - MG | #FFFDA5 | EE35 | 2025-03-17 | 2025-03-27
COLO 4 | Cell 3 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO4 Cell 3 - MG | #FFFDA5 | EE36 | 2025-03-27 | 2025-04-03
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 3 - ER | #FFFDA5 | EE1 | 2025-01-28 | 2025-02-10
COLO 4 | Cell 3 | Electrical Room | Anning - Johnson | Install Ceiling - COLO4 Cell 3 - ER | #3399FF | J17 | 2025-02-11 | 2025-02-13
COLO 4 | Cell 3 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO4 Cell 3 - ER | #987655 | GH3 | 2025-02-14 | 2025-02-20
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO4 Cell 3 - ER | #FFFDA5 | EE27 | 2025-02-17 | 2025-02-21
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO4 Cell 3 - ER | #FFFDA5 | EE23 | 2025-02-17 | 2025-02-21
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO4 Cell 3 - ER | #FFFDA5 | EE71 | 2025-02-17 | 2025-02-21
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | #FFFDA5 | EE72 | 2025-02-13 | 2025-02-26
COLO 4 | Cell 3 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO4 Cell 3 - ER | #3399FF | J36 | 2025-02-24 | 2025-02-28
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO4 Cell 3 - ER | #FFFDA5 | EE28 | 2025-02-25 | 2025-03-03
COLO 4 | Cell 3 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER | #FFFDA5 | EE29 | 2025-04-01 | 2025-04-21
COLO 4 | Cell 3 | Electrical Room | All Trades | Finishes and Signage - COLO4 Cell 3 - ER | #F2F2F2 | ALL3 | 2025-04-17 | 2025-04-23
COLO 4 | Cell 3 | Data Hall | Gurtz Electric | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH | #FFFDA5 | EE74 | 2025-01-28 | 2025-02-12
COLO 4 | Cell 3 | Data Hall | Anning - Johnson | Security Screen Installation - COLO4 Cell 3 - DH | #3399FF | J6 | 2025-02-18 | 2025-02-20
COLO 4 | Cell 3 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO4 Cell 3 - DH | #3399FF | J7 | 2025-02-21 | 2025-02-27
COLO 4 | Cell 3 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH | #FFFDA5 | EE73 | 2025-02-28 | 2025-03-13
COLO 4 | Cell 3 | Data Hall | Gurtz Electric | Install PDU's - COLO4 Cell 3 - DH | #FFFDA5 | EE7 | 2025-03-14 | 2025-03-20
COLO 4 | Cell 3 | Data Hall | Interior System | Begin HAC Assembly - COLO4 Cell 3 - DH | #FED7E8 | S1 | 2025-03-14 | 2025-03-20
COLO 4 | Cell 3 | Data Hall | Gurtz Electric | Install Busway - COLO4 Cell 3 - DH | #FFFDA5 | EE10 | 2025-03-18 | 2025-03-24
COLO 4 | Cell 3 | Data Hall | Interior System | HAC install and Rise - COLO4 Cell 3 - DH | #FED7E8 | S2 | 2025-03-21 | 2025-03-27
COLO 4 | Cell 3 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO4 Cell 3 - DH | #FFFDA5 | EE17 | 2025-03-21 | 2025-04-03
COLO 4 | Cell 3 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 3 - DH | #EF9E5B | ET7 | 2025-03-28 | 2025-04-10
COLO 4 | Cell 3 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO4 Cell 3 - DH | #FFFDA5 | EE18 | 2025-04-01 | 2025-04-21
COLO 4 | Cell 3 | Data Hall | All Trades | Finishes and Signage - COLO4 Cell 3 - DH | #F2F2F2 | ALL3 | 2025-04-15 | 2025-04-21
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO4 Cell 3 | #FFFDA5 | EE62 | 2025-02-24 | 2025-02-24
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO4 Cell 3 | #FFFDA5 | EE57 | 2025-02-24 | 2025-02-24
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO4 Cell 3 | #FFFDA5 | EE60 | 2025-02-24 | 2025-02-24
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO4 Cell 3 | #FFFDA5 | EE58 | 2025-02-24 | 2025-02-24
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO4 Cell 3 | #FFFDA5 | EE59 | 2025-02-25 | 2025-02-25
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO4 Cell 3 | #FFFDA5 | EE63 | 2025-03-21 | 2025-03-21
COLO 4 | Cell 3 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO4 Cell 3 | #FFFDA5 | EE61 | 2025-03-25 | 2025-03-25
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO4 Cell 3 | #FFFDA5 | EE57 | 2025-05-05 | 2025-05-09
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO4 Cell 3 | #FFFDA5 | EE62 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO4 Cell 3 | #FFFDA5 | EE63 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO4 Cell 3 | #FFFDA5 | EE58 | 2025-05-12 | 2025-05-16
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO4 Cell 3 | #FFFDA5 | EE60 | 2025-05-19 | 2025-05-23
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO4 Cell 3 | #FFFDA5 | EE61 | 2025-05-19 | 2025-05-23
COLO 4 | Cell 3 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO4 Cell 3 | #FFFDA5 | EE59 | 2025-05-27 | 2025-06-02
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO4 Cell 3 | #FFFDA5 | EE57 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO4 Cell 3 | #FFFDA5 | EE62 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO4 Cell 3 | #FFFDA5 | EE63 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO4 Cell 3 | #FFFDA5 | EE58 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO4 Cell 3 | #FFFDA5 | EE60 | 2025-10-20 | 2025-10-24
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO4 Cell 3 | #FFFDA5 | EE59 | 2025-10-27 | 2025-11-07
COLO 4 | Cell 3 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO4 Cell 3 | #FFFDA5 | EE61 | 2025-11-10 | 2025-11-14
COLO 4 | Cell 4 | Mech Gallery | Great Lakes Air Design | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG | #CFE741 | GA3 | 2025-01-14 | 2025-01-20
COLO 4 | Cell 4 | Mech Gallery | Gurtz Electric | Overhead MEP Installation - COLO4 Cell 4 - MG | #FFFDA5 | EE73 | 2025-01-24 | 2025-02-06
COLO 4 | Cell 4 | Mech Gallery | Great Lakes Air Design | Deliver AHU into Mech. Gallery - COLO4 Cell 4 - MG | #CFE741 | GA12 | 2025-02-07 | 2025-02-10
COLO 4 | Cell 4 | Mech Gallery | All - Tech | Install Walls and Primer Paint - COLO4 Cell 4 - MG | #D6F2FF | T3 | 2025-02-18 | 2025-03-03
COLO 4 | Cell 4 | Mech Gallery | Anning - Johnson | Layout Ceiling and install Pencile Rod - COLO4 Cell 4 - MG | #3399FF | J9 | 2025-03-04 | 2025-03-04
COLO 4 | Cell 4 | Mech Gallery | Great Lakes Air Design | Placing the AHU - COLO4 Cell 4 - MG | #CFE741 | GA6 | 2025-03-11 | 2025-03-13
COLO 4 | Cell 4 | Mech Gallery | Gurtz Electric | Post Wall Overhead MEP - COLO4 Cell 4 - MG | #FFFDA5 | EE70 | 2025-03-04 | 2025-03-24
COLO 4 | Cell 4 | Mech Gallery | Gurtz Electric Telecom | Piping and Electrical Termination to AHUs - COLO4 Cell 4 - MG | #EF9E5B | ET22 | 2025-03-13 | 2025-03-27
COLO 4 | Cell 4 | Mech Gallery | Inspections | Pipe Testing - COLO4 Cell 4 - MG | #C00000 | I-R | 2025-03-27 | 2025-03-31
COLO 4 | Cell 4 | Mech Gallery | Gurtz Electric | Install ceiling and Light Fittings - COLO4 Cell 4 - MG | #FFFDA5 | EE35 | 2025-03-31 | 2025-04-10
COLO 4 | Cell 4 | Mech Gallery | Gurtz Electric | Trim out MEP - COLO4 Cell 4 - MG | #FFFDA5 | EE36 | 2025-04-10 | 2025-04-17
COLO 4 | Cell 4 | Electrical Room | All - Tech | Install Walls and Primer Paint - COLO4 Cell 4 - ER | #D6F2FF | T3 | 2025-01-10 | 2025-01-23
COLO 4 | Cell 4 | Electrical Room | Anning - Johnson | Install Upper Screens - COLO4 Cell 4 - ER | #3399FF | J37 | 2025-01-21 | 2025-01-27
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 4 - ER | #FFFDA5 | EE1 | 2025-02-11 | 2025-02-24
COLO 4 | Cell 4 | Electrical Room | Anning - Johnson | Install Ceiling - COLO4 Cell 4 - ER | #3399FF | J17 | 2025-02-25 | 2025-02-27
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Installation of ADP & ATS - COLO4 Cell 4 - ER | #FFFDA5 | EE27 | 2025-02-27 | 2025-03-05
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Installation of TCP/MSB - COLO4 Cell 4 - ER | #FFFDA5 | EE71 | 2025-02-27 | 2025-03-05
COLO 4 | Cell 4 | Electrical Room | Great Lakes HVAC | Install DX Split Units - COLO4 Cell 4 - ER | #987655 | GH3 | 2025-02-28 | 2025-03-06
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Installation of UPS Equipment - COLO4 Cell 4 - ER | #FFFDA5 | EE23 | 2025-03-03 | 2025-03-07
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Connect to Cable tray and conduit equipment - COLO4 Cell 4 - ER | #FFFDA5 | EE28 | 2025-03-04 | 2025-03-10
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | #FFFDA5 | EE72 | 2025-02-27 | 2025-03-12
COLO 4 | Cell 4 | Electrical Room | Anning - Johnson | Door Frame Installation - COLO4 Cell 4 - ER | #3399FF | J36 | 2025-03-10 | 2025-03-14
COLO 4 | Cell 4 | Electrical Room | Gurtz Electric | Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER | #FFFDA5 | EE29 | 2025-04-22 | 2025-05-12
COLO 4 | Cell 4 | Electrical Room | All Trades | Finishes and Signage - COLO4 Cell 4 - ER | #F2F2F2 | ALL3 | 2025-05-06 | 2025-05-12
COLO 4 | Cell 4 | Data Hall | Gurtz Electric | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 4 - DH | #FFFDA5 | EE74 | 2025-02-13 | 2025-02-28
COLO 4 | Cell 4 | Data Hall | Anning - Johnson | Security Screen Installation - COLO4 Cell 4 - DH | #3399FF | J6 | 2025-03-04 | 2025-03-06
COLO 4 | Cell 4 | Data Hall | Anning - Johnson | Ceiling Grid and Tile - COLO4 Cell 4 - DH | #3399FF | J7 | 2025-03-07 | 2025-03-13
COLO 4 | Cell 4 | Data Hall | Gurtz Electric | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 4 - DH | #FFFDA5 | EE73 | 2025-03-14 | 2025-03-27
COLO 4 | Cell 4 | Data Hall | Gurtz Electric | Install PDU's - COLO4 Cell 4 - DH | #FFFDA5 | EE7 | 2025-03-28 | 2025-04-03
COLO 4 | Cell 4 | Data Hall | Interior System | Begin HAC Assembly - COLO4 Cell 4 - DH | #FED7E8 | S1 | 2025-03-28 | 2025-04-03
COLO 4 | Cell 4 | Data Hall | Gurtz Electric | Install Busway - COLO4 Cell 4 - DH | #FFFDA5 | EE10 | 2025-04-01 | 2025-04-07
COLO 4 | Cell 4 | Data Hall | Interior System | HAC install and Rise - COLO4 Cell 4 - DH | #FED7E8 | S2 | 2025-04-04 | 2025-04-10
COLO 4 | Cell 4 | Data Hall | Gurtz Electric | Cable Pulling at PDU & Busway- COLO4 Cell 4 - DH | #FFFDA5 | EE17 | 2025-04-04 | 2025-04-17
COLO 4 | Cell 4 | Data Hall | WALSH | Closing Construction Access Door - COLO4 Cell 4 - DH | #04A261 | W4 | 2025-04-04 | 2025-04-24
COLO 4 | Cell 4 | Data Hall | Gurtz Electric Telecom | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH | #EF9E5B | ET7 | 2025-04-11 | 2025-04-24
COLO 4 | Cell 4 | Data Hall | Gurtz Electric | Termination at PDU & Busway - COLO4 Cell 4 - DH | #FFFDA5 | EE18 | 2025-04-22 | 2025-05-12
COLO 4 | Cell 4 | Data Hall | All Trades | Finishes and Signage - COLO4 Cell 4 - DH | #F2F2F2 | ALL3 | 2025-05-06 | 2025-05-12
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 TCP/MSB - COLO4 Cell 4 | #FFFDA5 | EE57 | 2025-03-06 | 2025-03-10
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 ATSs - COLO4 Cell 4 | #FFFDA5 | EE60 | 2025-03-06 | 2025-03-10
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 ADP - COLO4 Cell 4 | #FFFDA5 | EE58 | 2025-03-06 | 2025-03-10
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 UPS - COLO4 Cell 4 | #FFFDA5 | EE62 | 2025-03-10 | 2025-03-12
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 AHUs - COLO4 Cell 4 | #FFFDA5 | EE59 | 2025-03-11 | 2025-03-13
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 PDUs - COLO4 Cell 4 | #FFFDA5 | EE63 | 2025-04-04 | 2025-04-08
COLO 4 | Cell 4 | CX - L1 | Gurtz Electric | Interior - L1 Busway - COLO4 Cell 4 | #FFFDA5 | EE61 | 2025-04-08 | 2025-04-10
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 TCP/MSB - COLO4 Cell 4 | #FFFDA5 | EE57 | 2025-05-13 | 2025-05-19
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 UPS - COLO4 Cell 4 | #FFFDA5 | EE62 | 2025-05-20 | 2025-05-27
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 PDUs - COLO4 Cell 4 | #FFFDA5 | EE63 | 2025-05-20 | 2025-05-27
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ADP - COLO4 Cell 4 | #FFFDA5 | EE58 | 2025-05-20 | 2025-05-27
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 ATSs - COLO4 Cell 4 | #FFFDA5 | EE60 | 2025-05-28 | 2025-06-03
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 Busway - COLO4 Cell 4 | #FFFDA5 | EE61 | 2025-05-28 | 2025-06-03
COLO 4 | Cell 4 | CX - L2 | Gurtz Electric | Interior - L2 AHUs - COLO4 Cell 4 | #FFFDA5 | EE59 | 2025-07-16 | 2025-07-23
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 TCP/MSB - COLO4 Cell 4 | #FFFDA5 | EE57 | 2025-10-06 | 2025-10-10
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 UPS - COLO4 Cell 4 | #FFFDA5 | EE62 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 PDUs - COLO4 Cell 4 | #FFFDA5 | EE63 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ADP - COLO4 Cell 4 | #FFFDA5 | EE58 | 2025-10-13 | 2025-10-17
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 ATSs - COLO4 Cell 4 | #FFFDA5 | EE60 | 2025-10-20 | 2025-10-24
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 AHUs - COLO4 Cell 4 | #FFFDA5 | EE59 | 2025-10-27 | 2025-11-07
COLO 4 | Cell 4 | CX - L3 | Gurtz Electric | Interior - L3 Busway - COLO4 Cell 4 | #FFFDA5 | EE61 | 2025-11-10 | 2025-11-14
COLO 4 | All | CX - Microsoft | Microsoft | Level 4 Cx - Colo 4 | #000000 | MS1 | 2025-11-18 | 2025-12-16
COLO 4 | All | CX - Microsoft | Microsoft | Level 5 Cx / IST - Colo 4 | #000000 | MS2 | 2025-12-18 | 2025-12-19
Fiber | All | All | WALSH | MVS Fiber Procurement | #04A261 | W15 | 2024-12-09 | 2025-01-31
Fiber | All | All | WALSH | MVS Fiber Shipping | #04A261 | W16 | 2025-02-03 | 2025-02-14
Fiber | All | All | Gurtz Electric Telecom | Pull, Splice, & Test (3) UTS Fiber | #EF9E5B | ET30 | 2025-02-17 | 2025-03-13
Fiber | All | All | Gurtz Electric Telecom | Pull, Splice, & Test (5) UMS/URS Fiber | #EF9E5B | ET31 | 2025-02-17 | 2025-03-13
Fiber | COLO 2 | All | WALSH | Generator CEI Fiber Shipping Colo 2 | #04A261 | W6 | 2024-12-23 | 2025-01-22
Fiber | COLO 2 | All | WALSH | Backbone CEI Fiber Shipping Colo 2 | #04A261 | W7 | 2025-01-10 | 2025-01-23
Fiber | COLO 2 | All | WALSH | Interior CEI CAT6 Procurement Colo 2 | #04A261 | W9 | 2024-12-09 | 2025-01-28
Fiber | COLO 2 | All | Gurtz Electric | Pull Generator Fiber Colo 2 | #FFFDA5 | EE87 | 2025-01-23 | 2025-01-29
Fiber | COLO 2 | All | Gurtz Electric Telecom | Pull Backbone Fiber Colo 2 (CEI to FCR) | #EF9E5B | ET24 | 2025-01-24 | 2025-02-06
Fiber | COLO 2 | All | WALSH | Interior CEI CAT6 Shipping Colo 2 | #04A261 | W9 | 2025-01-29 | 2025-02-11
Fiber | COLO 2 | All | WALSH | 3456 Fiber Procurement Colo 2 | #04A261 | W12 | 2024-12-02 | 2025-03-05
Fiber | COLO 2 | All | WALSH | 288 Fiber Procurement Colo 2 | #04A261 | W11 | 2024-12-02 | 2025-03-10
Fiber | COLO 2 | All | Gurtz Electric Telecom | Pull Interior CEI CAT6 Colo 2 | #EF9E5B | ET28 | 2025-02-12 | 2025-03-11
Fiber | COLO 2 | All | WALSH | 3456 Fiber Shipping Colo 2 | #04A261 | W14 | 2025-03-06 | 2025-03-19
Fiber | COLO 2 | All | WALSH | 288 Fiber Shipping Colo 2 | #04A261 | W13 | 2025-03-11 | 2025-03-24
Fiber | COLO 2 | All | Gurtz Electric Telecom | Pull, Splice, & Test UPM Fiber Colo 2 | #EF9E5B | ET32 | 2025-03-14 | 2025-03-27
Fiber | COLO 2 | All | Gurtz Electric Telecom | 3456 Fiber Install, Populate, & Test Colo 2 | #EF9E5B | ET9 | 2025-03-20 | 2025-04-23
Fiber | COLO 2 | All | Gurtz Electric Telecom | 288 Fiber Install, Populate, & Test Colo 2 | #EF9E5B | ET11 | 2025-03-25 | 2025-05-19
Fiber | COLO 2 | All | Gurtz Electric Telecom | RNI Colo 2 | #EF9E5B | ET29 | 2025-05-20 | 2025-05-20
Fiber | COLO 3 | All | WALSH | Backbone CEI Fiber Procurement Colo 3 | #04A261 | W5 | 2024-12-09 | 2025-01-23
Fiber | COLO 3 | All | WALSH | Generator CEI Fiber Shipping Colo 3 | #04A261 | W6 | 2025-01-10 | 2025-01-24
Fiber | COLO 3 | All | WALSH | Backbone CEI Fiber Shipping Colo 3 | #04A261 | W7 | 2025-01-16 | 2025-01-29
Fiber | COLO 3 | All | WALSH | Interior CEI CAT6 Procurement Colo 3 | #04A261 | W9 | 2024-12-09 | 2025-02-11
Fiber | COLO 3 | All | Gurtz Electric | Pull Generator Fiber Colo 3 | #FFFDA5 | EE87 | 2025-02-06 | 2025-02-12
Fiber | COLO 3 | All | WALSH | Interior CEI CAT6 Shipping Colo 3 | #04A261 | W10 | 2025-02-12 | 2025-02-25
Fiber | COLO 3 | All | WALSH | 3456 Fiber Procurement Colo 3 | #04A261 | W12 | 2024-12-02 | 2025-03-05
Fiber | COLO 3 | All | Gurtz Electric Telecom | Pull Backbone Fiber Colo 3 (CEI to FCR) | #EF9E5B | ET24 | 2025-02-21 | 2025-03-06
Fiber | COLO 3 | All | WALSH | 3456 Fiber Shipping Colo 3 | #04A261 | W14 | 2025-03-06 | 2025-03-19
Fiber | COLO 3 | All | WALSH | 288 Fiber Procurement Colo 3 | #04A261 | W11 | 2024-12-02 | 2025-03-25
Fiber | COLO 3 | All | Gurtz Electric Telecom | Colo 3 UPM Ready for Fiber (L1 Complete Per Option 1) | #EF9E5B | ET26 | 2025-04-07 | 2025-04-07
Fiber | COLO 3 | All | WALSH | 288 Fiber Shipping Colo 3 | #04A261 | W13 | 2025-03-26 | 2025-04-08
Fiber | COLO 3 | All | Gurtz Electric Telecom | Pull, Splice, & Test UPM Fiber Colo 3 | #EF9E5B | ET32 | 2025-03-28 | 2025-04-10
Fiber | COLO 3 | All | Gurtz Electric Telecom | Pull Interior CEI CAT 6 Colo 3 | #EF9E5B | ET28 | 2025-04-09 | 2025-05-06
Fiber | COLO 3 | All | Gurtz Electric Telecom | Colo 3 UPM Ready for Fiber (L1 Complete Per Option 2) | #EF9E5B | ET27 | 2025-05-30 | 2025-05-30
Fiber | COLO 3 | All | Gurtz Electric Telecom | 3456 Fiber Install, Populate, & Test Colo 3 | #EF9E5B | ET9 | 2025-06-05 | 2025-07-09
Fiber | COLO 3 | All | Gurtz Electric Telecom | 288 Fiber Install, Populate, & Test Colo 3 | #EF9E5B | ET11 | 2025-07-15 | 2025-09-08
Fiber | COLO 3 | All | Gurtz Electric Telecom | RNI Colo 3 | #EF9E5B | ET29 | 2025-09-09 | 2025-09-09
Fiber | COLO 4 | All | WALSH | Backbone CEI Fiber Procurement Colo 4 | #04A261 | W5 | 2024-12-09 | 2025-01-27
Fiber | COLO 4 | All | WALSH | Generator CEI Fiber Procurement Colo 4 | #04A261 | W6 | 2024-12-09 | 2025-02-07
Fiber | COLO 4 | All | WALSH | Backbone CEI Fiber Shipping Colo 4 | #04A261 | W7 | 2025-01-28 | 2025-02-10
Fiber | COLO 4 | All | WALSH | Generator CEI Fiber Shipping Colo 4 | #04A261 | W8 | 2025-02-10 | 2025-02-21
Fiber | COLO 4 | All | WALSH | Interior CEI CAT6 Procurement Colo 4 | #04A261 | W9 | 2024-12-09 | 2025-02-25
Fiber | COLO 4 | All | Gurtz Electric | Pull Generator CAT6 Colo 4 | #FFFDA5 | EE87 | 2025-02-24 | 2025-02-28
Fiber | COLO 4 | All | WALSH | Interior CEI Fiber Shipping Colo 4 | #04A261 | W10 | 2025-02-26 | 2025-03-11
Fiber | COLO 4 | All | Gurtz Electric Telecom | Pull Backbone Fiber Colo 4 (CEI to FCR) | #EF9E5B | ET24 | 2025-03-07 | 2025-03-20
Fiber | COLO 4 | All | WALSH | 288 Fiber Procurement Colo 4 | #04A261 | W11 | 2024-12-02 | 2025-03-24
Fiber | COLO 4 | All | WALSH | 3456 Fiber Procurement Colo 4 | #04A261 | W12 | 2024-12-02 | 2025-03-31
Fiber | COLO 4 | All | WALSH | 288 Fiber Shipping Colo 4 | #04A261 | W13 | 2025-03-25 | 2025-04-07
Fiber | COLO 4 | All | WALSH | 3456 Fiber Shipping Colo 4 | #04A261 | W14 | 2025-04-01 | 2025-04-14
Fiber | COLO 4 | All | Gurtz Electric Telecom | Pull, Splice, & Test UPM Fiber Colo 4 | #EF9E5B | ET25 | 2025-04-11 | 2025-04-24
Fiber | COLO 4 | All | Gurtz Electric Telecom | Colo 4 UPM Ready for Fiber (L1 Complete Option 1) | #EF9E5B | ET26 | 2025-05-08 | 2025-05-08
Fiber | COLO 4 | All | Gurtz Electric Telecom | Colo 4 UPM Ready for Fiber (L1 Complete Option 2) | #EF9E5B | ET27 | 2025-05-30 | 2025-05-30
Fiber | COLO 4 | All | Gurtz Electric Telecom | Pull Interior Fiber Colo 4 | #EF9E5B | ET28 | 2025-05-07 | 2025-06-03
Fiber | COLO 4 | All | Gurtz Electric Telecom | 3456 Fiber Install, Populate, & Test Colo 4 | #EF9E5B | ET9 | 2025-07-10 | 2025-08-13
Fiber | COLO 4 | All | Gurtz Electric Telecom | 288 Fiber Install, Populate, & Test Colo 4 | #EF9E5B | ET11 | 2025-09-09 | 2025-11-03
Fiber | COLO 4 | All | Gurtz Electric Telecom | RNI Colo 4 | #EF9E5B | ET29 | 2025-11-04 | 2025-11-04
Fiber | COLO 5 | All | WALSH | Generator CEI Fiber Shipping Colo 5 | #04A261 | W8 | 2024-12-23 | 2025-01-22
Fiber | COLO 5 | All | WALSH | Backbone CEI Fiber Shipping Colo 5 | #04A261 | W7 | 2025-01-10 | 2025-01-23
Fiber | COLO 5 | All | Gurtz Electric | Pull Generator Fiber Colo 5 | #FFFDA5 | EE87 | 2025-01-30 | 2025-02-05
Fiber | COLO 5 | All | WALSH | Interior CEI Fiber Procurement Colo 5 | #04A261 | W9 | 2024-12-09 | 2025-02-11
Fiber | COLO 5 | All | WALSH | 288 Fiber Procurement Colo 5 | #04A261 | W11 | 2024-12-02 | 2025-02-12
Fiber | COLO 5 | All | Gurtz Electric Telecom | Pull Backbone Fiber Colo 5 (CEI to FCR) | #EF9E5B | ET24 | 2025-02-07 | 2025-02-20
Fiber | COLO 5 | All | WALSH | Interior CEI CAT6 Shipping Colo 5 | #04A261 | W10 | 2025-02-12 | 2025-02-25
Fiber | COLO 5 | All | WALSH | 288 Fiber Shipping Colo 5 | #04A261 | W13 | 2025-02-13 | 2025-02-26
Fiber | COLO 5 | All | WALSH | 3456 Fiber Procurement Colo 5 | #04A261 | W12 | 2024-12-02 | 2025-03-05
Fiber | COLO 5 | All | WALSH | 3456 Fiber Shipping Colo 5 | #04A261 | W14 | 2025-03-06 | 2025-03-19
Fiber | COLO 5 | All | Gurtz Electric Telecom | Pull Interior CAT6 Colo 5 | #EF9E5B | ET28 | 2025-03-12 | 2025-04-08
Fiber | COLO 5 | All | Gurtz Electric Telecom | Pull, Splice, & Test UPM Fiber Colo 5 | #EF9E5B | ET32 | 2025-03-28 | 2025-04-10
Fiber | COLO 5 | All | Gurtz Electric Telecom | Colo 5 UPM Ready for Fiber (L1 Complete Per Option 1) | #EF9E5B | ET26 | 2025-05-29 | 2025-05-29
Fiber | COLO 5 | All | Gurtz Electric Telecom | 3456 Fiber Install, Populate, & Test Colo 5 | #EF9E5B | ET9 | 2025-04-24 | 2025-06-04
Fiber | COLO 5 | All | Gurtz Electric Telecom | Colo 5 UPM Ready for Fiber (L1 Complete Per Option 2) | #EF9E5B | ET27 | 2025-06-17 | 2025-06-17
Fiber | COLO 5 | All | Gurtz Electric Telecom | 288 Fiber Install, Populate, & Test Colo 5 | #EF9E5B | ET11 | 2025-05-20 | 2025-07-14
Fiber | COLO 5 | All | Gurtz Electric Telecom | RNI Colo 5 | #EF9E5B | ET29 | 2025-07-15 | 2025-07-15
UPM | COLO 2 | Site | Gurtz Electric | Relocate 2 UPMs to Colo 2 | #FFFDA5 | EE75 | 2025-01-17 | 2025-01-20
UPM | COLO 2 | Site | Gurtz Electric | Term Wires to Relocated UPMs (2) | #FFFDA5 | EE76 | 2025-01-21 | 2025-02-10
UPM | COLO 2 | Site | Gurtz Electric | Complete L1 on Relocated UPMs | #FFFDA5 | EE77 | 2025-02-11 | 2025-02-11
UPM | COLO 3 | Site | Gurtz Electric | UPM ROJ (Qty: 4) | #FFFDA5 | EE78 | 2025-01-06 | 2025-05-30
UPM | COLO 3 | Site | Gurtz Electric | Install UPM (Total 4) | #FFFDA5 | EE79 | 2025-06-02 | 2025-06-11
UPM | COLO 3 | Site | Gurtz Electric | L1 UPM | #FFFDA5 | EE80 | 2025-06-13 | 2025-06-13
UPM | COLO 3 | Site | Gurtz Electric | Complete Wire Terms | #FFFDA5 | EE81 | 2025-06-16 | 2025-07-04
UPM | COLO 4 | Site | Gurtz Electric | UPM ROJ (Qty: 4) | #FFFDA5 | EE78 | 2025-01-06 | 2025-05-30
UPM | COLO 4 | Site | Gurtz Electric | Install UPM (Total 4) | #FFFDA5 | EE79 | 2025-06-12 | 2025-06-23
UPM | COLO 4 | Site | Gurtz Electric | L1 UPM | #FFFDA5 | EE80 | 2025-06-24 | 2025-06-24
UPM | COLO 4 | Site | Gurtz Electric | Complete Wire Terms | #FFFDA5 | EE81 | 2025-06-25 | 2025-07-15
UPM | COLO 5 | Site | Gurtz Electric | UPM ROJ (Qty: 3) | #FFFDA5 | EE78 | 2025-01-06 | 2025-05-30
UPM | COLO 5 | Site | Gurtz Electric | Install UPM (Total 3) | #FFFDA5 | EE79 | 2025-06-02 | 2025-06-09
UPM | COLO 5 | Site | Gurtz Electric | L1 UPM | #FFFDA5 | EE80 | 2025-06-10 | 2025-06-10
UPM | COLO 5 | Site | Gurtz Electric | Complete Wire Terms | #FFFDA5 | EE81 | 2025-06-11 | 2025-06-24
Exhaust System | Non-Installed Sets | All | WALSH | (8) Sets Returned to Manufacture | #04A261 | W16 | 2025-01-21 | 2025-01-22
Exhaust System | Non-Installed Sets | All | WALSH | (8) Sets Re-Finished | #04A261 | W17 | 2025-01-23 | 2025-02-06
Exhaust System | Non-Installed Sets | All | WALSH | (8) Sets Shipped Back to Jobsite | #04A261 | W18 | 2025-02-07 | 2025-02-08
Exhaust System | Installed Sets | All | Gurtz Electric | (8) Remove Installed Set Off of Generators | #FFFDA5 | EE82 | 2025-01-21 | 2025-02-19
Exhaust System | Installed Sets | All | WALSH | (8) Sets Returned to Manufacture | #04A261 | W16 | 2025-02-20 | 2025-02-21
Exhaust System | Installed Sets | All | WALSH | (8) Sets Re-Finished | #04A261 | W17 | 2025-02-22 | 2025-03-07
Exhaust System | Installed Sets | All | WALSH | (8) Sets Shipped Back to Jobsite | #04A261 | W18 | 2025-03-08 | 2025-03-10
Exhaust System | COLO 2 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SW) | #FFFDA5 | EE82 | 2025-02-17 | 2025-02-19
Exhaust System | COLO 2 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SE) | #FFFDA5 | EE83 | 2025-02-20 | 2025-02-22
Exhaust System | COLO 2 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NE) | #FFFDA5 | EE84 | 2025-02-24 | 2025-02-26
Exhaust System | COLO 2 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NW) | #FFFDA5 | EE85 | 2025-02-27 | 2025-03-01
Exhaust System | COLO 5 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SE) | #FFFDA5 | EE86 | 2025-02-10 | 2025-02-12
Exhaust System | COLO 5 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NE) | #FFFDA5 | EE85 | 2025-02-13 | 2025-02-15
Exhaust System | COLO 5 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NW) | #FFFDA5 | EE86 | 2025-03-03 | 2025-03-05
Exhaust System | COLO 5 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SW) | #FFFDA5 | EE83 | 2025-03-06 | 2025-03-08
Exhaust System | COLO 3 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SW) | #FFFDA5 | EE83 | 2025-03-11 | 2025-03-13
Exhaust System | COLO 3 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SE) | #FFFDA5 | EE84 | 2025-03-14 | 2025-03-17
Exhaust System | COLO 3 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NE) | #FFFDA5 | EE85 | 2025-04-01 | 2025-04-03
Exhaust System | COLO 3 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NW) | #FFFDA5 | EE86 | 2025-04-04 | 2025-04-07
Exhaust System | COLO 4 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SW) | #FFFDA5 | EE83 | 2025-03-18 | 2025-03-20
Exhaust System | COLO 4 | All | Gurtz Electric | Assemble & Install Exhaust System Set (SE) | #FFFDA5 | EE84 | 2025-03-21 | 2025-03-24
Exhaust System | COLO 4 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NE) | #FFFDA5 | EE85 | 2025-03-25 | 2025-03-27
Exhaust System | COLO 4 | All | Gurtz Electric | Assemble & Install Exhaust System Set (NW) | #FFFDA5 | EE86 | 2025-03-28 | 2025-03-31