## Sheet1
Phase | Location | Trade | Color | Activity Code | Activity Name | Start | Finish
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG | 2024-10-07 08:00 | 2024-10-11 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 1 - MG | 2024-10-09 08:00 | 2024-10-15 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER | 2024-11-19 08:00 | 2024-12-03 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO2 Cell 1 - MG | 2024-10-30 08:00 | 2024-10-31 17:00
Fitout | COLO 2 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO2 Cell 1 - MG | 2024-11-01 08:00 | 2024-11-14 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO2 Cell 1 - MG | 2024-11-22 08:00 | 2024-11-26 12:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO2 Cell 1 - MG | 2024-11-15 08:00 | 2024-11-15 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER | 2024-12-18 08:00 | 2025-01-09 17:00
Fitout | COLO 2 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO2 Cell 1 - MG | 2024-12-13 13:00 | 2024-12-26 12:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO2 Cell 2 - ER | 2024-12-04 08:00 | 2024-12-17 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO2 Cell 2 - ER | 2025-01-10 08:00 | 2025-01-30 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO2 Cell 3 - ER | 2024-12-18 08:00 | 2025-01-02 17:00
Fitout | COLO 2 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO2 Cell 1 - DH | 2024-12-19 08:00 | 2024-12-26 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO2 Cell 3 - ER | 2025-01-31 08:00 | 2025-02-20 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A2 | Security Screen Installation - COLO2 Cell 1 - DH | 2024-11-15 08:00 | 2024-11-19 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A3 | Ceiling Grid and Tile - COLO2 Cell 1 - DH | 2024-11-20 08:00 | 2024-11-26 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO2 Cell 4 - ER | 2025-01-03 08:00 | 2025-01-16 17:00
Fitout | COLO 2 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 1 - DH | 2024-12-27 08:00 | 2025-01-10 17:00
Fitout | COLO 2 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO2 Cell 1 - DH | 2025-01-14 08:00 | 2025-01-20 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO2 Cell 4 - ER | 2025-02-21 08:00 | 2025-03-13 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO3 Cell 1 - ER | 2025-01-13 08:00 | 2025-01-31 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO3 Cell 2 - ER | 2025-02-03 08:00 | 2025-02-21 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO3 Cell 1 - ER | 2024-12-16 08:00 | 2024-12-30 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO3 Cell 3 - ER | 2025-02-24 08:00 | 2025-03-14 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO3 Cell 2 - ER | 2024-12-31 08:00 | 2025-01-14 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO3 Cell 4 - ER | 2025-03-17 08:00 | 2025-04-04 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO4 Cell 1 - ER | 2025-02-19 08:00 | 2025-03-11 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO4 Cell 2 - ER | 2025-03-12 08:00 | 2025-04-01 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO3 Cell 3 - ER | 2025-01-15 08:00 | 2025-01-28 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO4 Cell 3 - ER | 2025-04-02 08:00 | 2025-04-22 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO3 Cell 4 - ER | 2025-01-29 08:00 | 2025-02-11 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO4 Cell 4 - ER | 2025-04-23 08:00 | 2025-05-13 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO5 Cell 1 - ER | 2024-12-17 08:00 | 2025-01-08 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO5 Cell 2 - ER | 2025-01-09 08:00 | 2025-01-29 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO4 Cell 1 - ER | 2025-02-06 08:00 | 2025-02-19 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO5 Cell 3 - ER | 2025-01-30 08:00 | 2025-02-19 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO4 Cell 2 - ER | 2025-02-24 08:00 | 2025-03-07 17:00
Fitout | COLO 2 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO2 Cell 1 - ER | 2024-10-07 08:00 | 2024-10-18 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO4 Cell 3 - ER | 2025-03-10 08:00 | 2025-03-21 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A4 | Install Upper Screens - COLO2 Cell 1 - ER | 2024-10-16 08:00 | 2024-10-22 17:00
Fitout | COLO 2 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO2 Cell 1 - ER | 2024-11-06 08:00 | 2024-11-08 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO4 Cell 4 - ER | 2025-03-24 08:00 | 2025-04-04 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E1 | Cable Pulling at Elec. Equipment - COLO5 Cell 4 - ER | 2025-02-20 08:00 | 2025-03-12 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH | 2024-12-30 08:00 | 2025-01-20 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway - COLO3 Cell 1 - DH | 2025-01-22 08:00 | 2025-02-11 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A5 | Door Frame Installation - COLO2 Cell 1 - ER | 2025-01-03 08:00 | 2025-01-09 17:00
Fitout | COLO 2 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO2 Cell 1 - ER | 2025-01-10 08:00 | 2025-01-16 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway - COLO4 Cell 1 - DH | 2025-02-20 08:00 | 2025-03-12 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 2 - MG | 2024-10-14 08:00 | 2024-10-18 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 2 - MG | 2024-10-16 08:00 | 2024-10-22 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO5 Cell 1 - ER | 2024-11-11 08:00 | 2024-11-22 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO2 Cell 2 - MG | 2024-11-13 08:00 | 2024-11-14 17:00
Fitout | COLO 2 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO2 Cell 2 - MG | 2024-11-15 08:00 | 2024-11-29 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO2 Cell 2 - MG | 2024-12-09 08:00 | 2024-12-11 12:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO2 Cell 2 - MG | 2024-12-02 08:00 | 2024-12-02 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway - COLO5 Cell 1 - DH | 2024-12-26 08:00 | 2025-01-16 17:00
Fitout | COLO 2 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO2 Cell 2 - MG | 2024-12-30 13:00 | 2025-01-10 12:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO5 Cell 2 - ER | 2024-11-25 08:00 | 2024-12-09 17:00
Fitout | COLO 2 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO2 Cell 2 - ER | 2024-10-21 08:00 | 2024-11-01 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO5 Cell 3 - ER | 2024-12-10 08:00 | 2024-12-23 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO2 Cell 2 - ER | 2024-10-30 08:00 | 2024-11-05 17:00
Fitout | COLO 2 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO2 Cell 2 - ER | 2024-11-20 08:00 | 2024-11-22 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG1 | Below Ceiling MEP Rough In - COLO5 Cell 4 - ER | 2024-12-24 08:00 | 2025-01-08 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway - COLO5 Cell 2 - DH | 2025-01-24 08:00 | 2025-02-13 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway- COLO2 Cell 2 - DH | 2025-01-06 08:00 | 2025-01-17 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway- COLO2 Cell 3 - DH | 2025-01-20 08:00 | 2025-01-31 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO2 Cell 2 - ER | 2025-01-03 08:00 | 2025-01-09 17:00
Fitout | COLO 2 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO2 Cell 2 - ER | 2025-01-28 08:00 | 2025-02-03 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway- COLO2 Cell 4 - DH | 2025-02-03 08:00 | 2025-02-14 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway- COLO3 Cell 2 - DH | 2025-02-05 08:00 | 2025-02-18 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO2 Cell 1 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO2 Cell 2 - DH | 2025-01-06 08:00 | 2025-01-10 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway- COLO3 Cell 3 - DH | 2025-02-19 08:00 | 2025-03-04 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO2 Cell 2 - DH | 2024-12-02 08:00 | 2024-12-04 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO2 Cell 2 - DH | 2024-12-05 08:00 | 2024-12-11 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO2 Cell 2 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 2 - DH | 2025-01-13 08:00 | 2025-01-24 17:00
Fitout | COLO 2 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO2 Cell 2 - DH | 2025-02-04 08:00 | 2025-02-10 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway- COLO3 Cell 4 - DH | 2025-03-05 08:00 | 2025-03-18 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway- COLO4 Cell 2 - DH | 2025-03-10 08:00 | 2025-03-21 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway- COLO4 Cell 3 - DH | 2025-03-25 08:00 | 2025-04-07 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO2 Cell 3 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway- COLO4 Cell 4 - DH | 2025-04-10 08:00 | 2025-04-23 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO2 Cell 4 | 2025-01-28 08:00 | 2025-01-28 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway- COLO5 Cell 3 - DH | 2025-02-07 08:00 | 2025-02-20 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E2 | Cable Pulling at PDU & Busway- COLO5 Cell 4 - DH | 2025-02-21 08:00 | 2025-03-06 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E3 | Install Generator - Colo 2 - North | 2024-11-19 08:00 | 2024-11-25 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO3 Cell 1 | 2025-02-04 08:00 | 2025-02-04 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E3 | Install Generator - Colo 2 - South | 2024-11-19 08:00 | 2024-11-25 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO3 Cell 2 | 2025-02-05 08:00 | 2025-02-05 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E3 | Install Generator - Colo 3 - North | 2024-11-25 08:00 | 2024-12-02 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E3 | Install Generator - Colo 3 - South | 2024-11-25 08:00 | 2024-12-02 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E3 | Install Generator - Colo 4 - North | 2024-12-10 08:00 | 2024-12-16 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO3 Cell 3 | 2025-02-06 08:00 | 2025-02-06 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E3 | Install Generator - Colo 4 - South | 2024-12-10 08:00 | 2024-12-16 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO3 Cell 4 | 2025-02-14 08:00 | 2025-02-14 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 3 - MG | 2024-10-21 08:00 | 2024-10-25 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 3 - MG | 2024-10-23 08:00 | 2024-10-29 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO4 Cell 1 | 2025-02-24 08:00 | 2025-02-24 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO2 Cell 3 - MG | 2024-11-27 08:00 | 2024-11-29 17:00
Fitout | COLO 2 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO2 Cell 3 - MG | 2024-12-02 08:00 | 2024-12-13 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO2 Cell 3 - MG | 2024-12-23 08:00 | 2024-12-26 12:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO2 Cell 3 - MG | 2024-12-16 08:00 | 2024-12-16 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E3 | Install Generator - Colo 5 - East | 2024-12-10 08:00 | 2024-12-16 17:00
Fitout | COLO 2 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO2 Cell 3 - MG | 2025-01-14 13:00 | 2025-01-24 12:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO4 Cell 2 | 2025-03-12 08:00 | 2025-03-12 17:00
Fitout | COLO 2 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO2 Cell 3 - ER | 2024-11-04 08:00 | 2024-11-15 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO4 Cell 3 | 2025-03-26 08:00 | 2025-03-26 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO2 Cell 3 - ER | 2024-11-13 08:00 | 2024-11-19 17:00
Fitout | COLO 2 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO2 Cell 3 - ER | 2024-12-05 08:00 | 2024-12-09 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO4 Cell 4 | 2025-04-08 08:00 | 2025-04-08 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E3 | Install Generator - Colo 5 - West | 2024-12-10 08:00 | 2024-12-16 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E4 | Install MEP raceway conduit and piping - Colo 2 - North | 2024-10-10 08:00 | 2024-10-30 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E4 | Install MEP raceway conduit and piping - Colo 2 - South | 2024-09-19 08:00 | 2024-10-09 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO2 Cell 3 - ER | 2025-01-10 08:00 | 2025-01-16 17:00
Fitout | COLO 2 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO2 Cell 3 - ER | 2025-02-18 08:00 | 2025-02-24 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E4 | Install MEP raceway conduit and piping - Colo 3 - North | 2024-10-17 08:00 | 2024-11-06 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E4 | Install MEP raceway conduit and piping - Colo 3 - South | 2024-09-26 08:00 | 2024-10-16 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO5 Cell 1 | 2024-12-16 08:00 | 2024-12-16 17:00
Fitout | COLO 2 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO2 Cell 3 - DH | 2025-01-20 08:00 | 2025-01-24 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E4 | Install MEP raceway conduit and piping - Colo 4 - North | 2024-10-24 08:00 | 2024-11-13 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO2 Cell 3 - DH | 2024-12-16 08:00 | 2024-12-18 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO2 Cell 3 - DH | 2024-12-19 08:00 | 2024-12-26 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO5 Cell 2 | 2024-12-23 08:00 | 2024-12-23 17:00
Fitout | COLO 2 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 3 - DH | 2025-01-27 08:00 | 2025-02-07 17:00
Fitout | COLO 2 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO2 Cell 3 - DH | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E4 | Install MEP raceway conduit and piping - Colo 4 - South | 2024-10-03 08:00 | 2024-10-23 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E4 | Install MEP raceway conduit and piping - Colo 5 - East | 2024-09-10 08:00 | 2024-09-30 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E4 | Install MEP raceway conduit and piping - Colo 5 - West | 2024-10-31 08:00 | 2024-11-20 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO5 Cell 3 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E5 | Install MV Gear - Colo 2 - North | 2024-10-31 08:00 | 2024-11-06 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG2 | Interior - L1 ADP - COLO5 Cell 4 | 2025-01-08 08:00 | 2025-01-08 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E5 | Install MV Gear - Colo 2 - South | 2024-10-10 08:00 | 2024-10-16 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E5 | Install MV Gear - Colo 3 - North | 2024-11-07 08:00 | 2024-11-13 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E5 | Install MV Gear - Colo 3 - South | 2024-10-17 08:00 | 2024-10-23 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO2 Cell 1 | 2025-01-08 08:00 | 2025-01-08 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E5 | Install MV Gear - Colo 4 - North | 2024-11-14 08:00 | 2024-11-20 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO2 Cell 2 | 2025-01-08 08:00 | 2025-01-08 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E5 | Install MV Gear - Colo 4 - South | 2024-10-24 08:00 | 2024-10-30 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E5 | Install MV Gear - Colo 5 - East | 2024-10-09 08:00 | 2024-10-15 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E5 | Install MV Gear - Colo 5 - West | 2024-11-21 08:00 | 2024-11-27 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO2 Cell 3 | 2025-01-22 08:00 | 2025-01-22 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO2 Cell 1 - ER | 2024-11-29 08:00 | 2024-12-05 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO2 Cell 4 | 2025-02-05 08:00 | 2025-02-05 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 4 - MG | 2024-10-28 08:00 | 2024-11-01 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO2 Cell 4 - MG | 2024-10-30 08:00 | 2024-11-05 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO3 Cell 1 | 2025-02-06 08:00 | 2025-02-06 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO2 Cell 4 - MG | 2024-12-12 08:00 | 2024-12-13 17:00
Fitout | COLO 2 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO2 Cell 4 - MG | 2024-12-16 08:00 | 2024-12-30 17:00
Fitout | COLO 2 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO2 Cell 4 - MG | 2025-01-08 08:00 | 2025-01-10 12:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO2 Cell 4 - MG | 2024-12-31 08:00 | 2024-12-31 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO2 Cell 2 - ER | 2024-12-06 08:00 | 2024-12-12 17:00
Fitout | COLO 2 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO2 Cell 4 - MG | 2025-01-28 13:00 | 2025-02-07 12:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO3 Cell 2 | 2025-02-07 08:00 | 2025-02-07 17:00
Fitout | COLO 2 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO2 Cell 4 - ER | 2024-11-18 08:00 | 2024-12-02 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO3 Cell 3 | 2025-02-21 08:00 | 2025-02-21 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO2 Cell 4 - ER | 2024-11-27 08:00 | 2024-12-04 17:00
Fitout | COLO 2 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO2 Cell 4 - ER | 2024-12-19 08:00 | 2024-12-23 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO3 Cell 4 | 2025-03-07 08:00 | 2025-03-07 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO2 Cell 3 - ER | 2024-12-20 08:00 | 2024-12-27 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO2 Cell 4 - ER | 2025-01-07 08:00 | 2025-01-13 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO3 Cell 1 - ER | 2025-01-02 08:00 | 2025-01-08 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO2 Cell 4 - ER | 2025-01-24 08:00 | 2025-01-30 17:00
Fitout | COLO 2 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO2 Cell 4 - ER | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO3 Cell 2 - ER | 2025-01-09 08:00 | 2025-01-15 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO3 Cell 3 - ER | 2025-01-17 08:00 | 2025-01-23 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO4 Cell 1 | 2025-02-26 08:00 | 2025-02-26 17:00
Fitout | COLO 2 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO2 Cell 4 - DH | 2025-02-03 08:00 | 2025-02-07 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO3 Cell 4 - ER | 2025-01-31 08:00 | 2025-02-06 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO2 Cell 4 - DH | 2024-12-31 08:00 | 2025-01-03 17:00
Fitout | COLO 2 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO2 Cell 4 - DH | 2025-01-06 08:00 | 2025-01-10 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO4 Cell 2 | 2025-03-14 08:00 | 2025-03-14 17:00
Fitout | COLO 2 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 4 - DH | 2025-02-10 08:00 | 2025-02-21 17:00
Fitout | COLO 2 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO2 Cell 4 - DH | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO4 Cell 1 - ER | 2025-02-10 08:00 | 2025-02-14 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO4 Cell 2 - ER | 2025-02-26 08:00 | 2025-03-04 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO4 Cell 3 - ER | 2025-03-12 08:00 | 2025-03-18 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO4 Cell 3 | 2025-03-28 08:00 | 2025-03-28 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO4 Cell 4 - ER | 2025-03-24 08:00 | 2025-03-28 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO4 Cell 4 | 2025-04-14 08:00 | 2025-04-14 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO5 Cell 1 - ER | 2024-11-29 08:00 | 2024-12-05 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO5 Cell 2 - ER | 2024-12-06 08:00 | 2024-12-12 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO5 Cell 3 - ER | 2024-12-13 08:00 | 2024-12-19 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO5 Cell 1 | 2025-01-03 08:00 | 2025-01-03 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E6 | Installation of ADP & ATS - COLO5 Cell 4 - ER | 2024-12-27 08:00 | 2025-01-03 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO5 Cell 2 | 2025-01-28 08:00 | 2025-01-28 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E7 | Installation of Mech. Piping and testing - Colo 2 - North | 2024-11-26 08:00 | 2024-12-17 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E7 | Installation of Mech. Piping and testing - Colo 2 - South | 2024-12-18 08:00 | 2025-01-09 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E7 | Installation of Mech. Piping and testing - Colo 3 - North | 2024-12-03 08:00 | 2024-12-23 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO5 Cell 3 | 2025-02-11 08:00 | 2025-02-11 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E7 | Installation of Mech. Piping and testing - Colo 3 - South | 2024-12-03 08:00 | 2024-12-23 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG3 | Interior - L1 AHUs - COLO5 Cell 4 | 2025-02-25 08:00 | 2025-02-25 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E7 | Installation of Mech. Piping and testing - Colo 4 - North | 2024-12-17 08:00 | 2025-01-08 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E7 | Installation of Mech. Piping and testing - Colo 4 - South | 2024-12-17 08:00 | 2025-01-08 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E7 | Installation of Mech. Piping and testing - Colo 5 - Eest | 2024-12-17 08:00 | 2025-01-08 17:00
Fitout | COLO 2 | Ralph Simpson, Crown Core | #F6EBE6 | RC1 | Install screen wall - Colo 2 - North | 2024-12-18 08:00 | 2025-01-16 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E7 | Installation of Mech. Piping and testing - Colo 5 - West | 2024-12-17 08:00 | 2025-01-08 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO2 Cell 1 - ER | 2024-11-29 08:00 | 2024-12-05 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO2 Cell 2 - ER | 2024-12-06 08:00 | 2024-12-12 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO2 Cell 3 - ER | 2024-12-20 08:00 | 2024-12-27 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO2 Cell 4 - ER | 2025-01-07 08:00 | 2025-01-13 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO3 Cell 1 - ER | 2024-12-18 08:00 | 2024-12-24 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO3 Cell 2 - ER | 2025-01-03 08:00 | 2025-01-09 17:00
Fitout | COLO 2 | Ralph Simpson, Crown Core | #F6EBE6 | RC1 | Install screen wall - Colo 2 - South | 2025-01-10 08:00 | 2025-02-06 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO3 Cell 3 - ER | 2025-01-17 08:00 | 2025-01-23 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO3 Cell 4 - ER | 2025-01-31 08:00 | 2025-02-06 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO4 Cell 1 - ER | 2025-02-10 08:00 | 2025-02-14 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO4 Cell 2 - ER | 2025-02-26 08:00 | 2025-03-04 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO4 Cell 3 - ER | 2025-03-12 08:00 | 2025-03-18 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO4 Cell 4 - ER | 2025-03-24 08:00 | 2025-03-28 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO5 Cell 1 - ER | 2024-12-06 08:00 | 2024-12-12 17:00
Fitout | COLO 5 | Ralph Simpson, Crown Core | #F6EBE6 | RC1 | Install screen wall - Colo 5 - West | 2025-01-09 08:00 | 2025-02-05 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO5 Cell 2 - ER | 2024-12-13 08:00 | 2024-12-19 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO5 Cell 3 - ER | 2024-12-20 08:00 | 2024-12-27 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E8 | Installation of MSB - COLO5 Cell 4 - ER | 2024-12-30 08:00 | 2025-01-06 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO2 Cell 1 - ER | 2024-12-04 08:00 | 2024-12-10 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO2 Cell 2 - ER | 2024-12-11 08:00 | 2024-12-17 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO2 Cell 3 - ER | 2025-01-03 08:00 | 2025-01-09 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO2 Cell 4 - ER | 2025-01-17 08:00 | 2025-01-23 17:00
Fitout | COLO 3 | Ralph Simpson, Crown Core | #F6EBE6 | RC1 | Install screen wall - Colo 3 - North | 2024-12-24 08:00 | 2025-01-22 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO3 Cell 1 - ER | 2025-01-24 08:00 | 2025-01-30 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO3 Cell 2 - ER | 2025-01-15 08:00 | 2025-01-21 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO3 Cell 3 - ER | 2025-01-29 08:00 | 2025-02-04 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO3 Cell 4 - ER | 2025-02-12 08:00 | 2025-02-18 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO4 Cell 1 - ER | 2025-02-13 08:00 | 2025-02-19 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO4 Cell 2 - ER | 2025-03-03 08:00 | 2025-03-07 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO4 Cell 3 - ER | 2025-03-17 08:00 | 2025-03-21 17:00
Fitout | COLO 4 | Ralph Simpson, Crown Core | #F6EBE6 | RC1 | Install screen wall - Colo 4 - North | 2025-01-09 08:00 | 2025-02-05 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO4 Cell 4 - ER | 2025-03-31 08:00 | 2025-04-04 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO5 Cell 1 - ER | 2024-11-25 08:00 | 2024-12-02 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO5 Cell 2 - ER | 2024-12-10 08:00 | 2024-12-16 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO5 Cell 3 - ER | 2024-12-24 08:00 | 2024-12-31 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E9 | Installation of UPS Equipment - COLO5 Cell 4 - ER | 2025-01-09 08:00 | 2025-01-15 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO2 Cell 1 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO2 Cell 2 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 3 | Ralph Simpson, Crown Core | #F6EBE6 | RC1 | Install screen wall - Colo 3 - South | 2024-12-24 08:00 | 2025-01-22 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO2 Cell 3 | 2025-01-21 08:00 | 2025-01-21 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO2 Cell 4 | 2025-02-04 08:00 | 2025-02-04 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO3 Cell 1 | 2025-02-05 08:00 | 2025-02-05 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO3 Cell 2 | 2025-02-06 08:00 | 2025-02-06 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO3 Cell 3 | 2025-02-20 08:00 | 2025-02-20 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO3 Cell 4 | 2025-03-06 08:00 | 2025-03-06 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO4 Cell 1 | 2025-02-25 08:00 | 2025-02-25 17:00
Fitout | COLO 4 | Ralph Simpson, Crown Core | #F6EBE6 | RC1 | Install screen wall - Colo 4 - South | 2025-01-09 08:00 | 2025-02-05 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO4 Cell 2 | 2025-03-13 08:00 | 2025-03-13 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO4 Cell 3 | 2025-03-27 08:00 | 2025-03-27 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO4 Cell 4 | 2025-04-11 08:00 | 2025-04-11 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO5 Cell 1 | 2024-12-27 08:00 | 2024-12-27 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO5 Cell 2 | 2025-01-27 08:00 | 2025-01-27 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO5 Cell 3 | 2025-02-10 08:00 | 2025-02-10 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E10 | Interior - L1 Busway - COLO5 Cell 4 | 2025-02-24 08:00 | 2025-02-24 17:00
Fitout | COLO 5 | Ralph Simpson, Crown Core | #F6EBE6 | RC1 | Install screen wall - Colo 5 - East | 2025-01-09 08:00 | 2025-02-05 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO2 Cell 1 | 2025-01-03 08:00 | 2025-01-03 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO2 Cell 2 | 2025-01-03 08:00 | 2025-01-03 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO2 Cell 3 | 2025-01-03 08:00 | 2025-01-03 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO2 Cell 4 | 2025-01-27 08:00 | 2025-01-27 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 1 - MG | 2024-11-06 08:00 | 2024-11-12 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 1 - MG | 2024-11-08 08:00 | 2024-11-14 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO2 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO3 Cell 1 - MG | 2024-12-02 08:00 | 2024-12-03 17:00
Fitout | COLO 3 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO3 Cell 1 - MG | 2024-12-04 08:00 | 2024-12-17 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO3 Cell 1 - MG | 2024-12-26 08:00 | 2024-12-30 12:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO3 Cell 1 - MG | 2024-12-18 08:00 | 2024-12-18 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO3 Cell 1 | 2025-02-03 08:00 | 2025-02-03 17:00
Fitout | COLO 3 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO3 Cell 1 - MG | 2025-01-16 13:00 | 2025-01-28 12:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO2 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 3 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO3 Cell 1 - ER | 2024-11-06 08:00 | 2024-11-19 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO2 Cell 3 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO3 Cell 1 - ER | 2024-11-15 08:00 | 2024-11-21 17:00
Fitout | COLO 3 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO3 Cell 1 - ER | 2024-12-09 08:00 | 2024-12-11 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO2 Cell 4 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO3 Cell 2 | 2025-02-04 08:00 | 2025-02-04 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO3 Cell 3 | 2025-02-05 08:00 | 2025-02-05 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO3 Cell 4 | 2025-02-13 08:00 | 2025-02-13 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO3 Cell 1 - ER | 2025-01-31 08:00 | 2025-02-06 17:00
Fitout | COLO 3 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO3 Cell 1 - ER | 2025-02-07 08:00 | 2025-02-13 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO4 Cell 1 | 2025-02-21 08:00 | 2025-02-21 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO4 Cell 2 | 2025-03-11 08:00 | 2025-03-11 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO3 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 3 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO3 Cell 1 - DH | 2025-01-22 08:00 | 2025-01-28 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO4 Cell 3 | 2025-03-25 08:00 | 2025-03-25 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO3 Cell 1 - DH | 2024-12-18 08:00 | 2024-12-20 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO3 Cell 1 - DH | 2024-12-23 08:00 | 2024-12-30 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO3 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 3 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 1 - DH | 2025-01-29 08:00 | 2025-02-11 17:00
Fitout | COLO 3 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO3 Cell 1 - DH | 2025-02-12 08:00 | 2025-02-18 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO4 Cell 4 | 2025-04-07 08:00 | 2025-04-07 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO5 Cell 1 | 2024-12-13 08:00 | 2024-12-13 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO5 Cell 2 | 2024-12-20 08:00 | 2024-12-20 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO3 Cell 3 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO5 Cell 3 | 2025-01-03 08:00 | 2025-01-03 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO3 Cell 4 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E11 | Interior - L1 MSB - COLO5 Cell 4 | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO2 Cell 1 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO2 Cell 2 | 2025-01-06 08:00 | 2025-01-06 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO4 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO2 Cell 3 | 2025-01-20 08:00 | 2025-01-20 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO4 Cell 2 | 2025-03-27 08:00 | 2025-04-02 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO2 Cell 4 | 2025-02-03 08:00 | 2025-02-03 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO3 Cell 1 | 2025-02-04 08:00 | 2025-02-04 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO3 Cell 2 | 2025-02-05 08:00 | 2025-02-05 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO4 Cell 3 | 2025-04-14 08:00 | 2025-04-18 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO3 Cell 3 | 2025-02-19 08:00 | 2025-02-19 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO4 Cell 4 | 2025-04-29 08:00 | 2025-05-05 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 2 - MG | 2024-11-13 08:00 | 2024-11-19 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 2 - MG | 2024-11-15 08:00 | 2024-11-21 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO5 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO3 Cell 2 - MG | 2024-12-16 08:00 | 2024-12-17 17:00
Fitout | COLO 3 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO3 Cell 2 - MG | 2024-12-18 08:00 | 2025-01-02 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO3 Cell 2 - MG | 2025-01-10 08:00 | 2025-01-14 12:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO3 Cell 2 - MG | 2025-01-03 08:00 | 2025-01-03 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO3 Cell 4 | 2025-03-05 08:00 | 2025-03-05 17:00
Fitout | COLO 3 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO3 Cell 2 - MG | 2025-01-30 13:00 | 2025-02-11 12:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO5 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 3 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO3 Cell 2 - ER | 2024-11-20 08:00 | 2024-12-04 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO5 Cell 3 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO3 Cell 2 - ER | 2024-12-02 08:00 | 2024-12-06 17:00
Fitout | COLO 3 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO3 Cell 2 - ER | 2024-12-23 08:00 | 2024-12-26 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L2 ADP - COLO5 Cell 4 | 2025-03-12 08:00 | 2025-03-18 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO4 Cell 1 | 2025-02-24 08:00 | 2025-02-24 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO4 Cell 2 | 2025-03-12 08:00 | 2025-03-12 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO4 Cell 3 | 2025-03-26 08:00 | 2025-03-26 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO3 Cell 2 - ER | 2025-01-22 08:00 | 2025-01-28 17:00
Fitout | COLO 3 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO3 Cell 2 - ER | 2025-02-19 08:00 | 2025-02-25 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO4 Cell 4 | 2025-04-10 08:00 | 2025-04-10 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO5 Cell 1 | 2024-12-26 08:00 | 2024-12-26 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO2 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 3 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO3 Cell 2 - DH | 2025-02-05 08:00 | 2025-02-11 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO5 Cell 2 | 2025-01-24 08:00 | 2025-01-24 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO3 Cell 2 - DH | 2025-01-03 08:00 | 2025-01-07 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO3 Cell 2 - DH | 2025-01-08 08:00 | 2025-01-14 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO2 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 3 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 2 - DH | 2025-02-12 08:00 | 2025-02-25 17:00
Fitout | COLO 3 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO3 Cell 2 - DH | 2025-02-26 08:00 | 2025-03-04 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO5 Cell 3 | 2025-02-07 08:00 | 2025-02-07 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E12 | Interior - L1 PDUs - COLO5 Cell 4 | 2025-02-21 08:00 | 2025-02-21 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO2 Cell 1 | 2025-01-02 08:00 | 2025-01-02 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO2 Cell 3 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO2 Cell 2 | 2025-01-02 08:00 | 2025-01-02 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO2 Cell 4 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO2 Cell 3 | 2025-01-02 08:00 | 2025-01-02 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO2 Cell 4 | 2025-01-24 08:00 | 2025-01-24 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO3 Cell 1 | 2025-01-31 08:00 | 2025-01-31 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO3 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO3 Cell 2 | 2025-02-03 08:00 | 2025-02-03 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO3 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO3 Cell 3 | 2025-02-04 08:00 | 2025-02-04 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO3 Cell 4 | 2025-02-12 08:00 | 2025-02-12 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO4 Cell 1 | 2025-02-20 08:00 | 2025-02-20 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO3 Cell 3 | 2025-04-09 08:00 | 2025-04-15 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO4 Cell 2 | 2025-03-10 08:00 | 2025-03-10 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO3 Cell 4 | 2025-04-30 08:00 | 2025-05-06 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 3 - MG | 2024-11-20 08:00 | 2024-11-26 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 3 - MG | 2024-11-22 08:00 | 2024-11-29 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO4 Cell 1 | 2025-03-27 08:00 | 2025-04-02 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO3 Cell 3 - MG | 2024-12-31 08:00 | 2025-01-02 17:00
Fitout | COLO 3 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO3 Cell 3 - MG | 2025-01-03 08:00 | 2025-01-16 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO3 Cell 3 - MG | 2025-01-24 08:00 | 2025-01-28 12:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO3 Cell 3 - MG | 2025-01-17 08:00 | 2025-01-17 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO4 Cell 3 | 2025-03-24 08:00 | 2025-03-24 17:00
Fitout | COLO 3 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO3 Cell 3 - MG | 2025-02-13 13:00 | 2025-02-25 12:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO4 Cell 2 | 2025-04-17 08:00 | 2025-04-23 17:00
Fitout | COLO 3 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO3 Cell 3 - ER | 2024-12-05 08:00 | 2024-12-18 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO4 Cell 3 | 2025-05-08 08:00 | 2025-05-14 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO3 Cell 3 - ER | 2024-12-16 08:00 | 2024-12-20 17:00
Fitout | COLO 3 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO3 Cell 3 - ER | 2025-01-08 08:00 | 2025-01-10 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO4 Cell 4 | 2025-05-30 08:00 | 2025-06-05 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO4 Cell 4 | 2025-04-07 08:00 | 2025-04-07 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO5 Cell 1 | 2024-12-03 08:00 | 2024-12-03 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO5 Cell 2 | 2024-12-17 08:00 | 2024-12-17 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO3 Cell 3 - ER | 2025-02-05 08:00 | 2025-02-11 17:00
Fitout | COLO 3 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO3 Cell 3 - ER | 2025-03-12 08:00 | 2025-03-18 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO5 Cell 3 | 2025-01-02 08:00 | 2025-01-02 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E13 | Interior - L1 UPS - COLO5 Cell 4 | 2025-01-02 08:00 | 2025-01-02 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO5 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 3 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO3 Cell 3 - DH | 2025-02-19 08:00 | 2025-02-25 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO2 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO3 Cell 3 - DH | 2025-01-17 08:00 | 2025-01-21 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO3 Cell 3 - DH | 2025-01-22 08:00 | 2025-01-28 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO5 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 3 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 3 - DH | 2025-02-26 08:00 | 2025-03-11 17:00
Fitout | COLO 3 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO3 Cell 3 - DH | 2025-03-19 08:00 | 2025-03-25 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO2 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO2 Cell 3 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO2 Cell 4 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO5 Cell 3 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO3 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L2 AHUs - COLO5 Cell 4 | 2025-04-11 08:00 | 2025-04-17 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO3 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO3 Cell 3 | 2025-04-02 08:00 | 2025-04-08 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO3 Cell 4 | 2025-04-23 08:00 | 2025-04-29 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO2 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO4 Cell 1 | 2025-03-20 08:00 | 2025-03-26 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO2 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO4 Cell 2 | 2025-04-10 08:00 | 2025-04-16 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO4 Cell 3 | 2025-05-01 08:00 | 2025-05-07 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO4 Cell 4 | 2025-05-22 08:00 | 2025-05-29 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO2 Cell 3 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO5 Cell 1 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO2 Cell 4 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO3 Cell 4 - MG | 2024-11-27 08:00 | 2024-12-04 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO3 Cell 4 - MG | 2024-12-02 08:00 | 2024-12-06 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO3 Cell 1 | 2025-04-16 08:00 | 2025-04-22 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO3 Cell 4 - MG | 2025-01-15 08:00 | 2025-01-16 17:00
Fitout | COLO 3 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO3 Cell 4 - MG | 2025-01-17 08:00 | 2025-01-30 17:00
Fitout | COLO 3 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO3 Cell 4 - MG | 2025-02-07 08:00 | 2025-02-11 12:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO3 Cell 4 - MG | 2025-01-31 08:00 | 2025-01-31 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO5 Cell 2 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 3 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO3 Cell 4 - MG | 2025-02-27 13:00 | 2025-03-11 12:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO3 Cell 2 | 2025-04-16 08:00 | 2025-04-22 17:00
Fitout | COLO 3 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO3 Cell 4 - ER | 2024-12-19 08:00 | 2025-01-03 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO3 Cell 3 | 2025-04-16 08:00 | 2025-04-22 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO3 Cell 4 - ER | 2024-12-31 08:00 | 2025-01-07 17:00
Fitout | COLO 3 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO3 Cell 4 - ER | 2025-01-22 08:00 | 2025-01-24 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO3 Cell 4 | 2025-04-30 08:00 | 2025-05-06 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO5 Cell 3 | 2025-03-18 08:00 | 2025-03-24 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E14 | Interior - L2 Busway - COLO5 Cell 4 | 2025-04-04 08:00 | 2025-04-10 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO2 Cell 1 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO3 Cell 4 - ER | 2025-02-19 08:00 | 2025-02-25 17:00
Fitout | COLO 3 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO3 Cell 4 - ER | 2025-04-02 08:00 | 2025-04-08 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO2 Cell 2 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO2 Cell 3 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO4 Cell 1 | 2025-05-27 08:00 | 2025-06-02 17:00
Fitout | COLO 3 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO3 Cell 4 - DH | 2025-03-05 08:00 | 2025-03-11 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO2 Cell 4 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO3 Cell 4 - DH | 2025-01-31 08:00 | 2025-02-04 17:00
Fitout | COLO 3 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO3 Cell 4 - DH | 2025-02-05 08:00 | 2025-02-11 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO4 Cell 2 | 2025-05-19 08:00 | 2025-05-23 17:00
Fitout | COLO 3 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO3 Cell 4 - DH | 2025-03-12 08:00 | 2025-03-25 17:00
Fitout | COLO 3 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO3 Cell 4 - DH | 2025-04-09 08:00 | 2025-04-15 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO3 Cell 1 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO3 Cell 2 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO3 Cell 3 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO4 Cell 3 | 2025-05-19 08:00 | 2025-05-23 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO3 Cell 4 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO4 Cell 4 | 2025-06-03 08:00 | 2025-06-09 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO4 Cell 1 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO4 Cell 2 | 2025-03-20 08:00 | 2025-03-26 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO4 Cell 3 | 2025-04-07 08:00 | 2025-04-11 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO5 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO4 Cell 4 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO5 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO5 Cell 1 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO5 Cell 2 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO5 Cell 3 | 2025-03-04 08:00 | 2025-03-10 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO5 Cell 3 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E15 | Interior - L2 MSB - COLO5 Cell 4 | 2025-03-05 08:00 | 2025-03-11 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG4 | Interior - L3 ADP - COLO5 Cell 4 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 1 - MG | 2024-12-05 08:00 | 2024-12-11 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 1 - MG | 2024-12-06 08:00 | 2024-12-12 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO2 Cell 1 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO4 Cell 1 - MG | 2024-12-30 08:00 | 2024-12-31 17:00
Fitout | COLO 4 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO4 Cell 1 - MG | 2025-01-02 08:00 | 2025-01-15 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO4 Cell 1 - MG | 2025-01-23 08:00 | 2025-01-27 12:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO4 Cell 1 - MG | 2025-01-16 08:00 | 2025-01-16 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO2 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 4 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO4 Cell 1 - MG | 2025-02-12 13:00 | 2025-02-24 12:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO2 Cell 2 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 4 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO4 Cell 1 - ER | 2025-01-06 08:00 | 2025-01-17 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO2 Cell 3 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO4 Cell 1 - ER | 2025-01-13 08:00 | 2025-01-17 17:00
Fitout | COLO 4 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO4 Cell 1 - ER | 2025-02-03 08:00 | 2025-02-05 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO2 Cell 4 | 2025-04-24 08:00 | 2025-04-30 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO2 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO2 Cell 3 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO2 Cell 4 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO4 Cell 1 - ER | 2025-02-20 08:00 | 2025-02-26 17:00
Fitout | COLO 4 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO4 Cell 1 - ER | 2025-03-07 08:00 | 2025-03-13 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO3 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO3 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO3 Cell 1 | 2025-04-30 08:00 | 2025-05-06 17:00
Fitout | COLO 4 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO4 Cell 1 - DH | 2025-02-20 08:00 | 2025-02-26 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO3 Cell 3 | 2025-03-26 08:00 | 2025-04-01 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO4 Cell 1 - DH | 2025-01-20 08:00 | 2025-01-22 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO4 Cell 1 - DH | 2025-01-23 08:00 | 2025-01-29 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO3 Cell 2 | 2025-04-30 08:00 | 2025-05-06 17:00
Fitout | COLO 4 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 1 - DH | 2025-02-27 08:00 | 2025-03-12 17:00
Fitout | COLO 4 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO4 Cell 1 - DH | 2025-03-13 08:00 | 2025-03-19 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO3 Cell 4 | 2025-04-16 08:00 | 2025-04-22 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO4 Cell 1 | 2025-03-13 08:00 | 2025-03-19 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO4 Cell 2 | 2025-04-03 08:00 | 2025-04-09 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO3 Cell 3 | 2025-04-23 08:00 | 2025-04-29 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO4 Cell 3 | 2025-04-24 08:00 | 2025-04-30 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO3 Cell 4 | 2025-05-20 08:00 | 2025-05-27 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO4 Cell 4 | 2025-05-15 08:00 | 2025-05-21 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO5 Cell 1 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO5 Cell 2 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO4 Cell 1 | 2025-06-10 08:00 | 2025-06-16 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO5 Cell 3 | 2025-03-11 08:00 | 2025-03-17 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO4 Cell 2 | 2025-06-03 08:00 | 2025-06-09 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E16 | Interior - L2 PDUs - COLO5 Cell 4 | 2025-03-28 08:00 | 2025-04-03 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO2 Cell 1 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO2 Cell 2 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO4 Cell 3 | 2025-06-03 08:00 | 2025-06-09 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO2 Cell 3 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO4 Cell 4 | 2025-06-20 08:00 | 2025-06-26 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 2 - MG | 2024-12-12 08:00 | 2024-12-18 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 2 - MG | 2024-12-16 08:00 | 2024-12-20 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO5 Cell 1 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO4 Cell 2 - MG | 2025-01-14 08:00 | 2025-01-15 17:00
Fitout | COLO 4 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO4 Cell 2 - MG | 2025-01-16 08:00 | 2025-01-29 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO4 Cell 2 - MG | 2025-02-06 08:00 | 2025-02-10 12:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO4 Cell 2 - MG | 2025-01-30 08:00 | 2025-01-30 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO2 Cell 4 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 4 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO4 Cell 2 - MG | 2025-02-26 13:00 | 2025-03-10 12:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO5 Cell 2 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 4 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO4 Cell 2 - ER | 2025-01-20 08:00 | 2025-01-31 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO5 Cell 3 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO4 Cell 2 - ER | 2025-01-29 08:00 | 2025-02-04 17:00
Fitout | COLO 4 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO4 Cell 2 - ER | 2025-02-19 08:00 | 2025-02-21 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG5 | Interior - L3 AHUs - COLO5 Cell 4 | 2025-04-24 08:00 | 2025-04-30 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO3 Cell 1 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO3 Cell 2 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO3 Cell 3 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO4 Cell 2 - ER | 2025-03-10 08:00 | 2025-03-14 17:00
Fitout | COLO 4 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO4 Cell 2 - ER | 2025-03-28 08:00 | 2025-04-03 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO3 Cell 4 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO4 Cell 1 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 1 - DH | 2024-10-07 08:00 | 2024-10-22 17:00
Fitout | COLO 4 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO4 Cell 2 - DH | 2025-03-10 08:00 | 2025-03-14 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO4 Cell 2 | 2025-03-13 08:00 | 2025-03-19 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO4 Cell 2 - DH | 2025-02-05 08:00 | 2025-02-07 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO4 Cell 2 - DH | 2025-02-10 08:00 | 2025-02-14 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 2 - DH | 2024-10-23 08:00 | 2024-11-07 17:00
Fitout | COLO 4 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 2 - DH | 2025-03-17 08:00 | 2025-03-28 17:00
Fitout | COLO 4 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO4 Cell 2 - DH | 2025-03-31 08:00 | 2025-04-04 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO4 Cell 3 | 2025-03-31 08:00 | 2025-04-04 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO4 Cell 4 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO5 Cell 1 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 3 - DH | 2024-11-08 08:00 | 2024-11-25 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO5 Cell 2 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 4 - DH | 2024-11-26 08:00 | 2024-12-12 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO5 Cell 3 | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E17 | Interior - L2 UPS - COLO5 Cell 4 | 2025-02-26 08:00 | 2025-03-04 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO2 Cell 1 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 1 - DH | 2024-11-06 08:00 | 2024-11-21 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO2 Cell 2 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 2 - DH | 2024-11-22 08:00 | 2024-12-10 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO2 Cell 3 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO2 Cell 4 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO3 Cell 1 | 2025-04-30 08:00 | 2025-05-06 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 3 - DH | 2024-12-11 08:00 | 2024-12-27 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO3 Cell 2 | 2025-04-30 08:00 | 2025-05-06 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO3 Cell 4 - DH | 2024-12-30 08:00 | 2025-01-15 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 3 - MG | 2024-12-19 08:00 | 2024-12-26 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 3 - MG | 2024-12-23 08:00 | 2024-12-30 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 1 - DH | 2025-01-06 08:00 | 2025-01-21 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO4 Cell 3 - MG | 2025-01-28 08:00 | 2025-01-29 17:00
Fitout | COLO 4 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO4 Cell 3 - MG | 2025-01-30 08:00 | 2025-02-12 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO4 Cell 3 - MG | 2025-02-20 08:00 | 2025-02-24 12:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO4 Cell 3 - MG | 2025-02-13 08:00 | 2025-02-13 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO3 Cell 3 | 2025-04-23 08:00 | 2025-04-29 17:00
Fitout | COLO 4 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO4 Cell 3 - MG | 2025-03-12 13:00 | 2025-03-24 12:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 2 - DH | 2025-01-22 08:00 | 2025-02-06 17:00
Fitout | COLO 4 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO4 Cell 3 - ER | 2025-02-03 08:00 | 2025-02-14 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 3 - DH | 2025-02-07 08:00 | 2025-02-24 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO4 Cell 3 - ER | 2025-02-12 08:00 | 2025-02-18 17:00
Fitout | COLO 4 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO4 Cell 3 - ER | 2025-03-05 08:00 | 2025-03-07 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO4 Cell 4 - DH | 2025-02-25 08:00 | 2025-03-12 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO3 Cell 4 | 2025-05-14 08:00 | 2025-05-20 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO4 Cell 1 | 2025-06-10 08:00 | 2025-06-16 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO4 Cell 2 | 2025-06-03 08:00 | 2025-06-09 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO4 Cell 3 - ER | 2025-03-24 08:00 | 2025-03-28 17:00
Fitout | COLO 4 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO4 Cell 3 - ER | 2025-04-18 08:00 | 2025-04-24 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO4 Cell 3 | 2025-06-03 08:00 | 2025-06-09 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO4 Cell 4 | 2025-06-17 08:00 | 2025-06-23 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 1 - DH | 2024-10-02 08:00 | 2024-10-29 17:00
Fitout | COLO 4 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO4 Cell 3 - DH | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO5 Cell 1 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO4 Cell 3 - DH | 2025-02-19 08:00 | 2025-02-21 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO4 Cell 3 - DH | 2025-02-25 08:00 | 2025-03-03 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 2 - DH | 2024-10-30 08:00 | 2024-11-14 17:00
Fitout | COLO 4 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 3 - DH | 2025-04-01 08:00 | 2025-04-14 17:00
Fitout | COLO 4 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO4 Cell 3 - DH | 2025-04-17 08:00 | 2025-04-23 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO5 Cell 2 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO5 Cell 3 | 2025-04-15 08:00 | 2025-04-21 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E18 | Interior - L3 Busway - COLO5 Cell 4 | 2025-04-22 08:00 | 2025-04-28 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 3 - DH | 2024-11-15 08:00 | 2024-12-03 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO2 Cell 1 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO5 Cell 4 - DH | 2024-12-04 08:00 | 2024-12-19 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO2 Cell 2 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO2 Cell 3 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO2 Cell 4 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO2 Cell 1 - MG | 2024-10-16 08:00 | 2024-10-29 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO3 Cell 1 | 2025-04-02 08:00 | 2025-04-08 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO2 Cell 2 - MG | 2024-10-30 08:00 | 2024-11-12 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO3 Cell 2 | 2025-04-02 08:00 | 2025-04-08 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO3 Cell 3 | 2025-04-02 08:00 | 2025-04-08 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO3 Cell 4 | 2025-04-02 08:00 | 2025-04-08 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO2 Cell 3 - MG | 2024-11-13 08:00 | 2024-11-26 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO4 Cell 1 | 2025-05-19 08:00 | 2025-05-23 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO2 Cell 4 - MG | 2024-11-27 08:00 | 2024-12-11 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO4 Cell 4 - MG | 2024-12-27 08:00 | 2025-01-03 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO4 Cell 4 - MG | 2024-12-31 08:00 | 2025-01-07 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO3 Cell 1 - MG | 2024-11-15 08:00 | 2024-11-29 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO4 Cell 4 - MG | 2025-02-11 08:00 | 2025-02-12 17:00
Fitout | COLO 4 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO4 Cell 4 - MG | 2025-02-13 08:00 | 2025-02-26 17:00
Fitout | COLO 4 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO4 Cell 4 - MG | 2025-03-06 08:00 | 2025-03-10 12:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO4 Cell 4 - MG | 2025-02-27 08:00 | 2025-02-27 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO4 Cell 2 | 2025-05-12 08:00 | 2025-05-16 17:00
Fitout | COLO 4 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO4 Cell 4 - MG | 2025-03-26 13:00 | 2025-04-07 12:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO3 Cell 2 - MG | 2024-12-02 08:00 | 2024-12-13 17:00
Fitout | COLO 4 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO4 Cell 4 - ER | 2025-02-17 08:00 | 2025-02-28 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO3 Cell 3 - MG | 2024-12-16 08:00 | 2024-12-30 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO4 Cell 4 - ER | 2025-02-26 08:00 | 2025-03-04 17:00
Fitout | COLO 4 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO4 Cell 4 - ER | 2025-03-19 08:00 | 2025-03-21 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO3 Cell 4 - MG | 2024-12-31 08:00 | 2025-01-14 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO4 Cell 3 | 2025-05-12 08:00 | 2025-05-16 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO4 Cell 4 | 2025-05-19 08:00 | 2025-05-23 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO5 Cell 1 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO4 Cell 4 - ER | 2025-04-07 08:00 | 2025-04-11 17:00
Fitout | COLO 4 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO4 Cell 4 - ER | 2025-05-07 08:00 | 2025-05-13 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO5 Cell 2 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A6 | Closing Construction Access Door - COLO4 Cell 4 - DH | 2025-04-10 08:00 | 2025-04-30 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO5 Cell 3 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO4 Cell 1 - MG | 2024-12-13 08:00 | 2024-12-27 17:00
Fitout | COLO 4 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO4 Cell 4 - DH | 2025-04-10 08:00 | 2025-04-16 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E19 | Interior - L3 MSB - COLO5 Cell 4 | 2025-04-01 08:00 | 2025-04-07 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO4 Cell 4 - DH | 2025-03-05 08:00 | 2025-03-07 17:00
Fitout | COLO 4 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO4 Cell 4 - DH | 2025-03-13 08:00 | 2025-03-19 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO4 Cell 2 - MG | 2024-12-30 08:00 | 2025-01-13 17:00
Fitout | COLO 4 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO4 Cell 4 - DH | 2025-04-17 08:00 | 2025-04-30 17:00
Fitout | COLO 4 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO4 Cell 4 - DH | 2025-05-08 08:00 | 2025-05-14 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO2 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO2 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO2 Cell 3 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO4 Cell 3 - MG | 2025-01-14 08:00 | 2025-01-27 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO2 Cell 4 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO4 Cell 4 - MG | 2025-01-28 08:00 | 2025-02-10 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO3 Cell 1 | 2025-04-09 08:00 | 2025-04-15 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO3 Cell 2 | 2025-04-09 08:00 | 2025-04-15 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO3 Cell 3 | 2025-04-09 08:00 | 2025-04-15 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO5 Cell 1 - MG | 2024-10-16 08:00 | 2024-10-29 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO3 Cell 4 | 2025-04-23 08:00 | 2025-04-29 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO5 Cell 2 - MG | 2024-10-30 08:00 | 2024-11-12 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO4 Cell 1 | 2025-05-27 08:00 | 2025-06-02 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO4 Cell 2 | 2025-05-19 08:00 | 2025-05-23 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO4 Cell 3 | 2025-05-19 08:00 | 2025-05-23 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO5 Cell 3 - MG | 2024-11-13 08:00 | 2024-11-26 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO4 Cell 4 | 2025-05-27 08:00 | 2025-06-02 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG7 | Overhead MEP Installation - COLO5 Cell 4 - MG | 2024-11-27 08:00 | 2024-12-11 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 1 - MG | 2024-10-07 08:00 | 2024-10-11 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 1 - MG | 2024-10-09 08:00 | 2024-10-15 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 1 - DH | 2024-11-27 08:00 | 2024-12-11 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO5 Cell 1 - MG | 2024-11-19 08:00 | 2024-11-20 17:00
Fitout | COLO 5 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO5 Cell 1 - MG | 2024-11-21 08:00 | 2024-12-05 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO5 Cell 1 - MG | 2024-12-13 08:00 | 2024-12-19 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO5 Cell 1 - MG | 2024-12-06 08:00 | 2024-12-06 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO5 Cell 1 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 5 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO5 Cell 1 - MG | 2025-01-09 08:00 | 2025-01-20 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 2 - DH | 2024-12-12 08:00 | 2024-12-26 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Damper in Ceiling (RAD) - COLO 5 Cell 1 - MG | 2025-01-21 08:00 | 2025-01-27 17:00
Fitout | COLO 5 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO5 Cell 1 - ER | 2024-10-02 08:00 | 2024-10-15 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 3 - DH | 2024-12-27 08:00 | 2025-01-10 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO5 Cell 1 - ER | 2024-10-16 08:00 | 2024-10-22 17:00
Fitout | COLO 5 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO5 Cell 1 - ER | 2024-11-06 08:00 | 2024-11-08 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 4 - DH | 2025-01-13 08:00 | 2025-01-24 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO5 Cell 2 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO5 Cell 3 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E20 | Interior - L3 PDUs - COLO5 Cell 4 | 2025-04-08 08:00 | 2025-04-14 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO5 Cell 1 - ER | 2024-12-03 08:00 | 2024-12-09 17:00
Fitout | COLO 5 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO5 Cell 1 - ER | 2025-01-06 08:00 | 2025-01-10 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO2 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO2 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 1 - DH | 2024-12-31 08:00 | 2025-01-14 17:00
Fitout | COLO 5 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO5 Cell 1 - DH | 2024-12-26 08:00 | 2025-01-02 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO2 Cell 3 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO5 Cell 1 - DH | 2024-11-21 08:00 | 2024-11-25 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO5 Cell 1 - DH | 2024-11-26 08:00 | 2024-12-03 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 2 - DH | 2025-01-15 08:00 | 2025-01-28 17:00
Fitout | COLO 5 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 1 - DH | 2025-01-03 08:00 | 2025-01-16 17:00
Fitout | COLO 5 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO5 Cell 1 - DH | 2025-01-17 08:00 | 2025-01-23 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO2 Cell 4 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO3 Cell 1 | 2025-03-26 08:00 | 2025-04-01 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO3 Cell 2 | 2025-03-26 08:00 | 2025-04-01 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 3 - DH | 2025-01-29 08:00 | 2025-02-11 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO3 Cell 3 | 2025-03-26 08:00 | 2025-04-01 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO3 Cell 4 - DH | 2025-02-12 08:00 | 2025-02-25 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO3 Cell 4 | 2025-03-26 08:00 | 2025-04-01 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO4 Cell 1 | 2025-05-12 08:00 | 2025-05-16 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO4 Cell 2 | 2025-03-17 08:00 | 2025-03-21 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 1 - DH | 2025-01-30 08:00 | 2025-02-12 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO4 Cell 3 | 2025-03-31 08:00 | 2025-04-04 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 2 - DH | 2025-02-17 08:00 | 2025-02-28 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO4 Cell 4 | 2025-05-12 08:00 | 2025-05-16 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO5 Cell 1 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO5 Cell 2 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 3 - DH | 2025-03-04 08:00 | 2025-03-17 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO5 Cell 3 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO4 Cell 4 - DH | 2025-03-20 08:00 | 2025-04-02 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 2 - MG | 2024-10-14 08:00 | 2024-10-18 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 2 - MG | 2024-10-16 08:00 | 2024-10-22 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 1 - DH | 2024-12-04 08:00 | 2024-12-17 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Deliver AHU into Mech. Gallery - COLO5 Cell 2 - MG | 2024-11-21 08:00 | 2024-11-22 17:00
Fitout | COLO 5 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO5 Cell 2 - MG | 2024-12-06 08:00 | 2024-12-19 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Placing the AHU - COLO5 Cell 2 - MG | 2024-12-30 08:00 | 2025-01-02 12:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO5 Cell 2 - MG | 2024-12-20 08:00 | 2024-12-20 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E21 | Interior - L3 UPS - COLO5 Cell 4 | 2025-03-25 08:00 | 2025-03-31 17:00
Fitout | COLO 5 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO5 Cell 2 - MG | 2025-01-23 08:00 | 2025-02-03 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 2 - DH | 2025-01-03 08:00 | 2025-01-16 17:00
Fitout | COLO 5 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO5 Cell 2 - ER | 2024-10-16 08:00 | 2024-10-29 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 3 - DH | 2025-01-17 08:00 | 2025-01-30 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO5 Cell 2 - ER | 2024-10-25 08:00 | 2024-10-31 17:00
Fitout | COLO 5 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO5 Cell 2 - ER | 2024-11-20 08:00 | 2024-11-22 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG8 | Overhead MEP Installation (Below Ceiling) - COLO5 Cell 4 - DH | 2025-01-31 08:00 | 2025-02-13 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E22 | L1 GEN - COLO2 | 2024-11-25 08:00 | 2024-11-29 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E23 | L1 UPM - COLO2 | 2024-11-22 08:00 | 2024-11-27 17:00
Fitout | ALL | Gurtz Electric | #D6F2FF | E24 | L1 UTS / UTSR - Site | 2025-01-21 08:00 | 2025-01-21 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO5 Cell 2 - ER | 2025-01-03 08:00 | 2025-01-09 17:00
Fitout | COLO 5 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO5 Cell 2 - ER | 2025-01-27 08:00 | 2025-01-31 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E25 | L1 XFMR - MV- COLO2 | 2024-10-31 08:00 | 2024-11-05 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E25 | L1 XFMR - MV- COLO3 | 2024-11-07 08:00 | 2024-11-12 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO2 Cell 1 - MG | 2024-11-15 08:00 | 2024-12-06 17:00
Fitout | COLO 5 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO5 Cell 2 - DH | 2025-01-24 08:00 | 2025-01-30 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E25 | L1 XFMR - MV- COLO4 | 2024-11-14 08:00 | 2024-11-19 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO5 Cell 2 - DH | 2024-12-20 08:00 | 2024-12-24 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO5 Cell 2 - DH | 2024-12-26 08:00 | 2025-01-02 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO2 Cell 2 - MG | 2024-12-02 08:00 | 2024-12-20 17:00
Fitout | COLO 5 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 2 - DH | 2025-01-31 08:00 | 2025-02-13 17:00
Fitout | COLO 5 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO5 Cell 2 - DH | 2025-02-28 08:00 | 2025-03-06 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E25 | L1 XFMR - MV- COLO5 | 2024-11-21 08:00 | 2024-11-26 17:00
Fitout | ALL | Gurtz Electric | #D6F2FF | E26 | L3 UTS / UTSR - Site | 2025-03-03 08:00 | 2025-03-07 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO2 Cell 1 - MG | 2024-11-26 13:00 | 2024-12-11 12:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO2 Cell 3 - MG | 2024-12-16 08:00 | 2025-01-07 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO2 Cell 2 - MG | 2024-12-11 13:00 | 2024-12-26 12:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO2 Cell 4 - MG | 2024-12-31 08:00 | 2025-01-21 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO2 Cell 3 - MG | 2024-12-26 13:00 | 2025-01-10 12:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO2 Cell 4 - MG | 2025-01-10 13:00 | 2025-01-24 12:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO3 Cell 1 - MG | 2024-12-30 13:00 | 2025-01-14 12:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO3 Cell 1 - MG | 2024-12-18 08:00 | 2025-01-09 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO3 Cell 2 - MG | 2025-01-14 13:00 | 2025-01-28 12:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO3 Cell 2 - MG | 2025-01-03 08:00 | 2025-01-23 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO3 Cell 3 - MG | 2025-01-28 13:00 | 2025-02-11 12:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO3 Cell 4 - MG | 2025-02-11 13:00 | 2025-02-25 12:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO4 Cell 1 - MG | 2025-01-27 13:00 | 2025-02-10 12:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO3 Cell 3 - MG | 2025-01-17 08:00 | 2025-02-06 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO4 Cell 2 - MG | 2025-02-10 13:00 | 2025-02-24 12:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO3 Cell 4 - MG | 2025-01-31 08:00 | 2025-02-20 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 3 - MG | 2024-10-21 08:00 | 2024-10-25 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 3 - MG | 2024-10-23 08:00 | 2024-10-29 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO4 Cell 1 - MG | 2025-01-16 08:00 | 2025-02-05 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO5 Cell 3 - MG | 2024-11-27 08:00 | 2024-11-29 17:00
Fitout | COLO 5 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO5 Cell 3 - MG | 2024-12-20 08:00 | 2025-01-06 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO5 Cell 3 - MG | 2025-01-14 08:00 | 2025-01-16 12:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO5 Cell 3 - MG | 2025-01-07 08:00 | 2025-01-07 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO4 Cell 3 - MG | 2025-02-24 13:00 | 2025-03-10 12:00
Fitout | COLO 5 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO5 Cell 3 - MG | 2025-02-06 08:00 | 2025-02-17 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO4 Cell 2 - MG | 2025-01-30 08:00 | 2025-02-19 17:00
Fitout | COLO 5 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO5 Cell 3 - ER | 2024-10-30 08:00 | 2024-11-12 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO4 Cell 3 - MG | 2025-02-13 08:00 | 2025-03-05 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO5 Cell 3 - ER | 2024-11-08 08:00 | 2024-11-14 17:00
Fitout | COLO 5 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO5 Cell 3 - ER | 2024-12-05 08:00 | 2024-12-09 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO4 Cell 4 - MG | 2025-02-27 08:00 | 2025-03-19 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO4 Cell 4 - MG | 2025-03-10 13:00 | 2025-03-24 12:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO5 Cell 1 - MG | 2024-12-20 08:00 | 2025-01-06 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO5 Cell 2 - MG | 2025-01-07 08:00 | 2025-01-20 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO5 Cell 3 - ER | 2025-01-03 08:00 | 2025-01-09 17:00
Fitout | COLO 5 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO5 Cell 3 - ER | 2025-03-07 08:00 | 2025-03-13 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO5 Cell 3 - MG | 2025-01-21 08:00 | 2025-02-03 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E27 | Piping and Electrical Termination to AHUs - COLO5 Cell 4 - MG | 2025-02-04 08:00 | 2025-02-17 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO5 Cell 1 - MG | 2024-12-06 08:00 | 2024-12-27 17:00
Fitout | COLO 5 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO5 Cell 3 - DH | 2025-02-07 08:00 | 2025-02-13 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E28 | Set the Generator - Colo 2 - North | 2024-10-22 08:00 | 2024-10-28 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO5 Cell 3 - DH | 2025-01-07 08:00 | 2025-01-09 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO5 Cell 3 - DH | 2025-01-10 08:00 | 2025-01-16 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO5 Cell 2 - MG | 2024-12-20 08:00 | 2025-01-13 17:00
Fitout | COLO 5 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 3 - DH | 2025-02-14 08:00 | 2025-02-27 17:00
Fitout | COLO 5 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO5 Cell 3 - DH | 2025-03-14 08:00 | 2025-03-20 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E28 | Set the Generator - Colo 2 - South | 2024-10-01 08:00 | 2024-10-07 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E28 | Set the Generator - Colo 3 - North | 2024-10-29 08:00 | 2024-11-04 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E28 | Set the Generator - Colo 3 - South | 2024-10-08 08:00 | 2024-10-14 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO5 Cell 3 - MG | 2025-01-07 08:00 | 2025-01-27 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E28 | Set the Generator - Colo 4 - North | 2024-11-05 08:00 | 2024-11-11 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG9 | Post Wall Overhead MEP - COLO5 Cell 4 - MG | 2025-01-21 08:00 | 2025-02-10 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E28 | Set the Generator - Colo 4 - South | 2024-10-15 08:00 | 2024-10-21 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E28 | Set the Generator - Colo 5 - East | 2024-09-20 08:00 | 2024-09-26 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E28 | Set the Generator - Colo 5 - West | 2024-11-12 08:00 | 2024-11-18 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 1 - ER | 2024-10-23 08:00 | 2024-11-05 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E29 | Set the MV Gear - Colo 2 - North | 2024-10-24 08:00 | 2024-10-30 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 2 - ER | 2024-11-06 08:00 | 2024-11-19 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E29 | Set the MV Gear - Colo 2 - South | 2024-10-03 08:00 | 2024-10-09 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E29 | Set the MV Gear - Colo 3 - North | 2024-10-31 08:00 | 2024-11-06 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E29 | Set the MV Gear - Colo 3 - South | 2024-10-10 08:00 | 2024-10-16 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 3 - ER | 2024-11-20 08:00 | 2024-12-04 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E29 | Set the MV Gear - Colo 4 - North | 2024-11-07 08:00 | 2024-11-13 17:00
Fitout | COLO 2 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 4 - ER | 2024-12-05 08:00 | 2024-12-18 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO5 Cell 4 - MG | 2024-10-28 08:00 | 2024-11-01 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G1 | Install Dampers and actuators at Louvers - Lower level (OA) - COLO5 Cell 4 - MG | 2024-10-30 08:00 | 2024-11-05 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 1 - ER | 2024-11-22 08:00 | 2024-12-06 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G2 | Deliver AHU into Mech. Gallery - COLO5 Cell 4 - MG | 2024-12-12 08:00 | 2024-12-13 17:00
Fitout | COLO 5 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO5 Cell 4 - MG | 2025-01-07 08:00 | 2025-01-20 17:00
Fitout | COLO 5 | Great Lakes Plumbing & Heating | #D6F2FF | G3 | Placing the AHU - COLO5 Cell 4 - MG | 2025-01-28 08:00 | 2025-01-30 12:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A1 | Layout Ceiling and install Pencile Rod - COLO5 Cell 4 - MG | 2025-01-21 08:00 | 2025-01-21 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E29 | Set the MV Gear - Colo 4 - South | 2024-10-17 08:00 | 2024-10-23 17:00
Fitout | COLO 5 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A7 | Install ceiling and Light Fittings - COLO5 Cell 4 - MG | 2025-02-20 08:00 | 2025-03-03 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 2 - ER | 2024-12-09 08:00 | 2024-12-20 17:00
Fitout | COLO 5 | All-Tech Decorating, Anning Johnson | #D6F2FF | TA1 | Install Walls and Primer Paint - COLO5 Cell 4 - ER | 2024-11-13 08:00 | 2024-11-26 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 3 - ER | 2024-12-23 08:00 | 2025-01-07 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A2 | Install Upper Screens - COLO5 Cell 4 - ER | 2024-11-22 08:00 | 2024-11-29 17:00
Fitout | COLO 5 | Anning-Johnson, Gurtz Electric | #EBBEA4 | A8 | Install Ceiling - COLO5 Cell 4 - ER | 2024-12-19 08:00 | 2024-12-23 17:00
Fitout | COLO 3 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO3 Cell 4 - ER | 2025-01-08 08:00 | 2025-01-21 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E29 | Set the MV Gear - Colo 5 - East | 2024-09-24 08:00 | 2024-09-30 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E29 | Set the MV Gear - Colo 5 - West | 2024-11-14 08:00 | 2024-11-20 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway - COLO2 Cell 2 - DH | 2025-01-21 08:00 | 2025-02-10 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A3 | Door Frame Installation - COLO5 Cell 4 - ER | 2025-01-16 08:00 | 2025-01-22 17:00
Fitout | COLO 5 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO5 Cell 4 - ER | 2025-03-21 08:00 | 2025-03-27 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway - COLO2 Cell 3 - DH | 2025-02-11 08:00 | 2025-03-03 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A6 | Closing Construction Access Door - COLO5 Cell 4 - DH | 2025-02-21 08:00 | 2025-03-13 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway - COLO2 Cell 4 - DH | 2025-03-04 08:00 | 2025-03-24 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 1 - ER | 2025-01-20 08:00 | 2025-01-31 17:00
Fitout | COLO 5 | Interior Systems, Gurtz Electric | #FF9494 | S1 | HAC install and Rise - COLO5 Cell 4 - DH | 2025-02-21 08:00 | 2025-02-27 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway - COLO3 Cell 2 - DH | 2025-02-12 08:00 | 2025-03-04 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A4 | Security Screen Installation - COLO5 Cell 4 - DH | 2025-01-21 08:00 | 2025-01-23 17:00
Fitout | COLO 5 | Anning-Johnson | #96CEFF | A5 | Ceiling Grid and Tile - COLO5 Cell 4 - DH | 2025-01-24 08:00 | 2025-01-30 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 2 - ER | 2025-02-05 08:00 | 2025-02-18 17:00
Fitout | COLO 5 | Everon, Gurtz Electric | #D6F2FF | VE1 | Install Low Voltage Wiring and Fiber Optic - COLO5 Cell 4 - DH | 2025-02-28 08:00 | 2025-03-13 17:00
Fitout | COLO 5 | All-Tech, Douglas Flooring, Scout | #D6F2FF | TD1 | Finishes and Signage - COLO5 Cell 4 - DH | 2025-03-28 08:00 | 2025-04-03 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway - COLO3 Cell 3 - DH | 2025-03-05 08:00 | 2025-03-25 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway - COLO3 Cell 4 - DH | 2025-03-26 08:00 | 2025-04-15 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway - COLO4 Cell 2 - DH | 2025-03-13 08:00 | 2025-04-02 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 3 - ER | 2025-02-19 08:00 | 2025-03-04 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway - COLO4 Cell 3 - DH | 2025-04-03 08:00 | 2025-04-23 17:00
Fitout | COLO 4 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO4 Cell 4 - ER | 2025-03-05 08:00 | 2025-03-18 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway - COLO4 Cell 4 - DH | 2025-04-24 08:00 | 2025-05-14 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway - COLO5 Cell 3 - DH | 2025-02-14 08:00 | 2025-03-06 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway - COLO5 Cell 4 - DH | 2025-03-07 08:00 | 2025-03-27 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 1 - ER | 2024-10-23 08:00 | 2024-11-05 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway- COLO2 Cell 1 - DH | 2024-12-19 08:00 | 2025-01-03 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 2 - ER | 2024-11-06 08:00 | 2024-11-19 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway- COLO3 Cell 1 - DH | 2025-01-22 08:00 | 2025-02-04 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway- COLO4 Cell 1 - DH | 2025-02-20 08:00 | 2025-03-05 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway- COLO5 Cell 1 - DH | 2024-12-26 08:00 | 2025-01-09 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 3 - ER | 2024-11-20 08:00 | 2024-12-04 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E30 | Termination at PDU & Busway- COLO5 Cell 2 - DH | 2025-02-14 08:00 | 2025-02-27 17:00
Fitout | COLO 5 | Gurtz Electric & Great Lakes Plumbing and Heating | #D6F2FF | EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO5 Cell 4 - ER | 2024-12-05 08:00 | 2024-12-18 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E31 | Wire pulling and termination for MSB - Colo 5 - West | 2024-12-17 08:00 | 2025-01-08 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E31 | Wire pulling and termination for MSB - Colo 2 - North | 2024-11-26 08:00 | 2024-12-17 17:00
Fitout | COLO 2 | Gurtz Electric | #D6F2FF | E31 | Wire pulling and termination for MSB - Colo 2 - South | 2024-11-26 08:00 | 2024-12-17 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E31 | Wire pulling and termination for MSB - Colo 3 - North | 2024-12-03 08:00 | 2024-12-23 17:00
Fitout | COLO 3 | Gurtz Electric | #D6F2FF | E31 | Wire pulling and termination for MSB - Colo 3 - South | 2024-12-03 08:00 | 2024-12-23 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E31 | Wire pulling and termination for MSB - Colo 4 - North | 2024-12-17 08:00 | 2025-01-08 17:00
Fitout | COLO 4 | Gurtz Electric | #D6F2FF | E31 | Wire pulling and termination for MSB - Colo 4 - South | 2024-12-17 08:00 | 2025-01-08 17:00
Fitout | COLO 5 | Gurtz Electric | #D6F2FF | E31 | Wire pulling and termination for MSB - Colo 5 - East | 2024-12-17 08:00 | 2025-01-08 17:00

## CFA - Schedule
|  | 2024 | 2024 | [84 empty] | 2025
|  | Oct | Oct | [23 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May
|  | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01
phase | location | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu
Fitout | ALL | Jan 21 Tue: E24; Mar 03 Mon: E26; Mar 04 Tue: E26; Mar 05 Wed: E26; Mar 06 Thu: E26; Mar 07 Fri: E26
| COLO 2 | G1 | G1 | G1 | G1 | G1 |  |  |  |  | A4 | A4 | A4 | A4 | A4 | A4 | A4 |  | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E25 | E25 | E25 | E25 | E25 | E25 | A8 | A8 | A8 | [6 empty] | A1 |  |  |  |  | A3 | A3 | A3 | A3 | A3 | A3 | A3 |  |  | E6 | E6 | E6 | E6 | E6 | E6 | E6 | [7 empty] | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | [6 empty] | E13 | A5 | A5 | A5 | A5 | A5 | A5 | A5 |  |  |  |  | TD1 | TD1 | TD1 | TD1 | TD1 | TD1 | TD1 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | [14 empty] | E17 | E17 | E17 | E17 | E17 | E17 | E17 | E15 | E15 | E15 | E15 | E15 | E15 | E15 | E16 | E16 | E16 | E16 | E16 | E16 | E16 | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E21 | E21 | E21 | E21 | E21 | E21 | E21 | E19 | E19 | E19 | E19 | E19 | E19 | E19 | E20 | E20 | E20 | E20 | E20 | E20 | E20 | E18 | E18 | E18 | E18 | E18 | E18 | E18
[17 empty] | E28 | E28 | E28 | E28 | E28 | E28 | E28 |  |  | E5 | E5 | E5 | E5 | E5 | E5 | E5 | [8 empty] | A2 | A2 | A2 | A2 | A2 | [5 empty] | E22 | E22 | E22 | E22 | E22 |  |  |  |  | E9 | E9 | E9 | E9 | E9 | E9 | E9 | [7 empty] | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | [60 empty] | EG4 | EG4 | EG4 | EG4 | EG4 | EG4 | EG4 | [7 empty] | EG5 | EG5 | EG5 | EG5 | EG5 | EG5 | EG5
[5 empty] | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 |  | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | [7 empty] | E23 | E23 | E23 | E23 | E23 | E23 |  | E8 | E8 | E8 | E8 | E8 | E8 | E8 | [13 empty] | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | [7 empty] | E11 |  |  | E12 | E10 | EG3
|  | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | [13 empty] | E3 | E3 | E3 | E3 | E3 | E3 | E3 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | [18 empty] | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2
[11 empty] | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | G2 | G2 | [25 empty] | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | [19 empty] | EG2
[52 empty] | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1
[45 empty] | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | [23 empty] | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1
[48 empty] | G3 | G3 | G3 | G3 | G3 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8
[41 empty] | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9
| COLO 3 | Oct 29 Tue: E28; Oct 30 Wed: E28; Oct 31 Thu: E28; Nov 01 Fri: E28; Nov 02 Sat: E28; Nov 03 Sun: E28; Nov 04 Mon: E28; Nov 07 Thu: E25; Nov 08 Fri: E25; Nov 09 Sat: E25; Nov 10 Sun: E25; Nov 11 Mon: E25; Nov 12 Tue: E25; Nov 15 Fri: A2; Nov 16 Sat: A2; Nov 17 Sun: A2; Nov 18 Mon: A2; Nov 19 Tue: A2; Nov 20 Wed: A2; Nov 21 Thu: A2; Nov 25 Mon: E3; Nov 26 Tue: E3; Nov 27 Wed: E3; Nov 28 Thu: E3; Nov 29 Fri: E3; Nov 30 Sat: E3; Dec 01 Sun: E3; Dec 02 Mon: E3; Dec 09 Mon: A8; Dec 10 Tue: A8; Dec 11 Wed: A8; Dec 18 Wed: A1; Dec 23 Mon: A5; Dec 24 Tue: A5; Dec 25 Wed: A5; Dec 26 Thu: A5; Dec 27 Fri: A5; Dec 28 Sat: A5; Dec 29 Sun: A5; Dec 30 Mon: A5; Jan 02 Thu: E6; Jan 03 Fri: E6; Jan 04 Sat: E6; Jan 05 Sun: E6; Jan 06 Mon: E6; Jan 07 Tue: E6; Jan 08 Wed: E6; Jan 16 Thu: A7; Jan 17 Fri: A7; Jan 18 Sat: A7; Jan 19 Sun: A7; Jan 20 Mon: A7; Jan 21 Tue: A7; Jan 22 Wed: A7; Jan 23 Thu: A7; Jan 24 Fri: A7; Jan 25 Sat: A7; Jan 26 Sun: A7; Jan 27 Mon: A7; Jan 28 Tue: A7; Jan 31 Fri: A3; Feb 01 Sat: A3; Feb 02 Sun: A3; Feb 03 Mon: A3; Feb 04 Tue: A3; Feb 05 Wed: A3; Feb 06 Thu: A3; Feb 07 Fri: TD1; Feb 08 Sat: TD1; Feb 09 Sun: TD1; Feb 10 Mon: TD1; Feb 11 Tue: TD1; Feb 12 Wed: TD1; Feb 13 Thu: TD1; Feb 25 Tue: E17; Feb 26 Wed: E17; Feb 27 Thu: E17; Feb 28 Fri: E17; Mar 01 Sat: E17; Mar 02 Sun: E17; Mar 03 Mon: E17; Mar 04 Tue: E15; Mar 05 Wed: E15; Mar 06 Thu: E15; Mar 07 Fri: E15; Mar 08 Sat: E15; Mar 09 Sun: E15; Mar 10 Mon: E15; Mar 11 Tue: E16; Mar 12 Wed: E16; Mar 13 Thu: E16; Mar 14 Fri: E16; Mar 15 Sat: E16; Mar 16 Sun: E16; Mar 17 Mon: E16; Mar 18 Tue: E14; Mar 19 Wed: E14; Mar 20 Thu: E14; Mar 21 Fri: E14; Mar 22 Sat: E14; Mar 23 Sun: E14; Mar 24 Mon: E14; Mar 26 Wed: E21; Mar 27 Thu: E21; Mar 28 Fri: E21; Mar 29 Sat: E21; Mar 30 Sun: E21; Mar 31 Mon: E21; Apr 01 Tue: E21; Apr 02 Wed: E19; Apr 03 Thu: E19; Apr 04 Fri: E19; Apr 05 Sat: E19; Apr 06 Sun: E19; Apr 07 Mon: E19; Apr 08 Tue: E19; Apr 09 Wed: E20; Apr 10 Thu: E20; Apr 11 Fri: E20; Apr 12 Sat: E20; Apr 13 Sun: E20; Apr 14 Mon: E20; Apr 15 Tue: E20
[26 empty] | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | [8 empty] | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | [11 empty] | A4 | A4 | A4 | [5 empty] | G3 | G3 | G3 | G3 | G3 | [13 empty] | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 |  |  | E11 | E12 | E10 | EG3 | [5 empty] | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | [6 empty] | EG4 | EG4 | EG4 | EG4 | EG4 | EG4 | EG4 | [7 empty] | EG5 | EG5 | EG5 | EG5 | EG5 | EG5 | EG5
[12 empty] | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | [8 empty] | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 |  |  |  | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | [6 empty] | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | [9 empty] | E9 | E9 | E9 | E9 | E9 | E9 | E9 | E13 |  |  |  | EG2
[32 empty] | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | [11 empty] | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | [7 empty] | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | [7 empty] | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2
[32 empty] | G1 | G1 | G1 | G1 | G1 | G1 | G1 | [19 empty] | G2 | G2 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | E8 | E8 | E8 | E8 | E8 | E8 | E8 | [28 empty] | S1 | S1 | S1 | S1 | S1 | S1 | S1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1
[72 empty] | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1
[74 empty] | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9
[80 empty] | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1
| COLO 4 | Nov 05 Tue: E28; Nov 06 Wed: E28; Nov 07 Thu: E28; Nov 08 Fri: E28; Nov 09 Sat: E28; Nov 10 Sun: E28; Nov 11 Mon: E28; Nov 14 Thu: E25; Nov 15 Fri: E25; Nov 16 Sat: E25; Nov 17 Sun: E25; Nov 18 Mon: E25; Nov 19 Tue: E25; Dec 10 Tue: E3; Dec 11 Wed: E3; Dec 12 Thu: E3; Dec 13 Fri: E3; Dec 14 Sat: E3; Dec 15 Sun: E3; Dec 16 Mon: E3; Dec 17 Tue: E31; Dec 18 Wed: E31; Dec 19 Thu: E31; Dec 20 Fri: E31; Dec 21 Sat: E31; Dec 22 Sun: E31; Dec 23 Mon: E31; Dec 24 Tue: E31; Dec 25 Wed: E31; Dec 26 Thu: E31; Dec 27 Fri: E31; Dec 28 Sat: E31; Dec 29 Sun: E31; Dec 30 Mon: E31; Dec 31 Tue: E31; Jan 01 Wed: E31; Jan 02 Thu: E31; Jan 03 Fri: E31; Jan 04 Sat: E31; Jan 05 Sun: E31; Jan 06 Mon: E31; Jan 07 Tue: E31; Jan 08 Wed: E31; Jan 16 Thu: A1; Jan 20 Mon: A4; Jan 21 Tue: A4; Jan 22 Wed: A4; Jan 23 Thu: A5; Jan 24 Fri: A5; Jan 25 Sat: A5; Jan 26 Sun: A5; Jan 27 Mon: A5; Jan 28 Tue: A5; Jan 29 Wed: A5; Feb 03 Mon: A8; Feb 04 Tue: A8; Feb 05 Wed: A8; Feb 10 Mon: E6; Feb 11 Tue: E6; Feb 12 Wed: E6; Feb 13 Thu: E6; Feb 14 Fri: E6; Feb 20 Thu: A3; Feb 21 Fri: A3; Feb 22 Sat: A3; Feb 23 Sun: A3; Feb 24 Mon: A3; Feb 25 Tue: A3; Feb 26 Wed: A3; Mar 04 Tue: E15; Mar 05 Wed: E15; Mar 06 Thu: E15; Mar 07 Fri: E15; Mar 08 Sat: E15; Mar 09 Sun: E15; Mar 10 Mon: E15; Mar 13 Thu: E16; Mar 14 Fri: E16; Mar 15 Sat: E16; Mar 16 Sun: E16; Mar 17 Mon: E16; Mar 18 Tue: E16; Mar 19 Wed: E16; Mar 20 Thu: E14; Mar 21 Fri: E14; Mar 22 Sat: E14; Mar 23 Sun: E14; Mar 24 Mon: E14; Mar 25 Tue: E14; Mar 26 Wed: E14; Mar 27 Thu: EG5; Mar 28 Fri: EG5; Mar 29 Sat: EG5; Mar 30 Sun: EG5; Mar 31 Mon: EG5; Apr 01 Tue: EG5; Apr 02 Wed: EG5; Apr 10 Thu: A6; Apr 11 Fri: A6; Apr 12 Sat: A6; Apr 13 Sun: A6; Apr 14 Mon: A6; Apr 15 Tue: A6; Apr 16 Wed: A6; Apr 17 Thu: A6; Apr 18 Fri: A6; Apr 19 Sat: A6; Apr 20 Sun: A6; Apr 21 Mon: A6; Apr 22 Tue: A6; Apr 23 Wed: A6; Apr 24 Thu: A6; Apr 25 Fri: A6; Apr 26 Sat: A6; Apr 27 Sun: A6; Apr 28 Mon: A6; Apr 29 Tue: A6; Apr 30 Wed: A6
[33 empty] | E29 | E29 | E29 | E29 | E29 | E29 | E29 | E5 | E5 | E5 | E5 | E5 | E5 | E5 | [14 empty] | G1 | G1 | G1 | G1 | G1 | G1 | G1 | [5 empty] | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 |  |  |  |  | A2 | A2 | A2 | A2 | A2 | [9 empty] | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 |  | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | E10 | EG3 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30
[19 empty] | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | E4 | [29 empty] | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 |  |  | G2 | G2 |  | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 |  |  |  |  | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | [9 empty] | E8 | E8 | E8 | E8 | E8 |  |  |  |  | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1
[93 empty] | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 | EG6 |  | G3 | G3 | G3 | G3 | G3 |  |  | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | E9 | E9 | E9 | E9 | E9 | E9 | E9 | E13 | E11 |  |  | E12 | E17 | E17 | E17 | E17 | E17 | E17 | E17 | [7 empty] | EG4 | EG4 | EG4 | EG4 | EG4 | EG4 | EG4
[103 empty] | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2
[96 empty] | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | [18 empty] | EG2 | [10 empty] | TD1 | TD1 | TD1 | TD1 | TD1 | TD1 | TD1
[138 empty] | S1 | S1 | S1 | S1 | S1 | S1 | S1
| COLO 5 |  |  | E5 | E5 | E5 | E5 | E5 | E5 | E5 | A2 | A2 | A2 | A2 | A2 | A2 | A2 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | EG10 | A8 | A8 | A8 | [10 empty] | G2 | G2 | A4 | A4 | A4 | A4 | A4 | A5 | A5 | A5 | A5 | A5 | A5 | A5 | A5 |  |  | A1 | [6 empty] | E11 |  |  | EG2 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | E1 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | A7 | [31 empty] | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 | A6 |  |  |  |  | E14 | E14 | E14 | E14 | E14 | E14 | E14 | E21 | E21 | E21 | E21 | E21 | E21 | E21 | E19 | E19 | E19 | E19 | E19 | E19 | E19 | E20 | E20 | E20 | E20 | E20 | E20 | E20 | E18 | E18 | E18 | E18 | E18 | E18 | E18
|  | G1 | G1 | G1 | G1 | G1 |  |  |  |  | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | EG7 | [22 empty] | E25 | E25 | E25 | E25 | E25 | E25 | [6 empty] | A3 | A3 | A3 | A3 | A3 | A3 | A3 | E3 | E3 | E3 | E3 | E3 | E3 | E3 | [9 empty] | E12 | E10 | [6 empty] | EG3 | [5 empty] | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | RC1 | [19 empty] | E17 | E17 | E17 | E17 | E17 | E17 | E17 | E15 | E15 | E15 | E15 | E15 | E15 | E15 | E16 | E16 | E16 | E16 | E16 | E16 | E16 | [7 empty] | EG5 | EG5 | EG5 | EG5 | EG5 | EG5 | EG5
[37 empty] | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 | EG1 |  |  | E9 | E9 | E9 | E9 | E9 | E9 | E9 | E9 | E13 |  |  | E8 | E8 | E8 | E8 | E8 | E8 | E8 | G3 | G3 | G3 | G3 | G3 | G3 | G3 | [6 empty] | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | E2 | [28 empty] | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 | E30 |  |  |  |  | EG4 | EG4 | EG4 | EG4 | EG4 | EG4 | EG4
[55 empty] | E6 | E6 | E6 | E6 | E6 | E6 | E6 | [14 empty] | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27 | E27
[47 empty] | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | TA1 | [11 empty] | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31 | E31
[73 empty] | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7 | E7
[60 empty] | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | EG8 | [8 empty] | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 |  |  |  | TD1 | TD1 | TD1 | TD1 | TD1
[62 empty] | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | EG9 | [6 empty] | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1 | VE1

## CFA - Legends
Fitout
All-Tech Decorating, Anning Johnson
TA1 | Install Walls and Primer Paint - COLO2 Cell 1 - MG
All-Tech, Douglas Flooring, Scout
TD1 | Finishes and Signage - COLO2 Cell 1 - DH
Anning-Johnson
A1 | Layout Ceiling and install Pencile Rod - COLO2 Cell 1 - MG
A2 | Security Screen Installation - COLO2 Cell 1 - DH
A3 | Ceiling Grid and Tile - COLO2 Cell 1 - DH
A4 | Install Upper Screens - COLO2 Cell 1 - ER
A5 | Door Frame Installation - COLO2 Cell 1 - ER
A6 | Closing Construction Access Door - COLO4 Cell 4 - DH
Anning-Johnson, Gurtz Electric
A7 | Install ceiling and Light Fittings - COLO2 Cell 1 - MG
A8 | Install Ceiling - COLO2 Cell 1 - ER
Everon, Gurtz Electric
VE1 | Install Low Voltage Wiring and Fiber Optic - COLO2 Cell 1 - DH
Great Lakes Plumbing & Heating
G1 | Install Dampers and actuators at Louvers - Upper level (RED) - COLO2 Cell 1 - MG
G2 | Deliver AHU into Mech. Gallery - COLO2 Cell 1 - MG
G3 | Placing the AHU - COLO2 Cell 1 - MG
Gurtz Electric
E1 | Cable Pulling at Elec. Equipment - COLO2 Cell 1 - ER
E10 | Interior - L1 Busway - COLO2 Cell 1
E11 | Interior - L1 MSB - COLO2 Cell 1
E12 | Interior - L1 PDUs - COLO2 Cell 1
E13 | Interior - L1 UPS - COLO2 Cell 1
E14 | Interior - L2 Busway - COLO2 Cell 1
E15 | Interior - L2 MSB - COLO2 Cell 1
E16 | Interior - L2 PDUs - COLO2 Cell 1
E17 | Interior - L2 UPS - COLO2 Cell 1
E18 | Interior - L3 Busway - COLO2 Cell 1
E19 | Interior - L3 MSB - COLO2 Cell 1
E2 | Cable Pulling at PDU & Busway - COLO2 Cell 1 - DH
E20 | Interior - L3 PDUs - COLO2 Cell 1
E21 | Interior - L3 UPS - COLO2 Cell 1
E22 | L1 GEN - COLO2
E23 | L1 UPM - COLO2
E24 | L1 UTS / UTSR - Site
E25 | L1 XFMR - MV- COLO2
E26 | L3 UTS / UTSR - Site
E27 | Piping and Electrical Termination to AHUs - COLO2 Cell 1 - MG
E28 | Set the Generator - Colo 2 - North
E29 | Set the MV Gear - Colo 2 - North
E3 | Install Generator - Colo 2 - North
E30 | Termination at PDU & Busway - COLO2 Cell 2 - DH
E31 | Wire pulling and termination for MSB - Colo 2 - North
E4 | Install MEP raceway conduit and piping - Colo 2 - North
E5 | Install MV Gear - Colo 2 - North
E6 | Installation of ADP & ATS - COLO2 Cell 1 - ER
E7 | Installation of Mech. Piping and testing - Colo 2 - North
E8 | Installation of MSB - COLO2 Cell 1 - ER
E9 | Installation of UPS Equipment - COLO2 Cell 1 - ER
Gurtz Electric & Great Lakes Plumbing and Heating
EG1 | Below Ceiling MEP Rough In - COLO2 Cell 1 - ER
EG10 | Sprinklers and Overhead MEP (Above Ceiling) - COLO2 Cell 1 - ER
EG2 | Interior - L1 ADP - COLO2 Cell 1
EG3 | Interior - L1 AHUs - COLO2 Cell 1
EG4 | Interior - L2 ADP - COLO2 Cell 1
EG5 | Interior - L2 AHUs - COLO2 Cell 1
EG6 | Overhead MEP and Hangers (Above Ceiling) - COLO2 Cell 1 - DH
EG7 | Overhead MEP Installation - COLO2 Cell 1 - MG
EG8 | Overhead MEP Installation (Below Ceiling) - COLO2 Cell 1 - DH
EG9 | Post Wall Overhead MEP - COLO2 Cell 1 - MG
Interior Systems, Gurtz Electric
S1 | HAC install and Rise - COLO2 Cell 1 - DH
Ralph Simpson, Crown Core
RC1 | Install screen wall - Colo 2 - North